## Sheet1
ID | TaskType | Label | PlannedStart | PlannedEnd | ActualStart | ActualEnd | Float | Status | File | Cluster_ID | ClusterID_File
A184220 | TT_Task | Transit Time | 20/08/2021 | 20/08/2021 | 15/08/2021 | 17/08/2021 | 0 | TK_Complete | 1653707999 | 1 | 1653707999_1
A184230 | TT_Task | Tooling Ready for Production | 01/06/2021 | 05/07/2021 | 12/04/2021 | 09/06/2021 | 0 | TK_Complete | 1653707999 | 2 | 1653707999_2
A184240 | TT_Task | Raw material Received at supplier end | 10/02/2021 | 13/04/2021 | 09/01/2021 | 10/03/2021 | 0 | TK_Complete | 1653707999 | 3 | 1653707999_3
A188410 | TT_Task | Production Lead Time | 10/06/2021 | 23/06/2021 | 10/06/2021 | 12/08/2021 | 0 | TK_Complete | 1653707999 | 4 | 1653707999_4
A188420 | TT_Task | FAI / ICR | 16/08/2021 | 19/08/2021 | 13/08/2021 | 14/08/2021 | 0 | TK_Complete | 1653707999 | 5 | 1653707999_5
A188470 | TT_Task | Tooling Ready for Production | 01/06/2021 | 05/07/2021 | 28/06/2021 | 01/07/2021 | 0 | TK_Complete | 1653707999 | 2 | 1653707999_2
A188480 | TT_Task | Raw material Received | 10/02/2021 | 13/04/2021 | 21/01/2021 | 31/03/2021 | 0 | TK_Complete | 1653707999 | 6 | 1653707999_6
A188500 | TT_Task | Production Lead Time | 16/08/2021 | 31/08/2021 | 01/07/2021 | 19/08/2021 | 0 | TK_Complete | 1653707999 | 4 | 1653707999_4
A188510 | TT_Task | FAI | 23/08/2021 | 24/08/2021 | 19/08/2021 | 19/08/2021 | 0 | TK_Complete | 1653707999 | 7 | 1653707999_7
A188520 | TT_Task | Transit Time | 25/08/2021 | 25/08/2021 | 20/08/2021 | 20/08/2021 | 0 | TK_Complete | 1653707999 | 1 | 1653707999_1
A188570 | TT_Task | Tooling Ready for Production | 30/09/2021 | 20/10/2021 | 16/09/2021 | 20/09/2021 | 0 | TK_Complete | 1653707999 | 2 | 1653707999_2
A188580 | TT_Task | Raw material Received | 10/02/2021 | 13/04/2021 | 21/01/2021 | 16/09/2021 | 0 | TK_Complete | 1653707999 | 6 | 1653707999_6
A188600 | TT_Task | Production Lead Time | 21/10/2021 | 10/11/2021 | 21/09/2021 | 05/10/2021 | 0 | TK_Complete | 1653707999 | 4 | 1653707999_4
A188610 | TT_Task | FAI | 20/10/2021 | 21/10/2021 | 06/10/2021 | 08/10/2021 | 0 | TK_Complete | 1653707999 | 7 | 1653707999_7
A188620 | TT_Task | Transit Time | 22/10/2021 | 25/10/2021 | 09/10/2021 | 11/10/2021 | 0 | TK_Complete | 1653707999 | 1 | 1653707999_1
A188670 | TT_Task | Tooling Ready for Production | 20/04/2021 | 14/06/2021 | 20/04/2021 | 05/06/2021 | 0 | TK_Complete | 1653707999 | 2 | 1653707999_2
A188680 | TT_Task | Raw material Received | 01/06/2021 | 02/08/2021 | 19/02/2021 | 17/05/2021 | 0 | TK_Complete | 1653707999 | 6 | 1653707999_6
A188700 | TT_Task | Production Lead Time | 03/08/2021 | 16/08/2021 | 07/06/2021 | 24/08/2021 | 0 | TK_Complete | 1653707999 | 4 | 1653707999_4
A188710 | TT_Task | FAI | 16/08/2021 | 20/08/2021 | 25/08/2021 | 26/08/2021 | 0 | TK_Complete | 1653707999 | 7 | 1653707999_7
A188720 | TT_Task | Transit Time | 23/08/2021 | 23/08/2021 | 27/08/2021 | 31/08/2021 | 0 | TK_Complete | 1653707999 | 1 | 1653707999_1
A188870 | TT_Task | Tooling Ready for Production | 01/06/2021 | 12/07/2021 | 01/06/2021 | 16/08/2021 | 0 | TK_Complete | 1653707999 | 2 | 1653707999_2
A188880 | TT_Task | Raw material Received | 01/06/2021 | 02/08/2021 | 01/06/2021 | 02/06/2021 | 0 | TK_Complete | 1653707999 | 6 | 1653707999_6
A188900 | TT_Task | Production Lead Time | 21/06/2021 | 02/07/2021 | 21/06/2021 | 16/08/2021 | 0 | TK_Complete | 1653707999 | 4 | 1653707999_4
A188910 | TT_Task | FAI | 16/08/2021 | 18/08/2021 | 16/08/2021 | 18/08/2021 | 0 | TK_Complete | 1653707999 | 7 | 1653707999_7
A188920 | TT_Task | Transit Time | 19/08/2021 | 19/08/2021 | 19/08/2021 | 19/08/2021 | 0 | TK_Complete | 1653707999 | 1 | 1653707999_1
A188970 | TT_Task | Tooling Ready for Production | 19/04/2021 | 28/05/2021 | 10/04/2021 | 01/06/2021 | 0 | TK_Complete | 1653707999 | 2 | 1653707999_2
A188980 | TT_Task | Raw material Received | 19/04/2021 | 18/06/2021 | 10/04/2021 | 22/04/2021 | 0 | TK_Complete | 1653707999 | 6 | 1653707999_6
A189000 | TT_Task | Production Lead Time | 01/06/2021 | 03/06/2021 | 26/06/2021 | 10/07/2021 | 0 | TK_Complete | 1653707999 | 4 | 1653707999_4
A189010 | TT_Task | FAI | 19/07/2021 | 23/07/2021 | 11/07/2021 | 11/07/2021 | 0 | TK_Complete | 1653707999 | 7 | 1653707999_7
A189020 | TT_Task | Transit Time | 26/07/2021 | 26/07/2021 | 12/07/2021 | 13/07/2021 | 0 | TK_Complete | 1653707999 | 1 | 1653707999_1
A189070 | TT_Task | Tooling Ready for Production | 19/04/2021 | 28/05/2021 | 23/02/2021 | 03/06/2021 | 0 | TK_Complete | 1653707999 | 2 | 1653707999_2
A189080 | TT_Task | Raw material Received | 19/04/2021 | 18/06/2021 | 18/02/2021 | 01/06/2021 | 0 | TK_Complete | 1653707999 | 6 | 1653707999_6
A189100 | TT_Task | Production Lead Time | 01/06/2021 | 28/06/2021 | 01/06/2021 | 13/07/2021 | 0 | TK_Complete | 1653707999 | 4 | 1653707999_4
A189110 | TT_Task | ICR (FAI shifted on other train) | 01/07/2021 | 02/07/2021 | 01/07/2021 | 02/07/2021 | 0 | TK_Complete | 1653707999 | 8 | 1653707999_8
A189120 | TT_Task | Transit Time | 05/07/2021 | 12/07/2021 | 05/07/2021 | 14/07/2021 | 0 | TK_Complete | 1653707999 | 1 | 1653707999_1
A189170 | TT_Task | Tooling Ready for Production | 01/06/2021 | 12/07/2021 | 01/05/2021 | 18/07/2021 | 0 | TK_Complete | 1653707999 | 2 | 1653707999_2
A189180 | TT_Task | Raw material Received | 19/04/2021 | 18/06/2021 | 17/02/2021 | 22/04/2021 | 0 | TK_Complete | 1653707999 | 6 | 1653707999_6
A189200 | TT_Task | Production Lead Time | 08/07/2021 | 21/07/2021 | 22/04/2021 | 16/08/2021 | 0 | TK_Complete | 1653707999 | 4 | 1653707999_4
A189210 | TT_Task | FAI | 16/08/2021 | 20/08/2021 | 16/08/2021 | 20/08/2021 | 0 | TK_Complete | 1653707999 | 7 | 1653707999_7
A189220 | TT_Task | Transit Time | 23/08/2021 | 23/08/2021 | 23/08/2021 | 23/08/2021 | 0 | TK_Complete | 1653707999 | 1 | 1653707999_1
A189270 | TT_Task | Tooling Ready for Production | 01/06/2021 | 12/07/2021 | 01/06/2021 | 03/08/2021 | 0 | TK_Complete | 1653707999 | 2 | 1653707999_2
A189280 | TT_Task | Raw material Received | 01/06/2021 | 02/08/2021 | 01/06/2021 | 02/06/2021 | 0 | TK_Complete | 1653707999 | 6 | 1653707999_6
A189300 | TT_Task | Production Lead Time | 16/08/2021 | 03/09/2021 | 04/08/2021 | 24/08/2021 | 0 | TK_Complete | 1653707999 | 4 | 1653707999_4
A189310 | TT_Task | FAI | 25/08/2021 | 26/08/2021 | 25/08/2021 | 26/08/2021 | 0 | TK_Complete | 1653707999 | 7 | 1653707999_7
A189320 | TT_Task | Transit Time | 27/08/2021 | 27/08/2021 | 27/08/2021 | 27/08/2021 | 0 | TK_Complete | 1653707999 | 1 | 1653707999_1
A189370 | TT_Task | Tooling Ready for Production | 30/09/2021 | 20/10/2021 | 28/07/2021 | 30/09/2021 | 0 | TK_Complete | 1653707999 | 2 | 1653707999_2
A189380 | TT_Task | Raw material Received | 30/09/2021 | 20/10/2021 | 28/07/2021 | 15/09/2021 | 0 | TK_Complete | 1653707999 | 6 | 1653707999_6
A189400 | TT_Task | Production Lead Time | 21/10/2021 | 17/11/2021 | 16/09/2021 | 08/11/2021 | 0 | TK_Complete | 1653707999 | 4 | 1653707999_4
A189410 | TT_Task | FAI | 01/11/2021 | 02/11/2021 | 09/11/2021 | 11/11/2021 | 0 | TK_Complete | 1653707999 | 7 | 1653707999_7
A189420 | TT_Task | Transit Time | 03/11/2021 | 03/11/2021 | 12/11/2021 | 15/11/2021 | 0 | TK_Complete | 1653707999 | 1 | 1653707999_1
A189470 | TT_Task | Tooling Ready for Production | 30/09/2021 | 13/10/2021 | 27/07/2021 | 29/09/2021 | 0 | TK_Complete | 1653707999 | 2 | 1653707999_2
A189500 | TT_Task | Production Lead Time | 14/10/2021 | 27/10/2021 | 01/09/2021 | 16/10/2021 | 0 | TK_Complete | 1653707999 | 4 | 1653707999_4
A189510 | TT_Task | FAI | 20/10/2021 | 22/10/2021 | 18/10/2021 | 18/10/2021 | 0 | TK_Complete | 1653707999 | 7 | 1653707999_7
A189520 | TT_Task | Transit Time | 25/10/2021 | 26/10/2021 | 18/10/2021 | 21/10/2021 | 0 | TK_Complete | 1653707999 | 1 | 1653707999_1
A185180 | TT_Task | Delivery in store | 30/11/2021 | 30/11/2021 | 27/11/2021 | 27/11/2021 | 0 | TK_Complete | 1653707999 | 9 | 1653707999_9
A185320 | TT_Task | Delivery in store | 23/12/2021 | 23/12/2021 | 20/12/2021 | 20/12/2021 | 0 | TK_Complete | 1653707999 | 9 | 1653707999_9
A185460 | TT_Task | Delivery in store | 31/12/2021 | 31/12/2021 | 31/12/2021 | 17/01/2022 | 0 | TK_Complete | 1653707999 | 9 | 1653707999_9
A185530 | TT_Task | Delivery in store | 24/01/2022 | 24/01/2022 | 01/01/2022 | 01/01/2022 | 0 | TK_Complete | 1653707999 | 9 | 1653707999_9
A185600 | TT_Task | Delivery in store | 10/01/2022 | 10/01/2022 | 20/01/2022 | 20/01/2022 | 0 | TK_Complete | 1653707999 | 9 | 1653707999_9
A185670 | TT_Task | Delivery in store | 17/01/2022 | 17/01/2022 | 20/01/2022 | 20/01/2022 | 0 | TK_Complete | 1653707999 | 9 | 1653707999_9
A185740 | TT_Task | Delivery in store | 31/01/2022 | 10/02/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 9 | 1653707999_9
A185810 | TT_Task | Delivery in store | 31/01/2022 | 31/01/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 9 | 1653707999_9
A186020 | TT_Task | Delivery in store | 31/01/2022 | 31/01/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 9 | 1653707999_9
A186090 | TT_Task | Delivery in store | 31/01/2022 | 31/01/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 9 | 1653707999_9
A186160 | TT_Task | M1B : Delivery in store | 31/01/2022 | 31/01/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 10 | 1653707999_10
A186170 | TT_Task | DME : Delivery in store(M1B used in DME) | 01/11/2021 | 21/12/2021 | 01/11/2021 | 13/12/2021 | 0 | TK_Complete | 1653707999 | 11 | 1653707999_11
A186180 | TT_Task | DMB : Delivery in store | 31/01/2022 | 31/01/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 12 | 1653707999_12
A186190 | TT_Task | T1A : Delivery in store | 31/01/2022 | 31/01/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 13 | 1653707999_13
A186200 | TT_Task | M1A : Delivery in store | 31/01/2022 | 31/01/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 10 | 1653707999_10
A186210 | TT_Task | T1B : Delivery in store | 01/11/2021 | 08/12/2021 | 01/11/2021 | 21/12/2021 | 0 | TK_Complete | 1653707999 | 13 | 1653707999_13
A186230 | TT_Task | M1B : Delivery in store | 31/01/2022 | 31/01/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 10 | 1653707999_10
A199310 | TT_Task | T1B : Delivery in store | 31/01/2022 | 31/01/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 13 | 1653707999_13
A199320 | TT_Task | M1A : Delivery in store | 31/01/2022 | 31/01/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 10 | 1653707999_10
A199330 | TT_Task | T1A : Delivery in store | 31/01/2022 | 31/01/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 13 | 1653707999_13
A199340 | TT_Task | DMB : Delivery in store | 31/01/2022 | 31/01/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 12 | 1653707999_12
A199350 | TT_Task | DME : Delivery in store | 31/01/2022 | 31/01/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 11 | 1653707999_11
A186370 | TT_Task | Delivery in store | 31/01/2022 | 31/01/2022 | nan | nan | 10551 | TK_NotStart | 1653707999 | 9 | 1653707999_9
A186440 | TT_Task | Delivery in store | 25/02/2022 | 25/02/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 9 | 1653707999_9
A186580 | TT_Task | Delivery in store | 31/01/2022 | 31/01/2022 | nan | nan | 10551 | TK_NotStart | 1653707999 | 9 | 1653707999_9
A186650 | TT_Task | Delivery in store | 31/01/2022 | 31/01/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 9 | 1653707999_9
A186720 | TT_Task | Delivery in store | 31/01/2022 | 31/01/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 9 | 1653707999_9
A186790 | TT_Task | Delivery in store | 31/01/2022 | 31/01/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 9 | 1653707999_9
A187070 | TT_Task | Delivery in store | 28/02/2022 | 28/02/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 9 | 1653707999_9
A199360 | TT_Task | T1B : Delivery in store | 31/01/2022 | 31/01/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 13 | 1653707999_13
A199370 | TT_Task | M1A : Delivery in store | 31/01/2022 | 31/01/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 10 | 1653707999_10
A199380 | TT_Task | T1A : Delivery in store | 31/01/2022 | 31/01/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 13 | 1653707999_13
A199390 | TT_Task | DMB : Delivery in store | 31/01/2022 | 31/01/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 12 | 1653707999_12
A199400 | TT_Task | DME : Delivery in store | 31/01/2022 | 04/03/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 11 | 1653707999_11
A187210 | TT_Task | Delivery in store | 31/01/2022 | 31/01/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 9 | 1653707999_9
A187280 | TT_Task | Delivery in store | 31/01/2022 | 31/01/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 9 | 1653707999_9
A187350 | TT_Task | Delivery in store | 31/01/2022 | 31/01/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 9 | 1653707999_9
A187420 | TT_Task | Delivery in store | 31/01/2022 | 31/01/2022 | 31/01/2022 | 31/01/2022 | 0 | TK_Complete | 1653707999 | 9 | 1653707999_9
A187490 | TT_Task | Delivery in store | 31/01/2022 | 31/01/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 9 | 1653707999_9
A187560 | TT_Task | Delivery in store | 31/01/2022 | 31/01/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 9 | 1653707999_9
A187630 | TT_Task | Delivery in store | 31/01/2022 | 31/01/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 9 | 1653707999_9
A187700 | TT_Task | Delivery in store | 08/02/2022 | 08/02/2022 | 30/11/2021 | 30/11/2021 | 0 | TK_Complete | 1653707999 | 9 | 1653707999_9
A187840 | TT_Task | Delivery in store | 31/01/2022 | 31/01/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 9 | 1653707999_9
A187910 | TT_Task | Delivery in store | 31/01/2022 | 31/01/2022 | nan | nan | 10551 | TK_NotStart | 1653707999 | 9 | 1653707999_9
A187980 | TT_Task | Delivery in store | 18/03/2022 | 18/03/2022 | nan | nan | 10279 | TK_NotStart | 1653707999 | 9 | 1653707999_9
A188190 | TT_Task | Delivery in store | 16/12/2021 | 16/12/2021 | 16/12/2021 | 16/12/2021 | 0 | TK_Complete | 1653707999 | 9 | 1653707999_9
A188260 | TT_Task | Delivery in store | 31/01/2022 | 31/01/2022 | 11/01/2022 | 11/01/2022 | 0 | TK_Complete | 1653707999 | 9 | 1653707999_9
A199200 | TT_Task | M1B : Harness Delivery to Savli (FBL 2.1) | 31/01/2022 | 31/01/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 14 | 1653707999_14
A199210 | TT_Task | T1B : Harness Delivery to Savli (FBL 2.1) | 31/01/2022 | 31/01/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 14 | 1653707999_14
A199220 | TT_Task | M1A : Harness Delivery to Savli (FBL 2.1) | 31/01/2022 | 31/01/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 14 | 1653707999_14
A199230 | TT_Task | T1A : Harness Delivery to Savli (FBL 2.1) | 31/01/2022 | 31/01/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 14 | 1653707999_14
A199240 | TT_Task | DMB : Harness Delivery to Savli (FBL 2.1) | 31/01/2022 | 04/02/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 14 | 1653707999_14
A199250 | TT_Task | DME : Harness Delivery to Savli (FBL 2.1) | 31/01/2022 | 31/01/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 14 | 1653707999_14
A199410 | TT_Task | M1B : Cabinate Delivery to Savli (FBL 2.1) | 31/01/2022 | 31/01/2022 | 31/01/2022 | 31/01/2022 | 0 | TK_Complete | 1653707999 | 15 | 1653707999_15
A199420 | TT_Task | T1B : Cabinate Delivery to Savli (FBL 2.1) | 31/01/2022 | 17/02/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 15 | 1653707999_15
A199430 | TT_Task | M1A : Cabinate Delivery to Savli (FBL 2.1) | 31/01/2022 | 25/02/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 15 | 1653707999_15
A199440 | TT_Task | T1A : Cabinate Delivery to Savli (FBL 2.1) | 31/01/2022 | 28/02/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 15 | 1653707999_15
A199450 | TT_Task | DMB : Cabinate Delivery to Savli (FBL 2.1) | 31/01/2022 | 04/03/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 15 | 1653707999_15
A199460 | TT_Task | DME : Cabinate Delivery to Savli (FBL 2.1) | 31/01/2022 | 04/03/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 15 | 1653707999_15
A201050 | TT_Task | Seat : Extrusion | 31/01/2022 | 31/01/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 16 | 1653707999_16
A201060 | TT_Task | Seat Cover : Extrusion (TBC) | 31/01/2022 | 31/01/2022 | nan | nan | 10551 | TK_NotStart | 1653707999 | 17 | 1653707999_17
A201070 | TT_Task | Coving : Extrusion | 01/11/2021 | 01/11/2021 | 01/11/2021 | 11/12/2021 | 0 | TK_Complete | 1653707999 | 18 | 1653707999_18
A201080 | TT_Task | Threashold Plate : Extrusion | 31/01/2022 | 31/01/2022 | 07/01/2022 | 07/01/2022 | 0 | TK_Complete | 1653707999 | 19 | 1653707999_19
A180310 | TT_Task | Requirement Management | 14/09/2020 | 14/09/2020 | 19/08/2020 | 28/10/2020 | 0 | TK_Complete | 1653707999 | 20 | 1653707999_20
A180320 | TT_Task | Concept Review ; Finalisation | 29/10/2020 | 23/11/2020 | 29/10/2020 | 20/11/2020 | 0 | TK_Complete | 1653707999 | 21 | 1653707999_21
A180340 | TT_Task | DAP Review ; Sing Off | 24/11/2020 | 09/12/2020 | 24/11/2020 | 12/01/2021 | 0 | TK_Complete | 1653707999 | 22 | 1653707999_22
A180350 | TT_Task | Supplier Lead Time | 10/02/2021 | 28/05/2021 | 13/01/2021 | 27/05/2021 | 0 | TK_Complete | 1653707999 | 23 | 1653707999_23
A180360 | TT_Task | FAI at Supplier | 01/06/2021 | 08/06/2021 | 01/06/2021 | 08/06/2021 | 0 | TK_Complete | 1653707999 | 24 | 1653707999_24
A180370 | TT_Task | Installation | 09/06/2021 | 24/06/2021 | 09/06/2021 | 28/06/2021 | 0 | TK_Complete | 1653707999 | 25 | 1653707999_25
A180380 | TT_Task | Validation ; Documentation | 25/06/2021 | 13/07/2021 | 25/06/2021 | 13/07/2021 | 0 | TK_Complete | 1653707999 | 26 | 1653707999_26
A182290 | TT_Task | Requirement Management | 14/09/2020 | 14/09/2020 | 19/08/2020 | 25/08/2020 | 0 | TK_Complete | 1653707999 | 20 | 1653707999_20
A182300 | TT_Task | Concept Review ; Finalisation | 18/02/2021 | 15/03/2021 | 26/08/2020 | 11/12/2020 | 0 | TK_Complete | 1653707999 | 21 | 1653707999_21
A182320 | TT_Task | DAP Review ; Sing Off | 01/06/2021 | 16/06/2021 | 15/04/2021 | 15/05/2021 | 0 | TK_Complete | 1653707999 | 22 | 1653707999_22
A182330 | TT_Task | Supplier Lead Time | 17/06/2021 | 28/07/2021 | 22/02/2021 | 25/06/2021 | 0 | TK_Complete | 1653707999 | 23 | 1653707999_23
A182340 | TT_Task | FAI at Supplier | 29/07/2021 | 04/08/2021 | 26/06/2021 | 02/07/2021 | 0 | TK_Complete | 1653707999 | 24 | 1653707999_24
A182350 | TT_Task | Installation | 05/08/2021 | 18/08/2021 | 03/07/2021 | 09/07/2021 | 0 | TK_Complete | 1653707999 | 25 | 1653707999_25
A182360 | TT_Task | Validation ; Documentation | 19/08/2021 | 25/08/2021 | 10/07/2021 | 14/07/2021 | 0 | TK_Complete | 1653707999 | 26 | 1653707999_26
A182490 | TT_Task | Requirement Management | 31/01/2022 | 08/02/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 20 | 1653707999_20
A182500 | TT_Task | Concept Review ; Finalisation | 09/02/2022 | 15/02/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 21 | 1653707999_21
A182520 | TT_Task | DAP Review ; Sing Off | 16/02/2022 | 28/04/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 22 | 1653707999_22
A182530 | TT_Task | Supplier Lead Time | 29/04/2022 | 16/08/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 23 | 1653707999_23
A182540 | TT_Task | FAI at Supplier | 17/08/2022 | 01/09/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 24 | 1653707999_24
A182550 | TT_Task | Installation | 02/09/2022 | 03/10/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 25 | 1653707999_25
A182560 | TT_Task | Validation ; Documentation | 04/10/2022 | 26/10/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 26 | 1653707999_26
A175120 | TT_Task | SLM - Lead Time | 31/01/2022 | 25/03/2022 | nan | nan | 10239 | TK_NotStart | 1653707999 | 27 | 1653707999_27
A182590 | TT_Task | Requirement Management | 14/09/2020 | 14/09/2020 | 19/08/2020 | 25/08/2020 | 0 | TK_Complete | 1653707999 | 20 | 1653707999_20
A182600 | TT_Task | Concept Review ; Finalisation | 09/06/2021 | 02/07/2021 | 25/08/2020 | 11/12/2020 | 0 | TK_Complete | 1653707999 | 21 | 1653707999_21
A182620 | TT_Task | DAP Review ; Sing Off | 05/07/2021 | 20/07/2021 | 12/12/2020 | 28/02/2021 | 0 | TK_Complete | 1653707999 | 22 | 1653707999_22
A182630 | TT_Task | Supplier Lead Time | 21/07/2021 | 05/11/2021 | 01/03/2021 | 25/05/2021 | 0 | TK_Complete | 1653707999 | 23 | 1653707999_23
A182640 | TT_Task | FAI at Supplier | 08/11/2021 | 23/11/2021 | 26/05/2021 | 01/06/2021 | 0 | TK_Complete | 1653707999 | 24 | 1653707999_24
A182650 | TT_Task | Installation | 24/11/2021 | 23/12/2021 | 02/06/2021 | 06/06/2021 | 0 | TK_Complete | 1653707999 | 25 | 1653707999_25
A182660 | TT_Task | Validation ; Documentation | 24/12/2021 | 11/01/2022 | 07/06/2021 | 20/06/2021 | 0 | TK_Complete | 1653707999 | 26 | 1653707999_26
A182690 | TT_Task | Requirement Management | 14/09/2020 | 14/09/2020 | 19/08/2020 | 25/08/2020 | 0 | TK_Complete | 1653707999 | 20 | 1653707999_20
A182700 | TT_Task | Concept Review ; Finalisation | 09/06/2021 | 02/07/2021 | 25/10/2020 | 25/10/2020 | 0 | TK_Complete | 1653707999 | 21 | 1653707999_21
A182720 | TT_Task | DAP Review ; Sing Off | 05/07/2021 | 20/07/2021 | 26/10/2020 | 30/11/2020 | 0 | TK_Complete | 1653707999 | 22 | 1653707999_22
A182730 | TT_Task | Supplier Lead Time | 21/07/2021 | 05/11/2021 | 01/12/2020 | 15/01/2021 | 0 | TK_Complete | 1653707999 | 23 | 1653707999_23
A182740 | TT_Task | FAI at Supplier | 08/11/2021 | 23/11/2021 | 16/01/2021 | 10/02/2021 | 0 | TK_Complete | 1653707999 | 24 | 1653707999_24
A182750 | TT_Task | Installation | 24/11/2021 | 23/12/2021 | 11/02/2021 | 12/02/2021 | 0 | TK_Complete | 1653707999 | 25 | 1653707999_25
A182760 | TT_Task | Validation ; Documentation | 24/12/2021 | 11/01/2022 | 13/02/2021 | 16/02/2021 | 0 | TK_Complete | 1653707999 | 26 | 1653707999_26
A182790 | TT_Task | Requirement Management | 14/09/2020 | 14/09/2020 | 19/08/2020 | 17/11/2020 | 0 | TK_Complete | 1653707999 | 20 | 1653707999_20
A182800 | TT_Task | Concept Review ; Finalisation | 01/06/2021 | 24/06/2021 | 17/11/2020 | 11/12/2020 | 0 | TK_Complete | 1653707999 | 21 | 1653707999_21
A182820 | TT_Task | DAP Review ; Sing Off | 25/06/2021 | 12/07/2021 | 11/12/2020 | 28/02/2021 | 0 | TK_Complete | 1653707999 | 22 | 1653707999_22
A182830 | TT_Task | Supplier Lead Time | 13/07/2021 | 28/10/2021 | 01/03/2021 | 22/06/2021 | 0 | TK_Complete | 1653707999 | 23 | 1653707999_23
A182840 | TT_Task | FAI at Supplier | 29/10/2021 | 15/11/2021 | 23/06/2021 | 23/06/2021 | 0 | TK_Complete | 1653707999 | 24 | 1653707999_24
A182850 | TT_Task | Installation | 16/11/2021 | 15/12/2021 | 24/06/2021 | 26/06/2021 | 0 | TK_Complete | 1653707999 | 25 | 1653707999_25
A182860 | TT_Task | Validation ; Documentation | 16/12/2021 | 03/01/2022 | 27/06/2021 | 30/06/2021 | 0 | TK_Complete | 1653707999 | 26 | 1653707999_26
A182890 | TT_Task | Requirement Management | 14/09/2020 | 14/09/2020 | 19/08/2020 | 25/08/2020 | 0 | TK_Complete | 1653707999 | 20 | 1653707999_20
A182900 | TT_Task | Concept Review ; Finalisation | 09/06/2021 | 02/07/2021 | 26/08/2020 | 10/04/2021 | 0 | TK_Complete | 1653707999 | 21 | 1653707999_21
A182920 | TT_Task | DAP Review ; Sing Off | 05/07/2021 | 20/07/2021 | 11/04/2021 | 15/05/2021 | 0 | TK_Complete | 1653707999 | 22 | 1653707999_22
A182930 | TT_Task | Supplier Lead Time | 21/07/2021 | 05/11/2021 | 17/05/2021 | 24/06/2021 | 0 | TK_Complete | 1653707999 | 23 | 1653707999_23
A182940 | TT_Task | FAI at Supplier | 08/11/2021 | 23/11/2021 | 25/06/2021 | 01/07/2021 | 0 | TK_Complete | 1653707999 | 24 | 1653707999_24
A182950 | TT_Task | Installation | 24/11/2021 | 23/12/2021 | 02/07/2021 | 23/07/2021 | 0 | TK_Complete | 1653707999 | 25 | 1653707999_25
A182960 | TT_Task | Validation ; Documentation | 23/07/2021 | 27/07/2021 | 23/07/2021 | 27/07/2021 | 0 | TK_Complete | 1653707999 | 26 | 1653707999_26
A182990 | TT_Task | Requirement Management | 01/06/2021 | 09/06/2021 | 17/06/2021 | 22/06/2021 | 0 | TK_Complete | 1653707999 | 20 | 1653707999_20
A183000 | TT_Task | Concept Review ; Finalisation | 10/06/2021 | 16/06/2021 | 22/06/2021 | 30/06/2021 | 0 | TK_Complete | 1653707999 | 21 | 1653707999_21
A183020 | TT_Task | DAP Review ; Sing Off | 17/06/2021 | 27/08/2021 | 30/06/2021 | 30/06/2021 | 0 | TK_Complete | 1653707999 | 22 | 1653707999_22
A183030 | TT_Task | Supplier Lead Time | 30/08/2021 | 15/12/2021 | 02/07/2021 | nan | 0 | TK_Active | 1653707999 | 23 | 1653707999_23
A183040 | TT_Task | FAI at Supplier | 31/01/2022 | 01/02/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 24 | 1653707999_24
A183050 | TT_Task | Installation | 02/02/2022 | 08/02/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 25 | 1653707999_25
A183060 | TT_Task | Validation ; Documentation | 09/02/2022 | 10/02/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 26 | 1653707999_26
A183090 | TT_Task | Requirement Management | 14/09/2020 | 14/09/2020 | 19/08/2020 | 25/08/2020 | 0 | TK_Complete | 1653707999 | 20 | 1653707999_20
A183100 | TT_Task | Concept Review ; Finalisation | 09/06/2021 | 18/06/2021 | 26/08/2020 | 10/04/2021 | 0 | TK_Complete | 1653707999 | 21 | 1653707999_21
A183120 | TT_Task | DAP Review ; Sing Off | 21/06/2021 | 09/08/2021 | 12/04/2021 | 30/05/2021 | 0 | TK_Complete | 1653707999 | 22 | 1653707999_22
A183130 | TT_Task | Supplier Lead Time | 10/08/2021 | 15/12/2021 | 31/05/2021 | nan | 0 | TK_Active | 1653707999 | 23 | 1653707999_23
A183140 | TT_Task | FAI at Supplier | 31/01/2022 | 01/02/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 24 | 1653707999_24
A183150 | TT_Task | Installation | 02/02/2022 | 08/02/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 25 | 1653707999_25
A183160 | TT_Task | Validation ; Documentation | 09/02/2022 | 11/02/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 26 | 1653707999_26
A180400 | TT_Task | SLM - Lead Time | 31/01/2022 | 25/03/2022 | nan | nan | 10239 | TK_NotStart | 1653707999 | 27 | 1653707999_27
A180420 | TT_Task | SLM - Lead Time | 31/01/2022 | 25/03/2022 | nan | nan | 10239 | TK_NotStart | 1653707999 | 27 | 1653707999_27
A180430 | TT_Task | SLM - Lead Time | 31/01/2022 | 25/03/2022 | nan | nan | 10239 | TK_NotStart | 1653707999 | 27 | 1653707999_27
A181690 | TT_Task | Requirement Management | 31/01/2022 | 31/01/2022 | nan | nan | 10551 | TK_NotStart | 1653707999 | 20 | 1653707999_20
A181700 | TT_Task | Concept Review ; Finalisation | 31/01/2022 | 31/01/2022 | nan | nan | 10551 | TK_NotStart | 1653707999 | 21 | 1653707999_21
A181720 | TT_Task | DAP Review ; Sing Off | 31/01/2022 | 31/01/2022 | nan | nan | 10551 | TK_NotStart | 1653707999 | 22 | 1653707999_22
A181730 | TT_Task | Supplier Lead Time | 31/01/2022 | 31/01/2022 | nan | nan | 10551 | TK_NotStart | 1653707999 | 23 | 1653707999_23
A181740 | TT_Task | FAI at Supplier | 31/01/2022 | 31/01/2022 | nan | nan | 10551 | TK_NotStart | 1653707999 | 24 | 1653707999_24
A181750 | TT_Task | Installation | 31/01/2022 | 31/01/2022 | nan | nan | 10551 | TK_NotStart | 1653707999 | 25 | 1653707999_25
A181760 | TT_Task | Validation ; Documentation | 31/01/2022 | 31/01/2022 | nan | nan | 10551 | TK_NotStart | 1653707999 | 26 | 1653707999_26
A180440 | TT_Task | SLM - Lead Time | 31/01/2022 | 25/03/2022 | nan | nan | 10239 | TK_NotStart | 1653707999 | 27 | 1653707999_27
A181790 | TT_Task | Requirement Management | 31/01/2022 | 31/01/2022 | nan | nan | 10551 | TK_NotStart | 1653707999 | 20 | 1653707999_20
A181800 | TT_Task | Concept Review ; Finalisation | 31/01/2022 | 31/01/2022 | nan | nan | 10551 | TK_NotStart | 1653707999 | 21 | 1653707999_21
A181820 | TT_Task | DAP Review ; Sing Off | 31/01/2022 | 31/01/2022 | nan | nan | 10551 | TK_NotStart | 1653707999 | 22 | 1653707999_22
A181830 | TT_Task | Supplier Lead Time | 31/01/2022 | 31/01/2022 | nan | nan | 10551 | TK_NotStart | 1653707999 | 23 | 1653707999_23
A181840 | TT_Task | FAI at Supplier | 31/01/2022 | 31/01/2022 | nan | nan | 10551 | TK_NotStart | 1653707999 | 24 | 1653707999_24
A181850 | TT_Task | Installation | 31/01/2022 | 31/01/2022 | nan | nan | 10551 | TK_NotStart | 1653707999 | 25 | 1653707999_25
A181860 | TT_Task | Validation ; Documentation | 31/01/2022 | 31/01/2022 | nan | nan | 10551 | TK_NotStart | 1653707999 | 26 | 1653707999_26
A180450 | TT_Task | SLM - Lead Time | 31/01/2022 | 25/03/2022 | nan | nan | 10239 | TK_NotStart | 1653707999 | 27 | 1653707999_27
A181890 | TT_Task | Requirement Management | 31/01/2022 | 31/01/2022 | nan | nan | 10551 | TK_NotStart | 1653707999 | 20 | 1653707999_20
A181900 | TT_Task | Concept Review ; Finalisation | 31/01/2022 | 31/01/2022 | nan | nan | 10551 | TK_NotStart | 1653707999 | 21 | 1653707999_21
A181920 | TT_Task | DAP Review ; Sing Off | 31/01/2022 | 31/01/2022 | nan | nan | 10551 | TK_NotStart | 1653707999 | 22 | 1653707999_22
A181930 | TT_Task | Supplier Lead Time | 31/01/2022 | 31/01/2022 | nan | nan | 10551 | TK_NotStart | 1653707999 | 23 | 1653707999_23
A181940 | TT_Task | FAI at Supplier | 31/01/2022 | 31/01/2022 | nan | nan | 10551 | TK_NotStart | 1653707999 | 24 | 1653707999_24
A181950 | TT_Task | Installation | 31/01/2022 | 31/01/2022 | nan | nan | 10551 | TK_NotStart | 1653707999 | 25 | 1653707999_25
A181960 | TT_Task | Validation ; Documentation | 31/01/2022 | 31/01/2022 | nan | nan | 10551 | TK_NotStart | 1653707999 | 26 | 1653707999_26
A180460 | TT_Task | SLM - Lead Time | 31/01/2022 | 25/03/2022 | nan | nan | 10239 | TK_NotStart | 1653707999 | 27 | 1653707999_27
A181990 | TT_Task | Requirement Management | 31/01/2022 | 31/01/2022 | nan | nan | 10551 | TK_NotStart | 1653707999 | 20 | 1653707999_20
A182000 | TT_Task | Concept Review ; Finalisation | 31/01/2022 | 31/01/2022 | nan | nan | 10551 | TK_NotStart | 1653707999 | 21 | 1653707999_21
A182020 | TT_Task | DAP Review ; Sing Off | 31/01/2022 | 31/01/2022 | nan | nan | 10551 | TK_NotStart | 1653707999 | 22 | 1653707999_22
A182030 | TT_Task | Supplier Lead Time | 31/01/2022 | 31/01/2022 | nan | nan | 10551 | TK_NotStart | 1653707999 | 23 | 1653707999_23
A182040 | TT_Task | FAI at Supplier | 31/01/2022 | 31/01/2022 | nan | nan | 10551 | TK_NotStart | 1653707999 | 24 | 1653707999_24
A182050 | TT_Task | Installation | 31/01/2022 | 31/01/2022 | nan | nan | 10551 | TK_NotStart | 1653707999 | 25 | 1653707999_25
A182060 | TT_Task | Validation ; Documentation | 31/01/2022 | 31/01/2022 | nan | nan | 10551 | TK_NotStart | 1653707999 | 26 | 1653707999_26
A180470 | TT_Task | SLM - Lead Time | 31/01/2022 | 25/03/2022 | nan | nan | 10239 | TK_NotStart | 1653707999 | 27 | 1653707999_27
A182090 | TT_Task | Requirement Management | 31/01/2022 | 31/01/2022 | nan | nan | 10551 | TK_NotStart | 1653707999 | 20 | 1653707999_20
A182100 | TT_Task | Concept Review ; Finalisation | 31/01/2022 | 31/01/2022 | nan | nan | 10551 | TK_NotStart | 1653707999 | 21 | 1653707999_21
A182120 | TT_Task | DAP Review ; Sing Off | 31/01/2022 | 31/01/2022 | nan | nan | 10551 | TK_NotStart | 1653707999 | 22 | 1653707999_22
A182130 | TT_Task | Supplier Lead Time | 31/01/2022 | 31/01/2022 | nan | nan | 10551 | TK_NotStart | 1653707999 | 23 | 1653707999_23
A182140 | TT_Task | FAI at Supplier | 31/01/2022 | 31/01/2022 | nan | nan | 10551 | TK_NotStart | 1653707999 | 24 | 1653707999_24
A182150 | TT_Task | Installation | 31/01/2022 | 31/01/2022 | nan | nan | 10551 | TK_NotStart | 1653707999 | 25 | 1653707999_25
A182160 | TT_Task | Validation ; Documentation | 31/01/2022 | 31/01/2022 | nan | nan | 10551 | TK_NotStart | 1653707999 | 26 | 1653707999_26
A182190 | TT_Task | Requirement Management | 31/01/2022 | 31/01/2022 | nan | nan | 10551 | TK_NotStart | 1653707999 | 20 | 1653707999_20
A182200 | TT_Task | Concept Review ; Finalisation | 31/01/2022 | 31/01/2022 | nan | nan | 10551 | TK_NotStart | 1653707999 | 21 | 1653707999_21
A182220 | TT_Task | DAP Review ; Sing Off | 31/01/2022 | 31/01/2022 | nan | nan | 10551 | TK_NotStart | 1653707999 | 22 | 1653707999_22
A182230 | TT_Task | Supplier Lead Time | 31/01/2022 | 31/01/2022 | nan | nan | 10551 | TK_NotStart | 1653707999 | 23 | 1653707999_23
A182240 | TT_Task | FAI at Supplier | 31/01/2022 | 31/01/2022 | nan | nan | 10551 | TK_NotStart | 1653707999 | 24 | 1653707999_24
A182250 | TT_Task | Installation | 31/01/2022 | 31/01/2022 | nan | nan | 10551 | TK_NotStart | 1653707999 | 25 | 1653707999_25
A182260 | TT_Task | Validation ; Documentation | 31/01/2022 | 31/01/2022 | nan | nan | 10551 | TK_NotStart | 1653707999 | 26 | 1653707999_26
A130100 | TT_Task | Design Release | 10/02/2021 | 21/05/2021 | 01/04/2020 | 26/02/2021 | 0 | TK_Complete | 1653707999 | 28 | 1653707999_28
A130110 | TT_Task | Procurement | 11/06/2021 | 20/09/2021 | 01/10/2020 | 28/05/2021 | 0 | TK_Complete | 1653707999 | 29 | 1653707999_29
A130120 | TT_Task | Manufacturing | 13/10/2021 | 29/12/2021 | 18/11/2020 | 28/05/2021 | 0 | TK_Complete | 1653707999 | 30 | 1653707999_30
A130130 | TT_Task | Customer Acceptance | 01/06/2021 | 28/06/2021 | 19/05/2021 | 08/06/2021 | 0 | TK_Complete | 1653707999 | 31 | 1653707999_31
A205760 | TT_Task | M1-B : T1C1 Underframe Structure | 27/09/2021 | 04/10/2021 | 27/09/2021 | 17/10/2021 | 0 | TK_Complete | 1653707999 | 32 | 1653707999_32
A205770 | TT_Task | M1-B :T1C1 Underframe Bars ; Bracket | 20/10/2021 | 22/10/2021 | 18/10/2021 | 27/10/2021 | 0 | TK_Complete | 1653707999 | 33 | 1653707999_33
A205780 | TT_Task | M1-B :T1C1 Underframe Trim | 27/10/2021 | 27/10/2021 | 27/10/2021 | 27/10/2021 | 0 | TK_Complete | 1653707999 | 34 | 1653707999_34
A205790 | TT_Task | M1-B :T1C1 Side wall preloading - RH | 14/09/2021 | 18/09/2021 | 03/09/2021 | 20/09/2021 | 0 | TK_Complete | 1653707999 | 35 | 1653707999_35
A205800 | TT_Task | M1-B :T1C1 Side wall final (B;B) - RH | 07/10/2021 | 07/10/2021 | 11/10/2021 | 23/10/2021 | 0 | TK_Complete | 1653707999 | 36 | 1653707999_36
A205810 | TT_Task | M1-B :T1C1 Roof Preloading + Spot | 06/09/2021 | 01/10/2021 | 16/07/2021 | 13/09/2021 | 0 | TK_Complete | 1653707999 | 37 | 1653707999_37
A205820 | TT_Task | M1-B :T1C1 Roof Bars ; brackets | 09/09/2021 | 16/09/2021 | 14/09/2021 | 28/09/2021 | 0 | TK_Complete | 1653707999 | 38 | 1653707999_38
A205830 | TT_Task | M1-B :T1C1 Roof Trim | 30/09/2021 | 05/10/2021 | 01/10/2021 | 08/10/2021 | 0 | TK_Complete | 1653707999 | 39 | 1653707999_39
A205840 | TT_Task | M1-B :T1C1 Erection - 1 | 27/10/2021 | 08/11/2021 | 28/10/2021 | 03/12/2021 | 0 | TK_Complete | 1653707999 | 40 | 1653707999_40
A205850 | TT_Task | M1-B :T1C1 Erection - 2 | 04/12/2021 | 04/12/2021 | 04/12/2021 | 06/12/2021 | 0 | TK_Complete | 1653707999 | 40 | 1653707999_40
A205970 | TT_Task | M1-B :T1C1 Side wall preloading - LH | 07/10/2021 | 08/10/2021 | 10/10/2021 | 14/10/2021 | 0 | TK_Complete | 1653707999 | 35 | 1653707999_35
A205980 | TT_Task | M1-B :T1C1 Side wall final (B;B) - LH | 22/10/2021 | 22/10/2021 | 22/10/2021 | 22/10/2021 | 0 | TK_Complete | 1653707999 | 36 | 1653707999_36
A205990 | TT_Task | M1-B :T1C1 Side wall Anti collision - RH | 21/09/2021 | 24/09/2021 | 21/09/2021 | 29/09/2021 | 0 | TK_Complete | 1653707999 | 41 | 1653707999_41
A206000 | TT_Task | M1-B :T1C1 Side wall Anti collision + spot - LH | 20/10/2021 | 21/10/2021 | 20/10/2021 | 22/10/2021 | 0 | TK_Complete | 1653707999 | 42 | 1653707999_42
A207120 | TT_Task | M1-B :T1C1 Side wall Re-Preloading - RH (Delay Event due to Part rejection) | 30/09/2021 | 01/10/2021 | 29/09/2021 | 04/10/2021 | 0 | TK_Complete | 1653707999 | 43 | 1653707999_43
A207130 | TT_Task | M1-B :T1C1 Side wall spot - RH | 01/10/2021 | 02/10/2021 | 05/10/2021 | 10/10/2021 | 0 | TK_Complete | 1653707999 | 44 | 1653707999_44
A206150 | TT_Task | T1-B :T1C3 Underframe Structure + Spot | 18/10/2021 | 27/10/2021 | 18/10/2021 | 23/11/2021 | 0 | TK_Complete | 1653707999 | 45 | 1653707999_45
A206160 | TT_Task | T1-B :T1C3 Underframe Bars ; Bracket | 23/11/2021 | 25/11/2021 | 23/11/2021 | 30/11/2021 | 0 | TK_Complete | 1653707999 | 46 | 1653707999_46
A206170 | TT_Task | T1-B :T1C3 Underframe Trim | 30/11/2021 | 02/12/2021 | 01/12/2021 | 04/12/2021 | 0 | TK_Complete | 1653707999 | 47 | 1653707999_47
A206180 | TT_Task | T1-B :T1C3 Side wall preloading - RH | 13/11/2021 | 13/11/2021 | 10/11/2021 | 21/12/2021 | 0 | TK_Complete | 1653707999 | 48 | 1653707999_48
A206190 | TT_Task | T1-B :T1C3 Side wall final (B;B) - RH | 27/11/2021 | 27/11/2021 | 27/11/2021 | 24/12/2021 | 0 | TK_Complete | 1653707999 | 49 | 1653707999_49
A206200 | TT_Task | T1-B :T1C3 Roof Preloading + Spot (4 D waiting for IQC) | 17/09/2021 | 30/09/2021 | 17/09/2021 | 12/10/2021 | 0 | TK_Complete | 1653707999 | 50 | 1653707999_50
A206210 | TT_Task | T1-B :T1C3 Roof Bars ; brackets | 13/10/2021 | 20/10/2021 | 13/10/2021 | 27/10/2021 | 0 | TK_Complete | 1653707999 | 51 | 1653707999_51
A206220 | TT_Task | T1-B :T1C3 Roof Trim | 01/11/2021 | 08/11/2021 | 10/11/2021 | 28/12/2021 | 0 | TK_Complete | 1653707999 | 52 | 1653707999_52
A206230 | TT_Task | T1-B :T1C3 Erection - 1 | 06/01/2022 | 10/01/2022 | 07/01/2022 | 18/01/2022 | 0 | TK_Complete | 1653707999 | 53 | 1653707999_53
A206240 | TT_Task | T1-B :T1C3 Erection - 2 | 18/01/2022 | 20/01/2022 | 18/01/2022 | 20/01/2022 | 0 | TK_Complete | 1653707999 | 53 | 1653707999_53
A206250 | TT_Task | T1-B :T1C3 Side wall preloading - LH | 23/11/2021 | 23/11/2021 | 23/11/2021 | 23/12/2021 | 0 | TK_Complete | 1653707999 | 48 | 1653707999_48
A206260 | TT_Task | T1-B :T1C3 Side wall final (B;B) - LH | 06/12/2021 | 06/12/2021 | 06/12/2021 | 28/12/2021 | 0 | TK_Complete | 1653707999 | 49 | 1653707999_49
A206270 | TT_Task | T1-B :T1C3 Side wall Anti collision + spot - RH | 18/11/2021 | 19/11/2021 | 17/11/2021 | 24/12/2021 | 0 | TK_Complete | 1653707999 | 54 | 1653707999_54
A206280 | TT_Task | T1-B :T1C3 Side wall Anti collision + spot - LH | 01/12/2021 | 02/12/2021 | 01/12/2021 | 25/12/2021 | 0 | TK_Complete | 1653707999 | 54 | 1653707999_54
A207110 | TT_Task | T1-B :T1C3 Roof Tooling Modification (Delay event) | 09/09/2021 | 15/09/2021 | 09/09/2021 | 16/09/2021 | 0 | TK_Complete | 1653707999 | 55 | 1653707999_55
A207140 | TT_Task | T1-B : Delay event : Sidewall skin Waiting | 22/10/2021 | 06/11/2021 | 22/10/2021 | 12/11/2021 | 0 | TK_Complete | 1653707999 | 56 | 1653707999_56
A207160 | TT_Task | T1-B :T1C UF Rejected, New UF to be produce | 06/12/2021 | 15/12/2021 | 06/12/2021 | 06/01/2022 | 0 | TK_Complete | 1653707999 | 57 | 1653707999_57
A206010 | TT_Task | DME : T1C2 Underframe Structure | 18/11/2021 | 24/11/2021 | 17/11/2021 | 15/12/2021 | 0 | TK_Complete | 1653707999 | 58 | 1653707999_58
A206020 | TT_Task | DME : T1C2 Underframe Bars ; Bracket | 10/12/2021 | 14/12/2021 | 10/12/2021 | 16/12/2021 | 0 | TK_Complete | 1653707999 | 59 | 1653707999_59
A206030 | TT_Task | DME : T1C2 Underframe Trim | 15/12/2021 | 15/12/2021 | 15/12/2021 | 15/12/2021 | 0 | TK_Complete | 1653707999 | 60 | 1653707999_60
A206040 | TT_Task | DME : T1C2 Side wall preloading - RH | 06/12/2021 | 09/12/2021 | 06/12/2021 | 09/12/2021 | 0 | TK_Complete | 1653707999 | 61 | 1653707999_61
A206050 | TT_Task | DME : T1C2 Side wall final (B;B) - RH | 14/12/2021 | 14/12/2021 | 14/12/2021 | 14/12/2021 | 0 | TK_Complete | 1653707999 | 62 | 1653707999_62
A206060 | TT_Task | DME : T1C2 Roof Preloading + Spot | 10/11/2021 | 17/11/2021 | 08/11/2021 | 15/11/2021 | 0 | TK_Complete | 1653707999 | 63 | 1653707999_63
A206070 | TT_Task | DME : T1C2 Roof Bars ; brackets | 13/11/2021 | 19/11/2021 | 15/11/2021 | 11/12/2021 | 0 | TK_Complete | 1653707999 | 64 | 1653707999_64
A206080 | TT_Task | DME : T1C2 Roof Trim | 14/12/2021 | 15/12/2021 | 15/12/2021 | 23/12/2021 | 0 | TK_Complete | 1653707999 | 65 | 1653707999_65
A206090 | TT_Task | DME : T1C2 Erection - 1 | 16/12/2021 | 21/12/2021 | 16/12/2021 | 31/12/2021 | 0 | TK_Complete | 1653707999 | 66 | 1653707999_66
A206100 | TT_Task | DME : T1C2 Erection - 2 | 29/12/2021 | 31/12/2021 | 01/01/2022 | 06/01/2022 | 0 | TK_Complete | 1653707999 | 66 | 1653707999_66
A206110 | TT_Task | DME : T1C2 Side wall preloading - LH | 14/12/2021 | 15/12/2021 | 14/12/2021 | 15/12/2021 | 0 | TK_Complete | 1653707999 | 61 | 1653707999_61
A206120 | TT_Task | DME : T1C2 Side wall final (B;B) - LH | 16/12/2021 | 16/12/2021 | 16/12/2021 | 16/12/2021 | 0 | TK_Complete | 1653707999 | 62 | 1653707999_62
A206130 | TT_Task | DME : T1C2 Side wall Anti collision + spot - RH | 13/12/2021 | 14/12/2021 | 13/12/2021 | 14/12/2021 | 0 | TK_Complete | 1653707999 | 67 | 1653707999_67
A206140 | TT_Task | DME : T1C2 Side wall Anti collision + spot - LH | 15/12/2021 | 16/12/2021 | 15/12/2021 | 16/12/2021 | 0 | TK_Complete | 1653707999 | 67 | 1653707999_67
A207150 | TT_Task | DME : Delay event - Carline delivery due to Eng Change ; development activity. | 01/11/2021 | 09/11/2021 | 01/11/2021 | 06/11/2021 | 0 | TK_Complete | 1653707999 | 68 | 1653707999_68
A206430 | TT_Task | M1-A : T1C5 Underframe Structure (Convert T1B to M1A) | 13/12/2021 | 17/12/2021 | 20/12/2021 | 11/01/2022 | 0 | TK_Complete | 1653707999 | 69 | 1653707999_69
A206440 | TT_Task | M1-A : T1C5 Underframe Bars ; Bracket | 24/12/2021 | 24/12/2021 | 24/12/2021 | 24/12/2021 | 0 | TK_Complete | 1653707999 | 33 | 1653707999_33
A206450 | TT_Task | M1-A : T1C5 Underframe Trim | 12/01/2022 | 13/01/2022 | 11/01/2022 | 19/01/2022 | 0 | TK_Complete | 1653707999 | 34 | 1653707999_34
A206460 | TT_Task | M1-A : T1C5 Side wall preloading - RH | 23/12/2021 | 23/12/2021 | 27/12/2021 | 01/01/2022 | 0 | TK_Complete | 1653707999 | 70 | 1653707999_70
A206470 | TT_Task | M1-A : T1C5 Side wall final (B;B) - RH | 06/01/2022 | 06/01/2022 | 07/01/2022 | 07/01/2022 | 0 | TK_Complete | 1653707999 | 36 | 1653707999_36
A206480 | TT_Task | M1-A : T1C5 Roof Preloading + Spot | 15/11/2021 | 19/11/2021 | 16/11/2021 | 30/11/2021 | 0 | TK_Complete | 1653707999 | 37 | 1653707999_37
A206490 | TT_Task | M1-A : T1C5 Roof Bars ; brackets | 24/12/2021 | 28/12/2021 | 14/12/2021 | 04/01/2022 | 0 | TK_Complete | 1653707999 | 38 | 1653707999_38
A206500 | TT_Task | M1-A : T1C5 Roof Trim | 05/01/2022 | 07/01/2022 | 10/01/2022 | 21/01/2022 | 0 | TK_Complete | 1653707999 | 39 | 1653707999_39
A206510 | TT_Task | M1-A : T1C5 Erection - 1 | 27/01/2022 | 31/01/2022 | 25/01/2022 | 01/02/2022 | 0 | TK_Complete | 1653707999 | 71 | 1653707999_71
A206520 | TT_Task | M1-A : T1C5 Erection - 2 | 02/02/2022 | 03/02/2022 | 01/02/2022 | 02/02/2022 | 0 | TK_Complete | 1653707999 | 71 | 1653707999_71
A206530 | TT_Task | M1-A : T1C5 Side wall preloading - LH | 05/01/2022 | 05/01/2022 | 06/01/2022 | 22/01/2022 | 0 | TK_Complete | 1653707999 | 70 | 1653707999_70
A206540 | TT_Task | M1-A : T1C5 Side wall final (B;B) - LH | 25/01/2022 | 25/01/2022 | 24/01/2022 | 24/01/2022 | 0 | TK_Complete | 1653707999 | 36 | 1653707999_36
A206550 | TT_Task | M1-A : T1C5 Side wall Anti collision + spot - RH | 28/12/2021 | 28/12/2021 | 28/12/2021 | 06/01/2022 | 0 | TK_Complete | 1653707999 | 72 | 1653707999_72
A206560 | TT_Task | M1-A : T1C5 Side wall Anti collision + spot - LH | 25/01/2022 | 25/01/2022 | 23/01/2022 | 23/01/2022 | 0 | TK_Complete | 1653707999 | 72 | 1653707999_72
A206570 | TT_Task | T-1.2 :T1C6 Underframe Structure | 27/12/2021 | 30/12/2021 | 25/12/2021 | 11/01/2022 | 0 | TK_Complete | 1653707999 | 73 | 1653707999_73
A206580 | TT_Task | T-1.2 :T1C6 Underframe Bars ; Bracket | 11/01/2022 | 17/01/2022 | 11/01/2022 | 25/01/2022 | 0 | TK_Complete | 1653707999 | 74 | 1653707999_74
A206590 | TT_Task | T-1.2 :T1C6 Underframe Trim | 25/01/2022 | 27/01/2022 | 27/01/2022 | 29/01/2022 | 0 | TK_Complete | 1653707999 | 75 | 1653707999_75
A206600 | TT_Task | T-1.2 :T1C6 Side wall preloading - RH | 24/01/2022 | 24/01/2022 | 25/01/2022 | 29/01/2022 | 0 | TK_Complete | 1653707999 | 76 | 1653707999_76
A206610 | TT_Task | T-1.2 :T1C6 Side wall final (B;B) - RH | 01/02/2022 | 01/02/2022 | 01/02/2022 | 01/02/2022 | 0 | TK_Complete | 1653707999 | 77 | 1653707999_77
A206620 | TT_Task | T-1.2 :T1C6 Roof Preloading + Spot | 21/12/2021 | 24/12/2021 | 21/12/2021 | 04/01/2022 | 0 | TK_Complete | 1653707999 | 78 | 1653707999_78
A206630 | TT_Task | T-1.2 :T1C6 Roof Bars ; brackets | 05/01/2022 | 08/01/2022 | 08/01/2022 | 22/01/2022 | 0 | TK_Complete | 1653707999 | 51 | 1653707999_51
A206640 | TT_Task | T-1.2 :T1C6 Roof Trim | 21/01/2022 | 24/01/2022 | 27/01/2022 | 31/01/2022 | 0 | TK_Complete | 1653707999 | 79 | 1653707999_79
A206650 | TT_Task | T-1.2 :T1C6 Erection - 1 | 04/02/2022 | 07/02/2022 | 07/02/2022 | nan | 0 | TK_Active | 1653707999 | 80 | 1653707999_80
A206660 | TT_Task | T-1.2 :T1C6 Erection - 2 | 10/02/2022 | 11/02/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 80 | 1653707999_80
A206670 | TT_Task | T-1.2 :T1C6 Side wall preloading - LH | 01/02/2022 | 01/02/2022 | 01/02/2022 | 04/02/2022 | 0 | TK_Complete | 1653707999 | 76 | 1653707999_76
A206680 | TT_Task | T-1.2 :T1C6 Side wall final (B;B) - LH | 03/02/2022 | 03/02/2022 | 06/02/2022 | 07/02/2022 | 0 | TK_Complete | 1653707999 | 77 | 1653707999_77
A206690 | TT_Task | T-1.2 :T1C6 Side wall Anti collision + spot - RH | 28/01/2022 | 28/01/2022 | 28/01/2022 | 31/01/2022 | 0 | TK_Complete | 1653707999 | 81 | 1653707999_81
A206700 | TT_Task | T-1.2 :T1C6 Side wall Anti collision + spot - LH | 02/02/2022 | 02/02/2022 | 04/02/2022 | 05/02/2022 | 0 | TK_Complete | 1653707999 | 81 | 1653707999_81
A206290 | TT_Task | DMB : T1C4 Underframe Structure | 10/01/2022 | 13/01/2022 | 10/01/2022 | 28/01/2022 | 0 | TK_Complete | 1653707999 | 82 | 1653707999_82
A206300 | TT_Task | DMB : T1C4 Underframe Bars ; Bracket | 28/01/2022 | 01/02/2022 | 28/01/2022 | nan | 0 | TK_Active | 1653707999 | 83 | 1653707999_83
A206310 | TT_Task | DMB : T1C4 Underframe Trim | 10/02/2022 | 11/02/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 84 | 1653707999_84
A206320 | TT_Task | DMB : T1C4 Side wall preloading - RH | 05/02/2022 | 05/02/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 85 | 1653707999_85
A206330 | TT_Task | DMB : T1C4 Side wall final (B;B) - RH | 07/02/2022 | 08/02/2022 | 07/02/2022 | nan | 28 | TK_Active | 1653707999 | 86 | 1653707999_86
A206340 | TT_Task | DMB : T1C4 Roof Preloading + Spot | 04/01/2022 | 07/01/2022 | 12/01/2022 | 25/01/2022 | 0 | TK_Complete | 1653707999 | 87 | 1653707999_87
A206350 | TT_Task | DMB : T1C4 Roof Bars ; brackets | 25/01/2022 | 29/01/2022 | 25/01/2022 | 01/02/2022 | 0 | TK_Complete | 1653707999 | 88 | 1653707999_88
A206360 | TT_Task | DMB : T1C4 Roof Trim | 07/02/2022 | 09/02/2022 | nan | nan | 16 | TK_NotStart | 1653707999 | 89 | 1653707999_89
A206370 | TT_Task | DMB : T1C4 Erection - 1 | 12/02/2022 | 15/02/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 90 | 1653707999_90
A206380 | TT_Task | DMB : T1C4 Erection - 2 | 16/02/2022 | 17/02/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 90 | 1653707999_90
A206390 | TT_Task | DMB : T1C4 Side wall preloading - LH | 07/02/2022 | 07/02/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 85 | 1653707999_85
A206400 | TT_Task | DMB : T1C4 Side wall final (B;B) - LH | 09/02/2022 | 09/02/2022 | nan | nan | 16 | TK_NotStart | 1653707999 | 86 | 1653707999_86
A206410 | TT_Task | DMB : T1C4 Side wall Anti collision + spot - RH | 05/02/2022 | 07/02/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 91 | 1653707999_91
A206420 | TT_Task | DMB : T1C4 Side wall Anti collision + spot - LH | 08/02/2022 | 08/02/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 91 | 1653707999_91
A207300 | TT_Task | M1B : Indus Input to MSSL / Savli (Rework Inst) | 17/01/2022 | 20/01/2022 | 17/01/2022 | 24/01/2022 | 0 | TK_Complete | 1653707999 | 92 | 1653707999_92
A207310 | TT_Task | M1B : Material Lead time from MSSL to Savli | 21/01/2022 | 31/01/2022 | 21/01/2022 | 31/01/2022 | 0 | TK_Complete | 1653707999 | 93 | 1653707999_93
A207330 | TT_Task | DME : Indus Input to MSSL / Savli (Rework Inst) | 17/01/2022 | 24/01/2022 | 17/01/2022 | 24/01/2022 | 0 | TK_Complete | 1653707999 | 94 | 1653707999_94
A207340 | TT_Task | DME : Material Lead time from MSSL to Savli | 25/01/2022 | 08/02/2022 | 25/01/2022 | nan | 0 | TK_Active | 1653707999 | 95 | 1653707999_95
A207360 | TT_Task | T1B : Indus Input to MSSL / Savli (Rework Inst) | 28/01/2022 | 02/02/2022 | 28/01/2022 | nan | 0 | TK_Active | 1653707999 | 96 | 1653707999_96
A207370 | TT_Task | T1B : Material Lead time from MSSL to Savli | 08/02/2022 | 11/02/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 97 | 1653707999_97
A207390 | TT_Task | M1A : Indus Input to MSSL / Savli (Rework Inst) | 24/01/2022 | 29/01/2022 | 24/01/2022 | 01/02/2022 | 0 | TK_Complete | 1653707999 | 92 | 1653707999_92
A207400 | TT_Task | M1A : Material Lead time from MSSL to Savli | 01/02/2022 | 14/02/2022 | nan | nan | 32 | TK_NotStart | 1653707999 | 93 | 1653707999_93
A207420 | TT_Task | T1A : Indus Input to MSSL / Savli (Rework Inst) | 07/02/2022 | 10/02/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 96 | 1653707999_96
A207430 | TT_Task | T1A : Material Lead time from MSSL to Savli | 11/02/2022 | 22/02/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 97 | 1653707999_97
A207450 | TT_Task | DMB : Indus Input to MSSL / Savli (Rework Inst) | 07/02/2022 | 11/02/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 94 | 1653707999_94
A207460 | TT_Task | DMB : Material Lead time from MSSL to Savli | 12/02/2022 | 26/02/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 95 | 1653707999_95
A205860 | TT_Task | M1-B :T1C1 Window ; Floor Trim | 22/12/2021 | 24/12/2021 | 22/12/2021 | 17/01/2022 | 0 | TK_Complete | 1653707999 | 98 | 1653707999_98
A205870 | TT_Task | M1-B :T1C1 Doors installation | 18/01/2022 | 20/01/2022 | 18/01/2022 | nan | 0 | TK_Active | 1653707999 | 99 | 1653707999_99
A207170 | TT_Task | M1-B : Quality Clearance ; completion of Pending CWS work | 06/12/2021 | 16/12/2021 | 06/12/2021 | 22/12/2021 | 0 | TK_Complete | 1653707999 | 100 | 1653707999_100
A207280 | TT_Task | Delay event : Door Header Installation solution + Installation | 01/11/2021 | 12/11/2021 | 06/12/2021 | 07/01/2022 | 0 | TK_Complete | 1653707999 | 101 | 1653707999_101
A205740 | TT_Task | T-1.1 :T1C3 Window ; Floor Trim | 31/01/2022 | 02/02/2022 | 25/01/2022 | 02/02/2022 | 0 | TK_Complete | 1653707999 | 102 | 1653707999_102
A205750 | TT_Task | T-1.1 :T1C3 Doors installation | 14/02/2022 | 16/02/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 103 | 1653707999_103
A205720 | TT_Task | DME : T1C2 Window ; Floor Trim | 18/01/2022 | 20/01/2022 | 18/01/2022 | 29/01/2022 | 0 | TK_Complete | 1653707999 | 104 | 1653707999_104
A205730 | TT_Task | DME : T1C2 Doors installation ; Cab pre-assembly | 10/02/2022 | 12/02/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 105 | 1653707999_105
A206710 | TT_Task | M1-A : T1C5 Window ; Floor Trim | 03/02/2022 | 05/02/2022 | 03/02/2022 | nan | 0 | TK_Active | 1653707999 | 98 | 1653707999_98
A206720 | TT_Task | M1-A : T1C5 Doors installation | 17/02/2022 | 19/02/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 99 | 1653707999_99
A206730 | TT_Task | T-1.2 :T1C6 Window ; Floor Trim | 12/02/2022 | 15/02/2022 | nan | nan | 8 | TK_NotStart | 1653707999 | 102 | 1653707999_102
A206740 | TT_Task | T-1.2 :T1C6 Doors installation ; Cab pre-assembly | 17/02/2022 | 19/02/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 106 | 1653707999_106
A205880 | TT_Task | DMB : T1C4 Window ; Floor Trim | 18/02/2022 | 21/02/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 107 | 1653707999_107
A205890 | TT_Task | DMB : T1C4 Doors installation ; Cab pre-assembly | 22/02/2022 | 24/02/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 108 | 1653707999_108
A205900 | TT_Task | M1-B :T1C1 Roof Equip ; Interior | 10/02/2022 | 10/02/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 109 | 1653707999_109
A205910 | TT_Task | M1-B :T1C1 U/F Equip ; Cab | 14/02/2022 | 15/02/2022 | 28/01/2022 | nan | 0 | TK_Active | 1653707999 | 110 | 1653707999_110
A205920 | TT_Task | M1-B :T1C1 Exterior ; Interior1 | 10/02/2022 | 12/02/2022 | 02/02/2022 | nan | 0 | TK_Active | 1653707999 | 111 | 1653707999_111
A205930 | TT_Task | M1-B :T1C1 Exterior ; Interior2 | 10/02/2022 | 10/02/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 111 | 1653707999_111
A205940 | TT_Task | M1-B :T1C1 Exterior ; Interior3 | 10/02/2022 | 11/02/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 111 | 1653707999_111
A205950 | TT_Task | M1-B :T1C1 Bogie Installation | 12/02/2022 | 14/02/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 112 | 1653707999_112
A206750 | TT_Task | M1-B :T1C1 Underframe Cable Duct ; Piping-01 | 04/02/2022 | 10/02/2022 | 25/01/2022 | nan | 0 | TK_Active | 1653707999 | 113 | 1653707999_113
A207180 | TT_Task | M1B : Retrofit (Before Testing) - Parking Station | 12/02/2022 | 12/02/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 114 | 1653707999_114
A207190 | TT_Task | M1B : Retrofit (After Single Car Testing) - AK line need to use | 22/02/2022 | 24/02/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 115 | 1653707999_115
A207220 | TT_Task | M1-B :T1C1 Static Test | 12/02/2022 | 12/02/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 116 | 1653707999_116
A206760 | TT_Task | T-1.1 :T1C3 Roof Equip ; Interior | 23/02/2022 | 23/02/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 117 | 1653707999_117
A206770 | TT_Task | T-1.1 :T1C3 U/F Equip ; Cab | 19/02/2022 | 22/02/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 118 | 1653707999_118
A206780 | TT_Task | T-1.1 :T1C3 Exterior ; Interior1 | 10/02/2022 | 12/02/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 119 | 1653707999_119
A206790 | TT_Task | T-1.1 :T1C3 Exterior ; Interior2 | 14/02/2022 | 14/02/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 119 | 1653707999_119
A206800 | TT_Task | T-1.1 :T1C3 Exterior ; Interior3 | 23/02/2022 | 23/02/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 119 | 1653707999_119
A206810 | TT_Task | T1-B :T1C3 Bogie Installation + HVAC Retrofit | 25/02/2022 | 26/02/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 120 | 1653707999_120
A206820 | TT_Task | T-1.1 :T1C3 Underframe Cable Duct ; Piping-01 | 12/02/2022 | 18/02/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 121 | 1653707999_121
A207240 | TT_Task | T1-B :T1C1 Static Test | 23/02/2022 | 24/02/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 122 | 1653707999_122
A206830 | TT_Task | DME : T1C2 Roof Equip ; Interior | 17/02/2022 | 17/02/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 123 | 1653707999_123
A206840 | TT_Task | DME : T1C2 U/F Equip ; Cab | 14/02/2022 | 16/02/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 124 | 1653707999_124
A206850 | TT_Task | DME : T1C2 Exterior ; Interior1 | 14/02/2022 | 16/02/2022 | 28/01/2022 | nan | 0 | TK_Active | 1653707999 | 125 | 1653707999_125
A206860 | TT_Task | DME : T1C2 Exterior ; Interior2 | 17/02/2022 | 19/02/2022 | 08/02/2022 | nan | 0 | TK_Active | 1653707999 | 125 | 1653707999_125
A206870 | TT_Task | DME : T1C2 Exterior ; Interior3 | 17/02/2022 | 17/02/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 125 | 1653707999_125
A206880 | TT_Task | DME : T1C2 Bogie Installation | 19/02/2022 | 21/02/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 126 | 1653707999_126
A206890 | TT_Task | DME : T1C2 Underframe Cable Duct ; Piping-01 | 09/02/2022 | 11/02/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 127 | 1653707999_127
A207200 | TT_Task | DME : Retrofit (Before Testing) - Parking Station | 19/02/2022 | 19/02/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 114 | 1653707999_114
A207210 | TT_Task | DME : Retrofit (After Single Car Testing) - AK line need to use | 23/02/2022 | 26/02/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 115 | 1653707999_115
A207230 | TT_Task | DME :T1C1 Static Test | 17/02/2022 | 18/02/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 128 | 1653707999_128
A206970 | TT_Task | M1-A : T1C5 Roof Equip ; Interior | 26/02/2022 | 01/03/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 109 | 1653707999_109
A206980 | TT_Task | M1-A : T1C5 U/F Equip ; Cab | 23/02/2022 | 25/02/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 110 | 1653707999_110
A206990 | TT_Task | M1-A : T1C5 Exterior ; Interior1 | 17/02/2022 | 19/02/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 129 | 1653707999_129
A207000 | TT_Task | M1-A : T1C5 Exterior ; Interior2 | 19/02/2022 | 22/02/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 129 | 1653707999_129
A207010 | TT_Task | M1-A : T1C5 Exterior ; Interior3 | 02/03/2022 | 04/03/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 129 | 1653707999_129
A207020 | TT_Task | M1-A : T1C5 Bogie Installation + HVAC Retrofit | 08/03/2022 | 11/03/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 120 | 1653707999_120
A207030 | TT_Task | M1-A : T1C5 Underframe Cable Duct ; Piping-01 | 19/02/2022 | 22/02/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 113 | 1653707999_113
A207250 | TT_Task | M1-A :T1C1 Static Test | 05/03/2022 | 07/03/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 116 | 1653707999_116
A207040 | TT_Task | T-1.2 :T1C6 Roof Equip ; Interior | 02/03/2022 | 04/03/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 117 | 1653707999_117
A207050 | TT_Task | T-1.2 :T1C6 U/F Equip ; Cab | 26/02/2022 | 01/03/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 130 | 1653707999_130
A207060 | TT_Task | T-1.2 :T1C6 Exterior ; Interior1 | 17/02/2022 | 19/02/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 131 | 1653707999_131
A207070 | TT_Task | T-1.2 :T1C6 Exterior ; Interior2 | 21/02/2022 | 23/02/2022 | nan | nan | 8 | TK_NotStart | 1653707999 | 131 | 1653707999_131
A207080 | TT_Task | T-1.2 :T1C6 Exterior ; Interior3 | 05/03/2022 | 08/03/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 131 | 1653707999_131
A207090 | TT_Task | T-1.2 :T1C6 Bogie Installation + HVAC Retrofit | 12/03/2022 | 16/03/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 120 | 1653707999_120
A207100 | TT_Task | T-1.2 :T1C6 Underframe Cable Duct ; Piping-01 | 23/02/2022 | 25/02/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 121 | 1653707999_121
A207260 | TT_Task | T-1.2 :T1C1 Static Test | 09/03/2022 | 10/03/2022 | nan | nan | 8 | TK_NotStart | 1653707999 | 122 | 1653707999_122
A206900 | TT_Task | DMB : T1C4 Roof Equip ; Interior | 07/03/2022 | 09/03/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 132 | 1653707999_132
A206910 | TT_Task | DMB : T1C4 U/F Equip ; Cab | 03/03/2022 | 05/03/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 133 | 1653707999_133
A206920 | TT_Task | DMB : T1C4 Exterior ; Interior1 | 22/02/2022 | 24/02/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 134 | 1653707999_134
A206930 | TT_Task | DMB : T1C4 Exterior ; Interior2 | 25/02/2022 | 28/02/2022 | nan | nan | 16 | TK_NotStart | 1653707999 | 134 | 1653707999_134
A206940 | TT_Task | DMB : T1C4 Exterior ; Interior3 | 10/03/2022 | 12/03/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 134 | 1653707999_134
A206950 | TT_Task | DMB : T1C4 Bogie Installation + HVAC Retrofit | 17/03/2022 | 22/03/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 135 | 1653707999_135
A206960 | TT_Task | DMB : T1C4 Underframe Cable Duct ; Piping-01 | 28/02/2022 | 02/03/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 136 | 1653707999_136
A207270 | TT_Task | DMB :T1C1 Static Test | 14/03/2022 | 15/03/2022 | nan | nan | 8 | TK_NotStart | 1653707999 | 128 | 1653707999_128
A208220 | TT_Task | Single Car Testing | 31/01/2022 | 31/01/2022 | nan | nan | 10551 | TK_NotStart | 1653707999 | 137 | 1653707999_137
A207480 | TT_Task | Water Test | 25/02/2022 | 25/02/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 138 | 1653707999_138
A207490 | TT_Task | Protective bonding and return current test | 15/02/2022 | 19/02/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 139 | 1653707999_139
A207500 | TT_Task | Mechanical air tightness test | 21/02/2022 | 21/02/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 140 | 1653707999_140
A207510 | TT_Task | Static Gauge test | 26/02/2022 | 26/02/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 141 | 1653707999_141
A207520 | TT_Task | Weighing Test at AW0 | 28/02/2022 | 28/02/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 142 | 1653707999_142
A207470 | TT_Task | Lifting ability test (Type test) | 05/03/2022 | 07/03/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 143 | 1653707999_143
A207530 | TT_Task | Weighing Test at AW4 | 07/03/2022 | 10/03/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 144 | 1653707999_144
A207540 | TT_Task | Clearance tests (car body to bogie ) at AW0 | 11/03/2022 | 11/03/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 145 | 1653707999_145
A207550 | TT_Task | Clearance tests (car body to bogie ) at AW4 | 10/03/2022 | 11/03/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 145 | 1653707999_145
A208190 | TT_Task | Sway Test ; Wheel Unloading | 28/02/2022 | 05/03/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 146 | 1653707999_146
A208230 | TT_Task | Single Car Testing | 31/01/2022 | 31/01/2022 | nan | nan | 10551 | TK_NotStart | 1653707999 | 137 | 1653707999_137
A207570 | TT_Task | Water Test | 28/02/2022 | 28/02/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 138 | 1653707999_138
A207580 | TT_Task | Protective bonding and return current test | 01/03/2022 | 01/03/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 139 | 1653707999_139
A207590 | TT_Task | Mechanical air tightness test | 01/03/2022 | 02/03/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 140 | 1653707999_140
A207600 | TT_Task | Static Gauge test | 02/03/2022 | 03/03/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 141 | 1653707999_141
A207610 | TT_Task | Weighing Test at AW0 | 03/03/2022 | 03/03/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 142 | 1653707999_142
A207560 | TT_Task | Lifting ability test (Type test) | 04/03/2022 | 04/03/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 143 | 1653707999_143
A207620 | TT_Task | Weighing Test at AW4 | 05/03/2022 | 07/03/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 144 | 1653707999_144
A207630 | TT_Task | Clearance tests (car body to bogie ) at AW0 | 09/03/2022 | 09/03/2022 | nan | nan | 20 | TK_NotStart | 1653707999 | 145 | 1653707999_145
A207640 | TT_Task | Clearance tests (car body to bogie ) at AW4 | 08/03/2022 | 08/03/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 145 | 1653707999_145
A208240 | TT_Task | Single Car Testing | 31/01/2022 | 31/01/2022 | nan | nan | 10551 | TK_NotStart | 1653707999 | 137 | 1653707999_137
A207650 | TT_Task | Water Test | 26/02/2022 | 28/02/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 138 | 1653707999_138
A207660 | TT_Task | Protective bonding and return current test | 22/02/2022 | 22/02/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 139 | 1653707999_139
A207670 | TT_Task | Mechanical air tightness test | 22/02/2022 | 23/02/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 140 | 1653707999_140
A207680 | TT_Task | Static Gauge test | 28/02/2022 | 01/03/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 141 | 1653707999_141
A207690 | TT_Task | Weighing Test at AW0 | 01/03/2022 | 01/03/2022 | nan | nan | 28 | TK_NotStart | 1653707999 | 142 | 1653707999_142
A208210 | TT_Task | Sway Test ; Wheel Unloading | 05/03/2022 | 11/03/2022 | nan | nan | 4 | TK_NotStart | 1653707999 | 146 | 1653707999_146
A208250 | TT_Task | Single Car Testing | 31/01/2022 | 31/01/2022 | nan | nan | 10551 | TK_NotStart | 1653707999 | 137 | 1653707999_137
A207700 | TT_Task | Water Test | 12/03/2022 | 12/03/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 138 | 1653707999_138
A207710 | TT_Task | Protective bonding and return current test | 14/03/2022 | 14/03/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 139 | 1653707999_139
A207720 | TT_Task | Mechanical air tightness test | 15/03/2022 | 15/03/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 140 | 1653707999_140
A207730 | TT_Task | Static Gauge test | 16/03/2022 | 16/03/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 141 | 1653707999_141
A207740 | TT_Task | Weighing Test at AW0 | 17/03/2022 | 17/03/2022 | nan | nan | 60 | TK_NotStart | 1653707999 | 142 | 1653707999_142
A207750 | TT_Task | Water Test | 17/03/2022 | 17/03/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 138 | 1653707999_138
A207760 | TT_Task | Protective bonding and return current test | 19/03/2022 | 19/03/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 139 | 1653707999_139
A207770 | TT_Task | Mechanical air tightness test | 19/03/2022 | 21/03/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 140 | 1653707999_140
A207780 | TT_Task | Static Gauge test | 21/03/2022 | 22/03/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 141 | 1653707999_141
A207790 | TT_Task | Weighing Test at AW0 | 22/03/2022 | 22/03/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 142 | 1653707999_142
A208200 | TT_Task | Sway Test ; Wheel Unloading | 23/03/2022 | 26/03/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 146 | 1653707999_146
A207800 | TT_Task | Water Test | 23/03/2022 | 23/03/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 138 | 1653707999_138
A207810 | TT_Task | Protective bonding and return current test | 24/03/2022 | 24/03/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 139 | 1653707999_139
A207820 | TT_Task | Mechanical air tightness test | 24/03/2022 | 25/03/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 140 | 1653707999_140
A207830 | TT_Task | Static Gauge test | 25/03/2022 | 26/03/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 141 | 1653707999_141
A207840 | TT_Task | Weighing Test at AW0 | 26/03/2022 | 26/03/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 142 | 1653707999_142
A207850 | TT_Task | Inter car couple for 3 car formation | 12/03/2022 | 12/03/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 147 | 1653707999_147
A207860 | TT_Task | Data link Test (MVB,IP etc..) | 14/03/2022 | 14/03/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 148 | 1653707999_148
A207870 | TT_Task | Battery start up for 3 car, Battery contactor-Normal control, Hex switch setting, Cab activation and Battery earth fault | 14/03/2022 | 16/03/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 149 | 1653707999_149
A207880 | TT_Task | TCMS Software downloading | 17/03/2022 | 21/03/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 150 | 1653707999_150
A207890 | TT_Task | Auxilary Power supply check, 3 phase CB check, Shore supply check, 1;3 phase load check and Battery charger test. | 22/03/2022 | 22/03/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 151 | 1653707999_151
A207900 | TT_Task | Automatic Coupler Routine Test | 17/03/2022 | 17/03/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 152 | 1653707999_152
A207910 | TT_Task | FSD system routine test | 17/03/2022 | 17/03/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 153 | 1653707999_153
A207920 | TT_Task | Brake System Static Routine Test | 22/03/2022 | 22/03/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 154 | 1653707999_154
A207930 | TT_Task | Door Routine test for saloon, cab, partition,intermediate and emergency doors | 22/03/2022 | 22/03/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 155 | 1653707999_155
A207940 | TT_Task | Wind screen wiper and washer, Horn and windscreen demister routine test | 22/03/2022 | 22/03/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 156 | 1653707999_156
A207950 | TT_Task | Traction Static test | 22/03/2022 | 22/03/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 157 | 1653707999_157
A207960 | TT_Task | HVAC system routine test | 17/03/2022 | 17/03/2022 | nan | nan | 24 | TK_NotStart | 1653707999 | 158 | 1653707999_158
A207970 | TT_Task | High Voltage Test | 22/03/2022 | 22/03/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 159 | 1653707999_159
A207980 | TT_Task | PA/PIS system routine test | 22/03/2022 | 22/03/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 160 | 1653707999_160
A207990 | TT_Task | CCTV system routine test | 22/03/2022 | 22/03/2022 | nan | nan | 40 | TK_NotStart | 1653707999 | 161 | 1653707999_161
A208000 | TT_Task | Inter car couple for 6 car formation | 27/03/2022 | 27/03/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 147 | 1653707999_147
A208010 | TT_Task | Data link Test (MVB,IP etc..) | 28/03/2022 | 28/03/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 148 | 1653707999_148
A208020 | TT_Task | Battery start up for 3 car, Battery contactor-Normal control, Hex switch setting, Cab activation and Battery earth fault | 29/03/2022 | 30/03/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 149 | 1653707999_149
A208030 | TT_Task | TCMS Software downloading, TCMS communication check for the MVB and TCMS I/O test | 31/03/2022 | 10/04/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 162 | 1653707999_162
A208040 | TT_Task | Auxilary Power supply check, 3 phase CB check, Shore supply check, 1;3 phase load check and Battery charger test. | 03/04/2022 | 06/04/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 151 | 1653707999_151
A208050 | TT_Task | Automatic Coupler Routine Test | 31/03/2022 | 31/03/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 152 | 1653707999_152
A208060 | TT_Task | FSD system routine test | 31/03/2022 | 31/03/2022 | nan | nan | 112 | TK_NotStart | 1653707999 | 153 | 1653707999_153
A208070 | TT_Task | Brake System Static Routine Test | 07/04/2022 | 10/04/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 154 | 1653707999_154
A208080 | TT_Task | Door Routine test for saloon, cab, partition,intermediate and emergency doors | 07/04/2022 | 07/04/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 155 | 1653707999_155
A208090 | TT_Task | Wind screen wiper and washer, Horn and windscreen demister routine test | 07/04/2022 | 07/04/2022 | nan | nan | 32 | TK_NotStart | 1653707999 | 156 | 1653707999_156
A208100 | TT_Task | Traction Static test | 11/04/2022 | 12/04/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 157 | 1653707999_157
A208110 | TT_Task | HVAC system routine test | 13/04/2022 | 13/04/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 158 | 1653707999_158
A208120 | TT_Task | High Voltage Test | 13/04/2022 | 13/04/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 159 | 1653707999_159
A208130 | TT_Task | PA/PIS system routine test (at Depot) | 14/04/2022 | 14/04/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 160 | 1653707999_160
A208140 | TT_Task | CCTV system routine test (at Depot) | 14/04/2022 | 14/04/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 161 | 1653707999_161
A208150 | TT_Task | Compressed air 6 car lekage routine test | 03/04/2022 | 03/04/2022 | nan | nan | 32 | TK_NotStart | 1653707999 | 163 | 1653707999_163
A208160 | TT_Task | Initial movement, speed pickups, propulsion test (low speed) | 14/04/2022 | 14/04/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 164 | 1653707999_164
A208170 | TT_Task | 6 Car Un coupling | 14/04/2022 | 15/04/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 165 | 1653707999_165
A205960 | TT_Task | TS (RRTS prototype 1) - Logistic | 18/04/2022 | 24/04/2022 | nan | nan | 14099 | TK_NotStart | 1653707999 | 166 | 1653707999_166
A208180 | TT_Task | Retrofit | 15/04/2022 | 18/04/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 167 | 1653707999_167
A202950 | TT_Task | M1-B : T1C1 Underframe Structure | 27/09/2021 | 04/10/2021 | 27/09/2021 | 17/10/2021 | 0 | TK_Complete | 1653707999 | 32 | 1653707999_32
A202960 | TT_Task | M1-B :T1C1 Underframe Bars ; Bracket | 20/10/2021 | 22/10/2021 | 18/10/2021 | 27/10/2021 | 0 | TK_Complete | 1653707999 | 33 | 1653707999_33
A202970 | TT_Task | M1-B :T1C1 Underframe Trim | 27/10/2021 | 27/10/2021 | 27/10/2021 | 27/10/2021 | 0 | TK_Complete | 1653707999 | 34 | 1653707999_34
A202980 | TT_Task | M1-B :T1C1 Side wall preloading - RH | 14/09/2021 | 18/09/2021 | 03/09/2021 | 20/09/2021 | 0 | TK_Complete | 1653707999 | 35 | 1653707999_35
A202990 | TT_Task | M1-B :T1C1 Side wall final (B;B) - RH | 07/10/2021 | 07/10/2021 | 11/10/2021 | 23/10/2021 | 0 | TK_Complete | 1653707999 | 36 | 1653707999_36
A203000 | TT_Task | M1-B :T1C1 Roof Preloading + Spot | 06/09/2021 | 01/10/2021 | 16/07/2021 | 13/09/2021 | 0 | TK_Complete | 1653707999 | 37 | 1653707999_37
A203010 | TT_Task | M1-B :T1C1 Roof Bars ; brackets | 09/09/2021 | 16/09/2021 | 14/09/2021 | 28/09/2021 | 0 | TK_Complete | 1653707999 | 38 | 1653707999_38
A203020 | TT_Task | M1-B :T1C1 Roof Trim | 30/09/2021 | 05/10/2021 | 01/10/2021 | 08/10/2021 | 0 | TK_Complete | 1653707999 | 39 | 1653707999_39
A203030 | TT_Task | M1-B :T1C1 Erection - 1 | 27/10/2021 | 08/11/2021 | 28/10/2021 | 03/12/2021 | 0 | TK_Complete | 1653707999 | 40 | 1653707999_40
A203040 | TT_Task | M1-B :T1C1 Erection - 2 | 04/12/2021 | 04/12/2021 | 04/12/2021 | 06/12/2021 | 0 | TK_Complete | 1653707999 | 40 | 1653707999_40
A203150 | TT_Task | M1-B :T1C1 Side wall preloading - LH | 07/10/2021 | 08/10/2021 | 10/10/2021 | 14/10/2021 | 0 | TK_Complete | 1653707999 | 35 | 1653707999_35
A203160 | TT_Task | M1-B :T1C1 Side wall final (B;B) - LH | 22/10/2021 | 22/10/2021 | 22/10/2021 | 22/10/2021 | 0 | TK_Complete | 1653707999 | 36 | 1653707999_36
A203170 | TT_Task | M1-B :T1C1 Side wall Anti collision - RH | 21/09/2021 | 24/09/2021 | 21/09/2021 | 29/09/2021 | 0 | TK_Complete | 1653707999 | 41 | 1653707999_41
A203180 | TT_Task | M1-B :T1C1 Side wall Anti collision + spot - LH | 20/10/2021 | 21/10/2021 | 20/10/2021 | 22/10/2021 | 0 | TK_Complete | 1653707999 | 42 | 1653707999_42
A204390 | TT_Task | M1-B :T1C1 Side wall Re-Preloading - RH (Delay Event due to Part rejection) | 30/09/2021 | 01/10/2021 | 29/09/2021 | 04/10/2021 | 0 | TK_Complete | 1653707999 | 43 | 1653707999_43
A204400 | TT_Task | M1-B :T1C1 Side wall spot - RH | 01/10/2021 | 02/10/2021 | 05/10/2021 | 10/10/2021 | 0 | TK_Complete | 1653707999 | 44 | 1653707999_44
A203330 | TT_Task | T1-B :T1C3 Underframe Structure + Spot | 18/10/2021 | 27/10/2021 | 18/10/2021 | 23/11/2021 | 0 | TK_Complete | 1653707999 | 45 | 1653707999_45
A203340 | TT_Task | T1-B :T1C3 Underframe Bars ; Bracket | 23/11/2021 | 25/11/2021 | 23/11/2021 | 30/11/2021 | 0 | TK_Complete | 1653707999 | 46 | 1653707999_46
A203350 | TT_Task | T1-B :T1C3 Underframe Trim | 30/11/2021 | 02/12/2021 | 01/12/2021 | 04/12/2021 | 0 | TK_Complete | 1653707999 | 47 | 1653707999_47
A203360 | TT_Task | T1-B :T1C3 Side wall preloading - RH | 13/11/2021 | 13/11/2021 | 10/11/2021 | 21/12/2021 | 0 | TK_Complete | 1653707999 | 48 | 1653707999_48
A203370 | TT_Task | T1-B :T1C3 Side wall final (B;B) - RH | 27/11/2021 | 27/11/2021 | 27/11/2021 | 24/12/2021 | 0 | TK_Complete | 1653707999 | 49 | 1653707999_49
A203380 | TT_Task | T1-B :T1C3 Roof Preloading + Spot (4 D waiting for IQC) | 17/09/2021 | 30/09/2021 | 17/09/2021 | 12/10/2021 | 0 | TK_Complete | 1653707999 | 50 | 1653707999_50
A203390 | TT_Task | T1-B :T1C3 Roof Bars ; brackets | 13/10/2021 | 20/10/2021 | 13/10/2021 | 27/10/2021 | 0 | TK_Complete | 1653707999 | 51 | 1653707999_51
A203400 | TT_Task | T1-B :T1C3 Roof Trim | 01/11/2021 | 08/11/2021 | 10/11/2021 | 28/12/2021 | 0 | TK_Complete | 1653707999 | 52 | 1653707999_52
A203410 | TT_Task | T1-B :T1C3 Erection - 1 | 06/01/2022 | 10/01/2022 | 07/01/2022 | nan | 0 | TK_Active | 1653707999 | 53 | 1653707999_53
A203420 | TT_Task | T1-B :T1C3 Erection - 2 | 31/01/2022 | 02/02/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 53 | 1653707999_53
A203430 | TT_Task | T1-B :T1C3 Side wall preloading - LH | 23/11/2021 | 23/11/2021 | 23/11/2021 | 23/12/2021 | 0 | TK_Complete | 1653707999 | 48 | 1653707999_48
A203440 | TT_Task | T1-B :T1C3 Side wall final (B;B) - LH | 06/12/2021 | 06/12/2021 | 06/12/2021 | 28/12/2021 | 0 | TK_Complete | 1653707999 | 49 | 1653707999_49
A203450 | TT_Task | T1-B :T1C3 Side wall Anti collision + spot - RH | 18/11/2021 | 19/11/2021 | 17/11/2021 | 24/12/2021 | 0 | TK_Complete | 1653707999 | 54 | 1653707999_54
A203460 | TT_Task | T1-B :T1C3 Side wall Anti collision + spot - LH | 01/12/2021 | 02/12/2021 | 01/12/2021 | 25/12/2021 | 0 | TK_Complete | 1653707999 | 54 | 1653707999_54
A204380 | TT_Task | T1-B :T1C3 Roof Tooling Modification (Delay event) | 09/09/2021 | 15/09/2021 | 09/09/2021 | 16/09/2021 | 0 | TK_Complete | 1653707999 | 55 | 1653707999_55
A204410 | TT_Task | T1-B : Delay event : Sidewall skin Waiting | 22/10/2021 | 06/11/2021 | 22/10/2021 | 12/11/2021 | 0 | TK_Complete | 1653707999 | 56 | 1653707999_56
A204430 | TT_Task | T1-B :T1C UF Rejected, New UF to be produce | 06/12/2021 | 15/12/2021 | 06/12/2021 | 06/01/2022 | 0 | TK_Complete | 1653707999 | 57 | 1653707999_57
A203190 | TT_Task | DME : T1C2 Underframe Structure | 18/11/2021 | 24/11/2021 | 17/11/2021 | 15/12/2021 | 0 | TK_Complete | 1653707999 | 58 | 1653707999_58
A203200 | TT_Task | DME : T1C2 Underframe Bars ; Bracket | 10/12/2021 | 14/12/2021 | 10/12/2021 | 16/12/2021 | 0 | TK_Complete | 1653707999 | 59 | 1653707999_59
A203210 | TT_Task | DME : T1C2 Underframe Trim | 15/12/2021 | 15/12/2021 | 15/12/2021 | 15/12/2021 | 0 | TK_Complete | 1653707999 | 60 | 1653707999_60
A203220 | TT_Task | DME : T1C2 Side wall preloading - RH | 06/12/2021 | 09/12/2021 | 06/12/2021 | 09/12/2021 | 0 | TK_Complete | 1653707999 | 61 | 1653707999_61
A203230 | TT_Task | DME : T1C2 Side wall final (B;B) - RH | 14/12/2021 | 14/12/2021 | 14/12/2021 | 14/12/2021 | 0 | TK_Complete | 1653707999 | 62 | 1653707999_62
A203240 | TT_Task | DME : T1C2 Roof Preloading + Spot | 10/11/2021 | 17/11/2021 | 08/11/2021 | 15/11/2021 | 0 | TK_Complete | 1653707999 | 63 | 1653707999_63
A203250 | TT_Task | DME : T1C2 Roof Bars ; brackets | 13/11/2021 | 19/11/2021 | 15/11/2021 | 11/12/2021 | 0 | TK_Complete | 1653707999 | 64 | 1653707999_64
A203260 | TT_Task | DME : T1C2 Roof Trim | 14/12/2021 | 15/12/2021 | 15/12/2021 | 23/12/2021 | 0 | TK_Complete | 1653707999 | 65 | 1653707999_65
A203270 | TT_Task | DME : T1C2 Erection - 1 | 16/12/2021 | 21/12/2021 | 16/12/2021 | 31/12/2021 | 0 | TK_Complete | 1653707999 | 66 | 1653707999_66
A203280 | TT_Task | DME : T1C2 Erection - 2 | 29/12/2021 | 31/12/2021 | 01/01/2022 | 06/01/2022 | 0 | TK_Complete | 1653707999 | 66 | 1653707999_66
A203290 | TT_Task | DME : T1C2 Side wall preloading - LH | 14/12/2021 | 15/12/2021 | 14/12/2021 | 15/12/2021 | 0 | TK_Complete | 1653707999 | 61 | 1653707999_61
A203300 | TT_Task | DME : T1C2 Side wall final (B;B) - LH | 16/12/2021 | 16/12/2021 | 16/12/2021 | 16/12/2021 | 0 | TK_Complete | 1653707999 | 62 | 1653707999_62
A203310 | TT_Task | DME : T1C2 Side wall Anti collision + spot - RH | 13/12/2021 | 14/12/2021 | 13/12/2021 | 14/12/2021 | 0 | TK_Complete | 1653707999 | 67 | 1653707999_67
A203320 | TT_Task | DME : T1C2 Side wall Anti collision + spot - LH | 15/12/2021 | 16/12/2021 | 15/12/2021 | 16/12/2021 | 0 | TK_Complete | 1653707999 | 67 | 1653707999_67
A204420 | TT_Task | DME : Delay event - Carline delivery due to Eng Change ; development activity. | 01/11/2021 | 09/11/2021 | 01/11/2021 | 06/11/2021 | 0 | TK_Complete | 1653707999 | 68 | 1653707999_68
A203610 | TT_Task | M1-A : T1C5 Underframe Structure (Convert T1B to M1A) | 13/12/2021 | 17/12/2021 | 20/12/2021 | 11/01/2022 | 0 | TK_Complete | 1653707999 | 69 | 1653707999_69
A203620 | TT_Task | M1-A : T1C5 Underframe Bars ; Bracket | 24/12/2021 | 24/12/2021 | 24/12/2021 | 24/12/2021 | 0 | TK_Complete | 1653707999 | 33 | 1653707999_33
A203630 | TT_Task | M1-A : T1C5 Underframe Trim | 12/01/2022 | 13/01/2022 | 11/01/2022 | nan | 0 | TK_Active | 1653707999 | 34 | 1653707999_34
A203640 | TT_Task | M1-A : T1C5 Side wall preloading - RH | 23/12/2021 | 23/12/2021 | 27/12/2021 | 01/01/2022 | 0 | TK_Complete | 1653707999 | 70 | 1653707999_70
A203650 | TT_Task | M1-A : T1C5 Side wall final (B;B) - RH | 06/01/2022 | 06/01/2022 | 07/01/2022 | 07/01/2022 | 0 | TK_Complete | 1653707999 | 36 | 1653707999_36
A203660 | TT_Task | M1-A : T1C5 Roof Preloading + Spot | 15/11/2021 | 19/11/2021 | 16/11/2021 | 30/11/2021 | 0 | TK_Complete | 1653707999 | 37 | 1653707999_37
A203670 | TT_Task | M1-A : T1C5 Roof Bars ; brackets | 24/12/2021 | 28/12/2021 | 14/12/2021 | 04/01/2022 | 0 | TK_Complete | 1653707999 | 38 | 1653707999_38
A203680 | TT_Task | M1-A : T1C5 Roof Trim | 05/01/2022 | 07/01/2022 | 10/01/2022 | nan | 0 | TK_Active | 1653707999 | 39 | 1653707999_39
A203690 | TT_Task | M1-A : T1C5 Erection - 1 | 01/02/2022 | 04/02/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 71 | 1653707999_71
A203700 | TT_Task | M1-A : T1C5 Erection - 2 | 05/02/2022 | 08/02/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 71 | 1653707999_71
A203710 | TT_Task | M1-A : T1C5 Side wall preloading - LH | 05/01/2022 | 05/01/2022 | 06/01/2022 | nan | 0 | TK_Active | 1653707999 | 70 | 1653707999_70
A203720 | TT_Task | M1-A : T1C5 Side wall final (B;B) - LH | 31/01/2022 | 31/01/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 36 | 1653707999_36
A203730 | TT_Task | M1-A : T1C5 Side wall Anti collision + spot - RH | 28/12/2021 | 28/12/2021 | 28/12/2021 | 06/01/2022 | 0 | TK_Complete | 1653707999 | 72 | 1653707999_72
A203740 | TT_Task | M1-A : T1C5 Side wall Anti collision + spot - LH | 31/01/2022 | 31/01/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 72 | 1653707999_72
A203750 | TT_Task | T-1.2 :T1C6 Underframe Structure | 27/12/2021 | 30/12/2021 | 25/12/2021 | 11/01/2022 | 0 | TK_Complete | 1653707999 | 73 | 1653707999_73
A203760 | TT_Task | T-1.2 :T1C6 Underframe Bars ; Bracket | 11/01/2022 | 17/01/2022 | 11/01/2022 | nan | 0 | TK_Active | 1653707999 | 74 | 1653707999_74
A203770 | TT_Task | T-1.2 :T1C6 Underframe Trim | 31/01/2022 | 01/02/2022 | nan | nan | 16 | TK_NotStart | 1653707999 | 75 | 1653707999_75
A203780 | TT_Task | T-1.2 :T1C6 Side wall preloading - RH | 31/01/2022 | 31/01/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 76 | 1653707999_76
A203790 | TT_Task | T-1.2 :T1C6 Side wall final (B;B) - RH | 02/02/2022 | 02/02/2022 | nan | nan | 16 | TK_NotStart | 1653707999 | 77 | 1653707999_77
A203800 | TT_Task | T-1.2 :T1C6 Roof Preloading + Spot | 21/12/2021 | 24/12/2021 | 21/12/2021 | 04/01/2022 | 0 | TK_Complete | 1653707999 | 78 | 1653707999_78
A203810 | TT_Task | T-1.2 :T1C6 Roof Bars ; brackets | 05/01/2022 | 08/01/2022 | 08/01/2022 | nan | 0 | TK_Active | 1653707999 | 51 | 1653707999_51
A203820 | TT_Task | T-1.2 :T1C6 Roof Trim | 31/01/2022 | 02/02/2022 | nan | nan | 8 | TK_NotStart | 1653707999 | 79 | 1653707999_79
A203830 | TT_Task | T-1.2 :T1C6 Erection - 1 | 05/02/2022 | 09/02/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 80 | 1653707999_80
A203840 | TT_Task | T-1.2 :T1C6 Erection - 2 | 10/02/2022 | 12/02/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 80 | 1653707999_80
A203850 | TT_Task | T-1.2 :T1C6 Side wall preloading - LH | 02/02/2022 | 02/02/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 76 | 1653707999_76
A203860 | TT_Task | T-1.2 :T1C6 Side wall final (B;B) - LH | 04/02/2022 | 04/02/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 77 | 1653707999_77
A203870 | TT_Task | T-1.2 :T1C6 Side wall Anti collision + spot - RH | 01/02/2022 | 01/02/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 81 | 1653707999_81
A203880 | TT_Task | T-1.2 :T1C6 Side wall Anti collision + spot - LH | 03/02/2022 | 03/02/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 81 | 1653707999_81
A203470 | TT_Task | DMB : T1C4 Underframe Structure | 10/01/2022 | 13/01/2022 | 10/01/2022 | nan | 0 | TK_Active | 1653707999 | 82 | 1653707999_82
A203480 | TT_Task | DMB : T1C4 Underframe Bars ; Bracket | 31/01/2022 | 03/02/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 83 | 1653707999_83
A203490 | TT_Task | DMB : T1C4 Underframe Trim | 04/02/2022 | 05/02/2022 | nan | nan | 24 | TK_NotStart | 1653707999 | 84 | 1653707999_84
A203500 | TT_Task | DMB : T1C4 Side wall preloading - RH | 04/02/2022 | 04/02/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 85 | 1653707999_85
A203510 | TT_Task | DMB : T1C4 Side wall final (B;B) - RH | 05/02/2022 | 07/02/2022 | nan | nan | 20 | TK_NotStart | 1653707999 | 86 | 1653707999_86
A203520 | TT_Task | DMB : T1C4 Roof Preloading + Spot | 04/01/2022 | 07/01/2022 | 12/01/2022 | nan | 0 | TK_Active | 1653707999 | 87 | 1653707999_87
A203530 | TT_Task | DMB : T1C4 Roof Bars ; brackets | 31/01/2022 | 03/02/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 88 | 1653707999_88
A203540 | TT_Task | DMB : T1C4 Roof Trim | 04/02/2022 | 07/02/2022 | nan | nan | 16 | TK_NotStart | 1653707999 | 89 | 1653707999_89
A203550 | TT_Task | DMB : T1C4 Erection - 1 | 10/02/2022 | 14/02/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 90 | 1653707999_90
A203560 | TT_Task | DMB : T1C4 Erection - 2 | 15/02/2022 | 17/02/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 90 | 1653707999_90
A203570 | TT_Task | DMB : T1C4 Side wall preloading - LH | 05/02/2022 | 05/02/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 85 | 1653707999_85
A203580 | TT_Task | DMB : T1C4 Side wall final (B;B) - LH | 08/02/2022 | 08/02/2022 | nan | nan | 8 | TK_NotStart | 1653707999 | 86 | 1653707999_86
A203590 | TT_Task | DMB : T1C4 Side wall Anti collision + spot - RH | 04/02/2022 | 05/02/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 91 | 1653707999_91
A203600 | TT_Task | DMB : T1C4 Side wall Anti collision + spot - LH | 07/02/2022 | 07/02/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 91 | 1653707999_91
A204570 | TT_Task | M1B : Indus Input to MSSL / Savli (Rework Inst) | 31/01/2022 | 03/02/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 92 | 1653707999_92
A204580 | TT_Task | M1B : Material Lead time from MSSL to Savli | 04/02/2022 | 17/02/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 93 | 1653707999_93
A204600 | TT_Task | DME : Indus Input to MSSL / Savli (Rework Inst) | 31/01/2022 | 07/02/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 94 | 1653707999_94
A204610 | TT_Task | DME : Material Lead time from MSSL to Savli | 08/02/2022 | 15/02/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 95 | 1653707999_95
A204630 | TT_Task | T1B : Indus Input to MSSL / Savli (Rework Inst) | 31/01/2022 | 04/02/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 96 | 1653707999_96
A204640 | TT_Task | T1B : Material Lead time from MSSL to Savli | 05/02/2022 | 18/02/2022 | nan | nan | 16 | TK_NotStart | 1653707999 | 97 | 1653707999_97
A204660 | TT_Task | M1A : Indus Input to MSSL / Savli (Rework Inst) | 31/01/2022 | 04/02/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 92 | 1653707999_92
A204670 | TT_Task | M1A : Material Lead time from MSSL to Savli | 05/02/2022 | 12/02/2022 | nan | nan | 40 | TK_NotStart | 1653707999 | 93 | 1653707999_93
A204690 | TT_Task | T1A : Indus Input to MSSL / Savli (Rework Inst) | 04/02/2022 | 09/02/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 96 | 1653707999_96
A204700 | TT_Task | T1A : Material Lead time from MSSL to Savli | 10/02/2022 | 17/02/2022 | nan | nan | 40 | TK_NotStart | 1653707999 | 97 | 1653707999_97
A204720 | TT_Task | DMB : Indus Input to MSSL / Savli (Rework Inst) | 04/02/2022 | 09/02/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 94 | 1653707999_94
A204730 | TT_Task | DMB : Material Lead time from MSSL to Savli | 10/02/2022 | 17/02/2022 | nan | nan | 72 | TK_NotStart | 1653707999 | 95 | 1653707999_95
A203050 | TT_Task | M1-B :T1C1 Window ; Floor Trim | 22/12/2021 | 24/12/2021 | 22/12/2021 | nan | 0 | TK_Active | 1653707999 | 98 | 1653707999_98
A203060 | TT_Task | M1-B :T1C1 Doors installation(only Leaf need to install in next Station) | 31/01/2022 | 02/02/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 168 | 1653707999_168
A204440 | TT_Task | M1-B : Quality Clearance ; completion of Pending CWS work | 06/12/2021 | 16/12/2021 | 06/12/2021 | 22/12/2021 | 0 | TK_Complete | 1653707999 | 100 | 1653707999_100
A204550 | TT_Task | Delay event : Door Header Installation solution + Installation | 01/11/2021 | 12/11/2021 | 06/12/2021 | 07/01/2022 | 0 | TK_Complete | 1653707999 | 101 | 1653707999_101
A202930 | TT_Task | T-1.1 :T1C3 Window ; Floor Trim | 03/02/2022 | 05/02/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 102 | 1653707999_102
A202940 | TT_Task | T-1.1 :T1C3 Doors installation(only Leaf need to install in next Station) | 07/02/2022 | 09/02/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 168 | 1653707999_168
A202910 | TT_Task | DME : T1C2 Window ; Floor Trim | 18/01/2022 | 20/01/2022 | 18/01/2022 | nan | 0 | TK_Active | 1653707999 | 104 | 1653707999_104
A202920 | TT_Task | DME : T1C2 Doors installation ; Cab pre-assembly(only Leaf need to install in next Station) | 03/02/2022 | 05/02/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 105 | 1653707999_105
A203890 | TT_Task | M1-A : T1C5 Window ; Floor Trim | 09/02/2022 | 11/02/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 98 | 1653707999_98
A203900 | TT_Task | M1-A : T1C5 Doors installation(only Leaf need to install in next Station) | 12/02/2022 | 15/02/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 168 | 1653707999_168
A203910 | TT_Task | T-1.2 :T1C6 Window ; Floor Trim | 14/02/2022 | 16/02/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 102 | 1653707999_102
A203920 | TT_Task | T-1.2 :T1C6 Doors installation ; Cab pre-assembly | 17/02/2022 | 19/02/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 106 | 1653707999_106
A203070 | TT_Task | DMB : T1C4 Window ; Floor Trim | 18/02/2022 | 21/02/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 107 | 1653707999_107
A203080 | TT_Task | DMB : T1C4 Doors installation ; Cab pre-assembly | 22/02/2022 | 24/02/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 108 | 1653707999_108
A203090 | TT_Task | M1-B :T1C1 Roof Equip ; Interior | 25/02/2022 | 28/02/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 109 | 1653707999_109
A203100 | TT_Task | M1-B :T1C1 U/F Equip ; Cab | 22/02/2022 | 24/02/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 110 | 1653707999_110
A203110 | TT_Task | M1-B :T1C1 Exterior ; Interior1 | 03/02/2022 | 05/02/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 111 | 1653707999_111
A203120 | TT_Task | M1-B :T1C1 Exterior ; Interior2 | 07/02/2022 | 09/02/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 111 | 1653707999_111
A203130 | TT_Task | M1-B :T1C1 Exterior ; Interior3 | 01/03/2022 | 03/03/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 111 | 1653707999_111
A203140 | TT_Task | M1-B :T1C1 Bogie Installation | 14/03/2022 | 16/03/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 112 | 1653707999_112
A203930 | TT_Task | M1-B :T1C1 Underframe Cable Duct ; Piping-01 | 18/02/2022 | 21/02/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 113 | 1653707999_113
A204450 | TT_Task | M1B : Retrofit (Before Testing) - Parking Station | 07/03/2022 | 12/03/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 114 | 1653707999_114
A204460 | TT_Task | M1B : Retrofit (After Single Car Testing) - AK line need to use | 06/04/2022 | 08/04/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 115 | 1653707999_115
A204490 | TT_Task | M1-B :T1C1 Static Test | 04/03/2022 | 05/03/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 116 | 1653707999_116
A203940 | TT_Task | T-1.1 :T1C3 Roof Equip ; Interior | 04/03/2022 | 07/03/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 117 | 1653707999_117
A203950 | TT_Task | T-1.1 :T1C3 U/F Equip ; Cab | 01/03/2022 | 03/03/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 118 | 1653707999_118
A203960 | TT_Task | T-1.1 :T1C3 Exterior ; Interior1 | 10/02/2022 | 12/02/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 119 | 1653707999_119
A203970 | TT_Task | T-1.1 :T1C3 Exterior ; Interior2 | 14/02/2022 | 16/02/2022 | nan | nan | 16 | TK_NotStart | 1653707999 | 119 | 1653707999_119
A203980 | TT_Task | T-1.1 :T1C3 Exterior ; Interior3 | 08/03/2022 | 10/03/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 119 | 1653707999_119
A203990 | TT_Task | T-1.1 :T1C3 Bogie Installation | 22/03/2022 | 24/03/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 169 | 1653707999_169
A204000 | TT_Task | T-1.1 :T1C3 Underframe Cable Duct ; Piping-01 | 22/02/2022 | 24/02/2022 | nan | nan | 24 | TK_NotStart | 1653707999 | 121 | 1653707999_121
A204510 | TT_Task | T1-B :T1C1 Static Test | 11/03/2022 | 12/03/2022 | nan | nan | 48 | TK_NotStart | 1653707999 | 122 | 1653707999_122
A204010 | TT_Task | DME : T1C2 Roof Equip ; Interior | 01/03/2022 | 03/03/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 123 | 1653707999_123
A204020 | TT_Task | DME : T1C2 U/F Equip ; Cab | 25/02/2022 | 28/02/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 124 | 1653707999_124
A204030 | TT_Task | DME : T1C2 Exterior ; Interior1 | 07/02/2022 | 09/02/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 125 | 1653707999_125
A204040 | TT_Task | DME : T1C2 Exterior ; Interior2 | 10/02/2022 | 12/02/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 125 | 1653707999_125
A204050 | TT_Task | DME : T1C2 Exterior ; Interior3 | 04/03/2022 | 07/03/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 125 | 1653707999_125
A204060 | TT_Task | DME : T1C2 Bogie Installation | 17/03/2022 | 21/03/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 126 | 1653707999_126
A204070 | TT_Task | DME : T1C2 Underframe Cable Duct ; Piping-01 | 16/02/2022 | 18/02/2022 | nan | nan | 40 | TK_NotStart | 1653707999 | 127 | 1653707999_127
A204470 | TT_Task | DME : Retrofit (Before Testing) - Parking Station | 10/03/2022 | 16/03/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 114 | 1653707999_114
A204480 | TT_Task | DME : Retrofit (After Single Car Testing) - AK line need to use | 08/04/2022 | 08/04/2022 | nan | nan | 8 | TK_NotStart | 1653707999 | 115 | 1653707999_115
A204500 | TT_Task | DME :T1C1 Static Test | 08/03/2022 | 09/03/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 128 | 1653707999_128
A204150 | TT_Task | M1-A : T1C5 Roof Equip ; Interior | 08/03/2022 | 10/03/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 109 | 1653707999_109
A204160 | TT_Task | M1-A : T1C5 U/F Equip ; Cab | 04/03/2022 | 07/03/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 110 | 1653707999_110
A204170 | TT_Task | M1-A : T1C5 Exterior ; Interior1 | 16/02/2022 | 18/02/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 129 | 1653707999_129
A204180 | TT_Task | M1-A : T1C5 Exterior ; Interior2 | 19/02/2022 | 22/02/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 129 | 1653707999_129
A204190 | TT_Task | M1-A : T1C5 Exterior ; Interior3 | 11/03/2022 | 14/03/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 129 | 1653707999_129
A204200 | TT_Task | M1-A : T1C5 Bogie Installation | 25/03/2022 | 28/03/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 112 | 1653707999_112
A204210 | TT_Task | M1-A : T1C5 Underframe Cable Duct ; Piping-01 | 19/02/2022 | 22/02/2022 | nan | nan | 64 | TK_NotStart | 1653707999 | 113 | 1653707999_113
A204520 | TT_Task | M1-A :T1C1 Static Test | 15/03/2022 | 16/03/2022 | nan | nan | 48 | TK_NotStart | 1653707999 | 116 | 1653707999_116
A204220 | TT_Task | T-1.2 :T1C6 Roof Equip ; Interior | 11/03/2022 | 14/03/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 117 | 1653707999_117
A204230 | TT_Task | T-1.2 :T1C6 U/F Equip ; Cab | 08/03/2022 | 10/03/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 130 | 1653707999_130
A204240 | TT_Task | T-1.2 :T1C6 Exterior ; Interior1 | 21/02/2022 | 23/02/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 131 | 1653707999_131
A204250 | TT_Task | T-1.2 :T1C6 Exterior ; Interior2 | 24/02/2022 | 26/02/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 131 | 1653707999_131
A204260 | TT_Task | T-1.2 :T1C6 Exterior ; Interior3 | 15/03/2022 | 17/03/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 131 | 1653707999_131
A204270 | TT_Task | T-1.2 :T1C6 Bogie Installation | 29/03/2022 | 31/03/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 169 | 1653707999_169
A204280 | TT_Task | T-1.2 :T1C6 Underframe Cable Duct ; Piping-01 | 24/02/2022 | 26/02/2022 | nan | nan | 56 | TK_NotStart | 1653707999 | 121 | 1653707999_121
A204530 | TT_Task | T-1.2 :T1C1 Static Test | 19/03/2022 | 21/03/2022 | nan | nan | 48 | TK_NotStart | 1653707999 | 122 | 1653707999_122
A204080 | TT_Task | DMB : T1C4 Roof Equip ; Interior | 15/03/2022 | 17/03/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 132 | 1653707999_132
A204090 | TT_Task | DMB : T1C4 U/F Equip ; Cab | 11/03/2022 | 14/03/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 133 | 1653707999_133
A204100 | TT_Task | DMB : T1C4 Exterior ; Interior1 | 25/02/2022 | 28/02/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 134 | 1653707999_134
A204110 | TT_Task | DMB : T1C4 Exterior ; Interior2 | 01/03/2022 | 03/03/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 134 | 1653707999_134
A204120 | TT_Task | DMB : T1C4 Exterior ; Interior3 | 19/03/2022 | 22/03/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 134 | 1653707999_134
A204130 | TT_Task | DMB : T1C4 Bogie Installation | 01/04/2022 | 04/04/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 170 | 1653707999_170
A204140 | TT_Task | DMB : T1C4 Underframe Cable Duct ; Piping-01 | 01/03/2022 | 03/03/2022 | nan | nan | 48 | TK_NotStart | 1653707999 | 136 | 1653707999_136
A204540 | TT_Task | DMB :T1C1 Static Test | 23/03/2022 | 24/03/2022 | nan | nan | 48 | TK_NotStart | 1653707999 | 128 | 1653707999_128
A204290 | TT_Task | M1-B :single car | 17/03/2022 | 05/04/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 171 | 1653707999_171
A204300 | TT_Task | T-1.1 :single car | 25/03/2022 | 08/04/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 172 | 1653707999_172
A204310 | TT_Task | DME : single car | 22/03/2022 | 07/04/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 173 | 1653707999_173
A204330 | TT_Task | M1-A : single car | 29/03/2022 | 01/04/2022 | nan | nan | 48 | TK_NotStart | 1653707999 | 171 | 1653707999_171
A204340 | TT_Task | T-1.2 :single car | 01/04/2022 | 05/04/2022 | nan | nan | 24 | TK_NotStart | 1653707999 | 172 | 1653707999_172
A204320 | TT_Task | DMB : single car | 05/04/2022 | 08/04/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 174 | 1653707999_174
A204350 | TT_Task | 3 Car Testing | 09/04/2022 | 16/04/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 175 | 1653707999_175
A204360 | TT_Task | 3 Car Testing | 09/04/2022 | 16/04/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 175 | 1653707999_175
A204370 | TT_Task | 6 Car Testing + Interior Finalization (7D) | 18/04/2022 | 03/05/2022 | nan | nan | 11743 | TK_NotStart | 1653707999 | 176 | 1653707999_176
A199510 | TT_Task | M1-B : T1C1 Underframe Structure | 27/09/2021 | 04/10/2021 | 27/09/2021 | 17/10/2021 | 0 | TK_Complete | 1653707999 | 32 | 1653707999_32
A199520 | TT_Task | M1-B :T1C1 Underframe Bars ; Bracket | 20/10/2021 | 22/10/2021 | 18/10/2021 | 27/10/2021 | 0 | TK_Complete | 1653707999 | 33 | 1653707999_33
A199530 | TT_Task | M1-B :T1C1 Underframe Trim | 27/10/2021 | 27/10/2021 | 27/10/2021 | 27/10/2021 | 0 | TK_Complete | 1653707999 | 34 | 1653707999_34
A199540 | TT_Task | M1-B :T1C1 Side wall preloading - RH | 14/09/2021 | 18/09/2021 | 03/09/2021 | 20/09/2021 | 0 | TK_Complete | 1653707999 | 35 | 1653707999_35
A199550 | TT_Task | M1-B :T1C1 Side wall final (B;B) - RH | 07/10/2021 | 07/10/2021 | 11/10/2021 | 23/10/2021 | 0 | TK_Complete | 1653707999 | 36 | 1653707999_36
A199560 | TT_Task | M1-B :T1C1 Roof Preloading + Spot | 06/09/2021 | 01/10/2021 | 16/07/2021 | 13/09/2021 | 0 | TK_Complete | 1653707999 | 37 | 1653707999_37
A199570 | TT_Task | M1-B :T1C1 Roof Bars ; brackets | 09/09/2021 | 16/09/2021 | 14/09/2021 | 28/09/2021 | 0 | TK_Complete | 1653707999 | 38 | 1653707999_38
A199580 | TT_Task | M1-B :T1C1 Roof Trim | 30/09/2021 | 05/10/2021 | 01/10/2021 | 08/10/2021 | 0 | TK_Complete | 1653707999 | 39 | 1653707999_39
A199590 | TT_Task | M1-B :T1C1 Erection - 1 | 27/10/2021 | 11/11/2021 | 28/10/2021 | nan | 0 | TK_Active | 1653707999 | 40 | 1653707999_40
A199600 | TT_Task | M1-B :T1C1 Erection - 2 | 31/01/2022 | 03/02/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 40 | 1653707999_40
A199710 | TT_Task | M1-B :T1C1 Side wall preloading - LH | 07/10/2021 | 08/10/2021 | 10/10/2021 | 14/10/2021 | 0 | TK_Complete | 1653707999 | 35 | 1653707999_35
A199720 | TT_Task | M1-B :T1C1 Side wall final (B;B) - LH | 22/10/2021 | 22/10/2021 | 22/10/2021 | 22/10/2021 | 0 | TK_Complete | 1653707999 | 36 | 1653707999_36
A199730 | TT_Task | M1-B :T1C1 Side wall Anti collision - RH | 21/09/2021 | 24/09/2021 | 21/09/2021 | 29/09/2021 | 0 | TK_Complete | 1653707999 | 41 | 1653707999_41
A199740 | TT_Task | M1-B :T1C1 Side wall Anti collision + spot - LH | 20/10/2021 | 21/10/2021 | 20/10/2021 | 22/10/2021 | 0 | TK_Complete | 1653707999 | 42 | 1653707999_42
A200960 | TT_Task | M1-B :T1C1 Side wall Re-Preloading - RH (Delay Event due to Part rejection) | 30/09/2021 | 01/10/2021 | 29/09/2021 | 04/10/2021 | 0 | TK_Complete | 1653707999 | 43 | 1653707999_43
A200970 | TT_Task | M1-B :T1C1 Side wall spot - RH | 01/10/2021 | 04/10/2021 | 05/10/2021 | 10/10/2021 | 0 | TK_Complete | 1653707999 | 44 | 1653707999_44
A199890 | TT_Task | T-1.1 :T1C3 Underframe Structure + Spot | 18/10/2021 | 27/10/2021 | 18/10/2021 | nan | 0 | TK_Active | 1653707999 | 45 | 1653707999_45
A199900 | TT_Task | T-1.1 :T1C3 Underframe Bars ; Bracket | 31/01/2022 | 03/02/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 74 | 1653707999_74
A199910 | TT_Task | T-1.1 :T1C3 Underframe Trim | 04/02/2022 | 04/02/2022 | nan | nan | 8 | TK_NotStart | 1653707999 | 75 | 1653707999_75
A199920 | TT_Task | T-1.1 :T1C3 Side wall preloading - RH | 31/01/2022 | 31/01/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 48 | 1653707999_48
A199930 | TT_Task | T-1.1 :T1C3 Side wall final (B;B) - RH | 01/02/2022 | 01/02/2022 | nan | nan | 26 | TK_NotStart | 1653707999 | 49 | 1653707999_49
A199940 | TT_Task | T-1.1 :T1C3 Roof Preloading + Spot (4 D waiting for IQC) | 17/09/2021 | 30/09/2021 | 17/09/2021 | 12/10/2021 | 0 | TK_Complete | 1653707999 | 50 | 1653707999_50
A199950 | TT_Task | T-1.1 :T1C3 Roof Bars ; brackets | 13/10/2021 | 20/10/2021 | 13/10/2021 | 27/10/2021 | 0 | TK_Complete | 1653707999 | 51 | 1653707999_51
A199960 | TT_Task | T-1.1 :T1C3 Roof Trim | 31/01/2022 | 04/02/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 79 | 1653707999_79
A199970 | TT_Task | T-1.1 :T1C3 Erection - 1 | 05/02/2022 | 10/02/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 80 | 1653707999_80
A199980 | TT_Task | T-1.1 :T1C3 Erection - 2 | 11/02/2022 | 16/02/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 80 | 1653707999_80
A199990 | TT_Task | T-1.1 :T1C3 Side wall preloading - LH | 01/02/2022 | 02/02/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 48 | 1653707999_48
A200000 | TT_Task | T-1.1 :T1C3 Side wall final (B;B) - LH | 03/02/2022 | 03/02/2022 | nan | nan | 8 | TK_NotStart | 1653707999 | 49 | 1653707999_49
A200010 | TT_Task | T-1.1 :T1C3 Side wall Anti collision + spot - RH | 31/01/2022 | 01/02/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 54 | 1653707999_54
A200020 | TT_Task | T-1.1 :T1C3 Side wall Anti collision + spot - LH | 02/02/2022 | 03/02/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 54 | 1653707999_54
A200950 | TT_Task | T-1.1 :T1C3 Roof Tooling Modification (Delay event) | 09/09/2021 | 15/09/2021 | 09/09/2021 | 16/09/2021 | 0 | TK_Complete | 1653707999 | 55 | 1653707999_55
A201030 | TT_Task | Delay event : Sidewall skin Waiting | 22/10/2021 | 06/11/2021 | 22/10/2021 | nan | 0 | TK_Active | 1653707999 | 56 | 1653707999_56
A199750 | TT_Task | DME : T1C2 Underframe Structure | 31/01/2022 | 04/02/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 58 | 1653707999_58
A199760 | TT_Task | DME : T1C2 Underframe Bars ; Bracket | 05/02/2022 | 09/02/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 59 | 1653707999_59
A199770 | TT_Task | DME : T1C2 Underframe Trim | 10/02/2022 | 10/02/2022 | nan | nan | 8 | TK_NotStart | 1653707999 | 60 | 1653707999_60
A199780 | TT_Task | DME : T1C2 Side wall preloading - RH | 03/02/2022 | 04/02/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 61 | 1653707999_61
A199790 | TT_Task | DME : T1C2 Side wall final (B;B) - RH | 07/02/2022 | 07/02/2022 | nan | nan | 29 | TK_NotStart | 1653707999 | 62 | 1653707999_62
A199800 | TT_Task | DME : T1C2 Roof Preloading + Spot | 10/11/2021 | 15/11/2021 | 24/10/2021 | nan | 0 | TK_Active | 1653707999 | 63 | 1653707999_63
A199810 | TT_Task | DME : T1C2 Roof Bars ; brackets | 31/01/2022 | 04/02/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 64 | 1653707999_64
A199820 | TT_Task | DME : T1C2 Roof Trim | 05/02/2022 | 08/02/2022 | nan | nan | 8 | TK_NotStart | 1653707999 | 65 | 1653707999_65
A199830 | TT_Task | DME : T1C2 Erection - 1 | 11/02/2022 | 15/02/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 66 | 1653707999_66
A199840 | TT_Task | DME : T1C2 Erection - 2 | 17/02/2022 | 21/02/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 66 | 1653707999_66
A199850 | TT_Task | DME : T1C2 Side wall preloading - LH | 07/02/2022 | 07/02/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 61 | 1653707999_61
A199860 | TT_Task | DME : T1C2 Side wall final (B;B) - LH | 09/02/2022 | 09/02/2022 | nan | nan | 11 | TK_NotStart | 1653707999 | 62 | 1653707999_62
A199870 | TT_Task | DME : T1C2 Side wall Anti collision + spot - RH | 04/02/2022 | 07/02/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 67 | 1653707999_67
A199880 | TT_Task | DME : T1C2 Side wall Anti collision + spot - LH | 07/02/2022 | 09/02/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 67 | 1653707999_67
A200450 | TT_Task | DME : Compression Test | 22/02/2022 | 22/02/2022 | nan | nan | 12223 | TK_NotStart | 1653707999 | 177 | 1653707999_177
A201040 | TT_Task | DME : Delay event - Carline delivery due to Eng Change ; development activity. | 01/11/2021 | 09/11/2021 | 12/10/2021 | 23/10/2021 | 0 | TK_Complete | 1653707999 | 68 | 1653707999_68
A200170 | TT_Task | M1-A : T1C5 Underframe Structure | 05/02/2022 | 08/02/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 32 | 1653707999_32
A200180 | TT_Task | M1-A : T1C5 Underframe Bars ; Bracket | 10/02/2022 | 12/02/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 33 | 1653707999_33
A200190 | TT_Task | M1-A : T1C5 Underframe Trim | 14/02/2022 | 15/02/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 34 | 1653707999_34
A200200 | TT_Task | M1-A : T1C5 Side wall preloading - RH | 09/02/2022 | 10/02/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 70 | 1653707999_70
A200210 | TT_Task | M1-A : T1C5 Side wall final (B;B) - RH | 11/02/2022 | 11/02/2022 | nan | nan | 24 | TK_NotStart | 1653707999 | 36 | 1653707999_36
A200220 | TT_Task | M1-A : T1C5 Roof Preloading + Spot | 31/01/2022 | 03/02/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 37 | 1653707999_37
A200230 | TT_Task | M1-A : T1C5 Roof Bars ; brackets | 05/02/2022 | 09/02/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 38 | 1653707999_38
A200240 | TT_Task | M1-A : T1C5 Roof Trim | 10/02/2022 | 12/02/2022 | nan | nan | 8 | TK_NotStart | 1653707999 | 39 | 1653707999_39
A200250 | TT_Task | M1-A : T1C5 Erection - 1 | 16/02/2022 | 21/02/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 71 | 1653707999_71
A200260 | TT_Task | M1-A : T1C5 Erection - 2 | 22/02/2022 | 26/02/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 71 | 1653707999_71
A200270 | TT_Task | M1-A : T1C5 Side wall preloading - LH | 11/02/2022 | 12/02/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 70 | 1653707999_70
A200280 | TT_Task | M1-A : T1C5 Side wall final (B;B) - LH | 15/02/2022 | 15/02/2022 | nan | nan | 5 | TK_NotStart | 1653707999 | 36 | 1653707999_36
A200290 | TT_Task | M1-A : T1C5 Side wall Anti collision + spot - RH | 10/02/2022 | 11/02/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 72 | 1653707999_72
A200300 | TT_Task | M1-A : T1C5 Side wall Anti collision + spot - LH | 12/02/2022 | 15/02/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 72 | 1653707999_72
A200310 | TT_Task | T-1.2 :T1C6 Underframe Structure | 09/02/2022 | 12/02/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 73 | 1653707999_73
A200320 | TT_Task | T-1.2 :T1C6 Underframe Bars ; Bracket | 14/02/2022 | 16/02/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 74 | 1653707999_74
A200330 | TT_Task | T-1.2 :T1C6 Underframe Trim | 17/02/2022 | 18/02/2022 | nan | nan | 16 | TK_NotStart | 1653707999 | 75 | 1653707999_75
A200340 | TT_Task | T-1.2 :T1C6 Side wall preloading - RH | 15/02/2022 | 15/02/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 76 | 1653707999_76
A200350 | TT_Task | T-1.2 :T1C6 Side wall final (B;B) - RH | 17/02/2022 | 17/02/2022 | nan | nan | 27 | TK_NotStart | 1653707999 | 77 | 1653707999_77
A200360 | TT_Task | T-1.2 :T1C6 Roof Preloading + Spot | 04/02/2022 | 08/02/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 78 | 1653707999_78
A200370 | TT_Task | T-1.2 :T1C6 Roof Bars ; brackets | 10/02/2022 | 14/02/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 51 | 1653707999_51
A200380 | TT_Task | T-1.2 :T1C6 Roof Trim | 15/02/2022 | 17/02/2022 | nan | nan | 8 | TK_NotStart | 1653707999 | 79 | 1653707999_79
A200390 | TT_Task | T-1.2 :T1C6 Erection - 1 | 22/02/2022 | 25/02/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 80 | 1653707999_80
A200400 | TT_Task | T-1.2 :T1C6 Erection - 2 | 28/02/2022 | 03/03/2022 | nan | nan | 24 | TK_NotStart | 1653707999 | 80 | 1653707999_80
A200410 | TT_Task | T-1.2 :T1C6 Side wall preloading - LH | 17/02/2022 | 18/02/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 76 | 1653707999_76
A200420 | TT_Task | T-1.2 :T1C6 Side wall final (B;B) - LH | 19/02/2022 | 19/02/2022 | nan | nan | 8 | TK_NotStart | 1653707999 | 77 | 1653707999_77
A200430 | TT_Task | T-1.2 :T1C6 Side wall Anti collision + spot - RH | 15/02/2022 | 17/02/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 81 | 1653707999_81
A200440 | TT_Task | T-1.2 :T1C6 Side wall Anti collision + spot - LH | 18/02/2022 | 19/02/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 81 | 1653707999_81
A200030 | TT_Task | DMB : T1C4 Underframe Structure | 14/02/2022 | 17/02/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 82 | 1653707999_82
A200040 | TT_Task | DMB : T1C4 Underframe Bars ; Bracket | 18/02/2022 | 22/02/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 83 | 1653707999_83
A200050 | TT_Task | DMB : T1C4 Underframe Trim | 23/02/2022 | 24/02/2022 | nan | nan | 8 | TK_NotStart | 1653707999 | 84 | 1653707999_84
A200060 | TT_Task | DMB : T1C4 Side wall preloading - RH | 19/02/2022 | 21/02/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 85 | 1653707999_85
A200070 | TT_Task | DMB : T1C4 Side wall final (B;B) - RH | 23/02/2022 | 23/02/2022 | nan | nan | 22 | TK_NotStart | 1653707999 | 86 | 1653707999_86
A200080 | TT_Task | DMB : T1C4 Roof Preloading + Spot | 09/02/2022 | 12/02/2022 | nan | nan | 8 | TK_NotStart | 1653707999 | 87 | 1653707999_87
A200090 | TT_Task | DMB : T1C4 Roof Bars ; brackets | 15/02/2022 | 18/02/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 88 | 1653707999_88
A200100 | TT_Task | DMB : T1C4 Roof Trim | 19/02/2022 | 22/02/2022 | nan | nan | 24 | TK_NotStart | 1653707999 | 89 | 1653707999_89
A200110 | TT_Task | DMB : T1C4 Erection - 1 | 26/02/2022 | 07/03/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 90 | 1653707999_90
A200120 | TT_Task | DMB : T1C4 Erection - 2 | 08/03/2022 | 11/03/2022 | nan | nan | 8 | TK_NotStart | 1653707999 | 90 | 1653707999_90
A200130 | TT_Task | DMB : T1C4 Side wall preloading - LH | 23/02/2022 | 23/02/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 85 | 1653707999_85
A200140 | TT_Task | DMB : T1C4 Side wall final (B;B) - LH | 25/02/2022 | 25/02/2022 | nan | nan | 3 | TK_NotStart | 1653707999 | 86 | 1653707999_86
A200150 | TT_Task | DMB : T1C4 Side wall Anti collision + spot - RH | 21/02/2022 | 23/02/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 91 | 1653707999_91
A200160 | TT_Task | DMB : T1C4 Side wall Anti collision + spot - LH | 23/02/2022 | 25/02/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 91 | 1653707999_91
A199610 | TT_Task | M1-B :T1C1 Window ; Floor Trim | 04/02/2022 | 11/02/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 98 | 1653707999_98
A199620 | TT_Task | M1-B :T1C1 Doors installation | 12/02/2022 | 19/02/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 99 | 1653707999_99
A199490 | TT_Task | T-1.1 :T1C3 Window ; Floor Trim | 17/02/2022 | 23/02/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 102 | 1653707999_102
A199500 | TT_Task | T-1.1 :T1C3 Doors installation | 24/02/2022 | 02/03/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 103 | 1653707999_103
A200460 | TT_Task | M1-A : T1C5 Window ; Floor Trim | 01/03/2022 | 07/03/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 98 | 1653707999_98
A200470 | TT_Task | M1-A : T1C5 Doors installation | 08/03/2022 | 14/03/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 99 | 1653707999_99
A200480 | TT_Task | T-1.2 :T1C6 Window ; Floor Trim | 08/03/2022 | 12/03/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 102 | 1653707999_102
A200490 | TT_Task | T-1.2 :T1C6 Doors installation ; Cab pre-assembly | 15/03/2022 | 21/03/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 106 | 1653707999_106
A199630 | TT_Task | DMB : T1C4 Window ; Floor Trim | 14/03/2022 | 19/03/2022 | nan | nan | 8 | TK_NotStart | 1653707999 | 107 | 1653707999_107
A199640 | TT_Task | DMB : T1C4 Doors installation ; Cab pre-assembly | 22/03/2022 | 26/03/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 108 | 1653707999_108
A199470 | TT_Task | DME : T1C2 Window ; Floor Trim | 24/02/2022 | 28/02/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 104 | 1653707999_104
A199480 | TT_Task | DME : T1C2 Doors installation ; Cab pre-assembly | 03/03/2022 | 07/03/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 105 | 1653707999_105
A199650 | TT_Task | M1-B :T1C1 U/F Equip ; Cab | 16/03/2022 | 22/03/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 110 | 1653707999_110
A199660 | TT_Task | M1-B :T1C1 Roof Equip ; Interior | 09/03/2022 | 15/03/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 109 | 1653707999_109
A199670 | TT_Task | M1-B :T1C1 Exterior ; Interior1 | 21/02/2022 | 01/03/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 111 | 1653707999_111
A199680 | TT_Task | M1-B :T1C1 Exterior ; Interior2 | 02/03/2022 | 08/03/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 111 | 1653707999_111
A199690 | TT_Task | M1-B :T1C1 Exterior ; Interior3 | 23/03/2022 | 28/03/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 111 | 1653707999_111
A199700 | TT_Task | M1-B :T1C1 Bogie Installation | 29/03/2022 | 02/04/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 112 | 1653707999_112
A200500 | TT_Task | M1-B :T1C1 Underframe Cable Duct ; Piping-01 | 09/03/2022 | 22/03/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 113 | 1653707999_113
A200510 | TT_Task | T-1.1 :T1C3 U/F Equip ; Cab | 23/03/2022 | 26/03/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 118 | 1653707999_118
A200520 | TT_Task | T-1.1 :T1C3 Roof Equip ; Interior | 16/03/2022 | 21/03/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 117 | 1653707999_117
A200530 | TT_Task | T-1.1 :T1C3 Exterior ; Interior1 | 03/03/2022 | 07/03/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 119 | 1653707999_119
A200540 | TT_Task | T-1.1 :T1C3 Exterior ; Interior2 | 09/03/2022 | 12/03/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 119 | 1653707999_119
A200550 | TT_Task | T-1.1 :T1C3 Exterior ; Interior3 | 29/03/2022 | 01/04/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 119 | 1653707999_119
A200560 | TT_Task | T-1.1 :T1C3 Bogie Installation | 04/04/2022 | 07/04/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 169 | 1653707999_169
A200570 | TT_Task | T-1.1 :T1C3 Underframe Cable Duct ; Piping-01 | 14/03/2022 | 26/03/2022 | nan | nan | 8 | TK_NotStart | 1653707999 | 121 | 1653707999_121
A200720 | TT_Task | M1-A : T1C5 U/F Equip ; Cab | 31/03/2022 | 04/04/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 110 | 1653707999_110
A200730 | TT_Task | M1-A : T1C5 Roof Equip ; Interior | 25/03/2022 | 29/03/2022 | nan | nan | 8 | TK_NotStart | 1653707999 | 109 | 1653707999_109
A200740 | TT_Task | M1-A : T1C5 Exterior ; Interior1 | 15/03/2022 | 19/03/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 129 | 1653707999_129
A200750 | TT_Task | M1-A : T1C5 Exterior ; Interior2 | 21/03/2022 | 24/03/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 129 | 1653707999_129
A200760 | TT_Task | M1-A : T1C5 Exterior ; Interior3 | 06/04/2022 | 09/04/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 129 | 1653707999_129
A200770 | TT_Task | M1-A : T1C5 Bogie Installation | 11/04/2022 | 14/04/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 112 | 1653707999_112
A200780 | TT_Task | M1-A : T1C5 Underframe Cable Duct ; Piping-01 | 26/03/2022 | 04/04/2022 | nan | nan | 8 | TK_NotStart | 1653707999 | 113 | 1653707999_113
A200790 | TT_Task | T-1.2 :T1C6 U/F Equip ; Cab | 05/04/2022 | 08/04/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 130 | 1653707999_130
A200800 | TT_Task | T-1.2 :T1C6 Roof Equip ; Interior | 31/03/2022 | 04/04/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 117 | 1653707999_117
A200810 | TT_Task | T-1.2 :T1C6 Exterior ; Interior1 | 22/03/2022 | 25/03/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 131 | 1653707999_131
A200820 | TT_Task | T-1.2 :T1C6 Exterior ; Interior2 | 26/03/2022 | 30/03/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 131 | 1653707999_131
A200830 | TT_Task | T-1.2 :T1C6 Exterior ; Interior3 | 11/04/2022 | 14/04/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 131 | 1653707999_131
A200840 | TT_Task | T-1.2 :T1C6 Bogie Installation | 15/04/2022 | 16/04/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 169 | 1653707999_169
A200850 | TT_Task | T-1.2 :T1C6 Underframe Cable Duct ; Piping-01 | 01/04/2022 | 08/04/2022 | nan | nan | 8 | TK_NotStart | 1653707999 | 121 | 1653707999_121
A200650 | TT_Task | DMB : T1C4 U/F Equip ; Cab | 11/04/2022 | 14/04/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 133 | 1653707999_133
A200660 | TT_Task | DMB : T1C4 Roof Equip ; Interior | 06/04/2022 | 09/04/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 132 | 1653707999_132
A200670 | TT_Task | DMB : T1C4 Exterior ; Interior1 | 28/03/2022 | 31/03/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 134 | 1653707999_134
A200680 | TT_Task | DMB : T1C4 Exterior ; Interior2 | 01/04/2022 | 05/04/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 134 | 1653707999_134
A200690 | TT_Task | DMB : T1C4 Exterior ; Interior3 | 15/04/2022 | 19/04/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 134 | 1653707999_134
A200700 | TT_Task | DMB : T1C4 Bogie Installation | 20/04/2022 | 21/04/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 170 | 1653707999_170
A200710 | TT_Task | DMB : T1C4 Underframe Cable Duct ; Piping-01 | 05/04/2022 | 14/04/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 136 | 1653707999_136
A200580 | TT_Task | DME : T1C2 U/F Equip ; Cab | 28/03/2022 | 30/03/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 124 | 1653707999_124
A200590 | TT_Task | DME : T1C2 Roof Equip ; Interior | 22/03/2022 | 24/03/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 123 | 1653707999_123
A200600 | TT_Task | DME : T1C2 Exterior ; Interior1 | 08/03/2022 | 10/03/2022 | nan | nan | 16 | TK_NotStart | 1653707999 | 125 | 1653707999_125
A200610 | TT_Task | DME : T1C2 Exterior ; Interior2 | 14/03/2022 | 16/03/2022 | nan | nan | 16 | TK_NotStart | 1653707999 | 125 | 1653707999_125
A200620 | TT_Task | DME : T1C2 Exterior ; Interior3 | 02/04/2022 | 05/04/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 125 | 1653707999_125
A200630 | TT_Task | DME : T1C2 Bogie Installation | 08/04/2022 | 09/04/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 126 | 1653707999_126
A200640 | TT_Task | DME : T1C2 Underframe Cable Duct ; Piping-01 | 19/03/2022 | 30/03/2022 | nan | nan | 16 | TK_NotStart | 1653707999 | 127 | 1653707999_127
A200860 | TT_Task | M1-B :single car | 04/04/2022 | 02/05/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 171 | 1653707999_171
A200980 | TT_Task | Continuity test | 31/01/2022 | 31/01/2022 | nan | nan | 10551 | TK_NotStart | 1653707999 | 178 | 1653707999_178
A200990 | TT_Task | Insulation impedance test and Hipot test | 31/01/2022 | 31/01/2022 | nan | nan | 10551 | TK_NotStart | 1653707999 | 179 | 1653707999_179
A201000 | TT_Task | Data links tests. MVB, Cat 5. | 31/01/2022 | 31/01/2022 | nan | nan | 10551 | TK_NotStart | 1653707999 | 180 | 1653707999_180
A201010 | TT_Task | Water Test (Sealing Test) (Type + Routine) | 31/01/2022 | 31/01/2022 | nan | nan | 10551 | TK_NotStart | 1653707999 | 181 | 1653707999_181
A201020 | TT_Task | Dimesional + Static gauge test (Type + Routine) | 31/01/2022 | 31/01/2022 | nan | nan | 10551 | TK_NotStart | 1653707999 | 182 | 1653707999_182
A200870 | TT_Task | T-1.1 :single car | 08/04/2022 | 30/04/2022 | nan | nan | 8 | TK_NotStart | 1653707999 | 172 | 1653707999_172
A200880 | TT_Task | DME : single car | 11/04/2022 | 20/04/2022 | nan | nan | 80 | TK_NotStart | 1653707999 | 173 | 1653707999_173
A200900 | TT_Task | M1-A : single car | 15/04/2022 | 29/04/2022 | nan | nan | 40 | TK_NotStart | 1653707999 | 171 | 1653707999_171
A200910 | TT_Task | T-1.2 :single car | 18/04/2022 | 02/05/2022 | nan | nan | 24 | TK_NotStart | 1653707999 | 172 | 1653707999_172
A200890 | TT_Task | DMB : single car | 22/04/2022 | 05/05/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 174 | 1653707999_174
A200920 | TT_Task | 3 Car Testing | 03/05/2022 | 07/05/2022 | nan | nan | 24 | TK_NotStart | 1653707999 | 175 | 1653707999_175
A200930 | TT_Task | 3 Car Testing | 06/05/2022 | 11/05/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 175 | 1653707999_175
A200940 | TT_Task | 6 Car Testing | 12/05/2022 | 03/06/2022 | nan | nan | 11527 | TK_NotStart | 1653707999 | 175 | 1653707999_175
A175680 | TT_Task | M1-B : T1C1 Underframe Structure | 27/09/2021 | 04/10/2021 | 27/09/2021 | 17/10/2021 | 0 | TK_Complete | 1653707999 | 32 | 1653707999_32
A175700 | TT_Task | M1-B :T1C1 Underframe Bars ; Bracket | 20/10/2021 | 22/10/2021 | 18/10/2021 | 27/10/2021 | 0 | TK_Complete | 1653707999 | 33 | 1653707999_33
A175710 | TT_Task | M1-B :T1C1 Underframe Trim | 27/10/2021 | 27/10/2021 | 27/10/2021 | 27/10/2021 | 0 | TK_Complete | 1653707999 | 34 | 1653707999_34
A175720 | TT_Task | M1-B :T1C1 Side wall preloading - RH | 14/09/2021 | 18/09/2021 | 03/09/2021 | 20/09/2021 | 0 | TK_Complete | 1653707999 | 35 | 1653707999_35
A175721 | TT_Task | M1-B :T1C1 Side wall preloading - LH | 07/10/2021 | 08/10/2021 | 10/10/2021 | 14/10/2021 | 0 | TK_Complete | 1653707999 | 35 | 1653707999_35
A175730 | TT_Task | M1-B :T1C1 Side wall final (B;B) - RH | 07/10/2021 | 07/10/2021 | 11/10/2021 | 23/10/2021 | 0 | TK_Complete | 1653707999 | 36 | 1653707999_36
A175731 | TT_Task | M1-B :T1C1 Side wall final (B;B) - LH | 22/10/2021 | 22/10/2021 | 22/10/2021 | 22/10/2021 | 0 | TK_Complete | 1653707999 | 36 | 1653707999_36
A175740 | TT_Task | M1-B :T1C1 Roof Preloading + Spot | 06/09/2021 | 01/10/2021 | 16/07/2021 | 13/09/2021 | 0 | TK_Complete | 1653707999 | 37 | 1653707999_37
A175750 | TT_Task | M1-B :T1C1 Roof Bars ; brackets | 09/09/2021 | 16/09/2021 | 14/09/2021 | 28/09/2021 | 0 | TK_Complete | 1653707999 | 38 | 1653707999_38
A175760 | TT_Task | M1-B :T1C1 Roof Trim | 30/09/2021 | 05/10/2021 | 01/10/2021 | 08/10/2021 | 0 | TK_Complete | 1653707999 | 39 | 1653707999_39
A175770 | TT_Task | M1-B :T1C1 Erection - 1 | 27/10/2021 | 08/11/2021 | 28/10/2021 | 03/12/2021 | 0 | TK_Complete | 1653707999 | 40 | 1653707999_40
A175780 | TT_Task | M1-B :T1C1 Erection - 2 | 04/12/2021 | 04/12/2021 | 04/12/2021 | 06/12/2021 | 0 | TK_Complete | 1653707999 | 40 | 1653707999_40
A177980 | TT_Task | M1-B :T1C1 Side wall Anti collision - RH | 21/09/2021 | 24/09/2021 | 21/09/2021 | 29/09/2021 | 0 | TK_Complete | 1653707999 | 41 | 1653707999_41
A177981 | TT_Task | M1-B :T1C1 Side wall Re-Preloading - RH (Delay Event due to Part rejection) | 30/09/2021 | 01/10/2021 | 29/09/2021 | 04/10/2021 | 0 | TK_Complete | 1653707999 | 43 | 1653707999_43
A177982 | TT_Task | M1-B :T1C1 Side wall spot - RH | 01/10/2021 | 02/10/2021 | 05/10/2021 | 10/10/2021 | 0 | TK_Complete | 1653707999 | 44 | 1653707999_44
A177990 | TT_Task | M1-B :T1C1 Side wall Anti collision + spot - LH | 20/10/2021 | 21/10/2021 | 20/10/2021 | 22/10/2021 | 0 | TK_Complete | 1653707999 | 42 | 1653707999_42
A189780 | TT_Task | T1-B :T1C3 Side wall preloading - RH | 13/11/2021 | 13/11/2021 | 10/11/2021 | 21/12/2021 | 0 | TK_Complete | 1653707999 | 48 | 1653707999_48
A189790 | TT_Task | T1-B :T1C3 Side wall preloading - LH | 23/11/2021 | 23/11/2021 | 23/11/2021 | 23/12/2021 | 0 | TK_Complete | 1653707999 | 48 | 1653707999_48
A189800 | TT_Task | T1-B :T1C3 Roof Preloading + Spot (4 D waiting for IQC) | 17/09/2021 | 30/09/2021 | 17/09/2021 | 12/10/2021 | 0 | TK_Complete | 1653707999 | 50 | 1653707999_50
A189810 | TT_Task | T1-B :T1C3 Side wall Anti collision + spot - RH | 18/11/2021 | 19/11/2021 | 17/11/2021 | 24/12/2021 | 0 | TK_Complete | 1653707999 | 54 | 1653707999_54
A189820 | TT_Task | T1-B :T1C3 Side wall Anti collision + spot - LH | 01/12/2021 | 02/12/2021 | 01/12/2021 | 25/12/2021 | 0 | TK_Complete | 1653707999 | 54 | 1653707999_54
A189830 | TT_Task | T1-B :T1C3 Underframe Structure + Spot | 18/10/2021 | 27/10/2021 | 18/10/2021 | 23/11/2021 | 0 | TK_Complete | 1653707999 | 45 | 1653707999_45
A189840 | TT_Task | T1-B :T1C3 Side wall final (B;B) - RH | 27/11/2021 | 27/11/2021 | 27/11/2021 | 24/12/2021 | 0 | TK_Complete | 1653707999 | 49 | 1653707999_49
A189850 | TT_Task | T1-B :T1C3 Roof Bars ; brackets | 13/10/2021 | 20/10/2021 | 13/10/2021 | 27/10/2021 | 0 | TK_Complete | 1653707999 | 51 | 1653707999_51
A189860 | TT_Task | T1-B :T1C3 Side wall final (B;B) - LH | 06/12/2021 | 06/12/2021 | 06/12/2021 | 28/12/2021 | 0 | TK_Complete | 1653707999 | 49 | 1653707999_49
A189870 | TT_Task | T1-B :T1C3 Underframe Bars ; Bracket | 23/11/2021 | 25/11/2021 | 23/11/2021 | 30/11/2021 | 0 | TK_Complete | 1653707999 | 46 | 1653707999_46
A189880 | TT_Task | T1-B :T1C3 Roof Trim | 01/11/2021 | 08/11/2021 | 10/11/2021 | 28/12/2021 | 0 | TK_Complete | 1653707999 | 52 | 1653707999_52
A189890 | TT_Task | T1-B :T1C3 Underframe Trim | 30/11/2021 | 02/12/2021 | 01/12/2021 | 04/12/2021 | 0 | TK_Complete | 1653707999 | 47 | 1653707999_47
A189891 | TT_Task | T1-B :T1C UF Rejected, New UF to be produce | 06/12/2021 | 15/12/2021 | 06/12/2021 | 06/01/2022 | 0 | TK_Complete | 1653707999 | 57 | 1653707999_57
A189900 | TT_Task | T1-B :T1C3 Erection - 1 | 06/01/2022 | 10/01/2022 | 07/01/2022 | 18/01/2022 | 0 | TK_Complete | 1653707999 | 53 | 1653707999_53
A189910 | TT_Task | T1-B :T1C3 Erection - 2 | 18/01/2022 | 20/01/2022 | 18/01/2022 | 20/01/2022 | 0 | TK_Complete | 1653707999 | 53 | 1653707999_53
A190740 | TT_Task | T1-B :T1C3 Roof Tooling Modification (Delay event) | 09/09/2021 | 15/09/2021 | 09/09/2021 | 16/09/2021 | 0 | TK_Complete | 1653707999 | 55 | 1653707999_55
A190840 | TT_Task | T1-B : Delay event : Sidewall skin Waiting | 22/10/2021 | 06/11/2021 | 22/10/2021 | 12/11/2021 | 0 | TK_Complete | 1653707999 | 56 | 1653707999_56
A189640 | TT_Task | DME : T1C2 Side wall preloading - RH | 06/12/2021 | 09/12/2021 | 06/12/2021 | 09/12/2021 | 0 | TK_Complete | 1653707999 | 61 | 1653707999_61
A189650 | TT_Task | DME : T1C2 Side wall preloading - LH | 14/12/2021 | 15/12/2021 | 14/12/2021 | 15/12/2021 | 0 | TK_Complete | 1653707999 | 61 | 1653707999_61
A189659 | TT_Task | DME : Delay event - Carline delivery due to Eng Change ; development activity. | 01/11/2021 | 09/11/2021 | 01/11/2021 | 06/11/2021 | 0 | TK_Complete | 1653707999 | 68 | 1653707999_68
A189660 | TT_Task | DME : T1C2 Roof Preloading + Spot | 10/11/2021 | 17/11/2021 | 08/11/2021 | 15/11/2021 | 0 | TK_Complete | 1653707999 | 63 | 1653707999_63
A189670 | TT_Task | DME : T1C2 Side wall Anti collision + spot - RH | 13/12/2021 | 14/12/2021 | 13/12/2021 | 14/12/2021 | 0 | TK_Complete | 1653707999 | 67 | 1653707999_67
A189680 | TT_Task | DME : T1C2 Side wall Anti collision + spot - LH | 15/12/2021 | 16/12/2021 | 15/12/2021 | 16/12/2021 | 0 | TK_Complete | 1653707999 | 67 | 1653707999_67
A189690 | TT_Task | DME : T1C2 Underframe Structure | 18/11/2021 | 24/11/2021 | 17/11/2021 | 15/12/2021 | 0 | TK_Complete | 1653707999 | 58 | 1653707999_58
A189700 | TT_Task | DME : T1C2 Side wall final (B;B) - RH | 14/12/2021 | 14/12/2021 | 14/12/2021 | 14/12/2021 | 0 | TK_Complete | 1653707999 | 62 | 1653707999_62
A189710 | TT_Task | DME : T1C2 Roof Bars ; brackets | 13/11/2021 | 19/11/2021 | 15/11/2021 | 11/12/2021 | 0 | TK_Complete | 1653707999 | 64 | 1653707999_64
A189720 | TT_Task | DME : T1C2 Side wall final (B;B) - LH | 16/12/2021 | 16/12/2021 | 16/12/2021 | 16/12/2021 | 0 | TK_Complete | 1653707999 | 62 | 1653707999_62
A189730 | TT_Task | DME : T1C2 Underframe Bars ; Bracket | 10/12/2021 | 14/12/2021 | 10/12/2021 | 16/12/2021 | 0 | TK_Complete | 1653707999 | 59 | 1653707999_59
A189740 | TT_Task | DME : T1C2 Roof Trim | 14/12/2021 | 15/12/2021 | 15/12/2021 | 23/12/2021 | 0 | TK_Complete | 1653707999 | 65 | 1653707999_65
A189750 | TT_Task | DME : T1C2 Underframe Trim | 15/12/2021 | 15/12/2021 | 15/12/2021 | 15/12/2021 | 0 | TK_Complete | 1653707999 | 60 | 1653707999_60
A189760 | TT_Task | DME : T1C2 Erection - 1 | 16/12/2021 | 21/12/2021 | 16/12/2021 | 31/12/2021 | 0 | TK_Complete | 1653707999 | 66 | 1653707999_66
A189770 | TT_Task | DME : T1C2 Erection - 2 | 29/12/2021 | 31/12/2021 | 01/01/2022 | 06/01/2022 | 0 | TK_Complete | 1653707999 | 66 | 1653707999_66
A190060 | TT_Task | M1-A : T1C5 Side wall preloading - RH | 23/12/2021 | 23/12/2021 | 27/12/2021 | 01/01/2022 | 0 | TK_Complete | 1653707999 | 70 | 1653707999_70
A190070 | TT_Task | M1-A : T1C5 Side wall preloading - LH | 05/01/2022 | 05/01/2022 | 06/01/2022 | 22/01/2022 | 0 | TK_Complete | 1653707999 | 70 | 1653707999_70
A190080 | TT_Task | M1-A : T1C5 Roof Preloading + Spot | 15/11/2021 | 19/11/2021 | 16/11/2021 | 30/11/2021 | 0 | TK_Complete | 1653707999 | 37 | 1653707999_37
A190090 | TT_Task | M1-A : T1C5 Side wall Anti collision + spot - RH | 28/12/2021 | 28/12/2021 | 28/12/2021 | 06/01/2022 | 0 | TK_Complete | 1653707999 | 72 | 1653707999_72
A190100 | TT_Task | M1-A : T1C5 Side wall Anti collision + spot - LH | 25/01/2022 | 25/01/2022 | 23/01/2022 | 23/01/2022 | 0 | TK_Complete | 1653707999 | 72 | 1653707999_72
A190110 | TT_Task | M1-A : T1C5 Underframe Structure (Convert T1B to M1A) | 13/12/2021 | 17/12/2021 | 20/12/2021 | 11/01/2022 | 0 | TK_Complete | 1653707999 | 69 | 1653707999_69
A190120 | TT_Task | M1-A : T1C5 Side wall final (B;B) - RH | 06/01/2022 | 06/01/2022 | 07/01/2022 | 07/01/2022 | 0 | TK_Complete | 1653707999 | 36 | 1653707999_36
A190130 | TT_Task | M1-A : T1C5 Roof Bars ; brackets | 24/12/2021 | 28/12/2021 | 14/12/2021 | 04/01/2022 | 0 | TK_Complete | 1653707999 | 38 | 1653707999_38
A190140 | TT_Task | M1-A : T1C5 Side wall final (B;B) - LH | 25/01/2022 | 25/01/2022 | 24/01/2022 | 24/01/2022 | 0 | TK_Complete | 1653707999 | 36 | 1653707999_36
A190150 | TT_Task | M1-A : T1C5 Underframe Bars ; Bracket | 24/12/2021 | 24/12/2021 | 24/12/2021 | 24/12/2021 | 0 | TK_Complete | 1653707999 | 33 | 1653707999_33
A190160 | TT_Task | M1-A : T1C5 Roof Trim | 05/01/2022 | 07/01/2022 | 10/01/2022 | 21/01/2022 | 0 | TK_Complete | 1653707999 | 39 | 1653707999_39
A190170 | TT_Task | M1-A : T1C5 Underframe Trim | 12/01/2022 | 13/01/2022 | 11/01/2022 | 19/01/2022 | 0 | TK_Complete | 1653707999 | 34 | 1653707999_34
A190180 | TT_Task | M1-A : T1C5 Erection - 1 | 27/01/2022 | 31/01/2022 | 25/01/2022 | 01/02/2022 | 0 | TK_Complete | 1653707999 | 71 | 1653707999_71
A190190 | TT_Task | M1-A : T1C5 Erection - 2 | 02/02/2022 | 03/02/2022 | 01/02/2022 | 02/02/2022 | 0 | TK_Complete | 1653707999 | 71 | 1653707999_71
A190200 | TT_Task | T-1.2 :T1C6 Side wall preloading - RH | 24/01/2022 | 24/01/2022 | 25/01/2022 | 29/01/2022 | 0 | TK_Complete | 1653707999 | 76 | 1653707999_76
A190210 | TT_Task | T-1.2 :T1C6 Side wall preloading - LH | 01/02/2022 | 01/02/2022 | 01/02/2022 | 04/02/2022 | 0 | TK_Complete | 1653707999 | 76 | 1653707999_76
A190220 | TT_Task | T-1.2 :T1C6 Roof Preloading + Spot | 21/12/2021 | 24/12/2021 | 21/12/2021 | 04/01/2022 | 0 | TK_Complete | 1653707999 | 78 | 1653707999_78
A190230 | TT_Task | T-1.2 :T1C6 Side wall Anti collision + spot - RH | 28/01/2022 | 28/01/2022 | 28/01/2022 | 31/01/2022 | 0 | TK_Complete | 1653707999 | 81 | 1653707999_81
A190240 | TT_Task | T-1.2 :T1C6 Side wall Anti collision + spot - LH | 02/02/2022 | 02/02/2022 | 04/02/2022 | 05/02/2022 | 0 | TK_Complete | 1653707999 | 81 | 1653707999_81
A190250 | TT_Task | T-1.2 :T1C6 Underframe Structure | 27/12/2021 | 30/12/2021 | 25/12/2021 | 11/01/2022 | 0 | TK_Complete | 1653707999 | 73 | 1653707999_73
A190260 | TT_Task | T-1.2 :T1C6 Side wall final (B;B) - RH | 01/02/2022 | 01/02/2022 | 01/02/2022 | 01/02/2022 | 0 | TK_Complete | 1653707999 | 77 | 1653707999_77
A190270 | TT_Task | T-1.2 :T1C6 Roof Bars ; brackets | 05/01/2022 | 08/01/2022 | 08/01/2022 | 22/01/2022 | 0 | TK_Complete | 1653707999 | 51 | 1653707999_51
A190280 | TT_Task | T-1.2 :T1C6 Side wall final (B;B) - LH | 03/02/2022 | 03/02/2022 | 06/02/2022 | 07/02/2022 | 0 | TK_Complete | 1653707999 | 77 | 1653707999_77
A190290 | TT_Task | T-1.2 :T1C6 Underframe Bars ; Bracket | 11/01/2022 | 17/01/2022 | 11/01/2022 | 25/01/2022 | 0 | TK_Complete | 1653707999 | 74 | 1653707999_74
A190300 | TT_Task | T-1.2 :T1C6 Roof Trim | 21/01/2022 | 24/01/2022 | 27/01/2022 | 31/01/2022 | 0 | TK_Complete | 1653707999 | 79 | 1653707999_79
A190310 | TT_Task | T-1.2 :T1C6 Underframe Trim | 25/01/2022 | 27/01/2022 | 27/01/2022 | 29/01/2022 | 0 | TK_Complete | 1653707999 | 75 | 1653707999_75
A190320 | TT_Task | T-1.2 :T1C6 Erection - 1 | 04/02/2022 | 07/02/2022 | 07/02/2022 | 09/02/2022 | 0 | TK_Complete | 1653707999 | 80 | 1653707999_80
A190330 | TT_Task | T-1.2 :T1C6 Erection - 2 | 10/02/2022 | 11/02/2022 | 10/02/2022 | 11/02/2022 | 0 | TK_Complete | 1653707999 | 80 | 1653707999_80
A189920 | TT_Task | DMB : T1C4 Side wall preloading - RH | 05/02/2022 | 05/02/2022 | 05/02/2022 | 17/02/2022 | 0 | TK_Complete | 1653707999 | 85 | 1653707999_85
A189930 | TT_Task | DMB : T1C4 Side wall preloading - LH | 07/02/2022 | 07/02/2022 | 16/02/2022 | 21/02/2022 | 0 | TK_Complete | 1653707999 | 85 | 1653707999_85
A189940 | TT_Task | DMB : T1C4 Roof Preloading + Spot | 04/01/2022 | 07/01/2022 | 12/01/2022 | 25/01/2022 | 0 | TK_Complete | 1653707999 | 87 | 1653707999_87
A189950 | TT_Task | DMB : T1C4 Side wall Anti collision + spot - RH | 05/02/2022 | 07/02/2022 | 05/02/2022 | 18/02/2022 | 0 | TK_Complete | 1653707999 | 91 | 1653707999_91
A189960 | TT_Task | DMB : T1C4 Side wall Anti collision + spot - LH | 22/02/2022 | 23/02/2022 | 22/02/2022 | 23/02/2022 | 0 | TK_Complete | 1653707999 | 91 | 1653707999_91
A189970 | TT_Task | DMB : T1C4 Underframe Structure | 10/01/2022 | 13/01/2022 | 10/01/2022 | 28/01/2022 | 0 | TK_Complete | 1653707999 | 82 | 1653707999_82
A189980 | TT_Task | DMB : T1C4 Side wall final (B;B) - RH | 07/02/2022 | 08/02/2022 | 07/02/2022 | 19/02/2022 | 0 | TK_Complete | 1653707999 | 86 | 1653707999_86
A189990 | TT_Task | DMB : T1C4 Roof Bars ; brackets | 25/01/2022 | 29/01/2022 | 25/01/2022 | 01/02/2022 | 0 | TK_Complete | 1653707999 | 88 | 1653707999_88
A190000 | TT_Task | DMB : T1C4 Side wall final (B;B) - LH | 24/02/2022 | 24/02/2022 | 24/02/2022 | 24/02/2022 | 0 | TK_Complete | 1653707999 | 86 | 1653707999_86
A190010 | TT_Task | DMB : T1C4 Underframe Bars ; Bracket | 28/01/2022 | 01/02/2022 | 28/01/2022 | 11/02/2022 | 0 | TK_Complete | 1653707999 | 83 | 1653707999_83
A190020 | TT_Task | DMB : T1C4 Roof Trim | 07/02/2022 | 09/02/2022 | 14/02/2022 | 22/02/2022 | 0 | TK_Complete | 1653707999 | 89 | 1653707999_89
A190030 | TT_Task | DMB : T1C4 Underframe Trim | 10/02/2022 | 11/02/2022 | 12/02/2022 | 16/02/2022 | 0 | TK_Complete | 1653707999 | 84 | 1653707999_84
A190040 | TT_Task | DMB : T1C4 Erection - 1 | 24/02/2022 | 25/02/2022 | 24/02/2022 | 03/03/2022 | 0 | TK_Complete | 1653707999 | 90 | 1653707999_90
A190050 | TT_Task | DMB : T1C4 Erection - 2 | 26/02/2022 | 28/02/2022 | 03/03/2022 | 04/03/2022 | 0 | TK_Complete | 1653707999 | 90 | 1653707999_90
A175790 | TT_Task | M1-B :T1C1 Window ; Floor Trim | 22/12/2021 | 24/12/2021 | 22/12/2021 | 17/01/2022 | 0 | TK_Complete | 1653707999 | 98 | 1653707999_98
A175800 | TT_Task | M1-B :T1C1 Doors installation | 18/01/2022 | 20/01/2022 | 18/01/2022 | 08/02/2022 | 0 | TK_Complete | 1653707999 | 99 | 1653707999_99
A175810 | TT_Task | M1-B : Quality Clearance ; completion of Pending CWS work | 06/12/2021 | 16/12/2021 | 06/12/2021 | 22/12/2021 | 0 | TK_Complete | 1653707999 | 100 | 1653707999_100
A175820 | TT_Task | Delay event : Door Header Installation solution + Installation | 01/11/2021 | 12/11/2021 | 06/12/2021 | 07/01/2022 | 0 | TK_Complete | 1653707999 | 101 | 1653707999_101
A175600 | TT_Task | T-1.1 :T1C3 Window ; Floor Trim | 31/01/2022 | 02/02/2022 | 25/01/2022 | 02/02/2022 | 0 | TK_Complete | 1653707999 | 102 | 1653707999_102
A175610 | TT_Task | T-1.1 :T1C3 Doors installation | 21/02/2022 | 23/02/2022 | 21/02/2022 | 25/02/2022 | 0 | TK_Complete | 1653707999 | 103 | 1653707999_103
A175400 | TT_Task | DME : T1C2 Window ; Floor Trim | 18/01/2022 | 20/01/2022 | 18/01/2022 | 29/01/2022 | 0 | TK_Complete | 1653707999 | 104 | 1653707999_104
A175410 | TT_Task | DME : T1C2 Doors installation ; Cab pre-assembly | 10/02/2022 | 12/02/2022 | 10/02/2022 | 15/02/2022 | 0 | TK_Complete | 1653707999 | 105 | 1653707999_105
A190350 | TT_Task | M1-A : T1C5 Window ; Floor Trim | 03/02/2022 | 05/02/2022 | 03/02/2022 | 09/02/2022 | 0 | TK_Complete | 1653707999 | 98 | 1653707999_98
A190360 | TT_Task | M1-A : T1C5 Doors installation | 18/02/2022 | 21/02/2022 | 18/02/2022 | 24/02/2022 | 0 | TK_Complete | 1653707999 | 99 | 1653707999_99
A190370 | TT_Task | T-1.2 :T1C6 Window ; Floor Trim | 12/02/2022 | 15/02/2022 | 12/02/2022 | 25/02/2022 | 0 | TK_Complete | 1653707999 | 102 | 1653707999_102
A190380 | TT_Task | T-1.2 :T1C6 Doors installation ; Cab pre-assembly | 25/02/2022 | 28/02/2022 | 25/02/2022 | 10/03/2022 | 0 | TK_Complete | 1653707999 | 106 | 1653707999_106
A175980 | TT_Task | DMB : T1C4 Window ; Floor Trim | 05/03/2022 | 08/03/2022 | 05/03/2022 | 10/03/2022 | 0 | TK_Complete | 1653707999 | 107 | 1653707999_107
A175990 | TT_Task | DMB : T1C4 Doors installation ; Cab pre-assembly | 09/03/2022 | 11/03/2022 | 14/03/2022 | nan | 128 | TK_Active | 1653707999 | 108 | 1653707999_108
A202740 | TT_Task | M1B : Indus Input to MSSL / Savli (Rework Inst) | 17/01/2022 | 20/01/2022 | 17/01/2022 | 24/01/2022 | 0 | TK_Complete | 1653707999 | 92 | 1653707999_92
A202750 | TT_Task | M1B : Material Lead time from MSSL to Savli | 21/01/2022 | 31/01/2022 | 21/01/2022 | 31/01/2022 | 0 | TK_Complete | 1653707999 | 93 | 1653707999_93
A202770 | TT_Task | DME : Indus Input to MSSL / Savli (Rework Inst) | 17/01/2022 | 24/01/2022 | 17/01/2022 | 24/01/2022 | 0 | TK_Complete | 1653707999 | 94 | 1653707999_94
A202780 | TT_Task | DME : Material Lead time from MSSL to Savli | 25/01/2022 | 08/02/2022 | 25/01/2022 | 14/02/2022 | 0 | TK_Complete | 1653707999 | 95 | 1653707999_95
A202800 | TT_Task | T1B : Indus Input to MSSL / Savli (Rework Inst) | 28/01/2022 | 02/02/2022 | 28/01/2022 | 07/02/2022 | 0 | TK_Complete | 1653707999 | 96 | 1653707999_96
A202810 | TT_Task | T1B : Material Lead time from MSSL to Savli | 08/02/2022 | 11/02/2022 | 08/02/2022 | 17/02/2022 | 0 | TK_Complete | 1653707999 | 97 | 1653707999_97
A202830 | TT_Task | M1A : Indus Input to MSSL / Savli (Rework Inst) | 24/01/2022 | 29/01/2022 | 24/01/2022 | 01/02/2022 | 0 | TK_Complete | 1653707999 | 92 | 1653707999_92
A202840 | TT_Task | M1A : Material Lead time from MSSL to Savli | 01/02/2022 | 14/02/2022 | 01/02/2022 | 21/02/2022 | 0 | TK_Complete | 1653707999 | 93 | 1653707999_93
A202860 | TT_Task | T1A : Indus Input to MSSL / Savli (Rework Inst) | 07/02/2022 | 10/02/2022 | 07/02/2022 | 11/02/2022 | 0 | TK_Complete | 1653707999 | 96 | 1653707999_96
A202870 | TT_Task | T1A : Material Lead time from MSSL to Savli | 11/02/2022 | 22/02/2022 | 11/02/2022 | 09/03/2022 | 0 | TK_Complete | 1653707999 | 97 | 1653707999_97
A202890 | TT_Task | DMB : Indus Input to MSSL / Savli (Rework Inst) | 07/02/2022 | 11/02/2022 | 07/02/2022 | 11/02/2022 | 0 | TK_Complete | 1653707999 | 94 | 1653707999_94
A202900 | TT_Task | DMB : Material Lead time from MSSL to Savli | 12/02/2022 | 26/02/2022 | 12/02/2022 | nan | 0 | TK_Active | 1653707999 | 95 | 1653707999_95
A176190 | TT_Task | M1-B :T1C1 Roof Equip ; Interior | 10/02/2022 | 10/02/2022 | 10/02/2022 | 10/02/2022 | 0 | TK_Complete | 1653707999 | 109 | 1653707999_109
A176200 | TT_Task | M1-B :T1C1 U/F Equip ; Cab | 14/02/2022 | 15/02/2022 | 28/01/2022 | 10/02/2022 | 0 | TK_Complete | 1653707999 | 110 | 1653707999_110
A176210 | TT_Task | M1-B :T1C1 Exterior ; Interior1 | 10/02/2022 | 12/02/2022 | 02/02/2022 | 10/02/2022 | 0 | TK_Complete | 1653707999 | 111 | 1653707999_111
A176220 | TT_Task | M1-B :T1C1 Exterior ; Interior2 | 10/02/2022 | 10/02/2022 | 10/02/2022 | 10/02/2022 | 0 | TK_Complete | 1653707999 | 111 | 1653707999_111
A176230 | TT_Task | M1-B :T1C1 Exterior ; Interior3 | 10/02/2022 | 12/02/2022 | 10/02/2022 | 15/02/2022 | 0 | TK_Complete | 1653707999 | 111 | 1653707999_111
A176240 | TT_Task | M1-B :T1C1 Bogie Installation | 12/02/2022 | 12/02/2022 | 15/02/2022 | 02/03/2022 | 0 | TK_Complete | 1653707999 | 112 | 1653707999_112
A176250 | TT_Task | M1-B :T1C1 Underframe Cable Duct ; Piping-01 | 04/02/2022 | 10/02/2022 | 25/01/2022 | 09/02/2022 | 0 | TK_Complete | 1653707999 | 113 | 1653707999_113
A208380 | TT_Task | M1B : Insulation impedance test and Hipot test | 26/02/2022 | 28/02/2022 | 26/02/2022 | 03/03/2022 | 0 | TK_Complete | 1653707999 | 179 | 1653707999_179
A190390 | TT_Task | T-1.1 :T1C3 Underframe Cable Duct ; Piping-01 | 19/02/2022 | 23/02/2022 | 19/02/2022 | 05/03/2022 | 0 | TK_Complete | 1653707999 | 121 | 1653707999_121
A190400 | TT_Task | T-1.1 :T1C3 Roof Equip ; Interior | 02/03/2022 | 02/03/2022 | 02/03/2022 | 13/03/2022 | 0 | TK_Complete | 1653707999 | 117 | 1653707999_117
A190410 | TT_Task | T-1.1 :T1C3 U/F Equip ; Cab | 01/03/2022 | 01/03/2022 | 01/03/2022 | 09/03/2022 | 0 | TK_Complete | 1653707999 | 118 | 1653707999_118
A190420 | TT_Task | T-1.1 :T1C3 Exterior ; Interior1 | 17/02/2022 | 17/02/2022 | 17/02/2022 | 17/02/2022 | 0 | TK_Complete | 1653707999 | 119 | 1653707999_119
A190430 | TT_Task | T-1.1 :T1C3 Exterior ; Interior2 | 17/02/2022 | 17/02/2022 | 17/02/2022 | 24/02/2022 | 0 | TK_Complete | 1653707999 | 119 | 1653707999_119
A190440 | TT_Task | T-1.1 :T1C3 Exterior ; Interior3 | 10/03/2022 | 10/03/2022 | 13/03/2022 | nan | 0 | TK_Active | 1653707999 | 119 | 1653707999_119
A190450 | TT_Task | T1-B :T1C3 Insulation impedance test and Hipot test | 19/03/2022 | 21/03/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 183 | 1653707999_183
A202690 | TT_Task | T1-B :T1C1 Bogie Installation | 16/03/2022 | 17/03/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 169 | 1653707999_169
A190460 | TT_Task | DME : T1C2 Underframe Cable Duct ; Piping-01 | 09/02/2022 | 11/02/2022 | 09/02/2022 | 19/02/2022 | 0 | TK_Complete | 1653707999 | 127 | 1653707999_127
A190470 | TT_Task | DME : T1C2 Roof Equip ; Interior | 01/03/2022 | 01/03/2022 | 01/03/2022 | 01/03/2022 | 0 | TK_Complete | 1653707999 | 123 | 1653707999_123
A190480 | TT_Task | DME : T1C2 U/F Equip ; Cab | 17/02/2022 | 19/02/2022 | 21/02/2022 | 28/02/2022 | 0 | TK_Complete | 1653707999 | 124 | 1653707999_124
A190490 | TT_Task | DME : T1C2 Exterior ; Interior1 | 14/02/2022 | 16/02/2022 | 28/01/2022 | 14/02/2022 | 0 | TK_Complete | 1653707999 | 125 | 1653707999_125
A190500 | TT_Task | DME : T1C2 Exterior ; Interior2 | 17/02/2022 | 19/02/2022 | 08/02/2022 | 14/02/2022 | 0 | TK_Complete | 1653707999 | 125 | 1653707999_125
A190510 | TT_Task | DME : T1C2 Exterior ; Interior3 | 01/03/2022 | 02/03/2022 | 01/03/2022 | 09/03/2022 | 0 | TK_Complete | 1653707999 | 125 | 1653707999_125
A190520 | TT_Task | DME : T1C2 Insulation impedance test and Hipot test | 19/03/2022 | 21/03/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 183 | 1653707999_183
A202680 | TT_Task | DME :T1C2 Bogie Installation | 09/03/2022 | 10/03/2022 | 09/03/2022 | 17/03/2022 | 0 | TK_Complete | 1653707999 | 126 | 1653707999_126
A190600 | TT_Task | M1-A : T1C5 Underframe Cable Duct ; Piping-01 | 05/03/2022 | 08/03/2022 | 05/03/2022 | 11/03/2022 | 0 | TK_Complete | 1653707999 | 113 | 1653707999_113
A190610 | TT_Task | M1-A : T1C5 Roof Equip ; Interior | 16/03/2022 | 16/03/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 109 | 1653707999_109
A190620 | TT_Task | M1-A : T1C5 U/F Equip ; Cab | 09/03/2022 | 09/03/2022 | 09/03/2022 | nan | 0 | TK_Active | 1653707999 | 110 | 1653707999_110
A190630 | TT_Task | M1-A : T1C5 Exterior ; Interior1 | 18/02/2022 | 21/02/2022 | 18/02/2022 | nan | 0 | TK_Active | 1653707999 | 129 | 1653707999_129
A190640 | TT_Task | M1-A : T1C5 Exterior ; Interior2 | 24/02/2022 | 26/02/2022 | 24/02/2022 | nan | 0 | TK_Active | 1653707999 | 129 | 1653707999_129
A190650 | TT_Task | M1-A : T1C5 Exterior ; Interior3 | 17/03/2022 | 17/03/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 129 | 1653707999_129
A190660 | TT_Task | M1-A : T1C5 Bogie Installation + HVAC Retrofit | 22/03/2022 | 23/03/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 120 | 1653707999_120
A202700 | TT_Task | M1-A :T1C1 Insulation impedance test and Hipot test | 19/03/2022 | 21/03/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 183 | 1653707999_183
A190670 | TT_Task | T-1.2 :T1C6 Underframe Cable Duct ; Piping-01 | 11/03/2022 | 14/03/2022 | 11/03/2022 | nan | 0 | TK_Active | 1653707999 | 121 | 1653707999_121
A190680 | TT_Task | T-1.2 :T1C6 Roof Equip ; Interior | 19/03/2022 | 21/03/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 117 | 1653707999_117
A190690 | TT_Task | T-1.2 :T1C6 U/F Equip ; Cab | 17/03/2022 | 17/03/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 130 | 1653707999_130
A190700 | TT_Task | T-1.2 :T1C6 Exterior ; Interior1 | 25/02/2022 | 28/02/2022 | 25/02/2022 | nan | 0 | TK_Active | 1653707999 | 131 | 1653707999_131
A190710 | TT_Task | T-1.2 :T1C6 Exterior ; Interior2 | 01/03/2022 | 03/03/2022 | 01/03/2022 | nan | 80 | TK_Active | 1653707999 | 131 | 1653707999_131
A190720 | TT_Task | T-1.2 :T1C6 Exterior ; Interior3 | 22/03/2022 | 23/03/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 131 | 1653707999_131
A190730 | TT_Task | T-1.2 :T1C6 Bogie Installation + HVAC Retrofit | 26/03/2022 | 28/03/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 120 | 1653707999_120
A202710 | TT_Task | T-1.2 :T1C1 Insulation impedance test and Hipot test | 24/03/2022 | 25/03/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 183 | 1653707999_183
A190530 | TT_Task | DMB : T1C4 Underframe Cable Duct ; Piping-01 | 19/03/2022 | 21/03/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 136 | 1653707999_136
A190540 | TT_Task | DMB : T1C4 Roof Equip ; Interior | 23/03/2022 | 24/03/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 132 | 1653707999_132
A190550 | TT_Task | DMB : T1C4 U/F Equip ; Cab | 22/03/2022 | 22/03/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 133 | 1653707999_133
A190560 | TT_Task | DMB : T1C4 Exterior ; Interior1 | 14/03/2022 | 15/03/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 134 | 1653707999_134
A190570 | TT_Task | DMB : T1C4 Exterior ; Interior2 | 16/03/2022 | 17/03/2022 | nan | nan | 16 | TK_NotStart | 1653707999 | 134 | 1653707999_134
A190580 | TT_Task | DMB : T1C4 Exterior ; Interior3 | 25/03/2022 | 26/03/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 134 | 1653707999_134
A190590 | TT_Task | DMB : T1C4 Bogie Installation + HVAC Retrofit | 30/03/2022 | 31/03/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 135 | 1653707999_135
A202720 | TT_Task | DMB :T1C1 Insulation impedance test and Hipot test | 28/03/2022 | 29/03/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 183 | 1653707999_183
A208340 | TT_Task | M1B : Retrofit | 14/04/2022 | 18/04/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 184 | 1653707999_184
A208350 | TT_Task | T1B : Retrofit | 14/04/2022 | 18/04/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 167 | 1653707999_167
A208360 | TT_Task | DME : Retrofit | 14/04/2022 | 19/04/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 185 | 1653707999_185
A204750 | TT_Task | Water Test | 18/04/2022 | 19/04/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 138 | 1653707999_138
A204760 | TT_Task | Protective bonding and return current test | 07/03/2022 | 07/03/2022 | nan | nan | 108 | TK_NotStart | 1653707999 | 139 | 1653707999_139
A204770 | TT_Task | Mechanical air tightness test | 05/03/2022 | 05/03/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 140 | 1653707999_140
A204780 | TT_Task | Static Gauge test | 20/04/2022 | 20/04/2022 | nan | nan | 48 | TK_NotStart | 1653707999 | 141 | 1653707999_141
A204790 | TT_Task | Weighing Test at AW0 | 19/04/2022 | 19/04/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 142 | 1653707999_142
A208420 | TT_Task | Data link ; MVB Test | 04/03/2022 | 04/03/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 186 | 1653707999_186
A204840 | TT_Task | Water Test | 18/04/2022 | 19/04/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 138 | 1653707999_138
A204850 | TT_Task | Protective bonding and return current test | 24/03/2022 | 24/03/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 139 | 1653707999_139
A204860 | TT_Task | Mechanical air tightness test | 23/03/2022 | 23/03/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 140 | 1653707999_140
A204870 | TT_Task | Static Gauge test | 20/04/2022 | 20/04/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 141 | 1653707999_141
A204880 | TT_Task | Weighing Test at AW0 | 19/04/2022 | 19/04/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 142 | 1653707999_142
A208430 | TT_Task | Data link ; MVB Test | 22/03/2022 | 22/03/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 186 | 1653707999_186
A208450 | TT_Task | Sway Test ; Wheel Unloading | 21/04/2022 | 26/04/2022 | nan | nan | 8 | TK_NotStart | 1653707999 | 146 | 1653707999_146
A204930 | TT_Task | Water Test | 19/04/2022 | 20/04/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 138 | 1653707999_138
A204940 | TT_Task | Protective bonding and return current test | 24/03/2022 | 24/03/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 139 | 1653707999_139
A204950 | TT_Task | Mechanical air tightness test | 23/03/2022 | 23/03/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 140 | 1653707999_140
A204960 | TT_Task | Static Gauge test | 21/04/2022 | 21/04/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 141 | 1653707999_141
A204970 | TT_Task | Weighing Test at AW0 | 20/04/2022 | 20/04/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 142 | 1653707999_142
A208440 | TT_Task | Data link ; MVB Test | 22/03/2022 | 22/03/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 186 | 1653707999_186
A205710 | TT_Task | Sway Test ; Wheel Unloading | 22/04/2022 | 27/04/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 146 | 1653707999_146
A205020 | TT_Task | Water Test | 24/03/2022 | 25/03/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 138 | 1653707999_138
A205030 | TT_Task | Protective bonding and return current test | 25/03/2022 | 26/03/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 139 | 1653707999_139
A205040 | TT_Task | Mechanical air tightness test | 26/03/2022 | 28/03/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 140 | 1653707999_140
A205050 | TT_Task | Static Gauge test | 28/03/2022 | 29/03/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 141 | 1653707999_141
A205060 | TT_Task | Weighing Test at AW0 | 24/03/2022 | 24/03/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 142 | 1653707999_142
A205690 | TT_Task | Sway Test ; Wheel Unloading | 29/03/2022 | 04/04/2022 | nan | nan | 12 | TK_NotStart | 1653707999 | 146 | 1653707999_146
A205110 | TT_Task | Water Test | 30/03/2022 | 30/03/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 138 | 1653707999_138
A205120 | TT_Task | Protective bonding and return current test | 29/03/2022 | 29/03/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 139 | 1653707999_139
A205130 | TT_Task | Mechanical air tightness test | 31/03/2022 | 31/03/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 140 | 1653707999_140
A205140 | TT_Task | Static Gauge test | 01/04/2022 | 01/04/2022 | nan | nan | 24 | TK_NotStart | 1653707999 | 141 | 1653707999_141
A205150 | TT_Task | Weighing Test at AW0 | 29/03/2022 | 29/03/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 142 | 1653707999_142
A205200 | TT_Task | Water Test | 02/04/2022 | 02/04/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 138 | 1653707999_138
A205210 | TT_Task | Protective bonding and return current test | 01/04/2022 | 01/04/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 139 | 1653707999_139
A205220 | TT_Task | Mechanical air tightness test | 04/04/2022 | 04/04/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 140 | 1653707999_140
A205230 | TT_Task | Static Gauge test | 05/04/2022 | 05/04/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 141 | 1653707999_141
A205240 | TT_Task | Weighing Test at AW0 | 01/04/2022 | 01/04/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 142 | 1653707999_142
A205290 | TT_Task | Inter car couple for 3 car formation | 24/03/2022 | 24/03/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 147 | 1653707999_147
A205300 | TT_Task | Train line Verification-Offline checking (Cab activation, EB loop, Traction safe loop, Door safe loop and Brake wiring) | 25/03/2022 | 30/03/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 187 | 1653707999_187
A205310 | TT_Task | Data Communication Test (MVB,IP etc..) | 25/03/2022 | 25/03/2022 | nan | nan | 32 | TK_NotStart | 1653707999 | 188 | 1653707999_188
A205320 | TT_Task | TCMS and other sub system software download (Doors,PA/PIS,CCTV,FSD,HVAC, BECU, EVR etc..) | 01/04/2022 | 06/04/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 189 | 1653707999_189
A205330 | TT_Task | TCMS I/O Test | 04/04/2022 | 12/04/2022 | nan | nan | 8 | TK_NotStart | 1653707999 | 190 | 1653707999_190
A205340 | TT_Task | Battery start up for 3 car, Normal bus 1;2 check and Battery contactor controls check. | 31/03/2022 | 01/04/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 191 | 1653707999_191
A205370 | TT_Task | Cab activation and Cab operating panel operation | 01/04/2022 | 02/04/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 192 | 1653707999_192
A205380 | TT_Task | Brake system static routine test | 08/04/2022 | 13/04/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 154 | 1653707999_154
A205390 | TT_Task | Coupler cover test | 08/04/2022 | 08/04/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 193 | 1653707999_193
A205410 | TT_Task | Light system routine test for Saloon,Cab,head,tail,marker,maintenance and emergency light | 09/04/2022 | 09/04/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 194 | 1653707999_194
A205420 | TT_Task | ACM Software download,Auxilary Power supply check, 3 phase CB check, Shore supply check, | 01/04/2022 | 04/04/2022 | nan | nan | 64 | TK_NotStart | 1653707999 | 195 | 1653707999_195
A205430 | TT_Task | Door Routine test for saloon, cab, partition,intermediate and emergency doors | 09/04/2022 | 11/04/2022 | nan | nan | 12 | TK_NotStart | 1653707999 | 155 | 1653707999_155
A205440 | TT_Task | Wind screen wiper and washer, Horn and windscreen demister routine test | 11/04/2022 | 11/04/2022 | nan | nan | 12 | TK_NotStart | 1653707999 | 156 | 1653707999_156
A205450 | TT_Task | FSD system routine testt | 09/04/2022 | 09/04/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 153 | 1653707999_153
A205460 | TT_Task | Traction Static test | 11/04/2022 | 12/04/2022 | nan | nan | 4 | TK_NotStart | 1653707999 | 157 | 1653707999_157
A208390 | TT_Task | Initial movement, speed pickups, propulsion test (low speed) | 11/04/2022 | 11/04/2022 | nan | nan | 12 | TK_NotStart | 1653707999 | 164 | 1653707999_164
A208400 | TT_Task | PC11+uncoupling | 13/04/2022 | 14/04/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 196 | 1653707999_196
A208410 | TT_Task | High voltage test, Pan up/down test, Primary voltage feedback test, | 06/04/2022 | 08/04/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 197 | 1653707999_197
A208460 | TT_Task | Inter car couple for 3 car formation | 06/04/2022 | 06/04/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 147 | 1653707999_147
A208470 | TT_Task | Train line Verification-Offline checking (Cab activation, EB loop, Traction safe loop, Door safe loop and Brake wiring) | 06/04/2022 | 12/04/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 187 | 1653707999_187
A208480 | TT_Task | Data Communication Test (MVB,IP etc..) | 06/04/2022 | 07/04/2022 | nan | nan | 32 | TK_NotStart | 1653707999 | 188 | 1653707999_188
A208490 | TT_Task | TCMS and other sub system software download (Doors,PA/PIS,CCTV,FSD,HVAC, BECU, EVR etc..) | 14/04/2022 | 18/04/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 189 | 1653707999_189
A208500 | TT_Task | TCMS I/O Test | 16/04/2022 | 23/04/2022 | nan | nan | 8 | TK_NotStart | 1653707999 | 190 | 1653707999_190
A208510 | TT_Task | Battery start up for 3 car, Normal bus 1;2 check and Battery contactor controls check. | 12/04/2022 | 13/04/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 191 | 1653707999_191
A208520 | TT_Task | Cab activation and Cab operating panel operation | 14/04/2022 | 15/04/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 192 | 1653707999_192
A208530 | TT_Task | Brake system static routine test | 21/04/2022 | 25/04/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 154 | 1653707999_154
A208540 | TT_Task | Coupler cover test | 21/04/2022 | 21/04/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 193 | 1653707999_193
A208550 | TT_Task | Light system routine test for Saloon,Cab,head,tail,marker,maintenance and emergency light | 21/04/2022 | 22/04/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 194 | 1653707999_194
A208560 | TT_Task | ACM Software download,Auxilary Power supply check, 3 phase CB check, Shore supply check, | 14/04/2022 | 15/04/2022 | nan | nan | 64 | TK_NotStart | 1653707999 | 195 | 1653707999_195
A208570 | TT_Task | Door Routine test for saloon, cab, partition,intermediate and emergency doors | 21/04/2022 | 23/04/2022 | nan | nan | 12 | TK_NotStart | 1653707999 | 155 | 1653707999_155
A208580 | TT_Task | Wind screen wiper and washer, Horn and windscreen demister routine test | 22/04/2022 | 23/04/2022 | nan | nan | 12 | TK_NotStart | 1653707999 | 156 | 1653707999_156
A208590 | TT_Task | FSD system routine testt | 21/04/2022 | 22/04/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 153 | 1653707999_153
A208600 | TT_Task | Traction Static test | 22/04/2022 | 25/04/2022 | nan | nan | 4 | TK_NotStart | 1653707999 | 157 | 1653707999_157
A208610 | TT_Task | Initial movement, speed pickups, propulsion test (low speed) | 22/04/2022 | 23/04/2022 | nan | nan | 12 | TK_NotStart | 1653707999 | 164 | 1653707999_164
A208620 | TT_Task | PC11+uncoupling | 26/04/2022 | 26/04/2022 | nan | nan | 8 | TK_NotStart | 1653707999 | 196 | 1653707999_196
A208630 | TT_Task | High voltage test, Pan up/down test, Primary voltage feedback test, | 19/04/2022 | 20/04/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 197 | 1653707999_197
A183380 | TT_Task | TS (RRTS prototype 1) - Logistic | 30/04/2022 | 05/05/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 166 | 1653707999_166
A208370 | TT_Task | Packing | 28/04/2022 | 29/04/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 198 | 1653707999_198
A171440 | TT_Task | Testing | 31/01/2022 | 23/02/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 199 | 1653707999_199
A171450 | TT_Task | Testing | 24/02/2022 | 22/03/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 199 | 1653707999_199
A171700 | TT_Task | Testing | 23/03/2022 | 14/04/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 199 | 1653707999_199
A171710 | TT_Task | Testing | 15/04/2022 | 11/05/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 199 | 1653707999_199
A171960 | TT_Task | Testing | 12/05/2022 | 08/06/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 199 | 1653707999_199
A171970 | TT_Task | Testing | 09/06/2022 | 11/07/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 199 | 1653707999_199
A172220 | TT_Task | Testing | 12/07/2022 | 09/08/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 199 | 1653707999_199
A172230 | TT_Task | Testing | 10/08/2022 | 30/08/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 199 | 1653707999_199
A172480 | TT_Task | Testing | 31/08/2022 | 27/09/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 199 | 1653707999_199
A172490 | TT_Task | Testing | 28/09/2022 | 19/10/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 199 | 1653707999_199
A172740 | TT_Task | Testing | 20/10/2022 | 07/11/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 199 | 1653707999_199
A172750 | TT_Task | Testing | 08/11/2022 | 01/12/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 199 | 1653707999_199
A173000 | TT_Task | Testing | 02/12/2022 | 28/12/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 199 | 1653707999_199
A173010 | TT_Task | Testing | 29/12/2022 | 26/01/2023 | nan | nan | 0 | TK_NotStart | 1653707999 | 199 | 1653707999_199
A173260 | TT_Task | Testing | 27/01/2023 | 16/02/2023 | nan | nan | 0 | TK_NotStart | 1653707999 | 199 | 1653707999_199
A173270 | TT_Task | Testing | 17/02/2023 | 14/03/2023 | nan | nan | 0 | TK_NotStart | 1653707999 | 199 | 1653707999_199
A173400 | TT_Task | Testing | 15/03/2023 | 11/04/2023 | nan | nan | 0 | TK_NotStart | 1653707999 | 199 | 1653707999_199
A173650 | TT_Task | Testing | 12/04/2023 | 03/05/2023 | nan | nan | 0 | TK_NotStart | 1653707999 | 199 | 1653707999_199
A173660 | TT_Task | Testing | 04/05/2023 | 25/05/2023 | nan | nan | 0 | TK_NotStart | 1653707999 | 199 | 1653707999_199
A173910 | TT_Task | Testing | 26/05/2023 | 15/06/2023 | nan | nan | 0 | TK_NotStart | 1653707999 | 199 | 1653707999_199
A173920 | TT_Task | Testing | 16/06/2023 | 11/07/2023 | nan | nan | 0 | TK_NotStart | 1653707999 | 199 | 1653707999_199
A174170 | TT_Task | Testing | 12/07/2023 | 07/08/2023 | nan | nan | 0 | TK_NotStart | 1653707999 | 199 | 1653707999_199
A174180 | TT_Task | Testing | 08/08/2023 | 05/09/2023 | nan | nan | 0 | TK_NotStart | 1653707999 | 199 | 1653707999_199
A174430 | TT_Task | Testing | 06/09/2023 | 22/09/2023 | nan | nan | 0 | TK_NotStart | 1653707999 | 199 | 1653707999_199
A174440 | TT_Task | Testing | 25/09/2023 | 24/10/2023 | nan | nan | 0 | TK_NotStart | 1653707999 | 199 | 1653707999_199
A174690 | TT_Task | Testing | 25/10/2023 | 22/11/2023 | nan | nan | 0 | TK_NotStart | 1653707999 | 199 | 1653707999_199
A174700 | TT_Task | Testing | 23/11/2023 | 21/12/2023 | nan | nan | 6607 | TK_NotStart | 1653707999 | 199 | 1653707999_199
A174730 | TT_Task | Testing | 31/01/2022 | 28/03/2022 | nan | nan | 10231 | TK_NotStart | 1653707999 | 199 | 1653707999_199
A174740 | TT_Task | Testing | 31/01/2022 | 21/03/2022 | nan | nan | 10271 | TK_NotStart | 1653707999 | 199 | 1653707999_199
A174750 | TT_Task | Testing | 31/01/2022 | 07/04/2022 | nan | nan | 10167 | TK_NotStart | 1653707999 | 199 | 1653707999_199
A174760 | TT_Task | Testing | 31/01/2022 | 31/03/2022 | nan | nan | 10207 | TK_NotStart | 1653707999 | 199 | 1653707999_199
A174770 | TT_Task | Testing | 31/01/2022 | 01/04/2022 | nan | nan | 10199 | TK_NotStart | 1653707999 | 199 | 1653707999_199
A174780 | TT_Task | Testing | 31/01/2022 | 01/04/2022 | nan | nan | 10199 | TK_NotStart | 1653707999 | 199 | 1653707999_199
A174790 | TT_Task | Testing | 31/01/2022 | 01/04/2022 | nan | nan | 10199 | TK_NotStart | 1653707999 | 199 | 1653707999_199
A174800 | TT_Task | Testing | 31/01/2022 | 01/04/2022 | nan | nan | 10199 | TK_NotStart | 1653707999 | 199 | 1653707999_199
A174810 | TT_Task | Testing | 31/01/2022 | 01/04/2022 | nan | nan | 10199 | TK_NotStart | 1653707999 | 199 | 1653707999_199
A183390 | TT_Task | TS (RRTS prototype 2) | 30/06/2022 | 08/07/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 200 | 1653707999_200
A183400 | TT_Task | TS RRTS #3 | 02/08/2022 | 10/08/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 201 | 1653707999_201
A183410 | TT_Task | TS RRTS #4 | 01/09/2022 | 10/09/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 201 | 1653707999_201
A183420 | TT_Task | TS RRTS #5 | 06/10/2022 | 14/10/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 201 | 1653707999_201
A183430 | TT_Task | TS RRTS #6 | 31/10/2022 | 08/11/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 201 | 1653707999_201
A183440 | TT_Task | TS RRTS #7 | 15/11/2022 | 23/11/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 201 | 1653707999_201
A183450 | TT_Task | TS RRTS #8 | 03/01/2023 | 10/01/2023 | nan | nan | 0 | TK_NotStart | 1653707999 | 201 | 1653707999_201
A183460 | TT_Task | TS RRTS #9 | 10/02/2023 | 18/02/2023 | nan | nan | 0 | TK_NotStart | 1653707999 | 201 | 1653707999_201
A183470 | TT_Task | TS RRTS #10 | 08/03/2023 | 16/03/2023 | nan | nan | 0 | TK_NotStart | 1653707999 | 201 | 1653707999_201
A183480 | TT_Task | TS RRTS #11 | 04/04/2023 | 11/04/2023 | nan | nan | 0 | TK_NotStart | 1653707999 | 201 | 1653707999_201
A183490 | TT_Task | TS RRTS #12 | 22/04/2023 | 01/05/2023 | nan | nan | 0 | TK_NotStart | 1653707999 | 201 | 1653707999_201
A183500 | TT_Task | TS RRTS #13 | 13/05/2023 | 22/05/2023 | nan | nan | 0 | TK_NotStart | 1653707999 | 202 | 1653707999_202
A183510 | TT_Task | TS RRTS #14 | 13/06/2023 | 21/06/2023 | nan | nan | 0 | TK_NotStart | 1653707999 | 202 | 1653707999_202
A183520 | TT_Task | TS RRTS #15 | 12/07/2023 | 20/07/2023 | nan | nan | 0 | TK_NotStart | 1653707999 | 202 | 1653707999_202
A183530 | TT_Task | TS RRTS #16 | 09/08/2023 | 17/08/2023 | nan | nan | 0 | TK_NotStart | 1653707999 | 202 | 1653707999_202
A183540 | TT_Task | TS RRTS #17 | 07/09/2023 | 15/09/2023 | nan | nan | 0 | TK_NotStart | 1653707999 | 202 | 1653707999_202
A183550 | TT_Task | TS RRTS #18 | 06/10/2023 | 14/10/2023 | nan | nan | 0 | TK_NotStart | 1653707999 | 202 | 1653707999_202
A183560 | TT_Task | TS RRTS #19 | 04/11/2023 | 15/11/2023 | nan | nan | 0 | TK_NotStart | 1653707999 | 202 | 1653707999_202
A183570 | TT_Task | TS RRTS #20 | 09/12/2023 | 18/12/2023 | nan | nan | 0 | TK_NotStart | 1653707999 | 202 | 1653707999_202
A183580 | TT_Task | TS RRTS #21 | 09/01/2024 | 17/01/2024 | nan | nan | 0 | TK_NotStart | 1653707999 | 202 | 1653707999_202
A183590 | TT_Task | TS RRTS #22 | 07/02/2024 | 15/02/2024 | nan | nan | 0 | TK_NotStart | 1653707999 | 202 | 1653707999_202
A183600 | TT_Task | TS MRTS #1 | 27/04/2024 | 06/05/2024 | nan | nan | 0 | TK_NotStart | 1653707999 | 203 | 1653707999_203
A183610 | TT_Task | TS RRTS #23 | 06/03/2024 | 14/03/2024 | nan | nan | 0 | TK_NotStart | 1653707999 | 202 | 1653707999_202
A183620 | TT_Task | TS RRTS #24 | 29/03/2024 | 06/04/2024 | nan | nan | 0 | TK_NotStart | 1653707999 | 202 | 1653707999_202
A183630 | TT_Task | TS RRTS #25 | 10/04/2024 | 17/04/2024 | nan | nan | 0 | TK_NotStart | 1653707999 | 202 | 1653707999_202
A183640 | TT_Task | TS RRTS #26 | 29/05/2024 | 05/06/2024 | nan | nan | 0 | TK_NotStart | 1653707999 | 202 | 1653707999_202
A183650 | TT_Task | TS MRTS #2 | 03/07/2024 | 11/07/2024 | nan | nan | 0 | TK_NotStart | 1653707999 | 203 | 1653707999_203
A183660 | TT_Task | TS RRTS #27 | 21/06/2024 | 29/06/2024 | nan | nan | 0 | TK_NotStart | 1653707999 | 202 | 1653707999_202
A183670 | TT_Task | TS MRTS #3 | 10/07/2024 | 18/07/2024 | nan | nan | 0 | TK_NotStart | 1653707999 | 203 | 1653707999_203
A183680 | TT_Task | TS RRTS #28 | 23/08/2024 | 02/09/2024 | nan | nan | 0 | TK_NotStart | 1653707999 | 202 | 1653707999_202
A183690 | TT_Task | TS RRTS #29 | 25/09/2024 | 04/10/2024 | nan | nan | 0 | TK_NotStart | 1653707999 | 202 | 1653707999_202
A183700 | TT_Task | TS MRTS #4 | 28/09/2024 | 09/10/2024 | nan | nan | 0 | TK_NotStart | 1653707999 | 203 | 1653707999_203
A183710 | TT_Task | TS RRTS #30 | 23/10/2024 | 31/10/2024 | nan | nan | 0 | TK_NotStart | 1653707999 | 202 | 1653707999_202
A183720 | TT_Task | TS MRTS #5 | 21/11/2024 | 29/11/2024 | nan | nan | 0 | TK_NotStart | 1653707999 | 203 | 1653707999_203
A183730 | TT_Task | TS MRTS #6 | 04/12/2024 | 11/12/2024 | nan | nan | 0 | TK_NotStart | 1653707999 | 203 | 1653707999_203
A183740 | TT_Task | TS MRTS #7 | 17/12/2024 | 24/12/2024 | nan | nan | 0 | TK_NotStart | 1653707999 | 203 | 1653707999_203
A183750 | TT_Task | TS MRTS #8 | 02/01/2025 | 10/01/2025 | nan | nan | 0 | TK_NotStart | 1653707999 | 203 | 1653707999_203
A183760 | TT_Task | TS MRTS #9 | 16/01/2025 | 23/01/2025 | nan | nan | 0 | TK_NotStart | 1653707999 | 203 | 1653707999_203
A183770 | TT_Task | TS MRTS #10 | 30/01/2025 | 07/02/2025 | nan | nan | 0 | TK_NotStart | 1653707999 | 203 | 1653707999_203
A183780 | TT_Task | T;C, Integrated Testing ; service trail of RRTS TS #1 | 06/05/2022 | 15/10/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 204 | 1653707999_204
A183790 | TT_Task | T;C, Integrated Testing ; service trail of RRTS TS #2 | 08/07/2022 | 14/11/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 204 | 1653707999_204
A183800 | TT_Task | T;C, Integrated Testing ; service trail of RRTS TS #3 | 10/08/2022 | 20/01/2023 | nan | nan | 0 | TK_NotStart | 1653707999 | 204 | 1653707999_204
A183810 | TT_Task | T;C, Integrated Testing ; service trail of RRTS TS #4 | 10/09/2022 | 01/11/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 204 | 1653707999_204
A183820 | TT_Task | T;C, Integrated Testing ; service trail of RRTS TS #5 | 14/10/2022 | 03/12/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 204 | 1653707999_204
A183830 | TT_Task | T;C, Integrated Testing ; service trail of RRTS TS #6 | 08/11/2022 | 24/12/2022 | nan | nan | 0 | TK_NotStart | 1653707999 | 204 | 1653707999_204
A183840 | TT_Task | T;C, Integrated Testing ; service trail of RRTS TS #7 | 23/11/2022 | 09/01/2023 | nan | nan | 0 | TK_NotStart | 1653707999 | 204 | 1653707999_204
A183850 | TT_Task | T;C, Integrated Testing ; service trail of RRTS TS #8 | 11/01/2023 | 27/02/2023 | nan | nan | 0 | TK_NotStart | 1653707999 | 204 | 1653707999_204
A183860 | TT_Task | T;C, Integrated Testing ; service trail of RRTS TS #9 | 18/02/2023 | 07/04/2023 | nan | nan | 0 | TK_NotStart | 1653707999 | 204 | 1653707999_204
A183870 | TT_Task | T;C, Integrated Testing ; service trail of RRTS TS #10 | 16/03/2023 | 02/05/2023 | nan | nan | 0 | TK_NotStart | 1653707999 | 204 | 1653707999_204
A183880 | TT_Task | T;C, Integrated Testing ; service trail of RRTS TS #11 | 12/04/2023 | 27/05/2023 | nan | nan | 0 | TK_NotStart | 1653707999 | 204 | 1653707999_204
A183890 | TT_Task | T;C, Integrated Testing ; service trail of RRTS TS #12 | 01/05/2023 | 16/06/2023 | nan | nan | 0 | TK_NotStart | 1653707999 | 204 | 1653707999_204
A183900 | TT_Task | T;C, Integrated Testing ; service trail of RRTS TS #13 | 22/05/2023 | 07/07/2023 | nan | nan | 0 | TK_NotStart | 1653707999 | 204 | 1653707999_204
A183910 | TT_Task | T;C, Integrated Testing ; service trail of RRTS TS #14 | 21/06/2023 | 07/08/2023 | nan | nan | 0 | TK_NotStart | 1653707999 | 204 | 1653707999_204
A183920 | TT_Task | T;C, Integrated Testing ; service trail of RRTS TS #15 | 20/07/2023 | 08/09/2023 | nan | nan | 0 | TK_NotStart | 1653707999 | 204 | 1653707999_204
A183930 | TT_Task | T;C, Integrated Testing ; service trail of RRTS TS #16 | 18/08/2023 | 05/10/2023 | nan | nan | 0 | TK_NotStart | 1653707999 | 204 | 1653707999_204
A183940 | TT_Task | T;C, Integrated Testing ; service trail of RRTS TS #17 | 15/09/2023 | 02/11/2023 | nan | nan | 0 | TK_NotStart | 1653707999 | 204 | 1653707999_204
A183950 | TT_Task | T;C, Integrated Testing ; service trail of RRTS TS #18 | 14/10/2023 | 04/12/2023 | nan | nan | 0 | TK_NotStart | 1653707999 | 204 | 1653707999_204
A183960 | TT_Task | T;C, Integrated Testing ; service trail of RRTS TS #19 | 15/11/2023 | 02/01/2024 | nan | nan | 0 | TK_NotStart | 1653707999 | 204 | 1653707999_204
A183970 | TT_Task | T;C, Integrated Testing ; service trail of RRTS TS #20 | 18/12/2023 | 06/02/2024 | nan | nan | 0 | TK_NotStart | 1653707999 | 204 | 1653707999_204
A183980 | TT_Task | T;C, Integrated Testing ; service trail of RRTS TS #21 | 18/01/2024 | 05/03/2024 | nan | nan | 0 | TK_NotStart | 1653707999 | 204 | 1653707999_204
A183990 | TT_Task | T;C, Integrated Testing ; service trail of RRTS TS #22 | 15/02/2024 | 03/04/2024 | nan | nan | 0 | TK_NotStart | 1653707999 | 204 | 1653707999_204
A184000 | TT_Task | T;C, Integrated Testing ; service trail of RRTS TS #23 | 14/03/2024 | 01/05/2024 | nan | nan | 0 | TK_NotStart | 1653707999 | 204 | 1653707999_204
A184010 | TT_Task | T;C, Integrated Testing ; service trail of MRTS TS#1 | 06/05/2024 | 21/08/2024 | nan | nan | 0 | TK_NotStart | 1653707999 | 205 | 1653707999_205
A184020 | TT_Task | T;C, Integrated Testing ; service trail of RRTS TS #24 | 06/04/2024 | 23/05/2024 | nan | nan | 0 | TK_NotStart | 1653707999 | 204 | 1653707999_204
A184030 | TT_Task | T;C, Integrated Testing ; service trail of RRTS TS #25 | 18/04/2024 | 03/06/2024 | nan | nan | 0 | TK_NotStart | 1653707999 | 204 | 1653707999_204
A184040 | TT_Task | T;C, Integrated Testing ; service trail of RRTS TS #26 | 06/06/2024 | 22/07/2024 | nan | nan | 0 | TK_NotStart | 1653707999 | 204 | 1653707999_204
A184050 | TT_Task | T;C, Integrated Testing ; service trail of RRTS TS #27 | 29/06/2024 | 16/08/2024 | nan | nan | 0 | TK_NotStart | 1653707999 | 204 | 1653707999_204
A184060 | TT_Task | T;C, Integrated Testing ; service trail of MRTS TS#2 | 11/07/2024 | 24/09/2024 | nan | nan | 0 | TK_NotStart | 1653707999 | 205 | 1653707999_205
A184070 | TT_Task | T;C, Integrated Testing ; service trail of RRTS TS #28 | 02/09/2024 | 22/10/2024 | nan | nan | 0 | TK_NotStart | 1653707999 | 204 | 1653707999_204
A184080 | TT_Task | T;C, Integrated Testing ; service trail of RRTS TS #29 | 05/10/2024 | 20/11/2024 | nan | nan | 0 | TK_NotStart | 1653707999 | 204 | 1653707999_204
A184090 | TT_Task | T;C, Integrated Testing ; service trail of MRTS TS#3 | 18/07/2024 | 06/09/2024 | nan | nan | 0 | TK_NotStart | 1653707999 | 205 | 1653707999_205
A184100 | TT_Task | T;C, Integrated Testing ; service trail of RRTS TS #30 | 31/10/2024 | 17/12/2024 | nan | nan | 0 | TK_NotStart | 1653707999 | 204 | 1653707999_204
A184110 | TT_Task | T;C, Integrated Testing ; service trail of MRTS TS#4 | 09/10/2024 | 25/11/2024 | nan | nan | 0 | TK_NotStart | 1653707999 | 205 | 1653707999_205
A184120 | TT_Task | T;C, Integrated Testing ; service trail of MRTS TS#5 | 29/11/2024 | 17/01/2025 | nan | nan | 0 | TK_NotStart | 1653707999 | 205 | 1653707999_205
A184130 | TT_Task | T;C, Integrated Testing ; service trail of MRTS TS#6 | 12/12/2024 | 29/01/2025 | nan | nan | 0 | TK_NotStart | 1653707999 | 205 | 1653707999_205
A184140 | TT_Task | T;C, Integrated Testing ; service trail of MRTS TS#7 | 25/12/2024 | 11/02/2025 | nan | nan | 0 | TK_NotStart | 1653707999 | 205 | 1653707999_205
A184150 | TT_Task | T;C, Integrated Testing ; service trail of MRTS TS#8 | 10/01/2025 | 28/02/2025 | nan | nan | 0 | TK_NotStart | 1653707999 | 205 | 1653707999_205
A184160 | TT_Task | T;C, Integrated Testing ; service trail of MRTS TS#9 | 24/01/2025 | 11/03/2025 | nan | nan | 0 | TK_NotStart | 1653707999 | 205 | 1653707999_205
A184170 | TT_Task | T;C, Integrated Testing ; service trail of MRTS TS#10 | 07/02/2025 | 27/03/2025 | nan | nan | 0 | TK_NotStart | 1653707999 | 205 | 1653707999_205
MOCK100390 | TT_Task | Mock-up Development and Customer Review Phase for Mock up | 16/02/2021 | 31/05/2021 | 16/02/2021 | 31/05/2021 | 0 | TK_Complete | 222308392 | 1 | 222308392_1
MOCK100380 | TT_Task | Design Freeze for Mock up | 01/06/2021 | 07/07/2021 | 01/06/2021 | 06/07/2021 | 0 | TK_Complete | 222308392 | 2 | 222308392_2
MOCK100220 | TT_Task | Concept Development and Supplier Contracting of Mock-up | 15/12/2020 | 15/02/2021 | 15/12/2020 | 15/02/2021 | 0 | TK_Complete | 222308392 | 1 | 222308392_1
A157480 | TT_Task | Warranty Period of the Last Train for Customer Site Management Warranty (Base Order) | 18/07/2028 | 16/07/2032 | nan | nan | 0 | TK_NotStart | 222308392 | 3 | 222308392_3
PROD115300 | TT_Task | Vehicle 001 - Dynamische IBS - Kunde | 03/08/2023 | 21/09/2023 | nan | nan | 0 | TK_NotStart | 222308392 | 4 | 222308392_4
PROD115320 | TT_Task | Vehicle 001 - Trial Operation gem. 16.2 | 18/12/2023 | 08/03/2024 | nan | nan | 0 | TK_NotStart | 222308392 | 5 | 222308392_5
PROD115330 | TT_Task | Vehicle 001 - Abnahme durch BVG | 02/09/2024 | 02/09/2024 | nan | nan | 0 | TK_NotStart | 222308392 | 6 | 222308392_6
PROD115470 | TT_Task | Vehicle 002 - Rohbau (first module) | 21/06/2022 | 25/11/2022 | nan | nan | 0 | TK_NotStart | 222308392 | 7 | 222308392_7
PROD115480 | TT_Task | Vehicle 002 - Oberflache (first module) | 30/01/2023 | 22/02/2023 | nan | nan | 0 | TK_NotStart | 222308392 | 8 | 222308392_8
PROD115490 | TT_Task | Vehicle 002 - Innenausbau | 23/02/2023 | 01/06/2023 | nan | nan | 0 | TK_NotStart | 222308392 | 9 | 222308392_9
PROD115500 | TT_Task | Vehicle 002 - Statistic ; Dynamic IBS | 02/06/2023 | 25/08/2023 | nan | nan | 0 | TK_NotStart | 222308392 | 10 | 222308392_10
PROD115510 | TT_Task | Vehicle 002 - Versand zum Kunde | 28/08/2023 | 31/08/2023 | nan | nan | 0 | TK_NotStart | 222308392 | 4 | 222308392_4
PROD115430 | TT_Task | Vehicle 002 - Kunden IBS ; Testphase | 01/09/2023 | 28/11/2023 | nan | nan | 0 | TK_NotStart | 222308392 | 11 | 222308392_11
PROD115450 | TT_Task | Vehicle 002 - Trial Operation gem. 16.2 | 29/11/2023 | 20/02/2024 | nan | nan | 0 | TK_NotStart | 222308392 | 5 | 222308392_5
PROD115460 | TT_Task | Vehicle 002 - Abnahme durch BVG | 02/09/2024 | 02/09/2024 | nan | nan | 0 | TK_NotStart | 222308392 | 6 | 222308392_6
PROD115560 | TT_Task | Vehicle 004 - Rohbau (first module) | 21/12/2022 | 25/04/2023 | nan | nan | 0 | TK_NotStart | 222308392 | 7 | 222308392_7
PROD115570 | TT_Task | Vehicle 004 - Oberflache (first module) | 26/04/2023 | 22/05/2023 | nan | nan | 0 | TK_NotStart | 222308392 | 8 | 222308392_8
PROD115580 | TT_Task | Vehicle 004 - Innenausbau | 23/05/2023 | 28/07/2023 | nan | nan | 0 | TK_NotStart | 222308392 | 9 | 222308392_9
PROD115590 | TT_Task | Vehicle 004 - Statistic ; Dynamic IBS | 31/07/2023 | 11/10/2023 | nan | nan | 0 | TK_NotStart | 222308392 | 10 | 222308392_10
PROD115600 | TT_Task | Vehicle 004 - Versand zum Kunde | 25/03/2024 | 28/03/2024 | nan | nan | 0 | TK_NotStart | 222308392 | 4 | 222308392_4
PROD115520 | TT_Task | Vehicle 004 - Kunden IBS ; Testphase | 29/03/2024 | 29/05/2024 | nan | nan | 0 | TK_NotStart | 222308392 | 11 | 222308392_11
PROD115540 | TT_Task | Vehicle 004 - Trial Operation gem. 16.2 | 30/05/2024 | 21/08/2024 | nan | nan | 0 | TK_NotStart | 222308392 | 5 | 222308392_5
PROD115550 | TT_Task | Vehicle 004 - Abnahme durch BVG | 15/10/2024 | 15/10/2024 | nan | nan | 0 | TK_NotStart | 222308392 | 6 | 222308392_6
PROD115650 | TT_Task | Vehicle 005 - Rohbau (first module) | 01/02/2023 | 29/05/2023 | nan | nan | 0 | TK_NotStart | 222308392 | 7 | 222308392_7
PROD115660 | TT_Task | Vehicle 005 - Oberflache (first module) | 30/05/2023 | 22/06/2023 | nan | nan | 0 | TK_NotStart | 222308392 | 8 | 222308392_8
PROD115670 | TT_Task | Vehicle 005 - Innenausbau | 23/06/2023 | 12/09/2023 | nan | nan | 0 | TK_NotStart | 222308392 | 9 | 222308392_9
PROD115680 | TT_Task | Vehicle 005 - Statistic ; Dynamic IBS | 13/09/2023 | 30/11/2023 | nan | nan | 0 | TK_NotStart | 222308392 | 10 | 222308392_10
PROD115690 | TT_Task | Vehicle 005 - Versand zum Kunde | 01/12/2023 | 06/12/2023 | nan | nan | 0 | TK_NotStart | 222308392 | 4 | 222308392_4
PROD115610 | TT_Task | Vehicle 005 - Kunden IBS ; Testphase | 07/12/2023 | 29/01/2024 | nan | nan | 0 | TK_NotStart | 222308392 | 11 | 222308392_11
PROD115630 | TT_Task | Vehicle 005 - Trial Operation gem. 16.2 | 30/01/2024 | 22/04/2024 | nan | nan | 0 | TK_NotStart | 222308392 | 5 | 222308392_5
PROD115640 | TT_Task | Vehicle 005 - Abnahme durch BVG | 03/09/2024 | 03/09/2024 | nan | nan | 0 | TK_NotStart | 222308392 | 6 | 222308392_6
PROD115740 | TT_Task | Vehicle 006 - Rohbau (first module) | 15/03/2023 | 11/07/2023 | nan | nan | 0 | TK_NotStart | 222308392 | 7 | 222308392_7
PROD115750 | TT_Task | Vehicle 006 - Oberflache (first module) | 12/07/2023 | 17/08/2023 | nan | nan | 0 | TK_NotStart | 222308392 | 8 | 222308392_8
PROD115760 | TT_Task | Vehicle 006 - Innenausbau | 18/08/2023 | 26/10/2023 | nan | nan | 0 | TK_NotStart | 222308392 | 9 | 222308392_9
PROD115770 | TT_Task | Vehicle 006 - Statistic ; Dynamic IBS | 27/10/2023 | 09/01/2024 | nan | nan | 0 | TK_NotStart | 222308392 | 10 | 222308392_10
PROD115780 | TT_Task | Vehicle 006 - Versand zum Kunde | 08/03/2024 | 13/03/2024 | nan | nan | 0 | TK_NotStart | 222308392 | 4 | 222308392_4
PROD115700 | TT_Task | Vehicle 006 - Kunden IBS ; Testphase | 14/03/2024 | 06/05/2024 | nan | nan | 0 | TK_NotStart | 222308392 | 11 | 222308392_11
PROD115720 | TT_Task | Vehicle 006 - Trial Operation gem. 16.2 | 07/05/2024 | 29/07/2024 | nan | nan | 0 | TK_NotStart | 222308392 | 5 | 222308392_5
PROD115730 | TT_Task | Vehicle 006 - Abnahme durch BVG | 26/09/2024 | 26/09/2024 | nan | nan | 0 | TK_NotStart | 222308392 | 6 | 222308392_6
PROD115830 | TT_Task | Vehicle 007 - Rohbau | 29/09/2023 | 29/09/2023 | nan | nan | 0 | TK_NotStart | 222308392 | 12 | 222308392_12
PROD115840 | TT_Task | Vehicle 007 - Oberflache | 29/09/2023 | 29/09/2023 | nan | nan | 0 | TK_NotStart | 222308392 | 13 | 222308392_13
PROD115850 | TT_Task | Vehicle 007 - Ausbau II | 29/09/2023 | 20/08/2024 | nan | nan | 0 | TK_NotStart | 222308392 | 14 | 222308392_14
PROD115860 | TT_Task | Vehicle 007 - Statistic ; Dynamic IBS | 21/08/2024 | 15/11/2024 | nan | nan | 0 | TK_NotStart | 222308392 | 10 | 222308392_10
PROD115870 | TT_Task | Vehicle 007 - Versand zum Kunde | 18/11/2024 | 20/11/2024 | nan | nan | 0 | TK_NotStart | 222308392 | 4 | 222308392_4
PROD115790 | TT_Task | Vehicle 007 - Kunden IBS ; Testphase | 21/11/2024 | 14/01/2025 | nan | nan | 0 | TK_NotStart | 222308392 | 11 | 222308392_11
PROD115810 | TT_Task | Vehicle 007 - Trial Operation | 15/01/2025 | 08/04/2025 | nan | nan | 0 | TK_NotStart | 222308392 | 15 | 222308392_15
PROD115820 | TT_Task | Vehicle 007 - Abnahme durch BVG | 09/04/2025 | 09/04/2025 | nan | nan | 0 | TK_NotStart | 222308392 | 6 | 222308392_6
PROD115920 | TT_Task | Vehicle 008 - Rohbau | 08/07/2024 | 08/07/2024 | nan | nan | 0 | TK_NotStart | 222308392 | 12 | 222308392_12
PROD115930 | TT_Task | Vehicle 008 - Oberflache | 08/07/2024 | 08/07/2024 | nan | nan | 0 | TK_NotStart | 222308392 | 13 | 222308392_13
PROD115940 | TT_Task | Vehicle 008 - Ausbau II | 08/07/2024 | 26/09/2024 | nan | nan | 0 | TK_NotStart | 222308392 | 14 | 222308392_14
PROD115950 | TT_Task | Vehicle 008 - Statistic ; Dynamic IBS | 27/09/2024 | 06/01/2025 | nan | nan | 0 | TK_NotStart | 222308392 | 10 | 222308392_10
PROD115960 | TT_Task | Vehicle 008 - Versand zum Kunde | 07/01/2025 | 09/01/2025 | nan | nan | 0 | TK_NotStart | 222308392 | 4 | 222308392_4
PROD115880 | TT_Task | Vehicle 008 - Kunden IBS ; Testphase | 10/01/2025 | 17/03/2025 | nan | nan | 0 | TK_NotStart | 222308392 | 11 | 222308392_11
PROD115900 | TT_Task | Vehicle 008 - Trial Operation | 18/03/2025 | 09/06/2025 | nan | nan | 0 | TK_NotStart | 222308392 | 15 | 222308392_15
PROD115910 | TT_Task | Vehicle 008 - Abnahme durch BVG | 10/06/2025 | 10/06/2025 | nan | nan | 0 | TK_NotStart | 222308392 | 6 | 222308392_6
PROD116010 | TT_Task | Vehicle 009 - Rohbau | 30/08/2024 | 30/08/2024 | nan | nan | 0 | TK_NotStart | 222308392 | 12 | 222308392_12
PROD116020 | TT_Task | Vehicle 009 - Oberflache | 30/08/2024 | 30/08/2024 | nan | nan | 0 | TK_NotStart | 222308392 | 13 | 222308392_13
PROD116030 | TT_Task | Vehicle 009 - Ausbau II | 30/08/2024 | 24/10/2024 | nan | nan | 0 | TK_NotStart | 222308392 | 14 | 222308392_14
PROD116040 | TT_Task | Vehicle 009 - Statistic ; Dynamic IBS | 25/10/2024 | 30/01/2025 | nan | nan | 0 | TK_NotStart | 222308392 | 10 | 222308392_10
PROD116050 | TT_Task | Vehicle 009 - Versand zum Kunde | 31/01/2025 | 04/02/2025 | nan | nan | 0 | TK_NotStart | 222308392 | 4 | 222308392_4
PROD115970 | TT_Task | Vehicle 009 - Kunden IBS ; Testphase | 05/02/2025 | 31/03/2025 | nan | nan | 0 | TK_NotStart | 222308392 | 11 | 222308392_11
PROD115990 | TT_Task | Vehicle 009 - Trial Operation | 01/04/2025 | 23/06/2025 | nan | nan | 0 | TK_NotStart | 222308392 | 15 | 222308392_15
PROD116000 | TT_Task | Vehicle 009 - Abnahme durch BVG | 24/06/2025 | 24/06/2025 | nan | nan | 0 | TK_NotStart | 222308392 | 6 | 222308392_6
PROD116100 | TT_Task | Vehicle 010 - Rohbau | 25/09/2024 | 25/09/2024 | nan | nan | 0 | TK_NotStart | 222308392 | 12 | 222308392_12
PROD116110 | TT_Task | Vehicle 010 - Oberflache | 25/09/2024 | 25/09/2024 | nan | nan | 0 | TK_NotStart | 222308392 | 13 | 222308392_13
PROD116120 | TT_Task | Vehicle 010 - Ausbau II | 25/09/2024 | 22/11/2024 | nan | nan | 0 | TK_NotStart | 222308392 | 14 | 222308392_14
PROD116130 | TT_Task | Vehicle 010 - Statistic ; Dynamic IBS | 25/11/2024 | 25/02/2025 | nan | nan | 0 | TK_NotStart | 222308392 | 10 | 222308392_10
PROD116140 | TT_Task | Vehicle 010 - Versand zum Kunde | 26/02/2025 | 28/02/2025 | nan | nan | 0 | TK_NotStart | 222308392 | 4 | 222308392_4
PROD116060 | TT_Task | Vehicle 010 - Kunden IBS ; Testphase | 03/03/2025 | 24/04/2025 | nan | nan | 0 | TK_NotStart | 222308392 | 11 | 222308392_11
PROD116080 | TT_Task | Vehicle 010 - Trial Operation | 25/04/2025 | 17/07/2025 | nan | nan | 0 | TK_NotStart | 222308392 | 15 | 222308392_15
PROD116090 | TT_Task | Vehicle 010 - Abnahme durch BVG | 18/07/2025 | 18/07/2025 | nan | nan | 0 | TK_NotStart | 222308392 | 6 | 222308392_6
PROD116190 | TT_Task | Vehicle 011 - Rohbau | 23/10/2024 | 23/10/2024 | nan | nan | 0 | TK_NotStart | 222308392 | 12 | 222308392_12
PROD116200 | TT_Task | Vehicle 011 - Oberflache | 23/10/2024 | 23/10/2024 | nan | nan | 0 | TK_NotStart | 222308392 | 13 | 222308392_13
PROD116210 | TT_Task | Vehicle 011 - Ausbau II | 23/10/2024 | 18/12/2024 | nan | nan | 0 | TK_NotStart | 222308392 | 14 | 222308392_14
PROD116220 | TT_Task | Vehicle 011 - Statistic ; Dynamic IBS | 19/12/2024 | 21/03/2025 | nan | nan | 0 | TK_NotStart | 222308392 | 10 | 222308392_10
PROD116230 | TT_Task | Vehicle 011 - Versand zum Kunde | 24/03/2025 | 26/03/2025 | nan | nan | 0 | TK_NotStart | 222308392 | 4 | 222308392_4
PROD116150 | TT_Task | Vehicle 011 - Kunden IBS ; Testphase | 27/03/2025 | 20/05/2025 | nan | nan | 0 | TK_NotStart | 222308392 | 11 | 222308392_11
PROD116170 | TT_Task | Vehicle 011 - Trial Operation | 21/05/2025 | 12/08/2025 | nan | nan | 0 | TK_NotStart | 222308392 | 15 | 222308392_15
PROD116180 | TT_Task | Vehicle 011 - Abnahme durch BVG | 13/08/2025 | 13/08/2025 | nan | nan | 0 | TK_NotStart | 222308392 | 6 | 222308392_6
PROD116280 | TT_Task | Vehicle 012 - Rohbau | 21/11/2024 | 21/11/2024 | nan | nan | 0 | TK_NotStart | 222308392 | 12 | 222308392_12
PROD116290 | TT_Task | Vehicle 012 - Oberflache | 21/11/2024 | 21/11/2024 | nan | nan | 0 | TK_NotStart | 222308392 | 13 | 222308392_13
PROD116300 | TT_Task | Vehicle 012 - Ausbau II | 21/11/2024 | 23/01/2025 | nan | nan | 0 | TK_NotStart | 222308392 | 14 | 222308392_14
PROD116310 | TT_Task | Vehicle 012 - Statistic ; Dynamic IBS | 24/01/2025 | 16/04/2025 | nan | nan | 0 | TK_NotStart | 222308392 | 10 | 222308392_10
PROD116320 | TT_Task | Vehicle 012 - Versand zum Kunde | 17/04/2025 | 21/04/2025 | nan | nan | 0 | TK_NotStart | 222308392 | 4 | 222308392_4
PROD116240 | TT_Task | Vehicle 012 - Kunden IBS ; Testphase | 22/04/2025 | 13/06/2025 | nan | nan | 0 | TK_NotStart | 222308392 | 11 | 222308392_11
PROD116260 | TT_Task | Vehicle 012 - Trial Operation | 16/06/2025 | 05/09/2025 | nan | nan | 0 | TK_NotStart | 222308392 | 15 | 222308392_15
PROD116270 | TT_Task | Vehicle 012 - Abnahme durch BVG | 08/09/2025 | 08/09/2025 | nan | nan | 0 | TK_NotStart | 222308392 | 6 | 222308392_6
PROD116370 | TT_Task | Vehicle 013 - Rohbau | 17/12/2024 | 17/12/2024 | nan | nan | 0 | TK_NotStart | 222308392 | 12 | 222308392_12
PROD116380 | TT_Task | Vehicle 013 - Oberflache | 17/12/2024 | 17/12/2024 | nan | nan | 0 | TK_NotStart | 222308392 | 13 | 222308392_13
PROD116390 | TT_Task | Vehicle 013 - Ausbau II | 17/12/2024 | 18/02/2025 | nan | nan | 0 | TK_NotStart | 222308392 | 14 | 222308392_14
PROD116400 | TT_Task | Vehicle 013 - Statistic ; Dynamic IBS | 19/02/2025 | 16/05/2025 | nan | nan | 0 | TK_NotStart | 222308392 | 10 | 222308392_10
PROD116410 | TT_Task | Vehicle 013 - Versand zum Kunde | 19/05/2025 | 21/05/2025 | nan | nan | 0 | TK_NotStart | 222308392 | 4 | 222308392_4
PROD116330 | TT_Task | Vehicle 013 - Kunden IBS ; Testphase | 22/05/2025 | 08/07/2025 | nan | nan | 0 | TK_NotStart | 222308392 | 11 | 222308392_11
PROD116350 | TT_Task | Vehicle 013 - Trial Operation | 09/07/2025 | 23/09/2025 | nan | nan | 0 | TK_NotStart | 222308392 | 15 | 222308392_15
PROD116360 | TT_Task | Vehicle 013 - Abnahme durch BVG | 24/09/2025 | 24/09/2025 | nan | nan | 0 | TK_NotStart | 222308392 | 6 | 222308392_6
PROD116460 | TT_Task | Vehicle 014 - Rohbau | 22/01/2025 | 22/01/2025 | nan | nan | 0 | TK_NotStart | 222308392 | 12 | 222308392_12
PROD116470 | TT_Task | Vehicle 014 - Oberflache | 22/01/2025 | 22/01/2025 | nan | nan | 0 | TK_NotStart | 222308392 | 13 | 222308392_13
PROD116480 | TT_Task | Vehicle 014 - Ausbau II | 22/01/2025 | 14/03/2025 | nan | nan | 0 | TK_NotStart | 222308392 | 14 | 222308392_14
PROD116490 | TT_Task | Vehicle 014 - Statistic ; Dynamic IBS | 17/03/2025 | 16/06/2025 | nan | nan | 0 | TK_NotStart | 222308392 | 10 | 222308392_10
PROD116500 | TT_Task | Vehicle 014 - Versand zum Kunde | 17/06/2025 | 19/06/2025 | nan | nan | 0 | TK_NotStart | 222308392 | 4 | 222308392_4
PROD116420 | TT_Task | Vehicle 014 - Kunden IBS ; Testphase | 20/06/2025 | 13/08/2025 | nan | nan | 0 | TK_NotStart | 222308392 | 11 | 222308392_11
PROD116440 | TT_Task | Vehicle 014 - Trial Operation | 14/08/2025 | 29/10/2025 | nan | nan | 0 | TK_NotStart | 222308392 | 15 | 222308392_15
PROD116450 | TT_Task | Vehicle 014 - Abnahme durch BVG | 30/10/2025 | 30/10/2025 | nan | nan | 0 | TK_NotStart | 222308392 | 6 | 222308392_6
PROD116550 | TT_Task | Vehicle 015 - Rohbau | 17/02/2025 | 17/02/2025 | nan | nan | 0 | TK_NotStart | 222308392 | 12 | 222308392_12
PROD116560 | TT_Task | Vehicle 015 - Oberflache | 17/02/2025 | 17/02/2025 | nan | nan | 0 | TK_NotStart | 222308392 | 13 | 222308392_13
PROD116570 | TT_Task | Vehicle 015 - Ausbau II | 17/02/2025 | 09/04/2025 | nan | nan | 0 | TK_NotStart | 222308392 | 14 | 222308392_14
PROD116580 | TT_Task | Vehicle 015 - Statistic ; Dynamic IBS | 10/04/2025 | 10/07/2025 | nan | nan | 0 | TK_NotStart | 222308392 | 10 | 222308392_10
PROD116590 | TT_Task | Vehicle 015 - Versand zum Kunde | 11/07/2025 | 15/07/2025 | nan | nan | 0 | TK_NotStart | 222308392 | 4 | 222308392_4
PROD116510 | TT_Task | Vehicle 015 - Kunden IBS ; Testphase | 16/07/2025 | 09/09/2025 | nan | nan | 0 | TK_NotStart | 222308392 | 11 | 222308392_11
PROD116530 | TT_Task | Vehicle 015 - Trial Operation | 10/09/2025 | 02/12/2025 | nan | nan | 0 | TK_NotStart | 222308392 | 15 | 222308392_15
PROD116540 | TT_Task | Vehicle 015 - Abnahme durch BVG | 03/12/2025 | 03/12/2025 | nan | nan | 0 | TK_NotStart | 222308392 | 6 | 222308392_6
PROD116640 | TT_Task | Vehicle 016 - Rohbau | 13/03/2025 | 13/03/2025 | nan | nan | 0 | TK_NotStart | 222308392 | 12 | 222308392_12
PROD116650 | TT_Task | Vehicle 016 - Oberflache | 13/03/2025 | 13/03/2025 | nan | nan | 0 | TK_NotStart | 222308392 | 13 | 222308392_13
PROD116660 | TT_Task | Vehicle 016 - Ausbau II | 13/03/2025 | 09/05/2025 | nan | nan | 0 | TK_NotStart | 222308392 | 14 | 222308392_14
PROD116670 | TT_Task | Vehicle 016 - Statistic ; Dynamic IBS | 12/05/2025 | 19/08/2025 | nan | nan | 0 | TK_NotStart | 222308392 | 10 | 222308392_10
PROD116680 | TT_Task | Vehicle 016 - Versand zum Kunde | 20/08/2025 | 22/08/2025 | nan | nan | 0 | TK_NotStart | 222308392 | 4 | 222308392_4
PROD116600 | TT_Task | Vehicle 016 - Kunden IBS ; Testphase | 25/08/2025 | 16/10/2025 | nan | nan | 0 | TK_NotStart | 222308392 | 11 | 222308392_11
PROD116620 | TT_Task | Vehicle 016 - Trial Operation | 17/10/2025 | 08/01/2026 | nan | nan | 0 | TK_NotStart | 222308392 | 15 | 222308392_15
PROD116630 | TT_Task | Vehicle 016 - Abnahme durch BVG | 09/01/2026 | 09/01/2026 | nan | nan | 0 | TK_NotStart | 222308392 | 6 | 222308392_6
PROD116730 | TT_Task | Vehicle 017 - Rohbau | 08/04/2025 | 08/04/2025 | nan | nan | 0 | TK_NotStart | 222308392 | 12 | 222308392_12
PROD116740 | TT_Task | Vehicle 017 - Oberflache | 08/04/2025 | 08/04/2025 | nan | nan | 0 | TK_NotStart | 222308392 | 13 | 222308392_13
PROD116750 | TT_Task | Vehicle 017 - Ausbau II | 08/04/2025 | 06/06/2025 | nan | nan | 0 | TK_NotStart | 222308392 | 14 | 222308392_14
PROD116760 | TT_Task | Vehicle 017 - Statistic ; Dynamic IBS | 09/06/2025 | 12/09/2025 | nan | nan | 0 | TK_NotStart | 222308392 | 10 | 222308392_10
PROD116770 | TT_Task | Vehicle 017 - Versand zum Kunde | 15/09/2025 | 17/09/2025 | nan | nan | 0 | TK_NotStart | 222308392 | 4 | 222308392_4
PROD116690 | TT_Task | Vehicle 017 - Kunden IBS ; Testphase | 18/09/2025 | 11/11/2025 | nan | nan | 0 | TK_NotStart | 222308392 | 11 | 222308392_11
PROD116710 | TT_Task | Vehicle 017 - Trial Operation | 12/11/2025 | 03/02/2026 | nan | nan | 0 | TK_NotStart | 222308392 | 15 | 222308392_15
PROD116720 | TT_Task | Vehicle 017 - Abnahme durch BVG | 04/02/2026 | 04/02/2026 | nan | nan | 0 | TK_NotStart | 222308392 | 6 | 222308392_6
PROD116820 | TT_Task | Vehicle 018 - Rohbau | 08/05/2025 | 08/05/2025 | nan | nan | 0 | TK_NotStart | 222308392 | 12 | 222308392_12
PROD116830 | TT_Task | Vehicle 018 - Oberflache | 08/05/2025 | 08/05/2025 | nan | nan | 0 | TK_NotStart | 222308392 | 13 | 222308392_13
PROD116840 | TT_Task | Vehicle 018 - Ausbau II | 08/05/2025 | 03/07/2025 | nan | nan | 0 | TK_NotStart | 222308392 | 14 | 222308392_14
PROD116850 | TT_Task | Vehicle 018 - Statistic ; Dynamic IBS | 04/07/2025 | 09/10/2025 | nan | nan | 0 | TK_NotStart | 222308392 | 10 | 222308392_10
PROD116860 | TT_Task | Vehicle 018 - Versand zum Kunde | 10/10/2025 | 14/10/2025 | nan | nan | 0 | TK_NotStart | 222308392 | 4 | 222308392_4
PROD116780 | TT_Task | Vehicle 018 - Kunden IBS ; Testphase | 15/10/2025 | 08/12/2025 | nan | nan | 0 | TK_NotStart | 222308392 | 11 | 222308392_11
PROD116800 | TT_Task | Vehicle 018 - Trial Operation | 09/12/2025 | 02/03/2026 | nan | nan | 0 | TK_NotStart | 222308392 | 15 | 222308392_15
PROD116810 | TT_Task | Vehicle 018 - Abnahme durch BVG | 03/03/2026 | 03/03/2026 | nan | nan | 0 | TK_NotStart | 222308392 | 6 | 222308392_6
PROD116910 | TT_Task | Vehicle 019 - Rohbau | 05/06/2025 | 05/06/2025 | nan | nan | 0 | TK_NotStart | 222308392 | 12 | 222308392_12
PROD116920 | TT_Task | Vehicle 019 - Oberflache | 05/06/2025 | 05/06/2025 | nan | nan | 0 | TK_NotStart | 222308392 | 13 | 222308392_13
PROD116930 | TT_Task | Vehicle 019 - Ausbau II | 05/06/2025 | 08/08/2025 | nan | nan | 0 | TK_NotStart | 222308392 | 14 | 222308392_14
PROD116940 | TT_Task | Vehicle 019 - Statistic ; Dynamic IBS | 11/08/2025 | 05/11/2025 | nan | nan | 0 | TK_NotStart | 222308392 | 10 | 222308392_10
PROD116950 | TT_Task | Vehicle 019 - Versand zum Kunde | 06/11/2025 | 10/11/2025 | nan | nan | 0 | TK_NotStart | 222308392 | 4 | 222308392_4
PROD116870 | TT_Task | Vehicle 019 - Kunden IBS ; Testphase | 11/11/2025 | 02/01/2026 | nan | nan | 0 | TK_NotStart | 222308392 | 11 | 222308392_11
PROD116890 | TT_Task | Vehicle 019 - Trial Operation | 05/01/2026 | 27/03/2026 | nan | nan | 0 | TK_NotStart | 222308392 | 15 | 222308392_15
PROD116900 | TT_Task | Vehicle 019 - Abnahme durch BVG | 30/03/2026 | 30/03/2026 | nan | nan | 0 | TK_NotStart | 222308392 | 6 | 222308392_6
PROD117000 | TT_Task | Vehicle 020 - Rohbau | 10/07/2025 | 10/07/2025 | nan | nan | 0 | TK_NotStart | 222308392 | 12 | 222308392_12
PROD117010 | TT_Task | Vehicle 020 - Oberflache | 10/07/2025 | 10/07/2025 | nan | nan | 0 | TK_NotStart | 222308392 | 13 | 222308392_13
PROD117020 | TT_Task | Vehicle 020 - Ausbau II | 10/07/2025 | 05/09/2025 | nan | nan | 0 | TK_NotStart | 222308392 | 14 | 222308392_14
PROD117030 | TT_Task | Vehicle 020 - Statistic ; Dynamic IBS | 08/09/2025 | 02/12/2025 | nan | nan | 0 | TK_NotStart | 222308392 | 10 | 222308392_10
PROD117040 | TT_Task | Vehicle 020 - Versand zum Kunde | 03/12/2025 | 05/12/2025 | nan | nan | 0 | TK_NotStart | 222308392 | 4 | 222308392_4
PROD116960 | TT_Task | Vehicle 020 - Kunden IBS ; Testphase | 08/12/2025 | 29/01/2026 | nan | nan | 0 | TK_NotStart | 222308392 | 11 | 222308392_11
PROD116980 | TT_Task | Vehicle 020 - Trial Operation | 30/01/2026 | 23/04/2026 | nan | nan | 0 | TK_NotStart | 222308392 | 15 | 222308392_15
PROD116990 | TT_Task | Vehicle 020 - Abnahme durch BVG | 24/04/2026 | 24/04/2026 | nan | nan | 0 | TK_NotStart | 222308392 | 6 | 222308392_6
MET-WS1.1-1040 | TT_Task | WT1 FO1 WS1 - Tooling Definition, Fabrication, Installation | 04/07/2022 | 07/10/2022 | nan | nan | 0 | TK_NotStart | 222308392 | 16 | 222308392_16
MET-WS1.1-1020 | TT_Task | WT1 FO1 WS1 - MBOM Implementation, Logistics Preparation, C Parts Lead Time | 04/07/2022 | 07/10/2022 | nan | nan | 0 | TK_NotStart | 222308392 | 17 | 222308392_17
A236470 | TT_Task | Project Kick-off | 15/12/2020 | 28/12/2020 | 15/12/2020 | 11/01/2021 | 0 | TK_Complete | 222308392 | 18 | 222308392_18
A236480 | TT_Task | Bid to Project Handover | 12/01/2021 | 26/02/2021 | 12/01/2021 | 26/02/2021 | 0 | TK_Complete | 222308392 | 19 | 222308392_19
A236490 | TT_Task | Validation of Bid Assumptions ; Project Feasibility | 12/01/2021 | 26/02/2021 | 12/01/2021 | 26/02/2021 | 0 | TK_Complete | 222308392 | 20 | 222308392_20
A236500 | TT_Task | Requirements Freeze and Baselining | 12/01/2021 | 26/02/2021 | 12/01/2021 | 26/02/2021 | 0 | TK_Complete | 222308392 | 21 | 222308392_21
A236510 | TT_Task | GR1 Self-Assessment | 01/03/2021 | 05/03/2021 | 01/03/2021 | 05/03/2021 | 0 | TK_Complete | 222308392 | 22 | 222308392_22
A236520 | TT_Task | Collect Bid SMB Documents | 15/12/2020 | 28/12/2020 | 15/12/2020 | 11/01/2021 | 0 | TK_Complete | 222308392 | 23 | 222308392_23
A236530 | TT_Task | Update of Bid Project Schedule | 12/01/2021 | 18/01/2021 | 12/01/2021 | 18/01/2021 | 0 | TK_Complete | 222308392 | 20 | 222308392_20
A236540 | TT_Task | Planning Kick Off Meeting | 19/01/2021 | 25/01/2021 | 19/01/2021 | 25/01/2021 | 0 | TK_Complete | 222308392 | 24 | 222308392_24
A236550 | TT_Task | Preparation of Draft Project Functional Schedules | 26/01/2021 | 22/02/2021 | 26/01/2021 | 22/02/2021 | 0 | TK_Complete | 222308392 | 25 | 222308392_25
A236560 | TT_Task | Integration of Draft Project Functional Schedules | 23/02/2021 | 01/03/2021 | 23/02/2021 | 01/03/2021 | 0 | TK_Complete | 222308392 | 25 | 222308392_25
A236570 | TT_Task | Planning ; Risks Review Meeting | 02/03/2021 | 08/03/2021 | 02/03/2021 | 08/03/2021 | 0 | TK_Complete | 222308392 | 24 | 222308392_24
A236580 | TT_Task | Preparation of Final Project Functional Schedules | 09/03/2021 | 22/03/2021 | 09/03/2021 | 22/03/2021 | 0 | TK_Complete | 222308392 | 25 | 222308392_25
A236590 | TT_Task | Integration of Final Project Functional Schedules | 23/03/2021 | 29/03/2021 | 23/03/2021 | 29/03/2021 | 0 | TK_Complete | 222308392 | 25 | 222308392_25
A236600 | TT_Task | Harmonization Meeting | 30/03/2021 | 05/04/2021 | 30/03/2021 | 06/04/2021 | 0 | TK_Complete | 222308392 | 26 | 222308392_26
A236620 | TT_Task | GR2 Self-Assessment | 07/04/2021 | 13/04/2021 | 07/04/2021 | 13/04/2021 | 0 | TK_Complete | 222308392 | 22 | 222308392_22
A236630 | TT_Task | GR3 Self-Assessment | 09/09/2021 | 22/09/2021 | 09/09/2021 | 22/09/2021 | 0 | TK_Complete | 222308392 | 22 | 222308392_22
A236640 | TT_Task | GR4 Self-Assessment | 25/05/2022 | 16/06/2022 | nan | nan | 0 | TK_NotStart | 222308392 | 22 | 222308392_22
A236650 | TT_Task | GR5 Self-Assessment | 09/09/2022 | 03/10/2022 | nan | nan | 0 | TK_NotStart | 222308392 | 22 | 222308392_22
A236660 | TT_Task | GR6 Self-Assessment | 10/03/2023 | 16/03/2023 | nan | nan | 0 | TK_NotStart | 222308392 | 22 | 222308392_22
A236670 | TT_Task | GR7 Self-Assessment | 31/07/2024 | 06/08/2024 | nan | nan | 0 | TK_NotStart | 222308392 | 22 | 222308392_22
A236680 | TT_Task | GR8 Self-Assessment | 18/07/2028 | 24/07/2028 | nan | nan | 0 | TK_NotStart | 222308392 | 22 | 222308392_22
A236690 | TT_Task | GR9 Self-Assessment | 19/07/2032 | 23/07/2032 | nan | nan | 0 | TK_NotStart | 222308392 | 22 | 222308392_22
25863-204050 | TT_Task | Application for Payment 01 - First Advance Payment (100% of Non-Recurring Costs) | 15/12/2020 | 28/01/2021 | 15/12/2020 | 28/01/2021 | 0 | TK_Complete | 222308392 | 27 | 222308392_27
25863-204060 | TT_Task | Application for Payment 02.1 - Advance Payment for Vehicle Deliveries in 2023 (30%) | 01/01/2021 | 28/01/2021 | 01/01/2021 | 28/01/2021 | 0 | TK_Complete | 222308392 | 28 | 222308392_28
A16510 | TT_Task | Vehicle 001 - Static Tests | 10/03/2023 | 15/05/2023 | nan | nan | 0 | TK_NotStart | 222308392 | 29 | 222308392_29
A16530 | TT_Task | Vehicle 001 - Finishing ; Factory Acceptance (G?tepr?fung 1) | 06/07/2023 | 26/07/2023 | nan | nan | 0 | TK_NotStart | 222308392 | 30 | 222308392_30
A16540 | TT_Task | Vehicle 001 - Transport to Berlin | 31/07/2023 | 03/08/2023 | nan | nan | 0 | TK_NotStart | 222308392 | 31 | 222308392_31
A16550 | TT_Task | Vehicle 001 - Depot Infrastructure Tests | 15/08/2023 | 21/08/2023 | nan | nan | 0 | TK_NotStart | 222308392 | 32 | 222308392_32
A16560 | TT_Task | Vehicle 001 - Vehicle Type Tests | 26/09/2023 | 17/11/2023 | nan | nan | 0 | TK_NotStart | 222308392 | 33 | 222308392_33
A16570 | TT_Task | Vehicle 001 - Customer Tests (G?tepr?fung 2 incl. 6 hours (100km) test run) | 20/11/2023 | 24/11/2023 | nan | nan | 0 | TK_NotStart | 222308392 | 34 | 222308392_34
A16580 | TT_Task | Vehicle 001 - Customer Tests (test phase without passengers) | 27/11/2023 | 15/12/2023 | nan | nan | 0 | TK_NotStart | 222308392 | 35 | 222308392_35
A16610 | TT_Task | Vehicle 001 - Preparation of Final Reports/Certificates | 18/12/2023 | 18/01/2024 | nan | nan | 0 | TK_NotStart | 222308392 | 36 | 222308392_36
A236920 | TT_Task | Vehicle 001 - Dynamic Tests | 16/05/2023 | 05/07/2023 | nan | nan | 0 | TK_NotStart | 222308392 | 29 | 222308392_29
A236960 | TT_Task | Vehicle 001 - Site Commissioning Tests | 22/08/2023 | 25/09/2023 | nan | nan | 0 | TK_NotStart | 222308392 | 32 | 222308392_32
A236970 | TT_Task | Driver for the Critical Path Calculation for the First Vehicle | 03/09/2024 | 02/11/2043 | nan | nan | 0 | TK_NotStart | 222308392 | 37 | 222308392_37
PROD117170 | TT_Task | Vehicle 001 - Testphase gem. 15.3 | 27/11/2023 | 15/12/2023 | nan | nan | 0 | TK_NotStart | 222308392 | 5 | 222308392_5
PROD117240 | TT_Task | Vehicle 003 - Trial Operation gem. 16.2 | 14/05/2024 | 05/08/2024 | nan | nan | 0 | TK_NotStart | 222308392 | 5 | 222308392_5
PROD117250 | TT_Task | Vehicle 003 - Abnahme durch BVG | 14/10/2024 | 14/10/2024 | nan | nan | 0 | TK_NotStart | 222308392 | 6 | 222308392_6
A236990 | TT_Task | Vehicle 001 - Evaluation Maintenance Tasks | 11/03/2024 | 30/08/2024 | nan | nan | 0 | TK_NotStart | 222308392 | 38 | 222308392_38
A237010 | TT_Task | Vehicle 003 - Static Tests | 27/06/2023 | 04/09/2023 | nan | nan | 0 | TK_NotStart | 222308392 | 29 | 222308392_29
A237030 | TT_Task | Vehicle 003 - Dynamic Tests | 05/09/2023 | 11/10/2023 | nan | nan | 0 | TK_NotStart | 222308392 | 29 | 222308392_29
A237040 | TT_Task | Vehicle 003 - Finishing ; Factory Acceptance (G?tepr?fung 1) | 10/01/2024 | 30/01/2024 | nan | nan | 0 | TK_NotStart | 222308392 | 30 | 222308392_30
A237060 | TT_Task | Vehicle 003 - Check after Unloading ; Site Commissioning Tests | 06/02/2024 | 26/02/2024 | nan | nan | 0 | TK_NotStart | 222308392 | 32 | 222308392_32
A237070 | TT_Task | Vehicle 003 - Customer Tests (G?tepr?fung 2 incl. 6 hours (100km) test run) | 07/05/2024 | 13/05/2024 | nan | nan | 0 | TK_NotStart | 222308392 | 34 | 222308392_34
A237080 | TT_Task | Vehicle 003 - Customer Tests (test phase without passengers) | 14/05/2024 | 04/06/2024 | nan | nan | 0 | TK_NotStart | 222308392 | 35 | 222308392_35
A237090 | TT_Task | Vehicle 003 - Preparation of Final Reports/Certificates | 05/06/2024 | 16/07/2024 | nan | nan | 0 | TK_NotStart | 222308392 | 36 | 222308392_36
A237110 | TT_Task | Vehicle 003 - Evaluation Maintenance Tasks | 06/08/2024 | 11/10/2024 | nan | nan | 0 | TK_NotStart | 222308392 | 38 | 222308392_38
A237120 | TT_Task | Vehicle 002 - Evaluation Maintenance Tasks | 21/02/2024 | 14/08/2024 | nan | nan | 96 | TK_NotStart | 222308392 | 38 | 222308392_38
A237130 | TT_Task | Vehicle 004 - Evaluation Maintenance Tasks | 22/08/2024 | 14/10/2024 | nan | nan | 0 | TK_NotStart | 222308392 | 38 | 222308392_38
A237140 | TT_Task | Vehicle 005 - Evaluation Maintenance Tasks | 23/04/2024 | 02/09/2024 | nan | nan | 0 | TK_NotStart | 222308392 | 38 | 222308392_38
A237150 | TT_Task | Vehicle 006 - Evaluation Maintenance Tasks | 30/07/2024 | 25/09/2024 | nan | nan | 0 | TK_NotStart | 222308392 | 38 | 222308392_38
25863-204460 | TT_Task | Application for Payment 02.2 - Advance Payment for Vehicle Deliveries in 2024 (30%) | 01/01/2022 | 31/01/2022 | 13/12/2021 | 24/12/2021 | 0 | TK_Complete | 222308392 | 28 | 222308392_28
25863-204470 | TT_Task | Application for Payment 02.3 - Advance Payment for Vehicle Deliveries in 2025 (30%) | 01/01/2023 | 31/01/2023 | nan | nan | 0 | TK_NotStart | 222308392 | 28 | 222308392_28
25863-204471 | TT_Task | Application for Payment 03.001 - TAB Acceptance Vehicle 001 (30%) | 05/01/2024 | 04/02/2024 | nan | nan | 0 | TK_NotStart | 222308392 | 39 | 222308392_39
25863-204472 | TT_Task | Application for Payment 03.002 - TAB Acceptance Vehicle 002 (30%) | 24/06/2024 | 24/07/2024 | nan | nan | 0 | TK_NotStart | 222308392 | 39 | 222308392_39
25863-204473 | TT_Task | Application for Payment 03.003 - TAB Acceptance Vehicle 003 (30%) | 09/01/2024 | 08/02/2024 | nan | nan | 0 | TK_NotStart | 222308392 | 39 | 222308392_39
25863-204474 | TT_Task | Application for Payment 03.004 - TAB Acceptance Vehicle 004 (30%) | 10/07/2024 | 09/08/2024 | nan | nan | 0 | TK_NotStart | 222308392 | 39 | 222308392_39
25863-204475 | TT_Task | Application for Payment 03.005 - TAB Acceptance Vehicle 005 (30%) | 11/03/2024 | 10/04/2024 | nan | nan | 0 | TK_NotStart | 222308392 | 39 | 222308392_39
25863-204476 | TT_Task | Application for Payment 03.006 - TAB Acceptance Vehicle 006 (30%) | 17/06/2024 | 17/07/2024 | nan | nan | 0 | TK_NotStart | 222308392 | 39 | 222308392_39
25863-204477 | TT_Task | Application for Payment 03.007 - TAB Acceptance Vehicle 007 (30%) | 25/02/2025 | 27/03/2025 | nan | nan | 0 | TK_NotStart | 222308392 | 39 | 222308392_39
25863-204478 | TT_Task | Application for Payment 03.008 - TAB Acceptance Vehicle 008 (30%) | 28/04/2025 | 28/05/2025 | nan | nan | 0 | TK_NotStart | 222308392 | 39 | 222308392_39
25863-204479 | TT_Task | Application for Payment 03.009 - TAB Acceptance Vehicle 009 (30%) | 12/05/2025 | 11/06/2025 | nan | nan | 0 | TK_NotStart | 222308392 | 39 | 222308392_39
25863-204480 | TT_Task | Application for Payment 03.010 - TAB Acceptance Vehicle 010 (30%) | 05/06/2025 | 05/07/2025 | nan | nan | 0 | TK_NotStart | 222308392 | 39 | 222308392_39
25863-204481 | TT_Task | Application for Payment 03.011 - TAB Acceptance Vehicle 011 (30%) | 01/07/2025 | 31/07/2025 | nan | nan | 0 | TK_NotStart | 222308392 | 39 | 222308392_39
25863-204482 | TT_Task | Application for Payment 03.012 - TAB Acceptance Vehicle 012 (30%) | 25/07/2025 | 24/08/2025 | nan | nan | 0 | TK_NotStart | 222308392 | 39 | 222308392_39
25863-204483 | TT_Task | Application for Payment 03.013 - TAB Acceptance Vehicle 013 (30%) | 19/08/2025 | 18/09/2025 | nan | nan | 0 | TK_NotStart | 222308392 | 39 | 222308392_39
25863-204484 | TT_Task | Application for Payment 03.014 - TAB Acceptance Vehicle 014 (30%) | 24/09/2025 | 24/10/2025 | nan | nan | 0 | TK_NotStart | 222308392 | 39 | 222308392_39
25863-204485 | TT_Task | Application for Payment 03.015 - TAB Acceptance Vehicle 015 (30%) | 21/10/2025 | 20/11/2025 | nan | nan | 0 | TK_NotStart | 222308392 | 39 | 222308392_39
25863-204486 | TT_Task | Application for Payment 03.016 - TAB Acceptance Vehicle 016 (30%) | 27/11/2025 | 27/12/2025 | nan | nan | 0 | TK_NotStart | 222308392 | 39 | 222308392_39
25863-204487 | TT_Task | Application for Payment 03.017 - TAB Acceptance Vehicle 017 (30%) | 23/12/2025 | 22/01/2026 | nan | nan | 0 | TK_NotStart | 222308392 | 39 | 222308392_39
25863-204488 | TT_Task | Application for Payment 03.018 - TAB Acceptance Vehicle 018 (30%) | 19/01/2026 | 18/02/2026 | nan | nan | 0 | TK_NotStart | 222308392 | 39 | 222308392_39
25863-204489 | TT_Task | Application for Payment 03.019 - TAB Acceptance Vehicle 019 (30%) | 13/02/2026 | 15/03/2026 | nan | nan | 0 | TK_NotStart | 222308392 | 39 | 222308392_39
25863-204490 | TT_Task | Application for Payment 03.020 - TAB Acceptance Vehicle 020 (30%) | 12/03/2026 | 11/04/2026 | nan | nan | 0 | TK_NotStart | 222308392 | 39 | 222308392_39
25863-204491 | TT_Task | Application for Payment 04.001 - Final Acceptance Vehicle 001 (40%) | 02/09/2024 | 02/10/2024 | nan | nan | 0 | TK_NotStart | 222308392 | 40 | 222308392_40
25863-204492 | TT_Task | Application for Payment 04.002 - Final Acceptance Vehicle 002 (40%) | 14/10/2024 | 13/11/2024 | nan | nan | 0 | TK_NotStart | 222308392 | 40 | 222308392_40
25863-204493 | TT_Task | Application for Payment 04.003 - Final Acceptance Vehicle 003 (40%) | 02/09/2024 | 02/10/2024 | nan | nan | 0 | TK_NotStart | 222308392 | 40 | 222308392_40
25863-204494 | TT_Task | Application for Payment 04.004 - Final Acceptance Vehicle 004 (40%) | 15/10/2024 | 14/11/2024 | nan | nan | 0 | TK_NotStart | 222308392 | 40 | 222308392_40
25863-204495 | TT_Task | Application for Payment 04.005 - Final Acceptance Vehicle 005 (40%) | 03/09/2024 | 03/10/2024 | nan | nan | 0 | TK_NotStart | 222308392 | 40 | 222308392_40
25863-204496 | TT_Task | Application for Payment 04.006 - Final Acceptance Vehicle 006 (40%) | 26/09/2024 | 26/10/2024 | nan | nan | 0 | TK_NotStart | 222308392 | 40 | 222308392_40
25863-204497 | TT_Task | Application for Payment 04.007 - Final Acceptance Vehicle 007 (40%) | 09/04/2025 | 09/05/2025 | nan | nan | 0 | TK_NotStart | 222308392 | 40 | 222308392_40
25863-204498 | TT_Task | Application for Payment 04.008 - Final Acceptance Vehicle 008 (40%) | 10/06/2025 | 10/07/2025 | nan | nan | 0 | TK_NotStart | 222308392 | 40 | 222308392_40
25863-204499 | TT_Task | Application for Payment 04.009 - Final Acceptance Vehicle 009 (40%) | 24/06/2025 | 24/07/2025 | nan | nan | 0 | TK_NotStart | 222308392 | 40 | 222308392_40
25863-204500 | TT_Task | Application for Payment 04.010 - Final Acceptance Vehicle 010 (40%) | 18/07/2025 | 17/08/2025 | nan | nan | 0 | TK_NotStart | 222308392 | 40 | 222308392_40
25863-204501 | TT_Task | Application for Payment 04.011 - Final Acceptance Vehicle 011 (40%) | 13/08/2025 | 12/09/2025 | nan | nan | 0 | TK_NotStart | 222308392 | 40 | 222308392_40
25863-204502 | TT_Task | Application for Payment 04.012 - Final Acceptance Vehicle 012 (40%) | 08/09/2025 | 08/10/2025 | nan | nan | 0 | TK_NotStart | 222308392 | 40 | 222308392_40
25863-204503 | TT_Task | Application for Payment 04.013 - Final Acceptance Vehicle 013 (40%) | 24/09/2025 | 24/10/2025 | nan | nan | 0 | TK_NotStart | 222308392 | 40 | 222308392_40
25863-204504 | TT_Task | Application for Payment 04.014 - Final Acceptance Vehicle 014 (40%) | 30/10/2025 | 29/11/2025 | nan | nan | 0 | TK_NotStart | 222308392 | 40 | 222308392_40
25863-204505 | TT_Task | Application for Payment 04.015 - Final Acceptance Vehicle 015 (40%) | 03/12/2025 | 02/01/2026 | nan | nan | 0 | TK_NotStart | 222308392 | 40 | 222308392_40
25863-204506 | TT_Task | Application for Payment 04.016 - Final Acceptance Vehicle 016 (40%) | 09/01/2026 | 08/02/2026 | nan | nan | 0 | TK_NotStart | 222308392 | 40 | 222308392_40
25863-204507 | TT_Task | Application for Payment 04.017 - Final Acceptance Vehicle 017 (40%) | 04/02/2026 | 06/03/2026 | nan | nan | 0 | TK_NotStart | 222308392 | 40 | 222308392_40
25863-204508 | TT_Task | Application for Payment 04.018 - Final Acceptance Vehicle 018 (40%) | 03/03/2026 | 02/04/2026 | nan | nan | 0 | TK_NotStart | 222308392 | 40 | 222308392_40
25863-204509 | TT_Task | Application for Payment 04.019 - Final Acceptance Vehicle 019 (40%) | 30/03/2026 | 29/04/2026 | nan | nan | 0 | TK_NotStart | 222308392 | 40 | 222308392_40
25863-204510 | TT_Task | Application for Payment 04.020 - Final Acceptance Vehicle 020 (40%) | 24/04/2026 | 24/05/2026 | nan | nan | 0 | TK_NotStart | 222308392 | 40 | 222308392_40
A237160 | TT_Task | Vehicle 001 - TAB (BOStrab) Approval Period | 19/01/2024 | 01/02/2024 | nan | nan | 0 | TK_NotStart | 222308392 | 41 | 222308392_41
A237170 | TT_Task | Vehicle 003 - TAB (BOStrab) Approval Period | 17/07/2024 | 30/07/2024 | nan | nan | 0 | TK_NotStart | 222308392 | 41 | 222308392_41
PROD117420 | TT_Task | Vehicle 002 - Routine Acceptance Process | 01/02/2024 | 15/02/2024 | nan | nan | 0 | TK_NotStart | 222308392 | 42 | 222308392_42
PROD117440 | TT_Task | Vehicle 004 - Routine Acceptance Process | 22/08/2024 | 04/09/2024 | nan | nan | 0 | TK_NotStart | 222308392 | 42 | 222308392_42
PROD117460 | TT_Task | Vehicle 005 - Routine Acceptance Process | 18/01/2024 | 01/02/2024 | nan | nan | 0 | TK_NotStart | 222308392 | 42 | 222308392_42
PROD117480 | TT_Task | Vehicle 006 - Routine Acceptance Process | 23/04/2024 | 06/05/2024 | nan | nan | 0 | TK_NotStart | 222308392 | 42 | 222308392_42
PROD117500 | TT_Task | Vehicle 007 - Routine Acceptance Process | 01/01/2025 | 14/01/2025 | nan | nan | 0 | TK_NotStart | 222308392 | 42 | 222308392_42
PROD117520 | TT_Task | Vehicle 008 - Routine Acceptance Process | 04/03/2025 | 17/03/2025 | nan | nan | 0 | TK_NotStart | 222308392 | 42 | 222308392_42
PROD117540 | TT_Task | Vehicle 009 - Routine Acceptance Process | 18/03/2025 | 31/03/2025 | nan | nan | 0 | TK_NotStart | 222308392 | 42 | 222308392_42
PROD117560 | TT_Task | Vehicle 010 - Routine Acceptance Process | 11/04/2025 | 24/04/2025 | nan | nan | 0 | TK_NotStart | 222308392 | 42 | 222308392_42
PROD117580 | TT_Task | Vehicle 011 - Routine Acceptance Process | 07/05/2025 | 20/05/2025 | nan | nan | 0 | TK_NotStart | 222308392 | 42 | 222308392_42
PROD117600 | TT_Task | Vehicle 012 - Routine Acceptance Process | 02/06/2025 | 13/06/2025 | nan | nan | 0 | TK_NotStart | 222308392 | 42 | 222308392_42
PROD117620 | TT_Task | Vehicle 013 - Routine Acceptance Process | 25/06/2025 | 08/07/2025 | nan | nan | 0 | TK_NotStart | 222308392 | 42 | 222308392_42
PROD117640 | TT_Task | Vehicle 014 - Routine Acceptance Process | 31/07/2025 | 13/08/2025 | nan | nan | 0 | TK_NotStart | 222308392 | 42 | 222308392_42
PROD117660 | TT_Task | Vehicle 015 - Routine Acceptance Process | 27/08/2025 | 09/09/2025 | nan | nan | 0 | TK_NotStart | 222308392 | 42 | 222308392_42
PROD117680 | TT_Task | Vehicle 016 - Routine Acceptance Process | 03/10/2025 | 16/10/2025 | nan | nan | 0 | TK_NotStart | 222308392 | 42 | 222308392_42
PROD117700 | TT_Task | Vehicle 017 - Routine Acceptance Process | 29/10/2025 | 11/11/2025 | nan | nan | 0 | TK_NotStart | 222308392 | 42 | 222308392_42
PROD117720 | TT_Task | Vehicle 018 - Routine Acceptance Process | 25/11/2025 | 08/12/2025 | nan | nan | 0 | TK_NotStart | 222308392 | 42 | 222308392_42
PROD117740 | TT_Task | Vehicle 019 - Routine Acceptance Process | 22/12/2025 | 02/01/2026 | nan | nan | 0 | TK_NotStart | 222308392 | 42 | 222308392_42
PROD117760 | TT_Task | Vehicle 020 - Routine Acceptance Process | 16/01/2026 | 29/01/2026 | nan | nan | 0 | TK_NotStart | 222308392 | 42 | 222308392_42
A237180 | TT_Task | GR1 Challenge Reviews | 23/03/2021 | 23/03/2021 | 23/03/2021 | 23/03/2021 | 0 | TK_Complete | 222308392 | 43 | 222308392_43
A237190 | TT_Task | GR2 Challenge Reviews | 28/04/2021 | 28/04/2021 | 28/04/2021 | 28/04/2021 | 0 | TK_Complete | 222308392 | 43 | 222308392_43
A237200 | TT_Task | GR3 Challenge Reviews | 23/09/2021 | 06/10/2021 | 23/09/2021 | 06/10/2021 | 0 | TK_Complete | 222308392 | 43 | 222308392_43
A237210 | TT_Task | GR4 Challenge Reviews | 17/06/2022 | 23/06/2022 | nan | nan | 0 | TK_NotStart | 222308392 | 43 | 222308392_43
A237220 | TT_Task | GR5 Challenge Reviews | 04/10/2022 | 10/10/2022 | nan | nan | 0 | TK_NotStart | 222308392 | 43 | 222308392_43
A237230 | TT_Task | GR6 Challenge Reviews | 17/03/2023 | 30/03/2023 | nan | nan | 0 | TK_NotStart | 222308392 | 43 | 222308392_43
A237240 | TT_Task | GR7 Challenge Reviews | 07/08/2024 | 20/08/2024 | nan | nan | 0 | TK_NotStart | 222308392 | 43 | 222308392_43
A237250 | TT_Task | GR8 Challenge Reviews | 25/07/2028 | 07/08/2028 | nan | nan | 0 | TK_NotStart | 222308392 | 43 | 222308392_43
A237260 | TT_Task | GR9 Challenge Reviews | 26/07/2032 | 06/08/2032 | nan | nan | 0 | TK_NotStart | 222308392 | 43 | 222308392_43
A237270 | TT_Task | Vehicle 001 - TCMS Inputs Integration into the Final Reports | 18/12/2023 | 29/12/2023 | nan | nan | 112 | TK_NotStart | 222308392 | 44 | 222308392_44
A237280 | TT_Task | Vehicle 003 - TCMS Inputs Integration into the Final Reports | 05/06/2024 | 18/06/2024 | nan | nan | 160 | TK_NotStart | 222308392 | 44 | 222308392_44
A237290 | TT_Task | GR1 Closing of Open Points from the Self-Assessment | 08/03/2021 | 22/03/2021 | 08/03/2021 | 22/03/2021 | 0 | TK_Complete | 222308392 | 45 | 222308392_45
A237300 | TT_Task | GR2 Closing of Open Points from the Self-Assessment | 14/04/2021 | 27/04/2021 | 14/04/2021 | 27/04/2021 | 0 | TK_Complete | 222308392 | 45 | 222308392_45
PROD117780 | TT_Task | Vehicle 001 - Vormontage UG WT1 | 21/06/2022 | 25/07/2022 | nan | nan | 0 | TK_NotStart | 222308392 | 46 | 222308392_46
PROD117790 | TT_Task | Vehicle 001 - Vormontage UG WT9 | 25/05/2022 | 01/07/2022 | nan | nan | 0 | TK_NotStart | 222308392 | 46 | 222308392_46
PROD117800 | TT_Task | Vehicle 001 - Vormontage UG WT2 | 01/04/2022 | 05/05/2022 | nan | nan | 0 | TK_NotStart | 222308392 | 46 | 222308392_46
PROD117810 | TT_Task | Vehicle 001 - Montage UG WT1 | 26/07/2022 | 30/09/2022 | nan | nan | 0 | TK_NotStart | 222308392 | 47 | 222308392_47
PROD117820 | TT_Task | Vehicle 001 - Montage UG WT9 | 04/07/2022 | 08/09/2022 | nan | nan | 0 | TK_NotStart | 222308392 | 47 | 222308392_47
PROD117830 | TT_Task | Vehicle 001 - Montage UG WT2 | 08/06/2022 | 29/06/2022 | nan | nan | 0 | TK_NotStart | 222308392 | 47 | 222308392_47
PROD117840 | TT_Task | Vehicle 001 - Seitenwandgerippe WT1 | 22/08/2022 | 30/09/2022 | nan | nan | 42095 | TK_NotStart | 222308392 | 48 | 222308392_48
PROD117850 | TT_Task | Vehicle 001 - Seitenwandgerippe WT9 | 21/07/2022 | 08/09/2022 | nan | nan | 42223 | TK_NotStart | 222308392 | 48 | 222308392_48
PROD117860 | TT_Task | Vehicle 001 - Seitenwandgerippe WT2 | 23/05/2022 | 29/06/2022 | nan | nan | 42471 | TK_NotStart | 222308392 | 48 | 222308392_48
PROD117870 | TT_Task | Vehicle 001 - Rohbau Wagenkasten WT1 | 04/10/2022 | 01/11/2022 | nan | nan | 0 | TK_NotStart | 222308392 | 49 | 222308392_49
PROD117880 | TT_Task | Vehicle 001 - Rohbau Wagenkasten WT9 | 09/09/2022 | 07/10/2022 | nan | nan | 0 | TK_NotStart | 222308392 | 49 | 222308392_49
PROD117890 | TT_Task | Vehicle 001 - Rohbau Wagenkasten WT2 | 21/07/2022 | 29/08/2022 | nan | nan | 0 | TK_NotStart | 222308392 | 49 | 222308392_49
PROD117900 | TT_Task | Vehicle 001 - Rohbau Abnahme WT1 | 02/11/2022 | 15/11/2022 | nan | nan | 0 | TK_NotStart | 222308392 | 49 | 222308392_49
PROD117910 | TT_Task | Vehicle 001 - Rohbau Abnahme WT9 | 10/10/2022 | 21/10/2022 | nan | nan | 0 | TK_NotStart | 222308392 | 49 | 222308392_49
PROD117920 | TT_Task | Vehicle 001 - Rohbau Abnahme WT2 | 30/08/2022 | 12/09/2022 | nan | nan | 0 | TK_NotStart | 222308392 | 49 | 222308392_49
PROD117930 | TT_Task | Vehicle 001 - Oberflache WT1 | 17/11/2022 | 12/12/2022 | nan | nan | 0 | TK_NotStart | 222308392 | 50 | 222308392_50
PROD117940 | TT_Task | Vehicle 001 - Oberflache WT9 | 24/10/2022 | 18/11/2022 | nan | nan | 0 | TK_NotStart | 222308392 | 50 | 222308392_50
PROD117950 | TT_Task | Vehicle 001 - Oberflache WT2 | 13/09/2022 | 12/12/2022 | nan | nan | 0 | TK_NotStart | 222308392 | 50 | 222308392_50
PROD118050 | TT_Task | Vehicle 001 - FO1 WS1 WT1 | 13/12/2022 | 22/12/2022 | nan | nan | 0 | TK_NotStart | 222308392 | 51 | 222308392_51
PROD118060 | TT_Task | Vehicle 001 - FO1 WS1 WT9 | 21/11/2022 | 30/11/2022 | nan | nan | 0 | TK_NotStart | 222308392 | 51 | 222308392_51
PROD118070 | TT_Task | Vehicle 001 - FO1 WS1 WT2 | 13/12/2022 | 22/12/2022 | nan | nan | 0 | TK_NotStart | 222308392 | 51 | 222308392_51
PROD118080 | TT_Task | Vehicle 001 - FO1 WS1 WT3 | 23/12/2022 | 10/01/2023 | nan | nan | 0 | TK_NotStart | 222308392 | 52 | 222308392_52
PROD118090 | TT_Task | Vehicle 001 - FO1 WS1 WT4 | 19/12/2022 | 04/01/2023 | nan | nan | 0 | TK_NotStart | 222308392 | 51 | 222308392_51
PROD118100 | TT_Task | Vehicle 001 - FO1 WS1 WT5 | 25/11/2022 | 06/12/2022 | nan | nan | 0 | TK_NotStart | 222308392 | 53 | 222308392_53
PROD118110 | TT_Task | Vehicle 001 - FO1 WS1 WT6 | 14/11/2022 | 24/11/2022 | nan | nan | 0 | TK_NotStart | 222308392 | 54 | 222308392_54
PROD118120 | TT_Task | Vehicle 001 - FO1 WS1 WT7 | 01/12/2022 | 12/12/2022 | nan | nan | 0 | TK_NotStart | 222308392 | 55 | 222308392_55
PROD118130 | TT_Task | Vehicle 001 - FO1 WS1 WT8 | 21/11/2022 | 30/11/2022 | nan | nan | 0 | TK_NotStart | 222308392 | 51 | 222308392_51
PROD118140 | TT_Task | Vehicle 001 - FO1 WS2 WT1 (inc WS3) | 23/12/2022 | 11/01/2023 | nan | nan | 0 | TK_NotStart | 222308392 | 52 | 222308392_52
PROD118150 | TT_Task | Vehicle 001 - FO1 WS2 WT9 (inc WS3) | 01/12/2022 | 13/12/2022 | nan | nan | 0 | TK_NotStart | 222308392 | 52 | 222308392_52
PROD118160 | TT_Task | Vehicle 001 - FO1 WS2 WT2 (inc WS3) | 23/12/2022 | 11/01/2023 | nan | nan | 0 | TK_NotStart | 222308392 | 52 | 222308392_52
PROD118170 | TT_Task | Vehicle 001 - FO1 WS2 WT3 (inc WS3) | 11/01/2023 | 23/01/2023 | nan | nan | 0 | TK_NotStart | 222308392 | 52 | 222308392_52
PROD118180 | TT_Task | Vehicle 001 - FO1 WS2 WT4 (inc WS3) | 05/01/2023 | 17/01/2023 | nan | nan | 0 | TK_NotStart | 222308392 | 52 | 222308392_52
PROD118190 | TT_Task | Vehicle 001 - FO1 WS2 WT5 (inc WS3) | 07/12/2022 | 19/12/2022 | nan | nan | 0 | TK_NotStart | 222308392 | 53 | 222308392_53
PROD118200 | TT_Task | Vehicle 001 - FO1 WS2 WT6 (inc WS3) | 25/11/2022 | 07/12/2022 | nan | nan | 0 | TK_NotStart | 222308392 | 52 | 222308392_52
PROD118210 | TT_Task | Vehicle 001 - FO1 WS2 WT7 (inc WS3) | 13/12/2022 | 23/12/2022 | nan | nan | 0 | TK_NotStart | 222308392 | 55 | 222308392_55
PROD118220 | TT_Task | Vehicle 001 - FO1 WS2 WT8 (inc WS3) | 01/12/2022 | 13/12/2022 | nan | nan | 0 | TK_NotStart | 222308392 | 52 | 222308392_52
PROD118230 | TT_Task | Vehicle 001 - FO2 WS1 WT1 | 12/01/2023 | 20/01/2023 | nan | nan | 0 | TK_NotStart | 222308392 | 51 | 222308392_51
PROD118240 | TT_Task | Vehicle 001 - FO2 WS1 WT9 | 14/12/2022 | 22/12/2022 | nan | nan | 0 | TK_NotStart | 222308392 | 51 | 222308392_51
PROD118250 | TT_Task | Vehicle 001 - FO2 WS1 WT2 | 12/01/2023 | 17/01/2023 | nan | nan | 0 | TK_NotStart | 222308392 | 51 | 222308392_51
PROD118260 | TT_Task | Vehicle 001 - FO2 WS1 WT3 | 24/01/2023 | 27/01/2023 | nan | nan | 0 | TK_NotStart | 222308392 | 52 | 222308392_52
PROD118270 | TT_Task | Vehicle 001 - FO2 WS1 WT4 | 18/01/2023 | 23/01/2023 | nan | nan | 0 | TK_NotStart | 222308392 | 51 | 222308392_51
PROD118280 | TT_Task | Vehicle 001 - FO2 WS1 WT5 | 20/12/2022 | 23/12/2022 | nan | nan | 0 | TK_NotStart | 222308392 | 53 | 222308392_53
PROD118290 | TT_Task | Vehicle 001 - FO2 WS1 WT6 | 08/12/2022 | 13/12/2022 | nan | nan | 0 | TK_NotStart | 222308392 | 54 | 222308392_54
PROD118300 | TT_Task | Vehicle 001 - FO2 WS1 WT7 | 02/01/2023 | 05/01/2023 | nan | nan | 0 | TK_NotStart | 222308392 | 55 | 222308392_55
PROD118310 | TT_Task | Vehicle 001 - FO2 WS1 WT8 | 14/12/2022 | 19/12/2022 | nan | nan | 0 | TK_NotStart | 222308392 | 51 | 222308392_51
PROD118320 | TT_Task | Vehicle 001 - FO2 WS2 WT1 | 23/01/2023 | 31/01/2023 | nan | nan | 0 | TK_NotStart | 222308392 | 51 | 222308392_51
PROD118330 | TT_Task | Vehicle 001 - FO2 WS2 WT9 | 23/12/2022 | 09/01/2023 | nan | nan | 0 | TK_NotStart | 222308392 | 51 | 222308392_51
PROD118340 | TT_Task | Vehicle 001 - FO2 WS2 WT2 | 18/01/2023 | 23/01/2023 | nan | nan | 0 | TK_NotStart | 222308392 | 51 | 222308392_51
PROD118350 | TT_Task | Vehicle 001 - FO2 WS2 WT3 | 30/01/2023 | 02/02/2023 | nan | nan | 0 | TK_NotStart | 222308392 | 52 | 222308392_52
PROD118360 | TT_Task | Vehicle 001 - FO2 WS2 WT4 | 24/01/2023 | 27/01/2023 | nan | nan | 0 | TK_NotStart | 222308392 | 51 | 222308392_51
PROD118370 | TT_Task | Vehicle 001 - FO2 WS2 WT5 | 02/01/2023 | 05/01/2023 | nan | nan | 0 | TK_NotStart | 222308392 | 53 | 222308392_53
PROD118380 | TT_Task | Vehicle 001 - FO2 WS2 WT6 | 14/12/2022 | 19/12/2022 | nan | nan | 0 | TK_NotStart | 222308392 | 54 | 222308392_54
PROD118390 | TT_Task | Vehicle 001 - FO2 WS2 WT7 | 06/01/2023 | 11/01/2023 | nan | nan | 0 | TK_NotStart | 222308392 | 55 | 222308392_55
PROD118400 | TT_Task | Vehicle 001 - FO2 WS2 WT8 | 20/12/2022 | 23/12/2022 | nan | nan | 0 | TK_NotStart | 222308392 | 51 | 222308392_51
PROD118410 | TT_Task | Vehicle 001 - FO2 WS3 WT1 | 01/02/2023 | 09/02/2023 | nan | nan | 0 | TK_NotStart | 222308392 | 52 | 222308392_52
PROD118420 | TT_Task | Vehicle 001 - FO2 WS3 WT9 | 10/01/2023 | 18/01/2023 | nan | nan | 0 | TK_NotStart | 222308392 | 51 | 222308392_51
PROD118430 | TT_Task | Vehicle 001 - FO2 WS3 WT2 | 24/01/2023 | 27/01/2023 | nan | nan | 0 | TK_NotStart | 222308392 | 52 | 222308392_52
PROD118440 | TT_Task | Vehicle 001 - FO2 WS3 WT3 | 03/02/2023 | 08/02/2023 | nan | nan | 0 | TK_NotStart | 222308392 | 52 | 222308392_52
PROD118450 | TT_Task | Vehicle 001 - FO2 WS3 WT4 | 30/01/2023 | 02/02/2023 | nan | nan | 0 | TK_NotStart | 222308392 | 51 | 222308392_51
PROD118460 | TT_Task | Vehicle 001 - FO2 WS3 WT5 | 06/01/2023 | 11/01/2023 | nan | nan | 0 | TK_NotStart | 222308392 | 53 | 222308392_53
PROD118470 | TT_Task | Vehicle 001 - FO2 WS3 WT6 | 20/12/2022 | 23/12/2022 | nan | nan | 0 | TK_NotStart | 222308392 | 54 | 222308392_54
PROD118480 | TT_Task | Vehicle 001 - FO2 WS3 WT7 | 12/01/2023 | 17/01/2023 | nan | nan | 0 | TK_NotStart | 222308392 | 55 | 222308392_55
PROD118490 | TT_Task | Vehicle 001 - FO2 WS3 WT8 | 02/01/2023 | 05/01/2023 | nan | nan | 0 | TK_NotStart | 222308392 | 51 | 222308392_51
PROD118500 | TT_Task | Vehicle 001 - FO2 WS4 WT1 | 10/02/2023 | 20/02/2023 | nan | nan | 0 | TK_NotStart | 222308392 | 51 | 222308392_51
PROD118510 | TT_Task | Vehicle 001 - FO2 WS4 WT9 | 19/01/2023 | 27/01/2023 | nan | nan | 0 | TK_NotStart | 222308392 | 51 | 222308392_51
PROD118520 | TT_Task | Vehicle 001 - FO2 WS4 WT2 | 30/01/2023 | 02/02/2023 | nan | nan | 0 | TK_NotStart | 222308392 | 51 | 222308392_51
PROD118530 | TT_Task | Vehicle 001 - FO2 WS4 WT3 | 09/02/2023 | 14/02/2023 | nan | nan | 0 | TK_NotStart | 222308392 | 51 | 222308392_51
PROD118540 | TT_Task | Vehicle 001 - FO2 WS4 WT4 | 03/02/2023 | 08/02/2023 | nan | nan | 0 | TK_NotStart | 222308392 | 51 | 222308392_51
PROD118550 | TT_Task | Vehicle 001 - FO2 WS4 WT5 | 12/01/2023 | 17/01/2023 | nan | nan | 0 | TK_NotStart | 222308392 | 53 | 222308392_53
PROD118560 | TT_Task | Vehicle 001 - FO2 WS4 WT6 | 02/01/2023 | 05/01/2023 | nan | nan | 0 | TK_NotStart | 222308392 | 54 | 222308392_54
PROD118570 | TT_Task | Vehicle 001 - FO2 WS4 WT7 | 18/01/2023 | 23/01/2023 | nan | nan | 0 | TK_NotStart | 222308392 | 55 | 222308392_55
PROD118580 | TT_Task | Vehicle 001 - FO2 WS4 WT8 | 06/01/2023 | 11/01/2023 | nan | nan | 0 | TK_NotStart | 222308392 | 51 | 222308392_51
PROD118590 | TT_Task | Vehicle 001 - FO2 WS5 WT1 | 21/02/2023 | 21/02/2023 | nan | nan | 0 | TK_NotStart | 222308392 | 53 | 222308392_53
PROD118600 | TT_Task | Vehicle 001 - FO2 WS5 WT9 | 30/01/2023 | 30/01/2023 | nan | nan | 0 | TK_NotStart | 222308392 | 53 | 222308392_53
PROD118610 | TT_Task | Vehicle 001 - FO2 WS5 WT2 | 03/02/2023 | 03/02/2023 | nan | nan | 0 | TK_NotStart | 222308392 | 53 | 222308392_53
PROD118620 | TT_Task | Vehicle 001 - FO2 WS5 WT3 | 15/02/2023 | 15/02/2023 | nan | nan | 0 | TK_NotStart | 222308392 | 53 | 222308392_53
PROD118630 | TT_Task | Vehicle 001 - FO2 WS5 WT4 | 09/02/2023 | 09/02/2023 | nan | nan | 0 | TK_NotStart | 222308392 | 53 | 222308392_53
PROD118640 | TT_Task | Vehicle 001 - FO2 WS5 WT5 | 18/01/2023 | 18/01/2023 | nan | nan | 0 | TK_NotStart | 222308392 | 53 | 222308392_53
PROD118650 | TT_Task | Vehicle 001 - FO2 WS5 WT6 | 06/01/2023 | 06/01/2023 | nan | nan | 0 | TK_NotStart | 222308392 | 53 | 222308392_53
PROD118660 | TT_Task | Vehicle 001 - FO2 WS5 WT7 | 24/01/2023 | 24/01/2023 | nan | nan | 0 | TK_NotStart | 222308392 | 55 | 222308392_55
PROD118670 | TT_Task | Vehicle 001 - FO2 WS5 WT8 | 12/01/2023 | 12/01/2023 | nan | nan | 0 | TK_NotStart | 222308392 | 53 | 222308392_53
PROD118680 | TT_Task | Vehicle 001 - FO2 WS6 WT1 (inc Modulprufung) | 21/02/2023 | 01/03/2023 | nan | nan | 0 | TK_NotStart | 222308392 | 54 | 222308392_54
PROD118690 | TT_Task | Vehicle 001 - FO2 WS6 WT9 (inc Modulprufung) | 30/01/2023 | 07/02/2023 | nan | nan | 0 | TK_NotStart | 222308392 | 54 | 222308392_54
PROD118700 | TT_Task | Vehicle 001 - FO2 WS6 WT2 (inc Modulprufung) | 03/02/2023 | 13/02/2023 | nan | nan | 0 | TK_NotStart | 222308392 | 54 | 222308392_54
PROD118710 | TT_Task | Vehicle 001 - FO2 WS6 WT3 (inc Modulprufung) | 15/02/2023 | 23/02/2023 | nan | nan | 0 | TK_NotStart | 222308392 | 54 | 222308392_54
PROD118720 | TT_Task | Vehicle 001 - FO2 WS6 WT4 (inc Modulprufung) | 09/02/2023 | 17/02/2023 | nan | nan | 0 | TK_NotStart | 222308392 | 54 | 222308392_54
PROD118730 | TT_Task | Vehicle 001 - FO2 WS6 WT5 (inc Modulprufung) | 18/01/2023 | 26/01/2023 | nan | nan | 0 | TK_NotStart | 222308392 | 54 | 222308392_54
PROD118740 | TT_Task | Vehicle 001 - FO2 WS6 WT6 (inc Modulprufung) | 06/01/2023 | 16/01/2023 | nan | nan | 0 | TK_NotStart | 222308392 | 54 | 222308392_54
PROD118750 | TT_Task | Vehicle 001 - FO2 WS6 WT7 (inc Modulprufung) | 24/01/2023 | 01/02/2023 | nan | nan | 0 | TK_NotStart | 222308392 | 54 | 222308392_54
PROD118760 | TT_Task | Vehicle 001 - FO2 WS6 WT8 (inc Modulprufung) | 12/01/2023 | 20/01/2023 | nan | nan | 0 | TK_NotStart | 222308392 | 54 | 222308392_54
PROD118770 | TT_Task | Vehicle 001 - FO2 WS7 WT1 | 02/03/2023 | 09/03/2023 | nan | nan | 0 | TK_NotStart | 222308392 | 55 | 222308392_55
PROD118780 | TT_Task | Vehicle 001 - FO2 WS7 WT9 | 08/02/2023 | 09/03/2023 | nan | nan | 0 | TK_NotStart | 222308392 | 55 | 222308392_55
PROD118790 | TT_Task | Vehicle 001 - FO2 WS7 WT2 | 14/02/2023 | 09/03/2023 | nan | nan | 0 | TK_NotStart | 222308392 | 55 | 222308392_55
PROD118800 | TT_Task | Vehicle 001 - FO2 WS7 WT3 | 24/02/2023 | 09/03/2023 | nan | nan | 0 | TK_NotStart | 222308392 | 55 | 222308392_55
PROD118810 | TT_Task | Vehicle 001 - FO2 WS7 WT4 | 20/02/2023 | 09/03/2023 | nan | nan | 0 | TK_NotStart | 222308392 | 55 | 222308392_55
PROD118820 | TT_Task | Vehicle 001 - FO2 WS7 WT5 | 27/01/2023 | 09/03/2023 | nan | nan | 0 | TK_NotStart | 222308392 | 55 | 222308392_55
PROD118830 | TT_Task | Vehicle 001 - FO2 WS7 WT6 | 17/01/2023 | 09/03/2023 | nan | nan | 0 | TK_NotStart | 222308392 | 55 | 222308392_55
PROD118840 | TT_Task | Vehicle 001 - FO2 WS7 WT7 | 02/02/2023 | 09/03/2023 | nan | nan | 0 | TK_NotStart | 222308392 | 55 | 222308392_55
PROD118850 | TT_Task | Vehicle 001 - FO2 WS7 WT8 | 23/01/2023 | 09/03/2023 | nan | nan | 0 | TK_NotStart | 222308392 | 55 | 222308392_55
MET-WS1.1-1230 | TT_Task | WT1 FO1 WS2 - Tooling Definition, Fabrication, Installation | 25/05/2022 | 30/08/2022 | nan | nan | 0 | TK_NotStart | 222308392 | 16 | 222308392_16
MET-WS1.1-1240 | TT_Task | WT1 FO1 WS2 - MBOM Implementation, Logistics Preparation, C Parts Lead Time | 25/05/2022 | 30/08/2022 | nan | nan | 0 | TK_NotStart | 222308392 | 17 | 222308392_17
MET-WS1.1-1270 | TT_Task | WT1 FO2 WS1 - Tooling Definition, Fabrication, Installation | 25/05/2022 | 30/08/2022 | nan | nan | 0 | TK_NotStart | 222308392 | 16 | 222308392_16
MET-WS1.1-1280 | TT_Task | WT1 FO2 WS1 - MBOM Implementation, Logistics Preparation, C Parts Lead Time | 25/05/2022 | 30/08/2022 | nan | nan | 0 | TK_NotStart | 222308392 | 17 | 222308392_17
MET-WS1.1-1310 | TT_Task | WT1 FO2 WS2 - Tooling Definition, Fabrication, Installation | 25/05/2022 | 30/08/2022 | nan | nan | 0 | TK_NotStart | 222308392 | 16 | 222308392_16
MET-WS1.1-1320 | TT_Task | WT1 FO2 WS2 - MBOM Implementation, Logistics Preparation, C Parts Lead Time | 25/05/2022 | 30/08/2022 | nan | nan | 0 | TK_NotStart | 222308392 | 17 | 222308392_17
MET-WS1.1-1350 | TT_Task | WT1 FO2 WS3 - Tooling Definition, Fabrication, Installation | 13/06/2022 | 16/09/2022 | nan | nan | 0 | TK_NotStart | 222308392 | 56 | 222308392_56
MET-WS1.1-1360 | TT_Task | WT1 FO2 WS3 - MBOM Implementation, Logistics Preparation, C Parts Lead Time | 13/06/2022 | 16/09/2022 | nan | nan | 0 | TK_NotStart | 222308392 | 17 | 222308392_17
MET-WS1.1-1390 | TT_Task | WT1 FO2 WS4 - Tooling Definition, Fabrication, Installation | 26/05/2022 | 31/08/2022 | nan | nan | 0 | TK_NotStart | 222308392 | 16 | 222308392_16
MET-WS1.1-1400 | TT_Task | WT1 FO2 WS4 - MBOM Implementation, Logistics Preparation, C Parts Lead Time | 26/05/2022 | 31/08/2022 | nan | nan | 0 | TK_NotStart | 222308392 | 17 | 222308392_17
MET-WS1.1-1430 | TT_Task | WT1 FO2 WS5 - Tooling Definition, Fabrication, Installation | 02/06/2022 | 07/09/2022 | nan | nan | 0 | TK_NotStart | 222308392 | 57 | 222308392_57
MET-WS1.1-1440 | TT_Task | WT1 FO2 WS5 - MBOM Implementation, Logistics Preparation, C Parts Lead Time | 02/06/2022 | 07/09/2022 | nan | nan | 0 | TK_NotStart | 222308392 | 58 | 222308392_58
MET-WS1.1-1470 | TT_Task | WT1 FO2 WS6 - Tooling Definition, Fabrication, Installation | 07/07/2022 | 12/10/2022 | nan | nan | 0 | TK_NotStart | 222308392 | 59 | 222308392_59
MET-WS1.1-1480 | TT_Task | WT1 FO2 WS6 - MBOM Implementation, Logistics Preparation, C Parts Lead Time | 07/07/2022 | 12/10/2022 | nan | nan | 0 | TK_NotStart | 222308392 | 60 | 222308392_60
MET-WS1.1-1510 | TT_Task | WT1 FO2 WS7 - Tooling Definition, Fabrication, Installation | 06/06/2022 | 09/09/2022 | nan | nan | 0 | TK_NotStart | 222308392 | 61 | 222308392_61
MET-WS1.1-1520 | TT_Task | WT1 FO2 WS7 - MBOM Implementation, Logistics Preparation, C Parts Lead Time | 06/06/2022 | 09/09/2022 | nan | nan | 0 | TK_NotStart | 222308392 | 62 | 222308392_62
A237310 | TT_Task | Vehicle 003 - Doubletraction | 12/10/2023 | 11/12/2023 | nan | nan | 0 | TK_NotStart | 222308392 | 63 | 222308392_63
A237330 | TT_Task | Vehicle 003 - Transport to Berlin | 31/01/2024 | 05/02/2024 | nan | nan | 0 | TK_NotStart | 222308392 | 31 | 222308392_31
A237340 | TT_Task | Vehicle 003 - Vehicle Type Tests | 27/02/2024 | 06/05/2024 | nan | nan | 0 | TK_NotStart | 222308392 | 33 | 222308392_33
MET-WS1.1-1540 | TT_Task | WT2 FO1 WS1 - Tooling Definition, Fabrication, Installation | 25/05/2022 | 30/08/2022 | nan | nan | 0 | TK_NotStart | 222308392 | 16 | 222308392_16
MET-WS1.1-1550 | TT_Task | WT2 FO1 WS1 - MBOM Implementation, Logistics Preparation, C Parts Lead Time | 25/05/2022 | 30/08/2022 | nan | nan | 0 | TK_NotStart | 222308392 | 17 | 222308392_17
MET-WS1.1-1580 | TT_Task | WT3 FO1 WS1 - Tooling Definition, Fabrication, Installation | 25/05/2022 | 30/08/2022 | nan | nan | 0 | TK_NotStart | 222308392 | 56 | 222308392_56
MET-WS1.1-1590 | TT_Task | WT3 FO1 WS1 - MBOM Implementation, Logistics Preparation, C Parts Lead Time | 25/05/2022 | 30/08/2022 | nan | nan | 0 | TK_NotStart | 222308392 | 17 | 222308392_17
MET-WS1.1-1620 | TT_Task | WT4 FO1 WS1 - Tooling Definition, Fabrication, Installation | 25/05/2022 | 30/08/2022 | nan | nan | 0 | TK_NotStart | 222308392 | 16 | 222308392_16
MET-WS1.1-1630 | TT_Task | WT4 FO1 WS1 - MBOM Implementation, Logistics Preparation, C Parts Lead Time | 25/05/2022 | 30/08/2022 | nan | nan | 0 | TK_NotStart | 222308392 | 17 | 222308392_17
MET-WS1.1-1660 | TT_Task | WT5 FO1 WS1 - Tooling Definition, Fabrication, Installation | 25/05/2022 | 30/08/2022 | nan | nan | 0 | TK_NotStart | 222308392 | 57 | 222308392_57
MET-WS1.1-1670 | TT_Task | WT5 FO1 WS1 - MBOM Implementation, Logistics Preparation, C Parts Lead Time | 25/05/2022 | 30/08/2022 | nan | nan | 0 | TK_NotStart | 222308392 | 58 | 222308392_58
MET-WS1.1-1700 | TT_Task | WT6 FO1 WS1 - Tooling Definition, Fabrication, Installation | 25/05/2022 | 30/08/2022 | nan | nan | 0 | TK_NotStart | 222308392 | 59 | 222308392_59
MET-WS1.1-1710 | TT_Task | WT6 FO1 WS1 - MBOM Implementation, Logistics Preparation, C Parts Lead Time | 25/05/2022 | 30/08/2022 | nan | nan | 0 | TK_NotStart | 222308392 | 60 | 222308392_60
MET-WS1.1-1740 | TT_Task | WT7 FO1 WS1 - Tooling Definition, Fabrication, Installation | 25/05/2022 | 30/08/2022 | nan | nan | 0 | TK_NotStart | 222308392 | 61 | 222308392_61
MET-WS1.1-1750 | TT_Task | WT7 FO1 WS1 - MBOM Implementation, Logistics Preparation, C Parts Lead Time | 25/05/2022 | 30/08/2022 | nan | nan | 0 | TK_NotStart | 222308392 | 62 | 222308392_62
MET-WS1.1-1780 | TT_Task | WT8 FO1 WS1 - Tooling Definition, Fabrication, Installation | 25/05/2022 | 30/08/2022 | nan | nan | 0 | TK_NotStart | 222308392 | 64 | 222308392_64
MET-WS1.1-1790 | TT_Task | WT8 FO1 WS1 - MBOM Implementation, Logistics Preparation, C Parts Lead Time | 25/05/2022 | 30/08/2022 | nan | nan | 0 | TK_NotStart | 222308392 | 65 | 222308392_65
MET-WS1.1-1820 | TT_Task | WT9 FO1 WS1 - Tooling Definition, Fabrication, Installation | 25/05/2022 | 30/08/2022 | nan | nan | 0 | TK_NotStart | 222308392 | 66 | 222308392_66
MET-WS1.1-1830 | TT_Task | WT9 FO1 WS1 - MBOM Implementation, Logistics Preparation, C Parts Lead Time | 25/05/2022 | 30/08/2022 | nan | nan | 0 | TK_NotStart | 222308392 | 65 | 222308392_65
MET-WS1.1-1860 | TT_Task | WT2 FO1 WS2 - Tooling Definition, Fabrication, Installation | 25/05/2022 | 30/08/2022 | nan | nan | 0 | TK_NotStart | 222308392 | 16 | 222308392_16
MET-WS1.1-1870 | TT_Task | WT2 FO1 WS2 - MBOM Implementation, Logistics Preparation, C Parts Lead Time | 25/05/2022 | 30/08/2022 | nan | nan | 0 | TK_NotStart | 222308392 | 17 | 222308392_17
MET-WS1.1-1900 | TT_Task | WT3 FO1 WS2 - Tooling Definition, Fabrication, Installation | 25/05/2022 | 30/08/2022 | nan | nan | 0 | TK_NotStart | 222308392 | 56 | 222308392_56
MET-WS1.1-1910 | TT_Task | WT3 FO1 WS2 - MBOM Implementation, Logistics Preparation, C Parts Lead Time | 25/05/2022 | 30/08/2022 | nan | nan | 0 | TK_NotStart | 222308392 | 17 | 222308392_17
MET-WS1.1-1940 | TT_Task | WT4 FO1 WS2 - Tooling Definition, Fabrication, Installation | 25/05/2022 | 30/08/2022 | nan | nan | 0 | TK_NotStart | 222308392 | 16 | 222308392_16
MET-WS1.1-1950 | TT_Task | WT4 FO1 WS2 - MBOM Implementation, Logistics Preparation, C Parts Lead Time | 25/05/2022 | 30/08/2022 | nan | nan | 0 | TK_NotStart | 222308392 | 17 | 222308392_17
MET-WS1.1-1980 | TT_Task | WT5 FO1 WS2 - Tooling Definition, Fabrication, Installation | 25/05/2022 | 30/08/2022 | nan | nan | 0 | TK_NotStart | 222308392 | 57 | 222308392_57
MET-WS1.1-1990 | TT_Task | WT5 FO1 WS2 - MBOM Implementation, Logistics Preparation, C Parts Lead Time | 25/05/2022 | 30/08/2022 | nan | nan | 0 | TK_NotStart | 222308392 | 58 | 222308392_58
MET-WS1.1-2020 | TT_Task | WT6 FO1 WS2 - Tooling Definition, Fabrication, Installation | 25/05/2022 | 30/08/2022 | nan | nan | 0 | TK_NotStart | 222308392 | 59 | 222308392_59
MET-WS1.1-2030 | TT_Task | WT6 FO1 WS2 - MBOM Implementation, Logistics Preparation, C Parts Lead Time | 25/05/2022 | 30/08/2022 | nan | nan | 0 | TK_NotStart | 222308392 | 60 | 222308392_60
MET-WS1.1-2060 | TT_Task | WT7 FO1 WS2 - Tooling Definition, Fabrication, Installation | 25/05/2022 | 30/08/2022 | nan | nan | 0 | TK_NotStart | 222308392 | 61 | 222308392_61
MET-WS1.1-2070 | TT_Task | WT7 FO1 WS2 - MBOM Implementation, Logistics Preparation, C Parts Lead Time | 25/05/2022 | 30/08/2022 | nan | nan | 0 | TK_NotStart | 222308392 | 62 | 222308392_62
MET-WS1.1-2100 | TT_Task | WT8 FO1 WS2 - Tooling Definition, Fabrication, Installation | 25/05/2022 | 30/08/2022 | nan | nan | 0 | TK_NotStart | 222308392 | 64 | 222308392_64
MET-WS1.1-2110 | TT_Task | WT8 FO1 WS2 - MBOM Implementation, Logistics Preparation, C Parts Lead Time | 25/05/2022 | 30/08/2022 | nan | nan | 0 | TK_NotStart | 222308392 | 65 | 222308392_65
MET-WS1.1-2140 | TT_Task | WT9 FO1 WS2 - Tooling Definition, Fabrication, Installation | 25/05/2022 | 30/08/2022 | nan | nan | 0 | TK_NotStart | 222308392 | 66 | 222308392_66
MET-WS1.1-2150 | TT_Task | WT9 FO1 WS2 - MBOM Implementation, Logistics Preparation, C Parts Lead Time | 25/05/2022 | 30/08/2022 | nan | nan | 0 | TK_NotStart | 222308392 | 65 | 222308392_65
MET-WS1.1-2180 | TT_Task | WT2 FO2 WS1 - Tooling Definition, Fabrication, Installation | 25/05/2022 | 30/08/2022 | nan | nan | 0 | TK_NotStart | 222308392 | 16 | 222308392_16
MET-WS1.1-2190 | TT_Task | WT2 FO2 WS1 - MBOM Implementation, Logistics Preparation, C Parts Lead Time | 25/05/2022 | 30/08/2022 | nan | nan | 0 | TK_NotStart | 222308392 | 17 | 222308392_17
MET-WS1.1-2220 | TT_Task | WT3 FO2 WS1 - Tooling Definition, Fabrication, Installation | 25/05/2022 | 30/08/2022 | nan | nan | 0 | TK_NotStart | 222308392 | 56 | 222308392_56
MET-WS1.1-2230 | TT_Task | WT3 FO2 WS1 - MBOM Implementation, Logistics Preparation, C Parts Lead Time | 25/05/2022 | 30/08/2022 | nan | nan | 0 | TK_NotStart | 222308392 | 17 | 222308392_17
MET-WS1.1-2260 | TT_Task | WT4 FO2 WS1 - Tooling Definition, Fabrication, Installation | 25/05/2022 | 30/08/2022 | nan | nan | 0 | TK_NotStart | 222308392 | 16 | 222308392_16
MET-WS1.1-2270 | TT_Task | WT4 FO2 WS1 - MBOM Implementation, Logistics Preparation, C Parts Lead Time | 25/05/2022 | 30/08/2022 | nan | nan | 0 | TK_NotStart | 222308392 | 17 | 222308392_17
MET-WS1.1-2300 | TT_Task | WT5 FO2 WS1 - Tooling Definition, Fabrication, Installation | 25/05/2022 | 30/08/2022 | nan | nan | 0 | TK_NotStart | 222308392 | 57 | 222308392_57
MET-WS1.1-2310 | TT_Task | WT5 FO2 WS1 - MBOM Implementation, Logistics Preparation, C Parts Lead Time | 25/05/2022 | 30/08/2022 | nan | nan | 0 | TK_NotStart | 222308392 | 58 | 222308392_58
MET-WS1.1-2340 | TT_Task | WT6 FO2 WS1 - Tooling Definition, Fabrication, Installation | 25/05/2022 | 30/08/2022 | nan | nan | 0 | TK_NotStart | 222308392 | 59 | 222308392_59
MET-WS1.1-2350 | TT_Task | WT6 FO2 WS1 - MBOM Implementation, Logistics Preparation, C Parts Lead Time | 25/05/2022 | 30/08/2022 | nan | nan | 0 | TK_NotStart | 222308392 | 60 | 222308392_60
MET-WS1.1-2380 | TT_Task | WT7 FO2 WS1 - Tooling Definition, Fabrication, Installation | 06/06/2022 | 09/09/2022 | nan | nan | 0 | TK_NotStart | 222308392 | 61 | 222308392_61
MET-WS1.1-2390 | TT_Task | WT7 FO2 WS1 - MBOM Implementation, Logistics Preparation, C Parts Lead Time | 06/06/2022 | 09/09/2022 | nan | nan | 0 | TK_NotStart | 222308392 | 62 | 222308392_62
MET-WS1.1-2420 | TT_Task | WT8 FO2 WS1 - Tooling Definition, Fabrication, Installation | 25/05/2022 | 30/08/2022 | nan | nan | 0 | TK_NotStart | 222308392 | 64 | 222308392_64
MET-WS1.1-2430 | TT_Task | WT8 FO2 WS1 - MBOM Implementation, Logistics Preparation, C Parts Lead Time | 25/05/2022 | 30/08/2022 | nan | nan | 0 | TK_NotStart | 222308392 | 65 | 222308392_65
MET-WS1.1-2460 | TT_Task | WT9 FO2 WS1 - Tooling Definition, Fabrication, Installation | 25/05/2022 | 30/08/2022 | nan | nan | 0 | TK_NotStart | 222308392 | 66 | 222308392_66
MET-WS1.1-2470 | TT_Task | WT9 FO2 WS1 - MBOM Implementation, Logistics Preparation, C Parts Lead Time | 25/05/2022 | 30/08/2022 | nan | nan | 0 | TK_NotStart | 222308392 | 65 | 222308392_65
MET-WS1.1-2500 | TT_Task | WT2 FO2 WS2 - Tooling Definition, Fabrication, Installation | 09/09/2022 | 15/12/2022 | nan | nan | 0 | TK_NotStart | 222308392 | 16 | 222308392_16
MET-WS1.1-2510 | TT_Task | WT2 FO2 WS2 - MBOM Implementation, Logistics Preparation, C Parts Lead Time | 09/09/2022 | 15/12/2022 | nan | nan | 0 | TK_NotStart | 222308392 | 17 | 222308392_17
MET-WS1.1-2540 | TT_Task | WT3 FO2 WS2 - Tooling Definition, Fabrication, Installation | 25/05/2022 | 30/08/2022 | nan | nan | 0 | TK_NotStart | 222308392 | 56 | 222308392_56
MET-WS1.1-2550 | TT_Task | WT3 FO2 WS2 - MBOM Implementation, Logistics Preparation, C Parts Lead Time | 25/05/2022 | 30/08/2022 | nan | nan | 0 | TK_NotStart | 222308392 | 17 | 222308392_17
MET-WS1.1-2580 | TT_Task | WT4 FO2 WS2 - Tooling Definition, Fabrication, Installation | 25/05/2022 | 30/08/2022 | nan | nan | 0 | TK_NotStart | 222308392 | 16 | 222308392_16
MET-WS1.1-2590 | TT_Task | WT4 FO2 WS2 - MBOM Implementation, Logistics Preparation, C Parts Lead Time | 25/05/2022 | 30/08/2022 | nan | nan | 0 | TK_NotStart | 222308392 | 17 | 222308392_17
MET-WS1.1-2620 | TT_Task | WT5 FO2 WS2 - Tooling Definition, Fabrication, Installation | 25/05/2022 | 30/08/2022 | nan | nan | 0 | TK_NotStart | 222308392 | 57 | 222308392_57
MET-WS1.1-2630 | TT_Task | WT5 FO2 WS2 - MBOM Implementation, Logistics Preparation, C Parts Lead Time | 25/05/2022 | 30/08/2022 | nan | nan | 0 | TK_NotStart | 222308392 | 58 | 222308392_58
MET-WS1.1-2660 | TT_Task | WT6 FO2 WS2 - Tooling Definition, Fabrication, Installation | 25/05/2022 | 30/08/2022 | nan | nan | 0 | TK_NotStart | 222308392 | 59 | 222308392_59
MET-WS1.1-2670 | TT_Task | WT6 FO2 WS2 - MBOM Implementation, Logistics Preparation, C Parts Lead Time | 25/05/2022 | 30/08/2022 | nan | nan | 0 | TK_NotStart | 222308392 | 60 | 222308392_60
MET-WS1.1-2700 | TT_Task | WT7 FO2 WS2 - Tooling Definition, Fabrication, Installation | 25/05/2022 | 30/08/2022 | nan | nan | 0 | TK_NotStart | 222308392 | 61 | 222308392_61
MET-WS1.1-2710 | TT_Task | WT7 FO2 WS2 - MBOM Implementation, Logistics Preparation, C Parts Lead Time | 25/05/2022 | 30/08/2022 | nan | nan | 0 | TK_NotStart | 222308392 | 62 | 222308392_62
MET-WS1.1-2740 | TT_Task | WT8 FO2 WS2 - Tooling Definition, Fabrication, Installation | 25/05/2022 | 30/08/2022 | nan | nan | 0 | TK_NotStart | 222308392 | 64 | 222308392_64
MET-WS1.1-2750 | TT_Task | WT8 FO2 WS2 - MBOM Implementation, Logistics Preparation, C Parts Lead Time | 25/05/2022 | 30/08/2022 | nan | nan | 0 | TK_NotStart | 222308392 | 65 | 222308392_65
MET-WS1.1-2780 | TT_Task | WT9 FO2 WS2 - Tooling Definition, Fabrication, Installation | 29/08/2022 | 02/12/2022 | nan | nan | 0 | TK_NotStart | 222308392 | 66 | 222308392_66
MET-WS1.1-2790 | TT_Task | WT9 FO2 WS2 - MBOM Implementation, Logistics Preparation, C Parts Lead Time | 29/08/2022 | 02/12/2022 | nan | nan | 0 | TK_NotStart | 222308392 | 65 | 222308392_65
MET-WS1.1-2820 | TT_Task | WT2 FO2 WS3 - Tooling Definition, Fabrication, Installation | 17/10/2022 | 20/01/2023 | nan | nan | 0 | TK_NotStart | 222308392 | 56 | 222308392_56
MET-WS1.1-2830 | TT_Task | WT2 FO2 WS3 - MBOM Implementation, Logistics Preparation, C Parts Lead Time | 17/10/2022 | 20/01/2023 | nan | nan | 0 | TK_NotStart | 222308392 | 17 | 222308392_17
MET-WS1.1-2860 | TT_Task | WT3 FO2 WS3 - Tooling Definition, Fabrication, Installation | 23/05/2022 | 26/08/2022 | nan | nan | 0 | TK_NotStart | 222308392 | 56 | 222308392_56
MET-WS1.1-2870 | TT_Task | WT3 FO2 WS3 - MBOM Implementation, Logistics Preparation, C Parts Lead Time | 23/05/2022 | 26/08/2022 | nan | nan | 0 | TK_NotStart | 222308392 | 17 | 222308392_17
MET-WS1.1-2900 | TT_Task | WT4 FO2 WS3 - Tooling Definition, Fabrication, Installation | 17/10/2022 | 20/01/2023 | nan | nan | 0 | TK_NotStart | 222308392 | 56 | 222308392_56
MET-WS1.1-2910 | TT_Task | WT4 FO2 WS3 - MBOM Implementation, Logistics Preparation, C Parts Lead Time | 17/10/2022 | 20/01/2023 | nan | nan | 0 | TK_NotStart | 222308392 | 17 | 222308392_17
MET-WS1.1-2940 | TT_Task | WT5 FO2 WS3 - Tooling Definition, Fabrication, Installation | 26/05/2022 | 31/08/2022 | nan | nan | 0 | TK_NotStart | 222308392 | 57 | 222308392_57
MET-WS1.1-2950 | TT_Task | WT5 FO2 WS3 - MBOM Implementation, Logistics Preparation, C Parts Lead Time | 26/05/2022 | 31/08/2022 | nan | nan | 0 | TK_NotStart | 222308392 | 58 | 222308392_58
MET-WS1.1-2980 | TT_Task | WT6 FO2 WS3 - Tooling Definition, Fabrication, Installation | 17/10/2022 | 20/01/2023 | nan | nan | 0 | TK_NotStart | 222308392 | 59 | 222308392_59
MET-WS1.1-2990 | TT_Task | WT6 FO2 WS3 - MBOM Implementation, Logistics Preparation, C Parts Lead Time | 17/10/2022 | 20/01/2023 | nan | nan | 0 | TK_NotStart | 222308392 | 60 | 222308392_60
MET-WS1.1-3020 | TT_Task | WT7 FO2 WS3 - Tooling Definition, Fabrication, Installation | 23/05/2022 | 26/08/2022 | nan | nan | 0 | TK_NotStart | 222308392 | 61 | 222308392_61
MET-WS1.1-3030 | TT_Task | WT7 FO2 WS3 - MBOM Implementation, Logistics Preparation, C Parts Lead Time | 23/05/2022 | 26/08/2022 | nan | nan | 0 | TK_NotStart | 222308392 | 62 | 222308392_62
MET-WS1.1-3060 | TT_Task | WT8 FO2 WS3 - Tooling Definition, Fabrication, Installation | 17/10/2022 | 20/01/2023 | nan | nan | 0 | TK_NotStart | 222308392 | 64 | 222308392_64
MET-WS1.1-3070 | TT_Task | WT8 FO2 WS3 - MBOM Implementation, Logistics Preparation, C Parts Lead Time | 17/10/2022 | 20/01/2023 | nan | nan | 0 | TK_NotStart | 222308392 | 65 | 222308392_65
MET-WS1.1-3100 | TT_Task | WT9 FO2 WS3 - Tooling Definition, Fabrication, Installation | 13/06/2022 | 16/09/2022 | nan | nan | 0 | TK_NotStart | 222308392 | 66 | 222308392_66
MET-WS1.1-3110 | TT_Task | WT9 FO2 WS3 - MBOM Implementation, Logistics Preparation, C Parts Lead Time | 13/06/2022 | 16/09/2022 | nan | nan | 0 | TK_NotStart | 222308392 | 65 | 222308392_65
MET-WS1.1-3140 | TT_Task | WT2 FO2 WS4 - Tooling Definition, Fabrication, Installation | 16/05/2022 | 19/08/2022 | nan | nan | 0 | TK_NotStart | 222308392 | 16 | 222308392_16
MET-WS1.1-3150 | TT_Task | WT2 FO2 WS4 - MBOM Implementation, Logistics Preparation, C Parts Lead Time | 16/05/2022 | 19/08/2022 | nan | nan | 0 | TK_NotStart | 222308392 | 17 | 222308392_17
MET-WS1.1-3180 | TT_Task | WT3 FO2 WS4 - Tooling Definition, Fabrication, Installation | 26/05/2022 | 31/08/2022 | nan | nan | 0 | TK_NotStart | 222308392 | 56 | 222308392_56
MET-WS1.1-3190 | TT_Task | WT3 FO2 WS4 - MBOM Implementation, Logistics Preparation, C Parts Lead Time | 26/05/2022 | 31/08/2022 | nan | nan | 0 | TK_NotStart | 222308392 | 17 | 222308392_17
MET-WS1.1-3220 | TT_Task | WT4 FO2 WS4 - Tooling Definition, Fabrication, Installation | 23/05/2022 | 26/08/2022 | nan | nan | 0 | TK_NotStart | 222308392 | 16 | 222308392_16
MET-WS1.1-3230 | TT_Task | WT4 FO2 WS4 - MBOM Implementation, Logistics Preparation, C Parts Lead Time | 23/05/2022 | 26/08/2022 | nan | nan | 0 | TK_NotStart | 222308392 | 17 | 222308392_17
MET-WS1.1-3260 | TT_Task | WT5 FO2 WS4 - Tooling Definition, Fabrication, Installation | 26/05/2022 | 31/08/2022 | nan | nan | 0 | TK_NotStart | 222308392 | 57 | 222308392_57
MET-WS1.1-3270 | TT_Task | WT5 FO2 WS4 - MBOM Implementation, Logistics Preparation, C Parts Lead Time | 26/05/2022 | 31/08/2022 | nan | nan | 0 | TK_NotStart | 222308392 | 58 | 222308392_58
MET-WS1.1-3300 | TT_Task | WT6 FO2 WS4 - Tooling Definition, Fabrication, Installation | 23/05/2022 | 26/08/2022 | nan | nan | 0 | TK_NotStart | 222308392 | 59 | 222308392_59
MET-WS1.1-3310 | TT_Task | WT6 FO2 WS4 - MBOM Implementation, Logistics Preparation, C Parts Lead Time | 23/05/2022 | 26/08/2022 | nan | nan | 0 | TK_NotStart | 222308392 | 60 | 222308392_60
MET-WS1.1-3340 | TT_Task | WT7 FO2 WS4 - Tooling Definition, Fabrication, Installation | 26/05/2022 | 31/08/2022 | nan | nan | 0 | TK_NotStart | 222308392 | 61 | 222308392_61
MET-WS1.1-3350 | TT_Task | WT7 FO2 WS4 - MBOM Implementation, Logistics Preparation, C Parts Lead Time | 26/05/2022 | 31/08/2022 | nan | nan | 0 | TK_NotStart | 222308392 | 62 | 222308392_62
MET-WS1.1-3380 | TT_Task | WT8 FO2 WS4 - Tooling Definition, Fabrication, Installation | 16/05/2022 | 19/08/2022 | nan | nan | 0 | TK_NotStart | 222308392 | 64 | 222308392_64
MET-WS1.1-3390 | TT_Task | WT8 FO2 WS4 - MBOM Implementation, Logistics Preparation, C Parts Lead Time | 16/05/2022 | 19/08/2022 | nan | nan | 0 | TK_NotStart | 222308392 | 65 | 222308392_65
MET-WS1.1-3420 | TT_Task | WT9 FO2 WS4 - Tooling Definition, Fabrication, Installation | 26/05/2022 | 31/08/2022 | nan | nan | 0 | TK_NotStart | 222308392 | 66 | 222308392_66
MET-WS1.1-3430 | TT_Task | WT9 FO2 WS4 - MBOM Implementation, Logistics Preparation, C Parts Lead Time | 26/05/2022 | 31/08/2022 | nan | nan | 0 | TK_NotStart | 222308392 | 65 | 222308392_65
MET-WS1.1-3460 | TT_Task | WT2 FO2 WS5 - Tooling Definition, Fabrication, Installation | 25/05/2022 | 30/08/2022 | nan | nan | 0 | TK_NotStart | 222308392 | 57 | 222308392_57
MET-WS1.1-3470 | TT_Task | WT2 FO2 WS5 - MBOM Implementation, Logistics Preparation, C Parts Lead Time | 25/05/2022 | 30/08/2022 | nan | nan | 0 | TK_NotStart | 222308392 | 58 | 222308392_58
MET-WS1.1-3500 | TT_Task | WT3 FO2 WS5 - Tooling Definition, Fabrication, Installation | 26/05/2022 | 31/08/2022 | nan | nan | 0 | TK_NotStart | 222308392 | 57 | 222308392_57
MET-WS1.1-3510 | TT_Task | WT3 FO2 WS5 - MBOM Implementation, Logistics Preparation, C Parts Lead Time | 26/05/2022 | 31/08/2022 | nan | nan | 0 | TK_NotStart | 222308392 | 58 | 222308392_58
MET-WS1.1-3540 | TT_Task | WT4 FO2 WS5 - Tooling Definition, Fabrication, Installation | 26/05/2022 | 31/08/2022 | nan | nan | 0 | TK_NotStart | 222308392 | 57 | 222308392_57
MET-WS1.1-3550 | TT_Task | WT4 FO2 WS5 - MBOM Implementation, Logistics Preparation, C Parts Lead Time | 26/05/2022 | 31/08/2022 | nan | nan | 0 | TK_NotStart | 222308392 | 58 | 222308392_58
MET-WS1.1-3580 | TT_Task | WT5 FO2 WS5 - Tooling Definition, Fabrication, Installation | 06/06/2022 | 09/09/2022 | nan | nan | 0 | TK_NotStart | 222308392 | 57 | 222308392_57
MET-WS1.1-3590 | TT_Task | WT5 FO2 WS5 - MBOM Implementation, Logistics Preparation, C Parts Lead Time | 06/06/2022 | 09/09/2022 | nan | nan | 0 | TK_NotStart | 222308392 | 58 | 222308392_58
MET-WS1.1-3620 | TT_Task | WT6 FO2 WS5 - Tooling Definition, Fabrication, Installation | 16/06/2022 | 21/09/2022 | nan | nan | 0 | TK_NotStart | 222308392 | 59 | 222308392_59
MET-WS1.1-3630 | TT_Task | WT6 FO2 WS5 - MBOM Implementation, Logistics Preparation, C Parts Lead Time | 16/06/2022 | 21/09/2022 | nan | nan | 0 | TK_NotStart | 222308392 | 60 | 222308392_60
MET-WS1.1-3660 | TT_Task | WT7 FO2 WS5 - Tooling Definition, Fabrication, Installation | 04/07/2022 | 07/10/2022 | nan | nan | 0 | TK_NotStart | 222308392 | 61 | 222308392_61
MET-WS1.1-3670 | TT_Task | WT7 FO2 WS5 - MBOM Implementation, Logistics Preparation, C Parts Lead Time | 04/07/2022 | 07/10/2022 | nan | nan | 0 | TK_NotStart | 222308392 | 62 | 222308392_62
MET-WS1.1-3700 | TT_Task | WT8 FO2 WS5 - Tooling Definition, Fabrication, Installation | 27/06/2022 | 30/09/2022 | nan | nan | 0 | TK_NotStart | 222308392 | 57 | 222308392_57
MET-WS1.1-3710 | TT_Task | WT8 FO2 WS5 - MBOM Implementation, Logistics Preparation, C Parts Lead Time | 27/06/2022 | 30/09/2022 | nan | nan | 0 | TK_NotStart | 222308392 | 65 | 222308392_65
MET-WS1.1-3740 | TT_Task | WT9 FO2 WS5 - Tooling Definition, Fabrication, Installation | 04/07/2022 | 07/10/2022 | nan | nan | 0 | TK_NotStart | 222308392 | 66 | 222308392_66
MET-WS1.1-3750 | TT_Task | WT9 FO2 WS5 - MBOM Implementation, Logistics Preparation, C Parts Lead Time | 04/07/2022 | 07/10/2022 | nan | nan | 0 | TK_NotStart | 222308392 | 65 | 222308392_65
MET-WS1.1-3780 | TT_Task | WT2 FO2 WS6 - Tooling Definition, Fabrication, Installation | 23/05/2022 | 26/08/2022 | nan | nan | 0 | TK_NotStart | 222308392 | 59 | 222308392_59
MET-WS1.1-3790 | TT_Task | WT2 FO2 WS6 - MBOM Implementation, Logistics Preparation, C Parts Lead Time | 23/05/2022 | 26/08/2022 | nan | nan | 0 | TK_NotStart | 222308392 | 60 | 222308392_60
MET-WS1.1-3820 | TT_Task | WT3 FO2 WS6 - Tooling Definition, Fabrication, Installation | 06/06/2022 | 09/09/2022 | nan | nan | 0 | TK_NotStart | 222308392 | 59 | 222308392_59
MET-WS1.1-3830 | TT_Task | WT3 FO2 WS6 - MBOM Implementation, Logistics Preparation, C Parts Lead Time | 06/06/2022 | 09/09/2022 | nan | nan | 0 | TK_NotStart | 222308392 | 60 | 222308392_60
MET-WS1.1-3860 | TT_Task | WT4 FO2 WS6 - Tooling Definition, Fabrication, Installation | 23/05/2022 | 26/08/2022 | nan | nan | 0 | TK_NotStart | 222308392 | 59 | 222308392_59
MET-WS1.1-3870 | TT_Task | WT4 FO2 WS6 - MBOM Implementation, Logistics Preparation, C Parts Lead Time | 23/05/2022 | 26/08/2022 | nan | nan | 0 | TK_NotStart | 222308392 | 60 | 222308392_60
MET-WS1.1-3900 | TT_Task | WT5 FO2 WS6 - Tooling Definition, Fabrication, Installation | 13/06/2022 | 16/09/2022 | nan | nan | 0 | TK_NotStart | 222308392 | 59 | 222308392_59
MET-WS1.1-3910 | TT_Task | WT5 FO2 WS6 - MBOM Implementation, Logistics Preparation, C Parts Lead Time | 13/06/2022 | 16/09/2022 | nan | nan | 0 | TK_NotStart | 222308392 | 60 | 222308392_60
MET-WS1.1-3940 | TT_Task | WT6 FO2 WS6 - Tooling Definition, Fabrication, Installation | 23/05/2022 | 26/08/2022 | nan | nan | 0 | TK_NotStart | 222308392 | 59 | 222308392_59
MET-WS1.1-3950 | TT_Task | WT6 FO2 WS6 - MBOM Implementation, Logistics Preparation, C Parts Lead Time | 23/05/2022 | 26/08/2022 | nan | nan | 0 | TK_NotStart | 222308392 | 60 | 222308392_60
MET-WS1.1-3980 | TT_Task | WT7 FO2 WS6 - Tooling Definition, Fabrication, Installation | 06/06/2022 | 09/09/2022 | nan | nan | 0 | TK_NotStart | 222308392 | 61 | 222308392_61
MET-WS1.1-3990 | TT_Task | WT7 FO2 WS6 - MBOM Implementation, Logistics Preparation, C Parts Lead Time | 06/06/2022 | 09/09/2022 | nan | nan | 0 | TK_NotStart | 222308392 | 60 | 222308392_60
MET-WS1.1-4020 | TT_Task | WT8 FO2 WS6 - Tooling Definition, Fabrication, Installation | 23/05/2022 | 26/08/2022 | nan | nan | 0 | TK_NotStart | 222308392 | 59 | 222308392_59
MET-WS1.1-4030 | TT_Task | WT8 FO2 WS6 - MBOM Implementation, Logistics Preparation, C Parts Lead Time | 23/05/2022 | 26/08/2022 | nan | nan | 0 | TK_NotStart | 222308392 | 60 | 222308392_60
MET-WS1.1-4060 | TT_Task | WT9 FO2 WS6 - Tooling Definition, Fabrication, Installation | 07/07/2022 | 12/10/2022 | nan | nan | 0 | TK_NotStart | 222308392 | 59 | 222308392_59
MET-WS1.1-4070 | TT_Task | WT9 FO2 WS6 - MBOM Implementation, Logistics Preparation, C Parts Lead Time | 07/07/2022 | 12/10/2022 | nan | nan | 0 | TK_NotStart | 222308392 | 60 | 222308392_60
MET-WS1.1-4100 | TT_Task | WT2 FO2 WS7 - Tooling Definition, Fabrication, Installation | 06/06/2022 | 09/09/2022 | nan | nan | 0 | TK_NotStart | 222308392 | 61 | 222308392_61
MET-WS1.1-4110 | TT_Task | WT2 FO2 WS7 - MBOM Implementation, Logistics Preparation, C Parts Lead Time | 06/06/2022 | 09/09/2022 | nan | nan | 0 | TK_NotStart | 222308392 | 62 | 222308392_62
MET-WS1.1-4140 | TT_Task | WT3 FO2 WS7 - Tooling Definition, Fabrication, Installation | 06/06/2022 | 09/09/2022 | nan | nan | 0 | TK_NotStart | 222308392 | 61 | 222308392_61
MET-WS1.1-4150 | TT_Task | WT3 FO2 WS7 - MBOM Implementation, Logistics Preparation, C Parts Lead Time | 06/06/2022 | 09/09/2022 | nan | nan | 0 | TK_NotStart | 222308392 | 62 | 222308392_62
MET-WS1.1-4180 | TT_Task | WT4 FO2 WS7 - Tooling Definition, Fabrication, Installation | 06/06/2022 | 09/09/2022 | nan | nan | 0 | TK_NotStart | 222308392 | 61 | 222308392_61
MET-WS1.1-4190 | TT_Task | WT4 FO2 WS7 - MBOM Implementation, Logistics Preparation, C Parts Lead Time | 06/06/2022 | 09/09/2022 | nan | nan | 0 | TK_NotStart | 222308392 | 62 | 222308392_62
MET-WS1.1-4220 | TT_Task | WT5 FO2 WS7 - Tooling Definition, Fabrication, Installation | 06/06/2022 | 09/09/2022 | nan | nan | 0 | TK_NotStart | 222308392 | 61 | 222308392_61
MET-WS1.1-4230 | TT_Task | WT5 FO2 WS7 - MBOM Implementation, Logistics Preparation, C Parts Lead Time | 06/06/2022 | 09/09/2022 | nan | nan | 0 | TK_NotStart | 222308392 | 62 | 222308392_62
MET-WS1.1-4260 | TT_Task | WT6 FO2 WS7 - Tooling Definition, Fabrication, Installation | 06/06/2022 | 09/09/2022 | nan | nan | 0 | TK_NotStart | 222308392 | 61 | 222308392_61
MET-WS1.1-4270 | TT_Task | WT6 FO2 WS7 - MBOM Implementation, Logistics Preparation, C Parts Lead Time | 06/06/2022 | 09/09/2022 | nan | nan | 0 | TK_NotStart | 222308392 | 60 | 222308392_60
MET-WS1.1-4300 | TT_Task | WT7 FO2 WS7 - Tooling Definition, Fabrication, Installation | 06/06/2022 | 09/09/2022 | nan | nan | 0 | TK_NotStart | 222308392 | 61 | 222308392_61
MET-WS1.1-4310 | TT_Task | WT7 FO2 WS7 - MBOM Implementation, Logistics Preparation, C Parts Lead Time | 06/06/2022 | 09/09/2022 | nan | nan | 0 | TK_NotStart | 222308392 | 62 | 222308392_62
MET-WS1.1-4340 | TT_Task | WT8 FO2 WS7 - Tooling Definition, Fabrication, Installation | 06/06/2022 | 09/09/2022 | nan | nan | 0 | TK_NotStart | 222308392 | 61 | 222308392_61
MET-WS1.1-4350 | TT_Task | WT8 FO2 WS7 - MBOM Implementation, Logistics Preparation, C Parts Lead Time | 06/06/2022 | 09/09/2022 | nan | nan | 0 | TK_NotStart | 222308392 | 62 | 222308392_62
MET-WS1.1-4380 | TT_Task | WT9 FO2 WS7 - Tooling Definition, Fabrication, Installation | 06/06/2022 | 09/09/2022 | nan | nan | 0 | TK_NotStart | 222308392 | 61 | 222308392_61
MET-WS1.1-4390 | TT_Task | WT9 FO2 WS7 - MBOM Implementation, Logistics Preparation, C Parts Lead Time | 06/06/2022 | 09/09/2022 | nan | nan | 0 | TK_NotStart | 222308392 | 62 | 222308392_62
A237350 | TT_Task | Pflichtenheft Phase | 15/12/2020 | 28/12/2020 | 15/12/2020 | 15/03/2021 | 0 | TK_Complete | 222308392 | 67 | 222308392_67
A237360 | TT_Task | Customer Review of Pflichtenheft | 15/03/2021 | 15/06/2021 | 15/03/2021 | 15/06/2021 | 0 | TK_Complete | 222308392 | 68 | 222308392_68
A237370 | TT_Task | Update of Pflichtenheft Based on Customer Feedback | 16/06/2021 | 26/08/2021 | 16/06/2021 | 26/08/2021 | 0 | TK_Complete | 222308392 | 68 | 222308392_68
A237380 | TT_Task | Customer Review of the Updated Pflichtenheft | 27/08/2021 | 10/09/2021 | 27/08/2021 | 17/11/2021 | 0 | TK_Complete | 222308392 | 68 | 222308392_68
A237390 | TT_Task | GR2 Decision Pending | 29/04/2021 | 20/05/2021 | 29/04/2021 | 20/05/2021 | 0 | TK_Complete | 222308392 | 69 | 222308392_69
PROD120160 | TT_Task | Vehicle 001 - Vormontage UG WT3 | 27/06/2022 | 29/07/2022 | nan | nan | 0 | TK_NotStart | 222308392 | 46 | 222308392_46
PROD120170 | TT_Task | Vehicle 001 - Vormontage UG WT4 | 18/03/2022 | 21/04/2022 | nan | nan | 0 | TK_NotStart | 222308392 | 46 | 222308392_46
PROD120180 | TT_Task | Vehicle 001 - Vormontage UG WT5 | 03/06/2022 | 08/07/2022 | nan | nan | 0 | TK_NotStart | 222308392 | 46 | 222308392_46
PROD120190 | TT_Task | Vehicle 001 - Vormontage UG WT6 | 25/03/2022 | 28/04/2022 | nan | nan | 0 | TK_NotStart | 222308392 | 46 | 222308392_46
PROD120200 | TT_Task | Vehicle 001 - Vormontage UG WT7 | 13/06/2022 | 15/07/2022 | nan | nan | 0 | TK_NotStart | 222308392 | 46 | 222308392_46
PROD120210 | TT_Task | Vehicle 001 - Vormontage UG WT8 | 19/04/2022 | 19/05/2022 | nan | nan | 0 | TK_NotStart | 222308392 | 46 | 222308392_46
PROD120220 | TT_Task | Vehicle 001 - Montage UG WT3 | 09/08/2022 | 10/10/2022 | nan | nan | 0 | TK_NotStart | 222308392 | 47 | 222308392_47
PROD120230 | TT_Task | Vehicle 001 - Montage UG WT4 | 20/05/2022 | 15/06/2022 | nan | nan | 0 | TK_NotStart | 222308392 | 47 | 222308392_47
PROD120240 | TT_Task | Vehicle 001 - Montage UG WT5 | 11/07/2022 | 15/09/2022 | nan | nan | 0 | TK_NotStart | 222308392 | 47 | 222308392_47
PROD120250 | TT_Task | Vehicle 001 - Montage UG WT6 | 31/05/2022 | 22/06/2022 | nan | nan | 0 | TK_NotStart | 222308392 | 47 | 222308392_47
PROD120260 | TT_Task | Vehicle 001 - Montage UG WT7 | 18/07/2022 | 22/09/2022 | nan | nan | 0 | TK_NotStart | 222308392 | 47 | 222308392_47
PROD120270 | TT_Task | Vehicle 001 - Montage UG WT8 | 22/06/2022 | 13/07/2022 | nan | nan | 0 | TK_NotStart | 222308392 | 47 | 222308392_47
PROD120280 | TT_Task | Vehicle 001 - Rohbau Wagenkasten WT3 | 11/10/2022 | 04/11/2022 | nan | nan | 0 | TK_NotStart | 222308392 | 49 | 222308392_49
PROD120290 | TT_Task | Vehicle 001 - Rohbau Wagenkasten WT4 | 07/07/2022 | 15/08/2022 | nan | nan | 0 | TK_NotStart | 222308392 | 49 | 222308392_49
PROD120300 | TT_Task | Vehicle 001 - Rohbau Wagenkasten WT5 | 16/09/2022 | 12/10/2022 | nan | nan | 0 | TK_NotStart | 222308392 | 49 | 222308392_49
PROD120310 | TT_Task | Vehicle 001 - Rohbau Wagenkasten WT6 | 14/07/2022 | 22/08/2022 | nan | nan | 0 | TK_NotStart | 222308392 | 49 | 222308392_49
PROD120320 | TT_Task | Vehicle 001 - Rohbau Wagenkasten WT7 | 23/09/2022 | 19/10/2022 | nan | nan | 0 | TK_NotStart | 222308392 | 49 | 222308392_49
PROD120330 | TT_Task | Vehicle 001 - Rohbau Wagenkasten WT8 | 18/08/2022 | 12/09/2022 | nan | nan | 0 | TK_NotStart | 222308392 | 49 | 222308392_49
PROD120340 | TT_Task | Vehicle 001 - Seitenwandgerippe WT3 | 29/08/2022 | 10/10/2022 | nan | nan | 42055 | TK_NotStart | 222308392 | 48 | 222308392_48
PROD120350 | TT_Task | Vehicle 001 - Seitenwandgerippe WT4 | 09/05/2022 | 15/06/2022 | nan | nan | 42551 | TK_NotStart | 222308392 | 48 | 222308392_48
PROD120360 | TT_Task | Vehicle 001 - Seitenwandgerippe WT5 | 28/07/2022 | 15/09/2022 | nan | nan | 42183 | TK_NotStart | 222308392 | 48 | 222308392_48
PROD120370 | TT_Task | Vehicle 001 - Seitenwandgerippe WT6 | 16/05/2022 | 22/06/2022 | nan | nan | 42511 | TK_NotStart | 222308392 | 48 | 222308392_48
PROD120380 | TT_Task | Vehicle 001 - Seitenwandgerippe WT7 | 12/08/2022 | 22/09/2022 | nan | nan | 42143 | TK_NotStart | 222308392 | 48 | 222308392_48
PROD120390 | TT_Task | Vehicle 001 - Seitenwandgerippe WT8 | 09/06/2022 | 13/07/2022 | nan | nan | 42391 | TK_NotStart | 222308392 | 48 | 222308392_48
PROD120400 | TT_Task | Vehicle 001 - Rohbau Abnahme WT3 | 07/11/2022 | 15/11/2022 | nan | nan | 0 | TK_NotStart | 222308392 | 49 | 222308392_49
PROD120410 | TT_Task | Vehicle 001 - Rohbau Abnahme WT4 | 16/08/2022 | 29/08/2022 | nan | nan | 0 | TK_NotStart | 222308392 | 49 | 222308392_49
PROD120420 | TT_Task | Vehicle 001 - Rohbau Abnahme WT5 | 13/10/2022 | 26/10/2022 | nan | nan | 0 | TK_NotStart | 222308392 | 49 | 222308392_49
PROD120430 | TT_Task | Vehicle 001 - Rohbau Abnahme WT6 | 23/08/2022 | 05/09/2022 | nan | nan | 0 | TK_NotStart | 222308392 | 49 | 222308392_49
PROD120440 | TT_Task | Vehicle 001 - Rohbau Abnahme WT7 | 20/10/2022 | 26/10/2022 | nan | nan | 0 | TK_NotStart | 222308392 | 49 | 222308392_49
PROD120450 | TT_Task | Vehicle 001 - Rohbau Abnahme WT8 | 13/09/2022 | 26/09/2022 | nan | nan | 0 | TK_NotStart | 222308392 | 49 | 222308392_49
PROD120460 | TT_Task | Vehicle 001 - Oberflache WT3 | 17/11/2022 | 22/12/2022 | nan | nan | 0 | TK_NotStart | 222308392 | 50 | 222308392_50
PROD120470 | TT_Task | Vehicle 001 - Oberflache WT4 | 30/08/2022 | 16/12/2022 | nan | nan | 0 | TK_NotStart | 222308392 | 50 | 222308392_50
PROD120480 | TT_Task | Vehicle 001 - Oberflache WT5 | 27/10/2022 | 24/11/2022 | nan | nan | 0 | TK_NotStart | 222308392 | 50 | 222308392_50
PROD120490 | TT_Task | Vehicle 001 - Oberflache WT6 | 06/09/2022 | 11/11/2022 | nan | nan | 0 | TK_NotStart | 222308392 | 50 | 222308392_50
PROD120500 | TT_Task | Vehicle 001 - Oberflache WT7 | 27/10/2022 | 30/11/2022 | nan | nan | 0 | TK_NotStart | 222308392 | 50 | 222308392_50
PROD120510 | TT_Task | Vehicle 001 - Oberflache WT8 | 27/09/2022 | 18/11/2022 | nan | nan | 0 | TK_NotStart | 222308392 | 50 | 222308392_50
A237400 | TT_Task | Vehicle 001 - Vehicle Separation for Transport | 27/07/2023 | 28/07/2023 | nan | nan | 0 | TK_NotStart | 222308392 | 70 | 222308392_70
A237410 | TT_Task | Vehicle 001 - Vehicle Connection after Transport | 04/08/2023 | 14/08/2023 | nan | nan | 0 | TK_NotStart | 222308392 | 70 | 222308392_70
PROD120730 | TT_Task | Vehicle 002 - Druckversuch (first module) | 28/11/2022 | 27/01/2023 | nan | nan | 0 | TK_NotStart | 222308392 | 7 | 222308392_7
PROD120740 | TT_Task | Vehicle 004 - Doppeltraktion | 12/10/2023 | 11/12/2023 | nan | nan | 0 | TK_NotStart | 222308392 | 71 | 222308392_71
PROD120750 | TT_Task | Vehicle 004 - Restarbeiten/Werksabnahme | 10/01/2024 | 30/01/2024 | nan | nan | 0 | TK_NotStart | 222308392 | 71 | 222308392_71
PROD120760 | TT_Task | Vehicle 004 - Klimakammertest | 31/01/2024 | 22/03/2024 | nan | nan | 0 | TK_NotStart | 222308392 | 72 | 222308392_72
A237420 | TT_Task | Vehicle 003 - Validation Vehicle Functions ; EMC pre-test | 12/12/2023 | 09/01/2024 | nan | nan | 0 | TK_NotStart | 222308392 | 73 | 222308392_73
PROD120770 | TT_Task | Vehicle 004 - Validation vehicle functions ; EMC pre-test | 12/12/2023 | 09/01/2024 | nan | nan | 0 | TK_NotStart | 222308392 | 73 | 222308392_73
PROD120780 | TT_Task | Vehicle 001 - AT Vehicle type Tests - Kunde | 21/09/2023 | 09/11/2023 | nan | nan | 89 | TK_NotStart | 222308392 | 33 | 222308392_33
PROD120900 | TT_Task | Delivery of KTP Materials | 24/08/2022 | 25/08/2022 | nan | nan | 2528 | TK_NotStart | 222308392 | 74 | 222308392_74
PROD120910 | TT_Task | Vehicle 003 - Rohbau (first module) | 10/11/2022 | 14/03/2023 | nan | nan | 0 | TK_NotStart | 222308392 | 7 | 222308392_7
PROD120920 | TT_Task | Vehicle 003 - Oberflache (first module) | 15/03/2023 | 10/04/2023 | nan | nan | 0 | TK_NotStart | 222308392 | 8 | 222308392_8
PROD120930 | TT_Task | Vehicle 003 - Innenausbau | 11/04/2023 | 26/06/2023 | nan | nan | 0 | TK_NotStart | 222308392 | 9 | 222308392_9
PROD120940 | TT_Task | Vehicle 006 - Klimakammertest | 10/01/2024 | 07/03/2024 | nan | nan | 0 | TK_NotStart | 222308392 | 72 | 222308392_72
25863-801710 | TT_Task | Trial Run of Vehicle #01 | 18/05/2022 | 09/08/2022 | nan | nan | 0 | TK_NotStart | 1391426496 | 1 | 1391426496_1
25863-802070 | TT_Task | Trial Run of Vehicle #02 | 01/06/2022 | 23/08/2022 | nan | nan | 0 | TK_NotStart | 1391426496 | 1 | 1391426496_1
25863-803070 | TT_Task | Trial Run of Vehicle #03 | 17/05/2022 | 08/08/2022 | nan | nan | 0 | TK_NotStart | 1391426496 | 1 | 1391426496_1
25863-804070 | TT_Task | Trial Run of Vehicle #04 | 17/05/2022 | 08/08/2022 | nan | nan | 0 | TK_NotStart | 1391426496 | 1 | 1391426496_1
25863-805070 | TT_Task | Trial Run of Vehicle #05 | 26/05/2022 | 17/08/2022 | nan | nan | 0 | TK_NotStart | 1391426496 | 1 | 1391426496_1
25863-806070 | TT_Task | Trial Run of Vehicle #06 | 15/06/2022 | 06/09/2022 | nan | nan | 0 | TK_NotStart | 1391426496 | 1 | 1391426496_1
25863-807070 | TT_Task | Trial Run of Vehicle #07 | 19/07/2022 | 10/10/2022 | nan | nan | 0 | TK_NotStart | 1391426496 | 1 | 1391426496_1
25863-808070 | TT_Task | Trial Run of Vehicle #08 | 05/08/2022 | 27/10/2022 | nan | nan | 0 | TK_NotStart | 1391426496 | 1 | 1391426496_1
25863-809070 | TT_Task | Trial Run of Vehicle #09 | 23/08/2022 | 14/11/2022 | nan | nan | 0 | TK_NotStart | 1391426496 | 1 | 1391426496_1
25863-810070 | TT_Task | Trial Run of Vehicle #10 | 27/09/2022 | 19/12/2022 | nan | nan | 0 | TK_NotStart | 1391426496 | 2 | 1391426496_2
25863-811070 | TT_Task | Trial Run of Vehicle #11 | 19/10/2022 | 13/12/2022 | nan | nan | 0 | TK_NotStart | 1391426496 | 2 | 1391426496_2
25863-812070 | TT_Task | Trial Run of Vehicle #12 | 02/11/2022 | 27/12/2022 | nan | nan | 0 | TK_NotStart | 1391426496 | 2 | 1391426496_2
25863-813070 | TT_Task | Trial Run of Vehicle #13 | 16/11/2022 | 10/01/2023 | nan | nan | 0 | TK_NotStart | 1391426496 | 2 | 1391426496_2
25863-814070 | TT_Task | Trial Run of Vehicle #14 | 29/11/2022 | 23/01/2023 | nan | nan | 0 | TK_NotStart | 1391426496 | 2 | 1391426496_2
25863-815070 | TT_Task | Trial Run of Vehicle #15 | 09/12/2022 | 02/02/2023 | nan | nan | 0 | TK_NotStart | 1391426496 | 2 | 1391426496_2
25863-816070 | TT_Task | Trial Run of Vehicle #16 | 23/12/2022 | 16/02/2023 | nan | nan | 0 | TK_NotStart | 1391426496 | 2 | 1391426496_2
25863-817070 | TT_Task | Trial Run of Vehicle #17 | 20/01/2023 | 16/03/2023 | nan | nan | 0 | TK_NotStart | 1391426496 | 2 | 1391426496_2
25863-818070 | TT_Task | Trial Run of Vehicle #18 | 01/02/2023 | 28/03/2023 | nan | nan | 0 | TK_NotStart | 1391426496 | 2 | 1391426496_2
25863-819070 | TT_Task | Trial Run of Vehicle #19 | 15/02/2023 | 11/04/2023 | nan | nan | 0 | TK_NotStart | 1391426496 | 2 | 1391426496_2
25863-820070 | TT_Task | Trial Run of Vehicle #20 | 27/02/2023 | 21/04/2023 | nan | nan | 0 | TK_NotStart | 1391426496 | 2 | 1391426496_2
25863-821070 | TT_Task | Trial Run of Vehicle #21 | 09/03/2023 | 03/05/2023 | nan | nan | 0 | TK_NotStart | 1391426496 | 2 | 1391426496_2
25863-822070 | TT_Task | Trial Run of Vehicle #22 | 17/04/2023 | 09/06/2023 | nan | nan | 0 | TK_NotStart | 1391426496 | 2 | 1391426496_2
25863-823070 | TT_Task | Trial Run of Vehicle #23 | 05/04/2023 | 30/05/2023 | nan | nan | 0 | TK_NotStart | 1391426496 | 2 | 1391426496_2
25863-824070 | TT_Task | Trial Run of Vehicle #24 | 07/04/2023 | 01/06/2023 | nan | nan | 0 | TK_NotStart | 1391426496 | 2 | 1391426496_2
25863-825070 | TT_Task | Trial Run of Vehicle #25 | 14/04/2023 | 08/06/2023 | nan | nan | 0 | TK_NotStart | 1391426496 | 2 | 1391426496_2
25863-826070 | TT_Task | Trial Run of Vehicle #26 | 26/04/2023 | 23/05/2023 | nan | nan | 0 | TK_NotStart | 1391426496 | 2 | 1391426496_2
25863-827070 | TT_Task | Trial Run of Vehicle #27 | 09/05/2023 | 05/06/2023 | nan | nan | 0 | TK_NotStart | 1391426496 | 2 | 1391426496_2
25863-828070 | TT_Task | Trial Run of Vehicle #28 | 23/05/2023 | 19/06/2023 | nan | nan | 0 | TK_NotStart | 1391426496 | 2 | 1391426496_2
25863-829070 | TT_Task | Trial Run of Vehicle #29 | 02/06/2023 | 29/06/2023 | nan | nan | 0 | TK_NotStart | 1391426496 | 2 | 1391426496_2
25863-830070 | TT_Task | Trial Run of Vehicle #30 | 14/06/2023 | 11/07/2023 | nan | nan | 0 | TK_NotStart | 1391426496 | 2 | 1391426496_2
25863-802010 | TT_Task | Fitout 2 HZA #02 | 04/06/2021 | 22/09/2021 | 07/06/2021 | 29/10/2021 | 0 | TK_Complete | 1391426496 | 3 | 1391426496_3
25863-803010 | TT_Task | Fitout 2 HZA #03 | 26/10/2021 | 29/11/2021 | 26/10/2021 | nan | 0 | TK_Active | 1391426496 | 3 | 1391426496_3
25863-803020 | TT_Task | E-Pr?fung, stat./dyn. IBS BZ #03 | 07/02/2022 | 04/03/2022 | nan | nan | 0 | TK_NotStart | 1391426496 | 4 | 1391426496_4
25863-803040 | TT_Task | Transport to Customer of Vehicle #03 | 21/03/2022 | 22/03/2022 | nan | nan | 0 | TK_NotStart | 1391426496 | 5 | 1391426496_5
25863-804010 | TT_Task | Fitout 2 HZA #04 | 13/10/2021 | 10/12/2021 | 03/12/2021 | nan | 0 | TK_Active | 1391426496 | 3 | 1391426496_3
25863-804020 | TT_Task | E-Pr?fung, stat./dyn. IBS BZ #04 | 23/02/2022 | 15/03/2022 | nan | nan | 0 | TK_NotStart | 1391426496 | 4 | 1391426496_4
25863-804040 | TT_Task | Transport to Customer of Vehicle #04 | 30/03/2022 | 31/03/2022 | nan | nan | 0 | TK_NotStart | 1391426496 | 5 | 1391426496_5
25863-805010 | TT_Task | Fitout 2 HZA #05 | 06/12/2021 | 17/02/2022 | 06/12/2021 | nan | 0 | TK_Active | 1391426496 | 3 | 1391426496_3
25863-805020 | TT_Task | E-Pr?fung, stat./dyn. IBS BZ #05 | 21/03/2022 | 06/04/2022 | nan | nan | 0 | TK_NotStart | 1391426496 | 4 | 1391426496_4
25863-805040 | TT_Task | Transport to Customer of Vehicle #05 | 25/04/2022 | 26/04/2022 | nan | nan | 0 | TK_NotStart | 1391426496 | 5 | 1391426496_5
25863-806010 | TT_Task | Fitout 2 HZA #06 | 01/02/2022 | 07/04/2022 | nan | nan | 0 | TK_NotStart | 1391426496 | 3 | 1391426496_3
25863-806020 | TT_Task | E-Pr?fung, stat./dyn. IBS BZ #06 | 08/04/2022 | 25/04/2022 | nan | nan | 0 | TK_NotStart | 1391426496 | 4 | 1391426496_4
25863-806040 | TT_Task | Transport to Customer of Vehicle #06 | 10/05/2022 | 11/05/2022 | nan | nan | 0 | TK_NotStart | 1391426496 | 5 | 1391426496_5
25863-807010 | TT_Task | Fitout 2 HZA #07 | 11/03/2022 | 13/05/2022 | nan | nan | 0 | TK_NotStart | 1391426496 | 3 | 1391426496_3
25863-807020 | TT_Task | E-Pr?fung, stat./dyn. IBS BZ #07 | 16/05/2022 | 31/05/2022 | nan | nan | 0 | TK_NotStart | 1391426496 | 4 | 1391426496_4
25863-807040 | TT_Task | Transport to Customer of Vehicle #07 | 16/06/2022 | 17/06/2022 | nan | nan | 0 | TK_NotStart | 1391426496 | 5 | 1391426496_5
25863-808010 | TT_Task | Fitout 2 HZA #08 | 11/04/2022 | 03/06/2022 | nan | nan | 0 | TK_NotStart | 1391426496 | 3 | 1391426496_3
25863-808020 | TT_Task | E-Pr?fung, stat./dyn. IBS BZ #08 | 07/06/2022 | 20/06/2022 | nan | nan | 0 | TK_NotStart | 1391426496 | 4 | 1391426496_4
25863-808040 | TT_Task | Transport to Customer of Vehicle #08 | 05/07/2022 | 06/07/2022 | nan | nan | 0 | TK_NotStart | 1391426496 | 5 | 1391426496_5
25863-809010 | TT_Task | Fitout 2 HZA #09 | 25/04/2022 | 22/06/2022 | nan | nan | 0 | TK_NotStart | 1391426496 | 3 | 1391426496_3
25863-809020 | TT_Task | E-Pr?fung, stat./dyn. IBS BZ #09 | 23/06/2022 | 06/07/2022 | nan | nan | 0 | TK_NotStart | 1391426496 | 4 | 1391426496_4
25863-809040 | TT_Task | Transport to Customer of Vehicle #09 | 21/07/2022 | 22/07/2022 | nan | nan | 0 | TK_NotStart | 1391426496 | 5 | 1391426496_5
25863-810010 | TT_Task | Fitout 2 HZA #10 | 17/05/2022 | 14/07/2022 | nan | nan | 0 | TK_NotStart | 1391426496 | 3 | 1391426496_3
25863-810020 | TT_Task | E-Pr?fung, stat./dyn. IBS BZ #10 | 15/07/2022 | 28/07/2022 | nan | nan | 0 | TK_NotStart | 1391426496 | 4 | 1391426496_4
25863-810040 | TT_Task | Transport to Customer of Vehicle #10 | 25/08/2022 | 26/08/2022 | nan | nan | 0 | TK_NotStart | 1391426496 | 5 | 1391426496_5
25863-811010 | TT_Task | Fitout 2 HZA #11 | 07/06/2022 | 25/07/2022 | nan | nan | 32 | TK_NotStart | 1391426496 | 3 | 1391426496_3
25863-811020 | TT_Task | E-Pr?fung, stat./dyn. IBS BZ #11 | 15/08/2022 | 26/08/2022 | nan | nan | 0 | TK_NotStart | 1391426496 | 4 | 1391426496_4
25863-811040 | TT_Task | Transport to Customer of Vehicle #11 | 15/09/2022 | 16/09/2022 | nan | nan | 0 | TK_NotStart | 1391426496 | 5 | 1391426496_5
25863-812010 | TT_Task | Fitout 2 HZA #12 | 23/06/2022 | 24/08/2022 | nan | nan | 32 | TK_NotStart | 1391426496 | 3 | 1391426496_3
25863-812020 | TT_Task | E-Pr?fung, stat./dyn. IBS BZ #12 | 31/08/2022 | 13/09/2022 | nan | nan | 0 | TK_NotStart | 1391426496 | 4 | 1391426496_4
25863-812040 | TT_Task | Transport to Customer of Vehicle #12 | 28/09/2022 | 29/09/2022 | nan | nan | 0 | TK_NotStart | 1391426496 | 5 | 1391426496_5
25863-813010 | TT_Task | Fitout 2 HZA #13 | 05/07/2022 | 05/09/2022 | nan | nan | 32 | TK_NotStart | 1391426496 | 3 | 1391426496_3
25863-813020 | TT_Task | E-Pr?fung, stat./dyn. IBS BZ #13 | 12/09/2022 | 23/09/2022 | nan | nan | 0 | TK_NotStart | 1391426496 | 4 | 1391426496_4
25863-813040 | TT_Task | Transport to Customer of Vehicle #13 | 13/10/2022 | 14/10/2022 | nan | nan | 0 | TK_NotStart | 1391426496 | 5 | 1391426496_5
25863-814010 | TT_Task | Fitout 2 HZA #14 | 15/07/2022 | 19/09/2022 | nan | nan | 32 | TK_NotStart | 1391426496 | 3 | 1391426496_3
25863-814020 | TT_Task | E-Pr?fung, stat./dyn. IBS BZ #14 | 26/09/2022 | 10/10/2022 | nan | nan | 0 | TK_NotStart | 1391426496 | 4 | 1391426496_4
25863-814040 | TT_Task | Transport to Customer of Vehicle #14 | 25/10/2022 | 26/10/2022 | nan | nan | 0 | TK_NotStart | 1391426496 | 5 | 1391426496_5
25863-815010 | TT_Task | Fitout 2 HZA #15 | 27/07/2022 | 29/09/2022 | nan | nan | 32 | TK_NotStart | 1391426496 | 3 | 1391426496_3
25863-815020 | TT_Task | E-Pr?fung, stat./dyn. IBS BZ #15 | 07/10/2022 | 20/10/2022 | nan | nan | 0 | TK_NotStart | 1391426496 | 4 | 1391426496_4
25863-815040 | TT_Task | Transport to Customer of Vehicle #15 | 07/11/2022 | 08/11/2022 | nan | nan | 0 | TK_NotStart | 1391426496 | 5 | 1391426496_5
25863-816010 | TT_Task | Fitout 2 HZA #16 | 25/08/2022 | 14/10/2022 | nan | nan | 32 | TK_NotStart | 1391426496 | 3 | 1391426496_3
25863-816020 | TT_Task | E-Pr?fung, stat./dyn. IBS BZ #16 | 21/10/2022 | 04/11/2022 | nan | nan | 0 | TK_NotStart | 1391426496 | 4 | 1391426496_4
25863-816040 | TT_Task | Transport to Customer of Vehicle #16 | 22/11/2022 | 23/11/2022 | nan | nan | 0 | TK_NotStart | 1391426496 | 5 | 1391426496_5
25863-817010 | TT_Task | Fitout 2 HZA #17 | 19/09/2022 | 09/11/2022 | nan | nan | 32 | TK_NotStart | 1391426496 | 3 | 1391426496_3
25863-817020 | TT_Task | E-Pr?fung, stat./dyn. IBS BZ #17 | 17/11/2022 | 29/11/2022 | nan | nan | 0 | TK_NotStart | 1391426496 | 4 | 1391426496_4
25863-817040 | TT_Task | Transport to Customer of Vehicle #17 | 13/12/2022 | 14/12/2022 | nan | nan | 0 | TK_NotStart | 1391426496 | 5 | 1391426496_5
25863-818010 | TT_Task | Fitout 2 HZA #18 | 29/09/2022 | 22/11/2022 | nan | nan | 32 | TK_NotStart | 1391426496 | 3 | 1391426496_3
25863-818020 | TT_Task | E-Pr?fung, stat./dyn. IBS BZ #18 | 29/11/2022 | 09/12/2022 | nan | nan | 0 | TK_NotStart | 1391426496 | 4 | 1391426496_4
25863-818040 | TT_Task | Transport to Customer of Vehicle #18 | 23/12/2022 | 02/01/2023 | nan | nan | 0 | TK_NotStart | 1391426496 | 5 | 1391426496_5
25863-819010 | TT_Task | Fitout 2 HZA #19 | 12/10/2022 | 02/12/2022 | nan | nan | 32 | TK_NotStart | 1391426496 | 3 | 1391426496_3
25863-819020 | TT_Task | E-Pr?fung, stat./dyn. IBS BZ #19 | 09/12/2022 | 22/12/2022 | nan | nan | 0 | TK_NotStart | 1391426496 | 4 | 1391426496_4
25863-819040 | TT_Task | Transport to Customer of Vehicle #19 | 13/01/2023 | 16/01/2023 | nan | nan | 0 | TK_NotStart | 1391426496 | 5 | 1391426496_5
25863-820010 | TT_Task | Fitout 2 HZA #20 | 24/10/2022 | 14/12/2022 | nan | nan | 32 | TK_NotStart | 1391426496 | 3 | 1391426496_3
25863-820020 | TT_Task | E-Pr?fung, stat./dyn. IBS BZ #20 | 21/12/2022 | 10/01/2023 | nan | nan | 0 | TK_NotStart | 1391426496 | 4 | 1391426496_4
25863-820040 | TT_Task | Transport to Customer of Vehicle #20 | 25/01/2023 | 26/01/2023 | nan | nan | 0 | TK_NotStart | 1391426496 | 5 | 1391426496_5
25863-821010 | TT_Task | Fitout 2 HZA #21 | 04/11/2022 | 02/01/2023 | nan | nan | 32 | TK_NotStart | 1391426496 | 3 | 1391426496_3
25863-821020 | TT_Task | E-Pr?fung, stat./dyn. IBS BZ #21 | 09/01/2023 | 20/01/2023 | nan | nan | 0 | TK_NotStart | 1391426496 | 4 | 1391426496_4
25863-821040 | TT_Task | Transport to Customer of Vehicle #21 | 06/02/2023 | 07/02/2023 | nan | nan | 0 | TK_NotStart | 1391426496 | 5 | 1391426496_5
25863-822010 | TT_Task | Fitout 2 HZA #22 | 07/09/2022 | 27/10/2022 | nan | nan | 32 | TK_NotStart | 1391426496 | 3 | 1391426496_3
25863-822020 | TT_Task | E-Pr?fung, stat./dyn. IBS BZ #22 | 04/11/2022 | 23/12/2022 | nan | nan | 0 | TK_NotStart | 1391426496 | 4 | 1391426496_4
25863-822040 | TT_Task | Transport to Customer of Vehicle #22 | 23/01/2023 | 24/01/2023 | nan | nan | 0 | TK_NotStart | 1391426496 | 5 | 1391426496_5
25863-823010 | TT_Task | Fitout 2 HZA #23 | 17/11/2022 | 12/01/2023 | nan | nan | 32 | TK_NotStart | 1391426496 | 3 | 1391426496_3
25863-823020 | TT_Task | E-Pr?fung, stat./dyn. IBS BZ #23 | 19/01/2023 | 15/02/2023 | nan | nan | 0 | TK_NotStart | 1391426496 | 4 | 1391426496_4
25863-823040 | TT_Task | Transport to Customer of Vehicle #23 | 03/03/2023 | 06/03/2023 | nan | nan | 0 | TK_NotStart | 1391426496 | 5 | 1391426496_5
25863-824010 | TT_Task | Fitout 2 HZA #24 | 29/11/2022 | 24/01/2023 | nan | nan | 32 | TK_NotStart | 1391426496 | 3 | 1391426496_3
25863-824020 | TT_Task | E-Pr?fung, stat./dyn. IBS BZ #24 | 31/01/2023 | 20/02/2023 | nan | nan | 0 | TK_NotStart | 1391426496 | 4 | 1391426496_4
25863-824040 | TT_Task | Transport to Customer of Vehicle #24 | 07/03/2023 | 08/03/2023 | nan | nan | 0 | TK_NotStart | 1391426496 | 5 | 1391426496_5
25863-825010 | TT_Task | Fitout 2 HZA #25 | 09/12/2022 | 03/02/2023 | nan | nan | 32 | TK_NotStart | 1391426496 | 3 | 1391426496_3
25863-825020 | TT_Task | E-Pr?fung, stat./dyn. IBS BZ #25 | 10/02/2023 | 23/02/2023 | nan | nan | 0 | TK_NotStart | 1391426496 | 4 | 1391426496_4
25863-825040 | TT_Task | Transport to Customer of Vehicle #25 | 10/03/2023 | 13/03/2023 | nan | nan | 0 | TK_NotStart | 1391426496 | 5 | 1391426496_5
25863-826010 | TT_Task | Fitout 2 HZA #26 | 21/12/2022 | 15/02/2023 | nan | nan | 32 | TK_NotStart | 1391426496 | 3 | 1391426496_3
25863-826020 | TT_Task | E-Pr?fung, stat./dyn. IBS BZ #26 | 22/02/2023 | 07/03/2023 | nan | nan | 0 | TK_NotStart | 1391426496 | 4 | 1391426496_4
25863-826040 | TT_Task | Transport to Customer of Vehicle #26 | 22/03/2023 | 23/03/2023 | nan | nan | 0 | TK_NotStart | 1391426496 | 5 | 1391426496_5
25863-827010 | TT_Task | Fitout 2 HZA #27 | 09/01/2023 | 27/02/2023 | nan | nan | 32 | TK_NotStart | 1391426496 | 3 | 1391426496_3
25863-827020 | TT_Task | E-Pr?fung, stat./dyn. IBS BZ #27 | 06/03/2023 | 17/03/2023 | nan | nan | 0 | TK_NotStart | 1391426496 | 4 | 1391426496_4
25863-827040 | TT_Task | Transport to Customer of Vehicle #27 | 03/04/2023 | 04/04/2023 | nan | nan | 0 | TK_NotStart | 1391426496 | 5 | 1391426496_5
25863-828010 | TT_Task | Fitout 2 HZA #28 | 19/01/2023 | 09/03/2023 | nan | nan | 32 | TK_NotStart | 1391426496 | 3 | 1391426496_3
25863-828020 | TT_Task | E-Pr?fung, stat./dyn. IBS BZ #28 | 16/03/2023 | 29/03/2023 | nan | nan | 0 | TK_NotStart | 1391426496 | 4 | 1391426496_4
25863-828040 | TT_Task | Transport to Customer of Vehicle #28 | 17/04/2023 | 18/04/2023 | nan | nan | 0 | TK_NotStart | 1391426496 | 5 | 1391426496_5
25863-829010 | TT_Task | Fitout 2 HZA #29 | 31/01/2023 | 21/03/2023 | nan | nan | 32 | TK_NotStart | 1391426496 | 3 | 1391426496_3
25863-829020 | TT_Task | E-Pr?fung, stat./dyn. IBS BZ #29 | 28/03/2023 | 12/04/2023 | nan | nan | 0 | TK_NotStart | 1391426496 | 4 | 1391426496_4
25863-829040 | TT_Task | Transport to Customer of Vehicle #29 | 26/04/2023 | 27/04/2023 | nan | nan | 0 | TK_NotStart | 1391426496 | 5 | 1391426496_5
25863-830010 | TT_Task | Fitout 2 HZA #30 | 10/02/2023 | 31/03/2023 | nan | nan | 32 | TK_NotStart | 1391426496 | 3 | 1391426496_3
25863-830020 | TT_Task | E-Pr?fung, stat./dyn. IBS BZ #30 | 11/04/2023 | 24/04/2023 | nan | nan | 0 | TK_NotStart | 1391426496 | 4 | 1391426496_4
25863-830040 | TT_Task | Transport to Customer of Vehicle #30 | 09/05/2023 | 10/05/2023 | nan | nan | 0 | TK_NotStart | 1391426496 | 5 | 1391426496_5
25863-409058 | TT_Task | Bogies - Shipment and the 1st Delivery | 18/05/2021 | 18/05/2021 | 04/05/2021 | 04/05/2021 | 0 | TK_Complete | 1391426496 | 6 | 1391426496_6
25863-801010 | TT_Task | Fitout 1 HZA WT1 #01 | 10/12/2020 | 03/02/2021 | 18/12/2020 | 11/02/2021 | 0 | TK_Complete | 1391426496 | 7 | 1391426496_7
25863-802000 | TT_Task | Rohbau inkl. Oberfl?che HZA #02 | 27/10/2020 | 26/03/2021 | 27/10/2020 | 28/04/2021 | 0 | TK_Complete | 1391426496 | 8 | 1391426496_8
25863-803000 | TT_Task | Rohbau inkl. Oberfl?che HZA #03 | 10/12/2020 | 30/06/2021 | 10/12/2020 | 28/09/2021 | 0 | TK_Complete | 1391426496 | 8 | 1391426496_8
25863-804000 | TT_Task | Rohbau inkl. Oberfl?che HZA #04 | 07/06/2021 | 10/09/2021 | 07/06/2021 | 26/08/2021 | 0 | TK_Complete | 1391426496 | 8 | 1391426496_8
25863-805000 | TT_Task | Rohbau inkl. Oberfl?che HZA #05 | 02/07/2021 | 29/09/2021 | 02/07/2021 | 11/10/2021 | 0 | TK_Complete | 1391426496 | 8 | 1391426496_8
25863-806000 | TT_Task | Rohbau inkl. Oberfl?che HZA #06 | 15/07/2021 | 22/10/2021 | 15/07/2021 | 26/11/2021 | 0 | TK_Complete | 1391426496 | 8 | 1391426496_8
25863-807000 | TT_Task | Rohbau inkl. Oberfl?che HZA #07 | 26/08/2021 | 01/11/2021 | 26/08/2021 | nan | 0 | TK_Active | 1391426496 | 8 | 1391426496_8
25863-808000 | TT_Task | Rohbau inkl. Oberfl?che HZA #08 | 17/09/2021 | 18/11/2021 | 17/09/2021 | nan | 0 | TK_Active | 1391426496 | 8 | 1391426496_8
25863-809000 | TT_Task | Rohbau inkl. Oberfl?che HZA #09 | 13/10/2021 | 06/12/2021 | 13/10/2021 | nan | 0 | TK_Active | 1391426496 | 8 | 1391426496_8
25863-810000 | TT_Task | Rohbau inkl. Oberfl?che HZA #10 | 24/01/2022 | 28/04/2022 | nan | nan | 0 | TK_NotStart | 1391426496 | 8 | 1391426496_8
25863-811000 | TT_Task | Rohbau inkl. Oberfl?che HZA #11 | 07/02/2022 | 16/05/2022 | nan | nan | 0 | TK_NotStart | 1391426496 | 8 | 1391426496_8
25863-812000 | TT_Task | Rohbau inkl. Oberfl?che HZA #12 | 21/02/2022 | 03/06/2022 | nan | nan | 0 | TK_NotStart | 1391426496 | 8 | 1391426496_8
25863-813000 | TT_Task | Rohbau inkl. Oberfl?che HZA #13 | 07/03/2022 | 16/06/2022 | nan | nan | 0 | TK_NotStart | 1391426496 | 8 | 1391426496_8
25863-814000 | TT_Task | Rohbau inkl. Oberfl?che HZA #14 | 21/03/2022 | 28/06/2022 | nan | nan | 0 | TK_NotStart | 1391426496 | 8 | 1391426496_8
25863-815000 | TT_Task | Rohbau inkl. Oberfl?che HZA #15 | 04/04/2022 | 08/07/2022 | nan | nan | 0 | TK_NotStart | 1391426496 | 8 | 1391426496_8
25863-816000 | TT_Task | Rohbau inkl. Oberfl?che HZA #16 | 20/04/2022 | 25/07/2022 | nan | nan | 0 | TK_NotStart | 1391426496 | 8 | 1391426496_8
25863-817000 | TT_Task | Rohbau inkl. Oberfl?che HZA #17 | 18/05/2022 | 31/08/2022 | nan | nan | 0 | TK_NotStart | 1391426496 | 8 | 1391426496_8
25863-818000 | TT_Task | Rohbau inkl. Oberfl?che HZA #18 | 06/05/2022 | 12/09/2022 | nan | nan | 0 | TK_NotStart | 1391426496 | 8 | 1391426496_8
25863-819000 | TT_Task | Rohbau inkl. Oberfl?che HZA #19 | 17/05/2022 | 22/09/2022 | nan | nan | 0 | TK_NotStart | 1391426496 | 8 | 1391426496_8
25863-820000 | TT_Task | Rohbau inkl. Oberfl?che HZA #20 | 01/06/2022 | 05/10/2022 | nan | nan | 0 | TK_NotStart | 1391426496 | 8 | 1391426496_8
25863-821000 | TT_Task | Rohbau inkl. Oberfl?che HZA #21 | 15/06/2022 | 17/10/2022 | nan | nan | 0 | TK_NotStart | 1391426496 | 8 | 1391426496_8
25863-822000 | TT_Task | Rohbau inkl. Oberfl?che HZA #22 | 04/05/2022 | 17/08/2022 | nan | nan | 0 | TK_NotStart | 1391426496 | 8 | 1391426496_8
25863-823000 | TT_Task | Rohbau inkl. Oberfl?che HZA #23 | 15/07/2022 | 25/10/2022 | nan | nan | 0 | TK_NotStart | 1391426496 | 8 | 1391426496_8
25863-824000 | TT_Task | Rohbau inkl. Oberfl?che HZA #24 | 27/07/2022 | 07/11/2022 | nan | nan | 0 | TK_NotStart | 1391426496 | 8 | 1391426496_8
25863-825000 | TT_Task | Rohbau inkl. Oberfl?che HZA #25 | 24/08/2022 | 22/11/2022 | nan | nan | 0 | TK_NotStart | 1391426496 | 8 | 1391426496_8
25863-826000 | TT_Task | Rohbau inkl. Oberfl?che HZA #26 | 05/09/2022 | 02/12/2022 | nan | nan | 0 | TK_NotStart | 1391426496 | 8 | 1391426496_8
25863-827000 | TT_Task | Rohbau inkl. Oberfl?che HZA #27 | 15/09/2022 | 14/12/2022 | nan | nan | 0 | TK_NotStart | 1391426496 | 8 | 1391426496_8
25863-828000 | TT_Task | Rohbau inkl. Oberfl?che HZA #28 | 27/09/2022 | 02/01/2023 | nan | nan | 0 | TK_NotStart | 1391426496 | 8 | 1391426496_8
25863-829000 | TT_Task | Rohbau inkl. Oberfl?che HZA #29 | 10/10/2022 | 12/01/2023 | nan | nan | 0 | TK_NotStart | 1391426496 | 8 | 1391426496_8
25863-830000 | TT_Task | Rohbau inkl. Oberfl?che HZA #30 | 20/10/2022 | 24/01/2023 | nan | nan | 0 | TK_NotStart | 1391426496 | 8 | 1391426496_8
25863-803030 | TT_Task | Factory Handover (Werksabnahme ; Restarbeiten/Werksabnahme) #03 | 07/03/2022 | 18/03/2022 | nan | nan | 0 | TK_NotStart | 1391426496 | 9 | 1391426496_9
25863-803050 | TT_Task | Customer Dynamic Test (including Documentation) #03 | 23/03/2022 | 21/04/2022 | nan | nan | 0 | TK_NotStart | 1391426496 | 10 | 1391426496_10
25863-804030 | TT_Task | Factory Handover (Werksabnahme ; Restarbeiten/Werksabnahme) #04 | 16/03/2022 | 29/03/2022 | nan | nan | 0 | TK_NotStart | 1391426496 | 9 | 1391426496_9
25863-804050 | TT_Task | Customer Dynamic Test (including Documentation) #04 | 01/04/2022 | 02/05/2022 | nan | nan | 0 | TK_NotStart | 1391426496 | 10 | 1391426496_10
25863-805030 | TT_Task | Factory Handover (Werksabnahme ; Restarbeiten/Werksabnahme) #05 | 07/04/2022 | 22/04/2022 | nan | nan | 0 | TK_NotStart | 1391426496 | 9 | 1391426496_9
25863-805050 | TT_Task | Customer Dynamic Test (including Documentation) #05 | 27/04/2022 | 24/05/2022 | nan | nan | 0 | TK_NotStart | 1391426496 | 10 | 1391426496_10
25863-806030 | TT_Task | Factory Handover (Werksabnahme ; Restarbeiten/Werksabnahme) #06 | 26/04/2022 | 09/05/2022 | nan | nan | 0 | TK_NotStart | 1391426496 | 9 | 1391426496_9
25863-806050 | TT_Task | Customer Dynamic Test (including Documentation) #06 | 12/05/2022 | 13/06/2022 | nan | nan | 0 | TK_NotStart | 1391426496 | 10 | 1391426496_10
25863-807030 | TT_Task | Factory Handover (Werksabnahme ; Restarbeiten/Werksabnahme) #07 | 01/06/2022 | 15/06/2022 | nan | nan | 0 | TK_NotStart | 1391426496 | 9 | 1391426496_9
25863-807050 | TT_Task | Customer Dynamic Test (including Documentation) #07 | 20/06/2022 | 15/07/2022 | nan | nan | 0 | TK_NotStart | 1391426496 | 10 | 1391426496_10
25863-808030 | TT_Task | Factory Handover (Werksabnahme ; Restarbeiten/Werksabnahme) #08 | 21/06/2022 | 04/07/2022 | nan | nan | 0 | TK_NotStart | 1391426496 | 9 | 1391426496_9
25863-808050 | TT_Task | Customer Dynamic Test (including Documentation) #08 | 07/07/2022 | 03/08/2022 | nan | nan | 0 | TK_NotStart | 1391426496 | 10 | 1391426496_10
25863-809030 | TT_Task | Factory Handover (Werksabnahme ; Restarbeiten/Werksabnahme) #09 | 07/07/2022 | 20/07/2022 | nan | nan | 0 | TK_NotStart | 1391426496 | 9 | 1391426496_9
25863-809050 | TT_Task | Customer Dynamic Test (including Documentation) #09 | 25/07/2022 | 19/08/2022 | nan | nan | 0 | TK_NotStart | 1391426496 | 10 | 1391426496_10
25863-810030 | TT_Task | Factory Handover (Werksabnahme ; Restarbeiten/Werksabnahme) #10 | 29/07/2022 | 24/08/2022 | nan | nan | 0 | TK_NotStart | 1391426496 | 9 | 1391426496_9
25863-810050 | TT_Task | Customer Dynamic Test (including Documentation) #10 | 29/08/2022 | 23/09/2022 | nan | nan | 0 | TK_NotStart | 1391426496 | 10 | 1391426496_10
25863-811030 | TT_Task | Factory Handover (Werksabnahme ; Restarbeiten/Werksabnahme) #11 | 29/08/2022 | 14/09/2022 | nan | nan | 0 | TK_NotStart | 1391426496 | 9 | 1391426496_9
25863-811050 | TT_Task | Customer Dynamic Test (including Documentation) #11 | 19/09/2022 | 17/10/2022 | nan | nan | 0 | TK_NotStart | 1391426496 | 10 | 1391426496_10
25863-812030 | TT_Task | Factory Handover (Werksabnahme ; Restarbeiten/Werksabnahme) #12 | 14/09/2022 | 27/09/2022 | nan | nan | 0 | TK_NotStart | 1391426496 | 9 | 1391426496_9
25863-812050 | TT_Task | Customer Dynamic Test (including Documentation) #12 | 30/09/2022 | 28/10/2022 | nan | nan | 0 | TK_NotStart | 1391426496 | 10 | 1391426496_10
25863-813030 | TT_Task | Factory Handover (Werksabnahme ; Restarbeiten/Werksabnahme) #13 | 26/09/2022 | 12/10/2022 | nan | nan | 0 | TK_NotStart | 1391426496 | 9 | 1391426496_9
25863-813050 | TT_Task | Customer Dynamic Test (including Documentation) #13 | 17/10/2022 | 14/11/2022 | nan | nan | 0 | TK_NotStart | 1391426496 | 10 | 1391426496_10
25863-830030 | TT_Task | Factory Handover (Werksabnahme ; Restarbeiten/Werksabnahme) #30 | 25/04/2023 | 08/05/2023 | nan | nan | 0 | TK_NotStart | 1391426496 | 9 | 1391426496_9
25863-830050 | TT_Task | Customer Dynamic Test (including Documentation) #30 | 11/05/2023 | 12/06/2023 | nan | nan | 0 | TK_NotStart | 1391426496 | 10 | 1391426496_10
25863-829030 | TT_Task | Factory Handover (Werksabnahme ; Restarbeiten/Werksabnahme) #29 | 13/04/2023 | 25/04/2023 | nan | nan | 0 | TK_NotStart | 1391426496 | 9 | 1391426496_9
25863-829050 | TT_Task | Customer Dynamic Test (including Documentation) #29 | 28/04/2023 | 31/05/2023 | nan | nan | 0 | TK_NotStart | 1391426496 | 10 | 1391426496_10
25863-828030 | TT_Task | Factory Handover (Werksabnahme ; Restarbeiten/Werksabnahme) #28 | 30/03/2023 | 14/04/2023 | nan | nan | 0 | TK_NotStart | 1391426496 | 9 | 1391426496_9
25863-828050 | TT_Task | Customer Dynamic Test (including Documentation) #28 | 19/04/2023 | 17/05/2023 | nan | nan | 0 | TK_NotStart | 1391426496 | 10 | 1391426496_10
25863-827030 | TT_Task | Factory Handover (Werksabnahme ; Restarbeiten/Werksabnahme) #27 | 20/03/2023 | 31/03/2023 | nan | nan | 0 | TK_NotStart | 1391426496 | 9 | 1391426496_9
25863-827050 | TT_Task | Customer Dynamic Test (including Documentation) #27 | 05/04/2023 | 05/05/2023 | nan | nan | 0 | TK_NotStart | 1391426496 | 10 | 1391426496_10
25863-826030 | TT_Task | Factory Handover (Werksabnahme ; Restarbeiten/Werksabnahme) #26 | 08/03/2023 | 21/03/2023 | nan | nan | 0 | TK_NotStart | 1391426496 | 9 | 1391426496_9
25863-826050 | TT_Task | Customer Dynamic Test (including Documentation) #26 | 24/03/2023 | 24/04/2023 | nan | nan | 0 | TK_NotStart | 1391426496 | 10 | 1391426496_10
25863-825030 | TT_Task | Factory Handover (Werksabnahme ; Restarbeiten/Werksabnahme) #25 | 24/02/2023 | 09/03/2023 | nan | nan | 0 | TK_NotStart | 1391426496 | 9 | 1391426496_9
25863-825050 | TT_Task | Customer Dynamic Test (including Documentation) #25 | 14/03/2023 | 12/04/2023 | nan | nan | 0 | TK_NotStart | 1391426496 | 10 | 1391426496_10
25863-823030 | TT_Task | Factory Handover (Werksabnahme ; Restarbeiten/Werksabnahme) #23 | 16/02/2023 | 02/03/2023 | nan | nan | 0 | TK_NotStart | 1391426496 | 9 | 1391426496_9
25863-823050 | TT_Task | Customer Dynamic Test (including Documentation) #23 | 07/03/2023 | 03/04/2023 | nan | nan | 0 | TK_NotStart | 1391426496 | 10 | 1391426496_10
25863-824030 | TT_Task | Factory Handover (Werksabnahme ; Restarbeiten/Werksabnahme) #24 | 21/02/2023 | 06/03/2023 | nan | nan | 0 | TK_NotStart | 1391426496 | 9 | 1391426496_9
25863-824050 | TT_Task | Customer Dynamic Test (including Documentation) #24 | 09/03/2023 | 05/04/2023 | nan | nan | 0 | TK_NotStart | 1391426496 | 10 | 1391426496_10
25863-822030 | TT_Task | Factory Handover (Werksabnahme ; Restarbeiten/Werksabnahme) #22 | 02/01/2023 | 20/01/2023 | nan | nan | 0 | TK_NotStart | 1391426496 | 9 | 1391426496_9
25863-822050 | TT_Task | Customer Dynamic Test (including Documentation) #22 | 25/01/2023 | 13/04/2023 | nan | nan | 0 | TK_NotStart | 1391426496 | 10 | 1391426496_10
25863-821030 | TT_Task | Factory Handover (Werksabnahme ; Restarbeiten/Werksabnahme) #21 | 23/01/2023 | 03/02/2023 | nan | nan | 0 | TK_NotStart | 1391426496 | 9 | 1391426496_9
25863-821050 | TT_Task | Customer Dynamic Test (including Documentation) #21 | 08/02/2023 | 07/03/2023 | nan | nan | 0 | TK_NotStart | 1391426496 | 10 | 1391426496_10
25863-819030 | TT_Task | Factory Handover (Werksabnahme ; Restarbeiten/Werksabnahme) #19 | 23/12/2022 | 12/01/2023 | nan | nan | 0 | TK_NotStart | 1391426496 | 9 | 1391426496_9
25863-819050 | TT_Task | Customer Dynamic Test (including Documentation) #19 | 17/01/2023 | 13/02/2023 | nan | nan | 0 | TK_NotStart | 1391426496 | 10 | 1391426496_10
25863-820030 | TT_Task | Factory Handover (Werksabnahme ; Restarbeiten/Werksabnahme) #20 | 11/01/2023 | 24/01/2023 | nan | nan | 0 | TK_NotStart | 1391426496 | 9 | 1391426496_9
25863-820050 | TT_Task | Customer Dynamic Test (including Documentation) #20 | 27/01/2023 | 23/02/2023 | nan | nan | 0 | TK_NotStart | 1391426496 | 10 | 1391426496_10
25863-818030 | TT_Task | Factory Handover (Werksabnahme ; Restarbeiten/Werksabnahme) #18 | 12/12/2022 | 22/12/2022 | nan | nan | 0 | TK_NotStart | 1391426496 | 9 | 1391426496_9
25863-818050 | TT_Task | Customer Dynamic Test (including Documentation) #18 | 03/01/2023 | 30/01/2023 | nan | nan | 0 | TK_NotStart | 1391426496 | 10 | 1391426496_10
25863-817030 | TT_Task | Factory Handover (Werksabnahme ; Restarbeiten/Werksabnahme) #17 | 30/11/2022 | 12/12/2022 | nan | nan | 0 | TK_NotStart | 1391426496 | 9 | 1391426496_9
25863-817050 | TT_Task | Customer Dynamic Test (including Documentation) #17 | 15/12/2022 | 18/01/2023 | nan | nan | 0 | TK_NotStart | 1391426496 | 10 | 1391426496_10
25863-816030 | TT_Task | Factory Handover (Werksabnahme ; Restarbeiten/Werksabnahme) #16 | 07/11/2022 | 21/11/2022 | nan | nan | 0 | TK_NotStart | 1391426496 | 9 | 1391426496_9
25863-816050 | TT_Task | Customer Dynamic Test (including Documentation) #16 | 24/11/2022 | 21/12/2022 | nan | nan | 0 | TK_NotStart | 1391426496 | 10 | 1391426496_10
25863-815030 | TT_Task | Factory Handover (Werksabnahme ; Restarbeiten/Werksabnahme) #15 | 21/10/2022 | 04/11/2022 | nan | nan | 0 | TK_NotStart | 1391426496 | 9 | 1391426496_9
25863-815050 | TT_Task | Customer Dynamic Test (including Documentation) #15 | 09/11/2022 | 07/12/2022 | nan | nan | 0 | TK_NotStart | 1391426496 | 10 | 1391426496_10
25863-814030 | TT_Task | Factory Handover (Werksabnahme ; Restarbeiten/Werksabnahme) #14 | 11/10/2022 | 24/10/2022 | nan | nan | 0 | TK_NotStart | 1391426496 | 9 | 1391426496_9
25863-814050 | TT_Task | Customer Dynamic Test (including Documentation) #14 | 27/10/2022 | 25/11/2022 | nan | nan | 0 | TK_NotStart | 1391426496 | 10 | 1391426496_10
25863-801700 | TT_Task | Pr?fung vor Freigabe Probebetrieb #01 | 16/05/2022 | 17/05/2022 | nan | nan | 0 | TK_NotStart | 1391426496 | 11 | 1391426496_11
25863-802060 | TT_Task | Pr?fung vor Freigabe Probebetrieb #02 | 31/05/2022 | 31/05/2022 | nan | nan | 0 | TK_NotStart | 1391426496 | 11 | 1391426496_11
25863-803060 | TT_Task | Pr?fung vor Freigabe Probebetrieb #03 | 22/04/2022 | 22/04/2022 | nan | nan | 127 | TK_NotStart | 1391426496 | 11 | 1391426496_11
25863-804060 | TT_Task | Pr?fung vor Freigabe Probebetrieb #04 | 03/05/2022 | 03/05/2022 | nan | nan | 71 | TK_NotStart | 1391426496 | 11 | 1391426496_11
25863-805060 | TT_Task | Pr?fung vor Freigabe Probebetrieb #05 | 25/05/2022 | 25/05/2022 | nan | nan | 0 | TK_NotStart | 1391426496 | 11 | 1391426496_11
25863-806060 | TT_Task | Pr?fung vor Freigabe Probebetrieb #06 | 14/06/2022 | 14/06/2022 | nan | nan | 0 | TK_NotStart | 1391426496 | 11 | 1391426496_11
25863-807060 | TT_Task | Pr?fung vor Freigabe Probebetrieb #07 | 18/07/2022 | 18/07/2022 | nan | nan | 0 | TK_NotStart | 1391426496 | 11 | 1391426496_11
25863-808060 | TT_Task | Pr?fung vor Freigabe Probebetrieb #08 | 04/08/2022 | 04/08/2022 | nan | nan | 0 | TK_NotStart | 1391426496 | 11 | 1391426496_11
25863-809060 | TT_Task | Pr?fung vor Freigabe Probebetrieb #09 | 22/08/2022 | 22/08/2022 | nan | nan | 0 | TK_NotStart | 1391426496 | 11 | 1391426496_11
25863-810060 | TT_Task | Pr?fung vor Freigabe Probebetrieb #10 | 26/09/2022 | 26/09/2022 | nan | nan | 0 | TK_NotStart | 1391426496 | 11 | 1391426496_11
25863-811060 | TT_Task | Pr?fung vor Freigabe Probebetrieb #11 | 18/10/2022 | 18/10/2022 | nan | nan | 0 | TK_NotStart | 1391426496 | 11 | 1391426496_11
25863-812060 | TT_Task | Pr?fung vor Freigabe Probebetrieb #12 | 01/11/2022 | 01/11/2022 | nan | nan | 0 | TK_NotStart | 1391426496 | 11 | 1391426496_11
25863-813060 | TT_Task | Pr?fung vor Freigabe Probebetrieb #13 | 15/11/2022 | 15/11/2022 | nan | nan | 0 | TK_NotStart | 1391426496 | 11 | 1391426496_11
25863-814060 | TT_Task | Pr?fung vor Freigabe Probebetrieb #14 | 28/11/2022 | 28/11/2022 | nan | nan | 0 | TK_NotStart | 1391426496 | 11 | 1391426496_11
25863-815060 | TT_Task | Pr?fung vor Freigabe Probebetrieb #15 | 08/12/2022 | 08/12/2022 | nan | nan | 0 | TK_NotStart | 1391426496 | 11 | 1391426496_11
25863-816060 | TT_Task | Pr?fung vor Freigabe Probebetrieb #16 | 22/12/2022 | 22/12/2022 | nan | nan | 0 | TK_NotStart | 1391426496 | 11 | 1391426496_11
25863-817060 | TT_Task | Pr?fung vor Freigabe Probebetrieb #17 | 19/01/2023 | 19/01/2023 | nan | nan | 0 | TK_NotStart | 1391426496 | 11 | 1391426496_11
25863-818060 | TT_Task | Pr?fung vor Freigabe Probebetrieb #18 | 31/01/2023 | 31/01/2023 | nan | nan | 0 | TK_NotStart | 1391426496 | 11 | 1391426496_11
25863-819060 | TT_Task | Pr?fung vor Freigabe Probebetrieb #19 | 14/02/2023 | 14/02/2023 | nan | nan | 0 | TK_NotStart | 1391426496 | 11 | 1391426496_11
25863-820060 | TT_Task | Pr?fung vor Freigabe Probebetrieb #20 | 24/02/2023 | 24/02/2023 | nan | nan | 0 | TK_NotStart | 1391426496 | 11 | 1391426496_11
25863-821060 | TT_Task | Pr?fung vor Freigabe Probebetrieb #21 | 08/03/2023 | 08/03/2023 | nan | nan | 0 | TK_NotStart | 1391426496 | 11 | 1391426496_11
25863-822060 | TT_Task | Pr?fung vor Freigabe Probebetrieb #22 | 14/04/2023 | 14/04/2023 | nan | nan | 0 | TK_NotStart | 1391426496 | 11 | 1391426496_11
25863-823060 | TT_Task | Pr?fung vor Freigabe Probebetrieb #23 | 04/04/2023 | 04/04/2023 | nan | nan | 0 | TK_NotStart | 1391426496 | 11 | 1391426496_11
25863-824060 | TT_Task | Pr?fung vor Freigabe Probebetrieb #24 | 06/04/2023 | 06/04/2023 | nan | nan | 0 | TK_NotStart | 1391426496 | 11 | 1391426496_11
25863-825060 | TT_Task | Pr?fung vor Freigabe Probebetrieb #25 | 13/04/2023 | 13/04/2023 | nan | nan | 0 | TK_NotStart | 1391426496 | 11 | 1391426496_11
25863-826060 | TT_Task | Pr?fung vor Freigabe Probebetrieb #26 | 25/04/2023 | 25/04/2023 | nan | nan | 0 | TK_NotStart | 1391426496 | 11 | 1391426496_11
25863-827060 | TT_Task | Pr?fung vor Freigabe Probebetrieb #27 | 08/05/2023 | 08/05/2023 | nan | nan | 0 | TK_NotStart | 1391426496 | 11 | 1391426496_11
25863-828060 | TT_Task | Pr?fung vor Freigabe Probebetrieb #28 | 22/05/2023 | 22/05/2023 | nan | nan | 0 | TK_NotStart | 1391426496 | 11 | 1391426496_11
25863-829060 | TT_Task | Pr?fung vor Freigabe Probebetrieb #29 | 01/06/2023 | 01/06/2023 | nan | nan | 0 | TK_NotStart | 1391426496 | 11 | 1391426496_11
25863-830060 | TT_Task | Pr?fung vor Freigabe Probebetrieb #30 | 13/06/2023 | 13/06/2023 | nan | nan | 0 | TK_NotStart | 1391426496 | 11 | 1391426496_11
25863-204000 | TT_Task | Application for Payment 01 - Notice to Proceed | 23/08/2019 | 02/09/2019 | 23/08/2019 | 02/09/2019 | 0 | TK_Complete | 1391426496 | 12 | 1391426496_12
25863-204010 | TT_Task | Application for Payment 02 - Finalization Pflichtenheft + Delivery MOCKUP + Delivery of doc. pack. A (mono) | 02/12/2019 | 20/12/2019 | 02/12/2019 | 20/12/2019 | 0 | TK_Complete | 1391426496 | 13 | 1391426496_13
25863-204020 | TT_Task | Application for Payment 03 - Delivery of (doc. pack.B), #1 to customer, 1st bogies;spec. tools;cons. stock, 1:32) | 28/02/2022 | 25/03/2022 | 26/11/2021 | 23/12/2021 | 0 | TK_Complete | 1391426496 | 13 | 1391426496_13
25863-204030 | TT_Task | Application for Payment 04 - Delivery of (doc. pack. C (mono); B(bi) + #2 to customer + ) + final acceptance #1 | 11/08/2022 | 07/09/2022 | nan | nan | 16 | TK_NotStart | 1391426496 | 13 | 1391426496_13
25863-204040 | TT_Task | Application for Payment 05 - Auth. appr. for 1st bi-direction + Fin. acc. of #1 to #6 + Del.#15 | 09/11/2022 | 06/12/2022 | nan | nan | 16 | TK_NotStart | 1391426496 | 12 | 1391426496_12
25863-204050 | TT_Task | Application for Payment 06 - Final Acceptance of First Bi-direction Vehicle | 12/06/2023 | 07/07/2023 | nan | nan | 0 | TK_NotStart | 1391426496 | 14 | 1391426496_14
25863-204060 | TT_Task | Application for Payment 07 - Final Acceptance of Last Uni-direction Vehicle | 30/06/2023 | 27/07/2023 | nan | nan | 8 | TK_NotStart | 1391426496 | 14 | 1391426496_14
25863-204070 | TT_Task | Application for Payment 08 - Final Acceptance of Last Bi-direction Vehicle | 18/09/2023 | 13/10/2023 | nan | nan | 0 | TK_NotStart | 1391426496 | 14 | 1391426496_14
25863-171740 | TT_Task | TCMS - Definition of the HW Scope | 06/04/2020 | 15/06/2020 | 22/08/2019 | 28/10/2019 | 0 | TK_Complete | 1391426496 | 15 | 1391426496_15
25863-171750 | TT_Task | TCMS - Procurement of TCMS HW | 29/10/2019 | 23/11/2020 | 29/10/2019 | 14/12/2020 | 0 | TK_Complete | 1391426496 | 15 | 1391426496_15
25863-171760 | TT_Task | TCMS - Delivery of 1st TCMS HW | 14/12/2020 | 18/01/2021 | 14/12/2020 | 19/01/2021 | 0 | TK_Complete | 1391426496 | 15 | 1391426496_15
25863-MOCK100290 | TT_Task | Delivery Mock up to the Customer | 25/11/2019 | 29/11/2019 | 25/11/2019 | 29/11/2019 | 0 | TK_Complete | 1391426496 | 16 | 1391426496_16
25863-MOCK100340 | TT_Task | Presentation to Stakeholders | 02/12/2019 | 13/12/2019 | 02/12/2019 | 13/12/2019 | 0 | TK_Complete | 1391426496 | 17 | 1391426496_17
25863-MOCK100360 | TT_Task | Design Freeze between Mock up Supplier and BT | 09/09/2019 | 13/09/2019 | 09/09/2019 | 13/09/2019 | 0 | TK_Complete | 1391426496 | 18 | 1391426496_18
25863-MOCK100240 | TT_Task | Concept Design (Driver Room, Passenger Compartment) | 27/05/2019 | 19/07/2019 | 27/05/2019 | 19/07/2019 | 0 | TK_Complete | 1391426496 | 19 | 1391426496_19
25863-MOCK100230 | TT_Task | Hold Point | 10/06/2019 | 14/06/2019 | 10/06/2019 | 14/06/2019 | 0 | TK_Complete | 1391426496 | 20 | 1391426496_20
25863-MOCK100220 | TT_Task | NTP (Mock up) | 27/05/2019 | 31/05/2019 | 27/05/2019 | 31/05/2019 | 0 | TK_Complete | 1391426496 | 21 | 1391426496_21
25863-MOCK100310 | TT_Task | Creation of Production Sketches, Detailed Reconciliation | 08/07/2019 | 30/08/2019 | 08/07/2019 | 30/08/2019 | 0 | TK_Complete | 1391426496 | 22 | 1391426496_22
25863-MOCK100300 | TT_Task | Creation of Mock up BOM | 27/05/2019 | 05/07/2019 | 27/05/2019 | 05/07/2019 | 0 | TK_Complete | 1391426496 | 23 | 1391426496_23
25863-MOCK100380 | TT_Task | Design Freeze for Ready for Painting the Mock up | 16/12/2019 | 20/12/2019 | 16/12/2019 | 20/12/2019 | 0 | TK_Complete | 1391426496 | 24 | 1391426496_24
25863-MOCK100370 | TT_Task | Design Freeze Mock up for BGr Construction | 18/11/2019 | 22/11/2019 | 18/11/2019 | 22/11/2019 | 0 | TK_Complete | 1391426496 | 18 | 1391426496_18
25863-MOCK100250 | TT_Task | Creation Mock up, Construction Manual | 08/07/2019 | 13/09/2019 | 08/07/2019 | 13/09/2019 | 0 | TK_Complete | 1391426496 | 25 | 1391426496_25
25863-MOCK100260 | TT_Task | Construction Mock up | 19/08/2019 | 25/10/2019 | 19/08/2019 | 25/10/2019 | 0 | TK_Complete | 1391426496 | 25 | 1391426496_25
25863-MOCK100270 | TT_Task | Interim Acceptance BT, Customer and Mock up - Supplier | 26/08/2019 | 30/08/2019 | 26/08/2019 | 30/08/2019 | 0 | TK_Complete | 1391426496 | 26 | 1391426496_26
25863-MOCK100280 | TT_Task | Acceptance of Mock up by Customers | 21/10/2019 | 25/10/2019 | 21/10/2019 | 25/10/2019 | 0 | TK_Complete | 1391426496 | 16 | 1391426496_16
25863-MOCK100320 | TT_Task | Procurement Material | 17/06/2019 | 04/10/2019 | 17/06/2019 | 04/10/2019 | 0 | TK_Complete | 1391426496 | 27 | 1391426496_27
25863-MOCK100330 | TT_Task | Working Sessions with Customer | 28/10/2019 | 15/11/2019 | 28/10/2019 | 15/11/2019 | 0 | TK_Complete | 1391426496 | 28 | 1391426496_28
25863-MOCK100350 | TT_Task | Design Freeze for Painting the Mock up | 01/07/2019 | 05/07/2019 | 01/07/2019 | 05/07/2019 | 0 | TK_Complete | 1391426496 | 24 | 1391426496_24
25863-MOCK100275 | TT_Task | Interim Acceptance BT, Customer and Mock up - Supplier | 23/09/2019 | 27/09/2019 | 23/09/2019 | 27/09/2019 | 0 | TK_Complete | 1391426496 | 26 | 1391426496_26
25863-801020 | TT_Task | Transport of Shell from Gorlitz to Bautzen of WT1 #01 | 12/02/2021 | 16/02/2021 | 12/02/2021 | 17/02/2021 | 0 | TK_Complete | 1391426496 | 29 | 1391426496_29
25863-801200 | TT_Task | Station F20 of WT1 #01 | 17/02/2021 | 01/03/2021 | 17/02/2021 | 01/03/2021 | 0 | TK_Complete | 1391426496 | 30 | 1391426496_30
25863-801210 | TT_Task | Station F21 of WT1 #01 | 02/03/2021 | 12/03/2021 | 02/03/2021 | 07/07/2021 | 0 | TK_Complete | 1391426496 | 31 | 1391426496_31
25863-801220 | TT_Task | Station F22 (including E-Pr?fung Verkabelung) of WT1 #01 | 15/03/2021 | 24/03/2021 | 15/03/2021 | 07/07/2021 | 0 | TK_Complete | 1391426496 | 32 | 1391426496_32
25863-801230 | TT_Task | Station F23 of WT1 #01 | 25/03/2021 | 01/04/2021 | 25/03/2021 | 07/07/2021 | 0 | TK_Complete | 1391426496 | 31 | 1391426496_31
25863-801090 | TT_Task | Transport of Shell from Gorlitz to Bautzen of WT4 #01 | 08/04/2021 | 09/04/2021 | 08/04/2021 | 09/04/2021 | 0 | TK_Complete | 1391426496 | 29 | 1391426496_29
25863-801520 | TT_Task | Station F20 of WT4 #01 | 12/04/2021 | 19/04/2021 | 12/04/2021 | 18/05/2021 | 0 | TK_Complete | 1391426496 | 30 | 1391426496_30
25863-801530 | TT_Task | Station F21 of WT4 #01 | 20/04/2021 | 26/04/2021 | 20/04/2021 | 07/07/2021 | 0 | TK_Complete | 1391426496 | 31 | 1391426496_31
25863-801540 | TT_Task | Station F22 (including E-Pr?fung Verkabelung) of WT4 #01 | 27/04/2021 | 06/05/2021 | 27/04/2021 | 07/07/2021 | 0 | TK_Complete | 1391426496 | 32 | 1391426496_32
25863-801550 | TT_Task | Station F23 of WT4 #01 | 07/05/2021 | 17/05/2021 | 07/05/2021 | 07/07/2021 | 0 | TK_Complete | 1391426496 | 31 | 1391426496_31
25863-801060 | TT_Task | Fitout 1 HZB WT3 #01 | 08/03/2021 | 25/03/2021 | 05/03/2021 | 05/04/2021 | 0 | TK_Complete | 1391426496 | 7 | 1391426496_7
25863-801590 | TT_Task | Station F27 of WT4 #01 | 22/06/2021 | 29/06/2021 | 22/06/2021 | 07/07/2021 | 0 | TK_Complete | 1391426496 | 31 | 1391426496_31
25863-602110 | TT_Task | SD WT1 WS F21 - MBOM Implementation, Logistics Preparation, C Parts Lead Time, Tooling Definition, Fabrication, Installa | 26/10/2020 | 29/01/2021 | 26/10/2020 | 29/01/2021 | 0 | TK_Complete | 1391426496 | 33 | 1391426496_33
25863-602210 | TT_Task | SD WT1 WS F22 - MBOM Implementation, Logistics Preparation, C Parts Lead Time, Tooling Definition, Fabrication, Installa | 18/11/2020 | 23/02/2021 | 18/11/2020 | 29/01/2021 | 0 | TK_Complete | 1391426496 | 33 | 1391426496_33
25863-902010 | TT_Task | Warranty Period of the Last Train for Field Technical Support (Base Order) | 11/07/2023 | 09/07/2026 | nan | nan | 0 | TK_NotStart | 1391426496 | 34 | 1391426496_34
25863-801005 | TT_Task | Carbody Production HZA WT1 #01 | 08/09/2020 | 13/01/2021 | 08/09/2020 | 17/12/2020 | 0 | TK_Complete | 1391426496 | 35 | 1391426496_35
25863-801055 | TT_Task | Carbody Production HZB WT3 #01 | 28/10/2020 | 03/02/2021 | 26/10/2020 | 04/03/2021 | 0 | TK_Complete | 1391426496 | 35 | 1391426496_35
25863-602010 | TT_Task | SD WT1 WS F20 - MBOM Implementation, Logistics Preparation, C Parts Lead Time, Tooling Definition, Fabrication, Installa | 26/10/2020 | 29/01/2021 | 26/10/2020 | 08/01/2021 | 0 | TK_Complete | 1391426496 | 33 | 1391426496_33
25863-602310 | TT_Task | SD WT1 WS F23 - MBOM Implementation, Logistics Preparation, C Parts Lead Time, Tooling Definition, Fabrication, Installa | 11/01/2021 | 19/02/2021 | 11/01/2021 | 16/03/2021 | 0 | TK_Complete | 1391426496 | 36 | 1391426496_36
25863-801240 | TT_Task | Station F24 of WT1 #01 | 06/04/2021 | 21/04/2021 | 06/04/2021 | 07/07/2021 | 0 | TK_Complete | 1391426496 | 31 | 1391426496_31
25863-801250 | TT_Task | Station F25 (E-Pr?fung Ger?te) of WT1 #01 | 22/04/2021 | 11/05/2021 | 22/04/2021 | 07/07/2021 | 0 | TK_Complete | 1391426496 | 37 | 1391426496_37
25863-801260 | TT_Task | Station F26 of WT1 #01 | 12/05/2021 | 31/05/2021 | 12/05/2021 | 07/07/2021 | 0 | TK_Complete | 1391426496 | 38 | 1391426496_38
25863-801270 | TT_Task | Station F27 of WT1 #01 | 04/06/2021 | 29/06/2021 | 04/06/2021 | 07/07/2021 | 0 | TK_Complete | 1391426496 | 31 | 1391426496_31
25863-801280 | TT_Task | Station F20 of WT3 #01 | 08/04/2021 | 15/04/2021 | 08/04/2021 | 07/07/2021 | 0 | TK_Complete | 1391426496 | 30 | 1391426496_30
25863-801290 | TT_Task | Station F21 of WT3 #01 | 16/04/2021 | 22/04/2021 | 16/04/2021 | 07/07/2021 | 0 | TK_Complete | 1391426496 | 31 | 1391426496_31
25863-801300 | TT_Task | Station F22 (including E-Pr?fung Verkabelung) of WT3 #01 | 28/04/2021 | 07/05/2021 | 28/04/2021 | 07/07/2021 | 0 | TK_Complete | 1391426496 | 32 | 1391426496_32
25863-801310 | TT_Task | Station F23 of WT3 #01 | 10/05/2021 | 18/05/2021 | 10/05/2021 | 07/07/2021 | 0 | TK_Complete | 1391426496 | 31 | 1391426496_31
25863-801320 | TT_Task | Station F24 of WT3 #01 | 19/05/2021 | 27/05/2021 | 19/05/2021 | 07/07/2021 | 0 | TK_Complete | 1391426496 | 31 | 1391426496_31
25863-801330 | TT_Task | Station F25 (E-Pr?fung Ger?te) of WT3 #01 | 28/05/2021 | 11/06/2021 | 28/05/2021 | 07/07/2021 | 0 | TK_Complete | 1391426496 | 37 | 1391426496_37
25863-801340 | TT_Task | Station F26 of WT3 #01 | 14/06/2021 | 23/06/2021 | 14/06/2021 | 07/07/2021 | 0 | TK_Complete | 1391426496 | 38 | 1391426496_38
25863-801350 | TT_Task | Station F27 of WT3 #01 | 24/06/2021 | 29/06/2021 | 24/06/2021 | 07/07/2021 | 0 | TK_Complete | 1391426496 | 31 | 1391426496_31
25863-801360 | TT_Task | Station F20 of WT5 #01 | 09/03/2021 | 18/03/2021 | 09/03/2021 | 18/05/2021 | 0 | TK_Complete | 1391426496 | 30 | 1391426496_30
25863-801370 | TT_Task | Station F21 of WT5 #01 | 19/03/2021 | 30/03/2021 | 19/03/2021 | 07/07/2021 | 0 | TK_Complete | 1391426496 | 31 | 1391426496_31
25863-801380 | TT_Task | Station F22 (including E-Pr?fung Verkabelung) of WT5 #01 | 31/03/2021 | 15/04/2021 | 31/03/2021 | 07/07/2021 | 0 | TK_Complete | 1391426496 | 32 | 1391426496_32
25863-801390 | TT_Task | Station F23 of WT5 #01 | 16/04/2021 | 23/04/2021 | 16/04/2021 | 07/07/2021 | 0 | TK_Complete | 1391426496 | 31 | 1391426496_31
25863-801400 | TT_Task | Station F24 of WT5 #01 | 26/04/2021 | 11/05/2021 | 26/04/2021 | 07/07/2021 | 0 | TK_Complete | 1391426496 | 31 | 1391426496_31
25863-801410 | TT_Task | Station F25 (E-Pr?fung Ger?te) of WT5 #01 | 12/05/2021 | 28/05/2021 | 12/05/2021 | 07/07/2021 | 0 | TK_Complete | 1391426496 | 37 | 1391426496_37
25863-801420 | TT_Task | Station F26 of WT5 #01 | 01/06/2021 | 08/06/2021 | 01/06/2021 | 07/07/2021 | 0 | TK_Complete | 1391426496 | 38 | 1391426496_38
25863-801430 | TT_Task | Station F27 of WT5 #01 | 09/06/2021 | 29/06/2021 | 09/06/2021 | 07/07/2021 | 0 | TK_Complete | 1391426496 | 31 | 1391426496_31
25863-801440 | TT_Task | Station F20 of WT2 #01 | 12/04/2021 | 16/04/2021 | 12/04/2021 | 24/05/2021 | 0 | TK_Complete | 1391426496 | 30 | 1391426496_30
25863-801450 | TT_Task | Station F21 of WT2 #01 | 19/04/2021 | 27/04/2021 | 19/04/2021 | 07/07/2021 | 0 | TK_Complete | 1391426496 | 31 | 1391426496_31
25863-801460 | TT_Task | Station F22 (including E-Pr?fung Verkabelung) of WT2 #01 | 28/04/2021 | 06/05/2021 | 28/04/2021 | 07/07/2021 | 0 | TK_Complete | 1391426496 | 32 | 1391426496_32
25863-801470 | TT_Task | Station F23 of WT2 #01 | 07/05/2021 | 18/05/2021 | 07/05/2021 | 07/07/2021 | 0 | TK_Complete | 1391426496 | 31 | 1391426496_31
25863-801480 | TT_Task | Station F24 of WT2 #01 | 19/05/2021 | 26/05/2021 | 19/05/2021 | 07/07/2021 | 0 | TK_Complete | 1391426496 | 31 | 1391426496_31
25863-801490 | TT_Task | Station F25 (E-Pr?fung Ger?te) of WT2 #01 | 27/05/2021 | 10/06/2021 | 27/05/2021 | 07/07/2021 | 0 | TK_Complete | 1391426496 | 37 | 1391426496_37
25863-801500 | TT_Task | Station F26 of WT2 #01 | 08/06/2021 | 15/06/2021 | 08/06/2021 | 07/07/2021 | 0 | TK_Complete | 1391426496 | 38 | 1391426496_38
25863-801510 | TT_Task | Station F27 of WT2 #01 | 16/06/2021 | 29/06/2021 | 16/06/2021 | 07/07/2021 | 0 | TK_Complete | 1391426496 | 31 | 1391426496_31
25863-801560 | TT_Task | Station F24 of WT4 #01 | 18/05/2021 | 27/05/2021 | 18/05/2021 | 07/07/2021 | 0 | TK_Complete | 1391426496 | 31 | 1391426496_31
25863-801570 | TT_Task | Station F25 (E-Pr?fung Ger?te) of WT4 #01 | 28/05/2021 | 09/06/2021 | 28/05/2021 | 07/07/2021 | 0 | TK_Complete | 1391426496 | 37 | 1391426496_37
25863-801580 | TT_Task | Station F26 of WT4 #01 | 10/06/2021 | 21/06/2021 | 10/06/2021 | 07/07/2021 | 0 | TK_Complete | 1391426496 | 38 | 1391426496_38
25863-801070 | TT_Task | Transport of Shell from Gorlitz to Bautzen of WT3 #01 | 06/04/2021 | 07/04/2021 | 06/04/2021 | 07/04/2021 | 0 | TK_Complete | 1391426496 | 29 | 1391426496_29
25863-801110 | TT_Task | Transport of Shell from Gorlitz to Bautzen of WT5 #01 | 04/03/2021 | 05/03/2021 | 05/03/2021 | 08/03/2021 | 0 | TK_Complete | 1391426496 | 29 | 1391426496_29
25863-801040 | TT_Task | Transport of Shell from Gorlitz to Bautzen of WT2 #01 | 07/04/2021 | 08/04/2021 | 08/04/2021 | 09/04/2021 | 0 | TK_Complete | 1391426496 | 29 | 1391426496_29
25863-602410 | TT_Task | SD WT1 WS F24 - MBOM Implementation, Logistics Preparation, C Parts Lead Time, Tooling Definition, Fabrication, Installa | 13/01/2021 | 26/02/2021 | 13/01/2021 | 05/02/2021 | 0 | TK_Complete | 1391426496 | 33 | 1391426496_33
25863-602510 | TT_Task | SD WT1 WS F25 - MBOM Implementation, Logistics Preparation, C Parts Lead Time, Tooling Definition, Fabrication, Installa | 13/01/2021 | 05/03/2021 | 13/01/2021 | 05/02/2021 | 0 | TK_Complete | 1391426496 | 33 | 1391426496_33
25863-602610 | TT_Task | SD WT1 WS F26 - MBOM Implementation, Logistics Preparation, C Parts Lead Time, Tooling Definition, Fabrication, Installa | 21/09/2020 | 25/12/2020 | 21/09/2020 | 05/02/2021 | 0 | TK_Complete | 1391426496 | 33 | 1391426496_33
25863-602710 | TT_Task | SD WT1 WS F27 - MBOM Implementation, Logistics Preparation, C Parts Lead Time, Tooling Definition, Fabrication, Installa | 22/02/2021 | 26/02/2021 | 22/02/2021 | 26/02/2021 | 0 | TK_Complete | 1391426496 | 33 | 1391426496_33
25863-COVID-00032 | TT_Task | COVID-00032 Nutzung von Catia im Home Office nicht uneingeschr?nkt m?glich (Konstruktion Seitenwand) | 16/03/2020 | 15/04/2020 | 16/03/2020 | 15/04/2020 | 0 | TK_Complete | 1391426496 | 39 | 1391426496_39
25863-COVID-00033 | TT_Task | COVID-00033 Spezielle Blechqualit?ten nicht verf?gbar in Polen (Warenverkehr eingeschr?nkt) | 16/03/2020 | 15/04/2020 | 16/03/2020 | 15/04/2020 | 0 | TK_Complete | 1391426496 | 40 | 1391426496_40
25863-COVID-00034 | TT_Task | COVID-00034 Zwei t?giger WS mit dem Kunden zum Thema DG in Siegen aufgrund der Reiserestriktionen abgesagt | 18/03/2020 | 28/03/2020 | 18/03/2020 | 28/03/2020 | 0 | TK_Complete | 1391426496 | 41 | 1391426496_41
25863-COVID-00044 | TT_Task | COVID-00044 chief engineer ist seit 14.03.2020 in Quarant?ne | 14/03/2020 | 24/03/2020 | 14/03/2020 | 24/03/2020 | 0 | TK_Complete | 1391426496 | 42 | 1391426496_42
25863-COVID-00045 | TT_Task | COVID-00045 Lieferant stellt die Arbeiten ein ab 23.03.2020 | 22/03/2020 | 19/04/2020 | 22/03/2020 | 19/04/2020 | 0 | TK_Complete | 1391426496 | 43 | 1391426496_43
25863-COVID-00046 | TT_Task | COVID-00046 Lock Down Verzug in der Konstruktion und Zeichnungserstellung aller mechanischen Baugruppen | 23/03/2020 | 07/04/2020 | 23/03/2020 | 07/04/2020 | 0 | TK_Complete | 1391426496 | 44 | 1391426496_44
25863-COVID-00047 | TT_Task | COVID-00047 Verschiebung Projekttermin auf Grund der notwendigen Aktionen seitens DVB | 18/03/2020 | 22/03/2020 | 18/03/2020 | 22/03/2020 | 0 | TK_Complete | 1391426496 | 45 | 1391426496_45
25863-COVID-00270 | TT_Task | COVID-00270 Versp?tete Angebotsabgabe Sitze | 22/04/2020 | 02/05/2020 | 22/04/2020 | 02/05/2020 | 0 | TK_Complete | 1391426496 | 46 | 1391426496_46
25863-COVID-00271 | TT_Task | COVID-00271 Versp?tete Angebotsabgabe Fenster | 22/04/2020 | 02/05/2020 | 22/04/2020 | 02/05/2020 | 0 | TK_Complete | 1391426496 | 46 | 1391426496_46
25863-COVID-00272 | TT_Task | COVID-00272 Behinderung einzelner Schl?sselfunktionen bei Bombardier | 22/04/2020 | 22/04/2020 | 22/04/2020 | 22/04/2020 | 0 | TK_Complete | 1391426496 | 47 | 1391426496_47
25863-PROC105100 | TT_Task | Windscreen wiper (Scheibenwischer) - PO Placement and/or Contract (Trigger for Supplier Leadtime) | 07/04/2020 | 24/07/2020 | 07/04/2020 | 10/07/2020 | 0 | TK_Complete | 1391426496 | 48 | 1391426496_48
25863-PROC105110 | TT_Task | Windscreen wiper (Scheibenwischer) - BBI Collection from Supplier | 10/07/2020 | 03/09/2020 | 10/07/2020 | 17/09/2020 | 0 | TK_Complete | 1391426496 | 48 | 1391426496_48
25863-PROC105120 | TT_Task | Windscreen wiper (Scheibenwischer) - Supplier Lead Time | 10/07/2020 | 11/01/2021 | 10/07/2020 | 09/03/2021 | 0 | TK_Complete | 1391426496 | 48 | 1391426496_48
25863-PROC105160 | TT_Task | Backward mirrors (R?ckfahrkamera) - PO Placement and/or Contract (Trigger for Supplier Leadtime) | 15/05/2020 | 30/06/2020 | 15/05/2020 | 31/07/2020 | 0 | TK_Complete | 1391426496 | 49 | 1391426496_49
25863-PROC105180 | TT_Task | Backward mirrors (R?ckfahrkamera) - Supplier Lead Time | 31/07/2020 | 19/11/2020 | 31/07/2020 | 23/02/2021 | 0 | TK_Complete | 1391426496 | 49 | 1391426496_49
25863-PROC105220 | TT_Task | Buffers/draw gears (Energieverzehrelement) - PO Placement and/or Contract (Trigger for Supplier Leadtime) | 04/05/2020 | 10/07/2020 | 04/05/2020 | 27/07/2020 | 0 | TK_Complete | 1391426496 | 50 | 1391426496_50
25863-PROC105230 | TT_Task | Buffers/draw gears (Energieverzehrelement) - BBI Collection from Supplier | 31/07/2020 | 24/09/2020 | 31/07/2020 | 17/09/2020 | 0 | TK_Complete | 1391426496 | 51 | 1391426496_51
25863-PROC105240 | TT_Task | Buffers/draw gears (Energieverzehrelement) - Supplier Lead Time | 31/07/2020 | 31/07/2020 | 31/07/2020 | 05/02/2021 | 0 | TK_Complete | 1391426496 | 52 | 1391426496_52
25863-PROC105280 | TT_Task | Buffers/draw gears (Sto?b?gel) - PO Placement and/or Contract (Trigger for Supplier Leadtime) | 04/05/2020 | 10/08/2020 | 04/05/2020 | 08/02/2021 | 0 | TK_Complete | 1391426496 | 50 | 1391426496_50
25863-PROC105290 | TT_Task | Buffers/draw gears (Sto?b?gel) - BBI Collection from Supplier | 03/08/2020 | 25/09/2020 | 17/09/2020 | 17/09/2020 | 0 | TK_Complete | 1391426496 | 51 | 1391426496_51
25863-PROC105300 | TT_Task | Buffers/draw gears (Sto?b?gel) - Supplier Lead Time | 08/02/2021 | 19/03/2021 | 08/02/2021 | 26/04/2021 | 0 | TK_Complete | 1391426496 | 52 | 1391426496_52
25863-PROC105340 | TT_Task | Gangways (Wellenbalg) - PO Placement and/or Contract (Trigger for Supplier Leadtime) | 20/03/2020 | 10/07/2020 | 20/03/2020 | 10/07/2020 | 0 | TK_Complete | 1391426496 | 53 | 1391426496_53
25863-PROC105360 | TT_Task | Gangways (Wellenbalg) - Supplier Lead Time | 10/07/2020 | 18/01/2021 | 10/07/2020 | 01/03/2021 | 0 | TK_Complete | 1391426496 | 53 | 1391426496_53
25863-PROC105400 | TT_Task | Gangways (Drehscheibe) - PO Placement and/or Contract (Trigger for Supplier Leadtime) | 20/03/2020 | 10/07/2020 | 20/03/2020 | 10/07/2020 | 0 | TK_Complete | 1391426496 | 53 | 1391426496_53
25863-PROC105420 | TT_Task | Gangways (Drehscheibe) - Supplier Lead Time | 10/07/2020 | 18/01/2021 | 10/07/2020 | 01/03/2021 | 0 | TK_Complete | 1391426496 | 53 | 1391426496_53
25863-PROC105460 | TT_Task | Couplers (Kupplung) - PO Placement and/or Contract (Trigger for Supplier Leadtime) | 02/04/2020 | 10/07/2020 | 02/04/2020 | 31/07/2020 | 0 | TK_Complete | 1391426496 | 54 | 1391426496_54
25863-PROC105470 | TT_Task | Couplers (Kupplung) - BBI Collection from Supplier | 31/07/2020 | 24/09/2020 | 31/07/2020 | 17/09/2020 | 0 | TK_Complete | 1391426496 | 55 | 1391426496_55
25863-PROC105480 | TT_Task | Couplers (Kupplung) - Supplier Lead Time | 31/07/2020 | 14/01/2021 | 31/07/2020 | 08/03/2021 | 0 | TK_Complete | 1391426496 | 54 | 1391426496_54
25863-PROC105520 | TT_Task | Body skirts (Fahrzeugsch?rzen) - PO Placement and/or Contract (Trigger for Supplier Leadtime) | 28/05/2020 | 14/09/2020 | 28/05/2020 | 08/10/2020 | 0 | TK_Complete | 1391426496 | 56 | 1391426496_56
25863-PROC105540 | TT_Task | Body skirts (Fahrzeugsch?rzen) - Supplier Lead Time | 08/10/2020 | 24/02/2021 | 08/10/2020 | 30/04/2021 | 0 | TK_Complete | 1391426496 | 56 | 1391426496_56
25863-PROC105580 | TT_Task | Polyester front end (GFK Aussenverkleidung) - PO Placement and/or Contract (Trigger for Supplier Leadtime) | 15/06/2020 | 10/08/2020 | 15/06/2020 | 08/10/2020 | 0 | TK_Complete | 1391426496 | 57 | 1391426496_57
25863-PROC105600 | TT_Task | Polyester front end (GFK Aussenverkleidung) - Supplier Lead Time | 08/10/2020 | 04/01/2021 | 08/10/2020 | 23/03/2021 | 0 | TK_Complete | 1391426496 | 57 | 1391426496_57
25863-PROC105640 | TT_Task | Roof spoiler (Dachblenden) - PO Placement and/or Contract (Trigger for Supplier Leadtime) | 10/06/2020 | 17/08/2020 | 10/06/2020 | 06/10/2020 | 0 | TK_Complete | 1391426496 | 58 | 1391426496_58
25863-PROC105660 | TT_Task | Roof spoiler (Dachblenden) - Supplier Lead Time | 06/10/2020 | 04/01/2021 | 06/10/2020 | 24/03/2021 | 0 | TK_Complete | 1391426496 | 58 | 1391426496_58
25863-PROC105700 | TT_Task | Bogie fittings (Sandung) - PO Placement and/or Contract (Trigger for Supplier Leadtime) | 27/02/2020 | 15/07/2020 | 27/02/2020 | 15/07/2020 | 0 | TK_Complete | 1391426496 | 59 | 1391426496_59
25863-PROC105710 | TT_Task | Bogie fittings (Sandung) - BBI Collection from Supplier | 15/07/2020 | 08/09/2020 | 15/07/2020 | 17/09/2020 | 0 | TK_Complete | 1391426496 | 59 | 1391426496_59
25863-PROC105720 | TT_Task | Bogie fittings (Sandung) - Supplier Lead Time | 15/07/2020 | 18/01/2021 | 15/07/2020 | 20/04/2021 | 0 | TK_Complete | 1391426496 | 59 | 1391426496_59
25863-PROC105760 | TT_Task | Flange lubrication systems (Spurkranzschmierung) - PO Placement and/or Contract (Trigger for Supplier Leadtime) | 14/02/2020 | 10/07/2020 | 14/02/2020 | 09/09/2020 | 0 | TK_Complete | 1391426496 | 60 | 1391426496_60
25863-PROC105770 | TT_Task | Flange lubrication systems (Spurkranzschmierung) - BBI Collection from Supplier | 09/09/2020 | 03/11/2020 | 09/09/2020 | 10/09/2020 | 0 | TK_Complete | 1391426496 | 60 | 1391426496_60
25863-PROC105780 | TT_Task | Flange lubrication systems (Spurkranzschmierung) - Supplier Lead Time | 09/09/2020 | 26/01/2021 | 09/09/2020 | 08/06/2021 | 0 | TK_Complete | 1391426496 | 60 | 1391426496_60
25863-PROC105820 | TT_Task | Pantograph (Stromabnehmer) - PO Placement and/or Contract (Trigger for Supplier Leadtime) | 14/02/2020 | 13/05/2020 | 14/02/2020 | 14/08/2020 | 0 | TK_Complete | 1391426496 | 61 | 1391426496_61
25863-PROC105830 | TT_Task | Pantograph (Stromabnehmer) - BBI Collection from Supplier | 14/08/2020 | 08/10/2020 | 14/08/2020 | 17/09/2020 | 0 | TK_Complete | 1391426496 | 55 | 1391426496_55
25863-PROC105840 | TT_Task | Pantograph (Stromabnehmer) - Supplier Lead Time | 14/08/2020 | 03/12/2020 | 14/08/2020 | 29/03/2021 | 0 | TK_Complete | 1391426496 | 61 | 1391426496_61
25863-PROC105880 | TT_Task | Auxiliary converters (BNU) - PO Placement and/or Contract (Trigger for Supplier Leadtime) | 16/01/2020 | 11/05/2020 | 16/01/2020 | 31/07/2020 | 0 | TK_Complete | 1391426496 | 62 | 1391426496_62
25863-PROC105890 | TT_Task | Auxiliary converters (BNU) - BBI Collection from Supplier | 31/07/2020 | 24/09/2020 | 31/07/2020 | 01/08/2020 | 0 | TK_Complete | 1391426496 | 62 | 1391426496_62
25863-PROC105900 | TT_Task | Auxiliary converters (BNU) - Supplier Lead Time | 31/07/2020 | 08/04/2021 | 31/07/2020 | 30/03/2021 | 0 | TK_Complete | 1391426496 | 62 | 1391426496_62
25863-PROC105940 | TT_Task | Batteries (Batterie) - PO Placement and/or Contract (Trigger for Supplier Leadtime) | 10/03/2020 | 07/09/2020 | 10/03/2020 | 31/07/2020 | 0 | TK_Complete | 1391426496 | 63 | 1391426496_63
25863-PROC105950 | TT_Task | Batteries (Batterie) - BBI Collection from Supplier | 31/07/2020 | 24/09/2020 | 31/07/2020 | 28/08/2020 | 0 | TK_Complete | 1391426496 | 64 | 1391426496_64
25863-PROC105960 | TT_Task | Batteries (Batterie) - Supplier Lead Time | 31/07/2020 | 17/12/2020 | 31/07/2020 | 17/03/2021 | 0 | TK_Complete | 1391426496 | 65 | 1391426496_65
25863-PROC106000 | TT_Task | Battery boxes (Batteriekiste) - PO Placement and/or Contract (Trigger for Supplier Leadtime) | 24/01/2020 | 03/08/2020 | 24/01/2020 | 18/01/2021 | 0 | TK_Complete | 1391426496 | 63 | 1391426496_63
25863-PROC106010 | TT_Task | Battery boxes (Batteriekiste) - BBI Collection from Supplier | 28/08/2020 | 22/10/2020 | 28/08/2020 | 28/08/2020 | 0 | TK_Complete | 1391426496 | 64 | 1391426496_64
25863-PROC106020 | TT_Task | Battery boxes (Batteriekiste) - Supplier Lead Time | 16/03/2021 | 26/03/2021 | 18/01/2021 | 03/05/2021 | 0 | TK_Complete | 1391426496 | 65 | 1391426496_65
25863-PROC106060 | TT_Task | Braking system (Bremse) - PO Placement and/or Contract (Trigger for Supplier Leadtime) | 24/04/2020 | 01/06/2020 | 24/04/2020 | 21/07/2020 | 0 | TK_Complete | 1391426496 | 66 | 1391426496_66
25863-PROC106070 | TT_Task | Braking system (Bremse) - BBI Collection from Supplier | 31/07/2020 | 24/09/2020 | 31/07/2020 | 01/08/2020 | 0 | TK_Complete | 1391426496 | 66 | 1391426496_66
25863-PROC106080 | TT_Task | Braking system (Bremse) - Supplier Lead Time | 31/07/2020 | 11/02/2021 | 31/07/2020 | 21/12/2020 | 0 | TK_Complete | 1391426496 | 66 | 1391426496_66
25863-PROC106120 | TT_Task | Stanchions (Haltestangen) - PO Placement and/or Contract (Trigger for Supplier Leadtime) | 04/06/2020 | 17/08/2020 | 04/06/2020 | 08/10/2020 | 0 | TK_Complete | 1391426496 | 67 | 1391426496_67
25863-PROC106140 | TT_Task | Stanchions (Haltestangen) - Supplier Lead Time | 08/10/2020 | 01/02/2021 | 08/10/2020 | 26/04/2021 | 0 | TK_Complete | 1391426496 | 67 | 1391426496_67
25863-PROC106180 | TT_Task | Interior lights systems (Innenbeleuchtung) - PO Placement and/or Contract (Trigger for Supplier Leadtime) | 20/02/2020 | 29/05/2020 | 20/02/2020 | 14/08/2020 | 0 | TK_Complete | 1391426496 | 68 | 1391426496_68
25863-PROC106190 | TT_Task | Interior lights systems (Innenbeleuchtung) - BBI Collection from Supplier | 14/08/2020 | 08/10/2020 | 14/08/2020 | 17/09/2020 | 0 | TK_Complete | 1391426496 | 69 | 1391426496_69
25863-PROC106200 | TT_Task | Interior lights systems (Innenbeleuchtung) - Supplier Lead Time | 14/08/2020 | 31/12/2020 | 14/08/2020 | 06/04/2021 | 0 | TK_Complete | 1391426496 | 70 | 1391426496_70
25863-PROC106240 | TT_Task | Exterior lights systems (Au?enbeleuchtung) - PO Placement and/or Contract (Trigger for Supplier Leadtime) | 23/03/2020 | 31/08/2020 | 23/03/2020 | 09/09/2020 | 0 | TK_Complete | 1391426496 | 68 | 1391426496_68
25863-PROC106250 | TT_Task | Exterior lights systems (Au?enbeleuchtung) - BBI Collection from Supplier | 09/09/2020 | 03/11/2020 | 09/09/2020 | 10/09/2020 | 0 | TK_Complete | 1391426496 | 69 | 1391426496_69
25863-PROC106260 | TT_Task | Exterior lights systems (Au?enbeleuchtung) - Supplier Lead Time | 09/09/2020 | 26/01/2021 | 09/09/2020 | 08/03/2021 | 0 | TK_Complete | 1391426496 | 70 | 1391426496_70
25863-PROC106300 | TT_Task | Interior doors (Fahrerstandstrennwand) - PO Placement and/or Contract (Trigger for Supplier Leadtime) | 21/02/2020 | 13/05/2020 | 21/02/2020 | 24/07/2020 | 0 | TK_Complete | 1391426496 | 71 | 1391426496_71
25863-PROC106310 | TT_Task | Interior doors (Fahrerstandstrennwand) - BBI Collection from Supplier | 24/07/2020 | 17/09/2020 | 24/07/2020 | 17/09/2020 | 0 | TK_Complete | 1391426496 | 72 | 1391426496_72
25863-PROC106320 | TT_Task | Interior doors (Fahrerstandstrennwand) - Supplier Lead Time | 24/07/2020 | 24/12/2020 | 24/07/2020 | 02/03/2021 | 0 | TK_Complete | 1391426496 | 73 | 1391426496_73
25863-PROC106360 | TT_Task | Driver's facilities (Fahr- / Bremshebel) - PO Placement and/or Contract (Trigger for Supplier Leadtime) | 11/02/2020 | 29/05/2020 | 11/02/2020 | 21/09/2020 | 0 | TK_Complete | 1391426496 | 74 | 1391426496_74
25863-PROC106370 | TT_Task | Driver's facilities (Fahr- / Bremshebel) - BBI Collection from Supplier | 21/09/2020 | 13/11/2020 | 21/09/2020 | 22/09/2020 | 0 | TK_Complete | 1391426496 | 75 | 1391426496_75
25863-PROC106380 | TT_Task | Driver's facilities (Fahr- / Bremshebel) - Supplier Lead Time | 21/09/2020 | 04/01/2021 | 21/09/2020 | 29/04/2021 | 0 | TK_Complete | 1391426496 | 76 | 1391426496_76
25863-PROC106480 | TT_Task | Driver's facilities (Fu?podest) - PO Placement and/or Contract (Trigger for Supplier Leadtime) | 23/03/2020 | 29/05/2020 | 23/03/2020 | 24/07/2020 | 0 | TK_Complete | 1391426496 | 74 | 1391426496_74
25863-PROC106490 | TT_Task | Driver's facilities (Fu?podest) - BBI Collection from Supplier | 24/07/2020 | 17/09/2020 | 24/07/2020 | 17/09/2020 | 0 | TK_Complete | 1391426496 | 75 | 1391426496_75
25863-PROC106500 | TT_Task | Driver's facilities (Fu?podest) - Supplier Lead Time | 24/07/2020 | 01/02/2021 | 24/07/2020 | 31/05/2021 | 0 | TK_Complete | 1391426496 | 76 | 1391426496_76
25863-PROC106540 | TT_Task | Driver's desk (Fahrerstandsgeschr?nk) - PO Placement and/or Contract (Trigger for Supplier Leadtime) | 10/07/2020 | 04/09/2020 | 10/07/2020 | 07/10/2020 | 0 | TK_Complete | 1391426496 | 74 | 1391426496_74
25863-PROC106560 | TT_Task | Driver's desk (Fahrerstandsgeschr?nk) - Supplier Lead Time | 07/10/2020 | 16/02/2021 | 07/10/2020 | 25/05/2021 | 0 | TK_Complete | 1391426496 | 76 | 1391426496_76
25863-PROC106600 | TT_Task | Driver's seat (Fahrersitz) - PO Placement and/or Contract (Trigger for Supplier Leadtime) | 10/03/2020 | 14/09/2020 | 10/03/2020 | 13/11/2020 | 0 | TK_Complete | 1391426496 | 74 | 1391426496_74
25863-PROC106610 | TT_Task | Driver's seat (Fahrersitz) - BBI Collection from Supplier | 17/09/2020 | 11/11/2020 | 17/09/2020 | 17/09/2020 | 0 | TK_Complete | 1391426496 | 77 | 1391426496_77
25863-PROC106620 | TT_Task | Driver's seat (Fahrersitz) - Supplier Lead Time | 13/11/2020 | 03/03/2021 | 13/11/2020 | 19/03/2021 | 0 | TK_Complete | 1391426496 | 76 | 1391426496_76
25863-PROC106660 | TT_Task | Instructor's seat (Fahrlehrersitz) - PO Placement and/or Contract (Trigger for Supplier Leadtime) | 10/03/2020 | 10/08/2020 | 10/03/2020 | 13/11/2020 | 0 | TK_Complete | 1391426496 | 74 | 1391426496_74
25863-PROC106670 | TT_Task | Instructor's seat (Fahrlehrersitz) - BBI Collection from Supplier | 13/11/2020 | 07/01/2021 | 17/09/2020 | 17/09/2020 | 0 | TK_Complete | 1391426496 | 77 | 1391426496_77
25863-PROC106680 | TT_Task | Instructor's seat (Fahrlehrersitz) - Supplier Lead Time | 13/11/2020 | 03/03/2021 | 13/11/2020 | 13/04/2021 | 0 | TK_Complete | 1391426496 | 76 | 1391426496_76
25863-PROC106720 | TT_Task | Seats (Passagiersitze FZ2) - PO Placement and/or Contract (Trigger for Supplier Leadtime) | 14/08/2020 | 09/10/2020 | 14/08/2020 | 11/09/2020 | 0 | TK_Complete | 1391426496 | 74 | 1391426496_74
25863-PROC106730 | TT_Task | Seats (Passagiersitze FZ2) - BBI Collection from Supplier | 11/09/2020 | 05/11/2020 | 11/09/2020 | 17/09/2020 | 0 | TK_Complete | 1391426496 | 77 | 1391426496_77
25863-PROC106740 | TT_Task | Seats (Passagiersitze FZ2) - Supplier Lead Time | 11/09/2020 | 22/04/2021 | 11/09/2020 | 07/07/2021 | 0 | TK_Complete | 1391426496 | 78 | 1391426496_78
25863-PROC106780 | TT_Task | Seats (Passagiersitze FZ1) - PO Placement and/or Contract (Trigger for Supplier Leadtime) | 27/02/2020 | 15/06/2020 | 27/02/2020 | 23/07/2020 | 0 | TK_Complete | 1391426496 | 74 | 1391426496_74
25863-PROC106790 | TT_Task | Seats (Passagiersitze FZ1) - BBI Collection from Supplier | 23/07/2020 | 16/09/2020 | 23/07/2020 | 17/09/2020 | 0 | TK_Complete | 1391426496 | 77 | 1391426496_77
25863-PROC106800 | TT_Task | Seats (Passagiersitze FZ1) - Supplier Lead Time | 23/07/2020 | 08/02/2021 | 23/07/2020 | 08/01/2021 | 0 | TK_Complete | 1391426496 | 78 | 1391426496_78
25863-PROC106840 | TT_Task | Sidewall modules (Innenverkleidung GFK Cab) - PO Placement and/or Contract (Trigger for Supplier Leadtime) | 31/07/2020 | 25/09/2020 | 31/07/2020 | 02/10/2020 | 0 | TK_Complete | 1391426496 | 79 | 1391426496_79
25863-PROC106860 | TT_Task | Sidewall modules (Innenverkleidung GFK Cab) - Supplier Lead Time | 02/10/2020 | 18/01/2021 | 02/10/2020 | 03/05/2021 | 0 | TK_Complete | 1391426496 | 79 | 1391426496_79
25863-PROC106900 | TT_Task | Sidewall modules (Innenverkleidung GFK Fahrg.) - PO Placement and/or Contract (Trigger for Supplier Leadtime) | 16/06/2020 | 11/08/2020 | 16/06/2020 | 02/10/2020 | 0 | TK_Complete | 1391426496 | 79 | 1391426496_79
25863-PROC106920 | TT_Task | Sidewall modules (Innenverkleidung GFK Fahrg.) - Supplier Lead Time | 02/10/2020 | 18/01/2021 | 02/10/2020 | 30/04/2021 | 0 | TK_Complete | 1391426496 | 79 | 1391426496_79
25863-PROC106960 | TT_Task | Ceilings module (Innendecke inkl. Vouten Fahrg.) - PO Placement and/or Contract (Trigger for Supplier Leadtime) | 11/06/2020 | 09/07/2020 | 10/06/2020 | 07/09/2020 | 0 | TK_Complete | 1391426496 | 80 | 1391426496_80
25863-PROC106980 | TT_Task | Ceilings module (Innendecke inkl. Vouten Fahrg.) - Supplier Lead Time | 07/09/2020 | 18/12/2020 | 07/09/2020 | 23/02/2021 | 0 | TK_Complete | 1391426496 | 80 | 1391426496_80
25863-PROC107020 | TT_Task | Ceilings module (Innendecke inkl. Vouten Cab (GFK)) - PO Placement and/or Contract (Trigger for Supplier Leadtime) | 07/08/2020 | 02/10/2020 | 07/08/2020 | 25/09/2020 | 0 | TK_Complete | 1391426496 | 80 | 1391426496_80
25863-PROC107040 | TT_Task | Ceilings module (Innendecke inkl. Vouten Cab (GFK)) - Supplier Lead Time | 25/09/2020 | 18/01/2021 | 25/09/2020 | 03/05/2021 | 0 | TK_Complete | 1391426496 | 80 | 1391426496_80
25863-PROC107080 | TT_Task | On board control system (KWR) - PO Placement and/or Contract (Trigger for Supplier Leadtime) | 20/04/2020 | 26/06/2020 | 20/04/2020 | 20/07/2020 | 0 | TK_Complete | 1391426496 | 81 | 1391426496_81
25863-PROC107090 | TT_Task | On board control system (KWR) - BBI Collection from Supplier | 20/07/2020 | 11/09/2020 | 20/07/2020 | 17/09/2020 | 0 | TK_Complete | 1391426496 | 82 | 1391426496_82
25863-PROC107100 | TT_Task | On board control system (KWR) - Supplier Lead Time | 20/07/2020 | 04/12/2020 | 20/07/2020 | 03/05/2021 | 0 | TK_Complete | 1391426496 | 81 | 1391426496_81
25863-PROC107140 | TT_Task | Saloon surveillance (CCTV Innenkameras) - PO Placement and/or Contract (Trigger for Supplier Leadtime) | 23/04/2020 | 30/06/2020 | 23/04/2020 | 07/08/2020 | 0 | TK_Complete | 1391426496 | 83 | 1391426496_83
25863-PROC107150 | TT_Task | Saloon surveillance (CCTV Innenkameras) - BBI Collection from Supplier | 07/08/2020 | 01/10/2020 | 07/08/2020 | 17/09/2020 | 0 | TK_Complete | 1391426496 | 83 | 1391426496_83
25863-PROC107160 | TT_Task | Saloon surveillance (CCTV Innenkameras) - Supplier Lead Time | 07/08/2020 | 28/01/2021 | 07/08/2020 | 30/03/2021 | 0 | TK_Complete | 1391426496 | 83 | 1391426496_83
25863-PROC107200 | TT_Task | Audio comm. (PIS/PAS) (ITCS inkl. FLM) - PO Placement and/or Contract (Trigger for Supplier Leadtime) | 08/04/2020 | 10/06/2020 | 08/04/2020 | 07/08/2020 | 0 | TK_Complete | 1391426496 | 84 | 1391426496_84
25863-PROC107210 | TT_Task | Audio comm. (PIS/PAS) (ITCS inkl. FLM) - BBI Collection from Supplier | 07/08/2020 | 01/10/2020 | 07/08/2020 | 17/09/2020 | 0 | TK_Complete | 1391426496 | 85 | 1391426496_85
25863-PROC107220 | TT_Task | Audio comm. (PIS/PAS) (ITCS inkl. FLM) - Supplier Lead Time | 07/08/2020 | 07/01/2021 | 07/08/2020 | 26/04/2021 | 0 | TK_Complete | 1391426496 | 86 | 1391426496_86
25863-PROC107260 | TT_Task | Audio comm. (PIS/PAS) (ELA / Lautsprecher) - PO Placement and/or Contract (Trigger for Supplier Leadtime) | 24/06/2020 | 17/08/2020 | 24/06/2020 | 04/09/2020 | 0 | TK_Complete | 1391426496 | 84 | 1391426496_84
25863-PROC107270 | TT_Task | Audio comm. (PIS/PAS) (ELA / Lautsprecher) - BBI Collection from Supplier | 04/09/2020 | 29/10/2020 | 04/09/2020 | 17/09/2020 | 0 | TK_Complete | 1391426496 | 85 | 1391426496_85
25863-PROC107280 | TT_Task | Audio comm. (PIS/PAS) (ELA / Lautsprecher) - Supplier Lead Time | 04/09/2020 | 04/01/2021 | 04/09/2020 | 31/05/2021 | 0 | TK_Complete | 1391426496 | 86 | 1391426496_86
25863-PROC107320 | TT_Task | Visual comm. (PIS/PAS) (Au?enanzeiger) - PO Placement and/or Contract (Trigger for Supplier Leadtime) | 02/04/2020 | 26/06/2020 | 02/04/2020 | 07/08/2020 | 0 | TK_Complete | 1391426496 | 84 | 1391426496_84
25863-PROC107330 | TT_Task | Visual comm. (PIS/PAS) (Au?enanzeiger) - BBI Collection from Supplier | 07/08/2020 | 01/10/2020 | 07/08/2020 | 17/09/2020 | 0 | TK_Complete | 1391426496 | 87 | 1391426496_87
25863-PROC107340 | TT_Task | Visual comm. (PIS/PAS) (Au?enanzeiger) - Supplier Lead Time | 07/08/2020 | 07/01/2021 | 07/08/2020 | 05/07/2021 | 0 | TK_Complete | 1391426496 | 88 | 1391426496_88
25863-PROC107380 | TT_Task | Visual comm. (PIS/PAS) (Infotainment) - PO Placement and/or Contract (Trigger for Supplier Leadtime) | 02/04/2020 | 26/06/2020 | 02/04/2020 | 04/09/2020 | 0 | TK_Complete | 1391426496 | 84 | 1391426496_84
25863-PROC107390 | TT_Task | Visual comm. (PIS/PAS) (Infotainment) - BBI Collection from Supplier | 04/09/2020 | 29/10/2020 | 04/09/2020 | 17/09/2020 | 0 | TK_Complete | 1391426496 | 87 | 1391426496_87
25863-PROC107400 | TT_Task | Visual comm. (PIS/PAS) (Infotainment) - Supplier Lead Time | 04/09/2020 | 18/01/2021 | 04/09/2020 | 08/03/2021 | 0 | TK_Complete | 1391426496 | 88 | 1391426496_88
25863-PROC107440 | TT_Task | Passenger counting system (Fahrgastz?hlung) - PO Placement and/or Contract (Trigger for Supplier Leadtime) | 02/04/2020 | 26/06/2020 | 02/04/2020 | 30/07/2020 | 0 | TK_Complete | 1391426496 | 89 | 1391426496_89
25863-PROC107450 | TT_Task | Passenger counting system (Fahrgastz?hlung) - BBI Collection from Supplier | 07/08/2020 | 01/10/2020 | 07/08/2020 | 17/09/2020 | 0 | TK_Complete | 1391426496 | 89 | 1391426496_89
25863-PROC107460 | TT_Task | Passenger counting system (Fahrgastz?hlung) - Supplier Lead Time | 30/07/2020 | 11/01/2021 | 30/07/2020 | 08/03/2021 | 0 | TK_Complete | 1391426496 | 89 | 1391426496_89
25863-PROC107500 | TT_Task | Entertainment systems (Fahrgast WLAN) - PO Placement and/or Contract (Trigger for Supplier Leadtime) | 08/04/2020 | 26/06/2020 | 08/04/2020 | 30/09/2020 | 0 | TK_Complete | 1391426496 | 90 | 1391426496_90
25863-PROC107510 | TT_Task | Entertainment systems (Fahrgast WLAN) - BBI Collection from Supplier | 30/09/2020 | 24/11/2020 | 30/09/2020 | 17/02/2021 | 0 | TK_Complete | 1391426496 | 91 | 1391426496_91
25863-PROC107520 | TT_Task | Entertainment systems (Fahrgast WLAN) - Supplier Lead Time | 30/09/2020 | 04/01/2021 | 30/09/2020 | 17/02/2021 | 0 | TK_Complete | 1391426496 | 90 | 1391426496_90
25863-PROC107560 | TT_Task | Driver door systems (T?r Cab) - PO Placement and/or Contract (Trigger for Supplier Leadtime) | 21/04/2020 | 27/04/2020 | 21/04/2020 | 31/07/2020 | 0 | TK_Complete | 1391426496 | 71 | 1391426496_71
25863-PROC107570 | TT_Task | Driver door systems (T?r Cab) - BBI Collection from Supplier | 31/07/2020 | 24/09/2020 | 31/07/2020 | 17/09/2020 | 0 | TK_Complete | 1391426496 | 72 | 1391426496_72
25863-PROC107580 | TT_Task | Driver door systems (T?r Cab) - Supplier Lead Time | 31/07/2020 | 25/03/2021 | 31/07/2020 | 19/04/2021 | 0 | TK_Complete | 1391426496 | 73 | 1391426496_73
25863-PROC107620 | TT_Task | Passenger door systems (T?ren Passagierraum) - PO Placement and/or Contract (Trigger for Supplier Leadtime) | 21/04/2020 | 27/04/2020 | 21/04/2020 | 31/07/2020 | 0 | TK_Complete | 1391426496 | 71 | 1391426496_71
25863-PROC107630 | TT_Task | Passenger door systems (T?ren Passagierraum) - BBI Collection from Supplier | 31/07/2020 | 24/09/2020 | 31/07/2020 | 17/09/2020 | 0 | TK_Complete | 1391426496 | 72 | 1391426496_72
25863-PROC107640 | TT_Task | Passenger door systems (T?ren Passagierraum) - Supplier Lead Time | 31/07/2020 | 25/03/2021 | 31/07/2020 | 19/04/2021 | 0 | TK_Complete | 1391426496 | 73 | 1391426496_73
25863-PROC107680 | TT_Task | Door ramp systems (Einstiegsrampe) - PO Placement and/or Contract (Trigger for Supplier Leadtime) | 27/02/2020 | 29/05/2020 | 27/02/2020 | 08/01/2021 | 0 | TK_Complete | 1391426496 | 71 | 1391426496_71
25863-PROC107690 | TT_Task | Door ramp systems (Einstiegsrampe) - BBI Collection from Supplier | 03/08/2020 | 25/09/2020 | 17/09/2020 | 17/09/2020 | 0 | TK_Complete | 1391426496 | 72 | 1391426496_72
25863-PROC107700 | TT_Task | Door ramp systems (Einstiegsrampe) - Supplier Lead Time | 08/01/2021 | 17/03/2021 | 08/01/2021 | 19/05/2021 | 0 | TK_Complete | 1391426496 | 73 | 1391426496_73
25863-PROC107740 | TT_Task | HVAC driver's cab (HVAC Cab) - PO Placement and/or Contract (Trigger for Supplier Leadtime) | 06/12/2019 | 04/05/2020 | 06/12/2019 | 31/07/2020 | 0 | TK_Complete | 1391426496 | 92 | 1391426496_92
25863-PROC107760 | TT_Task | HVAC driver's cab (HVAC Cab) - Supplier Lead Time | 31/07/2020 | 08/04/2021 | 31/07/2020 | 15/03/2021 | 0 | TK_Complete | 1391426496 | 93 | 1391426496_93
25863-PROC107800 | TT_Task | HVAC saloon (HVAC Fahrgastraum) - PO Placement and/or Contract (Trigger for Supplier Leadtime) | 06/12/2019 | 04/05/2020 | 06/12/2019 | 31/07/2020 | 0 | TK_Complete | 1391426496 | 92 | 1391426496_92
25863-PROC107820 | TT_Task | HVAC saloon (HVAC Fahrgastraum) - Supplier Lead Time | 31/07/2020 | 08/04/2021 | 31/07/2020 | 08/04/2021 | 0 | TK_Complete | 1391426496 | 93 | 1391426496_93
25863-PROC107860 | TT_Task | Control Center (ODAS) - PO Placement and/or Contract (Trigger for Supplier Leadtime) | 21/07/2020 | 07/08/2020 | 21/07/2020 | 26/10/2020 | 0 | TK_Complete | 1391426496 | 94 | 1391426496_94
25863-PROC107870 | TT_Task | Control Center (ODAS) - BBI Collection from Supplier | 08/10/2020 | 02/12/2020 | 26/10/2020 | 27/10/2020 | 0 | TK_Complete | 1391426496 | 82 | 1391426496_82
25863-PROC107880 | TT_Task | Control Center (ODAS) - Supplier Lead Time | 26/10/2020 | 06/01/2021 | 26/10/2020 | 29/06/2021 | 0 | TK_Complete | 1391426496 | 94 | 1391426496_94
25863-PROC107920 | TT_Task | Bearings (Gelenklager) - PO Placement and/or Contract (Trigger for Supplier Leadtime) | 18/02/2020 | 22/06/2020 | 18/02/2020 | 08/07/2020 | 0 | TK_Complete | 1391426496 | 95 | 1391426496_95
25863-PROC107930 | TT_Task | Bearings (Gelenklager) - BBI Collection from Supplier | 09/07/2020 | 02/09/2020 | 09/07/2020 | 10/07/2020 | 0 | TK_Complete | 1391426496 | 75 | 1391426496_75
25863-PROC107940 | TT_Task | Bearings (Gelenklager) - Supplier Lead Time | 09/07/2020 | 18/01/2021 | 09/07/2020 | 26/02/2021 | 0 | TK_Complete | 1391426496 | 95 | 1391426496_95
25863-PROC107980 | TT_Task | Blinds (Rollos) - PO Placement and/or Contract (Trigger for Supplier Leadtime) | 21/07/2020 | 15/09/2020 | 21/07/2020 | 08/02/2021 | 0 | TK_Complete | 1391426496 | 96 | 1391426496_96
25863-PROC107990 | TT_Task | Blinds (Rollos) - BBI Collection from Supplier | 15/09/2020 | 09/11/2020 | 17/09/2020 | 17/09/2020 | 0 | TK_Complete | 1391426496 | 55 | 1391426496_55
25863-PROC108000 | TT_Task | Blinds (Rollos) - Supplier Lead Time | 08/02/2021 | 19/03/2021 | 08/02/2021 | 05/07/2021 | 0 | TK_Complete | 1391426496 | 96 | 1391426496_96
25863-PROC107903 | TT_Task | Buffer (Soft Nose) - PO Placement and/or Contract (Trigger for Supplier Leadtime) | 20/07/2020 | 31/07/2020 | 17/07/2020 | 28/07/2020 | 0 | TK_Complete | 1391426496 | 50 | 1391426496_50
25863-PROC107906 | TT_Task | Buffer (Soft Nose) - Supplier Lead Time | 28/07/2020 | 12/02/2021 | 28/07/2020 | 12/04/2021 | 0 | TK_Complete | 1391426496 | 52 | 1391426496_52
25863-701040 | TT_Task | FZ1 - Transport | 16/09/2021 | 17/09/2021 | 16/09/2021 | 17/09/2021 | 0 | TK_Complete | 1391426496 | 97 | 1391426496_97
25863-702030 | TT_Task | FZ2 - Transport | 16/03/2022 | 17/03/2022 | nan | nan | 0 | TK_NotStart | 1391426496 | 97 | 1391426496_97
25863-703000 | TT_Task | Regelversuche der Heizungs-, L?ftungs- und Klimasysteme (Fr?hling) | 07/06/2022 | 13/06/2022 | nan | nan | 0 | TK_NotStart | 1391426496 | 98 | 1391426496_98
25863-703010 | TT_Task | Regelversuche der Heizungs-, L?ftungs- und Klimasysteme (Sommer) | 14/06/2022 | 20/06/2022 | nan | nan | 0 | TK_NotStart | 1391426496 | 98 | 1391426496_98
25863-703020 | TT_Task | Regelversuche der Heizungs-, L?ftungs- und Klimasysteme (Herbst) | 21/06/2022 | 27/06/2022 | nan | nan | 7895 | TK_NotStart | 1391426496 | 98 | 1391426496_98
25863-901000 | TT_Task | DRAFT - Fahrlehrer-schulung (F1) | 03/01/2022 | 31/01/2022 | nan | nan | 0 | TK_NotStart | 1391426496 | 99 | 1391426496_99
25863-901010 | TT_Task | DRAFT - Eingleisen (I2) | 03/01/2022 | 31/01/2022 | nan | nan | 8695 | TK_NotStart | 1391426496 | 100 | 1391426496_100
25863-901020 | TT_Task | DRAFT - Fahrzeugkonzept (I1) | 01/02/2022 | 04/07/2022 | nan | nan | 7855 | TK_NotStart | 1391426496 | 100 | 1391426496_100
25863-901030 | TT_Task | DRAFT - Systemschulungen (I3-I18) | 01/02/2022 | 04/07/2022 | nan | nan | 7855 | TK_NotStart | 1391426496 | 101 | 1391426496_101
25863-901040 | TT_Task | DRAFT - Fertigungsbegleitung (I17) | 01/02/2022 | 04/07/2022 | nan | nan | 7855 | TK_NotStart | 1391426496 | 102 | 1391426496_102
25863-801025 | TT_Task | Carbody Production HZA WT2 #01 | 26/10/2020 | 03/02/2021 | 26/10/2020 | 18/03/2021 | 0 | TK_Complete | 1391426496 | 35 | 1391426496_35
25863-801075 | TT_Task | Carbody Production HZB WT4 #01 | 11/11/2020 | 11/02/2021 | 11/11/2020 | 04/03/2021 | 0 | TK_Complete | 1391426496 | 35 | 1391426496_35
25863-801095 | TT_Task | Carbody Production HZB WT5 #01 | 08/10/2020 | 28/01/2021 | 19/10/2020 | 29/01/2021 | 0 | TK_Complete | 1391426496 | 35 | 1391426496_35
25863-801030 | TT_Task | Fitout 1 HZA WT2 #01 | 29/03/2021 | 06/04/2021 | 19/03/2021 | 07/04/2021 | 0 | TK_Complete | 1391426496 | 7 | 1391426496_7
25863-801080 | TT_Task | Fitout 1 HZB WT4 #01 | 08/03/2021 | 25/03/2021 | 05/03/2021 | 07/04/2021 | 0 | TK_Complete | 1391426496 | 7 | 1391426496_7
25863-801100 | TT_Task | Fitout 1 HZB WT5 #01 | 01/02/2021 | 03/02/2021 | 01/02/2021 | 04/03/2021 | 0 | TK_Complete | 1391426496 | 7 | 1391426496_7
25863-COVID-00309 | TT_Task | COVID-00309 Verf?gbarkeit Mitrac Plattform Release 1.18 und Ethernet IO | 30/04/2020 | 20/05/2020 | 30/04/2020 | 20/05/2020 | 0 | TK_Complete | 1391426496 | 103 | 1391426496_103
25863-COVID-00313 | TT_Task | COVID-00313 Reduzierte Arbeitszeit (4 Tagewoche) 80% in Siegen | 12/04/2020 | 22/04/2020 | 12/04/2020 | 22/04/2020 | 0 | TK_Complete | 1391426496 | 104 | 1391426496_104
25863-205030 | TT_Task | COVID-00032 Nutzung von Catia im Home Office nicht uneingeschr?nkt m?glich (Konstruktion Seitenwand) | 16/03/2020 | 15/04/2020 | 16/03/2020 | 15/04/2020 | 0 | TK_Complete | 1391426496 | 39 | 1391426496_39
25863-800500 | TT_Task | COVID-00033 Spezielle Blechqualit?ten nicht verf?gbar in Polen (Warenverkehr eingeschr?nkt) | 16/03/2020 | 15/04/2020 | 16/03/2020 | 15/04/2020 | 0 | TK_Complete | 1391426496 | 40 | 1391426496_40
25863-409054 | TT_Task | COVID-00034 Zwei t?giger WS mit dem Kunden zum Thema DG in Siegen aufgrund der Reiserestriktionen abgesagt | 18/03/2020 | 28/03/2020 | 18/03/2020 | 28/03/2020 | 0 | TK_Complete | 1391426496 | 41 | 1391426496_41
25863-705020 | TT_Task | Bearbeitungszeit TAB | 16/05/2022 | 16/05/2022 | nan | nan | 0 | TK_NotStart | 1391426496 | 105 | 1391426496_105
25863-101595 | TT_Task | COVID-00044 chief engineer ist seit 14.03.2020 in Quarant?ne | 14/03/2020 | 24/03/2020 | 14/03/2020 | 24/03/2020 | 0 | TK_Complete | 1391426496 | 42 | 1391426496_42
25863-409062 | TT_Task | COVID-00045 Lieferant stellt die Arbeiten ein ab 23.03.2020 | 22/03/2020 | 19/04/2020 | 22/03/2020 | 19/04/2020 | 0 | TK_Complete | 1391426496 | 43 | 1391426496_43
25863-101596 | TT_Task | COVID-00046 Lock Down Verzug in der Konstruktion und Zeichnungserstellung aller mechanischen Baugruppen | 23/03/2020 | 07/04/2020 | 23/03/2020 | 07/04/2020 | 0 | TK_Complete | 1391426496 | 44 | 1391426496_44
25863-101525 | TT_Task | COVID-00047 Verschiebung Projekttermin auf Grund der notwendigen Aktionen seitens DVB | 18/03/2020 | 22/03/2020 | 18/03/2020 | 22/03/2020 | 0 | TK_Complete | 1391426496 | 45 | 1391426496_45
25863-PROC106755 | TT_Task | COVID-00270 Versp?tete Angebotsabgabe Sitze | 22/04/2020 | 02/05/2020 | 22/04/2020 | 02/05/2020 | 0 | TK_Complete | 1391426496 | 46 | 1391426496_46
25863-400000 | TT_Task | COVID-00271 Versp?tete Angebotsabgabe Fenster | 22/04/2020 | 02/05/2020 | 22/04/2020 | 02/05/2020 | 0 | TK_Complete | 1391426496 | 46 | 1391426496_46
25863-83405 | TT_Task | COVID-00309 Verf?gbarkeit Mitrac Plattform Release 1.18 und Ethernet IO | 30/04/2020 | 20/05/2020 | 30/04/2020 | 20/05/2020 | 0 | TK_Complete | 1391426496 | 103 | 1391426496_103
25863-409056 | TT_Task | COVID-00313 Reduzierte Arbeitszeit (4 Tagewoche) 80% in Siegen | 12/04/2020 | 22/04/2020 | 12/04/2020 | 22/04/2020 | 0 | TK_Complete | 1391426496 | 104 | 1391426496_104
25863-605220 | TT_Task | SD WT2 WS F20 - MBOM Implementation, Logistics Preparation, C Parts Lead Time, Tooling Definition, Fabrication, Installa | 26/10/2020 | 29/01/2021 | 26/10/2020 | 26/03/2021 | 0 | TK_Complete | 1391426496 | 33 | 1391426496_33
25863-605221 | TT_Task | SD WT2 WS F21 - MBOM Implementation, Logistics Preparation, C Parts Lead Time, Tooling Definition, Fabrication, Installa | 26/10/2020 | 29/01/2021 | 26/10/2020 | 09/04/2021 | 0 | TK_Complete | 1391426496 | 33 | 1391426496_33
25863-605222 | TT_Task | SD WT2 WS F22 - MBOM Implementation, Logistics Preparation, C Parts Lead Time, Tooling Definition, Fabrication, Installa | 09/11/2020 | 12/02/2021 | 09/11/2020 | 12/02/2021 | 0 | TK_Complete | 1391426496 | 33 | 1391426496_33
25863-605223 | TT_Task | SD WT2 WS F23 - MBOM Implementation, Logistics Preparation, C Parts Lead Time, Tooling Definition, Fabrication, Installa | 13/08/2020 | 18/11/2020 | 13/08/2020 | 13/11/2020 | 0 | TK_Complete | 1391426496 | 36 | 1391426496_36
25863-605224 | TT_Task | SD WT2 WS F24 - MBOM Implementation, Logistics Preparation, C Parts Lead Time, Tooling Definition, Fabrication, Installa | 13/01/2021 | 26/02/2021 | 31/08/2020 | 18/12/2020 | 0 | TK_Complete | 1391426496 | 33 | 1391426496_33
25863-605225 | TT_Task | SD WT2 WS F25 - MBOM Implementation, Logistics Preparation, C Parts Lead Time, Tooling Definition, Fabrication, Installa | 13/01/2021 | 05/03/2021 | 13/01/2021 | 15/01/2021 | 0 | TK_Complete | 1391426496 | 33 | 1391426496_33
25863-605226 | TT_Task | SD WT2 WS F26 - MBOM Implementation, Logistics Preparation, C Parts Lead Time, Tooling Definition, Fabrication, Installa | 26/08/2020 | 01/12/2020 | 26/08/2020 | 22/12/2020 | 0 | TK_Complete | 1391426496 | 33 | 1391426496_33
25863-605227 | TT_Task | SD WT2 WS F27 - MBOM Implementation, Logistics Preparation, C Parts Lead Time, Tooling Definition, Fabrication, Installa | 22/02/2021 | 26/02/2021 | 22/02/2021 | 26/02/2021 | 0 | TK_Complete | 1391426496 | 33 | 1391426496_33
25863-605320 | TT_Task | SD WT3 WS F20 - MBOM Implementation, Logistics Preparation, C Parts Lead Time, Tooling Definition, Fabrication, Installa | 26/10/2020 | 29/01/2021 | 26/10/2020 | 13/11/2020 | 0 | TK_Complete | 1391426496 | 36 | 1391426496_36
25863-605321 | TT_Task | SD WT3 WS F21 - MBOM Implementation, Logistics Preparation, C Parts Lead Time, Tooling Definition, Fabrication, Installa | 15/10/2020 | 20/01/2021 | 15/10/2020 | 09/04/2021 | 0 | TK_Complete | 1391426496 | 36 | 1391426496_36
25863-605322 | TT_Task | SD WT3 WS F22 - MBOM Implementation, Logistics Preparation, C Parts Lead Time, Tooling Definition, Fabrication, Installa | 09/11/2020 | 12/02/2021 | 09/11/2020 | 15/01/2021 | 0 | TK_Complete | 1391426496 | 36 | 1391426496_36
25863-605323 | TT_Task | SD WT3 WS F23 - MBOM Implementation, Logistics Preparation, C Parts Lead Time, Tooling Definition, Fabrication, Installa | 30/11/2020 | 05/03/2021 | 30/11/2020 | 01/12/2020 | 0 | TK_Complete | 1391426496 | 36 | 1391426496_36
25863-605324 | TT_Task | SD WT3 WS F24 - MBOM Implementation, Logistics Preparation, C Parts Lead Time, Tooling Definition, Fabrication, Installa | 13/01/2021 | 05/03/2021 | 13/01/2021 | 14/01/2021 | 0 | TK_Complete | 1391426496 | 36 | 1391426496_36
25863-605325 | TT_Task | SD WT3 WS F25 - MBOM Implementation, Logistics Preparation, C Parts Lead Time, Tooling Definition, Fabrication, Installa | 13/01/2021 | 05/03/2021 | 13/01/2021 | 15/01/2021 | 0 | TK_Complete | 1391426496 | 36 | 1391426496_36
25863-605326 | TT_Task | SD WT3 WS F26 - MBOM Implementation, Logistics Preparation, C Parts Lead Time, Tooling Definition, Fabrication, Installa | 26/08/2020 | 01/12/2020 | 26/08/2020 | 22/01/2021 | 0 | TK_Complete | 1391426496 | 36 | 1391426496_36
25863-605327 | TT_Task | SD WT3 WS F27 - MBOM Implementation, Logistics Preparation, C Parts Lead Time, Tooling Definition, Fabrication, Installa | 22/02/2021 | 26/02/2021 | 22/02/2021 | 26/02/2021 | 0 | TK_Complete | 1391426496 | 36 | 1391426496_36
25863-605420 | TT_Task | SD WT4 WS F20 - MBOM Implementation, Logistics Preparation, C Parts Lead Time, Tooling Definition, Fabrication, Installa | 26/10/2020 | 29/01/2021 | 26/10/2020 | 15/01/2021 | 0 | TK_Complete | 1391426496 | 106 | 1391426496_106
25863-605421 | TT_Task | SD WT4 WS F21 - MBOM Implementation, Logistics Preparation, C Parts Lead Time, Tooling Definition, Fabrication, Installa | 26/10/2020 | 29/01/2021 | 26/10/2020 | 19/03/2021 | 0 | TK_Complete | 1391426496 | 106 | 1391426496_106
25863-605422 | TT_Task | SD WT4 WS F22 - MBOM Implementation, Logistics Preparation, C Parts Lead Time, Tooling Definition, Fabrication, Installa | 09/11/2020 | 12/02/2021 | 09/11/2020 | 22/12/2020 | 0 | TK_Complete | 1391426496 | 106 | 1391426496_106
25863-605423 | TT_Task | SD WT4 WS F23 - MBOM Implementation, Logistics Preparation, C Parts Lead Time, Tooling Definition, Fabrication, Installa | 13/08/2020 | 18/11/2020 | 13/08/2020 | 10/02/2021 | 0 | TK_Complete | 1391426496 | 106 | 1391426496_106
25863-605424 | TT_Task | SD WT4 WS F24 - MBOM Implementation, Logistics Preparation, C Parts Lead Time, Tooling Definition, Fabrication, Installa | 14/12/2020 | 05/03/2021 | 14/12/2020 | 18/12/2020 | 0 | TK_Complete | 1391426496 | 106 | 1391426496_106
25863-605425 | TT_Task | SD WT4 WS F25 - MBOM Implementation, Logistics Preparation, C Parts Lead Time, Tooling Definition, Fabrication, Installa | 13/01/2021 | 05/03/2021 | 13/01/2021 | 15/01/2021 | 0 | TK_Complete | 1391426496 | 106 | 1391426496_106
25863-605426 | TT_Task | SD WT4 WS F26 - MBOM Implementation, Logistics Preparation, C Parts Lead Time, Tooling Definition, Fabrication, Installa | 18/09/2020 | 24/12/2020 | 18/09/2020 | 11/12/2020 | 0 | TK_Complete | 1391426496 | 106 | 1391426496_106
25863-605427 | TT_Task | SD WT4 WS F27 - MBOM Implementation, Logistics Preparation, C Parts Lead Time, Tooling Definition, Fabrication, Installa | 22/02/2021 | 26/02/2021 | 22/02/2021 | 26/02/2021 | 0 | TK_Complete | 1391426496 | 106 | 1391426496_106
25863-605520 | TT_Task | SD WT5 WS F20 - MBOM Implementation, Logistics Preparation, C Parts Lead Time, Tooling Definition, Fabrication, Installa | 26/10/2020 | 29/01/2021 | 26/10/2020 | 13/11/2020 | 0 | TK_Complete | 1391426496 | 107 | 1391426496_107
25863-605521 | TT_Task | SD WT5 WS F21 - MBOM Implementation, Logistics Preparation, C Parts Lead Time, Tooling Definition, Fabrication, Installa | 13/11/2020 | 18/02/2021 | 13/11/2020 | 19/02/2021 | 0 | TK_Complete | 1391426496 | 107 | 1391426496_107
25863-605522 | TT_Task | SD WT5 WS F22 - MBOM Implementation, Logistics Preparation, C Parts Lead Time, Tooling Definition, Fabrication, Installa | 18/11/2020 | 23/02/2021 | 18/11/2020 | 29/01/2021 | 0 | TK_Complete | 1391426496 | 107 | 1391426496_107
25863-605523 | TT_Task | SD WT5 WS F23 - MBOM Implementation, Logistics Preparation, C Parts Lead Time, Tooling Definition, Fabrication, Installa | 11/01/2021 | 26/02/2021 | 11/01/2021 | 15/01/2021 | 0 | TK_Complete | 1391426496 | 107 | 1391426496_107
25863-605524 | TT_Task | SD WT5 WS F24 - MBOM Implementation, Logistics Preparation, C Parts Lead Time, Tooling Definition, Fabrication, Installa | 13/01/2021 | 05/03/2021 | 13/01/2021 | 22/01/2021 | 0 | TK_Complete | 1391426496 | 107 | 1391426496_107
25863-605525 | TT_Task | SD WT5 WS F25 - MBOM Implementation, Logistics Preparation, C Parts Lead Time, Tooling Definition, Fabrication, Installa | 13/01/2021 | 05/03/2021 | 13/01/2021 | 05/02/2021 | 0 | TK_Complete | 1391426496 | 107 | 1391426496_107
25863-605526 | TT_Task | SD WT5 WS F26 - MBOM Implementation, Logistics Preparation, C Parts Lead Time, Tooling Definition, Fabrication, Installa | 27/08/2020 | 02/12/2020 | 27/08/2020 | 15/01/2021 | 0 | TK_Complete | 1391426496 | 107 | 1391426496_107
25863-605527 | TT_Task | SD WT5 WS F27 - MBOM Implementation, Logistics Preparation, C Parts Lead Time, Tooling Definition, Fabrication, Installa | 22/02/2021 | 26/02/2021 | 22/02/2021 | 26/02/2021 | 0 | TK_Complete | 1391426496 | 107 | 1391426496_107
25863-606120 | TT_Task | BD WT1 WS F20 - MBOM Implementation, Logistics Preparation, C Parts Lead Time, Tooling Definition, Fabrication, Installa | 06/11/2020 | 11/02/2021 | 06/11/2020 | 11/02/2021 | 0 | TK_Complete | 1391426496 | 108 | 1391426496_108
25863-606121 | TT_Task | BD WT1 WS F21 - MBOM Implementation, Logistics Preparation, C Parts Lead Time, Tooling Definition, Fabrication, Installa | 03/05/2021 | 06/08/2021 | 03/05/2021 | 06/08/2021 | 0 | TK_Complete | 1391426496 | 108 | 1391426496_108
25863-606122 | TT_Task | BD WT1 WS F22 - MBOM Implementation, Logistics Preparation, C Parts Lead Time, Tooling Definition, Fabrication, Installa | 03/05/2021 | 06/08/2021 | 03/05/2021 | 06/08/2021 | 0 | TK_Complete | 1391426496 | 108 | 1391426496_108
25863-606123 | TT_Task | BD WT1 WS F23 - MBOM Implementation, Logistics Preparation, C Parts Lead Time, Tooling Definition, Fabrication, Installa | 11/01/2021 | 16/04/2021 | 11/01/2021 | 12/01/2021 | 0 | TK_Complete | 1391426496 | 36 | 1391426496_36
25863-606124 | TT_Task | BD WT1 WS F24 - MBOM Implementation, Logistics Preparation, C Parts Lead Time, Tooling Definition, Fabrication, Installa | 03/05/2021 | 06/08/2021 | 03/05/2021 | 06/08/2021 | 0 | TK_Complete | 1391426496 | 108 | 1391426496_108
25863-606125 | TT_Task | BD WT1 WS F25 - MBOM Implementation, Logistics Preparation, C Parts Lead Time, Tooling Definition, Fabrication, Installa | 19/02/2021 | 27/05/2021 | 19/02/2021 | 27/05/2021 | 0 | TK_Complete | 1391426496 | 108 | 1391426496_108
25863-606126 | TT_Task | BD WT1 WS F26 - MBOM Implementation, Logistics Preparation, C Parts Lead Time, Tooling Definition, Fabrication, Installa | 14/12/2020 | 19/03/2021 | 14/12/2020 | nan | 856 | TK_Active | 1391426496 | 108 | 1391426496_108
25863-606127 | TT_Task | BD WT1 WS F27 - MBOM Implementation, Logistics Preparation, C Parts Lead Time, Tooling Definition, Fabrication, Installa | 11/01/2021 | 16/04/2021 | 11/01/2021 | 16/04/2021 | 0 | TK_Complete | 1391426496 | 108 | 1391426496_108
25863-606220 | TT_Task | BD WT2 WS F20 - MBOM Implementation, Logistics Preparation, C Parts Lead Time, Tooling Definition, Fabrication, Installa | 06/11/2020 | 11/02/2021 | 06/11/2020 | 11/02/2021 | 0 | TK_Complete | 1391426496 | 108 | 1391426496_108
25863-606221 | TT_Task | BD WT2 WS F21 - MBOM Implementation, Logistics Preparation, C Parts Lead Time, Tooling Definition, Fabrication, Installa | 03/05/2021 | 06/08/2021 | 03/05/2021 | 06/08/2021 | 0 | TK_Complete | 1391426496 | 108 | 1391426496_108
25863-606222 | TT_Task | BD WT2 WS F22 - MBOM Implementation, Logistics Preparation, C Parts Lead Time, Tooling Definition, Fabrication, Installa | 25/01/2021 | 30/04/2021 | 25/01/2021 | 30/04/2021 | 0 | TK_Complete | 1391426496 | 108 | 1391426496_108
25863-606223 | TT_Task | BD WT2 WS F23 - MBOM Implementation, Logistics Preparation, C Parts Lead Time, Tooling Definition, Fabrication, Installa | 13/08/2020 | 18/11/2020 | 13/08/2020 | 13/11/2020 | 0 | TK_Complete | 1391426496 | 36 | 1391426496_36
25863-606224 | TT_Task | BD WT2 WS F24 - MBOM Implementation, Logistics Preparation, C Parts Lead Time, Tooling Definition, Fabrication, Installa | 03/05/2021 | 06/08/2021 | 03/05/2021 | 06/08/2021 | 0 | TK_Complete | 1391426496 | 108 | 1391426496_108
25863-606225 | TT_Task | BD WT2 WS F25 - MBOM Implementation, Logistics Preparation, C Parts Lead Time, Tooling Definition, Fabrication, Installa | 05/01/2022 | 12/04/2022 | nan | nan | 840 | TK_NotStart | 1391426496 | 108 | 1391426496_108
25863-606226 | TT_Task | BD WT2 WS F26 - MBOM Implementation, Logistics Preparation, C Parts Lead Time, Tooling Definition, Fabrication, Installa | 30/10/2020 | 04/02/2021 | 30/10/2020 | 04/02/2021 | 0 | TK_Complete | 1391426496 | 108 | 1391426496_108
25863-606227 | TT_Task | BD WT2 WS F27 - MBOM Implementation, Logistics Preparation, C Parts Lead Time, Tooling Definition, Fabrication, Installa | 19/02/2021 | 27/05/2021 | 19/02/2021 | 27/05/2021 | 0 | TK_Complete | 1391426496 | 108 | 1391426496_108
25863-606320 | TT_Task | BD WT3 WS F20 - MBOM Implementation, Logistics Preparation, C Parts Lead Time, Tooling Definition, Fabrication, Installa | 03/05/2021 | 06/08/2021 | 03/05/2021 | 06/08/2021 | 0 | TK_Complete | 1391426496 | 36 | 1391426496_36
25863-606321 | TT_Task | BD WT3 WS F21 - MBOM Implementation, Logistics Preparation, C Parts Lead Time, Tooling Definition, Fabrication, Installa | 03/05/2021 | 06/08/2021 | 03/05/2021 | 06/08/2021 | 0 | TK_Complete | 1391426496 | 36 | 1391426496_36
25863-606322 | TT_Task | BD WT3 WS F22 - MBOM Implementation, Logistics Preparation, C Parts Lead Time, Tooling Definition, Fabrication, Installa | 15/02/2021 | 21/05/2021 | 15/02/2021 | 21/05/2021 | 0 | TK_Complete | 1391426496 | 36 | 1391426496_36
25863-606323 | TT_Task | BD WT3 WS F23 - MBOM Implementation, Logistics Preparation, C Parts Lead Time, Tooling Definition, Fabrication, Installa | 30/11/2020 | 05/03/2021 | 30/11/2020 | 01/12/2020 | 0 | TK_Complete | 1391426496 | 36 | 1391426496_36
25863-606324 | TT_Task | BD WT3 WS F24 - MBOM Implementation, Logistics Preparation, C Parts Lead Time, Tooling Definition, Fabrication, Installa | 19/02/2021 | 27/05/2021 | 19/02/2021 | 27/05/2021 | 0 | TK_Complete | 1391426496 | 36 | 1391426496_36
25863-606325 | TT_Task | BD WT3 WS F25 - MBOM Implementation, Logistics Preparation, C Parts Lead Time, Tooling Definition, Fabrication, Installa | 19/02/2021 | 27/05/2021 | 19/02/2021 | 22/02/2021 | 0 | TK_Complete | 1391426496 | 36 | 1391426496_36
25863-606326 | TT_Task | BD WT3 WS F26 - MBOM Implementation, Logistics Preparation, C Parts Lead Time, Tooling Definition, Fabrication, Installa | 26/08/2020 | 01/12/2020 | 26/08/2020 | 22/01/2021 | 0 | TK_Complete | 1391426496 | 36 | 1391426496_36
25863-606327 | TT_Task | BD WT3 WS F27 - MBOM Implementation, Logistics Preparation, C Parts Lead Time, Tooling Definition, Fabrication, Installa | 19/02/2021 | 27/05/2021 | 19/02/2021 | 27/05/2021 | 0 | TK_Complete | 1391426496 | 36 | 1391426496_36
25863-606420 | TT_Task | BD WT4 WS F20 - MBOM Implementation, Logistics Preparation, C Parts Lead Time, Tooling Definition, Fabrication, Installa | 03/05/2021 | 06/08/2021 | 03/05/2021 | 06/08/2021 | 0 | TK_Complete | 1391426496 | 106 | 1391426496_106
25863-606421 | TT_Task | BD WT4 WS F21 - MBOM Implementation, Logistics Preparation, C Parts Lead Time, Tooling Definition, Fabrication, Installa | 03/05/2021 | 06/08/2021 | 03/05/2021 | 06/08/2021 | 0 | TK_Complete | 1391426496 | 106 | 1391426496_106
25863-606422 | TT_Task | BD WT4 WS F22 - MBOM Implementation, Logistics Preparation, C Parts Lead Time, Tooling Definition, Fabrication, Installa | 25/01/2021 | 30/04/2021 | 25/01/2021 | 30/04/2021 | 0 | TK_Complete | 1391426496 | 106 | 1391426496_106
25863-606423 | TT_Task | BD WT4 WS F23 - MBOM Implementation, Logistics Preparation, C Parts Lead Time, Tooling Definition, Fabrication, Installa | 13/08/2020 | 18/11/2020 | 13/08/2020 | 13/11/2020 | 0 | TK_Complete | 1391426496 | 106 | 1391426496_106
25863-606424 | TT_Task | BD WT4 WS F24 - MBOM Implementation, Logistics Preparation, C Parts Lead Time, Tooling Definition, Fabrication, Installa | 19/02/2021 | 27/05/2021 | 19/02/2021 | 27/05/2021 | 0 | TK_Complete | 1391426496 | 106 | 1391426496_106
25863-606425 | TT_Task | BD WT4 WS F25 - MBOM Implementation, Logistics Preparation, C Parts Lead Time, Tooling Definition, Fabrication, Installa | 03/05/2021 | 06/08/2021 | 03/05/2021 | 06/08/2021 | 0 | TK_Complete | 1391426496 | 106 | 1391426496_106
25863-606426 | TT_Task | BD WT4 WS F26 - MBOM Implementation, Logistics Preparation, C Parts Lead Time, Tooling Definition, Fabrication, Installa | 16/10/2020 | 21/01/2021 | 16/10/2020 | 21/01/2021 | 0 | TK_Complete | 1391426496 | 106 | 1391426496_106
25863-606427 | TT_Task | BD WT4 WS F27 - MBOM Implementation, Logistics Preparation, C Parts Lead Time, Tooling Definition, Fabrication, Installa | 11/01/2021 | 16/04/2021 | 11/01/2021 | 16/04/2021 | 0 | TK_Complete | 1391426496 | 106 | 1391426496_106
25863-606520 | TT_Task | BD WT5 WS F20 - MBOM Implementation, Logistics Preparation, C Parts Lead Time, Tooling Definition, Fabrication, Installa | 06/11/2020 | 11/02/2021 | 06/11/2020 | 11/02/2021 | 0 | TK_Complete | 1391426496 | 107 | 1391426496_107
25863-606521 | TT_Task | BD WT5 WS F21 - MBOM Implementation, Logistics Preparation, C Parts Lead Time, Tooling Definition, Fabrication, Installa | 03/05/2021 | 06/08/2021 | 03/05/2021 | 06/08/2021 | 0 | TK_Complete | 1391426496 | 107 | 1391426496_107
25863-606522 | TT_Task | BD WT5 WS F22 - MBOM Implementation, Logistics Preparation, C Parts Lead Time, Tooling Definition, Fabrication, Installa | 03/05/2021 | 06/08/2021 | 03/05/2021 | 06/08/2021 | 0 | TK_Complete | 1391426496 | 107 | 1391426496_107
25863-606523 | TT_Task | BD WT5 WS F23 - MBOM Implementation, Logistics Preparation, C Parts Lead Time, Tooling Definition, Fabrication, Installa | 11/01/2021 | 16/04/2021 | 11/01/2021 | 05/03/2021 | 0 | TK_Complete | 1391426496 | 107 | 1391426496_107
25863-606524 | TT_Task | BD WT5 WS F24 - MBOM Implementation, Logistics Preparation, C Parts Lead Time, Tooling Definition, Fabrication, Installa | 03/05/2021 | 06/08/2021 | 03/05/2021 | 06/08/2021 | 0 | TK_Complete | 1391426496 | 107 | 1391426496_107
25863-606525 | TT_Task | BD WT5 WS F25 - MBOM Implementation, Logistics Preparation, C Parts Lead Time, Tooling Definition, Fabrication, Installa | 19/02/2021 | 27/05/2021 | 19/02/2021 | 27/05/2021 | 0 | TK_Complete | 1391426496 | 107 | 1391426496_107
25863-606526 | TT_Task | BD WT5 WS F26 - MBOM Implementation, Logistics Preparation, C Parts Lead Time, Tooling Definition, Fabrication, Installa | 29/10/2020 | 03/02/2021 | 29/10/2020 | 03/02/2021 | 0 | TK_Complete | 1391426496 | 107 | 1391426496_107
25863-606527 | TT_Task | BD WT5 WS F27 - MBOM Implementation, Logistics Preparation, C Parts Lead Time, Tooling Definition, Fabrication, Installa | 11/01/2021 | 16/04/2021 | 11/01/2021 | 16/04/2021 | 0 | TK_Complete | 1391426496 | 107 | 1391426496_107
25863-600000 | TT_Task | SD CBY - MBOM Implementation, Logistics Preparation, C Parts Lead Time, Tooling Definition, Fabrication, Installa | 23/10/2020 | 28/01/2021 | 23/10/2020 | 26/10/2020 | 0 | TK_Complete | 1391426496 | 109 | 1391426496_109
25863-802002 | TT_Task | Rohbau inkl. Oberfl?che HZB #02 | 12/11/2020 | 09/04/2021 | 12/11/2020 | 30/06/2021 | 0 | TK_Complete | 1391426496 | 110 | 1391426496_110
25863-802006 | TT_Task | Fitout 1 (including Transport) HZA #02 | 28/04/2021 | 21/05/2021 | 29/04/2021 | 04/06/2021 | 0 | TK_Complete | 1391426496 | 111 | 1391426496_111
25863-802008 | TT_Task | Fitout 1 (including Transport) HZB #02 | 19/05/2021 | 09/06/2021 | 19/05/2021 | 28/06/2021 | 0 | TK_Complete | 1391426496 | 112 | 1391426496_112
25863-802015 | TT_Task | Fitout 2 HZB #02 | 24/06/2021 | 16/09/2021 | 24/06/2021 | 29/10/2021 | 0 | TK_Complete | 1391426496 | 113 | 1391426496_113
25863-803002 | TT_Task | Rohbau inkl. Oberfl?che HZB #03 | 17/12/2020 | 12/07/2021 | 17/12/2020 | 26/07/2021 | 0 | TK_Complete | 1391426496 | 110 | 1391426496_110
25863-803006 | TT_Task | Fitout 1 (including Transport) HZA #03 | 29/09/2021 | 27/10/2021 | 29/09/2021 | 06/10/2021 | 0 | TK_Complete | 1391426496 | 111 | 1391426496_111
25863-803008 | TT_Task | Fitout 1 (including Transport) HZB #03 | 20/07/2021 | 12/08/2021 | 20/07/2021 | 24/08/2021 | 0 | TK_Complete | 1391426496 | 112 | 1391426496_112
25863-803015 | TT_Task | Fitout 2 HZB #03 | 25/08/2021 | 22/11/2021 | 23/08/2021 | nan | 0 | TK_Active | 1391426496 | 113 | 1391426496_113
25863-804002 | TT_Task | Rohbau inkl. Oberfl?che HZB #04 | 04/06/2021 | 17/09/2021 | 04/06/2021 | 13/09/2021 | 0 | TK_Complete | 1391426496 | 110 | 1391426496_110
25863-804006 | TT_Task | Fitout 1 (including Transport) HZA #04 | 30/08/2021 | 16/09/2021 | 27/08/2021 | 23/09/2021 | 0 | TK_Complete | 1391426496 | 111 | 1391426496_111
25863-804008 | TT_Task | Fitout 1 (including Transport) HZB #04 | 15/09/2021 | 08/10/2021 | 14/09/2021 | 28/10/2021 | 0 | TK_Complete | 1391426496 | 112 | 1391426496_112
25863-804015 | TT_Task | Fitout 2 HZB #04 | 28/10/2021 | 18/01/2022 | 03/12/2021 | nan | 0 | TK_Active | 1391426496 | 113 | 1391426496_113
25863-805002 | TT_Task | Rohbau inkl. Oberfl?che HZB #05 | 14/07/2021 | 01/10/2021 | 14/07/2021 | 18/11/2021 | 0 | TK_Complete | 1391426496 | 110 | 1391426496_110
25863-805006 | TT_Task | Fitout 1 (including Transport) HZA #05 | 27/09/2021 | 22/10/2021 | 21/10/2021 | 06/12/2021 | 0 | TK_Complete | 1391426496 | 111 | 1391426496_111
25863-805008 | TT_Task | Fitout 1 (including Transport) HZB #05 | 19/11/2021 | 01/12/2021 | 19/11/2021 | 14/01/2022 | 0 | TK_Complete | 1391426496 | 112 | 1391426496_112
25863-805015 | TT_Task | Fitout 2 HZB #05 | 14/01/2022 | 18/03/2022 | 17/01/2022 | nan | 0 | TK_Active | 1391426496 | 113 | 1391426496_113
25863-806002 | TT_Task | Rohbau inkl. Oberfl?che HZB #06 | 15/07/2021 | 28/10/2021 | 15/07/2021 | 25/11/2021 | 0 | TK_Complete | 1391426496 | 110 | 1391426496_110
25863-806006 | TT_Task | Fitout 1 (including Transport) HZA #06 | 29/11/2021 | 06/01/2022 | 29/11/2021 | nan | 0 | TK_Active | 1391426496 | 111 | 1391426496_111
25863-806008 | TT_Task | Fitout 1 (including Transport) HZB #06 | 26/11/2021 | 18/02/2022 | 26/11/2021 | nan | 0 | TK_Active | 1391426496 | 112 | 1391426496_112
25863-806015 | TT_Task | Fitout 2 HZB #06 | 17/02/2022 | 07/04/2022 | nan | nan | 0 | TK_NotStart | 1391426496 | 113 | 1391426496_113
25863-807002 | TT_Task | Rohbau inkl. Oberfl?che HZB #07 | 27/08/2021 | 09/11/2021 | 27/08/2021 | nan | 0 | TK_Active | 1391426496 | 110 | 1391426496_110
25863-807006 | TT_Task | Fitout 1 (including Transport) HZA #07 | 02/02/2022 | 01/03/2022 | nan | nan | 0 | TK_NotStart | 1391426496 | 111 | 1391426496_111
25863-807008 | TT_Task | Fitout 1 (including Transport) HZB #07 | 15/02/2022 | 15/03/2022 | nan | nan | 0 | TK_NotStart | 1391426496 | 112 | 1391426496_112
25863-807015 | TT_Task | Fitout 2 HZB #07 | 23/03/2022 | 13/05/2022 | nan | nan | 0 | TK_NotStart | 1391426496 | 113 | 1391426496_113
25863-808002 | TT_Task | Rohbau inkl. Oberfl?che HZB #08 | 20/09/2021 | 26/11/2021 | 20/09/2021 | nan | 0 | TK_Active | 1391426496 | 110 | 1391426496_110
25863-808006 | TT_Task | Fitout 1 (including Transport) HZA #08 | 13/01/2022 | 25/03/2022 | nan | nan | 0 | TK_NotStart | 1391426496 | 111 | 1391426496_111
25863-808008 | TT_Task | Fitout 1 (including Transport) HZB #08 | 13/01/2022 | 06/04/2022 | nan | nan | 0 | TK_NotStart | 1391426496 | 112 | 1391426496_112
25863-808015 | TT_Task | Fitout 2 HZB #08 | 19/04/2022 | 03/06/2022 | nan | nan | 0 | TK_NotStart | 1391426496 | 113 | 1391426496_113
25863-809002 | TT_Task | Rohbau inkl. Oberfl?che HZB #09 | 13/10/2021 | 15/12/2021 | 13/10/2021 | nan | 0 | TK_Active | 1391426496 | 110 | 1391426496_110
25863-809006 | TT_Task | Fitout 1 (including Transport) HZA #09 | 01/02/2022 | 19/04/2022 | nan | nan | 0 | TK_NotStart | 1391426496 | 111 | 1391426496_111
25863-809008 | TT_Task | Fitout 1 (including Transport) HZB #09 | 01/02/2022 | 02/05/2022 | nan | nan | 0 | TK_NotStart | 1391426496 | 112 | 1391426496_112
25863-809015 | TT_Task | Fitout 2 HZB #09 | 03/05/2022 | 22/06/2022 | nan | nan | 0 | TK_NotStart | 1391426496 | 113 | 1391426496_113
25863-810002 | TT_Task | Rohbau inkl. Oberfl?che HZB #10 | 24/01/2022 | 04/05/2022 | nan | nan | 0 | TK_NotStart | 1391426496 | 110 | 1391426496_110
25863-810006 | TT_Task | Fitout 1 (including Transport) HZA #10 | 29/04/2022 | 12/05/2022 | nan | nan | 0 | TK_NotStart | 1391426496 | 111 | 1391426496_111
25863-810008 | TT_Task | Fitout 1 (including Transport) HZB #10 | 05/05/2022 | 24/05/2022 | nan | nan | 0 | TK_NotStart | 1391426496 | 112 | 1391426496_112
25863-810015 | TT_Task | Fitout 2 HZB #10 | 25/05/2022 | 14/07/2022 | nan | nan | 0 | TK_NotStart | 1391426496 | 113 | 1391426496_113
25863-811002 | TT_Task | Rohbau inkl. Oberfl?che HZB #11 | 07/02/2022 | 20/05/2022 | nan | nan | 0 | TK_NotStart | 1391426496 | 110 | 1391426496_110
25863-811006 | TT_Task | Fitout 1 (including Transport) HZA #11 | 17/05/2022 | 02/06/2022 | nan | nan | 0 | TK_NotStart | 1391426496 | 111 | 1391426496_111
25863-811008 | TT_Task | Fitout 1 (including Transport) HZB #11 | 23/05/2022 | 09/06/2022 | nan | nan | 0 | TK_NotStart | 1391426496 | 112 | 1391426496_112
25863-811015 | TT_Task | Fitout 2 HZB #11 | 13/06/2022 | 29/07/2022 | nan | nan | 0 | TK_NotStart | 1391426496 | 113 | 1391426496_113
25863-812002 | TT_Task | Rohbau inkl. Oberfl?che HZB #12 | 21/02/2022 | 10/06/2022 | nan | nan | 0 | TK_NotStart | 1391426496 | 110 | 1391426496_110
25863-812006 | TT_Task | Fitout 1 (including Transport) HZA #12 | 07/06/2022 | 15/06/2022 | nan | nan | 0 | TK_NotStart | 1391426496 | 111 | 1391426496_111
25863-812008 | TT_Task | Fitout 1 (including Transport) HZB #12 | 13/06/2022 | 21/06/2022 | nan | nan | 0 | TK_NotStart | 1391426496 | 112 | 1391426496_112
25863-812015 | TT_Task | Fitout 2 HZB #12 | 29/06/2022 | 30/08/2022 | nan | nan | 0 | TK_NotStart | 1391426496 | 113 | 1391426496_113
25863-813002 | TT_Task | Rohbau inkl. Oberfl?che HZB #13 | 07/03/2022 | 22/06/2022 | nan | nan | 0 | TK_NotStart | 1391426496 | 110 | 1391426496_110
25863-813006 | TT_Task | Fitout 1 (including Transport) HZA #13 | 17/06/2022 | 27/06/2022 | nan | nan | 0 | TK_NotStart | 1391426496 | 111 | 1391426496_111
25863-813008 | TT_Task | Fitout 1 (including Transport) HZB #13 | 23/06/2022 | 01/07/2022 | nan | nan | 0 | TK_NotStart | 1391426496 | 112 | 1391426496_112
25863-813015 | TT_Task | Fitout 2 HZB #13 | 11/07/2022 | 09/09/2022 | nan | nan | 0 | TK_NotStart | 1391426496 | 113 | 1391426496_113
25863-814002 | TT_Task | Rohbau inkl. Oberfl?che HZB #14 | 21/03/2022 | 04/07/2022 | nan | nan | 0 | TK_NotStart | 1391426496 | 110 | 1391426496_110
25863-814006 | TT_Task | Fitout 1 (including Transport) HZA #14 | 29/06/2022 | 07/07/2022 | nan | nan | 0 | TK_NotStart | 1391426496 | 111 | 1391426496_111
25863-814008 | TT_Task | Fitout 1 (including Transport) HZB #14 | 05/07/2022 | 13/07/2022 | nan | nan | 0 | TK_NotStart | 1391426496 | 112 | 1391426496_112
25863-814015 | TT_Task | Fitout 2 HZB #14 | 21/07/2022 | 23/09/2022 | nan | nan | 0 | TK_NotStart | 1391426496 | 113 | 1391426496_113
25863-815002 | TT_Task | Rohbau inkl. Oberfl?che HZB #15 | 04/04/2022 | 14/07/2022 | nan | nan | 0 | TK_NotStart | 1391426496 | 110 | 1391426496_110
25863-815006 | TT_Task | Fitout 1 (including Transport) HZA #15 | 11/07/2022 | 19/07/2022 | nan | nan | 0 | TK_NotStart | 1391426496 | 111 | 1391426496_111
25863-815008 | TT_Task | Fitout 1 (including Transport) HZB #15 | 15/07/2022 | 25/07/2022 | nan | nan | 0 | TK_NotStart | 1391426496 | 112 | 1391426496_112
25863-815015 | TT_Task | Fitout 2 HZB #15 | 16/08/2022 | 06/10/2022 | nan | nan | 0 | TK_NotStart | 1391426496 | 113 | 1391426496_113
25863-816002 | TT_Task | Rohbau inkl. Oberfl?che HZB #16 | 20/04/2022 | 12/08/2022 | nan | nan | 0 | TK_NotStart | 1391426496 | 110 | 1391426496_110
25863-816006 | TT_Task | Fitout 1 (including Transport) HZA #16 | 26/07/2022 | 15/08/2022 | nan | nan | 0 | TK_NotStart | 1391426496 | 111 | 1391426496_111
25863-816008 | TT_Task | Fitout 1 (including Transport) HZB #16 | 15/08/2022 | 22/08/2022 | nan | nan | 0 | TK_NotStart | 1391426496 | 112 | 1391426496_112
25863-816015 | TT_Task | Fitout 2 HZB #16 | 31/08/2022 | 20/10/2022 | nan | nan | 0 | TK_NotStart | 1391426496 | 113 | 1391426496_113
25863-817002 | TT_Task | Rohbau inkl. Oberfl?che HZB #17 | 18/05/2022 | 06/09/2022 | nan | nan | 0 | TK_NotStart | 1391426496 | 110 | 1391426496_110
25863-817006 | TT_Task | Fitout 1 (including Transport) HZA #17 | 01/09/2022 | 07/09/2022 | nan | nan | 0 | TK_NotStart | 1391426496 | 111 | 1391426496_111
25863-817008 | TT_Task | Fitout 1 (including Transport) HZB #17 | 07/09/2022 | 13/09/2022 | nan | nan | 0 | TK_NotStart | 1391426496 | 112 | 1391426496_112
25863-817015 | TT_Task | Fitout 2 HZB #17 | 23/09/2022 | 15/11/2022 | nan | nan | 0 | TK_NotStart | 1391426496 | 113 | 1391426496_113
25863-818002 | TT_Task | Rohbau inkl. Oberfl?che HZB #18 | 06/05/2022 | 16/09/2022 | nan | nan | 0 | TK_NotStart | 1391426496 | 110 | 1391426496_110
25863-818006 | TT_Task | Fitout 1 (including Transport) HZA #18 | 13/09/2022 | 19/09/2022 | nan | nan | 0 | TK_NotStart | 1391426496 | 111 | 1391426496_111
25863-818008 | TT_Task | Fitout 1 (including Transport) HZB #18 | 19/09/2022 | 23/09/2022 | nan | nan | 0 | TK_NotStart | 1391426496 | 112 | 1391426496_112
25863-818015 | TT_Task | Fitout 2 HZB #18 | 06/10/2022 | 28/11/2022 | nan | nan | 0 | TK_NotStart | 1391426496 | 113 | 1391426496_113
25863-819002 | TT_Task | Rohbau inkl. Oberfl?che HZB #19 | 17/05/2022 | 28/09/2022 | nan | nan | 0 | TK_NotStart | 1391426496 | 110 | 1391426496_110
25863-819006 | TT_Task | Fitout 1 (including Transport) HZA #19 | 23/09/2022 | 29/09/2022 | nan | nan | 0 | TK_NotStart | 1391426496 | 111 | 1391426496_111
25863-819008 | TT_Task | Fitout 1 (including Transport) HZB #19 | 29/09/2022 | 06/10/2022 | nan | nan | 0 | TK_NotStart | 1391426496 | 112 | 1391426496_112
25863-819015 | TT_Task | Fitout 2 HZB #19 | 18/10/2022 | 08/12/2022 | nan | nan | 0 | TK_NotStart | 1391426496 | 113 | 1391426496_113
25863-820002 | TT_Task | Rohbau inkl. Oberfl?che HZB #20 | 01/06/2022 | 11/10/2022 | nan | nan | 0 | TK_NotStart | 1391426496 | 110 | 1391426496_110
25863-820006 | TT_Task | Fitout 1 (including Transport) HZA #20 | 06/10/2022 | 12/10/2022 | nan | nan | 0 | TK_NotStart | 1391426496 | 111 | 1391426496_111
25863-820008 | TT_Task | Fitout 1 (including Transport) HZB #20 | 12/10/2022 | 18/10/2022 | nan | nan | 0 | TK_NotStart | 1391426496 | 112 | 1391426496_112
25863-820015 | TT_Task | Fitout 2 HZB #20 | 28/10/2022 | 20/12/2022 | nan | nan | 0 | TK_NotStart | 1391426496 | 113 | 1391426496_113
25863-821002 | TT_Task | Rohbau inkl. Oberfl?che HZB #21 | 15/06/2022 | 21/10/2022 | nan | nan | 0 | TK_NotStart | 1391426496 | 110 | 1391426496_110
25863-821006 | TT_Task | Fitout 1 (including Transport) HZA #21 | 18/10/2022 | 24/10/2022 | nan | nan | 0 | TK_NotStart | 1391426496 | 111 | 1391426496_111
25863-821008 | TT_Task | Fitout 1 (including Transport) HZB #21 | 24/10/2022 | 28/10/2022 | nan | nan | 0 | TK_NotStart | 1391426496 | 112 | 1391426496_112
25863-821015 | TT_Task | Fitout 2 HZB #21 | 10/11/2022 | 06/01/2023 | nan | nan | 0 | TK_NotStart | 1391426496 | 113 | 1391426496_113
25863-822002 | TT_Task | Rohbau inkl. Oberfl?che HZB #22 | 04/05/2022 | 23/08/2022 | nan | nan | 0 | TK_NotStart | 1391426496 | 110 | 1391426496_110
25863-822006 | TT_Task | Fitout 1 (including Transport) HZA #22 | 18/08/2022 | 26/08/2022 | nan | nan | 0 | TK_NotStart | 1391426496 | 111 | 1391426496_111
25863-822008 | TT_Task | Fitout 1 (including Transport) HZB #22 | 24/08/2022 | 01/09/2022 | nan | nan | 0 | TK_NotStart | 1391426496 | 112 | 1391426496_112
25863-822015 | TT_Task | Fitout 2 HZB #22 | 13/09/2022 | 03/11/2022 | nan | nan | 0 | TK_NotStart | 1391426496 | 113 | 1391426496_113
25863-823002 | TT_Task | Rohbau inkl. Oberfl?che HZB #23 | 15/07/2022 | 01/11/2022 | nan | nan | 0 | TK_NotStart | 1391426496 | 110 | 1391426496_110
25863-823006 | TT_Task | Fitout 1 (including Transport) HZA #23 | 26/10/2022 | 04/11/2022 | nan | nan | 0 | TK_NotStart | 1391426496 | 111 | 1391426496_111
25863-823008 | TT_Task | Fitout 1 (including Transport) HZB #23 | 02/11/2022 | 10/11/2022 | nan | nan | 0 | TK_NotStart | 1391426496 | 112 | 1391426496_112
25863-823015 | TT_Task | Fitout 2 HZB #23 | 23/11/2022 | 18/01/2023 | nan | nan | 0 | TK_NotStart | 1391426496 | 113 | 1391426496_113
25863-824002 | TT_Task | Rohbau inkl. Oberfl?che HZB #24 | 27/07/2022 | 11/11/2022 | nan | nan | 0 | TK_NotStart | 1391426496 | 110 | 1391426496_110
25863-824006 | TT_Task | Fitout 1 (including Transport) HZA #24 | 08/11/2022 | 17/11/2022 | nan | nan | 0 | TK_NotStart | 1391426496 | 111 | 1391426496_111
25863-824008 | TT_Task | Fitout 1 (including Transport) HZB #24 | 14/11/2022 | 23/11/2022 | nan | nan | 0 | TK_NotStart | 1391426496 | 112 | 1391426496_112
25863-824015 | TT_Task | Fitout 2 HZB #24 | 05/12/2022 | 30/01/2023 | nan | nan | 0 | TK_NotStart | 1391426496 | 113 | 1391426496_113
25863-825002 | TT_Task | Rohbau inkl. Oberfl?che HZB #25 | 24/08/2022 | 28/11/2022 | nan | nan | 0 | TK_NotStart | 1391426496 | 110 | 1391426496_110
25863-825006 | TT_Task | Fitout 1 (including Transport) HZA #25 | 23/11/2022 | 29/11/2022 | nan | nan | 0 | TK_NotStart | 1391426496 | 111 | 1391426496_111
25863-825008 | TT_Task | Fitout 1 (including Transport) HZB #25 | 29/11/2022 | 05/12/2022 | nan | nan | 0 | TK_NotStart | 1391426496 | 112 | 1391426496_112
25863-825015 | TT_Task | Fitout 2 HZB #25 | 15/12/2022 | 09/02/2023 | nan | nan | 0 | TK_NotStart | 1391426496 | 113 | 1391426496_113
25863-826002 | TT_Task | Rohbau inkl. Oberfl?che HZB #26 | 05/09/2022 | 08/12/2022 | nan | nan | 0 | TK_NotStart | 1391426496 | 110 | 1391426496_110
25863-826006 | TT_Task | Fitout 1 (including Transport) HZA #26 | 05/12/2022 | 09/12/2022 | nan | nan | 0 | TK_NotStart | 1391426496 | 111 | 1391426496_111
25863-826008 | TT_Task | Fitout 1 (including Transport) HZB #26 | 09/12/2022 | 15/12/2022 | nan | nan | 0 | TK_NotStart | 1391426496 | 112 | 1391426496_112
25863-826015 | TT_Task | Fitout 2 HZB #26 | 03/01/2023 | 21/02/2023 | nan | nan | 0 | TK_NotStart | 1391426496 | 113 | 1391426496_113
25863-827002 | TT_Task | Rohbau inkl. Oberfl?che HZB #27 | 15/09/2022 | 20/12/2022 | nan | nan | 0 | TK_NotStart | 1391426496 | 110 | 1391426496_110
25863-827006 | TT_Task | Fitout 1 (including Transport) HZA #27 | 15/12/2022 | 21/12/2022 | nan | nan | 0 | TK_NotStart | 1391426496 | 111 | 1391426496_111
25863-827008 | TT_Task | Fitout 1 (including Transport) HZB #27 | 21/12/2022 | 03/01/2023 | nan | nan | 0 | TK_NotStart | 1391426496 | 112 | 1391426496_112
25863-827015 | TT_Task | Fitout 2 HZB #27 | 13/01/2023 | 03/03/2023 | nan | nan | 0 | TK_NotStart | 1391426496 | 113 | 1391426496_113
25863-828002 | TT_Task | Rohbau inkl. Oberfl?che HZB #28 | 27/09/2022 | 06/01/2023 | nan | nan | 0 | TK_NotStart | 1391426496 | 110 | 1391426496_110
25863-828006 | TT_Task | Fitout 1 (including Transport) HZA #28 | 03/01/2023 | 09/01/2023 | nan | nan | 0 | TK_NotStart | 1391426496 | 111 | 1391426496_111
25863-828008 | TT_Task | Fitout 1 (including Transport) HZB #28 | 09/01/2023 | 13/01/2023 | nan | nan | 0 | TK_NotStart | 1391426496 | 112 | 1391426496_112
25863-828015 | TT_Task | Fitout 2 HZB #28 | 25/01/2023 | 15/03/2023 | nan | nan | 0 | TK_NotStart | 1391426496 | 113 | 1391426496_113
25863-829002 | TT_Task | Rohbau inkl. Oberfl?che HZB #29 | 10/10/2022 | 18/01/2023 | nan | nan | 0 | TK_NotStart | 1391426496 | 110 | 1391426496_110
25863-829006 | TT_Task | Fitout 1 (including Transport) HZA #29 | 13/01/2023 | 19/01/2023 | nan | nan | 0 | TK_NotStart | 1391426496 | 111 | 1391426496_111
25863-829008 | TT_Task | Fitout 1 (including Transport) HZB #29 | 19/01/2023 | 25/01/2023 | nan | nan | 0 | TK_NotStart | 1391426496 | 112 | 1391426496_112
25863-829015 | TT_Task | Fitout 2 HZB #29 | 06/02/2023 | 27/03/2023 | nan | nan | 0 | TK_NotStart | 1391426496 | 113 | 1391426496_113
25863-830002 | TT_Task | Rohbau inkl. Oberfl?che HZB #30 | 20/10/2022 | 30/01/2023 | nan | nan | 0 | TK_NotStart | 1391426496 | 110 | 1391426496_110
25863-830006 | TT_Task | Fitout 1 (including Transport) HZA #30 | 25/01/2023 | 31/01/2023 | nan | nan | 0 | TK_NotStart | 1391426496 | 111 | 1391426496_111
25863-830008 | TT_Task | Fitout 1 (including Transport) HZB #30 | 31/01/2023 | 06/02/2023 | nan | nan | 0 | TK_NotStart | 1391426496 | 112 | 1391426496_112
25863-830015 | TT_Task | Fitout 2 HZB #30 | 16/02/2023 | 06/04/2023 | nan | nan | 0 | TK_NotStart | 1391426496 | 113 | 1391426496_113
25863-850010 | TT_Task | Einbau ?nderungspaket A #01 | 08/11/2021 | 08/11/2021 | 08/11/2021 | 08/11/2021 | 0 | TK_Complete | 1391426496 | 114 | 1391426496_114
25863-COVID-00421 | TT_Task | COVID-00421 delay in production of underframe BM5 from met-chem | 29/10/2020 | 31/10/2020 | 29/10/2020 | 31/10/2020 | 0 | TK_Complete | 1391426496 | 115 | 1391426496_115
25863-COVID-00422 | TT_Task | COVID-00422 suspension of 1st shift in CTLF-production-line in GR | 16/11/2020 | 23/11/2020 | 16/11/2020 | 23/11/2020 | 0 | TK_Complete | 1391426496 | 116 | 1391426496_116
25863-800505 | TT_Task | COVID-00422 suspension of 1st shift in CTLF-production-line in GR | 16/11/2020 | 23/11/2020 | 16/11/2020 | 23/11/2020 | 0 | TK_Complete | 1391426496 | 116 | 1391426496_116
25863-801092 | TT_Task | COVID-00421 delay in production of underframe BM5 from met-chem | 29/10/2020 | 31/10/2020 | 29/10/2020 | 31/10/2020 | 0 | TK_Complete | 1391426496 | 115 | 1391426496_115
25863-COVID-00434 | TT_Task | COVID-00434 12 wks delay for HVAC units from Kiepe | 04/12/2020 | 26/02/2021 | 04/12/2020 | 26/02/2021 | 0 | TK_Complete | 1391426496 | 117 | 1391426496_117
25863-PROC107825 | TT_Task | COVID-00434 12 wks delay for HVAC units from Kiepe | 04/12/2020 | 26/02/2021 | 04/12/2020 | 26/02/2021 | 0 | TK_Complete | 1391426496 | 117 | 1391426496_117
25863-COVID-00435 | TT_Task | COVID-00435 Delayed delivery for cables;e-cabinets from supplier KTP | 12/11/2020 | 22/11/2020 | 12/11/2020 | 22/11/2020 | 0 | TK_Complete | 1391426496 | 118 | 1391426496_118
25863-COVID-00436 | TT_Task | COVID-00436 quarantine for OPS employees in G?rlitz | 08/12/2020 | 29/12/2020 | 08/12/2020 | 29/12/2020 | 0 | TK_Complete | 1391426496 | 119 | 1391426496_119
25863-409045 | TT_Task | COVID-00435 Delayed delivery for cables;e-cabinets from supplier KTP | 12/11/2020 | 22/11/2020 | 12/11/2020 | 22/11/2020 | 0 | TK_Complete | 1391426496 | 118 | 1391426496_118
25863-802001 | TT_Task | COVID-00436 quarantine for OPS employees in G?rlitz | 08/12/2020 | 29/12/2020 | 08/12/2020 | 29/12/2020 | 0 | TK_Complete | 1391426496 | 119 | 1391426496_119
25863-600010 | TT_Task | BD CBY - MBOM Implementation, Logistics Preparation, C Parts Lead Time, Tooling Definition, Fabrication, Installa | 15/06/2021 | 20/09/2021 | 15/06/2021 | 20/09/2021 | 0 | TK_Complete | 1391426496 | 109 | 1391426496_109
25863-161030 | TT_Task | Purchasing Option for 10 additional vehicles (until 31.12.2021) | 03/01/2022 | 03/01/2022 | nan | nan | 39560 | TK_NotStart | 1391426496 | 120 | 1391426496_120
25863-COVID-00447 | TT_Task | COVID-00447 9 day delay on milestone Start of F02- Production in Bautzen | 16/03/2021 | 29/03/2021 | 16/03/2021 | 29/03/2021 | 0 | TK_Complete | 1391426496 | 121 | 1391426496_121
25863-801029 | TT_Task | COVID-00447 9 day delay on milestone Start of F02- Production in Bautzen | 16/03/2021 | 29/03/2021 | 16/03/2021 | 29/03/2021 | 0 | TK_Complete | 1391426496 | 121 | 1391426496_121
25863-801059 | TT_Task | COVID-00447 9 day delay on milestone Start of F02- Production in Bautzen | 16/03/2021 | 29/03/2021 | 16/03/2021 | 29/03/2021 | 0 | TK_Complete | 1391426496 | 121 | 1391426496_121
25863-801079 | TT_Task | COVID-00447 9 day delay on milestone Start of F02- Production in Bautzen | 16/03/2021 | 29/03/2021 | 16/03/2021 | 29/03/2021 | 0 | TK_Complete | 1391426496 | 121 | 1391426496_121
25863-850020 | TT_Task | Einbau ?nderungspaket B #01 | 08/11/2021 | 08/11/2021 | 08/11/2021 | 08/11/2021 | 0 | TK_Complete | 1391426496 | 114 | 1391426496_114
CUS0080 | TT_Task | Technical presentations and questions delivery to customer | 26/04/2021 | 30/04/2021 | 14/04/2021 | 12/05/2021 | 0 | TK_Complete | -569914933 | 1 | -569914933_1
CUS0090 | TT_Task | Customer Presentations | 26/04/2021 | 07/05/2021 | 26/04/2021 | 23/07/2021 | 0 | TK_Complete | -569914933 | 1 | -569914933_1
CUS0085 | TT_Task | Customer Review of Submittal | 15/04/2021 | 12/05/2021 | 15/04/2021 | 13/05/2021 | 0 | TK_Complete | -569914933 | 2 | -569914933_2
PM1005 | TT_Task | Payment Milestone 1 - Metra Review/Approval | 13/04/2021 | 10/05/2021 | 13/04/2021 | 29/04/2021 | 0 | TK_Complete | -569914933 | 3 | -569914933_3
PM1015 | TT_Task | Payment Milestone 2 - Metra Review/Approval | 07/06/2021 | 02/07/2021 | 07/06/2021 | 30/06/2021 | 0 | TK_Complete | -569914933 | 3 | -569914933_3
PM1025 | TT_Task | Payment Milestone 3 - Metra Review/Approval | 29/11/2021 | 04/01/2022 | 24/11/2021 | 07/12/2021 | 0 | TK_Complete | -569914933 | 3 | -569914933_3
PM1035 | TT_Task | Payment Milestone 4 - Metra Review/Approval | 25/01/2022 | 22/02/2022 | 25/01/2022 | 24/02/2022 | 0 | TK_Complete | -569914933 | 3 | -569914933_3
PM1045 | TT_Task | Payment Milestone 5 - Metra Review/Approval | 28/10/2022 | 24/11/2022 | nan | nan | 0 | TK_NotStart | -569914933 | 3 | -569914933_3
PM1055 | TT_Task | Payment Milestone 6 - Metra Review/Approval | 06/03/2023 | 31/03/2023 | nan | nan | 0 | TK_NotStart | -569914933 | 3 | -569914933_3
PM1065 | TT_Task | Payment Milestone 7 - Metra Review/Approval | 28/01/2027 | 25/02/2027 | nan | nan | 0 | TK_NotStart | -569914933 | 3 | -569914933_3
PM1075 | TT_Task | Payment Milestone 9 - Metra Review/Approval | 12/05/2027 | 09/06/2027 | nan | nan | 0 | TK_NotStart | -569914933 | 3 | -569914933_3
PM1085 | TT_Task | Payment Milestone 10 - Metra Review/Approval | 24/01/2024 | 21/02/2024 | nan | nan | 0 | TK_NotStart | -569914933 | 3 | -569914933_3
PM1175 | TT_Task | Payment Milestone 14 - Metra Review/Approval | 21/10/2024 | 15/11/2024 | nan | nan | 0 | TK_NotStart | -569914933 | 3 | -569914933_3
PM1195 | TT_Task | Payment Milestone 16 - Metra Review/Approval | 05/05/2027 | 02/06/2027 | nan | nan | 0 | TK_NotStart | -569914933 | 3 | -569914933_3
PM1205 | TT_Task | Payment Milestone 17 - Metra Review/Approval | 21/01/2033 | 17/02/2033 | nan | nan | 0 | TK_NotStart | -569914933 | 3 | -569914933_3
DR1000 | TT_Task | Sub-System PDR Packages Preparation | 25/10/2021 | 24/01/2022 | 25/10/2021 | 22/12/2021 | 0 | TK_Complete | -569914933 | 4 | -569914933_4
DR1010 | TT_Task | Sub-System PDR Package Deliveries | 17/11/2021 | 14/12/2021 | 05/11/2021 | 10/01/2022 | 0 | TK_Complete | -569914933 | 4 | -569914933_4
DR1020 | TT_Task | Sub-System PDR Packages - Customer Review | 08/11/2021 | 10/12/2021 | 08/11/2021 | 19/01/2022 | 0 | TK_Complete | -569914933 | 4 | -569914933_4
DR1030 | TT_Task | Sub-System PDR Customer Approval (Split into multiple submittals for individual review) | 30/11/2021 | 07/01/2022 | 30/11/2021 | nan | 0 | TK_Active | -569914933 | 2 | -569914933_2
DR1040 | TT_Task | Sub-System IDR Packages Preparation | 29/06/2022 | 27/09/2022 | nan | nan | 0 | TK_NotStart | -569914933 | 5 | -569914933_5
DR1050 | TT_Task | Sub-System IDR Package Deliveries | 04/08/2022 | 29/09/2022 | nan | nan | 232 | TK_NotStart | -569914933 | 5 | -569914933_5
DR1060 | TT_Task | Sub-System IDR Packages - Customer Review | 15/09/2022 | 13/10/2022 | nan | nan | 0 | TK_NotStart | -569914933 | 5 | -569914933_5
DR1070 | TT_Task | Sub-System IDR Customer Approval (Split into multiple submittals for individual review) | 29/09/2022 | 27/10/2022 | nan | nan | 0 | TK_NotStart | -569914933 | 2 | -569914933_2
DR1080 | TT_Task | Sub-System FDR Packages Preparation | 14/10/2022 | 13/01/2023 | nan | nan | 0 | TK_NotStart | -569914933 | 6 | -569914933_6
DR1090 | TT_Task | Sub-System FDR Package Deliveries | 11/11/2022 | 19/01/2023 | nan | nan | 0 | TK_NotStart | -569914933 | 6 | -569914933_6
DR1100 | TT_Task | Sub-System FDR Packages - Customer Review | 13/01/2023 | 09/02/2023 | nan | nan | 0 | TK_NotStart | -569914933 | 6 | -569914933_6
DR1110 | TT_Task | Sub-System FDR Customer Approval (Split into multiple submittals for individual review) | 03/02/2023 | 03/03/2023 | nan | nan | 0 | TK_NotStart | -569914933 | 2 | -569914933_2
DR1120 | TT_Task | CBS PDR Package Preparation | 16/04/2021 | 04/06/2021 | 16/04/2021 | 02/06/2021 | 0 | TK_Complete | -569914933 | 7 | -569914933_7
DR1140 | TT_Task | CBS PDR Package - Customer Review | 04/06/2021 | 24/06/2021 | 04/06/2021 | 22/06/2021 | 0 | TK_Complete | -569914933 | 7 | -569914933_7
DR1160 | TT_Task | CBS IDR Package Preparation | 30/09/2021 | 24/01/2022 | 01/09/2021 | 01/02/2022 | 0 | TK_Complete | -569914933 | 7 | -569914933_7
DR1180 | TT_Task | CBS IDR Package - Customer Review ; Meeting | 03/02/2022 | 24/02/2022 | 03/02/2022 | 02/03/2022 | 0 | TK_Complete | -569914933 | 7 | -569914933_7
DR1200 | TT_Task | CBS FDR Package Preparation | 31/03/2022 | 22/07/2022 | nan | nan | 0 | TK_NotStart | -569914933 | 6 | -569914933_6
DR1220 | TT_Task | CBS FDR Package - Customer Review | 25/07/2022 | 12/08/2022 | nan | nan | 0 | TK_NotStart | -569914933 | 6 | -569914933_6
DR1145 | TT_Task | CBS PDR Package - Customer Review Meeting | 12/07/2021 | 12/07/2021 | 21/06/2021 | 22/06/2021 | 0 | TK_Complete | -569914933 | 7 | -569914933_7
DR1240 | TT_Task | Bogie PDR Package Preparation | 31/08/2021 | 01/11/2021 | 31/08/2021 | 21/10/2021 | 0 | TK_Complete | -569914933 | 8 | -569914933_8
DR1260 | TT_Task | Bogie PDR Package - Customer Review | 25/10/2021 | 12/11/2021 | 25/10/2021 | 09/12/2021 | 0 | TK_Complete | -569914933 | 8 | -569914933_8
DR1280 | TT_Task | Bogie IDR Package Preparation | 17/06/2022 | 21/09/2022 | 10/12/2021 | nan | 0 | TK_Active | -569914933 | 8 | -569914933_8
DR1300 | TT_Task | Bogie IDR Package - Customer Review | 02/05/2022 | 26/05/2022 | nan | nan | 0 | TK_NotStart | -569914933 | 8 | -569914933_8
DR1320 | TT_Task | Bogie FDR Package Preparation | 21/06/2022 | 20/09/2022 | nan | nan | 0 | TK_NotStart | -569914933 | 6 | -569914933_6
DR1340 | TT_Task | Bogie FDR Package - Customer Review | 21/09/2022 | 12/10/2022 | nan | nan | 0 | TK_NotStart | -569914933 | 6 | -569914933_6
A1230 | TT_Task | Synthesis Module - Requirement Synthesis | 05/04/2021 | 27/09/2021 | 05/04/2021 | 27/09/2021 | 0 | TK_Complete | -569914933 | 9 | -569914933_9
A1240 | TT_Task | Requirement Specification Train Level | 05/04/2021 | 05/11/2021 | 05/04/2021 | 30/11/2021 | 0 | TK_Complete | -569914933 | 10 | -569914933_10
A1250 | TT_Task | Requirement Specification Component Level / Transversal Requirements Allocation | 13/07/2021 | 10/12/2021 | 13/07/2021 | 10/12/2021 | 0 | TK_Complete | -569914933 | 10 | -569914933_10
A1260 | TT_Task | Architecture Design Functional Specification | 05/04/2021 | 08/02/2022 | 05/04/2021 | 30/11/2021 | 0 | TK_Complete | -569914933 | 9 | -569914933_9
A1270 | TT_Task | Technical Purchasing Specifications | 02/06/2021 | 01/03/2022 | 02/06/2021 | nan | 0 | TK_Active | -569914933 | 11 | -569914933_11
A1280 | TT_Task | Workshop with Suppliers | 15/07/2021 | 14/07/2022 | 15/07/2021 | nan | 0 | TK_Active | -569914933 | 12 | -569914933_12
A1290 | TT_Task | Business Awards | 22/04/2021 | 14/12/2021 | 22/04/2021 | nan | 0 | TK_Active | -569914933 | 13 | -569914933_13
A1300 | TT_Task | 3D Frozen from Suppliers | 30/11/2021 | 15/08/2022 | 30/11/2021 | nan | 0 | TK_Active | -569914933 | 14 | -569914933_14
A1310 | TT_Task | 2D/3D Master from Supplier | 16/08/2022 | 17/01/2023 | nan | nan | 1080 | TK_NotStart | -569914933 | 14 | -569914933_14
A1320 | TT_Task | CBS Phase I | 05/04/2021 | 08/02/2022 | 05/04/2021 | 26/11/2021 | 0 | TK_Complete | -569914933 | 15 | -569914933_15
A1330 | TT_Task | CBS Phase P | 29/11/2021 | 05/04/2022 | 29/11/2021 | nan | 0 | TK_Active | -569914933 | 15 | -569914933_15
A1340 | TT_Task | CBS Phase C | 06/04/2022 | 18/10/2022 | nan | nan | 696 | TK_NotStart | -569914933 | 15 | -569914933_15
A1350 | TT_Task | Interior Phase I | 05/04/2021 | 09/03/2022 | 05/04/2021 | 31/03/2022 | 0 | TK_Complete | -569914933 | 16 | -569914933_16
A1360 | TT_Task | Interior Phase P | 31/03/2022 | 27/09/2022 | nan | nan | 0 | TK_NotStart | -569914933 | 16 | -569914933_16
A1370 | TT_Task | Interior Phase C | 28/09/2022 | 02/03/2023 | nan | nan | 832 | TK_NotStart | -569914933 | 16 | -569914933_16
A1380 | TT_Task | Fitting Phase I | 05/04/2021 | 09/03/2022 | 05/04/2021 | 31/03/2022 | 0 | TK_Complete | -569914933 | 17 | -569914933_17
A1390 | TT_Task | Fitting Phase P | 31/03/2022 | 27/09/2022 | nan | nan | 0 | TK_NotStart | -569914933 | 17 | -569914933_17
A1400 | TT_Task | Fitting Phase C | 28/09/2022 | 02/03/2023 | nan | nan | 832 | TK_NotStart | -569914933 | 17 | -569914933_17
A1410 | TT_Task | MI Electrical Phase I | 05/04/2021 | 09/03/2022 | 05/04/2021 | 31/03/2022 | 0 | TK_Complete | -569914933 | 18 | -569914933_18
A1420 | TT_Task | MI Electrical Phase P | 31/03/2022 | 27/09/2022 | nan | nan | 0 | TK_NotStart | -569914933 | 18 | -569914933_18
A1430 | TT_Task | MI Electrical Phase C | 28/09/2022 | 02/03/2023 | nan | nan | 832 | TK_NotStart | -569914933 | 18 | -569914933_18
A1440 | TT_Task | Synoptics Development | 05/04/2021 | 04/05/2022 | 05/04/2021 | nan | 0 | TK_Active | -569914933 | 19 | -569914933_19
A1450 | TT_Task | Schematics Development | 03/09/2021 | 03/06/2022 | 03/09/2021 | nan | 616 | TK_Active | -569914933 | 19 | -569914933_19
A1460 | TT_Task | Electrical Database | 30/11/2021 | 03/06/2022 | 30/11/2021 | nan | 0 | TK_Active | -569914933 | 20 | -569914933_20
A1470 | TT_Task | Electrical Interface Specifications from Suppliers | 30/06/2021 | 01/04/2022 | 30/06/2021 | nan | 0 | TK_Active | -569914933 | 20 | -569914933_20
A1480 | TT_Task | Harness Design Phase P | 01/04/2022 | 28/09/2022 | nan | nan | 0 | TK_NotStart | -569914933 | 21 | -569914933_21
A1490 | TT_Task | Harness Design Phase C | 29/09/2022 | 07/02/2023 | nan | nan | 128 | TK_NotStart | -569914933 | 21 | -569914933_21
A2980 | TT_Task | Software Quality Plans | 05/04/2021 | 09/03/2022 | 05/04/2021 | nan | 0 | TK_Active | -569914933 | 22 | -569914933_22
A2990 | TT_Task | Implement Software Specification and Coding | 12/04/2022 | 14/03/2023 | nan | nan | 0 | TK_NotStart | -569914933 | 22 | -569914933_22
A3000 | TT_Task | Software Overall Test Reports | 15/03/2023 | 22/06/2023 | nan | nan | 0 | TK_NotStart | -569914933 | 23 | -569914933_23
A3010 | TT_Task | Network Integration Test Reports | 15/03/2023 | 22/06/2023 | nan | nan | 1072 | TK_NotStart | -569914933 | 23 | -569914933_23
A3020 | TT_Task | Software Source Code Verification Report | 07/10/2022 | 14/03/2023 | nan | nan | 0 | TK_NotStart | -569914933 | 22 | -569914933_22
A1500 | TT_Task | Technical Purchasing Specification - Doors Ext | 05/04/2021 | 28/05/2021 | 05/04/2021 | 03/06/2021 | 0 | TK_Complete | -569914933 | 24 | -569914933_24
A1510 | TT_Task | PO - Doors Ext | 11/11/2021 | 15/11/2021 | 11/11/2021 | 01/03/2022 | 0 | TK_Complete | -569914933 | 25 | -569914933_25
A1520 | TT_Task | Lead Time - Doors Ext | 02/03/2022 | 15/05/2023 | 02/03/2022 | nan | 32 | TK_Active | -569914933 | 26 | -569914933_26
A1505 | TT_Task | Business Award - Doors Ext (D1) | 05/04/2021 | 21/05/2021 | 05/04/2021 | 22/04/2021 | 0 | TK_Complete | -569914933 | 13 | -569914933_13
A1540 | TT_Task | Technical Purchasing Specification - Floor | 30/07/2021 | 24/08/2021 | 30/07/2021 | 02/08/2021 | 0 | TK_Complete | -569914933 | 11 | -569914933_11
A1560 | TT_Task | PO - Floor | 12/10/2021 | 08/12/2021 | 12/10/2021 | 25/02/2022 | 0 | TK_Complete | -569914933 | 25 | -569914933_25
A1570 | TT_Task | Lead Time - Floor | 28/02/2022 | 25/07/2023 | 28/02/2022 | nan | 424 | TK_Active | -569914933 | 26 | -569914933_26
A1550 | TT_Task | Business Award - Floor (D3) | 03/08/2021 | 27/09/2021 | 03/08/2021 | 08/10/2021 | 0 | TK_Complete | -569914933 | 27 | -569914933_27
A1580 | TT_Task | Technical Purchasing Specification - Coupler | 05/04/2021 | 28/05/2021 | 05/04/2021 | 03/06/2021 | 0 | TK_Complete | -569914933 | 11 | -569914933_11
A1600 | TT_Task | PO - Coupler | 26/08/2021 | 20/09/2021 | 26/08/2021 | 19/10/2021 | 0 | TK_Complete | -569914933 | 28 | -569914933_28
A1610 | TT_Task | Lead Time - Coupler | 29/10/2021 | 13/04/2023 | 20/10/2021 | nan | 1224 | TK_Active | -569914933 | 26 | -569914933_26
A1590 | TT_Task | Business Award - Coupler (D1) | 16/04/2021 | 04/06/2021 | 16/04/2021 | 10/05/2021 | 0 | TK_Complete | -569914933 | 13 | -569914933_13
A1660 | TT_Task | Technical Purchasing Specification - Diaphram | 01/06/2021 | 04/04/2022 | 30/04/2021 | 26/07/2021 | 0 | TK_Complete | -569914933 | 11 | -569914933_11
A1680 | TT_Task | PO - Diaphram | 18/10/2021 | 15/11/2021 | 18/10/2021 | 01/02/2022 | 0 | TK_Complete | -569914933 | 28 | -569914933_28
A1690 | TT_Task | Lead Time - Diaphram | 02/02/2022 | 31/05/2023 | 02/02/2022 | nan | 912 | TK_Active | -569914933 | 26 | -569914933_26
A1670 | TT_Task | Business Award - Diaphram (D3) | 30/06/2021 | 15/10/2021 | 30/06/2021 | 14/10/2021 | 0 | TK_Complete | -569914933 | 27 | -569914933_27
A1700 | TT_Task | Technical Purchasing Specification - Toilets | 05/04/2021 | 09/09/2021 | 05/04/2021 | 02/06/2021 | 0 | TK_Complete | -569914933 | 29 | -569914933_29
A1720 | TT_Task | PO - Toilets | 15/11/2021 | 13/01/2022 | 15/11/2021 | 17/02/2022 | 0 | TK_Complete | -569914933 | 29 | -569914933_29
A1730 | TT_Task | Lead Time - Toilets | 18/02/2022 | 20/07/2023 | 18/02/2022 | nan | 648 | TK_Active | -569914933 | 29 | -569914933_29
A1710 | TT_Task | Business Award - Toilets (D2) | 26/07/2021 | 15/09/2021 | 26/07/2021 | 15/11/2021 | 0 | TK_Complete | -569914933 | 13 | -569914933_13
A1740 | TT_Task | Technical Purchasing Specification - Passenger HVAC | 05/04/2021 | 28/05/2021 | 05/04/2021 | 03/06/2021 | 0 | TK_Complete | -569914933 | 30 | -569914933_30
A1760 | TT_Task | PO - Passenger HVAC | 19/08/2021 | 15/11/2021 | 19/08/2021 | 04/03/2022 | 0 | TK_Complete | -569914933 | 30 | -569914933_30
A1770 | TT_Task | Lead Time - Passenger HVAC | 07/03/2022 | 24/04/2023 | 07/03/2022 | nan | 616 | TK_Active | -569914933 | 26 | -569914933_26
A1750 | TT_Task | Business Award - Passenger HVAC (D1) | 05/04/2021 | 21/05/2021 | 05/04/2021 | 22/04/2021 | 0 | TK_Complete | -569914933 | 30 | -569914933_30
A1780 | TT_Task | Technical Purchasing Specification - Batteries | 01/06/2021 | 04/04/2022 | 30/04/2021 | 07/07/2021 | 0 | TK_Complete | -569914933 | 31 | -569914933_31
A1800 | TT_Task | PO - Batteries | 25/10/2021 | 15/11/2021 | 25/10/2021 | 25/03/2022 | 0 | TK_Complete | -569914933 | 31 | -569914933_31
A1810 | TT_Task | Lead Time - Batteries | 28/03/2022 | 12/07/2023 | 28/03/2022 | nan | 640 | TK_Active | -569914933 | 26 | -569914933_26
A1790 | TT_Task | Business Award - Batteries (D3) | 30/06/2021 | 06/10/2021 | 30/06/2021 | 22/10/2021 | 0 | TK_Complete | -569914933 | 27 | -569914933_27
A1860 | TT_Task | Technical Purchasing Specification - Brake Modules | 05/04/2021 | 28/05/2021 | 05/04/2021 | 03/06/2021 | 0 | TK_Complete | -569914933 | 32 | -569914933_32
A1880 | TT_Task | PO - Brake Modules | 26/08/2021 | 15/11/2021 | 26/08/2021 | 31/03/2022 | 0 | TK_Complete | -569914933 | 32 | -569914933_32
A1890 | TT_Task | Lead Time - Brake Modules | 31/03/2022 | 18/07/2023 | nan | nan | 392 | TK_NotStart | -569914933 | 32 | -569914933_32
A1870 | TT_Task | Business Award - Brake Modules (D1) | 05/04/2021 | 21/05/2021 | 05/04/2021 | 22/04/2021 | 0 | TK_Complete | -569914933 | 32 | -569914933_32
A1900 | TT_Task | Technical Purchasing Specification - Passenger Seats | 05/04/2021 | 09/09/2021 | 05/04/2021 | 02/06/2021 | 0 | TK_Complete | -569914933 | 33 | -569914933_33
A1920 | TT_Task | PO - Passenger Seats | 18/10/2021 | 19/11/2021 | 18/10/2021 | 29/11/2021 | 0 | TK_Complete | -569914933 | 33 | -569914933_33
A1930 | TT_Task | Lead Time - Passenger Seats | 30/11/2021 | 31/08/2023 | 30/11/2021 | nan | 608 | TK_Active | -569914933 | 33 | -569914933_33
A1910 | TT_Task | Business Award - Passenger Seats (D2) | 06/08/2021 | 28/09/2021 | 06/08/2021 | 15/10/2021 | 0 | TK_Complete | -569914933 | 33 | -569914933_33
A1980 | TT_Task | Technical Purchasing Specification - Windows | 01/06/2021 | 04/04/2022 | 30/04/2021 | 28/07/2021 | 0 | TK_Complete | -569914933 | 11 | -569914933_11
A2000 | TT_Task | PO - Windows | 25/10/2021 | 29/11/2021 | 25/10/2021 | 07/02/2022 | 0 | TK_Complete | -569914933 | 25 | -569914933_25
A2010 | TT_Task | Lead Time - Windows | 08/02/2022 | 28/04/2023 | 08/02/2022 | nan | 576 | TK_Active | -569914933 | 26 | -569914933_26
A1990 | TT_Task | Business Award - Windows (D3) | 27/08/2021 | 14/10/2021 | 27/08/2021 | 22/10/2021 | 0 | TK_Complete | -569914933 | 27 | -569914933_27
A2020 | TT_Task | Technical Purchasing Specification - PACIS | 01/06/2021 | 04/04/2022 | 30/04/2021 | 08/07/2021 | 0 | TK_Complete | -569914933 | 11 | -569914933_11
A2040 | TT_Task | PO - PACIS | 19/10/2021 | 15/11/2021 | 19/10/2021 | 25/02/2022 | 0 | TK_Complete | -569914933 | 34 | -569914933_34
A2050 | TT_Task | Lead Time - PACIS | 28/02/2022 | 25/07/2023 | 28/02/2022 | nan | 400 | TK_Active | -569914933 | 34 | -569914933_34
A2030 | TT_Task | Business Award - PACIS (D3) | 01/09/2021 | 26/10/2021 | 01/09/2021 | 18/10/2021 | 0 | TK_Complete | -569914933 | 27 | -569914933_27
A3030 | TT_Task | Technical Purchasing Specification - Wheelchair Lift | 05/04/2021 | 28/05/2021 | 05/04/2021 | 05/05/2021 | 0 | TK_Complete | -569914933 | 35 | -569914933_35
A3040 | TT_Task | PO - Wheelchair Lift | 01/10/2021 | 29/10/2021 | 01/10/2021 | 15/02/2022 | 0 | TK_Complete | -569914933 | 35 | -569914933_35
A3050 | TT_Task | Lead Time - Wheelchair Lift | 16/02/2022 | 02/05/2023 | 16/02/2022 | nan | 488 | TK_Active | -569914933 | 35 | -569914933_35
A3060 | TT_Task | Business Award - Wheelchair Lift (D1) | 16/04/2021 | 04/06/2021 | 16/04/2021 | 20/07/2021 | 0 | TK_Complete | -569914933 | 35 | -569914933_35
A3080 | TT_Task | Technical Purchasing Specification - Signalling | 01/06/2021 | 04/04/2022 | 30/04/2021 | 22/09/2021 | 0 | TK_Complete | -569914933 | 11 | -569914933_11
A3090 | TT_Task | PO - Signalling | 07/02/2022 | 11/03/2022 | 07/02/2022 | 29/03/2022 | 0 | TK_Complete | -569914933 | 28 | -569914933_28
A3100 | TT_Task | Lead Time - Signalling | 03/08/2022 | 31/08/2023 | nan | nan | 496 | TK_NotStart | -569914933 | 26 | -569914933_26
A3110 | TT_Task | Business Award - Signalling (D3) | 29/10/2021 | 05/01/2022 | 19/10/2021 | 29/03/2022 | 0 | TK_Complete | -569914933 | 27 | -569914933_27
A2880 | TT_Task | Technical Purchasing Specification - Interiors | 05/04/2021 | 28/05/2021 | 05/04/2021 | 03/06/2021 | 0 | TK_Complete | -569914933 | 24 | -569914933_24
A2890 | TT_Task | PO - Interiors | 22/10/2021 | 15/11/2021 | 22/10/2021 | 01/03/2022 | 0 | TK_Complete | -569914933 | 25 | -569914933_25
A2900 | TT_Task | Lead Time - Interiors | 02/03/2022 | 30/03/2023 | 02/03/2022 | nan | 0 | TK_Active | -569914933 | 26 | -569914933_26
A2910 | TT_Task | Business Award - Interiors (D1) | 16/04/2021 | 04/06/2021 | 16/04/2021 | 22/04/2021 | 0 | TK_Complete | -569914933 | 13 | -569914933_13
A2915 | TT_Task | Transport | 31/03/2023 | 14/07/2023 | nan | nan | 768 | TK_NotStart | -569914933 | 36 | -569914933_36
A2930 | TT_Task | Technical Purchasing Specification - Bogies | 05/04/2021 | 28/05/2021 | 05/04/2021 | 03/06/2021 | 0 | TK_Complete | -569914933 | 11 | -569914933_11
A2940 | TT_Task | PO - Bogies | 08/06/2021 | 30/06/2021 | 08/06/2021 | 15/07/2021 | 0 | TK_Complete | -569914933 | 28 | -569914933_28
A2950 | TT_Task | Lead Time - Bogies | 14/02/2022 | 28/04/2023 | 14/02/2022 | nan | 840 | TK_Active | -569914933 | 26 | -569914933_26
A2960 | TT_Task | Business Award - Bogies (D1) | 05/04/2021 | 21/05/2021 | 05/04/2021 | 26/04/2021 | 0 | TK_Complete | -569914933 | 13 | -569914933_13
A2060 | TT_Task | Interiors - Requirements Specification Delivery | 31/01/2022 | 27/01/2023 | 06/10/2021 | nan | 1440 | TK_Active | -569914933 | 24 | -569914933_24
A3130 | TT_Task | Bogie Phase I | 05/04/2021 | 04/11/2021 | 05/04/2021 | 04/11/2021 | 0 | TK_Complete | -569914933 | 37 | -569914933_37
A3140 | TT_Task | Bogie Phase P | 05/11/2021 | 12/08/2022 | 05/11/2021 | nan | 0 | TK_Active | -569914933 | 37 | -569914933_37
A3150 | TT_Task | Bogie Phase C | 15/08/2022 | 20/12/2022 | nan | nan | 0 | TK_NotStart | -569914933 | 37 | -569914933_37
A2070 | TT_Task | Train Electrical - Schematics Design | 05/04/2021 | 31/03/2022 | 05/04/2021 | nan | 0 | TK_Active | -569914933 | 38 | -569914933_38
A2080 | TT_Task | NEO Process - Harness Design (pilot) | 02/02/2022 | 11/11/2022 | 04/01/2022 | nan | 0 | TK_Active | -569914933 | 39 | -569914933_39
A2220 | TT_Task | NEO Process - Harness Design (serial) | 14/10/2022 | 04/08/2023 | nan | nan | 0 | TK_NotStart | -569914933 | 39 | -569914933_39
A2090 | TT_Task | Electrical Compo (Cable ; Connectors) | 14/10/2022 | 24/02/2023 | nan | nan | 136 | TK_NotStart | -569914933 | 40 | -569914933_40
A2100 | TT_Task | Mechanical Compo (Covers, Bulkhead Crossing) | 14/10/2022 | 24/02/2023 | nan | nan | 136 | TK_NotStart | -569914933 | 41 | -569914933_41
A2110 | TT_Task | Sheetmetal Work | 14/10/2022 | 23/01/2023 | nan | nan | 320 | TK_NotStart | -569914933 | 42 | -569914933_42
A2120 | TT_Task | Industrialization | 14/10/2022 | 21/03/2023 | nan | nan | 0 | TK_NotStart | -569914933 | 43 | -569914933_43
A2130 | TT_Task | Harness Manufacturing (pilot) | 11/11/2022 | 21/03/2023 | nan | nan | 728 | TK_NotStart | -569914933 | 44 | -569914933_44
A2360 | TT_Task | Harness Manufacturing (serial) | 07/08/2023 | 01/09/2023 | nan | nan | 808 | TK_NotStart | -569914933 | 44 | -569914933_44
A2140 | TT_Task | 3D Design ready and shared with manufacturing tooling manufacturer | 01/06/2021 | 01/06/2022 | 03/05/2021 | nan | 0 | TK_Active | -569914933 | 45 | -569914933_45
A2150 | TT_Task | 2D Design ready and shared with manufacturing tooling manufacturer | 04/04/2022 | 12/10/2022 | nan | nan | 728 | TK_NotStart | -569914933 | 45 | -569914933_45
A2160 | TT_Task | Specification for Robots and Line RFQ | 05/04/2021 | 13/07/2021 | 05/04/2021 | 05/05/2021 | 0 | TK_Complete | -569914933 | 46 | -569914933_46
A2170 | TT_Task | Quotes from Integrators | 19/04/2021 | 17/05/2021 | 19/04/2021 | 10/05/2021 | 0 | TK_Complete | -569914933 | 47 | -569914933_47
A2180 | TT_Task | PO to Line Builder (For Phase 1) | 07/06/2021 | 02/07/2021 | 07/06/2021 | 25/06/2021 | 0 | TK_Complete | -569914933 | 48 | -569914933_48
A2190 | TT_Task | Process Confirmation (Phase 1) | 04/08/2021 | 26/08/2021 | 28/06/2021 | 31/12/2021 | 0 | TK_Complete | -569914933 | 49 | -569914933_49
A2200 | TT_Task | Purchasing Long Lead Items for the line: Robots, Welding Equip,Welding Guns,KBK | 31/03/2022 | 22/07/2022 | nan | nan | 0 | TK_NotStart | -569914933 | 50 | -569914933_50
A2210 | TT_Task | Shipping and Logistics | 27/06/2022 | 06/12/2022 | nan | nan | 174 | TK_NotStart | -569914933 | 36 | -569914933_36
A2230 | TT_Task | Installation | 27/06/2022 | 16/01/2023 | nan | nan | 0 | TK_NotStart | -569914933 | 51 | -569914933_51
A2240 | TT_Task | Commissioning (Phase 2) | 19/04/2022 | 16/01/2023 | nan | nan | 0 | TK_NotStart | -569914933 | 49 | -569914933_49
A2250 | TT_Task | Handover | 16/01/2023 | 09/03/2023 | nan | nan | 594 | TK_NotStart | -569914933 | 52 | -569914933_52
A2151 | TT_Task | CBS facility steel lead time | 30/04/2021 | 27/08/2021 | 05/04/2021 | 02/08/2021 | 0 | TK_Complete | -569914933 | 53 | -569914933_53
A2155 | TT_Task | CBS facility build - Workshop | 15/09/2021 | 17/05/2022 | 15/09/2021 | nan | 0 | TK_Active | -569914933 | 54 | -569914933_54
A2157 | TT_Task | CBS facility build - office | 02/05/2022 | 29/08/2022 | nan | nan | 726 | TK_NotStart | -569914933 | 54 | -569914933_54
D2151 | TT_Task | Delay Event - CBS facility steel lead time (LeChase) | 03/08/2021 | 14/09/2021 | 03/08/2021 | 14/09/2021 | 0 | TK_Complete | -569914933 | 53 | -569914933_53
A2260 | TT_Task | Fixtures for Sub-assemblies stations:PO, Shipment ; Installation | 31/03/2022 | 22/07/2022 | nan | nan | 0 | TK_NotStart | -569914933 | 55 | -569914933_55
A2270 | TT_Task | Fixtures for Mainline Stations: PO, Shipment ; Installation | 27/05/2022 | 14/09/2022 | nan | nan | 0 | TK_NotStart | -569914933 | 55 | -569914933_55
A2280 | TT_Task | Qualifications for Manual Processes | 25/07/2022 | 12/12/2022 | nan | nan | 0 | TK_NotStart | -569914933 | 56 | -569914933_56
A2290 | TT_Task | Qualifications for Automated Processes | 15/09/2022 | 01/12/2022 | nan | nan | 0 | TK_NotStart | -569914933 | 56 | -569914933_56
A2300 | TT_Task | Robots Programming | 13/12/2022 | 28/02/2023 | nan | nan | 0 | TK_NotStart | -569914933 | 57 | -569914933_57
A2340 | TT_Task | Build 1st Carshell - Cab (Detailed below) | 01/03/2023 | 23/06/2023 | nan | nan | 0 | TK_NotStart | -569914933 | 58 | -569914933_58
A2490 | TT_Task | Build 2nd Carshell - Trailer with Toilet | 14/03/2023 | 12/07/2023 | nan | nan | 0 | TK_NotStart | -569914933 | 59 | -569914933_59
A2500 | TT_Task | Build 3rd Carshell - Trailer with out Toilet | 27/03/2023 | 25/07/2023 | nan | nan | 208 | TK_NotStart | -569914933 | 59 | -569914933_59
A2335 | TT_Task | CBS0 Assembly | 01/03/2023 | 22/06/2023 | nan | nan | 0 | TK_NotStart | -569914933 | 54 | -569914933_54
A2338 | TT_Task | CBS0 - CBS Structural Qualification Testing | 28/07/2023 | 23/10/2023 | nan | nan | 0 | TK_NotStart | -569914933 | 60 | -569914933_60
A2350 | TT_Task | FAI - Carbody Shell | 19/06/2023 | 23/06/2023 | nan | nan | 176 | TK_NotStart | -569914933 | 61 | -569914933_61
A3160 | TT_Task | Minor Subs - Arc Weld | 01/03/2023 | 13/03/2023 | nan | nan | 0 | TK_NotStart | -569914933 | 62 | -569914933_62
A3170 | TT_Task | Large Sub - Cross Beam Upper Floor | 14/03/2023 | 24/03/2023 | nan | nan | 0 | TK_NotStart | -569914933 | 63 | -569914933_63
A3190 | TT_Task | Large Sub - Upper Floor | 27/03/2023 | 06/04/2023 | nan | nan | 0 | TK_NotStart | -569914933 | 63 | -569914933_63
A3200 | TT_Task | Large Sub - Lower Floor | 27/03/2023 | 06/04/2023 | nan | nan | 0 | TK_NotStart | -569914933 | 63 | -569914933_63
A3210 | TT_Task | Large Sub - Door Frame | 27/03/2023 | 06/04/2023 | nan | nan | 0 | TK_NotStart | -569914933 | 64 | -569914933_64
A3220 | TT_Task | Large Sub - Side Module | 27/03/2023 | 06/04/2023 | nan | nan | 0 | TK_NotStart | -569914933 | 65 | -569914933_65
A3180 | TT_Task | Large Sub - Side Sill | 14/03/2023 | 24/03/2023 | nan | nan | 0 | TK_NotStart | -569914933 | 65 | -569914933_65
A3240 | TT_Task | UF-1 Upper Floor | 10/04/2023 | 20/04/2023 | nan | nan | 0 | TK_NotStart | -569914933 | 66 | -569914933_66
A3230 | TT_Task | Large Sub - Lower Roof | 27/03/2023 | 06/04/2023 | nan | nan | 0 | TK_NotStart | -569914933 | 64 | -569914933_64
A2439 | TT_Task | UF-2 Lower Floor | 10/04/2023 | 20/04/2023 | nan | nan | 0 | TK_NotStart | -569914933 | 66 | -569914933_66
A2445 | TT_Task | Minor Subs - Resistance Spot Weld | 01/03/2023 | 13/03/2023 | nan | nan | 0 | TK_NotStart | -569914933 | 62 | -569914933_62
A2885 | TT_Task | Large Sub - Cross Beam Lower Floor | 14/03/2023 | 24/03/2023 | nan | nan | 0 | TK_NotStart | -569914933 | 63 | -569914933_63
A2449 | TT_Task | UF-3 Full Under Floor Assembly | 21/04/2023 | 03/05/2023 | nan | nan | 0 | TK_NotStart | -569914933 | 66 | -569914933_66
A2459 | TT_Task | SF-1 Side Wall Assembly | 10/04/2023 | 20/04/2023 | nan | nan | 0 | TK_NotStart | -569914933 | 67 | -569914933_67
A2469 | TT_Task | SF-2 Side Wall Finishing | 21/04/2023 | 03/05/2023 | nan | nan | 0 | TK_NotStart | -569914933 | 67 | -569914933_67
A2479 | TT_Task | RF-1 Roof Assembly | 10/04/2023 | 20/04/2023 | nan | nan | 0 | TK_NotStart | -569914933 | 68 | -569914933_68
A3250 | TT_Task | RF-2 Roof Finishing | 21/04/2023 | 03/05/2023 | nan | nan | 0 | TK_NotStart | -569914933 | 68 | -569914933_68
A2489 | TT_Task | EF-1 End Frame (Wall) Assembly | 21/04/2023 | 03/05/2023 | nan | nan | 0 | TK_NotStart | -569914933 | 67 | -569914933_67
A2499 | TT_Task | CBS-1 Carshell Erection | 04/05/2023 | 16/05/2023 | nan | nan | 0 | TK_NotStart | -569914933 | 69 | -569914933_69
A2509 | TT_Task | CBS-2 Carshell Finishing | 17/05/2023 | 30/05/2023 | nan | nan | 0 | TK_NotStart | -569914933 | 69 | -569914933_69
A2519 | TT_Task | CBS - Secondary Structure | 31/05/2023 | 12/06/2023 | nan | nan | 0 | TK_NotStart | -569914933 | 60 | -569914933_60
A2529 | TT_Task | CBS - PC02 Alstom Quality Inspcetions | 13/06/2023 | 23/06/2023 | nan | nan | 0 | TK_NotStart | -569914933 | 70 | -569914933_70
SP5900 | TT_Task | Station 1 | 07/08/2023 | 17/08/2023 | nan | nan | 0 | TK_NotStart | -569914933 | 71 | -569914933_71
SP5910 | TT_Task | Station 2 | 18/08/2023 | 30/08/2023 | nan | nan | 0 | TK_NotStart | -569914933 | 71 | -569914933_71
SP5920 | TT_Task | Water Test | 31/08/2023 | 13/09/2023 | nan | nan | 0 | TK_NotStart | -569914933 | 72 | -569914933_72
SP5930 | TT_Task | Station 3 | 27/09/2023 | 10/10/2023 | nan | nan | 0 | TK_NotStart | -569914933 | 73 | -569914933_73
SP5940 | TT_Task | Station 4 | 11/10/2023 | 23/10/2023 | nan | nan | 0 | TK_NotStart | -569914933 | 73 | -569914933_73
SP5950 | TT_Task | Station 5 | 24/10/2023 | 03/11/2023 | nan | nan | 0 | TK_NotStart | -569914933 | 74 | -569914933_74
SP5960 | TT_Task | Station 6 | 06/11/2023 | 16/11/2023 | nan | nan | 0 | TK_NotStart | -569914933 | 74 | -569914933_74
SP5970 | TT_Task | DITMCO | 17/11/2023 | 06/12/2023 | nan | nan | 0 | TK_NotStart | -569914933 | 75 | -569914933_75
SP5980 | TT_Task | Station 7 | 07/12/2023 | 19/12/2023 | nan | nan | 0 | TK_NotStart | -569914933 | 74 | -569914933_74
SP5990 | TT_Task | Station 8 | 20/12/2023 | 10/01/2024 | nan | nan | 0 | TK_NotStart | -569914933 | 74 | -569914933_74
SP6000 | TT_Task | PC09 - Alstom Fitting Completion Inspections | 11/01/2024 | 23/01/2024 | nan | nan | 0 | TK_NotStart | -569914933 | 70 | -569914933_70
SP6010 | TT_Task | Static Testing 1 | 24/01/2024 | 05/02/2024 | nan | nan | 0 | TK_NotStart | -569914933 | 76 | -569914933_76
SP6020 | TT_Task | Static Testing 2 | 06/02/2024 | 16/02/2024 | nan | nan | 0 | TK_NotStart | -569914933 | 76 | -569914933_76
SP6030 | TT_Task | PC11 - Customer Final Inspections | 04/03/2024 | 14/03/2024 | nan | nan | 0 | TK_NotStart | -569914933 | 77 | -569914933_77
SP6320 | TT_Task | Deliver 1st Pre-Series Car | 07/05/2024 | 04/06/2024 | nan | nan | 0 | TK_NotStart | -569914933 | 78 | -569914933_78
SP6330 | TT_Task | Validation, Commissioning, Conditional Acceptance | 05/06/2024 | 25/09/2024 | nan | nan | 0 | TK_NotStart | -569914933 | 79 | -569914933_79
SP6035 | TT_Task | FAI - 1st Completed Car Assembly | 15/03/2024 | 21/03/2024 | nan | nan | 248 | TK_NotStart | -569914933 | 61 | -569914933_61
SP5925 | TT_Task | Water Test 2 | 14/09/2023 | 26/09/2023 | nan | nan | 0 | TK_NotStart | -569914933 | 72 | -569914933_72
SP6025 | TT_Task | PC11 Inspection Prep | 20/02/2024 | 01/03/2024 | nan | nan | 0 | TK_NotStart | -569914933 | 77 | -569914933_77
SP6040 | TT_Task | Station 1 | 18/08/2023 | 30/08/2023 | nan | nan | 0 | TK_NotStart | -569914933 | 71 | -569914933_71
SP6050 | TT_Task | Station 2 | 31/08/2023 | 13/09/2023 | nan | nan | 0 | TK_NotStart | -569914933 | 71 | -569914933_71
SP6060 | TT_Task | Water Test | 14/09/2023 | 26/09/2023 | nan | nan | 0 | TK_NotStart | -569914933 | 72 | -569914933_72
SP6070 | TT_Task | Station 3 | 11/10/2023 | 23/10/2023 | nan | nan | 0 | TK_NotStart | -569914933 | 73 | -569914933_73
SP6080 | TT_Task | Station 4 | 24/10/2023 | 03/11/2023 | nan | nan | 0 | TK_NotStart | -569914933 | 73 | -569914933_73
SP6090 | TT_Task | Station 5 | 06/11/2023 | 16/11/2023 | nan | nan | 0 | TK_NotStart | -569914933 | 74 | -569914933_74
SP6100 | TT_Task | Station 6 | 17/11/2023 | 04/12/2023 | nan | nan | 0 | TK_NotStart | -569914933 | 74 | -569914933_74
SP6110 | TT_Task | DITMCO | 05/12/2023 | 13/12/2023 | nan | nan | 0 | TK_NotStart | -569914933 | 75 | -569914933_75
SP6120 | TT_Task | Station 7 | 14/12/2023 | 02/01/2024 | nan | nan | 0 | TK_NotStart | -569914933 | 74 | -569914933_74
SP6130 | TT_Task | Station 8 | 03/01/2024 | 11/01/2024 | nan | nan | 0 | TK_NotStart | -569914933 | 74 | -569914933_74
SP6140 | TT_Task | PC09 - Alstom Fitting Completion Inspections | 12/01/2024 | 22/01/2024 | nan | nan | 0 | TK_NotStart | -569914933 | 70 | -569914933_70
SP6150 | TT_Task | Static Testing 1 | 23/01/2024 | 31/01/2024 | nan | nan | 0 | TK_NotStart | -569914933 | 76 | -569914933_76
SP6160 | TT_Task | Static Testing 2 | 01/02/2024 | 09/02/2024 | nan | nan | 0 | TK_NotStart | -569914933 | 76 | -569914933_76
SP6170 | TT_Task | PC11 - Customer Final Inspections | 21/02/2024 | 28/02/2024 | nan | nan | 168 | TK_NotStart | -569914933 | 77 | -569914933_77
SP6340 | TT_Task | Deliver 2nd Pre-Series Car | 07/05/2024 | 04/06/2024 | nan | nan | 0 | TK_NotStart | -569914933 | 78 | -569914933_78
SP6350 | TT_Task | Validation, Commissioning, Conditional Acceptance | 05/06/2024 | 25/09/2024 | nan | nan | 0 | TK_NotStart | -569914933 | 79 | -569914933_79
SP6065 | TT_Task | Water Test 2 | 27/09/2023 | 10/10/2023 | nan | nan | 0 | TK_NotStart | -569914933 | 72 | -569914933_72
SP6165 | TT_Task | PC11 Inspection Prep | 12/02/2024 | 20/02/2024 | nan | nan | 0 | TK_NotStart | -569914933 | 77 | -569914933_77
SP6180 | TT_Task | Station 1 | 31/08/2023 | 13/09/2023 | nan | nan | 0 | TK_NotStart | -569914933 | 71 | -569914933_71
SP6190 | TT_Task | Station 2 | 14/09/2023 | 26/09/2023 | nan | nan | 0 | TK_NotStart | -569914933 | 71 | -569914933_71
SP6200 | TT_Task | Water Test | 27/09/2023 | 10/10/2023 | nan | nan | 0 | TK_NotStart | -569914933 | 72 | -569914933_72
SP6210 | TT_Task | Station 3 | 24/10/2023 | 03/11/2023 | nan | nan | 0 | TK_NotStart | -569914933 | 73 | -569914933_73
SP6220 | TT_Task | Station 4 | 06/11/2023 | 16/11/2023 | nan | nan | 0 | TK_NotStart | -569914933 | 73 | -569914933_73
SP6230 | TT_Task | Station 5 | 17/11/2023 | 04/12/2023 | nan | nan | 0 | TK_NotStart | -569914933 | 74 | -569914933_74
SP6240 | TT_Task | Station 6 | 05/12/2023 | 13/12/2023 | nan | nan | 0 | TK_NotStart | -569914933 | 74 | -569914933_74
SP6250 | TT_Task | DITMCO | 14/12/2023 | 02/01/2024 | nan | nan | 0 | TK_NotStart | -569914933 | 75 | -569914933_75
SP6260 | TT_Task | Station 7 | 03/01/2024 | 11/01/2024 | nan | nan | 0 | TK_NotStart | -569914933 | 74 | -569914933_74
SP6270 | TT_Task | Station 8 | 12/01/2024 | 22/01/2024 | nan | nan | 0 | TK_NotStart | -569914933 | 74 | -569914933_74
SP6280 | TT_Task | PC09 - Alstom Fitting Completion Inspections | 23/01/2024 | 31/01/2024 | nan | nan | 0 | TK_NotStart | -569914933 | 70 | -569914933_70
SP6290 | TT_Task | Static Testing 1 | 01/02/2024 | 09/02/2024 | nan | nan | 0 | TK_NotStart | -569914933 | 76 | -569914933_76
SP6300 | TT_Task | Static Testing 2 | 12/02/2024 | 20/02/2024 | nan | nan | 0 | TK_NotStart | -569914933 | 76 | -569914933_76
SP6310 | TT_Task | PC11 - Customer Final Inspections | 29/02/2024 | 07/03/2024 | nan | nan | 200 | TK_NotStart | -569914933 | 77 | -569914933_77
SP6360 | TT_Task | Deliver 3rd Pre-Series Car | 07/05/2024 | 04/06/2024 | nan | nan | 0 | TK_NotStart | -569914933 | 78 | -569914933_78
SP6370 | TT_Task | Validation, Commissioning, Conditional Acceptance | 05/06/2024 | 25/09/2024 | nan | nan | 0 | TK_NotStart | -569914933 | 79 | -569914933_79
SP6205 | TT_Task | Water Test 2 | 11/10/2023 | 23/10/2023 | nan | nan | 0 | TK_NotStart | -569914933 | 72 | -569914933_72
SP6305 | TT_Task | PC11 Inspection Prep | 21/02/2024 | 28/02/2024 | nan | nan | 0 | TK_NotStart | -569914933 | 77 | -569914933_77
SP6380 | TT_Task | Validation Testing - Hornell (Testing divided between Cars 1,2,3) | 15/03/2024 | 06/05/2024 | nan | nan | 0 | TK_NotStart | -569914933 | 80 | -569914933_80
SP6390 | TT_Task | Transportation - Pilot Cars to Chicago | 07/05/2024 | 04/06/2024 | nan | nan | 0 | TK_NotStart | -569914933 | 81 | -569914933_81
SP6400 | TT_Task | Validation Testing - Chicago | 05/06/2024 | 03/09/2024 | nan | nan | 0 | TK_NotStart | -569914933 | 80 | -569914933_80
SP6410 | TT_Task | Station 1 | 14/09/2023 | 26/09/2023 | nan | nan | 0 | TK_NotStart | -569914933 | 71 | -569914933_71
SP6420 | TT_Task | Station 2 | 27/09/2023 | 10/10/2023 | nan | nan | 0 | TK_NotStart | -569914933 | 71 | -569914933_71
SP6430 | TT_Task | Water Test | 11/10/2023 | 23/10/2023 | nan | nan | 0 | TK_NotStart | -569914933 | 72 | -569914933_72
SP6440 | TT_Task | Station 3 | 06/11/2023 | 16/11/2023 | nan | nan | 0 | TK_NotStart | -569914933 | 73 | -569914933_73
SP6450 | TT_Task | Station 4 | 17/11/2023 | 04/12/2023 | nan | nan | 0 | TK_NotStart | -569914933 | 73 | -569914933_73
SP6460 | TT_Task | Station 5 | 05/12/2023 | 13/12/2023 | nan | nan | 0 | TK_NotStart | -569914933 | 74 | -569914933_74
SP6470 | TT_Task | Station 6 | 14/12/2023 | 02/01/2024 | nan | nan | 0 | TK_NotStart | -569914933 | 74 | -569914933_74
SP6480 | TT_Task | DITMCO | 03/01/2024 | 11/01/2024 | nan | nan | 0 | TK_NotStart | -569914933 | 75 | -569914933_75
SP6490 | TT_Task | Station 7 | 12/01/2024 | 22/01/2024 | nan | nan | 0 | TK_NotStart | -569914933 | 74 | -569914933_74
SP6500 | TT_Task | Station 8 | 23/01/2024 | 31/01/2024 | nan | nan | 0 | TK_NotStart | -569914933 | 74 | -569914933_74
SP6510 | TT_Task | PC09 - Alstom Fitting Completion Inspections | 01/02/2024 | 09/02/2024 | nan | nan | 0 | TK_NotStart | -569914933 | 70 | -569914933_70
SP6520 | TT_Task | Static Testing 1 | 12/02/2024 | 20/02/2024 | nan | nan | 0 | TK_NotStart | -569914933 | 76 | -569914933_76
SP6530 | TT_Task | Static Testing 2 | 21/02/2024 | 28/02/2024 | nan | nan | 0 | TK_NotStart | -569914933 | 76 | -569914933_76
SP6540 | TT_Task | PC11 - Customer Final Inspections | 08/03/2024 | 15/03/2024 | nan | nan | 280 | TK_NotStart | -569914933 | 77 | -569914933_77
SP6550 | TT_Task | Deliver 4th Pre-Series Car | 07/05/2024 | 04/06/2024 | nan | nan | 472 | TK_NotStart | -569914933 | 78 | -569914933_78
SP6560 | TT_Task | Commissioning, Conditional Acceptance, Training | 04/09/2024 | 25/09/2024 | nan | nan | 0 | TK_NotStart | -569914933 | 79 | -569914933_79
SP6435 | TT_Task | Water Test 2 | 24/10/2023 | 03/11/2023 | nan | nan | 0 | TK_NotStart | -569914933 | 72 | -569914933_72
SP6535 | TT_Task | PC11 Inspection Prep | 29/02/2024 | 07/03/2024 | nan | nan | 0 | TK_NotStart | -569914933 | 77 | -569914933_77
P1012 | TT_Task | Metra Base Order Cars 5 thru 10: Manufacture ; Test | 12/02/2024 | 03/10/2024 | nan | nan | 0 | TK_NotStart | -569914933 | 82 | -569914933_82
P1032 | TT_Task | Metra Base Order Cars 5 thru 10: Deliver | 04/10/2024 | 18/10/2024 | nan | nan | 0 | TK_NotStart | -569914933 | 83 | -569914933_83
P1042 | TT_Task | Metra Base Order Cars 5 thru 10: Cond Acceptance | 21/10/2024 | 01/11/2024 | nan | nan | 0 | TK_NotStart | -569914933 | 84 | -569914933_84
P1052 | TT_Task | Metra Base Order Cars 21 thru 28: Manufacture ; Test | 04/10/2024 | 13/03/2025 | nan | nan | 0 | TK_NotStart | -569914933 | 82 | -569914933_82
P1062 | TT_Task | Metra Base Order Cars 21 thru 28: Deliver | 14/03/2025 | 27/03/2025 | nan | nan | 0 | TK_NotStart | -569914933 | 83 | -569914933_83
P1072 | TT_Task | Metra Base Order Cars 21 thru 28: Cond Acceptance | 28/03/2025 | 10/04/2025 | nan | nan | 0 | TK_NotStart | -569914933 | 84 | -569914933_84
P1049 | TT_Task | Metra Base Order Cars 16 thru 20: Manufacture ; Test | 25/07/2024 | 20/12/2024 | nan | nan | 0 | TK_NotStart | -569914933 | 82 | -569914933_82
P1050 | TT_Task | Metra Base Order Cars 16 thru 20: Deliver | 02/01/2025 | 15/01/2025 | nan | nan | 0 | TK_NotStart | -569914933 | 83 | -569914933_83
P1051 | TT_Task | Metra Base Order Cars 16 thru 20: Cond Acceptance | 16/01/2025 | 29/01/2025 | nan | nan | 0 | TK_NotStart | -569914933 | 84 | -569914933_84
P1043 | TT_Task | Metra Base Order Cars 11 thru 15: Manufacture ; Test | 08/05/2024 | 15/11/2024 | nan | nan | 0 | TK_NotStart | -569914933 | 82 | -569914933_82
P1044 | TT_Task | Metra Base Order Cars 11 thru 15: Deliver | 18/11/2024 | 06/12/2024 | nan | nan | 0 | TK_NotStart | -569914933 | 83 | -569914933_83
P1045 | TT_Task | Metra Base Order Cars 11 thru 15: Cond Acceptance | 09/12/2024 | 20/12/2024 | nan | nan | 0 | TK_NotStart | -569914933 | 84 | -569914933_84
A2370 | TT_Task | VRE - Base Order Cars: 1 - 10 Manufacture ; Test | 02/01/2025 | 23/05/2025 | nan | nan | 0 | TK_NotStart | -569914933 | 85 | -569914933_85
A2400 | TT_Task | VRE - Base Order Cars: 1 - 10 Deliver | 27/05/2025 | 09/06/2025 | nan | nan | 0 | TK_NotStart | -569914933 | 85 | -569914933_85
A2410 | TT_Task | VRE - Base Order Cars: 1 - 10 Commissioning, Training, Cond Acceptance | 10/06/2025 | 23/06/2025 | nan | nan | 0 | TK_NotStart | -569914933 | 85 | -569914933_85
A2420 | TT_Task | VRE - Base Order Cars: 11 - 21 Manufacture ; Test | 07/03/2025 | 07/07/2025 | nan | nan | 0 | TK_NotStart | -569914933 | 85 | -569914933_85
A2430 | TT_Task | VRE - Base Order Cars: 11 - 21 Deliver | 08/07/2025 | 21/07/2025 | nan | nan | 0 | TK_NotStart | -569914933 | 85 | -569914933_85
A2440 | TT_Task | VRE - Base Order Cars: 11 - 21 Commissioning, Cond Acceptance | 22/07/2025 | 04/08/2025 | nan | nan | 0 | TK_NotStart | -569914933 | 85 | -569914933_85
A2510 | TT_Task | VRE - Warranty Period (6 Years) | 24/06/2025 | 16/01/2032 | nan | nan | 2112 | TK_NotStart | -569914933 | 86 | -569914933_86
P1082 | TT_Task | Metra Base Order Cars 29 thru 37: Manufacture ; Test | 21/04/2025 | 28/07/2025 | nan | nan | 0 | TK_NotStart | -569914933 | 82 | -569914933_82
P1092 | TT_Task | Metra Base Order Cars 29 thru 37: Deliver | 29/07/2025 | 11/08/2025 | nan | nan | 0 | TK_NotStart | -569914933 | 83 | -569914933_83
P1102 | TT_Task | Metra Base Order Cars 29 thru 37: Cond Acceptance | 12/08/2025 | 25/08/2025 | nan | nan | 0 | TK_NotStart | -569914933 | 84 | -569914933_84
P1112 | TT_Task | Metra Base Order Cars 38 thru 44: Manufacture ; Test | 19/05/2025 | 18/08/2025 | nan | nan | 0 | TK_NotStart | -569914933 | 82 | -569914933_82
P1122 | TT_Task | Metra Base Order Cars 38 thru 44: Deliver | 19/08/2025 | 02/09/2025 | nan | nan | 0 | TK_NotStart | -569914933 | 83 | -569914933_83
P1132 | TT_Task | Metra Base Order Cars 38 thru 44: Cond Acceptance | 03/09/2025 | 16/09/2025 | nan | nan | 0 | TK_NotStart | -569914933 | 84 | -569914933_84
P1142 | TT_Task | Metra Base Order Cars 45 thru 51: Manufacture ; Test | 10/06/2025 | 09/09/2025 | nan | nan | 0 | TK_NotStart | -569914933 | 82 | -569914933_82
P1152 | TT_Task | Metra Base Order Cars 45 thru 51: Deliver | 10/09/2025 | 23/09/2025 | nan | nan | 0 | TK_NotStart | -569914933 | 83 | -569914933_83
P1162 | TT_Task | Metra Base Order Cars 45 thru 51: Cond Acceptance | 24/09/2025 | 07/10/2025 | nan | nan | 0 | TK_NotStart | -569914933 | 84 | -569914933_84
P1172 | TT_Task | Metra Base Order Cars 52 thru 56: Manufacture ; Test | 08/07/2025 | 30/09/2025 | nan | nan | 0 | TK_NotStart | -569914933 | 82 | -569914933_82
P1182 | TT_Task | Metra Base Order Cars 52 thru 56: Deliver | 01/10/2025 | 15/10/2025 | nan | nan | 0 | TK_NotStart | -569914933 | 83 | -569914933_83
P1192 | TT_Task | Metra Base Order Cars 52 thru 56: Cond Acceptance | 16/10/2025 | 29/10/2025 | nan | nan | 0 | TK_NotStart | -569914933 | 84 | -569914933_84
P1202 | TT_Task | Metra Base Order Cars 57 thru 61: Manufacture ; Test | 29/07/2025 | 22/10/2025 | nan | nan | 0 | TK_NotStart | -569914933 | 82 | -569914933_82
P1212 | TT_Task | Metra Base Order Cars 57 thru 61: Deliver | 23/10/2025 | 05/11/2025 | nan | nan | 0 | TK_NotStart | -569914933 | 83 | -569914933_83
P1222 | TT_Task | Metra Base Order Cars 57 thru 61: Cond Acceptance | 06/11/2025 | 19/11/2025 | nan | nan | 0 | TK_NotStart | -569914933 | 84 | -569914933_84
P1232 | TT_Task | Metra Base Order Cars 62 thru 69: Manufacture ; Test | 19/08/2025 | 12/11/2025 | nan | nan | 0 | TK_NotStart | -569914933 | 82 | -569914933_82
P1242 | TT_Task | Metra Base Order Cars 62 thru 69: Deliver | 13/11/2025 | 03/12/2025 | nan | nan | 0 | TK_NotStart | -569914933 | 83 | -569914933_83
P1252 | TT_Task | Metra Base Order Cars 62 thru 69: Cond Acceptance | 04/12/2025 | 17/12/2025 | nan | nan | 0 | TK_NotStart | -569914933 | 84 | -569914933_84
P1262 | TT_Task | Metra Base Order Cars 70 thru 75: Manufacture ; Test | 10/09/2025 | 10/12/2025 | nan | nan | 0 | TK_NotStart | -569914933 | 82 | -569914933_82
P1272 | TT_Task | Metra Base Order Cars 70 thru 75: Deliver | 11/12/2025 | 07/01/2026 | nan | nan | 0 | TK_NotStart | -569914933 | 83 | -569914933_83
P1282 | TT_Task | Metra Base Order Cars 70 thru 75: Cond Acceptance | 08/01/2026 | 21/01/2026 | nan | nan | 0 | TK_NotStart | -569914933 | 84 | -569914933_84
P1292 | TT_Task | Metra Base Order Cars 76 thru 82: Manufacture ; Test | 01/10/2025 | 14/01/2026 | nan | nan | 0 | TK_NotStart | -569914933 | 82 | -569914933_82
P1302 | TT_Task | Metra Base Order Cars 76 thru 82: Deliver | 15/01/2026 | 28/01/2026 | nan | nan | 0 | TK_NotStart | -569914933 | 83 | -569914933_83
P1312 | TT_Task | Metra Base Order Cars 76 thru 82: Cond Acceptance | 29/01/2026 | 11/02/2026 | nan | nan | 0 | TK_NotStart | -569914933 | 84 | -569914933_84
P1322 | TT_Task | Metra Base Order Cars 83 thru 89: Manufacture ; Test | 23/10/2025 | 04/02/2026 | nan | nan | 0 | TK_NotStart | -569914933 | 82 | -569914933_82
P1332 | TT_Task | Metra Base Order Cars 83 thru 89: Deliver | 05/02/2026 | 19/02/2026 | nan | nan | 0 | TK_NotStart | -569914933 | 83 | -569914933_83
P1342 | TT_Task | Metra Base Order Cars 83 thru 89: Cond Acceptance | 20/02/2026 | 05/03/2026 | nan | nan | 0 | TK_NotStart | -569914933 | 84 | -569914933_84
P1352 | TT_Task | Metra Base Order Cars 90 thru 97: Manufacture ; Test | 13/11/2025 | 26/02/2026 | nan | nan | 0 | TK_NotStart | -569914933 | 82 | -569914933_82
P1362 | TT_Task | Metra Base Order Cars 90 thru 97: Deliver | 27/02/2026 | 12/03/2026 | nan | nan | 0 | TK_NotStart | -569914933 | 83 | -569914933_83
P1372 | TT_Task | Metra Base Order Cars 90 thru 97: Cond Acceptance | 13/03/2026 | 26/03/2026 | nan | nan | 0 | TK_NotStart | -569914933 | 84 | -569914933_84
P1382 | TT_Task | Metra Base Order Cars 98 thru 103: Manufacture ; Test | 08/12/2025 | 16/03/2026 | nan | nan | 0 | TK_NotStart | -569914933 | 82 | -569914933_82
P1392 | TT_Task | Metra Base Order Cars 98 thru 103: Deliver | 17/03/2026 | 30/03/2026 | nan | nan | 0 | TK_NotStart | -569914933 | 83 | -569914933_83
P1402 | TT_Task | Metra Base Order Cars 98 thru 103: Cond Acceptance | 31/03/2026 | 14/04/2026 | nan | nan | 0 | TK_NotStart | -569914933 | 84 | -569914933_84
P1412 | TT_Task | Metra Base Order Cars 104 thru 109: Manufacture ; Test | 07/01/2026 | 01/04/2026 | nan | nan | 0 | TK_NotStart | -569914933 | 87 | -569914933_87
P1422 | TT_Task | Metra Base Order Cars 104 thru 109: Deliver | 02/04/2026 | 16/04/2026 | nan | nan | 0 | TK_NotStart | -569914933 | 83 | -569914933_83
P1432 | TT_Task | Metra Base Order Cars 104 thru 109: Cond Acceptance | 17/04/2026 | 30/04/2026 | nan | nan | 0 | TK_NotStart | -569914933 | 84 | -569914933_84
P1442 | TT_Task | Metra Base Order Cars 110 thru 117: Manufacture ; Test | 23/01/2026 | 20/04/2026 | nan | nan | 0 | TK_NotStart | -569914933 | 87 | -569914933_87
P1452 | TT_Task | Metra Base Order Cars 110 thru 117: Deliver | 21/04/2026 | 04/05/2026 | nan | nan | 0 | TK_NotStart | -569914933 | 83 | -569914933_83
P1462 | TT_Task | Metra Base Order Cars 110 thru 117: Cond Acceptance | 05/05/2026 | 18/05/2026 | nan | nan | 0 | TK_NotStart | -569914933 | 84 | -569914933_84
P1472 | TT_Task | Metra Base Order Cars 118 thru 123: Manufacture ; Test | 10/02/2026 | 06/05/2026 | nan | nan | 0 | TK_NotStart | -569914933 | 87 | -569914933_87
P1482 | TT_Task | Metra Base Order Cars 118 thru 123: Deliver | 07/05/2026 | 20/05/2026 | nan | nan | 0 | TK_NotStart | -569914933 | 83 | -569914933_83
P1492 | TT_Task | Metra Base Order Cars 118 thru 123: Cond Acceptance | 21/05/2026 | 04/06/2026 | nan | nan | 0 | TK_NotStart | -569914933 | 84 | -569914933_84
P1502 | TT_Task | Metra Base Order Cars 124 thru 131: Manufacture ; Test | 27/02/2026 | 22/05/2026 | nan | nan | 0 | TK_NotStart | -569914933 | 87 | -569914933_87
P1512 | TT_Task | Metra Base Order Cars 124 thru 131: Deliver | 26/05/2026 | 08/06/2026 | nan | nan | 0 | TK_NotStart | -569914933 | 83 | -569914933_83
P1522 | TT_Task | Metra Base Order Cars 124 thru 131: Cond Acceptance | 09/06/2026 | 22/06/2026 | nan | nan | 0 | TK_NotStart | -569914933 | 84 | -569914933_84
P1532 | TT_Task | Metra Base Order Cars 132 thru 136: Manufacture ; Test | 17/03/2026 | 10/06/2026 | nan | nan | 0 | TK_NotStart | -569914933 | 87 | -569914933_87
P1542 | TT_Task | Metra Base Order Cars 132 thru 136: Deliver | 11/06/2026 | 24/06/2026 | nan | nan | 0 | TK_NotStart | -569914933 | 83 | -569914933_83
P1552 | TT_Task | Metra Base Order Cars 132 thru 136: Cond Acceptance | 25/06/2026 | 15/07/2026 | nan | nan | 0 | TK_NotStart | -569914933 | 84 | -569914933_84
P1562 | TT_Task | Metra Base Order Cars 137 thru 141: Manufacture ; Test | 02/04/2026 | 26/06/2026 | nan | nan | 0 | TK_NotStart | -569914933 | 87 | -569914933_87
P1572 | TT_Task | Metra Base Order Cars 137 thru 141: Deliver | 06/07/2026 | 17/07/2026 | nan | nan | 0 | TK_NotStart | -569914933 | 87 | -569914933_87
P1582 | TT_Task | Metra Base Order Cars 137 thru 141: Cond Acceptance | 20/07/2026 | 31/07/2026 | nan | nan | 0 | TK_NotStart | -569914933 | 84 | -569914933_84
P1592 | TT_Task | Metra Base Order Cars 142 thru 148: Manufacture ; Test | 21/04/2026 | 21/07/2026 | nan | nan | 0 | TK_NotStart | -569914933 | 87 | -569914933_87
P1602 | TT_Task | Metra Base Order Cars 142 thru 148: Deliver | 22/07/2026 | 04/08/2026 | nan | nan | 0 | TK_NotStart | -569914933 | 83 | -569914933_83
P1612 | TT_Task | Metra Base Order Cars 142 thru 148: Cond Acceptance | 05/08/2026 | 18/08/2026 | nan | nan | 0 | TK_NotStart | -569914933 | 84 | -569914933_84
P1622 | TT_Task | Metra Base Order Cars 149 thru 155: Manufacture ; Test | 07/05/2026 | 06/08/2026 | nan | nan | 0 | TK_NotStart | -569914933 | 87 | -569914933_87
P1632 | TT_Task | Metra Base Order Cars 149 thru 155: Deliver | 07/08/2026 | 20/08/2026 | nan | nan | 0 | TK_NotStart | -569914933 | 83 | -569914933_83
P1642 | TT_Task | Metra Base Order Cars 149 thru 155: Cond Acceptance | 21/08/2026 | 03/09/2026 | nan | nan | 0 | TK_NotStart | -569914933 | 84 | -569914933_84
P1652 | TT_Task | Metra Base Order Cars 156 thru 162: Manufacture ; Test | 26/05/2026 | 24/08/2026 | nan | nan | 0 | TK_NotStart | -569914933 | 87 | -569914933_87
P1662 | TT_Task | Metra Base Order Cars 156 thru 162: Deliver | 25/08/2026 | 08/09/2026 | nan | nan | 0 | TK_NotStart | -569914933 | 83 | -569914933_83
P1672 | TT_Task | Metra Base Order Cars 156 thru 162: Cond Acceptance | 09/09/2026 | 22/09/2026 | nan | nan | 0 | TK_NotStart | -569914933 | 84 | -569914933_84
P1682 | TT_Task | Metra Base Order Cars 163 thru 169: Manufacture ; Test | 11/06/2026 | 10/09/2026 | nan | nan | 0 | TK_NotStart | -569914933 | 87 | -569914933_87
P1692 | TT_Task | Metra Base Order Cars 163 thru 169: Deliver | 11/09/2026 | 24/09/2026 | nan | nan | 0 | TK_NotStart | -569914933 | 87 | -569914933_87
P1702 | TT_Task | Metra Base Order Cars 163 thru 169: Cond Acceptance | 25/09/2026 | 08/10/2026 | nan | nan | 0 | TK_NotStart | -569914933 | 84 | -569914933_84
P1712 | TT_Task | Metra Base Order Cars 170 thru 176: Manufacture ; Test | 06/07/2026 | 28/09/2026 | nan | nan | 0 | TK_NotStart | -569914933 | 87 | -569914933_87
P1722 | TT_Task | Metra Base Order Cars 170 thru 176: Deliver | 29/09/2026 | 13/10/2026 | nan | nan | 0 | TK_NotStart | -569914933 | 83 | -569914933_83
P1732 | TT_Task | Metra Base Order Cars 170 thru 176: Cond Acceptance | 14/10/2026 | 27/10/2026 | nan | nan | 0 | TK_NotStart | -569914933 | 84 | -569914933_84
P1742 | TT_Task | Metra Base Order Cars 177 thru 183: Manufacture ; Test | 22/07/2026 | 15/10/2026 | nan | nan | 0 | TK_NotStart | -569914933 | 87 | -569914933_87
P1752 | TT_Task | Metra Base Order Cars 177 thru 183: Deliver | 16/10/2026 | 29/10/2026 | nan | nan | 0 | TK_NotStart | -569914933 | 87 | -569914933_87
P1762 | TT_Task | Metra Base Order Cars 177 thru 183: Cond Acceptance | 30/10/2026 | 12/11/2026 | nan | nan | 0 | TK_NotStart | -569914933 | 84 | -569914933_84
P1772 | TT_Task | Metra Base Order Cars 184 thru 189: Manufacture ; Test | 07/08/2026 | 02/11/2026 | nan | nan | 0 | TK_NotStart | -569914933 | 87 | -569914933_87
P1782 | TT_Task | Metra Base Order Cars 184 thru 189: Deliver | 03/11/2026 | 16/11/2026 | nan | nan | 0 | TK_NotStart | -569914933 | 83 | -569914933_83
P1792 | TT_Task | Metra Base Order Cars 184 thru 189: Cond Acceptance | 17/11/2026 | 07/12/2026 | nan | nan | 0 | TK_NotStart | -569914933 | 84 | -569914933_84
P1802 | TT_Task | Metra Base Order Cars 190 thru 196: Manufacture ; Test | 25/08/2026 | 18/11/2026 | nan | nan | 0 | TK_NotStart | -569914933 | 87 | -569914933_87
P1812 | TT_Task | Metra Base Order Cars 190 thru 196: Deliver | 19/11/2026 | 09/12/2026 | nan | nan | 0 | TK_NotStart | -569914933 | 83 | -569914933_83
P1822 | TT_Task | Metra Base Order Cars 190 thru 196: Cond Acceptance | 10/12/2026 | 23/12/2026 | nan | nan | 0 | TK_NotStart | -569914933 | 84 | -569914933_84
P1832 | TT_Task | Metra Base Order Cars 197 thru 200: Manufacture ; Test | 05/10/2026 | 07/12/2026 | nan | nan | 0 | TK_NotStart | -569914933 | 87 | -569914933_87
P1842 | TT_Task | Metra Base Order Cars 197 thru 200: Deliver | 08/12/2026 | 21/12/2026 | nan | nan | 0 | TK_NotStart | -569914933 | 83 | -569914933_83
P1852 | TT_Task | Metra Base Order Cars 197 thru 200: Cond Acceptance | 04/01/2027 | 15/01/2027 | nan | nan | 0 | TK_NotStart | -569914933 | 84 | -569914933_84
P1862 | TT_Task | Training 2nd Phase: Final Base Car (Commences 2 months following Conditional Acceptance - prior to revenue service) | 16/03/2027 | 11/05/2027 | nan | nan | 0 | TK_NotStart | -569914933 | 88 | -569914933_88
A2520 | TT_Task | Metra Base Order Total Warranty Period (6 Years per Car) | 26/09/2024 | 20/01/2033 | nan | nan | 0 | TK_NotStart | -569914933 | 89 | -569914933_89
A7680 | TT_Task | Warranty Period Car 1 | 26/09/2024 | 26/09/2030 | nan | nan | 0 | TK_NotStart | -569914933 | 90 | -569914933_90
A7690 | TT_Task | Warranty Period Car 2 | 26/09/2024 | 26/09/2030 | nan | nan | 4840 | TK_NotStart | -569914933 | 90 | -569914933_90
A7700 | TT_Task | Warranty Period Car 3 | 26/09/2024 | 26/09/2030 | nan | nan | 4840 | TK_NotStart | -569914933 | 90 | -569914933_90
A7710 | TT_Task | Warranty Period Car 4 | 26/09/2024 | 26/09/2030 | nan | nan | 4840 | TK_NotStart | -569914933 | 90 | -569914933_90
A7720 | TT_Task | Warranty Period Car 5 | 04/11/2024 | 01/11/2030 | nan | nan | 4632 | TK_NotStart | -569914933 | 90 | -569914933_90
A7730 | TT_Task | Warranty Period Car 6 | 04/11/2024 | 01/11/2030 | nan | nan | 4632 | TK_NotStart | -569914933 | 90 | -569914933_90
A7740 | TT_Task | Warranty Period Car 7 | 04/11/2024 | 01/11/2030 | nan | nan | 4632 | TK_NotStart | -569914933 | 91 | -569914933_91
A7750 | TT_Task | Warranty Period Car 8 | 04/11/2024 | 01/11/2030 | nan | nan | 4632 | TK_NotStart | -569914933 | 92 | -569914933_92
A7760 | TT_Task | Warranty Period Car 9 | 04/11/2024 | 01/11/2030 | nan | nan | 4632 | TK_NotStart | -569914933 | 93 | -569914933_93
A7770 | TT_Task | Warranty Period Car 10 | 04/11/2024 | 01/11/2030 | nan | nan | 4632 | TK_NotStart | -569914933 | 93 | -569914933_93
A7780 | TT_Task | Warranty Period Car 11 | 02/01/2025 | 13/12/2030 | nan | nan | 4392 | TK_NotStart | -569914933 | 93 | -569914933_93
A7790 | TT_Task | Warranty Period Car 12 | 02/01/2025 | 13/12/2030 | nan | nan | 4392 | TK_NotStart | -569914933 | 94 | -569914933_94
A7800 | TT_Task | Warranty Period Car 13 | 02/01/2025 | 13/12/2030 | nan | nan | 4392 | TK_NotStart | -569914933 | 94 | -569914933_94
A7810 | TT_Task | Warranty Period Car 14 | 02/01/2025 | 13/12/2030 | nan | nan | 4392 | TK_NotStart | -569914933 | 94 | -569914933_94
A7820 | TT_Task | Warranty Period Car 15 | 02/01/2025 | 13/12/2030 | nan | nan | 4392 | TK_NotStart | -569914933 | 94 | -569914933_94
A7830 | TT_Task | Warranty Period Car 16 | 30/01/2025 | 10/01/2031 | nan | nan | 4232 | TK_NotStart | -569914933 | 94 | -569914933_94
A7840 | TT_Task | Warranty Period Car 17 | 30/01/2025 | 10/01/2031 | nan | nan | 4232 | TK_NotStart | -569914933 | 94 | -569914933_94
A7850 | TT_Task | Warranty Period Car 18 | 30/01/2025 | 10/01/2031 | nan | nan | 4232 | TK_NotStart | -569914933 | 94 | -569914933_94
A7860 | TT_Task | Warranty Period Car 19 | 30/01/2025 | 10/01/2031 | nan | nan | 4232 | TK_NotStart | -569914933 | 94 | -569914933_94
A7870 | TT_Task | Warranty Period Car 20 | 30/01/2025 | 10/01/2031 | nan | nan | 4232 | TK_NotStart | -569914933 | 94 | -569914933_94
A7880 | TT_Task | Warranty Period Car 21 | 11/04/2025 | 21/03/2031 | nan | nan | 3832 | TK_NotStart | -569914933 | 94 | -569914933_94
A7890 | TT_Task | Warranty Period Car 22 | 11/04/2025 | 21/03/2031 | nan | nan | 3832 | TK_NotStart | -569914933 | 94 | -569914933_94
A7900 | TT_Task | Warranty Period Car 23 | 11/04/2025 | 21/03/2031 | nan | nan | 3832 | TK_NotStart | -569914933 | 95 | -569914933_95
A7910 | TT_Task | Warranty Period Car 24 | 11/04/2025 | 21/03/2031 | nan | nan | 3832 | TK_NotStart | -569914933 | 95 | -569914933_95
A7920 | TT_Task | Warranty Period Car 25 | 11/04/2025 | 21/03/2031 | nan | nan | 3832 | TK_NotStart | -569914933 | 95 | -569914933_95
A7930 | TT_Task | Warranty Period Car 26 | 11/04/2025 | 21/03/2031 | nan | nan | 3832 | TK_NotStart | -569914933 | 95 | -569914933_95
A7940 | TT_Task | Warranty Period Car 27 | 11/04/2025 | 21/03/2031 | nan | nan | 3832 | TK_NotStart | -569914933 | 95 | -569914933_95
A7950 | TT_Task | Warranty Period Car 28 | 11/04/2025 | 21/03/2031 | nan | nan | 3832 | TK_NotStart | -569914933 | 95 | -569914933_95
A7960 | TT_Task | Warranty Period Car 29 - VRE Car 1 | 24/06/2025 | 30/05/2031 | nan | nan | 200 | TK_NotStart | -569914933 | 96 | -569914933_96
A7970 | TT_Task | Warranty Period Car 30 - VRE Car 2 | 24/06/2025 | 30/05/2031 | nan | nan | 200 | TK_NotStart | -569914933 | 96 | -569914933_96
A7980 | TT_Task | Warranty Period Car 31 - VRE Car 3 | 24/06/2025 | 30/05/2031 | nan | nan | 200 | TK_NotStart | -569914933 | 96 | -569914933_96
A7990 | TT_Task | Warranty Period Car 32 - VRE Car 4 | 24/06/2025 | 30/05/2031 | nan | nan | 200 | TK_NotStart | -569914933 | 96 | -569914933_96
A8000 | TT_Task | Warranty Period Car 33 - VRE Car 5 | 24/06/2025 | 30/05/2031 | nan | nan | 200 | TK_NotStart | -569914933 | 96 | -569914933_96
A8010 | TT_Task | Warranty Period Car 34 - VRE Car 6 | 24/06/2025 | 30/05/2031 | nan | nan | 200 | TK_NotStart | -569914933 | 96 | -569914933_96
A8020 | TT_Task | Warranty Period Car 35 - VRE Car 7 | 24/06/2025 | 30/05/2031 | nan | nan | 200 | TK_NotStart | -569914933 | 91 | -569914933_91
A8030 | TT_Task | Warranty Period Car 36 - VRE Car 8 | 24/06/2025 | 30/05/2031 | nan | nan | 200 | TK_NotStart | -569914933 | 96 | -569914933_96
A8040 | TT_Task | Warranty Period Car 37 - VRE Car 9 | 24/06/2025 | 30/05/2031 | nan | nan | 200 | TK_NotStart | -569914933 | 97 | -569914933_97
A8050 | TT_Task | Warranty Period Car 38 - VRE Car 10 | 24/06/2025 | 30/05/2031 | nan | nan | 200 | TK_NotStart | -569914933 | 97 | -569914933_97
A8060 | TT_Task | Warranty Period Car 39 - VRE Car 11 | 05/08/2025 | 04/07/2031 | nan | nan | 0 | TK_NotStart | -569914933 | 97 | -569914933_97
A8070 | TT_Task | Warranty Period Car 40 - VRE Car 12 | 05/08/2025 | 04/07/2031 | nan | nan | 0 | TK_NotStart | -569914933 | 97 | -569914933_97
A8080 | TT_Task | Warranty Period Car 41 - VRE Car 13 | 05/08/2025 | 04/07/2031 | nan | nan | 0 | TK_NotStart | -569914933 | 97 | -569914933_97
A8090 | TT_Task | Warranty Period Car 42 - VRE Car 14 | 05/08/2025 | 04/07/2031 | nan | nan | 0 | TK_NotStart | -569914933 | 97 | -569914933_97
A8100 | TT_Task | Warranty Period Car 43 - VRE Car 15 | 05/08/2025 | 04/07/2031 | nan | nan | 0 | TK_NotStart | -569914933 | 97 | -569914933_97
A8110 | TT_Task | Warranty Period Car 44 - VRE Car 16 | 05/08/2025 | 04/07/2031 | nan | nan | 0 | TK_NotStart | -569914933 | 97 | -569914933_97
A8120 | TT_Task | Warranty Period Car 45 - VRE Car 17 | 05/08/2025 | 04/07/2031 | nan | nan | 0 | TK_NotStart | -569914933 | 97 | -569914933_97
A8130 | TT_Task | Warranty Period Car 46 - VRE Car 18 | 05/08/2025 | 04/07/2031 | nan | nan | 0 | TK_NotStart | -569914933 | 97 | -569914933_97
A8140 | TT_Task | Warranty Period Car 47 - VRE Car 19 | 05/08/2025 | 04/07/2031 | nan | nan | 0 | TK_NotStart | -569914933 | 97 | -569914933_97
A8150 | TT_Task | Warranty Period Car 48 - VRE Car 20 | 05/08/2025 | 04/07/2031 | nan | nan | 0 | TK_NotStart | -569914933 | 97 | -569914933_97
A8160 | TT_Task | Warranty Period Car 49 - VRE Car 21 | 05/08/2025 | 04/07/2031 | nan | nan | 0 | TK_NotStart | -569914933 | 97 | -569914933_97
A8170 | TT_Task | Warranty Period Car 50 | 26/08/2025 | 25/07/2031 | nan | nan | 3112 | TK_NotStart | -569914933 | 98 | -569914933_98
A8180 | TT_Task | Warranty Period Car 51 | 26/08/2025 | 25/07/2031 | nan | nan | 3112 | TK_NotStart | -569914933 | 98 | -569914933_98
A8190 | TT_Task | Warranty Period Car 52 | 26/08/2025 | 25/07/2031 | nan | nan | 3112 | TK_NotStart | -569914933 | 98 | -569914933_98
A8200 | TT_Task | Warranty Period Car 53 | 26/08/2025 | 25/07/2031 | nan | nan | 3112 | TK_NotStart | -569914933 | 98 | -569914933_98
A8210 | TT_Task | Warranty Period Car 54 | 26/08/2025 | 25/07/2031 | nan | nan | 3112 | TK_NotStart | -569914933 | 98 | -569914933_98
A8220 | TT_Task | Warranty Period Car 55 | 26/08/2025 | 25/07/2031 | nan | nan | 3112 | TK_NotStart | -569914933 | 98 | -569914933_98
A8230 | TT_Task | Warranty Period Car 56 | 26/08/2025 | 25/07/2031 | nan | nan | 3112 | TK_NotStart | -569914933 | 98 | -569914933_98
A8240 | TT_Task | Warranty Period Car 57 | 26/08/2025 | 25/07/2031 | nan | nan | 3112 | TK_NotStart | -569914933 | 98 | -569914933_98
A8250 | TT_Task | Warranty Period Car 58 | 26/08/2025 | 25/07/2031 | nan | nan | 3112 | TK_NotStart | -569914933 | 98 | -569914933_98
A8260 | TT_Task | Warranty Period Car 59 | 17/09/2025 | 15/08/2031 | nan | nan | 2992 | TK_NotStart | -569914933 | 98 | -569914933_98
A8270 | TT_Task | Warranty Period Car 60 | 17/09/2025 | 15/08/2031 | nan | nan | 2992 | TK_NotStart | -569914933 | 98 | -569914933_98
A8280 | TT_Task | Warranty Period Car 61 | 17/09/2025 | 15/08/2031 | nan | nan | 2992 | TK_NotStart | -569914933 | 93 | -569914933_93
A8290 | TT_Task | Warranty Period Car 62 | 17/09/2025 | 15/08/2031 | nan | nan | 2992 | TK_NotStart | -569914933 | 98 | -569914933_98
A8300 | TT_Task | Warranty Period Car 63 | 17/09/2025 | 15/08/2031 | nan | nan | 2992 | TK_NotStart | -569914933 | 98 | -569914933_98
A8310 | TT_Task | Warranty Period Car 64 | 17/09/2025 | 15/08/2031 | nan | nan | 2992 | TK_NotStart | -569914933 | 98 | -569914933_98
A8320 | TT_Task | Warranty Period Car 65 | 17/09/2025 | 15/08/2031 | nan | nan | 2992 | TK_NotStart | -569914933 | 98 | -569914933_98
A8330 | TT_Task | Warranty Period Car 66 | 08/10/2025 | 05/09/2031 | nan | nan | 2872 | TK_NotStart | -569914933 | 98 | -569914933_98
A8340 | TT_Task | Warranty Period Car 67 | 08/10/2025 | 05/09/2031 | nan | nan | 2872 | TK_NotStart | -569914933 | 98 | -569914933_98
A8350 | TT_Task | Warranty Period Car 68 | 08/10/2025 | 05/09/2031 | nan | nan | 2872 | TK_NotStart | -569914933 | 91 | -569914933_91
A8360 | TT_Task | Warranty Period Car 69 | 08/10/2025 | 05/09/2031 | nan | nan | 2872 | TK_NotStart | -569914933 | 91 | -569914933_91
A8370 | TT_Task | Warranty Period Car 70 | 08/10/2025 | 05/09/2031 | nan | nan | 2872 | TK_NotStart | -569914933 | 91 | -569914933_91
A8380 | TT_Task | Warranty Period Car 71 | 08/10/2025 | 05/09/2031 | nan | nan | 2872 | TK_NotStart | -569914933 | 91 | -569914933_91
A8390 | TT_Task | Warranty Period Car 72 | 08/10/2025 | 05/09/2031 | nan | nan | 2872 | TK_NotStart | -569914933 | 91 | -569914933_91
A8400 | TT_Task | Warranty Period Car 73 | 30/10/2025 | 26/09/2031 | nan | nan | 2752 | TK_NotStart | -569914933 | 91 | -569914933_91
A8410 | TT_Task | Warranty Period Car 74 | 30/10/2025 | 26/09/2031 | nan | nan | 2752 | TK_NotStart | -569914933 | 91 | -569914933_91
A8420 | TT_Task | Warranty Period Car 75 | 30/10/2025 | 26/09/2031 | nan | nan | 2752 | TK_NotStart | -569914933 | 91 | -569914933_91
A8430 | TT_Task | Warranty Period Car 76 | 30/10/2025 | 26/09/2031 | nan | nan | 2752 | TK_NotStart | -569914933 | 91 | -569914933_91
A8440 | TT_Task | Warranty Period Car 77 | 30/10/2025 | 26/09/2031 | nan | nan | 2752 | TK_NotStart | -569914933 | 91 | -569914933_91
A8450 | TT_Task | Warranty Period Car 78 | 20/11/2025 | 17/10/2031 | nan | nan | 2632 | TK_NotStart | -569914933 | 91 | -569914933_91
A8460 | TT_Task | Warranty Period Car 79 | 20/11/2025 | 17/10/2031 | nan | nan | 2632 | TK_NotStart | -569914933 | 91 | -569914933_91
A8470 | TT_Task | Warranty Period Car 80 | 20/11/2025 | 17/10/2031 | nan | nan | 2632 | TK_NotStart | -569914933 | 92 | -569914933_92
A8480 | TT_Task | Warranty Period Car 81 | 20/11/2025 | 17/10/2031 | nan | nan | 2632 | TK_NotStart | -569914933 | 92 | -569914933_92
A8490 | TT_Task | Warranty Period Car 82 | 20/11/2025 | 17/10/2031 | nan | nan | 2632 | TK_NotStart | -569914933 | 92 | -569914933_92
A8500 | TT_Task | Warranty Period Car 83 | 18/12/2025 | 07/11/2031 | nan | nan | 2512 | TK_NotStart | -569914933 | 92 | -569914933_92
A8510 | TT_Task | Warranty Period Car 84 | 18/12/2025 | 07/11/2031 | nan | nan | 2512 | TK_NotStart | -569914933 | 92 | -569914933_92
A8520 | TT_Task | Warranty Period Car 85 | 18/12/2025 | 07/11/2031 | nan | nan | 2512 | TK_NotStart | -569914933 | 92 | -569914933_92
A8530 | TT_Task | Warranty Period Car 86 | 18/12/2025 | 07/11/2031 | nan | nan | 2512 | TK_NotStart | -569914933 | 92 | -569914933_92
A8540 | TT_Task | Warranty Period Car 87 | 18/12/2025 | 07/11/2031 | nan | nan | 2512 | TK_NotStart | -569914933 | 92 | -569914933_92
A8550 | TT_Task | Warranty Period Car 88 | 18/12/2025 | 07/11/2031 | nan | nan | 2512 | TK_NotStart | -569914933 | 92 | -569914933_92
A8560 | TT_Task | Warranty Period Car 89 | 18/12/2025 | 07/11/2031 | nan | nan | 2512 | TK_NotStart | -569914933 | 92 | -569914933_92
A8570 | TT_Task | Warranty Period Car 90 | 18/12/2025 | 07/11/2031 | nan | nan | 2512 | TK_NotStart | -569914933 | 99 | -569914933_99
A8580 | TT_Task | Warranty Period Car 91 | 22/01/2026 | 28/11/2031 | nan | nan | 2392 | TK_NotStart | -569914933 | 99 | -569914933_99
A8590 | TT_Task | Warranty Period Car 92 | 22/01/2026 | 28/11/2031 | nan | nan | 2392 | TK_NotStart | -569914933 | 99 | -569914933_99
A8600 | TT_Task | Warranty Period Car 93 | 22/01/2026 | 28/11/2031 | nan | nan | 2392 | TK_NotStart | -569914933 | 99 | -569914933_99
A8610 | TT_Task | Warranty Period Car 94 | 22/01/2026 | 28/11/2031 | nan | nan | 2392 | TK_NotStart | -569914933 | 99 | -569914933_99
A8620 | TT_Task | Warranty Period Car 95 | 22/01/2026 | 28/11/2031 | nan | nan | 2392 | TK_NotStart | -569914933 | 99 | -569914933_99
A8630 | TT_Task | Warranty Period Car 96 | 22/01/2026 | 28/11/2031 | nan | nan | 2392 | TK_NotStart | -569914933 | 99 | -569914933_99
A8640 | TT_Task | Warranty Period Car 97 | 12/02/2026 | 19/12/2031 | nan | nan | 2272 | TK_NotStart | -569914933 | 99 | -569914933_99
A8650 | TT_Task | Warranty Period Car 98 | 12/02/2026 | 19/12/2031 | nan | nan | 2272 | TK_NotStart | -569914933 | 99 | -569914933_99
A8660 | TT_Task | Warranty Period Car 99 | 12/02/2026 | 19/12/2031 | nan | nan | 2272 | TK_NotStart | -569914933 | 99 | -569914933_99
A8670 | TT_Task | Warranty Period Car 100 | 12/02/2026 | 19/12/2031 | nan | nan | 2272 | TK_NotStart | -569914933 | 100 | -569914933_100
A8680 | TT_Task | Warranty Period Car 101 | 12/02/2026 | 19/12/2031 | nan | nan | 2272 | TK_NotStart | -569914933 | 100 | -569914933_100
A8690 | TT_Task | Warranty Period Car 102 | 12/02/2026 | 19/12/2031 | nan | nan | 2272 | TK_NotStart | -569914933 | 100 | -569914933_100
A8700 | TT_Task | Warranty Period Car 103 | 12/02/2026 | 19/12/2031 | nan | nan | 2272 | TK_NotStart | -569914933 | 100 | -569914933_100
A8710 | TT_Task | Warranty Period Car 104 | 06/03/2026 | 09/01/2032 | nan | nan | 2152 | TK_NotStart | -569914933 | 100 | -569914933_100
A8720 | TT_Task | Warranty Period Car 105 | 06/03/2026 | 09/01/2032 | nan | nan | 2152 | TK_NotStart | -569914933 | 100 | -569914933_100
A8730 | TT_Task | Warranty Period Car 106 | 06/03/2026 | 09/01/2032 | nan | nan | 2152 | TK_NotStart | -569914933 | 93 | -569914933_93
A8740 | TT_Task | Warranty Period Car 107 | 06/03/2026 | 09/01/2032 | nan | nan | 2152 | TK_NotStart | -569914933 | 91 | -569914933_91
A8750 | TT_Task | Warranty Period Car 108 | 06/03/2026 | 09/01/2032 | nan | nan | 2152 | TK_NotStart | -569914933 | 91 | -569914933_91
A8760 | TT_Task | Warranty Period Car 109 | 06/03/2026 | 09/01/2032 | nan | nan | 2152 | TK_NotStart | -569914933 | 91 | -569914933_91
A8770 | TT_Task | Warranty Period Car 110 | 06/03/2026 | 09/01/2032 | nan | nan | 2152 | TK_NotStart | -569914933 | 101 | -569914933_101
A8780 | TT_Task | Warranty Period Car 111 | 27/03/2026 | 30/01/2032 | nan | nan | 2032 | TK_NotStart | -569914933 | 93 | -569914933_93
A8790 | TT_Task | Warranty Period Car 112 | 27/03/2026 | 30/01/2032 | nan | nan | 2032 | TK_NotStart | -569914933 | 93 | -569914933_93
A8800 | TT_Task | Warranty Period Car 113 | 27/03/2026 | 30/01/2032 | nan | nan | 2032 | TK_NotStart | -569914933 | 93 | -569914933_93
A8810 | TT_Task | Warranty Period Car 114 | 27/03/2026 | 30/01/2032 | nan | nan | 2032 | TK_NotStart | -569914933 | 93 | -569914933_93
A8820 | TT_Task | Warranty Period Car 115 | 27/03/2026 | 30/01/2032 | nan | nan | 2032 | TK_NotStart | -569914933 | 102 | -569914933_102
A8830 | TT_Task | Warranty Period Car 116 | 27/03/2026 | 30/01/2032 | nan | nan | 2032 | TK_NotStart | -569914933 | 93 | -569914933_93
A8840 | TT_Task | Warranty Period Car 117 | 27/03/2026 | 30/01/2032 | nan | nan | 2032 | TK_NotStart | -569914933 | 102 | -569914933_102
A8850 | TT_Task | Warranty Period Car 118 | 27/03/2026 | 30/01/2032 | nan | nan | 2032 | TK_NotStart | -569914933 | 93 | -569914933_93
A8860 | TT_Task | Warranty Period Car 119 | 15/04/2026 | 17/02/2032 | nan | nan | 1936 | TK_NotStart | -569914933 | 93 | -569914933_93
A8870 | TT_Task | Warranty Period Car 120 | 15/04/2026 | 17/02/2032 | nan | nan | 1936 | TK_NotStart | -569914933 | 101 | -569914933_101
A8880 | TT_Task | Warranty Period Car 121 | 15/04/2026 | 17/02/2032 | nan | nan | 1936 | TK_NotStart | -569914933 | 93 | -569914933_93
A8890 | TT_Task | Warranty Period Car 122 | 15/04/2026 | 17/02/2032 | nan | nan | 1936 | TK_NotStart | -569914933 | 101 | -569914933_101
A8900 | TT_Task | Warranty Period Car 123 | 15/04/2026 | 17/02/2032 | nan | nan | 1936 | TK_NotStart | -569914933 | 102 | -569914933_102
A8910 | TT_Task | Warranty Period Car 124 | 15/04/2026 | 17/02/2032 | nan | nan | 1936 | TK_NotStart | -569914933 | 102 | -569914933_102
A8920 | TT_Task | Warranty Period Car 125 | 01/05/2026 | 04/03/2032 | nan | nan | 1840 | TK_NotStart | -569914933 | 102 | -569914933_102
A8930 | TT_Task | Warranty Period Car 126 | 01/05/2026 | 04/03/2032 | nan | nan | 1840 | TK_NotStart | -569914933 | 102 | -569914933_102
A8940 | TT_Task | Warranty Period Car 127 | 01/05/2026 | 04/03/2032 | nan | nan | 1840 | TK_NotStart | -569914933 | 102 | -569914933_102
A8950 | TT_Task | Warranty Period Car 128 | 01/05/2026 | 04/03/2032 | nan | nan | 1840 | TK_NotStart | -569914933 | 102 | -569914933_102
A8960 | TT_Task | Warranty Period Car 129 | 01/05/2026 | 04/03/2032 | nan | nan | 1840 | TK_NotStart | -569914933 | 102 | -569914933_102
A8970 | TT_Task | Warranty Period Car 130 | 01/05/2026 | 04/03/2032 | nan | nan | 1840 | TK_NotStart | -569914933 | 102 | -569914933_102
A8980 | TT_Task | Warranty Period Car 131 | 19/05/2026 | 22/03/2032 | nan | nan | 1744 | TK_NotStart | -569914933 | 102 | -569914933_102
A8990 | TT_Task | Warranty Period Car 132 | 19/05/2026 | 22/03/2032 | nan | nan | 1744 | TK_NotStart | -569914933 | 102 | -569914933_102
A9000 | TT_Task | Warranty Period Car 133 | 19/05/2026 | 22/03/2032 | nan | nan | 1744 | TK_NotStart | -569914933 | 102 | -569914933_102
A9010 | TT_Task | Warranty Period Car 134 | 19/05/2026 | 22/03/2032 | nan | nan | 1744 | TK_NotStart | -569914933 | 102 | -569914933_102
A9020 | TT_Task | Warranty Period Car 135 | 19/05/2026 | 22/03/2032 | nan | nan | 1744 | TK_NotStart | -569914933 | 103 | -569914933_103
A9030 | TT_Task | Warranty Period Car 136 | 19/05/2026 | 22/03/2032 | nan | nan | 1744 | TK_NotStart | -569914933 | 102 | -569914933_102
A9040 | TT_Task | Warranty Period Car 137 | 19/05/2026 | 22/03/2032 | nan | nan | 1744 | TK_NotStart | -569914933 | 102 | -569914933_102
A9050 | TT_Task | Warranty Period Car 138 | 19/05/2026 | 22/03/2032 | nan | nan | 1744 | TK_NotStart | -569914933 | 102 | -569914933_102
A9060 | TT_Task | Warranty Period Car 139 | 05/06/2026 | 07/04/2032 | nan | nan | 1648 | TK_NotStart | -569914933 | 102 | -569914933_102
A9070 | TT_Task | Warranty Period Car 140 | 05/06/2026 | 07/04/2032 | nan | nan | 1648 | TK_NotStart | -569914933 | 103 | -569914933_103
A9080 | TT_Task | Warranty Period Car 141 | 05/06/2026 | 07/04/2032 | nan | nan | 1648 | TK_NotStart | -569914933 | 103 | -569914933_103
A9090 | TT_Task | Warranty Period Car 142 | 05/06/2026 | 07/04/2032 | nan | nan | 1648 | TK_NotStart | -569914933 | 103 | -569914933_103
A9100 | TT_Task | Warranty Period Car 143 | 05/06/2026 | 07/04/2032 | nan | nan | 1648 | TK_NotStart | -569914933 | 103 | -569914933_103
A9110 | TT_Task | Warranty Period Car 144 | 05/06/2026 | 07/04/2032 | nan | nan | 1648 | TK_NotStart | -569914933 | 104 | -569914933_104
A9120 | TT_Task | Warranty Period Car 145 | 23/06/2026 | 23/04/2032 | nan | nan | 1552 | TK_NotStart | -569914933 | 103 | -569914933_103
A9130 | TT_Task | Warranty Period Car 146 | 23/06/2026 | 23/04/2032 | nan | nan | 1552 | TK_NotStart | -569914933 | 103 | -569914933_103
A9140 | TT_Task | Warranty Period Car 147 | 23/06/2026 | 23/04/2032 | nan | nan | 1552 | TK_NotStart | -569914933 | 103 | -569914933_103
A9150 | TT_Task | Warranty Period Car 148 | 23/06/2026 | 23/04/2032 | nan | nan | 1552 | TK_NotStart | -569914933 | 103 | -569914933_103
A9160 | TT_Task | Warranty Period Car 149 | 23/06/2026 | 23/04/2032 | nan | nan | 1552 | TK_NotStart | -569914933 | 103 | -569914933_103
A9170 | TT_Task | Warranty Period Car 150 | 23/06/2026 | 23/04/2032 | nan | nan | 1552 | TK_NotStart | -569914933 | 103 | -569914933_103
A9180 | TT_Task | Warranty Period Car 151 | 23/06/2026 | 23/04/2032 | nan | nan | 1552 | TK_NotStart | -569914933 | 103 | -569914933_103
A9190 | TT_Task | Warranty Period Car 152 | 23/06/2026 | 23/04/2032 | nan | nan | 1552 | TK_NotStart | -569914933 | 103 | -569914933_103
A9200 | TT_Task | Warranty Period Car 153 | 16/07/2026 | 11/05/2032 | nan | nan | 1456 | TK_NotStart | -569914933 | 103 | -569914933_103
A9210 | TT_Task | Warranty Period Car 154 | 16/07/2026 | 11/05/2032 | nan | nan | 1456 | TK_NotStart | -569914933 | 103 | -569914933_103
A9220 | TT_Task | Warranty Period Car 155 | 16/07/2026 | 11/05/2032 | nan | nan | 1456 | TK_NotStart | -569914933 | 103 | -569914933_103
A9230 | TT_Task | Warranty Period Car 156 | 16/07/2026 | 11/05/2032 | nan | nan | 1456 | TK_NotStart | -569914933 | 105 | -569914933_105
A9240 | TT_Task | Warranty Period Car 157 | 16/07/2026 | 11/05/2032 | nan | nan | 1456 | TK_NotStart | -569914933 | 105 | -569914933_105
A9250 | TT_Task | Warranty Period Car 158 | 03/08/2026 | 27/05/2032 | nan | nan | 1360 | TK_NotStart | -569914933 | 105 | -569914933_105
A9260 | TT_Task | Warranty Period Car 159 | 03/08/2026 | 27/05/2032 | nan | nan | 1360 | TK_NotStart | -569914933 | 105 | -569914933_105
A9270 | TT_Task | Warranty Period Car 160 | 03/08/2026 | 27/05/2032 | nan | nan | 1360 | TK_NotStart | -569914933 | 103 | -569914933_103
A9280 | TT_Task | Warranty Period Car 161 | 03/08/2026 | 27/05/2032 | nan | nan | 1360 | TK_NotStart | -569914933 | 105 | -569914933_105
A9290 | TT_Task | Warranty Period Car 162 | 03/08/2026 | 27/05/2032 | nan | nan | 1360 | TK_NotStart | -569914933 | 104 | -569914933_104
A9300 | TT_Task | Warranty Period Car 163 | 19/08/2026 | 14/06/2032 | nan | nan | 1264 | TK_NotStart | -569914933 | 105 | -569914933_105
A9310 | TT_Task | Warranty Period Car 164 | 19/08/2026 | 14/06/2032 | nan | nan | 1264 | TK_NotStart | -569914933 | 105 | -569914933_105
A9320 | TT_Task | Warranty Period Car 165 | 19/08/2026 | 14/06/2032 | nan | nan | 1264 | TK_NotStart | -569914933 | 103 | -569914933_103
A9330 | TT_Task | Warranty Period Car 166 | 19/08/2026 | 14/06/2032 | nan | nan | 1264 | TK_NotStart | -569914933 | 105 | -569914933_105
A9340 | TT_Task | Warranty Period Car 167 | 19/08/2026 | 14/06/2032 | nan | nan | 1264 | TK_NotStart | -569914933 | 105 | -569914933_105
A9350 | TT_Task | Warranty Period Car 168 | 19/08/2026 | 14/06/2032 | nan | nan | 1264 | TK_NotStart | -569914933 | 102 | -569914933_102
A9360 | TT_Task | Warranty Period Car 169 | 19/08/2026 | 14/06/2032 | nan | nan | 1264 | TK_NotStart | -569914933 | 105 | -569914933_105
A9370 | TT_Task | Warranty Period Car 170 | 04/09/2026 | 30/06/2032 | nan | nan | 1168 | TK_NotStart | -569914933 | 103 | -569914933_103
A9380 | TT_Task | Warranty Period Car 171 | 04/09/2026 | 30/06/2032 | nan | nan | 1168 | TK_NotStart | -569914933 | 105 | -569914933_105
A9390 | TT_Task | Warranty Period Car 172 | 04/09/2026 | 30/06/2032 | nan | nan | 1168 | TK_NotStart | -569914933 | 106 | -569914933_106
A9400 | TT_Task | Warranty Period Car 173 | 04/09/2026 | 30/06/2032 | nan | nan | 1168 | TK_NotStart | -569914933 | 106 | -569914933_106
A9410 | TT_Task | Warranty Period Car 174 | 04/09/2026 | 30/06/2032 | nan | nan | 1168 | TK_NotStart | -569914933 | 105 | -569914933_105
A9420 | TT_Task | Warranty Period Car 175 | 04/09/2026 | 30/06/2032 | nan | nan | 1168 | TK_NotStart | -569914933 | 103 | -569914933_103
A9430 | TT_Task | Warranty Period Car 176 | 04/09/2026 | 30/06/2032 | nan | nan | 1168 | TK_NotStart | -569914933 | 106 | -569914933_106
A9440 | TT_Task | Warranty Period Car 177 | 23/09/2026 | 16/07/2032 | nan | nan | 1072 | TK_NotStart | -569914933 | 106 | -569914933_106
A9450 | TT_Task | Warranty Period Car 178 | 23/09/2026 | 16/07/2032 | nan | nan | 1072 | TK_NotStart | -569914933 | 105 | -569914933_105
A9460 | TT_Task | Warranty Period Car 179 | 23/09/2026 | 16/07/2032 | nan | nan | 1072 | TK_NotStart | -569914933 | 106 | -569914933_106
A9470 | TT_Task | Warranty Period Car 180 | 23/09/2026 | 16/07/2032 | nan | nan | 1072 | TK_NotStart | -569914933 | 106 | -569914933_106
A9480 | TT_Task | Warranty Period Car 181 | 23/09/2026 | 16/07/2032 | nan | nan | 1072 | TK_NotStart | -569914933 | 106 | -569914933_106
A9490 | TT_Task | Warranty Period Car 182 | 23/09/2026 | 16/07/2032 | nan | nan | 1072 | TK_NotStart | -569914933 | 106 | -569914933_106
A9500 | TT_Task | Warranty Period Car 183 | 23/09/2026 | 16/07/2032 | nan | nan | 1072 | TK_NotStart | -569914933 | 101 | -569914933_101
A9510 | TT_Task | Warranty Period Car 184 | 09/10/2026 | 03/08/2032 | nan | nan | 976 | TK_NotStart | -569914933 | 104 | -569914933_104
A9520 | TT_Task | Warranty Period Car 185 | 09/10/2026 | 03/08/2032 | nan | nan | 976 | TK_NotStart | -569914933 | 106 | -569914933_106
A9530 | TT_Task | Warranty Period Car 186 | 09/10/2026 | 03/08/2032 | nan | nan | 976 | TK_NotStart | -569914933 | 104 | -569914933_104
A9540 | TT_Task | Warranty Period Car 187 | 09/10/2026 | 03/08/2032 | nan | nan | 976 | TK_NotStart | -569914933 | 104 | -569914933_104
A9550 | TT_Task | Warranty Period Car 188 | 09/10/2026 | 03/08/2032 | nan | nan | 976 | TK_NotStart | -569914933 | 104 | -569914933_104
A9560 | TT_Task | Warranty Period Car 189 | 09/10/2026 | 03/08/2032 | nan | nan | 976 | TK_NotStart | -569914933 | 104 | -569914933_104
A9570 | TT_Task | Warranty Period Car 190 | 09/10/2026 | 03/08/2032 | nan | nan | 976 | TK_NotStart | -569914933 | 104 | -569914933_104
A9580 | TT_Task | Warranty Period Car 191 | 28/10/2026 | 19/08/2032 | nan | nan | 880 | TK_NotStart | -569914933 | 104 | -569914933_104
A9590 | TT_Task | Warranty Period Car 192 | 28/10/2026 | 19/08/2032 | nan | nan | 880 | TK_NotStart | -569914933 | 102 | -569914933_102
A9600 | TT_Task | Warranty Period Car 193 | 28/10/2026 | 19/08/2032 | nan | nan | 880 | TK_NotStart | -569914933 | 104 | -569914933_104
A9610 | TT_Task | Warranty Period Car 194 | 28/10/2026 | 19/08/2032 | nan | nan | 880 | TK_NotStart | -569914933 | 104 | -569914933_104
A9620 | TT_Task | Warranty Period Car 195 | 28/10/2026 | 19/08/2032 | nan | nan | 880 | TK_NotStart | -569914933 | 104 | -569914933_104
A9630 | TT_Task | Warranty Period Car 196 | 28/10/2026 | 19/08/2032 | nan | nan | 880 | TK_NotStart | -569914933 | 104 | -569914933_104
A9640 | TT_Task | Warranty Period Car 197 | 28/10/2026 | 19/08/2032 | nan | nan | 880 | TK_NotStart | -569914933 | 104 | -569914933_104
A9650 | TT_Task | Warranty Period Car 198 | 13/11/2026 | 06/09/2032 | nan | nan | 784 | TK_NotStart | -569914933 | 104 | -569914933_104
A9660 | TT_Task | Warranty Period Car 199 | 13/11/2026 | 06/09/2032 | nan | nan | 784 | TK_NotStart | -569914933 | 104 | -569914933_104
A9670 | TT_Task | Warranty Period Car 200 | 13/11/2026 | 06/09/2032 | nan | nan | 784 | TK_NotStart | -569914933 | 101 | -569914933_101
A9680 | TT_Task | Warranty Period Car 201 | 13/11/2026 | 06/09/2032 | nan | nan | 784 | TK_NotStart | -569914933 | 101 | -569914933_101
A9690 | TT_Task | Warranty Period Car 202 | 13/11/2026 | 06/09/2032 | nan | nan | 784 | TK_NotStart | -569914933 | 101 | -569914933_101
A9700 | TT_Task | Warranty Period Car 203 | 13/11/2026 | 06/09/2032 | nan | nan | 784 | TK_NotStart | -569914933 | 101 | -569914933_101
A9710 | TT_Task | Warranty Period Car 204 | 13/11/2026 | 06/09/2032 | nan | nan | 784 | TK_NotStart | -569914933 | 101 | -569914933_101
A9720 | TT_Task | Warranty Period Car 205 | 08/12/2026 | 22/09/2032 | nan | nan | 688 | TK_NotStart | -569914933 | 101 | -569914933_101
A9730 | TT_Task | Warranty Period Car 206 | 08/12/2026 | 22/09/2032 | nan | nan | 688 | TK_NotStart | -569914933 | 101 | -569914933_101
A9740 | TT_Task | Warranty Period Car 207 | 08/12/2026 | 22/09/2032 | nan | nan | 688 | TK_NotStart | -569914933 | 101 | -569914933_101
A9750 | TT_Task | Warranty Period Car 208 | 08/12/2026 | 22/09/2032 | nan | nan | 688 | TK_NotStart | -569914933 | 101 | -569914933_101
A9760 | TT_Task | Warranty Period Car 209 | 08/12/2026 | 22/09/2032 | nan | nan | 688 | TK_NotStart | -569914933 | 101 | -569914933_101
A9770 | TT_Task | Warranty Period Car 210 | 08/12/2026 | 22/09/2032 | nan | nan | 688 | TK_NotStart | -569914933 | 101 | -569914933_101
A9780 | TT_Task | Warranty Period Car 211 | 04/01/2027 | 08/10/2032 | nan | nan | 592 | TK_NotStart | -569914933 | 101 | -569914933_101
A9790 | TT_Task | Warranty Period Car 212 | 04/01/2027 | 08/10/2032 | nan | nan | 592 | TK_NotStart | -569914933 | 106 | -569914933_106
A9800 | TT_Task | Warranty Period Car 213 | 04/01/2027 | 08/10/2032 | nan | nan | 592 | TK_NotStart | -569914933 | 106 | -569914933_106
A9810 | TT_Task | Warranty Period Car 214 | 04/01/2027 | 08/10/2032 | nan | nan | 592 | TK_NotStart | -569914933 | 104 | -569914933_104
A9820 | TT_Task | Warranty Period Car 215 | 04/01/2027 | 08/10/2032 | nan | nan | 592 | TK_NotStart | -569914933 | 106 | -569914933_106
A9830 | TT_Task | Warranty Period Car 216 | 04/01/2027 | 08/10/2032 | nan | nan | 592 | TK_NotStart | -569914933 | 106 | -569914933_106
A9840 | TT_Task | Warranty Period Car 217 | 04/01/2027 | 08/10/2032 | nan | nan | 592 | TK_NotStart | -569914933 | 105 | -569914933_105
A9850 | TT_Task | Warranty Period Car 218 | 18/01/2027 | 22/10/2032 | nan | nan | 512 | TK_NotStart | -569914933 | 106 | -569914933_106
A9860 | TT_Task | Warranty Period Car 219 | 18/01/2027 | 22/10/2032 | nan | nan | 512 | TK_NotStart | -569914933 | 106 | -569914933_106
A9870 | TT_Task | Warranty Period Car 220 | 18/01/2027 | 22/10/2032 | nan | nan | 512 | TK_NotStart | -569914933 | 101 | -569914933_101
A9880 | TT_Task | Warranty Period Car 221 | 18/01/2027 | 22/10/2032 | nan | nan | 0 | TK_NotStart | -569914933 | 101 | -569914933_101
OP1020 | TT_Task | VRE - 48 Option Cars: Manufacture ; test/Delivery/Cond Acceptance | 08/12/2026 | 28/09/2027 | nan | nan | 0 | TK_NotStart | -569914933 | 85 | -569914933_85
OP1030 | TT_Task | VRE - 48 Option Cars: Warranty Period (6 Years) | 11/02/2027 | 14/12/2033 | nan | nan | 7448 | TK_NotStart | -569914933 | 86 | -569914933_86
OP1040 | TT_Task | Metra - Option Order 300 cars: Manufacture ; test/Delivery/Cond Acceptance | 13/07/2027 | 11/07/2031 | nan | nan | 0 | TK_NotStart | -569914933 | 84 | -569914933_84
OP1050 | TT_Task | Metra - Option Order 300 cars: Warranty Period (6 Years) | 06/10/2027 | 09/07/2037 | nan | nan | 0 | TK_NotStart | -569914933 | 89 | -569914933_89
A2185 | TT_Task | PO to Line Builder (For Phase 2) | 31/03/2022 | 20/04/2022 | nan | nan | 30 | TK_NotStart | -569914933 | 48 | -569914933_48
A9890 | TT_Task | Customer FAI - Doors Ext | 26/07/2023 | 15/08/2023 | nan | nan | 0 | TK_NotStart | -569914933 | 107 | -569914933_107
A9900 | TT_Task | Customer FAI - Floors | 02/11/2022 | 22/11/2022 | nan | nan | 1400 | TK_NotStart | -569914933 | 107 | -569914933_107
A9910 | TT_Task | Customer FAI - Coupler | 08/03/2023 | 28/03/2023 | nan | nan | 744 | TK_NotStart | -569914933 | 108 | -569914933_108
A9920 | TT_Task | Customer FAI - Diaphram | 15/02/2023 | 08/03/2023 | nan | nan | 856 | TK_NotStart | -569914933 | 108 | -569914933_108
A9930 | TT_Task | Customer FAI - Toilets | 16/02/2023 | 09/03/2023 | nan | nan | 848 | TK_NotStart | -569914933 | 107 | -569914933_107
A9940 | TT_Task | Customer FAI - HVAC | 05/04/2023 | 26/04/2023 | nan | nan | 584 | TK_NotStart | -569914933 | 107 | -569914933_107
A9950 | TT_Task | Customer FAI - Batteries | 21/03/2023 | 11/04/2023 | nan | nan | 672 | TK_NotStart | -569914933 | 31 | -569914933_31
A9960 | TT_Task | Customer FAI - Brake Modules | 04/05/2023 | 24/05/2023 | nan | nan | 424 | TK_NotStart | -569914933 | 32 | -569914933_32
A9970 | TT_Task | Customer FAI - Passenger Seats | 30/05/2023 | 19/06/2023 | nan | nan | 288 | TK_NotStart | -569914933 | 33 | -569914933_33
A9980 | TT_Task | Customer FAI - Windows | 14/02/2023 | 07/03/2023 | nan | nan | 864 | TK_NotStart | -569914933 | 108 | -569914933_108
A9990 | TT_Task | Customer FAI - PACIS | 17/05/2023 | 07/06/2023 | nan | nan | 352 | TK_NotStart | -569914933 | 108 | -569914933_108
A10000 | TT_Task | Customer FAI - Wheelchair Lift | 18/05/2023 | 08/06/2023 | nan | nan | 344 | TK_NotStart | -569914933 | 35 | -569914933_35
A10010 | TT_Task | Customer FAI - Signalling | 18/05/2023 | 08/06/2023 | nan | nan | 344 | TK_NotStart | -569914933 | 108 | -569914933_108
A10020 | TT_Task | Customer FAI - Interiors | 15/05/2023 | 05/06/2023 | nan | nan | 368 | TK_NotStart | -569914933 | 107 | -569914933_107
A10030 | TT_Task | Customer FAI - Bogies | 13/04/2023 | 03/05/2023 | nan | nan | 544 | TK_NotStart | -569914933 | 108 | -569914933_108
CUS1010 | TT_Task | Perform Customer FAI's | 26/07/2023 | 16/02/2024 | nan | nan | 184 | TK_NotStart | -569914933 | 108 | -569914933_108
PM1337 | TT_Task | Payment Milestone 1 - VRE Review/Approval | 13/04/2021 | 10/05/2021 | 13/07/2021 | 12/08/2021 | 0 | TK_Complete | -569914933 | 109 | -569914933_109
PM1347 | TT_Task | Payment Milestone 2 - VRE Review/Approval | 07/06/2021 | 02/07/2021 | 13/07/2021 | 12/08/2021 | 0 | TK_Complete | -569914933 | 109 | -569914933_109
PM1357 | TT_Task | Payment Milestone 3 - VRE Review/Approval | 29/10/2021 | 02/12/2021 | 24/11/2021 | nan | 0 | TK_Active | -569914933 | 109 | -569914933_109
PM1367 | TT_Task | Payment Milestone 4 - VRE Review/Approval | 25/01/2022 | 22/02/2022 | 25/01/2022 | 24/02/2022 | 0 | TK_Complete | -569914933 | 109 | -569914933_109
PM1377 | TT_Task | Payment Milestone 5 - VRE Review/Approval | 28/10/2022 | 24/11/2022 | nan | nan | 0 | TK_NotStart | -569914933 | 109 | -569914933_109
PM1387 | TT_Task | Payment Milestone 6 - VRE Review/Approval | 06/03/2023 | 31/03/2023 | nan | nan | 0 | TK_NotStart | -569914933 | 109 | -569914933_109
PM1397 | TT_Task | Payment Milestone 7 - VRE Review/Approval | 22/07/2025 | 18/08/2025 | nan | nan | 0 | TK_NotStart | -569914933 | 109 | -569914933_109
PM1407 | TT_Task | Payment Milestone 9 - VRE Review/Approval | 24/06/2025 | 28/07/2025 | nan | nan | 0 | TK_NotStart | -569914933 | 109 | -569914933_109
PM1417 | TT_Task | Payment Milestone 10 - VRE Review/Approval | 24/01/2024 | 21/02/2024 | nan | nan | 0 | TK_NotStart | -569914933 | 109 | -569914933_109
PM1427 | TT_Task | Payment Milestone 14 - VRE Review/Approval | 10/06/2025 | 14/07/2025 | nan | nan | 0 | TK_NotStart | -569914933 | 109 | -569914933_109
PM1437 | TT_Task | Payment Milestone 16 - VRE Review/Approval | 11/08/2026 | 08/09/2026 | nan | nan | 0 | TK_NotStart | -569914933 | 109 | -569914933_109
PM1447 | TT_Task | Payment Milestone 17 - VRE Review/Approval | 07/07/2031 | 01/08/2031 | nan | nan | 0 | TK_NotStart | -569914933 | 109 | -569914933_109
MRPP2-GEN.10558 | TT_Task | Mobilization and Initial Works until Contract Award | 03/09/2019 | 09/12/2019 | 03/09/2019 | 09/12/2019 | 0 | TK_Complete | 1208363553 | 1 | 1208363553_1
MRPP2-DE3.23860 | TT_Task | Schedule 30 Part F - Maintenance Depot Equipment (M5 Payment Milestone) | 22/10/2021 | 21/08/2027 | 22/10/2021 | nan | 75984 | TK_Active | 1208363553 | 2 | 1208363553_2
MRPP2-GEN.10310 | TT_Task | Bellevue Depot Deployment of Mechanical, Electrical Equipment and Workers | 14/05/2021 | 06/08/2021 | 14/05/2021 | 06/08/2021 | 0 | TK_Complete | 1208363553 | 3 | 1208363553_3
MRPP2-GEN.10500 | TT_Task | Bellevue Depot Mechanical Works | 14/05/2021 | 06/08/2021 | 14/05/2021 | 06/08/2021 | 0 | TK_Complete | 1208363553 | 3 | 1208363553_3
MRPP2-GEN.10505 | TT_Task | Bellevue Depot Electrical Works | 01/07/2021 | 27/08/2021 | 01/07/2021 | 27/08/2021 | 0 | TK_Complete | 1208363553 | 3 | 1208363553_3
MRPP2-GEN.10790 | TT_Task | Bellevue Depot Assembly Facility Validation | 30/08/2021 | 22/09/2021 | 30/08/2021 | 22/09/2021 | 0 | TK_Complete | 1208363553 | 4 | 1208363553_4
MRPP2-GEN.50000 | TT_Task | Bellevue Depot Assembly Facility Handover RIM Accreditation - Application Prep | 23/09/2020 | 21/10/2020 | 23/09/2020 | 21/10/2020 | 0 | TK_Complete | 1208363553 | 4 | 1208363553_4
MRPP2-GEN.50020 | TT_Task | Bellevue Depot Assembly Facility Handover RIM Accreditation Process | 22/10/2020 | 13/05/2021 | 22/10/2020 | 13/05/2021 | 0 | TK_Complete | 1208363553 | 4 | 1208363553_4
MRPP2-GEN.50040 | TT_Task | Bellevue Depot Assembly Facility Handover RSO Accreditation - Application Prep | 06/10/2020 | 02/11/2020 | 06/10/2020 | 02/11/2020 | 0 | TK_Complete | 1208363553 | 5 | 1208363553_5
MRPP2-GEN.50060 | TT_Task | Bellevue Depot Assembly Facility Handover RSO Accreditation Process | 03/11/2020 | 13/05/2021 | 03/11/2020 | 13/05/2021 | 0 | TK_Complete | 1208363553 | 5 | 1208363553_5
MRPP2-MGT.10000 | TT_Task | Sch. 5 - Verification and Validation Plan | 02/12/2019 | 11/12/2019 | 01/12/2019 | 11/12/2019 | 0 | TK_Complete | 1208363553 | 6 | 1208363553_6
MRPP2-MGT.10070 | TT_Task | Sch. 5 - Verification and Validation Plan PTA Review | 12/12/2019 | 13/01/2020 | 12/12/2019 | 13/01/2020 | 0 | TK_Complete | 1208363553 | 6 | 1208363553_6
MRPP2-MGT.10080 | TT_Task | Sch. 5 - Verification and Validation Plan Incorporate Comments ; Resubmit Rev.2 | 14/01/2020 | 12/03/2020 | 14/01/2020 | 12/03/2020 | 0 | TK_Complete | 1208363553 | 7 | 1208363553_7
MRPP2-MGT.11923 | TT_Task | Sch. 5 - Verification and Validation Plan PTA 2nd Review ; Comments | 13/03/2020 | 06/04/2020 | 13/03/2020 | 06/04/2020 | 0 | TK_Complete | 1208363553 | 6 | 1208363553_6
MRPP2-MGT.11943 | TT_Task | Sch. 5 - Verification and Validation Plan Incorporate Comments ; Resubmit Rev.3 | 07/04/2020 | 30/04/2020 | 07/04/2020 | 30/04/2020 | 0 | TK_Complete | 1208363553 | 7 | 1208363553_7
MRPP2-MGT.11953 | TT_Task | Sch. 5 - Verification and Validation Plan PTA 3rd Review ; Approval | 01/05/2020 | 22/05/2020 | 01/05/2020 | 22/05/2020 | 0 | TK_Complete | 1208363553 | 6 | 1208363553_6
MRPP2-MGT.11883 | TT_Task | Design Plan EMU M1 | 02/12/2019 | 10/12/2019 | 01/12/2019 | 10/12/2019 | 0 | TK_Complete | 1208363553 | 8 | 1208363553_8
MRPP2-MGT.11903 | TT_Task | Design Plan - PTA Review ; Comment Rev0 EMU M1 | 15/04/2020 | 12/05/2020 | 15/04/2020 | 12/05/2020 | 0 | TK_Complete | 1208363553 | 9 | 1208363553_9
MRPP2-MGT.11933 | TT_Task | Design Plan Resubmit Rev. 0 EMU M1 | 11/12/2019 | 14/04/2020 | 11/12/2019 | 14/04/2020 | 0 | TK_Complete | 1208363553 | 8 | 1208363553_8
MRPP2-MGT.12013 | TT_Task | Design Plan - Resubmit Rev.1 EMU M1 | 13/05/2020 | 16/06/2020 | 13/05/2020 | 16/06/2020 | 0 | TK_Complete | 1208363553 | 8 | 1208363553_8
MRPP2-MGT.12023 | TT_Task | Design Plan - PTA Review ; Comment Rev,1 EMU M1 | 17/06/2020 | 10/07/2020 | 17/06/2020 | 10/07/2020 | 0 | TK_Complete | 1208363553 | 9 | 1208363553_9
MRPP2-MGT.12063 | TT_Task | Design Plan - Resubmit Rev.2 EMU M1 | 13/07/2020 | 03/08/2020 | 13/07/2020 | 03/08/2020 | 0 | TK_Complete | 1208363553 | 8 | 1208363553_8
MRPP2-MGT.12073 | TT_Task | Design Plan - PTA Review ; Comment Rev,2 EMU M1 | 04/08/2020 | 28/08/2020 | 04/08/2020 | 28/08/2020 | 0 | TK_Complete | 1208363553 | 9 | 1208363553_9
MRPP2-MGT.10040 | TT_Task | Sch. 5 - Occupational Safety and Health Management Plan | 11/12/2019 | 10/01/2020 | 11/12/2019 | 10/01/2020 | 0 | TK_Complete | 1208363553 | 10 | 1208363553_10
MRPP2-MGT.10170 | TT_Task | Sch. 5 - Occupational Safety and Health Management Plan PTA Review Rev.1 | 13/01/2020 | 04/02/2020 | 13/01/2020 | 04/02/2020 | 0 | TK_Complete | 1208363553 | 10 | 1208363553_10
MRPP2-MGT.10230 | TT_Task | Sch. 5 - Occupational Safety and Health Management Plan Incorporate Comments ; Resubmit Rev.2 | 05/02/2020 | 24/02/2020 | 05/02/2020 | 24/02/2020 | 0 | TK_Complete | 1208363553 | 10 | 1208363553_10
MRPP2-MGT.11973 | TT_Task | Sch. 5 - Occupational Safety and Health Management Plan PTA Review Rev.2 ; Approval | 25/02/2020 | 03/03/2020 | 25/02/2020 | 03/03/2020 | 0 | TK_Complete | 1208363553 | 10 | 1208363553_10
MRPP2-MGT.10030 | TT_Task | Sch. 5 - Quality Management Plan | 11/12/2019 | 10/01/2020 | 11/12/2019 | 10/01/2020 | 0 | TK_Complete | 1208363553 | 11 | 1208363553_11
MRPP2-MGT.10160 | TT_Task | Sch. 5 - Quality Management Plan PTA Review Rev.1 | 13/01/2020 | 04/02/2020 | 13/01/2020 | 04/02/2020 | 0 | TK_Complete | 1208363553 | 11 | 1208363553_11
MRPP2-MGT.10220 | TT_Task | Sch. 5 - Quality Management Plan Incorporate Comments ; Resubmit Rev.2 | 05/02/2020 | 10/03/2020 | 05/02/2020 | 10/03/2020 | 0 | TK_Complete | 1208363553 | 12 | 1208363553_12
MRPP2-MGT.11983 | TT_Task | Sch. 5 - Quality Management Plan PTA Review Rev.2 ; Approval | 11/03/2020 | 25/03/2020 | 11/03/2020 | 25/03/2020 | 0 | TK_Complete | 1208363553 | 11 | 1208363553_11
MRPP2-MGT.10010 | TT_Task | Sch. 5 - Aboriginal Engagement and Participation Plan | 11/12/2019 | 10/01/2020 | 11/12/2019 | 10/01/2020 | 0 | TK_Complete | 1208363553 | 13 | 1208363553_13
MRPP2-MGT.10140 | TT_Task | Sch. 5 - Aboriginal Engagement and Participation Plan PTA 1st Review ; Comments | 13/01/2020 | 10/02/2020 | 13/01/2020 | 10/02/2020 | 0 | TK_Complete | 1208363553 | 13 | 1208363553_13
MRPP2-MGT.10200 | TT_Task | Sch. 5 - Aboriginal Engagement and Participation Plan Incorporate Comments and Resubmit Rev.2 | 11/02/2020 | 03/04/2020 | 11/02/2020 | 03/04/2020 | 0 | TK_Complete | 1208363553 | 13 | 1208363553_13
MRPP2-MGT.11963 | TT_Task | Sch. 5 - Aboriginal Engagement and Participation Plan PTA 2nd Review ; Comments | 06/04/2020 | 05/05/2020 | 06/04/2020 | 05/05/2020 | 0 | TK_Complete | 1208363553 | 13 | 1208363553_13
MRPP2-MGT.12033 | TT_Task | Sch. 5 - Aboriginal Engagement and Participation Plan Incorporate Comments and Resubmit Rev.3 | 06/05/2020 | 28/06/2021 | 06/05/2020 | 28/06/2021 | 0 | TK_Complete | 1208363553 | 13 | 1208363553_13
MRPP2-MGT.12043 | TT_Task | Sch. 5 - Aboriginal Engagement and Participation Plan PTA 3nd Review ; Approval | 29/06/2021 | 02/11/2021 | 29/06/2021 | 02/11/2021 | 0 | TK_Complete | 1208363553 | 13 | 1208363553_13
MRPP2-MGT.10050 | TT_Task | Sch. 5 - Record Keeping Plan | 11/12/2019 | 10/01/2020 | 11/12/2019 | 10/01/2020 | 0 | TK_Complete | 1208363553 | 14 | 1208363553_14
MRPP2-MGT.10180 | TT_Task | Sch. 5 - Record Keeping Plan PTA 1st Review ; Comments | 13/01/2020 | 10/02/2020 | 13/01/2020 | 10/02/2020 | 0 | TK_Complete | 1208363553 | 14 | 1208363553_14
MRPP2-MGT.10240 | TT_Task | Sch. 5 - Record Keeping Plan Incorporate Comments and Resubmit Rev.2 | 11/02/2020 | 20/03/2020 | 11/02/2020 | 20/03/2020 | 0 | TK_Complete | 1208363553 | 14 | 1208363553_14
MRPP2-MGT.11993 | TT_Task | Sch. 5 - Record Keeping Plan PTA 2nd Review ; Approval | 23/03/2020 | 31/03/2020 | 21/03/2020 | 31/03/2020 | 0 | TK_Complete | 1208363553 | 14 | 1208363553_14
MRPP2-MGT.10020 | TT_Task | Sch. 5 - Environmental Management Plan (Delivery Phase) | 11/12/2019 | 10/01/2020 | 11/12/2019 | 10/01/2020 | 0 | TK_Complete | 1208363553 | 15 | 1208363553_15
MRPP2-MGT.10150 | TT_Task | Sch. 5 - Environmental Management Plan (Delivery Phase) PTA 1st Review ; Comments | 13/01/2020 | 04/02/2020 | 13/01/2020 | 04/02/2020 | 0 | TK_Complete | 1208363553 | 16 | 1208363553_16
MRPP2-MGT.10210 | TT_Task | Sch. 5 - Environmental Management Plan (Delivery Phase) Incorporate Comments ; Resubmit Rev.2 | 05/02/2020 | 10/03/2020 | 05/02/2020 | 10/03/2020 | 0 | TK_Complete | 1208363553 | 12 | 1208363553_12
MRPP2-MGT.12003 | TT_Task | Sch. 5 - Environmental Management Plan (Delivery Phase) PTA 2nd Review ; Approval | 11/03/2020 | 26/03/2020 | 11/03/2020 | 26/03/2020 | 0 | TK_Complete | 1208363553 | 16 | 1208363553_16
MRPP2-MGT.10310 | TT_Task | Sch. 5 - Maintenance Services Management Plan | 07/02/2020 | 29/05/2020 | 07/02/2020 | 29/05/2020 | 0 | TK_Complete | 1208363553 | 15 | 1208363553_15
MRPP2-MGT.10340 | TT_Task | Sch. 5 - Maintenance Services Management Plan PTA Review Rev.1 | 02/06/2020 | 23/06/2020 | 02/06/2020 | 23/06/2020 | 0 | TK_Complete | 1208363553 | 17 | 1208363553_17
MRPP2-MGT.10350 | TT_Task | Sch. 5 - Maintenance Services Management Plan Incorporate Comments and Resubmit Rev. 2 | 24/06/2020 | 12/11/2020 | 24/06/2020 | 12/11/2020 | 0 | TK_Complete | 1208363553 | 12 | 1208363553_12
MRPP2-MGT.12103 | TT_Task | Sch. 5 - Maintenance Services Management Plan PTA Review Rev.2 | 13/11/2020 | 10/12/2020 | 13/11/2020 | 10/12/2020 | 0 | TK_Complete | 1208363553 | 17 | 1208363553_17
MRPP2-MGT.10190 | TT_Task | Sch. 5 - Rail Safety Management System and Rail Safety Management Plan | 11/12/2019 | 17/04/2020 | 11/12/2019 | 17/04/2020 | 0 | TK_Complete | 1208363553 | 18 | 1208363553_18
MRPP2-MGT.10260 | TT_Task | Sch. 5 - Rail Safety Management System and Rail Safety Management Plan PTA 1st Review ; Comments | 20/04/2020 | 14/05/2020 | 20/04/2020 | 14/05/2020 | 0 | TK_Complete | 1208363553 | 19 | 1208363553_19
MRPP2-MGT.10270 | TT_Task | Sch. 5 - Rail Safety Management System and Rail Safety Management Plan Resubmit Rev.2 | 15/05/2020 | 02/06/2020 | 15/05/2020 | 02/06/2020 | 0 | TK_Complete | 1208363553 | 18 | 1208363553_18
MRPP2-MGT.12053 | TT_Task | Sch. 5 - Rail Safety Management System and Rail Safety Management Plan PTA 2nd Review ; Comments | 03/06/2020 | 26/06/2020 | 03/06/2020 | 26/06/2020 | 0 | TK_Complete | 1208363553 | 19 | 1208363553_19
MRPP2-MGT.12083 | TT_Task | Sch. 5 - Rail Safety Management System and Rail Safety Management Plan Resubmit Rev.3 | 29/06/2020 | 03/08/2020 | 29/06/2020 | 03/08/2020 | 0 | TK_Complete | 1208363553 | 18 | 1208363553_18
MRPP2-MGT.12093 | TT_Task | Sch. 5 - Rail Safety Management System and Rail Safety Management Plan PTA 3rd Review ; Comments | 04/08/2020 | 27/08/2020 | 04/08/2020 | 27/08/2020 | 0 | TK_Complete | 1208363553 | 19 | 1208363553_19
MRPP2-MGT.12113 | TT_Task | Sch. 5 - Rail Safety Management System and Rail Safety Management Plan Resubmit Rev.4 | 28/08/2020 | 16/09/2020 | 28/08/2020 | 16/09/2020 | 0 | TK_Complete | 1208363553 | 18 | 1208363553_18
MRPP2-MGT.12123 | TT_Task | Sch. 5 - Rail Safety Management System and Rail Safety Management Plan PTA 4th Review ; Approval | 17/09/2020 | 05/10/2020 | 17/09/2020 | 05/10/2020 | 0 | TK_Complete | 1208363553 | 19 | 1208363553_19
MRPP2-MGT.10280 | TT_Task | Sch. 5 - Inspection and Test Plan | 26/03/2020 | 09/09/2020 | 26/03/2020 | 09/09/2020 | 0 | TK_Complete | 1208363553 | 20 | 1208363553_20
MRPP2-MGT.10300 | TT_Task | Sch. 5 - Inspection and Test Plan PTA Review Rev.A | 10/09/2020 | 07/10/2020 | 10/09/2020 | 07/10/2020 | 0 | TK_Complete | 1208363553 | 20 | 1208363553_20
MRPP2-MGT.10320 | TT_Task | Sch. 5 - Inspection and Test Plan Incorporate Comments and Submit Rev.B | 08/10/2020 | 07/01/2021 | 08/10/2020 | 07/01/2021 | 0 | TK_Complete | 1208363553 | 20 | 1208363553_20
MRPP2-MGT.12133 | TT_Task | Sch. 5 - Inspection and Test Plan PTA Review ; Approval Rev.B | 08/01/2021 | 08/02/2021 | 08/01/2021 | 08/02/2021 | 0 | TK_Complete | 1208363553 | 20 | 1208363553_20
MRPP2-MGT.10370 | TT_Task | Sch. 5 - Technical Maintenance Plan | 28/12/2022 | 23/02/2023 | nan | nan | 0 | TK_NotStart | 1208363553 | 15 | 1208363553_15
MRPP2-MGT.10410 | TT_Task | Sch. 5 - Technical Maintenance Plan PTA Review | 24/02/2023 | 23/03/2023 | nan | nan | 0 | TK_NotStart | 1208363553 | 17 | 1208363553_17
MRPP2-MGT.10430 | TT_Task | Sch. 5 - Technical Maintenance Plan Incorporate Comments | 24/03/2023 | 06/04/2023 | nan | nan | 1184 | TK_NotStart | 1208363553 | 12 | 1208363553_12
MRPP2-MGT.10440 | TT_Task | Sch. 5 - Environmental Management Plan (Maintenance Phase) | 31/03/2023 | 30/05/2023 | nan | nan | 0 | TK_NotStart | 1208363553 | 15 | 1208363553_15
MRPP2-MGT.10460 | TT_Task | Sch. 5 - Environmental Management Plan (Maintenance Phase) PTA Review | 31/05/2023 | 28/06/2023 | nan | nan | 0 | TK_NotStart | 1208363553 | 16 | 1208363553_16
MRPP2-MGT.10470 | TT_Task | Sch. 5 - Environmental Management Plan (Maintenance Phase) Incorporate Comments | 29/06/2023 | 12/07/2023 | nan | nan | 1104 | TK_NotStart | 1208363553 | 12 | 1208363553_12
MRPP2-MGT.10360 | TT_Task | Sch. 5 - Training Plan | 25/09/2020 | 12/03/2021 | 25/09/2020 | 12/03/2021 | 0 | TK_Complete | 1208363553 | 21 | 1208363553_21
MRPP2-MGT.10390 | TT_Task | Sch. 5 - Training Plan PTA Review Rev.A | 15/03/2021 | 15/04/2021 | 15/03/2021 | 15/04/2021 | 0 | TK_Complete | 1208363553 | 21 | 1208363553_21
MRPP2-MGT.10420 | TT_Task | Sch. 5 - Training Plan Incorporate Comments ; Submit Rev.B | 16/04/2021 | 29/07/2021 | 16/04/2021 | 29/07/2021 | 0 | TK_Complete | 1208363553 | 7 | 1208363553_7
MRPP2-MGT.12143 | TT_Task | Sch. 5 - Training Plan PTA Review Rev.B | 30/07/2021 | 27/08/2021 | 30/07/2021 | 27/08/2021 | 0 | TK_Complete | 1208363553 | 21 | 1208363553_21
MRPP2-DE1.10410 | TT_Task | Train Specification EMU M1 | 28/11/2019 | 28/02/2020 | 28/11/2019 | 28/02/2020 | 0 | TK_Complete | 1208363553 | 22 | 1208363553_22
MRPP2-DE1.10833 | TT_Task | Train Specification - PTA Design Review Rev.A EMU M1 | 03/03/2020 | 27/03/2020 | 02/03/2020 | 27/03/2020 | 0 | TK_Complete | 1208363553 | 23 | 1208363553_23
MRPP2-DE1.15183 | TT_Task | Train Specification - Resubmit Rev.B EMU M1 | 30/03/2020 | 04/06/2020 | 30/03/2020 | 04/06/2020 | 0 | TK_Complete | 1208363553 | 22 | 1208363553_22
MRPP2-DE1.15193 | TT_Task | Train Specification - PTA Design Review Rev.B EMU M1 | 05/06/2020 | 30/06/2020 | 05/06/2020 | 30/06/2020 | 0 | TK_Complete | 1208363553 | 23 | 1208363553_23
MRPP2-DE1.15613 | TT_Task | Train Specification - Resubmit Rev.C EMU M1 | 01/07/2020 | 31/07/2020 | 01/07/2020 | 31/07/2020 | 0 | TK_Complete | 1208363553 | 22 | 1208363553_22
MRPP2-DE1.15623 | TT_Task | Train Specification - PTA Design Review Rev.C EMU M1 | 03/08/2020 | 27/08/2020 | 03/08/2020 | 27/08/2020 | 0 | TK_Complete | 1208363553 | 23 | 1208363553_23
MRPP2-DE1.11363 | TT_Task | Document Management Plan (DMP) EMU M1 | 12/12/2019 | 26/03/2020 | 12/12/2019 | 26/03/2020 | 0 | TK_Complete | 1208363553 | 24 | 1208363553_24
MRPP2-DE1.11373 | TT_Task | Document Management Plan (DMP) - PTA Design Review Rev.A EMU M1 | 27/03/2020 | 21/04/2020 | 27/03/2020 | 21/04/2020 | 0 | TK_Complete | 1208363553 | 25 | 1208363553_25
MRPP2-DE1.15203 | TT_Task | Document Management Plan (DMP) - Resubmit Rev.B EMU M1 | 22/04/2020 | 30/04/2020 | 22/04/2020 | 30/04/2020 | 0 | TK_Complete | 1208363553 | 24 | 1208363553_24
MRPP2-DE1.15213 | TT_Task | Document Management Plan (DMP) - PTA Design Review Rev.B EMU M1 | 01/05/2020 | 14/05/2020 | 01/05/2020 | 14/05/2020 | 0 | TK_Complete | 1208363553 | 25 | 1208363553_25
MRPP2-DE2.12543 | TT_Task | Preliminary Design Specification - Equipment Mounting EMU M2 | 16/04/2020 | 30/07/2020 | 16/04/2020 | 30/07/2020 | 0 | TK_Complete | 1208363553 | 26 | 1208363553_26
MRPP2-DE2.12563 | TT_Task | Preliminary Design Specification - Equipment Mounting - PTA Design Review Rev.A EMU M2 | 31/07/2020 | 25/08/2020 | 31/07/2020 | 25/08/2020 | 0 | TK_Complete | 1208363553 | 26 | 1208363553_26
MRPP2-DE2.18213 | TT_Task | Preliminary Design Specification - Equipment Mounting - Resubmit Rev.B EMU M2 | 26/08/2020 | 21/09/2020 | 26/08/2020 | 21/09/2020 | 0 | TK_Complete | 1208363553 | 26 | 1208363553_26
MRPP2-DE2.18223 | TT_Task | Preliminary Design Specification - Equipment Mounting - PTA Design Review Rev.B EMU M2 | 21/09/2020 | 14/10/2020 | 21/09/2020 | 14/10/2020 | 0 | TK_Complete | 1208363553 | 26 | 1208363553_26
MRPP2-DE2.12743 | TT_Task | Preliminary Kinematic Envelope Calculation Report EMU M2 | 05/06/2020 | 07/07/2020 | 05/06/2020 | 07/07/2020 | 0 | TK_Complete | 1208363553 | 27 | 1208363553_27
MRPP2-DE2.12763 | TT_Task | Preliminary Kinematic Envelope Calculation Report - PTA Design Review Rev.A EMU M2 | 08/07/2020 | 31/07/2020 | 08/07/2020 | 31/07/2020 | 0 | TK_Complete | 1208363553 | 28 | 1208363553_28
MRPP2-DE2.18133 | TT_Task | Preliminary Kinematic Envelope Calculation Report - Resubmit Rev.B EMU M2 | 03/08/2020 | 21/10/2020 | 03/08/2020 | 21/10/2020 | 0 | TK_Complete | 1208363553 | 27 | 1208363553_27
MRPP2-DE2.18143 | TT_Task | Preliminary Kinematic Envelope Calculation Report - PTA Design Review Rev.B EMU M2 | 22/10/2020 | 17/11/2020 | 22/10/2020 | 17/11/2020 | 0 | TK_Complete | 1208363553 | 28 | 1208363553_28
MRPP2-DE2.12143 | TT_Task | Description for Neutral Section Detection and functioning EMU M2 | 22/07/2020 | 02/10/2020 | 22/07/2020 | 02/10/2020 | 0 | TK_Complete | 1208363553 | 29 | 1208363553_29
MRPP2-DE2.12163 | TT_Task | Description for Neutral Section Detection and functioning - PTA Design Review Rev.A EMU M2 | 05/10/2020 | 29/10/2020 | 05/10/2020 | 29/10/2020 | 0 | TK_Complete | 1208363553 | 29 | 1208363553_29
MRPP2-DE2.18533 | TT_Task | Description for Neutral Section Detection and functioning - Submit Rev.B EMU M2 | 30/10/2020 | 25/01/2021 | 30/10/2020 | 25/01/2021 | 0 | TK_Complete | 1208363553 | 29 | 1208363553_29
MRPP2-DE2.18543 | TT_Task | Description for Neutral Section Detection and functioning - PTA Design Review Rev.B EMU M2 | 27/01/2021 | 19/02/2021 | 27/01/2021 | 19/02/2021 | 0 | TK_Complete | 1208363553 | 29 | 1208363553_29
MRPP2-DE3.10420 | TT_Task | Train Configuration ; Main Dimensions EMU M3 | 16/10/2020 | 02/02/2021 | 16/10/2020 | 02/02/2021 | 0 | TK_Complete | 1208363553 | 30 | 1208363553_30
MRPP2-DE3.10813 | TT_Task | Train Configuration ; Main Dimensions - PTA Design Review Rev.A EMU M3 | 03/02/2021 | 03/03/2021 | 03/02/2021 | 03/03/2021 | 0 | TK_Complete | 1208363553 | 23 | 1208363553_23
MRPP2-DE3.22630 | TT_Task | Train Configuration ; Main Dimensions - Submit Rev.B EMU M3 | 04/03/2021 | 30/07/2021 | 04/03/2021 | 30/07/2021 | 0 | TK_Complete | 1208363553 | 30 | 1208363553_30
MRPP2-DE3.22640 | TT_Task | Train Configuration ; Main Dimensions - PTA Design Review Rev.B EMU M3 | 02/08/2021 | 31/08/2021 | 02/08/2021 | 31/08/2021 | 0 | TK_Complete | 1208363553 | 23 | 1208363553_23
MRPP2-DE3.27150 | TT_Task | Train Configuration ; Main Dimensions - Submit Rev.C EMU M3 | 01/09/2021 | 20/09/2021 | 01/09/2021 | 20/09/2021 | 0 | TK_Complete | 1208363553 | 30 | 1208363553_30
MRPP2-DE3.27160 | TT_Task | Train Configuration ; Main Dimensions - PTA Design Review Rev.C EMU M3 | 21/09/2021 | 21/10/2021 | 21/09/2021 | 21/10/2021 | 0 | TK_Complete | 1208363553 | 23 | 1208363553_23
MRPP2-DE3.10790 | TT_Task | Train Operation Control Description EMU M3 | 16/10/2020 | 27/01/2021 | 16/10/2020 | 27/01/2021 | 0 | TK_Complete | 1208363553 | 31 | 1208363553_31
MRPP2-DE3.10800 | TT_Task | Train Operation Control Description - PTA Design Review Rev.A EMU M3 | 28/01/2021 | 24/02/2021 | 28/01/2021 | 24/02/2021 | 0 | TK_Complete | 1208363553 | 32 | 1208363553_32
MRPP2-DE3.22570 | TT_Task | Train Operation Control Description - Submit Rev.B EMU M3 | 25/02/2021 | 09/04/2021 | 25/02/2021 | 09/04/2021 | 0 | TK_Complete | 1208363553 | 31 | 1208363553_31
MRPP2-DE3.22580 | TT_Task | Train Operation Control Description - PTA Design Review Rev.B EMU M3 | 12/04/2021 | 10/05/2021 | 12/04/2021 | 10/05/2021 | 0 | TK_Complete | 1208363553 | 32 | 1208363553_32
MRPP2-DE3.23350 | TT_Task | Train Operation Control Description - Submit Rev.C EMU M3 | 11/05/2021 | 12/07/2021 | 11/05/2021 | 12/07/2021 | 0 | TK_Complete | 1208363553 | 31 | 1208363553_31
MRPP2-DE3.23360 | TT_Task | Train Operation Control Description - PTA Design Review Rev.C EMU M3 | 13/07/2021 | 19/08/2021 | 13/07/2021 | 19/08/2021 | 0 | TK_Complete | 1208363553 | 32 | 1208363553_32
MRPP2-DE3.27170 | TT_Task | Train Operation Control Description - Submit Rev.D EMU M3 | 20/08/2021 | 26/11/2021 | 20/08/2021 | 26/11/2021 | 0 | TK_Complete | 1208363553 | 31 | 1208363553_31
MRPP2-DE3.27180 | TT_Task | Train Operation Control Description - PTA Design Review Rev.D EMU M3 | 29/11/2021 | 24/12/2021 | 29/11/2021 | 14/02/2022 | 0 | TK_Complete | 1208363553 | 32 | 1208363553_32
MRPP2-DE3.11090 | TT_Task | ILS Management Plan EMU M3 | 16/10/2020 | 28/10/2020 | 16/10/2020 | 28/10/2020 | 0 | TK_Complete | 1208363553 | 33 | 1208363553_33
MRPP2-DE3.11100 | TT_Task | ILS Management Plan - PTA Design Review Rev.A EMU M3 | 29/10/2020 | 24/11/2020 | 29/10/2020 | 24/11/2020 | 0 | TK_Complete | 1208363553 | 34 | 1208363553_34
MRPP2-DE3.22450 | TT_Task | ILS Management Plan - Submit Rev.B EMU M3 | 25/11/2020 | 23/02/2021 | 25/11/2020 | 23/02/2021 | 0 | TK_Complete | 1208363553 | 33 | 1208363553_33
MRPP2-DE3.22460 | TT_Task | ILS Management Plan - PTA Design Review Rev.B EMU M3 | 24/02/2021 | 25/03/2021 | 24/02/2021 | 25/03/2021 | 0 | TK_Complete | 1208363553 | 34 | 1208363553_34
MRPP2-DE3.10933 | TT_Task | Maintenance Demonstration plan EMU M3 | 16/10/2020 | 12/01/2021 | 16/10/2020 | 12/01/2021 | 0 | TK_Complete | 1208363553 | 35 | 1208363553_35
MRPP2-DE3.10943 | TT_Task | Maintenance Demonstration plan - PTA Design Review EMU M3 | 13/01/2021 | 11/02/2021 | 13/01/2021 | 11/02/2021 | 0 | TK_Complete | 1208363553 | 35 | 1208363553_35
MRPP2-DE3.12340 | TT_Task | Final Kinematic Envelope Calculation Report EMU M3 | 16/11/2020 | 01/09/2021 | 16/11/2020 | 01/09/2021 | 0 | TK_Complete | 1208363553 | 27 | 1208363553_27
MRPP2-DE3.12360 | TT_Task | Final Kinematic Envelope Calculation Report - PTA Design Review Rev. A EMU M3 | 02/09/2021 | 14/10/2021 | 02/09/2021 | 14/10/2021 | 0 | TK_Complete | 1208363553 | 28 | 1208363553_28
MRPP2-DE3.28210 | TT_Task | Final Kinematic Envelope Calculation Report - Submit Rev. B EMU M3 | 15/10/2021 | 29/11/2021 | 15/10/2021 | 29/11/2021 | 0 | TK_Complete | 1208363553 | 27 | 1208363553_27
MRPP2-DE3.28220 | TT_Task | Final Kinematic Envelope Calculation Report - PTA Design Review Rev. B EMU M3 | 30/11/2021 | 03/01/2022 | 30/11/2021 | 31/01/2022 | 0 | TK_Complete | 1208363553 | 28 | 1208363553_28
MRPP2-DE3.13700 | TT_Task | Harmonic Calculations Report EMU M3 | 11/01/2021 | 25/02/2021 | 11/01/2021 | 25/02/2021 | 0 | TK_Complete | 1208363553 | 36 | 1208363553_36
MRPP2-DE3.13720 | TT_Task | Harmonic Calculations Report - PTA Design Review EMU M3 | 26/02/2021 | 26/03/2021 | 26/02/2021 | 26/03/2021 | 0 | TK_Complete | 1208363553 | 36 | 1208363553_36
MRPP2-DE3.19010 | TT_Task | Design and CAD guidelines EMU - PTA Review Rev.A | 30/07/2020 | 24/08/2020 | 30/07/2020 | 24/08/2020 | 0 | TK_Complete | 1208363553 | 37 | 1208363553_37
MRPP2-DE3.22390 | TT_Task | Design and CAD guidelines EMU - Submission Rev.B | 25/08/2020 | 05/11/2020 | 25/08/2020 | 05/11/2020 | 0 | TK_Complete | 1208363553 | 37 | 1208363553_37
MRPP2-DE3.22400 | TT_Task | Design and CAD guidelines EMU - PTA Review ; Approval Rev.B | 06/11/2020 | 02/12/2020 | 06/11/2020 | 02/12/2020 | 0 | TK_Complete | 1208363553 | 37 | 1208363553_37
MRPP2-DE3.19030 | TT_Task | Safety Validation Plan EMU - PTA Review and Comments Rev.A | 06/04/2021 | 05/05/2021 | 06/04/2021 | 05/05/2021 | 0 | TK_Complete | 1208363553 | 38 | 1208363553_38
MRPP2-DE3.23390 | TT_Task | Safety Validation Plan EMU - Submission Rev.B | 06/05/2021 | 27/07/2021 | 06/05/2021 | 27/07/2021 | 0 | TK_Complete | 1208363553 | 39 | 1208363553_39
MRPP2-DE3.23400 | TT_Task | Safety Validation Plan EMU - PTA Review and Approval Rev.B | 28/07/2021 | 26/08/2021 | 28/07/2021 | 26/08/2021 | 0 | TK_Complete | 1208363553 | 38 | 1208363553_38
MRPP2-DE3.27190 | TT_Task | Safety Validation Plan EMU - Submission Rev.C | 27/08/2021 | 12/10/2021 | 27/08/2021 | 12/10/2021 | 0 | TK_Complete | 1208363553 | 39 | 1208363553_39
MRPP2-DE3.27200 | TT_Task | Safety Validation Plan EMU - PTA Review Rev.C | 13/10/2021 | 12/11/2021 | 13/10/2021 | 12/11/2021 | 0 | TK_Complete | 1208363553 | 38 | 1208363553_38
MRPP2-DE3.28230 | TT_Task | Safety Validation Plan EMU - Submission Rev.D | 15/11/2021 | 10/02/2022 | 15/11/2021 | nan | 0 | TK_Active | 1208363553 | 39 | 1208363553_39
MRPP2-DE3.28240 | TT_Task | Safety Validation Plan EMU - PTA Review Rev.D | 13/04/2022 | 11/05/2022 | nan | nan | 64712 | TK_NotStart | 1208363553 | 38 | 1208363553_38
MRPP2-DE3.18990 | TT_Task | Project Management Plan EMU - PTA Review and Approval | 30/06/2020 | 27/07/2020 | 30/06/2020 | 27/07/2020 | 0 | TK_Complete | 1208363553 | 40 | 1208363553_40
MRPP2-DE3.19070 | TT_Task | Maintainability Plan EMU - PTA Review and Approval | 24/02/2020 | 11/06/2020 | 24/02/2020 | 11/06/2020 | 0 | TK_Complete | 1208363553 | 41 | 1208363553_41
MRPP2-DE3.19100 | TT_Task | Project Quality Plan, Associated Procedures EMU - PTA Review and Approval | 31/08/2020 | 25/09/2020 | 31/08/2020 | 25/09/2020 | 0 | TK_Complete | 1208363553 | 40 | 1208363553_40
MRPP2-DE3.19110 | TT_Task | Life cycle Cost Plan EMU - PTA Review and Approval | 16/10/2020 | 11/11/2020 | 16/10/2020 | 11/11/2020 | 0 | TK_Complete | 1208363553 | 42 | 1208363553_42
MRPP2-DE3.19120 | TT_Task | IDTP General Presentation EMU - PTA Review and Approval Rev.A | 17/03/2021 | 10/12/2021 | 17/03/2021 | 10/05/2021 | 0 | TK_Complete | 1208363553 | 43 | 1208363553_43
MRPP2-DE3.29400 | TT_Task | IDTP General Presentation EMU - Submission Rev.B | 04/03/2022 | 17/03/2022 | 11/05/2021 | nan | 0 | TK_Active | 1208363553 | 43 | 1208363553_43
MRPP2-DE3.29410 | TT_Task | IDTP General Presentation EMU - PTA Review and Approval Rev.B | 13/05/2022 | 10/06/2022 | nan | nan | 64544 | TK_NotStart | 1208363553 | 43 | 1208363553_43
MRPP2-DE3.19180 | TT_Task | Static Sway Type Test Procedure EMU - PTA Review Rev.A | 28/01/2022 | 24/02/2022 | 24/01/2022 | 21/02/2022 | 0 | TK_Complete | 1208363553 | 44 | 1208363553_44
MRPP2-DE3.29500 | TT_Task | Static Sway Type Test Procedure EMU - Submission Rev.B | 28/01/2022 | 10/02/2022 | 22/02/2022 | 08/03/2022 | 0 | TK_Complete | 1208363553 | 44 | 1208363553_44
MRPP2-DE3.29510 | TT_Task | Static Sway Type Test Procedure EMU - PTA Review Rev.B | 28/04/2022 | 25/05/2022 | 09/03/2022 | nan | 64872 | TK_Active | 1208363553 | 44 | 1208363553_44
MRPP2-DE3.19210 | TT_Task | Lifting Ability Type Test Procedure EMU - PTA Review and Approval | 30/06/2021 | 26/08/2021 | 30/06/2021 | 26/08/2021 | 0 | TK_Complete | 1208363553 | 45 | 1208363553_45
MRPP2-DE3.19140 | TT_Task | Static Gauge Type Test Procedure EMU - PTA Review Rev.A | 01/11/2021 | 19/11/2021 | 01/11/2021 | 19/11/2021 | 0 | TK_Complete | 1208363553 | 46 | 1208363553_46
MRPP2-DE3.28250 | TT_Task | Static Gauge Type Test Procedure EMU - Submission Rev.B | 22/11/2021 | 23/12/2021 | 22/11/2021 | 09/03/2022 | 0 | TK_Complete | 1208363553 | 46 | 1208363553_46
MRPP2-DE3.28260 | TT_Task | Static Gauge Type Test Procedure EMU - PTA Review Rev.B | 18/04/2022 | 16/05/2022 | 10/03/2022 | nan | 64864 | TK_Active | 1208363553 | 46 | 1208363553_46
MRPP2-DE3.19810 | TT_Task | Driving Functional Type Test Procedure - DRV EMU - PTA Review Rev.A | 28/01/2022 | 24/02/2022 | 16/12/2021 | 20/12/2021 | 0 | TK_Complete | 1208363553 | 47 | 1208363553_47
MRPP2-DE3.28920 | TT_Task | Driving Functional Type Test Procedure - DRV EMU - Submission Rev. B | 28/01/2022 | 24/02/2022 | 21/12/2021 | 03/02/2022 | 0 | TK_Complete | 1208363553 | 47 | 1208363553_47
MRPP2-DE3.28930 | TT_Task | Driving Functional Type Test Procedure - DRV EMU - PTA Review Rev.B | 24/03/2022 | 22/04/2022 | 04/02/2022 | 21/02/2022 | 0 | TK_Complete | 1208363553 | 47 | 1208363553_47
MRPP2-DE3.19890 | TT_Task | Fire ; Smoke Detection Functional Type Test Procedure ? FSD EMU - PTA Review Rev.A | 03/02/2022 | 02/03/2022 | 03/12/2021 | 01/02/2022 | 0 | TK_Complete | 1208363553 | 48 | 1208363553_48
MRPP2-DE3.29340 | TT_Task | Fire ; Smoke Detection Functional Type Test Procedure ? FSD EMU - Submission Rev.B | 04/03/2022 | 17/03/2022 | 02/02/2022 | nan | 0 | TK_Active | 1208363553 | 48 | 1208363553_48
MRPP2-DE3.29350 | TT_Task | Fire ; Smoke Detection Functional Type Test Procedure ? FSD EMU - PTA Review Rev.B | 22/04/2022 | 20/05/2022 | nan | nan | 64656 | TK_NotStart | 1208363553 | 48 | 1208363553_48
MRPP2-DE3.19910 | TT_Task | Kinematic Envelope Type Test Procedure EMU - PTA Review Rev.A | 03/02/2022 | 02/03/2022 | 22/12/2021 | 11/02/2022 | 0 | TK_Complete | 1208363553 | 49 | 1208363553_49
MRPP2-DE3.29420 | TT_Task | Kinematic Envelope Type Test Procedure EMU - Submission Rev.B | 04/03/2022 | 17/03/2022 | 14/02/2022 | nan | 0 | TK_Active | 1208363553 | 49 | 1208363553_49
MRPP2-DE3.29430 | TT_Task | Kinematic Envelope Type Test Procedure EMU - PTA Review Rev.B | 22/04/2022 | 20/05/2022 | nan | nan | 64656 | TK_NotStart | 1208363553 | 49 | 1208363553_49
MRPP2-DE3.19930 | TT_Task | Traction and Braking Performance Dynamic Type Test Procedure EMU - PTA Review and Approval | 26/04/2022 | 23/05/2022 | nan | nan | 64648 | TK_NotStart | 1208363553 | 50 | 1208363553_50
MRPP2-DE3.19940 | TT_Task | WSP Type Test Procedure EMU - PTA Review and Approval | 28/04/2022 | 25/05/2022 | nan | nan | 64632 | TK_NotStart | 1208363553 | 51 | 1208363553_51
MRPP2-DE3.19960 | TT_Task | Resistance to Motion Type Test Procedure EMU - PTA Review Rev.A | 28/01/2022 | 24/02/2022 | 22/11/2021 | 13/12/2021 | 0 | TK_Complete | 1208363553 | 52 | 1208363553_52
MRPP2-DE3.28940 | TT_Task | Resistance to Motion Type Test Procedure EMU - Submission Rev.B | 28/01/2022 | 10/02/2022 | 14/12/2021 | 24/01/2022 | 0 | TK_Complete | 1208363553 | 52 | 1208363553_52
MRPP2-DE3.28950 | TT_Task | Resistance to Motion Type Test Procedure EMU - PTA Review Rev.B | 28/01/2022 | 24/02/2022 | 25/01/2022 | 10/03/2022 | 0 | TK_Complete | 1208363553 | 52 | 1208363553_52
MRPP2-DE3.19970 | TT_Task | Journey Time Check Type Test Procedure EMU - PTA Review and Approval | 03/11/2021 | 30/11/2021 | 03/11/2021 | 30/11/2021 | 0 | TK_Complete | 1208363553 | 53 | 1208363553_53
MRPP2-DE3.19980 | TT_Task | Rescue Type Test Procedure EMU - PTA Review Rev.A | 03/11/2021 | 10/12/2021 | 03/11/2021 | 13/12/2021 | 0 | TK_Complete | 1208363553 | 54 | 1208363553_54
MRPP2-DE3.28960 | TT_Task | Rescue Type Test Procedure EMU - Submission Rev.B | 28/01/2022 | 10/02/2022 | 14/12/2021 | 09/03/2022 | 0 | TK_Complete | 1208363553 | 54 | 1208363553_54
MRPP2-DE3.28970 | TT_Task | Rescue Type Test Procedure EMU - PTA Review Rev.B | 19/04/2022 | 17/05/2022 | 10/03/2022 | 25/03/2022 | 0 | TK_Complete | 1208363553 | 54 | 1208363553_54
MRPP2-DE3.29880 | TT_Task | Rescue Type Test Procedure EMU - Submission Rev.C | 28/01/2022 | 10/02/2022 | 28/03/2022 | nan | 0 | TK_Active | 1208363553 | 54 | 1208363553_54
MRPP2-DE3.29890 | TT_Task | Rescue Type Test Procedure EMU - PTA Review Rev.C | 22/04/2022 | 20/05/2022 | nan | nan | 64656 | TK_NotStart | 1208363553 | 54 | 1208363553_54
MRPP2-DE3.19990 | TT_Task | Energy Consumption Type Test Procedure EMU - PTA Review and Approval | 29/04/2022 | 26/05/2022 | nan | nan | 64624 | TK_NotStart | 1208363553 | 55 | 1208363553_55
MRPP2-DE3.20020 | TT_Task | Ride Comfort Type Test Procedure EMU - PTA Review and Approval | 26/04/2022 | 23/05/2022 | nan | nan | 64648 | TK_NotStart | 1208363553 | 56 | 1208363553_56
MRPP2-DE3.20050 | TT_Task | Total Harmonic Distortion Type Test Procedure EMU - PTA Review and Approval (Doc Propose to Delete) | 11/05/2022 | 08/06/2022 | nan | nan | 64560 | TK_NotStart | 1208363553 | 57 | 1208363553_57
MRPP2-DE3.19620 | TT_Task | Type Test Specification - Gauging (Static + Kinematic) EMU - PTA Review and Approval (Doc Propose to Delete) | 11/05/2022 | 08/06/2022 | nan | nan | 64560 | TK_NotStart | 1208363553 | 58 | 1208363553_58
MRPP2-DE3.19740 | TT_Task | Operation ; MaintenanceManuals Plan EMU - PTA Review Rev. A | 10/05/2021 | 03/06/2021 | 10/05/2021 | 03/06/2021 | 0 | TK_Complete | 1208363553 | 59 | 1208363553_59
MRPP2-DE3.23600 | TT_Task | Operation ; MaintenanceManuals Plan EMU - Submission Rev.B | 04/06/2021 | 14/10/2021 | 04/06/2021 | 14/10/2021 | 0 | TK_Complete | 1208363553 | 60 | 1208363553_60
MRPP2-DE3.23610 | TT_Task | Operation ; MaintenanceManuals Plan EMU - PTA Review and Approval Rev. B | 15/10/2021 | 24/11/2021 | 15/10/2021 | 24/11/2021 | 0 | TK_Complete | 1208363553 | 59 | 1208363553_59
MRPP2-DE3.28270 | TT_Task | Operation ; MaintenanceManuals Plan EMU - Submission Rev.C | 25/11/2021 | 31/01/2022 | 25/11/2021 | nan | 0 | TK_Active | 1208363553 | 60 | 1208363553_60
MRPP2-DE3.28280 | TT_Task | Operation ; MaintenanceManuals Plan EMU - PTA Review and Approval Rev. C | 16/05/2022 | 13/06/2022 | nan | nan | 64536 | TK_NotStart | 1208363553 | 59 | 1208363553_59
MRPP2-DE3.20070 | TT_Task | Training Manual for Train Operators EMU - PTA Review and Approval | 08/07/2022 | 04/08/2022 | nan | nan | 2136 | TK_NotStart | 1208363553 | 61 | 1208363553_61
MRPP2-DE3.20080 | TT_Task | Training Manual for Maintenance Staff EMU - PTA Review and Approval | 08/07/2022 | 04/08/2022 | nan | nan | 2136 | TK_NotStart | 1208363553 | 61 | 1208363553_61
MRPP2-DE3.20090 | TT_Task | Operation ; Maintenance Manuals EMU - PTA Review and Approval | 08/07/2022 | 04/08/2022 | nan | nan | 2136 | TK_NotStart | 1208363553 | 59 | 1208363553_59
MRPP2-DE1.12363 | TT_Task | Car Static Profile ; Carbody Cross Section Report EMU M1 | 12/12/2019 | 28/02/2020 | 12/12/2019 | 28/02/2020 | 0 | TK_Complete | 1208363553 | 62 | 1208363553_62
MRPP2-DE1.12383 | TT_Task | Car Static Profile ; Carbody Cross Section Report - PTA Design Review Rev.A EMU M1 | 03/03/2020 | 17/03/2020 | 02/03/2020 | 17/03/2020 | 0 | TK_Complete | 1208363553 | 62 | 1208363553_62
MRPP2-DE1.15033 | TT_Task | Car Static Profile ; Carbody Cross Section Report - PTA Design Review Rev.B EMU M1 | 02/04/2020 | 30/04/2020 | 02/04/2020 | 30/04/2020 | 0 | TK_Complete | 1208363553 | 62 | 1208363553_62
MRPP2-DE1.15043 | TT_Task | Car Static Profile ; Carbody Cross Section Report - Resubmit to PTA Rev.B EMU M1 | 18/03/2020 | 01/04/2020 | 18/03/2020 | 01/04/2020 | 0 | TK_Complete | 1208363553 | 62 | 1208363553_62
MRPP2-DE1.15373 | TT_Task | Car Static Profile ; Carbody Cross Section Report - Resubmit to PTA Rev.C EMU M1 | 01/05/2020 | 12/06/2020 | 01/05/2020 | 12/06/2020 | 0 | TK_Complete | 1208363553 | 62 | 1208363553_62
MRPP2-DE1.15383 | TT_Task | Car Static Profile ; Carbody Cross Section Report - PTA Design Review Rev.C EMU M1 | 15/06/2020 | 09/07/2020 | 15/06/2020 | 09/07/2020 | 0 | TK_Complete | 1208363553 | 62 | 1208363553_62
MRPP2-DE1.10883 | TT_Task | Preliminary Design Specification ? Carbody Structure including Load Cases EMU M1 | 25/02/2020 | 19/05/2020 | 25/02/2020 | 19/05/2020 | 0 | TK_Complete | 1208363553 | 63 | 1208363553_63
MRPP2-DE1.10893 | TT_Task | Preliminary Design Specification ? Carbody Structure including Load Cases - PTA Design Review Rev.A EMU M1 | 20/05/2020 | 17/06/2020 | 20/05/2020 | 17/06/2020 | 0 | TK_Complete | 1208363553 | 63 | 1208363553_63
MRPP2-DE1.15593 | TT_Task | Preliminary Design Specification ? Carbody Structure including Load Cases - Resubmit Rev.B EMU M1 | 18/06/2020 | 28/07/2020 | 18/06/2020 | 28/07/2020 | 0 | TK_Complete | 1208363553 | 63 | 1208363553_63
MRPP2-DE1.15603 | TT_Task | Preliminary Design Specification ? Carbody Structure including Load Cases - PTA Design Review Rev.B EMU M1 | 29/07/2020 | 24/08/2020 | 29/07/2020 | 24/08/2020 | 0 | TK_Complete | 1208363553 | 63 | 1208363553_63
MRPP2-DE2.10913 | TT_Task | Preliminary Carbody crashworthiness report EMU M2 | 22/07/2020 | 02/10/2020 | 22/07/2020 | 02/10/2020 | 0 | TK_Complete | 1208363553 | 64 | 1208363553_64
MRPP2-DE2.10923 | TT_Task | Preliminary Carbody crashworthiness report - PTA Design Review Rev.A EMU M2 | 05/10/2020 | 29/10/2020 | 05/10/2020 | 29/10/2020 | 0 | TK_Complete | 1208363553 | 65 | 1208363553_65
MRPP2-DE2.18553 | TT_Task | Preliminary Carbody crashworthiness report - Submit Rev.B EMU M2 | 30/10/2020 | 06/01/2021 | 30/10/2020 | 06/01/2021 | 0 | TK_Complete | 1208363553 | 64 | 1208363553_64
MRPP2-DE2.18563 | TT_Task | Preliminary Carbody crashworthiness report - PTA Design Review Rev.B EMU M2 | 07/01/2021 | 05/02/2021 | 07/01/2021 | 05/02/2021 | 0 | TK_Complete | 1208363553 | 65 | 1208363553_65
MRPP2-DE2.18863 | TT_Task | Preliminary Carbody crashworthiness report - Submit Rev.C EMU M2 | 08/02/2021 | 18/02/2021 | 08/02/2021 | 18/02/2021 | 0 | TK_Complete | 1208363553 | 64 | 1208363553_64
MRPP2-DE2.18873 | TT_Task | Preliminary Carbody crashworthiness report - PTA Design Review Rev.C EMU M2 | 19/02/2021 | 09/03/2021 | 19/02/2021 | 09/03/2021 | 0 | TK_Complete | 1208363553 | 65 | 1208363553_65
MRPP2-DE3.12100 | TT_Task | Car End Clearance Report EMU M3 | 12/10/2020 | 28/01/2021 | 12/10/2020 | 28/01/2021 | 0 | TK_Complete | 1208363553 | 66 | 1208363553_66
MRPP2-DE3.12120 | TT_Task | Car End Clearance Report - PTA Design Review Rev.A EMU M3 | 29/01/2021 | 25/02/2021 | 29/01/2021 | 25/02/2021 | 0 | TK_Complete | 1208363553 | 67 | 1208363553_67
MRPP2-DE3.22610 | TT_Task | Car End Clearance Report - Submit Rev.B EMU M3 | 26/02/2021 | 27/05/2021 | 26/02/2021 | 27/05/2021 | 0 | TK_Complete | 1208363553 | 66 | 1208363553_66
MRPP2-DE3.22620 | TT_Task | Car End Clearance Report - PTA Design Review Rev.B EMU M3 | 28/05/2021 | 29/06/2021 | 28/05/2021 | 29/06/2021 | 0 | TK_Complete | 1208363553 | 67 | 1208363553_67
MRPP2-DE3.12180 | TT_Task | Detailed Design Specification - Carbody Structure EMU M3 | 11/11/2020 | 02/02/2021 | 11/11/2020 | 02/02/2021 | 0 | TK_Complete | 1208363553 | 68 | 1208363553_68
MRPP2-DE3.12200 | TT_Task | Detailed Design Specification - Carbody Structure - PTA Design Review Rev.A EMU M3 | 03/02/2021 | 03/03/2021 | 03/02/2021 | 03/03/2021 | 0 | TK_Complete | 1208363553 | 68 | 1208363553_68
MRPP2-DE3.22650 | TT_Task | Detailed Design Specification - Carbody Structure - Submit Rev.B EMU M3 | 04/03/2021 | 18/05/2021 | 04/03/2021 | 18/05/2021 | 0 | TK_Complete | 1208363553 | 68 | 1208363553_68
MRPP2-DE3.22660 | TT_Task | Detailed Design Specification - Carbody Structure - PTA Design Review Rev.B EMU M3 | 19/05/2021 | 17/06/2021 | 19/05/2021 | 17/06/2021 | 0 | TK_Complete | 1208363553 | 68 | 1208363553_68
MRPP2-DE3.23880 | TT_Task | Detailed Design Specification - Carbody Structure - Submit Rev.C EMU M3 | 18/06/2021 | 04/10/2021 | 18/06/2021 | 04/10/2021 | 0 | TK_Complete | 1208363553 | 68 | 1208363553_68
MRPP2-DE3.23890 | TT_Task | Detailed Design Specification - Carbody Structure - PTA Design Review Rev.C EMU M3 | 05/10/2021 | 21/10/2021 | 05/10/2021 | 21/10/2021 | 0 | TK_Complete | 1208363553 | 68 | 1208363553_68
MRPP2-DE3.14420 | TT_Task | Equipment Mounting Detailed Design Specification (Roof, Underframe) EMU M3 | 27/01/2021 | 15/02/2021 | 27/01/2021 | 15/02/2021 | 0 | TK_Complete | 1208363553 | 69 | 1208363553_69
MRPP2-DE3.14440 | TT_Task | Equipment Mounting Detailed Design Specification (Roof, Underframe) - PTA Design Review Rev.A EMU M3 | 16/02/2021 | 16/03/2021 | 16/02/2021 | 16/03/2021 | 0 | TK_Complete | 1208363553 | 69 | 1208363553_69
MRPP2-DE3.22850 | TT_Task | Equipment Mounting Detailed Design Specification (Roof, Underframe) - Submit Rev.B EMU M3 | 17/03/2021 | 17/05/2021 | 17/03/2021 | 17/05/2021 | 0 | TK_Complete | 1208363553 | 69 | 1208363553_69
MRPP2-DE3.22860 | TT_Task | Equipment Mounting Detailed Design Specification (Roof, Underframe) - PTA Design Review Rev.B EMU M3 | 18/05/2021 | 09/09/2021 | 18/05/2021 | 09/09/2021 | 0 | TK_Complete | 1208363553 | 69 | 1208363553_69
MRPP2-DE3.27450 | TT_Task | Equipment Mounting Detailed Design Specification (Roof, Underframe) - Submit Rev.C EMU M3 | 10/09/2021 | 13/12/2021 | 10/09/2021 | 06/12/2021 | 0 | TK_Complete | 1208363553 | 69 | 1208363553_69
MRPP2-DE3.27460 | TT_Task | Equipment Mounting Detailed Design Specification (Roof, Underframe) - PTA Design Review Rev.C EMU M3 | 07/02/2022 | 04/03/2022 | 07/12/2021 | 25/02/2022 | 0 | TK_Complete | 1208363553 | 69 | 1208363553_69
MRPP2-DE3.14060 | TT_Task | Carbody Structure Detailed FEA Report EMU M3 | 27/01/2021 | 08/02/2021 | 27/01/2021 | 08/02/2021 | 0 | TK_Complete | 1208363553 | 70 | 1208363553_70
MRPP2-DE3.14080 | TT_Task | Carbody Structure Detailed FEA Report - PTA Design Review Rev.A EMU M3 | 09/02/2021 | 10/03/2021 | 09/02/2021 | 10/03/2021 | 0 | TK_Complete | 1208363553 | 70 | 1208363553_70
MRPP2-DE3.22670 | TT_Task | Carbody Structure Detailed FEA Report - Submit Rev.B EMU M3 | 11/03/2021 | 22/04/2021 | 11/03/2021 | 22/04/2021 | 0 | TK_Complete | 1208363553 | 70 | 1208363553_70
MRPP2-DE3.22680 | TT_Task | Carbody Structure Detailed FEA Report - PTA Design Review Rev.B EMU M3 | 23/04/2021 | 24/05/2021 | 23/04/2021 | 24/05/2021 | 0 | TK_Complete | 1208363553 | 70 | 1208363553_70
MRPP2-DE3.23410 | TT_Task | Carbody Structure Detailed FEA Report - Submit Rev.C EMU M3 | 25/05/2021 | 07/07/2021 | 25/05/2021 | 07/07/2021 | 0 | TK_Complete | 1208363553 | 70 | 1208363553_70
MRPP2-DE3.23420 | TT_Task | Carbody Structure Detailed FEA Report - PTA Design Review Rev.C EMU M3 | 08/07/2021 | 12/08/2021 | 08/07/2021 | 12/08/2021 | 0 | TK_Complete | 1208363553 | 70 | 1208363553_70
MRPP2-DE3.27210 | TT_Task | Carbody Structure Detailed FEA Report - Submit Rev.D EMU M3 | 13/08/2021 | 13/10/2021 | 13/08/2021 | 13/10/2021 | 0 | TK_Complete | 1208363553 | 70 | 1208363553_70
MRPP2-DE3.27220 | TT_Task | Carbody Structure Detailed FEA Report - PTA Design Review Rev.D EMU M3 | 14/10/2021 | 10/11/2021 | 14/10/2021 | 10/11/2021 | 0 | TK_Complete | 1208363553 | 70 | 1208363553_70
MRPP2-DE3.14100 | TT_Task | Carbody crashworthiness report EMU M3 | 27/01/2021 | 23/07/2021 | 27/01/2021 | 23/07/2021 | 0 | TK_Complete | 1208363553 | 64 | 1208363553_64
MRPP2-DE3.14120 | TT_Task | Carbody crashworthiness report - PTA Design Review Rev.A EMU M3 | 26/07/2021 | 23/08/2021 | 26/07/2021 | 23/08/2021 | 0 | TK_Complete | 1208363553 | 65 | 1208363553_65
MRPP2-DE3.27230 | TT_Task | Carbody crashworthiness report - Submit Rev.B EMU M3 | 24/08/2021 | 14/12/2021 | 24/08/2021 | 25/01/2022 | 0 | TK_Complete | 1208363553 | 64 | 1208363553_64
MRPP2-DE3.27240 | TT_Task | Carbody crashworthiness report - PTA Design Review Rev.B EMU M3 | 01/02/2022 | 28/02/2022 | 27/01/2022 | 25/02/2022 | 0 | TK_Complete | 1208363553 | 65 | 1208363553_65
MRPP2-DE3.19150 | TT_Task | Watertightness Type Test Procedure EMU - PTA Review Rev.A | 24/06/2021 | 26/07/2021 | 24/06/2021 | 26/07/2021 | 0 | TK_Complete | 1208363553 | 71 | 1208363553_71
MRPP2-DE3.24170 | TT_Task | Watertightness Type Test Procedure EMU - Submission Rev.B | 27/07/2021 | 11/10/2021 | 27/07/2021 | 11/10/2021 | 0 | TK_Complete | 1208363553 | 71 | 1208363553_71
MRPP2-DE3.24180 | TT_Task | Watertightness Type Test Procedure EMU - PTA Review ; Approval Rev.B | 12/10/2021 | 10/12/2021 | 12/10/2021 | 19/01/2022 | 0 | TK_Complete | 1208363553 | 71 | 1208363553_71
MRPP2-DE3.19170 | TT_Task | Car-Car Clearance Type Test Procedure EMU - PTA Review Rev.A | 18/06/2021 | 22/07/2021 | 18/06/2021 | 22/07/2021 | 0 | TK_Complete | 1208363553 | 72 | 1208363553_72
MRPP2-DE3.24190 | TT_Task | Car-Car Clearance Type Test Procedure EMU - Submission Rev.B | 23/07/2021 | 14/10/2021 | 23/07/2021 | 14/10/2021 | 0 | TK_Complete | 1208363553 | 73 | 1208363553_73
MRPP2-DE3.24200 | TT_Task | Car-Car Clearance Type Test Procedure EMU - PTA Review Rev.B | 15/10/2021 | 11/11/2021 | 15/10/2021 | 11/11/2021 | 0 | TK_Complete | 1208363553 | 72 | 1208363553_72
MRPP2-DE3.28290 | TT_Task | Car-Car Clearance Type Test Procedure EMU - Submission Rev.C | 12/11/2021 | 18/01/2022 | 12/11/2021 | 11/03/2022 | 0 | TK_Complete | 1208363553 | 73 | 1208363553_73
MRPP2-DE3.28300 | TT_Task | Car-Car Clearance Type Test Procedure EMU - PTA Review ; Approval Rev.C | 14/03/2022 | 12/04/2022 | 12/03/2022 | 29/03/2022 | 0 | TK_Complete | 1208363553 | 72 | 1208363553_72
MRPP2-DE3.19220 | TT_Task | Carbody Structural Type Test Procedure EMU - PTA Review Rev.A | 23/08/2021 | 24/09/2021 | 23/08/2021 | 24/09/2021 | 0 | TK_Complete | 1208363553 | 74 | 1208363553_74
MRPP2-DE3.27470 | TT_Task | Carbody Structural Type Test Procedure EMU - Submission Rev.B | 24/09/2021 | 20/12/2021 | 24/09/2021 | nan | 0 | TK_Active | 1208363553 | 74 | 1208363553_74
MRPP2-DE3.27480 | TT_Task | Carbody Structural Type Test Procedure EMU - PTA Review Rev.B | 13/04/2022 | 11/05/2022 | nan | nan | 64712 | TK_NotStart | 1208363553 | 74 | 1208363553_74
MRPP2-DE3.19320 | TT_Task | Test Specification of Damper EMU - PTA Review Rev.A | 21/05/2021 | 14/06/2021 | 21/05/2021 | 14/06/2021 | 0 | TK_Complete | 1208363553 | 75 | 1208363553_75
MRPP2-DE3.23960 | TT_Task | Test Specification of Damper EMU - Submission Rev.B | 15/06/2021 | 24/08/2021 | 15/06/2021 | 24/08/2021 | 0 | TK_Complete | 1208363553 | 75 | 1208363553_75
MRPP2-DE3.23970 | TT_Task | Test Specification of Damper EMU - PTA Review and Approval Rev.B | 25/08/2021 | 24/09/2021 | 25/08/2021 | 24/09/2021 | 0 | TK_Complete | 1208363553 | 75 | 1208363553_75
MRPP2-DE3.19380 | TT_Task | Type Test Specification - Windscreen EMU - PTA Review and Approval | 15/06/2021 | 20/07/2021 | 15/06/2021 | 20/07/2021 | 0 | TK_Complete | 1208363553 | 76 | 1208363553_76
MRPP2-DE3.24210 | TT_Task | Type Test Specification - Windscreen EMU - Submission Rev.B | 21/07/2021 | 22/11/2021 | 21/07/2021 | 22/11/2021 | 0 | TK_Complete | 1208363553 | 76 | 1208363553_76
MRPP2-DE3.24220 | TT_Task | Type Test Specification - Windscreen EMU - PTA Review Rev.B | 23/11/2021 | 20/12/2021 | 23/11/2021 | 13/12/2021 | 0 | TK_Complete | 1208363553 | 76 | 1208363553_76
MRPP2-DE3.28980 | TT_Task | Type Test Specification - Windscreen EMU - Submission Rev.C | 28/01/2022 | 10/02/2022 | 14/12/2021 | nan | 0 | TK_Active | 1208363553 | 76 | 1208363553_76
MRPP2-DE3.28990 | TT_Task | Type Test Specification - Windscreen EMU - PTA Review Rev.C | 15/04/2022 | 13/05/2022 | nan | nan | 64696 | TK_NotStart | 1208363553 | 76 | 1208363553_76
MRPP2-DE3.19390 | TT_Task | Type Test Specification - Windows EMU - PTA Review Rev.A | 26/05/2021 | 25/06/2021 | 26/05/2021 | 25/06/2021 | 0 | TK_Complete | 1208363553 | 77 | 1208363553_77
MRPP2-DE3.24010 | TT_Task | Type Test Specification - Windows EMU - Submission Rev.B | 28/06/2021 | 12/08/2021 | 26/06/2021 | 12/08/2021 | 0 | TK_Complete | 1208363553 | 77 | 1208363553_77
MRPP2-DE3.24020 | TT_Task | Type Test Specification - Windows EMU - PTA Review ; Approval Rev.B | 13/08/2021 | 09/09/2021 | 13/08/2021 | 09/09/2021 | 0 | TK_Complete | 1208363553 | 77 | 1208363553_77
MRPP2-DE3.19770 | TT_Task | Wiper Performance Type Test Procedure EMU - PTA Review Rev.A | 28/01/2022 | 24/02/2022 | 13/12/2021 | 18/01/2022 | 0 | TK_Complete | 1208363553 | 78 | 1208363553_78
MRPP2-DE3.29000 | TT_Task | Wiper Performance Type Test Procedure EMU - Submission Rev.B | 28/01/2022 | 10/02/2022 | 19/01/2022 | 08/02/2022 | 0 | TK_Complete | 1208363553 | 78 | 1208363553_78
MRPP2-DE3.29010 | TT_Task | Wiper Performance Type Test Procedure EMU - PTA Review Rev.B | 14/03/2022 | 12/04/2022 | 09/02/2022 | 01/03/2022 | 0 | TK_Complete | 1208363553 | 78 | 1208363553_78
MRPP2-DE1.10560 | TT_Task | System Description of Bogies EMU M1 | 27/01/2020 | 22/04/2020 | 27/01/2020 | 22/04/2020 | 0 | TK_Complete | 1208363553 | 79 | 1208363553_79
MRPP2-DE1.10570 | TT_Task | System Description of Bogies - PTA Design Review Rev. A EMU M1 | 23/04/2020 | 14/05/2020 | 23/04/2020 | 14/05/2020 | 0 | TK_Complete | 1208363553 | 80 | 1208363553_80
MRPP2-DE1.15403 | TT_Task | System Description of Bogies - PTA Design Review Rev. B EMU M1 | 17/06/2020 | 09/07/2020 | 17/06/2020 | 09/07/2020 | 0 | TK_Complete | 1208363553 | 80 | 1208363553_80
MRPP2-DE1.15413 | TT_Task | System Description of Bogies - Resubmit Rev. B EMU M1 | 15/05/2020 | 16/06/2020 | 15/05/2020 | 16/06/2020 | 0 | TK_Complete | 1208363553 | 79 | 1208363553_79
MRPP2-DE1.15633 | TT_Task | System Description of Bogies - PTA Design Review Rev. C EMU M1 | 31/07/2020 | 04/08/2020 | 31/07/2020 | 04/08/2020 | 0 | TK_Complete | 1208363553 | 80 | 1208363553_80
MRPP2-DE1.15643 | TT_Task | System Description of Bogies - Resubmit Rev. C EMU M1 | 10/07/2020 | 30/07/2020 | 10/07/2020 | 30/07/2020 | 0 | TK_Complete | 1208363553 | 79 | 1208363553_79
MRPP2-DE2.12463 | TT_Task | Technical specification of Secondary suspension EMU M2 | 08/07/2020 | 09/09/2020 | 08/07/2020 | 09/09/2020 | 0 | TK_Complete | 1208363553 | 81 | 1208363553_81
MRPP2-DE2.12483 | TT_Task | Technical specification of Secondary suspension - PTA Design Review EMU M2 | 10/09/2020 | 05/10/2020 | 10/09/2020 | 05/10/2020 | 0 | TK_Complete | 1208363553 | 81 | 1208363553_81
MRPP2-DE2.18333 | TT_Task | Technical specification of Secondary suspension - Submit Rev.B EMU M2 | 06/10/2020 | 10/12/2020 | 06/10/2020 | 10/12/2020 | 0 | TK_Complete | 1208363553 | 81 | 1208363553_81
MRPP2-DE2.18343 | TT_Task | Technical specification of Secondary suspension - PTA Design Review Rev.B EMU M2 | 11/12/2020 | 27/01/2021 | 11/12/2020 | 27/01/2021 | 0 | TK_Complete | 1208363553 | 81 | 1208363553_81
MRPP2-DE2.12183 | TT_Task | Technical Description for Wheel Slip Detection and Correction System EMU M2 | 08/07/2020 | 21/09/2020 | 08/07/2020 | 21/09/2020 | 0 | TK_Complete | 1208363553 | 82 | 1208363553_82
MRPP2-DE2.12203 | TT_Task | Technical Description for Wheel Slip Detection and Correction System - PTA Design Review Rev.A EMU M2 | 21/09/2020 | 14/10/2020 | 21/09/2020 | 14/10/2020 | 0 | TK_Complete | 1208363553 | 82 | 1208363553_82
MRPP2-DE2.18613 | TT_Task | Technical Description for Wheel Slip Detection and Correction System - Submit Rev.B EMU M2 | 15/10/2020 | 07/12/2020 | 15/10/2020 | 07/12/2020 | 0 | TK_Complete | 1208363553 | 82 | 1208363553_82
MRPP2-DE2.18623 | TT_Task | Technical Description for Wheel Slip Detection and Correction System - PTA Design Review Rev.B EMU M2 | 08/12/2020 | 15/01/2021 | 08/12/2020 | 15/01/2021 | 0 | TK_Complete | 1208363553 | 82 | 1208363553_82
MRPP2-DE2.12423 | TT_Task | Technical Specification and drawings of Driving gear and coupling system EMU M2 | 22/07/2020 | 24/09/2020 | 22/07/2020 | 24/09/2020 | 0 | TK_Complete | 1208363553 | 83 | 1208363553_83
MRPP2-DE2.12443 | TT_Task | Technical Specification and drawings of Driving gear and coupling system - PTA Design Review EMU M2 | 25/09/2020 | 19/10/2020 | 25/09/2020 | 19/10/2020 | 0 | TK_Complete | 1208363553 | 83 | 1208363553_83
MRPP2-DE3.13740 | TT_Task | Final Analysis and simulations ? Vehicle Dynamic Analysis Report of Bogie - Vehicle Dynamic Analysis of Bogie EMU M3 | 14/01/2021 | 01/04/2021 | 14/01/2021 | 03/04/2021 | 0 | TK_Complete | 1208363553 | 84 | 1208363553_84
MRPP2-DE3.13760 | TT_Task | Final Analysis and simulations - Vehicle Dynamic Analysis of Bogie - PTA Design Review Rev.A EMU M3 | 06/04/2021 | 05/05/2021 | 06/04/2021 | 05/05/2021 | 0 | TK_Complete | 1208363553 | 84 | 1208363553_84
MRPP2-DE3.23370 | TT_Task | Final Analysis and simulations - Vehicle Dynamic Analysis of Bogie - Submit Rev.B EMU M3 | 06/05/2021 | 09/09/2021 | 06/05/2021 | 09/09/2021 | 0 | TK_Complete | 1208363553 | 84 | 1208363553_84
MRPP2-DE3.23380 | TT_Task | Final Analysis and simulations - Vehicle Dynamic Analysis of Bogie - PTA Design Review Rev.B EMU M3 | 10/09/2021 | 14/10/2021 | 10/09/2021 | 14/10/2021 | 0 | TK_Complete | 1208363553 | 84 | 1208363553_84
MRPP2-DE3.28310 | TT_Task | Final Analysis and simulations - Vehicle Dynamic Analysis of Bogie - Submit Rev.C EMU M3 | 15/10/2021 | 17/12/2021 | 15/10/2021 | 20/01/2022 | 0 | TK_Complete | 1208363553 | 84 | 1208363553_84
MRPP2-DE3.28320 | TT_Task | Final Analysis and simulations - Vehicle Dynamic Analysis of Bogie - PTA Design Review Rev.C EMU M3 | 11/02/2022 | 10/03/2022 | 21/01/2022 | 09/02/2022 | 0 | TK_Complete | 1208363553 | 84 | 1208363553_84
MRPP2-DE3.12300 | TT_Task | FEA Report of Bogie Frame EMU M3 | 14/01/2021 | 16/02/2021 | 14/01/2021 | 16/02/2021 | 0 | TK_Complete | 1208363553 | 85 | 1208363553_85
MRPP2-DE3.12320 | TT_Task | FEA Report of Bogie Frame - PTA Design Review Rev.A EMU M3 | 17/02/2021 | 16/03/2021 | 17/02/2021 | 16/03/2021 | 0 | TK_Complete | 1208363553 | 85 | 1208363553_85
MRPP2-DE3.22830 | TT_Task | FEA Report of Bogie Frame - Submit Rev.B EMU M3 | 17/03/2021 | 09/06/2021 | 17/03/2021 | 09/06/2021 | 0 | TK_Complete | 1208363553 | 85 | 1208363553_85
MRPP2-DE3.22840 | TT_Task | FEA Report of Bogie Frame - PTA Design Review Rev.B EMU M3 | 10/06/2021 | 13/07/2021 | 10/06/2021 | 13/07/2021 | 0 | TK_Complete | 1208363553 | 85 | 1208363553_85
MRPP2-DE3.13850 | TT_Task | Detail Description of Bogie Brake Equipment EMU M3 | 21/01/2021 | 17/03/2021 | 21/01/2021 | 17/03/2021 | 0 | TK_Complete | 1208363553 | 86 | 1208363553_86
MRPP2-DE3.14010 | TT_Task | Detail Description of Bogie Brake Equipment - PTA Design Review Rev.A EMU M3 | 18/03/2021 | 19/04/2021 | 18/03/2021 | 19/04/2021 | 0 | TK_Complete | 1208363553 | 86 | 1208363553_86
MRPP2-DE3.23010 | TT_Task | Detail Description of Bogie Brake Equipment - Submit Rev.B EMU M3 | 20/04/2021 | 02/07/2021 | 20/04/2021 | 02/07/2021 | 0 | TK_Complete | 1208363553 | 86 | 1208363553_86
MRPP2-DE3.23020 | TT_Task | Detail Description of Bogie Brake Equipment - PTA Design Review Rev.B EMU M3 | 05/07/2021 | 03/08/2021 | 03/07/2021 | 03/08/2021 | 0 | TK_Complete | 1208363553 | 86 | 1208363553_86
MRPP2-DE3.27030 | TT_Task | Detail Description of Bogie Brake Equipment - Submit Rev.C EMU M3 | 04/08/2021 | 09/09/2021 | 04/08/2021 | 09/09/2021 | 0 | TK_Complete | 1208363553 | 86 | 1208363553_86
MRPP2-DE3.27040 | TT_Task | Detail Description of Bogie Brake Equipment - PTA Design Review Rev.C EMU M3 | 10/09/2021 | 13/10/2021 | 10/09/2021 | 13/10/2021 | 0 | TK_Complete | 1208363553 | 86 | 1208363553_86
MRPP2-DE3.14300 | TT_Task | Thermal Calculations of Wheel EMU M3 | 27/01/2021 | 25/02/2021 | 27/01/2021 | 25/02/2021 | 0 | TK_Complete | 1208363553 | 87 | 1208363553_87
MRPP2-DE3.14320 | TT_Task | Thermal Calculations of Wheel - PTA Design Review EMU M3 | 26/02/2021 | 25/03/2021 | 26/02/2021 | 25/03/2021 | 0 | TK_Complete | 1208363553 | 87 | 1208363553_87
MRPP2-DE3.13860 | TT_Task | Wheel Stress Calculations Report EMU M3 | 27/01/2021 | 10/03/2021 | 27/01/2021 | 10/03/2021 | 0 | TK_Complete | 1208363553 | 88 | 1208363553_88
MRPP2-DE3.13910 | TT_Task | Wheel Stress Calculations Report - PTA Design Review Rev.A EMU M3 | 11/03/2021 | 30/03/2021 | 11/03/2021 | 30/03/2021 | 0 | TK_Complete | 1208363553 | 88 | 1208363553_88
MRPP2-DE3.22990 | TT_Task | Wheel Stress Calculations Report - Submit Rev.B EMU M3 | 31/03/2021 | 28/04/2021 | 31/03/2021 | 28/04/2021 | 0 | TK_Complete | 1208363553 | 88 | 1208363553_88
MRPP2-DE3.23000 | TT_Task | Wheel Stress Calculations Report - PTA Design Review Rev.B EMU M3 | 29/04/2021 | 26/05/2021 | 29/04/2021 | 26/05/2021 | 0 | TK_Complete | 1208363553 | 88 | 1208363553_88
MRPP2-DE3.23540 | TT_Task | Wheel Stress Calculations Report - Submit Rev.C EMU M3 | 27/05/2021 | 27/07/2021 | 27/05/2021 | 27/07/2021 | 0 | TK_Complete | 1208363553 | 88 | 1208363553_88
MRPP2-DE3.23550 | TT_Task | Wheel Stress Calculations Report - PTA Design Review Rev.C EMU M3 | 28/07/2021 | 13/08/2021 | 28/07/2021 | 13/08/2021 | 0 | TK_Complete | 1208363553 | 88 | 1208363553_88
MRPP2-DE3.14380 | TT_Task | L10 Calculation Report for Axle Box Bearing EMU M3 | 29/01/2021 | 18/03/2021 | 29/01/2021 | 18/03/2021 | 0 | TK_Complete | 1208363553 | 89 | 1208363553_89
MRPP2-DE3.14400 | TT_Task | L10 Calculation Report for Axle Box Bearing - PTA Design Review Rev.A EMU M3 | 19/03/2021 | 19/04/2021 | 19/03/2021 | 19/04/2021 | 0 | TK_Complete | 1208363553 | 89 | 1208363553_89
MRPP2-DE3.23030 | TT_Task | L10 Calculation Report for Axle Box Bearing - Submit Rev.B EMU M3 | 20/04/2021 | 10/06/2021 | 20/04/2021 | 10/06/2021 | 0 | TK_Complete | 1208363553 | 89 | 1208363553_89
MRPP2-DE3.23040 | TT_Task | L10 Calculation Report for Axle Box Bearing - PTA Design Review Rev.B EMU M3 | 11/06/2021 | 08/07/2021 | 11/06/2021 | 08/07/2021 | 0 | TK_Complete | 1208363553 | 89 | 1208363553_89
MRPP2-DE3.13840 | TT_Task | Axle Strength Calculations Report EMU M3 | 29/01/2021 | 26/03/2021 | 29/01/2021 | 26/03/2021 | 0 | TK_Complete | 1208363553 | 90 | 1208363553_90
MRPP2-DE3.13980 | TT_Task | Axle Strength Calculations Report - PTA Design Review Rev.A EMU M3 | 29/03/2021 | 28/04/2021 | 29/03/2021 | 28/04/2021 | 0 | TK_Complete | 1208363553 | 90 | 1208363553_90
MRPP2-DE3.23290 | TT_Task | Axle Strength Calculations Report - Submit Rev.B EMU M3 | 29/04/2021 | 21/07/2021 | 29/04/2021 | 21/07/2021 | 0 | TK_Complete | 1208363553 | 90 | 1208363553_90
MRPP2-DE3.23300 | TT_Task | Axle Strength Calculations Report - PTA Design Review Rev.B EMU M3 | 22/07/2021 | 30/08/2021 | 22/07/2021 | 30/08/2021 | 0 | TK_Complete | 1208363553 | 90 | 1208363553_90
MRPP2-DE3.27250 | TT_Task | Axle Strength Calculations Report - Submit Rev.C EMU M3 | 31/08/2021 | 17/09/2021 | 31/08/2021 | 17/09/2021 | 0 | TK_Complete | 1208363553 | 90 | 1208363553_90
MRPP2-DE3.27260 | TT_Task | Axle Strength Calculations Report - PTA Design Review Rev.C EMU M3 | 20/09/2021 | 19/10/2021 | 20/09/2021 | 19/10/2021 | 0 | TK_Complete | 1208363553 | 90 | 1208363553_90
MRPP2-DE3.14340 | TT_Task | FEA Report of Axle Box EMU M3 | 29/01/2021 | 30/03/2021 | 29/01/2021 | 30/03/2021 | 0 | TK_Complete | 1208363553 | 91 | 1208363553_91
MRPP2-DE3.14350 | TT_Task | FEA Report of Axle Box - PTA Design Review Rev.A EMU M3 | 31/03/2021 | 29/04/2021 | 31/03/2021 | 29/04/2021 | 0 | TK_Complete | 1208363553 | 91 | 1208363553_91
MRPP2-DE3.23330 | TT_Task | FEA Report of Axle Box - Submit Rev.B EMU M3 | 30/04/2021 | 05/07/2021 | 30/04/2021 | 05/07/2021 | 0 | TK_Complete | 1208363553 | 91 | 1208363553_91
MRPP2-DE3.23340 | TT_Task | FEA Report of Axle Box - PTA Design Review Rev.B EMU M3 | 06/07/2021 | 05/08/2021 | 06/07/2021 | 05/08/2021 | 0 | TK_Complete | 1208363553 | 91 | 1208363553_91
MRPP2-DE3.14220 | TT_Task | Gear Pinions, Analysis of Stresses, Selection of Bearing, Gear Case and Transmission Assembly Report EMU M3 | 29/01/2021 | 01/03/2021 | 29/01/2021 | 01/03/2021 | 0 | TK_Complete | 1208363553 | 92 | 1208363553_92
MRPP2-DE3.14240 | TT_Task | Gear pinions, analysis of stresses, selection of bearing, gear case and transmissioin assy - PTA Design Review EMU Stage | 02/03/2021 | 29/03/2021 | 02/03/2021 | 29/03/2021 | 0 | TK_Complete | 1208363553 | 92 | 1208363553_92
MRPP2-DE3.19040 | TT_Task | Technical Drawings of Wheel Flange Lubricator EMU - PTA Review and Approval | 04/08/2020 | 01/09/2020 | 04/08/2020 | 01/09/2020 | 0 | TK_Complete | 1208363553 | 93 | 1208363553_93
MRPP2-DE3.19160 | TT_Task | Car-Bogie Clearance Type Test Procedure EMU - PTA Review Rev.A | 26/10/2021 | 24/11/2021 | 26/10/2021 | 24/11/2021 | 0 | TK_Complete | 1208363553 | 72 | 1208363553_72
MRPP2-DE3.28330 | TT_Task | Car-Bogie Clearance Type Test Procedure EMU - Submission Rev.B | 25/11/2021 | 20/12/2021 | 25/11/2021 | 28/02/2022 | 0 | TK_Complete | 1208363553 | 73 | 1208363553_73
MRPP2-DE3.28340 | TT_Task | Car-Bogie Clearance Type Test Procedure EMU - PTA Review Rev.B | 11/03/2022 | 07/04/2022 | 01/03/2022 | 17/03/2022 | 0 | TK_Complete | 1208363553 | 72 | 1208363553_72
MRPP2-DE3.19190 | TT_Task | Bogie Rotational Resistance Type Test Procedure EMU - PTA Review Rev.A | 28/01/2022 | 24/02/2022 | 08/12/2021 | 14/01/2022 | 0 | TK_Complete | 1208363553 | 94 | 1208363553_94
MRPP2-DE3.29020 | TT_Task | Bogie Rotational Resistance Type Test Procedure EMU - Submission Rev.B | 28/01/2022 | 24/02/2022 | 17/01/2022 | 10/02/2022 | 0 | TK_Complete | 1208363553 | 94 | 1208363553_94
MRPP2-DE3.29030 | TT_Task | Bogie Rotational Resistance Type Test Procedure EMU - PTA Review Rev.B | 25/03/2022 | 26/04/2022 | 11/02/2022 | 18/02/2022 | 0 | TK_Complete | 1208363553 | 94 | 1208363553_94
MRPP2-DE3.19200 | TT_Task | Wheel Unloading Type Test Procedure EMU - PTA Review Rev.A | 10/03/2022 | 06/04/2022 | 28/01/2022 | 22/02/2022 | 0 | TK_Complete | 1208363553 | 95 | 1208363553_95
MRPP2-DE3.29520 | TT_Task | Wheel Unloading Type Test Procedure EMU - Submission Rev.B | 10/03/2022 | 23/03/2022 | 23/02/2022 | nan | 0 | TK_Active | 1208363553 | 95 | 1208363553_95
MRPP2-DE3.29530 | TT_Task | Wheel Unloading Type Test Procedure EMU - PTA Review Rev.B | 13/04/2022 | 11/05/2022 | nan | nan | 64712 | TK_NotStart | 1208363553 | 95 | 1208363553_95
MRPP2-DE3.19300 | TT_Task | Test Specification of Bogie Frame static load / Fatigue load EMU - PTA Review and Approval | 29/04/2022 | 26/05/2022 | nan | nan | 64624 | TK_NotStart | 1208363553 | 96 | 1208363553_96
MRPP2-DE3.19310 | TT_Task | Test Specification of Primary suspension EMU - PTA Review Rev.A | 03/05/2021 | 26/05/2021 | 03/05/2021 | 26/05/2021 | 0 | TK_Complete | 1208363553 | 97 | 1208363553_97
MRPP2-DE3.23500 | TT_Task | Test Specification of Primary suspension EMU - Submission Rev.B | 27/05/2021 | 13/07/2021 | 27/05/2021 | 13/07/2021 | 0 | TK_Complete | 1208363553 | 97 | 1208363553_97
MRPP2-DE3.23510 | TT_Task | Test Specification of Primary suspension EMU - PTA Review Rev.B | 14/07/2021 | 13/08/2021 | 14/07/2021 | 13/08/2021 | 0 | TK_Complete | 1208363553 | 97 | 1208363553_97
MRPP2-DE3.27270 | TT_Task | Test Specification of Primary suspension EMU - Submission Rev.C | 16/08/2021 | 06/10/2021 | 14/08/2021 | 06/10/2021 | 0 | TK_Complete | 1208363553 | 97 | 1208363553_97
MRPP2-DE3.27280 | TT_Task | Test Specification of Primary suspension EMU - PTA Review Rev.C | 07/10/2021 | 28/10/2021 | 07/10/2021 | 28/10/2021 | 0 | TK_Complete | 1208363553 | 97 | 1208363553_97
MRPP2-DE3.19330 | TT_Task | Test Specification of Wheel EMU - PTA Review Rev.A | 10/05/2021 | 03/06/2021 | 10/05/2021 | 03/06/2021 | 0 | TK_Complete | 1208363553 | 98 | 1208363553_98
MRPP2-DE3.23620 | TT_Task | Test Specification of Wheel EMU - Submission Rev. B | 04/06/2021 | 16/07/2021 | 04/06/2021 | 16/07/2021 | 0 | TK_Complete | 1208363553 | 99 | 1208363553_99
MRPP2-DE3.23630 | TT_Task | Test Specification of Wheel EMU - PTA Review and Approval Rev.B | 19/07/2021 | 19/08/2021 | 17/07/2021 | 19/08/2021 | 0 | TK_Complete | 1208363553 | 98 | 1208363553_98
MRPP2-DE3.19340 | TT_Task | Test specification of Axle EMU - PTA Review Rev.A | 10/05/2021 | 03/06/2021 | 10/05/2021 | 03/06/2021 | 0 | TK_Complete | 1208363553 | 98 | 1208363553_98
MRPP2-DE3.23640 | TT_Task | Test specification of Axle EMU - Submission Rev. B | 04/06/2021 | 07/07/2021 | 04/06/2021 | 07/07/2021 | 0 | TK_Complete | 1208363553 | 99 | 1208363553_99
MRPP2-DE3.23650 | TT_Task | Test specification of Axle EMU - PTA Review and Approval Rev.B | 08/07/2021 | 06/08/2021 | 08/07/2021 | 06/08/2021 | 0 | TK_Complete | 1208363553 | 98 | 1208363553_98
MRPP2-DE3.19350 | TT_Task | Test Specification of Driving gear system - EMU EMU - PTA Review and Approval | 12/04/2021 | 10/05/2021 | 12/04/2021 | 10/05/2021 | 0 | TK_Complete | 1208363553 | 100 | 1208363553_100
MRPP2-DE3.19360 | TT_Task | Test Specification of Gearbox - EMU EMU - PTA Review Rev.A | 25/05/2021 | 23/06/2021 | 25/05/2021 | 23/06/2021 | 0 | TK_Complete | 1208363553 | 100 | 1208363553_100
MRPP2-DE3.24030 | TT_Task | Test Specification of Gearbox - EMU EMU - Submission Rev.B | 24/06/2021 | 07/09/2021 | 24/06/2021 | 07/09/2021 | 0 | TK_Complete | 1208363553 | 100 | 1208363553_100
MRPP2-DE3.24040 | TT_Task | Test Specification of Gearbox - EMU EMU - PTA Review Rev.B | 08/09/2021 | 12/10/2021 | 08/09/2021 | 12/10/2021 | 0 | TK_Complete | 1208363553 | 100 | 1208363553_100
MRPP2-DE3.28350 | TT_Task | Test Specification of Gearbox - EMU EMU - Submission Rev.C | 13/10/2021 | 07/03/2022 | 13/10/2021 | 23/12/2021 | 0 | TK_Complete | 1208363553 | 100 | 1208363553_100
MRPP2-DE3.28360 | TT_Task | Test Specification of Gearbox - EMU EMU - PTA Review Rev.C | 08/03/2022 | 04/04/2022 | 24/12/2021 | 27/01/2022 | 0 | TK_Complete | 1208363553 | 100 | 1208363553_100
MRPP2-DE3.29260 | TT_Task | Test Specification of Gearbox - EMU EMU - Submission Rev.D | 13/10/2021 | 26/10/2021 | 28/01/2022 | nan | 0 | TK_Active | 1208363553 | 100 | 1208363553_100
MRPP2-DE3.29270 | TT_Task | Test Specification of Gearbox - EMU EMU - PTA Review Rev.D | 28/04/2022 | 25/05/2022 | nan | nan | 64632 | TK_NotStart | 1208363553 | 100 | 1208363553_100
MRPP2-DE3.19440 | TT_Task | Test specification of Wheel Flange Lubricator EMU - PTA Review and Approval (Doc Propose to Delete) | 23/05/2022 | 20/06/2022 | nan | nan | 64496 | TK_NotStart | 1208363553 | 93 | 1208363553_93
MRPP2-DE3.19550 | TT_Task | Inspection instruction of complete Bogie EMU - PTA Review Rev.A | 14/06/2021 | 13/07/2021 | 14/06/2021 | 13/07/2021 | 0 | TK_Complete | 1208363553 | 101 | 1208363553_101
MRPP2-DE3.24230 | TT_Task | Inspection instruction of complete Bogie EMU - Submission Rev.B | 14/07/2021 | 18/11/2021 | 14/07/2021 | 18/11/2021 | 0 | TK_Complete | 1208363553 | 101 | 1208363553_101
MRPP2-DE3.24240 | TT_Task | Inspection instruction of complete Bogie EMU - PTA Review ; Approval Rev.B | 19/11/2021 | 16/12/2021 | 19/11/2021 | 13/12/2021 | 0 | TK_Complete | 1208363553 | 101 | 1208363553_101
MRPP2-DE3.19680 | TT_Task | Software document for propulsion system EMU - PTA Review and Approval Rev.A | 30/06/2021 | 03/08/2021 | 30/06/2021 | 03/08/2021 | 0 | TK_Complete | 1208363553 | 102 | 1208363553_102
MRPP2-DE3.27070 | TT_Task | Software document for propulsion system EMU - Submission Rev.B | 04/08/2021 | 11/11/2021 | 04/08/2021 | 11/11/2021 | 0 | TK_Complete | 1208363553 | 103 | 1208363553_103
MRPP2-DE3.27080 | TT_Task | Software document for propulsion system EMU - PTA Review and Approval Rev.B | 12/11/2021 | 10/12/2021 | 12/11/2021 | 11/01/2022 | 0 | TK_Complete | 1208363553 | 102 | 1208363553_102
MRPP2-DE3.29040 | TT_Task | Software document for propulsion system EMU - Submission Rev.C | 28/01/2022 | 10/02/2022 | 12/01/2022 | nan | 0 | TK_Active | 1208363553 | 103 | 1208363553_103
MRPP2-DE3.29050 | TT_Task | Software document for propulsion system EMU - PTA Review and Approval Rev.C | 16/05/2022 | 13/06/2022 | nan | nan | 64536 | TK_NotStart | 1208363553 | 102 | 1208363553_102
MRPP2-DE1.10853 | TT_Task | System Description of Brakes EMU M1 | 27/01/2020 | 30/04/2020 | 27/01/2020 | 30/04/2020 | 0 | TK_Complete | 1208363553 | 104 | 1208363553_104
MRPP2-DE1.10863 | TT_Task | System Description of Brakes - PTA Design Review and Comments EMU M1 | 04/05/2020 | 27/05/2020 | 04/05/2020 | 27/05/2020 | 0 | TK_Complete | 1208363553 | 105 | 1208363553_105
MRPP2-DE1.15513 | TT_Task | System Description of Brakes - Resubmit Rev.B EMU M1 | 28/05/2020 | 05/08/2020 | 28/05/2020 | 05/08/2020 | 0 | TK_Complete | 1208363553 | 104 | 1208363553_104
MRPP2-DE1.15523 | TT_Task | System Description of Brakes - PTA Design Review and Comments Rev.B EMU M1 | 06/08/2020 | 27/08/2020 | 06/08/2020 | 27/08/2020 | 0 | TK_Complete | 1208363553 | 105 | 1208363553_105
MRPP2-DE2.12943 | TT_Task | Detailed Technical Description of Brake System (Including Brake Control Equipment) EMU M2 | 08/07/2020 | 07/10/2020 | 08/07/2020 | 07/10/2020 | 0 | TK_Complete | 1208363553 | 104 | 1208363553_104
MRPP2-DE2.12963 | TT_Task | Detailed Technical Description of Brake System (Including Brake Control Equipment) - PTA Design Review Rev.A EMU M2 | 08/10/2020 | 03/11/2020 | 08/10/2020 | 03/11/2020 | 0 | TK_Complete | 1208363553 | 105 | 1208363553_105
MRPP2-DE2.18633 | TT_Task | Detailed Technical Description of Brake System (Including Brake Control Equipment) - Submit Rev.B EMU M2 | 04/11/2020 | 17/12/2020 | 04/11/2020 | 17/12/2020 | 0 | TK_Complete | 1208363553 | 104 | 1208363553_104
MRPP2-DE2.18643 | TT_Task | Detailed Technical Description of Brake System (Including Brake Control Equipment) - PTA Design Review Rev.B EMU M2 | 18/12/2020 | 04/02/2021 | 18/12/2020 | 04/02/2021 | 0 | TK_Complete | 1208363553 | 105 | 1208363553_105
MRPP2-DE2.18883 | TT_Task | Detailed Technical Description of Brake System (Including Brake Control Equipment) - Submit Rev.C EMU M2 | 05/02/2020 | 08/03/2021 | 05/02/2020 | 08/03/2021 | 0 | TK_Complete | 1208363553 | 104 | 1208363553_104
MRPP2-DE2.18893 | TT_Task | Detailed Technical Description of Brake System (Including Brake Control Equipment) - PTA Design Review Rev.C EMU M2 | 09/03/2021 | 30/03/2021 | 09/03/2021 | 30/03/2021 | 0 | TK_Complete | 1208363553 | 105 | 1208363553_105
MRPP2-DE2.10853 | TT_Task | Detailed Technical Description of Air Distribution and Supply System EMU M2 | 08/07/2020 | 08/10/2020 | 08/07/2020 | 08/10/2020 | 0 | TK_Complete | 1208363553 | 106 | 1208363553_106
MRPP2-DE2.10863 | TT_Task | Detailed Technical Description of Air Distribution and Supply System - PTA Design Review Rev.A EMU M2 | 09/10/2020 | 04/11/2020 | 09/10/2020 | 04/11/2020 | 0 | TK_Complete | 1208363553 | 107 | 1208363553_107
MRPP2-DE2.18653 | TT_Task | Detailed Technical Description of Air Distribution and Supply System - Submit Rev.B EMU M2 | 05/11/2020 | 21/12/2020 | 05/11/2020 | 21/12/2020 | 0 | TK_Complete | 1208363553 | 106 | 1208363553_106
MRPP2-DE2.18663 | TT_Task | Detailed Technical Description of Air Distribution and Supply System - PTA Design Review Rev.B EMU M2 | 22/12/2020 | 05/02/2021 | 22/12/2020 | 05/02/2021 | 0 | TK_Complete | 1208363553 | 107 | 1208363553_107
MRPP2-DE3.10780 | TT_Task | Detail Design Specification ? Pneumatic Piping including Schematic Diagrams EMU M3 | 02/10/2020 | 01/02/2021 | 02/10/2020 | 01/02/2021 | 0 | TK_Complete | 1208363553 | 108 | 1208363553_108
MRPP2-DE3.10883 | TT_Task | Detail Design Specification ? Pneumatic Piping including Schematic Diagrams - PTA Design Review Rev.A EMU M3 | 02/02/2021 | 02/03/2021 | 02/02/2021 | 02/03/2021 | 0 | TK_Complete | 1208363553 | 108 | 1208363553_108
MRPP2-DE3.22690 | TT_Task | Detail Design Specification ? Pneumatic Piping including Schematic Diagrams - Submit Rev.B EMU M3 | 03/03/2021 | 20/04/2021 | 03/03/2021 | 20/04/2021 | 0 | TK_Complete | 1208363553 | 108 | 1208363553_108
MRPP2-DE3.22700 | TT_Task | Detail Design Specification ? Pneumatic Piping including Schematic Diagrams - PTA Design Review Rev.B EMU M3 | 21/04/2021 | 18/05/2021 | 21/04/2021 | 18/05/2021 | 0 | TK_Complete | 1208363553 | 108 | 1208363553_108
MRPP2-DE3.13660 | TT_Task | Brake Performance Calculations EMU M3 | 30/12/2020 | 26/03/2021 | 30/12/2020 | 26/03/2021 | 0 | TK_Complete | 1208363553 | 109 | 1208363553_109
MRPP2-DE3.13680 | TT_Task | Brake Performance Calculations - PTA Design Review Rev.A EMU M3 | 29/03/2021 | 28/04/2021 | 29/03/2021 | 28/04/2021 | 0 | TK_Complete | 1208363553 | 110 | 1208363553_110
MRPP2-DE3.23310 | TT_Task | Brake Performance Calculations - Submit Rev.B EMU M3 | 29/04/2021 | 22/07/2021 | 29/04/2021 | 22/07/2021 | 0 | TK_Complete | 1208363553 | 109 | 1208363553_109
MRPP2-DE3.23320 | TT_Task | Brake Performance Calculations - PTA Design Review Rev.B EMU M3 | 23/07/2021 | 30/08/2021 | 23/07/2021 | 30/08/2021 | 0 | TK_Complete | 1208363553 | 110 | 1208363553_110
MRPP2-DE3.27290 | TT_Task | Brake Performance Calculations - Submit Rev.C EMU M3 | 31/08/2021 | 20/09/2021 | 31/08/2021 | 20/09/2021 | 0 | TK_Complete | 1208363553 | 109 | 1208363553_109
MRPP2-DE3.27300 | TT_Task | Brake Performance Calculations - PTA Design Review Rev.C EMU M3 | 21/09/2021 | 21/10/2021 | 21/09/2021 | 21/10/2021 | 0 | TK_Complete | 1208363553 | 110 | 1208363553_110
MRPP2-DE3.28370 | TT_Task | Brake Performance Calculations - Submit Rev.D EMU M3 | 22/10/2021 | 26/10/2021 | 22/10/2021 | 26/10/2021 | 0 | TK_Complete | 1208363553 | 109 | 1208363553_109
MRPP2-DE3.28380 | TT_Task | Brake Performance Calculations - PTA Design Review ; Approval Rev.D EMU M3 | 27/10/2021 | 18/11/2021 | 27/10/2021 | 18/11/2021 | 0 | TK_Complete | 1208363553 | 110 | 1208363553_110
MRPP2-DE3.19090 | TT_Task | Air Consumption calculations EMU - PTA Review and Approval | 24/08/2020 | 17/09/2020 | 24/08/2020 | 17/09/2020 | 0 | TK_Complete | 1208363553 | 111 | 1208363553_111
MRPP2-DE3.19830 | TT_Task | Air System Functional Type Test Procedure - AIR EMU - PTA Review and Approval | 03/12/2021 | 03/01/2022 | 03/12/2021 | 22/12/2021 | 0 | TK_Complete | 1208363553 | 112 | 1208363553_112
MRPP2-DE3.19840 | TT_Task | Brake Functional Type Test Procedure ? BRK EMU - PTA Review and Approval | 04/04/2022 | 04/05/2022 | 02/03/2022 | nan | 64880 | TK_Active | 1208363553 | 113 | 1208363553_113
MRPP2-DE3.19920 | TT_Task | Air System Performance Type Test Procedure EMU - PTA Review Rev.A | 27/10/2021 | 24/11/2021 | 27/10/2021 | 24/11/2021 | 0 | TK_Complete | 1208363553 | 112 | 1208363553_112
MRPP2-DE3.28390 | TT_Task | Air System Performance Type Test Procedure EMU - Submission Rev.B | 25/11/2021 | 14/12/2021 | 25/11/2021 | 07/12/2021 | 0 | TK_Complete | 1208363553 | 114 | 1208363553_114
MRPP2-DE3.28400 | TT_Task | Air System Performance Type Test Procedure EMU - PTA Review Rev.B | 08/02/2022 | 07/03/2022 | 08/12/2021 | 14/01/2022 | 0 | TK_Complete | 1208363553 | 112 | 1208363553_112
MRPP2-DE3.19950 | TT_Task | Parking Brake/ Holding Brake Type Test Procedure EMU - PTA Review Rev.A | 28/01/2022 | 24/02/2022 | 08/12/2021 | 14/01/2022 | 0 | TK_Complete | 1208363553 | 115 | 1208363553_115
MRPP2-DE3.29060 | TT_Task | Parking Brake/ Holding Brake Type Test Procedure EMU - Submission Rev.B | 28/01/2022 | 10/02/2022 | 17/01/2022 | 02/03/2022 | 0 | TK_Complete | 1208363553 | 115 | 1208363553_115
MRPP2-DE3.29070 | TT_Task | Parking Brake/ Holding Brake Type Test Procedure EMU - PTA Review Rev.B | 26/04/2022 | 23/05/2022 | 03/03/2022 | nan | 64880 | TK_Active | 1208363553 | 115 | 1208363553_115
MRPP2-DE3.19580 | TT_Task | Test Specification for Air Supply System EMU - PTA Review and Approval (Doc Propose to Delete) | 23/05/2022 | 20/06/2022 | nan | nan | 64496 | TK_NotStart | 1208363553 | 57 | 1208363553_57
MRPP2-DE3.19670 | TT_Task | Software document for Brake system EMU - PTA Review and Approval | 28/04/2022 | 25/05/2022 | nan | nan | 64632 | TK_NotStart | 1208363553 | 116 | 1208363553_116
MRPP2-DE2.12583 | TT_Task | Preliminary Design Specification ? Saloon Interior and Facilities including DDA EMU M2 | 22/07/2020 | 02/10/2020 | 22/07/2020 | 02/10/2020 | 0 | TK_Complete | 1208363553 | 117 | 1208363553_117
MRPP2-DE2.12603 | TT_Task | Preliminary Design Specification ? Saloon Interior and Facilities including DDA - PTA Design Review Rev.A EMU M2 | 05/10/2020 | 29/10/2020 | 05/10/2020 | 29/10/2020 | 0 | TK_Complete | 1208363553 | 117 | 1208363553_117
MRPP2-DE2.18573 | TT_Task | Preliminary Design Specification ? Saloon Interior and Facilities including DDA - Submit Rev.B EMU M2 | 30/10/2020 | 17/12/2020 | 30/10/2020 | 17/12/2020 | 0 | TK_Complete | 1208363553 | 117 | 1208363553_117
MRPP2-DE2.18583 | TT_Task | Preliminary Design Specification ? Saloon Interior and Facilities including DDA - PTA Design Review Rev.B EMU M2 | 18/12/2020 | 04/02/2021 | 18/12/2020 | 04/02/2021 | 0 | TK_Complete | 1208363553 | 117 | 1208363553_117
MRPP2-DE3.13500 | TT_Task | Detailed Design Specification- Partition Wall EMU M3 | 04/12/2020 | 16/02/2021 | 04/12/2020 | 16/02/2021 | 0 | TK_Complete | 1208363553 | 118 | 1208363553_118
MRPP2-DE3.13510 | TT_Task | Detailed Design Specification- Partition Wall - PTA Design Review Rev.A EMU M3 | 17/02/2021 | 16/03/2021 | 17/02/2021 | 16/03/2021 | 0 | TK_Complete | 1208363553 | 118 | 1208363553_118
MRPP2-DE3.22810 | TT_Task | Detailed Design Specification- Partition Wall - Submit Rev.B EMU M3 | 17/03/2021 | 15/09/2021 | 17/03/2021 | 15/09/2021 | 0 | TK_Complete | 1208363553 | 118 | 1208363553_118
MRPP2-DE3.22820 | TT_Task | Detailed Design Specification- Partition Wall - PTA Design Review Rev.B EMU M3 | 16/09/2021 | 28/10/2021 | 16/09/2021 | 28/10/2021 | 0 | TK_Complete | 1208363553 | 118 | 1208363553_118
MRPP2-DE3.28410 | TT_Task | Detailed Design Specification- Partition Wall - Submit Rev.C EMU M3 | 29/10/2021 | 10/12/2021 | 29/10/2021 | 14/12/2021 | 0 | TK_Complete | 1208363553 | 118 | 1208363553_118
MRPP2-DE3.28420 | TT_Task | Detailed Design Specification- Partition Wall - PTA Design Review Rev.C EMU M3 | 04/02/2022 | 03/03/2022 | 15/12/2021 | 18/02/2022 | 0 | TK_Complete | 1208363553 | 118 | 1208363553_118
MRPP2-DE3.13540 | TT_Task | Ergonomic reports for cab - Visibility study report, Driver Desk EMU M3 | 14/12/2020 | 11/02/2021 | 14/12/2020 | 11/02/2021 | 0 | TK_Complete | 1208363553 | 119 | 1208363553_119
MRPP2-DE3.13560 | TT_Task | Ergonomic reports for cab - Visibility study report, Driver Desk - PTA Design Review Rev.A EMU M3 | 12/02/2021 | 12/03/2021 | 12/02/2021 | 12/03/2021 | 0 | TK_Complete | 1208363553 | 119 | 1208363553_119
MRPP2-DE3.22750 | TT_Task | Ergonomic reports for cab - Visibility study report, Driver Desk - Submit Rev.B EMU M3 | 15/03/2021 | 14/05/2021 | 15/03/2021 | 14/05/2021 | 0 | TK_Complete | 1208363553 | 119 | 1208363553_119
MRPP2-DE3.22760 | TT_Task | Ergonomic reports for cab - Visibility study report, Driver Desk - PTA Design Review Rev.B EMU M3 | 17/05/2021 | 14/06/2021 | 17/05/2021 | 14/06/2021 | 0 | TK_Complete | 1208363553 | 119 | 1208363553_119
MRPP2-DE3.23900 | TT_Task | Ergonomic reports for cab - Visibility study report, Driver Desk - Submit Rev.C EMU M3 | 15/06/2021 | 20/09/2021 | 15/06/2021 | 20/09/2021 | 0 | TK_Complete | 1208363553 | 119 | 1208363553_119
MRPP2-DE3.23910 | TT_Task | Ergonomic reports for cab - Visibility study report, Driver Desk - PTA Design Review Rev.C EMU M3 | 21/09/2021 | 30/11/2021 | 21/09/2021 | 30/11/2021 | 0 | TK_Complete | 1208363553 | 119 | 1208363553_119
MRPP2-DE3.28830 | TT_Task | Ergonomic reports for cab - Visibility study report, Driver Desk - Submit Rev.D EMU M3 | 01/12/2021 | 05/01/2022 | 01/12/2021 | 28/01/2022 | 0 | TK_Complete | 1208363553 | 119 | 1208363553_119
MRPP2-DE3.28840 | TT_Task | Ergonomic reports for cab - Visibility study report, Driver Desk - PTA Design Review Rev.D EMU M3 | 07/03/2022 | 01/04/2022 | 31/01/2022 | 25/02/2022 | 0 | TK_Complete | 1208363553 | 119 | 1208363553_119
MRPP2-DE3.13580 | TT_Task | Ergonomic report for saloon EMU M3 | 14/12/2020 | 24/02/2021 | 14/12/2020 | 24/02/2021 | 0 | TK_Complete | 1208363553 | 120 | 1208363553_120
MRPP2-DE3.13600 | TT_Task | Ergonomic report for saloon - PTA Design Review Rev.A EMU M3 | 25/02/2021 | 24/03/2021 | 25/02/2021 | 24/03/2021 | 0 | TK_Complete | 1208363553 | 120 | 1208363553_120
MRPP2-DE3.22910 | TT_Task | Ergonomic report for saloon - Submit Rev.B EMU M3 | 25/03/2021 | 08/06/2021 | 25/03/2021 | 08/06/2021 | 0 | TK_Complete | 1208363553 | 120 | 1208363553_120
MRPP2-DE3.22920 | TT_Task | Ergonomic report for saloon - PTA Design Review Rev.B EMU M3 | 10/06/2021 | 06/07/2021 | 10/06/2021 | 06/07/2021 | 0 | TK_Complete | 1208363553 | 120 | 1208363553_120
MRPP2-DE3.24250 | TT_Task | Ergonomic report for saloon - Submit Rev.C EMU M3 | 07/07/2021 | 26/08/2021 | 07/07/2021 | 26/08/2021 | 0 | TK_Complete | 1208363553 | 120 | 1208363553_120
MRPP2-DE3.24260 | TT_Task | Ergonomic report for saloon - PTA Design Review Rev.C EMU M3 | 27/08/2021 | 01/10/2021 | 27/08/2021 | 01/10/2021 | 0 | TK_Complete | 1208363553 | 120 | 1208363553_120
MRPP2-DE3.13620 | TT_Task | Detailed Design Specification ? Saloon Interior and Facilities including DDA EMU M3 | 23/12/2020 | 25/03/2021 | 23/12/2020 | 25/03/2021 | 0 | TK_Complete | 1208363553 | 117 | 1208363553_117
MRPP2-DE3.13640 | TT_Task | Detailed Design Specification ? Saloon Interior and Facilities including DDA - PTA Design Review Rev.A EMU M3 | 26/03/2021 | 27/04/2021 | 26/03/2021 | 27/04/2021 | 0 | TK_Complete | 1208363553 | 117 | 1208363553_117
MRPP2-DE3.23270 | TT_Task | Detailed Design Specification ? Saloon Interior and Facilities including DDA - Submit Rev.B EMU M3 | 28/04/2021 | 20/08/2021 | 28/04/2021 | 20/08/2021 | 0 | TK_Complete | 1208363553 | 117 | 1208363553_117
MRPP2-DE3.23280 | TT_Task | Detailed Design Specification ? Saloon Interior and Facilities including DDA - PTA Design Review Rev.B EMU M3 | 23/08/2021 | 21/09/2021 | 23/08/2021 | 21/09/2021 | 0 | TK_Complete | 1208363553 | 117 | 1208363553_117
MRPP2-DE3.14140 | TT_Task | Final Exterior and Interior Design book - Interior sample material EMU | 09/06/2021 | 31/01/2022 | 09/06/2021 | 01/02/2022 | 0 | TK_Complete | 1208363553 | 121 | 1208363553_121
MRPP2-DE3.14160 | TT_Task | Final Exterior and Interior Design book - Interior sample material - PTA Design Review EMU | 08/03/2022 | 04/04/2022 | 02/02/2022 | nan | 0 | TK_Active | 1208363553 | 121 | 1208363553_121
MRPP2-DE3.19400 | TT_Task | Type Test Specification - Straphangers Endurance EMU - PTA Review and Approval | 12/07/2021 | 06/08/2021 | 12/07/2021 | 06/08/2021 | 0 | TK_Complete | 1208363553 | 122 | 1208363553_122
MRPP2-DE3.19490 | TT_Task | Detailed Design Specification - Signage and labelling EMU - PTA Review and Approval | 26/05/2022 | 23/06/2022 | nan | nan | 64472 | TK_NotStart | 1208363553 | 123 | 1208363553_123
MRPP2-DE3.19590 | TT_Task | Type Test Specification - Saloon Lighting and Gangway Lighting EMU - PTA Review Rev.A | 22/06/2021 | 22/07/2021 | 22/06/2021 | 22/07/2021 | 0 | TK_Complete | 1208363553 | 124 | 1208363553_124
MRPP2-DE3.24270 | TT_Task | Type Test Specification - Saloon Lighting and Gangway Lighting EMU - Submission Rev.B | 23/07/2021 | 18/11/2021 | 23/07/2021 | 18/11/2021 | 0 | TK_Complete | 1208363553 | 124 | 1208363553_124
MRPP2-DE3.24280 | TT_Task | Type Test Specification - Saloon Lighting and Gangway Lighting EMU - PTA Review ; Approval Rev.B | 19/11/2021 | 16/12/2021 | 19/11/2021 | 13/12/2021 | 0 | TK_Complete | 1208363553 | 124 | 1208363553_124
MRPP2-DE3.29080 | TT_Task | Type Test Specification - Saloon Lighting and Gangway Lighting EMU - Submission Rev.C | 28/01/2022 | 10/02/2022 | 14/12/2021 | nan | 0 | TK_Active | 1208363553 | 124 | 1208363553_124
MRPP2-DE3.29090 | TT_Task | Type Test Specification - Saloon Lighting and Gangway Lighting EMU - PTA Review ; Approval Rev.C | 15/04/2022 | 13/05/2022 | nan | nan | 64696 | TK_NotStart | 1208363553 | 124 | 1208363553_124
MRPP2-DE3.19610 | TT_Task | Type Test Specification - Interior Components EMU - PTA Review Rev.A | 04/08/2021 | 02/09/2021 | 04/08/2021 | 02/09/2021 | 0 | TK_Complete | 1208363553 | 125 | 1208363553_125
MRPP2-DE3.27430 | TT_Task | Type Test Specification - Interior Components EMU - Submission Rev.B | 03/09/2021 | 15/02/2022 | 03/09/2021 | 10/01/2022 | 0 | TK_Complete | 1208363553 | 125 | 1208363553_125
MRPP2-DE3.27440 | TT_Task | Type Test Specification - Interior Components EMU - PTA Review Rev.B | 16/02/2022 | 15/03/2022 | 11/01/2022 | 10/03/2022 | 0 | TK_Complete | 1208363553 | 125 | 1208363553_125
MRPP2-DE3.29660 | TT_Task | Type Test Specification - Interior Components EMU - Submission Rev.C | 03/09/2021 | 16/09/2021 | 11/03/2022 | nan | 0 | TK_Active | 1208363553 | 125 | 1208363553_125
MRPP2-DE3.29670 | TT_Task | Type Test Specification - Interior Components EMU - PTA Review Rev.C | 27/04/2022 | 24/05/2022 | nan | nan | 64640 | TK_NotStart | 1208363553 | 125 | 1208363553_125
MRPP2-DE3.19630 | TT_Task | Type Test Specification - Floor Fire Resistance EMU - PTA Review Rev.A | 23/06/2021 | 22/07/2021 | 23/06/2021 | 22/07/2021 | 0 | TK_Complete | 1208363553 | 126 | 1208363553_126
MRPP2-DE3.24290 | TT_Task | Type Test Specification - Floor Fire Resistance EMU - Submission Rev.B | 23/07/2021 | 26/11/2021 | 23/07/2021 | 26/11/2021 | 0 | TK_Complete | 1208363553 | 126 | 1208363553_126
MRPP2-DE3.24300 | TT_Task | Type Test Specification - Floor Fire Resistance EMU - PTA Review Rev.B | 29/11/2021 | 24/12/2021 | 29/11/2021 | 21/12/2021 | 0 | TK_Complete | 1208363553 | 126 | 1208363553_126
MRPP2-DE3.29100 | TT_Task | Type Test Specification - Floor Fire Resistance EMU - Submission Rev.C | 28/01/2022 | 10/02/2022 | 22/12/2021 | nan | 0 | TK_Active | 1208363553 | 126 | 1208363553_126
MRPP2-DE3.29110 | TT_Task | Type Test Specification - Floor Fire Resistance EMU - PTA Review Rev.B | 23/05/2022 | 20/06/2022 | nan | nan | 64496 | TK_NotStart | 1208363553 | 126 | 1208363553_126
MRPP2-DE2.12863 | TT_Task | System description of TCMS EMU M2 | 18/05/2020 | 21/07/2020 | 18/05/2020 | 21/07/2020 | 0 | TK_Complete | 1208363553 | 127 | 1208363553_127
MRPP2-DE2.12883 | TT_Task | System description of TCMS - PTA Design Review Rev.A EMU M2 | 22/07/2020 | 12/08/2020 | 22/07/2020 | 12/08/2020 | 0 | TK_Complete | 1208363553 | 128 | 1208363553_128
MRPP2-DE2.18173 | TT_Task | System description of TCMS - Resubmit Rev.B EMU M2 | 13/08/2020 | 01/10/2020 | 13/08/2020 | 01/10/2020 | 0 | TK_Complete | 1208363553 | 127 | 1208363553_127
MRPP2-DE2.18183 | TT_Task | System description of TCMS - PTA Design Review Rev.B EMU M2 | 02/10/2020 | 23/10/2020 | 02/10/2020 | 23/10/2020 | 0 | TK_Complete | 1208363553 | 128 | 1208363553_128
MRPP2-DE2.12823 | TT_Task | Technical Description and Drawings of Master Controller EMU M2 | 09/07/2020 | 11/09/2020 | 09/07/2020 | 11/09/2020 | 0 | TK_Complete | 1208363553 | 129 | 1208363553_129
MRPP2-DE2.12843 | TT_Task | Technical Description and Drawings of Master Controller - PTA Design Review EMU M2 | 14/09/2020 | 12/10/2020 | 14/09/2020 | 12/10/2020 | 0 | TK_Complete | 1208363553 | 129 | 1208363553_129
MRPP2-DE2.12663 | TT_Task | Functional Description Document of TCMS EMU M2 | 28/07/2020 | 07/10/2020 | 28/07/2020 | 07/10/2020 | 0 | TK_Complete | 1208363553 | 127 | 1208363553_127
MRPP2-DE2.12683 | TT_Task | Functional Description Document of TCMS - PTA Design Review Rev.A EMU M2 | 08/10/2020 | 03/11/2020 | 08/10/2020 | 03/11/2020 | 0 | TK_Complete | 1208363553 | 128 | 1208363553_128
MRPP2-DE2.18673 | TT_Task | Functional Description Document of TCMS - Submit Rev.B EMU M2 | 04/11/2020 | 22/01/2021 | 04/11/2020 | 22/01/2021 | 0 | TK_Complete | 1208363553 | 127 | 1208363553_127
MRPP2-DE2.18683 | TT_Task | Functional Description Document of TCMS - PTA Design Review Rev.B EMU M2 | 25/01/2021 | 19/02/2021 | 25/01/2021 | 19/02/2021 | 0 | TK_Complete | 1208363553 | 128 | 1208363553_128
MRPP2-DE2.12703 | TT_Task | Technical Description of HMI EMU M2 | 28/07/2020 | 29/09/2020 | 28/07/2020 | 29/09/2020 | 0 | TK_Complete | 1208363553 | 130 | 1208363553_130
MRPP2-DE2.12723 | TT_Task | Technical Description of HMI - PTA Design Review Rev.A EMU M2 | 30/09/2020 | 23/10/2020 | 30/09/2020 | 24/10/2020 | 0 | TK_Complete | 1208363553 | 131 | 1208363553_131
MRPP2-DE2.18513 | TT_Task | Technical Description of HMI - Submit Rev.B EMU M2 | 26/10/2020 | 06/01/2021 | 26/10/2020 | 06/01/2021 | 0 | TK_Complete | 1208363553 | 130 | 1208363553_130
MRPP2-DE2.18523 | TT_Task | Technical Description of HMI - PTA Design Review Rev.B EMU M2 | 07/01/2021 | 08/02/2021 | 07/01/2021 | 08/02/2021 | 0 | TK_Complete | 1208363553 | 131 | 1208363553_131
MRPP2-DE3.10820 | TT_Task | Technical specification of TCMS EMU M3 | 12/10/2020 | 22/03/2021 | 12/10/2020 | 22/03/2021 | 0 | TK_Complete | 1208363553 | 132 | 1208363553_132
MRPP2-DE3.10830 | TT_Task | Technical specification of TCMS - PTA Design Review Rev.A EMU M3 | 23/03/2021 | 21/04/2021 | 23/03/2021 | 21/04/2021 | 0 | TK_Complete | 1208363553 | 132 | 1208363553_132
MRPP2-DE3.23210 | TT_Task | Technical specification of TCMS - Submit Rev.B EMU M3 | 22/04/2021 | 23/07/2021 | 22/04/2021 | 23/07/2021 | 0 | TK_Complete | 1208363553 | 132 | 1208363553_132
MRPP2-DE3.23220 | TT_Task | Technical specification of TCMS - PTA Design Review Rev.B EMU M3 | 26/07/2021 | 23/08/2021 | 24/07/2021 | 23/08/2021 | 0 | TK_Complete | 1208363553 | 132 | 1208363553_132
MRPP2-DE3.19250 | TT_Task | Train Control Network (TCN) Static Functional Type Test Procedure (EMU) EMU - PTA Review Rev.A | 03/02/2022 | 02/03/2022 | 10/12/2021 | 18/01/2022 | 0 | TK_Complete | 1208363553 | 133 | 1208363553_133
MRPP2-DE3.29240 | TT_Task | Train Control Network (TCN) Static Functional Type Test Procedure (EMU) EMU - Submission Rev.B | 28/01/2022 | 10/02/2022 | 19/01/2022 | 02/03/2022 | 0 | TK_Complete | 1208363553 | 133 | 1208363553_133
MRPP2-DE3.29250 | TT_Task | Train Control Network (TCN) Static Functional Type Test Procedure (EMU) EMU - PTA Review Rev.B | 12/04/2022 | 10/05/2022 | 03/03/2022 | 29/03/2022 | 0 | TK_Complete | 1208363553 | 133 | 1208363553_133
MRPP2-DE3.19280 | TT_Task | TCMS Dynamic Type Test Procedure EMU - PTA Review and Approval | 28/04/2022 | 25/05/2022 | nan | nan | 64632 | TK_NotStart | 1208363553 | 134 | 1208363553_134
MRPP2-DE3.19420 | TT_Task | Test Specification of Master Controller EMU - PTA Review ; Approval Rev.A | 12/05/2021 | 09/06/2021 | 12/05/2021 | 09/06/2021 | 0 | TK_Complete | 1208363553 | 135 | 1208363553_135
MRPP2-DE3.22270 | TT_Task | Software document of TCMS EMU - PTA Review and Approval | 28/04/2022 | 25/05/2022 | nan | nan | 408 | TK_NotStart | 1208363553 | 136 | 1208363553_136
MRPP2-DE1.12083 | TT_Task | Preliminary Vehicle Performance EMU M1 | 13/01/2020 | 08/04/2020 | 13/01/2020 | 08/04/2020 | 0 | TK_Complete | 1208363553 | 137 | 1208363553_137
MRPP2-DE1.12103 | TT_Task | Preliminary Vehicle Performance - PTA Design Review Rev. A EMU M1 | 09/04/2020 | 05/05/2020 | 09/04/2020 | 05/05/2020 | 0 | TK_Complete | 1208363553 | 138 | 1208363553_138
MRPP2-DE1.15423 | TT_Task | Preliminary Vehicle Performance - Resubmit Rev. B EMU M1 | 06/05/2020 | 12/06/2020 | 06/05/2020 | 12/06/2020 | 0 | TK_Complete | 1208363553 | 137 | 1208363553_137
MRPP2-DE1.15433 | TT_Task | Preliminary Vehicle Performance - PTA Design Review Rev. B EMU M1 | 15/06/2020 | 01/07/2020 | 15/06/2020 | 01/07/2020 | 0 | TK_Complete | 1208363553 | 138 | 1208363553_138
MRPP2-DE1.10973 | TT_Task | System Description and Drawings of Traction Convertor EMU M1 | 13/01/2020 | 06/04/2020 | 13/01/2020 | 06/04/2020 | 0 | TK_Complete | 1208363553 | 139 | 1208363553_139
MRPP2-DE1.10983 | TT_Task | System Description and Drawings of Traction Convertor - PTA Design Review Rev.A EMU M1 | 07/04/2020 | 30/04/2020 | 07/04/2020 | 30/04/2020 | 0 | TK_Complete | 1208363553 | 140 | 1208363553_140
MRPP2-DE1.15263 | TT_Task | System Description and Drawings of Traction Convertor - Resubmit Rev.B EMU M1 | 01/05/2020 | 11/06/2020 | 01/05/2020 | 11/06/2020 | 0 | TK_Complete | 1208363553 | 139 | 1208363553_139
MRPP2-DE1.15273 | TT_Task | System Description and Drawings of Traction Convertor - PTA Design Review Rev.B EMU M1 | 12/06/2020 | 01/07/2020 | 12/06/2020 | 01/07/2020 | 0 | TK_Complete | 1208363553 | 140 | 1208363553_140
MRPP2-DE2.15106 | TT_Task | Sub-system Safety Requirement Specification EMU M2 | 31/07/2020 | 18/08/2020 | 31/07/2020 | 18/08/2020 | 0 | TK_Complete | 1208363553 | 141 | 1208363553_141
MRPP2-DE2.15126 | TT_Task | Sub-system Safety Requirement Specification - PTA Design Review Rev.A EMU M2 | 19/08/2020 | 14/09/2020 | 19/08/2020 | 14/09/2020 | 0 | TK_Complete | 1208363553 | 141 | 1208363553_141
MRPP2-DE2.18253 | TT_Task | Sub-system Safety Requirement Specification - Resubmit Rev.B EMU M2 | 15/09/2020 | 08/12/2020 | 15/09/2020 | 08/12/2020 | 0 | TK_Complete | 1208363553 | 141 | 1208363553_141
MRPP2-DE2.18263 | TT_Task | Sub-system Safety Requirement Specification - PTA Design Review Rev.B EMU M2 | 09/12/2020 | 21/01/2021 | 09/12/2020 | 21/01/2021 | 0 | TK_Complete | 1208363553 | 141 | 1208363553_141
MRPP2-DE2.18793 | TT_Task | Sub-system Safety Requirement Specification - Resubmit Rev.C EMU M2 | 22/01/2021 | 19/03/2021 | 22/01/2021 | 19/03/2021 | 0 | TK_Complete | 1208363553 | 141 | 1208363553_141
MRPP2-DE2.18803 | TT_Task | Sub-system Safety Requirement Specification - PTA Design Review Rev.C EMU M2 | 22/03/2021 | 20/04/2021 | 22/03/2021 | 20/04/2021 | 0 | TK_Complete | 1208363553 | 141 | 1208363553_141
MRPP2-DE2.12383 | TT_Task | Technical Description and Drawings of Traction Motor EMU M2 | 20/07/2020 | 30/07/2020 | 20/07/2020 | 30/07/2020 | 0 | TK_Complete | 1208363553 | 142 | 1208363553_142
MRPP2-DE2.12403 | TT_Task | Technical Description and Drawings of Traction Motor - PTA Design Review Rev.A EMU M2 | 31/07/2020 | 20/08/2020 | 31/07/2020 | 20/08/2020 | 0 | TK_Complete | 1208363553 | 140 | 1208363553_140
MRPP2-DE2.18233 | TT_Task | Technical Description and Drawings of Traction Motor - Submit Rev.B EMU M2 | 21/08/2020 | 22/09/2020 | 21/08/2020 | 22/09/2020 | 0 | TK_Complete | 1208363553 | 142 | 1208363553_142
MRPP2-DE2.18243 | TT_Task | Technical Description and Drawings of Traction Motor - PTA Design Review Rev.B EMU M2 | 23/09/2020 | 08/10/2020 | 23/09/2020 | 08/10/2020 | 0 | TK_Complete | 1208363553 | 140 | 1208363553_140
MRPP2-DE3.10903 | TT_Task | Technical Description and Drawings of Transformer EMU M3 | 02/10/2020 | 17/11/2020 | 02/10/2020 | 17/11/2020 | 0 | TK_Complete | 1208363553 | 143 | 1208363553_143
MRPP2-DE3.10913 | TT_Task | Technical Description and Drawings of Transformer - PTA Design Review EMU M3 | 18/11/2020 | 10/12/2020 | 18/11/2020 | 10/12/2020 | 0 | TK_Complete | 1208363553 | 143 | 1208363553_143
MRPP2-DE3.12140 | TT_Task | Energy Consumption Anlaysis EMU M3 | 16/10/2020 | 19/02/2021 | 16/10/2020 | 19/02/2021 | 0 | TK_Complete | 1208363553 | 144 | 1208363553_144
MRPP2-DE3.12160 | TT_Task | Energy Consumption Anlaysis - PTA Design Review Rev.A EMU M3 | 22/02/2021 | 17/03/2021 | 22/02/2021 | 17/03/2021 | 0 | TK_Complete | 1208363553 | 144 | 1208363553_144
MRPP2-DE3.22890 | TT_Task | Energy Consumption Anlaysis - Submit Rev.B EMU M3 | 18/03/2021 | 22/04/2021 | 18/03/2021 | 22/04/2021 | 0 | TK_Complete | 1208363553 | 144 | 1208363553_144
MRPP2-DE3.22900 | TT_Task | Energy Consumption Anlaysis - PTA Design Review Rev.B EMU M3 | 23/04/2021 | 19/05/2021 | 23/04/2021 | 19/05/2021 | 0 | TK_Complete | 1208363553 | 144 | 1208363553_144
MRPP2-DE3.10636 | TT_Task | Final Analysis and Simulation - Train Level Performance Report - PTA Design Review Rev.A EMU M3 | 28/01/2021 | 24/02/2021 | 28/01/2021 | 24/02/2021 | 0 | TK_Complete | 1208363553 | 145 | 1208363553_145
MRPP2-DE3.10656 | TT_Task | Final Analysis and Simulation - Train Level Performance Report EMU M3 | 16/11/2020 | 27/01/2021 | 16/11/2020 | 27/01/2021 | 0 | TK_Complete | 1208363553 | 145 | 1208363553_145
MRPP2-DE3.22590 | TT_Task | Final Analysis and Simulation - Train Level Performance Report - Submit Rev.B EMU M3 | 25/02/2021 | 07/05/2021 | 25/02/2021 | 07/05/2021 | 0 | TK_Complete | 1208363553 | 145 | 1208363553_145
MRPP2-DE3.22600 | TT_Task | Final Analysis and Simulation - Train Level Performance Report - PTA Design Review Rev.B EMU M3 | 10/05/2021 | 03/06/2021 | 10/05/2021 | 03/06/2021 | 0 | TK_Complete | 1208363553 | 145 | 1208363553_145
MRPP2-DE3.23580 | TT_Task | Final Analysis and Simulation - Train Level Performance Report - Submit Rev.C EMU M3 | 04/06/2021 | 03/09/2021 | 04/06/2021 | 03/09/2021 | 0 | TK_Complete | 1208363553 | 145 | 1208363553_145
MRPP2-DE3.23590 | TT_Task | Final Analysis and Simulation - Train Level Performance Report - PTA Design Review Rev.C EMU M3 | 06/09/2021 | 30/09/2021 | 06/09/2021 | 30/09/2021 | 0 | TK_Complete | 1208363553 | 145 | 1208363553_145
MRPP2-DE3.11030 | TT_Task | Final electrical schematic diagrams EMU M3 | 16/11/2020 | 18/06/2021 | 16/11/2020 | 18/06/2021 | 0 | TK_Complete | 1208363553 | 146 | 1208363553_146
MRPP2-DE3.11040 | TT_Task | Final electrical schematic diagrams - PTA Design Review Rev.A EMU M3 | 22/06/2021 | 28/07/2021 | 22/06/2021 | 28/07/2021 | 0 | TK_Complete | 1208363553 | 146 | 1208363553_146
MRPP2-DE3.26970 | TT_Task | Final electrical schematic diagrams - Submit Rev.B EMU M3 | 29/07/2021 | 28/09/2021 | 29/07/2021 | 28/09/2021 | 0 | TK_Complete | 1208363553 | 146 | 1208363553_146
MRPP2-DE3.26980 | TT_Task | Final electrical schematic diagrams - PTA Design Review Rev.B EMU M3 | 29/09/2021 | 10/12/2021 | 29/09/2021 | 25/02/2022 | 0 | TK_Complete | 1208363553 | 146 | 1208363553_146
MRPP2-DE3.19850 | TT_Task | Traction Functional Type Test Procedure ? TBS EMU - PTA Review Rev.A | 28/01/2022 | 24/02/2022 | 14/01/2022 | 04/02/2022 | 0 | TK_Complete | 1208363553 | 147 | 1208363553_147
MRPP2-DE3.29360 | TT_Task | Traction Functional Type Test Procedure ? TBS EMU - Submission Rev.B | 04/03/2022 | 17/03/2022 | 07/02/2022 | nan | 0 | TK_Active | 1208363553 | 147 | 1208363553_147
MRPP2-DE3.29370 | TT_Task | Traction Functional Type Test Procedure ? TBS EMU - PTA Review Rev.B | 26/04/2022 | 23/05/2022 | nan | nan | 64648 | TK_NotStart | 1208363553 | 147 | 1208363553_147
MRPP2-DE3.19480 | TT_Task | Test Specification of Traction Convertor EMU - PTA Review Rev.A | 14/05/2021 | 09/06/2021 | 14/05/2021 | 09/06/2021 | 0 | TK_Complete | 1208363553 | 140 | 1208363553_140
MRPP2-DE3.23700 | TT_Task | Test Specification of Traction Convertor EMU - Submission Rev.B | 10/06/2021 | 17/08/2021 | 10/06/2021 | 17/08/2021 | 0 | TK_Complete | 1208363553 | 99 | 1208363553_99
MRPP2-DE3.23710 | TT_Task | Test Specification of Traction Convertor EMU - PTA Review and Approval Rev.B | 18/08/2021 | 13/09/2021 | 18/08/2021 | 13/09/2021 | 0 | TK_Complete | 1208363553 | 140 | 1208363553_140
MRPP2-DE3.19500 | TT_Task | Test Specification of Traction Motor EMU - PTA Review Rev.A | 13/05/2021 | 09/06/2021 | 13/05/2021 | 09/06/2021 | 0 | TK_Complete | 1208363553 | 140 | 1208363553_140
MRPP2-DE3.23720 | TT_Task | Test Specification of Traction Motor EMU - Submission Rev. B | 10/06/2021 | 17/08/2021 | 10/06/2021 | 17/08/2021 | 0 | TK_Complete | 1208363553 | 99 | 1208363553_99
MRPP2-DE3.23730 | TT_Task | Test Specification of Traction Motor EMU - PTA Review and Approval Rev.B | 18/08/2021 | 13/09/2021 | 18/08/2021 | 13/09/2021 | 0 | TK_Complete | 1208363553 | 140 | 1208363553_140
MRPP2-DE3.19570 | TT_Task | Test Specification of Dynamometer Test EMU - PTA Review and Approval Rev.A | 01/07/2021 | 03/08/2021 | 01/07/2021 | 03/08/2021 | 0 | TK_Complete | 1208363553 | 148 | 1208363553_148
MRPP2-DE3.27090 | TT_Task | Test Specification of Dynamometer Test EMU - Submission Rev.B | 04/08/2021 | 31/01/2022 | 04/08/2021 | 25/11/2021 | 0 | TK_Complete | 1208363553 | 148 | 1208363553_148
MRPP2-DE3.27100 | TT_Task | Test Specification of Dynamometer Test EMU - PTA Review and Approval Rev.B | 24/03/2022 | 22/04/2022 | 26/11/2021 | 09/12/2021 | 0 | TK_Complete | 1208363553 | 148 | 1208363553_148
MRPP2-DE3.29120 | TT_Task | Test Specification of Dynamometer Test EMU - Submission Rev.C | 04/08/2021 | 17/08/2021 | 10/12/2021 | 24/03/2022 | 0 | TK_Complete | 1208363553 | 148 | 1208363553_148
MRPP2-DE3.29130 | TT_Task | Test Specification of Dynamometer Test EMU - PTA Review and Approval Rev.C | 12/04/2022 | 10/05/2022 | 25/03/2022 | nan | 64800 | TK_Active | 1208363553 | 148 | 1208363553_148
MRPP2-DE1.11003 | TT_Task | System Description of Gangway EMU M1 | 10/02/2020 | 06/05/2020 | 10/02/2020 | 06/05/2020 | 0 | TK_Complete | 1208363553 | 149 | 1208363553_149
MRPP2-DE1.11013 | TT_Task | System Description of Gangway - PTA Design Review EMU M1 | 07/05/2020 | 03/06/2020 | 07/05/2020 | 03/06/2020 | 0 | TK_Complete | 1208363553 | 150 | 1208363553_150
MRPP2-DE2.11033 | TT_Task | Detailed Design Specification of Gangway EMU M2 | 22/07/2020 | 11/09/2020 | 22/07/2020 | 11/09/2020 | 0 | TK_Complete | 1208363553 | 151 | 1208363553_151
MRPP2-DE2.11043 | TT_Task | Detailed Design Specification of Gangway - PTA Design Review Rev.A EMU M2 | 14/09/2020 | 12/10/2020 | 14/09/2020 | 12/10/2020 | 0 | TK_Complete | 1208363553 | 150 | 1208363553_150
MRPP2-DE2.18433 | TT_Task | Detailed Design Specification of Gangway - Submit Rev.B EMU M2 | 13/10/2020 | 14/12/2020 | 13/10/2020 | 14/12/2020 | 0 | TK_Complete | 1208363553 | 151 | 1208363553_151
MRPP2-DE2.18443 | TT_Task | Detailed Design Specification of Gangway - PTA Design Review Rev.B EMU M2 | 15/12/2020 | 01/02/2021 | 15/12/2020 | 01/02/2021 | 0 | TK_Complete | 1208363553 | 150 | 1208363553_150
MRPP2-DE2.18843 | TT_Task | Detailed Design Specification of Gangway - Submit Rev.C EMU M2 | 02/02/2021 | 04/06/2021 | 02/02/2021 | 04/06/2021 | 0 | TK_Complete | 1208363553 | 151 | 1208363553_151
MRPP2-DE2.18853 | TT_Task | Detailed Design Specification of Gangway - PTA Design Review Rev.C EMU M2 | 08/06/2021 | 29/06/2021 | 08/06/2021 | 29/06/2021 | 0 | TK_Complete | 1208363553 | 150 | 1208363553_150
MRPP2-DE3.19370 | TT_Task | Test Specification - Gangway EMU - PTA Review Rev.A | 16/06/2021 | 20/07/2021 | 16/06/2021 | 20/07/2021 | 0 | TK_Complete | 1208363553 | 152 | 1208363553_152
MRPP2-DE3.24310 | TT_Task | Test Specification - Gangway EMU - Submission Rev.B | 21/07/2021 | 14/03/2022 | 21/07/2021 | 16/12/2021 | 0 | TK_Complete | 1208363553 | 152 | 1208363553_152
MRPP2-DE3.24320 | TT_Task | Test Specification - Gangway EMU - PTA Review and Approval Rev.B | 15/03/2022 | 13/04/2022 | 17/12/2021 | 27/01/2022 | 0 | TK_Complete | 1208363553 | 152 | 1208363553_152
MRPP2-DE3.29280 | TT_Task | Test Specification - Gangway EMU - Submission Rev.C | 21/07/2021 | 03/08/2021 | 28/01/2022 | nan | 0 | TK_Active | 1208363553 | 152 | 1208363553_152
MRPP2-DE3.29290 | TT_Task | Test Specification - Gangway EMU - PTA Review and Approval Rev.C | 06/05/2022 | 02/06/2022 | nan | nan | 64584 | TK_NotStart | 1208363553 | 152 | 1208363553_152
MRPP2-DE3.19430 | TT_Task | Gangway ; Coupler Movement Analysis EMU - PTA Review Rev.A | 12/07/2021 | 12/08/2021 | 10/07/2021 | 12/08/2021 | 0 | TK_Complete | 1208363553 | 153 | 1208363553_153
MRPP2-DE3.27310 | TT_Task | Gangway ; Coupler Movement Analysis EMU - Submission Rev.B | 13/08/2021 | 20/01/2022 | 13/08/2021 | nan | 0 | TK_Active | 1208363553 | 153 | 1208363553_153
MRPP2-DE3.27320 | TT_Task | Gangway ; Coupler Movement Analysis EMU - PTA Review Rev.B | 02/05/2022 | 27/05/2022 | nan | nan | 64616 | TK_NotStart | 1208363553 | 153 | 1208363553_153
MRPP2-DE1.11033 | TT_Task | System Description of Coupling System EMU M1 | 27/01/2020 | 06/05/2020 | 27/01/2020 | 06/05/2020 | 0 | TK_Complete | 1208363553 | 154 | 1208363553_154
MRPP2-DE1.11043 | TT_Task | System Description of Coupling System - PTA Design Review Rev.A EMU M1 | 07/05/2020 | 02/06/2020 | 07/05/2020 | 02/06/2020 | 0 | TK_Complete | 1208363553 | 155 | 1208363553_155
MRPP2-DE1.15533 | TT_Task | System Description of Coupling System - Resubmit Rev.B EMU M1 | 03/06/2020 | 11/06/2020 | 03/06/2020 | 11/06/2020 | 0 | TK_Complete | 1208363553 | 154 | 1208363553_154
MRPP2-DE1.15543 | TT_Task | System Description of Coupling System - PTA Design Review Rev.B EMU M1 | 12/06/2020 | 30/06/2020 | 12/06/2020 | 30/06/2020 | 0 | TK_Complete | 1208363553 | 155 | 1208363553_155
MRPP2-DE1.15653 | TT_Task | System Description of Coupling System - Resubmit Rev.C EMU M1 | 01/07/2020 | 17/07/2020 | 01/07/2020 | 17/07/2020 | 0 | TK_Complete | 1208363553 | 154 | 1208363553_154
MRPP2-DE1.15663 | TT_Task | System Description of Coupling System - PTA Design Review Rev.C EMU M1 | 20/07/2020 | 03/08/2020 | 20/07/2020 | 03/08/2020 | 0 | TK_Complete | 1208363553 | 155 | 1208363553_155
MRPP2-DE2.11063 | TT_Task | Detailed Design Specification of Couplers EMU M2 | 22/07/2020 | 25/09/2020 | 22/07/2020 | 25/09/2020 | 0 | TK_Complete | 1208363553 | 156 | 1208363553_156
MRPP2-DE2.11073 | TT_Task | Detailed Design Specification of Couplers - PTA Design Review Rev.A EMU M2 | 29/09/2020 | 21/10/2020 | 28/09/2020 | 21/10/2020 | 0 | TK_Complete | 1208363553 | 156 | 1208363553_156
MRPP2-DE2.18493 | TT_Task | Detailed Design Specification of Couplers - Submit Rev.B EMU M2 | 22/10/2020 | 14/01/2021 | 22/10/2020 | 14/01/2021 | 0 | TK_Complete | 1208363553 | 156 | 1208363553_156
MRPP2-DE2.18503 | TT_Task | Detailed Design Specification of Couplers - PTA Design Review Rev.B EMU M2 | 15/01/2021 | 11/02/2021 | 15/01/2021 | 11/02/2021 | 0 | TK_Complete | 1208363553 | 156 | 1208363553_156
MRPP2-DE3.12220 | TT_Task | Collision and Energy Absorption Calculation Report of Coupler System EMU M3 | 08/12/2020 | 10/02/2021 | 08/12/2020 | 10/02/2021 | 0 | TK_Complete | 1208363553 | 157 | 1208363553_157
MRPP2-DE3.12240 | TT_Task | Collision and Energy Absorption Calculation Report of Coupler System - PTA Design Review Rev.A EMU M3 | 11/02/2021 | 11/03/2021 | 11/02/2021 | 11/03/2021 | 0 | TK_Complete | 1208363553 | 157 | 1208363553_157
MRPP2-DE3.22730 | TT_Task | Collision and Energy Absorption Calculation Report of Coupler System - Submit Rev.B EMU M3 | 12/03/2021 | 08/06/2021 | 12/03/2021 | 08/06/2021 | 0 | TK_Complete | 1208363553 | 157 | 1208363553_157
MRPP2-DE3.22740 | TT_Task | Collision and Energy Absorption Calculation Report of Coupler System - PTA Design Review Rev.B EMU M3 | 09/06/2021 | 06/07/2021 | 09/06/2021 | 06/07/2021 | 0 | TK_Complete | 1208363553 | 157 | 1208363553_157
MRPP2-DE3.24330 | TT_Task | Collision and Energy Absorption Calculation Report of Coupler System - Submit Rev.C EMU M3 | 07/07/2021 | 01/10/2021 | 07/07/2021 | 01/10/2021 | 0 | TK_Complete | 1208363553 | 157 | 1208363553_157
MRPP2-DE3.24340 | TT_Task | Collision and Energy Absorption Calculation Report of Coupler System - PTA Design Review Rev.C EMU M3 | 04/10/2021 | 10/12/2021 | 04/10/2021 | 07/12/2021 | 0 | TK_Complete | 1208363553 | 157 | 1208363553_157
MRPP2-DE3.19410 | TT_Task | Type Test Specification - Couplers EMU - PTA Review and Approval Rev.A | 07/07/2021 | 05/08/2021 | 07/07/2021 | 05/08/2021 | 0 | TK_Complete | 1208363553 | 158 | 1208363553_158
MRPP2-DE3.27110 | TT_Task | Type Test Specification - Couplers EMU - Submission Rev.B | 06/08/2021 | 24/11/2021 | 06/08/2021 | 24/11/2021 | 0 | TK_Complete | 1208363553 | 158 | 1208363553_158
MRPP2-DE3.27120 | TT_Task | Type Test Specification - Couplers EMU - PTA Review and Approval Rev.B | 25/11/2021 | 22/12/2021 | 25/11/2021 | 15/12/2021 | 0 | TK_Complete | 1208363553 | 158 | 1208363553_158
MRPP2-DE1.12603 | TT_Task | System Description of Cab and Saloon HVAC EMU M1 | 30/01/2020 | 28/04/2020 | 30/01/2020 | 28/04/2020 | 0 | TK_Complete | 1208363553 | 159 | 1208363553_159
MRPP2-DE1.12623 | TT_Task | System Description of Cab and Saloon HVAC - PTA Design Review Rev.A EMU M1 | 29/04/2020 | 25/05/2020 | 29/04/2020 | 25/05/2020 | 0 | TK_Complete | 1208363553 | 160 | 1208363553_160
MRPP2-DE1.15493 | TT_Task | System Description of Cab and Saloon HVAC - Resubmit Rev.B EMU M1 | 26/05/2020 | 29/06/2020 | 26/05/2020 | 29/06/2020 | 0 | TK_Complete | 1208363553 | 159 | 1208363553_159
MRPP2-DE1.15503 | TT_Task | System Description of Cab and Saloon HVAC - PTA Design Review Rev.B EMU M1 | 30/06/2020 | 23/07/2020 | 30/06/2020 | 23/07/2020 | 0 | TK_Complete | 1208363553 | 160 | 1208363553_160
MRPP2-DE2.11123 | TT_Task | Technical Description and Drawings of Cab and Saloon HVAC EMU M2 | 09/06/2020 | 08/09/2020 | 09/06/2020 | 08/09/2020 | 0 | TK_Complete | 1208363553 | 159 | 1208363553_159
MRPP2-DE2.11133 | TT_Task | Technical Description and Drawings of Cab and Saloon HVAC - PTA Design Review Rev.A EMU M2 | 09/09/2020 | 05/10/2020 | 09/09/2020 | 05/10/2020 | 0 | TK_Complete | 1208363553 | 160 | 1208363553_160
MRPP2-DE2.18353 | TT_Task | Technical Description and Drawings of Cab and Saloon HVAC - Submit Rev.B EMU M2 | 06/10/2020 | 10/12/2020 | 06/10/2020 | 10/12/2020 | 0 | TK_Complete | 1208363553 | 159 | 1208363553_159
MRPP2-DE2.18363 | TT_Task | Technical Description and Drawings of Cab and Saloon HVAC - PTA Design Review Rev.B EMU M2 | 11/12/2020 | 27/01/2021 | 11/12/2020 | 27/01/2021 | 0 | TK_Complete | 1208363553 | 160 | 1208363553_160
MRPP2-DE3.11093 | TT_Task | Climate Comfort Prediction Report EMU M3 | 11/09/2020 | 22/01/2021 | 11/09/2020 | 22/01/2021 | 0 | TK_Complete | 1208363553 | 161 | 1208363553_161
MRPP2-DE3.11103 | TT_Task | Climate Comfort Prediction Report - PTA Design Review Rev.A EMU M3 | 25/01/2021 | 19/02/2021 | 25/01/2021 | 19/02/2021 | 0 | TK_Complete | 1208363553 | 161 | 1208363553_161
MRPP2-DE3.22550 | TT_Task | Climate Comfort Prediction Report - Submit Rev.B EMU M3 | 22/02/2021 | 06/04/2021 | 22/02/2021 | 06/04/2021 | 0 | TK_Complete | 1208363553 | 161 | 1208363553_161
MRPP2-DE3.22560 | TT_Task | Climate Comfort Prediction Report - PTA Design Review Rev.B EMU M3 | 07/04/2021 | 04/05/2021 | 07/04/2021 | 04/05/2021 | 0 | TK_Complete | 1208363553 | 161 | 1208363553_161
MRPP2-DE3.14460 | TT_Task | Heat Load Calculations Report EMU M3 | 29/01/2021 | 10/03/2021 | 29/01/2021 | 10/03/2021 | 0 | TK_Complete | 1208363553 | 162 | 1208363553_162
MRPP2-DE3.14480 | TT_Task | Heat Load Calculations Report - PTA Design Review Rev.A EMU M3 | 11/03/2021 | 15/04/2021 | 11/03/2021 | 15/04/2021 | 0 | TK_Complete | 1208363553 | 162 | 1208363553_162
MRPP2-DE3.23050 | TT_Task | Heat Load Calculations Report - Submit Rev.B EMU M3 | 16/04/2021 | 01/06/2021 | 16/04/2021 | 01/06/2021 | 0 | TK_Complete | 1208363553 | 162 | 1208363553_162
MRPP2-DE3.23060 | TT_Task | Heat Load Calculations Report - PTA Design Review Rev.B EMU M3 | 02/06/2021 | 30/06/2021 | 02/06/2021 | 30/06/2021 | 0 | TK_Complete | 1208363553 | 162 | 1208363553_162
MRPP2-DE3.24150 | TT_Task | Heat Load Calculations Report - Submit Rev.C EMU M3 | 01/07/2021 | 10/08/2021 | 01/07/2021 | 10/08/2021 | 0 | TK_Complete | 1208363553 | 162 | 1208363553_162
MRPP2-DE3.24160 | TT_Task | Heat Load Calculations Report - PTA Design Review Rev.C EMU M3 | 11/08/2021 | 13/09/2021 | 11/08/2021 | 13/09/2021 | 0 | TK_Complete | 1208363553 | 162 | 1208363553_162
MRPP2-DE3.19230 | TT_Task | HVAC Performance Type Test Procedure EMU - PTA Review Rev.A | 16/06/2021 | 26/07/2021 | 16/06/2021 | 26/07/2021 | 0 | TK_Complete | 1208363553 | 163 | 1208363553_163
MRPP2-DE3.24350 | TT_Task | HVAC Performance Type Test Procedure EMU - Submission Rev.B | 27/07/2021 | 17/01/2022 | 27/07/2021 | 02/03/2022 | 0 | TK_Complete | 1208363553 | 114 | 1208363553_114
MRPP2-DE3.24360 | TT_Task | HVAC Performance Type Test Procedure EMU - PTA Review Rev.B | 04/02/2022 | 03/03/2022 | 03/03/2022 | nan | 64880 | TK_Active | 1208363553 | 163 | 1208363553_163
MRPP2-DE3.19880 | TT_Task | HVAC Functional Type Test Procedure ? CLM EMU - PTA Review and Approval | 10/03/2022 | 06/04/2022 | 25/02/2022 | nan | 64880 | TK_Active | 1208363553 | 163 | 1208363553_163
MRPP2-DE3.19560 | TT_Task | Test Specification of Saloon HVAC EMU - PTA Review and Approval (Doc Propose to Delete) | 23/06/2021 | 26/07/2021 | 23/06/2021 | 26/07/2021 | 0 | TK_Complete | 1208363553 | 164 | 1208363553_164
MRPP2-DE3.24370 | TT_Task | Test Specification of Saloon HVAC EMU - Submission Rev.B (Doc Propose to Delete) | 27/07/2021 | 29/04/2022 | 27/07/2021 | nan | 0 | TK_Active | 1208363553 | 164 | 1208363553_164
MRPP2-DE3.24380 | TT_Task | HVAC Performance Type Test Procedure EMU - PTA Review Rev.B (Doc Propose to Delete) | 02/05/2022 | 27/05/2022 | nan | nan | 64616 | TK_NotStart | 1208363553 | 163 | 1208363553_163
MRPP2-DE3.19660 | TT_Task | Software document for HVAC System EMU - PTA Review and Approval | 01/07/2021 | 03/08/2021 | 01/07/2021 | 03/08/2021 | 0 | TK_Complete | 1208363553 | 165 | 1208363553_165
MRPP2-DE1.11093 | TT_Task | System Description of Passenger Doors EMU M1 | 27/01/2020 | 28/04/2020 | 27/01/2020 | 28/04/2020 | 0 | TK_Complete | 1208363553 | 166 | 1208363553_166
MRPP2-DE1.11103 | TT_Task | System Description of Passenger Doors - PTA Design Review EMU M1 | 29/04/2020 | 15/05/2020 | 29/04/2020 | 15/05/2020 | 0 | TK_Complete | 1208363553 | 166 | 1208363553_166
MRPP2-DE2.13343 | TT_Task | Technical Description and Drawings of Passenger Doors EMU M2 | 31/07/2020 | 06/10/2020 | 31/07/2020 | 06/10/2020 | 0 | TK_Complete | 1208363553 | 166 | 1208363553_166
MRPP2-DE2.13363 | TT_Task | Technical Description and Drawings of Passenger Doors - PTA Design Review Rev.A EMU M2 | 07/10/2020 | 02/11/2020 | 07/10/2020 | 02/11/2020 | 0 | TK_Complete | 1208363553 | 166 | 1208363553_166
MRPP2-DE2.18593 | TT_Task | Technical Description and Drawings of Passenger Doors - Submit Rev.B EMU M2 | 03/11/2020 | 18/12/2020 | 03/11/2020 | 18/12/2020 | 0 | TK_Complete | 1208363553 | 166 | 1208363553_166
MRPP2-DE2.18603 | TT_Task | Technical Description and Drawings of Passenger Doors - PTA Design Review Rev.B EMU M2 | 21/12/2020 | 04/02/2021 | 21/12/2020 | 04/02/2021 | 0 | TK_Complete | 1208363553 | 166 | 1208363553_166
MRPP2-DE3.19860 | TT_Task | Doors Functional Type Test Procedure - IDR EMU - PTA Review and Approval | 28/01/2022 | 24/02/2022 | 14/01/2022 | nan | 64880 | TK_Active | 1208363553 | 167 | 1208363553_167
MRPP2-DE3.19450 | TT_Task | Test specification of Passenger saloon Door EMU - PTA Review Rev.A | 24/08/2021 | 24/09/2021 | 24/08/2021 | 24/09/2021 | 0 | TK_Complete | 1208363553 | 168 | 1208363553_168
MRPP2-DE3.27510 | TT_Task | Test specification of Passenger saloon Door EMU - Submission Rev.B | 28/09/2021 | 10/12/2021 | 27/09/2021 | 11/01/2022 | 0 | TK_Complete | 1208363553 | 168 | 1208363553_168
MRPP2-DE3.27520 | TT_Task | Test specification of Passenger saloon Door EMU - PTA Review Rev.B | 04/02/2022 | 11/03/2022 | 12/01/2022 | 10/03/2022 | 0 | TK_Complete | 1208363553 | 168 | 1208363553_168
MRPP2-DE3.29680 | TT_Task | Test specification of Passenger saloon Door EMU - Submission Rev.C | 04/04/2022 | 19/04/2022 | 11/03/2022 | nan | 0 | TK_Active | 1208363553 | 168 | 1208363553_168
MRPP2-DE3.29690 | TT_Task | Test specification of Passenger saloon Door EMU - PTA Review Rev.C | 27/04/2022 | 24/05/2022 | nan | nan | 64640 | TK_NotStart | 1208363553 | 168 | 1208363553_168
MRPP2-DE3.19650 | TT_Task | Software document for Door System EMU - PTA Review Rev.A | 25/06/2021 | 27/07/2021 | 25/06/2021 | 27/07/2021 | 0 | TK_Complete | 1208363553 | 169 | 1208363553_169
MRPP2-DE3.24450 | TT_Task | Software document for Door System EMU - Submission Rev.B | 28/07/2021 | 14/02/2022 | 28/07/2021 | 10/11/2021 | 0 | TK_Complete | 1208363553 | 169 | 1208363553_169
MRPP2-DE3.24460 | TT_Task | Software document for Door System EMU - PTA Review Rev.B | 11/03/2022 | 07/04/2022 | 11/11/2021 | 21/02/2022 | 0 | TK_Complete | 1208363553 | 169 | 1208363553_169
MRPP2-DE3.29540 | TT_Task | Software document for Door System EMU - Submission Rev.C | 28/07/2021 | 24/08/2021 | 22/02/2022 | nan | 0 | TK_Active | 1208363553 | 169 | 1208363553_169
MRPP2-DE3.29550 | TT_Task | Software document for Door System EMU - PTA Review Rev.C | 02/05/2022 | 13/05/2022 | nan | nan | 64696 | TK_NotStart | 1208363553 | 169 | 1208363553_169
MRPP2-DE3.19750 | TT_Task | Doors Performance Type Test Procedure EMU - PTA Review Rev.A | 19/10/2021 | 19/11/2021 | 19/10/2021 | 19/11/2021 | 0 | TK_Complete | 1208363553 | 170 | 1208363553_170
MRPP2-DE3.28430 | TT_Task | Doors Performance Type Test Procedure EMU - Submission Rev.B | 22/11/2021 | 21/12/2021 | 22/11/2021 | 03/03/2022 | 0 | TK_Complete | 1208363553 | 170 | 1208363553_170
MRPP2-DE3.28440 | TT_Task | Doors Performance Type Test Procedure EMU - PTA Review Rev.B | 18/04/2022 | 16/05/2022 | 04/03/2022 | 24/03/2022 | 0 | TK_Complete | 1208363553 | 170 | 1208363553_170
MRPP2-DE3.29860 | TT_Task | Doors Performance Type Test Procedure EMU - Submission Rev.C | 22/11/2021 | 03/12/2021 | 25/03/2022 | nan | 0 | TK_Active | 1208363553 | 170 | 1208363553_170
MRPP2-DE3.29870 | TT_Task | Doors Performance Type Test Procedure EMU - PTA Review Rev.C | 17/05/2022 | 14/06/2022 | nan | nan | 64528 | TK_NotStart | 1208363553 | 170 | 1208363553_170
MRPP2-DE1.11123 | TT_Task | System Description of Auxiliary Supply System EMU M1 | 13/01/2020 | 06/04/2020 | 13/01/2020 | 06/04/2020 | 0 | TK_Complete | 1208363553 | 171 | 1208363553_171
MRPP2-DE1.11133 | TT_Task | System Description of Auxiliary Supply System - PTA Design Review Rev.A EMU M1 | 07/04/2020 | 30/04/2020 | 07/04/2020 | 30/04/2020 | 0 | TK_Complete | 1208363553 | 172 | 1208363553_172
MRPP2-DE1.15283 | TT_Task | System Description of Auxiliary Supply System - Resubmit Rev.B EMU M1 | 01/05/2020 | 11/06/2020 | 01/05/2020 | 11/06/2020 | 0 | TK_Complete | 1208363553 | 171 | 1208363553_171
MRPP2-DE1.15293 | TT_Task | System Description of Auxiliary Supply System - PTA Design Review Rev.B EMU M1 | 12/06/2020 | 26/06/2020 | 12/06/2020 | 26/06/2020 | 0 | TK_Complete | 1208363553 | 172 | 1208363553_172
MRPP2-DE2.12343 | TT_Task | Technical Description and Drawings of Surge Arrestor EMU M2 | 08/07/2020 | 16/07/2020 | 08/07/2020 | 16/07/2020 | 0 | TK_Complete | 1208363553 | 173 | 1208363553_173
MRPP2-DE2.12363 | TT_Task | Technical Description and Drawings of Surge Arrestor - PTA Design Review Rev.A EMU M2 | 17/07/2020 | 31/07/2020 | 17/07/2020 | 31/07/2020 | 0 | TK_Complete | 1208363553 | 173 | 1208363553_173
MRPP2-DE2.18153 | TT_Task | Technical Description and Drawings of Surge Arrestor - Resubmit Rev.B EMU M2 | 03/08/2020 | 12/08/2020 | 03/08/2020 | 12/08/2020 | 0 | TK_Complete | 1208363553 | 173 | 1208363553_173
MRPP2-DE2.18163 | TT_Task | Technical Description and Drawings of Surge Arrestor - PTA Design Review Rev.B EMU M2 | 13/08/2020 | 20/08/2020 | 13/08/2020 | 20/08/2020 | 0 | TK_Complete | 1208363553 | 173 | 1208363553_173
MRPP2-DE2.12263 | TT_Task | Technical Description and Drawings of 25 kV Vacuum Circuit Breaker EMU M2 | 22/07/2020 | 13/08/2020 | 22/07/2020 | 13/08/2020 | 0 | TK_Complete | 1208363553 | 174 | 1208363553_174
MRPP2-DE2.12283 | TT_Task | Technical Description and Drawings of 25 kV Vacuum Circuit Breaker - PTA Design Review Rev.A EMU M2 | 14/08/2020 | 01/09/2020 | 14/08/2020 | 01/09/2020 | 0 | TK_Complete | 1208363553 | 174 | 1208363553_174
MRPP2-DE2.18273 | TT_Task | Technical Description and Drawings of 25 kV Vacuum Circuit Breaker - Resubmit Rev.B EMU M2 | 02/09/2020 | 22/09/2020 | 02/09/2020 | 22/09/2020 | 0 | TK_Complete | 1208363553 | 174 | 1208363553_174
MRPP2-DE2.18283 | TT_Task | Technical Description and Drawings of 25 kV Vacuum Circuit Breaker - PTA Design Review Rev.B EMU M2 | 23/09/2020 | 08/10/2020 | 23/09/2020 | 08/10/2020 | 0 | TK_Complete | 1208363553 | 174 | 1208363553_174
MRPP2-DE2.12303 | TT_Task | Technical Description and Drawings of Earthing Switch EMU M2 | 22/07/2020 | 13/08/2020 | 22/07/2020 | 13/08/2020 | 0 | TK_Complete | 1208363553 | 175 | 1208363553_175
MRPP2-DE2.12323 | TT_Task | Technical Description and Drawings of Earthing Switch - PTA Design Review Rev.A EMU M2 | 14/08/2020 | 01/09/2020 | 14/08/2020 | 01/09/2020 | 0 | TK_Complete | 1208363553 | 175 | 1208363553_175
MRPP2-DE2.18293 | TT_Task | Technical Description and Drawings of Earthing Switch - Resubmit Rev.B EMU M2 | 02/09/2020 | 22/09/2020 | 02/09/2020 | 22/09/2020 | 0 | TK_Complete | 1208363553 | 175 | 1208363553_175
MRPP2-DE2.18303 | TT_Task | Technical Description and Drawings of Earthing Switch - PTA Design Review Rev.B EMU M2 | 23/09/2020 | 08/10/2020 | 23/09/2020 | 08/10/2020 | 0 | TK_Complete | 1208363553 | 175 | 1208363553_175
MRPP2-DE2.12623 | TT_Task | Auxiliary Load Calculation Report for AC and DC EMU M2 | 22/07/2020 | 21/08/2020 | 22/07/2020 | 21/08/2020 | 0 | TK_Complete | 1208363553 | 176 | 1208363553_176
MRPP2-DE2.12643 | TT_Task | Auxiliary Load Calculation Report for AC and DC - PTA Design Review Rev.A EMU M2 | 24/08/2020 | 17/09/2020 | 24/08/2020 | 17/09/2020 | 0 | TK_Complete | 1208363553 | 177 | 1208363553_177
MRPP2-DE2.18313 | TT_Task | Auxiliary Load Calculation Report for AC and DC - Resubmit Rev.B EMU M2 | 18/09/2020 | 14/10/2020 | 18/09/2020 | 14/10/2020 | 0 | TK_Complete | 1208363553 | 176 | 1208363553_176
MRPP2-DE2.18323 | TT_Task | Auxiliary Load Calculation Report for AC and DC - PTA Design Review Rev.B EMU M2 | 15/10/2020 | 09/11/2020 | 15/10/2020 | 09/11/2020 | 0 | TK_Complete | 1208363553 | 177 | 1208363553_177
MRPP2-DE2.11153 | TT_Task | Technical Description and Drawings of Auxiliary Supply System EMU M2 | 31/07/2020 | 09/09/2020 | 31/07/2020 | 09/09/2020 | 0 | TK_Complete | 1208363553 | 171 | 1208363553_171
MRPP2-DE2.11163 | TT_Task | Technical Description and Drawings of Auxiliary Supply System - PTA Design Review Rev.A EMU M2 | 10/09/2020 | 06/10/2020 | 10/09/2020 | 06/10/2020 | 0 | TK_Complete | 1208363553 | 172 | 1208363553_172
MRPP2-DE2.18373 | TT_Task | Technical Description and Drawings of Auxiliary Supply System - Submit Rev.B EMU M2 | 07/10/2020 | 28/10/2020 | 07/10/2020 | 28/10/2020 | 0 | TK_Complete | 1208363553 | 171 | 1208363553_171
MRPP2-DE2.18383 | TT_Task | Technical Description and Drawings of Auxiliary Supply System - PTA Design Review Rev.B EMU M2 | 29/10/2020 | 19/11/2020 | 29/10/2020 | 19/11/2020 | 0 | TK_Complete | 1208363553 | 172 | 1208363553_172
MRPP2-DE2.18733 | TT_Task | Technical Description and Drawings of Auxiliary Supply System - Submit Rev.C EMU M2 | 20/11/2020 | 07/01/2021 | 20/11/2020 | 07/01/2021 | 0 | TK_Complete | 1208363553 | 171 | 1208363553_171
MRPP2-DE2.18743 | TT_Task | Technical Description and Drawings of Auxiliary Supply System - PTA Design Review Rev.C EMU M2 | 08/01/2021 | 08/02/2021 | 08/01/2021 | 08/02/2021 | 0 | TK_Complete | 1208363553 | 172 | 1208363553_172
MRPP2-DE3.19020 | TT_Task | Preliminary Electrical Schematic Diagrams (EMU) - General EMU - PTA Review and Comments Rev.A | 02/12/2020 | 19/01/2021 | 02/12/2020 | 19/01/2021 | 0 | TK_Complete | 1208363553 | 178 | 1208363553_178
MRPP2-DE3.23070 | TT_Task | Preliminary Electrical Schematic Diagrams (EMU) - General EMU - Submission Rev.B | 20/01/2021 | 12/04/2021 | 20/01/2021 | 12/04/2021 | 0 | TK_Complete | 1208363553 | 178 | 1208363553_178
MRPP2-DE3.23080 | TT_Task | Preliminary Electrical Schematic Diagrams (EMU) - General EMU - PTA Review and Approval Rev.B | 13/04/2021 | 11/05/2021 | 13/04/2021 | 11/05/2021 | 0 | TK_Complete | 1208363553 | 178 | 1208363553_178
MRPP2-DE3.19060 | TT_Task | Technical Description and Drawings of wires ; Cable EMU - PTA Review and Approval | 13/08/2020 | 11/09/2020 | 13/08/2020 | 11/09/2020 | 0 | TK_Complete | 1208363553 | 179 | 1208363553_179
MRPP2-DE3.19240 | TT_Task | Vehicle Earthing Type Test Procedure EMU - PTA Review Rev.A | 04/08/2021 | 08/09/2021 | 04/08/2021 | 08/09/2021 | 0 | TK_Complete | 1208363553 | 180 | 1208363553_180
MRPP2-DE3.27530 | TT_Task | Vehicle Earthing Type Test Procedure EMU - Submission Rev.A | 09/09/2021 | 03/11/2021 | 09/09/2021 | 03/11/2021 | 0 | TK_Complete | 1208363553 | 180 | 1208363553_180
MRPP2-DE3.27540 | TT_Task | Vehicle Earthing Type Test Procedure EMU - PTA Review Rev.B | 04/11/2021 | 26/11/2021 | 04/11/2021 | 26/11/2021 | 0 | TK_Complete | 1208363553 | 180 | 1208363553_180
MRPP2-DE3.19820 | TT_Task | Electrical Energy Functional Type Test Procedure EMU - PTA Review and Approval | 03/02/2022 | 02/03/2022 | 18/01/2022 | nan | 64880 | TK_Active | 1208363553 | 55 | 1208363553_55
MRPP2-DE3.19900 | TT_Task | Event Recorder Functional Type Test Procedure ? JRU EMU - PTA Review and Approval | 04/04/2022 | 04/05/2022 | 04/03/2022 | nan | 64880 | TK_Active | 1208363553 | 181 | 1208363553_181
MRPP2-DE3.20030 | TT_Task | Current Collection Type Test Procedure EMU - PTA Review and Approval | 20/04/2022 | 18/05/2022 | nan | nan | 64672 | TK_NotStart | 1208363553 | 51 | 1208363553_51
MRPP2-DE3.19870 | TT_Task | Lighting ; External Signage Functional Type Test Procedure = LIG ; ESG EMU - PTA Review Rev.A | 23/09/2021 | 19/10/2021 | 23/09/2021 | 19/10/2021 | 0 | TK_Complete | 1208363553 | 182 | 1208363553_182
MRPP2-DE3.28450 | TT_Task | Lighting ; External Signage Functional Type Test Procedure = LIG ; ESG EMU - Submission Rev.B | 20/10/2021 | 21/01/2022 | 20/10/2021 | 18/01/2022 | 0 | TK_Complete | 1208363553 | 182 | 1208363553_182
MRPP2-DE3.28460 | TT_Task | Lighting ; External Signage Functional Type Test Procedure = LIG ; ESG EMU - PTA Review Rev.B | 11/03/2022 | 07/04/2022 | 19/01/2022 | nan | 64880 | TK_Active | 1208363553 | 182 | 1208363553_182
MRPP2-DE3.19290 | TT_Task | Test Specification of Battery System EMU - PTA Review Rev.A | 24/05/2021 | 23/06/2021 | 24/05/2021 | 23/06/2021 | 0 | TK_Complete | 1208363553 | 183 | 1208363553_183
MRPP2-DE3.24050 | TT_Task | Test Specification of Battery System EMU - Submission Rev.B | 24/06/2021 | 09/09/2021 | 24/06/2021 | 09/09/2021 | 0 | TK_Complete | 1208363553 | 183 | 1208363553_183
MRPP2-DE3.24060 | TT_Task | Test Specification of Battery System EMU - PTA Review Rev.B | 10/09/2021 | 19/10/2021 | 10/09/2021 | 19/10/2021 | 0 | TK_Complete | 1208363553 | 183 | 1208363553_183
MRPP2-DE3.28470 | TT_Task | Test Specification of Battery System EMU - Submission Rev.C | 20/10/2021 | 18/01/2022 | 20/10/2021 | nan | 0 | TK_Active | 1208363553 | 183 | 1208363553_183
MRPP2-DE3.28480 | TT_Task | Test Specification of Battery System EMU - PTA Review Rev.C | 26/04/2022 | 23/05/2022 | nan | nan | 64648 | TK_NotStart | 1208363553 | 183 | 1208363553_183
MRPP2-DE3.19460 | TT_Task | Test specification of 25 kV Vacuum Circuit Breaker EMU - PTA Review Rev.A | 07/09/2021 | 19/10/2021 | 07/09/2021 | 19/10/2021 | 0 | TK_Complete | 1208363553 | 174 | 1208363553_174
MRPP2-DE3.28490 | TT_Task | Test specification of 25 kV Vacuum Circuit Breaker EMU - Submission Rev.B | 20/10/2021 | 20/01/2022 | 20/10/2021 | nan | 0 | TK_Active | 1208363553 | 174 | 1208363553_174
MRPP2-DE3.28500 | TT_Task | Test specification of 25 kV Vacuum Circuit Breaker EMU - PTA Review Rev.B | 20/04/2022 | 18/05/2022 | nan | nan | 64672 | TK_NotStart | 1208363553 | 174 | 1208363553_174
MRPP2-DE3.19470 | TT_Task | Test specification of Surge Arrestor EMU - PTA Review Rev.A | 12/05/2021 | 09/06/2021 | 12/05/2021 | 09/06/2021 | 0 | TK_Complete | 1208363553 | 173 | 1208363553_173
MRPP2-DE3.23740 | TT_Task | Test specification of Surge Arrestor EMU - Submission Rev.B | 10/06/2021 | 05/08/2021 | 10/06/2021 | 05/08/2021 | 0 | TK_Complete | 1208363553 | 173 | 1208363553_173
MRPP2-DE3.23750 | TT_Task | Test specification of Surge Arrestor EMU - PTA Review and Approval Rev.B | 06/08/2021 | 08/09/2021 | 06/08/2021 | 08/09/2021 | 0 | TK_Complete | 1208363553 | 173 | 1208363553_173
MRPP2-DE3.19520 | TT_Task | Test specification of Transformer EMU - PTA Review Rev.A | 10/06/2021 | 08/07/2021 | 10/06/2021 | 08/07/2021 | 0 | TK_Complete | 1208363553 | 184 | 1208363553_184
MRPP2-DE3.24390 | TT_Task | Test specification of Transformer EMU - Submission Rev.B | 09/07/2021 | 31/01/2022 | 09/07/2021 | nan | 0 | TK_Active | 1208363553 | 184 | 1208363553_184
MRPP2-DE3.24400 | TT_Task | Test specification of Transformer EMU - PTA Review Rev.B | 21/04/2022 | 19/05/2022 | nan | nan | 64664 | TK_NotStart | 1208363553 | 184 | 1208363553_184
MRPP2-DE3.19530 | TT_Task | Test specification of Earthing Switch EMU - PTA Review Rev.A | 07/09/2021 | 19/10/2021 | 07/09/2021 | 19/10/2021 | 0 | TK_Complete | 1208363553 | 175 | 1208363553_175
MRPP2-DE3.28510 | TT_Task | Test specification of Earthing Switch EMU - Submission Rev.B | 20/10/2021 | 17/01/2022 | 20/10/2021 | nan | 0 | TK_Active | 1208363553 | 175 | 1208363553_175
MRPP2-DE3.28520 | TT_Task | Test specification of Earthing Switch EMU - PTA Review Rev.B | 26/04/2022 | 23/05/2022 | nan | nan | 64648 | TK_NotStart | 1208363553 | 175 | 1208363553_175
MRPP2-DE3.19540 | TT_Task | Test Specification of Auxiliary Convertor EMU - PTA Review and Approval Rev.A | 18/06/2021 | 22/07/2021 | 18/06/2021 | 22/07/2021 | 0 | TK_Complete | 1208363553 | 185 | 1208363553_185
MRPP2-DE3.24410 | TT_Task | Test Specification of Auxiliary Convertor EMU - Submission Rev.B | 23/07/2021 | 31/01/2022 | 23/07/2021 | 02/12/2021 | 0 | TK_Complete | 1208363553 | 185 | 1208363553_185
MRPP2-DE3.24420 | TT_Task | Test Specification of Auxiliary Convertor EMU - PTA Review Rev.B | 24/03/2022 | 22/04/2022 | 03/12/2021 | nan | 64880 | TK_Active | 1208363553 | 185 | 1208363553_185
MRPP2-DE3.19690 | TT_Task | Software document for Auxiliary supply system EMU - PTA Review Rev.A | 14/07/2021 | 12/08/2021 | 14/07/2021 | 12/08/2021 | 0 | TK_Complete | 1208363553 | 186 | 1208363553_186
MRPP2-DE3.27330 | TT_Task | Software document for Auxiliary supply system EMU - Submission Rev.B | 13/08/2021 | 18/02/2022 | 13/08/2021 | nan | 0 | TK_Active | 1208363553 | 186 | 1208363553_186
MRPP2-DE3.27340 | TT_Task | Software document for Auxiliary supply system EMU - PTA Review Rev.B | 16/05/2022 | 13/06/2022 | nan | nan | 64536 | TK_NotStart | 1208363553 | 186 | 1208363553_186
MRPP2-DE3.19760 | TT_Task | Lighting Performance Type Test Procedure EMU - PTA Review Rev.A | 28/10/2021 | 26/11/2021 | 28/10/2021 | 26/11/2021 | 0 | TK_Complete | 1208363553 | 187 | 1208363553_187
MRPP2-DE3.28530 | TT_Task | Lighting Performance Type Test Procedure EMU - Submission Rev.B | 29/11/2021 | 22/12/2021 | 29/11/2021 | 12/01/2022 | 0 | TK_Complete | 1208363553 | 187 | 1208363553_187
MRPP2-DE3.28540 | TT_Task | Lighting Performance Type Test Procedure EMU - PTA Review Rev.B | 16/02/2022 | 15/03/2022 | 13/01/2022 | 18/02/2022 | 0 | TK_Complete | 1208363553 | 187 | 1208363553_187
MRPP2-DE3.29480 | TT_Task | Lighting Performance Type Test Procedure EMU - Submission Rev.C | 29/11/2021 | 10/12/2021 | 21/02/2022 | nan | 0 | TK_Active | 1208363553 | 187 | 1208363553_187
MRPP2-DE3.29490 | TT_Task | Lighting Performance Type Test Procedure EMU - PTA Review Rev.C | 15/04/2022 | 13/05/2022 | nan | nan | 64696 | TK_NotStart | 1208363553 | 187 | 1208363553_187
MRPP2-DE3.19780 | TT_Task | Battery Autonomy and Charging Type Test Procedure EMU - PTA Review Rev.A | 28/01/2022 | 24/02/2022 | 14/12/2021 | 18/01/2022 | 0 | TK_Complete | 1208363553 | 188 | 1208363553_188
MRPP2-DE3.29140 | TT_Task | Battery Autonomy and Charging Type Test Procedure EMU - Submission Rev.B | 28/01/2022 | 10/02/2022 | 19/01/2022 | nan | 0 | TK_Active | 1208363553 | 188 | 1208363553_188
MRPP2-DE3.29150 | TT_Task | Battery Autonomy and Charging Type Test Procedure EMU - PTA Review Rev.B | 28/04/2022 | 25/05/2022 | nan | nan | 64632 | TK_NotStart | 1208363553 | 188 | 1208363553_188
MRPP2-DE1.11153 | TT_Task | System Description of PACIS EMU M1 | 28/02/2020 | 11/05/2020 | 28/02/2020 | 11/05/2020 | 0 | TK_Complete | 1208363553 | 189 | 1208363553_189
MRPP2-DE1.11163 | TT_Task | System Description of PACIS - PTA Design Review Rev.A EMU M1 | 12/05/2020 | 05/06/2020 | 12/05/2020 | 05/06/2020 | 0 | TK_Complete | 1208363553 | 190 | 1208363553_190
MRPP2-DE1.15553 | TT_Task | System Description of PACIS Resubmit Rev.B EMU M1 | 08/06/2020 | 12/06/2020 | 08/06/2020 | 12/06/2020 | 0 | TK_Complete | 1208363553 | 189 | 1208363553_189
MRPP2-DE1.15563 | TT_Task | System Description of PACIS - PTA Design Review Rev.B EMU M1 | 15/06/2020 | 09/07/2020 | 15/06/2020 | 09/07/2020 | 0 | TK_Complete | 1208363553 | 190 | 1208363553_190
MRPP2-DE2.11003 | TT_Task | Final System Description of PACIS EMU M2 | 31/07/2020 | 09/10/2020 | 31/07/2020 | 09/10/2020 | 0 | TK_Complete | 1208363553 | 189 | 1208363553_189
MRPP2-DE2.11013 | TT_Task | Final System Description of PACIS - PTA Design Review Rev.A EMU M2 | 12/10/2020 | 05/11/2020 | 12/10/2020 | 05/11/2020 | 0 | TK_Complete | 1208363553 | 190 | 1208363553_190
MRPP2-DE2.18693 | TT_Task | Final System Description of PACIS - Submit Rev.B EMU M2 | 06/11/2020 | 08/01/2021 | 06/11/2020 | 08/01/2021 | 0 | TK_Complete | 1208363553 | 189 | 1208363553_189
MRPP2-DE2.18703 | TT_Task | Final System Description of PACIS - PTA Design Review Rev.B EMU M2 | 11/01/2021 | 09/02/2021 | 11/01/2021 | 09/02/2021 | 0 | TK_Complete | 1208363553 | 190 | 1208363553_190
MRPP2-DE2.18903 | TT_Task | Final System Description of PACIS - Submit Rev.C EMU M2 | 10/02/2020 | 29/03/2021 | 10/02/2020 | 29/03/2021 | 0 | TK_Complete | 1208363553 | 189 | 1208363553_189
MRPP2-DE2.18913 | TT_Task | Final System Description of PACIS - PTA Design Review Rev.C EMU M2 | 30/03/2021 | 29/04/2021 | 30/03/2021 | 29/04/2021 | 0 | TK_Complete | 1208363553 | 190 | 1208363553_190
MRPP2-DE3.19260 | TT_Task | PACIS Static Type Test Procedure ? PAI ; VSS EMU - PTA Review and Approval | 28/04/2022 | 25/05/2022 | nan | nan | 64632 | TK_NotStart | 1208363553 | 191 | 1208363553_191
MRPP2-DE3.19270 | TT_Task | PACIS Dynamic Type Test Procedure ? PAI ; VSS EMU - PTA Review and Approval | 29/04/2022 | 26/05/2022 | nan | nan | 64624 | TK_NotStart | 1208363553 | 191 | 1208363553_191
MRPP2-DE3.19640 | TT_Task | Test Specification of PACIS system EMU - PTA Review and Approval | 25/05/2021 | 02/07/2021 | 25/05/2021 | 02/07/2021 | 0 | TK_Complete | 1208363553 | 191 | 1208363553_191
MRPP2-DE1.11213 | TT_Task | System Description of Pantograph EMU M1 | 27/01/2020 | 28/04/2020 | 27/01/2020 | 28/04/2020 | 0 | TK_Complete | 1208363553 | 192 | 1208363553_192
MRPP2-DE1.11223 | TT_Task | System Description of Pantograph - PTA Design Review Rev. A EMU M1 | 29/04/2020 | 22/05/2020 | 29/04/2020 | 22/05/2020 | 0 | TK_Complete | 1208363553 | 192 | 1208363553_192
MRPP2-DE1.15453 | TT_Task | System Description of Pantograph - Resubmit Rev. B EMU M1 | 25/05/2020 | 15/06/2020 | 25/05/2020 | 15/06/2020 | 0 | TK_Complete | 1208363553 | 192 | 1208363553_192
MRPP2-DE1.15463 | TT_Task | System Description of Pantograph - PTA Design Review Rev. B EMU M1 | 16/06/2020 | 01/07/2020 | 16/06/2020 | 01/07/2020 | 0 | TK_Complete | 1208363553 | 192 | 1208363553_192
MRPP2-DE2.11243 | TT_Task | Technical Description and Drawings of Pantograph EMU M2 | 03/07/2020 | 25/09/2020 | 03/07/2020 | 28/09/2020 | 0 | TK_Complete | 1208363553 | 192 | 1208363553_192
MRPP2-DE2.11253 | TT_Task | Technical Description and Drawings of Pantograph - PTA Design Review EMU M2 | 29/09/2020 | 22/10/2020 | 29/09/2020 | 22/10/2020 | 0 | TK_Complete | 1208363553 | 192 | 1208363553_192
MRPP2-DE3.19510 | TT_Task | Test specification of Roof Mounted Pantograph EMU - PTA Review Rev.A | 27/05/2021 | 25/06/2021 | 27/05/2021 | 25/06/2021 | 0 | TK_Complete | 1208363553 | 193 | 1208363553_193
MRPP2-DE3.24070 | TT_Task | Test specification of Roof Mounted Pantograph EMU - Submission Rev.B | 28/06/2021 | 13/09/2021 | 28/06/2021 | 13/09/2021 | 0 | TK_Complete | 1208363553 | 193 | 1208363553_193
MRPP2-DE3.24080 | TT_Task | Test specification of Roof Mounted Pantograph EMU - PTA Review Rev.B | 14/09/2021 | 22/10/2021 | 14/09/2021 | 22/10/2021 | 0 | TK_Complete | 1208363553 | 193 | 1208363553_193
MRPP2-DE3.28550 | TT_Task | Test specification of Roof Mounted Pantograph EMU - Submission Rev.C | 25/10/2021 | 24/01/2022 | 25/10/2021 | 10/01/2022 | 0 | TK_Complete | 1208363553 | 193 | 1208363553_193
MRPP2-DE3.28560 | TT_Task | Test specification of Roof Mounted Pantograph EMU - PTA Review Rev.C | 18/03/2022 | 18/04/2022 | 11/01/2022 | 04/02/2022 | 0 | TK_Complete | 1208363553 | 193 | 1208363553_193
MRPP2-DE3.19790 | TT_Task | Pantograph Type Test Procedure EMU - PTA Review Rev.A | 30/09/2021 | 19/10/2021 | 30/09/2021 | 19/10/2021 | 0 | TK_Complete | 1208363553 | 194 | 1208363553_194
MRPP2-DE3.28570 | TT_Task | Pantograph Type Test Procedure EMU - Submission Rev.B | 20/10/2021 | 22/11/2021 | 20/10/2021 | 22/11/2021 | 0 | TK_Complete | 1208363553 | 194 | 1208363553_194
MRPP2-DE3.28580 | TT_Task | Pantograph Type Test Procedure EMU - PTA Review Rev.B | 23/11/2021 | 21/12/2021 | 23/11/2021 | 09/12/2021 | 0 | TK_Complete | 1208363553 | 194 | 1208363553_194
MRPP2-DE2.11303 | TT_Task | Preliminary Design Specification ? CAB EMU M2 | 22/07/2020 | 08/09/2020 | 22/07/2020 | 08/09/2020 | 0 | TK_Complete | 1208363553 | 195 | 1208363553_195
MRPP2-DE2.11313 | TT_Task | Preliminary Design Specification ? CAB - PTA Design Review Rev.A EMU M2 | 09/09/2020 | 05/10/2020 | 09/09/2020 | 05/10/2020 | 0 | TK_Complete | 1208363553 | 195 | 1208363553_195
MRPP2-DE2.18393 | TT_Task | Preliminary Design Specification ? CAB - Submit Rev.B EMU M2 | 06/10/2020 | 14/01/2021 | 06/10/2020 | 14/01/2021 | 0 | TK_Complete | 1208363553 | 195 | 1208363553_195
MRPP2-DE2.18403 | TT_Task | Preliminary Design Specification ? CAB - PTA Design Review Rev.B EMU M2 | 15/01/2021 | 12/02/2021 | 15/01/2021 | 12/02/2021 | 0 | TK_Complete | 1208363553 | 195 | 1208363553_195
MRPP2-DE3.13780 | TT_Task | Detailed Design Specification - Cab EMU M3 | 15/01/2021 | 18/03/2021 | 15/01/2021 | 18/03/2021 | 0 | TK_Complete | 1208363553 | 196 | 1208363553_196
MRPP2-DE3.13790 | TT_Task | Detailed Design Specification - Cab - PTA Design Review Rev.A EMU M3 | 19/03/2021 | 20/04/2021 | 19/03/2021 | 20/04/2021 | 0 | TK_Complete | 1208363553 | 196 | 1208363553_196
MRPP2-DE3.23170 | TT_Task | Detailed Design Specification - Cab - Submit Rev.B EMU M3 | 21/04/2021 | 30/08/2021 | 21/04/2021 | 30/08/2021 | 0 | TK_Complete | 1208363553 | 196 | 1208363553_196
MRPP2-DE3.23180 | TT_Task | Detailed Design Specification - Cab - PTA Design Review Rev.B EMU M3 | 31/08/2021 | 22/10/2021 | 31/08/2021 | 22/10/2021 | 0 | TK_Complete | 1208363553 | 196 | 1208363553_196
MRPP2-DE3.28590 | TT_Task | Detailed Design Specification - Cab - Submit Rev.C EMU M3 | 25/10/2021 | 30/11/2021 | 25/10/2021 | 30/11/2021 | 0 | TK_Complete | 1208363553 | 196 | 1208363553_196
MRPP2-DE3.28600 | TT_Task | Detailed Design Specification - Cab - PTA Design Review Rev.C EMU M3 | 01/12/2021 | 03/01/2022 | 01/12/2021 | 23/02/2022 | 0 | TK_Complete | 1208363553 | 196 | 1208363553_196
MRPP2-DE3.19800 | TT_Task | IDTP Detail Specification EMU - PTA Review and Approval | 12/05/2022 | 09/06/2022 | nan | nan | 64552 | TK_NotStart | 1208363553 | 43 | 1208363553_43
MRPP2-DE3.10850 | TT_Task | Trains and HV ; Traction Power (HVT) Detailed Interface Specification EMU M3 | 11/01/2021 | 10/02/2021 | 11/01/2021 | 10/02/2021 | 0 | TK_Complete | 1208363553 | 197 | 1208363553_197
MRPP2-DE3.10860 | TT_Task | Trains and HV ; Traction Power (HVT) Detailed Interface Specification - PTA Design Review EMU M3 | 11/02/2021 | 10/03/2021 | 11/02/2021 | 10/03/2021 | 0 | TK_Complete | 1208363553 | 197 | 1208363553_197
MRPP2-DE3.10590 | TT_Task | Trains and Signalling (SIG) Detailed Interface Specification EMU M3 | 11/01/2021 | 23/03/2021 | 11/01/2021 | 23/03/2021 | 0 | TK_Complete | 1208363553 | 198 | 1208363553_198
MRPP2-DE3.10600 | TT_Task | Trains and Signalling (SIG) Detailed Interface Specification - PTA Design Review Rev.A EMU M3 | 24/03/2021 | 22/04/2021 | 24/03/2021 | 22/04/2021 | 0 | TK_Complete | 1208363553 | 198 | 1208363553_198
MRPP2-DE3.23230 | TT_Task | Trains and Signalling (SIG) Detailed Interface Specification - Submit Rev.B EMU M3 | 23/04/2021 | 14/05/2021 | 23/04/2021 | 14/05/2021 | 0 | TK_Complete | 1208363553 | 198 | 1208363553_198
MRPP2-DE3.23240 | TT_Task | Trains and Signalling (SIG) Detailed Interface Specification - PTA Design Review Rev.B EMU M3 | 17/05/2021 | 14/06/2021 | 17/05/2021 | 14/06/2021 | 0 | TK_Complete | 1208363553 | 198 | 1208363553_198
MRPP2-DE3.23920 | TT_Task | Trains and Signalling (SIG) Detailed Interface Specification - Submit Rev.C EMU M3 | 15/06/2021 | 20/07/2021 | 15/06/2021 | 20/07/2021 | 0 | TK_Complete | 1208363553 | 198 | 1208363553_198
MRPP2-DE3.23930 | TT_Task | Trains and Signalling (SIG) Detailed Interface Specification - PTA Design Review Rev.C EMU M3 | 21/07/2021 | 23/08/2021 | 21/07/2021 | 23/08/2021 | 0 | TK_Complete | 1208363553 | 198 | 1208363553_198
MRPP2-DE3.11750 | TT_Task | Trains and Radio System (RAD) Detailed Interface Specification EMU M3 | 11/01/2021 | 09/03/2021 | 11/01/2021 | 09/03/2021 | 0 | TK_Complete | 1208363553 | 199 | 1208363553_199
MRPP2-DE3.11760 | TT_Task | Trains and Radio System (RAD) Detailed Interface Specification - PTA Design Review Rev.A EMU M3 | 10/03/2021 | 01/04/2021 | 10/03/2021 | 01/04/2021 | 0 | TK_Complete | 1208363553 | 199 | 1208363553_199
MRPP2-DE3.23090 | TT_Task | Trains and Radio System (RAD) Detailed Interface Specification - Submit Rev.B EMU M3 | 06/04/2021 | 04/05/2021 | 06/04/2021 | 04/05/2021 | 0 | TK_Complete | 1208363553 | 199 | 1208363553_199
MRPP2-DE3.23100 | TT_Task | Trains and Radio System (RAD) Detailed Interface Specification - PTA Design Review Rev.B EMU M3 | 05/05/2021 | 01/06/2021 | 05/05/2021 | 01/06/2021 | 0 | TK_Complete | 1208363553 | 199 | 1208363553_199
MRPP2-DE3.23520 | TT_Task | Trains and Radio System (RAD) Detailed Interface Specification - Submit Rev.C EMU M3 | 02/06/2021 | 28/09/2021 | 02/06/2021 | 28/09/2021 | 0 | TK_Complete | 1208363553 | 199 | 1208363553_199
MRPP2-DE3.23530 | TT_Task | Trains and Radio System (RAD) Detailed Interface Specification - PTA Design Review Rev.C EMU M3 | 29/09/2021 | 10/12/2021 | 29/09/2021 | 17/01/2022 | 0 | TK_Complete | 1208363553 | 199 | 1208363553_199
MRPP2-DE3.11790 | TT_Task | Trains and Depot Equipment (DEQ) Detailed Interface Specification EMU M3 | 11/01/2021 | 10/02/2021 | 11/01/2021 | 10/02/2021 | 0 | TK_Complete | 1208363553 | 200 | 1208363553_200
MRPP2-DE3.11800 | TT_Task | Trains and Depot Equipment (DEQ) Detailed Interface Specification - PTA Design Review EMU M3 | 11/02/2021 | 10/03/2021 | 11/02/2021 | 10/03/2021 | 0 | TK_Complete | 1208363553 | 200 | 1208363553_200
MRPP2-DE3.11830 | TT_Task | Trains and Civil Works - Station ; Depot (CWS) Detailed Interface Specification EMU M3 | 11/01/2021 | 10/02/2021 | 11/01/2021 | 10/02/2021 | 0 | TK_Complete | 1208363553 | 200 | 1208363553_200
MRPP2-DE3.11840 | TT_Task | Trains and Civil Works - Station ; Depot (CWS) Detailed Interface Specification - PTA Design Review EMU M3 | 11/02/2021 | 10/03/2021 | 11/02/2021 | 10/03/2021 | 0 | TK_Complete | 1208363553 | 200 | 1208363553_200
MRPP2-DE3.19000 | TT_Task | Interface Management Plan EMU - PTA Review Rev.A | 12/02/2021 | 15/03/2021 | 12/02/2021 | 15/03/2021 | 0 | TK_Complete | 1208363553 | 201 | 1208363553_201
MRPP2-DE3.22770 | TT_Task | Interface Management Plan EMU - Submission Rev.B | 16/03/2021 | 12/08/2021 | 16/03/2021 | 12/08/2021 | 0 | TK_Complete | 1208363553 | 60 | 1208363553_60
MRPP2-DE3.22780 | TT_Task | Interface Management Plan EMU - PTA Review ; Approval Rev.A | 13/08/2021 | 01/10/2021 | 13/08/2021 | 01/10/2021 | 0 | TK_Complete | 1208363553 | 201 | 1208363553_201
MRPP2-DE1.12003 | TT_Task | EMC Control Plan EMU M1 | 13/01/2020 | 06/04/2020 | 13/01/2020 | 06/04/2020 | 0 | TK_Complete | 1208363553 | 8 | 1208363553_8
MRPP2-DE1.12023 | TT_Task | EMC Control Plan - PTA Design Review Rev.A EMU M1 | 07/04/2020 | 30/04/2020 | 07/04/2020 | 30/04/2020 | 0 | TK_Complete | 1208363553 | 202 | 1208363553_202
MRPP2-DE1.15303 | TT_Task | EMC Control Plan - Resubmit Rev.B EMU M1 | 01/05/2020 | 18/06/2020 | 01/05/2020 | 18/06/2020 | 0 | TK_Complete | 1208363553 | 203 | 1208363553_203
MRPP2-DE1.15313 | TT_Task | EMC Control Plan - PTA Design Review Rev.B EMU M1 | 19/06/2020 | 10/07/2020 | 19/06/2020 | 10/07/2020 | 0 | TK_Complete | 1208363553 | 202 | 1208363553_202
MRPP2-DE1.15673 | TT_Task | EMC Control Plan - Resubmit Rev.C EMU M1 | 13/07/2020 | 03/08/2020 | 11/07/2020 | 03/08/2020 | 0 | TK_Complete | 1208363553 | 203 | 1208363553_203
MRPP2-DE1.15683 | TT_Task | EMC Control Plan - PTA Design Review Rev.C EMU M1 | 04/08/2020 | 28/08/2020 | 04/08/2020 | 28/08/2020 | 0 | TK_Complete | 1208363553 | 202 | 1208363553_202
MRPP2-DE3.20040 | TT_Task | EMC Type Test Procedure EMU - PTA Review and Approval | 31/05/2022 | 28/06/2022 | nan | nan | 64448 | TK_NotStart | 1208363553 | 51 | 1208363553_51
MRPP2-DE1.12403 | TT_Task | Preliminary Fire Safety Design Report EMU M1 | 17/12/2019 | 13/03/2020 | 17/12/2019 | 13/03/2020 | 0 | TK_Complete | 1208363553 | 204 | 1208363553_204
MRPP2-DE1.12423 | TT_Task | Preliminary Fire Safety Design Report - PTA Design Review Rev.A EMU M1 | 16/03/2020 | 03/04/2020 | 16/03/2020 | 03/04/2020 | 0 | TK_Complete | 1208363553 | 205 | 1208363553_205
MRPP2-DE1.15223 | TT_Task | Preliminary Fire Safety Design Report - Resubmit Rev.B EMU M1 | 06/04/2020 | 15/05/2020 | 06/04/2020 | 15/05/2020 | 0 | TK_Complete | 1208363553 | 204 | 1208363553_204
MRPP2-DE1.15233 | TT_Task | Preliminary Fire Safety Design Report - PTA Design Review Rev.B EMU M1 | 18/05/2020 | 11/06/2020 | 18/05/2020 | 11/06/2020 | 0 | TK_Complete | 1208363553 | 205 | 1208363553_205
MRPP2-DE1.15573 | TT_Task | Preliminary Fire Safety Design Report - Resubmit Rev.C EMU M1 | 12/06/2020 | 14/07/2020 | 12/06/2020 | 14/07/2020 | 0 | TK_Complete | 1208363553 | 204 | 1208363553_204
MRPP2-DE1.15583 | TT_Task | Preliminary Fire Safety Design Report - PTA Design Review Rev.C EMU M1 | 15/07/2020 | 10/08/2020 | 15/07/2020 | 10/08/2020 | 0 | TK_Complete | 1208363553 | 205 | 1208363553_205
MRPP2-DE1.12243 | TT_Task | System Description of Fire and Smoke detection system EMU M1 | 27/01/2020 | 28/04/2020 | 27/01/2020 | 28/04/2020 | 0 | TK_Complete | 1208363553 | 206 | 1208363553_206
MRPP2-DE1.12263 | TT_Task | System Description of Fire and Smoke detection system - PTA Design Review EMU M1 | 29/04/2020 | 21/05/2020 | 29/04/2020 | 21/05/2020 | 0 | TK_Complete | 1208363553 | 206 | 1208363553_206
MRPP2-DE3.13820 | TT_Task | Detailed Fire Safety Design Report EMU M3 | 29/01/2021 | 11/03/2021 | 29/01/2021 | 11/03/2021 | 0 | TK_Complete | 1208363553 | 204 | 1208363553_204
MRPP2-DE3.13890 | TT_Task | Detailed Fire Safety Design Report - PTA Design Review Rev.A EMU M3 | 12/03/2021 | 15/04/2021 | 12/03/2021 | 15/04/2021 | 0 | TK_Complete | 1208363553 | 205 | 1208363553_205
MRPP2-DE3.23110 | TT_Task | Detailed Fire Safety Design Report - Submit Rev.B EMU M3 | 16/04/2021 | 08/07/2021 | 16/04/2021 | 08/07/2021 | 0 | TK_Complete | 1208363553 | 204 | 1208363553_204
MRPP2-DE3.23120 | TT_Task | Detailed Fire Safety Design Report - PTA Design Review Rev.B EMU M3 | 09/07/2021 | 19/08/2021 | 09/07/2021 | 19/08/2021 | 0 | TK_Complete | 1208363553 | 205 | 1208363553_205
MRPP2-DE3.27350 | TT_Task | Detailed Fire Safety Design Report - Submit Rev.C EMU M3 | 20/08/2021 | 17/11/2021 | 20/08/2021 | 17/11/2021 | 0 | TK_Complete | 1208363553 | 204 | 1208363553_204
MRPP2-DE3.27360 | TT_Task | Detailed Fire Safety Design Report - PTA Design Review Rev.C EMU M3 | 18/11/2021 | 15/12/2021 | 18/11/2021 | 04/02/2022 | 0 | TK_Complete | 1208363553 | 205 | 1208363553_205
MRPP2-DE2.12503 | TT_Task | Noise and Vibration Assurance plan EMU M2 | 05/06/2020 | 06/08/2020 | 05/06/2020 | 06/08/2020 | 0 | TK_Complete | 1208363553 | 207 | 1208363553_207
MRPP2-DE2.12523 | TT_Task | Noise and Vibration Assurance plan - PTA Design Review EMU M2 | 07/08/2020 | 31/08/2020 | 07/08/2020 | 31/08/2020 | 0 | TK_Complete | 1208363553 | 207 | 1208363553_207
MRPP2-DE2.12223 | TT_Task | Noise Report - Preliminary Specification and Prediction EMU M3 | 16/07/2020 | 13/10/2020 | 16/07/2020 | 13/10/2020 | 0 | TK_Complete | 1208363553 | 208 | 1208363553_208
MRPP2-DE2.12243 | TT_Task | Noise Report - Preliminary Specification and Prediction - PTA Design Review Rev.A EMU M3 | 14/10/2020 | 09/11/2020 | 14/10/2020 | 09/11/2020 | 0 | TK_Complete | 1208363553 | 209 | 1208363553_209
MRPP2-DE2.18713 | TT_Task | Noise Report - Preliminary Specification and Prediction - Submit Rev.B EMU M3 | 10/11/2020 | 25/01/2021 | 10/11/2020 | 25/01/2021 | 0 | TK_Complete | 1208363553 | 208 | 1208363553_208
MRPP2-DE2.18723 | TT_Task | Noise Report - Preliminary Specification and Prediction - PTA Design Review Rev.B EMU M3 | 27/01/2021 | 22/02/2021 | 26/01/2021 | 22/02/2021 | 0 | TK_Complete | 1208363553 | 209 | 1208363553_209
MRPP2-DE2.18983 | TT_Task | Noise Report - Preliminary Specification and Prediction - Submit Rev.C EMU M3 | 23/02/2021 | 31/03/2021 | 23/02/2021 | 31/03/2021 | 0 | TK_Complete | 1208363553 | 208 | 1208363553_208
MRPP2-DE2.18993 | TT_Task | Noise Report - Preliminary Specification and Prediction - PTA Design Review Rev.C EMU M3 | 01/04/2021 | 03/05/2021 | 01/04/2021 | 03/05/2021 | 0 | TK_Complete | 1208363553 | 209 | 1208363553_209
MRPP2-DE3.13870 | TT_Task | Noise Report - Final Prediction EMU M3 | 29/01/2021 | 15/09/2021 | 29/01/2021 | 15/09/2021 | 0 | TK_Complete | 1208363553 | 208 | 1208363553_208
MRPP2-DE3.14030 | TT_Task | Noise Report - Final Prediction - PTA Design Review Rev.A EMU M3 | 16/09/2021 | 22/10/2021 | 16/09/2021 | 22/10/2021 | 0 | TK_Complete | 1208363553 | 209 | 1208363553_209
MRPP2-DE3.28610 | TT_Task | Noise Report - Final Prediction - Submit Rev.B EMU M3 | 25/10/2021 | 10/12/2021 | 25/10/2021 | 08/12/2021 | 0 | TK_Complete | 1208363553 | 208 | 1208363553_208
MRPP2-DE3.28620 | TT_Task | Noise Report - Final Prediction - PTA Design Review Rev.B EMU M3 | 04/02/2022 | 03/03/2022 | 09/12/2021 | 31/01/2022 | 0 | TK_Complete | 1208363553 | 209 | 1208363553_209
MRPP2-DE3.20000 | TT_Task | Noise Static Type Test Procedure EMU - PTA Review Rev.A | 28/01/2022 | 24/02/2022 | 09/12/2021 | 14/01/2022 | 0 | TK_Complete | 1208363553 | 210 | 1208363553_210
MRPP2-DE3.29160 | TT_Task | Noise Static Type Test Procedure EMU - Submission Rev.B | 28/01/2022 | 10/02/2022 | 17/01/2022 | nan | 0 | TK_Active | 1208363553 | 210 | 1208363553_210
MRPP2-DE3.29170 | TT_Task | Noise Static Type Test Procedure EMU - PTA Review Rev.B | 21/04/2022 | 19/05/2022 | nan | nan | 64664 | TK_NotStart | 1208363553 | 210 | 1208363553_210
MRPP2-DE3.20010 | TT_Task | Noise Dynamic Type Test Procedure EMU - PTA Review and Approval | 14/03/2022 | 12/04/2022 | 02/03/2022 | nan | 64880 | TK_Active | 1208363553 | 210 | 1208363553_210
MRPP2-DE1.11333 | TT_Task | Weight Management Plan EMU M1 | 30/12/2019 | 04/02/2020 | 30/12/2019 | 04/02/2020 | 0 | TK_Complete | 1208363553 | 211 | 1208363553_211
MRPP2-DE1.11343 | TT_Task | Weight Management Plan - PTA Design Review Rev.A EMU M1 | 05/02/2020 | 27/02/2020 | 05/02/2020 | 27/02/2020 | 0 | TK_Complete | 1208363553 | 212 | 1208363553_212
MRPP2-DE1.15053 | TT_Task | Weight Management Plan - Resubmit to PTA Rev.B EMU M1 | 28/02/2020 | 23/03/2020 | 28/02/2020 | 23/03/2020 | 0 | TK_Complete | 1208363553 | 211 | 1208363553_211
MRPP2-DE1.15063 | TT_Task | Weight Management Plan - PTA Design Review Rev.B EMU M1 | 24/03/2020 | 06/04/2020 | 24/03/2020 | 06/04/2020 | 0 | TK_Complete | 1208363553 | 212 | 1208363553_212
MRPP2-DE3.12260 | TT_Task | Weight distribution calculations report EMU M3 | 16/10/2020 | 19/11/2020 | 16/10/2020 | 19/11/2020 | 0 | TK_Complete | 1208363553 | 213 | 1208363553_213
MRPP2-DE3.12280 | TT_Task | Weight distribution calculations report - PTA Design Review EMU M3 | 20/11/2020 | 16/12/2020 | 20/11/2020 | 16/12/2020 | 0 | TK_Complete | 1208363553 | 213 | 1208363553_213
MRPP2-DE3.11120 | TT_Task | Final Passengers Load and capacity calculations EMU M3 | 30/10/2020 | 15/12/2020 | 30/10/2020 | 15/12/2020 | 0 | TK_Complete | 1208363553 | 214 | 1208363553_214
MRPP2-DE3.11130 | TT_Task | Final Passengers Load and capacity calculations - PTA Design Review Rev.A EMU M3 | 16/12/2020 | 01/02/2021 | 16/12/2020 | 01/02/2021 | 0 | TK_Complete | 1208363553 | 214 | 1208363553_214
MRPP2-DE3.22530 | TT_Task | Final Passengers Load and capacity calculations - Submit Rev.B EMU M3 | 02/02/2021 | 22/02/2021 | 02/02/2021 | 22/02/2021 | 0 | TK_Complete | 1208363553 | 214 | 1208363553_214
MRPP2-DE3.22540 | TT_Task | Final Passengers Load and capacity calculations - PTA Design Review Rev.B EMU M3 | 23/02/2021 | 12/03/2021 | 23/02/2021 | 12/03/2021 | 0 | TK_Complete | 1208363553 | 214 | 1208363553_214
MRPP2-DE3.19130 | TT_Task | Weighment Type Test Procedure EMU - PTA Review Rev.A | 23/09/2021 | 12/10/2021 | 23/09/2021 | 12/10/2021 | 0 | TK_Complete | 1208363553 | 215 | 1208363553_215
MRPP2-DE3.28630 | TT_Task | Weighment Type Test Procedure EMU - Submission Rev.B | 13/10/2021 | 22/12/2021 | 13/10/2021 | 23/12/2021 | 0 | TK_Complete | 1208363553 | 215 | 1208363553_215
MRPP2-DE3.28640 | TT_Task | Weighment Type Test Procedure EMU - PTA Review Rev.B | 16/02/2022 | 15/03/2022 | 24/12/2021 | 27/01/2022 | 0 | TK_Complete | 1208363553 | 215 | 1208363553_215
MRPP2-DE3.19600 | TT_Task | Type Test Specification - Load test of Floor panel EMU - PTA Review Rev.A | 07/07/2021 | 05/08/2021 | 07/07/2021 | 05/08/2021 | 0 | TK_Complete | 1208363553 | 216 | 1208363553_216
MRPP2-DE3.27130 | TT_Task | Type Test Specification - Load test of Floor panel EMU - Submission Rev.B | 06/08/2021 | 15/02/2022 | 06/08/2021 | nan | 0 | TK_Active | 1208363553 | 216 | 1208363553_216
MRPP2-DE3.27140 | TT_Task | Type Test Specification - Load test of Floor panel EMU - PTA Review and Approval Rev.B | 26/04/2022 | 23/05/2022 | nan | nan | 64648 | TK_NotStart | 1208363553 | 216 | 1208363553_216
MRPP2-DE1.12163 | TT_Task | Schedule of Hazard Analysis EMU M1 | 30/12/2019 | 12/02/2020 | 30/12/2019 | 12/02/2020 | 0 | TK_Complete | 1208363553 | 217 | 1208363553_217
MRPP2-DE1.12183 | TT_Task | Schedule of Hazard Analysis - PTA Design Review Rev.A EMU M1 | 13/02/2020 | 06/03/2020 | 13/02/2020 | 06/03/2020 | 0 | TK_Complete | 1208363553 | 218 | 1208363553_218
MRPP2-DE1.15073 | TT_Task | Schedule of Hazard Analysis - Resubmit Rev.B EMU M1 | 09/03/2020 | 08/04/2020 | 09/03/2020 | 08/04/2020 | 0 | TK_Complete | 1208363553 | 217 | 1208363553_217
MRPP2-DE1.15083 | TT_Task | Schedule of Hazard Analysis - PTA Design Review Rev.B EMU M1 | 09/04/2020 | 30/04/2020 | 09/04/2020 | 30/04/2020 | 0 | TK_Complete | 1208363553 | 218 | 1208363553_218
MRPP2-DE1.12123 | TT_Task | Safety Assurance Plan EMU M1 | 30/12/2019 | 21/02/2020 | 30/12/2019 | 21/02/2020 | 0 | TK_Complete | 1208363553 | 219 | 1208363553_219
MRPP2-DE1.12143 | TT_Task | Safety Assurance Plan - PTA Design Review Rev.A EMU M1 | 24/02/2020 | 20/03/2020 | 24/02/2020 | 20/03/2020 | 0 | TK_Complete | 1208363553 | 220 | 1208363553_220
MRPP2-DE1.15103 | TT_Task | Safety Assurance Plan - PTA Design Review Rev.B EMU M1 | 22/04/2020 | 07/05/2020 | 22/04/2020 | 07/05/2020 | 0 | TK_Complete | 1208363553 | 220 | 1208363553_220
MRPP2-DE1.15113 | TT_Task | Safety Assurance Plan - Resubmit Rev.B EMU M1 | 23/03/2020 | 21/04/2020 | 23/03/2020 | 21/04/2020 | 0 | TK_Complete | 1208363553 | 219 | 1208363553_219
MRPP2-DE2.11393 | TT_Task | Reliability, Availability and Maintainability Plan EMU M2 | 11/02/2020 | 21/02/2020 | 11/02/2020 | 21/02/2020 | 0 | TK_Complete | 1208363553 | 221 | 1208363553_221
MRPP2-DE2.11403 | TT_Task | Reliability, Availability and Maintainability Plan - PTA Design Review Rev.A EMU M2 | 24/02/2020 | 17/03/2020 | 23/02/2020 | 17/03/2020 | 0 | TK_Complete | 1208363553 | 221 | 1208363553_221
MRPP2-DE2.18093 | TT_Task | Reliability, Availability and Maintainability Plan - Resubmit Rev.B EMU M2 | 18/03/2020 | 19/05/2020 | 18/03/2020 | 19/05/2020 | 0 | TK_Complete | 1208363553 | 221 | 1208363553_221
MRPP2-DE2.18103 | TT_Task | Reliability, Availability and Maintainability Plan - PTA Design Review Rev.B EMU M2 | 20/05/2020 | 11/06/2020 | 20/05/2020 | 11/06/2020 | 0 | TK_Complete | 1208363553 | 221 | 1208363553_221
MRPP2-DE2.13063 | TT_Task | Train Software Management Plan EMU M2 | 05/03/2020 | 30/04/2020 | 05/03/2020 | 30/04/2020 | 0 | TK_Complete | 1208363553 | 222 | 1208363553_222
MRPP2-DE2.13083 | TT_Task | Train Software Management Plan - PTA Design Review EMU M2 | 01/05/2020 | 22/05/2020 | 01/05/2020 | 22/05/2020 | 0 | TK_Complete | 1208363553 | 222 | 1208363553_222
MRPP2-DE3.10770 | TT_Task | Preliminary Hazard Analysis (PHA) EMU M3 | 22/06/2020 | 01/07/2020 | 22/06/2020 | 01/07/2020 | 0 | TK_Complete | 1208363553 | 223 | 1208363553_223
MRPP2-DE3.10838 | TT_Task | Preliminary Hazard Analysis (PHA) - PTA Design Review Rev.A EMU M3 | 02/07/2020 | 10/07/2020 | 02/07/2020 | 10/07/2020 | 0 | TK_Complete | 1208363553 | 224 | 1208363553_224
MRPP2-DE3.22410 | TT_Task | Preliminary Hazard Analysis (PHA) - Submit Rev.B EMU M3 | 13/07/2020 | 04/12/2020 | 13/07/2020 | 04/12/2020 | 0 | TK_Complete | 1208363553 | 223 | 1208363553_223
MRPP2-DE3.22420 | TT_Task | Preliminary Hazard Analysis (PHA) - PTA Design Review Rev.B EMU M3 | 07/12/2020 | 21/01/2021 | 07/12/2020 | 21/01/2021 | 0 | TK_Complete | 1208363553 | 224 | 1208363553_224
MRPP2-DE3.22490 | TT_Task | Preliminary Hazard Analysis (PHA) - Submit Rev.C EMU M3 | 22/01/2021 | 20/07/2021 | 22/01/2021 | 20/07/2021 | 0 | TK_Complete | 1208363553 | 223 | 1208363553_223
MRPP2-DE3.22500 | TT_Task | Preliminary Hazard Analysis (PHA) - PTA Design Review Rev.C EMU M3 | 21/07/2021 | 26/08/2021 | 21/07/2021 | 26/08/2021 | 0 | TK_Complete | 1208363553 | 224 | 1208363553_224
MRPP2-DE3.12380 | TT_Task | Reliability Apportionment and Prediction Report EMU M3 | 05/10/2020 | 22/10/2020 | 05/10/2020 | 22/10/2020 | 0 | TK_Complete | 1208363553 | 225 | 1208363553_225
MRPP2-DE3.12400 | TT_Task | Reliability Apportionment and Prediction Report - PTA Design Review Rev.A EMU M3 | 23/10/2020 | 18/11/2020 | 23/10/2020 | 18/11/2020 | 0 | TK_Complete | 1208363553 | 226 | 1208363553_226
MRPP2-DE3.22470 | TT_Task | Reliability Apportionment and Prediction Report - Submit Rev.B EMU M3 | 19/11/2020 | 26/02/2021 | 19/11/2020 | 26/02/2021 | 0 | TK_Complete | 1208363553 | 225 | 1208363553_225
MRPP2-DE3.22480 | TT_Task | Reliability Apportionment and Prediction Report - PTA Design Review Rev.B EMU M3 | 02/03/2021 | 29/03/2021 | 02/03/2021 | 29/03/2021 | 0 | TK_Complete | 1208363553 | 226 | 1208363553_226
MRPP2-DE3.22970 | TT_Task | Reliability Apportionment and Prediction Report - Submit Rev.C EMU M3 | 30/03/2021 | 05/05/2021 | 30/03/2021 | 05/05/2021 | 0 | TK_Complete | 1208363553 | 225 | 1208363553_225
MRPP2-DE3.22980 | TT_Task | Reliability Apportionment and Prediction Report - PTA Design Review Rev.C EMU M3 | 06/05/2021 | 04/06/2021 | 06/05/2021 | 04/06/2021 | 0 | TK_Complete | 1208363553 | 226 | 1208363553_226
MRPP2-DE3.24090 | TT_Task | Reliability Apportionment and Prediction Report - Submit Rev.D EMU M3 | 08/06/2021 | 21/07/2021 | 07/06/2021 | 21/07/2021 | 0 | TK_Complete | 1208363553 | 225 | 1208363553_225
MRPP2-DE3.24100 | TT_Task | Reliability Apportionment and Prediction Report - PTA Design Review Rev.D EMU M3 | 22/07/2021 | 02/09/2021 | 22/07/2021 | 02/09/2021 | 0 | TK_Complete | 1208363553 | 226 | 1208363553_226
MRPP2-DE3.10963 | TT_Task | RAM demonstration ; FRACAS Plan EMU M3 | 14/01/2021 | 09/03/2021 | 14/01/2021 | 09/03/2021 | 0 | TK_Complete | 1208363553 | 227 | 1208363553_227
MRPP2-DE3.10973 | TT_Task | RAM demonstration ; FRACAS Plan - PTA Design Review Rev.A EMU M3 | 10/03/2021 | 01/04/2021 | 10/03/2021 | 01/04/2021 | 0 | TK_Complete | 1208363553 | 228 | 1208363553_228
MRPP2-DE3.23130 | TT_Task | RAM demonstration ; FRACAS Plan - Submit Rev.B EMU M3 | 06/04/2021 | 10/06/2021 | 02/04/2021 | 10/06/2021 | 0 | TK_Complete | 1208363553 | 227 | 1208363553_227
MRPP2-DE3.23140 | TT_Task | RAM demonstration ; FRACAS Plan - PTA Design Review Rev.B EMU M3 | 11/06/2021 | 20/07/2021 | 11/06/2021 | 20/07/2021 | 0 | TK_Complete | 1208363553 | 228 | 1208363553_228
MRPP2-DE3.24430 | TT_Task | RAM demonstration ; FRACAS Plan - Submit Rev.C EMU M3 | 21/07/2021 | 27/10/2021 | 21/07/2021 | 27/10/2021 | 0 | TK_Complete | 1208363553 | 227 | 1208363553_227
MRPP2-DE3.24440 | TT_Task | RAM demonstration ; FRACAS Plan - PTA Design Review Rev.C EMU M3 | 28/10/2021 | 10/12/2021 | 28/10/2021 | 14/01/2022 | 0 | TK_Complete | 1208363553 | 228 | 1208363553_228
MRPP2-DE3.29180 | TT_Task | RAM demonstration ; FRACAS Plan - Submit Rev.D EMU M3 | 28/01/2022 | 10/02/2022 | 17/01/2022 | 20/01/2022 | 0 | TK_Complete | 1208363553 | 227 | 1208363553_227
MRPP2-DE3.29190 | TT_Task | RAM demonstration ; FRACAS Plan - PTA Design Review Rev.D EMU M3 | 11/02/2022 | 10/03/2022 | 21/01/2022 | 09/02/2022 | 0 | TK_Complete | 1208363553 | 228 | 1208363553_228
MRPP2-DE3.14180 | TT_Task | Interface hazard analysis (IHA) EMU M3 | 01/09/2020 | 17/09/2020 | 01/09/2020 | 17/09/2020 | 0 | TK_Complete | 1208363553 | 229 | 1208363553_229
MRPP2-DE3.14200 | TT_Task | Interface hazard analysis (IHA) - PTA Design Review Rev.A EMU M3 | 18/09/2020 | 14/10/2020 | 18/09/2020 | 14/10/2020 | 0 | TK_Complete | 1208363553 | 230 | 1208363553_230
MRPP2-DE3.22430 | TT_Task | Interface hazard analysis (IHA) - Submit Rev.B EMU M3 | 15/10/2020 | 22/02/2021 | 15/10/2020 | 22/02/2021 | 0 | TK_Complete | 1208363553 | 229 | 1208363553_229
MRPP2-DE3.22440 | TT_Task | Interface hazard analysis (IHA) - PTA Design Review Rev.B EMU M3 | 23/02/2021 | 23/03/2021 | 23/02/2021 | 23/03/2021 | 0 | TK_Complete | 1208363553 | 230 | 1208363553_230
MRPP2-DE3.22930 | TT_Task | Interface hazard analysis (IHA) - Submit Rev.C EMU M3 | 24/03/2021 | 09/08/2021 | 24/03/2021 | 09/08/2021 | 0 | TK_Complete | 1208363553 | 229 | 1208363553_229
MRPP2-DE3.22940 | TT_Task | Interface hazard analysis (IHA) - PTA Design Review Rev.C EMU M3 | 10/08/2021 | 01/10/2021 | 10/08/2021 | 01/10/2021 | 0 | TK_Complete | 1208363553 | 230 | 1208363553_230
MRPP2-DE3.14260 | TT_Task | Subsystem hazard analysis (SSHA) EMU M3 | 27/01/2021 | 24/02/2021 | 27/01/2021 | 24/02/2021 | 0 | TK_Complete | 1208363553 | 231 | 1208363553_231
MRPP2-DE3.14280 | TT_Task | Subsystem hazard analysis (SSHA) - PTA Design Review Rev.A EMU M3 | 25/02/2021 | 26/03/2021 | 25/02/2021 | 26/03/2021 | 0 | TK_Complete | 1208363553 | 232 | 1208363553_232
MRPP2-DE3.22950 | TT_Task | Subsystem hazard analysis (SSHA) - Submit Rev.B EMU M3 | 29/03/2021 | 13/08/2021 | 29/03/2021 | 13/08/2021 | 0 | TK_Complete | 1208363553 | 231 | 1208363553_231
MRPP2-DE3.22960 | TT_Task | Subsystem hazard analysis (SSHA) - PTA Design Review Rev.B EMU M3 | 16/08/2021 | 30/09/2021 | 14/08/2021 | 30/09/2021 | 0 | TK_Complete | 1208363553 | 232 | 1208363553_232
MRPP2-DE3.27550 | TT_Task | Subsystem hazard analysis (SSHA) - Submit Rev.C EMU M3 | 01/10/2021 | 10/01/2022 | 01/10/2021 | 11/01/2022 | 0 | TK_Complete | 1208363553 | 231 | 1208363553_231
MRPP2-DE3.27560 | TT_Task | Subsystem hazard analysis (SSHA) - PTA Design Review Rev.C EMU M3 | 04/03/2022 | 31/03/2022 | 12/01/2022 | 08/02/2022 | 0 | TK_Complete | 1208363553 | 232 | 1208363553_232
MRPP2-DE3.14540 | TT_Task | Safety Critical Item List EMU M3 | 27/01/2021 | 25/02/2021 | 27/01/2021 | 25/02/2021 | 0 | TK_Complete | 1208363553 | 233 | 1208363553_233
MRPP2-DE3.14560 | TT_Task | Safety Critical Item List - PTA Design Review EMU M3 | 26/02/2021 | 25/03/2021 | 26/02/2021 | 25/03/2021 | 0 | TK_Complete | 1208363553 | 233 | 1208363553_233
MRPP2-DE3.13830 | TT_Task | Reliability Critical Item List EMU M3 | 27/01/2021 | 25/02/2021 | 27/01/2021 | 25/02/2021 | 0 | TK_Complete | 1208363553 | 233 | 1208363553_233
MRPP2-DE3.13950 | TT_Task | Reliability Critical Item List - PTA Design Review EMU M3 | 26/02/2021 | 25/03/2021 | 26/02/2021 | 25/03/2021 | 0 | TK_Complete | 1208363553 | 233 | 1208363553_233
MRPP2-DE3.14500 | TT_Task | Failure modes effects and criticality analysis (FMECA) EMU M3 | 29/12/2020 | 11/01/2021 | 29/12/2020 | 11/01/2021 | 0 | TK_Complete | 1208363553 | 234 | 1208363553_234
MRPP2-DE3.14520 | TT_Task | Failure modes effects and criticality analysis (FMECA) - PTA Design Review Rev.A EMU M3 | 12/01/2021 | 10/02/2021 | 12/01/2021 | 10/02/2021 | 0 | TK_Complete | 1208363553 | 235 | 1208363553_235
MRPP2-DE3.22710 | TT_Task | Failure modes effects and criticality analysis (FMECA) - Submit Rev.B EMU M3 | 11/02/2021 | 23/04/2021 | 11/02/2021 | 23/04/2021 | 0 | TK_Complete | 1208363553 | 234 | 1208363553_234
MRPP2-DE3.22720 | TT_Task | Failure modes effects and criticality analysis (FMECA) - PTA Design Review Rev.B EMU M3 | 27/04/2021 | 21/05/2021 | 27/04/2021 | 21/05/2021 | 0 | TK_Complete | 1208363553 | 235 | 1208363553_235
MRPP2-DE3.23470 | TT_Task | Failure modes effects and criticality analysis (FMECA) - Submit Rev.C EMU M3 | 24/05/2021 | 11/10/2021 | 24/05/2021 | 11/10/2021 | 0 | TK_Complete | 1208363553 | 234 | 1208363553_234
MRPP2-DE3.23480 | TT_Task | Failure modes effects and criticality analysis (FMECA) - PTA Design Review Rev.C EMU M3 | 12/10/2021 | 10/12/2021 | 12/10/2021 | 22/02/2022 | 0 | TK_Complete | 1208363553 | 235 | 1208363553_235
MRPP2-DE3.19700 | TT_Task | Quantitative fault tree analysis EMU - PTA Review Rev.A | 19/07/2021 | 19/08/2021 | 17/07/2021 | 19/08/2021 | 0 | TK_Complete | 1208363553 | 236 | 1208363553_236
MRPP2-DE3.27370 | TT_Task | Quantitative fault tree analysis EMU - PTA Review Rev.B | 31/03/2022 | 02/05/2022 | 10/12/2021 | 01/03/2022 | 0 | TK_Complete | 1208363553 | 236 | 1208363553_236
MRPP2-DE3.27380 | TT_Task | Quantitative fault tree analysis EMU - Submission Rev.B | 20/08/2021 | 07/02/2022 | 20/08/2021 | 09/12/2021 | 0 | TK_Complete | 1208363553 | 236 | 1208363553_236
MRPP2-DE3.29600 | TT_Task | Quantitative fault tree analysis EMU - Submission Rev.C | 04/04/2022 | 27/04/2022 | 02/03/2022 | nan | 0 | TK_Active | 1208363553 | 236 | 1208363553_236
MRPP2-DE3.29610 | TT_Task | Quantitative fault tree analysis EMU - PTA Review Rev.C | 13/05/2022 | 10/06/2022 | nan | nan | 64544 | TK_NotStart | 1208363553 | 236 | 1208363553_236
MRPP2-DE3.19710 | TT_Task | Design Safety Study Report EMU - PTA Review Rev.A | 03/08/2021 | 09/09/2021 | 03/08/2021 | 09/09/2021 | 0 | TK_Complete | 1208363553 | 237 | 1208363553_237
MRPP2-DE3.27570 | TT_Task | Design Safety Study Report EMU - Submission Rev.B | 10/09/2021 | 08/02/2022 | 10/09/2021 | 13/12/2021 | 0 | TK_Complete | 1208363553 | 237 | 1208363553_237
MRPP2-DE3.27580 | TT_Task | Design Safety Study Report EMU - PTA Review Rev.B | 01/04/2022 | 03/05/2022 | 14/12/2021 | 04/02/2022 | 0 | TK_Complete | 1208363553 | 237 | 1208363553_237
MRPP2-DE3.29380 | TT_Task | Design Safety Study Report EMU - Submission Rev.C | 10/09/2021 | 23/09/2021 | 07/02/2022 | nan | 0 | TK_Active | 1208363553 | 237 | 1208363553_237
MRPP2-DE3.29390 | TT_Task | Design Safety Study Report EMU - PTA Review Rev.C | 20/06/2022 | 15/07/2022 | nan | nan | 64344 | TK_NotStart | 1208363553 | 237 | 1208363553_237
MRPP2-DE3.19720 | TT_Task | Hazard Log EMU - PTA Review and Approval | 15/04/2022 | 13/05/2022 | 20/01/2022 | nan | 64880 | TK_Active | 1208363553 | 238 | 1208363553_238
MRPP2-DE3.19730 | TT_Task | Application Safety Case EMU - PTA Review and Approval | 29/04/2022 | 26/05/2022 | nan | nan | 64624 | TK_NotStart | 1208363553 | 38 | 1208363553_38
MRPP2-DE3.28850 | TT_Task | Electrical Activities In Anticipation | 01/10/2021 | 15/12/2021 | 01/10/2021 | 15/12/2021 | 0 | TK_Complete | 1208363553 | 239 | 1208363553_239
MRPP2-DE3.28870 | TT_Task | Train Electrical - Synoptic | 09/02/2022 | 01/03/2022 | 16/12/2021 | 06/01/2022 | 0 | TK_Complete | 1208363553 | 240 | 1208363553_240
MRPP2-DE3.28880 | TT_Task | COE - SPS Analysis, FD, Step - 1 | 02/03/2022 | 05/04/2022 | 07/01/2022 | 11/02/2022 | 0 | TK_Complete | 1208363553 | 241 | 1208363553_241
MRPP2-DE3.28890 | TT_Task | COE - Step - 2 | 21/03/2022 | 19/04/2022 | 14/02/2022 | 11/03/2022 | 0 | TK_Complete | 1208363553 | 242 | 1208363553_242
MRPP2-DE3.28900 | TT_Task | CJB - Manufacturing ; Delivery of Modified Train Harnesses / Cubicles | 20/05/2022 | 21/11/2022 | nan | nan | 0 | TK_NotStart | 1208363553 | 243 | 1208363553_243
MRPP2-DE3.28910 | TT_Task | COE - Step - 3 to 6 | 14/04/2022 | 15/08/2022 | 14/03/2022 | nan | 0 | TK_Active | 1208363553 | 242 | 1208363553_242
MRPP2-DE3.24490 | TT_Task | IOS List EMU | 03/05/2021 | 21/05/2021 | 01/05/2021 | 21/05/2021 | 0 | TK_Complete | 1208363553 | 244 | 1208363553_244
MRPP2-DE3.24520 | TT_Task | IOS List - PTA Design Review Rev.A EMU | 24/05/2021 | 02/07/2021 | 22/05/2021 | 02/07/2021 | 0 | TK_Complete | 1208363553 | 245 | 1208363553_245
MRPP2-DE3.24890 | TT_Task | IOS List - Submit Rev.B EMU | 05/07/2021 | 16/12/2021 | 03/07/2021 | 22/12/2021 | 0 | TK_Complete | 1208363553 | 244 | 1208363553_244
MRPP2-DE3.24900 | TT_Task | IOS List - PTA Design Review ; Approval Rev.B EMU | 10/02/2022 | 09/03/2022 | 23/12/2021 | 18/03/2022 | 0 | TK_Complete | 1208363553 | 245 | 1208363553_245
MRPP2-DE3.25730 | TT_Task | Detailed Design Specification of PACIS EMU M3 | 01/07/2021 | 22/07/2021 | 01/07/2021 | 22/07/2021 | 0 | TK_Complete | 1208363553 | 246 | 1208363553_246
MRPP2-DE3.25750 | TT_Task | Detailed Design Specification of PACIS - PTA Design Review Rev.A EMU M3 | 23/07/2021 | 27/08/2021 | 23/07/2021 | 27/08/2021 | 0 | TK_Complete | 1208363553 | 246 | 1208363553_246
MRPP2-DE3.25760 | TT_Task | Detailed Design Specification of PACIS - Submit Rev.B EMU M3 | 30/08/2021 | 30/11/2021 | 30/08/2021 | 30/11/2021 | 0 | TK_Complete | 1208363553 | 246 | 1208363553_246
MRPP2-DE3.25770 | TT_Task | Detailed Design Specification of PACIS - PTA Design Review ; Approval Rev.B EMU M3 | 01/12/2021 | 03/01/2022 | 01/12/2021 | 14/02/2022 | 0 | TK_Complete | 1208363553 | 246 | 1208363553_246
MRPP2-DE3.24850 | TT_Task | Inspection Instruction for Complete Carbody EMU - PTA Review Rev.A | 19/04/2022 | 17/05/2022 | nan | nan | 64680 | TK_NotStart | 1208363553 | 247 | 1208363553_247
MRPP2-DE3.24860 | TT_Task | Ergonomics Management Plan EMU - PTA Review Rev.A | 12/05/2020 | 15/06/2020 | 12/05/2020 | 15/06/2020 | 0 | TK_Complete | 1208363553 | 248 | 1208363553_248
MRPP2-DE3.26570 | TT_Task | Ergonomics Management Plan EMU - Submission Rev.B | 16/06/2020 | 11/08/2020 | 16/06/2020 | 11/08/2020 | 0 | TK_Complete | 1208363553 | 248 | 1208363553_248
MRPP2-DE3.26580 | TT_Task | Ergonomics Management Plan EMU - PTA Review ; Approval Rev.B | 12/08/2020 | 07/09/2020 | 12/08/2020 | 07/09/2020 | 0 | TK_Complete | 1208363553 | 248 | 1208363553_248
MRPP2-DE3.24870 | TT_Task | Surface Protection / Corrosion Management Plan EMU - PTA Review Rev.A | 07/05/2020 | 02/06/2020 | 07/05/2020 | 02/06/2020 | 0 | TK_Complete | 1208363553 | 249 | 1208363553_249
MRPP2-DE3.26590 | TT_Task | Surface Protection / Corrosion Management Plan EMU - Submission Rev.B | 03/06/2020 | 17/07/2020 | 03/06/2020 | 17/07/2020 | 0 | TK_Complete | 1208363553 | 249 | 1208363553_249
MRPP2-DE3.26600 | TT_Task | Surface Protection / Corrosion Management Plan EMU - PTA Review ; Approval Rev.B | 20/07/2020 | 04/08/2020 | 18/07/2020 | 04/08/2020 | 0 | TK_Complete | 1208363553 | 249 | 1208363553_249
MRPP2-DE3.26620 | TT_Task | Noise Management Plan EMU - PTA Review Rev.A | 04/05/2020 | 28/05/2020 | 02/05/2020 | 28/05/2020 | 0 | TK_Complete | 1208363553 | 207 | 1208363553_207
MRPP2-DE3.26630 | TT_Task | Noise Management Plan EMU - Submission Rev.B | 29/05/2020 | 04/08/2020 | 29/05/2020 | 04/08/2020 | 0 | TK_Complete | 1208363553 | 207 | 1208363553_207
MRPP2-DE3.26640 | TT_Task | Noise Management Plan EMU - PTA Review ; Approval Rev.B | 05/08/2020 | 01/09/2020 | 05/08/2020 | 01/09/2020 | 0 | TK_Complete | 1208363553 | 207 | 1208363553_207
MRPP2-DE3.26660 | TT_Task | Configuration and Change Management Plan EMU - PTA Review Rev.A | 17/08/2020 | 10/09/2020 | 15/08/2020 | 10/09/2020 | 0 | TK_Complete | 1208363553 | 250 | 1208363553_250
MRPP2-DE3.26670 | TT_Task | Configuration and Change Management Plan EMU - Submission Rev.B | 11/09/2020 | 18/12/2020 | 11/09/2020 | 18/12/2020 | 0 | TK_Complete | 1208363553 | 60 | 1208363553_60
MRPP2-DE3.26680 | TT_Task | Configuration and Change Management Plan EMU - PTA Review ; Approval Rev.B | 21/12/2020 | 05/02/2021 | 19/12/2020 | 05/02/2021 | 0 | TK_Complete | 1208363553 | 250 | 1208363553_250
MRPP2-DE3.25180 | TT_Task | Obsolescence Management Plan EMU - PTA Review Rev.A | 01/04/2021 | 03/05/2021 | 01/04/2021 | 03/05/2021 | 0 | TK_Complete | 1208363553 | 251 | 1208363553_251
MRPP2-DE3.26690 | TT_Task | Obsolescence Management Plan EMU - Submission Rev.B | 04/05/2021 | 25/01/2022 | 04/05/2021 | 10/03/2022 | 0 | TK_Complete | 1208363553 | 251 | 1208363553_251
MRPP2-DE3.26700 | TT_Task | Obsolescence Management Plan EMU - PTA Review Rev.B | 20/04/2022 | 18/05/2022 | 11/03/2022 | nan | 64880 | TK_Active | 1208363553 | 251 | 1208363553_251
MRPP2-DE3.25160 | TT_Task | Certification Plan (EMU ; DMU) EMU - PTA Review and Approval | 19/04/2022 | 17/05/2022 | nan | nan | 64680 | TK_NotStart | 1208363553 | 252 | 1208363553_252
MRPP2-DE3.25150 | TT_Task | List of Signages and Livery EMU - PTA Review Rev.A | 02/06/2021 | 30/06/2021 | 02/06/2021 | 30/06/2021 | 0 | TK_Complete | 1208363553 | 253 | 1208363553_253
MRPP2-DE3.26710 | TT_Task | List of Signages and Livery EMU - Submission Rev.B | 01/07/2021 | 20/01/2022 | 01/07/2021 | nan | 0 | TK_Active | 1208363553 | 253 | 1208363553_253
MRPP2-DE3.26720 | TT_Task | List of Signages and Livery EMU - PTA Review Rev.B | 02/05/2022 | 27/05/2022 | nan | nan | 64616 | TK_NotStart | 1208363553 | 253 | 1208363553_253
MRPP2-DE3.25310 | TT_Task | Dangerous Substance Report EMU - PTA Review and Approval | 31/05/2022 | 28/06/2022 | nan | nan | 64448 | TK_NotStart | 1208363553 | 254 | 1208363553_254
MRPP2-DE3.25320 | TT_Task | Digital 3D - Model Specification EMU - PTA Review and Approval Rev.A | 18/09/2020 | 14/10/2020 | 18/09/2020 | 14/10/2020 | 0 | TK_Complete | 1208363553 | 255 | 1208363553_255
MRPP2-DE3.25340 | TT_Task | Digital 3D - Model V1 EMU - PTA Review and Approval | 31/05/2022 | 28/06/2022 | nan | nan | 64448 | TK_NotStart | 1208363553 | 255 | 1208363553_255
MRPP2-DE3.25330 | TT_Task | Digital 3D - Model V2 EMU - PTA Review and Approval | 31/05/2022 | 28/06/2022 | nan | nan | 64448 | TK_NotStart | 1208363553 | 255 | 1208363553_255
MRPP2-DE3.25260 | TT_Task | Bogie Frame validation applicability note EMU - PTA Review and Approval Rev.A | 24/09/2020 | 19/10/2020 | 24/09/2020 | 19/10/2020 | 0 | TK_Complete | 1208363553 | 256 | 1208363553_256
MRPP2-DE3.26750 | TT_Task | Bogie Frame validation applicability note EMU - Submission Rev.B | 20/10/2020 | 26/02/2021 | 20/10/2020 | 26/02/2021 | 0 | TK_Complete | 1208363553 | 256 | 1208363553_256
MRPP2-DE3.26760 | TT_Task | Bogie Frame validation applicability note EMU - PTA Review and Approval Rev.B | 01/03/2021 | 29/03/2021 | 27/02/2021 | 29/03/2021 | 0 | TK_Complete | 1208363553 | 256 | 1208363553_256
MRPP2-DE3.26780 | TT_Task | Dangerous Substance derogation report (EMU ; DMU) - PTA Review and Approval Rev.A | 15/10/2020 | 11/11/2020 | 15/10/2020 | 11/11/2020 | 0 | TK_Complete | 1208363553 | 254 | 1208363553_254
MRPP2-DE3.26790 | TT_Task | Dangerous Substance derogation report (EMU ; DMU) - Submission Rev.B | 12/11/2020 | 08/02/2021 | 12/11/2020 | 08/02/2021 | 0 | TK_Complete | 1208363553 | 254 | 1208363553_254
MRPP2-DE3.26800 | TT_Task | Dangerous Substance derogation report (EMU ; DMU) - PTA Review and Approval Rev.B | 09/02/2021 | 08/03/2021 | 09/02/2021 | 08/03/2021 | 0 | TK_Complete | 1208363553 | 254 | 1208363553_254
MRPP2-DE3.26820 | TT_Task | Lock Specification EMU - PTA Review and Approval Rev.A | 17/12/2020 | 02/02/2021 | 17/12/2020 | 02/02/2021 | 0 | TK_Complete | 1208363553 | 257 | 1208363553_257
MRPP2-DE3.26830 | TT_Task | Lock Specification EMU - Submission Rev.B | 03/02/2021 | 16/04/2021 | 03/02/2021 | 16/04/2021 | 0 | TK_Complete | 1208363553 | 257 | 1208363553_257
MRPP2-DE3.26840 | TT_Task | Lock Specification EMU - PTA Review and Approval Rev.B | 19/04/2021 | 17/05/2021 | 17/04/2021 | 17/05/2021 | 0 | TK_Complete | 1208363553 | 257 | 1208363553_257
MRPP2-DE3.25230 | TT_Task | Interior Lighting Performances EMU - PTA Review and Approval | 22/04/2022 | 20/05/2022 | nan | nan | 64656 | TK_NotStart | 1208363553 | 258 | 1208363553_258
MRPP2-DE3.25550 | TT_Task | Task Analysis EMU - PTA Review Rev.A | 14/10/2021 | 24/11/2021 | 14/10/2021 | 24/11/2021 | 0 | TK_Complete | 1208363553 | 259 | 1208363553_259
MRPP2-DE3.28650 | TT_Task | Task Analysis EMU - Submission Rev.B | 25/11/2021 | 17/02/2022 | 25/11/2021 | nan | 0 | TK_Active | 1208363553 | 259 | 1208363553_259
MRPP2-DE3.28660 | TT_Task | Task Analysis EMU - PTA Review Rev.B | 29/04/2022 | 26/05/2022 | nan | nan | 64624 | TK_NotStart | 1208363553 | 259 | 1208363553_259
MRPP2-DE3.25560 | TT_Task | Ergonomic Assessment of Maintenance EMU - PTA Review and Approval | 29/04/2022 | 26/05/2022 | nan | nan | 64624 | TK_NotStart | 1208363553 | 260 | 1208363553_260
MRPP2-DE3.25570 | TT_Task | Train to Ground Connectivity System Interfaces Description (EMU ; DMU) EMU - PTA Review Rev.A | 30/08/2021 | 10/12/2021 | 28/08/2021 | 17/01/2022 | 0 | TK_Complete | 1208363553 | 261 | 1208363553_261
MRPP2-DE3.29200 | TT_Task | Train to Ground Connectivity System Interfaces Description (EMU ; DMU) EMU - Submission Rev.B | 28/01/2022 | 10/02/2022 | 18/01/2022 | nan | 0 | TK_Active | 1208363553 | 261 | 1208363553_261
MRPP2-DE3.29210 | TT_Task | Train to Ground Connectivity System Interfaces Description (EMU ; DMU) EMU - PTA Review Rev.B | 14/04/2022 | 12/05/2022 | nan | nan | 64704 | TK_NotStart | 1208363553 | 261 | 1208363553_261
MRPP2-DE3.25580 | TT_Task | HVAC - Air Filter EMU - PTA Review Rev.A | 09/04/2021 | 07/05/2021 | 09/04/2021 | 07/05/2021 | 0 | TK_Complete | 1208363553 | 262 | 1208363553_262
MRPP2-DE3.26850 | TT_Task | HVAC - Air Filter EMU - Submission Rev.B | 10/05/2021 | 15/11/2021 | 08/05/2021 | 15/11/2021 | 0 | TK_Complete | 1208363553 | 262 | 1208363553_262
MRPP2-DE3.26860 | TT_Task | HVAC - Air Filter EMU - PTA Review ; Approval Rev.B | 16/11/2021 | 30/11/2021 | 16/11/2021 | 30/11/2021 | 0 | TK_Complete | 1208363553 | 262 | 1208363553_262
MRPP2-DE3.25650 | TT_Task | Tip-up Seat Description and General Assembly Drawing EMU - PTA Review Rev.A | 16/05/2022 | 13/06/2022 | 20/12/2021 | 01/03/2022 | 0 | TK_Complete | 1208363553 | 263 | 1208363553_263
MRPP2-DE3.29620 | TT_Task | Tip-up Seat Description and General Assembly Drawing EMU - Submission Rev.B | 16/05/2022 | 27/05/2022 | 02/03/2022 | nan | 0 | TK_Active | 1208363553 | 263 | 1208363553_263
MRPP2-DE3.29630 | TT_Task | Tip-up Seat Description and General Assembly Drawing EMU - PTA Review Rev.B | 26/04/2022 | 23/05/2022 | nan | nan | 64648 | TK_NotStart | 1208363553 | 263 | 1208363553_263
MRPP2-DE3.26880 | TT_Task | Detail design specification Wifi EMU - PTA Review Rev.A | 13/04/2021 | 11/05/2021 | 13/04/2021 | 11/05/2021 | 0 | TK_Complete | 1208363553 | 264 | 1208363553_264
MRPP2-DE3.26890 | TT_Task | Detail design specification Wifi EMU - Submission Rev.B | 12/05/2021 | 17/11/2021 | 12/05/2021 | 17/11/2021 | 0 | TK_Complete | 1208363553 | 264 | 1208363553_264
MRPP2-DE3.26900 | TT_Task | Detail design specification Wifi EMU - PTA Review ; Approval Rev.B | 18/11/2021 | 15/12/2021 | 18/11/2021 | nan | 64880 | TK_Active | 1208363553 | 264 | 1208363553_264
MRPP2-DE3.25640 | TT_Task | Final fire safety design report EMU - PTA Review and Approval | 16/05/2022 | 13/06/2022 | nan | nan | 64536 | TK_NotStart | 1208363553 | 205 | 1208363553_205
MRPP2-DE3.25630 | TT_Task | Human Factor Issues Register EMU - PTA Review and Approval Rev.A | 29/06/2021 | 28/07/2021 | 29/06/2021 | 28/07/2021 | 0 | TK_Complete | 1208363553 | 265 | 1208363553_265
MRPP2-DE3.27010 | TT_Task | Human Factor Issues Register EMU - Submission Rev.B | 29/07/2021 | 12/11/2021 | 29/07/2021 | 12/11/2021 | 0 | TK_Complete | 1208363553 | 266 | 1208363553_266
MRPP2-DE3.27020 | TT_Task | Human Factor Issues Register EMU - PTA Review and Approval Rev.B | 15/11/2021 | 10/12/2021 | 15/11/2021 | 21/02/2022 | 0 | TK_Complete | 1208363553 | 265 | 1208363553_265
MRPP2-DE3.29560 | TT_Task | Human Factor Issues Register EMU - Submission Rev.C | 29/07/2021 | 11/08/2021 | 22/02/2022 | nan | 0 | TK_Active | 1208363553 | 266 | 1208363553_266
MRPP2-DE3.29570 | TT_Task | Human Factor Issues Register EMU - PTA Review and Approval Rev.C | 06/05/2022 | 02/06/2022 | nan | nan | 64584 | TK_NotStart | 1208363553 | 265 | 1208363553_265
MRPP2-DE3.26920 | TT_Task | Finite Element Calculation Report - Bogie To Carbody Connection EMU - PTA Review Rev.A | 25/09/2020 | 21/10/2020 | 25/09/2020 | 21/10/2020 | 0 | TK_Complete | 1208363553 | 267 | 1208363553_267
MRPP2-DE3.26930 | TT_Task | Finite Element Calculation Report - Bogie To Carbody Connection EMU - Submission Rev.B | 22/10/2020 | 04/03/2021 | 22/10/2020 | 04/03/2021 | 0 | TK_Complete | 1208363553 | 267 | 1208363553_267
MRPP2-DE3.26940 | TT_Task | Finite Element Calculation Report - Bogie To Carbody Connection EMU - PTA Review ; Approval Rev.B | 05/03/2021 | 30/03/2021 | 05/03/2021 | 30/03/2021 | 0 | TK_Complete | 1208363553 | 267 | 1208363553_267
MRPP2-DE3.25480 | TT_Task | Traction System Combined Test Specification EMU - PTA Review and Approval Rev.A | 28/06/2021 | 27/07/2021 | 26/06/2021 | 27/07/2021 | 0 | TK_Complete | 1208363553 | 50 | 1208363553_50
MRPP2-DE3.26950 | TT_Task | Traction System Combined Test Specification EMU - Submission Rev.B | 28/07/2021 | 22/10/2021 | 28/07/2021 | 22/10/2021 | 0 | TK_Complete | 1208363553 | 99 | 1208363553_99
MRPP2-DE3.26960 | TT_Task | Traction System Combined Test Specification EMU - PTA Review and Approval Rev.B | 29/04/2022 | 26/05/2022 | nan | nan | 64624 | TK_NotStart | 1208363553 | 50 | 1208363553_50
MRPP2-DE3.28670 | TT_Task | Traction System Combined Test Specification EMU - Submission Rev.C | 25/10/2021 | 15/02/2022 | 25/10/2021 | nan | 0 | TK_Active | 1208363553 | 99 | 1208363553_99
MRPP2-DE3.28680 | TT_Task | Traction System Combined Test Specification EMU - PTA Review and Approval Rev.C | 25/10/2021 | 19/11/2021 | 25/10/2021 | 19/11/2021 | 0 | TK_Complete | 1208363553 | 50 | 1208363553_50
MRPP2-DE3.25500 | TT_Task | Electrical Design MOP for AS7530 EMU - PTA Review and Approval | 14/04/2022 | 12/05/2022 | nan | nan | 64704 | TK_NotStart | 1208363553 | 268 | 1208363553_268
MRPP2-DE3.25490 | TT_Task | Electrical Design MOP for EN50153 EMU - PTA Review and Approval | 13/04/2022 | 11/05/2022 | nan | nan | 64712 | TK_NotStart | 1208363553 | 268 | 1208363553_268
MRPP2-DE3.25420 | TT_Task | Interior Saloon FEA Reports EMU - PTA Review Rev.A | 28/01/2022 | 24/02/2022 | 23/12/2021 | 03/03/2022 | 0 | TK_Complete | 1208363553 | 269 | 1208363553_269
MRPP2-DE3.29700 | TT_Task | Interior Saloon FEA Reports EMU - Submission Rev.B | 04/04/2022 | 19/04/2022 | 04/03/2022 | nan | 0 | TK_Active | 1208363553 | 269 | 1208363553_269
MRPP2-DE3.29710 | TT_Task | Interior Saloon FEA Reports EMU - PTA Review Rev.B | 26/05/2022 | 23/06/2022 | nan | nan | 64472 | TK_NotStart | 1208363553 | 269 | 1208363553_269
MRPP2-DE3.25410 | TT_Task | Interior GA Drawing (EMU) EMU - PTA Review and Approval | 31/03/2022 | 02/05/2022 | 25/02/2022 | nan | 64880 | TK_Active | 1208363553 | 270 | 1208363553_270
MRPP2-DE3.25400 | TT_Task | Fitting GA Drawing (EMU) EMU - PTA Review Rev.A | 04/03/2022 | 31/03/2022 | 19/01/2022 | 22/03/2022 | 0 | TK_Complete | 1208363553 | 271 | 1208363553_271
MRPP2-DE3.29800 | TT_Task | Fitting GA Drawing (EMU) EMU - Submission Rev.B | 04/04/2022 | 19/04/2022 | 23/03/2022 | nan | 0 | TK_Active | 1208363553 | 271 | 1208363553_271
MRPP2-DE3.29810 | TT_Task | Fitting GA Drawing (EMU) EMU - PTA Review Rev.B | 23/05/2022 | 20/06/2022 | nan | nan | 64496 | TK_NotStart | 1208363553 | 271 | 1208363553_271
MRPP2-DE3.25700 | TT_Task | CAB GA Drawing EMU - PTA Review and Approval | 07/04/2022 | 09/05/2022 | 01/12/2021 | 23/02/2022 | 0 | TK_Complete | 1208363553 | 270 | 1208363553_270
MRPP2-DE3.25710 | TT_Task | Pneumatics GA Drawing EMU - PTA Review Rev.A | 04/03/2022 | 31/03/2022 | 01/02/2022 | 29/03/2022 | 0 | TK_Complete | 1208363553 | 272 | 1208363553_272
MRPP2-DE3.29900 | TT_Task | Pneumatics GA Drawing EMU - Submission Rev.B | 04/03/2022 | 31/03/2022 | 30/03/2022 | nan | 0 | TK_Active | 1208363553 | 272 | 1208363553_272
MRPP2-DE3.29910 | TT_Task | Pneumatics GA Drawing EMU - PTA Review Rev.B | 27/04/2022 | 24/05/2022 | nan | nan | 64640 | TK_NotStart | 1208363553 | 272 | 1208363553_272
MRPP2-DE3.25720 | TT_Task | Cabin Climate Comfort Prediction Report (EMU ; DMU) - PTA Review Rev.A | 04/08/2021 | 08/09/2021 | 04/08/2021 | 08/09/2021 | 0 | TK_Complete | 1208363553 | 273 | 1208363553_273
MRPP2-DE3.27590 | TT_Task | Cabin Climate Comfort Prediction Report (EMU ; DMU) - Submission Rev.B | 09/09/2021 | 16/11/2021 | 09/09/2021 | 16/11/2021 | 0 | TK_Complete | 1208363553 | 273 | 1208363553_273
MRPP2-DE3.27600 | TT_Task | Cabin Climate Comfort Prediction Report (EMU ; DMU) - PTA Review Rev.B | 17/11/2021 | 14/12/2021 | 17/11/2021 | 14/01/2022 | 0 | TK_Complete | 1208363553 | 273 | 1208363553_273
MRPP2-DE3.25390 | TT_Task | Aerodynamic effects ; Pressure calculation report (EMU ; DMU) - PTA Review Rev.A | 25/08/2021 | 24/09/2021 | 25/08/2021 | 24/09/2021 | 0 | TK_Complete | 1208363553 | 274 | 1208363553_274
MRPP2-DE3.27610 | TT_Task | Aerodynamic effects ; Pressure calculation report (EMU ; DMU) - Submission Rev.B | 28/09/2021 | 16/11/2021 | 28/09/2021 | 16/11/2021 | 0 | TK_Complete | 1208363553 | 274 | 1208363553_274
MRPP2-DE3.27620 | TT_Task | Aerodynamic effects ; Pressure calculation report (EMU ; DMU) - PTA Review Rev.B | 17/11/2021 | 14/12/2021 | 17/11/2021 | 18/01/2022 | 0 | TK_Complete | 1208363553 | 274 | 1208363553_274
MRPP2-DE3.27780 | TT_Task | Technical Specification for CAB Full Scale Mockup EMU - PTA Review and Approval | 21/05/2020 | 16/06/2020 | 21/05/2020 | 16/06/2020 | 0 | TK_Complete | 1208363553 | 275 | 1208363553_275
MRPP2-DE3.27800 | TT_Task | Technical Specification for Saloon Full Scale Mockup EMU - PTA Review and Approval | 21/05/2020 | 16/06/2020 | 21/05/2020 | 16/06/2020 | 0 | TK_Complete | 1208363553 | 276 | 1208363553_276
MRPP2-DE3.27820 | TT_Task | Train level test specification for Radio system EMU - PTA Review and Approval (Doc Propose to Delete) | 29/04/2022 | 26/05/2022 | nan | nan | 64624 | TK_NotStart | 1208363553 | 57 | 1208363553_57
MRPP2-DE3.27840 | TT_Task | Passenger Flow Evaluation EMU - PTA Review and Approval | 22/10/2020 | 17/11/2020 | 22/10/2020 | 17/11/2020 | 0 | TK_Complete | 1208363553 | 277 | 1208363553_277
MRPP2-DE3.27860 | TT_Task | Test Running Procedure EMU - PTA Review and Approval | 21/04/2022 | 19/05/2022 | nan | nan | 64664 | TK_NotStart | 1208363553 | 51 | 1208363553_51
MRPP2-DE3.27880 | TT_Task | Trial Journey Test Procedure EMU - PTA Review and Approval | 28/04/2022 | 25/05/2022 | nan | nan | 64632 | TK_NotStart | 1208363553 | 53 | 1208363553_53
MRPP2-DE3.27900 | TT_Task | Technical Specification and Drawings of Interior Lighting EMU - PTA Review Rev.A | 12/11/2021 | 10/12/2021 | 12/11/2021 | 20/12/2021 | 0 | TK_Complete | 1208363553 | 258 | 1208363553_258
MRPP2-DE3.29220 | TT_Task | Technical Specification and Drawings of Interior Lighting EMU - Submission Rev.B | 28/01/2022 | 10/02/2022 | 21/12/2021 | nan | 0 | TK_Active | 1208363553 | 258 | 1208363553_258
MRPP2-DE3.29230 | TT_Task | Technical Specification and Drawings of Interior Lighting EMU - PTA Review Rev.B | 21/04/2022 | 19/05/2022 | nan | nan | 64664 | TK_NotStart | 1208363553 | 258 | 1208363553_258
MRPP2-DE3.27920 | TT_Task | Safety Related Application Conditions (SRAC) to external interfaces EMU - PTA Review Rev.A | 10/03/2022 | 06/04/2022 | 25/01/2022 | 22/03/2022 | 0 | TK_Complete | 1208363553 | 278 | 1208363553_278
MRPP2-DE3.29820 | TT_Task | Safety Related Application Conditions (SRAC) to external interfaces EMU - Submission Rev.B | 04/04/2022 | 19/04/2022 | 23/03/2022 | nan | 0 | TK_Active | 1208363553 | 278 | 1208363553_278
MRPP2-DE3.29830 | TT_Task | Safety Related Application Conditions (SRAC) to external interfaces EMU - PTA Review Rev.B | 01/06/2022 | 29/06/2022 | nan | nan | 64440 | TK_NotStart | 1208363553 | 278 | 1208363553_278
MRPP2-DE3.27940 | TT_Task | Sanding Functional Type Test Procedure ? SAN EMU - PTA Review and Approval | 04/04/2022 | 04/05/2022 | 01/03/2022 | nan | 64880 | TK_Active | 1208363553 | 279 | 1208363553_279
MRPP2-DE3.27960 | TT_Task | Coupling Functional Type Test Procedure ? CPL EMU - PTA Review and Approval | 10/03/2022 | 06/04/2022 | 15/02/2022 | 17/03/2022 | 0 | TK_Complete | 1208363553 | 280 | 1208363553_280
MRPP2-DE3.27980 | TT_Task | Antenna Co-existence Study EMU - PTA Review Rev.A | 10/03/2022 | 06/04/2022 | 01/02/2022 | 03/03/2022 | 0 | TK_Complete | 1208363553 | 281 | 1208363553_281
MRPP2-DE3.29720 | TT_Task | Antenna Co-existence Study EMU - Submission Rev.B | 10/03/2022 | 23/03/2022 | 04/03/2022 | nan | 0 | TK_Active | 1208363553 | 281 | 1208363553_281
MRPP2-DE3.29730 | TT_Task | Antenna Co-existence Study EMU - PTA Review Rev.B | 06/05/2022 | 02/06/2022 | nan | nan | 64584 | TK_NotStart | 1208363553 | 281 | 1208363553_281
MRPP2-DE1.10283 | TT_Task | Mock-up Design - Technical Specification for CAB Rev.A EMU | 10/01/2020 | 27/03/2020 | 10/01/2020 | 27/03/2020 | 0 | TK_Complete | 1208363553 | 195 | 1208363553_195
MRPP2-DE1.10462 | TT_Task | Mock-up Design - Technical Specification for Saloon Rev.A EMU | 21/02/2020 | 27/03/2020 | 21/02/2020 | 27/03/2020 | 0 | TK_Complete | 1208363553 | 276 | 1208363553_276
MRPP2-DE1.13913 | TT_Task | Mock-up Design - Technical Specification for Saloon - PTA Design Review ; Approval Rev.B EMU | 21/05/2020 | 16/06/2020 | 21/05/2020 | 16/06/2020 | 0 | TK_Complete | 1208363553 | 276 | 1208363553_276
MRPP2-DE1.15323 | TT_Task | Mock-up Design - Technical Specification for CAB - PTA Design Review Rev.A EMU | 30/03/2020 | 17/04/2020 | 30/03/2020 | 17/04/2020 | 0 | TK_Complete | 1208363553 | 275 | 1208363553_275
MRPP2-DE1.15333 | TT_Task | Mock-up Design - Technical Specification for Saloon EMU - PTA Design Review Rev.A EMU | 30/03/2020 | 17/04/2020 | 30/03/2020 | 17/04/2020 | 0 | TK_Complete | 1208363553 | 276 | 1208363553_276
MRPP2-DE1.15343 | TT_Task | Mock-up Design - Technical Specification for CAB - Resubmit Rev.B to PTA for Review EMU | 20/04/2020 | 20/05/2020 | 20/04/2020 | 20/05/2020 | 0 | TK_Complete | 1208363553 | 275 | 1208363553_275
MRPP2-DE1.15353 | TT_Task | Mock-up Design - Technical Specification for Saloon EMU - Resubmit Rev.B to PTA for Review EMU | 20/04/2020 | 20/05/2020 | 20/04/2020 | 20/05/2020 | 0 | TK_Complete | 1208363553 | 276 | 1208363553_276
MRPP2-DE1.15363 | TT_Task | Mock-up Design - Technical Specification for CAB - PTA Design Review Rev.B EMU | 21/05/2020 | 16/06/2020 | 21/05/2020 | 16/06/2020 | 0 | TK_Complete | 1208363553 | 275 | 1208363553_275
MRPP2.SOU.33020 | TT_Task | EMU - TPS for Side Sill (CRF Parts) | 10/12/2019 | 04/05/2020 | 10/12/2019 | 04/05/2020 | 0 | TK_Complete | 1208363553 | 282 | 1208363553_282
MRPP2.SOU.33030 | TT_Task | EMU - TPS for Underframe Panels (CRF Parts) | 10/12/2019 | 04/05/2020 | 10/12/2019 | 04/05/2020 | 0 | TK_Complete | 1208363553 | 283 | 1208363553_283
MRPP2.SOU.33040 | TT_Task | EMU - TPS for Roof Corrugation (CRF Parts) | 10/12/2019 | 07/05/2020 | 10/12/2019 | 07/05/2020 | 0 | TK_Complete | 1208363553 | 284 | 1208363553_284
MRPP2.SOU.33050 | TT_Task | EMU - TPS for Cantrail with Integrated roof gutter (CRF Parts) | 10/12/2019 | 04/05/2020 | 10/12/2019 | 04/05/2020 | 0 | TK_Complete | 1208363553 | 285 | 1208363553_285
MRPP2.SOU.33090 | TT_Task | EMU - TPS for End Under Frame - EUF | 22/01/2020 | 26/05/2020 | 22/01/2020 | 26/05/2020 | 0 | TK_Complete | 1208363553 | 286 | 1208363553_286
MRPP2.SOU.33100 | TT_Task | EMU - TPS for Door Frame (CRF Section) | 22/01/2020 | 21/04/2020 | 22/01/2020 | 21/04/2020 | 0 | TK_Complete | 1208363553 | 287 | 1208363553_287
MRPP2.SOU.33110 | TT_Task | EMU - TPS for Carline | 22/01/2020 | 08/05/2020 | 22/01/2020 | 08/05/2020 | 0 | TK_Complete | 1208363553 | 288 | 1208363553_288
MRPP2.SOU.33130 | TT_Task | EMU - TPS for Casting - Equipment Support | 22/01/2020 | 05/06/2020 | 22/01/2020 | 05/06/2020 | 0 | TK_Complete | 1208363553 | 289 | 1208363553_289
MRPP2.SOU.33410 | TT_Task | EMU - TPS for Side Wall Cut ; bend parts ; Letter Board (in Small parts) | 19/02/2020 | 21/04/2020 | 19/02/2020 | 21/04/2020 | 0 | TK_Complete | 1208363553 | 290 | 1208363553_290
MRPP2.SOU.33460 | TT_Task | EMU - TPS for Windows | 01/04/2020 | 09/04/2020 | 01/04/2020 | 09/04/2020 | 0 | TK_Complete | 1208363553 | 291 | 1208363553_291
MRPP2.SOU.33060 | TT_Task | EMU - TPS for Bogie Frame | 29/01/2020 | 03/03/2020 | 29/01/2020 | 03/03/2020 | 0 | TK_Complete | 1208363553 | 292 | 1208363553_292
MRPP2.SOU.33200 | TT_Task | EMU - TPS for Wheels | 10/03/2020 | 30/03/2020 | 10/03/2020 | 30/03/2020 | 0 | TK_Complete | 1208363553 | 293 | 1208363553_293
MRPP2.SOU.33210 | TT_Task | EMU - TPS for Axles | 10/03/2020 | 30/03/2020 | 10/03/2020 | 30/03/2020 | 0 | TK_Complete | 1208363553 | 293 | 1208363553_293
MRPP2.SOU.33220 | TT_Task | EMU - TPS for Axle box ; bearing | 10/03/2020 | 30/03/2020 | 10/03/2020 | 30/03/2020 | 0 | TK_Complete | 1208363553 | 293 | 1208363553_293
MRPP2.SOU.33490 | TT_Task | EMU - TPS for Primary Suspension | 06/05/2020 | 26/06/2020 | 06/05/2020 | 26/06/2020 | 0 | TK_Complete | 1208363553 | 294 | 1208363553_294
MRPP2.SOU.33500 | TT_Task | EMU - TPS for Secondary Suspension | 01/04/2020 | 16/04/2020 | 01/04/2020 | 16/04/2020 | 0 | TK_Complete | 1208363553 | 294 | 1208363553_294
MRPP2.SOU.33170 | TT_Task | EMU - TPS for Pipes | 10/03/2020 | 07/08/2020 | 10/03/2020 | 07/08/2020 | 0 | TK_Complete | 1208363553 | 295 | 1208363553_295
MRPP2.SOU.33180 | TT_Task | EMU - TPS for Brakes | 10/03/2020 | 03/04/2020 | 10/03/2020 | 03/04/2020 | 0 | TK_Complete | 1208363553 | 296 | 1208363553_296
MRPP2.SOU.33140 | TT_Task | EMU - TPS for Wind screen | 19/02/2020 | 24/04/2020 | 19/02/2020 | 27/04/2020 | 0 | TK_Complete | 1208363553 | 297 | 1208363553_297
MRPP2.SOU.33150 | TT_Task | EMU - TPS for Vinyl | 19/02/2020 | 24/04/2020 | 19/02/2020 | 27/04/2020 | 0 | TK_Complete | 1208363553 | 298 | 1208363553_298
MRPP2.SOU.33160 | TT_Task | EMU - TPS for Floor Covering | 19/02/2020 | 24/04/2020 | 19/02/2020 | 27/04/2020 | 0 | TK_Complete | 1208363553 | 299 | 1208363553_299
MRPP2.SOU.33230 | TT_Task | EMU - TPS for Cab garnishing | 03/03/2020 | 07/10/2020 | 03/03/2020 | 07/10/2020 | 0 | TK_Complete | 1208363553 | 300 | 1208363553_300
MRPP2.SOU.33240 | TT_Task | EMU - TPS for Grabpoles and grab handles | 03/03/2020 | 07/10/2020 | 03/03/2020 | 07/10/2020 | 0 | TK_Complete | 1208363553 | 301 | 1208363553_301
MRPP2.SOU.33250 | TT_Task | EMU - TPS for Hand rails | 03/03/2020 | 07/10/2020 | 03/03/2020 | 07/10/2020 | 0 | TK_Complete | 1208363553 | 302 | 1208363553_302
MRPP2.SOU.33260 | TT_Task | EMU - TPS for Interior ceiling, LED, Duct including lighting | 03/03/2020 | 30/09/2020 | 03/03/2020 | 30/09/2020 | 0 | TK_Complete | 1208363553 | 303 | 1208363553_303
MRPP2.SOU.33280 | TT_Task | EMU - TPS for Seats (Longitudinal) | 03/03/2020 | 08/04/2020 | 03/03/2020 | 08/04/2020 | 0 | TK_Complete | 1208363553 | 304 | 1208363553_304
MRPP2.SOU.33070 | TT_Task | EMU - TPS for Crash box | 06/03/2020 | 07/08/2020 | 06/03/2020 | 07/08/2020 | 0 | TK_Complete | 1208363553 | 305 | 1208363553_305
MRPP2.SOU.33390 | TT_Task | EMU - TPS for TCMS Equipment | 31/03/2020 | 22/05/2020 | 31/03/2020 | 22/05/2020 | 0 | TK_Complete | 1208363553 | 291 | 1208363553_291
MRPP2.SOU.33450 | TT_Task | EMU - TPS for Master Controller - MCP | 06/04/2020 | 20/04/2020 | 05/04/2020 | 20/04/2020 | 0 | TK_Complete | 1208363553 | 291 | 1208363553_291
MRPP2.SOU.33270 | TT_Task | EMU - TPS for Traction converter | 31/01/2020 | 14/04/2020 | 31/01/2020 | 14/04/2020 | 0 | TK_Complete | 1208363553 | 293 | 1208363553_293
MRPP2.SOU.33290 | TT_Task | EMU - TPS for Auxiliary converter - CVS | 07/02/2020 | 27/02/2020 | 07/02/2020 | 27/02/2020 | 0 | TK_Complete | 1208363553 | 185 | 1208363553_185
MRPP2.SOU.33350 | TT_Task | EMU - TPS for LV box | 14/02/2020 | 07/08/2020 | 14/02/2020 | 07/08/2020 | 0 | TK_Complete | 1208363553 | 306 | 1208363553_306
MRPP2.SOU.33380 | TT_Task | EMU - TPS for Traction motor | 14/02/2020 | 30/03/2020 | 14/02/2020 | 30/03/2020 | 0 | TK_Complete | 1208363553 | 293 | 1208363553_293
MRPP2.SOU.33430 | TT_Task | EMU - TPS for Gangway | 24/03/2020 | 09/04/2020 | 24/03/2020 | 09/04/2020 | 0 | TK_Complete | 1208363553 | 307 | 1208363553_307
MRPP2.SOU.33420 | TT_Task | EMU - TPS for Coupler | 10/03/2020 | 15/04/2020 | 10/03/2020 | 15/04/2020 | 0 | TK_Complete | 1208363553 | 308 | 1208363553_308
MRPP2.SOU.33310 | TT_Task | EMU - TPS for HVAC | 07/02/2020 | 27/02/2020 | 07/02/2020 | 27/02/2020 | 0 | TK_Complete | 1208363553 | 309 | 1208363553_309
MRPP2.SOU.33000 | TT_Task | EMU - TPS for Passenger Doors | 29/01/2020 | 09/04/2020 | 29/01/2020 | 10/04/2020 | 0 | TK_Complete | 1208363553 | 310 | 1208363553_310
MRPP2.SOU.33300 | TT_Task | EMU - TPS for Elec comp | 11/02/2020 | 07/08/2020 | 11/02/2020 | 07/08/2020 | 0 | TK_Complete | 1208363553 | 311 | 1208363553_311
MRPP2.SOU.33320 | TT_Task | EMU - TPS for Relays | 14/02/2020 | 07/08/2020 | 14/02/2020 | 07/08/2020 | 0 | TK_Complete | 1208363553 | 312 | 1208363553_312
MRPP2.SOU.33330 | TT_Task | EMU - TPS for Cable trays | 14/02/2020 | 07/08/2020 | 14/02/2020 | 07/08/2020 | 0 | TK_Complete | 1208363553 | 313 | 1208363553_313
MRPP2.SOU.33340 | TT_Task | EMU - TPS for Battery ; battery box | 14/02/2020 | 02/04/2020 | 14/02/2020 | 02/04/2020 | 0 | TK_Complete | 1208363553 | 314 | 1208363553_314
MRPP2.SOU.33360 | TT_Task | EMU - TPS for Cabinets | 14/02/2020 | 07/08/2020 | 14/02/2020 | 07/08/2020 | 0 | TK_Complete | 1208363553 | 315 | 1208363553_315
MRPP2.SOU.33400 | TT_Task | EMU - TPS for Cables | 10/02/2020 | 15/06/2020 | 10/02/2020 | 15/06/2020 | 0 | TK_Complete | 1208363553 | 313 | 1208363553_313
MRPP2.SOU.33370 | TT_Task | EMU - TPS for PACIS | 31/03/2020 | 08/04/2020 | 31/03/2020 | 08/04/2020 | 0 | TK_Complete | 1208363553 | 316 | 1208363553_316
MRPP2.SOU.33480 | TT_Task | EMU - TPS for Pantograph | 25/03/2020 | 03/04/2020 | 25/03/2020 | 03/04/2020 | 0 | TK_Complete | 1208363553 | 317 | 1208363553_317
MRPP2.SOU.33010 | TT_Task | EMU - TPS for Driver Cab | 10/12/2019 | 05/06/2020 | 10/12/2019 | 05/06/2020 | 0 | TK_Complete | 1208363553 | 318 | 1208363553_318
MRPP2.SOU.33470 | TT_Task | EMU - TPS for Front mask | 01/04/2020 | 30/09/2020 | 01/04/2020 | 30/09/2020 | 0 | TK_Complete | 1208363553 | 319 | 1208363553_319
MRPP2-SOU.10640 | TT_Task | EMU - RFQ Steel Casting - Equipment Support | 22/01/2020 | 19/06/2020 | 22/01/2020 | 19/06/2020 | 0 | TK_Complete | 1208363553 | 289 | 1208363553_289
MRPP2-SOU.11210 | TT_Task | EMU - BA Steel Casting - Equipment Support | 22/06/2020 | 18/12/2020 | 22/06/2020 | 18/12/2020 | 0 | TK_Complete | 1208363553 | 289 | 1208363553_289
MRPP2-SUP.10100 | TT_Task | EMU - PO Steel Casting - Equipment Support - 1st Fleet (5 trainsets) | 21/12/2020 | 15/01/2021 | 21/12/2020 | 15/01/2021 | 0 | TK_Complete | 1208363553 | 320 | 1208363553_320
MRPP2-SUP.14270 | TT_Task | EMU - Production Steel Casting - Equipment Support - 1st Fleet (5 trainsets) | 18/01/2021 | 09/08/2021 | 18/01/2021 | 09/08/2021 | 0 | TK_Complete | 1208363553 | 320 | 1208363553_320
MRPP2-SUP.18330 | TT_Task | EMU - FAI Steel Casting - Equipment Support | 10/08/2021 | 23/08/2021 | 10/08/2021 | 23/08/2021 | 0 | TK_Complete | 1208363553 | 289 | 1208363553_289
MRPP2-SUP.18880 | TT_Task | EMU - DEL Steel Casting - Equipment Support delivery - 1st Fleet (5 trainsets) | 10/08/2021 | 29/12/2021 | 10/08/2021 | 29/12/2021 | 0 | TK_Complete | 1208363553 | 320 | 1208363553_320
MRPP2-SOU.11150 | TT_Task | EMU - RFQ Driver Cab | 31/12/2019 | 22/06/2020 | 31/12/2019 | 22/06/2020 | 0 | TK_Complete | 1208363553 | 318 | 1208363553_318
MRPP2-SOU.11155 | TT_Task | EMU - BA Driver Cab | 23/06/2020 | 15/09/2020 | 23/06/2020 | 15/09/2020 | 0 | TK_Complete | 1208363553 | 318 | 1208363553_318
MRPP2-SUP.10010 | TT_Task | EMU - PO Driver Cab - 1st Fleet (5 trainsets) | 16/09/2020 | 01/10/2020 | 16/09/2020 | 01/10/2020 | 0 | TK_Complete | 1208363553 | 321 | 1208363553_321
MRPP2-SUP.14160 | TT_Task | EMU - Production Driver Cab - 1st Fleet (5 trainsets) | 02/10/2020 | 09/08/2021 | 02/10/2020 | 09/08/2021 | 0 | TK_Complete | 1208363553 | 321 | 1208363553_321
MRPP2-SUP.18370 | TT_Task | EMU - FAI Driver Cab | 10/08/2021 | 23/08/2021 | 10/08/2021 | 23/08/2021 | 0 | TK_Complete | 1208363553 | 318 | 1208363553_318
MRPP2-SUP.19010 | TT_Task | EMU - DEL Driver Cab RM delivery - 1st Fleet (5 trainsets) | 24/08/2021 | 12/01/2022 | 24/08/2021 | 12/01/2022 | 0 | TK_Complete | 1208363553 | 321 | 1208363553_321
MRPP2-SOU.10590 | TT_Task | EMU - RFQ Side Sill (CRF Parts) | 31/12/2019 | 22/05/2020 | 31/12/2019 | 22/05/2020 | 0 | TK_Complete | 1208363553 | 282 | 1208363553_282
MRPP2-SOU.11160 | TT_Task | EMU - BA Side Sill (CRF Parts) | 25/05/2020 | 30/06/2020 | 25/05/2020 | 30/06/2020 | 0 | TK_Complete | 1208363553 | 282 | 1208363553_282
MRPP2-SUP.10020 | TT_Task | EMU - PO Side Sill (CRF Parts) - 1st Fleet (5 trainsets) | 01/07/2020 | 19/10/2020 | 01/07/2020 | 19/10/2020 | 0 | TK_Complete | 1208363553 | 322 | 1208363553_322
MRPP2-SUP.14170 | TT_Task | EMU - Production Side Sill (CRF Parts) - 1st Fleet (5 trainsets) | 20/10/2020 | 04/01/2021 | 20/10/2020 | 04/01/2021 | 0 | TK_Complete | 1208363553 | 322 | 1208363553_322
MRPP2-SUP.18380 | TT_Task | EMU - FAI Side Sill (CRF Parts) | 08/12/2020 | 20/01/2021 | 08/12/2020 | 20/01/2021 | 0 | TK_Complete | 1208363553 | 282 | 1208363553_282
MRPP2-SUP.19020 | TT_Task | EMU - DEL Side Sill (CRF Parts) RM delivery - 1st Fleet (5 trainsets) | 19/11/2020 | 15/04/2021 | 19/11/2020 | 15/04/2021 | 0 | TK_Complete | 1208363553 | 322 | 1208363553_322
MRPP2-SOU.10600 | TT_Task | EMU - RFQ Underframe Panels (CRF Parts) | 31/12/2019 | 22/05/2020 | 31/12/2019 | 22/05/2020 | 0 | TK_Complete | 1208363553 | 283 | 1208363553_283
MRPP2-SOU.11170 | TT_Task | EMU - BA Underframe Panels (CRF Parts) | 25/05/2020 | 16/09/2020 | 25/05/2020 | 16/09/2020 | 0 | TK_Complete | 1208363553 | 283 | 1208363553_283
MRPP2-SUP.10030 | TT_Task | EMU - PO Underframe Panels (CRF Parts) - 1st Fleet (5 trainsets) | 17/09/2020 | 16/10/2020 | 17/09/2020 | 16/10/2020 | 0 | TK_Complete | 1208363553 | 323 | 1208363553_323
MRPP2-SUP.14180 | TT_Task | EMU - Production Underframe Panels (CRF Parts) - 1st Fleet (5 trainsets) | 19/10/2020 | 04/01/2021 | 19/10/2020 | 04/01/2021 | 0 | TK_Complete | 1208363553 | 323 | 1208363553_323
MRPP2-SUP.18390 | TT_Task | EMU - FAI Underframe Panels (CRF Parts) | 05/11/2020 | 05/02/2021 | 05/11/2020 | 05/02/2021 | 0 | TK_Complete | 1208363553 | 283 | 1208363553_283
MRPP2-SUP.19030 | TT_Task | EMU - DEL Underframe Panels (CRF Parts) delivery - 1st Fleet (5 trainsets) | 19/11/2020 | 15/04/2021 | 19/11/2020 | 15/04/2021 | 0 | TK_Complete | 1208363553 | 323 | 1208363553_323
MRPP2-SOU.10610 | TT_Task | EMU - RFQ Roof Corrugation (CRF Parts) | 31/12/2019 | 22/05/2020 | 31/12/2019 | 22/05/2020 | 0 | TK_Complete | 1208363553 | 284 | 1208363553_284
MRPP2-SOU.11180 | TT_Task | EMU - BA Roof Corrugation (CRF Parts) | 25/05/2020 | 16/09/2020 | 25/05/2020 | 16/09/2020 | 0 | TK_Complete | 1208363553 | 284 | 1208363553_284
MRPP2-SUP.10040 | TT_Task | EMU - PO Roof Corrugation (CRF Parts) - 1st Fleet (5 trainsets) | 17/09/2020 | 16/10/2020 | 17/09/2020 | 16/10/2020 | 0 | TK_Complete | 1208363553 | 324 | 1208363553_324
MRPP2-SUP.14190 | TT_Task | EMU - Production Roof Corrugation (CRF Parts) - 1st Fleet (5 trainsets) | 19/10/2020 | 04/01/2021 | 19/10/2020 | 04/01/2021 | 0 | TK_Complete | 1208363553 | 324 | 1208363553_324
MRPP2-SUP.18400 | TT_Task | EMU - FAI Roof Corrugation (CRF Parts) | 08/12/2020 | 08/01/2021 | 08/12/2020 | 08/01/2021 | 0 | TK_Complete | 1208363553 | 284 | 1208363553_284
MRPP2-SUP.19040 | TT_Task | EMU - DEL Roof Corrugation (CRF Parts) delivery - 1st Fleet (5 trainsets) | 19/11/2020 | 15/04/2021 | 19/11/2020 | 15/04/2021 | 0 | TK_Complete | 1208363553 | 324 | 1208363553_324
MRPP2-SOU.10620 | TT_Task | EMU - RFQ Cantrail with Integrated roof gutter (CRF Parts) | 31/12/2019 | 22/05/2020 | 31/12/2019 | 22/05/2020 | 0 | TK_Complete | 1208363553 | 285 | 1208363553_285
MRPP2-SOU.11190 | TT_Task | EMU - BA Cantrail with Integrated roof gutter (CRF Parts) | 25/05/2020 | 04/06/2020 | 25/05/2020 | 04/06/2020 | 0 | TK_Complete | 1208363553 | 285 | 1208363553_285
MRPP2-SUP.10050 | TT_Task | EMU - PO Cantrail with Integrated roof gutter (CRF Parts) - 1st Fleet (5 trainsets) | 05/06/2020 | 07/07/2020 | 05/06/2020 | 07/07/2020 | 0 | TK_Complete | 1208363553 | 325 | 1208363553_325
MRPP2-SUP.14200 | TT_Task | EMU - Production Cantrail with Integrated roof gutter (CRF Parts) - 1st Fleet (5 trainsets) | 08/07/2020 | 04/01/2021 | 08/07/2020 | 04/01/2021 | 0 | TK_Complete | 1208363553 | 325 | 1208363553_325
MRPP2-SUP.18410 | TT_Task | EMU - FAI Cantrail with Integrated roof gutter (CRF Parts) | 17/11/2020 | 30/11/2020 | 17/11/2020 | 30/11/2020 | 0 | TK_Complete | 1208363553 | 285 | 1208363553_285
MRPP2-SUP.19050 | TT_Task | EMU - DEL Cantrail with Integrated roof gutter (CRF Parts) delivery - 1st Fleet (5 trainsets) | 01/12/2020 | 28/04/2021 | 01/12/2020 | 28/04/2021 | 0 | TK_Complete | 1208363553 | 325 | 1208363553_325
MRPP2-SOU.10710 | TT_Task | EMU - RFQ EUF | 27/05/2020 | 24/07/2020 | 27/05/2020 | 24/07/2020 | 0 | TK_Complete | 1208363553 | 286 | 1208363553_286
MRPP2-SOU.11340 | TT_Task | EMU - BA EUF | 27/07/2020 | 11/09/2020 | 27/07/2020 | 11/09/2020 | 0 | TK_Complete | 1208363553 | 286 | 1208363553_286
MRPP2-SUP.10120 | TT_Task | EMU - PO EUF - 1st Fleet (5 trainsets) | 14/09/2020 | 02/10/2020 | 14/09/2020 | 02/10/2020 | 0 | TK_Complete | 1208363553 | 326 | 1208363553_326
MRPP2-SUP.14250 | TT_Task | EMU - Production EUF - 1st Fleet (5 trainsets) | 05/10/2020 | 08/02/2021 | 05/10/2020 | 08/02/2021 | 0 | TK_Complete | 1208363553 | 327 | 1208363553_327
MRPP2-SUP.18350 | TT_Task | EMU - FAI EUF | 16/12/2020 | 02/02/2021 | 16/12/2020 | 02/02/2021 | 0 | TK_Complete | 1208363553 | 328 | 1208363553_328
MRPP2-SUP.18960 | TT_Task | EMU - DEL EUF delivery - 1st Fleet (5 trainsets) | 11/01/2021 | 08/04/2021 | 11/01/2021 | 08/04/2021 | 0 | TK_Complete | 1208363553 | 329 | 1208363553_329
MRPP2-SOU.10660 | TT_Task | EMU - RFQ Carline | 22/01/2020 | 05/06/2020 | 22/01/2020 | 05/06/2020 | 0 | TK_Complete | 1208363553 | 288 | 1208363553_288
MRPP2-SOU.11230 | TT_Task | EMU - BA Carline | 08/06/2020 | 04/09/2020 | 06/06/2020 | 04/09/2020 | 0 | TK_Complete | 1208363553 | 288 | 1208363553_288
MRPP2-SUP.10060 | TT_Task | EMU - PO Carline - 1st Fleet (5 trainsets) | 07/09/2020 | 30/10/2020 | 07/09/2020 | 30/10/2020 | 0 | TK_Complete | 1208363553 | 330 | 1208363553_330
MRPP2-SUP.14210 | TT_Task | EMU - Production Carline - 1st Fleet (5 trainsets) | 02/11/2020 | 05/02/2021 | 02/11/2020 | 05/02/2021 | 0 | TK_Complete | 1208363553 | 331 | 1208363553_331
MRPP2-SUP.18300 | TT_Task | EMU - FAI Carline | 14/12/2020 | 06/01/2021 | 14/12/2020 | 06/01/2021 | 0 | TK_Complete | 1208363553 | 328 | 1208363553_328
MRPP2-SUP.18890 | TT_Task | EMU - DEL Carline delivery - 1st Fleet (5 trainsets) | 07/01/2021 | 06/05/2021 | 07/01/2021 | 06/05/2021 | 0 | TK_Complete | 1208363553 | 331 | 1208363553_331
MRPP2-SOU.10670 | TT_Task | EMU - RFQ Door Frame (CRF section) | 22/01/2020 | 05/06/2020 | 22/01/2020 | 05/06/2020 | 0 | TK_Complete | 1208363553 | 287 | 1208363553_287
MRPP2-SOU.11240 | TT_Task | EMU - BA Door Frame (CRF section) | 08/06/2020 | 13/07/2020 | 06/06/2020 | 13/07/2020 | 0 | TK_Complete | 1208363553 | 287 | 1208363553_287
MRPP2-SUP.10070 | TT_Task | EMU - PO Door Frame (CRF section) - 1st Fleet (5 trainsets) | 14/07/2020 | 24/07/2020 | 14/07/2020 | 24/07/2020 | 0 | TK_Complete | 1208363553 | 332 | 1208363553_332
MRPP2-SUP.14220 | TT_Task | EMU - Production Door Frame (CRF section) - 1st Fleet (5 trainsets) | 27/07/2020 | 29/01/2021 | 27/07/2020 | 29/01/2021 | 0 | TK_Complete | 1208363553 | 332 | 1208363553_332
MRPP2-SUP.18310 | TT_Task | EMU - FAI Door Frame (CRF section) | 10/12/2020 | 29/01/2021 | 10/12/2020 | 29/01/2021 | 0 | TK_Complete | 1208363553 | 287 | 1208363553_287
MRPP2-SUP.18900 | TT_Task | EMU - DEL Door Frame (CRF section) delivery - 1st Fleet (5 trainsets) | 05/01/2021 | 28/05/2021 | 05/01/2021 | 28/05/2021 | 0 | TK_Complete | 1208363553 | 332 | 1208363553_332
MRPP2-SOU.10700 | TT_Task | EMU - RFQ Sidewall (Cut ; Bend Parts) | 22/04/2020 | 08/06/2020 | 22/04/2020 | 08/06/2020 | 0 | TK_Complete | 1208363553 | 290 | 1208363553_290
MRPP2-SOU.11330 | TT_Task | EMU - BA Sidewall (Cut ; Bend Parts) | 09/06/2020 | 13/07/2020 | 09/06/2020 | 13/07/2020 | 0 | TK_Complete | 1208363553 | 290 | 1208363553_290
MRPP2-SUP.10280 | TT_Task | EMU - PO Sidewall (Cut ; Bend Parts) - 1st Fleet (5 trainsets) | 14/07/2020 | 24/07/2020 | 14/07/2020 | 24/07/2020 | 0 | TK_Complete | 1208363553 | 333 | 1208363553_333
MRPP2-SUP.14460 | TT_Task | EMU - Production Sidewall (Cut ; Bend Parts) - 1st Fleet (5 trainsets) | 27/07/2020 | 01/02/2021 | 27/07/2020 | 01/02/2021 | 0 | TK_Complete | 1208363553 | 333 | 1208363553_333
MRPP2-SUP.18290 | TT_Task | EMU - FAI Sidewall (Cut ; Bend Parts) | 30/11/2020 | 18/12/2020 | 30/11/2020 | 18/12/2020 | 0 | TK_Complete | 1208363553 | 290 | 1208363553_290
MRPP2-SUP.18860 | TT_Task | EMU - DEL Sidewall (Cut ; Bend Parts) delivery - 1st Fleet (5 trainsets) | 21/12/2020 | 18/05/2021 | 21/12/2020 | 18/05/2021 | 0 | TK_Complete | 1208363553 | 333 | 1208363553_333
MRPP2-SUP.11280 | TT_Task | EMU - PO Stainless Steel (C;B, CRF) - 2nd Fleet (6 trainsets) | 28/01/2022 | 24/03/2022 | 06/12/2021 | 01/02/2022 | 0 | TK_Complete | 1208363553 | 334 | 1208363553_334
MRPP2-SUP.15410 | TT_Task | EMU - Production Stainless Steel (C;B, CRF) - 2nd Fleet (6 trainsets) | 09/03/2022 | 16/02/2023 | 02/02/2022 | nan | 0 | TK_Active | 1208363553 | 334 | 1208363553_334
MRPP2-SUP.21000 | TT_Task | EMU - DEL Stainless Steel (C;B, CRF) delivery - 2nd Fleet (6 trainsets) | 02/11/2022 | 27/04/2023 | nan | nan | 0 | TK_NotStart | 1208363553 | 334 | 1208363553_334
MRPP2-SUP.11340 | TT_Task | EMU - PO Carbon Steel RM - 2nd Fleet (6 trainsets) | 04/03/2022 | 31/03/2022 | 02/02/2022 | 01/03/2022 | 0 | TK_Complete | 1208363553 | 335 | 1208363553_335
MRPP2-SUP.15470 | TT_Task | EMU - Production Carbon Steel RM - 2nd Fleet (6 trainsets) | 01/04/2022 | 15/03/2023 | 02/03/2022 | nan | 0 | TK_Active | 1208363553 | 335 | 1208363553_335
MRPP2-SUP.21010 | TT_Task | EMU - DEL Carbon Steel RM delivery - 2nd Fleet (6 trainsets) | 30/11/2022 | 25/05/2023 | nan | nan | 0 | TK_NotStart | 1208363553 | 335 | 1208363553_335
MRPP2-SUP.11350 | TT_Task | EMU - PO Steel Casting - Equipment Support - 2nd Fleet (6 trainsets) | 04/03/2022 | 31/03/2022 | 02/02/2022 | 01/03/2022 | 0 | TK_Complete | 1208363553 | 320 | 1208363553_320
MRPP2-SUP.15480 | TT_Task | EMU - Production Steel Casting - Equipment Support - 2nd Fleet (6 trainsets) | 01/04/2022 | 15/03/2023 | 02/03/2022 | nan | 0 | TK_Active | 1208363553 | 320 | 1208363553_320
MRPP2-SUP.21020 | TT_Task | EMU - DEL Steel Casting - Equipment Support delivery - 2nd Fleet (6 trainsets) | 30/11/2022 | 25/05/2023 | nan | nan | 0 | TK_NotStart | 1208363553 | 320 | 1208363553_320
MRPP2-SUP.11360 | TT_Task | EMU - PO Driver Cab - 2nd Fleet (6 trainsets) | 04/03/2022 | 31/03/2022 | 02/02/2022 | 01/03/2022 | 0 | TK_Complete | 1208363553 | 321 | 1208363553_321
MRPP2-SUP.15490 | TT_Task | EMU - Production Driver Cab - 2nd Fleet (6 trainsets) | 01/04/2022 | 15/03/2023 | 02/03/2022 | nan | 0 | TK_Active | 1208363553 | 321 | 1208363553_321
MRPP2-SUP.21370 | TT_Task | EMU - DEL Driver Cab delivery - 2nd Fleet (6 trainsets) | 14/12/2022 | 09/06/2023 | nan | nan | 0 | TK_NotStart | 1208363553 | 321 | 1208363553_321
MRPP2-SUP.11370 | TT_Task | EMU - PO Side Sill (CRF Parts) - 2nd Fleet (6 trainsets) | 04/03/2022 | 31/03/2022 | 02/02/2022 | 01/03/2022 | 0 | TK_Complete | 1208363553 | 322 | 1208363553_322
MRPP2-SUP.15500 | TT_Task | EMU - Production Side Sill (CRF Parts) - 2nd Fleet (6 trainsets) | 01/04/2022 | 15/03/2023 | 02/03/2022 | nan | 0 | TK_Active | 1208363553 | 322 | 1208363553_322
MRPP2-SUP.21380 | TT_Task | EMU - DEL Side Sill (CRF Parts) delivery - 2nd Fleet (6 trainsets) | 14/12/2022 | 09/06/2023 | nan | nan | 0 | TK_NotStart | 1208363553 | 322 | 1208363553_322
MRPP2-SUP.11380 | TT_Task | EMU - PO Underframe Panels (CRF Parts) - 2nd Fleet (6 trainsets) | 04/03/2022 | 31/03/2022 | 02/02/2022 | 01/03/2022 | 0 | TK_Complete | 1208363553 | 323 | 1208363553_323
MRPP2-SUP.15510 | TT_Task | EMU - Production Underframe Panels (CRF Parts) - 2nd Fleet (6 trainsets) | 01/04/2022 | 15/03/2023 | 02/03/2022 | nan | 0 | TK_Active | 1208363553 | 323 | 1208363553_323
MRPP2-SUP.21390 | TT_Task | EMU - DEL Underframe Panels (CRF Parts) delivery - 2nd Fleet (6 trainsets) | 14/12/2022 | 09/06/2023 | nan | nan | 0 | TK_NotStart | 1208363553 | 323 | 1208363553_323
MRPP2-SUP.11390 | TT_Task | EMU - PO Roof Corrugation (CRF Parts) - 2nd Fleet (6 trainsets) | 04/03/2022 | 31/03/2022 | 02/02/2022 | 01/03/2022 | 0 | TK_Complete | 1208363553 | 324 | 1208363553_324
MRPP2-SUP.15520 | TT_Task | EMU - Production Roof Corrugation (CRF Parts) - 2nd Fleet (6 trainsets) | 01/04/2022 | 15/03/2023 | 02/03/2022 | nan | 0 | TK_Active | 1208363553 | 324 | 1208363553_324
MRPP2-SUP.21400 | TT_Task | EMU - DEL Roof Corrugation (CRF Parts) delivery - 2nd Fleet (6 trainsets) | 14/12/2022 | 09/06/2023 | nan | nan | 0 | TK_NotStart | 1208363553 | 324 | 1208363553_324
MRPP2-SUP.11400 | TT_Task | EMU - PO Cantrail with Integrated roof gutter (CRF Parts) - 2nd Fleet (6 trainsets) | 04/03/2022 | 31/03/2022 | 02/02/2022 | 01/03/2022 | 0 | TK_Complete | 1208363553 | 325 | 1208363553_325
MRPP2-SUP.15530 | TT_Task | EMU - Production Cantrail with Integrated roof gutter (CRF Parts) - 2nd Fleet (6 trainsets) | 01/04/2022 | 15/03/2023 | 02/03/2022 | nan | 0 | TK_Active | 1208363553 | 325 | 1208363553_325
MRPP2-SUP.21410 | TT_Task | EMU - DEL Cantrail with Integrated roof gutter (CRF Parts) delivery - 2nd Fleet (6 trainsets) | 14/12/2022 | 09/06/2023 | nan | nan | 0 | TK_NotStart | 1208363553 | 325 | 1208363553_325
MRPP2-SUP.11330 | TT_Task | EMU - PO EUF - 2nd Fleet (6 trainsets) | 04/03/2022 | 31/03/2022 | 02/02/2022 | 01/03/2022 | 0 | TK_Complete | 1208363553 | 326 | 1208363553_326
MRPP2-SUP.15460 | TT_Task | EMU - Production EUF - 2nd Fleet (6 trainsets) | 01/04/2022 | 15/02/2023 | 02/03/2022 | nan | 0 | TK_Active | 1208363553 | 327 | 1208363553_327
MRPP2-SUP.21120 | TT_Task | EMU - DEL EUF delivery - 2nd Fleet (6 trainsets) | 05/10/2022 | 27/03/2023 | nan | nan | 0 | TK_NotStart | 1208363553 | 329 | 1208363553_329
MRPP2-SUP.11410 | TT_Task | EMU - PO Carline - 2nd Fleet (6 trainsets) | 04/03/2022 | 31/03/2022 | 02/02/2022 | 01/03/2022 | 0 | TK_Complete | 1208363553 | 330 | 1208363553_330
MRPP2-SUP.15540 | TT_Task | EMU - Production Carline - 2nd Fleet (6 trainsets) | 01/04/2022 | 15/02/2023 | 02/03/2022 | nan | 0 | TK_Active | 1208363553 | 331 | 1208363553_331
MRPP2-SUP.21130 | TT_Task | EMU - DEL Carline delivery - 2nd Fleet (6 trainsets) | 05/10/2022 | 27/03/2023 | nan | nan | 0 | TK_NotStart | 1208363553 | 331 | 1208363553_331
MRPP2-SUP.11420 | TT_Task | EMU - PO Door Frame (CRF section) - 2nd Fleet (6 trainsets) | 04/03/2022 | 31/03/2022 | 02/02/2022 | 01/03/2022 | 0 | TK_Complete | 1208363553 | 332 | 1208363553_332
MRPP2-SUP.15550 | TT_Task | EMU - Production Door Frame (CRF section) - 2nd Fleet (6 trainsets) | 01/04/2022 | 15/02/2023 | 02/03/2022 | nan | 0 | TK_Active | 1208363553 | 332 | 1208363553_332
MRPP2-SUP.21140 | TT_Task | EMU - DEL Door Frame (CRF section) delivery - 2nd Fleet (6 trainsets) | 05/10/2022 | 27/03/2023 | nan | nan | 0 | TK_NotStart | 1208363553 | 332 | 1208363553_332
MRPP2-SUP.11320 | TT_Task | EMU - PO Sidewall (Cut ; Bend Parts) - 2nd Fleet (6 trainsets) | 04/03/2022 | 31/03/2022 | 02/02/2022 | 01/03/2022 | 0 | TK_Complete | 1208363553 | 333 | 1208363553_333
MRPP2-SUP.15450 | TT_Task | EMU - Production Sidewall (Cut ; Bend Parts) - 2nd Fleet (6 trainsets) | 01/04/2022 | 15/02/2023 | 02/03/2022 | nan | 0 | TK_Active | 1208363553 | 333 | 1208363553_333
MRPP2-SUP.21110 | TT_Task | EMU - DEL Sidewall (Cut ; Bend Parts) delivery - 2nd Fleet (6 trainsets) | 23/08/2022 | 13/02/2023 | nan | nan | 0 | TK_NotStart | 1208363553 | 333 | 1208363553_333
MRPP2-SUP.11430 | TT_Task | EMU - PO Letter Board (in Small parts) - 2nd Fleet (6 trainsets) | 04/03/2022 | 31/03/2022 | 02/02/2022 | 01/03/2022 | 0 | TK_Complete | 1208363553 | 336 | 1208363553_336
MRPP2-SUP.15560 | TT_Task | EMU - Production Letter Board (in Small parts) - 2nd Fleet (6 trainsets) | 01/04/2022 | 15/02/2023 | 02/03/2022 | nan | 0 | TK_Active | 1208363553 | 336 | 1208363553_336
MRPP2-SUP.21150 | TT_Task | EMU - DEL Letter Board (in Small parts) delivery - 2nd Fleet (6 trainsets) | 23/08/2022 | 13/02/2023 | nan | nan | 0 | TK_NotStart | 1208363553 | 336 | 1208363553_336
MRPP2-SUP.11610 | TT_Task | EMU - PO Stainless Steel (C;B, CRF) - 3rd Fleet (6 trainsets) | 21/09/2022 | 05/10/2022 | nan | nan | 0 | TK_NotStart | 1208363553 | 334 | 1208363553_334
MRPP2-SUP.15740 | TT_Task | EMU - Production Stainless Steel (C;B, CRF) - 3rd Fleet (6 trainsets) | 06/10/2022 | 26/06/2023 | nan | nan | 0 | TK_NotStart | 1208363553 | 334 | 1208363553_334
MRPP2-SUP.21640 | TT_Task | EMU - DEL Stainless Steel (C;B, CRF) delivery - 3rd Fleet (6 trainsets) | 15/03/2023 | 04/09/2023 | nan | nan | 0 | TK_NotStart | 1208363553 | 334 | 1208363553_334
MRPP2-SUP.11730 | TT_Task | EMU - PO Carbon Steel RM - 3rd Fleet (6 trainsets) | 06/10/2022 | 02/11/2022 | nan | nan | 0 | TK_NotStart | 1208363553 | 335 | 1208363553_335
MRPP2-SUP.15860 | TT_Task | EMU - Production Carbon Steel RM - 3rd Fleet (6 trainsets) | 03/11/2022 | 24/07/2023 | nan | nan | 0 | TK_NotStart | 1208363553 | 335 | 1208363553_335
MRPP2-SUP.21650 | TT_Task | EMU - DEL Carbon Steel RM delivery - 3rd Fleet (6 trainsets) | 14/04/2023 | 03/10/2023 | nan | nan | 0 | TK_NotStart | 1208363553 | 335 | 1208363553_335
MRPP2-SUP.11740 | TT_Task | EMU - PO Steel Casting - Equipment Support - 3rd Fleet (6 trainsets) | 06/10/2022 | 02/11/2022 | nan | nan | 0 | TK_NotStart | 1208363553 | 320 | 1208363553_320
MRPP2-SUP.15870 | TT_Task | EMU - Production Steel Casting - Equipment Support - 3rd Fleet (6 trainsets) | 03/11/2022 | 24/07/2023 | nan | nan | 0 | TK_NotStart | 1208363553 | 320 | 1208363553_320
MRPP2-SUP.21660 | TT_Task | EMU - DEL Steel Casting - Equipment Support delivery - 3rd Fleet (6 trainsets) | 14/04/2023 | 03/10/2023 | nan | nan | 0 | TK_NotStart | 1208363553 | 320 | 1208363553_320
MRPP2-SUP.11620 | TT_Task | EMU - PO Driver Cab - 3rd Fleet (6 trainsets) | 21/09/2022 | 19/10/2022 | nan | nan | 0 | TK_NotStart | 1208363553 | 321 | 1208363553_321
MRPP2-SUP.15750 | TT_Task | EMU - Production Driver Cab - 3rd Fleet (6 trainsets) | 20/10/2022 | 03/10/2023 | nan | nan | 0 | TK_NotStart | 1208363553 | 321 | 1208363553_321
MRPP2-SUP.21800 | TT_Task | EMU - DEL Driver Cab delivery - 3rd Fleet (6 trainsets) | 08/08/2023 | 29/01/2024 | nan | nan | 0 | TK_NotStart | 1208363553 | 321 | 1208363553_321
MRPP2-SUP.11630 | TT_Task | EMU - PO Side Sill (CRF Parts) - 3rd Fleet (6 trainsets) | 21/09/2022 | 19/10/2022 | nan | nan | 0 | TK_NotStart | 1208363553 | 322 | 1208363553_322
MRPP2-SUP.15760 | TT_Task | EMU - Production Side Sill (CRF Parts) - 3rd Fleet (6 trainsets) | 20/10/2022 | 03/10/2023 | nan | nan | 0 | TK_NotStart | 1208363553 | 322 | 1208363553_322
MRPP2-SUP.21810 | TT_Task | EMU - DEL Side Sill (CRF Parts) delivery - 3rd Fleet (6 trainsets) | 08/08/2023 | 29/01/2024 | nan | nan | 0 | TK_NotStart | 1208363553 | 322 | 1208363553_322
MRPP2-SUP.11640 | TT_Task | EMU - PO Underframe Panels (CRF Parts) - 3rd Fleet (6 trainsets) | 21/09/2022 | 19/10/2022 | nan | nan | 0 | TK_NotStart | 1208363553 | 323 | 1208363553_323
MRPP2-SUP.15770 | TT_Task | EMU - Production Underframe Panels (CRF Parts) - 3rd Fleet (6 trainsets) | 20/10/2022 | 03/10/2023 | nan | nan | 0 | TK_NotStart | 1208363553 | 323 | 1208363553_323
MRPP2-SUP.21820 | TT_Task | EMU - DEL Underframe Panels (CRF Parts) delivery - 3rd Fleet (6 trainsets) | 08/08/2023 | 29/01/2024 | nan | nan | 0 | TK_NotStart | 1208363553 | 323 | 1208363553_323
MRPP2-SUP.11650 | TT_Task | EMU - PO Roof Corrugation (CRF Parts) - 3rd Fleet (6 trainsets) | 21/09/2022 | 19/10/2022 | nan | nan | 0 | TK_NotStart | 1208363553 | 324 | 1208363553_324
MRPP2-SUP.15780 | TT_Task | EMU - Production Roof Corrugation (CRF Parts) - 3rd Fleet (6 trainsets) | 20/10/2022 | 03/10/2023 | nan | nan | 0 | TK_NotStart | 1208363553 | 324 | 1208363553_324
MRPP2-SUP.21830 | TT_Task | EMU - DEL Roof Corrugation (CRF Parts) delivery - 3rd Fleet (6 trainsets) | 08/08/2023 | 29/01/2024 | nan | nan | 0 | TK_NotStart | 1208363553 | 324 | 1208363553_324
MRPP2-SUP.11660 | TT_Task | EMU - PO Cantrail with Integrated roof gutter (CRF Parts) - 3rd Fleet (6 trainsets) | 21/09/2022 | 19/10/2022 | nan | nan | 0 | TK_NotStart | 1208363553 | 325 | 1208363553_325
MRPP2-SUP.15790 | TT_Task | EMU - Production Cantrail with Integrated roof gutter (CRF Parts) - 3rd Fleet (6 trainsets) | 20/10/2022 | 03/10/2023 | nan | nan | 0 | TK_NotStart | 1208363553 | 325 | 1208363553_325
MRPP2-SUP.21840 | TT_Task | EMU - DEL Cantrail with Integrated roof gutter (CRF Parts) delivery - 3rd Fleet (6 trainsets) | 08/08/2023 | 29/01/2024 | nan | nan | 0 | TK_NotStart | 1208363553 | 325 | 1208363553_325
MRPP2-SUP.11680 | TT_Task | EMU - PO EUF - 3rd Fleet (6 trainsets) | 06/10/2022 | 02/11/2022 | nan | nan | 0 | TK_NotStart | 1208363553 | 326 | 1208363553_326
MRPP2-SUP.15810 | TT_Task | EMU - Production EUF - 3rd Fleet (6 trainsets) | 03/11/2022 | 18/09/2023 | nan | nan | 0 | TK_NotStart | 1208363553 | 327 | 1208363553_327
MRPP2-SUP.21710 | TT_Task | EMU - DEL EUF delivery - 3rd Fleet (6 trainsets) | 11/07/2023 | 28/12/2023 | nan | nan | 0 | TK_NotStart | 1208363553 | 329 | 1208363553_329
MRPP2-SUP.11750 | TT_Task | EMU - PO Carline - 3rd Fleet (6 trainsets) | 06/10/2022 | 02/11/2022 | nan | nan | 0 | TK_NotStart | 1208363553 | 330 | 1208363553_330
MRPP2-SUP.15880 | TT_Task | EMU - Production Carline - 3rd Fleet (6 trainsets) | 03/11/2022 | 18/09/2023 | nan | nan | 0 | TK_NotStart | 1208363553 | 331 | 1208363553_331
MRPP2-SUP.21720 | TT_Task | EMU - DEL Carline delivery - 3rd Fleet (6 trainsets) | 11/07/2023 | 28/12/2023 | nan | nan | 0 | TK_NotStart | 1208363553 | 331 | 1208363553_331
MRPP2-SUP.11760 | TT_Task | EMU - PO Door Frame (CRF section) - 3rd Fleet (6 trainsets) | 06/10/2022 | 02/11/2022 | nan | nan | 0 | TK_NotStart | 1208363553 | 332 | 1208363553_332
MRPP2-SUP.15890 | TT_Task | EMU - Production Door Frame (CRF section) - 3rd Fleet (6 trainsets) | 03/11/2022 | 18/09/2023 | nan | nan | 0 | TK_NotStart | 1208363553 | 332 | 1208363553_332
MRPP2-SUP.21730 | TT_Task | EMU - DEL Door Frame (CRF section) delivery - 3rd Fleet (6 trainsets) | 11/07/2023 | 28/12/2023 | nan | nan | 0 | TK_NotStart | 1208363553 | 332 | 1208363553_332
MRPP2-SUP.11670 | TT_Task | EMU - PO Sidewall (Cut ; Bend Parts) - 3rd Fleet (6 trainsets) | 03/11/2022 | 30/11/2022 | nan | nan | 0 | TK_NotStart | 1208363553 | 333 | 1208363553_333
MRPP2-SUP.15800 | TT_Task | EMU - Production Sidewall (Cut ; Bend Parts) - 3rd Fleet (6 trainsets) | 01/12/2022 | 17/10/2023 | nan | nan | 0 | TK_NotStart | 1208363553 | 333 | 1208363553_333
MRPP2-SUP.21700 | TT_Task | EMU - DEL Sidewall (Cut ; Bend Parts) - 3rd Fleet (6 trainsets) | 29/05/2023 | 14/11/2023 | nan | nan | 0 | TK_NotStart | 1208363553 | 333 | 1208363553_333
MRPP2-SUP.11770 | TT_Task | EMU - PO Letter Board (in Small parts) - 3rd Fleet (6 trainsets) | 01/12/2022 | 30/12/2022 | nan | nan | 0 | TK_NotStart | 1208363553 | 336 | 1208363553_336
MRPP2-SUP.15900 | TT_Task | EMU - Production Letter Board (in Small parts) - 3rd Fleet (6 trainsets) | 03/01/2023 | 14/11/2023 | nan | nan | 0 | TK_NotStart | 1208363553 | 336 | 1208363553_336
MRPP2-SUP.21740 | TT_Task | EMU - DEL Letter Board (in Small parts) - 3rd Fleet (6 trainsets) | 27/06/2023 | 12/12/2023 | nan | nan | 0 | TK_NotStart | 1208363553 | 336 | 1208363553_336
MRPP2-SUP.12350 | TT_Task | EMU - PO Stainless Steel (C;B, CRF) - 4th Fleet (6 trainsets) | 06/09/2023 | 04/10/2023 | nan | nan | 0 | TK_NotStart | 1208363553 | 334 | 1208363553_334
MRPP2-SUP.16480 | TT_Task | EMU - Production Stainless Steel (C;B, CRF) - 4th Fleet (6 trainsets) | 05/10/2023 | 24/06/2024 | nan | nan | 0 | TK_NotStart | 1208363553 | 334 | 1208363553_334
MRPP2-SUP.22470 | TT_Task | EMU - DEL Stainless Steel (C;B, CRF) - 4th Fleet (6 trainsets) | 13/03/2024 | 02/09/2024 | nan | nan | 0 | TK_NotStart | 1208363553 | 334 | 1208363553_334
MRPP2-SUP.12440 | TT_Task | EMU - PO Carbon Steel RM - 4th Fleet (6 trainsets) | 05/10/2023 | 01/11/2023 | nan | nan | 0 | TK_NotStart | 1208363553 | 335 | 1208363553_335
MRPP2-SUP.16570 | TT_Task | EMU - Production Carbon Steel RM - 4th Fleet (6 trainsets) | 02/11/2023 | 22/07/2024 | nan | nan | 0 | TK_NotStart | 1208363553 | 335 | 1208363553_335
MRPP2-SUP.22500 | TT_Task | EMU - DEL Carbon Steel RM - 4th Fleet (6 trainsets) | 10/04/2024 | 01/10/2024 | nan | nan | 0 | TK_NotStart | 1208363553 | 335 | 1208363553_335
MRPP2-SUP.12450 | TT_Task | EMU - PO Steel Casting - Equipment Support - 4th Fleet (6 trainsets) | 05/10/2023 | 01/11/2023 | nan | nan | 0 | TK_NotStart | 1208363553 | 320 | 1208363553_320
MRPP2-SUP.16580 | TT_Task | EMU - Production Steel Casting - Equipment Support - 4th Fleet (6 trainsets) | 02/11/2023 | 22/07/2024 | nan | nan | 0 | TK_NotStart | 1208363553 | 320 | 1208363553_320
MRPP2-SUP.22510 | TT_Task | EMU - DEL Steel Casting - Equipment Support - 4th Fleet (6 trainsets) | 10/04/2024 | 01/10/2024 | nan | nan | 0 | TK_NotStart | 1208363553 | 320 | 1208363553_320
MRPP2-SUP.12360 | TT_Task | EMU - PO Driver Cab - 4th Fleet (6 trainsets) | 06/09/2023 | 04/10/2023 | nan | nan | 0 | TK_NotStart | 1208363553 | 321 | 1208363553_321
MRPP2-SUP.16490 | TT_Task | EMU - Production Driver Cab - 4th Fleet (6 trainsets) | 05/10/2023 | 16/09/2024 | nan | nan | 0 | TK_NotStart | 1208363553 | 321 | 1208363553_321
MRPP2-SUP.22680 | TT_Task | EMU - DEL Driver Cab - 4th Fleet (6 trainsets) | 23/07/2024 | 10/01/2025 | nan | nan | 0 | TK_NotStart | 1208363553 | 321 | 1208363553_321
MRPP2-SUP.12370 | TT_Task | EMU - PO Side Sill (CRF Parts) - 4th Fleet (6 trainsets) | 06/09/2023 | 04/10/2023 | nan | nan | 0 | TK_NotStart | 1208363553 | 322 | 1208363553_322
MRPP2-SUP.16500 | TT_Task | EMU - Production Side Sill (CRF Parts) - 4th Fleet (6 trainsets) | 05/10/2023 | 16/09/2024 | nan | nan | 0 | TK_NotStart | 1208363553 | 322 | 1208363553_322
MRPP2-SUP.22690 | TT_Task | EMU - DEL Side Sill (CRF Parts) - 4th Fleet (6 trainsets) | 23/07/2024 | 10/01/2025 | nan | nan | 0 | TK_NotStart | 1208363553 | 322 | 1208363553_322
MRPP2-SUP.12380 | TT_Task | EMU - PO Underframe Panels (CRF Parts) - 4th Fleet (6 trainsets) | 06/09/2023 | 04/10/2023 | nan | nan | 0 | TK_NotStart | 1208363553 | 323 | 1208363553_323
MRPP2-SUP.16510 | TT_Task | EMU - Production Underframe Panels (CRF Parts) - 4th Fleet (6 trainsets) | 05/10/2023 | 16/09/2024 | nan | nan | 0 | TK_NotStart | 1208363553 | 323 | 1208363553_323
MRPP2-SUP.22700 | TT_Task | EMU - DEL Underframe Panels (CRF Parts) - 4th Fleet (6 trainsets) | 23/07/2024 | 10/01/2025 | nan | nan | 0 | TK_NotStart | 1208363553 | 323 | 1208363553_323
MRPP2-SUP.12390 | TT_Task | EMU - PO Roof Corrugation (CRF Parts) - 4th Fleet (6 trainsets) | 06/09/2023 | 04/10/2023 | nan | nan | 0 | TK_NotStart | 1208363553 | 324 | 1208363553_324
MRPP2-SUP.16520 | TT_Task | EMU - Production Roof Corrugation (CRF Parts) - 4th Fleet (6 trainsets) | 05/10/2023 | 16/09/2024 | nan | nan | 0 | TK_NotStart | 1208363553 | 324 | 1208363553_324
MRPP2-SUP.22710 | TT_Task | EMU - DEL Roof Corrugation (CRF Parts) - 4th Fleet (6 trainsets) | 23/07/2024 | 10/01/2025 | nan | nan | 0 | TK_NotStart | 1208363553 | 324 | 1208363553_324
MRPP2-SUP.12400 | TT_Task | EMU - PO Cantrail with Integrated roof gutter (CRF Parts) - 4th Fleet (6 trainsets) | 06/09/2023 | 04/10/2023 | nan | nan | 0 | TK_NotStart | 1208363553 | 325 | 1208363553_325
MRPP2-SUP.16530 | TT_Task | EMU - Production Cantrail with Integrated roof gutter (CRF Parts) - 4th Fleet (6 trainsets) | 05/10/2023 | 16/09/2024 | nan | nan | 0 | TK_NotStart | 1208363553 | 325 | 1208363553_325
MRPP2-SUP.22720 | TT_Task | EMU - DEL Cantrail with Integrated roof gutter (CRF Parts) - 4th Fleet (6 trainsets) | 23/07/2024 | 10/01/2025 | nan | nan | 0 | TK_NotStart | 1208363553 | 325 | 1208363553_325
MRPP2-SUP.12430 | TT_Task | EMU - PO EUF - 4th Fleet (6 trainsets) | 05/10/2023 | 01/11/2023 | nan | nan | 0 | TK_NotStart | 1208363553 | 326 | 1208363553_326
MRPP2-SUP.16560 | TT_Task | EMU - Production EUF - 4th Fleet (6 trainsets) | 02/11/2023 | 16/09/2024 | nan | nan | 0 | TK_NotStart | 1208363553 | 327 | 1208363553_327
MRPP2-SUP.22580 | TT_Task | EMU - DEL EUF delivery - 4th Fleet (6 trainsets) | 11/06/2024 | 26/11/2024 | nan | nan | 0 | TK_NotStart | 1208363553 | 329 | 1208363553_329
MRPP2-SUP.12460 | TT_Task | EMU - PO Carline - 4th Fleet (6 trainsets) | 05/10/2023 | 01/11/2023 | nan | nan | 0 | TK_NotStart | 1208363553 | 330 | 1208363553_330
MRPP2-SUP.16590 | TT_Task | EMU - Production Carline - 4th Fleet (6 trainsets) | 02/11/2023 | 16/09/2024 | nan | nan | 0 | TK_NotStart | 1208363553 | 331 | 1208363553_331
MRPP2-SUP.22590 | TT_Task | EMU - DEL Carline - 4th Fleet (6 trainsets) | 11/06/2024 | 26/11/2024 | nan | nan | 0 | TK_NotStart | 1208363553 | 330 | 1208363553_330
MRPP2-SUP.12470 | TT_Task | EMU - PO Door Frame (CRF section) - 4th Fleet (6 trainsets) | 05/10/2023 | 01/11/2023 | nan | nan | 0 | TK_NotStart | 1208363553 | 332 | 1208363553_332
MRPP2-SUP.16600 | TT_Task | EMU - Production Door Frame (CRF section) - 4th Fleet (6 trainsets) | 02/11/2023 | 16/09/2024 | nan | nan | 0 | TK_NotStart | 1208363553 | 332 | 1208363553_332
MRPP2-SUP.22600 | TT_Task | EMU - DEL Door Frame (CRF section) - 4th Fleet (6 trainsets) | 11/06/2024 | 26/11/2024 | nan | nan | 0 | TK_NotStart | 1208363553 | 332 | 1208363553_332
MRPP2-SUP.12420 | TT_Task | EMU - PO Sidewall (Cut ; Bend Parts) - 4th Fleet (6 trainsets) | 05/10/2023 | 01/11/2023 | nan | nan | 0 | TK_NotStart | 1208363553 | 333 | 1208363553_333
MRPP2-SUP.16550 | TT_Task | EMU - Production Sidewall (Cut ; Bend Parts) - 4th Fleet (6 trainsets) | 02/11/2023 | 16/09/2024 | nan | nan | 0 | TK_NotStart | 1208363553 | 333 | 1208363553_333
MRPP2-SUP.22570 | TT_Task | EMU - DEL Sidewall (Cut ; Bend Parts) - 4th Fleet (6 trainsets) | 29/04/2024 | 15/10/2024 | nan | nan | 0 | TK_NotStart | 1208363553 | 333 | 1208363553_333
MRPP2-SUP.12480 | TT_Task | EMU - PO Letter Board (in Small parts) - 4th Fleet (6 trainsets) | 05/10/2023 | 01/11/2023 | nan | nan | 0 | TK_NotStart | 1208363553 | 336 | 1208363553_336
MRPP2-SUP.16610 | TT_Task | EMU - Production Letter Board (in Small parts) - 4th Fleet (6 trainsets) | 02/11/2023 | 16/09/2024 | nan | nan | 0 | TK_NotStart | 1208363553 | 336 | 1208363553_336
MRPP2-SUP.22610 | TT_Task | EMU - DEL Letter Board (in Small parts) - 4th Fleet (6 trainsets) | 29/04/2024 | 15/10/2024 | nan | nan | 0 | TK_NotStart | 1208363553 | 336 | 1208363553_336
MRPP2-SUP.12840 | TT_Task | EMU - PO Stainless Steel (C;B, CRF) - 5th Fleet (6 trainsets) | 04/09/2024 | 02/10/2024 | nan | nan | 0 | TK_NotStart | 1208363553 | 334 | 1208363553_334
MRPP2-SUP.16970 | TT_Task | EMU - Production Stainless Steel (C;B, CRF) - 5th Fleet (6 trainsets) | 03/10/2024 | 23/06/2025 | nan | nan | 0 | TK_NotStart | 1208363553 | 334 | 1208363553_334
MRPP2-SUP.23040 | TT_Task | EMU - DEL Stainless Steel (C;B, CRF) delivery - 5th Fleet (6 trainsets) | 12/03/2025 | 01/09/2025 | nan | nan | 0 | TK_NotStart | 1208363553 | 334 | 1208363553_334
MRPP2-SUP.12940 | TT_Task | EMU - PO Carbon Steel RM - 5th Fleet (6 trainsets) | 03/10/2024 | 30/10/2024 | nan | nan | 0 | TK_NotStart | 1208363553 | 335 | 1208363553_335
MRPP2-SUP.17070 | TT_Task | EMU - Production Carbon Steel RM - 5th Fleet (6 trainsets) | 31/10/2024 | 21/07/2025 | nan | nan | 0 | TK_NotStart | 1208363553 | 335 | 1208363553_335
MRPP2-SUP.23110 | TT_Task | EMU - DEL Carbon Steel RM - 5th Fleet (6 trainsets) | 09/04/2025 | 30/09/2025 | nan | nan | 0 | TK_NotStart | 1208363553 | 335 | 1208363553_335
MRPP2-SUP.12950 | TT_Task | EMU - PO Steel Casting - Equipment Support - 5th Fleet (6 trainsets) | 03/10/2024 | 30/10/2024 | nan | nan | 0 | TK_NotStart | 1208363553 | 320 | 1208363553_320
MRPP2-SUP.17080 | TT_Task | EMU - Production Steel Casting - Equipment Support - 5th Fleet (6 trainsets) | 31/10/2024 | 21/07/2025 | nan | nan | 0 | TK_NotStart | 1208363553 | 320 | 1208363553_320
MRPP2-SUP.23120 | TT_Task | EMU - DEL Steel Casting - Equipment Support - 5th Fleet (6 trainsets) | 09/04/2025 | 30/09/2025 | nan | nan | 0 | TK_NotStart | 1208363553 | 320 | 1208363553_320
MRPP2-SUP.12850 | TT_Task | EMU - PO Driver Cab - 5th Fleet (6 trainsets) | 04/09/2024 | 02/10/2024 | nan | nan | 0 | TK_NotStart | 1208363553 | 321 | 1208363553_321
MRPP2-SUP.16980 | TT_Task | EMU - Production Driver Cab - 5th Fleet (6 trainsets) | 03/10/2024 | 15/09/2025 | nan | nan | 0 | TK_NotStart | 1208363553 | 321 | 1208363553_321
MRPP2-SUP.23310 | TT_Task | EMU - DEL Driver Cab - 5th Fleet (6 trainsets) | 22/07/2025 | 09/01/2026 | nan | nan | 0 | TK_NotStart | 1208363553 | 321 | 1208363553_321
MRPP2-SUP.12860 | TT_Task | EMU - PO Side Sill (CRF Parts) - 5th Fleet (6 trainsets) | 04/09/2024 | 02/10/2024 | nan | nan | 0 | TK_NotStart | 1208363553 | 322 | 1208363553_322
MRPP2-SUP.16990 | TT_Task | EMU - Production Side Sill (CRF Parts) - 5th Fleet (6 trainsets) | 03/10/2024 | 15/09/2025 | nan | nan | 0 | TK_NotStart | 1208363553 | 322 | 1208363553_322
MRPP2-SUP.23320 | TT_Task | EMU - DEL Side Sill (CRF Parts) - 5th Fleet (6 trainsets) | 22/07/2025 | 09/01/2026 | nan | nan | 0 | TK_NotStart | 1208363553 | 322 | 1208363553_322
MRPP2-SUP.12870 | TT_Task | EMU - PO Underframe Panels (CRF Parts) - 5th Fleet (6 trainsets) | 04/09/2024 | 02/10/2024 | nan | nan | 0 | TK_NotStart | 1208363553 | 323 | 1208363553_323
MRPP2-SUP.17000 | TT_Task | EMU - Production Underframe Panels (CRF Parts) - 5th Fleet (6 trainsets) | 03/10/2024 | 15/09/2025 | nan | nan | 0 | TK_NotStart | 1208363553 | 323 | 1208363553_323
MRPP2-SUP.23330 | TT_Task | EMU - DEL Underframe Panels (CRF Parts) - 5th Fleet (6 trainsets) | 22/07/2025 | 09/01/2026 | nan | nan | 0 | TK_NotStart | 1208363553 | 323 | 1208363553_323
MRPP2-SUP.12880 | TT_Task | EMU - PO Roof Corrugation (CRF Parts) - 5th Fleet (6 trainsets) | 04/09/2024 | 02/10/2024 | nan | nan | 0 | TK_NotStart | 1208363553 | 324 | 1208363553_324
MRPP2-SUP.17010 | TT_Task | EMU - Production Roof Corrugation (CRF Parts) - 5th Fleet (6 trainsets) | 03/10/2024 | 15/09/2025 | nan | nan | 0 | TK_NotStart | 1208363553 | 324 | 1208363553_324
MRPP2-SUP.23340 | TT_Task | EMU - DEL Roof Corrugation (CRF Parts) - 5th Fleet (6 trainsets) | 22/07/2025 | 09/01/2026 | nan | nan | 0 | TK_NotStart | 1208363553 | 324 | 1208363553_324
MRPP2-SUP.12890 | TT_Task | EMU - PO Cantrail with Integrated roof gutter (CRF Parts) - 5th Fleet (6 trainsets) | 04/09/2024 | 02/10/2024 | nan | nan | 0 | TK_NotStart | 1208363553 | 325 | 1208363553_325
MRPP2-SUP.17020 | TT_Task | EMU - Production Cantrail with Integrated roof gutter (CRF Parts) - 5th Fleet (6 trainsets) | 03/10/2024 | 15/09/2025 | nan | nan | 0 | TK_NotStart | 1208363553 | 325 | 1208363553_325
MRPP2-SUP.23350 | TT_Task | EMU - DEL Cantrail with Integrated roof gutter (CRF Parts) - 5th Fleet (6 trainsets) | 22/07/2025 | 09/01/2026 | nan | nan | 0 | TK_NotStart | 1208363553 | 325 | 1208363553_325
MRPP2-SUP.12930 | TT_Task | EMU - PO EUF - 5th Fleet (6 trainsets) | 03/10/2024 | 30/10/2024 | nan | nan | 0 | TK_NotStart | 1208363553 | 326 | 1208363553_326
MRPP2-SUP.17060 | TT_Task | EMU - Production EUF - 5th Fleet (6 trainsets) | 31/10/2024 | 15/09/2025 | nan | nan | 0 | TK_NotStart | 1208363553 | 327 | 1208363553_327
MRPP2-SUP.23190 | TT_Task | EMU - DEL EUF delivery - 5th Fleet (6 trainsets) | 10/06/2025 | 25/11/2025 | nan | nan | 0 | TK_NotStart | 1208363553 | 329 | 1208363553_329
MRPP2-SUP.12960 | TT_Task | EMU - PO Carline - 5th Fleet (6 trainsets) | 03/10/2024 | 30/10/2024 | nan | nan | 0 | TK_NotStart | 1208363553 | 330 | 1208363553_330
MRPP2-SUP.17090 | TT_Task | EMU - Production Carline - 5th Fleet (6 trainsets) | 31/10/2024 | 15/09/2025 | nan | nan | 0 | TK_NotStart | 1208363553 | 331 | 1208363553_331
MRPP2-SUP.23200 | TT_Task | EMU - DEL Carline - 5th Fleet (6 trainsets) | 10/06/2025 | 25/11/2025 | nan | nan | 0 | TK_NotStart | 1208363553 | 330 | 1208363553_330
MRPP2-SUP.12970 | TT_Task | EMU - PO Door Frame (CRF section) - 5th Fleet (6 trainsets) | 03/10/2024 | 30/10/2024 | nan | nan | 0 | TK_NotStart | 1208363553 | 332 | 1208363553_332
MRPP2-SUP.17100 | TT_Task | EMU - Production Door Frame (CRF section) - 5th Fleet (6 trainsets) | 31/10/2024 | 15/09/2025 | nan | nan | 0 | TK_NotStart | 1208363553 | 332 | 1208363553_332
MRPP2-SUP.23210 | TT_Task | EMU - DEL Door Frame (CRF section) - 5th Fleet (6 trainsets) | 10/06/2025 | 25/11/2025 | nan | nan | 0 | TK_NotStart | 1208363553 | 332 | 1208363553_332
MRPP2-SUP.13050 | TT_Task | EMU - PO Sidewall (Cut ; Bend Parts) - 5th Fleet (6 trainsets) | 31/10/2024 | 27/11/2024 | nan | nan | 0 | TK_NotStart | 1208363553 | 333 | 1208363553_333
MRPP2-SUP.17180 | TT_Task | EMU - Production Sidewall (Cut ; Bend Parts) - 5th Fleet (6 trainsets) | 28/11/2024 | 14/10/2025 | nan | nan | 0 | TK_NotStart | 1208363553 | 333 | 1208363553_333
MRPP2-SUP.23260 | TT_Task | EMU - DEL Sidewall (Cut ; Bend Parts) - 5th Fleet (6 trainsets) | 26/05/2025 | 11/11/2025 | nan | nan | 0 | TK_NotStart | 1208363553 | 333 | 1208363553_333
MRPP2-SUP.12980 | TT_Task | EMU - PO Letter Board (in Small parts) - 5th Fleet (6 trainsets) | 03/10/2024 | 30/10/2024 | nan | nan | 0 | TK_NotStart | 1208363553 | 336 | 1208363553_336
MRPP2-SUP.17110 | TT_Task | EMU - Production Letter Board (in Small parts) - 5th Fleet (6 trainsets) | 31/10/2024 | 15/09/2025 | nan | nan | 0 | TK_NotStart | 1208363553 | 336 | 1208363553_336
MRPP2-SUP.23220 | TT_Task | EMU - DEL Letter Board (in Small parts) - 5th Fleet (6 trainsets) | 28/04/2025 | 14/10/2025 | nan | nan | 0 | TK_NotStart | 1208363553 | 336 | 1208363553_336
MRPP2-SUP.13350 | TT_Task | EMU - PO Stainless Steel (C;B, CRF) - 6th Fleet (6 trainsets) | 03/07/2025 | 30/07/2025 | nan | nan | 0 | TK_NotStart | 1208363553 | 334 | 1208363553_334
MRPP2-SUP.17480 | TT_Task | EMU - Production Stainless Steel (C;B, CRF) - 6th Fleet (6 trainsets) | 31/07/2025 | 07/10/2026 | nan | nan | 0 | TK_NotStart | 1208363553 | 334 | 1208363553_334
MRPP2-SUP.23690 | TT_Task | EMU - DEL Stainless Steel (C;B, CRF) - 6th Fleet (6 trainsets) | 05/05/2026 | 21/10/2026 | nan | nan | 0 | TK_NotStart | 1208363553 | 334 | 1208363553_334
MRPP2-SUP.13450 | TT_Task | EMU - PO Carbon Steel RM - 6th Fleet (6 trainsets) | 31/07/2025 | 27/08/2025 | nan | nan | 0 | TK_NotStart | 1208363553 | 335 | 1208363553_335
MRPP2-SUP.17580 | TT_Task | EMU - Production Carbon Steel RM - 6th Fleet (6 trainsets) | 28/08/2025 | 04/11/2026 | nan | nan | 0 | TK_NotStart | 1208363553 | 335 | 1208363553_335
MRPP2-SUP.23730 | TT_Task | EMU - DEL Carbon Steel RM - 6th Fleet (6 trainsets) | 03/06/2026 | 18/11/2026 | nan | nan | 0 | TK_NotStart | 1208363553 | 335 | 1208363553_335
MRPP2-SUP.13460 | TT_Task | EMU - PO Steel Casting - Equipment Support - 6th Fleet (6 trainsets) | 31/07/2025 | 27/08/2025 | nan | nan | 0 | TK_NotStart | 1208363553 | 320 | 1208363553_320
MRPP2-SUP.17590 | TT_Task | EMU - Production Steel Casting - Equipment Support - 6th Fleet (6 trainsets) | 28/08/2025 | 04/11/2026 | nan | nan | 0 | TK_NotStart | 1208363553 | 320 | 1208363553_320
MRPP2-SUP.23740 | TT_Task | EMU - DEL Steel Casting - Equipment Support - 6th Fleet (6 trainsets) | 03/06/2026 | 18/11/2026 | nan | nan | 0 | TK_NotStart | 1208363553 | 320 | 1208363553_320
MRPP2-SUP.13360 | TT_Task | EMU - PO Driver Cab - 6th Fleet (6 trainsets) | 03/07/2025 | 30/07/2025 | nan | nan | 0 | TK_NotStart | 1208363553 | 321 | 1208363553_321
MRPP2-SUP.17490 | TT_Task | EMU - Production Driver Cab - 6th Fleet (6 trainsets) | 31/07/2025 | 07/10/2026 | nan | nan | 0 | TK_NotStart | 1208363553 | 321 | 1208363553_321
MRPP2-SUP.23950 | TT_Task | EMU - DEL Driver Cab - 6th Fleet (6 trainsets) | 19/05/2026 | 04/11/2026 | nan | nan | 0 | TK_NotStart | 1208363553 | 321 | 1208363553_321
MRPP2-SUP.13370 | TT_Task | EMU - PO Side Sill (CRF Parts) - 6th Fleet (6 trainsets) | 03/07/2025 | 30/07/2025 | nan | nan | 0 | TK_NotStart | 1208363553 | 322 | 1208363553_322
MRPP2-SUP.17500 | TT_Task | EMU - Production Side Sill (CRF Parts) - 6th Fleet (6 trainsets) | 31/07/2025 | 07/10/2026 | nan | nan | 0 | TK_NotStart | 1208363553 | 322 | 1208363553_322
MRPP2-SUP.23960 | TT_Task | EMU - DEL Side Sill (CRF Parts) - 6th Fleet (6 trainsets) | 19/05/2026 | 04/11/2026 | nan | nan | 0 | TK_NotStart | 1208363553 | 322 | 1208363553_322
MRPP2-SUP.13380 | TT_Task | EMU - PO Underframe Panels (CRF Parts) - 6th Fleet (6 trainsets) | 03/07/2025 | 30/07/2025 | nan | nan | 0 | TK_NotStart | 1208363553 | 323 | 1208363553_323
MRPP2-SUP.17510 | TT_Task | EMU - Production Underframe Panels (CRF Parts) - 6th Fleet (6 trainsets) | 31/07/2025 | 07/10/2026 | nan | nan | 0 | TK_NotStart | 1208363553 | 323 | 1208363553_323
MRPP2-SUP.23970 | TT_Task | EMU - DEL Underframe Panels (CRF Parts) - 6th Fleet (6 trainsets) | 19/05/2026 | 04/11/2026 | nan | nan | 0 | TK_NotStart | 1208363553 | 323 | 1208363553_323
MRPP2-SUP.13390 | TT_Task | EMU - PO Roof Corrugation (CRF Parts) - 6th Fleet (6 trainsets) | 03/07/2025 | 30/07/2025 | nan | nan | 0 | TK_NotStart | 1208363553 | 324 | 1208363553_324
MRPP2-SUP.17520 | TT_Task | EMU - Production Roof Corrugation (CRF Parts) - 6th Fleet (6 trainsets) | 31/07/2025 | 07/10/2026 | nan | nan | 0 | TK_NotStart | 1208363553 | 324 | 1208363553_324
MRPP2-SUP.23980 | TT_Task | EMU - DEL Roof Corrugation (CRF Parts) - 6th Fleet (6 trainsets) | 19/05/2026 | 04/11/2026 | nan | nan | 0 | TK_NotStart | 1208363553 | 324 | 1208363553_324
MRPP2-SUP.13400 | TT_Task | EMU - PO Cantrail with Integrated roof gutter (CRF Parts) - 6th Fleet (6 trainsets) | 03/07/2025 | 30/07/2025 | nan | nan | 0 | TK_NotStart | 1208363553 | 325 | 1208363553_325
MRPP2-SUP.17530 | TT_Task | EMU - Production Cantrail with Integrated roof gutter (CRF Parts) - 6th Fleet (6 trainsets) | 31/07/2025 | 07/10/2026 | nan | nan | 0 | TK_NotStart | 1208363553 | 325 | 1208363553_325
MRPP2-SUP.23990 | TT_Task | EMU - DEL Cantrail with Integrated roof gutter (CRF Parts) - 6th Fleet (6 trainsets) | 19/05/2026 | 04/11/2026 | nan | nan | 0 | TK_NotStart | 1208363553 | 325 | 1208363553_325
MRPP2-SUP.13440 | TT_Task | EMU - PO EUF - 6th Fleet (6 trainsets) | 31/07/2025 | 27/08/2025 | nan | nan | 0 | TK_NotStart | 1208363553 | 326 | 1208363553_326
MRPP2-SUP.17570 | TT_Task | EMU - Production EUF - 6th Fleet (6 trainsets) | 28/08/2025 | 04/11/2026 | nan | nan | 0 | TK_NotStart | 1208363553 | 327 | 1208363553_327
MRPP2-SUP.23840 | TT_Task | EMU - DEL EUF delivery - 6th Fleet (6 trainsets) | 02/04/2026 | 18/11/2026 | nan | nan | 0 | TK_NotStart | 1208363553 | 329 | 1208363553_329
MRPP2-SUP.13470 | TT_Task | EMU - PO Carline - 6th Fleet (6 trainsets) | 31/07/2025 | 27/08/2025 | nan | nan | 0 | TK_NotStart | 1208363553 | 330 | 1208363553_330
MRPP2-SUP.17600 | TT_Task | EMU - Production Carline - 6th Fleet (6 trainsets) | 28/08/2025 | 04/11/2026 | nan | nan | 0 | TK_NotStart | 1208363553 | 331 | 1208363553_331
MRPP2-SUP.23850 | TT_Task | EMU - DEL Carline - 6th Fleet (6 trainsets) | 02/04/2026 | 18/11/2026 | nan | nan | 0 | TK_NotStart | 1208363553 | 330 | 1208363553_330
MRPP2-SUP.13480 | TT_Task | EMU - PO Door Frame (CRF section) - 6th Fleet (6 trainsets) | 31/07/2025 | 27/08/2025 | nan | nan | 0 | TK_NotStart | 1208363553 | 332 | 1208363553_332
MRPP2-SUP.17610 | TT_Task | EMU - Production Door Frame (CRF section) - 6th Fleet (6 trainsets) | 28/08/2025 | 04/11/2026 | nan | nan | 0 | TK_NotStart | 1208363553 | 332 | 1208363553_332
MRPP2-SUP.23860 | TT_Task | EMU - DEL Door Frame (CRF section) - 6th Fleet (6 trainsets) | 02/04/2026 | 18/11/2026 | nan | nan | 0 | TK_NotStart | 1208363553 | 332 | 1208363553_332
MRPP2-SUP.13430 | TT_Task | EMU - PO Sidewall (Cut ; Bend Parts) - 6th Fleet (6 trainsets) | 31/07/2025 | 27/08/2025 | nan | nan | 0 | TK_NotStart | 1208363553 | 333 | 1208363553_333
MRPP2-SUP.17560 | TT_Task | EMU - Production Sidewall (Cut ; Bend Parts) - 6th Fleet (6 trainsets) | 28/08/2025 | 04/11/2026 | nan | nan | 0 | TK_NotStart | 1208363553 | 333 | 1208363553_333
MRPP2-SUP.23830 | TT_Task | EMU - DEL Sidewall (Cut ; Bend Parts) - 6th Fleet (6 trainsets) | 19/02/2026 | 02/12/2026 | nan | nan | 0 | TK_NotStart | 1208363553 | 333 | 1208363553_333
MRPP2-SUP.13490 | TT_Task | EMU - PO Letter Board (in Small parts) - 6th Fleet (6 trainsets) | 31/07/2025 | 27/08/2025 | nan | nan | 0 | TK_NotStart | 1208363553 | 336 | 1208363553_336
MRPP2-SUP.17620 | TT_Task | EMU - Production Letter Board (in Small parts) - 6th Fleet (6 trainsets) | 28/08/2025 | 04/11/2026 | nan | nan | 0 | TK_NotStart | 1208363553 | 336 | 1208363553_336
MRPP2-SUP.23870 | TT_Task | EMU - DEL Letter Board (in Small parts) - 6th Fleet (6 trainsets) | 19/02/2026 | 02/12/2026 | nan | nan | 0 | TK_NotStart | 1208363553 | 336 | 1208363553_336
MRPP2-SUP.13780 | TT_Task | EMU - PO Stainless Steel (C;B, CRF) - 7th Fleet (6 trainsets) | 12/06/2026 | 09/07/2026 | nan | nan | 0 | TK_NotStart | 1208363553 | 334 | 1208363553_334
MRPP2-SUP.17910 | TT_Task | EMU - Production Stainless Steel (C;B, CRF) - 7th Fleet (6 trainsets) | 10/07/2026 | 23/06/2027 | nan | nan | 0 | TK_NotStart | 1208363553 | 334 | 1208363553_334
MRPP2-SUP.24200 | TT_Task | EMU - DEL Stainless Steel (C;B, CRF) - 7th Fleet (6 trainsets) | 13/04/2027 | 30/09/2027 | nan | nan | 0 | TK_NotStart | 1208363553 | 334 | 1208363553_334
MRPP2-SUP.13870 | TT_Task | EMU - PO Carbon Steel RM - 7th Fleet (6 trainsets) | 10/07/2026 | 06/08/2026 | nan | nan | 0 | TK_NotStart | 1208363553 | 335 | 1208363553_335
MRPP2-SUP.18000 | TT_Task | EMU - Production Carbon Steel RM - 7th Fleet (6 trainsets) | 07/08/2026 | 21/07/2027 | nan | nan | 0 | TK_NotStart | 1208363553 | 335 | 1208363553_335
MRPP2-SUP.24210 | TT_Task | EMU - DEL Carbon Steel RM - 7th Fleet (6 trainsets) | 12/05/2027 | 28/10/2027 | nan | nan | 0 | TK_NotStart | 1208363553 | 335 | 1208363553_335
MRPP2-SUP.13880 | TT_Task | EMU - PO Steel Casting - Equipment Support - 7th Fleet (6 trainsets) | 10/07/2026 | 06/08/2026 | nan | nan | 0 | TK_NotStart | 1208363553 | 320 | 1208363553_320
MRPP2-SUP.18010 | TT_Task | EMU - Production Steel Casting - Equipment Support - 7th Fleet (6 trainsets) | 07/08/2026 | 21/07/2027 | nan | nan | 0 | TK_NotStart | 1208363553 | 320 | 1208363553_320
MRPP2-SUP.24220 | TT_Task | EMU - DEL Steel Casting - Equipment Support - 7th Fleet (6 trainsets) | 12/05/2027 | 28/10/2027 | nan | nan | 0 | TK_NotStart | 1208363553 | 320 | 1208363553_320
MRPP2-SUP.13790 | TT_Task | EMU - PO Driver Cab - 7th Fleet (6 trainsets) | 12/06/2026 | 09/07/2026 | nan | nan | 0 | TK_NotStart | 1208363553 | 321 | 1208363553_321
MRPP2-SUP.17920 | TT_Task | EMU - Production Driver Cab - 7th Fleet (6 trainsets) | 10/07/2026 | 23/06/2027 | nan | nan | 0 | TK_NotStart | 1208363553 | 321 | 1208363553_321
MRPP2-SUP.24460 | TT_Task | EMU - DEL Driver Cab - 7th Fleet (6 trainsets) | 28/04/2027 | 14/10/2027 | nan | nan | 0 | TK_NotStart | 1208363553 | 321 | 1208363553_321
MRPP2-SUP.13800 | TT_Task | EMU - PO Side Sill (CRF Parts) - 7th Fleet (6 trainsets) | 12/06/2026 | 09/07/2026 | nan | nan | 0 | TK_NotStart | 1208363553 | 322 | 1208363553_322
MRPP2-SUP.17930 | TT_Task | EMU - Production Side Sill (CRF Parts) - 7th Fleet (6 trainsets) | 10/07/2026 | 23/06/2027 | nan | nan | 0 | TK_NotStart | 1208363553 | 322 | 1208363553_322
MRPP2-SUP.24470 | TT_Task | EMU - DEL Side Sill (CRF Parts) - 7th Fleet (6 trainsets) | 28/04/2027 | 14/10/2027 | nan | nan | 0 | TK_NotStart | 1208363553 | 322 | 1208363553_322
MRPP2-SUP.13810 | TT_Task | EMU - PO Underframe Panels (CRF Parts) - 7th Fleet (6 trainsets) | 12/06/2026 | 09/07/2026 | nan | nan | 0 | TK_NotStart | 1208363553 | 323 | 1208363553_323
MRPP2-SUP.17940 | TT_Task | EMU - Production Underframe Panels (CRF Parts) - 7th Fleet (6 trainsets) | 10/07/2026 | 23/06/2027 | nan | nan | 0 | TK_NotStart | 1208363553 | 323 | 1208363553_323
MRPP2-SUP.24480 | TT_Task | EMU - DEL Underframe Panels (CRF Parts) - 7th Fleet (6 trainsets) | 28/04/2027 | 14/10/2027 | nan | nan | 0 | TK_NotStart | 1208363553 | 323 | 1208363553_323
MRPP2-SUP.13820 | TT_Task | EMU - PO Roof Corrugation (CRF Parts) - 7th Fleet (6 trainsets) | 12/06/2026 | 09/07/2026 | nan | nan | 0 | TK_NotStart | 1208363553 | 324 | 1208363553_324
MRPP2-SUP.17950 | TT_Task | EMU - Production Roof Corrugation (CRF Parts) - 7th Fleet (6 trainsets) | 10/07/2026 | 23/06/2027 | nan | nan | 0 | TK_NotStart | 1208363553 | 324 | 1208363553_324
MRPP2-SUP.24490 | TT_Task | EMU - DEL Roof Corrugation (CRF Parts) - 7th Fleet (6 trainsets) | 28/04/2027 | 14/10/2027 | nan | nan | 0 | TK_NotStart | 1208363553 | 324 | 1208363553_324
MRPP2-SUP.13830 | TT_Task | EMU - PO Cantrail with Integrated roof gutter (CRF Parts) - 7th Fleet (6 trainsets) | 12/06/2026 | 09/07/2026 | nan | nan | 0 | TK_NotStart | 1208363553 | 325 | 1208363553_325
MRPP2-SUP.17960 | TT_Task | EMU - Production Cantrail with Integrated roof gutter (CRF Parts) - 7th Fleet (6 trainsets) | 10/07/2026 | 23/06/2027 | nan | nan | 0 | TK_NotStart | 1208363553 | 325 | 1208363553_325
MRPP2-SUP.24500 | TT_Task | EMU - DEL Cantrail with Integrated roof gutter (CRF Parts) - 7th Fleet (6 trainsets) | 28/04/2027 | 14/10/2027 | nan | nan | 0 | TK_NotStart | 1208363553 | 325 | 1208363553_325
MRPP2-SUP.13860 | TT_Task | EMU - PO EUF - 7th Fleet (6 trainsets) | 10/07/2026 | 06/08/2026 | nan | nan | 0 | TK_NotStart | 1208363553 | 326 | 1208363553_326
MRPP2-SUP.17990 | TT_Task | EMU - Production EUF - 7th Fleet (6 trainsets) | 07/08/2026 | 23/06/2027 | nan | nan | 0 | TK_NotStart | 1208363553 | 327 | 1208363553_327
MRPP2-SUP.24310 | TT_Task | EMU - DEL EUF delivery - 7th Fleet (6 trainsets) | 12/03/2027 | 01/09/2027 | nan | nan | 0 | TK_NotStart | 1208363553 | 329 | 1208363553_329
MRPP2-SUP.13890 | TT_Task | EMU - PO Carline - 7th Fleet (6 trainsets) | 10/07/2026 | 06/08/2026 | nan | nan | 0 | TK_NotStart | 1208363553 | 330 | 1208363553_330
MRPP2-SUP.18020 | TT_Task | EMU - Production Carline - 7th Fleet (6 trainsets) | 07/08/2026 | 23/06/2027 | nan | nan | 0 | TK_NotStart | 1208363553 | 331 | 1208363553_331
MRPP2-SUP.24350 | TT_Task | EMU - DEL Carline - 7th Fleet (6 trainsets) | 12/03/2027 | 01/09/2027 | nan | nan | 0 | TK_NotStart | 1208363553 | 330 | 1208363553_330
MRPP2-SUP.13900 | TT_Task | EMU - PO Door Frame (CRF section) - 7th Fleet (6 trainsets) | 10/07/2026 | 06/08/2026 | nan | nan | 0 | TK_NotStart | 1208363553 | 332 | 1208363553_332
MRPP2-SUP.18030 | TT_Task | EMU - Production Door Frame (CRF section) - 7th Fleet (6 trainsets) | 07/08/2026 | 23/06/2027 | nan | nan | 0 | TK_NotStart | 1208363553 | 332 | 1208363553_332
MRPP2-SUP.24360 | TT_Task | EMU - DEL Door Frame (CRF section) - 7th Fleet (6 trainsets) | 12/03/2027 | 01/09/2027 | nan | nan | 0 | TK_NotStart | 1208363553 | 332 | 1208363553_332
MRPP2-SUP.13850 | TT_Task | EMU - PO Sidewall (Cut ; Bend Parts) - 7th Fleet (6 trainsets) | 10/07/2026 | 06/08/2026 | nan | nan | 0 | TK_NotStart | 1208363553 | 333 | 1208363553_333
MRPP2-SUP.17980 | TT_Task | EMU - Production Sidewall (Cut ; Bend Parts) - 7th Fleet (6 trainsets) | 07/08/2026 | 23/06/2027 | nan | nan | 0 | TK_NotStart | 1208363553 | 333 | 1208363553_333
MRPP2-SUP.24300 | TT_Task | EMU - DEL Sidewall (Cut ; Bend Parts) - 7th Fleet (6 trainsets) | 29/01/2027 | 21/07/2027 | nan | nan | 0 | TK_NotStart | 1208363553 | 333 | 1208363553_333
MRPP2-SUP.13910 | TT_Task | EMU - PO Letter Board (in Small parts) - 7th Fleet (6 trainsets) | 10/07/2026 | 06/08/2026 | nan | nan | 0 | TK_NotStart | 1208363553 | 336 | 1208363553_336
MRPP2-SUP.18040 | TT_Task | EMU - Production Letter Board (in Small parts) - 7th Fleet (6 trainsets) | 07/08/2026 | 23/06/2027 | nan | nan | 0 | TK_NotStart | 1208363553 | 336 | 1208363553_336
MRPP2-SUP.24370 | TT_Task | EMU - DEL Letter Board (in Small parts) - 7th Fleet (6 trainsets) | 29/01/2027 | 21/07/2027 | nan | nan | 0 | TK_NotStart | 1208363553 | 336 | 1208363553_336
MRPP2-SOU.10780 | TT_Task | EMU - RFQ Bogie Frame | 31/03/2020 | 15/04/2020 | 31/03/2020 | 15/04/2020 | 0 | TK_Complete | 1208363553 | 292 | 1208363553_292
MRPP2-SOU.11310 | TT_Task | EMU - BA Bogie Frame | 16/04/2020 | 07/05/2020 | 16/04/2020 | 07/05/2020 | 0 | TK_Complete | 1208363553 | 292 | 1208363553_292
MRPP2-SUP.10080 | TT_Task | EMU - PO Bogie Frame - 1st Fleet (5 trainsets) | 08/05/2020 | 24/07/2020 | 08/05/2020 | 24/07/2020 | 0 | TK_Complete | 1208363553 | 337 | 1208363553_337
MRPP2-SUP.14230 | TT_Task | EMU - Production Bogie Frame - 1st Fleet (5 trainsets) | 27/07/2020 | 17/05/2021 | 27/07/2020 | 17/05/2021 | 0 | TK_Complete | 1208363553 | 337 | 1208363553_337
MRPP2-SUP.18600 | TT_Task | EMU - FAI Bogie Frame | 04/02/2021 | 03/03/2021 | 04/02/2021 | 03/03/2021 | 0 | TK_Complete | 1208363553 | 338 | 1208363553_338
MRPP2-SUP.19420 | TT_Task | EMU - DEL Bogie Frame delivery - 1st Fleet (5 trainsets) | 04/03/2021 | 19/10/2021 | 04/03/2021 | 19/10/2021 | 0 | TK_Complete | 1208363553 | 339 | 1208363553_339
MRPP2-SOU.10760 | TT_Task | EMU - RFQ Axle box ; bearing | 31/03/2020 | 03/04/2020 | 31/03/2020 | 03/04/2020 | 0 | TK_Complete | 1208363553 | 340 | 1208363553_340
MRPP2-SOU.11270 | TT_Task | EMU - BA Axle box ; bearing | 06/04/2020 | 14/07/2020 | 04/04/2020 | 14/07/2020 | 0 | TK_Complete | 1208363553 | 340 | 1208363553_340
MRPP2-SUP.10150 | TT_Task | EMU - PO Axle box ; bearing - 1st Fleet (5 trainsets) | 15/07/2020 | 05/08/2020 | 15/07/2020 | 05/08/2020 | 0 | TK_Complete | 1208363553 | 341 | 1208363553_341
MRPP2-SUP.14340 | TT_Task | EMU - Production Axle box ; bearing - 1st Fleet (5 trainsets) | 06/08/2020 | 01/06/2021 | 06/08/2020 | 01/06/2021 | 0 | TK_Complete | 1208363553 | 341 | 1208363553_341
MRPP2-SUP.18700 | TT_Task | EMU - FAI Axle box ; bearing | 05/03/2021 | 01/04/2021 | 05/03/2021 | 01/04/2021 | 0 | TK_Complete | 1208363553 | 340 | 1208363553_340
MRPP2-SUP.19530 | TT_Task | EMU - DEL Axle box ; bearing delivery - 1st Fleet (5 trainsets) | 06/04/2021 | 19/10/2021 | 02/04/2021 | 19/10/2021 | 0 | TK_Complete | 1208363553 | 341 | 1208363553_341
MRPP2-SOU.10750 | TT_Task | EMU - RFQ Wheels | 31/03/2020 | 11/05/2020 | 31/03/2020 | 11/05/2020 | 0 | TK_Complete | 1208363553 | 342 | 1208363553_342
MRPP2-SOU.11260 | TT_Task | EMU - BA Wheels | 12/05/2020 | 26/06/2020 | 12/05/2020 | 26/06/2020 | 0 | TK_Complete | 1208363553 | 343 | 1208363553_343
MRPP2-SUP.10140 | TT_Task | EMU - PO Wheels - 1st Fleet (5 trainsets) | 29/06/2020 | 09/10/2020 | 29/06/2020 | 09/10/2020 | 0 | TK_Complete | 1208363553 | 344 | 1208363553_344
MRPP2-SUP.14330 | TT_Task | EMU - Production Wheels - 1st Fleet (5 trainsets) | 12/10/2020 | 09/08/2021 | 12/10/2020 | 09/08/2021 | 0 | TK_Complete | 1208363553 | 344 | 1208363553_344
MRPP2-SUP.18690 | TT_Task | EMU - FAI Wheels | 10/08/2021 | 23/08/2021 | 10/08/2021 | 23/08/2021 | 0 | TK_Complete | 1208363553 | 345 | 1208363553_345
MRPP2-SUP.19520 | TT_Task | EMU - DEL Wheels delivery - 1st Fleet (5 trainsets) | 24/08/2021 | 12/01/2022 | 24/08/2021 | 12/01/2022 | 0 | TK_Complete | 1208363553 | 346 | 1208363553_346
MRPP2-SOU.10810 | TT_Task | EMU - RFQ HVAC | 28/02/2020 | 15/04/2020 | 28/02/2020 | 15/04/2020 | 0 | TK_Complete | 1208363553 | 347 | 1208363553_347
MRPP2-SOU.11390 | TT_Task | EMU - BA HVAC | 16/04/2020 | 04/06/2020 | 16/04/2020 | 04/06/2020 | 0 | TK_Complete | 1208363553 | 309 | 1208363553_309
MRPP2-SUP.10250 | TT_Task | EMU - PO HVAC - 1st Fleet (5 trainsets) | 05/06/2020 | 08/09/2020 | 05/06/2020 | 08/09/2020 | 0 | TK_Complete | 1208363553 | 348 | 1208363553_348
MRPP2-SUP.14380 | TT_Task | EMU - Production HVAC - 1st Fleet (5 trainsets) | 09/09/2020 | 09/08/2021 | 09/09/2020 | 09/08/2021 | 0 | TK_Complete | 1208363553 | 348 | 1208363553_348
MRPP2-SUP.18780 | TT_Task | EMU - FAI HVAC | 10/08/2021 | 28/09/2021 | 10/08/2021 | 28/09/2021 | 0 | TK_Complete | 1208363553 | 309 | 1208363553_309
MRPP2-SUP.20010 | TT_Task | EMU - DEL HVAC delivery - 1st Fleet (5 trainsets) | 24/08/2021 | 12/01/2022 | 24/08/2021 | 12/01/2022 | 0 | TK_Complete | 1208363553 | 349 | 1208363553_349
MRPP2-SOU.10910 | TT_Task | EMU - RFQ Windows | 14/04/2020 | 05/05/2020 | 10/04/2020 | 05/05/2020 | 0 | TK_Complete | 1208363553 | 347 | 1208363553_347
MRPP2-SOU.11520 | TT_Task | EMU - BA Windows | 06/05/2020 | 17/07/2020 | 06/05/2020 | 17/07/2020 | 0 | TK_Complete | 1208363553 | 350 | 1208363553_350
MRPP2-SUP.10380 | TT_Task | EMU - PO Windows - 1st Fleet (5 trainsets) | 20/07/2020 | 13/11/2020 | 20/07/2020 | 13/11/2020 | 0 | TK_Complete | 1208363553 | 351 | 1208363553_351
MRPP2-SUP.14510 | TT_Task | EMU - Production Windows - 1st Fleet (5 trainsets) | 16/11/2020 | 08/04/2021 | 16/11/2020 | 08/04/2021 | 0 | TK_Complete | 1208363553 | 352 | 1208363553_352
MRPP2-SUP.18810 | TT_Task | EMU - FAI Windows | 09/04/2021 | 07/05/2021 | 09/04/2021 | 07/05/2021 | 0 | TK_Complete | 1208363553 | 350 | 1208363553_350
MRPP2-SUP.19910 | TT_Task | EMU - DEL Windows delivery - 1st Fleet (5 trainsets) | 10/05/2021 | 19/10/2021 | 10/05/2021 | 19/10/2021 | 0 | TK_Complete | 1208363553 | 353 | 1208363553_353
MRPP2-SOU.10800 | TT_Task | EMU - RFQ Passenger doors | 14/04/2020 | 05/05/2020 | 13/04/2020 | 13/04/2020 | 0 | TK_Complete | 1208363553 | 310 | 1208363553_310
MRPP2-SOU.11380 | TT_Task | EMU - BA Passenger doors | 14/04/2020 | 27/05/2020 | 14/04/2020 | 27/05/2020 | 0 | TK_Complete | 1208363553 | 310 | 1208363553_310
MRPP2-SUP.10270 | TT_Task | EMU - PO Passenger doors - 1st Fleet (5 trainsets) | 28/05/2020 | 07/08/2020 | 28/05/2020 | 07/08/2020 | 0 | TK_Complete | 1208363553 | 354 | 1208363553_354
MRPP2-SUP.14520 | TT_Task | EMU - Production Passenger doors - 1st Fleet (5 trainsets) | 10/08/2020 | 12/07/2021 | 10/08/2020 | 12/07/2021 | 0 | TK_Complete | 1208363553 | 354 | 1208363553_354
MRPP2-SUP.18840 | TT_Task | EMU - FAI Passenger doors | 13/07/2021 | 08/09/2021 | 13/07/2021 | 08/09/2021 | 0 | TK_Complete | 1208363553 | 310 | 1208363553_310
MRPP2-SUP.20000 | TT_Task | EMU - DEL Passenger doors delivery - 1st Fleet (5 trainsets) | 10/08/2021 | 29/12/2021 | 10/08/2021 | 29/12/2021 | 0 | TK_Complete | 1208363553 | 355 | 1208363553_355
MRPP2-SOU.10730 | TT_Task | EMU - RFQ Axles | 10/03/2020 | 27/03/2020 | 10/03/2020 | 27/03/2020 | 0 | TK_Complete | 1208363553 | 342 | 1208363553_342
MRPP2-SOU.11250 | TT_Task | EMU - BA Axles | 30/03/2020 | 29/05/2020 | 30/03/2020 | 29/05/2020 | 0 | TK_Complete | 1208363553 | 343 | 1208363553_343
MRPP2-SUP.10130 | TT_Task | EMU - PO Axles - 1st Fleet (5 trainsets) | 02/06/2020 | 01/09/2020 | 01/06/2020 | 01/09/2020 | 0 | TK_Complete | 1208363553 | 356 | 1208363553_356
MRPP2-SUP.14320 | TT_Task | EMU - Production Axles - 1st Fleet (5 trainsets) | 02/09/2020 | 26/05/2021 | 02/09/2020 | 26/05/2021 | 0 | TK_Complete | 1208363553 | 356 | 1208363553_356
MRPP2-SUP.18680 | TT_Task | EMU - FAI Axles | 01/03/2021 | 26/03/2021 | 01/03/2021 | 26/03/2021 | 0 | TK_Complete | 1208363553 | 345 | 1208363553_345
MRPP2-SUP.19500 | TT_Task | EMU - DEL Axles delivery - 1st Fleet (5 trainsets) | 29/03/2021 | 19/10/2021 | 29/03/2021 | 19/10/2021 | 0 | TK_Complete | 1208363553 | 357 | 1208363553_357
MRPP2-SOU.10770 | TT_Task | EMU - RFQ Brakes | 06/04/2020 | 14/04/2020 | 06/04/2020 | 14/04/2020 | 0 | TK_Complete | 1208363553 | 296 | 1208363553_296
MRPP2-SOU.11280 | TT_Task | EMU - BA Brakes | 15/04/2020 | 04/06/2020 | 15/04/2020 | 04/06/2020 | 0 | TK_Complete | 1208363553 | 296 | 1208363553_296
MRPP2-SUP.10160 | TT_Task | EMU - PO Brakes - 1st Fleet (5 trainsets) | 05/06/2020 | 08/09/2020 | 05/06/2020 | 08/09/2020 | 0 | TK_Complete | 1208363553 | 358 | 1208363553_358
MRPP2-SUP.14350 | TT_Task | EMU - Production Brakes - 1st Fleet (5 trainsets) | 09/09/2020 | 09/08/2021 | 09/09/2020 | 09/08/2021 | 0 | TK_Complete | 1208363553 | 358 | 1208363553_358
MRPP2-SUP.18710 | TT_Task | EMU - FAI Brakes | 10/08/2021 | 23/08/2021 | 10/08/2021 | 23/08/2021 | 0 | TK_Complete | 1208363553 | 296 | 1208363553_296
MRPP2-SUP.19690 | TT_Task | EMU - DEL Brakes delivery - 1st Fleet (5 trainsets) | 24/08/2021 | 12/01/2022 | 24/08/2021 | 12/01/2022 | 0 | TK_Complete | 1208363553 | 359 | 1208363553_359
MRPP2-SOU.10860 | TT_Task | EMU - RFQ Traction converter | 15/04/2020 | 29/04/2020 | 15/04/2020 | 29/04/2020 | 0 | TK_Complete | 1208363553 | 342 | 1208363553_342
MRPP2-SOU.11360 | TT_Task | EMU - BA Traction converter | 30/04/2020 | 20/05/2020 | 30/04/2020 | 20/05/2020 | 0 | TK_Complete | 1208363553 | 139 | 1208363553_139
MRPP2-SUP.10230 | TT_Task | EMU - PO Traction converter - 1st Fleet (5 trainsets) | 21/05/2020 | 11/06/2020 | 21/05/2020 | 11/06/2020 | 0 | TK_Complete | 1208363553 | 360 | 1208363553_360
MRPP2-SUP.14370 | TT_Task | EMU - Production Traction converter - 1st Fleet (5 trainsets) | 12/06/2020 | 09/08/2021 | 12/06/2020 | 09/08/2021 | 0 | TK_Complete | 1208363553 | 360 | 1208363553_360
MRPP2-SUP.18770 | TT_Task | EMU - FAI Traction converter | 10/08/2021 | 06/09/2021 | 10/08/2021 | 06/09/2021 | 0 | TK_Complete | 1208363553 | 139 | 1208363553_139
MRPP2-SUP.19900 | TT_Task | EMU - DEL Traction converter delivery - 1st Fleet (5 trainsets) | 07/09/2021 | 27/01/2022 | 07/09/2021 | 27/01/2022 | 0 | TK_Complete | 1208363553 | 361 | 1208363553_361
MRPP2-SOU.10840 | TT_Task | EMU - RFQ Traction motor | 31/03/2020 | 15/04/2020 | 31/03/2020 | 15/04/2020 | 0 | TK_Complete | 1208363553 | 342 | 1208363553_342
MRPP2-SOU.11480 | TT_Task | EMU - BA Traction motor | 16/04/2020 | 07/05/2020 | 16/04/2020 | 07/05/2020 | 0 | TK_Complete | 1208363553 | 142 | 1208363553_142
MRPP2-SUP.10200 | TT_Task | EMU - PO Traction motor - 1st Fleet (5 trainsets) | 08/05/2020 | 28/05/2020 | 08/05/2020 | 28/05/2020 | 0 | TK_Complete | 1208363553 | 362 | 1208363553_362
MRPP2-SUP.14300 | TT_Task | EMU - Production Traction motor - 1st Fleet (5 trainsets) | 29/05/2020 | 25/05/2021 | 29/05/2020 | 25/05/2021 | 0 | TK_Complete | 1208363553 | 362 | 1208363553_362
MRPP2-SUP.18670 | TT_Task | EMU - FAI Traction motor | 26/02/2021 | 25/03/2021 | 26/02/2021 | 25/03/2021 | 0 | TK_Complete | 1208363553 | 142 | 1208363553_142
MRPP2-SUP.19600 | TT_Task | EMU - DEL Traction motor delivery - 1st Fleet (5 trainsets) | 26/03/2021 | 19/10/2021 | 26/03/2021 | 19/10/2021 | 0 | TK_Complete | 1208363553 | 363 | 1208363553_363
MRPP2-SOU.10680 | TT_Task | EMU - RFQ Primary Suspension | 06/05/2020 | 15/07/2020 | 06/05/2020 | 15/07/2020 | 0 | TK_Complete | 1208363553 | 294 | 1208363553_294
MRPP2-SOU.11290 | TT_Task | EMU - BA Primary Suspension | 16/07/2020 | 31/07/2020 | 16/07/2020 | 31/07/2020 | 0 | TK_Complete | 1208363553 | 294 | 1208363553_294
MRPP2-SUP.10180 | TT_Task | EMU - PO Primary Suspension - 1st Fleet (5 trainsets) | 31/07/2020 | 04/11/2020 | 31/07/2020 | 04/11/2020 | 0 | TK_Complete | 1208363553 | 364 | 1208363553_364
MRPP2-SUP.14280 | TT_Task | EMU - Production Primary Suspension - 1st Fleet (5 trainsets) | 05/11/2020 | 21/04/2021 | 05/11/2020 | 21/04/2021 | 0 | TK_Complete | 1208363553 | 365 | 1208363553_365
MRPP2-SUP.18630 | TT_Task | EMU - FAI Primary Suspension | 01/04/2021 | 22/04/2021 | 01/04/2021 | 22/04/2021 | 0 | TK_Complete | 1208363553 | 366 | 1208363553_366
MRPP2-SUP.19380 | TT_Task | EMU - DEL Primary Suspension delivery - 1st Fleet (5 trainsets) | 23/04/2021 | 19/10/2021 | 23/04/2021 | 19/10/2021 | 0 | TK_Complete | 1208363553 | 367 | 1208363553_367
MRPP2-SOU.10690 | TT_Task | EMU - RFQ Secondary Suspension | 17/04/2020 | 19/05/2020 | 17/04/2020 | 19/05/2020 | 0 | TK_Complete | 1208363553 | 294 | 1208363553_294
MRPP2-SOU.11300 | TT_Task | EMU - BA Secondary Suspension | 20/05/2020 | 20/07/2020 | 20/05/2020 | 20/07/2020 | 0 | TK_Complete | 1208363553 | 294 | 1208363553_294
MRPP2-SUP.10190 | TT_Task | EMU - PO Secondary Suspension - 1st Fleet (5 trainsets) | 21/07/2020 | 14/12/2020 | 21/07/2020 | 14/12/2020 | 0 | TK_Complete | 1208363553 | 364 | 1208363553_364
MRPP2-SUP.14290 | TT_Task | EMU - Production Secondary Suspension - 1st Fleet (5 trainsets) | 15/12/2020 | 23/08/2021 | 15/12/2020 | 23/08/2021 | 0 | TK_Complete | 1208363553 | 365 | 1208363553_365
MRPP2-SUP.18640 | TT_Task | EMU - FAI Secondary Suspension | 01/04/2021 | 22/04/2021 | 01/04/2021 | 22/04/2021 | 0 | TK_Complete | 1208363553 | 366 | 1208363553_366
MRPP2-SUP.19390 | TT_Task | EMU - DEL Secondary Suspension delivery - 1st Fleet (5 trainsets) | 23/04/2021 | 19/10/2021 | 23/04/2021 | 19/10/2021 | 0 | TK_Complete | 1208363553 | 367 | 1208363553_367
MRPP2-SOU.11060 | TT_Task | EMU - RFQ CVS | 28/02/2020 | 15/04/2020 | 28/02/2020 | 15/04/2020 | 0 | TK_Complete | 1208363553 | 368 | 1208363553_368
MRPP2-SOU.11660 | TT_Task | EMU - BA CVS | 16/04/2020 | 07/05/2020 | 16/04/2020 | 07/05/2020 | 0 | TK_Complete | 1208363553 | 368 | 1208363553_368
MRPP2-SUP.10520 | TT_Task | EMU - PO CVS - 1st Fleet (5 trainsets) | 08/05/2020 | 28/05/2020 | 08/05/2020 | 28/05/2020 | 0 | TK_Complete | 1208363553 | 369 | 1208363553_369
MRPP2-SUP.14650 | TT_Task | EMU - Production CVS - 1st Fleet (5 trainsets) | 29/05/2020 | 23/08/2021 | 29/05/2020 | 23/08/2021 | 0 | TK_Complete | 1208363553 | 370 | 1208363553_370
MRPP2-SUP.18750 | TT_Task | EMU - FAI CVS | 26/03/2021 | 16/04/2021 | 26/03/2021 | 16/04/2021 | 0 | TK_Complete | 1208363553 | 328 | 1208363553_328
MRPP2-SUP.19410 | TT_Task | EMU - DEL CVS delivery - 1st Fleet (5 trainsets) | 19/04/2021 | 19/10/2021 | 19/04/2021 | 19/10/2021 | 0 | TK_Complete | 1208363553 | 371 | 1208363553_371
MRPP2-SOU.10920 | TT_Task | EMU - RFQ Coupler | 09/04/2020 | 09/04/2020 | 09/04/2020 | 09/04/2020 | 0 | TK_Complete | 1208363553 | 308 | 1208363553_308
MRPP2-SOU.11530 | TT_Task | EMU - BA Coupler | 14/04/2020 | 02/06/2020 | 10/04/2020 | 02/06/2020 | 0 | TK_Complete | 1208363553 | 308 | 1208363553_308
MRPP2-SUP.10390 | TT_Task | EMU - PO Coupler - 1st Fleet (5 trainsets) | 03/06/2020 | 08/09/2020 | 03/06/2020 | 08/09/2020 | 0 | TK_Complete | 1208363553 | 372 | 1208363553_372
MRPP2-SUP.14530 | TT_Task | EMU - Production Coupler - 1st Fleet (5 trainsets) | 09/09/2020 | 20/05/2021 | 09/09/2020 | 20/05/2021 | 0 | TK_Complete | 1208363553 | 372 | 1208363553_372
MRPP2-SUP.18550 | TT_Task | EMU - FAI Coupler | 09/03/2021 | 14/04/2021 | 09/03/2021 | 14/04/2021 | 0 | TK_Complete | 1208363553 | 328 | 1208363553_328
MRPP2-SUP.19400 | TT_Task | EMU - DEL Coupler delivery - 1st Fleet (5 trainsets) | 15/04/2021 | 19/10/2021 | 15/04/2021 | 19/10/2021 | 0 | TK_Complete | 1208363553 | 373 | 1208363553_373
MRPP2-SOU.10930 | TT_Task | EMU - RFQ ( Request for Quotation) - Gangway | 14/04/2020 | 28/04/2020 | 10/04/2020 | 13/04/2020 | 0 | TK_Complete | 1208363553 | 307 | 1208363553_307
MRPP2-SOU.11560 | TT_Task | EMU - BA ( Business Award) -Gangway | 14/04/2020 | 02/06/2020 | 14/04/2020 | 02/06/2020 | 0 | TK_Complete | 1208363553 | 307 | 1208363553_307
MRPP2-SUP.10420 | TT_Task | EMU - PO (Purchase Order)-Gangway - 1st Fleet (5 trainsets) | 03/06/2020 | 17/07/2020 | 03/06/2020 | 17/07/2020 | 0 | TK_Complete | 1208363553 | 374 | 1208363553_374
MRPP2-SUP.14540 | TT_Task | EMU - Production ( Component process time)-Gangway - 1st Fleet (5 trainsets) | 20/07/2020 | 09/08/2021 | 20/07/2020 | 09/08/2021 | 0 | TK_Complete | 1208363553 | 375 | 1208363553_375
MRPP2-SUP.18560 | TT_Task | EMU - FAI ( Inspection)-Gangway | 10/08/2021 | 23/08/2021 | 10/08/2021 | 23/08/2021 | 0 | TK_Complete | 1208363553 | 307 | 1208363553_307
MRPP2-SUP.19280 | TT_Task | EMU - DEL Component Delivery-Gangway - 1st Fleet (5 trainsets) | 24/08/2021 | 12/01/2022 | 24/08/2021 | 12/01/2022 | 0 | TK_Complete | 1208363553 | 376 | 1208363553_376
MRPP2-SOU.10720 | TT_Task | EMU - RFQ Pipes | 10/08/2020 | 28/08/2020 | 10/08/2020 | 28/08/2020 | 0 | TK_Complete | 1208363553 | 295 | 1208363553_295
MRPP2-SOU.11350 | TT_Task | EMU - BA Pipes | 31/08/2020 | 18/09/2020 | 31/08/2020 | 18/09/2020 | 0 | TK_Complete | 1208363553 | 295 | 1208363553_295
MRPP2-SUP.10220 | TT_Task | EMU - PO Pipes - 1st Fleet (5 trainsets) | 21/09/2020 | 26/03/2021 | 21/09/2020 | 26/03/2021 | 0 | TK_Complete | 1208363553 | 377 | 1208363553_377
MRPP2-SUP.14360 | TT_Task | EMU - Production Pipes - 1st Fleet (5 trainsets) | 26/03/2021 | 09/08/2021 | 26/03/2021 | 09/08/2021 | 0 | TK_Complete | 1208363553 | 377 | 1208363553_377
MRPP2-SUP.18740 | TT_Task | EMU - FAI Pipes | 10/08/2021 | 23/08/2021 | 10/08/2021 | 23/08/2021 | 0 | TK_Complete | 1208363553 | 295 | 1208363553_295
MRPP2-SUP.19450 | TT_Task | EMU - DEL Pipes delivery - 1st Fleet (5 trainsets) | 24/08/2021 | 12/01/2022 | 24/08/2021 | 12/01/2022 | 0 | TK_Complete | 1208363553 | 378 | 1208363553_378
MRPP2-SOU.10960 | TT_Task | EMU - RFQ Cables | 16/06/2020 | 18/06/2020 | 16/06/2020 | 18/06/2020 | 0 | TK_Complete | 1208363553 | 379 | 1208363553_379
MRPP2-SOU.11490 | TT_Task | EMU - BA Cables | 19/06/2020 | 04/09/2020 | 19/06/2020 | 04/09/2020 | 0 | TK_Complete | 1208363553 | 380 | 1208363553_380
MRPP2-SUP.10360 | TT_Task | EMU - PO Cables - 1st Fleet (5 trainsets) | 07/09/2020 | 20/11/2020 | 07/09/2020 | 20/11/2020 | 0 | TK_Complete | 1208363553 | 381 | 1208363553_381
MRPP2-SUP.14490 | TT_Task | EMU - Production Cables - 1st Fleet (5 trainsets) | 23/11/2020 | 09/08/2021 | 23/11/2020 | 09/08/2021 | 0 | TK_Complete | 1208363553 | 381 | 1208363553_381
MRPP2-SUP.18530 | TT_Task | EMU - FAI Cables | 10/08/2021 | 23/08/2021 | 10/08/2021 | 23/08/2021 | 0 | TK_Complete | 1208363553 | 380 | 1208363553_380
MRPP2-SUP.19510 | TT_Task | EMU - DEL Cables delivery - 1st Fleet (5 trainsets) | 24/08/2021 | 12/01/2022 | 24/08/2021 | 12/01/2022 | 0 | TK_Complete | 1208363553 | 382 | 1208363553_382
MRPP2-SOU.10980 | TT_Task | EMU - RFQ Cable trays | 03/08/2020 | 14/08/2020 | 03/08/2020 | 14/08/2020 | 0 | TK_Complete | 1208363553 | 379 | 1208363553_379
MRPP2-SOU.11400 | TT_Task | EMU - BA Cable trays | 17/08/2020 | 28/10/2020 | 17/08/2020 | 28/10/2020 | 0 | TK_Complete | 1208363553 | 380 | 1208363553_380
MRPP2-SUP.10260 | TT_Task | EMU - PO Cable trays - 1st Fleet (5 trainsets) | 29/10/2020 | 20/11/2020 | 29/10/2020 | 20/11/2020 | 0 | TK_Complete | 1208363553 | 383 | 1208363553_383
MRPP2-SUP.14420 | TT_Task | EMU - Production Cable trays - 1st Fleet (5 trainsets) | 23/11/2020 | 09/08/2021 | 23/11/2020 | 09/08/2021 | 0 | TK_Complete | 1208363553 | 383 | 1208363553_383
MRPP2-SUP.18470 | TT_Task | EMU - FAI Cable trays | 10/08/2021 | 06/09/2021 | 10/08/2021 | 06/09/2021 | 0 | TK_Complete | 1208363553 | 380 | 1208363553_380
MRPP2-SUP.19230 | TT_Task | EMU - DEL Cable trays delivery - 1st Fleet (5 trainsets) | 07/09/2021 | 19/01/2022 | 07/09/2021 | 19/01/2022 | 0 | TK_Complete | 1208363553 | 383 | 1208363553_383
MRPP2-SOU.10880 | TT_Task | EMU - RFQ Floor covering | 28/04/2020 | 06/05/2020 | 28/04/2020 | 06/05/2020 | 0 | TK_Complete | 1208363553 | 299 | 1208363553_299
MRPP2-SOU.11450 | TT_Task | EMU - BA Floor covering | 07/05/2020 | 08/07/2020 | 07/05/2020 | 08/07/2020 | 0 | TK_Complete | 1208363553 | 299 | 1208363553_299
MRPP2-SUP.10330 | TT_Task | EMU - PO Floor covering - 1st Fleet (5 trainsets) | 09/07/2020 | 04/09/2020 | 09/07/2020 | 04/09/2020 | 0 | TK_Complete | 1208363553 | 384 | 1208363553_384
MRPP2-SUP.14450 | TT_Task | EMU - Production Floor covering - 1st Fleet (5 trainsets) | 07/09/2020 | 09/08/2021 | 07/09/2020 | 09/08/2021 | 0 | TK_Complete | 1208363553 | 385 | 1208363553_385
MRPP2-SUP.18500 | TT_Task | EMU - FAI Floor covering | 10/08/2021 | 23/08/2021 | 10/08/2021 | 23/08/2021 | 0 | TK_Complete | 1208363553 | 299 | 1208363553_299
MRPP2-SUP.19150 | TT_Task | EMU - DEL Floor covering delivery - 1st Fleet (5 trainsets) | 24/08/2021 | 12/01/2022 | 24/08/2021 | 12/01/2022 | 0 | TK_Complete | 1208363553 | 386 | 1208363553_386
MRPP2-SOU.11080 | TT_Task | EMU - RFQ Pantograph | 06/04/2020 | 07/04/2020 | 06/04/2020 | 07/04/2020 | 0 | TK_Complete | 1208363553 | 317 | 1208363553_317
MRPP2-SOU.11650 | TT_Task | EMU - BA Pantograph | 08/04/2020 | 11/06/2020 | 08/04/2020 | 11/06/2020 | 0 | TK_Complete | 1208363553 | 317 | 1208363553_317
MRPP2-SUP.10510 | TT_Task | EMU - PO Pantograph - 1st Fleet (5 trainsets) | 12/06/2020 | 25/09/2020 | 12/06/2020 | 25/09/2020 | 0 | TK_Complete | 1208363553 | 387 | 1208363553_387
MRPP2-SUP.14630 | TT_Task | EMU - Production Pantograph - 1st Fleet (5 trainsets) | 29/09/2020 | 09/08/2021 | 28/09/2020 | 09/08/2021 | 0 | TK_Complete | 1208363553 | 387 | 1208363553_387
MRPP2-SUP.18730 | TT_Task | EMU - FAI Pantograph | 10/08/2021 | 23/08/2021 | 10/08/2021 | 23/08/2021 | 0 | TK_Complete | 1208363553 | 317 | 1208363553_317
MRPP2-SUP.19730 | TT_Task | EMU - DEL Pantograph delivery - 1st Fleet (5 trainsets) | 24/08/2021 | 12/01/2022 | 24/08/2021 | 12/01/2022 | 0 | TK_Complete | 1208363553 | 388 | 1208363553_388
MRPP2-SOU.10820 | TT_Task | EMU - RFQ Wind screen | 28/04/2020 | 05/05/2020 | 28/04/2020 | 05/05/2020 | 0 | TK_Complete | 1208363553 | 297 | 1208363553_297
MRPP2-SOU.11410 | TT_Task | EMU - BA Wind screen | 06/05/2020 | 17/07/2020 | 06/05/2020 | 17/07/2020 | 0 | TK_Complete | 1208363553 | 297 | 1208363553_297
MRPP2-SUP.10290 | TT_Task | EMU - PO Wind screen - 1st Fleet (5 trainsets) | 20/07/2020 | 13/11/2020 | 20/07/2020 | 13/11/2020 | 0 | TK_Complete | 1208363553 | 389 | 1208363553_389
MRPP2-SUP.14430 | TT_Task | EMU - Production Wind screen - 1st Fleet (5 trainsets) | 16/11/2020 | 09/08/2021 | 16/11/2020 | 09/08/2021 | 0 | TK_Complete | 1208363553 | 389 | 1208363553_389
MRPP2-SUP.18480 | TT_Task | EMU - FAI Wind screen | 10/08/2021 | 23/08/2021 | 10/08/2021 | 23/08/2021 | 0 | TK_Complete | 1208363553 | 297 | 1208363553_297
MRPP2-SUP.19270 | TT_Task | EMU - DEL Wind screen delivery - 1st Fleet (5 trainsets) | 24/08/2021 | 12/01/2022 | 24/08/2021 | 12/01/2022 | 0 | TK_Complete | 1208363553 | 390 | 1208363553_390
MRPP2-SOU.11070 | TT_Task | EMU - RFQ Front mask | 29/09/2020 | 19/10/2020 | 29/09/2020 | 19/10/2020 | 0 | TK_Complete | 1208363553 | 319 | 1208363553_319
MRPP2-SOU.11640 | TT_Task | EMU - BA Front mask | 20/10/2020 | 18/12/2020 | 20/10/2020 | 18/12/2020 | 0 | TK_Complete | 1208363553 | 319 | 1208363553_319
MRPP2-SUP.10500 | TT_Task | EMU - PO Front mask - 1st Fleet (5 trainsets) | 21/12/2020 | 16/03/2021 | 21/12/2020 | 16/03/2021 | 0 | TK_Complete | 1208363553 | 391 | 1208363553_391
MRPP2-SUP.14620 | TT_Task | EMU - Production Front mask - 1st Fleet (5 trainsets) | 17/03/2021 | 13/05/2021 | 17/03/2021 | 13/05/2021 | 0 | TK_Complete | 1208363553 | 391 | 1208363553_391
MRPP2-SUP.18720 | TT_Task | EMU - FAI Front mask | 16/03/2021 | 06/04/2021 | 16/03/2021 | 06/04/2021 | 0 | TK_Complete | 1208363553 | 319 | 1208363553_319
MRPP2-SUP.19550 | TT_Task | EMU - DEL Front mask delivery - 1st Fleet (5 trainsets) | 14/05/2021 | 19/10/2021 | 14/05/2021 | 19/10/2021 | 0 | TK_Complete | 1208363553 | 392 | 1208363553_392
MRPP2-SOU.10970 | TT_Task | EMU - RFQ Relays | 10/08/2020 | 04/09/2020 | 10/08/2020 | 04/09/2020 | 0 | TK_Complete | 1208363553 | 347 | 1208363553_347
MRPP2-SOU.11550 | TT_Task | EMU - BA Relays | 07/09/2020 | 05/10/2020 | 07/09/2020 | 05/10/2020 | 0 | TK_Complete | 1208363553 | 312 | 1208363553_312
MRPP2-SUP.10410 | TT_Task | EMU - PO Relays - 1st Fleet (5 trainsets) | 06/10/2020 | 20/11/2020 | 06/10/2020 | 20/11/2020 | 0 | TK_Complete | 1208363553 | 393 | 1208363553_393
MRPP2-SUP.14570 | TT_Task | EMU - Production Relays - 1st Fleet (5 trainsets) | 23/11/2020 | 09/08/2021 | 23/11/2020 | 09/08/2021 | 0 | TK_Complete | 1208363553 | 393 | 1208363553_393
MRPP2-SUP.18590 | TT_Task | EMU - FAI Relays | 10/08/2021 | 23/08/2021 | 10/08/2021 | 23/08/2021 | 0 | TK_Complete | 1208363553 | 312 | 1208363553_312
MRPP2-SUP.19220 | TT_Task | EMU - DEL Relays delivery - 1st Fleet (5 trainsets) | 31/08/2021 | 19/01/2022 | 31/08/2021 | 19/01/2022 | 0 | TK_Complete | 1208363553 | 394 | 1208363553_394
MRPP2-SOU.11000 | TT_Task | EMU - RFQ Cabinets | 10/08/2020 | 28/08/2020 | 10/08/2020 | 28/08/2020 | 0 | TK_Complete | 1208363553 | 315 | 1208363553_315
MRPP2-SOU.11580 | TT_Task | EMU - BA Cabinets | 31/08/2020 | 28/10/2020 | 31/08/2020 | 28/10/2020 | 0 | TK_Complete | 1208363553 | 315 | 1208363553_315
MRPP2-SUP.10440 | TT_Task | EMU - PO Cabinets - 1st Fleet (5 trainsets) | 29/10/2020 | 20/11/2020 | 29/10/2020 | 20/11/2020 | 0 | TK_Complete | 1208363553 | 395 | 1208363553_395
MRPP2-SUP.14610 | TT_Task | EMU - Production Cabinets - 1st Fleet (5 trainsets) | 23/11/2020 | 09/08/2021 | 23/11/2020 | 09/08/2021 | 0 | TK_Complete | 1208363553 | 395 | 1208363553_395
MRPP2-SUP.18660 | TT_Task | EMU - FAI Cabinets | 10/08/2021 | 23/08/2021 | 10/08/2021 | 23/08/2021 | 0 | TK_Complete | 1208363553 | 315 | 1208363553_315
MRPP2-SUP.19430 | TT_Task | EMU - DEL Cabinets delivery - 1st Fleet (5 trainsets) | 24/08/2021 | 12/01/2022 | 24/08/2021 | 12/01/2022 | 0 | TK_Complete | 1208363553 | 396 | 1208363553_396
MRPP2-SOU.10950 | TT_Task | EMU - RFQ Elec comp | 10/08/2020 | 28/08/2020 | 10/08/2020 | 28/08/2020 | 0 | TK_Complete | 1208363553 | 347 | 1208363553_347
MRPP2-SOU.11540 | TT_Task | EMU - BA Elec comp | 31/08/2020 | 18/09/2020 | 31/08/2020 | 18/09/2020 | 0 | TK_Complete | 1208363553 | 311 | 1208363553_311
MRPP2-SUP.10400 | TT_Task | EMU - PO Elec comp - 1st Fleet (5 trainsets) | 21/09/2020 | 20/11/2020 | 21/09/2020 | 20/11/2020 | 0 | TK_Complete | 1208363553 | 397 | 1208363553_397
MRPP2-SUP.14560 | TT_Task | EMU - Production Elec comp - 1st Fleet (5 trainsets) | 23/11/2020 | 09/08/2021 | 23/11/2020 | 09/08/2021 | 0 | TK_Complete | 1208363553 | 398 | 1208363553_398
MRPP2-SUP.18580 | TT_Task | EMU - FAI Elec comp | 10/08/2021 | 23/08/2021 | 10/08/2021 | 23/08/2021 | 0 | TK_Complete | 1208363553 | 328 | 1208363553_328
MRPP2-SUP.19210 | TT_Task | EMU - DEL Elec comp delivery - 1st Fleet (5 trainsets) | 24/08/2021 | 12/01/2022 | 24/08/2021 | 12/01/2022 | 0 | TK_Complete | 1208363553 | 399 | 1208363553_399
MRPP2-SOU.11010 | TT_Task | EMU - RFQ LV box | 10/08/2020 | 28/08/2020 | 10/08/2020 | 28/08/2020 | 0 | TK_Complete | 1208363553 | 306 | 1208363553_306
MRPP2-SOU.11590 | TT_Task | EMU - BA LV box | 17/08/2020 | 16/10/2020 | 17/08/2020 | 16/10/2020 | 0 | TK_Complete | 1208363553 | 306 | 1208363553_306
MRPP2-SUP.10450 | TT_Task | EMU - PO LV box - 1st Fleet (5 trainsets) | 19/10/2020 | 20/11/2020 | 19/10/2020 | 20/11/2020 | 0 | TK_Complete | 1208363553 | 400 | 1208363553_400
MRPP2-SUP.14550 | TT_Task | EMU - Production LV box - 1st Fleet (5 trainsets) | 23/11/2020 | 09/08/2021 | 23/11/2020 | 09/08/2021 | 0 | TK_Complete | 1208363553 | 400 | 1208363553_400
MRPP2-SUP.18570 | TT_Task | EMU - FAI LV box | 10/08/2021 | 15/10/2021 | 10/08/2021 | 15/10/2021 | 0 | TK_Complete | 1208363553 | 328 | 1208363553_328
MRPP2-SUP.19290 | TT_Task | EMU - DEL LV box delivery - 1st Fleet (5 trainsets) | 30/08/2021 | 19/01/2022 | 30/08/2021 | 19/01/2022 | 0 | TK_Complete | 1208363553 | 401 | 1208363553_401
MRPP2-SOU.11020 | TT_Task | EMU - RFQ Battery ; battery box | 03/04/2020 | 15/04/2020 | 03/04/2020 | 15/04/2020 | 0 | TK_Complete | 1208363553 | 314 | 1208363553_314
MRPP2-SOU.11600 | TT_Task | EMU - BA Battery ; battery box | 20/04/2020 | 19/06/2020 | 20/04/2020 | 19/06/2020 | 0 | TK_Complete | 1208363553 | 314 | 1208363553_314
MRPP2-SUP.10370 | TT_Task | EMU - PO Battery ; battery box | 22/06/2020 | 25/09/2020 | 22/06/2020 | 25/09/2020 | 0 | TK_Complete | 1208363553 | 314 | 1208363553_314
MRPP2-SUP.14500 | TT_Task | EMU - Production Battery ; battery box | 29/09/2020 | 08/11/2021 | 29/09/2020 | 08/11/2021 | 0 | TK_Complete | 1208363553 | 314 | 1208363553_314
MRPP2-SUP.18540 | TT_Task | EMU - FAI Battery ; battery box | 09/11/2021 | 22/11/2021 | 09/11/2021 | 22/11/2021 | 0 | TK_Complete | 1208363553 | 314 | 1208363553_314
MRPP2-SUP.19250 | TT_Task | EMU - DEL Battery ; battery box delivery - 1st Fleet (5 trainsets) | 24/08/2021 | 12/01/2022 | 24/08/2021 | 12/01/2022 | 0 | TK_Complete | 1208363553 | 402 | 1208363553_402
MRPP2-SOU.10740 | TT_Task | EMU - RFQ Crash box | 10/08/2020 | 04/09/2020 | 10/08/2020 | 04/09/2020 | 0 | TK_Complete | 1208363553 | 347 | 1208363553_347
MRPP2-SOU.11370 | TT_Task | EMU - BA Crash box | 07/09/2020 | 15/12/2020 | 07/09/2020 | 15/12/2020 | 0 | TK_Complete | 1208363553 | 305 | 1208363553_305
MRPP2-SUP.10240 | TT_Task | EMU - PO Crash box - 1st Fleet (5 trainsets) | 16/12/2020 | 08/02/2021 | 16/12/2020 | 08/02/2021 | 0 | TK_Complete | 1208363553 | 403 | 1208363553_403
MRPP2-SUP.14410 | TT_Task | EMU - Production Crash box - 1st Fleet (5 trainsets) | 09/02/2021 | 09/08/2021 | 09/02/2021 | 09/08/2021 | 0 | TK_Complete | 1208363553 | 403 | 1208363553_403
MRPP2-SUP.18460 | TT_Task | EMU - FAI Crash box | 10/08/2021 | 23/08/2021 | 10/08/2021 | 23/08/2021 | 0 | TK_Complete | 1208363553 | 305 | 1208363553_305
MRPP2-SUP.19140 | TT_Task | EMU - DEL Crash box delivery - 1st Fleet (5 trainsets) | 24/08/2021 | 12/01/2022 | 24/08/2021 | 12/01/2022 | 0 | TK_Complete | 1208363553 | 404 | 1208363553_404
MRPP2-SOU.11130 | TT_Task | EMU - RFQ Interior and lighting | 29/09/2020 | 19/10/2020 | 29/09/2020 | 19/10/2020 | 0 | TK_Complete | 1208363553 | 405 | 1208363553_405
MRPP2-SOU.11680 | TT_Task | EMU - BA Interior and lighting | 20/10/2020 | 29/01/2021 | 20/10/2020 | 29/01/2021 | 0 | TK_Complete | 1208363553 | 405 | 1208363553_405
MRPP2-SUP.10540 | TT_Task | EMU - PO Interior and lighting - 1st Fleet (5 trainsets) | 01/02/2021 | 26/03/2021 | 01/02/2021 | 26/03/2021 | 0 | TK_Complete | 1208363553 | 406 | 1208363553_406
MRPP2-SUP.14690 | TT_Task | EMU - Production Interior and lighting - 1st Fleet (5 trainsets) | 01/04/2021 | 09/08/2021 | 01/04/2021 | 09/08/2021 | 0 | TK_Complete | 1208363553 | 407 | 1208363553_407
MRPP2-SUP.18830 | TT_Task | EMU - FAI Interior and lighting | 10/08/2021 | 23/08/2021 | 10/08/2021 | 23/08/2021 | 0 | TK_Complete | 1208363553 | 405 | 1208363553_405
MRPP2-SUP.19850 | TT_Task | EMU - DEL Interior and lighting delivery - 1st Fleet (5 trainsets) | 24/08/2021 | 12/01/2022 | 24/08/2021 | 12/01/2022 | 0 | TK_Complete | 1208363553 | 407 | 1208363553_407
MRPP2-SOU.10870 | TT_Task | EMU - RFQ Hand rails | 29/09/2020 | 19/10/2020 | 29/09/2020 | 19/10/2020 | 0 | TK_Complete | 1208363553 | 302 | 1208363553_302
MRPP2-SOU.11440 | TT_Task | EMU - BA Hand rails | 20/10/2020 | 29/01/2021 | 20/10/2020 | 29/01/2021 | 0 | TK_Complete | 1208363553 | 302 | 1208363553_302
MRPP2-SUP.10320 | TT_Task | EMU - PO Hand rails - 1st Fleet (5 trainsets) | 01/02/2021 | 16/03/2021 | 01/02/2021 | 16/03/2021 | 0 | TK_Complete | 1208363553 | 408 | 1208363553_408
MRPP2-SUP.14390 | TT_Task | EMU - Production Hand rails - 1st Fleet (5 trainsets) | 17/03/2021 | 22/11/2021 | 17/03/2021 | 22/11/2021 | 0 | TK_Complete | 1208363553 | 408 | 1208363553_408
MRPP2-SUP.18440 | TT_Task | EMU - FAI Hand rails | 18/01/2022 | 01/02/2022 | 18/01/2022 | 01/02/2022 | 0 | TK_Complete | 1208363553 | 302 | 1208363553_302
MRPP2-SUP.19130 | TT_Task | EMU - DEL Hand rails delivery - 1st Fleet (5 trainsets) | 24/08/2021 | 12/01/2022 | 24/08/2021 | 12/01/2022 | 0 | TK_Complete | 1208363553 | 409 | 1208363553_409
MRPP2-SOU.10850 | TT_Task | EMU - RFQ Grabpoles and grab handles | 29/09/2020 | 19/10/2020 | 29/09/2020 | 19/10/2020 | 0 | TK_Complete | 1208363553 | 301 | 1208363553_301
MRPP2-SOU.11430 | TT_Task | EMU - BA Grabpoles and grab handles | 20/10/2020 | 29/01/2021 | 20/10/2020 | 29/01/2021 | 0 | TK_Complete | 1208363553 | 301 | 1208363553_301
MRPP2-SUP.10310 | TT_Task | EMU - PO Grabpoles and grab handles - 1st Fleet (5 trainsets) | 01/02/2021 | 16/03/2021 | 01/02/2021 | 16/03/2021 | 0 | TK_Complete | 1208363553 | 410 | 1208363553_410
MRPP2-SUP.14440 | TT_Task | EMU - Production Grabpoles and grab handles - 1st Fleet (5 trainsets) | 17/03/2021 | 22/11/2021 | 17/03/2021 | 22/11/2021 | 0 | TK_Complete | 1208363553 | 410 | 1208363553_410
MRPP2-SUP.18490 | TT_Task | EMU - FAI Grabpoles and grab handles | 23/11/2021 | 10/12/2021 | 23/11/2021 | 10/12/2021 | 0 | TK_Complete | 1208363553 | 301 | 1208363553_301
MRPP2-SUP.19170 | TT_Task | EMU - DEL Grabpoles and grab handles delivery - 1st Fleet (5 trainsets) | 24/08/2021 | 12/01/2022 | 24/08/2021 | 12/01/2022 | 0 | TK_Complete | 1208363553 | 410 | 1208363553_410
MRPP2-SOU.10900 | TT_Task | EMU - RFQ Cab garnishing | 29/09/2020 | 08/10/2020 | 29/09/2020 | 08/10/2020 | 0 | TK_Complete | 1208363553 | 300 | 1208363553_300
MRPP2-SOU.11470 | TT_Task | EMU - BA Cab garnishing | 08/10/2020 | 29/10/2020 | 08/10/2020 | 29/10/2020 | 0 | TK_Complete | 1208363553 | 300 | 1208363553_300
MRPP2-SUP.10350 | TT_Task | EMU - PO Cab garnishing - 1st Fleet (5 trainsets) | 30/10/2020 | 12/11/2020 | 30/10/2020 | 12/11/2020 | 0 | TK_Complete | 1208363553 | 411 | 1208363553_411
MRPP2-SUP.14400 | TT_Task | EMU - Production Cab garnishing - 1st Fleet (5 trainsets) | 13/11/2020 | 01/11/2021 | 13/11/2020 | 01/11/2021 | 0 | TK_Complete | 1208363553 | 411 | 1208363553_411
MRPP2-SUP.18450 | TT_Task | EMU - FAI Cab garnishing | 02/11/2021 | 10/12/2021 | 02/11/2021 | 10/12/2021 | 0 | TK_Complete | 1208363553 | 300 | 1208363553_300
MRPP2-SUP.19160 | TT_Task | EMU - DEL Cab garnishing delivery - 1st Fleet (5 trainsets) | 30/08/2021 | 18/01/2022 | 30/08/2021 | 18/01/2022 | 0 | TK_Complete | 1208363553 | 411 | 1208363553_411
MRPP2-SOU.10890 | TT_Task | EMU - RFQ Seats | 09/04/2020 | 24/04/2020 | 09/04/2020 | 24/04/2020 | 0 | TK_Complete | 1208363553 | 304 | 1208363553_304
MRPP2-SOU.11460 | TT_Task | EMU - BA Seats | 28/04/2020 | 27/05/2020 | 27/04/2020 | 27/05/2020 | 0 | TK_Complete | 1208363553 | 304 | 1208363553_304
MRPP2-SUP.10340 | TT_Task | EMU - PO Seats - 1st Fleet (5 trainsets) | 28/05/2020 | 07/08/2020 | 28/05/2020 | 07/08/2020 | 0 | TK_Complete | 1208363553 | 412 | 1208363553_412
MRPP2-SUP.14480 | TT_Task | EMU - Production Seats - 1st Fleet (5 trainsets) | 10/08/2020 | 22/11/2021 | 10/08/2020 | 22/11/2021 | 0 | TK_Complete | 1208363553 | 412 | 1208363553_412
MRPP2-SUP.18520 | TT_Task | EMU - FAI Seats | 23/11/2021 | 10/12/2021 | 23/11/2021 | 10/12/2021 | 0 | TK_Complete | 1208363553 | 304 | 1208363553_304
MRPP2-SUP.19310 | TT_Task | EMU - DEL Seats delivery - 1st Fleet (5 trainsets) | 24/08/2021 | 12/01/2022 | 24/08/2021 | 12/01/2022 | 0 | TK_Complete | 1208363553 | 413 | 1208363553_413
MRPP2-SOU.10990 | TT_Task | EMU - RFQ PACIS | 09/04/2020 | 09/04/2020 | 09/04/2020 | 09/04/2020 | 0 | TK_Complete | 1208363553 | 316 | 1208363553_316
MRPP2-SOU.11570 | TT_Task | EMU - BA PACIS | 14/04/2020 | 28/05/2020 | 14/04/2020 | 28/05/2020 | 0 | TK_Complete | 1208363553 | 316 | 1208363553_316
MRPP2-SUP.10430 | TT_Task | EMU - PO PACIS - 1st Fleet (5 trainsets) | 29/05/2020 | 07/08/2020 | 29/05/2020 | 07/08/2020 | 0 | TK_Complete | 1208363553 | 414 | 1208363553_414
MRPP2-SUP.14580 | TT_Task | EMU - Production PACIS - 1st Fleet (5 trainsets) | 10/08/2020 | 09/08/2021 | 10/08/2020 | 09/08/2021 | 0 | TK_Complete | 1208363553 | 414 | 1208363553_414
MRPP2-SUP.18760 | TT_Task | EMU - FAI PACIS | 10/08/2021 | 23/08/2021 | 10/08/2021 | 23/08/2021 | 0 | TK_Complete | 1208363553 | 328 | 1208363553_328
MRPP2-SUP.19460 | TT_Task | EMU - DEL PACIS delivery - 1st Fleet (5 trainsets) | 24/08/2021 | 12/01/2022 | 24/08/2021 | 12/01/2022 | 0 | TK_Complete | 1208363553 | 415 | 1208363553_415
MRPP2-SOU.10830 | TT_Task | EMU - RFQ MCP | 21/04/2020 | 07/05/2020 | 21/04/2020 | 07/05/2020 | 0 | TK_Complete | 1208363553 | 347 | 1208363553_347
MRPP2-SOU.11420 | TT_Task | EMU - BA MCP | 08/05/2020 | 08/07/2020 | 08/05/2020 | 08/07/2020 | 0 | TK_Complete | 1208363553 | 416 | 1208363553_416
MRPP2-SUP.10300 | TT_Task | EMU - PO MCP - 1st Fleet (5 trainsets) | 09/07/2020 | 27/10/2020 | 09/07/2020 | 27/10/2020 | 0 | TK_Complete | 1208363553 | 417 | 1208363553_417
MRPP2-SUP.14470 | TT_Task | EMU - Production MCP - 1st Fleet (5 trainsets) | 28/10/2020 | 06/08/2021 | 28/10/2020 | 06/08/2021 | 0 | TK_Complete | 1208363553 | 418 | 1208363553_418
MRPP2-SUP.18510 | TT_Task | EMU - FAI MCP | 12/10/2021 | 25/10/2021 | 12/10/2021 | 25/10/2021 | 0 | TK_Complete | 1208363553 | 416 | 1208363553_416
MRPP2-SUP.19260 | TT_Task | EMU - DEL MCP delivery - 1st Fleet (5 trainsets) | 23/08/2021 | 11/01/2022 | 23/08/2021 | 11/01/2022 | 0 | TK_Complete | 1208363553 | 419 | 1208363553_419
MRPP2-SOU.11030 | TT_Task | EMU - RFQ TCMS equipment | 07/05/2020 | 04/06/2020 | 07/05/2020 | 04/06/2020 | 0 | TK_Complete | 1208363553 | 420 | 1208363553_420
MRPP2-SOU.11610 | TT_Task | EMU - BA TCMS equipment | 05/06/2020 | 02/07/2020 | 05/06/2020 | 02/07/2020 | 0 | TK_Complete | 1208363553 | 420 | 1208363553_420
MRPP2-SUP.10470 | TT_Task | EMU - PO TCMS equipment - 1st Fleet (5 trainsets) | 03/07/2020 | 07/08/2020 | 03/07/2020 | 07/08/2020 | 0 | TK_Complete | 1208363553 | 421 | 1208363553_421
MRPP2-SUP.14590 | TT_Task | EMU - Production TCMS equipment - 1st Fleet (5 trainsets) | 10/08/2020 | 11/08/2021 | 10/08/2020 | 11/08/2021 | 0 | TK_Complete | 1208363553 | 422 | 1208363553_422
MRPP2-SUP.18620 | TT_Task | EMU - FAI TCMS equipment | 12/08/2021 | 25/08/2021 | 12/08/2021 | 25/08/2021 | 0 | TK_Complete | 1208363553 | 420 | 1208363553_420
MRPP2-SUP.19560 | TT_Task | EMU - DEL TCMS equipment delivery - 1st Fleet (5 trainsets) | 26/08/2021 | 14/01/2022 | 26/08/2021 | 14/01/2022 | 0 | TK_Complete | 1208363553 | 422 | 1208363553_422
MRPP2-SUP.27120 | TT_Task | EMU - FAI Transformer | 04/05/2021 | 14/05/2021 | 04/05/2021 | 14/05/2021 | 0 | TK_Complete | 1208363553 | 345 | 1208363553_345
MRPP2-SUP.27130 | TT_Task | EMU - FAI VCB | 12/08/2021 | 24/09/2021 | 12/08/2021 | 24/09/2021 | 0 | TK_Complete | 1208363553 | 328 | 1208363553_328
MRPP2-SUP.27140 | TT_Task | EMU - FAI Gearbox | 12/08/2021 | 25/08/2021 | 12/08/2021 | 25/08/2021 | 0 | TK_Complete | 1208363553 | 345 | 1208363553_345
MRPP2-SUP.27150 | TT_Task | EMU - FAI Completed Bogie | 12/08/2021 | 12/10/2021 | 12/08/2021 | 12/10/2021 | 0 | TK_Complete | 1208363553 | 338 | 1208363553_338
MRPP2-SUP.11120 | TT_Task | EMU - PO Bogie Frame - 2nd Fleet (6 trainsets) | 28/01/2022 | 24/02/2022 | 06/12/2021 | 03/01/2022 | 0 | TK_Complete | 1208363553 | 337 | 1208363553_337
MRPP2-SUP.15250 | TT_Task | EMU - Production Bogie Frame - 2nd Fleet (6 trainsets) | 25/02/2022 | 08/05/2023 | 04/01/2022 | nan | 0 | TK_Active | 1208363553 | 337 | 1208363553_337
MRPP2-SUP.21080 | TT_Task | EMU - DEL Bogie Frame delivery - 2nd Fleet (6 trainsets) | 02/11/2022 | 27/04/2023 | nan | nan | 0 | TK_NotStart | 1208363553 | 339 | 1208363553_339
MRPP2-SUP.11140 | TT_Task | EMU - PO Bogie Assy - 2nd Fleet (6 trainsets) | 28/01/2022 | 24/02/2022 | 06/12/2021 | 03/01/2022 | 0 | TK_Complete | 1208363553 | 423 | 1208363553_423
MRPP2-SUP.15270 | TT_Task | EMU - Production Bogie Assy - 2nd Fleet (6 trainsets) | 25/02/2022 | 08/05/2023 | 04/01/2022 | nan | 0 | TK_Active | 1208363553 | 423 | 1208363553_423
MRPP2-SUP.21100 | TT_Task | EMU - DEL Bogie Assy delivery - 2nd Fleet (6 trainsets) | 02/11/2022 | 27/04/2023 | nan | nan | 0 | TK_NotStart | 1208363553 | 339 | 1208363553_339
MRPP2-SUP.11130 | TT_Task | EMU - PO Axle box ; bearing - 2nd Fleet (6 trainsets) | 28/01/2022 | 24/02/2022 | 06/12/2021 | 03/01/2022 | 0 | TK_Complete | 1208363553 | 341 | 1208363553_341
MRPP2-SUP.15260 | TT_Task | EMU - Production Axle box ; bearing - 2nd Fleet (6 trainsets) | 25/02/2022 | 08/05/2023 | 04/01/2022 | nan | 0 | TK_Active | 1208363553 | 341 | 1208363553_341
MRPP2-SUP.21090 | TT_Task | EMU - DEL Axle box ; bearing delivery - 2nd Fleet (6 trainsets) | 14/12/2022 | 09/06/2023 | nan | nan | 0 | TK_NotStart | 1208363553 | 341 | 1208363553_341
MRPP2-SUP.11110 | TT_Task | EMU - PO Wheels - 2nd Fleet (6 trainsets) | 28/01/2022 | 24/02/2022 | 04/01/2022 | 01/02/2022 | 0 | TK_Complete | 1208363553 | 344 | 1208363553_344
MRPP2-SUP.15240 | TT_Task | EMU - Production Wheels - 2nd Fleet (6 trainsets) | 09/03/2022 | 18/05/2023 | 02/02/2022 | nan | 0 | TK_Active | 1208363553 | 344 | 1208363553_344
MRPP2-SUP.21070 | TT_Task | EMU - DEL Wheels delivery - 2nd Fleet (6 trainsets) | 16/01/2023 | 07/07/2023 | nan | nan | 0 | TK_NotStart | 1208363553 | 346 | 1208363553_346
MRPP2-SUP.11100 | TT_Task | EMU - PO Axles - 2nd Fleet (6 trainsets) | 28/01/2022 | 24/02/2022 | 04/01/2022 | 01/02/2022 | 0 | TK_Complete | 1208363553 | 356 | 1208363553_356
MRPP2-SUP.15230 | TT_Task | EMU - Production Axles - 2nd Fleet (6 trainsets) | 09/03/2022 | 18/05/2023 | 02/02/2022 | nan | 0 | TK_Active | 1208363553 | 356 | 1208363553_356
MRPP2-SUP.21060 | TT_Task | EMU - DEL Axles delivery - 2nd Fleet (6 trainsets) | 16/01/2023 | 07/07/2023 | nan | nan | 0 | TK_NotStart | 1208363553 | 357 | 1208363553_357
MRPP2-SUP.11160 | TT_Task | EMU - PO Brakes - 2nd Fleet (6 trainsets) | 04/03/2022 | 31/03/2022 | 02/02/2022 | 01/03/2022 | 0 | TK_Complete | 1208363553 | 358 | 1208363553_358
MRPP2-SUP.15290 | TT_Task | EMU - Production Brakes - 2nd Fleet (6 trainsets) | 01/04/2022 | 13/06/2023 | 02/03/2022 | nan | 0 | TK_Active | 1208363553 | 358 | 1208363553_358
MRPP2-SUP.21220 | TT_Task | EMU - DEL Brakes delivery - 2nd Fleet (6 trainsets) | 14/02/2023 | 04/08/2023 | nan | nan | 0 | TK_NotStart | 1208363553 | 359 | 1208363553_359
MRPP2-SUP.11190 | TT_Task | EMU - PO Traction converter - 2nd Fleet (6 trainsets) | 04/03/2022 | 31/03/2022 | 02/02/2022 | 01/03/2022 | 0 | TK_Complete | 1208363553 | 360 | 1208363553_360
MRPP2-SUP.15320 | TT_Task | EMU - Production Traction converter - 2nd Fleet (6 trainsets) | 01/04/2022 | 13/06/2023 | 02/03/2022 | nan | 0 | TK_Active | 1208363553 | 360 | 1208363553_360
MRPP2-SUP.21300 | TT_Task | EMU - DEL Traction converter delivery - 2nd Fleet (6 trainsets) | 14/02/2023 | 04/08/2023 | nan | nan | 0 | TK_NotStart | 1208363553 | 361 | 1208363553_361
MRPP2-SUP.11180 | TT_Task | EMU - PO Traction motor - 2nd Fleet (6 trainsets) | 04/03/2022 | 31/03/2022 | 02/02/2022 | 01/03/2022 | 0 | TK_Complete | 1208363553 | 362 | 1208363553_362
MRPP2-SUP.15310 | TT_Task | EMU - Production Traction motor - 2nd Fleet (6 trainsets) | 01/04/2022 | 13/06/2023 | 02/03/2022 | nan | 0 | TK_Active | 1208363553 | 362 | 1208363553_362
MRPP2-SUP.21290 | TT_Task | EMU - DEL Traction motor delivery - 2nd Fleet (6 trainsets) | 14/02/2023 | 04/08/2023 | nan | nan | 0 | TK_NotStart | 1208363553 | 363 | 1208363553_363
MRPP2-SUP.11200 | TT_Task | EMU - PO Primary Suspension - 2nd Fleet (6 trainsets) | 04/03/2022 | 31/03/2022 | 02/02/2022 | 01/03/2022 | 0 | TK_Complete | 1208363553 | 364 | 1208363553_364
MRPP2-SUP.15330 | TT_Task | EMU - Production Primary Suspension - 2nd Fleet (6 trainsets) | 01/04/2022 | 13/06/2023 | 02/03/2022 | nan | 0 | TK_Active | 1208363553 | 365 | 1208363553_365
MRPP2-SUP.21340 | TT_Task | EMU - DEL Primary Suspension delivery - 2nd Fleet (6 trainsets) | 14/02/2023 | 04/08/2023 | nan | nan | 0 | TK_NotStart | 1208363553 | 367 | 1208363553_367
MRPP2-SUP.11210 | TT_Task | EMU - PO Secondary Suspension - 2nd Fleet (6 trainsets) | 04/03/2022 | 31/03/2022 | 02/02/2022 | 01/03/2022 | 0 | TK_Complete | 1208363553 | 364 | 1208363553_364
MRPP2-SUP.15340 | TT_Task | EMU - Production Secondary Suspension - 2nd Fleet (6 trainsets) | 01/04/2022 | 13/06/2023 | 02/03/2022 | nan | 0 | TK_Active | 1208363553 | 365 | 1208363553_365
MRPP2-SUP.21350 | TT_Task | EMU - DEL Secondary Suspension delivery - 2nd Fleet (6 trainsets) | 14/02/2023 | 04/08/2023 | nan | nan | 0 | TK_NotStart | 1208363553 | 367 | 1208363553_367
MRPP2-SUP.11260 | TT_Task | EMU - PO CVS - 2nd Fleet (6 trainsets) | 04/03/2022 | 31/03/2022 | 02/02/2022 | 01/03/2022 | 0 | TK_Complete | 1208363553 | 369 | 1208363553_369
MRPP2-SUP.15390 | TT_Task | EMU - Production CVS - 2nd Fleet (6 trainsets) | 01/04/2022 | 13/06/2023 | 02/03/2022 | nan | 0 | TK_Active | 1208363553 | 370 | 1208363553_370
MRPP2-SUP.21200 | TT_Task | EMU - DEL CVS delivery - 2nd Fleet (6 trainsets) | 14/02/2023 | 04/08/2023 | nan | nan | 0 | TK_NotStart | 1208363553 | 371 | 1208363553_371
MRPP2-SUP.11230 | TT_Task | EMU - PO Coupler - 2nd Fleet (6 trainsets) | 01/04/2022 | 03/05/2022 | 02/03/2022 | 29/03/2022 | 0 | TK_Complete | 1208363553 | 372 | 1208363553_372
MRPP2-SUP.15360 | TT_Task | EMU - Production Coupler - 2nd Fleet (6 trainsets) | 03/05/2022 | 10/07/2023 | 30/03/2022 | nan | 0 | TK_Active | 1208363553 | 372 | 1208363553_372
MRPP2-SUP.21170 | TT_Task | EMU - DEL Coupler delivery - 2nd Fleet (6 trainsets) | 14/03/2023 | 01/09/2023 | nan | nan | 0 | TK_NotStart | 1208363553 | 373 | 1208363553_373
MRPP2-SUP.11270 | TT_Task | EMU - PO (Purchase Order)-Gangway - 2nd Fleet (6 trainsets) | 04/03/2022 | 31/03/2022 | 02/03/2022 | 29/03/2022 | 0 | TK_Complete | 1208363553 | 374 | 1208363553_374
MRPP2-SUP.15400 | TT_Task | EMU - Production ( Component process time)-Gangway - 2nd Fleet (6 trainsets) | 03/05/2022 | 10/07/2023 | 30/03/2022 | nan | 0 | TK_Active | 1208363553 | 375 | 1208363553_375
MRPP2-SUP.21210 | TT_Task | EMU - DEL Component-Gangway-Delivery - 2nd Fleet (6 trainsets) | 14/03/2023 | 01/09/2023 | nan | nan | 0 | TK_NotStart | 1208363553 | 376 | 1208363553_376
MRPP2-SUP.11240 | TT_Task | EMU - PO Pipes - 2nd Fleet (6 trainsets) | 04/03/2022 | 31/03/2022 | 02/03/2022 | 29/03/2022 | 0 | TK_Complete | 1208363553 | 377 | 1208363553_377
MRPP2-SUP.15370 | TT_Task | EMU - Production Pipes - 2nd Fleet (6 trainsets) | 03/05/2022 | 10/07/2023 | 30/03/2022 | nan | 0 | TK_Active | 1208363553 | 377 | 1208363553_377
MRPP2-SUP.21180 | TT_Task | EMU - DEL Pipes delivery - 2nd Fleet (6 trainsets) | 14/03/2023 | 01/09/2023 | nan | nan | 0 | TK_NotStart | 1208363553 | 378 | 1208363553_378
MRPP2-SUP.11250 | TT_Task | EMU - PO Cables - 2nd Fleet (6 trainsets) | 04/03/2022 | 31/03/2022 | 02/03/2022 | 29/03/2022 | 0 | TK_Complete | 1208363553 | 381 | 1208363553_381
MRPP2-SUP.15380 | TT_Task | EMU - Production Cables - 2nd Fleet (6 trainsets) | 03/05/2022 | 10/07/2023 | 30/03/2022 | nan | 0 | TK_Active | 1208363553 | 381 | 1208363553_381
MRPP2-SUP.21190 | TT_Task | EMU - DEL Cables delivery - 2nd Fleet (6 trainsets) | 14/03/2023 | 01/09/2023 | nan | nan | 0 | TK_NotStart | 1208363553 | 382 | 1208363553_382
MRPP2-SUP.11300 | TT_Task | EMU - PO Cable trays - 2nd Fleet (6 trainsets) | 04/03/2022 | 31/03/2022 | 02/03/2022 | 29/03/2022 | 0 | TK_Complete | 1208363553 | 383 | 1208363553_383
MRPP2-SUP.15430 | TT_Task | EMU - Production Cable trays - 2nd Fleet (6 trainsets) | 03/05/2022 | 10/07/2023 | 30/03/2022 | nan | 0 | TK_Active | 1208363553 | 383 | 1208363553_383
MRPP2-SUP.21320 | TT_Task | EMU - DEL Cable trays delivery - 2nd Fleet (6 trainsets) | 14/03/2023 | 01/09/2023 | nan | nan | 0 | TK_NotStart | 1208363553 | 383 | 1208363553_383
MRPP2-SUP.11310 | TT_Task | EMU - PO Floor covering - 2nd Fleet (6 trainsets) | 04/03/2022 | 31/03/2022 | 02/03/2022 | 29/03/2022 | 0 | TK_Complete | 1208363553 | 384 | 1208363553_384
MRPP2-SUP.15440 | TT_Task | EMU - Production Floor covering - 2nd Fleet (6 trainsets) | 03/05/2022 | 10/07/2023 | 30/03/2022 | nan | 0 | TK_Active | 1208363553 | 385 | 1208363553_385
MRPP2-SUP.21330 | TT_Task | EMU - DEL Floor covering delivery - 2nd Fleet (6 trainsets) | 14/03/2023 | 01/09/2023 | nan | nan | 0 | TK_NotStart | 1208363553 | 386 | 1208363553_386
MRPP2-SUP.11470 | TT_Task | EMU - PO Pantograph - 2nd Fleet (6 trainsets) | 04/03/2022 | 31/03/2022 | 02/03/2022 | 29/03/2022 | 0 | TK_Complete | 1208363553 | 387 | 1208363553_387
MRPP2-SUP.15600 | TT_Task | EMU - Production Pantograph - 2nd Fleet (6 trainsets) | 03/05/2022 | 10/07/2023 | 30/03/2022 | nan | 0 | TK_Active | 1208363553 | 387 | 1208363553_387
MRPP2-SUP.21450 | TT_Task | EMU - DEL Pantograph delivery - 2nd Fleet (6 trainsets) | 14/03/2023 | 01/09/2023 | nan | nan | 0 | TK_NotStart | 1208363553 | 388 | 1208363553_388
MRPP2-SUP.11440 | TT_Task | EMU - PO Wind screen - 2nd Fleet (6 trainsets) | 04/03/2022 | 31/03/2022 | 02/03/2022 | 29/03/2022 | 0 | TK_Complete | 1208363553 | 389 | 1208363553_389
MRPP2-SUP.15570 | TT_Task | EMU - Production Wind screen - 2nd Fleet (6 trainsets) | 03/05/2022 | 10/07/2023 | 30/03/2022 | nan | 0 | TK_Active | 1208363553 | 389 | 1208363553_389
MRPP2-SUP.21420 | TT_Task | EMU - DEL Wind screen delivery - 2nd Fleet (6 trainsets) | 14/03/2023 | 01/09/2023 | nan | nan | 0 | TK_NotStart | 1208363553 | 390 | 1208363553_390
MRPP2-SUP.11450 | TT_Task | EMU - PO Front mask - 2nd Fleet (6 trainsets) | 04/03/2022 | 31/03/2022 | 02/03/2022 | 29/03/2022 | 0 | TK_Complete | 1208363553 | 391 | 1208363553_391
MRPP2-SUP.15580 | TT_Task | EMU - Production Front mask - 2nd Fleet (6 trainsets) | 03/05/2022 | 10/07/2023 | 30/03/2022 | nan | 0 | TK_Active | 1208363553 | 391 | 1208363553_391
MRPP2-SUP.21430 | TT_Task | EMU - DEL Front mask delivery - 2nd Fleet (6 trainsets) | 14/03/2023 | 01/09/2023 | nan | nan | 0 | TK_NotStart | 1208363553 | 392 | 1208363553_392
MRPP2-SUP.11460 | TT_Task | EMU - PO Relays - 2nd Fleet (6 trainsets) | 04/03/2022 | 31/03/2022 | 02/03/2022 | 29/03/2022 | 0 | TK_Complete | 1208363553 | 393 | 1208363553_393
MRPP2-SUP.15590 | TT_Task | EMU - Production Relays - 2nd Fleet (6 trainsets) | 03/05/2022 | 10/07/2023 | 30/03/2022 | nan | 0 | TK_Active | 1208363553 | 393 | 1208363553_393
MRPP2-SUP.21440 | TT_Task | EMU - DEL Relays delivery - 2nd Fleet (6 trainsets) | 14/03/2023 | 01/09/2023 | nan | nan | 0 | TK_NotStart | 1208363553 | 394 | 1208363553_394
MRPP2-SUP.11480 | TT_Task | EMU - PO Cabinets - 2nd Fleet (6 trainsets) | 04/03/2022 | 31/03/2022 | 02/03/2022 | 29/03/2022 | 0 | TK_Complete | 1208363553 | 395 | 1208363553_395
MRPP2-SUP.15610 | TT_Task | EMU - Production Cabinets - 2nd Fleet (6 trainsets) | 03/05/2022 | 10/07/2023 | 30/03/2022 | nan | 0 | TK_Active | 1208363553 | 395 | 1208363553_395
MRPP2-SUP.21510 | TT_Task | EMU - DEL Cabinets delivery - 2nd Fleet (6 trainsets) | 14/03/2023 | 01/09/2023 | nan | nan | 0 | TK_NotStart | 1208363553 | 396 | 1208363553_396
MRPP2-SUP.11490 | TT_Task | EMU - PO Elec comp - 2nd Fleet (6 trainsets) | 04/03/2022 | 31/03/2022 | 02/03/2022 | 29/03/2022 | 0 | TK_Complete | 1208363553 | 397 | 1208363553_397
MRPP2-SUP.15620 | TT_Task | EMU - Production Elec comp - 2nd Fleet (6 trainsets) | 03/05/2022 | 10/07/2023 | 30/03/2022 | nan | 0 | TK_Active | 1208363553 | 398 | 1208363553_398
MRPP2-SUP.21520 | TT_Task | EMU - DEL Elec comp delivery - 2nd Fleet (6 trainsets) | 14/03/2023 | 01/09/2023 | nan | nan | 0 | TK_NotStart | 1208363553 | 399 | 1208363553_399
MRPP2-SUP.11500 | TT_Task | EMU - PO LV box - 2nd Fleet (6 trainsets) | 04/03/2022 | 31/03/2022 | 02/03/2022 | 29/03/2022 | 0 | TK_Complete | 1208363553 | 400 | 1208363553_400
MRPP2-SUP.15630 | TT_Task | EMU - Production LV box - 2nd Fleet (6 trainsets) | 03/05/2022 | 10/07/2023 | 30/03/2022 | nan | 0 | TK_Active | 1208363553 | 400 | 1208363553_400
MRPP2-SUP.21530 | TT_Task | EMU - DEL LV box delivery - 2nd Fleet (6 trainsets) | 14/03/2023 | 01/09/2023 | nan | nan | 0 | TK_NotStart | 1208363553 | 401 | 1208363553_401
MRPP2-SUP.11510 | TT_Task | EMU - PO Battery ; battery box - 2nd Fleet (6 trainsets) | 04/03/2022 | 31/03/2022 | 02/03/2022 | 29/03/2022 | 0 | TK_Complete | 1208363553 | 402 | 1208363553_402
MRPP2-SUP.15640 | TT_Task | EMU - Production Battery ; battery box - 2nd Fleet (6 trainsets) | 03/05/2022 | 10/07/2023 | 30/03/2022 | nan | 0 | TK_Active | 1208363553 | 402 | 1208363553_402
MRPP2-SUP.21540 | TT_Task | EMU - DEL Battery ; battery box delivery - 2nd Fleet (6 trainsets) | 14/03/2023 | 01/09/2023 | nan | nan | 0 | TK_NotStart | 1208363553 | 402 | 1208363553_402
MRPP2-SUP.11520 | TT_Task | EMU - PO Crash box - 2nd Fleet (6 trainsets) | 04/03/2022 | 31/03/2022 | 02/03/2022 | 29/03/2022 | 0 | TK_Complete | 1208363553 | 403 | 1208363553_403
MRPP2-SUP.15650 | TT_Task | EMU - Production Crash box - 2nd Fleet (6 trainsets) | 03/05/2022 | 10/07/2023 | 30/03/2022 | nan | 0 | TK_Active | 1208363553 | 403 | 1208363553_403
MRPP2-SUP.21550 | TT_Task | EMU - DEL Crash box delivery - 2nd Fleet (6 trainsets) | 14/03/2023 | 01/09/2023 | nan | nan | 0 | TK_NotStart | 1208363553 | 404 | 1208363553_404
MRPP2-SUP.11590 | TT_Task | EMU - PO Interior and lighting - 2nd Fleet (6 trainsets) | 04/03/2022 | 31/03/2022 | 02/03/2022 | 29/03/2022 | 0 | TK_Complete | 1208363553 | 406 | 1208363553_406
MRPP2-SUP.15720 | TT_Task | EMU - Production Interior and lighting - 2nd Fleet (6 trainsets) | 03/05/2022 | 10/07/2023 | 30/03/2022 | nan | 0 | TK_Active | 1208363553 | 407 | 1208363553_407
MRPP2-SUP.21620 | TT_Task | EMU - DEL Interior and lighting delivery - 2nd Fleet (6 trainsets) | 14/03/2023 | 01/09/2023 | nan | nan | 0 | TK_NotStart | 1208363553 | 407 | 1208363553_407
MRPP2-SUP.11550 | TT_Task | EMU - PO Hand rails - 2nd Fleet (6 trainsets) | 04/03/2022 | 31/03/2022 | 02/03/2022 | 29/03/2022 | 0 | TK_Complete | 1208363553 | 408 | 1208363553_408
MRPP2-SUP.15680 | TT_Task | EMU - Production Hand rails - 2nd Fleet (6 trainsets) | 03/05/2022 | 10/07/2023 | 30/03/2022 | nan | 0 | TK_Active | 1208363553 | 408 | 1208363553_408
MRPP2-SUP.21580 | TT_Task | EMU - DEL Hand rails delivery - 2nd Fleet (6 trainsets) | 14/03/2023 | 01/09/2023 | nan | nan | 0 | TK_NotStart | 1208363553 | 409 | 1208363553_409
MRPP2-SUP.11540 | TT_Task | EMU - PO Grabpoles and grab handles - 2nd Fleet (6 trainsets) | 04/03/2022 | 31/03/2022 | 02/03/2022 | 29/03/2022 | 0 | TK_Complete | 1208363553 | 410 | 1208363553_410
MRPP2-SUP.15670 | TT_Task | EMU - Production Grabpoles and grab handles - 2nd Fleet (6 trainsets) | 03/05/2022 | 10/07/2023 | 30/03/2022 | nan | 0 | TK_Active | 1208363553 | 410 | 1208363553_410
MRPP2-SUP.21570 | TT_Task | EMU - DEL Grabpoles and grab handles delivery - 2nd Fleet (6 trainsets) | 14/03/2023 | 01/09/2023 | nan | nan | 0 | TK_NotStart | 1208363553 | 410 | 1208363553_410
MRPP2-SUP.11600 | TT_Task | EMU - PO Cab garnishing - 2nd Fleet (6 trainsets) | 04/03/2022 | 31/03/2022 | 02/03/2022 | 29/03/2022 | 0 | TK_Complete | 1208363553 | 411 | 1208363553_411
MRPP2-SUP.15730 | TT_Task | EMU - Production Cab garnishing - 2nd Fleet (6 trainsets) | 03/05/2022 | 10/07/2023 | 30/03/2022 | nan | 0 | TK_Active | 1208363553 | 411 | 1208363553_411
MRPP2-SUP.21630 | TT_Task | EMU - DEL Cab garnishing delivery - 2nd Fleet (6 trainsets) | 14/03/2023 | 01/09/2023 | nan | nan | 0 | TK_NotStart | 1208363553 | 411 | 1208363553_411
MRPP2-SUP.11580 | TT_Task | EMU - PO Seats - 2nd Fleet (6 trainsets) | 04/03/2022 | 31/03/2022 | 02/03/2022 | 29/03/2022 | 0 | TK_Complete | 1208363553 | 412 | 1208363553_412
MRPP2-SUP.15710 | TT_Task | EMU - Production Seats - 2nd Fleet (6 trainsets) | 03/05/2022 | 10/07/2023 | 30/03/2022 | nan | 0 | TK_Active | 1208363553 | 412 | 1208363553_412
MRPP2-SUP.21610 | TT_Task | EMU - DEL Seats delivery - 2nd Fleet (6 trainsets) | 14/03/2023 | 01/09/2023 | nan | nan | 0 | TK_NotStart | 1208363553 | 413 | 1208363553_413
MRPP2-SUP.11560 | TT_Task | EMU - PO PACIS - 2nd Fleet (6 trainsets) | 04/03/2022 | 31/03/2022 | 02/03/2022 | 29/03/2022 | 0 | TK_Complete | 1208363553 | 414 | 1208363553_414
MRPP2-SUP.15690 | TT_Task | EMU - Production PACIS - 2nd Fleet (6 trainsets) | 03/05/2022 | 10/07/2023 | 30/03/2022 | nan | 0 | TK_Active | 1208363553 | 414 | 1208363553_414
MRPP2-SUP.21590 | TT_Task | EMU - DEL PACIS delivery - 2nd Fleet (6 trainsets) | 14/03/2023 | 01/09/2023 | nan | nan | 0 | TK_NotStart | 1208363553 | 415 | 1208363553_415
MRPP2-SUP.11530 | TT_Task | EMU - PO MCP - 2nd Fleet (6 trainsets) | 04/04/2022 | 04/05/2022 | 30/03/2022 | nan | 0 | TK_Active | 1208363553 | 417 | 1208363553_417
MRPP2-SUP.15660 | TT_Task | EMU - Production MCP - 2nd Fleet (6 trainsets) | 02/05/2022 | 07/07/2023 | nan | nan | 0 | TK_NotStart | 1208363553 | 418 | 1208363553_418
MRPP2-SUP.21560 | TT_Task | EMU - DEL MCP delivery - 2nd Fleet (6 trainsets) | 13/04/2023 | 02/10/2023 | nan | nan | 0 | TK_NotStart | 1208363553 | 419 | 1208363553_419
MRPP2-SUP.11570 | TT_Task | EMU - PO TCMS equipment - 2nd Fleet (6 trainsets) | 04/04/2022 | 04/05/2022 | 30/03/2022 | nan | 0 | TK_Active | 1208363553 | 421 | 1208363553_421
MRPP2-SUP.15700 | TT_Task | EMU - Production TCMS equipment - 2nd Fleet (6 trainsets) | 02/05/2022 | 07/07/2023 | nan | nan | 0 | TK_NotStart | 1208363553 | 422 | 1208363553_422
MRPP2-SUP.21600 | TT_Task | EMU - DEL TCMS equipment delivery - 2nd Fleet (6 trainsets) | 13/04/2023 | 02/10/2023 | nan | nan | 0 | TK_NotStart | 1208363553 | 422 | 1208363553_422
MRPP2-SUP.11150 | TT_Task | EMU - PO HVAC - 2nd Fleet (6 trainsets) | 04/04/2022 | 04/05/2022 | 30/03/2022 | nan | 0 | TK_Active | 1208363553 | 348 | 1208363553_348
MRPP2-SUP.15280 | TT_Task | EMU - Production HVAC - 2nd Fleet (6 trainsets) | 02/05/2022 | 07/07/2023 | nan | nan | 0 | TK_NotStart | 1208363553 | 348 | 1208363553_348
MRPP2-SUP.21160 | TT_Task | EMU - DEL HVAC delivery - 2nd Fleet (6 trainsets) | 13/04/2023 | 02/10/2023 | nan | nan | 0 | TK_NotStart | 1208363553 | 349 | 1208363553_349
MRPP2-SUP.11170 | TT_Task | EMU - PO Windows - 2nd Fleet (6 trainsets) | 04/04/2022 | 04/05/2022 | 30/03/2022 | nan | 0 | TK_Active | 1208363553 | 351 | 1208363553_351
MRPP2-SUP.15300 | TT_Task | EMU - Production Windows - 2nd Fleet (6 trainsets) | 02/05/2022 | 07/07/2023 | nan | nan | 0 | TK_NotStart | 1208363553 | 352 | 1208363553_352
MRPP2-SUP.21280 | TT_Task | EMU - DEL Windows delivery - 2nd Fleet (6 trainsets) | 13/04/2023 | 02/10/2023 | nan | nan | 0 | TK_NotStart | 1208363553 | 353 | 1208363553_353
MRPP2-SUP.11220 | TT_Task | EMU - PO Passenger doors - 2nd Fleet (6 trainsets) | 04/04/2022 | 04/05/2022 | 30/03/2022 | nan | 0 | TK_Active | 1208363553 | 354 | 1208363553_354
MRPP2-SUP.15350 | TT_Task | EMU - Production Passenger doors - 2nd Fleet (6 trainsets) | 02/05/2022 | 07/07/2023 | nan | nan | 0 | TK_NotStart | 1208363553 | 354 | 1208363553_354
MRPP2-SUP.21360 | TT_Task | EMU - DEL Passenger doors delivery - 2nd Fleet (6 trainsets) | 13/04/2023 | 02/10/2023 | nan | nan | 0 | TK_NotStart | 1208363553 | 355 | 1208363553_355
MRPP2-SUP.11700 | TT_Task | EMU - PO Bogie Frame - 3rd Fleet (6 trainsets) | 21/09/2022 | 19/10/2022 | nan | nan | 0 | TK_NotStart | 1208363553 | 337 | 1208363553_337
MRPP2-SUP.15830 | TT_Task | EMU - Production Bogie Frame - 3rd Fleet (6 trainsets) | 20/10/2022 | 28/12/2023 | nan | nan | 0 | TK_NotStart | 1208363553 | 337 | 1208363553_337
MRPP2-SUP.21910 | TT_Task | EMU - DEL Bogie Frame delivery - 3rd Fleet (6 trainsets) | 22/08/2023 | 12/02/2024 | nan | nan | 0 | TK_NotStart | 1208363553 | 339 | 1208363553_339
MRPP2-SUP.11720 | TT_Task | EMU - PO Bogie Assy - 3rd Fleet (6 trainsets) | 21/09/2022 | 19/10/2022 | nan | nan | 0 | TK_NotStart | 1208363553 | 423 | 1208363553_423
MRPP2-SUP.15850 | TT_Task | EMU - Production Bogie Assy - 3rd Fleet (6 trainsets) | 20/10/2022 | 28/12/2023 | nan | nan | 0 | TK_NotStart | 1208363553 | 423 | 1208363553_423
MRPP2-SUP.21930 | TT_Task | EMU - DEL Bogie Assy delivery - 3rd Fleet (6 trainsets) | 22/08/2023 | 12/02/2024 | nan | nan | 0 | TK_NotStart | 1208363553 | 339 | 1208363553_339
MRPP2-SUP.11710 | TT_Task | EMU - PO Axle box ; bearing - 3rd Fleet (6 trainsets) | 21/09/2022 | 19/10/2022 | nan | nan | 0 | TK_NotStart | 1208363553 | 341 | 1208363553_341
MRPP2-SUP.15840 | TT_Task | EMU - Production Axle box ; bearing - 3rd Fleet (6 trainsets) | 20/10/2022 | 28/12/2023 | nan | nan | 0 | TK_NotStart | 1208363553 | 341 | 1208363553_341
MRPP2-SUP.21920 | TT_Task | EMU - DEL Axle box ; bearing delivery - 3rd Fleet (6 trainsets) | 22/08/2023 | 12/02/2024 | nan | nan | 0 | TK_NotStart | 1208363553 | 341 | 1208363553_341
MRPP2-SUP.11690 | TT_Task | EMU - PO Wheels - 3rd Fleet (6 trainsets) | 21/09/2022 | 19/10/2022 | nan | nan | 0 | TK_NotStart | 1208363553 | 344 | 1208363553_344
MRPP2-SUP.15820 | TT_Task | EMU - Production Wheels - 3rd Fleet (6 trainsets) | 20/10/2022 | 28/12/2023 | nan | nan | 0 | TK_NotStart | 1208363553 | 344 | 1208363553_344
MRPP2-SUP.21900 | TT_Task | EMU - DEL Wheels delivery - 3rd Fleet (6 trainsets) | 22/08/2023 | 12/02/2024 | nan | nan | 0 | TK_NotStart | 1208363553 | 346 | 1208363553_346
MRPP2-SUP.11790 | TT_Task | EMU - PO Axles - 3rd Fleet (6 trainsets) | 20/10/2022 | 16/11/2022 | nan | nan | 0 | TK_NotStart | 1208363553 | 356 | 1208363553_356
MRPP2-SUP.15920 | TT_Task | EMU - Production Axles - 3rd Fleet (6 trainsets) | 17/11/2022 | 29/01/2024 | nan | nan | 0 | TK_NotStart | 1208363553 | 356 | 1208363553_356
MRPP2-SUP.22010 | TT_Task | EMU - DEL Axles delivery - 3rd Fleet (6 trainsets) | 01/11/2023 | 24/04/2024 | nan | nan | 0 | TK_NotStart | 1208363553 | 357 | 1208363553_357
MRPP2-SUP.11810 | TT_Task | EMU - PO Brakes - 3rd Fleet (6 trainsets) | 17/11/2022 | 14/12/2022 | nan | nan | 0 | TK_NotStart | 1208363553 | 358 | 1208363553_358
MRPP2-SUP.15940 | TT_Task | EMU - Production Brakes - 3rd Fleet (6 trainsets) | 15/12/2022 | 26/02/2024 | nan | nan | 0 | TK_NotStart | 1208363553 | 358 | 1208363553_358
MRPP2-SUP.22210 | TT_Task | EMU - DEL Brakes delivery - 3rd Fleet (6 trainsets) | 29/11/2023 | 23/05/2024 | nan | nan | 0 | TK_NotStart | 1208363553 | 359 | 1208363553_359
MRPP2-SUP.11900 | TT_Task | EMU - PO Traction converter - 3rd Fleet (6 trainsets) | 17/11/2022 | 14/12/2022 | nan | nan | 0 | TK_NotStart | 1208363553 | 360 | 1208363553_360
MRPP2-SUP.16030 | TT_Task | EMU - Production Traction converter - 3rd Fleet (6 trainsets) | 15/12/2022 | 28/12/2023 | nan | nan | 0 | TK_NotStart | 1208363553 | 360 | 1208363553_360
MRPP2-SUP.22240 | TT_Task | EMU - DEL Traction converter delivery - 3rd Fleet (6 trainsets) | 01/11/2023 | 24/04/2024 | nan | nan | 0 | TK_NotStart | 1208363553 | 361 | 1208363553_361
MRPP2-SUP.11880 | TT_Task | EMU - PO Traction motor - 3rd Fleet (6 trainsets) | 17/11/2022 | 14/12/2022 | nan | nan | 0 | TK_NotStart | 1208363553 | 362 | 1208363553_362
MRPP2-SUP.16010 | TT_Task | EMU - Production Traction motor - 3rd Fleet (6 trainsets) | 15/12/2022 | 28/12/2023 | nan | nan | 0 | TK_NotStart | 1208363553 | 362 | 1208363553_362
MRPP2-SUP.22230 | TT_Task | EMU - DEL Traction motor delivery - 3rd Fleet (6 trainsets) | 01/11/2023 | 24/04/2024 | nan | nan | 0 | TK_NotStart | 1208363553 | 363 | 1208363553_363
MRPP2-SUP.12040 | TT_Task | EMU - PO Primary Suspension - 3rd Fleet (6 trainsets) | 17/11/2022 | 14/12/2022 | nan | nan | 0 | TK_NotStart | 1208363553 | 364 | 1208363553_364
MRPP2-SUP.16170 | TT_Task | EMU - Production Primary Suspension - 3rd Fleet (6 trainsets) | 15/12/2022 | 26/02/2024 | nan | nan | 0 | TK_NotStart | 1208363553 | 365 | 1208363553_365
MRPP2-SUP.22260 | TT_Task | EMU - DEL Primary Suspension delivery - 3rd Fleet (6 trainsets) | 29/11/2023 | 23/05/2024 | nan | nan | 0 | TK_NotStart | 1208363553 | 367 | 1208363553_367
MRPP2-SUP.12050 | TT_Task | EMU - PO Secondary Suspension - 3rd Fleet (6 trainsets) | 17/11/2022 | 14/12/2022 | nan | nan | 0 | TK_NotStart | 1208363553 | 364 | 1208363553_364
MRPP2-SUP.16180 | TT_Task | EMU - Production Secondary Suspension - 3rd Fleet (6 trainsets) | 15/12/2022 | 26/02/2024 | nan | nan | 0 | TK_NotStart | 1208363553 | 365 | 1208363553_365
MRPP2-SUP.22270 | TT_Task | EMU - DEL Secondary Suspension delivery - 3rd Fleet (6 trainsets) | 29/11/2023 | 23/05/2024 | nan | nan | 0 | TK_NotStart | 1208363553 | 367 | 1208363553_367
MRPP2-SUP.11980 | TT_Task | EMU - PO CVS - 3rd Fleet (6 trainsets) | 17/11/2022 | 14/12/2022 | nan | nan | 0 | TK_NotStart | 1208363553 | 369 | 1208363553_369
MRPP2-SUP.16110 | TT_Task | EMU - Production CVS - 3rd Fleet (6 trainsets) | 15/12/2022 | 26/02/2024 | nan | nan | 0 | TK_NotStart | 1208363553 | 370 | 1208363553_370
MRPP2-SUP.22250 | TT_Task | EMU - DEL CVS delivery - 3rd Fleet (6 trainsets) | 15/11/2023 | 09/05/2024 | nan | nan | 0 | TK_NotStart | 1208363553 | 371 | 1208363553_371
MRPP2-SUP.11830 | TT_Task | EMU - PO Coupler - 3rd Fleet (6 trainsets) | 17/11/2022 | 14/12/2022 | nan | nan | 0 | TK_NotStart | 1208363553 | 372 | 1208363553_372
MRPP2-SUP.15960 | TT_Task | EMU - Production Coupler - 3rd Fleet (6 trainsets) | 15/12/2022 | 26/02/2024 | nan | nan | 0 | TK_NotStart | 1208363553 | 372 | 1208363553_372
MRPP2-SUP.21950 | TT_Task | EMU - DEL Coupler delivery - 3rd Fleet (6 trainsets) | 29/11/2023 | 23/05/2024 | nan | nan | 0 | TK_NotStart | 1208363553 | 373 | 1208363553_373
MRPP2-SUP.11990 | TT_Task | EMU - PO (Purchase Order)-Gangway - 3rd Fleet (6 trainsets) | 17/11/2022 | 14/12/2022 | nan | nan | 0 | TK_NotStart | 1208363553 | 374 | 1208363553_374
MRPP2-SUP.16120 | TT_Task | EMU - Production ( Component process time)-Gangway - 3rd Fleet (6 trainsets) | 15/12/2022 | 26/02/2024 | nan | nan | 0 | TK_NotStart | 1208363553 | 375 | 1208363553_375
MRPP2-SUP.22090 | TT_Task | EMU - DEL Component-Gangway Delivery - 3rd Fleet (6 trainsets) | 29/11/2023 | 23/05/2024 | nan | nan | 0 | TK_NotStart | 1208363553 | 376 | 1208363553_376
MRPP2-SUP.11870 | TT_Task | EMU - PO Pipes - 3rd Fleet (6 trainsets) | 17/11/2022 | 14/12/2022 | nan | nan | 0 | TK_NotStart | 1208363553 | 377 | 1208363553_377
MRPP2-SUP.16000 | TT_Task | EMU - Production Pipes - 3rd Fleet (6 trainsets) | 15/12/2022 | 26/02/2024 | nan | nan | 0 | TK_NotStart | 1208363553 | 377 | 1208363553_377
MRPP2-SUP.21990 | TT_Task | EMU - DEL Pipes delivery - 3rd Fleet (6 trainsets) | 29/11/2023 | 23/05/2024 | nan | nan | 0 | TK_NotStart | 1208363553 | 378 | 1208363553_378
MRPP2-SUP.11910 | TT_Task | EMU - PO Cables - 3rd Fleet (6 trainsets) | 17/11/2022 | 14/12/2022 | nan | nan | 0 | TK_NotStart | 1208363553 | 381 | 1208363553_381
MRPP2-SUP.16040 | TT_Task | EMU - Production Cables - 3rd Fleet (6 trainsets) | 15/12/2022 | 26/02/2024 | nan | nan | 0 | TK_NotStart | 1208363553 | 381 | 1208363553_381
MRPP2-SUP.22020 | TT_Task | EMU - DEL Cables delivery - 3rd Fleet (6 trainsets) | 29/11/2023 | 23/05/2024 | nan | nan | 0 | TK_NotStart | 1208363553 | 382 | 1208363553_382
MRPP2-SUP.11970 | TT_Task | EMU - PO Cable trays - 3rd Fleet (6 trainsets) | 17/11/2022 | 14/12/2022 | nan | nan | 0 | TK_NotStart | 1208363553 | 383 | 1208363553_383
MRPP2-SUP.16100 | TT_Task | EMU - Production Cable trays - 3rd Fleet (6 trainsets) | 15/12/2022 | 26/02/2024 | nan | nan | 0 | TK_NotStart | 1208363553 | 383 | 1208363553_383
MRPP2-SUP.22080 | TT_Task | EMU - DEL Cable trays delivery - 3rd Fleet (6 trainsets) | 29/11/2023 | 23/05/2024 | nan | nan | 0 | TK_NotStart | 1208363553 | 383 | 1208363553_383
MRPP2-SUP.12010 | TT_Task | EMU - PO Floor covering - 3rd Fleet (6 trainsets) | 17/11/2022 | 14/12/2022 | nan | nan | 0 | TK_NotStart | 1208363553 | 384 | 1208363553_384
MRPP2-SUP.16140 | TT_Task | EMU - Production Floor covering - 3rd Fleet (6 trainsets) | 15/12/2022 | 26/02/2024 | nan | nan | 0 | TK_NotStart | 1208363553 | 385 | 1208363553_385
MRPP2-SUP.22110 | TT_Task | EMU - DEL Floor covering delivery - 3rd Fleet (6 trainsets) | 29/11/2023 | 23/05/2024 | nan | nan | 0 | TK_NotStart | 1208363553 | 386 | 1208363553_386
MRPP2-SUP.12100 | TT_Task | EMU - PO Pantograph - 3rd Fleet (6 trainsets) | 17/11/2022 | 14/12/2022 | nan | nan | 0 | TK_NotStart | 1208363553 | 387 | 1208363553_387
MRPP2-SUP.16230 | TT_Task | EMU - Production Pantograph - 3rd Fleet (6 trainsets) | 15/12/2022 | 26/02/2024 | nan | nan | 0 | TK_NotStart | 1208363553 | 387 | 1208363553_387
MRPP2-SUP.22180 | TT_Task | EMU - DEL Pantograph delivery - 3rd Fleet (6 trainsets) | 29/11/2023 | 23/05/2024 | nan | nan | 0 | TK_NotStart | 1208363553 | 388 | 1208363553_388
MRPP2-SUP.11840 | TT_Task | EMU - PO Wind screen - 3rd Fleet (6 trainsets) | 17/11/2022 | 14/12/2022 | nan | nan | 0 | TK_NotStart | 1208363553 | 389 | 1208363553_389
MRPP2-SUP.15970 | TT_Task | EMU - Production Wind screen - 3rd Fleet (6 trainsets) | 15/12/2022 | 26/02/2024 | nan | nan | 0 | TK_NotStart | 1208363553 | 389 | 1208363553_389
MRPP2-SUP.21960 | TT_Task | EMU - DEL Wind screen delivery - 3rd Fleet (6 trainsets) | 29/11/2023 | 23/05/2024 | nan | nan | 0 | TK_NotStart | 1208363553 | 390 | 1208363553_390
MRPP2-SUP.11940 | TT_Task | EMU - PO Front mask - 3rd Fleet (6 trainsets) | 17/11/2022 | 14/12/2022 | nan | nan | 0 | TK_NotStart | 1208363553 | 391 | 1208363553_391
MRPP2-SUP.16070 | TT_Task | EMU - Production Front mask - 3rd Fleet (6 trainsets) | 15/12/2022 | 26/02/2024 | nan | nan | 0 | TK_NotStart | 1208363553 | 391 | 1208363553_391
MRPP2-SUP.22050 | TT_Task | EMU - DEL Front mask delivery - 3rd Fleet (6 trainsets) | 29/11/2023 | 23/05/2024 | nan | nan | 0 | TK_NotStart | 1208363553 | 392 | 1208363553_392
MRPP2-SUP.11950 | TT_Task | EMU - PO Relays - 3rd Fleet (6 trainsets) | 17/11/2022 | 14/12/2022 | nan | nan | 0 | TK_NotStart | 1208363553 | 393 | 1208363553_393
MRPP2-SUP.16080 | TT_Task | EMU - Production Relays - 3rd Fleet (6 trainsets) | 15/12/2022 | 26/02/2024 | nan | nan | 0 | TK_NotStart | 1208363553 | 393 | 1208363553_393
MRPP2-SUP.22060 | TT_Task | EMU - DEL Relays delivery - 3rd Fleet (6 trainsets) | 29/11/2023 | 23/05/2024 | nan | nan | 0 | TK_NotStart | 1208363553 | 394 | 1208363553_394
MRPP2-SUP.12070 | TT_Task | EMU - PO Cabinets - 3rd Fleet (6 trainsets) | 17/11/2022 | 14/12/2022 | nan | nan | 0 | TK_NotStart | 1208363553 | 395 | 1208363553_395
MRPP2-SUP.16200 | TT_Task | EMU - Production Cabinets - 3rd Fleet (6 trainsets) | 15/12/2022 | 26/02/2024 | nan | nan | 0 | TK_NotStart | 1208363553 | 395 | 1208363553_395
MRPP2-SUP.22150 | TT_Task | EMU - DEL Cabinets delivery - 3rd Fleet (6 trainsets) | 29/11/2023 | 23/05/2024 | nan | nan | 0 | TK_NotStart | 1208363553 | 396 | 1208363553_396
MRPP2-SUP.11860 | TT_Task | EMU - PO Elec comp - 3rd Fleet (6 trainsets) | 17/11/2022 | 14/12/2022 | nan | nan | 0 | TK_NotStart | 1208363553 | 397 | 1208363553_397
MRPP2-SUP.15990 | TT_Task | EMU - Production Elec comp - 3rd Fleet (6 trainsets) | 15/12/2022 | 26/02/2024 | nan | nan | 0 | TK_NotStart | 1208363553 | 398 | 1208363553_398
MRPP2-SUP.21980 | TT_Task | EMU - DEL Elec comp delivery - 3rd Fleet (6 trainsets) | 29/11/2023 | 23/05/2024 | nan | nan | 0 | TK_NotStart | 1208363553 | 399 | 1208363553_399
MRPP2-SUP.12090 | TT_Task | EMU - PO LV box - 3rd Fleet (6 trainsets) | 17/11/2022 | 14/12/2022 | nan | nan | 0 | TK_NotStart | 1208363553 | 400 | 1208363553_400
MRPP2-SUP.16220 | TT_Task | EMU - Production LV box - 3rd Fleet (6 trainsets) | 15/12/2022 | 26/02/2024 | nan | nan | 0 | TK_NotStart | 1208363553 | 400 | 1208363553_400
MRPP2-SUP.22170 | TT_Task | EMU - DEL LV box delivery - 3rd Fleet (6 trainsets) | 29/11/2023 | 23/05/2024 | nan | nan | 0 | TK_NotStart | 1208363553 | 401 | 1208363553_401
MRPP2-SUP.12110 | TT_Task | EMU - PO Battery ; battery box - 3rd Fleet (6 trainsets) | 17/11/2022 | 14/12/2022 | nan | nan | 0 | TK_NotStart | 1208363553 | 402 | 1208363553_402
MRPP2-SUP.16240 | TT_Task | EMU - Production Battery ; battery box - 3rd Fleet (6 trainsets) | 15/12/2022 | 26/02/2024 | nan | nan | 0 | TK_NotStart | 1208363553 | 402 | 1208363553_402
MRPP2-SUP.22190 | TT_Task | EMU - DEL Battery ; battery box delivery - 3rd Fleet (6 trainsets) | 29/11/2023 | 23/05/2024 | nan | nan | 0 | TK_NotStart | 1208363553 | 402 | 1208363553_402
MRPP2-SUP.11930 | TT_Task | EMU - PO Crash box - 3rd Fleet (6 trainsets) | 17/11/2022 | 14/12/2022 | nan | nan | 0 | TK_NotStart | 1208363553 | 403 | 1208363553_403
MRPP2-SUP.16060 | TT_Task | EMU - Production Crash box - 3rd Fleet (6 trainsets) | 15/12/2022 | 26/02/2024 | nan | nan | 0 | TK_NotStart | 1208363553 | 403 | 1208363553_403
MRPP2-SUP.22040 | TT_Task | EMU - DEL Crash box delivery - 3rd Fleet (6 trainsets) | 29/11/2023 | 23/05/2024 | nan | nan | 0 | TK_NotStart | 1208363553 | 404 | 1208363553_404
MRPP2-SUP.12060 | TT_Task | EMU - PO Interior and lighting - 3rd Fleet (6 trainsets) | 17/11/2022 | 14/12/2022 | nan | nan | 0 | TK_NotStart | 1208363553 | 406 | 1208363553_406
MRPP2-SUP.16190 | TT_Task | EMU - Production Interior and lighting - 3rd Fleet (6 trainsets) | 15/12/2022 | 28/12/2023 | nan | nan | 0 | TK_NotStart | 1208363553 | 407 | 1208363553_407
MRPP2-SUP.22140 | TT_Task | EMU - DEL Interior and lighting delivery - 3rd Fleet (6 trainsets) | 15/11/2023 | 09/05/2024 | nan | nan | 0 | TK_NotStart | 1208363553 | 407 | 1208363553_407
MRPP2-SUP.11920 | TT_Task | EMU - PO Hand rails - 3rd Fleet (6 trainsets) | 17/11/2022 | 14/12/2022 | nan | nan | 0 | TK_NotStart | 1208363553 | 408 | 1208363553_408
MRPP2-SUP.16050 | TT_Task | EMU - Production Hand rails - 3rd Fleet (6 trainsets) | 15/12/2022 | 26/02/2024 | nan | nan | 0 | TK_NotStart | 1208363553 | 408 | 1208363553_408
MRPP2-SUP.22030 | TT_Task | EMU - DEL Hand rails delivery - 3rd Fleet (6 trainsets) | 29/11/2023 | 23/05/2024 | nan | nan | 0 | TK_NotStart | 1208363553 | 409 | 1208363553_409
MRPP2-SUP.11890 | TT_Task | EMU - PO Grabpoles and grab handles - 3rd Fleet (6 trainsets) | 17/11/2022 | 14/12/2022 | nan | nan | 0 | TK_NotStart | 1208363553 | 410 | 1208363553_410
MRPP2-SUP.16020 | TT_Task | EMU - Production Grabpoles and grab handles - 3rd Fleet (6 trainsets) | 15/12/2022 | 26/02/2024 | nan | nan | 0 | TK_NotStart | 1208363553 | 410 | 1208363553_410
MRPP2-SUP.22000 | TT_Task | EMU - DEL Grabpoles and grab handles delivery - 3rd Fleet (6 trainsets) | 29/11/2023 | 23/05/2024 | nan | nan | 0 | TK_NotStart | 1208363553 | 410 | 1208363553_410
MRPP2-SUP.12080 | TT_Task | EMU - PO Cab garnishing - 3rd Fleet (6 trainsets) | 17/11/2022 | 14/12/2022 | nan | nan | 0 | TK_NotStart | 1208363553 | 411 | 1208363553_411
MRPP2-SUP.16210 | TT_Task | EMU - Production Cab garnishing - 3rd Fleet (6 trainsets) | 15/12/2022 | 26/02/2024 | nan | nan | 0 | TK_NotStart | 1208363553 | 411 | 1208363553_411
MRPP2-SUP.22160 | TT_Task | EMU - DEL Cab garnishing delivery - 3rd Fleet (6 trainsets) | 29/11/2023 | 23/05/2024 | nan | nan | 0 | TK_NotStart | 1208363553 | 411 | 1208363553_411
MRPP2-SUP.12030 | TT_Task | EMU - PO Seats - 3rd Fleet (6 trainsets) | 17/11/2022 | 14/12/2022 | nan | nan | 0 | TK_NotStart | 1208363553 | 412 | 1208363553_412
MRPP2-SUP.16160 | TT_Task | EMU - Production Seats - 3rd Fleet (6 trainsets) | 15/12/2022 | 26/02/2024 | nan | nan | 0 | TK_NotStart | 1208363553 | 412 | 1208363553_412
MRPP2-SUP.22130 | TT_Task | EMU - DEL Seats delivery - 3rd Fleet (6 trainsets) | 29/11/2023 | 23/05/2024 | nan | nan | 0 | TK_NotStart | 1208363553 | 413 | 1208363553_413
MRPP2-SUP.12000 | TT_Task | EMU - PO PACIS - 3rd Fleet (6 trainsets) | 17/11/2022 | 14/12/2022 | nan | nan | 0 | TK_NotStart | 1208363553 | 414 | 1208363553_414
MRPP2-SUP.16130 | TT_Task | EMU - Production PACIS - 3rd Fleet (6 trainsets) | 15/12/2022 | 28/12/2023 | nan | nan | 0 | TK_NotStart | 1208363553 | 414 | 1208363553_414
MRPP2-SUP.22100 | TT_Task | EMU - DEL PACIS delivery - 3rd Fleet (6 trainsets) | 15/11/2023 | 09/05/2024 | nan | nan | 0 | TK_NotStart | 1208363553 | 415 | 1208363553_415
MRPP2-SUP.11850 | TT_Task | EMU - PO MCP - 3rd Fleet (6 trainsets) | 17/11/2022 | 14/12/2022 | nan | nan | 0 | TK_NotStart | 1208363553 | 417 | 1208363553_417
MRPP2-SUP.15980 | TT_Task | EMU - Production MCP - 3rd Fleet (6 trainsets) | 15/12/2022 | 26/02/2024 | nan | nan | 0 | TK_NotStart | 1208363553 | 418 | 1208363553_418
MRPP2-SUP.21970 | TT_Task | EMU - DEL MCP delivery - 3rd Fleet (6 trainsets) | 29/11/2023 | 23/05/2024 | nan | nan | 0 | TK_NotStart | 1208363553 | 419 | 1208363553_419
MRPP2-SUP.12020 | TT_Task | EMU - PO TCMS equipment - 3rd Fleet (6 trainsets) | 17/11/2022 | 14/12/2022 | nan | nan | 0 | TK_NotStart | 1208363553 | 421 | 1208363553_421
MRPP2-SUP.16150 | TT_Task | EMU - Production TCMS equipment - 3rd Fleet (6 trainsets) | 15/12/2022 | 28/12/2023 | nan | nan | 0 | TK_NotStart | 1208363553 | 422 | 1208363553_422
MRPP2-SUP.22120 | TT_Task | EMU - DEL TCMS equipment delivery - 3rd Fleet (6 trainsets) | 15/11/2023 | 09/05/2024 | nan | nan | 0 | TK_NotStart | 1208363553 | 422 | 1208363553_422
MRPP2-SUP.11780 | TT_Task | EMU - PO HVAC - 3rd Fleet (6 trainsets) | 21/09/2022 | 19/10/2022 | nan | nan | 0 | TK_NotStart | 1208363553 | 348 | 1208363553_348
MRPP2-SUP.15910 | TT_Task | EMU - Production HVAC - 3rd Fleet (6 trainsets) | 20/10/2022 | 28/12/2023 | nan | nan | 0 | TK_NotStart | 1208363553 | 348 | 1208363553_348
MRPP2-SUP.21940 | TT_Task | EMU - DEL HVAC delivery - 3rd Fleet (6 trainsets) | 22/08/2023 | 12/02/2024 | nan | nan | 0 | TK_NotStart | 1208363553 | 349 | 1208363553_349
MRPP2-SUP.11800 | TT_Task | EMU - PO Windows - 3rd Fleet (6 trainsets) | 21/09/2022 | 19/10/2022 | nan | nan | 0 | TK_NotStart | 1208363553 | 351 | 1208363553_351
MRPP2-SUP.15930 | TT_Task | EMU - Production Windows - 3rd Fleet (6 trainsets) | 20/10/2022 | 28/12/2023 | nan | nan | 0 | TK_NotStart | 1208363553 | 352 | 1208363553_352
MRPP2-SUP.22200 | TT_Task | EMU - DEL Windows delivery - 3rd Fleet (6 trainsets) | 22/08/2023 | 12/02/2024 | nan | nan | 0 | TK_NotStart | 1208363553 | 353 | 1208363553_353
MRPP2-SUP.11820 | TT_Task | EMU - PO Passenger doors - 3rd Fleet (6 trainsets) | 21/09/2022 | 19/10/2022 | nan | nan | 0 | TK_NotStart | 1208363553 | 354 | 1208363553_354
MRPP2-SUP.15950 | TT_Task | EMU - Production Passenger doors - 3rd Fleet (6 trainsets) | 20/10/2022 | 28/12/2023 | nan | nan | 0 | TK_NotStart | 1208363553 | 354 | 1208363553_354
MRPP2-SUP.22220 | TT_Task | EMU - DEL Passenger doors delivery - 3rd Fleet (6 trainsets) | 22/08/2023 | 12/02/2024 | nan | nan | 0 | TK_NotStart | 1208363553 | 355 | 1208363553_355
MRPP2-SUP.12130 | TT_Task | EMU - PO Bogie Frame - 4th Fleet (6 trainsets) | 06/09/2023 | 04/10/2023 | nan | nan | 0 | TK_NotStart | 1208363553 | 337 | 1208363553_337
MRPP2-SUP.16260 | TT_Task | EMU - Production Bogie Frame - 4th Fleet (6 trainsets) | 05/10/2023 | 15/10/2024 | nan | nan | 0 | TK_NotStart | 1208363553 | 337 | 1208363553_337
MRPP2-SUP.22310 | TT_Task | EMU - DEL Bogie Frame delivery - 4th Fleet (6 trainsets) | 06/08/2024 | 24/01/2025 | nan | nan | 0 | TK_NotStart | 1208363553 | 339 | 1208363553_339
MRPP2-SUP.12150 | TT_Task | EMU - PO Bogie Assy - 4th Fleet (6 trainsets) | 06/09/2023 | 04/10/2023 | nan | nan | 0 | TK_NotStart | 1208363553 | 423 | 1208363553_423
MRPP2-SUP.16280 | TT_Task | EMU - Production Bogie Assy - 4th Fleet (6 trainsets) | 05/10/2023 | 15/10/2024 | nan | nan | 0 | TK_NotStart | 1208363553 | 423 | 1208363553_423
MRPP2-SUP.22330 | TT_Task | EMU - DEL Bogie Assy delivery - 4th Fleet (6 trainsets) | 06/08/2024 | 24/01/2025 | nan | nan | 0 | TK_NotStart | 1208363553 | 339 | 1208363553_339
MRPP2-SUP.12140 | TT_Task | EMU - PO Axle box ; bearing - 4th Fleet (6 trainsets) | 06/09/2023 | 04/10/2023 | nan | nan | 0 | TK_NotStart | 1208363553 | 341 | 1208363553_341
MRPP2-SUP.16270 | TT_Task | EMU - Production Axle box ; bearing - 4th Fleet (6 trainsets) | 05/10/2023 | 10/12/2024 | nan | nan | 0 | TK_NotStart | 1208363553 | 341 | 1208363553_341
MRPP2-SUP.22320 | TT_Task | EMU - DEL Axle box ; bearing delivery - 4th Fleet (6 trainsets) | 17/09/2024 | 10/03/2025 | nan | nan | 0 | TK_NotStart | 1208363553 | 341 | 1208363553_341
MRPP2-SUP.12120 | TT_Task | EMU - PO Wheels - 4th Fleet (6 trainsets) | 06/09/2023 | 04/10/2023 | nan | nan | 0 | TK_NotStart | 1208363553 | 344 | 1208363553_344
MRPP2-SUP.16250 | TT_Task | EMU - Production Wheels - 4th Fleet (6 trainsets) | 05/10/2023 | 10/12/2024 | nan | nan | 0 | TK_NotStart | 1208363553 | 344 | 1208363553_344
MRPP2-SUP.22290 | TT_Task | EMU - DEL Wheels delivery - 4th Fleet (6 trainsets) | 17/09/2024 | 10/03/2025 | nan | nan | 0 | TK_NotStart | 1208363553 | 346 | 1208363553_346
MRPP2-SUP.12190 | TT_Task | EMU - PO Axles - 4th Fleet (6 trainsets) | 06/09/2023 | 04/10/2023 | nan | nan | 0 | TK_NotStart | 1208363553 | 356 | 1208363553_356
MRPP2-SUP.16320 | TT_Task | EMU - Production Axles - 4th Fleet (6 trainsets) | 05/10/2023 | 10/12/2024 | nan | nan | 0 | TK_NotStart | 1208363553 | 356 | 1208363553_356
MRPP2-SUP.22370 | TT_Task | EMU - DEL Axles delivery - 4th Fleet (6 trainsets) | 17/09/2024 | 10/03/2025 | nan | nan | 0 | TK_NotStart | 1208363553 | 357 | 1208363553_357
MRPP2-SUP.12200 | TT_Task | EMU - PO Brakes - 4th Fleet (6 trainsets) | 06/09/2023 | 04/10/2023 | nan | nan | 0 | TK_NotStart | 1208363553 | 358 | 1208363553_358
MRPP2-SUP.16330 | TT_Task | EMU - Production Brakes - 4th Fleet (6 trainsets) | 05/10/2023 | 10/12/2024 | nan | nan | 0 | TK_NotStart | 1208363553 | 358 | 1208363553_358
MRPP2-SUP.22390 | TT_Task | EMU - DEL Brakes delivery - 4th Fleet (6 trainsets) | 17/09/2024 | 10/03/2025 | nan | nan | 0 | TK_NotStart | 1208363553 | 359 | 1208363553_359
MRPP2-SUP.12180 | TT_Task | EMU - PO Traction converter - 4th Fleet (6 trainsets) | 06/09/2023 | 04/10/2023 | nan | nan | 0 | TK_NotStart | 1208363553 | 360 | 1208363553_360
MRPP2-SUP.16310 | TT_Task | EMU - Production Traction converter - 4th Fleet (6 trainsets) | 05/10/2023 | 15/10/2024 | nan | nan | 0 | TK_NotStart | 1208363553 | 360 | 1208363553_360
MRPP2-SUP.22360 | TT_Task | EMU - DEL Traction converter delivery - 4th Fleet (6 trainsets) | 20/08/2024 | 10/02/2025 | nan | nan | 0 | TK_NotStart | 1208363553 | 361 | 1208363553_361
MRPP2-SUP.12170 | TT_Task | EMU - PO Traction motor - 4th Fleet (6 trainsets) | 06/09/2023 | 04/10/2023 | nan | nan | 0 | TK_NotStart | 1208363553 | 362 | 1208363553_362
MRPP2-SUP.16300 | TT_Task | EMU - Production Traction motor - 4th Fleet (6 trainsets) | 05/10/2023 | 15/10/2024 | nan | nan | 0 | TK_NotStart | 1208363553 | 362 | 1208363553_362
MRPP2-SUP.22350 | TT_Task | EMU - DEL Traction motor delivery - 4th Fleet (6 trainsets) | 20/08/2024 | 10/02/2025 | nan | nan | 0 | TK_NotStart | 1208363553 | 363 | 1208363553_363
MRPP2-SUP.12240 | TT_Task | EMU - PO Primary Suspension - 4th Fleet (6 trainsets) | 06/09/2023 | 04/10/2023 | nan | nan | 0 | TK_NotStart | 1208363553 | 364 | 1208363553_364
MRPP2-SUP.16370 | TT_Task | EMU - Production Primary Suspension - 4th Fleet (6 trainsets) | 05/10/2023 | 10/12/2024 | nan | nan | 0 | TK_NotStart | 1208363553 | 365 | 1208363553_365
MRPP2-SUP.22450 | TT_Task | EMU - DEL Primary Suspension delivery - 4th Fleet (6 trainsets) | 17/09/2024 | 10/03/2025 | nan | nan | 0 | TK_NotStart | 1208363553 | 367 | 1208363553_367
MRPP2-SUP.12250 | TT_Task | EMU - PO Secondary Suspension - 4th Fleet (6 trainsets) | 06/09/2023 | 04/10/2023 | nan | nan | 0 | TK_NotStart | 1208363553 | 364 | 1208363553_364
MRPP2-SUP.16380 | TT_Task | EMU - Production Secondary Suspension - 4th Fleet (6 trainsets) | 05/10/2023 | 10/12/2024 | nan | nan | 0 | TK_NotStart | 1208363553 | 365 | 1208363553_365
MRPP2-SUP.22460 | TT_Task | EMU - DEL Secondary Suspension delivery - 4th Fleet (6 trainsets) | 17/09/2024 | 10/03/2025 | nan | nan | 0 | TK_NotStart | 1208363553 | 367 | 1208363553_367
MRPP2-SUP.12230 | TT_Task | EMU - PO CVS - 4th Fleet (6 trainsets) | 06/09/2023 | 04/10/2023 | nan | nan | 0 | TK_NotStart | 1208363553 | 369 | 1208363553_369
MRPP2-SUP.16360 | TT_Task | EMU - Production CVS - 4th Fleet (6 trainsets) | 05/10/2023 | 10/12/2024 | nan | nan | 0 | TK_NotStart | 1208363553 | 370 | 1208363553_370
MRPP2-SUP.22300 | TT_Task | EMU - DEL CVS delivery - 4th Fleet (6 trainsets) | 03/09/2024 | 24/02/2025 | nan | nan | 0 | TK_NotStart | 1208363553 | 371 | 1208363553_371
MRPP2-SUP.12220 | TT_Task | EMU - PO Coupler - 4th Fleet (6 trainsets) | 06/09/2023 | 04/10/2023 | nan | nan | 0 | TK_NotStart | 1208363553 | 372 | 1208363553_372
MRPP2-SUP.16350 | TT_Task | EMU - Production Coupler - 4th Fleet (6 trainsets) | 05/10/2023 | 10/12/2024 | nan | nan | 0 | TK_NotStart | 1208363553 | 372 | 1208363553_372
MRPP2-SUP.22280 | TT_Task | EMU - DEL Coupler delivery - 4th Fleet (6 trainsets) | 17/09/2024 | 10/03/2025 | nan | nan | 0 | TK_NotStart | 1208363553 | 373 | 1208363553_373
MRPP2-SUP.12270 | TT_Task | EMU - PO (Purchase Order)-Gangway - 4th Fleet (6 trainsets) | 06/09/2023 | 04/10/2023 | nan | nan | 0 | TK_NotStart | 1208363553 | 374 | 1208363553_374
MRPP2-SUP.16400 | TT_Task | EMU - Production ( Component process time)-Gangway - 4th Fleet (6 trainsets) | 05/10/2023 | 10/12/2024 | nan | nan | 0 | TK_NotStart | 1208363553 | 375 | 1208363553_375
MRPP2-SUP.22380 | TT_Task | EMU - DEL Component-Gangway Delivery - 4th Fleet (6 trainsets) | 17/09/2024 | 10/03/2025 | nan | nan | 0 | TK_NotStart | 1208363553 | 376 | 1208363553_376
MRPP2-SUP.12280 | TT_Task | EMU - PO Pipes - 4th Fleet (6 trainsets) | 06/09/2023 | 04/10/2023 | nan | nan | 0 | TK_NotStart | 1208363553 | 377 | 1208363553_377
MRPP2-SUP.16410 | TT_Task | EMU - Production Pipes - 4th Fleet (6 trainsets) | 05/10/2023 | 10/12/2024 | nan | nan | 0 | TK_NotStart | 1208363553 | 377 | 1208363553_377
MRPP2-SUP.22410 | TT_Task | EMU - DEL Pipes delivery - 4th Fleet (6 trainsets) | 17/09/2024 | 10/03/2025 | nan | nan | 0 | TK_NotStart | 1208363553 | 378 | 1208363553_378
MRPP2-SUP.12290 | TT_Task | EMU - PO Cables - 4th Fleet (6 trainsets) | 06/09/2023 | 04/10/2023 | nan | nan | 0 | TK_NotStart | 1208363553 | 381 | 1208363553_381
MRPP2-SUP.16420 | TT_Task | EMU - Production Cables - 4th Fleet (6 trainsets) | 05/10/2023 | 10/12/2024 | nan | nan | 0 | TK_NotStart | 1208363553 | 381 | 1208363553_381
MRPP2-SUP.22420 | TT_Task | EMU - DEL Cables delivery - 4th Fleet (6 trainsets) | 17/09/2024 | 10/03/2025 | nan | nan | 0 | TK_NotStart | 1208363553 | 382 | 1208363553_382
MRPP2-SUP.12300 | TT_Task | EMU - PO Cable trays - 4th Fleet (6 trainsets) | 06/09/2023 | 04/10/2023 | nan | nan | 0 | TK_NotStart | 1208363553 | 383 | 1208363553_383
MRPP2-SUP.16430 | TT_Task | EMU - Production Cable trays - 4th Fleet (6 trainsets) | 05/10/2023 | 10/12/2024 | nan | nan | 0 | TK_NotStart | 1208363553 | 383 | 1208363553_383
MRPP2-SUP.22430 | TT_Task | EMU - DEL Cable trays delivery - 4th Fleet (6 trainsets) | 17/09/2024 | 10/03/2025 | nan | nan | 0 | TK_NotStart | 1208363553 | 383 | 1208363553_383
MRPP2-SUP.12310 | TT_Task | EMU - PO Floor covering - 4th Fleet (6 trainsets) | 06/09/2023 | 04/10/2023 | nan | nan | 0 | TK_NotStart | 1208363553 | 384 | 1208363553_384
MRPP2-SUP.16440 | TT_Task | EMU - Production Floor covering - 4th Fleet (6 trainsets) | 05/10/2023 | 10/12/2024 | nan | nan | 0 | TK_NotStart | 1208363553 | 385 | 1208363553_385
MRPP2-SUP.22440 | TT_Task | EMU - DEL Floor covering delivery - 4th Fleet (6 trainsets) | 17/09/2024 | 10/03/2025 | nan | nan | 0 | TK_NotStart | 1208363553 | 386 | 1208363553_386
MRPP2-SUP.12330 | TT_Task | EMU - PO Pantograph - 4th Fleet (6 trainsets) | 06/09/2023 | 04/10/2023 | nan | nan | 0 | TK_NotStart | 1208363553 | 387 | 1208363553_387
MRPP2-SUP.16460 | TT_Task | EMU - Production Pantograph - 4th Fleet (6 trainsets) | 05/10/2023 | 10/12/2024 | nan | nan | 0 | TK_NotStart | 1208363553 | 387 | 1208363553_387
MRPP2-SUP.22530 | TT_Task | EMU - DEL Pantograph delivery - 4th Fleet (6 trainsets) | 17/09/2024 | 10/03/2025 | nan | nan | 0 | TK_NotStart | 1208363553 | 388 | 1208363553_388
MRPP2-SUP.12340 | TT_Task | EMU - PO Wind screen - 4th Fleet (6 trainsets) | 06/09/2023 | 04/10/2023 | nan | nan | 0 | TK_NotStart | 1208363553 | 389 | 1208363553_389
MRPP2-SUP.16470 | TT_Task | EMU - Production Wind screen - 4th Fleet (6 trainsets) | 05/10/2023 | 10/12/2024 | nan | nan | 0 | TK_NotStart | 1208363553 | 389 | 1208363553_389
MRPP2-SUP.22560 | TT_Task | EMU - DEL Wind screen delivery - 4th Fleet (6 trainsets) | 17/09/2024 | 10/03/2025 | nan | nan | 0 | TK_NotStart | 1208363553 | 390 | 1208363553_390
MRPP2-SUP.12410 | TT_Task | EMU - PO Front mask - 4th Fleet (6 trainsets) | 05/10/2023 | 01/11/2023 | nan | nan | 0 | TK_NotStart | 1208363553 | 391 | 1208363553_391
MRPP2-SUP.16540 | TT_Task | EMU - Production Front mask - 4th Fleet (6 trainsets) | 02/11/2023 | 10/01/2025 | nan | nan | 0 | TK_NotStart | 1208363553 | 391 | 1208363553_391
MRPP2-SUP.22620 | TT_Task | EMU - DEL Front mask delivery - 4th Fleet (6 trainsets) | 16/10/2024 | 07/04/2025 | nan | nan | 0 | TK_NotStart | 1208363553 | 392 | 1208363553_392
MRPP2-SUP.12510 | TT_Task | EMU - PO Relays - 4th Fleet (6 trainsets) | 05/10/2023 | 01/11/2023 | nan | nan | 0 | TK_NotStart | 1208363553 | 393 | 1208363553_393
MRPP2-SUP.16640 | TT_Task | EMU - Production Relays - 4th Fleet (6 trainsets) | 02/11/2023 | 10/01/2025 | nan | nan | 0 | TK_NotStart | 1208363553 | 393 | 1208363553_393
MRPP2-SUP.22750 | TT_Task | EMU - DEL Relays delivery - 4th Fleet (6 trainsets) | 16/10/2024 | 07/04/2025 | nan | nan | 0 | TK_NotStart | 1208363553 | 394 | 1208363553_394
MRPP2-SUP.12530 | TT_Task | EMU - PO Cabinets - 4th Fleet (6 trainsets) | 05/10/2023 | 01/11/2023 | nan | nan | 0 | TK_NotStart | 1208363553 | 395 | 1208363553_395
MRPP2-SUP.16660 | TT_Task | EMU - Production Cabinets - 4th Fleet (6 trainsets) | 02/11/2023 | 10/01/2025 | nan | nan | 0 | TK_NotStart | 1208363553 | 395 | 1208363553_395
MRPP2-SUP.22770 | TT_Task | EMU - DEL Cabinets delivery - 4th Fleet (6 trainsets) | 16/10/2024 | 07/04/2025 | nan | nan | 0 | TK_NotStart | 1208363553 | 396 | 1208363553_396
MRPP2-SUP.12490 | TT_Task | EMU - PO Elec comp - 4th Fleet (6 trainsets) | 05/10/2023 | 01/11/2023 | nan | nan | 0 | TK_NotStart | 1208363553 | 397 | 1208363553_397
MRPP2-SUP.16620 | TT_Task | EMU - Production Elec comp - 4th Fleet (6 trainsets) | 02/11/2023 | 10/01/2025 | nan | nan | 0 | TK_NotStart | 1208363553 | 398 | 1208363553_398
MRPP2-SUP.22730 | TT_Task | EMU - DEL Elec comp delivery - 4th Fleet (6 trainsets) | 16/10/2024 | 07/04/2025 | nan | nan | 0 | TK_NotStart | 1208363553 | 399 | 1208363553_399
MRPP2-SUP.12540 | TT_Task | EMU - PO LV box - 4th Fleet (6 trainsets) | 05/10/2023 | 01/11/2023 | nan | nan | 0 | TK_NotStart | 1208363553 | 400 | 1208363553_400
MRPP2-SUP.16670 | TT_Task | EMU - Production LV box - 4th Fleet (6 trainsets) | 02/11/2023 | 10/01/2025 | nan | nan | 0 | TK_NotStart | 1208363553 | 400 | 1208363553_400
MRPP2-SUP.22780 | TT_Task | EMU - DEL LV box delivery - 4th Fleet (6 trainsets) | 16/10/2024 | 07/04/2025 | nan | nan | 0 | TK_NotStart | 1208363553 | 401 | 1208363553_401
MRPP2-SUP.12550 | TT_Task | EMU - PO Battery ; battery box - 4th Fleet (6 trainsets) | 05/10/2023 | 01/11/2023 | nan | nan | 0 | TK_NotStart | 1208363553 | 402 | 1208363553_402
MRPP2-SUP.16680 | TT_Task | EMU - Production Battery ; battery box - 4th Fleet (6 trainsets) | 02/11/2023 | 10/01/2025 | nan | nan | 0 | TK_NotStart | 1208363553 | 402 | 1208363553_402
MRPP2-SUP.22790 | TT_Task | EMU - DEL Battery ; battery box delivery - 4th Fleet (6 trainsets) | 16/10/2024 | 07/04/2025 | nan | nan | 0 | TK_NotStart | 1208363553 | 402 | 1208363553_402
MRPP2-SUP.12500 | TT_Task | EMU - PO Crash box - 4th Fleet (6 trainsets) | 05/10/2023 | 01/11/2023 | nan | nan | 0 | TK_NotStart | 1208363553 | 403 | 1208363553_403
MRPP2-SUP.16630 | TT_Task | EMU - Production Crash box - 4th Fleet (6 trainsets) | 02/11/2023 | 10/01/2025 | nan | nan | 0 | TK_NotStart | 1208363553 | 403 | 1208363553_403
MRPP2-SUP.22740 | TT_Task | EMU - DEL Crash box delivery - 4th Fleet (6 trainsets) | 16/10/2024 | 07/04/2025 | nan | nan | 0 | TK_NotStart | 1208363553 | 404 | 1208363553_404
MRPP2-SUP.12520 | TT_Task | EMU - PO Interior and lighting - 4th Fleet (6 trainsets) | 05/10/2023 | 01/11/2023 | nan | nan | 0 | TK_NotStart | 1208363553 | 406 | 1208363553_406
MRPP2-SUP.16650 | TT_Task | EMU - Production Interior and lighting - 4th Fleet (6 trainsets) | 02/11/2023 | 10/12/2024 | nan | nan | 0 | TK_NotStart | 1208363553 | 407 | 1208363553_407
MRPP2-SUP.22760 | TT_Task | EMU - DEL Interior and lighting delivery - 4th Fleet (6 trainsets) | 02/10/2024 | 24/03/2025 | nan | nan | 0 | TK_NotStart | 1208363553 | 407 | 1208363553_407
MRPP2-SUP.12570 | TT_Task | EMU - PO Hand rails - 4th Fleet (6 trainsets) | 05/10/2023 | 01/11/2023 | nan | nan | 0 | TK_NotStart | 1208363553 | 408 | 1208363553_408
MRPP2-SUP.16700 | TT_Task | EMU - Production Hand rails - 4th Fleet (6 trainsets) | 02/11/2023 | 10/01/2025 | nan | nan | 0 | TK_NotStart | 1208363553 | 408 | 1208363553_408
MRPP2-SUP.22860 | TT_Task | EMU - DEL Hand rails delivery - 4th Fleet (6 trainsets) | 16/10/2024 | 07/04/2025 | nan | nan | 0 | TK_NotStart | 1208363553 | 409 | 1208363553_409
MRPP2-SUP.12560 | TT_Task | EMU - PO Grabpoles and grab handles - 4th Fleet (6 trainsets) | 05/10/2023 | 01/11/2023 | nan | nan | 0 | TK_NotStart | 1208363553 | 410 | 1208363553_410
MRPP2-SUP.16690 | TT_Task | EMU - Production Grabpoles and grab handles - 4th Fleet (6 trainsets) | 02/11/2023 | 10/01/2025 | nan | nan | 0 | TK_NotStart | 1208363553 | 410 | 1208363553_410
MRPP2-SUP.22850 | TT_Task | EMU - DEL Grabpoles and grab handles delivery - 4th Fleet (6 trainsets) | 16/10/2024 | 07/04/2025 | nan | nan | 0 | TK_NotStart | 1208363553 | 410 | 1208363553_410
MRPP2-SUP.12580 | TT_Task | EMU - PO Cab garnishing - 4th Fleet (6 trainsets) | 05/10/2023 | 01/11/2023 | nan | nan | 0 | TK_NotStart | 1208363553 | 411 | 1208363553_411
MRPP2-SUP.16710 | TT_Task | EMU - Production Cab garnishing - 4th Fleet (6 trainsets) | 02/11/2023 | 10/01/2025 | nan | nan | 0 | TK_NotStart | 1208363553 | 411 | 1208363553_411
MRPP2-SUP.22870 | TT_Task | EMU - DEL Cab garnishing delivery - 4th Fleet (6 trainsets) | 16/10/2024 | 07/04/2025 | nan | nan | 0 | TK_NotStart | 1208363553 | 411 | 1208363553_411
MRPP2-SUP.12610 | TT_Task | EMU - PO Seats - 4th Fleet (6 trainsets) | 05/10/2023 | 01/11/2023 | nan | nan | 0 | TK_NotStart | 1208363553 | 412 | 1208363553_412
MRPP2-SUP.16740 | TT_Task | EMU - Production Seats - 4th Fleet (6 trainsets) | 02/11/2023 | 10/01/2025 | nan | nan | 0 | TK_NotStart | 1208363553 | 412 | 1208363553_412
MRPP2-SUP.22900 | TT_Task | EMU - DEL Seats delivery - 4th Fleet (6 trainsets) | 02/10/2024 | 24/03/2025 | nan | nan | 0 | TK_NotStart | 1208363553 | 413 | 1208363553_413
MRPP2-SUP.12600 | TT_Task | EMU - PO PACIS - 4th Fleet (6 trainsets) | 05/10/2023 | 01/11/2023 | nan | nan | 0 | TK_NotStart | 1208363553 | 414 | 1208363553_414
MRPP2-SUP.16730 | TT_Task | EMU - Production PACIS - 4th Fleet (6 trainsets) | 02/11/2023 | 10/12/2024 | nan | nan | 0 | TK_NotStart | 1208363553 | 414 | 1208363553_414
MRPP2-SUP.22890 | TT_Task | EMU - DEL PACIS delivery - 4th Fleet (6 trainsets) | 02/10/2024 | 24/03/2025 | nan | nan | 0 | TK_NotStart | 1208363553 | 415 | 1208363553_415
MRPP2-SUP.12590 | TT_Task | EMU - PO MCP - 4th Fleet (6 trainsets) | 05/10/2023 | 01/11/2023 | nan | nan | 0 | TK_NotStart | 1208363553 | 417 | 1208363553_417
MRPP2-SUP.16720 | TT_Task | EMU - Production MCP - 4th Fleet (6 trainsets) | 02/11/2023 | 10/01/2025 | nan | nan | 0 | TK_NotStart | 1208363553 | 418 | 1208363553_418
MRPP2-SUP.22880 | TT_Task | EMU - DEL MCP delivery - 4th Fleet (6 trainsets) | 02/10/2024 | 24/03/2025 | nan | nan | 0 | TK_NotStart | 1208363553 | 419 | 1208363553_419
MRPP2-SUP.12620 | TT_Task | EMU - PO TCMS equipment - 4th Fleet (6 trainsets) | 05/10/2023 | 01/11/2023 | nan | nan | 0 | TK_NotStart | 1208363553 | 421 | 1208363553_421
MRPP2-SUP.16750 | TT_Task | EMU - Production TCMS equipment - 4th Fleet (6 trainsets) | 02/11/2023 | 10/12/2024 | nan | nan | 0 | TK_NotStart | 1208363553 | 422 | 1208363553_422
MRPP2-SUP.22910 | TT_Task | EMU - DEL TCMS equipment delivery - 4th Fleet (6 trainsets) | 02/10/2024 | 24/03/2025 | nan | nan | 0 | TK_NotStart | 1208363553 | 422 | 1208363553_422
MRPP2-SUP.12160 | TT_Task | EMU - PO HVAC - 4th Fleet (6 trainsets) | 06/09/2023 | 04/10/2023 | nan | nan | 0 | TK_NotStart | 1208363553 | 348 | 1208363553_348
MRPP2-SUP.16290 | TT_Task | EMU - Production HVAC - 4th Fleet (6 trainsets) | 05/10/2023 | 10/12/2024 | nan | nan | 0 | TK_NotStart | 1208363553 | 348 | 1208363553_348
MRPP2-SUP.22340 | TT_Task | EMU - DEL HVAC delivery - 4th Fleet (6 trainsets) | 20/08/2024 | 10/02/2025 | nan | nan | 0 | TK_NotStart | 1208363553 | 349 | 1208363553_349
MRPP2-SUP.12210 | TT_Task | EMU - PO Windows - 4th Fleet (6 trainsets) | 06/09/2023 | 04/10/2023 | nan | nan | 0 | TK_NotStart | 1208363553 | 351 | 1208363553_351
MRPP2-SUP.16340 | TT_Task | EMU - Production Windows - 4th Fleet (6 trainsets) | 05/10/2023 | 10/12/2024 | nan | nan | 0 | TK_NotStart | 1208363553 | 352 | 1208363553_352
MRPP2-SUP.22400 | TT_Task | EMU - DEL Windows delivery - 4th Fleet (6 trainsets) | 20/08/2024 | 10/02/2025 | nan | nan | 0 | TK_NotStart | 1208363553 | 353 | 1208363553_353
MRPP2-SUP.12260 | TT_Task | EMU - PO Passenger doors - 4th Fleet (6 trainsets) | 06/09/2023 | 04/10/2023 | nan | nan | 0 | TK_NotStart | 1208363553 | 354 | 1208363553_354
MRPP2-SUP.16390 | TT_Task | EMU - Production Passenger doors - 4th Fleet (6 trainsets) | 05/10/2023 | 10/12/2024 | nan | nan | 0 | TK_NotStart | 1208363553 | 354 | 1208363553_354
MRPP2-SUP.22480 | TT_Task | EMU - DEL Passenger doors delivery - 4th Fleet (6 trainsets) | 20/08/2024 | 10/02/2025 | nan | nan | 0 | TK_NotStart | 1208363553 | 355 | 1208363553_355
MRPP2-SUP.12640 | TT_Task | EMU - PO Bogie Frame - 5th Fleet (6 trainsets) | 04/09/2024 | 02/10/2024 | nan | nan | 0 | TK_NotStart | 1208363553 | 337 | 1208363553_337
MRPP2-SUP.16770 | TT_Task | EMU - Production Bogie Frame - 5th Fleet (6 trainsets) | 03/10/2024 | 14/10/2025 | nan | nan | 0 | TK_NotStart | 1208363553 | 337 | 1208363553_337
MRPP2-SUP.22950 | TT_Task | EMU - DEL Bogie Frame delivery - 5th Fleet (6 trainsets) | 22/07/2025 | 09/01/2026 | nan | nan | 0 | TK_NotStart | 1208363553 | 339 | 1208363553_339
MRPP2-SUP.12660 | TT_Task | EMU - PO Bogie Assy - 5th Fleet (6 trainsets) | 04/09/2024 | 02/10/2024 | nan | nan | 0 | TK_NotStart | 1208363553 | 423 | 1208363553_423
MRPP2-SUP.16790 | TT_Task | EMU - Production Bogie Assy - 5th Fleet (6 trainsets) | 03/10/2024 | 14/10/2025 | nan | nan | 0 | TK_NotStart | 1208363553 | 423 | 1208363553_423
MRPP2-SUP.22970 | TT_Task | EMU - DEL Bogie Assy delivery - 5th Fleet (6 trainsets) | 22/07/2025 | 09/01/2026 | nan | nan | 0 | TK_NotStart | 1208363553 | 339 | 1208363553_339
MRPP2-SUP.12650 | TT_Task | EMU - PO Axle box ; bearing - 5th Fleet (6 trainsets) | 04/09/2024 | 02/10/2024 | nan | nan | 0 | TK_NotStart | 1208363553 | 341 | 1208363553_341
MRPP2-SUP.16780 | TT_Task | EMU - Production Axle box ; bearing - 5th Fleet (6 trainsets) | 03/10/2024 | 09/12/2025 | nan | nan | 0 | TK_NotStart | 1208363553 | 341 | 1208363553_341
MRPP2-SUP.22960 | TT_Task | EMU - DEL Axle box ; bearing delivery - 5th Fleet (6 trainsets) | 16/09/2025 | 09/03/2026 | nan | nan | 0 | TK_NotStart | 1208363553 | 341 | 1208363553_341
MRPP2-SUP.12630 | TT_Task | EMU - PO Wheels - 5th Fleet (6 trainsets) | 04/09/2024 | 02/10/2024 | nan | nan | 0 | TK_NotStart | 1208363553 | 344 | 1208363553_344
MRPP2-SUP.16760 | TT_Task | EMU - Production Wheels - 5th Fleet (6 trainsets) | 03/10/2024 | 09/12/2025 | nan | nan | 0 | TK_NotStart | 1208363553 | 344 | 1208363553_344
MRPP2-SUP.22930 | TT_Task | EMU - DEL Wheels delivery - 5th Fleet (6 trainsets) | 16/09/2025 | 09/03/2026 | nan | nan | 0 | TK_NotStart | 1208363553 | 346 | 1208363553_346
MRPP2-SUP.12700 | TT_Task | EMU - PO Axles - 5th Fleet (6 trainsets) | 03/10/2024 | 30/10/2024 | nan | nan | 0 | TK_NotStart | 1208363553 | 356 | 1208363553_356
MRPP2-SUP.16830 | TT_Task | EMU - Production Axles - 5th Fleet (6 trainsets) | 31/10/2024 | 09/01/2026 | nan | nan | 0 | TK_NotStart | 1208363553 | 356 | 1208363553_356
MRPP2-SUP.23010 | TT_Task | EMU - DEL Axles delivery - 5th Fleet (6 trainsets) | 15/10/2025 | 06/04/2026 | nan | nan | 0 | TK_NotStart | 1208363553 | 357 | 1208363553_357
MRPP2-SUP.12710 | TT_Task | EMU - PO Brakes - 5th Fleet (6 trainsets) | 03/10/2024 | 30/10/2024 | nan | nan | 0 | TK_NotStart | 1208363553 | 358 | 1208363553_358
MRPP2-SUP.16840 | TT_Task | EMU - Production Brakes - 5th Fleet (6 trainsets) | 31/10/2024 | 09/01/2026 | nan | nan | 0 | TK_NotStart | 1208363553 | 358 | 1208363553_358
MRPP2-SUP.23030 | TT_Task | EMU - DEL Brakes delivery - 5th Fleet (6 trainsets) | 15/10/2025 | 06/04/2026 | nan | nan | 0 | TK_NotStart | 1208363553 | 359 | 1208363553_359
MRPP2-SUP.12690 | TT_Task | EMU - PO Traction converter - 5th Fleet (6 trainsets) | 03/10/2024 | 30/10/2024 | nan | nan | 0 | TK_NotStart | 1208363553 | 360 | 1208363553_360
MRPP2-SUP.16820 | TT_Task | EMU - Production Traction converter - 5th Fleet (6 trainsets) | 31/10/2024 | 11/11/2025 | nan | nan | 0 | TK_NotStart | 1208363553 | 360 | 1208363553_360
MRPP2-SUP.23000 | TT_Task | EMU - DEL Traction converter delivery - 5th Fleet (6 trainsets) | 16/09/2025 | 09/03/2026 | nan | nan | 0 | TK_NotStart | 1208363553 | 361 | 1208363553_361
MRPP2-SUP.12680 | TT_Task | EMU - PO Traction motor - 5th Fleet (6 trainsets) | 03/10/2024 | 30/10/2024 | nan | nan | 0 | TK_NotStart | 1208363553 | 362 | 1208363553_362
MRPP2-SUP.16810 | TT_Task | EMU - Production Traction motor - 5th Fleet (6 trainsets) | 31/10/2024 | 11/11/2025 | nan | nan | 0 | TK_NotStart | 1208363553 | 362 | 1208363553_362
MRPP2-SUP.22990 | TT_Task | EMU - DEL Traction motor delivery - 5th Fleet (6 trainsets) | 16/09/2025 | 09/03/2026 | nan | nan | 0 | TK_NotStart | 1208363553 | 363 | 1208363553_363
MRPP2-SUP.12750 | TT_Task | EMU - PO Primary Suspension - 5th Fleet (6 trainsets) | 03/10/2024 | 30/10/2024 | nan | nan | 0 | TK_NotStart | 1208363553 | 364 | 1208363553_364
MRPP2-SUP.16880 | TT_Task | EMU - Production Primary Suspension - 5th Fleet (6 trainsets) | 31/10/2024 | 09/01/2026 | nan | nan | 0 | TK_NotStart | 1208363553 | 365 | 1208363553_365
MRPP2-SUP.23090 | TT_Task | EMU - DEL Primary Suspension delivery - 5th Fleet (6 trainsets) | 15/10/2025 | 06/04/2026 | nan | nan | 0 | TK_NotStart | 1208363553 | 367 | 1208363553_367
MRPP2-SUP.12760 | TT_Task | EMU - PO Secondary Suspension - 5th Fleet (6 trainsets) | 03/10/2024 | 30/10/2024 | nan | nan | 0 | TK_NotStart | 1208363553 | 364 | 1208363553_364
MRPP2-SUP.16890 | TT_Task | EMU - Production Secondary Suspension - 5th Fleet (6 trainsets) | 31/10/2024 | 09/01/2026 | nan | nan | 0 | TK_NotStart | 1208363553 | 365 | 1208363553_365
MRPP2-SUP.23100 | TT_Task | EMU - DEL Secondary Suspension delivery - 5th Fleet (6 trainsets) | 15/10/2025 | 06/04/2026 | nan | nan | 0 | TK_NotStart | 1208363553 | 367 | 1208363553_367
MRPP2-SUP.12740 | TT_Task | EMU - PO CVS - 5th Fleet (6 trainsets) | 03/10/2024 | 30/10/2024 | nan | nan | 0 | TK_NotStart | 1208363553 | 369 | 1208363553_369
MRPP2-SUP.16870 | TT_Task | EMU - Production CVS - 5th Fleet (6 trainsets) | 31/10/2024 | 09/12/2025 | nan | nan | 0 | TK_NotStart | 1208363553 | 370 | 1208363553_370
MRPP2-SUP.22940 | TT_Task | EMU - DEL CVS delivery - 5th Fleet (6 trainsets) | 01/10/2025 | 23/03/2026 | nan | nan | 0 | TK_NotStart | 1208363553 | 371 | 1208363553_371
MRPP2-SUP.12730 | TT_Task | EMU - PO Coupler - 5th Fleet (6 trainsets) | 03/10/2024 | 30/10/2024 | nan | nan | 0 | TK_NotStart | 1208363553 | 372 | 1208363553_372
MRPP2-SUP.16860 | TT_Task | EMU - Production Coupler - 5th Fleet (6 trainsets) | 31/10/2024 | 09/01/2026 | nan | nan | 0 | TK_NotStart | 1208363553 | 372 | 1208363553_372
MRPP2-SUP.22920 | TT_Task | EMU - DEL Coupler delivery - 5th Fleet (6 trainsets) | 15/10/2025 | 06/04/2026 | nan | nan | 0 | TK_NotStart | 1208363553 | 373 | 1208363553_373
MRPP2-SUP.12780 | TT_Task | EMU - PO (Purchase Order)-Gangway - 5th Fleet (6 trainsets) | 03/10/2024 | 30/10/2024 | nan | nan | 0 | TK_NotStart | 1208363553 | 374 | 1208363553_374
MRPP2-SUP.16910 | TT_Task | EMU - Production ( Component process time)-Gangway - 5th Fleet (6 trainsets) | 31/10/2024 | 09/01/2026 | nan | nan | 0 | TK_NotStart | 1208363553 | 375 | 1208363553_375
MRPP2-SUP.23020 | TT_Task | EMU - DEL Component-Gangway Delivery - 5th Fleet (6 trainsets) | 15/10/2025 | 06/04/2026 | nan | nan | 0 | TK_NotStart | 1208363553 | 376 | 1208363553_376
MRPP2-SUP.12790 | TT_Task | EMU - PO Pipes - 5th Fleet (6 trainsets) | 03/10/2024 | 30/10/2024 | nan | nan | 0 | TK_NotStart | 1208363553 | 377 | 1208363553_377
MRPP2-SUP.16920 | TT_Task | EMU - Production Pipes - 5th Fleet (6 trainsets) | 31/10/2024 | 09/01/2026 | nan | nan | 0 | TK_NotStart | 1208363553 | 377 | 1208363553_377
MRPP2-SUP.23060 | TT_Task | EMU - DEL Pipes delivery - 5th Fleet (6 trainsets) | 15/10/2025 | 06/04/2026 | nan | nan | 0 | TK_NotStart | 1208363553 | 378 | 1208363553_378
MRPP2-SUP.12800 | TT_Task | EMU - PO Cables - 5th Fleet (6 trainsets) | 03/10/2024 | 30/10/2024 | nan | nan | 0 | TK_NotStart | 1208363553 | 381 | 1208363553_381
MRPP2-SUP.16930 | TT_Task | EMU - Production Cables - 5th Fleet (6 trainsets) | 31/10/2024 | 09/01/2026 | nan | nan | 0 | TK_NotStart | 1208363553 | 381 | 1208363553_381
MRPP2-SUP.23070 | TT_Task | EMU - DEL Cables delivery - 5th Fleet (6 trainsets) | 15/10/2025 | 06/04/2026 | nan | nan | 0 | TK_NotStart | 1208363553 | 382 | 1208363553_382
MRPP2-SUP.12810 | TT_Task | EMU - PO Cable trays - 5th Fleet (6 trainsets) | 03/10/2024 | 30/10/2024 | nan | nan | 0 | TK_NotStart | 1208363553 | 383 | 1208363553_383
MRPP2-SUP.16940 | TT_Task | EMU - Production Cable trays - 5th Fleet (6 trainsets) | 31/10/2024 | 09/01/2026 | nan | nan | 0 | TK_NotStart | 1208363553 | 383 | 1208363553_383
MRPP2-SUP.23080 | TT_Task | EMU - DEL Cable trays delivery - 5th Fleet (6 trainsets) | 15/10/2025 | 06/04/2026 | nan | nan | 0 | TK_NotStart | 1208363553 | 383 | 1208363553_383
MRPP2-SUP.12820 | TT_Task | EMU - PO Floor covering - 5th Fleet (6 trainsets) | 31/10/2024 | 27/11/2024 | nan | nan | 0 | TK_NotStart | 1208363553 | 384 | 1208363553_384
MRPP2-SUP.16950 | TT_Task | EMU - Production Floor covering - 5th Fleet (6 trainsets) | 28/11/2024 | 09/02/2026 | nan | nan | 0 | TK_NotStart | 1208363553 | 385 | 1208363553_385
MRPP2-SUP.23150 | TT_Task | EMU - DEL Floor covering delivery - 5th Fleet (6 trainsets) | 12/11/2025 | 07/05/2026 | nan | nan | 0 | TK_NotStart | 1208363553 | 386 | 1208363553_386
MRPP2-SUP.12920 | TT_Task | EMU - PO Pantograph - 5th Fleet (6 trainsets) | 31/10/2024 | 27/11/2024 | nan | nan | 0 | TK_NotStart | 1208363553 | 387 | 1208363553_387
MRPP2-SUP.17050 | TT_Task | EMU - Production Pantograph - 5th Fleet (6 trainsets) | 28/11/2024 | 09/02/2026 | nan | nan | 0 | TK_NotStart | 1208363553 | 387 | 1208363553_387
MRPP2-SUP.23250 | TT_Task | EMU - DEL Pantograph delivery - 5th Fleet (6 trainsets) | 15/10/2025 | 06/04/2026 | nan | nan | 0 | TK_NotStart | 1208363553 | 388 | 1208363553_388
MRPP2-SUP.12900 | TT_Task | EMU - PO Wind screen - 5th Fleet (6 trainsets) | 31/10/2024 | 27/11/2024 | nan | nan | 0 | TK_NotStart | 1208363553 | 389 | 1208363553_389
MRPP2-SUP.17030 | TT_Task | EMU - Production Wind screen - 5th Fleet (6 trainsets) | 28/11/2024 | 09/02/2026 | nan | nan | 0 | TK_NotStart | 1208363553 | 389 | 1208363553_389
MRPP2-SUP.23230 | TT_Task | EMU - DEL Wind screen delivery - 5th Fleet (6 trainsets) | 15/10/2025 | 06/04/2026 | nan | nan | 0 | TK_NotStart | 1208363553 | 390 | 1208363553_390
MRPP2-SUP.12910 | TT_Task | EMU - PO Front mask - 5th Fleet (6 trainsets) | 31/10/2024 | 27/11/2024 | nan | nan | 0 | TK_NotStart | 1208363553 | 391 | 1208363553_391
MRPP2-SUP.17040 | TT_Task | EMU - Production Front mask - 5th Fleet (6 trainsets) | 28/11/2024 | 09/02/2026 | nan | nan | 0 | TK_NotStart | 1208363553 | 391 | 1208363553_391
MRPP2-SUP.23240 | TT_Task | EMU - DEL Front mask delivery - 5th Fleet (6 trainsets) | 15/10/2025 | 06/04/2026 | nan | nan | 0 | TK_NotStart | 1208363553 | 392 | 1208363553_392
MRPP2-SUP.13010 | TT_Task | EMU - PO Relays - 5th Fleet (6 trainsets) | 31/10/2024 | 27/11/2024 | nan | nan | 0 | TK_NotStart | 1208363553 | 393 | 1208363553_393
MRPP2-SUP.17140 | TT_Task | EMU - Production Relays - 5th Fleet (6 trainsets) | 28/11/2024 | 09/02/2026 | nan | nan | 0 | TK_NotStart | 1208363553 | 393 | 1208363553_393
MRPP2-SUP.23380 | TT_Task | EMU - DEL Relays delivery - 5th Fleet (6 trainsets) | 15/10/2025 | 06/04/2026 | nan | nan | 0 | TK_NotStart | 1208363553 | 394 | 1208363553_394
MRPP2-SUP.13020 | TT_Task | EMU - PO Cabinets - 5th Fleet (6 trainsets) | 31/10/2024 | 27/11/2024 | nan | nan | 0 | TK_NotStart | 1208363553 | 395 | 1208363553_395
MRPP2-SUP.17150 | TT_Task | EMU - Production Cabinets - 5th Fleet (6 trainsets) | 28/11/2024 | 09/02/2026 | nan | nan | 0 | TK_NotStart | 1208363553 | 395 | 1208363553_395
MRPP2-SUP.23390 | TT_Task | EMU - DEL Cabinets delivery - 5th Fleet (6 trainsets) | 15/10/2025 | 06/04/2026 | nan | nan | 0 | TK_NotStart | 1208363553 | 396 | 1208363553_396
MRPP2-SUP.12990 | TT_Task | EMU - PO Elec comp - 5th Fleet (6 trainsets) | 31/10/2024 | 27/11/2024 | nan | nan | 0 | TK_NotStart | 1208363553 | 397 | 1208363553_397
MRPP2-SUP.17120 | TT_Task | EMU - Production Elec comp - 5th Fleet (6 trainsets) | 28/11/2024 | 09/02/2026 | nan | nan | 0 | TK_NotStart | 1208363553 | 398 | 1208363553_398
MRPP2-SUP.23360 | TT_Task | EMU - DEL Elec comp delivery - 5th Fleet (6 trainsets) | 15/10/2025 | 06/04/2026 | nan | nan | 0 | TK_NotStart | 1208363553 | 399 | 1208363553_399
MRPP2-SUP.13030 | TT_Task | EMU - PO LV box - 5th Fleet (6 trainsets) | 31/10/2024 | 27/11/2024 | nan | nan | 0 | TK_NotStart | 1208363553 | 400 | 1208363553_400
MRPP2-SUP.17160 | TT_Task | EMU - Production LV box - 5th Fleet (6 trainsets) | 28/11/2024 | 09/02/2026 | nan | nan | 0 | TK_NotStart | 1208363553 | 400 | 1208363553_400
MRPP2-SUP.23400 | TT_Task | EMU - DEL LV box delivery - 5th Fleet (6 trainsets) | 15/10/2025 | 06/04/2026 | nan | nan | 0 | TK_NotStart | 1208363553 | 401 | 1208363553_401
MRPP2-SUP.13040 | TT_Task | EMU - PO Battery ; battery box - 5th Fleet (6 trainsets) | 31/10/2024 | 27/11/2024 | nan | nan | 0 | TK_NotStart | 1208363553 | 402 | 1208363553_402
MRPP2-SUP.17170 | TT_Task | EMU - Production Battery ; battery box - 5th Fleet (6 trainsets) | 28/11/2024 | 09/02/2026 | nan | nan | 0 | TK_NotStart | 1208363553 | 402 | 1208363553_402
MRPP2-SUP.23410 | TT_Task | EMU - DEL Battery ; battery box delivery - 5th Fleet (6 trainsets) | 15/10/2025 | 06/04/2026 | nan | nan | 0 | TK_NotStart | 1208363553 | 402 | 1208363553_402
MRPP2-SUP.13000 | TT_Task | EMU - PO Crash box - 5th Fleet (6 trainsets) | 31/10/2024 | 27/11/2024 | nan | nan | 0 | TK_NotStart | 1208363553 | 403 | 1208363553_403
MRPP2-SUP.17130 | TT_Task | EMU - Production Crash box - 5th Fleet (6 trainsets) | 28/11/2024 | 09/02/2026 | nan | nan | 0 | TK_NotStart | 1208363553 | 403 | 1208363553_403
MRPP2-SUP.23370 | TT_Task | EMU - DEL Crash box delivery - 5th Fleet (6 trainsets) | 15/10/2025 | 06/04/2026 | nan | nan | 0 | TK_NotStart | 1208363553 | 404 | 1208363553_404
MRPP2-SUP.13080 | TT_Task | EMU - PO Interior and lighting - 5th Fleet (6 trainsets) | 31/10/2024 | 27/11/2024 | nan | nan | 0 | TK_NotStart | 1208363553 | 406 | 1208363553_406
MRPP2-SUP.17210 | TT_Task | EMU - Production Interior and lighting - 5th Fleet (6 trainsets) | 28/11/2024 | 09/01/2026 | nan | nan | 0 | TK_NotStart | 1208363553 | 407 | 1208363553_407
MRPP2-SUP.23500 | TT_Task | EMU - DEL Interior and lighting delivery - 5th Fleet (6 trainsets) | 29/10/2025 | 22/04/2026 | nan | nan | 0 | TK_NotStart | 1208363553 | 407 | 1208363553_407
MRPP2-SUP.13070 | TT_Task | EMU - PO Hand rails - 5th Fleet (6 trainsets) | 31/10/2024 | 27/11/2024 | nan | nan | 0 | TK_NotStart | 1208363553 | 408 | 1208363553_408
MRPP2-SUP.17200 | TT_Task | EMU - Production Hand rails - 5th Fleet (6 trainsets) | 28/11/2024 | 09/02/2026 | nan | nan | 0 | TK_NotStart | 1208363553 | 408 | 1208363553_408
MRPP2-SUP.23490 | TT_Task | EMU - DEL Hand rails delivery - 5th Fleet (6 trainsets) | 15/10/2025 | 06/04/2026 | nan | nan | 0 | TK_NotStart | 1208363553 | 409 | 1208363553_409
MRPP2-SUP.13060 | TT_Task | EMU - PO Grabpoles and grab handles - 5th Fleet (6 trainsets) | 31/10/2024 | 27/11/2024 | nan | nan | 0 | TK_NotStart | 1208363553 | 410 | 1208363553_410
MRPP2-SUP.17190 | TT_Task | EMU - Production Grabpoles and grab handles - 5th Fleet (6 trainsets) | 28/11/2024 | 09/02/2026 | nan | nan | 0 | TK_NotStart | 1208363553 | 410 | 1208363553_410
MRPP2-SUP.23480 | TT_Task | EMU - DEL Grabpoles and grab handles delivery - 5th Fleet (6 trainsets) | 15/10/2025 | 06/04/2026 | nan | nan | 0 | TK_NotStart | 1208363553 | 410 | 1208363553_410
MRPP2-SUP.13090 | TT_Task | EMU - PO Cab garnishing - 5th Fleet (6 trainsets) | 31/10/2024 | 27/11/2024 | nan | nan | 0 | TK_NotStart | 1208363553 | 411 | 1208363553_411
MRPP2-SUP.17220 | TT_Task | EMU - Production Cab garnishing - 5th Fleet (6 trainsets) | 28/11/2024 | 09/02/2026 | nan | nan | 0 | TK_NotStart | 1208363553 | 411 | 1208363553_411
MRPP2-SUP.23510 | TT_Task | EMU - DEL Cab garnishing delivery - 5th Fleet (6 trainsets) | 15/10/2025 | 06/04/2026 | nan | nan | 0 | TK_NotStart | 1208363553 | 411 | 1208363553_411
MRPP2-SUP.13140 | TT_Task | EMU - PO Seats - 5th Fleet (6 trainsets) | 31/10/2024 | 27/11/2024 | nan | nan | 0 | TK_NotStart | 1208363553 | 412 | 1208363553_412
MRPP2-SUP.17270 | TT_Task | EMU - Production Seats - 5th Fleet (6 trainsets) | 28/11/2024 | 09/02/2026 | nan | nan | 0 | TK_NotStart | 1208363553 | 412 | 1208363553_412
MRPP2-SUP.23520 | TT_Task | EMU - DEL Seats delivery - 5th Fleet (6 trainsets) | 15/10/2025 | 06/04/2026 | nan | nan | 0 | TK_NotStart | 1208363553 | 413 | 1208363553_413
MRPP2-SUP.13190 | TT_Task | EMU - PO PACIS - 5th Fleet (6 trainsets) | 31/10/2024 | 27/11/2024 | nan | nan | 0 | TK_NotStart | 1208363553 | 414 | 1208363553_414
MRPP2-SUP.17320 | TT_Task | EMU - Production PACIS - 5th Fleet (6 trainsets) | 28/11/2024 | 09/01/2026 | nan | nan | 0 | TK_NotStart | 1208363553 | 414 | 1208363553_414
MRPP2-SUP.23540 | TT_Task | EMU - DEL PACIS delivery - 5th Fleet (6 trainsets) | 29/10/2025 | 22/04/2026 | nan | nan | 0 | TK_NotStart | 1208363553 | 415 | 1208363553_415
MRPP2-SUP.13180 | TT_Task | EMU - PO MCP - 5th Fleet (6 trainsets) | 31/10/2024 | 27/11/2024 | nan | nan | 0 | TK_NotStart | 1208363553 | 417 | 1208363553_417
MRPP2-SUP.17310 | TT_Task | EMU - Production MCP - 5th Fleet (6 trainsets) | 28/11/2024 | 09/02/2026 | nan | nan | 0 | TK_NotStart | 1208363553 | 418 | 1208363553_418
MRPP2-SUP.23530 | TT_Task | EMU - DEL MCP delivery - 5th Fleet (6 trainsets) | 15/10/2025 | 06/04/2026 | nan | nan | 0 | TK_NotStart | 1208363553 | 419 | 1208363553_419
MRPP2-SUP.13220 | TT_Task | EMU - PO TCMS equipment - 5th Fleet (6 trainsets) | 31/10/2024 | 27/11/2024 | nan | nan | 0 | TK_NotStart | 1208363553 | 421 | 1208363553_421
MRPP2-SUP.17350 | TT_Task | EMU - Production TCMS equipment - 5th Fleet (6 trainsets) | 28/11/2024 | 09/01/2026 | nan | nan | 0 | TK_NotStart | 1208363553 | 422 | 1208363553_422
MRPP2-SUP.23590 | TT_Task | EMU - DEL TCMS equipment delivery - 5th Fleet (6 trainsets) | 29/10/2025 | 22/04/2026 | nan | nan | 0 | TK_NotStart | 1208363553 | 422 | 1208363553_422
MRPP2-SUP.12670 | TT_Task | EMU - PO HVAC - 5th Fleet (6 trainsets) | 03/10/2024 | 30/10/2024 | nan | nan | 0 | TK_NotStart | 1208363553 | 348 | 1208363553_348
MRPP2-SUP.16800 | TT_Task | EMU - Production HVAC - 5th Fleet (6 trainsets) | 31/10/2024 | 09/01/2026 | nan | nan | 0 | TK_NotStart | 1208363553 | 348 | 1208363553_348
MRPP2-SUP.22980 | TT_Task | EMU - DEL HVAC delivery - 5th Fleet (6 trainsets) | 15/10/2025 | 06/04/2026 | nan | nan | 0 | TK_NotStart | 1208363553 | 349 | 1208363553_349
MRPP2-SUP.12720 | TT_Task | EMU - PO Windows - 5th Fleet (6 trainsets) | 03/10/2024 | 30/10/2024 | nan | nan | 0 | TK_NotStart | 1208363553 | 351 | 1208363553_351
MRPP2-SUP.16850 | TT_Task | EMU - Production Windows - 5th Fleet (6 trainsets) | 31/10/2024 | 09/01/2026 | nan | nan | 0 | TK_NotStart | 1208363553 | 352 | 1208363553_352
MRPP2-SUP.23050 | TT_Task | EMU - DEL Windows delivery - 5th Fleet (6 trainsets) | 15/10/2025 | 06/04/2026 | nan | nan | 0 | TK_NotStart | 1208363553 | 353 | 1208363553_353
MRPP2-SUP.12770 | TT_Task | EMU - PO Passenger doors - 5th Fleet (6 trainsets) | 03/10/2024 | 30/10/2024 | nan | nan | 0 | TK_NotStart | 1208363553 | 354 | 1208363553_354
MRPP2-SUP.16900 | TT_Task | EMU - Production Passenger doors - 5th Fleet (6 trainsets) | 31/10/2024 | 09/01/2026 | nan | nan | 0 | TK_NotStart | 1208363553 | 354 | 1208363553_354
MRPP2-SUP.23140 | TT_Task | EMU - DEL Passenger doors delivery - 5th Fleet (6 trainsets) | 15/10/2025 | 06/04/2026 | nan | nan | 0 | TK_NotStart | 1208363553 | 355 | 1208363553_355
MRPP2-SUP.13110 | TT_Task | EMU - PO Bogie Frame - 6th Fleet (6 trainsets) | 03/07/2025 | 30/07/2025 | nan | nan | 0 | TK_NotStart | 1208363553 | 337 | 1208363553_337
MRPP2-SUP.17240 | TT_Task | EMU - Production Bogie Frame - 6th Fleet (6 trainsets) | 31/07/2025 | 07/10/2026 | nan | nan | 0 | TK_NotStart | 1208363553 | 337 | 1208363553_337
MRPP2-SUP.23560 | TT_Task | EMU - DEL Bogie Frame delivery - 6th Fleet (6 trainsets) | 03/06/2026 | 18/11/2026 | nan | nan | 0 | TK_NotStart | 1208363553 | 339 | 1208363553_339
MRPP2-SUP.13130 | TT_Task | EMU - PO Bogie Assy - 6th Fleet (6 trainsets) | 03/07/2025 | 30/07/2025 | nan | nan | 0 | TK_NotStart | 1208363553 | 423 | 1208363553_423
MRPP2-SUP.17260 | TT_Task | EMU - Production Bogie Assy - 6th Fleet (6 trainsets) | 31/07/2025 | 07/10/2026 | nan | nan | 0 | TK_NotStart | 1208363553 | 423 | 1208363553_423
MRPP2-SUP.23580 | TT_Task | EMU - DEL Bogie Assy delivery - 6th Fleet (6 trainsets) | 03/06/2026 | 18/11/2026 | nan | nan | 0 | TK_NotStart | 1208363553 | 339 | 1208363553_339
MRPP2-SUP.13120 | TT_Task | EMU - PO Axle box ; bearing - 6th Fleet (6 trainsets) | 03/07/2025 | 30/07/2025 | nan | nan | 0 | TK_NotStart | 1208363553 | 341 | 1208363553_341
MRPP2-SUP.17250 | TT_Task | EMU - Production Axle box ; bearing - 6th Fleet (6 trainsets) | 31/07/2025 | 07/10/2026 | nan | nan | 0 | TK_NotStart | 1208363553 | 341 | 1208363553_341
MRPP2-SUP.23570 | TT_Task | EMU - DEL Axle box ; bearing delivery - 6th Fleet (6 trainsets) | 15/07/2026 | 04/01/2027 | nan | nan | 0 | TK_NotStart | 1208363553 | 341 | 1208363553_341
MRPP2-SUP.13100 | TT_Task | EMU - PO Wheels - 6th Fleet (6 trainsets) | 03/07/2025 | 30/07/2025 | nan | nan | 0 | TK_NotStart | 1208363553 | 344 | 1208363553_344
MRPP2-SUP.17230 | TT_Task | EMU - Production Wheels - 6th Fleet (6 trainsets) | 31/07/2025 | 07/10/2026 | nan | nan | 0 | TK_NotStart | 1208363553 | 344 | 1208363553_344
MRPP2-SUP.23550 | TT_Task | EMU - DEL Wheels delivery - 6th Fleet (6 trainsets) | 15/07/2026 | 04/01/2027 | nan | nan | 0 | TK_NotStart | 1208363553 | 346 | 1208363553_346
MRPP2-SUP.13160 | TT_Task | EMU - PO Axles - 6th Fleet (6 trainsets) | 03/07/2025 | 30/07/2025 | nan | nan | 0 | TK_NotStart | 1208363553 | 356 | 1208363553_356
MRPP2-SUP.17290 | TT_Task | EMU - Production Axles - 6th Fleet (6 trainsets) | 31/07/2025 | 07/10/2026 | nan | nan | 0 | TK_NotStart | 1208363553 | 356 | 1208363553_356
MRPP2-SUP.23610 | TT_Task | EMU - DEL Axles delivery - 6th Fleet (6 trainsets) | 15/07/2026 | 04/01/2027 | nan | nan | 0 | TK_NotStart | 1208363553 | 357 | 1208363553_357
MRPP2-SUP.13170 | TT_Task | EMU - PO Brakes - 6th Fleet (6 trainsets) | 03/07/2025 | 30/07/2025 | nan | nan | 0 | TK_NotStart | 1208363553 | 358 | 1208363553_358
MRPP2-SUP.17300 | TT_Task | EMU - Production Brakes - 6th Fleet (6 trainsets) | 31/07/2025 | 07/10/2026 | nan | nan | 0 | TK_NotStart | 1208363553 | 358 | 1208363553_358
MRPP2-SUP.23620 | TT_Task | EMU - DEL Brakes delivery - 6th Fleet (6 trainsets) | 15/07/2026 | 04/01/2027 | nan | nan | 0 | TK_NotStart | 1208363553 | 359 | 1208363553_359
MRPP2-SUP.13210 | TT_Task | EMU - PO Traction converter - 6th Fleet (6 trainsets) | 03/07/2025 | 30/07/2025 | nan | nan | 0 | TK_NotStart | 1208363553 | 360 | 1208363553_360
MRPP2-SUP.17340 | TT_Task | EMU - Production Traction converter - 6th Fleet (6 trainsets) | 31/07/2025 | 07/10/2026 | nan | nan | 0 | TK_NotStart | 1208363553 | 360 | 1208363553_360
MRPP2-SUP.23640 | TT_Task | EMU - DEL Traction converter delivery - 6th Fleet (6 trainsets) | 15/07/2026 | 04/01/2027 | nan | nan | 0 | TK_NotStart | 1208363553 | 361 | 1208363553_361
MRPP2-SUP.13240 | TT_Task | EMU - PO Traction motor - 6th Fleet (6 trainsets) | 03/07/2025 | 30/07/2025 | nan | nan | 0 | TK_NotStart | 1208363553 | 362 | 1208363553_362
MRPP2-SUP.17370 | TT_Task | EMU - Production Traction motor - 6th Fleet (6 trainsets) | 31/07/2025 | 07/10/2026 | nan | nan | 0 | TK_NotStart | 1208363553 | 362 | 1208363553_362
MRPP2-SUP.23680 | TT_Task | EMU - DEL Traction motor delivery - 6th Fleet (6 trainsets) | 15/07/2026 | 04/01/2027 | nan | nan | 0 | TK_NotStart | 1208363553 | 363 | 1208363553_363
MRPP2-SUP.13260 | TT_Task | EMU - PO Primary Suspension - 6th Fleet (6 trainsets) | 03/07/2025 | 30/07/2025 | nan | nan | 0 | TK_NotStart | 1208363553 | 364 | 1208363553_364
MRPP2-SUP.17390 | TT_Task | EMU - Production Primary Suspension - 6th Fleet (6 trainsets) | 31/07/2025 | 07/10/2026 | nan | nan | 0 | TK_NotStart | 1208363553 | 365 | 1208363553_365
MRPP2-SUP.23710 | TT_Task | EMU - DEL Primary Suspension delivery - 6th Fleet (6 trainsets) | 15/07/2026 | 04/01/2027 | nan | nan | 0 | TK_NotStart | 1208363553 | 367 | 1208363553_367
MRPP2-SUP.13270 | TT_Task | EMU - PO Secondary Suspension - 6th Fleet (6 trainsets) | 03/07/2025 | 30/07/2025 | nan | nan | 0 | TK_NotStart | 1208363553 | 364 | 1208363553_364
MRPP2-SUP.17400 | TT_Task | EMU - Production Secondary Suspension - 6th Fleet (6 trainsets) | 31/07/2025 | 07/10/2026 | nan | nan | 0 | TK_NotStart | 1208363553 | 365 | 1208363553_365
MRPP2-SUP.23720 | TT_Task | EMU - DEL Secondary Suspension delivery - 6th Fleet (6 trainsets) | 15/07/2026 | 04/01/2027 | nan | nan | 0 | TK_NotStart | 1208363553 | 367 | 1208363553_367
MRPP2-SUP.13250 | TT_Task | EMU - PO CVS - 6th Fleet (6 trainsets) | 03/07/2025 | 30/07/2025 | nan | nan | 0 | TK_NotStart | 1208363553 | 369 | 1208363553_369
MRPP2-SUP.17380 | TT_Task | EMU - Production CVS - 6th Fleet (6 trainsets) | 31/07/2025 | 07/10/2026 | nan | nan | 0 | TK_NotStart | 1208363553 | 370 | 1208363553_370
MRPP2-SUP.23650 | TT_Task | EMU - DEL CVS delivery - 6th Fleet (6 trainsets) | 15/07/2026 | 04/01/2027 | nan | nan | 0 | TK_NotStart | 1208363553 | 371 | 1208363553_371
MRPP2-SUP.13280 | TT_Task | EMU - PO Coupler - 6th Fleet (6 trainsets) | 03/07/2025 | 30/07/2025 | nan | nan | 0 | TK_NotStart | 1208363553 | 372 | 1208363553_372
MRPP2-SUP.17410 | TT_Task | EMU - Production Coupler - 6th Fleet (6 trainsets) | 31/07/2025 | 07/10/2026 | nan | nan | 0 | TK_NotStart | 1208363553 | 372 | 1208363553_372
MRPP2-SUP.23670 | TT_Task | EMU - DEL Coupler delivery - 6th Fleet (6 trainsets) | 15/07/2026 | 04/01/2027 | nan | nan | 0 | TK_NotStart | 1208363553 | 373 | 1208363553_373
MRPP2-SUP.13290 | TT_Task | EMU - PO (Purchase Order)-Gangway - 6th Fleet (6 trainsets) | 03/07/2025 | 30/07/2025 | nan | nan | 0 | TK_NotStart | 1208363553 | 374 | 1208363553_374
MRPP2-SUP.17420 | TT_Task | EMU - Production ( Component process time)-Gangway - 6th Fleet (6 trainsets) | 31/07/2025 | 07/10/2026 | nan | nan | 0 | TK_NotStart | 1208363553 | 375 | 1208363553_375
MRPP2-SUP.23700 | TT_Task | EMU - DEL Component Delivery-Gangway - 6th Fleet (6 trainsets) | 15/07/2026 | 04/01/2027 | nan | nan | 0 | TK_NotStart | 1208363553 | 376 | 1208363553_376
MRPP2-SUP.13300 | TT_Task | EMU - PO Pipes - 6th Fleet (6 trainsets) | 03/07/2025 | 30/07/2025 | nan | nan | 0 | TK_NotStart | 1208363553 | 377 | 1208363553_377
MRPP2-SUP.17430 | TT_Task | EMU - Production Pipes - 6th Fleet (6 trainsets) | 31/07/2025 | 07/10/2026 | nan | nan | 0 | TK_NotStart | 1208363553 | 377 | 1208363553_377
MRPP2-SUP.23760 | TT_Task | EMU - DEL Pipes delivery - 6th Fleet (6 trainsets) | 15/07/2026 | 04/01/2027 | nan | nan | 0 | TK_NotStart | 1208363553 | 378 | 1208363553_378
MRPP2-SUP.13310 | TT_Task | EMU - PO Cables - 6th Fleet (6 trainsets) | 03/07/2025 | 30/07/2025 | nan | nan | 0 | TK_NotStart | 1208363553 | 381 | 1208363553_381
MRPP2-SUP.17440 | TT_Task | EMU - Production Cables - 6th Fleet (6 trainsets) | 31/07/2025 | 07/10/2026 | nan | nan | 0 | TK_NotStart | 1208363553 | 381 | 1208363553_381
MRPP2-SUP.23770 | TT_Task | EMU - DEL Cables delivery - 6th Fleet (6 trainsets) | 15/07/2026 | 04/01/2027 | nan | nan | 0 | TK_NotStart | 1208363553 | 382 | 1208363553_382
MRPP2-SUP.13320 | TT_Task | EMU - PO Cable trays - 6th Fleet (6 trainsets) | 03/07/2025 | 30/07/2025 | nan | nan | 0 | TK_NotStart | 1208363553 | 383 | 1208363553_383
MRPP2-SUP.17450 | TT_Task | EMU - Production Cable trays - 6th Fleet (6 trainsets) | 31/07/2025 | 07/10/2026 | nan | nan | 0 | TK_NotStart | 1208363553 | 383 | 1208363553_383
MRPP2-SUP.23780 | TT_Task | EMU - DEL Cable trays delivery - 6th Fleet (6 trainsets) | 15/07/2026 | 04/01/2027 | nan | nan | 0 | TK_NotStart | 1208363553 | 383 | 1208363553_383
MRPP2-SUP.13330 | TT_Task | EMU - PO Floor covering - 6th Fleet (6 trainsets) | 03/07/2025 | 30/07/2025 | nan | nan | 0 | TK_NotStart | 1208363553 | 384 | 1208363553_384
MRPP2-SUP.17460 | TT_Task | EMU - Production Floor covering - 6th Fleet (6 trainsets) | 31/07/2025 | 07/10/2026 | nan | nan | 0 | TK_NotStart | 1208363553 | 385 | 1208363553_385
MRPP2-SUP.23790 | TT_Task | EMU - DEL Floor covering delivery - 6th Fleet (6 trainsets) | 15/07/2026 | 04/01/2027 | nan | nan | 0 | TK_NotStart | 1208363553 | 386 | 1208363553_386
MRPP2-SUP.13420 | TT_Task | EMU - PO Pantograph - 6th Fleet (6 trainsets) | 03/07/2025 | 30/07/2025 | nan | nan | 0 | TK_NotStart | 1208363553 | 387 | 1208363553_387
MRPP2-SUP.17550 | TT_Task | EMU - Production Pantograph - 6th Fleet (6 trainsets) | 31/07/2025 | 07/10/2026 | nan | nan | 0 | TK_NotStart | 1208363553 | 387 | 1208363553_387
MRPP2-SUP.23890 | TT_Task | EMU - DEL Pantograph delivery - 6th Fleet (6 trainsets) | 15/07/2026 | 04/01/2027 | nan | nan | 0 | TK_NotStart | 1208363553 | 388 | 1208363553_388
MRPP2-SUP.13410 | TT_Task | EMU - PO Wind screen - 6th Fleet (6 trainsets) | 03/07/2025 | 30/07/2025 | nan | nan | 0 | TK_NotStart | 1208363553 | 389 | 1208363553_389
MRPP2-SUP.17540 | TT_Task | EMU - Production Wind screen - 6th Fleet (6 trainsets) | 31/07/2025 | 07/10/2026 | nan | nan | 0 | TK_NotStart | 1208363553 | 389 | 1208363553_389
MRPP2-SUP.23880 | TT_Task | EMU - DEL Wind screen delivery - 6th Fleet (6 trainsets) | 15/07/2026 | 04/01/2027 | nan | nan | 0 | TK_NotStart | 1208363553 | 390 | 1208363553_390
MRPP2-SUP.13500 | TT_Task | EMU - PO Front mask - 6th Fleet (6 trainsets) | 03/07/2025 | 30/07/2025 | nan | nan | 0 | TK_NotStart | 1208363553 | 391 | 1208363553_391
MRPP2-SUP.17630 | TT_Task | EMU - Production Front mask - 6th Fleet (6 trainsets) | 31/07/2025 | 07/10/2026 | nan | nan | 0 | TK_NotStart | 1208363553 | 391 | 1208363553_391
MRPP2-SUP.24000 | TT_Task | EMU - DEL Front mask delivery - 6th Fleet (6 trainsets) | 15/07/2026 | 04/01/2027 | nan | nan | 0 | TK_NotStart | 1208363553 | 392 | 1208363553_392
MRPP2-SUP.13530 | TT_Task | EMU - PO Relays - 6th Fleet (6 trainsets) | 03/07/2025 | 30/07/2025 | nan | nan | 0 | TK_NotStart | 1208363553 | 393 | 1208363553_393
MRPP2-SUP.17660 | TT_Task | EMU - Production Relays - 6th Fleet (6 trainsets) | 31/07/2025 | 07/10/2026 | nan | nan | 0 | TK_NotStart | 1208363553 | 393 | 1208363553_393
MRPP2-SUP.24080 | TT_Task | EMU - DEL Relays delivery - 6th Fleet (6 trainsets) | 15/07/2026 | 04/01/2027 | nan | nan | 0 | TK_NotStart | 1208363553 | 394 | 1208363553_394
MRPP2-SUP.13540 | TT_Task | EMU - PO Cabinets - 6th Fleet (6 trainsets) | 03/07/2025 | 30/07/2025 | nan | nan | 0 | TK_NotStart | 1208363553 | 395 | 1208363553_395
MRPP2-SUP.17670 | TT_Task | EMU - Production Cabinets - 6th Fleet (6 trainsets) | 31/07/2025 | 07/10/2026 | nan | nan | 0 | TK_NotStart | 1208363553 | 395 | 1208363553_395
MRPP2-SUP.24090 | TT_Task | EMU - DEL Cabinets delivery - 6th Fleet (6 trainsets) | 15/07/2026 | 04/01/2027 | nan | nan | 0 | TK_NotStart | 1208363553 | 396 | 1208363553_396
MRPP2-SUP.13510 | TT_Task | EMU - PO Elec comp - 6th Fleet (6 trainsets) | 03/07/2025 | 30/07/2025 | nan | nan | 0 | TK_NotStart | 1208363553 | 397 | 1208363553_397
MRPP2-SUP.17640 | TT_Task | EMU - Production Elec comp - 6th Fleet (6 trainsets) | 31/07/2025 | 07/10/2026 | nan | nan | 0 | TK_NotStart | 1208363553 | 398 | 1208363553_398
MRPP2-SUP.24060 | TT_Task | EMU - DEL Elec comp delivery - 6th Fleet (6 trainsets) | 15/07/2026 | 04/01/2027 | nan | nan | 0 | TK_NotStart | 1208363553 | 399 | 1208363553_399
MRPP2-SUP.13550 | TT_Task | EMU - PO LV box - 6th Fleet (6 trainsets) | 03/07/2025 | 30/07/2025 | nan | nan | 0 | TK_NotStart | 1208363553 | 400 | 1208363553_400
MRPP2-SUP.17680 | TT_Task | EMU - Production LV box - 6th Fleet (6 trainsets) | 31/07/2025 | 07/10/2026 | nan | nan | 0 | TK_NotStart | 1208363553 | 400 | 1208363553_400
MRPP2-SUP.24100 | TT_Task | EMU - DEL LV box delivery - 6th Fleet (6 trainsets) | 15/07/2026 | 04/01/2027 | nan | nan | 0 | TK_NotStart | 1208363553 | 401 | 1208363553_401
MRPP2-SUP.13560 | TT_Task | EMU - PO Battery ; battery box - 6th Fleet (6 trainsets) | 03/07/2025 | 30/07/2025 | nan | nan | 0 | TK_NotStart | 1208363553 | 402 | 1208363553_402
MRPP2-SUP.17690 | TT_Task | EMU - Production Battery ; battery box - 6th Fleet (6 trainsets) | 31/07/2025 | 07/10/2026 | nan | nan | 0 | TK_NotStart | 1208363553 | 402 | 1208363553_402
MRPP2-SUP.24110 | TT_Task | EMU - DEL Battery ; battery box delivery - 6th Fleet (6 trainsets) | 15/07/2026 | 04/01/2027 | nan | nan | 0 | TK_NotStart | 1208363553 | 402 | 1208363553_402
MRPP2-SUP.13520 | TT_Task | EMU - PO Crash box - 6th Fleet (6 trainsets) | 03/07/2025 | 30/07/2025 | nan | nan | 0 | TK_NotStart | 1208363553 | 403 | 1208363553_403
MRPP2-SUP.17650 | TT_Task | EMU - Production Crash box - 6th Fleet (6 trainsets) | 31/07/2025 | 07/10/2026 | nan | nan | 0 | TK_NotStart | 1208363553 | 403 | 1208363553_403
MRPP2-SUP.24070 | TT_Task | EMU - DEL Crash box delivery - 6th Fleet (6 trainsets) | 15/07/2026 | 04/01/2027 | nan | nan | 0 | TK_NotStart | 1208363553 | 404 | 1208363553_404
MRPP2-SUP.13620 | TT_Task | EMU - PO Interior and lighting - 6th Fleet (6 trainsets) | 03/07/2025 | 30/07/2025 | nan | nan | 0 | TK_NotStart | 1208363553 | 406 | 1208363553_406
MRPP2-SUP.17750 | TT_Task | EMU - Production Interior and lighting - 6th Fleet (6 trainsets) | 31/07/2025 | 18/11/2026 | nan | nan | 0 | TK_NotStart | 1208363553 | 407 | 1208363553_407
MRPP2-SUP.24170 | TT_Task | EMU - DEL Interior and lighting delivery - 6th Fleet (6 trainsets) | 15/07/2026 | 04/01/2027 | nan | nan | 0 | TK_NotStart | 1208363553 | 407 | 1208363553_407
MRPP2-SUP.13590 | TT_Task | EMU - PO Hand rails - 6th Fleet (6 trainsets) | 03/07/2025 | 30/07/2025 | nan | nan | 0 | TK_NotStart | 1208363553 | 408 | 1208363553_408
MRPP2-SUP.17720 | TT_Task | EMU - Production Hand rails - 6th Fleet (6 trainsets) | 31/07/2025 | 07/10/2026 | nan | nan | 0 | TK_NotStart | 1208363553 | 408 | 1208363553_408
MRPP2-SUP.24140 | TT_Task | EMU - DEL Hand rails delivery - 6th Fleet (6 trainsets) | 15/07/2026 | 04/01/2027 | nan | nan | 0 | TK_NotStart | 1208363553 | 409 | 1208363553_409
MRPP2-SUP.13580 | TT_Task | EMU - PO Grabpoles and grab handles - 6th Fleet (6 trainsets) | 03/07/2025 | 30/07/2025 | nan | nan | 0 | TK_NotStart | 1208363553 | 410 | 1208363553_410
MRPP2-SUP.17710 | TT_Task | EMU - Production Grabpoles and grab handles - 6th Fleet (6 trainsets) | 31/07/2025 | 07/10/2026 | nan | nan | 0 | TK_NotStart | 1208363553 | 410 | 1208363553_410
MRPP2-SUP.24130 | TT_Task | EMU - DEL Grabpoles and grab handles delivery - 6th Fleet (6 trainsets) | 15/07/2026 | 04/01/2027 | nan | nan | 0 | TK_NotStart | 1208363553 | 410 | 1208363553_410
MRPP2-SUP.13630 | TT_Task | EMU - PO Cab garnishing - 6th Fleet (6 trainsets) | 03/07/2025 | 30/07/2025 | nan | nan | 0 | TK_NotStart | 1208363553 | 411 | 1208363553_411
MRPP2-SUP.17760 | TT_Task | EMU - Production Cab garnishing - 6th Fleet (6 trainsets) | 31/07/2025 | 07/10/2026 | nan | nan | 0 | TK_NotStart | 1208363553 | 411 | 1208363553_411
MRPP2-SUP.24180 | TT_Task | EMU - DEL Cab garnishing delivery - 6th Fleet (6 trainsets) | 15/07/2026 | 04/01/2027 | nan | nan | 0 | TK_NotStart | 1208363553 | 411 | 1208363553_411
MRPP2-SUP.13610 | TT_Task | EMU - PO Seats - 6th Fleet (6 trainsets) | 03/07/2025 | 30/07/2025 | nan | nan | 0 | TK_NotStart | 1208363553 | 412 | 1208363553_412
MRPP2-SUP.17740 | TT_Task | EMU - Production Seats - 6th Fleet (6 trainsets) | 31/07/2025 | 07/10/2026 | nan | nan | 0 | TK_NotStart | 1208363553 | 412 | 1208363553_412
MRPP2-SUP.24160 | TT_Task | EMU - DEL Seats delivery - 6th Fleet (6 trainsets) | 15/07/2026 | 04/01/2027 | nan | nan | 0 | TK_NotStart | 1208363553 | 413 | 1208363553_413
MRPP2-SUP.13600 | TT_Task | EMU - PO PACIS - 6th Fleet (6 trainsets) | 03/07/2025 | 30/07/2025 | nan | nan | 0 | TK_NotStart | 1208363553 | 414 | 1208363553_414
MRPP2-SUP.17730 | TT_Task | EMU - Production PACIS - 6th Fleet (6 trainsets) | 31/07/2025 | 07/10/2026 | nan | nan | 0 | TK_NotStart | 1208363553 | 414 | 1208363553_414
MRPP2-SUP.24150 | TT_Task | EMU - DEL PACIS delivery - 6th Fleet (6 trainsets) | 15/07/2026 | 04/01/2027 | nan | nan | 0 | TK_NotStart | 1208363553 | 415 | 1208363553_415
MRPP2-SUP.13570 | TT_Task | EMU - PO MCP - 6th Fleet (6 trainsets) | 03/07/2025 | 30/07/2025 | nan | nan | 0 | TK_NotStart | 1208363553 | 417 | 1208363553_417
MRPP2-SUP.17700 | TT_Task | EMU - Production MCP - 6th Fleet (6 trainsets) | 31/07/2025 | 07/10/2026 | nan | nan | 0 | TK_NotStart | 1208363553 | 418 | 1208363553_418
MRPP2-SUP.24120 | TT_Task | EMU - DEL MCP delivery - 6th Fleet (6 trainsets) | 15/07/2026 | 04/01/2027 | nan | nan | 0 | TK_NotStart | 1208363553 | 419 | 1208363553_419
MRPP2-SUP.13640 | TT_Task | EMU - PO TCMS equipment - 6th Fleet (6 trainsets) | 03/07/2025 | 30/07/2025 | nan | nan | 0 | TK_NotStart | 1208363553 | 421 | 1208363553_421
MRPP2-SUP.17770 | TT_Task | EMU - Production TCMS equipment - 6th Fleet (6 trainsets) | 31/07/2025 | 08/09/2026 | nan | nan | 0 | TK_NotStart | 1208363553 | 422 | 1208363553_422
MRPP2-SUP.24190 | TT_Task | EMU - DEL TCMS equipment delivery - 6th Fleet (6 trainsets) | 15/07/2026 | 04/01/2027 | nan | nan | 0 | TK_NotStart | 1208363553 | 422 | 1208363553_422
MRPP2-SUP.13150 | TT_Task | EMU - PO HVAC - 6th Fleet (6 trainsets) | 31/07/2025 | 27/08/2025 | nan | nan | 0 | TK_NotStart | 1208363553 | 348 | 1208363553_348
MRPP2-SUP.17280 | TT_Task | EMU - Production HVAC - 6th Fleet (6 trainsets) | 28/08/2025 | 04/11/2026 | nan | nan | 0 | TK_NotStart | 1208363553 | 348 | 1208363553_348
MRPP2-SUP.23600 | TT_Task | EMU - DEL HVAC delivery - 6th Fleet (6 trainsets) | 12/08/2026 | 02/02/2027 | nan | nan | 0 | TK_NotStart | 1208363553 | 349 | 1208363553_349
MRPP2-SUP.13200 | TT_Task | EMU - PO Windows - 6th Fleet (6 trainsets) | 28/08/2025 | 24/09/2025 | nan | nan | 0 | TK_NotStart | 1208363553 | 351 | 1208363553_351
MRPP2-SUP.17330 | TT_Task | EMU - Production Windows - 6th Fleet (6 trainsets) | 25/09/2025 | 02/12/2026 | nan | nan | 0 | TK_NotStart | 1208363553 | 352 | 1208363553_352
MRPP2-SUP.23630 | TT_Task | EMU - DEL Windows delivery - 6th Fleet (6 trainsets) | 09/09/2026 | 02/03/2027 | nan | nan | 0 | TK_NotStart | 1208363553 | 353 | 1208363553_353
MRPP2-SUP.13230 | TT_Task | EMU - PO Passenger doors - 6th Fleet (6 trainsets) | 28/08/2025 | 24/09/2025 | nan | nan | 0 | TK_NotStart | 1208363553 | 354 | 1208363553_354
MRPP2-SUP.17360 | TT_Task | EMU - Production Passenger doors - 6th Fleet (6 trainsets) | 25/09/2025 | 02/12/2026 | nan | nan | 0 | TK_NotStart | 1208363553 | 354 | 1208363553_354
MRPP2-SUP.23660 | TT_Task | EMU - DEL Passenger doors delivery - 6th Fleet (6 trainsets) | 09/09/2026 | 02/03/2027 | nan | nan | 0 | TK_NotStart | 1208363553 | 355 | 1208363553_355
MRPP2-SUP.13660 | TT_Task | EMU - PO Bogie Frame - 7th Fleet (6 trainsets) | 12/06/2026 | 09/07/2026 | nan | nan | 0 | TK_NotStart | 1208363553 | 337 | 1208363553_337
MRPP2-SUP.17790 | TT_Task | EMU - Production Bogie Frame - 7th Fleet (6 trainsets) | 10/07/2026 | 21/07/2027 | nan | nan | 0 | TK_NotStart | 1208363553 | 337 | 1208363553_337
MRPP2-SUP.24250 | TT_Task | EMU - DEL Bogie Frame delivery - 7th Fleet (6 trainsets) | 12/05/2027 | 28/10/2027 | nan | nan | 0 | TK_NotStart | 1208363553 | 339 | 1208363553_339
MRPP2-SUP.13680 | TT_Task | EMU - PO Bogie Assy - 7th Fleet (6 trainsets) | 12/06/2026 | 09/07/2026 | nan | nan | 0 | TK_NotStart | 1208363553 | 423 | 1208363553_423
MRPP2-SUP.17810 | TT_Task | EMU - Production Bogie Assy - 7th Fleet (6 trainsets) | 10/07/2026 | 21/07/2027 | nan | nan | 0 | TK_NotStart | 1208363553 | 423 | 1208363553_423
MRPP2-SUP.24270 | TT_Task | EMU - DEL Bogie Assy delivery - 7th Fleet (6 trainsets) | 12/05/2027 | 28/10/2027 | nan | nan | 0 | TK_NotStart | 1208363553 | 339 | 1208363553_339
MRPP2-SUP.13670 | TT_Task | EMU - PO Axle box ; bearing - 7th Fleet (6 trainsets) | 12/06/2026 | 09/07/2026 | nan | nan | 0 | TK_NotStart | 1208363553 | 341 | 1208363553_341
MRPP2-SUP.17800 | TT_Task | EMU - Production Axle box ; bearing - 7th Fleet (6 trainsets) | 10/07/2026 | 15/09/2027 | nan | nan | 0 | TK_NotStart | 1208363553 | 341 | 1208363553_341
MRPP2-SUP.24260 | TT_Task | EMU - DEL Axle box ; bearing delivery - 7th Fleet (6 trainsets) | 24/06/2027 | 09/12/2027 | nan | nan | 0 | TK_NotStart | 1208363553 | 341 | 1208363553_341
MRPP2-SUP.13650 | TT_Task | EMU - PO Wheels - 7th Fleet (6 trainsets) | 12/06/2026 | 09/07/2026 | nan | nan | 0 | TK_NotStart | 1208363553 | 344 | 1208363553_344
MRPP2-SUP.17780 | TT_Task | EMU - Production Wheels - 7th Fleet (6 trainsets) | 10/07/2026 | 15/09/2027 | nan | nan | 0 | TK_NotStart | 1208363553 | 344 | 1208363553_344
MRPP2-SUP.24240 | TT_Task | EMU - DEL Wheels delivery - 7th Fleet (6 trainsets) | 24/06/2027 | 09/12/2027 | nan | nan | 0 | TK_NotStart | 1208363553 | 346 | 1208363553_346
MRPP2-SUP.13700 | TT_Task | EMU - PO Axles - 7th Fleet (6 trainsets) | 10/07/2026 | 06/08/2026 | nan | nan | 0 | TK_NotStart | 1208363553 | 356 | 1208363553_356
MRPP2-SUP.17830 | TT_Task | EMU - Production Axles - 7th Fleet (6 trainsets) | 07/08/2026 | 14/10/2027 | nan | nan | 0 | TK_NotStart | 1208363553 | 356 | 1208363553_356
MRPP2-SUP.24330 | TT_Task | EMU - DEL Axles delivery - 7th Fleet (6 trainsets) | 22/07/2027 | 07/01/2028 | nan | nan | 0 | TK_NotStart | 1208363553 | 357 | 1208363553_357
MRPP2-SUP.13710 | TT_Task | EMU - PO Brakes - 7th Fleet (6 trainsets) | 10/07/2026 | 06/08/2026 | nan | nan | 0 | TK_NotStart | 1208363553 | 358 | 1208363553_358
MRPP2-SUP.17840 | TT_Task | EMU - Production Brakes - 7th Fleet (6 trainsets) | 07/08/2026 | 14/10/2027 | nan | nan | 0 | TK_NotStart | 1208363553 | 358 | 1208363553_358
MRPP2-SUP.24340 | TT_Task | EMU - DEL Brakes delivery - 7th Fleet (6 trainsets) | 22/07/2027 | 07/01/2028 | nan | nan | 0 | TK_NotStart | 1208363553 | 359 | 1208363553_359
MRPP2-SUP.13730 | TT_Task | EMU - PO Traction converter - 7th Fleet (6 trainsets) | 07/08/2026 | 03/09/2026 | nan | nan | 0 | TK_NotStart | 1208363553 | 360 | 1208363553_360
MRPP2-SUP.17860 | TT_Task | EMU - Production Traction converter - 7th Fleet (6 trainsets) | 04/09/2026 | 15/09/2027 | nan | nan | 0 | TK_NotStart | 1208363553 | 360 | 1208363553_360
MRPP2-SUP.24390 | TT_Task | EMU - DEL Traction converter delivery - 7th Fleet (6 trainsets) | 19/08/2027 | 07/02/2028 | nan | nan | 0 | TK_NotStart | 1208363553 | 361 | 1208363553_361
MRPP2-SUP.13750 | TT_Task | EMU - PO Traction motor - 7th Fleet (6 trainsets) | 04/09/2026 | 02/10/2026 | nan | nan | 0 | TK_NotStart | 1208363553 | 362 | 1208363553_362
MRPP2-SUP.17880 | TT_Task | EMU - Production Traction motor - 7th Fleet (6 trainsets) | 05/10/2026 | 14/10/2027 | nan | nan | 0 | TK_NotStart | 1208363553 | 362 | 1208363553_362
MRPP2-SUP.24530 | TT_Task | EMU - DEL Traction motor delivery - 7th Fleet (6 trainsets) | 16/09/2027 | 06/03/2028 | nan | nan | 0 | TK_NotStart | 1208363553 | 363 | 1208363553_363
MRPP2-SUP.13760 | TT_Task | EMU - PO Primary Suspension - 7th Fleet (6 trainsets) | 04/09/2026 | 02/10/2026 | nan | nan | 0 | TK_NotStart | 1208363553 | 364 | 1208363553_364
MRPP2-SUP.17890 | TT_Task | EMU - Production Primary Suspension - 7th Fleet (6 trainsets) | 05/10/2026 | 09/12/2027 | nan | nan | 0 | TK_NotStart | 1208363553 | 365 | 1208363553_365
MRPP2-SUP.24540 | TT_Task | EMU - DEL Primary Suspension delivery - 7th Fleet (6 trainsets) | 16/09/2027 | 06/03/2028 | nan | nan | 0 | TK_NotStart | 1208363553 | 367 | 1208363553_367
MRPP2-SUP.13770 | TT_Task | EMU - PO Secondary Suspension - 7th Fleet (6 trainsets) | 04/09/2026 | 02/10/2026 | nan | nan | 0 | TK_NotStart | 1208363553 | 364 | 1208363553_364
MRPP2-SUP.17900 | TT_Task | EMU - Production Secondary Suspension - 7th Fleet (6 trainsets) | 05/10/2026 | 09/12/2027 | nan | nan | 0 | TK_NotStart | 1208363553 | 365 | 1208363553_365
MRPP2-SUP.24550 | TT_Task | EMU - DEL Secondary Suspension delivery - 7th Fleet (6 trainsets) | 16/09/2027 | 06/03/2028 | nan | nan | 0 | TK_NotStart | 1208363553 | 367 | 1208363553_367
MRPP2-SUP.13840 | TT_Task | EMU - PO CVS - 7th Fleet (6 trainsets) | 04/09/2026 | 02/10/2026 | nan | nan | 0 | TK_NotStart | 1208363553 | 369 | 1208363553_369
MRPP2-SUP.17970 | TT_Task | EMU - Production CVS - 7th Fleet (6 trainsets) | 05/10/2026 | 09/12/2027 | nan | nan | 0 | TK_NotStart | 1208363553 | 370 | 1208363553_370
MRPP2-SUP.24400 | TT_Task | EMU - DEL CVS delivery - 7th Fleet (6 trainsets) | 16/09/2027 | 06/03/2028 | nan | nan | 0 | TK_NotStart | 1208363553 | 371 | 1208363553_371
MRPP2-SUP.13920 | TT_Task | EMU - PO Coupler - 7th Fleet (6 trainsets) | 04/09/2026 | 02/10/2026 | nan | nan | 0 | TK_NotStart | 1208363553 | 372 | 1208363553_372
MRPP2-SUP.18050 | TT_Task | EMU - Production Coupler - 7th Fleet (6 trainsets) | 05/10/2026 | 09/12/2027 | nan | nan | 0 | TK_NotStart | 1208363553 | 372 | 1208363553_372
MRPP2-SUP.24520 | TT_Task | EMU - DEL Coupler delivery - 7th Fleet (6 trainsets) | 16/09/2027 | 06/03/2028 | nan | nan | 0 | TK_NotStart | 1208363553 | 373 | 1208363553_373
MRPP2-SUP.13930 | TT_Task | EMU - PO (Purchase Order)-Gangway - 7th Fleet (6 trainsets) | 04/09/2026 | 02/10/2026 | nan | nan | 0 | TK_NotStart | 1208363553 | 374 | 1208363553_374
MRPP2-SUP.18060 | TT_Task | EMU - Production ( Component process time)-Gangway - 7th Fleet (6 trainsets) | 05/10/2026 | 09/12/2027 | nan | nan | 0 | TK_NotStart | 1208363553 | 375 | 1208363553_375
MRPP2-SUP.24610 | TT_Task | EMU - DEL Component-Gangway Delivery - 7th Fleet (6 trainsets) | 16/09/2027 | 06/03/2028 | nan | nan | 0 | TK_NotStart | 1208363553 | 376 | 1208363553_376
MRPP2-SUP.13940 | TT_Task | EMU - PO Pipes - 7th Fleet (6 trainsets) | 04/09/2026 | 02/10/2026 | nan | nan | 0 | TK_NotStart | 1208363553 | 377 | 1208363553_377
MRPP2-SUP.18070 | TT_Task | EMU - Production Pipes - 7th Fleet (6 trainsets) | 05/10/2026 | 09/12/2027 | nan | nan | 0 | TK_NotStart | 1208363553 | 377 | 1208363553_377
MRPP2-SUP.24620 | TT_Task | EMU - DEL Pipes delivery - 7th Fleet (6 trainsets) | 16/09/2027 | 06/03/2028 | nan | nan | 0 | TK_NotStart | 1208363553 | 378 | 1208363553_378
MRPP2-SUP.13950 | TT_Task | EMU - PO Cables - 7th Fleet (6 trainsets) | 04/09/2026 | 02/10/2026 | nan | nan | 0 | TK_NotStart | 1208363553 | 381 | 1208363553_381
MRPP2-SUP.18080 | TT_Task | EMU - Production Cables - 7th Fleet (6 trainsets) | 05/10/2026 | 09/12/2027 | nan | nan | 0 | TK_NotStart | 1208363553 | 381 | 1208363553_381
MRPP2-SUP.24630 | TT_Task | EMU - DEL Cables delivery - 7th Fleet (6 trainsets) | 16/09/2027 | 06/03/2028 | nan | nan | 0 | TK_NotStart | 1208363553 | 382 | 1208363553_382
MRPP2-SUP.13960 | TT_Task | EMU - PO Cable trays - 7th Fleet (6 trainsets) | 04/09/2026 | 02/10/2026 | nan | nan | 0 | TK_NotStart | 1208363553 | 383 | 1208363553_383
MRPP2-SUP.18090 | TT_Task | EMU - Production Cable trays - 7th Fleet (6 trainsets) | 05/10/2026 | 09/12/2027 | nan | nan | 0 | TK_NotStart | 1208363553 | 383 | 1208363553_383
MRPP2-SUP.24640 | TT_Task | EMU - DEL Cable trays delivery - 7th Fleet (6 trainsets) | 16/09/2027 | 06/03/2028 | nan | nan | 0 | TK_NotStart | 1208363553 | 383 | 1208363553_383
MRPP2-SUP.13970 | TT_Task | EMU - PO Floor covering - 7th Fleet (6 trainsets) | 04/09/2026 | 02/10/2026 | nan | nan | 0 | TK_NotStart | 1208363553 | 384 | 1208363553_384
MRPP2-SUP.18100 | TT_Task | EMU - Production Floor covering - 7th Fleet (6 trainsets) | 05/10/2026 | 09/12/2027 | nan | nan | 0 | TK_NotStart | 1208363553 | 385 | 1208363553_385
MRPP2-SUP.24650 | TT_Task | EMU - DEL Floor covering delivery - 7th Fleet (6 trainsets) | 16/09/2027 | 06/03/2028 | nan | nan | 0 | TK_NotStart | 1208363553 | 386 | 1208363553_386
MRPP2-SUP.14010 | TT_Task | EMU - PO Pantograph - 7th Fleet (6 trainsets) | 04/09/2026 | 02/10/2026 | nan | nan | 0 | TK_NotStart | 1208363553 | 387 | 1208363553_387
MRPP2-SUP.18140 | TT_Task | EMU - Production Pantograph - 7th Fleet (6 trainsets) | 05/10/2026 | 09/12/2027 | nan | nan | 0 | TK_NotStart | 1208363553 | 387 | 1208363553_387
MRPP2-SUP.24690 | TT_Task | EMU - DEL Pantograph delivery - 7th Fleet (6 trainsets) | 16/09/2027 | 06/03/2028 | nan | nan | 0 | TK_NotStart | 1208363553 | 388 | 1208363553_388
MRPP2-SUP.13990 | TT_Task | EMU - PO Wind screen - 7th Fleet (6 trainsets) | 04/09/2026 | 02/10/2026 | nan | nan | 0 | TK_NotStart | 1208363553 | 389 | 1208363553_389
MRPP2-SUP.18120 | TT_Task | EMU - Production Wind screen - 7th Fleet (6 trainsets) | 05/10/2026 | 09/12/2027 | nan | nan | 0 | TK_NotStart | 1208363553 | 389 | 1208363553_389
MRPP2-SUP.24670 | TT_Task | EMU - DEL Wind screen delivery - 7th Fleet (6 trainsets) | 16/09/2027 | 06/03/2028 | nan | nan | 0 | TK_NotStart | 1208363553 | 390 | 1208363553_390
MRPP2-SUP.14000 | TT_Task | EMU - PO Front mask - 7th Fleet (6 trainsets) | 04/09/2026 | 02/10/2026 | nan | nan | 0 | TK_NotStart | 1208363553 | 391 | 1208363553_391
MRPP2-SUP.18130 | TT_Task | EMU - Production Front mask - 7th Fleet (6 trainsets) | 05/10/2026 | 09/12/2027 | nan | nan | 0 | TK_NotStart | 1208363553 | 391 | 1208363553_391
MRPP2-SUP.24680 | TT_Task | EMU - DEL Front mask delivery - 7th Fleet (6 trainsets) | 16/09/2027 | 06/03/2028 | nan | nan | 0 | TK_NotStart | 1208363553 | 392 | 1208363553_392
MRPP2-SUP.14040 | TT_Task | EMU - PO Relays - 7th Fleet (6 trainsets) | 04/09/2026 | 02/10/2026 | nan | nan | 0 | TK_NotStart | 1208363553 | 393 | 1208363553_393
MRPP2-SUP.18170 | TT_Task | EMU - Production Relays - 7th Fleet (6 trainsets) | 05/10/2026 | 09/12/2027 | nan | nan | 0 | TK_NotStart | 1208363553 | 393 | 1208363553_393
MRPP2-SUP.24720 | TT_Task | EMU - DEL Relays delivery - 7th Fleet (6 trainsets) | 16/09/2027 | 06/03/2028 | nan | nan | 0 | TK_NotStart | 1208363553 | 394 | 1208363553_394
MRPP2-SUP.14050 | TT_Task | EMU - PO Cabinets - 7th Fleet (6 trainsets) | 04/09/2026 | 02/10/2026 | nan | nan | 0 | TK_NotStart | 1208363553 | 395 | 1208363553_395
MRPP2-SUP.18180 | TT_Task | EMU - Production Cabinets - 7th Fleet (6 trainsets) | 05/10/2026 | 09/12/2027 | nan | nan | 0 | TK_NotStart | 1208363553 | 395 | 1208363553_395
MRPP2-SUP.24730 | TT_Task | EMU - DEL Cabinets delivery - 7th Fleet (6 trainsets) | 16/09/2027 | 06/03/2028 | nan | nan | 0 | TK_NotStart | 1208363553 | 396 | 1208363553_396
MRPP2-SUP.14020 | TT_Task | EMU - PO Elec comp - 7th Fleet (6 trainsets) | 04/09/2026 | 02/10/2026 | nan | nan | 0 | TK_NotStart | 1208363553 | 397 | 1208363553_397
MRPP2-SUP.18150 | TT_Task | EMU - Production Elec comp - 7th Fleet (6 trainsets) | 05/10/2026 | 09/12/2027 | nan | nan | 0 | TK_NotStart | 1208363553 | 398 | 1208363553_398
MRPP2-SUP.24700 | TT_Task | EMU - DEL Elec comp delivery - 7th Fleet (6 trainsets) | 16/09/2027 | 06/03/2028 | nan | nan | 0 | TK_NotStart | 1208363553 | 399 | 1208363553_399
MRPP2-SUP.14060 | TT_Task | EMU - PO LV box - 7th Fleet (6 trainsets) | 04/09/2026 | 02/10/2026 | nan | nan | 0 | TK_NotStart | 1208363553 | 400 | 1208363553_400
MRPP2-SUP.18190 | TT_Task | EMU - Production LV box - 7th Fleet (6 trainsets) | 05/10/2026 | 09/12/2027 | nan | nan | 0 | TK_NotStart | 1208363553 | 400 | 1208363553_400
MRPP2-SUP.24740 | TT_Task | EMU - DEL LV box delivery - 7th Fleet (6 trainsets) | 16/09/2027 | 06/03/2028 | nan | nan | 0 | TK_NotStart | 1208363553 | 401 | 1208363553_401
MRPP2-SUP.14070 | TT_Task | EMU - PO Battery ; battery box - 7th Fleet (6 trainsets) | 04/09/2026 | 02/10/2026 | nan | nan | 0 | TK_NotStart | 1208363553 | 402 | 1208363553_402
MRPP2-SUP.18200 | TT_Task | EMU - Production Battery ; battery box - 7th Fleet (6 trainsets) | 05/10/2026 | 09/12/2027 | nan | nan | 0 | TK_NotStart | 1208363553 | 402 | 1208363553_402
MRPP2-SUP.24750 | TT_Task | EMU - DEL Battery ; battery box delivery - 7th Fleet (6 trainsets) | 16/09/2027 | 06/03/2028 | nan | nan | 0 | TK_NotStart | 1208363553 | 402 | 1208363553_402
MRPP2-SUP.14030 | TT_Task | EMU - PO Crash box - 7th Fleet (6 trainsets) | 04/09/2026 | 02/10/2026 | nan | nan | 0 | TK_NotStart | 1208363553 | 403 | 1208363553_403
MRPP2-SUP.18160 | TT_Task | EMU - Production Crash box - 7th Fleet (6 trainsets) | 05/10/2026 | 09/12/2027 | nan | nan | 0 | TK_NotStart | 1208363553 | 403 | 1208363553_403
MRPP2-SUP.24710 | TT_Task | EMU - DEL Crash box delivery - 7th Fleet (6 trainsets) | 16/09/2027 | 06/03/2028 | nan | nan | 0 | TK_NotStart | 1208363553 | 404 | 1208363553_404
MRPP2-SUP.14140 | TT_Task | EMU - PO Interior and lighting - 7th Fleet (6 trainsets) | 04/09/2026 | 02/10/2026 | nan | nan | 0 | TK_NotStart | 1208363553 | 406 | 1208363553_406
MRPP2-SUP.18270 | TT_Task | EMU - Production Interior and lighting - 7th Fleet (6 trainsets) | 05/10/2026 | 09/12/2027 | nan | nan | 0 | TK_NotStart | 1208363553 | 407 | 1208363553_407
MRPP2-SUP.24820 | TT_Task | EMU - DEL Interior and lighting delivery - 7th Fleet (6 trainsets) | 16/09/2027 | 06/03/2028 | nan | nan | 0 | TK_NotStart | 1208363553 | 407 | 1208363553_407
MRPP2-SUP.14100 | TT_Task | EMU - PO Hand rails - 7th Fleet (6 trainsets) | 04/09/2026 | 02/10/2026 | nan | nan | 0 | TK_NotStart | 1208363553 | 408 | 1208363553_408
MRPP2-SUP.18230 | TT_Task | EMU - Production Hand rails - 7th Fleet (6 trainsets) | 05/10/2026 | 09/12/2027 | nan | nan | 0 | TK_NotStart | 1208363553 | 408 | 1208363553_408
MRPP2-SUP.24780 | TT_Task | EMU - DEL Hand rails delivery - 7th Fleet (6 trainsets) | 16/09/2027 | 06/03/2028 | nan | nan | 0 | TK_NotStart | 1208363553 | 409 | 1208363553_409
MRPP2-SUP.14090 | TT_Task | EMU - PO Grabpoles and grab handles - 7th Fleet (6 trainsets) | 04/09/2026 | 02/10/2026 | nan | nan | 0 | TK_NotStart | 1208363553 | 410 | 1208363553_410
MRPP2-SUP.18220 | TT_Task | EMU - Production Grabpoles and grab handles - 7th Fleet (6 trainsets) | 05/10/2026 | 09/12/2027 | nan | nan | 0 | TK_NotStart | 1208363553 | 410 | 1208363553_410
MRPP2-SUP.24770 | TT_Task | EMU - DEL Grabpoles and grab handles delivery - 7th Fleet (6 trainsets) | 16/09/2027 | 06/03/2028 | nan | nan | 0 | TK_NotStart | 1208363553 | 410 | 1208363553_410
MRPP2-SUP.14150 | TT_Task | EMU - PO Cab garnishing - 7th Fleet (6 trainsets) | 04/09/2026 | 02/10/2026 | nan | nan | 0 | TK_NotStart | 1208363553 | 411 | 1208363553_411
MRPP2-SUP.18280 | TT_Task | EMU - Production Cab garnishing - 7th Fleet (6 trainsets) | 05/10/2026 | 09/12/2027 | nan | nan | 0 | TK_NotStart | 1208363553 | 411 | 1208363553_411
MRPP2-SUP.24830 | TT_Task | EMU - DEL Cab garnishing delivery - 7th Fleet (6 trainsets) | 16/09/2027 | 06/03/2028 | nan | nan | 0 | TK_NotStart | 1208363553 | 411 | 1208363553_411
MRPP2-SUP.14130 | TT_Task | EMU - PO Seats - 7th Fleet (6 trainsets) | 04/09/2026 | 02/10/2026 | nan | nan | 0 | TK_NotStart | 1208363553 | 412 | 1208363553_412
MRPP2-SUP.18260 | TT_Task | EMU - Production Seats - 7th Fleet (6 trainsets) | 05/10/2026 | 09/12/2027 | nan | nan | 0 | TK_NotStart | 1208363553 | 412 | 1208363553_412
MRPP2-SUP.24810 | TT_Task | EMU - DEL Seats delivery - 7th Fleet (6 trainsets) | 16/09/2027 | 06/03/2028 | nan | nan | 0 | TK_NotStart | 1208363553 | 413 | 1208363553_413
MRPP2-SUP.14110 | TT_Task | EMU - PO PACIS - 7th Fleet (6 trainsets) | 04/09/2026 | 02/10/2026 | nan | nan | 0 | TK_NotStart | 1208363553 | 414 | 1208363553_414
MRPP2-SUP.18240 | TT_Task | EMU - Production PACIS - 7th Fleet (6 trainsets) | 05/10/2026 | 09/12/2027 | nan | nan | 0 | TK_NotStart | 1208363553 | 414 | 1208363553_414
MRPP2-SUP.24790 | TT_Task | EMU - DEL PACIS delivery - 7th Fleet (6 trainsets) | 16/09/2027 | 06/03/2028 | nan | nan | 0 | TK_NotStart | 1208363553 | 415 | 1208363553_415
MRPP2-SUP.14080 | TT_Task | EMU - PO MCP - 7th Fleet (6 trainsets) | 04/09/2026 | 02/10/2026 | nan | nan | 0 | TK_NotStart | 1208363553 | 417 | 1208363553_417
MRPP2-SUP.18210 | TT_Task | EMU - Production MCP - 7th Fleet (6 trainsets) | 05/10/2026 | 09/12/2027 | nan | nan | 0 | TK_NotStart | 1208363553 | 418 | 1208363553_418
MRPP2-SUP.24760 | TT_Task | EMU - DEL MCP delivery - 7th Fleet (6 trainsets) | 16/09/2027 | 06/03/2028 | nan | nan | 0 | TK_NotStart | 1208363553 | 419 | 1208363553_419
MRPP2-SUP.14120 | TT_Task | EMU - PO TCMS equipment - 7th Fleet (6 trainsets) | 04/09/2026 | 02/10/2026 | nan | nan | 0 | TK_NotStart | 1208363553 | 421 | 1208363553_421
MRPP2-SUP.18250 | TT_Task | EMU - Production TCMS equipment - 7th Fleet (6 trainsets) | 05/10/2026 | 09/12/2027 | nan | nan | 0 | TK_NotStart | 1208363553 | 422 | 1208363553_422
MRPP2-SUP.24800 | TT_Task | EMU - DEL TCMS equipment delivery - 7th Fleet (6 trainsets) | 16/09/2027 | 06/03/2028 | nan | nan | 0 | TK_NotStart | 1208363553 | 422 | 1208363553_422
MRPP2-SUP.13690 | TT_Task | EMU - PO HVAC - 7th Fleet (6 trainsets) | 12/06/2026 | 09/07/2026 | nan | nan | 0 | TK_NotStart | 1208363553 | 348 | 1208363553_348
MRPP2-SUP.17820 | TT_Task | EMU - Production HVAC - 7th Fleet (6 trainsets) | 10/07/2026 | 15/09/2027 | nan | nan | 0 | TK_NotStart | 1208363553 | 348 | 1208363553_348
MRPP2-SUP.24320 | TT_Task | EMU - DEL HVAC delivery - 7th Fleet (6 trainsets) | 10/06/2027 | 25/11/2027 | nan | nan | 0 | TK_NotStart | 1208363553 | 349 | 1208363553_349
MRPP2-SUP.13720 | TT_Task | EMU - PO Windows - 7th Fleet (6 trainsets) | 12/06/2026 | 09/07/2026 | nan | nan | 0 | TK_NotStart | 1208363553 | 351 | 1208363553_351
MRPP2-SUP.17850 | TT_Task | EMU - Production Windows - 7th Fleet (6 trainsets) | 10/07/2026 | 15/09/2027 | nan | nan | 0 | TK_NotStart | 1208363553 | 352 | 1208363553_352
MRPP2-SUP.24380 | TT_Task | EMU - DEL Windows delivery - 7th Fleet (6 trainsets) | 10/06/2027 | 25/11/2027 | nan | nan | 0 | TK_NotStart | 1208363553 | 353 | 1208363553_353
MRPP2-SUP.13740 | TT_Task | EMU - PO Passenger doors - 7th Fleet (6 trainsets) | 12/06/2026 | 09/07/2026 | nan | nan | 0 | TK_NotStart | 1208363553 | 354 | 1208363553_354
MRPP2-SUP.17870 | TT_Task | EMU - Production Passenger doors - 7th Fleet (6 trainsets) | 10/07/2026 | 15/09/2027 | nan | nan | 0 | TK_NotStart | 1208363553 | 354 | 1208363553_354
MRPP2-SUP.24510 | TT_Task | EMU - DEL Passenger doors delivery - 7th Fleet (6 trainsets) | 10/06/2027 | 25/11/2027 | nan | nan | 0 | TK_NotStart | 1208363553 | 355 | 1208363553_355
MRPP2-EAT.00010 | TT_Task | EMU - Train 01 - Carbodyshell Manufacture 1st CBS | 22/02/2021 | 04/05/2021 | 22/02/2021 | 04/05/2021 | 0 | TK_Complete | 1208363553 | 424 | 1208363553_424
MRPP2-EAT.00030 | TT_Task | EMU - Train 01 - Transport 1st CBS transport to Perth | 05/05/2021 | 08/07/2021 | 05/05/2021 | 08/07/2021 | 0 | TK_Complete | 1208363553 | 425 | 1208363553_425
MRPP2-EAT.00040 | TT_Task | EMU - Train 01 - Carbodyshell Manufacture 2nd CBS | 05/05/2021 | 01/06/2021 | 05/05/2021 | 01/06/2021 | 0 | TK_Complete | 1208363553 | 424 | 1208363553_424
MRPP2-EAT.00050 | TT_Task | EMU - Train 01 - Transport 2nd CBS transport to Perth | 02/06/2021 | 05/08/2021 | 02/06/2021 | 05/08/2021 | 0 | TK_Complete | 1208363553 | 425 | 1208363553_425
MRPP2-EAT.00060 | TT_Task | EMU - Train 01 - Carbodyshell Manufacture 3rd, 4th ; 5th CBS | 02/06/2021 | 22/09/2021 | 02/06/2021 | 22/09/2021 | 0 | TK_Complete | 1208363553 | 424 | 1208363553_424
MRPP2-EAT.00070 | TT_Task | EMU - Train 01 - Transport 3rd, 4th ; 5th CBS transport to Perth | 15/07/2021 | 02/12/2021 | 15/07/2021 | 02/12/2021 | 0 | TK_Complete | 1208363553 | 425 | 1208363553_425
MRPP2-EAT.00080 | TT_Task | EMU - Train 01 - Carbodyshell Manufacture 6th CBS | 15/07/2021 | 09/12/2021 | 15/07/2021 | 09/12/2021 | 0 | TK_Complete | 1208363553 | 424 | 1208363553_424
MRPP2-EAT.00090 | TT_Task | EMU - Train 01 - Transport 6th CBS transport to Perth | 24/02/2022 | 30/03/2022 | 03/01/2022 | 07/02/2022 | 0 | TK_Complete | 1208363553 | 425 | 1208363553_425
MRPP2-EAT.00150 | TT_Task | EMU - Train 01 - Assemble Bogie in Perth | 23/09/2021 | 17/05/2022 | 23/09/2021 | nan | 0 | TK_Active | 1208363553 | 426 | 1208363553_426
MRPP2-EAT.00160 | TT_Task | EMU - Train 01 - Fitting | 22/10/2021 | 15/06/2022 | 22/10/2021 | nan | 0 | TK_Active | 1208363553 | 427 | 1208363553_427
MRPP2-EAT.00170 | TT_Task | EMU - Train 01 - Routine Test (Incl. Mechanical Car Level Validation) | 11/03/2022 | 26/08/2022 | 04/02/2022 | nan | 0 | TK_Active | 1208363553 | 428 | 1208363553_428
MRPP2-EAT.13280 | TT_Task | EMU - Train 01 - Fitting CBS 01 @FS1 | 22/10/2021 | 11/11/2021 | 22/10/2021 | 11/11/2021 | 0 | TK_Complete | 1208363553 | 429 | 1208363553_429
MRPP2-EAT.13290 | TT_Task | EMU - Train 01 - Fitting CBS 01 @FS2 | 12/11/2021 | 02/12/2021 | 12/11/2021 | 02/12/2021 | 0 | TK_Complete | 1208363553 | 429 | 1208363553_429
MRPP2-EAT.13300 | TT_Task | EMU - Train 01 - Fitting CBS 01 @FS3 ; Dielec | 03/12/2021 | 23/12/2021 | 03/12/2021 | 23/12/2021 | 0 | TK_Complete | 1208363553 | 429 | 1208363553_429
MRPP2-EAT.13310 | TT_Task | EMU - Train 01 - Fitting CBS 01 @FS4 | 17/02/2022 | 14/03/2022 | 24/12/2021 | 19/01/2022 | 0 | TK_Complete | 1208363553 | 429 | 1208363553_429
MRPP2-EAT.13320 | TT_Task | EMU - Train 01 - Fitting CBS 01 @FS5 | 15/03/2022 | 28/03/2022 | 20/01/2022 | 03/02/2022 | 0 | TK_Complete | 1208363553 | 429 | 1208363553_429
MRPP2-EAT.13330 | TT_Task | EMU - Train 01 - Fitting CBS 02 @FS1 | 12/11/2021 | 02/12/2021 | 12/11/2021 | 02/12/2021 | 0 | TK_Complete | 1208363553 | 429 | 1208363553_429
MRPP2-EAT.13340 | TT_Task | EMU - Train 01 - Fitting CBS 02 @FS2 | 03/12/2021 | 23/12/2021 | 03/12/2021 | 23/12/2021 | 0 | TK_Complete | 1208363553 | 429 | 1208363553_429
MRPP2-EAT.13350 | TT_Task | EMU - Train 01 - Fitting CBS 02 @FS3 ; Dielec | 17/02/2022 | 14/03/2022 | 24/12/2021 | 19/01/2022 | 0 | TK_Complete | 1208363553 | 429 | 1208363553_429
MRPP2-EAT.13360 | TT_Task | EMU - Train 01 - Fitting CBS 02 @FS4 | 15/03/2022 | 07/04/2022 | 20/01/2022 | 15/02/2022 | 0 | TK_Complete | 1208363553 | 429 | 1208363553_429
MRPP2-EAT.13370 | TT_Task | EMU - Train 01 - Fitting CBS 02 @FS5 | 23/03/2022 | 05/04/2022 | 16/02/2022 | 01/03/2022 | 0 | TK_Complete | 1208363553 | 429 | 1208363553_429
MRPP2-EAT.13380 | TT_Task | EMU - Train 01 - Fitting CBS 03 @FS1 | 03/12/2021 | 23/12/2021 | 03/12/2021 | 23/12/2021 | 0 | TK_Complete | 1208363553 | 429 | 1208363553_429
MRPP2-EAT.13390 | TT_Task | EMU - Train 01 - Fitting CBS 03 @FS2 | 17/02/2022 | 14/03/2022 | 24/12/2021 | 19/01/2022 | 0 | TK_Complete | 1208363553 | 429 | 1208363553_429
MRPP2-EAT.13400 | TT_Task | EMU - Train 01 - Fitting CBS 03 @FS3 ; Dielec | 15/03/2022 | 07/04/2022 | 20/01/2022 | 15/02/2022 | 0 | TK_Complete | 1208363553 | 429 | 1208363553_429
MRPP2-EAT.13410 | TT_Task | EMU - Train 01 - Fitting CBS 03 @FS4 | 23/03/2022 | 19/04/2022 | 16/02/2022 | 11/03/2022 | 0 | TK_Complete | 1208363553 | 429 | 1208363553_429
MRPP2-EAT.13420 | TT_Task | EMU - Train 01 - Fitting CBS 04 @FS5 | 14/04/2022 | 28/04/2022 | 14/03/2022 | 25/03/2022 | 0 | TK_Complete | 1208363553 | 429 | 1208363553_429
MRPP2-EAT.13430 | TT_Task | EMU - Train 01 - Fitting CBS 04 @FS1 | 28/01/2022 | 22/02/2022 | 24/12/2021 | 19/01/2022 | 0 | TK_Complete | 1208363553 | 429 | 1208363553_429
MRPP2-EAT.13440 | TT_Task | EMU - Train 01 - Fitting CBS 04 @FS2 | 23/02/2022 | 18/03/2022 | 20/01/2022 | 15/02/2022 | 0 | TK_Complete | 1208363553 | 429 | 1208363553_429
MRPP2-EAT.13450 | TT_Task | EMU - Train 01 - Fitting CBS 04 @FS3 ; Dielec | 23/03/2022 | 19/04/2022 | 16/02/2022 | 11/03/2022 | 0 | TK_Complete | 1208363553 | 429 | 1208363553_429
MRPP2-EAT.13460 | TT_Task | EMU - Train 01 - Fitting CBS 04 @FS4 | 14/04/2022 | 10/05/2022 | 14/03/2022 | nan | 0 | TK_Active | 1208363553 | 429 | 1208363553_429
MRPP2-EAT.13470 | TT_Task | EMU - Train 01 - Fitting CBS 04 @FS5 | 07/04/2022 | 22/04/2022 | nan | nan | 0 | TK_NotStart | 1208363553 | 429 | 1208363553_429
MRPP2-EAT.13480 | TT_Task | EMU - Train 01 - Fitting CBS 05 @FS1 | 28/01/2022 | 22/02/2022 | 20/01/2022 | 15/02/2022 | 0 | TK_Complete | 1208363553 | 429 | 1208363553_429
MRPP2-EAT.13490 | TT_Task | EMU - Train 01 - Fitting CBS 05 @FS2 | 23/03/2022 | 19/04/2022 | 16/02/2022 | 11/03/2022 | 0 | TK_Complete | 1208363553 | 429 | 1208363553_429
MRPP2-EAT.13500 | TT_Task | EMU - Train 01 - Fitting CBS 05 @FS3 ; Dielec | 14/04/2022 | 10/05/2022 | 14/03/2022 | nan | 0 | TK_Active | 1208363553 | 429 | 1208363553_429
MRPP2-EAT.13510 | TT_Task | EMU - Train 01 - Fitting CBS 05 @FS4 | 07/04/2022 | 05/05/2022 | nan | nan | 0 | TK_NotStart | 1208363553 | 429 | 1208363553_429
MRPP2-EAT.13520 | TT_Task | EMU - Train 01 - Fitting CBS 05 @FS5 | 06/05/2022 | 19/05/2022 | nan | nan | 0 | TK_NotStart | 1208363553 | 429 | 1208363553_429
MRPP2-EAT.13530 | TT_Task | EMU - Train 01 - Fitting CBS 06 @FS1 | 04/03/2022 | 29/03/2022 | 16/02/2022 | 11/03/2022 | 0 | TK_Complete | 1208363553 | 429 | 1208363553_429
MRPP2-EAT.13540 | TT_Task | EMU - Train 01 - Fitting CBS 06 @FS2 | 14/04/2022 | 10/05/2022 | 14/03/2022 | nan | 0 | TK_Active | 1208363553 | 429 | 1208363553_429
MRPP2-EAT.13550 | TT_Task | EMU - Train 01 - Fitting CBS 06 @FS3 ; Dielec | 07/04/2022 | 05/05/2022 | nan | nan | 0 | TK_NotStart | 1208363553 | 429 | 1208363553_429
MRPP2-EAT.13560 | TT_Task | EMU - Train 01 - Fitting CBS 06 @FS4 | 06/05/2022 | 31/05/2022 | nan | nan | 0 | TK_NotStart | 1208363553 | 429 | 1208363553_429
MRPP2-EAT.13570 | TT_Task | EMU - Train 01 - Fitting CBS 06 @FS5 | 01/06/2022 | 15/06/2022 | nan | nan | 0 | TK_NotStart | 1208363553 | 429 | 1208363553_429
MRPP2-EAT.00200 | TT_Task | EMU - Train 02 - Carbodyshell Manufacture 1st [2] CBS | 26/08/2021 | 31/12/2021 | 26/08/2021 | 31/12/2021 | 0 | TK_Complete | 1208363553 | 424 | 1208363553_424
MRPP2-EAT.00230 | TT_Task | EMU - Train 02 - Transport 1st [2] CBS transport to Perth | 28/01/2022 | 01/04/2022 | 03/01/2022 | 08/03/2022 | 0 | TK_Complete | 1208363553 | 425 | 1208363553_425
MRPP2-EAT.00240 | TT_Task | EMU - Train 02 - Carbodyshell Manufacture 2nd [2] CBS | 24/02/2022 | 06/04/2022 | 03/01/2022 | 14/02/2022 | 0 | TK_Complete | 1208363553 | 424 | 1208363553_424
MRPP2-EAT.00260 | TT_Task | EMU - Train 02 - Transport 2nd [2] CBS transport to Perth | 04/03/2022 | 11/05/2022 | 15/02/2022 | nan | 72 | TK_Active | 1208363553 | 425 | 1208363553_425
MRPP2-EAT.00270 | TT_Task | EMU - Train 02 - Carbodyshell Manufacture 3rd [2] CBS | 04/03/2022 | 18/04/2022 | 15/02/2022 | 28/03/2022 | 0 | TK_Complete | 1208363553 | 424 | 1208363553_424
MRPP2-EAT.00290 | TT_Task | EMU - Train 02 - Assemble Bogie in Perth | 04/03/2022 | 16/08/2022 | 28/02/2022 | nan | 0 | TK_Active | 1208363553 | 426 | 1208363553_426
MRPP2-EAT.00310 | TT_Task | EMU - Train 02 - Transport 3rd [2] CBS transport to Perth | 04/04/2022 | 10/06/2022 | 29/03/2022 | nan | 56 | TK_Active | 1208363553 | 425 | 1208363553_425
MRPP2-EAT.00340 | TT_Task | EMU - Train 02 - Routine Test (Incl. Car-Level Routine Testing (HVAC) and HVAC Performance Type Test - I | 23/06/2022 | 21/09/2022 | nan | nan | 0 | TK_NotStart | 1208363553 | 114 | 1208363553_114
MRPP2-EAT.13580 | TT_Task | EMU - Train 02 - Fitting CBS 01 @FS1 (Dates are Indicative) | 04/04/2022 | 02/05/2022 | 14/03/2022 | nan | 0 | TK_Active | 1208363553 | 430 | 1208363553_430
MRPP2-EAT.13590 | TT_Task | EMU - Train 02 - Fitting CBS 01 @FS2 (Dates are Indicative) | 07/04/2022 | 05/05/2022 | nan | nan | 0 | TK_NotStart | 1208363553 | 430 | 1208363553_430
MRPP2-EAT.13600 | TT_Task | EMU - Train 02 - Fitting CBS 01 @FS3 ; Dielec (Dates are Indicative) | 06/05/2022 | 31/05/2022 | nan | nan | 0 | TK_NotStart | 1208363553 | 431 | 1208363553_431
MRPP2-EAT.13610 | TT_Task | EMU - Train 02 - Fitting CBS 01 @FS4 (Dates are Indicative) | 01/06/2022 | 15/06/2022 | nan | nan | 0 | TK_NotStart | 1208363553 | 432 | 1208363553_432
MRPP2-EAT.13620 | TT_Task | EMU - Train 02 - Fitting CBS 01 @FS5 (Dates are Indicative) | 16/06/2022 | 22/06/2022 | nan | nan | 0 | TK_NotStart | 1208363553 | 433 | 1208363553_433
MRPP2-EAT.13630 | TT_Task | EMU - Train 02 - Fitting CBS 02 @FS1 (Dates are Indicative) | 07/04/2022 | 05/05/2022 | nan | nan | 0 | TK_NotStart | 1208363553 | 430 | 1208363553_430
MRPP2-EAT.13640 | TT_Task | EMU - Train 02 - Fitting CBS 02 @FS2 (Dates are Indicative) | 06/05/2022 | 31/05/2022 | nan | nan | 0 | TK_NotStart | 1208363553 | 430 | 1208363553_430
MRPP2-EAT.13650 | TT_Task | EMU - Train 02 - Fitting CBS 02 @FS3 ; Dielec (Dates are Indicative) | 01/06/2022 | 15/06/2022 | nan | nan | 0 | TK_NotStart | 1208363553 | 431 | 1208363553_431
MRPP2-EAT.13660 | TT_Task | EMU - Train 02 - Fitting CBS 02 @FS4 (Dates are Indicative) | 16/06/2022 | 29/06/2022 | nan | nan | 0 | TK_NotStart | 1208363553 | 432 | 1208363553_432
MRPP2-EAT.13670 | TT_Task | EMU - Train 02 - Fitting CBS 02 @FS5 (Dates are Indicative) | 30/06/2022 | 06/07/2022 | nan | nan | 0 | TK_NotStart | 1208363553 | 433 | 1208363553_433
MRPP2-EAT.13680 | TT_Task | EMU - Train 02 - Fitting CBS 03 @FS1 (Dates are Indicative) | 06/05/2022 | 31/05/2022 | nan | nan | 0 | TK_NotStart | 1208363553 | 430 | 1208363553_430
MRPP2-EAT.13690 | TT_Task | EMU - Train 02 - Fitting CBS 03 @FS2 (Dates are Indicative) | 01/06/2022 | 15/06/2022 | nan | nan | 0 | TK_NotStart | 1208363553 | 430 | 1208363553_430
MRPP2-EAT.13700 | TT_Task | EMU - Train 02 - Fitting CBS 03 @FS3 ; Dielec (Dates are Indicative) | 16/06/2022 | 29/06/2022 | nan | nan | 0 | TK_NotStart | 1208363553 | 431 | 1208363553_431
MRPP2-EAT.13710 | TT_Task | EMU - Train 02 - Fitting CBS 03 @FS4 (Dates are Indicative) | 30/06/2022 | 13/07/2022 | nan | nan | 0 | TK_NotStart | 1208363553 | 432 | 1208363553_432
MRPP2-EAT.13720 | TT_Task | EMU - Train 02 - Fitting CBS 04 @FS5 (Dates are Indicative) | 14/07/2022 | 20/07/2022 | nan | nan | 0 | TK_NotStart | 1208363553 | 433 | 1208363553_433
MRPP2-EAT.13730 | TT_Task | EMU - Train 02 - Fitting CBS 04 @FS1 (Dates are Indicative) | 01/06/2022 | 15/06/2022 | nan | nan | 0 | TK_NotStart | 1208363553 | 430 | 1208363553_430
MRPP2-EAT.13740 | TT_Task | EMU - Train 02 - Fitting CBS 04 @FS2 (Dates are Indicative) | 16/06/2022 | 29/06/2022 | nan | nan | 0 | TK_NotStart | 1208363553 | 430 | 1208363553_430
MRPP2-EAT.13750 | TT_Task | EMU - Train 02 - Fitting CBS 04 @FS3 ; Dielec (Dates are Indicative) | 30/06/2022 | 13/07/2022 | nan | nan | 0 | TK_NotStart | 1208363553 | 431 | 1208363553_431
MRPP2-EAT.13760 | TT_Task | EMU - Train 02 - Fitting CBS 04 @FS4 (Dates are Indicative) | 14/07/2022 | 27/07/2022 | nan | nan | 0 | TK_NotStart | 1208363553 | 432 | 1208363553_432
MRPP2-EAT.13770 | TT_Task | EMU - Train 02 - Fitting CBS 04 @FS5 (Dates are Indicative) | 28/07/2022 | 03/08/2022 | nan | nan | 0 | TK_NotStart | 1208363553 | 433 | 1208363553_433
MRPP2-EAT.13780 | TT_Task | EMU - Train 02 - Fitting CBS 05 @FS1 (Dates are Indicative) | 16/06/2022 | 29/06/2022 | nan | nan | 0 | TK_NotStart | 1208363553 | 433 | 1208363553_433
MRPP2-EAT.13790 | TT_Task | EMU - Train 02 - Fitting CBS 05 @FS2 (Dates are Indicative) | 30/06/2022 | 13/07/2022 | nan | nan | 0 | TK_NotStart | 1208363553 | 433 | 1208363553_433
MRPP2-EAT.13800 | TT_Task | EMU - Train 02 - Fitting CBS 05 @FS3 ; Dielec (Dates are Indicative) | 14/07/2022 | 27/07/2022 | nan | nan | 0 | TK_NotStart | 1208363553 | 431 | 1208363553_431
MRPP2-EAT.13810 | TT_Task | EMU - Train 02 - Fitting CBS 05 @FS4 (Dates are Indicative) | 28/07/2022 | 10/08/2022 | nan | nan | 0 | TK_NotStart | 1208363553 | 432 | 1208363553_432
MRPP2-EAT.13820 | TT_Task | EMU - Train 02 - Fitting CBS 05 @FS5 (Dates are Indicative) | 11/08/2022 | 17/08/2022 | nan | nan | 0 | TK_NotStart | 1208363553 | 433 | 1208363553_433
MRPP2-EAT.13830 | TT_Task | EMU - Train 02 - Fitting CBS 06 @FS1 (Dates are Indicative) | 30/06/2022 | 13/07/2022 | nan | nan | 0 | TK_NotStart | 1208363553 | 434 | 1208363553_434
MRPP2-EAT.13840 | TT_Task | EMU - Train 02 - Fitting CBS 06 @FS2 (Dates are Indicative) | 14/07/2022 | 27/07/2022 | nan | nan | 0 | TK_NotStart | 1208363553 | 434 | 1208363553_434
MRPP2-EAT.13850 | TT_Task | EMU - Train 02 - Fitting CBS 06 @FS3 ; Dielec (Dates are Indicative) | 28/07/2022 | 10/08/2022 | nan | nan | 0 | TK_NotStart | 1208363553 | 431 | 1208363553_431
MRPP2-EAT.13860 | TT_Task | EMU - Train 02 - Fitting CBS 06 @FS4 (Dates are Indicative) | 11/08/2022 | 24/08/2022 | nan | nan | 0 | TK_NotStart | 1208363553 | 434 | 1208363553_434
MRPP2-EAT.13870 | TT_Task | EMU - Train 02 - Fitting CBS 06 @FS5 (Dates are Indicative) | 25/08/2022 | 31/08/2022 | nan | nan | 0 | TK_NotStart | 1208363553 | 434 | 1208363553_434
MRPP2-EAT.10020 | TT_Task | EMU - Train 03 - Carbodyshell | 04/04/2022 | 10/06/2022 | 29/03/2022 | nan | 0 | TK_Active | 1208363553 | 435 | 1208363553_435
MRPP2-EAT.10470 | TT_Task | EMU - Train 03 - Assemble Bogie in Perth | 29/07/2022 | 24/03/2023 | nan | nan | 240 | TK_NotStart | 1208363553 | 426 | 1208363553_426
MRPP2-EAT.10480 | TT_Task | EMU - Train 03 - CBS Transport from Sri City Fty to Bellevue Depot | 07/06/2022 | 09/08/2022 | nan | nan | 0 | TK_NotStart | 1208363553 | 436 | 1208363553_436
MRPP2-EAT.12070 | TT_Task | EMU - Train 03 - Routine Test | 06/02/2023 | 10/05/2023 | nan | nan | 0 | TK_NotStart | 1208363553 | 437 | 1208363553_437
MRPP2-EAT.13880 | TT_Task | EMU - Train 03 - Fitting CBS 01 @FS1 (Dates are Indicative) | 12/08/2022 | 25/08/2022 | nan | nan | 0 | TK_NotStart | 1208363553 | 430 | 1208363553_430
MRPP2-EAT.13890 | TT_Task | EMU - Train 03 - Fitting CBS 01 @FS2 (Dates are Indicative) | 26/08/2022 | 08/09/2022 | nan | nan | 0 | TK_NotStart | 1208363553 | 430 | 1208363553_430
MRPP2-EAT.13910 | TT_Task | EMU - Train 03 - Fitting CBS 01 @FS4 (Dates are Indicative) | 20/12/2022 | 19/01/2023 | nan | nan | 0 | TK_NotStart | 1208363553 | 432 | 1208363553_432
MRPP2-EAT.13920 | TT_Task | EMU - Train 03 - Fitting CBS 01 @FS5 (Dates are Indicative) | 20/01/2023 | 03/02/2023 | nan | nan | 0 | TK_NotStart | 1208363553 | 433 | 1208363553_433
MRPP2-EAT.14780 | TT_Task | EMU - Train 03 - Fitting CBS 01 @FS3 ; Dielec (Dates are Indicative) - Impacted | 22/11/2022 | 19/12/2022 | nan | nan | 0 | TK_NotStart | 1208363553 | 438 | 1208363553_438
MRPP2-EAT.14790 | TT_Task | EMU - Train 03 - Fitting CBS 01 @FS3 ; Dielec (Dates are Indicative) - Not Impacted | 09/09/2022 | 20/09/2022 | nan | nan | 344 | TK_NotStart | 1208363553 | 438 | 1208363553_438
MRPP2-EAT.13930 | TT_Task | EMU - Train 03 - Fitting CBS 02 @FS1 (Dates are Indicative) | 26/08/2022 | 08/09/2022 | nan | nan | 0 | TK_NotStart | 1208363553 | 430 | 1208363553_430
MRPP2-EAT.13950 | TT_Task | EMU - Train 03 - Fitting CBS 02 @FS3 ; Dielec (Dates are Indicative) | 20/12/2022 | 19/01/2023 | nan | nan | 0 | TK_NotStart | 1208363553 | 431 | 1208363553_431
MRPP2-EAT.13960 | TT_Task | EMU - Train 03 - Fitting CBS 02 @FS4 (Dates are Indicative) | 20/01/2023 | 13/02/2023 | nan | nan | 0 | TK_NotStart | 1208363553 | 432 | 1208363553_432
MRPP2-EAT.13970 | TT_Task | EMU - Train 03 - Fitting CBS 02 @FS5 (Dates are Indicative) | 14/02/2023 | 23/02/2023 | nan | nan | 0 | TK_NotStart | 1208363553 | 433 | 1208363553_433
MRPP2-EAT.14800 | TT_Task | EMU - Train 03 - Fitting CBS 02 @FS2 (Dates are Indicative) - Not Impacted | 09/09/2022 | 20/09/2022 | nan | nan | 0 | TK_NotStart | 1208363553 | 438 | 1208363553_438
MRPP2-EAT.14810 | TT_Task | EMU - Train 03 - Fitting CBS 02 @FS2 (Dates are Indicative) - Impacted | 22/11/2022 | 19/12/2022 | nan | nan | 0 | TK_NotStart | 1208363553 | 438 | 1208363553_438
MRPP2-EAT.13990 | TT_Task | EMU - Train 03 - Fitting CBS 03 @FS2 (Dates are Indicative) | 20/12/2022 | 19/01/2023 | nan | nan | 0 | TK_NotStart | 1208363553 | 430 | 1208363553_430
MRPP2-EAT.14000 | TT_Task | EMU - Train 03 - Fitting CBS 03 @FS3 ; Dielec (Dates are Indicative) | 20/01/2023 | 13/02/2023 | nan | nan | 0 | TK_NotStart | 1208363553 | 431 | 1208363553_431
MRPP2-EAT.14010 | TT_Task | EMU - Train 03 - Fitting CBS 03 @FS4 (Dates are Indicative) | 14/02/2023 | 02/03/2023 | nan | nan | 0 | TK_NotStart | 1208363553 | 432 | 1208363553_432
MRPP2-EAT.14020 | TT_Task | EMU - Train 03 - Fitting CBS 03 @FS5 (Dates are Indicative) | 03/03/2023 | 09/03/2023 | nan | nan | 0 | TK_NotStart | 1208363553 | 433 | 1208363553_433
MRPP2-EAT.14820 | TT_Task | EMU - Train 03 - Fitting CBS 03 @FS1 (Dates are Indicative) - Not Impacted | 21/09/2022 | 03/10/2022 | nan | nan | 280 | TK_NotStart | 1208363553 | 438 | 1208363553_438
MRPP2-EAT.14830 | TT_Task | EMU - Train 03 - Fitting CBS 03 @FS1 (Dates are Indicative) - Impacted | 22/11/2022 | 19/12/2022 | nan | nan | 0 | TK_NotStart | 1208363553 | 438 | 1208363553_438
MRPP2-EAT.14030 | TT_Task | EMU - Train 03 - Fitting CBS 04 @FS1 (Dates are Indicative) | 20/12/2022 | 19/01/2023 | nan | nan | 0 | TK_NotStart | 1208363553 | 430 | 1208363553_430
MRPP2-EAT.14040 | TT_Task | EMU - Train 03 - Fitting CBS 04 @FS2 (Dates are Indicative) | 20/01/2023 | 13/02/2023 | nan | nan | 0 | TK_NotStart | 1208363553 | 430 | 1208363553_430
MRPP2-EAT.14050 | TT_Task | EMU - Train 03 - Fitting CBS 04 @FS3 ; Dielec (Dates are Indicative) | 14/02/2023 | 02/03/2023 | nan | nan | 0 | TK_NotStart | 1208363553 | 431 | 1208363553_431
MRPP2-EAT.14060 | TT_Task | EMU - Train 03 - Fitting CBS 04 @FS4 (Dates are Indicative) | 03/03/2023 | 14/03/2023 | nan | nan | 0 | TK_NotStart | 1208363553 | 432 | 1208363553_432
MRPP2-EAT.14070 | TT_Task | EMU - Train 03 - Fitting CBS 04 @FS5 (Dates are Indicative) | 15/03/2023 | 21/03/2023 | nan | nan | 0 | TK_NotStart | 1208363553 | 433 | 1208363553_433
MRPP2-EAT.14080 | TT_Task | EMU - Train 03 - Fitting CBS 05 @FS1 (Dates are Indicative) | 20/01/2023 | 13/02/2023 | nan | nan | 0 | TK_NotStart | 1208363553 | 433 | 1208363553_433
MRPP2-EAT.14090 | TT_Task | EMU - Train 03 - Fitting CBS 05 @FS2 (Dates are Indicative) | 14/02/2023 | 02/03/2023 | nan | nan | 0 | TK_NotStart | 1208363553 | 433 | 1208363553_433
MRPP2-EAT.14100 | TT_Task | EMU - Train 03 - Fitting CBS 05 @FS3 ; Dielec (Dates are Indicative) | 03/03/2023 | 14/03/2023 | nan | nan | 0 | TK_NotStart | 1208363553 | 431 | 1208363553_431
MRPP2-EAT.14110 | TT_Task | EMU - Train 03 - Fitting CBS 05 @FS4 (Dates are Indicative) | 15/03/2023 | 24/03/2023 | nan | nan | 0 | TK_NotStart | 1208363553 | 432 | 1208363553_432
MRPP2-EAT.14120 | TT_Task | EMU - Train 03 - Fitting CBS 05 @FS5 (Dates are Indicative) | 27/03/2023 | 31/03/2023 | nan | nan | 0 | TK_NotStart | 1208363553 | 433 | 1208363553_433
MRPP2-EAT.14130 | TT_Task | EMU - Train 03 - Fitting CBS 06 @FS1 (Dates are Indicative) | 14/02/2023 | 02/03/2023 | nan | nan | 0 | TK_NotStart | 1208363553 | 434 | 1208363553_434
MRPP2-EAT.14140 | TT_Task | EMU - Train 03 - Fitting CBS 06 @FS2 (Dates are Indicative) | 03/03/2023 | 14/03/2023 | nan | nan | 0 | TK_NotStart | 1208363553 | 434 | 1208363553_434
MRPP2-EAT.14150 | TT_Task | EMU - Train 03 - Fitting CBS 06 @FS3 ; Dielec (Dates are Indicative) | 15/03/2023 | 24/03/2023 | nan | nan | 0 | TK_NotStart | 1208363553 | 431 | 1208363553_431
MRPP2-EAT.14160 | TT_Task | EMU - Train 03 - Fitting CBS 06 @FS4 (Dates are Indicative) | 27/03/2023 | 05/04/2023 | nan | nan | 0 | TK_NotStart | 1208363553 | 434 | 1208363553_434
MRPP2-EAT.14170 | TT_Task | EMU - Train 03 - Fitting CBS 06 @FS5 (Dates are Indicative) | 06/04/2023 | 14/04/2023 | nan | nan | 0 | TK_NotStart | 1208363553 | 434 | 1208363553_434
MRPP2-EAT.10030 | TT_Task | EMU - Train 04 - Carbodyshell | 07/06/2022 | 27/07/2022 | nan | nan | 0 | TK_NotStart | 1208363553 | 439 | 1208363553_439
MRPP2-EAT.10490 | TT_Task | EMU - Train 04 - Assemble Bogie in Perth | 17/02/2023 | 06/06/2023 | nan | nan | 0 | TK_NotStart | 1208363553 | 426 | 1208363553_426
MRPP2-EAT.10500 | TT_Task | EMU - Train 04 - CBS Transport from Sri City Fty to Bellevue Depot | 10/08/2022 | 13/10/2022 | nan | nan | 0 | TK_NotStart | 1208363553 | 436 | 1208363553_436
MRPP2-EAT.12080 | TT_Task | EMU - Train 04 - Routine Test | 28/04/2023 | 31/07/2023 | nan | nan | 0 | TK_NotStart | 1208363553 | 437 | 1208363553_437
MRPP2-EAT.14180 | TT_Task | EMU - Train 04 - Fitting CBS 01 @FS1 (Dates are Indicative) | 03/03/2023 | 14/03/2023 | nan | nan | 0 | TK_NotStart | 1208363553 | 430 | 1208363553_430
MRPP2-EAT.14190 | TT_Task | EMU - Train 04 - Fitting CBS 01 @FS2 (Dates are Indicative) | 15/03/2023 | 24/03/2023 | nan | nan | 0 | TK_NotStart | 1208363553 | 430 | 1208363553_430
MRPP2-EAT.14200 | TT_Task | EMU - Train 04 - Fitting CBS 01 @FS3 ; Dielec (Dates are Indicative) | 27/03/2023 | 05/04/2023 | nan | nan | 0 | TK_NotStart | 1208363553 | 431 | 1208363553_431
MRPP2-EAT.14210 | TT_Task | EMU - Train 04 - Fitting CBS 01 @FS4 (Dates are Indicative) | 06/04/2023 | 19/04/2023 | nan | nan | 0 | TK_NotStart | 1208363553 | 432 | 1208363553_432
MRPP2-EAT.14220 | TT_Task | EMU - Train 04 - Fitting CBS 01 @FS5 (Dates are Indicative) | 20/04/2023 | 27/04/2023 | nan | nan | 0 | TK_NotStart | 1208363553 | 433 | 1208363553_433
MRPP2-EAT.14230 | TT_Task | EMU - Train 04 - Fitting CBS 02 @FS1 (Dates are Indicative) | 15/03/2023 | 24/03/2023 | nan | nan | 0 | TK_NotStart | 1208363553 | 430 | 1208363553_430
MRPP2-EAT.14240 | TT_Task | EMU - Train 04 - Fitting CBS 02 @FS2 (Dates are Indicative) | 27/03/2023 | 05/04/2023 | nan | nan | 0 | TK_NotStart | 1208363553 | 430 | 1208363553_430
MRPP2-EAT.14250 | TT_Task | EMU - Train 04 - Fitting CBS 02 @FS3 ; Dielec (Dates are Indicative) | 06/04/2023 | 19/04/2023 | nan | nan | 0 | TK_NotStart | 1208363553 | 431 | 1208363553_431
MRPP2-EAT.14260 | TT_Task | EMU - Train 04 - Fitting CBS 02 @FS4 (Dates are Indicative) | 20/04/2023 | 02/05/2023 | nan | nan | 0 | TK_NotStart | 1208363553 | 432 | 1208363553_432
MRPP2-EAT.14270 | TT_Task | EMU - Train 04 - Fitting CBS 02 @FS5 (Dates are Indicative) | 03/05/2023 | 09/05/2023 | nan | nan | 0 | TK_NotStart | 1208363553 | 433 | 1208363553_433
MRPP2-EAT.14280 | TT_Task | EMU - Train 04 - Fitting CBS 03 @FS1 (Dates are Indicative) | 27/03/2023 | 05/04/2023 | nan | nan | 0 | TK_NotStart | 1208363553 | 430 | 1208363553_430
MRPP2-EAT.14290 | TT_Task | EMU - Train 04 - Fitting CBS 03 @FS2 (Dates are Indicative) | 06/04/2023 | 19/04/2023 | nan | nan | 0 | TK_NotStart | 1208363553 | 430 | 1208363553_430
MRPP2-EAT.14300 | TT_Task | EMU - Train 04 - Fitting CBS 03 @FS3 ; Dielec (Dates are Indicative) | 20/04/2023 | 02/05/2023 | nan | nan | 0 | TK_NotStart | 1208363553 | 431 | 1208363553_431
MRPP2-EAT.14310 | TT_Task | EMU - Train 04 - Fitting CBS 03 @FS4 (Dates are Indicative) | 03/05/2023 | 12/05/2023 | nan | nan | 0 | TK_NotStart | 1208363553 | 432 | 1208363553_432
MRPP2-EAT.14320 | TT_Task | EMU - Train 04 - Fitting CBS 04 @FS5 (Dates are Indicative) | 15/05/2023 | 19/05/2023 | nan | nan | 0 | TK_NotStart | 1208363553 | 433 | 1208363553_433
MRPP2-EAT.14330 | TT_Task | EMU - Train 04 - Fitting CBS 04 @FS1 (Dates are Indicative) | 06/04/2023 | 19/04/2023 | nan | nan | 0 | TK_NotStart | 1208363553 | 430 | 1208363553_430
MRPP2-EAT.14340 | TT_Task | EMU - Train 04 - Fitting CBS 04 @FS2 (Dates are Indicative) | 20/04/2023 | 02/05/2023 | nan | nan | 0 | TK_NotStart | 1208363553 | 430 | 1208363553_430
MRPP2-EAT.14350 | TT_Task | EMU - Train 04 - Fitting CBS 04 @FS3 ; Dielec (Dates are Indicative) | 03/05/2023 | 12/05/2023 | nan | nan | 0 | TK_NotStart | 1208363553 | 431 | 1208363553_431
MRPP2-EAT.14360 | TT_Task | EMU - Train 04 - Fitting CBS 04 @FS4 (Dates are Indicative) | 15/05/2023 | 24/05/2023 | nan | nan | 0 | TK_NotStart | 1208363553 | 432 | 1208363553_432
MRPP2-EAT.14370 | TT_Task | EMU - Train 04 - Fitting CBS 04 @FS5 (Dates are Indicative) | 25/05/2023 | 31/05/2023 | nan | nan | 0 | TK_NotStart | 1208363553 | 433 | 1208363553_433
MRPP2-EAT.14380 | TT_Task | EMU - Train 04 - Fitting CBS 05 @FS1 (Dates are Indicative) | 20/04/2023 | 02/05/2023 | nan | nan | 0 | TK_NotStart | 1208363553 | 433 | 1208363553_433
MRPP2-EAT.14390 | TT_Task | EMU - Train 04 - Fitting CBS 05 @FS2 (Dates are Indicative) | 03/05/2023 | 12/05/2023 | nan | nan | 0 | TK_NotStart | 1208363553 | 433 | 1208363553_433
MRPP2-EAT.14400 | TT_Task | EMU - Train 04 - Fitting CBS 05 @FS3 ; Dielec (Dates are Indicative) | 15/05/2023 | 24/05/2023 | nan | nan | 0 | TK_NotStart | 1208363553 | 431 | 1208363553_431
MRPP2-EAT.14410 | TT_Task | EMU - Train 04 - Fitting CBS 05 @FS4 (Dates are Indicative) | 25/05/2023 | 06/06/2023 | nan | nan | 0 | TK_NotStart | 1208363553 | 432 | 1208363553_432
MRPP2-EAT.14420 | TT_Task | EMU - Train 04 - Fitting CBS 05 @FS5 (Dates are Indicative) | 07/06/2023 | 13/06/2023 | nan | nan | 0 | TK_NotStart | 1208363553 | 433 | 1208363553_433
MRPP2-EAT.14430 | TT_Task | EMU - Train 04 - Fitting CBS 06 @FS1 (Dates are Indicative) | 03/05/2023 | 12/05/2023 | nan | nan | 0 | TK_NotStart | 1208363553 | 434 | 1208363553_434
MRPP2-EAT.14440 | TT_Task | EMU - Train 04 - Fitting CBS 06 @FS2 (Dates are Indicative) | 15/05/2023 | 24/05/2023 | nan | nan | 0 | TK_NotStart | 1208363553 | 434 | 1208363553_434
MRPP2-EAT.14450 | TT_Task | EMU - Train 04 - Fitting CBS 06 @FS3 ; Dielec (Dates are Indicative) | 25/05/2023 | 06/06/2023 | nan | nan | 0 | TK_NotStart | 1208363553 | 431 | 1208363553_431
MRPP2-EAT.14460 | TT_Task | EMU - Train 04 - Fitting CBS 06 @FS4 (Dates are Indicative) | 07/06/2023 | 16/06/2023 | nan | nan | 0 | TK_NotStart | 1208363553 | 434 | 1208363553_434
MRPP2-EAT.14470 | TT_Task | EMU - Train 04 - Fitting CBS 06 @FS5 (Dates are Indicative) | 19/06/2023 | 20/06/2023 | nan | nan | 0 | TK_NotStart | 1208363553 | 434 | 1208363553_434
MRPP2-EAT.10040 | TT_Task | EMU - Train 05 - Carbodyshell | 28/07/2022 | 30/09/2022 | nan | nan | 0 | TK_NotStart | 1208363553 | 435 | 1208363553_435
MRPP2-EAT.10510 | TT_Task | EMU - Train 05 - Assemble Bogie in Perth | 01/05/2023 | 28/07/2023 | nan | nan | 0 | TK_NotStart | 1208363553 | 426 | 1208363553_426
MRPP2-EAT.10520 | TT_Task | EMU - Train 05 - CBS Transport from Sri City Fty to Bellevue Depot | 14/10/2022 | 16/12/2022 | nan | nan | 992 | TK_NotStart | 1208363553 | 436 | 1208363553_436
MRPP2-EAT.12090 | TT_Task | EMU - Train 05 - Routine Test | 30/06/2023 | 30/08/2023 | nan | nan | 0 | TK_NotStart | 1208363553 | 437 | 1208363553_437
MRPP2-EAT.14480 | TT_Task | EMU - Train 05 - Fitting CBS 01 @FS1 (Dates are Indicative) | 15/05/2023 | 24/05/2023 | nan | nan | 0 | TK_NotStart | 1208363553 | 433 | 1208363553_433
MRPP2-EAT.14490 | TT_Task | EMU - Train 05 - Fitting CBS 01 @FS2 (Dates are Indicative) | 25/05/2023 | 06/06/2023 | nan | nan | 0 | TK_NotStart | 1208363553 | 433 | 1208363553_433
MRPP2-EAT.14500 | TT_Task | EMU - Train 05 - Fitting CBS 01 @FS3 ; Dielec (Dates are Indicative) | 07/06/2023 | 16/06/2023 | nan | nan | 0 | TK_NotStart | 1208363553 | 431 | 1208363553_431
MRPP2-EAT.14510 | TT_Task | EMU - Train 05 - Fitting CBS 01 @FS4 (Dates are Indicative) | 19/06/2023 | 26/06/2023 | nan | nan | 0 | TK_NotStart | 1208363553 | 432 | 1208363553_432
MRPP2-EAT.14520 | TT_Task | EMU - Train 05 - Fitting CBS 01 @FS5 (Dates are Indicative) | 27/06/2023 | 28/06/2023 | nan | nan | 0 | TK_NotStart | 1208363553 | 433 | 1208363553_433
MRPP2-EAT.14530 | TT_Task | EMU - Train 05 - Fitting CBS 02 @FS1 (Dates are Indicative) | 25/05/2023 | 06/06/2023 | nan | nan | 0 | TK_NotStart | 1208363553 | 433 | 1208363553_433
MRPP2-EAT.14540 | TT_Task | EMU - Train 05 - Fitting CBS 02 @FS2 (Dates are Indicative) | 07/06/2023 | 16/06/2023 | nan | nan | 0 | TK_NotStart | 1208363553 | 433 | 1208363553_433
MRPP2-EAT.14550 | TT_Task | EMU - Train 05 - Fitting CBS 02 @FS3 ; Dielec (Dates are Indicative) | 19/06/2023 | 26/06/2023 | nan | nan | 0 | TK_NotStart | 1208363553 | 431 | 1208363553_431
MRPP2-EAT.14560 | TT_Task | EMU - Train 05 - Fitting CBS 02 @FS4 (Dates are Indicative) | 27/06/2023 | 04/07/2023 | nan | nan | 0 | TK_NotStart | 1208363553 | 432 | 1208363553_432
MRPP2-EAT.14570 | TT_Task | EMU - Train 05 - Fitting CBS 02 @FS5 (Dates are Indicative) | 05/07/2023 | 06/07/2023 | nan | nan | 0 | TK_NotStart | 1208363553 | 433 | 1208363553_433
MRPP2-EAT.14580 | TT_Task | EMU - Train 05 - Fitting CBS 03 @FS1 (Dates are Indicative) | 07/06/2023 | 16/06/2023 | nan | nan | 0 | TK_NotStart | 1208363553 | 433 | 1208363553_433
MRPP2-EAT.14590 | TT_Task | EMU - Train 05 - Fitting CBS 03 @FS2 (Dates are Indicative) | 19/06/2023 | 26/06/2023 | nan | nan | 0 | TK_NotStart | 1208363553 | 433 | 1208363553_433
MRPP2-EAT.14600 | TT_Task | EMU - Train 05 - Fitting CBS 03 @FS3 ; Dielec (Dates are Indicative) | 27/06/2023 | 04/07/2023 | nan | nan | 0 | TK_NotStart | 1208363553 | 431 | 1208363553_431
MRPP2-EAT.14610 | TT_Task | EMU - Train 05 - Fitting CBS 03 @FS4 (Dates are Indicative) | 05/07/2023 | 12/07/2023 | nan | nan | 0 | TK_NotStart | 1208363553 | 432 | 1208363553_432
MRPP2-EAT.14620 | TT_Task | EMU - Train 05 - Fitting CBS 03 @FS5 (Dates are Indicative) | 13/07/2023 | 14/07/2023 | nan | nan | 0 | TK_NotStart | 1208363553 | 433 | 1208363553_433
MRPP2-EAT.14630 | TT_Task | EMU - Train 05 - Fitting CBS 04 @FS1 (Dates are Indicative) | 19/06/2023 | 26/06/2023 | nan | nan | 0 | TK_NotStart | 1208363553 | 433 | 1208363553_433
MRPP2-EAT.14640 | TT_Task | EMU - Train 05 - Fitting CBS 04 @FS2 (Dates are Indicative) | 27/06/2023 | 04/07/2023 | nan | nan | 0 | TK_NotStart | 1208363553 | 433 | 1208363553_433
MRPP2-EAT.14650 | TT_Task | EMU - Train 05 - Fitting CBS 04 @FS3 ; Dielec (Dates are Indicative) | 05/07/2023 | 12/07/2023 | nan | nan | 0 | TK_NotStart | 1208363553 | 431 | 1208363553_431
MRPP2-EAT.14660 | TT_Task | EMU - Train 05 - Fitting CBS 04 @FS4 (Dates are Indicative) | 13/07/2023 | 20/07/2023 | nan | nan | 0 | TK_NotStart | 1208363553 | 432 | 1208363553_432
MRPP2-EAT.14670 | TT_Task | EMU - Train 05 - Fitting CBS 04 @FS5 (Dates are Indicative) | 21/07/2023 | 24/07/2023 | nan | nan | 0 | TK_NotStart | 1208363553 | 433 | 1208363553_433
MRPP2-EAT.14680 | TT_Task | EMU - Train 05 - Fitting CBS 05 @FS1 (Dates are Indicative) | 27/06/2023 | 04/07/2023 | nan | nan | 0 | TK_NotStart | 1208363553 | 433 | 1208363553_433
MRPP2-EAT.14690 | TT_Task | EMU - Train 05 - Fitting CBS 05 @FS2 (Dates are Indicative) | 05/07/2023 | 12/07/2023 | nan | nan | 0 | TK_NotStart | 1208363553 | 433 | 1208363553_433
MRPP2-EAT.14700 | TT_Task | EMU - Train 05 - Fitting CBS 05 @FS3 ; Dielec (Dates are Indicative) | 13/07/2023 | 20/07/2023 | nan | nan | 0 | TK_NotStart | 1208363553 | 431 | 1208363553_431
MRPP2-EAT.14710 | TT_Task | EMU - Train 05 - Fitting CBS 05 @FS4 (Dates are Indicative) | 21/07/2023 | 28/07/2023 | nan | nan | 0 | TK_NotStart | 1208363553 | 432 | 1208363553_432
MRPP2-EAT.14720 | TT_Task | EMU - Train 05 - Fitting CBS 05 @FS5 (Dates are Indicative) | 31/07/2023 | 01/08/2023 | nan | nan | 0 | TK_NotStart | 1208363553 | 433 | 1208363553_433
MRPP2-EAT.14730 | TT_Task | EMU - Train 05 - Fitting CBS 06 @FS1 (Dates are Indicative) | 05/07/2023 | 12/07/2023 | nan | nan | 0 | TK_NotStart | 1208363553 | 434 | 1208363553_434
MRPP2-EAT.14740 | TT_Task | EMU - Train 05 - Fitting CBS 06 @FS2 (Dates are Indicative) | 13/07/2023 | 20/07/2023 | nan | nan | 0 | TK_NotStart | 1208363553 | 434 | 1208363553_434
MRPP2-EAT.14750 | TT_Task | EMU - Train 05 - Fitting CBS 06 @FS3 ; Dielec (Dates are Indicative) | 21/07/2023 | 28/07/2023 | nan | nan | 0 | TK_NotStart | 1208363553 | 431 | 1208363553_431
MRPP2-EAT.14760 | TT_Task | EMU - Train 05 - Fitting CBS 06 @FS4 (Dates are Indicative) | 31/07/2023 | 07/08/2023 | nan | nan | 0 | TK_NotStart | 1208363553 | 434 | 1208363553_434
MRPP2-EAT.14770 | TT_Task | EMU - Train 05 - Fitting CBS 06 @FS5 (Dates are Indicative) | 08/08/2023 | 09/08/2023 | nan | nan | 0 | TK_NotStart | 1208363553 | 434 | 1208363553_434
MRPP2-EAT.10050 | TT_Task | EMU - Train 06 - Carbodyshell | 21/02/2023 | 28/04/2023 | nan | nan | 0 | TK_NotStart | 1208363553 | 435 | 1208363553_435
MRPP2-EAT.10530 | TT_Task | EMU - Train 06 - Assemble Bogie in Perth | 21/11/2023 | 29/01/2024 | nan | nan | 0 | TK_NotStart | 1208363553 | 426 | 1208363553_426
MRPP2-EAT.10540 | TT_Task | EMU - Train 06 - CBS Transport from Sri City Fty to Bellevue Depot | 01/05/2023 | 04/07/2023 | nan | nan | 0 | TK_NotStart | 1208363553 | 436 | 1208363553_436
MRPP2-EAT.11340 | TT_Task | EMU - Train 06 - Fitting | 05/12/2023 | 12/02/2024 | nan | nan | 0 | TK_NotStart | 1208363553 | 427 | 1208363553_427
MRPP2-EAT.12100 | TT_Task | EMU - Train 06 - Routine Test | 08/01/2024 | 11/03/2024 | nan | nan | 0 | TK_NotStart | 1208363553 | 437 | 1208363553_437
MRPP2-EAT.10060 | TT_Task | EMU - Train 07 - Carbodyshell | 01/05/2023 | 04/07/2023 | nan | nan | 0 | TK_NotStart | 1208363553 | 435 | 1208363553_435
MRPP2-EAT.10550 | TT_Task | EMU - Train 07 - Assemble Bogie in Perth | 05/01/2024 | 11/03/2024 | nan | nan | 0 | TK_NotStart | 1208363553 | 426 | 1208363553_426
MRPP2-EAT.10560 | TT_Task | EMU - Train 07 - CBS Transport from Sri City Fty to Bellevue Depot | 05/07/2023 | 06/09/2023 | nan | nan | 736 | TK_NotStart | 1208363553 | 436 | 1208363553_436
MRPP2-EAT.11360 | TT_Task | EMU - Train 07 - Fitting | 19/01/2024 | 25/03/2024 | nan | nan | 0 | TK_NotStart | 1208363553 | 427 | 1208363553_427
MRPP2-EAT.12110 | TT_Task | EMU - Train 07 - Routine Test | 20/02/2024 | 24/04/2024 | nan | nan | 0 | TK_NotStart | 1208363553 | 437 | 1208363553_437
MRPP2-EAT.10070 | TT_Task | EMU - Train 08 - Carbodyshell | 05/07/2023 | 06/09/2023 | nan | nan | 0 | TK_NotStart | 1208363553 | 435 | 1208363553_435
MRPP2-EAT.10570 | TT_Task | EMU - Train 08 - Assemble Bogie in Perth | 19/02/2024 | 24/04/2024 | nan | nan | 0 | TK_NotStart | 1208363553 | 426 | 1208363553_426
MRPP2-EAT.10580 | TT_Task | EMU - Train 08 - CBS Transport from Sri City Fty to Bellevue Depot | 07/09/2023 | 10/11/2023 | nan | nan | 608 | TK_NotStart | 1208363553 | 436 | 1208363553_436
MRPP2-EAT.11380 | TT_Task | EMU - Train 08 - Fitting | 04/03/2024 | 09/05/2024 | nan | nan | 0 | TK_NotStart | 1208363553 | 427 | 1208363553_427
MRPP2-EAT.12120 | TT_Task | EMU - Train 08 - Routine Test | 02/04/2024 | 07/06/2024 | nan | nan | 0 | TK_NotStart | 1208363553 | 437 | 1208363553_437
MRPP2-EAT.10080 | TT_Task | EMU - Train 09 - Carbodyshell | 07/09/2023 | 06/11/2023 | nan | nan | 0 | TK_NotStart | 1208363553 | 435 | 1208363553_435
MRPP2-EAT.10590 | TT_Task | EMU - Train 09 - Assemble Bogie in Perth | 01/04/2024 | 07/06/2024 | nan | nan | 0 | TK_NotStart | 1208363553 | 426 | 1208363553_426
MRPP2-EAT.10600 | TT_Task | EMU - Train 09 - CBS Transport from Sri City Fty to Bellevue Depot | 07/11/2023 | 12/01/2024 | nan | nan | 512 | TK_NotStart | 1208363553 | 436 | 1208363553_436
MRPP2-EAT.11400 | TT_Task | EMU - Train 09 - Fitting | 17/04/2024 | 21/06/2024 | nan | nan | 0 | TK_NotStart | 1208363553 | 427 | 1208363553_427
MRPP2-EAT.12130 | TT_Task | EMU - Train 09 - Routine Test | 17/05/2024 | 19/07/2024 | nan | nan | 0 | TK_NotStart | 1208363553 | 437 | 1208363553_437
MRPP2-EAT.10090 | TT_Task | EMU - Train 10 - Carbodyshell | 07/11/2023 | 08/01/2024 | nan | nan | 0 | TK_NotStart | 1208363553 | 439 | 1208363553_439
MRPP2-EAT.10610 | TT_Task | EMU - Train 10 - Assemble Bogie in Perth | 16/05/2024 | 19/07/2024 | nan | nan | 0 | TK_NotStart | 1208363553 | 426 | 1208363553_426
MRPP2-EAT.10620 | TT_Task | EMU - Train 10 - CBS Transport from Sri City Fty to Bellevue Depot | 09/01/2024 | 13/03/2024 | nan | nan | 416 | TK_NotStart | 1208363553 | 436 | 1208363553_436
MRPP2-EAT.11420 | TT_Task | EMU - Train 10 - Fitting | 30/05/2024 | 02/08/2024 | nan | nan | 0 | TK_NotStart | 1208363553 | 440 | 1208363553_440
MRPP2-EAT.12140 | TT_Task | EMU - Train 10 - Routine Test | 01/07/2024 | 30/08/2024 | nan | nan | 0 | TK_NotStart | 1208363553 | 441 | 1208363553_441
MRPP2-EAT.10100 | TT_Task | EMU - Train 11 - Carbodyshell | 09/01/2024 | 07/03/2024 | nan | nan | 0 | TK_NotStart | 1208363553 | 439 | 1208363553_439
MRPP2-EAT.10630 | TT_Task | EMU - Train 11 - Assemble Bogie in Perth | 28/06/2024 | 30/08/2024 | nan | nan | 0 | TK_NotStart | 1208363553 | 426 | 1208363553_426
MRPP2-EAT.10640 | TT_Task | EMU - Train 11 - CBS Transport from Sri City Fty to Bellevue Depot | 08/03/2024 | 15/05/2024 | nan | nan | 320 | TK_NotStart | 1208363553 | 436 | 1208363553_436
MRPP2-EAT.11440 | TT_Task | EMU - Train 11 - Fitting | 12/07/2024 | 13/09/2024 | nan | nan | 0 | TK_NotStart | 1208363553 | 440 | 1208363553_440
MRPP2-EAT.12150 | TT_Task | EMU - Train 11 - Routine Test | 12/08/2024 | 14/10/2024 | nan | nan | 0 | TK_NotStart | 1208363553 | 441 | 1208363553_441
MRPP2-EAT.10110 | TT_Task | EMU - Train 12 - Carbodyshell | 08/03/2024 | 09/05/2024 | nan | nan | 0 | TK_NotStart | 1208363553 | 439 | 1208363553_439
MRPP2-EAT.10650 | TT_Task | EMU - Train 12 - Assemble Bogie in Perth | 09/08/2024 | 14/10/2024 | nan | nan | 0 | TK_NotStart | 1208363553 | 426 | 1208363553_426
MRPP2-EAT.10660 | TT_Task | EMU - Train 12 - CBS Transport from Sri City Fty to Bellevue Depot | 10/05/2024 | 15/07/2024 | nan | nan | 224 | TK_NotStart | 1208363553 | 436 | 1208363553_436
MRPP2-EAT.11460 | TT_Task | EMU - Train 12 - Fitting | 23/08/2024 | 28/10/2024 | nan | nan | 0 | TK_NotStart | 1208363553 | 440 | 1208363553_440
MRPP2-EAT.12160 | TT_Task | EMU - Train 12 - Routine Test | 23/09/2024 | 25/11/2024 | nan | nan | 0 | TK_NotStart | 1208363553 | 441 | 1208363553_441
MRPP2-EAT.10120 | TT_Task | EMU - Train 13 - Carbodyshell | 10/05/2024 | 09/07/2024 | nan | nan | 0 | TK_NotStart | 1208363553 | 439 | 1208363553_439
MRPP2-EAT.10670 | TT_Task | EMU - Train 13 - Assemble Bogie in Perth | 20/09/2024 | 25/11/2024 | nan | nan | 0 | TK_NotStart | 1208363553 | 426 | 1208363553_426
MRPP2-EAT.10680 | TT_Task | EMU - Train 13 - CBS Transport from Sri City Fty to Bellevue Depot | 10/07/2024 | 11/09/2024 | nan | nan | 128 | TK_NotStart | 1208363553 | 436 | 1208363553_436
MRPP2-EAT.11480 | TT_Task | EMU - Train 13 - Fitting | 07/10/2024 | 09/12/2024 | nan | nan | 0 | TK_NotStart | 1208363553 | 440 | 1208363553_440
MRPP2-EAT.12170 | TT_Task | EMU - Train 13 - Routine Test | 05/11/2024 | 09/01/2025 | nan | nan | 0 | TK_NotStart | 1208363553 | 441 | 1208363553_441
MRPP2-EAT.10130 | TT_Task | EMU - Train 14 - Carbodyshell | 10/07/2024 | 05/09/2024 | nan | nan | 0 | TK_NotStart | 1208363553 | 439 | 1208363553_439
MRPP2-EAT.10690 | TT_Task | EMU - Train 14 - Assemble Bogie in Perth | 04/11/2024 | 09/01/2025 | nan | nan | 0 | TK_NotStart | 1208363553 | 426 | 1208363553_426
MRPP2-EAT.10700 | TT_Task | EMU - Train 14 - CBS Transport from Sri City Fty to Bellevue Depot | 08/08/2024 | 11/10/2024 | nan | nan | 200 | TK_NotStart | 1208363553 | 436 | 1208363553_436
MRPP2-EAT.11500 | TT_Task | EMU - Train 14 - Fitting | 18/11/2024 | 23/01/2025 | nan | nan | 0 | TK_NotStart | 1208363553 | 440 | 1208363553_440
MRPP2-EAT.12180 | TT_Task | EMU - Train 14 - Routine Test | 17/12/2024 | 21/02/2025 | nan | nan | 0 | TK_NotStart | 1208363553 | 441 | 1208363553_441
MRPP2-EAT.10140 | TT_Task | EMU - Train 15 - Carbodyshell | 06/09/2024 | 05/11/2024 | nan | nan | 0 | TK_NotStart | 1208363553 | 439 | 1208363553_439
MRPP2-EAT.10710 | TT_Task | EMU - Train 15 - Assemble Bogie in Perth | 24/12/2024 | 17/03/2025 | nan | nan | 0 | TK_NotStart | 1208363553 | 426 | 1208363553_426
MRPP2-EAT.10720 | TT_Task | EMU - Train 15 - CBS Transport from Sri City Fty to Bellevue Depot | 08/10/2024 | 10/12/2024 | nan | nan | 152 | TK_NotStart | 1208363553 | 436 | 1208363553_436
MRPP2-EAT.11520 | TT_Task | EMU - Train 15 - Fitting | 10/01/2025 | 31/03/2025 | nan | nan | 0 | TK_NotStart | 1208363553 | 440 | 1208363553_440
MRPP2-EAT.12190 | TT_Task | EMU - Train 15 - Routine Test | 18/02/2025 | 01/05/2025 | nan | nan | 0 | TK_NotStart | 1208363553 | 441 | 1208363553_441
MRPP2-EAT.10150 | TT_Task | EMU - Train 16 - Carbodyshell | 06/11/2024 | 07/01/2025 | nan | nan | 0 | TK_NotStart | 1208363553 | 439 | 1208363553_439
MRPP2-EAT.10730 | TT_Task | EMU - Train 16 - Assemble Bogie in Perth | 18/02/2025 | 09/05/2025 | nan | nan | 0 | TK_NotStart | 1208363553 | 426 | 1208363553_426
MRPP2-EAT.10740 | TT_Task | EMU - Train 16 - CBS Transport from Sri City Fty to Bellevue Depot | 04/12/2024 | 12/02/2025 | nan | nan | 108 | TK_NotStart | 1208363553 | 436 | 1208363553_436
MRPP2-EAT.11540 | TT_Task | EMU - Train 16 - Fitting | 04/03/2025 | 23/05/2025 | nan | nan | 0 | TK_NotStart | 1208363553 | 440 | 1208363553_440
MRPP2-EAT.12200 | TT_Task | EMU - Train 16 - Routine Test | 09/04/2025 | 23/06/2025 | nan | nan | 0 | TK_NotStart | 1208363553 | 441 | 1208363553_441
MRPP2-EAT.10160 | TT_Task | EMU - Train 17 - Carbodyshell | 07/01/2025 | 05/03/2025 | nan | nan | 0 | TK_NotStart | 1208363553 | 439 | 1208363553_439
MRPP2-EAT.10750 | TT_Task | EMU - Train 17 - Assemble Bogie in Perth | 09/04/2025 | 14/07/2025 | nan | nan | 0 | TK_NotStart | 1208363553 | 426 | 1208363553_426
MRPP2-EAT.10760 | TT_Task | EMU - Train 17 - CBS Transport from Sri City Fty to Bellevue Depot | 04/02/2025 | 09/04/2025 | nan | nan | 76 | TK_NotStart | 1208363553 | 436 | 1208363553_436
MRPP2-EAT.11560 | TT_Task | EMU - Train 17 - Fitting | 28/04/2025 | 28/07/2025 | nan | nan | 0 | TK_NotStart | 1208363553 | 440 | 1208363553_440
MRPP2-EAT.12210 | TT_Task | EMU - Train 17 - Routine Test | 10/06/2025 | 25/08/2025 | nan | nan | 0 | TK_NotStart | 1208363553 | 441 | 1208363553_441
MRPP2-EAT.10170 | TT_Task | EMU - Train 18 - Carbodyshell | 05/03/2025 | 22/04/2025 | nan | nan | 0 | TK_NotStart | 1208363553 | 439 | 1208363553_439
MRPP2-EAT.10770 | TT_Task | EMU - Train 18 - Assemble Bogie in Perth | 12/06/2025 | 10/09/2025 | nan | nan | 0 | TK_NotStart | 1208363553 | 426 | 1208363553_426
MRPP2-EAT.10780 | TT_Task | EMU - Train 18 - CBS Transport from Sri City Fty to Bellevue Depot | 20/03/2025 | 28/05/2025 | nan | nan | 156 | TK_NotStart | 1208363553 | 436 | 1208363553_436
MRPP2-EAT.11580 | TT_Task | EMU - Train 18 - Fitting | 26/06/2025 | 24/09/2025 | nan | nan | 0 | TK_NotStart | 1208363553 | 442 | 1208363553_442
MRPP2-EAT.12220 | TT_Task | EMU - Train 18 - Routine Test | 07/08/2025 | 23/10/2025 | nan | nan | 0 | TK_NotStart | 1208363553 | 443 | 1208363553_443
MRPP2-EAT.10180 | TT_Task | EMU - Train 19 - Carbodyshell | 22/04/2025 | 12/06/2025 | nan | nan | 0 | TK_NotStart | 1208363553 | 439 | 1208363553_439
MRPP2-EAT.10790 | TT_Task | EMU - Train 19 - Assemble Bogie in Perth | 11/08/2025 | 28/10/2025 | nan | nan | 0 | TK_NotStart | 1208363553 | 426 | 1208363553_426
MRPP2-EAT.10800 | TT_Task | EMU - Train 19 - CBS Transport from Sri City Fty to Bellevue Depot | 13/05/2025 | 17/07/2025 | nan | nan | 212 | TK_NotStart | 1208363553 | 436 | 1208363553_436
MRPP2-EAT.11600 | TT_Task | EMU - Train 19 - Fitting | 25/08/2025 | 11/11/2025 | nan | nan | 0 | TK_NotStart | 1208363553 | 442 | 1208363553_442
MRPP2-EAT.12230 | TT_Task | EMU - Train 19 - Routine Test | 01/10/2025 | 09/12/2025 | nan | nan | 0 | TK_NotStart | 1208363553 | 443 | 1208363553_443
MRPP2-EAT.10190 | TT_Task | EMU - Train 20 - Carbodyshell | 12/06/2025 | 07/08/2025 | nan | nan | 0 | TK_NotStart | 1208363553 | 439 | 1208363553_439
MRPP2-EAT.10810 | TT_Task | EMU - Train 20 - Assemble Bogie in Perth | 01/10/2025 | 17/12/2025 | nan | nan | 0 | TK_NotStart | 1208363553 | 426 | 1208363553_426
MRPP2-EAT.10820 | TT_Task | EMU - Train 20 - CBS Transport from Sri City Fty to Bellevue Depot | 09/07/2025 | 11/09/2025 | nan | nan | 180 | TK_NotStart | 1208363553 | 436 | 1208363553_436
MRPP2-EAT.11620 | TT_Task | EMU - Train 20 - Fitting | 15/10/2025 | 05/01/2026 | nan | nan | 0 | TK_NotStart | 1208363553 | 442 | 1208363553_442
MRPP2-EAT.12240 | TT_Task | EMU - Train 20 - Routine Test | 20/11/2025 | 03/02/2026 | nan | nan | 0 | TK_NotStart | 1208363553 | 443 | 1208363553_443
MRPP2-EAT.10200 | TT_Task | EMU - Train 21 - Carbodyshell | 07/08/2025 | 06/10/2025 | nan | nan | 0 | TK_NotStart | 1208363553 | 439 | 1208363553_439
MRPP2-EAT.10830 | TT_Task | EMU - Train 21 - Assemble Bogie in Perth | 20/11/2025 | 11/02/2026 | nan | nan | 0 | TK_NotStart | 1208363553 | 426 | 1208363553_426
MRPP2-EAT.10840 | TT_Task | EMU - Train 21 - CBS Transport from Sri City Fty to Bellevue Depot | 05/09/2025 | 10/11/2025 | nan | nan | 136 | TK_NotStart | 1208363553 | 436 | 1208363553_436
MRPP2-EAT.11640 | TT_Task | EMU - Train 21 - Fitting | 04/12/2025 | 25/02/2026 | nan | nan | 0 | TK_NotStart | 1208363553 | 442 | 1208363553_442
MRPP2-EAT.12250 | TT_Task | EMU - Train 21 - Routine Test | 14/01/2026 | 25/03/2026 | nan | nan | 0 | TK_NotStart | 1208363553 | 443 | 1208363553_443
MRPP2-EAT.10210 | TT_Task | EMU - Train 22 - Carbodyshell | 07/10/2025 | 03/12/2025 | nan | nan | 0 | TK_NotStart | 1208363553 | 439 | 1208363553_439
MRPP2-EAT.10850 | TT_Task | EMU - Train 22 - Assemble Bogie in Perth | 14/01/2026 | 02/04/2026 | nan | nan | 0 | TK_NotStart | 1208363553 | 426 | 1208363553_426
MRPP2-EAT.10860 | TT_Task | EMU - Train 22 - CBS Transport from Sri City Fty to Bellevue Depot | 04/11/2025 | 12/01/2026 | nan | nan | 92 | TK_NotStart | 1208363553 | 436 | 1208363553_436
MRPP2-EAT.11660 | TT_Task | EMU - Train 22 - Fitting | 29/01/2026 | 20/04/2026 | nan | nan | 0 | TK_NotStart | 1208363553 | 442 | 1208363553_442
MRPP2-EAT.12260 | TT_Task | EMU - Train 22 - Routine Test | 06/03/2026 | 19/05/2026 | nan | nan | 0 | TK_NotStart | 1208363553 | 443 | 1208363553_443
MRPP2-EAT.10220 | TT_Task | EMU - Train 23 - Carbodyshell | 03/12/2025 | 30/01/2026 | nan | nan | 0 | TK_NotStart | 1208363553 | 439 | 1208363553_439
MRPP2-EAT.10870 | TT_Task | EMU - Train 23 - Assemble Bogie in Perth | 06/03/2026 | 27/05/2026 | nan | nan | 0 | TK_NotStart | 1208363553 | 426 | 1208363553_426
MRPP2-EAT.10880 | TT_Task | EMU - Train 23 - CBS Transport from Sri City Fty to Bellevue Depot | 30/12/2025 | 06/03/2026 | nan | nan | 76 | TK_NotStart | 1208363553 | 436 | 1208363553_436
MRPP2-EAT.11680 | TT_Task | EMU - Train 23 - Fitting | 20/03/2026 | 11/06/2026 | nan | nan | 0 | TK_NotStart | 1208363553 | 442 | 1208363553_442
MRPP2-EAT.12270 | TT_Task | EMU - Train 23 - Routine Test | 30/04/2026 | 09/07/2026 | nan | nan | 0 | TK_NotStart | 1208363553 | 443 | 1208363553_443
MRPP2-EAT.10230 | TT_Task | EMU - Train 24 - Carbodyshell | 30/01/2026 | 30/03/2026 | nan | nan | 0 | TK_NotStart | 1208363553 | 439 | 1208363553_439
MRPP2-EAT.10890 | TT_Task | EMU - Train 24 - Assemble Bogie in Perth | 30/04/2026 | 17/07/2026 | nan | nan | 0 | TK_NotStart | 1208363553 | 426 | 1208363553_426
MRPP2-EAT.10900 | TT_Task | EMU - Train 24 - CBS Transport from Sri City Fty to Bellevue Depot | 02/03/2026 | 07/05/2026 | nan | nan | 32 | TK_NotStart | 1208363553 | 436 | 1208363553_436
MRPP2-EAT.11700 | TT_Task | EMU - Train 24 - Fitting | 14/05/2026 | 31/07/2026 | nan | nan | 0 | TK_NotStart | 1208363553 | 442 | 1208363553_442
MRPP2-EAT.12280 | TT_Task | EMU - Train 24 - Routine Test | 22/06/2026 | 28/08/2026 | nan | nan | 0 | TK_NotStart | 1208363553 | 443 | 1208363553_443
MRPP2-EAT.10240 | TT_Task | EMU - Train 25 - Carbodyshell | 31/03/2026 | 28/05/2026 | nan | nan | 0 | TK_NotStart | 1208363553 | 439 | 1208363553_439
MRPP2-EAT.10910 | TT_Task | EMU - Train 25 - Assemble Bogie in Perth | 22/06/2026 | 18/09/2026 | nan | nan | 0 | TK_NotStart | 1208363553 | 426 | 1208363553_426
MRPP2-EAT.10920 | TT_Task | EMU - Train 25 - CBS Transport from Sri City Fty to Bellevue Depot | 30/04/2026 | 03/07/2026 | nan | nan | 0 | TK_NotStart | 1208363553 | 436 | 1208363553_436
MRPP2-EAT.11720 | TT_Task | EMU - Train 25 - Fitting | 06/07/2026 | 05/10/2026 | nan | nan | 0 | TK_NotStart | 1208363553 | 442 | 1208363553_442
MRPP2-EAT.12290 | TT_Task | EMU - Train 25 - Routine Test | 17/08/2026 | 02/11/2026 | nan | nan | 0 | TK_NotStart | 1208363553 | 443 | 1208363553_443
MRPP2-EAT.10250 | TT_Task | EMU - Train 26 - Carbodyshell | 29/05/2026 | 28/07/2026 | nan | nan | 0 | TK_NotStart | 1208363553 | 444 | 1208363553_444
MRPP2-EAT.10930 | TT_Task | EMU - Train 26 - Assemble Bogie in Perth | 19/08/2026 | 18/11/2026 | nan | nan | 0 | TK_NotStart | 1208363553 | 426 | 1208363553_426
MRPP2-EAT.10940 | TT_Task | EMU - Train 26 - CBS Transport from Sri City Fty to Bellevue Depot | 29/06/2026 | 01/09/2026 | nan | nan | 4 | TK_NotStart | 1208363553 | 436 | 1208363553_436
MRPP2-EAT.11740 | TT_Task | EMU - Train 26 - Fitting | 02/09/2026 | 02/12/2026 | nan | nan | 0 | TK_NotStart | 1208363553 | 445 | 1208363553_445
MRPP2-EAT.12300 | TT_Task | EMU - Train 26 - Routine Test | 15/10/2026 | 04/01/2027 | nan | nan | 0 | TK_NotStart | 1208363553 | 446 | 1208363553_446
MRPP2-EAT.10260 | TT_Task | EMU - Train 27 - Carbodyshell | 28/07/2026 | 22/09/2026 | nan | nan | 0 | TK_NotStart | 1208363553 | 444 | 1208363553_444
MRPP2-EAT.10950 | TT_Task | EMU - Train 27 - Assemble Bogie in Perth | 19/10/2026 | 20/01/2027 | nan | nan | 0 | TK_NotStart | 1208363553 | 426 | 1208363553_426
MRPP2-EAT.10960 | TT_Task | EMU - Train 27 - CBS Transport from Sri City Fty to Bellevue Depot | 24/08/2026 | 28/10/2026 | nan | nan | 20 | TK_NotStart | 1208363553 | 436 | 1208363553_436
MRPP2-EAT.11760 | TT_Task | EMU - Train 27 - Fitting | 02/11/2026 | 04/02/2027 | nan | nan | 0 | TK_NotStart | 1208363553 | 445 | 1208363553_445
MRPP2-EAT.12310 | TT_Task | EMU - Train 27 - Routine Test | 14/12/2026 | 04/03/2027 | nan | nan | 0 | TK_NotStart | 1208363553 | 446 | 1208363553_446
MRPP2-EAT.10270 | TT_Task | EMU - Train 28 - Carbodyshell | 22/09/2026 | 18/11/2026 | nan | nan | 0 | TK_NotStart | 1208363553 | 444 | 1208363553_444
MRPP2-EAT.10970 | TT_Task | EMU - Train 28 - Assemble Bogie in Perth | 16/12/2026 | 22/03/2027 | nan | nan | 0 | TK_NotStart | 1208363553 | 426 | 1208363553_426
MRPP2-EAT.10980 | TT_Task | EMU - Train 28 - CBS Transport from Sri City Fty to Bellevue Depot | 19/10/2026 | 22/12/2026 | nan | nan | 44 | TK_NotStart | 1208363553 | 436 | 1208363553_436
MRPP2-EAT.11780 | TT_Task | EMU - Train 28 - Fitting | 04/01/2027 | 05/04/2027 | nan | nan | 0 | TK_NotStart | 1208363553 | 445 | 1208363553_445
MRPP2-EAT.12320 | TT_Task | EMU - Train 28 - Routine Test | 16/02/2027 | 06/05/2027 | nan | nan | 0 | TK_NotStart | 1208363553 | 446 | 1208363553_446
MRPP2-EAT.10280 | TT_Task | EMU - Train 29 - Carbodyshell | 18/11/2026 | 18/01/2027 | nan | nan | 0 | TK_NotStart | 1208363553 | 444 | 1208363553_444
MRPP2-EAT.10990 | TT_Task | EMU - Train 29 - Assemble Bogie in Perth | 18/02/2027 | 24/05/2027 | nan | nan | 0 | TK_NotStart | 1208363553 | 426 | 1208363553_426
MRPP2-EAT.11000 | TT_Task | EMU - Train 29 - CBS Transport from Sri City Fty to Bellevue Depot | 08/12/2026 | 16/02/2027 | nan | nan | 92 | TK_NotStart | 1208363553 | 436 | 1208363553_436
MRPP2-EAT.11800 | TT_Task | EMU - Train 29 - Fitting | 04/03/2027 | 08/06/2027 | nan | nan | 0 | TK_NotStart | 1208363553 | 445 | 1208363553_445
MRPP2-EAT.12330 | TT_Task | EMU - Train 29 - Routine Test | 19/04/2027 | 06/07/2027 | nan | nan | 0 | TK_NotStart | 1208363553 | 446 | 1208363553_446
MRPP2-EAT.10290 | TT_Task | EMU - Train 30 - Carbodyshell | 18/01/2027 | 17/03/2027 | nan | nan | 0 | TK_NotStart | 1208363553 | 444 | 1208363553_444
MRPP2-EAT.11010 | TT_Task | EMU - Train 30 - Assemble Bogie in Perth | 21/04/2027 | 22/07/2027 | nan | nan | 0 | TK_NotStart | 1208363553 | 426 | 1208363553_426
MRPP2-EAT.11020 | TT_Task | EMU - Train 30 - CBS Transport from Sri City Fty to Bellevue Depot | 09/02/2027 | 16/04/2027 | nan | nan | 100 | TK_NotStart | 1208363553 | 436 | 1208363553_436
MRPP2-EAT.11820 | TT_Task | EMU - Train 30 - Fitting | 06/05/2027 | 05/08/2027 | nan | nan | 0 | TK_NotStart | 1208363553 | 445 | 1208363553_445
MRPP2-EAT.12340 | TT_Task | EMU - Train 30 - Routine Test | 18/06/2027 | 02/09/2027 | nan | nan | 0 | TK_NotStart | 1208363553 | 446 | 1208363553_446
MRPP2-EAT.10300 | TT_Task | EMU - Train 31 - Carbodyshell | 17/03/2027 | 17/05/2027 | nan | nan | 0 | TK_NotStart | 1208363553 | 444 | 1208363553_444
MRPP2-EAT.11030 | TT_Task | EMU - Train 31 - Assemble Bogie in Perth | 22/06/2027 | 20/09/2027 | nan | nan | 0 | TK_NotStart | 1208363553 | 426 | 1208363553_426
MRPP2-EAT.11040 | TT_Task | EMU - Train 31 - CBS Transport from Sri City Fty to Bellevue Depot | 06/04/2027 | 15/06/2027 | nan | nan | 116 | TK_NotStart | 1208363553 | 436 | 1208363553_436
MRPP2-EAT.11840 | TT_Task | EMU - Train 31 - Fitting | 06/07/2027 | 05/10/2027 | nan | nan | 0 | TK_NotStart | 1208363553 | 447 | 1208363553_447
MRPP2-EAT.12350 | TT_Task | EMU - Train 31 - Routine Test | 17/08/2027 | 02/11/2027 | nan | nan | 0 | TK_NotStart | 1208363553 | 446 | 1208363553_446
MRPP2-EAT.10310 | TT_Task | EMU - Train 32 - Carbodyshell | 17/05/2027 | 13/07/2027 | nan | nan | 0 | TK_NotStart | 1208363553 | 444 | 1208363553_444
MRPP2-EAT.11050 | TT_Task | EMU - Train 32 - Assemble Bogie in Perth | 19/08/2027 | 05/11/2027 | nan | nan | 16 | TK_NotStart | 1208363553 | 426 | 1208363553_426
MRPP2-EAT.11060 | TT_Task | EMU - Train 32 - CBS Transport from Sri City Fty to Bellevue Depot | 04/06/2027 | 10/08/2027 | nan | nan | 132 | TK_NotStart | 1208363553 | 436 | 1208363553_436
MRPP2-EAT.11860 | TT_Task | EMU - Train 32 - Fitting | 02/09/2027 | 19/11/2027 | nan | nan | 0 | TK_NotStart | 1208363553 | 447 | 1208363553_447
MRPP2-EAT.12360 | TT_Task | EMU - Train 32 - Routine Test | 11/10/2027 | 17/12/2027 | nan | nan | 0 | TK_NotStart | 1208363553 | 446 | 1208363553_446
MRPP2-EAT.10320 | TT_Task | EMU - Train 33 - Carbodyshell | 13/07/2027 | 07/09/2027 | nan | nan | 0 | TK_NotStart | 1208363553 | 444 | 1208363553_444
MRPP2-EAT.11070 | TT_Task | EMU - Train 33 - Assemble Bogie in Perth | 11/10/2027 | 28/12/2027 | nan | nan | 0 | TK_NotStart | 1208363553 | 426 | 1208363553_426
MRPP2-EAT.11080 | TT_Task | EMU - Train 33 - CBS Transport from Sri City Fty to Bellevue Depot | 02/08/2027 | 06/10/2027 | nan | nan | 100 | TK_NotStart | 1208363553 | 436 | 1208363553_436
MRPP2-EAT.11880 | TT_Task | EMU - Train 33 - Fitting | 25/10/2027 | 11/01/2028 | nan | nan | 0 | TK_NotStart | 1208363553 | 447 | 1208363553_447
MRPP2-EAT.12370 | TT_Task | EMU - Train 33 - Routine Test | 30/11/2027 | 09/02/2028 | nan | nan | 0 | TK_NotStart | 1208363553 | 446 | 1208363553_446
MRPP2-EAT.10330 | TT_Task | EMU - Train 34 - Carbodyshell | 07/09/2027 | 03/11/2027 | nan | nan | 0 | TK_NotStart | 1208363553 | 444 | 1208363553_444
MRPP2-EAT.11090 | TT_Task | EMU - Train 34 - Assemble Bogie in Perth | 30/11/2027 | 17/02/2028 | nan | nan | 0 | TK_NotStart | 1208363553 | 426 | 1208363553_426
MRPP2-EAT.11100 | TT_Task | EMU - Train 34 - CBS Transport from Sri City Fty to Bellevue Depot | 28/09/2027 | 01/12/2027 | nan | nan | 68 | TK_NotStart | 1208363553 | 436 | 1208363553_436
MRPP2-EAT.11900 | TT_Task | EMU - Train 34 - Fitting | 14/12/2027 | 02/03/2028 | nan | nan | 0 | TK_NotStart | 1208363553 | 447 | 1208363553_447
MRPP2-EAT.12380 | TT_Task | EMU - Train 34 - Routine Test | 20/01/2028 | 30/03/2028 | nan | nan | 0 | TK_NotStart | 1208363553 | 446 | 1208363553_446
MRPP2-EAT.10340 | TT_Task | EMU - Train 35 - Carbodyshell | 03/11/2027 | 30/12/2027 | nan | nan | 0 | TK_NotStart | 1208363553 | 444 | 1208363553_444
MRPP2-EAT.11110 | TT_Task | EMU - Train 35 - Assemble Bogie in Perth | 20/01/2028 | 11/04/2028 | nan | nan | 0 | TK_NotStart | 1208363553 | 426 | 1208363553_426
MRPP2-EAT.11120 | TT_Task | EMU - Train 35 - CBS Transport from Sri City Fty to Bellevue Depot | 23/11/2027 | 28/01/2028 | nan | nan | 36 | TK_NotStart | 1208363553 | 436 | 1208363553_436
MRPP2-EAT.11920 | TT_Task | EMU - Train 35 - Fitting | 04/02/2028 | 26/04/2028 | nan | nan | 0 | TK_NotStart | 1208363553 | 447 | 1208363553_447
MRPP2-EAT.12390 | TT_Task | EMU - Train 35 - Routine Test | 13/03/2028 | 24/05/2028 | nan | nan | 0 | TK_NotStart | 1208363553 | 446 | 1208363553_446
MRPP2-EAT.10350 | TT_Task | EMU - Train 36 - Carbodyshell | 30/12/2027 | 25/02/2028 | nan | nan | 0 | TK_NotStart | 1208363553 | 444 | 1208363553_444
MRPP2-EAT.11130 | TT_Task | EMU - Train 36 - Assemble Bogie in Perth | 13/03/2028 | 01/06/2028 | nan | nan | 0 | TK_NotStart | 1208363553 | 426 | 1208363553_426
MRPP2-EAT.11140 | TT_Task | EMU - Train 36 - CBS Transport from Sri City Fty to Bellevue Depot | 19/01/2028 | 24/03/2028 | nan | nan | 4 | TK_NotStart | 1208363553 | 436 | 1208363553_436
MRPP2-EAT.11940 | TT_Task | EMU - Train 36 - Fitting | 27/03/2028 | 16/06/2028 | nan | nan | 0 | TK_NotStart | 1208363553 | 447 | 1208363553_447
MRPP2-EAT.12400 | TT_Task | EMU - Train 36 - Routine Test | 05/05/2028 | 14/07/2028 | nan | nan | 0 | TK_NotStart | 1208363553 | 446 | 1208363553_446
MRPP2-EAT.10360 | TT_Task | EMU - Train 37 - Carbodyshell | 25/02/2028 | 26/04/2028 | nan | nan | 0 | TK_NotStart | 1208363553 | 444 | 1208363553_444
MRPP2-EAT.11150 | TT_Task | EMU - Train 37 - Assemble Bogie in Perth | 15/05/2028 | 14/08/2028 | nan | nan | 0 | TK_NotStart | 1208363553 | 426 | 1208363553_426
MRPP2-EAT.11160 | TT_Task | EMU - Train 37 - CBS Transport from Sri City Fty to Bellevue Depot | 16/03/2028 | 24/05/2028 | nan | nan | 20 | TK_NotStart | 1208363553 | 436 | 1208363553_436
MRPP2-EAT.11960 | TT_Task | EMU - Train 37 - Fitting | 29/05/2028 | 28/08/2028 | nan | nan | 0 | TK_NotStart | 1208363553 | 447 | 1208363553_447
MRPP2-EAT.12410 | TT_Task | EMU - Train 37 - Routine Test | 11/07/2028 | 26/09/2028 | nan | nan | 0 | TK_NotStart | 1208363553 | 446 | 1208363553_446
MRPP2-EAT.10370 | TT_Task | EMU - Train 38 - Carbodyshell | 26/04/2028 | 22/06/2028 | nan | nan | 0 | TK_NotStart | 1208363553 | 444 | 1208363553_444
MRPP2-EAT.11170 | TT_Task | EMU - Train 38 - Assemble Bogie in Perth | 13/07/2028 | 12/10/2028 | nan | nan | 0 | TK_NotStart | 1208363553 | 426 | 1208363553_426
MRPP2-EAT.11180 | TT_Task | EMU - Train 38 - CBS Transport from Sri City Fty to Bellevue Depot | 16/05/2028 | 20/07/2028 | nan | nan | 36 | TK_NotStart | 1208363553 | 436 | 1208363553_436
MRPP2-EAT.11980 | TT_Task | EMU - Train 38 - Fitting | 27/07/2028 | 26/10/2028 | nan | nan | 0 | TK_NotStart | 1208363553 | 447 | 1208363553_447
MRPP2-EAT.12420 | TT_Task | EMU - Train 38 - Routine Test | 07/09/2028 | 23/11/2028 | nan | nan | 0 | TK_NotStart | 1208363553 | 446 | 1208363553_446
MRPP2-EAT.10380 | TT_Task | EMU - Train 39 - Carbodyshell | 14/06/2028 | 09/08/2028 | nan | nan | 0 | TK_NotStart | 1208363553 | 444 | 1208363553_444
MRPP2-EAT.11190 | TT_Task | EMU - Train 39 - Assemble Bogie in Perth | 11/09/2028 | 11/12/2028 | nan | nan | 0 | TK_NotStart | 1208363553 | 426 | 1208363553_426
MRPP2-EAT.11200 | TT_Task | EMU - Train 39 - CBS Transport from Sri City Fty to Bellevue Depot | 12/07/2028 | 06/09/2028 | nan | nan | 100 | TK_NotStart | 1208363553 | 436 | 1208363553_436
MRPP2-EAT.12000 | TT_Task | EMU - Train 39 - Fitting | 26/09/2028 | 27/12/2028 | nan | nan | 0 | TK_NotStart | 1208363553 | 447 | 1208363553_447
MRPP2-EAT.12430 | TT_Task | EMU - Train 39 - Routine Test | 07/11/2028 | 25/01/2029 | nan | nan | 0 | TK_NotStart | 1208363553 | 446 | 1208363553_446
MRPP2-EAT.10390 | TT_Task | EMU - Train 40 - Carbodyshell | 09/08/2028 | 05/10/2028 | nan | nan | 0 | TK_NotStart | 1208363553 | 444 | 1208363553_444
MRPP2-EAT.11210 | TT_Task | EMU - Train 40 - Assemble Bogie in Perth | 09/11/2028 | 13/02/2029 | nan | nan | 0 | TK_NotStart | 1208363553 | 426 | 1208363553_426
MRPP2-EAT.11220 | TT_Task | EMU - Train 40 - CBS Transport from Sri City Fty to Bellevue Depot | 06/09/2028 | 02/11/2028 | nan | nan | 116 | TK_NotStart | 1208363553 | 436 | 1208363553_436
MRPP2-EAT.12020 | TT_Task | EMU - Train 40 - Fitting | 23/11/2028 | 27/02/2029 | nan | nan | 0 | TK_NotStart | 1208363553 | 447 | 1208363553_447
MRPP2-EAT.12440 | TT_Task | EMU - Train 40 - Routine Test | 09/01/2029 | 27/03/2029 | nan | nan | 0 | TK_NotStart | 1208363553 | 446 | 1208363553_446
MRPP2-EAT.10400 | TT_Task | EMU - Train 41 - Carbodyshell | 05/10/2028 | 23/11/2028 | nan | nan | 0 | TK_NotStart | 1208363553 | 444 | 1208363553_444
MRPP2-EAT.11230 | TT_Task | EMU - Train 41 - Assemble Bogie in Perth | 11/01/2029 | 12/04/2029 | nan | nan | 0 | TK_NotStart | 1208363553 | 426 | 1208363553_426
MRPP2-EAT.11240 | TT_Task | EMU - Train 41 - CBS Transport from Sri City Fty to Bellevue Depot | 26/10/2028 | 21/12/2028 | nan | nan | 172 | TK_NotStart | 1208363553 | 436 | 1208363553_436
MRPP2-EAT.12040 | TT_Task | EMU - Train 41 - Fitting | 25/01/2029 | 01/05/2029 | nan | nan | 0 | TK_NotStart | 1208363553 | 447 | 1208363553_447
MRPP2-EAT.12450 | TT_Task | EMU - Train 41 - Routine Test | 09/03/2029 | 29/05/2029 | nan | nan | 0 | TK_NotStart | 1208363553 | 446 | 1208363553_446
MRPP2-GEN.11430 | TT_Task | Mock-up Manufacturing, Assembly ; Final Fit-out by RPC (Cab) | 29/06/2020 | 30/04/2021 | 29/06/2020 | 30/04/2021 | 0 | TK_Complete | 1208363553 | 448 | 1208363553_448
MRPP2-GEN.11450 | TT_Task | Mock-up Delivery to Perth (Cab) | 03/05/2021 | 10/05/2021 | 03/05/2021 | 10/05/2021 | 0 | TK_Complete | 1208363553 | 449 | 1208363553_449
MRPP2-EPA.10000 | TT_Task | EMU - Train 01 Preliminary Acceptance Test ; PTA Certification | 20/06/2022 | 05/08/2022 | nan | nan | 0 | TK_NotStart | 1208363553 | 450 | 1208363553_450
MRPP2-EPA.10010 | TT_Task | EMU - Train 02 Preliminary Acceptance Test ; PTA Certification | 12/09/2022 | 06/10/2022 | nan | nan | 0 | TK_NotStart | 1208363553 | 450 | 1208363553_450
MRPP2-EPA.10020 | TT_Task | EMU - Train 03 Preliminary Acceptance Test ; PTA Certification | 12/04/2023 | 10/05/2023 | nan | nan | 0 | TK_NotStart | 1208363553 | 450 | 1208363553_450
MRPP2-EPA.10030 | TT_Task | EMU - Train 04 Preliminary Acceptance Test ; PTA Certification | 14/07/2023 | 10/08/2023 | nan | nan | 0 | TK_NotStart | 1208363553 | 450 | 1208363553_450
MRPP2-EPA.10040 | TT_Task | EMU - Train 05 Preliminary Acceptance Test ; PTA Certification | 04/08/2023 | 04/09/2023 | nan | nan | 0 | TK_NotStart | 1208363553 | 450 | 1208363553_450
MRPP2-EPA.10050 | TT_Task | EMU - Train 06 Preliminary Acceptance Test ; PTA Certification | 14/02/2024 | 02/04/2024 | nan | nan | 0 | TK_NotStart | 1208363553 | 450 | 1208363553_450
MRPP2-EPA.10060 | TT_Task | EMU - Train 07 Preliminary Acceptance Test ; PTA Certification | 01/04/2024 | 22/05/2024 | nan | nan | 0 | TK_NotStart | 1208363553 | 450 | 1208363553_450
MRPP2-EPA.10070 | TT_Task | EMU - Train 08 Preliminary Acceptance Test ; PTA Certification | 23/05/2024 | 11/07/2024 | nan | nan | 0 | TK_NotStart | 1208363553 | 450 | 1208363553_450
MRPP2-EPA.10080 | TT_Task | EMU - Train 09 Preliminary Acceptance Test ; PTA Certification | 18/07/2024 | 04/09/2024 | nan | nan | 0 | TK_NotStart | 1208363553 | 450 | 1208363553_450
MRPP2-EPA.10090 | TT_Task | EMU - Train 10 Preliminary Acceptance Test ; PTA Certification | 30/08/2024 | 21/10/2024 | nan | nan | 0 | TK_NotStart | 1208363553 | 451 | 1208363553_451
MRPP2-EPA.10100 | TT_Task | EMU - Train 11 Preliminary Acceptance Test ; PTA Certification | 04/09/2024 | 23/10/2024 | nan | nan | 0 | TK_NotStart | 1208363553 | 451 | 1208363553_451
MRPP2-EPA.10110 | TT_Task | EMU - Train 12 Preliminary Acceptance Test ; PTA Certification | 01/11/2024 | 19/12/2024 | nan | nan | 0 | TK_NotStart | 1208363553 | 451 | 1208363553_451
MRPP2-EPA.10120 | TT_Task | EMU - Train 13 Preliminary Acceptance Test ; PTA Certification | 20/11/2024 | 13/01/2025 | nan | nan | 0 | TK_NotStart | 1208363553 | 451 | 1208363553_451
MRPP2-EPA.10130 | TT_Task | EMU - Train 14 Preliminary Acceptance Test ; PTA Certification | 17/01/2025 | 10/03/2025 | nan | nan | 0 | TK_NotStart | 1208363553 | 451 | 1208363553_451
MRPP2-EPA.10140 | TT_Task | EMU - Train 15 Preliminary Acceptance Test ; PTA Certification | 14/03/2025 | 06/05/2025 | nan | nan | 0 | TK_NotStart | 1208363553 | 451 | 1208363553_451
MRPP2-EPA.10150 | TT_Task | EMU - Train 16 Preliminary Acceptance Test ; PTA Certification | 22/05/2025 | 10/07/2025 | nan | nan | 0 | TK_NotStart | 1208363553 | 451 | 1208363553_451
MRPP2-EPA.10160 | TT_Task | EMU - Train 17 Preliminary Acceptance Test ; PTA Certification | 16/07/2025 | 02/09/2025 | nan | nan | 0 | TK_NotStart | 1208363553 | 451 | 1208363553_451
MRPP2-EPA.10170 | TT_Task | EMU - Train 18 Preliminary Acceptance Test ; PTA Certification | 05/09/2025 | 27/10/2025 | nan | nan | 0 | TK_NotStart | 1208363553 | 451 | 1208363553_451
MRPP2-EPA.10180 | TT_Task | EMU - Train 19 Preliminary Acceptance Test ; PTA Certification | 27/10/2025 | 15/12/2025 | nan | nan | 0 | TK_NotStart | 1208363553 | 451 | 1208363553_451
MRPP2-EPA.10190 | TT_Task | EMU - Train 20 Preliminary Acceptance Test ; PTA Certification | 22/12/2025 | 12/02/2026 | nan | nan | 0 | TK_NotStart | 1208363553 | 451 | 1208363553_451
MRPP2-EPA.10200 | TT_Task | EMU - Train 21 Preliminary Acceptance Test ; PTA Certification | 20/02/2026 | 09/04/2026 | nan | nan | 0 | TK_NotStart | 1208363553 | 451 | 1208363553_451
MRPP2-EPA.10210 | TT_Task | EMU - Train 22 Preliminary Acceptance Test ; PTA Certification | 23/04/2026 | 12/06/2026 | nan | nan | 0 | TK_NotStart | 1208363553 | 451 | 1208363553_451
MRPP2-EPA.10220 | TT_Task | EMU - Train 23 Preliminary Acceptance Test ; PTA Certification | 22/06/2026 | 07/08/2026 | nan | nan | 0 | TK_NotStart | 1208363553 | 451 | 1208363553_451
MRPP2-EPA.10230 | TT_Task | EMU - Train 24 Preliminary Acceptance Test ; PTA Certification | 20/08/2026 | 08/10/2026 | nan | nan | 0 | TK_NotStart | 1208363553 | 451 | 1208363553_451
MRPP2-EPA.10240 | TT_Task | EMU - Train 25 Preliminary Acceptance Test ; PTA Certification | 15/10/2026 | 02/12/2026 | nan | nan | 0 | TK_NotStart | 1208363553 | 451 | 1208363553_451
MRPP2-EPA.10250 | TT_Task | EMU - Train 26 Preliminary Acceptance Test ; PTA Certification | 04/12/2026 | 27/01/2027 | nan | nan | 0 | TK_NotStart | 1208363553 | 451 | 1208363553_451
MRPP2-EPA.10260 | TT_Task | EMU - Train 27 Preliminary Acceptance Test ; PTA Certification | 08/02/2027 | 26/03/2027 | nan | nan | 0 | TK_NotStart | 1208363553 | 451 | 1208363553_451
MRPP2-EPA.10270 | TT_Task | EMU - Train 28 Preliminary Acceptance Test ; PTA Certification | 31/03/2027 | 21/05/2027 | nan | nan | 0 | TK_NotStart | 1208363553 | 451 | 1208363553_451
MRPP2-EPA.10280 | TT_Task | EMU - Train 29 Preliminary Acceptance Test ; PTA Certification | 03/06/2027 | 22/07/2027 | nan | nan | 0 | TK_NotStart | 1208363553 | 451 | 1208363553_451
MRPP2-EPA.10290 | TT_Task | EMU - Train 30 Preliminary Acceptance Test ; PTA Certification | 28/07/2027 | 14/09/2027 | nan | nan | 0 | TK_NotStart | 1208363553 | 451 | 1208363553_451
MRPP2-EPA.10300 | TT_Task | EMU - Train 31 Preliminary Acceptance Test ; PTA Certification | 21/09/2027 | 09/11/2027 | nan | nan | 0 | TK_NotStart | 1208363553 | 451 | 1208363553_451
MRPP2-EPA.10310 | TT_Task | EMU - Train 32 Preliminary Acceptance Test ; PTA Certification | 16/11/2027 | 04/01/2028 | nan | nan | 0 | TK_NotStart | 1208363553 | 451 | 1208363553_451
MRPP2-EPA.10320 | TT_Task | EMU - Train 33 Preliminary Acceptance Test ; PTA Certification | 11/01/2028 | 29/02/2028 | nan | nan | 0 | TK_NotStart | 1208363553 | 451 | 1208363553_451
MRPP2-EPA.10330 | TT_Task | EMU - Train 34 Preliminary Acceptance Test ; PTA Certification | 08/03/2028 | 28/04/2028 | nan | nan | 0 | TK_NotStart | 1208363553 | 451 | 1208363553_451
MRPP2-EPA.10340 | TT_Task | EMU - Train 35 Preliminary Acceptance Test ; PTA Certification | 10/05/2028 | 28/06/2028 | nan | nan | 0 | TK_NotStart | 1208363553 | 451 | 1208363553_451
MRPP2-EPA.10350 | TT_Task | EMU - Train 36 Preliminary Acceptance Test ; PTA Certification | 30/06/2028 | 17/08/2028 | nan | nan | 0 | TK_NotStart | 1208363553 | 451 | 1208363553_451
MRPP2-EPA.10360 | TT_Task | EMU - Train 37 Preliminary Acceptance Test ; PTA Certification | 30/08/2028 | 18/10/2028 | nan | nan | 0 | TK_NotStart | 1208363553 | 451 | 1208363553_451
MRPP2-EPA.10370 | TT_Task | EMU - Train 38 Preliminary Acceptance Test ; PTA Certification | 26/10/2028 | 13/12/2028 | nan | nan | 0 | TK_NotStart | 1208363553 | 451 | 1208363553_451
MRPP2-EPA.10380 | TT_Task | EMU - Train 39 Preliminary Acceptance Test ; PTA Certification | 15/12/2028 | 07/02/2029 | nan | nan | 0 | TK_NotStart | 1208363553 | 451 | 1208363553_451
MRPP2-EPA.10390 | TT_Task | EMU - Train 40 Preliminary Acceptance Test ; PTA Certification | 14/02/2029 | 03/04/2029 | nan | nan | 0 | TK_NotStart | 1208363553 | 451 | 1208363553_451
MRPP2-EPA.10400 | TT_Task | EMU - Train 41 Preliminary Acceptance Test ; PTA Certification | 20/04/2029 | 08/06/2029 | nan | nan | 0 | TK_NotStart | 1208363553 | 451 | 1208363553_451
MRPP2-EQA.10450 | TT_Task | EMU - Train 01 Certification Period by PTA for Provisional Acceptance | 06/10/2023 | 02/11/2023 | nan | nan | 0 | TK_NotStart | 1208363553 | 452 | 1208363553_452
MRPP2-EQA.10500 | TT_Task | EMU - Train 01 Service Trials | 04/10/2023 | 19/10/2023 | nan | nan | 0 | TK_NotStart | 1208363553 | 453 | 1208363553_453
MRPP2-EQA.10520 | TT_Task | EMU - Train 01 Additional Period for Retrofit + Serial Test | 26/07/2023 | 03/10/2023 | nan | nan | 0 | TK_NotStart | 1208363553 | 454 | 1208363553_454
MRPP2-EQA.10600 | TT_Task | EMU - Train 01 Static Functional Validation | 08/08/2022 | 09/09/2022 | nan | nan | 0 | TK_NotStart | 1208363553 | 455 | 1208363553_455
MRPP2-EQA.10620 | TT_Task | EMU - Train 01 Driver Training (Final Phase) | 12/09/2022 | 23/09/2022 | nan | nan | 0 | TK_NotStart | 1208363553 | 428 | 1208363553_428
MRPP2-EQA.10630 | TT_Task | EMU - Train 01 Dynamic Integration ; Tuning | 27/09/2022 | 01/12/2022 | nan | nan | 0 | TK_NotStart | 1208363553 | 456 | 1208363553_456
MRPP2-EQA.10640 | TT_Task | EMU - Train 01 Dynamic Validation | 02/12/2022 | 25/07/2023 | nan | nan | 0 | TK_NotStart | 1208363553 | 455 | 1208363553_455
MRPP2-EQA.10490 | TT_Task | EMU - Train 02 Certification Period by PTA for Provisional Acceptance | 20/10/2023 | 16/11/2023 | nan | nan | 0 | TK_NotStart | 1208363553 | 452 | 1208363553_452
MRPP2-EQA.10510 | TT_Task | EMU - Train 02 Service Trials | 17/10/2023 | 01/11/2023 | nan | nan | 0 | TK_NotStart | 1208363553 | 453 | 1208363553_453
MRPP2-EQA.10530 | TT_Task | EMU - Train 02 Additional Period for Retrofit + Serial Test | 26/07/2023 | 16/10/2023 | nan | nan | 0 | TK_NotStart | 1208363553 | 454 | 1208363553_454
MRPP2-EQA.10680 | TT_Task | EMU - Train 02 Static Functional Validation | 07/10/2022 | 23/11/2022 | nan | nan | 0 | TK_NotStart | 1208363553 | 455 | 1208363553_455
MRPP2-EQA.10690 | TT_Task | EMU - Train 02 Static Performance Validation | 24/11/2022 | 28/12/2022 | nan | nan | 0 | TK_NotStart | 1208363553 | 455 | 1208363553_455
MRPP2-EQA.10730 | TT_Task | EMU - Train 02 Dynamic Validation | 29/12/2022 | 25/07/2023 | nan | nan | 0 | TK_NotStart | 1208363553 | 455 | 1208363553_455
MRPP2-EQA.10020 | TT_Task | EMU - Train 03 Certification Period by PTA for Provisional Acceptance | 14/08/2023 | 25/08/2023 | nan | nan | 0 | TK_NotStart | 1208363553 | 452 | 1208363553_452
MRPP2-EQA.10550 | TT_Task | EMU - Train 03 Retrofit | 26/07/2023 | 28/07/2023 | nan | nan | 0 | TK_NotStart | 1208363553 | 457 | 1208363553_457
MRPP2-EQA.10560 | TT_Task | EMU - Train 03 Service Trials | 31/07/2023 | 11/08/2023 | nan | nan | 0 | TK_NotStart | 1208363553 | 453 | 1208363553_453
MRPP2-EQA.10710 | TT_Task | EMU - Train 03 Dynamic Validation | 11/05/2023 | 25/07/2023 | nan | nan | 0 | TK_NotStart | 1208363553 | 455 | 1208363553_455
MRPP2-EQA.10030 | TT_Task | EMU - Train 04 Provisional Acceptance Tests ; PTA Certification | 21/08/2023 | 01/09/2023 | nan | nan | 0 | TK_NotStart | 1208363553 | 458 | 1208363553_458
MRPP2-EQA.10570 | TT_Task | EMU - Train 04 Service Trials | 11/08/2023 | 24/08/2023 | nan | nan | 0 | TK_NotStart | 1208363553 | 453 | 1208363553_453
MRPP2-EQA.10040 | TT_Task | EMU - Train 05 Provisional Acceptance Tests ; PTA Certification | 18/09/2023 | 02/10/2023 | nan | nan | 0 | TK_NotStart | 1208363553 | 458 | 1208363553_458
MRPP2-EQA.10590 | TT_Task | EMU - Train 05 Service Trials | 05/09/2023 | 18/09/2023 | nan | nan | 0 | TK_NotStart | 1208363553 | 453 | 1208363553_453
MRPP2-EQA.10050 | TT_Task | EMU - Train 06 Provisional Acceptance Tests ; PTA Certification | 03/04/2024 | 21/05/2024 | nan | nan | 0 | TK_NotStart | 1208363553 | 458 | 1208363553_458
MRPP2-EQA.10060 | TT_Task | EMU - Train 07 Provisional Acceptance Tests ; PTA Certification | 23/05/2024 | 10/07/2024 | nan | nan | 0 | TK_NotStart | 1208363553 | 458 | 1208363553_458
MRPP2-EQA.10070 | TT_Task | EMU - Train 08 Provisional Acceptance Tests ; PTA Certification | 18/07/2024 | 04/09/2024 | nan | nan | 0 | TK_NotStart | 1208363553 | 458 | 1208363553_458
MRPP2-EQA.10080 | TT_Task | EMU - Train 09 Provisional Acceptance Tests ; PTA Certification | 05/09/2024 | 22/10/2024 | nan | nan | 0 | TK_NotStart | 1208363553 | 458 | 1208363553_458
MRPP2-EQA.10090 | TT_Task | EMU - Train 10 Provisional Acceptance Tests ; PTA Certification | 24/10/2024 | 11/12/2024 | nan | nan | 0 | TK_NotStart | 1208363553 | 458 | 1208363553_458
MRPP2-EQA.10100 | TT_Task | EMU - Train 11 Provisional Acceptance Tests ; PTA Certification | 25/10/2024 | 12/12/2024 | nan | nan | 0 | TK_NotStart | 1208363553 | 458 | 1208363553_458
MRPP2-EQA.10110 | TT_Task | EMU - Train 12 Provisional Acceptance Tests ; PTA Certification | 23/12/2024 | 13/02/2025 | nan | nan | 0 | TK_NotStart | 1208363553 | 458 | 1208363553_458
MRPP2-EQA.10120 | TT_Task | EMU - Train 13 Provisional Acceptance Tests ; PTA Certification | 20/01/2025 | 10/03/2025 | nan | nan | 0 | TK_NotStart | 1208363553 | 458 | 1208363553_458
MRPP2-EQA.10130 | TT_Task | EMU - Train 14 Provisional Acceptance Tests ; PTA Certification | 13/03/2025 | 05/05/2025 | nan | nan | 0 | TK_NotStart | 1208363553 | 458 | 1208363553_458
MRPP2-EQA.10140 | TT_Task | EMU - Train 15 Provisional Acceptance Tests ; PTA Certification | 19/05/2025 | 07/07/2025 | nan | nan | 0 | TK_NotStart | 1208363553 | 458 | 1208363553_458
MRPP2-EQA.10150 | TT_Task | EMU - Train 16 Provisional Acceptance Tests ; PTA Certification | 22/07/2025 | 08/09/2025 | nan | nan | 0 | TK_NotStart | 1208363553 | 458 | 1208363553_458
MRPP2-EQA.10160 | TT_Task | EMU - Train 17 Provisional Acceptance Tests ; PTA Certification | 18/09/2025 | 06/11/2025 | nan | nan | 0 | TK_NotStart | 1208363553 | 458 | 1208363553_458
MRPP2-EQA.10170 | TT_Task | EMU - Train 18 Provisional Acceptance Tests ; PTA Certification | 14/11/2025 | 06/01/2026 | nan | nan | 0 | TK_NotStart | 1208363553 | 458 | 1208363553_458
MRPP2-EQA.10180 | TT_Task | EMU - Train 19 Provisional Acceptance Tests ; PTA Certification | 08/01/2026 | 26/02/2026 | nan | nan | 0 | TK_NotStart | 1208363553 | 458 | 1208363553_458
MRPP2-EQA.10190 | TT_Task | EMU - Train 20 Provisional Acceptance Tests ; PTA Certification | 05/03/2026 | 24/04/2026 | nan | nan | 0 | TK_NotStart | 1208363553 | 458 | 1208363553_458
MRPP2-EQA.10200 | TT_Task | EMU - Train 21 Provisional Acceptance Tests ; PTA Certification | 04/05/2026 | 22/06/2026 | nan | nan | 0 | TK_NotStart | 1208363553 | 458 | 1208363553_458
MRPP2-EQA.10210 | TT_Task | EMU - Train 22 Provisional Acceptance Tests ; PTA Certification | 03/07/2026 | 20/08/2026 | nan | nan | 0 | TK_NotStart | 1208363553 | 458 | 1208363553_458
MRPP2-EQA.10220 | TT_Task | EMU - Train 23 Provisional Acceptance Tests ; PTA Certification | 01/09/2026 | 20/10/2026 | nan | nan | 0 | TK_NotStart | 1208363553 | 458 | 1208363553_458
MRPP2-EQA.10230 | TT_Task | EMU - Train 24 Provisional Acceptance Tests ; PTA Certification | 29/10/2026 | 16/12/2026 | nan | nan | 0 | TK_NotStart | 1208363553 | 458 | 1208363553_458
MRPP2-EQA.10240 | TT_Task | EMU - Train 25 Provisional Acceptance Tests ; PTA Certification | 18/12/2026 | 10/02/2027 | nan | nan | 0 | TK_NotStart | 1208363553 | 458 | 1208363553_458
MRPP2-EQA.10250 | TT_Task | EMU - Train 26 Provisional Acceptance Tests ; PTA Certification | 17/02/2027 | 06/04/2027 | nan | nan | 0 | TK_NotStart | 1208363553 | 458 | 1208363553_458
MRPP2-EQA.10260 | TT_Task | EMU - Train 27 Provisional Acceptance Tests ; PTA Certification | 19/04/2027 | 08/06/2027 | nan | nan | 0 | TK_NotStart | 1208363553 | 458 | 1208363553_458
MRPP2-EQA.10270 | TT_Task | EMU - Train 28 Provisional Acceptance Tests ; PTA Certification | 17/06/2027 | 04/08/2027 | nan | nan | 0 | TK_NotStart | 1208363553 | 458 | 1208363553_458
MRPP2-EQA.10280 | TT_Task | EMU - Train 29 Provisional Acceptance Tests ; PTA Certification | 16/08/2027 | 04/10/2027 | nan | nan | 0 | TK_NotStart | 1208363553 | 458 | 1208363553_458
MRPP2-EQA.10290 | TT_Task | EMU - Train 30 Provisional Acceptance Tests ; PTA Certification | 12/10/2027 | 29/11/2027 | nan | nan | 0 | TK_NotStart | 1208363553 | 458 | 1208363553_458
MRPP2-EQA.10300 | TT_Task | EMU - Train 31 Provisional Acceptance Tests ; PTA Certification | 01/12/2027 | 19/01/2028 | nan | nan | 0 | TK_NotStart | 1208363553 | 458 | 1208363553_458
MRPP2-EQA.10310 | TT_Task | EMU - Train 32 Provisional Acceptance Tests ; PTA Certification | 24/01/2028 | 13/03/2028 | nan | nan | 0 | TK_NotStart | 1208363553 | 458 | 1208363553_458
MRPP2-EQA.10320 | TT_Task | EMU - Train 33 Provisional Acceptance Tests ; PTA Certification | 16/03/2028 | 08/05/2028 | nan | nan | 0 | TK_NotStart | 1208363553 | 458 | 1208363553_458
MRPP2-EQA.10330 | TT_Task | EMU - Train 34 Provisional Acceptance Tests ; PTA Certification | 12/05/2028 | 30/06/2028 | nan | nan | 0 | TK_NotStart | 1208363553 | 458 | 1208363553_458
MRPP2-EQA.10340 | TT_Task | EMU - Train 35 Provisional Acceptance Tests ; PTA Certification | 06/07/2028 | 23/08/2028 | nan | nan | 0 | TK_NotStart | 1208363553 | 458 | 1208363553_458
MRPP2-EQA.10350 | TT_Task | EMU - Train 36 Provisional Acceptance Tests ; PTA Certification | 31/08/2028 | 19/10/2028 | nan | nan | 0 | TK_NotStart | 1208363553 | 458 | 1208363553_458
MRPP2-EQA.10360 | TT_Task | EMU - Train 37 Provisional Acceptance Tests ; PTA Certification | 31/10/2028 | 18/12/2028 | nan | nan | 0 | TK_NotStart | 1208363553 | 458 | 1208363553_458
MRPP2-EQA.10370 | TT_Task | EMU - Train 38 Provisional Acceptance Tests ; PTA Certification | 20/12/2028 | 12/02/2029 | nan | nan | 0 | TK_NotStart | 1208363553 | 458 | 1208363553_458
MRPP2-EQA.10380 | TT_Task | EMU - Train 39 Provisional Acceptance Tests ; PTA Certification | 20/02/2029 | 09/04/2029 | nan | nan | 0 | TK_NotStart | 1208363553 | 458 | 1208363553_458
MRPP2-EQA.10390 | TT_Task | EMU - Train 40 Provisional Acceptance Tests ; PTA Certification | 12/04/2029 | 05/06/2029 | nan | nan | 0 | TK_NotStart | 1208363553 | 458 | 1208363553_458
MRPP2-EQA.10400 | TT_Task | EMU - Train 41 Provisional Acceptance Tests ; PTA Certification | 19/06/2029 | 06/08/2029 | nan | nan | 0 | TK_NotStart | 1208363553 | 458 | 1208363553_458
MRPP2-EFA.10000 | TT_Task | EMU - Train 01 Final Acceptance Tests ; PTA Certification | 15/01/2024 | 22/04/2024 | nan | nan | 0 | TK_NotStart | 1208363553 | 450 | 1208363553_450
MRPP2-EFA.10010 | TT_Task | EMU - Train 02 Final Acceptance Tests ; PTA Certification | 29/01/2024 | 06/05/2024 | nan | nan | 0 | TK_NotStart | 1208363553 | 450 | 1208363553_450
MRPP2-EFA.10020 | TT_Task | EMU - Train 03 Final Acceptance Tests ; PTA Certification | 26/04/2024 | 11/06/2024 | nan | nan | 0 | TK_NotStart | 1208363553 | 450 | 1208363553_450
MRPP2-EFA.10030 | TT_Task | EMU - Train 04 Final Acceptance Tests ; PTA Certification | 29/05/2024 | 12/07/2024 | nan | nan | 0 | TK_NotStart | 1208363553 | 450 | 1208363553_450
MRPP2-EFA.10040 | TT_Task | EMU - Train 05 Final Acceptance Tests ; PTA Certification | 02/07/2024 | 14/08/2024 | nan | nan | 0 | TK_NotStart | 1208363553 | 450 | 1208363553_450
MRPP2-EFA.10050 | TT_Task | EMU - Train 06 Final Acceptance Tests ; PTA Certification | 18/10/2024 | 02/12/2024 | nan | nan | 0 | TK_NotStart | 1208363553 | 450 | 1208363553_450
MRPP2-EFA.10060 | TT_Task | EMU - Train 07 Final Acceptance Tests ; PTA Certification | 05/12/2024 | 22/01/2025 | nan | nan | 0 | TK_NotStart | 1208363553 | 450 | 1208363553_450
MRPP2-EFA.10070 | TT_Task | EMU - Train 08 Final Acceptance Tests ; PTA Certification | 30/01/2025 | 14/03/2025 | nan | nan | 0 | TK_NotStart | 1208363553 | 450 | 1208363553_450
MRPP2-EFA.10080 | TT_Task | EMU - Train 09 Final Acceptance Tests ; PTA Certification | 17/03/2025 | 02/05/2025 | nan | nan | 0 | TK_NotStart | 1208363553 | 450 | 1208363553_450
MRPP2-EFA.10090 | TT_Task | EMU - Train 10 Final Acceptance Tests ; PTA Certification | 05/05/2025 | 18/06/2025 | nan | nan | 0 | TK_NotStart | 1208363553 | 451 | 1208363553_451
MRPP2-EFA.10100 | TT_Task | EMU - Train 11 Final Acceptance Tests ; PTA Certification | 06/05/2025 | 19/06/2025 | nan | nan | 0 | TK_NotStart | 1208363553 | 451 | 1208363553_451
MRPP2-EFA.10110 | TT_Task | EMU - Train 12 Final Acceptance Tests ; PTA Certification | 09/07/2025 | 21/08/2025 | nan | nan | 0 | TK_NotStart | 1208363553 | 451 | 1208363553_451
MRPP2-EFA.10120 | TT_Task | EMU - Train 13 Final Acceptance Tests ; PTA Certification | 06/08/2025 | 18/09/2025 | nan | nan | 0 | TK_NotStart | 1208363553 | 451 | 1208363553_451
MRPP2-EFA.10130 | TT_Task | EMU - Train 14 Final Acceptance Tests ; PTA Certification | 07/10/2025 | 19/11/2025 | nan | nan | 0 | TK_NotStart | 1208363553 | 451 | 1208363553_451
MRPP2-EFA.10140 | TT_Task | EMU - Train 15 Final Acceptance Tests ; PTA Certification | 28/11/2025 | 15/01/2026 | nan | nan | 0 | TK_NotStart | 1208363553 | 451 | 1208363553_451
MRPP2-EFA.10150 | TT_Task | EMU - Train 16 Final Acceptance Tests ; PTA Certification | 29/01/2026 | 13/03/2026 | nan | nan | 0 | TK_NotStart | 1208363553 | 451 | 1208363553_451
MRPP2-EFA.10160 | TT_Task | EMU - Train 17 Final Acceptance Tests ; PTA Certification | 24/03/2026 | 11/05/2026 | nan | nan | 0 | TK_NotStart | 1208363553 | 451 | 1208363553_451
MRPP2-EFA.10170 | TT_Task | EMU - Train 18 Final Acceptance Tests ; PTA Certification | 27/05/2026 | 10/07/2026 | nan | nan | 0 | TK_NotStart | 1208363553 | 451 | 1208363553_451
MRPP2-EFA.10180 | TT_Task | EMU - Train 19 Final Acceptance Tests ; PTA Certification | 24/07/2026 | 07/09/2026 | nan | nan | 0 | TK_NotStart | 1208363553 | 451 | 1208363553_451
MRPP2-EFA.10190 | TT_Task | EMU - Train 20 Final Acceptance Tests ; PTA Certification | 24/09/2026 | 09/11/2026 | nan | nan | 0 | TK_NotStart | 1208363553 | 451 | 1208363553_451
MRPP2-EFA.10200 | TT_Task | EMU - Train 21 Final Acceptance Tests ; PTA Certification | 17/11/2026 | 04/01/2027 | nan | nan | 0 | TK_NotStart | 1208363553 | 451 | 1208363553_451
MRPP2-EFA.10210 | TT_Task | EMU - Train 22 Final Acceptance Tests ; PTA Certification | 14/01/2027 | 01/03/2027 | nan | nan | 0 | TK_NotStart | 1208363553 | 451 | 1208363553_451
MRPP2-EFA.10220 | TT_Task | EMU - Train 23 Final Acceptance Tests ; PTA Certification | 10/03/2027 | 27/04/2027 | nan | nan | 0 | TK_NotStart | 1208363553 | 451 | 1208363553_451
MRPP2-EFA.10230 | TT_Task | EMU - Train 24 Final Acceptance Tests ; PTA Certification | 07/05/2027 | 22/06/2027 | nan | nan | 0 | TK_NotStart | 1208363553 | 451 | 1208363553_451
MRPP2-EFA.10240 | TT_Task | EMU - Train 25 Final Acceptance Tests ; PTA Certification | 09/07/2027 | 23/08/2027 | nan | nan | 0 | TK_NotStart | 1208363553 | 451 | 1208363553_451
MRPP2-EFA.10250 | TT_Task | EMU - Train 26 Final Acceptance Tests ; PTA Certification | 06/09/2027 | 20/10/2027 | nan | nan | 0 | TK_NotStart | 1208363553 | 451 | 1208363553_451
MRPP2-EFA.10260 | TT_Task | EMU - Train 27 Final Acceptance Tests ; PTA Certification | 03/11/2027 | 16/12/2027 | nan | nan | 0 | TK_NotStart | 1208363553 | 451 | 1208363553_451
MRPP2-EFA.10270 | TT_Task | EMU - Train 28 Final Acceptance Tests ; PTA Certification | 28/12/2027 | 10/02/2028 | nan | nan | 0 | TK_NotStart | 1208363553 | 451 | 1208363553_451
MRPP2-EFA.10280 | TT_Task | EMU - Train 29 Final Acceptance Tests ; PTA Certification | 24/02/2028 | 11/04/2028 | nan | nan | 0 | TK_NotStart | 1208363553 | 451 | 1208363553_451
MRPP2-EFA.10290 | TT_Task | EMU - Train 30 Final Acceptance Tests ; PTA Certification | 17/04/2028 | 31/05/2028 | nan | nan | 0 | TK_NotStart | 1208363553 | 451 | 1208363553_451
MRPP2-EFA.10300 | TT_Task | EMU - Train 31 Final Acceptance Tests ; PTA Certification | 09/06/2028 | 24/07/2028 | nan | nan | 0 | TK_NotStart | 1208363553 | 451 | 1208363553_451
MRPP2-EFA.10310 | TT_Task | EMU - Train 32 Final Acceptance Tests ; PTA Certification | 08/08/2028 | 20/09/2028 | nan | nan | 0 | TK_NotStart | 1208363553 | 451 | 1208363553_451
MRPP2-EFA.10320 | TT_Task | EMU - Train 33 Final Acceptance Tests ; PTA Certification | 03/10/2028 | 15/11/2028 | nan | nan | 0 | TK_NotStart | 1208363553 | 451 | 1208363553_451
MRPP2-EFA.10330 | TT_Task | EMU - Train 34 Final Acceptance Tests ; PTA Certification | 21/11/2028 | 08/01/2029 | nan | nan | 0 | TK_NotStart | 1208363553 | 451 | 1208363553_451
MRPP2-EFA.10340 | TT_Task | EMU - Train 35 Final Acceptance Tests ; PTA Certification | 17/01/2029 | 02/03/2029 | nan | nan | 0 | TK_NotStart | 1208363553 | 451 | 1208363553_451
MRPP2-EFA.10350 | TT_Task | EMU - Train 36 Final Acceptance Tests ; PTA Certification | 07/03/2029 | 23/04/2029 | nan | nan | 0 | TK_NotStart | 1208363553 | 451 | 1208363553_451
MRPP2-EFA.10360 | TT_Task | EMU - Train 37 Final Acceptance Tests ; PTA Certification | 10/05/2029 | 25/06/2029 | nan | nan | 0 | TK_NotStart | 1208363553 | 451 | 1208363553_451
MRPP2-EFA.10370 | TT_Task | EMU - Train 38 Final Acceptance Tests ; PTA Certification | 09/07/2029 | 21/08/2029 | nan | nan | 0 | TK_NotStart | 1208363553 | 451 | 1208363553_451
MRPP2-EFA.10380 | TT_Task | EMU - Train 39 Final Acceptance Tests ; PTA Certification | 06/09/2029 | 22/10/2029 | nan | nan | 0 | TK_NotStart | 1208363553 | 451 | 1208363553_451
MRPP2-EFA.10390 | TT_Task | EMU - Train 40 Final Acceptance Tests ; PTA Certification | 01/11/2029 | 17/12/2029 | nan | nan | 0 | TK_NotStart | 1208363553 | 451 | 1208363553_451
MRPP2-EFA.10400 | TT_Task | EMU - Train 41 Final Acceptance Tests ; PTA Certification | 13/12/2029 | 07/02/2030 | nan | nan | 0 | TK_NotStart | 1208363553 | 451 | 1208363553_451
MRPP2-GEN.11410 | TT_Task | EMU Stage - Mock-up Final Client Review | 11/05/2021 | 05/07/2021 | 11/05/2021 | 05/07/2021 | 0 | TK_Complete | 1208363553 | 459 | 1208363553_459
MRPP2-DE1.13923 | TT_Task | Train Specification DMU M1 | 19/12/2019 | 09/10/2020 | 19/12/2019 | 09/10/2020 | 0 | TK_Complete | 1208363553 | 460 | 1208363553_460
MRPP2-DE1.14093 | TT_Task | Train Specification - PTA Design Review Rev.A DMU M1 | 12/10/2020 | 05/11/2020 | 12/10/2020 | 05/11/2020 | 0 | TK_Complete | 1208363553 | 461 | 1208363553_461
MRPP2-DE1.16003 | TT_Task | Train Specification - Submit Rev.B DMU M1 | 06/11/2020 | 05/02/2021 | 06/11/2020 | 05/02/2021 | 0 | TK_Complete | 1208363553 | 460 | 1208363553_460
MRPP2-DE1.16013 | TT_Task | Train Specification - PTA Design Review Rev.B DMU M1 | 08/02/2021 | 09/03/2021 | 08/02/2021 | 09/03/2021 | 0 | TK_Complete | 1208363553 | 461 | 1208363553_461
MRPP2-DE1.16043 | TT_Task | Train Specification - Submit Rev.C DMU M1 | 10/03/2021 | 30/04/2021 | 10/03/2021 | 30/04/2021 | 0 | TK_Complete | 1208363553 | 460 | 1208363553_460
MRPP2-DE1.16053 | TT_Task | Train Specification - PTA Design Review Rev.C DMU M1 | 01/04/2021 | 31/05/2021 | 01/04/2021 | 31/05/2021 | 0 | TK_Complete | 1208363553 | 461 | 1208363553_461
MRPP2-DE1.14033 | TT_Task | Document Management Plan (DMP) DMU M1 | 23/12/2019 | 26/03/2020 | 23/12/2019 | 26/03/2020 | 0 | TK_Complete | 1208363553 | 24 | 1208363553_24
MRPP2-DE1.14423 | TT_Task | Document Management Plan (DMP) - PTA Design Review DMU M1 | 27/03/2020 | 21/04/2020 | 27/03/2020 | 21/04/2020 | 0 | TK_Complete | 1208363553 | 25 | 1208363553_25
MRPP2-DE1.15243 | TT_Task | Document Management Plan (DMP) - Resubmit Rev.B DMU M1 | 22/04/2020 | 30/04/2020 | 22/04/2020 | 30/04/2020 | 0 | TK_Complete | 1208363553 | 24 | 1208363553_24
MRPP2-DE1.15253 | TT_Task | Document Management Plan (DMP) - PTA Design Review Rev.B DMU M1 | 01/05/2020 | 14/05/2020 | 01/05/2020 | 14/05/2020 | 0 | TK_Complete | 1208363553 | 25 | 1208363553_25
MRPP2-DE2.16063 | TT_Task | Preliminary Design Specification ? Equipment Mounting DMU M2 | 16/04/2020 | 29/01/2021 | 16/04/2020 | 29/01/2021 | 0 | TK_Complete | 1208363553 | 462 | 1208363553_462
MRPP2-DE2.16083 | TT_Task | Preliminary Design Specification ? Equipment Mounting - PTA Design Review Rev.A DMU M2 | 01/02/2021 | 25/02/2021 | 01/02/2021 | 25/02/2021 | 0 | TK_Complete | 1208363553 | 462 | 1208363553_462
MRPP2-DE2.19003 | TT_Task | Preliminary Design Specification ? Equipment Mounting - Submit Rev.B DMU M2 | 26/02/2021 | 23/03/2021 | 26/02/2021 | 23/03/2021 | 0 | TK_Complete | 1208363553 | 462 | 1208363553_462
MRPP2-DE2.19013 | TT_Task | Preliminary Design Specification ? Equipment Mounting - PTA Design Review Rev.B DMU M2 | 24/03/2021 | 22/04/2021 | 24/03/2021 | 22/04/2021 | 0 | TK_Complete | 1208363553 | 462 | 1208363553_462
MRPP2-DE2.19203 | TT_Task | Preliminary Design Specification ? Equipment Mounting - Submit Rev.C DMU M2 | 23/04/2021 | 31/05/2021 | 23/04/2021 | 31/05/2021 | 0 | TK_Complete | 1208363553 | 462 | 1208363553_462
MRPP2-DE2.19213 | TT_Task | Preliminary Design Specification ? Equipment Mounting - PTA Design Review Rev.C DMU M2 | 31/05/2021 | 29/06/2021 | 31/05/2021 | 29/06/2021 | 0 | TK_Complete | 1208363553 | 462 | 1208363553_462
MRPP2-DE2.16263 | TT_Task | Preliminary Kinematic Envelope Calculation Report DMU M2 | 28/05/2020 | 10/02/2021 | 28/05/2020 | 10/02/2021 | 0 | TK_Complete | 1208363553 | 27 | 1208363553_27
MRPP2-DE2.16283 | TT_Task | Preliminary Kinematic Envelope Calculation Report - PTA Design Review Rev.A DMU M2 | 11/02/2021 | 11/03/2021 | 11/02/2021 | 11/03/2021 | 0 | TK_Complete | 1208363553 | 28 | 1208363553_28
MRPP2-DE2.19063 | TT_Task | Preliminary Kinematic Envelope Calculation Report - Submit Rev.B DMU M2 | 12/03/2021 | 01/02/2022 | 12/03/2021 | nan | 0 | TK_Active | 1208363553 | 27 | 1208363553_27
MRPP2-DE2.19073 | TT_Task | Preliminary Kinematic Envelope Calculation Report - PTA Design Review Rev.B DMU M2 | 12/04/2022 | 10/05/2022 | nan | nan | 0 | TK_NotStart | 1208363553 | 28 | 1208363553_28
MRPP2-DE3.14590 | TT_Task | Train Configuration ; Main Dimensions DMU M3 | 08/09/2020 | 08/10/2021 | 08/09/2020 | 08/10/2021 | 0 | TK_Complete | 1208363553 | 30 | 1208363553_30
MRPP2-DE3.14790 | TT_Task | Train Configuration ; Main Dimensions - PTA Design Review Rev.A DMU M3 | 11/10/2021 | 12/11/2021 | 11/10/2021 | 12/11/2021 | 0 | TK_Complete | 1208363553 | 461 | 1208363553_461
MRPP2-DE3.28690 | TT_Task | Train Configuration ; Main Dimensions - Submit Rev.B DMU M3 | 15/11/2021 | 29/03/2022 | 15/11/2021 | nan | 0 | TK_Active | 1208363553 | 30 | 1208363553_30
MRPP2-DE3.28700 | TT_Task | Train Configuration ; Main Dimensions - PTA Design Review Rev.B DMU M3 | 12/04/2022 | 10/05/2022 | nan | nan | 0 | TK_NotStart | 1208363553 | 461 | 1208363553_461
MRPP2-DE3.14620 | TT_Task | Train Operation Control Description DMU M3 | 08/09/2020 | 23/04/2021 | 08/09/2020 | 26/04/2021 | 0 | TK_Complete | 1208363553 | 463 | 1208363553_463
MRPP2-DE3.14880 | TT_Task | Train Operation Control Description - PTA Design Review Rev. A DMU M3 | 27/04/2021 | 25/05/2021 | 27/04/2021 | 25/05/2021 | 0 | TK_Complete | 1208363553 | 461 | 1208363553_461
MRPP2-DE3.23430 | TT_Task | Train Operation Control Description - Submit Rev. B DMU M3 | 26/05/2021 | 09/08/2021 | 26/05/2021 | 09/08/2021 | 0 | TK_Complete | 1208363553 | 463 | 1208363553_463
MRPP2-DE3.23440 | TT_Task | Train Operation Control Description - PTA Design Review Rev. B DMU M3 | 10/08/2021 | 04/10/2021 | 10/08/2021 | 04/10/2021 | 0 | TK_Complete | 1208363553 | 461 | 1208363553_461
MRPP2-DE3.27630 | TT_Task | Train Operation Control Description - Submit Rev. C DMU M3 | 05/10/2021 | 05/05/2022 | 05/10/2021 | nan | 0 | TK_Active | 1208363553 | 463 | 1208363553_463
MRPP2-DE3.27640 | TT_Task | Train Operation Control Description - PTA Design Review Rev. C DMU M3 | 06/05/2022 | 02/06/2022 | nan | nan | 0 | TK_NotStart | 1208363553 | 461 | 1208363553_461
MRPP2-DE3.14660 | TT_Task | ILS Management Plan DMU M3 | 08/09/2020 | 08/03/2021 | 08/09/2020 | 08/03/2021 | 0 | TK_Complete | 1208363553 | 464 | 1208363553_464
MRPP2-DE3.15000 | TT_Task | ILS Management Plan - PTA Design Review Rev.A DMU M3 | 09/03/2021 | 20/04/2021 | 09/03/2021 | 20/04/2021 | 0 | TK_Complete | 1208363553 | 34 | 1208363553_34
MRPP2-DE3.23190 | TT_Task | ILS Management Plan - Submit Rev.B DMU M3 | 21/04/2021 | 28/04/2022 | 21/04/2021 | nan | 0 | TK_Active | 1208363553 | 464 | 1208363553_464
MRPP2-DE3.23200 | TT_Task | ILS Management Plan - PTA Design Review Rev.B DMU M3 | 29/04/2022 | 26/05/2022 | nan | nan | 0 | TK_NotStart | 1208363553 | 34 | 1208363553_34
MRPP2-DE3.14720 | TT_Task | Maintenance Demonstration plan DMU M3 | 08/09/2020 | 15/03/2021 | 08/09/2020 | 15/03/2021 | 0 | TK_Complete | 1208363553 | 465 | 1208363553_465
MRPP2-DE3.15080 | TT_Task | Maintenance Demonstration plan - PTA Design Review DMU M3 | 16/03/2021 | 15/04/2021 | 16/03/2021 | 15/04/2021 | 0 | TK_Complete | 1208363553 | 465 | 1208363553_465
MRPP2-DE3.15500 | TT_Task | Final Kinematic Envelope Calculation Report DMU M3 | 07/10/2020 | 20/04/2022 | 07/10/2020 | nan | 0 | TK_Active | 1208363553 | 27 | 1208363553_27
MRPP2-DE3.15520 | TT_Task | Final Kinematic Envelope Calculation Report - PTA Design Review DMU M3 | 21/04/2022 | 19/05/2022 | nan | nan | 0 | TK_NotStart | 1208363553 | 28 | 1208363553_28
MRPP2-DE3.14710 | TT_Task | Final Analysis and Simulation - Train Level Performance Report DMU M3 | 07/10/2020 | 03/05/2022 | 07/10/2020 | nan | 0 | TK_Active | 1208363553 | 461 | 1208363553_461
MRPP2-DE3.14760 | TT_Task | Final Analysis and Simulation - Train Level Performance Report - PTA Design Review DMU M3 | 04/05/2022 | 31/05/2022 | nan | nan | 0 | TK_NotStart | 1208363553 | 461 | 1208363553_461
MRPP2-DE3.21260 | TT_Task | Design and CAD guidelines DMU - PTA Review and Approval | 02/10/2020 | 23/10/2020 | 02/10/2020 | 24/10/2020 | 0 | TK_Complete | 1208363553 | 37 | 1208363553_37
MRPP2-DE3.21320 | TT_Task | Maintainability Plan DMU - PTA Review and Approval | 03/12/2020 | 04/01/2021 | 03/12/2020 | 04/01/2021 | 0 | TK_Complete | 1208363553 | 41 | 1208363553_41
MRPP2-DE3.21350 | TT_Task | Life cycle Cost Plan DMU - PTA Review Rev.A | 15/02/2021 | 15/03/2021 | 15/02/2021 | 15/03/2021 | 0 | TK_Complete | 1208363553 | 42 | 1208363553_42
MRPP2-DE3.22790 | TT_Task | Life cycle Cost Plan DMU - Submission Rev.B | 16/03/2021 | 08/02/2022 | 16/03/2021 | nan | 0 | TK_Active | 1208363553 | 42 | 1208363553_42
MRPP2-DE3.22800 | TT_Task | Life cycle Cost Plan DMU - PTA Review Rev.B | 12/04/2022 | 10/05/2022 | nan | nan | 64720 | TK_NotStart | 1208363553 | 42 | 1208363553_42
MRPP2-DE3.21370 | TT_Task | Static Gauge Type Test Procedure DMU - PTA Review and Approval | 25/08/2022 | 21/09/2022 | nan | nan | 1920 | TK_NotStart | 1208363553 | 46 | 1208363553_46
MRPP2-DE3.21410 | TT_Task | Static Sway Type Test Procedure DMU - PTA Review and Approval | 25/08/2022 | 21/09/2022 | nan | nan | 1920 | TK_NotStart | 1208363553 | 44 | 1208363553_44
MRPP2-DE3.21440 | TT_Task | Lifting Ability Type Test Procedure DMU - PTA Review and Approval | 25/08/2022 | 21/09/2022 | nan | nan | 1920 | TK_NotStart | 1208363553 | 45 | 1208363553_45
MRPP2-DE3.21750 | TT_Task | Type Test Specification - Gauging (Static + Kinematic) DMU - PTA Review and Approval | 25/08/2022 | 21/09/2022 | nan | nan | 1920 | TK_NotStart | 1208363553 | 58 | 1208363553_58
MRPP2-DE3.21870 | TT_Task | Operation ; MaintenanceManuals Plan DMU - PTA Review and Approval | 27/09/2022 | 24/10/2022 | 04/01/2022 | nan | 1736 | TK_Active | 1208363553 | 41 | 1208363553_41
MRPP2-DE3.21940 | TT_Task | IDTP Detail Specification DMU - PTA Review and Approval | 27/09/2022 | 24/10/2022 | nan | nan | 1744 | TK_NotStart | 1208363553 | 43 | 1208363553_43
MRPP2-DE3.21990 | TT_Task | Driving Functional Type Test Procedure - DRV DMU - PTA Review and Approval | 27/09/2022 | 24/10/2022 | nan | nan | 1744 | TK_NotStart | 1208363553 | 47 | 1208363553_47
MRPP2-DE3.22060 | TT_Task | Fire ; Smoke Detection Functional Type Test Procedure ? FSD DMU - PTA Review and Approval | 27/09/2022 | 24/10/2022 | nan | nan | 1744 | TK_NotStart | 1208363553 | 48 | 1208363553_48
MRPP2-DE3.22080 | TT_Task | Kinematic Envelope Type Test Procedure DMU - PTA Review and Approval | 27/09/2022 | 24/10/2022 | nan | nan | 1744 | TK_NotStart | 1208363553 | 49 | 1208363553_49
MRPP2-DE3.22100 | TT_Task | Traction and Braking Performance Dynamic Type Test Procedure DMU - PTA Review and Approval | 27/09/2022 | 24/10/2022 | nan | nan | 1744 | TK_NotStart | 1208363553 | 50 | 1208363553_50
MRPP2-DE3.22110 | TT_Task | WSP Type Test Procedure DMU - PTA Review and Approval | 27/09/2022 | 24/10/2022 | nan | nan | 1744 | TK_NotStart | 1208363553 | 51 | 1208363553_51
MRPP2-DE3.22140 | TT_Task | Resistance to Motion Type Test Procedure DMU - PTA Review and Approval | 27/09/2022 | 24/10/2022 | nan | nan | 1744 | TK_NotStart | 1208363553 | 52 | 1208363553_52
MRPP2-DE3.22150 | TT_Task | Journey Time Check Type Test Procedure DMU - PTA Review and Approval | 27/09/2022 | 24/10/2022 | nan | nan | 1744 | TK_NotStart | 1208363553 | 53 | 1208363553_53
MRPP2-DE3.22160 | TT_Task | Rescue Type Test Procedure DMU - PTA Review and Approval | 27/09/2022 | 24/10/2022 | nan | nan | 1744 | TK_NotStart | 1208363553 | 54 | 1208363553_54
MRPP2-DE3.22170 | TT_Task | Energy Consumption Type Test Procedure DMU - PTA Review and Approval | 27/09/2022 | 24/10/2022 | nan | nan | 1744 | TK_NotStart | 1208363553 | 55 | 1208363553_55
MRPP2-DE3.22200 | TT_Task | Ride Comfort Type Test Procedure DMU - PTA Review and Approval | 27/09/2022 | 24/10/2022 | nan | nan | 1744 | TK_NotStart | 1208363553 | 56 | 1208363553_56
MRPP2-DE3.22250 | TT_Task | Operation ; Maintenance Manuals DMU - PTA Review and Approval | 20/02/2023 | 17/03/2023 | nan | nan | 1440 | TK_NotStart | 1208363553 | 41 | 1208363553_41
MRPP2-DE3.22230 | TT_Task | Training Manual for Train Operators?? DMU - PTA Review and Approval | 20/02/2023 | 17/03/2023 | nan | nan | 1440 | TK_NotStart | 1208363553 | 61 | 1208363553_61
MRPP2-DE3.22240 | TT_Task | Training Manual for Maintenance Staff DMU - PTA Review and Approval | 20/02/2023 | 17/03/2023 | nan | nan | 1440 | TK_NotStart | 1208363553 | 61 | 1208363553_61
MRPP2-DE1.14763 | TT_Task | Car Static Profile ; Carbody Cross Section Report DMU M1 | 19/12/2019 | 21/08/2020 | 19/12/2019 | 21/08/2020 | 0 | TK_Complete | 1208363553 | 62 | 1208363553_62
MRPP2-DE1.14783 | TT_Task | Car Static Profile ; Carbody Cross Section Report - PTA Design Review DMU M1 | 24/08/2020 | 17/09/2020 | 24/08/2020 | 17/09/2020 | 0 | TK_Complete | 1208363553 | 62 | 1208363553_62
MRPP2-DE1.13953 | TT_Task | Preliminary Design Specification ? Carbody Structure including Load Cases DMU M1 | 11/03/2020 | 25/09/2020 | 11/03/2020 | 28/09/2020 | 0 | TK_Complete | 1208363553 | 63 | 1208363553_63
MRPP2-DE1.14153 | TT_Task | Preliminary Design Specification ? Carbody Structure including Load Cases - PTA Design Review Rev.A DMU M1 | 29/09/2020 | 22/10/2020 | 29/09/2020 | 22/10/2020 | 0 | TK_Complete | 1208363553 | 63 | 1208363553_63
MRPP2-DE1.15943 | TT_Task | Preliminary Design Specification ? Carbody Structure including Load Cases - Submit Rev.B DMU M1 | 23/10/2020 | 03/02/2021 | 23/10/2020 | 03/02/2021 | 0 | TK_Complete | 1208363553 | 63 | 1208363553_63
MRPP2-DE1.15953 | TT_Task | Preliminary Design Specification ? Carbody Structure including Load Cases - PTA Design Review Rev.B DMU M1 | 04/02/2021 | 04/03/2021 | 04/02/2021 | 04/03/2021 | 0 | TK_Complete | 1208363553 | 63 | 1208363553_63
MRPP2-DE1.16063 | TT_Task | Preliminary Design Specification ? Carbody Structure including Load Cases - Submit Rev.C DMU M1 | 05/03/2021 | 23/04/2021 | 05/03/2021 | 23/04/2021 | 0 | TK_Complete | 1208363553 | 63 | 1208363553_63
MRPP2-DE1.16073 | TT_Task | Preliminary Design Specification ? Carbody Structure including Load Cases - PTA Design Review Rev.C DMU M1 | 27/04/2021 | 24/05/2021 | 27/04/2021 | 24/05/2021 | 0 | TK_Complete | 1208363553 | 63 | 1208363553_63
MRPP2-DE2.15153 | TT_Task | Preliminary Carbody crashworthiness report DMU M2 | 24/07/2020 | 19/05/2021 | 24/07/2020 | 19/05/2021 | 0 | TK_Complete | 1208363553 | 466 | 1208363553_466
MRPP2-DE2.15313 | TT_Task | Preliminary Carbody crashworthiness report - PTA Design Review Rev.A DMU M2 | 20/05/2021 | 17/06/2021 | 20/05/2021 | 17/06/2021 | 0 | TK_Complete | 1208363553 | 466 | 1208363553_466
MRPP2-DE2.19323 | TT_Task | Preliminary Carbody crashworthiness report - Submit Rev.B DMU M2 | 18/06/2021 | 11/03/2022 | 18/06/2021 | nan | 0 | TK_Active | 1208363553 | 466 | 1208363553_466
MRPP2-DE2.19333 | TT_Task | Preliminary Carbody crashworthiness report - PTA Design Review Rev.B DMU M2 | 12/04/2022 | 10/05/2022 | nan | nan | 0 | TK_NotStart | 1208363553 | 466 | 1208363553_466
MRPP2-DE3.15260 | TT_Task | Car End Clearance Report DMU M3 | 03/09/2020 | 24/06/2021 | 03/09/2020 | 24/06/2021 | 0 | TK_Complete | 1208363553 | 66 | 1208363553_66
MRPP2-DE3.15280 | TT_Task | Car End Clearance Report - PTA Design Review Rev.A DMU M3 | 25/06/2021 | 27/07/2021 | 25/06/2021 | 27/07/2021 | 0 | TK_Complete | 1208363553 | 67 | 1208363553_67
MRPP2-DE3.24470 | TT_Task | Car End Clearance Report - Submit Rev.A DMU M3 | 28/07/2021 | 26/04/2022 | 28/07/2021 | nan | 0 | TK_Active | 1208363553 | 66 | 1208363553_66
MRPP2-DE3.24480 | TT_Task | Car End Clearance Report - Submit Rev.B DMU M3 | 27/04/2022 | 24/05/2022 | nan | nan | 0 | TK_NotStart | 1208363553 | 66 | 1208363553_66
MRPP2-DE3.15340 | TT_Task | Detailed Design Specification ? Carbody Structure DMU M3 | 02/10/2020 | 19/10/2021 | 02/10/2020 | 19/10/2021 | 0 | TK_Complete | 1208363553 | 467 | 1208363553_467
MRPP2-DE3.15360 | TT_Task | Detailed Design Specification ? Carbody Structure - PTA Design Review Rev.A DMU M3 | 20/10/2021 | 22/11/2021 | 20/10/2021 | 22/11/2021 | 0 | TK_Complete | 1208363553 | 467 | 1208363553_467
MRPP2-DE3.28710 | TT_Task | Detailed Design Specification ? Carbody Structure - Submit Rev.B DMU M3 | 23/11/2021 | 19/04/2022 | 23/11/2021 | nan | 0 | TK_Active | 1208363553 | 467 | 1208363553_467
MRPP2-DE3.28720 | TT_Task | Detailed Design Specification ? Carbody Structure - PTA Design Review Rev.B DMU M3 | 20/04/2022 | 18/05/2022 | nan | nan | 0 | TK_NotStart | 1208363553 | 467 | 1208363553_467
MRPP2-DE3.16500 | TT_Task | Equipment Mounting Detailed Design Specification (Roof, Underframe) DMU M3 | 23/06/2021 | 29/09/2021 | 23/06/2021 | 29/09/2021 | 0 | TK_Complete | 1208363553 | 468 | 1208363553_468
MRPP2-DE3.16520 | TT_Task | Equipment Mounting Detailed Design Specification (Roof, Underframe) - PTA Design Review Rev.A DMU M3 | 30/09/2021 | 10/11/2021 | 30/09/2021 | 10/11/2021 | 0 | TK_Complete | 1208363553 | 468 | 1208363553_468
MRPP2-DE3.28730 | TT_Task | Equipment Mounting Detailed Design Specification (Roof, Underframe) - Submit Rev.B DMU M3 | 11/11/2021 | 18/04/2022 | 11/11/2021 | nan | 0 | TK_Active | 1208363553 | 468 | 1208363553_468
MRPP2-DE3.28740 | TT_Task | Equipment Mounting Detailed Design Specification (Roof, Underframe) - PTA Design Review Rev.B DMU M3 | 19/04/2022 | 17/05/2022 | nan | nan | 0 | TK_NotStart | 1208363553 | 468 | 1208363553_468
MRPP2-DE3.16140 | TT_Task | Carbody Structure Detailed FEA Report DMU M3 | 30/09/2021 | 22/03/2022 | 30/09/2021 | nan | 0 | TK_Active | 1208363553 | 70 | 1208363553_70
MRPP2-DE3.16160 | TT_Task | Carbody Structure Detailed FEA Report - PTA Design Review DMU M3 | 12/04/2022 | 10/05/2022 | nan | nan | 0 | TK_NotStart | 1208363553 | 70 | 1208363553_70
MRPP2-DE3.16180 | TT_Task | Carbody crashworthiness report DMU M3 | 19/04/2021 | 13/04/2022 | 19/04/2021 | nan | 0 | TK_Active | 1208363553 | 466 | 1208363553_466
MRPP2-DE3.16200 | TT_Task | Carbody crashworthiness report - PTA Design Review DMU M3 | 14/04/2022 | 12/05/2022 | nan | nan | 0 | TK_NotStart | 1208363553 | 466 | 1208363553_466
MRPP2-DE3.15580 | TT_Task | Detailed Design Specification- Partition Wall DMU M3 | 29/10/2020 | 12/04/2022 | 29/10/2020 | 28/01/2022 | 0 | TK_Complete | 1208363553 | 469 | 1208363553_469
MRPP2-DE3.15590 | TT_Task | Detailed Design Specification- Partition Wall - PTA Design Review Rev.A DMU M3 | 19/05/2022 | 16/06/2022 | 31/01/2022 | 22/03/2022 | 0 | TK_Complete | 1208363553 | 469 | 1208363553_469
MRPP2-DE3.29780 | TT_Task | Detailed Design Specification- Partition Wall - Submit Rev.B DMU M3 | 04/04/2022 | 19/04/2022 | 23/03/2022 | nan | 0 | TK_Active | 1208363553 | 469 | 1208363553_469
MRPP2-DE3.29790 | TT_Task | Detailed Design Specification- Partition Wall - PTA Design Review Rev.B DMU M3 | 12/04/2022 | 10/05/2022 | nan | nan | 0 | TK_NotStart | 1208363553 | 469 | 1208363553_469
MRPP2-DE3.21380 | TT_Task | Watertightness Type Test Procedure DMU - PTA Review and Approval | 28/10/2022 | 24/11/2022 | nan | nan | 1560 | TK_NotStart | 1208363553 | 71 | 1208363553_71
MRPP2-DE3.21400 | TT_Task | Car-Car Clearance Type Test Procedure DMU - PTA Review and Approval | 24/11/2022 | 21/12/2022 | nan | nan | 1408 | TK_NotStart | 1208363553 | 72 | 1208363553_72
MRPP2-DE3.21560 | TT_Task | Test Specification of Damper DMU - PTA Review and Approval | 02/09/2022 | 30/09/2022 | nan | nan | 1872 | TK_NotStart | 1208363553 | 75 | 1208363553_75
MRPP2-DE3.21390 | TT_Task | Car-Bogie Clearance Type Test Procedure DMU - PTA Review and Approval | 01/09/2022 | 29/09/2022 | nan | nan | 1880 | TK_NotStart | 1208363553 | 72 | 1208363553_72
MRPP2-DE3.21600 | TT_Task | Type Test Specification - Windscreen DMU - PTA Review and Approval | 15/12/2022 | 16/01/2023 | nan | nan | 1288 | TK_NotStart | 1208363553 | 76 | 1208363553_76
MRPP2-DE3.21610 | TT_Task | Type Test Specification - Windows DMU - PTA Review and Approval | 19/12/2022 | 18/01/2023 | nan | nan | 1272 | TK_NotStart | 1208363553 | 470 | 1208363553_470
MRPP2-DE3.21910 | TT_Task | Wiper Performance Type Test Procedure DMU - PTA Review and Approval | 19/12/2022 | 18/01/2023 | nan | nan | 1272 | TK_NotStart | 1208363553 | 78 | 1208363553_78
MRPP2-DE1.13933 | TT_Task | System Description of Bogies DMU M1 | 07/02/2020 | 12/08/2020 | 07/02/2020 | 12/08/2020 | 0 | TK_Complete | 1208363553 | 79 | 1208363553_79
MRPP2-DE1.14073 | TT_Task | System Description of Bogies - PTA Design Review Rev.A DMU M1 | 13/08/2020 | 07/09/2020 | 13/08/2020 | 07/09/2020 | 0 | TK_Complete | 1208363553 | 80 | 1208363553_80
MRPP2-DE1.15733 | TT_Task | System Description of Bogies - Resubmit Rev.B DMU M1 | 08/09/2020 | 13/10/2020 | 08/09/2020 | 13/10/2020 | 0 | TK_Complete | 1208363553 | 79 | 1208363553_79
MRPP2-DE1.15743 | TT_Task | System Description of Bogies - PTA Design Review Rev.B DMU M1 | 14/10/2020 | 09/11/2020 | 14/10/2020 | 09/11/2020 | 0 | TK_Complete | 1208363553 | 80 | 1208363553_80
MRPP2-DE2.15983 | TT_Task | Technical specification of Secondary suspension DMU M2 | 29/06/2020 | 20/11/2020 | 29/06/2020 | 20/11/2020 | 0 | TK_Complete | 1208363553 | 81 | 1208363553_81
MRPP2-DE2.16003 | TT_Task | Technical specification of Secondary suspension - PTA Design Review DMU M2 | 23/11/2020 | 16/12/2020 | 23/11/2020 | 16/12/2020 | 0 | TK_Complete | 1208363553 | 81 | 1208363553_81
MRPP2-DE2.15703 | TT_Task | Technical Description for Wheel Slip Detection and Correction System DMU M2 | 29/06/2020 | 12/01/2021 | 29/06/2020 | 12/01/2021 | 0 | TK_Complete | 1208363553 | 82 | 1208363553_82
MRPP2-DE2.15723 | TT_Task | Technical Description for Wheel Slip Detection and Correction System - PTA Design Review Rev.A DMU M2 | 13/01/2021 | 11/02/2021 | 13/01/2021 | 11/02/2021 | 0 | TK_Complete | 1208363553 | 82 | 1208363553_82
MRPP2-DE2.18923 | TT_Task | Technical Description for Wheel Slip Detection and Correction System - Submit Rev.B DMU M2 | 13/02/2020 | 17/05/2021 | 13/02/2020 | 17/05/2021 | 0 | TK_Complete | 1208363553 | 82 | 1208363553_82
MRPP2-DE2.18933 | TT_Task | Technical Description for Wheel Slip Detection and Correction System - PTA Design Review Rev.B DMU M2 | 18/05/2021 | 15/06/2021 | 18/05/2021 | 15/06/2021 | 0 | TK_Complete | 1208363553 | 82 | 1208363553_82
MRPP2-DE2.19443 | TT_Task | Technical Description for Wheel Slip Detection and Correction System - Submit Rev.C DMU M2 | 16/06/2021 | 25/11/2021 | 16/06/2021 | 25/11/2021 | 0 | TK_Complete | 1208363553 | 82 | 1208363553_82
MRPP2-DE2.19453 | TT_Task | Technical Description for Wheel Slip Detection and Correction System - PTA Design Review Rev.C DMU M2 | 26/11/2021 | 23/12/2021 | 26/11/2021 | 12/01/2022 | 0 | TK_Complete | 1208363553 | 82 | 1208363553_82
MRPP2-DE2.15943 | TT_Task | Technical Specification and drawings of Axle Dive Gear Unit DMU M2 | 10/07/2020 | 08/01/2021 | 10/07/2020 | 08/01/2021 | 0 | TK_Complete | 1208363553 | 471 | 1208363553_471
MRPP2-DE2.15963 | TT_Task | Technical Specification and drawings of Axle Dive Gear Unit - PTA Design Review Rev.A DMU M2 | 11/01/2021 | 09/02/2021 | 11/01/2021 | 09/02/2021 | 0 | TK_Complete | 1208363553 | 471 | 1208363553_471
MRPP2-DE2.18943 | TT_Task | Technical Specification and drawings of Axle Dive Gear Unit - Submit Rev.B DMU M2 | 10/02/2021 | 29/03/2021 | 10/02/2021 | 29/03/2021 | 0 | TK_Complete | 1208363553 | 471 | 1208363553_471
MRPP2-DE2.18953 | TT_Task | Technical Specification and drawings of Axle Dive Gear Unit - PTA Design Review Rev.B DMU M2 | 30/03/2021 | 29/04/2021 | 30/03/2021 | 29/04/2021 | 0 | TK_Complete | 1208363553 | 471 | 1208363553_471
MRPP2-DE2.19243 | TT_Task | Technical Specification and drawings of Axle Dive Gear Unit - Submit Rev.C DMU M2 | 30/04/2021 | 21/04/2022 | 30/04/2021 | nan | 0 | TK_Active | 1208363553 | 471 | 1208363553_471
MRPP2-DE2.19253 | TT_Task | Technical Specification and drawings of Axle Dive Gear Unit - PTA Design Review Rev.C DMU M2 | 22/04/2022 | 20/05/2022 | nan | nan | 0 | TK_NotStart | 1208363553 | 471 | 1208363553_471
MRPP2-DE3.15820 | TT_Task | Final Analysis and simulations ? Vehicle Dynamic Analysis Report of Bogie DMU M3 | 04/12/2020 | 07/04/2022 | 04/12/2020 | nan | 0 | TK_Active | 1208363553 | 84 | 1208363553_84
MRPP2-DE3.15840 | TT_Task | Final Analysis and simulations ? Vehicle Dynamic Analysis Report of Bogie - PTA Design Review DMU M3 | 12/04/2022 | 10/05/2022 | nan | nan | 0 | TK_NotStart | 1208363553 | 84 | 1208363553_84
MRPP2-DE3.15460 | TT_Task | FEA Report of Bogie Frame DMU M3 | 04/12/2020 | 02/05/2022 | 04/12/2020 | nan | 0 | TK_Active | 1208363553 | 85 | 1208363553_85
MRPP2-DE3.15480 | TT_Task | FEA Report of Bogie Frame - PTA Design Review DMU M3 | 03/05/2022 | 30/05/2022 | nan | nan | 0 | TK_NotStart | 1208363553 | 85 | 1208363553_85
MRPP2-DE3.15930 | TT_Task | Detail Description of Bogie Brake Equipment DMU M3 | 10/12/2020 | 18/05/2021 | 10/12/2020 | 18/05/2021 | 0 | TK_Complete | 1208363553 | 86 | 1208363553_86
MRPP2-DE3.16090 | TT_Task | Detail Description of Bogie Brake Equipment - PTA Design Review Rev.A DMU M3 | 19/05/2021 | 17/06/2021 | 19/05/2021 | 17/06/2021 | 0 | TK_Complete | 1208363553 | 86 | 1208363553_86
MRPP2-DE3.24110 | TT_Task | Detail Description of Bogie Brake Equipment - Submit Rev.B DMU M3 | 18/06/2021 | 11/03/2022 | 18/06/2021 | nan | 0 | TK_Active | 1208363553 | 86 | 1208363553_86
MRPP2-DE3.24120 | TT_Task | Detail Description of Bogie Brake Equipment - PTA Design Review Rev.B DMU M3 | 12/04/2022 | 10/05/2022 | nan | nan | 0 | TK_NotStart | 1208363553 | 86 | 1208363553_86
MRPP2-DE3.16380 | TT_Task | Thermal Calculations of Wheel DMU M3 | 17/12/2020 | 09/03/2021 | 17/12/2020 | 09/03/2021 | 0 | TK_Complete | 1208363553 | 87 | 1208363553_87
MRPP2-DE3.16400 | TT_Task | Thermal Calculations of Wheel - PTA Design Review DMU M3 | 10/03/2021 | 08/04/2021 | 10/03/2021 | 08/04/2021 | 0 | TK_Complete | 1208363553 | 87 | 1208363553_87
MRPP2-DE3.15940 | TT_Task | Wheel Stress calculations DMU M3 | 17/12/2020 | 30/04/2021 | 17/12/2020 | 30/04/2021 | 0 | TK_Complete | 1208363553 | 472 | 1208363553_472
MRPP2-DE3.15990 | TT_Task | Wheel Stress calculations - PTA Design Review Rev.A DMU M3 | 03/05/2021 | 26/05/2021 | 03/05/2021 | 26/05/2021 | 0 | TK_Complete | 1208363553 | 472 | 1208363553_472
MRPP2-DE3.23560 | TT_Task | Wheel Stress calculations - Submit Rev.B DMU M3 | 27/05/2021 | 31/03/2022 | 27/05/2021 | nan | 0 | TK_Active | 1208363553 | 472 | 1208363553_472
MRPP2-DE3.23570 | TT_Task | Wheel Stress calculations - PTA Design Review Rev.B DMU M3 | 12/04/2022 | 10/05/2022 | nan | nan | 0 | TK_NotStart | 1208363553 | 472 | 1208363553_472
MRPP2-DE3.15920 | TT_Task | Axle strength calculations DMU M3 | 17/12/2020 | 20/04/2021 | 17/12/2020 | 20/04/2021 | 0 | TK_Complete | 1208363553 | 473 | 1208363553_473
MRPP2-DE3.16060 | TT_Task | Axle strength calculations - PTA Design Review Rev.A DMU M3 | 21/04/2021 | 18/05/2021 | 21/04/2021 | 18/05/2021 | 0 | TK_Complete | 1208363553 | 473 | 1208363553_473
MRPP2-DE3.23450 | TT_Task | Axle strength calculations - Submit Rev.B DMU M3 | 19/05/2021 | 12/04/2022 | 19/05/2021 | nan | 0 | TK_Active | 1208363553 | 473 | 1208363553_473
MRPP2-DE3.23460 | TT_Task | Axle strength calculations - PTA Design Review Rev.B DMU M3 | 13/04/2022 | 11/05/2022 | nan | nan | 0 | TK_NotStart | 1208363553 | 473 | 1208363553_473
MRPP2-DE3.16420 | TT_Task | FEA Report of Axle Box DMU M3 | 17/12/2020 | 09/03/2021 | 17/12/2020 | 09/03/2021 | 0 | TK_Complete | 1208363553 | 91 | 1208363553_91
MRPP2-DE3.16430 | TT_Task | FEA Report of Axle Box - PTA Design Review DMU M3 | 10/03/2021 | 08/04/2021 | 10/03/2021 | 08/04/2021 | 0 | TK_Complete | 1208363553 | 91 | 1208363553_91
MRPP2-DE3.16300 | TT_Task | Technical Specification and drawings of Axle drive gear unit DMU M3 | 17/12/2020 | 08/09/2021 | 17/12/2020 | 08/09/2021 | 0 | TK_Complete | 1208363553 | 474 | 1208363553_474
MRPP2-DE3.16320 | TT_Task | Technical Specification and drawings of Axle drive gear unit - PTA Design Review DMU Stage | 09/09/2021 | 07/10/2021 | 09/09/2021 | 07/10/2021 | 0 | TK_Complete | 1208363553 | 474 | 1208363553_474
MRPP2-DE3.16460 | TT_Task | L10 Calculation report of Axle Box Bearing DMU M3 | 17/12/2020 | 28/06/2021 | 17/12/2020 | 28/06/2021 | 0 | TK_Complete | 1208363553 | 89 | 1208363553_89
MRPP2-DE3.16480 | TT_Task | L10 Calculation report of Axle Box Bearing - PTA Design Review Rev.A DMU M3 | 29/06/2021 | 28/07/2021 | 29/06/2021 | 28/07/2021 | 0 | TK_Complete | 1208363553 | 89 | 1208363553_89
MRPP2-DE3.26990 | TT_Task | L10 Calculation report of Axle Box Bearing Submit Rev.B DMU M3 | 29/07/2021 | 04/05/2022 | 29/07/2021 | nan | 0 | TK_Active | 1208363553 | 89 | 1208363553_89
MRPP2-DE3.27000 | TT_Task | L10 Calculation report of Axle Box Bearing - PTA Design Review Rev.B DMU M3 | 05/05/2022 | 01/06/2022 | nan | nan | 0 | TK_NotStart | 1208363553 | 89 | 1208363553_89
MRPP2-DE3.21290 | TT_Task | Technical Drawings of Wheel Flange Lubricator DMU - PTA Review and Approval | 03/12/2020 | 04/01/2021 | 03/12/2020 | 04/01/2021 | 0 | TK_Complete | 1208363553 | 93 | 1208363553_93
MRPP2-DE3.21420 | TT_Task | Bogie Rotational Resistance Type Test Procedure DMU - PTA Review and Approval | 25/11/2022 | 22/12/2022 | nan | nan | 1400 | TK_NotStart | 1208363553 | 94 | 1208363553_94
MRPP2-DE3.21430 | TT_Task | Wheel Unloading Type Test Procedure DMU - PTA Review and Approval | 25/11/2022 | 22/12/2022 | nan | nan | 1400 | TK_NotStart | 1208363553 | 475 | 1208363553_475
MRPP2-DE3.21540 | TT_Task | Test Specification of Bogie Frame static load / Fatigue load DMU - PTA Review and Approval | 31/10/2022 | 25/11/2022 | nan | nan | 1552 | TK_NotStart | 1208363553 | 96 | 1208363553_96
MRPP2-DE3.21550 | TT_Task | Test Specification of Primary suspension DMU - PTA Review and Approval | 31/10/2022 | 25/11/2022 | nan | nan | 1552 | TK_NotStart | 1208363553 | 97 | 1208363553_97
MRPP2-DE3.21570 | TT_Task | Test Specification of Wheel DMU - PTA Review and Approval | 31/10/2022 | 25/11/2022 | nan | nan | 1552 | TK_NotStart | 1208363553 | 475 | 1208363553_475
MRPP2-DE3.21580 | TT_Task | Test specification of Axle DMU - PTA Review and Approval | 31/10/2022 | 25/11/2022 | nan | nan | 1552 | TK_NotStart | 1208363553 | 475 | 1208363553_475
MRPP2-DE3.21660 | TT_Task | Test specification of Wheel Flange Lubricator DMU - PTA Review and Approval | 23/11/2021 | 20/12/2021 | 23/11/2021 | 20/12/2021 | 0 | TK_Complete | 1208363553 | 93 | 1208363553_93
MRPP2-DE3.21690 | TT_Task | Inspection instruction of complete Bogie DMU - PTA Review and Approval | 19/01/2023 | 16/02/2023 | nan | nan | 1112 | TK_NotStart | 1208363553 | 101 | 1208363553_101
MRPP2-DE3.21810 | TT_Task | Software document for propulsion system DMU - PTA Review and Approval | 27/10/2022 | 23/11/2022 | nan | nan | 1568 | TK_NotStart | 1208363553 | 102 | 1208363553_102
MRPP2-DE3.21950 | TT_Task | Test Specification of Driving gear system - DMU DMU - PTA Review and Approval (Removed from Design Plan) | 08/03/2022 | 04/04/2022 | 08/03/2022 | 04/04/2022 | 0 | TK_Complete | 1208363553 | 474 | 1208363553_474
MRPP2-DE3.21960 | TT_Task | Test Specification of Gearbox - DMU DMU - PTA Review and Approval | 04/01/2023 | 01/02/2023 | nan | nan | 1200 | TK_NotStart | 1208363553 | 474 | 1208363553_474
MRPP2-DE1.13943 | TT_Task | System Description of Brakes DMU M1 | 07/02/2020 | 02/10/2020 | 07/02/2020 | 02/10/2020 | 0 | TK_Complete | 1208363553 | 476 | 1208363553_476
MRPP2-DE1.14123 | TT_Task | System Description of Brakes - PTA Design Review Rev.A DMU M1 | 05/10/2020 | 29/10/2020 | 05/10/2020 | 29/10/2020 | 0 | TK_Complete | 1208363553 | 476 | 1208363553_476
MRPP2-DE1.15963 | TT_Task | System Description of Brakes - Submit Rev.B DMU M1 | 30/10/2020 | 27/11/2020 | 30/10/2020 | 27/11/2020 | 0 | TK_Complete | 1208363553 | 476 | 1208363553_476
MRPP2-DE1.15973 | TT_Task | System Description of Brakes - PTA Design Review Rev.B DMU M1 | 30/11/2020 | 18/01/2021 | 30/11/2020 | 18/01/2021 | 0 | TK_Complete | 1208363553 | 476 | 1208363553_476
MRPP2-DE2.16383 | TT_Task | Detailed Technical Description of Brake System (Including Brake Control Equipment) DMU M2 | 29/06/2020 | 25/03/2021 | 29/06/2020 | 25/03/2021 | 0 | TK_Complete | 1208363553 | 476 | 1208363553_476
MRPP2-DE2.16403 | TT_Task | Detailed Technical Description of Brake System (Including Brake Control Equipment) - PTA Design Review Rev.A DMU M2 | 26/03/2021 | 27/04/2021 | 26/03/2021 | 27/04/2021 | 0 | TK_Complete | 1208363553 | 476 | 1208363553_476
MRPP2-DE2.19223 | TT_Task | Detailed Technical Description of Brake System (Including Brake Control Equipment) - Submit Rev.B DMU M2 | 28/04/2021 | 28/07/2021 | 28/04/2021 | 28/07/2021 | 0 | TK_Complete | 1208363553 | 476 | 1208363553_476
MRPP2-DE2.19233 | TT_Task | Detailed Technical Description of Brake System (Including Brake Control Equipment) - PTA Design Review Rev.B DMU M2 | 29/07/2021 | 31/08/2021 | 29/07/2021 | 31/08/2021 | 0 | TK_Complete | 1208363553 | 476 | 1208363553_476
MRPP2-DE2.15143 | TT_Task | Detailed Technical Description of Air Distribution and Supply System DMU M2 | 29/06/2020 | 05/02/2021 | 29/06/2020 | 05/02/2021 | 0 | TK_Complete | 1208363553 | 106 | 1208363553_106
MRPP2-DE2.15283 | TT_Task | Detailed Technical Description of Air Distribution and Supply System - PTA Design Review Rev.A DMU M2 | 08/02/2021 | 08/03/2021 | 08/02/2021 | 08/03/2021 | 0 | TK_Complete | 1208363553 | 107 | 1208363553_107
MRPP2-DE2.19043 | TT_Task | Detailed Technical Description of Air Distribution and Supply System - Submit Rev.B DMU M2 | 09/03/2021 | 28/04/2021 | 09/03/2021 | 28/04/2021 | 0 | TK_Complete | 1208363553 | 106 | 1208363553_106
MRPP2-DE2.19053 | TT_Task | Detailed Technical Description of Air Distribution and Supply System - PTA Design Review Rev.B DMU M2 | 29/04/2021 | 26/05/2021 | 29/04/2021 | 26/05/2021 | 0 | TK_Complete | 1208363553 | 107 | 1208363553_107
MRPP2-DE3.14610 | TT_Task | Detail Design Specification ? Pneumatic Piping including Schematic Diagrams DMU M3 | 25/08/2020 | 15/03/2021 | 25/08/2020 | 15/03/2021 | 0 | TK_Complete | 1208363553 | 108 | 1208363553_108
MRPP2-DE3.14850 | TT_Task | Detail Design Specification ? Pneumatic Piping including Schematic Diagrams - PTA Design Review Rev.A DMU M3 | 16/03/2021 | 15/04/2021 | 16/03/2021 | 15/04/2021 | 0 | TK_Complete | 1208363553 | 108 | 1208363553_108
MRPP2-DE3.23150 | TT_Task | Detail Design Specification ? Pneumatic Piping including Schematic Diagrams - Submit Rev.B DMU M3 | 16/04/2021 | 08/07/2021 | 16/04/2021 | 08/07/2021 | 0 | TK_Complete | 1208363553 | 108 | 1208363553_108
MRPP2-DE3.23160 | TT_Task | Detail Design Specification ? Pneumatic Piping including Schematic Diagrams - PTA Design Review Rev.B DMU M3 | 09/07/2021 | 11/08/2021 | 09/07/2021 | 11/08/2021 | 0 | TK_Complete | 1208363553 | 108 | 1208363553_108
MRPP2-DE3.27050 | TT_Task | Detail Design Specification ? Pneumatic Piping including Schematic Diagrams - Submit Rev.C DMU M3 | 12/08/2021 | 03/11/2021 | 12/08/2021 | 03/11/2021 | 0 | TK_Complete | 1208363553 | 108 | 1208363553_108
MRPP2-DE3.27060 | TT_Task | Detail Design Specification ? Pneumatic Piping including Schematic Diagrams - PTA Design Review Rev.C DMU M3 | 04/11/2021 | 26/11/2021 | 04/11/2021 | 26/11/2021 | 0 | TK_Complete | 1208363553 | 108 | 1208363553_108
MRPP2-DE3.15740 | TT_Task | Brake Performance Calculations Report DMU M3 | 23/11/2020 | 19/05/2021 | 23/11/2020 | 19/05/2021 | 0 | TK_Complete | 1208363553 | 477 | 1208363553_477
MRPP2-DE3.15760 | TT_Task | Brake Performance Calculations Report - PTA Design Review Rev.A DMU M3 | 20/05/2021 | 17/06/2021 | 20/05/2021 | 17/06/2021 | 0 | TK_Complete | 1208363553 | 477 | 1208363553_477
MRPP2-DE3.23940 | TT_Task | Brake Performance Calculations Report - Submit Rev.B DMU M3 | 18/06/2021 | 21/04/2022 | 18/06/2021 | nan | 0 | TK_Active | 1208363553 | 477 | 1208363553_477
MRPP2-DE3.23950 | TT_Task | Brake Performance Calculations Report - PTA Design Review Rev.B DMU M3 | 22/04/2022 | 20/05/2022 | nan | nan | 0 | TK_NotStart | 1208363553 | 477 | 1208363553_477
MRPP2-DE3.21340 | TT_Task | Air Consumption calculations DMU - PTA Review and Approval | 25/03/2021 | 23/04/2021 | 25/03/2021 | 23/04/2021 | 0 | TK_Complete | 1208363553 | 111 | 1208363553_111
MRPP2-DE3.21710 | TT_Task | Test Specification for Air Supply System DMU - PTA Review and Approval | 16/01/2023 | 13/02/2023 | nan | nan | 1136 | TK_NotStart | 1208363553 | 112 | 1208363553_112
MRPP2-DE3.21800 | TT_Task | Software document for Brake system DMU - PTA Review and Approval | 16/01/2023 | 13/02/2023 | nan | nan | 1136 | TK_NotStart | 1208363553 | 116 | 1208363553_116
MRPP2-DE3.22000 | TT_Task | Air System Functional Type Test Procedure - AIR DMU - PTA Review and Approval | 16/01/2023 | 13/02/2023 | nan | nan | 1136 | TK_NotStart | 1208363553 | 112 | 1208363553_112
MRPP2-DE3.22010 | TT_Task | Brake Functional Type Test Procedure ? BRK DMU - PTA Review and Approval | 10/11/2022 | 07/12/2022 | nan | nan | 1488 | TK_NotStart | 1208363553 | 113 | 1208363553_113
MRPP2-DE3.22090 | TT_Task | Air System Performance Type Test Procedure DMU - PTA Review and Approval | 10/11/2022 | 07/12/2022 | nan | nan | 1488 | TK_NotStart | 1208363553 | 112 | 1208363553_112
MRPP2-DE3.22120 | TT_Task | Parking Brake/ Holding Brake Type Test Procedure DMU - PTA Review and Approval | 10/11/2022 | 07/12/2022 | nan | nan | 1488 | TK_NotStart | 1208363553 | 115 | 1208363553_115
MRPP2-DE2.16103 | TT_Task | Preliminary Design Specification - Saloon Interior DMU M2 | 10/07/2020 | 23/02/2021 | 10/07/2020 | 23/02/2021 | 0 | TK_Complete | 1208363553 | 478 | 1208363553_478
MRPP2-DE2.16123 | TT_Task | Preliminary Design Specification ? Saloon Interior and Facilities including DDA - PTA Design Review Rev.A DMU M2 | 24/02/2021 | 24/03/2021 | 24/02/2021 | 24/03/2021 | 0 | TK_Complete | 1208363553 | 478 | 1208363553_478
MRPP2-DE2.19123 | TT_Task | Preliminary Design Specification ? Saloon Interior and Facilities including DDA - Submit Rev.B DMU M2 | 25/03/2021 | 05/07/2021 | 25/03/2021 | 05/07/2021 | 0 | TK_Complete | 1208363553 | 478 | 1208363553_478
MRPP2-DE2.19133 | TT_Task | Preliminary Design Specification ? Saloon Interior and Facilities including DDA - PTA Design Review Rev.B DMU M2 | 06/07/2021 | 09/09/2021 | 06/07/2021 | 09/09/2021 | 0 | TK_Complete | 1208363553 | 478 | 1208363553_478
MRPP2-DE2.19403 | TT_Task | Preliminary Design Specification ? Saloon Interior and Facilities including DDA - Submit Rev.C DMU M2 | 10/09/2021 | 09/02/2022 | 10/09/2021 | nan | 0 | TK_Active | 1208363553 | 478 | 1208363553_478
MRPP2-DE2.19413 | TT_Task | Preliminary Design Specification ? Saloon Interior and Facilities including DDA - PTA Design Review Rev.C DMU M2 | 12/04/2022 | 10/05/2022 | nan | nan | 0 | TK_NotStart | 1208363553 | 478 | 1208363553_478
MRPP2-DE3.15620 | TT_Task | Ergonomic reports for cab - Visibility study report, Driver Desk DMU M3 | 06/11/2020 | 19/10/2021 | 06/11/2020 | 19/10/2021 | 0 | TK_Complete | 1208363553 | 119 | 1208363553_119
MRPP2-DE3.15640 | TT_Task | Ergonomic reports for cab - Visibility study report, Driver Desk - PTA Design Review Rev.A DMU M3 | 20/10/2021 | 10/12/2021 | 20/10/2021 | 04/02/2022 | 0 | TK_Complete | 1208363553 | 119 | 1208363553_119
MRPP2-DE3.29300 | TT_Task | Ergonomic reports for cab - Visibility study report, Driver Desk - Submit Rev. B DMU M3 | 04/03/2022 | 29/04/2022 | 07/02/2022 | nan | 0 | TK_Active | 1208363553 | 119 | 1208363553_119
MRPP2-DE3.29310 | TT_Task | Ergonomic reports for cab - Visibility study report, Driver Desk - PTA Design Review Rev.B DMU M3 | 12/04/2022 | 03/06/2022 | nan | nan | 0 | TK_NotStart | 1208363553 | 119 | 1208363553_119
MRPP2-DE3.15660 | TT_Task | Ergonomic report for saloon DMU M3 | 06/11/2020 | 03/05/2022 | 06/11/2020 | nan | 0 | TK_Active | 1208363553 | 120 | 1208363553_120
MRPP2-DE3.15680 | TT_Task | Ergonomic report for saloon - PTA Design Review DMU M3 | 04/05/2022 | 31/05/2022 | nan | nan | 0 | TK_NotStart | 1208363553 | 120 | 1208363553_120
MRPP2-DE3.15700 | TT_Task | Detailed Design Specification ? Saloon Interior and Facilities including DDA DMU M3 | 18/11/2020 | 03/05/2022 | 18/11/2020 | nan | 0 | TK_Active | 1208363553 | 478 | 1208363553_478
MRPP2-DE3.15720 | TT_Task | Detailed Design Specification ? Saloon Interior and Facilities including DDA - PTA Design Review DMU M3 | 04/05/2022 | 31/05/2022 | nan | nan | 0 | TK_NotStart | 1208363553 | 478 | 1208363553_478
MRPP2-DE3.16220 | TT_Task | Final Exterior and Interior Design book - Interior sample material DMU M3 | 03/03/2021 | 28/04/2022 | 03/03/2021 | nan | 0 | TK_Active | 1208363553 | 121 | 1208363553_121
MRPP2-DE3.16240 | TT_Task | Final Exterior and Interior Design book - Interior sample material - PTA Design Review DMU M3 | 29/04/2022 | 26/05/2022 | nan | nan | 0 | TK_NotStart | 1208363553 | 121 | 1208363553_121
MRPP2-DE3.21620 | TT_Task | Type Test Specification - Straphangers Endurance DMU - PTA Review and Approval | 27/10/2021 | 23/11/2021 | 27/10/2021 | 23/11/2021 | 0 | TK_Complete | 1208363553 | 122 | 1208363553_122
MRPP2-DE3.21680 | TT_Task | Detailed Design Specification - Signage and labelling DMU - PTA Review and Approval | 25/11/2022 | 22/12/2022 | nan | nan | 1400 | TK_NotStart | 1208363553 | 123 | 1208363553_123
MRPP2-DE3.21720 | TT_Task | Type Test Specification - Saloon Lighting and Gangway Lighting DMU - PTA Review and Approval | 25/11/2022 | 22/12/2022 | nan | nan | 1400 | TK_NotStart | 1208363553 | 124 | 1208363553_124
MRPP2-DE3.21730 | TT_Task | Type Test Specification - Load test of Floor panel DMU - PTA Review and Approval | 27/10/2022 | 23/11/2022 | nan | nan | 1568 | TK_NotStart | 1208363553 | 216 | 1208363553_216
MRPP2-DE3.21740 | TT_Task | Type Test Specification - Interior Components DMU - PTA Review and Approval | 27/10/2022 | 23/11/2022 | nan | nan | 1568 | TK_NotStart | 1208363553 | 470 | 1208363553_470
MRPP2-DE3.21760 | TT_Task | Type Test Specification - Floor Fire Resistance DMU - PTA Review Rev.A | 19/08/2021 | 24/09/2021 | 19/08/2021 | 24/09/2021 | 0 | TK_Complete | 1208363553 | 126 | 1208363553_126
MRPP2-DE3.27670 | TT_Task | Type Test Specification - Floor Fire Resistance DMU - Submission Rev.B | 28/09/2021 | 22/03/2022 | 28/09/2021 | nan | 0 | TK_Active | 1208363553 | 126 | 1208363553_126
MRPP2-DE3.27680 | TT_Task | Type Test Specification - Floor Fire Resistance DMU - PTA Review Rev.B | 12/04/2022 | 10/05/2022 | nan | nan | 64720 | TK_NotStart | 1208363553 | 126 | 1208363553_126
MRPP2-DE3.21900 | TT_Task | Lighting Performance Type Test Procedure DMU - PTA Review and Approval | 27/10/2022 | 23/11/2022 | nan | nan | 1568 | TK_NotStart | 1208363553 | 187 | 1208363553_187
MRPP2-DE3.22040 | TT_Task | Lighting ; External Signage Functional Type Test Procedure = LIG ; ESG DMU - PTA Review and Approval | 16/01/2023 | 13/02/2023 | nan | nan | 1136 | TK_NotStart | 1208363553 | 182 | 1208363553_182
MRPP2-DE2.16343 | TT_Task | System Description of TCMS DMU M2 | 01/05/2020 | 15/11/2021 | 01/05/2020 | 15/11/2021 | 0 | TK_Complete | 1208363553 | 479 | 1208363553_479
MRPP2-DE2.16363 | TT_Task | System Description of TCMS - PTA Design Review Rev.A DMU M2 | 16/11/2021 | 07/02/2022 | 16/11/2021 | nan | 0 | TK_Active | 1208363553 | 480 | 1208363553_480
MRPP2-DE2.16183 | TT_Task | Functional Description Document of TCMS DMU M2 | 15/07/2020 | 03/03/2021 | 15/07/2020 | 03/03/2021 | 0 | TK_Complete | 1208363553 | 481 | 1208363553_481
MRPP2-DE2.16203 | TT_Task | Functional Description Document of TCMS - PTA Design Review Rev.A DMU M2 | 04/03/2021 | 31/03/2021 | 04/03/2021 | 31/03/2021 | 0 | TK_Complete | 1208363553 | 480 | 1208363553_480
MRPP2-DE2.19163 | TT_Task | Functional Description Document of TCMS - Submit Rev.B DMU M2 | 01/04/2021 | 04/06/2021 | 01/04/2021 | 07/06/2021 | 0 | TK_Complete | 1208363553 | 481 | 1208363553_481
MRPP2-DE2.19173 | TT_Task | Functional Description Document of TCMS - PTA Design Review Rev.B DMU M2 | 08/06/2021 | 07/07/2021 | 08/06/2021 | 07/07/2021 | 0 | TK_Complete | 1208363553 | 480 | 1208363553_480
MRPP2-DE2.19343 | TT_Task | Functional Description Document of TCMS - Submit Rev.C DMU M2 | 08/07/2021 | 25/02/2022 | 08/07/2021 | nan | 0 | TK_Active | 1208363553 | 481 | 1208363553_481
MRPP2-DE2.19353 | TT_Task | Functional Description Document of TCMS - PTA Design Review Rev.C DMU M2 | 12/04/2022 | 10/05/2022 | nan | nan | 0 | TK_NotStart | 1208363553 | 480 | 1208363553_480
MRPP2-DE2.16223 | TT_Task | Technical Description of HMI DMU M2 | 15/07/2020 | 18/02/2021 | 15/07/2020 | 18/02/2021 | 0 | TK_Complete | 1208363553 | 130 | 1208363553_130
MRPP2-DE2.16243 | TT_Task | Technical Description of HMI - PTA Design Review Rev.A DMU M2 | 19/02/2021 | 18/03/2021 | 19/02/2021 | 18/03/2021 | 0 | TK_Complete | 1208363553 | 131 | 1208363553_131
MRPP2-DE2.19083 | TT_Task | Technical Description of HMI - Submit Rev.B DMU M2 | 19/03/2021 | 22/02/2022 | 19/03/2021 | nan | 0 | TK_Active | 1208363553 | 130 | 1208363553_130
MRPP2-DE2.19093 | TT_Task | Technical Description of HMI - PTA Design Review Rev.B DMU M2 | 12/04/2022 | 10/05/2022 | nan | nan | 0 | TK_NotStart | 1208363553 | 131 | 1208363553_131
MRPP2-DE2.16303 | TT_Task | Technical Description and Drawings of Master Controller DMU M2 | 24/07/2020 | 19/10/2020 | 24/07/2020 | 19/10/2020 | 0 | TK_Complete | 1208363553 | 129 | 1208363553_129
MRPP2-DE2.16323 | TT_Task | Technical Description and Drawings of Master Controller - PTA Design Review DMU M2 | 20/10/2020 | 17/11/2020 | 20/10/2020 | 17/11/2020 | 0 | TK_Complete | 1208363553 | 129 | 1208363553_129
MRPP2-DE3.14630 | TT_Task | Technical specification of TCMS DMU M3 | 03/09/2020 | 29/04/2022 | 03/09/2020 | nan | 0 | TK_Active | 1208363553 | 479 | 1208363553_479
MRPP2-DE3.14910 | TT_Task | Technical specification of TCMS - PTA Design Review DMU M3 | 02/05/2022 | 27/05/2022 | nan | nan | 0 | TK_NotStart | 1208363553 | 480 | 1208363553_480
MRPP2-DE3.21270 | TT_Task | Preliminary Electrical Schematic Diagrams DMU - PTA Review and Approval | 21/12/2022 | 20/01/2023 | nan | nan | 63296 | TK_NotStart | 1208363553 | 482 | 1208363553_482
MRPP2-DE3.21460 | TT_Task | TCMS Static Type Test Procedure DMU - PTA Review and Approval | 14/11/2022 | 09/12/2022 | nan | nan | 1472 | TK_NotStart | 1208363553 | 134 | 1208363553_134
MRPP2-DE3.21510 | TT_Task | TCMS Dynamic Type Test Procedure DMU - PTA Review and Approval | 14/11/2022 | 09/12/2022 | nan | nan | 1472 | TK_NotStart | 1208363553 | 134 | 1208363553_134
MRPP2-DE3.21640 | TT_Task | Test Specification of Master Controller DMU - PTA Review and Approval | 28/07/2021 | 26/08/2021 | 28/07/2021 | 26/08/2021 | 0 | TK_Complete | 1208363553 | 135 | 1208363553_135
MRPP2-DE1.14603 | TT_Task | Preliminary Vehicle Performance DMU M1 | 22/01/2020 | 09/09/2020 | 22/01/2020 | 09/09/2020 | 0 | TK_Complete | 1208363553 | 137 | 1208363553_137
MRPP2-DE1.14623 | TT_Task | Preliminary Vehicle Performance - PTA Design Review Rev.A DMU M1 | 10/09/2020 | 05/10/2020 | 10/09/2020 | 05/10/2020 | 0 | TK_Complete | 1208363553 | 138 | 1208363553_138
MRPP2-DE1.15793 | TT_Task | Preliminary Vehicle Performance - Submit Rev.B DMU M1 | 06/10/2020 | 03/02/2021 | 06/10/2020 | 03/02/2021 | 0 | TK_Complete | 1208363553 | 137 | 1208363553_137
MRPP2-DE1.15803 | TT_Task | Preliminary Vehicle Performance - PTA Design Review Rev.B DMU M1 | 04/02/2021 | 04/03/2021 | 04/02/2021 | 04/03/2021 | 0 | TK_Complete | 1208363553 | 138 | 1208363553_138
MRPP2-DE3.22020 | TT_Task | Traction Functional Type Test Procedure ? TBS DMU - PTA Review and Approval | 18/01/2023 | 15/02/2023 | nan | nan | 1120 | TK_NotStart | 1208363553 | 147 | 1208363553_147
MRPP2-DE1.13973 | TT_Task | System Description of Gangway DMU M1 | 24/02/2020 | 16/07/2020 | 24/02/2020 | 16/07/2020 | 0 | TK_Complete | 1208363553 | 149 | 1208363553_149
MRPP2-DE1.14213 | TT_Task | System Description of Gangway - PTA Design Review Rev.A DMU M1 | 17/07/2020 | 31/07/2020 | 17/07/2020 | 31/07/2020 | 0 | TK_Complete | 1208363553 | 150 | 1208363553_150
MRPP2-DE1.15713 | TT_Task | System Description of Gangway - Resubmit Rev.B DMU M1 | 03/08/2020 | 19/08/2020 | 03/08/2020 | 19/08/2020 | 0 | TK_Complete | 1208363553 | 149 | 1208363553_149
MRPP2-DE1.15723 | TT_Task | System Description of Gangway - PTA Design Review Rev.B DMU M1 | 20/08/2020 | 14/09/2020 | 20/08/2020 | 14/09/2020 | 0 | TK_Complete | 1208363553 | 150 | 1208363553_150
MRPP2-DE2.15173 | TT_Task | Detailed Design Specification of Gangway DMU M2 | 10/07/2020 | 11/09/2020 | 10/07/2020 | 11/09/2020 | 0 | TK_Complete | 1208363553 | 151 | 1208363553_151
MRPP2-DE2.15373 | TT_Task | Detailed Design Specification of Gangway - PTA Design Review Rev.A DMU M2 | 14/09/2020 | 12/10/2020 | 14/09/2020 | 12/10/2020 | 0 | TK_Complete | 1208363553 | 150 | 1208363553_150
MRPP2-DE2.18453 | TT_Task | Detailed Design Specification of Gangway - Submit Rev.B DMU M2 | 13/10/2020 | 16/12/2020 | 13/10/2020 | 16/12/2020 | 0 | TK_Complete | 1208363553 | 151 | 1208363553_151
MRPP2-DE2.18463 | TT_Task | Detailed Design Specification of Gangway - PTA Design Review Rev.B DMU M2 | 17/12/2020 | 02/02/2021 | 17/12/2020 | 02/02/2021 | 0 | TK_Complete | 1208363553 | 150 | 1208363553_150
MRPP2-DE2.18963 | TT_Task | Detailed Design Specification of Gangway - Submit Rev.C DMU M2 | 03/02/2021 | 04/06/2021 | 03/02/2021 | 04/06/2021 | 0 | TK_Complete | 1208363553 | 151 | 1208363553_151
MRPP2-DE2.18973 | TT_Task | Detailed Design Specification of Gangway - PTA Design Review Rev.C DMU M2 | 08/06/2021 | 29/06/2021 | 05/06/2021 | 29/06/2021 | 0 | TK_Complete | 1208363553 | 150 | 1208363553_150
MRPP2-DE3.21590 | TT_Task | Test Specification - Gangway DMU - PTA Review and Approval | 24/11/2022 | 21/12/2022 | nan | nan | 1408 | TK_NotStart | 1208363553 | 152 | 1208363553_152
MRPP2-DE3.21650 | TT_Task | Gangway ; Coupler Movement Analysis DMU - PTA Review and Approval | 18/01/2023 | 15/02/2023 | nan | nan | 1120 | TK_NotStart | 1208363553 | 153 | 1208363553_153
MRPP2-DE1.13983 | TT_Task | System Description of Coupling System DMU M1 | 07/02/2020 | 18/06/2020 | 07/02/2020 | 18/06/2020 | 0 | TK_Complete | 1208363553 | 483 | 1208363553_483
MRPP2-DE1.14243 | TT_Task | System Description of Coupling System - PTA Design Review Rev.A DMU M1 | 19/06/2020 | 09/07/2020 | 19/06/2020 | 09/07/2020 | 0 | TK_Complete | 1208363553 | 155 | 1208363553_155
MRPP2-DE1.15693 | TT_Task | System Description of Coupling System - Resubmit Rev.B DMU M1 | 10/07/2020 | 11/08/2020 | 10/07/2020 | 11/08/2020 | 0 | TK_Complete | 1208363553 | 483 | 1208363553_483
MRPP2-DE1.15703 | TT_Task | System Description of Coupling System - PTA Design Review Rev.B DMU M1 | 12/08/2020 | 07/09/2020 | 12/08/2020 | 07/09/2020 | 0 | TK_Complete | 1208363553 | 155 | 1208363553_155
MRPP2-DE2.15183 | TT_Task | Detailed Design Specification of Couplers DMU M2 | 10/07/2020 | 20/10/2020 | 10/07/2020 | 20/10/2020 | 0 | TK_Complete | 1208363553 | 156 | 1208363553_156
MRPP2-DE2.15403 | TT_Task | Detailed Design Specification of Couplers - PTA Design Review Rev.A DMU M2 | 21/10/2020 | 12/11/2020 | 21/10/2020 | 12/11/2020 | 0 | TK_Complete | 1208363553 | 156 | 1208363553_156
MRPP2-DE2.18753 | TT_Task | Detailed Design Specification of Couplers - Submit Rev.B DMU M2 | 13/11/2020 | 11/03/2021 | 13/11/2020 | 11/03/2021 | 0 | TK_Complete | 1208363553 | 156 | 1208363553_156
MRPP2-DE2.18763 | TT_Task | Detailed Design Specification of Couplers - PTA Design Review Rev.B DMU M2 | 12/03/2021 | 15/04/2021 | 12/03/2021 | 15/04/2021 | 0 | TK_Complete | 1208363553 | 156 | 1208363553_156
MRPP2-DE3.15380 | TT_Task | Collision and Energy Absorption Calculation Report of Coupler System DMU M3 | 30/10/2020 | 29/04/2022 | 30/10/2020 | nan | 0 | TK_Active | 1208363553 | 157 | 1208363553_157
MRPP2-DE3.15400 | TT_Task | Collision and Energy Absorption Calculation Report of Coupler System - PTA Design Review DMU M3 | 02/05/2022 | 27/05/2022 | nan | nan | 0 | TK_NotStart | 1208363553 | 157 | 1208363553_157
MRPP2-DE3.21630 | TT_Task | Type Test Specification - Couplers DMU - PTA Review and Approval | 04/11/2022 | 01/12/2022 | nan | nan | 1520 | TK_NotStart | 1208363553 | 158 | 1208363553_158
MRPP2-DE1.14843 | TT_Task | System Description of Cab and Saloon HVAC DMU M1 | 12/02/2020 | 02/10/2020 | 12/02/2020 | 02/10/2020 | 0 | TK_Complete | 1208363553 | 484 | 1208363553_484
MRPP2-DE1.14863 | TT_Task | System Description of Cab and Saloon HVAC - PTA Design Review Rev.A DMU M1 | 05/10/2020 | 29/10/2020 | 05/10/2020 | 29/10/2020 | 0 | TK_Complete | 1208363553 | 160 | 1208363553_160
MRPP2-DE1.15983 | TT_Task | System Description of Cab and Saloon HVAC - Submit Rev.B DMU M1 | 30/10/2020 | 01/02/2021 | 30/10/2020 | 01/02/2021 | 0 | TK_Complete | 1208363553 | 484 | 1208363553_484
MRPP2-DE1.15993 | TT_Task | System Description of Cab and Saloon HVAC - PTA Design Review Rev.B DMU M1 | 02/02/2021 | 02/03/2021 | 02/02/2021 | 02/03/2021 | 0 | TK_Complete | 1208363553 | 160 | 1208363553_160
MRPP2-DE1.16083 | TT_Task | System Description of Cab and Saloon HVAC - Submit Rev.C DMU M1 | 03/03/2021 | 26/05/2021 | 03/03/2021 | 26/05/2021 | 0 | TK_Complete | 1208363553 | 484 | 1208363553_484
MRPP2-DE1.16093 | TT_Task | System Description of Cab and Saloon HVAC - PTA Design Review Rev.C DMU M1 | 27/05/2021 | 25/06/2021 | 27/05/2021 | 25/06/2021 | 0 | TK_Complete | 1208363553 | 160 | 1208363553_160
MRPP2-DE2.15203 | TT_Task | Technical Description and Drawings of Cab and Saloon HVAC DMU M2 | 27/07/2020 | 04/03/2021 | 27/07/2020 | 04/03/2021 | 0 | TK_Complete | 1208363553 | 484 | 1208363553_484
MRPP2-DE2.15463 | TT_Task | Technical Description and Drawings of Cab and Saloon HVAC - PTA Design Review DMU M2 | 05/03/2021 | 31/03/2021 | 05/03/2021 | 31/03/2021 | 0 | TK_Complete | 1208363553 | 160 | 1208363553_160
MRPP2-DE3.15193 | TT_Task | Climate Comfort Prediction Report DMU M3 | 27/07/2020 | 18/04/2022 | 27/07/2020 | nan | 0 | TK_Active | 1208363553 | 161 | 1208363553_161
MRPP2-DE3.15433 | TT_Task | Climate Comfort Prediction Report - PTA Design Review DMU M3 | 19/04/2022 | 17/05/2022 | nan | nan | 0 | TK_NotStart | 1208363553 | 161 | 1208363553_161
MRPP2-DE3.16540 | TT_Task | Heat Load Calculations DMU M3 | 18/12/2020 | 20/05/2021 | 18/12/2020 | 20/05/2021 | 0 | TK_Complete | 1208363553 | 485 | 1208363553_485
MRPP2-DE3.16560 | TT_Task | Heat Load Calculations - PTA Design Review Rev.A DMU M3 | 21/05/2021 | 23/06/2021 | 21/05/2021 | 23/06/2021 | 0 | TK_Complete | 1208363553 | 485 | 1208363553_485
MRPP2-DE3.24130 | TT_Task | Heat Load Calculations - Submit Rev.B DMU M3 | 24/06/2021 | 10/08/2021 | 24/06/2021 | 10/08/2021 | 0 | TK_Complete | 1208363553 | 485 | 1208363553_485
MRPP2-DE3.24140 | TT_Task | Heat Load Calculations - PTA Design Review Rev.B DMU M3 | 11/08/2021 | 13/09/2021 | 11/08/2021 | 13/09/2021 | 0 | TK_Complete | 1208363553 | 485 | 1208363553_485
MRPP2-DE3.21700 | TT_Task | Test Specification of Saloon HVAC DMU - PTA Review and Approval | 24/11/2022 | 21/12/2022 | nan | nan | 1408 | TK_NotStart | 1208363553 | 160 | 1208363553_160
MRPP2-DE3.21790 | TT_Task | Software document for HVAC System DMU - PTA Review Rev.A | 24/11/2022 | 21/12/2022 | 04/01/2022 | 17/03/2022 | 0 | TK_Complete | 1208363553 | 165 | 1208363553_165
MRPP2-DE3.29740 | TT_Task | Software document for HVAC System DMU - Submission Rev.B | 24/11/2022 | 07/12/2022 | 18/03/2022 | nan | 0 | TK_Active | 1208363553 | 165 | 1208363553_165
MRPP2-DE3.29750 | TT_Task | Software document for HVAC System DMU - PTA Review Rev.B | 12/04/2022 | 10/05/2022 | nan | nan | 64720 | TK_NotStart | 1208363553 | 165 | 1208363553_165
MRPP2-DE3.22050 | TT_Task | HVAC Functional Type Test Procedure ? CLM DMU - PTA Review and Approval | 24/11/2022 | 21/12/2022 | nan | nan | 1408 | TK_NotStart | 1208363553 | 163 | 1208363553_163
MRPP2-DE1.13993 | TT_Task | System Description of Passenger Doors DMU M1 | 07/02/2020 | 16/09/2020 | 07/02/2020 | 16/09/2020 | 0 | TK_Complete | 1208363553 | 486 | 1208363553_486
MRPP2-DE1.14273 | TT_Task | System Description of Passenger Doors - PTA Design Review Rev.A DMU M1 | 17/09/2020 | 12/10/2020 | 17/09/2020 | 12/10/2020 | 0 | TK_Complete | 1208363553 | 486 | 1208363553_486
MRPP2-DE1.15863 | TT_Task | System Description of Passenger Doors- Submit Rev.B DMU M1 | 13/10/2020 | 14/12/2020 | 13/10/2020 | 14/12/2020 | 0 | TK_Complete | 1208363553 | 486 | 1208363553_486
MRPP2-DE1.15873 | TT_Task | System Description of Passenger Doors - PTA Design Review Rev.B DMU M1 | 15/12/2020 | 01/02/2021 | 15/12/2020 | 01/02/2021 | 0 | TK_Complete | 1208363553 | 486 | 1208363553_486
MRPP2-DE2.16463 | TT_Task | Technical Description and Drawings of Passenger Doors DMU M2 | 24/07/2020 | 22/03/2021 | 24/07/2020 | 22/03/2021 | 0 | TK_Complete | 1208363553 | 486 | 1208363553_486
MRPP2-DE2.16483 | TT_Task | Technical Description and Drawings of Passenger Doors - PTA Design Review Rev.A DMU M2 | 23/03/2021 | 21/04/2021 | 23/03/2021 | 21/04/2021 | 0 | TK_Complete | 1208363553 | 486 | 1208363553_486
MRPP2-DE2.19183 | TT_Task | Technical Description and Drawings of Passenger Doors - Submit Rev.B DMU M2 | 21/04/2021 | 24/06/2021 | 21/04/2021 | 24/06/2021 | 0 | TK_Complete | 1208363553 | 486 | 1208363553_486
MRPP2-DE2.19193 | TT_Task | Technical Description and Drawings of Passenger Doors - PTA Design Review Rev.B DMU M2 | 25/06/2021 | 26/07/2021 | 25/06/2021 | 26/07/2021 | 0 | TK_Complete | 1208363553 | 486 | 1208363553_486
MRPP2-DE3.21670 | TT_Task | Test specification of Passenger saloon Door DMU - PTA Review Rev.A | 09/09/2021 | 06/10/2021 | 09/09/2021 | 06/10/2021 | 0 | TK_Complete | 1208363553 | 168 | 1208363553_168
MRPP2-DE3.27690 | TT_Task | Test specification of Passenger saloon Door DMU - Submission Rev.B | 07/10/2021 | 08/03/2022 | 07/10/2021 | nan | 0 | TK_Active | 1208363553 | 168 | 1208363553_168
MRPP2-DE3.27700 | TT_Task | Test specification of Passenger saloon Door DMU - PTA Review Rev.B | 12/04/2022 | 10/05/2022 | nan | nan | 64720 | TK_NotStart | 1208363553 | 168 | 1208363553_168
MRPP2-DE3.21780 | TT_Task | Software document for Door System DMU - PTA Review and Approval | 17/11/2022 | 14/12/2022 | nan | nan | 1448 | TK_NotStart | 1208363553 | 169 | 1208363553_169
MRPP2-DE3.21880 | TT_Task | Doors Functional Type Test Procedure ? DRS DMU - PTA Review and Approval | 05/01/2023 | 02/02/2023 | nan | nan | 1192 | TK_NotStart | 1208363553 | 167 | 1208363553_167
MRPP2-DE3.22030 | TT_Task | Doors Performance Type Test Procedure DMU - PTA Review and Approval | 21/11/2022 | 16/12/2022 | nan | nan | 1432 | TK_NotStart | 1208363553 | 167 | 1208363553_167
MRPP2-DE1.14003 | TT_Task | System Description of Auxiliary Supply System DMU M1 (N/A) | 22/01/2020 | 08/04/2020 | 22/01/2020 | 08/04/2020 | 0 | TK_Complete | 1208363553 | 487 | 1208363553_487
MRPP2-DE1.14303 | TT_Task | System Description of Auxiliary Supply System - PTA Design Review DMU M1 (N/A) | 08/04/2020 | 08/04/2020 | 08/04/2020 | 08/04/2020 | 0 | TK_Complete | 1208363553 | 172 | 1208363553_172
MRPP2-DE2.16143 | TT_Task | Auxiliary Load Calculation Report for AC and DC DMU M2 | 10/07/2020 | 02/12/2020 | 10/07/2020 | 02/12/2020 | 0 | TK_Complete | 1208363553 | 176 | 1208363553_176
MRPP2-DE2.16163 | TT_Task | Auxiliary Load Calculation Report for AC and DC - PTA Design Review Rev.A DMU M2 | 03/12/2020 | 18/01/2021 | 03/12/2020 | 18/01/2021 | 0 | TK_Complete | 1208363553 | 177 | 1208363553_177
MRPP2-DE2.18773 | TT_Task | Auxiliary Load Calculation Report for AC and DC - Submit Rev.B DMU M2 | 19/01/2021 | 19/02/2021 | 19/01/2021 | 19/02/2021 | 0 | TK_Complete | 1208363553 | 176 | 1208363553_176
MRPP2-DE2.18783 | TT_Task | Auxiliary Load Calculation Report for AC and DC - PTA Design Review Rev.B DMU M2 | 22/02/2021 | 22/03/2021 | 22/02/2021 | 22/03/2021 | 0 | TK_Complete | 1208363553 | 177 | 1208363553_177
MRPP2-DE2.19103 | TT_Task | Auxiliary Load Calculation Report for AC and DC - Submit Rev.C DMU M2 | 23/03/2021 | 16/04/2021 | 23/03/2021 | 16/04/2021 | 0 | TK_Complete | 1208363553 | 176 | 1208363553_176
MRPP2-DE2.19113 | TT_Task | Auxiliary Load Calculation Report for AC and DC - PTA Design Review Rev.C DMU M2 | 19/04/2021 | 17/05/2021 | 19/04/2021 | 17/05/2021 | 0 | TK_Complete | 1208363553 | 177 | 1208363553_177
MRPP2-DE2.15213 | TT_Task | Technical Description and Drawings of Auxiliary Supply System DMU M2 | 27/07/2020 | 30/03/2021 | 27/07/2020 | 30/03/2021 | 0 | TK_Complete | 1208363553 | 487 | 1208363553_487
MRPP2-DE2.15493 | TT_Task | Technical Description and Drawings of Auxiliary Supply System- PTA Design Review Rev.A DMU M2 | 31/03/2021 | 30/04/2021 | 31/03/2021 | 30/04/2021 | 0 | TK_Complete | 1208363553 | 172 | 1208363553_172
MRPP2-DE2.19263 | TT_Task | Technical Description and Drawings of Auxiliary Supply System - Submit Rev.B DMU M2 | 03/05/2021 | 14/06/2021 | 03/05/2021 | 14/06/2021 | 0 | TK_Complete | 1208363553 | 487 | 1208363553_487
MRPP2-DE2.19273 | TT_Task | Technical Description and Drawings of Auxiliary Supply System- PTA Design Review RevB DMU M2 | 15/06/2021 | 20/07/2021 | 15/06/2021 | 20/07/2021 | 0 | TK_Complete | 1208363553 | 172 | 1208363553_172
MRPP2-DE2.19363 | TT_Task | Technical Description and Drawings of Auxiliary Supply System - Submit Rev.C DMU M2 | 21/07/2021 | 03/09/2021 | 21/07/2021 | 03/09/2021 | 0 | TK_Complete | 1208363553 | 487 | 1208363553_487
MRPP2-DE2.19373 | TT_Task | Technical Description and Drawings of Auxiliary Supply System- PTA Design Review Rev.C DMU M2 | 06/09/2021 | 06/10/2021 | 06/09/2021 | 06/10/2021 | 0 | TK_Complete | 1208363553 | 172 | 1208363553_172
MRPP2-DE3.15300 | TT_Task | Energy Consumption Analysis Report DMU M3 | 08/09/2020 | 19/04/2022 | 08/09/2020 | nan | 0 | TK_Active | 1208363553 | 488 | 1208363553_488
MRPP2-DE3.15320 | TT_Task | Energy Consumption Analysis Report - PTA Design Review DMU M3 | 20/04/2022 | 18/05/2022 | nan | nan | 0 | TK_NotStart | 1208363553 | 488 | 1208363553_488
MRPP2-DE3.14650 | TT_Task | Final electrical schematic diagrams DMU M3 | 07/10/2020 | 28/04/2022 | 07/10/2020 | 15/09/2021 | 0 | TK_Complete | 1208363553 | 482 | 1208363553_482
MRPP2-DE3.14970 | TT_Task | Final electrical schematic diagrams - PTA Design Review Rev.A DMU M3 | 29/04/2022 | 26/05/2022 | 16/09/2021 | 17/03/2022 | 0 | TK_Complete | 1208363553 | 482 | 1208363553_482
MRPP2-DE3.29760 | TT_Task | Final electrical schematic diagrams - Submit Rev.B DMU M3 | 04/04/2022 | 19/04/2022 | 18/03/2022 | nan | 0 | TK_Active | 1208363553 | 482 | 1208363553_482
MRPP2-DE3.29770 | TT_Task | Final electrical schematic diagrams - PTA Design Review Rev.B DMU M3 | 12/04/2022 | 10/05/2022 | nan | nan | 0 | TK_NotStart | 1208363553 | 482 | 1208363553_482
MRPP2-DE3.21310 | TT_Task | Technical Description and Drawings of wires ; Cable DMU - PTA Review Rev.A | 18/02/2021 | 17/03/2021 | 18/02/2021 | 17/03/2021 | 0 | TK_Complete | 1208363553 | 179 | 1208363553_179
MRPP2-DE3.22870 | TT_Task | Technical Description and Drawings of wires ; Cable DMU - Submission Rev.B | 18/03/2021 | 06/05/2022 | 18/03/2021 | 02/02/2022 | 0 | TK_Complete | 1208363553 | 179 | 1208363553_179
MRPP2-DE3.22880 | TT_Task | Technical Description and Drawings of wires ; Cable DMU - PTA Review ; Approval Rev.B | 14/06/2022 | 11/07/2022 | 03/02/2022 | 22/03/2022 | 0 | TK_Complete | 1208363553 | 179 | 1208363553_179
MRPP2-DE3.29840 | TT_Task | Technical Description and Drawings of wires ; Cable DMU - Submission Rev.C | 18/03/2021 | 31/03/2021 | 23/03/2021 | nan | 0 | TK_Active | 1208363553 | 179 | 1208363553_179
MRPP2-DE3.29850 | TT_Task | Technical Description and Drawings of wires ; Cable DMU - PTA Review ; Approval Rev.C | 12/04/2022 | 10/05/2022 | nan | nan | 64720 | TK_NotStart | 1208363553 | 179 | 1208363553_179
MRPP2-DE3.21450 | TT_Task | Vehicle Earthing Type Test Procedure DMU - PTA Review and Approval | 14/11/2022 | 09/12/2022 | nan | nan | 1472 | TK_NotStart | 1208363553 | 180 | 1208363553_180
MRPP2-DE3.21530 | TT_Task | Test Specification of Battery System DMU - PTA Review and Approval | 17/10/2022 | 11/11/2022 | nan | nan | 1632 | TK_NotStart | 1208363553 | 489 | 1208363553_489
MRPP2-DE3.21820 | TT_Task | Software document for Auxiliary supply system DMU - PTA Review and Approval (Removed From Design Plan) | 15/03/2022 | 13/04/2022 | 15/03/2022 | 13/04/2022 | 0 | TK_Complete | 1208363553 | 186 | 1208363553_186
MRPP2-DE3.21920 | TT_Task | Battery Autonomy and Charging Type Test Procedure DMU - PTA Review and Approval | 05/12/2022 | 04/01/2023 | nan | nan | 1352 | TK_NotStart | 1208363553 | 188 | 1208363553_188
MRPP2-DE3.21980 | TT_Task | Test Specification of battery and battery charger DMU - PTA Review and Approval | 16/01/2023 | 13/02/2023 | nan | nan | 1136 | TK_NotStart | 1208363553 | 489 | 1208363553_489
MRPP2-DE3.22070 | TT_Task | Event Recorder Functional Type Test Procedure ? JRU DMU - PTA Review and Approval | 25/01/2023 | 22/02/2023 | nan | nan | 1080 | TK_NotStart | 1208363553 | 181 | 1208363553_181
MRPP2-DE1.14013 | TT_Task | System Description of PACIS DMU M1 | 16/03/2020 | 18/08/2020 | 16/03/2020 | 18/08/2020 | 0 | TK_Complete | 1208363553 | 490 | 1208363553_490
MRPP2-DE1.14333 | TT_Task | System Description of PACIS - PTA Design Review Rev.A DMU M1 | 19/08/2020 | 14/09/2020 | 19/08/2020 | 14/09/2020 | 0 | TK_Complete | 1208363553 | 491 | 1208363553_491
MRPP2-DE1.15753 | TT_Task | System Description of PACIS - Resubmit Rev.B DMU M1 | 15/09/2020 | 14/10/2020 | 15/09/2020 | 14/10/2020 | 0 | TK_Complete | 1208363553 | 189 | 1208363553_189
MRPP2-DE1.15763 | TT_Task | System Description of PACIS - PTA Design Review Rev.B DMU M1 | 15/10/2020 | 09/11/2020 | 15/10/2020 | 09/11/2020 | 0 | TK_Complete | 1208363553 | 491 | 1208363553_491
MRPP2-DE2.15163 | TT_Task | Technical Specification and Drawings of PACIS DMU M2 | 27/07/2020 | 09/04/2021 | 27/07/2020 | 09/04/2021 | 0 | TK_Complete | 1208363553 | 490 | 1208363553_490
MRPP2-DE2.15343 | TT_Task | Technical Specification and Drawings of PACIS - PTA Design Review Rev.A DMU M2 | 12/04/2021 | 11/05/2021 | 12/04/2021 | 11/05/2021 | 0 | TK_Complete | 1208363553 | 491 | 1208363553_491
MRPP2-DE2.19283 | TT_Task | Technical Specification and Drawings of PACIS - Submit Rev.B DMU M2 | 03/11/2021 | 15/02/2022 | 03/11/2021 | nan | 0 | TK_Active | 1208363553 | 490 | 1208363553_490
MRPP2-DE2.19293 | TT_Task | Technical Specification and Drawings of PACIS - PTA Design Review Rev.B DMU M2 | 02/09/2021 | 02/11/2021 | 02/09/2021 | 02/11/2021 | 0 | TK_Complete | 1208363553 | 491 | 1208363553_491
MRPP2-DE2.19463 | TT_Task | Technical Specification and Drawings of PACIS - Submit Rev.C DMU M2 | 12/05/2021 | 01/09/2021 | 12/05/2021 | 01/09/2021 | 0 | TK_Complete | 1208363553 | 490 | 1208363553_490
MRPP2-DE2.19473 | TT_Task | Technical Specification and Drawings of PACIS - PTA Design Review Rev.C DMU M2 | 12/04/2022 | 10/05/2022 | nan | nan | 0 | TK_NotStart | 1208363553 | 491 | 1208363553_491
MRPP2-DE3.21490 | TT_Task | PACIS Static Type Test Procedure ? PAI ; VSS DMU - PTA Review and Approval | 27/01/2023 | 23/02/2023 | nan | nan | 1072 | TK_NotStart | 1208363553 | 191 | 1208363553_191
MRPP2-DE3.21500 | TT_Task | PACIS Dynamic Type Test Procedure ? PAI ; VSS DMU - PTA Review and Approval | 19/01/2023 | 16/02/2023 | nan | nan | 1112 | TK_NotStart | 1208363553 | 191 | 1208363553_191
MRPP2-DE3.21770 | TT_Task | Test Specification of PACIS system DMU - PTA Review and Approval | 19/01/2023 | 16/02/2023 | nan | nan | 1112 | TK_NotStart | 1208363553 | 191 | 1208363553_191
MRPP2-DE2.15253 | TT_Task | Preliminary Design Specification ? CAB DMU M2 | 10/07/2020 | 28/01/2021 | 10/07/2020 | 28/01/2021 | 0 | TK_Complete | 1208363553 | 492 | 1208363553_492
MRPP2-DE2.15583 | TT_Task | Preliminary Design Specification ? CAB - PTA Design Review Rev.A DMU M2 | 29/01/2021 | 25/02/2021 | 29/01/2021 | 25/02/2021 | 0 | TK_Complete | 1208363553 | 492 | 1208363553_492
MRPP2-DE2.19023 | TT_Task | Preliminary Design Specification ? CAB - Submit Rev.B DMU M2 | 26/02/2021 | 23/04/2021 | 26/02/2021 | 26/04/2021 | 0 | TK_Complete | 1208363553 | 492 | 1208363553_492
MRPP2-DE2.19033 | TT_Task | Preliminary Design Specification ? CAB - PTA Design Review Rev.B DMU M2 | 27/04/2021 | 25/05/2021 | 27/04/2021 | 25/05/2021 | 0 | TK_Complete | 1208363553 | 492 | 1208363553_492
MRPP2-DE2.19303 | TT_Task | Preliminary Design Specification ? CAB - Submit Rev.C DMU M2 | 26/05/2021 | 22/10/2021 | 26/05/2021 | 22/10/2021 | 0 | TK_Complete | 1208363553 | 492 | 1208363553_492
MRPP2-DE2.19313 | TT_Task | Preliminary Design Specification ? CAB - PTA Design Review Rev.C DMU M2 | 25/10/2021 | 10/12/2021 | 25/10/2021 | 04/02/2022 | 0 | TK_Complete | 1208363553 | 492 | 1208363553_492
MRPP2-DE3.15860 | TT_Task | Detailed Design Specification - Cab DMU M3 | 07/12/2020 | 06/05/2022 | 07/12/2020 | 01/02/2022 | 0 | TK_Complete | 1208363553 | 492 | 1208363553_492
MRPP2-DE3.15870 | TT_Task | Detailed Design Specification - Cab - PTA Design Review DMU M3 | 14/06/2022 | 11/07/2022 | 02/02/2022 | nan | 0 | TK_Active | 1208363553 | 492 | 1208363553_492
MRPP2-DE3.14580 | TT_Task | Trains and Signalling (SIG) Detailed Interface Specification DMU M3 | 01/12/2020 | 05/05/2022 | 01/12/2020 | nan | 0 | TK_Active | 1208363553 | 198 | 1208363553_198
MRPP2-DE3.14740 | TT_Task | Trains and Signalling (SIG) Detailed Interface Specification - PTA Design Review DMU M3 | 06/05/2022 | 02/06/2022 | nan | nan | 0 | TK_NotStart | 1208363553 | 198 | 1208363553_198
MRPP2-DE3.15140 | TT_Task | Trains and Radio System (RAD) Detailed Interface Specification DMU M3 | 01/12/2020 | 04/10/2021 | 01/12/2020 | 04/10/2021 | 0 | TK_Complete | 1208363553 | 199 | 1208363553_199
MRPP2-DE3.15160 | TT_Task | Trains and Radio System (RAD) Detailed Interface Specification - PTA Design Review Rev.A DMU M3 | 05/10/2021 | 24/12/2021 | 05/10/2021 | 02/02/2022 | 0 | TK_Complete | 1208363553 | 199 | 1208363553_199
MRPP2-DE3.29320 | TT_Task | Trains and Radio System (RAD) Detailed Interface Specification - Submit Rev.B DMU M3 | 04/03/2022 | 30/05/2022 | 03/02/2022 | nan | 0 | TK_Active | 1208363553 | 199 | 1208363553_199
MRPP2-DE3.29330 | TT_Task | Trains and Radio System (RAD) Detailed Interface Specification - PTA Design Review Rev.B DMU M3 | 12/04/2022 | 10/05/2022 | nan | nan | 0 | TK_NotStart | 1208363553 | 199 | 1208363553_199
MRPP2-DE3.15180 | TT_Task | Trains and Depot Equipment (DEQ) Detailed Interface Specification DMU M3 | 01/12/2020 | 19/03/2021 | 01/12/2020 | 19/03/2021 | 0 | TK_Complete | 1208363553 | 493 | 1208363553_493
MRPP2-DE3.15200 | TT_Task | Trains and Depot Equipment (DEQ) Detailed Interface Specification - PTA Design Review DMU M3 | 22/02/2021 | 19/03/2021 | 22/02/2021 | 19/03/2021 | 0 | TK_Complete | 1208363553 | 493 | 1208363553_493
MRPP2-DE3.15220 | TT_Task | Trains and Civil Works - Station ; Depot (CWS) Detailed Interface Specification DMU M3 | 01/12/2020 | 19/02/2021 | 01/12/2020 | 19/02/2021 | 0 | TK_Complete | 1208363553 | 493 | 1208363553_493
MRPP2-DE3.15240 | TT_Task | Trains and Civil Works - Station ; Depot (CWS) Detailed Interface Specification - PTA Design Review DMU M3 | 22/02/2021 | 19/03/2021 | 22/02/2021 | 19/03/2021 | 0 | TK_Complete | 1208363553 | 493 | 1208363553_493
MRPP2-DE1.14563 | TT_Task | EMC Control Plan DMU M1 | 22/01/2020 | 16/04/2020 | 22/01/2020 | 16/04/2020 | 0 | TK_Complete | 1208363553 | 203 | 1208363553_203
MRPP2-DE1.14583 | TT_Task | EMC Control Plan - PTA Design Review Rev.A DMU M1 | 17/04/2020 | 05/05/2020 | 17/04/2020 | 05/05/2020 | 0 | TK_Complete | 1208363553 | 202 | 1208363553_202
MRPP2-DE1.15473 | TT_Task | EMC Control Plan - Resubmit Rev.B DMU M1 | 06/05/2020 | 03/08/2020 | 06/05/2020 | 03/08/2020 | 0 | TK_Complete | 1208363553 | 203 | 1208363553_203
MRPP2-DE1.15483 | TT_Task | EMC Control Plan - PTA Design Review Rev.B DMU M1 | 04/08/2020 | 28/08/2020 | 04/08/2020 | 28/08/2020 | 0 | TK_Complete | 1208363553 | 202 | 1208363553_202
MRPP2-DE3.22210 | TT_Task | EMC Type Test Procedure DMU - PTA Review and Approval | 20/10/2022 | 16/11/2022 | nan | nan | 1608 | TK_NotStart | 1208363553 | 51 | 1208363553_51
MRPP2-DE1.14803 | TT_Task | Preliminary Fire Safety Design Report DMU M1 | 30/12/2019 | 08/09/2020 | 30/12/2019 | 08/09/2020 | 0 | TK_Complete | 1208363553 | 494 | 1208363553_494
MRPP2-DE1.14823 | TT_Task | Preliminary Fire Safety Design Report - PTA Design Review Rev.A DMU M1 | 09/09/2020 | 05/10/2020 | 09/09/2020 | 05/10/2020 | 0 | TK_Complete | 1208363553 | 494 | 1208363553_494
MRPP2-DE1.15823 | TT_Task | Preliminary Fire Safety Design Report - PTA Design Review Rev.B DMU M1 | 03/11/2020 | 27/11/2020 | 03/11/2020 | 27/11/2020 | 0 | TK_Complete | 1208363553 | 494 | 1208363553_494
MRPP2-DE1.15833 | TT_Task | Preliminary Fire Safety Design Report - Submit Rev.B DMU M1 | 06/10/2020 | 02/11/2020 | 06/10/2020 | 02/11/2020 | 0 | TK_Complete | 1208363553 | 494 | 1208363553_494
MRPP2-DE1.14723 | TT_Task | System Description of Fire and Smoke detection system DMU M1 | 07/02/2020 | 22/09/2020 | 07/02/2020 | 22/09/2020 | 0 | TK_Complete | 1208363553 | 206 | 1208363553_206
MRPP2-DE1.14743 | TT_Task | System Description of Fire and Smoke detection system - PTA Design Review Rev.A DMU M1 | 23/09/2020 | 19/10/2020 | 23/09/2020 | 19/10/2020 | 0 | TK_Complete | 1208363553 | 206 | 1208363553_206
MRPP2-DE1.15903 | TT_Task | System Description of Fire and Smoke detection system - Submit Rev.B DMU M1 | 20/10/2020 | 04/02/2021 | 20/10/2020 | 04/02/2021 | 0 | TK_Complete | 1208363553 | 206 | 1208363553_206
MRPP2-DE1.15913 | TT_Task | System Description of Fire and Smoke detection system - PTA Design Review Rev.B DMU M1 | 05/02/2021 | 05/03/2021 | 05/02/2021 | 05/03/2021 | 0 | TK_Complete | 1208363553 | 206 | 1208363553_206
MRPP2-DE3.15900 | TT_Task | Detailed Fire Safety Design Report (Version 1) DMU M3 | 23/12/2020 | 23/05/2022 | 23/12/2020 | nan | 0 | TK_Active | 1208363553 | 494 | 1208363553_494
MRPP2-DE3.15970 | TT_Task | Detailed Fire Safety Design Report (Version 1) - PTA Design Review DMU M3 | 24/05/2022 | 21/06/2022 | nan | nan | 0 | TK_NotStart | 1208363553 | 494 | 1208363553_494
MRPP2-DE2.16023 | TT_Task | Noise and Vibration Assurance plan DMU M2 | 28/05/2020 | 08/09/2020 | 28/05/2020 | 08/09/2020 | 0 | TK_Complete | 1208363553 | 495 | 1208363553_495
MRPP2-DE2.16043 | TT_Task | Noise and Vibration Assurance plan - PTA Design Review Rev.A DMU M2 | 09/09/2020 | 05/10/2020 | 09/09/2020 | 05/10/2020 | 0 | TK_Complete | 1208363553 | 495 | 1208363553_495
MRPP2-DE2.18413 | TT_Task | Noise and Vibration Assurance plan - Submit Rev.B DMU M2 | 06/10/2020 | 07/04/2021 | 06/10/2020 | 07/04/2021 | 0 | TK_Complete | 1208363553 | 495 | 1208363553_495
MRPP2-DE2.18423 | TT_Task | Noise and Vibration Assurance plan - PTA Design Review Rev.B DMU M2 | 08/04/2021 | 06/05/2021 | 08/04/2021 | 06/05/2021 | 0 | TK_Complete | 1208363553 | 495 | 1208363553_495
MRPP2-DE2.15743 | TT_Task | Noise Report - Preliminary Specification ; Prediction DMU M3 | 24/07/2020 | 28/07/2021 | 24/07/2020 | 28/07/2021 | 0 | TK_Complete | 1208363553 | 496 | 1208363553_496
MRPP2-DE2.15763 | TT_Task | Noise Report - Preliminary Specification ; Prediction - PTA Design Review Rev.A DMU M3 | 29/07/2021 | 31/08/2021 | 29/07/2021 | 31/08/2021 | 0 | TK_Complete | 1208363553 | 497 | 1208363553_497
MRPP2-DE2.19423 | TT_Task | Noise Report - Preliminary Specification ; Prediction - Submit Rev.B DMU M3 | 01/09/2021 | 22/10/2021 | 01/09/2021 | 22/10/2021 | 0 | TK_Complete | 1208363553 | 496 | 1208363553_496
MRPP2-DE2.19433 | TT_Task | Noise Report - Preliminary Specification ; Prediction - PTA Design Review Rev.B DMU M3 | 25/10/2021 | 26/11/2021 | 25/10/2021 | 26/11/2021 | 0 | TK_Complete | 1208363553 | 497 | 1208363553_497
MRPP2-DE3.15950 | TT_Task | Noise Report - Final Prediction DMU M3 | 04/03/2022 | 24/05/2022 | 09/02/2022 | nan | 0 | TK_Active | 1208363553 | 496 | 1208363553_496
MRPP2-DE3.16110 | TT_Task | Noise Report - Final Prediction - PTA Design Review DMU M3 | 02/05/2022 | 27/05/2022 | nan | nan | 0 | TK_NotStart | 1208363553 | 497 | 1208363553_497
MRPP2-DE3.22180 | TT_Task | Noise Static Type Test Procedure Non-M Design Document - DMU | 02/12/2022 | 03/01/2023 | nan | nan | 1360 | TK_NotStart | 1208363553 | 498 | 1208363553_498
MRPP2-DE3.22190 | TT_Task | Noise Dynamic Type Test Procedure Non-M Design Document - DMU | 02/12/2022 | 03/01/2023 | nan | nan | 1360 | TK_NotStart | 1208363553 | 498 | 1208363553_498
MRPP2-DE1.14053 | TT_Task | Weight Management Plan DMU M1 | 21/11/2019 | 04/02/2020 | 21/11/2019 | 04/02/2020 | 0 | TK_Complete | 1208363553 | 211 | 1208363553_211
MRPP2-DE1.14393 | TT_Task | Weight Management Plan - PTA Design Review Rev.A DMU M1 | 05/02/2020 | 27/02/2020 | 05/02/2020 | 27/02/2020 | 0 | TK_Complete | 1208363553 | 212 | 1208363553_212
MRPP2-DE1.15123 | TT_Task | Weight Management Plan- Resubmit Rev.B DMU M1 | 28/02/2020 | 23/03/2020 | 28/02/2020 | 23/03/2020 | 0 | TK_Complete | 1208363553 | 211 | 1208363553_211
MRPP2-DE1.15133 | TT_Task | Weight Management Plan - PTA Design Review Rev.B DMU M1 | 24/03/2020 | 06/04/2020 | 24/03/2020 | 06/04/2020 | 0 | TK_Complete | 1208363553 | 212 | 1208363553_212
MRPP2-DE3.15420 | TT_Task | Weight distribution calculations report DMU M3 | 08/09/2020 | 03/05/2022 | 08/09/2020 | nan | 0 | TK_Active | 1208363553 | 213 | 1208363553_213
MRPP2-DE3.15440 | TT_Task | Weight distribution calculations report - PTA Design Review DMU M3 | 04/05/2022 | 31/05/2022 | nan | nan | 0 | TK_NotStart | 1208363553 | 213 | 1208363553_213
MRPP2-DE3.14670 | TT_Task | Final Passengers Load and capacity calculations DMU M3 | 23/09/2020 | 13/09/2021 | 23/09/2020 | 13/09/2021 | 0 | TK_Complete | 1208363553 | 214 | 1208363553_214
MRPP2-DE3.15030 | TT_Task | Final Passengers Load and capacity calculations - PTA Design Review Rev.A DMU M3 | 14/09/2021 | 28/10/2021 | 14/09/2021 | 28/10/2021 | 0 | TK_Complete | 1208363553 | 214 | 1208363553_214
MRPP2-DE3.28750 | TT_Task | Final Passengers Load and capacity calculations - Submit Rev.B DMU M3 | 29/10/2021 | 16/02/2022 | 29/10/2021 | nan | 0 | TK_Active | 1208363553 | 214 | 1208363553_214
MRPP2-DE3.28760 | TT_Task | Final Passengers Load and capacity calculations - PTA Design Review Rev.B DMU M3 | 12/04/2022 | 10/05/2022 | nan | nan | 0 | TK_NotStart | 1208363553 | 214 | 1208363553_214
MRPP2-DE3.21360 | TT_Task | Weighment Type Test Procedure DMU - PTA Review and Approval | 30/09/2022 | 27/10/2022 | nan | nan | 1720 | TK_NotStart | 1208363553 | 215 | 1208363553_215
MRPP2-DE1.14683 | TT_Task | Schedule of Hazard Analysis DMU M1 | 29/11/2019 | 21/02/2020 | 29/11/2019 | 21/02/2020 | 0 | TK_Complete | 1208363553 | 217 | 1208363553_217
MRPP2-DE1.14703 | TT_Task | Schedule of Hazard Analysis - PTA Design Review Rev.A DMU M1 | 24/02/2020 | 06/03/2020 | 24/02/2020 | 06/03/2020 | 0 | TK_Complete | 1208363553 | 218 | 1208363553_218
MRPP2-DE1.15143 | TT_Task | Schedule of Hazard Analysis - Resubmit Rev.B DMU M1 | 09/03/2020 | 08/04/2020 | 09/03/2020 | 08/04/2020 | 0 | TK_Complete | 1208363553 | 217 | 1208363553_217
MRPP2-DE1.15153 | TT_Task | Schedule of Hazard Analysis - PTA Design Review Rev.B DMU M1 | 09/04/2020 | 30/04/2020 | 09/04/2020 | 30/04/2020 | 0 | TK_Complete | 1208363553 | 218 | 1208363553_218
MRPP2-DE1.14643 | TT_Task | Safety Assurance Plan DMU M1 | 05/12/2019 | 24/02/2020 | 05/12/2019 | 24/02/2020 | 0 | TK_Complete | 1208363553 | 219 | 1208363553_219
MRPP2-DE1.14663 | TT_Task | Safety Assurance Plan - PTA Design Review Rev.A DMU M1 | 25/02/2020 | 20/03/2020 | 25/02/2020 | 20/03/2020 | 0 | TK_Complete | 1208363553 | 220 | 1208363553_220
MRPP2-DE1.15163 | TT_Task | Safety Assurance Plan - Resubmit Rev.B DMU M1 | 23/03/2020 | 21/04/2020 | 23/03/2020 | 21/04/2020 | 0 | TK_Complete | 1208363553 | 219 | 1208363553_219
MRPP2-DE1.15173 | TT_Task | Safety Assurance Plan - PTA Design Review Rev.B DMU M1 | 22/04/2020 | 07/05/2020 | 22/04/2020 | 07/05/2020 | 0 | TK_Complete | 1208363553 | 220 | 1208363553_220
MRPP2-DE2.15243 | TT_Task | Reliability, Availability and Maintainability Plan DMU M2 | 11/12/2019 | 21/02/2020 | 11/12/2019 | 21/02/2020 | 0 | TK_Complete | 1208363553 | 499 | 1208363553_499
MRPP2-DE2.15643 | TT_Task | Reliability, Availability and Maintainability Plan - PTA Design Review Rev.A DMU M2 | 24/02/2020 | 17/03/2020 | 24/02/2020 | 17/03/2020 | 0 | TK_Complete | 1208363553 | 500 | 1208363553_500
MRPP2-DE2.18113 | TT_Task | Reliability, Availability and Maintainability Plan - Resubmit Rev.B DMU M2 | 18/03/2020 | 01/07/2020 | 18/03/2020 | 01/07/2020 | 0 | TK_Complete | 1208363553 | 499 | 1208363553_499
MRPP2-DE2.18123 | TT_Task | Reliability, Availability and Maintainability Plan - PTA Design Review Rev.B DMU M2 | 02/07/2020 | 23/07/2020 | 02/07/2020 | 23/07/2020 | 0 | TK_Complete | 1208363553 | 500 | 1208363553_500
MRPP2-DE2.18193 | TT_Task | Reliability, Availability and Maintainability Plan - Resubmit Rev.C DMU M2 | 24/07/2020 | 21/08/2020 | 24/07/2020 | 21/08/2020 | 0 | TK_Complete | 1208363553 | 499 | 1208363553_499
MRPP2-DE2.18203 | TT_Task | Reliability, Availability and Maintainability Plan - PTA Design Review Rev.C DMU M2 | 24/08/2020 | 17/09/2020 | 24/08/2020 | 17/09/2020 | 0 | TK_Complete | 1208363553 | 500 | 1208363553_500
MRPP2-DE2.16503 | TT_Task | Sub-system Safety Requirement Specification DMU M2 | 02/09/2020 | 08/12/2020 | 02/09/2020 | 08/12/2020 | 0 | TK_Complete | 1208363553 | 501 | 1208363553_501
MRPP2-DE2.16523 | TT_Task | Sub-system Safety Requirement Specification - PTA Design Review Rev.A DMU M2 | 09/12/2020 | 21/01/2021 | 09/12/2020 | 21/01/2021 | 0 | TK_Complete | 1208363553 | 501 | 1208363553_501
MRPP2-DE2.18823 | TT_Task | Sub-system Safety Requirement Specification - PTA Design Review Rev.B DMU M2 | 06/04/2021 | 04/05/2021 | 02/04/2021 | 04/05/2021 | 0 | TK_Complete | 1208363553 | 501 | 1208363553_501
MRPP2-DE2.18833 | TT_Task | Sub-system Safety Requirement Specification - Submit Rev.B DMU M2 | 22/01/2021 | 01/04/2021 | 22/01/2021 | 01/04/2021 | 0 | TK_Complete | 1208363553 | 501 | 1208363553_501
MRPP2-DE2.16423 | TT_Task | Train Software Management Plan DMU M2 | 07/02/2020 | 29/04/2020 | 07/02/2020 | 29/04/2020 | 0 | TK_Complete | 1208363553 | 222 | 1208363553_222
MRPP2-DE2.16443 | TT_Task | Train Software Management Plan - PTA Design Review DMU M2 | 30/04/2020 | 27/05/2020 | 30/04/2020 | 27/05/2020 | 0 | TK_Complete | 1208363553 | 222 | 1208363553_222
MRPP2-DE3.14600 | TT_Task | Preliminary Hazard Analysis (PHA) DMU M3 | 25/08/2020 | 04/12/2020 | 25/08/2020 | 04/12/2020 | 0 | TK_Complete | 1208363553 | 502 | 1208363553_502
MRPP2-DE3.14820 | TT_Task | Preliminary Hazard Analysis (PHA) - PTA Design Review Rev.A DMU M3 | 07/12/2020 | 21/01/2021 | 07/12/2020 | 21/01/2021 | 0 | TK_Complete | 1208363553 | 224 | 1208363553_224
MRPP2-DE3.22510 | TT_Task | Preliminary Hazard Analysis (PHA) - Submit Rev.B DMU M3 | 22/01/2021 | 09/11/2021 | 22/01/2021 | 09/11/2021 | 0 | TK_Complete | 1208363553 | 502 | 1208363553_502
MRPP2-DE3.22520 | TT_Task | Preliminary Hazard Analysis (PHA) - PTA Design Review Rev.B DMU M3 | 10/11/2021 | 10/12/2021 | 10/11/2021 | 18/02/2022 | 0 | TK_Complete | 1208363553 | 224 | 1208363553_224
MRPP2-DE3.29440 | TT_Task | Preliminary Hazard Analysis (PHA) - Submit Rev.C DMU M3 | 22/01/2021 | 05/02/2021 | 19/02/2021 | nan | 0 | TK_Active | 1208363553 | 502 | 1208363553_502
MRPP2-DE3.29450 | TT_Task | Preliminary Hazard Analysis (PHA) - PTA Design Review Rev.C DMU M3 | 12/04/2022 | 10/05/2022 | nan | nan | 0 | TK_NotStart | 1208363553 | 224 | 1208363553_224
MRPP2-DE3.15540 | TT_Task | Reliability Apportionment and Prediction Report DMU M3 | 07/10/2020 | 12/07/2021 | 07/10/2020 | 12/07/2021 | 0 | TK_Complete | 1208363553 | 503 | 1208363553_503
MRPP2-DE3.15560 | TT_Task | Reliability Apportionment and Prediction Report - PTA Design Review Rev.A DMU M3 | 13/07/2021 | 13/08/2021 | 13/07/2021 | 13/08/2021 | 0 | TK_Complete | 1208363553 | 500 | 1208363553_500
MRPP2-DE3.27390 | TT_Task | Reliability Apportionment and Prediction Report - Submit Rev.B DMU M3 | 16/08/2021 | 21/09/2021 | 14/08/2021 | 21/09/2021 | 0 | TK_Complete | 1208363553 | 503 | 1208363553_503
MRPP2-DE3.27400 | TT_Task | Reliability Apportionment and Prediction Report - PTA Design Review Rev.B DMU M3 | 22/09/2021 | 02/11/2021 | 22/09/2021 | 02/11/2021 | 0 | TK_Complete | 1208363553 | 500 | 1208363553_500
MRPP2-DE3.28770 | TT_Task | Reliability Apportionment and Prediction Report - Submit Rev.C DMU M3 | 03/11/2021 | 11/02/2022 | 03/11/2021 | nan | 0 | TK_Active | 1208363553 | 503 | 1208363553_503
MRPP2-DE3.28780 | TT_Task | Reliability Apportionment and Prediction Report - PTA Design Review Rev.C DMU M3 | 12/04/2022 | 10/05/2022 | nan | nan | 0 | TK_NotStart | 1208363553 | 500 | 1208363553_500
MRPP2-DE3.14680 | TT_Task | RAM demonstration ; FRACAS Plan DMU M3 | 04/12/2020 | 11/06/2021 | 04/12/2020 | 11/06/2021 | 0 | TK_Complete | 1208363553 | 504 | 1208363553_504
MRPP2-DE3.15110 | TT_Task | RAM demonstration ; FRACAS Plan - PTA Design Review Rev.A DMU M3 | 14/06/2021 | 13/08/2021 | 14/06/2021 | 13/08/2021 | 0 | TK_Complete | 1208363553 | 228 | 1208363553_228
MRPP2-DE3.27410 | TT_Task | RAM demonstration ; FRACAS Plan - Submit Rev.B DMU M3 | 16/08/2021 | 02/12/2021 | 16/08/2021 | 02/12/2021 | 0 | TK_Complete | 1208363553 | 504 | 1208363553_504
MRPP2-DE3.27420 | TT_Task | RAM demonstration ; FRACAS Plan - PTA Design Review Rev.B DMU M3 | 03/12/2021 | 03/01/2022 | 03/12/2021 | 01/03/2022 | 0 | TK_Complete | 1208363553 | 228 | 1208363553_228
MRPP2-DE3.29580 | TT_Task | RAM demonstration ; FRACAS Plan - Submit Rev.C DMU M3 | 04/03/2022 | 17/03/2022 | 02/03/2022 | nan | 0 | TK_Active | 1208363553 | 504 | 1208363553_504
MRPP2-DE3.29590 | TT_Task | RAM demonstration ; FRACAS Plan - PTA Design Review Rev.C DMU M3 | 12/04/2022 | 10/05/2022 | nan | nan | 0 | TK_NotStart | 1208363553 | 228 | 1208363553_228
MRPP2-DE3.16260 | TT_Task | Interface hazard analysis (IHA) DMU M3 | 11/09/2020 | 12/03/2021 | 11/09/2020 | 12/03/2021 | 0 | TK_Complete | 1208363553 | 229 | 1208363553_229
MRPP2-DE3.16280 | TT_Task | Interface hazard analysis (IHA) - PTA Design Review Rev.A DMU M3 | 15/03/2021 | 22/04/2021 | 15/03/2021 | 22/04/2021 | 0 | TK_Complete | 1208363553 | 230 | 1208363553_230
MRPP2-DE3.23250 | TT_Task | Interface hazard analysis (IHA) - Submit Rev.B DMU M3 | 23/04/2021 | 09/11/2021 | 23/04/2021 | 09/11/2021 | 0 | TK_Complete | 1208363553 | 229 | 1208363553_229
MRPP2-DE3.23260 | TT_Task | Interface hazard analysis (IHA) - PTA Design Review Rev.B DMU M3 | 10/11/2021 | 10/12/2021 | 10/11/2021 | 18/02/2022 | 0 | TK_Complete | 1208363553 | 230 | 1208363553_230
MRPP2-DE3.29460 | TT_Task | Interface hazard analysis (IHA) - Submit Rev.C DMU M3 | 04/03/2022 | 17/03/2022 | 21/02/2022 | nan | 0 | TK_Active | 1208363553 | 229 | 1208363553_229
MRPP2-DE3.29470 | TT_Task | Interface hazard analysis (IHA) - PTA Design Review Rev.C DMU M3 | 12/04/2022 | 10/05/2022 | nan | nan | 0 | TK_NotStart | 1208363553 | 230 | 1208363553_230
MRPP2-DE3.16340 | TT_Task | Subsystem hazard analysis (SSHA) DMU M3 | 17/12/2020 | 10/05/2021 | 17/12/2020 | 10/05/2021 | 0 | TK_Complete | 1208363553 | 231 | 1208363553_231
MRPP2-DE3.16360 | TT_Task | Subsystem hazard analysis (SSHA) - PTA Design Review Rev.A DMU M3 | 11/05/2021 | 08/06/2021 | 11/05/2021 | 08/06/2021 | 0 | TK_Complete | 1208363553 | 232 | 1208363553_232
MRPP2-DE3.23660 | TT_Task | Subsystem hazard analysis (SSHA) - Submit Rev.B DMU M3 | 09/06/2021 | 13/08/2021 | 09/06/2021 | 13/08/2021 | 0 | TK_Complete | 1208363553 | 231 | 1208363553_231
MRPP2-DE3.23670 | TT_Task | Subsystem hazard analysis (SSHA) - PTA Design Review Rev.B DMU M3 | 16/08/2021 | 30/09/2021 | 14/08/2021 | 30/09/2021 | 0 | TK_Complete | 1208363553 | 232 | 1208363553_232
MRPP2-DE3.27650 | TT_Task | Subsystem hazard analysis (SSHA) - Submit Rev.C DMU M3 | 01/10/2021 | 15/02/2022 | 01/10/2021 | nan | 32 | TK_Active | 1208363553 | 231 | 1208363553_231
MRPP2-DE3.27660 | TT_Task | Subsystem hazard analysis (SSHA) - PTA Design Review Rev.C DMU M3 | 12/04/2022 | 10/05/2022 | nan | nan | 0 | TK_NotStart | 1208363553 | 232 | 1208363553_232
MRPP2-DE3.16580 | TT_Task | Failure modes effects and criticality analysis (FMECA) DMU M3 | 23/12/2020 | 06/09/2021 | 23/12/2020 | 06/09/2021 | 0 | TK_Complete | 1208363553 | 234 | 1208363553_234
MRPP2-DE3.16600 | TT_Task | Failure modes effects and criticality analysis (FMECA) - PTA Design Review Rev.A DMU M3 | 07/09/2021 | 13/10/2021 | 07/09/2021 | 13/10/2021 | 0 | TK_Complete | 1208363553 | 235 | 1208363553_235
MRPP2-DE3.28790 | TT_Task | Failure modes effects and criticality analysis (FMECA) - Submit Rev.B DMU M3 | 14/10/2021 | 22/03/2022 | 14/10/2021 | nan | 0 | TK_Active | 1208363553 | 234 | 1208363553_234
MRPP2-DE3.28800 | TT_Task | Failure modes effects and criticality analysis (FMECA) - PTA Design Review Rev.B DMU M3 | 12/04/2022 | 10/05/2022 | nan | nan | 0 | TK_NotStart | 1208363553 | 235 | 1208363553_235
MRPP2-DE3.16620 | TT_Task | Safety Critical Item List DMU M3 | 23/12/2020 | 15/03/2021 | 23/12/2020 | 15/03/2021 | 0 | TK_Complete | 1208363553 | 505 | 1208363553_505
MRPP2-DE3.16640 | TT_Task | Safety Critical Item List - PTA Design Review DMU M3 | 16/03/2021 | 14/04/2021 | 16/03/2021 | 14/04/2021 | 0 | TK_Complete | 1208363553 | 505 | 1208363553_505
MRPP2-DE3.15910 | TT_Task | Reliability Critical Item List DMU M3 | 23/12/2020 | 15/09/2021 | 23/12/2020 | 15/09/2021 | 0 | TK_Complete | 1208363553 | 505 | 1208363553_505
MRPP2-DE3.16030 | TT_Task | Reliability Critical Item List - PTA Design Review DMU M3 | 16/09/2021 | 14/10/2021 | 16/09/2021 | 14/10/2021 | 0 | TK_Complete | 1208363553 | 505 | 1208363553_505
MRPP2-DE3.21280 | TT_Task | Safety Validation Plan DMU - PTA Review Rev.A | 08/09/2021 | 19/10/2021 | 08/09/2021 | 19/10/2021 | 0 | TK_Complete | 1208363553 | 506 | 1208363553_506
MRPP2-DE3.28810 | TT_Task | Safety Validation Plan DMU - Submission Rev.B | 20/10/2021 | 06/05/2022 | 20/10/2021 | nan | 0 | TK_Active | 1208363553 | 506 | 1208363553_506
MRPP2-DE3.28820 | TT_Task | Safety Validation Plan DMU - PTA Review Rev.B | 09/05/2022 | 03/06/2022 | nan | nan | 64576 | TK_NotStart | 1208363553 | 506 | 1208363553_506
MRPP2-DE3.21830 | TT_Task | Quantitative fault tree analysis DMU - PTA Review Rev.A | 13/02/2023 | 10/03/2023 | 28/12/2021 | 01/03/2022 | 0 | TK_Complete | 1208363553 | 507 | 1208363553_507
MRPP2-DE3.29640 | TT_Task | Quantitative fault tree analysis DMU - Submission Rev.B | 04/03/2022 | 17/03/2022 | 02/03/2022 | nan | 0 | TK_Active | 1208363553 | 507 | 1208363553_507
MRPP2-DE3.29650 | TT_Task | Quantitative fault tree analysis DMU - PTA Review Rev.B | 12/04/2022 | 10/05/2022 | nan | nan | 64720 | TK_NotStart | 1208363553 | 507 | 1208363553_507
MRPP2-DE3.21840 | TT_Task | Design Safety Study Report DMU - PTA Review and Approval | 13/02/2023 | 10/03/2023 | nan | nan | 984 | TK_NotStart | 1208363553 | 506 | 1208363553_506
MRPP2-DE3.21850 | TT_Task | Hazard Log DMU - PTA Review and Approval | 13/02/2023 | 10/03/2023 | nan | nan | 984 | TK_NotStart | 1208363553 | 238 | 1208363553_238
MRPP2-DE3.21860 | TT_Task | Application Safety Case DMU - PTA Review and Approval | 13/02/2023 | 10/03/2023 | nan | nan | 984 | TK_NotStart | 1208363553 | 506 | 1208363553_506
MRPP2-DE1.13873 | TT_Task | System Description of Power Pack DMU M1 | 31/03/2020 | 04/09/2020 | 31/03/2020 | 04/09/2020 | 0 | TK_Complete | 1208363553 | 508 | 1208363553_508
MRPP2-DE1.13893 | TT_Task | System Description of Power Pack - PTA Design Review Rev.A DMU M1 | 07/09/2020 | 05/10/2020 | 07/09/2020 | 05/10/2020 | 0 | TK_Complete | 1208363553 | 509 | 1208363553_509
MRPP2-DE1.15843 | TT_Task | System Description of Power Pack - Submit Rev.B DMU M1 | 06/10/2020 | 20/01/2021 | 06/10/2020 | 20/01/2021 | 0 | TK_Complete | 1208363553 | 508 | 1208363553_508
MRPP2-DE1.15853 | TT_Task | System Description of Power Pack - PTA Design Review Rev.B DMU M1 | 21/01/2021 | 16/02/2021 | 21/01/2021 | 16/02/2021 | 0 | TK_Complete | 1208363553 | 509 | 1208363553_509
MRPP2-DE2.16543 | TT_Task | Technical Description of Power Pack DMU M2 | 01/10/2020 | 03/03/2021 | 01/10/2020 | 03/03/2021 | 0 | TK_Complete | 1208363553 | 508 | 1208363553_508
MRPP2-DE2.16563 | TT_Task | Technical Description of Power Pack - PTA Design Review Rev.A DMU M2 | 04/03/2021 | 30/03/2021 | 04/03/2021 | 30/03/2021 | 0 | TK_Complete | 1208363553 | 509 | 1208363553_509
MRPP2-DE2.19143 | TT_Task | Technical Description of Power Pack - Submit Rev.B DMU M2 | 31/03/2021 | 02/07/2021 | 31/03/2021 | 02/07/2021 | 0 | TK_Complete | 1208363553 | 508 | 1208363553_508
MRPP2-DE2.19153 | TT_Task | Technical Description of Power Pack - PTA Design Review Rev.B DMU M2 | 05/07/2021 | 06/08/2021 | 03/07/2021 | 06/08/2021 | 0 | TK_Complete | 1208363553 | 509 | 1208363553_509
MRPP2-DE2.19383 | TT_Task | Technical Description of Power Pack - Submit Rev.C DMU M2 | 09/08/2021 | 15/02/2022 | 09/08/2021 | 17/12/2021 | 0 | TK_Complete | 1208363553 | 508 | 1208363553_508
MRPP2-DE2.19393 | TT_Task | Technical Description of Power Pack - PTA Design Review Rev.C DMU M2 | 11/03/2022 | 07/04/2022 | 20/12/2021 | 01/03/2022 | 0 | TK_Complete | 1208363553 | 509 | 1208363553_509
MRPP2-DE3.21470 | TT_Task | Power Pack Functional Type Test Procedure DMU - PTA Review and Approval | 18/11/2022 | 15/12/2022 | nan | nan | 1440 | TK_NotStart | 1208363553 | 489 | 1208363553_489
MRPP2-DE3.21930 | TT_Task | Thermal Engine Static Type Test Procedure DMU - PTA Review and Approval | 18/11/2022 | 15/12/2022 | nan | nan | 1440 | TK_NotStart | 1208363553 | 510 | 1208363553_510
MRPP2-DE3.21970 | TT_Task | Test Specification of AC Generator DMU - PTA Review and Approval | 22/12/2022 | 23/01/2023 | nan | nan | 1248 | TK_NotStart | 1208363553 | 489 | 1208363553_489
MRPP2-DE3.22130 | TT_Task | Thermal Engine Dynamic Type Test Procedure DMU - PTA Review and Approval | 18/01/2023 | 15/02/2023 | nan | nan | 1120 | TK_NotStart | 1208363553 | 510 | 1208363553_510
MRPP2-DE1.14883 | TT_Task | System Description - Toilet DMU M1 | 31/03/2020 | 26/08/2020 | 31/03/2020 | 26/08/2020 | 0 | TK_Complete | 1208363553 | 511 | 1208363553_511
MRPP2-DE1.14903 | TT_Task | System Description - Toilet - PTA Design Review Rev.A DMU M1 | 27/08/2020 | 21/09/2020 | 27/08/2020 | 21/09/2020 | 0 | TK_Complete | 1208363553 | 512 | 1208363553_512
MRPP2-DE1.15773 | TT_Task | System Description - Toilet - Resubmit Rev.B DMU M1 | 22/09/2020 | 05/11/2020 | 22/09/2020 | 05/11/2020 | 0 | TK_Complete | 1208363553 | 511 | 1208363553_511
MRPP2-DE1.15783 | TT_Task | System Description - Toilet - PTA Design Review Rev.B DMU M1 | 06/11/2020 | 02/12/2020 | 06/11/2020 | 02/12/2020 | 0 | TK_Complete | 1208363553 | 512 | 1208363553_512
MRPP2-DE1.16023 | TT_Task | System Description - Toilet - Resubmit Rev.C DMU M1 | 03/12/2020 | 04/05/2021 | 03/12/2020 | 04/05/2021 | 0 | TK_Complete | 1208363553 | 511 | 1208363553_511
MRPP2-DE1.16033 | TT_Task | System Description - Toilet - PTA Design Review Rev.C DMU M1 | 05/05/2021 | 31/05/2021 | 05/05/2021 | 31/05/2021 | 0 | TK_Complete | 1208363553 | 512 | 1208363553_512
MRPP2-DE2.16583 | TT_Task | Final Technical Description and Drawings of Toilets DMU M3 | 26/04/2022 | 24/05/2022 | nan | nan | 0 | TK_NotStart | 1208363553 | 512 | 1208363553_512
MRPP2-DE2.16603 | TT_Task | Final Technical Description and Drawings of Toilets - PTA Design Review DMU M3 | 25/05/2022 | 22/06/2022 | nan | nan | 0 | TK_NotStart | 1208363553 | 512 | 1208363553_512
MRPP2-DE3.21520 | TT_Task | Toilet System Functional Type Test Procedure ? TOI DMU - PTA Review and Approval | 10/11/2022 | 07/12/2022 | nan | nan | 1488 | TK_NotStart | 1208363553 | 470 | 1208363553_470
MRPP2-DE1.14923 | TT_Task | System Description - Galley DMU M1 | 31/03/2020 | 29/09/2020 | 31/03/2020 | 29/09/2020 | 0 | TK_Complete | 1208363553 | 513 | 1208363553_513
MRPP2-DE1.14943 | TT_Task | System Description - Galley - PTA Design Review Rev.A DMU M1 | 30/09/2020 | 22/10/2020 | 30/09/2020 | 22/10/2020 | 0 | TK_Complete | 1208363553 | 514 | 1208363553_514
MRPP2-DE1.15923 | TT_Task | System Description - Galley - Submit Rev.B DMU M1 | 23/10/2020 | 04/02/2021 | 23/10/2020 | 04/02/2021 | 0 | TK_Complete | 1208363553 | 513 | 1208363553_513
MRPP2-DE1.15933 | TT_Task | System Description - Galley - PTA Design Review Rev.B DMU M1 | 05/02/2021 | 05/03/2021 | 05/02/2021 | 05/03/2021 | 0 | TK_Complete | 1208363553 | 514 | 1208363553_514
MRPP2-DE1.16103 | TT_Task | System Description - Galley - Submit Rev.C DMU M1 | 08/03/2021 | 16/04/2021 | 08/03/2021 | 16/04/2021 | 0 | TK_Complete | 1208363553 | 513 | 1208363553_513
MRPP2-DE1.16113 | TT_Task | System Description - Galley - PTA Design Review Rev.C DMU M1 | 19/04/2021 | 17/05/2021 | 19/04/2021 | 17/05/2021 | 0 | TK_Complete | 1208363553 | 514 | 1208363553_514
MRPP2-DE1.16123 | TT_Task | System Description - Galley - Submit Rev.D DMU M1 | 18/05/2021 | 05/08/2021 | 18/05/2021 | 05/08/2021 | 0 | TK_Complete | 1208363553 | 513 | 1208363553_513
MRPP2-DE1.16133 | TT_Task | System Description - Galley - PTA Design Review Rev.D DMU M1 | 06/08/2021 | 21/09/2021 | 06/08/2021 | 21/09/2021 | 0 | TK_Complete | 1208363553 | 514 | 1208363553_514
MRPP2-DE2.16623 | TT_Task | Final Technical Description and Drawings of Galley DMU M3 | 04/04/2022 | 23/06/2022 | 04/03/2022 | nan | 0 | TK_Active | 1208363553 | 515 | 1208363553_515
MRPP2-DE2.16643 | TT_Task | Final Technical Description and Drawings of Galley - PTA Design Review DMU M3 | 25/05/2022 | 22/06/2022 | nan | nan | 0 | TK_NotStart | 1208363553 | 515 | 1208363553_515
MRPP2-DE3.22220 | TT_Task | Galley Functional Type Test Procedure ? CAT (DMU) DMU - PTA Review and Approval | 23/06/2022 | 20/07/2022 | nan | nan | 2280 | TK_NotStart | 1208363553 | 470 | 1208363553_470
MRPP2-DE1.14963 | TT_Task | System Description - Internal Door DMU M1 | 31/03/2020 | 16/09/2020 | 31/03/2020 | 16/09/2020 | 0 | TK_Complete | 1208363553 | 516 | 1208363553_516
MRPP2-DE1.14983 | TT_Task | System Description - Internal Door - PTA Design Review Rev.A DMU M1 | 17/09/2020 | 12/10/2020 | 17/09/2020 | 12/10/2020 | 0 | TK_Complete | 1208363553 | 516 | 1208363553_516
MRPP2-DE1.15883 | TT_Task | System Description - Internal Door - Submit Rev.B DMU M1 | 13/10/2020 | 15/12/2020 | 13/10/2020 | 15/12/2020 | 0 | TK_Complete | 1208363553 | 516 | 1208363553_516
MRPP2-DE1.15893 | TT_Task | System Description - Internal Door - PTA Design Review Rev.B DMU M1 | 16/12/2020 | 29/01/2021 | 16/12/2020 | 29/01/2021 | 0 | TK_Complete | 1208363553 | 516 | 1208363553_516
MRPP2-DE2.16663 | TT_Task | Final Technical Description and Drawings of Internal Door DMU M3 | 05/05/2021 | 25/11/2021 | 05/05/2021 | 25/11/2021 | 0 | TK_Complete | 1208363553 | 516 | 1208363553_516
MRPP2-DE2.16683 | TT_Task | Final Technical Description and Drawings of Internal Door - PTA Design Review Rev.A DMU M3 | 26/11/2021 | 23/12/2021 | 26/11/2021 | 22/02/2022 | 0 | TK_Complete | 1208363553 | 516 | 1208363553_516
MRPP2-DE2.19483 | TT_Task | Final Technical Description and Drawings of Internal Door - Submit Rev.B DMU M3 | 04/03/2022 | 17/03/2022 | 23/02/2022 | nan | 0 | TK_Active | 1208363553 | 516 | 1208363553_516
MRPP2-DE2.19493 | TT_Task | Final Technical Description and Drawings of Internal Door - PTA Design Review Rev.B DMU M3 | 12/04/2022 | 10/05/2022 | nan | nan | 0 | TK_NotStart | 1208363553 | 516 | 1208363553_516
MRPP2-DE3.21480 | TT_Task | Internal Doors Functional Type Test Procedure ? IDR DMU - PTA Review and Approval | 08/12/2022 | 09/01/2023 | nan | nan | 1328 | TK_NotStart | 1208363553 | 167 | 1208363553_167
MRPP2-DE3.21890 | TT_Task | Internal Doors Performance Type Test Procedure DMU - PTA Review and Approval | 08/12/2022 | 09/01/2023 | nan | nan | 1328 | TK_NotStart | 1208363553 | 167 | 1208363553_167
MRPP2-DE3.25780 | TT_Task | IOS List DMU M3 | 03/05/2021 | 20/05/2021 | 01/05/2021 | 20/05/2021 | 0 | TK_Complete | 1208363553 | 517 | 1208363553_517
MRPP2-DE3.25800 | TT_Task | IOS List - PTA Design Review Rev.A DMU M3 | 21/05/2021 | 02/07/2021 | 21/05/2021 | 02/07/2021 | 0 | TK_Complete | 1208363553 | 245 | 1208363553_245
MRPP2-DE3.25890 | TT_Task | IOS List - Submit Rev.B DMU M3 | 05/07/2021 | 18/04/2022 | 03/07/2021 | nan | 0 | TK_Active | 1208363553 | 517 | 1208363553_517
MRPP2-DE3.25900 | TT_Task | IOS List - PTA Design Review ; Approval Rev.B DMU M3 | 19/04/2022 | 17/05/2022 | nan | nan | 64680 | TK_NotStart | 1208363553 | 245 | 1208363553_245
MRPP2-DE3.25870 | TT_Task | Surface Protection / Corrosion Management Plan DMU - PTA Review Rev.A | 28/05/2021 | 28/06/2021 | 28/05/2021 | 28/06/2021 | 0 | TK_Complete | 1208363553 | 249 | 1208363553_249
MRPP2-DE3.26530 | TT_Task | Surface Protection / Corrosion Management Plan DMU - Submission Rev.B | 29/06/2021 | 29/10/2021 | 29/06/2021 | 29/10/2021 | 0 | TK_Complete | 1208363553 | 249 | 1208363553_249
MRPP2-DE3.26540 | TT_Task | Surface Protection / Corrosion Management Plan DMU - PTA Review Rev.B | 01/11/2021 | 26/11/2021 | 01/11/2021 | 26/11/2021 | 0 | TK_Complete | 1208363553 | 249 | 1208363553_249
MRPP2-DE3.25980 | TT_Task | Obsolescence Management Plan DMU - PTA Review Rev.A | 24/06/2021 | 26/07/2021 | 24/06/2021 | 26/07/2021 | 0 | TK_Complete | 1208363553 | 518 | 1208363553_518
MRPP2-DE3.26550 | TT_Task | Obsolescence Management Plan DMU - Submission Rev.B | 27/07/2021 | 24/05/2022 | 27/07/2021 | 11/03/2022 | 0 | TK_Complete | 1208363553 | 518 | 1208363553_518
MRPP2-DE3.26560 | TT_Task | Obsolescence Management Plan DMU - PTA Review Rev.B | 25/05/2022 | 22/06/2022 | 14/03/2022 | nan | 64872 | TK_Active | 1208363553 | 518 | 1208363553_518
MRPP2-DE3.26110 | TT_Task | Dangerous Substance Report DMU - PTA Review and Approval | 07/04/2022 | 09/05/2022 | nan | nan | 64728 | TK_NotStart | 1208363553 | 254 | 1208363553_254
MRPP2-DE3.26350 | TT_Task | Interface Management Plan DMU - PTA Review and Approval | 13/08/2021 | 01/10/2021 | 13/08/2021 | 01/10/2021 | 0 | TK_Complete | 1208363553 | 201 | 1208363553_201
MRPP2-DE3.26040 | TT_Task | Lock Specification DMU - PTA Review and Approval | 11/11/2022 | 08/12/2022 | nan | nan | 63520 | TK_NotStart | 1208363553 | 519 | 1208363553_519
MRPP2-DE3.26030 | TT_Task | Interior Lighting Performances DMU - PTA Review and Approval | 16/12/2022 | 17/01/2023 | nan | nan | 63320 | TK_NotStart | 1208363553 | 258 | 1208363553_258
MRPP2-DE3.26430 | TT_Task | Human Factor Issues Register DMU - PTA Review and Approval | 12/01/2023 | 09/02/2023 | nan | nan | 63192 | TK_NotStart | 1208363553 | 265 | 1208363553_265
MRPP2-DE3.26270 | TT_Task | Seat Configuration Change DMU - PTA Review and Approval | 04/01/2023 | 01/02/2023 | nan | nan | 63240 | TK_NotStart | 1208363553 | 519 | 1208363553_519
MRPP2-DE3.26220 | TT_Task | Interior Saloon FEA Reports DMU - PTA Review and Approval | 08/12/2022 | 09/01/2023 | nan | nan | 63368 | TK_NotStart | 1208363553 | 269 | 1208363553_269
MRPP2-DE3.26500 | TT_Task | Lock Document DMU - PTA Review and Approval | 07/12/2022 | 06/01/2023 | nan | nan | 63376 | TK_NotStart | 1208363553 | 519 | 1208363553_519
MRPP2-DE3.26520 | TT_Task | Gaps ; Flush Document (DMU) - PTA Review and Approval | 09/01/2023 | 06/02/2023 | nan | nan | 63216 | TK_NotStart | 1208363553 | 519 | 1208363553_519
MRPP2-DE3.26210 | TT_Task | Interior GA Drawing (DMU) EMU - PTA Review and Approval | 23/11/2022 | 20/12/2022 | nan | nan | 63456 | TK_NotStart | 1208363553 | 270 | 1208363553_270
MRPP2-DE3.26200 | TT_Task | Fitting GA Drawing (DMU) EMU - PTA Review and Approval | 23/11/2022 | 20/12/2022 | nan | nan | 63456 | TK_NotStart | 1208363553 | 271 | 1208363553_271
MRPP2-DE3.26510 | TT_Task | Pneumatics GA Drawing DMU - PTA Review and Approval | 09/01/2023 | 06/02/2023 | nan | nan | 63216 | TK_NotStart | 1208363553 | 272 | 1208363553_272
MRPP2-DE3.28000 | TT_Task | Ergonomic Assessment of Maintenance DMU - PTA Review and Approval | 15/11/2022 | 12/12/2022 | nan | nan | 63504 | TK_NotStart | 1208363553 | 260 | 1208363553_260
MRPP2-DE3.28020 | TT_Task | Engineering Virtual Mockup Specification - Saloon and Cab / Digital 3D - Model Specification - PTA Review and Approval | 18/09/2020 | 14/10/2020 | 18/09/2020 | 14/10/2020 | 0 | TK_Complete | 1208363553 | 276 | 1208363553_276
MRPP2-DE3.28040 | TT_Task | Electrical Energy Functional Type Test Procedure ? MVS DMU - PTA Review and Approval | 27/09/2022 | 24/10/2022 | nan | nan | 63784 | TK_NotStart | 1208363553 | 55 | 1208363553_55
MRPP2-DE3.28060 | TT_Task | Sanding Functional Type Test Procedure ? SAN DMU - PTA Review and Approval | 30/09/2022 | 27/10/2022 | nan | nan | 63760 | TK_NotStart | 1208363553 | 279 | 1208363553_279
MRPP2-DE3.28080 | TT_Task | Coupling Functional Type Test Procedure ? CPL DMU - PTA Review and Approval | 14/10/2022 | 10/11/2022 | nan | nan | 63680 | TK_NotStart | 1208363553 | 280 | 1208363553_280
MRPP2-DE3.28140 | TT_Task | Inspection instruction for complete carbody DMU - PTA Review and Approval | 14/10/2022 | 10/11/2022 | nan | nan | 63680 | TK_NotStart | 1208363553 | 247 | 1208363553_247
MRPP2-DE3.28160 | TT_Task | Software document for TCMS DMU - PTA Review and Approval | 13/01/2023 | 10/02/2023 | nan | nan | 63184 | TK_NotStart | 1208363553 | 136 | 1208363553_136
MRPP2-DE3.28180 | TT_Task | Training Plan DMU - PTA Review and Approval | 30/07/2021 | 27/08/2021 | 30/07/2021 | 27/08/2021 | 0 | TK_Complete | 1208363553 | 252 | 1208363553_252
MRPP2-DE3.28120 | TT_Task | Ergonomics Management Plan DMU - PTA Review and Approval | 24/01/2023 | 21/02/2023 | 13/01/2022 | nan | 64880 | TK_Active | 1208363553 | 248 | 1208363553_248
MRPP2-DE3.28100 | TT_Task | Passenger Flow Evaluation DMU - PTA Review and Approval | 25/03/2021 | 23/04/2021 | 25/03/2021 | 23/04/2021 | 0 | TK_Complete | 1208363553 | 277 | 1208363553_277
MRPP2-DE3.28200 | TT_Task | Certification Plan DMU - PTA Review and Approval | 12/01/2023 | 09/02/2023 | nan | nan | 63192 | TK_NotStart | 1208363553 | 252 | 1208363553_252
MRPP2-DE1.15003 | TT_Task | Digital 3D-Model Specification DMU | 11/03/2020 | 18/09/2020 | 11/03/2020 | 18/09/2020 | 0 | TK_Complete | 1208363553 | 520 | 1208363553_520
MRPP2-DE1.15023 | TT_Task | Digital 3D-Model Specification - PTA Design Review DMU | 17/09/2020 | 14/10/2020 | 17/09/2020 | 14/10/2020 | 0 | TK_Complete | 1208363553 | 521 | 1208363553_521
MRPP2-DE2.18053 | TT_Task | Digital 3D-Model V1 DMU | 29/07/2021 | 31/01/2022 | 29/07/2021 | nan | 0 | TK_Active | 1208363553 | 520 | 1208363553_520
MRPP2-DE2.18073 | TT_Task | Digital 3D-Model V1 - PTA Design Review DMU | 12/04/2022 | 10/05/2022 | nan | nan | 0 | TK_NotStart | 1208363553 | 521 | 1208363553_521
MRPP2-DE3.22280 | TT_Task | Digital 3D-Model V2 DMU | 18/01/2021 | 31/03/2022 | 18/01/2021 | nan | 0 | TK_Active | 1208363553 | 520 | 1208363553_520
MRPP2-DE3.22300 | TT_Task | Digital 3D-Model V2 - PTA Design Review DMU | 12/04/2022 | 10/05/2022 | nan | nan | 0 | TK_NotStart | 1208363553 | 521 | 1208363553_521
MRPP2.SOU.33510 | TT_Task | DMU - TPS for Power Pack and System | 16/06/2020 | 01/10/2020 | 16/06/2020 | 01/10/2020 | 0 | TK_Complete | 1208363553 | 508 | 1208363553_508
MRPP2.SOU.33550 | TT_Task | DMU - TPS for Toilet Components | 28/07/2020 | 07/09/2020 | 28/07/2020 | 07/09/2020 | 0 | TK_Complete | 1208363553 | 522 | 1208363553_522
MRPP2-SOU.11050 | TT_Task | DMU - RFQ Diesel Engine | 28/07/2020 | 06/10/2020 | 28/07/2020 | 06/10/2020 | 0 | TK_Complete | 1208363553 | 523 | 1208363553_523
MRPP2-SOU.11630 | TT_Task | DMU - BA Diesel Engine | 07/10/2020 | 15/02/2021 | 07/10/2020 | 15/02/2021 | 0 | TK_Complete | 1208363553 | 524 | 1208363553_524
MRPP2-SUP.10530 | TT_Task | DMU - PO Diesel Engine | 16/02/2021 | 15/03/2021 | 16/02/2021 | 15/03/2021 | 0 | TK_Complete | 1208363553 | 524 | 1208363553_524
MRPP2-SUP.14670 | TT_Task | DMU - Production Diesel Engine | 16/03/2021 | 21/12/2022 | 16/03/2021 | nan | 0 | TK_Active | 1208363553 | 524 | 1208363553_524
MRPP2-SUP.18850 | TT_Task | DMU - FAI Diesel Engine | 24/11/2022 | 21/02/2023 | nan | nan | 0 | TK_NotStart | 1208363553 | 524 | 1208363553_524
MRPP2-SUP.20650 | TT_Task | DMU - DEL Diesel Engine delivery | 22/02/2023 | 01/05/2023 | nan | nan | 0 | TK_NotStart | 1208363553 | 524 | 1208363553_524
MRPP2-SOU.11090 | TT_Task | DMU - RFQ Diesel Engine Cooling System | 07/10/2020 | 08/12/2020 | 07/10/2020 | 08/12/2020 | 0 | TK_Complete | 1208363553 | 523 | 1208363553_523
MRPP2-SOU.11510 | TT_Task | DMU - BA Diesel Engine Cooling System | 09/12/2020 | 08/03/2021 | 09/12/2020 | 08/03/2021 | 0 | TK_Complete | 1208363553 | 523 | 1208363553_523
MRPP2-SUP.10480 | TT_Task | DMU - PO Diesel Engine Cooling System | 09/03/2021 | 07/04/2021 | 09/03/2021 | 07/04/2021 | 0 | TK_Complete | 1208363553 | 523 | 1208363553_523
MRPP2-SUP.14660 | TT_Task | DMU - Production Diesel Engine Cooling System | 08/04/2021 | 28/03/2023 | 08/04/2021 | nan | 0 | TK_Active | 1208363553 | 523 | 1208363553_523
MRPP2-SUP.18420 | TT_Task | DMU - FAI Diesel Engine Cooling System | 30/09/2022 | 22/12/2022 | nan | nan | 224 | TK_NotStart | 1208363553 | 523 | 1208363553_523
MRPP2-SUP.19700 | TT_Task | DMU - DEL Diesel Engine Cooling System delivery | 07/02/2023 | 13/04/2023 | nan | nan | 0 | TK_NotStart | 1208363553 | 523 | 1208363553_523
MRPP2-SOU.11110 | TT_Task | DMU - RFQ DC Generator | 07/10/2020 | 08/12/2020 | 07/10/2020 | 08/12/2020 | 0 | TK_Complete | 1208363553 | 525 | 1208363553_525
MRPP2-SOU.11700 | TT_Task | DMU - BA DC Generator | 09/12/2020 | 08/03/2021 | 09/12/2020 | 08/03/2021 | 0 | TK_Complete | 1208363553 | 525 | 1208363553_525
MRPP2-SUP.10840 | TT_Task | DMU - PO DC Generator | 09/03/2021 | 07/04/2021 | 09/03/2021 | 07/04/2021 | 0 | TK_Complete | 1208363553 | 525 | 1208363553_525
MRPP2-SUP.14970 | TT_Task | DMU - Production DC Generator | 08/04/2021 | 31/01/2023 | 08/04/2021 | nan | 0 | TK_Active | 1208363553 | 525 | 1208363553_525
MRPP2-SUP.18800 | TT_Task | DMU - FAI DC Generator | 01/12/2022 | 28/02/2023 | nan | nan | 0 | TK_NotStart | 1208363553 | 525 | 1208363553_525
MRPP2-SUP.20330 | TT_Task | DMU - DEL DC Generator delivery | 01/03/2023 | 08/05/2023 | nan | nan | 0 | TK_NotStart | 1208363553 | 525 | 1208363553_525
MRPP2-SOU.11100 | TT_Task | DMU - RFQ Air Compressor System | 07/10/2020 | 08/12/2020 | 07/10/2020 | 08/12/2020 | 0 | TK_Complete | 1208363553 | 526 | 1208363553_526
MRPP2-SOU.11690 | TT_Task | DMU - BA Air Compressor System | 09/12/2020 | 08/03/2021 | 09/12/2020 | 08/03/2021 | 0 | TK_Complete | 1208363553 | 526 | 1208363553_526
MRPP2-SUP.10830 | TT_Task | DMU - PO Air Compressor System | 09/03/2021 | 07/04/2021 | 09/03/2021 | 07/04/2021 | 0 | TK_Complete | 1208363553 | 526 | 1208363553_526
MRPP2-SUP.14910 | TT_Task | DMU - Production Air Compressor System | 08/04/2021 | 31/01/2023 | 08/04/2021 | nan | 0 | TK_Active | 1208363553 | 526 | 1208363553_526
MRPP2-SUP.18790 | TT_Task | DMU - FAI Air Compressor System | 01/12/2022 | 28/02/2023 | nan | nan | 0 | TK_NotStart | 1208363553 | 526 | 1208363553_526
MRPP2-SUP.20320 | TT_Task | DMU - DEL Air Compressor System delivery | 01/03/2023 | 08/05/2023 | nan | nan | 0 | TK_NotStart | 1208363553 | 526 | 1208363553_526
MRPP2-SOU.11120 | TT_Task | DMU - RFQ Engine Electrical Components | 07/10/2020 | 08/12/2020 | 07/10/2020 | 08/12/2020 | 0 | TK_Complete | 1208363553 | 527 | 1208363553_527
MRPP2-SOU.11710 | TT_Task | DMU - BA Engine Electrical Components | 09/12/2020 | 08/03/2021 | 09/12/2020 | 08/03/2021 | 0 | TK_Complete | 1208363553 | 527 | 1208363553_527
MRPP2-SUP.10850 | TT_Task | DMU - PO Engine Electrical Components | 09/03/2021 | 07/04/2021 | 09/03/2021 | 07/04/2021 | 0 | TK_Complete | 1208363553 | 527 | 1208363553_527
MRPP2-SUP.14980 | TT_Task | DMU - Production Engine Electrical Components | 08/04/2021 | 31/01/2023 | 08/04/2021 | nan | 0 | TK_Active | 1208363553 | 527 | 1208363553_527
MRPP2-SUP.18820 | TT_Task | DMU - FAI Engine Electrical Components | 01/12/2022 | 28/02/2023 | nan | nan | 0 | TK_NotStart | 1208363553 | 527 | 1208363553_527
MRPP2-SUP.20340 | TT_Task | DMU - DEL Engine Electrical Components delivery | 01/03/2023 | 08/05/2023 | nan | nan | 0 | TK_NotStart | 1208363553 | 527 | 1208363553_527
MRPP2-SOU.11140 | TT_Task | DMU - RFQ Toilet Components | 08/09/2020 | 10/11/2020 | 08/09/2020 | 10/11/2020 | 0 | TK_Complete | 1208363553 | 522 | 1208363553_522
MRPP2-SOU.11670 | TT_Task | DMU - BA Toilet Components | 11/11/2020 | 08/02/2021 | 11/11/2020 | 08/02/2021 | 0 | TK_Complete | 1208363553 | 522 | 1208363553_522
MRPP2-SUP.10550 | TT_Task | DMU - PO Toilet Components | 09/02/2021 | 08/03/2021 | 09/02/2021 | 08/03/2021 | 0 | TK_Complete | 1208363553 | 522 | 1208363553_522
MRPP2-SUP.14680 | TT_Task | DMU - Production Toilet Components | 09/03/2021 | 30/12/2022 | 09/03/2021 | nan | 0 | TK_Active | 1208363553 | 522 | 1208363553_522
MRPP2-SUP.18430 | TT_Task | DMU - FAI Toilet Components | 20/10/2022 | 30/11/2022 | nan | nan | 0 | TK_NotStart | 1208363553 | 522 | 1208363553_522
MRPP2-SUP.19240 | TT_Task | DMU - DEL Toilet Components Delivery | 01/12/2022 | 13/04/2023 | nan | nan | 0 | TK_NotStart | 1208363553 | 522 | 1208363553_522
MRPP2-SUP.10560 | TT_Task | DMU - PO Stainless Steel (C;B, CRF) - 2nd Fleet (6 trainsets) | 16/11/2020 | 11/12/2020 | 16/11/2020 | 11/12/2020 | 0 | TK_Complete | 1208363553 | 334 | 1208363553_334
MRPP2-SUP.14700 | TT_Task | DMU - Production Stainless Steel (C;B, CRF) | 14/12/2020 | 19/05/2022 | 14/12/2020 | nan | 0 | TK_Active | 1208363553 | 528 | 1208363553_528
MRPP2-SUP.19120 | TT_Task | DMU - DEL Stainless Steel (C;B, CRF) delivery | 04/04/2022 | 22/09/2022 | 08/03/2022 | nan | 0 | TK_Active | 1208363553 | 528 | 1208363553_528
MRPP2-SUP.10700 | TT_Task | DMU - PO Carbon Steel RM | 14/12/2020 | 13/01/2021 | 14/12/2020 | 13/01/2021 | 0 | TK_Complete | 1208363553 | 529 | 1208363553_529
MRPP2-SUP.14840 | TT_Task | DMU - Production Carbon Steel RM | 14/01/2021 | 17/06/2022 | 14/01/2021 | nan | 0 | TK_Active | 1208363553 | 529 | 1208363553_529
MRPP2-SUP.19180 | TT_Task | DMU - DEL Carbon Steel RM delivery | 04/04/2022 | 22/09/2022 | 22/03/2022 | nan | 0 | TK_Active | 1208363553 | 529 | 1208363553_529
MRPP2-SUP.10710 | TT_Task | DMU - PO Steel Casting - Equipment Support | 14/12/2020 | 13/01/2021 | 14/12/2020 | 13/01/2021 | 0 | TK_Complete | 1208363553 | 530 | 1208363553_530
MRPP2-SUP.14850 | TT_Task | DMU - Production Steel Casting - Equipment Support | 14/01/2021 | 17/06/2022 | 14/01/2021 | nan | 0 | TK_Active | 1208363553 | 530 | 1208363553_530
MRPP2-SUP.19190 | TT_Task | DMU - DEL Steel Casting - Equipment Support delivery | 04/04/2022 | 22/09/2022 | 22/03/2022 | nan | 0 | TK_Active | 1208363553 | 530 | 1208363553_530
MRPP2-SUP.10570 | TT_Task | DMU - PO Driver Cab | 16/11/2020 | 11/12/2020 | 16/11/2020 | 11/12/2020 | 0 | TK_Complete | 1208363553 | 531 | 1208363553_531
MRPP2-SUP.14710 | TT_Task | DMU - Production Driver Cab | 14/12/2020 | 29/07/2022 | 14/12/2020 | nan | 0 | TK_Active | 1208363553 | 531 | 1208363553_531
MRPP2-SUP.20020 | TT_Task | DMU - DEL Driver Cab delivery | 04/07/2022 | 19/12/2022 | nan | nan | 0 | TK_NotStart | 1208363553 | 531 | 1208363553_531
MRPP2-SUP.10580 | TT_Task | DMU - PO Side Sill (CRF Parts) | 16/11/2020 | 11/12/2020 | 16/11/2020 | 11/12/2020 | 0 | TK_Complete | 1208363553 | 532 | 1208363553_532
MRPP2-SUP.14720 | TT_Task | DMU - Production Side Sill (CRF Parts) | 14/12/2020 | 22/09/2022 | 14/12/2020 | nan | 0 | TK_Active | 1208363553 | 532 | 1208363553_532
MRPP2-SUP.20030 | TT_Task | DMU - DEL Side Sill (CRF Parts) delivery | 06/05/2022 | 24/10/2022 | nan | nan | 0 | TK_NotStart | 1208363553 | 532 | 1208363553_532
MRPP2-SUP.10590 | TT_Task | DMU - PO Underframe Panels (CRF Parts) | 16/11/2020 | 11/12/2020 | 16/11/2020 | 11/12/2020 | 0 | TK_Complete | 1208363553 | 533 | 1208363553_533
MRPP2-SUP.14730 | TT_Task | DMU - Production Underframe Panels (CRF Parts) | 14/12/2020 | 22/09/2022 | 14/12/2020 | nan | 0 | TK_Active | 1208363553 | 533 | 1208363553_533
MRPP2-SUP.20040 | TT_Task | DMU - DEL Underframe Panels (CRF Parts) delivery | 21/04/2022 | 10/10/2022 | nan | nan | 0 | TK_NotStart | 1208363553 | 533 | 1208363553_533
MRPP2-SUP.10600 | TT_Task | DMU - PO Roof Corrugation (CRF Parts) | 16/11/2020 | 11/12/2020 | 16/11/2020 | 11/12/2020 | 0 | TK_Complete | 1208363553 | 534 | 1208363553_534
MRPP2-SUP.14740 | TT_Task | DMU - Production Roof Corrugation (CRF Parts) | 14/12/2020 | 14/07/2022 | 14/12/2020 | nan | 0 | TK_Active | 1208363553 | 534 | 1208363553_534
MRPP2-SUP.20050 | TT_Task | DMU - DEL Roof Corrugation (CRF Parts) delivery | 21/04/2022 | 10/10/2022 | nan | nan | 0 | TK_NotStart | 1208363553 | 534 | 1208363553_534
MRPP2-SUP.10610 | TT_Task | DMU - PO Cantrail with Integrated roof gutter (CRF Parts) | 16/11/2020 | 11/12/2020 | 16/11/2020 | 11/12/2020 | 0 | TK_Complete | 1208363553 | 285 | 1208363553_285
MRPP2-SUP.14750 | TT_Task | DMU - Production Cantrail with Integrated roof gutter (CRF Parts) | 14/12/2020 | 14/07/2022 | 14/12/2020 | nan | 0 | TK_Active | 1208363553 | 285 | 1208363553_285
MRPP2-SUP.20060 | TT_Task | DMU - DEL Cantrail with Integrated roof gutter (CRF Parts) delivery | 21/04/2022 | 10/10/2022 | nan | nan | 0 | TK_NotStart | 1208363553 | 285 | 1208363553_285
MRPP2-SUP.10690 | TT_Task | DMU - PO EUF | 14/12/2020 | 13/01/2021 | 14/12/2020 | 13/01/2021 | 0 | TK_Complete | 1208363553 | 535 | 1208363553_535
MRPP2-SUP.14830 | TT_Task | DMU - Production EUF | 14/01/2021 | 11/08/2022 | 14/01/2021 | nan | 0 | TK_Active | 1208363553 | 535 | 1208363553_535
MRPP2-SUP.19650 | TT_Task | DMU - DEL EUF delivery | 20/05/2022 | 07/11/2022 | nan | nan | 0 | TK_NotStart | 1208363553 | 535 | 1208363553_535
MRPP2-SUP.10720 | TT_Task | DMU - PO Carline | 14/12/2020 | 13/01/2021 | 14/12/2020 | 13/01/2021 | 0 | TK_Complete | 1208363553 | 536 | 1208363553_536
MRPP2-SUP.14860 | TT_Task | DMU - Production Carline | 14/01/2021 | 11/08/2022 | 14/01/2021 | nan | 0 | TK_Active | 1208363553 | 536 | 1208363553_536
MRPP2-SUP.19660 | TT_Task | DMU - DEL Carline delivery | 20/05/2022 | 07/11/2022 | nan | nan | 0 | TK_NotStart | 1208363553 | 536 | 1208363553_536
MRPP2-SUP.10730 | TT_Task | DMU - PO Door Frame (CRF section) | 14/12/2020 | 13/01/2021 | 14/12/2020 | 13/01/2021 | 0 | TK_Complete | 1208363553 | 537 | 1208363553_537
MRPP2-SUP.14870 | TT_Task | DMU - Production Door Frame (CRF section) | 14/01/2021 | 11/08/2022 | 14/01/2021 | nan | 0 | TK_Active | 1208363553 | 537 | 1208363553_537
MRPP2-SUP.19670 | TT_Task | DMU - DEL Door Frame (CRF section) delivery | 20/05/2022 | 07/11/2022 | nan | nan | 0 | TK_NotStart | 1208363553 | 537 | 1208363553_537
MRPP2-SUP.10680 | TT_Task | DMU - PO Sidewall (Cut ; Bend Parts) | 14/12/2020 | 13/01/2021 | 14/12/2020 | 13/01/2021 | 0 | TK_Complete | 1208363553 | 538 | 1208363553_538
MRPP2-SUP.14820 | TT_Task | DMU - Production Sidewall (Cut ; Bend Parts) | 14/01/2021 | 11/08/2022 | 14/01/2021 | nan | 0 | TK_Active | 1208363553 | 538 | 1208363553_538
MRPP2-SUP.19640 | TT_Task | DMU - DEL Sidewall (Cut ; Bend Parts) delivery | 20/05/2022 | 07/11/2022 | nan | nan | 0 | TK_NotStart | 1208363553 | 538 | 1208363553_538
MRPP2-SUP.10740 | TT_Task | DMU - PO Letter Board (in Small parts) | 14/12/2020 | 13/01/2021 | 14/12/2020 | 13/01/2021 | 0 | TK_Complete | 1208363553 | 539 | 1208363553_539
MRPP2-SUP.14880 | TT_Task | DMU - Production Letter Board (in Small parts) | 14/01/2021 | 11/08/2022 | 14/01/2021 | nan | 0 | TK_Active | 1208363553 | 539 | 1208363553_539
MRPP2-SUP.19680 | TT_Task | DMU - DEL Letter Board (in Small parts) delivery | 20/05/2022 | 07/11/2022 | nan | nan | 0 | TK_NotStart | 1208363553 | 539 | 1208363553_539
MRPP2-SUP.10650 | TT_Task | DMU - PO Bogie Frame | 16/11/2020 | 11/12/2020 | 16/11/2020 | 11/12/2020 | 0 | TK_Complete | 1208363553 | 540 | 1208363553_540
MRPP2-SUP.14790 | TT_Task | DMU - Production Bogie Frame | 14/12/2020 | 02/05/2023 | 14/12/2020 | nan | 0 | TK_Active | 1208363553 | 540 | 1208363553_540
MRPP2-SUP.20200 | TT_Task | DMU - DEL Bogie Frame delivery | 06/01/2023 | 29/06/2023 | nan | nan | 0 | TK_NotStart | 1208363553 | 540 | 1208363553_540
MRPP2-SUP.10670 | TT_Task | DMU - PO Bogie Assy | 16/11/2020 | 11/12/2020 | 16/11/2020 | 11/12/2020 | 0 | TK_Complete | 1208363553 | 541 | 1208363553_541
MRPP2-SUP.14810 | TT_Task | DMU - Production Bogie Assy | 14/12/2020 | 02/05/2023 | 14/12/2020 | nan | 0 | TK_Active | 1208363553 | 541 | 1208363553_541
MRPP2-SUP.20220 | TT_Task | DMU - DEL Bogie Assy delivery | 06/01/2023 | 29/06/2023 | nan | nan | 0 | TK_NotStart | 1208363553 | 541 | 1208363553_541
MRPP2-SUP.10660 | TT_Task | DMU - PO Axle box ; bearing | 16/11/2020 | 11/12/2020 | 16/11/2020 | 11/12/2020 | 0 | TK_Complete | 1208363553 | 542 | 1208363553_542
MRPP2-SUP.14800 | TT_Task | DMU - Production Axle box ; bearing | 14/12/2020 | 28/06/2023 | 14/12/2020 | nan | 0 | TK_Active | 1208363553 | 542 | 1208363553_542
MRPP2-SUP.20210 | TT_Task | DMU - DEL Axle box ; bearing delivery | 03/04/2023 | 21/09/2023 | nan | nan | 0 | TK_NotStart | 1208363553 | 542 | 1208363553_542
MRPP2-SUP.10640 | TT_Task | DMU - PO Wheels | 16/11/2020 | 11/12/2020 | 16/11/2020 | 11/12/2020 | 0 | TK_Complete | 1208363553 | 543 | 1208363553_543
MRPP2-SUP.14780 | TT_Task | DMU - Production Wheels | 14/12/2020 | 28/06/2023 | 14/12/2020 | nan | 0 | TK_Active | 1208363553 | 543 | 1208363553_543
MRPP2-SUP.20190 | TT_Task | DMU - DEL Wheels delivery | 03/04/2023 | 21/09/2023 | nan | nan | 0 | TK_NotStart | 1208363553 | 543 | 1208363553_543
MRPP2-SUP.10630 | TT_Task | DMU - PO Axles | 16/11/2020 | 11/12/2020 | 16/11/2020 | 11/12/2020 | 0 | TK_Complete | 1208363553 | 543 | 1208363553_543
MRPP2-SUP.14770 | TT_Task | DMU - Production Axles | 14/12/2020 | 28/06/2023 | 14/12/2020 | nan | 0 | TK_Active | 1208363553 | 543 | 1208363553_543
MRPP2-SUP.20180 | TT_Task | DMU - DEL Axles delivery | 03/04/2023 | 21/09/2023 | nan | nan | 0 | TK_NotStart | 1208363553 | 543 | 1208363553_543
MRPP2-SUP.10760 | TT_Task | DMU - PO Brakes | 14/12/2020 | 13/01/2021 | 14/12/2020 | 13/01/2021 | 0 | TK_Complete | 1208363553 | 544 | 1208363553_544
MRPP2-SUP.14900 | TT_Task | DMU - Production Brakes | 14/01/2021 | 26/07/2023 | 14/01/2021 | nan | 0 | TK_Active | 1208363553 | 544 | 1208363553_544
MRPP2-SUP.20310 | TT_Task | DMU - DEL Brakes delivery | 03/04/2023 | 21/09/2023 | nan | nan | 0 | TK_NotStart | 1208363553 | 544 | 1208363553_544
MRPP2-SUP.10790 | TT_Task | DMU - PO Traction converter | 14/01/2021 | 11/02/2021 | 14/01/2021 | 11/02/2021 | 0 | TK_Complete | 1208363553 | 545 | 1208363553_545
MRPP2-SUP.14940 | TT_Task | DMU - Production Traction converter | 12/02/2021 | 28/06/2023 | 12/02/2021 | nan | 0 | TK_Active | 1208363553 | 545 | 1208363553_545
MRPP2-SUP.20410 | TT_Task | DMU - DEL Traction converter delivery | 06/03/2023 | 24/08/2023 | nan | nan | 0 | TK_NotStart | 1208363553 | 545 | 1208363553_545
MRPP2-SUP.10780 | TT_Task | DMU - PO Traction motor | 14/01/2021 | 11/02/2021 | 14/01/2021 | 11/02/2021 | 0 | TK_Complete | 1208363553 | 546 | 1208363553_546
MRPP2-SUP.14930 | TT_Task | DMU - Production Traction motor | 12/02/2021 | 28/06/2023 | 12/02/2021 | nan | 0 | TK_Active | 1208363553 | 546 | 1208363553_546
MRPP2-SUP.20390 | TT_Task | DMU - DEL Traction motor delivery | 06/03/2023 | 24/08/2023 | nan | nan | 0 | TK_NotStart | 1208363553 | 546 | 1208363553_546
MRPP2-SUP.10800 | TT_Task | DMU - PO Primary Suspension | 14/01/2021 | 11/02/2021 | 14/01/2021 | 11/02/2021 | 0 | TK_Complete | 1208363553 | 547 | 1208363553_547
MRPP2-SUP.14950 | TT_Task | DMU - Production Primary Suspension | 12/02/2021 | 12/07/2023 | 12/02/2021 | nan | 0 | TK_Active | 1208363553 | 547 | 1208363553_547
MRPP2-SUP.20520 | TT_Task | DMU - DEL Primary Suspension delivery | 19/04/2023 | 06/10/2023 | nan | nan | 0 | TK_NotStart | 1208363553 | 547 | 1208363553_547
MRPP2-SUP.10810 | TT_Task | DMU - PO Secondary Suspension | 14/01/2021 | 11/02/2021 | 14/01/2021 | 11/02/2021 | 0 | TK_Complete | 1208363553 | 547 | 1208363553_547
MRPP2-SUP.14960 | TT_Task | DMU - Production Secondary Suspension | 12/02/2021 | 12/07/2023 | 12/02/2021 | nan | 0 | TK_Active | 1208363553 | 547 | 1208363553_547
MRPP2-SUP.20530 | TT_Task | DMU - DEL Secondary Suspension delivery | 19/04/2023 | 06/10/2023 | nan | nan | 0 | TK_NotStart | 1208363553 | 547 | 1208363553_547
MRPP2-SUP.10890 | TT_Task | DMU - PO CVS | 12/02/2021 | 11/03/2021 | 12/02/2021 | 11/03/2021 | 0 | TK_Complete | 1208363553 | 548 | 1208363553_548
MRPP2-SUP.15020 | TT_Task | DMU - Production CVS | 12/03/2021 | 30/05/2023 | 12/03/2021 | nan | 0 | TK_Active | 1208363553 | 548 | 1208363553_548
MRPP2-SUP.20290 | TT_Task | DMU - DEL CVS delivery | 06/02/2023 | 27/07/2023 | nan | nan | 0 | TK_NotStart | 1208363553 | 548 | 1208363553_548
MRPP2-SUP.10860 | TT_Task | DMU - PO Coupler | 12/02/2021 | 11/03/2021 | 12/02/2021 | 11/03/2021 | 0 | TK_Complete | 1208363553 | 549 | 1208363553_549
MRPP2-SUP.14990 | TT_Task | DMU - Production Coupler | 12/03/2021 | 12/07/2023 | 12/03/2021 | nan | 0 | TK_Active | 1208363553 | 549 | 1208363553_549
MRPP2-SUP.20260 | TT_Task | DMU - DEL Coupler delivery | 19/04/2023 | 06/10/2023 | nan | nan | 0 | TK_NotStart | 1208363553 | 549 | 1208363553_549
MRPP2-SUP.10900 | TT_Task | DMU - PO (Purchase Order)-Gangway | 12/02/2021 | 11/03/2021 | 12/02/2021 | 11/03/2021 | 0 | TK_Complete | 1208363553 | 550 | 1208363553_550
MRPP2-SUP.15030 | TT_Task | DMU - Production ( Component process time)-Gangway | 12/03/2021 | 12/07/2023 | 12/03/2021 | nan | 0 | TK_Active | 1208363553 | 550 | 1208363553_550
MRPP2-SUP.20300 | TT_Task | DMU - DEL Component Delivery-Gangway | 19/04/2023 | 06/10/2023 | nan | nan | 0 | TK_NotStart | 1208363553 | 550 | 1208363553_550
MRPP2-SUP.10870 | TT_Task | DMU - PO Pipes | 12/02/2021 | 11/03/2021 | 12/02/2021 | 11/03/2021 | 0 | TK_Complete | 1208363553 | 551 | 1208363553_551
MRPP2-SUP.15000 | TT_Task | DMU - Production Pipes | 12/03/2021 | 12/07/2023 | 12/03/2021 | nan | 0 | TK_Active | 1208363553 | 551 | 1208363553_551
MRPP2-SUP.20270 | TT_Task | DMU - DEL Pipes delivery | 19/04/2023 | 06/10/2023 | nan | nan | 0 | TK_NotStart | 1208363553 | 551 | 1208363553_551
MRPP2-SUP.10880 | TT_Task | DMU - PO Cables | 12/02/2021 | 11/03/2021 | 12/02/2021 | 11/03/2021 | 0 | TK_Complete | 1208363553 | 552 | 1208363553_552
MRPP2-SUP.15010 | TT_Task | DMU - Production Cables | 12/03/2021 | 12/07/2023 | 12/03/2021 | nan | 0 | TK_Active | 1208363553 | 552 | 1208363553_552
MRPP2-SUP.20280 | TT_Task | DMU - DEL Cables delivery | 19/04/2023 | 06/10/2023 | nan | nan | 0 | TK_NotStart | 1208363553 | 552 | 1208363553_552
MRPP2-SUP.11000 | TT_Task | DMU - PO Cable trays | 12/03/2021 | 12/04/2021 | 12/03/2021 | 12/04/2021 | 0 | TK_Complete | 1208363553 | 553 | 1208363553_553
MRPP2-SUP.15130 | TT_Task | DMU - Production Cable trays | 13/04/2021 | 30/05/2023 | 13/04/2021 | nan | 0 | TK_Active | 1208363553 | 553 | 1208363553_553
MRPP2-SUP.20470 | TT_Task | DMU - DEL Cable trays delivery | 06/03/2023 | 24/08/2023 | nan | nan | 0 | TK_NotStart | 1208363553 | 553 | 1208363553_553
MRPP2-SUP.11020 | TT_Task | DMU - PO Floor covering | 12/03/2021 | 12/04/2021 | 12/03/2021 | 12/04/2021 | 0 | TK_Complete | 1208363553 | 554 | 1208363553_554
MRPP2-SUP.15150 | TT_Task | DMU - Production Floor covering | 13/04/2021 | 30/05/2023 | 13/04/2021 | nan | 0 | TK_Active | 1208363553 | 554 | 1208363553_554
MRPP2-SUP.20490 | TT_Task | DMU - DEL Floor covering delivery | 06/03/2023 | 24/08/2023 | nan | nan | 0 | TK_NotStart | 1208363553 | 554 | 1208363553_554
MRPP2-SUP.10910 | TT_Task | DMU - PO Wind screen | 12/03/2021 | 12/04/2021 | 12/03/2021 | 12/04/2021 | 0 | TK_Complete | 1208363553 | 555 | 1208363553_555
MRPP2-SUP.15040 | TT_Task | DMU - Production Wind screen | 13/04/2021 | 30/05/2023 | 13/04/2021 | nan | 0 | TK_Active | 1208363553 | 555 | 1208363553_555
MRPP2-SUP.20360 | TT_Task | DMU - DEL Wind screen delivery | 06/03/2023 | 24/08/2023 | nan | nan | 0 | TK_NotStart | 1208363553 | 555 | 1208363553_555
MRPP2-SUP.10970 | TT_Task | DMU - PO Front mask | 12/03/2021 | 12/04/2021 | 12/03/2021 | 12/04/2021 | 0 | TK_Complete | 1208363553 | 556 | 1208363553_556
MRPP2-SUP.15100 | TT_Task | DMU - Production Front mask | 13/04/2021 | 30/05/2023 | 13/04/2021 | nan | 0 | TK_Active | 1208363553 | 556 | 1208363553_556
MRPP2-SUP.20440 | TT_Task | DMU - DEL Front mask delivery | 06/03/2023 | 24/08/2023 | nan | nan | 0 | TK_NotStart | 1208363553 | 556 | 1208363553_556
MRPP2-SUP.10980 | TT_Task | DMU - PO Relays | 12/03/2021 | 12/04/2021 | 12/03/2021 | 12/04/2021 | 0 | TK_Complete | 1208363553 | 557 | 1208363553_557
MRPP2-SUP.15110 | TT_Task | DMU - Production Relays | 13/04/2021 | 30/05/2023 | 13/04/2021 | nan | 0 | TK_Active | 1208363553 | 557 | 1208363553_557
MRPP2-SUP.20450 | TT_Task | DMU - DEL Relays delivery | 06/03/2023 | 24/08/2023 | nan | nan | 0 | TK_NotStart | 1208363553 | 557 | 1208363553_557
MRPP2-SUP.11060 | TT_Task | DMU - PO Cabinets | 12/03/2021 | 12/04/2021 | 12/03/2021 | 12/04/2021 | 0 | TK_Complete | 1208363553 | 558 | 1208363553_558
MRPP2-SUP.15190 | TT_Task | DMU - Production Cabinets | 13/04/2021 | 30/05/2023 | 13/04/2021 | nan | 0 | TK_Active | 1208363553 | 558 | 1208363553_558
MRPP2-SUP.20550 | TT_Task | DMU - DEL Cabinets delivery | 06/03/2023 | 24/08/2023 | nan | nan | 0 | TK_NotStart | 1208363553 | 558 | 1208363553_558
MRPP2-SUP.10930 | TT_Task | DMU - PO Elec comp | 12/03/2021 | 12/04/2021 | 12/03/2021 | 12/04/2021 | 0 | TK_Complete | 1208363553 | 559 | 1208363553_559
MRPP2-SUP.15060 | TT_Task | DMU - Production Elec comp | 13/04/2021 | 30/05/2023 | 13/04/2021 | nan | 0 | TK_Active | 1208363553 | 559 | 1208363553_559
MRPP2-SUP.20380 | TT_Task | DMU - DEL Elec comp delivery | 06/03/2023 | 24/08/2023 | nan | nan | 0 | TK_NotStart | 1208363553 | 559 | 1208363553_559
MRPP2-SUP.11080 | TT_Task | DMU - PO LV box | 12/03/2021 | 12/04/2021 | 12/03/2021 | 12/04/2021 | 0 | TK_Complete | 1208363553 | 560 | 1208363553_560
MRPP2-SUP.15210 | TT_Task | DMU - Production LV box | 13/04/2021 | 30/05/2023 | 13/04/2021 | nan | 0 | TK_Active | 1208363553 | 560 | 1208363553_560
MRPP2-SUP.20570 | TT_Task | DMU - DEL LV box delivery | 06/03/2023 | 24/08/2023 | nan | nan | 0 | TK_NotStart | 1208363553 | 560 | 1208363553_560
MRPP2-SUP.11090 | TT_Task | DMU - PO Battery ; battery box | 12/03/2021 | 12/04/2021 | 12/03/2021 | 12/04/2021 | 0 | TK_Complete | 1208363553 | 561 | 1208363553_561
MRPP2-SUP.15220 | TT_Task | DMU - Production Battery ; battery box | 13/04/2021 | 30/05/2023 | 13/04/2021 | nan | 0 | TK_Active | 1208363553 | 561 | 1208363553_561
MRPP2-SUP.20580 | TT_Task | DMU - DEL Battery ; battery box delivery | 06/03/2023 | 24/08/2023 | nan | nan | 0 | TK_NotStart | 1208363553 | 561 | 1208363553_561
MRPP2-SUP.10960 | TT_Task | DMU - PO Crash box | 12/03/2021 | 12/04/2021 | 12/03/2021 | 12/04/2021 | 0 | TK_Complete | 1208363553 | 562 | 1208363553_562
MRPP2-SUP.15090 | TT_Task | DMU - Production Crash box | 13/04/2021 | 30/05/2023 | 13/04/2021 | nan | 0 | TK_Active | 1208363553 | 562 | 1208363553_562
MRPP2-SUP.20430 | TT_Task | DMU - DEL Crash box delivery | 06/03/2023 | 24/08/2023 | nan | nan | 0 | TK_NotStart | 1208363553 | 562 | 1208363553_562
MRPP2-SUP.11050 | TT_Task | DMU - PO Interior and lighting | 12/03/2021 | 12/04/2021 | 12/03/2021 | 12/04/2021 | 0 | TK_Complete | 1208363553 | 563 | 1208363553_563
MRPP2-SUP.15180 | TT_Task | DMU - Production Interior and lighting | 13/04/2021 | 28/06/2023 | 13/04/2021 | nan | 0 | TK_Active | 1208363553 | 563 | 1208363553_563
MRPP2-SUP.20540 | TT_Task | DMU - DEL Interior and lighting delivery | 06/03/2023 | 24/08/2023 | nan | nan | 0 | TK_NotStart | 1208363553 | 563 | 1208363553_563
MRPP2-SUP.10950 | TT_Task | DMU - PO Hand rails | 12/03/2021 | 12/04/2021 | 12/03/2021 | 12/04/2021 | 0 | TK_Complete | 1208363553 | 564 | 1208363553_564
MRPP2-SUP.15080 | TT_Task | DMU - Production Hand rails | 13/04/2021 | 30/05/2023 | 13/04/2021 | nan | 0 | TK_Active | 1208363553 | 564 | 1208363553_564
MRPP2-SUP.20420 | TT_Task | DMU - DEL Hand rails delivery | 06/03/2023 | 24/08/2023 | nan | nan | 0 | TK_NotStart | 1208363553 | 564 | 1208363553_564
MRPP2-SUP.10940 | TT_Task | DMU - PO Grabpoles and grab handles | 12/03/2021 | 12/04/2021 | 12/03/2021 | 12/04/2021 | 0 | TK_Complete | 1208363553 | 565 | 1208363553_565
MRPP2-SUP.15070 | TT_Task | DMU - Production Grabpoles and grab handles | 13/04/2021 | 30/05/2023 | 13/04/2021 | nan | 0 | TK_Active | 1208363553 | 565 | 1208363553_565
MRPP2-SUP.20400 | TT_Task | DMU - DEL Grabpoles and grab handles delivery | 06/03/2023 | 24/08/2023 | nan | nan | 0 | TK_NotStart | 1208363553 | 565 | 1208363553_565
MRPP2-SUP.11070 | TT_Task | DMU - PO Cab garnishing | 12/03/2021 | 12/04/2021 | 12/03/2021 | 12/04/2021 | 0 | TK_Complete | 1208363553 | 566 | 1208363553_566
MRPP2-SUP.15200 | TT_Task | DMU - Production Cab garnishing | 13/04/2021 | 30/05/2023 | 13/04/2021 | nan | 0 | TK_Active | 1208363553 | 566 | 1208363553_566
MRPP2-SUP.20560 | TT_Task | DMU - DEL Cab garnishing delivery | 06/03/2023 | 24/08/2023 | nan | nan | 0 | TK_NotStart | 1208363553 | 566 | 1208363553_566
MRPP2-SUP.11040 | TT_Task | DMU - PO Seats | 12/03/2021 | 12/04/2021 | 12/03/2021 | 12/04/2021 | 0 | TK_Complete | 1208363553 | 567 | 1208363553_567
MRPP2-SUP.15170 | TT_Task | DMU - Production Seats | 13/04/2021 | 30/05/2023 | 13/04/2021 | nan | 0 | TK_Active | 1208363553 | 567 | 1208363553_567
MRPP2-SUP.20510 | TT_Task | DMU - DEL Seats delivery | 06/03/2023 | 24/08/2023 | nan | nan | 0 | TK_NotStart | 1208363553 | 567 | 1208363553_567
MRPP2-SUP.11010 | TT_Task | DMU - PO PACIS | 12/03/2021 | 12/04/2021 | 12/03/2021 | 12/04/2021 | 0 | TK_Complete | 1208363553 | 568 | 1208363553_568
MRPP2-SUP.15140 | TT_Task | DMU - Production PACIS | 13/04/2021 | 28/06/2023 | 13/04/2021 | nan | 0 | TK_Active | 1208363553 | 568 | 1208363553_568
MRPP2-SUP.20480 | TT_Task | DMU - DEL PACIS delivery | 06/03/2023 | 24/08/2023 | nan | nan | 0 | TK_NotStart | 1208363553 | 568 | 1208363553_568
MRPP2-SUP.10920 | TT_Task | DMU - PO MCP | 12/03/2021 | 12/04/2021 | 12/03/2021 | 12/04/2021 | 0 | TK_Complete | 1208363553 | 569 | 1208363553_569
MRPP2-SUP.15050 | TT_Task | DMU - Production MCP | 13/04/2021 | 30/05/2023 | 13/04/2021 | nan | 0 | TK_Active | 1208363553 | 569 | 1208363553_569
MRPP2-SUP.20370 | TT_Task | DMU - DEL MCP delivery | 06/03/2023 | 24/08/2023 | nan | nan | 0 | TK_NotStart | 1208363553 | 569 | 1208363553_569
MRPP2-SUP.11030 | TT_Task | DMU - PO TCMS equipment | 12/03/2021 | 12/04/2021 | 12/03/2021 | 12/04/2021 | 0 | TK_Complete | 1208363553 | 479 | 1208363553_479
MRPP2-SUP.15160 | TT_Task | DMU - Production TCMS equipment | 13/04/2021 | 28/06/2023 | 13/04/2021 | nan | 0 | TK_Active | 1208363553 | 479 | 1208363553_479
MRPP2-SUP.20500 | TT_Task | DMU - DEL TCMS equipment delivery | 06/03/2023 | 24/08/2023 | nan | nan | 0 | TK_NotStart | 1208363553 | 479 | 1208363553_479
MRPP2-SUP.10620 | TT_Task | DMU - PO HVAC | 16/11/2020 | 11/12/2020 | 16/11/2020 | 11/12/2020 | 0 | TK_Complete | 1208363553 | 570 | 1208363553_570
MRPP2-SUP.14760 | TT_Task | DMU - Production HVAC | 14/12/2020 | 28/06/2023 | 14/12/2020 | nan | 0 | TK_Active | 1208363553 | 570 | 1208363553_570
MRPP2-SUP.20070 | TT_Task | DMU - DEL HVAC delivery | 03/04/2023 | 21/09/2023 | nan | nan | 0 | TK_NotStart | 1208363553 | 570 | 1208363553_570
MRPP2-SUP.10750 | TT_Task | DMU - PO Windows | 14/12/2020 | 13/01/2021 | 14/12/2020 | 13/01/2021 | 0 | TK_Complete | 1208363553 | 571 | 1208363553_571
MRPP2-SUP.14890 | TT_Task | DMU - Production Windows | 14/01/2021 | 26/07/2023 | 14/01/2021 | nan | 0 | TK_Active | 1208363553 | 571 | 1208363553_571
MRPP2-SUP.20250 | TT_Task | DMU - DEL Windows delivery | 04/05/2023 | 20/10/2023 | nan | nan | 0 | TK_NotStart | 1208363553 | 571 | 1208363553_571
MRPP2-SUP.10770 | TT_Task | DMU - PO Passenger doors | 14/01/2021 | 11/02/2021 | 14/01/2021 | 11/02/2021 | 0 | TK_Complete | 1208363553 | 572 | 1208363553_572
MRPP2-SUP.14920 | TT_Task | DMU - Production Passenger doors | 12/02/2021 | 05/10/2023 | 12/02/2021 | nan | 0 | TK_Active | 1208363553 | 572 | 1208363553_572
MRPP2-SUP.20350 | TT_Task | DMU - DEL Passenger doors delivery | 20/03/2023 | 07/09/2023 | nan | nan | 0 | TK_NotStart | 1208363553 | 572 | 1208363553_572
MRPP2-DAT.10008 | TT_Task | DMU - Train 01 - CBS Transport from Sri City Fty to Bellevue Depot | 13/12/2022 | 24/02/2023 | nan | nan | 0 | TK_NotStart | 1208363553 | 436 | 1208363553_436
MRPP2-DAT.10028 | TT_Task | DMU - Train 02 - CBS Transport from Sri City Fty to Bellevue Depot | 27/02/2023 | 04/05/2023 | nan | nan | 688 | TK_NotStart | 1208363553 | 436 | 1208363553_436
MRPP2-DPA.10000 | TT_Task | DMU - Train 01 Preliminary Acceptance | 16/10/2023 | 01/12/2023 | nan | nan | 0 | TK_NotStart | 1208363553 | 573 | 1208363553_573
MRPP2-DPA.10010 | TT_Task | DMU - Train 02 Preliminary Acceptance | 20/12/2023 | 05/02/2024 | nan | nan | 0 | TK_NotStart | 1208363553 | 573 | 1208363553_573
MRPP2-DQA.10000 | TT_Task | DMU - Train 01 Provisional Acceptance Tests | 11/04/2024 | 01/05/2024 | nan | nan | 0 | TK_NotStart | 1208363553 | 573 | 1208363553_573
MRPP2-DQA.10020 | TT_Task | DMU - Train 01 Dynamic Validation | 04/12/2023 | 20/02/2024 | nan | nan | 0 | TK_NotStart | 1208363553 | 574 | 1208363553_574
MRPP2-DQA.10030 | TT_Task | DMU - Train 01 Retrofit | 21/02/2024 | 27/03/2024 | nan | nan | 0 | TK_NotStart | 1208363553 | 457 | 1208363553_457
MRPP2-DQA.10040 | TT_Task | DMU - Train 01 Service Trials | 28/03/2024 | 10/04/2024 | nan | nan | 0 | TK_NotStart | 1208363553 | 575 | 1208363553_575
MRPP2-DQA.10010 | TT_Task | DMU - Train 02 Provisional Acceptance Tests | 31/05/2024 | 12/06/2024 | nan | nan | 0 | TK_NotStart | 1208363553 | 573 | 1208363553_573
MRPP2-DQA.10050 | TT_Task | DMU - Train 02 Retrofit | 17/04/2024 | 16/05/2024 | nan | nan | 0 | TK_NotStart | 1208363553 | 457 | 1208363553_457
MRPP2-DQA.10060 | TT_Task | DMU - Train 02 Service Trials | 17/05/2024 | 30/05/2024 | nan | nan | 0 | TK_NotStart | 1208363553 | 575 | 1208363553_575
MRPP2-DQA.10070 | TT_Task | DMU - Train 02 Dynamic Validation | 06/02/2024 | 16/04/2024 | nan | nan | 0 | TK_NotStart | 1208363553 | 574 | 1208363553_574
MRPP2-DFA.10000 | TT_Task | DMU - Train 01 Final Acceptance Tests | 23/08/2024 | 18/10/2024 | nan | nan | 0 | TK_NotStart | 1208363553 | 573 | 1208363553_573
MRPP2-DFA.10010 | TT_Task | DMU - Train 02 Final Acceptance Tests | 24/10/2024 | 18/12/2024 | nan | nan | 0 | TK_NotStart | 1208363553 | 573 | 1208363553_573
MRPP2-DWA.10000 | TT_Task | DMU - Warranty/DLP Period DMU Trainsets | 02/05/2024 | 30/04/2026 | nan | nan | 0 | TK_NotStart | 1208363553 | 576 | 1208363553_576
MRPP2-EMS.11270 | TT_Task | Initial Term 20 years + Two [5-year] extensions = 30 Years (In Total) | 28/08/2023 | 22/08/2053 | nan | nan | 0 | TK_NotStart | 1208363553 | 577 | 1208363553_577
MRPP2-EMS.11000 | TT_Task | Test of incidents and accidents response procedures | 01/02/2023 | 01/05/2023 | nan | nan | 62760 | TK_NotStart | 1208363553 | 578 | 1208363553_578
MRPP2-EMS.11210 | TT_Task | Participation to the T ; C Phase (Prelim to Final Acceptance ~ 41 EMUs) | 01/07/2022 | 07/09/2029 | nan | nan | 784 | TK_NotStart | 1208363553 | 579 | 1208363553_579
MRPP2-EMS.10040 | TT_Task | Mapping of staff competencies and requirements | 27/11/2019 | 28/05/2021 | 27/11/2019 | 28/05/2021 | 0 | TK_Complete | 1208363553 | 580 | 1208363553_580
MRPP2-EMS.10110 | TT_Task | Develop employee EBA | 28/11/2019 | 09/06/2020 | 28/11/2019 | 09/06/2020 | 0 | TK_Complete | 1208363553 | 581 | 1208363553_581
MRPP2-EMS.10270 | TT_Task | Recruitment of blue collar staff | 27/09/2022 | 03/04/2023 | nan | nan | 0 | TK_NotStart | 1208363553 | 582 | 1208363553_582
MRPP2-EMS.10600 | TT_Task | Selection of sub-contracted services amd temporary employees | 27/09/2022 | 03/04/2023 | nan | nan | 62896 | TK_NotStart | 1208363553 | 583 | 1208363553_583
MRPP2-EMS.10000 | TT_Task | Regulatory standards and compliance assessed | 19/11/2019 | 24/02/2020 | 19/11/2019 | 24/02/2020 | 0 | TK_Complete | 1208363553 | 584 | 1208363553_584
MRPP2-EMS.10090 | TT_Task | Initial REACH Statement | 18/12/2019 | 10/02/2020 | 18/12/2019 | 10/02/2020 | 0 | TK_Complete | 1208363553 | 585 | 1208363553_585
MRPP2-EMS.10100 | TT_Task | Extraction from CLAMP showing the candidate substances | 18/12/2019 | 10/02/2020 | 18/12/2019 | 10/02/2020 | 0 | TK_Complete | 1208363553 | 586 | 1208363553_586
MRPP2-EMS.10120 | TT_Task | EHS Risk Analysis | 24/01/2020 | 12/01/2021 | 24/01/2020 | 12/01/2021 | 0 | TK_Complete | 1208363553 | 587 | 1208363553_587
MRPP2-EMS.10140 | TT_Task | Alstom Health and Safety road map analysis and deployment | 11/02/2020 | 18/06/2020 | 11/02/2020 | 18/06/2020 | 0 | TK_Complete | 1208363553 | 588 | 1208363553_588
MRPP2-EMS.10200 | TT_Task | Health ; Safety Plan updated | 19/06/2020 | 22/07/2020 | 19/06/2020 | 22/07/2020 | 0 | TK_Complete | 1208363553 | 589 | 1208363553_589
MRPP2-EMS.10220 | TT_Task | Production of EHS Plan: KPI defined, tools and deviations collection method defined | 23/07/2020 | 15/10/2020 | 23/07/2020 | 15/10/2020 | 0 | TK_Complete | 1208363553 | 587 | 1208363553_587
MRPP2-EMS.10060 | TT_Task | Review and confirm the contractual scope of work : Contract Compliance Matrix | 28/11/2019 | 27/01/2020 | 28/11/2019 | 27/01/2020 | 0 | TK_Complete | 1208363553 | 590 | 1208363553_590
MRPP2-EMS.10070 | TT_Task | Set-up the necessary insurance policies | 28/11/2019 | 27/01/2020 | 28/11/2019 | 27/01/2020 | 0 | TK_Complete | 1208363553 | 591 | 1208363553_591
MRPP2-EMS.10130 | TT_Task | Review the contract to record all requiremnts for mobilisation | 28/01/2020 | 24/02/2020 | 28/01/2020 | 24/02/2020 | 0 | TK_Complete | 1208363553 | 592 | 1208363553_592
MRPP2-EMS.10020 | TT_Task | Set up agreement with all internal Alstom industrial participating units including; scopes of responsibility and supply | 28/11/2019 | 08/06/2020 | 28/11/2019 | 08/06/2020 | 0 | TK_Complete | 1208363553 | 593 | 1208363553_593
MRPP2-EMS.10260 | TT_Task | Develop Interface protocol with PTA ; B Maintainer | 09/07/2021 | 01/10/2021 | 09/07/2021 | 01/10/2021 | 0 | TK_Complete | 1208363553 | 201 | 1208363553_201
MRPP2-EMS.10280 | TT_Task | Produce documentation or needed contracts to maintain infrastructue/depot facilities | 04/03/2022 | 09/12/2022 | 24/02/2022 | nan | 0 | TK_Active | 1208363553 | 594 | 1208363553_594
MRPP2-EMS.10510 | TT_Task | Set up existing repair and overhaul processes | 25/07/2022 | 21/03/2023 | nan | nan | 0 | TK_NotStart | 1208363553 | 595 | 1208363553_595
MRPP2-EMS.10520 | TT_Task | Produce service level agreements | 29/04/2022 | 21/03/2023 | nan | nan | 0 | TK_NotStart | 1208363553 | 593 | 1208363553_593
MRPP2-EMS.10780 | TT_Task | Produce disaster recovery plan | 22/05/2023 | 03/07/2023 | nan | nan | 62408 | TK_NotStart | 1208363553 | 596 | 1208363553_596
MRPP2-EMS.10820 | TT_Task | Set-up the internal communication area (War Room) | 11/08/2022 | 21/03/2023 | nan | nan | 62968 | TK_NotStart | 1208363553 | 597 | 1208363553_597
MRPP2-EMS.10990 | TT_Task | Ensure facilities are adequate to be used with no outstanding issues | 05/05/2022 | 01/06/2022 | nan | nan | 64592 | TK_NotStart | 1208363553 | 598 | 1208363553_598
MRPP2-EMS.10560 | TT_Task | SQA/SQD framework in place | 21/12/2022 | 20/02/2023 | nan | nan | 336 | TK_NotStart | 1208363553 | 599 | 1208363553_599
MRPP2-EMS.10740 | TT_Task | QRQC Deployment | 23/03/2023 | 20/06/2023 | nan | nan | 0 | TK_NotStart | 1208363553 | 600 | 1208363553_600
MRPP2-EMS.11250 | TT_Task | Special processes requirements identified and implemented | 18/04/2023 | 20/06/2023 | nan | nan | 62480 | TK_NotStart | 1208363553 | 601 | 1208363553_601
MRPP2-EMS.10050 | TT_Task | Set-up the necessary security documents (Performance Bond, Guarantee?) | 28/11/2019 | 24/12/2019 | 28/11/2019 | 24/12/2019 | 0 | TK_Complete | 1208363553 | 602 | 1208363553_602
MRPP2-EMS.10080 | TT_Task | Review depot layout in accordance with latest APSYS roadmap | 28/11/2019 | 08/06/2020 | 28/11/2019 | 08/06/2020 | 0 | TK_Complete | 1208363553 | 603 | 1208363553_603
MRPP2-EMS.10190 | TT_Task | Door to floor value stream mapping | 09/06/2020 | 22/02/2021 | 09/06/2020 | 22/02/2021 | 0 | TK_Complete | 1208363553 | 604 | 1208363553_604
MRPP2-EMS.10590 | TT_Task | Training and coaching | 23/12/2022 | 20/06/2023 | nan | nan | 62480 | TK_NotStart | 1208363553 | 605 | 1208363553_605
MRPP2-EMS.10710 | TT_Task | Source, procure, install, commission depot equipment | 06/01/2023 | 03/07/2023 | nan | nan | 62408 | TK_NotStart | 1208363553 | 606 | 1208363553_606
MRPP2-EMS.10720 | TT_Task | Visual Management cells in place | 28/03/2023 | 04/08/2023 | nan | nan | 62216 | TK_NotStart | 1208363553 | 607 | 1208363553_607
MRPP2-EMS.11020 | TT_Task | Method times defined for each maintenance exam | 16/03/2023 | 20/06/2023 | nan | nan | 0 | TK_NotStart | 1208363553 | 608 | 1208363553_608
MRPP2-EMS.11030 | TT_Task | Short term interval monitoring in place | 16/03/2023 | 20/06/2023 | nan | nan | 0 | TK_NotStart | 1208363553 | 609 | 1208363553_609
MRPP2-EMS.11040 | TT_Task | Task sequencing plan in place | 16/03/2023 | 20/06/2023 | nan | nan | 0 | TK_NotStart | 1208363553 | 610 | 1208363553_610
MRPP2-EMS.11050 | TT_Task | Task sequencing routine maintenance inspections completed | 16/03/2023 | 20/06/2023 | nan | nan | 0 | TK_NotStart | 1208363553 | 610 | 1208363553_610
MRPP2-EMS.10150 | TT_Task | CPR (Critical Project Review) Cycle Stats | 09/03/2020 | 15/04/2020 | 09/03/2020 | 15/04/2020 | 0 | TK_Complete | 1208363553 | 611 | 1208363553_611
MRPP2-EMS.10160 | TT_Task | Finance Set-up the necessary hedging arrangements &lt;WBS Summary Bar&gt; | 09/03/2020 | 26/09/2023 | 09/03/2020 | nan | 0 | TK_Active | 1208363553 | 612 | 1208363553_612
MRPP2-EMS.10170 | TT_Task | Opportunity register upate | 09/04/2020 | 13/05/2020 | 09/04/2020 | 13/05/2020 | 0 | TK_Complete | 1208363553 | 613 | 1208363553_613
MRPP2-EMS.10410 | TT_Task | Work Package Set-up / Optimization | 04/03/2021 | 18/05/2021 | 04/03/2021 | 18/05/2021 | 0 | TK_Complete | 1208363553 | 614 | 1208363553_614
MRPP2-EMS.10610 | TT_Task | Project Management Plan updates | 18/04/2023 | 20/06/2023 | nan | nan | 0 | TK_NotStart | 1208363553 | 615 | 1208363553_615
MRPP2-EMS.11230 | TT_Task | Close out issues from previous gate review (MGR) | 07/04/2022 | 14/07/2022 | nan | nan | 64352 | TK_NotStart | 1208363553 | 616 | 1208363553_616
MRPP2-EMS.11240 | TT_Task | PMP validation by management and implementation | 10/02/2023 | 20/06/2023 | nan | nan | 0 | TK_NotStart | 1208363553 | 617 | 1208363553_617
MRPP2-EMS.10210 | TT_Task | Training schedule | 29/05/2020 | 21/08/2020 | 29/05/2020 | 21/08/2020 | 0 | TK_Complete | 1208363553 | 618 | 1208363553_618
MRPP2-EMS.10230 | TT_Task | Inductions | 24/08/2022 | 24/07/2023 | nan | nan | 0 | TK_NotStart | 1208363553 | 619 | 1208363553_619
MRPP2-EMS.10770 | TT_Task | Training by the OEM (O ; M Manuals) | 01/05/2023 | 24/07/2023 | nan | nan | 0 | TK_NotStart | 1208363553 | 620 | 1208363553_620
MRPP2-EMS.10980 | TT_Task | Training by Alstom SME | 15/03/2023 | 24/07/2023 | nan | nan | 62288 | TK_NotStart | 1208363553 | 621 | 1208363553_621
MRPP2-EMS.10180 | TT_Task | Set up GSI ready to place the orders | 12/05/2020 | 13/11/2020 | 12/05/2020 | 13/11/2020 | 0 | TK_Complete | 1208363553 | 622 | 1208363553_622
MRPP2-EMS.10250 | TT_Task | Codification process of all parts used on project | 07/09/2020 | 12/03/2021 | 07/09/2020 | 12/03/2021 | 0 | TK_Complete | 1208363553 | 623 | 1208363553_623
MRPP2-EMS.10310 | TT_Task | Identify and set-up contracts with the necessary Subcontractors (including SLA for critical Equipments) | 14/10/2021 | 06/02/2023 | 14/10/2021 | nan | 0 | TK_Active | 1208363553 | 624 | 1208363553_624
MRPP2-EMS.10320 | TT_Task | Place orders for long and medium lead time items | 30/09/2021 | 14/11/2022 | 30/09/2021 | nan | 63664 | TK_Active | 1208363553 | 625 | 1208363553_625
MRPP2-EMS.10360 | TT_Task | Delivery and control of intial spares are defined ; set up material shortage list | 10/02/2021 | 12/03/2021 | 10/02/2021 | 12/03/2021 | 0 | TK_Complete | 1208363553 | 626 | 1208363553_626
MRPP2-EMS.10380 | TT_Task | Set up warehouse and all facilitie to manage all part types including special storage conditions | 08/06/2022 | 03/07/2023 | nan | nan | 0 | TK_NotStart | 1208363553 | 627 | 1208363553_627
MRPP2-EMS.10400 | TT_Task | Frame agreements contracted with critical suppliers, including obsolescence monitoring | 25/11/2021 | 06/02/2023 | 25/11/2021 | nan | 63216 | TK_Active | 1208363553 | 628 | 1208363553_628
MRPP2-EMS.10420 | TT_Task | Out-source orders in place for equipment of services | 14/10/2021 | 06/02/2023 | 14/10/2021 | nan | 63216 | TK_Active | 1208363553 | 629 | 1208363553_629
MRPP2-EMS.10470 | TT_Task | Identify and set-up contracts with the Material suppliers | 21/07/2021 | 06/02/2023 | 21/07/2021 | nan | 63216 | TK_Active | 1208363553 | 624 | 1208363553_624
MRPP2-EMS.10480 | TT_Task | Organise the Warehouse | 15/02/2023 | 03/07/2023 | nan | nan | 62408 | TK_NotStart | 1208363553 | 627 | 1208363553_627
MRPP2-EMS.10490 | TT_Task | Complete Hand-Over of special / specific tools | 13/07/2022 | 12/06/2023 | nan | nan | 0 | TK_NotStart | 1208363553 | 630 | 1208363553_630
MRPP2-EMS.10630 | TT_Task | Define documentation and IS requirements | 13/05/2020 | 13/05/2021 | 13/05/2020 | 13/05/2021 | 0 | TK_Complete | 1208363553 | 631 | 1208363553_631
MRPP2-EMS.10645 | TT_Task | Finalise work package manager, task, scope and repsonsibilities | 14/04/2023 | 12/06/2023 | nan | nan | 62528 | TK_NotStart | 1208363553 | 614 | 1208363553_614
MRPP2-EMS.10680 | TT_Task | Incoming inspection regime in place | 12/10/2022 | 06/02/2023 | nan | nan | 63216 | TK_NotStart | 1208363553 | 632 | 1208363553_632
MRPP2-EMS.10690 | TT_Task | MRP in place | 08/05/2023 | 03/07/2023 | nan | nan | 0 | TK_NotStart | 1208363553 | 633 | 1208363553_633
MRPP2-EMS.10840 | TT_Task | Define maintenance/ repair strategy for sub-system | 04/04/2022 | 05/01/2023 | 04/03/2022 | nan | 63552 | TK_Active | 1208363553 | 595 | 1208363553_595
MRPP2-EMS.10850 | TT_Task | Set up sourcing activities for the project | 12/05/2020 | 12/05/2021 | 12/05/2020 | 12/05/2021 | 0 | TK_Complete | 1208363553 | 634 | 1208363553_634
MRPP2-EMS.10240 | TT_Task | Business Requirements outlined, discussed ; delivered | 07/09/2020 | 12/03/2021 | 07/09/2020 | 12/03/2021 | 0 | TK_Complete | 1208363553 | 635 | 1208363553_635
MRPP2-EMS.10290 | TT_Task | Implement MMIS | 06/10/2021 | 17/06/2022 | 06/10/2021 | nan | 64504 | TK_Active | 1208363553 | 636 | 1208363553_636
MRPP2-EMS.10570 | TT_Task | Physical implementation of offices / Network | 04/03/2022 | 03/05/2022 | 03/03/2022 | nan | 2008 | TK_Active | 1208363553 | 637 | 1208363553_637
MRPP2-EMS.10760 | TT_Task | Set-up the Maintenance project KPIs (contractual, per domain) | 23/01/2023 | 01/05/2023 | nan | nan | 0 | TK_NotStart | 1208363553 | 638 | 1208363553_638
MRPP2-EMS.10800 | TT_Task | PBS and Asset codification definition | 28/03/2023 | 01/05/2023 | nan | nan | 62760 | TK_NotStart | 1208363553 | 639 | 1208363553_639
MRPP2-EMS.10890 | TT_Task | master data loaded Go Live MMS | 01/05/2023 | 01/06/2023 | nan | nan | 62576 | TK_NotStart | 1208363553 | 640 | 1208363553_640
MRPP2-EMS.10900 | TT_Task | Implement the Maintenance Plan into MMS | 24/03/2023 | 01/05/2023 | nan | nan | 0 | TK_NotStart | 1208363553 | 638 | 1208363553_638
MRPP2-EMS.10910 | TT_Task | Store Management live in the MMS | 24/03/2023 | 01/05/2023 | nan | nan | 62760 | TK_NotStart | 1208363553 | 641 | 1208363553_641
MRPP2-EMS.10940 | TT_Task | MMS Training | 27/03/2023 | 01/06/2023 | nan | nan | 0 | TK_NotStart | 1208363553 | 621 | 1208363553_621
MRPP2-EMS.10950 | TT_Task | Create the performance Report System | 27/03/2023 | 01/05/2023 | nan | nan | 0 | TK_NotStart | 1208363553 | 642 | 1208363553_642
MRPP2-EMS.11010 | TT_Task | Reliability and contractual reports in place | 01/05/2023 | 01/06/2023 | nan | nan | 0 | TK_NotStart | 1208363553 | 643 | 1208363553_643
MRPP2-EMS.10300 | TT_Task | Organise the maintenance site base (including IT / Tel) | 11/10/2022 | 05/01/2023 | nan | nan | 63384 | TK_NotStart | 1208363553 | 644 | 1208363553_644
MRPP2-EMS.10390 | TT_Task | Produce and validate Method Statements | 17/01/2023 | 24/07/2023 | nan | nan | 62288 | TK_NotStart | 1208363553 | 645 | 1208363553_645
MRPP2-EMS.10395 | TT_Task | Receive full set of Maintenance documentation drafts | 10/02/2021 | 12/03/2021 | 10/02/2021 | 12/03/2021 | 0 | TK_Complete | 1208363553 | 646 | 1208363553_646
MRPP2-EMS.10430 | TT_Task | Safety critical parts recorded in CLAMP; Safety critical operations are identified | 02/02/2023 | 01/05/2023 | nan | nan | 62760 | TK_NotStart | 1208363553 | 647 | 1208363553_647
MRPP2-EMS.10440 | TT_Task | Define serialised and traceable items | 02/02/2023 | 01/05/2023 | nan | nan | 62760 | TK_NotStart | 1208363553 | 648 | 1208363553_648
MRPP2-EMS.10450 | TT_Task | Transfer of LCC to project controller to prepare project forecast | 14/04/2021 | 26/05/2021 | 14/04/2021 | 26/05/2021 | 0 | TK_Complete | 1208363553 | 649 | 1208363553_649
MRPP2-EMS.10530 | TT_Task | Production of workshop instructions/maintenance plan | 29/11/2021 | 05/01/2023 | 29/11/2021 | nan | 63384 | TK_Active | 1208363553 | 594 | 1208363553_594
MRPP2-EMS.10540 | TT_Task | Production of tools list | 25/08/2022 | 01/03/2023 | nan | nan | 63080 | TK_NotStart | 1208363553 | 630 | 1208363553_630
MRPP2-EMS.10550 | TT_Task | Production of LCC ; Spare parts list | 25/08/2022 | 01/03/2023 | nan | nan | 63080 | TK_NotStart | 1208363553 | 650 | 1208363553_650
MRPP2-EMS.10620 | TT_Task | Design Authority is known - contact available | 06/04/2021 | 01/06/2021 | 06/04/2021 | 01/06/2021 | 0 | TK_Complete | 1208363553 | 651 | 1208363553_651
MRPP2-EMS.10660 | TT_Task | ReceptionO ; M Final Manuals | 04/04/2022 | 01/06/2022 | 03/03/2022 | nan | 64768 | TK_Active | 1208363553 | 652 | 1208363553_652
MRPP2-EMS.10830 | TT_Task | Implement ways of measuring fleet reliability and warranty outstanding works | 24/11/2022 | 02/06/2023 | nan | nan | 62568 | TK_NotStart | 1208363553 | 653 | 1208363553_653
MRPP2-EMS.10860 | TT_Task | Produce evidence of compliance with relevant standards | 22/03/2023 | 19/05/2023 | nan | nan | 62648 | TK_NotStart | 1208363553 | 584 | 1208363553_584
MRPP2-EMS.10930 | TT_Task | Establish baseline configuration | 06/04/2021 | 26/05/2021 | 05/04/2021 | 26/05/2021 | 0 | TK_Complete | 1208363553 | 654 | 1208363553_654
MRPP2-EMS.11090 | TT_Task | Modification status records are available | 27/06/2023 | 24/07/2023 | nan | nan | 62288 | TK_NotStart | 1208363553 | 655 | 1208363553_655
MRPP2-EMS.11100 | TT_Task | Configuration records of the fleet are available | 01/05/2023 | 24/07/2023 | nan | nan | 62288 | TK_NotStart | 1208363553 | 656 | 1208363553_656
MRPP2-EMS.11110 | TT_Task | Monitoring of contractual allocations and performance for each element of scope | 29/05/2023 | 24/07/2023 | nan | nan | 62288 | TK_NotStart | 1208363553 | 643 | 1208363553_643
MRPP2-EMS.11120 | TT_Task | Create reliability growth plan | 22/03/2023 | 19/05/2023 | nan | nan | 62648 | TK_NotStart | 1208363553 | 657 | 1208363553_657
MRPP2-EMS.10460 | TT_Task | Develop procedure required for day 1 maintenance operations | 07/09/2022 | 05/05/2023 | nan | nan | 0 | TK_NotStart | 1208363553 | 638 | 1208363553_638
MRPP2-EMS.10670 | TT_Task | Validate that all main safety related tasks have been audited | 08/03/2023 | 05/05/2023 | nan | nan | 0 | TK_NotStart | 1208363553 | 658 | 1208363553_658
MRPP2-EMS.10790 | TT_Task | Development of System of icident reporting and responsibilities | 06/04/2021 | 12/05/2021 | 05/04/2021 | 12/05/2021 | 0 | TK_Complete | 1208363553 | 659 | 1208363553_659
MRPP2-EMS.10870 | TT_Task | Establish customer complaints management system and operating in line with local site QMS | 08/03/2023 | 05/05/2023 | nan | nan | 62728 | TK_NotStart | 1208363553 | 660 | 1208363553_660
MRPP2-EMS.11150 | TT_Task | Produce technical and commercial Rex | 08/12/2022 | 05/05/2023 | nan | nan | 62728 | TK_NotStart | 1208363553 | 661 | 1208363553_661
MRPP2-OPT.30000 | TT_Task | Optional Order Train CBS/Fitting Supply Production 1st Fleet 1st to 6th EMU [6 units] | 25/11/2027 | 22/11/2028 | nan | nan | 0 | TK_NotStart | 1208363553 | 662 | 1208363553_662
MRPP2-OPT.30010 | TT_Task | Optional Order Train CBS/Fitting Supply Deliveries 1st Fleet 1st to 6th EMU [6 units] | 25/07/2028 | 25/07/2029 | nan | nan | 0 | TK_NotStart | 1208363553 | 662 | 1208363553_662
MRPP2-OPT.30030 | TT_Task | Optional Order Train CBS/Fitting Supply Production 2nd Fleet 7th to 12th EMU [6 units] | 03/05/2028 | 03/05/2029 | nan | nan | 0 | TK_NotStart | 1208363553 | 662 | 1208363553_662
MRPP2-OPT.30040 | TT_Task | Optional Order Train CBS/Fitting Supply Deliveries 2nd Fleet 7th to 12th EMU [6 units] | 28/12/2028 | 09/01/2030 | nan | nan | 0 | TK_NotStart | 1208363553 | 662 | 1208363553_662
MRPP2-OPT.30060 | TT_Task | Optional Order Train CBS/Fitting Supply Production 3rd Fleet 13th to 18th EMU [6 units] | 10/10/2028 | 10/10/2029 | nan | nan | 0 | TK_NotStart | 1208363553 | 662 | 1208363553_662
MRPP2-OPT.30070 | TT_Task | Optional Order Train CBS/Fitting Supply Deliveries 3rd Fleet 13th to 18th EMU [6 units] | 12/06/2029 | 14/06/2030 | nan | nan | 0 | TK_NotStart | 1208363553 | 662 | 1208363553_662
MRPP2-OPT.30090 | TT_Task | Optional Order Train CBS/Fitting Supply Production 4th Fleet 19th to 24th EMU [6 units] | 19/03/2029 | 27/03/2030 | nan | nan | 0 | TK_NotStart | 1208363553 | 662 | 1208363553_662
MRPP2-OPT.30100 | TT_Task | Optional Order Train CBS/Fitting Supply Deliveries 4th Fleet 19th to 24th EMU [6 units] | 14/11/2029 | 15/11/2030 | nan | nan | 0 | TK_NotStart | 1208363553 | 662 | 1208363553_662
MRPP2-OPT.30120 | TT_Task | Optional Order Train CBS/Fitting Supply Production 5th Fleet 25th to 30th EMU [6 units] | 27/08/2029 | 29/08/2030 | nan | nan | 0 | TK_NotStart | 1208363553 | 662 | 1208363553_662
MRPP2-OPT.30130 | TT_Task | Optional Order Train CBS/Fitting Supply Deliveries 5th Fleet 25th to 30th EMU [6 units] | 02/05/2030 | 21/04/2031 | nan | nan | 0 | TK_NotStart | 1208363553 | 662 | 1208363553_662
MRPP2-OPT.11500 | TT_Task | EMU - Train 01 - Carbodyshell | 19/09/2028 | 17/10/2028 | nan | nan | 0 | TK_NotStart | 1208363553 | 435 | 1208363553_435
MRPP2-OPT.11880 | TT_Task | EMU - Train 01 - Bogie | 21/12/2028 | 22/01/2029 | nan | nan | 120 | TK_NotStart | 1208363553 | 663 | 1208363553_663
MRPP2-OPT.12380 | TT_Task | EMU - Train 01 - CBS Transport from Sri City Fty to Bellevue Depot | 18/10/2028 | 20/12/2028 | nan | nan | 0 | TK_NotStart | 1208363553 | 436 | 1208363553_436
MRPP2-OPT.12990 | TT_Task | EMU - Train 01 - Pre-Fitting | 21/12/2028 | 13/02/2029 | nan | nan | 0 | TK_NotStart | 1208363553 | 664 | 1208363553_664
MRPP2-OPT.13300 | TT_Task | EMU - Train 01 - Fitting | 02/01/2029 | 20/02/2029 | nan | nan | 0 | TK_NotStart | 1208363553 | 427 | 1208363553_427
MRPP2-OPT.13690 | TT_Task | EMU - Train 01 - Routine Test | 21/02/2029 | 20/03/2029 | nan | nan | 0 | TK_NotStart | 1208363553 | 437 | 1208363553_437
MRPP2-OPT.11810 | TT_Task | EMU - Train 02 - Carbodyshell | 18/10/2028 | 14/11/2028 | nan | nan | 0 | TK_NotStart | 1208363553 | 435 | 1208363553_435
MRPP2-OPT.11890 | TT_Task | EMU - Train 02 - Bogie | 23/01/2029 | 20/02/2029 | nan | nan | 120 | TK_NotStart | 1208363553 | 663 | 1208363553_663
MRPP2-OPT.12390 | TT_Task | EMU - Train 02 - CBS Transport from Sri City Fty to Bellevue Depot | 15/11/2028 | 22/01/2029 | nan | nan | 0 | TK_NotStart | 1208363553 | 436 | 1208363553_436
MRPP2-OPT.12850 | TT_Task | EMU - Train 02 - Pre-Fitting | 23/01/2029 | 13/03/2029 | nan | nan | 0 | TK_NotStart | 1208363553 | 664 | 1208363553_664
MRPP2-OPT.13510 | TT_Task | EMU - Train 02 - Fitting | 31/01/2029 | 20/03/2029 | nan | nan | 0 | TK_NotStart | 1208363553 | 427 | 1208363553_427
MRPP2-OPT.13830 | TT_Task | EMU - Train 02 - Routine Test | 21/03/2029 | 19/04/2029 | nan | nan | 0 | TK_NotStart | 1208363553 | 437 | 1208363553_437
MRPP2-OPT.12370 | TT_Task | EMU - Train 03 - Carbodyshell | 15/11/2028 | 12/12/2028 | nan | nan | 0 | TK_NotStart | 1208363553 | 435 | 1208363553_435
MRPP2-OPT.12480 | TT_Task | EMU - Train 03 - Bogie | 21/02/2029 | 20/03/2029 | nan | nan | 120 | TK_NotStart | 1208363553 | 663 | 1208363553_663
MRPP2-OPT.12840 | TT_Task | EMU - Train 03 - CBS Transport from Sri City Fty to Bellevue Depot | 13/12/2028 | 20/02/2029 | nan | nan | 0 | TK_NotStart | 1208363553 | 436 | 1208363553_436
MRPP2-OPT.13430 | TT_Task | EMU - Train 03 - Pre-Fitting | 21/02/2029 | 10/04/2029 | nan | nan | 0 | TK_NotStart | 1208363553 | 664 | 1208363553_664
MRPP2-OPT.13630 | TT_Task | EMU - Train 03 - Fitting | 28/02/2029 | 19/04/2029 | nan | nan | 0 | TK_NotStart | 1208363553 | 427 | 1208363553_427
MRPP2-OPT.14020 | TT_Task | EMU - Train 03 - Routine Test | 20/04/2029 | 18/05/2029 | nan | nan | 0 | TK_NotStart | 1208363553 | 437 | 1208363553_437
MRPP2-OPT.12830 | TT_Task | EMU - Train 04 - Carbodyshell | 13/12/2028 | 12/01/2029 | nan | nan | 0 | TK_NotStart | 1208363553 | 439 | 1208363553_439
MRPP2-OPT.13090 | TT_Task | EMU - Train 04 - Bogie | 21/03/2029 | 19/04/2029 | nan | nan | 240 | TK_NotStart | 1208363553 | 663 | 1208363553_663
MRPP2-OPT.13420 | TT_Task | EMU - Train 04 - CBS Transport from Sri City Fty to Bellevue Depot | 15/01/2029 | 20/03/2029 | nan | nan | 0 | TK_NotStart | 1208363553 | 436 | 1208363553_436
MRPP2-OPT.13620 | TT_Task | EMU - Train 04 - Pre-Fitting | 21/03/2029 | 01/06/2029 | nan | nan | 0 | TK_NotStart | 1208363553 | 664 | 1208363553_664
MRPP2-OPT.13780 | TT_Task | EMU - Train 04 - Fitting | 28/03/2029 | 11/06/2029 | nan | nan | 0 | TK_NotStart | 1208363553 | 427 | 1208363553_427
MRPP2-OPT.14230 | TT_Task | EMU - Train 04 - Routine Test | 12/06/2029 | 09/07/2029 | nan | nan | 0 | TK_NotStart | 1208363553 | 437 | 1208363553_437
MRPP2-OPT.13410 | TT_Task | EMU - Train 05 - Carbodyshell | 15/01/2029 | 12/02/2029 | nan | nan | 0 | TK_NotStart | 1208363553 | 435 | 1208363553_435
MRPP2-OPT.13470 | TT_Task | EMU - Train 05 - Bogie | 20/04/2029 | 18/05/2029 | nan | nan | 40 | TK_NotStart | 1208363553 | 663 | 1208363553_663
MRPP2-OPT.13600 | TT_Task | EMU - Train 05 - CBS Transport from Sri City Fty to Bellevue Depot | 13/02/2029 | 19/04/2029 | nan | nan | 0 | TK_NotStart | 1208363553 | 436 | 1208363553_436
MRPP2-OPT.13850 | TT_Task | EMU - Train 05 - Pre-Fitting | 20/04/2029 | 02/07/2029 | nan | nan | 0 | TK_NotStart | 1208363553 | 664 | 1208363553_664
MRPP2-OPT.13970 | TT_Task | EMU - Train 05 - Fitting | 30/04/2029 | 09/07/2029 | nan | nan | 0 | TK_NotStart | 1208363553 | 427 | 1208363553_427
MRPP2-OPT.14540 | TT_Task | EMU - Train 05 - Routine Test | 10/07/2029 | 06/08/2029 | nan | nan | 0 | TK_NotStart | 1208363553 | 437 | 1208363553_437
MRPP2-OPT.13590 | TT_Task | EMU - Train 06 - Carbodyshell | 13/02/2029 | 12/03/2029 | nan | nan | 0 | TK_NotStart | 1208363553 | 435 | 1208363553_435
MRPP2-OPT.13680 | TT_Task | EMU - Train 06 - Bogie | 21/05/2029 | 18/06/2029 | nan | nan | 160 | TK_NotStart | 1208363553 | 663 | 1208363553_663
MRPP2-OPT.13810 | TT_Task | EMU - Train 06 - CBS Transport from Sri City Fty to Bellevue Depot | 13/03/2029 | 18/05/2029 | nan | nan | 0 | TK_NotStart | 1208363553 | 436 | 1208363553_436
MRPP2-OPT.14090 | TT_Task | EMU - Train 06 - Pre-Fitting | 21/05/2029 | 30/07/2029 | nan | nan | 0 | TK_NotStart | 1208363553 | 664 | 1208363553_664
MRPP2-OPT.14260 | TT_Task | EMU - Train 06 - Fitting | 19/06/2029 | 27/08/2029 | nan | nan | 0 | TK_NotStart | 1208363553 | 427 | 1208363553_427
MRPP2-OPT.15370 | TT_Task | EMU - Train 06 - Routine Test | 28/08/2029 | 23/10/2029 | nan | nan | 0 | TK_NotStart | 1208363553 | 437 | 1208363553_437
MRPP2-OPT.13910 | TT_Task | EMU - Train 07 - Carbodyshell | 13/03/2029 | 26/04/2029 | nan | nan | 0 | TK_NotStart | 1208363553 | 435 | 1208363553_435
MRPP2-OPT.13960 | TT_Task | EMU - Train 07 - Bogie | 03/07/2029 | 13/08/2029 | nan | nan | 160 | TK_NotStart | 1208363553 | 663 | 1208363553_663
MRPP2-OPT.14140 | TT_Task | EMU - Train 07 - CBS Transport from Sri City Fty to Bellevue Depot | 27/04/2029 | 02/07/2029 | nan | nan | 0 | TK_NotStart | 1208363553 | 436 | 1208363553_436
MRPP2-OPT.14710 | TT_Task | EMU - Train 07 - Pre-Fitting | 03/07/2029 | 10/09/2029 | nan | nan | 0 | TK_NotStart | 1208363553 | 664 | 1208363553_664
MRPP2-OPT.15070 | TT_Task | EMU - Train 07 - Fitting | 31/07/2029 | 06/11/2029 | nan | nan | 0 | TK_NotStart | 1208363553 | 427 | 1208363553_427
MRPP2-OPT.15960 | TT_Task | EMU - Train 07 - Routine Test | 07/11/2029 | 15/01/2030 | nan | nan | 0 | TK_NotStart | 1208363553 | 437 | 1208363553_437
MRPP2-OPT.14130 | TT_Task | EMU - Train 08 - Carbodyshell | 27/04/2029 | 08/06/2029 | nan | nan | 0 | TK_NotStart | 1208363553 | 435 | 1208363553_435
MRPP2-OPT.14250 | TT_Task | EMU - Train 08 - Bogie | 14/08/2029 | 25/09/2029 | nan | nan | 240 | TK_NotStart | 1208363553 | 663 | 1208363553_663
MRPP2-OPT.14670 | TT_Task | EMU - Train 08 - CBS Transport from Sri City Fty to Bellevue Depot | 11/06/2029 | 13/08/2029 | nan | nan | 0 | TK_NotStart | 1208363553 | 436 | 1208363553_436
MRPP2-OPT.15450 | TT_Task | EMU - Train 08 - Pre-Fitting | 14/08/2029 | 23/10/2029 | nan | nan | 0 | TK_NotStart | 1208363553 | 664 | 1208363553_664
MRPP2-OPT.15580 | TT_Task | EMU - Train 08 - Fitting | 26/09/2029 | 15/01/2030 | nan | nan | 0 | TK_NotStart | 1208363553 | 427 | 1208363553_427
MRPP2-OPT.16430 | TT_Task | EMU - Train 08 - Routine Test | 16/01/2030 | 12/03/2030 | nan | nan | 0 | TK_NotStart | 1208363553 | 437 | 1208363553_437
MRPP2-OPT.14660 | TT_Task | EMU - Train 09 - Carbodyshell | 11/06/2029 | 20/07/2029 | nan | nan | 0 | TK_NotStart | 1208363553 | 435 | 1208363553_435
MRPP2-OPT.14860 | TT_Task | EMU - Train 09 - Bogie | 26/09/2029 | 06/11/2029 | nan | nan | 320 | TK_NotStart | 1208363553 | 663 | 1208363553_663
MRPP2-OPT.15430 | TT_Task | EMU - Train 09 - CBS Transport from Sri City Fty to Bellevue Depot | 23/07/2029 | 25/09/2029 | nan | nan | 0 | TK_NotStart | 1208363553 | 436 | 1208363553_436
MRPP2-OPT.15900 | TT_Task | EMU - Train 09 - Pre-Fitting | 26/09/2029 | 04/12/2029 | nan | nan | 0 | TK_NotStart | 1208363553 | 664 | 1208363553_664
MRPP2-OPT.16200 | TT_Task | EMU - Train 09 - Fitting | 21/11/2029 | 12/03/2030 | nan | nan | 0 | TK_NotStart | 1208363553 | 427 | 1208363553_427
MRPP2-OPT.16630 | TT_Task | EMU - Train 09 - Routine Test | 13/03/2030 | 07/05/2030 | nan | nan | 0 | TK_NotStart | 1208363553 | 437 | 1208363553_437
MRPP2-OPT.15420 | TT_Task | EMU - Train 10 - Carbodyshell | 23/07/2029 | 31/08/2029 | nan | nan | 0 | TK_NotStart | 1208363553 | 439 | 1208363553_439
MRPP2-OPT.15560 | TT_Task | EMU - Train 10 - Bogie | 07/11/2029 | 18/12/2029 | nan | nan | 80 | TK_NotStart | 1208363553 | 665 | 1208363553_665
MRPP2-OPT.15890 | TT_Task | EMU - Train 10 - CBS Transport from Sri City Fty to Bellevue Depot | 03/09/2029 | 06/11/2029 | nan | nan | 0 | TK_NotStart | 1208363553 | 436 | 1208363553_436
MRPP2-OPT.16420 | TT_Task | EMU - Train 10 - Pre-Fitting | 07/11/2029 | 29/01/2030 | nan | nan | 0 | TK_NotStart | 1208363553 | 666 | 1208363553_666
MRPP2-OPT.16500 | TT_Task | EMU - Train 10 - Fitting | 16/01/2030 | 23/04/2030 | nan | nan | 80 | TK_NotStart | 1208363553 | 440 | 1208363553_440
MRPP2-OPT.16780 | TT_Task | EMU - Train 10 - Routine Test | 08/05/2030 | 02/07/2030 | nan | nan | 0 | TK_NotStart | 1208363553 | 441 | 1208363553_441
MRPP2-OPT.15880 | TT_Task | EMU - Train 11 - Carbodyshell | 03/09/2029 | 15/10/2029 | nan | nan | 0 | TK_NotStart | 1208363553 | 439 | 1208363553_439
MRPP2-OPT.16130 | TT_Task | EMU - Train 11 - Bogie | 19/12/2029 | 12/02/2030 | nan | nan | 160 | TK_NotStart | 1208363553 | 665 | 1208363553_665
MRPP2-OPT.16410 | TT_Task | EMU - Train 11 - CBS Transport from Sri City Fty to Bellevue Depot | 16/10/2029 | 18/12/2029 | nan | nan | 0 | TK_NotStart | 1208363553 | 436 | 1208363553_436
MRPP2-OPT.16620 | TT_Task | EMU - Train 11 - Pre-Fitting | 19/12/2029 | 26/03/2030 | nan | nan | 0 | TK_NotStart | 1208363553 | 666 | 1208363553_666
MRPP2-OPT.16680 | TT_Task | EMU - Train 11 - Fitting | 13/03/2030 | 18/06/2030 | nan | nan | 80 | TK_NotStart | 1208363553 | 440 | 1208363553_440
MRPP2-OPT.17100 | TT_Task | EMU - Train 11 - Routine Test | 03/07/2030 | 27/08/2030 | nan | nan | 0 | TK_NotStart | 1208363553 | 441 | 1208363553_441
MRPP2-OPT.16400 | TT_Task | EMU - Train 12 - Carbodyshell | 16/10/2029 | 26/11/2029 | nan | nan | 0 | TK_NotStart | 1208363553 | 439 | 1208363553_439
MRPP2-OPT.16480 | TT_Task | EMU - Train 12 - Bogie | 13/02/2030 | 26/03/2030 | nan | nan | 0 | TK_NotStart | 1208363553 | 665 | 1208363553_665
MRPP2-OPT.16600 | TT_Task | EMU - Train 12 - CBS Transport from Sri City Fty to Bellevue Depot | 27/11/2029 | 12/02/2030 | nan | nan | 0 | TK_NotStart | 1208363553 | 436 | 1208363553_436
MRPP2-OPT.16760 | TT_Task | EMU - Train 12 - Pre-Fitting | 13/02/2030 | 07/05/2030 | nan | nan | 0 | TK_NotStart | 1208363553 | 666 | 1208363553_666
MRPP2-OPT.16870 | TT_Task | EMU - Train 12 - Fitting | 27/03/2030 | 02/07/2030 | nan | nan | 320 | TK_NotStart | 1208363553 | 440 | 1208363553_440
MRPP2-OPT.17410 | TT_Task | EMU - Train 12 - Routine Test | 28/08/2030 | 22/10/2030 | nan | nan | 0 | TK_NotStart | 1208363553 | 441 | 1208363553_441
MRPP2-OPT.16590 | TT_Task | EMU - Train 13 - Carbodyshell | 27/11/2029 | 21/01/2030 | nan | nan | 0 | TK_NotStart | 1208363553 | 439 | 1208363553_439
MRPP2-OPT.16660 | TT_Task | EMU - Train 13 - Bogie | 27/03/2030 | 07/05/2030 | nan | nan | 160 | TK_NotStart | 1208363553 | 665 | 1208363553_665
MRPP2-OPT.16750 | TT_Task | EMU - Train 13 - CBS Transport from Sri City Fty to Bellevue Depot | 22/01/2030 | 26/03/2030 | nan | nan | 0 | TK_NotStart | 1208363553 | 436 | 1208363553_436
MRPP2-OPT.17080 | TT_Task | EMU - Train 13 - Pre-Fitting | 27/03/2030 | 18/06/2030 | nan | nan | 0 | TK_NotStart | 1208363553 | 666 | 1208363553_666
MRPP2-OPT.17230 | TT_Task | EMU - Train 13 - Fitting | 05/06/2030 | 10/09/2030 | nan | nan | 240 | TK_NotStart | 1208363553 | 440 | 1208363553_440
MRPP2-OPT.17710 | TT_Task | EMU - Train 13 - Routine Test | 23/10/2030 | 17/12/2030 | nan | nan | 0 | TK_NotStart | 1208363553 | 441 | 1208363553_441
MRPP2-OPT.16740 | TT_Task | EMU - Train 14 - Carbodyshell | 22/01/2030 | 04/03/2030 | nan | nan | 0 | TK_NotStart | 1208363553 | 439 | 1208363553_439
MRPP2-OPT.16850 | TT_Task | EMU - Train 14 - Bogie | 08/05/2030 | 18/06/2030 | nan | nan | 160 | TK_NotStart | 1208363553 | 665 | 1208363553_665
MRPP2-OPT.17070 | TT_Task | EMU - Train 14 - CBS Transport from Sri City Fty to Bellevue Depot | 05/03/2030 | 07/05/2030 | nan | nan | 0 | TK_NotStart | 1208363553 | 436 | 1208363553_436
MRPP2-OPT.17390 | TT_Task | EMU - Train 14 - Pre-Fitting | 08/05/2030 | 30/07/2030 | nan | nan | 0 | TK_NotStart | 1208363553 | 666 | 1208363553_666
MRPP2-OPT.17560 | TT_Task | EMU - Train 14 - Fitting | 17/07/2030 | 22/10/2030 | nan | nan | 320 | TK_NotStart | 1208363553 | 440 | 1208363553_440
MRPP2-OPT.17850 | TT_Task | EMU - Train 14 - Routine Test | 18/12/2030 | 11/02/2031 | nan | nan | 0 | TK_NotStart | 1208363553 | 441 | 1208363553_441
MRPP2-OPT.17060 | TT_Task | EMU - Train 15 - Carbodyshell | 05/03/2030 | 15/04/2030 | nan | nan | 0 | TK_NotStart | 1208363553 | 439 | 1208363553_439
MRPP2-OPT.17210 | TT_Task | EMU - Train 15 - Bogie | 19/06/2030 | 30/07/2030 | nan | nan | 160 | TK_NotStart | 1208363553 | 665 | 1208363553_665
MRPP2-OPT.17380 | TT_Task | EMU - Train 15 - CBS Transport from Sri City Fty to Bellevue Depot | 16/04/2030 | 18/06/2030 | nan | nan | 0 | TK_NotStart | 1208363553 | 436 | 1208363553_436
MRPP2-OPT.17700 | TT_Task | EMU - Train 15 - Pre-Fitting | 19/06/2030 | 10/09/2030 | nan | nan | 0 | TK_NotStart | 1208363553 | 666 | 1208363553_666
MRPP2-OPT.17760 | TT_Task | EMU - Train 15 - Fitting | 28/08/2030 | 03/12/2030 | nan | nan | 400 | TK_NotStart | 1208363553 | 440 | 1208363553_440
MRPP2-OPT.17950 | TT_Task | EMU - Train 15 - Routine Test | 12/02/2031 | 08/04/2031 | nan | nan | 0 | TK_NotStart | 1208363553 | 441 | 1208363553_441
MRPP2-OPT.17370 | TT_Task | EMU - Train 16 - Carbodyshell | 16/04/2030 | 27/05/2030 | nan | nan | 0 | TK_NotStart | 1208363553 | 439 | 1208363553_439
MRPP2-OPT.17490 | TT_Task | EMU - Train 16 - Bogie | 31/07/2030 | 10/09/2030 | nan | nan | 0 | TK_NotStart | 1208363553 | 665 | 1208363553_665
MRPP2-OPT.17690 | TT_Task | EMU - Train 16 - CBS Transport from Sri City Fty to Bellevue Depot | 28/05/2030 | 30/07/2030 | nan | nan | 0 | TK_NotStart | 1208363553 | 436 | 1208363553_436
MRPP2-OPT.17840 | TT_Task | EMU - Train 16 - Pre-Fitting | 11/09/2030 | 03/12/2030 | nan | nan | 0 | TK_NotStart | 1208363553 | 666 | 1208363553_666
MRPP2-OPT.17890 | TT_Task | EMU - Train 16 - Fitting | 20/11/2030 | 25/02/2031 | nan | nan | 240 | TK_NotStart | 1208363553 | 440 | 1208363553_440
MRPP2-OPT.18050 | TT_Task | EMU - Train 16 - Routine Test | 09/04/2031 | 03/06/2031 | nan | nan | 0 | TK_NotStart | 1208363553 | 441 | 1208363553_441
MRPP2-OPT.17680 | TT_Task | EMU - Train 17 - Carbodyshell | 28/05/2030 | 08/07/2030 | nan | nan | 0 | TK_NotStart | 1208363553 | 439 | 1208363553_439
MRPP2-OPT.17740 | TT_Task | EMU - Train 17 - Bogie | 11/09/2030 | 22/10/2030 | nan | nan | 0 | TK_NotStart | 1208363553 | 665 | 1208363553_665
MRPP2-OPT.17830 | TT_Task | EMU - Train 17 - CBS Transport from Sri City Fty to Bellevue Depot | 09/07/2030 | 10/09/2030 | nan | nan | 0 | TK_NotStart | 1208363553 | 436 | 1208363553_436
MRPP2-OPT.17940 | TT_Task | EMU - Train 17 - Pre-Fitting | 23/10/2030 | 14/01/2031 | nan | nan | 0 | TK_NotStart | 1208363553 | 666 | 1208363553_666
MRPP2-OPT.17990 | TT_Task | EMU - Train 17 - Fitting | 01/01/2031 | 08/04/2031 | nan | nan | 320 | TK_NotStart | 1208363553 | 440 | 1208363553_440
MRPP2-OPT.18150 | TT_Task | EMU - Train 17 - Routine Test | 04/06/2031 | 29/07/2031 | nan | nan | 0 | TK_NotStart | 1208363553 | 441 | 1208363553_441
MRPP2-OPT.17820 | TT_Task | EMU - Train 18 - Carbodyshell | 09/07/2030 | 19/08/2030 | nan | nan | 0 | TK_NotStart | 1208363553 | 439 | 1208363553_439
MRPP2-OPT.17870 | TT_Task | EMU - Train 18 - Bogie | 23/10/2030 | 03/12/2030 | nan | nan | 0 | TK_NotStart | 1208363553 | 665 | 1208363553_665
MRPP2-OPT.17930 | TT_Task | EMU - Train 18 - CBS Transport from Sri City Fty to Bellevue Depot | 20/08/2030 | 22/10/2030 | nan | nan | 0 | TK_NotStart | 1208363553 | 436 | 1208363553_436
MRPP2-OPT.18040 | TT_Task | EMU - Train 18 - Pre-Fitting | 04/12/2030 | 25/02/2031 | nan | nan | 0 | TK_NotStart | 1208363553 | 666 | 1208363553_666
MRPP2-OPT.18080 | TT_Task | EMU - Train 18 - Fitting | 12/02/2031 | 20/05/2031 | nan | nan | 400 | TK_NotStart | 1208363553 | 442 | 1208363553_442
MRPP2-OPT.18250 | TT_Task | EMU - Train 18 - Routine Test | 30/07/2031 | 23/09/2031 | nan | nan | 0 | TK_NotStart | 1208363553 | 443 | 1208363553_443
MRPP2-OPT.17920 | TT_Task | EMU - Train 19 - Carbodyshell | 20/08/2030 | 30/09/2030 | nan | nan | 0 | TK_NotStart | 1208363553 | 439 | 1208363553_439
MRPP2-OPT.17970 | TT_Task | EMU - Train 19 - Bogie | 04/12/2030 | 14/01/2031 | nan | nan | 0 | TK_NotStart | 1208363553 | 665 | 1208363553_665
MRPP2-OPT.18030 | TT_Task | EMU - Train 19 - CBS Transport from Sri City Fty to Bellevue Depot | 01/10/2030 | 03/12/2030 | nan | nan | 0 | TK_NotStart | 1208363553 | 436 | 1208363553_436
MRPP2-OPT.18140 | TT_Task | EMU - Train 19 - Pre-Fitting | 15/01/2031 | 08/04/2031 | nan | nan | 0 | TK_NotStart | 1208363553 | 666 | 1208363553_666
MRPP2-OPT.18180 | TT_Task | EMU - Train 19 - Fitting | 26/03/2031 | 01/07/2031 | nan | nan | 480 | TK_NotStart | 1208363553 | 442 | 1208363553_442
MRPP2-OPT.18350 | TT_Task | EMU - Train 19 - Routine Test | 24/09/2031 | 18/11/2031 | nan | nan | 0 | TK_NotStart | 1208363553 | 443 | 1208363553_443
MRPP2-OPT.18020 | TT_Task | EMU - Train 20 - Carbodyshell | 01/10/2030 | 11/11/2030 | nan | nan | 0 | TK_NotStart | 1208363553 | 439 | 1208363553_439
MRPP2-OPT.18060 | TT_Task | EMU - Train 20 - Bogie | 15/01/2031 | 25/02/2031 | nan | nan | 0 | TK_NotStart | 1208363553 | 665 | 1208363553_665
MRPP2-OPT.18130 | TT_Task | EMU - Train 20 - CBS Transport from Sri City Fty to Bellevue Depot | 12/11/2030 | 14/01/2031 | nan | nan | 0 | TK_NotStart | 1208363553 | 436 | 1208363553_436
MRPP2-OPT.18240 | TT_Task | EMU - Train 20 - Pre-Fitting | 26/02/2031 | 20/05/2031 | nan | nan | 0 | TK_NotStart | 1208363553 | 666 | 1208363553_666
MRPP2-OPT.18280 | TT_Task | EMU - Train 20 - Fitting | 07/05/2031 | 12/08/2031 | nan | nan | 560 | TK_NotStart | 1208363553 | 442 | 1208363553_442
MRPP2-OPT.18450 | TT_Task | EMU - Train 20 - Routine Test | 19/11/2031 | 13/01/2032 | nan | nan | 0 | TK_NotStart | 1208363553 | 443 | 1208363553_443
MRPP2-OPT.18120 | TT_Task | EMU - Train 21 - Carbodyshell | 12/11/2030 | 23/12/2030 | nan | nan | 0 | TK_NotStart | 1208363553 | 439 | 1208363553_439
MRPP2-OPT.18160 | TT_Task | EMU - Train 21 - Bogie | 26/02/2031 | 08/04/2031 | nan | nan | 0 | TK_NotStart | 1208363553 | 665 | 1208363553_665
MRPP2-OPT.18230 | TT_Task | EMU - Train 21 - CBS Transport from Sri City Fty to Bellevue Depot | 24/12/2030 | 25/02/2031 | nan | nan | 0 | TK_NotStart | 1208363553 | 436 | 1208363553_436
MRPP2-OPT.18340 | TT_Task | EMU - Train 21 - Pre-Fitting | 09/04/2031 | 01/07/2031 | nan | nan | 0 | TK_NotStart | 1208363553 | 666 | 1208363553_666
MRPP2-OPT.18380 | TT_Task | EMU - Train 21 - Fitting | 18/06/2031 | 23/09/2031 | nan | nan | 640 | TK_NotStart | 1208363553 | 442 | 1208363553_442
MRPP2-OPT.18550 | TT_Task | EMU - Train 21 - Routine Test | 14/01/2032 | 09/03/2032 | nan | nan | 0 | TK_NotStart | 1208363553 | 443 | 1208363553_443
MRPP2-OPT.18220 | TT_Task | EMU - Train 22 - Carbodyshell | 24/12/2030 | 03/02/2031 | nan | nan | 0 | TK_NotStart | 1208363553 | 439 | 1208363553_439
MRPP2-OPT.18260 | TT_Task | EMU - Train 22 - Bogie | 09/04/2031 | 20/05/2031 | nan | nan | 0 | TK_NotStart | 1208363553 | 665 | 1208363553_665
MRPP2-OPT.18330 | TT_Task | EMU - Train 22 - CBS Transport from Sri City Fty to Bellevue Depot | 04/02/2031 | 08/04/2031 | nan | nan | 0 | TK_NotStart | 1208363553 | 436 | 1208363553_436
MRPP2-OPT.18440 | TT_Task | EMU - Train 22 - Pre-Fitting | 21/05/2031 | 12/08/2031 | nan | nan | 0 | TK_NotStart | 1208363553 | 442 | 1208363553_442
MRPP2-OPT.18470 | TT_Task | EMU - Train 22 - Fitting | 30/07/2031 | 04/11/2031 | nan | nan | 720 | TK_NotStart | 1208363553 | 442 | 1208363553_442
MRPP2-OPT.18650 | TT_Task | EMU - Train 22 - Routine Test | 10/03/2032 | 04/05/2032 | nan | nan | 0 | TK_NotStart | 1208363553 | 443 | 1208363553_443
MRPP2-OPT.18320 | TT_Task | EMU - Train 23 - Carbodyshell | 04/02/2031 | 17/03/2031 | nan | nan | 0 | TK_NotStart | 1208363553 | 439 | 1208363553_439
MRPP2-OPT.18360 | TT_Task | EMU - Train 23 - Bogie | 21/05/2031 | 01/07/2031 | nan | nan | 0 | TK_NotStart | 1208363553 | 665 | 1208363553_665
MRPP2-OPT.18430 | TT_Task | EMU - Train 23 - CBS Transport from Sri City Fty to Bellevue Depot | 18/03/2031 | 20/05/2031 | nan | nan | 0 | TK_NotStart | 1208363553 | 436 | 1208363553_436
MRPP2-OPT.18540 | TT_Task | EMU - Train 23 - Pre-Fitting | 02/07/2031 | 23/09/2031 | nan | nan | 0 | TK_NotStart | 1208363553 | 666 | 1208363553_666
MRPP2-OPT.18570 | TT_Task | EMU - Train 23 - Fitting | 10/09/2031 | 16/12/2031 | nan | nan | 800 | TK_NotStart | 1208363553 | 442 | 1208363553_442
MRPP2-OPT.18750 | TT_Task | EMU - Train 23 - Routine Test | 05/05/2032 | 29/06/2032 | nan | nan | 0 | TK_NotStart | 1208363553 | 443 | 1208363553_443
MRPP2-OPT.18420 | TT_Task | EMU - Train 24 - Carbodyshell | 18/03/2031 | 28/04/2031 | nan | nan | 0 | TK_NotStart | 1208363553 | 439 | 1208363553_439
MRPP2-OPT.18460 | TT_Task | EMU - Train 24 - Bogie | 02/07/2031 | 12/08/2031 | nan | nan | 0 | TK_NotStart | 1208363553 | 665 | 1208363553_665
MRPP2-OPT.18530 | TT_Task | EMU - Train 24 - CBS Transport from Sri City Fty to Bellevue Depot | 29/04/2031 | 01/07/2031 | nan | nan | 0 | TK_NotStart | 1208363553 | 436 | 1208363553_436
MRPP2-OPT.18640 | TT_Task | EMU - Train 24 - Pre-Fitting | 13/08/2031 | 04/11/2031 | nan | nan | 0 | TK_NotStart | 1208363553 | 666 | 1208363553_666
MRPP2-OPT.18670 | TT_Task | EMU - Train 24 - Fitting | 22/10/2031 | 27/01/2032 | nan | nan | 880 | TK_NotStart | 1208363553 | 442 | 1208363553_442
MRPP2-OPT.18850 | TT_Task | EMU - Train 24 - Routine Test | 30/06/2032 | 24/08/2032 | nan | nan | 0 | TK_NotStart | 1208363553 | 443 | 1208363553_443
MRPP2-OPT.18520 | TT_Task | EMU - Train 25 - Carbodyshell | 29/04/2031 | 09/06/2031 | nan | nan | 0 | TK_NotStart | 1208363553 | 439 | 1208363553_439
MRPP2-OPT.18560 | TT_Task | EMU - Train 25 - Bogie | 13/08/2031 | 23/09/2031 | nan | nan | 0 | TK_NotStart | 1208363553 | 665 | 1208363553_665
MRPP2-OPT.18630 | TT_Task | EMU - Train 25 - CBS Transport from Sri City Fty to Bellevue Depot | 10/06/2031 | 12/08/2031 | nan | nan | 0 | TK_NotStart | 1208363553 | 436 | 1208363553_436
MRPP2-OPT.18740 | TT_Task | EMU - Train 25 - Pre-Fitting | 24/09/2031 | 16/12/2031 | nan | nan | 0 | TK_NotStart | 1208363553 | 666 | 1208363553_666
MRPP2-OPT.18770 | TT_Task | EMU - Train 25 - Fitting | 03/12/2031 | 09/03/2032 | nan | nan | 960 | TK_NotStart | 1208363553 | 442 | 1208363553_442
MRPP2-OPT.18950 | TT_Task | EMU - Train 25 - Routine Test | 25/08/2032 | 19/10/2032 | nan | nan | 0 | TK_NotStart | 1208363553 | 443 | 1208363553_443
MRPP2-OPT.18620 | TT_Task | EMU - Train 26 - Carbodyshell | 10/06/2031 | 21/07/2031 | nan | nan | 0 | TK_NotStart | 1208363553 | 444 | 1208363553_444
MRPP2-OPT.18660 | TT_Task | EMU - Train 26 - Bogie | 24/09/2031 | 04/11/2031 | nan | nan | 0 | TK_NotStart | 1208363553 | 665 | 1208363553_665
MRPP2-OPT.18730 | TT_Task | EMU - Train 26 - CBS Transport from Sri City Fty to Bellevue Depot | 22/07/2031 | 23/09/2031 | nan | nan | 0 | TK_NotStart | 1208363553 | 436 | 1208363553_436
MRPP2-OPT.18840 | TT_Task | EMU - Train 26 - Pre-Fitting | 05/11/2031 | 27/01/2032 | nan | nan | 0 | TK_NotStart | 1208363553 | 666 | 1208363553_666
MRPP2-OPT.18870 | TT_Task | EMU - Train 26 - Fitting | 14/01/2032 | 20/04/2032 | nan | nan | 1040 | TK_NotStart | 1208363553 | 445 | 1208363553_445
MRPP2-OPT.19050 | TT_Task | EMU - Train 26 - Routine Test | 20/10/2032 | 14/12/2032 | nan | nan | 0 | TK_NotStart | 1208363553 | 446 | 1208363553_446
MRPP2-OPT.18720 | TT_Task | EMU - Train 27 - Carbodyshell | 22/07/2031 | 01/09/2031 | nan | nan | 0 | TK_NotStart | 1208363553 | 444 | 1208363553_444
MRPP2-OPT.18760 | TT_Task | EMU - Train 27 - Bogie | 05/11/2031 | 16/12/2031 | nan | nan | 0 | TK_NotStart | 1208363553 | 665 | 1208363553_665
MRPP2-OPT.18830 | TT_Task | EMU - Train 27 - CBS Transport from Sri City Fty to Bellevue Depot | 02/09/2031 | 04/11/2031 | nan | nan | 0 | TK_NotStart | 1208363553 | 436 | 1208363553_436
MRPP2-OPT.18940 | TT_Task | EMU - Train 27 - Pre-Fitting | 17/12/2031 | 09/03/2032 | nan | nan | 0 | TK_NotStart | 1208363553 | 666 | 1208363553_666
MRPP2-OPT.18970 | TT_Task | EMU - Train 27 - Fitting | 25/02/2032 | 01/06/2032 | nan | nan | 1120 | TK_NotStart | 1208363553 | 445 | 1208363553_445
MRPP2-OPT.19140 | TT_Task | EMU - Train 27 - Routine Test | 15/12/2032 | 08/02/2033 | nan | nan | 0 | TK_NotStart | 1208363553 | 446 | 1208363553_446
MRPP2-OPT.18820 | TT_Task | EMU - Train 28 - Carbodyshell | 02/09/2031 | 13/10/2031 | nan | nan | 0 | TK_NotStart | 1208363553 | 444 | 1208363553_444
MRPP2-OPT.18860 | TT_Task | EMU - Train 28 - Bogie | 17/12/2031 | 27/01/2032 | nan | nan | 0 | TK_NotStart | 1208363553 | 665 | 1208363553_665
MRPP2-OPT.18930 | TT_Task | EMU - Train 28 - CBS Transport from Sri City Fty to Bellevue Depot | 14/10/2031 | 16/12/2031 | nan | nan | 0 | TK_NotStart | 1208363553 | 436 | 1208363553_436
MRPP2-OPT.19040 | TT_Task | EMU - Train 28 - Pre-Fitting | 28/01/2032 | 20/04/2032 | nan | nan | 0 | TK_NotStart | 1208363553 | 666 | 1208363553_666
MRPP2-OPT.19070 | TT_Task | EMU - Train 28 - Fitting | 07/04/2032 | 13/07/2032 | nan | nan | 1200 | TK_NotStart | 1208363553 | 445 | 1208363553_445
MRPP2-OPT.19210 | TT_Task | EMU - Train 28 - Routine Test | 09/02/2033 | 05/04/2033 | nan | nan | 0 | TK_NotStart | 1208363553 | 446 | 1208363553_446
MRPP2-OPT.18920 | TT_Task | EMU - Train 29 - Carbodyshell | 14/10/2031 | 24/11/2031 | nan | nan | 0 | TK_NotStart | 1208363553 | 444 | 1208363553_444
MRPP2-OPT.18960 | TT_Task | EMU - Train 29 - Bogie | 28/01/2032 | 09/03/2032 | nan | nan | 0 | TK_NotStart | 1208363553 | 665 | 1208363553_665
MRPP2-OPT.19020 | TT_Task | EMU - Train 29 - CBS Transport from Sri City Fty to Bellevue Depot | 25/11/2031 | 27/01/2032 | nan | nan | 0 | TK_NotStart | 1208363553 | 436 | 1208363553_436
MRPP2-OPT.19130 | TT_Task | EMU - Train 29 - Pre-Fitting | 10/03/2032 | 01/06/2032 | nan | nan | 0 | TK_NotStart | 1208363553 | 666 | 1208363553_666
MRPP2-OPT.19150 | TT_Task | EMU - Train 29 - Fitting | 19/05/2032 | 24/08/2032 | nan | nan | 1280 | TK_NotStart | 1208363553 | 445 | 1208363553_445
MRPP2-OPT.19270 | TT_Task | EMU - Train 29 - Routine Test | 06/04/2033 | 31/05/2033 | nan | nan | 0 | TK_NotStart | 1208363553 | 446 | 1208363553_446
MRPP2-OPT.19030 | TT_Task | EMU - Train 30 - Carbodyshell | 25/11/2031 | 05/01/2032 | nan | nan | 0 | TK_NotStart | 1208363553 | 444 | 1208363553_444
MRPP2-OPT.19060 | TT_Task | EMU - Train 30 - Bogie | 10/03/2032 | 20/04/2032 | nan | nan | 0 | TK_NotStart | 1208363553 | 665 | 1208363553_665
MRPP2-OPT.19120 | TT_Task | EMU - Train 30 - CBS Transport from Sri City Fty to Bellevue Depot | 06/01/2032 | 09/03/2032 | nan | nan | 0 | TK_NotStart | 1208363553 | 436 | 1208363553_436
MRPP2-OPT.19200 | TT_Task | EMU - Train 30 - Pre-Fitting | 21/04/2032 | 13/07/2032 | nan | nan | 0 | TK_NotStart | 1208363553 | 666 | 1208363553_666
MRPP2-OPT.19220 | TT_Task | EMU - Train 30 - Fitting | 30/06/2032 | 05/10/2032 | nan | nan | 1360 | TK_NotStart | 1208363553 | 445 | 1208363553_445
MRPP2-OPT.19310 | TT_Task | EMU - Train 30 - Routine Test | 01/06/2033 | 26/07/2033 | nan | nan | 0 | TK_NotStart | 1208363553 | 446 | 1208363553_446
MRPP2-OPT.13840 | TT_Task | EMU - Train 01 Preliminary Acceptance Test ; PTA Certification | 21/03/2029 | 03/04/2029 | nan | nan | 0 | TK_NotStart | 1208363553 | 450 | 1208363553_450
MRPP2-OPT.14030 | TT_Task | EMU - Train 02 Preliminary Acceptance Test ; PTA Certification | 20/04/2029 | 18/05/2029 | nan | nan | 0 | TK_NotStart | 1208363553 | 450 | 1208363553_450
MRPP2-OPT.14240 | TT_Task | EMU - Train 03 Preliminary Acceptance Test ; PTA Certification | 21/05/2029 | 02/07/2029 | nan | nan | 40 | TK_NotStart | 1208363553 | 450 | 1208363553_450
MRPP2-OPT.14530 | TT_Task | EMU - Train 04 Preliminary Acceptance Test ; PTA Certification | 10/07/2029 | 20/08/2029 | nan | nan | 0 | TK_NotStart | 1208363553 | 450 | 1208363553_450
MRPP2-OPT.15140 | TT_Task | EMU - Train 05 Preliminary Acceptance Test ; PTA Certification | 21/08/2029 | 02/10/2029 | nan | nan | 120 | TK_NotStart | 1208363553 | 450 | 1208363553_450
MRPP2-OPT.15640 | TT_Task | EMU - Train 06 Preliminary Acceptance Test ; PTA Certification | 24/10/2029 | 04/12/2029 | nan | nan | 128 | TK_NotStart | 1208363553 | 450 | 1208363553_450
MRPP2-OPT.16320 | TT_Task | EMU - Train 07 Preliminary Acceptance Test ; PTA Certification | 16/01/2030 | 26/02/2030 | nan | nan | 80 | TK_NotStart | 1208363553 | 450 | 1208363553_450
MRPP2-OPT.16560 | TT_Task | EMU - Train 08 Preliminary Acceptance Test ; PTA Certification | 13/03/2030 | 23/04/2030 | nan | nan | 80 | TK_NotStart | 1208363553 | 450 | 1208363553_450
MRPP2-OPT.16720 | TT_Task | EMU - Train 09 Preliminary Acceptance Test ; PTA Certification | 08/05/2030 | 18/06/2030 | nan | nan | 80 | TK_NotStart | 1208363553 | 450 | 1208363553_450
MRPP2-OPT.17010 | TT_Task | EMU - Train 10 Preliminary Acceptance Test ; PTA Certification | 03/07/2030 | 13/08/2030 | nan | nan | 80 | TK_NotStart | 1208363553 | 451 | 1208363553_451
MRPP2-OPT.17290 | TT_Task | EMU - Train 11 Preliminary Acceptance Test ; PTA Certification | 28/08/2030 | 08/10/2030 | nan | nan | 80 | TK_NotStart | 1208363553 | 451 | 1208363553_451
MRPP2-OPT.17620 | TT_Task | EMU - Train 12 Preliminary Acceptance Test ; PTA Certification | 23/10/2030 | 03/12/2030 | nan | nan | 80 | TK_NotStart | 1208363553 | 451 | 1208363553_451
MRPP2-OPT.17800 | TT_Task | EMU - Train 13 Preliminary Acceptance Test ; PTA Certification | 18/12/2030 | 11/02/2031 | nan | nan | 0 | TK_NotStart | 1208363553 | 451 | 1208363553_451
MRPP2-OPT.17910 | TT_Task | EMU - Train 14 Preliminary Acceptance Test ; PTA Certification | 12/02/2031 | 08/04/2031 | nan | nan | 0 | TK_NotStart | 1208363553 | 451 | 1208363553_451
MRPP2-OPT.18010 | TT_Task | EMU - Train 15 Preliminary Acceptance Test ; PTA Certification | 09/04/2031 | 03/06/2031 | nan | nan | 0 | TK_NotStart | 1208363553 | 451 | 1208363553_451
MRPP2-OPT.18110 | TT_Task | EMU - Train 16 Preliminary Acceptance Test ; PTA Certification | 04/06/2031 | 29/07/2031 | nan | nan | 0 | TK_NotStart | 1208363553 | 451 | 1208363553_451
MRPP2-OPT.18210 | TT_Task | EMU - Train 17 Preliminary Acceptance Test ; PTA Certification | 30/07/2031 | 23/09/2031 | nan | nan | 0 | TK_NotStart | 1208363553 | 451 | 1208363553_451
MRPP2-OPT.18310 | TT_Task | EMU - Train 18 Preliminary Acceptance Test ; PTA Certification | 24/09/2031 | 18/11/2031 | nan | nan | 0 | TK_NotStart | 1208363553 | 451 | 1208363553_451
MRPP2-OPT.18410 | TT_Task | EMU - Train 19 Preliminary Acceptance Test ; PTA Certification | 19/11/2031 | 13/01/2032 | nan | nan | 0 | TK_NotStart | 1208363553 | 451 | 1208363553_451
MRPP2-OPT.18510 | TT_Task | EMU - Train 20 Preliminary Acceptance Test ; PTA Certification | 14/01/2032 | 09/03/2032 | nan | nan | 0 | TK_NotStart | 1208363553 | 451 | 1208363553_451
MRPP2-OPT.18610 | TT_Task | EMU - Train 21 Preliminary Acceptance Test ; PTA Certification | 10/03/2032 | 04/05/2032 | nan | nan | 0 | TK_NotStart | 1208363553 | 451 | 1208363553_451
MRPP2-OPT.18700 | TT_Task | EMU - Train 22 Preliminary Acceptance Test ; PTA Certification | 05/05/2032 | 29/06/2032 | nan | nan | 0 | TK_NotStart | 1208363553 | 451 | 1208363553_451
MRPP2-OPT.18800 | TT_Task | EMU - Train 23 Preliminary Acceptance Test ; PTA Certification | 30/06/2032 | 24/08/2032 | nan | nan | 0 | TK_NotStart | 1208363553 | 451 | 1208363553_451
MRPP2-OPT.18900 | TT_Task | EMU - Train 24 Preliminary Acceptance Test ; PTA Certification | 25/08/2032 | 19/10/2032 | nan | nan | 0 | TK_NotStart | 1208363553 | 451 | 1208363553_451
MRPP2-OPT.19000 | TT_Task | EMU - Train 25 Preliminary Acceptance Test ; PTA Certification | 20/10/2032 | 14/12/2032 | nan | nan | 0 | TK_NotStart | 1208363553 | 451 | 1208363553_451
MRPP2-OPT.19090 | TT_Task | EMU - Train 26 Preliminary Acceptance Test ; PTA Certification | 15/12/2032 | 08/02/2033 | nan | nan | 0 | TK_NotStart | 1208363553 | 451 | 1208363553_451
MRPP2-OPT.19170 | TT_Task | EMU - Train 27 Preliminary Acceptance Test ; PTA Certification | 09/02/2033 | 05/04/2033 | nan | nan | 0 | TK_NotStart | 1208363553 | 451 | 1208363553_451
MRPP2-OPT.19240 | TT_Task | EMU - Train 28 Preliminary Acceptance Test ; PTA Certification | 06/04/2033 | 31/05/2033 | nan | nan | 0 | TK_NotStart | 1208363553 | 451 | 1208363553_451
MRPP2-OPT.19290 | TT_Task | EMU - Train 29 Preliminary Acceptance Test ; PTA Certification | 01/06/2033 | 26/07/2033 | nan | nan | 0 | TK_NotStart | 1208363553 | 451 | 1208363553_451
MRPP2-OPT.19340 | TT_Task | EMU - Train 30 Preliminary Acceptance Test ; PTA Certification | 27/07/2033 | 20/09/2033 | nan | nan | 64 | TK_NotStart | 1208363553 | 451 | 1208363553_451
MRPP2-OPT.14070 | TT_Task | EMU - Train 01 Provisional Acceptance Tests ; PTA Certification | 04/04/2029 | 18/05/2029 | nan | nan | 0 | TK_NotStart | 1208363553 | 458 | 1208363553_458
MRPP2-OPT.14500 | TT_Task | EMU - Train 02 Provisional Acceptance Tests ; PTA Certification | 21/05/2029 | 12/07/2029 | nan | nan | 0 | TK_NotStart | 1208363553 | 458 | 1208363553_458
MRPP2-OPT.15350 | TT_Task | EMU - Train 03 Provisional Acceptance Tests ; PTA Certification | 13/07/2029 | 04/09/2029 | nan | nan | 0 | TK_NotStart | 1208363553 | 458 | 1208363553_458
MRPP2-OPT.15810 | TT_Task | EMU - Train 04 Provisional Acceptance Tests ; PTA Certification | 05/09/2029 | 29/10/2029 | nan | nan | 0 | TK_NotStart | 1208363553 | 458 | 1208363553_458
MRPP2-OPT.16390 | TT_Task | EMU - Train 05 Provisional Acceptance Tests ; PTA Certification | 30/10/2029 | 09/01/2030 | nan | nan | 0 | TK_NotStart | 1208363553 | 458 | 1208363553_458
MRPP2-OPT.16610 | TT_Task | EMU - Train 06 Provisional Acceptance Tests ; PTA Certification | 10/01/2030 | 13/03/2030 | nan | nan | 0 | TK_NotStart | 1208363553 | 458 | 1208363553_458
MRPP2-OPT.16770 | TT_Task | EMU - Train 07 Provisional Acceptance Tests ; PTA Certification | 14/03/2030 | 15/05/2030 | nan | nan | 0 | TK_NotStart | 1208363553 | 458 | 1208363553_458
MRPP2-OPT.17140 | TT_Task | EMU - Train 08 Provisional Acceptance Tests ; PTA Certification | 16/05/2030 | 17/07/2030 | nan | nan | 0 | TK_NotStart | 1208363553 | 458 | 1208363553_458
MRPP2-OPT.17430 | TT_Task | EMU - Train 09 Provisional Acceptance Tests ; PTA Certification | 18/07/2030 | 18/09/2030 | nan | nan | 0 | TK_NotStart | 1208363553 | 458 | 1208363553_458
MRPP2-OPT.17720 | TT_Task | EMU - Train 10 Provisional Acceptance Tests ; PTA Certification | 19/09/2030 | 20/11/2030 | nan | nan | 0 | TK_NotStart | 1208363553 | 458 | 1208363553_458
MRPP2-OPT.17860 | TT_Task | EMU - Train 11 Provisional Acceptance Tests ; PTA Certification | 21/11/2030 | 22/01/2031 | nan | nan | 0 | TK_NotStart | 1208363553 | 458 | 1208363553_458
MRPP2-OPT.17960 | TT_Task | EMU - Train 12 Provisional Acceptance Tests ; PTA Certification | 23/01/2031 | 26/03/2031 | nan | nan | 0 | TK_NotStart | 1208363553 | 458 | 1208363553_458
MRPP2-OPT.18070 | TT_Task | EMU - Train 13 Provisional Acceptance Tests ; PTA Certification | 27/03/2031 | 28/05/2031 | nan | nan | 0 | TK_NotStart | 1208363553 | 458 | 1208363553_458
MRPP2-OPT.18170 | TT_Task | EMU - Train 14 Provisional Acceptance Tests ; PTA Certification | 29/05/2031 | 30/07/2031 | nan | nan | 0 | TK_NotStart | 1208363553 | 458 | 1208363553_458
MRPP2-OPT.18270 | TT_Task | EMU - Train 15 Provisional Acceptance Tests ; PTA Certification | 31/07/2031 | 01/10/2031 | nan | nan | 0 | TK_NotStart | 1208363553 | 458 | 1208363553_458
MRPP2-OPT.18370 | TT_Task | EMU - Train 16 Provisional Acceptance Tests ; PTA Certification | 02/10/2031 | 03/12/2031 | nan | nan | 0 | TK_NotStart | 1208363553 | 458 | 1208363553_458
MRPP2-OPT.18480 | TT_Task | EMU - Train 17 Provisional Acceptance Tests ; PTA Certification | 04/12/2031 | 04/02/2032 | nan | nan | 0 | TK_NotStart | 1208363553 | 458 | 1208363553_458
MRPP2-OPT.18580 | TT_Task | EMU - Train 18 Provisional Acceptance Tests ; PTA Certification | 05/02/2032 | 31/03/2032 | nan | nan | 0 | TK_NotStart | 1208363553 | 458 | 1208363553_458
MRPP2-OPT.18680 | TT_Task | EMU - Train 19 Provisional Acceptance Tests ; PTA Certification | 01/04/2032 | 26/05/2032 | nan | nan | 0 | TK_NotStart | 1208363553 | 458 | 1208363553_458
MRPP2-OPT.18780 | TT_Task | EMU - Train 20 Provisional Acceptance Tests ; PTA Certification | 27/05/2032 | 21/07/2032 | nan | nan | 0 | TK_NotStart | 1208363553 | 458 | 1208363553_458
MRPP2-OPT.18880 | TT_Task | EMU - Train 21 Provisional Acceptance Tests ; PTA Certification | 22/07/2032 | 15/09/2032 | nan | nan | 0 | TK_NotStart | 1208363553 | 458 | 1208363553_458
MRPP2-OPT.18980 | TT_Task | EMU - Train 22 Provisional Acceptance Tests ; PTA Certification | 16/09/2032 | 10/11/2032 | nan | nan | 0 | TK_NotStart | 1208363553 | 458 | 1208363553_458
MRPP2-OPT.19100 | TT_Task | EMU - Train 23 Provisional Acceptance Tests ; PTA Certification | 11/11/2032 | 12/01/2033 | nan | nan | 0 | TK_NotStart | 1208363553 | 458 | 1208363553_458
MRPP2-OPT.19180 | TT_Task | EMU - Train 24 Provisional Acceptance Tests ; PTA Certification | 13/01/2033 | 16/03/2033 | nan | nan | 0 | TK_NotStart | 1208363553 | 458 | 1208363553_458
MRPP2-OPT.19250 | TT_Task | EMU - Train 25 Provisional Acceptance Tests ; PTA Certification | 17/03/2033 | 18/05/2033 | nan | nan | 0 | TK_NotStart | 1208363553 | 458 | 1208363553_458
MRPP2-OPT.19300 | TT_Task | EMU - Train 26 Provisional Acceptance Tests ; PTA Certification | 19/05/2033 | 20/07/2033 | nan | nan | 0 | TK_NotStart | 1208363553 | 458 | 1208363553_458
MRPP2-OPT.19350 | TT_Task | EMU - Train 27 Provisional Acceptance Tests ; PTA Certification | 21/07/2033 | 21/09/2033 | nan | nan | 0 | TK_NotStart | 1208363553 | 458 | 1208363553_458
MRPP2-OPT.19370 | TT_Task | EMU - Train 28 Provisional Acceptance Tests ; PTA Certification | 22/09/2033 | 23/11/2033 | nan | nan | 0 | TK_NotStart | 1208363553 | 458 | 1208363553_458
MRPP2-OPT.19390 | TT_Task | EMU - Train 29 Provisional Acceptance Tests ; PTA Certification | 24/11/2033 | 25/01/2034 | nan | nan | 0 | TK_NotStart | 1208363553 | 458 | 1208363553_458
MRPP2-OPT.19410 | TT_Task | EMU - Train 30 Provisional Acceptance Tests ; PTA Certification | 26/01/2034 | 23/03/2034 | nan | nan | 0 | TK_NotStart | 1208363553 | 458 | 1208363553_458
MRPP2-OPT.15970 | TT_Task | EMU - Train 01 Final Acceptance Tests ; PTA Certification | 10/10/2029 | 22/11/2029 | nan | nan | 48 | TK_NotStart | 1208363553 | 450 | 1208363553_450
MRPP2-OPT.16440 | TT_Task | EMU - Train 02 Final Acceptance Tests ; PTA Certification | 03/12/2029 | 29/01/2030 | nan | nan | 48 | TK_NotStart | 1208363553 | 450 | 1208363553_450
MRPP2-OPT.16640 | TT_Task | EMU - Train 03 Final Acceptance Tests ; PTA Certification | 07/02/2030 | 22/03/2030 | nan | nan | 48 | TK_NotStart | 1208363553 | 450 | 1208363553_450
MRPP2-OPT.16840 | TT_Task | EMU - Train 04 Final Acceptance Tests ; PTA Certification | 02/04/2030 | 15/05/2030 | nan | nan | 80 | TK_NotStart | 1208363553 | 450 | 1208363553_450
MRPP2-OPT.17200 | TT_Task | EMU - Train 05 Final Acceptance Tests ; PTA Certification | 30/05/2030 | 12/07/2030 | nan | nan | 104 | TK_NotStart | 1208363553 | 450 | 1208363553_450
MRPP2-OPT.17500 | TT_Task | EMU - Train 06 Final Acceptance Tests ; PTA Certification | 01/08/2030 | 13/09/2030 | nan | nan | 104 | TK_NotStart | 1208363553 | 450 | 1208363553_450
MRPP2-OPT.17750 | TT_Task | EMU - Train 07 Final Acceptance Tests ; PTA Certification | 03/10/2030 | 15/11/2030 | nan | nan | 104 | TK_NotStart | 1208363553 | 450 | 1208363553_450
MRPP2-OPT.17880 | TT_Task | EMU - Train 08 Final Acceptance Tests ; PTA Certification | 05/12/2030 | 17/01/2031 | nan | nan | 104 | TK_NotStart | 1208363553 | 450 | 1208363553_450
MRPP2-OPT.17980 | TT_Task | EMU - Train 09 Final Acceptance Tests ; PTA Certification | 06/02/2031 | 21/03/2031 | nan | nan | 104 | TK_NotStart | 1208363553 | 450 | 1208363553_450
MRPP2-OPT.18090 | TT_Task | EMU - Train 10 Final Acceptance Tests ; PTA Certification | 10/04/2031 | 23/05/2031 | nan | nan | 104 | TK_NotStart | 1208363553 | 451 | 1208363553_451
MRPP2-OPT.18190 | TT_Task | EMU - Train 11 Final Acceptance Tests ; PTA Certification | 12/06/2031 | 25/07/2031 | nan | nan | 104 | TK_NotStart | 1208363553 | 451 | 1208363553_451
MRPP2-OPT.18290 | TT_Task | EMU - Train 12 Final Acceptance Tests ; PTA Certification | 14/08/2031 | 26/09/2031 | nan | nan | 104 | TK_NotStart | 1208363553 | 451 | 1208363553_451
MRPP2-OPT.18390 | TT_Task | EMU - Train 13 Final Acceptance Tests ; PTA Certification | 16/10/2031 | 28/11/2031 | nan | nan | 104 | TK_NotStart | 1208363553 | 451 | 1208363553_451
MRPP2-OPT.18490 | TT_Task | EMU - Train 14 Final Acceptance Tests ; PTA Certification | 18/12/2031 | 30/01/2032 | nan | nan | 104 | TK_NotStart | 1208363553 | 451 | 1208363553_451
MRPP2-OPT.18590 | TT_Task | EMU - Train 15 Final Acceptance Tests ; PTA Certification | 19/02/2032 | 02/04/2032 | nan | nan | 104 | TK_NotStart | 1208363553 | 451 | 1208363553_451
MRPP2-OPT.18710 | TT_Task | EMU - Train 16 Final Acceptance Tests ; PTA Certification | 22/04/2032 | 04/06/2032 | nan | nan | 104 | TK_NotStart | 1208363553 | 451 | 1208363553_451
MRPP2-OPT.18810 | TT_Task | EMU - Train 17 Final Acceptance Tests ; PTA Certification | 24/06/2032 | 06/08/2032 | nan | nan | 64 | TK_NotStart | 1208363553 | 451 | 1208363553_451
MRPP2-OPT.18910 | TT_Task | EMU - Train 18 Final Acceptance Tests ; PTA Certification | 19/08/2032 | 01/10/2032 | nan | nan | 64 | TK_NotStart | 1208363553 | 451 | 1208363553_451
MRPP2-OPT.19010 | TT_Task | EMU - Train 19 Final Acceptance Tests ; PTA Certification | 14/10/2032 | 26/11/2032 | nan | nan | 64 | TK_NotStart | 1208363553 | 451 | 1208363553_451
MRPP2-OPT.19110 | TT_Task | EMU - Train 20 Final Acceptance Tests ; PTA Certification | 09/12/2032 | 21/01/2033 | nan | nan | 64 | TK_NotStart | 1208363553 | 451 | 1208363553_451
MRPP2-OPT.19190 | TT_Task | EMU - Train 21 Final Acceptance Tests ; PTA Certification | 03/02/2033 | 18/03/2033 | nan | nan | 64 | TK_NotStart | 1208363553 | 451 | 1208363553_451
MRPP2-OPT.19260 | TT_Task | EMU - Train 22 Final Acceptance Tests ; PTA Certification | 31/03/2033 | 13/05/2033 | nan | nan | 104 | TK_NotStart | 1208363553 | 451 | 1208363553_451
MRPP2-OPT.19320 | TT_Task | EMU - Train 23 Final Acceptance Tests ; PTA Certification | 02/06/2033 | 15/07/2033 | nan | nan | 104 | TK_NotStart | 1208363553 | 451 | 1208363553_451
MRPP2-OPT.19360 | TT_Task | EMU - Train 24 Final Acceptance Tests ; PTA Certification | 04/08/2033 | 16/09/2033 | nan | nan | 104 | TK_NotStart | 1208363553 | 451 | 1208363553_451
MRPP2-OPT.19380 | TT_Task | EMU - Train 25 Final Acceptance Tests ; PTA Certification | 06/10/2033 | 18/11/2033 | nan | nan | 104 | TK_NotStart | 1208363553 | 451 | 1208363553_451
MRPP2-OPT.19400 | TT_Task | EMU - Train 26 Final Acceptance Tests ; PTA Certification | 08/12/2033 | 20/01/2034 | nan | nan | 104 | TK_NotStart | 1208363553 | 451 | 1208363553_451
MRPP2-OPT.19420 | TT_Task | EMU - Train 27 Final Acceptance Tests ; PTA Certification | 09/02/2034 | 24/03/2034 | nan | nan | 104 | TK_NotStart | 1208363553 | 451 | 1208363553_451
MRPP2-OPT.19430 | TT_Task | EMU - Train 28 Final Acceptance Tests ; PTA Certification | 13/04/2034 | 26/05/2034 | nan | nan | 104 | TK_NotStart | 1208363553 | 451 | 1208363553_451
MRPP2-OPT.19440 | TT_Task | EMU - Train 29 Final Acceptance Tests ; PTA Certification | 15/06/2034 | 28/07/2034 | nan | nan | 72 | TK_NotStart | 1208363553 | 451 | 1208363553_451
MRPP2-OPT.19450 | TT_Task | EMU - Train 30 Final Acceptance Tests ; PTA Certification | 11/08/2034 | 25/09/2034 | nan | nan | 32 | TK_NotStart | 1208363553 | 451 | 1208363553_451
MML3RSTDEL1000 | TT_Task | Submission of Insurance for transit of equipment | 10/09/2018 | 10/10/2018 | 10/09/2018 | 09/10/2018 | 0 | TK_Complete | -824745350 | 1 | -824745350_1
MML3RSTDEL1010 | TT_Task | Submission of Insurance for physical loss or damage to the Facilities | 25/09/2019 | 25/10/2019 | 10/09/2018 | 09/10/2018 | 0 | TK_Complete | -824745350 | 1 | -824745350_1
MML3RSTDEL1020 | TT_Task | Submission of Insurance for injury or death suffered by third party and loss of or damage to property | 10/09/2018 | 10/10/2018 | 10/09/2018 | 09/10/2018 | 0 | TK_Complete | -824745350 | 1 | -824745350_1
MML3RSTDEL1030 | TT_Task | Submission of Insurance for Worker | 25/09/2019 | 25/10/2019 | 10/09/2018 | 09/10/2018 | 0 | TK_Complete | -824745350 | 1 | -824745350_1
MML3RSTDEL1040 | TT_Task | Submission of Insurance for financial consequences of professional negligence | 25/09/2019 | 24/11/2019 | 10/09/2018 | 22/01/2019 | 0 | TK_Complete | -824745350 | 1 | -824745350_1
MML3RSTDEL1050 | TT_Task | Mobilization of Key Personnel and supporting staff at Site | 25/09/2019 | 01/10/2019 | 10/09/2018 | 16/09/2018 | 0 | TK_Complete | -824745350 | 2 | -824745350_2
MML3RSTDEL1060 | TT_Task | Mobilization of Design staff | 25/09/2019 | 01/10/2019 | 10/09/2018 | 16/09/2018 | 0 | TK_Complete | -824745350 | 2 | -824745350_2
MML3RSTDEL1070 | TT_Task | Submission of Design Section organisation Chart including Designer Mobilization chart | 25/09/2019 | 01/10/2019 | 10/09/2018 | 16/09/2018 | 0 | TK_Complete | -824745350 | 3 | -824745350_3
MML3RSTDEL1080 | TT_Task | Appointment of Contractor's representative | 25/09/2019 | 08/10/2019 | 10/09/2018 | 29/01/2019 | 0 | TK_Complete | -824745350 | 4 | -824745350_4
MML3RSTDEL1100 | TT_Task | Submission of Advance Bank Guarantee | 25/09/2019 | 22/10/2019 | 10/09/2018 | 07/10/2018 | 0 | TK_Complete | -824745350 | 5 | -824745350_5
MML3RSTDEL1110 | TT_Task | Submission of Performance Bank Guarantee | 25/09/2019 | 22/10/2019 | 10/09/2018 | 07/10/2018 | 0 | TK_Complete | -824745350 | 5 | -824745350_5
MML3RSTDEL1090 | TT_Task | Submission by Alstom: Organisation chart alongwith CV of Key Personnel | 25/09/2019 | 15/10/2019 | 10/09/2018 | 30/09/2018 | 0 | TK_Complete | -824745350 | 6 | -824745350_6
MML3RSTDEL1120 | TT_Task | Submission by Alstom: Design Consultant | 25/09/2019 | 08/11/2019 | 10/09/2018 | 24/10/2018 | 0 | TK_Complete | -824745350 | 7 | -824745350_7
MML3RSTDEL1130 | TT_Task | Submission by Alstom: Initial version of the Works Programme Draft | 25/08/2019 | 23/09/2019 | 10/09/2018 | 26/10/2018 | 0 | TK_Complete | -824745350 | 8 | -824745350_8
MML3RSTDEL1140 | TT_Task | Submission by Alstom: Detailed Works Programme | 25/08/2019 | 23/09/2019 | 14/03/2019 | 24/04/2019 | 0 | TK_Complete | -824745350 | 8 | -824745350_8
MML3RSTDEL1150 | TT_Task | Submission by Alstom: Design Submission Programme | 25/08/2019 | 23/09/2019 | 10/09/2018 | 26/10/2018 | 0 | TK_Complete | -824745350 | 7 | -824745350_7
MML3RSTDEL1160 | TT_Task | Submission by Alstom: Design, Procurement, Manufacturing and Manufacturing Testing Programme | 25/08/2019 | 23/10/2019 | 10/09/2018 | 14/01/2019 | 0 | TK_Complete | -824745350 | 9 | -824745350_9
MML3RSTDEL1170 | TT_Task | Submission by Alstom: Material Control Schedule | 25/08/2019 | 23/10/2019 | 10/09/2018 | 29/11/2018 | 0 | TK_Complete | -824745350 | 10 | -824745350_10
MML3RSTDEL1180 | TT_Task | Submission by Alstom: Manufacturing Testing Programme | 25/08/2019 | 23/10/2019 | 10/09/2018 | 27/11/2018 | 0 | TK_Complete | -824745350 | 9 | -824745350_9
MML3RSTDEL1190 | TT_Task | Submission by Alstom: Installation Programme - Preliminary | 25/08/2019 | 23/10/2019 | 10/09/2018 | 27/11/2018 | 0 | TK_Complete | -824745350 | 11 | -824745350_11
MML3RSTDEL1200 | TT_Task | Submission by Alstom: Testing ; Commissioning Programme | 25/08/2019 | 23/10/2019 | 10/09/2018 | 27/11/2018 | 0 | TK_Complete | -824745350 | 12 | -824745350_12
MML3RSTDEL1210 | TT_Task | Submission by Alstom: Training Programme | 25/08/2019 | 20/02/2020 | 10/09/2018 | 23/05/2019 | 0 | TK_Complete | -824745350 | 13 | -824745350_13
MML3RSTDEL1220 | TT_Task | Submission by Alstom: Three Month Rolling Programme (initial) | 25/08/2019 | 07/09/2019 | 10/09/2018 | 24/09/2018 | 0 | TK_Complete | -824745350 | 8 | -824745350_8
MML3RSTDEL1230 | TT_Task | Submission by Alstom: Five Week Rolling Programme (initial submission) | 25/08/2019 | 07/09/2019 | 10/09/2018 | 24/09/2018 | 0 | TK_Complete | -824745350 | 8 | -824745350_8
MML3RSTDEL1250 | TT_Task | Submission by Alstom: Physical Progress Report (baseline) | 25/08/2019 | 23/09/2019 | 10/09/2018 | 26/10/2018 | 0 | TK_Complete | -824745350 | 13 | -824745350_13
MML3RSTDEL1260 | TT_Task | Submission by Alstom: Contractor?s Project Plans | 25/08/2019 | 23/10/2019 | 10/09/2018 | 19/12/2018 | 0 | TK_Complete | -824745350 | 14 | -824745350_14
MML3RSTDEL1270 | TT_Task | Submission by Alstom: Project Management Plan | 25/08/2019 | 23/09/2019 | 10/09/2018 | 26/10/2018 | 0 | TK_Complete | -824745350 | 14 | -824745350_14
MML3RSTDEL1280 | TT_Task | Submission by Alstom: Interface Management Plan | 25/08/2019 | 23/09/2019 | 10/09/2018 | 26/10/2018 | 0 | TK_Complete | -824745350 | 15 | -824745350_15
MML3RSTDEL1290 | TT_Task | Submission by Alstom: Quality Plan and associated procedures | 25/08/2019 | 21/09/2019 | 10/09/2018 | 26/10/2018 | 0 | TK_Complete | -824745350 | 7 | -824745350_7
MML3RSTDEL1300 | TT_Task | Submission by Alstom: QMS documentation | 25/08/2019 | 21/09/2019 | 10/09/2018 | 26/10/2018 | 0 | TK_Complete | -824745350 | 16 | -824745350_16
MML3RSTDEL1310 | TT_Task | Submission by Alstom: Particulars of Site Supervision | 25/02/2022 | 25/02/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 17 | -824745350_17
MML3RSTDEL1320 | TT_Task | Submission by Alstom: System Safety Assurance Plan | 25/08/2019 | 23/10/2019 | 10/09/2018 | 16/11/2018 | 0 | TK_Complete | -824745350 | 18 | -824745350_18
MML3RSTDEL1330 | TT_Task | Submission by Alstom: Design safety case | 27/01/2020 | 27/01/2020 | 27/01/2020 | 27/01/2020 | 0 | TK_Complete | -824745350 | 19 | -824745350_19
MML3RSTDEL1340 | TT_Task | Submission by Alstom: Construction safety case | 27/01/2020 | 25/02/2020 | 27/01/2020 | 28/01/2020 | 0 | TK_Complete | -824745350 | 20 | -824745350_20
MML3RSTDEL1350 | TT_Task | Submission by Alstom: Test ; Commissioning safety case | 27/01/2020 | 28/01/2020 | 27/01/2020 | 28/01/2020 | 0 | TK_Complete | -824745350 | 12 | -824745350_12
MML3RSTDEL1360 | TT_Task | Submission by Alstom: Safety documentation Safety Forms required for opening of line | 02/09/2022 | 26/09/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 21 | -824745350_21
MML3RSTDEL1370 | TT_Task | Submission by Alstom: Construction Phase OHS ; E Documentation | 25/08/2019 | 23/09/2019 | 10/09/2018 | 07/01/2019 | 0 | TK_Complete | -824745350 | 22 | -824745350_22
MML3RSTDEL1380 | TT_Task | Submission by Alstom: Site Environmental Plan | 26/10/2018 | 26/10/2018 | 26/10/2018 | 26/10/2018 | 0 | TK_Complete | -824745350 | 23 | -824745350_23
MML3RSTDEL1390 | TT_Task | Submission by Alstom: Software Quality Assurance Plan | 25/08/2019 | 23/10/2019 | 10/09/2018 | 23/11/2018 | 0 | TK_Complete | -824745350 | 24 | -824745350_24
MML3RSTDEL1400 | TT_Task | Submission by Alstom: EMC Management Plan | 25/08/2019 | 23/10/2019 | 10/09/2018 | 29/11/2018 | 0 | TK_Complete | -824745350 | 25 | -824745350_25
MML3RSTDEL1410 | TT_Task | Submission by Alstom: Design Plan | 25/08/2019 | 23/10/2019 | 10/09/2018 | 09/11/2018 | 0 | TK_Complete | -824745350 | 7 | -824745350_7
MML3RSTDEL1420 | TT_Task | Submission by Alstom: Design Verification and Validation Plan | 25/08/2019 | 23/10/2019 | 10/09/2018 | 23/11/2018 | 0 | TK_Complete | -824745350 | 7 | -824745350_7
MML3RSTDEL1430 | TT_Task | Submission by Alstom: Procurement, Manufacturing and Testing Delivery Plan | 25/08/2019 | 23/10/2019 | 10/09/2018 | 27/11/2018 | 0 | TK_Complete | -824745350 | 9 | -824745350_9
MML3RSTDEL1440 | TT_Task | Submission by Alstom: Construction and Installation Management Plans | 10/09/2018 | 08/11/2018 | 10/09/2018 | 08/11/2018 | 0 | TK_Complete | -824745350 | 20 | -824745350_20
MML3RSTDEL1450 | TT_Task | Submission by Alstom: Inspection Testing ; Commissioning Plan | 25/08/2019 | 20/02/2020 | 10/09/2018 | 22/03/2019 | 0 | TK_Complete | -824745350 | 12 | -824745350_12
MML3RSTDEL1460 | TT_Task | Submission by Alstom: Operation ; Maintenance Manuals Plan | 18/11/2019 | 18/11/2019 | 18/11/2019 | 18/11/2019 | 0 | TK_Complete | -824745350 | 11 | -824745350_11
MML3RSTDEL1470 | TT_Task | Submission by Alstom: Training Plan | 16/10/2019 | 16/10/2019 | 16/10/2019 | 16/10/2019 | 0 | TK_Complete | -824745350 | 13 | -824745350_13
MML3RSTDEL1480 | TT_Task | Submission by Alstom: Spare Management Plan | 20/11/2019 | 20/11/2019 | 20/11/2019 | 20/11/2019 | 0 | TK_Complete | -824745350 | 26 | -824745350_26
MML3RSTDEL1490 | TT_Task | Submission by Alstom: Defects Liability Management Plans | 01/03/2023 | 20/03/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 27 | -824745350_27
MML3RSTDEL1500 | TT_Task | Submission by Alstom: Assistance of Maintenance Plan | 20/11/2019 | 20/11/2019 | 20/11/2019 | 20/11/2019 | 0 | TK_Complete | -824745350 | 28 | -824745350_28
MML3RSTDEL1510 | TT_Task | Submission by Alstom: Comprehensive Maintenance Plan | 18/11/2019 | 18/11/2019 | 18/11/2019 | 18/11/2019 | 0 | TK_Complete | -824745350 | 28 | -824745350_28
MML3RSTDEL1650 | TT_Task | Submission by Alstom: RAM Plan | 25/08/2019 | 04/12/2019 | 10/09/2018 | 27/11/2018 | 0 | TK_Complete | -824745350 | 29 | -824745350_29
MML3RSTDEL2450 | TT_Task | Submission by Alstom: Schedule of Hazard Analysis | 25/08/2019 | 01/01/2020 | 10/09/2018 | 25/10/2019 | 0 | TK_Complete | -824745350 | 30 | -824745350_30
MML3RSTDEL2750 | TT_Task | Submission by Alstom: Preliminary Fire Safety Design Report | 25/08/2019 | 21/10/2019 | 10/09/2018 | 29/11/2018 | 0 | TK_Complete | -824745350 | 31 | -824745350_31
MML3RSTDEL1930 | TT_Task | Review/ Comments from Project Manager: Initial version of the Works Programme Draft | 25/08/2019 | 07/09/2019 | 27/10/2018 | 06/11/2018 | 0 | TK_Complete | -824745350 | 32 | -824745350_32
MML3RSTDEL1940 | TT_Task | Review/ Comments from Project Manager: Detailed Works Programme | 25/08/2019 | 07/09/2019 | 25/04/2019 | 20/05/2019 | 0 | TK_Complete | -824745350 | 32 | -824745350_32
MML3RSTDEL1950 | TT_Task | Review/ Comments from Project Manager: Design Submission Programme | 25/08/2019 | 07/09/2019 | 27/10/2018 | 27/10/2018 | 0 | TK_Complete | -824745350 | 33 | -824745350_33
MML3RSTDEL1960 | TT_Task | Review/ Comments from Project Manager: Design, Procurement, Manufacturing and Manufacturing Testing Programme | 25/08/2019 | 07/09/2019 | 15/01/2019 | 11/02/2019 | 0 | TK_Complete | -824745350 | 34 | -824745350_34
MML3RSTDEL1970 | TT_Task | Review/ Comments from Project Manager: Material Control Schedule | 25/08/2019 | 07/09/2019 | 30/11/2018 | 12/12/2018 | 0 | TK_Complete | -824745350 | 35 | -824745350_35
MML3RSTDEL1980 | TT_Task | Review/ Comments from Project Manager: Manufacturing Testing Programme | 25/08/2019 | 07/09/2019 | 29/11/2018 | 11/12/2018 | 0 | TK_Complete | -824745350 | 34 | -824745350_34
MML3RSTDEL1990 | TT_Task | Review/ Comments from Project Manager: Installation Programme - Preliminary | 28/11/2018 | 11/12/2018 | 28/11/2018 | 10/12/2018 | 0 | TK_Complete | -824745350 | 36 | -824745350_36
MML3RSTDEL2000 | TT_Task | Review/ Comments from Project Manager: Testing ; Commissioning Programme | 25/08/2019 | 07/09/2019 | 28/11/2018 | 28/12/2018 | 0 | TK_Complete | -824745350 | 37 | -824745350_37
MML3RSTDEL2010 | TT_Task | Review/ Comments from Project Manager: Training Programme | 25/08/2019 | 07/09/2019 | 24/05/2019 | 04/06/2019 | 0 | TK_Complete | -824745350 | 38 | -824745350_38
MML3RSTDEL2020 | TT_Task | Review/ Comments from Project Manager: Three Month Rolling Programme (initial) | 25/08/2019 | 07/09/2019 | 25/09/2018 | 03/10/2018 | 0 | TK_Complete | -824745350 | 39 | -824745350_39
MML3RSTDEL2030 | TT_Task | Review/ Comments from Project Manager: Five Week Rolling Programme (initial submission) | 08/09/2019 | 21/09/2019 | 25/09/2018 | 03/10/2018 | 0 | TK_Complete | -824745350 | 39 | -824745350_39
MML3RSTDEL2050 | TT_Task | Review/ Comments from Project Manager: Physical Progress Report (baseline) | 25/08/2019 | 07/09/2019 | 27/10/2018 | 06/11/2019 | 0 | TK_Complete | -824745350 | 40 | -824745350_40
MML3RSTDEL2060 | TT_Task | Review/ Comments from Project Manager: Contractor?s Project Plans | 25/08/2019 | 07/09/2019 | 20/12/2018 | 14/01/2019 | 0 | TK_Complete | -824745350 | 33 | -824745350_33
MML3RSTDEL2070 | TT_Task | Review/ Comments from Project Manager: Project Management Plan | 25/08/2019 | 07/09/2019 | 27/10/2018 | 06/11/2018 | 0 | TK_Complete | -824745350 | 33 | -824745350_33
MML3RSTDEL2080 | TT_Task | Review/ Comments from Project Manager: Interface Management Plan | 25/08/2019 | 07/09/2019 | 27/10/2018 | 03/11/2018 | 0 | TK_Complete | -824745350 | 33 | -824745350_33
MML3RSTDEL2090 | TT_Task | Review/ Comments from Project Manager: Quality Plan and associated procedures | 25/08/2019 | 07/09/2019 | 27/10/2018 | 06/11/2018 | 0 | TK_Complete | -824745350 | 33 | -824745350_33
MML3RSTDEL2100 | TT_Task | Review/ Comments from Project Manager: Particulars of Site Supervision | 25/02/2022 | 10/03/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 41 | -824745350_41
MML3RSTDEL2110 | TT_Task | Review/ Comments from Project Manager: System Safety Assurance Plan | 25/08/2019 | 07/09/2019 | 17/11/2018 | 05/12/2018 | 0 | TK_Complete | -824745350 | 42 | -824745350_42
MML3RSTDEL2120 | TT_Task | Review/ Comments from Project Manager: Design safety case | 11/03/2023 | 20/03/2023 | 27/01/2020 | 17/02/2020 | 0 | TK_Complete | -824745350 | 42 | -824745350_42
MML3RSTDEL2130 | TT_Task | Review/ Comments from Project Manager: Construction safety case | 12/07/2021 | 25/07/2021 | 28/01/2020 | 17/02/2020 | 0 | TK_Complete | -824745350 | 42 | -824745350_42
MML3RSTDEL2140 | TT_Task | Review/ Comments from Project Manager: Test ; Commissioning safety case | 12/07/2021 | 25/07/2021 | 28/01/2020 | 17/02/2020 | 0 | TK_Complete | -824745350 | 37 | -824745350_37
MML3RSTDEL2150 | TT_Task | Review/ Comments from Project Manager: Safety documentation Safety Forms required for opening of line | 27/09/2022 | 10/10/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 21 | -824745350_21
MML3RSTDEL2160 | TT_Task | Review/ Comments from Project Manager: Construction Phase OHS ; E Documentation | 25/08/2019 | 07/09/2019 | 08/01/2019 | 04/02/2019 | 0 | TK_Complete | -824745350 | 43 | -824745350_43
MML3RSTDEL2170 | TT_Task | Review/ Comments from Project Manager: Site Environmental Plan | 27/10/2018 | 17/11/2018 | 27/10/2018 | 17/11/2018 | 0 | TK_Complete | -824745350 | 33 | -824745350_33
MML3RSTDEL2180 | TT_Task | Review/ Comments from Project Manager: Software Quality Assurance Plan | 25/08/2019 | 07/09/2019 | 24/11/2018 | 26/12/2018 | 0 | TK_Complete | -824745350 | 33 | -824745350_33
MML3RSTDEL2190 | TT_Task | Review/ Comments from Project Manager: EMC Management Plan | 30/11/2018 | 13/12/2018 | 30/11/2018 | 19/12/2018 | 0 | TK_Complete | -824745350 | 44 | -824745350_44
MML3RSTDEL2200 | TT_Task | Review/ Comments from Project Manager: Design Plan | 25/08/2019 | 07/09/2019 | 10/11/2018 | 15/11/2018 | 0 | TK_Complete | -824745350 | 33 | -824745350_33
MML3RSTDEL2210 | TT_Task | Review/ Comments from Project Manager: Design Verification and Validation Plan | 25/08/2019 | 07/09/2019 | 24/11/2018 | 06/12/2018 | 0 | TK_Complete | -824745350 | 33 | -824745350_33
MML3RSTDEL2220 | TT_Task | Review/ Comments from Project Manager: Procurement, Manufacturing and Testing Delivery Plan | 25/08/2019 | 07/09/2019 | 28/11/2018 | 10/12/2018 | 0 | TK_Complete | -824745350 | 34 | -824745350_34
MML3RSTDEL2230 | TT_Task | Review/ Comments from Project Manager: Construction and Installation Management Plans | 09/11/2018 | 22/11/2018 | 09/11/2018 | 22/11/2018 | 0 | TK_Complete | -824745350 | 36 | -824745350_36
MML3RSTDEL2240 | TT_Task | Review/ Comments from Project Manager: Inspection Testing ; Commissioning Plan | 25/08/2019 | 07/09/2019 | 23/03/2019 | 05/04/2019 | 0 | TK_Complete | -824745350 | 37 | -824745350_37
MML3RSTDEL2250 | TT_Task | Review/ Comments from Project Manager: Operation ; Maintenance Manuals Plan | 16/11/2019 | 16/11/2019 | 19/11/2019 | 03/12/2019 | 0 | TK_Complete | -824745350 | 45 | -824745350_45
MML3RSTDEL2260 | TT_Task | Review/ Comments from Project Manager: Training Plan | 17/10/2019 | 02/11/2019 | 17/10/2019 | 02/11/2019 | 0 | TK_Complete | -824745350 | 38 | -824745350_38
MML3RSTDEL2270 | TT_Task | Review/ Comments from Project Manager: Spare Management Plan | 21/11/2019 | 04/12/2019 | 21/11/2019 | 04/12/2019 | 0 | TK_Complete | -824745350 | 33 | -824745350_33
MML3RSTDEL2280 | TT_Task | Review/ Comments from Project Manager: Defects Liability Management Plans | 21/03/2023 | 03/04/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 27 | -824745350_27
MML3RSTDEL2290 | TT_Task | Review/ Comments from Project Manager: Assistance of Maintenance Plan | 12/07/2021 | 25/07/2021 | 21/11/2019 | 04/12/2019 | 0 | TK_Complete | -824745350 | 45 | -824745350_45
MML3RSTDEL2300 | TT_Task | Review/ Comments from Project Manager: Comprehensive Maintenance Plan | 12/07/2021 | 25/07/2021 | 19/11/2019 | 04/12/2019 | 0 | TK_Complete | -824745350 | 45 | -824745350_45
MML3RSTDEL2310 | TT_Task | Review/ Comments from Project Manager: QMS documentation | 22/09/2019 | 05/10/2019 | 27/10/2018 | 06/11/2018 | 0 | TK_Complete | -824745350 | 32 | -824745350_32
MML3RSTDEL2320 | TT_Task | Review/ Comments from Project Manager: Organisation chart alongwith CV of Key Personnel | 25/09/2019 | 08/10/2019 | 01/10/2018 | 14/10/2018 | 0 | TK_Complete | -824745350 | 6 | -824745350_6
MML3RSTDEL2330 | TT_Task | Review/ Comments from Project Manager: Design Consultant | 25/10/2018 | 07/11/2018 | 25/10/2018 | 07/11/2018 | 0 | TK_Complete | -824745350 | 33 | -824745350_33
MML3RSTSPA6930 | TT_Task | Review/ Comments from Project Manager:RAM Plan | 25/08/2019 | 07/09/2019 | 28/11/2018 | 10/12/2018 | 0 | TK_Complete | -824745350 | 46 | -824745350_46
MML3RSTSPA6940 | TT_Task | Review/ Comments from Project Manager:Schedule of Hazard Analysis | 25/08/2019 | 07/09/2019 | 26/10/2018 | 27/10/2018 | 0 | TK_Complete | -824745350 | 47 | -824745350_47
MML3RSTSPA6950 | TT_Task | Review/ Comments from Project Manager: Preliminary Fire Safety Design Report | 25/08/2019 | 07/09/2019 | 30/11/2018 | 07/01/2019 | 0 | TK_Complete | -824745350 | 48 | -824745350_48
MML3RSTDEL2340 | TT_Task | Resubmission by Alstom: Initial version of the Works Programme Draft | 25/08/2019 | 07/09/2019 | 07/11/2018 | 14/01/2019 | 0 | TK_Complete | -824745350 | 8 | -824745350_8
MML3RSTDEL2350 | TT_Task | Resubmission by Alstom: Detailed Works Programme | 25/08/2019 | 07/09/2019 | 21/05/2019 | 10/06/2019 | 0 | TK_Complete | -824745350 | 49 | -824745350_49
MML3RSTDEL2360 | TT_Task | Resubmission by Alstom: Design Submission Programme | 08/09/2019 | 21/09/2019 | 28/10/2018 | 06/11/2018 | 0 | TK_Complete | -824745350 | 50 | -824745350_50
MML3RSTDEL2370 | TT_Task | Resubmission by Alstom: Design, Procurement, Manufacturing and Manufacturing Testing Programme | 25/08/2019 | 07/09/2019 | 12/02/2019 | 22/02/2019 | 0 | TK_Complete | -824745350 | 9 | -824745350_9
MML3RSTDEL2380 | TT_Task | Resubmission by Alstom: Material Control Schedule | 25/08/2019 | 07/09/2019 | 13/12/2018 | 04/02/2019 | 0 | TK_Complete | -824745350 | 10 | -824745350_10
MML3RSTDEL2390 | TT_Task | Resubmission by Alstom: Manufacturing Testing Programme | 25/08/2019 | 07/09/2019 | 12/12/2018 | 14/01/2019 | 0 | TK_Complete | -824745350 | 9 | -824745350_9
MML3RSTDEL2400 | TT_Task | Resubmission by Alstom: Installation Programme - Preliminary | 25/08/2019 | 07/09/2019 | 11/12/2018 | 14/01/2019 | 0 | TK_Complete | -824745350 | 11 | -824745350_11
MML3RSTDEL2410 | TT_Task | Resubmission by Alstom: Testing ; Commissioning Programme | 25/08/2019 | 07/09/2019 | 29/12/2018 | 14/01/2019 | 0 | TK_Complete | -824745350 | 49 | -824745350_49
MML3RSTDEL2420 | TT_Task | Resubmission by Alstom: Training Programme | 25/08/2019 | 07/09/2019 | 05/06/2019 | 19/06/2019 | 0 | TK_Complete | -824745350 | 13 | -824745350_13
MML3RSTDEL2430 | TT_Task | Resubmission by Alstom: Three Month Rolling Programme (initial) | 25/08/2019 | 07/09/2019 | 04/10/2018 | 29/11/2018 | 0 | TK_Complete | -824745350 | 8 | -824745350_8
MML3RSTDEL2440 | TT_Task | Resubmission by Alstom: Five Week Rolling Programme (initial submission) | 25/08/2019 | 07/09/2019 | 04/10/2018 | 29/11/2018 | 0 | TK_Complete | -824745350 | 8 | -824745350_8
MML3RSTDEL2460 | TT_Task | Resubmission by Alstom: Physical Progress Report (baseline) | 25/08/2019 | 07/09/2019 | 07/11/2018 | 10/04/2019 | 0 | TK_Complete | -824745350 | 13 | -824745350_13
MML3RSTDEL2470 | TT_Task | Resubmission by Alstom: Contractor?s Project Plans | 25/08/2019 | 07/09/2019 | 15/01/2019 | 04/02/2019 | 0 | TK_Complete | -824745350 | 14 | -824745350_14
MML3RSTDEL2480 | TT_Task | Resubmission by Alstom: Project Management Plan | 25/08/2019 | 07/09/2019 | 07/11/2018 | 13/12/2018 | 0 | TK_Complete | -824745350 | 14 | -824745350_14
MML3RSTDEL2490 | TT_Task | Resubmission by Alstom: Interface Management Plan | 25/08/2019 | 07/09/2019 | 04/11/2018 | 19/12/2018 | 0 | TK_Complete | -824745350 | 15 | -824745350_15
MML3RSTDEL2500 | TT_Task | Resubmission by Alstom: Quality Plan and associated procedures | 25/08/2019 | 07/09/2019 | 07/11/2018 | 19/12/2018 | 0 | TK_Complete | -824745350 | 49 | -824745350_49
MML3RSTDEL2510 | TT_Task | Resubmission by Alstom: Particulars of Site Supervision | 11/03/2022 | 24/03/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 17 | -824745350_17
MML3RSTDEL2520 | TT_Task | Resubmission by Alstom: System Safety Assurance Plan | 25/08/2019 | 07/09/2019 | 06/12/2018 | 21/12/2018 | 0 | TK_Complete | -824745350 | 18 | -824745350_18
MML3RSTDEL2530 | TT_Task | Resubmission by Alstom: Design safety case | 21/03/2023 | 30/03/2023 | 18/02/2020 | 20/04/2021 | 0 | TK_Complete | -824745350 | 50 | -824745350_50
MML3RSTDEL2540 | TT_Task | Resubmission by Alstom: Construction safety case | 26/07/2021 | 08/08/2021 | 18/02/2020 | 12/08/2020 | 0 | TK_Complete | -824745350 | 20 | -824745350_20
MML3RSTDEL2550 | TT_Task | Resubmission by Alstom: Test ; Commissioning safety case | 26/07/2021 | 08/08/2021 | 18/02/2020 | 12/08/2020 | 0 | TK_Complete | -824745350 | 49 | -824745350_49
MML3RSTDEL2560 | TT_Task | Resubmission by Alstom: Safety documentation Safety Forms required for opening of line | 11/10/2022 | 24/10/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 21 | -824745350_21
MML3RSTDEL2570 | TT_Task | Resubmission by Alstom: Construction Phase OHS ; E Documentation | 25/08/2019 | 07/09/2019 | 05/02/2019 | 18/02/2019 | 0 | TK_Complete | -824745350 | 22 | -824745350_22
MML3RSTDEL2580 | TT_Task | Resubmission by Alstom: Site Environmental Plan | 18/11/2018 | 09/05/2019 | 18/11/2018 | 09/05/2019 | 0 | TK_Complete | -824745350 | 23 | -824745350_23
MML3RSTDEL2590 | TT_Task | Resubmission by Alstom: Software Quality Assurance Plan | 25/08/2019 | 07/09/2019 | 27/12/2018 | 06/05/2019 | 0 | TK_Complete | -824745350 | 24 | -824745350_24
MML3RSTDEL2600 | TT_Task | Resubmission by Alstom: EMC Management Plan | 20/12/2018 | 02/01/2019 | 20/12/2018 | 03/08/2019 | 0 | TK_Complete | -824745350 | 25 | -824745350_25
MML3RSTDEL2610 | TT_Task | Resubmission by Alstom: Design Plan | 25/08/2019 | 07/09/2019 | 16/11/2018 | 30/01/2019 | 0 | TK_Complete | -824745350 | 50 | -824745350_50
MML3RSTDEL2620 | TT_Task | Resubmission by Alstom: Design Verification and Validation Plan | 25/08/2019 | 07/09/2019 | 07/12/2018 | 29/01/2019 | 0 | TK_Complete | -824745350 | 50 | -824745350_50
MML3RSTDEL2630 | TT_Task | Resubmission by Alstom: Procurement, Manufacturing and Testing Delivery Plan | 25/08/2019 | 07/09/2019 | 11/12/2018 | 19/12/2018 | 0 | TK_Complete | -824745350 | 9 | -824745350_9
MML3RSTDEL2640 | TT_Task | Resubmission by Alstom: Construction and Installation Management Plans | 23/11/2018 | 06/12/2018 | 23/11/2018 | 06/12/2018 | 0 | TK_Complete | -824745350 | 20 | -824745350_20
MML3RSTDEL2650 | TT_Task | Resubmission by Alstom: Inspection Testing ; Commissioning Plan | 25/08/2019 | 07/09/2019 | 06/04/2019 | 29/04/2019 | 0 | TK_Complete | -824745350 | 12 | -824745350_12
MML3RSTDEL2660 | TT_Task | Resubmission by Alstom: Operation ; Maintenance Manuals Plan | 12/07/2021 | 25/07/2021 | 04/12/2019 | 08/05/2020 | 0 | TK_Complete | -824745350 | 49 | -824745350_49
MML3RSTDEL2670 | TT_Task | Resubmission by Alstom: Training Plan | 03/11/2019 | 20/11/2019 | 03/11/2019 | 20/11/2019 | 0 | TK_Complete | -824745350 | 13 | -824745350_13
MML3RSTDEL2680 | TT_Task | Resubmission by Alstom: Spare Management Plan | 05/12/2019 | 04/02/2020 | 05/12/2019 | 04/02/2020 | 0 | TK_Complete | -824745350 | 26 | -824745350_26
MML3RSTDEL2690 | TT_Task | Resubmission by Alstom: Defects Liability Management Plans | 04/04/2023 | 17/04/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 27 | -824745350_27
MML3RSTDEL2700 | TT_Task | Resubmission by Alstom: Assistance of Maintenance Plan | 26/07/2021 | 08/08/2021 | 05/12/2019 | 30/04/2020 | 0 | TK_Complete | -824745350 | 28 | -824745350_28
MML3RSTDEL2710 | TT_Task | Resubmission by Alstom: Comprehensive Maintenance Plan | 26/07/2021 | 08/08/2021 | 05/12/2019 | 30/04/2020 | 0 | TK_Complete | -824745350 | 28 | -824745350_28
MML3RSTDEL2720 | TT_Task | Resubmission by Alstom: QMS documentation | 25/08/2019 | 07/09/2019 | 07/11/2018 | 19/12/2018 | 0 | TK_Complete | -824745350 | 16 | -824745350_16
MML3RSTDEL2730 | TT_Task | Resubmission by Alstom: Organisation chart alongwith CV of Key Personnel | 15/10/2018 | 28/10/2018 | 15/10/2018 | 28/10/2018 | 0 | TK_Complete | -824745350 | 6 | -824745350_6
MML3RSTDEL2740 | TT_Task | Resubmission by Alstom: Design Consultant | 08/11/2018 | 21/11/2018 | 08/11/2018 | 21/11/2018 | 0 | TK_Complete | -824745350 | 50 | -824745350_50
MML3RSTSPA6960 | TT_Task | Resubmission by Alstom: RAM Plan | 25/08/2019 | 07/09/2019 | 11/12/2018 | 21/12/2018 | 0 | TK_Complete | -824745350 | 29 | -824745350_29
MML3RSTSPA6970 | TT_Task | Resubmission by Alstom: Schedule of Hazard Analysis | 25/08/2019 | 07/09/2019 | 28/10/2018 | 06/11/2018 | 0 | TK_Complete | -824745350 | 30 | -824745350_30
MML3RSTSPA6980 | TT_Task | Resubmission by Alstom: Preliminary Fire Safety Design Report | 25/08/2019 | 07/09/2019 | 08/01/2019 | 17/01/2019 | 0 | TK_Complete | -824745350 | 31 | -824745350_31
MML3RSTDEL1520 | TT_Task | NONO/ NOWC from Project Manager: NONO of Key Personnel Auxiliary Converter | 25/09/2019 | 08/10/2019 | 29/10/2018 | 29/11/2018 | 0 | TK_Complete | -824745350 | 51 | -824745350_51
MML3RSTDEL1530 | TT_Task | NONO/ NOWC from Project Manager: Design Consultant | 22/11/2018 | 05/12/2018 | 22/11/2018 | 05/12/2018 | 0 | TK_Complete | -824745350 | 52 | -824745350_52
MML3RSTDEL1540 | TT_Task | NONO/ NOWC from Project Manager: Initial version of the Works Programme Draft | 25/08/2019 | 07/09/2019 | 15/01/2019 | 13/03/2019 | 0 | TK_Complete | -824745350 | 52 | -824745350_52
MML3RSTDEL1550 | TT_Task | NONO/ NOWC from Project Manager: Detailed Works Programme | 25/08/2019 | 07/09/2019 | 11/06/2019 | 23/08/2019 | 0 | TK_Complete | -824745350 | 52 | -824745350_52
MML3RSTDEL1560 | TT_Task | NONO/ NOWC from Project Manager: Design Submission Programme | 25/08/2019 | 07/09/2019 | 07/11/2018 | 14/06/2019 | 0 | TK_Complete | -824745350 | 52 | -824745350_52
MML3RSTDEL1570 | TT_Task | NONO/ NOWC from Project Manager: Design, Procurement, Manufacturing and Manufacturing Testing Programme | 25/08/2019 | 07/09/2019 | 12/02/2019 | 22/02/2019 | 0 | TK_Complete | -824745350 | 53 | -824745350_53
MML3RSTDEL1580 | TT_Task | NONO/ NOWC from Project Manager: Material Control Schedule | 25/08/2019 | 07/09/2019 | 05/02/2019 | 21/07/2019 | 0 | TK_Complete | -824745350 | 35 | -824745350_35
MML3RSTDEL1590 | TT_Task | NONO/ NOWC from Project Manager: Manufacturing Testing Programme | 25/08/2019 | 07/09/2019 | 05/02/2019 | 21/07/2019 | 0 | TK_Complete | -824745350 | 53 | -824745350_53
MML3RSTDEL1600 | TT_Task | NONO/ NOWC from Project Manager: Installation Programme - Preliminary | 25/08/2019 | 07/09/2019 | 15/01/2019 | 10/03/2019 | 0 | TK_Complete | -824745350 | 52 | -824745350_52
MML3RSTDEL1610 | TT_Task | NONO/ NOWC from Project Manager: Testing ; Commissioning Programme | 25/08/2019 | 07/09/2019 | 15/01/2019 | 22/08/2019 | 0 | TK_Complete | -824745350 | 53 | -824745350_53
MML3RSTDEL1620 | TT_Task | NONO/ NOWC from Project Manager: Training Programme | 25/08/2019 | 07/09/2019 | 20/06/2019 | 19/08/2019 | 0 | TK_Complete | -824745350 | 54 | -824745350_54
MML3RSTDEL1630 | TT_Task | NONO/ NOWC from Project Manager: Three Month Rolling Programme (initial) | 25/08/2019 | 07/09/2019 | 30/11/2018 | 07/05/2019 | 0 | TK_Complete | -824745350 | 39 | -824745350_39
MML3RSTDEL1640 | TT_Task | NONO/ NOWC from Project Manager: Five Week Rolling Programme (initial submission) | 25/08/2019 | 07/09/2019 | 30/11/2018 | 20/05/2019 | 0 | TK_Complete | -824745350 | 39 | -824745350_39
MML3RSTDEL1660 | TT_Task | NONO/ NOWC from Project Manager: Physical Progress Report (baseline) | 25/08/2019 | 07/09/2019 | 11/04/2019 | 13/08/2019 | 0 | TK_Complete | -824745350 | 40 | -824745350_40
MML3RSTDEL1670 | TT_Task | NONO/ NOWC from Project Manager: Contractor?s Project Plans | 25/08/2019 | 07/09/2019 | 05/02/2019 | 15/03/2019 | 0 | TK_Complete | -824745350 | 52 | -824745350_52
MML3RSTDEL1680 | TT_Task | NONO/ NOWC from Project Manager: Project Management Plan | 25/08/2019 | 07/09/2019 | 14/12/2018 | 03/05/2019 | 0 | TK_Complete | -824745350 | 52 | -824745350_52
MML3RSTDEL1690 | TT_Task | NONO/ NOWC from Project Manager: Interface Management Plan | 25/08/2019 | 07/09/2019 | 20/12/2018 | 20/04/2019 | 0 | TK_Complete | -824745350 | 52 | -824745350_52
MML3RSTDEL1700 | TT_Task | NONO/ NOWC from Project Manager: Quality Plan and associated procedures | 25/08/2019 | 07/09/2019 | 20/12/2018 | 23/04/2019 | 0 | TK_Complete | -824745350 | 52 | -824745350_52
MML3RSTDEL1710 | TT_Task | NONO/ NOWC from Project Manager: Particulars of Site Supervision | 25/03/2022 | 07/04/2022 | nan | nan | 1160 | TK_NotStart | -824745350 | 41 | -824745350_41
MML3RSTDEL1720 | TT_Task | NONO/ NOWC from Project Manager: System Safety Assurance Plan | 25/08/2019 | 07/09/2019 | 22/12/2018 | 04/04/2019 | 0 | TK_Complete | -824745350 | 55 | -824745350_55
MML3RSTDEL1730 | TT_Task | NONO/ NOWC from Project Manager: Design safety case | 25/02/2022 | 25/02/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 55 | -824745350_55
MML3RSTDEL1740 | TT_Task | NONO/ NOWC from Project Manager: Construction safety case | 13/08/2020 | 07/09/2020 | 13/08/2020 | 07/09/2020 | 0 | TK_Complete | -824745350 | 55 | -824745350_55
MML3RSTDEL1750 | TT_Task | NONO/ NOWC from Project Manager: Test ; Commissioning safety case | 13/08/2020 | 07/09/2020 | 13/08/2020 | 07/09/2020 | 0 | TK_Complete | -824745350 | 53 | -824745350_53
MML3RSTDEL1760 | TT_Task | NONO/ NOWC from Project Manager: Safety documentation Safety Forms required for opening of line | 25/10/2022 | 07/11/2022 | nan | nan | 600 | TK_NotStart | -824745350 | 21 | -824745350_21
MML3RSTDEL1770 | TT_Task | NONO/ NOWC from Project Manager: Construction Phase OHS ; E Documentation | 25/08/2019 | 07/09/2019 | 19/02/2019 | 02/04/2019 | 0 | TK_Complete | -824745350 | 43 | -824745350_43
MML3RSTDEL1780 | TT_Task | NONO/ NOWC from Project Manager: Site Environmental Plan | 10/05/2019 | 23/05/2019 | 10/05/2019 | 23/05/2019 | 0 | TK_Complete | -824745350 | 52 | -824745350_52
MML3RSTDEL1790 | TT_Task | NONO/ NOWC from Project Manager: Software Quality Assurance Plan | 25/08/2019 | 07/09/2019 | 08/05/2019 | 07/08/2019 | 0 | TK_Complete | -824745350 | 52 | -824745350_52
MML3RSTDEL1800 | TT_Task | NONO/ NOWC from Project Manager: EMC Management Plan | 05/08/2019 | 18/08/2019 | 05/08/2019 | 07/08/2019 | 0 | TK_Complete | -824745350 | 44 | -824745350_44
MML3RSTDEL1810 | TT_Task | NONO/ NOWC from Project Manager: Design Plan | 25/08/2019 | 07/09/2019 | 31/01/2019 | 20/05/2019 | 0 | TK_Complete | -824745350 | 52 | -824745350_52
MML3RSTDEL1820 | TT_Task | NONO/ NOWC from Project Manager: Design Verification and Validation Plan | 25/08/2019 | 07/09/2019 | 30/01/2019 | 08/04/2019 | 0 | TK_Complete | -824745350 | 55 | -824745350_55
MML3RSTDEL1830 | TT_Task | NONO/ NOWC from Project Manager: Procurement, Manufacturing and Testing Delivery Plan | 25/08/2019 | 07/09/2019 | 20/12/2018 | 04/05/2019 | 0 | TK_Complete | -824745350 | 53 | -824745350_53
MML3RSTDEL1840 | TT_Task | NONO/ NOWC from Project Manager: Construction and Installation Management Plans | 07/12/2018 | 20/12/2018 | 07/12/2018 | 20/12/2018 | 0 | TK_Complete | -824745350 | 52 | -824745350_52
MML3RSTDEL1850 | TT_Task | NONO/ NOWC from Project Manager: Inspection Testing ; Commissioning Plan | 19/08/2019 | 07/12/2019 | 30/04/2019 | 19/08/2019 | 0 | TK_Complete | -824745350 | 53 | -824745350_53
MML3RSTDEL1860 | TT_Task | NONO/ NOWC from Project Manager: Operation ; Maintenance Manuals Plan | 12/07/2021 | 25/07/2021 | 09/05/2020 | 13/05/2020 | 0 | TK_Complete | -824745350 | 56 | -824745350_56
MML3RSTDEL1870 | TT_Task | NONO/ NOWC from Project Manager: Training Plan | 20/11/2019 | 20/11/2019 | 20/11/2019 | 20/11/2019 | 0 | TK_Complete | -824745350 | 54 | -824745350_54
MML3RSTDEL1880 | TT_Task | NONO/ NOWC from Project Manager: Spare Management Plan | 05/02/2020 | 18/02/2020 | 05/02/2020 | 18/02/2020 | 0 | TK_Complete | -824745350 | 52 | -824745350_52
MML3RSTDEL1890 | TT_Task | NONO/ NOWC from Project Manager: Defects Liability Management Plans | 18/04/2023 | 01/05/2023 | nan | nan | 2376 | TK_NotStart | -824745350 | 27 | -824745350_27
MML3RSTDEL1900 | TT_Task | NONO/ NOWC from Project Manager: Assistance of Maintenance Plan | 12/07/2021 | 25/07/2021 | 01/05/2020 | 09/05/2020 | 0 | TK_Complete | -824745350 | 57 | -824745350_57
MML3RSTDEL1910 | TT_Task | NONO/ NOWC from Project Manager: Comprehensive Maintenance Plan | 12/07/2021 | 25/07/2021 | 01/05/2020 | 09/05/2020 | 0 | TK_Complete | -824745350 | 57 | -824745350_57
MML3RSTDEL1920 | TT_Task | NONO/ NOWC from Project Manager: QMS documentation | 08/09/2019 | 21/09/2019 | 20/12/2018 | 20/08/2019 | 0 | TK_Complete | -824745350 | 56 | -824745350_56
MML3RSTSPA6990 | TT_Task | NONO/ NOWC from Project Manager: RAM Plan | 25/08/2019 | 07/09/2019 | 22/12/2018 | 18/02/2019 | 0 | TK_Complete | -824745350 | 46 | -824745350_46
MML3RSTSPA7000 | TT_Task | NONO/ NOWC from Project Manager: Schedule of Hazard Analysis | 25/08/2019 | 07/09/2019 | 28/10/2018 | 06/11/2018 | 0 | TK_Complete | -824745350 | 58 | -824745350_58
MML3RSTSPA7010 | TT_Task | NONO/ NOWC from Project Manager: Preliminary Fire Safety Design Report | 25/08/2019 | 07/09/2019 | 18/01/2019 | 23/01/2019 | 0 | TK_Complete | -824745350 | 48 | -824745350_48
MML3RSTCOS0090 | TT_Task | Advance Cost | 29/09/2018 | 30/07/2019 | 29/09/2018 | 30/07/2019 | 0 | TK_Complete | -824745350 | 59 | -824745350_59
MML3RSTDES7840 | TT_Task | DSG Synthesis Module/ Requirement Specification Management | 25/09/2019 | 24/10/2019 | 17/09/2018 | 16/10/2018 | 0 | TK_Complete | -824745350 | 60 | -824745350_60
MML3RSTDES7850 | TT_Task | DSG Requirement Specification Level 1 Allocation | 26/09/2019 | 02/10/2019 | 08/09/2019 | 14/09/2019 | 0 | TK_Complete | -824745350 | 60 | -824745350_60
MML3RSTDES7860 | TT_Task | DSG Operational Context description OCD V-1 | 03/10/2019 | 23/10/2019 | 15/09/2019 | 25/09/2019 | 0 | TK_Complete | -824745350 | 61 | -824745350_61
MML3RSTDES7870 | TT_Task | DSG Operational context Description OCD Consolidated | 26/09/2019 | 16/10/2019 | 26/09/2019 | 22/10/2019 | 0 | TK_Complete | -824745350 | 61 | -824745350_61
MML3RSTDES7875 | TT_Task | DSG ADL1 | 25/10/2019 | 14/11/2019 | 09/09/2019 | 25/09/2019 | 0 | TK_Complete | -824745350 | 62 | -824745350_62
MML3RSTDES7880 | TT_Task | DSG Update General Studies (Layouts/ Mass/ Gauge) | 25/09/2019 | 29/09/2019 | 17/10/2018 | 24/10/2018 | 0 | TK_Complete | -824745350 | 63 | -824745350_63
MML3RSTDES7890 | TT_Task | DSG Layouts and Principles for allocation | 30/09/2019 | 29/10/2019 | 25/10/2018 | 29/10/2018 | 0 | TK_Complete | -824745350 | 60 | -824745350_60
MML3RSTDES7900 | TT_Task | DSG Preliminary electric architecture | 25/09/2019 | 24/10/2019 | 30/10/2018 | 30/11/2018 | 0 | TK_Complete | -824745350 | 64 | -824745350_64
MML3RSTDES7910 | TT_Task | DSG Preliminary Synoptic | 30/10/2019 | 11/11/2019 | 03/12/2018 | 17/12/2018 | 0 | TK_Complete | -824745350 | 63 | -824745350_63
MML3RSTDES7950 | TT_Task | INT OBE2 Onboard Electronics including RSL2 Train to ground radio communication - [Allocation] | 26/10/2019 | 24/11/2019 | 09/09/2019 | 13/09/2019 | 0 | TK_Complete | -824745350 | 65 | -824745350_65
MML3RSTDES7960 | TT_Task | INT OBE2 Onboard Electronics including RSL2 Train to ground radio com - [Consolidation Start] | 26/10/2019 | 04/11/2019 | 14/09/2019 | 18/09/2019 | 0 | TK_Complete | -824745350 | 65 | -824745350_65
MML3RSTDES7970 | TT_Task | INT RSL2 Signalling Equipment - Allocation | 26/10/2019 | 24/11/2019 | 19/09/2019 | 27/09/2019 | 0 | TK_Complete | -824745350 | 66 | -824745350_66
MML3RSTDES7980 | TT_Task | INT RSL2 Signalling Equipment - [Consolidation Start] | 25/11/2019 | 04/12/2019 | 28/09/2019 | 04/10/2019 | 0 | TK_Complete | -824745350 | 66 | -824745350_66
MML3RSTDES7990 | TT_Task | DSG Update Network Architecture | 25/10/2019 | 23/11/2019 | 06/05/2019 | 17/05/2019 | 0 | TK_Complete | -824745350 | 67 | -824745350_67
MML3RSTDES8000 | TT_Task | DSG ICD L1 Subsystems | 25/10/2019 | 23/12/2019 | 01/07/2019 | 30/09/2019 | 0 | TK_Complete | -824745350 | 62 | -824745350_62
MML3RSTDES8010 | TT_Task | INT ICD - ATC | 26/10/2019 | 24/12/2019 | 05/10/2019 | 24/10/2019 | 0 | TK_Complete | -824745350 | 68 | -824745350_68
MML3RSTDES8020 | TT_Task | INT PPS - ATP - Provide automatic train protection ; control | 26/10/2019 | 24/12/2019 | 05/10/2019 | 24/10/2019 | 0 | TK_Complete | -824745350 | 69 | -824745350_69
MML3RSTDES8030 | TT_Task | INT PPS - ATO - Provide automatic train operation | 26/10/2019 | 24/12/2019 | 05/10/2019 | 24/10/2019 | 0 | TK_Complete | -824745350 | 69 | -824745350_69
MML3RSTDES8040 | TT_Task | DSG Preliminary- Pure Principle Scheme (PPS) | 26/10/2019 | 24/12/2019 | 09/05/2019 | 09/07/2019 | 0 | TK_Complete | -824745350 | 70 | -824745350_70
MML3RSTDES8050 | TT_Task | DSG Final - Pure Principle Scheme (PPS) | 09/09/2019 | 09/11/2019 | 09/09/2019 | 09/11/2019 | 0 | TK_Complete | -824745350 | 70 | -824745350_70
MML3RSTDES8060 | TT_Task | DSG EBI (EBOM Long Lead Time electrical Eqpt) | 16/10/2019 | 09/11/2019 | 16/10/2019 | 09/11/2019 | 0 | TK_Complete | -824745350 | 71 | -824745350_71
MML3RSTDES8070 | TT_Task | DSG Solution Principle Scheme (SPS) | 11/11/2019 | 11/11/2019 | 11/11/2019 | 09/12/2019 | 0 | TK_Complete | -824745350 | 70 | -824745350_70
MML3RSTDES8080 | TT_Task | DSG FD (Functional Diagram) + RH (Requirement Harness) + Coherence Check | 10/12/2019 | 08/01/2020 | 10/12/2019 | 08/01/2020 | 0 | TK_Complete | -824745350 | 60 | -824745350_60
MML3RSTDES8090 | TT_Task | DSG Step 1: GH 2D ; Routing 2D | 09/01/2020 | 09/01/2020 | 09/01/2020 | 14/01/2020 | 0 | TK_Complete | -824745350 | 72 | -824745350_72
MML3RSTDES8100 | TT_Task | DSG Step 2: 3D integration ; Routing | 08/02/2020 | 08/03/2020 | 15/01/2020 | 28/01/2020 | 0 | TK_Complete | -824745350 | 72 | -824745350_72
MML3RSTDES8110 | TT_Task | DSG Step 3: Electrical BOM | 29/01/2020 | 06/07/2020 | 29/01/2020 | 06/07/2020 | 0 | TK_Complete | -824745350 | 64 | -824745350_64
MML3RSTDES8120 | TT_Task | DSG Step 4: 3D Mechanical integration | 07/07/2020 | 30/07/2020 | 07/07/2020 | 28/07/2020 | 0 | TK_Complete | -824745350 | 72 | -824745350_72
MML3RSTDES8130 | TT_Task | DSG Step 5: PH (Physical Harness) Release | 29/07/2020 | 08/08/2020 | 29/07/2020 | 08/08/2020 | 0 | TK_Complete | -824745350 | 73 | -824745350_73
MML3RSTDES8140 | TT_Task | DSG Step 6: Weight Release | 10/08/2020 | 15/08/2020 | 10/08/2020 | 15/08/2020 | 0 | TK_Complete | -824745350 | 73 | -824745350_73
MML3RSTDES8150 | TT_Task | DSG Step 7: 3D Master Installation release | 17/08/2020 | 24/08/2020 | 17/08/2020 | 24/08/2020 | 0 | TK_Complete | -824745350 | 72 | -824745350_72
MML3RSTDES8260 | TT_Task | Software Requirement Specifications | 26/01/2020 | 25/03/2020 | 10/06/2019 | 09/08/2019 | 0 | TK_Complete | -824745350 | 74 | -824745350_74
MML3RSTDES8270 | TT_Task | Software Design Specifications | 26/03/2020 | 24/05/2020 | 12/08/2019 | 11/10/2019 | 0 | TK_Complete | -824745350 | 74 | -824745350_74
MML3RSTDES8280 | TT_Task | Software Implementation (Control Build) | 25/05/2020 | 23/07/2020 | 14/10/2019 | 12/12/2019 | 0 | TK_Complete | -824745350 | 75 | -824745350_75
MML3RSTDES8290 | TT_Task | Software Implementation (Low Voltage Network Modelling) | 13/12/2019 | 18/03/2020 | 13/12/2019 | 18/03/2020 | 0 | TK_Complete | -824745350 | 76 | -824745350_76
MML3RSTDES8300 | TT_Task | V0 Test Bench Release | 19/03/2020 | 03/04/2020 | 19/03/2020 | 03/04/2020 | 0 | TK_Complete | -824745350 | 77 | -824745350_77
MML3RSTDES8310 | TT_Task | V1 Static Release | 04/04/2020 | 31/05/2021 | 04/04/2020 | 31/05/2021 | 0 | TK_Complete | -824745350 | 77 | -824745350_77
MML3RSTDES8320 | TT_Task | V2 Dynamic Release | 28/03/2022 | 11/04/2022 | nan | nan | 1448 | TK_NotStart | -824745350 | 77 | -824745350_77
MML3RSTDES7790 | TT_Task | PROC: Train Mock up - Consultation and PO release | 16/12/2018 | 14/01/2019 | 16/12/2018 | 14/01/2019 | 0 | TK_Complete | -824745350 | 78 | -824745350_78
MML3RSTDES7800 | TT_Task | PROC: Development of Mock up Structure | 27/08/2019 | 25/09/2019 | 27/08/2019 | 25/09/2019 | 0 | TK_Complete | -824745350 | 78 | -824745350_78
MML3RSTDES7802 | TT_Task | PROC: Car Body shell Integration | 26/09/2019 | 15/10/2019 | 26/09/2019 | 15/10/2019 | 0 | TK_Complete | -824745350 | 79 | -824745350_79
MML3RSTDES7804 | TT_Task | PROC: Saloon Integration/ Cabin Integration | 16/10/2019 | 25/10/2019 | 16/10/2019 | 25/10/2019 | 0 | TK_Complete | -824745350 | 80 | -824745350_80
MML3RSTDES7820 | TT_Task | PROC: Integration of physical samples and Visual mock-up of sub-system in train mock-up | 26/10/2019 | 29/10/2019 | 26/10/2019 | 04/11/2019 | 0 | TK_Complete | -824745350 | 78 | -824745350_78
MML3RSTDES7825 | TT_Task | PROC: Project Manager Inspection | 05/11/2019 | 05/11/2019 | 05/11/2019 | 05/11/2019 | 0 | TK_Complete | -824745350 | 37 | -824745350_37
MML3RSTDES7830 | TT_Task | PROC: NONO/ NOWC from Project Manager | 05/11/2019 | 05/11/2019 | 05/11/2019 | nan | 0 | TK_Active | -824745350 | 81 | -824745350_81
MML3RSTDES1000 | TT_Task | Preliminary Design: First Submission by Alstom - Train Specification | 25/08/2019 | 24/10/2019 | 10/09/2018 | 05/12/2018 | 0 | TK_Complete | -824745350 | 82 | -824745350_82
MML3RSTDES6270 | TT_Task | Preliminary Design: First Submission by Alstom - System Description of Fire and Smoke detection system | 25/08/2019 | 24/10/2019 | 10/09/2018 | 05/12/2018 | 0 | TK_Complete | -824745350 | 83 | -824745350_83
MML3RSTDES6280 | TT_Task | Prelimnary Design: First Submission by Alstom - Preliminary Vehicle Performance | 09/10/2019 | 24/10/2019 | 10/09/2018 | 05/12/2018 | 0 | TK_Complete | -824745350 | 84 | -824745350_84
MML3RSTDES6290 | TT_Task | Prelimnary Design: First Submission by Alstom - System Description of Bogies | 25/08/2019 | 24/10/2019 | 10/09/2018 | 05/12/2018 | 0 | TK_Complete | -824745350 | 85 | -824745350_85
MML3RSTDES6300 | TT_Task | Prelimnary Design: First Submission by Alstom - System Description of Brakes | 25/08/2019 | 03/11/2019 | 10/09/2018 | 06/12/2018 | 0 | TK_Complete | -824745350 | 86 | -824745350_86
MML3RSTDES6310 | TT_Task | Preliminary Design: First Submission by Alstom - System Description of Air Supply System | 25/08/2019 | 03/11/2019 | 10/09/2018 | 05/12/2018 | 0 | TK_Complete | -824745350 | 87 | -824745350_87
MML3RSTDES6320 | TT_Task | Preliminary Design: First Submission by Alstom - System Description of Passenger Doors | 25/08/2019 | 03/11/2019 | 10/09/2018 | 06/12/2018 | 0 | TK_Complete | -824745350 | 88 | -824745350_88
MML3RSTDES6330 | TT_Task | Preliminary Design: First Submission by Alstom - System Description of Front Detrainment Doors | 25/08/2019 | 03/11/2019 | 10/09/2018 | 06/12/2018 | 0 | TK_Complete | -824745350 | 89 | -824745350_89
MML3RSTDES6340 | TT_Task | Preliminary Design: First Submission by Alstom - System Description of Propulsion system | 25/08/2019 | 03/11/2019 | 10/09/2018 | 06/12/2018 | 0 | TK_Complete | -824745350 | 90 | -824745350_90
MML3RSTDES6350 | TT_Task | Preliminary Design: First Submission by Alstom - System Description of Pantograph | 09/10/2019 | 03/11/2019 | 25/10/2018 | 05/12/2018 | 0 | TK_Complete | -824745350 | 91 | -824745350_91
MML3RSTDES6360 | TT_Task | Preliminary Design: First Submission by Alstom - System Description of Auxiliary supply System | 25/08/2019 | 03/11/2019 | 10/09/2018 | 06/12/2018 | 0 | TK_Complete | -824745350 | 92 | -824745350_92
MML3RSTDES6370 | TT_Task | Preliminary Design: First Submission by Alstom - System Description of VAC | 25/08/2019 | 03/11/2019 | 10/09/2018 | 05/12/2018 | 0 | TK_Complete | -824745350 | 93 | -824745350_93
MML3RSTDES6380 | TT_Task | Preliminary Design: First Submission by Alstom - EMC Control Plan | 25/10/2018 | 07/11/2018 | 25/10/2018 | 29/11/2018 | 0 | TK_Complete | -824745350 | 25 | -824745350_25
MML3RSTDES6390 | TT_Task | Preliminary Design: First Submission by Alstom - System description of Lighting | 25/08/2019 | 13/11/2019 | 10/09/2018 | 06/12/2018 | 0 | TK_Complete | -824745350 | 94 | -824745350_94
MML3RSTDES6400 | TT_Task | Preliminary Design: First Submission by Alstom - System description of TCMS | 10/09/2018 | 05/12/2018 | 10/09/2018 | 05/12/2018 | 0 | TK_Complete | -824745350 | 95 | -824745350_95
MML3RSTDES6410 | TT_Task | Preliminary Design: First Submission by Alstom - System description of PACIS system | 10/09/2018 | 06/12/2018 | 10/09/2018 | 06/12/2018 | 0 | TK_Complete | -824745350 | 96 | -824745350_96
MML3RSTDES6420 | TT_Task | Preliminary Design: First Submission by Alstom - Vehicle control circuit - General | 10/09/2018 | 06/12/2018 | 10/09/2018 | 06/12/2018 | 0 | TK_Complete | -824745350 | 97 | -824745350_97
MML3RSTDES6430 | TT_Task | Preliminary Design: First Submission by Alstom - Technical Description and Drawings of wires ; Cable | 25/08/2019 | 29/09/2019 | 10/09/2018 | 06/12/2018 | 0 | TK_Complete | -824745350 | 98 | -824745350_98
MML3RSTDES6440 | TT_Task | Preliminary Design: First Submission by Alstom - Train Configuration ; Main Dimensions | 25/08/2019 | 13/11/2019 | 10/09/2018 | 05/12/2018 | 0 | TK_Complete | -824745350 | 82 | -824745350_82
MML3RSTDES6450 | TT_Task | Preliminary Design: First Submission by Alstom - Calculation of Passenger Capacity | 25/08/2019 | 13/11/2019 | 10/09/2018 | 05/12/2018 | 0 | TK_Complete | -824745350 | 99 | -824745350_99
MML3RSTDES6460 | TT_Task | Preliminary Design: First Submission by Alstom - Car Static Profile ; Carbody cross section | 25/08/2019 | 13/11/2019 | 10/09/2018 | 05/12/2018 | 0 | TK_Complete | -824745350 | 100 | -824745350_100
MML3RSTDES6470 | TT_Task | Preliminary Design: First Submission by Alstom - Preliminary Kinematic Envelope Calculation Report | 25/10/2018 | 06/12/2018 | 25/10/2018 | 06/12/2018 | 0 | TK_Complete | -824745350 | 101 | -824745350_101
MML3RSTDES6480 | TT_Task | Preliminary Design: First Submission by Alstom - Preliminary Fire Safety Design Report | 25/08/2019 | 13/11/2019 | 10/09/2018 | 29/11/2018 | 0 | TK_Complete | -824745350 | 31 | -824745350_31
MML3RSTDES6490 | TT_Task | Preliminary Design: First Submission by Alstom - Weight Management Plan | 25/10/2018 | 05/12/2018 | 25/10/2018 | 05/12/2018 | 0 | TK_Complete | -824745350 | 102 | -824745350_102
MML3RSTDES6500 | TT_Task | Preliminary Design: First Submission by Alstom - Noise and Vibration Assurance plan | 25/08/2019 | 07/11/2019 | 10/09/2018 | 05/12/2018 | 0 | TK_Complete | -824745350 | 103 | -824745350_103
MML3RSTDES6510 | TT_Task | Preliminary Design: First Submission by Alstom - Engineering Mockup Specification - Saloon and Cab | 25/10/2018 | 10/12/2018 | 25/10/2018 | 07/12/2018 | 0 | TK_Complete | -824745350 | 80 | -824745350_80
MML3RSTDES6520 | TT_Task | Preliminary Design: First Submission by Alstom - Validation Plan for Carbody Shell- FEA | 25/08/2019 | 13/11/2019 | 10/09/2018 | 05/12/2018 | 0 | TK_Complete | -824745350 | 104 | -824745350_104
MML3RSTDES6530 | TT_Task | Preliminary Design: First Submission by Alstom - Preliminary Design Specification - Carbody Structure | 25/08/2019 | 13/11/2019 | 10/09/2018 | 05/12/2018 | 0 | TK_Complete | -824745350 | 105 | -824745350_105
MML3RSTDES6540 | TT_Task | Preliminary Design: First Submission by Alstom - Preliminary Design Specification - Saloon Interior | 25/08/2019 | 04/11/2019 | 10/09/2018 | 05/12/2018 | 0 | TK_Complete | -824745350 | 106 | -824745350_106
MML3RSTDES6550 | TT_Task | Preliminary Design: First Submission by Alstom - Preliminary Design Specification - Cab | 10/09/2018 | 05/12/2018 | 10/09/2018 | 05/12/2018 | 0 | TK_Complete | -824745350 | 107 | -824745350_107
MML3RSTDES6560 | TT_Task | Preliminary Design: First Submission by Alstom - Preliminary Design Sepcification - Equipment Mounting | 10/09/2018 | 05/12/2018 | 10/09/2018 | 05/12/2018 | 0 | TK_Complete | -824745350 | 108 | -824745350_108
MML3RSTDES6570 | TT_Task | Preliminary Design: First Submission by Alstom - Preliminay Design Specification - Couplers | 25/08/2019 | 07/11/2019 | 10/09/2018 | 05/12/2018 | 0 | TK_Complete | -824745350 | 109 | -824745350_109
MML3RSTDES6580 | TT_Task | Preliminary Design: First Submission by Alstom - Preliminary Design Specification - Gangway | 25/08/2019 | 07/11/2019 | 10/09/2018 | 05/12/2018 | 0 | TK_Complete | -824745350 | 107 | -824745350_107
MML3RSTDES6590 | TT_Task | Preliminary Design: First Submission by Alstom - Exterior and Interior Design book | 25/08/2019 | 15/11/2019 | 10/09/2018 | 06/12/2018 | 0 | TK_Complete | -824745350 | 110 | -824745350_110
MML3RSTDES6600 | TT_Task | Preliminary Design: First Submission by Alstom - Preliminary Simulator Plan | 25/08/2019 | 12/11/2019 | 10/09/2018 | 05/12/2018 | 0 | TK_Complete | -824745350 | 111 | -824745350_111
MML3RSTDES6610 | TT_Task | Preliminary Design: First Submission by Alstom - Maintainability Plan | 25/08/2019 | 13/11/2019 | 10/09/2018 | 05/12/2018 | 0 | TK_Complete | -824745350 | 7 | -824745350_7
MML3RSTDES6620 | TT_Task | Preliminary Design: First Submission by Alstom - Safety Assurance Plan | 25/08/2019 | 22/10/2019 | 10/09/2018 | 16/11/2018 | 0 | TK_Complete | -824745350 | 18 | -824745350_18
MML3RSTDES6630 | TT_Task | Preliminary Design: First Submission by Alstom - Reliability ; Availability Maintability Plan | 10/09/2018 | 27/11/2018 | 10/09/2018 | 27/11/2018 | 0 | TK_Complete | -824745350 | 112 | -824745350_112
MML3RSTDES8160 | TT_Task | Preliminary Design: First Submission by Alstom - List of Standards | 25/08/2019 | 15/11/2019 | 10/09/2018 | 05/12/2018 | 0 | TK_Complete | -824745350 | 107 | -824745350_107
MML3RSTDES8170 | TT_Task | Preliminary Design: First Submission by Alstom - Wayside Rolling Stock Monitoring and Measurement System | 25/08/2019 | 15/11/2019 | 10/09/2018 | 25/03/2019 | 0 | TK_Complete | -824745350 | 113 | -824745350_113
MML3RSTDES8180 | TT_Task | Preliminary Design: First Submission by Alstom - Computer based Maintenance Management System (CMMS) | 25/08/2019 | 15/11/2019 | 10/09/2018 | 25/03/2019 | 0 | TK_Complete | -824745350 | 114 | -824745350_114
MML3RSTDES6640 | TT_Task | Preliminary Design: Review/ Comments from Project Manager - Train Specification | 25/08/2019 | 07/09/2019 | 06/12/2018 | 08/01/2019 | 0 | TK_Complete | -824745350 | 115 | -824745350_115
MML3RSTDES6650 | TT_Task | Preliminary Design: Review/ Comments from Project Manager - System Description of Fire and Smoke detection system | 25/08/2019 | 07/09/2019 | 06/12/2018 | 08/01/2019 | 0 | TK_Complete | -824745350 | 83 | -824745350_83
MML3RSTDES6660 | TT_Task | Preliminary Design: Review/ Comments from Project Manager - Preliminary Vehicle Performance | 09/10/2019 | 22/10/2019 | 06/12/2018 | 09/01/2019 | 0 | TK_Complete | -824745350 | 116 | -824745350_116
MML3RSTDES6670 | TT_Task | Preliminary Design: Review/ Comments from Project Manager - System Description of Bogies | 25/08/2019 | 07/09/2019 | 06/12/2018 | 10/01/2019 | 0 | TK_Complete | -824745350 | 117 | -824745350_117
MML3RSTDES6680 | TT_Task | Preliminary Design: Review/ Comments from Project Manager - System Description of Brakes | 25/08/2019 | 07/09/2019 | 07/12/2018 | 09/01/2019 | 0 | TK_Complete | -824745350 | 118 | -824745350_118
MML3RSTDES6690 | TT_Task | Preliminary Design: Review/ Comments from Project Manager - System Description of Air Supply System | 25/08/2019 | 07/09/2019 | 06/12/2018 | 09/01/2019 | 0 | TK_Complete | -824745350 | 119 | -824745350_119
MML3RSTDES6700 | TT_Task | Preliminary Design: Review/ Comments from Project Manager - System Description of Passenger Doors | 25/08/2019 | 07/09/2019 | 07/12/2018 | 08/01/2019 | 0 | TK_Complete | -824745350 | 120 | -824745350_120
MML3RSTDES6710 | TT_Task | Preliminary Design: Review/ Comments from Project Manager - System Description of Front Detrainment Doors | 25/08/2019 | 07/09/2019 | 07/12/2018 | 08/01/2019 | 0 | TK_Complete | -824745350 | 121 | -824745350_121
MML3RSTDES6720 | TT_Task | Preliminary Design: Review/ Comments from Project Manager - System Description of Propulsion system | 25/08/2019 | 07/09/2019 | 07/12/2018 | 09/01/2019 | 0 | TK_Complete | -824745350 | 122 | -824745350_122
MML3RSTDES6730 | TT_Task | Preliminary Design: Review/ Comments from Project Manager - System Description of Pantograph | 09/10/2019 | 22/10/2019 | 06/12/2018 | 08/01/2019 | 0 | TK_Complete | -824745350 | 123 | -824745350_123
MML3RSTDES6740 | TT_Task | Preliminary Design: Review/ Comments from Project Manager - System Description of Auxiliary supply System | 25/08/2019 | 07/09/2019 | 07/12/2018 | 08/01/2019 | 0 | TK_Complete | -824745350 | 124 | -824745350_124
MML3RSTDES6750 | TT_Task | Preliminary Design: Review/ Comments from Project Manager - System Description of VAC | 25/08/2019 | 07/09/2019 | 06/12/2018 | 08/01/2019 | 0 | TK_Complete | -824745350 | 125 | -824745350_125
MML3RSTDES6760 | TT_Task | Preliminary Design: Review/ Comments from Project Manager - EMC Control Plan | 30/11/2018 | 19/12/2018 | 30/11/2018 | 19/12/2018 | 0 | TK_Complete | -824745350 | 44 | -824745350_44
MML3RSTDES6770 | TT_Task | Preliminary Design: Review/ Comments from Project Manager - System description of Lighting | 25/08/2019 | 07/09/2019 | 07/12/2018 | 09/01/2019 | 0 | TK_Complete | -824745350 | 126 | -824745350_126
MML3RSTDES6780 | TT_Task | Preliminary Design: Review/ Comments from Project Manager - System description of TCMS | 06/12/2018 | 07/01/2019 | 06/12/2018 | 07/01/2019 | 0 | TK_Complete | -824745350 | 127 | -824745350_127
MML3RSTDES6790 | TT_Task | Preliminary Design: Review/ Comments from Project Manager - System description of PAPIS system | 07/12/2018 | 07/01/2019 | 07/12/2018 | 07/01/2019 | 0 | TK_Complete | -824745350 | 128 | -824745350_128
MML3RSTDES6800 | TT_Task | Preliminary Design: Review/ Comments from Project Manager - Vehicle control circuit - General | 07/12/2018 | 07/01/2019 | 07/12/2018 | 07/01/2019 | 0 | TK_Complete | -824745350 | 129 | -824745350_129
MML3RSTDES6810 | TT_Task | Preliminary Design: Review/ Comments from Project Manager - Technical Description and Drawings of wires ; Cable | 25/08/2019 | 07/09/2019 | 07/12/2018 | 08/01/2019 | 0 | TK_Complete | -824745350 | 98 | -824745350_98
MML3RSTDES6820 | TT_Task | Preliminary Design: Review/ Comments from Project Manager - Train Configuration ; Main Dimensions | 25/08/2019 | 07/09/2019 | 06/12/2018 | 08/01/2019 | 0 | TK_Complete | -824745350 | 115 | -824745350_115
MML3RSTDES6830 | TT_Task | Preliminary Design: Review/ Comments from Project Manager - Calculation of Passenger Capacity | 25/08/2019 | 07/09/2019 | 06/12/2018 | 08/01/2019 | 0 | TK_Complete | -824745350 | 99 | -824745350_99
MML3RSTDES6840 | TT_Task | Preliminary Design: Review/ Comments from Project Manager - Car Static Profile ; Carbody cross section | 25/08/2019 | 07/09/2019 | 06/12/2018 | 09/01/2019 | 0 | TK_Complete | -824745350 | 100 | -824745350_100
MML3RSTDES6850 | TT_Task | Preliminary Design: Review/ Comments from Project Manager - Preliminary Kinematic Envelope Calculation Report | 07/12/2018 | 07/01/2019 | 07/12/2018 | 07/01/2019 | 0 | TK_Complete | -824745350 | 130 | -824745350_130
MML3RSTDES6860 | TT_Task | Preliminary Design: Review/ Comments from Project Manager - Preliminary Fire Safety Design Report | 25/08/2019 | 07/09/2019 | 30/11/2018 | 07/01/2019 | 0 | TK_Complete | -824745350 | 48 | -824745350_48
MML3RSTDES6870 | TT_Task | Preliminary Design: Review/ Comments from Project Manager - Weight Management Plan | 06/12/2018 | 09/01/2019 | 06/12/2018 | 09/01/2019 | 0 | TK_Complete | -824745350 | 131 | -824745350_131
MML3RSTDES6880 | TT_Task | Preliminary Design: Review/ Comments from Project Manager - Noise and Vibration Assurance plan | 25/08/2019 | 07/09/2019 | 06/12/2018 | 14/01/2019 | 0 | TK_Complete | -824745350 | 132 | -824745350_132
MML3RSTDES6890 | TT_Task | Preliminary Design: Review/ Comments from Project Manager - Engineering Mockup Specification - Saloon and Cab | 08/12/2018 | 21/12/2018 | 08/12/2018 | 09/01/2019 | 0 | TK_Complete | -824745350 | 80 | -824745350_80
MML3RSTDES6900 | TT_Task | Preliminary Design: Review/ Comments from Project Manager - Validation Plan for Carbody Shell- FEA | 25/08/2019 | 07/09/2019 | 06/12/2018 | 09/01/2019 | 0 | TK_Complete | -824745350 | 104 | -824745350_104
MML3RSTDES6910 | TT_Task | Preliminary Design: Review/ Comments from Project Manager - Preliminary Design Specification - Carbody Structure | 25/08/2019 | 07/09/2019 | 06/12/2018 | 08/01/2019 | 0 | TK_Complete | -824745350 | 133 | -824745350_133
MML3RSTDES6920 | TT_Task | Preliminary Design: Review/ Comments from Project Manager - Preliminary Design Specification - Saloon Interior | 25/08/2019 | 07/09/2019 | 06/12/2018 | 09/01/2019 | 0 | TK_Complete | -824745350 | 106 | -824745350_106
MML3RSTDES6930 | TT_Task | Preliminary Design: Review/ Comments from Project Manager - Preliminary Design Specification - Cab | 06/12/2018 | 07/01/2019 | 06/12/2018 | 07/01/2019 | 0 | TK_Complete | -824745350 | 134 | -824745350_134
MML3RSTDES6940 | TT_Task | Preliminary Design: Review/ Comments from Project Manager - Preliminary Design Sepcification - Equipment Mounting | 06/12/2018 | 07/01/2019 | 06/12/2018 | 07/01/2019 | 0 | TK_Complete | -824745350 | 108 | -824745350_108
MML3RSTDES6950 | TT_Task | Preliminary Design: Review/ Comments from Project Manager - Preliminay Design Specification - Couplers | 25/08/2019 | 07/09/2019 | 06/12/2018 | 09/01/2019 | 0 | TK_Complete | -824745350 | 134 | -824745350_134
MML3RSTDES6960 | TT_Task | Preliminary Design: Review/ Comments from Project Manager - Preliminary Design Specification - Gangway | 25/08/2019 | 07/09/2019 | 06/12/2018 | 08/01/2019 | 0 | TK_Complete | -824745350 | 134 | -824745350_134
MML3RSTDES6970 | TT_Task | Preliminary Design: Review/ Comments from Project Manager - Exterior and Interior Design book | 25/08/2019 | 07/09/2019 | 07/12/2018 | 09/01/2019 | 0 | TK_Complete | -824745350 | 110 | -824745350_110
MML3RSTDES6980 | TT_Task | Preliminary Design: Review/ Comments from Project Manager - Preliminary Simulator Plan | 25/08/2019 | 07/09/2019 | 06/12/2018 | 09/01/2019 | 0 | TK_Complete | -824745350 | 135 | -824745350_135
MML3RSTDES6990 | TT_Task | Preliminary Design: Review/ Comments from Project Manager - Maintainability Plan | 25/08/2019 | 07/09/2019 | 06/12/2018 | 10/01/2019 | 0 | TK_Complete | -824745350 | 33 | -824745350_33
MML3RSTDES7000 | TT_Task | Preliminary Design: Review/ Comments from Project Manager - Safety Assurance Plan | 25/08/2019 | 07/09/2019 | 17/11/2018 | 05/12/2018 | 0 | TK_Complete | -824745350 | 42 | -824745350_42
MML3RSTDES7010 | TT_Task | Preliminary Design: Review/ Comments from Project Manager - Reliability ; Availability Maintability Plan | 28/11/2018 | 10/12/2018 | 28/11/2018 | 10/12/2018 | 0 | TK_Complete | -824745350 | 136 | -824745350_136
MML3RSTSPA7020 | TT_Task | Preliminary Design: Review/ Comments from Project Manager - List of Standards | 25/08/2019 | 07/09/2019 | 06/12/2018 | 08/01/2019 | 0 | TK_Complete | -824745350 | 134 | -824745350_134
MML3RSTSPA7030 | TT_Task | Preliminary Design: Review/ Comments from Project Manager - Wayside Rolling Stock Monitoring and Measurement System | 25/08/2019 | 07/09/2019 | 26/03/2019 | 08/04/2019 | 0 | TK_Complete | -824745350 | 113 | -824745350_113
MML3RSTSPA7040 | TT_Task | Preliminary Design: Review/ Comments from Project Manager - Computer based Maintenance Management System (CMMS) | 25/08/2019 | 07/09/2019 | 26/03/2019 | 26/03/2019 | 0 | TK_Complete | -824745350 | 137 | -824745350_137
MML3RSTDES7020 | TT_Task | Preliminary Design: Resubmission by Alstom - Train Specification | 25/08/2019 | 07/09/2019 | 09/01/2019 | 02/08/2019 | 0 | TK_Complete | -824745350 | 82 | -824745350_82
MML3RSTDES7030 | TT_Task | Preliminary Design: Resubmission by Alstom - System Description of Fire and Smoke detection system | 25/08/2019 | 07/09/2019 | 09/01/2019 | 27/06/2019 | 0 | TK_Complete | -824745350 | 83 | -824745350_83
MML3RSTDES7040 | TT_Task | Preliminary Design: Resubmission by Alstom - Preliminary Vehicle Performance | 09/10/2019 | 22/10/2019 | 10/01/2019 | 16/07/2019 | 0 | TK_Complete | -824745350 | 84 | -824745350_84
MML3RSTDES7050 | TT_Task | Preliminary Design: Resubmission by Alstom - System Description of Bogies | 25/08/2019 | 07/09/2019 | 11/01/2019 | 09/08/2019 | 0 | TK_Complete | -824745350 | 85 | -824745350_85
MML3RSTDES7060 | TT_Task | Preliminary Design: Resubmission by Alstom - System Description of Brakes | 25/08/2019 | 07/09/2019 | 10/01/2019 | 02/08/2019 | 0 | TK_Complete | -824745350 | 86 | -824745350_86
MML3RSTDES7070 | TT_Task | Preliminary Design: Resubmission by Alstom - System Description of Air Supply System | 25/08/2019 | 07/09/2019 | 10/01/2019 | 02/08/2019 | 0 | TK_Complete | -824745350 | 87 | -824745350_87
MML3RSTDES7080 | TT_Task | Preliminary Design: Resubmission by Alstom - System Description of Passenger Doors | 25/08/2019 | 07/09/2019 | 09/01/2019 | 28/05/2019 | 0 | TK_Complete | -824745350 | 88 | -824745350_88
MML3RSTDES7090 | TT_Task | Preliminary Design: Resubmission by Alstom - System Description of Front Detrainment Doors | 25/08/2019 | 07/09/2019 | 09/01/2019 | 28/05/2019 | 0 | TK_Complete | -824745350 | 89 | -824745350_89
MML3RSTDES7100 | TT_Task | Preliminary Design: Resubmission by Alstom - System Description of Propulsion system | 25/08/2019 | 07/09/2019 | 10/01/2019 | 03/08/2019 | 0 | TK_Complete | -824745350 | 90 | -824745350_90
MML3RSTDES7110 | TT_Task | Preliminary Design: Resubmission by Alstom - System Description of Pantograph | 09/10/2019 | 22/10/2019 | 09/01/2019 | 28/05/2019 | 0 | TK_Complete | -824745350 | 91 | -824745350_91
MML3RSTDES7120 | TT_Task | Preliminary Design: Resubmission by Alstom - System Description of Auxiliary supply System | 25/08/2019 | 07/09/2019 | 09/01/2019 | 03/08/2019 | 0 | TK_Complete | -824745350 | 92 | -824745350_92
MML3RSTDES7130 | TT_Task | Preliminary Design: Resubmission by Alstom - System Description of VAC | 25/08/2019 | 07/09/2019 | 09/01/2019 | 06/08/2019 | 0 | TK_Complete | -824745350 | 93 | -824745350_93
MML3RSTDES7140 | TT_Task | Preliminary Design: Resubmission by Alstom - EMC Control Plan | 21/12/2018 | 01/03/2019 | 21/12/2018 | 23/07/2019 | 0 | TK_Complete | -824745350 | 25 | -824745350_25
MML3RSTDES7150 | TT_Task | Preliminary Design: Resubmission by Alstom - System description of Lighting | 25/08/2019 | 07/09/2019 | 10/01/2019 | 06/05/2019 | 0 | TK_Complete | -824745350 | 94 | -824745350_94
MML3RSTDES7160 | TT_Task | Preliminary Design: Resubmission by Alstom - System description of TCMS | 22/06/2019 | 06/08/2019 | 22/06/2019 | 06/08/2019 | 0 | TK_Complete | -824745350 | 95 | -824745350_95
MML3RSTDES7170 | TT_Task | Preliminary Design: Resubmission by Alstom - System description of PAPIS system | 20/06/2019 | 03/08/2019 | 20/06/2019 | 03/08/2019 | 0 | TK_Complete | -824745350 | 138 | -824745350_138
MML3RSTDES7180 | TT_Task | Preliminary Design: Resubmission by Alstom - Vehicle control circuit - General | 09/07/2019 | 03/08/2019 | 09/07/2019 | 03/08/2019 | 0 | TK_Complete | -824745350 | 97 | -824745350_97
MML3RSTDES7190 | TT_Task | Preliminary Design: Resubmission by Alstom - Technical Description and Drawings of wires ; Cable | 25/08/2019 | 07/09/2019 | 09/01/2019 | 15/04/2019 | 0 | TK_Complete | -824745350 | 98 | -824745350_98
MML3RSTDES7200 | TT_Task | Preliminary Design: Resubmission by Alstom - Train Configuration ; Main Dimensions | 25/08/2019 | 07/09/2019 | 09/01/2019 | 06/08/2019 | 0 | TK_Complete | -824745350 | 82 | -824745350_82
MML3RSTDES7210 | TT_Task | Preliminary Design: Resubmission by Alstom - Calculation of Passenger Capacity | 25/08/2019 | 07/09/2019 | 09/01/2019 | 06/08/2019 | 0 | TK_Complete | -824745350 | 99 | -824745350_99
MML3RSTDES7220 | TT_Task | Preliminary Design: Resubmission by Alstom - Car Static Profile ; Carbody cross section | 25/08/2019 | 07/09/2019 | 10/01/2019 | 06/08/2019 | 0 | TK_Complete | -824745350 | 100 | -824745350_100
MML3RSTDES7230 | TT_Task | Preliminary Design: Resubmission by Alstom - Preliminary Kinematic Envelope Calculation Report | 08/01/2019 | 08/02/2019 | 10/06/2019 | 16/08/2019 | 0 | TK_Complete | -824745350 | 101 | -824745350_101
MML3RSTDES7240 | TT_Task | Preliminary Design: Resubmission by Alstom - Preliminary Fire Safety Design Report | 25/08/2019 | 07/09/2019 | 08/01/2019 | 21/08/2019 | 0 | TK_Complete | -824745350 | 31 | -824745350_31
MML3RSTDES7250 | TT_Task | Preliminary Design: Resubmission by Alstom - Weight Management Plan | 12/07/2019 | 06/08/2019 | 12/07/2019 | 06/08/2019 | 0 | TK_Complete | -824745350 | 102 | -824745350_102
MML3RSTDES7260 | TT_Task | Preliminary Design: Resubmission by Alstom - Noise and Vibration Assurance plan | 25/08/2019 | 07/09/2019 | 15/01/2019 | 06/08/2019 | 0 | TK_Complete | -824745350 | 103 | -824745350_103
MML3RSTDES7270 | TT_Task | Preliminary Design: Resubmission by Alstom - Engineering Mockup Specification - Saloon and Cab | 22/05/2019 | 26/08/2019 | 22/05/2019 | 26/08/2019 | 0 | TK_Complete | -824745350 | 80 | -824745350_80
MML3RSTDES7280 | TT_Task | Preliminary Design: Resubmission by Alstom - Validation Plan for Carbody Shell- FEA | 25/08/2019 | 07/09/2019 | 10/01/2019 | 28/08/2019 | 0 | TK_Complete | -824745350 | 104 | -824745350_104
MML3RSTDES7290 | TT_Task | Preliminary Design: Resubmission by Alstom - Preliminary Design Specification - Carbody Structure | 25/08/2019 | 07/09/2019 | 02/05/2019 | 30/08/2019 | 0 | TK_Complete | -824745350 | 105 | -824745350_105
MML3RSTDES7300 | TT_Task | Preliminary Design: Resubmission by Alstom - Preliminary Design Specification - Saloon Interior | 25/08/2019 | 07/09/2019 | 10/01/2019 | 10/08/2019 | 0 | TK_Complete | -824745350 | 106 | -824745350_106
MML3RSTDES7310 | TT_Task | Preliminary Design: Resubmission by Alstom - Preliminary Design Specification - Cab | 22/06/2019 | 08/08/2019 | 22/06/2019 | 08/08/2019 | 0 | TK_Complete | -824745350 | 107 | -824745350_107
MML3RSTDES7320 | TT_Task | Preliminary Design: Resubmission by Alstom - Preliminary Design Sepcification - Equipment Mounting | 24/06/2019 | 06/08/2019 | 24/06/2019 | 06/08/2019 | 0 | TK_Complete | -824745350 | 108 | -824745350_108
MML3RSTDES7330 | TT_Task | Preliminary Design: Resubmission by Alstom - Preliminay Design Specification - Couplers | 25/08/2019 | 07/09/2019 | 10/01/2019 | 27/08/2019 | 0 | TK_Complete | -824745350 | 109 | -824745350_109
MML3RSTDES7340 | TT_Task | Preliminary Design: Resubmission by Alstom - Preliminary Design Specification - Gangway | 25/08/2019 | 07/09/2019 | 09/01/2019 | 06/08/2019 | 0 | TK_Complete | -824745350 | 107 | -824745350_107
MML3RSTDES7350 | TT_Task | Preliminary Design: Resubmission by Alstom - Exterior and Interior Design book | 25/08/2019 | 07/09/2019 | 10/01/2019 | 06/08/2019 | 0 | TK_Complete | -824745350 | 110 | -824745350_110
MML3RSTDES7360 | TT_Task | Preliminary Design: Resubmission by Alstom - Preliminary Simulator Plan | 25/08/2019 | 07/09/2019 | 10/01/2019 | 30/08/2019 | 0 | TK_Complete | -824745350 | 111 | -824745350_111
MML3RSTDES7370 | TT_Task | Preliminary Design: Resubmission by Alstom - Maintainability Plan | 25/08/2019 | 07/09/2019 | 11/01/2019 | 15/02/2019 | 0 | TK_Complete | -824745350 | 50 | -824745350_50
MML3RSTDES7380 | TT_Task | Preliminary Design: Resubmission by Alstom - Safety Assurance Plan | 25/08/2019 | 07/09/2019 | 06/12/2018 | 21/12/2018 | 0 | TK_Complete | -824745350 | 18 | -824745350_18
MML3RSTDES7390 | TT_Task | Preliminary Design: Resubmission by Alstom - Reliability ; Availability Maintability Plan | 09/01/2019 | 24/01/2019 | 09/01/2019 | 24/01/2019 | 0 | TK_Complete | -824745350 | 112 | -824745350_112
MML3RSTSPA7050 | TT_Task | Preliminary Design: Resubmission by Alstom - List of Standards | 25/08/2019 | 07/09/2019 | 09/01/2019 | 23/08/2019 | 0 | TK_Complete | -824745350 | 107 | -824745350_107
MML3RSTSPA7060 | TT_Task | Preliminary Design: Resubmission by Alstom - Wayside Rolling Stock Monitoring and Measurement System | 25/08/2019 | 07/09/2019 | 09/04/2019 | 28/08/2019 | 0 | TK_Complete | -824745350 | 113 | -824745350_113
MML3RSTSPA7070 | TT_Task | Preliminary Design: Resubmission by Alstom - Computer based Maintenance Management System (CMMS) | 25/08/2019 | 07/09/2019 | 27/03/2019 | 27/03/2019 | 0 | TK_Complete | -824745350 | 114 | -824745350_114
MML3RSTDES7400 | TT_Task | Preliminary Design: NONO/ NOWC from Project Manager - Train Specification | 25/08/2019 | 07/09/2019 | 03/08/2019 | 05/08/2019 | 0 | TK_Complete | -824745350 | 115 | -824745350_115
MML3RSTDES7410 | TT_Task | Preliminary Design: NONO/ NOWC from Project Manager - System Description of Fire and Smoke detection system | 25/08/2019 | 07/09/2019 | 28/06/2019 | 11/07/2019 | 0 | TK_Complete | -824745350 | 83 | -824745350_83
MML3RSTDES7420 | TT_Task | Preliminary Design: NONO/ NOWC from Project Manager - Preliminary Vehicle Performance | 09/10/2019 | 22/10/2019 | 17/07/2019 | 02/08/2019 | 0 | TK_Complete | -824745350 | 129 | -824745350_129
MML3RSTDES7430 | TT_Task | Preliminary Design: NONO/ NOWC from Project Manager - System Description of Bogies | 25/08/2019 | 07/09/2019 | 10/08/2019 | 10/08/2019 | 0 | TK_Complete | -824745350 | 117 | -824745350_117
MML3RSTDES7440 | TT_Task | Preliminary Design: NONO/ NOWC from Project Manager - System Description of Brakes | 25/08/2019 | 07/09/2019 | 03/08/2019 | 07/08/2019 | 0 | TK_Complete | -824745350 | 139 | -824745350_139
MML3RSTDES7450 | TT_Task | Preliminary Design: NONO/ NOWC from Project Manager - System Description of Air Supply System | 25/08/2019 | 07/09/2019 | 03/08/2019 | 07/08/2019 | 0 | TK_Complete | -824745350 | 119 | -824745350_119
MML3RSTDES7460 | TT_Task | Preliminary Design: NONO/ NOWC from Project Manager - System Description of Passenger Doors | 25/08/2019 | 07/09/2019 | 29/05/2019 | 12/06/2019 | 0 | TK_Complete | -824745350 | 120 | -824745350_120
MML3RSTDES7470 | TT_Task | Preliminary Design: NONO/ NOWC from Project Manager - System Description of Front Detrainment Doors | 25/08/2019 | 07/09/2019 | 29/05/2019 | 12/06/2019 | 0 | TK_Complete | -824745350 | 121 | -824745350_121
MML3RSTDES7480 | TT_Task | Preliminary Design: NONO/ NOWC from Project Manager - System Description of Propulsion system | 25/08/2019 | 07/09/2019 | 04/08/2019 | 07/08/2019 | 0 | TK_Complete | -824745350 | 140 | -824745350_140
MML3RSTDES7490 | TT_Task | Preliminary Design: NONO/ NOWC from Project Manager - System Description of Pantograph | 09/10/2019 | 22/10/2019 | 29/05/2019 | 12/06/2019 | 0 | TK_Complete | -824745350 | 123 | -824745350_123
MML3RSTDES7500 | TT_Task | Preliminary Design: NONO/ NOWC from Project Manager - System Description of Auxiliary supply System | 25/08/2019 | 07/09/2019 | 04/08/2019 | 06/08/2019 | 0 | TK_Complete | -824745350 | 124 | -824745350_124
MML3RSTDES7510 | TT_Task | Preliminary Design: NONO/ NOWC from Project Manager - System Description of VAC | 25/08/2019 | 07/09/2019 | 07/08/2019 | 07/08/2019 | 0 | TK_Complete | -824745350 | 141 | -824745350_141
MML3RSTDES7520 | TT_Task | Preliminary Design: NONO/ NOWC from Project Manager - EMC Control Plan | 02/03/2019 | 07/08/2019 | 24/07/2019 | 07/08/2019 | 0 | TK_Complete | -824745350 | 44 | -824745350_44
MML3RSTDES7530 | TT_Task | Preliminary Design: NONO/ NOWC from Project Manager - System description of Lighting | 25/08/2019 | 07/09/2019 | 07/05/2019 | 16/05/2019 | 0 | TK_Complete | -824745350 | 126 | -824745350_126
MML3RSTDES7540 | TT_Task | Preliminary Design: NONO/ NOWC from Project Manager - System description of TCMS | 07/08/2019 | 07/08/2019 | 07/08/2019 | 07/08/2019 | 0 | TK_Complete | -824745350 | 127 | -824745350_127
MML3RSTDES7550 | TT_Task | Preliminary Design: NONO/ NOWC from Project Manager - System description of PAPIS system | 04/08/2019 | 05/08/2019 | 04/08/2019 | 05/08/2019 | 0 | TK_Complete | -824745350 | 128 | -824745350_128
MML3RSTDES7560 | TT_Task | Preliminary Design: NONO/ NOWC from Project Manager - Vehicle control circuit - General | 04/08/2019 | 06/08/2019 | 04/08/2019 | 06/08/2019 | 0 | TK_Complete | -824745350 | 129 | -824745350_129
MML3RSTDES7570 | TT_Task | Preliminary Design: NONO/ NOWC from Project Manager - Technical Description and Drawings of wires ; Cable | 25/08/2019 | 07/09/2019 | 16/04/2019 | 25/04/2019 | 0 | TK_Complete | -824745350 | 98 | -824745350_98
MML3RSTDES7580 | TT_Task | Preliminary Design: NONO/ NOWC from Project Manager - Train Configuration ; Main Dimensions | 25/08/2019 | 07/09/2019 | 07/08/2019 | 07/08/2019 | 0 | TK_Complete | -824745350 | 115 | -824745350_115
MML3RSTDES7590 | TT_Task | Preliminary Design: NONO/ NOWC from Project Manager - Calculation of Passenger Capacity | 25/08/2019 | 07/09/2019 | 07/08/2019 | 07/08/2019 | 0 | TK_Complete | -824745350 | 99 | -824745350_99
MML3RSTDES7600 | TT_Task | Preliminary Design: NONO/ NOWC from Project Manager - Car Static Profile ; Carbody cross section | 08/09/2019 | 21/09/2019 | 07/08/2019 | 10/08/2019 | 0 | TK_Complete | -824745350 | 100 | -824745350_100
MML3RSTDES7610 | TT_Task | Preliminary Design: NONO/ NOWC from Project Manager - Preliminary Kinematic Envelope Calculation Report | 16/08/2019 | 16/08/2019 | 16/08/2019 | 16/08/2019 | 0 | TK_Complete | -824745350 | 130 | -824745350_130
MML3RSTDES7620 | TT_Task | Preliminary Design: NONO/ NOWC from Project Manager - Preliminary Fire Safety Design Report | 25/08/2019 | 07/09/2019 | 22/08/2019 | 23/08/2019 | 0 | TK_Complete | -824745350 | 48 | -824745350_48
MML3RSTDES7630 | TT_Task | Preliminary Design: NONO/ NOWC from Project Manager - Weight Management Plan | 06/08/2019 | 07/08/2019 | 06/08/2019 | 07/08/2019 | 0 | TK_Complete | -824745350 | 131 | -824745350_131
MML3RSTDES7640 | TT_Task | Preliminary Design: NONO/ NOWC from Project Manager - Noise and Vibration Assurance plan | 25/08/2019 | 07/09/2019 | 07/08/2019 | 07/08/2019 | 0 | TK_Complete | -824745350 | 132 | -824745350_132
MML3RSTDES7650 | TT_Task | Preliminary Design: NONO/ NOWC from Project Manager - Engineering Mockup Specification - Saloon and Cab | 26/08/2019 | 26/08/2019 | 26/08/2019 | 26/08/2019 | 0 | TK_Complete | -824745350 | 80 | -824745350_80
MML3RSTDES7660 | TT_Task | Preliminary Design: NONO/ NOWC from Project Manager - Validation Plan for Carbody Shell- FEA | 08/09/2019 | 21/09/2019 | 29/08/2019 | 29/08/2019 | 0 | TK_Complete | -824745350 | 104 | -824745350_104
MML3RSTDES7670 | TT_Task | Preliminary Design: NONO/ NOWC from Project Manager - Preliminary Design Specification - Carbody Structure | 25/08/2019 | 25/08/2019 | 30/08/2019 | 30/08/2019 | 0 | TK_Complete | -824745350 | 133 | -824745350_133
MML3RSTDES7680 | TT_Task | Preliminary Design: NONO/ NOWC from Project Manager - Preliminary Design Specification - Saloon Interior | 25/08/2019 | 07/09/2019 | 11/08/2019 | 13/08/2019 | 0 | TK_Complete | -824745350 | 106 | -824745350_106
MML3RSTDES7690 | TT_Task | Preliminary Design: NONO/ NOWC from Project Manager - Preliminary Design Specification - Cab | 09/08/2019 | 09/08/2019 | 09/08/2019 | 09/08/2019 | 0 | TK_Complete | -824745350 | 142 | -824745350_142
MML3RSTDES7700 | TT_Task | Preliminary Design: NONO/ NOWC from Project Manager - Preliminary Design Sepcification - Equipment Mounting | 07/08/2019 | 07/08/2019 | 07/08/2019 | 07/08/2019 | 0 | TK_Complete | -824745350 | 108 | -824745350_108
MML3RSTDES7710 | TT_Task | Preliminary Design: NONO/ NOWC from Project Manager - Preliminay Design Specification - Couplers | 25/08/2019 | 07/09/2019 | 27/08/2019 | 27/08/2019 | 0 | TK_Complete | -824745350 | 142 | -824745350_142
MML3RSTDES7720 | TT_Task | Preliminary Design: NONO/ NOWC from Project Manager - Preliminary Design Specification - Gangway | 25/08/2019 | 07/09/2019 | 07/08/2019 | 07/08/2019 | 0 | TK_Complete | -824745350 | 142 | -824745350_142
MML3RSTDES7730 | TT_Task | Preliminary Design: NONO/ NOWC from Project Manager - Exterior and Interior Design book | 25/08/2019 | 07/09/2019 | 07/08/2019 | 07/08/2019 | 0 | TK_Complete | -824745350 | 110 | -824745350_110
MML3RSTDES7740 | TT_Task | Preliminary Design: NONO/ NOWC from Project Manager - Preliminary Simulator Plan | 25/08/2019 | 07/09/2019 | 30/08/2019 | 30/08/2019 | 0 | TK_Complete | -824745350 | 135 | -824745350_135
MML3RSTDES7750 | TT_Task | Preliminary Design: NONO/ NOWC from Project Manager - Maintainability Plan | 25/08/2019 | 07/09/2019 | 16/02/2019 | 01/03/2019 | 0 | TK_Complete | -824745350 | 52 | -824745350_52
MML3RSTDES7760 | TT_Task | Preliminary Design: NONO/ NOWC from Project Manager - Safety Assurance Plan | 25/08/2019 | 07/09/2019 | 22/12/2018 | 04/04/2019 | 0 | TK_Complete | -824745350 | 55 | -824745350_55
MML3RSTDES7770 | TT_Task | Preliminary Design: NONO/ NOWC from Project Manager - Reliability ; Availability Maintability Plan | 25/01/2019 | 18/02/2019 | 25/01/2019 | 18/02/2019 | 0 | TK_Complete | -824745350 | 136 | -824745350_136
MML3RSTDES7772 | TT_Task | Preliminary Design: NONO/ NOWC from Project Manager - List of Standards | 25/08/2019 | 07/09/2019 | 24/08/2019 | 06/09/2019 | 0 | TK_Complete | -824745350 | 52 | -824745350_52
MML3RSTDES7774 | TT_Task | Preliminary Design: NONO/ NOWC from Project Manager - Wayside Rolling Stock Monitoring and Measurement System | 25/08/2019 | 07/09/2019 | 28/08/2019 | 28/08/2019 | 0 | TK_Complete | -824745350 | 113 | -824745350_113
MML3RSTDES7776 | TT_Task | Preliminary Design: NONO/ NOWC from Project Manager - Computer based Maintenance Management System (CMMS) | 25/08/2019 | 07/09/2019 | 27/03/2019 | 27/03/2019 | 0 | TK_Complete | -824745350 | 137 | -824745350_137
MML3RSTDES1010 | TT_Task | Pre-final design: First submission by Alstom: Technical specfication and drawings of Driving gear ; coupling system | 11/01/2019 | 17/06/2019 | 11/01/2019 | 17/06/2019 | 0 | TK_Complete | -824745350 | 143 | -824745350_143
MML3RSTDES1020 | TT_Task | Pre-final design: First submission by Alstom: Technical drawings of Wheel flange lubricator | 11/01/2019 | 17/06/2019 | 11/01/2019 | 17/06/2019 | 0 | TK_Complete | -824745350 | 144 | -824745350_144
MML3RSTDES1030 | TT_Task | Pre-final design: First submission by Alstom: Air consumption calculations | 10/01/2019 | 17/06/2019 | 10/01/2019 | 17/06/2019 | 0 | TK_Complete | -824745350 | 145 | -824745350_145
MML3RSTDES1040 | TT_Task | Pre-final design: First submission by Alstom: Technical description and drawings of Passenger saloon door | 09/01/2019 | 17/06/2019 | 09/01/2019 | 17/06/2019 | 0 | TK_Complete | -824745350 | 146 | -824745350_146
MML3RSTDES1050 | TT_Task | Pre-final design: First submission by Alstom: Technical description and drawings of Front Detrainment doors | 09/01/2019 | 17/06/2019 | 09/01/2019 | 17/06/2019 | 0 | TK_Complete | -824745350 | 89 | -824745350_89
MML3RSTDES1060 | TT_Task | Pre-final design: First submission by Alstom: Technical Description and Drawings of 25 kV Vacuum Circuit Breaker | 10/01/2019 | 17/06/2019 | 10/01/2019 | 17/06/2019 | 0 | TK_Complete | -824745350 | 147 | -824745350_147
MML3RSTDES1070 | TT_Task | Pre-final design: First submission by Alstom: Technical Description and Drawings of Earthing Switch | 10/01/2019 | 17/06/2019 | 10/01/2019 | 17/06/2019 | 0 | TK_Complete | -824745350 | 148 | -824745350_148
MML3RSTDES1080 | TT_Task | Pre-final design: First submission by Alstom: Technical Description and Drawings of Surge Arrestor | 10/01/2019 | 17/06/2019 | 10/01/2019 | 17/06/2019 | 0 | TK_Complete | -824745350 | 149 | -824745350_149
MML3RSTDES1090 | TT_Task | Pre-final design: First submission by Alstom: Technical Description and Drawings of Traction Convertor | 10/01/2019 | 22/08/2019 | 10/01/2019 | 22/08/2019 | 0 | TK_Complete | -824745350 | 150 | -824745350_150
MML3RSTDES1100 | TT_Task | Pre-final design: First submission by Alstom: Technical Description and Drawings of Traction Motor | 11/01/2019 | 22/08/2019 | 11/01/2019 | 22/08/2019 | 0 | TK_Complete | -824745350 | 151 | -824745350_151
MML3RSTDES1110 | TT_Task | Pre-final design: First submission by Alstom: Technical Description and Drawings of Pantograph | 09/01/2019 | 16/09/2019 | 09/01/2019 | 16/09/2019 | 0 | TK_Complete | -824745350 | 91 | -824745350_91
MML3RSTDES1120 | TT_Task | Pre-final design: First submission by Alstom: Technical Description and Drawings of Transformer | 10/01/2019 | 22/08/2019 | 10/01/2019 | 22/08/2019 | 0 | TK_Complete | -824745350 | 152 | -824745350_152
MML3RSTDES1130 | TT_Task | Pre-final design: First submission by Alstom: Technical Specification and Drawings of Auxiliary Convertor | 09/01/2019 | 28/08/2019 | 09/01/2019 | 28/08/2019 | 0 | TK_Complete | -824745350 | 153 | -824745350_153
MML3RSTDES1140 | TT_Task | Pre-final design: First submission by Alstom: Technical Specification and Drawings of Battery Box | 09/01/2019 | 17/06/2019 | 09/01/2019 | 17/06/2019 | 0 | TK_Complete | -824745350 | 154 | -824745350_154
MML3RSTDES1150 | TT_Task | Pre-final design: First submission by Alstom: Technical Specification and Drawings of Battery Charger | 09/01/2019 | 04/09/2019 | 09/01/2019 | 04/09/2019 | 0 | TK_Complete | -824745350 | 155 | -824745350_155
MML3RSTDES1160 | TT_Task | Pre-final design: First submission by Alstom: Auxiliary Load Calculation for AC ; DC | 09/01/2019 | 19/08/2019 | 09/01/2019 | 19/08/2019 | 0 | TK_Complete | -824745350 | 156 | -824745350_156
MML3RSTDES1170 | TT_Task | Pre-final design: First submission by Alstom: Technical Description and Drawings of Saloon VAC | 09/01/2019 | 04/09/2019 | 09/01/2019 | 04/09/2019 | 0 | TK_Complete | -824745350 | 157 | -824745350_157
MML3RSTDES1180 | TT_Task | Pre-final design: First submission by Alstom: Technical specification ; Drawings of Lightings | 10/01/2019 | 17/06/2019 | 10/01/2019 | 17/06/2019 | 0 | TK_Complete | -824745350 | 94 | -824745350_94
MML3RSTDES1190 | TT_Task | Pre-final design: First submission by Alstom: Technical specification of Seconadary suspension | 11/01/2019 | 27/06/2019 | 11/01/2019 | 17/06/2019 | 0 | TK_Complete | -824745350 | 158 | -824745350_158
MML3RSTDES1200 | TT_Task | Pre-final design: First submission: Detailed Technical Description of Brake System (Including Brake Control Equipments) | 10/01/2019 | 19/08/2019 | 10/01/2019 | 19/08/2019 | 0 | TK_Complete | -824745350 | 118 | -824745350_118
MML3RSTDES1210 | TT_Task | Pre-final design: First submission by Alstom: Detailed Technical Description of Air Supply System | 09/01/2019 | 19/08/2019 | 09/01/2019 | 19/08/2019 | 0 | TK_Complete | -824745350 | 87 | -824745350_87
MML3RSTDES1220 | TT_Task | Pre-final design: First submission by Alstom: General arrangement for wheel slip detection and correction system | 10/01/2019 | 18/06/2019 | 10/01/2019 | 18/06/2019 | 0 | TK_Complete | -824745350 | 159 | -824745350_159
MML3RSTDES1230 | TT_Task | Pre-final design: First submission by Alstom:Heat Load Calculations | 09/01/2019 | 05/09/2019 | 09/01/2019 | 05/09/2019 | 0 | TK_Complete | -824745350 | 160 | -824745350_160
MML3RSTDES1240 | TT_Task | Pre-final design: First submission: Detailed Tech Description of Derailment Detection and Obstruction Deflection Device | 11/01/2019 | 08/03/2019 | 11/01/2019 | 28/08/2019 | 0 | TK_Complete | -824745350 | 161 | -824745350_161
MML3RSTDES1250 | TT_Task | Pre-final design: First submission by Alstom: Technical specification of TCMS | 08/01/2019 | 08/08/2019 | 08/01/2019 | 08/08/2019 | 0 | TK_Complete | -824745350 | 95 | -824745350_95
MML3RSTDES1260 | TT_Task | Pre-final design: First submission by Alstom: Technical Description and Drawings of Master Controller | 08/01/2019 | 08/08/2019 | 08/01/2019 | 08/08/2019 | 0 | TK_Complete | -824745350 | 162 | -824745350_162
MML3RSTDES1270 | TT_Task | Pre-final design: First submission by Alstom: Functional description of PACIS system | 08/01/2019 | 09/09/2019 | 08/01/2019 | 09/09/2019 | 0 | TK_Complete | -824745350 | 96 | -824745350_96
MML3RSTDES1280 | TT_Task | Pre-final design: First submission by Alstom: Carbody Structure Detailed FEA Report | 10/01/2019 | 23/09/2019 | 10/01/2019 | 23/09/2019 | 0 | TK_Complete | -824745350 | 163 | -824745350_163
MML3RSTDES1290 | TT_Task | Pre-final design: First submission by Alstom: Carbody crashworthiness report | 09/01/2019 | 23/09/2019 | 09/01/2019 | 23/09/2019 | 0 | TK_Complete | -824745350 | 164 | -824745350_164
MML3RSTDES1300 | TT_Task | Pre-final design: First submission by Alstom: Detailed Design Specification - Carbody Structure | 09/01/2019 | 20/09/2019 | 09/01/2019 | 20/09/2019 | 0 | TK_Complete | -824745350 | 105 | -824745350_105
MML3RSTDES1310 | TT_Task | Pre-final design: First submission by Alstom: Weight distribution calculations report | 08/09/2019 | 23/09/2019 | 08/09/2019 | 23/09/2019 | 0 | TK_Complete | -824745350 | 102 | -824745350_102
MML3RSTDES1320 | TT_Task | Pre-final design: First submission by Alstom:Car End clearance | 09/01/2019 | 20/08/2019 | 09/01/2019 | 20/08/2019 | 0 | TK_Complete | -824745350 | 84 | -824745350_84
MML3RSTDES1330 | TT_Task | Pre-final design: First submission by Alstom:Noise Report - Preliminary Specification ; Prediction | 15/01/2019 | 12/06/2019 | 15/01/2019 | 12/06/2019 | 0 | TK_Complete | -824745350 | 103 | -824745350_103
MML3RSTDES1340 | TT_Task | Pre-final design: First submission by Alstom:Final Kinematic Envelope Calculation Report | 26/07/2019 | 30/09/2019 | 26/07/2019 | 30/09/2019 | 0 | TK_Complete | -824745350 | 101 | -824745350_101
MML3RSTDES1350 | TT_Task | Pre-final design: First submission by Alstom: Ergonomic reports for cab - Visibility study report, Driver Desk | 08/01/2019 | 21/08/2019 | 08/01/2019 | 21/08/2019 | 0 | TK_Complete | -824745350 | 165 | -824745350_165
MML3RSTDES1360 | TT_Task | Pre-final design: First submission by Alstom: Ergonomic report for saloon | 08/01/2019 | 21/08/2019 | 08/01/2019 | 21/08/2019 | 0 | TK_Complete | -824745350 | 166 | -824745350_166
MML3RSTDES1370 | TT_Task | Pre-final design: First submission by Alstom: Climate Comfort Prediction report | 09/01/2019 | 12/06/2019 | 09/01/2019 | 12/06/2019 | 0 | TK_Complete | -824745350 | 167 | -824745350_167
MML3RSTDES1380 | TT_Task | Pre-final design: First submission by Alstom: Detailed Design Specification- Partition Wall | 10/01/2019 | 30/09/2019 | 10/01/2019 | 30/09/2019 | 0 | TK_Complete | -824745350 | 168 | -824745350_168
MML3RSTDES1390 | TT_Task | Pre-final design: First submission by Alstom: Detailed Design Specification - Saloon Interior | 08/09/2019 | 30/09/2019 | 08/09/2019 | 30/09/2019 | 0 | TK_Complete | -824745350 | 106 | -824745350_106
MML3RSTDES1400 | TT_Task | Pre-final design: First submission by Alstom: Detailed Design Specification - Cab | 08/09/2019 | 26/09/2019 | 08/09/2019 | 26/09/2019 | 0 | TK_Complete | -824745350 | 107 | -824745350_107
MML3RSTDES1410 | TT_Task | Pre-final design: First submission by Alstom: Detailed Design Specification - Signage and labelling | 10/01/2019 | 12/06/2019 | 10/01/2019 | 12/06/2019 | 0 | TK_Complete | -824745350 | 169 | -824745350_169
MML3RSTDES1420 | TT_Task | Pre-final design: First submission by Alstom: Collision and Energy Absorption Calculation Report of Coupler System | 06/12/2018 | 24/09/2019 | 06/12/2018 | 24/09/2019 | 0 | TK_Complete | -824745350 | 170 | -824745350_170
MML3RSTDES1430 | TT_Task | Pre-final design: First submission by Alstom: Detailed Design Specification -Couplers | 10/01/2019 | 18/06/2019 | 10/01/2019 | 18/06/2019 | 0 | TK_Complete | -824745350 | 109 | -824745350_109
MML3RSTDES1440 | TT_Task | Pre-final design: First submission by Alstom: Gangway ; Coupler Movement Analysis | 10/01/2019 | 24/09/2019 | 10/01/2019 | 24/09/2019 | 0 | TK_Complete | -824745350 | 171 | -824745350_171
MML3RSTDES1450 | TT_Task | Pre-final design: First submission by Alstom: Detailed Design Specification - Gangway | 09/01/2019 | 18/06/2019 | 09/01/2019 | 18/06/2019 | 0 | TK_Complete | -824745350 | 107 | -824745350_107
MML3RSTDES1460 | TT_Task | Pre-final design: First submission by Alstom: Equipment Mounting Detailed Design Specification (Roof, Underframe) | 08/09/2019 | 23/09/2019 | 08/09/2019 | 23/09/2019 | 0 | TK_Complete | -824745350 | 172 | -824745350_172
MML3RSTDES1470 | TT_Task | Pre-final design: First submission by Alstom: Detailed Design Specification - Pneumatic Piping | 08/01/2019 | 12/06/2019 | 08/01/2019 | 12/06/2019 | 0 | TK_Complete | -824745350 | 173 | -824745350_173
MML3RSTDES1480 | TT_Task | Pre-final design: First submission by Alstom: Training Programme | 10/01/2019 | 23/05/2019 | 10/01/2019 | 23/05/2019 | 0 | TK_Complete | -824745350 | 174 | -824745350_174
MML3RSTDES1490 | TT_Task | Pre-final design: First submission by Alstom: Preliminary Hazard Analysis (PHA) | 06/12/2018 | 27/03/2019 | 06/12/2018 | 27/03/2019 | 0 | TK_Complete | -824745350 | 175 | -824745350_175
MML3RSTDES1500 | TT_Task | Pre-final design: First submission by Alstom: Interface hazard analysis (IHA) | 14/03/2019 | 21/03/2019 | 17/05/2019 | 24/05/2019 | 0 | TK_Complete | -824745350 | 175 | -824745350_175
MML3RSTDES1510 | TT_Task | Pre-final design: First submission by Alstom: Subsystem hazard analysis (SSHA) | 06/12/2018 | 01/01/2019 | 06/12/2018 | 01/01/2019 | 0 | TK_Complete | -824745350 | 175 | -824745350_175
MML3RSTDES1520 | TT_Task | Pre-final design: First submission by Alstom: Operation and Support Hazard Analysis (OSHA) | 06/12/2018 | 26/03/2019 | 06/12/2018 | 26/03/2019 | 0 | TK_Complete | -824745350 | 175 | -824745350_175
MML3RSTDES1580 | TT_Task | Pre-final design: First submission by Alstom: Reliability Apportionment and Prediction Report | 11/12/2018 | 17/05/2019 | 11/12/2018 | 17/05/2019 | 0 | TK_Complete | -824745350 | 112 | -824745350_112
MML3RSTDES1590 | TT_Task | Pre-final design: First submission by Alstom: RAM Testing Plan | 11/12/2018 | 01/01/2019 | 11/12/2018 | 01/01/2019 | 0 | TK_Complete | -824745350 | 29 | -824745350_29
MML3RSTDES8190 | TT_Task | Pre-final design: First submission by Alstom: Sub system Safety Requirement Specification | 06/12/2018 | 26/03/2019 | 06/12/2018 | 26/03/2019 | 0 | TK_Complete | -824745350 | 18 | -824745350_18
MML3RSTDES8330 | TT_Task | Pre-final design: First submission by Alstom: Computer based Maintenance Management System (CMMS) | 31/08/2019 | 02/12/2019 | 31/08/2019 | 02/12/2019 | 0 | TK_Complete | -824745350 | 114 | -824745350_114
MML3RSTDES1530 | TT_Task | Pre-final Design Review/ Comments from Project Manager: Technical specfication and drawings of Driving gear ; coupling s | 18/06/2019 | 27/06/2019 | 18/06/2019 | 27/06/2019 | 0 | TK_Complete | -824745350 | 143 | -824745350_143
MML3RSTDES1540 | TT_Task | Pre-final Design Review/ Comments from Project Manager: Technical drawings of Wheel flange lubricator | 18/06/2019 | 27/06/2019 | 18/06/2019 | 27/06/2019 | 0 | TK_Complete | -824745350 | 144 | -824745350_144
MML3RSTDES1550 | TT_Task | Pre-final Design Review/ Comments from Project Manager: Air consumption calculations | 18/06/2019 | 26/06/2019 | 18/06/2019 | 26/06/2019 | 0 | TK_Complete | -824745350 | 145 | -824745350_145
MML3RSTDES1560 | TT_Task | Pre-final Design Review/ Comments from Project Manager: Technical description and drawings of Passenger saloon door | 19/06/2019 | 03/07/2019 | 19/06/2019 | 03/07/2019 | 0 | TK_Complete | -824745350 | 146 | -824745350_146
MML3RSTDES1570 | TT_Task | Pre-final Design Review/ Comments from Project Manager: Technical description and drawings of Front Detrainment doors | 18/06/2019 | 02/07/2019 | 18/06/2019 | 02/07/2019 | 0 | TK_Complete | -824745350 | 121 | -824745350_121
MML3RSTDES1600 | TT_Task | Pre-final Design Review/ Comments from Project Manager: Technical Description and Drawings of 25 kV Vacuum Circuit Break | 18/06/2019 | 05/07/2019 | 18/06/2019 | 05/07/2019 | 0 | TK_Complete | -824745350 | 147 | -824745350_147
MML3RSTDES1610 | TT_Task | Pre-final Design Review/ Comments from Project Manager: Technical Description and Drawings of Earthing Switch | 18/06/2019 | 28/06/2019 | 18/06/2019 | 28/06/2019 | 0 | TK_Complete | -824745350 | 148 | -824745350_148
MML3RSTDES1620 | TT_Task | Pre-final Design Review/ Comments from Project Manager: Technical Description and Drawings of Surge Arrestor | 18/06/2019 | 28/06/2019 | 18/06/2019 | 28/06/2019 | 0 | TK_Complete | -824745350 | 149 | -824745350_149
MML3RSTDES1630 | TT_Task | Pre-final Design Review/ Comments from Project Manager: Technical Description and Drawings of Traction Convertor | 23/08/2019 | 07/09/2019 | 23/08/2019 | 07/09/2019 | 0 | TK_Complete | -824745350 | 150 | -824745350_150
MML3RSTDES1640 | TT_Task | Pre-final Design Review/ Comments from Project Manager: Technical Description and Drawings of Traction Motor | 23/08/2019 | 05/09/2019 | 23/08/2019 | 05/09/2019 | 0 | TK_Complete | -824745350 | 151 | -824745350_151
MML3RSTDES1650 | TT_Task | Pre-final Design Review/ Comments from Project Manager: Technical Description and Drawings of Pantograph | 17/09/2019 | 24/09/2019 | 17/09/2019 | 24/09/2019 | 0 | TK_Complete | -824745350 | 123 | -824745350_123
MML3RSTDES1660 | TT_Task | Pre-final Design Review/ Comments from Project Manager: Technical Description and Drawings of Transformer | 23/08/2019 | 30/08/2019 | 23/08/2019 | 30/08/2019 | 0 | TK_Complete | -824745350 | 176 | -824745350_176
MML3RSTDES1670 | TT_Task | Pre-final Design Review/ Comments from Project Manager: Technical Specification and Drawings of Auxiliary Convertor | 29/08/2019 | 13/09/2019 | 29/08/2019 | 13/09/2019 | 0 | TK_Complete | -824745350 | 153 | -824745350_153
MML3RSTDES1680 | TT_Task | Pre-final Design Review/ Comments from Project Manager: Technical Specification and Drawings of Battery Box | 18/06/2019 | 28/06/2019 | 18/06/2019 | 28/06/2019 | 0 | TK_Complete | -824745350 | 154 | -824745350_154
MML3RSTDES1690 | TT_Task | Pre-final Design Review/ Comments from Project Manager: Technical Specification and Drawings of Battery Charger | 05/09/2019 | 16/10/2019 | 05/09/2019 | 19/09/2019 | 0 | TK_Complete | -824745350 | 155 | -824745350_155
MML3RSTDES1700 | TT_Task | Pre-final Design Review/ Comments from Project Manager: Auxiliary Load Calculation for AC ; DC | 20/08/2019 | 29/08/2019 | 20/08/2019 | 29/08/2019 | 0 | TK_Complete | -824745350 | 156 | -824745350_156
MML3RSTDES1710 | TT_Task | Pre-final Design Review/ Comments from Project Manager: Technical Description and Drawings of Saloon VAC | 05/09/2019 | 16/09/2019 | 05/09/2019 | 16/09/2019 | 0 | TK_Complete | -824745350 | 157 | -824745350_157
MML3RSTDES1720 | TT_Task | Pre-final Design Review/ Comments from Project Manager: Technical specification ; Drawings of Lightings | 18/06/2019 | 09/07/2019 | 18/06/2019 | 09/07/2019 | 0 | TK_Complete | -824745350 | 126 | -824745350_126
MML3RSTDES1730 | TT_Task | Pre-final Design Review/ Comments from Project Manager: Technical specification of Seconadary suspension | 18/06/2019 | 27/06/2019 | 18/06/2019 | 27/06/2019 | 0 | TK_Complete | -824745350 | 158 | -824745350_158
MML3RSTDES1740 | TT_Task | Pre-final Design Review/ Comments from Project Manager: Detailed Technical Description of Brake System | 20/08/2019 | 28/08/2019 | 20/08/2019 | 28/08/2019 | 0 | TK_Complete | -824745350 | 118 | -824745350_118
MML3RSTDES1750 | TT_Task | Pre-final Design Review/ Comments from Project Manager: Detailed Technical Description of Air Supply System | 20/08/2019 | 28/08/2019 | 20/08/2019 | 28/08/2019 | 0 | TK_Complete | -824745350 | 119 | -824745350_119
MML3RSTDES1760 | TT_Task | Pre-final Design Review/ Comments from Project Manager: General arrangement for wheel slip detection and correction syst | 19/06/2019 | 28/06/2019 | 19/06/2019 | 28/06/2019 | 0 | TK_Complete | -824745350 | 159 | -824745350_159
MML3RSTDES1770 | TT_Task | Pre-final Design Review/ Comments from Project Manager: Heat Load Calculations | 06/09/2019 | 19/09/2019 | 06/09/2019 | 19/09/2019 | 0 | TK_Complete | -824745350 | 160 | -824745350_160
MML3RSTDES1780 | TT_Task | Pre-final Design Review/ Comments from Project Manager: Detailed Description of Derailment Detection and Obstruction Def | 29/08/2019 | 07/09/2019 | 29/08/2019 | 07/09/2019 | 0 | TK_Complete | -824745350 | 161 | -824745350_161
MML3RSTDES1790 | TT_Task | Pre-final Design Review/ Comments from Project Manager: Technical specification of TCMS | 09/08/2019 | 21/08/2019 | 09/08/2019 | 21/08/2019 | 0 | TK_Complete | -824745350 | 127 | -824745350_127
MML3RSTDES1800 | TT_Task | Pre-final Design Review/ Comments from Project Manager: Technical Description and Drawings of Master Controller | 09/08/2019 | 21/08/2019 | 09/08/2019 | 21/08/2019 | 0 | TK_Complete | -824745350 | 177 | -824745350_177
MML3RSTDES1810 | TT_Task | Pre-final Design Review/ Comments from Project Manager: Functional description of PAPIS system | 10/09/2019 | 24/09/2019 | 10/09/2019 | 24/09/2019 | 0 | TK_Complete | -824745350 | 128 | -824745350_128
MML3RSTDES1820 | TT_Task | Pre-final Design Review/ Comments from Project Manager: Carbody Structure Detailed FEA Report | 24/09/2019 | 15/10/2019 | 24/09/2019 | 15/10/2019 | 0 | TK_Complete | -824745350 | 163 | -824745350_163
MML3RSTDES1830 | TT_Task | Pre-final Design Review/ Comments from Project Manager: Carbody crashworthiness report | 24/09/2019 | 10/10/2019 | 24/09/2019 | 10/10/2019 | 0 | TK_Complete | -824745350 | 164 | -824745350_164
MML3RSTDES1840 | TT_Task | Pre-final Design Review/ Comments from Project Manager: Detailed Design Specification - Carbody Structure | 21/09/2019 | 05/10/2019 | 21/09/2019 | 05/10/2019 | 0 | TK_Complete | -824745350 | 133 | -824745350_133
MML3RSTDES1850 | TT_Task | Pre-final Design Review/ Comments from Project Manager: Weight distribution calculations report | 24/09/2019 | 04/10/2019 | 24/09/2019 | 04/10/2019 | 0 | TK_Complete | -824745350 | 131 | -824745350_131
MML3RSTDES1860 | TT_Task | Pre-final Design Review/ Comments from Project Manager: Car End clearance | 21/08/2019 | 28/08/2019 | 21/08/2019 | 28/08/2019 | 0 | TK_Complete | -824745350 | 178 | -824745350_178
MML3RSTDES1870 | TT_Task | Pre-final Design Review/ Comments from Project Manager: Noise Report - Preliminary Specification ; Prediction | 13/06/2019 | 24/06/2019 | 13/06/2019 | 24/06/2019 | 0 | TK_Complete | -824745350 | 179 | -824745350_179
MML3RSTDES1880 | TT_Task | Pre-final Design Review/ Comments from Project Manager: Final Kinematic Envelope Calculation Report | 01/10/2019 | 10/10/2019 | 01/10/2019 | 10/10/2019 | 0 | TK_Complete | -824745350 | 130 | -824745350_130
MML3RSTDES1890 | TT_Task | Pre-final Design Review/ Comments from Project Manager: Ergonomic reports for cab - Visibility study report, Driver Desk | 22/08/2019 | 03/09/2019 | 22/08/2019 | 03/09/2019 | 0 | TK_Complete | -824745350 | 165 | -824745350_165
MML3RSTDES1900 | TT_Task | Pre-final Design Review/ Comments from Project Manager: Ergonomic report for saloon | 22/08/2019 | 28/08/2019 | 22/08/2019 | 28/08/2019 | 0 | TK_Complete | -824745350 | 166 | -824745350_166
MML3RSTDES1910 | TT_Task | Pre-final Design Review/ Comments from Project Manager: Climate Comfort Prediction report | 13/06/2019 | 21/06/2019 | 13/06/2019 | 21/06/2019 | 0 | TK_Complete | -824745350 | 167 | -824745350_167
MML3RSTDES1920 | TT_Task | Pre-final Design Review/ Comments from Project Manager: Detailed Design Specification- Partition Wall | 01/10/2019 | 09/10/2019 | 01/10/2019 | 09/10/2019 | 0 | TK_Complete | -824745350 | 168 | -824745350_168
MML3RSTDES1930 | TT_Task | Pre-final Design Review/ Comments from Project Manager: Detailed Design Specification - Saloon Interior | 01/10/2019 | 14/10/2019 | 01/10/2019 | 14/10/2019 | 0 | TK_Complete | -824745350 | 106 | -824745350_106
MML3RSTDES1940 | TT_Task | Pre-final Design Review/ Comments from Project Manager: Detailed Design Specification - Cab | 27/09/2019 | 09/10/2019 | 27/09/2019 | 09/10/2019 | 0 | TK_Complete | -824745350 | 134 | -824745350_134
MML3RSTDES1950 | TT_Task | Pre-final Design Review/ Comments from Project Manager: Detailed Design Specification - Signage and labelling | 13/06/2019 | 24/06/2019 | 13/06/2019 | 24/06/2019 | 0 | TK_Complete | -824745350 | 169 | -824745350_169
MML3RSTDES1960 | TT_Task | Pre-final Design Review/ Comments from Project Manager: Collision and Energy Absorption Calculation Report of Coupler Sy | 25/09/2019 | 14/10/2019 | 25/09/2019 | 14/10/2019 | 0 | TK_Complete | -824745350 | 170 | -824745350_170
MML3RSTDES1970 | TT_Task | Pre-final Design Review/ Comments from Project Manager: Detailed Design Specification -Couplers | 19/06/2019 | 04/07/2019 | 19/06/2019 | 04/07/2019 | 0 | TK_Complete | -824745350 | 134 | -824745350_134
MML3RSTDES1980 | TT_Task | Pre-final Design Review/ Comments from Project Manager: Gangway ; Coupler Movement Analysis | 25/09/2019 | 14/10/2019 | 25/09/2019 | 14/10/2019 | 0 | TK_Complete | -824745350 | 180 | -824745350_180
MML3RSTDES1990 | TT_Task | Pre-final Design Review/ Comments from Project Manager: Detailed Design Specification - Gangway | 19/06/2019 | 05/07/2019 | 19/06/2019 | 05/07/2019 | 0 | TK_Complete | -824745350 | 134 | -824745350_134
MML3RSTDES2000 | TT_Task | Pre-final Design Review/ Comments from Project Manager: Equipment Mounting Detailed Design Specification (Roof, Underfra | 24/09/2019 | 09/10/2019 | 24/09/2019 | 09/10/2019 | 0 | TK_Complete | -824745350 | 172 | -824745350_172
MML3RSTDES2010 | TT_Task | Pre-final Design Review/ Comments from Project Manager: Detailed Design Specification - Pneumatic Piping | 13/06/2019 | 26/06/2019 | 13/06/2019 | 26/06/2019 | 0 | TK_Complete | -824745350 | 173 | -824745350_173
MML3RSTDES2020 | TT_Task | Pre-final Design Review/ Comments from Project Manager: Training Programme | 24/05/2019 | 04/06/2019 | 24/05/2019 | 04/06/2019 | 0 | TK_Complete | -824745350 | 38 | -824745350_38
MML3RSTDES2030 | TT_Task | Pre-final Design Review/ Comments from Project Manager: Preliminary Hazard Analysis (PHA) | 28/03/2019 | 08/05/2019 | 28/03/2019 | 08/05/2019 | 0 | TK_Complete | -824745350 | 47 | -824745350_47
MML3RSTDES2040 | TT_Task | Pre-final Design Review/ Comments from Project Manager: Interface hazard analysis (IHA) | 25/05/2019 | 12/06/2019 | 25/05/2019 | 12/06/2019 | 0 | TK_Complete | -824745350 | 58 | -824745350_58
MML3RSTDES2050 | TT_Task | Pre-final Design Review/ Comments from Project Manager: Subsystem hazard analysis (SSHA) | 02/01/2019 | 16/10/2019 | 02/01/2019 | 16/10/2019 | 0 | TK_Complete | -824745350 | 47 | -824745350_47
MML3RSTDES2060 | TT_Task | Pre-final Design Review/ Comments from Project Manager: Operation and Support Hazard Analysis (OSHA) | 27/03/2019 | 08/05/2019 | 27/03/2019 | 08/05/2019 | 0 | TK_Complete | -824745350 | 47 | -824745350_47
MML3RSTDES2070 | TT_Task | Pre-final Design Review/ Comments from Project Manager: Reliability Apportionment and Prediction Report | 18/05/2019 | 04/06/2019 | 18/05/2019 | 04/06/2019 | 0 | TK_Complete | -824745350 | 136 | -824745350_136
MML3RSTDES2130 | TT_Task | Pre-final Design Review/ Comments from Project Manager: RAM Testing Plan | 02/01/2019 | 11/10/2019 | 02/01/2019 | 11/10/2019 | 0 | TK_Complete | -824745350 | 46 | -824745350_46
MML3RSTDES8200 | TT_Task | Pre-final Design Review/ Comments from Project Manager: Sub system Safety Requirement Specification | 27/03/2019 | 10/04/2019 | 27/03/2019 | 10/04/2019 | 0 | TK_Complete | -824745350 | 181 | -824745350_181
MML3RSTDES8340 | TT_Task | Pre-final Design Review/ Comments from Project Manager: Computer based Maintenance Management System (CMMS) | 03/12/2019 | 07/12/2019 | 03/12/2019 | 07/12/2019 | 0 | TK_Complete | -824745350 | 137 | -824745350_137
MML3RSTDES2080 | TT_Task | Pre-final Design Resubmission by Alstom: Technical specfication and drawings of Driving gear ; coupling system | 04/09/2019 | 17/09/2019 | 28/06/2019 | 05/12/2019 | 0 | TK_Complete | -824745350 | 143 | -824745350_143
MML3RSTDES2090 | TT_Task | Pre-final Design Resubmission by Alstom: Technical drawings of Wheel flange lubricator | 28/06/2019 | 23/01/2020 | 28/06/2019 | 23/01/2020 | 0 | TK_Complete | -824745350 | 144 | -824745350_144
MML3RSTDES2100 | TT_Task | Pre-final Design Resubmission by Alstom: Air consumption calculations | 27/06/2019 | 12/11/2019 | 27/06/2019 | 12/11/2019 | 0 | TK_Complete | -824745350 | 145 | -824745350_145
MML3RSTDES2110 | TT_Task | Pre-final Design Resubmission by Alstom: Technical description and drawings of Passenger saloon door | 04/07/2019 | 19/04/2020 | 04/07/2019 | 19/04/2020 | 0 | TK_Complete | -824745350 | 146 | -824745350_146
MML3RSTDES2120 | TT_Task | Pre-final Design Resubmission by Alstom: Technical description and drawings of Front Detrainment doors | 03/07/2019 | 16/07/2019 | 03/07/2019 | 26/11/2019 | 0 | TK_Complete | -824745350 | 89 | -824745350_89
MML3RSTDES2140 | TT_Task | Pre-final Design Resubmission by Alstom: Technical Description and Drawings of 25 kV Vacuum Circuit Breaker | 06/07/2019 | 28/11/2019 | 06/07/2019 | 28/11/2019 | 0 | TK_Complete | -824745350 | 147 | -824745350_147
MML3RSTDES2150 | TT_Task | Pre-final Design Resubmission by Alstom: Technical Description and Drawings of Earthing Switch | 29/06/2019 | 28/11/2019 | 29/06/2019 | 28/11/2019 | 0 | TK_Complete | -824745350 | 148 | -824745350_148
MML3RSTDES2160 | TT_Task | Pre-final Design Resubmission by Alstom: Technical Description and Drawings of Surge Arrestor | 29/06/2019 | 28/11/2019 | 29/06/2019 | 28/11/2019 | 0 | TK_Complete | -824745350 | 149 | -824745350_149
MML3RSTDES2170 | TT_Task | Pre-final Design Resubmission by Alstom: Technical Description and Drawings of Traction Convertor | 09/09/2019 | 12/02/2020 | 09/09/2019 | 12/02/2020 | 0 | TK_Complete | -824745350 | 150 | -824745350_150
MML3RSTDES2180 | TT_Task | Pre-final Design Resubmission by Alstom: Technical Description and Drawings of Traction Motor | 06/09/2019 | 04/02/2020 | 06/09/2019 | 04/02/2020 | 0 | TK_Complete | -824745350 | 151 | -824745350_151
MML3RSTDES2190 | TT_Task | Pre-final Design Resubmission by Alstom: Technical Description and Drawings of Pantograph | 25/09/2019 | 04/02/2020 | 25/09/2019 | 04/02/2020 | 0 | TK_Complete | -824745350 | 91 | -824745350_91
MML3RSTDES2200 | TT_Task | Pre-final Design Resubmission by Alstom: Technical Description and Drawings of Transformer | 31/08/2019 | 05/02/2020 | 31/08/2019 | 05/02/2020 | 0 | TK_Complete | -824745350 | 152 | -824745350_152
MML3RSTDES2210 | TT_Task | Pre-final Design Resubmission by Alstom: Technical Specification and Drawings of Auxiliary Convertor | 14/09/2019 | 10/04/2020 | 14/09/2019 | 10/04/2020 | 0 | TK_Complete | -824745350 | 153 | -824745350_153
MML3RSTDES2220 | TT_Task | Pre-final Design Resubmission by Alstom: Technical Specification and Drawings of Battery Box | 29/06/2019 | 04/04/2020 | 29/06/2019 | 04/04/2020 | 0 | TK_Complete | -824745350 | 154 | -824745350_154
MML3RSTDES2230 | TT_Task | Pre-final Design Resubmission by Alstom: Technical Specification and Drawings of Battery Charger | 16/10/2019 | 17/10/2019 | 20/09/2019 | 16/10/2019 | 0 | TK_Complete | -824745350 | 155 | -824745350_155
MML3RSTDES2240 | TT_Task | Pre-final Design Resubmission by Alstom: Auxiliary Load Calculation for AC ; DC | 16/10/2019 | 17/10/2019 | 30/08/2019 | 16/10/2019 | 0 | TK_Complete | -824745350 | 156 | -824745350_156
MML3RSTDES2250 | TT_Task | Pre-final Design Resubmission by Alstom: Technical Description and Drawings of Saloon VAC | 17/09/2019 | 02/12/2019 | 17/09/2019 | 02/12/2019 | 0 | TK_Complete | -824745350 | 157 | -824745350_157
MML3RSTDES2260 | TT_Task | Pre-final Design Resubmission by Alstom: Technical specification ; Drawings of Lightings | 10/07/2019 | 06/02/2020 | 10/07/2019 | 06/02/2020 | 0 | TK_Complete | -824745350 | 94 | -824745350_94
MML3RSTDES2270 | TT_Task | Pre-final Design Resubmission by Alstom: Technical specification of Seconadary suspension | 28/06/2019 | 09/12/2019 | 28/06/2019 | 09/12/2019 | 0 | TK_Complete | -824745350 | 158 | -824745350_158
MML3RSTDES2280 | TT_Task | Pre-final Design Resubmission by Alstom: Detailed Technical Description of Brake System | 29/08/2019 | 11/09/2019 | 29/08/2019 | 16/09/2020 | 0 | TK_Complete | -824745350 | 86 | -824745350_86
MML3RSTDES2290 | TT_Task | Pre-final Design Resubmission by Alstom: Detailed Technical Description of Air Supply System | 28/08/2019 | 30/12/2019 | 28/08/2019 | 30/12/2019 | 0 | TK_Complete | -824745350 | 87 | -824745350_87
MML3RSTDES2300 | TT_Task | Pre-final Design Resubmission by Alstom: General arrangement for wheel slip detection and correction system | 29/06/2019 | 30/12/2019 | 29/06/2019 | 30/12/2019 | 0 | TK_Complete | -824745350 | 159 | -824745350_159
MML3RSTDES2310 | TT_Task | Pre-final Design Resubmission by Alstom: Heat Load Calculations | 20/09/2019 | 02/12/2019 | 20/09/2019 | 02/12/2019 | 0 | TK_Complete | -824745350 | 160 | -824745350_160
MML3RSTDES2320 | TT_Task | Pre-final Design Resubmission by Alstom: Tech Description of Derailment Detection and Obstruction Deflection Device | 09/09/2019 | 28/07/2020 | 09/09/2019 | 28/07/2020 | 0 | TK_Complete | -824745350 | 161 | -824745350_161
MML3RSTDES2330 | TT_Task | Pre-final Design Resubmission by Alstom: Technical specification of TCMS | 22/08/2019 | 22/04/2020 | 22/08/2019 | 22/04/2020 | 0 | TK_Complete | -824745350 | 95 | -824745350_95
MML3RSTDES2340 | TT_Task | Pre-final Design Resubmission by Alstom: Technical Description and Drawings of Master Controller | 22/08/2019 | 05/02/2020 | 22/08/2019 | 05/02/2020 | 0 | TK_Complete | -824745350 | 162 | -824745350_162
MML3RSTDES2350 | TT_Task | Pre-final Design Resubmission by Alstom: Functional description of PAPIS system | 25/09/2019 | 29/06/2020 | 25/09/2019 | 29/06/2020 | 0 | TK_Complete | -824745350 | 138 | -824745350_138
MML3RSTDES2360 | TT_Task | Pre-final Design Resubmission by Alstom: Carbody Structure Detailed FEA Report | 16/10/2019 | 05/12/2019 | 16/10/2019 | 05/12/2019 | 0 | TK_Complete | -824745350 | 163 | -824745350_163
MML3RSTDES2370 | TT_Task | Pre-final Design Resubmission by Alstom: Carbody crashworthiness report | 11/10/2019 | 24/10/2019 | 11/10/2019 | 25/11/2019 | 0 | TK_Complete | -824745350 | 164 | -824745350_164
MML3RSTDES2380 | TT_Task | Pre-final Design Resubmission by Alstom: Detailed Design Specification - Carbody Structure | 07/10/2019 | 20/10/2019 | 07/10/2019 | 25/11/2019 | 0 | TK_Complete | -824745350 | 105 | -824745350_105
MML3RSTDES2390 | TT_Task | Pre-final Design Resubmission by Alstom: Weight distribution calculations report | 05/10/2019 | 25/11/2019 | 05/10/2019 | 25/11/2019 | 0 | TK_Complete | -824745350 | 102 | -824745350_102
MML3RSTDES2400 | TT_Task | Pre-final Design Resubmission by Alstom: Car End clearance | 29/08/2019 | 07/12/2019 | 29/08/2019 | 07/12/2019 | 0 | TK_Complete | -824745350 | 84 | -824745350_84
MML3RSTDES2410 | TT_Task | Pre-final Design Resubmission by Alstom: Noise Report - Preliminary Specification ; Prediction | 25/06/2019 | 24/07/2020 | 25/06/2019 | 24/07/2020 | 0 | TK_Complete | -824745350 | 103 | -824745350_103
MML3RSTDES2420 | TT_Task | Pre-final Design Resubmission by Alstom: Final Kinematic Envelope Calculation Report | 11/10/2019 | 14/10/2019 | 11/10/2019 | 25/11/2019 | 0 | TK_Complete | -824745350 | 101 | -824745350_101
MML3RSTDES2430 | TT_Task | Pre-final Design Resubmission by Alstom: Ergonomic reports for cab - Visibility study report, Driver Desk | 04/09/2019 | 30/11/2019 | 04/09/2019 | 30/11/2019 | 0 | TK_Complete | -824745350 | 165 | -824745350_165
MML3RSTDES2440 | TT_Task | Pre-final Design Resubmission by Alstom: Ergonomic report for saloon | 18/10/2019 | 19/10/2019 | 29/08/2019 | 18/10/2019 | 0 | TK_Complete | -824745350 | 166 | -824745350_166
MML3RSTDES2450 | TT_Task | Pre-final Design Resubmission by Alstom: Climate Comfort Prediction report | 21/08/2019 | 07/10/2019 | 22/06/2019 | 22/10/2019 | 0 | TK_Complete | -824745350 | 167 | -824745350_167
MML3RSTDES2460 | TT_Task | Pre-final Design Resubmission by Alstom: Detailed Design Specification- Partition Wall | 10/10/2019 | 10/06/2020 | 10/10/2019 | 10/06/2020 | 0 | TK_Complete | -824745350 | 168 | -824745350_168
MML3RSTDES2470 | TT_Task | Pre-final Design Resubmission by Alstom: Detailed Design Specification - Saloon Interior | 15/10/2019 | 28/10/2019 | 15/10/2019 | 18/09/2020 | 0 | TK_Complete | -824745350 | 106 | -824745350_106
MML3RSTDES2480 | TT_Task | Pre-final Design Resubmission by Alstom: Detailed Design Specification - Cab | 10/10/2019 | 31/12/2019 | 10/10/2019 | 31/12/2019 | 0 | TK_Complete | -824745350 | 107 | -824745350_107
MML3RSTDES2490 | TT_Task | Pre-final Design Resubmission by Alstom: Detailed Design Specification - Signage and labelling | 25/06/2019 | 26/11/2019 | 25/06/2019 | 26/11/2019 | 0 | TK_Complete | -824745350 | 169 | -824745350_169
MML3RSTDES2500 | TT_Task | Pre-final Design Resubmission by Alstom: Collision and Energy Absorption Calculation Report of Coupler System | 15/10/2019 | 28/10/2019 | 15/10/2019 | 25/11/2019 | 0 | TK_Complete | -824745350 | 170 | -824745350_170
MML3RSTDES2510 | TT_Task | Pre-final Design Resubmission by Alstom: Detailed Design Specification -Couplers | 05/07/2019 | 18/07/2019 | 05/07/2019 | 25/11/2019 | 0 | TK_Complete | -824745350 | 109 | -824745350_109
MML3RSTDES2520 | TT_Task | Pre-final Design Resubmission by Alstom: Gangway ; Coupler Movement Analysis | 15/10/2019 | 16/12/2019 | 15/10/2019 | 16/12/2019 | 0 | TK_Complete | -824745350 | 171 | -824745350_171
MML3RSTDES2530 | TT_Task | Pre-final Design Resubmission by Alstom: Detailed Design Specification - Gangway | 18/10/2019 | 19/10/2019 | 06/07/2019 | 18/10/2019 | 0 | TK_Complete | -824745350 | 107 | -824745350_107
MML3RSTDES2540 | TT_Task | Pre-final Design Resubmission by Alstom: Equipment Mounting Detailed Design Specification (Roof, Underframe) | 10/10/2019 | 30/11/2019 | 10/10/2019 | 30/11/2019 | 0 | TK_Complete | -824745350 | 172 | -824745350_172
MML3RSTDES2550 | TT_Task | Pre-final Design Resubmission by Alstom: Detailed Design Specification - Pneumatic Piping | 27/06/2019 | 26/11/2019 | 27/06/2019 | 26/11/2019 | 0 | TK_Complete | -824745350 | 173 | -824745350_173
MML3RSTDES2560 | TT_Task | Pre-final Design Resubmission by Alstom: Training Programme | 05/06/2019 | 08/08/2019 | 05/06/2019 | 08/08/2019 | 0 | TK_Complete | -824745350 | 50 | -824745350_50
MML3RSTDES2570 | TT_Task | Pre-final Design Resubmission by Alstom: Preliminary Hazard Analysis (PHA) | 09/05/2019 | 26/02/2020 | 09/05/2019 | 26/02/2020 | 0 | TK_Complete | -824745350 | 175 | -824745350_175
MML3RSTDES2580 | TT_Task | Pre-final Design Resubmission by Alstom: Interface hazard analysis (IHA) | 09/05/2019 | 26/02/2020 | 13/06/2019 | 26/02/2020 | 0 | TK_Complete | -824745350 | 175 | -824745350_175
MML3RSTDES2590 | TT_Task | Pre-final Design Resubmission by Alstom: Subsystem hazard analysis (SSHA) | 17/10/2019 | 26/02/2020 | 17/10/2019 | 26/02/2020 | 0 | TK_Complete | -824745350 | 175 | -824745350_175
MML3RSTDES2600 | TT_Task | Pre-final Design Resubmission by Alstom: Operation and Support Hazard Analysis (OSHA) | 09/05/2019 | 26/02/2020 | 09/05/2019 | 26/02/2020 | 0 | TK_Complete | -824745350 | 175 | -824745350_175
MML3RSTDES2610 | TT_Task | Pre-final Design Resubmission by Alstom: Reliability Apportionment and Prediction Report | 05/06/2019 | 26/02/2020 | 05/06/2019 | 26/02/2020 | 0 | TK_Complete | -824745350 | 112 | -824745350_112
MML3RSTDES2620 | TT_Task | Pre-final Design Resubmission by Alstom: RAM Testing Plan | 12/10/2019 | 25/10/2019 | 12/10/2019 | 19/11/2019 | 0 | TK_Complete | -824745350 | 29 | -824745350_29
MML3RSTDES8210 | TT_Task | Pre-final Design Resubmission by Alstom: Sub system Safety Requirement Specification | 13/06/2019 | 13/06/2019 | 11/04/2019 | 13/06/2019 | 0 | TK_Complete | -824745350 | 18 | -824745350_18
MML3RSTDES8350 | TT_Task | Pre-final Design Resubmission by Alstom:Computer based Maintenance Management System (CMMS) | 09/12/2019 | 04/03/2020 | 09/12/2019 | 04/03/2020 | 0 | TK_Complete | -824745350 | 114 | -824745350_114
MML3RSTDES2630 | TT_Task | Pre-final Design NONO/ NOWC from Project Manager: Technical specfication and drawings of Driving gear ; coupling system | 06/12/2019 | 06/12/2019 | 06/12/2019 | 06/12/2019 | 0 | TK_Complete | -824745350 | 182 | -824745350_182
MML3RSTDES2640 | TT_Task | Pre-final Design NONO/ NOWC from Project Manager: Technical drawings of Wheel flange lubricator | 24/01/2020 | 28/01/2020 | 24/01/2020 | 28/01/2020 | 0 | TK_Complete | -824745350 | 144 | -824745350_144
MML3RSTDES2650 | TT_Task | Pre-final Design NONO/ NOWC from Project Manager: Air consumption calculations | 13/11/2019 | 26/11/2019 | 13/11/2019 | 13/11/2019 | 0 | TK_Complete | -824745350 | 145 | -824745350_145
MML3RSTDES2660 | TT_Task | Pre-final Design NONO/ NOWC from Project Manager: Technical description and drawings of Passenger saloon door | 20/04/2020 | 28/04/2020 | 20/04/2020 | 28/04/2020 | 0 | TK_Complete | -824745350 | 120 | -824745350_120
MML3RSTDES2670 | TT_Task | Pre-final Design NONO/ NOWC from Project Manager: Technical description and drawings of Front Detrainment doors | 26/11/2019 | 30/11/2019 | 27/11/2019 | 12/12/2019 | 0 | TK_Complete | -824745350 | 121 | -824745350_121
MML3RSTDES2680 | TT_Task | Pre-final Design NONO/ NOWC from Project Manager: Technical Description and Drawings of 25 kV Vacuum Circuit Breaker | 29/11/2019 | 03/12/2019 | 29/11/2019 | 03/12/2019 | 0 | TK_Complete | -824745350 | 183 | -824745350_183
MML3RSTDES2690 | TT_Task | Pre-final Design NONO/ NOWC from Project Manager: Technical Description and Drawings of Earthing Switch | 30/11/2019 | 03/12/2019 | 30/11/2019 | 03/12/2019 | 0 | TK_Complete | -824745350 | 148 | -824745350_148
MML3RSTDES2700 | TT_Task | Pre-final Design NONO/ NOWC from Project Manager: Technical Description and Drawings of Surge Arrestor | 30/11/2019 | 03/12/2019 | 30/11/2019 | 03/12/2019 | 0 | TK_Complete | -824745350 | 149 | -824745350_149
MML3RSTDES2710 | TT_Task | Pre-final Design NONO/ NOWC from Project Manager: Technical Description and Drawings of Traction Convertor | 26/09/2019 | 06/02/2020 | 13/02/2020 | 27/02/2020 | 0 | TK_Complete | -824745350 | 184 | -824745350_184
MML3RSTDES2720 | TT_Task | Pre-final Design NONO/ NOWC from Project Manager: Technical Description and Drawings of Traction Motor | 07/09/2019 | 30/12/2019 | 05/02/2020 | 13/02/2020 | 0 | TK_Complete | -824745350 | 184 | -824745350_184
MML3RSTDES2730 | TT_Task | Pre-final Design NONO/ NOWC from Project Manager: Technical Description and Drawings of Pantograph | 26/09/2019 | 04/02/2020 | 05/02/2020 | 11/02/2020 | 0 | TK_Complete | -824745350 | 123 | -824745350_123
MML3RSTDES2740 | TT_Task | Pre-final Design NONO/ NOWC from Project Manager: Technical Description and Drawings of Transformer | 02/09/2019 | 05/02/2020 | 06/02/2020 | 07/02/2020 | 0 | TK_Complete | -824745350 | 176 | -824745350_176
MML3RSTDES2750 | TT_Task | Pre-final Design NONO/ NOWC from Project Manager: Technical Specification and Drawings of Auxiliary Convertor | 11/04/2020 | 20/04/2020 | 11/04/2020 | 20/04/2020 | 0 | TK_Complete | -824745350 | 51 | -824745350_51
MML3RSTDES2760 | TT_Task | Pre-final Design NONO/ NOWC from Project Manager: Technical Specification and Drawings of Battery Box | 05/04/2020 | 13/04/2020 | 05/04/2020 | 13/04/2020 | 0 | TK_Complete | -824745350 | 154 | -824745350_154
MML3RSTDES2770 | TT_Task | Pre-final Design NONO/ NOWC from Project Manager: Technical Specification and Drawings of Battery Charger | 17/10/2019 | 17/10/2019 | 17/10/2019 | 17/10/2019 | 0 | TK_Complete | -824745350 | 155 | -824745350_155
MML3RSTDES2780 | TT_Task | Pre-final Design NONO/ NOWC from Project Manager: Auxiliary Load Calculation for AC ; DC | 17/10/2019 | 17/10/2019 | 17/10/2019 | 17/10/2019 | 0 | TK_Complete | -824745350 | 156 | -824745350_156
MML3RSTDES2790 | TT_Task | Pre-final Design NONO/ NOWC from Project Manager: Technical Description and Drawings of Saloon VAC | 03/12/2019 | 05/12/2019 | 03/12/2019 | 05/12/2019 | 0 | TK_Complete | -824745350 | 157 | -824745350_157
MML3RSTDES2800 | TT_Task | Pre-final Design NONO/ NOWC from Project Manager: Technical specification ; Drawings of Lightings | 12/07/2019 | 06/02/2020 | 07/02/2020 | 13/02/2020 | 0 | TK_Complete | -824745350 | 126 | -824745350_126
MML3RSTDES2810 | TT_Task | Pre-final Design NONO/ NOWC from Project Manager: Technical specification of Seconadary suspension | 10/12/2019 | 21/12/2019 | 10/12/2019 | 21/12/2019 | 0 | TK_Complete | -824745350 | 158 | -824745350_158
MML3RSTDES2820 | TT_Task | Pre-final Design NONO/ NOWC from Project Manager: Detailed Technical Description of Brake System | 17/09/2020 | 18/09/2020 | 17/09/2020 | 18/09/2020 | 0 | TK_Complete | -824745350 | 139 | -824745350_139
MML3RSTDES2830 | TT_Task | Pre-final Design NONO/ NOWC from Project Manager: Detailed Technical Description of Air Supply System | 31/12/2019 | 08/01/2020 | 31/12/2019 | 08/01/2020 | 0 | TK_Complete | -824745350 | 119 | -824745350_119
MML3RSTDES2840 | TT_Task | Pre-final Design NONO/ NOWC from Project Manager: General arrangement for wheel slip detection and correction system | 31/12/2019 | 08/01/2020 | 31/12/2019 | 08/01/2020 | 0 | TK_Complete | -824745350 | 159 | -824745350_159
MML3RSTDES2850 | TT_Task | Pre-final Design NONO/ NOWC from Project Manager: Heat Load Calculations | 03/12/2019 | 05/12/2019 | 03/12/2019 | 05/12/2019 | 0 | TK_Complete | -824745350 | 160 | -824745350_160
MML3RSTDES2860 | TT_Task | Pre-final Design NONO/ NOWC from Project Manager: Technical Description of Derailment Detection and Obstruction Deflecti | 29/07/2020 | 31/07/2020 | 29/07/2020 | 31/07/2020 | 0 | TK_Complete | -824745350 | 161 | -824745350_161
MML3RSTDES2870 | TT_Task | Pre-final Design NONO/ NOWC from Project Manager: Technical specification of TCMS | 23/04/2020 | 28/04/2020 | 23/04/2020 | 28/04/2020 | 0 | TK_Complete | -824745350 | 127 | -824745350_127
MML3RSTDES2880 | TT_Task | Pre-final Design NONO/ NOWC from Project Manager: Technical Description and Drawings of Master Controller | 23/08/2019 | 05/02/2020 | 06/02/2020 | 13/02/2020 | 0 | TK_Complete | -824745350 | 177 | -824745350_177
MML3RSTDES2890 | TT_Task | Pre-final Design NONO/ NOWC from Project Manager: Functional description of PAPIS system | 30/06/2020 | 08/07/2020 | 30/06/2020 | 08/07/2020 | 0 | TK_Complete | -824745350 | 128 | -824745350_128
MML3RSTDES2900 | TT_Task | Pre-final Design NONO/ NOWC from Project Manager: Carbody Structure Detailed FEA Report | 06/12/2019 | 19/12/2019 | 06/12/2019 | 19/12/2019 | 0 | TK_Complete | -824745350 | 163 | -824745350_163
MML3RSTDES2910 | TT_Task | Pre-final Design NONO/ NOWC from Project Manager: Carbody crashworthiness report | 25/11/2019 | 27/11/2019 | 26/11/2019 | 27/11/2019 | 0 | TK_Complete | -824745350 | 164 | -824745350_164
MML3RSTDES2920 | TT_Task | Pre-final Design NONO/ NOWC from Project Manager: Detailed Design Specification - Carbody Structure | 26/11/2019 | 27/11/2019 | 26/11/2019 | 27/11/2019 | 0 | TK_Complete | -824745350 | 133 | -824745350_133
MML3RSTDES2930 | TT_Task | Pre-final Design NONO/ NOWC from Project Manager: Weight distribution calculations report | 26/11/2019 | 27/11/2019 | 26/11/2019 | 27/11/2019 | 0 | TK_Complete | -824745350 | 131 | -824745350_131
MML3RSTDES2940 | TT_Task | Pre-final Design NONO/ NOWC from Project Manager: Car End clearance | 09/12/2019 | 19/12/2019 | 09/12/2019 | 19/12/2019 | 0 | TK_Complete | -824745350 | 178 | -824745350_178
MML3RSTDES2950 | TT_Task | Pre-final Design NONO/ NOWC from Project Manager: Noise Report - Preliminary Specification ; Prediction | 25/07/2020 | 31/07/2020 | 25/07/2020 | 31/07/2020 | 0 | TK_Complete | -824745350 | 179 | -824745350_179
MML3RSTDES2960 | TT_Task | Pre-final Design NONO/ NOWC from Project Manager: Final Kinematic Envelope Calculation Report | 26/11/2019 | 29/11/2019 | 26/11/2019 | 29/11/2019 | 0 | TK_Complete | -824745350 | 130 | -824745350_130
MML3RSTDES2970 | TT_Task | Pre-final Design NONO/ NOWC from Project Manager: Ergonomic reports for cab - Visibility study report, Driver Desk | 02/12/2019 | 05/12/2019 | 02/12/2019 | 05/12/2019 | 0 | TK_Complete | -824745350 | 165 | -824745350_165
MML3RSTDES2980 | TT_Task | Pre-final Design NONO/ NOWC from Project Manager: Ergonomic report for saloon | 19/10/2019 | 19/10/2019 | 19/10/2019 | 19/10/2019 | 0 | TK_Complete | -824745350 | 166 | -824745350_166
MML3RSTDES2990 | TT_Task | Pre-final Design NONO/ NOWC from Project Manager: Climate Comfort Prediction report | 23/10/2019 | 23/10/2019 | 23/10/2019 | 23/10/2019 | 0 | TK_Complete | -824745350 | 167 | -824745350_167
MML3RSTDES3000 | TT_Task | Pre-final Design NONO/ NOWC from Project Manager: Detailed Design Specification- Partition Wall | 11/06/2020 | 17/06/2020 | 11/06/2020 | 17/06/2020 | 0 | TK_Complete | -824745350 | 168 | -824745350_168
MML3RSTDES3010 | TT_Task | Pre-final Design NONO/ NOWC from Project Manager: Detailed Design Specification - Saloon Interior | 19/09/2020 | 25/09/2020 | 19/09/2020 | 25/09/2020 | 0 | TK_Complete | -824745350 | 106 | -824745350_106
MML3RSTDES3020 | TT_Task | Pre-final Design NONO/ NOWC from Project Manager: Detailed Design Specification - Cab | 01/01/2020 | 07/01/2020 | 01/01/2020 | 07/01/2020 | 0 | TK_Complete | -824745350 | 142 | -824745350_142
MML3RSTDES3030 | TT_Task | Pre-final Design NONO/ NOWC from Project Manager: Detailed Design Specification - Signage and labelling | 27/11/2019 | 27/11/2019 | 27/11/2019 | 27/11/2019 | 0 | TK_Complete | -824745350 | 169 | -824745350_169
MML3RSTDES3040 | TT_Task | Pre-final Design NONO/ NOWC from Project Manager: Collision and Energy Absorption Calculation Report of Coupler System | 26/11/2019 | 27/11/2019 | 26/11/2019 | 27/11/2019 | 0 | TK_Complete | -824745350 | 170 | -824745350_170
MML3RSTDES3050 | TT_Task | Pre-final Design NONO/ NOWC from Project Manager: Detailed Design Specification -Couplers | 26/11/2019 | 27/11/2019 | 26/11/2019 | 27/11/2019 | 0 | TK_Complete | -824745350 | 142 | -824745350_142
MML3RSTDES3060 | TT_Task | Pre-final Design NONO/ NOWC from Project Manager: Gangway ; Coupler Movement Analysis | 17/12/2019 | 19/12/2019 | 17/12/2019 | 19/12/2019 | 0 | TK_Complete | -824745350 | 180 | -824745350_180
MML3RSTDES3070 | TT_Task | Pre-final Design NONO/ NOWC from Project Manager: Detailed Design Specification - Gangway | 19/10/2019 | 19/10/2019 | 19/10/2019 | 19/10/2019 | 0 | TK_Complete | -824745350 | 142 | -824745350_142
MML3RSTDES3080 | TT_Task | Pre-final Design NONO/ NOWC from Project Manager: Equipment Mounting Detailed Design Specification (Roof, Underframe) | 02/12/2019 | 05/12/2019 | 02/12/2019 | 05/12/2019 | 0 | TK_Complete | -824745350 | 172 | -824745350_172
MML3RSTDES3090 | TT_Task | Pre-final Design NONO/ NOWC from Project Manager: Detailed Design Specification - Pneumatic Piping | 27/11/2019 | 03/12/2019 | 27/11/2019 | 03/12/2019 | 0 | TK_Complete | -824745350 | 173 | -824745350_173
MML3RSTDES3100 | TT_Task | Pre-final Design NONO/ NOWC from Project Manager: Training Programme | 09/08/2019 | 09/08/2019 | 09/08/2019 | 09/08/2019 | 0 | TK_Complete | -824745350 | 54 | -824745350_54
MML3RSTDES3110 | TT_Task | Pre-final Design NONO/ NOWC from Project Manager: Preliminary Hazard Analysis (PHA) | 27/02/2020 | 13/03/2020 | 27/02/2020 | 16/03/2020 | 0 | TK_Complete | -824745350 | 58 | -824745350_58
MML3RSTDES3120 | TT_Task | Pre-final Design NONO/ NOWC from Project Manager: Interface hazard analysis (IHA) | 27/02/2020 | 13/03/2020 | 27/02/2020 | 13/03/2020 | 0 | TK_Complete | -824745350 | 58 | -824745350_58
MML3RSTDES3130 | TT_Task | Pre-final Design NONO/ NOWC from Project Manager: Subsystem hazard analysis (SSHA) | 27/02/2020 | 28/03/2020 | 27/02/2020 | 28/03/2020 | 0 | TK_Complete | -824745350 | 58 | -824745350_58
MML3RSTDES3140 | TT_Task | Pre-final Design NONO/ NOWC from Project Manager: Operation and Support Hazard Analysis (OSHA) | 27/02/2020 | 16/03/2020 | 27/02/2020 | 16/03/2020 | 0 | TK_Complete | -824745350 | 58 | -824745350_58
MML3RSTDES3150 | TT_Task | Pre-final Design NONO/ NOWC from Project Manager: Reliability Apportionment and Prediction Report | 27/02/2020 | 13/03/2020 | 27/02/2020 | 13/03/2020 | 0 | TK_Complete | -824745350 | 136 | -824745350_136
MML3RSTDES3160 | TT_Task | Pre-final Design NONO/ NOWC from Project Manager: RAM Testing Plan | 20/11/2019 | 21/11/2019 | 20/11/2019 | 21/11/2019 | 0 | TK_Complete | -824745350 | 46 | -824745350_46
MML3RSTDES3162 | TT_Task | Pre-final Design NONO/ NOWC from Project Manager: Sub system Safety Requirement Specification | 22/06/2019 | 22/06/2019 | 14/06/2019 | 22/06/2019 | 0 | TK_Complete | -824745350 | 181 | -824745350_181
MML3RSTDES3163 | TT_Task | Pre-final Design NONO/ NOWC from Project Manager: Computer based Maintenance Management System (CMMS) | 05/03/2020 | 05/03/2020 | 05/03/2020 | 05/03/2020 | 0 | TK_Complete | -824745350 | 137 | -824745350_137
MML3RSTDES3180 | TT_Task | Final design First submission by Alstom: Test Specification of Battery System | 20/09/2019 | 19/12/2019 | 20/09/2019 | 19/12/2019 | 0 | TK_Complete | -824745350 | 185 | -824745350_185
MML3RSTDES3190 | TT_Task | Final design First submission by Alstom: Train Operation Control Description | 04/10/2019 | 20/12/2019 | 04/10/2019 | 20/12/2019 | 0 | TK_Complete | -824745350 | 82 | -824745350_82
MML3RSTDES3200 | TT_Task | Final design First submission by Alstom: Energy Consumption Anlaysis | 09/11/2019 | 09/11/2019 | 09/11/2019 | 09/11/2019 | 0 | TK_Complete | -824745350 | 186 | -824745350_186
MML3RSTDES3210 | TT_Task | Final design First submission by Alstom: Ride Index Test Specification | 05/12/2019 | 05/12/2019 | 05/12/2019 | 05/12/2019 | 0 | TK_Complete | -824745350 | 187 | -824745350_187
MML3RSTDES3220 | TT_Task | Final design First submission by Alstom: Final Vehicle Performance | 24/10/2019 | 24/10/2019 | 24/10/2019 | 24/10/2019 | 0 | TK_Complete | -824745350 | 84 | -824745350_84
MML3RSTDES3230 | TT_Task | Final design First submission by Alstom: Inspection instruction of complete Bogie | 12/08/2019 | 27/11/2019 | 12/08/2019 | 27/11/2019 | 0 | TK_Complete | -824745350 | 188 | -824745350_188
MML3RSTDES3240 | TT_Task | Final design First submission by Alstom: Vehicle Dynamic Analysis of Bogie | 12/08/2019 | 05/12/2019 | 12/08/2019 | 05/12/2019 | 0 | TK_Complete | -824745350 | 189 | -824745350_189
MML3RSTDES3250 | TT_Task | Final design First submission by Alstom: FEA of Bogie Frame | 27/11/2019 | 27/11/2019 | 27/11/2019 | 27/11/2019 | 0 | TK_Complete | -824745350 | 190 | -824745350_190
MML3RSTDES3260 | TT_Task | Final design First submission by Alstom: Test Specification of Bogie Frame static load / Fatigue load | 27/11/2019 | 27/11/2019 | 27/11/2019 | 27/11/2019 | 0 | TK_Complete | -824745350 | 191 | -824745350_191
MML3RSTDES3270 | TT_Task | Final design First submission by Alstom: Test Specification of Primary suspension | 27/11/2019 | 27/11/2019 | 27/11/2019 | 27/11/2019 | 0 | TK_Complete | -824745350 | 192 | -824745350_192
MML3RSTDES3280 | TT_Task | Final design First submission by Alstom: Test Specification of Damper | 27/11/2019 | 27/11/2019 | 27/11/2019 | 27/11/2019 | 0 | TK_Complete | -824745350 | 193 | -824745350_193
MML3RSTDES3290 | TT_Task | Final design First submission by Alstom: Test Specification of Wheel | 27/11/2019 | 27/11/2019 | 27/11/2019 | 27/11/2019 | 0 | TK_Complete | -824745350 | 194 | -824745350_194
MML3RSTDES3300 | TT_Task | Final design First submission by Alstom: Test specification of Axle | 30/11/2019 | 30/11/2019 | 30/11/2019 | 30/11/2019 | 0 | TK_Complete | -824745350 | 195 | -824745350_195
MML3RSTDES3310 | TT_Task | Final design First submission by Alstom: Thermal Calculations of Wheel | 28/11/2019 | 10/01/2020 | 28/11/2019 | 10/01/2020 | 0 | TK_Complete | -824745350 | 196 | -824745350_196
MML3RSTDES3320 | TT_Task | Final design First submission by Alstom: Wheel Stress calculations | 28/11/2019 | 28/11/2019 | 28/11/2019 | 28/11/2019 | 0 | TK_Complete | -824745350 | 194 | -824745350_194
MML3RSTDES3330 | TT_Task | Final design First submission by Alstom: Axle strength calculations | 14/11/2019 | 14/11/2019 | 14/11/2019 | 14/11/2019 | 0 | TK_Complete | -824745350 | 195 | -824745350_195
MML3RSTDES3340 | TT_Task | Final design First submission by Alstom: FEA of center pivot, axle box and Traction Linkage | 28/11/2019 | 10/01/2020 | 28/11/2019 | 10/01/2020 | 0 | TK_Complete | -824745350 | 197 | -824745350_197
MML3RSTDES3350 | TT_Task | Final design First submission by Alstom: Test Specification of Driving gear system | 28/06/2019 | 05/12/2019 | 28/06/2019 | 05/12/2019 | 0 | TK_Complete | -824745350 | 143 | -824745350_143
MML3RSTDES3360 | TT_Task | Final design First submission by Alstom: Test Specification of Gearbox | 28/06/2019 | 05/12/2019 | 28/06/2019 | 05/12/2019 | 0 | TK_Complete | -824745350 | 143 | -824745350_143
MML3RSTDES3370 | TT_Task | Final design First submission by Alstom: Gear, analysis of stresses, selection of bearing, gear case and transmissioin | 28/06/2019 | 05/12/2019 | 28/06/2019 | 05/12/2019 | 0 | TK_Complete | -824745350 | 198 | -824745350_198
MML3RSTDES3380 | TT_Task | Final design First submission by Alstom: Test specification of Wheel Flange Lubricator | 28/06/2019 | 29/11/2019 | 28/06/2019 | 29/11/2019 | 0 | TK_Complete | -824745350 | 144 | -824745350_144
MML3RSTDES3390 | TT_Task | Final design First submission by Alstom: Life cycle calculation of Axle Box | 28/11/2019 | 28/11/2019 | 28/11/2019 | 28/11/2019 | 0 | TK_Complete | -824745350 | 199 | -824745350_199
MML3RSTDES3400 | TT_Task | Final design First submission by Alstom: Brake Performance Calculations | 27/11/2019 | 27/11/2019 | 27/11/2019 | 27/11/2019 | 0 | TK_Complete | -824745350 | 86 | -824745350_86
MML3RSTDES3410 | TT_Task | Final design First submission by Alstom: Test specification of Passenger saloon Door | 04/07/2019 | 05/12/2019 | 04/07/2019 | 05/12/2019 | 0 | TK_Complete | -824745350 | 146 | -824745350_146
MML3RSTDES3420 | TT_Task | Final design First submission by Alstom: Test specification of Front Detrainment Doors | 03/07/2019 | 24/12/2019 | 03/07/2019 | 24/12/2019 | 0 | TK_Complete | -824745350 | 89 | -824745350_89
MML3RSTDES3430 | TT_Task | Final design First submission by Alstom: Test specification of 25 kV Vacuum Circuit Breaker | 06/07/2019 | 20/12/2019 | 06/07/2019 | 20/12/2019 | 0 | TK_Complete | -824745350 | 147 | -824745350_147
MML3RSTDES3440 | TT_Task | Final design First submission by Alstom: Test specification of Surge Arrestor | 29/06/2019 | 12/02/2020 | 29/06/2019 | 12/02/2020 | 0 | TK_Complete | -824745350 | 149 | -824745350_149
MML3RSTDES3450 | TT_Task | Final design First submission by Alstom: Test Specification of Traction Convertor | 09/09/2019 | 24/10/2019 | 09/09/2019 | 24/10/2019 | 0 | TK_Complete | -824745350 | 150 | -824745350_150
MML3RSTDES3460 | TT_Task | Final design First submission by Alstom: Test Specification of Traction Motor | 06/09/2019 | 24/10/2019 | 06/09/2019 | 24/10/2019 | 0 | TK_Complete | -824745350 | 151 | -824745350_151
MML3RSTDES3470 | TT_Task | Final design First submission by Alstom: Test specification of Roof Mounted Pantograph | 25/09/2019 | 09/11/2019 | 25/09/2019 | 09/11/2019 | 0 | TK_Complete | -824745350 | 200 | -824745350_200
MML3RSTDES3480 | TT_Task | Final design First submission by Alstom: Test specification of Transformer | 31/08/2019 | 23/10/2019 | 31/08/2019 | 23/10/2019 | 0 | TK_Complete | -824745350 | 152 | -824745350_152
MML3RSTDES3490 | TT_Task | Final design First submission by Alstom: Test specification of Earthing Switch | 29/06/2019 | 20/12/2019 | 29/06/2019 | 20/12/2019 | 0 | TK_Complete | -824745350 | 148 | -824745350_148
MML3RSTDES3500 | TT_Task | Final design First submission by Alstom: Harmonic Calculations | 19/12/2019 | 19/12/2019 | 19/12/2019 | 19/12/2019 | 0 | TK_Complete | -824745350 | 201 | -824745350_201
MML3RSTDES3510 | TT_Task | Final design First submission by Alstom: Test Specification of Auxiliary Convertor | 14/09/2019 | 24/10/2019 | 14/09/2019 | 24/10/2019 | 0 | TK_Complete | -824745350 | 153 | -824745350_153
MML3RSTDES3520 | TT_Task | Final design First submission by Alstom: Software document for Door System | 22/08/2019 | 24/12/2019 | 22/08/2019 | 24/12/2019 | 0 | TK_Complete | -824745350 | 202 | -824745350_202
MML3RSTDES3530 | TT_Task | Final design First submission by Alstom: Software document for VAC System | 22/08/2019 | 24/12/2019 | 22/08/2019 | 24/12/2019 | 0 | TK_Complete | -824745350 | 93 | -824745350_93
MML3RSTDES3540 | TT_Task | Final design First submission by Alstom: Software document for Brake system | 22/08/2019 | 24/12/2019 | 22/08/2019 | 24/12/2019 | 0 | TK_Complete | -824745350 | 86 | -824745350_86
MML3RSTDES3550 | TT_Task | Final design First submission by Alstom: Software document for propulsion system | 22/08/2019 | 05/12/2019 | 22/08/2019 | 05/12/2019 | 0 | TK_Complete | -824745350 | 90 | -824745350_90
MML3RSTDES3560 | TT_Task | Final design First submission by Alstom: Software document for Auxiliary supply system | 22/08/2019 | 05/12/2019 | 22/08/2019 | 05/12/2019 | 0 | TK_Complete | -824745350 | 92 | -824745350_92
MML3RSTDES3570 | TT_Task | Final design First submission by Alstom: Test Specification of Saloon VAC | 17/09/2019 | 09/12/2019 | 17/09/2019 | 09/12/2019 | 0 | TK_Complete | -824745350 | 157 | -824745350_157
MML3RSTDES3580 | TT_Task | Final design First submission by Alstom: Test Specification of Dynamometer Test | 29/08/2019 | 16/11/2019 | 29/08/2019 | 06/02/2020 | 0 | TK_Complete | -824745350 | 203 | -824745350_203
MML3RSTDES3590 | TT_Task | Final design First submission by Alstom: Detail Description of Bogie Brake Equipment | 29/08/2019 | 14/11/2019 | 29/08/2019 | 14/11/2019 | 0 | TK_Complete | -824745350 | 204 | -824745350_204
MML3RSTDES3600 | TT_Task | Final design First submission by Alstom: Test Specification for Air Supply System | 29/08/2019 | 30/11/2019 | 29/08/2019 | 30/11/2019 | 0 | TK_Complete | -824745350 | 87 | -824745350_87
MML3RSTDES3610 | TT_Task | Final design First submission by Alstom: Type Test Specification - Saloon Lighting and Gangway Lighting | 10/07/2019 | 26/11/2019 | 10/07/2019 | 26/11/2019 | 0 | TK_Complete | -824745350 | 205 | -824745350_205
MML3RSTDES3620 | TT_Task | Final design First submission by Alstom: Description for Neutral Section Detection and functioning | 10/06/2019 | 18/06/2019 | 10/06/2019 | 18/06/2019 | 0 | TK_Complete | -824745350 | 206 | -824745350_206
MML3RSTDES3630 | TT_Task | Final design First submission by Alstom: Electrical Pure Principle scheme - Train | 11/11/2019 | 30/12/2019 | 11/11/2019 | 30/12/2019 | 0 | TK_Complete | -824745350 | 207 | -824745350_207
MML3RSTDES3640 | TT_Task | Final design First submission by Alstom: Test Specification of Master Controller | 09/09/2019 | 31/12/2019 | 09/09/2019 | 31/12/2019 | 0 | TK_Complete | -824745350 | 162 | -824745350_162
MML3RSTDES3650 | TT_Task | Final design First submission by Alstom: Technical specification and Drawings of PAPIS | 25/09/2019 | 18/02/2020 | 25/09/2019 | 18/02/2020 | 0 | TK_Complete | -824745350 | 208 | -824745350_208
MML3RSTDES3660 | TT_Task | Final design First submission by Alstom: Test Specification of PAPIS system | 25/09/2019 | 17/02/2020 | 25/09/2019 | 17/02/2020 | 0 | TK_Complete | -824745350 | 138 | -824745350_138
MML3RSTDES3670 | TT_Task | Final design First submission by Alstom: Solution Principal Scheme | 10/12/2019 | 30/12/2019 | 10/12/2019 | 30/12/2019 | 0 | TK_Complete | -824745350 | 209 | -824745350_209
MML3RSTDES3680 | TT_Task | Final design First submission by Alstom: Test Specification - Gangway | 15/10/2019 | 23/10/2019 | 15/10/2019 | 23/10/2019 | 0 | TK_Complete | -824745350 | 107 | -824745350_107
MML3RSTDES3690 | TT_Task | Final design First submission by Alstom: Type Test Specification - Load test of Floor panel | 15/10/2019 | 28/10/2019 | 15/10/2019 | 28/10/2019 | 0 | TK_Complete | -824745350 | 210 | -824745350_210
MML3RSTDES3700 | TT_Task | Final design First submission by Alstom: Type Test Specification - Windscreen | 15/10/2019 | 28/10/2019 | 15/10/2019 | 28/10/2019 | 0 | TK_Complete | -824745350 | 211 | -824745350_211
MML3RSTDES3710 | TT_Task | Final design First submission by Alstom: Type Test Specification - Windows | 15/10/2019 | 28/10/2019 | 15/10/2019 | 28/10/2019 | 0 | TK_Complete | -824745350 | 212 | -824745350_212
MML3RSTDES3720 | TT_Task | Final design First submission by Alstom: Type Test Specification - Interior Components | 15/10/2019 | 19/11/2019 | 15/10/2019 | 19/11/2019 | 0 | TK_Complete | -824745350 | 212 | -824745350_212
MML3RSTDES3730 | TT_Task | Final design First submission by Alstom: Type Test Specification - Gauging (Static + Kinematic) | 11/10/2019 | 15/11/2019 | 11/10/2019 | 15/11/2019 | 0 | TK_Complete | -824745350 | 213 | -824745350_213
MML3RSTDES3740 | TT_Task | Final design First submission by Alstom: Type Test Specification - Straphangers Endurance | 11/10/2019 | 24/10/2019 | 11/10/2019 | 24/10/2019 | 0 | TK_Complete | -824745350 | 214 | -824745350_214
MML3RSTDES3750 | TT_Task | Final design First submission by Alstom: Type Test Specification - Couplers | 15/10/2019 | 23/10/2019 | 15/10/2019 | 23/10/2019 | 0 | TK_Complete | -824745350 | 215 | -824745350_215
MML3RSTDES3760 | TT_Task | Final design First submission by Alstom: Type Test Specification - Floor Fire Resistance | 29/08/2019 | 24/10/2019 | 29/08/2019 | 24/10/2019 | 0 | TK_Complete | -824745350 | 216 | -824745350_216
MML3RSTDES3770 | TT_Task | Final design First submission by Alstom: Fire Engineering Report - Prediction | 05/02/2020 | 14/02/2020 | 05/02/2020 | 14/02/2020 | 0 | TK_Complete | -824745350 | 217 | -824745350_217
MML3RSTDES3780 | TT_Task | Final design First submission by Alstom: Noise Report - Final Prediction | 25/11/2019 | 03/02/2020 | 25/11/2019 | 29/01/2020 | 0 | TK_Complete | -824745350 | 103 | -824745350_103
MML3RSTDES3790 | TT_Task | Final design First submission by Alstom: Operation ; Maintenance Manuals Plan | 19/11/2019 | 19/11/2019 | 19/11/2019 | 19/11/2019 | 0 | TK_Complete | -824745350 | 11 | -824745350_11
MML3RSTDES3800 | TT_Task | Final design First submission by Alstom: Training Plan | 05/06/2019 | 16/10/2019 | 05/06/2019 | 16/10/2019 | 0 | TK_Complete | -824745350 | 174 | -824745350_174
MML3RSTDES3810 | TT_Task | Final design First submission by Alstom: Spare Management Plan | 20/11/2019 | 20/11/2019 | 20/11/2019 | 20/11/2019 | 0 | TK_Complete | -824745350 | 26 | -824745350_26
MML3RSTDES3820 | TT_Task | Final design First submission by Alstom: Assistance of Maintenance Plan | 12/10/2019 | 20/11/2019 | 12/10/2019 | 20/11/2019 | 0 | TK_Complete | -824745350 | 28 | -824745350_28
MML3RSTDES3830 | TT_Task | Final design First submission by Alstom: Comprehensive Maintenance Plan | 12/10/2019 | 19/11/2019 | 12/10/2019 | 19/11/2019 | 0 | TK_Complete | -824745350 | 28 | -824745350_28
MML3RSTDES3840 | TT_Task | Final design First submission by Alstom: Spare Parts List | 13/12/2019 | 13/12/2019 | 13/12/2019 | 13/12/2019 | 0 | TK_Complete | -824745350 | 218 | -824745350_218
MML3RSTDES3850 | TT_Task | Final design First submission by Alstom: Train Simulator ; CBT Specification | 17/08/2019 | 19/02/2020 | 17/08/2019 | 19/02/2020 | 0 | TK_Complete | -824745350 | 219 | -824745350_219
MML3RSTDES3860 | TT_Task | Final design First submission by Alstom: Maintenance Demonstration plan | 12/10/2019 | 13/12/2019 | 12/10/2019 | 13/12/2019 | 0 | TK_Complete | -824745350 | 28 | -824745350_28
MML3RSTDES3870 | TT_Task | Final design First submission by Alstom: Quantitative fault tree analysis | 12/10/2019 | 29/01/2020 | 12/10/2019 | 29/01/2020 | 0 | TK_Complete | -824745350 | 220 | -824745350_220
MML3RSTDES3880 | TT_Task | Final design First submission by Alstom: Failure modes effects and criticality analysis (FMECA) | 12/10/2019 | 23/12/2019 | 12/10/2019 | 23/12/2019 | 0 | TK_Complete | -824745350 | 112 | -824745350_112
MML3RSTDES3890 | TT_Task | Final design First submission by Alstom: Design Safety Study Report | 12/10/2019 | 27/01/2020 | 12/10/2019 | 27/01/2020 | 0 | TK_Complete | -824745350 | 19 | -824745350_19
MML3RSTDES3900 | TT_Task | Final design First submission by Alstom: Hazard Log | 17/10/2019 | 25/10/2019 | 17/10/2019 | 25/10/2019 | 0 | TK_Complete | -824745350 | 221 | -824745350_221
MML3RSTDES3910 | TT_Task | Final design First submission by Alstom: Safety Critical Item List | 12/10/2019 | 23/12/2019 | 12/10/2019 | 23/12/2019 | 0 | TK_Complete | -824745350 | 19 | -824745350_19
MML3RSTDES3920 | TT_Task | Final design First submission by Alstom: Reliability Critical Item List | 05/06/2019 | 23/12/2019 | 05/06/2019 | 23/12/2019 | 0 | TK_Complete | -824745350 | 19 | -824745350_19
MML3RSTDES3930 | TT_Task | Final design First submission by Alstom: RAM demonstration ; FRACAS Plan | 12/10/2019 | 26/11/2019 | 12/10/2019 | 26/11/2019 | 0 | TK_Complete | -824745350 | 29 | -824745350_29
MML3RSTDES3940 | TT_Task | Final design First submission by Alstom: Application Safety Case | 12/10/2019 | 13/02/2020 | 12/10/2019 | 27/01/2020 | 0 | TK_Complete | -824745350 | 19 | -824745350_19
MML3RSTDES8220 | TT_Task | Final design First submission by Alstom: Test Specification of Wayside Measurement ; Monitoring System | 04/10/2019 | 04/02/2020 | 04/10/2019 | 04/02/2020 | 0 | TK_Complete | -824745350 | 222 | -824745350_222
MML3RSTDES8230 | TT_Task | Final design First submission by Alstom: Technical Specification of CMMS | 20/07/2020 | 20/07/2020 | 20/07/2020 | 20/07/2020 | 0 | TK_Complete | -824745350 | 223 | -824745350_223
MML3RSTDES3950 | TT_Task | Final design Review/ Comments from Project Manager: Test Specification of Battery System | 20/12/2019 | 07/01/2020 | 20/12/2019 | 07/01/2020 | 0 | TK_Complete | -824745350 | 185 | -824745350_185
MML3RSTDES3960 | TT_Task | Final design Review/ Comments from Project Manager: Train Operation Control Description | 21/12/2019 | 06/01/2020 | 21/12/2019 | 06/01/2020 | 0 | TK_Complete | -824745350 | 224 | -824745350_224
MML3RSTDES3970 | TT_Task | Final design Review/ Comments from Project Manager: Energy Consumption Anlaysis | 11/11/2019 | 23/11/2019 | 11/11/2019 | 23/11/2019 | 0 | TK_Complete | -824745350 | 186 | -824745350_186
MML3RSTDES3980 | TT_Task | Final design Review/ Comments from Project Manager: Ride Index Test Specification | 06/12/2019 | 31/12/2019 | 06/12/2019 | 31/12/2019 | 0 | TK_Complete | -824745350 | 187 | -824745350_187
MML3RSTDES3990 | TT_Task | Final design Review/ Comments from Project Manager: Final Vehicle Performance | 25/10/2019 | 15/11/2019 | 25/10/2019 | 15/11/2019 | 0 | TK_Complete | -824745350 | 116 | -824745350_116
MML3RSTDES4000 | TT_Task | Final design Review/ Comments from Project Manager: Inspection instruction of complete Bogie | 28/11/2019 | 11/12/2019 | 28/11/2019 | 11/12/2019 | 0 | TK_Complete | -824745350 | 188 | -824745350_188
MML3RSTDES4010 | TT_Task | Final design Review/ Comments from Project Manager: Vehicle Dynamic Analysis of Bogie | 06/12/2019 | 31/12/2019 | 06/12/2019 | 31/12/2019 | 0 | TK_Complete | -824745350 | 189 | -824745350_189
MML3RSTDES4020 | TT_Task | Final design Review/ Comments from Project Manager: FEA of Bogie Frame | 28/11/2019 | 11/12/2019 | 28/11/2019 | 11/12/2019 | 0 | TK_Complete | -824745350 | 190 | -824745350_190
MML3RSTDES4030 | TT_Task | Final design Review/ Comments from Project Manager: Test Specification of Bogie Frame static load / Fatigue load | 28/11/2019 | 11/12/2019 | 28/11/2019 | 11/12/2019 | 0 | TK_Complete | -824745350 | 191 | -824745350_191
MML3RSTDES4040 | TT_Task | Final design Review/ Comments from Project Manager: Test Specification of Primary suspension | 28/11/2019 | 11/12/2019 | 28/11/2019 | 11/12/2019 | 0 | TK_Complete | -824745350 | 192 | -824745350_192
MML3RSTDES4050 | TT_Task | Final design Review/ Comments from Project Manager: Test Specification of Damper | 28/11/2019 | 11/12/2019 | 28/11/2019 | 11/12/2019 | 0 | TK_Complete | -824745350 | 193 | -824745350_193
MML3RSTDES4060 | TT_Task | Final design Review/ Comments from Project Manager: Test Specification of Wheel | 28/11/2019 | 11/12/2019 | 28/11/2019 | 11/12/2019 | 0 | TK_Complete | -824745350 | 194 | -824745350_194
MML3RSTDES4070 | TT_Task | Final design Review/ Comments from Project Manager: Test specification of Axle | 02/12/2019 | 11/12/2019 | 02/12/2019 | 11/12/2019 | 0 | TK_Complete | -824745350 | 195 | -824745350_195
MML3RSTDES4080 | TT_Task | Final design Review/ Comments from Project Manager: Thermal Calculations of Wheel | 11/01/2020 | 27/01/2020 | 11/01/2020 | 27/01/2020 | 0 | TK_Complete | -824745350 | 196 | -824745350_196
MML3RSTDES4090 | TT_Task | Final design Review/ Comments from Project Manager: Wheel Stress calculations | 29/11/2019 | 29/11/2019 | 29/11/2019 | 29/11/2019 | 0 | TK_Complete | -824745350 | 225 | -824745350_225
MML3RSTDES4100 | TT_Task | Final design Review/ Comments from Project Manager: Axle strength calculations | 15/11/2019 | 27/11/2019 | 15/11/2019 | 27/11/2019 | 0 | TK_Complete | -824745350 | 195 | -824745350_195
MML3RSTDES4110 | TT_Task | Final design Review/ Comments from Project Manager: FEA of center pivot, axle box and Traction Linkage | 11/01/2020 | 05/02/2020 | 11/01/2020 | 05/02/2020 | 0 | TK_Complete | -824745350 | 197 | -824745350_197
MML3RSTDES4120 | TT_Task | Final design Review/ Comments from Project Manager: Test Specification of Driving gear system | 06/12/2019 | 23/12/2019 | 06/12/2019 | 23/12/2019 | 0 | TK_Complete | -824745350 | 226 | -824745350_226
MML3RSTDES4130 | TT_Task | Final design Review/ Comments from Project Manager: Test Specification of Gearbox | 06/12/2019 | 23/12/2019 | 06/12/2019 | 23/12/2019 | 0 | TK_Complete | -824745350 | 226 | -824745350_226
MML3RSTDES4140 | TT_Task | Final design Review/ Comments from Project Manager: Gear, analysis of stresses, selection of bearing, gear case and tran | 06/12/2019 | 23/12/2019 | 06/12/2019 | 23/12/2019 | 0 | TK_Complete | -824745350 | 198 | -824745350_198
MML3RSTDES4150 | TT_Task | Final design Review/ Comments from Project Manager: Test specification of Wheel Flange Lubricator | 30/11/2019 | 11/12/2019 | 30/11/2019 | 11/12/2019 | 0 | TK_Complete | -824745350 | 144 | -824745350_144
MML3RSTDES4160 | TT_Task | Final design Review/ Comments from Project Manager: Life cycle calculation of Axle Box | 29/11/2019 | 12/12/2019 | 29/11/2019 | 14/12/2019 | 0 | TK_Complete | -824745350 | 199 | -824745350_199
MML3RSTDES4170 | TT_Task | Final design Review/ Comments from Project Manager: Brake Performance Calculations | 28/11/2019 | 13/12/2019 | 28/11/2019 | 13/12/2019 | 0 | TK_Complete | -824745350 | 227 | -824745350_227
MML3RSTDES4180 | TT_Task | Final design Review/ Comments from Project Manager: Test specification of Passenger saloon Door | 06/12/2019 | 19/12/2019 | 06/12/2019 | 19/12/2019 | 0 | TK_Complete | -824745350 | 146 | -824745350_146
MML3RSTDES4190 | TT_Task | Final design Review/ Comments from Project Manager: Test specification of Front Detrainment Doors | 25/12/2019 | 21/01/2020 | 25/12/2019 | 21/01/2020 | 0 | TK_Complete | -824745350 | 121 | -824745350_121
MML3RSTDES4200 | TT_Task | Final design Review/ Comments from Project Manager: Test specification of 25 kV Vacuum Circuit Breaker | 21/12/2019 | 08/01/2020 | 21/12/2019 | 08/01/2020 | 0 | TK_Complete | -824745350 | 147 | -824745350_147
MML3RSTDES4210 | TT_Task | Final design Review/ Comments from Project Manager: Test specification of Surge Arrestor | 13/02/2020 | 04/03/2020 | 13/02/2020 | 04/03/2020 | 0 | TK_Complete | -824745350 | 149 | -824745350_149
MML3RSTDES4220 | TT_Task | Final design Review/ Comments from Project Manager: Test Specification of Traction Convertor | 25/10/2019 | 15/11/2019 | 25/10/2019 | 15/11/2019 | 0 | TK_Complete | -824745350 | 150 | -824745350_150
MML3RSTDES4230 | TT_Task | Final design Review/ Comments from Project Manager: Test Specification of Traction Motor | 25/10/2019 | 09/11/2019 | 25/10/2019 | 09/11/2019 | 0 | TK_Complete | -824745350 | 151 | -824745350_151
MML3RSTDES4240 | TT_Task | Final design Review/ Comments from Project Manager: Test specification of Roof Mounted Pantograph | 11/11/2019 | 23/11/2019 | 11/11/2019 | 23/11/2019 | 0 | TK_Complete | -824745350 | 200 | -824745350_200
MML3RSTDES4250 | TT_Task | Final design Review/ Comments from Project Manager: Test specification of Transformer | 24/10/2019 | 07/11/2019 | 24/10/2019 | 07/11/2019 | 0 | TK_Complete | -824745350 | 176 | -824745350_176
MML3RSTDES4260 | TT_Task | Final design Review/ Comments from Project Manager: Test specification of Earthing Switch | 21/12/2019 | 08/01/2020 | 21/12/2019 | 08/01/2020 | 0 | TK_Complete | -824745350 | 148 | -824745350_148
MML3RSTDES4270 | TT_Task | Final design Review/ Comments from Project Manager: Harmonic Calculations | 20/12/2019 | 03/01/2020 | 20/12/2019 | 03/01/2020 | 0 | TK_Complete | -824745350 | 201 | -824745350_201
MML3RSTDES4280 | TT_Task | Final design Review/ Comments from Project Manager: Test Specification of Auxiliary Convertor | 25/10/2019 | 11/11/2019 | 25/10/2019 | 11/11/2019 | 0 | TK_Complete | -824745350 | 153 | -824745350_153
MML3RSTDES4290 | TT_Task | Final design Review/ Comments from Project Manager: Software document for Door System | 25/12/2019 | 07/01/2020 | 25/12/2019 | 31/01/2020 | 0 | TK_Complete | -824745350 | 202 | -824745350_202
MML3RSTDES4300 | TT_Task | Final design Review/ Comments from Project Manager: Software document for VAC System | 25/12/2019 | 07/01/2020 | 25/12/2019 | 07/01/2020 | 0 | TK_Complete | -824745350 | 125 | -824745350_125
MML3RSTDES4310 | TT_Task | Final design Review/ Comments from Project Manager: Software document for Brake system | 25/12/2019 | 08/01/2020 | 25/12/2019 | 08/01/2020 | 0 | TK_Complete | -824745350 | 118 | -824745350_118
MML3RSTDES4320 | TT_Task | Final design Review/ Comments from Project Manager: Software document for propulsion system | 06/12/2019 | 24/12/2019 | 06/12/2019 | 24/12/2019 | 0 | TK_Complete | -824745350 | 122 | -824745350_122
MML3RSTDES4330 | TT_Task | Final design Review/ Comments from Project Manager: Software document for Auxiliary supply system | 06/12/2019 | 20/12/2019 | 06/12/2019 | 20/12/2019 | 0 | TK_Complete | -824745350 | 124 | -824745350_124
MML3RSTDES4340 | TT_Task | Final design Review/ Comments from Project Manager: Test Specification of Saloon VAC | 10/12/2019 | 17/12/2019 | 10/12/2019 | 17/12/2019 | 0 | TK_Complete | -824745350 | 157 | -824745350_157
MML3RSTDES4350 | TT_Task | Final design Review/ Comments from Project Manager: Test Specification of Dynamometer Test | 07/02/2020 | 25/02/2020 | 07/02/2020 | 25/02/2020 | 0 | TK_Complete | -824745350 | 203 | -824745350_203
MML3RSTDES4360 | TT_Task | Final design Review/ Comments from Project Manager: Detail Description of Bogie Brake Equipment | 15/11/2019 | 28/11/2019 | 15/11/2019 | 28/11/2019 | 0 | TK_Complete | -824745350 | 204 | -824745350_204
MML3RSTDES4370 | TT_Task | Final design Review/ Comments from Project Manager: Test Specification for Air Supply System | 02/12/2019 | 17/12/2019 | 02/12/2019 | 17/12/2019 | 0 | TK_Complete | -824745350 | 228 | -824745350_228
MML3RSTDES4380 | TT_Task | Final design Review/ Comments from Project Manager: Type Test Specification - Saloon Lighting and Gangway Lighting | 27/11/2019 | 10/12/2019 | 27/11/2019 | 13/12/2019 | 0 | TK_Complete | -824745350 | 205 | -824745350_205
MML3RSTDES4390 | TT_Task | Final design Review/ Comments from Project Manager: Description for Neutral Section Detection and functioning | 19/06/2019 | 29/06/2019 | 19/06/2019 | 29/06/2019 | 0 | TK_Complete | -824745350 | 206 | -824745350_206
MML3RSTDES4400 | TT_Task | Final design Review/ Comments from Project Manager: Electrical Pure Principle scheme - Train | 31/12/2019 | 07/02/2020 | 31/12/2019 | 07/02/2020 | 0 | TK_Complete | -824745350 | 207 | -824745350_207
MML3RSTDES4410 | TT_Task | Final design Review/ Comments from Project Manager: Test Specification of Master Controller | 01/01/2020 | 17/01/2020 | 01/01/2020 | 17/01/2020 | 0 | TK_Complete | -824745350 | 177 | -824745350_177
MML3RSTDES4420 | TT_Task | Final design Review/ Comments from Project Manager: Technical specification and Drawings of PAPIS | 19/02/2020 | 03/03/2020 | 19/02/2020 | 03/03/2020 | 0 | TK_Complete | -824745350 | 128 | -824745350_128
MML3RSTDES4430 | TT_Task | Final design Review/ Comments from Project Manager: Test Specification of PAPIS system | 18/02/2020 | 03/03/2020 | 18/02/2020 | 03/03/2020 | 0 | TK_Complete | -824745350 | 128 | -824745350_128
MML3RSTDES4440 | TT_Task | Final design Review/ Comments from Project Manager: Solution Principal Scheme | 31/12/2019 | 03/03/2020 | 31/12/2019 | 03/03/2020 | 0 | TK_Complete | -824745350 | 209 | -824745350_209
MML3RSTDES4450 | TT_Task | Final design Review/ Comments from Project Manager: Test Specification - Gangway | 24/10/2019 | 06/11/2019 | 24/10/2019 | 06/11/2019 | 0 | TK_Complete | -824745350 | 229 | -824745350_229
MML3RSTDES4460 | TT_Task | Final design Review/ Comments from Project Manager: Type Test Specification - Load test of Floor panel | 29/10/2019 | 13/11/2019 | 29/10/2019 | 13/11/2019 | 0 | TK_Complete | -824745350 | 210 | -824745350_210
MML3RSTDES4470 | TT_Task | Final design Review/ Comments from Project Manager: Type Test Specification - Windscreen | 29/10/2019 | 02/11/2019 | 29/10/2019 | 02/11/2019 | 0 | TK_Complete | -824745350 | 211 | -824745350_211
MML3RSTDES4480 | TT_Task | Final design Review/ Comments from Project Manager: Type Test Specification - Windows | 29/10/2019 | 13/11/2019 | 29/10/2019 | 13/11/2019 | 0 | TK_Complete | -824745350 | 229 | -824745350_229
MML3RSTDES4490 | TT_Task | Final design Review/ Comments from Project Manager: Type Test Specification - Interior Components | 20/11/2019 | 30/12/2019 | 20/11/2019 | 30/11/2019 | 0 | TK_Complete | -824745350 | 229 | -824745350_229
MML3RSTDES4500 | TT_Task | Final design Review/ Comments from Project Manager: Type Test Specification - Gauging (Static + Kinematic) | 16/10/2019 | 29/10/2019 | 16/10/2019 | 03/12/2019 | 0 | TK_Complete | -824745350 | 213 | -824745350_213
MML3RSTDES4510 | TT_Task | Final design Review/ Comments from Project Manager: Type Test Specification - Straphangers Endurance | 25/10/2019 | 06/11/2019 | 25/10/2019 | 06/11/2019 | 0 | TK_Complete | -824745350 | 214 | -824745350_214
MML3RSTDES4520 | TT_Task | Final design Review/ Comments from Project Manager: Type Test Specification - Couplers | 24/10/2019 | 06/11/2019 | 24/10/2019 | 06/11/2019 | 0 | TK_Complete | -824745350 | 229 | -824745350_229
MML3RSTDES4530 | TT_Task | Final design Review/ Comments from Project Manager: Type Test Specification - Floor Fire Resistance | 25/10/2019 | 02/11/2019 | 25/10/2019 | 02/11/2019 | 0 | TK_Complete | -824745350 | 216 | -824745350_216
MML3RSTDES4540 | TT_Task | Final design Review/ Comments from Project Manager: Fire Engineering Report - Prediction | 15/02/2020 | 27/02/2020 | 15/02/2020 | 27/02/2020 | 0 | TK_Complete | -824745350 | 217 | -824745350_217
MML3RSTDES4550 | TT_Task | Final design Review/ Comments from Project Manager: Noise Report - Final Prediction | 30/01/2020 | 03/02/2020 | 30/01/2020 | 03/02/2020 | 0 | TK_Complete | -824745350 | 179 | -824745350_179
MML3RSTDES4560 | TT_Task | Final design Review/ Comments from Project Manager: Operation ; MaintenanceManuals Plan | 20/11/2019 | 03/12/2019 | 20/11/2019 | 03/12/2019 | 0 | TK_Complete | -824745350 | 45 | -824745350_45
MML3RSTDES4570 | TT_Task | Final design Review/ Comments from Project Manager: Training Plan | 17/10/2019 | 02/11/2019 | 17/10/2019 | 02/11/2019 | 0 | TK_Complete | -824745350 | 38 | -824745350_38
MML3RSTDES4580 | TT_Task | Final design Review/ Comments from Project Manager: Spare Management Plan | 21/11/2019 | 04/12/2019 | 21/11/2019 | 04/12/2019 | 0 | TK_Complete | -824745350 | 33 | -824745350_33
MML3RSTDES4590 | TT_Task | Final design Review/ Comments from Project Manager: Assistance of Maintenance Plan | 21/11/2019 | 04/12/2019 | 21/11/2019 | 04/12/2019 | 0 | TK_Complete | -824745350 | 45 | -824745350_45
MML3RSTDES4600 | TT_Task | Final design Review/ Comments from Project Manager: Comprehensive Maintenance Plan | 20/11/2019 | 04/12/2019 | 20/11/2019 | 04/12/2019 | 0 | TK_Complete | -824745350 | 45 | -824745350_45
MML3RSTDES4610 | TT_Task | Final design Review/ Comments from Project Manager: Spare Parts List | 13/12/2019 | 13/12/2019 | 13/12/2019 | 13/12/2019 | 0 | TK_Complete | -824745350 | 218 | -824745350_218
MML3RSTDES4620 | TT_Task | Final design Review/ Comments from Project Manager: Train Simulator ; CBT Specification | 20/02/2020 | 03/03/2020 | 20/02/2020 | 03/03/2020 | 0 | TK_Complete | -824745350 | 219 | -824745350_219
MML3RSTDES4630 | TT_Task | Final design Review/ Comments from Project Manager: Maintenance Demonstration plan | 13/12/2019 | 13/12/2019 | 14/12/2019 | 24/12/2019 | 0 | TK_Complete | -824745350 | 45 | -824745350_45
MML3RSTDES4640 | TT_Task | Final design Review/ Comments from Project Manager: Quantitative fault tree analysis | 30/01/2020 | 13/03/2020 | 30/01/2020 | 13/03/2020 | 0 | TK_Complete | -824745350 | 220 | -824745350_220
MML3RSTDES4650 | TT_Task | Final design Review/ Comments from Project Manager: Failure modes effects and criticality analysis (FMECA) | 23/12/2019 | 23/12/2019 | 24/12/2019 | 24/01/2020 | 0 | TK_Complete | -824745350 | 230 | -824745350_230
MML3RSTDES4660 | TT_Task | Final design Review/ Comments from Project Manager: Design Safety Study Report | 28/01/2020 | 13/02/2020 | 28/01/2020 | 13/02/2020 | 0 | TK_Complete | -824745350 | 42 | -824745350_42
MML3RSTDES4670 | TT_Task | Final design Review/ Comments from Project Manager: Hazard Log | 26/10/2019 | 06/11/2019 | 26/10/2019 | 06/11/2019 | 0 | TK_Complete | -824745350 | 47 | -824745350_47
MML3RSTDES4680 | TT_Task | Final design Review/ Comments from Project Manager: Safety Critical Item List | 24/12/2019 | 07/01/2020 | 24/12/2019 | 07/01/2020 | 0 | TK_Complete | -824745350 | 231 | -824745350_231
MML3RSTDES4690 | TT_Task | Final design Review/ Comments from Project Manager: Reliability Critical Item List | 24/12/2019 | 10/01/2020 | 24/12/2019 | 10/01/2020 | 0 | TK_Complete | -824745350 | 231 | -824745350_231
MML3RSTDES4700 | TT_Task | Final design Review/ Comments from Project Manager: RAM demonstration ; FRACAS Plan | 27/11/2019 | 04/12/2019 | 27/11/2019 | 04/12/2019 | 0 | TK_Complete | -824745350 | 232 | -824745350_232
MML3RSTDES4710 | TT_Task | Final design Review/ Comments from Project Manager: Application Safety Case | 28/01/2020 | 13/02/2020 | 28/01/2020 | 13/02/2020 | 0 | TK_Complete | -824745350 | 42 | -824745350_42
MML3RSTDES8240 | TT_Task | Final design Review/ Comments from Project Manager: Test Specification of Wayside Measurement ; Monitoring System | 05/02/2020 | 27/02/2020 | 05/02/2020 | 27/02/2020 | 0 | TK_Complete | -824745350 | 222 | -824745350_222
MML3RSTDES8250 | TT_Task | Final design Review/ Comments from Project Manager: Technical Specification of CMMS | 21/07/2020 | 06/08/2020 | 21/07/2020 | 06/08/2020 | 0 | TK_Complete | -824745350 | 223 | -824745350_223
MML3RSTDES4720 | TT_Task | Final design Resubmission: Test Specification of Battery System | 08/01/2020 | 13/05/2020 | 08/01/2020 | 13/05/2020 | 0 | TK_Complete | -824745350 | 185 | -824745350_185
MML3RSTDES4730 | TT_Task | Final design Resubmission: Train Operation Control Description | 07/01/2020 | 20/01/2020 | 07/01/2020 | 04/12/2020 | 0 | TK_Complete | -824745350 | 224 | -824745350_224
MML3RSTDES4740 | TT_Task | Final design Resubmission: Energy Consumption Anlaysis | 25/11/2019 | 17/05/2020 | 25/11/2019 | 17/05/2020 | 0 | TK_Complete | -824745350 | 186 | -824745350_186
MML3RSTDES4750 | TT_Task | Final design Resubmission: Ride Index Test Specification | 01/01/2020 | 14/01/2020 | 01/01/2020 | 09/12/2020 | 0 | TK_Complete | -824745350 | 187 | -824745350_187
MML3RSTDES4760 | TT_Task | Final design Resubmission: Final Vehicle Performance | 16/12/2019 | 06/05/2020 | 16/12/2019 | 06/05/2020 | 0 | TK_Complete | -824745350 | 116 | -824745350_116
MML3RSTDES4770 | TT_Task | Final design Resubmission: Inspection instruction of complete Bogie | 12/12/2019 | 25/12/2019 | 12/12/2019 | 04/02/2021 | 0 | TK_Complete | -824745350 | 188 | -824745350_188
MML3RSTDES4780 | TT_Task | Final design Resubmission: Vehicle Dynamic Analysis of Bogie | 01/01/2020 | 14/01/2020 | 01/01/2020 | 04/12/2020 | 0 | TK_Complete | -824745350 | 189 | -824745350_189
MML3RSTDES4790 | TT_Task | Final design Resubmission: FEA of Bogie Frame | 12/12/2019 | 25/09/2020 | 12/12/2019 | 07/09/2020 | 0 | TK_Complete | -824745350 | 190 | -824745350_190
MML3RSTDES4800 | TT_Task | Final design Resubmission: Test Specification of Bogie Frame static load / Fatigue load | 12/12/2019 | 07/09/2020 | 12/12/2019 | 07/09/2020 | 0 | TK_Complete | -824745350 | 191 | -824745350_191
MML3RSTDES4810 | TT_Task | Final design Resubmission: Test Specification of Primary suspension | 12/12/2019 | 25/12/2019 | 12/12/2019 | 12/01/2021 | 0 | TK_Complete | -824745350 | 192 | -824745350_192
MML3RSTDES4820 | TT_Task | Final design Resubmission: Test Specification of Damper | 12/12/2019 | 14/08/2020 | 12/12/2019 | 14/08/2020 | 0 | TK_Complete | -824745350 | 193 | -824745350_193
MML3RSTDES4830 | TT_Task | Final design Resubmission: Test Specification of Wheel | 12/12/2019 | 07/09/2020 | 12/12/2019 | 07/09/2020 | 0 | TK_Complete | -824745350 | 194 | -824745350_194
MML3RSTDES4840 | TT_Task | Final design Resubmission: Test specification of Axle | 12/12/2019 | 16/08/2020 | 12/12/2019 | 16/08/2020 | 0 | TK_Complete | -824745350 | 195 | -824745350_195
MML3RSTDES4850 | TT_Task | Final design Resubmission: Thermal Calculations of Wheel | 08/09/2020 | 14/09/2020 | 08/09/2020 | 14/09/2020 | 0 | TK_Complete | -824745350 | 196 | -824745350_196
MML3RSTDES4860 | TT_Task | Final design Resubmission: Wheel Stress calculations | 30/11/2019 | 07/09/2020 | 30/11/2019 | 07/09/2020 | 0 | TK_Complete | -824745350 | 225 | -824745350_225
MML3RSTDES4870 | TT_Task | Final design Resubmission: Axle strength calculations | 28/11/2019 | 15/08/2020 | 28/11/2019 | 15/08/2020 | 0 | TK_Complete | -824745350 | 195 | -824745350_195
MML3RSTDES4880 | TT_Task | Final design Resubmission: FEA of center pivot, axle box and Traction Linkage | 08/09/2020 | 21/09/2020 | 08/09/2020 | 04/12/2020 | 0 | TK_Complete | -824745350 | 197 | -824745350_197
MML3RSTDES4890 | TT_Task | Final design Resubmission: Test Specification of Driving gear system | 24/12/2019 | 17/07/2020 | 24/12/2019 | 17/07/2020 | 0 | TK_Complete | -824745350 | 226 | -824745350_226
MML3RSTDES4900 | TT_Task | Final design Resubmission: Test Specification of Gearbox | 24/12/2019 | 17/07/2020 | 24/12/2019 | 17/07/2020 | 0 | TK_Complete | -824745350 | 226 | -824745350_226
MML3RSTDES4910 | TT_Task | Final design Resubmission: Gear, analysis of stresses, selection of bearing, gear case and transmissioin | 24/12/2019 | 22/09/2020 | 24/12/2019 | 22/09/2020 | 0 | TK_Complete | -824745350 | 198 | -824745350_198
MML3RSTDES4920 | TT_Task | Final design Resubmission: Test specification of Wheel Flange Lubricator | 12/12/2019 | 25/12/2019 | 12/12/2019 | 23/11/2020 | 0 | TK_Complete | -824745350 | 144 | -824745350_144
MML3RSTDES4930 | TT_Task | Final design Resubmission: Life cycle calculation of Axle Box | 17/08/2020 | 17/08/2020 | 17/08/2020 | 09/11/2020 | 0 | TK_Complete | -824745350 | 199 | -824745350_199
MML3RSTDES4940 | TT_Task | Final design Resubmission: Brake Performance Calculations | 14/12/2019 | 31/05/2020 | 14/12/2019 | 31/05/2020 | 0 | TK_Complete | -824745350 | 227 | -824745350_227
MML3RSTDES4950 | TT_Task | Final design Resubmission: Test specification of Passenger saloon Door | 20/12/2019 | 02/01/2020 | 20/12/2019 | 16/02/2021 | 0 | TK_Complete | -824745350 | 146 | -824745350_146
MML3RSTDES4960 | TT_Task | Final design Resubmission: Test specification of Front Detrainment Doors | 22/01/2020 | 04/02/2020 | 22/01/2020 | 18/03/2021 | 0 | TK_Complete | -824745350 | 89 | -824745350_89
MML3RSTDES4970 | TT_Task | Final design Resubmission: Test specification of 25 kV Vacuum Circuit Breaker | 14/01/2021 | 14/01/2021 | 09/01/2020 | 14/01/2021 | 0 | TK_Complete | -824745350 | 147 | -824745350_147
MML3RSTDES4980 | TT_Task | Final design Resubmission: Test specification of Surge Arrestor | 05/03/2020 | 04/07/2020 | 05/03/2020 | 04/07/2020 | 0 | TK_Complete | -824745350 | 149 | -824745350_149
MML3RSTDES4990 | TT_Task | Final design Resubmission: Test Specification of Traction Convertor | 18/11/2019 | 15/08/2020 | 18/11/2019 | 15/08/2020 | 0 | TK_Complete | -824745350 | 150 | -824745350_150
MML3RSTDES5000 | TT_Task | Final design Resubmission: Test Specification of Traction Motor | 11/11/2019 | 30/03/2020 | 11/11/2019 | 30/03/2020 | 0 | TK_Complete | -824745350 | 151 | -824745350_151
MML3RSTDES5010 | TT_Task | Final design Resubmission: Test specification of Roof Mounted Pantograph | 25/11/2019 | 08/12/2019 | 25/11/2019 | 29/01/2021 | 0 | TK_Complete | -824745350 | 200 | -824745350_200
MML3RSTDES5020 | TT_Task | Final design Resubmission: Test specification of Transformer | 08/11/2019 | 16/08/2020 | 08/11/2019 | 16/08/2020 | 0 | TK_Complete | -824745350 | 176 | -824745350_176
MML3RSTDES5030 | TT_Task | Final design Resubmission: Test specification of Earthing Switch | 09/01/2020 | 06/08/2020 | 09/01/2020 | 06/08/2020 | 0 | TK_Complete | -824745350 | 148 | -824745350_148
MML3RSTDES5040 | TT_Task | Final design Resubmission: Harmonic Calculations | 04/01/2020 | 16/04/2020 | 04/01/2020 | 16/04/2020 | 0 | TK_Complete | -824745350 | 201 | -824745350_201
MML3RSTDES5050 | TT_Task | Final design Resubmission: Test Specification of Auxiliary Convertor | 12/11/2019 | 25/11/2019 | 12/11/2019 | 23/11/2020 | 0 | TK_Complete | -824745350 | 153 | -824745350_153
MML3RSTDES5060 | TT_Task | Final design Resubmission: Software document for Door System | 03/02/2020 | 16/02/2020 | 03/02/2020 | 17/01/2021 | 0 | TK_Complete | -824745350 | 202 | -824745350_202
MML3RSTDES5070 | TT_Task | Final design Resubmission: Software document for VAC System | 08/01/2020 | 17/07/2020 | 08/01/2020 | 17/07/2020 | 0 | TK_Complete | -824745350 | 125 | -824745350_125
MML3RSTDES5080 | TT_Task | Final design Resubmission: Software document for Brake system | 09/01/2020 | 22/01/2020 | 09/01/2020 | 17/01/2021 | 0 | TK_Complete | -824745350 | 118 | -824745350_118
MML3RSTDES5090 | TT_Task | Final design Resubmission: Software document for propulsion system | 25/12/2019 | 07/01/2020 | 25/12/2019 | 17/01/2021 | 0 | TK_Complete | -824745350 | 122 | -824745350_122
MML3RSTDES5100 | TT_Task | Final design Resubmission: Software document for Auxiliary supply system | 23/12/2019 | 05/01/2020 | 23/12/2019 | 16/01/2021 | 0 | TK_Complete | -824745350 | 124 | -824745350_124
MML3RSTDES5110 | TT_Task | Final design Resubmission: Test Specification of Saloon VAC | 18/12/2019 | 13/05/2020 | 18/12/2019 | 13/05/2020 | 0 | TK_Complete | -824745350 | 157 | -824745350_157
MML3RSTDES5120 | TT_Task | Final design Resubmission: Test Specification of Dynamometer Test | 26/02/2020 | 18/09/2020 | 26/02/2020 | 18/09/2020 | 0 | TK_Complete | -824745350 | 203 | -824745350_203
MML3RSTDES5130 | TT_Task | Final design Resubmission: Detail Description of Bogie Brake Equipment | 29/11/2019 | 24/03/2020 | 29/11/2019 | 24/03/2020 | 0 | TK_Complete | -824745350 | 204 | -824745350_204
MML3RSTDES5140 | TT_Task | Final design Resubmission: Test Specification for Air Supply System | 18/12/2019 | 17/03/2020 | 18/12/2019 | 17/03/2020 | 0 | TK_Complete | -824745350 | 228 | -824745350_228
MML3RSTDES5150 | TT_Task | Final design Resubmission: Type Test Specification - Saloon Lighting and Gangway Lighting | 14/12/2019 | 27/12/2019 | 14/12/2019 | 26/02/2021 | 0 | TK_Complete | -824745350 | 205 | -824745350_205
MML3RSTDES5160 | TT_Task | Final design Resubmission: Description for Neutral Section Detection and functioning | 30/06/2019 | 03/09/2020 | 30/06/2019 | 03/09/2020 | 0 | TK_Complete | -824745350 | 206 | -824745350_206
MML3RSTDES5170 | TT_Task | Final design Resubmission: Electrical Pure Principle scheme - Train | 01/07/2020 | 01/07/2020 | 08/02/2020 | 01/07/2020 | 0 | TK_Complete | -824745350 | 207 | -824745350_207
MML3RSTDES5180 | TT_Task | Final design Resubmission: Test Specification of Master Controller | 20/01/2020 | 10/04/2020 | 20/01/2020 | 10/04/2020 | 0 | TK_Complete | -824745350 | 162 | -824745350_162
MML3RSTDES5190 | TT_Task | Final design Resubmission: Technical specification and Drawings of PAPIS | 04/03/2020 | 03/06/2021 | 04/03/2020 | 03/06/2021 | 0 | TK_Complete | -824745350 | 208 | -824745350_208
MML3RSTDES5200 | TT_Task | Final design Resubmission: Test Specification of PAPIS system | 04/03/2020 | 29/11/2020 | 04/03/2020 | 16/03/2021 | 0 | TK_Complete | -824745350 | 138 | -824745350_138
MML3RSTDES5210 | TT_Task | Final design Resubmission: Solution Principal Scheme | 01/07/2020 | 01/07/2020 | 04/03/2020 | 01/07/2020 | 0 | TK_Complete | -824745350 | 209 | -824745350_209
MML3RSTDES5220 | TT_Task | Final design Resubmission: Test Specification - Gangway | 07/11/2019 | 12/08/2020 | 07/11/2019 | 12/08/2020 | 0 | TK_Complete | -824745350 | 233 | -824745350_233
MML3RSTDES5230 | TT_Task | Final design Resubmission: Type Test Specification - Load test of Floor panel | 14/11/2019 | 07/09/2020 | 14/11/2019 | 07/09/2020 | 0 | TK_Complete | -824745350 | 210 | -824745350_210
MML3RSTDES5240 | TT_Task | Final design Resubmission: Type Test Specification - Windscreen | 04/11/2019 | 17/11/2019 | 04/11/2019 | 30/12/2020 | 0 | TK_Complete | -824745350 | 211 | -824745350_211
MML3RSTDES5250 | TT_Task | Final design Resubmission: Type Test Specification - Windows | 14/11/2019 | 27/11/2019 | 14/11/2019 | 30/12/2020 | 0 | TK_Complete | -824745350 | 212 | -824745350_212
MML3RSTDES5260 | TT_Task | Final design Resubmission: Type Test Specification - Interior Components | 02/12/2019 | 15/12/2019 | 02/12/2019 | 13/01/2021 | 0 | TK_Complete | -824745350 | 212 | -824745350_212
MML3RSTDES5270 | TT_Task | Final design Resubmission: Type Test Specification - Gauging (Static + Kinematic) | 04/12/2019 | 28/07/2020 | 04/12/2019 | 28/07/2020 | 0 | TK_Complete | -824745350 | 213 | -824745350_213
MML3RSTDES5280 | TT_Task | Final design Resubmission: Type Test Specification - Straphangers Endurance | 07/11/2019 | 17/05/2020 | 07/11/2019 | 17/05/2020 | 0 | TK_Complete | -824745350 | 214 | -824745350_214
MML3RSTDES5290 | TT_Task | Final design Resubmission: Type Test Specification - Couplers | 07/11/2019 | 20/11/2019 | 07/11/2019 | 15/02/2021 | 0 | TK_Complete | -824745350 | 215 | -824745350_215
MML3RSTDES5300 | TT_Task | Final design Resubmission: Type Test Specification - Floor Fire Resistance | 04/11/2019 | 13/10/2020 | 04/11/2019 | 13/10/2020 | 0 | TK_Complete | -824745350 | 216 | -824745350_216
MML3RSTDES5310 | TT_Task | Final design Resubmission: Fire Engineering Report - Prediction | 28/02/2020 | 18/02/2021 | 28/02/2020 | 18/02/2021 | 0 | TK_Complete | -824745350 | 217 | -824745350_217
MML3RSTDES5320 | TT_Task | Final design Resubmission: Noise Report - Final Prediction | 04/02/2020 | 17/02/2020 | 04/02/2020 | 02/02/2021 | 0 | TK_Complete | -824745350 | 179 | -824745350_179
MML3RSTDES5330 | TT_Task | Final design Resubmission: Operation ; MaintenanceManuals Plan | 04/12/2019 | 08/05/2020 | 04/12/2019 | 08/05/2020 | 0 | TK_Complete | -824745350 | 234 | -824745350_234
MML3RSTDES5340 | TT_Task | Final design Resubmission: Training Plan | 04/11/2019 | 20/11/2019 | 04/11/2019 | 20/11/2019 | 0 | TK_Complete | -824745350 | 174 | -824745350_174
MML3RSTDES5350 | TT_Task | Final design Resubmission: Spare Management Plan | 05/12/2019 | 18/02/2020 | 05/12/2019 | 04/02/2020 | 0 | TK_Complete | -824745350 | 26 | -824745350_26
MML3RSTDES5360 | TT_Task | Final design Resubmission: Assistance of Maintenance Plan | 05/12/2019 | 30/04/2020 | 05/12/2019 | 30/04/2020 | 0 | TK_Complete | -824745350 | 234 | -824745350_234
MML3RSTDES5370 | TT_Task | Final design Resubmission: Comprehensive Maintenance Plan | 05/12/2019 | 30/04/2020 | 05/12/2019 | 30/04/2020 | 0 | TK_Complete | -824745350 | 234 | -824745350_234
MML3RSTDES5380 | TT_Task | Final design Resubmission: Spare Parts List | 14/12/2019 | 08/07/2020 | 14/12/2019 | 08/07/2020 | 0 | TK_Complete | -824745350 | 218 | -824745350_218
MML3RSTDES5390 | TT_Task | Final design Resubmission: Train Simulator ; CBT Specification | 04/03/2020 | 17/05/2021 | 04/03/2020 | 17/05/2021 | 0 | TK_Complete | -824745350 | 219 | -824745350_219
MML3RSTDES5400 | TT_Task | Final design Resubmission: Maintenance Demonstration plan | 25/12/2019 | 06/05/2020 | 25/12/2019 | 06/05/2020 | 0 | TK_Complete | -824745350 | 234 | -824745350_234
MML3RSTDES5410 | TT_Task | Final design Resubmission: Quantitative fault tree analysis | 14/03/2021 | 15/04/2021 | 14/03/2021 | 15/04/2021 | 0 | TK_Complete | -824745350 | 220 | -824745350_220
MML3RSTDES5420 | TT_Task | Final design Resubmission: Failure modes effects and criticality analysis (FMECA) | 25/01/2020 | 17/02/2020 | 25/01/2020 | 17/02/2020 | 0 | TK_Complete | -824745350 | 230 | -824745350_230
MML3RSTDES5430 | TT_Task | Final design Resubmission: Design Safety Study Report | 28/02/2020 | 18/02/2021 | 28/02/2020 | 25/05/2021 | 0 | TK_Complete | -824745350 | 235 | -824745350_235
MML3RSTDES5440 | TT_Task | Final design Resubmission: Hazard Log | 09/11/2020 | 15/04/2021 | 09/11/2020 | 15/04/2021 | 0 | TK_Complete | -824745350 | 221 | -824745350_221
MML3RSTDES5450 | TT_Task | Final design Resubmission: Safety Critical Item List | 08/01/2020 | 18/02/2020 | 08/01/2020 | 18/02/2020 | 0 | TK_Complete | -824745350 | 231 | -824745350_231
MML3RSTDES5460 | TT_Task | Final design Resubmission: Reliability Critical Item List | 13/01/2020 | 24/04/2020 | 13/01/2020 | 24/04/2020 | 0 | TK_Complete | -824745350 | 231 | -824745350_231
MML3RSTDES5470 | TT_Task | Final design Resubmission: RAM demonstration ; FRACAS Plan | 05/12/2019 | 24/04/2020 | 05/12/2019 | 24/04/2020 | 0 | TK_Complete | -824745350 | 232 | -824745350_232
MML3RSTDES5480 | TT_Task | Final design Resubmission: Application Safety Case | 15/02/2021 | 15/04/2021 | 15/02/2021 | 15/04/2021 | 0 | TK_Complete | -824745350 | 235 | -824745350_235
MML3RSTSPA7080 | TT_Task | Final design Resubmission:Test Specification of Wayside Measurement ; Monitoring System | 25/01/2021 | 29/01/2021 | 28/02/2020 | 19/05/2021 | 0 | TK_Complete | -824745350 | 222 | -824745350_222
MML3RSTSPA7090 | TT_Task | Final design Resubmission: Technical Specification of CMMS | 25/01/2021 | 29/01/2021 | 07/08/2020 | 29/01/2021 | 0 | TK_Complete | -824745350 | 223 | -824745350_223
MML3RSTSPA7100 | TT_Task | Final design Resubmission: Test Specification of Combined Test Bed | 24/07/2020 | 10/06/2021 | 24/07/2020 | 10/06/2021 | 0 | TK_Complete | -824745350 | 233 | -824745350_233
MML3RSTDES5490 | TT_Task | Final design NONO/ NOWC from Project Manager: Test Specification of Battery System | 14/05/2020 | 01/06/2020 | 14/05/2020 | 01/06/2020 | 0 | TK_Complete | -824745350 | 185 | -824745350_185
MML3RSTDES5500 | TT_Task | Final design NONO/ NOWC from Project Manager: Train Operation Control Description | 05/12/2020 | 16/12/2020 | 05/12/2020 | 16/12/2020 | 0 | TK_Complete | -824745350 | 115 | -824745350_115
MML3RSTDES5510 | TT_Task | Final design NONO/ NOWC from Project Manager: Energy Consumption Anlaysis | 18/05/2020 | 21/05/2020 | 18/05/2020 | 21/05/2020 | 0 | TK_Complete | -824745350 | 186 | -824745350_186
MML3RSTDES5520 | TT_Task | Final design NONO/ NOWC from Project Manager: Ride Index Test Specification | 10/12/2020 | 24/12/2020 | 10/12/2020 | 24/12/2020 | 0 | TK_Complete | -824745350 | 187 | -824745350_187
MML3RSTDES5530 | TT_Task | Final design NONO/ NOWC from Project Manager: Final Vehicle Performance | 07/05/2020 | 08/05/2020 | 07/05/2020 | 08/05/2020 | 0 | TK_Complete | -824745350 | 129 | -824745350_129
MML3RSTDES5540 | TT_Task | Final design NONO/ NOWC from Project Manager: Inspection instruction of complete Bogie | 04/02/2021 | 26/02/2021 | 04/02/2021 | 26/02/2021 | 0 | TK_Complete | -824745350 | 188 | -824745350_188
MML3RSTDES5550 | TT_Task | Final design NONO/ NOWC from Project Manager: Vehicle Dynamic Analysis of Bogie | 05/12/2020 | 24/12/2020 | 05/12/2020 | 24/12/2020 | 0 | TK_Complete | -824745350 | 189 | -824745350_189
MML3RSTDES5560 | TT_Task | Final design NONO/ NOWC from Project Manager: FEA of Bogie Frame | 08/09/2020 | 21/09/2020 | 08/09/2020 | 25/09/2020 | 0 | TK_Complete | -824745350 | 190 | -824745350_190
MML3RSTDES5570 | TT_Task | Final design NONO/ NOWC from Project Manager: Test Specification of Bogie Frame static load / Fatigue load | 08/09/2020 | 21/09/2020 | 08/09/2020 | 25/09/2020 | 0 | TK_Complete | -824745350 | 191 | -824745350_191
MML3RSTDES5580 | TT_Task | Final design NONO/ NOWC from Project Manager: Test Specification of Primary suspension | 27/01/2021 | 05/02/2021 | 13/01/2021 | 20/01/2021 | 0 | TK_Complete | -824745350 | 192 | -824745350_192
MML3RSTDES5590 | TT_Task | Final design NONO/ NOWC from Project Manager: Test Specification of Damper | 15/08/2020 | 28/08/2020 | 15/08/2020 | 28/08/2020 | 0 | TK_Complete | -824745350 | 193 | -824745350_193
MML3RSTDES5600 | TT_Task | Final design NONO/ NOWC from Project Manager: Test Specification of Wheel | 08/09/2020 | 14/09/2020 | 08/09/2020 | 14/09/2020 | 0 | TK_Complete | -824745350 | 236 | -824745350_236
MML3RSTDES5610 | TT_Task | Final design NONO/ NOWC from Project Manager: Test specification of Axle | 17/08/2020 | 31/08/2020 | 17/08/2020 | 31/08/2020 | 0 | TK_Complete | -824745350 | 195 | -824745350_195
MML3RSTDES5620 | TT_Task | Final design NONO/ NOWC from Project Manager: Thermal Calculations of Wheel | 15/09/2020 | 01/10/2020 | 15/09/2020 | 01/10/2020 | 0 | TK_Complete | -824745350 | 196 | -824745350_196
MML3RSTDES5630 | TT_Task | Final design NONO/ NOWC from Project Manager: Wheel Stress calculations | 08/09/2020 | 14/09/2020 | 08/09/2020 | 14/09/2020 | 0 | TK_Complete | -824745350 | 225 | -824745350_225
MML3RSTDES5640 | TT_Task | Final design NONO/ NOWC from Project Manager: Axle strength calculations | 17/08/2020 | 28/08/2020 | 17/08/2020 | 28/08/2020 | 0 | TK_Complete | -824745350 | 195 | -824745350_195
MML3RSTDES5650 | TT_Task | Final design NONO/ NOWC from Project Manager: FEA of center pivot, axle box and Traction Linkage | 05/12/2020 | 17/12/2020 | 05/12/2020 | 17/12/2020 | 0 | TK_Complete | -824745350 | 197 | -824745350_197
MML3RSTDES5660 | TT_Task | Final design NONO/ NOWC from Project Manager: Test Specification of Driving gear system | 18/07/2020 | 06/08/2020 | 18/07/2020 | 06/08/2020 | 0 | TK_Complete | -824745350 | 182 | -824745350_182
MML3RSTDES5670 | TT_Task | Final design NONO/ NOWC from Project Manager: Test Specification of Gearbox | 18/07/2020 | 06/08/2020 | 18/07/2020 | 06/08/2020 | 0 | TK_Complete | -824745350 | 182 | -824745350_182
MML3RSTDES5680 | TT_Task | Final design NONO/ NOWC from Project Manager: Gear, analysis of stresses, selection of bearing, gear case and transmissi | 23/09/2020 | 01/10/2020 | 23/09/2020 | 01/10/2020 | 0 | TK_Complete | -824745350 | 198 | -824745350_198
MML3RSTDES5690 | TT_Task | Final design NONO/ NOWC from Project Manager: Test specification of Wheel Flange Lubricator | 24/11/2020 | 24/11/2020 | 24/11/2020 | 24/11/2020 | 0 | TK_Complete | -824745350 | 144 | -824745350_144
MML3RSTDES5700 | TT_Task | Final design NONO/ NOWC from Project Manager: Life cycle calculation of Axle Box | 10/11/2020 | 17/11/2020 | 10/11/2020 | 17/11/2020 | 0 | TK_Complete | -824745350 | 199 | -824745350_199
MML3RSTDES5710 | TT_Task | Final design NONO/ NOWC from Project Manager: Brake Performance Calculations | 01/06/2020 | 02/06/2020 | 01/06/2020 | 02/06/2020 | 0 | TK_Complete | -824745350 | 139 | -824745350_139
MML3RSTDES5720 | TT_Task | Final design NONO/ NOWC from Project Manager: Test specification of Passenger saloon Door | 05/02/2021 | 05/02/2021 | 05/02/2021 | 05/02/2021 | 0 | TK_Complete | -824745350 | 120 | -824745350_120
MML3RSTDES5730 | TT_Task | Final design NONO/ NOWC from Project Manager: Test specification of Front Detrainment Doors | 05/03/2021 | 22/03/2021 | 05/03/2021 | 22/03/2021 | 0 | TK_Complete | -824745350 | 121 | -824745350_121
MML3RSTDES5740 | TT_Task | Final design NONO/ NOWC from Project Manager: Test specification of 25 kV Vacuum Circuit Breaker | 17/02/2021 | 25/02/2021 | 17/02/2021 | 25/02/2021 | 0 | TK_Complete | -824745350 | 183 | -824745350_183
MML3RSTDES5750 | TT_Task | Final design NONO/ NOWC from Project Manager: Test specification of Surge Arrestor | 06/07/2020 | 27/07/2020 | 06/07/2020 | 27/07/2020 | 0 | TK_Complete | -824745350 | 149 | -824745350_149
MML3RSTDES5760 | TT_Task | Final design NONO/ NOWC from Project Manager: Test Specification of Traction Convertor | 17/08/2020 | 28/08/2020 | 17/08/2020 | 28/08/2020 | 0 | TK_Complete | -824745350 | 184 | -824745350_184
MML3RSTDES5770 | TT_Task | Final design NONO/ NOWC from Project Manager: Test Specification of Traction Motor | 31/03/2020 | 16/04/2020 | 31/03/2020 | 16/04/2020 | 0 | TK_Complete | -824745350 | 184 | -824745350_184
MML3RSTDES5780 | TT_Task | Final design NONO/ NOWC from Project Manager: Test specification of Roof Mounted Pantograph | 09/02/2021 | 15/02/2021 | 09/02/2021 | 15/02/2021 | 0 | TK_Complete | -824745350 | 200 | -824745350_200
MML3RSTDES5790 | TT_Task | Final design NONO/ NOWC from Project Manager: Test specification of Transformer | 17/08/2020 | 28/08/2020 | 17/08/2020 | 28/08/2020 | 0 | TK_Complete | -824745350 | 176 | -824745350_176
MML3RSTDES5800 | TT_Task | Final design NONO/ NOWC from Project Manager: Test specification of Earthing Switch | 07/08/2020 | 28/08/2020 | 07/08/2020 | 28/08/2020 | 0 | TK_Complete | -824745350 | 148 | -824745350_148
MML3RSTDES5810 | TT_Task | Final design NONO/ NOWC from Project Manager: Harmonic Calculations | 17/04/2020 | 04/05/2020 | 17/04/2020 | 04/05/2020 | 0 | TK_Complete | -824745350 | 201 | -824745350_201
MML3RSTDES5820 | TT_Task | Final design NONO/ NOWC from Project Manager: Test Specification of Auxiliary Convertor | 24/11/2020 | 24/11/2020 | 24/11/2020 | 24/11/2020 | 0 | TK_Complete | -824745350 | 51 | -824745350_51
MML3RSTDES5830 | TT_Task | Final design NONO/ NOWC from Project Manager: Software document for Door System | 18/01/2021 | 25/01/2021 | 18/01/2021 | 01/02/2021 | 0 | TK_Complete | -824745350 | 202 | -824745350_202
MML3RSTDES5840 | TT_Task | Final design NONO/ NOWC from Project Manager: Software document for VAC System | 18/07/2020 | 31/07/2020 | 18/07/2020 | 31/07/2020 | 0 | TK_Complete | -824745350 | 141 | -824745350_141
MML3RSTDES5850 | TT_Task | Final design NONO/ NOWC from Project Manager: Software document for Brake system | 25/01/2021 | 02/02/2021 | 18/01/2021 | 29/01/2021 | 0 | TK_Complete | -824745350 | 139 | -824745350_139
MML3RSTDES5860 | TT_Task | Final design NONO/ NOWC from Project Manager: Software document for propulsion system | 25/01/2021 | 03/02/2021 | 18/01/2021 | 29/01/2021 | 0 | TK_Complete | -824745350 | 140 | -824745350_140
MML3RSTDES5870 | TT_Task | Final design NONO/ NOWC from Project Manager: Software document for Auxiliary supply system | 25/01/2021 | 02/02/2021 | 18/01/2021 | 01/02/2021 | 0 | TK_Complete | -824745350 | 124 | -824745350_124
MML3RSTDES5880 | TT_Task | Final design NONO/ NOWC from Project Manager: Test Specification of Saloon VAC | 14/05/2020 | 29/05/2020 | 14/05/2020 | 29/05/2020 | 0 | TK_Complete | -824745350 | 157 | -824745350_157
MML3RSTDES5890 | TT_Task | Final design NONO/ NOWC from Project Manager: Test Specification of Dynamometer Test | 19/09/2020 | 03/10/2020 | 19/09/2020 | 03/10/2020 | 0 | TK_Complete | -824745350 | 203 | -824745350_203
MML3RSTDES5900 | TT_Task | Final design NONO/ NOWC from Project Manager: Detail Description of Bogie Brake Equipment | 25/03/2020 | 13/04/2020 | 25/03/2020 | 13/04/2020 | 0 | TK_Complete | -824745350 | 204 | -824745350_204
MML3RSTDES5910 | TT_Task | Final design NONO/ NOWC from Project Manager: Test Specification for Air Supply System | 19/03/2020 | 30/03/2020 | 19/03/2020 | 30/03/2020 | 0 | TK_Complete | -824745350 | 119 | -824745350_119
MML3RSTDES5920 | TT_Task | Final design NONO/ NOWC from Project Manager: Type Test Specification - Saloon Lighting and Gangway Lighting | 25/04/2021 | 25/04/2021 | 15/04/2021 | 23/04/2021 | 0 | TK_Complete | -824745350 | 205 | -824745350_205
MML3RSTDES5930 | TT_Task | Final design NONO/ NOWC from Project Manager: Description for Neutral Section Detection and functioning | 04/09/2020 | 16/09/2020 | 04/09/2020 | 16/09/2020 | 0 | TK_Complete | -824745350 | 206 | -824745350_206
MML3RSTDES5940 | TT_Task | Final design NONO/ NOWC from Project Manager: Electrical Pure Principle scheme - Train | 25/04/2021 | 25/04/2021 | 12/03/2021 | 17/03/2021 | 0 | TK_Complete | -824745350 | 207 | -824745350_207
MML3RSTDES5950 | TT_Task | Final design NONO/ NOWC from Project Manager: Test Specification of Master Controller | 11/04/2020 | 21/04/2020 | 11/04/2020 | 21/04/2020 | 0 | TK_Complete | -824745350 | 177 | -824745350_177
MML3RSTDES5960 | TT_Task | Final design NONO/ NOWC from Project Manager: Technical specification and Drawings of PAPIS | 03/06/2021 | 03/06/2021 | 03/06/2021 | 03/06/2021 | 0 | TK_Complete | -824745350 | 128 | -824745350_128
MML3RSTDES5970 | TT_Task | Final design NONO/ NOWC from Project Manager: Test Specification of PAPIS system | 05/03/2021 | 20/03/2021 | 05/03/2021 | 20/03/2021 | 0 | TK_Complete | -824745350 | 128 | -824745350_128
MML3RSTDES5980 | TT_Task | Final design NONO/ NOWC from Project Manager: Solution Principal Scheme | 25/02/2021 | 17/03/2021 | 25/02/2021 | 17/03/2021 | 0 | TK_Complete | -824745350 | 209 | -824745350_209
MML3RSTDES5990 | TT_Task | Final design NONO/ NOWC from Project Manager: Test Specification - Gangway | 13/08/2020 | 07/09/2020 | 13/08/2020 | 07/09/2020 | 0 | TK_Complete | -824745350 | 237 | -824745350_237
MML3RSTDES6000 | TT_Task | Final design NONO/ NOWC from Project Manager: Type Test Specification - Load test of Floor panel | 08/09/2020 | 05/10/2020 | 08/09/2020 | 05/10/2020 | 0 | TK_Complete | -824745350 | 237 | -824745350_237
MML3RSTDES6010 | TT_Task | Final design NONO/ NOWC from Project Manager: Type Test Specification - Windscreen | 27/01/2021 | 05/02/2021 | 31/12/2020 | 20/01/2021 | 0 | TK_Complete | -824745350 | 211 | -824745350_211
MML3RSTDES6020 | TT_Task | Final design NONO/ NOWC from Project Manager: Type Test Specification - Windows | 27/01/2021 | 04/02/2021 | 31/12/2020 | 20/01/2021 | 0 | TK_Complete | -824745350 | 237 | -824745350_237
MML3RSTDES6030 | TT_Task | Final design NONO/ NOWC from Project Manager: Type Test Specification - Interior Components | 27/01/2021 | 05/02/2021 | 14/01/2021 | 20/01/2021 | 0 | TK_Complete | -824745350 | 237 | -824745350_237
MML3RSTDES6040 | TT_Task | Final design NONO/ NOWC from Project Manager: Type Test Specification - Gauging (Static + Kinematic) | 29/07/2020 | 14/08/2020 | 29/07/2020 | 14/08/2020 | 0 | TK_Complete | -824745350 | 213 | -824745350_213
MML3RSTDES6050 | TT_Task | Final design NONO/ NOWC from Project Manager: Type Test Specification - Straphangers Endurance | 18/05/2020 | 29/05/2020 | 18/05/2020 | 29/05/2020 | 0 | TK_Complete | -824745350 | 214 | -824745350_214
MML3RSTDES6060 | TT_Task | Final design NONO/ NOWC from Project Manager: Type Test Specification - Couplers | 09/02/2021 | 15/02/2021 | 09/02/2021 | 15/02/2021 | 0 | TK_Complete | -824745350 | 237 | -824745350_237
MML3RSTDES6070 | TT_Task | Final design NONO/ NOWC from Project Manager: Type Test Specification - Floor Fire Resistance | 14/10/2020 | 27/10/2020 | 14/10/2020 | 27/10/2020 | 0 | TK_Complete | -824745350 | 216 | -824745350_216
MML3RSTDES6080 | TT_Task | Final design NONO/ NOWC from Project Manager: Fire Engineering Report - Prediction | 25/04/2021 | 25/04/2021 | 12/04/2021 | 16/04/2021 | 0 | TK_Complete | -824745350 | 48 | -824745350_48
MML3RSTDES6090 | TT_Task | Final design NONO/ NOWC from Project Manager: Noise Report - Final Prediction | 10/02/2021 | 18/02/2021 | 10/02/2021 | 18/02/2021 | 0 | TK_Complete | -824745350 | 179 | -824745350_179
MML3RSTDES6100 | TT_Task | Final design NONO/ NOWC from Project Manager: Operation ; MaintenanceManuals Plan | 09/05/2020 | 11/05/2020 | 09/05/2020 | 11/05/2020 | 0 | TK_Complete | -824745350 | 57 | -824745350_57
MML3RSTDES6110 | TT_Task | Final design NONO/ NOWC from Project Manager: Training Plan | 20/11/2019 | 20/11/2019 | 20/11/2019 | 20/11/2019 | 0 | TK_Complete | -824745350 | 54 | -824745350_54
MML3RSTDES6120 | TT_Task | Final design NONO/ NOWC from Project Manager: Spare Management Plan | 12/11/2019 | 18/02/2020 | 05/02/2020 | 18/02/2020 | 0 | TK_Complete | -824745350 | 52 | -824745350_52
MML3RSTDES6130 | TT_Task | Final design NONO/ NOWC from Project Manager: Assistance of Maintenance Plan | 01/05/2020 | 09/05/2020 | 01/05/2020 | 09/05/2020 | 0 | TK_Complete | -824745350 | 57 | -824745350_57
MML3RSTDES6140 | TT_Task | Final design NONO/ NOWC from Project Manager: Comprehensive Maintenance Plan | 01/05/2020 | 09/05/2020 | 01/05/2020 | 10/05/2020 | 0 | TK_Complete | -824745350 | 57 | -824745350_57
MML3RSTDES6150 | TT_Task | Final design NONO/ NOWC from Project Manager: Spare Parts List | 09/07/2020 | 13/07/2020 | 09/07/2020 | 13/07/2020 | 0 | TK_Complete | -824745350 | 218 | -824745350_218
MML3RSTDES6160 | TT_Task | Final design NONO/ NOWC from Project Manager: Train Simulator ; CBT Specification | 28/05/2021 | 28/05/2021 | 28/05/2021 | 28/05/2021 | 0 | TK_Complete | -824745350 | 219 | -824745350_219
MML3RSTDES6170 | TT_Task | Final design NONO/ NOWC from Project Manager: Maintenance Demonstration plan | 07/05/2020 | 07/05/2020 | 07/05/2020 | 07/05/2020 | 0 | TK_Complete | -824745350 | 57 | -824745350_57
MML3RSTDES6180 | TT_Task | Final design NONO/ NOWC from Project Manager: Quantitative fault tree analysis | 15/04/2021 | 10/05/2021 | 15/04/2021 | 10/05/2021 | 0 | TK_Complete | -824745350 | 220 | -824745350_220
MML3RSTDES6190 | TT_Task | Final design NONO/ NOWC from Project Manager:Failure modes effects and criticality analysis (FMECA) | 25/04/2021 | 25/04/2021 | 15/04/2021 | 29/04/2021 | 0 | TK_Complete | -824745350 | 230 | -824745350_230
MML3RSTDES6200 | TT_Task | Final design NONO/ NOWC from Project Manager: Design Safety Study Report | 25/05/2021 | 25/05/2021 | 25/05/2021 | 25/05/2021 | 0 | TK_Complete | -824745350 | 55 | -824745350_55
MML3RSTDES6210 | TT_Task | Final design NONO/ NOWC from Project Manager: Hazard Log | 15/04/2021 | 10/05/2021 | 15/04/2021 | 10/05/2021 | 0 | TK_Complete | -824745350 | 58 | -824745350_58
MML3RSTDES6220 | TT_Task | Final design NONO/ NOWC from Project Manager: Safety Critical Item List | 19/02/2020 | 28/02/2020 | 19/02/2020 | 28/02/2020 | 0 | TK_Complete | -824745350 | 231 | -824745350_231
MML3RSTDES6230 | TT_Task | Final design NONO/ NOWC from Project Manager: Reliability Critical Item List | 25/04/2020 | 06/05/2020 | 25/04/2020 | 06/05/2020 | 0 | TK_Complete | -824745350 | 231 | -824745350_231
MML3RSTDES6240 | TT_Task | Final design NONO/ NOWC from Project Manager: RAM demonstration ; FRACAS Plan | 25/04/2020 | 06/05/2020 | 25/04/2020 | 06/05/2020 | 0 | TK_Complete | -824745350 | 46 | -824745350_46
MML3RSTDES6250 | TT_Task | Final design NONO/ NOWC from Project Manager: Application Safety Case | 16/02/2021 | 10/05/2021 | 16/02/2021 | 10/05/2021 | 0 | TK_Complete | -824745350 | 55 | -824745350_55
MML3RSTDES6252 | TT_Task | Final design NONO/ NOWC from Project Manager: Test Specification of Wayside Measurement ; Monitoring System | 29/01/2021 | 05/02/2021 | 29/01/2021 | 05/02/2021 | 0 | TK_Complete | -824745350 | 238 | -824745350_238
MML3RSTDES6254 | TT_Task | Final design NONO/ NOWC from Project Manager: Technical Specification of CMMS | 05/02/2021 | 05/02/2021 | 05/02/2021 | 05/02/2021 | 0 | TK_Complete | -824745350 | 223 | -824745350_223
MML3RSTDES6255 | TT_Task | Final design NONO/ NOWC from Project Manager: Test Specification of Combined Test Bed | 18/06/2021 | 18/06/2021 | 18/06/2021 | 18/06/2021 | 0 | TK_Complete | -824745350 | 237 | -824745350_237
MML3RSTVAL1000 | TT_Task | First Submission by Alstom: Functional Description Document of TCMS | 23/05/2020 | 23/05/2020 | 23/05/2020 | 23/05/2020 | 0 | TK_Complete | -824745350 | 95 | -824745350_95
MML3RSTVAL1010 | TT_Task | First Submission by Alstom: Technical Description of HMI | 20/03/2020 | 20/03/2020 | 20/03/2020 | 20/03/2020 | 0 | TK_Complete | -824745350 | 239 | -824745350_239
MML3RSTVAL1020 | TT_Task | First Submission by Alstom: Safety Validation Plan | 10/02/2021 | 10/02/2021 | 10/02/2021 | 10/02/2021 | 0 | TK_Complete | -824745350 | 7 | -824745350_7
MML3RSTVAL1030 | TT_Task | First Submission by Alstom: Static Gauge Type Test Procedure | 21/10/2020 | 21/10/2020 | 21/10/2020 | 21/10/2020 | 0 | TK_Complete | -824745350 | 240 | -824745350_240
MML3RSTVAL1040 | TT_Task | First Submission by Alstom: Car - Bogie Clearance Test Type Test Procedure | 16/09/2020 | 16/09/2020 | 16/09/2020 | 16/09/2020 | 0 | TK_Complete | -824745350 | 241 | -824745350_241
MML3RSTVAL1050 | TT_Task | First Submission by Alstom: Car - Car Clearance Test Type Test Procedure | 26/11/2020 | 26/11/2020 | 26/11/2020 | 26/11/2020 | 0 | TK_Complete | -824745350 | 241 | -824745350_241
MML3RSTVAL1060 | TT_Task | First Submission by Alstom: Static Sway Type Test Procedure | 20/11/2020 | 20/11/2020 | 20/11/2020 | 20/11/2020 | 0 | TK_Complete | -824745350 | 242 | -824745350_242
MML3RSTVAL1070 | TT_Task | First Submission by Alstom: Bogie Rotational Type Test Procedure | 11/09/2020 | 11/09/2020 | 11/09/2020 | 11/09/2020 | 0 | TK_Complete | -824745350 | 242 | -824745350_242
MML3RSTVAL1080 | TT_Task | First Submission by Alstom: Twist Test (Wheel Offloading) Type Test Procedure | 11/09/2020 | 11/09/2020 | 11/09/2020 | 11/09/2020 | 0 | TK_Complete | -824745350 | 242 | -824745350_242
MML3RSTVAL1090 | TT_Task | First Submission by Alstom: Car Weighing Type Test Procedure | 11/09/2020 | 11/09/2020 | 11/09/2020 | 11/09/2020 | 0 | TK_Complete | -824745350 | 241 | -824745350_241
MML3RSTVAL1100 | TT_Task | First Submission by Alstom: Watertightness Type Test Procedure | 16/09/2020 | 16/09/2020 | 16/09/2020 | 16/09/2020 | 0 | TK_Complete | -824745350 | 243 | -824745350_243
MML3RSTVAL1110 | TT_Task | First Submission by Alstom: Carbody Structural Type Test Procedure | 27/11/2020 | 27/11/2020 | 27/11/2020 | 27/11/2020 | 0 | TK_Complete | -824745350 | 241 | -824745350_241
MML3RSTVAL1120 | TT_Task | First Submission by Alstom: Climatic Chamber Type Test Procedure | 27/11/2020 | 27/11/2020 | 27/11/2020 | 27/11/2020 | 0 | TK_Complete | -824745350 | 244 | -824745350_244
MML3RSTVAL1130 | TT_Task | First Submission by Alstom: Lifting Ability Type Test Procedure | 11/09/2020 | 11/09/2020 | 11/09/2020 | 11/09/2020 | 0 | TK_Complete | -824745350 | 242 | -824745350_242
MML3RSTVAL1140 | TT_Task | First Submission by Alstom: Vehicle Earthing Type Test Procedure | 11/11/2020 | 11/11/2020 | 11/11/2020 | 11/11/2020 | 0 | TK_Complete | -824745350 | 245 | -824745350_245
MML3RSTVAL1150 | TT_Task | First Submission by Alstom: Battery Autonomy and Charging Type Test Procedure | 09/11/2020 | 09/11/2020 | 09/11/2020 | 09/11/2020 | 0 | TK_Complete | -824745350 | 185 | -824745350_185
MML3RSTVAL1160 | TT_Task | First Submission by Alstom: Doors System Functional Type Test Procedure | 09/11/2020 | 09/11/2020 | 09/11/2020 | 09/11/2020 | 0 | TK_Complete | -824745350 | 88 | -824745350_88
MML3RSTVAL1170 | TT_Task | First Submission by Alstom: Doors System Performance Test Procedure | 09/11/2020 | 09/11/2020 | 09/11/2020 | 09/11/2020 | 0 | TK_Complete | -824745350 | 88 | -824745350_88
MML3RSTVAL1180 | TT_Task | First Submission by Alstom: Event Recorder (EVR) Type Test Procedure | 12/11/2020 | 12/11/2020 | 12/11/2020 | 12/11/2020 | 0 | TK_Complete | -824745350 | 246 | -824745350_246
MML3RSTVAL1190 | TT_Task | First Submission by Alstom: Lighting Functional Type Test Procedure | 09/11/2020 | 09/11/2020 | 09/11/2020 | 09/11/2020 | 0 | TK_Complete | -824745350 | 247 | -824745350_247
MML3RSTVAL1200 | TT_Task | First Submission by Alstom: Lighting System Performance Type Test Procedure | 11/09/2020 | 11/09/2020 | 11/09/2020 | 11/09/2020 | 0 | TK_Complete | -824745350 | 247 | -824745350_247
MML3RSTVAL1210 | TT_Task | First Submission by Alstom: Emergency Detrainment Door Type Test Procedure | 11/09/2020 | 11/09/2020 | 11/09/2020 | 11/09/2020 | 0 | TK_Complete | -824745350 | 248 | -824745350_248
MML3RSTVAL1220 | TT_Task | First Submission by Alstom: Fire and Smoke (FSD) Test Procedure | 09/11/2020 | 09/11/2020 | 09/11/2020 | 09/11/2020 | 0 | TK_Complete | -824745350 | 249 | -824745350_249
MML3RSTVAL1230 | TT_Task | First Submission by Alstom: VAC Functional Type Test Procedure | 09/11/2020 | 09/11/2020 | 09/11/2020 | 09/11/2020 | 0 | TK_Complete | -824745350 | 250 | -824745350_250
MML3RSTVAL1240 | TT_Task | First Submission by Alstom: Pantograph Type Test Procedure | 12/11/2020 | 12/11/2020 | 12/11/2020 | 12/11/2020 | 0 | TK_Complete | -824745350 | 91 | -824745350_91
MML3RSTVAL1250 | TT_Task | First Submission by Alstom: TCMS Stati c Functional Test Procedure | 11/11/2020 | 11/11/2020 | 11/11/2020 | 11/11/2020 | 0 | TK_Complete | -824745350 | 251 | -824745350_251
MML3RSTVAL1260 | TT_Task | First Submission by Alstom: Electrical Energy Type Test (HVS, MVS) Procedure | 24/11/2020 | 24/11/2020 | 24/11/2020 | 24/11/2020 | 0 | TK_Complete | -824745350 | 252 | -824745350_252
MML3RSTVAL1270 | TT_Task | First Submission by Alstom: Driving Functional Test Procedure | 21/10/2020 | 21/10/2020 | 21/10/2020 | 21/10/2020 | 0 | TK_Complete | -824745350 | 242 | -824745350_242
MML3RSTVAL1280 | TT_Task | First Submission by Alstom: Air Production Type Test Procedure | 18/11/2020 | 18/11/2020 | 18/11/2020 | 18/11/2020 | 0 | TK_Complete | -824745350 | 253 | -824745350_253
MML3RSTVAL1290 | TT_Task | First Submission by Alstom: Brakes Type Test (Static) Procedure | 18/11/2020 | 18/11/2020 | 18/11/2020 | 18/11/2020 | 0 | TK_Complete | -824745350 | 254 | -824745350_254
MML3RSTVAL1300 | TT_Task | First Submission by Alstom: Traction Type Test (Static) Procedure | 19/11/2020 | 19/11/2020 | 19/11/2020 | 19/11/2020 | 0 | TK_Complete | -824745350 | 242 | -824745350_242
MML3RSTVAL1310 | TT_Task | First Submission by Alstom: Kinematic Envelope Type Test Procedure | 16/09/2020 | 16/09/2020 | 16/09/2020 | 16/09/2020 | 0 | TK_Complete | -824745350 | 242 | -824745350_242
MML3RSTVAL1320 | TT_Task | First Submission by Alstom: Noise Static Type Test Procedure | 26/11/2020 | 26/11/2020 | 26/11/2020 | 26/11/2020 | 0 | TK_Complete | -824745350 | 240 | -824745350_240
MML3RSTVAL1330 | TT_Task | First Submission by Alstom: Noise Dynamic Type Test Procedure | 26/11/2020 | 26/11/2020 | 26/11/2020 | 26/11/2020 | 0 | TK_Complete | -824745350 | 240 | -824745350_240
MML3RSTVAL1340 | TT_Task | First Submission by Alstom: PAPIS Static Type Test Procedure | 21/10/2020 | 27/10/2020 | 21/10/2020 | 21/10/2020 | 0 | TK_Complete | -824745350 | 250 | -824745350_250
MML3RSTVAL1350 | TT_Task | First Submission by Alstom: PAPIS Dynamic Type Test Procedure | 21/10/2020 | 26/10/2020 | 21/10/2020 | 21/10/2020 | 0 | TK_Complete | -824745350 | 250 | -824745350_250
MML3RSTVAL1360 | TT_Task | First Submission by Alstom: Ride Comfort and Stability Type Test Procedure | 27/11/2020 | 29/11/2020 | 27/11/2020 | 29/11/2020 | 0 | TK_Complete | -824745350 | 242 | -824745350_242
MML3RSTVAL1370 | TT_Task | First Submission by Alstom: TCMS Dynamic Functional Test Procedure | 21/10/2020 | 21/10/2020 | 21/10/2020 | 21/10/2020 | 0 | TK_Complete | -824745350 | 251 | -824745350_251
MML3RSTVAL1380 | TT_Task | First Submission by Alstom: Traction Brake Performance (Dynamic) Test Procedure | 18/11/2020 | 18/11/2020 | 18/11/2020 | 18/11/2020 | 0 | TK_Complete | -824745350 | 254 | -824745350_254
MML3RSTVAL1390 | TT_Task | First Submission by Alstom: Wheel Slide Type Test Procedure | 22/09/2020 | 22/09/2020 | 22/09/2020 | 22/09/2020 | 0 | TK_Complete | -824745350 | 242 | -824745350_242
MML3RSTVAL1400 | TT_Task | First Submission by Alstom: Parking Brake and Holding Brake Type Test Procedure | 11/11/2020 | 11/11/2020 | 11/11/2020 | 11/11/2020 | 0 | TK_Complete | -824745350 | 254 | -824745350_254
MML3RSTVAL1410 | TT_Task | First Submission by Alstom: Life cycle Cost Plan | 01/06/2022 | 16/06/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 255 | -824745350_255
MML3RSTVAL1420 | TT_Task | First Submission by Alstom: Training Manual for Train Operators | 01/06/2022 | 16/06/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 13 | -824745350_13
MML3RSTVAL1430 | TT_Task | First Submission by Alstom: Training Manual for Maintenance Staff | 01/06/2022 | 16/06/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 13 | -824745350_13
MML3RSTVAL1440 | TT_Task | First Submission by Alstom: Operation ; Maintenance Manuals | 16/06/2021 | 16/06/2021 | 16/06/2021 | 16/06/2021 | 0 | TK_Complete | -824745350 | 11 | -824745350_11
MML3RSTVAL1450 | TT_Task | First Submission by Alstom: Resistance to Motion Type Test Procedure | 27/11/2020 | 27/11/2020 | 27/11/2020 | 27/11/2020 | 0 | TK_Complete | -824745350 | 242 | -824745350_242
MML3RSTVAL1460 | TT_Task | First Submission by Alstom: Current Collection Type Test Procedure | 27/11/2020 | 27/11/2020 | 27/11/2020 | 27/11/2020 | 0 | TK_Complete | -824745350 | 250 | -824745350_250
MML3RSTVAL1470 | TT_Task | First Submission by Alstom: EMC Type Test Procedure | 01/12/2020 | 01/12/2020 | 01/12/2020 | 01/12/2020 | 0 | TK_Complete | -824745350 | 250 | -824745350_250
MML3RSTVAL1480 | TT_Task | First Submission by Alstom: Air Performance Type Test Procedure | 11/11/2020 | 11/11/2020 | 11/11/2020 | 11/11/2020 | 0 | TK_Complete | -824745350 | 253 | -824745350_253
MML3RSTVAL1490 | TT_Task | First Submission by Alstom: Rescue Test (Emergency Towing-Pushing) Test Procedure | 09/11/2020 | 09/11/2020 | 09/11/2020 | 09/11/2020 | 0 | TK_Complete | -824745350 | 256 | -824745350_256
MML3RSTVAL1500 | TT_Task | First Submission by Alstom: Energy Consumption Type Test Procedure | 27/11/2020 | 27/11/2020 | 27/11/2020 | 27/11/2020 | 0 | TK_Complete | -824745350 | 252 | -824745350_252
MML3RSTVAL1510 | TT_Task | NONO/ NOWC from Project Manager: Functional Description Document of TCMS | 11/05/2021 | 19/05/2021 | 11/05/2021 | 19/05/2021 | 0 | TK_Complete | -824745350 | 127 | -824745350_127
MML3RSTVAL1520 | TT_Task | NONO/ NOWC from Project Manager: Technical Description of HMI | 15/05/2021 | 20/05/2021 | 16/02/2021 | 23/02/2021 | 0 | TK_Complete | -824745350 | 52 | -824745350_52
MML3RSTVAL1530 | TT_Task | NONO/ NOWC from Project Manager: Safety Validation Plan | 15/05/2021 | 19/05/2021 | 24/03/2021 | 07/04/2021 | 0 | TK_Complete | -824745350 | 55 | -824745350_55
MML3RSTVAL1540 | TT_Task | NONO/ NOWC from Project Manager: Static Gauge Type Test Procedure | 29/03/2021 | 20/04/2021 | 29/03/2021 | 20/04/2021 | 0 | TK_Complete | -824745350 | 257 | -824745350_257
MML3RSTVAL1550 | TT_Task | NONO/ NOWC from Project Manager: Car - Bogie Clearance Test Type Test Procedure | 27/01/2021 | 27/01/2021 | 27/01/2021 | 27/01/2021 | 0 | TK_Complete | -824745350 | 258 | -824745350_258
MML3RSTVAL1560 | TT_Task | NONO/ NOWC from Project Manager: Car - Car Clearance Test Type Test Procedure | 27/01/2021 | 27/01/2021 | 27/01/2021 | 27/01/2021 | 0 | TK_Complete | -824745350 | 258 | -824745350_258
MML3RSTVAL1570 | TT_Task | NONO/ NOWC from Project Manager: Static Sway Type Test Procedure | 26/03/2021 | 07/04/2021 | 26/03/2021 | 07/04/2021 | 0 | TK_Complete | -824745350 | 236 | -824745350_236
MML3RSTVAL1580 | TT_Task | NONO/ NOWC from Project Manager: Bogie Rotational Type Test Procedure | 16/12/2020 | 23/12/2020 | 16/12/2020 | 23/12/2020 | 0 | TK_Complete | -824745350 | 236 | -824745350_236
MML3RSTVAL1590 | TT_Task | NONO/ NOWC from Project Manager: Twist Test (Wheel Offloading) Type Test Procedure | 19/02/2021 | 22/02/2021 | 15/01/2021 | 20/01/2021 | 0 | TK_Complete | -824745350 | 236 | -824745350_236
MML3RSTVAL1600 | TT_Task | NONO/ NOWC from Project Manager: Car Weighing Type Test Procedure | 27/01/2021 | 27/01/2021 | 27/01/2021 | 27/01/2021 | 0 | TK_Complete | -824745350 | 258 | -824745350_258
MML3RSTVAL1610 | TT_Task | NONO/ NOWC from Project Manager: Watertightness Type Test Procedure | 15/03/2021 | 17/03/2021 | 15/03/2021 | 17/03/2021 | 0 | TK_Complete | -824745350 | 243 | -824745350_243
MML3RSTVAL1620 | TT_Task | NONO/ NOWC from Project Manager: Carbody Structural Type Test Procedure | 15/05/2021 | 19/05/2021 | 12/04/2021 | 21/04/2021 | 0 | TK_Complete | -824745350 | 258 | -824745350_258
MML3RSTVAL1630 | TT_Task | NONO/ NOWC from Project Manager: Climatic Chamber Type Test Procedure | 02/07/2021 | 22/07/2021 | 02/07/2021 | 22/07/2021 | 0 | TK_Complete | -824745350 | 244 | -824745350_244
MML3RSTVAL1640 | TT_Task | NONO/ NOWC from Project Manager: Lifting Ability Type Test Procedure | 28/01/2021 | 17/03/2021 | 28/01/2021 | 17/03/2021 | 0 | TK_Complete | -824745350 | 259 | -824745350_259
MML3RSTVAL1650 | TT_Task | NONO/ NOWC from Project Manager: Vehicle Earthing Type Test Procedure | 15/05/2021 | 19/05/2021 | 10/03/2021 | 09/04/2021 | 0 | TK_Complete | -824745350 | 245 | -824745350_245
MML3RSTVAL1660 | TT_Task | NONO/ NOWC from Project Manager: Battery Autonomy and Charging Type Test Procedure | 07/04/2021 | 04/05/2021 | 07/04/2021 | 04/05/2021 | 0 | TK_Complete | -824745350 | 185 | -824745350_185
MML3RSTVAL1670 | TT_Task | NONO/ NOWC from Project Manager: Doors System Functional Type Test Procedure | 09/03/2021 | 31/03/2021 | 09/03/2021 | 31/03/2021 | 0 | TK_Complete | -824745350 | 238 | -824745350_238
MML3RSTVAL1680 | TT_Task | NONO/ NOWC from Project Manager: Doors System Performance Test Procedure | 23/03/2021 | 31/03/2021 | 23/03/2021 | 31/03/2021 | 0 | TK_Complete | -824745350 | 238 | -824745350_238
MML3RSTVAL1690 | TT_Task | NONO/ NOWC from Project Manager: Event Recorder (EVR) Type Test Procedure | 23/03/2021 | 06/05/2021 | 23/03/2021 | 06/05/2021 | 0 | TK_Complete | -824745350 | 246 | -824745350_246
MML3RSTVAL1700 | TT_Task | NONO/ NOWC from Project Manager: Lighting Functional Type Test Procedure | 20/01/2021 | 31/03/2021 | 20/01/2021 | 31/03/2021 | 0 | TK_Complete | -824745350 | 260 | -824745350_260
MML3RSTVAL1710 | TT_Task | NONO/ NOWC from Project Manager: Lighting System Performance Type Test Procedure | 30/04/2021 | 07/05/2021 | 30/04/2021 | 07/05/2021 | 0 | TK_Complete | -824745350 | 260 | -824745350_260
MML3RSTVAL1720 | TT_Task | NONO/ NOWC from Project Manager: Emergency Detrainment Door Type Test Procedure | 27/03/2021 | 09/04/2021 | 27/03/2021 | 09/04/2021 | 0 | TK_Complete | -824745350 | 248 | -824745350_248
MML3RSTVAL1730 | TT_Task | NONO/ NOWC from Project Manager: Fire and Smoke (FSD) Test Procedure | 09/04/2021 | 16/04/2021 | 09/04/2021 | 16/04/2021 | 0 | TK_Complete | -824745350 | 249 | -824745350_249
MML3RSTVAL1740 | TT_Task | NONO/ NOWC from Project Manager: VAC Functional Type Test Procedure | 15/05/2021 | 20/05/2021 | 10/03/2021 | 20/03/2021 | 0 | TK_Complete | -824745350 | 259 | -824745350_259
MML3RSTVAL1750 | TT_Task | NONO/ NOWC from Project Manager: Pantograph Type Test Procedure | 19/02/2021 | 15/04/2021 | 19/02/2021 | 15/04/2021 | 0 | TK_Complete | -824745350 | 261 | -824745350_261
MML3RSTVAL1760 | TT_Task | NONO/ NOWC from Project Manager: TCMS Static Functional Test Procedure | 01/06/2021 | 03/06/2021 | 01/06/2021 | 03/06/2021 | 0 | TK_Complete | -824745350 | 259 | -824745350_259
MML3RSTVAL1770 | TT_Task | NONO/ NOWC from Project Manager: Electrical Energy Type Test (HVS, MVS) Procedure | 06/05/2021 | 17/05/2021 | 06/05/2021 | 17/05/2021 | 0 | TK_Complete | -824745350 | 260 | -824745350_260
MML3RSTVAL1780 | TT_Task | NONO/ NOWC from Project Manager: Driving Functional Test Procedure | 11/05/2021 | 18/05/2021 | 11/05/2021 | 18/05/2021 | 0 | TK_Complete | -824745350 | 259 | -824745350_259
MML3RSTVAL1790 | TT_Task | NONO/ NOWC from Project Manager: Air Production Type Test Procedure | 03/03/2021 | 25/03/2021 | 03/03/2021 | 25/03/2021 | 0 | TK_Complete | -824745350 | 259 | -824745350_259
MML3RSTVAL1800 | TT_Task | NONO/ NOWC from Project Manager: Brakes Type Test (Static) Procedure | 24/03/2021 | 15/04/2021 | 24/03/2021 | 15/04/2021 | 0 | TK_Complete | -824745350 | 262 | -824745350_262
MML3RSTVAL1810 | TT_Task | NONO/ NOWC from Project Manager: Traction Type Test (Static) Procedure | 25/02/2021 | 12/03/2021 | 25/02/2021 | 12/03/2021 | 0 | TK_Complete | -824745350 | 236 | -824745350_236
MML3RSTVAL1820 | TT_Task | NONO/ NOWC from Project Manager: Kinematic Envelope Type Test Procedure | 30/04/2021 | 05/05/2021 | 30/04/2021 | 05/05/2021 | 0 | TK_Complete | -824745350 | 236 | -824745350_236
MML3RSTVAL1830 | TT_Task | NONO/ NOWC from Project Manager: Noise Static Type Test Procedure | 07/04/2021 | 04/05/2021 | 07/04/2021 | 04/05/2021 | 0 | TK_Complete | -824745350 | 257 | -824745350_257
MML3RSTVAL1840 | TT_Task | NONO/ NOWC from Project Manager: Noise Dynamic Type Test Procedure | 06/04/2021 | 10/05/2021 | 06/04/2021 | 10/05/2021 | 0 | TK_Complete | -824745350 | 257 | -824745350_257
MML3RSTVAL1850 | TT_Task | NONO/ NOWC from Project Manager: PAPIS Static Type Test Procedure | 15/02/2021 | 08/06/2021 | 15/02/2021 | 08/06/2021 | 0 | TK_Complete | -824745350 | 259 | -824745350_259
MML3RSTVAL1860 | TT_Task | NONO/ NOWC from Project Manager: PAPIS Dynamic Type Test Procedure | 15/02/2021 | 18/06/2021 | 15/02/2021 | 18/06/2021 | 0 | TK_Complete | -824745350 | 259 | -824745350_259
MML3RSTVAL1870 | TT_Task | NONO/ NOWC from Project Manager: Ride Comfort and Stability Type Test Procedure | 26/03/2021 | 05/04/2021 | 26/03/2021 | 05/04/2021 | 0 | TK_Complete | -824745350 | 236 | -824745350_236
MML3RSTVAL1880 | TT_Task | NONO/ NOWC from Project Manager: TCMS Dynamic Functional Test Procedure | 20/03/2021 | 04/06/2021 | 20/03/2021 | 04/06/2021 | 0 | TK_Complete | -824745350 | 259 | -824745350_259
MML3RSTVAL1890 | TT_Task | NONO/ NOWC from Project Manager: Traction Brake Performance (Dynamic) Test Procedure | 15/03/2021 | 31/03/2021 | 15/03/2021 | 31/03/2021 | 0 | TK_Complete | -824745350 | 262 | -824745350_262
MML3RSTVAL1900 | TT_Task | NONO/ NOWC from Project Manager: Wheel Slide Type Test Procedure | 19/02/2021 | 23/02/2021 | 15/01/2021 | 20/01/2021 | 0 | TK_Complete | -824745350 | 236 | -824745350_236
MML3RSTVAL1910 | TT_Task | NONO/ NOWC from Project Manager: Parking Brake and Holding Brake Type Test Procedure | 23/01/2021 | 25/03/2021 | 23/01/2021 | 25/03/2021 | 0 | TK_Complete | -824745350 | 262 | -824745350_262
MML3RSTVAL1920 | TT_Task | NONO/ NOWC from Project Manager: Life cycle Cost Plan | 17/06/2022 | 26/06/2022 | nan | nan | 520 | TK_NotStart | -824745350 | 52 | -824745350_52
MML3RSTVAL1930 | TT_Task | NONO/ NOWC from Project Manager: Training Manual for Train Operators | 17/06/2022 | 26/06/2022 | nan | nan | 520 | TK_NotStart | -824745350 | 54 | -824745350_54
MML3RSTVAL1940 | TT_Task | NONO/ NOWC from Project Manager: Training Manual for Maintenance Staff | 17/06/2022 | 26/06/2022 | nan | nan | 520 | TK_NotStart | -824745350 | 56 | -824745350_56
MML3RSTVAL1950 | TT_Task | NONO/ NOWC from Project Manager: Operation ; Maintenance Manuals | 01/06/2022 | 10/06/2022 | nan | nan | 648 | TK_NotStart | -824745350 | 56 | -824745350_56
MML3RSTVAL1960 | TT_Task | NONO/ NOWC from Project Manager: Resistance to Motion Type Test Procedure | 28/05/2021 | 03/06/2021 | 28/05/2021 | 03/06/2021 | 0 | TK_Complete | -824745350 | 236 | -824745350_236
MML3RSTVAL1970 | TT_Task | NONO/ NOWC from Project Manager: Current Collection Type Test Procedure | 20/05/2021 | 28/05/2021 | 20/05/2021 | 28/05/2021 | 0 | TK_Complete | -824745350 | 259 | -824745350_259
MML3RSTVAL1980 | TT_Task | NONO/ NOWC from Project Manager: EMC Type Test Procedure | 23/03/2021 | 22/04/2021 | 23/03/2021 | 22/04/2021 | 0 | TK_Complete | -824745350 | 259 | -824745350_259
MML3RSTVAL1990 | TT_Task | NONO/ NOWC from Project Manager: Air Performance Type Test Procedure | 19/02/2021 | 25/02/2021 | 19/02/2021 | 25/02/2021 | 0 | TK_Complete | -824745350 | 259 | -824745350_259
MML3RSTVAL2000 | TT_Task | NONO/ NOWC from Project Manager: Rescue Test (Emergency Towing-Pushing) Test Procedure | 19/02/2021 | 28/02/2021 | 12/01/2021 | 20/01/2021 | 0 | TK_Complete | -824745350 | 256 | -824745350_256
MML3RSTVAL2010 | TT_Task | NONO/ NOWC from Project Manager: Energy Consumption Type Test Procedure | 25/12/2021 | 29/12/2021 | 05/07/2021 | 22/07/2021 | 0 | TK_Complete | -824745350 | 260 | -824745350_260
MML3RSTPRO2030 | TT_Task | PROC Submission by Alstom for Supplier: VAC | 28/11/2018 | 18/09/2019 | 28/11/2018 | 18/09/2019 | 0 | TK_Complete | -824745350 | 263 | -824745350_263
MML3RSTPRO2040 | TT_Task | PROC NONO/ NOWC from Project Manager for Supplier: VAC | 18/02/2019 | 24/09/2019 | 18/02/2019 | 24/09/2019 | 0 | TK_Complete | -824745350 | 141 | -824745350_141
MML3RSTPRO2050 | TT_Task | PROC Submission by Alstom for Supplier: Brakes | 14/11/2018 | 18/06/2019 | 27/11/2018 | 02/07/2019 | 0 | TK_Complete | -824745350 | 264 | -824745350_264
MML3RSTPRO2060 | TT_Task | PROC NONO/ NOWC from Project Manager for Supplier: Brakes | 20/05/2019 | 08/10/2019 | 18/02/2019 | 09/07/2019 | 0 | TK_Complete | -824745350 | 139 | -824745350_139
MML3RSTPRO2070 | TT_Task | PROC Submission by Alstom for Supplier: Battery with Battery Box | 14/10/2019 | 12/11/2019 | 14/10/2019 | 07/11/2019 | 0 | TK_Complete | -824745350 | 265 | -824745350_265
MML3RSTPRO2080 | TT_Task | PROC NONO/ NOWC from Project Manager for Supplier: Battery with Battery Box | 15/10/2019 | 28/10/2019 | 15/10/2019 | 11/11/2019 | 0 | TK_Complete | -824745350 | 265 | -824745350_265
MML3RSTPRO2090 | TT_Task | PROC Submission by Alstom for Supplier: Passenger Doors | 14/11/2018 | 13/06/2019 | 27/11/2018 | 27/06/2019 | 0 | TK_Complete | -824745350 | 266 | -824745350_266
MML3RSTPRO2100 | TT_Task | PROC NONO/ NOWC from Project Manager for Supplier: Passenger Doors | 17/05/2019 | 06/10/2019 | 18/02/2019 | 10/07/2019 | 0 | TK_Complete | -824745350 | 267 | -824745350_267
MML3RSTPRO2110 | TT_Task | PROC Submission by Alstom for Supplier: Transformer | 10/11/2018 | 18/06/2019 | 23/11/2018 | 02/07/2019 | 0 | TK_Complete | -824745350 | 268 | -824745350_268
MML3RSTPRO2120 | TT_Task | PROC NONO/ NOWC from Project Manager for Supplier: Transformer | 11/04/2019 | 30/08/2019 | 18/02/2019 | 09/07/2019 | 0 | TK_Complete | -824745350 | 81 | -824745350_81
MML3RSTPRO2130 | TT_Task | PROC Submission by Alstom for Supplier: PAPIS | 09/04/2019 | 08/05/2019 | 09/04/2019 | 16/03/2021 | 0 | TK_Complete | -824745350 | 263 | -824745350_263
MML3RSTPRO2140 | TT_Task | PROC NONO/ NOWC from Project Manager for Supplier: PAPIS | 23/04/2019 | 06/05/2019 | 23/04/2019 | 22/03/2021 | 0 | TK_Complete | -824745350 | 269 | -824745350_269
MML3RSTPRO2150 | TT_Task | PROC Submission by Alstom for Supplier: Vacuum circuit breaker | 27/11/2018 | 18/09/2019 | 27/11/2018 | 18/09/2019 | 0 | TK_Complete | -824745350 | 270 | -824745350_270
MML3RSTPRO2160 | TT_Task | PROC NONO/ NOWC from Project Manager for Supplier: Vacuum circuit breaker | 18/02/2019 | 23/09/2019 | 18/02/2019 | 23/09/2019 | 0 | TK_Complete | -824745350 | 183 | -824745350_183
MML3RSTPRO2170 | TT_Task | PROC Submission by Alstom for Supplier: Gear Box and Coupling | 10/11/2018 | 26/07/2019 | 23/11/2018 | 09/08/2019 | 0 | TK_Complete | -824745350 | 271 | -824745350_271
MML3RSTPRO2180 | TT_Task | PROC NONO/ NOWC from Project Manager for Supplier: Gear Box and Coupling | 27/06/2019 | 26/12/2019 | 18/02/2019 | 20/08/2019 | 0 | TK_Complete | -824745350 | 271 | -824745350_271
MML3RSTPRO2190 | TT_Task | PROC Submission by Alstom for Supplier: Wheels | 13/07/2019 | 09/08/2019 | 13/07/2019 | 09/08/2019 | 0 | TK_Complete | -824745350 | 272 | -824745350_272
MML3RSTPRO2200 | TT_Task | PROC NONO/ NOWC from Project Manager for Supplier: Wheels | 25/07/2019 | 25/08/2019 | 25/07/2019 | 25/08/2019 | 0 | TK_Complete | -824745350 | 273 | -824745350_273
MML3RSTPRO2210 | TT_Task | PROC Submission by Alstom for Supplier: Automatic Coupler ; Semi-Permanent Coupler | 27/11/2018 | 18/07/2019 | 27/11/2018 | 18/07/2019 | 0 | TK_Complete | -824745350 | 274 | -824745350_274
MML3RSTPRO2220 | TT_Task | PROC NONO/ NOWC from Project Manager for Supplier: Automatic Coupler ; Semi-Permanent Coupler | 18/02/2019 | 25/07/2019 | 18/02/2019 | 25/07/2019 | 0 | TK_Complete | -824745350 | 275 | -824745350_275
MML3RSTPRO2230 | TT_Task | PROC Submission by Alstom for Supplier: Gangways | 27/11/2018 | 19/08/2019 | 27/11/2018 | 09/08/2019 | 0 | TK_Complete | -824745350 | 276 | -824745350_276
MML3RSTPRO2240 | TT_Task | PROC NONO/ NOWC from Project Manager for Supplier: Gangways | 18/02/2019 | 14/08/2019 | 18/02/2019 | 14/08/2019 | 0 | TK_Complete | -824745350 | 269 | -824745350_269
MML3RSTPRO2250 | TT_Task | PROC Submission by Alstom for Supplier: High Voltage System including Pantograph | 27/11/2018 | 10/12/2018 | 27/11/2018 | 10/12/2018 | 0 | TK_Complete | -824745350 | 277 | -824745350_277
MML3RSTPRO2260 | TT_Task | PROC NONO/ NOWC from Project Manager for Supplier: High Voltage System including Pantograph | 18/02/2019 | 13/08/2019 | 18/02/2019 | 13/08/2019 | 0 | TK_Complete | -824745350 | 277 | -824745350_277
MML3RSTPRO2270 | TT_Task | PROC Submission by Alstom for Supplier: Cab Mask | 21/02/2020 | 05/06/2020 | 21/02/2020 | 05/06/2020 | 0 | TK_Complete | -824745350 | 278 | -824745350_278
MML3RSTPRO2280 | TT_Task | PROC NONO/ NOWC from Project Manager for Supplier: Cab Mask | 03/03/2020 | 06/06/2020 | 03/03/2020 | 06/06/2020 | 0 | TK_Complete | -824745350 | 279 | -824745350_279
MML3RSTPRO2290 | TT_Task | PROC Submission by Alstom for Supplier: Head Light, Tail Light and Flasher Light | 25/01/2020 | 23/02/2020 | 24/08/2020 | 24/08/2020 | 0 | TK_Complete | -824745350 | 280 | -824745350_280
MML3RSTPRO2300 | TT_Task | PROC NONO/ NOWC from Project Manager for Supplier: Head Light, Tail Light and Flasher Light | 25/05/2021 | 25/05/2021 | 12/05/2021 | 12/05/2021 | 0 | TK_Complete | -824745350 | 280 | -824745350_280
MML3RSTPRO2310 | TT_Task | PROC Submission by Alstom for Supplier: 25KV cable with HV cable ; bushing | 09/09/2019 | 12/12/2019 | 09/09/2019 | 11/12/2019 | 0 | TK_Complete | -824745350 | 281 | -824745350_281
MML3RSTPRO2320 | TT_Task | PROC NONO/ NOWC from Project Manager for Supplier: 25KV cable with HV cable ; bushing | 24/09/2019 | 12/12/2019 | 24/09/2019 | 12/12/2019 | 0 | TK_Complete | -824745350 | 281 | -824745350_281
MML3RSTPRO2330 | TT_Task | PROC Submission by Alstom for Supplier: Master Controller | 09/07/2019 | 31/08/2019 | 26/07/2019 | 17/09/2019 | 0 | TK_Complete | -824745350 | 263 | -824745350_263
MML3RSTPRO2340 | TT_Task | PROC NONO/ NOWC from Project Manager for Supplier: Master Controller | 18/09/2019 | 24/09/2019 | 18/09/2019 | 24/09/2019 | 0 | TK_Complete | -824745350 | 81 | -824745350_81
MML3RSTPRO2350 | TT_Task | PROC Submission by Alstom for Supplier: Passenger Seat | 19/06/2020 | 19/06/2020 | 19/06/2020 | 19/06/2020 | 0 | TK_Complete | -824745350 | 282 | -824745350_282
MML3RSTPRO2360 | TT_Task | PROC NONO/ NOWC from Project Manager for Supplier: Passenger Seat | 24/06/2020 | 24/06/2020 | 24/06/2020 | 24/06/2020 | 0 | TK_Complete | -824745350 | 283 | -824745350_283
MML3RSTPRO2370 | TT_Task | PROC Submission by Alstom for Supplier: Car Interiors | 13/04/2020 | 26/06/2020 | 13/04/2020 | 26/06/2020 | 0 | TK_Complete | -824745350 | 284 | -824745350_284
MML3RSTPRO2380 | TT_Task | PROC NONO/ NOWC from Project Manager for Supplier: Car Interiors | 21/04/2020 | 29/06/2020 | 21/04/2020 | 29/06/2020 | 0 | TK_Complete | -824745350 | 285 | -824745350_285
MML3RSTPRO2390 | TT_Task | PROC Submission by Alstom for Supplier:Windows, Glasses and Windscreens | 09/08/2019 | 05/09/2019 | 09/08/2019 | 13/09/2019 | 0 | TK_Complete | -824745350 | 286 | -824745350_286
MML3RSTPRO2400 | TT_Task | PROC NONO/ NOWC from Project Manager for Supplier: Windows, Glasses and Windscreens | 14/09/2019 | 27/09/2019 | 14/09/2019 | 27/09/2019 | 0 | TK_Complete | -824745350 | 286 | -824745350_286
MML3RSTPRO2410 | TT_Task | PROC Submission by Alstom for Supplier: Cab Control Devices(Windscreen Wiper and Horn) | 22/06/2020 | 22/06/2020 | 22/06/2020 | 22/06/2020 | 0 | TK_Complete | -824745350 | 287 | -824745350_287
MML3RSTPRO2420 | TT_Task | PROC NONO/ NOWC from Project Manager for Supplier: Cab Control Devices(Windscreen Wiper and Horn) | 29/06/2020 | 29/06/2020 | 29/06/2020 | 29/06/2020 | 0 | TK_Complete | -824745350 | 287 | -824745350_287
MML3RSTPRO2430 | TT_Task | PROC Submission by Alstom for Supplier: Emergency Evacuation Ramp | 31/10/2019 | 20/11/2019 | 31/10/2019 | 20/11/2019 | 0 | TK_Complete | -824745350 | 288 | -824745350_288
MML3RSTPRO2440 | TT_Task | PROC NONO/ NOWC from Project Manager for Supplier: Emergency Evacuation Ramp | 05/11/2019 | 21/11/2019 | 05/11/2019 | 21/11/2019 | 0 | TK_Complete | -824745350 | 288 | -824745350_288
MML3RSTPRO2450 | TT_Task | PROC Submission by Alstom for Supplier: Primary Suspension(Primary Spring) | 28/08/2019 | 17/10/2019 | 28/08/2019 | 17/10/2019 | 0 | TK_Complete | -824745350 | 289 | -824745350_289
MML3RSTPRO2460 | TT_Task | PROC NONO/ NOWC from Project Manager for Supplier: Primary Suspension(Primary Spring) | 07/09/2019 | 30/10/2019 | 07/09/2019 | 30/10/2019 | 0 | TK_Complete | -824745350 | 290 | -824745350_290
MML3RSTPRO2470 | TT_Task | PROC Submission by Alstom for Supplier: Wheel Flange Lubricators | 04/10/2019 | 11/11/2019 | 04/10/2019 | 11/11/2019 | 0 | TK_Complete | -824745350 | 291 | -824745350_291
MML3RSTPRO2480 | TT_Task | PROC NONO/ NOWC from Project Manager for Supplier: Wheel Flange Lubricators | 10/10/2019 | 22/11/2019 | 10/10/2019 | 22/11/2019 | 0 | TK_Complete | -824745350 | 291 | -824745350_291
MML3RSTPRO2490 | TT_Task | PROC Submission by Alstom for Supplier: Obstacle Detector ; Deflector | 25/01/2020 | 23/02/2020 | 07/10/2019 | 07/10/2020 | 0 | TK_Complete | -824745350 | 292 | -824745350_292
MML3RSTPRO2500 | TT_Task | PROC NONO/ NOWC from Project Manager for Supplier: Obstacle Detector ; Deflector | 07/11/2019 | 14/10/2020 | 07/11/2019 | 14/10/2020 | 0 | TK_Complete | -824745350 | 292 | -824745350_292
MML3RSTPRO2510 | TT_Task | PROC Submission by Alstom for Supplier: Derailment Detector | 25/01/2020 | 07/10/2020 | 25/01/2020 | 07/10/2020 | 0 | TK_Complete | -824745350 | 293 | -824745350_293
MML3RSTPRO2520 | TT_Task | PROC NONO/ NOWC from Project Manager for Supplier: Derailment Detector | 12/02/2020 | 14/10/2020 | 12/02/2020 | 14/10/2020 | 0 | TK_Complete | -824745350 | 293 | -824745350_293
MML3RSTPRO2530 | TT_Task | PROC Submission by Alstom for Supplier: Secondary suspension (Air spring) | 28/08/2019 | 17/10/2019 | 28/08/2019 | 17/10/2019 | 0 | TK_Complete | -824745350 | 289 | -824745350_289
MML3RSTPRO2540 | TT_Task | PROC NONO/ NOWC from Project Manager for Supplier: Secondary suspension (Air spring) | 07/09/2019 | 30/10/2019 | 07/09/2019 | 30/10/2019 | 0 | TK_Complete | -824745350 | 290 | -824745350_290
MML3RSTPRO2550 | TT_Task | PROC Submission by Alstom for Supplier: Dampers(Vertical ; horizontal) | 16/10/2019 | 08/11/2019 | 16/10/2019 | 08/11/2019 | 0 | TK_Complete | -824745350 | 294 | -824745350_294
MML3RSTPRO2560 | TT_Task | PROC NONO/ NOWC from Project Manager for Supplier: Dampers(Vertical ; horizontal) | 06/11/2019 | 23/11/2019 | 06/11/2019 | 23/11/2019 | 0 | TK_Complete | -824745350 | 294 | -824745350_294
MML3RSTPRO2570 | TT_Task | PROC Submission by Alstom for Supplier: Axles and Axle roller Bearings | 09/08/2019 | 29/08/2019 | 09/08/2019 | 29/08/2019 | 0 | TK_Complete | -824745350 | 272 | -824745350_272
MML3RSTPRO2580 | TT_Task | PROC NONO/ NOWC from Project Manager for Supplier: Axles and Axle roller Bearings | 20/08/2019 | 03/09/2019 | 20/08/2019 | 03/09/2019 | 0 | TK_Complete | -824745350 | 295 | -824745350_295
MML3RSTPRO2590 | TT_Task | PROC Submission by Alstom for Supplier: Car Body Components | 11/11/2019 | 06/05/2020 | 11/11/2019 | 06/05/2020 | 0 | TK_Complete | -824745350 | 284 | -824745350_284
MML3RSTPRO2600 | TT_Task | PROC NONO/ NOWC from Project Manager for Supplier: Car Body Components | 22/11/2019 | 07/05/2020 | 22/11/2019 | 07/05/2020 | 0 | TK_Complete | -824745350 | 285 | -824745350_285
MML3RSTPRO2610 | TT_Task | PROC Submission by Alstom for Supplier: Detrainment Door | 31/10/2019 | 20/11/2019 | 31/10/2019 | 20/11/2019 | 0 | TK_Complete | -824745350 | 266 | -824745350_266
MML3RSTPRO2620 | TT_Task | PROC NONO/ NOWC from Project Manager for Supplier: Detrainment Door | 05/11/2019 | 21/11/2019 | 05/11/2019 | 21/11/2019 | 0 | TK_Complete | -824745350 | 267 | -824745350_267
MML3RSTPRO2810 | TT_Task | PROC Submission by Alstom for Supplier: Bogie Frame | 29/08/2019 | 08/11/2019 | 29/08/2019 | 08/11/2019 | 0 | TK_Complete | -824745350 | 263 | -824745350_263
MML3RSTPRO2820 | TT_Task | PROC NONO/ NOWC from Project Manager for Supplier: Bogie Frame | 06/11/2019 | 23/11/2019 | 06/11/2019 | 23/11/2019 | 0 | TK_Complete | -824745350 | 296 | -824745350_296
MML3RSTPRO2830 | TT_Task | PROC Submission by Alstom for Supplier: Way side Monitoring | 30/11/2019 | 30/11/2019 | 25/08/2020 | 25/08/2020 | 0 | TK_Complete | -824745350 | 263 | -824745350_263
MML3RSTPRO2840 | TT_Task | PROC NONO/ NOWC from Project Manager for Supplier: Way side Mointoring | 04/09/2020 | 04/09/2020 | 04/09/2020 | 04/09/2020 | 0 | TK_Complete | -824745350 | 269 | -824745350_269
MML3RSTPRO2850 | TT_Task | PROC Submission by Alstom for Supplier: Train Driving Simulator | 05/03/2020 | 17/07/2020 | 05/03/2020 | 17/07/2020 | 0 | TK_Complete | -824745350 | 297 | -824745350_297
MML3RSTPRO2860 | TT_Task | PROC NONO/ NOWC from Project Manager for Supplier: Train Driving Simulator | 16/03/2020 | 22/07/2020 | 16/03/2020 | 22/07/2020 | 0 | TK_Complete | -824745350 | 297 | -824745350_297
MML3RSTPRO2870 | TT_Task | PROC Submission by Alstom for Supplier: Bogie and Related Material | 08/11/2019 | 11/11/2019 | 08/11/2019 | 11/11/2019 | 0 | TK_Complete | -824745350 | 263 | -824745350_263
MML3RSTPRO2880 | TT_Task | PROC NONO/ NOWC from Project Manager for Supplier: Bogie and Related Material | 09/11/2019 | 23/11/2019 | 09/11/2019 | 23/11/2019 | 0 | TK_Complete | -824745350 | 296 | -824745350_296
MML3RSTPRO2890 | TT_Task | PROC Submission by Alstom for Supplier: Car Flooring | 30/07/2019 | 30/07/2019 | 30/07/2019 | 30/07/2019 | 0 | TK_Complete | -824745350 | 284 | -824745350_284
MML3RSTPRO2900 | TT_Task | PROC NONO/ NOWC from Project Manager for Supplier: Car Flooring | 31/07/2019 | 31/07/2019 | 31/07/2019 | 31/07/2019 | 0 | TK_Complete | -824745350 | 285 | -824745350_285
MML3RSTPRO2930 | TT_Task | PROC Submission by Alstom for Supplier: Cables and Glands | 13/08/2019 | 13/08/2019 | 13/08/2019 | 13/08/2019 | 0 | TK_Complete | -824745350 | 298 | -824745350_298
MML3RSTPRO2940 | TT_Task | PROC NONO/ NOWC from Project Manager for Supplier: Cables and Glands | 19/09/2019 | 19/09/2019 | 19/09/2019 | 19/09/2019 | 0 | TK_Complete | -824745350 | 298 | -824745350_298
MML3RSTPRO2950 | TT_Task | PROC Submission by Alstom for Supplier:TCMS | 19/08/2019 | 19/08/2019 | 19/08/2019 | 19/08/2019 | 0 | TK_Complete | -824745350 | 263 | -824745350_263
MML3RSTPRO2960 | TT_Task | PROC NONO/ NOWC from Project Manager for Supplier: TCMS | 20/08/2019 | 20/08/2019 | 20/08/2019 | 20/08/2019 | 0 | TK_Complete | -824745350 | 269 | -824745350_269
MML3RSTPRO2990 | TT_Task | PROC Submission by Alstom for Supplier: Grab Poles, Hand Rails, Grab handles and draught screens. | 10/07/2019 | 08/08/2019 | 10/07/2019 | 08/08/2019 | 0 | TK_Complete | -824745350 | 299 | -824745350_299
MML3RSTPRO3000 | TT_Task | PROC NONO/ NOWC from Project Manager for Supplier: Grab Poles, Hand Rails, Grab handles and draught screens. | 14/08/2019 | 27/09/2019 | 14/08/2019 | 27/09/2019 | 0 | TK_Complete | -824745350 | 299 | -824745350_299
MML3RSTPRO3010 | TT_Task | PROC Submission by Alstom for Supplier: Driver Seat | 18/07/2019 | 18/07/2019 | 18/07/2019 | 18/07/2019 | 0 | TK_Complete | -824745350 | 282 | -824745350_282
MML3RSTPRO3020 | TT_Task | PROC NONO/ NOWC from Project Manager for Supplier: Driver Seat | 14/08/2019 | 14/08/2019 | 14/08/2019 | 14/08/2019 | 0 | TK_Complete | -824745350 | 283 | -824745350_283
MML3RSTPRO3030 | TT_Task | PROC Submission by Alstom for Supplier: Propulsion system | 17/10/2019 | 17/10/2019 | 17/10/2019 | 17/10/2019 | 0 | TK_Complete | -824745350 | 90 | -824745350_90
MML3RSTPRO3040 | TT_Task | PROC NONO/ NOWC from Project Manager for Supplier: Propulsion system | 13/11/2019 | 13/11/2019 | 13/11/2019 | 13/11/2019 | 0 | TK_Complete | -824745350 | 140 | -824745350_140
MML3RSTPRO3050 | TT_Task | PROC Submission by Alstom for Supplier: Auxilary Power Supply | 19/09/2019 | 19/09/2019 | 19/09/2019 | 19/09/2019 | 0 | TK_Complete | -824745350 | 300 | -824745350_300
MML3RSTPRO3060 | TT_Task | PROC NONO/ NOWC from Project Manager for Supplier: Auxilary Power Supply | 21/09/2019 | 21/09/2019 | 21/09/2019 | 21/09/2019 | 0 | TK_Complete | -824745350 | 81 | -824745350_81
MML3RSTPRO3070 | TT_Task | PROC Submission by Alstom for Supplier: Signages | 01/07/2020 | 15/07/2020 | 01/07/2020 | 15/07/2020 | 0 | TK_Complete | -824745350 | 276 | -824745350_276
MML3RSTPRO3080 | TT_Task | PROC NONO/ NOWC from Project Manager for Supplier: Signages | 06/07/2020 | 19/07/2020 | 06/07/2020 | 19/07/2020 | 0 | TK_Complete | -824745350 | 269 | -824745350_269
MML3RSTPRO2630 | TT_Task | PROC Submission of list of items (Lot 1) by Alstom to be imported for obtaining sponsorship letter | 20/08/2019 | 20/08/2019 | 20/08/2019 | 20/08/2019 | 0 | TK_Complete | -824745350 | 301 | -824745350_301
MML3RSTPRO2640 | TT_Task | PROC Providing sponsorship letter and approval of items (Lot 1) to be imported (Project Manager Scope) | 21/08/2019 | 25/10/2019 | 21/08/2019 | 25/10/2019 | 0 | TK_Complete | -824745350 | 301 | -824745350_301
MML3RSTPRO2645 | TT_Task | PROC Submission of Sponsorship letter / documentations (by Alstom) for items to be imported Lot 1 | 26/01/2020 | 24/02/2020 | 28/10/2019 | 26/11/2019 | 0 | TK_Complete | -824745350 | 301 | -824745350_301
MML3RSTPRO2650 | TT_Task | PROC Approval from Customs to register for project import benefit (Items Lot 1) | 26/01/2020 | 25/03/2020 | 27/11/2019 | 15/12/2019 | 0 | TK_Complete | -824745350 | 302 | -824745350_302
MML3RSTPRO8810 | TT_Task | PROC Submission of list of items (Lot 2) by Alstom to be imported for obtaining sponsorship letter | 08/02/2020 | 08/03/2020 | 20/08/2019 | 20/08/2019 | 0 | TK_Complete | -824745350 | 301 | -824745350_301
MML3RSTPRO8820 | TT_Task | PROC Providing sponsorship letter and approval of items (Lot 2) to be imported from Project Manager | 09/03/2020 | 07/04/2020 | 20/08/2019 | 25/10/2019 | 0 | TK_Complete | -824745350 | 301 | -824745350_301
MML3RSTPRO8830 | TT_Task | PROC Contractor (Alstom) to register for project import benefit (Items Lot 2) | 08/02/2020 | 08/03/2020 | 28/10/2019 | 26/11/2019 | 0 | TK_Complete | -824745350 | 302 | -824745350_302
MML3RSTPRO1000 | TT_Task | PROC Car Body Shell Components/Material - GO For Tooling - NRC PO Release | 17/04/2019 | 15/06/2019 | 17/04/2019 | 15/06/2019 | 0 | TK_Complete | -824745350 | 79 | -824745350_79
MML3RSTPRO1002 | TT_Task | PROC Car Body Shell Components/Material - Procurement of Parts | 17/06/2019 | 15/09/2019 | 17/06/2019 | 15/09/2019 | 0 | TK_Complete | -824745350 | 79 | -824745350_79
MML3RSTPRO1010 | TT_Task | PROC Car Body Shell Components/Material - Manufacturing of Parts | 17/09/2019 | 26/09/2019 | 17/09/2019 | 16/03/2020 | 0 | TK_Complete | -824745350 | 79 | -824745350_79
MML3RSTPRO1020 | TT_Task | PROC Car Body Shell Components/Material - FAI (Long Profile parts) | 17/03/2020 | 18/08/2020 | 17/03/2020 | 18/08/2020 | 0 | TK_Complete | -824745350 | 79 | -824745350_79
MML3RSTPRO1030 | TT_Task | PROC Car Body Shell Components/Material - Packing ; Transportation from Supplier works to Alstom Factory | 19/08/2020 | 20/08/2020 | 19/08/2020 | 20/08/2020 | 0 | TK_Complete | -824745350 | 303 | -824745350_303
MML3RSTPRO1260 | TT_Task | PROC Battery with Battery Box Technical CBC discussion/ closure | 10/07/2019 | 07/09/2019 | 10/07/2019 | 29/07/2019 | 0 | TK_Complete | -824745350 | 265 | -824745350_265
MML3RSTPRO1265 | TT_Task | PROC Battery with Battery Box Commercial closure ; PO Release | 30/07/2019 | 20/08/2019 | 30/07/2019 | 20/08/2019 | 0 | TK_Complete | -824745350 | 265 | -824745350_265
MML3RSTPRO1270 | TT_Task | PROC Battery with Battery Box TRS freeze ; Conceptual design | 21/08/2019 | 24/09/2019 | 21/08/2019 | 24/09/2019 | 0 | TK_Complete | -824745350 | 265 | -824745350_265
MML3RSTPRO1271 | TT_Task | PROC Battery with Battery Box Detailed Design | 25/09/2019 | 18/10/2019 | 25/09/2019 | 18/10/2019 | 0 | TK_Complete | -824745350 | 265 | -824745350_265
MML3RSTPRO1272 | TT_Task | PROC Battery with Battery Box Long lead time items procurement | 25/09/2019 | 08/01/2020 | 25/09/2019 | 14/11/2019 | 0 | TK_Complete | -824745350 | 265 | -824745350_265
MML3RSTPRO1273 | TT_Task | PROC Battery with Battery Box Manufacturing | 15/11/2019 | 24/12/2019 | 15/11/2019 | 22/10/2020 | 0 | TK_Complete | -824745350 | 265 | -824745350_265
MML3RSTPRO1280 | TT_Task | PROC Battery with Battery Box FAI/ FAT | 24/10/2020 | 24/10/2020 | 23/10/2020 | 23/10/2020 | 0 | TK_Complete | -824745350 | 265 | -824745350_265
MML3RSTPRO1282 | TT_Task | PROC Battery with Battery Box NONO/ NOWC from Project Manager | 25/10/2020 | 20/11/2020 | 24/10/2020 | 24/10/2020 | 0 | TK_Complete | -824745350 | 265 | -824745350_265
MML3RSTPRO1290 | TT_Task | PROC Battery with Battery Box Packing ; Transportation from Supplier works to Alstom Factory | 20/11/2020 | 29/11/2020 | 20/11/2020 | 05/02/2021 | 0 | TK_Complete | -824745350 | 265 | -824745350_265
MML3RSTPRO1340 | TT_Task | PROC Mechanical Brakes Technical CBC discussion/ closure | 27/09/2018 | 22/12/2018 | 13/04/2019 | 09/07/2019 | 0 | TK_Complete | -824745350 | 304 | -824745350_304
MML3RSTPRO1345 | TT_Task | PROC Mechanical Brakes Commercial closure ; PO Release | 03/07/2019 | 09/07/2019 | 10/07/2019 | 20/07/2020 | 0 | TK_Complete | -824745350 | 304 | -824745350_304
MML3RSTPRO1350 | TT_Task | PROC Mechanical Brakes TRS freeze ; Conceptual design | 17/07/2019 | 30/08/2019 | 21/07/2020 | 25/07/2020 | 0 | TK_Complete | -824745350 | 305 | -824745350_305
MML3RSTPRO1351 | TT_Task | PROC Mechanical Brakes Detailed Design | 31/08/2019 | 14/03/2020 | 26/07/2020 | 27/07/2020 | 0 | TK_Complete | -824745350 | 264 | -824745350_264
MML3RSTPRO1352 | TT_Task | PROC Mechanical Brakes Long lead time items procurement | 31/08/2019 | 14/03/2020 | 26/07/2020 | 27/07/2020 | 0 | TK_Complete | -824745350 | 306 | -824745350_306
MML3RSTPRO1353 | TT_Task | PROC Mechanical Brakes Manufacturing | 16/03/2020 | 20/08/2020 | 28/07/2020 | 28/08/2020 | 0 | TK_Complete | -824745350 | 264 | -824745350_264
MML3RSTPRO1360 | TT_Task | PROC Mechanical Brakes - FAI/ FAT( Brake cylinder,BCU,BECU,air dryer,air reservior, motor ; aux comp set) | 25/02/2022 | 25/02/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 264 | -824745350_264
MML3RSTPRO1362 | TT_Task | PROC Mechanical Brakes NONO/ NOWC from Project Manager | 25/02/2022 | 25/02/2022 | nan | nan | 368 | TK_NotStart | -824745350 | 139 | -824745350_139
MML3RSTPRO1370 | TT_Task | PROC Mechanical Brakes - Packing ; Transportation from Supplier works to Alstom Factory | 24/09/2020 | 21/11/2020 | 24/09/2020 | 21/11/2020 | 0 | TK_Complete | -824745350 | 264 | -824745350_264
MML3RSTPRO1380 | TT_Task | PROC Passenger Doors - Technical CBC discussion/ closure | 08/04/2019 | 27/06/2019 | 09/04/2019 | 10/07/2019 | 0 | TK_Complete | -824745350 | 307 | -824745350_307
MML3RSTPRO1385 | TT_Task | PROC Passenger Doors - Commercial closure ; PO Release | 28/06/2019 | 11/07/2019 | 11/06/2019 | 21/06/2019 | 0 | TK_Complete | -824745350 | 308 | -824745350_308
MML3RSTPRO1390 | TT_Task | PROC Passenger Doors TRS freeze ; Conceptual design | 25/07/2019 | 28/08/2019 | 22/06/2019 | 28/08/2019 | 0 | TK_Complete | -824745350 | 309 | -824745350_309
MML3RSTPRO1391 | TT_Task | PROC Passenger Doors Detailed Design | 29/08/2019 | 25/10/2019 | 29/08/2019 | 25/10/2019 | 0 | TK_Complete | -824745350 | 310 | -824745350_310
MML3RSTPRO1392 | TT_Task | PROC Passenger Doors Long lead time items procurement | 29/08/2019 | 11/11/2019 | 29/08/2019 | 25/06/2020 | 0 | TK_Complete | -824745350 | 306 | -824745350_306
MML3RSTPRO1393 | TT_Task | PROC Passenger Doors Manufacturing | 26/06/2020 | 10/08/2020 | 26/06/2020 | 18/11/2020 | 0 | TK_Complete | -824745350 | 310 | -824745350_310
MML3RSTPRO1400 | TT_Task | PROC Passenger Doors - FAI/ FAT | 25/02/2022 | 25/02/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 310 | -824745350_310
MML3RSTPRO1402 | TT_Task | PROC Passenger Doors - NONO/ NOWC from Project Manager | 25/02/2022 | 25/02/2022 | nan | nan | 368 | TK_NotStart | -824745350 | 267 | -824745350_267
MML3RSTPRO1410 | TT_Task | PROC Passenger Doors - Packing ; Transportation from Supplier works to Alstom Factory | 14/09/2020 | 29/10/2020 | 14/09/2020 | 29/10/2020 | 0 | TK_Complete | -824745350 | 266 | -824745350_266
MML3RSTPRO1420 | TT_Task | PROC Transformer - Technical CBC discussion/ closure | 14/04/2019 | 03/07/2019 | 05/11/2018 | 17/12/2018 | 0 | TK_Complete | -824745350 | 311 | -824745350_311
MML3RSTPRO1425 | TT_Task | PROC Transformer - Commercial closure ; PO Release | 03/07/2019 | 16/07/2019 | 18/12/2018 | 27/12/2018 | 0 | TK_Complete | -824745350 | 312 | -824745350_312
MML3RSTPRO1430 | TT_Task | PROC Transformer TRS freeze ; Conceptual design | 24/07/2019 | 27/08/2019 | 28/12/2018 | 27/08/2019 | 0 | TK_Complete | -824745350 | 313 | -824745350_313
MML3RSTPRO1431 | TT_Task | PROC Transformer Detailed Design | 28/08/2019 | 28/10/2019 | 28/08/2019 | 28/10/2019 | 0 | TK_Complete | -824745350 | 268 | -824745350_268
MML3RSTPRO1432 | TT_Task | PROC Transformer Long lead time items procurement | 28/08/2019 | 04/11/2019 | 28/08/2019 | 04/11/2019 | 0 | TK_Complete | -824745350 | 314 | -824745350_314
MML3RSTPRO1433 | TT_Task | PROC Transformer Manufacturing | 05/11/2019 | 03/01/2020 | 05/11/2019 | 28/11/2019 | 0 | TK_Complete | -824745350 | 268 | -824745350_268
MML3RSTPRO1440 | TT_Task | PROC Transformer - FAI/ FAT (Incl Transformer Radiator Motor ; Oil Pump Motor) | 26/11/2019 | 26/11/2019 | 29/11/2019 | 29/11/2019 | 0 | TK_Complete | -824745350 | 315 | -824745350_315
MML3RSTPRO1442 | TT_Task | PROC Transformer - NONO/ NOWC from Project Manager | 27/12/2019 | 27/12/2019 | 27/12/2019 | 27/12/2019 | 0 | TK_Complete | -824745350 | 81 | -824745350_81
MML3RSTPRO1450 | TT_Task | PROC Transformer - Packing ; Transportation from Supplier works to Alstom Factory | 13/06/2020 | 26/09/2020 | 13/06/2020 | 26/09/2020 | 0 | TK_Complete | -824745350 | 268 | -824745350_268
MML3RSTPRO1580 | TT_Task | PROC Wheels - Technical CBC discussion/ closure | 22/05/2019 | 09/08/2019 | 28/02/2019 | 17/05/2019 | 0 | TK_Complete | -824745350 | 307 | -824745350_307
MML3RSTPRO1585 | TT_Task | PROC Wheels - Commercial closure ; PO Release | 10/08/2019 | 23/08/2019 | 18/05/2019 | 05/08/2019 | 0 | TK_Complete | -824745350 | 308 | -824745350_308
MML3RSTPRO1590 | TT_Task | PROC Wheels TRS freeze ; Conceptual design | 09/09/2019 | 13/10/2019 | 06/08/2019 | 13/10/2019 | 0 | TK_Complete | -824745350 | 305 | -824745350_305
MML3RSTPRO1592 | TT_Task | PROC Wheels Detailed Design | 14/10/2019 | 12/12/2019 | 14/10/2019 | 05/01/2020 | 0 | TK_Complete | -824745350 | 316 | -824745350_316
MML3RSTPRO1593 | TT_Task | PROC Wheels Long lead time items procurement | 14/10/2019 | 16/01/2020 | 14/10/2019 | 08/01/2020 | 0 | TK_Complete | -824745350 | 314 | -824745350_314
MML3RSTPRO1594 | TT_Task | PROC Wheels Manufacturing | 06/01/2020 | 07/02/2020 | 06/01/2020 | 12/02/2020 | 0 | TK_Complete | -824745350 | 316 | -824745350_316
MML3RSTPRO1600 | TT_Task | PROC Wheels - FAI/ FAT | 25/02/2022 | 25/02/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 317 | -824745350_317
MML3RSTPRO1602 | TT_Task | PROC Wheels - NONO/ NOWC from Project Manager | 26/02/2022 | 26/02/2022 | nan | nan | 304 | TK_NotStart | -824745350 | 273 | -824745350_273
MML3RSTPRO1610 | TT_Task | PROC Wheels - Packing ; Transportation from Supplier works to Alstom Factory | 28/03/2020 | 18/06/2020 | 28/03/2020 | 18/06/2020 | 0 | TK_Complete | -824745350 | 272 | -824745350_272
MML3RSTPRO1040 | TT_Task | PROC Couplers - Technical CBC discussion/ closure | 30/04/2019 | 18/07/2019 | 11/12/2018 | 22/03/2019 | 0 | TK_Complete | -824745350 | 274 | -824745350_274
MML3RSTPRO1045 | TT_Task | PROC Couplers - Commercial closure ; PO Release | 19/07/2019 | 01/08/2019 | 23/03/2019 | 09/04/2019 | 0 | TK_Complete | -824745350 | 274 | -824745350_274
MML3RSTPRO1050 | TT_Task | PROC Couplers TRS freeze ; Conceptual design | 09/08/2019 | 12/09/2019 | 10/04/2019 | 12/09/2019 | 0 | TK_Complete | -824745350 | 313 | -824745350_313
MML3RSTPRO1051 | TT_Task | PROC Couplers Detailed Design | 13/09/2019 | 28/10/2019 | 13/09/2019 | 28/10/2019 | 0 | TK_Complete | -824745350 | 274 | -824745350_274
MML3RSTPRO1052 | TT_Task | PROC Couplers Long lead time items procurement | 13/09/2019 | 10/07/2020 | 13/09/2019 | 10/07/2020 | 0 | TK_Complete | -824745350 | 318 | -824745350_318
MML3RSTPRO1053 | TT_Task | PROC Couplers Manufacturing | 11/07/2020 | 11/08/2020 | 11/07/2020 | 10/09/2020 | 0 | TK_Complete | -824745350 | 274 | -824745350_274
MML3RSTPRO1060 | TT_Task | PROC Couplers - FAI/ FAT | 13/08/2021 | 13/08/2021 | 13/08/2021 | 13/08/2021 | 0 | TK_Complete | -824745350 | 317 | -824745350_317
MML3RSTPRO1062 | TT_Task | PROC Couplers - NONO/ NOWC from Project Manager | 22/07/2021 | 22/07/2021 | 22/07/2021 | 22/07/2021 | 0 | TK_Complete | -824745350 | 275 | -824745350_275
MML3RSTPRO1070 | TT_Task | PROC Couplers - Packing ; Transportation from Supplier works to Alstom Factory | 16/09/2020 | 18/11/2020 | 16/09/2020 | 18/11/2020 | 0 | TK_Complete | -824745350 | 274 | -824745350_274
MML3RSTPRO1800 | TT_Task | PROC Bogie Frame - Technical CBC discussion/ closure | 11/06/2019 | 29/08/2019 | 15/02/2019 | 07/03/2019 | 0 | TK_Complete | -824745350 | 319 | -824745350_319
MML3RSTPRO1805 | TT_Task | PROC Bogie Frame - Commercial closure ; PO Release | 30/08/2019 | 03/09/2019 | 08/03/2019 | 21/05/2019 | 0 | TK_Complete | -824745350 | 319 | -824745350_319
MML3RSTPRO1810 | TT_Task | PROC Bogie Frame TRS freeze ; Conceptual design | 04/09/2019 | 23/09/2019 | 22/05/2019 | 23/09/2019 | 0 | TK_Complete | -824745350 | 313 | -824745350_313
MML3RSTPRO1811 | TT_Task | PROC Bogie Frame Detailed Design | 24/09/2019 | 30/09/2019 | 24/09/2019 | 30/09/2019 | 0 | TK_Complete | -824745350 | 320 | -824745350_320
MML3RSTPRO1812 | TT_Task | PROC Bogie Frame Long lead time items procurement | 24/09/2019 | 22/11/2019 | 24/09/2019 | 22/10/2019 | 0 | TK_Complete | -824745350 | 318 | -824745350_318
MML3RSTPRO1813 | TT_Task | PROC Bogie Frame Manufacturing | 23/10/2019 | 29/01/2020 | 23/10/2019 | 29/01/2020 | 0 | TK_Complete | -824745350 | 320 | -824745350_320
MML3RSTPRO1820 | TT_Task | PROC Bogie Frame - FAI/ FAT | 30/01/2020 | 30/01/2020 | 22/12/2020 | 22/12/2020 | 0 | TK_Complete | -824745350 | 317 | -824745350_317
MML3RSTPRO1822 | TT_Task | PROC Bogie Frame - NONO/ NOWC from Project Manager | 25/01/2021 | 25/01/2021 | 23/12/2020 | 23/12/2020 | 0 | TK_Complete | -824745350 | 296 | -824745350_296
MML3RSTPRO1830 | TT_Task | PROC Bogie Frame - Packing ; Transportation from Supplier works to Alstom Factory | 18/06/2020 | 16/09/2020 | 18/06/2020 | 16/09/2020 | 0 | TK_Complete | -824745350 | 303 | -824745350_303
MML3RSTPRO1980 | TT_Task | PROC Bogie Frame Manufacturing for Static and Fatigue tests | 25/01/2021 | 03/02/2021 | 25/12/2020 | 03/01/2021 | 0 | TK_Complete | -824745350 | 321 | -824745350_321
MML3RSTPRO1990 | TT_Task | PROC Bogie Frame Transportation (from India to France) for Static and Fatigue tests | 25/01/2021 | 03/02/2021 | 04/01/2021 | 10/02/2021 | 0 | TK_Complete | -824745350 | 321 | -824745350_321
MML3RSTPRO2000 | TT_Task | PROC Bogie Frame Inspection + Setup for Static and Fatigue tests (at France) | 25/12/2021 | 02/01/2022 | 26/11/2021 | 02/12/2021 | 0 | TK_Complete | -824745350 | 321 | -824745350_321
MML3RSTPRO2010 | TT_Task | PROC Bogie Frame Static and Fatigue tests (at France) + Report generation | 03/01/2022 | 27/06/2022 | 03/12/2021 | nan | 0 | TK_Active | -824745350 | 321 | -824745350_321
MML3RSTPRO2020 | TT_Task | PROC Bogie Frame Project Manager Witness for Static and Fatigue tests (at France) | 20/08/2022 | 26/08/2022 | nan | nan | 1488 | TK_NotStart | -824745350 | 321 | -824745350_321
MML3RSTPRO1160 | TT_Task | PROC Pantograph - Technical CBC discussion/ closure | 22/09/2018 | 10/12/2018 | 28/11/2018 | 26/07/2019 | 0 | TK_Complete | -824745350 | 322 | -824745350_322
MML3RSTPRO1165 | TT_Task | PROC Pantograph -Commercial closure ; PO Release | 11/12/2018 | 24/12/2018 | 27/07/2019 | 21/08/2019 | 0 | TK_Complete | -824745350 | 322 | -824745350_322
MML3RSTPRO1170 | TT_Task | PROC Pantograph TRS freeze ; Conceptual design | 28/08/2019 | 26/09/2019 | 22/08/2019 | 26/09/2019 | 0 | TK_Complete | -824745350 | 322 | -824745350_322
MML3RSTPRO1171 | TT_Task | PROC Pantograph Detailed Design | 27/09/2019 | 18/10/2019 | 27/09/2019 | 18/10/2019 | 0 | TK_Complete | -824745350 | 322 | -824745350_322
MML3RSTPRO1172 | TT_Task | PROC Pantograph Long lead time items procurement | 27/09/2019 | 17/06/2020 | 27/09/2019 | 17/06/2020 | 0 | TK_Complete | -824745350 | 318 | -824745350_318
MML3RSTPRO1173 | TT_Task | PROC Pantograph Manufacturing | 18/06/2020 | 17/07/2020 | 18/06/2020 | 24/08/2020 | 0 | TK_Complete | -824745350 | 322 | -824745350_322
MML3RSTPRO1180 | TT_Task | PROC Pantograph- FAI/ FAT | 20/07/2021 | 20/07/2021 | 20/07/2021 | 20/07/2021 | 0 | TK_Complete | -824745350 | 317 | -824745350_317
MML3RSTPRO1182 | TT_Task | PROC Pantograph- NONO/ NOWC from Project Manager | 20/07/2021 | 20/07/2021 | 20/07/2021 | 20/07/2021 | 0 | TK_Complete | -824745350 | 261 | -824745350_261
MML3RSTPRO1190 | TT_Task | PROC Pantograph - Packing ; Transportation from Supplier works to Alstom Factory | 03/09/2020 | 03/09/2020 | 03/09/2020 | 03/09/2020 | 0 | TK_Complete | -824745350 | 303 | -824745350_303
MML3RSTPRO1660 | TT_Task | PROC Traction Converter TRS freeze ; Conceptual design | 05/02/2019 | 09/05/2019 | 05/02/2019 | 09/05/2019 | 0 | TK_Complete | -824745350 | 305 | -824745350_305
MML3RSTPRO1661 | TT_Task | PROC Traction Converter Detailed Design | 10/05/2019 | 13/06/2019 | 10/05/2019 | 08/07/2019 | 0 | TK_Complete | -824745350 | 323 | -824745350_323
MML3RSTPRO1662 | TT_Task | PROC Traction Converter Long lead time items procurement | 10/05/2019 | 08/07/2019 | 10/05/2019 | 08/07/2019 | 0 | TK_Complete | -824745350 | 314 | -824745350_314
MML3RSTPRO1663 | TT_Task | PROC Traction Converter Packing ; Transportation of items | 09/07/2019 | 17/08/2019 | 09/07/2019 | 06/09/2019 | 0 | TK_Complete | -824745350 | 272 | -824745350_272
MML3RSTPRO1664 | TT_Task | PROC Traction Converter Manufacturing | 07/08/2020 | 02/11/2020 | 07/08/2020 | 02/11/2020 | 0 | TK_Complete | -824745350 | 323 | -824745350_323
MML3RSTPRO1670 | TT_Task | PROC IGBT Module and other power components - FAI/ FAT | 03/11/2020 | 18/11/2020 | 03/11/2020 | 18/11/2020 | 0 | TK_Complete | -824745350 | 315 | -824745350_315
MML3RSTPRO1680 | TT_Task | PROC Traction Converter: Combined System Propulsion tests (at CRL, Belgium) | 19/11/2020 | 08/12/2020 | 19/11/2020 | nan | 0 | TK_Active | -824745350 | 323 | -824745350_323
MML3RSTPRO1690 | TT_Task | PROC Traction Converter - FAI/ FAT | 09/03/2022 | 12/03/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 315 | -824745350_315
MML3RSTPRO1695 | TT_Task | PROC Traction Converter - NONO/ NOWC from Project Manager | 13/03/2022 | 13/03/2022 | nan | nan | 360 | TK_NotStart | -824745350 | 273 | -824745350_273
MML3RSTPRO1700 | TT_Task | PROC Traction Converter - Packing ; Transportation from Supplier works to Alstom Factory | 03/11/2020 | 09/11/2020 | 11/10/2020 | 01/01/2021 | 0 | TK_Complete | -824745350 | 272 | -824745350_272
MML3RSTPRO1710 | TT_Task | PROC Auxilary Power Supply TRS freeze ; Conceptual design | 05/02/2019 | 10/05/2019 | 05/02/2019 | 05/04/2019 | 0 | TK_Complete | -824745350 | 313 | -824745350_313
MML3RSTPRO1711 | TT_Task | PROC Auxilary Power Supply Detailed Design | 06/04/2019 | 04/06/2019 | 06/04/2019 | 04/06/2019 | 0 | TK_Complete | -824745350 | 300 | -824745350_300
MML3RSTPRO1712 | TT_Task | PROC Auxilary Power Supply Long lead time items procurement | 05/06/2019 | 03/08/2019 | 05/06/2019 | 03/08/2019 | 0 | TK_Complete | -824745350 | 314 | -824745350_314
MML3RSTPRO1713 | TT_Task | PROC Auxilary Power Supply - Packing ; transportation of items | 04/08/2019 | 02/10/2019 | 04/08/2019 | 02/10/2019 | 0 | TK_Complete | -824745350 | 300 | -824745350_300
MML3RSTPRO1714 | TT_Task | PROC Auxilary Power Supply Manufacturing | 03/10/2019 | 16/11/2019 | 03/10/2019 | 15/12/2020 | 0 | TK_Complete | -824745350 | 300 | -824745350_300
MML3RSTPRO1720 | TT_Task | PROC Auxilary Power Supply - FAI/ FAT | 25/02/2022 | 25/02/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 300 | -824745350_300
MML3RSTPRO1721 | TT_Task | PROC Auxilary Power Supply - NONO/ NOWC from Project Manager | 25/02/2022 | 25/02/2022 | nan | nan | 568 | TK_NotStart | -824745350 | 81 | -824745350_81
MML3RSTPRO1730 | TT_Task | PROC Auxilary Power Supply - Packing ; Transportation from Supplier works to Alstom Factory | 03/11/2020 | 09/11/2020 | 03/11/2020 | 25/12/2020 | 0 | TK_Complete | -824745350 | 300 | -824745350_300
MML3RSTPRO1371 | TT_Task | PROC Cab Mask - Technical CBC discussion/ closure | 10/08/2019 | 24/08/2019 | 27/02/2019 | 27/12/2019 | 0 | TK_Complete | -824745350 | 278 | -824745350_278
MML3RSTPRO1372 | TT_Task | PROC Cab Mask - Commercial closure ; PO Release | 18/02/2020 | 02/03/2020 | 28/12/2019 | 20/01/2020 | 0 | TK_Complete | -824745350 | 278 | -824745350_278
MML3RSTPRO1373 | TT_Task | PROC Cab Mask TRS freeze ; Conceptual design | 25/07/2020 | 07/08/2020 | 25/07/2020 | 07/08/2020 | 0 | TK_Complete | -824745350 | 313 | -824745350_313
MML3RSTPRO1374 | TT_Task | PROC Cab Mask Detailed Design | 08/08/2020 | 28/08/2020 | 08/08/2020 | 28/08/2020 | 0 | TK_Complete | -824745350 | 278 | -824745350_278
MML3RSTPRO1375 | TT_Task | PROC Cab Mask Long lead time items procurement | 08/08/2020 | 28/08/2020 | 08/08/2020 | 28/08/2020 | 0 | TK_Complete | -824745350 | 318 | -824745350_318
MML3RSTPRO1376 | TT_Task | PROC Cab Mask Manufacturing | 29/08/2020 | 17/09/2020 | 29/08/2020 | 12/11/2020 | 0 | TK_Complete | -824745350 | 278 | -824745350_278
MML3RSTPRO1377 | TT_Task | PROC Cab Mask - FAI/ FAT | 12/07/2021 | 12/07/2021 | 12/07/2021 | 12/07/2021 | 0 | TK_Complete | -824745350 | 317 | -824745350_317
MML3RSTPRO1378 | TT_Task | PROC Cab Mask NONO/ NOWC from Project Manager | 17/07/2021 | 17/07/2021 | 17/07/2021 | 17/07/2021 | 0 | TK_Complete | -824745350 | 279 | -824745350_279
MML3RSTPRO1379 | TT_Task | PROC Cab Mask - Packing ; Transportation from Supplier works to Alstom Factory | 25/12/2020 | 03/01/2021 | 26/11/2020 | 14/12/2020 | 0 | TK_Complete | -824745350 | 278 | -824745350_278
MML3RSTPRO8090 | TT_Task | PROC High Voltage System including 25KV cable with HV cable ; bushing Technical CBC discussion/ closure | 26/04/2019 | 06/11/2019 | 19/08/2019 | 06/11/2019 | 0 | TK_Complete | -824745350 | 281 | -824745350_281
MML3RSTPRO8092 | TT_Task | PROC High Voltage System including 25KV cable with HV cable ; bushing Commercial closure ; PO Release | 07/11/2019 | 05/12/2019 | 07/11/2019 | 05/12/2019 | 0 | TK_Complete | -824745350 | 281 | -824745350_281
MML3RSTPRO8094 | TT_Task | PROC High Voltage System including 25KV cable with HV cable ; bushing TRS freeze ; Conceptual design | 14/12/2019 | 25/03/2020 | 14/12/2019 | 25/03/2020 | 0 | TK_Complete | -824745350 | 281 | -824745350_281
MML3RSTPRO8096 | TT_Task | PROC High Voltage System including 25KV cable with HV cable ; bushing Detailed Design | 26/03/2020 | 09/04/2020 | 26/03/2020 | 09/04/2020 | 0 | TK_Complete | -824745350 | 281 | -824745350_281
MML3RSTPRO8098 | TT_Task | PROC High Voltage System including 25KV cable with HV cable ; bushing Long lead time items procurement | 10/04/2020 | 02/07/2020 | 10/04/2020 | 03/06/2020 | 0 | TK_Complete | -824745350 | 281 | -824745350_281
MML3RSTPRO8102 | TT_Task | PROC High Voltage System including 25KV cable with HV cable ; bushing Manufacturing | 25/06/2020 | 02/07/2020 | 04/06/2020 | 02/07/2020 | 0 | TK_Complete | -824745350 | 281 | -824745350_281
MML3RSTPRO8104 | TT_Task | PROC 25KV cable with HV cable ; bushing - FAI/ FAT | 25/02/2021 | 02/03/2021 | 09/02/2021 | 09/02/2021 | 0 | TK_Complete | -824745350 | 281 | -824745350_281
MML3RSTPRO8106 | TT_Task | PROC High Voltage System including 25KV cable with HV cable ; bushing NONO/ NOWC from Project Manager | 03/03/2021 | 03/03/2021 | 09/02/2021 | 09/02/2021 | 0 | TK_Complete | -824745350 | 281 | -824745350_281
MML3RSTPRO8110 | TT_Task | PROC High Voltage System including 25KV cable with HV cable ; bushing - Packing ; Transportation from Supplier works t | 16/07/2020 | 25/07/2020 | 16/07/2020 | 04/12/2020 | 0 | TK_Complete | -824745350 | 281 | -824745350_281
MML3RSTPRO8180 | TT_Task | PROC Master Controller Technical CBC discussion/ closure | 08/06/2019 | 06/08/2019 | 05/12/2018 | 20/05/2019 | 0 | TK_Complete | -824745350 | 311 | -824745350_311
MML3RSTPRO8182 | TT_Task | PROC Master Controller Commercial closure ; PO Release | 25/09/2019 | 08/10/2019 | 21/05/2019 | 27/07/2019 | 0 | TK_Complete | -824745350 | 312 | -824745350_312
MML3RSTPRO8184 | TT_Task | PROC Master Controller TRS freeze ; Conceptual design | 09/10/2019 | 24/10/2019 | 28/07/2019 | 24/10/2019 | 0 | TK_Complete | -824745350 | 324 | -824745350_324
MML3RSTPRO8188 | TT_Task | PROC Master Controller Detailed Design | 25/10/2019 | 08/11/2019 | 25/10/2019 | 23/11/2019 | 0 | TK_Complete | -824745350 | 325 | -824745350_325
MML3RSTPRO8192 | TT_Task | PROC Master Controller Long lead time items procurement | 25/10/2019 | 03/07/2020 | 25/10/2019 | 03/07/2020 | 0 | TK_Complete | -824745350 | 318 | -824745350_318
MML3RSTPRO8194 | TT_Task | PROC Master Controller Manufacturing | 04/07/2020 | 15/07/2020 | 04/07/2020 | 14/07/2020 | 0 | TK_Complete | -824745350 | 325 | -824745350_325
MML3RSTPRO8196 | TT_Task | PROC Master Controller - FAI/ FAT | 04/12/2020 | 04/12/2020 | 04/12/2020 | 04/12/2020 | 0 | TK_Complete | -824745350 | 326 | -824745350_326
MML3RSTPRO8198 | TT_Task | PROC Master Controller NONO/ NOWC from Project Manager | 25/01/2021 | 25/01/2021 | 04/12/2020 | 04/12/2020 | 0 | TK_Complete | -824745350 | 81 | -824745350_81
MML3RSTPRO8200 | TT_Task | PROC Master Controller - Packing ; Transportation from Supplier works to Alstom Factory | 26/12/2020 | 09/01/2021 | 16/07/2020 | 25/09/2020 | 0 | TK_Complete | -824745350 | 303 | -824745350_303
MML3RSTPRO7190 | TT_Task | PROC Passenger Seat - Technical CBC discussion/ closure | 08/08/2019 | 21/09/2019 | 01/11/2019 | 15/03/2020 | 0 | TK_Complete | -824745350 | 307 | -824745350_307
MML3RSTPRO7191 | TT_Task | PROC Passenger Seat - Commercial closure ; PO Release | 23/02/2020 | 07/03/2020 | 16/03/2020 | 09/04/2020 | 0 | TK_Complete | -824745350 | 308 | -824745350_308
MML3RSTPRO7192 | TT_Task | PROC Passenger Seat TRS freeze ; Conceptual design | 22/01/2020 | 03/08/2020 | 10/04/2020 | 03/08/2020 | 0 | TK_Complete | -824745350 | 309 | -824745350_309
MML3RSTPRO7193 | TT_Task | PROC Passenger Seat Detailed Design | 04/08/2020 | 17/08/2020 | 04/08/2020 | 17/08/2020 | 0 | TK_Complete | -824745350 | 327 | -824745350_327
MML3RSTPRO7194 | TT_Task | PROC Passenger Seat Long lead time items procurement | 02/11/2020 | 16/11/2020 | 18/08/2020 | 28/08/2020 | 0 | TK_Complete | -824745350 | 306 | -824745350_306
MML3RSTPRO7195 | TT_Task | PROC Passenger Seat Manufacturing | 17/11/2020 | 01/12/2020 | 29/08/2020 | 16/11/2020 | 0 | TK_Complete | -824745350 | 327 | -824745350_327
MML3RSTPRO7196 | TT_Task | PROC Passenger Seat - FAI/ FAT | 25/02/2022 | 25/02/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 327 | -824745350_327
MML3RSTPRO7197 | TT_Task | PROC Passenger Seat NONO/ NOWC from Project Manager | 26/02/2022 | 26/02/2022 | nan | nan | 360 | TK_NotStart | -824745350 | 283 | -824745350_283
MML3RSTPRO7198 | TT_Task | PROC Passenger Seat - Packing ; Transportation from Supplier works to Alstom Factory | 25/12/2020 | 03/01/2021 | 10/12/2020 | 25/12/2020 | 0 | TK_Complete | -824745350 | 282 | -824745350_282
MML3RSTPRO7280 | TT_Task | PROC Car Interior - Technical CBC discussion/ closure | 25/01/2020 | 08/02/2020 | 08/08/2019 | 09/10/2019 | 0 | TK_Complete | -824745350 | 307 | -824745350_307
MML3RSTPRO7281 | TT_Task | PROC Car Interior - Commercial closure ; PO Release | 23/02/2020 | 07/03/2020 | 11/10/2019 | 25/12/2019 | 0 | TK_Complete | -824745350 | 308 | -824745350_308
MML3RSTPRO7282 | TT_Task | PROC Car Interior TRS freeze ; Conceptual design | 08/03/2020 | 28/03/2020 | 26/12/2019 | 08/01/2020 | 0 | TK_Complete | -824745350 | 309 | -824745350_309
MML3RSTPRO7283 | TT_Task | PROC Car Interior Detailed Design | 09/01/2020 | 09/06/2020 | 09/01/2020 | 09/06/2020 | 0 | TK_Complete | -824745350 | 328 | -824745350_328
MML3RSTPRO7284 | TT_Task | PROC Car Interior Long lead time items procurement | 10/06/2020 | 20/06/2020 | 10/06/2020 | 26/09/2020 | 0 | TK_Complete | -824745350 | 306 | -824745350_306
MML3RSTPRO7285 | TT_Task | PROC Car Interior Manufacturing | 28/09/2020 | 12/10/2020 | 28/09/2020 | 30/12/2020 | 0 | TK_Complete | -824745350 | 328 | -824745350_328
MML3RSTPRO7286 | TT_Task | PROC Interior Panel - FAI/ FAT | 28/07/2021 | 28/07/2021 | 28/07/2021 | 28/07/2021 | 0 | TK_Complete | -824745350 | 329 | -824745350_329
MML3RSTPRO7287 | TT_Task | PROC Car Interior NONO/ NOWC from Project Manager | 28/07/2021 | 28/07/2021 | 28/07/2021 | 28/07/2021 | 0 | TK_Complete | -824745350 | 285 | -824745350_285
MML3RSTPRO7300 | TT_Task | PROC Car Interior - Packing ; Transportation from Supplier works to Alstom Factory | 25/12/2020 | 03/01/2021 | 24/09/2020 | 08/01/2021 | 0 | TK_Complete | -824745350 | 303 | -824745350_303
MML3RSTPRO7370 | TT_Task | PROC Windows, Glasses and Windscreen- Technical CBC discussion/ closure | 30/06/2019 | 27/09/2019 | 26/12/2018 | 26/06/2019 | 0 | TK_Complete | -824745350 | 286 | -824745350_286
MML3RSTPRO7371 | TT_Task | PROC Windows, Glasses and Windscreen- Commercial closure ; PO Release | 28/09/2019 | 05/10/2019 | 29/06/2019 | 30/08/2019 | 0 | TK_Complete | -824745350 | 286 | -824745350_286
MML3RSTPRO7373 | TT_Task | PROC Windows, Glasses and Windscreen TRS freeze ; Conceptual design | 07/10/2019 | 23/11/2019 | 31/08/2019 | 06/11/2019 | 0 | TK_Complete | -824745350 | 286 | -824745350_286
MML3RSTPRO7374 | TT_Task | PROC Windows, Glasses and Windscreen Detailed Design | 11/02/2020 | 11/03/2020 | 07/11/2019 | 18/12/2019 | 0 | TK_Complete | -824745350 | 286 | -824745350_286
MML3RSTPRO7375 | TT_Task | PROC Windows, Glasses and Windscreen Long lead time items procurement | 19/12/2019 | 08/07/2020 | 19/12/2019 | 08/07/2020 | 0 | TK_Complete | -824745350 | 286 | -824745350_286
MML3RSTPRO7376 | TT_Task | PROC Windows, Glasses and Windscreen Manufacturing | 09/07/2020 | 27/07/2020 | 09/07/2020 | 27/07/2020 | 0 | TK_Complete | -824745350 | 286 | -824745350_286
MML3RSTPRO7380 | TT_Task | PROC Windows, Glasses and Windscreen- FAI/ FAT | 25/02/2021 | 26/02/2021 | 23/02/2021 | 04/03/2021 | 0 | TK_Complete | -824745350 | 286 | -824745350_286
MML3RSTPRO7381 | TT_Task | PROC Windows, Glasses and Windscreen NONO/ NOWC from Project Manager | 01/03/2021 | 01/03/2021 | 05/03/2021 | 05/03/2021 | 0 | TK_Complete | -824745350 | 286 | -824745350_286
MML3RSTPRO7382 | TT_Task | PROC Windows, Glasses and Windscreen- Packing ; Transportation from Supplier works to Alstom Factory | 25/08/2020 | 09/10/2020 | 25/08/2020 | 09/10/2020 | 0 | TK_Complete | -824745350 | 286 | -824745350_286
MML3RSTPRO8030 | TT_Task | PROC Cab Control Devices - Technical CBC discussion/ closure | 12/08/2019 | 26/08/2019 | 17/01/2019 | 03/02/2020 | 0 | TK_Complete | -824745350 | 330 | -824745350_330
MML3RSTPRO8031 | TT_Task | PROC Cab Control Devices - Commercial closure ; PO Release | 23/02/2020 | 07/03/2020 | 04/02/2020 | 13/03/2020 | 0 | TK_Complete | -824745350 | 330 | -824745350_330
MML3RSTPRO8032 | TT_Task | PROC Cab Control Devices TRS freeze ; Conceptual design | 08/03/2020 | 11/04/2020 | 14/03/2020 | 30/03/2020 | 0 | TK_Complete | -824745350 | 313 | -824745350_313
MML3RSTPRO8033 | TT_Task | PROC Cab Control Devices Detailed Design | 12/04/2020 | 16/05/2020 | 31/03/2020 | 30/04/2020 | 0 | TK_Complete | -824745350 | 330 | -824745350_330
MML3RSTPRO8035 | TT_Task | PROC Cab Control Devices Long lead time items procurement | 17/01/2020 | 14/07/2020 | 01/05/2020 | 14/06/2020 | 0 | TK_Complete | -824745350 | 318 | -824745350_318
MML3RSTPRO8036 | TT_Task | PROC Cab Control Devices Manufacturing | 15/07/2020 | 03/08/2020 | 15/06/2020 | 19/11/2020 | 0 | TK_Complete | -824745350 | 330 | -824745350_330
MML3RSTPRO8040 | TT_Task | PROC Windscreen - FAI/ FAT | 20/07/2021 | 20/07/2021 | 20/07/2021 | 20/07/2021 | 0 | TK_Complete | -824745350 | 329 | -824745350_329
MML3RSTPRO8041 | TT_Task | PROC Cab Control Devices NONO/ NOWC from Project Manager | 20/07/2021 | 20/07/2021 | 20/07/2021 | 20/07/2021 | 0 | TK_Complete | -824745350 | 81 | -824745350_81
MML3RSTPRO8050 | TT_Task | PROC Cab Control Devices - Packing ; Transportation from Supplier works to Alstom Factory | 25/08/2020 | 03/09/2020 | 25/08/2020 | 14/12/2020 | 0 | TK_Complete | -824745350 | 303 | -824745350_303
MML3RSTPRO7460 | TT_Task | PROC Emergency Evacuation Ramp - Technical CBC discussion/ closure | 01/10/2019 | 21/11/2019 | 04/05/2019 | 23/06/2019 | 0 | TK_Complete | -824745350 | 288 | -824745350_288
MML3RSTPRO7461 | TT_Task | PROC Emergency Evacuation Ramp - Commercial closure ; PO Release | 22/11/2019 | 14/08/2020 | 24/06/2019 | 23/07/2019 | 0 | TK_Complete | -824745350 | 288 | -824745350_288
MML3RSTPRO7462 | TT_Task | PROC Emergency Evacuation Ramp TRS freeze ; Conceptual design | 27/07/2020 | 14/08/2020 | 24/07/2019 | 14/08/2020 | 0 | TK_Complete | -824745350 | 288 | -824745350_288
MML3RSTPRO7463 | TT_Task | PROC Emergency Evacuation Ramp Detailed Design | 15/08/2020 | 13/09/2020 | 15/08/2020 | 01/03/2021 | 0 | TK_Complete | -824745350 | 288 | -824745350_288
MML3RSTPRO7464 | TT_Task | PROC Emergency Evacuation Ramp Long lead time items procurement | 15/08/2020 | 13/09/2020 | 15/08/2020 | 05/02/2021 | 0 | TK_Complete | -824745350 | 288 | -824745350_288
MML3RSTPRO7465 | TT_Task | PROC Emergency Evacuation Ramp Manufacturing | 25/02/2021 | 28/02/2021 | 06/02/2021 | 15/03/2021 | 0 | TK_Complete | -824745350 | 288 | -824745350_288
MML3RSTPRO7470 | TT_Task | PROC Emergency Evacuation Ramp - FAI/ FAT | 25/04/2021 | 27/04/2021 | 06/04/2021 | 07/04/2021 | 0 | TK_Complete | -824745350 | 288 | -824745350_288
MML3RSTPRO7471 | TT_Task | PROC Emergency Evacuation Ramp NONO/ NOWC from Project Manager | 28/04/2021 | 28/04/2021 | 07/04/2021 | 07/04/2021 | 0 | TK_Complete | -824745350 | 288 | -824745350_288
MML3RSTPRO7480 | TT_Task | PROC Emergency Evacuation Ramp - Packing ; Transportation from Supplier works to Alstom Factory | 29/04/2021 | 02/05/2021 | 01/04/2021 | 10/04/2021 | 0 | TK_Complete | -824745350 | 288 | -824745350_288
MML3RSTPRO7550 | TT_Task | PROC Primary Suspension(Primary Spring) - Technical CBC discussion/ closure | 08/08/2019 | 22/08/2019 | 17/01/2019 | 22/08/2019 | 0 | TK_Complete | -824745350 | 331 | -824745350_331
MML3RSTPRO7551 | TT_Task | PROC Primary Suspension(Primary Spring) - Commercial closure ; PO Release | 23/08/2019 | 05/09/2019 | 23/08/2019 | 05/09/2019 | 0 | TK_Complete | -824745350 | 331 | -824745350_331
MML3RSTPRO7552 | TT_Task | PROC Primary Suspension(Primary Spring) TRS freeze ; Conceptual design | 06/09/2019 | 10/10/2019 | 06/09/2019 | 10/10/2019 | 0 | TK_Complete | -824745350 | 332 | -824745350_332
MML3RSTPRO7553 | TT_Task | PROC Primary Suspension(Primary Spring) Detailed Design | 11/10/2019 | 14/11/2019 | 11/10/2019 | 14/10/2019 | 0 | TK_Complete | -824745350 | 333 | -824745350_333
MML3RSTPRO7554 | TT_Task | PROC Primary Suspension(Primary Spring) Long lead time items procurement | 11/10/2019 | 04/12/2019 | 11/10/2019 | 24/10/2019 | 0 | TK_Complete | -824745350 | 334 | -824745350_334
MML3RSTPRO7555 | TT_Task | PROC Primary Suspension(Primary Spring) Manufacturing | 05/12/2019 | 08/01/2020 | 25/10/2019 | 25/12/2019 | 0 | TK_Complete | -824745350 | 333 | -824745350_333
MML3RSTPRO7560 | TT_Task | PROC Primary Suspension(Primary Spring) - FAI/ FAT | 25/02/2022 | 25/02/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 333 | -824745350_333
MML3RSTPRO7561 | TT_Task | PROC Primary Suspension(Primary Spring) NONO/ NOWC from Project Manager | 26/02/2022 | 26/02/2022 | nan | nan | 304 | TK_NotStart | -824745350 | 290 | -824745350_290
MML3RSTPRO7570 | TT_Task | PROC Primary Suspension(Primary Spring) - Packing ; Transportation from Supplier works to Alstom Factory | 05/05/2020 | 27/07/2020 | 05/05/2020 | 27/07/2020 | 0 | TK_Complete | -824745350 | 289 | -824745350_289
MML3RSTPRO7640 | TT_Task | PROC Wheel Flange Lubricators - Technical CBC discussion/ closure | 09/08/2019 | 23/08/2019 | 12/07/2019 | 05/11/2019 | 0 | TK_Complete | -824745350 | 291 | -824745350_291
MML3RSTPRO7641 | TT_Task | PROC Wheel Flange Lubricators - Commercial closure ; PO Release | 23/11/2019 | 06/12/2019 | 06/11/2019 | 20/01/2020 | 0 | TK_Complete | -824745350 | 291 | -824745350_291
MML3RSTPRO7642 | TT_Task | PROC Wheel Flange Lubricators TRS freeze ; Conceptual design | 25/01/2020 | 14/02/2020 | 21/01/2019 | 31/03/2020 | 0 | TK_Complete | -824745350 | 291 | -824745350_291
MML3RSTPRO7643 | TT_Task | PROC Wheel Flange Lubricators Detailed Design | 09/01/2020 | 11/06/2020 | 01/04/2020 | 11/06/2020 | 0 | TK_Complete | -824745350 | 291 | -824745350_291
MML3RSTPRO7644 | TT_Task | PROC Wheel Flange Lubricators Long lead time items procurement | 12/06/2020 | 13/07/2020 | 12/06/2020 | 13/07/2020 | 0 | TK_Complete | -824745350 | 291 | -824745350_291
MML3RSTPRO7645 | TT_Task | PROC Wheel Flange Lubricators Manufacturing | 14/07/2020 | 25/09/2020 | 14/07/2020 | 23/09/2020 | 0 | TK_Complete | -824745350 | 291 | -824745350_291
MML3RSTPRO7650 | TT_Task | PROC Wheel Flange Lubricators - FAI/ FAT | 25/01/2021 | 25/01/2021 | 11/01/2021 | 11/01/2021 | 0 | TK_Complete | -824745350 | 291 | -824745350_291
MML3RSTPRO7651 | TT_Task | PROC Wheel Flange Lubricators NONO/ NOWC from Project Manager | 25/01/2021 | 25/01/2021 | 11/01/2021 | 11/01/2021 | 0 | TK_Complete | -824745350 | 291 | -824745350_291
MML3RSTPRO7660 | TT_Task | PROC Wheel Flange Lubricators - Packing ; Transportation from Supplier works to Alstom Factory | 25/12/2020 | 31/12/2020 | 12/11/2020 | 12/11/2020 | 0 | TK_Complete | -824745350 | 291 | -824745350_291
MML3RSTPRO7730 | TT_Task | PROC Obstacle Detector ; Deflector - Technical CBC discussion/ closure | 07/08/2019 | 21/08/2019 | 06/06/2019 | 23/08/2019 | 0 | TK_Complete | -824745350 | 292 | -824745350_292
MML3RSTPRO7731 | TT_Task | PROC Obstacle Detector ; Deflector - Commercial closure ; PO Release | 24/02/2020 | 08/03/2020 | 24/08/2019 | 10/03/2020 | 0 | TK_Complete | -824745350 | 292 | -824745350_292
MML3RSTPRO7732 | TT_Task | PROC Obstacle Detector ; Deflector TRS freeze ; Conceptual design | 09/01/2020 | 20/08/2020 | 11/03/2020 | 20/08/2020 | 0 | TK_Complete | -824745350 | 292 | -824745350_292
MML3RSTPRO7733 | TT_Task | PROC Obstacle Detector ; Deflector Detailed Design | 21/08/2020 | 10/09/2020 | 21/08/2020 | 10/09/2020 | 0 | TK_Complete | -824745350 | 292 | -824745350_292
MML3RSTPRO7734 | TT_Task | PROC Obstacle Detector ; Deflector Long lead time items procurement | 11/09/2020 | 24/09/2020 | 11/09/2020 | 24/09/2020 | 0 | TK_Complete | -824745350 | 318 | -824745350_318
MML3RSTPRO7735 | TT_Task | PROC Obstacle Detector ; Deflector Manufacturing | 25/09/2020 | 31/10/2020 | 25/09/2020 | 23/11/2020 | 0 | TK_Complete | -824745350 | 292 | -824745350_292
MML3RSTPRO7740 | TT_Task | PROC Obstacle Detector ; Deflector - FAI/ FAT | 25/01/2021 | 05/02/2021 | 05/01/2021 | 05/01/2021 | 0 | TK_Complete | -824745350 | 292 | -824745350_292
MML3RSTPRO7745 | TT_Task | PROC Obstacle Detector ; Deflector NONO/ NOWC from Project Manager | 25/01/2021 | 25/01/2021 | 05/01/2021 | 05/01/2021 | 0 | TK_Complete | -824745350 | 292 | -824745350_292
MML3RSTPRO7750 | TT_Task | PROC Obstacle Detector ; Deflector - Packing ; Transportation from Supplier works to Alstom Factory | 25/12/2020 | 03/01/2021 | 18/12/2020 | 09/01/2021 | 0 | TK_Complete | -824745350 | 292 | -824745350_292
MML3RSTPRO1835 | TT_Task | PROC Consultation ; PO release: Long Lead part Electrical equipments(Contactors,Relays,MCB,Switches,Cables;Glands) | 11/11/2019 | 09/01/2020 | 12/08/2019 | 16/10/2019 | 0 | TK_Complete | -824745350 | 335 | -824745350_335
MML3RSTPRO1840 | TT_Task | PROC Procurement of Long Lead part Electrical equipments(Contactors,Relays,MCB,Switches,Cables;Glands) | 17/10/2019 | 23/04/2020 | 17/10/2019 | 23/04/2020 | 0 | TK_Complete | -824745350 | 335 | -824745350_335
MML3RSTPRO1845 | TT_Task | PROC Packing ; transportation of Long Lead part Electrical equipments(Contactors,Relays,MCB,Switches,Cables;Glands) | 24/04/2020 | 07/05/2020 | 24/04/2020 | 07/05/2020 | 0 | TK_Complete | -824745350 | 335 | -824745350_335
MML3RSTPRO1850 | TT_Task | PROC Procurement of Cubicles | 29/01/2020 | 08/09/2020 | 29/01/2020 | 08/09/2020 | 0 | TK_Complete | -824745350 | 336 | -824745350_336
MML3RSTPRO1860 | TT_Task | PROC Procurement of Driver Desk | 23/11/2020 | 23/11/2020 | 23/11/2020 | 23/11/2020 | 0 | TK_Complete | -824745350 | 336 | -824745350_336
MML3RSTPRO1870 | TT_Task | MFG CJB Industrialisation activities for Looming | 17/02/2020 | 01/03/2020 | 17/02/2020 | 01/09/2020 | 0 | TK_Complete | -824745350 | 337 | -824745350_337
MML3RSTPRO1880 | TT_Task | MFG Loomboard Configuration ; Looms Manufacturing | 28/07/2020 | 03/09/2020 | 02/09/2020 | 05/10/2020 | 0 | TK_Complete | -824745350 | 338 | -824745350_338
MML3RSTPRO1890 | TT_Task | MFG Looms: FAI/ FAT | 25/02/2022 | 25/02/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 339 | -824745350_339
MML3RSTPRO1900 | TT_Task | MFG Looms: Packing ; Transport from Coimbatore to Sricity | 17/09/2020 | 19/09/2020 | 17/09/2020 | 09/10/2020 | 0 | TK_Complete | -824745350 | 340 | -824745350_340
MML3RSTPRO1910 | TT_Task | MFG CJB Industrialisation activities for Cabinets, Driver desk, Jumper cables | 16/07/2020 | 22/07/2020 | 16/07/2020 | 20/10/2020 | 0 | TK_Complete | -824745350 | 337 | -824745350_337
MML3RSTPRO1920 | TT_Task | MFG Cabinets / Electric Panels: Manufacturing ; Assembly | 05/08/2020 | 23/08/2020 | 05/08/2020 | 19/11/2020 | 0 | TK_Complete | -824745350 | 341 | -824745350_341
MML3RSTPRO1930 | TT_Task | MFG Cabinets / Electric Panels: FAI/ FAT | 25/02/2022 | 28/02/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 341 | -824745350_341
MML3RSTPRO1935 | TT_Task | MFG Cabinets / Electric Panels: NONO/ NOWC from Project Manager | 01/03/2022 | 01/03/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 341 | -824745350_341
MML3RSTPRO1940 | TT_Task | MFG Cabinets / Electric Panels: Packing ; Transport from Coimbatore to Sricity | 26/09/2020 | 28/09/2020 | 26/09/2020 | 24/11/2020 | 0 | TK_Complete | -824745350 | 340 | -824745350_340
MML3RSTPRO1950 | TT_Task | MFG Driver Desk: Manufacturing | 01/08/2020 | 01/08/2020 | 01/08/2020 | 15/12/2020 | 0 | TK_Complete | -824745350 | 342 | -824745350_342
MML3RSTPRO1960 | TT_Task | MFG Driver Desk: FAI/ FAT | 12/07/2021 | 12/07/2021 | 12/07/2021 | 12/07/2021 | 0 | TK_Complete | -824745350 | 342 | -824745350_342
MML3RSTPRO1970 | TT_Task | MFG Driver Desk: Packing ; Transport from CJB to SCY | 29/12/2020 | 31/12/2020 | 20/08/2020 | 24/12/2020 | 0 | TK_Complete | -824745350 | 342 | -824745350_342
MML3RSTPRO8210 | TT_Task | PROC Bogie and Related Material - Technical CBC discussion/ closure | 30/07/2019 | 13/08/2019 | 24/05/2019 | 09/08/2019 | 0 | TK_Complete | -824745350 | 319 | -824745350_319
MML3RSTPRO8220 | TT_Task | PROC Bogie and Related Material - Commercial closure ; PO Release | 14/08/2019 | 27/08/2019 | 10/08/2019 | 30/08/2019 | 0 | TK_Complete | -824745350 | 319 | -824745350_319
MML3RSTPRO8230 | TT_Task | PROC Bogie and Related Material TRS freeze ; Conceptual design | 28/08/2019 | 11/10/2019 | 31/08/2019 | 11/10/2019 | 0 | TK_Complete | -824745350 | 313 | -824745350_313
MML3RSTPRO8240 | TT_Task | PROC Bogie and Related Material Detailed Design | 12/10/2019 | 02/07/2020 | 12/10/2019 | 15/10/2019 | 0 | TK_Complete | -824745350 | 320 | -824745350_320
MML3RSTPRO8250 | TT_Task | PROC Bogie and Related Material Long lead time items procurement | 12/10/2019 | 13/07/2020 | 12/10/2019 | 13/11/2019 | 0 | TK_Complete | -824745350 | 318 | -824745350_318
MML3RSTPRO8260 | TT_Task | PROC Bogie and Related Material Manufacturing | 14/07/2020 | 15/08/2020 | 14/11/2019 | 26/12/2019 | 0 | TK_Complete | -824745350 | 320 | -824745350_320
MML3RSTPRO8280 | TT_Task | PROC Bogie and Related Material NONO/ NOWC from Project Manager | 02/11/2020 | 02/11/2020 | 02/11/2020 | 02/11/2020 | 0 | TK_Complete | -824745350 | 296 | -824745350_296
MML3RSTPRO8290 | TT_Task | PROC Bogie and Related Material - Packing ; Transportation from Supplier works to Alstom Factory | 06/03/2020 | 15/03/2020 | 06/03/2020 | 02/11/2020 | 0 | TK_Complete | -824745350 | 303 | -824745350_303
MML3RSTPRO8390 | TT_Task | PROC Grab Poles, Hand Rails, Grab handles etc.. - Technical CBC discussion/ closure | 29/08/2019 | 27/09/2019 | 04/10/2019 | 15/03/2020 | 0 | TK_Complete | -824745350 | 299 | -824745350_299
MML3RSTPRO8400 | TT_Task | PROC Grab Poles, Hand Rails, Grab handles etc.. - Commercial closure ; PO Release | 28/09/2019 | 07/10/2019 | 28/09/2019 | 07/10/2019 | 0 | TK_Complete | -824745350 | 299 | -824745350_299
MML3RSTPRO8410 | TT_Task | PROC Grab Poles, Hand Rails, Grab handles etc.. TRS freeze ; Conceptual design | 08/10/2019 | 10/06/2020 | 08/10/2019 | 10/06/2020 | 0 | TK_Complete | -824745350 | 299 | -824745350_299
MML3RSTPRO8420 | TT_Task | PROC Grab Poles, Hand Rails, Grab handles etc... Detailed Design | 11/07/2020 | 20/08/2020 | 11/07/2020 | 20/08/2020 | 0 | TK_Complete | -824745350 | 299 | -824745350_299
MML3RSTPRO8430 | TT_Task | PROC Grab Poles, Hand Rails, Grab handles etc... Long lead time items procurement | 21/08/2020 | 10/09/2020 | 21/08/2020 | 10/09/2020 | 0 | TK_Complete | -824745350 | 299 | -824745350_299
MML3RSTPRO8440 | TT_Task | PROC Grab Poles, Hand Rails, Grab handles etc... Manufacturing | 11/09/2020 | 29/09/2020 | 11/09/2020 | 23/12/2020 | 0 | TK_Complete | -824745350 | 299 | -824745350_299
MML3RSTPRO8450 | TT_Task | PROC Grab Poles, Hand Rails, Grab handles etc... NONO/ NOWC from Project Manager | 14/06/2021 | 14/06/2021 | 14/06/2021 | 14/06/2021 | 0 | TK_Complete | -824745350 | 299 | -824745350_299
MML3RSTPRO8460 | TT_Task | PROC Grab Poles, Hand Rails, Grab handles etc.. - Packing ; Transportation from Supplier works to Alstom Factory | 02/11/2020 | 11/11/2020 | 02/11/2020 | 10/04/2021 | 0 | TK_Complete | -824745350 | 299 | -824745350_299
MML3RSTPRO8470 | TT_Task | PROC Driver seat - Technical CBC discussion/ closure | 25/01/2020 | 30/01/2020 | 17/01/2019 | 26/08/2019 | 0 | TK_Complete | -824745350 | 307 | -824745350_307
MML3RSTPRO8480 | TT_Task | PROC Driver seat - Commercial closure ; PO Release | 02/02/2020 | 15/02/2020 | 27/08/2019 | 26/08/2020 | 0 | TK_Complete | -824745350 | 308 | -824745350_308
MML3RSTPRO8490 | TT_Task | PROC Driver seat TRS freeze ; Conceptual design | 10/02/2020 | 23/02/2020 | 27/08/2020 | 28/08/2020 | 0 | TK_Complete | -824745350 | 309 | -824745350_309
MML3RSTPRO8500 | TT_Task | PROC Driver seat Detailed Design | 09/01/2020 | 04/08/2020 | 29/08/2020 | 01/09/2020 | 0 | TK_Complete | -824745350 | 327 | -824745350_327
MML3RSTPRO8510 | TT_Task | PROC Driver seat Long lead time items procurement | 05/08/2020 | 19/08/2020 | 01/09/2020 | 03/10/2020 | 0 | TK_Complete | -824745350 | 306 | -824745350_306
MML3RSTPRO8520 | TT_Task | PROC Driver seat Manufacturing | 04/10/2020 | 12/11/2020 | 04/10/2020 | 12/11/2020 | 0 | TK_Complete | -824745350 | 327 | -824745350_327
MML3RSTPRO8530 | TT_Task | PROC Driver seat NONO/ NOWC from Project Manager | 25/02/2022 | 25/02/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 283 | -824745350_283
MML3RSTPRO8540 | TT_Task | PROC Driver seat - Packing ; Transportation from Supplier works to Alstom Factory | 25/12/2020 | 03/01/2021 | 03/12/2020 | 03/12/2020 | 0 | TK_Complete | -824745350 | 282 | -824745350_282
MML3RSTPRO8550 | TT_Task | PROC Signages - Technical CBC discussion/ closure | 25/01/2020 | 07/02/2020 | 08/08/2019 | 17/10/2019 | 0 | TK_Complete | -824745350 | 343 | -824745350_343
MML3RSTPRO8560 | TT_Task | PROC Signages - Commercial closure ; PO Release | 25/07/2020 | 08/08/2020 | 25/07/2020 | 08/08/2020 | 0 | TK_Complete | -824745350 | 343 | -824745350_343
MML3RSTPRO8570 | TT_Task | PROC Signages TRS freeze ; Conceptual design | 10/08/2020 | 23/08/2020 | 10/08/2020 | 23/08/2020 | 0 | TK_Complete | -824745350 | 343 | -824745350_343
MML3RSTPRO8580 | TT_Task | PROC Signages Detailed Design | 24/08/2020 | 17/09/2020 | 24/08/2020 | 17/09/2020 | 0 | TK_Complete | -824745350 | 343 | -824745350_343
MML3RSTPRO8590 | TT_Task | PROC Signages Long lead time items procurement | 18/09/2020 | 02/10/2020 | 18/09/2020 | 06/02/2021 | 0 | TK_Complete | -824745350 | 318 | -824745350_318
MML3RSTPRO8600 | TT_Task | PROC Signages Manufacturing | 13/03/2021 | 23/03/2021 | 07/02/2021 | nan | 0 | TK_Active | -824745350 | 343 | -824745350_343
MML3RSTPRO8620 | TT_Task | PROC Signages NONO/ NOWC from Project Manager | 25/02/2022 | 25/02/2022 | nan | nan | 368 | TK_NotStart | -824745350 | 269 | -824745350_269
MML3RSTPRO8630 | TT_Task | PROC Signages - Packing ; Transportation from Supplier works to Alstom Factory | 25/02/2022 | 25/02/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 276 | -824745350_276
MML3RSTPRO8640 | TT_Task | PROC Lighting System - Technical CBC discussion/ closure | 28/08/2020 | 28/08/2020 | 28/08/2020 | 28/08/2020 | 0 | TK_Complete | -824745350 | 344 | -824745350_344
MML3RSTPRO8650 | TT_Task | PROC Lighting System - Commercial closure | 29/08/2020 | 30/09/2020 | 29/08/2020 | 30/10/2020 | 0 | TK_Complete | -824745350 | 344 | -824745350_344
MML3RSTPRO8660 | TT_Task | PROC Lighting System PO release | 31/10/2020 | 06/11/2020 | 31/10/2020 | 10/11/2020 | 0 | TK_Complete | -824745350 | 345 | -824745350_345
MML3RSTPRO8690 | TT_Task | PROC Lighting System Procurement of Parts | 25/11/2020 | 03/12/2020 | 25/11/2020 | 12/02/2021 | 0 | TK_Complete | -824745350 | 344 | -824745350_344
MML3RSTPRO8710 | TT_Task | PROC Lighting System NONO/ NOWC from Project Manager | 22/07/2021 | 22/07/2021 | 22/07/2021 | 22/07/2021 | 0 | TK_Complete | -824745350 | 81 | -824745350_81
MML3RSTPRO8720 | TT_Task | PROC Lighting System- Packing ; Transportation from Supplier works to Alstom Factory | 03/01/2021 | 12/01/2021 | 04/12/2020 | 19/01/2021 | 0 | TK_Complete | -824745350 | 344 | -824745350_344
MML3RSTPRO1080 | TT_Task | PROC Gangway - Technical CBC discussion/closure | 27/05/2019 | 14/08/2019 | 18/12/2018 | 31/05/2019 | 0 | TK_Complete | -824745350 | 346 | -824745350_346
MML3RSTPRO1085 | TT_Task | PROC Gangway - Commercial closure ; PO Release | 15/08/2019 | 28/08/2019 | 01/04/2019 | 22/08/2019 | 0 | TK_Complete | -824745350 | 346 | -824745350_346
MML3RSTPRO1090 | TT_Task | PROC Gangway TRS freeze ; Conceptual design | 29/08/2019 | 11/10/2019 | 23/08/2019 | 11/10/2019 | 0 | TK_Complete | -824745350 | 346 | -824745350_346
MML3RSTPRO1091 | TT_Task | PROC Gangway Detailed Design | 12/10/2019 | 21/11/2019 | 12/10/2019 | 21/11/2019 | 0 | TK_Complete | -824745350 | 346 | -824745350_346
MML3RSTPRO1092 | TT_Task | PROC Gangway Long lead time items procurement | 22/11/2019 | 12/08/2020 | 22/11/2019 | 12/08/2020 | 0 | TK_Complete | -824745350 | 318 | -824745350_318
MML3RSTPRO1093 | TT_Task | PROC Gangway Manufacturing | 13/08/2020 | 11/09/2020 | 13/08/2020 | 12/11/2020 | 0 | TK_Complete | -824745350 | 346 | -824745350_346
MML3RSTPRO1100 | TT_Task | PROC Gangway - FAI/ FAT | 26/11/2021 | 26/11/2021 | 26/11/2021 | 26/11/2021 | 0 | TK_Complete | -824745350 | 317 | -824745350_317
MML3RSTPRO1105 | TT_Task | PROC Gangway - NONO/ NOWC from Project Manager | 25/11/2021 | 25/11/2021 | 25/11/2021 | 25/11/2021 | 0 | TK_Complete | -824745350 | 269 | -824745350_269
MML3RSTPRO1110 | TT_Task | PROC Gangway - Packing ; Transportation from Supplier works to Alstom Factory | 25/12/2020 | 03/01/2021 | 26/11/2020 | 20/12/2020 | 0 | TK_Complete | -824745350 | 276 | -824745350_276
MML3RSTPRO8730 | TT_Task | PROC Depot Server for CCTV,Arc Measuring Device, Power Quality Measuring Device - Technical CBC discussion/ closure | 02/09/2019 | 01/10/2019 | 02/09/2019 | nan | 0 | TK_Active | -824745350 | 347 | -824745350_347
MML3RSTPRO8740 | TT_Task | PROC Depot Server for CCTV,Arc Measuring Device, Power Quality Measuring Device - Commercial closure | 17/03/2022 | 23/03/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 347 | -824745350_347
MML3RSTPRO8750 | TT_Task | PROC Depot Server for CCTV,Arc Measuring Device, Power Quality Measuring Device PO Release | 24/03/2022 | 30/03/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 347 | -824745350_347
MML3RSTPRO8780 | TT_Task | PROC Depot Server for CCTV,Arc Measuring Device, Power Quality Measuring Device Procurement of Items | 31/03/2022 | 28/07/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 347 | -824745350_347
MML3RSTPRO8790 | TT_Task | PROC Depot Server for CCTV,Arc Measuring Device, Power Quality Measuring Device NONO/ NOWC from Project Manager | 29/07/2022 | 29/07/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 347 | -824745350_347
MML3RSTPRO8800 | TT_Task | PROC Depot Server for CCTV, Arc Measuring Device, PQM- Packing ; Transportation from Supplier works to Alstom Factory | 30/07/2022 | 18/08/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 347 | -824745350_347
MML3RSTPRO1300 | TT_Task | PROC VAC Technical CBC discussion/ closure | 07/07/2019 | 24/09/2019 | 26/11/2018 | 10/04/2019 | 0 | TK_Complete | -824745350 | 311 | -824745350_311
MML3RSTPRO1305 | TT_Task | PROC VAC Commercial closure ; PO Release | 25/09/2019 | 08/10/2019 | 11/04/2019 | 19/06/2019 | 0 | TK_Complete | -824745350 | 312 | -824745350_312
MML3RSTPRO1310 | TT_Task | PROC VAC TRS freeze ; Conceptual design | 09/10/2019 | 24/10/2019 | 09/10/2019 | 24/10/2019 | 0 | TK_Complete | -824745350 | 313 | -824745350_313
MML3RSTPRO1311 | TT_Task | PROC VAC Detailed Design | 25/10/2019 | 13/11/2019 | 25/10/2019 | 13/11/2019 | 0 | TK_Complete | -824745350 | 348 | -824745350_348
MML3RSTPRO1312 | TT_Task | PROC VAC Long lead time items procurement | 25/01/2020 | 23/02/2020 | 14/11/2019 | 01/01/2020 | 0 | TK_Complete | -824745350 | 318 | -824745350_318
MML3RSTPRO1313 | TT_Task | PROC VAC Manufacturing | 02/01/2020 | 11/06/2020 | 02/01/2020 | 11/06/2020 | 0 | TK_Complete | -824745350 | 348 | -824745350_348
MML3RSTPRO1320 | TT_Task | PROC VAC FAI/ FAT | 25/02/2022 | 25/02/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 317 | -824745350_317
MML3RSTPRO1325 | TT_Task | PROC VAC NONO/ NOWC from Project Manager | 26/02/2022 | 26/02/2022 | nan | nan | 360 | TK_NotStart | -824745350 | 141 | -824745350_141
MML3RSTPRO1330 | TT_Task | PROC VAC Packing ; Transportation from Supplier works to Alstom Factory | 24/07/2020 | 28/09/2020 | 24/07/2020 | 28/09/2020 | 0 | TK_Complete | -824745350 | 303 | -824745350_303
MML3RSTPRO1460 | TT_Task | PROC Communication System - Technical CBC discussion/closure | 06/08/2019 | 14/10/2019 | 25/11/2018 | 27/02/2019 | 0 | TK_Complete | -824745350 | 311 | -824745350_311
MML3RSTPRO1465 | TT_Task | PROC Communication System - Commercial closure ; PO Release | 30/03/2020 | 08/04/2020 | 28/02/2019 | 23/08/2019 | 0 | TK_Complete | -824745350 | 312 | -824745350_312
MML3RSTPRO1470 | TT_Task | PROC Communication System TRS freeze ; Conceptual design | 09/04/2020 | 18/04/2020 | 24/08/2019 | 24/10/2019 | 0 | TK_Complete | -824745350 | 324 | -824745350_324
MML3RSTPRO1471 | TT_Task | PROC Communication System Detailed Design | 19/04/2020 | 18/05/2020 | 25/10/2019 | 22/01/2020 | 0 | TK_Complete | -824745350 | 349 | -824745350_349
MML3RSTPRO1472 | TT_Task | PROC Communication System Long lead time items procurement | 25/10/2019 | 23/09/2020 | 25/10/2019 | 08/09/2020 | 0 | TK_Complete | -824745350 | 318 | -824745350_318
MML3RSTPRO1473 | TT_Task | PROC Communication System Manufacturing | 09/09/2020 | 13/10/2020 | 09/09/2020 | 10/02/2021 | 0 | TK_Complete | -824745350 | 349 | -824745350_349
MML3RSTPRO1480 | TT_Task | PROC Communication System - FAI/ FAT | 25/02/2022 | 25/02/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 326 | -824745350_326
MML3RSTPRO1482 | TT_Task | PROC Communication System -NONO/ NOWC from Project Manager | 26/02/2022 | 26/02/2022 | nan | nan | 360 | TK_NotStart | -824745350 | 81 | -824745350_81
MML3RSTPRO1490 | TT_Task | PROC Communication System - Packing ; Transportation from Supplier works to Alstom Factory | 13/10/2020 | 21/10/2020 | 13/10/2020 | 21/10/2020 | 0 | TK_Complete | -824745350 | 303 | -824745350_303
MML3RSTPRO1500 | TT_Task | PROC Vacuum Circuit Breaker - Technical CBC discussion/closure | 27/06/2019 | 24/09/2019 | 27/06/2019 | 24/09/2019 | 0 | TK_Complete | -824745350 | 270 | -824745350_270
MML3RSTPRO1505 | TT_Task | PROC Vacuum Circuit Breaker - Commercial closure ; PO Release | 25/09/2019 | 08/10/2019 | 25/09/2019 | 08/10/2019 | 0 | TK_Complete | -824745350 | 270 | -824745350_270
MML3RSTPRO1510 | TT_Task | PROC Vacuum Circuit breaker TRS freeze ; Conceptual design | 09/10/2019 | 15/04/2020 | 09/10/2019 | 15/04/2020 | 0 | TK_Complete | -824745350 | 270 | -824745350_270
MML3RSTPRO1511 | TT_Task | PROC Vacuum Circuit breaker Detailed Design | 16/04/2020 | 25/07/2020 | 16/04/2020 | 25/07/2020 | 0 | TK_Complete | -824745350 | 270 | -824745350_270
MML3RSTPRO1512 | TT_Task | PROC Vacuum Circuit breaker Long lead time items procurement | 16/04/2020 | 25/08/2020 | 16/04/2020 | 25/08/2020 | 0 | TK_Complete | -824745350 | 314 | -824745350_314
MML3RSTPRO1513 | TT_Task | PROC Vacuum Circuit breaker Manufacturing | 26/08/2020 | 14/09/2020 | 26/08/2020 | 10/09/2020 | 0 | TK_Complete | -824745350 | 270 | -824745350_270
MML3RSTPRO1520 | TT_Task | PROC Vacuum Circuit Breaker - FAI/ FAT | 25/02/2022 | 26/02/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 270 | -824745350_270
MML3RSTPRO1525 | TT_Task | PROC Vacuum Circuit Breaker - NONO/ NOWC from Project Manager | 27/02/2022 | 27/02/2022 | nan | nan | 472 | TK_NotStart | -824745350 | 183 | -824745350_183
MML3RSTPRO1530 | TT_Task | PROC Vacuum Circuit Breaker - Packing ; Transportation from Supplier works to Alstom Factory | 24/07/2020 | 25/09/2020 | 24/07/2020 | 25/09/2020 | 0 | TK_Complete | -824745350 | 270 | -824745350_270
MML3RSTPRO1540 | TT_Task | PROC Gear Box and Coupling - Technical CBC discussion/closure | 23/05/2019 | 20/08/2019 | 30/10/2018 | 21/01/2019 | 0 | TK_Complete | -824745350 | 271 | -824745350_271
MML3RSTPRO1545 | TT_Task | PROC Gear Box and Coupling - Commercial closure ; PO Release | 21/08/2019 | 03/09/2019 | 22/01/2019 | 14/03/2019 | 0 | TK_Complete | -824745350 | 271 | -824745350_271
MML3RSTPRO1550 | TT_Task | PROC Gear Box and Coupling TRS freeze ; Conceptual design | 04/09/2019 | 18/10/2019 | 15/03/2019 | 24/09/2019 | 0 | TK_Complete | -824745350 | 313 | -824745350_313
MML3RSTPRO1551 | TT_Task | PROC Gear Box and Coupling Detailed Design | 25/09/2019 | 30/09/2019 | 25/09/2019 | 30/09/2019 | 0 | TK_Complete | -824745350 | 271 | -824745350_271
MML3RSTPRO1552 | TT_Task | PROC Gear Box and Coupling Long lead time items procurement | 25/09/2019 | 29/10/2019 | 25/09/2019 | 29/10/2019 | 0 | TK_Complete | -824745350 | 318 | -824745350_318
MML3RSTPRO1553 | TT_Task | PROC Gear Box and Coupling Manufacturing | 30/10/2019 | 13/12/2019 | 30/10/2019 | 02/04/2020 | 0 | TK_Complete | -824745350 | 271 | -824745350_271
MML3RSTPRO1560 | TT_Task | PROC Gear Box and Coupling - FAI/ FAT | 25/02/2022 | 25/02/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 271 | -824745350_271
MML3RSTPRO1562 | TT_Task | PROC Gear Box and Coupling - NONO/ NOWC from Project Manager | 26/02/2022 | 26/02/2022 | nan | nan | 304 | TK_NotStart | -824745350 | 271 | -824745350_271
MML3RSTPRO1570 | TT_Task | PROC Gear Box and Coupling - Packing ; Transportation from Supplier works to Alstom Factory | 04/03/2020 | 22/10/2020 | 04/03/2020 | 22/10/2020 | 0 | TK_Complete | -824745350 | 271 | -824745350_271
MML3RSTPRO1620 | TT_Task | PROC Axles and axle roller Bearings - Technical CBC discussion/closure | 17/05/2019 | 03/09/2019 | 24/01/2019 | 28/05/2019 | 0 | TK_Complete | -824745350 | 295 | -824745350_295
MML3RSTPRO1625 | TT_Task | PROC Axles and axle roller Bearings - Commercial closure ; PO Release | 04/09/2019 | 17/09/2019 | 29/05/2019 | 14/06/2019 | 0 | TK_Complete | -824745350 | 295 | -824745350_295
MML3RSTPRO1630 | TT_Task | PROC Axles and axle roller Bearings TRS freeze ; Conceptual design | 18/09/2019 | 07/10/2019 | 15/06/2019 | 07/10/2019 | 0 | TK_Complete | -824745350 | 305 | -824745350_305
MML3RSTPRO1631 | TT_Task | PROC Axles and axle roller Bearings Detailed Design | 08/10/2019 | 09/11/2019 | 08/10/2019 | 09/11/2019 | 0 | TK_Complete | -824745350 | 295 | -824745350_295
MML3RSTPRO1632 | TT_Task | PROC Axles and axle roller Bearings Long lead time items procurement | 08/10/2019 | 26/11/2019 | 08/10/2019 | 23/01/2020 | 0 | TK_Complete | -824745350 | 314 | -824745350_314
MML3RSTPRO1633 | TT_Task | PROC Axles and axle roller Bearings Manufacturing | 24/01/2020 | 18/06/2020 | 24/01/2020 | 17/06/2020 | 0 | TK_Complete | -824745350 | 295 | -824745350_295
MML3RSTPRO1640 | TT_Task | PROC Axles and axle roller Bearings - FAI/ FAT | 25/02/2022 | 25/02/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 295 | -824745350_295
MML3RSTPRO1642 | TT_Task | PROC Axles and axle roller Bearings - NONO/ NOWC from Project Manager | 26/02/2022 | 26/02/2022 | nan | nan | 304 | TK_NotStart | -824745350 | 295 | -824745350_295
MML3RSTPRO1650 | TT_Task | PROC Axles and axle roller Bearings - Packing ; Transportation from Supplier works to Alstom Factory | 08/04/2020 | 22/08/2020 | 08/04/2020 | 22/08/2020 | 0 | TK_Complete | -824745350 | 272 | -824745350_272
MML3RSTPRO1120 | TT_Task | PROC Front Detrainment Door Technical CBC discussion/closure | 09/10/2019 | 28/10/2019 | 06/02/2019 | 24/06/2019 | 0 | TK_Complete | -824745350 | 307 | -824745350_307
MML3RSTPRO1125 | TT_Task | PROC Front Detrainment Door Commercial closure ; PO Release | 25/01/2020 | 08/02/2020 | 25/06/2019 | 18/08/2019 | 0 | TK_Complete | -824745350 | 308 | -824745350_308
MML3RSTPRO1130 | TT_Task | PROC Front Detrainment Door TRS freeze ; Conceptual design | 09/02/2020 | 22/02/2020 | 20/09/2019 | 16/10/2019 | 0 | TK_Complete | -824745350 | 309 | -824745350_309
MML3RSTPRO1131 | TT_Task | PROC Front Detrainment Door Detailed Design | 23/02/2020 | 17/04/2020 | 17/10/2019 | 19/12/2019 | 0 | TK_Complete | -824745350 | 310 | -824745350_310
MML3RSTPRO1132 | TT_Task | PROC Front Detrainment Door Long lead time items procurement | 17/10/2019 | 22/07/2020 | 17/10/2019 | 22/07/2020 | 0 | TK_Complete | -824745350 | 306 | -824745350_306
MML3RSTPRO1133 | TT_Task | PROC Front Detrainment Door Manufacturing | 23/07/2020 | 21/08/2020 | 23/07/2020 | 20/11/2020 | 0 | TK_Complete | -824745350 | 310 | -824745350_310
MML3RSTPRO1140 | TT_Task | PROC Front Detrainment Door FAI/ FAT | 25/02/2022 | 25/02/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 310 | -824745350_310
MML3RSTPRO1145 | TT_Task | PROC Front Detrainment Door NONO/ NOWC from Project Manager | 26/02/2022 | 26/02/2022 | nan | nan | 360 | TK_NotStart | -824745350 | 267 | -824745350_267
MML3RSTPRO1150 | TT_Task | PROC Front Detrainment Door Packing ; Transportation from Supplier works to Alstom Factory | 26/12/2020 | 02/01/2021 | 20/12/2020 | 20/12/2020 | 0 | TK_Complete | -824745350 | 266 | -824745350_266
MML3RSTPRO1740 | TT_Task | PROC Traction Motor TRS freeze ; Conceptual design | 12/08/2019 | 26/08/2019 | 01/02/2019 | 08/05/2019 | 0 | TK_Complete | -824745350 | 305 | -824745350_305
MML3RSTPRO1741 | TT_Task | PROC Traction Motor Detailed Design | 25/03/2020 | 23/05/2020 | 09/05/2019 | 15/08/2019 | 0 | TK_Complete | -824745350 | 323 | -824745350_323
MML3RSTPRO1742 | TT_Task | PROC Traction Motor Long lead time items procurement | 25/03/2020 | 23/05/2020 | 16/09/2019 | 13/11/2019 | 0 | TK_Complete | -824745350 | 314 | -824745350_314
MML3RSTPRO1743 | TT_Task | PROC Traction Motor Manufacturing | 24/05/2020 | 02/07/2020 | 14/11/2019 | 08/01/2020 | 0 | TK_Complete | -824745350 | 323 | -824745350_323
MML3RSTPRO1750 | TT_Task | PROC Traction Motor FAI/ FAT | 25/02/2022 | 26/02/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 315 | -824745350_315
MML3RSTPRO1755 | TT_Task | PROC Traction Motor NONO/ NOWC from Project Manager | 27/02/2022 | 27/02/2022 | nan | nan | 224 | TK_NotStart | -824745350 | 273 | -824745350_273
MML3RSTPRO1760 | TT_Task | PROC Traction Motor Packing ; Transportation from Supplier works to Alstom Factory | 05/07/2020 | 28/09/2020 | 05/07/2020 | 28/09/2020 | 0 | TK_Complete | -824745350 | 272 | -824745350_272
MML3RSTPRO1770 | TT_Task | PROC TCMS TRS freeze ; Conceptual design | 02/07/2019 | 20/08/2019 | 02/07/2019 | 20/08/2019 | 0 | TK_Complete | -824745350 | 324 | -824745350_324
MML3RSTPRO1771 | TT_Task | PROC TCMS Detailed Design | 21/08/2019 | 09/10/2019 | 21/08/2019 | 31/10/2019 | 0 | TK_Complete | -824745350 | 350 | -824745350_350
MML3RSTPRO1772 | TT_Task | PROC TCMS Long lead time items procurement | 21/08/2019 | 25/08/2019 | 21/08/2019 | 31/12/2019 | 0 | TK_Complete | -824745350 | 318 | -824745350_318
MML3RSTPRO1773 | TT_Task | PROC TCMS Manufacturing | 01/01/2020 | 10/09/2020 | 01/01/2020 | 07/09/2020 | 0 | TK_Complete | -824745350 | 350 | -824745350_350
MML3RSTPRO1780 | TT_Task | PROC TCMS components FAI/ FAT | 25/02/2022 | 25/02/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 350 | -824745350_350
MML3RSTPRO1785 | TT_Task | PROC TCMS components NONO/ NOWC from Project Manager | 26/02/2022 | 26/02/2022 | nan | nan | 360 | TK_NotStart | -824745350 | 269 | -824745350_269
MML3RSTPRO1790 | TT_Task | PROC TCMS Components Packing ; Transportation from Supplier works to Alstom Factory | 08/09/2020 | 08/09/2020 | 08/09/2020 | 08/09/2020 | 0 | TK_Complete | -824745350 | 303 | -824745350_303
MML3RSTPRO1200 | TT_Task | PROC Wayside Monitoring System TRS freeze | 29/08/2019 | 26/12/2019 | 29/08/2019 | 29/11/2019 | 0 | TK_Complete | -824745350 | 324 | -824745350_324
MML3RSTPRO1202 | TT_Task | PROC Wayside Monitoring System PO release | 24/02/2020 | 24/03/2020 | 02/12/2019 | nan | 0 | TK_Active | -824745350 | 345 | -824745350_345
MML3RSTPRO1203 | TT_Task | PROC Wayside Monitoring System Detailed Design | 27/03/2022 | 22/09/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 351 | -824745350_351
MML3RSTPRO1204 | TT_Task | PROC Wayside Monitoring System Long lead time items procurement | 25/02/2022 | 23/08/2022 | nan | nan | 240 | TK_NotStart | -824745350 | 318 | -824745350_318
MML3RSTPRO1205 | TT_Task | PROC Wayside Monitoring Manufacturing | 23/09/2022 | 23/09/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 351 | -824745350_351
MML3RSTPRO1210 | TT_Task | PROC Wayside Monitoring System FAI/ FAT | 23/09/2022 | 25/09/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 326 | -824745350_326
MML3RSTPRO1214 | TT_Task | PROC Wayside Monitoring System NONO/ NOWC from Project Manager | 26/09/2022 | 26/09/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 238 | -824745350_238
MML3RSTPRO1215 | TT_Task | PROC Wayside Monitoring System Packing ; Transportation from Supplier works to Depot | 27/09/2022 | 25/11/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 351 | -824745350_351
MML3RSTPRO1220 | TT_Task | PROC Wayside Monitoring System Installation, Testing ; Commissioning at Depot | 26/11/2022 | 23/02/2023 | nan | nan | 656 | TK_NotStart | -824745350 | 351 | -824745350_351
MML3RSTPRO1230 | TT_Task | PROC Train Driving Simulator TRS freeze | 02/09/2019 | 31/10/2019 | 02/09/2019 | 08/11/2019 | 0 | TK_Complete | -824745350 | 324 | -824745350_324
MML3RSTPRO1231 | TT_Task | PROC Train Driving Simulator PO release | 09/11/2019 | 07/10/2020 | 09/11/2019 | 07/10/2020 | 0 | TK_Complete | -824745350 | 297 | -824745350_297
MML3RSTPRO1232 | TT_Task | PROC Train Driving Simulator Detailed Design | 25/02/2022 | 25/04/2022 | nan | nan | 480 | TK_NotStart | -824745350 | 297 | -824745350_297
MML3RSTPRO1233 | TT_Task | PROC Train Driving Simulator Long lead time items procurement | 25/02/2022 | 24/06/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 318 | -824745350_318
MML3RSTPRO1234 | TT_Task | PROC Train Driving Simulator Manufacturing | 25/06/2022 | 22/09/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 297 | -824745350_297
MML3RSTPRO1240 | TT_Task | PROC Train Driving Simulator FAI/ FAT | 23/09/2022 | 26/09/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 326 | -824745350_326
MML3RSTPRO1242 | TT_Task | PROC Train Driving Simulator NONO/ NOWC from Project Manager | 27/09/2022 | 27/09/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 297 | -824745350_297
MML3RSTPRO1245 | TT_Task | PROC Train Driving Simulator Packing ; Transportation from Supplier works to Depot | 28/09/2022 | 26/11/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 297 | -824745350_297
MML3RSTPRO1250 | TT_Task | PROC Train Driving Simulator Installation, Testing ; Commissioning at Depot | 27/11/2022 | 25/01/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 297 | -824745350_297
MML3RSTPRO7910 | TT_Task | PROC Secondary Suspension(Air Spring) - Technical CBC discussion/ closure | 10/08/2019 | 24/08/2019 | 11/04/2019 | 22/07/2019 | 0 | TK_Complete | -824745350 | 331 | -824745350_331
MML3RSTPRO7911 | TT_Task | PROC Secondary Suspension(Air Spring) - Commercial closure ; PO Release | 25/08/2019 | 07/09/2019 | 23/07/2019 | 08/08/2019 | 0 | TK_Complete | -824745350 | 331 | -824745350_331
MML3RSTPRO7912 | TT_Task | PROC Secondary Suspension(Air Spring) TRS freeze ; Conceptual design | 08/09/2019 | 28/09/2019 | 08/09/2019 | 28/09/2019 | 0 | TK_Complete | -824745350 | 332 | -824745350_332
MML3RSTPRO7913 | TT_Task | PROC Secondary Suspension(Air Spring) Detailed Design | 29/09/2019 | 31/12/2019 | 29/09/2019 | 31/12/2019 | 0 | TK_Complete | -824745350 | 333 | -824745350_333
MML3RSTPRO7914 | TT_Task | PROC Secondary Suspension(Air Spring) Long lead time items procurement | 30/09/2019 | 01/10/2019 | 30/09/2019 | 25/12/2019 | 0 | TK_Complete | -824745350 | 334 | -824745350_334
MML3RSTPRO7915 | TT_Task | PROC Secondary Suspension(Air Spring) Manufacturing | 25/02/2020 | 10/03/2020 | 26/12/2019 | 06/04/2020 | 0 | TK_Complete | -824745350 | 333 | -824745350_333
MML3RSTPRO7920 | TT_Task | PROC Secondary Suspension(Air Spring) - FAI/ FAT | 25/02/2022 | 22/04/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 333 | -824745350_333
MML3RSTPRO7921 | TT_Task | PROC Secondary Suspension(Air Spring) - NONO/ NOWC from Project Manager | 23/04/2022 | 23/04/2022 | nan | nan | 16 | TK_NotStart | -824745350 | 290 | -824745350_290
MML3RSTPRO7930 | TT_Task | PROC Secondary Suspension(Air Spring) - Packing ; Transportation from Supplier works to Alstom Factory | 22/04/2020 | 02/11/2020 | 22/04/2020 | 02/11/2020 | 0 | TK_Complete | -824745350 | 289 | -824745350_289
MML3RSTPRO8000 | TT_Task | PROC Damper(Vertical/Lateral) - Technical CBC discussion/ closure | 08/08/2019 | 22/08/2019 | 08/08/2019 | 22/08/2019 | 0 | TK_Complete | -824745350 | 294 | -824745350_294
MML3RSTPRO8001 | TT_Task | PROC Damper(Vertical/Lateral) - Commercial closure ; PO Release | 23/08/2019 | 05/09/2019 | 23/08/2019 | 05/09/2019 | 0 | TK_Complete | -824745350 | 294 | -824745350_294
MML3RSTPRO8002 | TT_Task | PROC Damper(Vertical/Lateral) TRS freeze ; Conceptual design | 06/09/2019 | 26/09/2019 | 06/09/2019 | 26/09/2019 | 0 | TK_Complete | -824745350 | 332 | -824745350_332
MML3RSTPRO8004 | TT_Task | PROC Damper(Vertical/Lateral) Detailed Design | 27/09/2019 | 25/11/2019 | 27/09/2019 | 18/12/2019 | 0 | TK_Complete | -824745350 | 294 | -824745350_294
MML3RSTPRO8005 | TT_Task | PROC Damper(Vertical/Lateral) Long lead time items procurement | 27/09/2019 | 25/11/2019 | 27/09/2019 | 16/01/2020 | 0 | TK_Complete | -824745350 | 334 | -824745350_334
MML3RSTPRO8006 | TT_Task | PROC Damper(Vertical/Lateral) Manufacturing | 17/01/2020 | 14/09/2020 | 17/01/2020 | 08/06/2020 | 0 | TK_Complete | -824745350 | 294 | -824745350_294
MML3RSTPRO8010 | TT_Task | PROC Damper(Vertical/Lateral) - FAI/ FAT | 25/02/2022 | 25/02/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 294 | -824745350_294
MML3RSTPRO8011 | TT_Task | PROC Damper(Vertical/Lateral) - NONO/ NOWC from Project Manager | 25/02/2022 | 25/02/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 294 | -824745350_294
MML3RSTPRO8020 | TT_Task | PROC Damper(Vertical/Lateral) - Packing ; Transportation from Supplier works to Alstom Factory | 28/06/2020 | 28/06/2020 | 28/06/2020 | 28/06/2020 | 0 | TK_Complete | -824745350 | 294 | -824745350_294
MML3RSTPRO8060 | TT_Task | PROC Head Light ,Tail Light and Flasher Light Technical CBC discussion/ closure | 08/08/2019 | 06/09/2019 | 08/08/2019 | 10/09/2019 | 0 | TK_Complete | -824745350 | 280 | -824745350_280
MML3RSTPRO8062 | TT_Task | PROC Head Light ,Tail Light and Flasher Light Commercial closure ; PO Release | 17/02/2020 | 08/03/2020 | 11/09/2019 | 30/09/2019 | 0 | TK_Complete | -824745350 | 280 | -824745350_280
MML3RSTPRO8064 | TT_Task | PROC Head Light ,Tail Light and Flasher Light TRS freeze ; Conceptual design | 09/03/2020 | 07/04/2020 | 01/10/2019 | 29/11/2019 | 0 | TK_Complete | -824745350 | 280 | -824745350_280
MML3RSTPRO8066 | TT_Task | PROC Head Light ,Tail Light and Flasher Light Detailed Design | 02/12/2019 | 20/03/2020 | 02/12/2019 | 20/03/2020 | 0 | TK_Complete | -824745350 | 280 | -824745350_280
MML3RSTPRO8068 | TT_Task | PROC Head Light ,Tail Light and Flasher Light Long lead time items procurement | 21/03/2020 | 27/08/2020 | 21/03/2020 | 27/08/2020 | 0 | TK_Complete | -824745350 | 280 | -824745350_280
MML3RSTPRO8072 | TT_Task | PROC Head Light ,Tail Light and Flasher Light Manufacturing | 28/08/2020 | 16/09/2020 | 28/08/2020 | 20/11/2020 | 0 | TK_Complete | -824745350 | 280 | -824745350_280
MML3RSTPRO8074 | TT_Task | PROC Head Light ,Tail Light and Flasher Light - FAI/ FAT | 25/02/2022 | 25/02/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 280 | -824745350_280
MML3RSTPRO8076 | TT_Task | PROC Head Light ,Tail Light and Flasher Light NONO/ NOWC from Project Manager | 25/02/2022 | 25/02/2022 | nan | nan | 368 | TK_NotStart | -824745350 | 280 | -824745350_280
MML3RSTPRO8080 | TT_Task | PROC Head Light ,Tail Light and Flasher Light - Packing ; Transportation from Supplier works to Alstom Factory | 31/12/2020 | 09/01/2021 | 04/12/2020 | 04/12/2020 | 0 | TK_Complete | -824745350 | 280 | -824745350_280
MML3RSTPRO7820 | TT_Task | PROC Derailment Detector - Technical CBC discussion/ closure | 05/08/2019 | 19/08/2019 | 06/06/2019 | 23/08/2019 | 0 | TK_Complete | -824745350 | 293 | -824745350_293
MML3RSTPRO7821 | TT_Task | PROC Derailment Detector - Commercial closure ; PO Release | 17/02/2020 | 08/03/2020 | 24/08/2019 | 10/03/2020 | 0 | TK_Complete | -824745350 | 293 | -824745350_293
MML3RSTPRO7822 | TT_Task | PROC Derailment Detector TRS freeze ; Conceptual design | 09/01/2020 | 12/02/2020 | 11/03/2020 | 12/04/2020 | 0 | TK_Complete | -824745350 | 313 | -824745350_313
MML3RSTPRO7823 | TT_Task | PROC Derailment Detector Detailed Design | 13/02/2020 | 04/03/2020 | 13/04/2020 | 04/05/2020 | 0 | TK_Complete | -824745350 | 293 | -824745350_293
MML3RSTPRO7824 | TT_Task | PROC Derailment Detector Long lead time items procurement | 05/03/2020 | 24/09/2020 | 05/05/2020 | 24/07/2020 | 0 | TK_Complete | -824745350 | 318 | -824745350_318
MML3RSTPRO7825 | TT_Task | PROC Derailment Detector Manufacturing | 25/07/2020 | 07/08/2020 | 25/07/2020 | 24/11/2020 | 0 | TK_Complete | -824745350 | 293 | -824745350_293
MML3RSTPRO7830 | TT_Task | PROC Derailment Detector - FAI/ FAT | 25/01/2021 | 26/01/2021 | 05/01/2021 | 05/01/2021 | 0 | TK_Complete | -824745350 | 293 | -824745350_293
MML3RSTPRO7831 | TT_Task | PROC Derailment Detector NONO/ NOWC from Project Manager | 27/01/2021 | 27/01/2021 | 05/01/2021 | 05/01/2021 | 0 | TK_Complete | -824745350 | 293 | -824745350_293
MML3RSTPRO7840 | TT_Task | PROC Derailment Detector - Packing ; Transportation from Supplier works to Alstom Factory | 26/12/2020 | 30/12/2020 | 18/12/2020 | 13/02/2021 | 0 | TK_Complete | -824745350 | 293 | -824745350_293
MML3RSTPRO8300 | TT_Task | PROC Car Flooring - Technical CBC discussion/ closure | 25/01/2020 | 23/02/2020 | 24/12/2018 | 27/06/2019 | 0 | TK_Complete | -824745350 | 307 | -824745350_307
MML3RSTPRO8310 | TT_Task | PROC Car Flooring - Commercial closure ; PO Release | 02/03/2020 | 22/03/2020 | 28/06/2019 | 31/08/2019 | 0 | TK_Complete | -824745350 | 308 | -824745350_308
MML3RSTPRO8320 | TT_Task | PROC Car Flooring TRS freeze ; Conceptual design | 23/03/2020 | 11/04/2020 | 01/09/2019 | 21/11/2019 | 0 | TK_Complete | -824745350 | 309 | -824745350_309
MML3RSTPRO8330 | TT_Task | PROC Car Flooring Detailed Design | 12/04/2020 | 21/05/2020 | 22/11/2019 | 31/12/2019 | 0 | TK_Complete | -824745350 | 328 | -824745350_328
MML3RSTPRO8340 | TT_Task | PROC Car Flooring Long lead time items procurement | 17/12/2019 | 01/07/2020 | 17/12/2019 | 01/04/2020 | 0 | TK_Complete | -824745350 | 306 | -824745350_306
MML3RSTPRO8350 | TT_Task | PROC Car Flooring Manufacturing | 02/07/2020 | 22/07/2020 | 02/04/2020 | 10/07/2020 | 0 | TK_Complete | -824745350 | 328 | -824745350_328
MML3RSTPRO8370 | TT_Task | PROC Car Flooring NONO/ NOWC from Project Manager | 05/08/2021 | 05/08/2021 | 05/08/2021 | 05/08/2021 | 0 | TK_Complete | -824745350 | 285 | -824745350_285
MML3RSTPRO8380 | TT_Task | PROC Car Flooring - Packing ; Transportation from Supplier works to Alstom Factory | 18/08/2020 | 18/08/2020 | 18/08/2020 | 18/08/2020 | 0 | TK_Complete | -824745350 | 303 | -824745350_303
MML3RSTMFG1010 | TT_Task | MFG TS01: CBS Module: Underframe ; Side Module Assembly including FAI/ Witness Point | 29/11/2019 | 28/12/2019 | 29/11/2019 | 12/11/2020 | 0 | TK_Complete | -824745350 | 352 | -824745350_352
MML3RSTMFG1015 | TT_Task | MFG TS01: CBS Module: Roof ; End Module Assembly including FAI/ Witness Point | 03/01/2020 | 17/01/2020 | 03/01/2020 | 12/11/2020 | 0 | TK_Complete | -824745350 | 353 | -824745350_353
MML3RSTMFG1020 | TT_Task | MFG TS01: Pre-equipped Module: Underframe ; Side Module Assembly including FAI/ Witness Point | 10/08/2020 | 08/09/2020 | 10/08/2020 | 28/12/2020 | 0 | TK_Complete | -824745350 | 352 | -824745350_352
MML3RSTMFG1025 | TT_Task | MFG TS01: Pre-equipped Module: Roof ; End Module Assembly including FAI/ Witness Point | 10/08/2020 | 30/08/2020 | 10/08/2020 | 28/12/2020 | 0 | TK_Complete | -824745350 | 353 | -824745350_353
MML3RSTMFG1029 | TT_Task | MFG TS01: Cabin structure Assembly including FAI/ Witness Point | 01/12/2020 | 11/12/2020 | 01/12/2020 | 28/12/2020 | 0 | TK_Complete | -824745350 | 354 | -824745350_354
MML3RSTMFG1040 | TT_Task | MFG TS01: Car Body Assembly (Hold Point) | 13/08/2020 | 19/08/2020 | 28/08/2020 | 06/01/2021 | 0 | TK_Complete | -824745350 | 354 | -824745350_354
MML3RSTMFG1045 | TT_Task | MFG TS01: Fitting of Components | 20/08/2020 | 06/09/2020 | 28/08/2020 | 08/03/2021 | 0 | TK_Complete | -824745350 | 355 | -824745350_355
MML3RSTMFG1050 | TT_Task | MFG TS01: Bogie Integration at Bogie Shop | 10/10/2020 | 26/10/2020 | 10/10/2020 | 22/01/2021 | 0 | TK_Complete | -824745350 | 356 | -824745350_356
MML3RSTMFG1070 | TT_Task | MFG TS01: Complete Bogie including load test / X-Factor FAI/ FAT/ Witness/ Hold Point | 23/11/2020 | 27/11/2020 | 23/11/2020 | 19/02/2021 | 0 | TK_Complete | -824745350 | 339 | -824745350_339
MML3RSTMFG1100 | TT_Task | MFG TS01: Bogie Assembly with Car Body, Wayside RFID tag, Levelling , Wayside RFID tag ; Water test (Witness Point) | 11/11/2020 | 16/11/2020 | 11/11/2020 | 25/02/2021 | 0 | TK_Complete | -824745350 | 357 | -824745350_357
MML3RSTMFG1150 | TT_Task | MFG TS01: Installation of Train borne equipment | 16/04/2021 | 04/05/2021 | 16/04/2021 | 04/05/2021 | 0 | TK_Complete | -824745350 | 358 | -824745350_358
MML3RSTMFG1180 | TT_Task | T;C TS01: Mechanical Car level tests (internal witness point) | 23/05/2021 | 23/05/2021 | 15/02/2021 | 06/03/2021 | 0 | TK_Complete | -824745350 | 359 | -824745350_359
MML3RSTMFG1200 | TT_Task | T;C TS01: Routine Static Tests (witness point) | 08/03/2021 | 17/08/2021 | 08/03/2021 | 17/08/2021 | 0 | TK_Complete | -824745350 | 360 | -824745350_360
MML3RSTMFG1300 | TT_Task | INT TS01: Static Integration test with signalling (witness point) | 02/09/2021 | 26/11/2021 | 02/09/2021 | 26/11/2021 | 0 | TK_Complete | -824745350 | 361 | -824745350_361
MML3RSTMFG1340 | TT_Task | T;C TS01: Static Functional Validation (Research Designs and Standards Organisation Mandatory) (Witness point) | 28/06/2021 | 27/07/2021 | 14/06/2021 | 29/11/2021 | 0 | TK_Complete | -824745350 | 362 | -824745350_362
MML3RSTMFG1380 | TT_Task | T;C TS01: Mechanical Car Level Test (Customer Witness) | 25/12/2021 | 26/01/2022 | 01/12/2021 | nan | 0 | TK_Active | -824745350 | 359 | -824745350_359
MML3RSTMFG1420 | TT_Task | MFG TS01: Internal Hold Point | 25/02/2022 | 01/03/2022 | 03/01/2022 | nan | 0 | TK_Active | -824745350 | 363 | -824745350_363
MML3RSTMFG1430 | TT_Task | MFG TS01: Project Manager Hold Point (Final Inspection before dispatch) | 25/02/2022 | 27/02/2022 | 03/01/2022 | nan | 0 | TK_Active | -824745350 | 364 | -824745350_364
MML3RSTMFG1431 | TT_Task | MFG TS01: NONO/ NOWC from Project Manager | 12/03/2022 | 12/03/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 365 | -824745350_365
MML3RSTMFG1440 | TT_Task | TRA TS01: Packing ; Transportation from Factory to Depot | 13/03/2022 | 27/03/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 366 | -824745350_366
MML3RSTMFG1030 | TT_Task | MFG Structural Car: Car Body Module Production including Witness Point | 09/07/2020 | 25/09/2020 | 09/07/2020 | 25/09/2020 | 0 | TK_Complete | -824745350 | 354 | -824745350_354
MML3RSTMFG1034 | TT_Task | MFG Structural Car: Car Body Shell Assembly including Witness Point | 26/09/2020 | 05/10/2020 | 26/09/2020 | 25/10/2020 | 0 | TK_Complete | -824745350 | 354 | -824745350_354
MML3RSTMFG1110 | TT_Task | TRA Structural Car: Packing ; Transportation from India to Europe | 25/07/2021 | 25/07/2021 | 25/07/2021 | 25/07/2021 | 0 | TK_Complete | -824745350 | 367 | -824745350_367
MML3RSTMFG1190 | TT_Task | MFG Structural Car: Setup for Compression Load test of Carbody | 29/06/2021 | 28/07/2021 | 15/04/2021 | 01/02/2022 | 0 | TK_Complete | -824745350 | 368 | -824745350_368
MML3RSTMFG1250 | TT_Task | MFG Structural Car: Customer Witness Compression Load test of Carbody (Static and Fatigue) | 19/03/2022 | 15/05/2022 | 01/02/2022 | 01/02/2022 | 0 | TK_Complete | -824745350 | 368 | -824745350_368
MML3RSTMFG1260 | TT_Task | TRA Structural Car: Packing ; Transportation from Europe to India(NOT REQUIRED) | 16/05/2022 | 16/05/2022 | 01/02/2022 | nan | 1120 | TK_Active | -824745350 | 367 | -824745350_367
MML3RSTMFG1060 | TT_Task | MFG Climatic Car: CBS Module Production including Witness Point | 25/01/2021 | 03/02/2021 | 20/01/2021 | 26/01/2021 | 0 | TK_Complete | -824745350 | 369 | -824745350_369
MML3RSTMFG1090 | TT_Task | MFG Climatic Car: Pre-equipped Module production including Witness Point | 27/02/2021 | 06/03/2021 | 27/01/2021 | 02/02/2021 | 0 | TK_Complete | -824745350 | 369 | -824745350_369
MML3RSTMFG1120 | TT_Task | MFG Climatic Car: Fitting ; Bogie Assembly including Witness Point | 07/03/2021 | 06/04/2021 | 10/02/2021 | 20/04/2021 | 0 | TK_Complete | -824745350 | 369 | -824745350_369
MML3RSTMFG1170 | TT_Task | TRA Climatic Car: Packing ; Transportation from India to Europe | 25/05/2021 | 16/08/2021 | 05/05/2021 | 30/07/2021 | 0 | TK_Complete | -824745350 | 367 | -824745350_367
MML3RSTMFG1240 | TT_Task | MFG Climatic Car: Setup for test | 05/08/2021 | 15/09/2021 | 05/08/2021 | 18/08/2021 | 0 | TK_Complete | -824745350 | 369 | -824745350_369
MML3RSTMFG1360 | TT_Task | MFG Climatic Car: Customer Witness Climatic car test | 12/10/2021 | 19/10/2021 | 19/08/2021 | 22/09/2021 | 0 | TK_Complete | -824745350 | 369 | -824745350_369
MML3RSTMFG1370 | TT_Task | TRA Climatic Car: Packing ; Transportation from Europe to India | 23/09/2021 | 21/11/2021 | 23/09/2021 | 05/02/2022 | 0 | TK_Complete | -824745350 | 367 | -824745350_367
MML3RSTMFG1080 | TT_Task | MFG TS02: CBS Module: Underframe ; Side Module Assembly (Witness point) | 31/12/2020 | 29/01/2021 | 01/12/2020 | 10/02/2021 | 0 | TK_Complete | -824745350 | 370 | -824745350_370
MML3RSTMFG1081 | TT_Task | MFG TS02: CBS Module: Roof ; End Module Assembly (Witness point) | 10/01/2021 | 08/02/2021 | 01/12/2020 | 10/02/2021 | 0 | TK_Complete | -824745350 | 371 | -824745350_371
MML3RSTMFG1082 | TT_Task | MFG TS02: Pre-equipped Module: Underframe ; Side Module Assembly (Witness Point) | 15/01/2021 | 13/02/2021 | 24/12/2020 | 10/03/2021 | 0 | TK_Complete | -824745350 | 352 | -824745350_352
MML3RSTMFG1130 | TT_Task | MFG TS02: Pre-equipped Module: Cabin Assembly/ Roof ; End Module Assembly (Witness point) | 20/01/2021 | 18/02/2021 | 24/12/2020 | 10/03/2021 | 0 | TK_Complete | -824745350 | 353 | -824745350_353
MML3RSTMFG1160 | TT_Task | MFG TS02: Car Body Assembly (Hold Point) | 26/02/2021 | 27/03/2021 | 07/01/2021 | 20/03/2021 | 0 | TK_Complete | -824745350 | 354 | -824745350_354
MML3RSTMFG1163 | TT_Task | MFG TS02: Fitting of Components | 05/03/2021 | 03/04/2021 | 18/01/2021 | 20/04/2021 | 0 | TK_Complete | -824745350 | 355 | -824745350_355
MML3RSTMFG1165 | TT_Task | MFG TS02: Bogie assembly with Car Body, Wayside RFID tag, Levelling , Wayside RFID tag ; Water test ; Witness Point | 25/04/2021 | 24/05/2021 | 08/02/2021 | 07/04/2021 | 0 | TK_Complete | -824745350 | 357 | -824745350_357
MML3RSTMFG1220 | TT_Task | MFG TS02: Installation of Train Borne equipment | 15/04/2021 | 18/06/2021 | 15/04/2021 | 18/06/2021 | 0 | TK_Complete | -824745350 | 358 | -824745350_358
MML3RSTMFG1290 | TT_Task | T;C TS02: Mechanical Car level Tests (Internal Witness Point) | 25/04/2021 | 27/05/2021 | 10/03/2021 | 09/07/2021 | 0 | TK_Complete | -824745350 | 359 | -824745350_359
MML3RSTMFG1310 | TT_Task | T;C TS02: RST (Factory Acceptance Test) (Witness Point) | 04/08/2021 | 25/08/2021 | 19/07/2021 | 25/01/2022 | 0 | TK_Complete | -824745350 | 360 | -824745350_360
MML3RSTMFG1540 | TT_Task | INT TS02: Static Integration testing with Signalling (Witness Point) | 13/03/2022 | 22/03/2022 | 07/01/2022 | nan | 0 | TK_Active | -824745350 | 361 | -824745350_361
MML3RSTMFG1610 | TT_Task | MFG TS02: Internal Hold Point | 22/03/2022 | 31/03/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 363 | -824745350_363
MML3RSTMFG1620 | TT_Task | MFG TS02: Project Manager Hold Point (Final Inspection before dispatch) | 01/04/2022 | 03/04/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 364 | -824745350_364
MML3RSTMFG1621 | TT_Task | MFG TS02: NONO/ NOWC from Project Manager | 04/04/2022 | 04/04/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 365 | -824745350_365
MML3RSTMFG1640 | TT_Task | TRA TS02: Packing ; Transportation from Factory to Depot | 05/04/2022 | 24/04/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 366 | -824745350_366
MML3RSTMFG1230 | TT_Task | MFG TS03: CBS Module: Underframe ; Side Module Assembly including Witness Point | 02/07/2021 | 19/11/2021 | 02/07/2021 | 19/11/2021 | 0 | TK_Complete | -824745350 | 370 | -824745350_370
MML3RSTMFG1231 | TT_Task | MFG TS03: CBS Module: Roof ; End Module Assembly including Witness Point | 01/07/2021 | 20/07/2021 | 01/07/2021 | 19/11/2021 | 0 | TK_Complete | -824745350 | 371 | -824745350_371
MML3RSTMFG1232 | TT_Task | MFG TS03: Pre-equipped Module: Underframe ; Side Module Assembly including Witness Point | 03/09/2021 | 22/09/2021 | 03/09/2021 | 12/12/2021 | 0 | TK_Complete | -824745350 | 352 | -824745350_352
MML3RSTMFG1280 | TT_Task | MFG TS03: Pre-equipped Module: Roof ; End Module Assembly including Witness Point | 03/09/2021 | 03/10/2021 | 03/09/2021 | 12/12/2021 | 0 | TK_Complete | -824745350 | 353 | -824745350_353
MML3RSTMFG1350 | TT_Task | MFG TS03: Carbody assembly (HOLD Point) + Fitting of components | 22/09/2021 | 06/10/2021 | 22/09/2021 | nan | 0 | TK_Active | -824745350 | 372 | -824745350_372
MML3RSTMFG1352 | TT_Task | MFG TS03: Bogie Integration at Bogie Shop + Final Inspection (HOLD point) | 25/01/2022 | 27/02/2022 | 01/11/2021 | nan | 0 | TK_Active | -824745350 | 356 | -824745350_356
MML3RSTMFG1355 | TT_Task | MFG TS03: Bogie assembly with Car Body, Wayside RFID tag , Wayside RFID tag ; Water test ; Witness Point | 24/02/2022 | 04/03/2022 | 01/11/2021 | nan | 0 | TK_Active | -824745350 | 357 | -824745350_357
MML3RSTMFG1490 | TT_Task | MFG TS03: Installation of Train borne equipment | 23/03/2022 | 12/04/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 358 | -824745350_358
MML3RSTMFG1570 | TT_Task | T;C TS03: Mechanical Car level test+RST(Witness Point) | 13/04/2022 | 12/05/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 373 | -824745350_373
MML3RSTMFG1700 | TT_Task | INT TS03: Static Integration testing with Signalling (Witness Point) | 13/05/2022 | 02/06/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 361 | -824745350_361
MML3RSTMFG1740 | TT_Task | MFG TS03: Internal Hold Point | 03/06/2022 | 12/06/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 363 | -824745350_363
MML3RSTMFG1810 | TT_Task | MFG TS03: Project Manager Hold Point (Final Inspection before dispatch) | 13/06/2022 | 15/06/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 364 | -824745350_364
MML3RSTMFG1811 | TT_Task | MFG TS03: NONO/ NOWC from Project Manager | 16/06/2022 | 16/06/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 365 | -824745350_365
MML3RSTMFG1820 | TT_Task | TRA TS03: Packing ; Transportation from Factory to Depot | 17/06/2022 | 06/07/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 366 | -824745350_366
MML3RSTMFG1270 | TT_Task | MFG TS04: CBS Module: Underframe ; Side Module Assembly including Witness Point | 10/11/2021 | 09/12/2021 | 10/11/2021 | nan | 0 | TK_Active | -824745350 | 370 | -824745350_370
MML3RSTMFG1271 | TT_Task | MFG TS04: CBS Module: Roof ; End Module Assembly including Witness Point | 10/11/2021 | 09/12/2021 | 10/11/2021 | nan | 0 | TK_Active | -824745350 | 371 | -824745350_371
MML3RSTMFG1272 | TT_Task | MFG TS04: Pre-equipped Module: Underframe ; Side Module Assembly including Witness Point | 18/03/2022 | 05/04/2022 | 01/02/2022 | nan | 32 | TK_Active | -824745350 | 352 | -824745350_352
MML3RSTMFG1320 | TT_Task | MFG TS04: Pre-equipped Module: Roof ; End Module Assembly including Witness Point | 07/03/2022 | 26/03/2022 | 01/02/2022 | nan | 0 | TK_Active | -824745350 | 353 | -824745350_353
MML3RSTMFG1390 | TT_Task | MFG TS04: Carbody assembly (HOLD Point) + Fitting of components | 22/03/2022 | 10/04/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 372 | -824745350_372
MML3RSTMFG1392 | TT_Task | MFG TS04: Bogie Integration at Bogie Shop + Final Inspection (HOLD point) | 27/03/2022 | 09/04/2022 | nan | nan | 8 | TK_NotStart | -824745350 | 356 | -824745350_356
MML3RSTMFG1393 | TT_Task | MFG TS04: Bogie assembly with Car Body , Wayside RFID tag , Wayside RFID tag ; Water test | 11/04/2022 | 16/04/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 357 | -824745350_357
MML3RSTMFG1560 | TT_Task | MFG TS04: Installation of Train borne equipment | 17/04/2022 | 27/04/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 358 | -824745350_358
MML3RSTMFG1630 | TT_Task | T;C TS04: Mechanical Car level test+RST (Witness Point) | 28/04/2022 | 17/05/2022 | nan | nan | 128 | TK_NotStart | -824745350 | 373 | -824745350_373
MML3RSTMFG1760 | TT_Task | INT TS04: Static Integration testing with Signalling (Witness Point) | 03/06/2022 | 12/06/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 361 | -824745350_361
MML3RSTMFG1850 | TT_Task | MFG TS04: Internal hold point | 13/06/2022 | 17/06/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 363 | -824745350_363
MML3RSTMFG1870 | TT_Task | MFG TS04: Project Manager Hold Point (Final Inspection before dispatch) | 18/06/2022 | 20/06/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 364 | -824745350_364
MML3RSTMFG1871 | TT_Task | MFG TS04: NONO/ NOWC from Project Manager | 21/06/2022 | 21/06/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 365 | -824745350_365
MML3RSTMFG1880 | TT_Task | TRA TS04: Packing ; Transportation from Factory to Depot | 22/06/2022 | 01/07/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 366 | -824745350_366
MML3RSTMFG1330 | TT_Task | MFG TS05: CBS Module: Underframe ; Side Module Assembly including Witness Point | 17/03/2022 | 05/04/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 370 | -824745350_370
MML3RSTMFG1331 | TT_Task | MFG TS05 CBS Module: Roof ; End Module Assembly including Witness Point | 17/03/2022 | 05/04/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 371 | -824745350_371
MML3RSTMFG1332 | TT_Task | MFG TS05 Pre-equipped Module: Underframe ; Side Module Assembly including Witness Point | 28/03/2022 | 11/04/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 352 | -824745350_352
MML3RSTMFG1400 | TT_Task | MFG TS05: Pre-equipped Module: Roof ; End Module Assembly including Witness Point | 29/03/2022 | 17/04/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 353 | -824745350_353
MML3RSTMFG1470 | TT_Task | MFG TS05: Carbody Assembly (HOLD Point) + Fitting of components | 13/04/2022 | 27/04/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 372 | -824745350_372
MML3RSTMFG1472 | TT_Task | MFG TS05: Bogie Integration at Bogie Shop + Final Inspection (HOLD point) | 06/04/2022 | 20/04/2022 | nan | nan | 56 | TK_NotStart | -824745350 | 356 | -824745350_356
MML3RSTMFG1473 | TT_Task | MFG TS05 Bogie Assembly with Car Body , Wayside RFID tag ; Water test ; Witness Point | 28/04/2022 | 07/05/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 357 | -824745350_357
MML3RSTMFG1660 | TT_Task | MFG TS05: Installation of Train borne equipment | 08/05/2022 | 14/05/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 358 | -824745350_358
MML3RSTMFG1730 | TT_Task | T;C TS05: Mechanical Car level test+RST (Witness Point) | 15/05/2022 | 26/05/2022 | nan | nan | 136 | TK_NotStart | -824745350 | 373 | -824745350_373
MML3RSTMFG1860 | TT_Task | INT TS05: Static Integration testing with Signalling (Witness Point) | 13/06/2022 | 22/06/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 361 | -824745350_361
MML3RSTMFG1940 | TT_Task | MFG TS05: Internal hold point | 23/06/2022 | 02/07/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 363 | -824745350_363
MML3RSTMFG1980 | TT_Task | MFG TS05: Project Manager Hold Point (Final Inspection before dispatch) | 03/07/2022 | 05/07/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 364 | -824745350_364
MML3RSTMFG1981 | TT_Task | MFG TS05: NONO/ NOWC from Project Manager | 06/07/2022 | 06/07/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 365 | -824745350_365
MML3RSTMFG2000 | TT_Task | TRA TS05: Packing ; Transportation from Factory to Depot | 07/07/2022 | 16/07/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 366 | -824745350_366
MML3RSTMFG1410 | TT_Task | MFG TS06: CBS Module: Underframe ; Side Module Assembly including Witness Point | 01/04/2022 | 25/04/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 370 | -824745350_370
MML3RSTMFG1412 | TT_Task | MFG TS06: CBS Module: Roof ; End Module Assembly including Witness Point | 06/04/2022 | 25/04/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 371 | -824745350_371
MML3RSTMFG1413 | TT_Task | MFG TS06: Pre-equipped Module: Underframe ; Side Module Assembly including Witness Point | 11/04/2022 | 05/05/2022 | nan | nan | 40 | TK_NotStart | -824745350 | 352 | -824745350_352
MML3RSTMFG1460 | TT_Task | MFG TS06: Pre-equipped Module: Roof ; End Module Assembly including Witness Point | 16/04/2022 | 05/05/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 353 | -824745350_353
MML3RSTMFG1530 | TT_Task | MFG TS06: Carbody Assembly (HOLD Point) + Fitting of components | 21/04/2022 | 15/05/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 372 | -824745350_372
MML3RSTMFG1531 | TT_Task | MFG TS06: Bogie Integration at Bogie Shop + Final Inspection (HOLD point) | 26/04/2022 | 10/05/2022 | nan | nan | 40 | TK_NotStart | -824745350 | 356 | -824745350_356
MML3RSTMFG1533 | TT_Task | MFG TS06: Bogie Assembly with Car Body , Wayside RFID tag ; Water test ; Witness Point | 16/05/2022 | 30/05/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 357 | -824745350_357
MML3RSTMFG1720 | TT_Task | MFG TS06: Installation of Train borne equipment | 31/05/2022 | 14/06/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 358 | -824745350_358
MML3RSTMFG1800 | TT_Task | T;C TS06 Mechanical Car level test+RST (Witness Point) | 15/06/2022 | 14/07/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 373 | -824745350_373
MML3RSTMFG1930 | TT_Task | INT TS06 Static Integration testing with Signalling (Witness Point) | 15/07/2022 | 24/07/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 361 | -824745350_361
MML3RSTMFG1990 | TT_Task | MFG TS06 Internal hold point | 25/07/2022 | 29/07/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 363 | -824745350_363
MML3RSTMFG2070 | TT_Task | MFG TS06: Project Manager Hold Point (Final Inspection before dispatch) | 30/07/2022 | 01/08/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 364 | -824745350_364
MML3RSTMFG2071 | TT_Task | MFG TS06 NONO/ NOWC from Project Manager | 02/08/2022 | 02/08/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 365 | -824745350_365
MML3RSTMFG2080 | TT_Task | TRA TS06: Packing ; Transportation from Factory to Depot | 03/08/2022 | 22/08/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 366 | -824745350_366
MML3RSTMFG1450 | TT_Task | MFG TS07: CBS Module: Underframe ; Side Module Assembly including Witness Point | 16/04/2022 | 10/05/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 370 | -824745350_370
MML3RSTMFG1451 | TT_Task | MFG TS07: CBS Module: Roof ; End Module Assembly including Witness Point | 11/05/2022 | 30/05/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 371 | -824745350_371
MML3RSTMFG1452 | TT_Task | MFG TS07: Pre-equipped Module: Underframe ; Side Module Assembly including Witness Point | 26/04/2022 | 20/05/2022 | nan | nan | 160 | TK_NotStart | -824745350 | 352 | -824745350_352
MML3RSTMFG1510 | TT_Task | MFG TS07: Pre-equipped Module: Roof ; End Module Assembly including Witness Point | 21/05/2022 | 09/06/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 353 | -824745350_353
MML3RSTMFG1590 | TT_Task | MFG TS07: Carbody Assembly (HOLD Point) + Fitting of components | 26/05/2022 | 19/06/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 372 | -824745350_372
MML3RSTMFG1592 | TT_Task | MFG TS07: Bogie Integration at Bogie Shop + Final Inspection (HOLD point) | 31/05/2022 | 19/06/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 356 | -824745350_356
MML3RSTMFG1593 | TT_Task | MFG TS07: Bogie Assembly with Car Body , Wayside RFID tag ; Water test ; Witness Point | 20/06/2022 | 09/07/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 357 | -824745350_357
MML3RSTMFG1840 | TT_Task | MFG TS07: Installation of Train borne equipment | 10/07/2022 | 24/07/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 358 | -824745350_358
MML3RSTMFG1920 | TT_Task | T;C TS07: Mechanical Car level test+RST (Witness Point) | 25/07/2022 | 23/08/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 373 | -824745350_373
MML3RSTMFG2060 | TT_Task | INT TS07: Static Integration testing with Signalling (Witness Point) | 24/08/2022 | 02/09/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 361 | -824745350_361
MML3RSTMFG2130 | TT_Task | MFG TS07: Internal hold point | 03/09/2022 | 12/09/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 363 | -824745350_363
MML3RSTMFG2200 | TT_Task | MFG TS07: Project Manager Hold Point (Final Inspection before dispatch) | 13/09/2022 | 15/09/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 364 | -824745350_364
MML3RSTMFG2201 | TT_Task | MFG TS07: NONO/ NOWC from Project Manager | 16/09/2022 | 16/09/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 365 | -824745350_365
MML3RSTMFG2220 | TT_Task | TRA TS07: Packing ; Transportation from Factory to Depot | 17/09/2022 | 06/10/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 366 | -824745350_366
MML3RSTMFG1520 | TT_Task | MFG TS08: CBS Module: Underframe ; Side Module Assembly including Witness Point | 06/05/2022 | 25/05/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 370 | -824745350_370
MML3RSTMFG1521 | TT_Task | MFG TS08: CBS Module: Roof ; End Module Assembly including Witness Point | 26/05/2022 | 14/06/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 371 | -824745350_371
MML3RSTMFG1522 | TT_Task | MFG TS08: Pre-equipped Module: Underframe ; Side Module Assembly including Witness Point | 16/05/2022 | 04/06/2022 | nan | nan | 160 | TK_NotStart | -824745350 | 352 | -824745350_352
MML3RSTMFG1600 | TT_Task | MFG TS08: Pre-equipped Module: Roof ; End Module Assembly including Witness Point | 05/06/2022 | 24/06/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 353 | -824745350_353
MML3RSTMFG1680 | TT_Task | MFG TS08: Carbody Assembly (HOLD Point) + Fitting of components | 15/06/2022 | 09/07/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 372 | -824745350_372
MML3RSTMFG1682 | TT_Task | MFG TS08: Bogie Integration at Bogie Shop + Final Inspection (HOLD point) | 15/06/2022 | 09/07/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 356 | -824745350_356
MML3RSTMFG1683 | TT_Task | MFG TS08: Bogie Assembly with Car Body , Wayside RFID tag ; Water test ; Witness Point | 10/07/2022 | 29/07/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 357 | -824745350_357
MML3RSTMFG1970 | TT_Task | MFG TS08: Installation of Train borne equipment | 30/07/2022 | 13/08/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 358 | -824745350_358
MML3RSTMFG2050 | TT_Task | T;C TS08: Mechanical Car level test+RST (Witness Point) | 14/08/2022 | 12/09/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 373 | -824745350_373
MML3RSTMFG2190 | TT_Task | INT TS08: Static Integration testing with Signalling (Witness Point) | 13/09/2022 | 22/09/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 361 | -824745350_361
MML3RSTMFG2260 | TT_Task | MFG TS08: Internal hold point | 23/09/2022 | 02/10/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 363 | -824745350_363
MML3RSTMFG2330 | TT_Task | MFG TS08: Project Manager Hold Point (Final Inspection before dispatch) | 03/10/2022 | 05/10/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 364 | -824745350_364
MML3RSTMFG2331 | TT_Task | MFG TS08: NONO/ NOWC from Project Manager | 06/10/2022 | 06/10/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 365 | -824745350_365
MML3RSTMFG2350 | TT_Task | TRA TS08: Packing ; Transportation from Factory to Depot | 07/10/2022 | 26/10/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 366 | -824745350_366
MML3RSTMFG1580 | TT_Task | MFG TS09: CBS Module: Underframe ; Side Module Assembly including Witness Point | 21/05/2022 | 09/06/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 370 | -824745350_370
MML3RSTMFG1581 | TT_Task | MFG TS09:: CBS Module: Roof ; End Module Assembly including Witness Point | 10/06/2022 | 29/06/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 371 | -824745350_371
MML3RSTMFG1582 | TT_Task | MFG TS09: Pre-equipped Module: Underframe ; Side Module Assembly including Witness Point | 31/05/2022 | 19/06/2022 | nan | nan | 160 | TK_NotStart | -824745350 | 352 | -824745350_352
MML3RSTMFG1670 | TT_Task | MFG TS09: Pre-equipped Module: Roof ; End Module Assembly including Witness Point | 20/06/2022 | 09/07/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 353 | -824745350_353
MML3RSTMFG1770 | TT_Task | MFG TS09: Carbody Assembly (HOLD Point) + Fitting of components | 30/06/2022 | 24/07/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 372 | -824745350_372
MML3RSTMFG1772 | TT_Task | MFG TS09: Bogie Integration at Bogie Shop + Final Inspection (HOLD point) | 30/06/2022 | 24/07/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 356 | -824745350_356
MML3RSTMFG1773 | TT_Task | MFG TS09: Bogie Assembly with Car Body , Wayside RFID tag ; Water test ; Witness Point | 25/07/2022 | 13/08/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 357 | -824745350_357
MML3RSTMFG2100 | TT_Task | MFG TS09: Installation of Train borne equipment | 14/08/2022 | 28/08/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 358 | -824745350_358
MML3RSTMFG2180 | TT_Task | T;C TS09: Mechanical Car level test+RST (Witness Point) | 29/08/2022 | 27/09/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 373 | -824745350_373
MML3RSTMFG2320 | TT_Task | INT TS09: Static Integration testing with Signalling (Witness Point) | 28/09/2022 | 07/10/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 361 | -824745350_361
MML3RSTMFG2370 | TT_Task | MFG TS09: Internal hold point | 08/10/2022 | 17/10/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 363 | -824745350_363
MML3RSTMFG2450 | TT_Task | MFG TS09: Project Manager Hold Point (Final Inspection before dispatch) | 18/10/2022 | 20/10/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 364 | -824745350_364
MML3RSTMFG2451 | TT_Task | MFG TS09: NONO/ NOWC from Project Manager | 21/10/2022 | 21/10/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 365 | -824745350_365
MML3RSTMFG2470 | TT_Task | TRA TS09: Packing ; Transportation from Factory to Depot | 22/10/2022 | 10/11/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 366 | -824745350_366
MML3RSTMFG1690 | TT_Task | MFG TS10: CBS Module: Underframe ; Side Module Assembly including Witness Point | 05/06/2022 | 24/06/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 370 | -824745350_370
MML3RSTMFG1691 | TT_Task | MFG TS10: CBS Module: Roof ; End Module Assembly including Witness Point | 25/06/2022 | 14/07/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 371 | -824745350_371
MML3RSTMFG1692 | TT_Task | MFG TS10: Pre-equipped Module: Underframe ; Side Module Assembly including Witness Point | 15/06/2022 | 04/07/2022 | nan | nan | 160 | TK_NotStart | -824745350 | 352 | -824745350_352
MML3RSTMFG1780 | TT_Task | MFG TS10: Pre-equipped Module: Roof ; End Module Assembly including Witness Point | 05/07/2022 | 24/07/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 353 | -824745350_353
MML3RSTMFG1890 | TT_Task | MFG TS10: Carbody Assembly (HOLD Point) + Fitting of components | 15/07/2022 | 03/08/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 372 | -824745350_372
MML3RSTMFG1891 | TT_Task | MFG TS10: Bogie Integration at Bogie Shop + Final Inspection (HOLD point) | 15/07/2022 | 03/08/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 356 | -824745350_356
MML3RSTMFG1892 | TT_Task | MFG TS10: Bogie Assembly with Car Body , Wayside RFID tag ; Water test ; Witness Point | 04/08/2022 | 23/08/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 357 | -824745350_357
MML3RSTMFG2170 | TT_Task | MFG TS10: Installation of Train borne equipment | 24/08/2022 | 07/09/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 358 | -824745350_358
MML3RSTMFG2270 | TT_Task | T;C TS10: Mechanical Car level test+RST (Witness Point) | 08/09/2022 | 07/10/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 373 | -824745350_373
MML3RSTMFG2430 | TT_Task | INT TS10: Static Integration testing with Signalling (Witness Point) | 08/10/2022 | 17/10/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 361 | -824745350_361
MML3RSTMFG2480 | TT_Task | MFG TS10: Internal hold point | 18/10/2022 | 27/10/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 363 | -824745350_363
MML3RSTMFG2560 | TT_Task | MFG TS10: Project Manager Hold Point (Final Inspection before dispatch) | 28/10/2022 | 30/10/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 364 | -824745350_364
MML3RSTMFG2561 | TT_Task | MFG TS10: NONO/ NOWC from Project Manager | 31/10/2022 | 31/10/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 365 | -824745350_365
MML3RSTMFG2570 | TT_Task | TRA TS10: Packing ; Transportation from Factory to Depot | 01/11/2022 | 20/11/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 366 | -824745350_366
MML3RSTMFG1790 | TT_Task | MFG TS11: CBS Module: Underframe ; Side Module Assembly including Witness Point | 20/06/2022 | 09/07/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 370 | -824745350_370
MML3RSTMFG1791 | TT_Task | MFG TS11: CBS Module: Roof ; End Module Assembly including Witness Point | 10/07/2022 | 29/07/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 371 | -824745350_371
MML3RSTMFG1792 | TT_Task | MFG TS11: Pre-equipped Module: Underframe ; Side Module Assembly including Witness Point | 30/06/2022 | 19/07/2022 | nan | nan | 160 | TK_NotStart | -824745350 | 352 | -824745350_352
MML3RSTMFG1910 | TT_Task | MFG TS11: Pre-equipped Module: Roof ; End Module Assembly including Witness Point | 20/07/2022 | 08/08/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 353 | -824745350_353
MML3RSTMFG2040 | TT_Task | MFG TS11: Carbody Assembly (HOLD Point) + Fitting of components | 30/07/2022 | 18/08/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 372 | -824745350_372
MML3RSTMFG2041 | TT_Task | MFG TS11: Bogie Integration at Bogie Shop + Final Inspection (HOLD point) | 30/07/2022 | 18/08/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 356 | -824745350_356
MML3RSTMFG2042 | TT_Task | MFG TS11: Bogie Assembly with Car Body , Wayside RFID tag ; Water test ; Witness Point | 19/08/2022 | 07/09/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 357 | -824745350_357
MML3RSTMFG2310 | TT_Task | MFG TS11: Installation of Train borne equipment | 08/09/2022 | 22/09/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 358 | -824745350_358
MML3RSTMFG2420 | TT_Task | T;C TS11: Mechanical Car level test+RST (Witness Point) | 23/09/2022 | 22/10/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 373 | -824745350_373
MML3RSTMFG2550 | TT_Task | INT TS11: Static Integration testing with Signalling (Witness Point) | 23/10/2022 | 01/11/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 361 | -824745350_361
MML3RSTMFG2640 | TT_Task | MFG TS11: Internal hold point | 02/11/2022 | 11/11/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 363 | -824745350_363
MML3RSTMFG2670 | TT_Task | MFG TS11: Project Manager Hold Point (Final Inspection before dispatch) | 12/11/2022 | 14/11/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 364 | -824745350_364
MML3RSTMFG2671 | TT_Task | MFG TS11: NONO/ NOWC from Project Manager | 15/11/2022 | 15/11/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 365 | -824745350_365
MML3RSTMFG2690 | TT_Task | TRA TS11: Packing ; Transportation from Factory to Depot | 16/11/2022 | 05/12/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 366 | -824745350_366
MML3RSTMFG1900 | TT_Task | MFG TS12: CBS Module: Underframe ; Side Module Assembly including Witness Point | 05/07/2022 | 24/07/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 370 | -824745350_370
MML3RSTMFG1901 | TT_Task | MFG TS12: CBS Module: Roof ; End Module Assembly including Witness Point | 25/07/2022 | 13/08/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 371 | -824745350_371
MML3RSTMFG1902 | TT_Task | MFG TS12: Pre-equipped Module: Underframe ; Side Module Assembly including Witness Point | 15/07/2022 | 03/08/2022 | nan | nan | 120 | TK_NotStart | -824745350 | 352 | -824745350_352
MML3RSTMFG2010 | TT_Task | MFG TS12: Pre-equipped Module: Roof ; End Module Assembly including Witness Point | 04/08/2022 | 23/08/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 353 | -824745350_353
MML3RSTMFG2150 | TT_Task | MFG TS12: Carbody Assembly (HOLD Point) + Fitting of components | 09/08/2022 | 28/08/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 372 | -824745350_372
MML3RSTMFG2151 | TT_Task | MFG TS12: Bogie Integration at Bogie Shop + Final Inspection (HOLD point) | 14/08/2022 | 28/08/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 356 | -824745350_356
MML3RSTMFG2152 | TT_Task | MFG TS12:: Bogie Assembly with Car Body , Wayside RFID tag ; Water test ; Witness Point | 29/08/2022 | 17/09/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 357 | -824745350_357
MML3RSTMFG2400 | TT_Task | MFG TS12: Installation of Train borne equipment | 18/09/2022 | 02/10/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 358 | -824745350_358
MML3RSTMFG2530 | TT_Task | T;C TS12: Mechanical Car level test+RST (Witness Point) | 03/10/2022 | 01/11/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 373 | -824745350_373
MML3RSTMFG2660 | TT_Task | INT TS12: Static Integration testing with Signalling (Witness Point) | 02/11/2022 | 11/11/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 361 | -824745350_361
MML3RSTMFG2750 | TT_Task | MFG TS12: Internal hold point | 12/11/2022 | 21/11/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 363 | -824745350_363
MML3RSTMFG2780 | TT_Task | MFG TS12: Project Manager Hold Point (Final Inspection before dispatch) | 22/11/2022 | 24/11/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 364 | -824745350_364
MML3RSTMFG2781 | TT_Task | MFG TS12: NONO/ NOWC from Project Manager | 25/11/2022 | 25/11/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 365 | -824745350_365
MML3RSTMFG2790 | TT_Task | TRA TS12: Packing ; Transportation from Factory to Depot | 26/11/2022 | 15/12/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 366 | -824745350_366
MML3RSTMFG2020 | TT_Task | MFG TS13: CBS Module: Underframe ; Side Module Assembly including Witness Point | 20/07/2022 | 08/08/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 370 | -824745350_370
MML3RSTMFG2021 | TT_Task | MFG TS13: CBS Module: Roof ; End Module Assembly including Witness Point | 09/08/2022 | 28/08/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 371 | -824745350_371
MML3RSTMFG2022 | TT_Task | MFG TS13: Pre-equipped Module: Underframe ; Side Module Assembly including Witness Point | 30/07/2022 | 18/08/2022 | nan | nan | 120 | TK_NotStart | -824745350 | 352 | -824745350_352
MML3RSTMFG2120 | TT_Task | MFG TS13:Pre-equipped Module: Roof ; End Module Assembly including Witness Point | 19/08/2022 | 07/09/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 353 | -824745350_353
MML3RSTMFG2250 | TT_Task | MFG TS13: Carbody Assembly (HOLD Point) + Fitting of components | 24/08/2022 | 12/09/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 372 | -824745350_372
MML3RSTMFG2251 | TT_Task | MFG TS13: Bogie Integration at Bogie Shop + Final Inspection (HOLD point) | 29/08/2022 | 12/09/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 356 | -824745350_356
MML3RSTMFG2252 | TT_Task | MFG TS13: Bogie Assembly with Car Body , Wayside RFID tag ; Water test ; Witness Point | 13/09/2022 | 02/10/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 357 | -824745350_357
MML3RSTMFG2520 | TT_Task | MFG TS13: Installation of Train borne equipment | 03/10/2022 | 17/10/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 358 | -824745350_358
MML3RSTMFG2630 | TT_Task | T;C TS13: Mechanical Car level test+RST (Witness Point) | 18/10/2022 | 16/11/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 373 | -824745350_373
MML3RSTMFG2770 | TT_Task | INT TS13: Static Integration testing with Signalling (Witness Point) | 17/11/2022 | 26/11/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 361 | -824745350_361
MML3RSTMFG2850 | TT_Task | MFG TS13: Internal hold point | 27/11/2022 | 06/12/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 363 | -824745350_363
MML3RSTMFG2890 | TT_Task | MFG TS13: Project Manager Hold Point (Final Inspection before dispatch) | 07/12/2022 | 09/12/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 364 | -824745350_364
MML3RSTMFG2891 | TT_Task | MFG TS13: NONO/ NOWC from Project Manager | 10/12/2022 | 10/12/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 365 | -824745350_365
MML3RSTMFG2900 | TT_Task | TRA TS13: Packing ; Transportation from Factory to Depot | 11/12/2022 | 30/12/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 366 | -824745350_366
MML3RSTMFG2110 | TT_Task | MFG TS14: CBS Module: Underframe ; Side Module Assembly including Witness Point | 04/08/2022 | 23/08/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 370 | -824745350_370
MML3RSTMFG2111 | TT_Task | MFG TS14: CBS Module: Roof ; End Module Assembly including Witness Point | 24/08/2022 | 12/09/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 371 | -824745350_371
MML3RSTMFG2112 | TT_Task | MFG TS14: Pre-equipped Module: Underframe ; Side Module Assembly including Witness Point | 14/08/2022 | 02/09/2022 | nan | nan | 120 | TK_NotStart | -824745350 | 352 | -824745350_352
MML3RSTMFG2230 | TT_Task | MFG TS14: Pre-equipped Module: Roof ; End Module Assembly including Witness Point | 03/09/2022 | 22/09/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 353 | -824745350_353
MML3RSTMFG2360 | TT_Task | MFG TS14:Carbody Assembly (HOLD Point) + Fitting of components | 08/09/2022 | 27/09/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 372 | -824745350_372
MML3RSTMFG2361 | TT_Task | MFG TS14: Bogie Integration at Bogie Shop + Final Inspection (HOLD point) | 13/09/2022 | 27/09/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 356 | -824745350_356
MML3RSTMFG2362 | TT_Task | MFG TS14: Bogie Assembly with Car Body , Wayside RFID tag ; Water test ; Witness Point | 28/09/2022 | 17/10/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 357 | -824745350_357
MML3RSTMFG2600 | TT_Task | MFG TS14: Installation of Train borne equipment | 18/10/2022 | 01/11/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 358 | -824745350_358
MML3RSTMFG2740 | TT_Task | T;C TS14: Mechanical Car level test+RST (Witness Point) | 02/11/2022 | 01/12/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 373 | -824745350_373
MML3RSTMFG2880 | TT_Task | INT TS14: Static Integration testing with Signalling (Witness Point) | 02/12/2022 | 11/12/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 361 | -824745350_361
MML3RSTMFG2960 | TT_Task | MFG TS14: Internal hold point | 12/12/2022 | 21/12/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 363 | -824745350_363
MML3RSTMFG3000 | TT_Task | MFG TS14: Project Manager Hold Point (Final Inspection before dispatch) | 22/12/2022 | 24/12/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 364 | -824745350_364
MML3RSTMFG3001 | TT_Task | MFG TS14: NONO/ NOWC from Project Manager | 25/12/2022 | 25/12/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 365 | -824745350_365
MML3RSTMFG3010 | TT_Task | TRA TS14: Packing ; Transportation from Factory to Depot | 26/12/2022 | 14/01/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 366 | -824745350_366
MML3RSTMFG2240 | TT_Task | MFG TS15: CBS Module: Underframe ; Side Module Assembly including Witness Point | 19/08/2022 | 07/09/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 370 | -824745350_370
MML3RSTMFG2241 | TT_Task | MFG TS15: CBS Module: Roof ; End Module Assembly including Witness Point | 08/09/2022 | 27/09/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 371 | -824745350_371
MML3RSTMFG2242 | TT_Task | MFG TS15: Pre-equipped Module: Underframe ; Side Module Assembly including Witness Point | 29/08/2022 | 17/09/2022 | nan | nan | 120 | TK_NotStart | -824745350 | 352 | -824745350_352
MML3RSTMFG2290 | TT_Task | MFG TS15: Pre-equipped Module: Roof ; End Module Assembly including Witness Point | 18/09/2022 | 07/10/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 353 | -824745350_353
MML3RSTMFG2440 | TT_Task | MFG TS15: Carbody Assembly (HOLD Point) + Fitting of components | 23/09/2022 | 12/10/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 372 | -824745350_372
MML3RSTMFG2441 | TT_Task | MFG TS15: Bogie Integration at Bogie Shop + Final Inspection (HOLD point) | 28/09/2022 | 12/10/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 356 | -824745350_356
MML3RSTMFG2442 | TT_Task | MFG TS15: Bogie Assembly with Car Body , Wayside RFID tag ; Water test ; Witness Point | 13/10/2022 | 01/11/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 357 | -824745350_357
MML3RSTMFG2720 | TT_Task | MFG TS15: Installation of Train borne equipment | 02/11/2022 | 16/11/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 358 | -824745350_358
MML3RSTMFG2840 | TT_Task | T;C TS15: Mechanical Car level test+RST (Witness Point) | 17/11/2022 | 16/12/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 373 | -824745350_373
MML3RSTMFG2990 | TT_Task | INT TS15: Static Integration testing with Signalling (Witness Point) | 17/12/2022 | 26/12/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 361 | -824745350_361
MML3RSTMFG3070 | TT_Task | MFG TS15: Internal hold point | 27/12/2022 | 05/01/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 363 | -824745350_363
MML3RSTMFG3110 | TT_Task | MFG TS15: Project Manager Hold Point (Final Inspection before dispatch) | 06/01/2023 | 08/01/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 364 | -824745350_364
MML3RSTMFG3111 | TT_Task | MFG TS15: NONO/ NOWC from Project Manager | 09/01/2023 | 09/01/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 365 | -824745350_365
MML3RSTMFG3120 | TT_Task | TRA TS15: Packing ; Transportation from Factory to Depot | 10/01/2023 | 29/01/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 366 | -824745350_366
MML3RSTMFG2300 | TT_Task | MFG TS16: CBS Module: Underframe ; Side Module Assembly including Witness Point | 03/09/2022 | 22/09/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 370 | -824745350_370
MML3RSTMFG2301 | TT_Task | MFG TS16: CBS Module: Roof ; End Module Assembly including Witness Point | 23/09/2022 | 12/10/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 371 | -824745350_371
MML3RSTMFG2302 | TT_Task | MFG TS16: Pre-equipped Module: Underframe ; Side Module Assembly including Witness Point | 13/09/2022 | 02/10/2022 | nan | nan | 120 | TK_NotStart | -824745350 | 352 | -824745350_352
MML3RSTMFG2410 | TT_Task | MFG TS16: Pre-equipped Module: Roof ; End Module Assembly including Witness Point | 03/10/2022 | 22/10/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 353 | -824745350_353
MML3RSTMFG2540 | TT_Task | MFG TS16: Carbody Assembly (HOLD Point) + Fitting of components | 08/10/2022 | 27/10/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 372 | -824745350_372
MML3RSTMFG2541 | TT_Task | MFG TS16: Bogie Integration at Bogie Shop + Final Inspection (HOLD point) | 13/10/2022 | 27/10/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 356 | -824745350_356
MML3RSTMFG2542 | TT_Task | MFG TS16: Bogie Assembly with Car Body , Wayside RFID tag ; Water test ; Witness Point | 28/10/2022 | 16/11/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 357 | -824745350_357
MML3RSTMFG2830 | TT_Task | MFG TS16: Installation of Train borne equipment | 17/11/2022 | 01/12/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 358 | -824745350_358
MML3RSTMFG2950 | TT_Task | T;C TS16: Mechanical Car level test+RST (Witness Point) | 02/12/2022 | 31/12/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 373 | -824745350_373
MML3RSTMFG3100 | TT_Task | INT TS16: Static Integration testing with Signalling (Witness Point) | 01/01/2023 | 10/01/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 361 | -824745350_361
MML3RSTMFG3180 | TT_Task | MFG TS16: Internal hold point | 11/01/2023 | 20/01/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 363 | -824745350_363
MML3RSTMFG3220 | TT_Task | MFG TS16: Project Manager Hold Point (Final Inspection before dispatch) | 21/01/2023 | 23/01/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 364 | -824745350_364
MML3RSTMFG3221 | TT_Task | MFG TS16: NONO/ NOWC from Project Manager | 24/01/2023 | 24/01/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 365 | -824745350_365
MML3RSTMFG3230 | TT_Task | TRA TS16: Packing ; Transportation from Factory to Depot | 25/01/2023 | 13/02/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 366 | -824745350_366
MML3RSTMFG2390 | TT_Task | MFG TS17: CBS Module: Underframe ; Side Module Assembly including Witness Point | 18/09/2022 | 07/10/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 370 | -824745350_370
MML3RSTMFG2391 | TT_Task | MFG TS17: CBS Module: Roof ; End Module Assembly including Witness Point | 08/10/2022 | 27/10/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 371 | -824745350_371
MML3RSTMFG2392 | TT_Task | MFG TS17: Pre-equipped Module: Underframe ; Side Module Assembly including Witness Point | 28/09/2022 | 17/10/2022 | nan | nan | 120 | TK_NotStart | -824745350 | 352 | -824745350_352
MML3RSTMFG2500 | TT_Task | MFG TS17: Pre-equipped Module: Roof ; End Module Assembly including Witness Point | 18/10/2022 | 06/11/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 353 | -824745350_353
MML3RSTMFG2650 | TT_Task | MFG TS17: Carbody Assembly (HOLD Point) + Fitting of components | 23/10/2022 | 11/11/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 372 | -824745350_372
MML3RSTMFG2651 | TT_Task | MFG TS17: Bogie Integration at Bogie Shop + Final Inspection (HOLD point) | 28/10/2022 | 11/11/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 356 | -824745350_356
MML3RSTMFG2652 | TT_Task | MFG TS17: Bogie Assembly with Car Body , Wayside RFID tag ; Water test ; Witness Point | 12/11/2022 | 01/12/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 357 | -824745350_357
MML3RSTMFG2920 | TT_Task | MFG TS17: Installation of Train borne equipment | 02/12/2022 | 16/12/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 358 | -824745350_358
MML3RSTMFG3060 | TT_Task | T;C TS17: Mechanical Car level test+RST (Witness Point) | 17/12/2022 | 15/01/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 373 | -824745350_373
MML3RSTMFG3210 | TT_Task | INT TS17: Static Integration testing with Signalling (Witness Point) | 16/01/2023 | 25/01/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 361 | -824745350_361
MML3RSTMFG3290 | TT_Task | MFG TS17: Internal hold point | 26/01/2023 | 04/02/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 363 | -824745350_363
MML3RSTMFG3330 | TT_Task | MFG TS17: Project Manager Hold Point (Final Inspection before dispatch) | 05/02/2023 | 07/02/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 364 | -824745350_364
MML3RSTMFG3331 | TT_Task | MFG TS17: NONO/ NOWC from Project Manager | 08/02/2023 | 08/02/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 365 | -824745350_365
MML3RSTMFG3340 | TT_Task | TRA TS17: Packing ; Transportation from Factory to Depot | 09/02/2023 | 28/02/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 366 | -824745350_366
MML3RSTMFG2510 | TT_Task | MFG TS18: CBS Module: Underframe ; Side Module Assembly including Witness Point | 03/10/2022 | 22/10/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 370 | -824745350_370
MML3RSTMFG2511 | TT_Task | MFG TS18: CBS Module: Roof ; End Module Assembly including Witness Point | 23/10/2022 | 11/11/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 371 | -824745350_371
MML3RSTMFG2522 | TT_Task | MFG TS18: Pre-equipped Module: Underframe ; Side Module Assembly including Witness Point | 13/10/2022 | 01/11/2022 | nan | nan | 120 | TK_NotStart | -824745350 | 352 | -824745350_352
MML3RSTMFG2610 | TT_Task | MFG TS18: Pre-equipped Module: Roof ; End Module Assembly including Witness Point | 02/11/2022 | 21/11/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 353 | -824745350_353
MML3RSTMFG2760 | TT_Task | MFG TS18: Carbody Assembly (HOLD Point) + Fitting of components | 07/11/2022 | 26/11/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 372 | -824745350_372
MML3RSTMFG2761 | TT_Task | MFG TS18: Bogie Integration at Bogie Shop + Final Inspection (HOLD point) | 12/11/2022 | 26/11/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 356 | -824745350_356
MML3RSTMFG2762 | TT_Task | MFG TS18: Bogie Assembly with Car Body , Wayside RFID tag ; Water test ; Witness Point | 27/11/2022 | 16/12/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 357 | -824745350_357
MML3RSTMFG3030 | TT_Task | MFG TS18: Installation of Train borne equipment | 17/12/2022 | 31/12/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 358 | -824745350_358
MML3RSTMFG3170 | TT_Task | T;C TS18: Mechanical Car level test+RST (Witness Point) | 01/01/2023 | 30/01/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 373 | -824745350_373
MML3RSTMFG3320 | TT_Task | INT TS18: Static Integration testing with Signalling (Witness Point) | 31/01/2023 | 09/02/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 361 | -824745350_361
MML3RSTMFG3400 | TT_Task | MFG TS18: Internal hold point | 10/02/2023 | 19/02/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 363 | -824745350_363
MML3RSTMFG3440 | TT_Task | MFG TS18: Project Manager Hold Point (Final Inspection before dispatch) | 20/02/2023 | 22/02/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 364 | -824745350_364
MML3RSTMFG3441 | TT_Task | MFG TS18: NONO/ NOWC from Project Manager | 23/02/2023 | 23/02/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 365 | -824745350_365
MML3RSTMFG3450 | TT_Task | TRA TS18: Packing ; Transportation from Factory to Depot | 24/02/2023 | 15/03/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 366 | -824745350_366
MML3RSTMFG2620 | TT_Task | MFG TS19: CBS Module: Underframe ; Side Module Assembly including Witness Point | 18/10/2022 | 06/11/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 370 | -824745350_370
MML3RSTMFG2621 | TT_Task | MFG TS19: CBS Module: Roof ; End Module Assembly including Witness Point | 07/11/2022 | 26/11/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 371 | -824745350_371
MML3RSTMFG2622 | TT_Task | MFG TS19: Pre-equipped Module: Underframe ; Side Module Assembly including Witness Point | 28/10/2022 | 16/11/2022 | nan | nan | 120 | TK_NotStart | -824745350 | 352 | -824745350_352
MML3RSTMFG2710 | TT_Task | MFG TS19: Pre-equipped Module: Roof ; End Module Assembly including Witness Point | 17/11/2022 | 06/12/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 353 | -824745350_353
MML3RSTMFG2870 | TT_Task | MFG TS19: Carbody Assembly (HOLD Point) + Fitting of components | 22/11/2022 | 11/12/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 372 | -824745350_372
MML3RSTMFG2871 | TT_Task | MFG TS19: Bogie Integration at Bogie Shop + Final Inspection (HOLD point) | 27/11/2022 | 11/12/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 356 | -824745350_356
MML3RSTMFG2872 | TT_Task | MFG TS19: Bogie Assembly with Car Body , Wayside RFID tag ; Water test ; Witness Point | 12/12/2022 | 31/12/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 357 | -824745350_357
MML3RSTMFG3140 | TT_Task | MFG TS19: Installation of Train borne equipment | 01/01/2023 | 15/01/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 358 | -824745350_358
MML3RSTMFG3280 | TT_Task | T;C TS19: Mechanical Car level test+RST (Witness Point) | 16/01/2023 | 14/02/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 373 | -824745350_373
MML3RSTMFG3430 | TT_Task | INT TS19: Static Integration testing with Signalling (Witness Point) | 15/02/2023 | 24/02/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 361 | -824745350_361
MML3RSTMFG3510 | TT_Task | MFG TS19: Internal hold point | 25/02/2023 | 06/03/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 363 | -824745350_363
MML3RSTMFG3550 | TT_Task | MFG TS19: Project Manager Hold Point (Final Inspection before dispatch) | 07/03/2023 | 09/03/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 364 | -824745350_364
MML3RSTMFG3551 | TT_Task | MFG TS19: Internal hold point | 10/03/2023 | 10/03/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 363 | -824745350_363
MML3RSTMFG3560 | TT_Task | TRA TS19: Packing ; Transportation from Factory to Depot | 11/03/2023 | 30/03/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 366 | -824745350_366
MML3RSTMFG2730 | TT_Task | MFG TS20: CBS Module: Underframe ; Side Module Assembly including Witness Point | 02/11/2022 | 21/11/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 370 | -824745350_370
MML3RSTMFG2731 | TT_Task | MFG TS20: CBS Module: Roof ; End Module Assembly including Witness Point | 22/11/2022 | 11/12/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 371 | -824745350_371
MML3RSTMFG2732 | TT_Task | MFG TS20: Pre-equipped Module: Underframe ; Side Module Assembly including Witness Point | 12/11/2022 | 01/12/2022 | nan | nan | 120 | TK_NotStart | -824745350 | 352 | -824745350_352
MML3RSTMFG2820 | TT_Task | MFG TS20: Pre-equipped Module: Roof ; End Module Assembly including Witness Point | 02/12/2022 | 21/12/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 353 | -824745350_353
MML3RSTMFG2980 | TT_Task | MFG TS20: Carbody Assembly (HOLD Point) + Fitting of components | 07/12/2022 | 26/12/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 372 | -824745350_372
MML3RSTMFG2981 | TT_Task | MFG TS20: Bogie Integration at Bogie Shop + Final Inspection (HOLD point) | 12/12/2022 | 26/12/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 356 | -824745350_356
MML3RSTMFG2982 | TT_Task | MFG TS20: Bogie Assembly with Car Body , Wayside RFID tag ; Water test ; Witness Point | 27/12/2022 | 15/01/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 357 | -824745350_357
MML3RSTMFG3260 | TT_Task | MFG TS20: Installation of Train borne equipment | 16/01/2023 | 30/01/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 358 | -824745350_358
MML3RSTMFG3390 | TT_Task | T;C TS20: Mechanical Car level test+RST (Witness Point) | 31/01/2023 | 01/03/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 373 | -824745350_373
MML3RSTMFG3540 | TT_Task | INT TS20: Static Integration testing with Signalling (Witness Point) | 02/03/2023 | 11/03/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 361 | -824745350_361
MML3RSTMFG3620 | TT_Task | MFG TS20: Internal hold point | 12/03/2023 | 21/03/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 363 | -824745350_363
MML3RSTMFG3650 | TT_Task | MFG TS20: Project Manager Hold Point (Final Inspection before dispatch) | 22/03/2023 | 24/03/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 364 | -824745350_364
MML3RSTMFG3651 | TT_Task | MFG TS20: NONO/ NOWC from Project Manager | 25/03/2023 | 25/03/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 365 | -824745350_365
MML3RSTMFG3660 | TT_Task | TRA TS20: Packing ; Transportation from Factory to Depot | 26/03/2023 | 14/04/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 366 | -824745350_366
MML3RSTMFG2810 | TT_Task | MFG TS21: CBS Module: Underframe ; Side Module Assembly including Witness Point | 17/11/2022 | 06/12/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 370 | -824745350_370
MML3RSTMFG2811 | TT_Task | MFG TS21: CBS Module: Roof ; End Module Assembly including Witness Point | 07/12/2022 | 26/12/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 371 | -824745350_371
MML3RSTMFG2822 | TT_Task | MFG TS21: Pre-equipped Module: Underframe ; Side Module Assembly including Witness Point | 27/11/2022 | 16/12/2022 | nan | nan | 120 | TK_NotStart | -824745350 | 352 | -824745350_352
MML3RSTMFG2930 | TT_Task | MFG TS21: Pre-equipped Module: Roof ; End Module Assembly including Witness Point | 17/12/2022 | 05/01/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 353 | -824745350_353
MML3RSTMFG3090 | TT_Task | MFG TS21: Carbody Assembly (HOLD Point) + Fitting of components | 22/12/2022 | 10/01/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 372 | -824745350_372
MML3RSTMFG3091 | TT_Task | MFG TS21: Bogie Integration at Bogie Shop + Final Inspection (HOLD point) | 27/12/2022 | 10/01/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 356 | -824745350_356
MML3RSTMFG3092 | TT_Task | MFG TS21: Bogie Assembly with Car Body , Wayside RFID tag ; Water test ; Witness Point | 11/01/2023 | 30/01/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 357 | -824745350_357
MML3RSTMFG3360 | TT_Task | MFG TS21: Installation of Train borne equipment | 31/01/2023 | 14/02/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 358 | -824745350_358
MML3RSTMFG3470 | TT_Task | T;C TS21: Mechanical Car level test+RST (Witness Point) | 15/02/2023 | 16/03/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 373 | -824745350_373
MML3RSTMFG3472 | TT_Task | TRA TS21: Static Integration testing with Signalling (Witness Point) | 17/03/2023 | 26/03/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 374 | -824745350_374
MML3RSTMFG3720 | TT_Task | MFG TS21: Internal hold point | 27/03/2023 | 05/04/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 363 | -824745350_363
MML3RSTMFG3750 | TT_Task | MFG TS21: Project Manager Hold Point (Final Inspection before dispatch) | 06/04/2023 | 08/04/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 364 | -824745350_364
MML3RSTMFG3751 | TT_Task | MFG TS21: NONO/ NOWC from Project Manager | 09/04/2023 | 09/04/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 365 | -824745350_365
MML3RSTMFG3760 | TT_Task | TRA TS21: Packing ; Transportation from Factory to Depot | 10/04/2023 | 29/04/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 366 | -824745350_366
MML3RSTMFG2940 | TT_Task | MFG TS22: CBS Module: Underframe ; Side Module Assembly including Witness Point | 02/12/2022 | 21/12/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 370 | -824745350_370
MML3RSTMFG2941 | TT_Task | MFG TS22: CBS Module: Roof ; End Module Assembly including Witness Point | 22/12/2022 | 10/01/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 371 | -824745350_371
MML3RSTMFG2942 | TT_Task | MFG TS22: Pre-equipped Module: Underframe ; Side Module Assembly including Witness Point | 12/12/2022 | 31/12/2022 | nan | nan | 120 | TK_NotStart | -824745350 | 352 | -824745350_352
MML3RSTMFG3040 | TT_Task | MFG TS22: Pre-equipped Module: Roof ; End Module Assembly including Witness Point | 01/01/2023 | 20/01/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 353 | -824745350_353
MML3RSTMFG3200 | TT_Task | MFG TS22: Carbody Assembly (HOLD Point) + Fitting of components | 06/01/2023 | 25/01/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 372 | -824745350_372
MML3RSTMFG3201 | TT_Task | MFG TS22: Bogie Integration at Bogie Shop + Final Inspection (HOLD point) | 11/01/2023 | 25/01/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 356 | -824745350_356
MML3RSTMFG3202 | TT_Task | MFG TS22: Bogie Assembly with Car Body , Wayside RFID tag ; Water test ; Witness Point | 26/01/2023 | 14/02/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 357 | -824745350_357
MML3RSTMFG3480 | TT_Task | MFG TS22: Installation of Train borne equipment | 15/02/2023 | 01/03/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 358 | -824745350_358
MML3RSTMFG3580 | TT_Task | T;C TS22: Mechanical Car level test+RST (Witness Point) | 02/03/2023 | 31/03/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 373 | -824745350_373
MML3RSTMFG3582 | TT_Task | TRA TS22: Static Integration testing with Signalling (Witness Point) | 01/04/2023 | 10/04/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 374 | -824745350_374
MML3RSTMFG3820 | TT_Task | MFG TS22: Internal hold point | 11/04/2023 | 20/04/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 363 | -824745350_363
MML3RSTMFG3850 | TT_Task | MFG TS22: Project Manager Hold Point (Final Inspection before dispatch) | 21/04/2023 | 23/04/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 364 | -824745350_364
MML3RSTMFG3851 | TT_Task | MFG TS22: NONO/ NOWC from Project Manager | 24/04/2023 | 24/04/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 365 | -824745350_365
MML3RSTMFG3860 | TT_Task | TRA TS22: Packing ; Transportation from Factory to Depot | 25/04/2023 | 14/05/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 366 | -824745350_366
MML3RSTMFG3050 | TT_Task | MFG TS23: CBS Module: Underframe ; Side Module Assembly including Witness Point | 17/12/2022 | 05/01/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 370 | -824745350_370
MML3RSTMFG3051 | TT_Task | MFG TS23: CBS Module: Roof ; End Module Assembly including Witness Point | 06/01/2023 | 25/01/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 371 | -824745350_371
MML3RSTMFG3052 | TT_Task | MFG TS23: Pre-equipped Module: Underframe ; Side Module Assembly including Witness Point | 27/12/2022 | 15/01/2023 | nan | nan | 120 | TK_NotStart | -824745350 | 352 | -824745350_352
MML3RSTMFG3150 | TT_Task | MFG TS23: Pre-equipped module: Roof ; End Mosule Assembly including Witness Point | 16/01/2023 | 04/02/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 353 | -824745350_353
MML3RSTMFG3310 | TT_Task | MFG TS23: Carbody Assembly (HOLD Point) + Fitting of components | 21/01/2023 | 09/02/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 372 | -824745350_372
MML3RSTMFG3311 | TT_Task | MFG TS23: Bogie Integration at Bogie Shop + Final Inspection (HOLD point) | 26/01/2023 | 09/02/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 356 | -824745350_356
MML3RSTMFG3312 | TT_Task | MFG TS23: Bogie Assembly with Car Body , Wayside RFID tag ; Water test ; Witness Point | 10/02/2023 | 01/03/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 357 | -824745350_357
MML3RSTMFG3590 | TT_Task | MFG TS23: Installation of Train borne equipment | 02/03/2023 | 16/03/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 358 | -824745350_358
MML3RSTMFG3680 | TT_Task | T;C TS23: Mechanical Car level test+RST (Witness Point) | 17/03/2023 | 15/04/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 373 | -824745350_373
MML3RSTMFG3682 | TT_Task | TRA TS23: Static Integration testing with Signalling (Witness Point) | 16/04/2023 | 25/04/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 374 | -824745350_374
MML3RSTMFG3920 | TT_Task | MFG TS23: Internal hold point | 26/04/2023 | 05/05/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 363 | -824745350_363
MML3RSTMFG3950 | TT_Task | MFG TS23: Project Manager Hold Point (Final Inspection before dispatch) | 06/05/2023 | 08/05/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 364 | -824745350_364
MML3RSTMFG3951 | TT_Task | MFG TS23: NONO/ NOWC from Project Manager | 09/05/2023 | 09/05/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 365 | -824745350_365
MML3RSTMFG3960 | TT_Task | TRA TS23: Packing ; Transportation from Factory to Depot | 10/05/2023 | 29/05/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 366 | -824745350_366
MML3RSTMFG3160 | TT_Task | MFG TS24: CBS Module: Underframe ; Side Module Assembly including Witness Point | 01/01/2023 | 20/01/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 370 | -824745350_370
MML3RSTMFG3161 | TT_Task | MFG TS24: CBS Module: Roof ; End Module Assembly including Witness Point | 21/01/2023 | 09/02/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 371 | -824745350_371
MML3RSTMFG3162 | TT_Task | MFG TS24: Pre-equipped Module: Underframe ; Side Module Assembly including Witness Point | 11/01/2023 | 30/01/2023 | nan | nan | 120 | TK_NotStart | -824745350 | 352 | -824745350_352
MML3RSTMFG3250 | TT_Task | MFG TS24: Pre-equipped Module: Roof ; End Module Assembly including Witness Point | 31/01/2023 | 19/02/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 353 | -824745350_353
MML3RSTMFG3420 | TT_Task | MFG TS24: Carbody Assembly (HOLD Point) + Fitting of components | 05/02/2023 | 24/02/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 372 | -824745350_372
MML3RSTMFG3421 | TT_Task | MFG TS24: Bogie Integration at Bogie Shop + Final Inspection (HOLD point) | 10/02/2023 | 24/02/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 356 | -824745350_356
MML3RSTMFG3422 | TT_Task | MFG TS24: Bogie Assembly with Car Body , Wayside RFID tag ; Water test ; Witness Point | 25/02/2023 | 16/03/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 357 | -824745350_357
MML3RSTMFG3690 | TT_Task | MFG TS24: Installation of Train borne equipment | 17/03/2023 | 31/03/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 358 | -824745350_358
MML3RSTMFG3780 | TT_Task | T;C TS24: Mechanical Car level test+RST (Witness Point) | 01/04/2023 | 30/04/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 373 | -824745350_373
MML3RSTMFG3782 | TT_Task | TRA TS24: Static Integration testing with Signalling (Witness Point) | 01/05/2023 | 10/05/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 374 | -824745350_374
MML3RSTMFG4010 | TT_Task | MFG TS24: Internal hold point | 11/05/2023 | 20/05/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 363 | -824745350_363
MML3RSTMFG4040 | TT_Task | MFG TS24: Project Manager Hold Point (Final Inspection before dispatch) | 21/05/2023 | 23/05/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 364 | -824745350_364
MML3RSTMFG4041 | TT_Task | MFG TS24: NONO/ NOWC from Project Manager | 24/05/2023 | 24/05/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 365 | -824745350_365
MML3RSTMFG4050 | TT_Task | TRA TS24: Packing ; Transportation from Factory to Depot | 25/05/2023 | 13/06/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 366 | -824745350_366
MML3RSTMFG3270 | TT_Task | MFG TS25: CBS Module: Underframe ; Side Module Assembly including Witness Point | 16/01/2023 | 04/02/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 370 | -824745350_370
MML3RSTMFG3271 | TT_Task | MFG TS25: CBS Module: Roof ; End Module Assembly including Witness Point | 05/02/2023 | 24/02/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 371 | -824745350_371
MML3RSTMFG3272 | TT_Task | MFG TS25: Pre-equipped Module: Underframe ; Side Module Assembly including Witness Point | 26/01/2023 | 14/02/2023 | nan | nan | 120 | TK_NotStart | -824745350 | 352 | -824745350_352
MML3RSTMFG3380 | TT_Task | MFG TS25: Pre-equipped Module: Roof ; End Module Assembly including Witness Point | 15/02/2023 | 06/03/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 353 | -824745350_353
MML3RSTMFG3530 | TT_Task | MFG TS25: Carbody Assembly (HOLD Point) + Fitting of components | 20/02/2023 | 11/03/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 372 | -824745350_372
MML3RSTMFG3531 | TT_Task | MFG TS25: Bogie Integration at Bogie Shop + Final Inspection (HOLD point) | 25/02/2023 | 11/03/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 356 | -824745350_356
MML3RSTMFG3532 | TT_Task | MFG TS25: Bogie Assembly with Car Body , Wayside RFID tag ; Water test ; Witness Point | 12/03/2023 | 31/03/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 357 | -824745350_357
MML3RSTMFG3790 | TT_Task | MFG TS25: Installation of Train borne equipment | 01/04/2023 | 15/04/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 358 | -824745350_358
MML3RSTMFG3890 | TT_Task | T;C TS25: Mechanical Car level test+RST (Witness Point) | 16/04/2023 | 15/05/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 373 | -824745350_373
MML3RSTMFG3892 | TT_Task | TRA TS25: Static Integration testing with Signalling (Witness Point) | 16/05/2023 | 25/05/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 374 | -824745350_374
MML3RSTMFG4090 | TT_Task | MFG TS25: Internal hold point | 26/05/2023 | 04/06/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 363 | -824745350_363
MML3RSTMFG4120 | TT_Task | MFG TS25: Project Manager Hold Point (Final Inspection before dispatch) | 05/06/2023 | 07/06/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 364 | -824745350_364
MML3RSTMFG4121 | TT_Task | MFG TS25: NONO/ NOWC from Project Manager | 08/06/2023 | 08/06/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 365 | -824745350_365
MML3RSTMFG4130 | TT_Task | TRA TS25: Packing ; Transportation from Factory to Depot | 09/06/2023 | 28/06/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 366 | -824745350_366
MML3RSTMFG3370 | TT_Task | MFG TS26: CBS Module: Underframe ; Side Module Assembly including Witness Point | 31/01/2023 | 19/02/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 370 | -824745350_370
MML3RSTMFG3371 | TT_Task | MFG TS26: CBS Module: Roof ; End Module Assembly including Witness Point | 20/02/2023 | 11/03/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 371 | -824745350_371
MML3RSTMFG3372 | TT_Task | MFG TS26: Pre-equipped Module: Underframe ; Side Module Assembly including Witness Point | 10/02/2023 | 01/03/2023 | nan | nan | 120 | TK_NotStart | -824745350 | 352 | -824745350_352
MML3RSTMFG3490 | TT_Task | MFG TS26: Pre-equipped Module: Roof ; End Module Assembly including Witness Point | 02/03/2023 | 21/03/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 353 | -824745350_353
MML3RSTMFG3640 | TT_Task | MFG TS26: Carbody Assembly (HOLD Point) + Fitting of components | 07/03/2023 | 26/03/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 372 | -824745350_372
MML3RSTMFG3641 | TT_Task | MFG TS26: Bogie Integration at Bogie Shop + Final Inspection (HOLD point) | 12/03/2023 | 26/03/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 356 | -824745350_356
MML3RSTMFG3642 | TT_Task | MFG TS26: Bogie Assembly with Car Body , Wayside RFID tag ; Water test ; Witness Point | 27/03/2023 | 15/04/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 357 | -824745350_357
MML3RSTMFG3880 | TT_Task | MFG TS26: Installation of Train borne equipment | 16/04/2023 | 30/04/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 358 | -824745350_358
MML3RSTMFG3980 | TT_Task | T;C TS26: Mechanical Car level test+RST (Witness Point) | 01/05/2023 | 30/05/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 373 | -824745350_373
MML3RSTMFG3982 | TT_Task | TRA TS26: Static Integration testing with Signalling (Witness Point) | 31/05/2023 | 09/06/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 374 | -824745350_374
MML3RSTMFG4170 | TT_Task | MFG TS26: Internal hold point | 10/06/2023 | 19/06/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 363 | -824745350_363
MML3RSTMFG4190 | TT_Task | MFG TS26: Project Manager Hold Point (Final Inspection before dispatch) | 20/06/2023 | 22/06/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 364 | -824745350_364
MML3RSTMFG4191 | TT_Task | MFG TS26: NONO/ NOWC from Project Manager | 23/06/2023 | 23/06/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 365 | -824745350_365
MML3RSTMFG4200 | TT_Task | TRA TS26: Packing ; Transportation from Factory to Depot | 24/06/2023 | 13/07/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 366 | -824745350_366
MML3RSTMFG3500 | TT_Task | MFG TS27: CBS Module: Underframe ; Side Module Assembly including Witness Point | 15/02/2023 | 06/03/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 370 | -824745350_370
MML3RSTMFG3501 | TT_Task | MFG TS27: CBS Module: Roof ; End Module Assembly including Witness Point | 07/03/2023 | 26/03/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 371 | -824745350_371
MML3RSTMFG3502 | TT_Task | MFG TS27: Pre-equipped Module: Underframe ; Side Module Assembly including Witness Point | 25/02/2023 | 16/03/2023 | nan | nan | 120 | TK_NotStart | -824745350 | 352 | -824745350_352
MML3RSTMFG3600 | TT_Task | MFG TS27: Pre-equipped module: Roof ; End Modue Assembly Including Witness Point | 17/03/2023 | 05/04/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 353 | -824745350_353
MML3RSTMFG3740 | TT_Task | MFG TS27: Carbody Assembly (HOLD Point) + Fitting of components | 22/03/2023 | 10/04/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 372 | -824745350_372
MML3RSTMFG3741 | TT_Task | MFG TS27: Bogie Integration at Bogie Shop + Final Inspection (HOLD point) | 27/03/2023 | 10/04/2023 | nan | nan | 160 | TK_NotStart | -824745350 | 356 | -824745350_356
MML3RSTMFG3742 | TT_Task | MFG TS27: Bogie Assembly with Car Body , Wayside RFID tag ; Water test ; Witness Point | 11/04/2023 | 30/04/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 357 | -824745350_357
MML3RSTMFG3990 | TT_Task | MFG TS27: Installation of Train borne equipment | 01/05/2023 | 15/05/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 358 | -824745350_358
MML3RSTMFG4070 | TT_Task | T;C TS27: Mechanical Car level test+RST (Witness Point) | 16/05/2023 | 14/06/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 373 | -824745350_373
MML3RSTMFG4072 | TT_Task | TRA TS27: Static Integration testing with Signalling (Witness Point) | 15/06/2023 | 24/06/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 374 | -824745350_374
MML3RSTMFG4240 | TT_Task | MFG TS27: Internal hold point | 25/06/2023 | 04/07/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 363 | -824745350_363
MML3RSTMFG4260 | TT_Task | MFG TS27: Project Manager Hold Point (Final Inspection before dispatch) | 05/07/2023 | 07/07/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 364 | -824745350_364
MML3RSTMFG4261 | TT_Task | MFG TS27: NONO/ NOWC from Project Manager | 08/07/2023 | 08/07/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 365 | -824745350_365
MML3RSTMFG4270 | TT_Task | TRA TS27: Packing ; Transportation from Factory to Depot | 09/07/2023 | 28/07/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 366 | -824745350_366
MML3RSTMFG3610 | TT_Task | MFG TS28: CBS Module: Underframe ; Side Module Assembly including Witness Point | 02/03/2023 | 21/03/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 370 | -824745350_370
MML3RSTMFG3611 | TT_Task | MFG TS28: CBS Module: Roof ; End Module Assembly including Witness Point | 22/03/2023 | 10/04/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 371 | -824745350_371
MML3RSTMFG3612 | TT_Task | MFG TS28: Pre-equipped Module: Underframe ; Side Module Assembly including Witness Point | 12/03/2023 | 31/03/2023 | nan | nan | 120 | TK_NotStart | -824745350 | 352 | -824745350_352
MML3RSTMFG3700 | TT_Task | MFG TS28: Pre-equipped Module: Roof ; End Module Assembly including Witness Point | 01/04/2023 | 20/04/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 353 | -824745350_353
MML3RSTMFG3840 | TT_Task | MFG TS28: Carbody Assembly (HOLD Point) + Fitting of components | 06/04/2023 | 25/04/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 372 | -824745350_372
MML3RSTMFG3841 | TT_Task | MFG TS28: Bogie Integration at Bogie Shop + Final Inspection (HOLD point) | 11/04/2023 | 25/04/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 356 | -824745350_356
MML3RSTMFG3842 | TT_Task | MFG TS28: Bogie Assembly with Car Body , Wayside RFID tag ; Water test ; Witness Point | 26/04/2023 | 15/05/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 357 | -824745350_357
MML3RSTMFG4080 | TT_Task | MFG TS28: Installation of Train borne equipment | 16/05/2023 | 30/05/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 358 | -824745350_358
MML3RSTMFG4150 | TT_Task | T;C TS28: Mechanical Car level test+RST (Witness Point) | 31/05/2023 | 29/06/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 373 | -824745350_373
MML3RSTMFG4152 | TT_Task | TRA TS28: Static Integration testing with Signalling (Witness Point) | 30/06/2023 | 09/07/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 374 | -824745350_374
MML3RSTMFG4310 | TT_Task | MFG TS28: Internal hold point | 10/07/2023 | 19/07/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 363 | -824745350_363
MML3RSTMFG4330 | TT_Task | MFG TS28: Project Manager Hold Point (Final Inspection before dispatch) | 20/07/2023 | 22/07/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 364 | -824745350_364
MML3RSTMFG4331 | TT_Task | MFG TS28: Internal hold point | 23/07/2023 | 23/07/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 363 | -824745350_363
MML3RSTMFG4340 | TT_Task | TRA TS28: Packing ; Transportation from Factory to Depot | 24/07/2023 | 12/08/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 366 | -824745350_366
MML3RSTMFG3710 | TT_Task | MFG TS29: CBS Module: Underframe ; Side Module Assembly including Witness Point | 17/03/2023 | 05/04/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 370 | -824745350_370
MML3RSTMFG3711 | TT_Task | MFG TS29: CBS Module: Roof ; End Module Assembly including Witness Point | 06/04/2023 | 25/04/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 371 | -824745350_371
MML3RSTMFG3712 | TT_Task | MFG TS29: Pre-equipped Module: Underframe ; Side Module Assembly including Witness Point | 27/03/2023 | 15/04/2023 | nan | nan | 120 | TK_NotStart | -824745350 | 352 | -824745350_352
MML3RSTMFG3800 | TT_Task | MFG TS29: Pre-equipped Module: Roof ; End Module Assembly including Witness Point | 16/04/2023 | 05/05/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 353 | -824745350_353
MML3RSTMFG3940 | TT_Task | MFG TS29: Carbody Assembly (HOLD Point) + Fitting of components | 21/04/2023 | 10/05/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 372 | -824745350_372
MML3RSTMFG3941 | TT_Task | MFG TS29: Bogie Integration at Bogie Shop + Final Inspection (HOLD point) | 26/04/2023 | 10/05/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 356 | -824745350_356
MML3RSTMFG3942 | TT_Task | MFG TS29: Bogie Assembly with Car Body , Wayside RFID tag ; Water test ; Witness Point | 11/05/2023 | 30/05/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 357 | -824745350_357
MML3RSTMFG4160 | TT_Task | MFG TS29: Installation of Train borne equipment | 31/05/2023 | 14/06/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 358 | -824745350_358
MML3RSTMFG4220 | TT_Task | T;C TS29: Mechanical Car level test+RST (Witness Point) | 15/06/2023 | 14/07/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 373 | -824745350_373
MML3RSTMFG4222 | TT_Task | TRA TS29: Static Integration testing with Signalling (Witness Point) | 15/07/2023 | 24/07/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 374 | -824745350_374
MML3RSTMFG4360 | TT_Task | MFG TS29: Internal hold point | 25/07/2023 | 03/08/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 363 | -824745350_363
MML3RSTMFG4380 | TT_Task | MFG TS29: Project Manager Hold Point (Final Inspection before dispatch) | 04/08/2023 | 06/08/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 364 | -824745350_364
MML3RSTMFG4381 | TT_Task | MFG TS29: NONO/ NOWC from Project Manager | 07/08/2023 | 07/08/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 365 | -824745350_365
MML3RSTMFG4390 | TT_Task | TRA TS29: Packing ; Transportation from Factory to Depot | 08/08/2023 | 27/08/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 366 | -824745350_366
MML3RSTMFG3810 | TT_Task | MFG TS30: CBS Module: Underframe ; Side Module Assembly including Witness Point | 01/04/2023 | 20/04/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 370 | -824745350_370
MML3RSTMFG3811 | TT_Task | MFG TS30: CBS Module: Roof ; End Module Assembly including Witness Point | 21/04/2023 | 10/05/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 371 | -824745350_371
MML3RSTMFG3812 | TT_Task | MFG TS30: Pre-equipped Module: Underframe ; Side Module Assembly including Witness Point | 11/04/2023 | 30/04/2023 | nan | nan | 120 | TK_NotStart | -824745350 | 352 | -824745350_352
MML3RSTMFG3900 | TT_Task | MFG TS30: Pre-equipped Module: Roof ; End Module Assembly including Witness Point | 01/05/2023 | 20/05/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 353 | -824745350_353
MML3RSTMFG4030 | TT_Task | MFG TS30: Carbody Assembly (HOLD Point) + Fitting of components | 06/05/2023 | 25/05/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 372 | -824745350_372
MML3RSTMFG4031 | TT_Task | MFG TS30: Bogie Integration at Bogie Shop + Final Inspection (HOLD point) | 11/05/2023 | 25/05/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 356 | -824745350_356
MML3RSTMFG4032 | TT_Task | MFG TS30: Bogie Assembly with Car Body , Wayside RFID tag ; Water test ; Witness Point | 26/05/2023 | 14/06/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 357 | -824745350_357
MML3RSTMFG4230 | TT_Task | MFG TS30: Installation of Train borne equipment | 15/06/2023 | 29/06/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 358 | -824745350_358
MML3RSTMFG4290 | TT_Task | T;C TS30: Mechanical Car level test+RST (Witness Point) | 30/06/2023 | 29/07/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 373 | -824745350_373
MML3RSTMFG4292 | TT_Task | TRA TS30: Static Integration testing with Signalling (Witness Point) | 30/07/2023 | 08/08/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 374 | -824745350_374
MML3RSTMFG4400 | TT_Task | MFG TS30: Internal hold point | 09/08/2023 | 13/08/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 363 | -824745350_363
MML3RSTMFG4420 | TT_Task | MFG TS30: Project Manager Hold Point (Final Inspection before dispatch) | 14/08/2023 | 16/08/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 364 | -824745350_364
MML3RSTMFG4421 | TT_Task | MFG TS30: NONO/ NOWC from Project Manager | 17/08/2023 | 17/08/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 365 | -824745350_365
MML3RSTMFG4430 | TT_Task | TRA TS30: Packing ; Transportation from Factory to Depot | 18/08/2023 | 06/09/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 366 | -824745350_366
MML3RSTMFG3910 | TT_Task | MFG TS31: CBS Module: Underframe ; Side Module Assembly including Witness Point | 11/04/2023 | 30/04/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 370 | -824745350_370
MML3RSTMFG3911 | TT_Task | MFG TS31: CBS Module: Roof ; End Module Assembly including Witness Point | 01/05/2023 | 20/05/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 371 | -824745350_371
MML3RSTMFG3912 | TT_Task | MFG TS31: Pre-equipped Module: Underframe ; Side Module Assembly including Witness Point | 21/04/2023 | 10/05/2023 | nan | nan | 120 | TK_NotStart | -824745350 | 352 | -824745350_352
MML3RSTMFG4000 | TT_Task | MFG TS31: Pre-equipped Module: Roof ; End Module Assembly including Witness Point | 11/05/2023 | 30/05/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 353 | -824745350_353
MML3RSTMFG4110 | TT_Task | MFG TS31: Carbody Assembly (HOLD Point) + Fitting of components | 16/05/2023 | 04/06/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 372 | -824745350_372
MML3RSTMFG4111 | TT_Task | MFG TS31: Bogie Integration at Bogie Shop + Final Inspection (HOLD point) | 21/05/2023 | 04/06/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 356 | -824745350_356
MML3RSTMFG4112 | TT_Task | MFG TS31: Bogie Assembly with Car Body , Wayside RFID tag ; Water test ; Witness Point | 05/06/2023 | 24/06/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 357 | -824745350_357
MML3RSTMFG4300 | TT_Task | MFG TS31: Installation of Train borne equipment | 25/06/2023 | 04/07/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 358 | -824745350_358
MML3RSTMFG4350 | TT_Task | T;C TS31: Mechanical test+RST (Witness Point) | 05/07/2023 | 29/07/2023 | nan | nan | 80 | TK_NotStart | -824745350 | 360 | -824745350_360
MML3RSTMFG4352 | TT_Task | TRA TS31: Static Integration testing with Signalling (Witness Point) | 09/08/2023 | 18/08/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 374 | -824745350_374
MML3RSTMFG4440 | TT_Task | MFG TS31: Internal hold point | 19/08/2023 | 23/08/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 363 | -824745350_363
MML3RSTMFG4460 | TT_Task | MFG TS31: Project Manager Hold Point (Final Inspection before dispatch) | 24/08/2023 | 26/08/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 364 | -824745350_364
MML3RSTMFG4461 | TT_Task | MFG TS31: NONO/ NOWC from Project Manager | 27/08/2023 | 27/08/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 365 | -824745350_365
MML3RSTMFG4470 | TT_Task | TRA TS31: Packing ; Transportation from Factory to Depot | 28/08/2023 | 16/09/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 366 | -824745350_366
MML3RSTINT2130 | TT_Task | INT DSG:To provide details of tunnel design drawings showing cuves, clearences,gradients,chainages | 10/09/2018 | 10/09/2018 | 13/03/2019 | 13/03/2019 | 0 | TK_Complete | -824745350 | 375 | -824745350_375
MML3RSTINT2140 | TT_Task | INT DSG:To provide details of emergency escape provision in tunnels | 10/09/2018 | 10/09/2018 | 22/01/2019 | 22/01/2019 | 0 | TK_Complete | -824745350 | 376 | -824745350_376
MML3RSTINT2150 | TT_Task | INT DSG:To provide maximum flood level | 13/03/2019 | 13/03/2019 | 13/03/2019 | 13/03/2019 | 0 | TK_Complete | -824745350 | 377 | -824745350_377
MML3RSTINT2160 | TT_Task | INT DSG:To provide station drawings showing the lift position w.r.f to platform | 13/03/2019 | 13/03/2019 | 13/03/2019 | 13/03/2019 | 0 | TK_Complete | -824745350 | 378 | -824745350_378
MML3RSTINT2170 | TT_Task | INT DSG:To provide details of tunnel design drawings showing cuves, clearences,gradients,chainages | 25/11/2019 | 25/11/2019 | 26/09/2019 | 26/09/2019 | 0 | TK_Complete | -824745350 | 375 | -824745350_375
MML3RSTINT2180 | TT_Task | INT DSG:To provide details of emergency escape provision in tunnels | 25/11/2019 | 25/11/2019 | 26/09/2019 | 26/09/2019 | 0 | TK_Complete | -824745350 | 376 | -824745350_376
MML3RSTINT2190 | TT_Task | INT DSG:To provide maximum flood level | 16/08/2019 | 16/08/2019 | 16/08/2019 | 16/08/2019 | 0 | TK_Complete | -824745350 | 377 | -824745350_377
MML3RSTINT2200 | TT_Task | INT DSG:To provide station drawings showing the lift position w.r.f to platform | 16/08/2019 | 16/08/2019 | 16/08/2019 | 16/08/2019 | 0 | TK_Complete | -824745350 | 378 | -824745350_378
MML3RSTINT2210 | TT_Task | INT DSG:To provide details of tunnel design drawings showing cuves, clearences,gradients,chainages | 11/09/2019 | 11/09/2019 | 11/09/2019 | 11/09/2019 | 0 | TK_Complete | -824745350 | 375 | -824745350_375
MML3RSTINT2220 | TT_Task | INT DSG:To provide details of emergency escape provision in tunnels | 11/09/2019 | 11/09/2019 | 11/09/2019 | 11/09/2019 | 0 | TK_Complete | -824745350 | 376 | -824745350_376
MML3RSTINT2230 | TT_Task | INT DSG:To provide maximum flood level | 11/09/2019 | 11/09/2019 | 11/09/2019 | 11/09/2019 | 0 | TK_Complete | -824745350 | 377 | -824745350_377
MML3RSTINT2240 | TT_Task | INT DSG:To provide station drawings showing the lift position w.r.f to platform | 25/11/2019 | 25/11/2019 | 11/09/2019 | 11/09/2019 | 0 | TK_Complete | -824745350 | 378 | -824745350_378
MML3RSTINT2250 | TT_Task | INT DSG:To provide details of tunnel design drawings showing cuves, clearences,gradients,chainages | 12/07/2019 | 12/07/2019 | 12/07/2019 | 12/07/2019 | 0 | TK_Complete | -824745350 | 375 | -824745350_375
MML3RSTINT2260 | TT_Task | INT DSG:To provide details of emergency escape provision in tunnels | 12/07/2019 | 12/07/2019 | 12/07/2019 | 12/07/2019 | 0 | TK_Complete | -824745350 | 376 | -824745350_376
MML3RSTINT2270 | TT_Task | INT DSG:To provide maximum flood level | 12/07/2019 | 12/07/2019 | 12/07/2019 | 12/07/2019 | 0 | TK_Complete | -824745350 | 377 | -824745350_377
MML3RSTINT2280 | TT_Task | INT DSG:To provide station drawings showing the lift position w.r.f to platform | 12/07/2019 | 12/07/2019 | 12/07/2019 | 12/07/2019 | 0 | TK_Complete | -824745350 | 378 | -824745350_378
MML3RSTINT2290 | TT_Task | INT DSG:To provide details of tunnel design drawings showing cuves, clearences,gradients,chainages | 23/07/2019 | 23/07/2019 | 23/07/2019 | 23/07/2019 | 0 | TK_Complete | -824745350 | 375 | -824745350_375
MML3RSTINT2300 | TT_Task | INT DSG:To provide details of emergency escape provision in tunnels | 04/03/2019 | 04/03/2019 | 04/03/2019 | 04/03/2019 | 0 | TK_Complete | -824745350 | 376 | -824745350_376
MML3RSTINT2310 | TT_Task | INT DSG:To provide maximum flood level | 23/07/2019 | 23/07/2019 | 23/07/2019 | 23/07/2019 | 0 | TK_Complete | -824745350 | 377 | -824745350_377
MML3RSTINT2320 | TT_Task | INT DSG:To provide station drawings showing the lift position w.r.f to platform | 18/04/2019 | 18/04/2019 | 18/04/2019 | 18/04/2019 | 0 | TK_Complete | -824745350 | 378 | -824745350_378
MML3RSTINT2330 | TT_Task | INT DSG:To provide details of tunnel design drawings showing cuves, clearences,gradients,chainages | 26/02/2019 | 26/02/2019 | 26/02/2019 | 26/02/2019 | 0 | TK_Complete | -824745350 | 375 | -824745350_375
MML3RSTINT2340 | TT_Task | INT DSG:To provide details of emergency escape provision in tunnels | 19/06/2019 | 19/06/2019 | 19/06/2019 | 19/06/2019 | 0 | TK_Complete | -824745350 | 376 | -824745350_376
MML3RSTINT2350 | TT_Task | INT DSG:To provide maximum flood level | 26/02/2019 | 26/02/2019 | 26/02/2019 | 26/02/2019 | 0 | TK_Complete | -824745350 | 377 | -824745350_377
MML3RSTINT2360 | TT_Task | INT DSG:To provide station drawings showing the lift position w.r.f to platform | 25/07/2019 | 25/07/2019 | 25/07/2019 | 25/07/2019 | 0 | TK_Complete | -824745350 | 378 | -824745350_378
MML3RSTINT2370 | TT_Task | INT DSG:To provide details of tunnel design drawings showing cuves, clearences,gradients,chainages | 05/03/2019 | 05/03/2019 | 05/03/2019 | 05/03/2019 | 0 | TK_Complete | -824745350 | 375 | -824745350_375
MML3RSTINT2380 | TT_Task | INT DSG:To provide details of emergency escape provision in tunnels | 05/03/2019 | 05/03/2019 | 05/03/2019 | 05/03/2019 | 0 | TK_Complete | -824745350 | 376 | -824745350_376
MML3RSTINT2390 | TT_Task | INT DSG:To provide maximum flood level | 12/03/2019 | 12/03/2019 | 12/03/2019 | 12/03/2019 | 0 | TK_Complete | -824745350 | 377 | -824745350_377
MML3RSTINT2400 | TT_Task | INT DSG:To provide station drawings showing the lift position w.r.f to platform | 12/03/2019 | 12/03/2019 | 12/03/2019 | 12/03/2019 | 0 | TK_Complete | -824745350 | 378 | -824745350_378
MML3RSTINT1030 | TT_Task | INT DSG:Complete details of track geometry, curves, gradients, Stiffness requirement relevant to rolling stock design | 25/09/2019 | 25/09/2019 | 17/05/2019 | 17/05/2019 | 0 | TK_Complete | -824745350 | 379 | -824745350_379
MML3RSTINT1040 | TT_Task | INT DSG:: Full details of Rail Hardness and Rail characteristics for wheel compatibility and optimum service life | 25/09/2019 | 25/09/2019 | 17/05/2019 | 17/05/2019 | 0 | TK_Complete | -824745350 | 379 | -824745350_379
MML3RSTINT1050 | TT_Task | INT DSG:: Final Track data for conducting the simulation of Traction and Braking (GAD) | 25/09/2019 | 25/09/2019 | 17/05/2019 | 17/05/2019 | 0 | TK_Complete | -824745350 | 380 | -824745350_380
MML3RSTINT1710 | TT_Task | INT DSG:: ATI Dimensions and provisions required | 25/09/2019 | 25/09/2019 | 17/05/2019 | 17/05/2019 | 0 | TK_Complete | -824745350 | 381 | -824745350_381
MML3RSTINT1000 | TT_Task | INT DSG:: Details of gradient of OCS to obtain smooth current collection | 15/10/2019 | 15/10/2019 | 15/10/2019 | 15/10/2019 | 0 | TK_Complete | -824745350 | 382 | -824745350_382
MML3RSTINT1010 | TT_Task | INT DSG:: OCS details incl material properties of contact wire to design Pantograph incl dimensions of collector strip | 01/07/2019 | 01/07/2019 | 01/07/2019 | 01/07/2019 | 0 | TK_Complete | -824745350 | 383 | -824745350_383
MML3RSTINT1020 | TT_Task | INT DSG:: Details of location, configuration and length of neutral sections | 07/08/2019 | 07/08/2019 | 07/08/2019 | 07/08/2019 | 0 | TK_Complete | -824745350 | 381 | -824745350_381
MML3RSTINT1060 | TT_Task | INT DSG:: STPT shall provide train radio to RS with instructions for location, mounting and ventilation of train radio | 10/09/2018 | 10/09/2018 | 05/09/2019 | 05/09/2019 | 0 | TK_Complete | -824745350 | 384 | -824745350_384
MML3RSTINT1070 | TT_Task | INT DSG: Train radio antenna with cabling to RS with instructions for location and mounting of train radio antenna | 10/09/2018 | 10/09/2018 | 05/09/2019 | 05/09/2019 | 0 | TK_Complete | -824745350 | 385 | -824745350_385
MML3RSTINT1080 | TT_Task | INT DSG: STPT shall provide train radio electrical power and earthing requirements to RSwith power cables and connectors | 10/09/2018 | 10/09/2018 | 05/09/2019 | 05/09/2019 | 0 | TK_Complete | -824745350 | 386 | -824745350_386
MML3RSTINT1090 | TT_Task | INT DSG: STPT Shall provide train radio controls, speaker, microphone and cables to RS with connection instructions. | 10/09/2018 | 10/09/2018 | 05/09/2019 | 05/09/2019 | 0 | TK_Complete | -824745350 | 384 | -824745350_384
MML3RSTINT1100 | TT_Task | INT DSG: Data interface details required for TCMS to display ATN identification to OCC for radio calls to and fro | 10/09/2018 | 10/09/2018 | 05/09/2019 | 05/09/2019 | 0 | TK_Complete | -824745350 | 387 | -824745350_387
MML3RSTINT1110 | TT_Task | INT DSG: Data interface details required for TCMS to provide train health data to OCC RS workstation. | 25/11/2019 | 25/11/2019 | 05/09/2019 | 05/09/2019 | 0 | TK_Complete | -824745350 | 388 | -824745350_388
MML3RSTINT1120 | TT_Task | INT DSG: Data and voice interface, protocol ; format details required for OCC originated announcement on RS PA system | 10/09/2018 | 10/09/2018 | 05/09/2019 | 05/09/2019 | 0 | TK_Complete | -824745350 | 387 | -824745350_387
MML3RSTINT1130 | TT_Task | INT DSG: Data required for OCC originated message on RS passenger information display system through radio in train | 05/09/2019 | 05/09/2019 | 05/09/2019 | 06/09/2019 | 0 | TK_Complete | -824745350 | 389 | -824745350_389
MML3RSTINT1140 | TT_Task | INT DSG: Data and voice interface details required for PEA alarm and voice communications between OCC and PEA | 10/09/2018 | 10/09/2018 | 05/09/2019 | 05/09/2019 | 0 | TK_Complete | -824745350 | 387 | -824745350_387
MML3RSTINT1150 | TT_Task | INT DSG: VTS radio and VTS equipment to RS with instructions for location, mounting and ventilation | 10/09/2018 | 10/09/2018 | 23/04/2019 | 23/04/2019 | 0 | TK_Complete | -824745350 | 385 | -824745350_385
MML3RSTINT1160 | TT_Task | INT DSG: VTS antenna and cable to RS with instructions for location and mounting. | 10/09/2018 | 10/09/2018 | 23/04/2019 | 23/04/2019 | 0 | TK_Complete | -824745350 | 385 | -824745350_385
MML3RSTINT1170 | TT_Task | INT DSG: Power supply details to interface VTS radio and VTS equipment with available electrical power in train | 10/09/2018 | 10/09/2018 | 23/04/2019 | 23/04/2019 | 0 | TK_Complete | -824745350 | 386 | -824745350_386
MML3RSTINT1180 | TT_Task | INT DSG: video interf details required by VTS for automatic RS PEA CCTV video from train to OCC caused by PEA activation | 10/09/2018 | 10/09/2018 | 23/04/2019 | 23/04/2019 | 0 | TK_Complete | -824745350 | 390 | -824745350_390
MML3RSTINT1190 | TT_Task | INT DSG: Video interface details required by VTS for RS CCTV video from train to OCC, selected by OCC | 10/09/2018 | 10/09/2018 | 23/04/2019 | 23/04/2019 | 0 | TK_Complete | -824745350 | 390 | -824745350_390
MML3RSTINT1200 | TT_Task | INT DSG: Maximum power consumed by STPT and equipment loads with required wire sizes and suggested circuit breaker sizes | 10/09/2018 | 10/09/2018 | 09/05/2019 | 09/05/2019 | 0 | TK_Complete | -824745350 | 391 | -824745350_391
MML3RSTINT1210 | TT_Task | INT DSG: Point-to-point destination of each train wire for all connections required with function of each for STPT | 10/09/2018 | 10/09/2018 | 09/05/2019 | 09/05/2019 | 0 | TK_Complete | -824745350 | 391 | -824745350_391
MML3RSTINT1220 | TT_Task | INT DSG: Control logic input / outputs required for Signalling, Train Control and Telecom equipment from / to RS | 10/09/2018 | 10/09/2018 | 05/09/2019 | 05/09/2019 | 0 | TK_Complete | -824745350 | 392 | -824745350_392
MML3RSTINT1230 | TT_Task | INT DSG: logic I /O required for Driving Mode (GOA4-GOA3-GOA2-Manual modes, Doors, Emergency, Help Point, Obstacle detec | 10/09/2018 | 10/09/2018 | 09/05/2019 | 09/05/2019 | 0 | TK_Complete | -824745350 | 392 | -824745350_392
MML3RSTINT1240 | TT_Task | INT DSG: Data input / outputs required for Driving Mode from / to RS | 10/09/2018 | 10/09/2018 | 09/05/2019 | 09/05/2019 | 0 | TK_Complete | -824745350 | 392 | -824745350_392
MML3RSTINT1250 | TT_Task | INT DSG: Data and logic I/O for Real Time Simulator and coordinate with RS the Design for Sotfware and Hardware | 05/09/2019 | 05/09/2019 | 05/09/2019 | 05/09/2019 | 0 | TK_Complete | -824745350 | 393 | -824745350_393
MML3RSTINT1260 | TT_Task | INT DSG: Electrical characteristics of the interconnection cabling and wiring for STPT | 10/09/2018 | 10/09/2018 | 05/09/2019 | 05/09/2019 | 0 | TK_Complete | -824745350 | 391 | -824745350_391
MML3RSTINT1270 | TT_Task | INT DSG: STPT Shall provide sensitivity levels and frequencies which must be avoided | 11/11/2019 | 11/11/2019 | 11/11/2019 | 11/11/2019 | 0 | TK_Complete | -824745350 | 394 | -824745350_394
MML3RSTINT1280 | TT_Task | INT DSG: Specific heat load for each Signalling, Train Control and Telecom equipment | 11/11/2019 | 11/11/2019 | 11/11/2019 | 12/11/2019 | 0 | TK_Complete | -824745350 | 395 | -824745350_395
MML3RSTINT1290 | TT_Task | INT DSG: EMC / EMI requirements to obviate interference in the operation of signalling and telecommunication equipment | 10/09/2018 | 10/09/2018 | 05/09/2019 | 05/09/2019 | 0 | TK_Complete | -824745350 | 396 | -824745350_396
MML3RSTINT1300 | TT_Task | INT DSG: Details of the RS provisions to enable the bidirectional transmission of data from the train to the wayside | 10/09/2018 | 10/09/2018 | 05/09/2019 | 05/09/2019 | 0 | TK_Complete | -824745350 | 397 | -824745350_397
MML3RSTINT1310 | TT_Task | INT DSG:Details of the provisions required for VTS video from the train to the OCC and video selection from OCC to train | 10/09/2018 | 10/09/2018 | 23/04/2019 | 23/04/2019 | 0 | TK_Complete | -824745350 | 390 | -824745350_390
MML3RSTINT1320 | TT_Task | INT DSG: Interface for recording the initiation, termination, and success or FAI/ FATlure of emergency calls | 06/12/2019 | 06/12/2019 | 06/12/2019 | 06/12/2019 | 0 | TK_Complete | -824745350 | 398 | -824745350_398
MML3RSTINT1330 | TT_Task | INT DSG: CBTC radio and CBTC equipment to RS with instructions for location, mounting and ventilation. | 10/09/2018 | 10/09/2018 | 04/09/2019 | 04/09/2019 | 0 | TK_Complete | -824745350 | 385 | -824745350_385
MML3RSTINT1340 | TT_Task | INT DSG: CBTC antenna and cable to RS with instructions for location and mounting | 10/09/2018 | 10/09/2018 | 04/09/2019 | 04/09/2019 | 0 | TK_Complete | -824745350 | 385 | -824745350_385
MML3RSTINT1350 | TT_Task | INT DSG: Electrical power and earthing requirements of CBTC radio and CBTC equipment to RS with cables and connectors | 10/09/2018 | 10/09/2018 | 04/09/2019 | 04/09/2019 | 0 | TK_Complete | -824745350 | 386 | -824745350_386
MML3RSTINT1360 | TT_Task | INT DSG: Interface details required by ST for RS TCMS data from train to OCC. | 10/09/2018 | 10/09/2018 | 04/09/2019 | 04/09/2019 | 0 | TK_Complete | -824745350 | 388 | -824745350_388
MML3RSTINT1370 | TT_Task | INT DSG: Details to RS of the Network Time Protocol for RS TCMS through CBTC | 10/09/2018 | 10/09/2018 | 04/09/2019 | 04/09/2019 | 0 | TK_Complete | -824745350 | 399 | -824745350_399
MML3RSTINT1380 | TT_Task | INT DSG: Interface details from Signalling System to provide next station announcement on RS public address system | 10/09/2018 | 10/09/2018 | 09/05/2019 | 09/05/2019 | 0 | TK_Complete | -824745350 | 400 | -824745350_400
MML3RSTINT1390 | TT_Task | INT DSG: Interface details required for Signalling ATC to receive the train integrity information from RS | 10/09/2018 | 10/09/2018 | 09/05/2019 | 09/05/2019 | 0 | TK_Complete | -824745350 | 397 | -824745350_397
MML3RSTINT1400 | TT_Task | INT DSG: Interface details from ATP/ATO/UTO for train braking and propulsion systems | 10/09/2018 | 10/09/2018 | 09/05/2019 | 09/05/2019 | 0 | TK_Complete | -824745350 | 401 | -824745350_401
MML3RSTINT1410 | TT_Task | INT DSG: Ethernet connection for the RS OCC workstation | 05/09/2019 | 05/09/2019 | 05/09/2019 | 05/09/2019 | 0 | TK_Complete | -824745350 | 388 | -824745350_388
MML3RSTINT1420 | TT_Task | INT DSG: Weight, dimensions, space required, mounting and fixing requirements etc. to install cubicles, antenna, etc | 10/09/2018 | 10/09/2018 | 05/09/2019 | 05/09/2019 | 0 | TK_Complete | -824745350 | 402 | -824745350_402
MML3RSTINT1430 | TT_Task | INT DSG: Mechanical requirements ; routing requirements of cabling for ST Systems | 10/09/2018 | 10/09/2018 | 05/09/2019 | 05/09/2019 | 0 | TK_Complete | -824745350 | 391 | -824745350_391
MML3RSTINT1440 | TT_Task | INT DSG: Details, application of use of train lines to RS Contractor | 10/09/2018 | 10/09/2018 | 09/05/2019 | 09/05/2019 | 0 | TK_Complete | -824745350 | 395 | -824745350_395
MML3RSTINT1450 | TT_Task | INT DSG: Details to RS Contractor of radio frequency to be used in train for CBTC system along with under floor Balise | 30/09/2019 | 30/09/2019 | 30/09/2019 | 30/09/2019 | 0 | TK_Complete | -824745350 | 395 | -824745350_395
MML3RSTINT1460 | TT_Task | INT DSG: Requirements for the automation of acceleration and braking system of the car. | 10/09/2018 | 10/09/2018 | 09/05/2019 | 09/05/2019 | 0 | TK_Complete | -824745350 | 380 | -824745350_380
MML3RSTINT1470 | TT_Task | INT DSG: Requirements of cab Signalling functions and control panel details. | 06/12/2019 | 06/12/2019 | 06/12/2019 | 06/12/2019 | 0 | TK_Complete | -824745350 | 392 | -824745350_392
MML3RSTINT1480 | TT_Task | INT DSG: Inputs to be made available for purpose of data logging of events to On-board data logger system | 06/12/2019 | 06/12/2019 | 06/12/2019 | 06/12/2019 | 0 | TK_Complete | -824745350 | 403 | -824745350_403
MML3RSTINT1490 | TT_Task | INT DSG: Provision to send remote commands from OCC to train and get feedback of the action taken | 10/09/2018 | 10/09/2018 | 09/05/2019 | 09/05/2019 | 0 | TK_Complete | -824745350 | 404 | -824745350_404
MML3RSTINT1500 | TT_Task | INT DSG: Details for installing under floor Transponder/Balise reading antenna and required location | 05/09/2019 | 05/09/2019 | 05/09/2019 | 05/09/2019 | 0 | TK_Complete | -824745350 | 402 | -824745350_402
MML3RSTINT1510 | TT_Task | INT DSG: Coordinate with RS for Door opening/Closing Sync time with PSD | 04/10/2019 | 04/10/2019 | 04/10/2019 | 04/10/2019 | 0 | TK_Complete | -824745350 | 393 | -824745350_393
MML3RSTINT1520 | TT_Task | INT DSG:Design to facilitate transition of driver cab as per grades of automation to changeover from STO to UTO/DTO mode | 04/04/2020 | 04/04/2020 | 04/04/2020 | 04/04/2020 | 0 | TK_Complete | -824745350 | 392 | -824745350_392
MML3RSTINT1530 | TT_Task | INT DSG: Operation of Passenger emergency stop devices as signalling distance calculation is more accurate | 25/12/2020 | 25/12/2020 | 20/12/2020 | 20/12/2020 | 0 | TK_Complete | -824745350 | 398 | -824745350_398
MML3RSTINT1540 | TT_Task | INT DSG: TCMS shall synchronize its clock with the system master clock through the ATP/ATO interface | 10/09/2018 | 10/09/2018 | 09/05/2019 | 09/05/2019 | 0 | TK_Complete | -824745350 | 399 | -824745350_399
MML3RSTINT1550 | TT_Task | INT DSG: Speed signal by ATC for Automatic speed calibration through GPS | 09/05/2019 | 09/05/2019 | 09/05/2019 | 09/05/2019 | 0 | TK_Complete | -824745350 | 405 | -824745350_405
MML3RSTINT1560 | TT_Task | INT DSG: Interface with ATC for remote intialization of train | 10/09/2018 | 10/09/2018 | 09/05/2019 | 09/05/2019 | 0 | TK_Complete | -824745350 | 397 | -824745350_397
MML3RSTINT1570 | TT_Task | INT DSG: Interface with ATC for automatic sleep function | 09/05/2019 | 09/05/2019 | 09/05/2019 | 09/05/2019 | 0 | TK_Complete | -824745350 | 406 | -824745350_406
MML3RSTINT1580 | TT_Task | INT DSG: Interface with ATC to be defined for Train standby function | 09/05/2019 | 09/05/2019 | 09/05/2019 | 09/05/2019 | 0 | TK_Complete | -824745350 | 406 | -824745350_406
MML3RSTINT1590 | TT_Task | INT DSG: Interface with ATC to be defined for Shunting operation | 09/05/2019 | 09/05/2019 | 09/05/2019 | 09/05/2019 | 0 | TK_Complete | -824745350 | 406 | -824745350_406
MML3RSTINT1600 | TT_Task | INT DSG: Interface ; design to be defined with ATC for UTO operation | 09/05/2019 | 09/05/2019 | 09/05/2019 | 09/05/2019 | 0 | TK_Complete | -824745350 | 406 | -824745350_406
MML3RSTINT1610 | TT_Task | INT DSG: Automatic Turn Back mode inputs | 09/05/2019 | 09/05/2019 | 09/05/2019 | 09/05/2019 | 0 | TK_Complete | -824745350 | 404 | -824745350_404
MML3RSTINT1620 | TT_Task | INT DSG: Interface for UTO mode of operation | 09/05/2019 | 09/05/2019 | 09/05/2019 | 09/05/2019 | 0 | TK_Complete | -824745350 | 406 | -824745350_406
MML3RSTINT1630 | TT_Task | INT DSG: Interface with signalling for Door operation | 09/05/2019 | 09/05/2019 | 09/05/2019 | 09/05/2019 | 0 | TK_Complete | -824745350 | 404 | -824745350_404
MML3RSTINT1640 | TT_Task | INT DSG: Interface with signalling for stop/over-run | 09/05/2019 | 09/05/2019 | 09/05/2019 | 09/05/2019 | 0 | TK_Complete | -824745350 | 404 | -824745350_404
MML3RSTINT1650 | TT_Task | INT DSG: Interface for undershoot/overshoot | 09/05/2019 | 09/05/2019 | 09/05/2019 | 09/05/2019 | 0 | TK_Complete | -824745350 | 406 | -824745350_406
MML3RSTINT1660 | TT_Task | INT DSG: Interface to finalize a list of commands ; respones for UTO mode which shall be present at CATS ; LATS | 09/05/2019 | 09/05/2019 | 09/05/2019 | 09/05/2019 | 0 | TK_Complete | -824745350 | 404 | -824745350_404
MML3RSTINT1670 | TT_Task | INT DSG: STPT to provide the requisite signal to Rolling Stock for the storage purpose | 09/05/2019 | 09/05/2019 | 09/05/2019 | 09/05/2019 | 0 | TK_Complete | -824745350 | 394 | -824745350_394
MML3RSTINT1680 | TT_Task | INT DSG: Two-way Communication between the Operations Control Centre (OCC) and train operator, via train radio equipment | 05/09/2019 | 05/09/2019 | 05/09/2019 | 05/09/2019 | 0 | TK_Complete | -824745350 | 389 | -824745350_389
MML3RSTINT1690 | TT_Task | INT DSG: Emergency passenger announcements on the train by OCC via train radio system | 05/09/2019 | 05/09/2019 | 05/09/2019 | 05/09/2019 | 0 | TK_Complete | -824745350 | 389 | -824745350_389
MML3RSTINT1700 | TT_Task | INT DSG: Inputs on bandwidth ; streams from all the cameras | 05/09/2019 | 05/09/2019 | 05/09/2019 | 05/09/2019 | 0 | TK_Complete | -824745350 | 67 | -824745350_67
MML3RSTINT2440 | TT_Task | INT DSG: Technical details(Technical/functional Interface/Electrical/Mechanical Interface/ equipments) from TR supplier | 25/12/2020 | 25/12/2020 | 15/12/2020 | 15/12/2020 | 0 | TK_Complete | -824745350 | 381 | -824745350_381
MML3RSTINT2450 | TT_Task | INT DSG: Technical Details(Layout, Functional interfaces) of ATS design. | 15/12/2020 | 15/12/2020 | 15/12/2020 | 15/12/2020 | 0 | TK_Complete | -824745350 | 381 | -824745350_381
MML3RSTINT1720 | TT_Task | INT DSG: Impedance value of OHE network for the harmonics analysis | 12/08/2019 | 12/08/2019 | 12/08/2019 | 12/08/2019 | 0 | TK_Complete | -824745350 | 407 | -824745350_407
MML3RSTINT1721 | TT_Task | INT DSG:DEM shall provide fire detection and fire detection and suppression system in simulator room | 09/08/2019 | 09/08/2019 | 09/08/2019 | 09/08/2019 | 0 | TK_Complete | -824745350 | 408 | -824745350_408
MML3RSTINT1731 | TT_Task | INT DSG:DEM Shall provide AC system for simulator room to achieve the designed room environment condition | 16/08/2019 | 16/08/2019 | 16/08/2019 | 16/08/2019 | 0 | TK_Complete | -824745350 | 408 | -824745350_408
MML3RSTINT1741 | TT_Task | INT DSG:RST SOD required for DRW Design works | 25/02/2022 | 18/04/2022 | nan | nan | 632 | TK_NotStart | -824745350 | 393 | -824745350_393
MML3RSTINT1730 | TT_Task | INT T;C:Joint Inspection and Confirm the maximum noise level w.r.t various operating speeds of RST | 28/03/2023 | 29/03/2023 | nan | nan | 384 | TK_NotStart | -824745350 | 409 | -824745350_409
MML3RSTINT2460 | TT_Task | INT T;C: shall be required to conduct integrated test with all systems | 28/03/2023 | 29/03/2023 | nan | nan | 384 | TK_NotStart | -824745350 | 410 | -824745350_410
MML3RSTINT1740 | TT_Task | INT T;C:Joint Inspection and Confirm the maximum noise level w.r.t various operating speeds of RST | 28/03/2023 | 29/03/2023 | nan | nan | 384 | TK_NotStart | -824745350 | 409 | -824745350_409
MML3RSTINT2470 | TT_Task | INT T;C: shall be required to conduct integrated test with all systems | 28/03/2023 | 29/03/2023 | nan | nan | 384 | TK_NotStart | -824745350 | 410 | -824745350_410
MML3RSTINT1750 | TT_Task | INT T;C:Joint Inspection and Confirm the maximum noise level w.r.t various operating speeds of RST | 28/03/2023 | 29/03/2023 | nan | nan | 384 | TK_NotStart | -824745350 | 409 | -824745350_409
MML3RSTINT2480 | TT_Task | INT T;C: shall be required to conduct integrated test with all systems | 28/03/2023 | 29/03/2023 | nan | nan | 384 | TK_NotStart | -824745350 | 410 | -824745350_410
MML3RSTINT1760 | TT_Task | INT T;C:Joint Inspection and Confirm the maximum noise level w.r.t various operating speeds of RST | 28/03/2023 | 29/03/2023 | nan | nan | 384 | TK_NotStart | -824745350 | 409 | -824745350_409
MML3RSTINT2490 | TT_Task | INT T;C: shall be required to conduct integrated test with all systems | 28/03/2023 | 29/03/2023 | nan | nan | 384 | TK_NotStart | -824745350 | 410 | -824745350_410
MML3RSTINT1770 | TT_Task | INT T;C:Joint Inspection and Confirm the maximum noise level w.r.t various operating speeds of RST | 28/03/2023 | 29/03/2023 | nan | nan | 384 | TK_NotStart | -824745350 | 409 | -824745350_409
MML3RSTINT2500 | TT_Task | INT T;C: shall be required to conduct integrated test with all systems | 28/03/2023 | 29/03/2023 | nan | nan | 384 | TK_NotStart | -824745350 | 410 | -824745350_410
MML3RSTINT1780 | TT_Task | INT T;C:Joint Inspection and Confirm the maximum noise level w.r.t various operating speeds of RST | 28/03/2023 | 29/03/2023 | nan | nan | 384 | TK_NotStart | -824745350 | 409 | -824745350_409
MML3RSTINT2510 | TT_Task | INT T;C: shall be required to conduct integrated test with all systems | 28/03/2023 | 29/03/2023 | nan | nan | 384 | TK_NotStart | -824745350 | 410 | -824745350_410
MML3RSTINT1790 | TT_Task | INT T;C:Joint Inspection and Confirm the maximum noise level w.r.t various operating speeds of RST | 28/03/2023 | 29/03/2023 | nan | nan | 384 | TK_NotStart | -824745350 | 409 | -824745350_409
MML3RSTINT2520 | TT_Task | INT T;C: shall be required to conduct integrated test with all systems | 28/03/2023 | 29/03/2023 | nan | nan | 384 | TK_NotStart | -824745350 | 410 | -824745350_410
MML3RSTINT1800 | TT_Task | INT T;C:OCS shall conduct current collection test jointly and adjust OCS to have smooth current collection | 23/04/2023 | 24/04/2023 | nan | nan | 176 | TK_NotStart | -824745350 | 382 | -824745350_382
MML3RSTINT1810 | TT_Task | INT T;C:OCS shall ensure reliable 25KV OCS system for T;C of metro cars | 23/04/2023 | 24/04/2023 | nan | nan | 176 | TK_NotStart | -824745350 | 411 | -824745350_411
MML3RSTINT1820 | TT_Task | INT T;C:OCS Shall ensure reliable with RST for testing of the neutral section detector | 01/01/2023 | 02/01/2023 | nan | nan | 448 | TK_NotStart | -824745350 | 412 | -824745350_412
MML3RSTINT1830 | TT_Task | INT T;C:OCS shall provide 25KV power supply to OHE for T;C of metro cars in depot and mainline | 17/11/2022 | 18/11/2022 | nan | nan | 808 | TK_NotStart | -824745350 | 411 | -824745350_411
MML3RSTINT1840 | TT_Task | INT T;C:OCS Shall verify that the maximum power requirements | 17/11/2022 | 18/11/2022 | nan | nan | 808 | TK_NotStart | -824745350 | 411 | -824745350_411
MML3RSTINT1850 | TT_Task | INT T;C:TWK shall provide necessary support to the RST contract during T;C of the RST and attend pilot train run test | 29/01/2023 | 30/01/2023 | nan | nan | 224 | TK_NotStart | -824745350 | 413 | -824745350_413
MML3RSTINT1851 | TT_Task | INT T;C:STPT Shall Prepare an integrated test plan covering real time simulatorr | 21/01/2023 | 25/01/2023 | nan | nan | 272 | TK_NotStart | -824745350 | 414 | -824745350_414
MML3RSTINT1852 | TT_Task | INT T;C:STPT Shall Prepare an integrated test plan covering prototype trains | 23/03/2022 | 27/03/2022 | nan | nan | 1 | TK_NotStart | -824745350 | 414 | -824745350_414
MML3RSTINT1853 | TT_Task | INT T;C:STPT Shall Prepare an integrated test plan covering other trains | 20/04/2022 | 24/04/2022 | nan | nan | 584 | TK_NotStart | -824745350 | 414 | -824745350_414
MML3RSTINT1860 | TT_Task | INT T;C:Jointly test the train radio from the driver control panel | 01/01/2023 | 02/01/2023 | nan | nan | 448 | TK_NotStart | -824745350 | 415 | -824745350_415
MML3RSTINT1870 | TT_Task | INT T;C:Jointly test the interface between the train radio and TCMS | 01/01/2023 | 02/01/2023 | nan | nan | 448 | TK_NotStart | -824745350 | 415 | -824745350_415
MML3RSTINT1880 | TT_Task | INT T;C:Jointly test the interface between the train radio and TCMS to provide train health data | 01/01/2023 | 02/01/2023 | nan | nan | 448 | TK_NotStart | -824745350 | 415 | -824745350_415
MML3RSTINT1890 | TT_Task | INT T;C:Jointly test the interface between train radio and the RS public address sysytem for OCC RS work station | 01/01/2023 | 02/01/2023 | nan | nan | 448 | TK_NotStart | -824745350 | 415 | -824745350_415
MML3RSTINT1900 | TT_Task | INT T;C:Jointly test the interface between train radio and the RS Passengers information signs for OCC orginated message | 01/01/2023 | 02/01/2023 | nan | nan | 448 | TK_NotStart | -824745350 | 415 | -824745350_415
MML3RSTINT1910 | TT_Task | INT T;C:Jointly test the voice and data interface between the train radio and RS passengers emergency alarm | 01/01/2023 | 02/01/2023 | nan | nan | 448 | TK_NotStart | -824745350 | 415 | -824745350_415
MML3RSTINT1920 | TT_Task | INT T;C:Jointly test the VTS video from the train to the wayside and video selection from wayside to train | 22/01/2023 | 23/01/2023 | nan | nan | 280 | TK_NotStart | -824745350 | 390 | -824745350_390
MML3RSTINT1930 | TT_Task | INT T;C:Jointly test the video interface between the VTS equipment and RS CCTV | 22/01/2023 | 23/01/2023 | nan | nan | 280 | TK_NotStart | -824745350 | 390 | -824745350_390
MML3RSTINT1940 | TT_Task | INT T;C:Jointly test the retrieval of RS camera stored video | 01/01/2023 | 02/01/2023 | nan | nan | 448 | TK_NotStart | -824745350 | 416 | -824745350_416
MML3RSTINT1950 | TT_Task | INT T;C:Jointly test the bidirectional transmission of data from the train to the wayside | 22/01/2023 | 23/01/2023 | nan | nan | 280 | TK_NotStart | -824745350 | 415 | -824745350_415
MML3RSTINT1960 | TT_Task | INT T;C:Jointly test the RS TCMS to receive the Network time protocol from signalling system CBTC | 22/01/2023 | 23/01/2023 | nan | nan | 280 | TK_NotStart | -824745350 | 399 | -824745350_399
MML3RSTINT1970 | TT_Task | INT T;C:Jointly test the next station announcement on RS public address system | 22/01/2023 | 23/01/2023 | nan | nan | 280 | TK_NotStart | -824745350 | 400 | -824745350_400
MML3RSTINT1980 | TT_Task | INT T;C:Jointky test the next station announcement on RS public address system | 22/01/2023 | 23/01/2023 | nan | nan | 280 | TK_NotStart | -824745350 | 400 | -824745350_400
MML3RSTINT1990 | TT_Task | INT T;C:Jointly test the RS interface with the signalling ATC to provide train integrity information on board ATC | 22/01/2023 | 23/01/2023 | nan | nan | 280 | TK_NotStart | -824745350 | 397 | -824745350_397
MML3RSTINT2000 | TT_Task | INT T;C:Jointly test the RS TCMS to interface with signalling sysytem for pantograph management | 22/01/2023 | 23/01/2023 | nan | nan | 280 | TK_NotStart | -824745350 | 399 | -824745350_399
MML3RSTINT2010 | TT_Task | INT T;C:Jointly test the interface for ATP/ATO to provide automatic backing and automatic acceleration | 22/01/2023 | 23/01/2023 | nan | nan | 280 | TK_NotStart | -824745350 | 401 | -824745350_401
MML3RSTINT2020 | TT_Task | INT T;C:Jointly test all train lines used by STPT between cars | 22/01/2023 | 23/01/2023 | nan | nan | 280 | TK_NotStart | -824745350 | 415 | -824745350_415
MML3RSTINT2030 | TT_Task | INT T;C:Jointly test the train fire alarm to OCC when train is operated in all driving modes | 01/01/2023 | 02/01/2023 | nan | nan | 448 | TK_NotStart | -824745350 | 415 | -824745350_415
MML3RSTINT2040 | TT_Task | INT T;C:Jointly test the RS on Board data logger system record events from ST | 22/01/2023 | 23/01/2023 | nan | nan | 280 | TK_NotStart | -824745350 | 403 | -824745350_403
MML3RSTINT2050 | TT_Task | INT T;C:Jointly test the neutral section detector to maintain required speed and braking profile | 22/01/2023 | 23/01/2023 | nan | nan | 280 | TK_NotStart | -824745350 | 412 | -824745350_412
MML3RSTINT2060 | TT_Task | INT T;C:Jointly test the ODM used by RST to control braking if obstruction is detected during UTO mode of operation | 22/01/2023 | 23/01/2023 | nan | nan | 280 | TK_NotStart | -824745350 | 412 | -824745350_412
MML3RSTINT2070 | TT_Task | INT T;C:Provision shall be made for remote wake up ; Self check, when required | 22/01/2023 | 23/01/2023 | nan | nan | 280 | TK_NotStart | -824745350 | 417 | -824745350_417
MML3RSTINT2080 | TT_Task | INT T;C:Joint testing of TCMS,breaking system,Operation of train in all modes,ADS,ATS and AVI system on test track | 22/01/2023 | 23/01/2023 | nan | nan | 280 | TK_NotStart | -824745350 | 418 | -824745350_418
MML3RSTINT2090 | TT_Task | INT T;C:Joint testing on the main line for TCMS,breaking system,operation of train in all modes,ADS,AVI system etc... | 22/01/2023 | 23/01/2023 | nan | nan | 280 | TK_NotStart | -824745350 | 418 | -824745350_418
MML3RSTINT2100 | TT_Task | INT T;C:STPT Shall check and verify if data logging for the system is functioning properly | 22/01/2023 | 23/01/2023 | nan | nan | 280 | TK_NotStart | -824745350 | 403 | -824745350_403
MML3RSTINT2110 | TT_Task | INT T;C:Joint test Demonstrating that Depot equipment are adapted and complaint to RST characteristics and requiremnets | 29/08/2022 | 30/08/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 419 | -824745350_419
MML3RSTINT2120 | TT_Task | INT T;C:CWD Shall conduct tests demonstrating that Depot Maintanence facilities suit RST | 29/08/2022 | 30/08/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 419 | -824745350_419
MML3RSTINT2125 | TT_Task | INT T;C:AMS Shall jointly test the functionality of Asset management system software according to the need of RST | 29/08/2022 | 30/08/2022 | nan | nan | 1448 | TK_NotStart | -824745350 | 420 | -824745350_420
MML3RSTINS1280 | TT_Task | INT CON:Joint inspection and confirm curves,gradients,chainages,levels and emergency escape provision | 29/08/2022 | 30/08/2022 | nan | nan | 320 | TK_NotStart | -824745350 | 421 | -824745350_421
MML3RSTINS1610 | TT_Task | INT CON:Conducting Test run and do modifications if required | 29/01/2023 | 30/01/2023 | nan | nan | 184 | TK_NotStart | -824745350 | 422 | -824745350_422
MML3RSTINS1290 | TT_Task | INT CON:Joint inspection and confirm curves,gradients,chainages,levels and emergency escape provision | 29/08/2022 | 30/08/2022 | nan | nan | 320 | TK_NotStart | -824745350 | 421 | -824745350_421
MML3RSTINS1620 | TT_Task | INT CON:Conducting Test run and do modifications if required | 29/01/2023 | 30/01/2023 | nan | nan | 184 | TK_NotStart | -824745350 | 422 | -824745350_422
MML3RSTINS1300 | TT_Task | INT CON:Joint inspection and confirm curves,gradients,chainages,levels and emergency escape provision | 29/08/2022 | 30/08/2022 | nan | nan | 320 | TK_NotStart | -824745350 | 421 | -824745350_421
MML3RSTINS1630 | TT_Task | INT CON:Conducting Test run and do modifications if required | 29/01/2023 | 30/01/2023 | nan | nan | 184 | TK_NotStart | -824745350 | 422 | -824745350_422
MML3RSTINS1310 | TT_Task | INT CON:Joint inspection and confirm curves,gradients,chainages,levels and emergency escape provision | 29/08/2022 | 30/08/2022 | nan | nan | 320 | TK_NotStart | -824745350 | 421 | -824745350_421
MML3RSTINS1640 | TT_Task | INT CON:Conducting Test run and do modifications if required | 29/01/2023 | 30/01/2023 | nan | nan | 184 | TK_NotStart | -824745350 | 422 | -824745350_422
MML3RSTINS1320 | TT_Task | INT CON::Joint inspection and confirm curves,gradients,chainages,levels and emergency escape provision | 29/08/2022 | 30/08/2022 | nan | nan | 320 | TK_NotStart | -824745350 | 421 | -824745350_421
MML3RSTINS1650 | TT_Task | INT CON:Conducting Test run and do modifications if required | 29/01/2023 | 30/01/2023 | nan | nan | 184 | TK_NotStart | -824745350 | 422 | -824745350_422
MML3RSTINS1330 | TT_Task | INT CON:Joint inspection and confirm curves,gradients,chainages,levels and emergency escape provision | 29/08/2022 | 30/08/2022 | nan | nan | 320 | TK_NotStart | -824745350 | 421 | -824745350_421
MML3RSTINS1660 | TT_Task | INT CON:Conducting Test run and do modifications if required | 27/01/2023 | 29/01/2023 | nan | nan | 200 | TK_NotStart | -824745350 | 422 | -824745350_422
MML3RSTINS1340 | TT_Task | INT CON:Joint inspection and confirm curves,gradients,chainages,levels and emergency escape provision | 29/08/2022 | 30/08/2022 | nan | nan | 320 | TK_NotStart | -824745350 | 421 | -824745350_421
MML3RSTINS1670 | TT_Task | INT CON:Conducting Test run and do modifications if required | 29/01/2023 | 30/01/2023 | nan | nan | 184 | TK_NotStart | -824745350 | 422 | -824745350_422
MML3RSTINS1350 | TT_Task | INT CON:OCS shall supply and install visual indication at OCS neutral section locations | 29/08/2022 | 30/08/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 423 | -824745350_423
MML3RSTINS1360 | TT_Task | INT CON:TWk shall check/verify the right feasibility for train evacuation path | 29/08/2022 | 30/08/2022 | nan | nan | 320 | TK_NotStart | -824745350 | 413 | -824745350_413
MML3RSTINS1370 | TT_Task | INT CON:Providing to RS the train radios,antennas,cabling,installation materials and controls and supervision by RS | 06/04/2021 | 06/04/2021 | 06/04/2021 | 06/04/2021 | 0 | TK_Complete | -824745350 | 384 | -824745350_384
MML3RSTINS1380 | TT_Task | INT CON:STPT shall provide to RS the equipment for interface between the train radio and the TCMS | 25/04/2021 | 25/04/2021 | 06/04/2021 | 06/04/2021 | 0 | TK_Complete | -824745350 | 384 | -824745350_384
MML3RSTINS1390 | TT_Task | INT CON:STPT shall provide to RS the equipment for interface between the train radio and the TCMS | 06/04/2021 | 06/04/2021 | 06/04/2021 | 06/04/2021 | 0 | TK_Complete | -824745350 | 384 | -824745350_384
MML3RSTINS1400 | TT_Task | INT CON:STPT shall provide to RS the equipment for the data and voice interface for OCC on RS Public address system | 06/04/2021 | 06/04/2021 | 06/04/2021 | 06/04/2021 | 0 | TK_Complete | -824745350 | 424 | -824745350_424
MML3RSTINS1410 | TT_Task | INT CON:STPT shall provide to RS the equipment for the data interface required for OCC on RS PIDS | 06/04/2021 | 06/04/2021 | 06/04/2021 | 06/04/2021 | 0 | TK_Complete | -824745350 | 424 | -824745350_424
MML3RSTINS1420 | TT_Task | INT CON:STPT shall provide to RS the equipment for data;voice interface for PEA alarm;voice coomunication B/W OCC;PEA | 06/04/2021 | 06/04/2021 | 06/04/2021 | 06/04/2021 | 0 | TK_Complete | -824745350 | 424 | -824745350_424
MML3RSTINS1430 | TT_Task | INT CON:STPT shall provide to RS the VTS radios,antennas,cabing and installation materials and supervise by RS | 06/04/2021 | 06/04/2021 | 06/04/2021 | 06/04/2021 | 0 | TK_Complete | -824745350 | 384 | -824745350_384
MML3RSTINS1440 | TT_Task | INT CON:STPT shall provide to RS the materials for video interface to VTS from RS PEA CCTV video from train to OCC | 06/04/2021 | 06/04/2021 | 06/04/2021 | 06/04/2021 | 0 | TK_Complete | -824745350 | 390 | -824745350_390
MML3RSTINS1450 | TT_Task | INT CON:STPT shall install the interface required for retrieval of RS camera video RS supervision | 06/04/2021 | 06/04/2021 | 06/04/2021 | 06/04/2021 | 0 | TK_Complete | -824745350 | 416 | -824745350_416
MML3RSTINS1460 | TT_Task | INT CON:STPT shall Provide to RS the CBTC radios ,antennas,cabling,installation materials and supervise by RS | 06/04/2021 | 06/04/2021 | 06/04/2021 | 06/04/2021 | 0 | TK_Complete | -824745350 | 384 | -824745350_384
MML3RSTINS1470 | TT_Task | INT CON:STPT shall Provide to RS the materials for data interface to CBTC from RS TCMS from train to OCC | 06/04/2021 | 06/04/2021 | 06/04/2021 | 06/04/2021 | 0 | TK_Complete | -824745350 | 388 | -824745350_388
MML3RSTINS1480 | TT_Task | INT CON:STPT shall provide the on-board ATC System equipments fro real time simulator and for the integration | 06/04/2021 | 06/04/2021 | 06/04/2021 | 06/04/2021 | 0 | TK_Complete | -824745350 | 425 | -824745350_425
MML3RSTINS1490 | TT_Task | INT CON:STPT shall supply the on-board ATC system equipment for all rakes to the RS contractor including prototype rakes | 06/04/2021 | 06/04/2021 | 06/04/2021 | 06/04/2021 | 0 | TK_Complete | -824745350 | 425 | -824745350_425
MML3RSTINS1500 | TT_Task | INT CON:STPT sahll supply of interface hardware b/w ATC;train braking and propulsion system | 06/04/2021 | 06/04/2021 | 06/04/2021 | 06/04/2021 | 0 | TK_Complete | -824745350 | 425 | -824745350_425
MML3RSTINS1510 | TT_Task | INT CON:STPT shall ensure that S;Tcables are installed with adequate seperation without mixing with other cables | 18/06/2021 | 18/06/2021 | 18/06/2021 | 18/06/2021 | 0 | TK_Complete | -824745350 | 426 | -824745350_426
MML3RSTINS1520 | TT_Task | INT CON:STPT shall check the interconnection b/w TCMS and ATC;train ratdio equipments | 18/06/2021 | 18/06/2021 | 18/06/2021 | 18/06/2021 | 0 | TK_Complete | -824745350 | 426 | -824745350_426
MML3RSTINS1530 | TT_Task | INT CON:STPT shall check and confirm the requirements of Earthing arrangement | 18/06/2021 | 18/06/2021 | 18/06/2021 | 18/06/2021 | 0 | TK_Complete | -824745350 | 245 | -824745350_245
MML3RSTINS1540 | TT_Task | INT CON:Provision shall be made for remote wake up ; self-check,when required | 18/06/2021 | 18/06/2021 | 18/06/2021 | 18/06/2021 | 0 | TK_Complete | -824745350 | 417 | -824745350_417
MML3RSTINS1550 | TT_Task | INT CON:CWD shall ensure conformance to design parameters during Depot Maintanence facilities construction | 29/08/2022 | 30/08/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 427 | -824745350_427
MML3RSTINS1560 | TT_Task | INT CON:CWD shall inform RST with any Depot Maintanence facilities Evolution and updating | 29/08/2022 | 30/08/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 419 | -824745350_419
MML3RSTINS1570 | TT_Task | INT CON:CWD shall provide base foundation and electrical power cable and compressed air line | 29/08/2022 | 30/08/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 428 | -824745350_428
MML3RSTINS1580 | TT_Task | INT CON:DEQ shall ensure confirmance to design parameters during manufacturing Depot Equipment | 29/08/2022 | 30/08/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 427 | -824745350_427
MML3RSTINS1590 | TT_Task | INT CON:DEQ shall inform RST with any Depot Equioment evolution and updating | 29/08/2022 | 30/08/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 419 | -824745350_419
MML3RSTINS1600 | TT_Task | INT CON:AMS Shall provide the connectivity arrangements for AMCP software at the designated locations decided by Project | 17/05/2023 | 18/05/2023 | nan | nan | 2240 | TK_NotStart | -824745350 | 429 | -824745350_429
MML3RSTINS1680 | TT_Task | INT CON:TVE to check the location of AC,Braking traction equipment etc...to provide over track/under platform ducts | 02/09/2022 | 03/09/2022 | nan | nan | 288 | TK_NotStart | -824745350 | 430 | -824745350_430
MML3RSTINS1690 | TT_Task | INT CON:TVE to check the location of AC,Braking traction equipment etc...to provide over track/under platform ducts | 02/09/2022 | 03/09/2022 | nan | nan | 288 | TK_NotStart | -824745350 | 430 | -824745350_430
MML3RSTINS1700 | TT_Task | INT CON:TVE to check the location of AC,Braking traction equipment etc...to provide over track/under platform ducts | 02/09/2022 | 03/09/2022 | nan | nan | 288 | TK_NotStart | -824745350 | 430 | -824745350_430
MML3RSTINT2410 | TT_Task | INT CON:Maintenance manual supply and agreed by both the parties | 26/09/2022 | 27/09/2022 | nan | nan | 760 | TK_NotStart | -824745350 | 431 | -824745350_431
MML3RSTINT2420 | TT_Task | INT CON:DEQ shall prepare and provide Maintenance manual of supplied Depot Equipment | 29/08/2022 | 30/08/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 427 | -824745350_427
MML3RSTINT2430 | TT_Task | INT CON:AMS Shall jointly accept and agree as per maintenance specifications | 17/05/2023 | 18/05/2023 | nan | nan | 2240 | TK_NotStart | -824745350 | 431 | -824745350_431
MML3RSTINS1010 | TT_Task | INS Design: Proposal for constrcution of site office ; warehouse | 25/02/2022 | 06/03/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 432 | -824745350_432
MML3RSTINS1011 | TT_Task | INS Review/ Comments from Project Manager: Proposal for constrcution of site office | 07/03/2022 | 13/03/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 433 | -824745350_433
MML3RSTINS1012 | TT_Task | INS Resubmission by Alstom: Proposal for constrcution of site office | 14/03/2022 | 20/03/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 433 | -824745350_433
MML3RSTINS1013 | TT_Task | INS NONO/ NOWC from Project Manager: Proposal for constrcution of site office | 21/03/2022 | 03/04/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 433 | -824745350_433
MML3RSTINS1015 | TT_Task | INS Site Clearence and Preparation for SIte office / Warehouse Construction | 07/03/2022 | 26/03/2022 | nan | nan | 64 | TK_NotStart | -824745350 | 432 | -824745350_432
MML3RSTINS1016 | TT_Task | INS Foundation work for Site office/ Warehouse Construction | 04/04/2022 | 18/04/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 432 | -824745350_432
MML3RSTINS1018 | TT_Task | INS Construction of Walls ; Columns for Site office / Warehouse Construction | 19/04/2022 | 03/05/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 434 | -824745350_434
MML3RSTINS1023 | TT_Task | INS Construction PLinth Wall ; Beams for Site office / Warehouse Construction | 04/05/2022 | 23/05/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 434 | -824745350_434
MML3RSTINS1024 | TT_Task | INS Interior works in Site office / Warehouse | 24/05/2022 | 12/06/2022 | nan | nan | 536 | TK_NotStart | -824745350 | 432 | -824745350_432
MML3RSTINS1025 | TT_Task | INS Finishing Works(Plastering, Expansion Joints etc..) of Site Office / Warehouse | 19/08/2022 | 28/08/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 432 | -824745350_432
MML3RSTINS1026 | TT_Task | INS Handover of Site Office and any other temporary facilities at Depot | 22/02/2026 | 22/02/2026 | nan | nan | 576 | TK_NotStart | -824745350 | 432 | -824745350_432
MML3RSTT&amp;C1000 | TT_Task | T;C RST Procedure: Preparation ; Submission of Test Procedure to Project Manager | 19/10/2020 | 19/10/2020 | 19/10/2020 | 19/10/2020 | 0 | TK_Complete | -824745350 | 435 | -824745350_435
MML3RSTT&amp;C1010 | TT_Task | T;C RST Procedure: Receipt of Comments from Project Manager | 20/10/2020 | 02/11/2020 | 20/10/2020 | 03/05/2021 | 0 | TK_Complete | -824745350 | 436 | -824745350_436
MML3RSTT&amp;C1030 | TT_Task | T;C RST Procedure: Resubmission of Test Procedure incorporating Project Manager comments | 04/05/2021 | 18/05/2021 | 04/05/2021 | 18/05/2021 | 0 | TK_Complete | -824745350 | 437 | -824745350_437
MML3RSTT&amp;C1040 | TT_Task | T;C RST Procedure: NONO/ NOWC from Project Manager | 18/05/2021 | 19/05/2021 | 18/05/2021 | 19/05/2021 | 0 | TK_Complete | -824745350 | 438 | -824745350_438
MML3RSTT&amp;C1020 | TT_Task | T;C NRT Procedure: Submission of Test Procedure to Project Manager | 19/05/2021 | 19/05/2021 | 19/05/2021 | 19/05/2021 | 0 | TK_Complete | -824745350 | 435 | -824745350_435
MML3RSTT&amp;C1050 | TT_Task | T;C NRT Procedure: Receipt of Comments from Project Manager | 12/11/2020 | 25/11/2020 | 12/11/2020 | 22/07/2021 | 0 | TK_Complete | -824745350 | 436 | -824745350_436
MML3RSTT&amp;C1070 | TT_Task | T;C NRT Procedure: Resubmission of Test Procedure incorporating Project Manager comments | 19/05/2021 | 22/07/2021 | 19/05/2021 | 22/07/2021 | 0 | TK_Complete | -824745350 | 437 | -824745350_437
MML3RSTT&amp;C1080 | TT_Task | T;C NRT Procedure: NONO/ NOWC from Project Manager | 23/07/2021 | 28/07/2021 | 23/07/2021 | 28/07/2021 | 0 | TK_Complete | -824745350 | 438 | -824745350_438
MML3RSTT&amp;C1060 | TT_Task | T;C RDT Procedure: Submission of Test Procedure to Project Manager | 27/10/2020 | 27/10/2020 | 27/10/2020 | 27/10/2020 | 0 | TK_Complete | -824745350 | 435 | -824745350_435
MML3RSTT&amp;C1090 | TT_Task | T;C RDT Procedure: Receipt of Comments from Project Manager | 28/10/2020 | 10/11/2020 | 28/10/2020 | 17/11/2020 | 0 | TK_Complete | -824745350 | 436 | -824745350_436
MML3RSTT&amp;C1110 | TT_Task | T;C RDT Procedure: Resubmission of Test Procedure incorporating Project Manager comments | 18/11/2020 | 25/01/2021 | 18/11/2020 | 25/01/2021 | 0 | TK_Complete | -824745350 | 437 | -824745350_437
MML3RSTT&amp;C1120 | TT_Task | T;C RDT Procedure: NONO/ NOWC from Project Manager | 26/01/2021 | 09/02/2021 | 26/01/2021 | 09/02/2021 | 0 | TK_Complete | -824745350 | 438 | -824745350_438
MML3RSTT&amp;C1100 | TT_Task | T;C STT Procedure: Submission of Test Procedure to Project Manager | 27/10/2020 | 27/10/2020 | 27/10/2020 | 27/10/2020 | 0 | TK_Complete | -824745350 | 435 | -824745350_435
MML3RSTT&amp;C1130 | TT_Task | T;C STT Procedure: Receipt of Comments from Project Manager | 28/10/2020 | 17/11/2020 | 28/10/2020 | 17/11/2020 | 0 | TK_Complete | -824745350 | 436 | -824745350_436
MML3RSTT&amp;C1140 | TT_Task | T;C STT Procedure: Resubmission of Test Procedure incorporating Project Manager comments | 18/11/2020 | 25/01/2021 | 18/11/2020 | 25/01/2021 | 0 | TK_Complete | -824745350 | 437 | -824745350_437
MML3RSTT&amp;C1150 | TT_Task | T;C STT Procedure: NONO/ NOWC from Project Manager | 26/01/2021 | 09/02/2021 | 26/01/2021 | 09/02/2021 | 0 | TK_Complete | -824745350 | 438 | -824745350_438
MML3RSTMFG4500 | TT_Task | First Submission by Alstom: Cars Unloading Method statement | 07/03/2022 | 11/03/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 439 | -824745350_439
MML3RSTMFG4510 | TT_Task | First Submission by Alstom: Configuration ; Change Management Method statement | 04/05/2022 | 08/05/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 15 | -824745350_15
MML3RSTMFG4520 | TT_Task | First Submission by Alstom: Site Warehouse Management method statement | 04/05/2022 | 08/05/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 440 | -824745350_440
MML3RSTMFG4530 | TT_Task | First Submission by Alstom: Site Warranty Management method statement | 04/05/2022 | 08/05/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 441 | -824745350_441
MML3RSTMFG4660 | TT_Task | First Submission by Alstom: Manufacturing Process Statement | 26/01/2020 | 03/02/2020 | 16/12/2019 | 16/12/2019 | 0 | TK_Complete | -824745350 | 9 | -824745350_9
MML3RSTMFG4540 | TT_Task | Review/ Comments from Project Manager: Cars Unloading Method statement | 12/03/2022 | 18/03/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 439 | -824745350_439
MML3RSTMFG4550 | TT_Task | Review/ Comments from Project Manager: Configuration ; Change Management Method statement | 09/05/2022 | 15/05/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 32 | -824745350_32
MML3RSTMFG4560 | TT_Task | Review/ Comments from Project Manager: Site Warehouse Management method statement | 09/05/2022 | 15/05/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 440 | -824745350_440
MML3RSTMFG4570 | TT_Task | Review/ Comments from Project Manager: Site Warranty Management method statement | 09/05/2022 | 15/05/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 441 | -824745350_441
MML3RSTMFG4670 | TT_Task | Review/ Comments from Project Manager: Manufacturing Process Statement | 26/01/2020 | 08/02/2020 | 08/01/2020 | 08/01/2020 | 0 | TK_Complete | -824745350 | 34 | -824745350_34
MML3RSTMFG4580 | TT_Task | Resubmission by Alstom: Cars Unloading Method statement | 19/03/2022 | 25/03/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 439 | -824745350_439
MML3RSTMFG4590 | TT_Task | Resubmission by Alstom: Configuration ; Change Management Method statement | 16/05/2022 | 22/05/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 15 | -824745350_15
MML3RSTMFG4600 | TT_Task | Resubmission by Alstom: Site Warehouse Management method statement | 16/05/2022 | 22/05/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 440 | -824745350_440
MML3RSTMFG4610 | TT_Task | Resubmission by Alstom: Site Warranty Management method statement | 16/05/2022 | 22/05/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 441 | -824745350_441
MML3RSTMFG4680 | TT_Task | Resubmission by Alstom: Manufacturing Process Statement | 02/06/2021 | 02/06/2021 | 02/06/2021 | 02/06/2021 | 0 | TK_Complete | -824745350 | 9 | -824745350_9
MML3RSTMFG4620 | TT_Task | NONO/ NOWC from Project Manager: Cars Unloading Method statement | 26/03/2022 | 01/04/2022 | nan | nan | 1208 | TK_NotStart | -824745350 | 439 | -824745350_439
MML3RSTMFG4630 | TT_Task | NONO/ NOWC from Project Manager: Configuration ; Change Management Method statement | 23/05/2022 | 29/05/2022 | nan | nan | 744 | TK_NotStart | -824745350 | 56 | -824745350_56
MML3RSTMFG4640 | TT_Task | NONO/ NOWC from Project Manager: Site Warehouse Management method statement | 23/05/2022 | 29/05/2022 | nan | nan | 744 | TK_NotStart | -824745350 | 440 | -824745350_440
MML3RSTMFG4650 | TT_Task | NONO/ NOWC from Project Manager: Site Warranty Management method statement | 23/05/2022 | 29/05/2022 | nan | nan | 744 | TK_NotStart | -824745350 | 441 | -824745350_441
MML3RSTMFG4690 | TT_Task | NONO/ NOWC from Project Manager: Manufacturing Process Statement | 02/06/2021 | 02/06/2021 | 02/06/2021 | 02/06/2021 | 0 | TK_Complete | -824745350 | 53 | -824745350_53
MML3RSTT&amp;C1160 | TT_Task | T;C TS01: Train Unloading at Depot | 31/08/2022 | 01/09/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 442 | -824745350_442
MML3RSTT&amp;C1165 | TT_Task | T;C TS01: Train Formation and Non Regression Tests | 02/09/2022 | 11/09/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 443 | -824745350_443
MML3RSTT&amp;C1170 | TT_Task | T;C TS01: Static Functional Validation (Research Designs and Standards Organisation Mandatory) | 12/09/2022 | 25/09/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 362 | -824745350_362
MML3RSTT&amp;C1175 | TT_Task | T;C TS01: Static validation perfomance type tests | 26/09/2022 | 09/10/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 360 | -824745350_360
MML3RSTT&amp;C1190 | TT_Task | T;C TS01:Traction braking system perfomance tuning | 10/10/2022 | 30/10/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 380 | -824745350_380
MML3RSTT&amp;C1192 | TT_Task | T;C TS01: Traction braking system perfomance testing | 31/10/2022 | 16/11/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 380 | -824745350_380
MML3RSTT&amp;C1194 | TT_Task | T;C TS01: Oscillation trails | 17/11/2022 | 06/12/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 444 | -824745350_444
MML3RSTT&amp;C1196 | TT_Task | T;C TS01: Dynamic perfomance | 07/12/2022 | 16/12/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 445 | -824745350_445
MML3RSTT&amp;C1260 | TT_Task | T;C TS01: Research Designs and Standards Organisation | 17/12/2022 | 19/12/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 362 | -824745350_362
MML3RSTT&amp;C1265 | TT_Task | T;C TS01: PAPIS(Static+Dynamic)+Neutral Section | 20/12/2022 | 31/12/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 445 | -824745350_445
MML3RSTT&amp;C1280 | TT_Task | INT TS01: Signalling Integration test (Static + Dynamic)+ Telecomm | 01/01/2023 | 21/01/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 446 | -824745350_446
MML3RSTT&amp;C1320 | TT_Task | T;C TS01: Post RST | 22/01/2023 | 28/01/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 447 | -824745350_447
MML3RSTT&amp;C1350 | TT_Task | T;C TS01: Trial Run (10,000Km) | 29/01/2023 | 22/02/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 448 | -824745350_448
MML3RSTT&amp;C1440 | TT_Task | T;C TS01: CMRS Campaign | 23/02/2023 | 25/02/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 447 | -824745350_447
MML3RSTT&amp;C1460 | TT_Task | T;C TS01: Maintenance + Joint Committee Inspection | 26/02/2023 | 27/02/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 449 | -824745350_449
MML3RSTT&amp;C1490 | TT_Task | T;C TS01: NONO/ NOWC from Project Manager | 28/02/2023 | 28/02/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 450 | -824745350_450
MML3RSTT&amp;C2240 | TT_Task | T;C TS01: EMC | 01/03/2023 | 12/03/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 447 | -824745350_447
MML3RSTT&amp;C2250 | TT_Task | T;C TS01: Static Dynamic Noise | 13/03/2023 | 27/03/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 445 | -824745350_445
MML3RSTT&amp;C2260 | TT_Task | T;C TS01: THD | 28/03/2023 | 08/04/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 447 | -824745350_447
MML3RSTT&amp;C2270 | TT_Task | T;C TS01: Energy Consumption | 09/04/2023 | 16/04/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 451 | -824745350_451
MML3RSTT&amp;C2280 | TT_Task | T;C TS01: Current Collection | 17/04/2023 | 22/04/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 382 | -824745350_382
MML3RSTT&amp;C2290 | TT_Task | T;C TS01: Wheel flange lubricator test | 23/04/2023 | 27/04/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 144 | -824745350_144
MML3RSTT&amp;C2300 | TT_Task | T;C TS01: Air generation unit | 28/04/2023 | 01/05/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 451 | -824745350_451
MML3RSTT&amp;C2310 | TT_Task | T;C TS01: Vehicle perfomance test | 02/05/2023 | 05/05/2023 | nan | nan | 88 | TK_NotStart | -824745350 | 359 | -824745350_359
MML3RSTT&amp;C1180 | TT_Task | T;C TS02: Train Unloading at Depot | 25/04/2022 | 26/04/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 442 | -824745350_442
MML3RSTT&amp;C1181 | TT_Task | T;C TS02: Train Formation | 27/04/2022 | 03/05/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 443 | -824745350_443
MML3RSTT&amp;C1182 | TT_Task | T;C TS02: Non Regression Tests | 04/05/2022 | 23/05/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 452 | -824745350_452
MML3RSTT&amp;C1183 | TT_Task | T;C TS02: Routine Dynamic Tests | 24/05/2022 | 07/06/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 453 | -824745350_453
MML3RSTT&amp;C1184 | TT_Task | T;C TS02: Signalling ; Telecom Static Tests | 08/06/2022 | 17/06/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 446 | -824745350_446
MML3RSTT&amp;C1204 | TT_Task | T;C TS02: Signalling Dynamic Tests | 18/06/2022 | 23/06/2022 | nan | nan | 1992 | TK_NotStart | -824745350 | 454 | -824745350_454
MML3RSTT&amp;C1214 | TT_Task | T;C TS02: Maintenance check + Joint Committee Closure | 28/02/2023 | 02/03/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 449 | -824745350_449
MML3RSTT&amp;C1520 | TT_Task | T;C TS02: Service Trials | 03/03/2023 | 12/03/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 448 | -824745350_448
MML3RSTT&amp;C1550 | TT_Task | T;C TS02: NONO/ NOWC from Project Manager | 13/03/2023 | 13/03/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 450 | -824745350_450
MML3RSTT&amp;C1210 | TT_Task | T;C TS03: Train Unloading at Depot | 07/07/2022 | 08/07/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 442 | -824745350_442
MML3RSTT&amp;C1211 | TT_Task | T;C TS03: Train Formation | 09/07/2022 | 15/07/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 443 | -824745350_443
MML3RSTT&amp;C1212 | TT_Task | T;C TS03: Non Regression Tests | 16/07/2022 | 04/08/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 452 | -824745350_452
MML3RSTT&amp;C1213 | TT_Task | T;C TS03: Routine Dynamic Tests | 05/08/2022 | 19/08/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 453 | -824745350_453
MML3RSTT&amp;C1215 | TT_Task | T;C TS03: Signalling ; Telecom Static Tests | 20/08/2022 | 29/08/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 446 | -824745350_446
MML3RSTT&amp;C1216 | TT_Task | T;C TS03: Signalling Dynamic Tests | 30/08/2022 | 04/09/2022 | nan | nan | 1432 | TK_NotStart | -824745350 | 454 | -824745350_454
MML3RSTT&amp;C1217 | TT_Task | T;C TS03: Maintenance check+Joint Committee Closure | 03/03/2023 | 05/03/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 449 | -824745350_449
MML3RSTT&amp;C1240 | TT_Task | T;C TS03: Service Trails | 13/03/2023 | 22/03/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 455 | -824745350_455
MML3RSTT&amp;C1340 | TT_Task | T;C TS03: NONO/ NOWC from Project Manager | 23/03/2023 | 23/03/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 450 | -824745350_450
MML3RSTT&amp;C1220 | TT_Task | T;C TS04: Train Unloading at Depot | 02/07/2022 | 03/07/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 442 | -824745350_442
MML3RSTT&amp;C1221 | TT_Task | T;C TS04: Train Formation | 04/07/2022 | 10/07/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 443 | -824745350_443
MML3RSTT&amp;C1222 | TT_Task | T;C TS04: Non Regression Tests | 11/07/2022 | 30/07/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 452 | -824745350_452
MML3RSTT&amp;C1223 | TT_Task | T;C TS04: Routine Dynamic Tests | 31/07/2022 | 14/08/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 453 | -824745350_453
MML3RSTT&amp;C1224 | TT_Task | T;C TS04: Signalling ; Telecom Static Tests | 15/08/2022 | 24/08/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 446 | -824745350_446
MML3RSTT&amp;C1225 | TT_Task | T;C TS04: Signalling Dynamic Tests | 25/08/2022 | 30/08/2022 | nan | nan | 1496 | TK_NotStart | -824745350 | 454 | -824745350_454
MML3RSTT&amp;C1226 | TT_Task | T;C TS04: Maintenance check+Joint Committee Closure | 06/03/2023 | 08/03/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 449 | -824745350_449
MML3RSTT&amp;C1300 | TT_Task | T;C TS04: Joint Committee Closure | 23/03/2023 | 01/04/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 449 | -824745350_449
MML3RSTT&amp;C1390 | TT_Task | T;C TS04: NONO/ NOWC from Project Manager | 02/04/2023 | 02/04/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 450 | -824745350_450
MML3RSTT&amp;C1250 | TT_Task | T;C TS05: Train Unloading at Depot | 17/07/2022 | 18/07/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 442 | -824745350_442
MML3RSTT&amp;C1270 | TT_Task | T;C TS05: Train Formation | 19/07/2022 | 25/07/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 443 | -824745350_443
MML3RSTT&amp;C1290 | TT_Task | T;C TS05: Non Regression Tests | 26/07/2022 | 14/08/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 452 | -824745350_452
MML3RSTT&amp;C1293 | TT_Task | T;C TS05: Routine Dynamic Tests | 15/08/2022 | 29/08/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 453 | -824745350_453
MML3RSTT&amp;C1295 | TT_Task | T;C TS05: Signalling ; Telecom Static Tests | 30/08/2022 | 08/09/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 446 | -824745350_446
MML3RSTT&amp;C1297 | TT_Task | T;C TS05: Signalling Dynamic Tests | 09/09/2022 | 14/09/2022 | nan | nan | 1400 | TK_NotStart | -824745350 | 454 | -824745350_454
MML3RSTT&amp;C1307 | TT_Task | T;C TS05: Maintenance check+Joint Committee Closure | 09/03/2023 | 11/03/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 449 | -824745350_449
MML3RSTT&amp;C1330 | TT_Task | T;C TS05: Service Trails | 02/04/2023 | 11/04/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 455 | -824745350_455
MML3RSTT&amp;C1420 | TT_Task | T;C TS05: NONO/ NOWC from Project Manager | 12/04/2023 | 12/04/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 450 | -824745350_450
MML3RSTT&amp;C1310 | TT_Task | T;C TS06: Train Unloading at Depot | 23/08/2022 | 24/08/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 442 | -824745350_442
MML3RSTT&amp;C1360 | TT_Task | T;C TS06: Train Formation | 25/08/2022 | 31/08/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 443 | -824745350_443
MML3RSTT&amp;C1361 | TT_Task | T;C TS06: Non Regression Tests | 01/09/2022 | 20/09/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 452 | -824745350_452
MML3RSTT&amp;C1362 | TT_Task | T;C TS06: Routine Dynamic Tests | 21/09/2022 | 05/10/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 453 | -824745350_453
MML3RSTT&amp;C1363 | TT_Task | T;C TS06: Signalling ; Telecom Static Tests | 06/10/2022 | 15/10/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 446 | -824745350_446
MML3RSTT&amp;C1364 | TT_Task | T;C TS06: Signalling Dynamic Tests | 16/10/2022 | 21/10/2022 | nan | nan | 1128 | TK_NotStart | -824745350 | 454 | -824745350_454
MML3RSTT&amp;C1365 | TT_Task | T;C TS06: Maintenance check+Joint Committee Closure | 12/03/2023 | 14/03/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 449 | -824745350_449
MML3RSTT&amp;C1380 | TT_Task | T;C TS06: Service Trails | 12/04/2023 | 21/04/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 455 | -824745350_455
MML3RSTT&amp;C1480 | TT_Task | T;C TS06: NONO/ NOWC from Project Managerr | 22/04/2023 | 22/04/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 450 | -824745350_450
MML3RSTT&amp;C1370 | TT_Task | T;C TS07: Train Unloading at Depot | 07/10/2022 | 08/10/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 442 | -824745350_442
MML3RSTT&amp;C1410 | TT_Task | T;C TS07: Train Formation | 09/10/2022 | 15/10/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 443 | -824745350_443
MML3RSTT&amp;C1411 | TT_Task | T;C TS07: Non Regression Tests | 16/10/2022 | 04/11/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 452 | -824745350_452
MML3RSTT&amp;C1412 | TT_Task | T;C TS07: Routine Dynamic Tests | 05/11/2022 | 19/11/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 453 | -824745350_453
MML3RSTT&amp;C1413 | TT_Task | T;C TS07: Signalling ; Telecom Static Tests | 20/11/2022 | 29/11/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 446 | -824745350_446
MML3RSTT&amp;C1414 | TT_Task | T;C TS07: Signalling Dynamic Tests | 30/11/2022 | 05/12/2022 | nan | nan | 792 | TK_NotStart | -824745350 | 454 | -824745350_454
MML3RSTT&amp;C1415 | TT_Task | T;C TS07: Maintenance check+Joint Committee Closure | 15/03/2023 | 17/03/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 449 | -824745350_449
MML3RSTT&amp;C1430 | TT_Task | T;C TS07: Service Trails | 22/04/2023 | 01/05/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 455 | -824745350_455
MML3RSTT&amp;C1530 | TT_Task | T;C TS07: NONO/ NOWC from Project Managerr | 02/05/2023 | 02/05/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 450 | -824745350_450
MML3RSTT&amp;C1400 | TT_Task | T;C TS08: Train Unloading at Depot | 27/10/2022 | 28/10/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 442 | -824745350_442
MML3RSTT&amp;C1450 | TT_Task | T;C TS08: Train Formation | 29/10/2022 | 04/11/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 443 | -824745350_443
MML3RSTT&amp;C1470 | TT_Task | T;C TS08: Non Regression Tests | 05/11/2022 | 24/11/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 452 | -824745350_452
MML3RSTT&amp;C1471 | TT_Task | T;C TS08: Routine Dynamic Tests | 25/11/2022 | 09/12/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 453 | -824745350_453
MML3RSTT&amp;C1472 | TT_Task | T;C TS08: Signalling ; Telecom Static Tests | 10/12/2022 | 19/12/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 446 | -824745350_446
MML3RSTT&amp;C1473 | TT_Task | T;C TS08: Signalling Dynamic Tests | 20/12/2022 | 25/12/2022 | nan | nan | 656 | TK_NotStart | -824745350 | 454 | -824745350_454
MML3RSTT&amp;C1474 | TT_Task | T;C TS08: Maintenance check+Joint Committee Closure | 18/03/2023 | 20/03/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 449 | -824745350_449
MML3RSTT&amp;C1510 | TT_Task | T;C TS08: Service Trails | 02/05/2023 | 11/05/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 455 | -824745350_455
MML3RSTT&amp;C1570 | TT_Task | T;C TS08: NONO/ NOWC from Project Manager | 12/05/2023 | 12/05/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 450 | -824745350_450
MML3RSTT&amp;C1500 | TT_Task | T;C TS09: Train Unloading at Depot | 11/11/2022 | 12/11/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 442 | -824745350_442
MML3RSTT&amp;C1501 | TT_Task | T;C TS09: Train Formation | 13/11/2022 | 19/11/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 443 | -824745350_443
MML3RSTT&amp;C1502 | TT_Task | T;C TS09: Non Regression Tests | 20/11/2022 | 09/12/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 452 | -824745350_452
MML3RSTT&amp;C1503 | TT_Task | T;C TS09: Routine Dynamic Tests | 10/12/2022 | 24/12/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 453 | -824745350_453
MML3RSTT&amp;C1504 | TT_Task | T;C TS09: Signalling ; Telecom Static Tests | 25/12/2022 | 03/01/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 446 | -824745350_446
MML3RSTT&amp;C1505 | TT_Task | T;C TS09: Signalling Dynamic Tests | 04/01/2023 | 09/01/2023 | nan | nan | 560 | TK_NotStart | -824745350 | 454 | -824745350_454
MML3RSTT&amp;C1506 | TT_Task | T;C TS09: Maintenance check+Joint Committee Closure | 21/03/2023 | 23/03/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 449 | -824745350_449
MML3RSTT&amp;C1560 | TT_Task | T;C TS09: Service Trails | 12/05/2023 | 21/05/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 455 | -824745350_455
MML3RSTT&amp;C1610 | TT_Task | T;C TS09: NONO/ NOWC from Project Manager | 22/05/2023 | 22/05/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 450 | -824745350_450
MML3RSTT&amp;C1540 | TT_Task | T;C TS10: Train Unloading at Depot | 21/11/2022 | 22/11/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 442 | -824745350_442
MML3RSTT&amp;C1541 | TT_Task | T;C TS10: Train Formation | 23/11/2022 | 29/11/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 443 | -824745350_443
MML3RSTT&amp;C1542 | TT_Task | T;C TS10: Non Regression Tests | 30/11/2022 | 19/12/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 452 | -824745350_452
MML3RSTT&amp;C1543 | TT_Task | T;C TS10: Routine Dynamic Tests | 20/12/2022 | 03/01/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 453 | -824745350_453
MML3RSTT&amp;C1544 | TT_Task | T;C TS10: Signalling ; Telecom Static Tests | 04/01/2023 | 13/01/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 446 | -824745350_446
MML3RSTT&amp;C1546 | TT_Task | T;C TS10:Signalling Dynamic Tests | 14/01/2023 | 19/01/2023 | nan | nan | 504 | TK_NotStart | -824745350 | 454 | -824745350_454
MML3RSTT&amp;C1547 | TT_Task | T;C TS10: Maintenance check+Joint Committee Closure | 24/03/2023 | 26/03/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 449 | -824745350_449
MML3RSTT&amp;C1590 | TT_Task | T;C TS10:Service Trails | 22/05/2023 | 31/05/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 455 | -824745350_455
MML3RSTT&amp;C1640 | TT_Task | T;C TS10: NONO/ NOWC from Project Manager | 01/06/2023 | 01/06/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 450 | -824745350_450
MML3RSTT&amp;C1580 | TT_Task | T;C TS11: Train Unloading at Depot | 06/12/2022 | 07/12/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 442 | -824745350_442
MML3RSTT&amp;C1581 | TT_Task | T;C TS11: Train Formation | 08/12/2022 | 14/12/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 443 | -824745350_443
MML3RSTT&amp;C1582 | TT_Task | T;C TS11: Non Regression Tests | 15/12/2022 | 03/01/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 452 | -824745350_452
MML3RSTT&amp;C1583 | TT_Task | T;C TS11: Routine Dynamic Tests | 04/01/2023 | 18/01/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 453 | -824745350_453
MML3RSTT&amp;C1584 | TT_Task | T;C TS11: Signalling ; Telecom Static Tests | 19/01/2023 | 28/01/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 446 | -824745350_446
MML3RSTT&amp;C1585 | TT_Task | T;C TS11: Signalling Dynamic Tests | 29/01/2023 | 03/02/2023 | nan | nan | 408 | TK_NotStart | -824745350 | 454 | -824745350_454
MML3RSTT&amp;C1586 | TT_Task | T;C TS11: Maintenance check+Joint Committee Closure | 27/03/2023 | 29/03/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 449 | -824745350_449
MML3RSTT&amp;C1620 | TT_Task | T;C TS11: Service Trails | 01/06/2023 | 10/06/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 455 | -824745350_455
MML3RSTT&amp;C1670 | TT_Task | T;C TS11: NONO/ NOWC from Project Manager | 11/06/2023 | 11/06/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 450 | -824745350_450
MML3RSTT&amp;C1600 | TT_Task | T;C TS12: Train Unloading at Depot | 16/12/2022 | 17/12/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 442 | -824745350_442
MML3RSTT&amp;C1601 | TT_Task | T;C TS12:Train Formation | 18/12/2022 | 24/12/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 443 | -824745350_443
MML3RSTT&amp;C1602 | TT_Task | T;C TS12: Non Regression Tests | 25/12/2022 | 13/01/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 452 | -824745350_452
MML3RSTT&amp;C1603 | TT_Task | T;C TS12:Routine Dynamic Tests | 14/01/2023 | 28/01/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 453 | -824745350_453
MML3RSTT&amp;C1604 | TT_Task | T;C TS12:Signalling ; Telecom Static Tests | 29/01/2023 | 07/02/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 446 | -824745350_446
MML3RSTT&amp;C1605 | TT_Task | T;C TS12: Signalling Dynamic Tests | 08/02/2023 | 13/02/2023 | nan | nan | 352 | TK_NotStart | -824745350 | 454 | -824745350_454
MML3RSTT&amp;C1606 | TT_Task | T;C TS12:Maintenance check+Joint Committee Closure | 30/03/2023 | 01/04/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 449 | -824745350_449
MML3RSTT&amp;C1650 | TT_Task | T;C TS12: Service Trails | 11/06/2023 | 20/06/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 455 | -824745350_455
MML3RSTT&amp;C1700 | TT_Task | T;C TS12: NONO/ NOWC from Project Manager | 21/06/2023 | 21/06/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 450 | -824745350_450
MML3RSTT&amp;C1630 | TT_Task | T;C TS13: Train Unloading at Depot | 31/12/2022 | 01/01/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 442 | -824745350_442
MML3RSTT&amp;C1631 | TT_Task | T;C TS13: Train Formation | 02/01/2023 | 08/01/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 443 | -824745350_443
MML3RSTT&amp;C1632 | TT_Task | T;C TS13: Non Regression Tests | 09/01/2023 | 28/01/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 452 | -824745350_452
MML3RSTT&amp;C1633 | TT_Task | T;C TS13: Routine Dynamic Tests | 29/01/2023 | 12/02/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 453 | -824745350_453
MML3RSTT&amp;C1634 | TT_Task | T;C TS13: Signalling ; Telecom Static Tests | 13/02/2023 | 22/02/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 446 | -824745350_446
MML3RSTT&amp;C1635 | TT_Task | T;C TS13: Signalling Dynamic Tests | 23/02/2023 | 28/02/2023 | nan | nan | 256 | TK_NotStart | -824745350 | 454 | -824745350_454
MML3RSTT&amp;C1636 | TT_Task | T;C TS13: Maintenance check+Joint Committee Closure | 02/04/2023 | 04/04/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 449 | -824745350_449
MML3RSTT&amp;C1680 | TT_Task | T;C TS13:Service Trails | 21/06/2023 | 30/06/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 455 | -824745350_455
MML3RSTT&amp;C1730 | TT_Task | T;C TS13: NONO/ NOWC from Project Manager | 01/07/2023 | 01/07/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 450 | -824745350_450
MML3RSTT&amp;C1660 | TT_Task | T;C TS14: Train Unloading at Depot | 15/01/2023 | 16/01/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 442 | -824745350_442
MML3RSTT&amp;C1661 | TT_Task | T;C TS14: Train Formation | 17/01/2023 | 23/01/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 443 | -824745350_443
MML3RSTT&amp;C1662 | TT_Task | T;C TS14: Non Regression Tests | 24/01/2023 | 12/02/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 452 | -824745350_452
MML3RSTT&amp;C1663 | TT_Task | T;C TS14: Routine Dynamic Tests | 13/02/2023 | 27/02/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 453 | -824745350_453
MML3RSTT&amp;C1664 | TT_Task | T;C TS14:Signalling ; Telecom Static Tests | 28/02/2023 | 09/03/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 446 | -824745350_446
MML3RSTT&amp;C1665 | TT_Task | T;C TS14: Signalling Dynamic Tests | 10/03/2023 | 15/03/2023 | nan | nan | 160 | TK_NotStart | -824745350 | 454 | -824745350_454
MML3RSTT&amp;C1666 | TT_Task | T;C TS14: Maintenance check+Joint Committee Closure | 05/04/2023 | 07/04/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 449 | -824745350_449
MML3RSTT&amp;C1710 | TT_Task | T;C TS14: Service Trails | 01/07/2023 | 10/07/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 455 | -824745350_455
MML3RSTT&amp;C1770 | TT_Task | T;C TS14: NONO/ NOWC from Project Managerr | 11/07/2023 | 11/07/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 450 | -824745350_450
MML3RSTT&amp;C1690 | TT_Task | T;C TS15: Train Unloading at Depot | 30/01/2023 | 31/01/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 442 | -824745350_442
MML3RSTT&amp;C1691 | TT_Task | T;C TS15:Train Formation | 01/02/2023 | 07/02/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 443 | -824745350_443
MML3RSTT&amp;C1692 | TT_Task | T;C TS15: Non Regression Tests | 08/02/2023 | 27/02/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 452 | -824745350_452
MML3RSTT&amp;C1693 | TT_Task | T;C TS15: Routine Dynamic Tests | 28/02/2023 | 14/03/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 453 | -824745350_453
MML3RSTT&amp;C1694 | TT_Task | T;C TS15: Signalling ; Telecom Static Tests | 15/03/2023 | 24/03/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 446 | -824745350_446
MML3RSTT&amp;C1695 | TT_Task | T;C TS15: Signalling Dynamic Tests | 25/03/2023 | 30/03/2023 | nan | nan | 64 | TK_NotStart | -824745350 | 454 | -824745350_454
MML3RSTT&amp;C1696 | TT_Task | T;C TS15: Maintenance check+Joint Committee Closure | 08/04/2023 | 10/04/2023 | nan | nan | 32 | TK_NotStart | -824745350 | 449 | -824745350_449
MML3RSTT&amp;C1740 | TT_Task | T;C TS15: Service Trails | 11/07/2023 | 20/07/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 455 | -824745350_455
MML3RSTT&amp;C1790 | TT_Task | T;C TS15: NONO/ NOWC from Project Manager | 21/07/2023 | 21/07/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 450 | -824745350_450
MML3RSTT&amp;C1720 | TT_Task | T;C TS16: Train Unloading at Depot | 14/02/2023 | 15/02/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 442 | -824745350_442
MML3RSTT&amp;C1721 | TT_Task | T;C TS16: Train Formation | 16/02/2023 | 22/02/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 443 | -824745350_443
MML3RSTT&amp;C1722 | TT_Task | T;C TS16: Non Regression Tests | 23/02/2023 | 14/03/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 452 | -824745350_452
MML3RSTT&amp;C1723 | TT_Task | T;C TS16: Routine Dynamic Tests | 15/03/2023 | 29/03/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 453 | -824745350_453
MML3RSTT&amp;C1724 | TT_Task | T;C TS16: Signalling ; Telecom Static Tests | 30/03/2023 | 08/04/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 446 | -824745350_446
MML3RSTT&amp;C1725 | TT_Task | T;C TS16:Signalling Dynamic Tests | 09/04/2023 | 14/04/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 454 | -824745350_454
MML3RSTT&amp;C1726 | TT_Task | T;C TS16: Maintenance check+Joint Committee Closure | 15/04/2023 | 17/04/2023 | nan | nan | 96 | TK_NotStart | -824745350 | 449 | -824745350_449
MML3RSTT&amp;C1760 | TT_Task | T;C TS16: Service Trails | 21/07/2023 | 30/07/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 455 | -824745350_455
MML3RSTT&amp;C1830 | TT_Task | T;C TS16: NONO/ NOWC from Project Manager | 31/07/2023 | 31/07/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 450 | -824745350_450
MML3RSTT&amp;C1750 | TT_Task | T;C TS17: Train Unloading at Depot | 01/03/2023 | 02/03/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 442 | -824745350_442
MML3RSTT&amp;C1751 | TT_Task | T;C TS17: Train Formation | 03/03/2023 | 09/03/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 443 | -824745350_443
MML3RSTT&amp;C1752 | TT_Task | T;C TS17: Non Regression Tests | 10/03/2023 | 29/03/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 452 | -824745350_452
MML3RSTT&amp;C1753 | TT_Task | T;C TS17: Routine Dynamic Tests | 30/03/2023 | 13/04/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 453 | -824745350_453
MML3RSTT&amp;C1754 | TT_Task | T;C TS17: Signalling ; Telecom Static Tests | 14/04/2023 | 23/04/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 446 | -824745350_446
MML3RSTT&amp;C1755 | TT_Task | T;C TS17: Signalling Dynamic Tests | 24/04/2023 | 29/04/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 454 | -824745350_454
MML3RSTT&amp;C1756 | TT_Task | T;C TS17: Maintenance check+Joint Committee Closure | 30/04/2023 | 02/05/2023 | nan | nan | 96 | TK_NotStart | -824745350 | 449 | -824745350_449
MML3RSTT&amp;C1800 | TT_Task | T;C TS17: Service Trails | 31/07/2023 | 09/08/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 455 | -824745350_455
MML3RSTT&amp;C1850 | TT_Task | T;C TS17: NONO/ NOWC from Project Manager | 10/08/2023 | 10/08/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 450 | -824745350_450
MML3RSTT&amp;C1780 | TT_Task | T;C TS18: Train Unloading at Depot | 16/03/2023 | 17/03/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 442 | -824745350_442
MML3RSTT&amp;C1781 | TT_Task | T;C TS18: Train Formation | 18/03/2023 | 24/03/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 443 | -824745350_443
MML3RSTT&amp;C1782 | TT_Task | T;C TS18: Non Regression Tests | 25/03/2023 | 13/04/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 452 | -824745350_452
MML3RSTT&amp;C1783 | TT_Task | T;C TS18: Routine Dynamic Tests | 14/04/2023 | 28/04/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 453 | -824745350_453
MML3RSTT&amp;C1784 | TT_Task | T;C TS18: Signalling ; Telecom Static Tests | 29/04/2023 | 08/05/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 446 | -824745350_446
MML3RSTT&amp;C1785 | TT_Task | T;C TS18: Signalling Dynamic Tests | 09/05/2023 | 14/05/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 454 | -824745350_454
MML3RSTT&amp;C1786 | TT_Task | T;C TS18: Maintenance check+Joint Committee Closure | 15/05/2023 | 17/05/2023 | nan | nan | 96 | TK_NotStart | -824745350 | 449 | -824745350_449
MML3RSTT&amp;C1820 | TT_Task | T;C TS18: Service Trails | 10/08/2023 | 19/08/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 455 | -824745350_455
MML3RSTT&amp;C1880 | TT_Task | T;C TS18: NONO/ NOWC from Project Manager | 20/08/2023 | 20/08/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 450 | -824745350_450
MML3RSTT&amp;C1810 | TT_Task | T;C TS19: Train Unloading at Depot | 31/03/2023 | 01/04/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 442 | -824745350_442
MML3RSTT&amp;C1811 | TT_Task | T;C TS19: Train Formation | 02/04/2023 | 08/04/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 443 | -824745350_443
MML3RSTT&amp;C1812 | TT_Task | T;C TS19: Non Regression Tests | 09/04/2023 | 28/04/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 452 | -824745350_452
MML3RSTT&amp;C1813 | TT_Task | T;C TS19: Routine Dynamic Tests | 29/04/2023 | 13/05/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 453 | -824745350_453
MML3RSTT&amp;C1814 | TT_Task | T;C TS19: Signalling ; Telecom Static Tests | 14/05/2023 | 23/05/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 446 | -824745350_446
MML3RSTT&amp;C1815 | TT_Task | T;C TS19: Signalling Dynamic Tests | 24/05/2023 | 29/05/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 454 | -824745350_454
MML3RSTT&amp;C1816 | TT_Task | T;C TS19: Maintenance check+Joint Committee Closure | 30/05/2023 | 01/06/2023 | nan | nan | 96 | TK_NotStart | -824745350 | 449 | -824745350_449
MML3RSTT&amp;C1860 | TT_Task | T;C TS19: Service Trails | 20/08/2023 | 29/08/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 455 | -824745350_455
MML3RSTT&amp;C1910 | TT_Task | T;C TS19: NONO/ NOWC from Project Manager | 30/08/2023 | 30/08/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 450 | -824745350_450
MML3RSTT&amp;C1840 | TT_Task | T;C TS20: Train Unloading at Depot | 15/04/2023 | 16/04/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 442 | -824745350_442
MML3RSTT&amp;C1841 | TT_Task | T;C TS20: Train Formation | 17/04/2023 | 23/04/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 443 | -824745350_443
MML3RSTT&amp;C1842 | TT_Task | T;C TS20: Non Regression Tests | 24/04/2023 | 13/05/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 452 | -824745350_452
MML3RSTT&amp;C1843 | TT_Task | T;C TS20: Routine Dynamic Tests | 14/05/2023 | 28/05/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 453 | -824745350_453
MML3RSTT&amp;C1844 | TT_Task | T;C TS20: Signalling ; Telecom Static Tests | 29/05/2023 | 07/06/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 446 | -824745350_446
MML3RSTT&amp;C1845 | TT_Task | T;C TS20: Signalling Dynamic Tests | 08/06/2023 | 13/06/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 454 | -824745350_454
MML3RSTT&amp;C1846 | TT_Task | T;C TS20: Maintenance check+Joint Committee Closure | 14/06/2023 | 16/06/2023 | nan | nan | 96 | TK_NotStart | -824745350 | 449 | -824745350_449
MML3RSTT&amp;C1890 | TT_Task | T;C TS20: Service Trails | 30/08/2023 | 08/09/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 455 | -824745350_455
MML3RSTT&amp;C1940 | TT_Task | T;C TS20: NONO/ NOWC from Project Manager | 09/09/2023 | 09/09/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 450 | -824745350_450
MML3RSTT&amp;C1870 | TT_Task | T;C TS21: Train Unloading at Depot | 30/04/2023 | 01/05/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 442 | -824745350_442
MML3RSTT&amp;C1871 | TT_Task | T;C TS21: Train Formation | 02/05/2023 | 08/05/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 443 | -824745350_443
MML3RSTT&amp;C1872 | TT_Task | T;C TS21: Non Regression Tests | 09/05/2023 | 28/05/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 452 | -824745350_452
MML3RSTT&amp;C1873 | TT_Task | T;C TS21: Routine Dynamic Tests | 29/05/2023 | 12/06/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 453 | -824745350_453
MML3RSTT&amp;C1874 | TT_Task | T;C TS21: Signalling ; Telecom Static Tests | 13/06/2023 | 22/06/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 446 | -824745350_446
MML3RSTT&amp;C1875 | TT_Task | T;C TS21: Signalling Dynamic Tests | 23/06/2023 | 28/06/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 454 | -824745350_454
MML3RSTT&amp;C1876 | TT_Task | T;C TS21: Maintenance check+Joint Committee Closure | 29/06/2023 | 01/07/2023 | nan | nan | 96 | TK_NotStart | -824745350 | 449 | -824745350_449
MML3RSTT&amp;C1920 | TT_Task | T;C TS21: Service Trails | 09/09/2023 | 18/09/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 455 | -824745350_455
MML3RSTT&amp;C1970 | TT_Task | T;C TS21: NONO/ NOWC from Project Manager | 19/09/2023 | 19/09/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 450 | -824745350_450
MML3RSTT&amp;C1900 | TT_Task | T;C TS22: Train Unloading at Depot | 15/05/2023 | 16/05/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 442 | -824745350_442
MML3RSTT&amp;C1901 | TT_Task | T;C TS22: Train Formation | 17/05/2023 | 23/05/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 443 | -824745350_443
MML3RSTT&amp;C1902 | TT_Task | T;C TS22: Non Regression Tests | 24/05/2023 | 12/06/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 452 | -824745350_452
MML3RSTT&amp;C1903 | TT_Task | T;C TS22: Routine Dynamic Tests | 13/06/2023 | 27/06/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 453 | -824745350_453
MML3RSTT&amp;C1904 | TT_Task | T;C TS22: Signalling ; Telecom Static Tests | 28/06/2023 | 07/07/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 446 | -824745350_446
MML3RSTT&amp;C1905 | TT_Task | T;C TS22: Signalling Dynamic Tests | 08/07/2023 | 13/07/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 454 | -824745350_454
MML3RSTT&amp;C1906 | TT_Task | T;C TS22: Maintenance check+Joint Committee Closure | 14/07/2023 | 16/07/2023 | nan | nan | 96 | TK_NotStart | -824745350 | 449 | -824745350_449
MML3RSTT&amp;C1950 | TT_Task | T;C TS22: Service Trails | 19/09/2023 | 28/09/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 455 | -824745350_455
MML3RSTT&amp;C2000 | TT_Task | T;C TS22: NONO/ NOWC from Project Manager | 29/09/2023 | 29/09/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 450 | -824745350_450
MML3RSTT&amp;C1930 | TT_Task | T;C TS23: Train Unloading at Depot | 30/05/2023 | 31/05/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 442 | -824745350_442
MML3RSTT&amp;C1931 | TT_Task | T;C TS23: Train Formation | 01/06/2023 | 07/06/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 443 | -824745350_443
MML3RSTT&amp;C1932 | TT_Task | T;C TS23: Non Regression Tests | 08/06/2023 | 27/06/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 452 | -824745350_452
MML3RSTT&amp;C1933 | TT_Task | T;C TS23: Routine Dynamic Tests | 28/06/2023 | 12/07/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 453 | -824745350_453
MML3RSTT&amp;C1934 | TT_Task | T;C TS23: Signalling ; Telecom Static Tests | 13/07/2023 | 22/07/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 446 | -824745350_446
MML3RSTT&amp;C1935 | TT_Task | T;C TS23: Signalling Dynamic Tests | 23/07/2023 | 28/07/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 454 | -824745350_454
MML3RSTT&amp;C1936 | TT_Task | T;C TS23: Maintenance check+Joint Committee Closure | 29/07/2023 | 31/07/2023 | nan | nan | 96 | TK_NotStart | -824745350 | 449 | -824745350_449
MML3RSTT&amp;C1980 | TT_Task | T;C TS23: Service Trails | 29/09/2023 | 08/10/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 455 | -824745350_455
MML3RSTT&amp;C2030 | TT_Task | T;C TS23: NONO/ NOWC from Project Manager | 09/10/2023 | 09/10/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 450 | -824745350_450
MML3RSTT&amp;C1960 | TT_Task | T;C TS24: Train Unloading at Depot | 14/06/2023 | 15/06/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 442 | -824745350_442
MML3RSTT&amp;C1961 | TT_Task | T;C TS24:Train Formation | 16/06/2023 | 22/06/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 443 | -824745350_443
MML3RSTT&amp;C1962 | TT_Task | T;C TS24: Non Regression Tests | 23/06/2023 | 12/07/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 452 | -824745350_452
MML3RSTT&amp;C1963 | TT_Task | T;C TS24: Routine Dynamic Tests | 13/07/2023 | 27/07/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 453 | -824745350_453
MML3RSTT&amp;C1964 | TT_Task | T;C TS24: Signalling ; Telecom Static Tests | 28/07/2023 | 06/08/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 446 | -824745350_446
MML3RSTT&amp;C1965 | TT_Task | T;C TS24:Signalling Dynamic Tests | 07/08/2023 | 12/08/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 454 | -824745350_454
MML3RSTT&amp;C1966 | TT_Task | T;C TS24:Maintenance check+Joint Committee Closure | 13/08/2023 | 15/08/2023 | nan | nan | 96 | TK_NotStart | -824745350 | 449 | -824745350_449
MML3RSTT&amp;C2010 | TT_Task | T;C TS24:Service Trails | 09/10/2023 | 18/10/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 455 | -824745350_455
MML3RSTT&amp;C2060 | TT_Task | T;C TS24: NONO/ NOWC from Project Manager | 19/10/2023 | 19/10/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 450 | -824745350_450
MML3RSTT&amp;C1990 | TT_Task | T;C TS25: Train Unloading at Depot | 29/06/2023 | 30/06/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 442 | -824745350_442
MML3RSTT&amp;C1991 | TT_Task | T;C TS25: Train Formation | 01/07/2023 | 07/07/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 443 | -824745350_443
MML3RSTT&amp;C1992 | TT_Task | T;C TS25: Non Regression Tests | 08/07/2023 | 27/07/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 452 | -824745350_452
MML3RSTT&amp;C1993 | TT_Task | T;C TS25: Routine Dynamic Tests | 28/07/2023 | 11/08/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 453 | -824745350_453
MML3RSTT&amp;C1994 | TT_Task | T;C TS25:Signalling ; Telecom Static Tests | 12/08/2023 | 21/08/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 446 | -824745350_446
MML3RSTT&amp;C1995 | TT_Task | T;C TS25:Signalling Dynamic Tests | 22/08/2023 | 27/08/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 454 | -824745350_454
MML3RSTT&amp;C1996 | TT_Task | T;C TS25: Maintenance check+Joint Committee Closure | 28/08/2023 | 30/08/2023 | nan | nan | 96 | TK_NotStart | -824745350 | 449 | -824745350_449
MML3RSTT&amp;C2040 | TT_Task | T;C TS25: Service Trails | 19/10/2023 | 28/10/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 455 | -824745350_455
MML3RSTT&amp;C2090 | TT_Task | T;C TS25: NONO/ NOWC from Project Manager | 29/10/2023 | 29/10/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 450 | -824745350_450
MML3RSTT&amp;C2020 | TT_Task | T;C TS26: Train Unloading at Depot | 14/07/2023 | 15/07/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 442 | -824745350_442
MML3RSTT&amp;C2021 | TT_Task | T;C TS26: Train Formation | 16/07/2023 | 22/07/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 443 | -824745350_443
MML3RSTT&amp;C2022 | TT_Task | T;C TS26: Non Regression Tests | 23/07/2023 | 11/08/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 452 | -824745350_452
MML3RSTT&amp;C2023 | TT_Task | T;C TS26: Routine Dynamic Tests | 12/08/2023 | 26/08/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 453 | -824745350_453
MML3RSTT&amp;C2024 | TT_Task | T;C TS26: Signalling ; Telecom Static Tests | 27/08/2023 | 05/09/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 446 | -824745350_446
MML3RSTT&amp;C2025 | TT_Task | T;C TS26: Signalling Dynamic Tests | 06/09/2023 | 11/09/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 454 | -824745350_454
MML3RSTT&amp;C2026 | TT_Task | T;C TS26: Maintenance check+Joint Committee Closure | 12/09/2023 | 14/09/2023 | nan | nan | 96 | TK_NotStart | -824745350 | 449 | -824745350_449
MML3RSTT&amp;C2070 | TT_Task | T;C TS26: Service Trails | 29/10/2023 | 07/11/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 455 | -824745350_455
MML3RSTT&amp;C2120 | TT_Task | T;C TS26: NONO/ NOWC from Project Manager | 08/11/2023 | 08/11/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 450 | -824745350_450
MML3RSTT&amp;C2050 | TT_Task | T;C TS27: Train Unloading at Depot | 29/07/2023 | 30/07/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 442 | -824745350_442
MML3RSTT&amp;C2051 | TT_Task | T;C TS27:Train Formation | 31/07/2023 | 06/08/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 443 | -824745350_443
MML3RSTT&amp;C2052 | TT_Task | T;C TS27: Non Regression Tests | 07/08/2023 | 26/08/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 452 | -824745350_452
MML3RSTT&amp;C2053 | TT_Task | T;C TS27: Routine Dynamic Tests | 27/08/2023 | 10/09/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 453 | -824745350_453
MML3RSTT&amp;C2054 | TT_Task | T;C TS27: Signalling ; Telecom Static Tests | 11/09/2023 | 20/09/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 446 | -824745350_446
MML3RSTT&amp;C2055 | TT_Task | T;C TS27: Signalling Dynamic Tests | 21/09/2023 | 26/09/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 454 | -824745350_454
MML3RSTT&amp;C2056 | TT_Task | T;C TS27: Maintenance check+Joint Committee Closure | 27/09/2023 | 29/09/2023 | nan | nan | 96 | TK_NotStart | -824745350 | 449 | -824745350_449
MML3RSTT&amp;C2100 | TT_Task | T;C TS27: Service Trails | 08/11/2023 | 17/11/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 455 | -824745350_455
MML3RSTT&amp;C2150 | TT_Task | T;C TS27: NONO/ NOWC from Project Manager | 18/11/2023 | 18/11/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 450 | -824745350_450
MML3RSTT&amp;C2080 | TT_Task | T;C TS28: Train Unloading at Depot | 13/08/2023 | 14/08/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 442 | -824745350_442
MML3RSTT&amp;C2081 | TT_Task | T;C TS28: Train Formation | 15/08/2023 | 21/08/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 443 | -824745350_443
MML3RSTT&amp;C2082 | TT_Task | T;C TS28: Non Regression Tests | 22/08/2023 | 10/09/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 452 | -824745350_452
MML3RSTT&amp;C2083 | TT_Task | T;C TS28: Routine Dynamic Tests | 11/09/2023 | 25/09/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 453 | -824745350_453
MML3RSTT&amp;C2084 | TT_Task | T;C TS28: Signalling ; Telecom Static Tests | 26/09/2023 | 05/10/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 446 | -824745350_446
MML3RSTT&amp;C2085 | TT_Task | T;C TS28: Signalling Dynamic Tests | 06/10/2023 | 11/10/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 454 | -824745350_454
MML3RSTT&amp;C2086 | TT_Task | T;C TS28: Maintenance check+Joint Committee Closure | 12/10/2023 | 14/10/2023 | nan | nan | 96 | TK_NotStart | -824745350 | 449 | -824745350_449
MML3RSTT&amp;C2130 | TT_Task | T;C TS28: Service Trails | 18/11/2023 | 27/11/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 455 | -824745350_455
MML3RSTT&amp;C2180 | TT_Task | T;C TS28: NONO/ NOWC from Project Manager | 28/11/2023 | 28/11/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 450 | -824745350_450
MML3RSTT&amp;C2110 | TT_Task | T;C TS29: Train Unloading at Depot | 28/08/2023 | 29/08/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 442 | -824745350_442
MML3RSTT&amp;C2111 | TT_Task | T;C TS29: Train Formation | 30/08/2023 | 05/09/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 443 | -824745350_443
MML3RSTT&amp;C2112 | TT_Task | T;C TS29: Non Regression Tests | 06/09/2023 | 25/09/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 452 | -824745350_452
MML3RSTT&amp;C2113 | TT_Task | T;C TS29: Routine Dynamic Tests | 26/09/2023 | 10/10/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 453 | -824745350_453
MML3RSTT&amp;C2114 | TT_Task | T;C TS29: Signalling ; Telecom Static Tests | 11/10/2023 | 20/10/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 446 | -824745350_446
MML3RSTT&amp;C2115 | TT_Task | T;C TS29:Signalling Dynamic Tests | 21/10/2023 | 26/10/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 454 | -824745350_454
MML3RSTT&amp;C2116 | TT_Task | T;C TS29: Maintenance check+Joint Committee Closure | 27/10/2023 | 29/10/2023 | nan | nan | 56 | TK_NotStart | -824745350 | 449 | -824745350_449
MML3RSTT&amp;C2160 | TT_Task | T;C TS29: Service Trails | 28/11/2023 | 07/12/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 455 | -824745350_455
MML3RSTT&amp;C2200 | TT_Task | T;C TS29: NONO/ NOWC from Project Manager | 08/12/2023 | 08/12/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 450 | -824745350_450
MML3RSTT&amp;C2140 | TT_Task | T;C TS30: Train Unloading at Depot | 07/09/2023 | 08/09/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 442 | -824745350_442
MML3RSTT&amp;C2141 | TT_Task | T;C TS30: Train Formation | 09/09/2023 | 15/09/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 443 | -824745350_443
MML3RSTT&amp;C2142 | TT_Task | T;C TS30: Non Regression Tests | 16/09/2023 | 05/10/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 452 | -824745350_452
MML3RSTT&amp;C2143 | TT_Task | T;C TS30: Routine Dynamic Tests | 06/10/2023 | 20/10/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 453 | -824745350_453
MML3RSTT&amp;C2144 | TT_Task | T;C TS30: Signalling ; Telecom Static Tests | 21/10/2023 | 30/10/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 446 | -824745350_446
MML3RSTT&amp;C2145 | TT_Task | T;C TS30: Signalling Dynamic Tests | 31/10/2023 | 05/11/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 454 | -824745350_454
MML3RSTT&amp;C2146 | TT_Task | T;C TS30:Maintenance check+Joint Committee Closure | 06/11/2023 | 08/11/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 449 | -824745350_449
MML3RSTT&amp;C2190 | TT_Task | T;C TS30: Service Trails | 08/12/2023 | 17/12/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 455 | -824745350_455
MML3RSTT&amp;C2220 | TT_Task | T;C TS30: NONO/ NOWC from Project Manager | 18/12/2023 | 18/12/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 450 | -824745350_450
MML3RSTT&amp;C2170 | TT_Task | T;C TS31: Train Unloading at Depot | 17/09/2023 | 18/09/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 442 | -824745350_442
MML3RSTT&amp;C2171 | TT_Task | T;C TS31:Train Formation | 19/09/2023 | 25/09/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 443 | -824745350_443
MML3RSTT&amp;C2172 | TT_Task | T;C TS31: Non Regression Tests | 26/09/2023 | 15/10/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 452 | -824745350_452
MML3RSTT&amp;C2173 | TT_Task | T;C TS31: Routine Dynamic Tests | 16/10/2023 | 23/10/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 453 | -824745350_453
MML3RSTT&amp;C2174 | TT_Task | T;C TS31: Signalling ; Telecom Static Tests | 24/10/2023 | 29/10/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 446 | -824745350_446
MML3RSTT&amp;C2175 | TT_Task | T;C TS31: Signalling Dynamic Tests | 30/10/2023 | 04/11/2023 | nan | nan | 32 | TK_NotStart | -824745350 | 454 | -824745350_454
MML3RSTT&amp;C2176 | TT_Task | T;C TS31: Maintenance check+Joint Committee Closure | 09/11/2023 | 11/11/2023 | nan | nan | 288 | TK_NotStart | -824745350 | 449 | -824745350_449
MML3RSTT&amp;C2210 | TT_Task | T;C TS31: Service Trails | 18/12/2023 | 27/12/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 455 | -824745350_455
MML3RSTT&amp;C2230 | TT_Task | T;C TS31: NONO/ NOWC from Project Manager | 28/12/2023 | 28/12/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 450 | -824745350_450
MML3RSTRAM1000 | TT_Task | Preparation of Service Check Sheets | 01/03/2023 | 30/03/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 456 | -824745350_456
MML3RSTRAM1010 | TT_Task | Approval of Service Check sheets from Customer | 31/03/2023 | 13/04/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 456 | -824745350_456
MML3RSTRAM1020 | TT_Task | Demonstration of Service Checks at depot to customer | 14/04/2023 | 13/05/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 456 | -824745350_456
MML3RSTRAM1030 | TT_Task | Preparation of MTTR values | 14/05/2023 | 12/06/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 457 | -824745350_457
MML3RSTRAM1040 | TT_Task | Approval of MTTR from Customer | 13/06/2023 | 26/06/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 458 | -824745350_458
MML3RSTRAM1050 | TT_Task | Demonstration of MTTR values | 27/06/2023 | 26/07/2023 | nan | nan | 1688 | TK_NotStart | -824745350 | 457 | -824745350_457
MML3RSTRAM1060 | TT_Task | Sub-system SIL Assessment Report/Certificate | 03/05/2023 | 16/05/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 459 | -824745350_459
MML3RSTDLP1000 | TT_Task | DLP TS01:Defect Liability Period Train#01 | 17/05/2023 | 04/05/2026 | nan | nan | 0 | TK_NotStart | -824745350 | 460 | -824745350_460
MML3RSTDLP1010 | TT_Task | DLP TS02:Defect Liability Period Train#02 | 17/05/2023 | 04/05/2026 | nan | nan | 0 | TK_NotStart | -824745350 | 460 | -824745350_460
MML3RSTDLP1020 | TT_Task | DLP TS03:Defect Liability Period Train#03 | 17/05/2023 | 04/05/2026 | nan | nan | 0 | TK_NotStart | -824745350 | 460 | -824745350_460
MML3RSTDLP1030 | TT_Task | DLP TS04:Defect Liability Period Train#04 | 17/05/2023 | 04/05/2026 | nan | nan | 0 | TK_NotStart | -824745350 | 460 | -824745350_460
MML3RSTDLP1040 | TT_Task | DLP TS05:Defect Liability Period Train#05 | 17/05/2023 | 04/05/2026 | nan | nan | 0 | TK_NotStart | -824745350 | 460 | -824745350_460
MML3RSTDLP1050 | TT_Task | DLP TS06:Defect Liability Period Train#06 | 17/05/2023 | 04/05/2026 | nan | nan | 0 | TK_NotStart | -824745350 | 460 | -824745350_460
MML3RSTDLP1060 | TT_Task | DLP TS07:Defect Liability Period Train#07 | 17/05/2023 | 04/05/2026 | nan | nan | 0 | TK_NotStart | -824745350 | 460 | -824745350_460
MML3RSTDLP1070 | TT_Task | DLP TS08:Defect Liability Period Train#08 | 23/02/2024 | 21/02/2026 | nan | nan | 576 | TK_NotStart | -824745350 | 460 | -824745350_460
MML3RSTDLP1080 | TT_Task | DLP TS09:Defect Liability Period Train#09 | 23/02/2024 | 21/02/2026 | nan | nan | 576 | TK_NotStart | -824745350 | 460 | -824745350_460
MML3RSTDLP1090 | TT_Task | DLP TS10:Defect Liability Period Train#10 | 23/02/2024 | 21/02/2026 | nan | nan | 576 | TK_NotStart | -824745350 | 460 | -824745350_460
MML3RSTDLP1100 | TT_Task | DLP TS11:Defect Liability Period Train#11 | 23/02/2024 | 21/02/2026 | nan | nan | 576 | TK_NotStart | -824745350 | 460 | -824745350_460
MML3RSTDLP1110 | TT_Task | DLP TS12:Defect Liability Period Train#12 | 23/02/2024 | 21/02/2026 | nan | nan | 576 | TK_NotStart | -824745350 | 460 | -824745350_460
MML3RSTDLP1120 | TT_Task | DLP TS13:Defect Liability Period Train#13 | 23/02/2024 | 21/02/2026 | nan | nan | 576 | TK_NotStart | -824745350 | 460 | -824745350_460
MML3RSTDLP1130 | TT_Task | DLP TS14:Defect Liability Period Train#14 | 23/02/2024 | 21/02/2026 | nan | nan | 576 | TK_NotStart | -824745350 | 460 | -824745350_460
MML3RSTDLP1140 | TT_Task | DLP TS15:Defect Liability Period Train#15 | 23/02/2024 | 21/02/2026 | nan | nan | 576 | TK_NotStart | -824745350 | 460 | -824745350_460
MML3RSTDLP1150 | TT_Task | DLP TS16:Defect Liability Period Train#16 | 23/02/2024 | 21/02/2026 | nan | nan | 576 | TK_NotStart | -824745350 | 460 | -824745350_460
MML3RSTDLP1160 | TT_Task | DLP TS17:Defect Liability Period Train#17 | 23/02/2024 | 21/02/2026 | nan | nan | 576 | TK_NotStart | -824745350 | 460 | -824745350_460
MML3RSTDLP1170 | TT_Task | DLP TS18:Defect Liability Period Train#18 | 23/02/2024 | 21/02/2026 | nan | nan | 576 | TK_NotStart | -824745350 | 460 | -824745350_460
MML3RSTDLP1180 | TT_Task | DLP TS19:Defect Liability Period Train#19 | 23/02/2024 | 21/02/2026 | nan | nan | 576 | TK_NotStart | -824745350 | 460 | -824745350_460
MML3RSTDLP1190 | TT_Task | DLP TS20:Defect Liability Period Train#20 | 23/02/2024 | 21/02/2026 | nan | nan | 576 | TK_NotStart | -824745350 | 460 | -824745350_460
MML3RSTDLP1200 | TT_Task | DLP TS21:Defect Liability Period Train#21 | 23/02/2024 | 21/02/2026 | nan | nan | 576 | TK_NotStart | -824745350 | 460 | -824745350_460
MML3RSTDLP1210 | TT_Task | DLP TS22:Defect Liability Period Train#22 | 23/02/2024 | 21/02/2026 | nan | nan | 576 | TK_NotStart | -824745350 | 460 | -824745350_460
MML3RSTDLP1220 | TT_Task | DLP TS23:Defect Liability Period Train#23 | 23/02/2024 | 21/02/2026 | nan | nan | 576 | TK_NotStart | -824745350 | 460 | -824745350_460
MML3RSTDLP1230 | TT_Task | DLP TS24:Defect Liability Period Train#24 | 23/02/2024 | 21/02/2026 | nan | nan | 576 | TK_NotStart | -824745350 | 460 | -824745350_460
MML3RSTDLP1240 | TT_Task | DLP TS25:Defect Liability Period Train#25 | 23/02/2024 | 21/02/2026 | nan | nan | 576 | TK_NotStart | -824745350 | 460 | -824745350_460
MML3RSTDLP1250 | TT_Task | DLP TS26:Defect Liability Period Train#26 | 23/02/2024 | 21/02/2026 | nan | nan | 576 | TK_NotStart | -824745350 | 460 | -824745350_460
MML3RSTDLP1260 | TT_Task | DLP TS27:Defect Liability Period Train#27 | 23/02/2024 | 21/02/2026 | nan | nan | 576 | TK_NotStart | -824745350 | 460 | -824745350_460
MML3RSTDLP1270 | TT_Task | DLP TS28:Defect Liability Period Train#28 | 23/02/2024 | 21/02/2026 | nan | nan | 576 | TK_NotStart | -824745350 | 460 | -824745350_460
MML3RSTDLP1280 | TT_Task | DLP TS29:Defect Liability Period Train#29 | 23/02/2024 | 21/02/2026 | nan | nan | 576 | TK_NotStart | -824745350 | 460 | -824745350_460
MML3RSTDLP1290 | TT_Task | DLP TS30:Defect Liability Period Train#30 | 23/02/2024 | 21/02/2026 | nan | nan | 576 | TK_NotStart | -824745350 | 460 | -824745350_460
MML3RSTDLP1300 | TT_Task | DLP TS31:Defect Liability Period Train#31 | 23/02/2024 | 21/02/2026 | nan | nan | 0 | TK_NotStart | -824745350 | 460 | -824745350_460
MML3RSTSPA1000 | TT_Task | GA11/GA21 (Phase I): List of Spares: Submission to Project Manager/ GC | 13/12/2019 | 13/12/2019 | 13/12/2019 | 14/12/2019 | 0 | TK_Complete | -824745350 | 461 | -824745350_461
MML3RSTSPA1010 | TT_Task | GA11/GA21 (Phase I): List of Spares : Comments from Project Manager/ GC | 16/12/2019 | 06/06/2020 | 16/12/2019 | 06/06/2020 | 0 | TK_Complete | -824745350 | 461 | -824745350_461
MML3RSTSPA1020 | TT_Task | GA11/GA21 (Phase I): List of Spares : Resubmission by Alstom | 08/06/2020 | 08/07/2020 | 08/06/2020 | 08/07/2020 | 0 | TK_Complete | -824745350 | 462 | -824745350_462
MML3RSTSPA1030 | TT_Task | GA11/GA21 (Phase I): List of Spares : NONO/ NOWC from Project Manager | 08/07/2020 | 08/07/2020 | 08/07/2020 | 08/07/2020 | 0 | TK_Complete | -824745350 | 463 | -824745350_463
MML3RSTSPA1040 | TT_Task | GA11/GA21 (Phase I): RFQ to Suppliers | 26/05/2021 | 09/06/2021 | 26/05/2021 | nan | 0 | TK_Active | -824745350 | 464 | -824745350_464
MML3RSTSPA1050 | TT_Task | GA11/GA21 (Phase I): Receipt of Quotation | 17/06/2021 | 01/07/2021 | 17/06/2021 | nan | 0 | TK_Active | -824745350 | 465 | -824745350_465
MML3RSTSPA1060 | TT_Task | GA11/GA21 (Phase I): Techno-commercial closures | 21/06/2021 | 05/07/2021 | 21/06/2021 | nan | 0 | TK_Active | -824745350 | 466 | -824745350_466
MML3RSTSPA1070 | TT_Task | GA11/GA21 (Phase I): Business Award/ PO Release | 21/06/2021 | 05/07/2021 | 22/06/2021 | nan | 0 | TK_Active | -824745350 | 467 | -824745350_467
MML3RSTSPA1080 | TT_Task | GA11/GA21 (Phase I): Procurement of Spares | 01/06/2022 | 29/08/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 468 | -824745350_468
MML3RSTSPA1090 | TT_Task | GA11/GA21 (Phase I): Packing ; Transportation to Depot | 30/08/2022 | 13/09/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 469 | -824745350_469
MML3RSTSPA1100 | TT_Task | GA11/GA21 (Phase I): Inspection for acceptance of Spares | 14/09/2022 | 18/09/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 470 | -824745350_470
MML3RSTSPA1110 | TT_Task | GA11/GA21 (Phase I): NONO/ NOWC from Project Manager | 19/09/2022 | 23/09/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 471 | -824745350_471
MML3RSTSPA1120 | TT_Task | GA11/GA21 (Phase I): Handing over | 24/09/2022 | 28/09/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 472 | -824745350_472
MML3RSTSPA1130 | TT_Task | GA12/GA22 (Phase I): List of Spares : Submission to Project Manager/ GC | 26/12/2020 | 08/01/2021 | 13/12/2019 | 14/12/2019 | 0 | TK_Complete | -824745350 | 461 | -824745350_461
MML3RSTSPA1140 | TT_Task | GA12/GA22 (Phase I): List of Spares : Comments from Project Manager/ GC | 09/01/2021 | 22/01/2021 | 16/12/2019 | 06/06/2020 | 0 | TK_Complete | -824745350 | 461 | -824745350_461
MML3RSTSPA6040 | TT_Task | GA12/GA22 (Phase I): List of Spares : Resubmission by Alstom | 23/01/2021 | 05/02/2021 | 08/06/2020 | 08/07/2020 | 0 | TK_Complete | -824745350 | 462 | -824745350_462
MML3RSTSPA6050 | TT_Task | GA12/GA22 (Phase I): List of Spares : NONO/ NOWC from Project Manager | 06/02/2021 | 19/02/2021 | 08/07/2020 | 08/07/2020 | 0 | TK_Complete | -824745350 | 463 | -824745350_463
MML3RSTSPA6060 | TT_Task | GA12/GA22 (Phase I): RFQ to Suppliers | 26/05/2021 | 09/06/2021 | 26/05/2021 | nan | 0 | TK_Active | -824745350 | 464 | -824745350_464
MML3RSTSPA6070 | TT_Task | GA12/GA22 (Phase I): Receipt of Quotation | 17/06/2021 | 01/07/2021 | 17/06/2021 | nan | 0 | TK_Active | -824745350 | 465 | -824745350_465
MML3RSTSPA6080 | TT_Task | GA12/GA22 (Phase I): Techno-commercial closures | 21/06/2021 | 05/07/2021 | 21/06/2021 | nan | 0 | TK_Active | -824745350 | 466 | -824745350_466
MML3RSTSPA6090 | TT_Task | GA12/GA22 (Phase I): Business Award/ PO Release | 22/06/2021 | 06/07/2021 | 22/06/2021 | nan | 0 | TK_Active | -824745350 | 467 | -824745350_467
MML3RSTSPA6100 | TT_Task | GA12/GA22 (Phase I): Procurement of Spares | 26/04/2022 | 24/07/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 468 | -824745350_468
MML3RSTSPA6110 | TT_Task | GA12/GA22 (Phase I): Packing ; Transportation to Depot | 25/07/2022 | 08/08/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 469 | -824745350_469
MML3RSTSPA6120 | TT_Task | GA12/GA22 (Phase I): Inspection for acceptance of Spares | 09/08/2022 | 13/08/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 470 | -824745350_470
MML3RSTSPA6130 | TT_Task | GA12/GA22 (Phase I): NONO/ NOWC from Project Manager | 14/08/2022 | 18/08/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 471 | -824745350_471
MML3RSTSPA6140 | TT_Task | GA12/GA22 (Phase I): Handing over | 19/08/2022 | 23/08/2022 | nan | nan | 2128 | TK_NotStart | -824745350 | 472 | -824745350_472
MML3RSTSPA6150 | TT_Task | GA14/GA24 (Phase I): List of Spares : Submission to Project Manager/ GC | 26/12/2020 | 08/01/2021 | 13/12/2019 | 14/12/2019 | 0 | TK_Complete | -824745350 | 461 | -824745350_461
MML3RSTSPA6160 | TT_Task | GA14/GA24 (Phase I): List of Spares : Comments from Project Manager/ GC | 09/01/2021 | 22/01/2021 | 16/12/2019 | 06/06/2020 | 0 | TK_Complete | -824745350 | 461 | -824745350_461
MML3RSTSPA6170 | TT_Task | GA14/GA24 (Phase I): List of Spares : Resubmission by Alstom | 23/01/2021 | 05/02/2021 | 08/06/2020 | 08/07/2020 | 0 | TK_Complete | -824745350 | 462 | -824745350_462
MML3RSTSPA6180 | TT_Task | GA14/GA24 (Phase I): List of Spares : NONO/ NOWC from Project Manager | 06/02/2021 | 19/02/2021 | 08/07/2020 | 08/07/2020 | 0 | TK_Complete | -824745350 | 463 | -824745350_463
MML3RSTSPA6190 | TT_Task | GA14/GA24 (Phase I): RFQ to Suppliers | 26/05/2021 | 09/06/2021 | 26/05/2021 | nan | 0 | TK_Active | -824745350 | 464 | -824745350_464
MML3RSTSPA6200 | TT_Task | GA14/GA24 (Phase I): Receipt of Quotation | 17/06/2021 | 01/07/2021 | 17/06/2021 | nan | 0 | TK_Active | -824745350 | 465 | -824745350_465
MML3RSTSPA6210 | TT_Task | GA14/GA24 (Phase I): Techno-commercial closures | 21/06/2021 | 05/07/2021 | 21/06/2021 | nan | 0 | TK_Active | -824745350 | 466 | -824745350_466
MML3RSTSPA6220 | TT_Task | GA14/GA24 (Phase I): Business Award/ PO Release | 11/04/2022 | 25/04/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 467 | -824745350_467
MML3RSTSPA6230 | TT_Task | GA14/GA24 (Phase I): Procurement of Spares | 26/04/2022 | 24/07/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 468 | -824745350_468
MML3RSTSPA6240 | TT_Task | GA14/GA24 (Phase I): Packing ; Transportation to Depot | 25/07/2022 | 08/08/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 469 | -824745350_469
MML3RSTSPA6250 | TT_Task | GA14/GA24 (Phase I): Inspection for acceptance of Spares | 09/08/2022 | 13/08/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 470 | -824745350_470
MML3RSTSPA6260 | TT_Task | GA14/GA24 (Phase I): NONO/ NOWC from Project Manager | 14/08/2022 | 18/08/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 471 | -824745350_471
MML3RSTSPA6270 | TT_Task | GA14/GA24 (Phase I): Handing over | 19/08/2022 | 23/08/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 472 | -824745350_472
MML3RSTSPA6280 | TT_Task | GA11/GA21 (Phase II): List of Spares : Submission to Project Manager/ GC | 13/12/2019 | 14/12/2019 | 13/12/2019 | 14/12/2019 | 0 | TK_Complete | -824745350 | 461 | -824745350_461
MML3RSTSPA6290 | TT_Task | GA11/GA21 (Phase II): List of Spares : Comments from Project Manager/ GC | 16/12/2019 | 06/06/2020 | 16/12/2019 | 06/06/2020 | 0 | TK_Complete | -824745350 | 461 | -824745350_461
MML3RSTSPA6300 | TT_Task | GA11/GA21 (Phase II): List of Spares : Resubmission by Alstom | 23/01/2021 | 05/02/2021 | 08/06/2020 | 08/07/2020 | 0 | TK_Complete | -824745350 | 462 | -824745350_462
MML3RSTSPA6310 | TT_Task | GA11/GA21 (Phase II): List of Spares : NONO/ NOWC from Project Manager | 08/07/2020 | 08/07/2020 | 08/07/2020 | 08/07/2020 | 0 | TK_Complete | -824745350 | 463 | -824745350_463
MML3RSTSPA6320 | TT_Task | GA11/GA21 (Phase II): RFQ to Suppliers | 25/02/2022 | 11/03/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 464 | -824745350_464
MML3RSTSPA6330 | TT_Task | GA11/GA21 (Phase II): Receipt of Quotation | 12/03/2022 | 26/03/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 465 | -824745350_465
MML3RSTSPA6340 | TT_Task | GA11/GA21 (Phase II): Techno-commercial closures | 27/03/2022 | 10/04/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 466 | -824745350_466
MML3RSTSPA6350 | TT_Task | GA11/GA21 (Phase II): Business Award/ PO Release | 11/04/2022 | 25/04/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 467 | -824745350_467
MML3RSTSPA6360 | TT_Task | GA11/GA21 (Phase II): Procurement of Spares | 26/04/2022 | 24/07/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 468 | -824745350_468
MML3RSTSPA6370 | TT_Task | GA11/GA21 (Phase II): Packing ; Transportation to Depot | 25/07/2022 | 08/08/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 469 | -824745350_469
MML3RSTSPA6380 | TT_Task | GA11/GA21 (Phase II): Inspection for acceptance of Spares | 09/08/2022 | 13/08/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 470 | -824745350_470
MML3RSTSPA6390 | TT_Task | GA11/GA21 (Phase II): NONO/ NOWC from Project Manager | 14/08/2022 | 18/08/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 471 | -824745350_471
MML3RSTSPA6400 | TT_Task | GA11/GA21 (Phase II): Handing over | 19/08/2022 | 23/08/2022 | nan | nan | 2832 | TK_NotStart | -824745350 | 472 | -824745350_472
MML3RSTSPA6410 | TT_Task | GA12/GA22 (Phase II): List of Spares : Submission to Project Manager/ GC | 13/12/2019 | 14/12/2019 | 13/12/2019 | 14/12/2019 | 0 | TK_Complete | -824745350 | 461 | -824745350_461
MML3RSTSPA6420 | TT_Task | GA12/GA22 (Phase II): List of Spares : Comments from Project Manager/ GC | 16/12/2019 | 06/06/2020 | 16/12/2019 | 06/06/2020 | 0 | TK_Complete | -824745350 | 461 | -824745350_461
MML3RSTSPA6430 | TT_Task | GA12/GA22 (Phase II): List of Spares : Resubmission by Alstom | 08/06/2020 | 08/07/2020 | 08/06/2020 | 08/07/2020 | 0 | TK_Complete | -824745350 | 462 | -824745350_462
MML3RSTSPA6440 | TT_Task | GA12/GA22 (Phase II): List of Spares : NONO/ NOWC from Project Manager | 08/07/2020 | 08/07/2020 | 08/07/2020 | 08/07/2020 | 0 | TK_Complete | -824745350 | 463 | -824745350_463
MML3RSTSPA6450 | TT_Task | GA12/GA22 (Phase II): RFQ to Suppliers | 25/02/2022 | 11/03/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 464 | -824745350_464
MML3RSTSPA6460 | TT_Task | GA12/GA22 (Phase II): Receipt of Quotation | 12/03/2022 | 26/03/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 465 | -824745350_465
MML3RSTSPA6470 | TT_Task | GA12/GA22 (Phase II): Techno-commercial closures | 27/03/2022 | 10/04/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 466 | -824745350_466
MML3RSTSPA6480 | TT_Task | GA12/GA22 (Phase II): Business Award/ PO Release | 11/04/2022 | 25/04/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 467 | -824745350_467
MML3RSTSPA6490 | TT_Task | GA12/GA22 (Phase II): Procurement of Spares | 26/04/2022 | 24/07/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 468 | -824745350_468
MML3RSTSPA6500 | TT_Task | GA12/GA22 (Phase II): Packing ; Transportation to Depot | 25/07/2022 | 08/08/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 469 | -824745350_469
MML3RSTSPA6510 | TT_Task | GA12/GA22 (Phase II): Inspection for acceptance of Spares | 09/08/2022 | 13/08/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 470 | -824745350_470
MML3RSTSPA6520 | TT_Task | GA12/GA22 (Phase II): NONO/ NOWC from Project Manager | 14/08/2022 | 18/08/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 471 | -824745350_471
MML3RSTSPA6530 | TT_Task | GA12/GA22 (Phase II): Handing over | 19/08/2022 | 23/08/2022 | nan | nan | 4384 | TK_NotStart | -824745350 | 472 | -824745350_472
MML3RSTSPA6540 | TT_Task | GA14/GA24 (Phase II): List of Spares : Submission to Project Manager/ GC | 13/12/2019 | 14/12/2019 | 13/12/2019 | 14/12/2019 | 0 | TK_Complete | -824745350 | 461 | -824745350_461
MML3RSTSPA6550 | TT_Task | GA14/GA24 (Phase II): List of Spares : Comments from Project Manager/ GC | 16/12/2019 | 06/06/2020 | 16/12/2019 | 06/06/2020 | 0 | TK_Complete | -824745350 | 461 | -824745350_461
MML3RSTSPA6560 | TT_Task | GA14/GA24 (Phase II): List of Spares : Resubmission by Alstom | 08/06/2020 | 08/07/2020 | 08/06/2020 | 08/07/2020 | 0 | TK_Complete | -824745350 | 462 | -824745350_462
MML3RSTSPA6570 | TT_Task | GA14/GA24 (Phase II): List of Spares : NONO/ NOWC from Project Manager | 08/07/2020 | 08/07/2020 | 08/07/2020 | 08/07/2020 | 0 | TK_Complete | -824745350 | 463 | -824745350_463
MML3RSTSPA6580 | TT_Task | GA14/GA24 (Phase II): RFQ to Suppliers | 25/02/2022 | 11/03/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 464 | -824745350_464
MML3RSTSPA6590 | TT_Task | GA14/GA24 (Phase II): Receipt of Quotation | 12/03/2022 | 26/03/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 465 | -824745350_465
MML3RSTSPA6600 | TT_Task | GA14/GA24 (Phase II): Techno-commercial closures | 27/03/2022 | 10/04/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 466 | -824745350_466
MML3RSTSPA6610 | TT_Task | GA14/GA24 (Phase II): Business Award/ PO Release | 11/04/2022 | 25/04/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 467 | -824745350_467
MML3RSTSPA6620 | TT_Task | GA14/GA24 (Phase II): Procurement of Spares | 26/04/2022 | 24/07/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 468 | -824745350_468
MML3RSTSPA6630 | TT_Task | GA14/GA24 (Phase II): Packing ; Transportation to Depot | 25/07/2022 | 08/08/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 469 | -824745350_469
MML3RSTSPA6640 | TT_Task | GA14/GA24 (Phase II): Inspection for acceptance of Spares | 09/08/2022 | 13/08/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 470 | -824745350_470
MML3RSTSPA6650 | TT_Task | GA14/GA24 (Phase II): NONO/ NOWC from Project Manager | 14/08/2022 | 18/08/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 471 | -824745350_471
MML3RSTSPA6660 | TT_Task | GA14/GA24 (Phase II): Handing over | 19/08/2022 | 23/08/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 472 | -824745350_472
MML3RSTSPA6670 | TT_Task | GA13/GA23 (Phase II): List of Spares : Submission to Project Manager/ GC | 13/12/2019 | 14/12/2019 | 13/12/2019 | 14/12/2019 | 0 | TK_Complete | -824745350 | 461 | -824745350_461
MML3RSTSPA6680 | TT_Task | GA13/GA23 (Phase II): List of Spares : Comments from Project Manager/ GC | 16/12/2019 | 06/06/2020 | 16/12/2019 | 06/06/2020 | 0 | TK_Complete | -824745350 | 461 | -824745350_461
MML3RSTSPA6690 | TT_Task | GA13/GA23 (Phase II): List of Spares : Resubmission by Alstom | 08/06/2020 | 08/07/2020 | 08/06/2020 | 08/07/2020 | 0 | TK_Complete | -824745350 | 462 | -824745350_462
MML3RSTSPA6700 | TT_Task | GA13/GA23 (Phase II): List of Spares : NONO/ NOWC from Project Manager | 08/07/2020 | 08/07/2020 | 08/07/2020 | 08/07/2020 | 0 | TK_Complete | -824745350 | 463 | -824745350_463
MML3RSTSPA6710 | TT_Task | GA13/GA23 (Phase II): RFQ to Suppliers | 24/08/2022 | 12/09/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 464 | -824745350_464
MML3RSTSPA6720 | TT_Task | GA13/GA23 (Phase II): Receipt of Quotation | 13/09/2022 | 02/10/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 465 | -824745350_465
MML3RSTSPA6730 | TT_Task | GA13/GA23 (Phase II): Techno-commercial closures | 03/10/2022 | 22/10/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 466 | -824745350_466
MML3RSTSPA6740 | TT_Task | GA13/GA23 (Phase II): Business Award/ PO Release | 23/10/2022 | 11/11/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 467 | -824745350_467
MML3RSTSPA6750 | TT_Task | GA13/GA23 (Phase II): Procurement of Spares | 12/11/2022 | 10/04/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 468 | -824745350_468
MML3RSTSPA6760 | TT_Task | GA13/GA23 (Phase II): Packing ; Transportation to Depot | 11/04/2023 | 15/05/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 469 | -824745350_469
MML3RSTSPA6770 | TT_Task | GA13/GA23 (Phase II): Inspection for acceptance of Spares | 16/05/2023 | 29/05/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 470 | -824745350_470
MML3RSTSPA6780 | TT_Task | GA13/GA23 (Phase II): NONO/ NOWC from Project Manager | 30/05/2023 | 12/06/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 471 | -824745350_471
MML3RSTSPA6790 | TT_Task | GA13/GA23 (Phase II): Handing over | 13/06/2023 | 26/06/2023 | nan | nan | 1928 | TK_NotStart | -824745350 | 472 | -824745350_472
MML3RSTSPA6800 | TT_Task | GA41 (Phase II): List of Spares : Submission to Project Manager/ GC | 13/12/2019 | 14/12/2019 | 13/12/2019 | 14/12/2019 | 0 | TK_Complete | -824745350 | 463 | -824745350_463
MML3RSTSPA6810 | TT_Task | GA41 (Phase II): List of Spares : Comments from Project Manager/ GC | 16/12/2019 | 06/06/2020 | 16/12/2019 | 06/06/2020 | 0 | TK_Complete | -824745350 | 463 | -824745350_463
MML3RSTSPA6820 | TT_Task | GA41 (Phase II): List of Spares : Resubmission by Alstom | 08/06/2020 | 08/07/2020 | 08/06/2020 | 08/07/2020 | 0 | TK_Complete | -824745350 | 462 | -824745350_462
MML3RSTSPA6830 | TT_Task | GA41 (Phase II): List of Spares : NONO/ NOWC from Project Manager | 08/07/2020 | 08/07/2020 | 08/07/2020 | 08/07/2020 | 0 | TK_Complete | -824745350 | 463 | -824745350_463
MML3RSTSPA6840 | TT_Task | GA41 (Phase II): RFQ to Suppliers | 24/08/2022 | 12/09/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 464 | -824745350_464
MML3RSTSPA6850 | TT_Task | GA41 (Phase II): Receipt of Quotation | 13/09/2022 | 02/10/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 465 | -824745350_465
MML3RSTSPA6860 | TT_Task | GA41 (Phase II): Techno-commercial closures | 03/10/2022 | 22/10/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 466 | -824745350_466
MML3RSTSPA6870 | TT_Task | GA41 (Phase II): Business Award/ PO Release | 23/10/2022 | 11/11/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 467 | -824745350_467
MML3RSTSPA6880 | TT_Task | GA41 (Phase II): Procurement of Spares | 12/11/2022 | 10/04/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 468 | -824745350_468
MML3RSTSPA6890 | TT_Task | GA41 (Phase II): Packing ; Transportation to Depot | 11/04/2023 | 15/05/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 469 | -824745350_469
MML3RSTSPA6900 | TT_Task | GA41 (Phase II): Inspection for acceptance of Spares | 16/05/2023 | 29/05/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 470 | -824745350_470
MML3RSTSPA6910 | TT_Task | GA41 (Phase II): NONO/ NOWC from Project Manager | 30/05/2023 | 12/06/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 471 | -824745350_471
MML3RSTSPA6920 | TT_Task | GA41 (Phase II): Handing over | 13/06/2023 | 26/06/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 472 | -824745350_472
MML3RSTTRN1000 | TT_Task | TRA System Overview | 14/03/2023 | 14/03/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 473 | -824745350_473
MML3RSTTRN1010 | TT_Task | TRA Doors ; VAC and Cab Equipment | 15/03/2023 | 15/03/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 474 | -824745350_474
MML3RSTTRN1020 | TT_Task | TRA TCMS | 16/03/2023 | 16/03/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 473 | -824745350_473
MML3RSTTRN1030 | TT_Task | TRA Brakes | 17/03/2023 | 17/03/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 475 | -824745350_475
MML3RSTTRN1040 | TT_Task | TRA Driving Procedure ; CEC Cabinet | 18/03/2023 | 18/03/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 476 | -824745350_476
MML3RSTTRN1050 | TT_Task | TRA Traction, Propulsion ; Normal Modes of Train Operation | 19/03/2023 | 19/03/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 477 | -824745350_477
MML3RSTTRN1060 | TT_Task | TRA Degraded Operation; Emergency Operation | 20/03/2023 | 20/03/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 478 | -824745350_478
MML3RSTTRN1070 | TT_Task | TRA Train Familiarization(includes saloon ; Cab) | 21/03/2023 | 21/03/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 477 | -824745350_477
MML3RSTTRN1080 | TT_Task | TRA Safety features(location of fire extinguisher ,camera, PEI operation) ; PAPIS, Radio | 22/03/2023 | 22/03/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 478 | -824745350_478
MML3RSTTRN1090 | TT_Task | TRA TCMS (operation ; Controls) | 23/03/2023 | 23/03/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 473 | -824745350_473
MML3RSTTRN1100 | TT_Task | TRA CEC panel familiarization | 24/03/2023 | 24/03/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 476 | -824745350_476
MML3RSTTRN1110 | TT_Task | TRA Door | 25/03/2023 | 25/03/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 474 | -824745350_474
MML3RSTTRN1120 | TT_Task | TRA Brake | 26/03/2023 | 26/03/2023 | nan | nan | 408 | TK_NotStart | -824745350 | 475 | -824745350_475
MML3RSTTRN1130 | TT_Task | TRA Pre-departure Check included in Checklist | 24/03/2023 | 24/03/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 479 | -824745350_479
MML3RSTTRN1140 | TT_Task | TRA Driver KM | 25/03/2023 | 28/03/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 480 | -824745350_480
MML3RSTTRN1150 | TT_Task | TRA Coupling Procedure | 29/03/2023 | 29/03/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 473 | -824745350_473
MML3RSTTRN1160 | TT_Task | TRA Operation of Emergency Detrainment Door | 30/03/2023 | 30/03/2023 | nan | nan | 376 | TK_NotStart | -824745350 | 248 | -824745350_248
MML3RSTTRN1170 | TT_Task | TRA Maintenance Training(Theoritical) | 10/10/2022 | 08/12/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 481 | -824745350_481
MML3RSTTRN1180 | TT_Task | TRA Maintenance Training(Hands on) | 09/12/2022 | 11/02/2023 | nan | nan | 632 | TK_NotStart | -824745350 | 481 | -824745350_481
MML3RSTTRN1190 | TT_Task | TRA Stage 1(Theoritical ) | 31/10/2022 | 29/12/2022 | nan | nan | 0 | TK_NotStart | -824745350 | 482 | -824745350_482
MML3RSTTRN1200 | TT_Task | TRA OEM Stage 2(Hands on Train) | 30/12/2022 | 04/03/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 482 | -824745350_482
MML3RSTTRN1210 | TT_Task | TRA Stage 1- Repeat | 05/03/2023 | 03/05/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 482 | -824745350_482
MML3RSTTRN1220 | TT_Task | TRA OEM Stage 2 Repeat | 04/05/2023 | 07/07/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 482 | -824745350_482
MML3RSTTRN1230 | TT_Task | TRA MMIS,PPIO, Stores ; Inventory Control | 08/07/2023 | 28/08/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 483 | -824745350_483
MML3RSTTRN1240 | TT_Task | TRA Maintenance Demonstration training | 29/08/2023 | 16/11/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 481 | -824745350_481
MML3RSTTRN1250 | TT_Task | TRA Special tools | 17/11/2023 | 05/01/2024 | nan | nan | 0 | TK_NotStart | -824745350 | 473 | -824745350_473
MML3RSTTRN1260 | TT_Task | TRA 10% reserved for miscellaneous Training requirements | 06/01/2024 | 22/02/2024 | nan | nan | 0 | TK_NotStart | -824745350 | 481 | -824745350_481
MML3RSTTRN1270 | TT_Task | TRA Off-shore training to Operators(Batch 1) | 19/12/2023 | 28/12/2023 | nan | nan | 0 | TK_NotStart | -824745350 | 484 | -824745350_484
MML3RSTTRN1280 | TT_Task | TRA Off-shore training to Operators(Batch 2) | 29/12/2023 | 07/01/2024 | nan | nan | 368 | TK_NotStart | -824745350 | 484 | -824745350_484
MML3RSTTRN1290 | TT_Task | TRA Off-shore training to Operators(Batch 1) | 29/12/2023 | 02/01/2024 | nan | nan | 0 | TK_NotStart | -824745350 | 484 | -824745350_484
MML3RSTTRN1300 | TT_Task | TRA Off-shore training to Operators(Batch 2) | 03/01/2024 | 07/01/2024 | nan | nan | 368 | TK_NotStart | -824745350 | 484 | -824745350_484
MML3RSTTRN1310 | TT_Task | TRA Driver Training (Batch 1) | 24/03/2023 | 02/04/2023 | nan | nan | 352 | TK_NotStart | -824745350 | 480 | -824745350_480
MML3RSTTRN1320 | TT_Task | TRA Driver Training (Batch 2) | 29/11/2023 | 08/12/2023 | nan | nan | 608 | TK_NotStart | -824745350 | 480 | -824745350_480
MML3RSTASB1000 | TT_Task | As Built Submission: Test Specification of Battery System | 29/12/2023 | 27/01/2024 | nan | nan | 240 | TK_NotStart | -824745350 | 185 | -824745350_185
MML3RSTASB1010 | TT_Task | As Built Submission: Train Operation Control Description | 29/12/2023 | 27/01/2024 | nan | nan | 240 | TK_NotStart | -824745350 | 224 | -824745350_224
MML3RSTASB1020 | TT_Task | As Built Submission: Energy Consumption Anlaysis | 29/12/2023 | 27/01/2024 | nan | nan | 240 | TK_NotStart | -824745350 | 186 | -824745350_186
MML3RSTASB1030 | TT_Task | As Built Submission: Ride Index Test Specification | 29/12/2023 | 27/01/2024 | nan | nan | 240 | TK_NotStart | -824745350 | 187 | -824745350_187
MML3RSTASB1040 | TT_Task | As Built Submission: Final Vehicle Performance | 29/12/2023 | 27/01/2024 | nan | nan | 240 | TK_NotStart | -824745350 | 116 | -824745350_116
MML3RSTASB1050 | TT_Task | As Built Submission: Inspection instruction of complete Bogie | 29/12/2023 | 27/01/2024 | nan | nan | 240 | TK_NotStart | -824745350 | 188 | -824745350_188
MML3RSTASB1060 | TT_Task | As Built Submission: Vehicle Dynamic Analysis of Bogie | 29/12/2023 | 27/01/2024 | nan | nan | 240 | TK_NotStart | -824745350 | 189 | -824745350_189
MML3RSTASB1070 | TT_Task | As Built Submission: FEA of Bogie Frame | 29/12/2023 | 27/01/2024 | nan | nan | 240 | TK_NotStart | -824745350 | 190 | -824745350_190
MML3RSTASB1080 | TT_Task | As Built Submission: Test Specification of Bogie Frame static load / Fatigue load | 29/12/2023 | 27/01/2024 | nan | nan | 240 | TK_NotStart | -824745350 | 191 | -824745350_191
MML3RSTASB1090 | TT_Task | As Built Submission: Test Specification of Primary suspension | 29/12/2023 | 27/01/2024 | nan | nan | 240 | TK_NotStart | -824745350 | 192 | -824745350_192
MML3RSTASB1100 | TT_Task | As Built Submission: Test Specification of Damper | 29/12/2023 | 27/01/2024 | nan | nan | 240 | TK_NotStart | -824745350 | 193 | -824745350_193
MML3RSTASB1110 | TT_Task | As Built Submission: Test Specification of Wheel | 29/12/2023 | 27/01/2024 | nan | nan | 240 | TK_NotStart | -824745350 | 194 | -824745350_194
MML3RSTASB1120 | TT_Task | As Built Submission: Test specification of Axle | 29/12/2023 | 27/01/2024 | nan | nan | 240 | TK_NotStart | -824745350 | 195 | -824745350_195
MML3RSTASB1130 | TT_Task | As Built Submission: Thermal Calculations of Wheel | 29/12/2023 | 27/01/2024 | nan | nan | 240 | TK_NotStart | -824745350 | 196 | -824745350_196
MML3RSTASB1140 | TT_Task | As Built Submission: Wheel Stress calculations | 29/12/2023 | 27/01/2024 | nan | nan | 240 | TK_NotStart | -824745350 | 225 | -824745350_225
MML3RSTASB1150 | TT_Task | As Built Submission: Axle strength calculations | 29/12/2023 | 27/01/2024 | nan | nan | 240 | TK_NotStart | -824745350 | 195 | -824745350_195
MML3RSTASB1160 | TT_Task | As Built Submission: FEA of center pivot, axle box and Traction Linkage | 29/12/2023 | 27/01/2024 | nan | nan | 240 | TK_NotStart | -824745350 | 197 | -824745350_197
MML3RSTASB1170 | TT_Task | As Built Submission: Test Specification of Driving gear system | 29/12/2023 | 27/01/2024 | nan | nan | 240 | TK_NotStart | -824745350 | 226 | -824745350_226
MML3RSTASB1180 | TT_Task | As Built Submission: Test Specification of Gearbox | 29/12/2023 | 27/01/2024 | nan | nan | 240 | TK_NotStart | -824745350 | 226 | -824745350_226
MML3RSTASB1190 | TT_Task | As Built Submission: Gear, analysis of stresses, selection of bearing, gear case and transmissioin | 29/12/2023 | 27/01/2024 | nan | nan | 240 | TK_NotStart | -824745350 | 198 | -824745350_198
MML3RSTASB1200 | TT_Task | As Built Submission: Test specification of Wheel Flange Lubricator | 29/12/2023 | 27/01/2024 | nan | nan | 240 | TK_NotStart | -824745350 | 144 | -824745350_144
MML3RSTASB1210 | TT_Task | As Built Submission: Life cycle calculation of Axle Box | 29/12/2023 | 27/01/2024 | nan | nan | 240 | TK_NotStart | -824745350 | 199 | -824745350_199
MML3RSTASB1220 | TT_Task | As Built Submission: Brake Performance Calculations | 29/12/2023 | 27/01/2024 | nan | nan | 240 | TK_NotStart | -824745350 | 227 | -824745350_227
MML3RSTASB1230 | TT_Task | As Built Submission: Test specification of Passenger saloon Door | 29/12/2023 | 27/01/2024 | nan | nan | 240 | TK_NotStart | -824745350 | 146 | -824745350_146
MML3RSTASB1240 | TT_Task | As Built Submission: Test specification of Front Detrainment Doors | 29/12/2023 | 27/01/2024 | nan | nan | 240 | TK_NotStart | -824745350 | 89 | -824745350_89
MML3RSTASB1250 | TT_Task | As Built Submission: Test specification of 25 kV Vacuum Circuit Breaker | 29/12/2023 | 27/01/2024 | nan | nan | 240 | TK_NotStart | -824745350 | 147 | -824745350_147
MML3RSTASB1260 | TT_Task | As Built Submission: Test specification of Surge Arrestor | 29/12/2023 | 27/01/2024 | nan | nan | 240 | TK_NotStart | -824745350 | 149 | -824745350_149
MML3RSTASB1270 | TT_Task | As Built Submission: Test Specification of Traction Convertor | 29/12/2023 | 27/01/2024 | nan | nan | 240 | TK_NotStart | -824745350 | 150 | -824745350_150
MML3RSTASB1280 | TT_Task | As Built Submission: Test Specification of Traction Motor | 29/12/2023 | 27/01/2024 | nan | nan | 240 | TK_NotStart | -824745350 | 151 | -824745350_151
MML3RSTASB1290 | TT_Task | As Built Submission: Test specification of Roof Mounted Pantograph | 29/12/2023 | 27/01/2024 | nan | nan | 240 | TK_NotStart | -824745350 | 200 | -824745350_200
MML3RSTASB1300 | TT_Task | As Built Submission: Test specification of Transformer | 29/12/2023 | 27/01/2024 | nan | nan | 240 | TK_NotStart | -824745350 | 176 | -824745350_176
MML3RSTASB1310 | TT_Task | As Built Submission: Test specification of Earthing Switch | 29/12/2023 | 27/01/2024 | nan | nan | 240 | TK_NotStart | -824745350 | 148 | -824745350_148
MML3RSTASB1320 | TT_Task | As Built Submission: Harmonic Calculations | 29/12/2023 | 27/01/2024 | nan | nan | 240 | TK_NotStart | -824745350 | 201 | -824745350_201
MML3RSTASB1330 | TT_Task | As Built Submission: Test Specification of Auxiliary Convertor | 29/12/2023 | 27/01/2024 | nan | nan | 240 | TK_NotStart | -824745350 | 153 | -824745350_153
MML3RSTASB1340 | TT_Task | As Built Submission: Software document for Door System | 29/12/2023 | 27/01/2024 | nan | nan | 240 | TK_NotStart | -824745350 | 202 | -824745350_202
MML3RSTASB1350 | TT_Task | As Built Submission: Software document for VAC System | 29/12/2023 | 27/01/2024 | nan | nan | 240 | TK_NotStart | -824745350 | 125 | -824745350_125
MML3RSTASB1360 | TT_Task | As Built Submission: Software document for Brake system | 29/12/2023 | 27/01/2024 | nan | nan | 0 | TK_NotStart | -824745350 | 118 | -824745350_118
MML3RSTASB1370 | TT_Task | As Built Submission: Software document for propulsion system | 28/01/2024 | 26/02/2024 | nan | nan | 0 | TK_NotStart | -824745350 | 122 | -824745350_122
MML3RSTASB1380 | TT_Task | As Built Submission: Software document for Auxiliary supply system | 28/01/2024 | 26/02/2024 | nan | nan | 0 | TK_NotStart | -824745350 | 124 | -824745350_124
MML3RSTASB1390 | TT_Task | As Built Submission: Test Specification of Saloon VAC | 28/01/2024 | 26/02/2024 | nan | nan | 0 | TK_NotStart | -824745350 | 157 | -824745350_157
MML3RSTASB1400 | TT_Task | As Built Submission: Test Specification of Dynamometer Test | 28/01/2024 | 26/02/2024 | nan | nan | 0 | TK_NotStart | -824745350 | 203 | -824745350_203
MML3RSTASB1410 | TT_Task | As Built Submission: Detail Description of Bogie Brake Equipment | 28/01/2024 | 26/02/2024 | nan | nan | 0 | TK_NotStart | -824745350 | 204 | -824745350_204
MML3RSTASB1420 | TT_Task | As Built Submission: Test Specification for Air Supply System | 28/01/2024 | 26/02/2024 | nan | nan | 0 | TK_NotStart | -824745350 | 228 | -824745350_228
MML3RSTASB1430 | TT_Task | As Built Submission: Type Test Specification - Saloon Lighting and Gangway Lighting | 28/01/2024 | 26/02/2024 | nan | nan | 0 | TK_NotStart | -824745350 | 205 | -824745350_205
MML3RSTASB1440 | TT_Task | As Built Submission: Description for Neutral Section Detection and functioning | 28/01/2024 | 26/02/2024 | nan | nan | 0 | TK_NotStart | -824745350 | 206 | -824745350_206
MML3RSTASB1450 | TT_Task | As Built Submission: Electrical Pure Principle scheme - Train | 28/01/2024 | 26/02/2024 | nan | nan | 0 | TK_NotStart | -824745350 | 207 | -824745350_207
MML3RSTASB1460 | TT_Task | As Built Submission: Test Specification of Master Controller | 28/01/2024 | 26/02/2024 | nan | nan | 0 | TK_NotStart | -824745350 | 162 | -824745350_162
MML3RSTASB1470 | TT_Task | As Built Submission: Technical specification and Drawings of PAPIS | 28/01/2024 | 26/02/2024 | nan | nan | 0 | TK_NotStart | -824745350 | 208 | -824745350_208
MML3RSTASB1480 | TT_Task | As Built Submission: Test Specification of PAPIS system | 28/01/2024 | 26/02/2024 | nan | nan | 0 | TK_NotStart | -824745350 | 138 | -824745350_138
MML3RSTASB1490 | TT_Task | As Built Submission: Solution Principal Scheme | 28/01/2024 | 26/02/2024 | nan | nan | 0 | TK_NotStart | -824745350 | 209 | -824745350_209
MML3RSTASB1500 | TT_Task | As Built Submission: Test Specification - Gangway | 28/01/2024 | 26/02/2024 | nan | nan | 0 | TK_NotStart | -824745350 | 233 | -824745350_233
MML3RSTASB1510 | TT_Task | As Built Submission: Type Test Specification - Load test of Floor panel | 28/01/2024 | 26/02/2024 | nan | nan | 0 | TK_NotStart | -824745350 | 210 | -824745350_210
MML3RSTASB1520 | TT_Task | As Built Submission: Type Test Specification - Windscreen | 28/01/2024 | 26/02/2024 | nan | nan | 0 | TK_NotStart | -824745350 | 211 | -824745350_211
MML3RSTASB1530 | TT_Task | As Built Submission: Type Test Specification - Windows | 28/01/2024 | 26/02/2024 | nan | nan | 0 | TK_NotStart | -824745350 | 212 | -824745350_212
MML3RSTASB1540 | TT_Task | As Built Submission: Type Test Specification - Interior Components | 28/01/2024 | 26/02/2024 | nan | nan | 0 | TK_NotStart | -824745350 | 212 | -824745350_212
MML3RSTASB1550 | TT_Task | As Built Submission: Type Test Specification - Gauging (Static + Kinematic) | 28/01/2024 | 26/02/2024 | nan | nan | 0 | TK_NotStart | -824745350 | 213 | -824745350_213
MML3RSTASB1560 | TT_Task | As Built Submission: Type Test Specification - Straphangers Endurance | 28/01/2024 | 26/02/2024 | nan | nan | 0 | TK_NotStart | -824745350 | 214 | -824745350_214
MML3RSTASB1570 | TT_Task | As Built Submission: Type Test Specification - Couplers | 28/01/2024 | 26/02/2024 | nan | nan | 0 | TK_NotStart | -824745350 | 215 | -824745350_215
MML3RSTASB1580 | TT_Task | As Built Submission: Type Test Specification - Floor Fire Resistance | 28/01/2024 | 26/02/2024 | nan | nan | 0 | TK_NotStart | -824745350 | 216 | -824745350_216
MML3RSTASB1590 | TT_Task | As Built Submission: Fire Engineering Report - Prediction | 28/01/2024 | 26/02/2024 | nan | nan | 0 | TK_NotStart | -824745350 | 217 | -824745350_217
MML3RSTASB1600 | TT_Task | As Built Submission: Noise Report - Final Prediction | 28/01/2024 | 26/02/2024 | nan | nan | 0 | TK_NotStart | -824745350 | 179 | -824745350_179
MML3RSTASB1610 | TT_Task | As Built Submission: Operation ; MaintenanceManuals Plan | 28/01/2024 | 26/02/2024 | nan | nan | 0 | TK_NotStart | -824745350 | 485 | -824745350_485
MML3RSTASB1620 | TT_Task | As Built Submission: Training Plan | 28/01/2024 | 26/02/2024 | nan | nan | 0 | TK_NotStart | -824745350 | 174 | -824745350_174
MML3RSTASB1630 | TT_Task | As Built Submission: Spare Management Plan | 28/01/2024 | 26/02/2024 | nan | nan | 0 | TK_NotStart | -824745350 | 26 | -824745350_26
MML3RSTASB1640 | TT_Task | As Built Submission: Assistance of Maintenance Plan | 28/01/2024 | 26/02/2024 | nan | nan | 0 | TK_NotStart | -824745350 | 485 | -824745350_485
MML3RSTASB1650 | TT_Task | As Built Submission: Comprehensive Maintenance Plan | 28/01/2024 | 26/02/2024 | nan | nan | 0 | TK_NotStart | -824745350 | 485 | -824745350_485
MML3RSTASB1660 | TT_Task | As Built Submission: Spare Parts List | 28/01/2024 | 26/02/2024 | nan | nan | 0 | TK_NotStart | -824745350 | 218 | -824745350_218
MML3RSTASB1670 | TT_Task | As Built Submission: Train Simulator ; CBT Specification | 28/01/2024 | 26/02/2024 | nan | nan | 0 | TK_NotStart | -824745350 | 219 | -824745350_219
MML3RSTASB1680 | TT_Task | As Built Submission: Maintenance Demonstration plan | 28/01/2024 | 26/02/2024 | nan | nan | 0 | TK_NotStart | -824745350 | 485 | -824745350_485
MML3RSTASB1690 | TT_Task | As Built Submission: Quantitative fault tree analysis | 28/01/2024 | 26/02/2024 | nan | nan | 0 | TK_NotStart | -824745350 | 220 | -824745350_220
MML3RSTASB1700 | TT_Task | As Built Submission: FAI/ FATlure modes effects and criticality analysis (FMECA) | 28/01/2024 | 26/02/2024 | nan | nan | 0 | TK_NotStart | -824745350 | 339 | -824745350_339
MML3RSTASB1710 | TT_Task | As Built Submission: Design Safety Study Report | 28/01/2024 | 26/02/2024 | nan | nan | 0 | TK_NotStart | -824745350 | 235 | -824745350_235
MML3RSTASB1720 | TT_Task | As Built Submission: Hazard Log | 28/01/2024 | 26/02/2024 | nan | nan | 0 | TK_NotStart | -824745350 | 221 | -824745350_221
MML3RSTASB1730 | TT_Task | As Built Submission: Safety Critical Item List | 28/01/2024 | 26/02/2024 | nan | nan | 0 | TK_NotStart | -824745350 | 231 | -824745350_231
MML3RSTASB1740 | TT_Task | As Built Submission: Reliability Critical Item List | 28/01/2024 | 26/02/2024 | nan | nan | 0 | TK_NotStart | -824745350 | 231 | -824745350_231
MML3RSTASB1750 | TT_Task | As Built Submission: RAM demonstration ; FRACAS Plan | 28/01/2024 | 26/02/2024 | nan | nan | 0 | TK_NotStart | -824745350 | 232 | -824745350_232
MML3RSTASB1760 | TT_Task | As Built Submission: Application Safety Case | 28/01/2024 | 26/02/2024 | nan | nan | 0 | TK_NotStart | -824745350 | 235 | -824745350_235
MML3RSTASB1770 | TT_Task | As Built Submission: Test Specification of Wayside Measurement ; Monitoring System | 28/01/2024 | 26/02/2024 | nan | nan | 0 | TK_NotStart | -824745350 | 222 | -824745350_222
MML3RSTASB1780 | TT_Task | As Built Submission: Technical Specification of CMMS | 28/01/2024 | 26/02/2024 | nan | nan | 0 | TK_NotStart | -824745350 | 223 | -824745350_223
MML3RSTCI1000 | TT_Task | SWC IMPACT: Tamil Nadu Lockdown Impact | 10/05/2021 | 06/06/2021 | 10/05/2021 | 06/06/2021 | 0 | TK_Complete | -824745350 | 486 | -824745350_486
MML3RSTCI1010 | TT_Task | SWC IMPACT: Delay in Supplier Availablity | 25/02/2022 | 01/03/2022 | 30/04/2021 | 25/02/2022 | 0 | TK_Complete | -824745350 | 487 | -824745350_487
MML3RSTCI1020 | TT_Task | SWC IMPACT: Mettalic Supplies | 25/06/2021 | 29/06/2021 | 25/06/2021 | 29/06/2021 | 0 | TK_Complete | -824745350 | 487 | -824745350_487
MML3RSTCI1030 | TT_Task | SWC IMPACT: Karnatka Lockdown | 27/04/2021 | 15/06/2021 | 27/04/2021 | 15/06/2021 | 0 | TK_Complete | -824745350 | 486 | -824745350_486
MML3RSTCI1040 | TT_Task | SWC IMPACT: CJB Plant Shutdown | 25/05/2021 | 07/06/2021 | 10/05/2021 | 25/06/2021 | 0 | TK_Complete | -824745350 | 486 | -824745350_486
A168210 | TT_Task | Application for Approval: Manufacturing Approval (TFA sections 10.5.4-10.5.5) | 02/01/2023 | 13/01/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 1 | 94810358_1
A168220 | TT_Task | Application for Approval: Delivery Certificate, 1st Trainset Final Assembly (TFA section 10.4.2) | 28/01/2021 | 10/02/2021 | 07/12/2020 | 21/12/2020 | 0 | TK_Complete | 94810358 | 2 | 94810358_2
A168230 | TT_Task | Application for Approval: Design-certificate DDR (section 10.3.2) | 15/11/2019 | 28/11/2019 | 15/11/2019 | 02/12/2019 | 0 | TK_Complete | 94810358 | 3 | 94810358_3
A168240 | TT_Task | Application for Approval: Design-certificate PDR (section 10.3.2) | 22/05/2019 | 04/06/2019 | 22/05/2019 | 28/06/2019 | 0 | TK_Complete | 94810358 | 3 | 94810358_3
A168250 | TT_Task | Application for Approval: Design-certificate CDR (section 10.3.2) | 03/12/2018 | 14/12/2018 | 07/11/2018 | 20/12/2018 | 0 | TK_Complete | 94810358 | 3 | 94810358_3
A79330 | TT_Task | Application for Approval: Updated Project Plan (section 10.2) | 04/04/2018 | 29/05/2018 | 04/04/2018 | 21/06/2018 | 0 | TK_Complete | 94810358 | 4 | 94810358_4
A167030 | TT_Task | Prepare For Ditlott | 04/04/2018 | 19/12/2018 | 04/04/2018 | 22/06/2018 | 0 | TK_Complete | 94810358 | 5 | 94810358_5
A167080 | TT_Task | Internal Preparation for Joint Planning of c-PDRs | 08/11/2018 | 25/07/2019 | 01/11/2018 | 06/11/2018 | 0 | TK_Complete | 94810358 | 6 | 94810358_6
A167100 | TT_Task | Translation of Project Plan Documents | 09/07/2018 | 25/03/2019 | 09/07/2018 | 02/11/2018 | 0 | TK_Complete | 94810358 | 7 | 94810358_7
A167150 | TT_Task | Monthly Project Meeting 001 | 12/06/2018 | 26/02/2019 | 04/06/2018 | 05/06/2018 | 0 | TK_Complete | 94810358 | 8 | 94810358_8
A167200 | TT_Task | Monthly Project Meeting 002 | 14/08/2018 | 30/04/2019 | 14/08/2018 | 14/08/2018 | 0 | TK_Complete | 94810358 | 8 | 94810358_8
A167210 | TT_Task | Monthly Project Meeting 003 | 18/09/2018 | 04/06/2019 | 18/09/2018 | 18/09/2018 | 0 | TK_Complete | 94810358 | 8 | 94810358_8
A167220 | TT_Task | Monthly Project Meeting 004 | 18/10/2018 | 04/07/2019 | 17/10/2018 | 18/10/2018 | 0 | TK_Complete | 94810358 | 8 | 94810358_8
A167230 | TT_Task | Monthly Project Meeting 005 | 07/11/2018 | 24/07/2019 | 06/11/2018 | 07/11/2018 | 0 | TK_Complete | 94810358 | 8 | 94810358_8
A167240 | TT_Task | Monthly Project Meeting 006 | 18/12/2018 | 03/09/2019 | 18/12/2018 | 20/12/2018 | 0 | TK_Complete | 94810358 | 8 | 94810358_8
A167250 | TT_Task | Monthly Project Meeting 007 | 08/01/2019 | 24/09/2019 | 15/01/2019 | 15/01/2019 | 0 | TK_Complete | 94810358 | 8 | 94810358_8
A167260 | TT_Task | Monthly Project Meeting 008 | 12/02/2019 | 29/10/2019 | 12/02/2019 | 12/02/2019 | 0 | TK_Complete | 94810358 | 8 | 94810358_8
A167270 | TT_Task | Monthly Project Meeting 009 | 12/03/2019 | 26/11/2019 | 12/03/2019 | 12/03/2019 | 0 | TK_Complete | 94810358 | 8 | 94810358_8
A167280 | TT_Task | Monthly Project Meeting 010 | 09/04/2019 | 24/12/2019 | 09/04/2019 | 09/04/2019 | 0 | TK_Complete | 94810358 | 8 | 94810358_8
A167290 | TT_Task | Monthly Project Meeting 011 | 14/05/2019 | 28/01/2020 | 14/05/2019 | 14/05/2019 | 0 | TK_Complete | 94810358 | 8 | 94810358_8
A167300 | TT_Task | Monthly Project Meeting 012 | 19/06/2019 | 04/03/2020 | 11/06/2019 | 11/06/2019 | 0 | TK_Complete | 94810358 | 8 | 94810358_8
A167330 | TT_Task | Monthly Project Meeting 015 | 10/09/2019 | 26/05/2020 | 10/09/2019 | 10/09/2019 | 0 | TK_Complete | 94810358 | 8 | 94810358_8
A167340 | TT_Task | Monthly Project Meeting 016 | 08/10/2019 | 23/06/2020 | 08/10/2019 | 08/10/2019 | 0 | TK_Complete | 94810358 | 8 | 94810358_8
A167350 | TT_Task | Monthly Project Meeting 017 | 05/11/2019 | 21/07/2020 | 05/11/2019 | 05/11/2019 | 0 | TK_Complete | 94810358 | 8 | 94810358_8
A167360 | TT_Task | Monthly Project Meeting 018 | 10/12/2019 | 25/08/2020 | 10/12/2019 | 10/12/2019 | 0 | TK_Complete | 94810358 | 8 | 94810358_8
A167370 | TT_Task | Monthly Project Meeting 019 | 14/01/2020 | 29/09/2020 | 14/01/2020 | 14/01/2020 | 0 | TK_Complete | 94810358 | 8 | 94810358_8
A184800 | TT_Task | Monthly Project Meeting 020 | 02/03/2020 | 16/11/2020 | 11/02/2020 | 11/02/2020 | 0 | TK_Complete | 94810358 | 9 | 94810358_9
A184810 | TT_Task | Monthly Project Meeting 021 | 01/09/2020 | 18/05/2021 | 10/03/2020 | 10/03/2020 | 0 | TK_Complete | 94810358 | 9 | 94810358_9
A184820 | TT_Task | Monthly Project Meeting 022 | 01/09/2020 | 18/05/2021 | 07/04/2020 | 07/04/2020 | 0 | TK_Complete | 94810358 | 9 | 94810358_9
A184830 | TT_Task | Monthly Project Meeting 023 | 01/09/2020 | 18/05/2021 | 05/05/2020 | 05/05/2020 | 0 | TK_Complete | 94810358 | 9 | 94810358_9
A184840 | TT_Task | Monthly Project Meeting 024 | 01/09/2020 | 18/05/2021 | 16/06/2020 | 16/06/2020 | 0 | TK_Complete | 94810358 | 9 | 94810358_9
A185360 | TT_Task | Monthly Project Meeting 025 | 13/11/2020 | 30/07/2021 | 27/10/2020 | 27/10/2020 | 0 | TK_Complete | 94810358 | 9 | 94810358_9
A185370 | TT_Task | Monthly Project Meeting 026 | 03/12/2020 | 19/08/2021 | 24/11/2020 | 24/11/2020 | 0 | TK_Complete | 94810358 | 9 | 94810358_9
A185380 | TT_Task | Monthly Project Meeting 027 | 18/12/2020 | 03/09/2021 | 15/12/2020 | 15/12/2020 | 0 | TK_Complete | 94810358 | 9 | 94810358_9
A185390 | TT_Task | Monthly Project Meeting 028 | 15/01/2021 | 01/10/2021 | 19/01/2021 | 19/01/2021 | 0 | TK_Complete | 94810358 | 8 | 94810358_8
A185560 | TT_Task | Monthly Project Meeting 029 | 25/03/2021 | 09/12/2021 | 23/02/2021 | 23/02/2021 | 0 | TK_Complete | 94810358 | 9 | 94810358_9
A185570 | TT_Task | Monthly Project Meeting 030 | 25/03/2021 | 09/12/2021 | 23/03/2021 | 23/03/2021 | 0 | TK_Complete | 94810358 | 9 | 94810358_9
A185580 | TT_Task | Monthly Project Meeting 031 | 20/04/2021 | 04/01/2022 | 20/04/2021 | 20/04/2021 | 0 | TK_Complete | 94810358 | 9 | 94810358_9
A185590 | TT_Task | Monthly Project Meeting 032 | 18/05/2021 | 01/02/2022 | 18/05/2021 | 18/05/2021 | 0 | TK_Complete | 94810358 | 9 | 94810358_9
A187200 | TT_Task | Monthly Project Meeting 033 | 15/06/2021 | 01/03/2022 | 15/06/2021 | 15/06/2021 | 0 | TK_Complete | 94810358 | 9 | 94810358_9
A187460 | TT_Task | Monthly Project Meeting 034 | 27/08/2021 | 13/05/2022 | 17/08/2021 | 17/08/2021 | 0 | TK_Complete | 94810358 | 9 | 94810358_9
A188230 | TT_Task | Monthly Project Meeting 035 | 24/09/2021 | 10/06/2022 | 14/09/2021 | 14/09/2021 | 0 | TK_Complete | 94810358 | 9 | 94810358_9
A188240 | TT_Task | Monthly Project Meeting 036 | 26/11/2021 | 12/08/2022 | 19/10/2021 | 19/10/2021 | 0 | TK_Complete | 94810358 | 9 | 94810358_9
A188250 | TT_Task | Monthly Project Meeting 037 | 26/11/2021 | 12/08/2022 | 16/11/2021 | 16/11/2021 | 0 | TK_Complete | 94810358 | 9 | 94810358_9
A188260 | TT_Task | Monthly Project Meeting 038 | 07/12/2021 | 23/08/2022 | 07/12/2021 | 07/12/2021 | 0 | TK_Complete | 94810358 | 8 | 94810358_8
A190210 | TT_Task | Monthly Project Meeting 039 | 18/01/2022 | 04/10/2022 | nan | nan | 16744 | TK_NotStart | 94810358 | 9 | 94810358_9
A190220 | TT_Task | Monthly Project Meeting 040 | 15/02/2022 | 01/11/2022 | nan | nan | 16584 | TK_NotStart | 94810358 | 9 | 94810358_9
A190230 | TT_Task | Monthly Project Meeting 041 | 15/03/2022 | 29/11/2022 | nan | nan | 16424 | TK_NotStart | 94810358 | 9 | 94810358_9
A190240 | TT_Task | Monthly Project Meeting 042 | 26/04/2022 | 10/01/2023 | nan | nan | 16184 | TK_NotStart | 94810358 | 9 | 94810358_9
A190250 | TT_Task | Monthly Project Meeting 043 | 24/05/2022 | 07/02/2023 | nan | nan | 16024 | TK_NotStart | 94810358 | 9 | 94810358_9
A190260 | TT_Task | Monthly Project Meeting 044 | 21/06/2022 | 07/03/2023 | nan | nan | 15864 | TK_NotStart | 94810358 | 9 | 94810358_9
A167140 | TT_Task | SteCo 001 | 30/05/2018 | 13/02/2019 | 30/05/2018 | 30/05/2018 | 0 | TK_Complete | 94810358 | 10 | 94810358_10
A167160 | TT_Task | SteCo 002 | 20/08/2018 | 06/05/2019 | 20/08/2018 | 20/08/2018 | 0 | TK_Complete | 94810358 | 11 | 94810358_11
A167380 | TT_Task | SteCo 003 | 16/11/2018 | 02/08/2019 | 16/11/2018 | 16/11/2018 | 0 | TK_Complete | 94810358 | 11 | 94810358_11
A167390 | TT_Task | SteCo 004 | 06/03/2019 | 20/11/2019 | 06/03/2019 | 06/03/2019 | 0 | TK_Complete | 94810358 | 11 | 94810358_11
A167400 | TT_Task | SteCo 005 | 19/06/2019 | 04/03/2020 | 19/06/2019 | 19/06/2019 | 0 | TK_Complete | 94810358 | 11 | 94810358_11
A184240 | TT_Task | SteCo 006 | 18/09/2019 | 03/06/2020 | 18/09/2019 | 18/09/2019 | 0 | TK_Complete | 94810358 | 11 | 94810358_11
A184250 | TT_Task | SteCo 007 | 17/12/2019 | 01/09/2020 | 16/12/2019 | 16/12/2019 | 0 | TK_Complete | 94810358 | 11 | 94810358_11
A184850 | TT_Task | SteCo 008 | 01/09/2020 | 18/05/2021 | 18/03/2020 | 18/03/2020 | 0 | TK_Complete | 94810358 | 11 | 94810358_11
A184860 | TT_Task | SteCo 009 | 01/09/2020 | 18/05/2021 | 17/06/2020 | 17/06/2020 | 0 | TK_Complete | 94810358 | 11 | 94810358_11
A184870 | TT_Task | SteCo 010 | 01/10/2020 | 17/06/2021 | 15/09/2020 | 15/09/2020 | 0 | TK_Complete | 94810358 | 10 | 94810358_10
A184880 | TT_Task | SteCo 011 | 03/12/2020 | 19/08/2021 | 16/11/2020 | 16/11/2020 | 0 | TK_Complete | 94810358 | 10 | 94810358_10
A188310 | TT_Task | SteCo 012 | 03/12/2020 | 19/08/2021 | 10/12/2020 | 10/12/2020 | 0 | TK_Complete | 94810358 | 10 | 94810358_10
A188320 | TT_Task | SteCo 013 | 03/12/2020 | 19/08/2021 | 02/06/2021 | 02/06/2021 | 0 | TK_Complete | 94810358 | 10 | 94810358_10
A188330 | TT_Task | SteCo 014 | 24/09/2021 | 10/06/2022 | 14/09/2021 | 14/09/2021 | 0 | TK_Complete | 94810358 | 10 | 94810358_10
A188340 | TT_Task | SteCo 015 | 26/11/2021 | 12/08/2022 | 10/11/2021 | 10/11/2021 | 0 | TK_Complete | 94810358 | 10 | 94810358_10
A190270 | TT_Task | SteCo 016 | 21/12/2021 | 06/09/2022 | nan | nan | 16904 | TK_NotStart | 94810358 | 10 | 94810358_10
A167040 | TT_Task | Ditlott | 25/06/2018 | 11/03/2019 | 25/06/2018 | 26/06/2018 | 0 | TK_Complete | 94810358 | 12 | 94810358_12
A167050 | TT_Task | Requirements Management | 27/06/2018 | 13/03/2019 | 27/06/2018 | 29/06/2018 | 0 | TK_Complete | 94810358 | 13 | 94810358_13
A167060 | TT_Task | Ditlott | 02/07/2018 | 18/03/2019 | 02/07/2018 | 06/07/2018 | 0 | TK_Complete | 94810358 | 12 | 94810358_12
A167070 | TT_Task | Evaluation of Pilot CCDRs | 06/07/2018 | 22/03/2019 | 06/07/2018 | 06/07/2018 | 0 | TK_Complete | 94810358 | 14 | 94810358_14
A167170 | TT_Task | Project Kick-off | 14/05/2018 | 16/05/2018 | 14/05/2018 | 16/05/2018 | 0 | TK_Complete | 94810358 | 15 | 94810358_15
A167180 | TT_Task | Industrial Desing Focus Group | 03/07/2018 | 04/07/2018 | 03/07/2018 | 04/07/2018 | 0 | TK_Complete | 94810358 | 16 | 94810358_16
A167420 | TT_Task | VT visit to BST Site | 22/08/2018 | 22/08/2018 | 22/08/2018 | 22/08/2018 | 0 | TK_Complete | 94810358 | 17 | 94810358_17
A167810 | TT_Task | CCB Kickoff | 29/08/2018 | 29/08/2018 | 29/08/2018 | 29/08/2018 | 0 | TK_Complete | 94810358 | 18 | 94810358_18
A167820 | TT_Task | Customer Non-Product Related Requirements Review | 05/09/2018 | 06/09/2018 | 05/09/2018 | 06/09/2018 | 0 | TK_Complete | 94810358 | 19 | 94810358_19
A171230 | TT_Task | Kick-off Meeting - Carbody (4S 01) | 31/01/2019 | 17/10/2019 | 31/01/2019 | 31/01/2019 | 0 | TK_Complete | 94810358 | 20 | 94810358_20
A171240 | TT_Task | PDR Closing Meeting - Carbody (4S 01) | 14/03/2019 | 28/11/2019 | 14/03/2019 | 14/03/2019 | 0 | TK_Complete | 94810358 | 21 | 94810358_21
A171250 | TT_Task | Kick-off Meeting - Train Control (4S 15) | 25/01/2019 | 11/10/2019 | 25/01/2019 | 25/01/2019 | 0 | TK_Complete | 94810358 | 22 | 94810358_22
A171260 | TT_Task | PDR Closing Meeting - Train Control (4S 15) | 20/03/2019 | 04/12/2019 | 20/03/2019 | 20/03/2019 | 0 | TK_Complete | 94810358 | 23 | 94810358_23
A183840 | TT_Task | PDR Closing Meeting - Train Control (4S 15) | 20/03/2019 | 04/12/2019 | 14/05/2019 | 14/05/2019 | 0 | TK_Complete | 94810358 | 23 | 94810358_23
A183810 | TT_Task | Kick-off Meeting - Train Control (4S 17) | 25/01/2019 | 11/10/2019 | 21/02/2019 | 21/02/2019 | 0 | TK_Complete | 94810358 | 22 | 94810358_22
A183820 | TT_Task | Kick-off Meeting - Train Control (4S 17) | 25/01/2019 | 11/10/2019 | 07/03/2019 | 07/03/2019 | 0 | TK_Complete | 94810358 | 22 | 94810358_22
A183850 | TT_Task | PDR Closing Meeting - Train Control (4S 17) | 20/03/2019 | 04/12/2019 | 11/04/2019 | 11/04/2019 | 0 | TK_Complete | 94810358 | 23 | 94810358_23
A183860 | TT_Task | PDR Closing Meeting - Train Control (4S 17) | 20/03/2019 | 04/12/2019 | 16/05/2019 | 16/05/2019 | 0 | TK_Complete | 94810358 | 23 | 94810358_23
A183830 | TT_Task | Kick-off Meeting - Train Control (4S 13, 4S 14) | 25/01/2019 | 11/10/2019 | 22/02/2019 | 22/02/2019 | 0 | TK_Complete | 94810358 | 22 | 94810358_22
A183870 | TT_Task | PDR Closing Meeting - Train Control (4S 13) | 20/03/2019 | 04/12/2019 | 27/03/2019 | 27/03/2019 | 0 | TK_Complete | 94810358 | 23 | 94810358_23
A183880 | TT_Task | PDR Closing Meeting - Train Control (4S 14.01) | 20/03/2019 | 04/12/2019 | 28/03/2019 | 28/03/2019 | 0 | TK_Complete | 94810358 | 23 | 94810358_23
A183890 | TT_Task | PDR Closing Meeting - Train Control (4S 14.02) | 20/03/2019 | 04/12/2019 | 29/03/2019 | 29/03/2019 | 0 | TK_Complete | 94810358 | 23 | 94810358_23
A171310 | TT_Task | Kick-off Meeting - Bogies (4S 04) | 31/01/2019 | 17/10/2019 | 31/01/2019 | 31/01/2019 | 0 | TK_Complete | 94810358 | 24 | 94810358_24
A171320 | TT_Task | PDR Closing Meeting - Bogies Winterization Workshop (4S 04) | 08/05/2019 | 22/01/2020 | 27/02/2019 | 27/02/2019 | 0 | TK_Complete | 94810358 | 25 | 94810358_25
A183900 | TT_Task | PDR Closing Meeting - Bogies (4S 04) | 08/05/2019 | 22/01/2020 | 19/03/2019 | 19/03/2019 | 0 | TK_Complete | 94810358 | 26 | 94810358_26
A183910 | TT_Task | PDR Closing Meeting - Bogies (4S 04) | 08/05/2019 | 22/01/2020 | 08/05/2019 | 08/05/2019 | 0 | TK_Complete | 94810358 | 26 | 94810358_26
A171330 | TT_Task | Kick-off Meeting - Propulsion (4S 09, 4S 10) | 20/02/2019 | 06/11/2019 | 20/02/2019 | 20/02/2019 | 0 | TK_Complete | 94810358 | 27 | 94810358_27
A171340 | TT_Task | PDR Closing Meeting - Propulsion (4S 09, 4S 10) | 13/05/2019 | 27/01/2020 | 09/05/2019 | 09/05/2019 | 0 | TK_Complete | 94810358 | 28 | 94810358_28
A183920 | TT_Task | PDR Closing Meeting - Propulsion (4S 09, 4S 10) | 13/05/2019 | 27/01/2020 | 10/05/2019 | 10/05/2019 | 0 | TK_Complete | 94810358 | 28 | 94810358_28
A183930 | TT_Task | PDR Closing Meeting - Propulsion (4S 09, 4S 10) | 13/05/2019 | 27/01/2020 | 13/05/2019 | 13/05/2019 | 0 | TK_Complete | 94810358 | 28 | 94810358_28
A183940 | TT_Task | PDR Closing Meeting - Propulsion (4S 09, 4S 10) | 13/05/2019 | 27/01/2020 | 14/05/2019 | 14/05/2019 | 0 | TK_Complete | 94810358 | 28 | 94810358_28
A183950 | TT_Task | PDR Closing Meeting - Propulsion (4S 09, 4S 10) | 13/05/2019 | 27/01/2020 | 21/05/2019 | 21/05/2019 | 0 | TK_Complete | 94810358 | 28 | 94810358_28
A171350 | TT_Task | Kick-off Meeting - Signalling (4S 16) | 13/02/2019 | 30/10/2019 | 13/02/2019 | 13/02/2019 | 0 | TK_Complete | 94810358 | 29 | 94810358_29
A171360 | TT_Task | PDR Closing Meeting - Signalling (4S 16) | 22/03/2019 | 06/12/2019 | 22/03/2019 | 22/03/2019 | 0 | TK_Complete | 94810358 | 30 | 94810358_30
A171370 | TT_Task | Kick-off Meeting - Interiors ; Exteriors (4S 11, 4S 12, 4S 21) | 30/01/2019 | 16/10/2019 | 30/01/2019 | 30/01/2019 | 0 | TK_Complete | 94810358 | 31 | 94810358_31
A171380 | TT_Task | PDR Closing Meeting - Interiors ; Exteriors (4S 12) | 15/05/2019 | 29/01/2020 | 02/04/2019 | 02/04/2019 | 0 | TK_Complete | 94810358 | 32 | 94810358_32
A183960 | TT_Task | Kick-off Meeting - Interiors ; Exteriors (4S 11, 4S 12, 4S 21) | 30/01/2019 | 16/10/2019 | 21/02/2019 | 21/02/2019 | 0 | TK_Complete | 94810358 | 31 | 94810358_31
A183970 | TT_Task | PDR Closing Meeting - Interiors ; Exteriors (4S 21) | 15/05/2019 | 29/01/2020 | 03/04/2019 | 03/04/2019 | 0 | TK_Complete | 94810358 | 32 | 94810358_32
A183980 | TT_Task | PDR Closing Meeting - Interiors ; Exteriors (4S 11) | 15/05/2019 | 29/01/2020 | 03/04/2019 | 03/04/2019 | 0 | TK_Complete | 94810358 | 32 | 94810358_32
A183990 | TT_Task | PDR Closing Meeting - Interiors ; Exteriors (4S 11) | 15/05/2019 | 29/01/2020 | 15/05/2019 | 15/05/2019 | 0 | TK_Complete | 94810358 | 32 | 94810358_32
A184000 | TT_Task | PDR Closing Meeting - Interiors ; Exteriors (4S 11) | 15/05/2019 | 29/01/2020 | 21/05/2019 | 21/05/2019 | 0 | TK_Complete | 94810358 | 32 | 94810358_32
A171390 | TT_Task | Kick-off Meeting - Interiors ; Exteriors (4S 02, 4S 03, 4S 07, 4S 08) | 14/02/2019 | 31/10/2019 | 14/02/2019 | 14/02/2019 | 0 | TK_Complete | 94810358 | 31 | 94810358_31
A171400 | TT_Task | PDR Closing Meeting - Interiors ; Exteriors (4S 03) | 26/03/2019 | 10/12/2019 | 26/03/2019 | 26/03/2019 | 0 | TK_Complete | 94810358 | 32 | 94810358_32
A184010 | TT_Task | Kick-off Meeting - Interiors ; Exteriors (4S 08) | 14/02/2019 | 31/10/2019 | 01/03/2019 | 01/03/2019 | 0 | TK_Complete | 94810358 | 31 | 94810358_31
A184020 | TT_Task | PDR Closing Meeting - Interiors ; Exteriors (4S 08) | 26/03/2019 | 10/12/2019 | 27/03/2019 | 27/03/2019 | 0 | TK_Complete | 94810358 | 32 | 94810358_32
A184030 | TT_Task | PDR Closing Meeting - Interiors ; Exteriors (4S 08) | 26/03/2019 | 10/12/2019 | 24/04/2019 | 24/04/2019 | 0 | TK_Complete | 94810358 | 32 | 94810358_32
A184040 | TT_Task | PDR Closing Meeting - Interiors ; Exteriors (4S 07) | 26/03/2019 | 10/12/2019 | 17/04/2019 | 17/04/2019 | 0 | TK_Complete | 94810358 | 32 | 94810358_32
A184050 | TT_Task | PDR Closing Meeting - Interiors ; Exteriors (4S 07) | 26/03/2019 | 10/12/2019 | 24/04/2019 | 24/04/2019 | 0 | TK_Complete | 94810358 | 32 | 94810358_32
A184060 | TT_Task | PDR Closing Meeting - Interiors ; Exteriors (4S 02) | 26/03/2019 | 10/12/2019 | 29/03/2019 | 29/03/2019 | 0 | TK_Complete | 94810358 | 32 | 94810358_32
A171410 | TT_Task | Kick-off Meeting - Interiors ; Exteriors (4S 05, 4S 06, 4S 22) | 21/02/2019 | 07/11/2019 | 21/02/2019 | 21/02/2019 | 0 | TK_Complete | 94810358 | 31 | 94810358_31
A171420 | TT_Task | PDR Closing Meeting - Interiors ; Exteriors (4S 05) | 13/05/2019 | 27/01/2020 | 26/03/2019 | 26/03/2019 | 0 | TK_Complete | 94810358 | 32 | 94810358_32
A184070 | TT_Task | PDR Closing Meeting - Interiors ; Exteriors (4S 05) | 13/05/2019 | 27/01/2020 | 25/04/2019 | 25/04/2019 | 0 | TK_Complete | 94810358 | 32 | 94810358_32
A184080 | TT_Task | PDR Closing Meeting - Interiors ; Exteriors (4S 05) | 13/05/2019 | 27/01/2020 | 13/05/2019 | 13/05/2019 | 0 | TK_Complete | 94810358 | 32 | 94810358_32
A184090 | TT_Task | PDR Closing Meeting - Interiors ; Exteriors (4S 06, 4S 22) | 13/05/2019 | 27/01/2020 | 26/03/2019 | 26/03/2019 | 0 | TK_Complete | 94810358 | 32 | 94810358_32
A184100 | TT_Task | PDR Closing Meeting - Interiors ; Exteriors (4S 06, 4S 22) | 13/05/2019 | 27/01/2020 | 25/04/2019 | 25/04/2019 | 0 | TK_Complete | 94810358 | 32 | 94810358_32
A171430 | TT_Task | Kick-off Meeting - Vehicle Integration ; Performance (05.01) | 21/02/2019 | 07/11/2019 | 21/02/2019 | 21/02/2019 | 0 | TK_Complete | 94810358 | 33 | 94810358_33
A171440 | TT_Task | PDR Closing Meeting - Vehicle Integration ; Performance (05.01) | 13/05/2019 | 27/01/2020 | 23/04/2019 | 23/04/2019 | 0 | TK_Complete | 94810358 | 34 | 94810358_34
A184110 | TT_Task | PDR Closing Meeting - Vehicle Integration ; Performance (05.01) | 13/05/2019 | 27/01/2020 | 16/05/2019 | 16/05/2019 | 0 | TK_Complete | 94810358 | 34 | 94810358_34
A171450 | TT_Task | Kick-off Meeting - Vehicle Integration ; Performance (1P, 2F) | 26/02/2019 | 12/11/2019 | 26/02/2019 | 26/02/2019 | 0 | TK_Complete | 94810358 | 33 | 94810358_33
A171460 | TT_Task | PDR Closing Meeting - Vehicle Integration ; Performance (2F) | 14/05/2019 | 28/01/2020 | 27/03/2019 | 27/03/2019 | 0 | TK_Complete | 94810358 | 34 | 94810358_34
A184120 | TT_Task | PDR Closing Meeting - Vehicle Integration ; Performance (1P 02.01.02) | 14/05/2019 | 28/01/2020 | 28/03/2019 | 28/03/2019 | 0 | TK_Complete | 94810358 | 34 | 94810358_34
A184130 | TT_Task | PDR Closing Meeting - Vehicle Integration ; Performance (1P 02.01.02) | 14/05/2019 | 28/01/2020 | 14/05/2019 | 14/05/2019 | 0 | TK_Complete | 94810358 | 34 | 94810358_34
A184140 | TT_Task | PDR Closing Meeting - Vehicle Integration ; Performance (1P 07) | 14/05/2019 | 28/01/2020 | 28/03/2019 | 28/03/2019 | 0 | TK_Complete | 94810358 | 34 | 94810358_34
A184150 | TT_Task | PDR Closing Meeting - Vehicle Integration ; Performance (1P 07) | 14/05/2019 | 28/01/2020 | 08/05/2019 | 08/05/2019 | 0 | TK_Complete | 94810358 | 34 | 94810358_34
A184160 | TT_Task | PDR Closing Meeting - Vehicle Integration ; Performance (1P 06.04) | 14/05/2019 | 28/01/2020 | 28/03/2019 | 28/03/2019 | 0 | TK_Complete | 94810358 | 34 | 94810358_34
A184170 | TT_Task | PDR Closing Meeting - Vehicle Integration ; Performance (1P 01) | 14/05/2019 | 28/01/2020 | 29/03/2019 | 29/03/2019 | 0 | TK_Complete | 94810358 | 34 | 94810358_34
A171470 | TT_Task | Kick-off Meeting - Electrical (4S 18) | 20/02/2019 | 06/11/2019 | 20/02/2019 | 20/02/2019 | 0 | TK_Complete | 94810358 | 35 | 94810358_35
A171480 | TT_Task | PDR Closing Meeting - Electrical (4S 18) | 25/03/2019 | 09/12/2019 | 25/03/2019 | 25/03/2019 | 0 | TK_Complete | 94810358 | 30 | 94810358_30
A171510 | TT_Task | Kick-off Meeting - Last Mile / Train Zero (5X 06) | 28/02/2019 | 14/11/2019 | 28/02/2019 | 28/02/2019 | 0 | TK_Complete | 94810358 | 36 | 94810358_36
A171520 | TT_Task | PDR Closing Meeting - Last Mile / Train Zero (5X 06) | 01/04/2019 | 16/12/2019 | 28/03/2019 | 28/03/2019 | 0 | TK_Complete | 94810358 | 37 | 94810358_37
A168260 | TT_Task | Requirements Management - Prepare Internal CDR | 04/04/2018 | 10/10/2018 | 04/04/2018 | 11/02/2019 | 0 | TK_Complete | 94810358 | 38 | 94810358_38
A168280 | TT_Task | Requirements Management - Prepare Internal PDR | 12/02/2019 | 12/02/2019 | 12/02/2019 | 31/07/2019 | 0 | TK_Complete | 94810358 | 39 | 94810358_39
A168300 | TT_Task | Requirements Management - Prepare Internal DDR | 01/08/2019 | 01/08/2019 | 01/08/2019 | 12/11/2019 | 0 | TK_Complete | 94810358 | 39 | 94810358_39
A184180 | TT_Task | Electromagnetic Compatibility and Earthing - Prepare Internal PDR | 12/02/2019 | 12/02/2019 | 21/02/2019 | 13/09/2019 | 0 | TK_Complete | 94810358 | 40 | 94810358_40
A184500 | TT_Task | Electromagnetic Compatibility and Earthing - Prepare Internal DDR | 10/09/2019 | 10/09/2019 | 16/09/2019 | 07/10/2020 | 0 | TK_Complete | 94810358 | 40 | 94810358_40
A160150 | TT_Task | Acoustics and Vibration - Prepare Internal CDR | 04/04/2018 | 10/10/2018 | 04/04/2018 | 28/11/2018 | 0 | TK_Complete | 94810358 | 41 | 94810358_41
A160310 | TT_Task | Aerodynamics - Prepare Internal CDR | 04/04/2018 | 10/10/2018 | 04/04/2018 | 26/11/2018 | 0 | TK_Complete | 94810358 | 42 | 94810358_42
A160630 | TT_Task | Industrial Design - Prepare Internal CDR | 04/04/2018 | 11/10/2018 | 04/04/2018 | 04/12/2018 | 0 | TK_Complete | 94810358 | 43 | 94810358_43
A168500 | TT_Task | Passenger flow - Prepare Internal CDR | 04/04/2018 | 11/10/2018 | 04/04/2018 | 10/10/2018 | 0 | TK_Complete | 94810358 | 44 | 94810358_44
A168070 | TT_Task | Ergonomics - Prepare Customer CDR | 04/04/2018 | 04/04/2018 | 04/04/2018 | 24/10/2018 | 0 | TK_Complete | 94810358 | 45 | 94810358_45
A184720 | TT_Task | Ergonomics - Prepare Customer DDR | 04/04/2018 | 04/04/2018 | 22/05/2019 | 19/11/2019 | 0 | TK_Complete | 94810358 | 45 | 94810358_45
A160950 | TT_Task | Product Safety - Prepare Internal CDR | 04/04/2018 | 18/09/2018 | 04/04/2018 | 14/02/2019 | 0 | TK_Complete | 94810358 | 43 | 94810358_43
A160980 | TT_Task | Product Safety - Prepare Internal PDR | 22/02/2019 | 22/02/2019 | 15/02/2019 | 09/09/2019 | 0 | TK_Complete | 94810358 | 46 | 94810358_46
A161040 | TT_Task | Product Safety - Prepare Internal DDR | 10/09/2019 | 10/09/2019 | 10/09/2019 | 08/04/2021 | 0 | TK_Complete | 94810358 | 46 | 94810358_46
A168560 | TT_Task | Fire Safety, Evacuation - Prepare Internal CDR | 04/04/2018 | 18/09/2018 | 04/04/2018 | 30/11/2018 | 0 | TK_Complete | 94810358 | 47 | 94810358_47
A168580 | TT_Task | Fire Safety, Evacuation - Prepare Internal PDR | 03/12/2018 | 03/12/2018 | 03/12/2018 | 09/09/2019 | 0 | TK_Complete | 94810358 | 47 | 94810358_47
A168600 | TT_Task | Fire Safety, Evacuation - Prepare Internal DDR | 10/09/2019 | 10/09/2019 | 10/09/2019 | 20/01/2021 | 0 | TK_Complete | 94810358 | 47 | 94810358_47
A168620 | TT_Task | Cybersecurity - Prepare Internal CDR | 04/04/2018 | 18/09/2018 | 04/04/2018 | 15/02/2019 | 0 | TK_Complete | 94810358 | 48 | 94810358_48
A168640 | TT_Task | Cybersecurity - Prepare Internal PDR | 18/02/2019 | 18/02/2019 | 18/02/2019 | 09/09/2019 | 0 | TK_Complete | 94810358 | 49 | 94810358_49
A168660 | TT_Task | Cybersecurity - Prepare Internal DDR | 10/09/2019 | 10/09/2019 | 10/09/2019 | 17/02/2020 | 0 | TK_Complete | 94810358 | 50 | 94810358_50
A184540 | TT_Task | Cybersecurity - Prepare Customer DDR | 04/04/2018 | 04/04/2018 | 22/05/2019 | 21/11/2019 | 0 | TK_Complete | 94810358 | 50 | 94810358_50
A161440 | TT_Task | RAM, Diagnostic, LCC - Prepare Customer CDR | 04/04/2018 | 04/04/2018 | 04/04/2018 | 18/09/2018 | 0 | TK_Complete | 94810358 | 51 | 94810358_51
A184700 | TT_Task | RAM/LCC - Prepare Customer DDR | 04/04/2018 | 04/04/2018 | 22/05/2019 | 19/11/2019 | 0 | TK_Complete | 94810358 | 52 | 94810358_52
A161430 | TT_Task | Reliability - Prepare Internal CDR | 04/04/2018 | 15/10/2018 | 04/04/2018 | 07/12/2018 | 0 | TK_Complete | 94810358 | 53 | 94810358_53
A161460 | TT_Task | Reliability - Prepare Internal PDR | 10/12/2018 | 10/12/2018 | 10/12/2018 | 05/11/2019 | 0 | TK_Complete | 94810358 | 54 | 94810358_54
A161520 | TT_Task | Reliability - Prepare Internal DDR | 05/11/2019 | 05/11/2019 | 05/11/2019 | 30/10/2020 | 0 | TK_Complete | 94810358 | 55 | 94810358_55
A168680 | TT_Task | Availability - Prepare Internal CDR | 04/04/2018 | 15/10/2018 | 04/04/2018 | 07/12/2018 | 0 | TK_Complete | 94810358 | 53 | 94810358_53
A168700 | TT_Task | Availability - Prepare Internal PDR | 10/12/2018 | 10/12/2018 | 10/12/2018 | 15/10/2019 | 0 | TK_Complete | 94810358 | 54 | 94810358_54
A168720 | TT_Task | Availability - Prepare Internal DDR | 15/10/2019 | 15/10/2019 | 15/10/2019 | 30/10/2020 | 0 | TK_Complete | 94810358 | 55 | 94810358_55
A168740 | TT_Task | Maintainability - Prepare Internal CDR | 04/04/2018 | 15/10/2018 | 04/04/2018 | 07/12/2018 | 0 | TK_Complete | 94810358 | 53 | 94810358_53
A168760 | TT_Task | Maintainability - Prepare Internal PDR | 10/12/2018 | 10/12/2018 | 10/12/2018 | 15/10/2019 | 0 | TK_Complete | 94810358 | 54 | 94810358_54
A168780 | TT_Task | Maintainability - Prepare Internal DDR | 15/10/2019 | 15/10/2019 | 15/10/2019 | 30/10/2020 | 0 | TK_Complete | 94810358 | 55 | 94810358_55
A168800 | TT_Task | Diagnostic - Prepare Internal CDR | 04/04/2018 | 15/10/2018 | 04/04/2018 | 07/12/2018 | 0 | TK_Complete | 94810358 | 43 | 94810358_43
A168820 | TT_Task | Diagnostic - Prepare Internal PDR | 10/12/2018 | 10/12/2018 | 10/12/2018 | 15/10/2019 | 0 | TK_Complete | 94810358 | 56 | 94810358_56
A168840 | TT_Task | Diagnostic - Prepare Internal DDR | 15/10/2019 | 15/10/2019 | 15/10/2019 | 10/03/2020 | 0 | TK_Complete | 94810358 | 57 | 94810358_57
A168860 | TT_Task | LCC - Prepare Internal CDR | 04/04/2018 | 15/10/2018 | 04/04/2018 | 07/12/2018 | 0 | TK_Complete | 94810358 | 58 | 94810358_58
A168880 | TT_Task | LCC - Prepare Internal PDR | 10/12/2018 | 10/12/2018 | 10/12/2018 | 15/10/2019 | 0 | TK_Complete | 94810358 | 59 | 94810358_59
A168900 | TT_Task | LCC - Prepare Internal DDR | 15/10/2019 | 15/10/2019 | 15/10/2019 | 30/10/2020 | 0 | TK_Complete | 94810358 | 59 | 94810358_59
A161590 | TT_Task | Structural Mechanics and Crash Safety - Prepare Internal CDR | 04/04/2018 | 17/09/2018 | 04/04/2018 | 21/11/2018 | 0 | TK_Complete | 94810358 | 60 | 94810358_60
A161600 | TT_Task | Structural Mechanics and Crash Safety - Prepare Customer CDR | 04/04/2018 | 04/04/2018 | 04/04/2018 | 05/07/2018 | 0 | TK_Complete | 94810358 | 60 | 94810358_60
A161910 | TT_Task | Journey Time and Energy Performance - Prepare Internal CDR | 04/04/2018 | 04/10/2018 | 04/04/2018 | 15/02/2019 | 0 | TK_Complete | 94810358 | 61 | 94810358_61
A162230 | TT_Task | Weight Performance - Prepare Internal CDR | 04/04/2018 | 01/10/2018 | 04/04/2018 | 15/02/2019 | 0 | TK_Complete | 94810358 | 62 | 94810358_62
A162390 | TT_Task | Vehicle Functions - Prepare Internal CDR | 04/04/2018 | 02/10/2018 | 04/04/2018 | 12/02/2019 | 0 | TK_Complete | 94810358 | 44 | 94810358_44
A82680 | TT_Task | FVRS - Power Supply Functions | 01/11/2017 | 28/02/2018 | 01/11/2017 | 01/02/2018 | 0 | TK_Complete | 94810358 | 63 | 94810358_63
A82690 | TT_Task | FVDS - Power Supply Functions | 02/02/2018 | 01/06/2018 | 02/02/2018 | 06/07/2018 | 0 | TK_Complete | 94810358 | 63 | 94810358_63
A82700 | TT_Task | FVRS - Drive Brake and Bogie Control Functions | 01/11/2017 | 28/02/2018 | 01/11/2017 | 01/02/2018 | 0 | TK_Complete | 94810358 | 64 | 94810358_64
A82710 | TT_Task | FVDS - Drive Brake and Bogie Control Functions | 02/02/2018 | 01/06/2018 | 02/02/2018 | 13/07/2018 | 0 | TK_Complete | 94810358 | 64 | 94810358_64
A82720 | TT_Task | FVRS - Door Control Functions | 01/11/2017 | 28/02/2018 | 01/11/2017 | 01/02/2018 | 0 | TK_Complete | 94810358 | 65 | 94810358_65
A82730 | TT_Task | FVDS - Door Control Functions | 02/02/2018 | 01/06/2018 | 02/02/2018 | 22/06/2018 | 0 | TK_Complete | 94810358 | 65 | 94810358_65
A82740 | TT_Task | FVRS - Passenger and Crew Comfort Function | 01/11/2017 | 28/02/2018 | 01/11/2017 | 01/02/2018 | 0 | TK_Complete | 94810358 | 66 | 94810358_66
A82750 | TT_Task | FVDS - Passenger and Crew Comfort Function | 02/02/2018 | 01/06/2018 | 02/02/2018 | 31/07/2018 | 0 | TK_Complete | 94810358 | 66 | 94810358_66
A82760 | TT_Task | FVRS - Passenger Information and Entertainment System Functions | 01/11/2017 | 28/02/2018 | 01/11/2017 | 01/02/2018 | 0 | TK_Complete | 94810358 | 67 | 94810358_67
A82770 | TT_Task | FVDS - Passenger Information and Entertainment System Functions | 02/02/2018 | 01/06/2018 | 02/02/2018 | 11/07/2018 | 0 | TK_Complete | 94810358 | 67 | 94810358_67
A82780 | TT_Task | FVRS - Train Control, Presence and Coupling Functions | 01/11/2017 | 28/02/2018 | 01/11/2017 | 01/02/2018 | 0 | TK_Complete | 94810358 | 68 | 94810358_68
A82790 | TT_Task | FVDS - Train Control, Presence and Coupling Functions | 02/02/2018 | 01/06/2018 | 02/02/2018 | 06/07/2018 | 0 | TK_Complete | 94810358 | 68 | 94810358_68
A82800 | TT_Task | FVRS - Train Protection, Automatic Train Operation and Operational Ground Communication Functions | 01/11/2017 | 28/02/2018 | 01/11/2017 | 16/02/2018 | 0 | TK_Complete | 94810358 | 69 | 94810358_69
A82810 | TT_Task | FVDS - Train Protection, Automatic Train Operation and Operational Ground Communication Functions | 19/02/2018 | 18/06/2018 | 19/02/2018 | 06/07/2018 | 0 | TK_Complete | 94810358 | 69 | 94810358_69
A82820 | TT_Task | FVRS - Diagnostics, Visualisation and Assitance Functions | 01/11/2017 | 28/02/2018 | 01/11/2017 | 01/02/2018 | 0 | TK_Complete | 94810358 | 70 | 94810358_70
A82830 | TT_Task | FVDS - Diagnostics, Visualisation and Assitance Functions | 02/02/2018 | 01/06/2018 | 02/02/2018 | 29/06/2018 | 0 | TK_Complete | 94810358 | 70 | 94810358_70
A162870 | TT_Task | Carbody - Prepare Internal CDR | 04/04/2018 | 18/09/2018 | 04/04/2018 | 13/02/2019 | 0 | TK_Complete | 94810358 | 71 | 94810358_71
A162880 | TT_Task | Carbody - Prepare Customer CDR | 04/04/2018 | 04/04/2018 | 04/04/2018 | 05/07/2018 | 0 | TK_Complete | 94810358 | 71 | 94810358_71
A168130 | TT_Task | Grafiti Protection/Painting System - Prepare Customer CDR | 04/04/2018 | 04/04/2018 | 04/04/2018 | 11/10/2018 | 0 | TK_Complete | 94810358 | 72 | 94810358_72
A169650 | TT_Task | Release of Production Drawings for Carbody Manufacturing (DM Car) | 15/01/2019 | 29/10/2019 | 15/01/2019 | 26/04/2019 | 0 | TK_Complete | 94810358 | 73 | 94810358_73
A169660 | TT_Task | Release of Production Drawings for Carbody Manufacturing (T Car) | 18/02/2019 | 17/12/2019 | 18/02/2019 | 21/06/2019 | 0 | TK_Complete | 94810358 | 73 | 94810358_73
A79040 | TT_Task | Release of Production Drawings for Carbody Mock-up | 01/11/2017 | 29/05/2018 | 01/11/2017 | 02/07/2018 | 0 | TK_Complete | 94810358 | 74 | 94810358_74
A79050 | TT_Task | Release of 18 Profile Drawing for Carbody Mock-up | 01/11/2017 | 20/03/2018 | 01/11/2017 | 15/05/2018 | 0 | TK_Complete | 94810358 | 75 | 94810358_75
A79070 | TT_Task | Release of Profile Drawings for Carbody Manufacturing (DM Car) | 01/11/2017 | 15/08/2018 | 01/11/2017 | 15/08/2018 | 0 | TK_Complete | 94810358 | 73 | 94810358_73
A88700 | TT_Task | Release of Profile Drawings for Carbody Manufacturing (T Car) | 01/11/2017 | 30/08/2018 | 01/11/2017 | 30/10/2018 | 0 | TK_Complete | 94810358 | 73 | 94810358_73
A79010 | TT_Task | Procurement of Alu Extrusions for Carbody Mock-up | 16/05/2018 | 05/10/2018 | 16/05/2018 | 12/10/2018 | 0 | TK_Complete | 94810358 | 76 | 94810358_76
A79060 | TT_Task | Procurement of Alu Extrusions for Carbody Manufacturing (DM Car) | 16/08/2018 | 15/01/2019 | 16/08/2018 | 03/04/2019 | 0 | TK_Complete | 94810358 | 76 | 94810358_76
A88690 | TT_Task | Procurement of Alu Extrusions for Carbody Manufacturing (T Car) | 31/08/2018 | 30/01/2019 | 31/10/2018 | 10/04/2019 | 0 | TK_Complete | 94810358 | 76 | 94810358_76
A83790 | TT_Task | Crash Energy Absorption - Lead Time 1st Product | 29/10/2019 | 13/04/2020 | 09/09/2019 | 01/09/2020 | 0 | TK_Complete | 94810358 | 77 | 94810358_77
A83860 | TT_Task | Crash Energy Absorption - SRD for Contract Negotiations | 04/04/2018 | 07/09/2018 | 04/04/2018 | 11/10/2018 | 0 | TK_Complete | 94810358 | 78 | 94810358_78
A83870 | TT_Task | Crash Energy Absorption - Supplier Contract | 19/11/2018 | 24/01/2019 | 12/10/2018 | 06/09/2019 | 0 | TK_Complete | 94810358 | 79 | 94810358_79
A83910 | TT_Task | Carbody Exterior Equipment - Collect Electrical BBIs | 10/09/2018 | 09/01/2019 | 04/04/2018 | 09/11/2018 | 0 | TK_Complete | 94810358 | 80 | 94810358_80
A163040 | TT_Task | Carbody Exterior Cab GRP/FRP Nose - Prepare Customer CDR | 04/04/2018 | 04/04/2018 | 04/04/2018 | 19/09/2018 | 0 | TK_Complete | 94810358 | 81 | 94810358_81
A83920 | TT_Task | Aerodynamic System - Lead Time 1st Product | 02/09/2019 | 13/03/2020 | 02/09/2019 | 24/06/2020 | 0 | TK_Complete | 94810358 | 82 | 94810358_82
A83990 | TT_Task | Aerodynamic System - SRD for Contract Negotiations | 04/04/2018 | 07/09/2018 | 04/04/2018 | 19/10/2018 | 0 | TK_Complete | 94810358 | 83 | 94810358_83
A84000 | TT_Task | Aerodynamic System - Supplier Contract | 19/11/2018 | 24/01/2019 | 22/10/2018 | 30/08/2019 | 0 | TK_Complete | 94810358 | 84 | 94810358_84
A163200 | TT_Task | Windows/Windscreens - Prepare Customer CDR | 04/04/2018 | 04/04/2018 | 04/04/2018 | 11/09/2018 | 0 | TK_Complete | 94810358 | 85 | 94810358_85
A84050 | TT_Task | Windows - Lead Time 1st Product | 01/08/2019 | 11/03/2020 | 31/07/2019 | 27/02/2020 | 0 | TK_Complete | 94810358 | 86 | 94810358_86
A84120 | TT_Task | Windows - SRD for Contract Negotiations | 04/04/2018 | 07/09/2018 | 04/04/2018 | 12/10/2018 | 0 | TK_Complete | 94810358 | 87 | 94810358_87
A84130 | TT_Task | Windows - Supplier Contract | 19/11/2018 | 24/01/2019 | 15/10/2018 | 30/07/2019 | 0 | TK_Complete | 94810358 | 88 | 94810358_88
A84180 | TT_Task | Windscreens - Lead Time 1st Product | 01/08/2019 | 11/03/2020 | 31/07/2019 | 27/02/2020 | 0 | TK_Complete | 94810358 | 89 | 94810358_89
A84250 | TT_Task | Windscreens - SRD for Contract Negotiations | 04/04/2018 | 07/09/2018 | 04/04/2018 | 12/10/2018 | 0 | TK_Complete | 94810358 | 90 | 94810358_90
A84260 | TT_Task | Windscreens - Supplier Contract | 15/10/2018 | 20/12/2018 | 15/10/2018 | 30/07/2019 | 0 | TK_Complete | 94810358 | 91 | 94810358_91
A163520 | TT_Task | Exterior Lighting - Prepare Customer CDR | 04/04/2018 | 04/04/2018 | 04/04/2018 | 12/09/2018 | 0 | TK_Complete | 94810358 | 92 | 94810358_92
A84310 | TT_Task | Exterior Lighting - Lead Time 1st Product | 08/10/2019 | 04/05/2020 | 08/10/2019 | 22/09/2020 | 0 | TK_Complete | 94810358 | 93 | 94810358_93
A84380 | TT_Task | Exterior Lighting - SRD for Contract Negotiations | 04/04/2018 | 07/09/2018 | 04/04/2018 | 08/10/2018 | 0 | TK_Complete | 94810358 | 94 | 94810358_94
A84390 | TT_Task | Exterior Lighting - Supplier Contract | 19/11/2018 | 24/01/2019 | 09/10/2018 | 08/10/2019 | 0 | TK_Complete | 94810358 | 95 | 94810358_95
A163680 | TT_Task | Weld on and Add on parts - Prepare Customer CDR | 04/04/2018 | 04/04/2018 | 04/04/2018 | 05/07/2018 | 0 | TK_Complete | 94810358 | 96 | 94810358_96
A163830 | TT_Task | Exterior Doors - Prepare Internal CDR | 04/04/2018 | 25/09/2018 | 04/04/2018 | 26/11/2018 | 0 | TK_Complete | 94810358 | 97 | 94810358_97
A163840 | TT_Task | Exterior Doors - Prepare Customer CDR | 04/04/2018 | 04/04/2018 | 04/04/2018 | 19/09/2018 | 0 | TK_Complete | 94810358 | 97 | 94810358_97
A163860 | TT_Task | Exterior Doors - Prepare Internal PDR | 27/11/2018 | 27/11/2018 | 27/11/2018 | 10/09/2019 | 0 | TK_Complete | 94810358 | 98 | 94810358_98
A163920 | TT_Task | Exterior Doors - Prepare Internal DDR | 11/09/2019 | 11/09/2019 | 11/09/2019 | 16/09/2020 | 0 | TK_Complete | 94810358 | 98 | 94810358_98
A84560 | TT_Task | Exterior Door - Collect Electrical BBIs | 10/09/2018 | 09/01/2019 | 04/04/2018 | 12/10/2018 | 0 | TK_Complete | 94810358 | 99 | 94810358_99
A84570 | TT_Task | Exterior Door Systems - Lead Time 1st Product | 08/02/2019 | 12/12/2019 | 11/02/2019 | 10/01/2020 | 0 | TK_Complete | 94810358 | 100 | 94810358_100
A84640 | TT_Task | Exterior Door Systems - SRD for Contract Negotiations | 04/04/2018 | 07/09/2018 | 04/04/2018 | 08/10/2018 | 0 | TK_Complete | 94810358 | 101 | 94810358_101
A84650 | TT_Task | Exterior Door Systems - Supplier Contract | 19/11/2018 | 24/01/2019 | 09/10/2018 | 30/05/2019 | 0 | TK_Complete | 94810358 | 102 | 94810358_102
A163990 | TT_Task | Bogie - Prepare Internal CDR | 04/04/2018 | 17/10/2018 | 04/04/2018 | 15/02/2019 | 0 | TK_Complete | 94810358 | 103 | 94810358_103
A164000 | TT_Task | Bogie - Prepare Customer CDR | 04/04/2018 | 04/04/2018 | 04/04/2018 | 23/10/2018 | 0 | TK_Complete | 94810358 | 103 | 94810358_103
A164020 | TT_Task | Bogie - Prepare Internal PDR | 18/02/2019 | 18/02/2019 | 18/02/2019 | 24/05/2019 | 0 | TK_Complete | 94810358 | 104 | 94810358_104
A164080 | TT_Task | Bogie - Prepare Internal DDR | 27/05/2019 | 27/05/2019 | 27/05/2019 | 27/11/2019 | 0 | TK_Complete | 94810358 | 104 | 94810358_104
A168190 | TT_Task | Bogie - Collect Electrical BBIs | 10/09/2018 | 09/01/2019 | 04/04/2018 | 19/10/2018 | 0 | TK_Complete | 94810358 | 105 | 94810358_105
A83680 | TT_Task | Bogies - Design Freeze for Production/Procurement | 04/04/2018 | 03/08/2018 | 04/04/2018 | 02/08/2018 | 0 | TK_Complete | 94810358 | 106 | 94810358_106
A83690 | TT_Task | Bogies - Lead Time 1st Product | 03/08/2018 | 15/11/2019 | 03/08/2018 | 29/10/2020 | 0 | TK_Complete | 94810358 | 107 | 94810358_107
A164160 | TT_Task | Interior Equipment - Prepare Customer CDR | 04/04/2018 | 04/04/2018 | 04/04/2018 | 14/08/2018 | 0 | TK_Complete | 94810358 | 108 | 94810358_108
A84820 | TT_Task | Interior Equipment - Collect Electrical BBIs | 10/09/2018 | 09/01/2019 | 04/04/2018 | 12/10/2018 | 0 | TK_Complete | 94810358 | 109 | 94810358_109
A84830 | TT_Task | Interior Doors - Lead Time 1st Product | 02/09/2019 | 13/03/2020 | 02/10/2019 | 13/03/2020 | 0 | TK_Complete | 94810358 | 100 | 94810358_100
A84900 | TT_Task | Interior Doors - SRD for Contract Negotiations | 04/04/2018 | 07/09/2018 | 04/04/2018 | 11/10/2018 | 0 | TK_Complete | 94810358 | 101 | 94810358_101
A84910 | TT_Task | Interior Doors - Supplier Contract | 19/11/2018 | 24/01/2019 | 12/10/2018 | 30/08/2019 | 0 | TK_Complete | 94810358 | 102 | 94810358_102
A84960 | TT_Task | Floors, Stairways and Vestibules - Lead Time 1st Product | 06/09/2019 | 19/03/2020 | 06/09/2019 | 20/01/2020 | 0 | TK_Complete | 94810358 | 110 | 94810358_110
A85030 | TT_Task | Floors, Stairways and Vestibules - SRD for Contract Negotiations | 04/04/2018 | 07/09/2018 | 04/04/2018 | 05/10/2018 | 0 | TK_Complete | 94810358 | 111 | 94810358_111
A85040 | TT_Task | Floors, Stairways and Vestibules - Supplier Contract | 19/11/2018 | 24/01/2019 | 08/10/2018 | 30/08/2019 | 0 | TK_Complete | 94810358 | 111 | 94810358_111
A85090 | TT_Task | Compartments - Lead Time 1st Product | 16/09/2019 | 28/02/2020 | 16/09/2019 | 20/01/2020 | 0 | TK_Complete | 94810358 | 112 | 94810358_112
A85160 | TT_Task | Compartments - SRD for Contract Negotiations | 04/04/2018 | 07/09/2018 | 04/04/2018 | 09/10/2018 | 0 | TK_Complete | 94810358 | 113 | 94810358_113
A85170 | TT_Task | Compartments - Supplier Contract | 19/11/2018 | 24/01/2019 | 10/10/2018 | 14/11/2019 | 0 | TK_Complete | 94810358 | 114 | 94810358_114
A85220 | TT_Task | Interior Lighting - Lead Time 1st Product | 02/09/2019 | 14/02/2020 | 02/09/2019 | 11/12/2019 | 0 | TK_Complete | 94810358 | 93 | 94810358_93
A85290 | TT_Task | Interior Lighting - SRD for Contract Negotiations | 04/04/2018 | 07/09/2018 | 04/04/2018 | 12/10/2018 | 0 | TK_Complete | 94810358 | 94 | 94810358_94
A85300 | TT_Task | Interior Lighting - Supplier Contract | 19/11/2018 | 24/01/2019 | 15/10/2018 | 30/08/2019 | 0 | TK_Complete | 94810358 | 95 | 94810358_95
A164320 | TT_Task | Drivers Cab - Prepare Customer CDR | 04/04/2018 | 04/04/2018 | 04/04/2018 | 11/10/2018 | 0 | TK_Complete | 94810358 | 115 | 94810358_115
A85350 | TT_Task | Drivers and Crew Seating - Lead Time 1st Product | 29/03/2019 | 27/02/2020 | 11/03/2019 | 16/09/2020 | 0 | TK_Complete | 94810358 | 116 | 94810358_116
A85420 | TT_Task | Drivers and Crew Seating - SRD for Contract Negotiations | 04/04/2018 | 07/09/2018 | 04/04/2018 | 09/10/2018 | 0 | TK_Complete | 94810358 | 117 | 94810358_117
A85430 | TT_Task | Drivers and Crew Seating - Supplier Contract | 19/11/2018 | 24/01/2019 | 10/10/2018 | 30/08/2019 | 0 | TK_Complete | 94810358 | 118 | 94810358_118
A168380 | TT_Task | Wash/Wipe - Prepare Customer CDR | 04/04/2018 | 04/04/2018 | 04/04/2018 | 24/10/2018 | 0 | TK_Complete | 94810358 | 119 | 94810358_119
A85610 | TT_Task | Wash/Wipe System - Lead Time 1st Product | 11/11/2019 | 14/08/2020 | 11/11/2019 | 05/10/2020 | 0 | TK_Complete | 94810358 | 120 | 94810358_120
A85680 | TT_Task | Wash/Wipe System - SRD for Contract Negotiations | 04/04/2018 | 07/09/2018 | 04/04/2018 | 02/10/2018 | 0 | TK_Complete | 94810358 | 121 | 94810358_121
A85690 | TT_Task | Wash/Wipe System - Supplier Contract | 03/10/2018 | 10/12/2018 | 03/10/2018 | 29/11/2019 | 0 | TK_Complete | 94810358 | 122 | 94810358_122
A168440 | TT_Task | Horn - Prepare Customer CDR | 04/04/2018 | 04/04/2018 | 04/04/2018 | 24/10/2018 | 0 | TK_Complete | 94810358 | 123 | 94810358_123
A85870 | TT_Task | Cab Back Wall - Lead Time 1st Product | 01/11/2019 | 16/04/2020 | 01/11/2019 | 20/01/2020 | 0 | TK_Complete | 94810358 | 124 | 94810358_124
A85940 | TT_Task | Cab Back Wall - SRD for Contract Negotiations | 04/04/2018 | 07/09/2018 | 04/04/2018 | 12/10/2018 | 0 | TK_Complete | 94810358 | 125 | 94810358_125
A85950 | TT_Task | Cab Back Wall - Supplier Contract | 19/11/2018 | 24/01/2019 | 15/10/2018 | 30/08/2019 | 0 | TK_Complete | 94810358 | 126 | 94810358_126
A164480 | TT_Task | Toilets and Sanitary System - Prepare Customer CDR | 04/04/2018 | 04/04/2018 | 04/04/2018 | 14/08/2018 | 0 | TK_Complete | 94810358 | 127 | 94810358_127
A86250 | TT_Task | Toilets and Sanitary System - Collect Electrical BBIs | 10/09/2018 | 09/01/2019 | 04/04/2018 | 12/10/2018 | 0 | TK_Complete | 94810358 | 128 | 94810358_128
A86260 | TT_Task | Toilets and Sanitary System - Lead Time 1st Product | 01/08/2019 | 15/07/2020 | 08/07/2019 | 02/06/2020 | 0 | TK_Complete | 94810358 | 129 | 94810358_129
A86330 | TT_Task | Toilets and Sanitary System - SRD for Contract Negotiations | 04/04/2018 | 07/09/2018 | 04/04/2018 | 02/10/2018 | 0 | TK_Complete | 94810358 | 130 | 94810358_130
A86340 | TT_Task | Toilets and Sanitary System - Supplier Contract | 19/11/2018 | 24/01/2019 | 03/10/2018 | 05/07/2019 | 0 | TK_Complete | 94810358 | 130 | 94810358_130
A164630 | TT_Task | HVAC - Prepare Internal CDR | 04/04/2018 | 03/10/2018 | 04/04/2018 | 27/11/2018 | 0 | TK_Complete | 94810358 | 131 | 94810358_131
A164640 | TT_Task | HVAC - Prepare Customer CDR | 04/04/2018 | 04/04/2018 | 04/04/2018 | 13/09/2018 | 0 | TK_Complete | 94810358 | 131 | 94810358_131
A164660 | TT_Task | HVAC - Prepare Internal PDR | 28/11/2018 | 28/11/2018 | 28/11/2018 | 15/10/2019 | 0 | TK_Complete | 94810358 | 132 | 94810358_132
A164720 | TT_Task | HVAC - Prepare Internal DDR | 15/10/2019 | 15/10/2019 | 15/10/2019 | 24/07/2020 | 0 | TK_Complete | 94810358 | 132 | 94810358_132
A86380 | TT_Task | HVAC - Collect Electrical BBIs | 10/09/2018 | 15/11/2018 | 04/04/2018 | 12/10/2018 | 0 | TK_Complete | 94810358 | 133 | 94810358_133
A86390 | TT_Task | HVAC - Lead Time 1st Product | 01/08/2019 | 20/05/2020 | 08/07/2019 | 10/01/2020 | 0 | TK_Complete | 94810358 | 134 | 94810358_134
A86460 | TT_Task | HVAC - SRD for Contract Negotiations | 04/04/2018 | 07/09/2018 | 04/04/2018 | 08/10/2018 | 0 | TK_Complete | 94810358 | 135 | 94810358_135
A86470 | TT_Task | HVAC - Supplier Contract | 19/11/2018 | 24/01/2019 | 09/10/2018 | 05/07/2019 | 0 | TK_Complete | 94810358 | 136 | 94810358_136
A164950 | TT_Task | Primary Energy Supply and Propulsion, Aux. Supply - Prepare Internal CDR | 04/04/2018 | 17/10/2018 | 04/04/2018 | 20/02/2019 | 0 | TK_Complete | 94810358 | 137 | 94810358_137
A164960 | TT_Task | Primary Energy Supply and Propulsion, Aux. Supply - Prepare Customer CDR | 04/04/2018 | 04/04/2018 | 04/04/2018 | 06/09/2018 | 0 | TK_Complete | 94810358 | 137 | 94810358_137
A164980 | TT_Task | Primary Energy Supply and Propulsion, Aux. Supply - Prepare Internal PDR | 21/02/2019 | 21/02/2019 | 21/02/2019 | 12/09/2019 | 0 | TK_Complete | 94810358 | 138 | 94810358_138
A165040 | TT_Task | Primary Energy Supply and Propulsion, Aux. Supply - Prepare Internal DDR | 13/09/2019 | 13/09/2019 | 13/09/2019 | 17/03/2021 | 0 | TK_Complete | 94810358 | 138 | 94810358_138
A168200 | TT_Task | Primary Energy Supply and Propulsion, Aux. Supply - Collect Electrical BBIs | 10/09/2018 | 09/01/2019 | 04/04/2018 | 30/10/2019 | 0 | TK_Complete | 94810358 | 139 | 94810358_139
A83560 | TT_Task | Primary Energy Supply and Propulsion - Design Freeze for Production/Procurement | 04/04/2018 | 03/08/2018 | 04/04/2018 | 16/11/2018 | 0 | TK_Complete | 94810358 | 140 | 94810358_140
A83580 | TT_Task | Primary Energy Supply and Propulsion - Lead Time 1st Product | 17/12/2018 | 17/04/2020 | 19/11/2018 | 18/09/2020 | 0 | TK_Complete | 94810358 | 141 | 94810358_141
A165110 | TT_Task | Braking and Air Supply - Prepare Internal CDR | 04/04/2018 | 08/10/2018 | 04/04/2018 | 20/02/2019 | 0 | TK_Complete | 94810358 | 142 | 94810358_142
A165120 | TT_Task | Braking and Air Supply - Prepare Customer CDR | 04/04/2018 | 04/04/2018 | 04/04/2018 | 13/09/2018 | 0 | TK_Complete | 94810358 | 142 | 94810358_142
A165140 | TT_Task | Braking and Air Supply - Prepare Internal PDR | 21/02/2019 | 21/02/2019 | 21/02/2019 | 12/09/2019 | 0 | TK_Complete | 94810358 | 143 | 94810358_143
A165200 | TT_Task | Braking and Air Supply - Prepare Internal DDR | 13/09/2019 | 13/09/2019 | 13/09/2019 | 04/03/2021 | 0 | TK_Complete | 94810358 | 143 | 94810358_143
A86780 | TT_Task | Braking and Air Supply - Lead Time 1st Product | 12/08/2019 | 07/08/2020 | 29/06/2019 | 21/08/2020 | 0 | TK_Complete | 94810358 | 144 | 94810358_144
A86850 | TT_Task | Braking and Air Supply - SRD for Contract Negotiations | 04/04/2018 | 07/09/2018 | 04/04/2018 | 19/10/2018 | 0 | TK_Complete | 94810358 | 145 | 94810358_145
A86860 | TT_Task | Braking and Air Supply - Supplier Contract | 19/11/2018 | 24/01/2019 | 22/10/2018 | 30/09/2019 | 0 | TK_Complete | 94810358 | 146 | 94810358_146
A165280 | TT_Task | Coupling and Interconnection - Prepare Customer CDR | 04/04/2018 | 04/04/2018 | 04/04/2018 | 15/08/2018 | 0 | TK_Complete | 94810358 | 147 | 94810358_147
A86900 | TT_Task | Coupling and Interconnection - Collect Electrical BBIs | 10/09/2018 | 09/01/2019 | 04/04/2018 | 22/10/2018 | 0 | TK_Complete | 94810358 | 148 | 94810358_148
A86910 | TT_Task | Coupling - Lead Time 1st Product | 24/06/2019 | 26/06/2020 | 22/05/2019 | 28/08/2020 | 0 | TK_Complete | 94810358 | 149 | 94810358_149
A86980 | TT_Task | Coupling - SRD for Contract Negotiations | 04/04/2018 | 07/09/2018 | 04/04/2018 | 10/10/2018 | 0 | TK_Complete | 94810358 | 150 | 94810358_150
A86990 | TT_Task | Coupling - Supplier Contract | 19/11/2018 | 24/01/2019 | 11/10/2018 | 21/05/2019 | 0 | TK_Complete | 94810358 | 151 | 94810358_151
A87040 | TT_Task | Gangway - Lead Time 1st Product | 24/06/2019 | 27/03/2020 | 22/05/2019 | 25/08/2020 | 0 | TK_Complete | 94810358 | 152 | 94810358_152
A87110 | TT_Task | Gangway - SRD for Contract Negotiations | 04/04/2018 | 07/09/2018 | 04/04/2018 | 05/10/2018 | 0 | TK_Complete | 94810358 | 153 | 94810358_153
A87120 | TT_Task | Gangway - Supplier Contract | 19/11/2018 | 24/01/2019 | 08/10/2018 | 21/05/2019 | 0 | TK_Complete | 94810358 | 154 | 94810358_154
A165760 | TT_Task | On Board Train Information (PIES) - Prepare Customer CDR | 04/04/2018 | 04/04/2018 | 04/04/2018 | 22/08/2018 | 0 | TK_Complete | 94810358 | 155 | 94810358_155
A184200 | TT_Task | On Board Train Information (PIES) - Prepare Internal PDR | 15/02/2019 | 15/02/2019 | 21/02/2019 | 11/09/2019 | 0 | TK_Complete | 94810358 | 156 | 94810358_156
A184520 | TT_Task | On Board Train Information (PIES) - Prepare Internal DDR | 12/09/2019 | 12/09/2019 | 12/09/2019 | 27/10/2020 | 0 | TK_Complete | 94810358 | 156 | 94810358_156
A184560 | TT_Task | On Board Train Information (PIES) - Prepare Customer DDR | 04/04/2018 | 04/04/2018 | 22/05/2019 | 23/10/2019 | 0 | TK_Complete | 94810358 | 155 | 94810358_155
A184570 | TT_Task | On Board Train Information (PIES) - Customer DDR | 01/11/2019 | 01/11/2019 | 23/10/2019 | 23/10/2019 | 0 | TK_Complete | 94810358 | 155 | 94810358_155
A87290 | TT_Task | On Board Train Information (PIES) - Collect Electrical BBIs | 10/09/2018 | 09/01/2019 | 04/04/2018 | 02/11/2018 | 0 | TK_Complete | 94810358 | 157 | 94810358_157
A87300 | TT_Task | On Board Train Information (PIES) - Lead Time 1st Product | 11/11/2019 | 23/10/2020 | 11/11/2019 | 23/07/2020 | 0 | TK_Complete | 94810358 | 158 | 94810358_158
A87370 | TT_Task | On Board Train Information (PIES) - SRD for Contract Negotiations | 04/04/2018 | 07/09/2018 | 04/04/2018 | 12/10/2018 | 0 | TK_Complete | 94810358 | 159 | 94810358_159
A87380 | TT_Task | On Board Train Information (PIES) - Supplier Contract | 19/11/2018 | 24/01/2019 | 15/10/2018 | 14/11/2019 | 0 | TK_Complete | 94810358 | 160 | 94810358_160
A165920 | TT_Task | CCTV, Passenger Counting and Ticketing - Prepare Customer CDR | 04/04/2018 | 04/04/2018 | 04/04/2018 | 22/08/2018 | 0 | TK_Complete | 94810358 | 161 | 94810358_161
A87420 | TT_Task | CCTV, Passenger Counting and Ticketing - Collect Electrical BBIs | 10/09/2018 | 09/01/2019 | 04/04/2018 | 12/10/2018 | 0 | TK_Complete | 94810358 | 162 | 94810358_162
A184580 | TT_Task | CCTV System - Prepare Customer DDR | 04/04/2018 | 04/04/2018 | 22/05/2019 | 22/10/2019 | 0 | TK_Complete | 94810358 | 163 | 94810358_163
A184590 | TT_Task | CCTV System - Customer DDR | 24/10/2019 | 24/10/2019 | 23/10/2019 | 23/10/2019 | 0 | TK_Complete | 94810358 | 163 | 94810358_163
A184600 | TT_Task | Passenger Counting - Prepare Customer DDR | 04/04/2018 | 04/04/2018 | 22/05/2019 | 23/10/2019 | 0 | TK_Complete | 94810358 | 164 | 94810358_164
A184610 | TT_Task | Passenger Counting - Customer DDR | 01/11/2019 | 01/11/2019 | 01/11/2019 | 01/11/2019 | 0 | TK_Complete | 94810358 | 164 | 94810358_164
A184620 | TT_Task | Ticketing System - Prepare Customer DDR | 04/04/2018 | 04/04/2018 | 22/05/2019 | 24/10/2019 | 0 | TK_Complete | 94810358 | 165 | 94810358_165
A87430 | TT_Task | CCTV, Passenger Counting and Ticketing - Lead Time 1st Product | 12/08/2019 | 03/04/2020 | 30/08/2019 | 29/09/2020 | 0 | TK_Complete | 94810358 | 166 | 94810358_166
A87500 | TT_Task | CCTV, Passenger Counting and Ticketing - SRD for Contract Negotiations | 04/04/2018 | 07/09/2018 | 04/04/2018 | 09/10/2018 | 0 | TK_Complete | 94810358 | 167 | 94810358_167
A87510 | TT_Task | CCTV, Passenger Counting and Ticketing - Supplier Contract | 19/11/2018 | 24/01/2019 | 10/10/2018 | 29/08/2019 | 0 | TK_Complete | 94810358 | 167 | 94810358_167
A166070 | TT_Task | Train Control - Prepare Internal CDR | 04/04/2018 | 27/09/2018 | 04/04/2018 | 14/02/2019 | 0 | TK_Complete | 94810358 | 168 | 94810358_168
A166080 | TT_Task | Train Control and Management System, TCMS - Prepare Customer CDR | 04/04/2018 | 04/04/2018 | 04/04/2018 | 01/10/2018 | 0 | TK_Complete | 94810358 | 169 | 94810358_169
A166100 | TT_Task | Train Control - Prepare Internal PDR | 15/02/2019 | 15/02/2019 | 15/02/2019 | 12/09/2019 | 0 | TK_Complete | 94810358 | 170 | 94810358_170
A166160 | TT_Task | Train Control - Prepare Internal DDR | 13/09/2019 | 13/09/2019 | 13/09/2019 | 26/10/2020 | 0 | TK_Complete | 94810358 | 171 | 94810358_171
A184640 | TT_Task | Train Control - Prepare Customer DDR | 04/04/2018 | 04/04/2018 | 22/05/2019 | 17/09/2019 | 0 | TK_Complete | 94810358 | 171 | 94810358_171
A87550 | TT_Task | Train Control - Collect Electrical BBIs | 10/09/2018 | 09/01/2019 | 04/04/2018 | 12/10/2018 | 0 | TK_Complete | 94810358 | 157 | 94810358_157
A83320 | TT_Task | T1 Development | 14/06/2018 | 02/10/2018 | 15/06/2018 | 07/12/2018 | 0 | TK_Complete | 94810358 | 172 | 94810358_172
A83340 | TT_Task | T2 Development | 03/12/2018 | 03/04/2019 | 10/12/2018 | 22/02/2019 | 0 | TK_Complete | 94810358 | 172 | 94810358_172
A83360 | TT_Task | T3 Development | 25/02/2019 | 26/06/2019 | 25/02/2019 | 02/12/2019 | 0 | TK_Complete | 94810358 | 173 | 94810358_173
A83380 | TT_Task | T4 Development | 01/01/2020 | 01/05/2020 | 03/12/2019 | 22/01/2020 | 0 | TK_Complete | 94810358 | 174 | 94810358_174
A83400 | TT_Task | T5 Development | 02/03/2020 | 01/07/2020 | 03/02/2020 | 28/02/2021 | 0 | TK_Complete | 94810358 | 175 | 94810358_175
A83420 | TT_Task | T6 Development | 03/12/2021 | 05/04/2022 | nan | nan | 0 | TK_NotStart | 94810358 | 176 | 94810358_176
A83440 | TT_Task | T7 Development | 16/03/2022 | 15/07/2022 | nan | nan | 0 | TK_NotStart | 94810358 | 177 | 94810358_177
A83460 | TT_Task | T8 Development | 28/04/2022 | 29/08/2022 | nan | nan | 0 | TK_NotStart | 94810358 | 178 | 94810358_178
A83480 | TT_Task | T9 Development | 10/06/2022 | 11/10/2022 | nan | nan | 0 | TK_NotStart | 94810358 | 179 | 94810358_179
A167450 | TT_Task | (EWIS) Circuit Diagram Preparation DM Car | 19/11/2018 | 03/05/2019 | 19/11/2018 | 29/05/2019 | 0 | TK_Complete | 94810358 | 180 | 94810358_180
A167460 | TT_Task | (EWIS) Circuit Diagram Preparation T Car | 19/11/2018 | 03/05/2019 | 19/11/2018 | 14/06/2019 | 0 | TK_Complete | 94810358 | 180 | 94810358_180
A167490 | TT_Task | (BST) Wiring Diagram Preparation DM Car | 30/05/2019 | 04/10/2019 | 29/04/2019 | 30/10/2019 | 0 | TK_Complete | 94810358 | 181 | 94810358_181
A167500 | TT_Task | (BST) Wiring Diagram Preparation T Car | 29/04/2019 | 13/09/2019 | 29/04/2019 | 29/11/2019 | 0 | TK_Complete | 94810358 | 181 | 94810358_181
A166230 | TT_Task | Signalling ATC ATP ATO and DAS - Prepare Internal CDR | 04/04/2018 | 27/09/2018 | 04/04/2018 | 11/02/2019 | 0 | TK_Complete | 94810358 | 182 | 94810358_182
A166240 | TT_Task | Signalling ATC ATP ATO and DAS - Prepare Customer CDR | 04/04/2018 | 04/04/2018 | 04/04/2018 | 02/10/2018 | 0 | TK_Complete | 94810358 | 182 | 94810358_182
A166260 | TT_Task | Signalling ATC ATP ATO and DAS - Prepare Internal PDR | 12/02/2019 | 12/02/2019 | 12/02/2019 | 12/09/2019 | 0 | TK_Complete | 94810358 | 182 | 94810358_182
A166320 | TT_Task | Signalling ATC ATP ATO and DAS - Prepare Internal DDR | 05/11/2019 | 05/11/2019 | 05/11/2019 | 23/03/2021 | 0 | TK_Complete | 94810358 | 182 | 94810358_182
A184660 | TT_Task | Signalling ATC ATP ATO and DAS - Prepare Customer DDR | 04/04/2018 | 04/04/2018 | 22/05/2019 | 04/12/2019 | 0 | TK_Complete | 94810358 | 182 | 94810358_182
A166400 | TT_Task | Train to Wayside Data Communication and Train Radio - Prepare Customer CDR | 04/04/2018 | 04/04/2018 | 04/04/2018 | 07/11/2018 | 0 | TK_Complete | 94810358 | 183 | 94810358_183
A184680 | TT_Task | Train to Wayside Data Communication - Prepare Customer DDR | 04/04/2018 | 04/04/2018 | 22/05/2019 | 19/11/2019 | 0 | TK_Complete | 94810358 | 184 | 94810358_184
A87810 | TT_Task | Train to Wayside Data Communication and Train Radio - Collect Electrical BBIs | 10/09/2018 | 09/01/2019 | 04/04/2018 | 09/11/2018 | 0 | TK_Complete | 94810358 | 185 | 94810358_185
A87820 | TT_Task | Train External Communications - Lead Time 1st Product | 12/08/2019 | 21/02/2020 | 30/08/2019 | 29/09/2020 | 0 | TK_Complete | 94810358 | 186 | 94810358_186
A87890 | TT_Task | Train External Communications - SRD for Contract Negotiations | 04/04/2018 | 07/09/2018 | 04/04/2018 | 12/10/2018 | 0 | TK_Complete | 94810358 | 187 | 94810358_187
A87900 | TT_Task | Train External Communications - Supplier Contract | 19/11/2018 | 24/01/2019 | 15/10/2018 | 29/08/2019 | 0 | TK_Complete | 94810358 | 188 | 94810358_188
A87950 | TT_Task | On Board Train Communication - Lead Time 1st Product | 11/11/2019 | 06/11/2020 | 11/11/2019 | 23/07/2020 | 0 | TK_Complete | 94810358 | 186 | 94810358_186
A88020 | TT_Task | On Board Train Communication - SRD for Contract Negotiations | 04/04/2018 | 07/09/2018 | 04/04/2018 | 12/10/2018 | 0 | TK_Complete | 94810358 | 159 | 94810358_159
A88030 | TT_Task | On Board Train Communication - Supplier Contract | 19/11/2018 | 24/01/2019 | 15/10/2018 | 14/11/2019 | 0 | TK_Complete | 94810358 | 160 | 94810358_160
A166560 | TT_Task | Electrical Harnesses and Cubicles - Prepare Customer CDR | 04/04/2018 | 04/04/2018 | 04/04/2018 | 18/09/2018 | 0 | TK_Complete | 94810358 | 189 | 94810358_189
A168320 | TT_Task | Pipework ; Hoses, Flange Lubrication - Prepare Customer CDR | 04/04/2018 | 04/04/2018 | 04/04/2018 | 23/10/2018 | 0 | TK_Complete | 94810358 | 190 | 94810358_190
A166880 | TT_Task | Fire Safety System - Prepare Customer CDR | 04/04/2018 | 04/04/2018 | 04/04/2018 | 12/09/2018 | 0 | TK_Complete | 94810358 | 191 | 94810358_191
A88460 | TT_Task | Fire Safety System - Collect Electrical BBIs | 04/04/2018 | 03/08/2018 | 04/04/2018 | 12/10/2018 | 0 | TK_Complete | 94810358 | 192 | 94810358_192
A88470 | TT_Task | Fire Safety System - Lead Time 1st Product | 01/03/2019 | 24/10/2019 | 22/03/2019 | 25/08/2020 | 0 | TK_Complete | 94810358 | 193 | 94810358_193
A88540 | TT_Task | Fire Safety System - SRD for Contract Negotiations | 04/04/2018 | 07/09/2018 | 04/04/2018 | 11/10/2018 | 0 | TK_Complete | 94810358 | 194 | 94810358_194
A88550 | TT_Task | Fire Safety System - Supplier Contract | 19/11/2018 | 24/01/2019 | 12/10/2018 | 21/03/2019 | 0 | TK_Complete | 94810358 | 195 | 94810358_195
A168010 | TT_Task | Locking - Prepare Customer CDR | 04/04/2018 | 04/04/2018 | 04/04/2018 | 10/10/2018 | 0 | TK_Complete | 94810358 | 196 | 94810358_196
A88590 | TT_Task | Locking - Collect Electrical BBIs | 10/09/2018 | 09/01/2019 | 04/04/2018 | 12/11/2018 | 0 | TK_Complete | 94810358 | 197 | 94810358_197
A17480 | TT_Task | Perform Integration Work for Station 7 | 24/06/2019 | 22/10/2019 | 10/06/2019 | 09/10/2019 | 0 | TK_Complete | 94810358 | 198 | 94810358_198
A88730 | TT_Task | Perform Integration Work for Station 8 | 24/06/2019 | 23/10/2019 | 14/06/2019 | 15/10/2019 | 0 | TK_Complete | 94810358 | 198 | 94810358_198
A88740 | TT_Task | Perform Integration Work for Station 9 | 28/06/2019 | 29/10/2019 | 20/06/2019 | 21/10/2019 | 0 | TK_Complete | 94810358 | 198 | 94810358_198
A167430 | TT_Task | Interior ; Electrical Preparation for DM Car | 08/10/2019 | 29/01/2020 | 08/10/2019 | 24/12/2019 | 0 | TK_Complete | 94810358 | 199 | 94810358_199
A167440 | TT_Task | Interior ; Electrical Preparation for T Car | 11/11/2019 | 06/02/2020 | 11/11/2019 | 06/01/2020 | 0 | TK_Complete | 94810358 | 200 | 94810358_200
A11400 | TT_Task | Standard Lead Time Methods and Procurement B;C Parts for Station 7 | 02/03/2020 | 08/07/2020 | 10/10/2019 | 07/09/2020 | 0 | TK_Complete | 94810358 | 201 | 94810358_201
A88710 | TT_Task | Standard Lead Time Methods and Procurement B;C Parts for Station 8 | 09/03/2020 | 15/07/2020 | 16/10/2019 | 22/09/2020 | 0 | TK_Complete | 94810358 | 201 | 94810358_201
A88720 | TT_Task | Standard Lead Time Methods and Procurement B;C Parts for Station 9 | 16/03/2020 | 22/07/2020 | 22/10/2019 | 23/10/2020 | 0 | TK_Complete | 94810358 | 201 | 94810358_201
ATL100010 | TT_Task | FVRS - Interface Evaluation | 04/10/2021 | 09/02/2022 | 04/10/2021 | 29/10/2021 | 0 | TK_Complete | 94810358 | 202 | 94810358_202
ATL100011 | TT_Task | FVRS - 1st Version Release | 01/11/2021 | 09/03/2022 | 01/11/2021 | 26/11/2021 | 0 | TK_Complete | 94810358 | 203 | 94810358_203
ATL100012 | TT_Task | FVRS - 1st Version Update | 29/11/2021 | 06/04/2022 | 29/11/2021 | nan | 0 | TK_Active | 94810358 | 203 | 94810358_203
ATL100013 | TT_Task | FVRS - 1st Version Update and Documentation | 28/02/2022 | 27/06/2022 | nan | nan | 0 | TK_NotStart | 94810358 | 203 | 94810358_203
ATL100020 | TT_Task | FVDS - Drive Brake - Interface Evaluation | 01/11/2021 | 09/03/2022 | 01/11/2021 | 26/11/2021 | 0 | TK_Complete | 94810358 | 204 | 94810358_204
ATL100021 | TT_Task | FVDS - Drive Brake - 1st Version Release | 29/11/2021 | 06/04/2022 | 29/11/2021 | nan | 0 | TK_Active | 94810358 | 205 | 94810358_205
ATL100022 | TT_Task | FVDS - Drive Brake - 1st Version Update and Documentation | 28/02/2022 | 27/06/2022 | nan | nan | 0 | TK_NotStart | 94810358 | 205 | 94810358_205
ATL100030 | TT_Task | FVDS - ATP - 1st Version Release (Start of CtC) | 03/01/2022 | 02/05/2022 | nan | nan | 0 | TK_NotStart | 94810358 | 206 | 94810358_206
ATL100031 | TT_Task | FVDS - ATP - 1st Version Update and Documentation | 28/02/2022 | 27/06/2022 | nan | nan | 0 | TK_NotStart | 94810358 | 206 | 94810358_206
ATL100040 | TT_Task | Virtual Bird Model - Check basis and 1st Model Preparation | 04/10/2021 | 09/02/2022 | 04/10/2021 | 26/11/2021 | 0 | TK_Complete | 94810358 | 207 | 94810358_207
ATL100041 | TT_Task | Virtual Bird Model - 1st Version Model Release | 03/01/2022 | 02/05/2022 | nan | nan | 0 | TK_NotStart | 94810358 | 208 | 94810358_208
ATL100042 | TT_Task | Virtual Bird Model - Operation Model Release | 31/01/2022 | 30/05/2022 | nan | nan | 0 | TK_NotStart | 94810358 | 208 | 94810358_208
ATL100043 | TT_Task | Virtual Bird Model - Final Model Release | 28/02/2022 | 27/06/2022 | nan | nan | 0 | TK_NotStart | 94810358 | 208 | 94810358_208
ATL100053 | TT_Task | Virtual Bird Simulation - 1st Version Simulation | 31/01/2022 | 30/05/2022 | nan | nan | 0 | TK_NotStart | 94810358 | 209 | 94810358_209
ATL100063 | TT_Task | Virtual Bird Simulation - Final Version Simulation | 28/02/2022 | 27/06/2022 | nan | nan | 0 | TK_NotStart | 94810358 | 209 | 94810358_209
ATL100813 | TT_Task | TCMS - System Requirement/ Achitecture - T2 Milestone (2 months Assumption) | 02/03/2022 | 29/06/2022 | nan | nan | 0 | TK_NotStart | 94810358 | 210 | 94810358_210
ATL100823 | TT_Task | TCMS - Software Implementation - T3.1 ; T4.1 Milestone (3 months Assumption) | 27/04/2022 | 24/08/2022 | nan | nan | 0 | TK_NotStart | 94810358 | 211 | 94810358_211
ATL100833 | TT_Task | TCMS - Lab Test Validation - T5.1 Milestone (2 months Assumption) | 20/07/2022 | 16/11/2022 | nan | nan | 0 | TK_NotStart | 94810358 | 212 | 94810358_212
ATL100843 | TT_Task | TCMS - Bug Fix and Release - T5.2 Milestone ( 2 months Assumption) | 14/09/2022 | 19/01/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 213 | 94810358_213
ATL100923 | TT_Task | System Interfaces Description preliminary version (SyID) for PGR | 11/02/2022 | 10/06/2022 | nan | nan | 0 | TK_NotStart | 94810358 | 214 | 94810358_214
ATL100953 | TT_Task | System Interfaces Description final version (SyID) for CGR | 19/04/2022 | 16/08/2022 | nan | nan | 0 | TK_NotStart | 94810358 | 215 | 94810358_215
ATL100963 | TT_Task | System Electrical Principles (SyEP) final version | 04/05/2022 | 31/08/2022 | nan | nan | 15680 | TK_NotStart | 94810358 | 216 | 94810358_216
ATL101073 | TT_Task | SyAD/SyID/SyRS Traceability | 04/05/2022 | 31/08/2022 | nan | nan | 0 | TK_NotStart | 94810358 | 217 | 94810358_217
ATL100773 | TT_Task | Installation Rules Constraints (IRC) | 14/12/2021 | 21/04/2022 | nan | nan | 0 | TK_NotStart | 94810358 | 218 | 94810358_218
ATL100793 | TT_Task | Consolidate Installation Rules evidences | 07/09/2022 | 12/01/2023 | nan | nan | 480 | TK_NotStart | 94810358 | 219 | 94810358_219
ATL100903 | TT_Task | System Requirements Specification preliminary version (SyRS) for SGR | 26/11/2021 | 05/04/2022 | 26/11/2021 | nan | 0 | TK_Active | 94810358 | 220 | 94810358_220
ATL100913 | TT_Task | System Arquitecture Description preliminary version (SyAD) for PGR | 14/01/2022 | 13/05/2022 | nan | nan | 0 | TK_NotStart | 94810358 | 221 | 94810358_221
ATL100933 | TT_Task | System Requirements Specification final version (SyRS) for PGR | 18/03/2022 | 15/07/2022 | nan | nan | 0 | TK_NotStart | 94810358 | 220 | 94810358_220
ATL100943 | TT_Task | System Arquitecture Description final version (SyAD) for CGR | 01/04/2022 | 29/07/2022 | nan | nan | 0 | TK_NotStart | 94810358 | 222 | 94810358_222
ATL101223 | TT_Task | SyRS/SyUN Traceability Traceability | 21/12/2021 | 28/04/2022 | nan | nan | 32 | TK_NotStart | 94810358 | 217 | 94810358_217
ATL101323 | TT_Task | ICD TRU | 11/02/2022 | 10/06/2022 | nan | nan | 16104 | TK_NotStart | 94810358 | 223 | 94810358_223
ATL101333 | TT_Task | ICD gateway TCMS | 21/01/2022 | 20/05/2022 | nan | nan | 0 | TK_NotStart | 94810358 | 224 | 94810358_224
ATL101343 | TT_Task | Technical Specification Gateway CIP-IPtCOM | 16/11/2021 | 24/03/2022 | 16/11/2021 | nan | 0 | TK_Active | 94810358 | 225 | 94810358_225
ATL101353 | TT_Task | Gateway Development | 25/02/2022 | 24/06/2022 | nan | nan | 0 | TK_NotStart | 94810358 | 226 | 94810358_226
ATL101363 | TT_Task | Gateway Development CRs | 01/06/2022 | 28/09/2022 | nan | nan | 1024 | TK_NotStart | 94810358 | 227 | 94810358_227
ATL100743 | TT_Task | System User Needs (SyUN) LU+PU revision | 27/10/2021 | 04/03/2022 | 27/10/2021 | 11/11/2021 | 0 | TK_Complete | 94810358 | 228 | 94810358_228
ATL100753 | TT_Task | System User Needs (SyUN) draft version and GAP analysis input vs SyUN and req coverage | 12/11/2021 | 22/03/2022 | 12/11/2021 | 25/11/2021 | 0 | TK_Complete | 94810358 | 229 | 94810358_229
ATL100763 | TT_Task | System User Needs (SyUN) consolidated version for SGR | 26/11/2021 | 05/04/2022 | 26/11/2021 | nan | 0 | TK_Active | 94810358 | 230 | 94810358_230
ATL101513 | TT_Task | Passport 7.3.1 Available | 29/10/2021 | 08/03/2022 | 29/10/2021 | 29/10/2021 | 0 | TK_Complete | 94810358 | 231 | 94810358_231
ATL101523 | TT_Task | Passport 7.4.0 Available | 25/02/2022 | 24/06/2022 | nan | nan | 0 | TK_NotStart | 94810358 | 231 | 94810358_231
ATL101533 | TT_Task | SC/ISA 7.4.0 Available | 08/04/2022 | 05/08/2022 | nan | nan | 392 | TK_NotStart | 94810358 | 232 | 94810358_232
ATL101543 | TT_Task | NoBo 7.4.0 Available | 17/06/2022 | 14/10/2022 | nan | nan | 15496 | TK_NotStart | 94810358 | 233 | 94810358_233
ATL101553 | TT_Task | DMI Passport 2.4.0 Available | 03/12/2021 | 12/04/2022 | nan | nan | 16560 | TK_NotStart | 94810358 | 234 | 94810358_234
ATL101123 | TT_Task | Customize Collecting Guide and pre-fill | 28/02/2022 | 27/06/2022 | nan | nan | 0 | TK_NotStart | 94810358 | 235 | 94810358_235
ATL101133 | TT_Task | Fill Data collecting guide by Customer / Train Integrator | 07/03/2022 | 04/07/2022 | nan | nan | 0 | TK_NotStart | 94810358 | 236 | 94810358_236
ATL101143 | TT_Task | EVC Guidelines/Launch Report | 04/04/2022 | 01/08/2022 | nan | nan | 0 | TK_NotStart | 94810358 | 237 | 94810358_237
ATL101153 | TT_Task | Fast prep | 05/05/2022 | 01/09/2022 | nan | nan | 832 | TK_NotStart | 94810358 | 238 | 94810358_238
ATL101163 | TT_Task | Lab Integration/Activity Report | 19/10/2022 | 23/02/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 239 | 94810358_239
ATL101173 | TT_Task | Release Note A | 03/11/2022 | 10/03/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 240 | 94810358_240
ATL101183 | TT_Task | SRACS Traceability for DP Process | 11/11/2022 | 20/03/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 241 | 94810358_241
ATL1001185 | TT_Task | EVC Guidelines/Launch Report | 10/08/2023 | 07/12/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 237 | 94810358_237
ATL1001186 | TT_Task | Fast Preparation | 17/08/2023 | 14/12/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 242 | 94810358_242
ATL1001187 | TT_Task | Lab Integration/Activity Report | 24/08/2023 | 21/12/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 239 | 94810358_239
ATL1001188 | TT_Task | Release Note B | 31/08/2023 | 05/01/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 240 | 94810358_240
ATL1001348 | TT_Task | EVC Guidelines/Launch Report | 21/11/2023 | 27/03/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 237 | 94810358_237
ATL1001358 | TT_Task | Fast Preparation | 28/11/2023 | 03/04/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 242 | 94810358_242
ATL1001368 | TT_Task | Lab Integration/Activity Report | 05/12/2023 | 10/04/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 239 | 94810358_239
ATL1001378 | TT_Task | Release Note C | 12/12/2023 | 17/04/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 240 | 94810358_240
ATL101473 | TT_Task | Data Verification (revisar empieza mas tarde) | 11/11/2022 | 20/03/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 243 | 94810358_243
ATL101483 | TT_Task | Test bench validation | 12/12/2022 | 18/04/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 244 | 94810358_244
ATL101493 | TT_Task | Data Validation | 14/12/2022 | 20/04/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 245 | 94810358_245
ATL101503 | TT_Task | Functional Tests (Including Report) | 03/01/2023 | 02/05/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 246 | 94810358_246
ATL101504 | TT_Task | SW Delivery Review for Odometry Testing | 24/01/2023 | 23/05/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 247 | 94810358_247
ATL101505 | TT_Task | Safety Authorisation for Odometry Testing | 25/01/2023 | 24/05/2023 | nan | nan | 800 | TK_NotStart | 94810358 | 248 | 94810358_248
ATL101423 | TT_Task | TCMS GW Integration | 18/05/2022 | 14/09/2022 | nan | nan | 0 | TK_NotStart | 94810358 | 249 | 94810358_249
ATL101433 | TT_Task | TCMS GW Validation | 03/01/2023 | 02/05/2023 | nan | nan | 14376 | TK_NotStart | 94810358 | 250 | 94810358_250
ATL1001198 | TT_Task | Update V;V documentation before campaign | 31/08/2023 | 05/01/2024 | nan | nan | 13000 | TK_NotStart | 94810358 | 251 | 94810358_251
ATL1001208 | TT_Task | Data Verification | 07/09/2023 | 12/01/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 252 | 94810358_252
ATL1001218 | TT_Task | Test bench validation | 21/09/2023 | 26/01/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 244 | 94810358_244
ATL1001228 | TT_Task | Data Validation | 25/09/2023 | 30/01/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 245 | 94810358_245
ATL1001238 | TT_Task | Functional Tests (Including Report) | 02/10/2023 | 06/02/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 246 | 94810358_246
ATL1001298 | TT_Task | Fast Prep proccess audit before Dynamic Testing | 09/10/2023 | 13/02/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 253 | 94810358_253
ATL1001308 | TT_Task | SW Delivery Review for Dynamic Testing | 13/10/2023 | 19/02/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 254 | 94810358_254
ATL1001318 | TT_Task | Quality Report for Dynamic Testing | 16/10/2023 | 20/02/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 255 | 94810358_255
ATL1001328 | TT_Task | Safety Authorisation for Dynamic Testing | 17/10/2023 | 21/02/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 256 | 94810358_256
ATL1001388 | TT_Task | Update V;V documentation before campaign | 12/12/2023 | 17/04/2024 | nan | nan | 12416 | TK_NotStart | 94810358 | 251 | 94810358_251
ATL1001398 | TT_Task | Data Verification | 19/12/2023 | 24/04/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 252 | 94810358_252
ATL1001408 | TT_Task | Test bench validation | 22/12/2023 | 29/04/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 244 | 94810358_244
ATL1001418 | TT_Task | Data Validation | 03/01/2024 | 01/05/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 245 | 94810358_245
ATL1001428 | TT_Task | Functional Tests (Including Report) | 05/01/2024 | 03/05/2024 | nan | nan | 12336 | TK_NotStart | 94810358 | 246 | 94810358_246
ATL101443 | TT_Task | Test Bench description | 11/02/2022 | 10/06/2022 | nan | nan | 824 | TK_NotStart | 94810358 | 257 | 94810358_257
ATL101453 | TT_Task | Test Bench preparation/ FIVP tests (cuando llega testbench) | 13/07/2022 | 09/11/2022 | nan | nan | 616 | TK_NotStart | 94810358 | 258 | 94810358_258
ATL101463 | TT_Task | Test Bench preparation RUN1 | 18/10/2022 | 22/02/2023 | nan | nan | 14800 | TK_NotStart | 94810358 | 259 | 94810358_259
ATL101464 | TT_Task | Test Bench preparation RUN2 | 23/08/2023 | 20/12/2023 | nan | nan | 13080 | TK_NotStart | 94810358 | 259 | 94810358_259
ATL101465 | TT_Task | Test Bench preparation RUN3 | 04/12/2023 | 09/04/2024 | nan | nan | 12496 | TK_NotStart | 94810358 | 259 | 94810358_259
ATL1001338 | TT_Task | To write Dynamic Functional site tests report | 16/11/2023 | 22/03/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 260 | 94810358_260
ATL101083 | TT_Task | Verification Reports Requirements | 25/05/2022 | 21/09/2022 | nan | nan | 0 | TK_NotStart | 94810358 | 261 | 94810358_261
ATL101093 | TT_Task | Lab Testing Procedures | 15/06/2022 | 12/10/2022 | nan | nan | 0 | TK_NotStart | 94810358 | 262 | 94810358_262
ATL101103 | TT_Task | Dynamic Tests Procedures | 13/07/2022 | 09/11/2022 | nan | nan | 0 | TK_NotStart | 94810358 | 263 | 94810358_263
ATL101113 | TT_Task | Verification Allocation Matrix (VAM)/ Traceability | 27/07/2022 | 23/11/2022 | nan | nan | 688 | TK_NotStart | 94810358 | 264 | 94810358_264
ATL101193 | TT_Task | RAM Report Draft | 18/03/2022 | 15/07/2022 | nan | nan | 56 | TK_NotStart | 94810358 | 265 | 94810358_265
ATL101203 | TT_Task | RAM Report approved for CGR Applic | 04/05/2022 | 31/08/2022 | nan | nan | 1136 | TK_NotStart | 94810358 | 266 | 94810358_266
ATL100783 | TT_Task | Reception Installation Rules by LU | 21/01/2022 | 20/05/2022 | nan | nan | 1296 | TK_NotStart | 94810358 | 267 | 94810358_267
ATL100092 | TT_Task | AT - Electrical ; Mechanical Design Concept Development (3 months for 1st Version of CTC Design) | 01/12/2021 | 08/04/2022 | 01/12/2021 | nan | 0 | TK_Active | 94810358 | 268 | 94810358_268
ATL100093 | TT_Task | AT - Electrical ; Mechanical Design Concept Development (3 months for Final Version of CTC Design) | 02/03/2022 | 29/06/2022 | nan | nan | 0 | TK_NotStart | 94810358 | 268 | 94810358_268
ATL101243 | TT_Task | BST - Wiring Design and Wiring List | 01/06/2022 | 01/06/2022 | nan | nan | 0 | TK_NotStart | 94810358 | 269 | 94810358_269
ATL101253 | TT_Task | BST - Cable Harnessess | 06/07/2022 | 06/07/2022 | nan | nan | 0 | TK_NotStart | 94810358 | 270 | 94810358_270
ATL101263 | TT_Task | BST - Detailed Mechanical Design | 08/06/2022 | 08/06/2022 | nan | nan | 0 | TK_NotStart | 94810358 | 271 | 94810358_271
ATL101273 | TT_Task | BST - Design Review (BST/ AT) | 03/08/2022 | 03/08/2022 | nan | nan | 0 | TK_NotStart | 94810358 | 272 | 94810358_272
ATL101283 | TT_Task | BST - 2D Drawing | 10/08/2022 | 10/08/2022 | nan | nan | 40 | TK_NotStart | 94810358 | 273 | 94810358_273
ATL101284 | TT_Task | AT - Detailed Electrical ; Mechanical Design | 01/06/2022 | 28/09/2022 | nan | nan | 0 | TK_NotStart | 94810358 | 274 | 94810358_274
ATL101293 | TT_Task | BST ; AT - TCUA Approval and Release | 14/09/2022 | 14/09/2022 | nan | nan | 0 | TK_NotStart | 94810358 | 275 | 94810358_275
ATL100112 | TT_Task | TCMS and ATLAS Integration Test Preparation (2 months Assumption) | 30/09/2022 | 16/02/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 276 | 94810358_276
ATL100113 | TT_Task | TCMS and ATLAS Integration Test incl. Software Update | 02/12/2022 | 20/04/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 276 | 94810358_276
ATL100433 | TT_Task | TCMS Development and Assessment (TCMS 2.. X) - Delta Assessment aligned w/ ATLAS - tb finalized before J5 (NOT USED) | 16/11/2023 | 22/03/2024 | nan | nan | 11528 | TK_NotStart | 94810358 | 277 | 94810358_277
A184490 | TT_Task | Delivery of the Materials for Testing (Driver Desk, Propulsion etc.) | 09/07/2019 | 05/11/2020 | 09/07/2019 | 18/10/2019 | 0 | TK_Complete | 94810358 | 278 | 94810358_278
A186440 | TT_Task | Train Zero Testing - Test Phase 2;3 Functional Test on Train Zero (Lv.4 Sub-system Tests - fBL 1.0.0.0) (TBC) | 03/12/2020 | 27/04/2021 | 04/08/2020 | nan | 0 | TK_Active | 94810358 | 279 | 94810358_279
A186450 | TT_Task | Train Zero Testing - Test Phase 4 Functional Test + Multiple Traction (FVTS Tests - fBL 1.1.0.0) (TBC) | 05/01/2022 | 29/03/2022 | nan | nan | 0 | TK_NotStart | 94810358 | 279 | 94810358_279
A186460 | TT_Task | Train Zero Testing - Test Phase 5 Regression (Lv.5 Tests) (TBC) | 30/03/2022 | 21/06/2022 | nan | nan | 15544 | TK_NotStart | 94810358 | 280 | 94810358_280
A186650 | TT_Task | RCS - ATP Train Zero Implementation / Setup (Link to RCS) | 03/09/2021 | 16/09/2021 | 11/06/2021 | 15/06/2021 | 0 | TK_Complete | 94810358 | 281 | 94810358_281
A186660 | TT_Task | RCS - ATP Train Zero Functional Integration Tests TZ1.1 &lt;&gt; TCMS Feature complete (Link to RCS) | 17/09/2021 | 30/09/2021 | 24/06/2021 | 28/06/2021 | 0 | TK_Complete | 94810358 | 282 | 94810358_282
A187140 | TT_Task | Lab HEN - Installation and Test Setup | 28/01/2021 | 17/02/2021 | 26/10/2020 | 13/11/2020 | 0 | TK_Complete | 94810358 | 283 | 94810358_283
A187150 | TT_Task | Lab HEN - ATP Integration Tests - Verification of Corrections, Changes ; Diagnostic | 25/06/2021 | 02/09/2021 | 16/11/2020 | 28/05/2021 | 0 | TK_Complete | 94810358 | 284 | 94810358_284
A20310 | TT_Task | Ordering of Parts for Train Zero | 04/04/2018 | 02/08/2019 | 04/04/2018 | 25/03/2019 | 0 | TK_Complete | 94810358 | 285 | 94810358_285
A81440 | TT_Task | Assembly and Commissioning of Train Zero (CTC Models + TZCS) | 25/03/2019 | 22/07/2020 | 25/03/2019 | 08/07/2019 | 0 | TK_Complete | 94810358 | 286 | 94810358_286
A81450 | TT_Task | Train Zero Testing - Test Phase 1 Commissioning Train Zero (Basic Tests) | 01/09/2020 | 30/12/2021 | 04/05/2020 | 31/07/2020 | 0 | TK_Complete | 94810358 | 287 | 94810358_287
A171150 | TT_Task | Single Typetesting in SWE for Trainset #001 | 08/08/2022 | 02/09/2022 | nan | nan | 0 | TK_NotStart | 94810358 | 288 | 94810358_288
A186940 | TT_Task | Customer Test PIS + CCTV + PCS triple traction for Trainset #001 | 02/01/2023 | 03/03/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 289 | 94810358_289
A186950 | TT_Task | Customer Test Operability Sce. DT for Trainset #001 | 16/01/2023 | 17/03/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 290 | 94810358_290
A188280 | TT_Task | Customer Test FVTS Typetest DT for Trainset #001 | 30/01/2023 | 31/03/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 291 | 94810358_291
A189250 | TT_Task | Re-commissioning (After Retrofit 4a)/ L4 ; FVTS/ DU Test/Tripple Unit Test/ Delta Tests of Trainset #001 | 01/02/2022 | 15/06/2022 | nan | nan | 0 | TK_NotStart | 94810358 | 292 | 94810358_292
A189480 | TT_Task | Customer Test Ride Comfort for Trainset #001 | 13/02/2023 | 14/04/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 293 | 94810358_293
A79080 | TT_Task | 1st Commissioning/ L4 ; FVTS/ Safety J1 ; J2 of Trainset #001 (incl. Re-run 1st Commissioning from 19.04.21) | 08/02/2021 | 22/06/2021 | 01/02/2021 | 10/09/2021 | 0 | TK_Complete | 94810358 | 294 | 94810358_294
A79130 | TT_Task | Re-commissioning (After Retrofit 4b)/ ST ; MT J2 Safety Tests/ Typetests of Trainset #001 | 16/05/2022 | 14/10/2022 | nan | nan | 0 | TK_NotStart | 94810358 | 295 | 94810358_295
A79140 | TT_Task | Triple Unit Typetesting in SWE for Trainset #001 (Assume Work in CW52/2022) | 03/10/2022 | 28/10/2022 | nan | nan | 0 | TK_NotStart | 94810358 | 296 | 94810358_296
A171180 | TT_Task | Single Typetesting incl. ETCS OB TT1 ; TT2 in SWE for Trainset #002 | 12/09/2022 | 25/11/2022 | nan | nan | 0 | TK_NotStart | 94810358 | 297 | 94810358_297
A186960 | TT_Task | Customer Test Energy Consumption Summer for Trainset #002 | 17/10/2022 | 16/12/2022 | nan | nan | 160 | TK_NotStart | 94810358 | 298 | 94810358_298
A186990 | TT_Task | Winterization Test Snowing/Raining/Wet) for Trainset #002 (Assume Work in CW52/2022) | 12/12/2022 | 06/01/2023 | nan | nan | 160 | TK_NotStart | 94810358 | 299 | 94810358_299
A187320 | TT_Task | Single Unit Typetesting in HEN (Air Flow Tests) for Trainset #002 | 25/06/2021 | 09/09/2021 | 15/06/2021 | 25/06/2021 | 0 | TK_Complete | 94810358 | 300 | 94810358_300
A187330 | TT_Task | Re-run Static ; Dynamic Commissioning for Trainset #002 (After Retrofit Slot 3 ; 4) | 18/04/2022 | 01/07/2022 | nan | nan | 0 | TK_NotStart | 94810358 | 301 | 94810358_301
A188270 | TT_Task | Single Unit Typetesting in HEN for Trainset #002 | 16/05/2022 | 14/10/2022 | nan | nan | 0 | TK_NotStart | 94810358 | 302 | 94810358_302
A79090 | TT_Task | Commissioning/ L4/ Retrofit Slot 3 ; 4 of Trainset #002 (incl. Time Impact of Re-run Commissioning) | 26/03/2021 | 20/07/2021 | 15/02/2021 | 23/07/2021 | 0 | TK_Complete | 94810358 | 303 | 94810358_303
A79150 | TT_Task | Single Unit Typetesting (Climatic Test/ HVAC in Minden and RTA Vienna) for Trainset #002 | 27/08/2021 | 11/11/2021 | 10/08/2021 | nan | 0 | TK_Active | 94810358 | 304 | 94810358_304
A79200 | TT_Task | Winterization Test Icy/Dry) for Trainset #002 (TBC) | 13/02/2023 | 10/03/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 305 | 94810358_305
A79210 | TT_Task | Double Unit Typetesting in SWE for Trainset #002 (NOT USED) | 03/12/2021 | 03/02/2022 | nan | nan | 16888 | TK_NotStart | 94810358 | 306 | 94810358_306
A171200 | TT_Task | Single Typetesting in SWE for Trainset #003 | 11/07/2022 | 23/09/2022 | nan | nan | 0 | TK_NotStart | 94810358 | 288 | 94810358_288
A187070 | TT_Task | Customer Test PIS + CCTV + PCS Triple Traction for Trainset #003 | 02/01/2023 | 17/03/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 289 | 94810358_289
A187310 | TT_Task | Purchaser's Validation ST for Trainset #003 | 23/01/2023 | 17/02/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 307 | 94810358_307
A187350 | TT_Task | Triple Unit Typetesting in SWE for Trainset #003 (Assume Work in CW52/2022) | 03/10/2022 | 02/12/2022 | nan | nan | 0 | TK_NotStart | 94810358 | 296 | 94810358_296
A189520 | TT_Task | Single + Multiple Unit J2 Safety Tests | 06/06/2022 | 12/09/2022 | nan | nan | 0 | TK_NotStart | 94810358 | 308 | 94810358_308
A189940 | TT_Task | Re-commissioning Test of Trainset #003 | 16/05/2022 | 22/08/2022 | nan | nan | 0 | TK_NotStart | 94810358 | 309 | 94810358_309
A189950 | TT_Task | Non-relevant Typetests and Customer Training for Trainset #003 | 30/01/2023 | 24/02/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 310 | 94810358_310
A79100 | TT_Task | Commissioning/ L4 ; FVTS/ Retrofit Slot 4a ; 4b/DU Test/Tripple Unit Test of Trainset #003 (Assume Work in CW52/2021) | 03/12/2021 | 11/03/2022 | 29/11/2021 | nan | 0 | TK_Active | 94810358 | 311 | 94810358_311
A79160 | TT_Task | Single Unit Typetesting in HEN for Trainset #003 (NOT USED) | 03/12/2021 | 03/03/2022 | nan | nan | 16088 | TK_NotStart | 94810358 | 302 | 94810358_302
A79250 | TT_Task | Customer Test Energy Consumption Winter for Trainset #003 | 27/03/2023 | 26/05/2023 | nan | nan | 80 | TK_NotStart | 94810358 | 298 | 94810358_298
A171220 | TT_Task | Single Typetesting in SWE for Trainset #004 | 28/03/2022 | 27/04/2022 | nan | nan | 0 | TK_NotStart | 94810358 | 288 | 94810358_288
A186970 | TT_Task | Customer Test Energy Consumption Spring/ Autumn for Trainset #004 | 19/09/2022 | 14/10/2022 | nan | nan | 0 | TK_NotStart | 94810358 | 298 | 94810358_298
A188820 | TT_Task | Re-commissioning/ L4 ; FVTS/ J1;J2 Safety Test/ Retrofit Slot 4a of Trainset #004 (Assume Work in CW52/2021) | 03/12/2021 | 23/12/2021 | nan | nan | 0 | TK_NotStart | 94810358 | 311 | 94810358_311
A79110 | TT_Task | 1st Commissioning of Trainset #004 | 25/06/2021 | 15/09/2021 | 07/06/2021 | 09/07/2021 | 0 | TK_Complete | 94810358 | 312 | 94810358_312
A79180 | TT_Task | Single Unit Typetesting in HEN for Trainset #004 (NOT USED) | 03/12/2021 | 13/01/2022 | nan | nan | 16072 | TK_NotStart | 94810358 | 302 | 94810358_302
A79230 | TT_Task | Double Unit Typetesting in SWE for Trainset #004 (NOT USED) | 03/12/2021 | 14/02/2022 | nan | nan | 16672 | TK_NotStart | 94810358 | 306 | 94810358_306
A186980 | TT_Task | Customer Test Operability Sce. DT for Trainset #005 | 16/01/2023 | 17/03/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 290 | 94810358_290
A187380 | TT_Task | Single Typetesting in SWE for Trainset #005 | 29/09/2022 | 31/10/2022 | nan | nan | 0 | TK_NotStart | 94810358 | 288 | 94810358_288
A187390 | TT_Task | Triple Unit Typetesting in SWE for Trainset #005 (Assume Work in CW52/2022) | 03/10/2022 | 02/12/2022 | nan | nan | 0 | TK_NotStart | 94810358 | 296 | 94810358_296
A188290 | TT_Task | Re-commissioning/ L4 ; FVTS/ Retrofit Slot 4b of Trainset #005 (After Retrofit Slot 3) | 21/02/2022 | 19/04/2022 | nan | nan | 0 | TK_NotStart | 94810358 | 303 | 94810358_303
A188300 | TT_Task | Customer Test FVTS Typetest DT for Trainset #005 | 30/01/2023 | 31/03/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 291 | 94810358_291
A189270 | TT_Task | Customer Test PIS + CCTV + PCS Triple Traction for Trainset #005 | 02/01/2023 | 17/03/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 289 | 94810358_289
A189570 | TT_Task | Customer Test Pressure Tightness for Trainset #005 | 20/02/2023 | 21/04/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 313 | 94810358_313
A79120 | TT_Task | 1st Commissioning/ L4 ; FVTS/ VT Train Driver Visit of Trainset #005 | 21/07/2021 | 16/09/2021 | 12/07/2021 | 24/11/2021 | 0 | TK_Complete | 94810358 | 314 | 94810358_314
A79190 | TT_Task | Single Unit Typetesting/ SU Safety Type Tests in HEN for Trainset #005 | 16/05/2022 | 16/08/2022 | nan | nan | 0 | TK_NotStart | 94810358 | 300 | 94810358_300
A167650 | TT_Task | Last Doc to NoBo (NOT USED) | 14/11/2022 | 02/12/2022 | nan | nan | 0 | TK_NotStart | 94810358 | 315 | 94810358_315
A186770 | TT_Task | ERATV Registration - Preparation of Entry and Information to ERA (1 month) (NOT USED) | 24/07/2023 | 10/11/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 316 | 94810358_316
A186780 | TT_Task | ERATV Registration - Validation and Publication by ERA (1 month) (NOT USED) | 21/08/2023 | 08/12/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 317 | 94810358_317
A186790 | TT_Task | Conformity to Type (C2T) (1 month) (NOT USED) | 18/09/2023 | 05/01/2024 | nan | nan | 13120 | TK_NotStart | 94810358 | 318 | 94810358_318
A186840 | TT_Task | Last Doc to DeBo (NOT USED) | 28/11/2022 | 16/12/2022 | nan | nan | 0 | TK_NotStart | 94810358 | 319 | 94810358_319
A186850 | TT_Task | Last Doc to AsBo and AsBo Report (NOT USED) | 12/12/2022 | 13/01/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 320 | 94810358_320
A79270 | TT_Task | Preparation of Last TT Report for Single Unit Operation (NOT USED) | 17/10/2022 | 11/11/2022 | nan | nan | 0 | TK_NotStart | 94810358 | 321 | 94810358_321
A79290 | TT_Task | NSA Working Time acc. to 4th Railway Package - Single Unit (5 months) (NOT USED) | 20/02/2023 | 09/06/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 322 | 94810358_322
A167660 | TT_Task | Last Doc to NoBo - Scenario A1 (NOT USED) | 06/02/2023 | 24/02/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 323 | 94810358_323
A186800 | TT_Task | ERATV Registration - Preparation of Entry and Information to ERA (1 month) - Scenario A1 (NOT USED) | 02/10/2023 | 19/01/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 316 | 94810358_316
A186810 | TT_Task | ERATV Registration - Validation and Publication by ERA (1month) - Scenario A1 (NOT USED) | 30/10/2023 | 16/02/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 317 | 94810358_317
A186820 | TT_Task | Conformity to Type (C2T) (1 month) - Scenario A1 (NOT USED) | 01/05/2023 | 18/08/2023 | nan | nan | 1040 | TK_NotStart | 94810358 | 318 | 94810358_318
A187050 | TT_Task | Last Doc to DeBo - Scenario A1 (NOT USED) | 20/02/2023 | 10/03/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 319 | 94810358_319
A187060 | TT_Task | Last Doc to AsBo and AsBo Report - Scenario A1 (NOT USED) | 06/03/2023 | 24/03/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 320 | 94810358_320
A79280 | TT_Task | Preparation of Last TT Report for Multiple Unit Operation - Scenario A1 (NOT USED) | 02/01/2023 | 06/01/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 321 | 94810358_321
A79300 | TT_Task | NSA Working Time acc. to 4th Railway Package - Multiple Unit (5 months) - Scenario A1 (NOT USED) | 01/05/2023 | 21/07/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 322 | 94810358_322
A189620 | TT_Task | Last TT Report Creation (1month plus 3 weeks ENG Buffer) | 02/01/2023 | 21/04/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 324 | 94810358_324
A189630 | TT_Task | NoBo/DeBo/AsBo Asessment (3 months) | 20/02/2023 | 09/06/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 325 | 94810358_325
A189860 | TT_Task | J5 Application and Approval Time (4 months) | 22/05/2023 | 08/09/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 326 | 94810358_326
A189640 | TT_Task | D;IS ISA Assessment, Last TT Report Creation (1month) and NoBo/DeBo/AsBo Asessment (3 months) | 16/11/2023 | 20/03/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 327 | 94810358_327
A189650 | TT_Task | J5 Application and Approval Time (4 months) | 21/03/2024 | 10/07/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 326 | 94810358_326
A189980 | TT_Task | Last TT Report Creation (1month) and NoBo/DeBo/AsBo Asessment (3 months) (TBC) | 07/12/2023 | 10/04/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 328 | 94810358_328
A189990 | TT_Task | J5 Application and Approval Time (4 months) (TBC) | 18/04/2024 | 07/08/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 326 | 94810358_326
A190080 | TT_Task | D;IS ISA Assessment (10 wks) | 16/11/2023 | 20/03/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 329 | 94810358_329
A190090 | TT_Task | NoBo/ DeBo/ AsBo Assessment (19 wks) | 08/02/2024 | 29/05/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 330 | 94810358_330
A190100 | TT_Task | ERA/ NSA Check and Assessment Process Time acc. to 4th Railway Package (5 months) | 20/06/2024 | 11/09/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 331 | 94810358_331
A190110 | TT_Task | Conformity to Type (C2T) (1 month in parallel with ERA/NSA check and Assessment Process) | 20/06/2024 | 09/10/2024 | nan | nan | 1040 | TK_NotStart | 94810358 | 332 | 94810358_332
A190120 | TT_Task | ERATV Registration - Preparation of Entry and Information to ERA (1 month) | 21/11/2024 | 26/03/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 316 | 94810358_316
A190130 | TT_Task | ERATV Registration - Validation and Publication by ERA (1month) | 19/12/2024 | 23/04/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 317 | 94810358_317
A75660 | TT_Task | Customer Review on the Mock-up Scope | 28/05/2018 | 08/06/2018 | 28/05/2018 | 29/05/2018 | 0 | TK_Complete | 94810358 | 333 | 94810358_333
A75930 | TT_Task | Customer Review of the White Mock-up | 04/10/2018 | 12/10/2018 | 04/10/2018 | 12/10/2018 | 0 | TK_Complete | 94810358 | 334 | 94810358_334
A75960 | TT_Task | Customer Review of the Final Mock-up | 10/12/2018 | 10/12/2018 | 10/12/2018 | 12/12/2018 | 0 | TK_Complete | 94810358 | 333 | 94810358_333
A75650 | TT_Task | Pre-Manufacturing Phase | 04/04/2018 | 25/05/2018 | 04/04/2018 | 25/05/2018 | 0 | TK_Complete | 94810358 | 335 | 94810358_335
A75920 | TT_Task | Manufacturing Phase (White Mock-up) | 30/05/2018 | 12/09/2018 | 30/05/2018 | 03/10/2018 | 0 | TK_Complete | 94810358 | 336 | 94810358_336
A75950 | TT_Task | Finalization Phase | 15/10/2018 | 14/12/2018 | 15/10/2018 | 07/12/2018 | 0 | TK_Complete | 94810358 | 337 | 94810358_337
A75980 | TT_Task | Utilization Phase | 20/12/2018 | 09/05/2019 | 20/12/2018 | 31/05/2019 | 0 | TK_Complete | 94810358 | 338 | 94810358_338
A169720 | TT_Task | Session 11 (C+FG) | 12/12/2018 | 25/12/2018 | 10/12/2018 | 12/12/2018 | 0 | TK_Complete | 94810358 | 339 | 94810358_339
A75680 | TT_Task | Session 1 (C) | 29/05/2018 | 29/05/2018 | 28/05/2018 | 29/05/2018 | 0 | TK_Complete | 94810358 | 340 | 94810358_340
A75690 | TT_Task | Session 2 (C) | 09/07/2018 | 09/07/2018 | 12/06/2018 | 13/06/2018 | 0 | TK_Complete | 94810358 | 340 | 94810358_340
A75700 | TT_Task | Session 3 (C) | 09/07/2018 | 20/07/2018 | 27/06/2018 | 28/06/2018 | 0 | TK_Complete | 94810358 | 340 | 94810358_340
A75710 | TT_Task | Session 4 (C+FG) | 23/07/2018 | 23/07/2018 | 04/07/2018 | 05/07/2018 | 0 | TK_Complete | 94810358 | 339 | 94810358_339
A75720 | TT_Task | Session 5 (C) | 23/07/2018 | 23/07/2018 | 15/08/2018 | 16/08/2018 | 0 | TK_Complete | 94810358 | 341 | 94810358_341
A75730 | TT_Task | Session 6 (C+FG) | 05/09/2018 | 05/09/2018 | 05/09/2018 | 05/09/2018 | 0 | TK_Complete | 94810358 | 339 | 94810358_339
A75740 | TT_Task | Session 7 (C) | 04/10/2018 | 17/10/2018 | 04/10/2018 | 05/10/2018 | 0 | TK_Complete | 94810358 | 341 | 94810358_341
A75750 | TT_Task | Session 8 (C) | 10/10/2018 | 10/10/2018 | 10/10/2018 | 11/10/2018 | 0 | TK_Complete | 94810358 | 341 | 94810358_341
A75760 | TT_Task | Session 9 (C) | 24/10/2018 | 06/11/2018 | 24/10/2018 | 25/10/2018 | 0 | TK_Complete | 94810358 | 341 | 94810358_341
A75770 | TT_Task | Session 10 (C) | 07/11/2018 | 07/11/2018 | 07/11/2018 | 08/11/2018 | 0 | TK_Complete | 94810358 | 341 | 94810358_341
A75780 | TT_Task | VT visit | 12/12/2018 | 25/12/2018 | 29/11/2018 | 29/11/2018 | 0 | TK_Complete | 94810358 | 342 | 94810358_342
A79020 | TT_Task | Methods Carbody Mock-up Preparation | 03/07/2018 | 20/08/2018 | 03/07/2018 | 20/08/2018 | 0 | TK_Complete | 94810358 | 74 | 94810358_74
A79030 | TT_Task | Production of Carbody Mock-up | 15/01/2019 | 15/04/2019 | 15/01/2019 | 26/04/2019 | 0 | TK_Complete | 94810358 | 74 | 94810358_74
A171880 | TT_Task | HP1a for Trainset #001 DM1 | 09/10/2019 | 13/03/2020 | 09/10/2019 | 09/10/2019 | 0 | TK_Complete | 94810358 | 343 | 94810358_343
A171890 | TT_Task | Painting for Trainset #001 DM1 | 10/10/2019 | 16/03/2020 | 10/10/2019 | 15/11/2019 | 0 | TK_Complete | 94810358 | 344 | 94810358_344
A171900 | TT_Task | HP1b for Trainset #001 DM1 | 18/11/2019 | 22/04/2020 | 18/11/2019 | 21/11/2019 | 0 | TK_Complete | 94810358 | 343 | 94810358_343
A171910 | TT_Task | Retrofit Carbody for Trainset #001 DM1 | 23/08/2019 | 28/01/2020 | 23/08/2019 | 08/10/2019 | 0 | TK_Complete | 94810358 | 345 | 94810358_345
A78990 | TT_Task | Carbody Manufacturing for Trainset #001 DM1 | 22/05/2019 | 25/10/2019 | 22/05/2019 | 22/08/2019 | 0 | TK_Complete | 94810358 | 346 | 94810358_346
A171950 | TT_Task | HP1a for Trainset #001 DM2 | 29/10/2019 | 02/04/2020 | 29/10/2019 | 29/10/2019 | 0 | TK_Complete | 94810358 | 343 | 94810358_343
A172000 | TT_Task | Painting for Trainset #001 DM2 | 30/10/2019 | 03/04/2020 | 30/10/2019 | 05/12/2019 | 0 | TK_Complete | 94810358 | 344 | 94810358_344
A172010 | TT_Task | HP1b for Trainset #001 DM2 | 01/01/2020 | 05/06/2020 | 12/12/2019 | 12/12/2019 | 0 | TK_Complete | 94810358 | 343 | 94810358_343
A172020 | TT_Task | Retrofit Carbody for Trainset #001 DM2 | 30/08/2019 | 04/02/2020 | 30/08/2019 | 28/10/2019 | 0 | TK_Complete | 94810358 | 345 | 94810358_345
A78980 | TT_Task | Carbody Manufacturing for Trainset #001 DM2 | 29/05/2019 | 01/11/2019 | 29/05/2019 | 29/08/2019 | 0 | TK_Complete | 94810358 | 346 | 94810358_346
A171990 | TT_Task | HP1a for Trainset #001 T | 29/10/2019 | 02/04/2020 | 29/10/2019 | 29/10/2019 | 0 | TK_Complete | 94810358 | 347 | 94810358_347
A172030 | TT_Task | Painting for Trainset #001 T | 05/11/2019 | 09/04/2020 | 29/10/2019 | 12/12/2019 | 0 | TK_Complete | 94810358 | 348 | 94810358_348
A172040 | TT_Task | HP1b for Trainset #001 T | 12/12/2019 | 18/05/2020 | 12/12/2019 | 18/12/2019 | 0 | TK_Complete | 94810358 | 347 | 94810358_347
A172050 | TT_Task | Retrofit Carbody for Trainset #001 T | 06/09/2019 | 11/02/2020 | 06/09/2019 | 28/10/2019 | 0 | TK_Complete | 94810358 | 345 | 94810358_345
A79000 | TT_Task | Carbody Manufacturing for Trainset #001 T | 05/06/2019 | 11/11/2019 | 05/06/2019 | 05/09/2019 | 0 | TK_Complete | 94810358 | 346 | 94810358_346
A184220 | TT_Task | Pre-Assembly for Trainset #001 DM1 | 01/01/2020 | 04/05/2020 | 25/12/2019 | 21/01/2020 | 0 | TK_Complete | 94810358 | 349 | 94810358_349
A61670 | TT_Task | Final Assembly for Trainset #001 DM1 | 09/01/2020 | 12/05/2020 | 08/01/2020 | 21/07/2020 | 0 | TK_Complete | 94810358 | 350 | 94810358_350
A61700 | TT_Task | Final Assembly for Trainset #001 DM2 | 13/01/2020 | 14/05/2020 | 13/01/2020 | 21/07/2020 | 0 | TK_Complete | 94810358 | 351 | 94810358_351
A184230 | TT_Task | Pre-Assembly for Trainset #001 T | 07/01/2020 | 06/05/2020 | 07/01/2020 | 24/01/2020 | 0 | TK_Complete | 94810358 | 349 | 94810358_349
A61740 | TT_Task | Final Assembly for Trainset #001 T | 15/01/2020 | 14/05/2020 | 15/01/2020 | 27/07/2020 | 0 | TK_Complete | 94810358 | 352 | 94810358_352
A187830 | TT_Task | Preparation of Transport to Sweden for Trainset #001 | 25/07/2022 | 01/08/2022 | nan | nan | 0 | TK_NotStart | 94810358 | 353 | 94810358_353
A74650 | TT_Task | Transport Carbody to Henningsdorf for Trainset #001 DM2 | 01/09/2020 | 25/10/2020 | 25/07/2020 | 07/09/2020 | 0 | TK_Complete | 94810358 | 354 | 94810358_354
A75990 | TT_Task | Transport Carbody to Henningsdorf for Trainset #001 DM1 | 01/09/2020 | 25/10/2020 | 25/07/2020 | 05/09/2020 | 0 | TK_Complete | 94810358 | 355 | 94810358_355
A76000 | TT_Task | Transport Carbody to Henningsdorf for Trainset #001 T | 01/09/2020 | 25/10/2020 | 30/07/2020 | 09/09/2020 | 0 | TK_Complete | 94810358 | 356 | 94810358_356
A79390 | TT_Task | Transport to Sweden for Trainset #001 (Depart from HEN in CW31/2022) | 01/08/2022 | 08/08/2022 | nan | nan | 0 | TK_NotStart | 94810358 | 357 | 94810358_357
A172100 | TT_Task | Fitout 2.8 for Trainset #001 DM1 | 17/11/2020 | 21/11/2020 | 23/10/2020 | 03/11/2020 | 0 | TK_Complete | 94810358 | 358 | 94810358_358
A172110 | TT_Task | Fitout 2.9 for Trainset #001 DM1 (4pt Leveling Test) | 09/11/2020 | 10/11/2020 | 05/11/2020 | 07/11/2020 | 0 | TK_Complete | 94810358 | 359 | 94810358_359
A172111 | TT_Task | Fitout 2.9 for Trainset #001 DM1 (PoB) | 13/11/2020 | 16/11/2020 | 12/11/2020 | 14/11/2020 | 0 | TK_Complete | 94810358 | 360 | 94810358_360
A172120 | TT_Task | Single Unit Testing for Trainset #001 DM1 | 18/11/2020 | 23/11/2020 | 18/11/2020 | 18/11/2020 | 0 | TK_Complete | 94810358 | 361 | 94810358_361
A184750 | TT_Task | AVM 0 Retrofit for Trainset #001 DM1 | 01/10/2020 | 07/10/2020 | 09/09/2020 | 18/09/2020 | 0 | TK_Complete | 94810358 | 362 | 94810358_362
A184910 | TT_Task | AVM 1 Retrofit for Trainset #001 DM1 | 29/10/2020 | 04/11/2020 | 09/10/2020 | 16/10/2020 | 0 | TK_Complete | 94810358 | 363 | 94810358_363
A185050 | TT_Task | Internal Inspection for Trainset #001 DM1 | 07/09/2020 | 07/09/2020 | 07/09/2020 | 07/09/2020 | 0 | TK_Complete | 94810358 | 364 | 94810358_364
A185060 | TT_Task | External Inspection for Trainset #001 DM1 | 07/09/2020 | 07/09/2020 | 08/09/2020 | 08/09/2020 | 0 | TK_Complete | 94810358 | 364 | 94810358_364
A185400 | TT_Task | QC Check and Rework for Trainset #001 DM1 (2nd Slot) | 18/11/2020 | 19/11/2020 | 16/11/2020 | 17/11/2020 | 0 | TK_Complete | 94810358 | 365 | 94810358_365
A185610 | TT_Task | QC Check for Trainset #001 DM1 (1st Slot) | 13/11/2020 | 16/11/2020 | 09/11/2020 | 12/11/2020 | 0 | TK_Complete | 94810358 | 365 | 94810358_365
A185940 | TT_Task | AVM 1 Retrofit of Missing Parts for Trainset #001 DM1 | 30/11/2020 | 04/12/2020 | 19/11/2020 | 26/11/2020 | 0 | TK_Complete | 94810358 | 366 | 94810358_366
A189040 | TT_Task | AVM1.3 Retrofit for Trainset #001 DM1 (2 Shifts w/ 5d/wk implemented from CW48 to end of 2021) | 03/12/2021 | 20/01/2022 | 03/11/2021 | nan | 0 | TK_Active | 94810358 | 367 | 94810358_367
A189050 | TT_Task | Single Car Testing for Trainset #001 DM1 (After Retrofit Slot 3 ; 4a) | 20/01/2022 | 21/01/2022 | nan | nan | 0 | TK_NotStart | 94810358 | 368 | 94810358_368
A189060 | TT_Task | QC Check and Rework for Trainset #001 DM1 (After Retrofit Slot 3 ; 4a) | 21/01/2022 | 24/01/2022 | nan | nan | 0 | TK_NotStart | 94810358 | 369 | 94810358_369
A189070 | TT_Task | Trainset #001 DM1 (4 points Leveling Test) (After Retrofit Slot 3) (NOT USED) | 03/12/2021 | 06/12/2021 | nan | nan | 16144 | TK_NotStart | 94810358 | 370 | 94810358_370
A189080 | TT_Task | Trainset #001 DM1 (PoB) (After Retrofit Slot 3 ; 4a) | 24/01/2022 | 25/01/2022 | nan | nan | 0 | TK_NotStart | 94810358 | 371 | 94810358_371
A189090 | TT_Task | QC Check and Rework for Trainset #001 DM1 (After Retrofit Slot 3 ; 4a) | 25/01/2022 | 26/01/2022 | nan | nan | 0 | TK_NotStart | 94810358 | 369 | 94810358_369
A189290 | TT_Task | Cab Dismount for Trainset #001 DM1 | 03/11/2021 | 08/11/2021 | 18/10/2021 | 21/10/2021 | 0 | TK_Complete | 94810358 | 372 | 94810358_372
A189300 | TT_Task | Sand Blasting ; Re-painting for Trainset #001 DM1 | 03/11/2021 | 06/11/2021 | 22/10/2021 | 01/11/2021 | 0 | TK_Complete | 94810358 | 373 | 94810358_373
A189410 | TT_Task | AVM1.4a Retrofit for Trainset #001 DM1 (1 Shift w/ 5d/wk planned) | 06/01/2022 | 16/02/2022 | nan | nan | 0 | TK_NotStart | 94810358 | 374 | 94810358_374
A36750 | TT_Task | Tempering of CBY for Trainset #001 DM1 | 07/09/2020 | 07/09/2020 | 06/09/2020 | 06/09/2020 | 0 | TK_Complete | 94810358 | 375 | 94810358_375
A43810 | TT_Task | Fitout 2.7 for Trainset #001 DM1 | 01/10/2020 | 06/10/2020 | 18/09/2020 | 02/11/2020 | 0 | TK_Complete | 94810358 | 358 | 94810358_358
A172130 | TT_Task | Tempering of CBY for Trainset #001 DM2 | 07/09/2020 | 08/09/2020 | 07/09/2020 | 07/09/2020 | 0 | TK_Complete | 94810358 | 376 | 94810358_376
A172150 | TT_Task | Fitout 2.8 for Trainset #001 DM2 | 06/11/2020 | 11/11/2020 | 26/10/2020 | 12/11/2020 | 0 | TK_Complete | 94810358 | 358 | 94810358_358
A172160 | TT_Task | Fitout 2.9 for Trainset #001 DM2 (4 points Leveling Test) | 16/11/2020 | 17/11/2020 | 12/11/2020 | 16/11/2020 | 0 | TK_Complete | 94810358 | 359 | 94810358_359
A172170 | TT_Task | AVM 1 Retrofit of Missing Parts for Trainset #001 DM2 | 03/12/2020 | 08/12/2020 | 24/11/2020 | 26/11/2020 | 0 | TK_Complete | 94810358 | 366 | 94810358_366
A184940 | TT_Task | AVM 0 Retrofit for Trainset #001 DM2 | 01/10/2020 | 07/10/2020 | 09/09/2020 | 23/09/2020 | 0 | TK_Complete | 94810358 | 362 | 94810358_362
A184950 | TT_Task | AVM 1 Retrofit for Trainset #001 DM2 | 04/11/2020 | 10/11/2020 | 17/10/2020 | 23/10/2020 | 0 | TK_Complete | 94810358 | 363 | 94810358_363
A185040 | TT_Task | Internal Inspection for Trainset #001 DM2 | 01/09/2020 | 01/09/2020 | 07/09/2020 | 07/09/2020 | 0 | TK_Complete | 94810358 | 364 | 94810358_364
A185410 | TT_Task | QC Check and Rework for Trainset #001 DM2 | 01/12/2020 | 03/12/2020 | 20/11/2020 | 23/11/2020 | 0 | TK_Complete | 94810358 | 377 | 94810358_377
A185950 | TT_Task | Profile Test Drive for Trainset #001 DM2 | 30/11/2020 | 30/11/2020 | 19/11/2020 | 19/11/2020 | 0 | TK_Complete | 94810358 | 378 | 94810358_378
A186040 | TT_Task | Fitout 2.9 for Trainset #001 DM2 (PoB) | 16/11/2020 | 17/11/2020 | 17/11/2020 | 18/11/2020 | 0 | TK_Complete | 94810358 | 360 | 94810358_360
A189100 | TT_Task | AVM1.3 Retrofit for Trainset #001 DM2 (2 Shifts w/ 5d/wk implemented from CW48 to end of 2021) | 02/12/2021 | 19/01/2022 | 10/11/2021 | nan | 0 | TK_Active | 94810358 | 367 | 94810358_367
A189110 | TT_Task | Single Car Testing for Trainset #001 DM2 (After Retrofit Slot 3 ; 4a) | 19/01/2022 | 20/01/2022 | nan | nan | 0 | TK_NotStart | 94810358 | 368 | 94810358_368
A189120 | TT_Task | QC Check and Rework for Trainset #001 DM2 (After Retrofit Slot 3 ; 4a) | 20/01/2022 | 21/01/2022 | nan | nan | 0 | TK_NotStart | 94810358 | 379 | 94810358_379
A189130 | TT_Task | Trainset #001 DM2 (4 points Leveling Test) (After Retrofit Slot 3) (NOT USED) | 03/12/2021 | 06/12/2021 | nan | nan | 16144 | TK_NotStart | 94810358 | 370 | 94810358_370
A189140 | TT_Task | Trainset #001 DM2 (PoB) (After Retrofit Slot 3 ; 4a) | 21/01/2022 | 24/01/2022 | nan | nan | 0 | TK_NotStart | 94810358 | 371 | 94810358_371
A189150 | TT_Task | QC Check and Rework for Trainset #001 DM2 (After Retrofit Slot 3 ; 4a) | 24/01/2022 | 25/01/2022 | nan | nan | 0 | TK_NotStart | 94810358 | 379 | 94810358_379
A189310 | TT_Task | Cab Dismount for Trainset #001 DM2 | 03/11/2021 | 08/11/2021 | 22/10/2021 | 26/10/2021 | 0 | TK_Complete | 94810358 | 372 | 94810358_372
A189320 | TT_Task | Sand Blasting ; Re-painting for Trainset #001 DM2 | 03/11/2021 | 06/11/2021 | 29/10/2021 | 07/11/2021 | 0 | TK_Complete | 94810358 | 373 | 94810358_373
A189420 | TT_Task | AVM1.4a Retrofit for Trainset #001 DM2 (1 Shift w/ 5d/wk planned) | 05/01/2022 | 15/02/2022 | nan | nan | 0 | TK_NotStart | 94810358 | 374 | 94810358_374
A43820 | TT_Task | Fitout 2.7 for Trainset #001 DM2 | 01/10/2020 | 06/10/2020 | 23/09/2020 | 12/11/2020 | 0 | TK_Complete | 94810358 | 358 | 94810358_358
A172180 | TT_Task | Tempering of CBY for Trainset #001 T | 01/10/2020 | 01/10/2020 | 09/09/2020 | 09/09/2020 | 0 | TK_Complete | 94810358 | 380 | 94810358_380
A172200 | TT_Task | Fitout 2.8 for Trainset #001 T | 02/11/2020 | 05/11/2020 | 19/10/2020 | 09/11/2020 | 0 | TK_Complete | 94810358 | 381 | 94810358_381
A172210 | TT_Task | Fitout 2.9 for Trainset #001 T (4 points Leveling Test) | 30/11/2020 | 01/12/2020 | 19/11/2020 | 19/11/2020 | 0 | TK_Complete | 94810358 | 382 | 94810358_382
A172220 | TT_Task | Profile Test Drive for Trainset #001 T | 30/11/2020 | 30/11/2020 | 25/11/2020 | 25/11/2020 | 0 | TK_Complete | 94810358 | 378 | 94810358_378
A184740 | TT_Task | AVM1 Retrofit for Trainset #001 T | 02/11/2020 | 06/11/2020 | 26/10/2020 | 30/10/2020 | 0 | TK_Complete | 94810358 | 383 | 94810358_383
A185000 | TT_Task | AVM 0 Retrofit for Trainset #001 T | 06/10/2020 | 12/10/2020 | 12/09/2020 | 23/09/2020 | 0 | TK_Complete | 94810358 | 384 | 94810358_384
A185020 | TT_Task | Internal Inspection for Trainset #001 T | 02/10/2020 | 02/10/2020 | 10/09/2020 | 10/09/2020 | 0 | TK_Complete | 94810358 | 385 | 94810358_385
A185030 | TT_Task | External Inspection for Trainset #001 T | 05/10/2020 | 05/10/2020 | 11/09/2020 | 11/09/2020 | 0 | TK_Complete | 94810358 | 385 | 94810358_385
A185420 | TT_Task | QC Check and Rework for Trainset #001 T | 02/12/2020 | 03/12/2020 | 23/11/2020 | 24/11/2020 | 0 | TK_Complete | 94810358 | 386 | 94810358_386
A186080 | TT_Task | Fitout 2.9 for Trainset #001 T (PoB) | 30/11/2020 | 01/12/2020 | 20/11/2020 | 20/11/2020 | 0 | TK_Complete | 94810358 | 387 | 94810358_387
A186090 | TT_Task | AVM 1 Retrofit of Missing Parts for Trainset #001 T | 02/11/2020 | 02/11/2020 | 26/11/2020 | 26/11/2020 | 0 | TK_Complete | 94810358 | 366 | 94810358_366
A189160 | TT_Task | AVM1.3 Retrofit for Trainset #001 T (2 Shifts w/ 5d/wk implemented from CW48 to end of 2021) | 26/11/2021 | 13/01/2022 | 16/11/2021 | nan | 0 | TK_Active | 94810358 | 367 | 94810358_367
A189170 | TT_Task | Single Car Testing for Trainset #001 T (After Retrofit Slot 3 ; 4a) | 17/01/2022 | 18/01/2022 | nan | nan | 0 | TK_NotStart | 94810358 | 388 | 94810358_388
A189180 | TT_Task | QC Check and Rework incl. Pressure Tightness Test for Trainset #001 T (After Retrofit Slot 3 ; 4a) | 18/01/2022 | 19/01/2022 | nan | nan | 0 | TK_NotStart | 94810358 | 389 | 94810358_389
A189190 | TT_Task | Trainset #001 T (4 points Leveling Test) (After Retrofit Slot 3) (NOT USED) | 03/12/2021 | 06/12/2021 | nan | nan | 16144 | TK_NotStart | 94810358 | 390 | 94810358_390
A189200 | TT_Task | Trainset #001 T (PoB) (After Retrofit Slot 3 ; 4a) | 20/01/2022 | 21/01/2022 | nan | nan | 0 | TK_NotStart | 94810358 | 391 | 94810358_391
A189210 | TT_Task | QC Check and Rework for Trainset #001 T (After Retrofit Slot 3 ; 4a) | 21/01/2022 | 24/01/2022 | nan | nan | 0 | TK_NotStart | 94810358 | 392 | 94810358_392
A189340 | TT_Task | Re-painting for Trainset #001 T | 26/11/2021 | 29/11/2021 | 09/11/2021 | 14/11/2021 | 0 | TK_Complete | 94810358 | 348 | 94810358_348
A189430 | TT_Task | AVM1.4a Retrofit for Trainset #001 T (1 Shift w/ 5d/wk planned) | 03/01/2022 | 11/02/2022 | nan | nan | 0 | TK_NotStart | 94810358 | 374 | 94810358_374
A43870 | TT_Task | Fitout 2.7 for Trainset #001 T | 06/11/2020 | 11/11/2020 | 24/10/2020 | 18/11/2020 | 0 | TK_Complete | 94810358 | 381 | 94810358_381
A185600 | TT_Task | Profile Test Drive for Trainset #001 | 01/12/2020 | 18/01/2021 | 01/12/2020 | 01/12/2020 | 0 | TK_Complete | 94810358 | 378 | 94810358_378
A186670 | TT_Task | AVM 1.1 Retrofit for Trainset #001 | 01/12/2020 | 08/01/2021 | 08/12/2020 | 29/01/2021 | 0 | TK_Complete | 94810358 | 383 | 94810358_383
A189220 | TT_Task | AVM1.3 Retrofit and De-coupling for Trainset #001 | 03/11/2021 | 08/12/2021 | 07/10/2021 | 07/10/2021 | 0 | TK_Complete | 94810358 | 393 | 94810358_393
A189230 | TT_Task | Train Completion for Trainset #001 (After Retrofit Slot 3 ; 4a) | 26/01/2022 | 21/02/2022 | nan | nan | 0 | TK_NotStart | 94810358 | 394 | 94810358_394
A189240 | TT_Task | QC Check and Rework for Trainset #001 (After Retrofit Slot 3 ; 4a) | 28/01/2022 | 04/03/2022 | nan | nan | 8 | TK_NotStart | 94810358 | 392 | 94810358_392
A189470 | TT_Task | Installation Supervision Prior to Transport to Sweden for Trainset #001 | 11/07/2022 | 15/08/2022 | nan | nan | 0 | TK_NotStart | 94810358 | 395 | 94810358_395
A189850 | TT_Task | AVM1.4b Retrofit for Trainset #001 | 02/05/2022 | 10/06/2022 | nan | nan | 0 | TK_NotStart | 94810358 | 383 | 94810358_383
A36900 | TT_Task | Train Completion for Trainset #001 | 30/11/2020 | 06/01/2021 | 27/11/2020 | 30/11/2020 | 0 | TK_Complete | 94810358 | 396 | 94810358_396
A40810 | TT_Task | Commissioning for Trainset #001 (Suspended to carry on AVM1.1 Retrofit) | 18/12/2020 | 02/03/2021 | 01/12/2020 | 07/12/2020 | 0 | TK_Complete | 94810358 | 397 | 94810358_397
A190150 | TT_Task | ATLAS Retrofit for Trainset #001 (8 wks in Sweden) (NOT USED) | 16/10/2023 | 20/11/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 398 | 94810358_398
A190160 | TT_Task | DIS Re-commissioning for Trainset #001 (3 wks in Sweden) (NOT USED) | 11/12/2023 | 26/02/2024 | nan | nan | 2976 | TK_NotStart | 94810358 | 399 | 94810358_399
A184970 | TT_Task | HP2 for Trainset #001 DM1 | 19/11/2020 | 20/11/2020 | 17/11/2020 | 17/11/2020 | 0 | TK_Complete | 94810358 | 400 | 94810358_400
A184990 | TT_Task | HP2 for Trainset #001 DM2 | 03/12/2020 | 03/12/2020 | 23/11/2020 | 23/11/2020 | 0 | TK_Complete | 94810358 | 400 | 94810358_400
A185010 | TT_Task | HP2 for Trainset #001 T | 03/12/2020 | 04/12/2020 | 24/11/2020 | 24/11/2020 | 0 | TK_Complete | 94810358 | 401 | 94810358_401
A186890 | TT_Task | QC Internal Check for Trainset #001 | 20/06/2022 | 18/11/2022 | nan | nan | 0 | TK_NotStart | 94810358 | 402 | 94810358_402
A187000 | TT_Task | HP4 for Trainset #001 | 04/07/2022 | 05/07/2022 | nan | nan | 0 | TK_NotStart | 94810358 | 403 | 94810358_403
A189350 | TT_Task | Re-work for Trainset #001 | 27/06/2022 | 25/11/2022 | nan | nan | 0 | TK_NotStart | 94810358 | 404 | 94810358_404
A11800 | TT_Task | Preliminary Takeover Inspection incl. HP5 for Trainset #001 | 18/09/2023 | 06/10/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 405 | 94810358_405
A12160 | TT_Task | Final Takeover Inspection for Trainset #001 | 17/09/2025 | 14/10/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 406 | 94810358_406
A185890 | TT_Task | 20000km Trial Operation for Trainset #001 (5 wks w/ J4 MT Approval EBICab) | 10/07/2023 | 14/08/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 407 | 94810358_407
A186470 | TT_Task | Pre- trial operation Batch #1 for Trainset #001 (9 wks and Close Track/ Night Time w/ J2 MT Approval EBICab) | 27/02/2023 | 12/05/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 408 | 94810358_408
A189910 | TT_Task | Pre- trial operation Batch #2 for Trainset #001 (5 wks w/ J4 MT Approval EBICab) | 01/05/2023 | 14/07/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 408 | 94810358_408
A61800 | TT_Task | Final Assembly for Trainset #002 DM1 | 02/03/2020 | 08/07/2020 | 03/02/2020 | 17/08/2020 | 0 | TK_Complete | 94810358 | 350 | 94810358_350
A180260 | TT_Task | Final Assembly for Trainset #002 DM2 | 09/03/2020 | 15/07/2020 | 10/02/2020 | 24/08/2020 | 0 | TK_Complete | 94810358 | 351 | 94810358_351
A180270 | TT_Task | Final Assembly for Trainset #002 T | 02/03/2020 | 08/07/2020 | 17/02/2020 | 31/08/2020 | 0 | TK_Complete | 94810358 | 352 | 94810358_352
A181570 | TT_Task | Transport Carbody to Henningsdorf for Trainset #002 T | 01/10/2020 | 25/11/2020 | 02/09/2020 | 15/10/2020 | 0 | TK_Complete | 94810358 | 356 | 94810358_356
A181580 | TT_Task | Transport Carbody to Henningsdorf for Trainset #002 DM2 | 01/09/2020 | 26/10/2020 | 26/08/2020 | 06/11/2020 | 0 | TK_Complete | 94810358 | 354 | 94810358_354
A186430 | TT_Task | Transport from RTA Vienna to Germany (HEN or BAU) for Trainset #002 | 31/01/2022 | 07/02/2022 | nan | nan | 0 | TK_NotStart | 94810358 | 409 | 94810358_409
A187340 | TT_Task | Transport from HEN to Minden for Trainset #002 | 03/09/2021 | 10/09/2021 | 09/08/2021 | 09/08/2021 | 0 | TK_Complete | 94810358 | 410 | 94810358_410
A187840 | TT_Task | Preparation of Transport to Sweden for Trainset #002 | 29/08/2022 | 05/09/2022 | nan | nan | 0 | TK_NotStart | 94810358 | 353 | 94810358_353
A187880 | TT_Task | Preparation of Transport from HEN to Minden for Trainset #002 | 27/08/2021 | 03/09/2021 | 26/07/2021 | 04/08/2021 | 0 | TK_Complete | 94810358 | 410 | 94810358_410
A76010 | TT_Task | Transport Carbody to Henningsdorf for Trainset #002 DM1 | 01/09/2020 | 26/10/2020 | 19/08/2020 | 28/09/2020 | 0 | TK_Complete | 94810358 | 355 | 94810358_355
A79400 | TT_Task | Transport to Sweden for Trainset #002 (Depart from HEN in CW36/2022) | 05/09/2022 | 12/09/2022 | nan | nan | 0 | TK_NotStart | 94810358 | 357 | 94810358_357
A172830 | TT_Task | Fitout 2.8 for Trainset #002 DM1 | 13/11/2020 | 18/11/2020 | 10/11/2020 | 01/12/2020 | 0 | TK_Complete | 94810358 | 411 | 94810358_411
A172840 | TT_Task | Fitout 2.9 for Trainset #002 DM1 (4 points Leveling Test) | 17/12/2020 | 18/12/2020 | 04/12/2020 | 04/12/2020 | 0 | TK_Complete | 94810358 | 359 | 94810358_359
A172850 | TT_Task | Single Car Testing for Trainset #002 DM1 | 08/01/2021 | 13/01/2021 | 21/12/2020 | 23/12/2020 | 0 | TK_Complete | 94810358 | 412 | 94810358_412
A184790 | TT_Task | AVM 0 Retrofit for Trainset #002 DM1 | 01/10/2020 | 07/10/2020 | 29/09/2020 | 09/11/2020 | 0 | TK_Complete | 94810358 | 362 | 94810358_362
A185070 | TT_Task | AVM1 Retrofit for Trainset #002 DM1 | 03/12/2020 | 09/12/2020 | 02/12/2020 | 14/12/2020 | 0 | TK_Complete | 94810358 | 363 | 94810358_363
A185430 | TT_Task | QC Check and Rework for Trainset #002 DM1 | 22/12/2020 | 23/12/2020 | 16/12/2020 | 17/12/2020 | 0 | TK_Complete | 94810358 | 377 | 94810358_377
A186100 | TT_Task | Fitout 2.9 for Trainset #002 DM1 (PoB) | 18/12/2020 | 21/12/2020 | 15/12/2020 | 15/12/2020 | 0 | TK_Complete | 94810358 | 360 | 94810358_360
A186750 | TT_Task | Car Paint Damage Repair (MET Repair Solution) for Trainset #002 DM1 | 08/02/2021 | 12/02/2021 | 08/02/2021 | 09/02/2021 | 0 | TK_Complete | 94810358 | 413 | 94810358_413
A189680 | TT_Task | AVM1.3 ; 1.4 Retrofit for Trainset #002 DM1 (1 Shift w/ 5d/wk planned) | 08/02/2022 | 14/02/2022 | nan | nan | 0 | TK_NotStart | 94810358 | 374 | 94810358_374
A189690 | TT_Task | Single Car Testing for Trainset #002 DM1 (After Retrofit Slot 4) | 28/03/2022 | 29/03/2022 | nan | nan | 0 | TK_NotStart | 94810358 | 368 | 94810358_368
A189700 | TT_Task | QC Check and Rework for Trainset #002 DM1 (After Retrofit Slot 4) | 29/03/2022 | 30/03/2022 | nan | nan | 0 | TK_NotStart | 94810358 | 369 | 94810358_369
A189710 | TT_Task | Trainset #002 DM1 (PoB) (After Retrofit Slot 4) | 30/03/2022 | 31/03/2022 | nan | nan | 0 | TK_NotStart | 94810358 | 371 | 94810358_371
A189720 | TT_Task | QC Check and Rework for Trainset #002 DM1 (After Retrofit Slot 4) | 31/03/2022 | 01/04/2022 | nan | nan | 0 | TK_NotStart | 94810358 | 369 | 94810358_369
A44840 | TT_Task | Tempering of CBY for Trainset #002 DM1 | 01/10/2020 | 01/10/2020 | 28/09/2020 | 28/09/2020 | 0 | TK_Complete | 94810358 | 375 | 94810358_375
A44930 | TT_Task | Fitout 2.7 for Trainset #002 DM1 | 10/11/2020 | 14/11/2020 | 04/11/2020 | 09/11/2020 | 0 | TK_Complete | 94810358 | 414 | 94810358_414
A172860 | TT_Task | Tempering of CBY for Trainset #002 DM2 | 19/11/2020 | 19/11/2020 | 16/11/2020 | 16/11/2020 | 0 | TK_Complete | 94810358 | 376 | 94810358_376
A172870 | TT_Task | Fitout 2.8 for Trainset #002 DM2 | 01/12/2020 | 04/12/2020 | 26/11/2020 | 02/12/2020 | 0 | TK_Complete | 94810358 | 415 | 94810358_415
A172880 | TT_Task | Fitout 2.9 for Trainset #002 DM2 (4 points Leveling Test) | 18/12/2020 | 21/12/2020 | 17/12/2020 | 17/12/2020 | 0 | TK_Complete | 94810358 | 359 | 94810358_359
A172890 | TT_Task | Single Car Testing for Trainset #002 DM2 | 13/01/2021 | 18/01/2021 | 28/12/2020 | 30/12/2020 | 0 | TK_Complete | 94810358 | 416 | 94810358_416
A185090 | TT_Task | AVM 0 Retrofit for Trainset #002 DM2 | 19/11/2020 | 25/11/2020 | 16/11/2020 | 20/11/2020 | 0 | TK_Complete | 94810358 | 362 | 94810358_362
A185100 | TT_Task | AVM1 Retrofit for Trainset #002 DM2 | 18/12/2020 | 28/12/2020 | 03/12/2020 | 16/12/2020 | 0 | TK_Complete | 94810358 | 363 | 94810358_363
A185450 | TT_Task | QC Check and Rework for Trainset #002 DM2 | 08/01/2021 | 11/01/2021 | 21/12/2020 | 22/12/2020 | 0 | TK_Complete | 94810358 | 377 | 94810358_377
A186130 | TT_Task | Fitout 2.9 for Trainset #002 DM2 (PoB) | 07/01/2021 | 08/01/2021 | 18/12/2020 | 18/12/2020 | 0 | TK_Complete | 94810358 | 360 | 94810358_360
A189730 | TT_Task | AVM1.3 ; 1.4 Retrofit for Trainset #002 DM2 (1 Shift w/ 5d/wk planned) | 09/02/2022 | 15/02/2022 | nan | nan | 0 | TK_NotStart | 94810358 | 374 | 94810358_374
A189740 | TT_Task | Single Car Testing for Trainset #002 DM2 (After Retrofit Slot 4) | 25/03/2022 | 28/03/2022 | nan | nan | 0 | TK_NotStart | 94810358 | 368 | 94810358_368
A189750 | TT_Task | QC Check and Rework for Trainset #002 DM2 (After Retrofit Slot 4) | 28/03/2022 | 29/03/2022 | nan | nan | 0 | TK_NotStart | 94810358 | 379 | 94810358_379
A189760 | TT_Task | Trainset #002 DM2 (PoB) (After Retrofit Slot 4) | 29/03/2022 | 30/03/2022 | nan | nan | 0 | TK_NotStart | 94810358 | 371 | 94810358_371
A189770 | TT_Task | QC Check and Rework for Trainset #002 DM2 (After Retrofit Slot 4) | 30/03/2022 | 31/03/2022 | nan | nan | 0 | TK_NotStart | 94810358 | 379 | 94810358_379
A44940 | TT_Task | Fitout 2.7 for Trainset #002 DM2 | 19/11/2020 | 24/11/2020 | 16/11/2020 | 26/11/2020 | 0 | TK_Complete | 94810358 | 417 | 94810358_417
A172900 | TT_Task | Tempering of CBY for Trainset #002 T | 19/11/2020 | 19/11/2020 | 16/11/2020 | 17/11/2020 | 0 | TK_Complete | 94810358 | 380 | 94810358_380
A172910 | TT_Task | Fitout 2.8 for Trainset #002 T | 03/12/2020 | 08/12/2020 | 01/12/2020 | 04/12/2020 | 0 | TK_Complete | 94810358 | 381 | 94810358_381
A172920 | TT_Task | Fitout 2.9 for Trainset #002 T (4 points Leveling Test) | 07/01/2021 | 08/01/2021 | 18/12/2020 | 22/12/2020 | 0 | TK_Complete | 94810358 | 382 | 94810358_382
A172930 | TT_Task | Single Car Testing for Trainset #002 T | 12/01/2021 | 15/01/2021 | 06/01/2021 | 08/01/2021 | 0 | TK_Complete | 94810358 | 418 | 94810358_418
A184780 | TT_Task | AVM1 Retrofit for Trainset #002 T | 18/12/2020 | 28/12/2020 | 07/12/2020 | 17/12/2020 | 0 | TK_Complete | 94810358 | 383 | 94810358_383
A185120 | TT_Task | AVM 0 Retrofit for Trainset #002 T | 19/11/2020 | 25/11/2020 | 17/11/2020 | 26/11/2020 | 0 | TK_Complete | 94810358 | 384 | 94810358_384
A185440 | TT_Task | QC Check and Rework for Trainset #002 T | 15/01/2021 | 18/01/2021 | 30/12/2020 | 04/01/2021 | 0 | TK_Complete | 94810358 | 386 | 94810358_386
A186160 | TT_Task | Fitout 2.9 for Trainset #002 T (PoB) | 12/01/2021 | 13/01/2021 | 23/12/2020 | 23/12/2020 | 0 | TK_Complete | 94810358 | 387 | 94810358_387
A189780 | TT_Task | AVM1.3 ; 1.4 Retrofit for Trainset #002 T (1 Shift w/ 5d/wk planned) | 14/02/2022 | 18/02/2022 | nan | nan | 0 | TK_NotStart | 94810358 | 374 | 94810358_374
A189790 | TT_Task | Single Car Testing for Trainset #002 T (After Retrofit Slot 4) | 21/03/2022 | 22/03/2022 | nan | nan | 0 | TK_NotStart | 94810358 | 388 | 94810358_388
A189800 | TT_Task | QC Check and Rework incl. Pressure Tightness Test for Trainset #002 T (After Retrofit Slot 4) | 22/03/2022 | 23/03/2022 | nan | nan | 0 | TK_NotStart | 94810358 | 389 | 94810358_389
A189810 | TT_Task | Trainset #002 T (PoB) (After Retrofit Slot 4) | 25/03/2022 | 28/03/2022 | nan | nan | 0 | TK_NotStart | 94810358 | 391 | 94810358_391
A189820 | TT_Task | QC Check and Rework for Trainset #002 T (After Retrofit Slot 4) | 28/03/2022 | 29/03/2022 | nan | nan | 0 | TK_NotStart | 94810358 | 392 | 94810358_392
A44950 | TT_Task | Fitout 2.7 for Trainset #002 T | 01/12/2020 | 04/12/2020 | 26/11/2020 | 30/11/2020 | 0 | TK_Complete | 94810358 | 419 | 94810358_419
A186760 | TT_Task | AVM 1.1 Retrofit of Missing Parts for Trainset #002 | 15/01/2021 | 28/01/2021 | 11/01/2021 | 12/02/2021 | 0 | TK_Complete | 94810358 | 366 | 94810358_366
A189260 | TT_Task | AVM1.3 ; 1.4 Retrofit and De-coupling for Trainset #002 | 07/02/2022 | 14/03/2022 | nan | nan | 0 | TK_NotStart | 94810358 | 393 | 94810358_393
A189490 | TT_Task | TCR G06.11.10 Retrofit incl. Re-commissioning for Trainset #002 | 18/07/2022 | 29/08/2022 | nan | nan | 0 | TK_NotStart | 94810358 | 420 | 94810358_420
A189500 | TT_Task | Installation Supervision Prior to Transport to Sweden for Trainset #002 | 22/08/2022 | 26/09/2022 | nan | nan | 0 | TK_NotStart | 94810358 | 395 | 94810358_395
A189830 | TT_Task | Train Completion for Trainset #002 (After Retrofit Slot 4) | 01/04/2022 | 03/05/2022 | nan | nan | 0 | TK_NotStart | 94810358 | 394 | 94810358_394
A189840 | TT_Task | QC Check and Rework for Trainset #002 (After Retrofit Slot 4) | 05/04/2022 | 16/05/2022 | nan | nan | 40 | TK_NotStart | 94810358 | 392 | 94810358_392
A44900 | TT_Task | Train Completion for Trainset #002 | 07/01/2021 | 02/02/2021 | 28/12/2020 | 29/12/2020 | 0 | TK_Complete | 94810358 | 396 | 94810358_396
A189920 | TT_Task | ATLAS Retrofit for Trainset #002 (8 wks in Sweden) | 20/03/2023 | 24/04/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 398 | 94810358_398
A189930 | TT_Task | DIS Re-commissioning for Trainset #002 (3 wks in Sweden) | 15/05/2023 | 12/07/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 399 | 94810358_399
A185080 | TT_Task | HP2 for Trainset #002 DM1 | 07/01/2021 | 07/01/2021 | 18/12/2020 | 18/12/2020 | 0 | TK_Complete | 94810358 | 421 | 94810358_421
A185110 | TT_Task | HP2 for Trainset #002 DM2 | 12/01/2021 | 12/01/2021 | 23/12/2020 | 23/12/2020 | 0 | TK_Complete | 94810358 | 422 | 94810358_422
A185130 | TT_Task | HP2 for Trainset #002 T (By trainset: Full Vehicle w/o Physical Inspection) | 25/03/2021 | 25/03/2021 | 09/02/2021 | 09/02/2021 | 0 | TK_Complete | 94810358 | 423 | 94810358_423
A186900 | TT_Task | QC Internal Check for Trainset #002 | 01/08/2022 | 14/10/2022 | nan | nan | 0 | TK_NotStart | 94810358 | 402 | 94810358_402
A187010 | TT_Task | HP4 for Trainset #002 | 15/08/2022 | 16/08/2022 | nan | nan | 0 | TK_NotStart | 94810358 | 403 | 94810358_403
A189360 | TT_Task | Re-work for Trainset #002 | 08/08/2022 | 21/10/2022 | nan | nan | 0 | TK_NotStart | 94810358 | 404 | 94810358_404
A11810 | TT_Task | Preliminary Takeover Inspection incl. HP5 for Trainset #002 (Assume Inspection in parallel w/ J5 Application) | 20/06/2024 | 17/07/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 424 | 94810358_424
A12170 | TT_Task | Final Takeover Inspection for Trainset #002 | 17/09/2025 | 14/10/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 406 | 94810358_406
A185900 | TT_Task | 20000km Trial Operation for Trainset #002 (3 months w/ J2 Approval ATLAS) - tb clarified | 23/10/2023 | 27/11/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 425 | 94810358_425
A186480 | TT_Task | Pre- trial operation for Trainset #002 (15 wks and Close Track/ Night Time w/ J2 Approval ATLAS) | 05/06/2023 | 08/09/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 426 | 94810358_426
A61920 | TT_Task | Final Assembly for Trainset #003 DM1 | 02/03/2020 | 29/06/2020 | 24/02/2020 | 07/09/2020 | 0 | TK_Complete | 94810358 | 350 | 94810358_350
A180290 | TT_Task | Final Assembly for Trainset #003 DM2 | 09/03/2020 | 15/07/2020 | 09/03/2020 | 14/09/2020 | 0 | TK_Complete | 94810358 | 351 | 94810358_351
A180300 | TT_Task | Final Assembly for Trainset #003 T | 01/09/2020 | 07/01/2021 | 08/06/2020 | 21/09/2020 | 0 | TK_Complete | 94810358 | 352 | 94810358_352
A181590 | TT_Task | Transport Carbody to Henningsdorf for Trainset #003 T | 01/10/2020 | 25/11/2020 | 23/09/2020 | 04/12/2020 | 0 | TK_Complete | 94810358 | 356 | 94810358_356
A181600 | TT_Task | Transport Carbody to Henningsdorf for Trainset #003 DM2 | 01/10/2020 | 25/11/2020 | 16/09/2020 | 26/11/2020 | 0 | TK_Complete | 94810358 | 354 | 94810358_354
A187850 | TT_Task | Prepararion of Transport to Sweden for Trainset #003 | 27/06/2022 | 04/07/2022 | nan | nan | 0 | TK_NotStart | 94810358 | 427 | 94810358_427
A76040 | TT_Task | Transport Carbody to Henningsdorf for Trainset #003 DM1 | 01/10/2020 | 25/11/2020 | 16/09/2020 | 20/11/2020 | 0 | TK_Complete | 94810358 | 355 | 94810358_355
A79410 | TT_Task | Transport to Sweden for Trainset #003 (Depart from HEN in CW27/2022) | 04/07/2022 | 11/07/2022 | nan | nan | 0 | TK_NotStart | 94810358 | 357 | 94810358_357
A173000 | TT_Task | Fitout 2.8 for Trainset #003 DM1 | 07/01/2021 | 12/01/2021 | 04/01/2021 | 14/01/2021 | 0 | TK_Complete | 94810358 | 411 | 94810358_411
A173010 | TT_Task | Fitout 2.9 for Trainset #003 DM1 (4 points Leveling Test) | 21/01/2021 | 22/01/2021 | 15/01/2021 | 18/01/2021 | 0 | TK_Complete | 94810358 | 359 | 94810358_359
A184770 | TT_Task | AVM 0 Retrofit for Trainset #003 DM1 | 03/12/2020 | 09/12/2020 | 23/11/2020 | 30/11/2020 | 0 | TK_Complete | 94810358 | 362 | 94810358_362
A185460 | TT_Task | QC Check and Rework for Trainset #003 DM1 | 28/01/2021 | 29/01/2021 | 21/01/2021 | 22/01/2021 | 0 | TK_Complete | 94810358 | 377 | 94810358_377
A186200 | TT_Task | Fitout 2.9 for Trainset #003 DM1 (PoB) | 21/01/2021 | 22/01/2021 | 19/01/2021 | 20/01/2021 | 0 | TK_Complete | 94810358 | 360 | 94810358_360
A187080 | TT_Task | AVM1 Retrofit for Trainset #003 DM1 (NOT USED) | 25/03/2021 | 29/03/2021 | 22/02/2021 | 22/02/2021 | 0 | TK_Complete | 94810358 | 363 | 94810358_363
A187680 | TT_Task | AVM1.2b Incl. AVM1.3 Retrofit for Trainset #003 DM1 | 22/07/2021 | 09/11/2021 | 21/07/2021 | 25/10/2021 | 0 | TK_Complete | 94810358 | 428 | 94810358_428
A187690 | TT_Task | Trainset #003 DM1 (4 points Leveling Test) (After Retrofit Slot 3) (NOT USED) | 03/12/2021 | 06/12/2021 | nan | nan | 16152 | TK_NotStart | 94810358 | 370 | 94810358_370
A187700 | TT_Task | Trainset #003 DM1 (PoB) (After Retrofit Slot 3) | 03/11/2021 | 04/11/2021 | 01/11/2021 | 01/11/2021 | 0 | TK_Complete | 94810358 | 371 | 94810358_371
A187710 | TT_Task | QC Check and Rework for Trainset #003 DM1 (After Retrofit Slot 3) | 04/11/2021 | 05/11/2021 | 02/11/2021 | 16/11/2021 | 0 | TK_Complete | 94810358 | 369 | 94810358_369
A187910 | TT_Task | Single Car Testing for Trainset #003 DM1 (After Retrofit Slot 3) | 03/11/2021 | 04/11/2021 | 26/10/2021 | 28/10/2021 | 0 | TK_Complete | 94810358 | 368 | 94810358_368
A187920 | TT_Task | QC Check and Rework for Trainset #003 DM1 (After Retrofit Slot 3) | 03/11/2021 | 04/11/2021 | 29/10/2021 | 29/10/2021 | 0 | TK_Complete | 94810358 | 369 | 94810358_369
A45010 | TT_Task | Tempering of CBY for Trainset #003 DM1 | 03/12/2020 | 03/12/2020 | 20/11/2020 | 20/11/2020 | 0 | TK_Complete | 94810358 | 375 | 94810358_375
A45100 | TT_Task | Fitout 2.7 for Trainset #003 DM1 | 03/12/2020 | 08/12/2020 | 01/12/2020 | 30/12/2020 | 0 | TK_Complete | 94810358 | 414 | 94810358_414
A173030 | TT_Task | Tempering of CBY for Trainset #003 DM2 | 18/12/2020 | 18/12/2020 | 15/12/2020 | 15/12/2020 | 0 | TK_Complete | 94810358 | 376 | 94810358_376
A173040 | TT_Task | Fitout 2.8 for Trainset #003 DM2 | 08/02/2021 | 11/02/2021 | 29/01/2021 | 01/02/2021 | 0 | TK_Complete | 94810358 | 415 | 94810358_415
A173050 | TT_Task | Fitout 2.9 for Trainset #003 DM2 (4 points Leveling Test) | 10/02/2021 | 11/02/2021 | 02/02/2021 | 04/02/2021 | 0 | TK_Complete | 94810358 | 359 | 94810358_359
A185160 | TT_Task | AVM 0 Retrofit for Trainset #003 DM2 | 21/12/2020 | 29/12/2020 | 16/12/2020 | 30/12/2020 | 0 | TK_Complete | 94810358 | 362 | 94810358_362
A185470 | TT_Task | QC Check and Rework for Trainset #003 DM2 | 12/02/2021 | 15/02/2021 | 08/02/2021 | 09/02/2021 | 0 | TK_Complete | 94810358 | 377 | 94810358_377
A186210 | TT_Task | Fitout 2.9 for Trainset #003 DM2 (PoB) | 12/02/2021 | 15/02/2021 | 05/02/2021 | 05/02/2021 | 0 | TK_Complete | 94810358 | 360 | 94810358_360
A187100 | TT_Task | AVM1 Retrofit for Trainset #003 DM2 | 25/03/2021 | 29/03/2021 | 12/02/2021 | 22/02/2021 | 0 | TK_Complete | 94810358 | 363 | 94810358_363
A187720 | TT_Task | AVM1.2b Incl. AVM1.3 Retrofit for Trainset #003 DM2 | 03/11/2021 | 28/02/2022 | 22/07/2021 | 21/10/2021 | 0 | TK_Complete | 94810358 | 428 | 94810358_428
A187730 | TT_Task | Trainset #003 DM2 (4 points Leveling Test) (After Retrofit Slot 3) (NOT USED) | 03/12/2021 | 06/12/2021 | nan | nan | 16128 | TK_NotStart | 94810358 | 370 | 94810358_370
A187740 | TT_Task | Trainset #003 DM2 (PoB) (After Retrofit Slot 3) | 03/11/2021 | 04/11/2021 | 28/10/2021 | 28/10/2021 | 0 | TK_Complete | 94810358 | 371 | 94810358_371
A187750 | TT_Task | QC Check and Rework for Trainset #003 DM2 (After Retrofit Slot 3) | 03/11/2021 | 04/11/2021 | 29/10/2021 | 15/11/2021 | 0 | TK_Complete | 94810358 | 379 | 94810358_379
A187930 | TT_Task | Single Car Testing for Trainset #003 DM2 (After Retrofit Slot 3) | 03/11/2021 | 04/11/2021 | 22/10/2021 | 26/10/2021 | 0 | TK_Complete | 94810358 | 368 | 94810358_368
A187940 | TT_Task | QC Check and Rework for Trainset #003 DM2 (After Retrofit Slot 3) | 04/11/2021 | 05/11/2021 | 27/10/2021 | 27/10/2021 | 0 | TK_Complete | 94810358 | 379 | 94810358_379
A45110 | TT_Task | Fitout 2.7 for Trainset #003 DM2 | 07/01/2021 | 12/01/2021 | 04/01/2021 | 28/01/2021 | 0 | TK_Complete | 94810358 | 417 | 94810358_417
A173070 | TT_Task | Tempering of CBY for Trainset #003 T | 07/01/2021 | 07/01/2021 | 23/12/2020 | 23/12/2020 | 0 | TK_Complete | 94810358 | 380 | 94810358_380
A173080 | TT_Task | Fitout 2.8 for Trainset #003 T | 28/01/2021 | 02/02/2021 | 22/01/2021 | 28/01/2021 | 0 | TK_Complete | 94810358 | 381 | 94810358_381
A173090 | TT_Task | Fitout 2.9 for Trainset #003 T (4 points Leveling Test) | 08/02/2021 | 09/02/2021 | 29/01/2021 | 01/02/2021 | 0 | TK_Complete | 94810358 | 382 | 94810358_382
A184760 | TT_Task | AVM 0 Retrofit for Trainset #003 T | 08/01/2021 | 14/01/2021 | 28/12/2020 | 18/01/2021 | 0 | TK_Complete | 94810358 | 384 | 94810358_384
A185480 | TT_Task | QC Check and Rework for Trainset #003 T | 08/02/2021 | 09/02/2021 | 03/02/2021 | 04/02/2021 | 0 | TK_Complete | 94810358 | 386 | 94810358_386
A186220 | TT_Task | Fitout 2.9 for Trainset #003 T (PoB) | 10/02/2021 | 11/02/2021 | 02/02/2021 | 02/02/2021 | 0 | TK_Complete | 94810358 | 387 | 94810358_387
A187760 | TT_Task | AVM1.2b Incl. AVM1.3 Retrofit for Trainset #003 T | 22/07/2021 | 09/11/2021 | 20/07/2021 | 22/10/2021 | 0 | TK_Complete | 94810358 | 428 | 94810358_428
A187770 | TT_Task | Trainset #003 T (4 points Leveling Test) (After Retrofit Slot 3) (NOT USED) | 03/12/2021 | 06/12/2021 | nan | nan | 16128 | TK_NotStart | 94810358 | 390 | 94810358_390
A187780 | TT_Task | Trainset #003 T (PoB) (After Retrofit Slot 3) | 09/11/2021 | 10/11/2021 | 02/11/2021 | 02/11/2021 | 0 | TK_Complete | 94810358 | 391 | 94810358_391
A187790 | TT_Task | QC Check and Rework for Trainset #003 T (After Retrofit Slot 3) | 26/11/2021 | 29/11/2021 | 11/11/2021 | 17/11/2021 | 0 | TK_Complete | 94810358 | 392 | 94810358_392
A187950 | TT_Task | Single Car Testing for Trainset #003 T (After Retrofit Slot 3) | 03/11/2021 | 04/11/2021 | 25/10/2021 | 27/10/2021 | 0 | TK_Complete | 94810358 | 388 | 94810358_388
A187960 | TT_Task | QC Check and Rework for Trainset #003 T (After Retrofit Slot 3) | 08/11/2021 | 09/11/2021 | 28/10/2021 | 01/11/2021 | 0 | TK_Complete | 94810358 | 392 | 94810358_392
A189370 | TT_Task | Rework for Trainset #003 T (After Retrofit Slot 3) | 26/11/2021 | 29/11/2021 | 03/11/2021 | 10/11/2021 | 0 | TK_Complete | 94810358 | 429 | 94810358_429
A45120 | TT_Task | Fitout 2.7 for Trainset #003 T | 21/01/2021 | 26/01/2021 | 18/01/2021 | 21/01/2021 | 0 | TK_Complete | 94810358 | 419 | 94810358_419
A185620 | TT_Task | AVM1.1 Retrofit for Trainset #003 (NOT USED) | 05/05/2021 | 15/06/2021 | 09/04/2021 | 09/04/2021 | 0 | TK_Complete | 94810358 | 383 | 94810358_383
A187190 | TT_Task | AVM1 Retrofit for Trainset #003 | 30/03/2021 | 09/04/2021 | 26/02/2021 | 04/03/2021 | 0 | TK_Complete | 94810358 | 383 | 94810358_383
A187240 | TT_Task | AVM1.2 Retrofit and De-coupling for Trainset #003 | 21/05/2021 | 29/06/2021 | 17/05/2021 | 19/07/2021 | 0 | TK_Complete | 94810358 | 393 | 94810358_393
A187270 | TT_Task | QC Check and Rework for Trainset #003 (After Retrofit Slot 3) | 26/11/2021 | 10/01/2022 | 24/11/2021 | 26/11/2021 | 0 | TK_Complete | 94810358 | 392 | 94810358_392
A187800 | TT_Task | Train Completion for Trainset #003 (After Retrofit Slot 3) | 01/12/2021 | 02/12/2021 | 23/11/2021 | 23/11/2021 | 0 | TK_Complete | 94810358 | 394 | 94810358_394
A189510 | TT_Task | Installation Supervision Prior to Transport to Sweden for Trainset #003 | 13/06/2022 | 18/07/2022 | nan | nan | 0 | TK_NotStart | 94810358 | 395 | 94810358_395
A45070 | TT_Task | Train Completion for Trainset #003 (01) | 30/03/2021 | 29/04/2021 | 05/03/2021 | 09/03/2021 | 0 | TK_Complete | 94810358 | 396 | 94810358_396
A45090 | TT_Task | Retrofit Re-testing for Trainset #003 (NOT USED) | 16/04/2021 | 22/04/2021 | 09/04/2021 | 09/04/2021 | 0 | TK_Complete | 94810358 | 429 | 94810358_429
A173060 | TT_Task | TT Single Car Testing (ENG Clearance/Swa Coeff.) for Trainset #003 DM2 | 25/03/2021 | 30/03/2021 | 23/02/2021 | 25/02/2021 | 0 | TK_Complete | 94810358 | 430 | 94810358_430
A186010 | TT_Task | TT Single Car Testing (ENG Clearance/ Cable length/ Swa Coeff.) for Trainset #003 DM1 | 28/01/2021 | 17/02/2021 | 25/01/2021 | 25/02/2021 | 0 | TK_Complete | 94810358 | 430 | 94810358_430
A186020 | TT_Task | TT Single Car Testing (ENG Clearance/ Cable length/ Swa Coeff.) for Trainset #003 T | 08/02/2021 | 26/02/2021 | 05/02/2021 | 25/02/2021 | 0 | TK_Complete | 94810358 | 430 | 94810358_430
A186380 | TT_Task | TT Testing - Safety against De-railment for Trainset #003 | 25/03/2021 | 15/04/2021 | 11/03/2021 | 09/04/2021 | 0 | TK_Complete | 94810358 | 431 | 94810358_431
A190170 | TT_Task | ATLAS Retrofit for Trainset #003 (8 wks in Sweden) (NOT USED) | 13/11/2023 | 18/12/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 398 | 94810358_398
A190180 | TT_Task | DIS Re-commissioning for Trainset #003 (3 wks in Sweden) (NOT USED) | 25/01/2024 | 25/03/2024 | nan | nan | 2816 | TK_NotStart | 94810358 | 399 | 94810358_399
A185150 | TT_Task | HP2 for Trainset #003 DM1 (By CBY Level w/ 1d Physical Inspection) and 1d Re-work | 09/12/2021 | 09/12/2021 | 22/11/2021 | 23/11/2021 | 0 | TK_Complete | 94810358 | 432 | 94810358_432
A185180 | TT_Task | HP2 for Trainset #003 DM2 (By CBY Level w/ 1d Physical Inspection) and 2d Re-work | 26/11/2021 | 26/11/2021 | 16/11/2021 | 17/11/2021 | 0 | TK_Complete | 94810358 | 432 | 94810358_432
A185190 | TT_Task | HP2 for Trainset #003 T (By CBY Level w/ 2d Physical Inspection) and 1d Re-work | 29/11/2021 | 29/11/2021 | 18/11/2021 | 19/11/2021 | 0 | TK_Complete | 94810358 | 432 | 94810358_432
A186910 | TT_Task | QC Internal Check for Trainset #003 | 02/05/2022 | 15/07/2022 | nan | nan | 0 | TK_NotStart | 94810358 | 402 | 94810358_402
A187020 | TT_Task | HP4 for Trainset #003 | 30/05/2022 | 31/05/2022 | nan | nan | 0 | TK_NotStart | 94810358 | 403 | 94810358_403
A189380 | TT_Task | Re-work for Trainset #003 | 09/05/2022 | 22/07/2022 | nan | nan | 0 | TK_NotStart | 94810358 | 404 | 94810358_404
A11820 | TT_Task | Preliminary Takeover Inspection incl. HP5 for Trainset #003 | 16/10/2023 | 10/11/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 405 | 94810358_405
A12180 | TT_Task | Final Takeover Inspection for Trainset #003 | 17/09/2025 | 14/10/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 406 | 94810358_406
A185910 | TT_Task | 20000km Trial Operation for Trainset #003 (5 wks w/ J4 MT Approval EBICab) | 11/09/2023 | 16/10/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 407 | 94810358_407
A186490 | TT_Task | Pre- trial operation for Trainset #003 (14 wks w/ J4 MT Approval EBICab) | 01/05/2023 | 20/10/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 408 | 94810358_408
A62040 | TT_Task | Final Assembly for Trainset #004 DM1 | 08/09/2020 | 15/01/2021 | 30/04/2020 | 21/09/2020 | 0 | TK_Complete | 94810358 | 350 | 94810358_350
A180320 | TT_Task | Final Assembly for Trainset #004 DM2 | 15/09/2020 | 21/01/2021 | 10/06/2020 | 28/09/2020 | 0 | TK_Complete | 94810358 | 351 | 94810358_351
A180330 | TT_Task | Final Assembly for Trainset #004 T | 22/09/2020 | 28/01/2021 | 18/06/2020 | 26/10/2020 | 0 | TK_Complete | 94810358 | 352 | 94810358_352
A181610 | TT_Task | Transport Carbody to Henningsdorf for Trainset #004 T | 29/10/2020 | 23/12/2020 | 28/10/2020 | 22/01/2021 | 0 | TK_Complete | 94810358 | 356 | 94810358_356
A181620 | TT_Task | Transport Carbody to Henningsdorf for Trainset #004 DM2 | 01/10/2020 | 25/11/2020 | 30/09/2020 | 08/01/2021 | 0 | TK_Complete | 94810358 | 354 | 94810358_354
A187860 | TT_Task | Preparation of Transport to Sweden for Trainset #004 (Assume SS+0d w/ Installation Supervision) | 14/03/2022 | 21/03/2022 | nan | nan | 0 | TK_NotStart | 94810358 | 353 | 94810358_353
A189660 | TT_Task | Preparation of Transport from Sweden to Germany for Trainset #004 | 10/10/2022 | 17/10/2022 | nan | nan | 0 | TK_NotStart | 94810358 | 433 | 94810358_433
A189670 | TT_Task | Transport from Sweden to Germany for Trainset #004 | 24/10/2022 | 31/10/2022 | nan | nan | 256 | TK_NotStart | 94810358 | 433 | 94810358_433
A190050 | TT_Task | Preparation of Transport from Germany to Sweden for Trainset #004 (After ATLAS Retrofit) | 01/06/2023 | 08/06/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 433 | 94810358_433
A190060 | TT_Task | Transport from Germany to Sweden for Trainset #004 (After ATLAS Retrofit) | 08/06/2023 | 15/06/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 433 | 94810358_433
A76070 | TT_Task | Transport Carbody to Henningsdorf for Trainset #004 DM1 | 01/10/2020 | 25/11/2020 | 30/09/2020 | 18/12/2020 | 0 | TK_Complete | 94810358 | 355 | 94810358_355
A79420 | TT_Task | Transport to Sweden for Trainset #004 (Depart from HEN in CW12/2022) | 21/03/2022 | 28/03/2022 | nan | nan | 0 | TK_NotStart | 94810358 | 357 | 94810358_357
A173170 | TT_Task | Fitout 2.8 for Trainset #004 DM1 | 08/02/2021 | 11/02/2021 | 02/02/2021 | 09/02/2021 | 0 | TK_Complete | 94810358 | 411 | 94810358_411
A173180 | TT_Task | Fitout 2.9 for Trainset #004 DM1 (4 points Leveling Test) | 12/02/2021 | 15/02/2021 | 10/02/2021 | 12/02/2021 | 0 | TK_Complete | 94810358 | 359 | 94810358_359
A173190 | TT_Task | Single Car Testing for Trainset #004 DM1 (NOT USED) | 01/04/2021 | 09/04/2021 | 01/03/2021 | 01/03/2021 | 0 | TK_Complete | 94810358 | 412 | 94810358_412
A185210 | TT_Task | AVM 0 Retrofit for Trainset #004 DM1 | 21/01/2021 | 25/01/2021 | 19/01/2021 | 25/01/2021 | 0 | TK_Complete | 94810358 | 362 | 94810358_362
A185490 | TT_Task | QC Check and Rework for Trainset #004 DM1 | 09/04/2021 | 12/04/2021 | 02/03/2021 | 03/03/2021 | 0 | TK_Complete | 94810358 | 377 | 94810358_377
A186260 | TT_Task | Fitout 2.9 for Trainset #004 DM1 (PoB) | 25/03/2021 | 29/03/2021 | 15/02/2021 | 16/02/2021 | 0 | TK_Complete | 94810358 | 360 | 94810358_360
A186690 | TT_Task | AVM1 Retrofit for Trainset #004 DM1 | 29/03/2021 | 30/03/2021 | 17/02/2021 | 01/03/2021 | 0 | TK_Complete | 94810358 | 363 | 94810358_363
A188830 | TT_Task | AVM1.3 Retrofit for Trainset #004 DM1 | 03/11/2021 | 10/12/2021 | 15/09/2021 | 22/11/2021 | 0 | TK_Complete | 94810358 | 363 | 94810358_363
A188840 | TT_Task | Single Car Testing for Trainset #004 DM1 (After Retrofit Slot 3) | 26/11/2021 | 29/11/2021 | 23/11/2021 | 23/11/2021 | 0 | TK_Complete | 94810358 | 368 | 94810358_368
A188850 | TT_Task | QC Check and Rework for Trainset #004 DM1 (After Retrofit Slot 3) | 01/12/2021 | 02/12/2021 | 24/11/2021 | 24/11/2021 | 0 | TK_Complete | 94810358 | 369 | 94810358_369
A188860 | TT_Task | Trainset #004 DM1 (4 points Leveling Test) (After Retrofit Slot 3) (NOT USED) | 03/12/2021 | 06/12/2021 | nan | nan | 16128 | TK_NotStart | 94810358 | 370 | 94810358_370
A188870 | TT_Task | Trainset #004 DM1 (PoB) (After Retrofit Slot 3) | 02/12/2021 | 03/12/2021 | 25/11/2021 | 25/11/2021 | 0 | TK_Complete | 94810358 | 371 | 94810358_371
A188880 | TT_Task | QC Check and Rework for Trainset #004 DM1 (After Retrofit Slot 3) | 03/12/2021 | 06/12/2021 | 26/11/2021 | 26/11/2021 | 0 | TK_Complete | 94810358 | 369 | 94810358_369
A45180 | TT_Task | Tempering of CBY for Trainset #004 DM1 | 21/01/2021 | 21/01/2021 | 18/01/2021 | 18/01/2021 | 0 | TK_Complete | 94810358 | 375 | 94810358_375
A45270 | TT_Task | Fitout 2.7 for Trainset #004 DM1 | 28/01/2021 | 02/02/2021 | 26/01/2021 | 01/02/2021 | 0 | TK_Complete | 94810358 | 414 | 94810358_414
A173200 | TT_Task | Tempering of CBY for Trainset #004 DM2 | 28/01/2021 | 28/01/2021 | 27/01/2021 | 27/01/2021 | 0 | TK_Complete | 94810358 | 376 | 94810358_376
A173210 | TT_Task | Fitout 2.8 for Trainset #004 DM2 | 25/03/2021 | 01/04/2021 | 15/02/2021 | 22/02/2021 | 0 | TK_Complete | 94810358 | 415 | 94810358_415
A173220 | TT_Task | Fitout 2.9 for Trainset #004 DM2 (4 points Leveling Test) | 25/03/2021 | 29/03/2021 | 23/02/2021 | 26/02/2021 | 0 | TK_Complete | 94810358 | 359 | 94810358_359
A173230 | TT_Task | Single Car Testing for Trainset #004 DM2 (NOT USED) | 16/04/2021 | 21/04/2021 | 04/03/2021 | 04/03/2021 | 0 | TK_Complete | 94810358 | 416 | 94810358_416
A185230 | TT_Task | AVM 0 Retrofit for Trainset #004 DM2 | 08/02/2021 | 10/02/2021 | 05/02/2021 | 09/02/2021 | 0 | TK_Complete | 94810358 | 362 | 94810358_362
A185500 | TT_Task | QC Check and Rework for Trainset #004 DM2 | 21/04/2021 | 22/04/2021 | 05/03/2021 | 08/03/2021 | 0 | TK_Complete | 94810358 | 377 | 94810358_377
A186270 | TT_Task | Fitout 2.9 for Trainset #004 DM2 (PoB) | 06/04/2021 | 08/04/2021 | 01/03/2021 | 02/03/2021 | 0 | TK_Complete | 94810358 | 360 | 94810358_360
A186700 | TT_Task | AVM1 Retrofit for Trainset #004 DM2 | 09/04/2021 | 12/04/2021 | 03/03/2021 | 04/03/2021 | 0 | TK_Complete | 94810358 | 363 | 94810358_363
A188890 | TT_Task | AVM1.3 Retrofit for Trainset #004 DM2 | 27/09/2021 | 08/11/2021 | 16/09/2021 | 22/11/2021 | 0 | TK_Complete | 94810358 | 363 | 94810358_363
A188900 | TT_Task | Single Car Testing for Trainset #004 DM2 (After Retrofit Slot 3) | 26/11/2021 | 29/11/2021 | 22/11/2021 | 22/11/2021 | 0 | TK_Complete | 94810358 | 368 | 94810358_368
A188910 | TT_Task | QC Check and Rework for Trainset #004 DM2 (After Retrofit Slot 3) | 01/12/2021 | 02/12/2021 | 23/11/2021 | 23/11/2021 | 0 | TK_Complete | 94810358 | 379 | 94810358_379
A188920 | TT_Task | Trainset #004 DM2 (4 points Leveling Test) (After Retrofit Slot 3) (NOT USED) | 03/12/2021 | 06/12/2021 | nan | nan | 16128 | TK_NotStart | 94810358 | 370 | 94810358_370
A188930 | TT_Task | Trainset #004 DM2 (PoB) (After Retrofit Slot 3) | 02/12/2021 | 03/12/2021 | 24/11/2021 | 24/11/2021 | 0 | TK_Complete | 94810358 | 371 | 94810358_371
A188940 | TT_Task | QC Check and Rework for Trainset #004 DM2 (After Retrofit Slot 3) | 03/12/2021 | 06/12/2021 | 25/11/2021 | 25/11/2021 | 0 | TK_Complete | 94810358 | 379 | 94810358_379
A45280 | TT_Task | Fitout 2.7 for Trainset #004 DM2 | 12/02/2021 | 17/02/2021 | 10/02/2021 | 12/02/2021 | 0 | TK_Complete | 94810358 | 417 | 94810358_417
A173240 | TT_Task | Tempering of CBY for Trainset #004 T | 08/02/2021 | 08/02/2021 | 22/01/2021 | 22/01/2021 | 0 | TK_Complete | 94810358 | 380 | 94810358_380
A173250 | TT_Task | Fitout 2.8 for Trainset #004 T | 12/02/2021 | 17/02/2021 | 11/02/2021 | 12/02/2021 | 0 | TK_Complete | 94810358 | 381 | 94810358_381
A173260 | TT_Task | Fitout 2.9 for Trainset #004 T (4 points Leveling Test) | 25/03/2021 | 29/03/2021 | 15/02/2021 | 17/02/2021 | 0 | TK_Complete | 94810358 | 382 | 94810358_382
A173270 | TT_Task | Single Car Testing for Trainset #004 T (NOT USED) | 13/04/2021 | 16/04/2021 | 03/03/2021 | 03/03/2021 | 0 | TK_Complete | 94810358 | 418 | 94810358_418
A185260 | TT_Task | AVM 0 Retrofit for Trainset #004 T | 08/02/2021 | 10/02/2021 | 22/01/2021 | 27/01/2021 | 0 | TK_Complete | 94810358 | 384 | 94810358_384
A185510 | TT_Task | QC Check and Rework for Trainset #004 T | 16/04/2021 | 19/04/2021 | 01/03/2021 | 02/03/2021 | 0 | TK_Complete | 94810358 | 386 | 94810358_386
A186280 | TT_Task | Fitout 2.9 for Trainset #004 T (PoB) | 30/03/2021 | 01/04/2021 | 18/02/2021 | 18/02/2021 | 0 | TK_Complete | 94810358 | 387 | 94810358_387
A186710 | TT_Task | AVM1 Retrofit for Trainset #004 T | 01/04/2021 | 06/04/2021 | 19/02/2021 | 03/03/2021 | 0 | TK_Complete | 94810358 | 383 | 94810358_383
A188950 | TT_Task | AVM1.3 Retrofit for Trainset #004 T | 27/09/2021 | 08/11/2021 | 17/09/2021 | 17/11/2021 | 0 | TK_Complete | 94810358 | 383 | 94810358_383
A188960 | TT_Task | Single Car Testing for Trainset #004 T (After Retrofit Slot 3) | 26/11/2021 | 29/11/2021 | 18/11/2021 | 22/11/2021 | 0 | TK_Complete | 94810358 | 388 | 94810358_388
A188970 | TT_Task | QC Check and Rework incl. Pressure Tightness Test for Trainset #004 T (After Retrofit Slot 3) | 26/11/2021 | 29/11/2021 | 23/11/2021 | 26/11/2021 | 0 | TK_Complete | 94810358 | 389 | 94810358_389
A188980 | TT_Task | Trainset #004 T (4 points Leveling Test) (After Retrofit Slot 3) (NOT USED) | 03/12/2021 | 06/12/2021 | nan | nan | 16128 | TK_NotStart | 94810358 | 390 | 94810358_390
A188990 | TT_Task | Trainset #004 T (PoB) (After Retrofit Slot 3) | 03/12/2021 | 06/12/2021 | 29/11/2021 | 29/11/2021 | 0 | TK_Complete | 94810358 | 391 | 94810358_391
A189000 | TT_Task | QC Check and Rework for Trainset #004 T (After Retrofit Slot 3) | 03/12/2021 | 07/12/2021 | 29/11/2021 | 30/11/2021 | 0 | TK_Complete | 94810358 | 392 | 94810358_392
A45290 | TT_Task | Fitout 2.7 for Trainset #004 T | 19/02/2021 | 24/02/2021 | 04/02/2021 | 09/02/2021 | 0 | TK_Complete | 94810358 | 419 | 94810358_419
A187120 | TT_Task | AVM1.1 Retrofit for Trainset #004 | 30/03/2021 | 10/05/2021 | 12/03/2021 | 29/03/2021 | 0 | TK_Complete | 94810358 | 383 | 94810358_383
A187250 | TT_Task | AVM1.2a Retrofit (TCR G05.40.01) for Trainset #004 | 28/05/2021 | 05/07/2021 | 03/05/2021 | 04/06/2021 | 0 | TK_Complete | 94810358 | 383 | 94810358_383
A187280 | TT_Task | BST - AT Site Investigation for Cab Bond for Trainset #004 | 22/04/2021 | 10/05/2021 | 06/04/2021 | 23/04/2021 | 0 | TK_Complete | 94810358 | 434 | 94810358_434
A187290 | TT_Task | PM Event for Cab Bond for Trainset #004 | 26/04/2021 | 28/05/2021 | 26/04/2021 | 26/04/2021 | 0 | TK_Complete | 94810358 | 435 | 94810358_435
A187300 | TT_Task | Preparation Work after PM Event regarding Cab Bond for Trainset #004 | 21/05/2021 | 22/06/2021 | 27/04/2021 | 30/04/2021 | 0 | TK_Complete | 94810358 | 435 | 94810358_435
A188810 | TT_Task | AVM1.2b Retrofit for Trainset #004 | 28/05/2021 | 11/06/2021 | 12/07/2021 | 27/07/2021 | 0 | TK_Complete | 94810358 | 383 | 94810358_383
A189010 | TT_Task | AVM1.3 Retrofit and De-coupling for Trainset #004 | 21/05/2021 | 25/05/2021 | 13/09/2021 | 14/09/2021 | 0 | TK_Complete | 94810358 | 393 | 94810358_393
A189020 | TT_Task | Train Completion for Trainset #004 (After Retrofit Slot 3) | 06/12/2021 | 10/01/2022 | 30/11/2021 | 01/12/2021 | 0 | TK_Complete | 94810358 | 394 | 94810358_394
A189030 | TT_Task | QC Check and Rework for Trainset #004 (After Retrofit Slot 3) | 08/12/2021 | 20/01/2022 | 02/12/2021 | 02/12/2021 | 0 | TK_Complete | 94810358 | 392 | 94810358_392
A189540 | TT_Task | Installation Supervision Prior to Transport to Sweden for Trainset #004 | 14/03/2022 | 18/04/2022 | nan | nan | 0 | TK_NotStart | 94810358 | 395 | 94810358_395
A45240 | TT_Task | Train Completion for Trainset #004 | 25/03/2021 | 27/04/2021 | 10/03/2021 | 11/03/2021 | 0 | TK_Complete | 94810358 | 396 | 94810358_396
ATL100212 | TT_Task | Material Delivery for ATLAS Retrofit for 1st and 2nd Vehicle (3 months acc. to Retrofit slot 3 Lesson Learnt) | 21/09/2022 | 26/01/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 436 | 94810358_436
ATL100213 | TT_Task | ATLAS Retrofit for Trainset #004 (10 wks in Germany) | 14/12/2022 | 02/05/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 398 | 94810358_398
ATL100214 | TT_Task | ROS Re-commissioning for Trainset #004 (5 wk in Germany) | 06/03/2023 | 18/07/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 437 | 94810358_437
ATL100215 | TT_Task | DIS Testing ; Commissioning for Trainset #004 (3 wks in Germany) | 14/04/2023 | 11/08/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 438 | 94810358_438
ATL100225 | TT_Task | DIS Odometry Tests for Trainset #004 | 15/06/2023 | 12/10/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 439 | 94810358_439
ATL100231 | TT_Task | DIS EMC Tests for Trainset #004 | 29/06/2023 | 26/10/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 440 | 94810358_440
ATL100232 | TT_Task | DIS ODO Test Report Preparation for Trainset #004 | 06/07/2023 | 02/11/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 441 | 94810358_441
ATL100236 | TT_Task | DIS ODO Tunning for Trainset #004 | 13/07/2023 | 09/11/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 442 | 94810358_442
ATL100237 | TT_Task | DIS Dynamic Functional site tests for Trainset #004 | 18/10/2023 | 22/02/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 443 | 94810358_443
ATL100238 | TT_Task | DIS ESC tests for Trainset #004 | 30/10/2023 | 05/03/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 440 | 94810358_440
ATL100239 | TT_Task | Train Functional Achitecture for Trainset #004 (2 wks) | 13/07/2023 | 09/11/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 444 | 94810358_444
A185220 | TT_Task | HP2 for Trainset #004 DM1 (By trainset w/ 3d Physical Inspection) and VT approved on 14.04.21 | 16/04/2021 | 16/04/2021 | 30/03/2021 | 01/04/2021 | 0 | TK_Complete | 94810358 | 445 | 94810358_445
A185240 | TT_Task | HP2 for Trainset #004 DM2 (By trainset w/ 3d Physical Inspection) and VT approved on 14.04.21 | 16/04/2021 | 16/04/2021 | 30/03/2021 | 01/04/2021 | 0 | TK_Complete | 94810358 | 445 | 94810358_445
A185250 | TT_Task | HP2 for Trainset #004 T (By trainset w/ 3d Physical Inspection) and VT approved on 14.04.21 | 16/04/2021 | 16/04/2021 | 30/03/2021 | 01/04/2021 | 0 | TK_Complete | 94810358 | 445 | 94810358_445
A186920 | TT_Task | QC Check and Rework for Trainset #004 (After ATLAS Retrofit) | 05/05/2023 | 08/05/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 446 | 94810358_446
A187030 | TT_Task | HP4 for Trainset #004 (After ATLAS Retrofit) | 24/05/2023 | 25/05/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 447 | 94810358_447
A189530 | TT_Task | AT ; VT Inspection for Trainset #004 (Strategy Change for HP4 prior to Transport to Sweden) | 07/03/2022 | 08/03/2022 | nan | nan | 0 | TK_NotStart | 94810358 | 448 | 94810358_448
A11830 | TT_Task | Preliminary Takeover Inspection incl. HP5 for Trainset #004 (Assume Insepection in parallel w/ J5 Application) | 20/06/2024 | 17/07/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 424 | 94810358_424
A12190 | TT_Task | Final Takeover Inspection for Trainset #004 | 17/09/2025 | 14/10/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 406 | 94810358_406
A185920 | TT_Task | 20000km Trial Operation for Trainset #004 (3 months w/ J2 Approval ATLAS) (TBC) | 25/01/2024 | 29/02/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 425 | 94810358_425
A186500 | TT_Task | Pre-trial Run Trainset #004 - Batch #01 (10 wks and Close Track/ Night Time w/ J2 Approval ATLAS) | 27/07/2023 | 06/12/2023 | nan | nan | 240 | TK_NotStart | 94810358 | 426 | 94810358_426
A190000 | TT_Task | Pre-trial Run Trainset #004 - Batch #02 (5 wks and Close Track/ Night Time w/ J2 Approval ATLAS) | 16/11/2023 | 27/03/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 426 | 94810358_426
A62160 | TT_Task | Final Assembly for Trainset #005 DM1 | 08/09/2020 | 08/01/2021 | 24/06/2020 | 07/12/2020 | 0 | TK_Complete | 94810358 | 350 | 94810358_350
A180350 | TT_Task | Final Assembly for Trainset #005 DM2 | 15/09/2020 | 21/01/2021 | 03/08/2020 | 14/12/2020 | 0 | TK_Complete | 94810358 | 351 | 94810358_351
A180360 | TT_Task | Final Assembly for Trainset #005 T | 22/09/2020 | 28/01/2021 | 03/08/2020 | 18/12/2020 | 0 | TK_Complete | 94810358 | 352 | 94810358_352
A181630 | TT_Task | Transport Carbody to Henningsdorf for Trainset #005 T | 07/01/2021 | 03/03/2021 | 23/12/2020 | 19/02/2021 | 0 | TK_Complete | 94810358 | 356 | 94810358_356
A181640 | TT_Task | Transport Carbody to Henningsdorf for Trainset #005 DM2 | 18/12/2020 | 11/02/2021 | 16/12/2020 | 17/02/2021 | 0 | TK_Complete | 94810358 | 354 | 94810358_354
A187870 | TT_Task | Preparation of Transport to Sweden for Trainset #005 | 19/09/2022 | 26/09/2022 | nan | nan | 0 | TK_NotStart | 94810358 | 353 | 94810358_353
A76100 | TT_Task | Transport Carbody to Henningsdorf for Trainset #005 DM1 | 18/12/2020 | 11/02/2021 | 09/12/2020 | 10/02/2021 | 0 | TK_Complete | 94810358 | 355 | 94810358_355
A79430 | TT_Task | Transport to Sweden for Trainset #005 (Depart from HEN in CW39/2022) | 26/09/2022 | 03/10/2022 | nan | nan | 0 | TK_NotStart | 94810358 | 357 | 94810358_357
A173340 | TT_Task | Fitout 2.8 for Trainset #005 DM1 | 01/04/2021 | 09/04/2021 | 23/02/2021 | 01/03/2021 | 0 | TK_Complete | 94810358 | 411 | 94810358_411
A173350 | TT_Task | Fitout 2.9 for Trainset #005 DM1 (4 points Leveling Test) | 12/04/2021 | 13/04/2021 | 02/03/2021 | 08/03/2021 | 0 | TK_Complete | 94810358 | 359 | 94810358_359
A173360 | TT_Task | Single Car Testing for Trainset #005 DM1 (NOT USED) | 21/04/2021 | 26/04/2021 | 11/03/2021 | 11/03/2021 | 0 | TK_Complete | 94810358 | 412 | 94810358_412
A185280 | TT_Task | AVM 0 Retrofit for Trainset #005 DM1 | 12/02/2021 | 16/02/2021 | 10/02/2021 | 12/02/2021 | 0 | TK_Complete | 94810358 | 362 | 94810358_362
A185520 | TT_Task | QC Check and Rework for Trainset #005 DM1 | 26/04/2021 | 27/04/2021 | 16/03/2021 | 19/03/2021 | 0 | TK_Complete | 94810358 | 377 | 94810358_377
A186320 | TT_Task | Fitout 2.9 for Trainset #005 DM1 (PoB) | 14/04/2021 | 15/04/2021 | 12/03/2021 | 15/03/2021 | 0 | TK_Complete | 94810358 | 360 | 94810358_360
A186720 | TT_Task | AVM1 Retrofit for Trainset #005 DM1 | 16/04/2021 | 19/04/2021 | 09/03/2021 | 11/03/2021 | 0 | TK_Complete | 94810358 | 363 | 94810358_363
A187210 | TT_Task | AVM1 Retrofit for Trainset #005 DM1 | 16/04/2021 | 19/04/2021 | 22/03/2021 | 23/03/2021 | 0 | TK_Complete | 94810358 | 363 | 94810358_363
A187980 | TT_Task | AVM1.3 Retrofit for Trainset #005 DM1 (2 Shifts w/ 5d/wk implemented from CW48 to end of 2021) | 03/12/2021 | 21/01/2022 | 29/11/2021 | nan | 0 | TK_Active | 94810358 | 367 | 94810358_367
A187990 | TT_Task | Single Car Testing for Trainset #005 DM1 (After Retrofit Slot 3 ; 4a) | 31/01/2022 | 01/02/2022 | nan | nan | 0 | TK_NotStart | 94810358 | 368 | 94810358_368
A188000 | TT_Task | QC Check and Rework for Trainset #005 DM1 (After Retrofit Slot 3 ; 4a) | 01/02/2022 | 02/02/2022 | nan | nan | 0 | TK_NotStart | 94810358 | 369 | 94810358_369
A188010 | TT_Task | Trainset #005 DM1 (4 points Leveling Test) (After Retrofit Slot 3) (NOT USED) | 03/12/2021 | 06/12/2021 | nan | nan | 16160 | TK_NotStart | 94810358 | 370 | 94810358_370
A188020 | TT_Task | Trainset #005 DM1 (PoB) (After Retrofit Slot 3 ; 4a) | 02/02/2022 | 03/02/2022 | nan | nan | 0 | TK_NotStart | 94810358 | 371 | 94810358_371
A188030 | TT_Task | QC Check and Rework for Trainset #005 DM1 (After Retrofit Slot 3 ; 4a) | 03/02/2022 | 04/02/2022 | nan | nan | 0 | TK_NotStart | 94810358 | 369 | 94810358_369
A189440 | TT_Task | AVM1.4a Retrofit for Trainset #005 DM1 (1 Shift w/ 5d/wk planned) | 20/01/2022 | 02/03/2022 | nan | nan | 0 | TK_NotStart | 94810358 | 374 | 94810358_374
A45350 | TT_Task | Tempering of CBY for Trainset #005 DM1 | 12/02/2021 | 12/02/2021 | 10/02/2021 | 10/02/2021 | 0 | TK_Complete | 94810358 | 375 | 94810358_375
A45440 | TT_Task | Fitout 2.7 for Trainset #005 DM1 | 25/03/2021 | 01/04/2021 | 15/02/2021 | 22/02/2021 | 0 | TK_Complete | 94810358 | 414 | 94810358_414
A173370 | TT_Task | Tempering of CBY for Trainset #005 DM2 | 25/03/2021 | 25/03/2021 | 16/02/2021 | 18/02/2021 | 0 | TK_Complete | 94810358 | 376 | 94810358_376
A173380 | TT_Task | Fitout 2.8 for Trainset #005 DM2 | 25/03/2021 | 01/04/2021 | 02/03/2021 | 12/03/2021 | 0 | TK_Complete | 94810358 | 415 | 94810358_415
A173390 | TT_Task | Fitout 2.9 for Trainset #005 DM2 (4 points Leveling Test) | 06/04/2021 | 08/04/2021 | 15/03/2021 | 19/03/2021 | 0 | TK_Complete | 94810358 | 359 | 94810358_359
A173400 | TT_Task | Single Car Testing for Trainset #005 DM2 (NOT USED) | 16/04/2021 | 21/04/2021 | 24/03/2021 | 24/03/2021 | 0 | TK_Complete | 94810358 | 416 | 94810358_416
A185310 | TT_Task | AVM 0 Retrofit for Trainset #005 DM2 | 25/03/2021 | 01/04/2021 | 19/02/2021 | 22/02/2021 | 0 | TK_Complete | 94810358 | 362 | 94810358_362
A185530 | TT_Task | QC Check and Rework for Trainset #005 DM2 | 30/03/2021 | 01/04/2021 | 29/03/2021 | 29/03/2021 | 0 | TK_Complete | 94810358 | 377 | 94810358_377
A186330 | TT_Task | Fitout 2.9 for Trainset #005 DM2 (PoB) | 25/03/2021 | 29/03/2021 | 25/03/2021 | 26/03/2021 | 0 | TK_Complete | 94810358 | 360 | 94810358_360
A186730 | TT_Task | AVM1 Retrofit for Trainset #005 DM2 | 13/04/2021 | 14/04/2021 | 22/03/2021 | 24/03/2021 | 0 | TK_Complete | 94810358 | 363 | 94810358_363
A187220 | TT_Task | AVM1 Retrofit for Trainset #005 DM2 | 01/04/2021 | 06/04/2021 | 30/03/2021 | 08/04/2021 | 0 | TK_Complete | 94810358 | 363 | 94810358_363
A188040 | TT_Task | AVM1.3 Retrofit for Trainset #005 DM2 (2 Shifts w/ 5d/wk implemented from CW48 to end of 2021) | 03/12/2021 | 21/01/2022 | 30/11/2021 | nan | 0 | TK_Active | 94810358 | 367 | 94810358_367
A188050 | TT_Task | Single Car Testing for Trainset #005 DM2 (After Retrofit Slot 3 ; 4a) | 28/01/2022 | 31/01/2022 | nan | nan | 0 | TK_NotStart | 94810358 | 368 | 94810358_368
A188060 | TT_Task | QC Check and Rework for Trainset #005 DM2 (After Retrofit Slot 3 ; 4a) | 31/01/2022 | 01/02/2022 | nan | nan | 0 | TK_NotStart | 94810358 | 379 | 94810358_379
A188070 | TT_Task | Trainset #005 DM2 (4 points Leveling Test) (After Retrofit Slot 3) (NOT USED) | 03/12/2021 | 06/12/2021 | nan | nan | 16160 | TK_NotStart | 94810358 | 370 | 94810358_370
A188080 | TT_Task | Trainset #005 DM2 (PoB) (After Retrofit Slot 3 ; 4a) | 01/02/2022 | 02/02/2022 | nan | nan | 0 | TK_NotStart | 94810358 | 371 | 94810358_371
A188090 | TT_Task | QC Check and Rework for Trainset #005 DM2 (After Retrofit Slot 3 ; 4a) | 02/02/2022 | 03/02/2022 | nan | nan | 0 | TK_NotStart | 94810358 | 379 | 94810358_379
A189450 | TT_Task | AVM1.4a Retrofit for Trainset #005 DM2 (1 Shift w/ 5d/wk planned) | 24/01/2022 | 04/03/2022 | nan | nan | 0 | TK_NotStart | 94810358 | 374 | 94810358_374
A45450 | TT_Task | Fitout 2.7 for Trainset #005 DM2 | 29/03/2021 | 08/04/2021 | 23/02/2021 | 01/03/2021 | 0 | TK_Complete | 94810358 | 417 | 94810358_417
A173410 | TT_Task | Tempering of CBY for Trainset #005 T | 25/03/2021 | 25/03/2021 | 24/02/2021 | 24/02/2021 | 0 | TK_Complete | 94810358 | 380 | 94810358_380
A173420 | TT_Task | Fitout 2.8 for Trainset #005 T | 25/03/2021 | 01/04/2021 | 15/03/2021 | 21/04/2021 | 0 | TK_Complete | 94810358 | 381 | 94810358_381
A173430 | TT_Task | Fitout 2.9 for Trainset #005 T (4 points Leveling Test) | 21/05/2021 | 25/05/2021 | 22/04/2021 | 23/04/2021 | 0 | TK_Complete | 94810358 | 382 | 94810358_382
A173440 | TT_Task | Single Car Testing for Trainset #005 T (NOT USED) | 27/05/2021 | 02/06/2021 | 27/04/2021 | 27/04/2021 | 0 | TK_Complete | 94810358 | 418 | 94810358_418
A185320 | TT_Task | AVM 0 Retrofit for Trainset #005 T | 25/03/2021 | 01/04/2021 | 25/02/2021 | 02/03/2021 | 0 | TK_Complete | 94810358 | 384 | 94810358_384
A185540 | TT_Task | QC Check and Rework for Trainset #005 T | 02/07/2021 | 05/07/2021 | 18/06/2021 | 18/06/2021 | 0 | TK_Complete | 94810358 | 386 | 94810358_386
A186340 | TT_Task | Fitout 2.9 for Trainset #005 T (PoB) | 26/05/2021 | 27/05/2021 | 26/04/2021 | 26/04/2021 | 0 | TK_Complete | 94810358 | 387 | 94810358_387
A186740 | TT_Task | AVM1 Retrofit for Trainset #005 T | 27/05/2021 | 28/05/2021 | 27/04/2021 | 27/04/2021 | 0 | TK_Complete | 94810358 | 383 | 94810358_383
A188100 | TT_Task | AVM1.3 Retrofit for Trainset #005 T (2 Shifts w/ 5d/wk implemented from CW48 to end of 2021) | 03/12/2021 | 21/01/2022 | 01/12/2021 | nan | 0 | TK_Active | 94810358 | 367 | 94810358_367
A188110 | TT_Task | Single Car Testing for Trainset #005 T (After Retrofit Slot 3 ; 4a) | 27/01/2022 | 28/01/2022 | nan | nan | 0 | TK_NotStart | 94810358 | 388 | 94810358_388
A188120 | TT_Task | QC Check and Rework for Trainset #005 T (After Retrofit Slot 3 ; 4a) | 28/01/2022 | 31/01/2022 | nan | nan | 0 | TK_NotStart | 94810358 | 392 | 94810358_392
A188130 | TT_Task | Trainset #005 T (4 points Leveling Test) (After Retrofit Slot 3) (NOT USED) | 03/12/2021 | 06/12/2021 | nan | nan | 16160 | TK_NotStart | 94810358 | 390 | 94810358_390
A188140 | TT_Task | Trainset #005 T (PoB) (After Retrofit Slot 3 ; 4a) | 31/01/2022 | 01/02/2022 | nan | nan | 0 | TK_NotStart | 94810358 | 391 | 94810358_391
A188150 | TT_Task | QC Check and Rework for Trainset #005 T (After Retrofit Slot 3 ; 4a) | 01/02/2022 | 02/02/2022 | nan | nan | 0 | TK_NotStart | 94810358 | 392 | 94810358_392
A189460 | TT_Task | AVM1.4a Retrofit for Trainset #005 T (1 Shift w/ 5d/wk planned) | 19/01/2022 | 01/03/2022 | nan | nan | 0 | TK_NotStart | 94810358 | 374 | 94810358_374
A45460 | TT_Task | Fitout 2.7 for Trainset #005 T | 30/03/2021 | 09/04/2021 | 02/03/2021 | 12/03/2021 | 0 | TK_Complete | 94810358 | 419 | 94810358_419
A187130 | TT_Task | AVM1.2a Retrofit for Trainset #005 | 21/05/2021 | 29/06/2021 | 10/05/2021 | 11/06/2021 | 0 | TK_Complete | 94810358 | 383 | 94810358_383
A187160 | TT_Task | AVM1.2b Retrofit for Trainset #005 | 25/06/2021 | 05/08/2021 | 16/06/2021 | 09/07/2021 | 0 | TK_Complete | 94810358 | 383 | 94810358_383
A187810 | TT_Task | Train Completion for Trainset #005 (After Retrofit Slot 3 ; 4a) | 14/02/2022 | 10/03/2022 | nan | nan | 0 | TK_NotStart | 94810358 | 394 | 94810358_394
A187820 | TT_Task | QC Check and Rework for Trainset #005 (After Retrofit Slot 3 ; 4a) | 16/02/2022 | 23/03/2022 | nan | nan | 0 | TK_NotStart | 94810358 | 392 | 94810358_392
A187970 | TT_Task | AVM1.3 Retrofit and De-coupling for Trainset #005 | 26/11/2021 | 10/01/2022 | 25/11/2021 | 25/11/2021 | 0 | TK_Complete | 94810358 | 393 | 94810358_393
A189550 | TT_Task | Installation Supervision Prior to Transport to Sweden for Trainset #005 | 12/09/2022 | 17/10/2022 | nan | nan | 0 | TK_NotStart | 94810358 | 395 | 94810358_395
A189560 | TT_Task | TCR G06.11.10 Retrofit incl. Re-commissioning for Trainset #005 (NOT USED) | 03/12/2021 | 20/01/2022 | nan | nan | 16080 | TK_NotStart | 94810358 | 420 | 94810358_420
A45410 | TT_Task | Train Completion for Trainset #005 (01) | 25/06/2021 | 23/07/2021 | 14/06/2021 | 15/06/2021 | 0 | TK_Complete | 94810358 | 396 | 94810358_396
A190190 | TT_Task | ATLAS Retrofit for Trainset #005 (8 wks in Sweden) (NOT USED) | 16/10/2023 | 20/11/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 398 | 94810358_398
A190200 | TT_Task | DIS Re-commissioning for Trainset #005 (3 wks in Sweden) (NOT USED) | 11/12/2023 | 26/02/2024 | nan | nan | 2976 | TK_NotStart | 94810358 | 399 | 94810358_399
A185270 | TT_Task | HP2 for Trainset #005 DM1 (By CBY Level w/ 1.5d Physical Inspection) and 0.5d Re-work | 10/02/2022 | 10/02/2022 | nan | nan | 0 | TK_NotStart | 94810358 | 432 | 94810358_432
A185290 | TT_Task | HP2 for Trainset #005 DM2 (By CBY Level w/ 2d Physical Inspection) and 2d Re-work | 08/02/2022 | 08/02/2022 | nan | nan | 0 | TK_NotStart | 94810358 | 432 | 94810358_432
A185300 | TT_Task | HP2 for Trainset #005 T (By CBY Level w/ 2d Physical Inspection) and 1d Re-work | 07/02/2022 | 07/02/2022 | nan | nan | 0 | TK_NotStart | 94810358 | 432 | 94810358_432
A186930 | TT_Task | QC Internal Check for Trainset #005 | 22/08/2022 | 26/09/2022 | nan | nan | 0 | TK_NotStart | 94810358 | 402 | 94810358_402
A187040 | TT_Task | HP4 for Trainset #005 | 05/09/2022 | 06/09/2022 | nan | nan | 0 | TK_NotStart | 94810358 | 403 | 94810358_403
A189400 | TT_Task | Re-work for Trainset #005 | 29/08/2022 | 03/10/2022 | nan | nan | 0 | TK_NotStart | 94810358 | 404 | 94810358_404
A11840 | TT_Task | Preliminary Takeover Inspection incl. HP5 for Trainset #005 | 18/09/2023 | 13/10/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 405 | 94810358_405
A12200 | TT_Task | Final Takeover Inspection for Trainset #005 | 17/09/2025 | 14/10/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 406 | 94810358_406
A185930 | TT_Task | 20000km Trial Operation for Trainset #005 (5 wks w/ J4 MT Approval EBICab) | 17/07/2023 | 21/08/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 407 | 94810358_407
A186510 | TT_Task | Pre- trial operation Batch #1 for Trainset #005 (8 wks and Close Track/ Night Time w/ J2 MT Approval EBICab) | 06/03/2023 | 15/09/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 408 | 94810358_408
A189970 | TT_Task | Pre- trial operation Batch #2 for Trainset #005 (6 wks w/ J4 MT Approval EBICab) | 01/05/2023 | 10/11/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 408 | 94810358_408
A11650 | TT_Task | Retrofit ; Re-commissioning for Trainset #001 (After Pre-trial Run) | 05/06/2023 | 10/07/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 449 | 94810358_449
A186520 | TT_Task | SU Net access tests for Trainset #001 | 03/07/2023 | 07/07/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 450 | 94810358_450
A11660 | TT_Task | Retrofit ; Re-commissioning for Trainset #002 (After Pre-trial Run) | 18/09/2023 | 23/10/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 449 | 94810358_449
A186530 | TT_Task | SU Net access tests for Trainset #002 | 16/10/2023 | 20/10/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 450 | 94810358_450
A11670 | TT_Task | Retrofit ; Re-commissioning for Trainset #003 (After Pre-trial Run) | 07/08/2023 | 11/09/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 449 | 94810358_449
A186540 | TT_Task | SU Net access tests for Trainset #003 | 04/09/2023 | 08/09/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 450 | 94810358_450
A11680 | TT_Task | Retrofit ; Re-commissioning for Trainset #004 (After Pre-trial Run) | 21/12/2023 | 25/01/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 449 | 94810358_449
A186550 | TT_Task | SU Net access tests for Trainset #004 | 18/01/2024 | 24/01/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 450 | 94810358_450
A11690 | TT_Task | Retrofit ; Re-commissioning for Trainset #005 (After Pre-trial Run) | 12/06/2023 | 17/07/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 449 | 94810358_449
A186560 | TT_Task | SU Net access tests for Trainset #005 | 10/07/2023 | 14/07/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 450 | 94810358_450
A62280 | TT_Task | Final Assembly for Trainset #006 DM1 | 30/05/2022 | 21/09/2022 | nan | nan | 0 | TK_NotStart | 94810358 | 350 | 94810358_350
A180380 | TT_Task | Final Assembly for Trainset #006 DM2 | 06/06/2022 | 12/10/2022 | nan | nan | 0 | TK_NotStart | 94810358 | 351 | 94810358_351
A180390 | TT_Task | Final Assembly for Trainset #006 T | 13/06/2022 | 19/10/2022 | nan | nan | 0 | TK_NotStart | 94810358 | 352 | 94810358_352
A181650 | TT_Task | Transport Carbody to Henningsdorf for Trainset #006 T | 06/10/2022 | 30/11/2022 | nan | nan | 0 | TK_NotStart | 94810358 | 356 | 94810358_356
A181660 | TT_Task | Transport Carbody to Henningsdorf for Trainset #006 DM2 | 29/09/2022 | 23/11/2022 | nan | nan | 0 | TK_NotStart | 94810358 | 354 | 94810358_354
A76130 | TT_Task | Transport Carbody to Henningsdorf for Trainset #006 DM1 | 22/09/2022 | 16/11/2022 | nan | nan | 0 | TK_NotStart | 94810358 | 355 | 94810358_355
A79380 | TT_Task | Transport to Sweden for Trainset #006 | 25/02/2023 | 02/03/2023 | nan | nan | 2232 | TK_NotStart | 94810358 | 427 | 94810358_427
A173510 | TT_Task | Fitout 2.8 for Trainset #006 DM1 | 24/11/2022 | 29/11/2022 | nan | nan | 0 | TK_NotStart | 94810358 | 411 | 94810358_411
A173520 | TT_Task | Fitout 2.9 for Trainset #006 DM1 | 30/11/2022 | 05/12/2022 | nan | nan | 0 | TK_NotStart | 94810358 | 451 | 94810358_451
A173530 | TT_Task | Single Car Testing for Trainset #006 DM1 | 06/12/2022 | 12/12/2022 | nan | nan | 0 | TK_NotStart | 94810358 | 412 | 94810358_412
A182610 | TT_Task | HP2 for Trainset #006 DM1 | 19/12/2022 | 22/12/2022 | nan | nan | 80 | TK_NotStart | 94810358 | 421 | 94810358_421
A45520 | TT_Task | Tempering of CBY for Trainset #006 DM1 | 17/11/2022 | 17/11/2022 | nan | nan | 0 | TK_NotStart | 94810358 | 375 | 94810358_375
A45610 | TT_Task | Fitout 2.7 for Trainset #006 DM1 | 18/11/2022 | 23/11/2022 | nan | nan | 0 | TK_NotStart | 94810358 | 414 | 94810358_414
A173540 | TT_Task | Tempering of CBY for Trainset #006 DM2 | 24/11/2022 | 24/11/2022 | nan | nan | 0 | TK_NotStart | 94810358 | 376 | 94810358_376
A173550 | TT_Task | Fitout 2.8 for Trainset #006 DM2 | 01/12/2022 | 06/12/2022 | nan | nan | 0 | TK_NotStart | 94810358 | 415 | 94810358_415
A173560 | TT_Task | Fitout 2.9 for Trainset #006 DM2 | 07/12/2022 | 13/12/2022 | nan | nan | 0 | TK_NotStart | 94810358 | 452 | 94810358_452
A173570 | TT_Task | Single Car Testing for Trainset #006 DM2 | 14/12/2022 | 19/12/2022 | nan | nan | 0 | TK_NotStart | 94810358 | 416 | 94810358_416
A182620 | TT_Task | HP2 for Trainset #006 DM2 | 04/01/2023 | 09/01/2023 | nan | nan | 40 | TK_NotStart | 94810358 | 422 | 94810358_422
A45620 | TT_Task | Fitout 2.7 for Trainset #006 DM2 | 25/11/2022 | 30/11/2022 | nan | nan | 0 | TK_NotStart | 94810358 | 417 | 94810358_417
A173580 | TT_Task | Tempering of CBY for Trainset #006 T | 01/12/2022 | 01/12/2022 | nan | nan | 0 | TK_NotStart | 94810358 | 380 | 94810358_380
A173590 | TT_Task | Fitout 2.8 for Trainset #006 T | 08/12/2022 | 14/12/2022 | nan | nan | 0 | TK_NotStart | 94810358 | 381 | 94810358_381
A173600 | TT_Task | Fitout 2.9 for Trainset #006 T | 15/12/2022 | 20/12/2022 | nan | nan | 0 | TK_NotStart | 94810358 | 453 | 94810358_453
A173610 | TT_Task | Single Car Testing for Trainset #006 T | 21/12/2022 | 04/01/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 418 | 94810358_418
A182630 | TT_Task | HP2 for Trainset #006 T | 11/01/2023 | 16/01/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 401 | 94810358_401
A45630 | TT_Task | Fitout 2.7 for Trainset #006 T | 02/12/2022 | 07/12/2022 | nan | nan | 0 | TK_NotStart | 94810358 | 419 | 94810358_419
A45580 | TT_Task | Train Completion for Trainset #006 | 12/01/2023 | 06/02/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 396 | 94810358_396
A45600 | TT_Task | Commissioning for Trainset #006 | 13/01/2023 | 10/02/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 312 | 94810358_312
A80430 | TT_Task | Quality/Customer Acceptance for Trainset #006 | 13/02/2023 | 24/02/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 454 | 94810358_454
A11890 | TT_Task | Preliminary Takeover Inspection for Trainset #006 (Assume Insepection in parallel w/ J5 Application) | 18/07/2024 | 14/08/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 424 | 94810358_424
A11900 | TT_Task | Final Takeover Inspection for Trainset #006 | 17/09/2025 | 14/10/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 406 | 94810358_406
A62400 | TT_Task | Final Assembly for Trainset #007 DM1 | 16/06/2022 | 10/10/2022 | nan | nan | 0 | TK_NotStart | 94810358 | 350 | 94810358_350
A180410 | TT_Task | Final Assembly for Trainset #007 DM2 | 23/06/2022 | 31/10/2022 | nan | nan | 0 | TK_NotStart | 94810358 | 351 | 94810358_351
A180420 | TT_Task | Final Assembly for Trainset #007 T | 30/06/2022 | 07/11/2022 | nan | nan | 0 | TK_NotStart | 94810358 | 352 | 94810358_352
A181670 | TT_Task | Transport Carbody to Henningsdorf for Trainset #007 T | 25/10/2022 | 19/12/2022 | nan | nan | 0 | TK_NotStart | 94810358 | 356 | 94810358_356
A181680 | TT_Task | Transport Carbody to Henningsdorf for Trainset #007 DM2 | 19/10/2022 | 13/12/2022 | nan | nan | 0 | TK_NotStart | 94810358 | 354 | 94810358_354
A76160 | TT_Task | Transport Carbody to Henningsdorf for Trainset #007 DM1 | 12/10/2022 | 06/12/2022 | nan | nan | 0 | TK_NotStart | 94810358 | 355 | 94810358_355
A79440 | TT_Task | Transport to Sweden for Trainset #007 | 11/03/2023 | 16/03/2023 | nan | nan | 3912 | TK_NotStart | 94810358 | 427 | 94810358_427
A173680 | TT_Task | Fitout 2.8 for Trainset #007 DM1 | 15/12/2022 | 20/12/2022 | nan | nan | 0 | TK_NotStart | 94810358 | 411 | 94810358_411
A173690 | TT_Task | Fitout 2.9 for Trainset #007 DM1 | 21/12/2022 | 04/01/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 451 | 94810358_451
A173700 | TT_Task | Single Car Testing for Trainset #007 DM1 | 05/01/2023 | 10/01/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 412 | 94810358_412
A182640 | TT_Task | HP2 for Trainset #007 DM1 | 16/01/2023 | 19/01/2023 | nan | nan | 64 | TK_NotStart | 94810358 | 421 | 94810358_421
A45690 | TT_Task | Tempering of CBY for Trainset #007 DM1 | 07/12/2022 | 07/12/2022 | nan | nan | 0 | TK_NotStart | 94810358 | 375 | 94810358_375
A45780 | TT_Task | Fitout 2.7 for Trainset #007 DM1 | 08/12/2022 | 14/12/2022 | nan | nan | 0 | TK_NotStart | 94810358 | 414 | 94810358_414
A173710 | TT_Task | Tempering of CBY for Trainset #007 DM2 | 14/12/2022 | 14/12/2022 | nan | nan | 0 | TK_NotStart | 94810358 | 376 | 94810358_376
A173720 | TT_Task | Fitout 2.8 for Trainset #007 DM2 | 21/12/2022 | 04/01/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 415 | 94810358_415
A173730 | TT_Task | Fitout 2.9 for Trainset #007 DM2 | 05/01/2023 | 10/01/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 452 | 94810358_452
A173740 | TT_Task | Single Car Testing for Trainset #007 DM2 | 11/01/2023 | 16/01/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 416 | 94810358_416
A182650 | TT_Task | HP2 for Trainset #007 DM2 | 20/01/2023 | 25/01/2023 | nan | nan | 32 | TK_NotStart | 94810358 | 422 | 94810358_422
A45790 | TT_Task | Fitout 2.7 for Trainset #007 DM2 | 15/12/2022 | 20/12/2022 | nan | nan | 0 | TK_NotStart | 94810358 | 417 | 94810358_417
A173750 | TT_Task | Tempering of CBY for Trainset #007 T | 20/12/2022 | 20/12/2022 | nan | nan | 0 | TK_NotStart | 94810358 | 380 | 94810358_380
A173760 | TT_Task | Fitout 2.8 for Trainset #007 T | 05/01/2023 | 10/01/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 381 | 94810358_381
A173770 | TT_Task | Fitout 2.9 for Trainset #007 T | 11/01/2023 | 16/01/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 453 | 94810358_453
A173780 | TT_Task | Single Car Testing for Trainset #007 T | 17/01/2023 | 20/01/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 418 | 94810358_418
A182660 | TT_Task | HP2 for Trainset #007 T | 26/01/2023 | 31/01/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 401 | 94810358_401
A45800 | TT_Task | Fitout 2.7 for Trainset #007 T | 21/12/2022 | 04/01/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 419 | 94810358_419
A45750 | TT_Task | Train Completion for Trainset #007 | 27/01/2023 | 17/02/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 396 | 94810358_396
A45770 | TT_Task | Commissioning for Trainset #007 | 30/01/2023 | 24/02/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 312 | 94810358_312
A80440 | TT_Task | Quality/Customer Acceptance for Trainset #007 | 27/02/2023 | 10/03/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 454 | 94810358_454
A13770 | TT_Task | Preliminary Takeover Inspection for Trainset #007 (Assume Insepection in parallel w/ J5 Application) | 18/07/2024 | 14/08/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 424 | 94810358_424
A13780 | TT_Task | Final Takeover Inspection for Trainset #007 | 17/09/2025 | 14/10/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 406 | 94810358_406
A62520 | TT_Task | Final Assembly for Trainset #008 DM1 | 13/07/2022 | 04/11/2022 | nan | nan | 0 | TK_NotStart | 94810358 | 350 | 94810358_350
A180440 | TT_Task | Final Assembly for Trainset #008 DM2 | 20/07/2022 | 25/11/2022 | nan | nan | 0 | TK_NotStart | 94810358 | 351 | 94810358_351
A180450 | TT_Task | Final Assembly for Trainset #008 T | 27/07/2022 | 02/12/2022 | nan | nan | 0 | TK_NotStart | 94810358 | 352 | 94810358_352
A181690 | TT_Task | Transport Carbody to Henningsdorf for Trainset #008 T | 21/11/2022 | 15/01/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 356 | 94810358_356
A181700 | TT_Task | Transport Carbody to Henningsdorf for Trainset #008 DM2 | 15/11/2022 | 09/01/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 354 | 94810358_354
A76190 | TT_Task | Transport Carbody to Henningsdorf for Trainset #008 DM1 | 09/11/2022 | 03/01/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 355 | 94810358_355
A79450 | TT_Task | Transport to Sweden for Trainset #008 | 24/03/2023 | 29/03/2023 | nan | nan | 4032 | TK_NotStart | 94810358 | 427 | 94810358_427
A173850 | TT_Task | Fitout 2.8 for Trainset #008 DM1 | 11/01/2023 | 16/01/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 411 | 94810358_411
A173860 | TT_Task | Fitout 2.9 for Trainset #008 DM1 | 17/01/2023 | 20/01/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 451 | 94810358_451
A173870 | TT_Task | Single Car Testing for Trainset #008 DM1 | 23/01/2023 | 26/01/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 412 | 94810358_412
A182670 | TT_Task | HP2 for Trainset #008 DM1 | 31/01/2023 | 06/02/2023 | nan | nan | 64 | TK_NotStart | 94810358 | 421 | 94810358_421
A45860 | TT_Task | Tempering of CBY for Trainset #008 DM1 | 04/01/2023 | 04/01/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 375 | 94810358_375
A45950 | TT_Task | Fitout 2.7 for Trainset #008 DM1 | 05/01/2023 | 10/01/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 414 | 94810358_414
A173880 | TT_Task | Tempering of CBY for Trainset #008 DM2 | 10/01/2023 | 10/01/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 376 | 94810358_376
A173890 | TT_Task | Fitout 2.8 for Trainset #008 DM2 | 17/01/2023 | 20/01/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 415 | 94810358_415
A173900 | TT_Task | Fitout 2.9 for Trainset #008 DM2 | 23/01/2023 | 26/01/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 452 | 94810358_452
A173910 | TT_Task | Single Car Testing for Trainset #008 DM2 | 27/01/2023 | 02/02/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 416 | 94810358_416
A182680 | TT_Task | HP2 for Trainset #008 DM2 | 07/02/2023 | 10/02/2023 | nan | nan | 32 | TK_NotStart | 94810358 | 422 | 94810358_422
A45960 | TT_Task | Fitout 2.7 for Trainset #008 DM2 | 11/01/2023 | 16/01/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 417 | 94810358_417
A173920 | TT_Task | Tempering of CBY for Trainset #008 T | 16/01/2023 | 16/01/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 380 | 94810358_380
A173930 | TT_Task | Fitout 2.8 for Trainset #008 T | 23/01/2023 | 26/01/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 381 | 94810358_381
A173940 | TT_Task | Fitout 2.9 for Trainset #008 T | 27/01/2023 | 02/02/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 453 | 94810358_453
A173950 | TT_Task | Single Car Testing for Trainset #008 T | 03/02/2023 | 08/02/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 418 | 94810358_418
A182690 | TT_Task | HP2 for Trainset #008 T | 13/02/2023 | 16/02/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 401 | 94810358_401
A45970 | TT_Task | Fitout 2.7 for Trainset #008 T | 17/01/2023 | 20/01/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 419 | 94810358_419
A45920 | TT_Task | Train Completion for Trainset #008 | 14/02/2023 | 03/03/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 396 | 94810358_396
A45940 | TT_Task | Commissioning for Trainset #008 | 15/02/2023 | 09/03/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 312 | 94810358_312
A80450 | TT_Task | Quality/Customer Acceptance for Trainset #008 | 10/03/2023 | 23/03/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 454 | 94810358_454
A13880 | TT_Task | Preliminary Takeover Inspection for Trainset #008 | 15/08/2024 | 11/09/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 455 | 94810358_455
A13890 | TT_Task | Final Takeover Inspection for Trainset #008 | 17/09/2025 | 14/10/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 406 | 94810358_406
A62640 | TT_Task | Final Assembly for Trainset #009 DM1 | 01/08/2022 | 23/11/2022 | nan | nan | 0 | TK_NotStart | 94810358 | 350 | 94810358_350
A180470 | TT_Task | Final Assembly for Trainset #009 DM2 | 08/08/2022 | 14/12/2022 | nan | nan | 0 | TK_NotStart | 94810358 | 351 | 94810358_351
A180480 | TT_Task | Final Assembly for Trainset #009 T | 15/08/2022 | 21/12/2022 | nan | nan | 0 | TK_NotStart | 94810358 | 352 | 94810358_352
A181710 | TT_Task | Transport Carbody to Henningsdorf for Trainset #009 T | 08/12/2022 | 01/02/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 356 | 94810358_356
A181720 | TT_Task | Transport Carbody to Henningsdorf for Trainset #009 DM2 | 01/12/2022 | 25/01/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 354 | 94810358_354
A76220 | TT_Task | Transport Carbody to Henningsdorf for Trainset #009 DM1 | 25/11/2022 | 19/01/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 355 | 94810358_355
A79460 | TT_Task | Transport to Sweden for Trainset #009 | 14/04/2023 | 19/04/2023 | nan | nan | 3864 | TK_NotStart | 94810358 | 427 | 94810358_427
A174020 | TT_Task | Fitout 2.8 for Trainset #009 DM1 | 27/01/2023 | 02/02/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 411 | 94810358_411
A174030 | TT_Task | Fitout 2.9 for Trainset #009 DM1 | 03/02/2023 | 08/02/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 451 | 94810358_451
A174040 | TT_Task | Single Car Testing for Trainset #009 DM1 | 09/02/2023 | 14/02/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 412 | 94810358_412
A182700 | TT_Task | HP2 for Trainset #009 DM1 | 16/02/2023 | 21/02/2023 | nan | nan | 64 | TK_NotStart | 94810358 | 421 | 94810358_421
A46030 | TT_Task | Tempering of CBY for Trainset #009 DM1 | 20/01/2023 | 20/01/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 375 | 94810358_375
A46120 | TT_Task | Fitout 2.7 for Trainset #009 DM1 | 23/01/2023 | 26/01/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 414 | 94810358_414
A174050 | TT_Task | Tempering of CBY for Trainset #009 DM2 | 26/01/2023 | 26/01/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 376 | 94810358_376
A174060 | TT_Task | Fitout 2.8 for Trainset #009 DM2 | 03/02/2023 | 08/02/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 415 | 94810358_415
A174070 | TT_Task | Fitout 2.9 for Trainset #009 DM2 | 09/02/2023 | 14/02/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 452 | 94810358_452
A174080 | TT_Task | Single Car Testing for Trainset #009 DM2 | 15/02/2023 | 20/02/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 416 | 94810358_416
A182710 | TT_Task | HP2 for Trainset #009 DM2 | 22/02/2023 | 27/02/2023 | nan | nan | 32 | TK_NotStart | 94810358 | 422 | 94810358_422
A46130 | TT_Task | Fitout 2.7 for Trainset #009 DM2 | 27/01/2023 | 02/02/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 417 | 94810358_417
A174090 | TT_Task | Tempering of CBY for Trainset #009 T | 02/02/2023 | 02/02/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 380 | 94810358_380
A174100 | TT_Task | Fitout 2.8 for Trainset #009 T | 09/02/2023 | 14/02/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 381 | 94810358_381
A174110 | TT_Task | Fitout 2.9 for Trainset #009 T | 15/02/2023 | 20/02/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 453 | 94810358_453
A174120 | TT_Task | Single Car Testing for Trainset #009 T | 21/02/2023 | 24/02/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 418 | 94810358_418
A182720 | TT_Task | HP2 for Trainset #009 T | 28/02/2023 | 03/03/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 401 | 94810358_401
A46140 | TT_Task | Fitout 2.7 for Trainset #009 T | 03/02/2023 | 08/02/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 419 | 94810358_419
A46090 | TT_Task | Train Completion for Trainset #009 | 01/03/2023 | 17/03/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 396 | 94810358_396
A46110 | TT_Task | Commissioning for Trainset #009 | 02/03/2023 | 23/03/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 312 | 94810358_312
A80460 | TT_Task | Quality/Customer Acceptance for Trainset #009 | 24/03/2023 | 13/04/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 454 | 94810358_454
A13990 | TT_Task | Preliminary Takeover Inspection for Trainset #009 | 15/08/2024 | 11/09/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 455 | 94810358_455
A14000 | TT_Task | Final Takeover Inspection for Trainset #009 | 17/09/2025 | 14/10/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 406 | 94810358_406
A62760 | TT_Task | Final Assembly for Trainset #010 DM1 | 17/08/2022 | 09/12/2022 | nan | nan | 0 | TK_NotStart | 94810358 | 350 | 94810358_350
A180500 | TT_Task | Final Assembly for Trainset #010 DM2 | 24/08/2022 | 30/12/2022 | nan | nan | 0 | TK_NotStart | 94810358 | 351 | 94810358_351
A180510 | TT_Task | Final Assembly for Trainset #010 T | 31/08/2022 | 06/01/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 352 | 94810358_352
A181730 | TT_Task | Transport Carbody to Henningsdorf for Trainset #010 T | 26/12/2022 | 19/02/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 356 | 94810358_356
A181740 | TT_Task | Transport Carbody to Henningsdorf for Trainset #010 DM2 | 20/12/2022 | 13/02/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 354 | 94810358_354
A76250 | TT_Task | Transport Carbody to Henningsdorf for Trainset #010 DM1 | 14/12/2022 | 07/02/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 355 | 94810358_355
A79470 | TT_Task | Transport to Sweden for Trainset #010 | 27/04/2023 | 02/05/2023 | nan | nan | 3984 | TK_NotStart | 94810358 | 427 | 94810358_427
A174190 | TT_Task | Fitout 2.8 for Trainset #010 DM1 | 15/02/2023 | 20/02/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 411 | 94810358_411
A174200 | TT_Task | Fitout 2.9 for Trainset #010 DM1 | 21/02/2023 | 24/02/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 451 | 94810358_451
A174210 | TT_Task | Single Car Testing for Trainset #010 DM1 | 27/02/2023 | 02/03/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 412 | 94810358_412
A182730 | TT_Task | HP2 for Trainset #010 DM1 | 03/03/2023 | 08/03/2023 | nan | nan | 64 | TK_NotStart | 94810358 | 421 | 94810358_421
A46200 | TT_Task | Tempering of CBY for Trainset #010 DM1 | 08/02/2023 | 08/02/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 375 | 94810358_375
A46290 | TT_Task | Fitout 2.7 for Trainset #010 DM1 | 09/02/2023 | 14/02/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 414 | 94810358_414
A174220 | TT_Task | Tempering of CBY for Trainset #010 DM2 | 14/02/2023 | 14/02/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 376 | 94810358_376
A174230 | TT_Task | Fitout 2.8 for Trainset #010 DM2 | 21/02/2023 | 24/02/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 415 | 94810358_415
A174240 | TT_Task | Fitout 2.9 for Trainset #010 DM2 | 27/02/2023 | 02/03/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 452 | 94810358_452
A174250 | TT_Task | Single Car Testing for Trainset #010 DM2 | 03/03/2023 | 08/03/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 416 | 94810358_416
A182740 | TT_Task | HP2 for Trainset #010 DM2 | 09/03/2023 | 14/03/2023 | nan | nan | 32 | TK_NotStart | 94810358 | 422 | 94810358_422
A46300 | TT_Task | Fitout 2.7 for Trainset #010 DM2 | 15/02/2023 | 20/02/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 417 | 94810358_417
A174260 | TT_Task | Tempering of CBY for Trainset #010 T | 20/02/2023 | 20/02/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 380 | 94810358_380
A174270 | TT_Task | Fitout 2.8 for Trainset #010 T | 27/02/2023 | 02/03/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 381 | 94810358_381
A174280 | TT_Task | Fitout 2.9 for Trainset #010 T | 03/03/2023 | 08/03/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 453 | 94810358_453
A174290 | TT_Task | Single Car Testing for Trainset #010 T | 09/03/2023 | 14/03/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 418 | 94810358_418
A182750 | TT_Task | HP2 for Trainset #010 T | 15/03/2023 | 20/03/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 401 | 94810358_401
A46310 | TT_Task | Fitout 2.7 for Trainset #010 T | 21/02/2023 | 24/02/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 419 | 94810358_419
A46260 | TT_Task | Train Completion for Trainset #010 | 16/03/2023 | 04/04/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 396 | 94810358_396
A46280 | TT_Task | Commissioning for Trainset #010 | 17/03/2023 | 13/04/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 312 | 94810358_312
A80470 | TT_Task | Quality/Customer Acceptance for Trainset #010 | 13/04/2023 | 26/04/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 454 | 94810358_454
A14100 | TT_Task | Preliminary Takeover Inspection for Trainset #010 | 12/09/2024 | 09/10/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 455 | 94810358_455
A14110 | TT_Task | Final Takeover Inspection for Trainset #010 | 17/09/2025 | 14/10/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 406 | 94810358_406
A62880 | TT_Task | Final Assembly for Trainset #011 DM1 | 02/09/2022 | 27/12/2022 | nan | nan | 0 | TK_NotStart | 94810358 | 350 | 94810358_350
A180530 | TT_Task | Final Assembly for Trainset #011 DM2 | 09/09/2022 | 17/01/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 351 | 94810358_351
A180540 | TT_Task | Final Assembly for Trainset #011 T | 16/09/2022 | 24/01/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 352 | 94810358_352
A181750 | TT_Task | Transport Carbody to Henningsdorf for Trainset #011 T | 11/01/2023 | 07/03/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 356 | 94810358_356
A181760 | TT_Task | Transport Carbody to Henningsdorf for Trainset #011 DM2 | 05/01/2023 | 01/03/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 354 | 94810358_354
A76280 | TT_Task | Transport Carbody to Henningsdorf for Trainset #011 DM1 | 30/12/2022 | 23/02/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 355 | 94810358_355
A79480 | TT_Task | Transport to Sweden for Trainset #011 | 13/05/2023 | 18/05/2023 | nan | nan | 3856 | TK_NotStart | 94810358 | 427 | 94810358_427
A174360 | TT_Task | Fitout 2.8 for Trainset #011 DM1 | 03/03/2023 | 08/03/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 411 | 94810358_411
A174370 | TT_Task | Fitout 2.9 for Trainset #011 DM1 | 09/03/2023 | 14/03/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 451 | 94810358_451
A174380 | TT_Task | Single Car Testing for Trainset #011 DM1 | 15/03/2023 | 20/03/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 412 | 94810358_412
A182760 | TT_Task | HP2 for Trainset #011 DM1 | 21/03/2023 | 24/03/2023 | nan | nan | 64 | TK_NotStart | 94810358 | 421 | 94810358_421
A46370 | TT_Task | Tempering of CBY for Trainset #011 DM1 | 24/02/2023 | 24/02/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 375 | 94810358_375
A46460 | TT_Task | Fitout 2.7 for Trainset #011 DM1 | 27/02/2023 | 02/03/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 414 | 94810358_414
A174390 | TT_Task | Tempering of CBY for Trainset #011 DM2 | 02/03/2023 | 02/03/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 376 | 94810358_376
A174400 | TT_Task | Fitout 2.8 for Trainset #011 DM2 | 09/03/2023 | 14/03/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 415 | 94810358_415
A174410 | TT_Task | Fitout 2.9 for Trainset #011 DM2 | 15/03/2023 | 20/03/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 452 | 94810358_452
A174420 | TT_Task | Single Car Testing for Trainset #011 DM2 | 21/03/2023 | 24/03/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 416 | 94810358_416
A182770 | TT_Task | HP2 for Trainset #011 DM2 | 27/03/2023 | 30/03/2023 | nan | nan | 32 | TK_NotStart | 94810358 | 422 | 94810358_422
A46470 | TT_Task | Fitout 2.7 for Trainset #011 DM2 | 03/03/2023 | 08/03/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 417 | 94810358_417
A174430 | TT_Task | Tempering of CBY for Trainset #011 T | 08/03/2023 | 08/03/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 380 | 94810358_380
A174440 | TT_Task | Fitout 2.8 for Trainset #011 T | 15/03/2023 | 20/03/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 381 | 94810358_381
A174450 | TT_Task | Fitout 2.9 for Trainset #011 T | 21/03/2023 | 24/03/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 453 | 94810358_453
A174460 | TT_Task | Single Car Testing for Trainset #011 T | 27/03/2023 | 30/03/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 418 | 94810358_418
A182780 | TT_Task | HP2 for Trainset #011 T | 03/04/2023 | 11/04/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 401 | 94810358_401
A46480 | TT_Task | Fitout 2.7 for Trainset #011 T | 09/03/2023 | 14/03/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 419 | 94810358_419
A46430 | TT_Task | Train Completion for Trainset #011 | 04/04/2023 | 26/04/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 396 | 94810358_396
A46450 | TT_Task | Commissioning for Trainset #011 | 06/04/2023 | 27/04/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 312 | 94810358_312
A80480 | TT_Task | Quality/Customer Acceptance for Trainset #011 | 28/04/2023 | 12/05/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 454 | 94810358_454
A14220 | TT_Task | Preliminary Takeover Inspection for Trainset #011 | 12/09/2024 | 09/10/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 455 | 94810358_455
A14230 | TT_Task | Final Takeover Inspection for Trainset #011 | 17/09/2025 | 14/10/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 406 | 94810358_406
A63000 | TT_Task | Final Assembly for Trainset #012 DM1 | 20/09/2022 | 12/01/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 350 | 94810358_350
A180560 | TT_Task | Final Assembly for Trainset #012 DM2 | 27/09/2022 | 02/02/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 351 | 94810358_351
A180570 | TT_Task | Final Assembly for Trainset #012 T | 04/10/2022 | 09/02/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 352 | 94810358_352
A181770 | TT_Task | Transport Carbody to Henningsdorf for Trainset #012 T | 27/01/2023 | 23/03/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 356 | 94810358_356
A181780 | TT_Task | Transport Carbody to Henningsdorf for Trainset #012 DM2 | 23/01/2023 | 19/03/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 354 | 94810358_354
A76310 | TT_Task | Transport Carbody to Henningsdorf for Trainset #012 DM1 | 17/01/2023 | 13/03/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 355 | 94810358_355
A79490 | TT_Task | Transport to Sweden for Trainset #012 | 02/06/2023 | 07/06/2023 | nan | nan | 3920 | TK_NotStart | 94810358 | 427 | 94810358_427
A174530 | TT_Task | Fitout 2.8 for Trainset #012 DM1 | 21/03/2023 | 24/03/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 411 | 94810358_411
A174540 | TT_Task | Fitout 2.9 for Trainset #012 DM1 | 27/03/2023 | 30/03/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 451 | 94810358_451
A174550 | TT_Task | Single Car Testing for Trainset #012 DM1 | 03/04/2023 | 11/04/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 412 | 94810358_412
A182790 | TT_Task | HP2 for Trainset #012 DM1 | 13/04/2023 | 18/04/2023 | nan | nan | 64 | TK_NotStart | 94810358 | 421 | 94810358_421
A46540 | TT_Task | Tempering of CBY for Trainset #012 DM1 | 14/03/2023 | 14/03/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 375 | 94810358_375
A46630 | TT_Task | Fitout 2.7 for Trainset #012 DM1 | 15/03/2023 | 20/03/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 414 | 94810358_414
A174560 | TT_Task | Tempering of CBY for Trainset #012 DM2 | 20/03/2023 | 20/03/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 376 | 94810358_376
A174570 | TT_Task | Fitout 2.8 for Trainset #012 DM2 | 27/03/2023 | 30/03/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 415 | 94810358_415
A174580 | TT_Task | Fitout 2.9 for Trainset #012 DM2 | 03/04/2023 | 11/04/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 452 | 94810358_452
A174590 | TT_Task | Single Car Testing for Trainset #012 DM2 | 13/04/2023 | 18/04/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 416 | 94810358_416
A182800 | TT_Task | HP2 for Trainset #012 DM2 | 19/04/2023 | 24/04/2023 | nan | nan | 32 | TK_NotStart | 94810358 | 422 | 94810358_422
A46640 | TT_Task | Fitout 2.7 for Trainset #012 DM2 | 21/03/2023 | 24/03/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 417 | 94810358_417
A174600 | TT_Task | Tempering of CBY for Trainset #012 T | 24/03/2023 | 24/03/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 380 | 94810358_380
A174610 | TT_Task | Fitout 2.8 for Trainset #012 T | 03/04/2023 | 11/04/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 381 | 94810358_381
A174620 | TT_Task | Fitout 2.9 for Trainset #012 T | 13/04/2023 | 18/04/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 453 | 94810358_453
A174630 | TT_Task | Single Car Testing for Trainset #012 T | 19/04/2023 | 24/04/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 418 | 94810358_418
A182810 | TT_Task | HP2 for Trainset #012 T | 25/04/2023 | 28/04/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 401 | 94810358_401
A46650 | TT_Task | Fitout 2.7 for Trainset #012 T | 27/03/2023 | 30/03/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 419 | 94810358_419
A46600 | TT_Task | Train Completion for Trainset #012 | 26/04/2023 | 15/05/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 396 | 94810358_396
A46620 | TT_Task | Commissioning for Trainset #012 | 27/04/2023 | 12/05/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 312 | 94810358_312
A80490 | TT_Task | Quality/Customer Acceptance for Trainset #012 | 15/05/2023 | 01/06/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 454 | 94810358_454
A14330 | TT_Task | Preliminary Takeover Inspection for Trainset #012 | 10/10/2024 | 06/11/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 455 | 94810358_455
A14340 | TT_Task | Final Takeover Inspection for Trainset #012 | 17/09/2025 | 14/10/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 406 | 94810358_406
A63120 | TT_Task | Final Assembly for Trainset #013 DM1 | 10/10/2022 | 01/02/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 350 | 94810358_350
A180590 | TT_Task | Final Assembly for Trainset #013 DM2 | 20/10/2022 | 27/02/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 351 | 94810358_351
A180600 | TT_Task | Final Assembly for Trainset #013 T | 27/10/2022 | 06/03/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 352 | 94810358_352
A181790 | TT_Task | Transport Carbody to Henningsdorf for Trainset #013 T | 21/02/2023 | 17/04/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 356 | 94810358_356
A181800 | TT_Task | Transport Carbody to Henningsdorf for Trainset #013 DM2 | 14/02/2023 | 10/04/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 354 | 94810358_354
A76340 | TT_Task | Transport Carbody to Henningsdorf for Trainset #013 DM1 | 02/02/2023 | 29/03/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 355 | 94810358_355
A79500 | TT_Task | Transport to Sweden for Trainset #013 | 17/06/2023 | 22/06/2023 | nan | nan | 3800 | TK_NotStart | 94810358 | 427 | 94810358_427
A174700 | TT_Task | Fitout 2.8 for Trainset #013 DM1 | 13/04/2023 | 18/04/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 411 | 94810358_411
A174710 | TT_Task | Fitout 2.9 for Trainset #013 DM1 | 19/04/2023 | 24/04/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 451 | 94810358_451
A174720 | TT_Task | Single Car Testing for Trainset #013 DM1 | 25/04/2023 | 28/04/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 412 | 94810358_412
A182820 | TT_Task | HP2 for Trainset #013 DM1 | 02/05/2023 | 05/05/2023 | nan | nan | 64 | TK_NotStart | 94810358 | 421 | 94810358_421
A46710 | TT_Task | Tempering of CBY for Trainset #013 DM1 | 30/03/2023 | 30/03/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 375 | 94810358_375
A46800 | TT_Task | Fitout 2.7 for Trainset #013 DM1 | 03/04/2023 | 11/04/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 414 | 94810358_414
A174730 | TT_Task | Tempering of CBY for Trainset #013 DM2 | 11/04/2023 | 11/04/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 376 | 94810358_376
A174740 | TT_Task | Fitout 2.8 for Trainset #013 DM2 | 19/04/2023 | 24/04/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 415 | 94810358_415
A174750 | TT_Task | Fitout 2.9 for Trainset #013 DM2 | 25/04/2023 | 28/04/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 452 | 94810358_452
A174760 | TT_Task | Single Car Testing for Trainset #013 DM2 | 02/05/2023 | 05/05/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 416 | 94810358_416
A182830 | TT_Task | HP2 for Trainset #013 DM2 | 08/05/2023 | 11/05/2023 | nan | nan | 32 | TK_NotStart | 94810358 | 422 | 94810358_422
A46810 | TT_Task | Fitout 2.7 for Trainset #013 DM2 | 13/04/2023 | 18/04/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 417 | 94810358_417
A174770 | TT_Task | Tempering of CBY for Trainset #013 T | 18/04/2023 | 18/04/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 380 | 94810358_380
A174780 | TT_Task | Fitout 2.8 for Trainset #013 T | 25/04/2023 | 28/04/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 381 | 94810358_381
A174790 | TT_Task | Fitout 2.9 for Trainset #013 T | 02/05/2023 | 05/05/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 453 | 94810358_453
A174800 | TT_Task | Single Car Testing for Trainset #013 T | 08/05/2023 | 11/05/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 418 | 94810358_418
A182840 | TT_Task | HP2 for Trainset #013 T | 12/05/2023 | 22/05/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 401 | 94810358_401
A46820 | TT_Task | Fitout 2.7 for Trainset #013 T | 19/04/2023 | 24/04/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 419 | 94810358_419
A46770 | TT_Task | Train Completion for Trainset #013 | 15/05/2023 | 06/06/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 396 | 94810358_396
A46790 | TT_Task | Commissioning for Trainset #013 | 17/05/2023 | 02/06/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 312 | 94810358_312
A80500 | TT_Task | Quality/Customer Acceptance for Trainset #013 | 05/06/2023 | 16/06/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 454 | 94810358_454
A14440 | TT_Task | Preliminary Takeover Inspection for Trainset #013 | 10/10/2024 | 06/11/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 455 | 94810358_455
A14450 | TT_Task | Final Takeover Inspection for Trainset #013 | 17/09/2025 | 14/10/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 406 | 94810358_406
A63240 | TT_Task | Final Assembly for Trainset #014 DM1 | 01/11/2022 | 23/02/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 350 | 94810358_350
A180620 | TT_Task | Final Assembly for Trainset #014 DM2 | 08/11/2022 | 16/03/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 351 | 94810358_351
A180630 | TT_Task | Final Assembly for Trainset #014 T | 15/11/2022 | 23/03/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 352 | 94810358_352
A181810 | TT_Task | Transport Carbody to Henningsdorf for Trainset #014 T | 10/03/2023 | 04/05/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 356 | 94810358_356
A181820 | TT_Task | Transport Carbody to Henningsdorf for Trainset #014 DM2 | 03/03/2023 | 27/04/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 354 | 94810358_354
A76370 | TT_Task | Transport Carbody to Henningsdorf for Trainset #014 DM1 | 27/02/2023 | 23/04/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 355 | 94810358_355
A79510 | TT_Task | Transport to Sweden for Trainset #014 | 06/07/2023 | 11/07/2023 | nan | nan | 3872 | TK_NotStart | 94810358 | 427 | 94810358_427
A174870 | TT_Task | Fitout 2.8 for Trainset #014 DM1 | 02/05/2023 | 05/05/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 411 | 94810358_411
A174880 | TT_Task | Fitout 2.9 for Trainset #014 DM1 | 08/05/2023 | 11/05/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 451 | 94810358_451
A174890 | TT_Task | Single Car Testing for Trainset #014 DM1 | 12/05/2023 | 22/05/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 412 | 94810358_412
A182850 | TT_Task | HP2 for Trainset #014 DM1 | 23/05/2023 | 26/05/2023 | nan | nan | 64 | TK_NotStart | 94810358 | 421 | 94810358_421
A46880 | TT_Task | Tempering of CBY for Trainset #014 DM1 | 24/04/2023 | 24/04/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 375 | 94810358_375
A46970 | TT_Task | Fitout 2.7 for Trainset #014 DM1 | 25/04/2023 | 28/04/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 414 | 94810358_414
A174900 | TT_Task | Tempering of CBY for Trainset #014 DM2 | 28/04/2023 | 28/04/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 376 | 94810358_376
A174910 | TT_Task | Fitout 2.8 for Trainset #014 DM2 | 08/05/2023 | 11/05/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 415 | 94810358_415
A174920 | TT_Task | Fitout 2.9 for Trainset #014 DM2 | 12/05/2023 | 22/05/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 452 | 94810358_452
A174930 | TT_Task | Single Car Testing for Trainset #014 DM2 | 23/05/2023 | 26/05/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 416 | 94810358_416
A182860 | TT_Task | HP2 for Trainset #014 DM2 | 30/05/2023 | 02/06/2023 | nan | nan | 32 | TK_NotStart | 94810358 | 422 | 94810358_422
A46980 | TT_Task | Fitout 2.7 for Trainset #014 DM2 | 02/05/2023 | 05/05/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 417 | 94810358_417
A174940 | TT_Task | Tempering of CBY for Trainset #014 T | 05/05/2023 | 05/05/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 380 | 94810358_380
A174950 | TT_Task | Fitout 2.8 for Trainset #014 T | 12/05/2023 | 22/05/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 381 | 94810358_381
A174960 | TT_Task | Fitout 2.9 for Trainset #014 T | 23/05/2023 | 26/05/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 453 | 94810358_453
A174970 | TT_Task | Single Car Testing for Trainset #014 T | 30/05/2023 | 02/06/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 418 | 94810358_418
A182870 | TT_Task | HP2 for Trainset #014 T | 05/06/2023 | 08/06/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 401 | 94810358_401
A46990 | TT_Task | Fitout 2.7 for Trainset #014 T | 08/05/2023 | 11/05/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 419 | 94810358_419
A46940 | TT_Task | Train Completion for Trainset #014 | 06/06/2023 | 22/06/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 396 | 94810358_396
A46960 | TT_Task | Commissioning for Trainset #014 | 07/06/2023 | 20/06/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 312 | 94810358_312
A80510 | TT_Task | Quality/Customer Acceptance for Trainset #014 | 21/06/2023 | 05/07/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 454 | 94810358_454
A14550 | TT_Task | Preliminary Takeover Inspection for Trainset #014 | 07/11/2024 | 04/12/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 455 | 94810358_455
A14560 | TT_Task | Final Takeover Inspection for Trainset #014 | 17/09/2025 | 14/10/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 406 | 94810358_406
A63360 | TT_Task | Final Assembly for Trainset #015 DM1 | 21/11/2022 | 15/03/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 350 | 94810358_350
A180650 | TT_Task | Final Assembly for Trainset #015 DM2 | 29/11/2022 | 06/04/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 351 | 94810358_351
A180660 | TT_Task | Final Assembly for Trainset #015 T | 06/12/2022 | 13/04/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 352 | 94810358_352
A181830 | TT_Task | Transport Carbody to Henningsdorf for Trainset #015 T | 31/03/2023 | 25/05/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 356 | 94810358_356
A181840 | TT_Task | Transport Carbody to Henningsdorf for Trainset #015 DM2 | 27/03/2023 | 21/05/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 354 | 94810358_354
A76400 | TT_Task | Transport Carbody to Henningsdorf for Trainset #015 DM1 | 16/03/2023 | 10/05/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 355 | 94810358_355
A79520 | TT_Task | Transport to Sweden for Trainset #015 | 26/07/2023 | 31/07/2023 | nan | nan | 3712 | TK_NotStart | 94810358 | 427 | 94810358_427
A175040 | TT_Task | Fitout 2.8 for Trainset #015 DM1 | 23/05/2023 | 26/05/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 411 | 94810358_411
A175050 | TT_Task | Fitout 2.9 for Trainset #015 DM1 | 30/05/2023 | 02/06/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 451 | 94810358_451
A175060 | TT_Task | Single Car Testing for Trainset #015 DM1 | 05/06/2023 | 08/06/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 412 | 94810358_412
A182880 | TT_Task | HP2 for Trainset #015 DM1 | 09/06/2023 | 14/06/2023 | nan | nan | 64 | TK_NotStart | 94810358 | 421 | 94810358_421
A47050 | TT_Task | Tempering of CBY for Trainset #015 DM1 | 11/05/2023 | 11/05/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 375 | 94810358_375
A47140 | TT_Task | Fitout 2.7 for Trainset #015 DM1 | 12/05/2023 | 22/05/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 414 | 94810358_414
A175070 | TT_Task | Tempering of CBY for Trainset #015 DM2 | 22/05/2023 | 22/05/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 376 | 94810358_376
A175080 | TT_Task | Fitout 2.8 for Trainset #015 DM2 | 30/05/2023 | 02/06/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 415 | 94810358_415
A175090 | TT_Task | Fitout 2.9 for Trainset #015 DM2 | 05/06/2023 | 08/06/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 452 | 94810358_452
A175100 | TT_Task | Single Car Testing for Trainset #015 DM2 | 09/06/2023 | 14/06/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 416 | 94810358_416
A182890 | TT_Task | HP2 for Trainset #015 DM2 | 15/06/2023 | 20/06/2023 | nan | nan | 32 | TK_NotStart | 94810358 | 422 | 94810358_422
A47150 | TT_Task | Fitout 2.7 for Trainset #015 DM2 | 23/05/2023 | 26/05/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 417 | 94810358_417
A175110 | TT_Task | Tempering of CBY for Trainset #015 T | 26/05/2023 | 26/05/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 380 | 94810358_380
A175120 | TT_Task | Fitout 2.8 for Trainset #015 T | 05/06/2023 | 08/06/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 381 | 94810358_381
A175130 | TT_Task | Fitout 2.9 for Trainset #015 T | 09/06/2023 | 14/06/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 453 | 94810358_453
A175140 | TT_Task | Single Car Testing for Trainset #015 T | 15/06/2023 | 20/06/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 418 | 94810358_418
A182900 | TT_Task | HP2 for Trainset #015 T | 21/06/2023 | 26/06/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 401 | 94810358_401
A47160 | TT_Task | Fitout 2.7 for Trainset #015 T | 30/05/2023 | 02/06/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 419 | 94810358_419
A47110 | TT_Task | Train Completion for Trainset #015 | 22/06/2023 | 11/07/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 396 | 94810358_396
A47130 | TT_Task | Commissioning for Trainset #015 | 23/06/2023 | 07/07/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 312 | 94810358_312
A80520 | TT_Task | Quality/Customer Acceptance for Trainset #015 | 10/07/2023 | 25/07/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 454 | 94810358_454
A14660 | TT_Task | Preliminary Takeover Inspection for Trainset #015 | 07/11/2024 | 04/12/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 455 | 94810358_455
A14670 | TT_Task | Final Takeover Inspection for Trainset #015 | 17/09/2025 | 14/10/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 406 | 94810358_406
A63480 | TT_Task | Final Assembly for Trainset #016 DM1 | 09/12/2022 | 04/04/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 350 | 94810358_350
A180680 | TT_Task | Final Assembly for Trainset #016 DM2 | 16/12/2022 | 25/04/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 351 | 94810358_351
A180690 | TT_Task | Final Assembly for Trainset #016 T | 23/12/2022 | 02/05/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 352 | 94810358_352
A181860 | TT_Task | Transport Carbody to Henningsdorf for Trainset #016 T | 19/04/2023 | 13/06/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 356 | 94810358_356
A181870 | TT_Task | Transport Carbody to Henningsdorf for Trainset #016 DM2 | 13/04/2023 | 07/06/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 354 | 94810358_354
A76430 | TT_Task | Transport Carbody to Henningsdorf for Trainset #016 DM1 | 07/04/2023 | 01/06/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 355 | 94810358_355
A79530 | TT_Task | Transport to Sweden for Trainset #016 | 16/08/2023 | 21/08/2023 | nan | nan | 3768 | TK_NotStart | 94810358 | 427 | 94810358_427
A175210 | TT_Task | Fitout 2.8 for Trainset #016 DM1 | 09/06/2023 | 14/06/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 411 | 94810358_411
A175220 | TT_Task | Fitout 2.9 for Trainset #016 DM1 | 15/06/2023 | 20/06/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 451 | 94810358_451
A175230 | TT_Task | Single Car Testing for Trainset #016 DM1 | 21/06/2023 | 26/06/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 412 | 94810358_412
A182910 | TT_Task | HP2 for Trainset #016 DM1 | 27/06/2023 | 03/07/2023 | nan | nan | 64 | TK_NotStart | 94810358 | 421 | 94810358_421
A47220 | TT_Task | Tempering of CBY for Trainset #016 DM1 | 02/06/2023 | 02/06/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 375 | 94810358_375
A47310 | TT_Task | Fitout 2.7 for Trainset #016 DM1 | 05/06/2023 | 08/06/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 414 | 94810358_414
A175240 | TT_Task | Tempering of CBY for Trainset #016 DM2 | 08/06/2023 | 08/06/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 376 | 94810358_376
A175250 | TT_Task | Fitout 2.8 for Trainset #016 DM2 | 15/06/2023 | 20/06/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 415 | 94810358_415
A175260 | TT_Task | Fitout 2.9 for Trainset #016 DM2 | 21/06/2023 | 26/06/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 452 | 94810358_452
A175270 | TT_Task | Single Car Testing for Trainset #016 DM2 | 27/06/2023 | 03/07/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 416 | 94810358_416
A182920 | TT_Task | HP2 for Trainset #016 DM2 | 04/07/2023 | 07/07/2023 | nan | nan | 32 | TK_NotStart | 94810358 | 422 | 94810358_422
A47320 | TT_Task | Fitout 2.7 for Trainset #016 DM2 | 09/06/2023 | 14/06/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 417 | 94810358_417
A175280 | TT_Task | Tempering of CBY for Trainset #016 T | 14/06/2023 | 14/06/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 380 | 94810358_380
A175290 | TT_Task | Fitout 2.8 for Trainset #016 T | 21/06/2023 | 26/06/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 381 | 94810358_381
A175300 | TT_Task | Fitout 2.9 for Trainset #016 T | 27/06/2023 | 03/07/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 453 | 94810358_453
A175310 | TT_Task | Single Car Testing for Trainset #016 T | 04/07/2023 | 07/07/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 418 | 94810358_418
A182930 | TT_Task | HP2 for Trainset #016 T | 10/07/2023 | 14/07/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 401 | 94810358_401
A47330 | TT_Task | Fitout 2.7 for Trainset #016 T | 15/06/2023 | 20/06/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 419 | 94810358_419
A47280 | TT_Task | Train Completion for Trainset #016 | 11/07/2023 | 01/08/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 396 | 94810358_396
A47300 | TT_Task | Commissioning for Trainset #016 | 13/07/2023 | 28/07/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 312 | 94810358_312
A80530 | TT_Task | Quality/Customer Acceptance for Trainset #016 | 31/07/2023 | 15/08/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 454 | 94810358_454
A14770 | TT_Task | Preliminary Takeover Inspection for Trainset #016 | 05/12/2024 | 01/01/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 455 | 94810358_455
A14780 | TT_Task | Final Takeover Inspection for Trainset #016 | 17/09/2025 | 14/10/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 406 | 94810358_406
A63600 | TT_Task | Final Assembly for Trainset #017 DM1 | 28/12/2022 | 21/04/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 350 | 94810358_350
A180710 | TT_Task | Final Assembly for Trainset #017 DM2 | 04/01/2023 | 12/05/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 351 | 94810358_351
A180720 | TT_Task | Final Assembly for Trainset #017 T | 11/01/2023 | 19/05/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 352 | 94810358_352
A181880 | TT_Task | Transport Carbody to Henningsdorf for Trainset #017 T | 08/05/2023 | 02/07/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 356 | 94810358_356
A181890 | TT_Task | Transport Carbody to Henningsdorf for Trainset #017 DM2 | 01/05/2023 | 25/06/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 354 | 94810358_354
A76460 | TT_Task | Transport Carbody to Henningsdorf for Trainset #017 DM1 | 25/04/2023 | 19/06/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 355 | 94810358_355
A79540 | TT_Task | Transport to Sweden for Trainset #017 | 02/09/2023 | 07/09/2023 | nan | nan | 3632 | TK_NotStart | 94810358 | 427 | 94810358_427
A175380 | TT_Task | Fitout 2.8 for Trainset #017 DM1 | 27/06/2023 | 03/07/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 411 | 94810358_411
A175390 | TT_Task | Fitout 2.9 for Trainset #017 DM1 | 04/07/2023 | 07/07/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 451 | 94810358_451
A175400 | TT_Task | Single Car Testing for Trainset #017 DM1 | 10/07/2023 | 14/07/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 412 | 94810358_412
A182940 | TT_Task | HP2 for Trainset #017 DM1 | 17/07/2023 | 21/07/2023 | nan | nan | 64 | TK_NotStart | 94810358 | 421 | 94810358_421
A47390 | TT_Task | Tempering of CBY for Trainset #017 DM1 | 20/06/2023 | 20/06/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 375 | 94810358_375
A47480 | TT_Task | Fitout 2.7 for Trainset #017 DM1 | 21/06/2023 | 26/06/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 414 | 94810358_414
A175410 | TT_Task | Tempering of CBY for Trainset #017 DM2 | 26/06/2023 | 26/06/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 376 | 94810358_376
A175420 | TT_Task | Fitout 2.8 for Trainset #017 DM2 | 04/07/2023 | 07/07/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 415 | 94810358_415
A175430 | TT_Task | Fitout 2.9 for Trainset #017 DM2 | 10/07/2023 | 14/07/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 452 | 94810358_452
A175440 | TT_Task | Single Car Testing for Trainset #017 DM2 | 17/07/2023 | 21/07/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 416 | 94810358_416
A182950 | TT_Task | HP2 for Trainset #017 DM2 | 24/07/2023 | 28/07/2023 | nan | nan | 32 | TK_NotStart | 94810358 | 422 | 94810358_422
A47490 | TT_Task | Fitout 2.7 for Trainset #017 DM2 | 27/06/2023 | 03/07/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 417 | 94810358_417
A175450 | TT_Task | Tempering of CBY for Trainset #017 T | 03/07/2023 | 03/07/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 380 | 94810358_380
A175460 | TT_Task | Fitout 2.8 for Trainset #017 T | 10/07/2023 | 14/07/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 381 | 94810358_381
A175470 | TT_Task | Fitout 2.9 for Trainset #017 T | 17/07/2023 | 21/07/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 453 | 94810358_453
A175480 | TT_Task | Single Car Testing for Trainset #017 T | 24/07/2023 | 28/07/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 418 | 94810358_418
A182960 | TT_Task | HP2 for Trainset #017 T | 31/07/2023 | 04/08/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 401 | 94810358_401
A47500 | TT_Task | Fitout 2.7 for Trainset #017 T | 04/07/2023 | 07/07/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 419 | 94810358_419
A47450 | TT_Task | Train Completion for Trainset #017 | 01/08/2023 | 22/08/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 396 | 94810358_396
A47470 | TT_Task | Commissioning for Trainset #017 | 03/08/2023 | 18/08/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 312 | 94810358_312
A80540 | TT_Task | Quality/Customer Acceptance for Trainset #017 | 21/08/2023 | 01/09/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 454 | 94810358_454
A14880 | TT_Task | Preliminary Takeover Inspection for Trainset #017 | 05/12/2024 | 01/01/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 455 | 94810358_455
A14890 | TT_Task | Final Takeover Inspection for Trainset #017 | 17/09/2025 | 14/10/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 406 | 94810358_406
A63720 | TT_Task | Final Assembly for Trainset #018 DM1 | 17/01/2023 | 11/05/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 350 | 94810358_350
A180740 | TT_Task | Final Assembly for Trainset #018 DM2 | 24/01/2023 | 01/06/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 351 | 94810358_351
A180750 | TT_Task | Final Assembly for Trainset #018 T | 31/01/2023 | 08/06/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 352 | 94810358_352
A181900 | TT_Task | Transport Carbody to Henningsdorf for Trainset #018 T | 26/05/2023 | 20/07/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 356 | 94810358_356
A181910 | TT_Task | Transport Carbody to Henningsdorf for Trainset #018 DM2 | 19/05/2023 | 13/07/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 354 | 94810358_354
A76490 | TT_Task | Transport Carbody to Henningsdorf for Trainset #018 DM1 | 12/05/2023 | 06/07/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 355 | 94810358_355
A79550 | TT_Task | Transport to Sweden for Trainset #018 | 20/09/2023 | 25/09/2023 | nan | nan | 3712 | TK_NotStart | 94810358 | 427 | 94810358_427
A175550 | TT_Task | Fitout 2.8 for Trainset #018 DM1 | 17/07/2023 | 21/07/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 411 | 94810358_411
A175560 | TT_Task | Fitout 2.9 for Trainset #018 DM1 | 24/07/2023 | 28/07/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 451 | 94810358_451
A175570 | TT_Task | Single Car Testing for Trainset #018 DM1 | 31/07/2023 | 04/08/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 412 | 94810358_412
A182970 | TT_Task | HP2 for Trainset #018 DM1 | 07/08/2023 | 11/08/2023 | nan | nan | 64 | TK_NotStart | 94810358 | 421 | 94810358_421
A47560 | TT_Task | Tempering of CBY for Trainset #018 DM1 | 07/07/2023 | 07/07/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 375 | 94810358_375
A47650 | TT_Task | Fitout 2.7 for Trainset #018 DM1 | 10/07/2023 | 14/07/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 414 | 94810358_414
A175580 | TT_Task | Tempering of CBY for Trainset #018 DM2 | 14/07/2023 | 14/07/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 376 | 94810358_376
A175590 | TT_Task | Fitout 2.8 for Trainset #018 DM2 | 24/07/2023 | 28/07/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 415 | 94810358_415
A175600 | TT_Task | Fitout 2.9 for Trainset #018 DM2 | 31/07/2023 | 04/08/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 452 | 94810358_452
A175610 | TT_Task | Single Car Testing for Trainset #018 DM2 | 07/08/2023 | 11/08/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 416 | 94810358_416
A182980 | TT_Task | HP2 for Trainset #018 DM2 | 14/08/2023 | 18/08/2023 | nan | nan | 32 | TK_NotStart | 94810358 | 422 | 94810358_422
A47660 | TT_Task | Fitout 2.7 for Trainset #018 DM2 | 17/07/2023 | 21/07/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 417 | 94810358_417
A175620 | TT_Task | Tempering of CBY for Trainset #018 T | 21/07/2023 | 21/07/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 380 | 94810358_380
A175630 | TT_Task | Fitout 2.8 for Trainset #018 T | 31/07/2023 | 04/08/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 381 | 94810358_381
A175640 | TT_Task | Fitout 2.9 for Trainset #018 T | 07/08/2023 | 11/08/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 453 | 94810358_453
A175650 | TT_Task | Single Car Testing for Trainset #018 T | 14/08/2023 | 18/08/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 418 | 94810358_418
A182990 | TT_Task | HP2 for Trainset #018 T | 21/08/2023 | 24/08/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 401 | 94810358_401
A47670 | TT_Task | Fitout 2.7 for Trainset #018 T | 24/07/2023 | 28/07/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 419 | 94810358_419
A47620 | TT_Task | Train Completion for Trainset #018 | 22/08/2023 | 07/09/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 396 | 94810358_396
A47640 | TT_Task | Commissioning for Trainset #018 | 23/08/2023 | 05/09/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 312 | 94810358_312
A80550 | TT_Task | Quality/Customer Acceptance for Trainset #018 | 06/09/2023 | 19/09/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 454 | 94810358_454
A14990 | TT_Task | Preliminary Takeover Inspection for Trainset #018 | 02/01/2025 | 29/01/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 455 | 94810358_455
A15000 | TT_Task | Final Takeover Inspection for Trainset #018 | 17/09/2025 | 14/10/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 406 | 94810358_406
A63840 | TT_Task | Final Assembly for Trainset #019 DM1 | 07/02/2023 | 01/06/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 350 | 94810358_350
A180770 | TT_Task | Final Assembly for Trainset #019 DM2 | 14/02/2023 | 22/06/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 351 | 94810358_351
A180780 | TT_Task | Final Assembly for Trainset #019 T | 21/02/2023 | 29/06/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 352 | 94810358_352
A181920 | TT_Task | Transport Carbody to Henningsdorf for Trainset #019 T | 16/06/2023 | 10/08/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 356 | 94810358_356
A181930 | TT_Task | Transport Carbody to Henningsdorf for Trainset #019 DM2 | 09/06/2023 | 03/08/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 354 | 94810358_354
A76520 | TT_Task | Transport Carbody to Henningsdorf for Trainset #019 DM1 | 02/06/2023 | 27/07/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 355 | 94810358_355
A79560 | TT_Task | Transport to Sweden for Trainset #019 | 11/10/2023 | 16/10/2023 | nan | nan | 3544 | TK_NotStart | 94810358 | 427 | 94810358_427
A175720 | TT_Task | Fitout 2.8 for Trainset #019 DM1 | 07/08/2023 | 11/08/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 411 | 94810358_411
A175730 | TT_Task | Fitout 2.9 for Trainset #019 DM1 | 14/08/2023 | 18/08/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 451 | 94810358_451
A175740 | TT_Task | Single Car Testing for Trainset #019 DM1 | 21/08/2023 | 24/08/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 412 | 94810358_412
A183000 | TT_Task | HP2 for Trainset #019 DM1 | 25/08/2023 | 30/08/2023 | nan | nan | 64 | TK_NotStart | 94810358 | 421 | 94810358_421
A47730 | TT_Task | Tempering of CBY for Trainset #019 DM1 | 28/07/2023 | 28/07/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 375 | 94810358_375
A47820 | TT_Task | Fitout 2.7 for Trainset #019 DM1 | 31/07/2023 | 04/08/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 414 | 94810358_414
A175750 | TT_Task | Tempering of CBY for Trainset #019 DM2 | 04/08/2023 | 04/08/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 376 | 94810358_376
A175760 | TT_Task | Fitout 2.8 for Trainset #019 DM2 | 14/08/2023 | 18/08/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 415 | 94810358_415
A175770 | TT_Task | Fitout 2.9 for Trainset #019 DM2 | 21/08/2023 | 24/08/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 452 | 94810358_452
A175780 | TT_Task | Single Car Testing for Trainset #019 DM2 | 25/08/2023 | 30/08/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 416 | 94810358_416
A183010 | TT_Task | HP2 for Trainset #019 DM2 | 31/08/2023 | 05/09/2023 | nan | nan | 32 | TK_NotStart | 94810358 | 422 | 94810358_422
A47830 | TT_Task | Fitout 2.7 for Trainset #019 DM2 | 07/08/2023 | 11/08/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 417 | 94810358_417
A175790 | TT_Task | Tempering of CBY for Trainset #019 T | 11/08/2023 | 11/08/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 380 | 94810358_380
A175800 | TT_Task | Fitout 2.8 for Trainset #019 T | 21/08/2023 | 24/08/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 381 | 94810358_381
A175810 | TT_Task | Fitout 2.9 for Trainset #019 T | 25/08/2023 | 30/08/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 453 | 94810358_453
A175820 | TT_Task | Single Car Testing for Trainset #019 T | 31/08/2023 | 05/09/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 418 | 94810358_418
A183020 | TT_Task | HP2 for Trainset #019 T | 06/09/2023 | 11/09/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 401 | 94810358_401
A47840 | TT_Task | Fitout 2.7 for Trainset #019 T | 14/08/2023 | 18/08/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 419 | 94810358_419
A47790 | TT_Task | Train Completion for Trainset #019 | 07/09/2023 | 25/09/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 396 | 94810358_396
A47810 | TT_Task | Commissioning for Trainset #019 | 08/09/2023 | 21/09/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 312 | 94810358_312
A80560 | TT_Task | Quality/Customer Acceptance for Trainset #019 | 22/09/2023 | 10/10/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 454 | 94810358_454
A15100 | TT_Task | Preliminary Takeover Inspection for Trainset #019 | 02/01/2025 | 29/01/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 455 | 94810358_455
A15110 | TT_Task | Final Takeover Inspection for Trainset #019 | 17/09/2025 | 14/10/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 406 | 94810358_406
A63960 | TT_Task | Final Assembly for Trainset #020 DM1 | 24/02/2023 | 20/06/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 350 | 94810358_350
A180800 | TT_Task | Final Assembly for Trainset #020 DM2 | 03/03/2023 | 11/07/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 351 | 94810358_351
A180810 | TT_Task | Final Assembly for Trainset #020 T | 10/03/2023 | 18/07/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 352 | 94810358_352
A181940 | TT_Task | Transport Carbody to Henningsdorf for Trainset #020 T | 05/07/2023 | 29/08/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 356 | 94810358_356
A181950 | TT_Task | Transport Carbody to Henningsdorf for Trainset #020 DM2 | 29/06/2023 | 23/08/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 354 | 94810358_354
A76550 | TT_Task | Transport Carbody to Henningsdorf for Trainset #020 DM1 | 23/06/2023 | 17/08/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 355 | 94810358_355
A79570 | TT_Task | Transport to Sweden for Trainset #020 | 02/11/2023 | 07/11/2023 | nan | nan | 3592 | TK_NotStart | 94810358 | 427 | 94810358_427
A175890 | TT_Task | Fitout 2.8 for Trainset #020 DM1 | 25/08/2023 | 30/08/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 411 | 94810358_411
A175900 | TT_Task | Fitout 2.9 for Trainset #020 DM1 | 31/08/2023 | 05/09/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 451 | 94810358_451
A175910 | TT_Task | Single Car Testing for Trainset #020 DM1 | 06/09/2023 | 11/09/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 412 | 94810358_412
A183030 | TT_Task | HP2 for Trainset #020 DM1 | 12/09/2023 | 15/09/2023 | nan | nan | 64 | TK_NotStart | 94810358 | 421 | 94810358_421
A47900 | TT_Task | Tempering of CBY for Trainset #020 DM1 | 18/08/2023 | 18/08/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 375 | 94810358_375
A47990 | TT_Task | Fitout 2.7 for Trainset #020 DM1 | 21/08/2023 | 24/08/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 414 | 94810358_414
A175920 | TT_Task | Tempering of CBY for Trainset #020 DM2 | 24/08/2023 | 24/08/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 376 | 94810358_376
A175930 | TT_Task | Fitout 2.8 for Trainset #020 DM2 | 31/08/2023 | 05/09/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 415 | 94810358_415
A175940 | TT_Task | Fitout 2.9 for Trainset #020 DM2 | 06/09/2023 | 11/09/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 452 | 94810358_452
A175950 | TT_Task | Single Car Testing for Trainset #020 DM2 | 12/09/2023 | 15/09/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 416 | 94810358_416
A183040 | TT_Task | HP2 for Trainset #020 DM2 | 18/09/2023 | 21/09/2023 | nan | nan | 32 | TK_NotStart | 94810358 | 422 | 94810358_422
A48000 | TT_Task | Fitout 2.7 for Trainset #020 DM2 | 25/08/2023 | 30/08/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 417 | 94810358_417
A175960 | TT_Task | Tempering of CBY for Trainset #020 T | 30/08/2023 | 30/08/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 380 | 94810358_380
A175970 | TT_Task | Fitout 2.8 for Trainset #020 T | 06/09/2023 | 11/09/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 381 | 94810358_381
A175980 | TT_Task | Fitout 2.9 for Trainset #020 T | 12/09/2023 | 15/09/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 453 | 94810358_453
A175990 | TT_Task | Single Car Testing for Trainset #020 T | 18/09/2023 | 21/09/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 418 | 94810358_418
A183050 | TT_Task | HP2 for Trainset #020 T | 22/09/2023 | 27/09/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 401 | 94810358_401
A48010 | TT_Task | Fitout 2.7 for Trainset #020 T | 31/08/2023 | 05/09/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 419 | 94810358_419
A47960 | TT_Task | Train Completion for Trainset #020 | 25/09/2023 | 17/10/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 396 | 94810358_396
A47980 | TT_Task | Commissioning for Trainset #020 | 26/09/2023 | 13/10/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 312 | 94810358_312
A80570 | TT_Task | Quality/Customer Acceptance for Trainset #020 | 16/10/2023 | 01/11/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 454 | 94810358_454
A15210 | TT_Task | Preliminary Takeover Inspection for Trainset #020 | 30/01/2025 | 26/02/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 455 | 94810358_455
A15220 | TT_Task | Final Takeover Inspection for Trainset #020 | 17/09/2025 | 14/10/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 406 | 94810358_406
A64080 | TT_Task | Final Assembly for Trainset #021 DM1 | 14/03/2023 | 06/07/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 350 | 94810358_350
A180830 | TT_Task | Final Assembly for Trainset #021 DM2 | 21/03/2023 | 27/07/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 351 | 94810358_351
A180840 | TT_Task | Final Assembly for Trainset #021 T | 28/03/2023 | 03/08/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 352 | 94810358_352
A181960 | TT_Task | Transport Carbody to Henningsdorf for Trainset #021 T | 21/07/2023 | 14/09/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 356 | 94810358_356
A181970 | TT_Task | Transport Carbody to Henningsdorf for Trainset #021 DM2 | 17/07/2023 | 10/09/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 354 | 94810358_354
A76580 | TT_Task | Transport Carbody to Henningsdorf for Trainset #021 DM1 | 11/07/2023 | 04/09/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 355 | 94810358_355
A79580 | TT_Task | Transport to Sweden for Trainset #021 | 21/11/2023 | 26/11/2023 | nan | nan | 3440 | TK_NotStart | 94810358 | 427 | 94810358_427
A176060 | TT_Task | Fitout 2.8 for Trainset #021 DM1 | 12/09/2023 | 15/09/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 411 | 94810358_411
A176070 | TT_Task | Fitout 2.9 for Trainset #021 DM1 | 18/09/2023 | 21/09/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 451 | 94810358_451
A176080 | TT_Task | Single Car Testing for Trainset #021 DM1 | 22/09/2023 | 27/09/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 412 | 94810358_412
A183060 | TT_Task | HP2 for Trainset #021 DM1 | 28/09/2023 | 06/10/2023 | nan | nan | 64 | TK_NotStart | 94810358 | 421 | 94810358_421
A48070 | TT_Task | Tempering of CBY for Trainset #021 DM1 | 05/09/2023 | 05/09/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 375 | 94810358_375
A48160 | TT_Task | Fitout 2.7 for Trainset #021 DM1 | 06/09/2023 | 11/09/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 414 | 94810358_414
A176090 | TT_Task | Tempering of CBY for Trainset #021 DM2 | 11/09/2023 | 11/09/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 376 | 94810358_376
A176100 | TT_Task | Fitout 2.8 for Trainset #021 DM2 | 18/09/2023 | 21/09/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 415 | 94810358_415
A176110 | TT_Task | Fitout 2.9 for Trainset #021 DM2 | 22/09/2023 | 27/09/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 452 | 94810358_452
A176120 | TT_Task | Single Car Testing for Trainset #021 DM2 | 28/09/2023 | 06/10/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 416 | 94810358_416
A183070 | TT_Task | HP2 for Trainset #021 DM2 | 09/10/2023 | 13/10/2023 | nan | nan | 32 | TK_NotStart | 94810358 | 422 | 94810358_422
A48170 | TT_Task | Fitout 2.7 for Trainset #021 DM2 | 12/09/2023 | 15/09/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 417 | 94810358_417
A176130 | TT_Task | Tempering of CBY for Trainset #021 T | 15/09/2023 | 15/09/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 380 | 94810358_380
A176140 | TT_Task | Fitout 2.8 for Trainset #021 T | 22/09/2023 | 27/09/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 381 | 94810358_381
A176150 | TT_Task | Fitout 2.9 for Trainset #021 T | 28/09/2023 | 06/10/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 453 | 94810358_453
A176160 | TT_Task | Single Car Testing for Trainset #021 T | 09/10/2023 | 13/10/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 418 | 94810358_418
A183080 | TT_Task | HP2 for Trainset #021 T | 16/10/2023 | 20/10/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 401 | 94810358_401
A48180 | TT_Task | Fitout 2.7 for Trainset #021 T | 18/09/2023 | 21/09/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 419 | 94810358_419
A48130 | TT_Task | Train Completion for Trainset #021 | 17/10/2023 | 08/11/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 396 | 94810358_396
A48150 | TT_Task | Commissioning for Trainset #021 | 19/10/2023 | 03/11/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 312 | 94810358_312
A80580 | TT_Task | Quality/Customer Acceptance for Trainset #021 | 06/11/2023 | 20/11/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 454 | 94810358_454
A15320 | TT_Task | Preliminary Takeover Inspection for Trainset #021 | 30/01/2025 | 26/02/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 455 | 94810358_455
A15330 | TT_Task | Final Takeover Inspection for Trainset #021 | 17/09/2025 | 14/10/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 406 | 94810358_406
A64200 | TT_Task | Final Assembly for Trainset #022 DM1 | 31/03/2023 | 25/07/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 350 | 94810358_350
A180860 | TT_Task | Final Assembly for Trainset #022 DM2 | 07/04/2023 | 15/08/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 351 | 94810358_351
A180870 | TT_Task | Final Assembly for Trainset #022 T | 18/04/2023 | 24/08/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 352 | 94810358_352
A181980 | TT_Task | Transport Carbody to Henningsdorf for Trainset #022 T | 11/08/2023 | 05/10/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 356 | 94810358_356
A181990 | TT_Task | Transport Carbody to Henningsdorf for Trainset #022 DM2 | 02/08/2023 | 26/09/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 354 | 94810358_354
A76610 | TT_Task | Transport Carbody to Henningsdorf for Trainset #022 DM1 | 27/07/2023 | 20/09/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 355 | 94810358_355
A79590 | TT_Task | Transport to Sweden for Trainset #022 | 07/12/2023 | 12/12/2023 | nan | nan | 3536 | TK_NotStart | 94810358 | 427 | 94810358_427
A176230 | TT_Task | Fitout 2.8 for Trainset #022 DM1 | 28/09/2023 | 06/10/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 411 | 94810358_411
A176240 | TT_Task | Fitout 2.9 for Trainset #022 DM1 | 09/10/2023 | 13/10/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 451 | 94810358_451
A176250 | TT_Task | Single Car Testing for Trainset #022 DM1 | 16/10/2023 | 20/10/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 412 | 94810358_412
A183090 | TT_Task | HP2 for Trainset #022 DM1 | 23/10/2023 | 26/10/2023 | nan | nan | 64 | TK_NotStart | 94810358 | 421 | 94810358_421
A48240 | TT_Task | Tempering of CBY for Trainset #022 DM1 | 21/09/2023 | 21/09/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 375 | 94810358_375
A48330 | TT_Task | Fitout 2.7 for Trainset #022 DM1 | 22/09/2023 | 27/09/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 414 | 94810358_414
A176260 | TT_Task | Tempering of CBY for Trainset #022 DM2 | 27/09/2023 | 27/09/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 376 | 94810358_376
A176270 | TT_Task | Fitout 2.8 for Trainset #022 DM2 | 09/10/2023 | 13/10/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 415 | 94810358_415
A176280 | TT_Task | Fitout 2.9 for Trainset #022 DM2 | 16/10/2023 | 20/10/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 452 | 94810358_452
A176290 | TT_Task | Single Car Testing for Trainset #022 DM2 | 23/10/2023 | 26/10/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 416 | 94810358_416
A183100 | TT_Task | HP2 for Trainset #022 DM2 | 27/10/2023 | 03/11/2023 | nan | nan | 32 | TK_NotStart | 94810358 | 422 | 94810358_422
A48340 | TT_Task | Fitout 2.7 for Trainset #022 DM2 | 28/09/2023 | 06/10/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 417 | 94810358_417
A176300 | TT_Task | Tempering of CBY for Trainset #022 T | 06/10/2023 | 06/10/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 380 | 94810358_380
A176310 | TT_Task | Fitout 2.8 for Trainset #022 T | 16/10/2023 | 20/10/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 381 | 94810358_381
A176320 | TT_Task | Fitout 2.9 for Trainset #022 T | 23/10/2023 | 26/10/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 453 | 94810358_453
A176330 | TT_Task | Single Car Testing for Trainset #022 T | 27/10/2023 | 03/11/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 418 | 94810358_418
A183110 | TT_Task | HP2 for Trainset #022 T | 06/11/2023 | 10/11/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 401 | 94810358_401
A48350 | TT_Task | Fitout 2.7 for Trainset #022 T | 09/10/2023 | 13/10/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 419 | 94810358_419
A48300 | TT_Task | Train Completion for Trainset #022 | 08/11/2023 | 24/11/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 396 | 94810358_396
A48320 | TT_Task | Commissioning for Trainset #022 | 09/11/2023 | 22/11/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 312 | 94810358_312
A80590 | TT_Task | Quality/Customer Acceptance for Trainset #022 | 23/11/2023 | 06/12/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 454 | 94810358_454
A15430 | TT_Task | Preliminary Takeover Inspection for Trainset #022 | 27/02/2025 | 26/03/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 455 | 94810358_455
A15440 | TT_Task | Final Takeover Inspection for Trainset #022 | 17/09/2025 | 14/10/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 406 | 94810358_406
A64320 | TT_Task | Final Assembly for Trainset #023 DM1 | 24/04/2023 | 16/08/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 350 | 94810358_350
A180890 | TT_Task | Final Assembly for Trainset #023 DM2 | 01/05/2023 | 06/09/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 351 | 94810358_351
A180900 | TT_Task | Final Assembly for Trainset #023 T | 08/05/2023 | 13/09/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 352 | 94810358_352
A182000 | TT_Task | Transport Carbody to Henningsdorf for Trainset #023 T | 31/08/2023 | 25/10/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 356 | 94810358_356
A182010 | TT_Task | Transport Carbody to Henningsdorf for Trainset #023 DM2 | 25/08/2023 | 19/10/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 354 | 94810358_354
A76640 | TT_Task | Transport Carbody to Henningsdorf for Trainset #023 DM1 | 18/08/2023 | 12/10/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 355 | 94810358_355
A79600 | TT_Task | Transport to Sweden for Trainset #023 | 05/01/2024 | 10/01/2024 | nan | nan | 3304 | TK_NotStart | 94810358 | 427 | 94810358_427
A176400 | TT_Task | Fitout 2.8 for Trainset #023 DM1 | 23/10/2023 | 26/10/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 411 | 94810358_411
A176410 | TT_Task | Fitout 2.9 for Trainset #023 DM1 | 27/10/2023 | 03/11/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 451 | 94810358_451
A176420 | TT_Task | Single Car Testing for Trainset #023 DM1 | 06/11/2023 | 10/11/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 412 | 94810358_412
A183120 | TT_Task | HP2 for Trainset #023 DM1 | 13/11/2023 | 16/11/2023 | nan | nan | 64 | TK_NotStart | 94810358 | 421 | 94810358_421
A48410 | TT_Task | Tempering of CBY for Trainset #023 DM1 | 13/10/2023 | 13/10/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 375 | 94810358_375
A48500 | TT_Task | Fitout 2.7 for Trainset #023 DM1 | 16/10/2023 | 20/10/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 414 | 94810358_414
A176430 | TT_Task | Tempering of CBY for Trainset #023 DM2 | 20/10/2023 | 20/10/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 376 | 94810358_376
A176440 | TT_Task | Fitout 2.8 for Trainset #023 DM2 | 27/10/2023 | 03/11/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 415 | 94810358_415
A176450 | TT_Task | Fitout 2.9 for Trainset #023 DM2 | 06/11/2023 | 10/11/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 452 | 94810358_452
A176460 | TT_Task | Single Car Testing for Trainset #023 DM2 | 13/11/2023 | 16/11/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 416 | 94810358_416
A183130 | TT_Task | HP2 for Trainset #023 DM2 | 17/11/2023 | 22/11/2023 | nan | nan | 32 | TK_NotStart | 94810358 | 422 | 94810358_422
A48510 | TT_Task | Fitout 2.7 for Trainset #023 DM2 | 23/10/2023 | 26/10/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 417 | 94810358_417
A176470 | TT_Task | Tempering of CBY for Trainset #023 T | 26/10/2023 | 26/10/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 380 | 94810358_380
A176480 | TT_Task | Fitout 2.8 for Trainset #023 T | 06/11/2023 | 10/11/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 381 | 94810358_381
A176490 | TT_Task | Fitout 2.9 for Trainset #023 T | 13/11/2023 | 16/11/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 453 | 94810358_453
A176500 | TT_Task | Single Car Testing for Trainset #023 T | 17/11/2023 | 22/11/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 418 | 94810358_418
A183140 | TT_Task | HP2 for Trainset #023 T | 23/11/2023 | 28/11/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 401 | 94810358_401
A48520 | TT_Task | Fitout 2.7 for Trainset #023 T | 27/10/2023 | 03/11/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 419 | 94810358_419
A48470 | TT_Task | Train Completion for Trainset #023 | 24/11/2023 | 13/12/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 396 | 94810358_396
A48490 | TT_Task | Commissioning for Trainset #023 | 27/11/2023 | 11/12/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 312 | 94810358_312
A80600 | TT_Task | Quality/Customer Acceptance for Trainset #023 | 12/12/2023 | 04/01/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 454 | 94810358_454
A15540 | TT_Task | Preliminary Takeover Inspection for Trainset #023 | 27/02/2025 | 26/03/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 455 | 94810358_455
A15550 | TT_Task | Final Takeover Inspection for Trainset #023 | 17/09/2025 | 14/10/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 406 | 94810358_406
A64440 | TT_Task | Final Assembly for Trainset #024 DM1 | 15/05/2023 | 06/09/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 350 | 94810358_350
A180920 | TT_Task | Final Assembly for Trainset #024 DM2 | 22/05/2023 | 27/09/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 351 | 94810358_351
A180930 | TT_Task | Final Assembly for Trainset #024 T | 29/05/2023 | 04/10/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 352 | 94810358_352
A182020 | TT_Task | Transport Carbody to Henningsdorf for Trainset #024 T | 21/09/2023 | 15/11/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 356 | 94810358_356
A182030 | TT_Task | Transport Carbody to Henningsdorf for Trainset #024 DM2 | 15/09/2023 | 09/11/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 354 | 94810358_354
A76670 | TT_Task | Transport Carbody to Henningsdorf for Trainset #024 DM1 | 08/09/2023 | 02/11/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 355 | 94810358_355
A79610 | TT_Task | Transport to Sweden for Trainset #024 | 23/01/2024 | 28/01/2024 | nan | nan | 3384 | TK_NotStart | 94810358 | 427 | 94810358_427
A176570 | TT_Task | Fitout 2.8 for Trainset #024 DM1 | 13/11/2023 | 16/11/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 411 | 94810358_411
A176580 | TT_Task | Fitout 2.9 for Trainset #024 DM1 | 17/11/2023 | 22/11/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 451 | 94810358_451
A176590 | TT_Task | Single Car Testing for Trainset #024 DM1 | 23/11/2023 | 28/11/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 412 | 94810358_412
A183150 | TT_Task | HP2 for Trainset #024 DM1 | 29/11/2023 | 04/12/2023 | nan | nan | 64 | TK_NotStart | 94810358 | 421 | 94810358_421
A48580 | TT_Task | Tempering of CBY for Trainset #024 DM1 | 03/11/2023 | 03/11/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 375 | 94810358_375
A48670 | TT_Task | Fitout 2.7 for Trainset #024 DM1 | 06/11/2023 | 10/11/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 414 | 94810358_414
A176600 | TT_Task | Tempering of CBY for Trainset #024 DM2 | 10/11/2023 | 10/11/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 376 | 94810358_376
A176610 | TT_Task | Fitout 2.8 for Trainset #024 DM2 | 17/11/2023 | 22/11/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 415 | 94810358_415
A176620 | TT_Task | Fitout 2.9 for Trainset #024 DM2 | 23/11/2023 | 28/11/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 452 | 94810358_452
A176630 | TT_Task | Single Car Testing for Trainset #024 DM2 | 29/11/2023 | 04/12/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 416 | 94810358_416
A183160 | TT_Task | HP2 for Trainset #024 DM2 | 05/12/2023 | 11/12/2023 | nan | nan | 32 | TK_NotStart | 94810358 | 422 | 94810358_422
A48680 | TT_Task | Fitout 2.7 for Trainset #024 DM2 | 13/11/2023 | 16/11/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 417 | 94810358_417
A176640 | TT_Task | Tempering of CBY for Trainset #024 T | 16/11/2023 | 16/11/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 380 | 94810358_380
A176650 | TT_Task | Fitout 2.8 for Trainset #024 T | 23/11/2023 | 28/11/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 381 | 94810358_381
A176660 | TT_Task | Fitout 2.9 for Trainset #024 T | 29/11/2023 | 04/12/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 453 | 94810358_453
A176670 | TT_Task | Single Car Testing for Trainset #024 T | 05/12/2023 | 11/12/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 418 | 94810358_418
A183170 | TT_Task | HP2 for Trainset #024 T | 12/12/2023 | 15/12/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 401 | 94810358_401
A48690 | TT_Task | Fitout 2.7 for Trainset #024 T | 17/11/2023 | 22/11/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 419 | 94810358_419
A48640 | TT_Task | Train Completion for Trainset #024 | 13/12/2023 | 10/01/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 396 | 94810358_396
A48660 | TT_Task | Commissioning for Trainset #024 | 14/12/2023 | 08/01/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 312 | 94810358_312
A80610 | TT_Task | Quality/Customer Acceptance for Trainset #024 | 09/01/2024 | 22/01/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 454 | 94810358_454
A15650 | TT_Task | Preliminary Takeover Inspection for Trainset #024 | 27/03/2025 | 23/04/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 455 | 94810358_455
A15660 | TT_Task | Final Takeover Inspection for Trainset #024 | 17/09/2025 | 14/10/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 406 | 94810358_406
A64560 | TT_Task | Final Assembly for Trainset #025 DM1 | 31/05/2023 | 22/09/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 350 | 94810358_350
A180950 | TT_Task | Final Assembly for Trainset #025 DM2 | 07/06/2023 | 13/10/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 351 | 94810358_351
A180960 | TT_Task | Final Assembly for Trainset #025 T | 14/06/2023 | 20/10/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 352 | 94810358_352
A182040 | TT_Task | Transport Carbody to Henningsdorf for Trainset #025 T | 09/10/2023 | 03/12/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 356 | 94810358_356
A182050 | TT_Task | Transport Carbody to Henningsdorf for Trainset #025 DM2 | 03/10/2023 | 27/11/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 354 | 94810358_354
A76700 | TT_Task | Transport Carbody to Henningsdorf for Trainset #025 DM1 | 27/09/2023 | 21/11/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 355 | 94810358_355
A79620 | TT_Task | Transport to Sweden for Trainset #025 | 09/02/2024 | 14/02/2024 | nan | nan | 3248 | TK_NotStart | 94810358 | 427 | 94810358_427
A176740 | TT_Task | Fitout 2.8 for Trainset #025 DM1 | 29/11/2023 | 04/12/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 411 | 94810358_411
A176750 | TT_Task | Fitout 2.9 for Trainset #025 DM1 | 05/12/2023 | 11/12/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 451 | 94810358_451
A176760 | TT_Task | Single Car Testing for Trainset #025 DM1 | 12/12/2023 | 15/12/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 412 | 94810358_412
A183180 | TT_Task | HP2 for Trainset #025 DM1 | 18/12/2023 | 21/12/2023 | nan | nan | 64 | TK_NotStart | 94810358 | 421 | 94810358_421
A48750 | TT_Task | Tempering of CBY for Trainset #025 DM1 | 22/11/2023 | 22/11/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 375 | 94810358_375
A48840 | TT_Task | Fitout 2.7 for Trainset #025 DM1 | 23/11/2023 | 28/11/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 414 | 94810358_414
A176770 | TT_Task | Tempering of CBY for Trainset #025 DM2 | 28/11/2023 | 28/11/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 376 | 94810358_376
A176780 | TT_Task | Fitout 2.8 for Trainset #025 DM2 | 05/12/2023 | 11/12/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 415 | 94810358_415
A176790 | TT_Task | Fitout 2.9 for Trainset #025 DM2 | 12/12/2023 | 15/12/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 452 | 94810358_452
A176800 | TT_Task | Single Car Testing for Trainset #025 DM2 | 18/12/2023 | 21/12/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 416 | 94810358_416
A183190 | TT_Task | HP2 for Trainset #025 DM2 | 02/01/2024 | 08/01/2024 | nan | nan | 32 | TK_NotStart | 94810358 | 422 | 94810358_422
A48850 | TT_Task | Fitout 2.7 for Trainset #025 DM2 | 29/11/2023 | 04/12/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 417 | 94810358_417
A176810 | TT_Task | Tempering of CBY for Trainset #025 T | 04/12/2023 | 04/12/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 380 | 94810358_380
A176820 | TT_Task | Fitout 2.8 for Trainset #025 T | 12/12/2023 | 15/12/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 381 | 94810358_381
A176830 | TT_Task | Fitout 2.9 for Trainset #025 T | 18/12/2023 | 21/12/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 453 | 94810358_453
A176840 | TT_Task | Single Car Testing for Trainset #025 T | 02/01/2024 | 08/01/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 418 | 94810358_418
A183200 | TT_Task | HP2 for Trainset #025 T | 09/01/2024 | 12/01/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 401 | 94810358_401
A48860 | TT_Task | Fitout 2.7 for Trainset #025 T | 05/12/2023 | 11/12/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 419 | 94810358_419
A48810 | TT_Task | Train Completion for Trainset #025 | 10/01/2024 | 26/01/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 396 | 94810358_396
A48830 | TT_Task | Commissioning for Trainset #025 | 11/01/2024 | 24/01/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 312 | 94810358_312
A80620 | TT_Task | Quality/Customer Acceptance for Trainset #025 | 25/01/2024 | 08/02/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 454 | 94810358_454
A15760 | TT_Task | Preliminary Takeover Inspection for Trainset #025 | 27/03/2025 | 23/04/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 455 | 94810358_455
A15770 | TT_Task | Final Takeover Inspection for Trainset #025 | 17/09/2025 | 14/10/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 406 | 94810358_406
A64680 | TT_Task | Final Assembly for Trainset #026 DM1 | 19/06/2023 | 11/10/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 350 | 94810358_350
A180980 | TT_Task | Final Assembly for Trainset #026 DM2 | 26/06/2023 | 01/11/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 351 | 94810358_351
A180990 | TT_Task | Final Assembly for Trainset #026 T | 03/07/2023 | 08/11/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 352 | 94810358_352
A182060 | TT_Task | Transport Carbody to Henningsdorf for Trainset #026 T | 26/10/2023 | 20/12/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 356 | 94810358_356
A182070 | TT_Task | Transport Carbody to Henningsdorf for Trainset #026 DM2 | 20/10/2023 | 14/12/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 354 | 94810358_354
A76730 | TT_Task | Transport Carbody to Henningsdorf for Trainset #026 DM1 | 16/10/2023 | 10/12/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 355 | 94810358_355
A79630 | TT_Task | Transport to Sweden for Trainset #026 | 27/02/2024 | 03/03/2024 | nan | nan | 3328 | TK_NotStart | 94810358 | 427 | 94810358_427
A176910 | TT_Task | Fitout 2.8 for Trainset #026 DM1 | 18/12/2023 | 21/12/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 411 | 94810358_411
A176920 | TT_Task | Fitout 2.9 for Trainset #026 DM1 | 02/01/2024 | 08/01/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 451 | 94810358_451
A176930 | TT_Task | Single Car Testing for Trainset #026 DM1 | 09/01/2024 | 12/01/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 412 | 94810358_412
A183210 | TT_Task | HP2 for Trainset #026 DM1 | 15/01/2024 | 18/01/2024 | nan | nan | 64 | TK_NotStart | 94810358 | 421 | 94810358_421
A48920 | TT_Task | Tempering of CBY for Trainset #026 DM1 | 11/12/2023 | 11/12/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 375 | 94810358_375
A49010 | TT_Task | Fitout 2.7 for Trainset #026 DM1 | 12/12/2023 | 15/12/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 414 | 94810358_414
A176940 | TT_Task | Tempering of CBY for Trainset #026 DM2 | 15/12/2023 | 15/12/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 376 | 94810358_376
A176950 | TT_Task | Fitout 2.8 for Trainset #026 DM2 | 02/01/2024 | 08/01/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 415 | 94810358_415
A176960 | TT_Task | Fitout 2.9 for Trainset #026 DM2 | 09/01/2024 | 12/01/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 452 | 94810358_452
A176970 | TT_Task | Single Car Testing for Trainset #026 DM2 | 15/01/2024 | 18/01/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 416 | 94810358_416
A183220 | TT_Task | HP2 for Trainset #026 DM2 | 19/01/2024 | 24/01/2024 | nan | nan | 32 | TK_NotStart | 94810358 | 422 | 94810358_422
A49020 | TT_Task | Fitout 2.7 for Trainset #026 DM2 | 18/12/2023 | 21/12/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 417 | 94810358_417
A176980 | TT_Task | Tempering of CBY for Trainset #026 T | 21/12/2023 | 21/12/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 380 | 94810358_380
A176990 | TT_Task | Fitout 2.8 for Trainset #026 T | 09/01/2024 | 12/01/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 381 | 94810358_381
A177000 | TT_Task | Fitout 2.9 for Trainset #026 T | 15/01/2024 | 18/01/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 453 | 94810358_453
A177010 | TT_Task | Single Car Testing for Trainset #026 T | 19/01/2024 | 24/01/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 418 | 94810358_418
A183230 | TT_Task | HP2 for Trainset #026 T | 25/01/2024 | 30/01/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 401 | 94810358_401
A49030 | TT_Task | Fitout 2.7 for Trainset #026 T | 02/01/2024 | 08/01/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 419 | 94810358_419
A48980 | TT_Task | Train Completion for Trainset #026 | 26/01/2024 | 14/02/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 396 | 94810358_396
A49000 | TT_Task | Commissioning for Trainset #026 | 29/01/2024 | 12/02/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 312 | 94810358_312
A80630 | TT_Task | Quality/Customer Acceptance for Trainset #026 | 13/02/2024 | 26/02/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 454 | 94810358_454
A15870 | TT_Task | Preliminary Takeover Inspection for Trainset #026 | 24/04/2025 | 21/05/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 455 | 94810358_455
A15880 | TT_Task | Final Takeover Inspection for Trainset #026 | 17/09/2025 | 14/10/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 406 | 94810358_406
A64800 | TT_Task | Final Assembly for Trainset #027 DM1 | 17/07/2023 | 08/11/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 350 | 94810358_350
A181010 | TT_Task | Final Assembly for Trainset #027 DM2 | 24/07/2023 | 29/11/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 351 | 94810358_351
A181020 | TT_Task | Final Assembly for Trainset #027 T | 31/07/2023 | 06/12/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 352 | 94810358_352
A182080 | TT_Task | Transport Carbody to Henningsdorf for Trainset #027 T | 23/11/2023 | 17/01/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 356 | 94810358_356
A182090 | TT_Task | Transport Carbody to Henningsdorf for Trainset #027 DM2 | 17/11/2023 | 11/01/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 354 | 94810358_354
A76760 | TT_Task | Transport Carbody to Henningsdorf for Trainset #027 DM1 | 13/11/2023 | 07/01/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 355 | 94810358_355
A79640 | TT_Task | Transport to Sweden for Trainset #027 | 14/03/2024 | 19/03/2024 | nan | nan | 3200 | TK_NotStart | 94810358 | 427 | 94810358_427
A177080 | TT_Task | Fitout 2.8 for Trainset #027 DM1 | 15/01/2024 | 18/01/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 411 | 94810358_411
A177090 | TT_Task | Fitout 2.9 for Trainset #027 DM1 | 19/01/2024 | 24/01/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 451 | 94810358_451
A177100 | TT_Task | Single Car Testing for Trainset #027 DM1 | 25/01/2024 | 30/01/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 412 | 94810358_412
A183240 | TT_Task | HP2 for Trainset #027 DM1 | 31/01/2024 | 05/02/2024 | nan | nan | 64 | TK_NotStart | 94810358 | 421 | 94810358_421
A49090 | TT_Task | Tempering of CBY for Trainset #027 DM1 | 08/01/2024 | 08/01/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 375 | 94810358_375
A49180 | TT_Task | Fitout 2.7 for Trainset #027 DM1 | 09/01/2024 | 12/01/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 414 | 94810358_414
A177110 | TT_Task | Tempering of CBY for Trainset #027 DM2 | 12/01/2024 | 12/01/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 376 | 94810358_376
A177120 | TT_Task | Fitout 2.8 for Trainset #027 DM2 | 19/01/2024 | 24/01/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 415 | 94810358_415
A177130 | TT_Task | Fitout 2.9 for Trainset #027 DM2 | 25/01/2024 | 30/01/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 452 | 94810358_452
A177140 | TT_Task | Single Car Testing for Trainset #027 DM2 | 31/01/2024 | 05/02/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 416 | 94810358_416
A183250 | TT_Task | HP2 for Trainset #027 DM2 | 06/02/2024 | 12/02/2024 | nan | nan | 32 | TK_NotStart | 94810358 | 422 | 94810358_422
A49190 | TT_Task | Fitout 2.7 for Trainset #027 DM2 | 15/01/2024 | 18/01/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 417 | 94810358_417
A177150 | TT_Task | Tempering of CBY for Trainset #027 T | 18/01/2024 | 18/01/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 380 | 94810358_380
A177160 | TT_Task | Fitout 2.8 for Trainset #027 T | 25/01/2024 | 30/01/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 381 | 94810358_381
A177170 | TT_Task | Fitout 2.9 for Trainset #027 T | 31/01/2024 | 05/02/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 453 | 94810358_453
A177180 | TT_Task | Single Car Testing for Trainset #027 T | 06/02/2024 | 12/02/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 418 | 94810358_418
A183260 | TT_Task | HP2 for Trainset #027 T | 13/02/2024 | 16/02/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 401 | 94810358_401
A49200 | TT_Task | Fitout 2.7 for Trainset #027 T | 19/01/2024 | 24/01/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 419 | 94810358_419
A49150 | TT_Task | Train Completion for Trainset #027 | 14/02/2024 | 01/03/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 396 | 94810358_396
A49170 | TT_Task | Commissioning for Trainset #027 | 15/02/2024 | 28/02/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 312 | 94810358_312
A80640 | TT_Task | Quality/Customer Acceptance for Trainset #027 | 29/02/2024 | 13/03/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 454 | 94810358_454
A15980 | TT_Task | Preliminary Takeover Inspection for Trainset #027 | 24/04/2025 | 21/05/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 455 | 94810358_455
A15990 | TT_Task | Final Takeover Inspection for Trainset #027 | 17/09/2025 | 14/10/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 406 | 94810358_406
A64920 | TT_Task | Final Assembly for Trainset #028 DM1 | 02/08/2023 | 24/11/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 350 | 94810358_350
A181040 | TT_Task | Final Assembly for Trainset #028 DM2 | 09/08/2023 | 15/12/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 351 | 94810358_351
A181050 | TT_Task | Final Assembly for Trainset #028 T | 16/08/2023 | 22/12/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 352 | 94810358_352
A182100 | TT_Task | Transport Carbody to Henningsdorf for Trainset #028 T | 11/12/2023 | 04/02/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 356 | 94810358_356
A182110 | TT_Task | Transport Carbody to Henningsdorf for Trainset #028 DM2 | 05/12/2023 | 29/01/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 354 | 94810358_354
A76790 | TT_Task | Transport Carbody to Henningsdorf for Trainset #028 DM1 | 29/11/2023 | 23/01/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 355 | 94810358_355
A79650 | TT_Task | Transport to Sweden for Trainset #028 | 06/04/2024 | 11/04/2024 | nan | nan | 3240 | TK_NotStart | 94810358 | 427 | 94810358_427
A177250 | TT_Task | Fitout 2.8 for Trainset #028 DM1 | 31/01/2024 | 05/02/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 411 | 94810358_411
A177260 | TT_Task | Fitout 2.9 for Trainset #028 DM1 | 06/02/2024 | 12/02/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 451 | 94810358_451
A177270 | TT_Task | Single Car Testing for Trainset #028 DM1 | 13/02/2024 | 16/02/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 412 | 94810358_412
A183270 | TT_Task | HP2 for Trainset #028 DM1 | 19/02/2024 | 22/02/2024 | nan | nan | 64 | TK_NotStart | 94810358 | 421 | 94810358_421
A49260 | TT_Task | Tempering of CBY for Trainset #028 DM1 | 24/01/2024 | 24/01/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 375 | 94810358_375
A49350 | TT_Task | Fitout 2.7 for Trainset #028 DM1 | 25/01/2024 | 30/01/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 414 | 94810358_414
A177280 | TT_Task | Tempering of CBY for Trainset #028 DM2 | 30/01/2024 | 30/01/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 376 | 94810358_376
A177290 | TT_Task | Fitout 2.8 for Trainset #028 DM2 | 06/02/2024 | 12/02/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 415 | 94810358_415
A177300 | TT_Task | Fitout 2.9 for Trainset #028 DM2 | 13/02/2024 | 16/02/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 452 | 94810358_452
A177310 | TT_Task | Single Car Testing for Trainset #028 DM2 | 19/02/2024 | 22/02/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 416 | 94810358_416
A183280 | TT_Task | HP2 for Trainset #028 DM2 | 23/02/2024 | 28/02/2024 | nan | nan | 32 | TK_NotStart | 94810358 | 422 | 94810358_422
A49360 | TT_Task | Fitout 2.7 for Trainset #028 DM2 | 31/01/2024 | 05/02/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 417 | 94810358_417
A177320 | TT_Task | Tempering of CBY for Trainset #028 T | 05/02/2024 | 05/02/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 380 | 94810358_380
A177330 | TT_Task | Fitout 2.8 for Trainset #028 T | 13/02/2024 | 16/02/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 381 | 94810358_381
A177340 | TT_Task | Fitout 2.9 for Trainset #028 T | 19/02/2024 | 22/02/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 453 | 94810358_453
A177350 | TT_Task | Single Car Testing for Trainset #028 T | 23/02/2024 | 28/02/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 418 | 94810358_418
A183290 | TT_Task | HP2 for Trainset #028 T | 29/02/2024 | 05/03/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 401 | 94810358_401
A49370 | TT_Task | Fitout 2.7 for Trainset #028 T | 06/02/2024 | 12/02/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 419 | 94810358_419
A49320 | TT_Task | Train Completion for Trainset #028 | 01/03/2024 | 19/03/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 396 | 94810358_396
A49340 | TT_Task | Commissioning for Trainset #028 | 04/03/2024 | 15/03/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 312 | 94810358_312
A80650 | TT_Task | Quality/Customer Acceptance for Trainset #028 | 18/03/2024 | 05/04/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 454 | 94810358_454
A16090 | TT_Task | Preliminary Takeover Inspection for Trainset #028 | 22/05/2025 | 18/06/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 455 | 94810358_455
A16100 | TT_Task | Final Takeover Inspection for Trainset #028 | 17/09/2025 | 14/10/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 406 | 94810358_406
A65040 | TT_Task | Final Assembly for Trainset #029 DM1 | 21/08/2023 | 13/12/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 350 | 94810358_350
A181070 | TT_Task | Final Assembly for Trainset #029 DM2 | 28/08/2023 | 03/01/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 351 | 94810358_351
A181080 | TT_Task | Final Assembly for Trainset #029 T | 04/09/2023 | 10/01/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 352 | 94810358_352
A182120 | TT_Task | Transport Carbody to Henningsdorf for Trainset #029 T | 28/12/2023 | 21/02/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 356 | 94810358_356
A182130 | TT_Task | Transport Carbody to Henningsdorf for Trainset #029 DM2 | 22/12/2023 | 15/02/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 354 | 94810358_354
A76820 | TT_Task | Transport Carbody to Henningsdorf for Trainset #029 DM1 | 18/12/2023 | 11/02/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 355 | 94810358_355
A79660 | TT_Task | Transport to Sweden for Trainset #029 | 24/04/2024 | 29/04/2024 | nan | nan | 3096 | TK_NotStart | 94810358 | 427 | 94810358_427
A177420 | TT_Task | Fitout 2.8 for Trainset #029 DM1 | 19/02/2024 | 22/02/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 411 | 94810358_411
A177430 | TT_Task | Fitout 2.9 for Trainset #029 DM1 | 23/02/2024 | 28/02/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 451 | 94810358_451
A177440 | TT_Task | Single Car Testing for Trainset #029 DM1 | 29/02/2024 | 05/03/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 412 | 94810358_412
A183300 | TT_Task | HP2 for Trainset #029 DM1 | 06/03/2024 | 11/03/2024 | nan | nan | 64 | TK_NotStart | 94810358 | 421 | 94810358_421
A49430 | TT_Task | Tempering of CBY for Trainset #029 DM1 | 12/02/2024 | 12/02/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 375 | 94810358_375
A49520 | TT_Task | Fitout 2.7 for Trainset #029 DM1 | 13/02/2024 | 16/02/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 414 | 94810358_414
A177450 | TT_Task | Tempering of CBY for Trainset #029 DM2 | 16/02/2024 | 16/02/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 376 | 94810358_376
A177460 | TT_Task | Fitout 2.8 for Trainset #029 DM2 | 23/02/2024 | 28/02/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 415 | 94810358_415
A177470 | TT_Task | Fitout 2.9 for Trainset #029 DM2 | 29/02/2024 | 05/03/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 452 | 94810358_452
A177480 | TT_Task | Single Car Testing for Trainset #029 DM2 | 06/03/2024 | 11/03/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 416 | 94810358_416
A183310 | TT_Task | HP2 for Trainset #029 DM2 | 12/03/2024 | 15/03/2024 | nan | nan | 32 | TK_NotStart | 94810358 | 422 | 94810358_422
A49530 | TT_Task | Fitout 2.7 for Trainset #029 DM2 | 19/02/2024 | 22/02/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 417 | 94810358_417
A177490 | TT_Task | Tempering of CBY for Trainset #029 T | 22/02/2024 | 22/02/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 380 | 94810358_380
A177500 | TT_Task | Fitout 2.8 for Trainset #029 T | 29/02/2024 | 05/03/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 381 | 94810358_381
A177510 | TT_Task | Fitout 2.9 for Trainset #029 T | 06/03/2024 | 11/03/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 453 | 94810358_453
A177520 | TT_Task | Single Car Testing for Trainset #029 T | 12/03/2024 | 15/03/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 418 | 94810358_418
A183320 | TT_Task | HP2 for Trainset #029 T | 18/03/2024 | 21/03/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 401 | 94810358_401
A49540 | TT_Task | Fitout 2.7 for Trainset #029 T | 23/02/2024 | 28/02/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 419 | 94810358_419
A49490 | TT_Task | Train Completion for Trainset #029 | 19/03/2024 | 11/04/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 396 | 94810358_396
A49510 | TT_Task | Commissioning for Trainset #029 | 20/03/2024 | 09/04/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 312 | 94810358_312
A80660 | TT_Task | Quality/Customer Acceptance for Trainset #029 | 10/04/2024 | 23/04/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 454 | 94810358_454
A16200 | TT_Task | Preliminary Takeover Inspection for Trainset #029 | 22/05/2025 | 18/06/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 455 | 94810358_455
A16210 | TT_Task | Final Takeover Inspection for Trainset #029 | 17/09/2025 | 14/10/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 406 | 94810358_406
A65160 | TT_Task | Final Assembly for Trainset #030 DM1 | 06/09/2023 | 29/12/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 350 | 94810358_350
A181100 | TT_Task | Final Assembly for Trainset #030 DM2 | 13/09/2023 | 19/01/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 351 | 94810358_351
A181110 | TT_Task | Final Assembly for Trainset #030 T | 20/09/2023 | 26/01/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 352 | 94810358_352
A182140 | TT_Task | Transport Carbody to Henningsdorf for Trainset #030 T | 15/01/2024 | 10/03/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 356 | 94810358_356
A182150 | TT_Task | Transport Carbody to Henningsdorf for Trainset #030 DM2 | 09/01/2024 | 04/03/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 354 | 94810358_354
A76850 | TT_Task | Transport Carbody to Henningsdorf for Trainset #030 DM1 | 03/01/2024 | 27/02/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 355 | 94810358_355
A79670 | TT_Task | Transport to Sweden for Trainset #030 | 16/05/2024 | 21/05/2024 | nan | nan | 3144 | TK_NotStart | 94810358 | 427 | 94810358_427
A177590 | TT_Task | Fitout 2.8 for Trainset #030 DM1 | 06/03/2024 | 11/03/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 411 | 94810358_411
A177600 | TT_Task | Fitout 2.9 for Trainset #030 DM1 | 12/03/2024 | 15/03/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 451 | 94810358_451
A177610 | TT_Task | Single Car Testing for Trainset #030 DM1 | 18/03/2024 | 21/03/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 412 | 94810358_412
A183330 | TT_Task | HP2 for Trainset #030 DM1 | 25/03/2024 | 02/04/2024 | nan | nan | 64 | TK_NotStart | 94810358 | 421 | 94810358_421
A49600 | TT_Task | Tempering of CBY for Trainset #030 DM1 | 28/02/2024 | 28/02/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 375 | 94810358_375
A49690 | TT_Task | Fitout 2.7 for Trainset #030 DM1 | 29/02/2024 | 05/03/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 414 | 94810358_414
A177620 | TT_Task | Tempering of CBY for Trainset #030 DM2 | 05/03/2024 | 05/03/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 376 | 94810358_376
A177630 | TT_Task | Fitout 2.8 for Trainset #030 DM2 | 12/03/2024 | 15/03/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 415 | 94810358_415
A177640 | TT_Task | Fitout 2.9 for Trainset #030 DM2 | 18/03/2024 | 21/03/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 452 | 94810358_452
A177650 | TT_Task | Single Car Testing for Trainset #030 DM2 | 25/03/2024 | 02/04/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 416 | 94810358_416
A183340 | TT_Task | HP2 for Trainset #030 DM2 | 04/04/2024 | 09/04/2024 | nan | nan | 32 | TK_NotStart | 94810358 | 422 | 94810358_422
A49700 | TT_Task | Fitout 2.7 for Trainset #030 DM2 | 06/03/2024 | 11/03/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 417 | 94810358_417
A177660 | TT_Task | Tempering of CBY for Trainset #030 T | 11/03/2024 | 11/03/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 380 | 94810358_380
A177670 | TT_Task | Fitout 2.8 for Trainset #030 T | 18/03/2024 | 21/03/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 381 | 94810358_381
A177680 | TT_Task | Fitout 2.9 for Trainset #030 T | 25/03/2024 | 02/04/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 453 | 94810358_453
A177690 | TT_Task | Single Car Testing for Trainset #030 T | 04/04/2024 | 09/04/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 418 | 94810358_418
A183350 | TT_Task | HP2 for Trainset #030 T | 10/04/2024 | 15/04/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 401 | 94810358_401
A49710 | TT_Task | Fitout 2.7 for Trainset #030 T | 12/03/2024 | 15/03/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 419 | 94810358_419
A49660 | TT_Task | Train Completion for Trainset #030 | 11/04/2024 | 29/04/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 396 | 94810358_396
A49680 | TT_Task | Commissioning for Trainset #030 | 12/04/2024 | 25/04/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 312 | 94810358_312
A80670 | TT_Task | Quality/Customer Acceptance for Trainset #030 | 26/04/2024 | 15/05/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 454 | 94810358_454
A16310 | TT_Task | Preliminary Takeover Inspection for Trainset #030 | 19/06/2025 | 16/07/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 455 | 94810358_455
A16320 | TT_Task | Final Takeover Inspection for Trainset #030 | 17/09/2025 | 14/10/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 406 | 94810358_406
A65280 | TT_Task | Final Assembly for Trainset #031 DM1 | 25/09/2023 | 17/01/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 350 | 94810358_350
A181130 | TT_Task | Final Assembly for Trainset #031 DM2 | 02/10/2023 | 07/02/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 351 | 94810358_351
A181140 | TT_Task | Final Assembly for Trainset #031 T | 12/10/2023 | 19/02/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 352 | 94810358_352
A182160 | TT_Task | Transport Carbody to Henningsdorf for Trainset #031 T | 06/02/2024 | 01/04/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 356 | 94810358_356
A182170 | TT_Task | Transport Carbody to Henningsdorf for Trainset #031 DM2 | 25/01/2024 | 20/03/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 354 | 94810358_354
A76880 | TT_Task | Transport Carbody to Henningsdorf for Trainset #031 DM1 | 19/01/2024 | 14/03/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 355 | 94810358_355
A79680 | TT_Task | Transport to Sweden for Trainset #031 | 04/06/2024 | 09/06/2024 | nan | nan | 2992 | TK_NotStart | 94810358 | 427 | 94810358_427
A177760 | TT_Task | Fitout 2.8 for Trainset #031 DM1 | 25/03/2024 | 02/04/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 411 | 94810358_411
A177770 | TT_Task | Fitout 2.9 for Trainset #031 DM1 | 04/04/2024 | 09/04/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 451 | 94810358_451
A177780 | TT_Task | Single Car Testing for Trainset #031 DM1 | 10/04/2024 | 15/04/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 412 | 94810358_412
A183360 | TT_Task | HP2 for Trainset #031 DM1 | 16/04/2024 | 19/04/2024 | nan | nan | 64 | TK_NotStart | 94810358 | 421 | 94810358_421
A49770 | TT_Task | Tempering of CBY for Trainset #031 DM1 | 15/03/2024 | 15/03/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 375 | 94810358_375
A49860 | TT_Task | Fitout 2.7 for Trainset #031 DM1 | 18/03/2024 | 21/03/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 414 | 94810358_414
A177790 | TT_Task | Tempering of CBY for Trainset #031 DM2 | 21/03/2024 | 21/03/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 376 | 94810358_376
A177800 | TT_Task | Fitout 2.8 for Trainset #031 DM2 | 04/04/2024 | 09/04/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 415 | 94810358_415
A177810 | TT_Task | Fitout 2.9 for Trainset #031 DM2 | 10/04/2024 | 15/04/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 452 | 94810358_452
A177820 | TT_Task | Single Car Testing for Trainset #031 DM2 | 16/04/2024 | 19/04/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 416 | 94810358_416
A183370 | TT_Task | HP2 for Trainset #031 DM2 | 22/04/2024 | 25/04/2024 | nan | nan | 32 | TK_NotStart | 94810358 | 422 | 94810358_422
A49870 | TT_Task | Fitout 2.7 for Trainset #031 DM2 | 25/03/2024 | 02/04/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 417 | 94810358_417
A177830 | TT_Task | Tempering of CBY for Trainset #031 T | 02/04/2024 | 02/04/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 380 | 94810358_380
A177840 | TT_Task | Fitout 2.8 for Trainset #031 T | 10/04/2024 | 15/04/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 381 | 94810358_381
A177850 | TT_Task | Fitout 2.9 for Trainset #031 T | 16/04/2024 | 19/04/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 453 | 94810358_453
A177860 | TT_Task | Single Car Testing for Trainset #031 T | 22/04/2024 | 25/04/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 418 | 94810358_418
A183380 | TT_Task | HP2 for Trainset #031 T | 26/04/2024 | 02/05/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 401 | 94810358_401
A49880 | TT_Task | Fitout 2.7 for Trainset #031 T | 04/04/2024 | 09/04/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 419 | 94810358_419
A49830 | TT_Task | Train Completion for Trainset #031 | 29/04/2024 | 22/05/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 396 | 94810358_396
A49850 | TT_Task | Commissioning for Trainset #031 | 30/04/2024 | 17/05/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 312 | 94810358_312
A80680 | TT_Task | Quality/Customer Acceptance for Trainset #031 | 21/05/2024 | 03/06/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 454 | 94810358_454
A16420 | TT_Task | Preliminary Takeover Inspection for Trainset #031 | 19/06/2025 | 16/07/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 455 | 94810358_455
A16430 | TT_Task | Final Takeover Inspection for Trainset #031 | 17/09/2025 | 14/10/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 406 | 94810358_406
A65400 | TT_Task | Final Assembly for Trainset #032 DM1 | 17/10/2023 | 08/02/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 350 | 94810358_350
A181160 | TT_Task | Final Assembly for Trainset #032 DM2 | 24/10/2023 | 29/02/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 351 | 94810358_351
A181170 | TT_Task | Final Assembly for Trainset #032 T | 31/10/2023 | 07/03/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 352 | 94810358_352
A182180 | TT_Task | Transport Carbody to Henningsdorf for Trainset #032 T | 23/02/2024 | 18/04/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 356 | 94810358_356
A182190 | TT_Task | Transport Carbody to Henningsdorf for Trainset #032 DM2 | 19/02/2024 | 14/04/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 354 | 94810358_354
A76910 | TT_Task | Transport Carbody to Henningsdorf for Trainset #032 DM1 | 13/02/2024 | 08/04/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 355 | 94810358_355
A79690 | TT_Task | Transport to Sweden for Trainset #032 | 20/06/2024 | 25/06/2024 | nan | nan | 3088 | TK_NotStart | 94810358 | 427 | 94810358_427
A177930 | TT_Task | Fitout 2.8 for Trainset #032 DM1 | 16/04/2024 | 19/04/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 411 | 94810358_411
A177940 | TT_Task | Fitout 2.9 for Trainset #032 DM1 | 22/04/2024 | 25/04/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 451 | 94810358_451
A177950 | TT_Task | Single Car Testing for Trainset #032 DM1 | 26/04/2024 | 02/05/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 412 | 94810358_412
A183390 | TT_Task | HP2 for Trainset #032 DM1 | 03/05/2024 | 13/05/2024 | nan | nan | 64 | TK_NotStart | 94810358 | 421 | 94810358_421
A49940 | TT_Task | Tempering of CBY for Trainset #032 DM1 | 09/04/2024 | 09/04/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 375 | 94810358_375
A50030 | TT_Task | Fitout 2.7 for Trainset #032 DM1 | 10/04/2024 | 15/04/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 414 | 94810358_414
A177960 | TT_Task | Tempering of CBY for Trainset #032 DM2 | 15/04/2024 | 15/04/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 376 | 94810358_376
A177970 | TT_Task | Fitout 2.8 for Trainset #032 DM2 | 22/04/2024 | 25/04/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 415 | 94810358_415
A177980 | TT_Task | Fitout 2.9 for Trainset #032 DM2 | 26/04/2024 | 02/05/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 452 | 94810358_452
A177990 | TT_Task | Single Car Testing for Trainset #032 DM2 | 03/05/2024 | 13/05/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 416 | 94810358_416
A183400 | TT_Task | HP2 for Trainset #032 DM2 | 14/05/2024 | 17/05/2024 | nan | nan | 32 | TK_NotStart | 94810358 | 422 | 94810358_422
A50040 | TT_Task | Fitout 2.7 for Trainset #032 DM2 | 16/04/2024 | 19/04/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 417 | 94810358_417
A178000 | TT_Task | Tempering of CBY for Trainset #032 T | 19/04/2024 | 19/04/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 380 | 94810358_380
A178010 | TT_Task | Fitout 2.8 for Trainset #032 T | 26/04/2024 | 02/05/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 381 | 94810358_381
A178020 | TT_Task | Fitout 2.9 for Trainset #032 T | 03/05/2024 | 13/05/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 453 | 94810358_453
A178030 | TT_Task | Single Car Testing for Trainset #032 T | 14/05/2024 | 17/05/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 418 | 94810358_418
A183410 | TT_Task | HP2 for Trainset #032 T | 21/05/2024 | 24/05/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 401 | 94810358_401
A50050 | TT_Task | Fitout 2.7 for Trainset #032 T | 22/04/2024 | 25/04/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 419 | 94810358_419
A50000 | TT_Task | Train Completion for Trainset #032 | 22/05/2024 | 07/06/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 396 | 94810358_396
A50020 | TT_Task | Commissioning for Trainset #032 | 23/05/2024 | 05/06/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 312 | 94810358_312
A80690 | TT_Task | Quality/Customer Acceptance for Trainset #032 | 06/06/2024 | 19/06/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 454 | 94810358_454
A16530 | TT_Task | Preliminary Takeover Inspection for Trainset #032 | 17/07/2025 | 13/08/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 455 | 94810358_455
A16540 | TT_Task | Final Takeover Inspection for Trainset #032 | 17/09/2025 | 14/10/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 406 | 94810358_406
A65520 | TT_Task | Final Assembly for Trainset #033 DM1 | 06/11/2023 | 28/02/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 350 | 94810358_350
A181190 | TT_Task | Final Assembly for Trainset #033 DM2 | 13/11/2023 | 20/03/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 351 | 94810358_351
A181200 | TT_Task | Final Assembly for Trainset #033 T | 22/11/2023 | 29/03/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 352 | 94810358_352
A182200 | TT_Task | Transport Carbody to Henningsdorf for Trainset #033 T | 18/03/2024 | 12/05/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 356 | 94810358_356
A182210 | TT_Task | Transport Carbody to Henningsdorf for Trainset #033 DM2 | 07/03/2024 | 01/05/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 354 | 94810358_354
A76940 | TT_Task | Transport Carbody to Henningsdorf for Trainset #033 DM1 | 29/02/2024 | 24/04/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 355 | 94810358_355
A79700 | TT_Task | Transport to Sweden for Trainset #033 | 09/07/2024 | 14/07/2024 | nan | nan | 2936 | TK_NotStart | 94810358 | 427 | 94810358_427
A178100 | TT_Task | Fitout 2.8 for Trainset #033 DM1 | 03/05/2024 | 13/05/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 411 | 94810358_411
A178110 | TT_Task | Fitout 2.9 for Trainset #033 DM1 | 14/05/2024 | 17/05/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 451 | 94810358_451
A178120 | TT_Task | Single Car Testing for Trainset #033 DM1 | 21/05/2024 | 24/05/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 412 | 94810358_412
A183420 | TT_Task | HP2 for Trainset #033 DM1 | 27/05/2024 | 30/05/2024 | nan | nan | 64 | TK_NotStart | 94810358 | 421 | 94810358_421
A50110 | TT_Task | Tempering of CBY for Trainset #033 DM1 | 25/04/2024 | 25/04/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 375 | 94810358_375
A50200 | TT_Task | Fitout 2.7 for Trainset #033 DM1 | 26/04/2024 | 02/05/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 414 | 94810358_414
A178130 | TT_Task | Tempering of CBY for Trainset #033 DM2 | 02/05/2024 | 02/05/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 376 | 94810358_376
A178140 | TT_Task | Fitout 2.8 for Trainset #033 DM2 | 14/05/2024 | 17/05/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 415 | 94810358_415
A178150 | TT_Task | Fitout 2.9 for Trainset #033 DM2 | 21/05/2024 | 24/05/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 452 | 94810358_452
A178160 | TT_Task | Single Car Testing for Trainset #033 DM2 | 27/05/2024 | 30/05/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 416 | 94810358_416
A183430 | TT_Task | HP2 for Trainset #033 DM2 | 31/05/2024 | 05/06/2024 | nan | nan | 32 | TK_NotStart | 94810358 | 422 | 94810358_422
A50210 | TT_Task | Fitout 2.7 for Trainset #033 DM2 | 03/05/2024 | 13/05/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 417 | 94810358_417
A178170 | TT_Task | Tempering of CBY for Trainset #033 T | 13/05/2024 | 13/05/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 380 | 94810358_380
A178180 | TT_Task | Fitout 2.8 for Trainset #033 T | 21/05/2024 | 24/05/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 381 | 94810358_381
A178190 | TT_Task | Fitout 2.9 for Trainset #033 T | 27/05/2024 | 30/05/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 453 | 94810358_453
A178200 | TT_Task | Single Car Testing for Trainset #033 T | 31/05/2024 | 05/06/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 418 | 94810358_418
A183440 | TT_Task | HP2 for Trainset #033 T | 06/06/2024 | 11/06/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 401 | 94810358_401
A50220 | TT_Task | Fitout 2.7 for Trainset #033 T | 14/05/2024 | 17/05/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 419 | 94810358_419
A50170 | TT_Task | Train Completion for Trainset #033 | 07/06/2024 | 25/06/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 396 | 94810358_396
A50190 | TT_Task | Commissioning for Trainset #033 | 10/06/2024 | 21/06/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 312 | 94810358_312
A80700 | TT_Task | Quality/Customer Acceptance for Trainset #033 | 24/06/2024 | 08/07/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 454 | 94810358_454
A16640 | TT_Task | Preliminary Takeover Inspection for Trainset #033 | 17/07/2025 | 13/08/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 455 | 94810358_455
A16650 | TT_Task | Final Takeover Inspection for Trainset #033 | 17/09/2025 | 14/10/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 406 | 94810358_406
A65640 | TT_Task | Final Assembly for Trainset #034 DM1 | 27/11/2023 | 20/03/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 350 | 94810358_350
A181220 | TT_Task | Final Assembly for Trainset #034 DM2 | 04/12/2023 | 10/04/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 351 | 94810358_351
A181230 | TT_Task | Final Assembly for Trainset #034 T | 11/12/2023 | 17/04/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 352 | 94810358_352
A182220 | TT_Task | Transport Carbody to Henningsdorf for Trainset #034 T | 04/04/2024 | 29/05/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 356 | 94810358_356
A182230 | TT_Task | Transport Carbody to Henningsdorf for Trainset #034 DM2 | 29/03/2024 | 23/05/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 354 | 94810358_354
A76970 | TT_Task | Transport Carbody to Henningsdorf for Trainset #034 DM1 | 22/03/2024 | 16/05/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 355 | 94810358_355
A79710 | TT_Task | Transport to Sweden for Trainset #034 | 30/07/2024 | 04/08/2024 | nan | nan | 2992 | TK_NotStart | 94810358 | 427 | 94810358_427
A178270 | TT_Task | Fitout 2.8 for Trainset #034 DM1 | 27/05/2024 | 30/05/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 411 | 94810358_411
A178280 | TT_Task | Fitout 2.9 for Trainset #034 DM1 | 31/05/2024 | 05/06/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 451 | 94810358_451
A178290 | TT_Task | Single Car Testing for Trainset #034 DM1 | 06/06/2024 | 11/06/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 412 | 94810358_412
A183450 | TT_Task | HP2 for Trainset #034 DM1 | 12/06/2024 | 17/06/2024 | nan | nan | 64 | TK_NotStart | 94810358 | 421 | 94810358_421
A50280 | TT_Task | Tempering of CBY for Trainset #034 DM1 | 17/05/2024 | 17/05/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 375 | 94810358_375
A50370 | TT_Task | Fitout 2.7 for Trainset #034 DM1 | 21/05/2024 | 24/05/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 414 | 94810358_414
A178300 | TT_Task | Tempering of CBY for Trainset #034 DM2 | 24/05/2024 | 24/05/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 376 | 94810358_376
A178310 | TT_Task | Fitout 2.8 for Trainset #034 DM2 | 31/05/2024 | 05/06/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 415 | 94810358_415
A178320 | TT_Task | Fitout 2.9 for Trainset #034 DM2 | 06/06/2024 | 11/06/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 452 | 94810358_452
A178330 | TT_Task | Single Car Testing for Trainset #034 DM2 | 12/06/2024 | 17/06/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 416 | 94810358_416
A183460 | TT_Task | HP2 for Trainset #034 DM2 | 18/06/2024 | 21/06/2024 | nan | nan | 32 | TK_NotStart | 94810358 | 422 | 94810358_422
A50380 | TT_Task | Fitout 2.7 for Trainset #034 DM2 | 27/05/2024 | 30/05/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 417 | 94810358_417
A178340 | TT_Task | Tempering of CBY for Trainset #034 T | 30/05/2024 | 30/05/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 380 | 94810358_380
A178350 | TT_Task | Fitout 2.8 for Trainset #034 T | 06/06/2024 | 11/06/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 381 | 94810358_381
A178360 | TT_Task | Fitout 2.9 for Trainset #034 T | 12/06/2024 | 17/06/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 453 | 94810358_453
A178370 | TT_Task | Single Car Testing for Trainset #034 T | 18/06/2024 | 21/06/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 418 | 94810358_418
A183470 | TT_Task | HP2 for Trainset #034 T | 24/06/2024 | 27/06/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 401 | 94810358_401
A50390 | TT_Task | Fitout 2.7 for Trainset #034 T | 31/05/2024 | 05/06/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 419 | 94810358_419
A50340 | TT_Task | Train Completion for Trainset #034 | 25/06/2024 | 15/07/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 396 | 94810358_396
A50360 | TT_Task | Commissioning for Trainset #034 | 26/06/2024 | 11/07/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 312 | 94810358_312
A80710 | TT_Task | Quality/Customer Acceptance for Trainset #034 | 12/07/2024 | 29/07/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 454 | 94810358_454
A16750 | TT_Task | Preliminary Takeover Inspection for Trainset #034 | 14/08/2025 | 10/09/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 455 | 94810358_455
A16760 | TT_Task | Final Takeover Inspection for Trainset #034 | 17/09/2025 | 14/10/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 406 | 94810358_406
A65760 | TT_Task | Final Assembly for Trainset #035 DM1 | 13/12/2023 | 05/04/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 350 | 94810358_350
A181250 | TT_Task | Final Assembly for Trainset #035 DM2 | 20/12/2023 | 26/04/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 351 | 94810358_351
A181260 | TT_Task | Final Assembly for Trainset #035 T | 27/12/2023 | 03/05/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 352 | 94810358_352
A182240 | TT_Task | Transport Carbody to Henningsdorf for Trainset #035 T | 22/04/2024 | 16/06/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 356 | 94810358_356
A182250 | TT_Task | Transport Carbody to Henningsdorf for Trainset #035 DM2 | 16/04/2024 | 10/06/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 354 | 94810358_354
A77000 | TT_Task | Transport Carbody to Henningsdorf for Trainset #035 DM1 | 10/04/2024 | 04/06/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 355 | 94810358_355
A79720 | TT_Task | Transport to Sweden for Trainset #035 | 20/08/2024 | 25/08/2024 | nan | nan | 2824 | TK_NotStart | 94810358 | 427 | 94810358_427
A178440 | TT_Task | Fitout 2.8 for Trainset #035 DM1 | 12/06/2024 | 17/06/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 411 | 94810358_411
A178450 | TT_Task | Fitout 2.9 for Trainset #035 DM1 | 18/06/2024 | 21/06/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 451 | 94810358_451
A178460 | TT_Task | Single Car Testing for Trainset #035 DM1 | 24/06/2024 | 27/06/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 412 | 94810358_412
A183480 | TT_Task | HP2 for Trainset #035 DM1 | 01/07/2024 | 04/07/2024 | nan | nan | 64 | TK_NotStart | 94810358 | 421 | 94810358_421
A50450 | TT_Task | Tempering of CBY for Trainset #035 DM1 | 05/06/2024 | 05/06/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 375 | 94810358_375
A50540 | TT_Task | Fitout 2.7 for Trainset #035 DM1 | 06/06/2024 | 11/06/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 414 | 94810358_414
A178470 | TT_Task | Tempering of CBY for Trainset #035 DM2 | 11/06/2024 | 11/06/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 376 | 94810358_376
A178480 | TT_Task | Fitout 2.8 for Trainset #035 DM2 | 18/06/2024 | 21/06/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 415 | 94810358_415
A178490 | TT_Task | Fitout 2.9 for Trainset #035 DM2 | 24/06/2024 | 27/06/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 452 | 94810358_452
A178500 | TT_Task | Single Car Testing for Trainset #035 DM2 | 01/07/2024 | 04/07/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 416 | 94810358_416
A183490 | TT_Task | HP2 for Trainset #035 DM2 | 05/07/2024 | 11/07/2024 | nan | nan | 32 | TK_NotStart | 94810358 | 422 | 94810358_422
A50550 | TT_Task | Fitout 2.7 for Trainset #035 DM2 | 12/06/2024 | 17/06/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 417 | 94810358_417
A178510 | TT_Task | Tempering of CBY for Trainset #035 T | 17/06/2024 | 17/06/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 380 | 94810358_380
A178520 | TT_Task | Fitout 2.8 for Trainset #035 T | 24/06/2024 | 27/06/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 381 | 94810358_381
A178530 | TT_Task | Fitout 2.9 for Trainset #035 T | 01/07/2024 | 04/07/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 453 | 94810358_453
A178540 | TT_Task | Single Car Testing for Trainset #035 T | 05/07/2024 | 11/07/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 418 | 94810358_418
A183500 | TT_Task | HP2 for Trainset #035 T | 12/07/2024 | 18/07/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 401 | 94810358_401
A50560 | TT_Task | Fitout 2.7 for Trainset #035 T | 18/06/2024 | 21/06/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 419 | 94810358_419
A50510 | TT_Task | Train Completion for Trainset #035 | 15/07/2024 | 05/08/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 396 | 94810358_396
A50530 | TT_Task | Commissioning for Trainset #035 | 16/07/2024 | 01/08/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 312 | 94810358_312
A80720 | TT_Task | Quality/Customer Acceptance for Trainset #035 | 02/08/2024 | 19/08/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 454 | 94810358_454
A16860 | TT_Task | Preliminary Takeover Inspection for Trainset #035 | 14/08/2025 | 10/09/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 455 | 94810358_455
A16870 | TT_Task | Final Takeover Inspection for Trainset #035 | 17/09/2025 | 14/10/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 406 | 94810358_406
A65880 | TT_Task | Final Assembly for Trainset #036 DM1 | 01/01/2024 | 24/04/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 350 | 94810358_350
A181280 | TT_Task | Final Assembly for Trainset #036 DM2 | 08/01/2024 | 15/05/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 351 | 94810358_351
A181290 | TT_Task | Final Assembly for Trainset #036 T | 15/01/2024 | 22/05/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 352 | 94810358_352
A182260 | TT_Task | Transport Carbody to Henningsdorf for Trainset #036 T | 09/05/2024 | 03/07/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 356 | 94810358_356
A182270 | TT_Task | Transport Carbody to Henningsdorf for Trainset #036 DM2 | 02/05/2024 | 26/06/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 354 | 94810358_354
A77030 | TT_Task | Transport Carbody to Henningsdorf for Trainset #036 DM1 | 26/04/2024 | 20/06/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 355 | 94810358_355
A79730 | TT_Task | Transport to Sweden for Trainset #036 | 05/09/2024 | 10/09/2024 | nan | nan | 2920 | TK_NotStart | 94810358 | 427 | 94810358_427
A178610 | TT_Task | Fitout 2.8 for Trainset #036 DM1 | 01/07/2024 | 04/07/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 411 | 94810358_411
A178620 | TT_Task | Fitout 2.9 for Trainset #036 DM1 | 05/07/2024 | 11/07/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 451 | 94810358_451
A178630 | TT_Task | Single Car Testing for Trainset #036 DM1 | 12/07/2024 | 18/07/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 412 | 94810358_412
A183510 | TT_Task | HP2 for Trainset #036 DM1 | 19/07/2024 | 25/07/2024 | nan | nan | 64 | TK_NotStart | 94810358 | 421 | 94810358_421
A50620 | TT_Task | Tempering of CBY for Trainset #036 DM1 | 21/06/2024 | 21/06/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 375 | 94810358_375
A50710 | TT_Task | Fitout 2.7 for Trainset #036 DM1 | 24/06/2024 | 27/06/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 414 | 94810358_414
A178640 | TT_Task | Tempering of CBY for Trainset #036 DM2 | 27/06/2024 | 27/06/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 376 | 94810358_376
A178650 | TT_Task | Fitout 2.8 for Trainset #036 DM2 | 05/07/2024 | 11/07/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 415 | 94810358_415
A178660 | TT_Task | Fitout 2.9 for Trainset #036 DM2 | 12/07/2024 | 18/07/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 452 | 94810358_452
A178670 | TT_Task | Single Car Testing for Trainset #036 DM2 | 19/07/2024 | 25/07/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 416 | 94810358_416
A183520 | TT_Task | HP2 for Trainset #036 DM2 | 26/07/2024 | 01/08/2024 | nan | nan | 32 | TK_NotStart | 94810358 | 422 | 94810358_422
A50720 | TT_Task | Fitout 2.7 for Trainset #036 DM2 | 01/07/2024 | 04/07/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 417 | 94810358_417
A178680 | TT_Task | Tempering of CBY for Trainset #036 T | 04/07/2024 | 04/07/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 380 | 94810358_380
A178690 | TT_Task | Fitout 2.8 for Trainset #036 T | 12/07/2024 | 18/07/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 381 | 94810358_381
A178700 | TT_Task | Fitout 2.9 for Trainset #036 T | 19/07/2024 | 25/07/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 453 | 94810358_453
A178710 | TT_Task | Single Car Testing for Trainset #036 T | 26/07/2024 | 01/08/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 418 | 94810358_418
A183530 | TT_Task | HP2 for Trainset #036 T | 02/08/2024 | 08/08/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 401 | 94810358_401
A50730 | TT_Task | Fitout 2.7 for Trainset #036 T | 05/07/2024 | 11/07/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 419 | 94810358_419
A50680 | TT_Task | Train Completion for Trainset #036 | 05/08/2024 | 23/08/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 396 | 94810358_396
A50700 | TT_Task | Commissioning for Trainset #036 | 06/08/2024 | 21/08/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 312 | 94810358_312
A80730 | TT_Task | Quality/Customer Acceptance for Trainset #036 | 22/08/2024 | 04/09/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 454 | 94810358_454
A16970 | TT_Task | Preliminary Takeover Inspection for Trainset #036 | 11/09/2025 | 08/10/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 455 | 94810358_455
A16980 | TT_Task | Final Takeover Inspection for Trainset #036 | 09/10/2025 | 05/11/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 406 | 94810358_406
A66000 | TT_Task | Final Assembly for Trainset #037 DM1 | 22/01/2024 | 15/05/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 350 | 94810358_350
A181310 | TT_Task | Final Assembly for Trainset #037 DM2 | 29/01/2024 | 05/06/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 351 | 94810358_351
A181320 | TT_Task | Final Assembly for Trainset #037 T | 05/02/2024 | 12/06/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 352 | 94810358_352
A182280 | TT_Task | Transport Carbody to Henningsdorf for Trainset #037 T | 30/05/2024 | 24/07/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 356 | 94810358_356
A182290 | TT_Task | Transport Carbody to Henningsdorf for Trainset #037 DM2 | 23/05/2024 | 17/07/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 354 | 94810358_354
A77060 | TT_Task | Transport Carbody to Henningsdorf for Trainset #037 DM1 | 16/05/2024 | 10/07/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 355 | 94810358_355
A79740 | TT_Task | Transport to Sweden for Trainset #037 | 21/09/2024 | 26/09/2024 | nan | nan | 2792 | TK_NotStart | 94810358 | 427 | 94810358_427
A178780 | TT_Task | Fitout 2.8 for Trainset #037 DM1 | 19/07/2024 | 25/07/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 411 | 94810358_411
A178790 | TT_Task | Fitout 2.9 for Trainset #037 DM1 | 26/07/2024 | 01/08/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 451 | 94810358_451
A178800 | TT_Task | Single Car Testing for Trainset #037 DM1 | 02/08/2024 | 08/08/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 412 | 94810358_412
A183540 | TT_Task | HP2 for Trainset #037 DM1 | 09/08/2024 | 15/08/2024 | nan | nan | 64 | TK_NotStart | 94810358 | 421 | 94810358_421
A50790 | TT_Task | Tempering of CBY for Trainset #037 DM1 | 11/07/2024 | 11/07/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 375 | 94810358_375
A50880 | TT_Task | Fitout 2.7 for Trainset #037 DM1 | 12/07/2024 | 18/07/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 414 | 94810358_414
A178810 | TT_Task | Tempering of CBY for Trainset #037 DM2 | 18/07/2024 | 18/07/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 376 | 94810358_376
A178820 | TT_Task | Fitout 2.8 for Trainset #037 DM2 | 26/07/2024 | 01/08/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 415 | 94810358_415
A178830 | TT_Task | Fitout 2.9 for Trainset #037 DM2 | 02/08/2024 | 08/08/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 452 | 94810358_452
A178840 | TT_Task | Single Car Testing for Trainset #037 DM2 | 09/08/2024 | 15/08/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 416 | 94810358_416
A183550 | TT_Task | HP2 for Trainset #037 DM2 | 16/08/2024 | 21/08/2024 | nan | nan | 32 | TK_NotStart | 94810358 | 422 | 94810358_422
A50890 | TT_Task | Fitout 2.7 for Trainset #037 DM2 | 19/07/2024 | 25/07/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 417 | 94810358_417
A178850 | TT_Task | Tempering of CBY for Trainset #037 T | 25/07/2024 | 25/07/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 380 | 94810358_380
A178860 | TT_Task | Fitout 2.8 for Trainset #037 T | 02/08/2024 | 08/08/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 381 | 94810358_381
A178870 | TT_Task | Fitout 2.9 for Trainset #037 T | 09/08/2024 | 15/08/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 453 | 94810358_453
A178880 | TT_Task | Single Car Testing for Trainset #037 T | 16/08/2024 | 21/08/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 418 | 94810358_418
A183560 | TT_Task | HP2 for Trainset #037 T | 22/08/2024 | 27/08/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 401 | 94810358_401
A50900 | TT_Task | Fitout 2.7 for Trainset #037 T | 26/07/2024 | 01/08/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 419 | 94810358_419
A50850 | TT_Task | Train Completion for Trainset #037 | 23/08/2024 | 10/09/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 396 | 94810358_396
A50870 | TT_Task | Commissioning for Trainset #037 | 26/08/2024 | 06/09/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 312 | 94810358_312
A80740 | TT_Task | Quality/Customer Acceptance for Trainset #037 | 09/09/2024 | 20/09/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 454 | 94810358_454
A17080 | TT_Task | Preliminary Takeover Inspection for Trainset #037 | 11/09/2025 | 08/10/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 455 | 94810358_455
A17090 | TT_Task | Final Takeover Inspection for Trainset #037 | 09/10/2025 | 05/11/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 406 | 94810358_406
A66120 | TT_Task | Final Assembly for Trainset #038 DM1 | 12/02/2024 | 05/06/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 350 | 94810358_350
A181340 | TT_Task | Final Assembly for Trainset #038 DM2 | 19/02/2024 | 26/06/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 351 | 94810358_351
A181350 | TT_Task | Final Assembly for Trainset #038 T | 26/02/2024 | 03/07/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 352 | 94810358_352
A182300 | TT_Task | Transport Carbody to Henningsdorf for Trainset #038 T | 20/06/2024 | 14/08/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 356 | 94810358_356
A182310 | TT_Task | Transport Carbody to Henningsdorf for Trainset #038 DM2 | 13/06/2024 | 07/08/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 354 | 94810358_354
A77090 | TT_Task | Transport Carbody to Henningsdorf for Trainset #038 DM1 | 06/06/2024 | 31/07/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 355 | 94810358_355
A79750 | TT_Task | Transport to Sweden for Trainset #038 | 15/10/2024 | 20/10/2024 | nan | nan | 2824 | TK_NotStart | 94810358 | 427 | 94810358_427
A178950 | TT_Task | Fitout 2.8 for Trainset #038 DM1 | 09/08/2024 | 15/08/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 411 | 94810358_411
A178960 | TT_Task | Fitout 2.9 for Trainset #038 DM1 | 16/08/2024 | 21/08/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 451 | 94810358_451
A178970 | TT_Task | Single Car Testing for Trainset #038 DM1 | 22/08/2024 | 27/08/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 412 | 94810358_412
A183570 | TT_Task | HP2 for Trainset #038 DM1 | 28/08/2024 | 02/09/2024 | nan | nan | 64 | TK_NotStart | 94810358 | 421 | 94810358_421
A50960 | TT_Task | Tempering of CBY for Trainset #038 DM1 | 01/08/2024 | 01/08/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 375 | 94810358_375
A51050 | TT_Task | Fitout 2.7 for Trainset #038 DM1 | 02/08/2024 | 08/08/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 414 | 94810358_414
A178980 | TT_Task | Tempering of CBY for Trainset #038 DM2 | 08/08/2024 | 08/08/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 376 | 94810358_376
A178990 | TT_Task | Fitout 2.8 for Trainset #038 DM2 | 16/08/2024 | 21/08/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 415 | 94810358_415
A179000 | TT_Task | Fitout 2.9 for Trainset #038 DM2 | 22/08/2024 | 27/08/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 452 | 94810358_452
A179010 | TT_Task | Single Car Testing for Trainset #038 DM2 | 28/08/2024 | 02/09/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 416 | 94810358_416
A183580 | TT_Task | HP2 for Trainset #038 DM2 | 03/09/2024 | 06/09/2024 | nan | nan | 32 | TK_NotStart | 94810358 | 422 | 94810358_422
A51060 | TT_Task | Fitout 2.7 for Trainset #038 DM2 | 09/08/2024 | 15/08/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 417 | 94810358_417
A179020 | TT_Task | Tempering of CBY for Trainset #038 T | 15/08/2024 | 15/08/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 380 | 94810358_380
A179030 | TT_Task | Fitout 2.8 for Trainset #038 T | 22/08/2024 | 27/08/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 381 | 94810358_381
A179040 | TT_Task | Fitout 2.9 for Trainset #038 T | 28/08/2024 | 02/09/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 453 | 94810358_453
A179050 | TT_Task | Single Car Testing for Trainset #038 T | 03/09/2024 | 06/09/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 418 | 94810358_418
A183590 | TT_Task | HP2 for Trainset #038 T | 09/09/2024 | 12/09/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 401 | 94810358_401
A51070 | TT_Task | Fitout 2.7 for Trainset #038 T | 16/08/2024 | 21/08/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 419 | 94810358_419
A51020 | TT_Task | Train Completion for Trainset #038 | 10/09/2024 | 26/09/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 396 | 94810358_396
A51040 | TT_Task | Commissioning for Trainset #038 | 11/09/2024 | 24/09/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 312 | 94810358_312
A80750 | TT_Task | Quality/Customer Acceptance for Trainset #038 | 25/09/2024 | 14/10/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 454 | 94810358_454
A17190 | TT_Task | Preliminary Takeover Inspection for Trainset #038 | 09/10/2025 | 05/11/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 455 | 94810358_455
A17200 | TT_Task | Final Takeover Inspection for Trainset #038 | 06/11/2025 | 03/12/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 406 | 94810358_406
A66240 | TT_Task | Final Assembly for Trainset #039 DM1 | 28/02/2024 | 21/06/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 350 | 94810358_350
A181370 | TT_Task | Final Assembly for Trainset #039 DM2 | 06/03/2024 | 12/07/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 351 | 94810358_351
A181380 | TT_Task | Final Assembly for Trainset #039 T | 13/03/2024 | 19/07/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 352 | 94810358_352
A182320 | TT_Task | Transport Carbody to Henningsdorf for Trainset #039 T | 08/07/2024 | 01/09/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 356 | 94810358_356
A182330 | TT_Task | Transport Carbody to Henningsdorf for Trainset #039 DM2 | 02/07/2024 | 26/08/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 354 | 94810358_354
A77120 | TT_Task | Transport Carbody to Henningsdorf for Trainset #039 DM1 | 26/06/2024 | 20/08/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 355 | 94810358_355
A79760 | TT_Task | Transport to Sweden for Trainset #039 | 02/11/2024 | 07/11/2024 | nan | nan | 2680 | TK_NotStart | 94810358 | 427 | 94810358_427
A179120 | TT_Task | Fitout 2.8 for Trainset #039 DM1 | 28/08/2024 | 02/09/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 411 | 94810358_411
A179130 | TT_Task | Fitout 2.9 for Trainset #039 DM1 | 03/09/2024 | 06/09/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 451 | 94810358_451
A179140 | TT_Task | Single Car Testing for Trainset #039 DM1 | 09/09/2024 | 12/09/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 412 | 94810358_412
A183600 | TT_Task | HP2 for Trainset #039 DM1 | 13/09/2024 | 18/09/2024 | nan | nan | 64 | TK_NotStart | 94810358 | 421 | 94810358_421
A51130 | TT_Task | Tempering of CBY for Trainset #039 DM1 | 21/08/2024 | 21/08/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 375 | 94810358_375
A51220 | TT_Task | Fitout 2.7 for Trainset #039 DM1 | 22/08/2024 | 27/08/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 414 | 94810358_414
A179150 | TT_Task | Tempering of CBY for Trainset #039 DM2 | 27/08/2024 | 27/08/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 376 | 94810358_376
A179160 | TT_Task | Fitout 2.8 for Trainset #039 DM2 | 03/09/2024 | 06/09/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 415 | 94810358_415
A179170 | TT_Task | Fitout 2.9 for Trainset #039 DM2 | 09/09/2024 | 12/09/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 452 | 94810358_452
A179180 | TT_Task | Single Car Testing for Trainset #039 DM2 | 13/09/2024 | 18/09/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 416 | 94810358_416
A183610 | TT_Task | HP2 for Trainset #039 DM2 | 19/09/2024 | 24/09/2024 | nan | nan | 32 | TK_NotStart | 94810358 | 422 | 94810358_422
A51230 | TT_Task | Fitout 2.7 for Trainset #039 DM2 | 28/08/2024 | 02/09/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 417 | 94810358_417
A179190 | TT_Task | Tempering of CBY for Trainset #039 T | 02/09/2024 | 02/09/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 380 | 94810358_380
A179200 | TT_Task | Fitout 2.8 for Trainset #039 T | 09/09/2024 | 12/09/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 381 | 94810358_381
A179210 | TT_Task | Fitout 2.9 for Trainset #039 T | 13/09/2024 | 18/09/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 453 | 94810358_453
A179220 | TT_Task | Single Car Testing for Trainset #039 T | 19/09/2024 | 24/09/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 418 | 94810358_418
A183620 | TT_Task | HP2 for Trainset #039 T | 25/09/2024 | 01/10/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 401 | 94810358_401
A51240 | TT_Task | Fitout 2.7 for Trainset #039 T | 03/09/2024 | 06/09/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 419 | 94810358_419
A51190 | TT_Task | Train Completion for Trainset #039 | 26/09/2024 | 21/10/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 396 | 94810358_396
A51210 | TT_Task | Commissioning for Trainset #039 | 30/09/2024 | 17/10/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 312 | 94810358_312
A80760 | TT_Task | Quality/Customer Acceptance for Trainset #039 | 18/10/2024 | 01/11/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 454 | 94810358_454
A17300 | TT_Task | Preliminary Takeover Inspection for Trainset #039 | 09/10/2025 | 05/11/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 455 | 94810358_455
A17310 | TT_Task | Final Takeover Inspection for Trainset #039 | 06/11/2025 | 03/12/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 406 | 94810358_406
A66360 | TT_Task | Final Assembly for Trainset #040 DM1 | 15/03/2024 | 09/07/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 456 | 94810358_456
A181400 | TT_Task | Final Assembly for Trainset #040 DM2 | 22/03/2024 | 30/07/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 457 | 94810358_457
A181410 | TT_Task | Final Assembly for Trainset #040 T | 29/03/2024 | 06/08/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 458 | 94810358_458
A182340 | TT_Task | Transport Carbody to Henningsdorf for Trainset #040 T | 24/07/2024 | 17/09/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 356 | 94810358_356
A182350 | TT_Task | Transport Carbody to Henningsdorf for Trainset #040 DM2 | 18/07/2024 | 11/09/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 354 | 94810358_354
A77150 | TT_Task | Transport Carbody to Henningsdorf for Trainset #040 DM1 | 12/07/2024 | 05/09/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 355 | 94810358_355
A79770 | TT_Task | Transport to Sweden for Trainset #040 | 21/11/2024 | 26/11/2024 | nan | nan | 2752 | TK_NotStart | 94810358 | 427 | 94810358_427
A179290 | TT_Task | Fitout 2.8 for Trainset #040 DM1 | 13/09/2024 | 18/09/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 358 | 94810358_358
A179300 | TT_Task | Fitout 2.9 for Trainset #040 DM1 | 19/09/2024 | 24/09/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 358 | 94810358_358
A179310 | TT_Task | Single Car Testing for Trainset #040 DM1 | 25/09/2024 | 01/10/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 412 | 94810358_412
A183630 | TT_Task | HP2 for Trainset #040 DM1 | 02/10/2024 | 10/10/2024 | nan | nan | 64 | TK_NotStart | 94810358 | 400 | 94810358_400
A51300 | TT_Task | Tempering of CBY for Trainset #040 DM1 | 06/09/2024 | 06/09/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 375 | 94810358_375
A51390 | TT_Task | Fitout 2.7 for Trainset #040 DM1 | 09/09/2024 | 12/09/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 358 | 94810358_358
A179320 | TT_Task | Tempering of CBY for Trainset #040 DM2 | 12/09/2024 | 12/09/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 376 | 94810358_376
A179330 | TT_Task | Fitout 2.8 for Trainset #040 DM2 | 19/09/2024 | 24/09/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 459 | 94810358_459
A179340 | TT_Task | Fitout 2.9 for Trainset #040 DM2 | 25/09/2024 | 01/10/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 459 | 94810358_459
A179350 | TT_Task | Single Car Testing for Trainset #040 DM2 | 02/10/2024 | 10/10/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 416 | 94810358_416
A183640 | TT_Task | HP2 for Trainset #040 DM2 | 11/10/2024 | 17/10/2024 | nan | nan | 32 | TK_NotStart | 94810358 | 400 | 94810358_400
A51400 | TT_Task | Fitout 2.7 for Trainset #040 DM2 | 13/09/2024 | 18/09/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 459 | 94810358_459
A179360 | TT_Task | Tempering of CBY for Trainset #040 T | 18/09/2024 | 18/09/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 380 | 94810358_380
A179370 | TT_Task | Fitout 2.8 for Trainset #040 T | 25/09/2024 | 01/10/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 460 | 94810358_460
A179380 | TT_Task | Fitout 2.9 for Trainset #040 T | 02/10/2024 | 10/10/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 461 | 94810358_461
A179390 | TT_Task | Single Car Testing for Trainset #040 T | 11/10/2024 | 17/10/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 418 | 94810358_418
A183650 | TT_Task | HP2 for Trainset #040 T | 18/10/2024 | 23/10/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 462 | 94810358_462
A51410 | TT_Task | Fitout 2.7 for Trainset #040 T | 19/09/2024 | 24/09/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 461 | 94810358_461
A51360 | TT_Task | Train Completion for Trainset #040 | 21/10/2024 | 08/11/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 463 | 94810358_463
A51380 | TT_Task | Commissioning for Trainset #040 | 22/10/2024 | 06/11/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 464 | 94810358_464
A80770 | TT_Task | Quality/Customer Acceptance for Trainset #040 | 07/11/2024 | 20/11/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 465 | 94810358_465
A17410 | TT_Task | Preliminary Takeover Inspection for Trainset #040 | 06/11/2025 | 03/12/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 455 | 94810358_455
A17420 | TT_Task | Final Takeover Inspection for Trainset #040 | 04/12/2025 | 19/01/2026 | nan | nan | 0 | TK_NotStart | 94810358 | 406 | 94810358_406
A169430 | TT_Task | Final Assembly for Trainset #041 DM1 | 04/04/2024 | 29/07/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 456 | 94810358_456
A181430 | TT_Task | Final Assembly for Trainset #041 DM2 | 11/04/2024 | 19/08/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 457 | 94810358_457
A181440 | TT_Task | Final Assembly for Trainset #041 T | 22/04/2024 | 28/08/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 458 | 94810358_458
A169480 | TT_Task | Transport Carbody to Henningsdorf for Trainset #041 T | 15/08/2024 | 09/10/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 356 | 94810358_356
A169530 | TT_Task | Transport to Sweden for Trainset #041 | 10/12/2024 | 15/12/2024 | nan | nan | 2600 | TK_NotStart | 94810358 | 427 | 94810358_427
A182360 | TT_Task | Transport Carbody to Henningsdorf for Trainset #041 DM2 | 06/08/2024 | 30/09/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 354 | 94810358_354
A182370 | TT_Task | Transport Carbody to Henningsdorf for Trainset #041 DM1 | 30/07/2024 | 23/09/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 355 | 94810358_355
A169080 | TT_Task | Tempering of CBY for Trainset #041 DM1 | 24/09/2024 | 24/09/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 375 | 94810358_375
A169120 | TT_Task | Fitout 2.7 for Trainset #041 DM1 | 25/09/2024 | 01/10/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 358 | 94810358_358
A179460 | TT_Task | Fitout 2.8 for Trainset #041 DM1 | 02/10/2024 | 10/10/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 358 | 94810358_358
A179470 | TT_Task | Fitout 2.9 for Trainset #041 DM1 | 11/10/2024 | 17/10/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 358 | 94810358_358
A179480 | TT_Task | Single Car Testing for Trainset #041 DM1 | 18/10/2024 | 23/10/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 412 | 94810358_412
A183660 | TT_Task | HP2 for Trainset #041 DM1 | 24/10/2024 | 29/10/2024 | nan | nan | 64 | TK_NotStart | 94810358 | 400 | 94810358_400
A169130 | TT_Task | Fitout 2.7 for Trainset #041 DM2 | 02/10/2024 | 10/10/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 459 | 94810358_459
A179490 | TT_Task | Tempering of CBY for Trainset #041 DM2 | 01/10/2024 | 01/10/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 376 | 94810358_376
A179500 | TT_Task | Fitout 2.8 for Trainset #041 DM2 | 11/10/2024 | 17/10/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 459 | 94810358_459
A179510 | TT_Task | Fitout 2.9 for Trainset #041 DM2 | 18/10/2024 | 23/10/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 459 | 94810358_459
A179520 | TT_Task | Single Car Testing for Trainset #041 DM2 | 24/10/2024 | 29/10/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 416 | 94810358_416
A183670 | TT_Task | HP2 for Trainset #041 DM2 | 30/10/2024 | 06/11/2024 | nan | nan | 32 | TK_NotStart | 94810358 | 400 | 94810358_400
A169140 | TT_Task | Fitout 2.7 for Trainset #041 T | 11/10/2024 | 17/10/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 461 | 94810358_461
A179530 | TT_Task | Tempering of CBY for Trainset #041 T | 10/10/2024 | 10/10/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 380 | 94810358_380
A179540 | TT_Task | Fitout 2.8 for Trainset #041 T | 18/10/2024 | 23/10/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 460 | 94810358_460
A179550 | TT_Task | Fitout 2.9 for Trainset #041 T | 24/10/2024 | 29/10/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 461 | 94810358_461
A179560 | TT_Task | Single Car Testing for Trainset #041 T | 30/10/2024 | 06/11/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 418 | 94810358_418
A183680 | TT_Task | HP2 for Trainset #041 T | 07/11/2024 | 12/11/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 462 | 94810358_462
A169100 | TT_Task | Train Completion for Trainset #041 | 08/11/2024 | 26/11/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 463 | 94810358_463
A169110 | TT_Task | Commissioning for Trainset #041 | 11/11/2024 | 22/11/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 464 | 94810358_464
A169580 | TT_Task | Quality/Customer Acceptance for Trainset #041 | 25/11/2024 | 09/12/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 465 | 94810358_465
A168980 | TT_Task | Preliminary Takeover Inspection for Trainset #041 | 06/11/2025 | 03/12/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 455 | 94810358_455
A168990 | TT_Task | Final Takeover Inspection for Trainset #041 | 04/12/2025 | 19/01/2026 | nan | nan | 0 | TK_NotStart | 94810358 | 406 | 94810358_406
A169440 | TT_Task | Final Assembly for Trainset #042 DM1 | 25/04/2024 | 19/08/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 456 | 94810358_456
A181460 | TT_Task | Final Assembly for Trainset #042 DM2 | 02/05/2024 | 09/09/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 457 | 94810358_457
A181470 | TT_Task | Final Assembly for Trainset #042 T | 09/05/2024 | 16/09/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 458 | 94810358_458
A169490 | TT_Task | Transport Carbody to Henningsdorf for Trainset #042 T | 03/09/2024 | 28/10/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 356 | 94810358_356
A169540 | TT_Task | Transport to Sweden for Trainset #042 | 07/01/2025 | 12/01/2025 | nan | nan | 2600 | TK_NotStart | 94810358 | 427 | 94810358_427
A182380 | TT_Task | Transport Carbody to Henningsdorf for Trainset #042 DM2 | 28/08/2024 | 22/10/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 354 | 94810358_354
A182390 | TT_Task | Transport Carbody to Henningsdorf for Trainset #042 DM1 | 22/08/2024 | 16/10/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 355 | 94810358_355
A169150 | TT_Task | Tempering of CBY for Trainset #042 DM1 | 17/10/2024 | 17/10/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 375 | 94810358_375
A169190 | TT_Task | Fitout 2.7 for Trainset #042 DM1 | 18/10/2024 | 23/10/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 358 | 94810358_358
A179630 | TT_Task | Fitout 2.8 for Trainset #042 DM1 | 24/10/2024 | 29/10/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 358 | 94810358_358
A179640 | TT_Task | Fitout 2.9 for Trainset #042 DM1 | 30/10/2024 | 06/11/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 358 | 94810358_358
A179650 | TT_Task | Single Car Testing for Trainset #042 DM1 | 07/11/2024 | 12/11/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 412 | 94810358_412
A183690 | TT_Task | HP2 for Trainset #042 DM1 | 13/11/2024 | 18/11/2024 | nan | nan | 64 | TK_NotStart | 94810358 | 400 | 94810358_400
A169200 | TT_Task | Fitout 2.7 for Trainset #042 DM2 | 24/10/2024 | 29/10/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 459 | 94810358_459
A179660 | TT_Task | Tempering of CBY for Trainset #042 DM2 | 23/10/2024 | 23/10/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 376 | 94810358_376
A179670 | TT_Task | Fitout 2.8 for Trainset #042 DM2 | 30/10/2024 | 06/11/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 459 | 94810358_459
A179680 | TT_Task | Fitout 2.9 for Trainset #042 DM2 | 07/11/2024 | 12/11/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 459 | 94810358_459
A179690 | TT_Task | Single Car Testing for Trainset #042 DM2 | 13/11/2024 | 18/11/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 416 | 94810358_416
A183700 | TT_Task | HP2 for Trainset #042 DM2 | 19/11/2024 | 22/11/2024 | nan | nan | 32 | TK_NotStart | 94810358 | 400 | 94810358_400
A169210 | TT_Task | Fitout 2.7 for Trainset #042 T | 30/10/2024 | 06/11/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 461 | 94810358_461
A179700 | TT_Task | Tempering of CBY for Trainset #042 T | 29/10/2024 | 29/10/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 380 | 94810358_380
A179710 | TT_Task | Fitout 2.8 for Trainset #042 T | 07/11/2024 | 12/11/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 460 | 94810358_460
A179720 | TT_Task | Fitout 2.9 for Trainset #042 T | 13/11/2024 | 18/11/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 461 | 94810358_461
A179730 | TT_Task | Single Car Testing for Trainset #042 T | 19/11/2024 | 22/11/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 418 | 94810358_418
A183710 | TT_Task | HP2 for Trainset #042 T | 25/11/2024 | 28/11/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 462 | 94810358_462
A169170 | TT_Task | Train Completion for Trainset #042 | 26/11/2024 | 13/12/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 463 | 94810358_463
A169180 | TT_Task | Commissioning for Trainset #042 | 27/11/2024 | 11/12/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 464 | 94810358_464
A169590 | TT_Task | Quality/Customer Acceptance for Trainset #042 | 12/12/2024 | 06/01/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 465 | 94810358_465
A169000 | TT_Task | Preliminary Takeover Inspection for Trainset #042 | 04/12/2025 | 31/12/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 455 | 94810358_455
A169010 | TT_Task | Final Takeover Inspection for Trainset #042 | 08/01/2026 | 04/02/2026 | nan | nan | 0 | TK_NotStart | 94810358 | 406 | 94810358_406
A169450 | TT_Task | Final Assembly for Trainset #043 DM1 | 15/05/2024 | 06/09/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 456 | 94810358_456
A181490 | TT_Task | Final Assembly for Trainset #043 DM2 | 22/05/2024 | 27/09/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 457 | 94810358_457
A181500 | TT_Task | Final Assembly for Trainset #043 T | 29/05/2024 | 04/10/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 458 | 94810358_458
A169500 | TT_Task | Transport Carbody to Henningsdorf for Trainset #043 T | 23/09/2024 | 17/11/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 356 | 94810358_356
A169550 | TT_Task | Transport to Sweden for Trainset #043 | 23/01/2025 | 28/01/2025 | nan | nan | 2472 | TK_NotStart | 94810358 | 427 | 94810358_427
A182400 | TT_Task | Transport Carbody to Henningsdorf for Trainset #043 DM2 | 17/09/2024 | 11/11/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 354 | 94810358_354
A182410 | TT_Task | Transport Carbody to Henningsdorf for Trainset #043 DM1 | 11/09/2024 | 05/11/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 355 | 94810358_355
A169220 | TT_Task | Tempering of CBY for Trainset #043 DM1 | 06/11/2024 | 06/11/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 375 | 94810358_375
A169260 | TT_Task | Fitout 2.7 for Trainset #043 DM1 | 07/11/2024 | 12/11/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 358 | 94810358_358
A179800 | TT_Task | Fitout 2.8 for Trainset #043 DM1 | 13/11/2024 | 18/11/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 358 | 94810358_358
A179810 | TT_Task | Fitout 2.9 for Trainset #043 DM1 | 19/11/2024 | 22/11/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 358 | 94810358_358
A179820 | TT_Task | Single Car Testing for Trainset #043 DM1 | 25/11/2024 | 28/11/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 412 | 94810358_412
A183720 | TT_Task | HP2 for Trainset #043 DM1 | 29/11/2024 | 04/12/2024 | nan | nan | 64 | TK_NotStart | 94810358 | 400 | 94810358_400
A169270 | TT_Task | Fitout 2.7 for Trainset #043 DM2 | 13/11/2024 | 18/11/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 459 | 94810358_459
A179830 | TT_Task | Tempering of CBY for Trainset #043 DM2 | 12/11/2024 | 12/11/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 376 | 94810358_376
A179840 | TT_Task | Fitout 2.8 for Trainset #043 DM2 | 19/11/2024 | 22/11/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 459 | 94810358_459
A179850 | TT_Task | Fitout 2.9 for Trainset #043 DM2 | 25/11/2024 | 28/11/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 459 | 94810358_459
A179860 | TT_Task | Single Car Testing for Trainset #043 DM2 | 29/11/2024 | 04/12/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 416 | 94810358_416
A183730 | TT_Task | HP2 for Trainset #043 DM2 | 05/12/2024 | 11/12/2024 | nan | nan | 32 | TK_NotStart | 94810358 | 400 | 94810358_400
A169280 | TT_Task | Fitout 2.7 for Trainset #043 T | 19/11/2024 | 22/11/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 461 | 94810358_461
A179870 | TT_Task | Tempering of CBY for Trainset #043 T | 18/11/2024 | 18/11/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 380 | 94810358_380
A179880 | TT_Task | Fitout 2.8 for Trainset #043 T | 25/11/2024 | 28/11/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 460 | 94810358_460
A179890 | TT_Task | Fitout 2.9 for Trainset #043 T | 29/11/2024 | 04/12/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 461 | 94810358_461
A179900 | TT_Task | Single Car Testing for Trainset #043 T | 05/12/2024 | 11/12/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 418 | 94810358_418
A183740 | TT_Task | HP2 for Trainset #043 T | 12/12/2024 | 17/12/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 462 | 94810358_462
A169240 | TT_Task | Train Completion for Trainset #043 | 13/12/2024 | 10/01/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 463 | 94810358_463
A169250 | TT_Task | Commissioning for Trainset #043 | 16/12/2024 | 08/01/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 464 | 94810358_464
A169600 | TT_Task | Quality/Customer Acceptance for Trainset #043 | 09/01/2025 | 22/01/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 465 | 94810358_465
A169020 | TT_Task | Preliminary Takeover Inspection for Trainset #043 | 04/12/2025 | 31/12/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 455 | 94810358_455
A169030 | TT_Task | Final Takeover Inspection for Trainset #043 | 08/01/2026 | 04/02/2026 | nan | nan | 0 | TK_NotStart | 94810358 | 406 | 94810358_406
A169460 | TT_Task | Final Assembly for Trainset #044 DM1 | 31/05/2024 | 24/09/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 456 | 94810358_456
A181520 | TT_Task | Final Assembly for Trainset #044 DM2 | 07/06/2024 | 15/10/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 457 | 94810358_457
A181530 | TT_Task | Final Assembly for Trainset #044 T | 14/06/2024 | 22/10/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 458 | 94810358_458
A169510 | TT_Task | Transport Carbody to Henningsdorf for Trainset #044 T | 09/10/2024 | 03/12/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 356 | 94810358_356
A169560 | TT_Task | Transport to Sweden for Trainset #044 | 08/02/2025 | 13/02/2025 | nan | nan | 2568 | TK_NotStart | 94810358 | 427 | 94810358_427
A182420 | TT_Task | Transport Carbody to Henningsdorf for Trainset #044 DM2 | 03/10/2024 | 27/11/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 354 | 94810358_354
A182430 | TT_Task | Transport Carbody to Henningsdorf for Trainset #044 DM1 | 27/09/2024 | 21/11/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 355 | 94810358_355
A169290 | TT_Task | Tempering of CBY for Trainset #044 DM1 | 22/11/2024 | 22/11/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 375 | 94810358_375
A169330 | TT_Task | Fitout 2.7 for Trainset #044 DM1 | 25/11/2024 | 28/11/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 358 | 94810358_358
A179970 | TT_Task | Fitout 2.8 for Trainset #044 DM1 | 29/11/2024 | 04/12/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 358 | 94810358_358
A179980 | TT_Task | Fitout 2.9 for Trainset #044 DM1 | 05/12/2024 | 11/12/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 358 | 94810358_358
A179990 | TT_Task | Single Car Testing for Trainset #044 DM1 | 12/12/2024 | 17/12/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 412 | 94810358_412
A183750 | TT_Task | HP2 for Trainset #044 DM1 | 18/12/2024 | 02/01/2025 | nan | nan | 64 | TK_NotStart | 94810358 | 400 | 94810358_400
A169340 | TT_Task | Fitout 2.7 for Trainset #044 DM2 | 29/11/2024 | 04/12/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 459 | 94810358_459
A180000 | TT_Task | Tempering of CBY for Trainset #044 DM2 | 28/11/2024 | 28/11/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 376 | 94810358_376
A180010 | TT_Task | Fitout 2.8 for Trainset #044 DM2 | 05/12/2024 | 11/12/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 459 | 94810358_459
A180020 | TT_Task | Fitout 2.9 for Trainset #044 DM2 | 12/12/2024 | 17/12/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 459 | 94810358_459
A180030 | TT_Task | Single Car Testing for Trainset #044 DM2 | 18/12/2024 | 02/01/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 416 | 94810358_416
A183760 | TT_Task | HP2 for Trainset #044 DM2 | 03/01/2025 | 08/01/2025 | nan | nan | 32 | TK_NotStart | 94810358 | 400 | 94810358_400
A169350 | TT_Task | Fitout 2.7 for Trainset #044 T | 05/12/2024 | 11/12/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 461 | 94810358_461
A180040 | TT_Task | Tempering of CBY for Trainset #044 T | 04/12/2024 | 04/12/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 380 | 94810358_380
A180050 | TT_Task | Fitout 2.8 for Trainset #044 T | 12/12/2024 | 17/12/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 460 | 94810358_460
A180060 | TT_Task | Fitout 2.9 for Trainset #044 T | 18/12/2024 | 02/01/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 461 | 94810358_461
A180070 | TT_Task | Single Car Testing for Trainset #044 T | 03/01/2025 | 08/01/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 418 | 94810358_418
A183770 | TT_Task | HP2 for Trainset #044 T | 09/01/2025 | 14/01/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 462 | 94810358_462
A169310 | TT_Task | Train Completion for Trainset #044 | 10/01/2025 | 28/01/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 463 | 94810358_463
A169320 | TT_Task | Commissioning for Trainset #044 | 13/01/2025 | 24/01/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 464 | 94810358_464
A169610 | TT_Task | Quality/Customer Acceptance for Trainset #044 | 27/01/2025 | 07/02/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 465 | 94810358_465
A169040 | TT_Task | Preliminary Takeover Inspection for Trainset #044 | 01/01/2026 | 28/01/2026 | nan | nan | 0 | TK_NotStart | 94810358 | 455 | 94810358_455
A169050 | TT_Task | Final Takeover Inspection for Trainset #044 | 29/01/2026 | 25/02/2026 | nan | nan | 0 | TK_NotStart | 94810358 | 406 | 94810358_406
A169470 | TT_Task | Final Assembly for Trainset #045 DM1 | 20/06/2024 | 14/10/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 456 | 94810358_456
A181550 | TT_Task | Final Assembly for Trainset #045 DM2 | 27/06/2024 | 04/11/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 457 | 94810358_457
A181560 | TT_Task | Final Assembly for Trainset #045 T | 15/07/2024 | 20/11/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 458 | 94810358_458
A169520 | TT_Task | Transport Carbody to Henningsdorf for Trainset #045 T | 07/11/2024 | 01/01/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 356 | 94810358_356
A169570 | TT_Task | Transport to Sweden for Trainset #045 | 26/02/2025 | 03/03/2025 | nan | nan | 2424 | TK_NotStart | 94810358 | 427 | 94810358_427
A182440 | TT_Task | Transport Carbody to Henningsdorf for Trainset #045 DM2 | 22/10/2024 | 16/12/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 354 | 94810358_354
A182450 | TT_Task | Transport Carbody to Henningsdorf for Trainset #045 DM1 | 16/10/2024 | 10/12/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 355 | 94810358_355
A169360 | TT_Task | Tempering of CBY for Trainset #045 DM1 | 11/12/2024 | 11/12/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 375 | 94810358_375
A169400 | TT_Task | Fitout 2.7 for Trainset #045 DM1 | 12/12/2024 | 17/12/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 358 | 94810358_358
A180140 | TT_Task | Fitout 2.8 for Trainset #045 DM1 | 18/12/2024 | 02/01/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 358 | 94810358_358
A180150 | TT_Task | Fitout 2.9 for Trainset #045 DM1 | 03/01/2025 | 08/01/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 358 | 94810358_358
A180160 | TT_Task | Single Car Testing for Trainset #045 DM1 | 09/01/2025 | 14/01/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 412 | 94810358_412
A183780 | TT_Task | HP2 for Trainset #045 DM1 | 15/01/2025 | 20/01/2025 | nan | nan | 64 | TK_NotStart | 94810358 | 400 | 94810358_400
A169410 | TT_Task | Fitout 2.7 for Trainset #045 DM2 | 18/12/2024 | 02/01/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 459 | 94810358_459
A180170 | TT_Task | Tempering of CBY for Trainset #045 DM2 | 17/12/2024 | 17/12/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 376 | 94810358_376
A180180 | TT_Task | Fitout 2.8 for Trainset #045 DM2 | 03/01/2025 | 08/01/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 459 | 94810358_459
A180190 | TT_Task | Fitout 2.9 for Trainset #045 DM2 | 09/01/2025 | 14/01/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 459 | 94810358_459
A180200 | TT_Task | Single Car Testing for Trainset #045 DM2 | 15/01/2025 | 20/01/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 416 | 94810358_416
A183790 | TT_Task | HP2 for Trainset #045 DM2 | 21/01/2025 | 24/01/2025 | nan | nan | 32 | TK_NotStart | 94810358 | 400 | 94810358_400
A169420 | TT_Task | Fitout 2.7 for Trainset #045 T | 03/01/2025 | 08/01/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 461 | 94810358_461
A180210 | TT_Task | Tempering of CBY for Trainset #045 T | 02/01/2025 | 02/01/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 380 | 94810358_380
A180220 | TT_Task | Fitout 2.8 for Trainset #045 T | 09/01/2025 | 14/01/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 460 | 94810358_460
A180230 | TT_Task | Fitout 2.9 for Trainset #045 T | 15/01/2025 | 20/01/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 461 | 94810358_461
A180240 | TT_Task | Single Car Testing for Trainset #045 T | 21/01/2025 | 24/01/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 418 | 94810358_418
A183800 | TT_Task | HP2 for Trainset #045 T | 27/01/2025 | 30/01/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 462 | 94810358_462
A169380 | TT_Task | Train Completion for Trainset #045 | 28/01/2025 | 13/02/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 463 | 94810358_463
A169390 | TT_Task | Commissioning for Trainset #045 | 29/01/2025 | 11/02/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 464 | 94810358_464
A169620 | TT_Task | Quality/Customer Acceptance for Trainset #045 | 12/02/2025 | 25/02/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 465 | 94810358_465
A169060 | TT_Task | Preliminary Takeover Inspection for Trainset #045 | 01/01/2026 | 28/01/2026 | nan | nan | 0 | TK_NotStart | 94810358 | 455 | 94810358_455
A169070 | TT_Task | Final Takeover Inspection for Trainset #045 | 29/01/2026 | 25/02/2026 | nan | nan | 0 | TK_NotStart | 94810358 | 406 | 94810358_406
A66480 | TT_Task | Final Assembly for Trainset #041 | 04/04/2024 | 29/07/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 466 | 94810358_466
A77180 | TT_Task | Transport Carbody to Henningsdorf for Trainset #041 | 30/07/2024 | 23/09/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 467 | 94810358_467
A79780 | TT_Task | Transport to Sweden for Trainset #041 | 20/11/2024 | 26/11/2024 | nan | nan | 2756 | TK_NotStart | 94810358 | 427 | 94810358_427
A51470 | TT_Task | Tempering of CBY for Trainset #041 First Carbody | 24/09/2024 | 24/09/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 468 | 94810358_468
A51530 | TT_Task | Train Completion for Trainset #041 | 02/10/2024 | 18/10/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 463 | 94810358_463
A51560 | TT_Task | First Final-assembly Station for Trainset #041 DM2 | 25/09/2024 | 26/09/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 469 | 94810358_469
A51570 | TT_Task | First Final-assembly Station for Trainset #041 DM1 | 26/09/2024 | 30/09/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 470 | 94810358_470
A51580 | TT_Task | First Final-assembly Station for Trainset #041 T1 | 01/10/2024 | 02/10/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 471 | 94810358_471
A51550 | TT_Task | Commissioning for Trainset #041 | 18/10/2024 | 06/11/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 464 | 94810358_464
A80780 | TT_Task | Quality/Customer Acceptance for Trainset #041 | 06/11/2024 | 20/11/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 465 | 94810358_465
A20820 | TT_Task | Preliminary Takeover for Trainset #041 | 06/11/2025 | 03/12/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 472 | 94810358_472
A20830 | TT_Task | Final Takeover for Trainset #041 | 04/12/2025 | 19/01/2026 | nan | nan | 7184 | TK_NotStart | 94810358 | 473 | 94810358_473
A66600 | TT_Task | Final Assembly for Trainset #042 | 11/04/2024 | 06/08/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 466 | 94810358_466
A77210 | TT_Task | Transport Carbody to Henningsdorf for Trainset #042 | 06/08/2024 | 01/10/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 467 | 94810358_467
A79790 | TT_Task | Transport to Sweden for Trainset #042 | 27/11/2024 | 02/12/2024 | nan | nan | 2816 | TK_NotStart | 94810358 | 427 | 94810358_427
A51640 | TT_Task | Tempering of CBY for Trainset #042 First Carbody | 01/10/2024 | 02/10/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 468 | 94810358_468
A51700 | TT_Task | Train Completion for Trainset #042 | 14/10/2024 | 24/10/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 463 | 94810358_463
A51730 | TT_Task | First Final-assembly Station for Trainset #042 DM2 | 02/10/2024 | 07/10/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 469 | 94810358_469
A51740 | TT_Task | First Final-assembly Station for Trainset #042 DM1 | 08/10/2024 | 10/10/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 470 | 94810358_470
A51750 | TT_Task | First Final-assembly Station for Trainset #042 T1 | 10/10/2024 | 11/10/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 471 | 94810358_471
A51720 | TT_Task | Commissioning for Trainset #042 | 25/10/2024 | 12/11/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 464 | 94810358_464
A80790 | TT_Task | Quality/Customer Acceptance for Trainset #042 | 13/11/2024 | 26/11/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 465 | 94810358_465
A20930 | TT_Task | Preliminary Takeover for Trainset #042 | 20/11/2025 | 17/12/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 472 | 94810358_472
A20940 | TT_Task | Final Takeover for Trainset #042 | 18/12/2025 | 02/02/2026 | nan | nan | 7104 | TK_NotStart | 94810358 | 473 | 94810358_473
A66720 | TT_Task | Final Assembly for Trainset #043 | 23/04/2024 | 15/08/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 466 | 94810358_466
A77240 | TT_Task | Transport Carbody to Henningsdorf for Trainset #043 | 16/08/2024 | 10/10/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 467 | 94810358_467
A79800 | TT_Task | Transport to Sweden for Trainset #043 | 03/12/2024 | 09/12/2024 | nan | nan | 2876 | TK_NotStart | 94810358 | 427 | 94810358_427
A51810 | TT_Task | Tempering of CBY for Trainset #043 First Carbody | 11/10/2024 | 11/10/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 468 | 94810358_468
A51870 | TT_Task | Train Completion for Trainset #043 | 21/10/2024 | 01/11/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 463 | 94810358_463
A51900 | TT_Task | First Final-assembly Station for Trainset #043 DM2 | 14/10/2024 | 15/10/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 469 | 94810358_469
A51910 | TT_Task | First Final-assembly Station for Trainset #043 DM1 | 15/10/2024 | 17/10/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 470 | 94810358_470
A51920 | TT_Task | First Final-assembly Station for Trainset #043 T1 | 18/10/2024 | 21/10/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 471 | 94810358_471
A51890 | TT_Task | Commissioning for Trainset #043 | 01/11/2024 | 19/11/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 464 | 94810358_464
A80800 | TT_Task | Quality/Customer Acceptance for Trainset #043 | 19/11/2024 | 03/12/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 465 | 94810358_465
A21040 | TT_Task | Preliminary Takeover for Trainset #043 | 04/12/2025 | 19/01/2026 | nan | nan | 0 | TK_NotStart | 94810358 | 472 | 94810358_472
A21050 | TT_Task | Final Takeover for Trainset #043 | 20/01/2026 | 16/02/2026 | nan | nan | 7024 | TK_NotStart | 94810358 | 473 | 94810358_473
A66840 | TT_Task | Final Assembly for Trainset #044 | 30/04/2024 | 23/08/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 466 | 94810358_466
A77270 | TT_Task | Transport Carbody to Henningsdorf for Trainset #044 | 23/08/2024 | 18/10/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 467 | 94810358_467
A79810 | TT_Task | Transport to Sweden for Trainset #044 | 11/12/2024 | 16/12/2024 | nan | nan | 2928 | TK_NotStart | 94810358 | 427 | 94810358_427
A51980 | TT_Task | Tempering of CBY for Trainset #044 First Carbody | 18/10/2024 | 21/10/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 468 | 94810358_468
A52040 | TT_Task | Train Completion for Trainset #044 | 28/10/2024 | 08/11/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 463 | 94810358_463
A52070 | TT_Task | First Final-assembly Station for Trainset #044 DM2 | 21/10/2024 | 22/10/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 469 | 94810358_469
A52080 | TT_Task | First Final-assembly Station for Trainset #044 DM1 | 23/10/2024 | 24/10/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 470 | 94810358_470
A52090 | TT_Task | First Final-assembly Station for Trainset #044 T1 | 24/10/2024 | 25/10/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 471 | 94810358_471
A52060 | TT_Task | Commissioning for Trainset #044 | 11/11/2024 | 25/11/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 464 | 94810358_464
A80810 | TT_Task | Quality/Customer Acceptance for Trainset #044 | 26/11/2024 | 10/12/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 465 | 94810358_465
A21150 | TT_Task | Preliminary Takeover for Trainset #044 | 18/12/2025 | 02/02/2026 | nan | nan | 0 | TK_NotStart | 94810358 | 472 | 94810358_472
A21160 | TT_Task | Final Takeover for Trainset #044 | 03/02/2026 | 02/03/2026 | nan | nan | 6944 | TK_NotStart | 94810358 | 473 | 94810358_473
A66960 | TT_Task | Final Assembly for Trainset #045 | 07/05/2024 | 29/08/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 466 | 94810358_466
A77300 | TT_Task | Transport Carbody to Henningsdorf for Trainset #045 | 30/08/2024 | 24/10/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 467 | 94810358_467
A79820 | TT_Task | Transport to Sweden for Trainset #045 | 17/12/2024 | 23/12/2024 | nan | nan | 3140 | TK_NotStart | 94810358 | 427 | 94810358_427
A52150 | TT_Task | Tempering of CBY for Trainset #045 First Carbody | 25/10/2024 | 25/10/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 468 | 94810358_468
A52210 | TT_Task | Train Completion for Trainset #045 | 04/11/2024 | 15/11/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 463 | 94810358_463
A52240 | TT_Task | First Final-assembly Station for Trainset #045 DM2 | 28/10/2024 | 29/10/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 469 | 94810358_469
A52250 | TT_Task | First Final-assembly Station for Trainset #045 DM1 | 29/10/2024 | 30/10/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 470 | 94810358_470
A52260 | TT_Task | First Final-assembly Station for Trainset #045 T1 | 01/11/2024 | 04/11/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 471 | 94810358_471
A52230 | TT_Task | Commissioning for Trainset #045 | 15/11/2024 | 02/12/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 464 | 94810358_464
A80820 | TT_Task | Quality/Customer Acceptance for Trainset #045 | 02/12/2024 | 17/12/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 465 | 94810358_465
A21260 | TT_Task | Preliminary Takeover for Trainset #045 | 20/01/2026 | 16/02/2026 | nan | nan | 0 | TK_NotStart | 94810358 | 472 | 94810358_472
A21270 | TT_Task | Final Takeover for Trainset #045 | 17/02/2026 | 16/03/2026 | nan | nan | 6864 | TK_NotStart | 94810358 | 473 | 94810358_473
A67080 | TT_Task | Final Assembly for Trainset #046 | 14/05/2024 | 06/09/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 466 | 94810358_466
A77330 | TT_Task | Transport Carbody to Henningsdorf for Trainset #046 | 06/09/2024 | 01/11/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 467 | 94810358_467
A79830 | TT_Task | Transport to Sweden for Trainset #046 | 03/01/2025 | 08/01/2025 | nan | nan | 3120 | TK_NotStart | 94810358 | 427 | 94810358_427
A52320 | TT_Task | Tempering of CBY for Trainset #046 First Carbody | 01/11/2024 | 04/11/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 468 | 94810358_468
A52380 | TT_Task | Train Completion for Trainset #046 | 12/11/2024 | 21/11/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 463 | 94810358_463
A52410 | TT_Task | First Final-assembly Station for Trainset #046 DM2 | 04/11/2024 | 06/11/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 469 | 94810358_469
A52420 | TT_Task | First Final-assembly Station for Trainset #046 DM1 | 07/11/2024 | 08/11/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 470 | 94810358_470
A52430 | TT_Task | First Final-assembly Station for Trainset #046 T1 | 08/11/2024 | 11/11/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 471 | 94810358_471
A52400 | TT_Task | Commissioning for Trainset #046 | 22/11/2024 | 09/12/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 464 | 94810358_464
A80830 | TT_Task | Quality/Customer Acceptance for Trainset #046 | 10/12/2024 | 02/01/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 465 | 94810358_465
A21370 | TT_Task | Preliminary Takeover for Trainset #046 | 03/02/2026 | 02/03/2026 | nan | nan | 0 | TK_NotStart | 94810358 | 472 | 94810358_472
A21380 | TT_Task | Final Takeover for Trainset #046 | 03/03/2026 | 30/03/2026 | nan | nan | 6784 | TK_NotStart | 94810358 | 473 | 94810358_473
A67200 | TT_Task | Final Assembly for Trainset #047 | 22/05/2024 | 13/09/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 466 | 94810358_466
A77360 | TT_Task | Transport Carbody to Henningsdorf for Trainset #047 | 16/09/2024 | 10/11/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 467 | 94810358_467
A79840 | TT_Task | Transport to Sweden for Trainset #047 | 09/01/2025 | 15/01/2025 | nan | nan | 3180 | TK_NotStart | 94810358 | 427 | 94810358_427
A52490 | TT_Task | Tempering of CBY for Trainset #047 First Carbody | 11/11/2024 | 11/11/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 468 | 94810358_468
A52550 | TT_Task | Train Completion for Trainset #047 | 18/11/2024 | 28/11/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 463 | 94810358_463
A52580 | TT_Task | First Final-assembly Station for Trainset #047 DM2 | 12/11/2024 | 13/11/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 469 | 94810358_469
A52590 | TT_Task | First Final-assembly Station for Trainset #047 DM1 | 13/11/2024 | 14/11/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 470 | 94810358_470
A52600 | TT_Task | First Final-assembly Station for Trainset #047 T1 | 15/11/2024 | 18/11/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 471 | 94810358_471
A52570 | TT_Task | Commissioning for Trainset #047 | 28/11/2024 | 16/12/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 464 | 94810358_464
A80840 | TT_Task | Quality/Customer Acceptance for Trainset #047 | 16/12/2024 | 09/01/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 465 | 94810358_465
A21480 | TT_Task | Preliminary Takeover for Trainset #047 | 17/02/2026 | 16/03/2026 | nan | nan | 0 | TK_NotStart | 94810358 | 472 | 94810358_472
A21490 | TT_Task | Final Takeover for Trainset #047 | 17/03/2026 | 13/04/2026 | nan | nan | 6704 | TK_NotStart | 94810358 | 473 | 94810358_473
A67320 | TT_Task | Final Assembly for Trainset #048 | 28/05/2024 | 20/09/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 466 | 94810358_466
A77390 | TT_Task | Transport Carbody to Henningsdorf for Trainset #048 | 20/09/2024 | 15/11/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 467 | 94810358_467
A79850 | TT_Task | Transport to Sweden for Trainset #048 | 16/01/2025 | 21/01/2025 | nan | nan | 3240 | TK_NotStart | 94810358 | 427 | 94810358_427
A52660 | TT_Task | Tempering of CBY for Trainset #048 First Carbody | 15/11/2024 | 18/11/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 468 | 94810358_468
A52720 | TT_Task | Train Completion for Trainset #048 | 25/11/2024 | 04/12/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 463 | 94810358_463
A52750 | TT_Task | First Final-assembly Station for Trainset #048 DM2 | 18/11/2024 | 19/11/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 469 | 94810358_469
A52760 | TT_Task | First Final-assembly Station for Trainset #048 DM1 | 20/11/2024 | 21/11/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 470 | 94810358_470
A52770 | TT_Task | First Final-assembly Station for Trainset #048 T1 | 21/11/2024 | 22/11/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 471 | 94810358_471
A52740 | TT_Task | Commissioning for Trainset #048 | 05/12/2024 | 01/01/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 464 | 94810358_464
A80850 | TT_Task | Quality/Customer Acceptance for Trainset #048 | 02/01/2025 | 15/01/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 465 | 94810358_465
A21590 | TT_Task | Preliminary Takeover for Trainset #048 | 03/03/2026 | 30/03/2026 | nan | nan | 0 | TK_NotStart | 94810358 | 472 | 94810358_472
A21600 | TT_Task | Final Takeover for Trainset #048 | 31/03/2026 | 27/04/2026 | nan | nan | 6624 | TK_NotStart | 94810358 | 473 | 94810358_473
A67440 | TT_Task | Final Assembly for Trainset #049 | 04/06/2024 | 26/09/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 466 | 94810358_466
A77420 | TT_Task | Transport Carbody to Henningsdorf for Trainset #049 | 27/09/2024 | 21/11/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 467 | 94810358_467
A79860 | TT_Task | Transport to Sweden for Trainset #049 | 22/01/2025 | 28/01/2025 | nan | nan | 3300 | TK_NotStart | 94810358 | 427 | 94810358_427
A52830 | TT_Task | Tempering of CBY for Trainset #049 First Carbody | 22/11/2024 | 22/11/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 468 | 94810358_468
A52890 | TT_Task | Train Completion for Trainset #049 | 29/11/2024 | 12/12/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 463 | 94810358_463
A52920 | TT_Task | First Final-assembly Station for Trainset #049 DM2 | 25/11/2024 | 26/11/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 469 | 94810358_469
A52930 | TT_Task | First Final-assembly Station for Trainset #049 DM1 | 26/11/2024 | 27/11/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 470 | 94810358_470
A52940 | TT_Task | First Final-assembly Station for Trainset #049 T1 | 28/11/2024 | 29/11/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 471 | 94810358_471
A52910 | TT_Task | Commissioning for Trainset #049 | 12/12/2024 | 08/01/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 464 | 94810358_464
A80860 | TT_Task | Quality/Customer Acceptance for Trainset #049 | 08/01/2025 | 22/01/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 465 | 94810358_465
A21700 | TT_Task | Preliminary Takeover for Trainset #049 | 17/03/2026 | 13/04/2026 | nan | nan | 0 | TK_NotStart | 94810358 | 472 | 94810358_472
A21710 | TT_Task | Final Takeover for Trainset #049 | 14/04/2026 | 11/05/2026 | nan | nan | 6544 | TK_NotStart | 94810358 | 473 | 94810358_473
A67560 | TT_Task | Final Assembly for Trainset #050 | 10/06/2024 | 03/10/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 474 | 94810358_474
A77450 | TT_Task | Transport Carbody to Henningsdorf for Trainset #050 | 03/10/2024 | 28/11/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 467 | 94810358_467
A79870 | TT_Task | Transport to Sweden for Trainset #050 | 29/01/2025 | 03/02/2025 | nan | nan | 3360 | TK_NotStart | 94810358 | 427 | 94810358_427
A53000 | TT_Task | Tempering of CBY for Trainset #050 First Carbody | 28/11/2024 | 29/11/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 468 | 94810358_468
A53060 | TT_Task | Train Completion for Trainset #050 | 09/12/2024 | 18/12/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 396 | 94810358_396
A53090 | TT_Task | First Final-assembly Station for Trainset #050 DM2 | 29/11/2024 | 02/12/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 470 | 94810358_470
A53100 | TT_Task | First Final-assembly Station for Trainset #050 DM1 | 03/12/2024 | 04/12/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 470 | 94810358_470
A53110 | TT_Task | First Final-assembly Station for Trainset #050 T1 | 04/12/2024 | 05/12/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 471 | 94810358_471
A53080 | TT_Task | Commissioning for Trainset #050 | 19/12/2024 | 14/01/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 312 | 94810358_312
A80870 | TT_Task | Quality/Customer Acceptance for Trainset #050 | 15/01/2025 | 28/01/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 454 | 94810358_454
A21810 | TT_Task | Preliminary Takeover for Trainset #050 | 31/03/2026 | 27/04/2026 | nan | nan | 0 | TK_NotStart | 94810358 | 475 | 94810358_475
A21820 | TT_Task | Final Takeover for Trainset #050 | 28/04/2026 | 25/05/2026 | nan | nan | 6464 | TK_NotStart | 94810358 | 475 | 94810358_475
A67680 | TT_Task | Final Assembly for Trainset #051 | 17/06/2024 | 09/10/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 474 | 94810358_474
A77480 | TT_Task | Transport Carbody to Henningsdorf for Trainset #051 | 10/10/2024 | 04/12/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 467 | 94810358_467
A79880 | TT_Task | Transport to Sweden for Trainset #051 | 04/02/2025 | 10/02/2025 | nan | nan | 3420 | TK_NotStart | 94810358 | 427 | 94810358_427
A53170 | TT_Task | Tempering of CBY for Trainset #051 First Carbody | 05/12/2024 | 05/12/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 468 | 94810358_468
A53230 | TT_Task | Train Completion for Trainset #051 | 13/12/2024 | 06/01/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 396 | 94810358_396
A53260 | TT_Task | First Final-assembly Station for Trainset #051 DM2 | 09/12/2024 | 10/12/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 469 | 94810358_469
A53270 | TT_Task | First Final-assembly Station for Trainset #051 DM1 | 10/12/2024 | 11/12/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 470 | 94810358_470
A53280 | TT_Task | First Final-assembly Station for Trainset #051 T1 | 12/12/2024 | 13/12/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 471 | 94810358_471
A53250 | TT_Task | Commissioning for Trainset #051 | 06/01/2025 | 21/01/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 312 | 94810358_312
A80880 | TT_Task | Quality/Customer Acceptance for Trainset #051 | 21/01/2025 | 04/02/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 454 | 94810358_454
A21920 | TT_Task | Preliminary Takeover for Trainset #051 | 14/04/2026 | 11/05/2026 | nan | nan | 0 | TK_NotStart | 94810358 | 472 | 94810358_472
A21930 | TT_Task | Final Takeover for Trainset #051 | 12/05/2026 | 08/06/2026 | nan | nan | 6384 | TK_NotStart | 94810358 | 473 | 94810358_473
A67800 | TT_Task | Final Assembly for Trainset #052 | 24/06/2024 | 17/10/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 474 | 94810358_474
A77510 | TT_Task | Transport Carbody to Henningsdorf for Trainset #052 | 17/10/2024 | 12/12/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 467 | 94810358_467
A79890 | TT_Task | Transport to Sweden for Trainset #052 | 11/02/2025 | 16/02/2025 | nan | nan | 3480 | TK_NotStart | 94810358 | 427 | 94810358_427
A53340 | TT_Task | Tempering of CBY for Trainset #052 First Carbody | 12/12/2024 | 13/12/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 468 | 94810358_468
A53400 | TT_Task | Train Completion for Trainset #052 | 01/01/2025 | 10/01/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 396 | 94810358_396
A53430 | TT_Task | First Final-assembly Station for Trainset #052 DM2 | 13/12/2024 | 16/12/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 469 | 94810358_469
A53440 | TT_Task | First Final-assembly Station for Trainset #052 DM1 | 17/12/2024 | 18/12/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 470 | 94810358_470
A53450 | TT_Task | First Final-assembly Station for Trainset #052 T1 | 18/12/2024 | 19/12/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 471 | 94810358_471
A53420 | TT_Task | Commissioning for Trainset #052 | 13/01/2025 | 27/01/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 312 | 94810358_312
A80890 | TT_Task | Quality/Customer Acceptance for Trainset #052 | 28/01/2025 | 10/02/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 454 | 94810358_454
A22030 | TT_Task | Preliminary Takeover for Trainset #052 | 28/04/2026 | 25/05/2026 | nan | nan | 0 | TK_NotStart | 94810358 | 472 | 94810358_472
A22040 | TT_Task | Final Takeover for Trainset #052 | 26/05/2026 | 22/06/2026 | nan | nan | 6304 | TK_NotStart | 94810358 | 473 | 94810358_473
A67920 | TT_Task | Final Assembly for Trainset #053 | 01/07/2024 | 23/10/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 474 | 94810358_474
A77540 | TT_Task | Transport Carbody to Henningsdorf for Trainset #053 | 24/10/2024 | 18/12/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 467 | 94810358_467
A79900 | TT_Task | Transport to Sweden for Trainset #053 | 17/02/2025 | 23/02/2025 | nan | nan | 3540 | TK_NotStart | 94810358 | 427 | 94810358_427
A53510 | TT_Task | Tempering of CBY for Trainset #053 First Carbody | 19/12/2024 | 19/12/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 468 | 94810358_468
A53570 | TT_Task | Train Completion for Trainset #053 | 07/01/2025 | 17/01/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 396 | 94810358_396
A53600 | TT_Task | First Final-assembly Station for Trainset #053 DM2 | 01/01/2025 | 02/01/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 469 | 94810358_469
A53610 | TT_Task | First Final-assembly Station for Trainset #053 DM1 | 02/01/2025 | 03/01/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 470 | 94810358_470
A53620 | TT_Task | First Final-assembly Station for Trainset #053 T1 | 06/01/2025 | 07/01/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 471 | 94810358_471
A53590 | TT_Task | Commissioning for Trainset #053 | 17/01/2025 | 03/02/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 312 | 94810358_312
A80900 | TT_Task | Quality/Customer Acceptance for Trainset #053 | 03/02/2025 | 17/02/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 454 | 94810358_454
A22140 | TT_Task | Preliminary Takeover for Trainset #053 | 12/05/2026 | 08/06/2026 | nan | nan | 0 | TK_NotStart | 94810358 | 472 | 94810358_472
A22150 | TT_Task | Final Takeover for Trainset #053 | 09/06/2026 | 06/08/2026 | nan | nan | 6224 | TK_NotStart | 94810358 | 473 | 94810358_473
A68040 | TT_Task | Final Assembly for Trainset #054 | 17/07/2024 | 11/11/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 474 | 94810358_474
A77570 | TT_Task | Transport Carbody to Henningsdorf for Trainset #054 | 11/11/2024 | 06/01/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 467 | 94810358_467
A79910 | TT_Task | Transport to Sweden for Trainset #054 | 22/02/2025 | 27/02/2025 | nan | nan | 3616 | TK_NotStart | 94810358 | 427 | 94810358_427
A53680 | TT_Task | Tempering of CBY for Trainset #054 First Carbody | 06/01/2025 | 07/01/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 468 | 94810358_468
A53740 | TT_Task | Train Completion for Trainset #054 | 14/01/2025 | 23/01/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 396 | 94810358_396
A53770 | TT_Task | First Final-assembly Station for Trainset #054 DM2 | 07/01/2025 | 08/01/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 469 | 94810358_469
A53780 | TT_Task | First Final-assembly Station for Trainset #054 DM1 | 09/01/2025 | 10/01/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 470 | 94810358_470
A53790 | TT_Task | First Final-assembly Station for Trainset #054 T1 | 10/01/2025 | 13/01/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 471 | 94810358_471
A53760 | TT_Task | Commissioning for Trainset #054 | 24/01/2025 | 07/02/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 312 | 94810358_312
A80910 | TT_Task | Quality/Customer Acceptance for Trainset #054 | 10/02/2025 | 21/02/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 454 | 94810358_454
A22250 | TT_Task | Preliminary Takeover for Trainset #054 | 26/05/2026 | 22/06/2026 | nan | nan | 0 | TK_NotStart | 94810358 | 472 | 94810358_472
A22260 | TT_Task | Final Takeover for Trainset #054 | 23/06/2026 | 20/08/2026 | nan | nan | 6144 | TK_NotStart | 94810358 | 473 | 94810358_473
A68160 | TT_Task | Final Assembly for Trainset #055 | 24/07/2024 | 15/11/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 474 | 94810358_474
A77600 | TT_Task | Transport Carbody to Henningsdorf for Trainset #055 | 18/11/2024 | 12/01/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 467 | 94810358_467
A79920 | TT_Task | Transport to Sweden for Trainset #055 | 28/02/2025 | 06/03/2025 | nan | nan | 3676 | TK_NotStart | 94810358 | 427 | 94810358_427
A53850 | TT_Task | Tempering of CBY for Trainset #055 First Carbody | 13/01/2025 | 13/01/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 468 | 94810358_468
A53910 | TT_Task | Train Completion for Trainset #055 | 20/01/2025 | 30/01/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 396 | 94810358_396
A53940 | TT_Task | First Final-assembly Station for Trainset #055 DM2 | 14/01/2025 | 15/01/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 469 | 94810358_469
A53950 | TT_Task | First Final-assembly Station for Trainset #055 DM1 | 15/01/2025 | 16/01/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 470 | 94810358_470
A53960 | TT_Task | First Final-assembly Station for Trainset #055 T1 | 17/01/2025 | 20/01/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 471 | 94810358_471
A53930 | TT_Task | Commissioning for Trainset #055 | 30/01/2025 | 14/02/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 312 | 94810358_312
A80920 | TT_Task | Quality/Customer Acceptance for Trainset #055 | 14/02/2025 | 28/02/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 454 | 94810358_454
A22360 | TT_Task | Preliminary Takeover for Trainset #055 | 09/06/2026 | 06/08/2026 | nan | nan | 0 | TK_NotStart | 94810358 | 472 | 94810358_472
A22370 | TT_Task | Final Takeover for Trainset #055 | 07/08/2026 | 03/09/2026 | nan | nan | 6064 | TK_NotStart | 94810358 | 473 | 94810358_473
A68280 | TT_Task | Final Assembly for Trainset #056 | 30/07/2024 | 22/11/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 474 | 94810358_474
A77630 | TT_Task | Transport Carbody to Henningsdorf for Trainset #056 | 22/11/2024 | 17/01/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 467 | 94810358_467
A79930 | TT_Task | Transport to Sweden for Trainset #056 | 07/03/2025 | 12/03/2025 | nan | nan | 3736 | TK_NotStart | 94810358 | 427 | 94810358_427
A54020 | TT_Task | Tempering of CBY for Trainset #056 First Carbody | 17/01/2025 | 20/01/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 468 | 94810358_468
A54080 | TT_Task | Train Completion for Trainset #056 | 27/01/2025 | 05/02/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 396 | 94810358_396
A54110 | TT_Task | First Final-assembly Station for Trainset #056 DM2 | 20/01/2025 | 21/01/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 469 | 94810358_469
A54120 | TT_Task | First Final-assembly Station for Trainset #056 DM1 | 22/01/2025 | 23/01/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 470 | 94810358_470
A54130 | TT_Task | First Final-assembly Station for Trainset #056 T1 | 23/01/2025 | 24/01/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 471 | 94810358_471
A54100 | TT_Task | Commissioning for Trainset #056 | 06/02/2025 | 20/02/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 312 | 94810358_312
A80930 | TT_Task | Quality/Customer Acceptance for Trainset #056 | 21/02/2025 | 06/03/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 454 | 94810358_454
A22470 | TT_Task | Preliminary Takeover for Trainset #056 | 23/06/2026 | 20/08/2026 | nan | nan | 0 | TK_NotStart | 94810358 | 472 | 94810358_472
A22480 | TT_Task | Final Takeover for Trainset #056 | 21/08/2026 | 17/09/2026 | nan | nan | 5984 | TK_NotStart | 94810358 | 473 | 94810358_473
A68400 | TT_Task | Final Assembly for Trainset #057 | 06/08/2024 | 28/11/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 474 | 94810358_474
A77660 | TT_Task | Transport Carbody to Henningsdorf for Trainset #057 | 29/11/2024 | 23/01/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 467 | 94810358_467
A79940 | TT_Task | Transport to Sweden for Trainset #057 | 13/03/2025 | 19/03/2025 | nan | nan | 4044 | TK_NotStart | 94810358 | 427 | 94810358_427
A54190 | TT_Task | Tempering of CBY for Trainset #057 First Carbody | 24/01/2025 | 24/01/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 468 | 94810358_468
A54250 | TT_Task | Train Completion for Trainset #057 | 31/01/2025 | 12/02/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 396 | 94810358_396
A54280 | TT_Task | First Final-assembly Station for Trainset #057 DM2 | 27/01/2025 | 28/01/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 469 | 94810358_469
A54290 | TT_Task | First Final-assembly Station for Trainset #057 DM1 | 28/01/2025 | 29/01/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 470 | 94810358_470
A54300 | TT_Task | First Final-assembly Station for Trainset #057 T1 | 30/01/2025 | 31/01/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 471 | 94810358_471
A54270 | TT_Task | Commissioning for Trainset #057 | 12/02/2025 | 27/02/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 312 | 94810358_312
A80940 | TT_Task | Quality/Customer Acceptance for Trainset #057 | 27/02/2025 | 13/03/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 454 | 94810358_454
A22580 | TT_Task | Preliminary Takeover for Trainset #057 | 07/08/2026 | 03/09/2026 | nan | nan | 0 | TK_NotStart | 94810358 | 472 | 94810358_472
A22590 | TT_Task | Final Takeover for Trainset #057 | 04/09/2026 | 01/10/2026 | nan | nan | 5904 | TK_NotStart | 94810358 | 473 | 94810358_473
A68520 | TT_Task | Final Assembly for Trainset #058 | 12/08/2024 | 05/12/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 474 | 94810358_474
A77690 | TT_Task | Transport Carbody to Henningsdorf for Trainset #058 | 05/12/2024 | 30/01/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 467 | 94810358_467
A79950 | TT_Task | Transport to Sweden for Trainset #058 | 20/03/2025 | 25/03/2025 | nan | nan | 4104 | TK_NotStart | 94810358 | 427 | 94810358_427
A54360 | TT_Task | Tempering of CBY for Trainset #058 First Carbody | 30/01/2025 | 31/01/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 468 | 94810358_468
A54420 | TT_Task | Train Completion for Trainset #058 | 07/02/2025 | 18/02/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 396 | 94810358_396
A54450 | TT_Task | First Final-assembly Station for Trainset #058 DM2 | 31/01/2025 | 03/02/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 469 | 94810358_469
A54460 | TT_Task | First Final-assembly Station for Trainset #058 DM1 | 04/02/2025 | 05/02/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 470 | 94810358_470
A54470 | TT_Task | First Final-assembly Station for Trainset #058 T1 | 05/02/2025 | 06/02/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 471 | 94810358_471
A54440 | TT_Task | Commissioning for Trainset #058 | 19/02/2025 | 05/03/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 312 | 94810358_312
A80950 | TT_Task | Quality/Customer Acceptance for Trainset #058 | 06/03/2025 | 19/03/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 454 | 94810358_454
A22690 | TT_Task | Preliminary Takeover for Trainset #058 | 21/08/2026 | 17/09/2026 | nan | nan | 0 | TK_NotStart | 94810358 | 472 | 94810358_472
A22700 | TT_Task | Final Takeover for Trainset #058 | 18/09/2026 | 15/10/2026 | nan | nan | 5824 | TK_NotStart | 94810358 | 473 | 94810358_473
A68640 | TT_Task | Final Assembly for Trainset #059 | 19/08/2024 | 11/12/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 474 | 94810358_474
A77720 | TT_Task | Transport Carbody to Henningsdorf for Trainset #059 | 12/12/2024 | 05/02/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 467 | 94810358_467
A79960 | TT_Task | Transport to Sweden for Trainset #059 | 26/03/2025 | 01/04/2025 | nan | nan | 4164 | TK_NotStart | 94810358 | 427 | 94810358_427
A54530 | TT_Task | Tempering of CBY for Trainset #059 First Carbody | 06/02/2025 | 06/02/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 468 | 94810358_468
A54590 | TT_Task | Train Completion for Trainset #059 | 13/02/2025 | 25/02/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 396 | 94810358_396
A54620 | TT_Task | First Final-assembly Station for Trainset #059 DM2 | 07/02/2025 | 10/02/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 469 | 94810358_469
A54630 | TT_Task | First Final-assembly Station for Trainset #059 DM1 | 10/02/2025 | 11/02/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 470 | 94810358_470
A54640 | TT_Task | First Final-assembly Station for Trainset #059 T1 | 12/02/2025 | 13/02/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 471 | 94810358_471
A54610 | TT_Task | Commissioning for Trainset #059 | 25/02/2025 | 12/03/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 312 | 94810358_312
A80960 | TT_Task | Quality/Customer Acceptance for Trainset #059 | 12/03/2025 | 26/03/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 454 | 94810358_454
A22800 | TT_Task | Preliminary Takeover for Trainset #059 | 04/09/2026 | 01/10/2026 | nan | nan | 0 | TK_NotStart | 94810358 | 472 | 94810358_472
A22810 | TT_Task | Final Takeover for Trainset #059 | 02/10/2026 | 29/10/2026 | nan | nan | 5744 | TK_NotStart | 94810358 | 473 | 94810358_473
A68760 | TT_Task | Final Assembly for Trainset #060 | 23/08/2024 | 18/12/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 474 | 94810358_474
A77750 | TT_Task | Transport Carbody to Henningsdorf for Trainset #060 | 18/12/2024 | 12/02/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 467 | 94810358_467
A79970 | TT_Task | Transport to Sweden for Trainset #060 | 02/04/2025 | 07/04/2025 | nan | nan | 4224 | TK_NotStart | 94810358 | 427 | 94810358_427
A54700 | TT_Task | Tempering of CBY for Trainset #060 First Carbody | 12/02/2025 | 13/02/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 468 | 94810358_468
A54760 | TT_Task | Train Completion for Trainset #060 | 20/02/2025 | 03/03/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 396 | 94810358_396
A54790 | TT_Task | First Final-assembly Station for Trainset #060 DM2 | 13/02/2025 | 14/02/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 469 | 94810358_469
A54800 | TT_Task | First Final-assembly Station for Trainset #060 DM1 | 17/02/2025 | 18/02/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 470 | 94810358_470
A54810 | TT_Task | First Final-assembly Station for Trainset #060 T1 | 18/02/2025 | 19/02/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 471 | 94810358_471
A54780 | TT_Task | Commissioning for Trainset #060 | 04/03/2025 | 18/03/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 312 | 94810358_312
A80970 | TT_Task | Quality/Customer Acceptance for Trainset #060 | 19/03/2025 | 01/04/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 454 | 94810358_454
A22910 | TT_Task | Preliminary Takeover for Trainset #060 | 18/09/2026 | 15/10/2026 | nan | nan | 0 | TK_NotStart | 94810358 | 472 | 94810358_472
A22920 | TT_Task | Final Takeover for Trainset #060 | 16/10/2026 | 12/11/2026 | nan | nan | 5664 | TK_NotStart | 94810358 | 473 | 94810358_473
A68880 | TT_Task | Final Assembly for Trainset #061 | 30/08/2024 | 24/12/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 474 | 94810358_474
A77780 | TT_Task | Transport Carbody to Henningsdorf for Trainset #061 | 25/12/2024 | 18/02/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 467 | 94810358_467
A79980 | TT_Task | Transport to Sweden for Trainset #061 | 08/04/2025 | 14/04/2025 | nan | nan | 4284 | TK_NotStart | 94810358 | 427 | 94810358_427
A54870 | TT_Task | Tempering of CBY for Trainset #061 First Carbody | 19/02/2025 | 19/02/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 468 | 94810358_468
A54930 | TT_Task | Train Completion for Trainset #061 | 26/02/2025 | 10/03/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 396 | 94810358_396
A54960 | TT_Task | First Final-assembly Station for Trainset #061 DM2 | 20/02/2025 | 21/02/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 469 | 94810358_469
A54970 | TT_Task | First Final-assembly Station for Trainset #061 DM1 | 21/02/2025 | 24/02/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 470 | 94810358_470
A54980 | TT_Task | First Final-assembly Station for Trainset #061 T1 | 25/02/2025 | 26/02/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 471 | 94810358_471
A54950 | TT_Task | Commissioning for Trainset #061 | 10/03/2025 | 25/03/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 312 | 94810358_312
A80980 | TT_Task | Quality/Customer Acceptance for Trainset #061 | 25/03/2025 | 08/04/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 454 | 94810358_454
A23020 | TT_Task | Preliminary Takeover for Trainset #061 | 02/10/2026 | 29/10/2026 | nan | nan | 0 | TK_NotStart | 94810358 | 472 | 94810358_472
A23030 | TT_Task | Final Takeover for Trainset #061 | 30/10/2026 | 26/11/2026 | nan | nan | 5584 | TK_NotStart | 94810358 | 473 | 94810358_473
A69000 | TT_Task | Final Assembly for Trainset #062 | 05/09/2024 | 31/12/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 474 | 94810358_474
A77810 | TT_Task | Transport Carbody to Henningsdorf for Trainset #062 | 31/12/2024 | 25/02/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 467 | 94810358_467
A79990 | TT_Task | Transport to Sweden for Trainset #062 | 15/04/2025 | 20/04/2025 | nan | nan | 4344 | TK_NotStart | 94810358 | 427 | 94810358_427
A55040 | TT_Task | Tempering of CBY for Trainset #062 First Carbody | 25/02/2025 | 26/02/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 468 | 94810358_468
A55100 | TT_Task | Train Completion for Trainset #062 | 05/03/2025 | 14/03/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 396 | 94810358_396
A55130 | TT_Task | First Final-assembly Station for Trainset #062 DM2 | 26/02/2025 | 27/02/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 469 | 94810358_469
A55140 | TT_Task | First Final-assembly Station for Trainset #062 DM1 | 28/02/2025 | 03/03/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 470 | 94810358_470
A55150 | TT_Task | First Final-assembly Station for Trainset #062 T1 | 03/03/2025 | 04/03/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 471 | 94810358_471
A55120 | TT_Task | Commissioning for Trainset #062 | 17/03/2025 | 31/03/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 312 | 94810358_312
A80990 | TT_Task | Quality/Customer Acceptance for Trainset #062 | 01/04/2025 | 14/04/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 454 | 94810358_454
A23130 | TT_Task | Preliminary Takeover for Trainset #062 | 16/10/2026 | 12/11/2026 | nan | nan | 0 | TK_NotStart | 94810358 | 472 | 94810358_472
A23140 | TT_Task | Final Takeover for Trainset #062 | 13/11/2026 | 10/12/2026 | nan | nan | 5504 | TK_NotStart | 94810358 | 473 | 94810358_473
A69120 | TT_Task | Final Assembly for Trainset #063 | 12/09/2024 | 06/01/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 474 | 94810358_474
A77840 | TT_Task | Transport Carbody to Henningsdorf for Trainset #063 | 07/01/2025 | 03/03/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 467 | 94810358_467
A80000 | TT_Task | Transport to Sweden for Trainset #063 | 21/04/2025 | 27/04/2025 | nan | nan | 4404 | TK_NotStart | 94810358 | 427 | 94810358_427
A55210 | TT_Task | Tempering of CBY for Trainset #063 First Carbody | 04/03/2025 | 04/03/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 468 | 94810358_468
A55270 | TT_Task | Train Completion for Trainset #063 | 11/03/2025 | 21/03/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 396 | 94810358_396
A55300 | TT_Task | First Final-assembly Station for Trainset #063 DM2 | 05/03/2025 | 06/03/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 469 | 94810358_469
A55310 | TT_Task | First Final-assembly Station for Trainset #063 DM1 | 06/03/2025 | 07/03/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 470 | 94810358_470
A55320 | TT_Task | First Final-assembly Station for Trainset #063 T1 | 10/03/2025 | 11/03/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 471 | 94810358_471
A55290 | TT_Task | Commissioning for Trainset #063 | 21/03/2025 | 07/04/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 312 | 94810358_312
A81000 | TT_Task | Quality/Customer Acceptance for Trainset #063 | 07/04/2025 | 21/04/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 454 | 94810358_454
A23240 | TT_Task | Preliminary Takeover for Trainset #063 | 30/10/2026 | 26/11/2026 | nan | nan | 0 | TK_NotStart | 94810358 | 472 | 94810358_472
A23250 | TT_Task | Final Takeover for Trainset #063 | 27/11/2026 | 13/01/2027 | nan | nan | 5424 | TK_NotStart | 94810358 | 473 | 94810358_473
A69240 | TT_Task | Final Assembly for Trainset #064 | 18/09/2024 | 13/01/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 474 | 94810358_474
A77870 | TT_Task | Transport Carbody to Henningsdorf for Trainset #064 | 13/01/2025 | 10/03/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 467 | 94810358_467
A80010 | TT_Task | Transport to Sweden for Trainset #064 | 26/04/2025 | 01/05/2025 | nan | nan | 4480 | TK_NotStart | 94810358 | 427 | 94810358_427
A55380 | TT_Task | Tempering of CBY for Trainset #064 First Carbody | 10/03/2025 | 11/03/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 468 | 94810358_468
A55440 | TT_Task | Train Completion for Trainset #064 | 18/03/2025 | 27/03/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 396 | 94810358_396
A55470 | TT_Task | First Final-assembly Station for Trainset #064 DM2 | 11/03/2025 | 12/03/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 469 | 94810358_469
A55480 | TT_Task | First Final-assembly Station for Trainset #064 DM1 | 13/03/2025 | 14/03/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 470 | 94810358_470
A55490 | TT_Task | First Final-assembly Station for Trainset #064 T1 | 14/03/2025 | 17/03/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 471 | 94810358_471
A55460 | TT_Task | Commissioning for Trainset #064 | 28/03/2025 | 11/04/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 312 | 94810358_312
A81010 | TT_Task | Quality/Customer Acceptance for Trainset #064 | 14/04/2025 | 25/04/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 454 | 94810358_454
A23350 | TT_Task | Preliminary Takeover for Trainset #064 | 13/11/2026 | 10/12/2026 | nan | nan | 0 | TK_NotStart | 94810358 | 472 | 94810358_472
A23360 | TT_Task | Final Takeover for Trainset #064 | 11/12/2026 | 27/01/2027 | nan | nan | 5344 | TK_NotStart | 94810358 | 473 | 94810358_473
A69360 | TT_Task | Final Assembly for Trainset #065 | 25/09/2024 | 17/01/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 474 | 94810358_474
A77900 | TT_Task | Transport Carbody to Henningsdorf for Trainset #065 | 20/01/2025 | 16/03/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 467 | 94810358_467
A80020 | TT_Task | Transport to Sweden for Trainset #065 | 02/05/2025 | 08/05/2025 | nan | nan | 4540 | TK_NotStart | 94810358 | 427 | 94810358_427
A55550 | TT_Task | Tempering of CBY for Trainset #065 First Carbody | 17/03/2025 | 17/03/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 468 | 94810358_468
A55610 | TT_Task | Train Completion for Trainset #065 | 24/03/2025 | 03/04/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 396 | 94810358_396
A55640 | TT_Task | First Final-assembly Station for Trainset #065 DM2 | 18/03/2025 | 19/03/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 469 | 94810358_469
A55650 | TT_Task | First Final-assembly Station for Trainset #065 DM1 | 19/03/2025 | 20/03/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 470 | 94810358_470
A55660 | TT_Task | First Final-assembly Station for Trainset #065 T1 | 21/03/2025 | 24/03/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 471 | 94810358_471
A55630 | TT_Task | Commissioning for Trainset #065 | 03/04/2025 | 18/04/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 312 | 94810358_312
A81020 | TT_Task | Quality/Customer Acceptance for Trainset #065 | 18/04/2025 | 02/05/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 454 | 94810358_454
A23460 | TT_Task | Preliminary Takeover for Trainset #065 | 27/11/2026 | 13/01/2027 | nan | nan | 0 | TK_NotStart | 94810358 | 472 | 94810358_472
A23470 | TT_Task | Final Takeover for Trainset #065 | 14/01/2027 | 10/02/2027 | nan | nan | 5264 | TK_NotStart | 94810358 | 473 | 94810358_473
A69480 | TT_Task | Final Assembly for Trainset #066 | 01/10/2024 | 24/01/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 474 | 94810358_474
A77930 | TT_Task | Transport Carbody to Henningsdorf for Trainset #066 | 24/01/2025 | 21/03/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 467 | 94810358_467
A80030 | TT_Task | Transport to Sweden for Trainset #066 | 09/05/2025 | 14/05/2025 | nan | nan | 4600 | TK_NotStart | 94810358 | 427 | 94810358_427
A55720 | TT_Task | Tempering of CBY for Trainset #066 First Carbody | 21/03/2025 | 24/03/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 468 | 94810358_468
A55780 | TT_Task | Train Completion for Trainset #066 | 31/03/2025 | 09/04/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 396 | 94810358_396
A55810 | TT_Task | First Final-assembly Station for Trainset #066 DM2 | 24/03/2025 | 25/03/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 469 | 94810358_469
A55820 | TT_Task | First Final-assembly Station for Trainset #066 DM1 | 26/03/2025 | 27/03/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 470 | 94810358_470
A55830 | TT_Task | First Final-assembly Station for Trainset #066 T1 | 27/03/2025 | 28/03/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 471 | 94810358_471
A55800 | TT_Task | Commissioning for Trainset #066 | 10/04/2025 | 24/04/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 312 | 94810358_312
A81030 | TT_Task | Quality/Customer Acceptance for Trainset #066 | 25/04/2025 | 08/05/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 454 | 94810358_454
A23570 | TT_Task | Preliminary Takeover for Trainset #066 | 11/12/2026 | 27/01/2027 | nan | nan | 0 | TK_NotStart | 94810358 | 472 | 94810358_472
A23580 | TT_Task | Final Takeover for Trainset #066 | 28/01/2027 | 24/02/2027 | nan | nan | 5184 | TK_NotStart | 94810358 | 473 | 94810358_473
A69600 | TT_Task | Final Assembly for Trainset #067 | 08/10/2024 | 30/01/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 474 | 94810358_474
A77960 | TT_Task | Transport Carbody to Henningsdorf for Trainset #067 | 31/01/2025 | 27/03/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 467 | 94810358_467
A80040 | TT_Task | Transport to Sweden for Trainset #067 | 15/05/2025 | 21/05/2025 | nan | nan | 4820 | TK_NotStart | 94810358 | 427 | 94810358_427
A55890 | TT_Task | Tempering of CBY for Trainset #067 First Carbody | 28/03/2025 | 28/03/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 468 | 94810358_468
A55950 | TT_Task | Train Completion for Trainset #067 | 04/04/2025 | 16/04/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 396 | 94810358_396
A55980 | TT_Task | First Final-assembly Station for Trainset #067 DM2 | 31/03/2025 | 01/04/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 469 | 94810358_469
A55990 | TT_Task | First Final-assembly Station for Trainset #067 DM1 | 01/04/2025 | 02/04/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 470 | 94810358_470
A56000 | TT_Task | First Final-assembly Station for Trainset #067 T1 | 03/04/2025 | 04/04/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 471 | 94810358_471
A55970 | TT_Task | Commissioning for Trainset #067 | 16/04/2025 | 01/05/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 312 | 94810358_312
A81040 | TT_Task | Quality/Customer Acceptance for Trainset #067 | 01/05/2025 | 15/05/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 454 | 94810358_454
A23680 | TT_Task | Preliminary Takeover for Trainset #067 | 14/01/2027 | 10/02/2027 | nan | nan | 0 | TK_NotStart | 94810358 | 472 | 94810358_472
A23690 | TT_Task | Final Takeover for Trainset #067 | 11/02/2027 | 10/03/2027 | nan | nan | 5104 | TK_NotStart | 94810358 | 473 | 94810358_473
A69720 | TT_Task | Final Assembly for Trainset #068 | 14/10/2024 | 06/02/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 474 | 94810358_474
A77990 | TT_Task | Transport Carbody to Henningsdorf for Trainset #068 | 06/02/2025 | 03/04/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 467 | 94810358_467
A80050 | TT_Task | Transport to Sweden for Trainset #068 | 22/05/2025 | 27/05/2025 | nan | nan | 4880 | TK_NotStart | 94810358 | 427 | 94810358_427
A56060 | TT_Task | Tempering of CBY for Trainset #068 First Carbody | 03/04/2025 | 04/04/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 468 | 94810358_468
A56120 | TT_Task | Train Completion for Trainset #068 | 11/04/2025 | 22/04/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 396 | 94810358_396
A56150 | TT_Task | First Final-assembly Station for Trainset #068 DM2 | 04/04/2025 | 07/04/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 469 | 94810358_469
A56160 | TT_Task | First Final-assembly Station for Trainset #068 DM1 | 08/04/2025 | 09/04/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 470 | 94810358_470
A56170 | TT_Task | First Final-assembly Station for Trainset #068 T1 | 09/04/2025 | 10/04/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 471 | 94810358_471
A56140 | TT_Task | Commissioning for Trainset #068 | 23/04/2025 | 07/05/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 312 | 94810358_312
A81050 | TT_Task | Quality/Customer Acceptance for Trainset #068 | 08/05/2025 | 21/05/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 454 | 94810358_454
A23790 | TT_Task | Preliminary Takeover for Trainset #068 | 28/01/2027 | 24/02/2027 | nan | nan | 0 | TK_NotStart | 94810358 | 472 | 94810358_472
A23800 | TT_Task | Final Takeover for Trainset #068 | 25/02/2027 | 24/03/2027 | nan | nan | 5024 | TK_NotStart | 94810358 | 473 | 94810358_473
A69840 | TT_Task | Final Assembly for Trainset #069 | 21/10/2024 | 12/02/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 474 | 94810358_474
A78020 | TT_Task | Transport Carbody to Henningsdorf for Trainset #069 | 13/02/2025 | 09/04/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 467 | 94810358_467
A80060 | TT_Task | Transport to Sweden for Trainset #069 | 28/05/2025 | 03/06/2025 | nan | nan | 4940 | TK_NotStart | 94810358 | 427 | 94810358_427
A56230 | TT_Task | Tempering of CBY for Trainset #069 First Carbody | 10/04/2025 | 10/04/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 468 | 94810358_468
A56290 | TT_Task | Train Completion for Trainset #069 | 17/04/2025 | 29/04/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 396 | 94810358_396
A56320 | TT_Task | First Final-assembly Station for Trainset #069 DM2 | 11/04/2025 | 14/04/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 469 | 94810358_469
A56330 | TT_Task | First Final-assembly Station for Trainset #069 DM1 | 14/04/2025 | 15/04/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 470 | 94810358_470
A56340 | TT_Task | First Final-assembly Station for Trainset #069 T1 | 16/04/2025 | 17/04/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 471 | 94810358_471
A56310 | TT_Task | Commissioning for Trainset #069 | 29/04/2025 | 14/05/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 312 | 94810358_312
A81060 | TT_Task | Quality/Customer Acceptance for Trainset #069 | 14/05/2025 | 28/05/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 454 | 94810358_454
A23900 | TT_Task | Preliminary Takeover for Trainset #069 | 11/02/2027 | 10/03/2027 | nan | nan | 0 | TK_NotStart | 94810358 | 472 | 94810358_472
A23910 | TT_Task | Final Takeover for Trainset #069 | 11/03/2027 | 07/04/2027 | nan | nan | 4944 | TK_NotStart | 94810358 | 473 | 94810358_473
A69960 | TT_Task | Final Assembly for Trainset #070 | 25/10/2024 | 19/02/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 474 | 94810358_474
A78050 | TT_Task | Transport Carbody to Henningsdorf for Trainset #070 | 19/02/2025 | 16/04/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 467 | 94810358_467
A80070 | TT_Task | Transport to Sweden for Trainset #070 | 04/06/2025 | 09/06/2025 | nan | nan | 5000 | TK_NotStart | 94810358 | 427 | 94810358_427
A56400 | TT_Task | Tempering of CBY for Trainset #070 First Carbody | 16/04/2025 | 17/04/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 468 | 94810358_468
A56460 | TT_Task | Train Completion for Trainset #070 | 24/04/2025 | 05/05/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 396 | 94810358_396
A56490 | TT_Task | First Final-assembly Station for Trainset #070 DM2 | 17/04/2025 | 18/04/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 469 | 94810358_469
A56500 | TT_Task | First Final-assembly Station for Trainset #070 DM1 | 21/04/2025 | 22/04/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 470 | 94810358_470
A56510 | TT_Task | First Final-assembly Station for Trainset #070 T1 | 22/04/2025 | 23/04/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 471 | 94810358_471
A56480 | TT_Task | Commissioning for Trainset #070 | 06/05/2025 | 20/05/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 312 | 94810358_312
A81070 | TT_Task | Quality/Customer Acceptance for Trainset #070 | 21/05/2025 | 03/06/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 454 | 94810358_454
A24010 | TT_Task | Preliminary Takeover for Trainset #070 | 25/02/2027 | 24/03/2027 | nan | nan | 0 | TK_NotStart | 94810358 | 472 | 94810358_472
A24020 | TT_Task | Final Takeover for Trainset #070 | 25/03/2027 | 21/04/2027 | nan | nan | 4864 | TK_NotStart | 94810358 | 473 | 94810358_473
A70080 | TT_Task | Final Assembly for Trainset #071 | 01/11/2024 | 25/02/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 474 | 94810358_474
A78080 | TT_Task | Transport Carbody to Henningsdorf for Trainset #071 | 26/02/2025 | 22/04/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 467 | 94810358_467
A80080 | TT_Task | Transport to Sweden for Trainset #071 | 10/06/2025 | 16/06/2025 | nan | nan | 5060 | TK_NotStart | 94810358 | 427 | 94810358_427
A56570 | TT_Task | Tempering of CBY for Trainset #071 First Carbody | 23/04/2025 | 23/04/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 468 | 94810358_468
A56630 | TT_Task | Train Completion for Trainset #071 | 30/04/2025 | 12/05/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 396 | 94810358_396
A56660 | TT_Task | First Final-assembly Station for Trainset #071 DM2 | 24/04/2025 | 25/04/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 469 | 94810358_469
A56670 | TT_Task | First Final-assembly Station for Trainset #071 DM1 | 25/04/2025 | 28/04/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 470 | 94810358_470
A56680 | TT_Task | First Final-assembly Station for Trainset #071 T1 | 29/04/2025 | 30/04/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 471 | 94810358_471
A56650 | TT_Task | Commissioning for Trainset #071 | 12/05/2025 | 27/05/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 312 | 94810358_312
A81080 | TT_Task | Quality/Customer Acceptance for Trainset #071 | 27/05/2025 | 10/06/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 454 | 94810358_454
A24120 | TT_Task | Preliminary Takeover for Trainset #071 | 11/03/2027 | 07/04/2027 | nan | nan | 0 | TK_NotStart | 94810358 | 472 | 94810358_472
A24130 | TT_Task | Final Takeover for Trainset #071 | 08/04/2027 | 05/05/2027 | nan | nan | 4784 | TK_NotStart | 94810358 | 473 | 94810358_473
A70200 | TT_Task | Final Assembly for Trainset #072 | 07/11/2024 | 04/03/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 474 | 94810358_474
A78110 | TT_Task | Transport Carbody to Henningsdorf for Trainset #072 | 04/03/2025 | 29/04/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 467 | 94810358_467
A80090 | TT_Task | Transport to Sweden for Trainset #072 | 17/06/2025 | 22/06/2025 | nan | nan | 5120 | TK_NotStart | 94810358 | 427 | 94810358_427
A56740 | TT_Task | Tempering of CBY for Trainset #072 First Carbody | 29/04/2025 | 30/04/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 468 | 94810358_468
A56800 | TT_Task | Train Completion for Trainset #072 | 07/05/2025 | 16/05/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 396 | 94810358_396
A56830 | TT_Task | First Final-assembly Station for Trainset #072 DM2 | 30/04/2025 | 01/05/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 469 | 94810358_469
A56840 | TT_Task | First Final-assembly Station for Trainset #072 DM1 | 02/05/2025 | 05/05/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 470 | 94810358_470
A56850 | TT_Task | First Final-assembly Station for Trainset #072 T1 | 05/05/2025 | 06/05/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 471 | 94810358_471
A56820 | TT_Task | Commissioning for Trainset #072 | 19/05/2025 | 02/06/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 312 | 94810358_312
A81090 | TT_Task | Quality/Customer Acceptance for Trainset #072 | 03/06/2025 | 16/06/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 454 | 94810358_454
A24230 | TT_Task | Preliminary Takeover for Trainset #072 | 25/03/2027 | 21/04/2027 | nan | nan | 0 | TK_NotStart | 94810358 | 472 | 94810358_472
A24240 | TT_Task | Final Takeover for Trainset #072 | 22/04/2027 | 19/05/2027 | nan | nan | 4704 | TK_NotStart | 94810358 | 473 | 94810358_473
A70320 | TT_Task | Final Assembly for Trainset #073 | 14/11/2024 | 10/03/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 474 | 94810358_474
A78140 | TT_Task | Transport Carbody to Henningsdorf for Trainset #073 | 11/03/2025 | 05/05/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 467 | 94810358_467
A80100 | TT_Task | Transport to Sweden for Trainset #073 | 23/06/2025 | 29/06/2025 | nan | nan | 5180 | TK_NotStart | 94810358 | 427 | 94810358_427
A56910 | TT_Task | Tempering of CBY for Trainset #073 First Carbody | 06/05/2025 | 06/05/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 468 | 94810358_468
A56970 | TT_Task | Train Completion for Trainset #073 | 13/05/2025 | 23/05/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 396 | 94810358_396
A57000 | TT_Task | First Final-assembly Station for Trainset #073 DM2 | 07/05/2025 | 08/05/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 469 | 94810358_469
A57010 | TT_Task | First Final-assembly Station for Trainset #073 DM1 | 08/05/2025 | 09/05/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 470 | 94810358_470
A57020 | TT_Task | First Final-assembly Station for Trainset #073 T1 | 12/05/2025 | 13/05/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 471 | 94810358_471
A56990 | TT_Task | Commissioning for Trainset #073 | 23/05/2025 | 09/06/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 312 | 94810358_312
A81100 | TT_Task | Quality/Customer Acceptance for Trainset #073 | 09/06/2025 | 23/06/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 454 | 94810358_454
A24340 | TT_Task | Preliminary Takeover for Trainset #073 | 08/04/2027 | 05/05/2027 | nan | nan | 0 | TK_NotStart | 94810358 | 472 | 94810358_472
A24350 | TT_Task | Final Takeover for Trainset #073 | 06/05/2027 | 02/06/2027 | nan | nan | 4624 | TK_NotStart | 94810358 | 473 | 94810358_473
A70440 | TT_Task | Final Assembly for Trainset #074 | 20/11/2024 | 17/03/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 474 | 94810358_474
A78170 | TT_Task | Transport Carbody to Henningsdorf for Trainset #074 | 17/03/2025 | 12/05/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 467 | 94810358_467
A80110 | TT_Task | Transport to Sweden for Trainset #074 | 28/06/2025 | 03/07/2025 | nan | nan | 5256 | TK_NotStart | 94810358 | 427 | 94810358_427
A57080 | TT_Task | Tempering of CBY for Trainset #074 First Carbody | 12/05/2025 | 13/05/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 468 | 94810358_468
A57140 | TT_Task | Train Completion for Trainset #074 | 20/05/2025 | 29/05/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 396 | 94810358_396
A57170 | TT_Task | First Final-assembly Station for Trainset #074 DM2 | 13/05/2025 | 14/05/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 469 | 94810358_469
A57180 | TT_Task | First Final-assembly Station for Trainset #074 DM1 | 15/05/2025 | 16/05/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 470 | 94810358_470
A57190 | TT_Task | First Final-assembly Station for Trainset #074 T1 | 16/05/2025 | 19/05/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 471 | 94810358_471
A57160 | TT_Task | Commissioning for Trainset #074 | 30/05/2025 | 13/06/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 312 | 94810358_312
A81110 | TT_Task | Quality/Customer Acceptance for Trainset #074 | 16/06/2025 | 27/06/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 454 | 94810358_454
A24450 | TT_Task | Preliminary Takeover for Trainset #074 | 22/04/2027 | 19/05/2027 | nan | nan | 0 | TK_NotStart | 94810358 | 472 | 94810358_472
A24460 | TT_Task | Final Takeover for Trainset #074 | 20/05/2027 | 16/06/2027 | nan | nan | 4544 | TK_NotStart | 94810358 | 473 | 94810358_473
A70560 | TT_Task | Final Assembly for Trainset #075 | 27/11/2024 | 21/03/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 474 | 94810358_474
A78200 | TT_Task | Transport Carbody to Henningsdorf for Trainset #075 | 24/03/2025 | 18/05/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 467 | 94810358_467
A80120 | TT_Task | Transport to Sweden for Trainset #075 | 04/07/2025 | 10/07/2025 | nan | nan | 5316 | TK_NotStart | 94810358 | 427 | 94810358_427
A57250 | TT_Task | Tempering of CBY for Trainset #075 First Carbody | 19/05/2025 | 19/05/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 468 | 94810358_468
A57310 | TT_Task | Train Completion for Trainset #075 | 26/05/2025 | 05/06/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 396 | 94810358_396
A57340 | TT_Task | First Final-assembly Station for Trainset #075 DM2 | 20/05/2025 | 21/05/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 469 | 94810358_469
A57350 | TT_Task | First Final-assembly Station for Trainset #075 DM1 | 21/05/2025 | 22/05/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 470 | 94810358_470
A57360 | TT_Task | First Final-assembly Station for Trainset #075 T1 | 23/05/2025 | 26/05/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 471 | 94810358_471
A57330 | TT_Task | Commissioning for Trainset #075 | 05/06/2025 | 20/06/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 312 | 94810358_312
A81120 | TT_Task | Quality/Customer Acceptance for Trainset #075 | 20/06/2025 | 04/07/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 454 | 94810358_454
A24560 | TT_Task | Preliminary Takeover for Trainset #075 | 06/05/2027 | 02/06/2027 | nan | nan | 0 | TK_NotStart | 94810358 | 472 | 94810358_472
A24570 | TT_Task | Final Takeover for Trainset #075 | 03/06/2027 | 30/06/2027 | nan | nan | 4464 | TK_NotStart | 94810358 | 473 | 94810358_473
A70680 | TT_Task | Final Assembly for Trainset #076 | 03/12/2024 | 28/03/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 474 | 94810358_474
A78230 | TT_Task | Transport Carbody to Henningsdorf for Trainset #076 | 28/03/2025 | 23/05/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 467 | 94810358_467
A80130 | TT_Task | Transport to Sweden for Trainset #076 | 11/07/2025 | 16/07/2025 | nan | nan | 5376 | TK_NotStart | 94810358 | 427 | 94810358_427
A57420 | TT_Task | Tempering of CBY for Trainset #076 First Carbody | 23/05/2025 | 26/05/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 468 | 94810358_468
A57480 | TT_Task | Train Completion for Trainset #076 | 02/06/2025 | 11/06/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 396 | 94810358_396
A57510 | TT_Task | First Final-assembly Station for Trainset #076 DM2 | 26/05/2025 | 27/05/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 469 | 94810358_469
A57520 | TT_Task | First Final-assembly Station for Trainset #076 DM1 | 28/05/2025 | 29/05/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 470 | 94810358_470
A57530 | TT_Task | First Final-assembly Station for Trainset #076 T1 | 29/05/2025 | 30/05/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 471 | 94810358_471
A57500 | TT_Task | Commissioning for Trainset #076 | 12/06/2025 | 26/06/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 312 | 94810358_312
A81130 | TT_Task | Quality/Customer Acceptance for Trainset #076 | 27/06/2025 | 10/07/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 454 | 94810358_454
A24670 | TT_Task | Preliminary Takeover for Trainset #076 | 20/05/2027 | 16/06/2027 | nan | nan | 0 | TK_NotStart | 94810358 | 472 | 94810358_472
A24680 | TT_Task | Final Takeover for Trainset #076 | 17/06/2027 | 16/08/2027 | nan | nan | 4384 | TK_NotStart | 94810358 | 473 | 94810358_473
A70800 | TT_Task | Final Assembly for Trainset #077 | 10/12/2024 | 03/04/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 474 | 94810358_474
A78260 | TT_Task | Transport Carbody to Henningsdorf for Trainset #077 | 04/04/2025 | 29/05/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 467 | 94810358_467
A80140 | TT_Task | Transport to Sweden for Trainset #077 | 17/07/2025 | 23/07/2025 | nan | nan | 5436 | TK_NotStart | 94810358 | 427 | 94810358_427
A57590 | TT_Task | Tempering of CBY for Trainset #077 First Carbody | 30/05/2025 | 30/05/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 468 | 94810358_468
A57650 | TT_Task | Train Completion for Trainset #077 | 06/06/2025 | 18/06/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 396 | 94810358_396
A57680 | TT_Task | First Final-assembly Station for Trainset #077 DM2 | 02/06/2025 | 03/06/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 469 | 94810358_469
A57690 | TT_Task | First Final-assembly Station for Trainset #077 DM1 | 03/06/2025 | 04/06/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 470 | 94810358_470
A57700 | TT_Task | First Final-assembly Station for Trainset #077 T1 | 05/06/2025 | 06/06/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 471 | 94810358_471
A57670 | TT_Task | Commissioning for Trainset #077 | 18/06/2025 | 03/07/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 312 | 94810358_312
A81140 | TT_Task | Quality/Customer Acceptance for Trainset #077 | 03/07/2025 | 17/07/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 454 | 94810358_454
A24780 | TT_Task | Preliminary Takeover for Trainset #077 | 03/06/2027 | 30/06/2027 | nan | nan | 0 | TK_NotStart | 94810358 | 472 | 94810358_472
A24790 | TT_Task | Final Takeover for Trainset #077 | 03/08/2027 | 30/08/2027 | nan | nan | 4304 | TK_NotStart | 94810358 | 473 | 94810358_473
A70920 | TT_Task | Final Assembly for Trainset #078 | 16/12/2024 | 10/04/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 474 | 94810358_474
A78290 | TT_Task | Transport Carbody to Henningsdorf for Trainset #078 | 10/04/2025 | 05/06/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 467 | 94810358_467
A80150 | TT_Task | Transport to Sweden for Trainset #078 | 24/07/2025 | 29/07/2025 | nan | nan | 5496 | TK_NotStart | 94810358 | 427 | 94810358_427
A57760 | TT_Task | Tempering of CBY for Trainset #078 First Carbody | 05/06/2025 | 06/06/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 468 | 94810358_468
A57820 | TT_Task | Train Completion for Trainset #078 | 13/06/2025 | 24/06/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 396 | 94810358_396
A57850 | TT_Task | First Final-assembly Station for Trainset #078 DM2 | 06/06/2025 | 09/06/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 469 | 94810358_469
A57860 | TT_Task | First Final-assembly Station for Trainset #078 DM1 | 10/06/2025 | 11/06/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 470 | 94810358_470
A57870 | TT_Task | First Final-assembly Station for Trainset #078 T1 | 11/06/2025 | 12/06/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 471 | 94810358_471
A57840 | TT_Task | Commissioning for Trainset #078 | 25/06/2025 | 09/07/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 312 | 94810358_312
A81150 | TT_Task | Quality/Customer Acceptance for Trainset #078 | 10/07/2025 | 23/07/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 454 | 94810358_454
A24890 | TT_Task | Preliminary Takeover for Trainset #078 | 17/06/2027 | 16/08/2027 | nan | nan | 0 | TK_NotStart | 94810358 | 472 | 94810358_472
A24900 | TT_Task | Final Takeover for Trainset #078 | 17/08/2027 | 13/09/2027 | nan | nan | 4224 | TK_NotStart | 94810358 | 473 | 94810358_473
A71040 | TT_Task | Final Assembly for Trainset #079 | 23/12/2024 | 16/04/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 474 | 94810358_474
A78320 | TT_Task | Transport Carbody to Henningsdorf for Trainset #079 | 17/04/2025 | 11/06/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 467 | 94810358_467
A80160 | TT_Task | Transport to Sweden for Trainset #079 | 30/07/2025 | 05/08/2025 | nan | nan | 5820 | TK_NotStart | 94810358 | 427 | 94810358_427
A57930 | TT_Task | Tempering of CBY for Trainset #079 First Carbody | 12/06/2025 | 12/06/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 468 | 94810358_468
A57990 | TT_Task | Train Completion for Trainset #079 | 19/06/2025 | 01/07/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 396 | 94810358_396
A58020 | TT_Task | First Final-assembly Station for Trainset #079 DM2 | 13/06/2025 | 16/06/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 469 | 94810358_469
A58030 | TT_Task | First Final-assembly Station for Trainset #079 DM1 | 16/06/2025 | 17/06/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 470 | 94810358_470
A58040 | TT_Task | First Final-assembly Station for Trainset #079 T1 | 18/06/2025 | 19/06/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 471 | 94810358_471
A58010 | TT_Task | Commissioning for Trainset #079 | 01/07/2025 | 16/07/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 312 | 94810358_312
A81160 | TT_Task | Quality/Customer Acceptance for Trainset #079 | 16/07/2025 | 30/07/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 454 | 94810358_454
A25000 | TT_Task | Preliminary Takeover for Trainset #079 | 03/08/2027 | 30/08/2027 | nan | nan | 0 | TK_NotStart | 94810358 | 472 | 94810358_472
A25010 | TT_Task | Final Takeover for Trainset #079 | 31/08/2027 | 27/09/2027 | nan | nan | 4144 | TK_NotStart | 94810358 | 473 | 94810358_473
A71160 | TT_Task | Final Assembly for Trainset #080 | 27/12/2024 | 23/04/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 474 | 94810358_474
A78350 | TT_Task | Transport Carbody to Henningsdorf for Trainset #080 | 23/04/2025 | 18/06/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 467 | 94810358_467
A80170 | TT_Task | Transport to Sweden for Trainset #080 | 06/08/2025 | 11/08/2025 | nan | nan | 5880 | TK_NotStart | 94810358 | 427 | 94810358_427
A58100 | TT_Task | Tempering of CBY for Trainset #080 First Carbody | 18/06/2025 | 19/06/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 468 | 94810358_468
A58160 | TT_Task | Train Completion for Trainset #080 | 26/06/2025 | 07/07/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 396 | 94810358_396
A58190 | TT_Task | First Final-assembly Station for Trainset #080 DM2 | 19/06/2025 | 20/06/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 469 | 94810358_469
A58200 | TT_Task | First Final-assembly Station for Trainset #080 DM1 | 23/06/2025 | 24/06/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 470 | 94810358_470
A58210 | TT_Task | First Final-assembly Station for Trainset #080 T1 | 24/06/2025 | 25/06/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 471 | 94810358_471
A58180 | TT_Task | Commissioning for Trainset #080 | 08/07/2025 | 22/07/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 312 | 94810358_312
A81170 | TT_Task | Quality/Customer Acceptance for Trainset #080 | 23/07/2025 | 05/08/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 454 | 94810358_454
A25110 | TT_Task | Preliminary Takeover for Trainset #080 | 17/08/2027 | 13/09/2027 | nan | nan | 0 | TK_NotStart | 94810358 | 472 | 94810358_472
A25120 | TT_Task | Final Takeover for Trainset #080 | 14/09/2027 | 11/10/2027 | nan | nan | 4064 | TK_NotStart | 94810358 | 473 | 94810358_473
A71280 | TT_Task | Final Assembly for Trainset #081 | 03/01/2025 | 29/04/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 474 | 94810358_474
A78380 | TT_Task | Transport Carbody to Henningsdorf for Trainset #081 | 30/04/2025 | 24/06/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 467 | 94810358_467
A80180 | TT_Task | Transport to Sweden for Trainset #081 | 12/08/2025 | 18/08/2025 | nan | nan | 5940 | TK_NotStart | 94810358 | 427 | 94810358_427
A58270 | TT_Task | Tempering of CBY for Trainset #081 First Carbody | 25/06/2025 | 25/06/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 468 | 94810358_468
A58330 | TT_Task | Train Completion for Trainset #081 | 02/07/2025 | 14/07/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 396 | 94810358_396
A58360 | TT_Task | First Final-assembly Station for Trainset #081 DM2 | 26/06/2025 | 27/06/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 469 | 94810358_469
A58370 | TT_Task | First Final-assembly Station for Trainset #081 DM1 | 27/06/2025 | 30/06/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 470 | 94810358_470
A58380 | TT_Task | First Final-assembly Station for Trainset #081 T1 | 01/07/2025 | 02/07/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 471 | 94810358_471
A58350 | TT_Task | Commissioning for Trainset #081 | 14/07/2025 | 29/07/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 312 | 94810358_312
A81180 | TT_Task | Quality/Customer Acceptance for Trainset #081 | 29/07/2025 | 12/08/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 454 | 94810358_454
A25220 | TT_Task | Preliminary Takeover for Trainset #081 | 31/08/2027 | 27/09/2027 | nan | nan | 0 | TK_NotStart | 94810358 | 472 | 94810358_472
A25230 | TT_Task | Final Takeover for Trainset #081 | 28/09/2027 | 25/10/2027 | nan | nan | 3984 | TK_NotStart | 94810358 | 473 | 94810358_473
A71400 | TT_Task | Final Assembly for Trainset #082 | 09/01/2025 | 06/05/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 474 | 94810358_474
A78410 | TT_Task | Transport Carbody to Henningsdorf for Trainset #082 | 06/05/2025 | 01/07/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 467 | 94810358_467
A80190 | TT_Task | Transport to Sweden for Trainset #082 | 19/08/2025 | 24/08/2025 | nan | nan | 6000 | TK_NotStart | 94810358 | 427 | 94810358_427
A58440 | TT_Task | Tempering of CBY for Trainset #082 First Carbody | 01/07/2025 | 02/07/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 468 | 94810358_468
A58500 | TT_Task | Train Completion for Trainset #082 | 09/07/2025 | 18/07/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 396 | 94810358_396
A58530 | TT_Task | First Final-assembly Station for Trainset #082 DM2 | 02/07/2025 | 03/07/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 469 | 94810358_469
A58540 | TT_Task | First Final-assembly Station for Trainset #082 DM1 | 04/07/2025 | 07/07/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 470 | 94810358_470
A58550 | TT_Task | First Final-assembly Station for Trainset #082 T1 | 07/07/2025 | 08/07/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 471 | 94810358_471
A58520 | TT_Task | Commissioning for Trainset #082 | 21/07/2025 | 04/08/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 312 | 94810358_312
A81190 | TT_Task | Quality/Customer Acceptance for Trainset #082 | 05/08/2025 | 18/08/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 454 | 94810358_454
A25330 | TT_Task | Preliminary Takeover for Trainset #082 | 14/09/2027 | 11/10/2027 | nan | nan | 0 | TK_NotStart | 94810358 | 472 | 94810358_472
A25340 | TT_Task | Final Takeover for Trainset #082 | 12/10/2027 | 08/11/2027 | nan | nan | 3904 | TK_NotStart | 94810358 | 473 | 94810358_473
A71520 | TT_Task | Final Assembly for Trainset #083 | 16/01/2025 | 12/05/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 474 | 94810358_474
A78440 | TT_Task | Transport Carbody to Henningsdorf for Trainset #083 | 13/05/2025 | 07/07/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 467 | 94810358_467
A80200 | TT_Task | Transport to Sweden for Trainset #083 | 25/08/2025 | 31/08/2025 | nan | nan | 6060 | TK_NotStart | 94810358 | 427 | 94810358_427
A58610 | TT_Task | Tempering of CBY for Trainset #083 First Carbody | 08/07/2025 | 08/07/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 468 | 94810358_468
A58670 | TT_Task | Train Completion for Trainset #083 | 15/07/2025 | 25/07/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 396 | 94810358_396
A58700 | TT_Task | First Final-assembly Station for Trainset #083 DM2 | 09/07/2025 | 10/07/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 469 | 94810358_469
A58710 | TT_Task | First Final-assembly Station for Trainset #083 DM1 | 10/07/2025 | 11/07/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 470 | 94810358_470
A58720 | TT_Task | First Final-assembly Station for Trainset #083 T1 | 14/07/2025 | 15/07/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 471 | 94810358_471
A58690 | TT_Task | Commissioning for Trainset #083 | 25/07/2025 | 11/08/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 312 | 94810358_312
A81200 | TT_Task | Quality/Customer Acceptance for Trainset #083 | 11/08/2025 | 25/08/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 454 | 94810358_454
A25440 | TT_Task | Preliminary Takeover for Trainset #083 | 28/09/2027 | 25/10/2027 | nan | nan | 0 | TK_NotStart | 94810358 | 472 | 94810358_472
A25450 | TT_Task | Final Takeover for Trainset #083 | 26/10/2027 | 22/11/2027 | nan | nan | 3824 | TK_NotStart | 94810358 | 473 | 94810358_473
A71640 | TT_Task | Final Assembly for Trainset #084 | 22/01/2025 | 19/05/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 474 | 94810358_474
A78470 | TT_Task | Transport Carbody to Henningsdorf for Trainset #084 | 19/05/2025 | 14/07/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 467 | 94810358_467
A80210 | TT_Task | Transport to Sweden for Trainset #084 | 30/08/2025 | 04/09/2025 | nan | nan | 6136 | TK_NotStart | 94810358 | 427 | 94810358_427
A58780 | TT_Task | Tempering of CBY for Trainset #084 First Carbody | 14/07/2025 | 15/07/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 468 | 94810358_468
A58840 | TT_Task | Train Completion for Trainset #084 | 22/07/2025 | 31/07/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 396 | 94810358_396
A58870 | TT_Task | First Final-assembly Station for Trainset #084 DM2 | 15/07/2025 | 16/07/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 469 | 94810358_469
A58880 | TT_Task | First Final-assembly Station for Trainset #084 DM1 | 17/07/2025 | 18/07/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 470 | 94810358_470
A58890 | TT_Task | First Final-assembly Station for Trainset #084 T1 | 18/07/2025 | 21/07/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 471 | 94810358_471
A58860 | TT_Task | Commissioning for Trainset #084 | 01/08/2025 | 15/08/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 312 | 94810358_312
A81210 | TT_Task | Quality/Customer Acceptance for Trainset #084 | 18/08/2025 | 29/08/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 454 | 94810358_454
A25550 | TT_Task | Preliminary Takeover for Trainset #084 | 12/10/2027 | 08/11/2027 | nan | nan | 0 | TK_NotStart | 94810358 | 472 | 94810358_472
A25560 | TT_Task | Final Takeover for Trainset #084 | 09/11/2027 | 06/12/2027 | nan | nan | 3744 | TK_NotStart | 94810358 | 473 | 94810358_473
A71760 | TT_Task | Final Assembly for Trainset #085 | 29/01/2025 | 23/05/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 474 | 94810358_474
A78500 | TT_Task | Transport Carbody to Henningsdorf for Trainset #085 | 26/05/2025 | 20/07/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 467 | 94810358_467
A80220 | TT_Task | Transport to Sweden for Trainset #085 | 05/09/2025 | 11/09/2025 | nan | nan | 6196 | TK_NotStart | 94810358 | 427 | 94810358_427
A58950 | TT_Task | Tempering of CBY for Trainset #085 First Carbody | 21/07/2025 | 21/07/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 468 | 94810358_468
A59010 | TT_Task | Train Completion for Trainset #085 | 28/07/2025 | 07/08/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 396 | 94810358_396
A59040 | TT_Task | First Final-assembly Station for Trainset #085 DM2 | 22/07/2025 | 23/07/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 469 | 94810358_469
A59050 | TT_Task | First Final-assembly Station for Trainset #085 DM1 | 23/07/2025 | 24/07/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 470 | 94810358_470
A59060 | TT_Task | First Final-assembly Station for Trainset #085 T1 | 25/07/2025 | 28/07/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 471 | 94810358_471
A59030 | TT_Task | Commissioning for Trainset #085 | 07/08/2025 | 22/08/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 312 | 94810358_312
A81220 | TT_Task | Quality/Customer Acceptance for Trainset #085 | 22/08/2025 | 05/09/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 454 | 94810358_454
A25660 | TT_Task | Preliminary Takeover for Trainset #085 | 26/10/2027 | 22/11/2027 | nan | nan | 0 | TK_NotStart | 94810358 | 472 | 94810358_472
A25670 | TT_Task | Final Takeover for Trainset #085 | 23/11/2027 | 10/01/2028 | nan | nan | 3664 | TK_NotStart | 94810358 | 473 | 94810358_473
A71880 | TT_Task | Final Assembly for Trainset #086 | 04/02/2025 | 30/05/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 474 | 94810358_474
A78530 | TT_Task | Transport Carbody to Henningsdorf for Trainset #086 | 30/05/2025 | 25/07/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 467 | 94810358_467
A80230 | TT_Task | Transport to Sweden for Trainset #086 | 12/09/2025 | 17/09/2025 | nan | nan | 6256 | TK_NotStart | 94810358 | 427 | 94810358_427
A59120 | TT_Task | Tempering of CBY for Trainset #086 First Carbody | 25/07/2025 | 28/07/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 468 | 94810358_468
A59180 | TT_Task | Train Completion for Trainset #086 | 04/08/2025 | 13/08/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 396 | 94810358_396
A59210 | TT_Task | First Final-assembly Station for Trainset #086 DM2 | 28/07/2025 | 29/07/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 469 | 94810358_469
A59220 | TT_Task | First Final-assembly Station for Trainset #086 DM1 | 30/07/2025 | 31/07/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 470 | 94810358_470
A59230 | TT_Task | First Final-assembly Station for Trainset #086 T1 | 31/07/2025 | 01/08/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 471 | 94810358_471
A59200 | TT_Task | Commissioning for Trainset #086 | 14/08/2025 | 28/08/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 312 | 94810358_312
A81230 | TT_Task | Quality/Customer Acceptance for Trainset #086 | 29/08/2025 | 11/09/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 454 | 94810358_454
A25770 | TT_Task | Preliminary Takeover for Trainset #086 | 09/11/2027 | 06/12/2027 | nan | nan | 0 | TK_NotStart | 94810358 | 472 | 94810358_472
A25780 | TT_Task | Final Takeover for Trainset #086 | 07/12/2027 | 24/01/2028 | nan | nan | 3584 | TK_NotStart | 94810358 | 473 | 94810358_473
A72000 | TT_Task | Final Assembly for Trainset #087 | 11/02/2025 | 05/06/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 474 | 94810358_474
A78560 | TT_Task | Transport Carbody to Henningsdorf for Trainset #087 | 06/06/2025 | 31/07/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 467 | 94810358_467
A80240 | TT_Task | Transport to Sweden for Trainset #087 | 18/09/2025 | 24/09/2025 | nan | nan | 6316 | TK_NotStart | 94810358 | 427 | 94810358_427
A59290 | TT_Task | Tempering of CBY for Trainset #087 First Carbody | 01/08/2025 | 01/08/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 468 | 94810358_468
A59350 | TT_Task | Train Completion for Trainset #087 | 08/08/2025 | 20/08/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 396 | 94810358_396
A59380 | TT_Task | First Final-assembly Station for Trainset #087 DM2 | 04/08/2025 | 05/08/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 469 | 94810358_469
A59390 | TT_Task | First Final-assembly Station for Trainset #087 DM1 | 05/08/2025 | 06/08/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 470 | 94810358_470
A59400 | TT_Task | First Final-assembly Station for Trainset #087 T1 | 07/08/2025 | 08/08/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 471 | 94810358_471
A59370 | TT_Task | Commissioning for Trainset #087 | 20/08/2025 | 04/09/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 312 | 94810358_312
A81240 | TT_Task | Quality/Customer Acceptance for Trainset #087 | 04/09/2025 | 18/09/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 454 | 94810358_454
A25880 | TT_Task | Preliminary Takeover for Trainset #087 | 23/11/2027 | 10/01/2028 | nan | nan | 0 | TK_NotStart | 94810358 | 472 | 94810358_472
A25890 | TT_Task | Final Takeover for Trainset #087 | 11/01/2028 | 07/02/2028 | nan | nan | 3504 | TK_NotStart | 94810358 | 473 | 94810358_473
A72120 | TT_Task | Final Assembly for Trainset #088 | 17/02/2025 | 12/06/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 474 | 94810358_474
A78590 | TT_Task | Transport Carbody to Henningsdorf for Trainset #088 | 12/06/2025 | 07/08/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 467 | 94810358_467
A80250 | TT_Task | Transport to Sweden for Trainset #088 | 25/09/2025 | 30/09/2025 | nan | nan | 6376 | TK_NotStart | 94810358 | 427 | 94810358_427
A59460 | TT_Task | Tempering of CBY for Trainset #088 First Carbody | 07/08/2025 | 08/08/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 468 | 94810358_468
A59520 | TT_Task | Train Completion for Trainset #088 | 15/08/2025 | 26/08/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 396 | 94810358_396
A59550 | TT_Task | First Final-assembly Station for Trainset #088 DM2 | 08/08/2025 | 11/08/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 469 | 94810358_469
A59560 | TT_Task | First Final-assembly Station for Trainset #088 DM1 | 12/08/2025 | 13/08/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 470 | 94810358_470
A59570 | TT_Task | First Final-assembly Station for Trainset #088 T1 | 13/08/2025 | 14/08/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 471 | 94810358_471
A59540 | TT_Task | Commissioning for Trainset #088 | 27/08/2025 | 10/09/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 312 | 94810358_312
A81250 | TT_Task | Quality/Customer Acceptance for Trainset #088 | 11/09/2025 | 24/09/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 454 | 94810358_454
A25990 | TT_Task | Preliminary Takeover for Trainset #088 | 07/12/2027 | 24/01/2028 | nan | nan | 0 | TK_NotStart | 94810358 | 472 | 94810358_472
A26000 | TT_Task | Final Takeover for Trainset #088 | 25/01/2028 | 21/02/2028 | nan | nan | 3424 | TK_NotStart | 94810358 | 473 | 94810358_473
A72240 | TT_Task | Final Assembly for Trainset #089 | 24/02/2025 | 18/06/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 474 | 94810358_474
A78620 | TT_Task | Transport Carbody to Henningsdorf for Trainset #089 | 19/06/2025 | 13/08/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 467 | 94810358_467
A80260 | TT_Task | Transport to Sweden for Trainset #089 | 01/10/2025 | 07/10/2025 | nan | nan | 6604 | TK_NotStart | 94810358 | 427 | 94810358_427
A59630 | TT_Task | Tempering of CBY for Trainset #089 First Carbody | 14/08/2025 | 14/08/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 468 | 94810358_468
A59690 | TT_Task | Train Completion for Trainset #089 | 21/08/2025 | 02/09/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 396 | 94810358_396
A59720 | TT_Task | First Final-assembly Station for Trainset #089 DM2 | 15/08/2025 | 18/08/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 469 | 94810358_469
A59730 | TT_Task | First Final-assembly Station for Trainset #089 DM1 | 18/08/2025 | 19/08/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 470 | 94810358_470
A59740 | TT_Task | First Final-assembly Station for Trainset #089 T1 | 20/08/2025 | 21/08/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 471 | 94810358_471
A59710 | TT_Task | Commissioning for Trainset #089 | 02/09/2025 | 17/09/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 312 | 94810358_312
A81260 | TT_Task | Quality/Customer Acceptance for Trainset #089 | 17/09/2025 | 01/10/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 454 | 94810358_454
A26100 | TT_Task | Preliminary Takeover for Trainset #089 | 11/01/2028 | 07/02/2028 | nan | nan | 0 | TK_NotStart | 94810358 | 472 | 94810358_472
A26110 | TT_Task | Final Takeover for Trainset #089 | 08/02/2028 | 06/03/2028 | nan | nan | 3344 | TK_NotStart | 94810358 | 473 | 94810358_473
A72360 | TT_Task | Final Assembly for Trainset #090 | 28/02/2025 | 25/06/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 474 | 94810358_474
A78650 | TT_Task | Transport Carbody to Henningsdorf for Trainset #090 | 25/06/2025 | 20/08/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 467 | 94810358_467
A80270 | TT_Task | Transport to Sweden for Trainset #090 | 08/10/2025 | 13/10/2025 | nan | nan | 6664 | TK_NotStart | 94810358 | 427 | 94810358_427
A59800 | TT_Task | Tempering of CBY for Trainset #090 First Carbody | 20/08/2025 | 21/08/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 468 | 94810358_468
A59860 | TT_Task | Train Completion for Trainset #090 | 28/08/2025 | 08/09/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 396 | 94810358_396
A59890 | TT_Task | First Final-assembly Station for Trainset #090 DM2 | 21/08/2025 | 22/08/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 469 | 94810358_469
A59900 | TT_Task | First Final-assembly Station for Trainset #090 DM1 | 25/08/2025 | 26/08/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 470 | 94810358_470
A59910 | TT_Task | First Final-assembly Station for Trainset #090 T1 | 26/08/2025 | 27/08/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 471 | 94810358_471
A59880 | TT_Task | Commissioning for Trainset #090 | 09/09/2025 | 23/09/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 312 | 94810358_312
A81270 | TT_Task | Quality/Customer Acceptance for Trainset #090 | 24/09/2025 | 07/10/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 454 | 94810358_454
A26210 | TT_Task | Preliminary Takeover for Trainset #090 | 25/01/2028 | 21/02/2028 | nan | nan | 0 | TK_NotStart | 94810358 | 472 | 94810358_472
A26220 | TT_Task | Final Takeover for Trainset #090 | 22/02/2028 | 20/03/2028 | nan | nan | 3264 | TK_NotStart | 94810358 | 473 | 94810358_473
A72480 | TT_Task | Final Assembly for Trainset #091 | 07/03/2025 | 01/07/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 474 | 94810358_474
A78680 | TT_Task | Transport Carbody to Henningsdorf for Trainset #091 | 02/07/2025 | 26/08/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 467 | 94810358_467
A80280 | TT_Task | Transport to Sweden for Trainset #091 | 14/10/2025 | 20/10/2025 | nan | nan | 6724 | TK_NotStart | 94810358 | 427 | 94810358_427
A59970 | TT_Task | Tempering of CBY for Trainset #091 First Carbody | 27/08/2025 | 27/08/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 468 | 94810358_468
A60030 | TT_Task | Train Completion for Trainset #091 | 03/09/2025 | 15/09/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 396 | 94810358_396
A60060 | TT_Task | First Final-assembly Station for Trainset #091 DM2 | 28/08/2025 | 29/08/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 469 | 94810358_469
A60070 | TT_Task | First Final-assembly Station for Trainset #091 DM1 | 29/08/2025 | 01/09/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 470 | 94810358_470
A60080 | TT_Task | First Final-assembly Station for Trainset #091 T1 | 02/09/2025 | 03/09/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 471 | 94810358_471
A60050 | TT_Task | Commissioning for Trainset #091 | 15/09/2025 | 30/09/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 312 | 94810358_312
A81280 | TT_Task | Quality/Customer Acceptance for Trainset #091 | 30/09/2025 | 14/10/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 454 | 94810358_454
A26320 | TT_Task | Preliminary Takeover for Trainset #091 | 08/02/2028 | 06/03/2028 | nan | nan | 0 | TK_NotStart | 94810358 | 472 | 94810358_472
A26330 | TT_Task | Final Takeover for Trainset #091 | 07/03/2028 | 03/04/2028 | nan | nan | 3184 | TK_NotStart | 94810358 | 473 | 94810358_473
A72600 | TT_Task | Final Assembly for Trainset #092 | 13/03/2025 | 08/07/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 474 | 94810358_474
A78710 | TT_Task | Transport Carbody to Henningsdorf for Trainset #092 | 08/07/2025 | 02/09/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 467 | 94810358_467
A80290 | TT_Task | Transport to Sweden for Trainset #092 | 21/10/2025 | 26/10/2025 | nan | nan | 6784 | TK_NotStart | 94810358 | 427 | 94810358_427
A60140 | TT_Task | Tempering of CBY for Trainset #092 First Carbody | 02/09/2025 | 03/09/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 468 | 94810358_468
A60200 | TT_Task | Train Completion for Trainset #092 | 10/09/2025 | 19/09/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 396 | 94810358_396
A60230 | TT_Task | First Final-assembly Station for Trainset #092 DM2 | 03/09/2025 | 04/09/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 469 | 94810358_469
A60240 | TT_Task | First Final-assembly Station for Trainset #092 DM1 | 05/09/2025 | 08/09/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 470 | 94810358_470
A60250 | TT_Task | First Final-assembly Station for Trainset #092 T1 | 08/09/2025 | 09/09/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 471 | 94810358_471
A60220 | TT_Task | Commissioning for Trainset #092 | 22/09/2025 | 06/10/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 312 | 94810358_312
A81290 | TT_Task | Quality/Customer Acceptance for Trainset #092 | 07/10/2025 | 20/10/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 454 | 94810358_454
A26430 | TT_Task | Preliminary Takeover for Trainset #092 | 22/02/2028 | 20/03/2028 | nan | nan | 0 | TK_NotStart | 94810358 | 472 | 94810358_472
A26440 | TT_Task | Final Takeover for Trainset #092 | 21/03/2028 | 17/04/2028 | nan | nan | 3104 | TK_NotStart | 94810358 | 473 | 94810358_473
A72720 | TT_Task | Final Assembly for Trainset #093 | 20/03/2025 | 14/07/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 474 | 94810358_474
A78740 | TT_Task | Transport Carbody to Henningsdorf for Trainset #093 | 15/07/2025 | 08/09/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 467 | 94810358_467
A80300 | TT_Task | Transport to Sweden for Trainset #093 | 27/10/2025 | 02/11/2025 | nan | nan | 6844 | TK_NotStart | 94810358 | 427 | 94810358_427
A60310 | TT_Task | Tempering of CBY for Trainset #093 First Carbody | 09/09/2025 | 09/09/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 468 | 94810358_468
A60370 | TT_Task | Train Completion for Trainset #093 | 16/09/2025 | 26/09/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 396 | 94810358_396
A60400 | TT_Task | First Final-assembly Station for Trainset #093 DM2 | 10/09/2025 | 11/09/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 469 | 94810358_469
A60410 | TT_Task | First Final-assembly Station for Trainset #093 DM1 | 11/09/2025 | 12/09/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 470 | 94810358_470
A60420 | TT_Task | First Final-assembly Station for Trainset #093 T1 | 15/09/2025 | 16/09/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 471 | 94810358_471
A60390 | TT_Task | Commissioning for Trainset #093 | 26/09/2025 | 13/10/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 312 | 94810358_312
A81300 | TT_Task | Quality/Customer Acceptance for Trainset #093 | 13/10/2025 | 27/10/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 454 | 94810358_454
A26540 | TT_Task | Preliminary Takeover for Trainset #093 | 07/03/2028 | 03/04/2028 | nan | nan | 0 | TK_NotStart | 94810358 | 472 | 94810358_472
A26550 | TT_Task | Final Takeover for Trainset #093 | 04/04/2028 | 01/05/2028 | nan | nan | 3024 | TK_NotStart | 94810358 | 473 | 94810358_473
A72840 | TT_Task | Final Assembly for Trainset #094 | 26/03/2025 | 21/07/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 474 | 94810358_474
A78770 | TT_Task | Transport Carbody to Henningsdorf for Trainset #094 | 21/07/2025 | 15/09/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 467 | 94810358_467
A80310 | TT_Task | Transport to Sweden for Trainset #094 | 01/11/2025 | 06/11/2025 | nan | nan | 6920 | TK_NotStart | 94810358 | 427 | 94810358_427
A60480 | TT_Task | Tempering of CBY for Trainset #094 First Carbody | 15/09/2025 | 16/09/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 468 | 94810358_468
A60540 | TT_Task | Train Completion for Trainset #094 | 23/09/2025 | 02/10/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 396 | 94810358_396
A60570 | TT_Task | First Final-assembly Station for Trainset #094 DM2 | 16/09/2025 | 17/09/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 469 | 94810358_469
A60580 | TT_Task | First Final-assembly Station for Trainset #094 DM1 | 18/09/2025 | 19/09/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 470 | 94810358_470
A60590 | TT_Task | First Final-assembly Station for Trainset #094 T1 | 19/09/2025 | 22/09/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 471 | 94810358_471
A60560 | TT_Task | Commissioning for Trainset #094 | 03/10/2025 | 17/10/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 312 | 94810358_312
A81310 | TT_Task | Quality/Customer Acceptance for Trainset #094 | 20/10/2025 | 31/10/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 454 | 94810358_454
A26650 | TT_Task | Preliminary Takeover for Trainset #094 | 21/03/2028 | 17/04/2028 | nan | nan | 0 | TK_NotStart | 94810358 | 472 | 94810358_472
A26660 | TT_Task | Final Takeover for Trainset #094 | 18/04/2028 | 15/05/2028 | nan | nan | 2944 | TK_NotStart | 94810358 | 473 | 94810358_473
A72960 | TT_Task | Final Assembly for Trainset #095 | 02/04/2025 | 25/07/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 474 | 94810358_474
A78800 | TT_Task | Transport Carbody to Henningsdorf for Trainset #095 | 28/07/2025 | 21/09/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 467 | 94810358_467
A80320 | TT_Task | Transport to Sweden for Trainset #095 | 07/11/2025 | 13/11/2025 | nan | nan | 6980 | TK_NotStart | 94810358 | 427 | 94810358_427
A60650 | TT_Task | Tempering of CBY for Trainset #095 First Carbody | 22/09/2025 | 22/09/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 468 | 94810358_468
A60710 | TT_Task | Train Completion for Trainset #095 | 29/09/2025 | 09/10/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 396 | 94810358_396
A60740 | TT_Task | First Final-assembly Station for Trainset #095 DM2 | 23/09/2025 | 24/09/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 469 | 94810358_469
A60750 | TT_Task | First Final-assembly Station for Trainset #095 DM1 | 24/09/2025 | 25/09/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 470 | 94810358_470
A60760 | TT_Task | First Final-assembly Station for Trainset #095 T1 | 26/09/2025 | 29/09/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 471 | 94810358_471
A60730 | TT_Task | Commissioning for Trainset #095 | 09/10/2025 | 24/10/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 312 | 94810358_312
A81320 | TT_Task | Quality/Customer Acceptance for Trainset #095 | 24/10/2025 | 07/11/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 454 | 94810358_454
A26760 | TT_Task | Preliminary Takeover for Trainset #095 | 04/04/2028 | 01/05/2028 | nan | nan | 0 | TK_NotStart | 94810358 | 472 | 94810358_472
A26770 | TT_Task | Final Takeover for Trainset #095 | 02/05/2028 | 29/05/2028 | nan | nan | 2864 | TK_NotStart | 94810358 | 473 | 94810358_473
A73080 | TT_Task | Final Assembly for Trainset #096 | 08/04/2025 | 01/08/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 474 | 94810358_474
A78830 | TT_Task | Transport Carbody to Henningsdorf for Trainset #096 | 01/08/2025 | 26/09/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 467 | 94810358_467
A80330 | TT_Task | Transport to Sweden for Trainset #096 | 14/11/2025 | 19/11/2025 | nan | nan | 7040 | TK_NotStart | 94810358 | 427 | 94810358_427
A60820 | TT_Task | Tempering of CBY for Trainset #096 First Carbody | 26/09/2025 | 29/09/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 468 | 94810358_468
A60880 | TT_Task | Train Completion for Trainset #096 | 06/10/2025 | 15/10/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 396 | 94810358_396
A60910 | TT_Task | First Final-assembly Station for Trainset #096 DM2 | 29/09/2025 | 30/09/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 469 | 94810358_469
A60920 | TT_Task | First Final-assembly Station for Trainset #096 DM1 | 01/10/2025 | 02/10/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 470 | 94810358_470
A60930 | TT_Task | First Final-assembly Station for Trainset #096 T1 | 02/10/2025 | 03/10/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 471 | 94810358_471
A60900 | TT_Task | Commissioning for Trainset #096 | 16/10/2025 | 30/10/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 312 | 94810358_312
A81330 | TT_Task | Quality/Customer Acceptance for Trainset #096 | 31/10/2025 | 13/11/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 454 | 94810358_454
A26870 | TT_Task | Preliminary Takeover for Trainset #096 | 18/04/2028 | 15/05/2028 | nan | nan | 0 | TK_NotStart | 94810358 | 472 | 94810358_472
A26880 | TT_Task | Final Takeover for Trainset #096 | 16/05/2028 | 12/06/2028 | nan | nan | 2784 | TK_NotStart | 94810358 | 473 | 94810358_473
A73200 | TT_Task | Final Assembly for Trainset #097 | 15/04/2025 | 07/08/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 474 | 94810358_474
A78860 | TT_Task | Transport Carbody to Henningsdorf for Trainset #097 | 08/08/2025 | 02/10/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 467 | 94810358_467
A80340 | TT_Task | Transport to Sweden for Trainset #097 | 20/11/2025 | 26/11/2025 | nan | nan | 7100 | TK_NotStart | 94810358 | 427 | 94810358_427
A60990 | TT_Task | Tempering of CBY for Trainset #097 First Carbody | 03/10/2025 | 03/10/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 468 | 94810358_468
A61050 | TT_Task | Train Completion for Trainset #097 | 10/10/2025 | 22/10/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 396 | 94810358_396
A61080 | TT_Task | First Final-assembly Station for Trainset #097 DM2 | 06/10/2025 | 07/10/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 469 | 94810358_469
A61090 | TT_Task | First Final-assembly Station for Trainset #097 DM1 | 07/10/2025 | 08/10/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 470 | 94810358_470
A61100 | TT_Task | First Final-assembly Station for Trainset #097 T1 | 09/10/2025 | 10/10/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 471 | 94810358_471
A61070 | TT_Task | Commissioning for Trainset #097 | 22/10/2025 | 06/11/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 312 | 94810358_312
A81340 | TT_Task | Quality/Customer Acceptance for Trainset #097 | 06/11/2025 | 20/11/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 454 | 94810358_454
A26980 | TT_Task | Preliminary Takeover for Trainset #097 | 02/05/2028 | 29/05/2028 | nan | nan | 0 | TK_NotStart | 94810358 | 472 | 94810358_472
A26990 | TT_Task | Final Takeover for Trainset #097 | 30/05/2028 | 26/06/2028 | nan | nan | 2704 | TK_NotStart | 94810358 | 473 | 94810358_473
A73320 | TT_Task | Final Assembly for Trainset #098 | 21/04/2025 | 14/08/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 474 | 94810358_474
A78890 | TT_Task | Transport Carbody to Henningsdorf for Trainset #098 | 14/08/2025 | 09/10/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 467 | 94810358_467
A80350 | TT_Task | Transport to Sweden for Trainset #098 | 27/11/2025 | 02/12/2025 | nan | nan | 7160 | TK_NotStart | 94810358 | 427 | 94810358_427
A61160 | TT_Task | Tempering of CBY for Trainset #098 First Carbody | 09/10/2025 | 10/10/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 468 | 94810358_468
A61220 | TT_Task | Train Completion for Trainset #098 | 17/10/2025 | 28/10/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 396 | 94810358_396
A61250 | TT_Task | First Final-assembly Station for Trainset #098 DM2 | 10/10/2025 | 13/10/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 469 | 94810358_469
A61260 | TT_Task | First Final-assembly Station for Trainset #098 DM1 | 14/10/2025 | 15/10/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 470 | 94810358_470
A61270 | TT_Task | First Final-assembly Station for Trainset #098 T1 | 15/10/2025 | 16/10/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 471 | 94810358_471
A61240 | TT_Task | Commissioning for Trainset #098 | 29/10/2025 | 12/11/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 312 | 94810358_312
A81350 | TT_Task | Quality/Customer Acceptance for Trainset #098 | 13/11/2025 | 26/11/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 454 | 94810358_454
A27090 | TT_Task | Preliminary Takeover for Trainset #098 | 16/05/2028 | 12/06/2028 | nan | nan | 0 | TK_NotStart | 94810358 | 472 | 94810358_472
A27100 | TT_Task | Final Takeover for Trainset #098 | 13/06/2028 | 10/08/2028 | nan | nan | 2624 | TK_NotStart | 94810358 | 473 | 94810358_473
A73440 | TT_Task | Final Assembly for Trainset #099 | 28/04/2025 | 20/08/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 474 | 94810358_474
A78920 | TT_Task | Transport Carbody to Henningsdorf for Trainset #099 | 21/08/2025 | 15/10/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 467 | 94810358_467
A80360 | TT_Task | Transport to Sweden for Trainset #099 | 03/12/2025 | 09/12/2025 | nan | nan | 7220 | TK_NotStart | 94810358 | 427 | 94810358_427
A61330 | TT_Task | Tempering of CBY for Trainset #099 First Carbody | 16/10/2025 | 16/10/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 468 | 94810358_468
A61390 | TT_Task | Train Completion for Trainset #099 | 23/10/2025 | 04/11/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 396 | 94810358_396
A61420 | TT_Task | First Final-assembly Station for Trainset #099 DM2 | 17/10/2025 | 20/10/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 469 | 94810358_469
A61430 | TT_Task | First Final-assembly Station for Trainset #099 DM1 | 20/10/2025 | 21/10/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 470 | 94810358_470
A61440 | TT_Task | First Final-assembly Station for Trainset #099 T1 | 22/10/2025 | 23/10/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 471 | 94810358_471
A61410 | TT_Task | Commissioning for Trainset #099 | 04/11/2025 | 19/11/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 312 | 94810358_312
A81360 | TT_Task | Quality/Customer Acceptance for Trainset #099 | 19/11/2025 | 03/12/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 454 | 94810358_454
A27200 | TT_Task | Preliminary Takeover for Trainset #099 | 30/05/2028 | 26/06/2028 | nan | nan | 0 | TK_NotStart | 94810358 | 472 | 94810358_472
A27210 | TT_Task | Final Takeover for Trainset #099 | 27/06/2028 | 24/08/2028 | nan | nan | 2544 | TK_NotStart | 94810358 | 473 | 94810358_473
A73560 | TT_Task | Final Assembly for Trainset #100 | 02/05/2025 | 27/08/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 474 | 94810358_474
A78950 | TT_Task | Transport Carbody to Henningsdorf for Trainset #100 | 27/08/2025 | 22/10/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 467 | 94810358_467
A80370 | TT_Task | Transport to Sweden for Trainset #100 | 10/12/2025 | 15/12/2025 | nan | nan | 7280 | TK_NotStart | 94810358 | 427 | 94810358_427
A61500 | TT_Task | Tempering of CBY for Trainset #100 First Carbody | 22/10/2025 | 23/10/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 468 | 94810358_468
A61560 | TT_Task | Train Completion for Trainset #100 | 30/10/2025 | 10/11/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 396 | 94810358_396
A61590 | TT_Task | First Final-assembly Station for Trainset #100 DM2 | 23/10/2025 | 24/10/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 470 | 94810358_470
A61600 | TT_Task | First Final-assembly Station for Trainset #100 DM1 | 27/10/2025 | 28/10/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 470 | 94810358_470
A61610 | TT_Task | First Final-assembly Station for Trainset #100 T1 | 28/10/2025 | 29/10/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 471 | 94810358_471
A61580 | TT_Task | Commissioning for Trainset #100 | 11/11/2025 | 25/11/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 312 | 94810358_312
A81370 | TT_Task | Quality/Customer Acceptance for Trainset #100 | 26/11/2025 | 09/12/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 454 | 94810358_454
A27310 | TT_Task | Preliminary Takeover for Trainset #100 | 13/06/2028 | 10/08/2028 | nan | nan | 0 | TK_NotStart | 94810358 | 475 | 94810358_475
A27320 | TT_Task | Final Takeover for Trainset #100 | 11/08/2028 | 07/09/2028 | nan | nan | 2464 | TK_NotStart | 94810358 | 475 | 94810358_475
A187500 | TT_Task | Update of CTC Diagram by AT (CR#203846 Additional Power Cable Line - VT Approval Date) | 23/07/2021 | 23/07/2021 | 22/07/2021 | 27/10/2021 | 0 | TK_Complete | 94810358 | 476 | 94810358_476
A187505 | TT_Task | Update of CTC Diagram by AT (Approx. 9 wks for Correction of Rev.J) | 26/11/2021 | 26/11/2021 | 03/11/2021 | nan | 0 | TK_Active | 94810358 | 477 | 94810358_477
A187510 | TT_Task | Creation of Electrical Installation Drawing | 26/11/2021 | 09/12/2021 | 28/10/2021 | 04/11/2021 | 0 | TK_Complete | 94810358 | 478 | 94810358_478
A187520 | TT_Task | Creation of Mechanical Installation Drawing and Related BoM | 17/12/2021 | 11/01/2022 | 28/10/2021 | 04/11/2021 | 0 | TK_Complete | 94810358 | 479 | 94810358_479
A187525 | TT_Task | Production Preparation (Translation from EBoM to MBoM + SOI) | 26/11/2021 | 09/12/2021 | 08/11/2021 | 17/12/2021 | 0 | TK_Complete | 94810358 | 480 | 94810358_480
A187525a | TT_Task | CR for Missing Interfaces (BST Scope) | 20/12/2021 | 12/01/2022 | 17/12/2021 | nan | 0 | TK_Active | 94810358 | 481 | 94810358_481
A187540 | TT_Task | Delivery of Parts from VT (VT's scope) for Trainset #001 to 005 | 28/05/2021 | 06/06/2021 | 04/05/2021 | 18/05/2021 | 0 | TK_Complete | 94810358 | 482 | 94810358_482
A187543 | TT_Task | Delivery of CDRL Documents from VT (VT's scope) | 21/05/2021 | 03/06/2021 | 22/03/2021 | 26/08/2021 | 0 | TK_Complete | 94810358 | 483 | 94810358_483
A187545 | TT_Task | Re-confirmation of Performance Areas (EMC, eco-design, fire safety etc.) by VT | 27/08/2021 | 09/09/2021 | 27/08/2021 | nan | 0 | TK_Active | 94810358 | 484 | 94810358_484
A187550 | TT_Task | Installation of Ticketing System on Trainset #001 during Retrofit Slot 4b | 02/05/2022 | 18/05/2022 | nan | nan | 0 | TK_NotStart | 94810358 | 485 | 94810358_485
A187600 | TT_Task | Testing of Ticketing System on Trainset #001 during Retrofit Slot 4b | 09/05/2022 | 13/05/2022 | nan | nan | 15520 | TK_NotStart | 94810358 | 486 | 94810358_486
A189580 | TT_Task | Installation of Ticketing System on Trainset #001 during Retrofit Slot 4a (NOT USED) | 17/01/2022 | 28/01/2022 | nan | nan | 0 | TK_NotStart | 94810358 | 485 | 94810358_485
A189590 | TT_Task | Testing of Ticketing System on Trainset #001 during Retrofit Slot 4a (NOT USED) | 24/01/2022 | 28/01/2022 | nan | nan | 16120 | TK_NotStart | 94810358 | 486 | 94810358_486
A187560 | TT_Task | Installation of Ticketing System on Trainset #002 during Retrofit Slot 4 | 21/02/2022 | 01/03/2022 | nan | nan | 0 | TK_NotStart | 94810358 | 485 | 94810358_485
A187610 | TT_Task | Testing of Ticketing System on Trainset #002 during Retrofit Slot 4 | 28/02/2022 | 04/03/2022 | nan | nan | 15920 | TK_NotStart | 94810358 | 486 | 94810358_486
A187570 | TT_Task | Installation of Ticketing System on Trainset #003 during Retrofit Slot 4b | 19/04/2022 | 03/05/2022 | nan | nan | 0 | TK_NotStart | 94810358 | 485 | 94810358_485
A187620 | TT_Task | Testing of Ticketing System on Trainset #003 during Retrofit Slot 4b | 26/04/2022 | 02/05/2022 | nan | nan | 15592 | TK_NotStart | 94810358 | 486 | 94810358_486
A189600 | TT_Task | Installation of Ticketing System on Trainset #003 during Retrofit Slot 4a (Option - Material Availibility TBC) | 31/01/2022 | 11/02/2022 | nan | nan | 0 | TK_NotStart | 94810358 | 487 | 94810358_487
A189610 | TT_Task | Testing of Ticketing System on Trainset #003 during Retrofit Slot 4a (Option - Material Availibility TBC) | 07/02/2022 | 11/02/2022 | nan | nan | 16040 | TK_NotStart | 94810358 | 487 | 94810358_487
A187580 | TT_Task | Installation of Ticketing System on Trainset #004 during Retrofit Slot 4a (Option - Material Availibility TBC) | 07/02/2022 | 18/02/2022 | nan | nan | 0 | TK_NotStart | 94810358 | 487 | 94810358_487
A187630 | TT_Task | Testing of Ticketing System on Trainset #004 during Retrofit Slot 4a (Option - Material Availibility TBC) | 14/02/2022 | 18/02/2022 | nan | nan | 16000 | TK_NotStart | 94810358 | 487 | 94810358_487
A207450 | TT_Task | Installation of Ticketing System on Trainset #004 during Retrofit Slot 4b (During ATLAS Retrofit TBC) | 14/12/2022 | 10/01/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 488 | 94810358_488
A207460 | TT_Task | Testing of Ticketing System on Trainset #004 during Retrofit Slot 4b (During ATLAS Retrofit TBC) | 04/01/2023 | 10/01/2023 | nan | nan | 14224 | TK_NotStart | 94810358 | 488 | 94810358_488
A187590 | TT_Task | Installation of Ticketing System on Trainset #005 during Retrofit Slot 4b | 19/04/2022 | 02/05/2022 | nan | nan | 0 | TK_NotStart | 94810358 | 485 | 94810358_485
A187640 | TT_Task | Testing of Ticketing System on Trainset #005 during Retrofit Slot 4b | 26/04/2022 | 02/05/2022 | nan | nan | 15592 | TK_NotStart | 94810358 | 486 | 94810358_486
A188210 | TT_Task | Installation of Ticketing System on Trainset #005 during Retrofit Slot 3 or 4a (NOT USED) | 17/01/2022 | 28/01/2022 | nan | nan | 0 | TK_NotStart | 94810358 | 485 | 94810358_485
A188220 | TT_Task | Testing of Ticketing System on Trainset #005 during Retrofit Slot 3 or 4a (NOT USED) | 24/01/2022 | 28/01/2022 | nan | nan | 16120 | TK_NotStart | 94810358 | 486 | 94810358_486
A193450 | TT_Task | Final Assembly for Trainset #006 DM1 | 13/06/2022 | 05/10/2022 | nan | nan | 0 | TK_NotStart | 94810358 | 350 | 94810358_350
A198700 | TT_Task | Final Assembly for Trainset #006 DM2 | 20/06/2022 | 26/10/2022 | nan | nan | 0 | TK_NotStart | 94810358 | 351 | 94810358_351
A198710 | TT_Task | Final Assembly for Trainset #006 T | 27/06/2022 | 02/11/2022 | nan | nan | 0 | TK_NotStart | 94810358 | 352 | 94810358_352
A193800 | TT_Task | Transport Carbody to Vasteras for Trainset #006 DM1 (8 weeks @ 7d/wk for Sea Freight) | 24/04/2023 | 18/06/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 489 | 94810358_489
A199400 | TT_Task | Transport Carbody to Vasteras for Trainset #006 T (8 weeks @ 7d/wk for Sea Freight) | 16/05/2023 | 10/07/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 490 | 94810358_490
A199410 | TT_Task | Transport Carbody to Vasteras for Trainset #006 DM2 (8 weeks @ 7d/wl for Sea Freight) | 04/05/2023 | 28/06/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 491 | 94810358_491
A191020 | TT_Task | Train Completion incl. Comissioning (2nd Track) and HP4 for Trainset #006 | 21/07/2023 | 14/08/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 492 | 94810358_492
A202740 | TT_Task | Final Assembly incl. Single Unit Test for Trainset #006 DM1 (1st Track) | 19/06/2023 | 19/06/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 493 | 94810358_493
A202750 | TT_Task | Final Assembly incl. Single Unit Test for Trainset #006 DM2 (1st Track) | 29/06/2023 | 29/06/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 494 | 94810358_494
A202760 | TT_Task | Final Assembly incl. Single Unit Test for Trainset #006 T (1st Track) | 11/07/2023 | 11/07/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 495 | 94810358_495
A190300 | TT_Task | Preliminary Takeover Inspection for Trainset #006 (regardless Swedish Breaks) | 02/05/2024 | 29/05/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 496 | 94810358_496
A202770 | TT_Task | Last TT Report Creation (1month) and NoBo/DeBo/AsBo Asessment (3 months, assume no changes in TCR) | 24/08/2023 | 13/12/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 328 | 94810358_328
A202780 | TT_Task | J5 Application and Approval Time (4 months) | 04/01/2024 | 24/04/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 326 | 94810358_326
A203170 | TT_Task | Final Assembly for Trainset #007 DM1 | 04/07/2022 | 26/10/2022 | nan | nan | 0 | TK_NotStart | 94810358 | 350 | 94810358_350
A203190 | TT_Task | Final Assembly for Trainset #007 DM2 | 11/07/2022 | 16/11/2022 | nan | nan | 0 | TK_NotStart | 94810358 | 351 | 94810358_351
A203200 | TT_Task | Final Assembly for Trainset #007 T | 18/07/2022 | 23/11/2022 | nan | nan | 0 | TK_NotStart | 94810358 | 352 | 94810358_352
A203180 | TT_Task | Transport Carbody to Vasteras for Trainset #007 DM1 (8 weeks @ 7d/wk for Sea Freight) | 02/10/2023 | 26/11/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 489 | 94810358_489
A203210 | TT_Task | Transport Carbody to Vasteras for Trainset #007 T (8 weeks @ 7d/wk for Sea Freight) | 07/11/2023 | 01/01/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 490 | 94810358_490
A203220 | TT_Task | Transport Carbody to Vasteras for Trainset #007 DM2 (8 weeks @ 7d/wl for Sea Freight) | 12/10/2023 | 06/12/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 491 | 94810358_491
A203160 | TT_Task | Train Completion incl. Comissioning (2nd Track) and HP4 for Trainset #007 | 12/01/2024 | 05/02/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 492 | 94810358_492
A203230 | TT_Task | Final Assembly incl. Single Unit Test for Trainset #007 DM1 (1st Track) | 27/11/2023 | 27/11/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 493 | 94810358_493
A203240 | TT_Task | Final Assembly incl. Single Unit Test for Trainset #007 DM2 (1st Track) | 07/12/2023 | 07/12/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 494 | 94810358_494
A203250 | TT_Task | Final Assembly incl. Single Unit Test for Trainset #007 T (1st Track) | 02/01/2024 | 02/01/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 495 | 94810358_495
A203150 | TT_Task | Preliminary Takeover Inspection for Trainset #007 (regardless Swedish Breaks) | 20/05/2024 | 14/06/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 496 | 94810358_496
A203280 | TT_Task | Final Assembly for Trainset #008 DM1 | 25/07/2022 | 16/11/2022 | nan | nan | 0 | TK_NotStart | 94810358 | 350 | 94810358_350
A203300 | TT_Task | Final Assembly for Trainset #008 DM2 | 01/08/2022 | 07/12/2022 | nan | nan | 0 | TK_NotStart | 94810358 | 351 | 94810358_351
A203310 | TT_Task | Final Assembly for Trainset #008 T | 08/08/2022 | 14/12/2022 | nan | nan | 0 | TK_NotStart | 94810358 | 352 | 94810358_352
A203290 | TT_Task | Transport Carbody to Vasteras for Trainset #008 DM1 (8 weeks @ 7d/wk for Sea Freight) | 17/11/2023 | 11/01/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 489 | 94810358_489
A203320 | TT_Task | Transport Carbody to Vasteras for Trainset #008 T (8 weeks @ 7d/wk for Sea Freight) | 11/12/2023 | 04/02/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 490 | 94810358_490
A203330 | TT_Task | Transport Carbody to Vasteras for Trainset #008 DM2 (8 weeks @ 7d/wl for Sea Freight) | 29/11/2023 | 23/01/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 491 | 94810358_491
A203270 | TT_Task | Train Completion incl. Comissioning (2nd Track) and HP4 for Trainset #008 | 15/02/2024 | 08/03/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 492 | 94810358_492
A203340 | TT_Task | Final Assembly incl. Single Unit Test for Trainset #008 DM1 (1st Track) | 12/01/2024 | 12/01/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 493 | 94810358_493
A203350 | TT_Task | Final Assembly incl. Single Unit Test for Trainset #008 DM2 (1st Track) | 24/01/2024 | 24/01/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 494 | 94810358_494
A203360 | TT_Task | Final Assembly incl. Single Unit Test for Trainset #008 T (1st Track) | 05/02/2024 | 05/02/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 495 | 94810358_495
A203260 | TT_Task | Preliminary Takeover Inspection for Trainset #008 (regardless Swedish Breaks) | 03/06/2024 | 28/06/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 496 | 94810358_496
A203390 | TT_Task | Final Assembly for Trainset #009 DM1 | 15/08/2022 | 07/12/2022 | nan | nan | 0 | TK_NotStart | 94810358 | 350 | 94810358_350
A203410 | TT_Task | Final Assembly for Trainset #009 DM2 | 22/08/2022 | 28/12/2022 | nan | nan | 0 | TK_NotStart | 94810358 | 351 | 94810358_351
A203420 | TT_Task | Final Assembly for Trainset #009 T | 29/08/2022 | 04/01/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 352 | 94810358_352
A203400 | TT_Task | Transport Carbody to Vasteras for Trainset #009 DM1 (8 weeks @ 7d/wk for Sea Freight) | 21/12/2023 | 14/02/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 489 | 94810358_489
A203430 | TT_Task | Transport Carbody to Vasteras for Trainset #009 T (8 weeks @ 7d/wk for Sea Freight) | 08/01/2024 | 03/03/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 490 | 94810358_490
A203440 | TT_Task | Transport Carbody to Vasteras for Trainset #009 DM2 (8 weeks @ 7d/wl for Sea Freight) | 29/12/2023 | 22/02/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 491 | 94810358_491
A203380 | TT_Task | Train Completion incl. Comissioning (2nd Track) and HP4 for Trainset #009 | 20/03/2024 | 11/04/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 492 | 94810358_492
A203450 | TT_Task | Final Assembly incl. Single Unit Test for Trainset #009 DM1 (1st Track) | 15/02/2024 | 15/02/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 493 | 94810358_493
A203460 | TT_Task | Final Assembly incl. Single Unit Test for Trainset #009 DM2 (1st Track) | 23/02/2024 | 23/02/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 494 | 94810358_494
A203470 | TT_Task | Final Assembly incl. Single Unit Test for Trainset #009 T (1st Track) | 04/03/2024 | 04/03/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 495 | 94810358_495
A203370 | TT_Task | Preliminary Takeover Inspection for Trainset #009 (regardless Swedish Breaks) | 17/06/2024 | 12/07/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 496 | 94810358_496
A203500 | TT_Task | Final Assembly for Trainset #010 DM1 | 05/09/2022 | 28/12/2022 | nan | nan | 0 | TK_NotStart | 94810358 | 350 | 94810358_350
A203520 | TT_Task | Final Assembly for Trainset #010 DM2 | 12/09/2022 | 18/01/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 351 | 94810358_351
A203530 | TT_Task | Final Assembly for Trainset #010 T | 19/09/2022 | 25/01/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 352 | 94810358_352
A203510 | TT_Task | Transport Carbody to Vasteras for Trainset #010 DM1 (8 weeks @ 7d/wk for Sea Freight) | 16/01/2024 | 11/03/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 489 | 94810358_489
A203540 | TT_Task | Transport Carbody to Vasteras for Trainset #010 T (8 weeks @ 7d/wk for Sea Freight) | 01/02/2024 | 27/03/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 490 | 94810358_490
A203550 | TT_Task | Transport Carbody to Vasteras for Trainset #010 DM2 (8 weeks @ 7d/wl for Sea Freight) | 24/01/2024 | 19/03/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 491 | 94810358_491
A203490 | TT_Task | Train Completion incl. Comissioning (2nd Track) and HP4 for Trainset #010 | 15/04/2024 | 07/05/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 492 | 94810358_492
A203560 | TT_Task | Final Assembly incl. Single Unit Test for Trainset #010 DM1 (1st Track) | 12/03/2024 | 12/03/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 493 | 94810358_493
A203570 | TT_Task | Final Assembly incl. Single Unit Test for Trainset #010 DM2 (1st Track) | 20/03/2024 | 20/03/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 494 | 94810358_494
A203580 | TT_Task | Final Assembly incl. Single Unit Test for Trainset #010 T (1st Track) | 28/03/2024 | 28/03/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 495 | 94810358_495
A203480 | TT_Task | Preliminary Takeover Inspection for Trainset #010 (regardless Swedish Breaks) | 01/07/2024 | 26/07/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 496 | 94810358_496
A203610 | TT_Task | Final Assembly for Trainset #011 DM1 | 26/09/2022 | 18/01/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 350 | 94810358_350
A203630 | TT_Task | Final Assembly for Trainset #011 DM2 | 03/10/2022 | 08/02/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 351 | 94810358_351
A203640 | TT_Task | Final Assembly for Trainset #011 T | 10/10/2022 | 15/02/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 352 | 94810358_352
A203620 | TT_Task | Transport Carbody to Vasteras for Trainset #011 DM1 (8 weeks @ 7d/wk for Sea Freight) | 09/02/2024 | 04/04/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 489 | 94810358_489
A203650 | TT_Task | Transport Carbody to Vasteras for Trainset #011 T (8 weeks @ 7d/wk for Sea Freight) | 27/02/2024 | 22/04/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 490 | 94810358_490
A203660 | TT_Task | Transport Carbody to Vasteras for Trainset #011 DM2 (8 weeks @ 7d/wl for Sea Freight) | 19/02/2024 | 14/04/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 491 | 94810358_491
A203600 | TT_Task | Train Completion incl. Comissioning (2nd Track) and HP4 for Trainset #011 | 09/05/2024 | 31/05/2024 | nan | nan | 232 | TK_NotStart | 94810358 | 492 | 94810358_492
A203670 | TT_Task | Final Assembly incl. Single Unit Test for Trainset #011 DM1 (1st Track) | 05/04/2024 | 05/04/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 493 | 94810358_493
A203680 | TT_Task | Final Assembly incl. Single Unit Test for Trainset #011 DM2 (1st Track) | 15/04/2024 | 15/04/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 494 | 94810358_494
A203690 | TT_Task | Final Assembly incl. Single Unit Test for Trainset #011 T (1st Track) | 23/04/2024 | 23/04/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 495 | 94810358_495
A203590 | TT_Task | Preliminary Takeover Inspection for Trainset #011 (regardless Swedish Breaks) | 15/07/2024 | 09/08/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 496 | 94810358_496
A203730 | TT_Task | Final Assembly for Trainset #012 DM1 | 17/10/2022 | 08/02/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 350 | 94810358_350
A203750 | TT_Task | Final Assembly for Trainset #012 DM2 | 24/10/2022 | 01/03/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 351 | 94810358_351
A203760 | TT_Task | Final Assembly for Trainset #012 T | 31/10/2022 | 08/03/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 352 | 94810358_352
A203740 | TT_Task | Transport Carbody to Vasteras for Trainset #012 DM1 (8 weeks @ 7d/wk for Sea Freight) | 06/03/2024 | 30/04/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 489 | 94810358_489
A203770 | TT_Task | Transport Carbody to Vasteras for Trainset #012 T (8 weeks @ 7d/wk for Sea Freight) | 20/03/2024 | 14/05/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 490 | 94810358_490
A203780 | TT_Task | Transport Carbody to Vasteras for Trainset #012 DM2 (8 weeks @ 7d/wl for Sea Freight) | 13/03/2024 | 07/05/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 491 | 94810358_491
A203720 | TT_Task | Train Completion incl. Comissioning (2nd Track) and HP4 for Trainset #012 | 22/05/2024 | 13/06/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 492 | 94810358_492
A203790 | TT_Task | Final Assembly incl. Single Unit Test for Trainset #012 DM1 (1st Track) | 01/05/2024 | 01/05/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 493 | 94810358_493
A203800 | TT_Task | Final Assembly incl. Single Unit Test for Trainset #012 DM2 (1st Track) | 08/05/2024 | 08/05/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 494 | 94810358_494
A203810 | TT_Task | Final Assembly incl. Single Unit Test for Trainset #012 T (1st Track) | 15/05/2024 | 15/05/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 495 | 94810358_495
A203710 | TT_Task | Preliminary Takeover Inspection for Trainset #012 (regardless Swedish Breaks) | 29/07/2024 | 23/08/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 496 | 94810358_496
A203840 | TT_Task | Final Assembly for Trainset #013 DM1 | 07/11/2022 | 01/03/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 350 | 94810358_350
A203860 | TT_Task | Final Assembly for Trainset #013 DM2 | 14/11/2022 | 22/03/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 351 | 94810358_351
A203870 | TT_Task | Final Assembly for Trainset #013 T | 21/11/2022 | 29/03/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 352 | 94810358_352
A203850 | TT_Task | Transport Carbody to Vasteras for Trainset #013 DM1 (8 weeks @ 7d/wk for Sea Freight) | 27/03/2024 | 21/05/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 489 | 94810358_489
A203880 | TT_Task | Transport Carbody to Vasteras for Trainset #013 T (8 weeks @ 7d/wk for Sea Freight) | 10/04/2024 | 04/06/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 490 | 94810358_490
A203890 | TT_Task | Transport Carbody to Vasteras for Trainset #013 DM2 (8 weeks @ 7d/wl for Sea Freight) | 03/04/2024 | 28/05/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 491 | 94810358_491
A203830 | TT_Task | Train Completion incl. Comissioning (2nd Track) and HP4 for Trainset #007 | 12/06/2024 | 04/07/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 492 | 94810358_492
A203900 | TT_Task | Final Assembly incl. Single Unit Test for Trainset #013 DM1 (1st Track) | 22/05/2024 | 22/05/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 493 | 94810358_493
A203910 | TT_Task | Final Assembly incl. Single Unit Test for Trainset #013 DM2 (1st Track) | 29/05/2024 | 29/05/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 494 | 94810358_494
A203920 | TT_Task | Final Assembly incl. Single Unit Test for Trainset #013 T (1st Track) | 05/06/2024 | 05/06/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 495 | 94810358_495
A203820 | TT_Task | Preliminary Takeover Inspection for Trainset #013 (regardless Swedish Breaks) | 12/08/2024 | 06/09/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 496 | 94810358_496
A203950 | TT_Task | Final Assembly for Trainset #014 DM1 | 28/11/2022 | 22/03/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 350 | 94810358_350
A203970 | TT_Task | Final Assembly for Trainset #014 DM2 | 05/12/2022 | 12/04/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 351 | 94810358_351
A203980 | TT_Task | Final Assembly for Trainset #014 T | 12/12/2022 | 19/04/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 352 | 94810358_352
A203960 | TT_Task | Transport Carbody to Vasteras for Trainset #014 DM1 (8 weeks @ 7d/wk for Sea Freight) | 17/04/2024 | 11/06/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 489 | 94810358_489
A203990 | TT_Task | Transport Carbody to Vasteras for Trainset #014 T (8 weeks @ 7d/wk for Sea Freight) | 01/05/2024 | 25/06/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 490 | 94810358_490
A204000 | TT_Task | Transport Carbody to Vasteras for Trainset #014 DM2 (8 weeks @ 7d/wl for Sea Freight) | 24/04/2024 | 18/06/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 491 | 94810358_491
A203940 | TT_Task | Train Completion incl. Comissioning (2nd Track) and HP4 for Trainset #014 | 03/07/2024 | 25/07/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 492 | 94810358_492
A204010 | TT_Task | Final Assembly incl. Single Unit Test for Trainset #014 DM1 (1st Track) | 12/06/2024 | 12/06/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 493 | 94810358_493
A204020 | TT_Task | Final Assembly incl. Single Unit Test for Trainset #014 DM2 (1st Track) | 19/06/2024 | 19/06/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 494 | 94810358_494
A204030 | TT_Task | Final Assembly incl. Single Unit Test for Trainset #014 T (1st Track) | 26/06/2024 | 26/06/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 495 | 94810358_495
A203930 | TT_Task | Preliminary Takeover Inspection for Trainset #014 (regardless Swedish Breaks) | 26/08/2024 | 20/09/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 496 | 94810358_496
A204060 | TT_Task | Final Assembly for Trainset #015 DM1 | 19/12/2022 | 12/04/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 350 | 94810358_350
A204080 | TT_Task | Final Assembly for Trainset #015 DM2 | 26/12/2022 | 03/05/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 351 | 94810358_351
A204090 | TT_Task | Final Assembly for Trainset #015 T | 02/01/2023 | 10/05/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 352 | 94810358_352
A204070 | TT_Task | Transport Carbody to Vasteras for Trainset #015 DM1 (8 weeks @ 7d/wk for Sea Freight) | 08/05/2024 | 02/07/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 489 | 94810358_489
A204100 | TT_Task | Transport Carbody to Vasteras for Trainset #015 T (8 weeks @ 7d/wk for Sea Freight) | 20/05/2024 | 14/07/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 490 | 94810358_490
A204110 | TT_Task | Transport Carbody to Vasteras for Trainset #015 DM2 (8 weeks @ 7d/wl for Sea Freight) | 14/05/2024 | 08/07/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 491 | 94810358_491
A204050 | TT_Task | Train Completion incl. Comissioning (2nd Track) and HP4 for Trainset #015 | 24/07/2024 | 15/08/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 492 | 94810358_492
A204120 | TT_Task | Final Assembly incl. Single Unit Test for Trainset #015 DM1 (1st Track) | 03/07/2024 | 03/07/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 493 | 94810358_493
A204130 | TT_Task | Final Assembly incl. Single Unit Test for Trainset #015 DM2 (1st Track) | 09/07/2024 | 09/07/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 494 | 94810358_494
A204140 | TT_Task | Final Assembly incl. Single Unit Test for Trainset #015 T (1st Track) | 15/07/2024 | 15/07/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 495 | 94810358_495
A204040 | TT_Task | Preliminary Takeover Inspection for Trainset #015 (regardless Swedish Breaks) | 09/09/2024 | 04/10/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 496 | 94810358_496
A204170 | TT_Task | Final Assembly for Trainset #016 DM1 | 09/01/2023 | 03/05/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 350 | 94810358_350
A204190 | TT_Task | Final Assembly for Trainset #016 DM2 | 16/01/2023 | 24/05/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 351 | 94810358_351
A204200 | TT_Task | Final Assembly for Trainset #016 T | 23/01/2023 | 31/05/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 352 | 94810358_352
A204180 | TT_Task | Transport Carbody to Vasteras for Trainset #016 DM1 (8 weeks @ 7d/wk for Sea Freight) | 24/05/2024 | 18/07/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 489 | 94810358_489
A204210 | TT_Task | Transport Carbody to Vasteras for Trainset #016 T (8 weeks @ 7d/wk for Sea Freight) | 05/06/2024 | 30/07/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 490 | 94810358_490
A204220 | TT_Task | Transport Carbody to Vasteras for Trainset #016 DM2 (8 weeks @ 7d/wl for Sea Freight) | 30/05/2024 | 24/07/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 491 | 94810358_491
A204160 | TT_Task | Train Completion incl. Comissioning (2nd Track) and HP4 for Trainset #016 | 09/08/2024 | 02/09/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 492 | 94810358_492
A204230 | TT_Task | Final Assembly incl. Single Unit Test for Trainset #016 DM1 (1st Track) | 19/07/2024 | 19/07/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 493 | 94810358_493
A204240 | TT_Task | Final Assembly incl. Single Unit Test for Trainset #016 DM2 (1st Track) | 25/07/2024 | 25/07/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 494 | 94810358_494
A204250 | TT_Task | Final Assembly incl. Single Unit Test for Trainset #016 T (1st Track) | 31/07/2024 | 31/07/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 495 | 94810358_495
A204150 | TT_Task | Preliminary Takeover Inspection for Trainset #016 (regardless Swedish Breaks) | 23/09/2024 | 18/10/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 496 | 94810358_496
A204280 | TT_Task | Final Assembly for Trainset #017 DM1 | 30/01/2023 | 24/05/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 350 | 94810358_350
A204300 | TT_Task | Final Assembly for Trainset #017 DM2 | 06/02/2023 | 14/06/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 351 | 94810358_351
A204310 | TT_Task | Final Assembly for Trainset #017 T | 13/02/2023 | 21/06/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 352 | 94810358_352
A204290 | TT_Task | Transport Carbody to Vasteras for Trainset #017 DM1 (8 weeks @ 7d/wk for Sea Freight) | 11/06/2024 | 05/08/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 489 | 94810358_489
A204320 | TT_Task | Transport Carbody to Vasteras for Trainset #017 T (8 weeks @ 7d/wk for Sea Freight) | 21/06/2024 | 15/08/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 490 | 94810358_490
A204330 | TT_Task | Transport Carbody to Vasteras for Trainset #017 DM2 (8 weeks @ 7d/wl for Sea Freight) | 17/06/2024 | 11/08/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 491 | 94810358_491
A204270 | TT_Task | Train Completion incl. Comissioning (2nd Track) and HP4 for Trainset #017 | 27/08/2024 | 18/09/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 492 | 94810358_492
A204340 | TT_Task | Final Assembly incl. Single Unit Test for Trainset #017 DM1 (1st Track) | 06/08/2024 | 06/08/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 493 | 94810358_493
A204350 | TT_Task | Final Assembly incl. Single Unit Test for Trainset #017 DM2 (1st Track) | 12/08/2024 | 12/08/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 494 | 94810358_494
A204360 | TT_Task | Final Assembly incl. Single Unit Test for Trainset #017 T (1st Track) | 16/08/2024 | 16/08/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 495 | 94810358_495
A204260 | TT_Task | Preliminary Takeover Inspection for Trainset #017 (regardless Swedish Breaks) | 07/10/2024 | 01/11/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 496 | 94810358_496
A204390 | TT_Task | Final Assembly for Trainset #018 DM1 | 20/02/2023 | 14/06/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 350 | 94810358_350
A204410 | TT_Task | Final Assembly for Trainset #018 DM2 | 27/02/2023 | 05/07/2023 | nan | nan | 0 | TK_NotStart | 94810358 | 351 | 94810358_351
A204420 | TT_Task | Final Assembly for Trainset #018 T | 06/03/2023 | 12/07/2023 | nan | nan | 2144 | TK_NotStart | 94810358 | 352 | 94810358_352
A204400 | TT_Task | Transport Carbody to Vasteras for Trainset #018 DM1 (8 weeks @ 7d/wk for Sea Freight) | 27/06/2024 | 21/08/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 489 | 94810358_489
A204430 | TT_Task | Transport Carbody to Vasteras for Trainset #018 T (8 weeks @ 7d/wk for Sea Freight) | 09/07/2024 | 02/09/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 490 | 94810358_490
A204440 | TT_Task | Transport Carbody to Vasteras for Trainset #018 DM2 (8 weeks @ 7d/wl for Sea Freight) | 03/07/2024 | 27/08/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 491 | 94810358_491
A204380 | TT_Task | Train Completion incl. Comissioning (2nd Track) and HP4 for Trainset #018 | 12/09/2024 | 04/10/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 492 | 94810358_492
A204450 | TT_Task | Final Assembly incl. Single Unit Test for Trainset #018 DM1 (1st Track) | 22/08/2024 | 22/08/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 493 | 94810358_493
A204460 | TT_Task | Final Assembly incl. Single Unit Test for Trainset #018 DM2 (1st Track) | 28/08/2024 | 28/08/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 494 | 94810358_494
A204470 | TT_Task | Final Assembly incl. Single Unit Test for Trainset #018 T (1st Track) | 03/09/2024 | 03/09/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 495 | 94810358_495
A204370 | TT_Task | Preliminary Takeover Inspection for Trainset #018 (regardless Swedish Breaks) | 21/10/2024 | 15/11/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 496 | 94810358_496
A204500 | TT_Task | Final Assembly for Trainset #019 DM1 | 03/12/2021 | 29/03/2022 | nan | nan | 0 | TK_NotStart | 94810358 | 350 | 94810358_350
A204520 | TT_Task | Final Assembly for Trainset #019 DM2 | 10/12/2021 | 19/04/2022 | nan | nan | 0 | TK_NotStart | 94810358 | 351 | 94810358_351
A204530 | TT_Task | Final Assembly for Trainset #019 T | 17/12/2021 | 26/04/2022 | nan | nan | 4768 | TK_NotStart | 94810358 | 352 | 94810358_352
A204510 | TT_Task | Transport Carbody to Vasteras for Trainset #019 DM1 (8 weeks @ 7d/wk for Sea Freight) | 15/07/2024 | 08/09/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 489 | 94810358_489
A204540 | TT_Task | Transport Carbody to Vasteras for Trainset #019 T (8 weeks @ 7d/wk for Sea Freight) | 25/07/2024 | 18/09/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 490 | 94810358_490
A204550 | TT_Task | Transport Carbody to Vasteras for Trainset #019 DM2 (8 weeks @ 7d/wl for Sea Freight) | 19/07/2024 | 12/09/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 491 | 94810358_491
A204490 | TT_Task | Train Completion incl. Comissioning (2nd Track) and HP4 for Trainset #019 | 30/09/2024 | 22/10/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 492 | 94810358_492
A204560 | TT_Task | Final Assembly incl. Single Unit Test for Trainset #019 DM1 (1st Track) | 09/09/2024 | 09/09/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 493 | 94810358_493
A204570 | TT_Task | Final Assembly incl. Single Unit Test for Trainset #019 DM2 (1st Track) | 13/09/2024 | 13/09/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 494 | 94810358_494
A204580 | TT_Task | Final Assembly incl. Single Unit Test for Trainset #019 T (1st Track) | 19/09/2024 | 19/09/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 495 | 94810358_495
A204480 | TT_Task | Preliminary Takeover Inspection for Trainset #019 (regardless Swedish Breaks) | 04/11/2024 | 29/11/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 496 | 94810358_496
A204610 | TT_Task | Final Assembly for Trainset #020 DM1 | 03/12/2021 | 29/03/2022 | nan | nan | 0 | TK_NotStart | 94810358 | 350 | 94810358_350
A204630 | TT_Task | Final Assembly for Trainset #020 DM2 | 10/12/2021 | 19/04/2022 | nan | nan | 0 | TK_NotStart | 94810358 | 351 | 94810358_351
A204640 | TT_Task | Final Assembly for Trainset #020 T | 17/12/2021 | 26/04/2022 | nan | nan | 4864 | TK_NotStart | 94810358 | 352 | 94810358_352
A204620 | TT_Task | Transport Carbody to Vasteras for Trainset #020 DM1 (8 weeks @ 7d/wk for Sea Freight) | 31/07/2024 | 24/09/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 489 | 94810358_489
A204650 | TT_Task | Transport Carbody to Vasteras for Trainset #020 T (8 weeks @ 7d/wk for Sea Freight) | 12/08/2024 | 06/10/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 490 | 94810358_490
A204660 | TT_Task | Transport Carbody to Vasteras for Trainset #020 DM2 (8 weeks @ 7d/wl for Sea Freight) | 06/08/2024 | 30/09/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 491 | 94810358_491
A204600 | TT_Task | Train Completion incl. Comissioning (2nd Track) and HP4 for Trainset #020 | 16/10/2024 | 07/11/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 492 | 94810358_492
A204670 | TT_Task | Final Assembly incl. Single Unit Test for Trainset #020 DM1 (1st Track) | 25/09/2024 | 25/09/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 493 | 94810358_493
A204680 | TT_Task | Final Assembly incl. Single Unit Test for Trainset #020 DM2 (1st Track) | 01/10/2024 | 01/10/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 494 | 94810358_494
A204690 | TT_Task | Final Assembly incl. Single Unit Test for Trainset #020 T (1st Track) | 07/10/2024 | 07/10/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 495 | 94810358_495
A204590 | TT_Task | Preliminary Takeover Inspection for Trainset #020 (regardless Swedish Breaks) | 18/11/2024 | 13/12/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 496 | 94810358_496
A204720 | TT_Task | Final Assembly for Trainset #021 DM1 | 03/12/2021 | 29/03/2022 | nan | nan | 0 | TK_NotStart | 94810358 | 350 | 94810358_350
A204740 | TT_Task | Final Assembly for Trainset #021 DM2 | 10/12/2021 | 19/04/2022 | nan | nan | 0 | TK_NotStart | 94810358 | 351 | 94810358_351
A204750 | TT_Task | Final Assembly for Trainset #021 T | 17/12/2021 | 26/04/2022 | nan | nan | 4960 | TK_NotStart | 94810358 | 352 | 94810358_352
A204730 | TT_Task | Transport Carbody to Vasteras for Trainset #021 DM1 (8 weeks @ 7d/wk for Sea Freight) | 16/08/2024 | 10/10/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 489 | 94810358_489
A204760 | TT_Task | Transport Carbody to Vasteras for Trainset #021 T (8 weeks @ 7d/wk for Sea Freight) | 28/08/2024 | 22/10/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 490 | 94810358_490
A204770 | TT_Task | Transport Carbody to Vasteras for Trainset #021 DM2 (8 weeks @ 7d/wl for Sea Freight) | 22/08/2024 | 16/10/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 491 | 94810358_491
A204710 | TT_Task | Train Completion incl. Comissioning (2nd Track) and HP4 for Trainset #021 | 01/11/2024 | 25/11/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 492 | 94810358_492
A204780 | TT_Task | Final Assembly incl. Single Unit Test for Trainset #021 DM1 (1st Track) | 11/10/2024 | 11/10/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 493 | 94810358_493
A204790 | TT_Task | Final Assembly incl. Single Unit Test for Trainset #021 DM2 (1st Track) | 17/10/2024 | 17/10/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 494 | 94810358_494
A204800 | TT_Task | Final Assembly incl. Single Unit Test for Trainset #021 T (1st Track) | 23/10/2024 | 23/10/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 495 | 94810358_495
A204700 | TT_Task | Preliminary Takeover Inspection for Trainset #021 (regardless Swedish Breaks) | 02/12/2024 | 27/12/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 496 | 94810358_496
A204830 | TT_Task | Final Assembly for Trainset #022 DM1 | 03/12/2021 | 29/03/2022 | nan | nan | 0 | TK_NotStart | 94810358 | 350 | 94810358_350
A204850 | TT_Task | Final Assembly for Trainset #022 DM2 | 10/12/2021 | 19/04/2022 | nan | nan | 0 | TK_NotStart | 94810358 | 351 | 94810358_351
A204860 | TT_Task | Final Assembly for Trainset #022 T | 17/12/2021 | 26/04/2022 | nan | nan | 5056 | TK_NotStart | 94810358 | 352 | 94810358_352
A204840 | TT_Task | Transport Carbody to Vasteras for Trainset #022 DM1 (8 weeks @ 7d/wk for Sea Freight) | 03/09/2024 | 28/10/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 489 | 94810358_489
A204870 | TT_Task | Transport Carbody to Vasteras for Trainset #022 T (8 weeks @ 7d/wk for Sea Freight) | 13/09/2024 | 07/11/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 490 | 94810358_490
A204880 | TT_Task | Transport Carbody to Vasteras for Trainset #022 DM2 (8 weeks @ 7d/wl for Sea Freight) | 09/09/2024 | 03/11/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 491 | 94810358_491
A204820 | TT_Task | Train Completion incl. Comissioning (2nd Track) and HP4 for Trainset #022 | 19/11/2024 | 11/12/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 492 | 94810358_492
A204890 | TT_Task | Final Assembly incl. Single Unit Test for Trainset #022 DM1 (1st Track) | 29/10/2024 | 29/10/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 493 | 94810358_493
A204900 | TT_Task | Final Assembly incl. Single Unit Test for Trainset #022 DM2 (1st Track) | 04/11/2024 | 04/11/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 494 | 94810358_494
A204910 | TT_Task | Final Assembly incl. Single Unit Test for Trainset #022 T (1st Track) | 08/11/2024 | 08/11/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 495 | 94810358_495
A204810 | TT_Task | Preliminary Takeover Inspection for Trainset #022 (regardless Swedish Breaks) | 16/12/2024 | 10/01/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 496 | 94810358_496
A204940 | TT_Task | Final Assembly for Trainset #023 DM1 | 03/12/2021 | 29/03/2022 | nan | nan | 0 | TK_NotStart | 94810358 | 350 | 94810358_350
A204960 | TT_Task | Final Assembly for Trainset #023 DM2 | 10/12/2021 | 19/04/2022 | nan | nan | 0 | TK_NotStart | 94810358 | 351 | 94810358_351
A204970 | TT_Task | Final Assembly for Trainset #023 T | 17/12/2021 | 26/04/2022 | nan | nan | 5152 | TK_NotStart | 94810358 | 352 | 94810358_352
A204950 | TT_Task | Transport Carbody to Vasteras for Trainset #023 DM1 (8 weeks @ 7d/wk for Sea Freight) | 19/09/2024 | 13/11/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 489 | 94810358_489
A204980 | TT_Task | Transport Carbody to Vasteras for Trainset #023 T (8 weeks @ 7d/wk for Sea Freight) | 01/10/2024 | 25/11/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 490 | 94810358_490
A204990 | TT_Task | Transport Carbody to Vasteras for Trainset #023 DM2 (8 weeks @ 7d/wl for Sea Freight) | 25/09/2024 | 19/11/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 491 | 94810358_491
A204930 | TT_Task | Train Completion incl. Comissioning (2nd Track) and HP4 for Trainset #023 | 05/12/2024 | 10/01/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 492 | 94810358_492
A205000 | TT_Task | Final Assembly incl. Single Unit Test for Trainset #023 DM1 (1st Track) | 14/11/2024 | 14/11/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 493 | 94810358_493
A205010 | TT_Task | Final Assembly incl. Single Unit Test for Trainset #023 DM2 (1st Track) | 20/11/2024 | 20/11/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 494 | 94810358_494
A205020 | TT_Task | Final Assembly incl. Single Unit Test for Trainset #023 T (1st Track) | 26/11/2024 | 26/11/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 495 | 94810358_495
A204920 | TT_Task | Preliminary Takeover Inspection for Trainset #023 (regardless Swedish Breaks) | 30/12/2024 | 24/01/2025 | nan | nan | 32 | TK_NotStart | 94810358 | 496 | 94810358_496
A205050 | TT_Task | Final Assembly for Trainset #024 DM1 | 03/12/2021 | 29/03/2022 | nan | nan | 0 | TK_NotStart | 94810358 | 350 | 94810358_350
A205070 | TT_Task | Final Assembly for Trainset #024 DM2 | 10/12/2021 | 19/04/2022 | nan | nan | 0 | TK_NotStart | 94810358 | 351 | 94810358_351
A205080 | TT_Task | Final Assembly for Trainset #024 T | 17/12/2021 | 26/04/2022 | nan | nan | 5232 | TK_NotStart | 94810358 | 352 | 94810358_352
A205060 | TT_Task | Transport Carbody to Vasteras for Trainset #024 DM1 (8 weeks @ 7d/wk for Sea Freight) | 07/10/2024 | 01/12/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 489 | 94810358_489
A205090 | TT_Task | Transport Carbody to Vasteras for Trainset #024 T (8 weeks @ 7d/wk for Sea Freight) | 15/10/2024 | 09/12/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 490 | 94810358_490
A205100 | TT_Task | Transport Carbody to Vasteras for Trainset #024 DM2 (8 weeks @ 7d/wl for Sea Freight) | 10/10/2024 | 04/12/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 491 | 94810358_491
A205040 | TT_Task | Train Completion incl. Comissioning (2nd Track) and HP4 for Trainset #024 | 06/01/2025 | 28/01/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 492 | 94810358_492
A205110 | TT_Task | Final Assembly incl. Single Unit Test for Trainset #024 DM1 (1st Track) | 02/12/2024 | 02/12/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 493 | 94810358_493
A205120 | TT_Task | Final Assembly incl. Single Unit Test for Trainset #024 DM2 (1st Track) | 05/12/2024 | 05/12/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 494 | 94810358_494
A205130 | TT_Task | Final Assembly incl. Single Unit Test for Trainset #024 T (1st Track) | 10/12/2024 | 10/12/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 495 | 94810358_495
A205030 | TT_Task | Preliminary Takeover Inspection for Trainset #024 (regardless Swedish Breaks) | 17/01/2025 | 13/02/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 496 | 94810358_496
A205160 | TT_Task | Final Assembly for Trainset #025 DM1 | 03/12/2021 | 29/03/2022 | nan | nan | 0 | TK_NotStart | 94810358 | 350 | 94810358_350
A205180 | TT_Task | Final Assembly for Trainset #025 DM2 | 10/12/2021 | 19/04/2022 | nan | nan | 0 | TK_NotStart | 94810358 | 351 | 94810358_351
A205190 | TT_Task | Final Assembly for Trainset #025 T | 17/12/2021 | 26/04/2022 | nan | nan | 5384 | TK_NotStart | 94810358 | 352 | 94810358_352
A205170 | TT_Task | Transport Carbody to Vasteras for Trainset #025 DM1 (8 weeks @ 7d/wk for Sea Freight) | 18/10/2024 | 12/12/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 489 | 94810358_489
A205200 | TT_Task | Transport Carbody to Vasteras for Trainset #025 T (8 weeks @ 7d/wk for Sea Freight) | 11/11/2024 | 05/01/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 490 | 94810358_490
A205210 | TT_Task | Transport Carbody to Vasteras for Trainset #025 DM2 (8 weeks @ 7d/wl for Sea Freight) | 23/10/2024 | 17/12/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 491 | 94810358_491
A205150 | TT_Task | Train Completion incl. Comissioning (2nd Track) and HP4 for Trainset #025 | 17/01/2025 | 10/02/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 492 | 94810358_492
A205220 | TT_Task | Final Assembly incl. Single Unit Test for Trainset #025 DM1 (1st Track) | 13/12/2024 | 13/12/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 493 | 94810358_493
A205230 | TT_Task | Final Assembly incl. Single Unit Test for Trainset #025 DM2 (1st Track) | 18/12/2024 | 18/12/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 494 | 94810358_494
A205240 | TT_Task | Final Assembly incl. Single Unit Test for Trainset #025 T (1st Track) | 06/01/2025 | 06/01/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 495 | 94810358_495
A205140 | TT_Task | Preliminary Takeover Inspection for Trainset #025 (regardless Swedish Breaks) | 31/01/2025 | 27/02/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 496 | 94810358_496
A205270 | TT_Task | Final Assembly for Trainset #026 DM1 | 03/12/2021 | 29/03/2022 | nan | nan | 0 | TK_NotStart | 94810358 | 350 | 94810358_350
A205290 | TT_Task | Final Assembly for Trainset #026 DM2 | 10/12/2021 | 19/04/2022 | nan | nan | 0 | TK_NotStart | 94810358 | 351 | 94810358_351
A205300 | TT_Task | Final Assembly for Trainset #026 T | 17/12/2021 | 26/04/2022 | nan | nan | 5456 | TK_NotStart | 94810358 | 352 | 94810358_352
A205280 | TT_Task | Transport Carbody to Vasteras for Trainset #026 DM1 (8 weeks @ 7d/wk for Sea Freight) | 14/11/2024 | 08/01/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 489 | 94810358_489
A205310 | TT_Task | Transport Carbody to Vasteras for Trainset #026 T (8 weeks @ 7d/wk for Sea Freight) | 22/11/2024 | 16/01/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 490 | 94810358_490
A205320 | TT_Task | Transport Carbody to Vasteras for Trainset #026 DM2 (8 weeks @ 7d/wl for Sea Freight) | 19/11/2024 | 13/01/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 491 | 94810358_491
A205260 | TT_Task | Train Completion incl. Comissioning (2nd Track) and HP4 for Trainset #026 | 30/01/2025 | 21/02/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 492 | 94810358_492
A205330 | TT_Task | Final Assembly incl. Single Unit Test for Trainset #026 DM1 (1st Track) | 09/01/2025 | 09/01/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 493 | 94810358_493
A205340 | TT_Task | Final Assembly incl. Single Unit Test for Trainset #026 DM2 (1st Track) | 14/01/2025 | 14/01/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 494 | 94810358_494
A205350 | TT_Task | Final Assembly incl. Single Unit Test for Trainset #026 T (1st Track) | 17/01/2025 | 17/01/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 495 | 94810358_495
A205250 | TT_Task | Preliminary Takeover Inspection for Trainset #026 (regardless Swedish Breaks) | 14/02/2025 | 13/03/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 496 | 94810358_496
A205380 | TT_Task | Final Assembly for Trainset #027 DM1 | 03/12/2021 | 29/03/2022 | nan | nan | 0 | TK_NotStart | 94810358 | 350 | 94810358_350
A205400 | TT_Task | Final Assembly for Trainset #027 DM2 | 10/12/2021 | 19/04/2022 | nan | nan | 0 | TK_NotStart | 94810358 | 351 | 94810358_351
A205410 | TT_Task | Final Assembly for Trainset #027 T | 17/12/2021 | 26/04/2022 | nan | nan | 5528 | TK_NotStart | 94810358 | 352 | 94810358_352
A205390 | TT_Task | Transport Carbody to Vasteras for Trainset #027 DM1 (8 weeks @ 7d/wk for Sea Freight) | 27/11/2024 | 21/01/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 489 | 94810358_489
A205420 | TT_Task | Transport Carbody to Vasteras for Trainset #027 T (8 weeks @ 7d/wk for Sea Freight) | 05/12/2024 | 29/01/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 490 | 94810358_490
A205430 | TT_Task | Transport Carbody to Vasteras for Trainset #027 DM2 (8 weeks @ 7d/wl for Sea Freight) | 02/12/2024 | 26/01/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 491 | 94810358_491
A205370 | TT_Task | Train Completion incl. Comissioning (2nd Track) and HP4 for Trainset #027 | 12/02/2025 | 06/03/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 492 | 94810358_492
A205440 | TT_Task | Final Assembly incl. Single Unit Test for Trainset #027 DM1 (1st Track) | 22/01/2025 | 22/01/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 493 | 94810358_493
A205450 | TT_Task | Final Assembly incl. Single Unit Test for Trainset #027 DM2 (1st Track) | 27/01/2025 | 27/01/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 494 | 94810358_494
A205460 | TT_Task | Final Assembly incl. Single Unit Test for Trainset #027 T (1st Track) | 30/01/2025 | 30/01/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 495 | 94810358_495
A205360 | TT_Task | Preliminary Takeover Inspection for Trainset #027 (regardless Swedish Breaks) | 28/02/2025 | 27/03/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 496 | 94810358_496
A205490 | TT_Task | Final Assembly for Trainset #028 DM1 | 03/12/2021 | 29/03/2022 | nan | nan | 0 | TK_NotStart | 94810358 | 350 | 94810358_350
A205510 | TT_Task | Final Assembly for Trainset #028 DM2 | 10/12/2021 | 19/04/2022 | nan | nan | 0 | TK_NotStart | 94810358 | 351 | 94810358_351
A205520 | TT_Task | Final Assembly for Trainset #028 T | 17/12/2021 | 26/04/2022 | nan | nan | 5600 | TK_NotStart | 94810358 | 352 | 94810358_352
A205500 | TT_Task | Transport Carbody to Vasteras for Trainset #028 DM1 (8 weeks @ 7d/wk for Sea Freight) | 10/12/2024 | 03/02/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 489 | 94810358_489
A205530 | TT_Task | Transport Carbody to Vasteras for Trainset #028 T (8 weeks @ 7d/wk for Sea Freight) | 18/12/2024 | 11/02/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 490 | 94810358_490
A205540 | TT_Task | Transport Carbody to Vasteras for Trainset #028 DM2 (8 weeks @ 7d/wl for Sea Freight) | 13/12/2024 | 06/02/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 491 | 94810358_491
A205480 | TT_Task | Train Completion incl. Comissioning (2nd Track) and HP4 for Trainset #028 | 25/02/2025 | 19/03/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 492 | 94810358_492
A205550 | TT_Task | Final Assembly incl. Single Unit Test for Trainset #028 DM1 (1st Track) | 04/02/2025 | 04/02/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 493 | 94810358_493
A205560 | TT_Task | Final Assembly incl. Single Unit Test for Trainset #028 DM2 (1st Track) | 07/02/2025 | 07/02/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 494 | 94810358_494
A205570 | TT_Task | Final Assembly incl. Single Unit Test for Trainset #028 T (1st Track) | 12/02/2025 | 12/02/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 495 | 94810358_495
A205470 | TT_Task | Preliminary Takeover Inspection for Trainset #028 (regardless Swedish Breaks) | 14/03/2025 | 10/04/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 496 | 94810358_496
A205600 | TT_Task | Final Assembly for Trainset #029 DM1 | 03/12/2021 | 29/03/2022 | nan | nan | 0 | TK_NotStart | 94810358 | 350 | 94810358_350
A205620 | TT_Task | Final Assembly for Trainset #029 DM2 | 10/12/2021 | 19/04/2022 | nan | nan | 0 | TK_NotStart | 94810358 | 351 | 94810358_351
A205630 | TT_Task | Final Assembly for Trainset #029 T | 17/12/2021 | 26/04/2022 | nan | nan | 5672 | TK_NotStart | 94810358 | 352 | 94810358_352
A205610 | TT_Task | Transport Carbody to Vasteras for Trainset #029 DM1 (8 weeks @ 7d/wk for Sea Freight) | 23/12/2024 | 16/02/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 489 | 94810358_489
A205640 | TT_Task | Transport Carbody to Vasteras for Trainset #029 T (8 weeks @ 7d/wk for Sea Freight) | 31/12/2024 | 24/02/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 490 | 94810358_490
A205650 | TT_Task | Transport Carbody to Vasteras for Trainset #029 DM2 (8 weeks @ 7d/wl for Sea Freight) | 26/12/2024 | 19/02/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 491 | 94810358_491
A205590 | TT_Task | Train Completion incl. Comissioning (2nd Track) and HP4 for Trainset #029 | 10/03/2025 | 01/04/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 492 | 94810358_492
A205660 | TT_Task | Final Assembly incl. Single Unit Test for Trainset #029 DM1 (1st Track) | 17/02/2025 | 17/02/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 493 | 94810358_493
A205670 | TT_Task | Final Assembly incl. Single Unit Test for Trainset #029 DM2 (1st Track) | 20/02/2025 | 20/02/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 494 | 94810358_494
A205680 | TT_Task | Final Assembly incl. Single Unit Test for Trainset #029 T (1st Track) | 25/02/2025 | 25/02/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 495 | 94810358_495
A205580 | TT_Task | Preliminary Takeover Inspection for Trainset #029 (regardless Swedish Breaks) | 28/03/2025 | 24/04/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 496 | 94810358_496
A205710 | TT_Task | Final Assembly for Trainset #030 DM1 | 03/12/2021 | 29/03/2022 | nan | nan | 0 | TK_NotStart | 94810358 | 350 | 94810358_350
A205730 | TT_Task | Final Assembly for Trainset #030 DM2 | 10/12/2021 | 19/04/2022 | nan | nan | 0 | TK_NotStart | 94810358 | 351 | 94810358_351
A205740 | TT_Task | Final Assembly for Trainset #030 T | 17/12/2021 | 26/04/2022 | nan | nan | 5744 | TK_NotStart | 94810358 | 352 | 94810358_352
A205720 | TT_Task | Transport Carbody to Vasteras for Trainset #030 DM1 (8 weeks @ 7d/wk for Sea Freight) | 03/01/2025 | 27/02/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 489 | 94810358_489
A205750 | TT_Task | Transport Carbody to Vasteras for Trainset #030 T (8 weeks @ 7d/wk for Sea Freight) | 13/01/2025 | 09/03/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 490 | 94810358_490
A205760 | TT_Task | Transport Carbody to Vasteras for Trainset #030 DM2 (8 weeks @ 7d/wl for Sea Freight) | 08/01/2025 | 04/03/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 491 | 94810358_491
A205700 | TT_Task | Train Completion incl. Comissioning (2nd Track) and HP4 for Trainset #030 | 21/03/2025 | 14/04/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 492 | 94810358_492
A205770 | TT_Task | Final Assembly incl. Single Unit Test for Trainset #030 DM1 (1st Track) | 28/02/2025 | 28/02/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 493 | 94810358_493
A205780 | TT_Task | Final Assembly incl. Single Unit Test for Trainset #030 DM2 (1st Track) | 05/03/2025 | 05/03/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 494 | 94810358_494
A205790 | TT_Task | Final Assembly incl. Single Unit Test for Trainset #030 T (1st Track) | 10/03/2025 | 10/03/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 495 | 94810358_495
A205690 | TT_Task | Preliminary Takeover Inspection for Trainset #030 (regardless Swedish Breaks) | 11/04/2025 | 08/05/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 496 | 94810358_496
A205820 | TT_Task | Final Assembly for Trainset #031 DM1 | 03/12/2021 | 29/03/2022 | nan | nan | 0 | TK_NotStart | 94810358 | 350 | 94810358_350
A205840 | TT_Task | Final Assembly for Trainset #031 DM2 | 10/12/2021 | 19/04/2022 | nan | nan | 0 | TK_NotStart | 94810358 | 351 | 94810358_351
A205850 | TT_Task | Final Assembly for Trainset #031 T | 17/12/2021 | 26/04/2022 | nan | nan | 5816 | TK_NotStart | 94810358 | 352 | 94810358_352
A205830 | TT_Task | Transport Carbody to Vasteras for Trainset #031 DM1 (8 weeks @ 7d/wk for Sea Freight) | 16/01/2025 | 12/03/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 489 | 94810358_489
A205860 | TT_Task | Transport Carbody to Vasteras for Trainset #031 T (8 weeks @ 7d/wk for Sea Freight) | 24/01/2025 | 20/03/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 490 | 94810358_490
A205870 | TT_Task | Transport Carbody to Vasteras for Trainset #031 DM2 (8 weeks @ 7d/wl for Sea Freight) | 21/01/2025 | 17/03/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 491 | 94810358_491
A205810 | TT_Task | Train Completion incl. Comissioning (2nd Track) and HP4 for Trainset #031 | 03/04/2025 | 25/04/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 492 | 94810358_492
A205880 | TT_Task | Final Assembly incl. Single Unit Test for Trainset #031 DM1 (1st Track) | 13/03/2025 | 13/03/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 493 | 94810358_493
A205890 | TT_Task | Final Assembly incl. Single Unit Test for Trainset #031 DM2 (1st Track) | 18/03/2025 | 18/03/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 494 | 94810358_494
A205900 | TT_Task | Final Assembly incl. Single Unit Test for Trainset #031 T (1st Track) | 21/03/2025 | 21/03/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 495 | 94810358_495
A205800 | TT_Task | Preliminary Takeover Inspection for Trainset #031 (regardless Swedish Breaks) | 25/04/2025 | 22/05/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 496 | 94810358_496
A205930 | TT_Task | Final Assembly for Trainset #032 DM1 | 03/12/2021 | 29/03/2022 | nan | nan | 0 | TK_NotStart | 94810358 | 350 | 94810358_350
A205950 | TT_Task | Final Assembly for Trainset #032 DM2 | 10/12/2021 | 19/04/2022 | nan | nan | 0 | TK_NotStart | 94810358 | 351 | 94810358_351
A205960 | TT_Task | Final Assembly for Trainset #032 T | 17/12/2021 | 26/04/2022 | nan | nan | 5888 | TK_NotStart | 94810358 | 352 | 94810358_352
A205940 | TT_Task | Transport Carbody to Vasteras for Trainset #032 DM1 (8 weeks @ 7d/wk for Sea Freight) | 29/01/2025 | 25/03/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 489 | 94810358_489
A205970 | TT_Task | Transport Carbody to Vasteras for Trainset #032 T (8 weeks @ 7d/wk for Sea Freight) | 06/02/2025 | 02/04/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 490 | 94810358_490
A205980 | TT_Task | Transport Carbody to Vasteras for Trainset #032 DM2 (8 weeks @ 7d/wl for Sea Freight) | 03/02/2025 | 30/03/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 491 | 94810358_491
A205920 | TT_Task | Train Completion incl. Comissioning (2nd Track) and HP4 for Trainset #032 | 16/04/2025 | 08/05/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 492 | 94810358_492
A205990 | TT_Task | Final Assembly incl. Single Unit Test for Trainset #032 DM1 (1st Track) | 26/03/2025 | 26/03/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 493 | 94810358_493
A206000 | TT_Task | Final Assembly incl. Single Unit Test for Trainset #032 DM2 (1st Track) | 31/03/2025 | 31/03/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 494 | 94810358_494
A206010 | TT_Task | Final Assembly incl. Single Unit Test for Trainset #032 T (1st Track) | 03/04/2025 | 03/04/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 495 | 94810358_495
A205910 | TT_Task | Preliminary Takeover Inspection for Trainset #032 (regardless Swedish Breaks) | 09/05/2025 | 05/06/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 496 | 94810358_496
A206040 | TT_Task | Final Assembly for Trainset #033 DM1 | 03/12/2021 | 29/03/2022 | nan | nan | 0 | TK_NotStart | 94810358 | 350 | 94810358_350
A206060 | TT_Task | Final Assembly for Trainset #033 DM2 | 10/12/2021 | 19/04/2022 | nan | nan | 0 | TK_NotStart | 94810358 | 351 | 94810358_351
A206070 | TT_Task | Final Assembly for Trainset #033 T | 17/12/2021 | 26/04/2022 | nan | nan | 5960 | TK_NotStart | 94810358 | 352 | 94810358_352
A206050 | TT_Task | Transport Carbody to Vasteras for Trainset #033 DM1 (8 weeks @ 7d/wk for Sea Freight) | 11/02/2025 | 07/04/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 489 | 94810358_489
A206080 | TT_Task | Transport Carbody to Vasteras for Trainset #033 T (8 weeks @ 7d/wk for Sea Freight) | 19/02/2025 | 15/04/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 490 | 94810358_490
A206090 | TT_Task | Transport Carbody to Vasteras for Trainset #033 DM2 (8 weeks @ 7d/wl for Sea Freight) | 14/02/2025 | 10/04/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 491 | 94810358_491
A206030 | TT_Task | Train Completion incl. Comissioning (2nd Track) and HP4 for Trainset #033 | 29/04/2025 | 21/05/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 492 | 94810358_492
A206100 | TT_Task | Final Assembly incl. Single Unit Test for Trainset #033 DM1 (1st Track) | 08/04/2025 | 08/04/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 493 | 94810358_493
A206110 | TT_Task | Final Assembly incl. Single Unit Test for Trainset #033 DM2 (1st Track) | 11/04/2025 | 11/04/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 494 | 94810358_494
A206120 | TT_Task | Final Assembly incl. Single Unit Test for Trainset #033 T (1st Track) | 16/04/2025 | 16/04/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 495 | 94810358_495
A206020 | TT_Task | Preliminary Takeover Inspection for Trainset #033 (regardless Swedish Breaks) | 23/05/2025 | 19/06/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 496 | 94810358_496
A206150 | TT_Task | Final Assembly for Trainset #034 DM1 | 03/12/2021 | 29/03/2022 | nan | nan | 0 | TK_NotStart | 94810358 | 350 | 94810358_350
A206170 | TT_Task | Final Assembly for Trainset #034 DM2 | 10/12/2021 | 19/04/2022 | nan | nan | 0 | TK_NotStart | 94810358 | 351 | 94810358_351
A206180 | TT_Task | Final Assembly for Trainset #034 T | 17/12/2021 | 26/04/2022 | nan | nan | 6032 | TK_NotStart | 94810358 | 352 | 94810358_352
A206160 | TT_Task | Transport Carbody to Vasteras for Trainset #034 DM1 (8 weeks @ 7d/wk for Sea Freight) | 24/02/2025 | 20/04/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 489 | 94810358_489
A206190 | TT_Task | Transport Carbody to Vasteras for Trainset #034 T (8 weeks @ 7d/wk for Sea Freight) | 04/03/2025 | 28/04/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 490 | 94810358_490
A206200 | TT_Task | Transport Carbody to Vasteras for Trainset #034 DM2 (8 weeks @ 7d/wl for Sea Freight) | 27/02/2025 | 23/04/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 491 | 94810358_491
A206140 | TT_Task | Train Completion incl. Comissioning (2nd Track) and HP4 for Trainset #034 | 12/05/2025 | 03/06/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 492 | 94810358_492
A206210 | TT_Task | Final Assembly incl. Single Unit Test for Trainset #034 DM1 (1st Track) | 21/04/2025 | 21/04/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 493 | 94810358_493
A206220 | TT_Task | Final Assembly incl. Single Unit Test for Trainset #034 DM2 (1st Track) | 24/04/2025 | 24/04/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 494 | 94810358_494
A206230 | TT_Task | Final Assembly incl. Single Unit Test for Trainset #034 T (1st Track) | 29/04/2025 | 29/04/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 495 | 94810358_495
A206130 | TT_Task | Preliminary Takeover Inspection for Trainset #034 (regardless Swedish Breaks) | 06/06/2025 | 03/07/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 496 | 94810358_496
A206260 | TT_Task | Final Assembly for Trainset #035 DM1 | 03/12/2021 | 29/03/2022 | nan | nan | 0 | TK_NotStart | 94810358 | 350 | 94810358_350
A206280 | TT_Task | Final Assembly for Trainset #035 DM2 | 10/12/2021 | 19/04/2022 | nan | nan | 0 | TK_NotStart | 94810358 | 351 | 94810358_351
A206290 | TT_Task | Final Assembly for Trainset #035 T | 17/12/2021 | 26/04/2022 | nan | nan | 6104 | TK_NotStart | 94810358 | 352 | 94810358_352
A206270 | TT_Task | Transport Carbody to Vasteras for Trainset #035 DM1 (8 weeks @ 7d/wk for Sea Freight) | 07/03/2025 | 01/05/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 489 | 94810358_489
A206300 | TT_Task | Transport Carbody to Vasteras for Trainset #035 T (8 weeks @ 7d/wk for Sea Freight) | 17/03/2025 | 11/05/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 490 | 94810358_490
A206310 | TT_Task | Transport Carbody to Vasteras for Trainset #035 DM2 (8 weeks @ 7d/wl for Sea Freight) | 12/03/2025 | 06/05/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 491 | 94810358_491
A206250 | TT_Task | Train Completion incl. Comissioning (2nd Track) and HP4 for Trainset #035 | 23/05/2025 | 16/06/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 492 | 94810358_492
A206320 | TT_Task | Final Assembly incl. Single Unit Test for Trainset #035 DM1 (1st Track) | 02/05/2025 | 02/05/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 493 | 94810358_493
A206330 | TT_Task | Final Assembly incl. Single Unit Test for Trainset #035 DM2 (1st Track) | 07/05/2025 | 07/05/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 494 | 94810358_494
A206340 | TT_Task | Final Assembly incl. Single Unit Test for Trainset #035 T (1st Track) | 12/05/2025 | 12/05/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 495 | 94810358_495
A206240 | TT_Task | Preliminary Takeover Inspection for Trainset #035 (regardless Swedish Breaks) | 20/06/2025 | 17/07/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 496 | 94810358_496
A206370 | TT_Task | Final Assembly for Trainset #036 DM1 | 03/12/2021 | 29/03/2022 | nan | nan | 0 | TK_NotStart | 94810358 | 350 | 94810358_350
A206390 | TT_Task | Final Assembly for Trainset #036 DM2 | 10/12/2021 | 19/04/2022 | nan | nan | 0 | TK_NotStart | 94810358 | 351 | 94810358_351
A206400 | TT_Task | Final Assembly for Trainset #036 T | 17/12/2021 | 26/04/2022 | nan | nan | 6176 | TK_NotStart | 94810358 | 352 | 94810358_352
A206380 | TT_Task | Transport Carbody to Vasteras for Trainset #036 DM1 (8 weeks @ 7d/wk for Sea Freight) | 20/03/2025 | 14/05/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 489 | 94810358_489
A206410 | TT_Task | Transport Carbody to Vasteras for Trainset #036 T (8 weeks @ 7d/wk for Sea Freight) | 28/03/2025 | 22/05/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 490 | 94810358_490
A206420 | TT_Task | Transport Carbody to Vasteras for Trainset #036 DM2 (8 weeks @ 7d/wl for Sea Freight) | 25/03/2025 | 19/05/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 491 | 94810358_491
A206360 | TT_Task | Train Completion incl. Comissioning (2nd Track) and HP4 for Trainset #036 | 05/06/2025 | 27/06/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 492 | 94810358_492
A206430 | TT_Task | Final Assembly incl. Single Unit Test for Trainset #036 DM1 (1st Track) | 15/05/2025 | 15/05/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 493 | 94810358_493
A206440 | TT_Task | Final Assembly incl. Single Unit Test for Trainset #036 DM2 (1st Track) | 20/05/2025 | 20/05/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 494 | 94810358_494
A206450 | TT_Task | Final Assembly incl. Single Unit Test for Trainset #036 T (1st Track) | 23/05/2025 | 23/05/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 495 | 94810358_495
A206350 | TT_Task | Preliminary Takeover Inspection for Trainset #036 (regardless Swedish Breaks) | 04/07/2025 | 31/07/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 496 | 94810358_496
A206480 | TT_Task | Final Assembly for Trainset #037 DM1 | 03/12/2021 | 29/03/2022 | nan | nan | 0 | TK_NotStart | 94810358 | 350 | 94810358_350
A206500 | TT_Task | Final Assembly for Trainset #037 DM2 | 10/12/2021 | 19/04/2022 | nan | nan | 0 | TK_NotStart | 94810358 | 351 | 94810358_351
A206510 | TT_Task | Final Assembly for Trainset #037 T | 17/12/2021 | 26/04/2022 | nan | nan | 6248 | TK_NotStart | 94810358 | 352 | 94810358_352
A206490 | TT_Task | Transport Carbody to Vasteras for Trainset #037 DM1 (8 weeks @ 7d/wk for Sea Freight) | 02/04/2025 | 27/05/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 489 | 94810358_489
A206520 | TT_Task | Transport Carbody to Vasteras for Trainset #037 T (8 weeks @ 7d/wk for Sea Freight) | 10/04/2025 | 04/06/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 490 | 94810358_490
A206530 | TT_Task | Transport Carbody to Vasteras for Trainset #037 DM2 (8 weeks @ 7d/wl for Sea Freight) | 07/04/2025 | 01/06/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 491 | 94810358_491
A206470 | TT_Task | Train Completion incl. Comissioning (2nd Track) and HP4 for Trainset #037 | 18/06/2025 | 10/07/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 492 | 94810358_492
A206540 | TT_Task | Final Assembly incl. Single Unit Test for Trainset #037 DM1 (1st Track) | 28/05/2025 | 28/05/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 493 | 94810358_493
A206550 | TT_Task | Final Assembly incl. Single Unit Test for Trainset #037 DM2 (1st Track) | 02/06/2025 | 02/06/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 494 | 94810358_494
A206560 | TT_Task | Final Assembly incl. Single Unit Test for Trainset #037 T (1st Track) | 05/06/2025 | 05/06/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 495 | 94810358_495
A206460 | TT_Task | Preliminary Takeover Inspection for Trainset #037 (regardless Swedish Breaks) | 18/07/2025 | 14/08/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 496 | 94810358_496
A206590 | TT_Task | Final Assembly for Trainset #038 DM1 | 03/12/2021 | 29/03/2022 | nan | nan | 0 | TK_NotStart | 94810358 | 350 | 94810358_350
A206610 | TT_Task | Final Assembly for Trainset #038 DM2 | 10/12/2021 | 19/04/2022 | nan | nan | 0 | TK_NotStart | 94810358 | 351 | 94810358_351
A206620 | TT_Task | Final Assembly for Trainset #038 T | 17/12/2021 | 26/04/2022 | nan | nan | 6320 | TK_NotStart | 94810358 | 352 | 94810358_352
A206600 | TT_Task | Transport Carbody to Vasteras for Trainset #038 DM1 (8 weeks @ 7d/wk for Sea Freight) | 15/04/2025 | 09/06/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 489 | 94810358_489
A206630 | TT_Task | Transport Carbody to Vasteras for Trainset #038 T (8 weeks @ 7d/wk for Sea Freight) | 23/04/2025 | 17/06/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 490 | 94810358_490
A206640 | TT_Task | Transport Carbody to Vasteras for Trainset #038 DM2 (8 weeks @ 7d/wl for Sea Freight) | 18/04/2025 | 12/06/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 491 | 94810358_491
A206580 | TT_Task | Train Completion incl. Comissioning (2nd Track) and HP4 for Trainset #038 | 01/07/2025 | 23/07/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 492 | 94810358_492
A206650 | TT_Task | Final Assembly incl. Single Unit Test for Trainset #038 DM1 (1st Track) | 10/06/2025 | 10/06/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 493 | 94810358_493
A206660 | TT_Task | Final Assembly incl. Single Unit Test for Trainset #038 DM2 (1st Track) | 13/06/2025 | 13/06/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 494 | 94810358_494
A206670 | TT_Task | Final Assembly incl. Single Unit Test for Trainset #038 T (1st Track) | 18/06/2025 | 18/06/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 495 | 94810358_495
A206570 | TT_Task | Preliminary Takeover Inspection for Trainset #038 (regardless Swedish Breaks) | 01/08/2025 | 28/08/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 496 | 94810358_496
A206700 | TT_Task | Final Assembly for Trainset #039 DM1 | 03/12/2021 | 29/03/2022 | nan | nan | 0 | TK_NotStart | 94810358 | 350 | 94810358_350
A206720 | TT_Task | Final Assembly for Trainset #039 DM2 | 10/12/2021 | 19/04/2022 | nan | nan | 0 | TK_NotStart | 94810358 | 351 | 94810358_351
A206730 | TT_Task | Final Assembly for Trainset #039 T | 17/12/2021 | 26/04/2022 | nan | nan | 6392 | TK_NotStart | 94810358 | 352 | 94810358_352
A206710 | TT_Task | Transport Carbody to Vasteras for Trainset #039 DM1 (8 weeks @ 7d/wk for Sea Freight) | 28/04/2025 | 22/06/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 489 | 94810358_489
A206740 | TT_Task | Transport Carbody to Vasteras for Trainset #039 T (8 weeks @ 7d/wk for Sea Freight) | 06/05/2025 | 30/06/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 490 | 94810358_490
A206750 | TT_Task | Transport Carbody to Vasteras for Trainset #039 DM2 (8 weeks @ 7d/wl for Sea Freight) | 01/05/2025 | 25/06/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 491 | 94810358_491
A206690 | TT_Task | Train Completion incl. Comissioning (2nd Track) and HP4 for Trainset #039 | 14/07/2025 | 05/08/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 492 | 94810358_492
A206760 | TT_Task | Final Assembly incl. Single Unit Test for Trainset #039 DM1 (1st Track) | 23/06/2025 | 23/06/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 493 | 94810358_493
A206770 | TT_Task | Final Assembly incl. Single Unit Test for Trainset #039 DM2 (1st Track) | 26/06/2025 | 26/06/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 494 | 94810358_494
A206780 | TT_Task | Final Assembly incl. Single Unit Test for Trainset #039 T (1st Track) | 01/07/2025 | 01/07/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 495 | 94810358_495
A206680 | TT_Task | Preliminary Takeover Inspection for Trainset #039 (regardless Swedish Breaks) | 15/08/2025 | 11/09/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 496 | 94810358_496
A206810 | TT_Task | Final Assembly for Trainset #040 DM1 | 03/12/2021 | 29/03/2022 | nan | nan | 0 | TK_NotStart | 94810358 | 456 | 94810358_456
A206830 | TT_Task | Final Assembly for Trainset #040 DM2 | 10/12/2021 | 19/04/2022 | nan | nan | 0 | TK_NotStart | 94810358 | 457 | 94810358_457
A206840 | TT_Task | Final Assembly for Trainset #040 T | 17/12/2021 | 26/04/2022 | nan | nan | 6464 | TK_NotStart | 94810358 | 458 | 94810358_458
A206820 | TT_Task | Transport Carbody to Vasteras for Trainset #040 DM1 (8 weeks @ 7d/wk for Sea Freight) | 09/05/2025 | 03/07/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 489 | 94810358_489
A206850 | TT_Task | Transport Carbody to Vasteras for Trainset #040 T (8 weeks @ 7d/wk for Sea Freight) | 19/05/2025 | 13/07/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 490 | 94810358_490
A206860 | TT_Task | Transport Carbody to Vasteras for Trainset #040 DM2 (8 weeks @ 7d/wl for Sea Freight) | 14/05/2025 | 08/07/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 491 | 94810358_491
A206800 | TT_Task | Train Completion incl. Comissioning (2nd Track) and HP4 for Trainset #040 | 25/07/2025 | 18/08/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 492 | 94810358_492
A206870 | TT_Task | Final Assembly incl. Single Unit Test for Trainset #040 DM1 (1st Track) | 04/07/2025 | 04/07/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 493 | 94810358_493
A206880 | TT_Task | Final Assembly incl. Single Unit Test for Trainset #040 DM2 (1st Track) | 09/07/2025 | 09/07/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 494 | 94810358_494
A206890 | TT_Task | Final Assembly incl. Single Unit Test for Trainset #040 T (1st Track) | 14/07/2025 | 14/07/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 495 | 94810358_495
A206790 | TT_Task | Preliminary Takeover Inspection for Trainset #040 (regardless Swedish Breaks) | 29/08/2025 | 25/09/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 496 | 94810358_496
A206920 | TT_Task | Final Assembly for Trainset #041 DM1 | 03/12/2021 | 29/03/2022 | nan | nan | 0 | TK_NotStart | 94810358 | 456 | 94810358_456
A206940 | TT_Task | Final Assembly for Trainset #041 DM2 | 10/12/2021 | 19/04/2022 | nan | nan | 0 | TK_NotStart | 94810358 | 457 | 94810358_457
A206950 | TT_Task | Final Assembly for Trainset #041 T | 17/12/2021 | 26/04/2022 | nan | nan | 6536 | TK_NotStart | 94810358 | 458 | 94810358_458
A206930 | TT_Task | Transport Carbody to Vasteras for Trainset #041 DM1 (8 weeks @ 7d/wk for Sea Freight) | 22/05/2025 | 16/07/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 489 | 94810358_489
A206960 | TT_Task | Transport Carbody to Vasteras for Trainset #041 T (8 weeks @ 7d/wk for Sea Freight) | 30/05/2025 | 24/07/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 490 | 94810358_490
A206970 | TT_Task | Transport Carbody to Vasteras for Trainset #041 DM2 (8 weeks @ 7d/wl for Sea Freight) | 27/05/2025 | 21/07/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 491 | 94810358_491
A206910 | TT_Task | Train Completion incl. Comissioning (2nd Track) and HP4 for Trainset #041 | 07/08/2025 | 29/08/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 492 | 94810358_492
A206980 | TT_Task | Final Assembly incl. Single Unit Test for Trainset #041 DM1 (1st Track) | 17/07/2025 | 17/07/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 493 | 94810358_493
A206990 | TT_Task | Final Assembly incl. Single Unit Test for Trainset #041 DM2 (1st Track) | 22/07/2025 | 22/07/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 494 | 94810358_494
A207000 | TT_Task | Final Assembly incl. Single Unit Test for Trainset #041 T (1st Track) | 25/07/2025 | 25/07/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 495 | 94810358_495
A206900 | TT_Task | Preliminary Takeover Inspection for Trainset #041 (regardless Swedish Breaks) | 12/09/2025 | 09/10/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 496 | 94810358_496
A207030 | TT_Task | Final Assembly for Trainset #042 DM1 | 03/12/2021 | 29/03/2022 | nan | nan | 0 | TK_NotStart | 94810358 | 456 | 94810358_456
A207050 | TT_Task | Final Assembly for Trainset #042 DM2 | 10/12/2021 | 19/04/2022 | nan | nan | 0 | TK_NotStart | 94810358 | 457 | 94810358_457
A207060 | TT_Task | Final Assembly for Trainset #042 T | 17/12/2021 | 26/04/2022 | nan | nan | 6608 | TK_NotStart | 94810358 | 458 | 94810358_458
A207040 | TT_Task | Transport Carbody to Vasteras for Trainset #042 DM1 (8 weeks @ 7d/wk for Sea Freight) | 04/06/2025 | 29/07/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 489 | 94810358_489
A207070 | TT_Task | Transport Carbody to Vasteras for Trainset #042 T (8 weeks @ 7d/wk for Sea Freight) | 12/06/2025 | 06/08/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 490 | 94810358_490
A207080 | TT_Task | Transport Carbody to Vasteras for Trainset #042 DM2 (8 weeks @ 7d/wl for Sea Freight) | 09/06/2025 | 03/08/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 491 | 94810358_491
A207020 | TT_Task | Train Completion incl. Comissioning (2nd Track) and HP4 for Trainset #042 | 20/08/2025 | 11/09/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 492 | 94810358_492
A207090 | TT_Task | Final Assembly incl. Single Unit Test for Trainset #042 DM1 (1st Track) | 30/07/2025 | 30/07/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 493 | 94810358_493
A207100 | TT_Task | Final Assembly incl. Single Unit Test for Trainset #042 DM2 (1st Track) | 04/08/2025 | 04/08/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 494 | 94810358_494
A207110 | TT_Task | Final Assembly incl. Single Unit Test for Trainset #042 T (1st Track) | 07/08/2025 | 07/08/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 495 | 94810358_495
A207010 | TT_Task | Preliminary Takeover Inspection for Trainset #042 (regardless Swedish Breaks) | 26/09/2025 | 23/10/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 496 | 94810358_496
A207140 | TT_Task | Final Assembly for Trainset #043 DM1 | 03/12/2021 | 29/03/2022 | nan | nan | 0 | TK_NotStart | 94810358 | 456 | 94810358_456
A207160 | TT_Task | Final Assembly for Trainset #043 DM2 | 10/12/2021 | 19/04/2022 | nan | nan | 0 | TK_NotStart | 94810358 | 457 | 94810358_457
A207170 | TT_Task | Final Assembly for Trainset #043 T | 17/12/2021 | 26/04/2022 | nan | nan | 6696 | TK_NotStart | 94810358 | 458 | 94810358_458
A207150 | TT_Task | Transport Carbody to Vasteras for Trainset #043 DM1 (8 weeks @ 7d/wk for Sea Freight) | 17/06/2025 | 11/08/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 489 | 94810358_489
A207180 | TT_Task | Transport Carbody to Vasteras for Trainset #043 T (8 weeks @ 7d/wk for Sea Freight) | 27/06/2025 | 21/08/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 490 | 94810358_490
A207190 | TT_Task | Transport Carbody to Vasteras for Trainset #043 DM2 (8 weeks @ 7d/wl for Sea Freight) | 23/06/2025 | 17/08/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 491 | 94810358_491
A207130 | TT_Task | Train Completion incl. Comissioning (2nd Track) and HP4 for Trainset #043 | 02/09/2025 | 24/09/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 492 | 94810358_492
A207200 | TT_Task | Final Assembly incl. Single Unit Test for Trainset #043 DM1 (1st Track) | 12/08/2025 | 12/08/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 493 | 94810358_493
A207210 | TT_Task | Final Assembly incl. Single Unit Test for Trainset #043 DM2 (1st Track) | 18/08/2025 | 18/08/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 494 | 94810358_494
A207220 | TT_Task | Final Assembly incl. Single Unit Test for Trainset #043 T (1st Track) | 22/08/2025 | 22/08/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 495 | 94810358_495
A207120 | TT_Task | Preliminary Takeover Inspection for Trainset #043 (regardless Swedish Breaks) | 10/10/2025 | 06/11/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 496 | 94810358_496
A207250 | TT_Task | Final Assembly for Trainset #044 DM1 | 03/12/2021 | 29/03/2022 | nan | nan | 0 | TK_NotStart | 94810358 | 456 | 94810358_456
A207270 | TT_Task | Final Assembly for Trainset #044 DM2 | 10/12/2021 | 19/04/2022 | nan | nan | 0 | TK_NotStart | 94810358 | 457 | 94810358_457
A207280 | TT_Task | Final Assembly for Trainset #044 T | 17/12/2021 | 26/04/2022 | nan | nan | 6808 | TK_NotStart | 94810358 | 458 | 94810358_458
A207260 | TT_Task | Transport Carbody to Vasteras for Trainset #044 DM1 (8 weeks @ 7d/wk for Sea Freight) | 03/07/2025 | 27/08/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 489 | 94810358_489
A207290 | TT_Task | Transport Carbody to Vasteras for Trainset #044 T (8 weeks @ 7d/wk for Sea Freight) | 17/07/2025 | 10/09/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 490 | 94810358_490
A207300 | TT_Task | Transport Carbody to Vasteras for Trainset #044 DM2 (8 weeks @ 7d/wl for Sea Freight) | 10/07/2025 | 03/09/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 491 | 94810358_491
A207240 | TT_Task | Train Completion incl. Comissioning (2nd Track) and HP4 for Trainset #044 | 18/09/2025 | 10/10/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 492 | 94810358_492
A207310 | TT_Task | Final Assembly incl. Single Unit Test for Trainset #044 DM1 (1st Track) | 28/08/2025 | 28/08/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 493 | 94810358_493
A207320 | TT_Task | Final Assembly incl. Single Unit Test for Trainset #044 DM2 (1st Track) | 04/09/2025 | 04/09/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 494 | 94810358_494
A207330 | TT_Task | Final Assembly incl. Single Unit Test for Trainset #044 T (1st Track) | 11/09/2025 | 11/09/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 495 | 94810358_495
A207230 | TT_Task | Preliminary Takeover Inspection for Trainset #044 (regardless Swedish Breaks) | 24/10/2025 | 20/11/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 496 | 94810358_496
A207360 | TT_Task | Final Assembly for Trainset #045 DM1 | 03/12/2021 | 29/03/2022 | nan | nan | 0 | TK_NotStart | 94810358 | 456 | 94810358_456
A207380 | TT_Task | Final Assembly for Trainset #045 DM2 | 10/12/2021 | 19/04/2022 | nan | nan | 0 | TK_NotStart | 94810358 | 457 | 94810358_457
A207390 | TT_Task | Final Assembly for Trainset #045 T | 17/12/2021 | 26/04/2022 | nan | nan | 6928 | TK_NotStart | 94810358 | 458 | 94810358_458
A207370 | TT_Task | Transport Carbody to Vasteras for Trainset #045 DM1 (8 weeks @ 7d/wk for Sea Freight) | 24/07/2025 | 17/09/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 489 | 94810358_489
A207400 | TT_Task | Transport Carbody to Vasteras for Trainset #045 T (8 weeks @ 7d/wk for Sea Freight) | 07/08/2025 | 01/10/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 490 | 94810358_490
A207410 | TT_Task | Transport Carbody to Vasteras for Trainset #045 DM2 (8 weeks @ 7d/wl for Sea Freight) | 31/07/2025 | 24/09/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 491 | 94810358_491
A207350 | TT_Task | Train Completion incl. Comissioning (2nd Track) and HP4 for Trainset #045 | 09/10/2025 | 31/10/2025 | nan | nan | 64 | TK_NotStart | 94810358 | 492 | 94810358_492
A207420 | TT_Task | Final Assembly incl. Single Unit Test for Trainset #045 DM1 (1st Track) | 18/09/2025 | 18/09/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 493 | 94810358_493
A207430 | TT_Task | Final Assembly incl. Single Unit Test for Trainset #045 DM2 (1st Track) | 25/09/2025 | 25/09/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 494 | 94810358_494
A207440 | TT_Task | Final Assembly incl. Single Unit Test for Trainset #045 T (1st Track) | 02/10/2025 | 02/10/2025 | nan | nan | 0 | TK_NotStart | 94810358 | 495 | 94810358_495
A207340 | TT_Task | Preliminary Takeover Inspection for Trainset #045 (regardless Swedish Breaks) | 11/11/2025 | 08/12/2025 | nan | nan | 200 | TK_NotStart | 94810358 | 496 | 94810358_496
A157130 | TT_Task | Validation Lead Time of the Actual LCC Values (NOT USED) | 28/01/2026 | 23/01/2027 | nan | nan | 0 | TK_NotStart | 94810358 | 497 | 94810358_497
A185870 | TT_Task | Validation Lead Time of the Actual Reliability Validation (NOT USED) | 10/07/2023 | 04/07/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 498 | 94810358_498
A186370 | TT_Task | Final RAM/ LCC Validation (Test Operation - At least 5 Trainsets PTO and 2,000,000km and minimum 14 Calendar Months) | 18/07/2024 | 02/07/2027 | nan | nan | 0 | TK_NotStart | 94810358 | 499 | 94810358_499
A157500 | TT_Task | Warranty Period of the Last Train for Integrated Logistic Support (NOT USED) | 28/01/2026 | 22/07/2026 | nan | nan | 0 | TK_NotStart | 94810358 | 500 | 94810358_500
A185635 | TT_Task | Supplier Documentation Reviews (NOT USED) | 13/11/2020 | 05/12/2022 | 06/01/2020 | 05/07/2020 | 0 | TK_Complete | 94810358 | 501 | 94810358_501
A185640 | TT_Task | Batch 1 Mapping, Production, Review, Verification, Validation and Translation | 13/11/2020 | 16/11/2022 | 17/12/2019 | nan | 0 | TK_Active | 94810358 | 502 | 94810358_502
A185660 | TT_Task | Batch 2 Mapping, Production, Review, Verification, Validation and Translation | 08/06/2021 | 09/06/2023 | 18/05/2020 | nan | 0 | TK_Active | 94810358 | 502 | 94810358_502
A185680 | TT_Task | Batch 3 Mapping, Production, Review, Verification, Validation and Translation | 03/01/2022 | 04/01/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 502 | 94810358_502
A185700 | TT_Task | Batch 4 Mapping, Production, Review, Verification, Validation and Translation | 03/01/2022 | 04/01/2024 | nan | nan | 0 | TK_NotStart | 94810358 | 502 | 94810358_502
A185750 | TT_Task | Training Period of Orienteringskurs incl. Production, Review and Execution (Indicative end date) | 22/04/2021 | 12/05/2023 | 01/03/2021 | nan | 0 | TK_Active | 94810358 | 503 | 94810358_503
A185760 | TT_Task | Training Period of Specialutbildning incl. Production, Review and Execution (Indicative end date) | 02/05/2022 | 21/05/2024 | nan | nan | 14440 | TK_NotStart | 94810358 | 504 | 94810358_504
A185770 | TT_Task | Training Period of F?rdjupad teknik och underh?llsutbildning incl. Production, Review and Execution (Ind. end date) | 01/06/2023 | 20/06/2025 | nan | nan | 10288 | TK_NotStart | 94810358 | 505 | 94810358_505
A185780 | TT_Task | Training Period of Grundutbildning incl. Production, Review and Execution (Indicative end date) | 03/01/2022 | 23/01/2024 | nan | nan | 14560 | TK_NotStart | 94810358 | 504 | 94810358_504
A185790 | TT_Task | Training Period of TrainMate incl. Production, Review and Execution (Indicative end date) | 03/01/2022 | 23/01/2024 | nan | nan | 13400 | TK_NotStart | 94810358 | 506 | 94810358_506
A185800 | TT_Task | Training Period of Utbildning f?r erfarenhets?verf?ring incl. Production, Review and Execution (Indicative end date) | 01/12/2027 | 20/12/2029 | nan | nan | 3280 | TK_NotStart | 94810358 | 507 | 94810358_507
A185810 | TT_Task | Training Period of F?rdjupad ?versiktsutbildning incl. Production and Review (Indicative end date) | 01/03/2022 | 20/03/2024 | nan | nan | 13696 | TK_NotStart | 94810358 | 508 | 94810358_508
A185820 | TT_Task | Training Period of F?rdjupande teknisk utbildning incl. Production and Review (Indicative end date) | 01/02/2022 | 21/02/2024 | nan | nan | 13816 | TK_NotStart | 94810358 | 508 | 94810358_508
A185830 | TT_Task | Training Period of F?rarutbildning incl. Production and Review (Indicative end date) | 04/01/2022 | 24/01/2024 | nan | nan | 13976 | TK_NotStart | 94810358 | 509 | 94810358_509
A185840 | TT_Task | Training Period of Utbildning f?r ombordpersonal incl. Production and Review (Indicative end date) | 04/01/2022 | 24/01/2024 | nan | nan | 13936 | TK_NotStart | 94810358 | 509 | 94810358_509
A185850 | TT_Task | Training Period of Rangerutbildning incl. Production and Review (Indicative end date) | 04/01/2022 | 24/01/2024 | nan | nan | 14056 | TK_NotStart | 94810358 | 510 | 94810358_510
A185860 | TT_Task | Training Period of St?dutbildning incl. Production and Review (Indicative end date) | 04/01/2022 | 24/01/2024 | nan | nan | 13856 | TK_NotStart | 94810358 | 509 | 94810358_509
A185730 | TT_Task | Mapping, Development and Test of Trainmate (VTM Functions) | 24/09/2021 | 27/09/2023 | 23/09/2021 | nan | 0 | TK_Active | 94810358 | 511 | 94810358_511
A157460 | TT_Task | Set-up Phase for Warranty Site | 14/04/2023 | 14/07/2023 | nan | nan | 13120 | TK_NotStart | 94810358 | 512 | 94810358_512
A157480 | TT_Task | Warranty Period of the Last Train | 28/01/2026 | 22/07/2026 | nan | nan | 0 | TK_NotStart | 94810358 | 513 | 94810358_513
A157350 | TT_Task | Set-up Phase for Field Technical Support (NOT USED) | 10/08/2023 | 09/11/2023 | nan | nan | 12976 | TK_NotStart | 94810358 | 514 | 94810358_514
A157450 | TT_Task | Warranty Period of the Last Train for Field Technical Support (NOT USED) | 28/01/2026 | 22/07/2026 | nan | nan | 0 | TK_NotStart | 94810358 | 513 | 94810358_513
A236630 | TT_Task | GR3 Self-Assessment | 13/05/2020 | 02/06/2020 | 09/04/2020 | 09/04/2020 | 0 | TK_Complete | 1201082599 | 1 | 1201082599_1
A236640 | TT_Task | GR4 Self-Assessment | 06/05/2020 | 26/05/2020 | 06/05/2020 | 26/05/2020 | 0 | TK_Complete | 1201082599 | 1 | 1201082599_1
A236680 | TT_Task | GR5 Self-Assessment | 11/09/2020 | 11/09/2020 | 11/09/2020 | 11/09/2020 | 0 | TK_Complete | 1201082599 | 1 | 1201082599_1
A236660 | TT_Task | GR6 Self-Assessment | 24/05/2021 | 04/06/2021 | 24/05/2021 | 04/06/2021 | 0 | TK_Complete | 1201082599 | 1 | 1201082599_1
A236670 | TT_Task | GR7 Self-Assessment | 30/09/2022 | 13/10/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 1 | 1201082599_1
COVID - 00243 | TT_Task | COVID - 00243 - First notification towards Customer regarding Covid-19 (HVAC system delivery) | 21/07/2020 | 21/07/2020 | 21/07/2020 | 21/07/2020 | 0 | TK_Complete | 1201082599 | 2 | 1201082599_2
COVID - 00244 | TT_Task | COVID - 00244 - First notification towards Customer regarding Covid-19 (couplers system delivery) | 16/03/2020 | 30/10/2020 | 16/03/2020 | 30/10/2020 | 0 | TK_Complete | 1201082599 | 2 | 1201082599_2
COVID - 00245 | TT_Task | COVID - 00245 - Impact on BTA manufacturing site (Extended Duration Innenausbau) | 01/01/2018 | 08/01/2018 | 24/03/2020 | 24/03/2020 | 0 | TK_Complete | 1201082599 | 3 | 1201082599_3
COVID - 00247 | TT_Task | COVID - 00247 - Travel restrictions (delayed Customer FAI) End Portal | 24/03/2020 | 21/04/2020 | 24/03/2020 | 21/04/2020 | 0 | TK_Complete | 1201082599 | 4 | 1201082599_4
COVID - 00249 | TT_Task | COVID - 00249 - Travel restrictions (delayed Customer FAI) Underframe | 26/03/2020 | 22/04/2020 | 26/03/2020 | 22/04/2020 | 0 | TK_Complete | 1201082599 | 4 | 1201082599_4
COVID - 00250 | TT_Task | COVID - 00250 - BT G?rlitz Covid-19 impact (intercompany supply of carbody end portal delayed) | 01/07/2020 | 13/07/2020 | 01/07/2020 | 13/07/2020 | 0 | TK_Complete | 1201082599 | 5 | 1201082599_5
COVID - 00251 | TT_Task | COVID - 00251 - Border closings lead to capacity problem (welding of side walls delayed) | 15/03/2020 | 18/03/2020 | 15/03/2020 | 18/03/2020 | 0 | TK_Complete | 1201082599 | 6 | 1201082599_6
COVID - 00252 | TT_Task | COVID - 00252 - White Colar Workers Lost Time (Engineering and Procurement IT Problems) | 24/03/2020 | 30/03/2020 | 24/03/2020 | 30/03/2020 | 0 | TK_Complete | 1201082599 | 7 | 1201082599_7
COVID - 00253 | TT_Task | COVID - 00253 - TDG annouced Force Majeure to BT | 17/08/2020 | 11/09/2020 | 17/08/2020 | 11/09/2020 | 0 | TK_Complete | 1201082599 | 8 | 1201082599_8
COVID - 00254 | TT_Task | COVID - 00254 - KTP annouced of Force Majeure to BT (potential impact on cable harnesses, cabling) | 04/05/2020 | 18/05/2020 | 04/05/2020 | 18/05/2020 | 0 | TK_Complete | 1201082599 | 9 | 1201082599_9
COVID - 00322 | TT_Task | COVID - 00322 - Covid-19 impact from Brno in CZ (delayed delivery of passenger doors) | 28/07/2020 | 23/09/2020 | 28/07/2020 | 23/09/2020 | 0 | TK_Complete | 1201082599 | 10 | 1201082599_10
COVID - 00347 | TT_Task | COVID - 00347 - Boarder closing lead to capacity problem (welding of side walls delayed) | 24/03/2020 | 27/03/2020 | 24/03/2020 | 27/03/2020 | 0 | TK_Complete | 1201082599 | 6 | 1201082599_6
COVID - 00348 | TT_Task | COVID - 00348 - Covid-19 impact on white collar workers (productivity) | 17/08/2020 | 26/09/2020 | 17/08/2020 | 26/09/2020 | 0 | TK_Complete | 1201082599 | 11 | 1201082599_11
COVID - 00349 | TT_Task | COVID - 00349 - R2P announced Force Majeure to BT (Rear View System) | 04/05/2020 | 01/08/2020 | 04/05/2020 | 01/08/2020 | 0 | TK_Complete | 1201082599 | 12 | 1201082599_12
COVID - 00350 | TT_Task | COVID - 00350 - R2P announced Force Majeure to BT (CCTV) | 17/05/2020 | 31/07/2020 | 17/05/2020 | 31/07/2020 | 0 | TK_Complete | 1201082599 | 12 | 1201082599_12
COVID - 00371 | TT_Task | COVID - 00371 -Covid impact white collar workers (Extention of Duration BBI due to productivity loss ) | 01/01/2018 | 30/07/2020 | 23/03/2020 | 30/07/2020 | 0 | TK_Complete | 1201082599 | 11 | 1201082599_11
COVID - XXXXX | TT_Task | COVID -XXXXX - Late start acc. A3 | 28/08/2020 | 12/10/2020 | 28/08/2020 | 12/10/2020 | 0 | TK_Complete | 1201082599 | 13 | 1201082599_13
COVID - XXXXX10 | TT_Task | COVID -XXXXX - Late start acc. A3 | 28/08/2020 | 18/10/2020 | 28/08/2020 | 18/10/2020 | 0 | TK_Complete | 1201082599 | 13 | 1201082599_13
COVID - XXXXX20 | TT_Task | COVID -XXXXX - Late start acc. A3 | 28/08/2020 | 12/10/2020 | 28/08/2020 | 12/10/2020 | 0 | TK_Complete | 1201082599 | 13 | 1201082599_13
COVID - XXXXX30 | TT_Task | COVID -XXXXX - Late start acc. A3 | 28/08/2020 | 12/10/2020 | 28/08/2020 | 12/10/2020 | 0 | TK_Complete | 1201082599 | 13 | 1201082599_13
PROC105100 | TT_Task | Carbody shell (Kopf Rohbau) - Supplier Selection and PO Placement | 13/12/2019 | 06/02/2020 | 13/12/2019 | 10/02/2020 | 0 | TK_Complete | 1201082599 | 14 | 1201082599_14
PROC105120 | TT_Task | Carbody shell (Kopf Rohbau) - Supplier Lead Time | 10/02/2020 | 10/07/2020 | 10/02/2020 | 04/08/2020 | 0 | TK_Complete | 1201082599 | 15 | 1201082599_15
PROC105280 | TT_Task | Buffers (Puffer / Crash Absorber) - Supplier Selection and PO Placement | 20/12/2019 | 13/02/2020 | 20/12/2019 | 16/03/2020 | 0 | TK_Complete | 1201082599 | 16 | 1201082599_16
PROC105300 | TT_Task | Buffers (Puffer / Crash Absorber) - Supplier Lead Time | 16/03/2020 | 31/07/2020 | 16/03/2020 | 03/12/2020 | 0 | TK_Complete | 1201082599 | 17 | 1201082599_17
PROC105640 | TT_Task | Body skirts (Fahrzeugsch?rzen) - Supplier Selection and PO Placement | 16/04/2020 | 10/06/2020 | 16/04/2020 | 05/08/2020 | 0 | TK_Complete | 1201082599 | 18 | 1201082599_18
PROC105660 | TT_Task | Body skirts (Fahrzeugsch?rzen) - Supplier Lead Time | 05/08/2020 | 11/01/2021 | 05/08/2020 | nan | 0 | TK_Active | 1201082599 | 18 | 1201082599_18
PROC105880 | TT_Task | Roof spoiler (Dachblenden) - Supplier Selection and PO Placement | 16/04/2020 | 10/06/2020 | 16/04/2020 | 15/05/2020 | 0 | TK_Complete | 1201082599 | 19 | 1201082599_19
PROC105900 | TT_Task | Roof spoiler (Dachblenden) - Supplier Lead Time | 15/05/2020 | 17/09/2020 | 15/05/2020 | 09/11/2020 | 0 | TK_Complete | 1201082599 | 19 | 1201082599_19
PROC105700 | TT_Task | Polyester front end (Scheinwerfertr?ger GFK - unlack.) - Supplier Selection and PO Placement | 09/03/2020 | 01/05/2020 | 09/03/2020 | 27/03/2020 | 0 | TK_Complete | 1201082599 | 20 | 1201082599_20
PROC105720 | TT_Task | Polyester front end (Scheinwerfertr?ger GFK - unlack.) - Supplier Lead Time | 27/03/2020 | 06/08/2020 | 27/03/2020 | 24/07/2020 | 0 | TK_Complete | 1201082599 | 21 | 1201082599_21
PROC105760 | TT_Task | Polyester front end (GFK Aussenverkl. Cab unlack.) - Supplier Selection and PO Placement | 19/02/2020 | 14/04/2020 | 19/02/2020 | 27/03/2020 | 0 | TK_Complete | 1201082599 | 20 | 1201082599_20
PROC105780 | TT_Task | Polyester front end (GFK Aussenverkl. Cab unlack.) - Supplier Lead Time | 27/03/2020 | 06/08/2020 | 27/03/2020 | 24/07/2020 | 0 | TK_Complete | 1201082599 | 21 | 1201082599_21
PROC105820 | TT_Task | Polyester front end (Kupplungsabdeckung unlack.) - Supplier Selection and PO Placement | 09/03/2020 | 01/05/2020 | 09/03/2020 | 27/03/2020 | 0 | TK_Complete | 1201082599 | 20 | 1201082599_20
PROC105840 | TT_Task | Polyester front end (Kupplungsabdeckung unlack.) - Supplier Lead Time | 27/03/2020 | 06/08/2020 | 27/03/2020 | 24/07/2020 | 0 | TK_Complete | 1201082599 | 21 | 1201082599_21
PROC105400 | TT_Task | Side windows (Seitenscheiben) - Supplier Selection and PO Placement | 19/03/2020 | 13/05/2020 | 19/03/2020 | 25/06/2020 | 0 | TK_Complete | 1201082599 | 22 | 1201082599_22
PROC105420 | TT_Task | Side windows (Seitenscheiben) - Supplier Lead Time | 25/06/2020 | 14/10/2020 | 25/06/2020 | 16/10/2020 | 0 | TK_Complete | 1201082599 | 23 | 1201082599_23
PROC105340 | TT_Task | Cab windscreens (Frontscheiben) - Supplier Selection and PO Placement | 12/09/2019 | 06/11/2019 | 12/09/2019 | 11/03/2020 | 0 | TK_Complete | 1201082599 | 24 | 1201082599_24
PROC105360 | TT_Task | Cab windscreens (Frontscheiben) - Supplier Lead Time | 11/03/2020 | 02/06/2020 | 11/03/2020 | 16/10/2020 | 0 | TK_Complete | 1201082599 | 24 | 1201082599_24
PROC106540 | TT_Task | Exterior lights systems (Au?enbeleuchtung) - Supplier Selection and PO Placement | 01/07/2019 | 23/08/2019 | 01/07/2019 | 02/12/2019 | 0 | TK_Complete | 1201082599 | 25 | 1201082599_25
PROC106550 | TT_Task | Exterior lights systems (Au?enbeleuchtung) - BBI Collection from Supplier | 02/12/2019 | 24/01/2020 | 02/12/2019 | 02/12/2019 | 0 | TK_Complete | 1201082599 | 26 | 1201082599_26
PROC106560 | TT_Task | Exterior lights systems (Au?enbeleuchtung) - Supplier Lead Time | 02/12/2019 | 17/04/2020 | 02/12/2019 | 20/01/2021 | 0 | TK_Complete | 1201082599 | 27 | 1201082599_27
PROC105220 | TT_Task | Backward mirrors (R?ckspiegelkameras) - Supplier Selection and PO Placement | 20/11/2019 | 14/01/2020 | 20/11/2019 | 27/01/2020 | 0 | TK_Complete | 1201082599 | 28 | 1201082599_28
PROC105230 | TT_Task | Backward mirrors (R?ckspiegelkameras) - BBI Collection from Supplier | 27/01/2020 | 20/03/2020 | 06/02/2020 | 06/02/2020 | 0 | TK_Complete | 1201082599 | 29 | 1201082599_29
PROC105240 | TT_Task | Backward mirrors (R?ckspiegelkameras) - Supplier Lead Time | 27/01/2020 | 17/07/2020 | 27/01/2020 | nan | 0 | TK_Active | 1201082599 | 28 | 1201082599_28
PROC107800 | TT_Task | Passenger door systems (Fahrgastt?ren) - Supplier Selection and PO Placement | 30/03/2020 | 13/05/2020 | 13/08/2019 | 13/05/2020 | 0 | TK_Complete | 1201082599 | 30 | 1201082599_30
PROC107810 | TT_Task | Passenger door systems (Fahrgastt?ren) - BBI Collection from Supplier | 14/05/2020 | 08/07/2020 | 14/05/2020 | 08/07/2020 | 0 | TK_Complete | 1201082599 | 31 | 1201082599_31
PROC107820 | TT_Task | Passenger door systems (Fahrgastt?ren) - Supplier Lead Time | 14/05/2020 | 23/12/2020 | 14/05/2020 | 12/11/2020 | 0 | TK_Complete | 1201082599 | 32 | 1201082599_32
PROC107740 | TT_Task | Driver door systems (Fahrerstandst?r Cab) - Supplier Selection and PO Placement | 10/06/2020 | 04/08/2020 | 26/06/2020 | 02/07/2020 | 0 | TK_Complete | 1201082599 | 30 | 1201082599_30
PROC107760 | TT_Task | Driver door systems (Fahrerstandst?r Cab) - Supplier Lead Time | 02/07/2020 | 18/11/2020 | 02/07/2020 | nan | 0 | TK_Active | 1201082599 | 32 | 1201082599_32
PROC107200 | TT_Task | Ceilings module (Innendecke (FGR) inkl. Vouten ) - Supplier Selection and PO Placement | 14/04/2020 | 08/06/2020 | 14/05/2020 | 15/05/2020 | 0 | TK_Complete | 1201082599 | 33 | 1201082599_33
PROC107220 | TT_Task | Ceilings module (Innendecke (FGR) inkl. Vouten ) - Supplier Lead Time | 15/05/2020 | 17/09/2020 | 15/05/2020 | 08/09/2020 | 0 | TK_Complete | 1201082599 | 34 | 1201082599_34
PROC107320 | TT_Task | Ceilings module (Innendecke FST CM (Vorbaud.)) - Supplier Selection and PO Placement | 09/03/2020 | 01/05/2020 | 09/03/2020 | 18/05/2020 | 0 | TK_Complete | 1201082599 | 33 | 1201082599_33
PROC107340 | TT_Task | Ceilings module (Innendecke FST CM (Vorbaud.)) - Supplier Lead Time | 29/05/2020 | 01/10/2020 | 18/05/2020 | 20/11/2020 | 0 | TK_Complete | 1201082599 | 34 | 1201082599_34
PROC106600 | TT_Task | Interior doors (Fahrerraumtrennwand) - Supplier Selection and PO Placement | 05/03/2020 | 29/04/2020 | 05/03/2020 | 19/06/2020 | 0 | TK_Complete | 1201082599 | 30 | 1201082599_30
PROC106620 | TT_Task | Interior doors (Fahrerraumtrennwand) - Supplier Lead Time | 19/06/2020 | 22/10/2020 | 19/06/2020 | 18/12/2020 | 0 | TK_Complete | 1201082599 | 32 | 1201082599_32
PROC106360 | TT_Task | Floors (Fu?bodenplatten) - Supplier Selection and PO Placement | 20/12/2019 | 13/02/2020 | 20/12/2019 | 11/03/2020 | 0 | TK_Complete | 1201082599 | 35 | 1201082599_35
PROC106380 | TT_Task | Floors (Fu?bodenplatten) - Supplier Lead Time | 11/03/2020 | 30/06/2020 | 11/03/2020 | 16/09/2020 | 0 | TK_Complete | 1201082599 | 36 | 1201082599_36
PROC108160 | TT_Task | Floor Coverings (Fussbodenbelag) - Supplier Selection and PO Placement | 20/02/2019 | 16/04/2019 | 20/02/2019 | 12/02/2020 | 0 | TK_Complete | 1201082599 | 35 | 1201082599_35
PROC108180 | TT_Task | Floor Coverings (Fussbodenbelag) - Supplier Lead Time | 12/02/2020 | 26/05/2020 | 12/02/2020 | 07/09/2020 | 0 | TK_Complete | 1201082599 | 36 | 1201082599_36
PROC107860 | TT_Task | Door ramp systems (Einstiegsrampe) - Supplier Selection and PO Placement | 21/04/2020 | 15/06/2020 | 21/04/2020 | 07/05/2020 | 0 | TK_Complete | 1201082599 | 37 | 1201082599_37
PROC107880 | TT_Task | Door ramp systems (Einstiegsrampe) - Supplier Lead Time | 07/05/2020 | 21/10/2020 | 07/05/2020 | 14/10/2020 | 0 | TK_Complete | 1201082599 | 32 | 1201082599_32
PROC107140 | TT_Task | Sidewall modules (Innenverkleidung GFK) - Supplier Selection and PO Placement | 10/04/2020 | 04/06/2020 | 10/04/2020 | 15/05/2020 | 0 | TK_Complete | 1201082599 | 38 | 1201082599_38
PROC107160 | TT_Task | Sidewall modules (Innenverkleidung GFK) - Supplier Lead Time | 15/05/2020 | 01/10/2020 | 15/05/2020 | 10/12/2020 | 0 | TK_Complete | 1201082599 | 38 | 1201082599_38
PROC108040 | TT_Task | Insulation elements (Isolierung) - Supplier Selection and PO Placement | 13/01/2020 | 06/03/2020 | 13/01/2020 | 02/03/2020 | 0 | TK_Complete | 1201082599 | 39 | 1201082599_39
PROC108060 | TT_Task | Insulation elements (Isolierung) - Supplier Lead Time | 02/03/2020 | 12/06/2020 | 02/03/2020 | 28/08/2020 | 0 | TK_Complete | 1201082599 | 40 | 1201082599_40
PROC106420 | TT_Task | Stanchions (Haltestangen) - Supplier Selection and PO Placement | 06/02/2020 | 01/04/2020 | 06/02/2020 | 08/05/2020 | 0 | TK_Complete | 1201082599 | 41 | 1201082599_41
PROC106440 | TT_Task | Stanchions (Haltestangen) - Supplier Lead Time | 08/05/2020 | 22/10/2020 | 08/05/2020 | 06/10/2020 | 0 | TK_Complete | 1201082599 | 42 | 1201082599_42
PROC107020 | TT_Task | Seats (GFK Sitzkisten) - Supplier Selection and PO Placement | 04/03/2020 | 28/04/2020 | 04/03/2020 | 26/06/2020 | 0 | TK_Complete | 1201082599 | 43 | 1201082599_43
PROC107040 | TT_Task | Seats (GFK Sitzkisten) - Supplier Lead Time | 26/06/2020 | 12/11/2020 | 26/06/2020 | 20/11/2020 | 0 | TK_Complete | 1201082599 | 44 | 1201082599_44
PROC107080 | TT_Task | Seats (Fahrgastsitze) - Supplier Selection and PO Placement | 04/03/2020 | 28/04/2020 | 04/03/2020 | 22/07/2020 | 0 | TK_Complete | 1201082599 | 43 | 1201082599_43
PROC107100 | TT_Task | Seats (Fahrgastsitze) - Supplier Lead Time | 10/07/2020 | 26/11/2020 | 22/07/2020 | 25/01/2021 | 0 | TK_Complete | 1201082599 | 44 | 1201082599_44
PROC106480 | TT_Task | Interior lights systems (Innenbeleuchtung) - Supplier Selection and PO Placement | 10/09/2019 | 04/11/2019 | 10/09/2019 | 02/12/2019 | 0 | TK_Complete | 1201082599 | 25 | 1201082599_25
PROC106500 | TT_Task | Interior lights systems (Innenbeleuchtung) - Supplier Lead Time | 02/12/2020 | 18/05/2021 | 02/12/2019 | 18/11/2020 | 0 | TK_Complete | 1201082599 | 27 | 1201082599_27
PROC106900 | TT_Task | Driver's seat (Fahrersitz) - Supplier Selection and PO Placement | 09/03/2020 | 01/05/2020 | 13/04/2020 | 05/05/2020 | 0 | TK_Complete | 1201082599 | 45 | 1201082599_45
PROC106920 | TT_Task | Driver's seat (Fahrersitz) - Supplier Lead Time | 05/05/2020 | 21/09/2020 | 05/05/2020 | 26/01/2021 | 0 | TK_Complete | 1201082599 | 44 | 1201082599_44
PROC106960 | TT_Task | Instructor's seat (Fahrlehrersitz) - Supplier Selection and PO Placement | 21/02/2020 | 16/04/2020 | 21/02/2020 | 05/05/2020 | 0 | TK_Complete | 1201082599 | 43 | 1201082599_43
PROC106980 | TT_Task | Instructor's seat (Fahrlehrersitz) - Supplier Lead Time | 05/05/2020 | 21/09/2020 | 05/05/2020 | 18/01/2021 | 0 | TK_Complete | 1201082599 | 44 | 1201082599_44
PROC106660 | TT_Task | Driver's facilities (Fahrbremshebel) - Supplier Selection and PO Placement | 31/01/2020 | 26/03/2020 | 31/01/2020 | 16/06/2020 | 0 | TK_Complete | 1201082599 | 45 | 1201082599_45
PROC106680 | TT_Task | Driver's facilities (Fahrbremshebel) - Supplier Lead Time | 16/06/2020 | 05/10/2020 | 16/06/2020 | 15/10/2020 | 0 | TK_Complete | 1201082599 | 46 | 1201082599_46
PROC106780 | TT_Task | Driver's desk (Fahrerpult/Banane) - Supplier Selection and PO Placement | 02/03/2020 | 24/04/2020 | 02/03/2020 | 27/03/2020 | 0 | TK_Complete | 1201082599 | 45 | 1201082599_45
PROC106800 | TT_Task | Driver's desk (Fahrerpult/Banane) - Supplier Lead Time | 27/03/2020 | 13/08/2020 | 27/03/2020 | 20/11/2020 | 0 | TK_Complete | 1201082599 | 47 | 1201082599_47
PROC106840 | TT_Task | Driver's desk (Fahrerstandsgeschr?nk) - Supplier Selection and PO Placement | 17/04/2020 | 11/06/2020 | 17/04/2020 | 06/07/2020 | 0 | TK_Complete | 1201082599 | 45 | 1201082599_45
PROC106860 | TT_Task | Driver's desk (Fahrerstandsgeschr?nk) - Supplier Lead Time | 10/07/2020 | 26/11/2020 | 06/07/2020 | 20/11/2020 | 0 | TK_Complete | 1201082599 | 47 | 1201082599_47
PROC105160 | TT_Task | Windscreen wiper (Scheibenwischer) - Supplier Selection and PO Placement | 17/06/2019 | 09/08/2019 | 17/06/2019 | 04/09/2019 | 0 | TK_Complete | 1201082599 | 48 | 1201082599_48
PROC105180 | TT_Task | Windscreen wiper (Scheibenwischer) - Supplier Lead Time | 04/09/2019 | 04/02/2020 | 04/09/2019 | 01/09/2020 | 0 | TK_Complete | 1201082599 | 48 | 1201082599_48
PROC106720 | TT_Task | Driver's facilities (Fusspodest) - Supplier Selection and PO Placement | 28/02/2020 | 23/04/2020 | 28/02/2020 | 02/04/2020 | 0 | TK_Complete | 1201082599 | 45 | 1201082599_45
PROC106740 | TT_Task | Driver's facilities (Fusspodest) - Supplier Lead Time | 02/04/2020 | 05/08/2020 | 02/04/2020 | 21/12/2020 | 0 | TK_Complete | 1201082599 | 46 | 1201082599_46
PROC108100 | TT_Task | Blinds (Rollo) - Supplier Selection and PO Placement | 20/05/2020 | 14/07/2020 | 20/05/2020 | 10/07/2020 | 0 | TK_Complete | 1201082599 | 49 | 1201082599_49
PROC108120 | TT_Task | Blinds (Rollo) - Supplier Lead Time | 15/07/2020 | 03/11/2020 | 10/07/2020 | nan | 0 | TK_Active | 1201082599 | 50 | 1201082599_50
PROC107920 | TT_Task | HVAC driver's cab (HVAC Fahrerstand) - Supplier Selection and PO Placement | 18/12/2019 | 11/02/2020 | 18/12/2019 | 08/05/2020 | 0 | TK_Complete | 1201082599 | 51 | 1201082599_51
PROC107930 | TT_Task | HVAC driver's cab (HVAC Fahrerstand) - BBI Collection from Supplier | 08/05/2020 | 02/07/2020 | 08/05/2020 | 08/05/2020 | 0 | TK_Complete | 1201082599 | 52 | 1201082599_52
PROC107940 | TT_Task | HVAC driver's cab (HVAC Fahrerstand) - Supplier Lead Time | 08/05/2020 | 14/01/2021 | 08/05/2020 | 14/01/2021 | 0 | TK_Complete | 1201082599 | 53 | 1201082599_53
PROC107980 | TT_Task | HVAC saloon (HVAC Fahrgastraum) - Supplier Selection and PO Placement | 18/12/2019 | 11/02/2020 | 18/12/2019 | 08/05/2020 | 0 | TK_Complete | 1201082599 | 51 | 1201082599_51
PROC108000 | TT_Task | HVAC saloon (HVAC Fahrgastraum) - Supplier Lead Time | 08/05/2020 | 14/01/2021 | 08/05/2020 | 14/01/2021 | 0 | TK_Complete | 1201082599 | 53 | 1201082599_53
PROC106120 | TT_Task | Auxiliary converters (BNU) - Supplier Selection and PO Placement | 24/05/2019 | 18/07/2019 | 24/05/2019 | 29/05/2020 | 0 | TK_Complete | 1201082599 | 54 | 1201082599_54
PROC106130 | TT_Task | Auxiliary converters (BNU) - BBI Collection from Supplier | 29/05/2020 | 23/07/2020 | 08/07/2019 | 27/11/2019 | 0 | TK_Complete | 1201082599 | 55 | 1201082599_55
PROC106140 | TT_Task | Auxiliary converters (BNU) - Supplier Lead Time | 29/05/2020 | 09/10/2020 | 29/05/2020 | 19/02/2021 | 0 | TK_Complete | 1201082599 | 56 | 1201082599_56
PROC106180 | TT_Task | Batteries (Batterie) - Supplier Selection and PO Placement | 31/05/2019 | 25/07/2019 | 31/05/2019 | 24/10/2019 | 0 | TK_Complete | 1201082599 | 57 | 1201082599_57
PROC106200 | TT_Task | Batteries (Batterie) - Supplier Lead Time | 24/10/2019 | 15/01/2020 | 24/10/2019 | 29/09/2020 | 0 | TK_Complete | 1201082599 | 58 | 1201082599_58
PROC106240 | TT_Task | Battery boxes (Batteriekiste /-ger?st) - Supplier Selection and PO Placement | 18/05/2020 | 10/07/2020 | 18/05/2020 | 17/07/2020 | 0 | TK_Complete | 1201082599 | 57 | 1201082599_57
PROC106260 | TT_Task | Battery boxes (Batteriekiste /-ger?st) - Supplier Lead Time | 13/07/2020 | 11/09/2020 | 17/07/2020 | 08/03/2021 | 0 | TK_Complete | 1201082599 | 58 | 1201082599_58
PROC106060 | TT_Task | Pantograph (Stromabnehmer) - Supplier Selection and PO Placement | 13/09/2019 | 07/11/2019 | 13/09/2019 | 27/02/2020 | 0 | TK_Complete | 1201082599 | 59 | 1201082599_59
PROC106080 | TT_Task | Pantograph (Stromabnehmer) - Supplier Lead Time | 27/02/2020 | 19/08/2020 | 27/02/2020 | 11/02/2021 | 0 | TK_Complete | 1201082599 | 60 | 1201082599_60
PROC105940 | TT_Task | Bogie fittings (Sandung) - Supplier Selection and PO Placement | 04/07/2019 | 28/08/2019 | 04/07/2019 | 30/04/2020 | 0 | TK_Complete | 1201082599 | 61 | 1201082599_61
PROC105950 | TT_Task | Bogie fittings (Sandung) - BBI Collection from Supplier | 30/04/2020 | 24/06/2020 | 26/08/2019 | 26/08/2019 | 0 | TK_Complete | 1201082599 | 61 | 1201082599_61
PROC105960 | TT_Task | Bogie fittings (Sandung) - Supplier Lead Time | 30/04/2020 | 07/09/2020 | 30/04/2020 | 15/09/2020 | 0 | TK_Complete | 1201082599 | 61 | 1201082599_61
PROC106000 | TT_Task | Flange lubrication (Spurkranzschmierung) - Supplier Selection and PO Placement | 30/10/2019 | 24/12/2019 | 30/10/2019 | 02/07/2020 | 0 | TK_Complete | 1201082599 | 62 | 1201082599_62
PROC106010 | TT_Task | Flange lubrication (Spurkranzschmierung) - BBI Collection from Supplier | 30/04/2020 | 24/06/2020 | 30/04/2020 | 30/04/2020 | 0 | TK_Complete | 1201082599 | 62 | 1201082599_62
PROC106020 | TT_Task | Flange lubrication (Spurkranzschmierung) - Supplier Lead Time | 02/07/2020 | 09/10/2020 | 02/07/2020 | 29/01/2021 | 0 | TK_Complete | 1201082599 | 62 | 1201082599_62
PROC106300 | TT_Task | Braking system (Bremse) - Supplier Selection and PO Placement | 05/08/2019 | 27/09/2019 | 05/08/2019 | 16/01/2020 | 0 | TK_Complete | 1201082599 | 63 | 1201082599_63
PROC106310 | TT_Task | Braking system (Bremse) - BBI Collection from Supplier | 16/01/2020 | 11/03/2020 | 26/07/2019 | 05/08/2019 | 0 | TK_Complete | 1201082599 | 64 | 1201082599_64
PROC106320 | TT_Task | Braking system (Bremse) - Supplier Lead Time | 16/01/2020 | 17/09/2020 | 16/01/2020 | 17/09/2020 | 0 | TK_Complete | 1201082599 | 65 | 1201082599_65
PROC105580 | TT_Task | Couplers (Kupplung) - Supplier Selection and PO Placement | 19/07/2019 | 12/09/2019 | 19/07/2019 | 12/12/2019 | 0 | TK_Complete | 1201082599 | 66 | 1201082599_66
PROC105600 | TT_Task | Couplers (Kupplung) - Supplier Lead Time | 12/12/2019 | 02/12/2020 | 12/12/2019 | 05/02/2021 | 0 | TK_Complete | 1201082599 | 67 | 1201082599_67
PROC105460 | TT_Task | Gangways (oberes querelastisches Drehg.) - Supplier Selection and PO Placement | 06/12/2019 | 30/01/2020 | 01/12/2019 | 02/12/2019 | 0 | TK_Complete | 1201082599 | 68 | 1201082599_68
PROC105480 | TT_Task | Gangways (oberes querelastisches Drehg.) - Supplier Lead Time | 02/12/2019 | 22/05/2020 | 02/12/2019 | 12/11/2020 | 0 | TK_Complete | 1201082599 | 69 | 1201082599_69
PROC105520 | TT_Task | Gangways (Wellenbalg ; Drehscheibe) - Supplier Selection and PO Placement | 06/12/2019 | 30/01/2020 | 06/12/2019 | 24/03/2020 | 0 | TK_Complete | 1201082599 | 68 | 1201082599_68
PROC105540 | TT_Task | Gangways (Wellenbalg ; Drehscheibe) - Supplier Lead Time | 31/01/2020 | 27/08/2020 | 24/03/2020 | 12/11/2020 | 0 | TK_Complete | 1201082599 | 69 | 1201082599_69
PROC107380 | TT_Task | On board control system (Drivers desk IDD/HMI) - Supplier Selection and PO Placement | 30/03/2020 | 22/05/2020 | 30/03/2020 | 26/06/2020 | 0 | TK_Complete | 1201082599 | 70 | 1201082599_70
PROC107390 | TT_Task | On board control system (Drivers desk IDD/HMI) - BBI Collection from Supplier | 26/06/2020 | 20/08/2020 | 10/04/2020 | 10/04/2020 | 0 | TK_Complete | 1201082599 | 70 | 1201082599_70
PROC107400 | TT_Task | On board control system (Drivers desk IDD/HMI) - Supplier Lead Time | 26/06/2020 | 15/10/2020 | 26/06/2020 | 15/09/2020 | 0 | TK_Complete | 1201082599 | 71 | 1201082599_71
PROC107560 | TT_Task | Visual comm. (PIS/PAS) (Au?enanzeiger) - Supplier Selection and PO Placement | 15/08/2019 | 09/10/2019 | 15/08/2019 | 25/06/2020 | 0 | TK_Complete | 1201082599 | 72 | 1201082599_72
PROC107570 | TT_Task | Visual comm. (PIS/PAS) (Au?enanzeiger) - BBI Collection from Supplier | 25/06/2020 | 19/08/2020 | 25/06/2020 | 25/06/2020 | 0 | TK_Complete | 1201082599 | 73 | 1201082599_73
PROC107580 | TT_Task | Visual comm. (PIS/PAS) (Au?enanzeiger) - Supplier Lead Time | 25/06/2020 | 30/09/2020 | 25/06/2020 | 19/11/2020 | 0 | TK_Complete | 1201082599 | 74 | 1201082599_74
PROC107620 | TT_Task | Visual comm. (PIS/PAS) (Interne Displays) - Supplier Selection and PO Placement | 15/08/2019 | 09/10/2019 | 15/08/2019 | 25/06/2020 | 0 | TK_Complete | 1201082599 | 72 | 1201082599_72
PROC107630 | TT_Task | Visual comm. (PIS/PAS) (Interne Displays) - BBI Collection from Supplier | 25/06/2020 | 19/08/2020 | 06/05/2020 | 06/05/2020 | 0 | TK_Complete | 1201082599 | 73 | 1201082599_73
PROC107640 | TT_Task | Visual comm. (PIS/PAS) (Interne Displays) - Supplier Lead Time | 25/06/2020 | 14/10/2020 | 25/06/2020 | 19/11/2020 | 0 | TK_Complete | 1201082599 | 74 | 1201082599_74
PROC107440 | TT_Task | Saloon surveillance (CCTV Innenkameras) - Supplier Selection and PO Placement | 20/11/2019 | 14/01/2020 | 20/11/2019 | 27/01/2020 | 0 | TK_Complete | 1201082599 | 75 | 1201082599_75
PROC107450 | TT_Task | Saloon surveillance (CCTV Innenkameras) - BBI Collection from Supplier | 27/01/2020 | 20/03/2020 | 26/07/2019 | 02/09/2019 | 0 | TK_Complete | 1201082599 | 75 | 1201082599_75
PROC107460 | TT_Task | Saloon surveillance (CCTV Innenkameras) - Supplier Lead Time | 27/01/2020 | 17/07/2020 | 27/01/2020 | 24/09/2020 | 0 | TK_Complete | 1201082599 | 75 | 1201082599_75
PROC107680 | TT_Task | Passenger counting system (Fahrgastz?hlung) - Supplier Selection and PO Placement | 16/12/2019 | 07/02/2020 | 16/12/2019 | 17/04/2020 | 0 | TK_Complete | 1201082599 | 76 | 1201082599_76
PROC107690 | TT_Task | Passenger counting system (Fahrgastz?hlung) - BBI Collection from Supplier | 17/04/2020 | 11/06/2020 | 10/02/2020 | 10/02/2020 | 0 | TK_Complete | 1201082599 | 76 | 1201082599_76
PROC107700 | TT_Task | Passenger counting system (Fahrgastz?hlung) - Supplier Lead Time | 17/04/2020 | 03/09/2020 | 17/04/2020 | 18/12/2020 | 0 | TK_Complete | 1201082599 | 76 | 1201082599_76
METH100680 | TT_Task | WS 201 CM7- MBOM Implementation, Logistics Preparation, C Parts Lead Time, Tooling Definition, Fabrication, Installation | 13/12/2019 | 16/04/2020 | 13/12/2019 | 20/04/2020 | 0 | TK_Complete | 1201082599 | 77 | 1201082599_77
METH100140 | TT_Task | WS 201 CM1- MBOM Implementation, Logistics Preparation, C Parts Lead Time, Tooling Definition, Fabrication, Installation | 01/01/2018 | 04/05/2018 | 13/12/2019 | 20/04/2020 | 0 | TK_Complete | 1201082599 | 77 | 1201082599_77
METH100020 | TT_Task | WS 202 - MBOM Implementation, Logistics Preparation, C Parts Lead Time, Tooling Definition, Fabrication, Installation | 18/08/2020 | 21/12/2020 | 04/02/2020 | 25/06/2020 | 0 | TK_Complete | 1201082599 | 77 | 1201082599_77
METH100050 | TT_Task | WS 203 - MBOM Implementation, Logistics Preparation, C Parts Lead Time, Tooling Definition, Fabrication, Installation | 01/01/2018 | 04/05/2018 | 20/04/2020 | 25/06/2020 | 0 | TK_Complete | 1201082599 | 77 | 1201082599_77
METH100110 | TT_Task | WS 204 - MBOM Implementation, Logistics Preparation, C Parts Lead Time, Tooling Definition, Fabrication, Installation | 17/04/2020 | 20/08/2020 | 17/04/2020 | 20/08/2020 | 0 | TK_Complete | 1201082599 | 77 | 1201082599_77
METH100170 | TT_Task | WS 206 - MBOM Implementation, Logistics Preparation, C Parts Lead Time, Tooling Definition, Fabrication, Installation | 18/08/2020 | 21/12/2020 | 13/01/2020 | 09/06/2020 | 0 | TK_Complete | 1201082599 | 77 | 1201082599_77
METH100200 | TT_Task | WS 207 - MBOM Implementation, Logistics Preparation, C Parts Lead Time, Tooling Definition, Fabrication, Installation | 25/06/2020 | 28/10/2020 | 25/06/2020 | 25/06/2020 | 0 | TK_Complete | 1201082599 | 77 | 1201082599_77
METH100230 | TT_Task | WS 301 - MBOM Implementation, Logistics Preparation, C Parts Lead Time, Tooling Definition, Fabrication, Installation | 03/09/2020 | 06/01/2021 | 18/12/2019 | 11/08/2020 | 0 | TK_Complete | 1201082599 | 78 | 1201082599_78
METH100320 | TT_Task | WS 302 - MBOM Implementation, Logistics Preparation, C Parts Lead Time, Tooling Definition, Fabrication, Installation | 24/04/2020 | 27/08/2020 | 24/04/2020 | 19/05/2020 | 0 | TK_Complete | 1201082599 | 78 | 1201082599_78
METH100260 | TT_Task | WS 303 - MBOM Implementation, Logistics Preparation, C Parts Lead Time, Tooling Definition, Fabrication, Installation | 15/07/2020 | 17/11/2020 | 17/02/2020 | 21/07/2020 | 0 | TK_Complete | 1201082599 | 78 | 1201082599_78
METH100290 | TT_Task | WS 304 - MBOM Implementation, Logistics Preparation, C Parts Lead Time, Tooling Definition, Fabrication, Installation | 03/09/2020 | 06/01/2021 | 27/02/2020 | 16/07/2020 | 0 | TK_Complete | 1201082599 | 78 | 1201082599_78
METH100350 | TT_Task | WS 308 - MBOM Implementation, Logistics Preparation, C Parts Lead Time, Tooling Definition, Fabrication, Installation | 28/09/2020 | 29/01/2021 | 06/03/2020 | 29/06/2020 | 0 | TK_Complete | 1201082599 | 78 | 1201082599_78
METH100380 | TT_Task | WS 309 - MBOM Implementation, Logistics Preparation, C Parts Lead Time, Tooling Definition, Fabrication, Installation | 20/04/2020 | 21/08/2020 | 16/04/2020 | 26/05/2020 | 0 | TK_Complete | 1201082599 | 78 | 1201082599_78
METH100410 | TT_Task | WS 310 - MBOM Implementation, Logistics Preparation, C Parts Lead Time, Tooling Definition, Fabrication, Installation | 17/08/2020 | 18/12/2020 | 13/02/2020 | 24/08/2020 | 0 | TK_Complete | 1201082599 | 78 | 1201082599_78
METH100440 | TT_Task | WS 311 - MBOM Implementation, Logistics Preparation, C Parts Lead Time, Tooling Definition, Fabrication, Installation | 30/10/2020 | 04/03/2021 | 14/02/2020 | 02/09/2020 | 0 | TK_Complete | 1201082599 | 78 | 1201082599_78
METH100470 | TT_Task | WS 312 - MBOM Implementation, Logistics Preparation, C Parts Lead Time, Tooling Definition, Fabrication, Installation | 30/10/2020 | 04/03/2021 | 17/01/2020 | 31/08/2020 | 0 | TK_Complete | 1201082599 | 78 | 1201082599_78
METH100500 | TT_Task | WS 313 - MBOM Implementation, Logistics Preparation, C Parts Lead Time, Tooling Definition, Fabrication, Installation | 18/08/2020 | 21/12/2020 | 13/02/2020 | 14/07/2020 | 0 | TK_Complete | 1201082599 | 78 | 1201082599_78
METH100560 | TT_Task | WS 314 - MBOM Implementation, Logistics Preparation, C Parts Lead Time, Tooling Definition, Fabrication, Installation | 13/10/2020 | 15/02/2021 | 05/02/2020 | 21/09/2020 | 0 | TK_Complete | 1201082599 | 78 | 1201082599_78
METH100590 | TT_Task | WS 315 - MBOM Implementation, Logistics Preparation, C Parts Lead Time, Tooling Definition, Fabrication, Installation | 24/04/2020 | 27/08/2020 | 17/01/2020 | 14/07/2020 | 0 | TK_Complete | 1201082599 | 78 | 1201082599_78
METH100620 | TT_Task | WS 316 - MBOM Implementation, Logistics Preparation, C Parts Lead Time, Tooling Definition, Fabrication, Installation | 01/01/2018 | 04/05/2018 | 17/01/2020 | 24/09/2020 | 0 | TK_Complete | 1201082599 | 78 | 1201082599_78
METH100650 | TT_Task | WS 401 - MBOM Implementation, Logistics Preparation, C Parts Lead Time, Tooling Definition, Fabrication, Installation | 14/08/2020 | 17/12/2020 | 14/08/2020 | 17/12/2020 | 0 | TK_Complete | 1201082599 | 78 | 1201082599_78
TTEST10050 | TT_Task | Trainset 01 - Transport zu WLB (Transport from WL to WLB) | 01/03/2021 | 01/03/2021 | nan | nan | 12191 | TK_NotStart | 1201082599 | 79 | 1201082599_79
TTEST10670 | TT_Task | Zulassung/Authorisation - Bauartgenehmigung (Type Approval) | 29/11/2019 | 15/07/2020 | 29/11/2019 | 17/07/2020 | 0 | TK_Complete | 1201082599 | 80 | 1201082599_80
TTEST10685 | TT_Task | Annahme Erhalt Bauartgenehmigung (Design Approval ) | 16/07/2020 | 15/02/2021 | 16/07/2020 | 16/02/2021 | 0 | TK_Complete | 1201082599 | 81 | 1201082599_81
TTEST10690 | TT_Task | Betriebsbewilligung (Operating license) | 21/06/2021 | 21/12/2021 | 16/12/2020 | nan | 0 | TK_Active | 1201082599 | 82 | 1201082599_82
TTEST10720 | TT_Task | Bearbeitungszeit Beh?rde (best case) (Processing time authority (best case)) | 11/08/2022 | 29/09/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 83 | 1201082599_83
TTEST10850 | TT_Task | Gutachten Betriebsbewilligung (Expert opinion operating license) | 18/07/2022 | 10/08/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 82 | 1201082599_82
A157725 | TT_Task | MPS Change from A2 to A04 due to Covid - CM 7 Rohbau | 30/04/2020 | 26/08/2020 | 30/04/2020 | 26/08/2020 | 0 | TK_Complete | 1201082599 | 84 | 1201082599_84
CWS1010 | TT_Task | Trainset 01 CM7 - Customer Inspection (Haltepunkt) | 01/01/2020 | 01/01/2020 | 04/08/2020 | 04/08/2020 | 0 | TK_Complete | 1201082599 | 85 | 1201082599_85
A157740 | TT_Task | Trainset 01 CM7 - Carbody Surface (Oberfl?che) | 04/08/2020 | 21/09/2020 | 30/09/2020 | 02/12/2020 | 0 | TK_Complete | 1201082599 | 86 | 1201082599_86
A236720 | TT_Task | MPS Change from A2 to A04 due to Covid - CM 7 Oberfl?che | 15/06/2020 | 04/08/2020 | 15/06/2020 | 14/10/2020 | 0 | TK_Complete | 1201082599 | 87 | 1201082599_87
COVID19 - 18 | TT_Task | COVID19 - 00007 - Productivity losses at the manufacturing site in Vienna (For all vehicles) | 01/01/2020 | 08/01/2020 | 04/08/2020 | 11/08/2020 | 0 | TK_Complete | 1201082599 | 88 | 1201082599_88
COVID19 - 278 | TT_Task | COVID19 - 00008 - Productivity losses in the white-collar sector at the Vienna site | 01/03/2021 | 22/03/2021 | 01/03/2021 | 22/03/2021 | 0 | TK_Complete | 1201082599 | 89 | 1201082599_89
A157750 | TT_Task | Trainset 01 CM7 - Fitout (Innenausbau) | 15/01/2021 | 05/02/2021 | 03/12/2020 | 12/02/2021 | 0 | TK_Complete | 1201082599 | 90 | 1201082599_90
A236730 | TT_Task | MPS Change from A2 to A04 due to Covid - CM 7 Innenausbau | 22/07/2020 | 10/09/2020 | 22/07/2020 | 23/11/2020 | 0 | TK_Complete | 1201082599 | 91 | 1201082599_91
COVID19 - 00007 | TT_Task | COVID19 - 00007 - Productivity losses at the manufacturing site in Vienna (For all vehicles) | 01/01/2020 | 08/01/2020 | 04/08/2020 | 11/08/2020 | 0 | TK_Complete | 1201082599 | 88 | 1201082599_88
COVID19 - 00012 | TT_Task | COVID19 - 00012 - TDG / Numerous force majeure notifications from subcontractors (Min. 4weeks delay) | 01/01/2020 | 15/01/2020 | 17/08/2020 | 14/09/2020 | 0 | TK_Complete | 1201082599 | 92 | 1201082599_92
A236740 | TT_Task | MPS Change from A2 to A04 due to Covid - CM 1 Rohbau | 30/04/2020 | 26/08/2020 | 30/04/2020 | 26/08/2020 | 0 | TK_Complete | 1201082599 | 84 | 1201082599_84
CWS1020 | TT_Task | Trainset 01 CM1 - Customer Inspection (Haltepunkt) | 01/01/2020 | 01/01/2020 | 26/08/2020 | 26/08/2020 | 0 | TK_Complete | 1201082599 | 85 | 1201082599_85
A157770 | TT_Task | Trainset 01 CM1 - Carbody Surface (Oberfl?che) | 16/10/2020 | 24/11/2020 | 04/11/2020 | 02/12/2020 | 0 | TK_Complete | 1201082599 | 86 | 1201082599_86
A236750 | TT_Task | MPS Change from A2 to A04 due to Covid - CM 1 Oberfl?che | 01/07/2020 | 14/08/2020 | 01/07/2020 | 27/10/2020 | 0 | TK_Complete | 1201082599 | 87 | 1201082599_87
COVID19 - 268 | TT_Task | COVID19 - 00008 - Productivity losses in the white-collar sector at the Vienna site | 01/03/2021 | 22/03/2021 | 01/03/2021 | 22/03/2021 | 0 | TK_Complete | 1201082599 | 89 | 1201082599_89
COVID19 - 28 | TT_Task | COVID19 - 00007 - Productivity losses at the manufacturing site in Vienna (For all vehicles) | 01/01/2020 | 08/01/2020 | 04/08/2020 | 11/08/2020 | 0 | TK_Complete | 1201082599 | 88 | 1201082599_88
A157780 | TT_Task | Trainset 01 CM1 - Fitout (Innenausbau) | 15/01/2021 | 15/01/2021 | 20/01/2021 | 18/02/2021 | 0 | TK_Complete | 1201082599 | 90 | 1201082599_90
A236760 | TT_Task | MPS Change from A2 to A04 due to Covid - CM 1 Innenausbau | 21/08/2020 | 22/09/2020 | 21/08/2020 | 03/12/2020 | 0 | TK_Complete | 1201082599 | 91 | 1201082599_91
COVID19 - 258 | TT_Task | COVID19 - 00008 - Productivity losses in the white-collar sector at the Vienna site | 01/03/2021 | 22/03/2021 | 01/03/2021 | 22/03/2021 | 0 | TK_Complete | 1201082599 | 89 | 1201082599_89
COVID19 - 38 | TT_Task | COVID19 - 00007 - Productivity losses at the manufacturing site in Vienna (For all vehicles) | 01/01/2020 | 08/01/2020 | 04/08/2020 | 11/08/2020 | 0 | TK_Complete | 1201082599 | 88 | 1201082599_88
COVID19 - 448 | TT_Task | COVID19 - 00012 - TDG / Numerous force majeure notifications from subcontractors (Min. 4weeks delay) | 01/01/2020 | 15/01/2020 | 17/08/2020 | 14/09/2020 | 0 | TK_Complete | 1201082599 | 92 | 1201082599_92
A157790 | TT_Task | Trainset 01 SM6 - Carbody Production (Rohbau Produktion) | 01/09/2020 | 01/09/2020 | 29/04/2020 | 27/05/2020 | 0 | TK_Complete | 1201082599 | 93 | 1201082599_93
A236770 | TT_Task | MPS Change from A2 to A04 due to Covid - SM 6 Rohbau | 07/05/2020 | 01/09/2020 | 07/05/2020 | 01/09/2020 | 0 | TK_Complete | 1201082599 | 84 | 1201082599_84
COVID19 - 00009 | TT_Task | COVID19 - 00009 - Bautzen / Poland and Czech Republic border closure, which prevented workers | 01/01/2020 | 08/01/2020 | 01/07/2020 | 08/07/2020 | 0 | TK_Complete | 1201082599 | 94 | 1201082599_94
COVID19 - 00013 | TT_Task | COVID19 - 00013 - Hisarlar / Factory closure between 20.3.20 - 05.04.20 | 20/03/2020 | 20/03/2020 | 20/03/2020 | 05/04/2020 | 0 | TK_Complete | 1201082599 | 95 | 1201082599_95
COVID19 - 00014 | TT_Task | COVID19 - 00014 - Duray / Factory closure between 27.3.20 - 13.04.20 | 27/03/2020 | 22/05/2020 | 27/03/2020 | 22/05/2020 | 0 | TK_Complete | 1201082599 | 96 | 1201082599_96
CW1030 | TT_Task | Trainset 01 SM6 - Transport from Goerlitz to Ceska Lipa | 08/12/2020 | 08/12/2020 | 12/06/2020 | 12/06/2020 | 0 | TK_Complete | 1201082599 | 97 | 1201082599_97
CWS1030 | TT_Task | Trainset 01 SM6 - Customer Inspection (Haltepunkt) | 01/01/2020 | 01/01/2020 | 27/05/2020 | 28/05/2020 | 0 | TK_Complete | 1201082599 | 98 | 1201082599_98
A157800 | TT_Task | Trainset 01 SM6 - Carbody Surface (Oberfl?che) | 09/12/2020 | 09/12/2020 | 12/06/2020 | 30/08/2020 | 0 | TK_Complete | 1201082599 | 99 | 1201082599_99
A236780 | TT_Task | MPS Change from A2 to A04 due to Covid - SM 6 Oberfl?che | 07/05/2020 | 31/08/2020 | 07/05/2020 | 01/09/2020 | 0 | TK_Complete | 1201082599 | 87 | 1201082599_87
COVID19 - 248 | TT_Task | COVID19 - 00008 - Productivity losses in the white-collar sector at the Vienna site | 01/03/2021 | 22/03/2021 | 01/03/2021 | 22/03/2021 | 0 | TK_Complete | 1201082599 | 89 | 1201082599_89
COVID19 - 538 | TT_Task | COVID19 - 00015 - Rawag / Reduction in production capacity due to illness and quarentien | 14/07/2020 | 07/08/2020 | 14/07/2020 | 07/08/2020 | 0 | TK_Complete | 1201082599 | 100 | 1201082599_100
COVID19 - 58 | TT_Task | COVID19 - 00007 - Productivity losses at the manufacturing site in Vienna (For all vehicles) | 01/01/2020 | 08/01/2020 | 04/08/2020 | 11/08/2020 | 0 | TK_Complete | 1201082599 | 88 | 1201082599_88
CW2290 | TT_Task | Trainset 01 SM6 - Transport from Ceska Lipa to Vienna | 31/12/2026 | 01/01/2027 | 30/08/2020 | 30/08/2020 | 0 | TK_Complete | 1201082599 | 101 | 1201082599_101
CW3550 | TT_Task | Trainset 01 SM6 - Bonding and Waxing (Kleben und Wachs) | 03/01/2020 | 03/01/2020 | 31/08/2020 | 09/12/2020 | 0 | TK_Complete | 1201082599 | 102 | 1201082599_102
A157810 | TT_Task | Trainset 01 SM6 - Fitout (Innenausbau) | 11/01/2021 | 20/01/2021 | 09/12/2020 | 17/02/2021 | 0 | TK_Complete | 1201082599 | 103 | 1201082599_103
A236790 | TT_Task | MPS Change from A2 to A04 due to Covid - SM 6 Innenausbau | 10/07/2020 | 05/10/2020 | 10/07/2020 | 05/11/2020 | 0 | TK_Complete | 1201082599 | 91 | 1201082599_91
COVID19 - 00006 | TT_Task | COVID19 - 00006 - IFE / Delay in the production, testing and approval of color samples for the door leaf | 16/06/2020 | 12/08/2020 | 16/06/2020 | 12/08/2020 | 0 | TK_Complete | 1201082599 | 104 | 1201082599_104
COVID19 - 00010 | TT_Task | COVID19 - 00010 - Short-time work at R2P.(12 Weeks) | 01/01/2020 | 25/03/2020 | 04/05/2020 | 27/07/2020 | 0 | TK_Complete | 1201082599 | 105 | 1201082599_105
COVID19 - 00011 | TT_Task | COVID19 - 00011 - Closing KTP plant Tczew 4.5.-18.5.2020 and a 4 -day working week | 04/05/2020 | 04/05/2020 | 04/05/2020 | 15/05/2020 | 0 | TK_Complete | 1201082599 | 106 | 1201082599_106
COVID19 - 00016 | TT_Task | COVID19 - 00016 - Monte Meao / Reduced production capactity and closures(Del Pas seats) | 16/04/2020 | 14/08/2020 | 16/04/2020 | 14/08/2020 | 0 | TK_Complete | 1201082599 | 107 | 1201082599_107
COVID19 - 238 | TT_Task | COVID19 - 00008 - Productivity losses in the white-collar sector at the Vienna site | 01/03/2021 | 22/03/2021 | 01/03/2021 | 22/03/2021 | 0 | TK_Complete | 1201082599 | 89 | 1201082599_89
COVID19 - 48 | TT_Task | COVID19 - 00007 - Productivity losses at the manufacturing site in Vienna (For all vehicles) | 01/01/2020 | 08/01/2020 | 04/08/2020 | 11/08/2020 | 0 | TK_Complete | 1201082599 | 88 | 1201082599_88
A157820 | TT_Task | Trainset 01 SM2 - Carbody Production (Rohbau Produktion) | 01/09/2020 | 01/09/2020 | 26/05/2020 | 06/07/2020 | 0 | TK_Complete | 1201082599 | 108 | 1201082599_108
A236800 | TT_Task | MPS Change from A2 to A04 due to Covid - SM 2 Rohbau | 07/05/2020 | 01/09/2020 | 07/05/2020 | 01/09/2020 | 0 | TK_Complete | 1201082599 | 84 | 1201082599_84
COVID19 - 328 | TT_Task | COVID19 - 00009 - Bautzen / Poland and Czech Republic border closure, which prevented workers | 01/01/2020 | 08/01/2020 | 01/07/2020 | 08/07/2020 | 0 | TK_Complete | 1201082599 | 94 | 1201082599_94
COVID19 - 458 | TT_Task | COVID19 - 00013 - Hisarlar / Factory closure between 20.3.20 - 05.04.20 | 20/03/2020 | 20/03/2020 | 20/03/2020 | 05/04/2020 | 0 | TK_Complete | 1201082599 | 95 | 1201082599_95
COVID19 - 468 | TT_Task | COVID19 - 00014 - Duray / Factory closure between 27.3.20 - 13.04.20 | 27/03/2020 | 22/05/2020 | 27/03/2020 | 22/05/2020 | 0 | TK_Complete | 1201082599 | 96 | 1201082599_96
CW1040 | TT_Task | Trainset 01 SM2 - Transport from Goerlitz to Ceska Lipa | 13/01/2021 | 13/01/2021 | 10/07/2020 | 10/07/2020 | 0 | TK_Complete | 1201082599 | 109 | 1201082599_109
CWS1040 | TT_Task | Trainset 01 SM2 - Customer Inspection (Haltepunkt) | 01/01/2020 | 01/01/2020 | 07/07/2020 | 09/07/2020 | 0 | TK_Complete | 1201082599 | 110 | 1201082599_110
A157830 | TT_Task | Trainset 01 SM2 - Carbody Surface (Oberfl?che) | 14/01/2021 | 14/01/2021 | 10/07/2020 | 02/11/2020 | 0 | TK_Complete | 1201082599 | 99 | 1201082599_99
A236810 | TT_Task | MPS Change from A2 to A04 due to Covid - SM 2 Oberfl?che | 07/05/2020 | 31/08/2020 | 07/05/2020 | 01/09/2020 | 0 | TK_Complete | 1201082599 | 87 | 1201082599_87
COVID19 - 00015 | TT_Task | COVID19 - 00015 - Rawag / Reduction in production capacity due to illness and quarentien | 14/07/2020 | 07/08/2020 | 14/07/2020 | 07/08/2020 | 0 | TK_Complete | 1201082599 | 100 | 1201082599_100
COVID19 - 228 | TT_Task | COVID19 - 00008 - Productivity losses in the white-collar sector at the Vienna site | 01/03/2021 | 22/03/2021 | 01/03/2021 | 22/03/2021 | 0 | TK_Complete | 1201082599 | 89 | 1201082599_89
COVID19 - 68 | TT_Task | COVID19 - 00007 - Productivity losses at the manufacturing site in Vienna (For all vehicles) | 01/01/2020 | 08/01/2020 | 04/08/2020 | 11/08/2020 | 0 | TK_Complete | 1201082599 | 88 | 1201082599_88
CW2300 | TT_Task | Trainset 01 SM2 - Transport from Ceska Lipa to Vienna | 31/12/2026 | 01/01/2027 | 02/11/2020 | 02/11/2020 | 0 | TK_Complete | 1201082599 | 111 | 1201082599_111
A157840 | TT_Task | Trainset 01 SM2 - Fitout (Innenausbau) | 11/12/2020 | 25/01/2021 | 14/01/2021 | 15/02/2021 | 0 | TK_Complete | 1201082599 | 103 | 1201082599_103
A236820 | TT_Task | MPS Change from A2 to A04 due to Covid - SM 2 Innenausbau | 16/07/2020 | 20/10/2020 | 16/07/2020 | 17/11/2020 | 0 | TK_Complete | 1201082599 | 91 | 1201082599_91
COVID19 - 218 | TT_Task | COVID19 - 00008 - Productivity losses in the white-collar sector at the Vienna site | 01/03/2021 | 22/03/2021 | 01/03/2021 | 22/03/2021 | 0 | TK_Complete | 1201082599 | 89 | 1201082599_89
COVID19 - 288 | TT_Task | COVID19 - 00006 - IFE / Delay in the production, testing and approval of color samples for the door leaf | 16/06/2020 | 12/08/2020 | 16/06/2020 | 12/08/2020 | 0 | TK_Complete | 1201082599 | 104 | 1201082599_104
COVID19 - 368 | TT_Task | COVID19 - 00010 - Short-time work at R2P.(12 Weeks) | 01/01/2020 | 25/03/2020 | 04/05/2020 | 27/07/2020 | 0 | TK_Complete | 1201082599 | 105 | 1201082599_105
COVID19 - 408 | TT_Task | COVID19 - 00011 - Closing KTP plant Tczew 4.5.-18.5.2020 and a 4 -day working week | 04/05/2020 | 04/05/2020 | 04/05/2020 | 15/05/2020 | 0 | TK_Complete | 1201082599 | 106 | 1201082599_106
COVID19 - 578 | TT_Task | COVID19 - 00016 - Monte Meao / Reduced production capactity and closures(Del Pas seats) | 16/04/2020 | 14/08/2020 | 16/04/2020 | 14/08/2020 | 0 | TK_Complete | 1201082599 | 107 | 1201082599_107
COVID19 - 78 | TT_Task | COVID19 - 00007 - Productivity losses at the manufacturing site in Vienna (For all vehicles) | 01/01/2020 | 08/01/2020 | 04/08/2020 | 11/08/2020 | 0 | TK_Complete | 1201082599 | 88 | 1201082599_88
CW3560 | TT_Task | Trainset 01 SM2 - Bonding and Waxing (Kleben und Wachs) | 03/01/2020 | 03/01/2020 | 03/11/2020 | 14/01/2021 | 0 | TK_Complete | 1201082599 | 112 | 1201082599_112
A157880 | TT_Task | Trainset 01 BM7 - Carbody Production (Rohbau Produktion) | 01/09/2020 | 01/09/2020 | 04/05/2020 | 02/07/2020 | 0 | TK_Complete | 1201082599 | 113 | 1201082599_113
A236860 | TT_Task | MPS Change from A2 to A04 due to Covid - BM 7 Rohbau | 07/05/2020 | 01/09/2020 | 07/05/2020 | 01/09/2020 | 0 | TK_Complete | 1201082599 | 84 | 1201082599_84
COVID19 - 338 | TT_Task | COVID19 - 00009 - Bautzen / Poland and Czech Republic border closure, which prevented workers | 01/01/2020 | 08/01/2020 | 01/07/2020 | 08/07/2020 | 0 | TK_Complete | 1201082599 | 94 | 1201082599_94
COVID19 - 478 | TT_Task | COVID19 - 00013 - Hisarlar / Factory closure between 20.3.20 - 05.04.20 | 20/03/2020 | 20/03/2020 | 20/03/2020 | 05/04/2020 | 0 | TK_Complete | 1201082599 | 95 | 1201082599_95
COVID19 - 488 | TT_Task | COVID19 - 00014 - Duray / Factory closure between 27.3.20 - 13.04.20 | 27/03/2020 | 22/05/2020 | 27/03/2020 | 22/05/2020 | 0 | TK_Complete | 1201082599 | 96 | 1201082599_96
CW1060 | TT_Task | Trainset 01 BM7 - Transport from Goerlitz to Ceska Lipa | 21/09/2020 | 21/09/2020 | 09/07/2020 | 10/07/2020 | 0 | TK_Complete | 1201082599 | 114 | 1201082599_114
CWS1060 | TT_Task | Trainset 01 BM7 - Customer Inspection (Haltepunkt) | 01/01/2020 | 01/01/2020 | 02/07/2020 | 09/07/2020 | 0 | TK_Complete | 1201082599 | 115 | 1201082599_115
A157890 | TT_Task | Trainset 01 BM7 - Carbody Surface (Oberfl?che) | 01/09/2020 | 01/09/2020 | 11/07/2020 | 20/09/2020 | 0 | TK_Complete | 1201082599 | 116 | 1201082599_116
A236870 | TT_Task | MPS Change from A2 to A04 due to Covid - BM 7 Oberfl?che | 07/05/2020 | 31/08/2020 | 07/05/2020 | 01/09/2020 | 0 | TK_Complete | 1201082599 | 87 | 1201082599_87
COVID19 - 208 | TT_Task | COVID19 - 00008 - Productivity losses in the white-collar sector at the Vienna site | 01/03/2021 | 22/03/2021 | 01/03/2021 | 22/03/2021 | 0 | TK_Complete | 1201082599 | 89 | 1201082599_89
COVID19 - 548 | TT_Task | COVID19 - 00015 - Rawag / Reduction in production capacity due to illness and quarentien | 14/07/2020 | 07/08/2020 | 14/07/2020 | 07/08/2020 | 0 | TK_Complete | 1201082599 | 100 | 1201082599_100
COVID19 - 88 | TT_Task | COVID19 - 00007 - Productivity losses at the manufacturing site in Vienna (For all vehicles) | 01/01/2020 | 08/01/2020 | 04/08/2020 | 11/08/2020 | 0 | TK_Complete | 1201082599 | 88 | 1201082599_88
CW2320 | TT_Task | Trainset 01 BM7 - Transport from Ceska Lipa to Vienna | 21/09/2020 | 21/09/2020 | 21/09/2020 | 21/09/2020 | 0 | TK_Complete | 1201082599 | 117 | 1201082599_117
CW3580 | TT_Task | Trainset 01 BM7 - Bonding and Waxing (Kleben und Wachs) | 03/01/2020 | 03/01/2020 | 22/09/2020 | 21/12/2020 | 0 | TK_Complete | 1201082599 | 118 | 1201082599_118
A157900 | TT_Task | Trainset 01 BM7 - Fitout (Innenausbau) | 11/01/2021 | 14/01/2021 | 21/12/2020 | 12/02/2021 | 0 | TK_Complete | 1201082599 | 119 | 1201082599_119
A236880 | TT_Task | MPS Change from A2 to A04 due to Covid - BM 7 Innenausbau | 10/07/2020 | 23/10/2020 | 10/07/2020 | 11/11/2020 | 0 | TK_Complete | 1201082599 | 91 | 1201082599_91
COVID19 - 00018 | TT_Task | COVID19 - 00018 - Hanning and Kahl / Delivery delays to H;K | 02/02/2021 | 09/03/2021 | 02/02/2021 | 09/03/2021 | 0 | TK_Complete | 1201082599 | 120 | 1201082599_120
COVID19 - 198 | TT_Task | COVID19 - 00008 - Productivity losses in the white-collar sector at the Vienna site | 01/03/2021 | 22/03/2021 | 01/03/2021 | 22/03/2021 | 0 | TK_Complete | 1201082599 | 89 | 1201082599_89
COVID19 - 298 | TT_Task | COVID19 - 00006 - IFE / Delay in the production, testing and approval of color samples for the door leaf | 16/06/2020 | 12/08/2020 | 16/06/2020 | 12/08/2020 | 0 | TK_Complete | 1201082599 | 104 | 1201082599_104
COVID19 - 378 | TT_Task | COVID19 - 00010 - Short-time work at R2P.(12 Weeks) | 01/01/2020 | 25/03/2020 | 04/05/2020 | 27/07/2020 | 0 | TK_Complete | 1201082599 | 105 | 1201082599_105
COVID19 - 418 | TT_Task | COVID19 - 00011 - Closing KTP plant Tczew 4.5.-18.5.2020 and a 4 -day working week | 04/05/2020 | 04/05/2020 | 04/05/2020 | 15/05/2020 | 0 | TK_Complete | 1201082599 | 106 | 1201082599_106
COVID19 - 588 | TT_Task | COVID19 - 00016 - Monte Meao / Reduced production capactity and closures(Del Pas seats) | 16/04/2020 | 14/08/2020 | 16/04/2020 | 14/08/2020 | 0 | TK_Complete | 1201082599 | 107 | 1201082599_107
COVID19 - 98 | TT_Task | COVID19 - 00007 - Productivity losses at the manufacturing site in Vienna (For all vehicles) | 01/01/2020 | 08/01/2020 | 04/08/2020 | 11/08/2020 | 0 | TK_Complete | 1201082599 | 88 | 1201082599_88
A157850 | TT_Task | Trainset 01 BM3 - Carbody Production (Rohbau Produktion) | 01/09/2020 | 01/09/2020 | 01/07/2020 | 23/07/2020 | 0 | TK_Complete | 1201082599 | 121 | 1201082599_121
A236830 | TT_Task | MPS Change from A2 to A04 due to Covid - BM 3 Rohbau | 07/05/2020 | 01/09/2020 | 07/05/2020 | 01/09/2020 | 0 | TK_Complete | 1201082599 | 84 | 1201082599_84
COVID19 - 348 | TT_Task | COVID19 - 00009 - Bautzen / Poland and Czech Republic border closure, which prevented workers | 01/01/2020 | 08/01/2020 | 01/07/2020 | 08/07/2020 | 0 | TK_Complete | 1201082599 | 94 | 1201082599_94
COVID19 - 498 | TT_Task | COVID19 - 00013 - Hisarlar / Factory closure between 20.3.20 - 05.04.20 | 20/03/2020 | 20/03/2020 | 20/03/2020 | 05/04/2020 | 0 | TK_Complete | 1201082599 | 95 | 1201082599_95
COVID19 - 508 | TT_Task | COVID19 - 00014 - Duray / Factory closure between 27.3.20 - 13.04.20 | 27/03/2020 | 22/05/2020 | 27/03/2020 | 22/05/2020 | 0 | TK_Complete | 1201082599 | 96 | 1201082599_96
CW1050 | TT_Task | Trainset 01 BM3 - Transport from Goerlitz to Ceska Lipa | 05/11/2020 | 05/11/2020 | 11/08/2020 | 11/08/2020 | 0 | TK_Complete | 1201082599 | 122 | 1201082599_122
CWS1050 | TT_Task | Trainset 01 BM3 - Customer Inspection (Haltepunkt) | 01/01/2020 | 01/01/2020 | 24/07/2020 | 29/07/2020 | 0 | TK_Complete | 1201082599 | 115 | 1201082599_115
A157860 | TT_Task | Trainset 01 BM3 - Carbody Surface (Oberfl?che) | 06/11/2020 | 06/11/2020 | 11/08/2020 | 21/09/2020 | 0 | TK_Complete | 1201082599 | 123 | 1201082599_123
A236840 | TT_Task | MPS Change from A2 to A04 due to Covid - BM 3 Oberfl?che | 07/05/2020 | 31/08/2020 | 07/05/2020 | 01/09/2020 | 0 | TK_Complete | 1201082599 | 87 | 1201082599_87
COVID19 - 108 | TT_Task | COVID19 - 00007 - Productivity losses at the manufacturing site in Vienna (For all vehicles) | 01/01/2020 | 08/01/2020 | 04/08/2020 | 11/08/2020 | 0 | TK_Complete | 1201082599 | 88 | 1201082599_88
COVID19 - 188 | TT_Task | COVID19 - 00008 - Productivity losses in the white-collar sector at the Vienna site | 01/03/2021 | 22/03/2021 | 01/03/2021 | 22/03/2021 | 0 | TK_Complete | 1201082599 | 89 | 1201082599_89
COVID19 - 558 | TT_Task | COVID19 - 00015 - Rawag / Reduction in production capacity due to illness and quarentien | 14/07/2020 | 07/08/2020 | 14/07/2020 | 07/08/2020 | 0 | TK_Complete | 1201082599 | 100 | 1201082599_100
CW2310 | TT_Task | Trainset 01 BM3 - Transport from Ceska Lipa to Vienna | 31/12/2026 | 01/01/2027 | 21/09/2020 | 21/09/2020 | 0 | TK_Complete | 1201082599 | 124 | 1201082599_124
CW3570 | TT_Task | Trainset 01 BM3 - Bonding and Waxing (Kleben und Wachs) | 03/01/2020 | 03/01/2020 | 22/09/2020 | 06/11/2020 | 0 | TK_Complete | 1201082599 | 125 | 1201082599_125
A157870 | TT_Task | Trainset 01 BM3 - Fitout (Innenausbau) | 17/11/2020 | 14/01/2021 | 06/11/2020 | 12/02/2021 | 0 | TK_Complete | 1201082599 | 126 | 1201082599_126
A236850 | TT_Task | MPS Change from A2 to A04 due to Covid - BM 3 Innenausbau | 16/07/2020 | 13/10/2020 | 16/07/2020 | 30/10/2020 | 0 | TK_Complete | 1201082599 | 91 | 1201082599_91
COVID19 - 00017 | TT_Task | COVID19 - 00017 - Delimon / Covid delay | 18/12/2020 | 18/01/2021 | 18/12/2020 | 18/01/2021 | 0 | TK_Complete | 1201082599 | 127 | 1201082599_127
COVID19 - 118 | TT_Task | COVID19 - 00007 - Productivity losses at the manufacturing site in Vienna (For all vehicles) | 01/01/2020 | 08/01/2020 | 04/08/2020 | 11/08/2020 | 0 | TK_Complete | 1201082599 | 88 | 1201082599_88
COVID19 - 178 | TT_Task | COVID19 - 00008 - Productivity losses in the white-collar sector at the Vienna site | 01/03/2021 | 22/03/2021 | 01/03/2021 | 22/03/2021 | 0 | TK_Complete | 1201082599 | 89 | 1201082599_89
COVID19 - 308 | TT_Task | COVID19 - 00006 - IFE / Delay in the production, testing and approval of color samples for the door leaf | 16/06/2020 | 12/08/2020 | 16/06/2020 | 12/08/2020 | 0 | TK_Complete | 1201082599 | 104 | 1201082599_104
COVID19 - 388 | TT_Task | COVID19 - 00010 - Short-time work at R2P.(12 Weeks) | 01/01/2020 | 25/03/2020 | 04/05/2020 | 27/07/2020 | 0 | TK_Complete | 1201082599 | 105 | 1201082599_105
COVID19 - 428 | TT_Task | COVID19 - 00011 - Closing KTP plant Tczew 4.5.-18.5.2020 and a 4 -day working week | 04/05/2020 | 04/05/2020 | 04/05/2020 | 15/05/2020 | 0 | TK_Complete | 1201082599 | 106 | 1201082599_106
COVID19 - 598 | TT_Task | COVID19 - 00016 - Monte Meao / Reduced production capactity and closures(Del Pas seats) | 16/04/2020 | 14/08/2020 | 16/04/2020 | 14/08/2020 | 0 | TK_Complete | 1201082599 | 107 | 1201082599_107
COVID19 - 618 | TT_Task | COVID19 - 00018 - Hanning and Kahl / Delivery delays to H;K | 02/02/2021 | 09/03/2021 | 02/02/2021 | 09/03/2021 | 0 | TK_Complete | 1201082599 | 120 | 1201082599_120
A157910 | TT_Task | Trainset 01 BM1 - Carbody Production (Rohbau Produktion) | 02/09/2020 | 02/09/2020 | 23/06/2020 | 14/07/2020 | 0 | TK_Complete | 1201082599 | 128 | 1201082599_128
A236890 | TT_Task | MPS Change from A2 to A04 due to Covid - BM 1 Rohbau | 07/05/2020 | 01/09/2020 | 07/05/2020 | 01/09/2020 | 0 | TK_Complete | 1201082599 | 84 | 1201082599_84
COVID19 - 358 | TT_Task | COVID19 - 00009 - Bautzen / Poland and Czech Republic border closure, which prevented workers | 01/01/2020 | 08/01/2020 | 01/07/2020 | 08/07/2020 | 0 | TK_Complete | 1201082599 | 94 | 1201082599_94
COVID19 - 518 | TT_Task | COVID19 - 00013 - Hisarlar / Factory closure between 20.3.20 - 05.04.20 | 20/03/2020 | 20/03/2020 | 20/03/2020 | 05/04/2020 | 0 | TK_Complete | 1201082599 | 95 | 1201082599_95
COVID19 - 528 | TT_Task | COVID19 - 00014 - Duray / Factory closure between 27.3.20 - 13.04.20 | 27/03/2020 | 22/05/2020 | 27/03/2020 | 22/05/2020 | 0 | TK_Complete | 1201082599 | 96 | 1201082599_96
CW1070 | TT_Task | Trainset 01 BM1 - Transport from Goerlitz to Ceska Lipa | 30/10/2020 | 30/10/2020 | 15/07/2020 | 15/07/2020 | 0 | TK_Complete | 1201082599 | 129 | 1201082599_129
CWS1070 | TT_Task | Trainset 01 BM1 - Customer Inspection (Haltepunkt) | 01/01/2020 | 01/01/2020 | 14/07/2020 | 14/07/2020 | 0 | TK_Complete | 1201082599 | 115 | 1201082599_115
A157920 | TT_Task | Trainset 01 BM1 - Carbody Surface (Oberfl?che) | 02/11/2020 | 02/11/2020 | 15/07/2020 | 02/11/2020 | 0 | TK_Complete | 1201082599 | 123 | 1201082599_123
A236900 | TT_Task | MPS Change from A2 to A04 due to Covid - BM 1 Oberfl?che | 07/05/2020 | 31/08/2020 | 07/05/2020 | 01/09/2020 | 0 | TK_Complete | 1201082599 | 87 | 1201082599_87
COVID19 - 128 | TT_Task | COVID19 - 00007 - Productivity losses at the manufacturing site in Vienna (For all vehicles) | 01/01/2020 | 08/01/2020 | 04/08/2020 | 11/08/2020 | 0 | TK_Complete | 1201082599 | 88 | 1201082599_88
COVID19 - 168 | TT_Task | COVID19 - 00008 - Productivity losses in the white-collar sector at the Vienna site | 01/03/2021 | 22/03/2021 | 01/03/2021 | 22/03/2021 | 0 | TK_Complete | 1201082599 | 89 | 1201082599_89
COVID19 - 568 | TT_Task | COVID19 - 00015 - Rawag / Reduction in production capacity due to illness and quarentien | 14/07/2020 | 07/08/2020 | 14/07/2020 | 07/08/2020 | 0 | TK_Complete | 1201082599 | 100 | 1201082599_100
CW2330 | TT_Task | Trainset 01 BM1 - Transport from Ceska Lipa to Vienna | 02/11/2020 | 02/11/2020 | 02/11/2020 | 02/11/2020 | 0 | TK_Complete | 1201082599 | 130 | 1201082599_130
CW3590 | TT_Task | Trainset 01 BM1 - Bonding and Waxing (Kleben und Wachs) | 03/01/2020 | 03/01/2020 | 03/11/2020 | 27/11/2020 | 0 | TK_Complete | 1201082599 | 131 | 1201082599_131
A157930 | TT_Task | Trainset 01 BM1 - Fitout (Innenausbau) | 19/01/2021 | 15/02/2021 | 23/12/2020 | 18/02/2021 | 0 | TK_Complete | 1201082599 | 126 | 1201082599_126
A236910 | TT_Task | MPS Change from A2 to A04 due to Covid - BM 1 Innenausbau | 28/07/2020 | 05/11/2020 | 28/07/2020 | 23/11/2020 | 0 | TK_Complete | 1201082599 | 91 | 1201082599_91
COVID19 - 138 | TT_Task | COVID19 - 00007 - Productivity losses at the manufacturing site in Vienna (For all vehicles) | 01/01/2020 | 08/01/2020 | 04/08/2020 | 11/08/2020 | 0 | TK_Complete | 1201082599 | 88 | 1201082599_88
COVID19 - 158 | TT_Task | COVID19 - 00008 - Productivity losses in the white-collar sector at the Vienna site | 01/03/2021 | 22/03/2021 | 01/03/2021 | 22/03/2021 | 0 | TK_Complete | 1201082599 | 89 | 1201082599_89
COVID19 - 318 | TT_Task | COVID19 - 00006 - IFE / Delay in the production, testing and approval of color samples for the door leaf | 16/06/2020 | 12/08/2020 | 16/06/2020 | 12/08/2020 | 0 | TK_Complete | 1201082599 | 104 | 1201082599_104
COVID19 - 398 | TT_Task | COVID19 - 00010 - Short-time work at R2P.(12 Weeks) | 01/01/2020 | 25/03/2020 | 04/05/2020 | 27/07/2020 | 0 | TK_Complete | 1201082599 | 105 | 1201082599_105
COVID19 - 438 | TT_Task | COVID19 - 00011 - Closing KTP plant Tczew 4.5.-18.5.2020 and a 4 -day working week | 04/05/2020 | 04/05/2020 | 04/05/2020 | 15/05/2020 | 0 | TK_Complete | 1201082599 | 106 | 1201082599_106
COVID19 - 608 | TT_Task | COVID19 - 00016 - Monte Meao / Reduced production capactity and closures(Del Pas seats) | 16/04/2020 | 14/08/2020 | 16/04/2020 | 14/08/2020 | 0 | TK_Complete | 1201082599 | 107 | 1201082599_107
COVID19 - 628 | TT_Task | COVID19 - 00018 - Hanning and Kahl / Delivery delays to H;K | 02/02/2021 | 09/03/2021 | 02/02/2021 | 09/03/2021 | 0 | TK_Complete | 1201082599 | 120 | 1201082599_120
A157940 | TT_Task | Trainset 01 - Train Completion (Zugbildung ; Aufsetzen) | 15/02/2021 | 26/02/2021 | 15/02/2021 | 26/02/2021 | 0 | TK_Complete | 1201082599 | 132 | 1201082599_132
A157950 | TT_Task | Trainset 01 - Static Testing (Standpr?fungen ) | 01/03/2021 | 28/04/2021 | 03/03/2021 | 21/05/2021 | 0 | TK_Complete | 1201082599 | 133 | 1201082599_133
A157954 | TT_Task | Trainset 01 - Transport to RTA (Transport zu RTA) | 25/05/2021 | 26/05/2021 | 25/05/2021 | 26/05/2021 | 0 | TK_Complete | 1201082599 | 134 | 1201082599_134
A157955 | TT_Task | Trainset 01 - Activities in RTA - Climate Chamber (Aktivit?ten RTA - Klimakammer) | 27/05/2021 | 06/07/2021 | 27/05/2021 | 02/07/2021 | 0 | TK_Complete | 1201082599 | 135 | 1201082599_135
A157960 | TT_Task | Trainset 01 - Rework (Nacharbeiten / Vorbereitungshalle) | 05/07/2021 | 13/07/2021 | 05/07/2021 | 13/07/2021 | 0 | TK_Complete | 1201082599 | 136 | 1201082599_136
A157961 | TT_Task | Trainset 01 - Customer Factory Inspection + Rework (Werksabnahme +Nacharbeit) | 23/03/2022 | 29/03/2022 | 23/03/2022 | 28/03/2022 | 0 | TK_Complete | 1201082599 | 137 | 1201082599_137
A157962 | TT_Task | Trainset 01 - Transport to WL (Transport zu WL) | 14/07/2021 | 15/07/2021 | 14/07/2021 | 15/07/2021 | 0 | TK_Complete | 1201082599 | 79 | 1201082599_79
A157963 | TT_Task | Trainset 01 - Test at WL Simmering (Test bei WL Simmering) | 15/07/2021 | 31/08/2021 | 15/07/2021 | 21/12/2021 | 0 | TK_Complete | 1201082599 | 138 | 1201082599_138
A157964 | TT_Task | Trainset 01 - Transport from Factory to WLB (Transport von AT zu WLB) | 12/04/2022 | 12/04/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 79 | 1201082599_79
A157970 | TT_Task | Trainset 01 - Customer Tests (IBN am Erf?lungsort) | 05/05/2022 | 23/05/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 139 | 1201082599_139
A157980 | TT_Task | Trainset 01 - Preliminary Customer Acceptance (Kundenabnahme) | 24/05/2022 | 25/05/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 140 | 1201082599_140
A157990 | TT_Task | Trainset 01 - Trial Period (Probebetrieb) | 29/09/2022 | 07/01/2023 | nan | nan | 0 | TK_NotStart | 1201082599 | 141 | 1201082599_141
A158000 | TT_Task | Trainset 01 - ATA notification trial operation complete and defect free (Meldung Probebetrieb bestanden und Mangelfrei) | 09/01/2023 | 11/01/2023 | nan | nan | 0 | TK_NotStart | 1201082599 | 142 | 1201082599_142
A236920 | TT_Task | MPS Change from A2 to A04 due to Covid - Train Completion | 14/09/2020 | 11/12/2020 | 14/09/2020 | 23/12/2020 | 0 | TK_Complete | 1201082599 | 91 | 1201082599_91
A239232 | TT_Task | Trainset 01 - Transport from WL to Factory for Retrofit (Transport von WL zu AT) | 22/12/2021 | 22/12/2021 | 22/12/2021 | 22/12/2021 | 0 | TK_Complete | 1201082599 | 79 | 1201082599_79
A239242 | TT_Task | Trainset 01 - Retrofit bei AT | 23/12/2021 | 24/01/2022 | 10/01/2022 | 25/01/2022 | 0 | TK_Complete | 1201082599 | 143 | 1201082599_143
A239252 | TT_Task | Trainset 01 - Re-Testing (IBN) +Finishing | 25/01/2022 | 16/02/2022 | 25/01/2022 | 25/02/2022 | 0 | TK_Complete | 1201082599 | 144 | 1201082599_144
A239272 | TT_Task | Trainset 01 - Quality Inspection +Rework (Q-Abnahme + Nachartbeit) | 28/02/2022 | 03/03/2022 | 28/02/2022 | 22/03/2022 | 0 | TK_Complete | 1201082599 | 145 | 1201082599_145
A239502 | TT_Task | Trainset 01 - Abstellen Werk 501 | 28/03/2022 | 11/04/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 146 | 1201082599_146
COVID19 - 00008 | TT_Task | COVID19 - 00008 - Productivity losses in the white-collar sector at the Vienna site | 01/03/2021 | 22/03/2021 | 01/03/2021 | 22/03/2021 | 0 | TK_Complete | 1201082599 | 89 | 1201082599_89
COVID19 - 148 | TT_Task | COVID19 - 00007 - Productivity losses at the manufacturing site in Vienna (For all vehicles) | 01/01/2020 | 08/01/2020 | 04/08/2020 | 11/08/2020 | 0 | TK_Complete | 1201082599 | 88 | 1201082599_88
PAYM10210 | TT_Task | WLB Approval to Start Trial Operation (Freigabe zum Probebetrieb) 01 | 30/05/2022 | 30/05/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 147 | 1201082599_147
A158030 | TT_Task | Trainset 02 CM7 - Carbody Surface (Oberfl?che) | 30/11/2020 | 11/03/2021 | 03/02/2021 | 26/03/2021 | 0 | TK_Complete | 1201082599 | 86 | 1201082599_86
A158040 | TT_Task | Trainset 02 CM7 - Fitout (Innenausbau) | 17/03/2021 | 07/04/2021 | 29/03/2021 | 20/04/2021 | 0 | TK_Complete | 1201082599 | 90 | 1201082599_90
CWS1080 | TT_Task | Trainset 02 CM7 - Customer Inspection (Haltepunkt) | 01/01/2020 | 01/01/2020 | 27/11/2020 | 27/11/2020 | 0 | TK_Complete | 1201082599 | 85 | 1201082599_85
A158060 | TT_Task | Trainset 02 CM1 - Carbody Surface (Oberfl?che) | 29/01/2021 | 03/03/2021 | 03/02/2021 | 06/04/2021 | 0 | TK_Complete | 1201082599 | 86 | 1201082599_86
A158070 | TT_Task | Trainset 02 CM1 - Fitout (Innenausbau) | 19/03/2021 | 09/04/2021 | 07/04/2021 | 28/04/2021 | 0 | TK_Complete | 1201082599 | 90 | 1201082599_90
CWS1090 | TT_Task | Trainset 02 CM1 - Customer Inspection (Haltepunkt) | 12/11/2020 | 12/11/2020 | 18/01/2021 | 18/01/2021 | 0 | TK_Complete | 1201082599 | 85 | 1201082599_85
A158080 | TT_Task | Trainset 02 SM6 - Carbody Production (Rohbau Produktion) | 11/01/2021 | 11/01/2021 | 29/06/2020 | 29/07/2020 | 0 | TK_Complete | 1201082599 | 93 | 1201082599_93
A158090 | TT_Task | Trainset 02 SM6 - Carbody Surface (Oberfl?che) | 12/01/2021 | 12/01/2021 | 10/08/2020 | 08/01/2021 | 0 | TK_Complete | 1201082599 | 99 | 1201082599_99
A158100 | TT_Task | Trainset 02 SM6 - Fitout (Innenausbau) | 03/03/2021 | 07/04/2021 | 17/03/2021 | 12/04/2021 | 0 | TK_Complete | 1201082599 | 103 | 1201082599_103
CW1100 | TT_Task | Trainset 02 SM6 - Transport from Goerlitz to Ceska Lipa | 11/01/2021 | 11/01/2021 | 10/08/2020 | 10/08/2020 | 0 | TK_Complete | 1201082599 | 97 | 1201082599_97
CW2360 | TT_Task | Trainset 02 SM6 - Transport from Ceska Lipa to Vienna | 13/01/2021 | 13/01/2021 | 11/01/2021 | 11/01/2021 | 0 | TK_Complete | 1201082599 | 101 | 1201082599_101
CW3620 | TT_Task | Trainset 02 SM6 - Bonding and Waxing (Kleben und Wachs) | 12/01/2021 | 19/01/2021 | 27/01/2021 | 16/03/2021 | 0 | TK_Complete | 1201082599 | 102 | 1201082599_102
CWS1100 | TT_Task | Trainset 02 SM6 - Customer Inspection (Haltepunkt) | 11/01/2021 | 11/01/2021 | 28/07/2020 | 29/07/2020 | 0 | TK_Complete | 1201082599 | 98 | 1201082599_98
A158110 | TT_Task | Trainset 02 SM2 - Carbody Production (Rohbau Produktion) | 15/01/2021 | 15/01/2021 | 13/10/2020 | 11/11/2020 | 0 | TK_Complete | 1201082599 | 108 | 1201082599_108
A158120 | TT_Task | Trainset 02 SM2 - Carbody Surface (Oberfl?che) | 12/11/2020 | 12/11/2020 | 20/11/2020 | 02/02/2021 | 0 | TK_Complete | 1201082599 | 99 | 1201082599_99
A158130 | TT_Task | Trainset 02 SM2 - Fitout (Innenausbau) | 11/03/2021 | 14/04/2021 | 17/03/2021 | 14/04/2021 | 0 | TK_Complete | 1201082599 | 103 | 1201082599_103
CW1110 | TT_Task | Trainset 02 SM2 - Transport from Goerlitz to Ceska Lipa | 11/11/2020 | 11/11/2020 | 20/11/2020 | 20/11/2020 | 0 | TK_Complete | 1201082599 | 109 | 1201082599_109
CW2370 | TT_Task | Trainset 02 SM2 - Transport from Ceska Lipa to Vienna | 03/02/2021 | 03/02/2021 | 03/02/2021 | 03/02/2021 | 0 | TK_Complete | 1201082599 | 111 | 1201082599_111
CW3630 | TT_Task | Trainset 02 SM2 - Bonding and Waxing (Kleben und Wachs) | 03/02/2021 | 23/02/2021 | 04/02/2021 | 16/03/2021 | 0 | TK_Complete | 1201082599 | 112 | 1201082599_112
CWS1110 | TT_Task | Trainset 02 SM2 - Customer Inspection (Haltepunkt) | 15/01/2021 | 15/01/2021 | 11/11/2020 | 11/11/2020 | 0 | TK_Complete | 1201082599 | 110 | 1201082599_110
A158170 | TT_Task | Trainset 02 BM7 - Carbody Production (Rohbau Produktion) | 11/01/2021 | 11/01/2021 | 08/07/2020 | 29/07/2020 | 0 | TK_Complete | 1201082599 | 113 | 1201082599_113
A158180 | TT_Task | Trainset 02 BM7 - Carbody Surface (Oberfl?che) | 12/01/2021 | 12/01/2021 | 10/08/2020 | 08/01/2021 | 0 | TK_Complete | 1201082599 | 116 | 1201082599_116
A158190 | TT_Task | Trainset 02 BM7 - Fitout (Innenausbau) | 26/03/2021 | 02/04/2021 | 31/03/2021 | 20/04/2021 | 0 | TK_Complete | 1201082599 | 119 | 1201082599_119
CW1130 | TT_Task | Trainset 02 BM7 - Transport from Goerlitz to Ceska Lipa | 11/01/2021 | 11/01/2021 | 10/08/2020 | 10/08/2020 | 0 | TK_Complete | 1201082599 | 114 | 1201082599_114
CW2390 | TT_Task | Trainset 02 BM7 - Transport from Ceska Lipa to Vienna | 13/01/2021 | 13/01/2021 | 11/01/2021 | 11/01/2021 | 0 | TK_Complete | 1201082599 | 117 | 1201082599_117
CW3650 | TT_Task | Trainset 02 BM7 - Bonding and Waxing (Kleben und Wachs) | 12/01/2021 | 19/01/2021 | 27/01/2021 | 29/03/2021 | 0 | TK_Complete | 1201082599 | 118 | 1201082599_118
CWS1130 | TT_Task | Trainset 02 BM7 - Customer Inspection (Haltepunkt) | 11/01/2021 | 11/01/2021 | 28/07/2020 | 29/07/2020 | 0 | TK_Complete | 1201082599 | 115 | 1201082599_115
A158140 | TT_Task | Trainset 02 BM3 - Carbody Production (Rohbau Produktion) | 15/01/2021 | 15/01/2021 | 16/10/2020 | 11/11/2020 | 0 | TK_Complete | 1201082599 | 121 | 1201082599_121
A158150 | TT_Task | Trainset 02 BM3 - Carbody Surface (Oberfl?che) | 18/01/2021 | 18/01/2021 | 16/11/2020 | 08/02/2021 | 0 | TK_Complete | 1201082599 | 123 | 1201082599_123
A158160 | TT_Task | Trainset 02 BM3 - Fitout (Innenausbau) | 08/03/2021 | 07/04/2021 | 12/03/2021 | 21/04/2021 | 0 | TK_Complete | 1201082599 | 126 | 1201082599_126
CW1120 | TT_Task | Trainset 02 BM3 - Transport from Goerlitz to Ceska Lipa | 15/01/2021 | 15/01/2021 | 16/11/2020 | 16/11/2020 | 0 | TK_Complete | 1201082599 | 122 | 1201082599_122
CW2380 | TT_Task | Trainset 02 BM3 - Transport from Ceska Lipa to Vienna | 09/02/2021 | 09/02/2021 | 09/02/2021 | 09/02/2021 | 0 | TK_Complete | 1201082599 | 124 | 1201082599_124
CW3640 | TT_Task | Trainset 02 BM3 - Bonding and Waxing (Kleben und Wachs) | 09/02/2021 | 12/02/2021 | 10/02/2021 | 11/03/2021 | 0 | TK_Complete | 1201082599 | 125 | 1201082599_125
CWS1120 | TT_Task | Trainset 02 BM3 - Customer Inspection (Haltepunkt) | 15/01/2021 | 15/01/2021 | 11/11/2020 | 11/11/2020 | 0 | TK_Complete | 1201082599 | 115 | 1201082599_115
A158200 | TT_Task | Trainset 02 BM1 - Carbody Production (Rohbau Produktion) | 21/01/2021 | 21/01/2021 | 20/10/2020 | 11/11/2020 | 0 | TK_Complete | 1201082599 | 128 | 1201082599_128
A158210 | TT_Task | Trainset 02 BM1 - Carbody Surface (Oberfl?che) | 22/01/2021 | 22/01/2021 | 16/11/2020 | 02/02/2021 | 0 | TK_Complete | 1201082599 | 123 | 1201082599_123
A158220 | TT_Task | Trainset 02 BM1 - Fitout (Innenausbau) | 24/02/2021 | 02/04/2021 | 24/03/2021 | 23/04/2021 | 0 | TK_Complete | 1201082599 | 126 | 1201082599_126
CW1140 | TT_Task | Trainset 02 BM1 - Transport from Goerlitz to Ceska Lipa | 21/01/2021 | 21/01/2021 | 16/11/2020 | 16/11/2020 | 0 | TK_Complete | 1201082599 | 129 | 1201082599_129
CW2400 | TT_Task | Trainset 02 BM1 - Transport from Ceska Lipa to Vienna | 15/02/2021 | 15/02/2021 | 03/02/2021 | 03/02/2021 | 0 | TK_Complete | 1201082599 | 130 | 1201082599_130
CW3660 | TT_Task | Trainset 02 BM1 - Bonding and Waxing (Kleben und Wachs) | 15/02/2021 | 22/02/2021 | 04/02/2021 | 23/03/2021 | 0 | TK_Complete | 1201082599 | 131 | 1201082599_131
CWS1140 | TT_Task | Trainset 02 BM1 - Customer Inspection (Haltepunkt) | 21/01/2021 | 21/01/2021 | 11/11/2020 | 11/11/2020 | 0 | TK_Complete | 1201082599 | 115 | 1201082599_115
A158230 | TT_Task | Trainset 02 - Train Completion (Zugbildung ; Aufsetzen) | 22/04/2021 | 04/05/2021 | 22/04/2021 | 04/05/2021 | 0 | TK_Complete | 1201082599 | 132 | 1201082599_132
A158240 | TT_Task | Trainset 02 - Static Testing - Pre- tests(Standpr?fungen - Vorpruefungen) | 05/05/2021 | 17/05/2021 | 05/05/2021 | 17/05/2021 | 0 | TK_Complete | 1201082599 | 133 | 1201082599_133
A158245 | TT_Task | Trainset 02 - Functional Testing with Software (Funktionspr?fung mit FZ-Software) | 18/05/2021 | 31/05/2021 | 18/05/2021 | 11/06/2021 | 0 | TK_Complete | 1201082599 | 148 | 1201082599_148
A158247 | TT_Task | Trainset 02 - Dynamic Test and Mech Test (Streckenpr?fungen and Mech Test) | 14/06/2021 | 25/06/2021 | 14/06/2021 | 25/06/2021 | 0 | TK_Complete | 1201082599 | 149 | 1201082599_149
A158250 | TT_Task | Trainset 02 - Rework (Restarbeiten) | 25/06/2021 | 01/07/2021 | 25/06/2021 | 01/07/2021 | 0 | TK_Complete | 1201082599 | 150 | 1201082599_150
A158253 | TT_Task | Trainset 02 - Customer Factory Inspection (Werksabnahme) | 02/07/2021 | 06/07/2021 | 02/07/2021 | 06/07/2021 | 0 | TK_Complete | 1201082599 | 151 | 1201082599_151
A158260 | TT_Task | Trainset 02 - First Customer Tests (Erste Test beim Kunden) | 21/12/2021 | 08/02/2022 | 21/12/2021 | nan | 0 | TK_Active | 1201082599 | 152 | 1201082599_152
A158270 | TT_Task | Trainset 02 - Preliminary Customer Acceptance (Kundenabnahme) | 22/09/2022 | 23/09/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 140 | 1201082599_140
A158280 | TT_Task | Trainset 02 - Trial Period (Probebetrieb) | 29/09/2022 | 07/01/2023 | nan | nan | 0 | TK_NotStart | 1201082599 | 141 | 1201082599_141
A158290 | TT_Task | Trainset 02 - ATA notification trial operation complete and defect free (Meldung Probebetrieb bestanden und Mangelfrei) | 09/01/2023 | 11/01/2023 | nan | nan | 0 | TK_NotStart | 1201082599 | 142 | 1201082599_142
A236922 | TT_Task | Trainset 02 - Transport to Customer (Transport zum Kunden) | 20/12/2021 | 20/12/2021 | 20/12/2021 | 20/12/2021 | 0 | TK_Complete | 1201082599 | 153 | 1201082599_153
A237012 | TT_Task | Trainset 02 - Transport to WL (Transport zu WL) | 06/07/2021 | 07/07/2021 | 06/07/2021 | 07/07/2021 | 0 | TK_Complete | 1201082599 | 79 | 1201082599_79
A237022 | TT_Task | Trainset 02 - Test at WL (Test bei WL) | 07/07/2021 | 03/11/2021 | 07/07/2021 | 17/12/2021 | 0 | TK_Complete | 1201082599 | 138 | 1201082599_138
A239192 | TT_Task | Trainset 02 - Transport back from WLB to AT for Retrofit (Transport zu AT) | 31/05/2022 | 31/05/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 154 | 1201082599_154
A239202 | TT_Task | Trainset 02 - Retrofit bei AT | 01/06/2022 | 24/06/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 143 | 1201082599_143
A239212 | TT_Task | Trainset 02 - Transport back to WLB after Retrofit (Transport zu WLB) | 31/08/2022 | 31/08/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 154 | 1201082599_154
A239222 | TT_Task | Trainset 02 - Customer Tests (IBN am Erf?lungsort) | 01/09/2022 | 21/09/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 139 | 1201082599_139
A239312 | TT_Task | Trainset 02 - Re-Testing (IBN) +Finishing | 27/06/2022 | 18/07/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 144 | 1201082599_144
A239332 | TT_Task | Trainset 02 - Quality Inspection +Rework (Q-Abnahme + Nachartbeit) | 19/07/2022 | 21/07/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 145 | 1201082599_145
A239352 | TT_Task | Trainset 02 - Customer Factory Inspection + Rework (Werksabnahme +Nacharbeit) | 22/07/2022 | 29/07/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 137 | 1201082599_137
A239512 | TT_Task | Trainset 02 - Abstellen Werk 502 | 01/08/2022 | 30/08/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 146 | 1201082599_146
PAYM10220 | TT_Task | WLB Approval to Start Trial Operation (Freigabe zum Probebetrieb) 02 | 26/09/2022 | 26/09/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 147 | 1201082599_147
A158320 | TT_Task | Trainset 03 CM7 - Carbody Surface (Oberfl?che) | 22/02/2021 | 01/04/2021 | 23/02/2021 | 26/05/2021 | 0 | TK_Complete | 1201082599 | 86 | 1201082599_86
A158330 | TT_Task | Trainset 03 CM7 - Fitout (Innenausbau) | 19/05/2021 | 31/05/2021 | 26/05/2021 | 30/06/2021 | 0 | TK_Complete | 1201082599 | 90 | 1201082599_90
CWS1150 | TT_Task | Trainset 03 CM7 - Customer Inspection (Haltepunkt) | 15/02/2021 | 15/02/2021 | 22/02/2021 | 22/02/2021 | 0 | TK_Complete | 1201082599 | 85 | 1201082599_85
A158350 | TT_Task | Trainset 03 CM1 - Carbody Surface (Oberfl?che) | 22/02/2021 | 01/04/2021 | 23/02/2021 | 07/06/2021 | 0 | TK_Complete | 1201082599 | 86 | 1201082599_86
A158360 | TT_Task | Trainset 03 CM1 - Fitout (Innenausbau) | 07/06/2021 | 16/06/2021 | 07/06/2021 | 06/07/2021 | 0 | TK_Complete | 1201082599 | 90 | 1201082599_90
CWS1160 | TT_Task | Trainset 03 CM1 - Customer Inspection (Haltepunkt) | 01/04/2021 | 01/04/2021 | 22/02/2021 | 22/02/2021 | 0 | TK_Complete | 1201082599 | 85 | 1201082599_85
A158370 | TT_Task | Trainset 03 SM6 - Carbody Production (Rohbau Produktion) | 14/01/2021 | 02/02/2021 | 14/01/2021 | 04/02/2021 | 0 | TK_Complete | 1201082599 | 93 | 1201082599_93
A158380 | TT_Task | Trainset 03 SM6 - Carbody Surface (Oberfl?che) | 16/02/2021 | 29/03/2021 | 16/02/2021 | 07/03/2021 | 0 | TK_Complete | 1201082599 | 99 | 1201082599_99
A158390 | TT_Task | Trainset 03 SM6 - Fitout (Innenausbau) | 21/04/2021 | 28/05/2021 | 22/04/2021 | 29/06/2021 | 0 | TK_Complete | 1201082599 | 103 | 1201082599_103
CW1170 | TT_Task | Trainset 03 SM6 - Transport from Goerlitz to Ceska Lipa | 08/02/2021 | 08/02/2021 | 16/02/2021 | 16/02/2021 | 0 | TK_Complete | 1201082599 | 97 | 1201082599_97
CW2430 | TT_Task | Trainset 03 SM6 - Transport from Ceska Lipa to Vienna | 05/03/2021 | 05/03/2021 | 08/03/2021 | 08/03/2021 | 0 | TK_Complete | 1201082599 | 101 | 1201082599_101
CW3690 | TT_Task | Trainset 03 SM6 - Bonding and Waxing (Kleben und Wachs) | 08/03/2021 | 16/03/2021 | 18/03/2021 | 21/04/2021 | 0 | TK_Complete | 1201082599 | 102 | 1201082599_102
CWS1170 | TT_Task | Trainset 03 SM6 - Customer Inspection (Haltepunkt) | 29/01/2021 | 02/02/2021 | 29/01/2021 | 04/02/2021 | 0 | TK_Complete | 1201082599 | 98 | 1201082599_98
A158400 | TT_Task | Trainset 03 SM2 - Carbody Production (Rohbau Produktion) | 27/01/2021 | 09/02/2021 | 27/01/2021 | 11/02/2021 | 0 | TK_Complete | 1201082599 | 108 | 1201082599_108
A158410 | TT_Task | Trainset 03 SM2 - Carbody Surface (Oberfl?che) | 17/02/2021 | 12/04/2021 | 16/02/2021 | 07/03/2021 | 0 | TK_Complete | 1201082599 | 99 | 1201082599_99
A158420 | TT_Task | Trainset 03 SM2 - Fitout (Innenausbau) | 07/06/2021 | 25/06/2021 | 26/05/2021 | 05/07/2021 | 0 | TK_Complete | 1201082599 | 103 | 1201082599_103
CW1180 | TT_Task | Trainset 03 SM2 - Transport from Goerlitz to Ceska Lipa | 12/02/2021 | 12/02/2021 | 17/02/2021 | 17/02/2021 | 0 | TK_Complete | 1201082599 | 109 | 1201082599_109
CW2440 | TT_Task | Trainset 03 SM2 - Transport from Ceska Lipa to Vienna | 01/04/2021 | 01/04/2021 | 17/03/2021 | 17/03/2021 | 0 | TK_Complete | 1201082599 | 111 | 1201082599_111
CW3700 | TT_Task | Trainset 03 SM2 - Bonding and Waxing (Kleben und Wachs) | 03/03/2021 | 20/04/2021 | 18/03/2021 | 25/05/2021 | 0 | TK_Complete | 1201082599 | 112 | 1201082599_112
CWS1180 | TT_Task | Trainset 03 SM2 - Customer Inspection (Haltepunkt) | 09/02/2021 | 09/02/2021 | 11/02/2021 | 11/02/2021 | 0 | TK_Complete | 1201082599 | 110 | 1201082599_110
A158460 | TT_Task | Trainset 03 BM7 - Carbody Production (Rohbau Produktion) | 15/01/2021 | 02/02/2021 | 15/01/2021 | 04/02/2021 | 0 | TK_Complete | 1201082599 | 113 | 1201082599_113
A158470 | TT_Task | Trainset 03 BM7 - Carbody Surface (Oberfl?che) | 08/02/2021 | 08/03/2021 | 08/02/2021 | 08/03/2021 | 0 | TK_Complete | 1201082599 | 116 | 1201082599_116
A158480 | TT_Task | Trainset 03 BM7 - Fitout (Innenausbau) | 19/05/2021 | 16/06/2021 | 19/05/2021 | 02/07/2021 | 0 | TK_Complete | 1201082599 | 119 | 1201082599_119
CW1200 | TT_Task | Trainset 03 BM7 - Transport from Goerlitz to Ceska Lipa | 08/02/2021 | 08/02/2021 | 08/02/2021 | 08/02/2021 | 0 | TK_Complete | 1201082599 | 114 | 1201082599_114
CW2460 | TT_Task | Trainset 03 BM7 - Transport from Ceska Lipa to Vienna | 02/03/2021 | 02/03/2021 | 09/03/2021 | 09/03/2021 | 0 | TK_Complete | 1201082599 | 117 | 1201082599_117
CW3720 | TT_Task | Trainset 03 BM7 - Bonding and Waxing (Kleben und Wachs) | 04/03/2021 | 15/03/2021 | 16/03/2021 | 19/05/2021 | 0 | TK_Complete | 1201082599 | 118 | 1201082599_118
CWS1200 | TT_Task | Trainset 03 BM7 - Customer Inspection (Haltepunkt) | 02/02/2021 | 02/02/2021 | 02/02/2021 | 04/02/2021 | 0 | TK_Complete | 1201082599 | 115 | 1201082599_115
A158430 | TT_Task | Trainset 03 BM3 - Carbody Production (Rohbau Produktion) | 21/01/2021 | 09/02/2021 | 21/01/2021 | 04/02/2021 | 0 | TK_Complete | 1201082599 | 121 | 1201082599_121
A158440 | TT_Task | Trainset 03 BM3 - Carbody Surface (Oberfl?che) | 08/02/2021 | 08/03/2021 | 08/02/2021 | 08/03/2021 | 0 | TK_Complete | 1201082599 | 123 | 1201082599_123
A158450 | TT_Task | Trainset 03 BM3 - Fitout (Innenausbau) | 21/05/2021 | 14/06/2021 | 21/05/2021 | 06/07/2021 | 0 | TK_Complete | 1201082599 | 126 | 1201082599_126
CW1190 | TT_Task | Trainset 03 BM3 - Transport from Goerlitz to Ceska Lipa | 12/02/2021 | 12/02/2021 | 08/02/2021 | 08/02/2021 | 0 | TK_Complete | 1201082599 | 122 | 1201082599_122
CW2450 | TT_Task | Trainset 03 BM3 - Transport from Ceska Lipa to Vienna | 02/03/2021 | 02/03/2021 | 09/03/2021 | 09/03/2021 | 0 | TK_Complete | 1201082599 | 124 | 1201082599_124
CW3710 | TT_Task | Trainset 03 BM3 - Bonding and Waxing (Kleben und Wachs) | 02/03/2021 | 11/03/2021 | 17/03/2021 | 20/05/2021 | 0 | TK_Complete | 1201082599 | 125 | 1201082599_125
CWS1190 | TT_Task | Trainset 03 BM3 - Customer Inspection (Haltepunkt) | 08/02/2021 | 09/02/2021 | 04/02/2021 | 04/02/2021 | 0 | TK_Complete | 1201082599 | 115 | 1201082599_115
A158490 | TT_Task | Trainset 03 BM1 - Carbody Production (Rohbau Produktion) | 28/01/2021 | 11/02/2021 | 28/01/2021 | 11/02/2021 | 0 | TK_Complete | 1201082599 | 128 | 1201082599_128
A158500 | TT_Task | Trainset 03 BM1 - Carbody Surface (Oberfl?che) | 17/02/2021 | 31/03/2021 | 17/02/2021 | 15/03/2021 | 0 | TK_Complete | 1201082599 | 123 | 1201082599_123
A158510 | TT_Task | Trainset 03 BM1 - Fitout (Innenausbau) | 28/05/2021 | 18/06/2021 | 28/05/2021 | 09/07/2021 | 0 | TK_Complete | 1201082599 | 126 | 1201082599_126
CW1210 | TT_Task | Trainset 03 BM1 - Transport from Goerlitz to Ceska Lipa | 16/02/2021 | 16/02/2021 | 17/02/2021 | 17/02/2021 | 0 | TK_Complete | 1201082599 | 129 | 1201082599_129
CW2470 | TT_Task | Trainset 03 BM1 - Transport from Ceska Lipa to Vienna | 01/04/2021 | 01/04/2021 | 16/03/2021 | 16/03/2021 | 0 | TK_Complete | 1201082599 | 130 | 1201082599_130
CW3730 | TT_Task | Trainset 03 BM1 - Bonding and Waxing (Kleben und Wachs) | 16/03/2021 | 19/04/2021 | 18/03/2021 | 27/05/2021 | 0 | TK_Complete | 1201082599 | 131 | 1201082599_131
CWS1210 | TT_Task | Trainset 03 BM1 - Customer Inspection (Haltepunkt) | 11/02/2021 | 11/02/2021 | 11/02/2021 | 11/02/2021 | 0 | TK_Complete | 1201082599 | 115 | 1201082599_115
A158520 | TT_Task | Trainset 03 - Train Completion (Zugbildung ; Aufsetzen) | 06/07/2021 | 15/07/2021 | 06/07/2021 | 02/08/2021 | 0 | TK_Complete | 1201082599 | 132 | 1201082599_132
A158530 | TT_Task | Trainset 03 - Static Testing (Standpr?fungen ) | 09/08/2021 | 30/08/2021 | 02/08/2021 | 03/09/2021 | 0 | TK_Complete | 1201082599 | 133 | 1201082599_133
A158540 | TT_Task | Trainset 03 - Rework (Restarbeiten) | 16/09/2021 | 23/09/2021 | 16/09/2021 | 23/09/2021 | 0 | TK_Complete | 1201082599 | 150 | 1201082599_150
A158550 | TT_Task | Trainset 03 - Customer Tests (IBN am Erf?lungsort) | 24/03/2022 | 13/04/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 139 | 1201082599_139
A158560 | TT_Task | Trainset 03 - Preliminary Customer Acceptance (Kundenabnahme) | 14/04/2022 | 15/04/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 140 | 1201082599_140
A158570 | TT_Task | Trainset 03 - Trial Period (Probebetrieb) | 01/10/2022 | 09/01/2023 | nan | nan | 0 | TK_NotStart | 1201082599 | 141 | 1201082599_141
A158580 | TT_Task | Trainset 03 - ATA notification trial operation complete and defect free (Meldung Probebetrieb bestanden und Mangelfrei) | 10/01/2023 | 12/01/2023 | nan | nan | 0 | TK_NotStart | 1201082599 | 142 | 1201082599_142
A236932 | TT_Task | Trainset 03 - Serial Dynamic Testing (Serientests dynamisch) | 06/09/2021 | 14/09/2021 | 06/09/2021 | 14/09/2021 | 0 | TK_Complete | 1201082599 | 155 | 1201082599_155
A236942 | TT_Task | Trainset 03 - Mechanical Testing (Mech. Tests) | 15/09/2021 | 15/09/2021 | 15/09/2021 | 15/09/2021 | 0 | TK_Complete | 1201082599 | 149 | 1201082599_149
A236952 | TT_Task | Trainset 03 - Customer Factory Inspection (Werksabnahme) | 24/09/2021 | 28/09/2021 | 24/09/2021 | 28/09/2021 | 0 | TK_Complete | 1201082599 | 151 | 1201082599_151
A236982 | TT_Task | Trainset 03 - Transport to Customer (Transport zum Kunden) | 29/09/2021 | 29/09/2021 | 29/09/2021 | 29/09/2021 | 0 | TK_Complete | 1201082599 | 153 | 1201082599_153
A239372 | TT_Task | Trainset 03 - Retrofit bei WLB | 10/03/2022 | 23/03/2022 | nan | nan | 120 | TK_NotStart | 1201082599 | 143 | 1201082599_143
A239442 | TT_Task | Trainset 03 - Betriebsfestigkeitsnachweis | 17/01/2022 | 03/03/2022 | 17/01/2022 | nan | 0 | TK_Active | 1201082599 | 156 | 1201082599_156
A239522 | TT_Task | Trainset 03 - ?berstellungsfahrt WLB 503 -1 | 19/04/2022 | 19/04/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 157 | 1201082599_157
A239532 | TT_Task | Trainset 03 - Abstellen WL 503 | 19/04/2022 | 20/04/2022 | nan | nan | 872 | TK_NotStart | 1201082599 | 158 | 1201082599_158
A239542 | TT_Task | Trainset 03 - ?berstellungsfahrt WLB 503 -2 | 30/09/2022 | 30/09/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 157 | 1201082599_157
PAYM10050 | TT_Task | WLB Approval Vehicle Delivery (Freigabe zur ?berstellung) 03 | 14/04/2022 | 14/04/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 159 | 1201082599_159
PAYM10230 | TT_Task | WLB Approval to Start Trial Operation (Freigabe zum Probebetrieb) 03 | 30/09/2022 | 30/09/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 147 | 1201082599_147
A158610 | TT_Task | Trainset 04 CM7 - Carbody Surface (Oberfl?che) | 26/05/2021 | 18/06/2021 | 01/06/2021 | 08/07/2021 | 0 | TK_Complete | 1201082599 | 86 | 1201082599_86
A158620 | TT_Task | Trainset 04 CM7 - Fitout (Innenausbau) | 28/06/2021 | 07/07/2021 | 08/07/2021 | 08/09/2021 | 0 | TK_Complete | 1201082599 | 90 | 1201082599_90
A158640 | TT_Task | Trainset 04 CM1 - Carbody Surface (Oberfl?che) | 01/06/2021 | 24/06/2021 | 01/06/2021 | 28/07/2021 | 0 | TK_Complete | 1201082599 | 86 | 1201082599_86
A158650 | TT_Task | Trainset 04 CM1 - Fitout (Innenausbau) | 15/07/2021 | 25/08/2021 | 16/08/2021 | 20/09/2021 | 0 | TK_Complete | 1201082599 | 90 | 1201082599_90
A158660 | TT_Task | Trainset 04 SM6 - Carbody Production (Rohbau Produktion) | 03/05/2021 | 10/05/2021 | 03/05/2021 | 21/05/2021 | 0 | TK_Complete | 1201082599 | 93 | 1201082599_93
A158670 | TT_Task | Trainset 04 SM6 - Carbody Surface (Oberfl?che) | 03/06/2021 | 02/07/2021 | 03/06/2021 | 28/06/2021 | 0 | TK_Complete | 1201082599 | 99 | 1201082599_99
A158680 | TT_Task | Trainset 04 SM6 - Fitout (Innenausbau) | 20/07/2021 | 12/08/2021 | 06/08/2021 | 31/08/2021 | 0 | TK_Complete | 1201082599 | 103 | 1201082599_103
CW1240 | TT_Task | Trainset 04 SM6 - Transport from Goerlitz to Ceska Lipa | 03/06/2021 | 03/06/2021 | 03/06/2021 | 03/06/2021 | 0 | TK_Complete | 1201082599 | 97 | 1201082599_97
CW2500 | TT_Task | Trainset 04 SM6 - Transport from Ceska Lipa to Vienna | 02/07/2021 | 05/07/2021 | 02/07/2021 | 02/07/2021 | 0 | TK_Complete | 1201082599 | 101 | 1201082599_101
CW36940 | TT_Task | Trainset 04 SM6 - Bonding and Waxing (Kleben und Wachs) | 05/07/2021 | 13/07/2021 | 05/07/2021 | 05/08/2021 | 0 | TK_Complete | 1201082599 | 102 | 1201082599_102
CWS1240 | TT_Task | Trainset 04 SM6 - Customer Inspection (Haltepunkt) | 21/05/2021 | 28/05/2021 | 25/05/2021 | 25/05/2021 | 0 | TK_Complete | 1201082599 | 110 | 1201082599_110
A158690 | TT_Task | Trainset 04 SM2 - Carbody Production (Rohbau Produktion) | 19/05/2021 | 03/06/2021 | 19/05/2021 | 01/06/2021 | 0 | TK_Complete | 1201082599 | 108 | 1201082599_108
A158700 | TT_Task | Trainset 04 SM2 - Carbody Surface (Oberfl?che) | 10/06/2021 | 08/07/2021 | 10/06/2021 | 01/07/2021 | 0 | TK_Complete | 1201082599 | 99 | 1201082599_99
A158710 | TT_Task | Trainset 04 SM2 - Fitout (Innenausbau) | 25/08/2021 | 17/09/2021 | 19/07/2021 | 29/09/2021 | 0 | TK_Complete | 1201082599 | 103 | 1201082599_103
CW1250 | TT_Task | Trainset 04 SM2 - Transport from Goerlitz to Ceska Lipa | 08/06/2021 | 09/06/2021 | 10/06/2021 | 10/06/2021 | 0 | TK_Complete | 1201082599 | 109 | 1201082599_109
CW2510 | TT_Task | Trainset 04 SM2 - Transport from Ceska Lipa to Vienna | 01/07/2021 | 01/07/2021 | 01/07/2021 | 01/07/2021 | 0 | TK_Complete | 1201082599 | 111 | 1201082599_111
CW3770 | TT_Task | Trainset 04 SM2 - Bonding and Waxing (Kleben und Wachs) | 02/07/2021 | 12/07/2021 | 02/07/2021 | 19/07/2021 | 0 | TK_Complete | 1201082599 | 112 | 1201082599_112
CWS1250 | TT_Task | Trainset 04 SM2 - Customer Inspection (Haltepunkt) | 04/06/2021 | 07/06/2021 | 01/06/2021 | 01/06/2021 | 0 | TK_Complete | 1201082599 | 110 | 1201082599_110
A158750 | TT_Task | Trainset 04 BM7 - Carbody Production (Rohbau Produktion) | 07/05/2021 | 13/05/2021 | 07/05/2021 | 28/05/2021 | 0 | TK_Complete | 1201082599 | 113 | 1201082599_113
A158760 | TT_Task | Trainset 04 BM7 - Carbody Surface (Oberfl?che) | 24/06/2021 | 22/07/2021 | 24/06/2021 | 14/07/2021 | 0 | TK_Complete | 1201082599 | 116 | 1201082599_116
A158770 | TT_Task | Trainset 04 BM7 - Fitout (Innenausbau) | 30/07/2021 | 18/08/2021 | 06/08/2021 | 29/09/2021 | 0 | TK_Complete | 1201082599 | 119 | 1201082599_119
CW1270 | TT_Task | Trainset 04 BM7 - Transport from Goerlitz to Ceska Lipa | 03/06/2021 | 03/06/2021 | 24/06/2021 | 24/06/2021 | 0 | TK_Complete | 1201082599 | 114 | 1201082599_114
CW2530 | TT_Task | Trainset 04 BM7 - Transport from Ceska Lipa to Vienna | 15/07/2021 | 15/07/2021 | 15/07/2021 | 15/07/2021 | 0 | TK_Complete | 1201082599 | 117 | 1201082599_117
CW3790 | TT_Task | Trainset 04 BM7 - Bonding and Waxing (Kleben und Wachs) | 16/07/2021 | 26/07/2021 | 16/07/2021 | 05/08/2021 | 0 | TK_Complete | 1201082599 | 118 | 1201082599_118
CWS1270 | TT_Task | Trainset 04 BM7 - Customer Inspection (Haltepunkt) | 28/05/2021 | 01/06/2021 | 28/05/2021 | 28/05/2021 | 0 | TK_Complete | 1201082599 | 115 | 1201082599_115
A158720 | TT_Task | Trainset 04 BM3 - Carbody Production (Rohbau Produktion) | 17/05/2021 | 21/05/2021 | 17/05/2021 | 27/05/2021 | 0 | TK_Complete | 1201082599 | 121 | 1201082599_121
A158730 | TT_Task | Trainset 04 BM3 - Carbody Surface (Oberfl?che) | 21/06/2021 | 12/07/2021 | 21/06/2021 | 12/07/2021 | 0 | TK_Complete | 1201082599 | 123 | 1201082599_123
A158740 | TT_Task | Trainset 04 BM3 - Fitout (Innenausbau) | 23/07/2021 | 18/08/2021 | 23/07/2021 | 14/09/2021 | 0 | TK_Complete | 1201082599 | 126 | 1201082599_126
CW1260 | TT_Task | Trainset 04 BM3 - Transport from Goerlitz to Ceska Lipa | 03/06/2021 | 03/06/2021 | 21/06/2021 | 21/06/2021 | 0 | TK_Complete | 1201082599 | 122 | 1201082599_122
CW2520 | TT_Task | Trainset 04 BM3 - Transport from Ceska Lipa to Vienna | 13/07/2021 | 13/07/2021 | 13/07/2021 | 13/07/2021 | 0 | TK_Complete | 1201082599 | 124 | 1201082599_124
CW3780 | TT_Task | Trainset 04 BM3 - Bonding and Waxing (Kleben und Wachs) | 14/07/2021 | 22/07/2021 | 14/07/2021 | 22/07/2021 | 0 | TK_Complete | 1201082599 | 125 | 1201082599_125
CWS1260 | TT_Task | Trainset 04 BM3 - Customer Inspection (Haltepunkt) | 28/05/2021 | 31/05/2021 | 01/06/2021 | 01/06/2021 | 0 | TK_Complete | 1201082599 | 115 | 1201082599_115
A158780 | TT_Task | Trainset 04 BM1 - Carbody Production (Rohbau Produktion) | 20/05/2021 | 26/05/2021 | 20/05/2021 | 31/05/2021 | 0 | TK_Complete | 1201082599 | 128 | 1201082599_128
A158790 | TT_Task | Trainset 04 BM1 - Carbody Surface (Oberfl?che) | 24/06/2021 | 14/07/2021 | 24/06/2021 | 16/07/2021 | 0 | TK_Complete | 1201082599 | 123 | 1201082599_123
A158800 | TT_Task | Trainset 04 BM1 - Fitout (Innenausbau) | 20/08/2021 | 08/09/2021 | 06/08/2021 | 16/09/2021 | 0 | TK_Complete | 1201082599 | 126 | 1201082599_126
CW1280 | TT_Task | Trainset 04 BM1 - Transport from Goerlitz to Ceska Lipa | 03/06/2021 | 03/06/2021 | 24/06/2021 | 24/06/2021 | 0 | TK_Complete | 1201082599 | 129 | 1201082599_129
CW2540 | TT_Task | Trainset 04 BM1 - Transport from Ceska Lipa to Vienna | 16/07/2021 | 16/07/2021 | 16/07/2021 | 16/07/2021 | 0 | TK_Complete | 1201082599 | 130 | 1201082599_130
CW3800 | TT_Task | Trainset 04 BM1 - Bonding and Waxing (Kleben und Wachs) | 19/07/2021 | 27/07/2021 | 19/07/2021 | 06/08/2021 | 0 | TK_Complete | 1201082599 | 131 | 1201082599_131
A158810 | TT_Task | Trainset 04 - Train Completion (Zugbildung ; Aufsetzen) | 05/10/2021 | 15/10/2021 | 05/10/2021 | 15/10/2021 | 0 | TK_Complete | 1201082599 | 132 | 1201082599_132
A158820 | TT_Task | Trainset 04 - Static ; Dynamic Testing | 15/10/2021 | 09/11/2021 | 18/10/2021 | 24/11/2021 | 0 | TK_Complete | 1201082599 | 160 | 1201082599_160
A158830 | TT_Task | Trainset 04 - Rework (Restarbeiten) | 25/11/2021 | 01/12/2021 | 25/11/2021 | 01/12/2021 | 0 | TK_Complete | 1201082599 | 150 | 1201082599_150
A158840 | TT_Task | Trainset 04 - Customer Tests (Test beim Kunden) | 10/01/2022 | 21/01/2022 | 10/01/2022 | nan | 0 | TK_Active | 1201082599 | 152 | 1201082599_152
A158850 | TT_Task | Trainset 04 - Preliminary Customer Acceptance (Kundenabnahme) | 10/03/2022 | 11/03/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 140 | 1201082599_140
A158860 | TT_Task | Trainset 04 - Trial Period (Probebetrieb) | 05/10/2022 | 13/01/2023 | nan | nan | 0 | TK_NotStart | 1201082599 | 141 | 1201082599_141
A158870 | TT_Task | Trainset 04 - ATA notification trial operation complete and defect free (Meldung Probebetrieb bestanden und Mangelfrei) | 16/01/2023 | 18/01/2023 | nan | nan | 0 | TK_NotStart | 1201082599 | 142 | 1201082599_142
A238772 | TT_Task | Trainset 04 - Customer Factory Inspection (Werksabnahme) | 02/12/2021 | 07/12/2021 | 02/12/2021 | 08/12/2021 | 0 | TK_Complete | 1201082599 | 151 | 1201082599_151
A238782 | TT_Task | Trainset 04 - Transport to Customer (Transport zum Kunden) | 09/12/2021 | 09/12/2021 | 09/12/2021 | 10/12/2021 | 0 | TK_Complete | 1201082599 | 153 | 1201082599_153
A239452 | TT_Task | Trainset 04 - Retrofit bei WLB | 03/03/2022 | 09/03/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 143 | 1201082599_143
A239592 | TT_Task | Trainset 04 - ?berstellungsfahrt WL 504 | 14/03/2022 | 14/03/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 161 | 1201082599_161
A239602 | TT_Task | Trainset 04 - Abstellen 504 | 14/03/2022 | 06/05/2022 | nan | nan | 800 | TK_NotStart | 1201082599 | 158 | 1201082599_158
A239612 | TT_Task | Trainset 04 - ?berstellungsfahrt WLB 504 | 05/10/2022 | 05/10/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 161 | 1201082599_161
PAYM10060 | TT_Task | WLB Approval Vehicle Delivery (Freigabe zur ?berstellung) 04 | 10/03/2022 | 10/03/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 159 | 1201082599_159
PAYM10240 | TT_Task | WLB Approval to Start Trial Operation (Freigabe zum Probebetrieb) 04 | 05/10/2022 | 05/10/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 147 | 1201082599_147
A158900 | TT_Task | Trainset 05 CM7 - Carbody Surface (Oberfl?che) | 29/06/2021 | 20/07/2021 | 13/07/2021 | 06/10/2021 | 0 | TK_Complete | 1201082599 | 86 | 1201082599_86
A158910 | TT_Task | Trainset 05 CM7 - Fitout (Innenausbau) | 06/10/2021 | 15/10/2021 | 07/10/2021 | 01/11/2021 | 0 | TK_Complete | 1201082599 | 90 | 1201082599_90
CWS1290 | TT_Task | Trainset 05 CM7 - Customer Inspection (Haltepunkt) | 22/06/2021 | 22/06/2021 | 22/06/2021 | 22/06/2021 | 0 | TK_Complete | 1201082599 | 85 | 1201082599_85
A158930 | TT_Task | Trainset 05 CM1 - Carbody Surface (Oberfl?che) | 05/07/2021 | 26/07/2021 | 14/07/2021 | 08/10/2021 | 0 | TK_Complete | 1201082599 | 86 | 1201082599_86
A158940 | TT_Task | Trainset 05 CM1 - Fitout (Innenausbau) | 11/10/2021 | 20/10/2021 | 11/10/2021 | 09/11/2021 | 0 | TK_Complete | 1201082599 | 90 | 1201082599_90
CWS1300 | TT_Task | Trainset 05 CM1 - Customer Inspection (Haltepunkt) | 22/06/2021 | 22/06/2021 | 22/06/2021 | 22/06/2021 | 0 | TK_Complete | 1201082599 | 85 | 1201082599_85
A158950 | TT_Task | Trainset 05 SM6 - Carbody Production (Rohbau Produktion) | 01/06/2021 | 09/06/2021 | 01/06/2021 | 11/06/2021 | 0 | TK_Complete | 1201082599 | 93 | 1201082599_93
A158960 | TT_Task | Trainset 05 SM6 - Carbody Surface (Oberfl?che) | 21/06/2021 | 08/07/2021 | 21/06/2021 | 08/07/2021 | 0 | TK_Complete | 1201082599 | 99 | 1201082599_99
A158970 | TT_Task | Trainset 05 SM6 - Fitout (Innenausbau) | 19/08/2021 | 13/09/2021 | 02/09/2021 | 15/10/2021 | 0 | TK_Complete | 1201082599 | 103 | 1201082599_103
CW1310 | TT_Task | Trainset 05 SM6 - Transport from Goerlitz to Ceska Lipa | 11/06/2021 | 11/06/2021 | 21/06/2021 | 21/06/2021 | 0 | TK_Complete | 1201082599 | 97 | 1201082599_97
CW2570 | TT_Task | Trainset 05 SM6 - Transport from Ceska Lipa to Vienna | 09/07/2021 | 09/07/2021 | 09/07/2021 | 09/07/2021 | 0 | TK_Complete | 1201082599 | 101 | 1201082599_101
CW3830 | TT_Task | Trainset 05 SM6 - Bonding and Waxing (Kleben und Wachs) | 12/07/2021 | 20/07/2021 | 26/07/2021 | 17/08/2021 | 0 | TK_Complete | 1201082599 | 102 | 1201082599_102
CWS1310 | TT_Task | Trainset 05 SM6 - Customer Inspection (Haltepunkt) | 10/06/2021 | 10/06/2021 | 14/06/2021 | 14/06/2021 | 0 | TK_Complete | 1201082599 | 98 | 1201082599_98
A158980 | TT_Task | Trainset 05 SM2 - Carbody Production (Rohbau Produktion) | 08/06/2021 | 16/06/2021 | 09/06/2021 | 25/06/2021 | 0 | TK_Complete | 1201082599 | 108 | 1201082599_108
A158990 | TT_Task | Trainset 05 SM2 - Carbody Surface (Oberfl?che) | 09/08/2021 | 06/09/2021 | 09/08/2021 | 06/09/2021 | 0 | TK_Complete | 1201082599 | 99 | 1201082599_99
A159000 | TT_Task | Trainset 05 SM2 - Fitout (Innenausbau) | 08/10/2021 | 09/11/2021 | 08/10/2021 | 17/11/2021 | 0 | TK_Complete | 1201082599 | 103 | 1201082599_103
CW1320 | TT_Task | Trainset 05 SM2 - Transport from Goerlitz to Ceska Lipa | 09/08/2021 | 09/08/2021 | 09/08/2021 | 09/08/2021 | 0 | TK_Complete | 1201082599 | 109 | 1201082599_109
CW2580 | TT_Task | Trainset 05 SM2 - Transport from Ceska Lipa to Vienna | 06/09/2021 | 07/09/2021 | 06/09/2021 | 07/09/2021 | 0 | TK_Complete | 1201082599 | 111 | 1201082599_111
CW3840 | TT_Task | Trainset 05 SM2 - Bonding and Waxing (Kleben und Wachs) | 07/09/2021 | 16/09/2021 | 07/09/2021 | 07/10/2021 | 0 | TK_Complete | 1201082599 | 112 | 1201082599_112
CWS1320 | TT_Task | Trainset 05 SM2 - Customer Inspection (Haltepunkt) | 17/06/2021 | 17/06/2021 | 28/06/2021 | 28/06/2021 | 0 | TK_Complete | 1201082599 | 110 | 1201082599_110
A159040 | TT_Task | Trainset 05 BM7 - Carbody Production (Rohbau Produktion) | 28/05/2021 | 04/06/2021 | 28/05/2021 | 07/06/2021 | 0 | TK_Complete | 1201082599 | 113 | 1201082599_113
A159050 | TT_Task | Trainset 05 BM7 - Carbody Surface (Oberfl?che) | 28/06/2021 | 06/08/2021 | 28/06/2021 | 29/07/2021 | 0 | TK_Complete | 1201082599 | 116 | 1201082599_116
A159060 | TT_Task | Trainset 05 BM7 - Fitout (Innenausbau) | 10/09/2021 | 29/09/2021 | 08/09/2021 | 12/10/2021 | 0 | TK_Complete | 1201082599 | 119 | 1201082599_119
CW1340 | TT_Task | Trainset 05 BM7 - Transport from Goerlitz to Ceska Lipa | 08/06/2021 | 08/06/2021 | 28/06/2021 | 28/06/2021 | 0 | TK_Complete | 1201082599 | 114 | 1201082599_114
CW2600 | TT_Task | Trainset 05 BM7 - Transport from Ceska Lipa to Vienna | 09/08/2021 | 09/08/2021 | 30/07/2021 | 30/07/2021 | 0 | TK_Complete | 1201082599 | 117 | 1201082599_117
CW3860 | TT_Task | Trainset 05 BM7 - Bonding and Waxing (Kleben und Wachs) | 30/07/2021 | 16/08/2021 | 30/07/2021 | 07/09/2021 | 0 | TK_Complete | 1201082599 | 118 | 1201082599_118
CWS1340 | TT_Task | Trainset 05 BM7 - Customer Inspection (Haltepunkt) | 07/06/2021 | 07/06/2021 | 08/06/2021 | 08/06/2021 | 0 | TK_Complete | 1201082599 | 115 | 1201082599_115
A159010 | TT_Task | Trainset 05 BM3 - Carbody Production (Rohbau Produktion) | 31/05/2021 | 08/06/2021 | 28/05/2021 | 10/06/2021 | 0 | TK_Complete | 1201082599 | 121 | 1201082599_121
A159020 | TT_Task | Trainset 05 BM3 - Carbody Surface (Oberfl?che) | 07/07/2021 | 13/08/2021 | 07/07/2021 | 30/08/2021 | 0 | TK_Complete | 1201082599 | 123 | 1201082599_123
A159030 | TT_Task | Trainset 05 BM3 - Fitout (Innenausbau) | 14/09/2021 | 01/10/2021 | 16/09/2021 | 14/10/2021 | 0 | TK_Complete | 1201082599 | 126 | 1201082599_126
CW1330 | TT_Task | Trainset 05 BM3 - Transport from Goerlitz to Ceska Lipa | 07/07/2021 | 07/07/2021 | 07/07/2021 | 07/07/2021 | 0 | TK_Complete | 1201082599 | 122 | 1201082599_122
CW2590 | TT_Task | Trainset 05 BM3 - Transport from Ceska Lipa to Vienna | 16/08/2021 | 16/08/2021 | 31/08/2021 | 31/08/2021 | 0 | TK_Complete | 1201082599 | 124 | 1201082599_124
CW3850 | TT_Task | Trainset 05 BM3 - Bonding and Waxing (Kleben und Wachs) | 31/08/2021 | 13/09/2021 | 31/08/2021 | 15/09/2021 | 0 | TK_Complete | 1201082599 | 125 | 1201082599_125
CWS1330 | TT_Task | Trainset 05 BM3 - Customer Inspection (Haltepunkt) | 09/06/2021 | 09/06/2021 | 10/06/2021 | 10/06/2021 | 0 | TK_Complete | 1201082599 | 115 | 1201082599_115
A159070 | TT_Task | Trainset 05 BM1 - Carbody Production (Rohbau Produktion) | 03/06/2021 | 10/06/2021 | 04/06/2021 | 15/06/2021 | 0 | TK_Complete | 1201082599 | 128 | 1201082599_128
A159080 | TT_Task | Trainset 05 BM1 - Carbody Surface (Oberfl?che) | 07/07/2021 | 13/08/2021 | 07/07/2021 | 30/08/2021 | 0 | TK_Complete | 1201082599 | 123 | 1201082599_123
A159090 | TT_Task | Trainset 05 BM1 - Fitout (Innenausbau) | 17/09/2021 | 06/10/2021 | 20/09/2021 | 04/11/2021 | 0 | TK_Complete | 1201082599 | 126 | 1201082599_126
CW1350 | TT_Task | Trainset 05 BM1 - Transport from Goerlitz to Ceska Lipa | 07/07/2021 | 07/07/2021 | 07/07/2021 | 07/07/2021 | 0 | TK_Complete | 1201082599 | 129 | 1201082599_129
CW2610 | TT_Task | Trainset 05 BM1 - Transport from Ceska Lipa to Vienna | 16/08/2021 | 16/08/2021 | 31/08/2021 | 31/08/2021 | 0 | TK_Complete | 1201082599 | 130 | 1201082599_130
CW3870 | TT_Task | Trainset 05 BM1 - Bonding and Waxing (Kleben und Wachs) | 31/08/2021 | 16/09/2021 | 31/08/2021 | 16/09/2021 | 0 | TK_Complete | 1201082599 | 131 | 1201082599_131
CWS1350 | TT_Task | Trainset 05 BM1 - Customer Inspection (Haltepunkt) | 11/06/2021 | 14/06/2021 | 16/06/2021 | 16/06/2021 | 0 | TK_Complete | 1201082599 | 115 | 1201082599_115
A159100 | TT_Task | Trainset 05 - Train Completion (Zugbildung ; Aufsetzen) | 17/11/2021 | 25/11/2021 | 17/11/2021 | 26/11/2021 | 0 | TK_Complete | 1201082599 | 132 | 1201082599_132
A159110 | TT_Task | Trainset 05 - Static ; Dynamic Testing | 29/11/2021 | 18/01/2022 | 29/11/2021 | 14/01/2022 | 0 | TK_Complete | 1201082599 | 160 | 1201082599_160
A159120 | TT_Task | Trainset 05 - Welding Repairs (Schwei?reparaturen) | 17/01/2022 | 26/01/2022 | 17/01/2022 | 28/01/2022 | 0 | TK_Complete | 1201082599 | 162 | 1201082599_162
A159130 | TT_Task | Trainset 05 - Customer Tests (IBN am Erf?lungsort) | 03/03/2022 | 23/03/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 139 | 1201082599_139
A159140 | TT_Task | Trainset 05 - Preliminary Customer Acceptance (Kundenabnahme) | 24/03/2022 | 25/03/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 140 | 1201082599_140
A159150 | TT_Task | Trainset 05 - Trial Period (Probebetrieb) | 10/10/2022 | 18/01/2023 | nan | nan | 0 | TK_NotStart | 1201082599 | 141 | 1201082599_141
A159160 | TT_Task | Trainset 05 - ATA notification trial operation complete and defect free (Meldung Probebetrieb bestanden und Mangelfrei) | 19/01/2023 | 23/01/2023 | nan | nan | 0 | TK_NotStart | 1201082599 | 142 | 1201082599_142
A238792 | TT_Task | Trainset 05 - Customer Factory Inspection + Rework (Werksabnahme +Nacharbeit) | 10/02/2022 | 15/02/2022 | 11/02/2022 | 16/02/2022 | 0 | TK_Complete | 1201082599 | 137 | 1201082599_137
A238802 | TT_Task | Trainset 05 - Transport to Customer (Transport zum Kunden) | 16/02/2022 | 16/02/2022 | 17/02/2022 | 17/02/2022 | 0 | TK_Complete | 1201082599 | 153 | 1201082599_153
A239462 | TT_Task | Trainset 05 - Re-Testing (IBN) +Finishing | 31/01/2022 | 31/01/2022 | 31/01/2022 | 31/01/2022 | 0 | TK_Complete | 1201082599 | 144 | 1201082599_144
A239472 | TT_Task | Trainset 05 - Quality Inspection +Rework (Q-Abnahme + Nachartbeit) | 01/02/2022 | 04/02/2022 | 01/02/2022 | 10/02/2022 | 0 | TK_Complete | 1201082599 | 145 | 1201082599_145
A239622 | TT_Task | Trainset 05 - ?berstellungsfahrt WL 505 | 28/03/2022 | 28/03/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 161 | 1201082599_161
A239632 | TT_Task | Trainset 05 - Abstellen 505 | 28/03/2022 | 28/03/2022 | nan | nan | 1032 | TK_NotStart | 1201082599 | 158 | 1201082599_158
A239642 | TT_Task | Trainset 05 - ?berstellungsfahrt WLB 505 | 05/10/2022 | 05/10/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 161 | 1201082599_161
PAYM10250 | TT_Task | WLB Approval to Start Trial Operation (Freigabe zum Probebetrieb) 05 | 05/10/2022 | 05/10/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 147 | 1201082599_147
A159190 | TT_Task | Trainset 06 CM7 - Carbody Surface (Oberfl?che) | 04/10/2021 | 09/11/2021 | 04/10/2021 | 09/11/2021 | 0 | TK_Complete | 1201082599 | 86 | 1201082599_86
A159200 | TT_Task | Trainset 06 CM7 - Fitout (Innenausbau) | 10/11/2021 | 19/11/2021 | 10/11/2021 | 19/11/2021 | 0 | TK_Complete | 1201082599 | 90 | 1201082599_90
CWS1360 | TT_Task | Trainset 06 CM7 - Customer Inspection (Haltepunkt) | 31/08/2021 | 31/08/2021 | 31/08/2021 | 31/08/2021 | 0 | TK_Complete | 1201082599 | 85 | 1201082599_85
A159220 | TT_Task | Trainset 06 CM1 - Carbody Surface (Oberfl?che) | 04/10/2021 | 11/11/2021 | 04/10/2021 | 11/11/2021 | 0 | TK_Complete | 1201082599 | 86 | 1201082599_86
A159230 | TT_Task | Trainset 06 CM1 - Fitout (Innenausbau) | 12/11/2021 | 23/11/2021 | 12/11/2021 | 19/11/2021 | 0 | TK_Complete | 1201082599 | 90 | 1201082599_90
CWS1370 | TT_Task | Trainset 06 CM1 - Customer Inspection (Haltepunkt) | 31/08/2021 | 31/08/2021 | 31/08/2021 | 31/08/2021 | 0 | TK_Complete | 1201082599 | 85 | 1201082599_85
A159240 | TT_Task | Trainset 06 SM6 - Carbody Production (Rohbau Produktion) | 13/07/2021 | 21/07/2021 | 15/07/2021 | 26/07/2021 | 0 | TK_Complete | 1201082599 | 93 | 1201082599_93
A159250 | TT_Task | Trainset 06 SM6 - Carbody Surface (Oberfl?che) | 10/08/2021 | 16/09/2021 | 10/08/2021 | 17/09/2021 | 0 | TK_Complete | 1201082599 | 99 | 1201082599_99
A159260 | TT_Task | Trainset 06 SM6 - Fitout (Innenausbau) | 19/10/2021 | 16/11/2021 | 18/10/2021 | 16/12/2021 | 0 | TK_Complete | 1201082599 | 103 | 1201082599_103
CW1380 | TT_Task | Trainset 06 SM6 - Transport from Goerlitz to Ceska Lipa | 10/08/2021 | 10/08/2021 | 10/08/2021 | 10/08/2021 | 0 | TK_Complete | 1201082599 | 97 | 1201082599_97
CW2640 | TT_Task | Trainset 06 SM6 - Transport from Ceska Lipa to Vienna | 22/09/2021 | 22/09/2021 | 01/10/2021 | 01/10/2021 | 0 | TK_Complete | 1201082599 | 101 | 1201082599_101
CW36930 | TT_Task | Trainset 06 SM6 - Bonding and Waxing (Kleben und Wachs) | 05/10/2021 | 15/10/2021 | 05/10/2021 | 18/10/2021 | 0 | TK_Complete | 1201082599 | 102 | 1201082599_102
CWS1380 | TT_Task | Trainset 06 SM6 - Customer Inspection (Haltepunkt) | 22/07/2021 | 22/07/2021 | 27/07/2021 | 27/07/2021 | 0 | TK_Complete | 1201082599 | 98 | 1201082599_98
A159270 | TT_Task | Trainset 06 SM2 - Carbody Production (Rohbau Produktion) | 19/07/2021 | 27/07/2021 | 20/07/2021 | 27/07/2021 | 0 | TK_Complete | 1201082599 | 108 | 1201082599_108
A159280 | TT_Task | Trainset 06 SM2 - Carbody Surface (Oberfl?che) | 10/08/2021 | 27/09/2021 | 10/08/2021 | 01/10/2021 | 0 | TK_Complete | 1201082599 | 99 | 1201082599_99
A159290 | TT_Task | Trainset 06 SM2 - Fitout (Innenausbau) | 21/10/2021 | 18/11/2021 | 27/10/2021 | 10/01/2022 | 0 | TK_Complete | 1201082599 | 103 | 1201082599_103
CW1390 | TT_Task | Trainset 06 SM2 - Transport from Goerlitz to Ceska Lipa | 10/08/2021 | 10/08/2021 | 10/08/2021 | 10/08/2021 | 0 | TK_Complete | 1201082599 | 109 | 1201082599_109
CW2650 | TT_Task | Trainset 06 SM2 - Transport from Ceska Lipa to Vienna | 28/09/2021 | 28/09/2021 | 04/10/2021 | 04/10/2021 | 0 | TK_Complete | 1201082599 | 111 | 1201082599_111
CW3910 | TT_Task | Trainset 06 SM2 - Bonding and Waxing (Kleben und Wachs) | 06/10/2021 | 20/10/2021 | 06/10/2021 | 20/10/2021 | 0 | TK_Complete | 1201082599 | 112 | 1201082599_112
CWS1390 | TT_Task | Trainset 06 SM2 - Customer Inspection (Haltepunkt) | 29/07/2021 | 29/07/2021 | 28/07/2021 | 28/07/2021 | 0 | TK_Complete | 1201082599 | 110 | 1201082599_110
A159330 | TT_Task | Trainset 06 BM7 - Carbody Production (Rohbau Produktion) | 19/07/2021 | 27/07/2021 | 19/07/2021 | 26/07/2021 | 0 | TK_Complete | 1201082599 | 113 | 1201082599_113
A159340 | TT_Task | Trainset 06 BM7 - Carbody Surface (Oberfl?che) | 09/08/2021 | 07/09/2021 | 09/08/2021 | 22/09/2021 | 0 | TK_Complete | 1201082599 | 116 | 1201082599_116
A159350 | TT_Task | Trainset 06 BM7 - Fitout (Innenausbau) | 13/10/2021 | 22/10/2021 | 13/10/2021 | 14/12/2021 | 0 | TK_Complete | 1201082599 | 119 | 1201082599_119
CW1410 | TT_Task | Trainset 06 BM7 - Transport from Goerlitz to Ceska Lipa | 09/08/2021 | 09/08/2021 | 09/08/2021 | 09/08/2021 | 0 | TK_Complete | 1201082599 | 114 | 1201082599_114
CW2670 | TT_Task | Trainset 06 BM7 - Transport from Ceska Lipa to Vienna | 23/09/2021 | 23/09/2021 | 23/09/2021 | 23/09/2021 | 0 | TK_Complete | 1201082599 | 117 | 1201082599_117
CW3930 | TT_Task | Trainset 06 BM7 - Bonding and Waxing (Kleben und Wachs) | 24/09/2021 | 04/10/2021 | 24/09/2021 | 12/10/2021 | 0 | TK_Complete | 1201082599 | 118 | 1201082599_118
CWS1410 | TT_Task | Trainset 06 BM7 - Customer Inspection (Haltepunkt) | 29/07/2021 | 30/07/2021 | 27/07/2021 | 27/07/2021 | 0 | TK_Complete | 1201082599 | 115 | 1201082599_115
A159300 | TT_Task | Trainset 06 BM3 - Carbody Production (Rohbau Produktion) | 15/07/2021 | 23/07/2021 | 23/07/2021 | 02/08/2021 | 0 | TK_Complete | 1201082599 | 121 | 1201082599_121
A159310 | TT_Task | Trainset 06 BM3 - Carbody Surface (Oberfl?che) | 09/08/2021 | 31/08/2021 | 09/08/2021 | 30/09/2021 | 0 | TK_Complete | 1201082599 | 123 | 1201082599_123
A159320 | TT_Task | Trainset 06 BM3 - Fitout (Innenausbau) | 18/10/2021 | 09/11/2021 | 18/10/2021 | 10/01/2022 | 0 | TK_Complete | 1201082599 | 126 | 1201082599_126
CW1400 | TT_Task | Trainset 06 BM3 - Transport from Goerlitz to Ceska Lipa | 09/08/2021 | 09/08/2021 | 09/08/2021 | 09/08/2021 | 0 | TK_Complete | 1201082599 | 122 | 1201082599_122
CW2660 | TT_Task | Trainset 06 BM3 - Transport from Ceska Lipa to Vienna | 28/09/2021 | 28/09/2021 | 01/10/2021 | 01/10/2021 | 0 | TK_Complete | 1201082599 | 124 | 1201082599_124
CW3920 | TT_Task | Trainset 06 BM3 - Bonding and Waxing (Kleben und Wachs) | 04/10/2021 | 29/10/2021 | 04/10/2021 | 18/10/2021 | 0 | TK_Complete | 1201082599 | 125 | 1201082599_125
CWS1400 | TT_Task | Trainset 06 BM3 - Customer Inspection (Haltepunkt) | 03/08/2021 | 03/08/2021 | 03/08/2021 | 03/08/2021 | 0 | TK_Complete | 1201082599 | 115 | 1201082599_115
A159360 | TT_Task | Trainset 06 BM1 - Carbody Production (Rohbau Produktion) | 26/07/2021 | 03/08/2021 | 26/07/2021 | 02/08/2021 | 0 | TK_Complete | 1201082599 | 128 | 1201082599_128
A159370 | TT_Task | Trainset 06 BM1 - Carbody Surface (Oberfl?che) | 10/08/2021 | 27/08/2021 | 10/08/2021 | 04/10/2021 | 0 | TK_Complete | 1201082599 | 123 | 1201082599_123
A159380 | TT_Task | Trainset 06 BM1 - Fitout (Innenausbau) | 28/10/2021 | 17/11/2021 | 29/10/2021 | 11/01/2022 | 0 | TK_Complete | 1201082599 | 126 | 1201082599_126
CW1420 | TT_Task | Trainset 06 BM1 - Transport from Goerlitz to Ceska Lipa | 10/08/2021 | 10/08/2021 | 10/08/2021 | 10/08/2021 | 0 | TK_Complete | 1201082599 | 129 | 1201082599_129
CW2680 | TT_Task | Trainset 06 BM1 - Transport from Ceska Lipa to Vienna | 04/10/2021 | 04/10/2021 | 05/10/2021 | 05/10/2021 | 0 | TK_Complete | 1201082599 | 130 | 1201082599_130
CW3940 | TT_Task | Trainset 06 BM1 - Bonding and Waxing (Kleben und Wachs) | 06/10/2021 | 03/11/2021 | 06/10/2021 | 28/10/2021 | 0 | TK_Complete | 1201082599 | 131 | 1201082599_131
CWS1420 | TT_Task | Trainset 06 BM1 - Customer Inspection (Haltepunkt) | 03/08/2021 | 03/08/2021 | 03/08/2021 | 03/08/2021 | 0 | TK_Complete | 1201082599 | 115 | 1201082599_115
A159390 | TT_Task | Trainset 06 - Train Completion (Zugbildung ; Aufsetzen) und Update Rev E | 10/01/2022 | 20/01/2022 | 10/01/2022 | 20/01/2022 | 0 | TK_Complete | 1201082599 | 132 | 1201082599_132
A159400 | TT_Task | Trainset 06 - Static ; Dynamic Testing (IBN +Finishing) | 21/01/2022 | 11/02/2022 | 21/01/2022 | 18/02/2022 | 0 | TK_Complete | 1201082599 | 163 | 1201082599_163
A159410 | TT_Task | Trainset 06 - Quality Inspection +Rework (Q-Abnahme + Nachartbeit) | 21/02/2022 | 25/02/2022 | 21/02/2022 | 25/02/2022 | 0 | TK_Complete | 1201082599 | 145 | 1201082599_145
A159420 | TT_Task | Trainset 06 - Customer Tests (IBN am Erf?lungsort) | 14/04/2022 | 04/05/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 139 | 1201082599_139
A159430 | TT_Task | Trainset 06 - Preliminary Customer Acceptance (Kundenabnahme) | 05/05/2022 | 06/05/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 140 | 1201082599_140
A159440 | TT_Task | Trainset 06 - Trial Period (Probebetrieb) | 10/10/2022 | 18/01/2023 | nan | nan | 0 | TK_NotStart | 1201082599 | 141 | 1201082599_141
A159450 | TT_Task | Trainset 06 - ATA notification trial operation complete and defect free (Meldung Probebetrieb bestanden und Mangelfrei) | 19/01/2023 | 23/01/2023 | nan | nan | 0 | TK_NotStart | 1201082599 | 142 | 1201082599_142
A238812 | TT_Task | Trainset 06 - Customer Factory Inspection + Rework (Werksabnahme +Nacharbeit) +Abstellen | 28/02/2022 | 14/03/2022 | 28/02/2022 | 14/03/2022 | 0 | TK_Complete | 1201082599 | 137 | 1201082599_137
A238822 | TT_Task | Trainset 06 - Transport to Customer (Transport zum Kunden) | 15/03/2022 | 15/03/2022 | 15/03/2022 | 15/03/2022 | 0 | TK_Complete | 1201082599 | 153 | 1201082599_153
A239652 | TT_Task | Trainset 06 - ?berstellungsfahrt WL 506 | 09/05/2022 | 09/05/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 161 | 1201082599_161
A239662 | TT_Task | Trainset 06 - Abstellen 506 | 09/05/2022 | 09/05/2022 | nan | nan | 824 | TK_NotStart | 1201082599 | 158 | 1201082599_158
A239672 | TT_Task | Trainset 06 - ?berstellungsfahrt WLB 506 | 10/10/2022 | 10/10/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 161 | 1201082599_161
PAYM10260 | TT_Task | WLB Approval to Start Trial Operation (Freigabe zum Probebetrieb) 06 | 10/10/2022 | 10/10/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 147 | 1201082599_147
A159480 | TT_Task | Trainset 07 CM7 - Carbody Surface (Oberfl?che) | 11/10/2021 | 04/11/2021 | 19/10/2021 | 22/11/2021 | 0 | TK_Complete | 1201082599 | 86 | 1201082599_86
A159490 | TT_Task | Trainset 07 CM7 - Fitout (Innenausbau) | 23/11/2021 | 02/12/2021 | 23/11/2021 | 09/12/2021 | 0 | TK_Complete | 1201082599 | 90 | 1201082599_90
CWS1430 | TT_Task | Trainset 07 CM7 - Customer Inspection (Haltepunkt) | 08/10/2021 | 08/10/2021 | 08/10/2021 | 08/10/2021 | 0 | TK_Complete | 1201082599 | 85 | 1201082599_85
A159510 | TT_Task | Trainset 07 CM1 - Carbody Surface (Oberfl?che) | 11/10/2021 | 04/11/2021 | 19/10/2021 | 23/11/2021 | 0 | TK_Complete | 1201082599 | 86 | 1201082599_86
A159520 | TT_Task | Trainset 07 CM1 - Fitout (Innenausbau) | 24/11/2021 | 23/12/2021 | 01/12/2021 | 14/12/2021 | 0 | TK_Complete | 1201082599 | 90 | 1201082599_90
CWS1440 | TT_Task | Trainset 07 CM1 - Customer Inspection (Haltepunkt) | 08/10/2021 | 08/10/2021 | 08/10/2021 | 08/10/2021 | 0 | TK_Complete | 1201082599 | 85 | 1201082599_85
A159530 | TT_Task | Trainset 07 SM6 - Carbody Production (Rohbau Produktion) | 12/08/2021 | 20/08/2021 | 12/08/2021 | 20/08/2021 | 0 | TK_Complete | 1201082599 | 93 | 1201082599_93
A159540 | TT_Task | Trainset 07 SM6 - Carbody Surface (Oberfl?che) | 26/08/2021 | 16/09/2021 | 26/08/2021 | 13/10/2021 | 0 | TK_Complete | 1201082599 | 99 | 1201082599_99
A159550 | TT_Task | Trainset 07 SM6 - Fitout (Innenausbau) | 08/11/2021 | 01/12/2021 | 08/11/2021 | 26/01/2022 | 0 | TK_Complete | 1201082599 | 103 | 1201082599_103
CW1450 | TT_Task | Trainset 07 SM6 - Transport from Goerlitz to Ceska Lipa | 26/08/2021 | 26/08/2021 | 26/08/2021 | 26/08/2021 | 0 | TK_Complete | 1201082599 | 97 | 1201082599_97
CW2710 | TT_Task | Trainset 07 SM6 - Transport from Ceska Lipa to Vienna | 14/10/2021 | 14/10/2021 | 14/10/2021 | 14/10/2021 | 0 | TK_Complete | 1201082599 | 101 | 1201082599_101
CW3970 | TT_Task | Trainset 07 SM6 - Bonding and Waxing (Kleben und Wachs) | 15/10/2021 | 22/10/2021 | 15/10/2021 | 05/11/2021 | 0 | TK_Complete | 1201082599 | 102 | 1201082599_102
CWS1450 | TT_Task | Trainset 07 SM6 - Customer Inspection (Haltepunkt) | 23/08/2021 | 23/08/2021 | 23/08/2021 | 23/08/2021 | 0 | TK_Complete | 1201082599 | 98 | 1201082599_98
A159560 | TT_Task | Trainset 07 SM2 - Carbody Production (Rohbau Produktion) | 19/08/2021 | 27/08/2021 | 19/08/2021 | 27/08/2021 | 0 | TK_Complete | 1201082599 | 108 | 1201082599_108
A159570 | TT_Task | Trainset 07 SM2 - Carbody Surface (Oberfl?che) | 02/09/2021 | 21/09/2021 | 02/09/2021 | 19/10/2021 | 0 | TK_Complete | 1201082599 | 99 | 1201082599_99
A159580 | TT_Task | Trainset 07 SM2 - Fitout (Innenausbau) | 12/11/2021 | 15/02/2022 | 12/11/2021 | 28/01/2022 | 0 | TK_Complete | 1201082599 | 103 | 1201082599_103
CW1460 | TT_Task | Trainset 07 SM2 - Transport from Goerlitz to Ceska Lipa | 02/09/2021 | 02/09/2021 | 02/09/2021 | 02/09/2021 | 0 | TK_Complete | 1201082599 | 109 | 1201082599_109
CW2720 | TT_Task | Trainset 07 SM2 - Transport from Ceska Lipa to Vienna | 20/10/2021 | 20/10/2021 | 20/10/2021 | 20/10/2021 | 0 | TK_Complete | 1201082599 | 111 | 1201082599_111
CW3980 | TT_Task | Trainset 07 SM2 - Bonding and Waxing (Kleben und Wachs) | 28/10/2021 | 05/11/2021 | 27/10/2021 | 10/11/2021 | 0 | TK_Complete | 1201082599 | 112 | 1201082599_112
CWS1460 | TT_Task | Trainset 07 SM2 - Customer Inspection (Haltepunkt) | 30/08/2021 | 30/08/2021 | 30/08/2021 | 30/08/2021 | 0 | TK_Complete | 1201082599 | 110 | 1201082599_110
A159620 | TT_Task | Trainset 07 BM7 - Carbody Production (Rohbau Produktion) | 13/08/2021 | 23/08/2021 | 13/08/2021 | 23/08/2021 | 0 | TK_Complete | 1201082599 | 113 | 1201082599_113
A159630 | TT_Task | Trainset 07 BM7 - Carbody Surface (Oberfl?che) | 26/08/2021 | 14/09/2021 | 26/08/2021 | 13/10/2021 | 0 | TK_Complete | 1201082599 | 116 | 1201082599_116
A159640 | TT_Task | Trainset 07 BM7 - Fitout (Innenausbau) | 10/11/2021 | 29/11/2021 | 10/11/2021 | 11/02/2022 | 0 | TK_Complete | 1201082599 | 119 | 1201082599_119
CW1480 | TT_Task | Trainset 07 BM7 - Transport from Goerlitz to Ceska Lipa | 26/08/2021 | 26/08/2021 | 26/08/2021 | 26/08/2021 | 0 | TK_Complete | 1201082599 | 114 | 1201082599_114
CW2740 | TT_Task | Trainset 07 BM7 - Transport from Ceska Lipa to Vienna | 14/10/2021 | 14/10/2021 | 14/10/2021 | 14/10/2021 | 0 | TK_Complete | 1201082599 | 117 | 1201082599_117
CW4000 | TT_Task | Trainset 07 BM7 - Bonding and Waxing (Kleben und Wachs) | 28/10/2021 | 05/11/2021 | 19/10/2021 | 10/11/2021 | 0 | TK_Complete | 1201082599 | 118 | 1201082599_118
CWS1480 | TT_Task | Trainset 07 BM7 - Customer Inspection (Haltepunkt) | 24/08/2021 | 24/08/2021 | 24/08/2021 | 24/08/2021 | 0 | TK_Complete | 1201082599 | 115 | 1201082599_115
A159590 | TT_Task | Trainset 07 BM3 - Carbody Production (Rohbau Produktion) | 16/08/2021 | 24/08/2021 | 16/08/2021 | 24/08/2021 | 0 | TK_Complete | 1201082599 | 121 | 1201082599_121
A159600 | TT_Task | Trainset 07 BM3 - Carbody Surface (Oberfl?che) | 27/08/2021 | 15/09/2021 | 27/08/2021 | 19/10/2021 | 0 | TK_Complete | 1201082599 | 123 | 1201082599_123
A159610 | TT_Task | Trainset 07 BM3 - Fitout (Innenausbau) | 24/11/2021 | 14/12/2021 | 24/11/2021 | 15/02/2022 | 0 | TK_Complete | 1201082599 | 126 | 1201082599_126
CW1470 | TT_Task | Trainset 07 BM3 - Transport from Goerlitz to Ceska Lipa | 27/08/2021 | 27/08/2021 | 27/08/2021 | 27/08/2021 | 0 | TK_Complete | 1201082599 | 122 | 1201082599_122
CW2730 | TT_Task | Trainset 07 BM3 - Transport from Ceska Lipa to Vienna | 20/10/2021 | 20/10/2021 | 20/10/2021 | 20/10/2021 | 0 | TK_Complete | 1201082599 | 124 | 1201082599_124
CW3990 | TT_Task | Trainset 07 BM3 - Bonding and Waxing (Kleben und Wachs) | 29/10/2021 | 09/11/2021 | 27/10/2021 | 23/11/2021 | 0 | TK_Complete | 1201082599 | 125 | 1201082599_125
CWS1470 | TT_Task | Trainset 07 BM3 - Customer Inspection (Haltepunkt) | 26/08/2021 | 26/08/2021 | 26/08/2021 | 26/08/2021 | 0 | TK_Complete | 1201082599 | 115 | 1201082599_115
A159650 | TT_Task | Trainset 07 BM1 - Carbody Production (Rohbau Produktion) | 20/08/2021 | 30/08/2021 | 20/08/2021 | 30/08/2021 | 0 | TK_Complete | 1201082599 | 128 | 1201082599_128
A159660 | TT_Task | Trainset 07 BM1 - Carbody Surface (Oberfl?che) | 02/09/2021 | 22/09/2021 | 02/09/2021 | 22/10/2021 | 0 | TK_Complete | 1201082599 | 123 | 1201082599_123
A159670 | TT_Task | Trainset 07 BM1 - Fitout (Innenausbau) | 29/11/2021 | 21/02/2022 | 29/11/2021 | 21/02/2022 | 0 | TK_Complete | 1201082599 | 126 | 1201082599_126
CW1490 | TT_Task | Trainset 07 BM1 - Transport from Goerlitz to Ceska Lipa | 02/09/2021 | 02/09/2021 | 02/09/2021 | 02/09/2021 | 0 | TK_Complete | 1201082599 | 129 | 1201082599_129
CW2750 | TT_Task | Trainset 07 BM1 - Transport from Ceska Lipa to Vienna | 28/10/2021 | 28/10/2021 | 22/10/2021 | 22/10/2021 | 0 | TK_Complete | 1201082599 | 130 | 1201082599_130
CW4010 | TT_Task | Trainset 07 BM1 - Bonding and Waxing (Kleben und Wachs) | 29/10/2021 | 26/11/2021 | 29/10/2021 | 26/11/2021 | 0 | TK_Complete | 1201082599 | 131 | 1201082599_131
CWS1490 | TT_Task | Trainset 07 BM1 - Customer Inspection (Haltepunkt) | 31/08/2021 | 31/08/2021 | 31/08/2021 | 31/08/2021 | 0 | TK_Complete | 1201082599 | 115 | 1201082599_115
A159680 | TT_Task | Trainset 07 - Train Completion (Zugbildung ; Aufsetzen) | 22/02/2022 | 01/03/2022 | 22/02/2022 | 07/03/2022 | 0 | TK_Complete | 1201082599 | 132 | 1201082599_132
A159690 | TT_Task | Trainset 07 - Static ; Dynamic Testing (IBN +Finishing) | 07/03/2022 | 21/03/2022 | 07/03/2022 | nan | 0 | TK_Active | 1201082599 | 163 | 1201082599_163
A159700 | TT_Task | Trainset 07 - Quality Inspection +Rework (Q-Abnahme + Nachartbeit) | 15/04/2022 | 19/04/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 145 | 1201082599_145
A159710 | TT_Task | Trainset 07 - Customer Tests (IBN am Erf?lungsort) | 24/05/2022 | 13/06/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 139 | 1201082599_139
A159720 | TT_Task | Trainset 07 - Preliminary Customer Acceptance (Kundenabnahme) | 14/06/2022 | 15/06/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 140 | 1201082599_140
A159730 | TT_Task | Trainset 07 - Trial Period (Probebetrieb) | 12/10/2022 | 20/01/2023 | nan | nan | 0 | TK_NotStart | 1201082599 | 141 | 1201082599_141
A159740 | TT_Task | Trainset 07 - ATA notification trial operation complete and defect free (Meldung Probebetrieb bestanden und Mangelfrei) | 23/01/2023 | 25/01/2023 | nan | nan | 0 | TK_NotStart | 1201082599 | 142 | 1201082599_142
A238832 | TT_Task | Trainset 07 - Customer Factory Inspection + Rework (Werksabnahme +Nacharbeit) | 20/04/2022 | 25/04/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 137 | 1201082599_137
A238842 | TT_Task | Trainset 07 - Transport to Customer (Transport zum Kunden) | 26/04/2022 | 26/04/2022 | nan | nan | 152 | TK_NotStart | 1201082599 | 153 | 1201082599_153
A239422 | TT_Task | Trainset 07 - Welding Repairs (Schwei?reparaturen) | 17/01/2022 | 28/01/2022 | 17/01/2022 | 08/02/2022 | 0 | TK_Complete | 1201082599 | 162 | 1201082599_162
A239682 | TT_Task | Trainset 07 - Abstellen Werk 507 | 26/04/2022 | 26/04/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 146 | 1201082599_146
A239692 | TT_Task | Trainset 07 - ?berstellungsfahrt WLB 507 -1 | 20/06/2022 | 20/06/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 157 | 1201082599_157
A239702 | TT_Task | Trainset 07 - Abstellen WL 507 | 20/06/2022 | 20/06/2022 | nan | nan | 624 | TK_NotStart | 1201082599 | 158 | 1201082599_158
A239712 | TT_Task | Trainset 07 - ?berstellungsfahrt WLB 507 -2 | 10/10/2022 | 10/10/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 157 | 1201082599_157
PAYM10270 | TT_Task | WLB Approval to Start Trial Operation (Freigabe zum Probebetrieb) 07 | 10/10/2022 | 10/10/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 147 | 1201082599_147
A159770 | TT_Task | Trainset 08 CM7 - Carbody Surface (Oberfl?che) | 15/11/2021 | 06/12/2021 | 15/11/2021 | 09/12/2021 | 0 | TK_Complete | 1201082599 | 86 | 1201082599_86
A159780 | TT_Task | Trainset 08 CM7 - Fitout (Innenausbau) | 10/12/2021 | 21/12/2021 | 10/12/2021 | 24/12/2021 | 0 | TK_Complete | 1201082599 | 90 | 1201082599_90
CWS1500 | TT_Task | Trainset 08 CM7 - Customer Inspection (Haltepunkt) | 04/11/2021 | 04/11/2021 | 04/11/2021 | 04/11/2021 | 0 | TK_Complete | 1201082599 | 85 | 1201082599_85
A159800 | TT_Task | Trainset 08 CM1 - Carbody Surface (Oberfl?che) | 15/11/2021 | 06/12/2021 | 15/11/2021 | 09/12/2021 | 0 | TK_Complete | 1201082599 | 86 | 1201082599_86
A159810 | TT_Task | Trainset 08 CM1 - Fitout (Innenausbau) | 10/12/2021 | 21/12/2021 | 10/12/2021 | 31/01/2022 | 0 | TK_Complete | 1201082599 | 90 | 1201082599_90
CWS1510 | TT_Task | Trainset 08 CM1 - Customer Inspection (Haltepunkt) | 04/11/2021 | 04/11/2021 | 04/11/2021 | 04/11/2021 | 0 | TK_Complete | 1201082599 | 85 | 1201082599_85
A159820 | TT_Task | Trainset 08 SM6 - Carbody Production (Rohbau Produktion) | 21/09/2021 | 12/10/2021 | 10/09/2021 | 20/09/2021 | 0 | TK_Complete | 1201082599 | 93 | 1201082599_93
A159830 | TT_Task | Trainset 08 SM6 - Carbody Surface (Oberfl?che) | 04/10/2021 | 01/11/2021 | 04/10/2021 | 15/11/2021 | 0 | TK_Complete | 1201082599 | 99 | 1201082599_99
A159840 | TT_Task | Trainset 08 SM6 - Fitout (Innenausbau) | 09/02/2022 | 16/02/2022 | 10/02/2022 | 03/03/2022 | 0 | TK_Complete | 1201082599 | 103 | 1201082599_103
CW1520 | TT_Task | Trainset 08 SM6 - Transport from Goerlitz to Ceska Lipa | 14/10/2021 | 14/10/2021 | 04/10/2021 | 04/10/2021 | 0 | TK_Complete | 1201082599 | 97 | 1201082599_97
CW2780 | TT_Task | Trainset 08 SM6 - Transport from Ceska Lipa to Vienna | 15/11/2021 | 15/11/2021 | 15/11/2021 | 15/11/2021 | 0 | TK_Complete | 1201082599 | 101 | 1201082599_101
CW4040 | TT_Task | Trainset 08 SM6 - Bonding and Waxing (Kleben und Wachs) | 16/11/2021 | 23/11/2021 | 16/11/2021 | 09/02/2022 | 0 | TK_Complete | 1201082599 | 102 | 1201082599_102
CWS1520 | TT_Task | Trainset 08 SM6 - Customer Inspection (Haltepunkt) | 13/10/2021 | 13/10/2021 | 21/09/2021 | 21/09/2021 | 0 | TK_Complete | 1201082599 | 98 | 1201082599_98
A159850 | TT_Task | Trainset 08 SM2 - Carbody Production (Rohbau Produktion) | 27/09/2021 | 18/10/2021 | 21/09/2021 | 29/09/2021 | 0 | TK_Complete | 1201082599 | 108 | 1201082599_108
A159860 | TT_Task | Trainset 08 SM2 - Carbody Surface (Oberfl?che) | 21/10/2021 | 17/11/2021 | 21/10/2021 | 16/11/2021 | 0 | TK_Complete | 1201082599 | 99 | 1201082599_99
A159870 | TT_Task | Trainset 08 SM2 - Fitout (Innenausbau) | 25/01/2022 | 14/02/2022 | 24/01/2022 | 16/02/2022 | 0 | TK_Complete | 1201082599 | 103 | 1201082599_103
CW1530 | TT_Task | Trainset 08 SM2 - Transport from Goerlitz to Ceska Lipa | 20/10/2021 | 20/10/2021 | 20/10/2021 | 20/10/2021 | 0 | TK_Complete | 1201082599 | 109 | 1201082599_109
CW2790 | TT_Task | Trainset 08 SM2 - Transport from Ceska Lipa to Vienna | 16/11/2021 | 16/11/2021 | 16/11/2021 | 16/11/2021 | 0 | TK_Complete | 1201082599 | 111 | 1201082599_111
CW4050 | TT_Task | Trainset 08 SM2 - Bonding and Waxing (Kleben und Wachs) | 17/11/2021 | 24/11/2021 | 17/11/2021 | 24/01/2022 | 0 | TK_Complete | 1201082599 | 112 | 1201082599_112
CWS1530 | TT_Task | Trainset 08 SM2 - Customer Inspection (Haltepunkt) | 19/10/2021 | 19/10/2021 | 30/09/2021 | 30/09/2021 | 0 | TK_Complete | 1201082599 | 110 | 1201082599_110
A159910 | TT_Task | Trainset 08 BM7 - Carbody Production (Rohbau Produktion) | 22/09/2021 | 12/10/2021 | 16/09/2021 | 23/09/2021 | 0 | TK_Complete | 1201082599 | 113 | 1201082599_113
A159920 | TT_Task | Trainset 08 BM7 - Carbody Surface (Oberfl?che) | 12/10/2021 | 08/11/2021 | 12/10/2021 | 08/11/2021 | 0 | TK_Complete | 1201082599 | 116 | 1201082599_116
A159930 | TT_Task | Trainset 08 BM7 - Fitout (Innenausbau) | 23/02/2022 | 01/03/2022 | 28/02/2022 | 07/03/2022 | 0 | TK_Complete | 1201082599 | 119 | 1201082599_119
CW1550 | TT_Task | Trainset 08 BM7 - Transport from Goerlitz to Ceska Lipa | 14/10/2021 | 14/10/2021 | 12/10/2021 | 12/10/2021 | 0 | TK_Complete | 1201082599 | 114 | 1201082599_114
CW2810 | TT_Task | Trainset 08 BM7 - Transport from Ceska Lipa to Vienna | 08/11/2021 | 09/11/2021 | 08/11/2021 | 09/11/2021 | 0 | TK_Complete | 1201082599 | 117 | 1201082599_117
CW4070 | TT_Task | Trainset 08 BM7 - Bonding and Waxing (Kleben und Wachs) | 09/11/2021 | 16/11/2021 | 16/11/2021 | 25/02/2022 | 0 | TK_Complete | 1201082599 | 118 | 1201082599_118
CWS1550 | TT_Task | Trainset 08 BM7 - Customer Inspection (Haltepunkt) | 13/10/2021 | 13/10/2021 | 24/09/2021 | 24/09/2021 | 0 | TK_Complete | 1201082599 | 115 | 1201082599_115
A159880 | TT_Task | Trainset 08 BM3 - Carbody Production (Rohbau Produktion) | 23/09/2021 | 18/10/2021 | 24/09/2021 | 07/10/2021 | 0 | TK_Complete | 1201082599 | 121 | 1201082599_121
A159890 | TT_Task | Trainset 08 BM3 - Carbody Surface (Oberfl?che) | 21/10/2021 | 17/11/2021 | 21/10/2021 | 15/11/2021 | 0 | TK_Complete | 1201082599 | 123 | 1201082599_123
A159900 | TT_Task | Trainset 08 BM3 - Fitout (Innenausbau) | 14/02/2022 | 10/03/2022 | 15/02/2022 | 08/03/2022 | 0 | TK_Complete | 1201082599 | 126 | 1201082599_126
CW1540 | TT_Task | Trainset 08 BM3 - Transport from Goerlitz to Ceska Lipa | 20/10/2021 | 20/10/2021 | 20/10/2021 | 20/10/2021 | 0 | TK_Complete | 1201082599 | 122 | 1201082599_122
CW2800 | TT_Task | Trainset 08 BM3 - Transport from Ceska Lipa to Vienna | 15/11/2021 | 15/11/2021 | 15/11/2021 | 15/11/2021 | 0 | TK_Complete | 1201082599 | 124 | 1201082599_124
CW4060 | TT_Task | Trainset 08 BM3 - Bonding and Waxing (Kleben und Wachs) | 16/11/2021 | 22/11/2021 | 16/11/2021 | 14/02/2022 | 0 | TK_Complete | 1201082599 | 125 | 1201082599_125
CWS1540 | TT_Task | Trainset 08 BM3 - Customer Inspection (Haltepunkt) | 19/10/2021 | 19/10/2021 | 08/10/2021 | 08/10/2021 | 0 | TK_Complete | 1201082599 | 115 | 1201082599_115
A159940 | TT_Task | Trainset 08 BM1 - Carbody Production (Rohbau Produktion) | 28/09/2021 | 22/10/2021 | 21/09/2021 | 29/09/2021 | 0 | TK_Complete | 1201082599 | 128 | 1201082599_128
A159950 | TT_Task | Trainset 08 BM1 - Carbody Surface (Oberfl?che) | 13/10/2021 | 17/11/2021 | 13/10/2021 | 17/11/2021 | 0 | TK_Complete | 1201082599 | 123 | 1201082599_123
A159960 | TT_Task | Trainset 08 BM1 - Fitout (Innenausbau) | 03/03/2022 | 09/03/2022 | 23/02/2022 | 11/03/2022 | 0 | TK_Complete | 1201082599 | 126 | 1201082599_126
CW1560 | TT_Task | Trainset 08 BM1 - Transport from Goerlitz to Ceska Lipa | 26/10/2021 | 26/10/2021 | 13/10/2021 | 13/10/2021 | 0 | TK_Complete | 1201082599 | 129 | 1201082599_129
CW2820 | TT_Task | Trainset 08 BM1 - Transport from Ceska Lipa to Vienna | 18/11/2021 | 18/11/2021 | 18/11/2021 | 18/11/2021 | 0 | TK_Complete | 1201082599 | 130 | 1201082599_130
CW4080 | TT_Task | Trainset 08 BM1 - Bonding and Waxing (Kleben und Wachs) | 19/11/2021 | 15/12/2021 | 19/11/2021 | 23/02/2022 | 0 | TK_Complete | 1201082599 | 131 | 1201082599_131
CWS1560 | TT_Task | Trainset 08 BM1 - Customer Inspection (Haltepunkt) | 25/10/2021 | 25/10/2021 | 30/09/2021 | 30/09/2021 | 0 | TK_Complete | 1201082599 | 115 | 1201082599_115
A159970 | TT_Task | Trainset 08 - Train Completion (Zugbildung ; Aufsetzen) | 14/03/2022 | 22/03/2022 | 14/03/2022 | nan | 136 | TK_Active | 1201082599 | 132 | 1201082599_132
A159980 | TT_Task | Trainset 08 - Static ; Dynamic Testing (IBN +Finishing) | 15/04/2022 | 09/05/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 163 | 1201082599_163
A159990 | TT_Task | Trainset 08 - Quality Inspection +Rework (Q-Abnahme + Nachartbeit) | 10/05/2022 | 12/05/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 145 | 1201082599_145
A160000 | TT_Task | Trainset 08 - Customer Tests (IBN am Erf?lungsort) | 14/06/2022 | 30/06/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 139 | 1201082599_139
A160010 | TT_Task | Trainset 08 - Preliminary Customer Acceptance (Kundenabnahme) | 01/07/2022 | 04/07/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 140 | 1201082599_140
A160020 | TT_Task | Trainset 08 - Trial Period (Probebetrieb) | 13/10/2022 | 21/01/2023 | nan | nan | 0 | TK_NotStart | 1201082599 | 141 | 1201082599_141
A160030 | TT_Task | Trainset 08 - ATA notification trial operation complete and defect free (Meldung Probebetrieb bestanden und Mangelfrei) | 23/01/2023 | 25/01/2023 | nan | nan | 0 | TK_NotStart | 1201082599 | 142 | 1201082599_142
A238852 | TT_Task | Trainset 08 - Customer Factory Inspection + Rework (Werksabnahme +Nacharbeit) | 13/05/2022 | 18/05/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 137 | 1201082599_137
A238862 | TT_Task | Trainset 08 - Transport to Customer (Transport zum Kunden) | 09/06/2022 | 09/06/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 153 | 1201082599_153
A239492 | TT_Task | Trainset 08 - Welding Repairs (Schwei?reparaturen) | 27/01/2022 | 07/02/2022 | 17/01/2022 | 07/02/2022 | 0 | TK_Complete | 1201082599 | 162 | 1201082599_162
A239552 | TT_Task | Trainset 08 - ?berstellungsfahrt WLB 508 -1 | 05/07/2022 | 05/07/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 157 | 1201082599_157
A239562 | TT_Task | Trainset 08 - Abstellen 508 Werk | 19/05/2022 | 08/06/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 146 | 1201082599_146
A239572 | TT_Task | Trainset 08 - Abstellen WL 508 | 05/07/2022 | 16/08/2022 | nan | nan | 328 | TK_NotStart | 1201082599 | 158 | 1201082599_158
A239582 | TT_Task | Trainset 08 - ?berstellungsfahrt WLB 508 -2 | 13/10/2022 | 13/10/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 157 | 1201082599_157
PAYM10280 | TT_Task | WLB Approval to Start Trial Operation (Freigabe zum Probebetrieb) 08 | 13/10/2022 | 13/10/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 147 | 1201082599_147
A160060 | TT_Task | Trainset 09 CM7 - Carbody Surface (Oberfl?che) | 02/12/2021 | 04/03/2022 | 07/12/2021 | 14/03/2022 | 0 | TK_Complete | 1201082599 | 86 | 1201082599_86
A160070 | TT_Task | Trainset 09 CM7 - Fitout (Innenausbau) | 15/03/2022 | 15/04/2022 | 15/03/2022 | 01/04/2022 | 0 | TK_Complete | 1201082599 | 90 | 1201082599_90
CWS1570 | TT_Task | Trainset 09 CM7 - Customer Inspection (Haltepunkt) | 25/11/2021 | 25/11/2021 | 25/11/2021 | 25/11/2021 | 0 | TK_Complete | 1201082599 | 85 | 1201082599_85
A160090 | TT_Task | Trainset 09 CM1 - Carbody Surface (Oberfl?che) | 31/01/2022 | 21/02/2022 | 31/01/2022 | 16/03/2022 | 0 | TK_Complete | 1201082599 | 86 | 1201082599_86
A160100 | TT_Task | Trainset 09 CM1 - Fitout (Innenausbau) | 17/03/2022 | 20/04/2022 | 17/03/2022 | 05/04/2022 | 0 | TK_Complete | 1201082599 | 90 | 1201082599_90
CWS1580 | TT_Task | Trainset 09 CM1 - Customer Inspection (Haltepunkt) | 25/11/2021 | 25/11/2021 | 25/11/2021 | 25/11/2021 | 0 | TK_Complete | 1201082599 | 85 | 1201082599_85
A160110 | TT_Task | Trainset 09 SM6 - Carbody Production (Rohbau Produktion) | 03/11/2021 | 01/12/2021 | 03/11/2021 | 01/12/2021 | 0 | TK_Complete | 1201082599 | 93 | 1201082599_93
A160120 | TT_Task | Trainset 09 SM6 - Carbody Surface (Oberfl?che) | 06/12/2021 | 17/12/2021 | 06/12/2021 | 17/12/2021 | 0 | TK_Complete | 1201082599 | 99 | 1201082599_99
A160130 | TT_Task | Trainset 09 SM6 - Fitout (Innenausbau) | 15/02/2022 | 10/03/2022 | 15/02/2022 | 10/03/2022 | 0 | TK_Complete | 1201082599 | 103 | 1201082599_103
CW1590 | TT_Task | Trainset 09 SM6 - Transport from Goerlitz to Ceska Lipa | 03/12/2021 | 03/12/2021 | 03/12/2021 | 03/12/2021 | 0 | TK_Complete | 1201082599 | 97 | 1201082599_97
CW2850 | TT_Task | Trainset 09 SM6 - Transport from Ceska Lipa to Vienna | 20/12/2021 | 20/12/2021 | 20/12/2021 | 20/12/2021 | 0 | TK_Complete | 1201082599 | 101 | 1201082599_101
CW4110 | TT_Task | Trainset 09 SM6 - Bonding and Waxing (Kleben und Wachs) | 02/02/2022 | 11/02/2022 | 02/02/2022 | 14/02/2022 | 0 | TK_Complete | 1201082599 | 102 | 1201082599_102
CWS1590 | TT_Task | Trainset 09 SM6 - Customer Inspection (Haltepunkt) | 02/12/2021 | 02/12/2021 | 02/12/2021 | 03/12/2021 | 0 | TK_Complete | 1201082599 | 98 | 1201082599_98
A160140 | TT_Task | Trainset 09 SM2 - Carbody Production (Rohbau Produktion) | 18/11/2021 | 08/12/2021 | 18/11/2021 | 08/12/2021 | 0 | TK_Complete | 1201082599 | 108 | 1201082599_108
A160150 | TT_Task | Trainset 09 SM2 - Carbody Surface (Oberfl?che) | 13/12/2021 | 07/01/2022 | 13/12/2021 | 07/01/2022 | 0 | TK_Complete | 1201082599 | 99 | 1201082599_99
A160160 | TT_Task | Trainset 09 SM2 - Fitout (Innenausbau) | 18/02/2022 | 15/03/2022 | 18/02/2022 | 15/03/2022 | 0 | TK_Complete | 1201082599 | 103 | 1201082599_103
CW1600 | TT_Task | Trainset 09 SM2 - Transport from Goerlitz to Ceska Lipa | 10/12/2021 | 10/12/2021 | 10/12/2021 | 10/12/2021 | 0 | TK_Complete | 1201082599 | 109 | 1201082599_109
CW2860 | TT_Task | Trainset 09 SM2 - Transport from Ceska Lipa to Vienna | 10/01/2022 | 10/01/2022 | 10/01/2022 | 10/01/2022 | 0 | TK_Complete | 1201082599 | 111 | 1201082599_111
CW4120 | TT_Task | Trainset 09 SM2 - Bonding and Waxing (Kleben und Wachs) | 04/02/2022 | 15/02/2022 | 04/02/2022 | 17/02/2022 | 0 | TK_Complete | 1201082599 | 112 | 1201082599_112
CWS1600 | TT_Task | Trainset 09 SM2 - Customer Inspection (Haltepunkt) | 09/12/2021 | 09/12/2021 | 09/12/2021 | 09/12/2021 | 0 | TK_Complete | 1201082599 | 110 | 1201082599_110
A160200 | TT_Task | Trainset 09 BM7 - Carbody Production (Rohbau Produktion) | 14/10/2021 | 02/11/2021 | 14/10/2021 | 08/11/2021 | 0 | TK_Complete | 1201082599 | 113 | 1201082599_113
A160210 | TT_Task | Trainset 09 BM7 - Carbody Surface (Oberfl?che) | 11/11/2021 | 08/12/2021 | 11/11/2021 | 06/12/2021 | 0 | TK_Complete | 1201082599 | 116 | 1201082599_116
A160220 | TT_Task | Trainset 09 BM7 - Fitout (Innenausbau) | 25/02/2022 | 14/03/2022 | 25/02/2022 | 14/03/2022 | 0 | TK_Complete | 1201082599 | 119 | 1201082599_119
CW1620 | TT_Task | Trainset 09 BM7 - Transport from Goerlitz to Ceska Lipa | 10/11/2021 | 11/11/2021 | 10/11/2021 | 11/11/2021 | 0 | TK_Complete | 1201082599 | 114 | 1201082599_114
CW2880 | TT_Task | Trainset 09 BM7 - Transport from Ceska Lipa to Vienna | 07/12/2021 | 07/12/2021 | 07/12/2021 | 07/12/2021 | 0 | TK_Complete | 1201082599 | 117 | 1201082599_117
CW4140 | TT_Task | Trainset 09 BM7 - Bonding and Waxing (Kleben und Wachs) | 31/01/2022 | 03/02/2022 | 31/01/2022 | 18/02/2022 | 0 | TK_Complete | 1201082599 | 118 | 1201082599_118
CWS1620 | TT_Task | Trainset 09 BM7 - Customer Inspection (Haltepunkt) | 09/11/2021 | 09/11/2021 | 09/11/2021 | 09/11/2021 | 0 | TK_Complete | 1201082599 | 115 | 1201082599_115
A160170 | TT_Task | Trainset 09 BM3 - Carbody Production (Rohbau Produktion) | 24/11/2021 | 02/12/2021 | 24/11/2021 | 08/12/2021 | 0 | TK_Complete | 1201082599 | 121 | 1201082599_121
A160180 | TT_Task | Trainset 09 BM3 - Carbody Surface (Oberfl?che) | 13/12/2021 | 07/01/2022 | 13/12/2021 | 07/01/2022 | 0 | TK_Complete | 1201082599 | 123 | 1201082599_123
A160190 | TT_Task | Trainset 09 BM3 - Fitout (Innenausbau) | 23/02/2022 | 16/03/2022 | 23/02/2022 | 16/03/2022 | 0 | TK_Complete | 1201082599 | 126 | 1201082599_126
CW1610 | TT_Task | Trainset 09 BM3 - Transport from Goerlitz to Ceska Lipa | 10/12/2021 | 10/12/2021 | 10/12/2021 | 10/12/2021 | 0 | TK_Complete | 1201082599 | 122 | 1201082599_122
CW2870 | TT_Task | Trainset 09 BM3 - Transport from Ceska Lipa to Vienna | 10/01/2022 | 10/01/2022 | 10/01/2022 | 10/01/2022 | 0 | TK_Complete | 1201082599 | 124 | 1201082599_124
CW4130 | TT_Task | Trainset 09 BM3 - Bonding and Waxing (Kleben und Wachs) | 17/01/2022 | 26/01/2022 | 02/02/2022 | 22/02/2022 | 0 | TK_Complete | 1201082599 | 125 | 1201082599_125
CWS1610 | TT_Task | Trainset 09 BM3 - Customer Inspection (Haltepunkt) | 09/12/2021 | 09/12/2021 | 09/12/2021 | 09/12/2021 | 0 | TK_Complete | 1201082599 | 115 | 1201082599_115
A160230 | TT_Task | Trainset 09 BM1 - Carbody Production (Rohbau Produktion) | 05/11/2021 | 12/11/2021 | 05/11/2021 | 01/12/2021 | 0 | TK_Complete | 1201082599 | 128 | 1201082599_128
A160240 | TT_Task | Trainset 09 BM1 - Carbody Surface (Oberfl?che) | 06/12/2021 | 20/12/2021 | 06/12/2021 | 20/12/2021 | 0 | TK_Complete | 1201082599 | 123 | 1201082599_123
A160250 | TT_Task | Trainset 09 BM1 - Fitout (Innenausbau) | 25/02/2022 | 18/03/2022 | 25/02/2022 | 18/03/2022 | 0 | TK_Complete | 1201082599 | 126 | 1201082599_126
CW1630 | TT_Task | Trainset 09 BM1 - Transport from Goerlitz to Ceska Lipa | 03/12/2021 | 03/12/2021 | 03/12/2021 | 03/12/2021 | 0 | TK_Complete | 1201082599 | 129 | 1201082599_129
CW2890 | TT_Task | Trainset 09 BM1 - Transport from Ceska Lipa to Vienna | 20/12/2021 | 21/12/2021 | 20/12/2021 | 21/12/2021 | 0 | TK_Complete | 1201082599 | 130 | 1201082599_130
CW4150 | TT_Task | Trainset 09 BM1 - Bonding and Waxing (Kleben und Wachs) | 08/02/2022 | 11/02/2022 | 08/02/2022 | 24/02/2022 | 0 | TK_Complete | 1201082599 | 131 | 1201082599_131
CWS1630 | TT_Task | Trainset 09 BM1 - Customer Inspection (Haltepunkt) | 02/12/2021 | 02/12/2021 | 02/12/2021 | 02/12/2021 | 0 | TK_Complete | 1201082599 | 115 | 1201082599_115
A160260 | TT_Task | Trainset 09 - Train Completion (Zugbildung ; Aufsetzen) | 04/04/2022 | 14/04/2022 | nan | nan | 128 | TK_NotStart | 1201082599 | 132 | 1201082599_132
A160270 | TT_Task | Trainset 09 - Static ; Dynamic Testing (IBN +Finishing) | 10/05/2022 | 24/05/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 163 | 1201082599_163
A160280 | TT_Task | Trainset 09 - Quality Inspection +Rework (Q-Abnahme + Nachartbeit) | 25/05/2022 | 01/06/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 145 | 1201082599_145
A160290 | TT_Task | Trainset 09 - Customer Tests (IBN am Erf?lungsort) | 22/09/2022 | 05/10/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 139 | 1201082599_139
A160300 | TT_Task | Trainset 09 - Preliminary Customer Acceptance (Kundenabnahme) | 06/10/2022 | 07/10/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 140 | 1201082599_140
A160310 | TT_Task | Trainset 09 - Trial Period (Probebetrieb) | 24/10/2022 | 01/02/2023 | nan | nan | 0 | TK_NotStart | 1201082599 | 141 | 1201082599_141
A160320 | TT_Task | Trainset 09 - ATA notification trial operation complete and defect free (Meldung Probebetrieb bestanden und Mangelfrei) | 02/02/2023 | 06/02/2023 | nan | nan | 0 | TK_NotStart | 1201082599 | 142 | 1201082599_142
A238872 | TT_Task | Trainset 09 - Customer Factory Inspection + Rework (Werksabnahme +Nacharbeit) | 02/06/2022 | 09/06/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 137 | 1201082599_137
A238882 | TT_Task | Trainset 09 - Transport to Customer (Transport zum Kunden) | 18/07/2022 | 18/07/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 153 | 1201082599_153
A239722 | TT_Task | Trainset 09 - Abstellen Werk 509 | 10/06/2022 | 15/07/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 146 | 1201082599_146
A239732 | TT_Task | Trainset 09 - ?berstellungsfahrt WLB 509 | 10/10/2022 | 10/10/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 157 | 1201082599_157
A239742 | TT_Task | Trainset 09 - Abstellen WL 509 | 10/10/2022 | 11/10/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 158 | 1201082599_158
A239752 | TT_Task | Trainset 09 - ?berstellungsfahrt WLB 509 | 12/10/2022 | 12/10/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 157 | 1201082599_157
PAYM10290 | TT_Task | WLB Approval to Start Trial Operation (Freigabe zum Probebetrieb) 09 | 12/10/2022 | 12/10/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 147 | 1201082599_147
A160350 | TT_Task | Trainset 10 CM7 - Carbody Surface (Oberfl?che) | 01/02/2022 | 17/03/2022 | 14/03/2022 | nan | 0 | TK_Active | 1201082599 | 164 | 1201082599_164
A160360 | TT_Task | Trainset 10 CM7 - Fitout (Innenausbau) | 05/04/2022 | 14/04/2022 | nan | nan | 8 | TK_NotStart | 1201082599 | 165 | 1201082599_165
CWS1640 | TT_Task | Trainset 10 CM7 - Customer Inspection (Haltepunkt) | 01/02/2022 | 01/02/2022 | 01/02/2022 | 01/02/2022 | 0 | TK_Complete | 1201082599 | 166 | 1201082599_166
A160380 | TT_Task | Trainset 10 CM1 - Carbody Surface (Oberfl?che) | 22/02/2022 | 15/03/2022 | 14/03/2022 | nan | 0 | TK_Active | 1201082599 | 164 | 1201082599_164
A160390 | TT_Task | Trainset 10 CM1 - Fitout (Innenausbau) | 07/04/2022 | 19/04/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 165 | 1201082599_165
CWS1650 | TT_Task | Trainset 10 CM1 - Customer Inspection (Haltepunkt) | 02/03/2022 | 02/03/2022 | 22/02/2022 | 22/02/2022 | 0 | TK_Complete | 1201082599 | 166 | 1201082599_166
A160400 | TT_Task | Trainset 10 SM6 - Carbody Production (Rohbau Produktion) | 02/12/2021 | 04/01/2022 | 02/12/2021 | 04/01/2022 | 0 | TK_Complete | 1201082599 | 93 | 1201082599_93
A160410 | TT_Task | Trainset 10 SM6 - Carbody Surface (Oberfl?che) | 07/01/2022 | 24/01/2022 | 07/01/2022 | 24/01/2022 | 0 | TK_Complete | 1201082599 | 167 | 1201082599_167
A160420 | TT_Task | Trainset 10 SM6 - Fitout (Innenausbau) | 03/03/2022 | 05/04/2022 | nan | nan | 64 | TK_NotStart | 1201082599 | 168 | 1201082599_168
CW1660 | TT_Task | Trainset 10 SM6 - Transport from Goerlitz to Ceska Lipa | 06/01/2022 | 06/01/2022 | 06/01/2022 | 06/01/2022 | 0 | TK_Complete | 1201082599 | 97 | 1201082599_97
CW2920 | TT_Task | Trainset 10 SM6 - Transport from Ceska Lipa to Vienna | 24/01/2022 | 25/01/2022 | 24/01/2022 | 25/01/2022 | 0 | TK_Complete | 1201082599 | 101 | 1201082599_101
CW4180 | TT_Task | Trainset 10 SM6 - Bonding and Waxing (Kleben und Wachs) | 17/02/2022 | 07/03/2022 | 17/02/2022 | 02/03/2022 | 0 | TK_Complete | 1201082599 | 102 | 1201082599_102
CWS1660 | TT_Task | Trainset 10 SM6 - Customer Inspection (Haltepunkt) | 05/01/2022 | 05/01/2022 | 05/01/2022 | 05/01/2022 | 0 | TK_Complete | 1201082599 | 98 | 1201082599_98
A160430 | TT_Task | Trainset 10 SM2 - Carbody Production (Rohbau Produktion) | 09/12/2021 | 30/12/2021 | 09/12/2021 | 30/12/2021 | 0 | TK_Complete | 1201082599 | 108 | 1201082599_108
A160440 | TT_Task | Trainset 10 SM2 - Carbody Surface (Oberfl?che) | 04/01/2022 | 19/01/2022 | 04/01/2022 | 19/01/2022 | 0 | TK_Complete | 1201082599 | 169 | 1201082599_169
A160450 | TT_Task | Trainset 10 SM2 - Fitout (Innenausbau) | 15/03/2022 | 07/04/2022 | 16/03/2022 | nan | 56 | TK_Active | 1201082599 | 170 | 1201082599_170
CW1670 | TT_Task | Trainset 10 SM2 - Transport from Goerlitz to Ceska Lipa | 03/01/2022 | 03/01/2022 | 03/01/2022 | 03/01/2022 | 0 | TK_Complete | 1201082599 | 109 | 1201082599_109
CW2930 | TT_Task | Trainset 10 SM2 - Transport from Ceska Lipa to Vienna | 19/01/2022 | 20/01/2022 | 19/01/2022 | 20/01/2022 | 0 | TK_Complete | 1201082599 | 111 | 1201082599_111
CW4190 | TT_Task | Trainset 10 SM2 - Bonding and Waxing (Kleben und Wachs) | 17/02/2022 | 11/03/2022 | 17/02/2022 | 15/03/2022 | 0 | TK_Complete | 1201082599 | 112 | 1201082599_112
CWS1670 | TT_Task | Trainset 10 SM2 - Customer Inspection (Haltepunkt) | 31/12/2021 | 31/12/2021 | 31/12/2021 | 31/12/2021 | 0 | TK_Complete | 1201082599 | 110 | 1201082599_110
A160490 | TT_Task | Trainset 10 BM7 - Carbody Production (Rohbau Produktion) | 26/11/2021 | 14/12/2021 | 26/11/2021 | 14/12/2021 | 0 | TK_Complete | 1201082599 | 113 | 1201082599_113
A160500 | TT_Task | Trainset 10 BM7 - Carbody Surface (Oberfl?che) | 17/12/2021 | 19/01/2022 | 17/12/2021 | 19/01/2022 | 0 | TK_Complete | 1201082599 | 116 | 1201082599_116
A160510 | TT_Task | Trainset 10 BM7 - Fitout (Innenausbau) | 23/03/2022 | 29/03/2022 | 16/03/2022 | nan | 72 | TK_Active | 1201082599 | 119 | 1201082599_119
CW1690 | TT_Task | Trainset 10 BM7 - Transport from Goerlitz to Ceska Lipa | 16/12/2021 | 16/12/2021 | 16/12/2021 | 16/12/2021 | 0 | TK_Complete | 1201082599 | 114 | 1201082599_114
CW2950 | TT_Task | Trainset 10 BM7 - Transport from Ceska Lipa to Vienna | 20/01/2022 | 20/01/2022 | 20/01/2022 | 20/01/2022 | 0 | TK_Complete | 1201082599 | 117 | 1201082599_117
CW4210 | TT_Task | Trainset 10 BM7 - Bonding and Waxing (Kleben und Wachs) | 17/02/2022 | 07/03/2022 | 28/02/2022 | 15/03/2022 | 0 | TK_Complete | 1201082599 | 118 | 1201082599_118
CWS1690 | TT_Task | Trainset 10 BM7 - Customer Inspection (Haltepunkt) | 15/12/2021 | 15/12/2021 | 15/12/2021 | 15/12/2021 | 0 | TK_Complete | 1201082599 | 171 | 1201082599_171
A160460 | TT_Task | Trainset 10 BM3 - Carbody Production (Rohbau Produktion) | 09/12/2021 | 30/12/2021 | 09/12/2021 | 30/12/2021 | 0 | TK_Complete | 1201082599 | 121 | 1201082599_121
A160470 | TT_Task | Trainset 10 BM3 - Carbody Surface (Oberfl?che) | 04/01/2022 | 19/01/2022 | 04/01/2022 | 19/01/2022 | 0 | TK_Complete | 1201082599 | 172 | 1201082599_172
A160480 | TT_Task | Trainset 10 BM3 - Fitout (Innenausbau) | 21/03/2022 | 07/04/2022 | nan | nan | 48 | TK_NotStart | 1201082599 | 173 | 1201082599_173
CW1680 | TT_Task | Trainset 10 BM3 - Transport from Goerlitz to Ceska Lipa | 03/01/2022 | 03/01/2022 | 03/01/2022 | 03/01/2022 | 0 | TK_Complete | 1201082599 | 122 | 1201082599_122
CW2940 | TT_Task | Trainset 10 BM3 - Transport from Ceska Lipa to Vienna | 19/01/2022 | 20/01/2022 | 19/01/2022 | 20/01/2022 | 0 | TK_Complete | 1201082599 | 124 | 1201082599_124
CW4200 | TT_Task | Trainset 10 BM3 - Bonding and Waxing (Kleben und Wachs) | 17/02/2022 | 11/03/2022 | 17/02/2022 | 17/03/2022 | 0 | TK_Complete | 1201082599 | 125 | 1201082599_125
CWS1680 | TT_Task | Trainset 10 BM3 - Customer Inspection (Haltepunkt) | 31/12/2021 | 31/12/2021 | 31/12/2021 | 31/12/2021 | 0 | TK_Complete | 1201082599 | 174 | 1201082599_174
A160520 | TT_Task | Trainset 10 BM1 - Carbody Production (Rohbau Produktion) | 02/12/2021 | 04/01/2022 | 02/12/2021 | 04/01/2022 | 0 | TK_Complete | 1201082599 | 128 | 1201082599_128
A160530 | TT_Task | Trainset 10 BM1 - Carbody Surface (Oberfl?che) | 07/01/2022 | 24/01/2022 | 07/01/2022 | 24/01/2022 | 0 | TK_Complete | 1201082599 | 172 | 1201082599_172
A160540 | TT_Task | Trainset 10 BM1 - Fitout (Innenausbau) | 22/03/2022 | 08/04/2022 | nan | nan | 56 | TK_NotStart | 1201082599 | 173 | 1201082599_173
CW1700 | TT_Task | Trainset 10 BM1 - Transport from Goerlitz to Ceska Lipa | 06/01/2022 | 06/01/2022 | 06/01/2022 | 06/01/2022 | 0 | TK_Complete | 1201082599 | 129 | 1201082599_129
CW2960 | TT_Task | Trainset 10 BM1 - Transport from Ceska Lipa to Vienna | 24/01/2022 | 25/01/2022 | 24/01/2022 | 25/01/2022 | 0 | TK_Complete | 1201082599 | 130 | 1201082599_130
CW4220 | TT_Task | Trainset 10 BM1 - Bonding and Waxing (Kleben und Wachs) | 17/02/2022 | 17/03/2022 | 07/03/2022 | nan | 0 | TK_Active | 1201082599 | 131 | 1201082599_131
CWS1700 | TT_Task | Trainset 10 BM1 - Customer Inspection (Haltepunkt) | 05/01/2022 | 05/01/2022 | 05/01/2022 | 05/01/2022 | 0 | TK_Complete | 1201082599 | 171 | 1201082599_171
A160550 | TT_Task | Trainset 10 - Train Completion (Zugbildung ; Aufsetzen) | 19/04/2022 | 29/04/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 175 | 1201082599_175
A160560 | TT_Task | Trainset 10 - Static ; Dynamic Testing (IBN +Finishing) | 02/05/2022 | 13/05/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 163 | 1201082599_163
A160570 | TT_Task | Trainset 10 - Quality Inspection +Rework (Q-Abnahme + Nachartbeit) | 16/05/2022 | 19/05/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 145 | 1201082599_145
A160580 | TT_Task | Trainset 10 - Customer Tests (IBN am Erf?lungsort) | 06/10/2022 | 19/10/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 139 | 1201082599_139
A160590 | TT_Task | Trainset 10 - Preliminary Customer Acceptance (Kundenabnahme) | 20/10/2022 | 21/10/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 140 | 1201082599_140
A160600 | TT_Task | Trainset 10 - Trial Period (Probebetrieb) | 24/10/2022 | 01/02/2023 | nan | nan | 0 | TK_NotStart | 1201082599 | 176 | 1201082599_176
A160610 | TT_Task | Trainset 10 - ATA notification trial operation complete and defect free (Meldung Probebetrieb bestanden und Mangelfrei) | 02/02/2023 | 06/02/2023 | nan | nan | 0 | TK_NotStart | 1201082599 | 142 | 1201082599_142
A238892 | TT_Task | Trainset 10 - Customer Factory Inspection + Rework (Werksabnahme +Nacharbeit) | 20/05/2022 | 25/05/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 137 | 1201082599_137
A238902 | TT_Task | Trainset 10 - Transport to Customer (Transport zum Kunden) | 30/05/2022 | 30/05/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 177 | 1201082599_177
PAYM10300 | TT_Task | WLB Approval to Start Trial Operation (Freigabe zum Probebetrieb) 10 | 24/10/2022 | 24/10/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 147 | 1201082599_147
A160640 | TT_Task | Trainset 11 CM7 - Carbody Surface (Oberfl?che) | 22/02/2022 | 15/03/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 164 | 1201082599_164
A160650 | TT_Task | Trainset 11 CM7 - Fitout (Innenausbau) | 16/03/2022 | 25/03/2022 | nan | nan | 192 | TK_NotStart | 1201082599 | 165 | 1201082599_165
CWS1710 | TT_Task | Trainset 11 CM7 - Customer Inspection (Haltepunkt) | 22/02/2022 | 22/02/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 166 | 1201082599_166
A160670 | TT_Task | Trainset 11 CM1 - Carbody Surface (Oberfl?che) | 15/03/2022 | 05/04/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 164 | 1201082599_164
A160680 | TT_Task | Trainset 11 CM1 - Fitout (Innenausbau) | 06/04/2022 | 15/04/2022 | nan | nan | 80 | TK_NotStart | 1201082599 | 165 | 1201082599_165
CWS1720 | TT_Task | Trainset 11 CM1 - Customer Inspection (Haltepunkt) | 15/03/2022 | 15/03/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 166 | 1201082599_166
A160690 | TT_Task | Trainset 11 SM6 - Carbody Production (Rohbau Produktion) | 05/01/2022 | 05/01/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 93 | 1201082599_93
A160700 | TT_Task | Trainset 11 SM6 - Carbody Surface (Oberfl?che) | 10/01/2022 | 24/01/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 167 | 1201082599_167
A160710 | TT_Task | Trainset 11 SM6 - Fitout (Innenausbau) | 24/03/2022 | 19/04/2022 | nan | nan | 64 | TK_NotStart | 1201082599 | 168 | 1201082599_168
CW1730 | TT_Task | Trainset 11 SM6 - Transport from Goerlitz to Ceska Lipa | 07/01/2022 | 07/01/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 97 | 1201082599_97
CW2990 | TT_Task | Trainset 11 SM6 - Transport from Ceska Lipa to Vienna | 24/01/2022 | 25/01/2022 | nan | nan | 204 | TK_NotStart | 1201082599 | 101 | 1201082599_101
CW4250 | TT_Task | Trainset 11 SM6 - Bonding and Waxing (Kleben und Wachs) | 02/03/2022 | 22/03/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 102 | 1201082599_102
CWS1730 | TT_Task | Trainset 11 SM6 - Customer Inspection (Haltepunkt) | 06/01/2022 | 06/01/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 98 | 1201082599_98
A160720 | TT_Task | Trainset 11 SM2 - Carbody Production (Rohbau Produktion) | 31/12/2021 | 07/01/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 108 | 1201082599_108
A160730 | TT_Task | Trainset 11 SM2 - Carbody Surface (Oberfl?che) | 12/01/2022 | 26/01/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 169 | 1201082599_169
A160740 | TT_Task | Trainset 11 SM2 - Fitout (Innenausbau) | 05/04/2022 | 29/04/2022 | nan | nan | 16 | TK_NotStart | 1201082599 | 170 | 1201082599_170
CW1740 | TT_Task | Trainset 11 SM2 - Transport from Goerlitz to Ceska Lipa | 11/01/2022 | 11/01/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 109 | 1201082599_109
CW3000 | TT_Task | Trainset 11 SM2 - Transport from Ceska Lipa to Vienna | 26/01/2022 | 27/01/2022 | nan | nan | 260 | TK_NotStart | 1201082599 | 111 | 1201082599_111
CW4260 | TT_Task | Trainset 11 SM2 - Bonding and Waxing (Kleben und Wachs) | 15/03/2022 | 04/04/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 112 | 1201082599_112
CWS1740 | TT_Task | Trainset 11 SM2 - Customer Inspection (Haltepunkt) | 10/01/2022 | 10/01/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 110 | 1201082599_110
A160780 | TT_Task | Trainset 11 BM7 - Carbody Production (Rohbau Produktion) | 20/12/2021 | 04/01/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 113 | 1201082599_113
A160790 | TT_Task | Trainset 11 BM7 - Carbody Surface (Oberfl?che) | 07/01/2022 | 21/01/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 116 | 1201082599_116
A160800 | TT_Task | Trainset 11 BM7 - Fitout (Innenausbau) | 11/04/2022 | 12/04/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 119 | 1201082599_119
CW1760 | TT_Task | Trainset 11 BM7 - Transport from Goerlitz to Ceska Lipa | 06/01/2022 | 06/01/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 114 | 1201082599_114
CW3020 | TT_Task | Trainset 11 BM7 - Transport from Ceska Lipa to Vienna | 21/01/2022 | 24/01/2022 | nan | nan | 284 | TK_NotStart | 1201082599 | 117 | 1201082599_117
CW4280 | TT_Task | Trainset 11 BM7 - Bonding and Waxing (Kleben und Wachs) | 15/03/2022 | 04/04/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 118 | 1201082599_118
CWS1760 | TT_Task | Trainset 11 BM7 - Customer Inspection (Haltepunkt) | 05/01/2022 | 05/01/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 171 | 1201082599_171
A160750 | TT_Task | Trainset 11 BM3 - Carbody Production (Rohbau Produktion) | 31/12/2021 | 07/01/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 121 | 1201082599_121
A160760 | TT_Task | Trainset 11 BM3 - Carbody Surface (Oberfl?che) | 12/01/2022 | 26/01/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 172 | 1201082599_172
A160770 | TT_Task | Trainset 11 BM3 - Fitout (Innenausbau) | 11/04/2022 | 29/04/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 173 | 1201082599_173
CW1750 | TT_Task | Trainset 11 BM3 - Transport from Goerlitz to Ceska Lipa | 11/01/2022 | 11/01/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 122 | 1201082599_122
CW3010 | TT_Task | Trainset 11 BM3 - Transport from Ceska Lipa to Vienna | 26/01/2022 | 27/01/2022 | nan | nan | 276 | TK_NotStart | 1201082599 | 124 | 1201082599_124
CW4270 | TT_Task | Trainset 11 BM3 - Bonding and Waxing (Kleben und Wachs) | 17/03/2022 | 06/04/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 125 | 1201082599_125
CWS1750 | TT_Task | Trainset 11 BM3 - Customer Inspection (Haltepunkt) | 10/01/2022 | 10/01/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 174 | 1201082599_174
A160810 | TT_Task | Trainset 11 BM1 - Carbody Production (Rohbau Produktion) | 05/01/2022 | 10/01/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 128 | 1201082599_128
A160820 | TT_Task | Trainset 11 BM1 - Carbody Surface (Oberfl?che) | 13/01/2022 | 27/01/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 172 | 1201082599_172
A160830 | TT_Task | Trainset 11 BM1 - Fitout (Innenausbau) | 12/04/2022 | 02/05/2022 | nan | nan | 8 | TK_NotStart | 1201082599 | 178 | 1201082599_178
CW1770 | TT_Task | Trainset 11 BM1 - Transport from Goerlitz to Ceska Lipa | 12/01/2022 | 12/01/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 129 | 1201082599_129
CW3030 | TT_Task | Trainset 11 BM1 - Transport from Ceska Lipa to Vienna | 27/01/2022 | 28/01/2022 | nan | nan | 292 | TK_NotStart | 1201082599 | 130 | 1201082599_130
CW4290 | TT_Task | Trainset 11 BM1 - Bonding and Waxing (Kleben und Wachs) | 22/03/2022 | 11/04/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 131 | 1201082599_131
CWS1770 | TT_Task | Trainset 11 BM1 - Customer Inspection (Haltepunkt) | 11/01/2022 | 11/01/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 171 | 1201082599_171
A160840 | TT_Task | Trainset 11 - Train Completion (Zugbildung ; Aufsetzen) | 02/05/2022 | 12/05/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 175 | 1201082599_175
A160850 | TT_Task | Trainset 11 - Static ; Dynamic Testing (IBN +Finishing) | 13/05/2022 | 31/05/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 163 | 1201082599_163
A160860 | TT_Task | Trainset 11 - Quality Inspection +Rework (Q-Abnahme + Nachartbeit) | 01/06/2022 | 07/06/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 145 | 1201082599_145
A160870 | TT_Task | Trainset 11 - Customer Tests (IBN am Erf?lungsort) | 20/10/2022 | 07/11/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 139 | 1201082599_139
A160880 | TT_Task | Trainset 11 - Preliminary Customer Acceptance (Kundenabnahme) | 08/11/2022 | 09/11/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 140 | 1201082599_140
A160890 | TT_Task | Trainset 11 - Trial Period (Probebetrieb) | 24/11/2022 | 04/03/2023 | nan | nan | 0 | TK_NotStart | 1201082599 | 176 | 1201082599_176
A160900 | TT_Task | Trainset 11 - ATA notification trial operation complete and defect free (Meldung Probebetrieb bestanden und Mangelfrei) | 06/03/2023 | 08/03/2023 | nan | nan | 0 | TK_NotStart | 1201082599 | 142 | 1201082599_142
A238912 | TT_Task | Trainset 11 - Customer Factory Inspection + Rework (Werksabnahme +Nacharbeit) | 08/06/2022 | 13/06/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 137 | 1201082599_137
A238922 | TT_Task | Trainset 11 - Transport to Customer (Transport zum Kunden) | 14/06/2022 | 14/06/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 177 | 1201082599_177
PAYM10310 | TT_Task | WLB Approval to Start Trial Operation (Freigabe zum Probebetrieb) 11 | 10/11/2022 | 10/11/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 147 | 1201082599_147
A160930 | TT_Task | Trainset 12 CM7 - Carbody Surface (Oberfl?che) | 15/03/2022 | 05/04/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 164 | 1201082599_164
A160940 | TT_Task | Trainset 12 CM7 - Fitout (Innenausbau) | 06/04/2022 | 15/04/2022 | nan | nan | 200 | TK_NotStart | 1201082599 | 165 | 1201082599_165
CWS1780 | TT_Task | Trainset 12 CM7 - Customer Inspection (Haltepunkt) | 15/03/2022 | 15/03/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 166 | 1201082599_166
A160960 | TT_Task | Trainset 12 CM1 - Carbody Surface (Oberfl?che) | 05/04/2022 | 27/04/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 164 | 1201082599_164
A160970 | TT_Task | Trainset 12 CM1 - Fitout (Innenausbau) | 28/04/2022 | 09/05/2022 | nan | nan | 88 | TK_NotStart | 1201082599 | 165 | 1201082599_165
CWS1790 | TT_Task | Trainset 12 CM1 - Customer Inspection (Haltepunkt) | 05/04/2022 | 05/04/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 166 | 1201082599_166
A160980 | TT_Task | Trainset 12 SM6 - Carbody Production (Rohbau Produktion) | 20/01/2022 | 27/01/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 93 | 1201082599_93
A160990 | TT_Task | Trainset 12 SM6 - Carbody Surface (Oberfl?che) | 01/02/2022 | 15/02/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 167 | 1201082599_167
A161000 | TT_Task | Trainset 12 SM6 - Fitout (Innenausbau) | 14/04/2022 | 10/05/2022 | nan | nan | 72 | TK_NotStart | 1201082599 | 168 | 1201082599_168
CW1800 | TT_Task | Trainset 12 SM6 - Transport from Goerlitz to Ceska Lipa | 31/01/2022 | 31/01/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 97 | 1201082599_97
CW3060 | TT_Task | Trainset 12 SM6 - Transport from Ceska Lipa to Vienna | 15/02/2022 | 16/02/2022 | nan | nan | 197 | TK_NotStart | 1201082599 | 101 | 1201082599_101
CW4320 | TT_Task | Trainset 12 SM6 - Bonding and Waxing (Kleben und Wachs) | 23/03/2022 | 12/04/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 102 | 1201082599_102
CWS1800 | TT_Task | Trainset 12 SM6 - Customer Inspection (Haltepunkt) | 28/01/2022 | 28/01/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 98 | 1201082599_98
A161010 | TT_Task | Trainset 12 SM2 - Carbody Production (Rohbau Produktion) | 24/01/2022 | 01/02/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 108 | 1201082599_108
A161020 | TT_Task | Trainset 12 SM2 - Carbody Surface (Oberfl?che) | 04/02/2022 | 18/02/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 169 | 1201082599_169
A161030 | TT_Task | Trainset 12 SM2 - Fitout (Innenausbau) | 27/04/2022 | 20/05/2022 | nan | nan | 24 | TK_NotStart | 1201082599 | 170 | 1201082599_170
CW1810 | TT_Task | Trainset 12 SM2 - Transport from Goerlitz to Ceska Lipa | 03/02/2022 | 03/02/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 109 | 1201082599_109
CW3070 | TT_Task | Trainset 12 SM2 - Transport from Ceska Lipa to Vienna | 18/02/2022 | 21/02/2022 | nan | nan | 245 | TK_NotStart | 1201082599 | 111 | 1201082599_111
CW4330 | TT_Task | Trainset 12 SM2 - Bonding and Waxing (Kleben und Wachs) | 05/04/2022 | 26/04/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 112 | 1201082599_112
CWS1810 | TT_Task | Trainset 12 SM2 - Customer Inspection (Haltepunkt) | 02/02/2022 | 02/02/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 110 | 1201082599_110
A161070 | TT_Task | Trainset 12 BM7 - Carbody Production (Rohbau Produktion) | 19/01/2022 | 26/01/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 113 | 1201082599_113
A161080 | TT_Task | Trainset 12 BM7 - Carbody Surface (Oberfl?che) | 31/01/2022 | 14/02/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 116 | 1201082599_116
A161090 | TT_Task | Trainset 12 BM7 - Fitout (Innenausbau) | 03/05/2022 | 20/05/2022 | nan | nan | 8 | TK_NotStart | 1201082599 | 119 | 1201082599_119
CW1830 | TT_Task | Trainset 12 BM7 - Transport from Goerlitz to Ceska Lipa | 28/01/2022 | 28/01/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 114 | 1201082599_114
CW3090 | TT_Task | Trainset 12 BM7 - Transport from Ceska Lipa to Vienna | 14/02/2022 | 15/02/2022 | nan | nan | 277 | TK_NotStart | 1201082599 | 117 | 1201082599_117
CW4350 | TT_Task | Trainset 12 BM7 - Bonding and Waxing (Kleben und Wachs) | 05/04/2022 | 26/04/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 118 | 1201082599_118
CWS1830 | TT_Task | Trainset 12 BM7 - Customer Inspection (Haltepunkt) | 27/01/2022 | 27/01/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 171 | 1201082599_171
A161040 | TT_Task | Trainset 12 BM3 - Carbody Production (Rohbau Produktion) | 21/01/2022 | 31/01/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 121 | 1201082599_121
A161050 | TT_Task | Trainset 12 BM3 - Carbody Surface (Oberfl?che) | 03/02/2022 | 16/02/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 172 | 1201082599_172
A161060 | TT_Task | Trainset 12 BM3 - Fitout (Innenausbau) | 03/05/2022 | 20/05/2022 | nan | nan | 8 | TK_NotStart | 1201082599 | 173 | 1201082599_173
CW1820 | TT_Task | Trainset 12 BM3 - Transport from Goerlitz to Ceska Lipa | 02/02/2022 | 02/02/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 122 | 1201082599_122
CW3080 | TT_Task | Trainset 12 BM3 - Transport from Ceska Lipa to Vienna | 17/02/2022 | 17/02/2022 | nan | nan | 272 | TK_NotStart | 1201082599 | 124 | 1201082599_124
CW4340 | TT_Task | Trainset 12 BM3 - Bonding and Waxing (Kleben und Wachs) | 07/04/2022 | 28/04/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 125 | 1201082599_125
CWS1820 | TT_Task | Trainset 12 BM3 - Customer Inspection (Haltepunkt) | 01/02/2022 | 01/02/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 174 | 1201082599_174
A161100 | TT_Task | Trainset 12 BM1 - Carbody Production (Rohbau Produktion) | 25/01/2022 | 02/02/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 128 | 1201082599_128
A161110 | TT_Task | Trainset 12 BM1 - Carbody Surface (Oberfl?che) | 07/02/2022 | 18/02/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 172 | 1201082599_172
A161120 | TT_Task | Trainset 12 BM1 - Fitout (Innenausbau) | 04/05/2022 | 23/05/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 178 | 1201082599_178
CW1840 | TT_Task | Trainset 12 BM1 - Transport from Goerlitz to Ceska Lipa | 04/02/2022 | 04/02/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 129 | 1201082599_129
CW3100 | TT_Task | Trainset 12 BM1 - Transport from Ceska Lipa to Vienna | 21/02/2022 | 21/02/2022 | nan | nan | 280 | TK_NotStart | 1201082599 | 130 | 1201082599_130
CW4360 | TT_Task | Trainset 12 BM1 - Bonding and Waxing (Kleben und Wachs) | 12/04/2022 | 03/05/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 131 | 1201082599_131
CWS1840 | TT_Task | Trainset 12 BM1 - Customer Inspection (Haltepunkt) | 03/02/2022 | 03/02/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 171 | 1201082599_171
A161130 | TT_Task | Trainset 12 - Train Completion (Zugbildung ; Aufsetzen) | 24/05/2022 | 03/06/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 175 | 1201082599_175
A161140 | TT_Task | Trainset 12 - Static ; Dynamic Testing (IBN +Finishing) | 07/06/2022 | 23/06/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 163 | 1201082599_163
A161150 | TT_Task | Trainset 12 - Quality Inspection +Rework (Q-Abnahme + Nachartbeit) | 24/06/2022 | 29/06/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 145 | 1201082599_145
A161160 | TT_Task | Trainset 12 - Customer Tests (IBN am Erf?lungsort) | 08/11/2022 | 21/11/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 139 | 1201082599_139
A161170 | TT_Task | Trainset 12 - Preliminary Customer Acceptance (Kundenabnahme) | 22/11/2022 | 23/11/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 140 | 1201082599_140
A161180 | TT_Task | Trainset 12 - Trial Period (Probebetrieb) | 24/11/2022 | 04/03/2023 | nan | nan | 0 | TK_NotStart | 1201082599 | 176 | 1201082599_176
A161190 | TT_Task | Trainset 12 - ATA notification trial operation complete and defect free (Meldung Probebetrieb bestanden und Mangelfrei) | 06/03/2023 | 08/03/2023 | nan | nan | 0 | TK_NotStart | 1201082599 | 142 | 1201082599_142
A238932 | TT_Task | Trainset 12 - Customer Factory Inspection + Rework (Werksabnahme +Nacharbeit) | 30/06/2022 | 05/07/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 137 | 1201082599_137
A238942 | TT_Task | Trainset 12 - Transport to Customer (Transport zum Kunden) | 06/07/2022 | 06/07/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 177 | 1201082599_177
PAYM10320 | TT_Task | WLB Approval to Start Trial Operation (Freigabe zum Probebetrieb) 12 | 24/11/2022 | 24/11/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 147 | 1201082599_147
A161220 | TT_Task | Trainset 13 CM7 - Carbody Surface (Oberfl?che) | 05/04/2022 | 27/04/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 164 | 1201082599_164
A161230 | TT_Task | Trainset 13 CM7 - Fitout (Innenausbau) | 28/04/2022 | 09/05/2022 | nan | nan | 192 | TK_NotStart | 1201082599 | 165 | 1201082599_165
CWS1850 | TT_Task | Trainset 13 CM7 - Customer Inspection (Haltepunkt) | 05/04/2022 | 05/04/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 166 | 1201082599_166
A161250 | TT_Task | Trainset 13 CM1 - Carbody Surface (Oberfl?che) | 27/04/2022 | 18/05/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 164 | 1201082599_164
A161260 | TT_Task | Trainset 13 CM1 - Fitout (Innenausbau) | 19/05/2022 | 01/06/2022 | nan | nan | 80 | TK_NotStart | 1201082599 | 165 | 1201082599_165
CWS1860 | TT_Task | Trainset 13 CM1 - Customer Inspection (Haltepunkt) | 27/04/2022 | 27/04/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 166 | 1201082599_166
A161270 | TT_Task | Trainset 13 SM6 - Carbody Production (Rohbau Produktion) | 01/02/2022 | 09/02/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 93 | 1201082599_93
A161280 | TT_Task | Trainset 13 SM6 - Carbody Surface (Oberfl?che) | 14/02/2022 | 28/02/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 167 | 1201082599_167
A161290 | TT_Task | Trainset 13 SM6 - Fitout (Innenausbau) | 06/05/2022 | 02/06/2022 | nan | nan | 64 | TK_NotStart | 1201082599 | 168 | 1201082599_168
CW1870 | TT_Task | Trainset 13 SM6 - Transport from Goerlitz to Ceska Lipa | 11/02/2022 | 11/02/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 97 | 1201082599_97
CW3130 | TT_Task | Trainset 13 SM6 - Transport from Ceska Lipa to Vienna | 01/03/2022 | 01/03/2022 | nan | nan | 240 | TK_NotStart | 1201082599 | 101 | 1201082599_101
CW4390 | TT_Task | Trainset 13 SM6 - Bonding and Waxing (Kleben und Wachs) | 13/04/2022 | 04/05/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 102 | 1201082599_102
CWS1870 | TT_Task | Trainset 13 SM6 - Customer Inspection (Haltepunkt) | 10/02/2022 | 10/02/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 98 | 1201082599_98
A161300 | TT_Task | Trainset 13 SM2 - Carbody Production (Rohbau Produktion) | 03/02/2022 | 11/02/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 108 | 1201082599_108
A161310 | TT_Task | Trainset 13 SM2 - Carbody Surface (Oberfl?che) | 16/02/2022 | 02/03/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 169 | 1201082599_169
A161320 | TT_Task | Trainset 13 SM2 - Fitout (Innenausbau) | 18/05/2022 | 15/06/2022 | nan | nan | 16 | TK_NotStart | 1201082599 | 170 | 1201082599_170
CW1880 | TT_Task | Trainset 13 SM2 - Transport from Goerlitz to Ceska Lipa | 15/02/2022 | 15/02/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 109 | 1201082599_109
CW3140 | TT_Task | Trainset 13 SM2 - Transport from Ceska Lipa to Vienna | 03/03/2022 | 03/03/2022 | nan | nan | 304 | TK_NotStart | 1201082599 | 111 | 1201082599_111
CW4400 | TT_Task | Trainset 13 SM2 - Bonding and Waxing (Kleben und Wachs) | 27/04/2022 | 17/05/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 112 | 1201082599_112
CWS1880 | TT_Task | Trainset 13 SM2 - Customer Inspection (Haltepunkt) | 14/02/2022 | 14/02/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 110 | 1201082599_110
A161360 | TT_Task | Trainset 13 BM7 - Carbody Production (Rohbau Produktion) | 31/01/2022 | 08/02/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 113 | 1201082599_113
A161370 | TT_Task | Trainset 13 BM7 - Carbody Surface (Oberfl?che) | 11/02/2022 | 25/02/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 116 | 1201082599_116
A161380 | TT_Task | Trainset 13 BM7 - Fitout (Innenausbau) | 24/05/2022 | 15/06/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 119 | 1201082599_119
CW1900 | TT_Task | Trainset 13 BM7 - Transport from Goerlitz to Ceska Lipa | 10/02/2022 | 10/02/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 114 | 1201082599_114
CW3160 | TT_Task | Trainset 13 BM7 - Transport from Ceska Lipa to Vienna | 28/02/2022 | 28/02/2022 | nan | nan | 328 | TK_NotStart | 1201082599 | 117 | 1201082599_117
CW4420 | TT_Task | Trainset 13 BM7 - Bonding and Waxing (Kleben und Wachs) | 27/04/2022 | 17/05/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 118 | 1201082599_118
CWS1900 | TT_Task | Trainset 13 BM7 - Customer Inspection (Haltepunkt) | 09/02/2022 | 09/02/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 171 | 1201082599_171
A161330 | TT_Task | Trainset 13 BM3 - Carbody Production (Rohbau Produktion) | 02/02/2022 | 10/02/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 121 | 1201082599_121
A161340 | TT_Task | Trainset 13 BM3 - Carbody Surface (Oberfl?che) | 15/02/2022 | 01/03/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 172 | 1201082599_172
A161350 | TT_Task | Trainset 13 BM3 - Fitout (Innenausbau) | 24/05/2022 | 15/06/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 173 | 1201082599_173
CW1890 | TT_Task | Trainset 13 BM3 - Transport from Goerlitz to Ceska Lipa | 14/02/2022 | 14/02/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 122 | 1201082599_122
CW3150 | TT_Task | Trainset 13 BM3 - Transport from Ceska Lipa to Vienna | 02/03/2022 | 02/03/2022 | nan | nan | 328 | TK_NotStart | 1201082599 | 124 | 1201082599_124
CW4410 | TT_Task | Trainset 13 BM3 - Bonding and Waxing (Kleben und Wachs) | 29/04/2022 | 19/05/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 125 | 1201082599_125
CWS1890 | TT_Task | Trainset 13 BM3 - Customer Inspection (Haltepunkt) | 11/02/2022 | 11/02/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 174 | 1201082599_174
A161390 | TT_Task | Trainset 13 BM1 - Carbody Production (Rohbau Produktion) | 04/02/2022 | 14/02/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 128 | 1201082599_128
A161400 | TT_Task | Trainset 13 BM1 - Carbody Surface (Oberfl?che) | 17/02/2022 | 03/03/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 172 | 1201082599_172
A161410 | TT_Task | Trainset 13 BM1 - Fitout (Innenausbau) | 25/05/2022 | 03/06/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 178 | 1201082599_178
CW1910 | TT_Task | Trainset 13 BM1 - Transport from Goerlitz to Ceska Lipa | 16/02/2022 | 16/02/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 129 | 1201082599_129
CW3170 | TT_Task | Trainset 13 BM1 - Transport from Ceska Lipa to Vienna | 04/03/2022 | 04/03/2022 | nan | nan | 336 | TK_NotStart | 1201082599 | 130 | 1201082599_130
CW4430 | TT_Task | Trainset 13 BM1 - Bonding and Waxing (Kleben und Wachs) | 04/05/2022 | 24/05/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 131 | 1201082599_131
CWS1910 | TT_Task | Trainset 13 BM1 - Customer Inspection (Haltepunkt) | 15/02/2022 | 15/02/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 171 | 1201082599_171
A161420 | TT_Task | Trainset 13 - Train Completion (Zugbildung ; Aufsetzen) | 20/06/2022 | 30/06/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 175 | 1201082599_175
A161430 | TT_Task | Trainset 13 - Static ; Dynamic Testing (IBN +Finishing) | 01/07/2022 | 15/07/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 163 | 1201082599_163
A161440 | TT_Task | Trainset 13 - Quality Inspection +Rework (Q-Abnahme + Nachartbeit) | 18/07/2022 | 21/07/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 145 | 1201082599_145
A161450 | TT_Task | Trainset 13 - Customer Tests (IBN am Erf?lungsort) | 22/11/2022 | 05/12/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 139 | 1201082599_139
A161460 | TT_Task | Trainset 13 - Preliminary Customer Acceptance (Kundenabnahme) | 06/12/2022 | 07/12/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 140 | 1201082599_140
A161470 | TT_Task | Trainset 13 - Trial Period (Probebetrieb) | 23/12/2022 | 02/04/2023 | nan | nan | 0 | TK_NotStart | 1201082599 | 176 | 1201082599_176
A161480 | TT_Task | Trainset 13 - ATA notification trial operation complete and defect free (Meldung Probebetrieb bestanden und Mangelfrei) | 03/04/2023 | 05/04/2023 | nan | nan | 0 | TK_NotStart | 1201082599 | 142 | 1201082599_142
A238952 | TT_Task | Trainset 13 - Customer Factory Inspection + Rework (Werksabnahme +Nacharbeit) | 22/07/2022 | 10/08/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 137 | 1201082599_137
A238962 | TT_Task | Trainset 13 - Transport to Customer (Transport zum Kunden) | 11/08/2022 | 11/08/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 177 | 1201082599_177
PAYM10330 | TT_Task | WLB Approval to Start Trial Operation (Freigabe zum Probebetrieb) 13 | 09/12/2022 | 09/12/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 147 | 1201082599_147
A161510 | TT_Task | Trainset 14 CM7 - Carbody Surface (Oberfl?che) | 27/04/2022 | 18/05/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 164 | 1201082599_164
A161520 | TT_Task | Trainset 14 CM7 - Fitout (Innenausbau) | 19/05/2022 | 01/06/2022 | nan | nan | 192 | TK_NotStart | 1201082599 | 165 | 1201082599_165
CWS1920 | TT_Task | Trainset 14 CM7 - Customer Inspection (Haltepunkt) | 27/04/2022 | 27/04/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 166 | 1201082599_166
A161540 | TT_Task | Trainset 14 CM1 - Carbody Surface (Oberfl?che) | 18/05/2022 | 13/06/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 164 | 1201082599_164
A161550 | TT_Task | Trainset 14 CM1 - Fitout (Innenausbau) | 14/06/2022 | 27/06/2022 | nan | nan | 80 | TK_NotStart | 1201082599 | 165 | 1201082599_165
CWS1930 | TT_Task | Trainset 14 CM1 - Customer Inspection (Haltepunkt) | 18/05/2022 | 18/05/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 166 | 1201082599_166
A161560 | TT_Task | Trainset 14 SM6 - Carbody Production (Rohbau Produktion) | 07/03/2022 | 14/03/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 93 | 1201082599_93
A161570 | TT_Task | Trainset 14 SM6 - Carbody Surface (Oberfl?che) | 17/03/2022 | 14/04/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 167 | 1201082599_167
A161580 | TT_Task | Trainset 14 SM6 - Fitout (Innenausbau) | 31/05/2022 | 28/06/2022 | nan | nan | 64 | TK_NotStart | 1201082599 | 168 | 1201082599_168
CW1940 | TT_Task | Trainset 14 SM6 - Transport from Goerlitz to Ceska Lipa | 16/03/2022 | 16/03/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 97 | 1201082599_97
CW3200 | TT_Task | Trainset 14 SM6 - Transport from Ceska Lipa to Vienna | 15/04/2022 | 15/04/2022 | nan | nan | 104 | TK_NotStart | 1201082599 | 101 | 1201082599_101
CW4460 | TT_Task | Trainset 14 SM6 - Bonding and Waxing (Kleben und Wachs) | 05/05/2022 | 25/05/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 102 | 1201082599_102
CWS1940 | TT_Task | Trainset 14 SM6 - Customer Inspection (Haltepunkt) | 15/03/2022 | 15/03/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 98 | 1201082599_98
A161590 | TT_Task | Trainset 14 SM2 - Carbody Production (Rohbau Produktion) | 09/03/2022 | 16/03/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 108 | 1201082599_108
A161600 | TT_Task | Trainset 14 SM2 - Carbody Surface (Oberfl?che) | 21/03/2022 | 18/04/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 169 | 1201082599_169
A161610 | TT_Task | Trainset 14 SM2 - Fitout (Innenausbau) | 13/06/2022 | 08/07/2022 | nan | nan | 16 | TK_NotStart | 1201082599 | 170 | 1201082599_170
CW1950 | TT_Task | Trainset 14 SM2 - Transport from Goerlitz to Ceska Lipa | 18/03/2022 | 18/03/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 109 | 1201082599_109
CW3210 | TT_Task | Trainset 14 SM2 - Transport from Ceska Lipa to Vienna | 19/04/2022 | 19/04/2022 | nan | nan | 160 | TK_NotStart | 1201082599 | 111 | 1201082599_111
CW4470 | TT_Task | Trainset 14 SM2 - Bonding and Waxing (Kleben und Wachs) | 18/05/2022 | 10/06/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 112 | 1201082599_112
CWS1950 | TT_Task | Trainset 14 SM2 - Customer Inspection (Haltepunkt) | 17/03/2022 | 17/03/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 110 | 1201082599_110
A161650 | TT_Task | Trainset 14 BM7 - Carbody Production (Rohbau Produktion) | 04/03/2022 | 11/03/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 113 | 1201082599_113
A161660 | TT_Task | Trainset 14 BM7 - Carbody Surface (Oberfl?che) | 16/03/2022 | 13/04/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 116 | 1201082599_116
A161670 | TT_Task | Trainset 14 BM7 - Fitout (Innenausbau) | 21/06/2022 | 08/07/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 119 | 1201082599_119
CW1970 | TT_Task | Trainset 14 BM7 - Transport from Goerlitz to Ceska Lipa | 15/03/2022 | 15/03/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 114 | 1201082599_114
CW3230 | TT_Task | Trainset 14 BM7 - Transport from Ceska Lipa to Vienna | 14/04/2022 | 14/04/2022 | nan | nan | 184 | TK_NotStart | 1201082599 | 117 | 1201082599_117
CW4490 | TT_Task | Trainset 14 BM7 - Bonding and Waxing (Kleben und Wachs) | 18/05/2022 | 10/06/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 118 | 1201082599_118
CWS1970 | TT_Task | Trainset 14 BM7 - Customer Inspection (Haltepunkt) | 14/03/2022 | 14/03/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 171 | 1201082599_171
A161620 | TT_Task | Trainset 14 BM3 - Carbody Production (Rohbau Produktion) | 08/03/2022 | 15/03/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 121 | 1201082599_121
A161630 | TT_Task | Trainset 14 BM3 - Carbody Surface (Oberfl?che) | 18/03/2022 | 15/04/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 172 | 1201082599_172
A161640 | TT_Task | Trainset 14 BM3 - Fitout (Innenausbau) | 21/06/2022 | 08/07/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 173 | 1201082599_173
CW1960 | TT_Task | Trainset 14 BM3 - Transport from Goerlitz to Ceska Lipa | 17/03/2022 | 17/03/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 122 | 1201082599_122
CW3220 | TT_Task | Trainset 14 BM3 - Transport from Ceska Lipa to Vienna | 18/04/2022 | 18/04/2022 | nan | nan | 184 | TK_NotStart | 1201082599 | 124 | 1201082599_124
CW4480 | TT_Task | Trainset 14 BM3 - Bonding and Waxing (Kleben und Wachs) | 20/05/2022 | 14/06/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 125 | 1201082599_125
CWS1960 | TT_Task | Trainset 14 BM3 - Customer Inspection (Haltepunkt) | 16/03/2022 | 16/03/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 174 | 1201082599_174
A161680 | TT_Task | Trainset 14 BM1 - Carbody Production (Rohbau Produktion) | 10/03/2022 | 17/03/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 128 | 1201082599_128
A161690 | TT_Task | Trainset 14 BM1 - Carbody Surface (Oberfl?che) | 22/03/2022 | 19/04/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 172 | 1201082599_172
A161700 | TT_Task | Trainset 14 BM1 - Fitout (Innenausbau) | 22/06/2022 | 11/07/2022 | nan | nan | 8 | TK_NotStart | 1201082599 | 178 | 1201082599_178
CW1980 | TT_Task | Trainset 14 BM1 - Transport from Goerlitz to Ceska Lipa | 21/03/2022 | 21/03/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 129 | 1201082599_129
CW3240 | TT_Task | Trainset 14 BM1 - Transport from Ceska Lipa to Vienna | 20/04/2022 | 20/04/2022 | nan | nan | 192 | TK_NotStart | 1201082599 | 130 | 1201082599_130
CW4500 | TT_Task | Trainset 14 BM1 - Bonding and Waxing (Kleben und Wachs) | 25/05/2022 | 21/06/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 131 | 1201082599_131
CWS1980 | TT_Task | Trainset 14 BM1 - Customer Inspection (Haltepunkt) | 18/03/2022 | 18/03/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 171 | 1201082599_171
A161710 | TT_Task | Trainset 14 - Train Completion (Zugbildung ; Aufsetzen) | 11/07/2022 | 21/07/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 175 | 1201082599_175
A161720 | TT_Task | Trainset 14 - Static ; Dynamic Testing (IBN +Finishing) | 22/07/2022 | 08/08/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 163 | 1201082599_163
A161730 | TT_Task | Trainset 14 - Quality Inspection +Rework (Q-Abnahme + Nachartbeit) | 09/08/2022 | 12/08/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 145 | 1201082599_145
A161740 | TT_Task | Trainset 14 - Customer Tests (IBN am Erf?lungsort) | 06/12/2022 | 20/12/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 139 | 1201082599_139
A161750 | TT_Task | Trainset 14 - Preliminary Customer Acceptance (Kundenabnahme) | 21/12/2022 | 22/12/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 140 | 1201082599_140
A161760 | TT_Task | Trainset 14 - Trial Period (Probebetrieb) | 23/12/2022 | 02/04/2023 | nan | nan | 0 | TK_NotStart | 1201082599 | 176 | 1201082599_176
A161770 | TT_Task | Trainset 14 - ATA notification trial operation complete and defect free (Meldung Probebetrieb bestanden und Mangelfrei) | 03/04/2023 | 05/04/2023 | nan | nan | 0 | TK_NotStart | 1201082599 | 142 | 1201082599_142
A238972 | TT_Task | Trainset 14 - Customer Factory Inspection + Rework (Werksabnahme +Nacharbeit) | 16/08/2022 | 19/08/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 137 | 1201082599_137
A238982 | TT_Task | Trainset 14 - Transport to Customer (Transport zum Kunden) | 22/08/2022 | 22/08/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 177 | 1201082599_177
PAYM10340 | TT_Task | WLB Approval to Start Trial Operation (Freigabe zum Probebetrieb) 14 | 23/12/2022 | 23/12/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 147 | 1201082599_147
A161800 | TT_Task | Trainset 15 CM7 - Carbody Surface (Oberfl?che) | 18/05/2022 | 13/06/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 164 | 1201082599_164
A161810 | TT_Task | Trainset 15 CM7 - Fitout (Innenausbau) | 14/06/2022 | 27/06/2022 | nan | nan | 192 | TK_NotStart | 1201082599 | 165 | 1201082599_165
CWS1990 | TT_Task | Trainset 15 CM7 - Customer Inspection (Haltepunkt) | 18/05/2022 | 18/05/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 166 | 1201082599_166
A161830 | TT_Task | Trainset 15 CM1 - Carbody Surface (Oberfl?che) | 13/06/2022 | 06/07/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 164 | 1201082599_164
A161840 | TT_Task | Trainset 15 CM1 - Fitout (Innenausbau) | 07/07/2022 | 18/07/2022 | nan | nan | 80 | TK_NotStart | 1201082599 | 165 | 1201082599_165
CWS2000 | TT_Task | Trainset 15 CM1 - Customer Inspection (Haltepunkt) | 13/06/2022 | 13/06/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 166 | 1201082599_166
A161850 | TT_Task | Trainset 15 SM6 - Carbody Production (Rohbau Produktion) | 17/03/2022 | 24/03/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 93 | 1201082599_93
A161860 | TT_Task | Trainset 15 SM6 - Carbody Surface (Oberfl?che) | 29/03/2022 | 26/04/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 167 | 1201082599_167
A161870 | TT_Task | Trainset 15 SM6 - Fitout (Innenausbau) | 24/06/2022 | 19/07/2022 | nan | nan | 64 | TK_NotStart | 1201082599 | 168 | 1201082599_168
CW2010 | TT_Task | Trainset 15 SM6 - Transport from Goerlitz to Ceska Lipa | 28/03/2022 | 28/03/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 97 | 1201082599_97
CW3270 | TT_Task | Trainset 15 SM6 - Transport from Ceska Lipa to Vienna | 27/04/2022 | 27/04/2022 | nan | nan | 176 | TK_NotStart | 1201082599 | 101 | 1201082599_101
CW4530 | TT_Task | Trainset 15 SM6 - Bonding and Waxing (Kleben und Wachs) | 30/05/2022 | 22/06/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 102 | 1201082599_102
CWS2010 | TT_Task | Trainset 15 SM6 - Customer Inspection (Haltepunkt) | 25/03/2022 | 25/03/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 98 | 1201082599_98
A161880 | TT_Task | Trainset 15 SM2 - Carbody Production (Rohbau Produktion) | 21/03/2022 | 28/03/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 108 | 1201082599_108
A161890 | TT_Task | Trainset 15 SM2 - Carbody Surface (Oberfl?che) | 31/03/2022 | 28/04/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 169 | 1201082599_169
A161900 | TT_Task | Trainset 15 SM2 - Fitout (Innenausbau) | 06/07/2022 | 12/08/2022 | nan | nan | 16 | TK_NotStart | 1201082599 | 170 | 1201082599_170
CW2020 | TT_Task | Trainset 15 SM2 - Transport from Goerlitz to Ceska Lipa | 30/03/2022 | 30/03/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 109 | 1201082599_109
CW3280 | TT_Task | Trainset 15 SM2 - Transport from Ceska Lipa to Vienna | 29/04/2022 | 29/04/2022 | nan | nan | 240 | TK_NotStart | 1201082599 | 111 | 1201082599_111
CW4540 | TT_Task | Trainset 15 SM2 - Bonding and Waxing (Kleben und Wachs) | 13/06/2022 | 05/07/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 112 | 1201082599_112
CWS2020 | TT_Task | Trainset 15 SM2 - Customer Inspection (Haltepunkt) | 29/03/2022 | 29/03/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 110 | 1201082599_110
A161940 | TT_Task | Trainset 15 BM7 - Carbody Production (Rohbau Produktion) | 16/03/2022 | 23/03/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 113 | 1201082599_113
A161950 | TT_Task | Trainset 15 BM7 - Carbody Surface (Oberfl?che) | 28/03/2022 | 25/04/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 116 | 1201082599_116
A161960 | TT_Task | Trainset 15 BM7 - Fitout (Innenausbau) | 12/07/2022 | 12/08/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 119 | 1201082599_119
CW2040 | TT_Task | Trainset 15 BM7 - Transport from Goerlitz to Ceska Lipa | 25/03/2022 | 25/03/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 114 | 1201082599_114
CW3300 | TT_Task | Trainset 15 BM7 - Transport from Ceska Lipa to Vienna | 26/04/2022 | 26/04/2022 | nan | nan | 264 | TK_NotStart | 1201082599 | 117 | 1201082599_117
CW4560 | TT_Task | Trainset 15 BM7 - Bonding and Waxing (Kleben und Wachs) | 13/06/2022 | 05/07/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 118 | 1201082599_118
CWS2040 | TT_Task | Trainset 15 BM7 - Customer Inspection (Haltepunkt) | 24/03/2022 | 24/03/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 171 | 1201082599_171
A161910 | TT_Task | Trainset 15 BM3 - Carbody Production (Rohbau Produktion) | 18/03/2022 | 25/03/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 121 | 1201082599_121
A161920 | TT_Task | Trainset 15 BM3 - Carbody Surface (Oberfl?che) | 30/03/2022 | 27/04/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 172 | 1201082599_172
A161930 | TT_Task | Trainset 15 BM3 - Fitout (Innenausbau) | 12/07/2022 | 12/08/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 173 | 1201082599_173
CW2030 | TT_Task | Trainset 15 BM3 - Transport from Goerlitz to Ceska Lipa | 29/03/2022 | 29/03/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 122 | 1201082599_122
CW3290 | TT_Task | Trainset 15 BM3 - Transport from Ceska Lipa to Vienna | 28/04/2022 | 28/04/2022 | nan | nan | 264 | TK_NotStart | 1201082599 | 124 | 1201082599_124
CW4550 | TT_Task | Trainset 15 BM3 - Bonding and Waxing (Kleben und Wachs) | 15/06/2022 | 07/07/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 125 | 1201082599_125
CWS2030 | TT_Task | Trainset 15 BM3 - Customer Inspection (Haltepunkt) | 28/03/2022 | 28/03/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 174 | 1201082599_174
A161970 | TT_Task | Trainset 15 BM1 - Carbody Production (Rohbau Produktion) | 22/03/2022 | 29/03/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 128 | 1201082599_128
A161980 | TT_Task | Trainset 15 BM1 - Carbody Surface (Oberfl?che) | 01/04/2022 | 29/04/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 172 | 1201082599_172
A161990 | TT_Task | Trainset 15 BM1 - Fitout (Innenausbau) | 13/07/2022 | 16/08/2022 | nan | nan | 8 | TK_NotStart | 1201082599 | 178 | 1201082599_178
CW2050 | TT_Task | Trainset 15 BM1 - Transport from Goerlitz to Ceska Lipa | 31/03/2022 | 31/03/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 129 | 1201082599_129
CW3310 | TT_Task | Trainset 15 BM1 - Transport from Ceska Lipa to Vienna | 02/05/2022 | 02/05/2022 | nan | nan | 288 | TK_NotStart | 1201082599 | 130 | 1201082599_130
CW4570 | TT_Task | Trainset 15 BM1 - Bonding and Waxing (Kleben und Wachs) | 22/06/2022 | 12/07/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 131 | 1201082599_131
CWS2050 | TT_Task | Trainset 15 BM1 - Customer Inspection (Haltepunkt) | 30/03/2022 | 30/03/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 171 | 1201082599_171
A162000 | TT_Task | Trainset 15 - Train Completion (Zugbildung ; Aufsetzen) | 16/08/2022 | 26/08/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 175 | 1201082599_175
A162010 | TT_Task | Trainset 15 - Static ; Dynamic Testing (IBN +Finishing) | 29/08/2022 | 12/09/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 163 | 1201082599_163
A162020 | TT_Task | Trainset 15 - Quality Inspection +Rework (Q-Abnahme + Nachartbeit) | 13/09/2022 | 16/09/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 145 | 1201082599_145
A162030 | TT_Task | Trainset 15 - Customer Tests (IBN am Erf?lungsort) | 21/12/2022 | 06/01/2023 | nan | nan | 0 | TK_NotStart | 1201082599 | 139 | 1201082599_139
A162040 | TT_Task | Trainset 15 - Preliminary Customer Acceptance (Kundenabnahme) | 09/01/2023 | 10/01/2023 | nan | nan | 0 | TK_NotStart | 1201082599 | 140 | 1201082599_140
A162050 | TT_Task | Trainset 15 - Trial Period (Probebetrieb) | 25/01/2023 | 05/05/2023 | nan | nan | 0 | TK_NotStart | 1201082599 | 176 | 1201082599_176
A162060 | TT_Task | Trainset 15 - ATA notification trial operation complete and defect free (Meldung Probebetrieb bestanden und Mangelfrei) | 08/05/2023 | 10/05/2023 | nan | nan | 0 | TK_NotStart | 1201082599 | 142 | 1201082599_142
A238992 | TT_Task | Trainset 15 - Customer Factory Inspection + Rework (Werksabnahme +Nacharbeit) | 19/09/2022 | 22/09/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 137 | 1201082599_137
A239002 | TT_Task | Trainset 15 - Transport to Customer (Transport zum Kunden) | 23/09/2022 | 23/09/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 177 | 1201082599_177
PAYM10350 | TT_Task | WLB Approval to Start Trial Operation (Freigabe zum Probebetrieb) 15 | 11/01/2023 | 11/01/2023 | nan | nan | 0 | TK_NotStart | 1201082599 | 147 | 1201082599_147
A162090 | TT_Task | Trainset 16 CM7 - Carbody Surface (Oberfl?che) | 13/06/2022 | 06/07/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 164 | 1201082599_164
A162100 | TT_Task | Trainset 16 CM7 - Fitout (Innenausbau) | 07/07/2022 | 18/07/2022 | nan | nan | 192 | TK_NotStart | 1201082599 | 165 | 1201082599_165
CWS2060 | TT_Task | Trainset 16 CM7 - Customer Inspection (Haltepunkt) | 13/06/2022 | 13/06/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 166 | 1201082599_166
A162120 | TT_Task | Trainset 16 CM1 - Carbody Surface (Oberfl?che) | 06/07/2022 | 10/08/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 164 | 1201082599_164
A162130 | TT_Task | Trainset 16 CM1 - Fitout (Innenausbau) | 11/08/2022 | 23/08/2022 | nan | nan | 80 | TK_NotStart | 1201082599 | 165 | 1201082599_165
CWS2070 | TT_Task | Trainset 16 CM1 - Customer Inspection (Haltepunkt) | 06/07/2022 | 06/07/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 166 | 1201082599_166
A162140 | TT_Task | Trainset 16 SM6 - Carbody Production (Rohbau Produktion) | 22/04/2022 | 29/04/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 93 | 1201082599_93
A162150 | TT_Task | Trainset 16 SM6 - Carbody Surface (Oberfl?che) | 04/05/2022 | 01/06/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 167 | 1201082599_167
A162160 | TT_Task | Trainset 16 SM6 - Fitout (Innenausbau) | 15/07/2022 | 24/08/2022 | nan | nan | 64 | TK_NotStart | 1201082599 | 168 | 1201082599_168
CW2080 | TT_Task | Trainset 16 SM6 - Transport from Goerlitz to Ceska Lipa | 03/05/2022 | 03/05/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 97 | 1201082599_97
CW3340 | TT_Task | Trainset 16 SM6 - Transport from Ceska Lipa to Vienna | 02/06/2022 | 02/06/2022 | nan | nan | 112 | TK_NotStart | 1201082599 | 101 | 1201082599_101
CW4600 | TT_Task | Trainset 16 SM6 - Bonding and Waxing (Kleben und Wachs) | 23/06/2022 | 13/07/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 102 | 1201082599_102
CWS2080 | TT_Task | Trainset 16 SM6 - Customer Inspection (Haltepunkt) | 02/05/2022 | 02/05/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 98 | 1201082599_98
A162170 | TT_Task | Trainset 16 SM2 - Carbody Production (Rohbau Produktion) | 26/04/2022 | 03/05/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 108 | 1201082599_108
A162180 | TT_Task | Trainset 16 SM2 - Carbody Surface (Oberfl?che) | 06/05/2022 | 03/06/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 169 | 1201082599_169
A162190 | TT_Task | Trainset 16 SM2 - Fitout (Innenausbau) | 10/08/2022 | 05/09/2022 | nan | nan | 16 | TK_NotStart | 1201082599 | 170 | 1201082599_170
CW2090 | TT_Task | Trainset 16 SM2 - Transport from Goerlitz to Ceska Lipa | 05/05/2022 | 05/05/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 109 | 1201082599_109
CW3350 | TT_Task | Trainset 16 SM2 - Transport from Ceska Lipa to Vienna | 06/06/2022 | 06/06/2022 | nan | nan | 168 | TK_NotStart | 1201082599 | 111 | 1201082599_111
CW4610 | TT_Task | Trainset 16 SM2 - Bonding and Waxing (Kleben und Wachs) | 06/07/2022 | 09/08/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 112 | 1201082599_112
CWS2090 | TT_Task | Trainset 16 SM2 - Customer Inspection (Haltepunkt) | 04/05/2022 | 04/05/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 110 | 1201082599_110
A162230 | TT_Task | Trainset 16 BM7 - Carbody Production (Rohbau Produktion) | 21/04/2022 | 28/04/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 113 | 1201082599_113
A162240 | TT_Task | Trainset 16 BM7 - Carbody Surface (Oberfl?che) | 03/05/2022 | 31/05/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 116 | 1201082599_116
A162250 | TT_Task | Trainset 16 BM7 - Fitout (Innenausbau) | 17/08/2022 | 05/09/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 119 | 1201082599_119
CW2110 | TT_Task | Trainset 16 BM7 - Transport from Goerlitz to Ceska Lipa | 02/05/2022 | 02/05/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 114 | 1201082599_114
CW3370 | TT_Task | Trainset 16 BM7 - Transport from Ceska Lipa to Vienna | 01/06/2022 | 01/06/2022 | nan | nan | 192 | TK_NotStart | 1201082599 | 117 | 1201082599_117
CW4630 | TT_Task | Trainset 16 BM7 - Bonding and Waxing (Kleben und Wachs) | 06/07/2022 | 09/08/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 118 | 1201082599_118
CWS2110 | TT_Task | Trainset 16 BM7 - Customer Inspection (Haltepunkt) | 29/04/2022 | 29/04/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 171 | 1201082599_171
A162200 | TT_Task | Trainset 16 BM3 - Carbody Production (Rohbau Produktion) | 25/04/2022 | 02/05/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 121 | 1201082599_121
A162210 | TT_Task | Trainset 16 BM3 - Carbody Surface (Oberfl?che) | 05/05/2022 | 02/06/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 172 | 1201082599_172
A162220 | TT_Task | Trainset 16 BM3 - Fitout (Innenausbau) | 17/08/2022 | 05/09/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 173 | 1201082599_173
CW2100 | TT_Task | Trainset 16 BM3 - Transport from Goerlitz to Ceska Lipa | 04/05/2022 | 04/05/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 122 | 1201082599_122
CW3360 | TT_Task | Trainset 16 BM3 - Transport from Ceska Lipa to Vienna | 03/06/2022 | 03/06/2022 | nan | nan | 192 | TK_NotStart | 1201082599 | 124 | 1201082599_124
CW4620 | TT_Task | Trainset 16 BM3 - Bonding and Waxing (Kleben und Wachs) | 08/07/2022 | 11/08/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 125 | 1201082599_125
CWS2100 | TT_Task | Trainset 16 BM3 - Customer Inspection (Haltepunkt) | 03/05/2022 | 03/05/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 174 | 1201082599_174
A162260 | TT_Task | Trainset 16 BM1 - Carbody Production (Rohbau Produktion) | 27/04/2022 | 04/05/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 128 | 1201082599_128
A162270 | TT_Task | Trainset 16 BM1 - Carbody Surface (Oberfl?che) | 09/05/2022 | 06/06/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 172 | 1201082599_172
A162280 | TT_Task | Trainset 16 BM1 - Fitout (Innenausbau) | 18/08/2022 | 06/09/2022 | nan | nan | 8 | TK_NotStart | 1201082599 | 178 | 1201082599_178
CW2120 | TT_Task | Trainset 16 BM1 - Transport from Goerlitz to Ceska Lipa | 06/05/2022 | 06/05/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 129 | 1201082599_129
CW3380 | TT_Task | Trainset 16 BM1 - Transport from Ceska Lipa to Vienna | 07/06/2022 | 07/06/2022 | nan | nan | 200 | TK_NotStart | 1201082599 | 130 | 1201082599_130
CW4640 | TT_Task | Trainset 16 BM1 - Bonding and Waxing (Kleben und Wachs) | 13/07/2022 | 17/08/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 131 | 1201082599_131
CWS2120 | TT_Task | Trainset 16 BM1 - Customer Inspection (Haltepunkt) | 05/05/2022 | 05/05/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 171 | 1201082599_171
A162290 | TT_Task | Trainset 16 - Train Completion (Zugbildung ; Aufsetzen) | 06/09/2022 | 16/09/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 175 | 1201082599_175
A162300 | TT_Task | Trainset 16 - Static ; Dynamic Testing (IBN +Finishing) | 19/09/2022 | 04/10/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 163 | 1201082599_163
A162310 | TT_Task | Trainset 16 - Quality Inspection +Rework (Q-Abnahme + Nachartbeit) | 05/10/2022 | 10/10/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 145 | 1201082599_145
A162320 | TT_Task | Trainset 16 - Customer Tests (IBN am Erf?lungsort) | 09/01/2023 | 20/01/2023 | nan | nan | 0 | TK_NotStart | 1201082599 | 139 | 1201082599_139
A162330 | TT_Task | Trainset 16 - Preliminary Customer Acceptance (Kundenabnahme) | 23/01/2023 | 24/01/2023 | nan | nan | 0 | TK_NotStart | 1201082599 | 140 | 1201082599_140
A162340 | TT_Task | Trainset 16 - Trial Period (Probebetrieb) | 25/01/2023 | 05/05/2023 | nan | nan | 0 | TK_NotStart | 1201082599 | 176 | 1201082599_176
A162350 | TT_Task | Trainset 16 - ATA notification trial operation complete and defect free (Meldung Probebetrieb bestanden und Mangelfrei) | 08/05/2023 | 10/05/2023 | nan | nan | 0 | TK_NotStart | 1201082599 | 142 | 1201082599_142
A239012 | TT_Task | Trainset 16 - Customer Factory Inspection + Rework (Werksabnahme +Nacharbeit) | 11/10/2022 | 14/10/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 137 | 1201082599_137
A239022 | TT_Task | Trainset 16 - Transport to Customer (Transport zum Kunden) | 17/10/2022 | 17/10/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 177 | 1201082599_177
PAYM10360 | TT_Task | WLB Approval to Start Trial Operation (Freigabe zum Probebetrieb) 16 | 25/01/2023 | 25/01/2023 | nan | nan | 0 | TK_NotStart | 1201082599 | 147 | 1201082599_147
A162380 | TT_Task | Trainset 17 CM7 - Carbody Surface (Oberfl?che) | 06/07/2022 | 10/08/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 164 | 1201082599_164
A162390 | TT_Task | Trainset 17 CM7 - Fitout (Innenausbau) | 11/08/2022 | 23/08/2022 | nan | nan | 192 | TK_NotStart | 1201082599 | 165 | 1201082599_165
CWS2130 | TT_Task | Trainset 17 CM7 - Customer Inspection (Haltepunkt) | 06/07/2022 | 06/07/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 166 | 1201082599_166
A162410 | TT_Task | Trainset 17 CM1 - Carbody Surface (Oberfl?che) | 10/08/2022 | 01/09/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 164 | 1201082599_164
A162420 | TT_Task | Trainset 17 CM1 - Fitout (Innenausbau) | 02/09/2022 | 13/09/2022 | nan | nan | 80 | TK_NotStart | 1201082599 | 165 | 1201082599_165
CWS2140 | TT_Task | Trainset 17 CM1 - Customer Inspection (Haltepunkt) | 10/08/2022 | 10/08/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 166 | 1201082599_166
A162430 | TT_Task | Trainset 17 SM6 - Carbody Production (Rohbau Produktion) | 04/05/2022 | 11/05/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 93 | 1201082599_93
A162440 | TT_Task | Trainset 17 SM6 - Carbody Surface (Oberfl?che) | 16/05/2022 | 13/06/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 167 | 1201082599_167
A162450 | TT_Task | Trainset 17 SM6 - Fitout (Innenausbau) | 22/08/2022 | 14/09/2022 | nan | nan | 64 | TK_NotStart | 1201082599 | 168 | 1201082599_168
CW2150 | TT_Task | Trainset 17 SM6 - Transport from Goerlitz to Ceska Lipa | 13/05/2022 | 13/05/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 97 | 1201082599_97
CW3410 | TT_Task | Trainset 17 SM6 - Transport from Ceska Lipa to Vienna | 14/06/2022 | 14/06/2022 | nan | nan | 168 | TK_NotStart | 1201082599 | 101 | 1201082599_101
CW4670 | TT_Task | Trainset 17 SM6 - Bonding and Waxing (Kleben und Wachs) | 14/07/2022 | 18/08/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 102 | 1201082599_102
CWS2150 | TT_Task | Trainset 17 SM6 - Customer Inspection (Haltepunkt) | 12/05/2022 | 12/05/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 98 | 1201082599_98
A162460 | TT_Task | Trainset 17 SM2 - Carbody Production (Rohbau Produktion) | 06/05/2022 | 13/05/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 108 | 1201082599_108
A162470 | TT_Task | Trainset 17 SM2 - Carbody Surface (Oberfl?che) | 18/05/2022 | 15/06/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 169 | 1201082599_169
A162480 | TT_Task | Trainset 17 SM2 - Fitout (Innenausbau) | 01/09/2022 | 26/09/2022 | nan | nan | 16 | TK_NotStart | 1201082599 | 170 | 1201082599_170
CW2160 | TT_Task | Trainset 17 SM2 - Transport from Goerlitz to Ceska Lipa | 17/05/2022 | 17/05/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 109 | 1201082599_109
CW3420 | TT_Task | Trainset 17 SM2 - Transport from Ceska Lipa to Vienna | 16/06/2022 | 16/06/2022 | nan | nan | 304 | TK_NotStart | 1201082599 | 111 | 1201082599_111
CW4680 | TT_Task | Trainset 17 SM2 - Bonding and Waxing (Kleben und Wachs) | 10/08/2022 | 31/08/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 112 | 1201082599_112
CWS2160 | TT_Task | Trainset 17 SM2 - Customer Inspection (Haltepunkt) | 16/05/2022 | 16/05/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 110 | 1201082599_110
A162520 | TT_Task | Trainset 17 BM7 - Carbody Production (Rohbau Produktion) | 03/05/2022 | 10/05/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 113 | 1201082599_113
A162530 | TT_Task | Trainset 17 BM7 - Carbody Surface (Oberfl?che) | 13/05/2022 | 10/06/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 116 | 1201082599_116
A162540 | TT_Task | Trainset 17 BM7 - Fitout (Innenausbau) | 07/09/2022 | 26/09/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 119 | 1201082599_119
CW2180 | TT_Task | Trainset 17 BM7 - Transport from Goerlitz to Ceska Lipa | 12/05/2022 | 12/05/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 114 | 1201082599_114
CW3440 | TT_Task | Trainset 17 BM7 - Transport from Ceska Lipa to Vienna | 13/06/2022 | 13/06/2022 | nan | nan | 328 | TK_NotStart | 1201082599 | 117 | 1201082599_117
CW4700 | TT_Task | Trainset 17 BM7 - Bonding and Waxing (Kleben und Wachs) | 10/08/2022 | 31/08/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 118 | 1201082599_118
CWS2180 | TT_Task | Trainset 17 BM7 - Customer Inspection (Haltepunkt) | 11/05/2022 | 11/05/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 171 | 1201082599_171
A162490 | TT_Task | Trainset 17 BM3 - Carbody Production (Rohbau Produktion) | 05/05/2022 | 12/05/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 121 | 1201082599_121
A162500 | TT_Task | Trainset 17 BM3 - Carbody Surface (Oberfl?che) | 17/05/2022 | 14/06/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 172 | 1201082599_172
A162510 | TT_Task | Trainset 17 BM3 - Fitout (Innenausbau) | 07/09/2022 | 26/09/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 173 | 1201082599_173
CW2170 | TT_Task | Trainset 17 BM3 - Transport from Goerlitz to Ceska Lipa | 16/05/2022 | 16/05/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 122 | 1201082599_122
CW3430 | TT_Task | Trainset 17 BM3 - Transport from Ceska Lipa to Vienna | 15/06/2022 | 15/06/2022 | nan | nan | 328 | TK_NotStart | 1201082599 | 124 | 1201082599_124
CW4690 | TT_Task | Trainset 17 BM3 - Bonding and Waxing (Kleben und Wachs) | 12/08/2022 | 02/09/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 125 | 1201082599_125
CWS2170 | TT_Task | Trainset 17 BM3 - Customer Inspection (Haltepunkt) | 13/05/2022 | 13/05/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 174 | 1201082599_174
A162550 | TT_Task | Trainset 17 BM1 - Carbody Production (Rohbau Produktion) | 09/05/2022 | 16/05/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 128 | 1201082599_128
A162560 | TT_Task | Trainset 17 BM1 - Carbody Surface (Oberfl?che) | 19/05/2022 | 16/06/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 172 | 1201082599_172
A162570 | TT_Task | Trainset 17 BM1 - Fitout (Innenausbau) | 08/09/2022 | 27/09/2022 | nan | nan | 8 | TK_NotStart | 1201082599 | 178 | 1201082599_178
CW2190 | TT_Task | Trainset 17 BM1 - Transport from Goerlitz to Ceska Lipa | 18/05/2022 | 18/05/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 129 | 1201082599_129
CW3450 | TT_Task | Trainset 17 BM1 - Transport from Ceska Lipa to Vienna | 17/06/2022 | 17/06/2022 | nan | nan | 344 | TK_NotStart | 1201082599 | 130 | 1201082599_130
CW4710 | TT_Task | Trainset 17 BM1 - Bonding and Waxing (Kleben und Wachs) | 18/08/2022 | 07/09/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 131 | 1201082599_131
CWS2190 | TT_Task | Trainset 17 BM1 - Customer Inspection (Haltepunkt) | 17/05/2022 | 17/05/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 171 | 1201082599_171
A162580 | TT_Task | Trainset 17 - Train Completion (Zugbildung ; Aufsetzen) | 27/09/2022 | 07/10/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 175 | 1201082599_175
A162590 | TT_Task | Trainset 17 - Static ; Dynamic Testing (IBN +Finishing) | 10/10/2022 | 24/10/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 163 | 1201082599_163
A162600 | TT_Task | Trainset 17 - Quality Inspection +Rework (Q-Abnahme + Nachartbeit) | 25/10/2022 | 02/11/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 145 | 1201082599_145
A162610 | TT_Task | Trainset 17 - Customer Tests (IBN am Erf?lungsort) | 23/01/2023 | 03/02/2023 | nan | nan | 0 | TK_NotStart | 1201082599 | 139 | 1201082599_139
A162620 | TT_Task | Trainset 17 - Preliminary Customer Acceptance (Kundenabnahme) | 06/02/2023 | 07/02/2023 | nan | nan | 0 | TK_NotStart | 1201082599 | 140 | 1201082599_140
A162630 | TT_Task | Trainset 17 - Trial Period (Probebetrieb) | 22/02/2023 | 02/06/2023 | nan | nan | 0 | TK_NotStart | 1201082599 | 176 | 1201082599_176
A162640 | TT_Task | Trainset 17 - ATA notification trial operation complete and defect free (Meldung Probebetrieb bestanden und Mangelfrei) | 05/06/2023 | 07/06/2023 | nan | nan | 0 | TK_NotStart | 1201082599 | 142 | 1201082599_142
A239032 | TT_Task | Trainset 17 - Customer Factory Inspection + Rework (Werksabnahme +Nacharbeit) | 03/11/2022 | 08/11/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 137 | 1201082599_137
A239042 | TT_Task | Trainset 17 - Transport to Customer (Transport zum Kunden) | 09/11/2022 | 09/11/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 177 | 1201082599_177
PAYM10370 | TT_Task | WLB Approval to Start Trial Operation (Freigabe zum Probebetrieb) 17 | 08/02/2023 | 08/02/2023 | nan | nan | 0 | TK_NotStart | 1201082599 | 147 | 1201082599_147
A162670 | TT_Task | Trainset 18 CM7 - Carbody Surface (Oberfl?che) | 10/08/2022 | 01/09/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 164 | 1201082599_164
A162680 | TT_Task | Trainset 18 CM7 - Fitout (Innenausbau) | 02/09/2022 | 13/09/2022 | nan | nan | 192 | TK_NotStart | 1201082599 | 165 | 1201082599_165
CWS2200 | TT_Task | Trainset 18 CM7 - Customer Inspection (Haltepunkt) | 10/08/2022 | 10/08/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 166 | 1201082599_166
A162700 | TT_Task | Trainset 18 CM1 - Carbody Surface (Oberfl?che) | 01/09/2022 | 22/09/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 164 | 1201082599_164
A162710 | TT_Task | Trainset 18 CM1 - Fitout (Innenausbau) | 23/09/2022 | 04/10/2022 | nan | nan | 80 | TK_NotStart | 1201082599 | 165 | 1201082599_165
CWS2210 | TT_Task | Trainset 18 CM1 - Customer Inspection (Haltepunkt) | 01/09/2022 | 01/09/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 166 | 1201082599_166
A162720 | TT_Task | Trainset 18 SM6 - Carbody Production (Rohbau Produktion) | 10/06/2022 | 17/06/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 93 | 1201082599_93
A162730 | TT_Task | Trainset 18 SM6 - Carbody Surface (Oberfl?che) | 22/06/2022 | 20/07/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 167 | 1201082599_167
A162740 | TT_Task | Trainset 18 SM6 - Fitout (Innenausbau) | 12/09/2022 | 05/10/2022 | nan | nan | 64 | TK_NotStart | 1201082599 | 168 | 1201082599_168
CW2220 | TT_Task | Trainset 18 SM6 - Transport from Goerlitz to Ceska Lipa | 21/06/2022 | 21/06/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 97 | 1201082599_97
CW3480 | TT_Task | Trainset 18 SM6 - Transport from Ceska Lipa to Vienna | 21/07/2022 | 21/07/2022 | nan | nan | 160 | TK_NotStart | 1201082599 | 101 | 1201082599_101
CW4740 | TT_Task | Trainset 18 SM6 - Bonding and Waxing (Kleben und Wachs) | 19/08/2022 | 08/09/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 102 | 1201082599_102
CWS2220 | TT_Task | Trainset 18 SM6 - Customer Inspection (Haltepunkt) | 20/06/2022 | 20/06/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 98 | 1201082599_98
A162750 | TT_Task | Trainset 18 SM2 - Carbody Production (Rohbau Produktion) | 14/06/2022 | 21/06/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 108 | 1201082599_108
A162760 | TT_Task | Trainset 18 SM2 - Carbody Surface (Oberfl?che) | 24/06/2022 | 22/07/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 169 | 1201082599_169
A162770 | TT_Task | Trainset 18 SM2 - Fitout (Innenausbau) | 22/09/2022 | 17/10/2022 | nan | nan | 16 | TK_NotStart | 1201082599 | 170 | 1201082599_170
CW2230 | TT_Task | Trainset 18 SM2 - Transport from Goerlitz to Ceska Lipa | 23/06/2022 | 23/06/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 109 | 1201082599_109
CW3490 | TT_Task | Trainset 18 SM2 - Transport from Ceska Lipa to Vienna | 25/07/2022 | 25/07/2022 | nan | nan | 216 | TK_NotStart | 1201082599 | 111 | 1201082599_111
CW4750 | TT_Task | Trainset 18 SM2 - Bonding and Waxing (Kleben und Wachs) | 01/09/2022 | 21/09/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 112 | 1201082599_112
CWS2230 | TT_Task | Trainset 18 SM2 - Customer Inspection (Haltepunkt) | 22/06/2022 | 22/06/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 110 | 1201082599_110
A162810 | TT_Task | Trainset 18 BM7 - Carbody Production (Rohbau Produktion) | 09/06/2022 | 16/06/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 113 | 1201082599_113
A162820 | TT_Task | Trainset 18 BM7 - Carbody Surface (Oberfl?che) | 21/06/2022 | 19/07/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 116 | 1201082599_116
A162830 | TT_Task | Trainset 18 BM7 - Fitout (Innenausbau) | 28/09/2022 | 17/10/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 119 | 1201082599_119
CW2250 | TT_Task | Trainset 18 BM7 - Transport from Goerlitz to Ceska Lipa | 20/06/2022 | 20/06/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 114 | 1201082599_114
CW3510 | TT_Task | Trainset 18 BM7 - Transport from Ceska Lipa to Vienna | 20/07/2022 | 20/07/2022 | nan | nan | 240 | TK_NotStart | 1201082599 | 117 | 1201082599_117
CW4770 | TT_Task | Trainset 18 BM7 - Bonding and Waxing (Kleben und Wachs) | 01/09/2022 | 21/09/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 118 | 1201082599_118
CWS2250 | TT_Task | Trainset 18 BM7 - Customer Inspection (Haltepunkt) | 17/06/2022 | 17/06/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 171 | 1201082599_171
A162780 | TT_Task | Trainset 18 BM3 - Carbody Production (Rohbau Produktion) | 13/06/2022 | 20/06/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 121 | 1201082599_121
A162790 | TT_Task | Trainset 18 BM3 - Carbody Surface (Oberfl?che) | 23/06/2022 | 21/07/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 172 | 1201082599_172
A162800 | TT_Task | Trainset 18 BM3 - Fitout (Innenausbau) | 28/09/2022 | 17/10/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 173 | 1201082599_173
CW2240 | TT_Task | Trainset 18 BM3 - Transport from Goerlitz to Ceska Lipa | 22/06/2022 | 22/06/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 122 | 1201082599_122
CW3500 | TT_Task | Trainset 18 BM3 - Transport from Ceska Lipa to Vienna | 22/07/2022 | 22/07/2022 | nan | nan | 240 | TK_NotStart | 1201082599 | 124 | 1201082599_124
CW4760 | TT_Task | Trainset 18 BM3 - Bonding and Waxing (Kleben und Wachs) | 05/09/2022 | 23/09/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 125 | 1201082599_125
CWS2240 | TT_Task | Trainset 18 BM3 - Customer Inspection (Haltepunkt) | 21/06/2022 | 21/06/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 174 | 1201082599_174
A162840 | TT_Task | Trainset 18 BM1 - Carbody Production (Rohbau Produktion) | 15/06/2022 | 22/06/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 128 | 1201082599_128
A162850 | TT_Task | Trainset 18 BM1 - Carbody Surface (Oberfl?che) | 27/06/2022 | 25/07/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 172 | 1201082599_172
A162860 | TT_Task | Trainset 18 BM1 - Fitout (Innenausbau) | 29/09/2022 | 18/10/2022 | nan | nan | 8 | TK_NotStart | 1201082599 | 178 | 1201082599_178
CW2260 | TT_Task | Trainset 18 BM1 - Transport from Goerlitz to Ceska Lipa | 24/06/2022 | 24/06/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 129 | 1201082599_129
CW3520 | TT_Task | Trainset 18 BM1 - Transport from Ceska Lipa to Vienna | 26/07/2022 | 26/07/2022 | nan | nan | 248 | TK_NotStart | 1201082599 | 130 | 1201082599_130
CW4780 | TT_Task | Trainset 18 BM1 - Bonding and Waxing (Kleben und Wachs) | 08/09/2022 | 28/09/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 131 | 1201082599_131
CWS2260 | TT_Task | Trainset 18 BM1 - Customer Inspection (Haltepunkt) | 23/06/2022 | 23/06/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 171 | 1201082599_171
A162870 | TT_Task | Trainset 18 - Train Completion (Zugbildung ; Aufsetzen) | 18/10/2022 | 02/11/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 175 | 1201082599_175
A162880 | TT_Task | Trainset 18 - Static ; Dynamic Testing (IBN +Finishing) | 03/11/2022 | 17/11/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 163 | 1201082599_163
A162890 | TT_Task | Trainset 18 - Quality Inspection +Rework (Q-Abnahme + Nachartbeit) | 18/11/2022 | 23/11/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 145 | 1201082599_145
A162900 | TT_Task | Trainset 18 - Customer Tests (IBN am Erf?lungsort) | 06/02/2023 | 17/02/2023 | nan | nan | 0 | TK_NotStart | 1201082599 | 139 | 1201082599_139
A162910 | TT_Task | Trainset 18 - Preliminary Customer Acceptance (Kundenabnahme) | 20/02/2023 | 21/02/2023 | nan | nan | 0 | TK_NotStart | 1201082599 | 140 | 1201082599_140
A162920 | TT_Task | Trainset 18 - Trial Period (Probebetrieb) | 22/02/2023 | 02/06/2023 | nan | nan | 0 | TK_NotStart | 1201082599 | 176 | 1201082599_176
A162930 | TT_Task | Trainset 18 - ATA notification trial operation complete and defect free (Meldung Probebetrieb bestanden und Mangelfrei) | 05/06/2023 | 07/06/2023 | nan | nan | 0 | TK_NotStart | 1201082599 | 142 | 1201082599_142
A239052 | TT_Task | Trainset 18 - Customer Factory Inspection + Rework (Werksabnahme +Nacharbeit) | 24/11/2022 | 29/11/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 137 | 1201082599_137
A239062 | TT_Task | Trainset 18 - Transport to Customer (Transport zum Kunden) | 30/11/2022 | 30/11/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 177 | 1201082599_177
PAYM10380 | TT_Task | WLB Approval to Start Trial Operation (Freigabe zum Probebetrieb) 18 | 22/02/2023 | 22/02/2023 | nan | nan | 0 | TK_NotStart | 1201082599 | 147 | 1201082599_147
A237042 | TT_Task | Trainset 19 CM7 - Carbody Surface (Oberfl?che) | 01/09/2022 | 22/09/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 164 | 1201082599_164
A237052 | TT_Task | Trainset 19 CM7 - Fitout (Innenausbau) | 23/09/2022 | 04/10/2022 | nan | nan | 192 | TK_NotStart | 1201082599 | 165 | 1201082599_165
CWS2270 | TT_Task | Trainset 19 CM7 - Customer Inspection (Haltepunkt) | 01/09/2022 | 01/09/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 166 | 1201082599_166
A237072 | TT_Task | Trainset 19 CM1 - Carbody Surface (Oberfl?che) | 22/09/2022 | 13/10/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 164 | 1201082599_164
A237082 | TT_Task | Trainset 19 CM1 - Fitout (Innenausbau) | 14/10/2022 | 25/10/2022 | nan | nan | 80 | TK_NotStart | 1201082599 | 165 | 1201082599_165
CWS2280 | TT_Task | Trainset 19 CM1 - Customer Inspection (Haltepunkt) | 22/09/2022 | 22/09/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 166 | 1201082599_166
A237092 | TT_Task | Trainset 19 SM6 - Carbody Production (Rohbau Produktion) | 14/07/2022 | 21/07/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 93 | 1201082599_93
A237102 | TT_Task | Trainset 19 SM6 - Carbody Surface (Oberfl?che) | 26/07/2022 | 23/08/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 167 | 1201082599_167
A237112 | TT_Task | Trainset 19 SM6 - Fitout (Innenausbau) | 03/10/2022 | 27/10/2022 | nan | nan | 64 | TK_NotStart | 1201082599 | 168 | 1201082599_168
CW36950 | TT_Task | Trainset 19 SM6 - Transport from Goerlitz to Ceska Lipa | 25/07/2022 | 25/07/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 97 | 1201082599_97
CW37250 | TT_Task | Trainset 19 SM6 - Transport from Ceska Lipa to Vienna | 24/08/2022 | 24/08/2022 | nan | nan | 88 | TK_NotStart | 1201082599 | 101 | 1201082599_101
CW37550 | TT_Task | Trainset 19 SM6 - Bonding and Waxing (Kleben und Wachs) | 09/09/2022 | 29/09/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 102 | 1201082599_102
CWS2290 | TT_Task | Trainset 19 SM6 - Customer Inspection (Haltepunkt) | 22/07/2022 | 22/07/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 98 | 1201082599_98
A237122 | TT_Task | Trainset 19 SM2 - Carbody Production (Rohbau Produktion) | 18/07/2022 | 25/07/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 108 | 1201082599_108
A237132 | TT_Task | Trainset 19 SM2 - Carbody Surface (Oberfl?che) | 28/07/2022 | 25/08/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 169 | 1201082599_169
A237142 | TT_Task | Trainset 19 SM2 - Fitout (Innenausbau) | 13/10/2022 | 10/11/2022 | nan | nan | 16 | TK_NotStart | 1201082599 | 170 | 1201082599_170
CW36960 | TT_Task | Trainset 19 SM2 - Transport from Goerlitz to Ceska Lipa | 27/07/2022 | 27/07/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 109 | 1201082599_109
CW37260 | TT_Task | Trainset 19 SM2 - Transport from Ceska Lipa to Vienna | 26/08/2022 | 26/08/2022 | nan | nan | 144 | TK_NotStart | 1201082599 | 111 | 1201082599_111
CW37560 | TT_Task | Trainset 19 SM2 - Bonding and Waxing (Kleben und Wachs) | 22/09/2022 | 12/10/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 112 | 1201082599_112
CWS2300 | TT_Task | Trainset 19 SM2 - Customer Inspection (Haltepunkt) | 26/07/2022 | 26/07/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 110 | 1201082599_110
A237182 | TT_Task | Trainset 19 BM7 - Carbody Production (Rohbau Produktion) | 13/07/2022 | 20/07/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 113 | 1201082599_113
A237192 | TT_Task | Trainset 19 BM7 - Carbody Surface (Oberfl?che) | 25/07/2022 | 22/08/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 116 | 1201082599_116
A237202 | TT_Task | Trainset 19 BM7 - Fitout (Innenausbau) | 19/10/2022 | 10/11/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 119 | 1201082599_119
CW36980 | TT_Task | Trainset 19 BM7 - Transport from Goerlitz to Ceska Lipa | 22/07/2022 | 22/07/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 114 | 1201082599_114
CW37280 | TT_Task | Trainset 19 BM7 - Transport from Ceska Lipa to Vienna | 23/08/2022 | 23/08/2022 | nan | nan | 168 | TK_NotStart | 1201082599 | 117 | 1201082599_117
CW37580 | TT_Task | Trainset 19 BM7 - Bonding and Waxing (Kleben und Wachs) | 22/09/2022 | 12/10/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 118 | 1201082599_118
CWS2320 | TT_Task | Trainset 19 BM7 - Customer Inspection (Haltepunkt) | 21/07/2022 | 21/07/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 171 | 1201082599_171
A237152 | TT_Task | Trainset 19 BM3 - Carbody Production (Rohbau Produktion) | 15/07/2022 | 22/07/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 121 | 1201082599_121
A237162 | TT_Task | Trainset 19 BM3 - Carbody Surface (Oberfl?che) | 27/07/2022 | 24/08/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 172 | 1201082599_172
A237172 | TT_Task | Trainset 19 BM3 - Fitout (Innenausbau) | 19/10/2022 | 10/11/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 173 | 1201082599_173
CW36970 | TT_Task | Trainset 19 BM3 - Transport from Goerlitz to Ceska Lipa | 26/07/2022 | 26/07/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 122 | 1201082599_122
CW37270 | TT_Task | Trainset 19 BM3 - Transport from Ceska Lipa to Vienna | 25/08/2022 | 25/08/2022 | nan | nan | 168 | TK_NotStart | 1201082599 | 124 | 1201082599_124
CW37570 | TT_Task | Trainset 19 BM3 - Bonding and Waxing (Kleben und Wachs) | 26/09/2022 | 14/10/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 125 | 1201082599_125
CWS2310 | TT_Task | Trainset 19 BM3 - Customer Inspection (Haltepunkt) | 25/07/2022 | 25/07/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 174 | 1201082599_174
A237212 | TT_Task | Trainset 19 BM1 - Carbody Production (Rohbau Produktion) | 19/07/2022 | 26/07/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 128 | 1201082599_128
A237222 | TT_Task | Trainset 19 BM1 - Carbody Surface (Oberfl?che) | 29/07/2022 | 26/08/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 172 | 1201082599_172
A237232 | TT_Task | Trainset 19 BM1 - Fitout (Innenausbau) | 20/10/2022 | 11/11/2022 | nan | nan | 8 | TK_NotStart | 1201082599 | 178 | 1201082599_178
CW36990 | TT_Task | Trainset 19 BM1 - Transport from Goerlitz to Ceska Lipa | 28/07/2022 | 28/07/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 129 | 1201082599_129
CW37290 | TT_Task | Trainset 19 BM1 - Transport from Ceska Lipa to Vienna | 29/08/2022 | 29/08/2022 | nan | nan | 176 | TK_NotStart | 1201082599 | 130 | 1201082599_130
CW37590 | TT_Task | Trainset 19 BM1 - Bonding and Waxing (Kleben und Wachs) | 29/09/2022 | 19/10/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 131 | 1201082599_131
CWS2330 | TT_Task | Trainset 19 BM1 - Customer Inspection (Haltepunkt) | 27/07/2022 | 27/07/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 171 | 1201082599_171
A237242 | TT_Task | Trainset 19 - Train Completion (Zugbildung ; Aufsetzen) | 11/11/2022 | 23/11/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 175 | 1201082599_175
A237252 | TT_Task | Trainset 19 - Static ; Dynamic Testing (IBN +Finishing) | 24/11/2022 | 09/12/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 163 | 1201082599_163
A237262 | TT_Task | Trainset 19 - Rework (Restarbeiten) | 12/12/2022 | 13/12/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 150 | 1201082599_150
A237272 | TT_Task | Trainset 19 - Customer Tests (Test beim Kunden) | 20/02/2023 | 24/02/2023 | nan | nan | 0 | TK_NotStart | 1201082599 | 152 | 1201082599_152
A237282 | TT_Task | Trainset 19 - Preliminary Customer Acceptance (Kundenabnahme) | 27/02/2023 | 28/02/2023 | nan | nan | 0 | TK_NotStart | 1201082599 | 140 | 1201082599_140
A237292 | TT_Task | Trainset 19 - Trial Period (Probebetrieb) | 08/03/2023 | 16/06/2023 | nan | nan | 0 | TK_NotStart | 1201082599 | 176 | 1201082599_176
A237302 | TT_Task | Trainset 19 - ATA notification trial operation complete and defect free (Meldung Probebetrieb bestanden und Mangelfrei) | 19/06/2023 | 21/06/2023 | nan | nan | 0 | TK_NotStart | 1201082599 | 142 | 1201082599_142
A239072 | TT_Task | Trainset 19 - Customer Factory Inspection (Werksabnahme) | 14/12/2022 | 19/12/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 151 | 1201082599_151
A239082 | TT_Task | Trainset 19 - Transport to Customer (Transport zum Kunden) | 20/12/2022 | 20/12/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 177 | 1201082599_177
PAYM11950 | TT_Task | WLB Approval to Start Trial Operation (Freigabe zum Probebetrieb) 19 | 01/03/2023 | 01/03/2023 | nan | nan | 40 | TK_NotStart | 1201082599 | 147 | 1201082599_147
A237332 | TT_Task | Trainset 20 CM7 - Carbody Surface (Oberfl?che) | 22/09/2022 | 13/10/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 164 | 1201082599_164
A237342 | TT_Task | Trainset 20 CM7 - Fitout (Innenausbau) | 14/10/2022 | 25/10/2022 | nan | nan | 192 | TK_NotStart | 1201082599 | 165 | 1201082599_165
CWS2340 | TT_Task | Trainset 20 CM7 - Customer Inspection (Haltepunkt) | 22/09/2022 | 22/09/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 166 | 1201082599_166
A237362 | TT_Task | Trainset 20 CM1 - Carbody Surface (Oberfl?che) | 13/10/2022 | 08/11/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 164 | 1201082599_164
A237372 | TT_Task | Trainset 20 CM1 - Fitout (Innenausbau) | 09/11/2022 | 18/11/2022 | nan | nan | 80 | TK_NotStart | 1201082599 | 165 | 1201082599_165
CWS2350 | TT_Task | Trainset 20 CM1 - Customer Inspection (Haltepunkt) | 13/10/2022 | 13/10/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 166 | 1201082599_166
A237382 | TT_Task | Trainset 20 SM6 - Carbody Production (Rohbau Produktion) | 26/07/2022 | 02/08/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 93 | 1201082599_93
A237392 | TT_Task | Trainset 20 SM6 - Carbody Surface (Oberfl?che) | 05/08/2022 | 02/09/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 167 | 1201082599_167
A237402 | TT_Task | Trainset 20 SM6 - Fitout (Innenausbau) | 24/10/2022 | 21/11/2022 | nan | nan | 64 | TK_NotStart | 1201082599 | 168 | 1201082599_168
CW37000 | TT_Task | Trainset 20 SM6 - Transport from Goerlitz to Ceska Lipa | 04/08/2022 | 04/08/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 97 | 1201082599_97
CW37300 | TT_Task | Trainset 20 SM6 - Transport from Ceska Lipa to Vienna | 05/09/2022 | 05/09/2022 | nan | nan | 144 | TK_NotStart | 1201082599 | 101 | 1201082599_101
CW37600 | TT_Task | Trainset 20 SM6 - Bonding and Waxing (Kleben und Wachs) | 30/09/2022 | 20/10/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 102 | 1201082599_102
CWS2360 | TT_Task | Trainset 20 SM6 - Customer Inspection (Haltepunkt) | 03/08/2022 | 03/08/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 98 | 1201082599_98
A237412 | TT_Task | Trainset 20 SM2 - Carbody Production (Rohbau Produktion) | 29/07/2022 | 05/08/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 108 | 1201082599_108
A237422 | TT_Task | Trainset 20 SM2 - Carbody Surface (Oberfl?che) | 10/08/2022 | 07/09/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 169 | 1201082599_169
A237432 | TT_Task | Trainset 20 SM2 - Fitout (Innenausbau) | 08/11/2022 | 01/12/2022 | nan | nan | 16 | TK_NotStart | 1201082599 | 170 | 1201082599_170
CW37010 | TT_Task | Trainset 20 SM2 - Transport from Goerlitz to Ceska Lipa | 09/08/2022 | 09/08/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 109 | 1201082599_109
CW37310 | TT_Task | Trainset 20 SM2 - Transport from Ceska Lipa to Vienna | 08/09/2022 | 08/09/2022 | nan | nan | 192 | TK_NotStart | 1201082599 | 111 | 1201082599_111
CW37610 | TT_Task | Trainset 20 SM2 - Bonding and Waxing (Kleben und Wachs) | 13/10/2022 | 07/11/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 112 | 1201082599_112
CWS2370 | TT_Task | Trainset 20 SM2 - Customer Inspection (Haltepunkt) | 08/08/2022 | 08/08/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 110 | 1201082599_110
A237472 | TT_Task | Trainset 20 BM7 - Carbody Production (Rohbau Produktion) | 25/07/2022 | 01/08/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 113 | 1201082599_113
A237482 | TT_Task | Trainset 20 BM7 - Carbody Surface (Oberfl?che) | 04/08/2022 | 01/09/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 116 | 1201082599_116
A237492 | TT_Task | Trainset 20 BM7 - Fitout (Innenausbau) | 14/11/2022 | 01/12/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 119 | 1201082599_119
CW37030 | TT_Task | Trainset 20 BM7 - Transport from Goerlitz to Ceska Lipa | 03/08/2022 | 03/08/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 114 | 1201082599_114
CW37330 | TT_Task | Trainset 20 BM7 - Transport from Ceska Lipa to Vienna | 02/09/2022 | 02/09/2022 | nan | nan | 224 | TK_NotStart | 1201082599 | 117 | 1201082599_117
CW37630 | TT_Task | Trainset 20 BM7 - Bonding and Waxing (Kleben und Wachs) | 13/10/2022 | 07/11/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 118 | 1201082599_118
CWS2390 | TT_Task | Trainset 20 BM7 - Customer Inspection (Haltepunkt) | 02/08/2022 | 02/08/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 171 | 1201082599_171
A237442 | TT_Task | Trainset 20 BM3 - Carbody Production (Rohbau Produktion) | 28/07/2022 | 04/08/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 121 | 1201082599_121
A237452 | TT_Task | Trainset 20 BM3 - Carbody Surface (Oberfl?che) | 09/08/2022 | 06/09/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 172 | 1201082599_172
A237462 | TT_Task | Trainset 20 BM3 - Fitout (Innenausbau) | 14/11/2022 | 01/12/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 173 | 1201082599_173
CW37020 | TT_Task | Trainset 20 BM3 - Transport from Goerlitz to Ceska Lipa | 08/08/2022 | 08/08/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 122 | 1201082599_122
CW37320 | TT_Task | Trainset 20 BM3 - Transport from Ceska Lipa to Vienna | 07/09/2022 | 07/09/2022 | nan | nan | 216 | TK_NotStart | 1201082599 | 124 | 1201082599_124
CW37620 | TT_Task | Trainset 20 BM3 - Bonding and Waxing (Kleben und Wachs) | 17/10/2022 | 09/11/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 125 | 1201082599_125
CWS2380 | TT_Task | Trainset 20 BM3 - Customer Inspection (Haltepunkt) | 05/08/2022 | 05/08/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 174 | 1201082599_174
A237502 | TT_Task | Trainset 20 BM1 - Carbody Production (Rohbau Produktion) | 15/08/2022 | 22/08/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 128 | 1201082599_128
A237512 | TT_Task | Trainset 20 BM1 - Carbody Surface (Oberfl?che) | 25/08/2022 | 22/09/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 172 | 1201082599_172
A237522 | TT_Task | Trainset 20 BM1 - Fitout (Innenausbau) | 15/11/2022 | 02/12/2022 | nan | nan | 8 | TK_NotStart | 1201082599 | 178 | 1201082599_178
CW37040 | TT_Task | Trainset 20 BM1 - Transport from Goerlitz to Ceska Lipa | 24/08/2022 | 24/08/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 129 | 1201082599_129
CW37340 | TT_Task | Trainset 20 BM1 - Transport from Ceska Lipa to Vienna | 23/09/2022 | 23/09/2022 | nan | nan | 144 | TK_NotStart | 1201082599 | 130 | 1201082599_130
CW37640 | TT_Task | Trainset 20 BM1 - Bonding and Waxing (Kleben und Wachs) | 20/10/2022 | 14/11/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 131 | 1201082599_131
CWS2400 | TT_Task | Trainset 20 BM1 - Customer Inspection (Haltepunkt) | 23/08/2022 | 23/08/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 171 | 1201082599_171
A237532 | TT_Task | Trainset 20 - Train Completion (Zugbildung ; Aufsetzen) | 02/12/2022 | 15/12/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 175 | 1201082599_175
A237542 | TT_Task | Trainset 20 - Static ; Dynamic Testing (IBN +Finishing) | 16/12/2022 | 13/01/2023 | nan | nan | 0 | TK_NotStart | 1201082599 | 163 | 1201082599_163
A237552 | TT_Task | Trainset 20 - Rework (Restarbeiten) | 16/01/2023 | 17/01/2023 | nan | nan | 0 | TK_NotStart | 1201082599 | 150 | 1201082599_150
A237562 | TT_Task | Trainset 20 - Customer Tests (Test beim Kunden) | 27/02/2023 | 03/03/2023 | nan | nan | 0 | TK_NotStart | 1201082599 | 152 | 1201082599_152
A237572 | TT_Task | Trainset 20 - Preliminary Customer Acceptance (Kundenabnahme) | 06/03/2023 | 07/03/2023 | nan | nan | 0 | TK_NotStart | 1201082599 | 140 | 1201082599_140
A237582 | TT_Task | Trainset 20 - Trial Period (Probebetrieb) | 08/03/2023 | 16/06/2023 | nan | nan | 0 | TK_NotStart | 1201082599 | 176 | 1201082599_176
A237592 | TT_Task | Trainset 20 - ATA notification trial operation complete and defect free (Meldung Probebetrieb bestanden und Mangelfrei) | 19/06/2023 | 21/06/2023 | nan | nan | 0 | TK_NotStart | 1201082599 | 142 | 1201082599_142
A239092 | TT_Task | Trainset 20 - Customer Factory Inspection (Werksabnahme) | 18/01/2023 | 23/01/2023 | nan | nan | 0 | TK_NotStart | 1201082599 | 151 | 1201082599_151
A239102 | TT_Task | Trainset 20 - Transport to Customer (Transport zum Kunden) | 24/01/2023 | 24/01/2023 | nan | nan | 0 | TK_NotStart | 1201082599 | 177 | 1201082599_177
PAYM11960 | TT_Task | WLB Approval to Start Trial Operation (Freigabe zum Probebetrieb) 20 | 08/03/2023 | 08/03/2023 | nan | nan | 0 | TK_NotStart | 1201082599 | 147 | 1201082599_147
A237622 | TT_Task | Trainset 21 CM7 - Carbody Surface (Oberfl?che) | 13/10/2022 | 08/11/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 164 | 1201082599_164
A237632 | TT_Task | Trainset 21 CM7 - Fitout (Innenausbau) | 09/11/2022 | 18/11/2022 | nan | nan | 192 | TK_NotStart | 1201082599 | 165 | 1201082599_165
CWS2410 | TT_Task | Trainset 21 CM7 - Customer Inspection (Haltepunkt) | 13/10/2022 | 13/10/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 166 | 1201082599_166
A237652 | TT_Task | Trainset 21 CM1 - Carbody Surface (Oberfl?che) | 08/11/2022 | 29/11/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 164 | 1201082599_164
A237662 | TT_Task | Trainset 21 CM1 - Fitout (Innenausbau) | 30/11/2022 | 12/12/2022 | nan | nan | 80 | TK_NotStart | 1201082599 | 165 | 1201082599_165
CWS2420 | TT_Task | Trainset 21 CM1 - Customer Inspection (Haltepunkt) | 08/11/2022 | 08/11/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 166 | 1201082599_166
A237672 | TT_Task | Trainset 21 SM6 - Carbody Production (Rohbau Produktion) | 14/09/2022 | 21/09/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 93 | 1201082599_93
A237682 | TT_Task | Trainset 21 SM6 - Carbody Surface (Oberfl?che) | 26/09/2022 | 24/10/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 167 | 1201082599_167
A237692 | TT_Task | Trainset 21 SM6 - Fitout (Innenausbau) | 22/11/2022 | 16/12/2022 | nan | nan | 40 | TK_NotStart | 1201082599 | 168 | 1201082599_168
CW37050 | TT_Task | Trainset 21 SM6 - Transport from Goerlitz to Ceska Lipa | 23/09/2022 | 23/09/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 97 | 1201082599_97
CW37350 | TT_Task | Trainset 21 SM6 - Transport from Ceska Lipa to Vienna | 25/10/2022 | 25/10/2022 | nan | nan | 8 | TK_NotStart | 1201082599 | 101 | 1201082599_101
CW37650 | TT_Task | Trainset 21 SM6 - Bonding and Waxing (Kleben und Wachs) | 27/10/2022 | 18/11/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 102 | 1201082599_102
CWS2430 | TT_Task | Trainset 21 SM6 - Customer Inspection (Haltepunkt) | 22/09/2022 | 22/09/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 98 | 1201082599_98
A237702 | TT_Task | Trainset 21 SM2 - Carbody Production (Rohbau Produktion) | 16/09/2022 | 23/09/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 108 | 1201082599_108
A237712 | TT_Task | Trainset 21 SM2 - Carbody Surface (Oberfl?che) | 28/09/2022 | 26/10/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 169 | 1201082599_169
A237722 | TT_Task | Trainset 21 SM2 - Fitout (Innenausbau) | 29/11/2022 | 23/12/2022 | nan | nan | 16 | TK_NotStart | 1201082599 | 170 | 1201082599_170
CW37060 | TT_Task | Trainset 21 SM2 - Transport from Goerlitz to Ceska Lipa | 27/09/2022 | 27/09/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 109 | 1201082599_109
CW37360 | TT_Task | Trainset 21 SM2 - Transport from Ceska Lipa to Vienna | 27/10/2022 | 27/10/2022 | nan | nan | 56 | TK_NotStart | 1201082599 | 111 | 1201082599_111
CW37660 | TT_Task | Trainset 21 SM2 - Bonding and Waxing (Kleben und Wachs) | 08/11/2022 | 28/11/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 112 | 1201082599_112
CWS2440 | TT_Task | Trainset 21 SM2 - Customer Inspection (Haltepunkt) | 26/09/2022 | 26/09/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 110 | 1201082599_110
A237762 | TT_Task | Trainset 21 BM7 - Carbody Production (Rohbau Produktion) | 13/09/2022 | 20/09/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 113 | 1201082599_113
A237772 | TT_Task | Trainset 21 BM7 - Carbody Surface (Oberfl?che) | 23/09/2022 | 21/10/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 116 | 1201082599_116
A237782 | TT_Task | Trainset 21 BM7 - Fitout (Innenausbau) | 05/12/2022 | 23/12/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 119 | 1201082599_119
CW37080 | TT_Task | Trainset 21 BM7 - Transport from Goerlitz to Ceska Lipa | 22/09/2022 | 22/09/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 114 | 1201082599_114
CW37380 | TT_Task | Trainset 21 BM7 - Transport from Ceska Lipa to Vienna | 24/10/2022 | 24/10/2022 | nan | nan | 80 | TK_NotStart | 1201082599 | 117 | 1201082599_117
CW37680 | TT_Task | Trainset 21 BM7 - Bonding and Waxing (Kleben und Wachs) | 08/11/2022 | 28/11/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 118 | 1201082599_118
CWS2460 | TT_Task | Trainset 21 BM7 - Customer Inspection (Haltepunkt) | 21/09/2022 | 21/09/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 171 | 1201082599_171
A237732 | TT_Task | Trainset 21 BM3 - Carbody Production (Rohbau Produktion) | 15/09/2022 | 22/09/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 121 | 1201082599_121
A237742 | TT_Task | Trainset 21 BM3 - Carbody Surface (Oberfl?che) | 27/09/2022 | 25/10/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 172 | 1201082599_172
A237752 | TT_Task | Trainset 21 BM3 - Fitout (Innenausbau) | 05/12/2022 | 23/12/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 173 | 1201082599_173
CW37070 | TT_Task | Trainset 21 BM3 - Transport from Goerlitz to Ceska Lipa | 26/09/2022 | 26/09/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 122 | 1201082599_122
CW37370 | TT_Task | Trainset 21 BM3 - Transport from Ceska Lipa to Vienna | 26/10/2022 | 26/10/2022 | nan | nan | 80 | TK_NotStart | 1201082599 | 124 | 1201082599_124
CW37670 | TT_Task | Trainset 21 BM3 - Bonding and Waxing (Kleben und Wachs) | 10/11/2022 | 30/11/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 125 | 1201082599_125
CWS2450 | TT_Task | Trainset 21 BM3 - Customer Inspection (Haltepunkt) | 23/09/2022 | 23/09/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 174 | 1201082599_174
A237792 | TT_Task | Trainset 21 BM1 - Carbody Production (Rohbau Produktion) | 19/09/2022 | 26/09/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 128 | 1201082599_128
A237802 | TT_Task | Trainset 21 BM1 - Carbody Surface (Oberfl?che) | 29/09/2022 | 27/10/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 172 | 1201082599_172
A237812 | TT_Task | Trainset 21 BM1 - Fitout (Innenausbau) | 06/12/2022 | 09/01/2023 | nan | nan | 8 | TK_NotStart | 1201082599 | 178 | 1201082599_178
CW37090 | TT_Task | Trainset 21 BM1 - Transport from Goerlitz to Ceska Lipa | 28/09/2022 | 28/09/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 129 | 1201082599_129
CW37390 | TT_Task | Trainset 21 BM1 - Transport from Ceska Lipa to Vienna | 28/10/2022 | 28/10/2022 | nan | nan | 88 | TK_NotStart | 1201082599 | 130 | 1201082599_130
CW37690 | TT_Task | Trainset 21 BM1 - Bonding and Waxing (Kleben und Wachs) | 15/11/2022 | 05/12/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 131 | 1201082599_131
CWS2470 | TT_Task | Trainset 21 BM1 - Customer Inspection (Haltepunkt) | 27/09/2022 | 27/09/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 171 | 1201082599_171
A237822 | TT_Task | Trainset 21 - Train Completion (Zugbildung ; Aufsetzen) | 09/01/2023 | 19/01/2023 | nan | nan | 0 | TK_NotStart | 1201082599 | 175 | 1201082599_175
A237832 | TT_Task | Trainset 21 - Static ; Dynamic Testing (IBN +Finishing) | 20/01/2023 | 03/02/2023 | nan | nan | 0 | TK_NotStart | 1201082599 | 163 | 1201082599_163
A237842 | TT_Task | Trainset 21 - Rework (Restarbeiten) | 06/02/2023 | 07/02/2023 | nan | nan | 0 | TK_NotStart | 1201082599 | 150 | 1201082599_150
A237852 | TT_Task | Trainset 21 - Customer Tests (Test beim Kunden) | 06/03/2023 | 10/03/2023 | nan | nan | 0 | TK_NotStart | 1201082599 | 152 | 1201082599_152
A237862 | TT_Task | Trainset 21 - Preliminary Customer Acceptance (Kundenabnahme) | 13/03/2023 | 14/03/2023 | nan | nan | 0 | TK_NotStart | 1201082599 | 140 | 1201082599_140
A237872 | TT_Task | Trainset 21 - Trial Period (Probebetrieb) | 22/03/2023 | 30/06/2023 | nan | nan | 0 | TK_NotStart | 1201082599 | 176 | 1201082599_176
A237882 | TT_Task | Trainset 21 - ATA notification trial operation complete and defect free (Meldung Probebetrieb bestanden und Mangelfrei) | 03/07/2023 | 05/07/2023 | nan | nan | 0 | TK_NotStart | 1201082599 | 142 | 1201082599_142
A239112 | TT_Task | Trainset 21 - Customer Factory Inspection (Werksabnahme) | 08/02/2023 | 13/02/2023 | nan | nan | 0 | TK_NotStart | 1201082599 | 151 | 1201082599_151
A239122 | TT_Task | Trainset 21 - Transport to Customer (Transport zum Kunden) | 14/02/2023 | 14/02/2023 | nan | nan | 0 | TK_NotStart | 1201082599 | 177 | 1201082599_177
PAYM11970 | TT_Task | WLB Approval to Start Trial Operation (Freigabe zum Probebetrieb) 21 | 15/03/2023 | 15/03/2023 | nan | nan | 40 | TK_NotStart | 1201082599 | 147 | 1201082599_147
A237912 | TT_Task | Trainset 22 CM7 - Carbody Surface (Oberfl?che) | 08/11/2022 | 29/11/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 164 | 1201082599_164
A237922 | TT_Task | Trainset 22 CM7 - Fitout (Innenausbau) | 30/11/2022 | 12/12/2022 | nan | nan | 192 | TK_NotStart | 1201082599 | 165 | 1201082599_165
CWS2480 | TT_Task | Trainset 22 CM7 - Customer Inspection (Haltepunkt) | 08/11/2022 | 08/11/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 166 | 1201082599_166
A237942 | TT_Task | Trainset 22 CM1 - Carbody Surface (Oberfl?che) | 29/11/2022 | 21/12/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 164 | 1201082599_164
A237952 | TT_Task | Trainset 22 CM1 - Fitout (Innenausbau) | 22/12/2022 | 16/01/2023 | nan | nan | 80 | TK_NotStart | 1201082599 | 165 | 1201082599_165
CWS2490 | TT_Task | Trainset 22 CM1 - Customer Inspection (Haltepunkt) | 29/11/2022 | 29/11/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 166 | 1201082599_166
A237962 | TT_Task | Trainset 22 SM6 - Carbody Production (Rohbau Produktion) | 26/09/2022 | 03/10/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 108 | 1201082599_108
A237972 | TT_Task | Trainset 22 SM6 - Carbody Surface (Oberfl?che) | 06/10/2022 | 03/11/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 169 | 1201082599_169
A237982 | TT_Task | Trainset 22 SM6 - Fitout (Innenausbau) | 14/12/2022 | 20/01/2023 | nan | nan | 40 | TK_NotStart | 1201082599 | 170 | 1201082599_170
CW37100 | TT_Task | Trainset 22 SM6 - Transport from Goerlitz to Ceska Lipa | 05/10/2022 | 05/10/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 97 | 1201082599_97
CW37400 | TT_Task | Trainset 22 SM6 - Transport from Ceska Lipa to Vienna | 04/11/2022 | 04/11/2022 | nan | nan | 80 | TK_NotStart | 1201082599 | 101 | 1201082599_101
CW37700 | TT_Task | Trainset 22 SM6 - Bonding and Waxing (Kleben und Wachs) | 21/11/2022 | 12/12/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 112 | 1201082599_112
CWS2500 | TT_Task | Trainset 22 SM6 - Customer Inspection (Haltepunkt) | 04/10/2022 | 04/10/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 110 | 1201082599_110
A237992 | TT_Task | Trainset 22 SM2 - Carbody Production (Rohbau Produktion) | 28/09/2022 | 05/10/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 108 | 1201082599_108
A238002 | TT_Task | Trainset 22 SM2 - Carbody Surface (Oberfl?che) | 10/10/2022 | 07/11/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 169 | 1201082599_169
A238012 | TT_Task | Trainset 22 SM2 - Fitout (Innenausbau) | 21/12/2022 | 27/01/2023 | nan | nan | 16 | TK_NotStart | 1201082599 | 170 | 1201082599_170
CW37110 | TT_Task | Trainset 22 SM2 - Transport from Goerlitz to Ceska Lipa | 07/10/2022 | 07/10/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 109 | 1201082599_109
CW37410 | TT_Task | Trainset 22 SM2 - Transport from Ceska Lipa to Vienna | 08/11/2022 | 08/11/2022 | nan | nan | 112 | TK_NotStart | 1201082599 | 111 | 1201082599_111
CW37710 | TT_Task | Trainset 22 SM2 - Bonding and Waxing (Kleben und Wachs) | 29/11/2022 | 20/12/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 112 | 1201082599_112
CWS2510 | TT_Task | Trainset 22 SM2 - Customer Inspection (Haltepunkt) | 06/10/2022 | 06/10/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 110 | 1201082599_110
A238052 | TT_Task | Trainset 22 BM7 - Carbody Production (Rohbau Produktion) | 23/09/2022 | 30/09/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 113 | 1201082599_113
A238062 | TT_Task | Trainset 22 BM7 - Carbody Surface (Oberfl?che) | 05/10/2022 | 02/11/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 116 | 1201082599_116
A238072 | TT_Task | Trainset 22 BM7 - Fitout (Innenausbau) | 10/01/2023 | 27/01/2023 | nan | nan | 0 | TK_NotStart | 1201082599 | 173 | 1201082599_173
CW37130 | TT_Task | Trainset 22 BM7 - Transport from Goerlitz to Ceska Lipa | 04/10/2022 | 04/10/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 114 | 1201082599_114
CW37430 | TT_Task | Trainset 22 BM7 - Transport from Ceska Lipa to Vienna | 03/11/2022 | 03/11/2022 | nan | nan | 136 | TK_NotStart | 1201082599 | 117 | 1201082599_117
CW37730 | TT_Task | Trainset 22 BM7 - Bonding and Waxing (Kleben und Wachs) | 29/11/2022 | 20/12/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 118 | 1201082599_118
CWS2530 | TT_Task | Trainset 22 BM7 - Customer Inspection (Haltepunkt) | 03/10/2022 | 03/10/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 171 | 1201082599_171
A238022 | TT_Task | Trainset 22 BM3 - Carbody Production (Rohbau Produktion) | 27/09/2022 | 04/10/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 121 | 1201082599_121
A238032 | TT_Task | Trainset 22 BM3 - Carbody Surface (Oberfl?che) | 07/10/2022 | 04/11/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 172 | 1201082599_172
A238042 | TT_Task | Trainset 22 BM3 - Fitout (Innenausbau) | 10/01/2023 | 27/01/2023 | nan | nan | 0 | TK_NotStart | 1201082599 | 173 | 1201082599_173
CW37120 | TT_Task | Trainset 22 BM3 - Transport from Goerlitz to Ceska Lipa | 06/10/2022 | 06/10/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 122 | 1201082599_122
CW37420 | TT_Task | Trainset 22 BM3 - Transport from Ceska Lipa to Vienna | 07/11/2022 | 07/11/2022 | nan | nan | 136 | TK_NotStart | 1201082599 | 124 | 1201082599_124
CW37720 | TT_Task | Trainset 22 BM3 - Bonding and Waxing (Kleben und Wachs) | 01/12/2022 | 22/12/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 131 | 1201082599_131
CWS2520 | TT_Task | Trainset 22 BM3 - Customer Inspection (Haltepunkt) | 05/10/2022 | 05/10/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 171 | 1201082599_171
A238082 | TT_Task | Trainset 22 BM1 - Carbody Production (Rohbau Produktion) | 29/09/2022 | 06/10/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 128 | 1201082599_128
A238092 | TT_Task | Trainset 22 BM1 - Carbody Surface (Oberfl?che) | 11/10/2022 | 08/11/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 172 | 1201082599_172
A238102 | TT_Task | Trainset 22 BM1 - Fitout (Innenausbau) | 11/01/2023 | 30/01/2023 | nan | nan | 8 | TK_NotStart | 1201082599 | 173 | 1201082599_173
CW37140 | TT_Task | Trainset 22 BM1 - Transport from Goerlitz to Ceska Lipa | 10/10/2022 | 10/10/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 129 | 1201082599_129
CW37440 | TT_Task | Trainset 22 BM1 - Transport from Ceska Lipa to Vienna | 09/11/2022 | 09/11/2022 | nan | nan | 144 | TK_NotStart | 1201082599 | 130 | 1201082599_130
CW37740 | TT_Task | Trainset 22 BM1 - Bonding and Waxing (Kleben und Wachs) | 06/12/2022 | 10/01/2023 | nan | nan | 0 | TK_NotStart | 1201082599 | 131 | 1201082599_131
CWS2540 | TT_Task | Trainset 22 BM1 - Customer Inspection (Haltepunkt) | 07/10/2022 | 07/10/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 171 | 1201082599_171
A238112 | TT_Task | Trainset 22 - Train Completion (Zugbildung ; Aufsetzen) | 30/01/2023 | 09/02/2023 | nan | nan | 0 | TK_NotStart | 1201082599 | 175 | 1201082599_175
A238122 | TT_Task | Trainset 22 - Static ; Dynamic Testing (IBN +Finishing) | 10/02/2023 | 24/02/2023 | nan | nan | 0 | TK_NotStart | 1201082599 | 163 | 1201082599_163
A238132 | TT_Task | Trainset 22 - Rework (Restarbeiten) | 27/02/2023 | 28/02/2023 | nan | nan | 0 | TK_NotStart | 1201082599 | 150 | 1201082599_150
A238142 | TT_Task | Trainset 22 - Customer Tests (Test beim Kunden) | 13/03/2023 | 17/03/2023 | nan | nan | 0 | TK_NotStart | 1201082599 | 152 | 1201082599_152
A238152 | TT_Task | Trainset 22 - Preliminary Customer Acceptance (Kundenabnahme) | 20/03/2023 | 21/03/2023 | nan | nan | 0 | TK_NotStart | 1201082599 | 140 | 1201082599_140
A238162 | TT_Task | Trainset 22 - Trial Period (Probebetrieb) | 22/03/2023 | 30/06/2023 | nan | nan | 0 | TK_NotStart | 1201082599 | 176 | 1201082599_176
A238172 | TT_Task | Trainset 22 - ATA notification trial operation complete and defect free (Meldung Probebetrieb bestanden und Mangelfrei) | 03/07/2023 | 05/07/2023 | nan | nan | 0 | TK_NotStart | 1201082599 | 142 | 1201082599_142
A239132 | TT_Task | Trainset 22 - Customer Factory Inspection (Werksabnahme) | 01/03/2023 | 06/03/2023 | nan | nan | 0 | TK_NotStart | 1201082599 | 151 | 1201082599_151
A239142 | TT_Task | Trainset 22 - Transport to Customer (Transport zum Kunden) | 07/03/2023 | 07/03/2023 | nan | nan | 0 | TK_NotStart | 1201082599 | 177 | 1201082599_177
PAYM11980 | TT_Task | WLB Approval to Start Trial Operation (Freigabe zum Probebetrieb) 22 | 22/03/2023 | 22/03/2023 | nan | nan | 0 | TK_NotStart | 1201082599 | 147 | 1201082599_147
A238202 | TT_Task | Trainset 23 CM7 - Carbody Surface (Oberfl?che) | 29/11/2022 | 21/12/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 164 | 1201082599_164
A238212 | TT_Task | Trainset 23 CM7 - Fitout (Innenausbau) | 22/12/2022 | 16/01/2023 | nan | nan | 192 | TK_NotStart | 1201082599 | 165 | 1201082599_165
CWS2550 | TT_Task | Trainset 23 CM7 - Customer Inspection (Haltepunkt) | 29/11/2022 | 29/11/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 166 | 1201082599_166
A238232 | TT_Task | Trainset 23 CM1 - Carbody Surface (Oberfl?che) | 21/12/2022 | 25/01/2023 | nan | nan | 0 | TK_NotStart | 1201082599 | 164 | 1201082599_164
A238242 | TT_Task | Trainset 23 CM1 - Fitout (Innenausbau) | 26/01/2023 | 06/02/2023 | nan | nan | 80 | TK_NotStart | 1201082599 | 165 | 1201082599_165
CWS2560 | TT_Task | Trainset 23 CM1 - Customer Inspection (Haltepunkt) | 21/12/2022 | 21/12/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 166 | 1201082599_166
A238252 | TT_Task | Trainset 23 SM6 - Carbody Production (Rohbau Produktion) | 01/11/2022 | 08/11/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 93 | 1201082599_93
A238262 | TT_Task | Trainset 23 SM6 - Carbody Surface (Oberfl?che) | 11/11/2022 | 09/12/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 167 | 1201082599_167
A238272 | TT_Task | Trainset 23 SM6 - Fitout (Innenausbau) | 18/01/2023 | 10/02/2023 | nan | nan | 40 | TK_NotStart | 1201082599 | 170 | 1201082599_170
CW37150 | TT_Task | Trainset 23 SM6 - Transport from Goerlitz to Ceska Lipa | 10/11/2022 | 10/11/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 97 | 1201082599_97
CW37450 | TT_Task | Trainset 23 SM6 - Transport from Ceska Lipa to Vienna | 12/12/2022 | 12/12/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 101 | 1201082599_101
CW37750 | TT_Task | Trainset 23 SM6 - Bonding and Waxing (Kleben und Wachs) | 13/12/2022 | 16/01/2023 | nan | nan | 0 | TK_NotStart | 1201082599 | 102 | 1201082599_102
CWS2570 | TT_Task | Trainset 23 SM6 - Customer Inspection (Haltepunkt) | 09/11/2022 | 09/11/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 98 | 1201082599_98
A238282 | TT_Task | Trainset 23 SM2 - Carbody Production (Rohbau Produktion) | 03/11/2022 | 10/11/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 108 | 1201082599_108
A238292 | TT_Task | Trainset 23 SM2 - Carbody Surface (Oberfl?che) | 15/11/2022 | 13/12/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 169 | 1201082599_169
A238302 | TT_Task | Trainset 23 SM2 - Fitout (Innenausbau) | 25/01/2023 | 17/02/2023 | nan | nan | 16 | TK_NotStart | 1201082599 | 170 | 1201082599_170
CW37160 | TT_Task | Trainset 23 SM2 - Transport from Goerlitz to Ceska Lipa | 14/11/2022 | 14/11/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 109 | 1201082599_109
CW37460 | TT_Task | Trainset 23 SM2 - Transport from Ceska Lipa to Vienna | 14/12/2022 | 14/12/2022 | nan | nan | 32 | TK_NotStart | 1201082599 | 111 | 1201082599_111
CW37760 | TT_Task | Trainset 23 SM2 - Bonding and Waxing (Kleben und Wachs) | 21/12/2022 | 24/01/2023 | nan | nan | 0 | TK_NotStart | 1201082599 | 112 | 1201082599_112
CWS2580 | TT_Task | Trainset 23 SM2 - Customer Inspection (Haltepunkt) | 11/11/2022 | 11/11/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 110 | 1201082599_110
A238342 | TT_Task | Trainset 23 BM7 - Carbody Production (Rohbau Produktion) | 28/10/2022 | 04/11/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 113 | 1201082599_113
A238352 | TT_Task | Trainset 23 BM7 - Carbody Surface (Oberfl?che) | 09/11/2022 | 07/12/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 116 | 1201082599_116
A238362 | TT_Task | Trainset 23 BM7 - Fitout (Innenausbau) | 31/01/2023 | 17/02/2023 | nan | nan | 0 | TK_NotStart | 1201082599 | 119 | 1201082599_119
CW37180 | TT_Task | Trainset 23 BM7 - Transport from Goerlitz to Ceska Lipa | 08/11/2022 | 08/11/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 114 | 1201082599_114
CW37480 | TT_Task | Trainset 23 BM7 - Transport from Ceska Lipa to Vienna | 08/12/2022 | 08/12/2022 | nan | nan | 64 | TK_NotStart | 1201082599 | 117 | 1201082599_117
CW37780 | TT_Task | Trainset 23 BM7 - Bonding and Waxing (Kleben und Wachs) | 21/12/2022 | 24/01/2023 | nan | nan | 0 | TK_NotStart | 1201082599 | 118 | 1201082599_118
CWS2600 | TT_Task | Trainset 23 BM7 - Customer Inspection (Haltepunkt) | 07/11/2022 | 07/11/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 171 | 1201082599_171
A238312 | TT_Task | Trainset 23 BM3 - Carbody Production (Rohbau Produktion) | 02/11/2022 | 09/11/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 121 | 1201082599_121
A238322 | TT_Task | Trainset 23 BM3 - Carbody Surface (Oberfl?che) | 14/11/2022 | 12/12/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 172 | 1201082599_172
A238332 | TT_Task | Trainset 23 BM3 - Fitout (Innenausbau) | 31/01/2023 | 17/02/2023 | nan | nan | 0 | TK_NotStart | 1201082599 | 173 | 1201082599_173
CW37170 | TT_Task | Trainset 23 BM3 - Transport from Goerlitz to Ceska Lipa | 11/11/2022 | 11/11/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 122 | 1201082599_122
CW37470 | TT_Task | Trainset 23 BM3 - Transport from Ceska Lipa to Vienna | 13/12/2022 | 13/12/2022 | nan | nan | 56 | TK_NotStart | 1201082599 | 124 | 1201082599_124
CW37770 | TT_Task | Trainset 23 BM3 - Bonding and Waxing (Kleben und Wachs) | 23/12/2022 | 26/01/2023 | nan | nan | 0 | TK_NotStart | 1201082599 | 125 | 1201082599_125
CWS2590 | TT_Task | Trainset 23 BM3 - Customer Inspection (Haltepunkt) | 10/11/2022 | 10/11/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 174 | 1201082599_174
A238372 | TT_Task | Trainset 23 BM1 - Carbody Production (Rohbau Produktion) | 04/11/2022 | 11/11/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 128 | 1201082599_128
A238382 | TT_Task | Trainset 23 BM1 - Carbody Surface (Oberfl?che) | 16/11/2022 | 14/12/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 172 | 1201082599_172
A238392 | TT_Task | Trainset 23 BM1 - Fitout (Innenausbau) | 01/02/2023 | 20/02/2023 | nan | nan | 8 | TK_NotStart | 1201082599 | 173 | 1201082599_173
CW37190 | TT_Task | Trainset 23 BM1 - Transport from Goerlitz to Ceska Lipa | 15/11/2022 | 15/11/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 129 | 1201082599_129
CW37490 | TT_Task | Trainset 23 BM1 - Transport from Ceska Lipa to Vienna | 15/12/2022 | 15/12/2022 | nan | nan | 144 | TK_NotStart | 1201082599 | 130 | 1201082599_130
CW37790 | TT_Task | Trainset 23 BM1 - Bonding and Waxing (Kleben und Wachs) | 11/01/2023 | 31/01/2023 | nan | nan | 0 | TK_NotStart | 1201082599 | 131 | 1201082599_131
CWS2610 | TT_Task | Trainset 23 BM1 - Customer Inspection (Haltepunkt) | 14/11/2022 | 14/11/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 171 | 1201082599_171
A238402 | TT_Task | Trainset 23 - Train Completion (Zugbildung ; Aufsetzen) | 20/02/2023 | 02/03/2023 | nan | nan | 0 | TK_NotStart | 1201082599 | 175 | 1201082599_175
A238412 | TT_Task | Trainset 23 - Static ; Dynamic Testing (IBN +Finishing) | 03/03/2023 | 17/03/2023 | nan | nan | 0 | TK_NotStart | 1201082599 | 163 | 1201082599_163
A238422 | TT_Task | Trainset 23 - Rework (Restarbeiten) | 20/03/2023 | 21/03/2023 | nan | nan | 0 | TK_NotStart | 1201082599 | 150 | 1201082599_150
A238432 | TT_Task | Trainset 23 - Customer Tests (Test beim Kunden) | 29/03/2023 | 04/04/2023 | nan | nan | 0 | TK_NotStart | 1201082599 | 152 | 1201082599_152
A238442 | TT_Task | Trainset 23 - Preliminary Customer Acceptance (Kundenabnahme) | 05/04/2023 | 06/04/2023 | nan | nan | 0 | TK_NotStart | 1201082599 | 140 | 1201082599_140
A238452 | TT_Task | Trainset 23 - Trial Period (Probebetrieb) | 01/05/2023 | 09/08/2023 | nan | nan | 0 | TK_NotStart | 1201082599 | 176 | 1201082599_176
A238462 | TT_Task | Trainset 23 - ATA notification trial operation complete and defect free (Meldung Probebetrieb bestanden und Mangelfrei) | 10/08/2023 | 14/08/2023 | nan | nan | 0 | TK_NotStart | 1201082599 | 142 | 1201082599_142
A239152 | TT_Task | Trainset 23 - Customer Factory Inspection (Werksabnahme) | 22/03/2023 | 27/03/2023 | nan | nan | 0 | TK_NotStart | 1201082599 | 151 | 1201082599_151
A239162 | TT_Task | Trainset 23 - Transport to Customer (Transport zum Kunden) | 28/03/2023 | 28/03/2023 | nan | nan | 0 | TK_NotStart | 1201082599 | 177 | 1201082599_177
PAYM11990 | TT_Task | WLB Approval to Start Trial Operation (Freigabe zum Probebetrieb) 23 | 07/04/2023 | 07/04/2023 | nan | nan | 128 | TK_NotStart | 1201082599 | 147 | 1201082599_147
A238492 | TT_Task | Trainset 24 CM7 - Carbody Surface (Oberfl?che) | 21/12/2022 | 25/01/2023 | nan | nan | 0 | TK_NotStart | 1201082599 | 164 | 1201082599_164
A238502 | TT_Task | Trainset 24 CM7 - Fitout (Innenausbau) | 26/01/2023 | 06/02/2023 | nan | nan | 192 | TK_NotStart | 1201082599 | 165 | 1201082599_165
CWS2620 | TT_Task | Trainset 24 CM7 - Customer Inspection (Haltepunkt) | 21/12/2022 | 21/12/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 166 | 1201082599_166
A238522 | TT_Task | Trainset 24 CM1 - Carbody Surface (Oberfl?che) | 25/01/2023 | 15/02/2023 | nan | nan | 0 | TK_NotStart | 1201082599 | 164 | 1201082599_164
A238532 | TT_Task | Trainset 24 CM1 - Fitout (Innenausbau) | 16/02/2023 | 27/02/2023 | nan | nan | 80 | TK_NotStart | 1201082599 | 165 | 1201082599_165
CWS2630 | TT_Task | Trainset 24 CM1 - Customer Inspection (Haltepunkt) | 25/01/2023 | 25/01/2023 | nan | nan | 0 | TK_NotStart | 1201082599 | 166 | 1201082599_166
A238542 | TT_Task | Trainset 24 SM6 - Carbody Production (Rohbau Produktion) | 11/11/2022 | 18/11/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 93 | 1201082599_93
A238552 | TT_Task | Trainset 24 SM6 - Carbody Surface (Oberfl?che) | 23/11/2022 | 21/12/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 167 | 1201082599_167
A238562 | TT_Task | Trainset 24 SM6 - Fitout (Innenausbau) | 08/02/2023 | 03/03/2023 | nan | nan | 40 | TK_NotStart | 1201082599 | 170 | 1201082599_170
CW37200 | TT_Task | Trainset 24 SM6 - Transport from Goerlitz to Ceska Lipa | 22/11/2022 | 22/11/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 97 | 1201082599_97
CW37500 | TT_Task | Trainset 24 SM6 - Transport from Ceska Lipa to Vienna | 22/12/2022 | 22/12/2022 | nan | nan | 136 | TK_NotStart | 1201082599 | 101 | 1201082599_101
CW37800 | TT_Task | Trainset 24 SM6 - Bonding and Waxing (Kleben und Wachs) | 17/01/2023 | 06/02/2023 | nan | nan | 0 | TK_NotStart | 1201082599 | 102 | 1201082599_102
CWS2640 | TT_Task | Trainset 24 SM6 - Customer Inspection (Haltepunkt) | 21/11/2022 | 21/11/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 98 | 1201082599_98
A238572 | TT_Task | Trainset 24 SM2 - Carbody Production (Rohbau Produktion) | 15/11/2022 | 22/11/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 108 | 1201082599_108
A238582 | TT_Task | Trainset 24 SM2 - Carbody Surface (Oberfl?che) | 25/11/2022 | 23/12/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 169 | 1201082599_169
A238592 | TT_Task | Trainset 24 SM2 - Fitout (Innenausbau) | 15/02/2023 | 10/03/2023 | nan | nan | 16 | TK_NotStart | 1201082599 | 170 | 1201082599_170
CW37210 | TT_Task | Trainset 24 SM2 - Transport from Goerlitz to Ceska Lipa | 24/11/2022 | 24/11/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 109 | 1201082599_109
CW37510 | TT_Task | Trainset 24 SM2 - Transport from Ceska Lipa to Vienna | 26/12/2022 | 26/12/2022 | nan | nan | 168 | TK_NotStart | 1201082599 | 111 | 1201082599_111
CW37810 | TT_Task | Trainset 24 SM2 - Bonding and Waxing (Kleben und Wachs) | 25/01/2023 | 14/02/2023 | nan | nan | 0 | TK_NotStart | 1201082599 | 112 | 1201082599_112
CWS2650 | TT_Task | Trainset 24 SM2 - Customer Inspection (Haltepunkt) | 23/11/2022 | 23/11/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 110 | 1201082599_110
A238632 | TT_Task | Trainset 24 BM7 - Carbody Production (Rohbau Produktion) | 10/11/2022 | 17/11/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 113 | 1201082599_113
A238642 | TT_Task | Trainset 24 BM7 - Carbody Surface (Oberfl?che) | 22/11/2022 | 20/12/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 116 | 1201082599_116
A238652 | TT_Task | Trainset 24 BM7 - Fitout (Innenausbau) | 21/02/2023 | 10/03/2023 | nan | nan | 0 | TK_NotStart | 1201082599 | 119 | 1201082599_119
CW37230 | TT_Task | Trainset 24 BM7 - Transport from Goerlitz to Ceska Lipa | 21/11/2022 | 21/11/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 114 | 1201082599_114
CW37530 | TT_Task | Trainset 24 BM7 - Transport from Ceska Lipa to Vienna | 21/12/2022 | 21/12/2022 | nan | nan | 192 | TK_NotStart | 1201082599 | 117 | 1201082599_117
CW37830 | TT_Task | Trainset 24 BM7 - Bonding and Waxing (Kleben und Wachs) | 25/01/2023 | 14/02/2023 | nan | nan | 0 | TK_NotStart | 1201082599 | 118 | 1201082599_118
CWS2670 | TT_Task | Trainset 24 BM7 - Customer Inspection (Haltepunkt) | 18/11/2022 | 18/11/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 171 | 1201082599_171
A238602 | TT_Task | Trainset 24 BM3 - Carbody Production (Rohbau Produktion) | 14/11/2022 | 21/11/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 121 | 1201082599_121
A238612 | TT_Task | Trainset 24 BM3 - Carbody Surface (Oberfl?che) | 24/11/2022 | 22/12/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 172 | 1201082599_172
A238622 | TT_Task | Trainset 24 BM3 - Fitout (Innenausbau) | 21/02/2023 | 10/03/2023 | nan | nan | 0 | TK_NotStart | 1201082599 | 173 | 1201082599_173
CW37220 | TT_Task | Trainset 24 BM3 - Transport from Goerlitz to Ceska Lipa | 23/11/2022 | 23/11/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 122 | 1201082599_122
CW37520 | TT_Task | Trainset 24 BM3 - Transport from Ceska Lipa to Vienna | 23/12/2022 | 23/12/2022 | nan | nan | 192 | TK_NotStart | 1201082599 | 124 | 1201082599_124
CW37820 | TT_Task | Trainset 24 BM3 - Bonding and Waxing (Kleben und Wachs) | 27/01/2023 | 16/02/2023 | nan | nan | 0 | TK_NotStart | 1201082599 | 125 | 1201082599_125
CWS2660 | TT_Task | Trainset 24 BM3 - Customer Inspection (Haltepunkt) | 22/11/2022 | 22/11/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 174 | 1201082599_174
A238662 | TT_Task | Trainset 24 BM1 - Carbody Production (Rohbau Produktion) | 17/11/2022 | 24/11/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 128 | 1201082599_128
A238672 | TT_Task | Trainset 24 BM1 - Carbody Surface (Oberfl?che) | 29/11/2022 | 27/12/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 172 | 1201082599_172
A238682 | TT_Task | Trainset 24 BM1 - Fitout (Innenausbau) | 22/02/2023 | 13/03/2023 | nan | nan | 8 | TK_NotStart | 1201082599 | 173 | 1201082599_173
CW37240 | TT_Task | Trainset 24 BM1 - Transport from Goerlitz to Ceska Lipa | 28/11/2022 | 28/11/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 129 | 1201082599_129
CW37540 | TT_Task | Trainset 24 BM1 - Transport from Ceska Lipa to Vienna | 28/12/2022 | 28/12/2022 | nan | nan | 192 | TK_NotStart | 1201082599 | 130 | 1201082599_130
CW37840 | TT_Task | Trainset 24 BM1 - Bonding and Waxing (Kleben und Wachs) | 01/02/2023 | 21/02/2023 | nan | nan | 0 | TK_NotStart | 1201082599 | 131 | 1201082599_131
CWS2680 | TT_Task | Trainset 24 BM1 - Customer Inspection (Haltepunkt) | 25/11/2022 | 25/11/2022 | nan | nan | 0 | TK_NotStart | 1201082599 | 171 | 1201082599_171
A238692 | TT_Task | Trainset 24 - Train Completion (Zugbildung ; Aufsetzen) | 13/03/2023 | 23/03/2023 | nan | nan | 0 | TK_NotStart | 1201082599 | 175 | 1201082599_175
A238702 | TT_Task | Trainset 24 - Static ; Dynamic Testing (IBN +Finishing) | 24/03/2023 | 07/04/2023 | nan | nan | 0 | TK_NotStart | 1201082599 | 163 | 1201082599_163
A238712 | TT_Task | Trainset 24 - Rework (Restarbeiten) | 11/04/2023 | 12/04/2023 | nan | nan | 0 | TK_NotStart | 1201082599 | 150 | 1201082599_150
A238722 | TT_Task | Trainset 24 - Customer Tests (Test beim Kunden) | 20/04/2023 | 26/04/2023 | nan | nan | 0 | TK_NotStart | 1201082599 | 152 | 1201082599_152
A238732 | TT_Task | Trainset 24 - Preliminary Customer Acceptance (Kundenabnahme) | 27/04/2023 | 28/04/2023 | nan | nan | 0 | TK_NotStart | 1201082599 | 140 | 1201082599_140
A238742 | TT_Task | Trainset 24 - Trial Period (Probebetrieb) | 01/05/2023 | 09/08/2023 | nan | nan | 0 | TK_NotStart | 1201082599 | 176 | 1201082599_176
A238752 | TT_Task | Trainset 24 - ATA notification trial operation complete and defect free (Meldung Probebetrieb bestanden und Mangelfrei) | 10/08/2023 | 14/08/2023 | nan | nan | 0 | TK_NotStart | 1201082599 | 142 | 1201082599_142
A239172 | TT_Task | Trainset 24 - Customer Factory Inspection (Werksabnahme) | 13/04/2023 | 18/04/2023 | nan | nan | 0 | TK_NotStart | 1201082599 | 151 | 1201082599_151
A239182 | TT_Task | Trainset 24 - Transport to Customer (Transport zum Kunden) | 19/04/2023 | 19/04/2023 | nan | nan | 0 | TK_NotStart | 1201082599 | 177 | 1201082599_177
PAYM12000 | TT_Task | WLB Approval to Start Trial Operation (Freigabe zum Probebetrieb) 24 | 01/05/2023 | 01/05/2023 | nan | nan | 0 | TK_NotStart | 1201082599 | 147 | 1201082599_147
FS_1070 | TT_Task | Draft Organisation | 30/01/2026 | 26/02/2026 | nan | nan | 0 | TK_NotStart | 1201082599 | 179 | 1201082599_179
FS_1090 | TT_Task | Agree scope of FSA Supply | 01/01/2026 | 30/03/2026 | nan | nan | 0 | TK_NotStart | 1201082599 | 180 | 1201082599_180
FS_1110 | TT_Task | Develop Costed Proposal | 27/02/2026 | 30/03/2026 | nan | nan | 0 | TK_NotStart | 1201082599 | 181 | 1201082599_181
FS_1060 | TT_Task | Generate Material Supply Proposal | 02/01/2026 | 26/02/2026 | nan | nan | 0 | TK_NotStart | 1201082599 | 182 | 1201082599_182
FS_1080 | TT_Task | Release Proposal for Consideration | 27/02/2026 | 26/03/2026 | nan | nan | 16 | TK_NotStart | 1201082599 | 183 | 1201082599_183
FS_1120 | TT_Task | Proposal Consideration | 31/03/2026 | 23/04/2026 | nan | nan | 0 | TK_NotStart | 1201082599 | 184 | 1201082599_184
FS_1130 | TT_Task | Finalise FSA / KPI's / Modus Operandi / Reporting etc.and incorporate VO | 24/04/2026 | 28/05/2026 | nan | nan | 0 | TK_NotStart | 1201082599 | 185 | 1201082599_185
FS_1150 | TT_Task | Mobilise Material Supply Chain | 29/05/2026 | 03/09/2026 | nan | nan | 0 | TK_NotStart | 1201082599 | 186 | 1201082599_186
FS_1170 | TT_Task | Finalise transfer of PI to FSA Technical Team | 06/10/2026 | 19/10/2026 | nan | nan | 0 | TK_NotStart | 1201082599 | 187 | 1201082599_187
FS_1210 | TT_Task | Recruit (if required) | 20/10/2026 | 30/11/2026 | nan | nan | 0 | TK_NotStart | 1201082599 | 188 | 1201082599_188
FS_1180 | TT_Task | Confirm OEM DA contact points | 06/10/2026 | 02/11/2026 | nan | nan | 0 | TK_NotStart | 1201082599 | 189 | 1201082599_189
FS_1190 | TT_Task | Review of Outstanding / emerging issues | 03/11/2026 | 06/11/2026 | nan | nan | 0 | TK_NotStart | 1201082599 | 190 | 1201082599_190
FS_1220 | TT_Task | Agree / develop support activities as required | 09/11/2026 | 25/12/2026 | nan | nan | 0 | TK_NotStart | 1201082599 | 191 | 1201082599_191
FS_1200 | TT_Task | Review of Outstanding / emerging issues | 03/11/2026 | 06/11/2026 | nan | nan | 0 | TK_NotStart | 1201082599 | 190 | 1201082599_190
FS_1230 | TT_Task | Agree / develop support activities as required | 09/11/2026 | 25/12/2026 | nan | nan | 0 | TK_NotStart | 1201082599 | 191 | 1201082599_191
FS_1000 | TT_Task | Develop Programme | 07/10/2024 | 06/01/2025 | nan | nan | 0 | TK_NotStart | 1201082599 | 192 | 1201082599_192
FS_1010 | TT_Task | Confirm Programme | 07/01/2025 | 27/01/2025 | nan | nan | 0 | TK_NotStart | 1201082599 | 193 | 1201082599_193
FS_1030 | TT_Task | Mobilise ACS Programme | 28/01/2025 | 02/06/2025 | nan | nan | 0 | TK_NotStart | 1201082599 | 194 | 1201082599_194
C720T147CF###0051140 | TT_Task | Train 01 500km Test Run (Readiness for commencement) | 08/08/2022 | 12/08/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 99 | 1112893334_99
C720T147CF###0050870 | TT_Task | Train 02 500km Test Run (Readiness for commencement) | 15/08/2022 | 19/08/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 99 | 1112893334_99
C720T147CF###0050900 | TT_Task | Train 03 500km Test Run (Readiness for commencement) | 22/08/2022 | 26/08/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 99 | 1112893334_99
C720T147CF###0050930 | TT_Task | Train 04 500km Test Run (Readiness for commencement) | 29/08/2022 | 02/09/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 99 | 1112893334_99
C720T147CF###0050940 | TT_Task | Train 05 500km Test Run (Readiness for commencement) | 05/09/2022 | 09/09/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 99 | 1112893334_99
C720T147CF###0050950 | TT_Task | Train 06 500km Test Run (Readiness for commencement) | 12/09/2022 | 16/09/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 99 | 1112893334_99
C720T147CF###0050970 | TT_Task | Train 07 500km Test Run (Readiness for commencement) | 19/09/2022 | 23/09/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 99 | 1112893334_99
C720T147CF###0050980 | TT_Task | Train 08 500km Test Run (Readiness for commencement) | 26/09/2022 | 30/09/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 99 | 1112893334_99
C720T147CF###0050990 | TT_Task | Train 09 500km Test Run (Readiness for commencement) | 03/10/2022 | 07/10/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 99 | 1112893334_99
C720T147CF###0051000 | TT_Task | Train 10 500km Test Run (Readiness for commencement) | 10/10/2022 | 14/10/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 99 | 1112893334_99
C720T147CF###0051010 | TT_Task | Train 11 500km Test Run (Readiness for commencement) | 17/10/2022 | 21/10/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 99 | 1112893334_99
C720T147CF###0051020 | TT_Task | Train 12 500km Test Run (Readiness for commencement) | 24/10/2022 | 28/10/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 99 | 1112893334_99
C720T147CF###0051030 | TT_Task | Train 13 500km Test Run (Readiness for commencement) | 31/10/2022 | 04/11/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 99 | 1112893334_99
C720T147CF###0051040 | TT_Task | Train 14 500km Test Run (Readiness for commencement) | 07/11/2022 | 11/11/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 99 | 1112893334_99
C720T147CF###0051050 | TT_Task | Train 15 500km Test Run (Readiness for commencement) | 14/11/2022 | 18/11/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 99 | 1112893334_99
C720T147CF###0051060 | TT_Task | Train 16 500km Test Run (Readiness for commencement) | 21/11/2022 | 25/11/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 99 | 1112893334_99
C720T147CF###0051070 | TT_Task | Train 17 500km Test Run (Readiness for commencement) | 28/11/2022 | 02/12/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 99 | 1112893334_99
C720T147CF###0051080 | TT_Task | Train 18 500km Test Run (Readiness for commencement) | 06/12/2022 | 12/12/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 99 | 1112893334_99
C720T147CF###0051090 | TT_Task | Train 19 500km Test Run (Readiness for commencement) | 13/12/2022 | 19/12/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 99 | 1112893334_99
C720T147CF###0051100 | TT_Task | Train 20 500km Test Run (Readiness for commencement) | 10/01/2023 | 16/01/2023 | nan | nan | 0 | TK_NotStart | 1112893334 | 99 | 1112893334_99
C720T147CF###0051110 | TT_Task | Train 21 500km Test Run (Readiness for commencement) | 31/01/2023 | 06/02/2023 | nan | nan | 0 | TK_NotStart | 1112893334 | 99 | 1112893334_99
C720T147CF###0051120 | TT_Task | Train 22 500km Test Run (Readiness for commencement) | 14/02/2023 | 20/02/2023 | nan | nan | 0 | TK_NotStart | 1112893334 | 99 | 1112893334_99
C720T147CF###0051130 | TT_Task | Train 23 500km Test Run (Readiness for commencement) | 08/03/2023 | 14/03/2023 | nan | nan | 0 | TK_NotStart | 1112893334 | 99 | 1112893334_99
C720T147CF###0050040 | TT_Task | Train 01 Train high speed dynamic test at NWRL (NTH) | 07/04/2022 | 20/04/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 98 | 1112893334_98
C720T147CF###0050120 | TT_Task | Train 02 Train high speed dynamic test at NWRL (NTH) | 20/04/2022 | 07/06/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 98 | 1112893334_98
C720T147CF###0050200 | TT_Task | Train 03 Train high speed dynamic test at NWRL (NTH) | 07/06/2022 | 29/06/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 98 | 1112893334_98
C720T147CF###0050300 | TT_Task | Train 04 Train high speed dynamic test at NWRL (NTH) | 29/06/2022 | 21/07/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 98 | 1112893334_98
C720T147CF###0050310 | TT_Task | Train 05 Train high speed dynamic test at NWRL (NTH) | 29/06/2022 | 21/07/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 98 | 1112893334_98
C720T147CF###0050340 | TT_Task | Train 06 Train high speed dynamic test at NWRL (NTH) | 21/07/2022 | 02/08/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 98 | 1112893334_98
C720T147CF###0050330 | TT_Task | Train 07 Train high speed dynamic test at NWRL (NTH) | 21/07/2022 | 02/08/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 98 | 1112893334_98
C720T147CF###0050390 | TT_Task | Train 08 Train high speed dynamic test at NWRL (NTH) | 02/08/2022 | 10/08/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 98 | 1112893334_98
C720T147CF###0050380 | TT_Task | Train 09 Train high speed dynamic test at NWRL (NTH) | 02/08/2022 | 10/08/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 98 | 1112893334_98
C720T147CF###0050420 | TT_Task | Train 10 Train high speed dynamic test at NWRL (NTH) | 10/08/2022 | 18/08/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 98 | 1112893334_98
C720T147CF###0050430 | TT_Task | Train 11 Train high speed dynamic test at NWRL (NTH) | 10/08/2022 | 18/08/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 98 | 1112893334_98
C720T147CF###0050480 | TT_Task | Train 12 Train high speed dynamic test at NWRL (NTH) | 18/08/2022 | 30/08/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 98 | 1112893334_98
C720T147CF###0050470 | TT_Task | Train 13 Train high speed dynamic test at NWRL (NTH) | 18/08/2022 | 30/08/2022 | nan | nan | 16 | TK_NotStart | 1112893334 | 98 | 1112893334_98
C720T147CF###0050520 | TT_Task | Train 14 Train high speed dynamic test at NWRL (NTH) | 13/09/2022 | 16/09/2022 | nan | nan | 9 | TK_NotStart | 1112893334 | 98 | 1112893334_98
C720T147CF###0050540 | TT_Task | Train 15 Train high speed dynamic test at NWRL (NTH) | 20/09/2022 | 23/09/2022 | nan | nan | 27 | TK_NotStart | 1112893334 | 98 | 1112893334_98
C720T147CF###0050590 | TT_Task | Train 16 Train high speed dynamic test at NWRL (NTH) | 18/10/2022 | 21/10/2022 | nan | nan | 11 | TK_NotStart | 1112893334 | 98 | 1112893334_98
C720T147CF###0050640 | TT_Task | Train 17 Train high speed dynamic test at NWRL (NTH) | 01/11/2022 | 09/11/2022 | nan | nan | 22 | TK_NotStart | 1112893334 | 98 | 1112893334_98
C720T147CF###0050690 | TT_Task | Train 18 Train high speed dynamic test at NWRL (NTH) | 29/11/2022 | 06/12/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 98 | 1112893334_98
C720T147CF###0050740 | TT_Task | Train 19 Train high speed dynamic test at NWRL (NTH) | 06/12/2022 | 13/12/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 98 | 1112893334_98
C720T147CF###0050790 | TT_Task | Train 20 Train high speed dynamic test at NWRL (NTH) | 03/01/2023 | 10/01/2023 | nan | nan | 0 | TK_NotStart | 1112893334 | 98 | 1112893334_98
C720T147CF###0050830 | TT_Task | Train 21 Train high speed dynamic test at NWRL (NTH) | 24/01/2023 | 31/01/2023 | nan | nan | 0 | TK_NotStart | 1112893334 | 98 | 1112893334_98
C720T147CF###0050860 | TT_Task | Train 22 Train high speed dynamic test at NWRL (NTH) | 07/02/2023 | 14/02/2023 | nan | nan | 0 | TK_NotStart | 1112893334 | 98 | 1112893334_98
C720T147CF###0050910 | TT_Task | Train 23 Train high speed dynamic test at NWRL (NTH) | 01/03/2023 | 08/03/2023 | nan | nan | 0 | TK_NotStart | 1112893334 | 98 | 1112893334_98
C720T147CF###0050020 | TT_Task | Train 01 Train low speed dynamic test at SMTF-[N] | 09/11/2021 | 06/12/2021 | 12/09/2021 | 20/10/2021 | 0 | TK_Complete | 1112893334 | 97 | 1112893334_97
C720T147CF###N050020 | TT_Task | Train 01 Train low speed dynamic test at SMTF-[N] (CC Dynamic Test) | 29/03/2022 | 07/04/2022 | nan | nan | 2 | TK_NotStart | 1112893334 | 97 | 1112893334_97
C720T147CF###0050050 | TT_Task | Train 02 Train low speed dynamic test at SMTF-[N] | 26/11/2021 | 23/12/2021 | 26/11/2021 | 03/12/2021 | 0 | TK_Complete | 1112893334 | 97 | 1112893334_97
C720T147CF###0050052 | TT_Task | Train 02 Train low speed dynamic test at SMTF-[N] (CC Dynamic Test) | 07/04/2022 | 13/04/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 97 | 1112893334_97
C720T147CF###0050070 | TT_Task | Train 03 Train low speed dynamic test at SMTF-[N] | 13/01/2022 | 13/01/2022 | 17/12/2021 | 23/12/2021 | 0 | TK_Complete | 1112893334 | 97 | 1112893334_97
C720T147CF###0050072 | TT_Task | Train 03 Train low speed dynamic test at SMTF-[N] (CC Dynamic Test) | 13/04/2022 | 20/04/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 97 | 1112893334_97
C720T147CF###0050100 | TT_Task | Train 04 Train low speed dynamic test at SMTF-[N] | 18/01/2022 | 07/02/2022 | 14/01/2022 | 18/01/2022 | 0 | TK_Complete | 1112893334 | 97 | 1112893334_97
C720T147CF###0050102 | TT_Task | Train 04 Train low speed dynamic test at SMTF-[N] (CC Dynamic Test) | 20/04/2022 | 27/04/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 97 | 1112893334_97
C720T147CF###0050110 | TT_Task | Train 05 Train low speed dynamic test at SMTF-[N] | 15/02/2022 | 07/03/2022 | 22/02/2022 | 04/03/2022 | 0 | TK_Complete | 1112893334 | 97 | 1112893334_97
C720T147CF###0050112 | TT_Task | Train 05 Train low speed dynamic test at SMTF-[N] (CC Dynamic Test) | 27/04/2022 | 04/05/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 97 | 1112893334_97
C720T147CF###0050130 | TT_Task | Train 06 Train low speed dynamic test at SMTF-[N] | 31/03/2022 | 06/04/2022 | 16/03/2022 | 18/04/2022 | 0 | TK_Complete | 1112893334 | 97 | 1112893334_97
C720T147CF###0050132 | TT_Task | Train 06 Train low speed dynamic test at SMTF-[N] (CC Dynamic Test) | 04/05/2022 | 11/05/2022 | nan | nan | 409 | TK_NotStart | 1112893334 | 97 | 1112893334_97
C720T147CF###0050160 | TT_Task | Train 07 Train low speed dynamic test at SMTF-[N] | 01/04/2022 | 06/04/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 97 | 1112893334_97
C720T147CF###0050180 | TT_Task | Train 08 Train low speed dynamic test at SMTF-[N] | 07/04/2022 | 14/04/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 97 | 1112893334_97
C720T147CF###0050210 | TT_Task | Train 09 Train low speed dynamic test at SMTF-[N] | 11/05/2022 | 24/05/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 97 | 1112893334_97
C720T147CF###0050250 | TT_Task | Train 10 Train low speed dynamic test at SMTF-[N] | 25/05/2022 | 07/06/2022 | nan | nan | 88 | TK_NotStart | 1112893334 | 97 | 1112893334_97
C720T147CF###0050270 | TT_Task | Train 11 Train low speed dynamic test at SMTF-[N] | 23/06/2022 | 06/07/2022 | nan | nan | 152 | TK_NotStart | 1112893334 | 97 | 1112893334_97
C720T147CF###0050290 | TT_Task | Train 12 Train low speed dynamic test at SMTF-[N] | 03/08/2022 | 09/08/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 97 | 1112893334_97
C720T147CF###0050360 | TT_Task | Train 13 Train low speed dynamic test at SMTF-[N] | 10/08/2022 | 16/08/2022 | nan | nan | 16 | TK_NotStart | 1112893334 | 97 | 1112893334_97
C720T147CF###0050440 | TT_Task | Train 14 Train low speed dynamic test at SMTF-[N] | 06/09/2022 | 12/09/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 97 | 1112893334_97
C720T147CF###0050500 | TT_Task | Train 15 Train low speed dynamic test at SMTF-[N] | 13/09/2022 | 19/09/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 97 | 1112893334_97
C720T147CF###0050560 | TT_Task | Train 16 Train low speed dynamic test at SMTF-[N] | 11/10/2022 | 17/10/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 97 | 1112893334_97
C720T147CF###0050610 | TT_Task | Train 17 Train low speed dynamic test at SMTF-[N] | 26/10/2022 | 01/11/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 97 | 1112893334_97
C720T147CF###0050660 | TT_Task | Train 18 Train low speed dynamic test at SMTF-[N] | 23/11/2022 | 29/11/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 97 | 1112893334_97
C720T147CF###0050720 | TT_Task | Train 19 Train low speed dynamic test at SMTF-[N] | 30/11/2022 | 06/12/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 97 | 1112893334_97
C720T147CF###0050770 | TT_Task | Train 20 Train low speed dynamic test at SMTF-[N] | 28/12/2022 | 03/01/2023 | nan | nan | 0 | TK_NotStart | 1112893334 | 97 | 1112893334_97
C720T147CF###0050810 | TT_Task | Train 21 Train low speed dynamic test at SMTF-[N] | 18/01/2023 | 24/01/2023 | nan | nan | 0 | TK_NotStart | 1112893334 | 97 | 1112893334_97
C720T147CF###0050850 | TT_Task | Train 22 Train low speed dynamic test at SMTF-[N] | 01/02/2023 | 07/02/2023 | nan | nan | 0 | TK_NotStart | 1112893334 | 97 | 1112893334_97
C720T147CF###0050890 | TT_Task | Train 23 Train low speed dynamic test at SMTF-[N] | 23/02/2023 | 01/03/2023 | nan | nan | 0 | TK_NotStart | 1112893334 | 97 | 1112893334_97
C720T147CF###0050000 | TT_Task | Train 01 Train Inspection ; Train static test at SMTF-[N] | 28/10/2021 | 22/12/2021 | 06/09/2021 | 12/10/2021 | 0 | TK_Complete | 1112893334 | 96 | 1112893334_96
C720T147CF###0050010 | TT_Task | Train 02 Train Inspection ; Train static test at SMTF-[N] | 14/10/2021 | 17/11/2021 | 18/10/2021 | 25/11/2021 | 0 | TK_Complete | 1112893334 | 96 | 1112893334_96
C720T147CF###0050030 | TT_Task | Train 03 Train Inspection ; Train static test at SMTF-[N] | 26/11/2021 | 30/12/2021 | 22/11/2021 | 10/12/2021 | 0 | TK_Complete | 1112893334 | 96 | 1112893334_96
C720T147CF###0050060 | TT_Task | Train 04 Train Inspection ; Train static test at SMTF-[N] | 31/12/2021 | 03/02/2022 | 02/12/2021 | 14/01/2022 | 0 | TK_Complete | 1112893334 | 96 | 1112893334_96
C720T147CF###0050080 | TT_Task | Train 05 Train Inspection ; Train static test at SMTF-[N] | 18/01/2022 | 21/02/2022 | 10/01/2022 | 10/02/2022 | 0 | TK_Complete | 1112893334 | 96 | 1112893334_96
C720T147CF###0050090 | TT_Task | Train 06 Train Inspection ; Train static test at SMTF-[N] | 22/02/2022 | 28/03/2022 | 17/01/2022 | 15/03/2022 | 0 | TK_Complete | 1112893334 | 96 | 1112893334_96
C720T147CF###0050140 | TT_Task | Train 07 Train Inspection ; Train static test at SMTF-[N] | 04/03/2022 | 07/04/2022 | 05/03/2022 | nan | 0 | TK_Active | 1112893334 | 96 | 1112893334_96
C720T147CF###0050170 | TT_Task | Train 08 Train Inspection ; Train static test at SMTF-[N] | 31/03/2022 | 04/05/2022 | 05/03/2022 | nan | 0 | TK_Active | 1112893334 | 96 | 1112893334_96
C720T147CF###0050190 | TT_Task | Train 09 Train Inspection ; Train static test at SMTF-[N] | 06/04/2022 | 10/05/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 96 | 1112893334_96
C720T147CF###0050220 | TT_Task | Train 10 Train Inspection ; Train static test at SMTF-[N] | 06/04/2022 | 18/05/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 96 | 1112893334_96
C720T147CF###0050240 | TT_Task | Train 11 Train Inspection ; Train static test at SMTF-[N] | 19/05/2022 | 22/06/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 96 | 1112893334_96
C720T147CF###0050260 | TT_Task | Train 12 Train Inspection ; Train static test at SMTF-[N] | 29/06/2022 | 02/08/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 96 | 1112893334_96
C720T147CF###0050280 | TT_Task | Train 13 Train Inspection ; Train static test at SMTF-[N] | 06/07/2022 | 09/08/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 96 | 1112893334_96
C720T147CF###0050320 | TT_Task | Train 14 Train Inspection ; Train static test at SMTF-[N] | 02/08/2022 | 05/09/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 96 | 1112893334_96
C720T147CF###0050370 | TT_Task | Train 15 Train Inspection ; Train static test at SMTF-[N] | 09/08/2022 | 12/09/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 96 | 1112893334_96
C720T147CF###0050450 | TT_Task | Train 16 Train Inspection ; Train static test at SMTF-[N] | 06/09/2022 | 10/10/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 96 | 1112893334_96
C720T147CF###0050510 | TT_Task | Train 17 Train Inspection ; Train static test at SMTF-[N] | 21/09/2022 | 25/10/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 96 | 1112893334_96
C720T147CF###0050570 | TT_Task | Train 18 Train Inspection ; Train static test at SMTF-[N] | 19/10/2022 | 22/11/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 96 | 1112893334_96
C720T147CF###0050630 | TT_Task | Train 19 Train Inspection ; Train static test at SMTF-[N] | 26/10/2022 | 29/11/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 96 | 1112893334_96
C720T147CF###0050680 | TT_Task | Train 20 Train Inspection ; Train static test at SMTF-[N] | 23/11/2022 | 27/12/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 96 | 1112893334_96
C720T147CF###0050730 | TT_Task | Train 21 Train Inspection ; Train static test at SMTF-[N] | 14/12/2022 | 17/01/2023 | nan | nan | 0 | TK_NotStart | 1112893334 | 96 | 1112893334_96
C720T147CF###0050780 | TT_Task | Train 22 Train Inspection ; Train static test at SMTF-[N] | 28/12/2022 | 31/01/2023 | nan | nan | 0 | TK_NotStart | 1112893334 | 96 | 1112893334_96
C720T147CF###0050820 | TT_Task | Train 23 Train Inspection ; Train static test at SMTF-[N] | 19/01/2023 | 22/02/2023 | nan | nan | 0 | TK_NotStart | 1112893334 | 96 | 1112893334_96
C720T147CF###0051530 | TT_Task | Alstom review of testing proceduces, permits and other preliminaries prior to testing | 27/09/2021 | 27/10/2021 | 06/09/2021 | 13/09/2021 | 0 | TK_Complete | 1112893334 | 95 | 1112893334_95
C720C147CF###0040870 | TT_Task | Train 13 - Fitting | 23/02/2022 | 03/05/2022 | 02/12/2021 | 28/12/2021 | 0 | TK_Complete | 1112893334 | 94 | 1112893334_94
C720C147CF###0040950 | TT_Task | Train 14 - Fitting | 25/03/2022 | 02/06/2022 | 15/12/2021 | 24/01/2022 | 0 | TK_Complete | 1112893334 | 94 | 1112893334_94
C720C147CF###0041010 | TT_Task | Train 15 - Fitting | 03/01/2022 | 11/03/2022 | 07/01/2022 | 16/02/2022 | 0 | TK_Complete | 1112893334 | 94 | 1112893334_94
C720C147CF###0041080 | TT_Task | Train 16 - Fitting | 08/02/2022 | 11/04/2022 | 30/01/2022 | 28/02/2022 | 0 | TK_Complete | 1112893334 | 94 | 1112893334_94
C720C147CF###0041180 | TT_Task | Train 17 - Fitting | 08/02/2022 | 11/04/2022 | 11/02/2022 | 11/03/2022 | 0 | TK_Complete | 1112893334 | 94 | 1112893334_94
C720C147CF###0041270 | TT_Task | Train 18 - Fitting | 07/03/2022 | 06/05/2022 | 09/03/2022 | nan | 0 | TK_Active | 1112893334 | 94 | 1112893334_94
C720C147CF###0041360 | TT_Task | Train 19 - Fitting | 11/03/2022 | 12/05/2022 | 09/03/2022 | nan | 0 | TK_Active | 1112893334 | 94 | 1112893334_94
C720C147CF###0041440 | TT_Task | Train 20 - Fitting | 04/04/2022 | 03/06/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 94 | 1112893334_94
C720C147CF###0041520 | TT_Task | Train 21 - Fitting | 11/04/2022 | 10/06/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 94 | 1112893334_94
C720C147CF###0041560 | TT_Task | Train 22 - Pre-Fitting | 18/04/2022 | 10/06/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 94 | 1112893334_94
C720C147CF###0041600 | TT_Task | Train 22 - Fitting | 02/05/2022 | 01/07/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 94 | 1112893334_94
C720C147CF###0041640 | TT_Task | Train 23 - Pre-Fitting | 09/05/2022 | 01/07/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 94 | 1112893334_94
C720C147CF###0041670 | TT_Task | Train 23 - Fitting | 23/05/2022 | 22/07/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 94 | 1112893334_94
C720C147CF###0040850 | TT_Task | Train 13 - Pre-Fitting | 08/11/2021 | 07/01/2022 | 25/11/2021 | 14/12/2021 | 0 | TK_Complete | 1112893334 | 93 | 1112893334_93
C720C147CF###0040900 | TT_Task | Train 14 - Pre-Fitting | 02/12/2021 | 02/02/2022 | 08/12/2021 | 20/12/2021 | 0 | TK_Complete | 1112893334 | 93 | 1112893334_93
C720C147CF###0040990 | TT_Task | Train 15 - Pre-Fitting | 27/12/2021 | 25/02/2022 | 27/12/2021 | 21/01/2022 | 0 | TK_Complete | 1112893334 | 93 | 1112893334_93
C720C147CF###0041050 | TT_Task | Train 16 - Pre-Fitting | 25/01/2022 | 21/03/2022 | 28/01/2022 | 09/02/2022 | 0 | TK_Complete | 1112893334 | 93 | 1112893334_93
C720C147CF###0041130 | TT_Task | Train 17 - Pre-Fitting | 25/01/2022 | 21/03/2022 | 05/02/2022 | 21/02/2022 | 0 | TK_Complete | 1112893334 | 93 | 1112893334_93
C720C147CF###0041250 | TT_Task | Train 18 - Pre-Fitting | 11/02/2022 | 07/04/2022 | 19/02/2022 | 09/03/2022 | 0 | TK_Complete | 1112893334 | 93 | 1112893334_93
C720C147CF###0041340 | TT_Task | Train 19 - Pre-Fitting | 25/02/2022 | 21/04/2022 | 07/03/2022 | 24/03/2022 | 0 | TK_Complete | 1112893334 | 93 | 1112893334_93
C720C147CF###0041390 | TT_Task | Train 20 - Pre-Fitting | 11/03/2022 | 05/05/2022 | 19/03/2022 | nan | 0 | TK_Active | 1112893334 | 93 | 1112893334_93
C720C147CF###0041500 | TT_Task | Train 21 - Pre-Fitting | 28/03/2022 | 20/05/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 93 | 1112893334_93
C720C147CF###0041030 | TT_Task | Train 10 - Shipment+delivery to SMTF depot | 16/02/2022 | 10/05/2022 | 29/01/2022 | nan | 0 | TK_Active | 1112893334 | 92 | 1112893334_92
C720C147CF###0041120 | TT_Task | Train 11 - Shipment+delivery to SMTF depot | 21/02/2022 | 13/05/2022 | 18/02/2022 | nan | 0 | TK_Active | 1112893334 | 92 | 1112893334_92
C720C147CF###0041160 | TT_Task | Train 12 - Shipment+delivery to SMTF depot | 06/04/2022 | 28/06/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 92 | 1112893334_92
C720C147CF###0041230 | TT_Task | Train 13 - Shipment+delivery to SMTF depot | 06/04/2022 | 28/06/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 92 | 1112893334_92
C720C147CF###0041310 | TT_Task | Train 14 - Shipment+delivery to SMTF depot | 06/04/2022 | 28/06/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 92 | 1112893334_92
C720C147CF###0041380 | TT_Task | Train 15 - Shipment+delivery to SMTF depot | 06/04/2022 | 28/06/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 92 | 1112893334_92
C720C147CF###0041460 | TT_Task | Train 16 - Shipment+delivery to SMTF depot | 18/04/2022 | 08/07/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 92 | 1112893334_92
C720C147CF###0041550 | TT_Task | Train 17 - Shipment+delivery to SMTF depot | 29/06/2022 | 20/09/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 92 | 1112893334_92
C720C147CF###0041620 | TT_Task | Train 18 - Shipment+delivery to SMTF depot | 29/06/2022 | 20/09/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 92 | 1112893334_92
C720C147CF###0041730 | TT_Task | Train 19 - Shipment+delivery to SMTF depot | 29/06/2022 | 20/09/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 92 | 1112893334_92
C720C147CF###0041810 | TT_Task | Train 20 - Shipment+delivery to SMTF depot | 18/07/2022 | 07/10/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 92 | 1112893334_92
C720C147CF###0041900 | TT_Task | Train 21 - Shipment+delivery to SMTF depot | 21/09/2022 | 13/12/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 92 | 1112893334_92
C720C147CF###0041980 | TT_Task | Train 22 - Shipment+delivery to SMTF depot | 21/09/2022 | 13/12/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 92 | 1112893334_92
C720C147CF###0042050 | TT_Task | Train 23 - Shipment+delivery to SMTF depot | 27/10/2022 | 18/01/2023 | nan | nan | 0 | TK_NotStart | 1112893334 | 92 | 1112893334_92
C720C147CF###0040960 | TT_Task | Train 10 - Preparation | 27/12/2021 | 07/01/2022 | 22/12/2021 | 28/01/2022 | 0 | TK_Complete | 1112893334 | 91 | 1112893334_91
C720C147CF###0041060 | TT_Task | Train 11 - Preparation | 03/01/2022 | 14/01/2022 | 20/01/2022 | 17/02/2022 | 0 | TK_Complete | 1112893334 | 91 | 1112893334_91
C720C147CF###0041100 | TT_Task | Train 12 - Preparation | 28/01/2022 | 10/02/2022 | 28/01/2022 | 28/02/2022 | 0 | TK_Complete | 1112893334 | 91 | 1112893334_91
C720C147CF###0041200 | TT_Task | Train 13 - Preparation | 11/02/2022 | 24/02/2022 | 18/02/2022 | 08/03/2022 | 0 | TK_Complete | 1112893334 | 91 | 1112893334_91
C720C147CF###0041280 | TT_Task | Train 14 - Preparation | 07/03/2022 | 18/03/2022 | 07/03/2022 | 21/03/2022 | 0 | TK_Complete | 1112893334 | 91 | 1112893334_91
C720C147CF###0041350 | TT_Task | Train 15 - Preparation | 22/03/2022 | 04/04/2022 | 22/03/2022 | nan | 0 | TK_Active | 1112893334 | 91 | 1112893334_91
C720C147CF###0041430 | TT_Task | Train 16 - Preparation | 04/04/2022 | 15/04/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 91 | 1112893334_91
C720C147CF###0041510 | TT_Task | Train 17 - Preparation | 18/04/2022 | 29/04/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 91 | 1112893334_91
C720C147CF###0041590 | TT_Task | Train 18 - Preparation | 16/05/2022 | 27/05/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 91 | 1112893334_91
C720C147CF###0041680 | TT_Task | Train 19 - Preparation | 30/05/2022 | 10/06/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 91 | 1112893334_91
C720C147CF###0041760 | TT_Task | Train 20 - Preparation | 04/07/2022 | 15/07/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 91 | 1112893334_91
C720C147CF###0041840 | TT_Task | Train 21 - Preparartion | 25/07/2022 | 05/08/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 91 | 1112893334_91
C720C147CF###0041920 | TT_Task | Train 22 - Preparation | 08/08/2022 | 19/08/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 91 | 1112893334_91
C720C147CF###0042000 | TT_Task | Train 23 - Preparation | 13/10/2022 | 26/10/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 91 | 1112893334_91
C720C147CF###0040860 | TT_Task | Train 10 - Routine Test | 30/11/2021 | 03/01/2022 | 02/11/2021 | 10/12/2021 | 0 | TK_Complete | 1112893334 | 90 | 1112893334_90
C720C147CF###0040940 | TT_Task | Train 11 - Routine Test | 30/12/2021 | 26/01/2022 | 06/12/2021 | 10/01/2022 | 0 | TK_Complete | 1112893334 | 90 | 1112893334_90
C720C147CF###0040970 | TT_Task | Train 12 - Routine Test | 31/01/2022 | 25/02/2022 | 29/12/2021 | 04/02/2022 | 0 | TK_Complete | 1112893334 | 90 | 1112893334_90
C720C147CF###0041090 | TT_Task | Train 13 - Routine Test | 14/02/2022 | 11/03/2022 | 10/01/2022 | 17/02/2022 | 0 | TK_Complete | 1112893334 | 90 | 1112893334_90
C720C147CF###0041190 | TT_Task | Train 14 - Routine Test | 25/01/2022 | 21/02/2022 | 28/01/2022 | 05/03/2022 | 0 | TK_Complete | 1112893334 | 90 | 1112893334_90
C720C147CF###0041260 | TT_Task | Train 15 - Routine Test | 08/03/2022 | 04/04/2022 | 21/02/2022 | 11/03/2022 | 0 | TK_Complete | 1112893334 | 90 | 1112893334_90
C720C147CF###0041320 | TT_Task | Train 16 - Routine Test | 07/03/2022 | 01/04/2022 | 05/03/2022 | nan | 0 | TK_Active | 1112893334 | 90 | 1112893334_90
C720C147CF###0041410 | TT_Task | Train 17 - Routine Test | 28/03/2022 | 22/04/2022 | 18/03/2022 | nan | 0 | TK_Active | 1112893334 | 90 | 1112893334_90
C720C147CF###0041470 | TT_Task | Train 18 - Routine Test | 18/04/2022 | 13/05/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 90 | 1112893334_90
C720C147CF###0041580 | TT_Task | Train 19 - Routine Test | 02/05/2022 | 27/05/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 90 | 1112893334_90
C720C147CF###0041660 | TT_Task | Train 20 - Routine Test | 06/06/2022 | 01/07/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 90 | 1112893334_90
C720C147CF###0041740 | TT_Task | Train 21 - Routine Test | 27/06/2022 | 22/07/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 90 | 1112893334_90
C720C147CF###0041820 | TT_Task | Train 22 - Routine Test | 11/07/2022 | 05/08/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 90 | 1112893334_90
C720C147CF###0041890 | TT_Task | Train 23 - Routine Test | 08/08/2022 | 02/09/2022 | nan | nan | 224 | TK_NotStart | 1112893334 | 90 | 1112893334_90
C720D147CF###0020150 | TT_Task | Trains/Stage-2 - Consolidate and submit the initial DIS and DITP for RS to TRK/OHW/TRS/SMTF[S]/PSD/RAD/SIG - Phase 1 | 01/07/2019 | 20/09/2019 | 01/04/2019 | 07/06/2019 | 0 | TK_Complete | 1112893334 | 9 | 1112893334_9
C720D147CF###0020200 | TT_Task | Trains/Stage-2 - Consolidate and submit the final DIS and DITP for RS to TRK/OHW/TRS/SMTF[S]/PSD/RAD/SIG - Phase 1 | 01/07/2019 | 20/09/2019 | 17/06/2019 | 09/12/2019 | 0 | TK_Complete | 1112893334 | 9 | 1112893334_9
C720D147CF###0021530 | TT_Task | Trains/Stage-2 - Consolidate and submit the initial DIS and DITP for RS to SIG/SWTRK/SWOHW/SWPSD/LWC/RAD - Phase 2 | 05/03/2020 | 14/04/2020 | 13/12/2019 | 02/04/2020 | 0 | TK_Complete | 1112893334 | 9 | 1112893334_9
C720D147CF###0021540 | TT_Task | Trains/Stage-2 - Consolidate and submit the final DIS and DITP for RS to SIG/SWTRK/SWOHW/SWPSD/LWC/RAD - Phase 2 | 18/06/2020 | 19/08/2020 | 03/04/2020 | 30/07/2020 | 0 | TK_Complete | 1112893334 | 9 | 1112893334_9
C720D147CF###0021570 | TT_Task | Trains/Stage-2 - Consolidate and submit the final DIS and DITP for RS to RS/SMTF,RAD/RS,SIG/RS,RS/OHW ; TRS,RS/TRK | 17/06/2019 | 06/09/2019 | 17/06/2019 | 09/12/2019 | 0 | TK_Complete | 1112893334 | 9 | 1112893334_9
C720C147CF###0040690 | TT_Task | Train 10 - Bogie | 10/11/2021 | 21/12/2021 | 01/10/2021 | 22/10/2021 | 0 | TK_Complete | 1112893334 | 89 | 1112893334_89
C720C147CF###0040800 | TT_Task | Train 11 - Bogie | 17/11/2021 | 28/12/2021 | 26/10/2021 | 16/11/2021 | 0 | TK_Complete | 1112893334 | 89 | 1112893334_89
C720C147CF###0040830 | TT_Task | Train 12 - Bogie | 14/02/2022 | 25/03/2022 | 17/11/2021 | 13/12/2021 | 0 | TK_Complete | 1112893334 | 89 | 1112893334_89
C720C147CF###0040910 | TT_Task | Train 13 - Bogie | 16/03/2022 | 26/04/2022 | 10/12/2021 | 24/12/2021 | 0 | TK_Complete | 1112893334 | 89 | 1112893334_89
C720C147CF###0040980 | TT_Task | Train 14 - Bogie | 29/12/2021 | 08/02/2022 | 20/12/2021 | 17/01/2022 | 0 | TK_Complete | 1112893334 | 89 | 1112893334_89
C720C147CF###0041040 | TT_Task | Train 15 - Bogie | 25/01/2022 | 07/03/2022 | 12/01/2022 | 10/02/2022 | 0 | TK_Complete | 1112893334 | 89 | 1112893334_89
C720C147CF###0041170 | TT_Task | Train 16 - Bogie | 22/02/2022 | 04/04/2022 | 05/02/2022 | 24/02/2022 | 0 | TK_Complete | 1112893334 | 89 | 1112893334_89
C720C147CF###0041210 | TT_Task | Train 17 - Bogie | 22/02/2022 | 04/04/2022 | 14/02/2022 | 04/03/2022 | 0 | TK_Complete | 1112893334 | 89 | 1112893334_89
C720C147CF###0041290 | TT_Task | Train 18 - Bogie | 14/03/2022 | 22/04/2022 | 04/03/2022 | 21/03/2022 | 0 | TK_Complete | 1112893334 | 89 | 1112893334_89
C720C147CF###0041400 | TT_Task | Train 19 - Bogie | 25/03/2022 | 05/05/2022 | 11/03/2022 | nan | 0 | TK_Active | 1112893334 | 89 | 1112893334_89
C720C147CF###0041480 | TT_Task | Train 20 - Bogie | 18/04/2022 | 27/05/2022 | nan | nan | 40 | TK_NotStart | 1112893334 | 89 | 1112893334_89
C720C147CF###0041570 | TT_Task | Train 21 - Bogie | 25/04/2022 | 03/06/2022 | nan | nan | 120 | TK_NotStart | 1112893334 | 89 | 1112893334_89
C720C147CF###0041650 | TT_Task | Train 22 - Bogie | 16/05/2022 | 24/06/2022 | nan | nan | 80 | TK_NotStart | 1112893334 | 89 | 1112893334_89
C720C147CF###0041700 | TT_Task | Train 23 - Bogie | 06/06/2022 | 15/07/2022 | nan | nan | 120 | TK_NotStart | 1112893334 | 89 | 1112893334_89
C720C147CF###0040580 | TT_Task | Train 10 - Pre-Fitting | 27/09/2021 | 03/12/2021 | 15/09/2021 | 01/10/2021 | 0 | TK_Complete | 1112893334 | 88 | 1112893334_88
C720C147CF###0040640 | TT_Task | Train 10 - Fitting | 27/10/2021 | 04/01/2022 | 27/09/2021 | 29/10/2021 | 0 | TK_Complete | 1112893334 | 88 | 1112893334_88
C720C147CF###0040680 | TT_Task | Train 11 - Pre-Fitting | 27/09/2021 | 03/12/2021 | 27/09/2021 | 19/10/2021 | 0 | TK_Complete | 1112893334 | 88 | 1112893334_88
C720C147CF###0040720 | TT_Task | Train 11 - Fitting | 27/10/2021 | 04/01/2022 | 12/10/2021 | 26/11/2021 | 0 | TK_Complete | 1112893334 | 88 | 1112893334_88
C720C147CF###0040750 | TT_Task | Train 12 - Pre-Fitting | 25/10/2021 | 24/12/2021 | 26/10/2021 | 23/11/2021 | 0 | TK_Complete | 1112893334 | 88 | 1112893334_88
C720C147CF###0040790 | TT_Task | Train 12 - Fitting | 24/01/2022 | 01/04/2022 | 08/11/2021 | 22/12/2021 | 0 | TK_Complete | 1112893334 | 88 | 1112893334_88
C720C147CF###0040500 | TT_Task | Train 10 - Carbodyshell | 25/08/2021 | 02/11/2021 | 10/08/2021 | 01/09/2021 | 0 | TK_Complete | 1112893334 | 87 | 1112893334_87
C720C147CF###0040590 | TT_Task | Train 11 - Carbodyshell | 27/09/2021 | 03/12/2021 | 27/08/2021 | 27/09/2021 | 0 | TK_Complete | 1112893334 | 87 | 1112893334_87
C720C147CF###0040700 | TT_Task | Train 12 - Carbodyshell | 27/09/2021 | 26/11/2021 | 27/09/2021 | 26/10/2021 | 0 | TK_Complete | 1112893334 | 87 | 1112893334_87
C720C147CF###0040760 | TT_Task | Train 13 - Carbodyshell | 25/10/2021 | 24/12/2021 | 25/10/2021 | 16/11/2021 | 0 | TK_Complete | 1112893334 | 87 | 1112893334_87
C720C147CF###0040840 | TT_Task | Train 14 - Carbodyshell | 22/11/2021 | 21/01/2022 | 18/11/2021 | 10/12/2021 | 0 | TK_Complete | 1112893334 | 87 | 1112893334_87
C720C147CF###0040890 | TT_Task | Train 15 - Carbodyshell | 09/12/2021 | 09/02/2022 | 01/12/2021 | 26/12/2021 | 0 | TK_Complete | 1112893334 | 87 | 1112893334_87
C720C147CF###0041000 | TT_Task | Train 16 - Carbodyshell | 27/12/2021 | 18/02/2022 | 22/12/2021 | 14/01/2022 | 0 | TK_Complete | 1112893334 | 87 | 1112893334_87
C720C147CF###0041070 | TT_Task | Train 17 - Carbodyshell | 17/01/2022 | 11/03/2022 | 07/01/2022 | 28/01/2022 | 0 | TK_Complete | 1112893334 | 87 | 1112893334_87
C720C147CF###0041140 | TT_Task | Train 18 - Carbodyshell | 28/01/2022 | 24/03/2022 | 27/01/2022 | 17/02/2022 | 0 | TK_Complete | 1112893334 | 87 | 1112893334_87
C720C147CF###0041240 | TT_Task | Train 19 - Carbodyshell | 08/02/2022 | 04/04/2022 | 02/02/2022 | 10/03/2022 | 0 | TK_Complete | 1112893334 | 87 | 1112893334_87
C720C147CF###0041330 | TT_Task | Train 20 - Carbodyshell | 25/02/2022 | 21/04/2022 | 25/02/2022 | 17/03/2022 | 0 | TK_Complete | 1112893334 | 87 | 1112893334_87
C720C147CF###0041420 | TT_Task | Train 21 - Carbodyshell | 18/03/2022 | 12/05/2022 | 12/03/2022 | nan | 0 | TK_Active | 1112893334 | 87 | 1112893334_87
C720C147CF###0041490 | TT_Task | Train 22 - Carbodyshell | 04/04/2022 | 27/05/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 87 | 1112893334_87
C720C147CF###0041540 | TT_Task | Train 23 - Carbodyshell | 25/04/2022 | 17/06/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 87 | 1112893334_87
C720C147CF###0040280 | TT_Task | Train 01 - Shipment+delivery to SMTF depot | 25/05/2021 | 16/08/2021 | 04/05/2021 | 30/08/2021 | 0 | TK_Complete | 1112893334 | 86 | 1112893334_86
C720C147CF###0040370 | TT_Task | Train 02 - Shipment+delivery to SMTF depot (Train stored at port and ship together Train03;04) | 27/09/2021 | 17/12/2021 | 30/08/2021 | 08/10/2021 | 0 | TK_Complete | 1112893334 | 86 | 1112893334_86
C720C147CF###0040420 | TT_Task | Train 03 - Shipment+delivery to SMTF depot (Train stored at port and ship together Train02;04) | 27/09/2021 | 17/12/2021 | 30/08/2021 | 15/10/2021 | 0 | TK_Complete | 1112893334 | 86 | 1112893334_86
C720C147CF###0040540 | TT_Task | Train 04 - Shipment+delivery to SMTF depot (Train stored at port and ship together Train02;03) | 27/09/2021 | 17/12/2021 | 30/08/2021 | 20/10/2021 | 0 | TK_Complete | 1112893334 | 86 | 1112893334_86
C720C147CF###0040610 | TT_Task | Train 05 - Shipment+delivery to SMTF depot | 04/10/2021 | 24/12/2021 | 01/10/2021 | 07/01/2022 | 0 | TK_Complete | 1112893334 | 86 | 1112893334_86
C720C147CF###0040660 | TT_Task | Train 06 - Shipment+delivery to SMTF depot | 04/10/2021 | 24/12/2021 | 14/10/2021 | 12/01/2022 | 0 | TK_Complete | 1112893334 | 86 | 1112893334_86
C720C147CF###0040740 | TT_Task | Train 07 - Shipment+delivery to SMTF depot | 01/12/2021 | 22/02/2022 | 03/12/2021 | 16/02/2022 | 0 | TK_Complete | 1112893334 | 86 | 1112893334_86
C720C147CF###0040820 | TT_Task | Train 08 - Shipment+delivery to SMTF depot | 14/12/2021 | 07/03/2022 | 20/12/2021 | 16/02/2022 | 0 | TK_Complete | 1112893334 | 86 | 1112893334_86
C720C147CF###0040930 | TT_Task | Train 09 - Shipment+delivery to SMTF depot | 25/01/2022 | 18/04/2022 | 06/01/2022 | nan | 0 | TK_Active | 1112893334 | 86 | 1112893334_86
C720C147CF###0040220 | TT_Task | Train 01 - Preparation | 27/04/2021 | 10/05/2021 | 12/04/2021 | 30/04/2021 | 0 | TK_Complete | 1112893334 | 85 | 1112893334_85
C720C147CF###0040320 | TT_Task | Train 02 - Preparation | 01/06/2021 | 14/06/2021 | 26/04/2021 | 18/06/2021 | 0 | TK_Complete | 1112893334 | 85 | 1112893334_85
C720C147CF###0040380 | TT_Task | Train 03 - Preparation | 25/06/2021 | 08/07/2021 | 01/06/2021 | 15/07/2021 | 0 | TK_Complete | 1112893334 | 85 | 1112893334_85
C720C147CF###0040480 | TT_Task | Train 04 - Preparation | 28/07/2021 | 10/08/2021 | 05/07/2021 | 11/08/2021 | 0 | TK_Complete | 1112893334 | 85 | 1112893334_85
C720C147CF###0040550 | TT_Task | Train 05 - Preparation | 01/09/2021 | 14/09/2021 | 10/08/2021 | 09/09/2021 | 0 | TK_Complete | 1112893334 | 85 | 1112893334_85
C720C147CF###0040630 | TT_Task | Train 06 - Preparation | 29/09/2021 | 12/10/2021 | 13/09/2021 | 12/10/2021 | 0 | TK_Complete | 1112893334 | 85 | 1112893334_85
C720C147CF###0040710 | TT_Task | Train 07 - Preparation | 27/09/2021 | 08/10/2021 | 14/10/2021 | 01/12/2021 | 0 | TK_Complete | 1112893334 | 85 | 1112893334_85
C720C147CF###0040780 | TT_Task | Train 08 - Preparation | 01/11/2021 | 12/11/2021 | 15/11/2021 | 13/12/2021 | 0 | TK_Complete | 1112893334 | 85 | 1112893334_85
C720C147CF###0040880 | TT_Task | Train 09 - Preparation | 01/12/2021 | 14/12/2021 | 02/12/2021 | 27/12/2021 | 0 | TK_Complete | 1112893334 | 85 | 1112893334_85
C720C147CF###0040180 | TT_Task | Train 01 - Validation Test | 25/03/2021 | 31/03/2021 | 16/03/2021 | 09/04/2021 | 0 | TK_Complete | 1112893334 | 84 | 1112893334_84
C720C147CF###0040250 | TT_Task | Train 02 - Validation Test - ***N/A | 25/03/2021 | 07/04/2021 | 24/03/2021 | 25/03/2021 | 0 | TK_Complete | 1112893334 | 84 | 1112893334_84
C720T147CF###N51538 | TT_Task | Train 01 Validation tests Non-UTO | 27/12/2021 | 31/12/2021 | 22/10/2021 | 08/02/2022 | 0 | TK_Complete | 1112893334 | 84 | 1112893334_84
C720T147CF###N51540 | TT_Task | Train 01 Validation tests UTO mode | 29/03/2022 | 19/05/2022 | nan | nan | 30 | TK_NotStart | 1112893334 | 84 | 1112893334_84
C720C147CF###0040120 | TT_Task | Train 01 - Routine Test | 05/03/2021 | 08/04/2021 | 01/02/2021 | 15/03/2021 | 0 | TK_Complete | 1112893334 | 83 | 1112893334_83
C720C147CF###0040160 | TT_Task | Train 02 - Routine Test | 30/04/2021 | 03/06/2021 | 25/02/2021 | 14/05/2021 | 0 | TK_Complete | 1112893334 | 83 | 1112893334_83
C720C147CF###0040290 | TT_Task | Train 03 - Routine Test | 25/03/2021 | 28/04/2021 | 24/03/2021 | 28/05/2021 | 0 | TK_Complete | 1112893334 | 83 | 1112893334_83
C720C147CF###0040400 | TT_Task | Train 04 - Routine Test | 07/05/2021 | 10/06/2021 | 07/05/2021 | 28/07/2021 | 0 | TK_Complete | 1112893334 | 83 | 1112893334_83
C720C147CF###0040460 | TT_Task | Train 05 - Routine Test | 25/06/2021 | 29/07/2021 | 25/06/2021 | 30/08/2021 | 0 | TK_Complete | 1112893334 | 83 | 1112893334_83
C720C147CF###0040490 | TT_Task | Train 06 - Routine Test | 26/08/2021 | 29/09/2021 | 26/07/2021 | 23/08/2021 | 0 | TK_Complete | 1112893334 | 83 | 1112893334_83
C720C147CF###0040570 | TT_Task | Train 07 - Routine Test | 30/08/2021 | 01/10/2021 | 05/08/2021 | 13/09/2021 | 0 | TK_Complete | 1112893334 | 83 | 1112893334_83
C720C147CF###0040670 | TT_Task | Train 08 - Routine Test | 01/10/2021 | 04/11/2021 | 06/09/2021 | 18/10/2021 | 0 | TK_Complete | 1112893334 | 83 | 1112893334_83
C720C147CF###0040770 | TT_Task | Train 09 - Routine Test | 22/10/2021 | 25/11/2021 | 04/10/2021 | 01/12/2021 | 0 | TK_Complete | 1112893334 | 83 | 1112893334_83
C720C147CF###0040060 | TT_Task | Train 01 - Bogie | 18/03/2021 | 12/05/2021 | 15/12/2020 | 24/01/2021 | 0 | TK_Complete | 1112893334 | 82 | 1112893334_82
C720C147CF###0040090 | TT_Task | Train 02 - Bogie | 25/02/2021 | 21/04/2021 | 20/01/2021 | 17/02/2021 | 0 | TK_Complete | 1112893334 | 82 | 1112893334_82
C720C147CF###0040150 | TT_Task | Train 03 - Bogie | 22/04/2021 | 02/06/2021 | 17/02/2021 | 10/03/2021 | 0 | TK_Complete | 1112893334 | 82 | 1112893334_82
C720C147CF###0040210 | TT_Task | Train 04 - Bogie | 08/06/2021 | 19/07/2021 | 26/02/2021 | 09/04/2021 | 0 | TK_Complete | 1112893334 | 82 | 1112893334_82
C720C147CF###0040310 | TT_Task | Train 05 - Bogie | 24/05/2021 | 02/07/2021 | 05/04/2021 | 10/05/2021 | 0 | TK_Complete | 1112893334 | 82 | 1112893334_82
C720C147CF###0040350 | TT_Task | Train 06 - Bogie | 30/06/2021 | 10/08/2021 | 28/05/2021 | 12/07/2021 | 0 | TK_Complete | 1112893334 | 82 | 1112893334_82
C720C147CF###0040450 | TT_Task | Train 07 - Bogie | 20/08/2021 | 30/09/2021 | 28/06/2021 | 22/07/2021 | 0 | TK_Complete | 1112893334 | 82 | 1112893334_82
C720C147CF###0040520 | TT_Task | Train 08 - Bogie | 30/08/2021 | 08/10/2021 | 26/07/2021 | 28/08/2021 | 0 | TK_Complete | 1112893334 | 82 | 1112893334_82
C720C147CF###0040620 | TT_Task | Train 09 - Bogie | 29/09/2021 | 09/11/2021 | 23/08/2021 | 17/09/2021 | 0 | TK_Complete | 1112893334 | 82 | 1112893334_82
C720C147CF###0040020 | TT_Task | Train 01 - Pre-Fitting | 28/01/2021 | 21/04/2021 | 24/11/2020 | 15/12/2020 | 0 | TK_Complete | 1112893334 | 81 | 1112893334_81
C720C147CF###0040030 | TT_Task | Train 01 - Fitting | 18/02/2021 | 12/05/2021 | 02/12/2020 | 30/01/2021 | 0 | TK_Complete | 1112893334 | 81 | 1112893334_81
C720C147CF###0040040 | TT_Task | Train 02 - Pre-Fitting | 25/01/2021 | 30/04/2021 | 01/01/2021 | 19/01/2021 | 0 | TK_Complete | 1112893334 | 81 | 1112893334_81
C720C147CF###0040070 | TT_Task | Train 02 - Fitting | 15/02/2021 | 21/05/2021 | 12/01/2021 | 23/02/2021 | 0 | TK_Complete | 1112893334 | 81 | 1112893334_81
C720C147CF###0040100 | TT_Task | Train 03 - Pre-Fitting | 25/02/2021 | 19/05/2021 | 01/02/2021 | 18/02/2021 | 0 | TK_Complete | 1112893334 | 81 | 1112893334_81
C720C147CF###0040110 | TT_Task | Train 03 - Fitting | 25/03/2021 | 16/06/2021 | 10/02/2021 | 16/03/2021 | 0 | TK_Complete | 1112893334 | 81 | 1112893334_81
C720C147CF###0040140 | TT_Task | Train 04 - Pre-Fitting | 18/03/2021 | 09/06/2021 | 11/02/2021 | 02/03/2021 | 0 | TK_Complete | 1112893334 | 81 | 1112893334_81
C720C147CF###0040170 | TT_Task | Train 04 - Fitting | 06/07/2021 | 27/09/2021 | 23/02/2021 | 16/04/2021 | 0 | TK_Complete | 1112893334 | 81 | 1112893334_81
C720C147CF###0040200 | TT_Task | Train 05 - Pre-Fitting | 15/04/2021 | 07/07/2021 | 18/03/2021 | 31/03/2021 | 0 | TK_Complete | 1112893334 | 81 | 1112893334_81
C720C147CF###0040230 | TT_Task | Train 05 - Fitting | 26/04/2021 | 16/07/2021 | 24/03/2021 | 07/06/2021 | 0 | TK_Complete | 1112893334 | 81 | 1112893334_81
C720C147CF###0040240 | TT_Task | Train 06 - Pre-Fitting | 17/05/2021 | 06/08/2021 | 24/04/2021 | 27/05/2021 | 0 | TK_Complete | 1112893334 | 81 | 1112893334_81
C720C147CF###0040300 | TT_Task | Train 06 - Fitting | 28/06/2021 | 10/09/2021 | 13/05/2021 | 20/07/2021 | 0 | TK_Complete | 1112893334 | 81 | 1112893334_81
C720C147CF###0040330 | TT_Task | Train 07 - Pre-Fitting | 25/06/2021 | 09/09/2021 | 08/06/2021 | 05/07/2021 | 0 | TK_Complete | 1112893334 | 81 | 1112893334_81
C720C147CF###0040390 | TT_Task | Train 07 - Fitting | 30/07/2021 | 07/10/2021 | 25/06/2021 | 31/07/2021 | 0 | TK_Complete | 1112893334 | 81 | 1112893334_81
C720C147CF###0040430 | TT_Task | Train 08 - Pre-Fitting | 26/07/2021 | 01/10/2021 | 01/07/2021 | 19/07/2021 | 0 | TK_Complete | 1112893334 | 81 | 1112893334_81
C720C147CF###0040470 | TT_Task | Train 08 - Fitting | 30/08/2021 | 05/11/2021 | 26/07/2021 | 30/08/2021 | 0 | TK_Complete | 1112893334 | 81 | 1112893334_81
C720C147CF###0040510 | TT_Task | Train 09 - Pre-Fitting | 25/08/2021 | 02/11/2021 | 05/08/2021 | 26/08/2021 | 0 | TK_Complete | 1112893334 | 81 | 1112893334_81
C720C147CF###0040560 | TT_Task | Train 09 - Fitting | 15/09/2021 | 23/11/2021 | 13/08/2021 | 30/09/2021 | 0 | TK_Complete | 1112893334 | 81 | 1112893334_81
C720C147CF###0040000 | TT_Task | Train 01 - Carbodyshell | 10/12/2020 | 03/03/2021 | 10/11/2020 | 04/12/2020 | 0 | TK_Complete | 1112893334 | 80 | 1112893334_80
C720C147CF###0040010 | TT_Task | Train 02 - Carbodyshell | 12/01/2021 | 26/04/2021 | 14/12/2020 | 31/12/2020 | 0 | TK_Complete | 1112893334 | 80 | 1112893334_80
C720C147CF###0040050 | TT_Task | Train 03 - Carbodyshell | 01/02/2021 | 30/04/2021 | 12/01/2021 | 05/02/2021 | 0 | TK_Complete | 1112893334 | 80 | 1112893334_80
C720C147CF###0040080 | TT_Task | Train 04 - Carbodyshell | 25/02/2021 | 26/05/2021 | 30/01/2021 | 22/02/2021 | 0 | TK_Complete | 1112893334 | 80 | 1112893334_80
C720C147CF###0040130 | TT_Task | Train 05 - Carbodyshell | 25/03/2021 | 16/06/2021 | 02/03/2021 | 19/03/2021 | 0 | TK_Complete | 1112893334 | 80 | 1112893334_80
C720C147CF###0040190 | TT_Task | Train 06 - Carbodyshell | 26/04/2021 | 16/07/2021 | 01/04/2021 | 28/04/2021 | 0 | TK_Complete | 1112893334 | 80 | 1112893334_80
C720C147CF###0040260 | TT_Task | Train 07 - Carbodyshell | 15/04/2021 | 30/06/2021 | 15/04/2021 | 09/06/2021 | 0 | TK_Complete | 1112893334 | 80 | 1112893334_80
C720C147CF###0040340 | TT_Task | Train 08 - Carbodyshell | 25/06/2021 | 02/09/2021 | 24/05/2021 | 05/07/2021 | 0 | TK_Complete | 1112893334 | 80 | 1112893334_80
C720C147CF###0040440 | TT_Task | Train 09 - Carbodyshell | 26/07/2021 | 01/10/2021 | 13/07/2021 | 04/08/2021 | 0 | TK_Complete | 1112893334 | 80 | 1112893334_80
C720D147CF###0020170 | TT_Task | Trains/Stage-2 - Preperation ; submission of updated delivery program complied with PS sec 29 ; TfNSW SM prog. protocol | 20/11/2019 | 17/12/2019 | 21/10/2019 | 20/12/2019 | 0 | TK_Complete | 1112893334 | 8 | 1112893334_8
C730D147BC###0010010 | TT_Task | Preperation ; submission of updated delivery program complied with SSC clause 17.3, PS sec.17 ; SM programming protocol | 01/11/2019 | 28/11/2019 | 15/10/2019 | 20/12/2019 | 0 | TK_Complete | 1112893334 | 8 | 1112893334_8
C720P147CF###0031890 | TT_Task | DEL Auxilary converter | 02/11/2020 | 27/11/2020 | 28/10/2020 | 08/12/2020 | 0 | TK_Complete | 1112893334 | 79 | 1112893334_79
C720P147CF###D87200 | TT_Task | Production Auxilary converter [Covid-19 delay event - China] | 27/04/2020 | 27/04/2020 | 27/01/2020 | 30/03/2020 | 0 | TK_Complete | 1112893334 | 79 | 1112893334_79
C720P147CF###0031450 | TT_Task | PO Wheels | 25/03/2020 | 23/04/2020 | 04/03/2020 | 09/03/2020 | 0 | TK_Complete | 1112893334 | 78 | 1112893334_78
C720P147CF###0031510 | TT_Task | PO Axles | 25/05/2020 | 22/06/2020 | 31/03/2020 | 17/04/2020 | 0 | TK_Complete | 1112893334 | 78 | 1112893334_78
C720P147CF###0031540 | TT_Task | Production Wheels | 25/03/2020 | 16/11/2020 | 10/03/2020 | 26/10/2020 | 0 | TK_Complete | 1112893334 | 78 | 1112893334_78
C720P147CF###0031570 | TT_Task | Production Axles | 25/06/2020 | 10/02/2021 | 04/05/2020 | 15/10/2020 | 0 | TK_Complete | 1112893334 | 78 | 1112893334_78
C720P147CF###0532710 | TT_Task | BA Obstacle detector | 23/06/2020 | 20/07/2020 | 05/12/2019 | 08/04/2020 | 0 | TK_Complete | 1112893334 | 77 | 1112893334_77
C720P147CF###0532750 | TT_Task | PO Obstacle detector | 21/07/2020 | 17/08/2020 | 09/04/2020 | 30/04/2020 | 0 | TK_Complete | 1112893334 | 77 | 1112893334_77
C720P147CF###5032790 | TT_Task | Production Obstacle detector | 25/06/2020 | 22/03/2021 | 07/05/2020 | 21/10/2020 | 0 | TK_Complete | 1112893334 | 77 | 1112893334_77
C720P147CF###32830 | TT_Task | DEL obstacle detector | 16/12/2020 | 28/01/2021 | 22/10/2020 | 02/11/2020 | 0 | TK_Complete | 1112893334 | 77 | 1112893334_77
C720P147CF###0532700 | TT_Task | BA Centre pivot | 23/06/2020 | 20/07/2020 | 05/12/2019 | 13/04/2020 | 0 | TK_Complete | 1112893334 | 76 | 1112893334_76
C720P147CF###0532740 | TT_Task | PO Centre pivot | 21/07/2020 | 17/08/2020 | 14/04/2020 | 08/05/2020 | 0 | TK_Complete | 1112893334 | 76 | 1112893334_76
C720P147CF###5032780 | TT_Task | Production Centre pivot | 18/08/2020 | 18/02/2021 | 20/05/2020 | 14/10/2020 | 0 | TK_Complete | 1112893334 | 76 | 1112893334_76
C720P147CF###32820 | TT_Task | DEL centre pivot | 06/11/2020 | 03/12/2020 | 28/10/2020 | 05/12/2020 | 0 | TK_Complete | 1112893334 | 76 | 1112893334_76
C720P147CF###0532690 | TT_Task | BA Couplings | 23/06/2020 | 20/07/2020 | 05/12/2019 | 26/03/2020 | 0 | TK_Complete | 1112893334 | 75 | 1112893334_75
C720P147CF###0532730 | TT_Task | PO Couplings | 21/07/2020 | 17/08/2020 | 27/03/2020 | 31/03/2020 | 0 | TK_Complete | 1112893334 | 75 | 1112893334_75
C720P147CF###5032770 | TT_Task | Production Couplings | 18/08/2020 | 18/02/2021 | 20/04/2020 | 16/10/2020 | 0 | TK_Complete | 1112893334 | 75 | 1112893334_75
C720P147CF###32810 | TT_Task | DEL couplings | 10/11/2020 | 27/01/2021 | 19/10/2020 | 27/10/2020 | 0 | TK_Complete | 1112893334 | 75 | 1112893334_75
C720P147CF###0532680 | TT_Task | BA Gearbox | 23/06/2020 | 20/07/2020 | 05/12/2019 | 18/03/2020 | 0 | TK_Complete | 1112893334 | 74 | 1112893334_74
C720P147CF###0532720 | TT_Task | PO Gearbox | 21/07/2020 | 17/08/2020 | 19/03/2020 | 31/03/2020 | 0 | TK_Complete | 1112893334 | 74 | 1112893334_74
C720P147CF###5032760 | TT_Task | Production Gearbox | 18/08/2020 | 17/05/2021 | 15/04/2020 | 23/10/2020 | 0 | TK_Complete | 1112893334 | 74 | 1112893334_74
C720P147CF###32800 | TT_Task | DEL gearbox | 18/11/2020 | 15/12/2020 | 27/10/2020 | 06/12/2020 | 0 | TK_Complete | 1112893334 | 74 | 1112893334_74
C720P147CF###0030840 | TT_Task | BA Axle box ; bearing | 25/02/2020 | 23/03/2020 | 05/12/2019 | 09/04/2020 | 0 | TK_Complete | 1112893334 | 73 | 1112893334_73
C720P147CF###0031490 | TT_Task | PO Axle box ; bearing | 25/05/2020 | 22/06/2020 | 10/04/2020 | 29/04/2020 | 0 | TK_Complete | 1112893334 | 73 | 1112893334_73
C720P147CF###0031560 | TT_Task | Production Axle box ; bearing | 25/06/2020 | 27/11/2020 | 06/05/2020 | 15/10/2020 | 0 | TK_Complete | 1112893334 | 73 | 1112893334_73
C720P147CF###0031900 | TT_Task | DEL Axle box ; bearing | 26/10/2020 | 18/12/2020 | 16/10/2020 | 22/12/2020 | 0 | TK_Complete | 1112893334 | 73 | 1112893334_73
C730D157BC###0010010 | TT_Task | Manufacturing SMTF[N] Depot DSER2 - Room Cables (*redundant with trackside cables) | 27/05/2020 | 19/08/2020 | 01/03/2020 | 02/03/2020 | 0 | TK_Complete | 1112893334 | 724 | 1112893334_724
C730D157BC###0010020 | TT_Task | FAI/FAT SMTF[N] Depot DSER2 - Room Cables (*redundant with trackside cables) | 20/08/2020 | 28/08/2020 | 18/03/2020 | 18/03/2020 | 0 | TK_Complete | 1112893334 | 724 | 1112893334_724
C730D157BC###0010030 | TT_Task | Material Delivery SMTF[N] Depot DSER2 - Room Cables (*redundant with trackside cables) | 31/08/2020 | 19/10/2020 | 24/03/2020 | 24/03/2020 | 0 | TK_Complete | 1112893334 | 724 | 1112893334_724
C730D157BC###0017875 | TT_Task | Manufacturing SMTF[N] Depot DSER2 - CCTV BTN (*redundant with DCS BTN) | 11/05/2020 | 03/08/2020 | 03/02/2020 | 03/02/2020 | 0 | TK_Complete | 1112893334 | 723 | 1112893334_723
C730D157BC###0017975 | TT_Task | FAI/FAT SMTF[N] Depot DSER2 - CCTV BTN (*redundant with DCS BTN) | 25/05/2020 | 02/06/2020 | 24/03/2020 | 24/03/2020 | 0 | TK_Complete | 1112893334 | 723 | 1112893334_723
C730D157BC###0018035 | TT_Task | Material Delivery SMTF[N] Depot DSER2 - CCTV BTN (*redundant with DCS BTN) | 11/06/2020 | 05/08/2020 | 05/05/2020 | 05/05/2020 | 0 | TK_Complete | 1112893334 | 723 | 1112893334_723
C730D157BC###N312110 | TT_Task | CAD Conversion -SER - Martin Place, Pitt St | 25/03/2021 | 31/03/2021 | 26/02/2021 | 25/08/2021 | 0 | TK_Complete | 1112893334 | 722 | 1112893334_722
C730D157BC###N312120 | TT_Task | CAD Conversion - SER - Victoria Cross, Crows Nest, Barangaroo | 25/03/2021 | 29/03/2021 | 01/03/2021 | 25/08/2021 | 0 | TK_Complete | 1112893334 | 722 | 1112893334_722
C730D157BC###N669463 | TT_Task | CAD Conversion - SER -Waterloo | 25/03/2021 | 26/03/2021 | 01/03/2021 | 25/08/2021 | 0 | TK_Complete | 1112893334 | 722 | 1112893334_722
C730D157BC###N709453 | TT_Task | CAD Conversion -SER - Chatswood, Sydenham, Central | 25/03/2021 | 31/03/2021 | 18/03/2021 | 25/04/2021 | 0 | TK_Complete | 1112893334 | 722 | 1112893334_722
C730D157BC###N209513 | TT_Task | CAD Conversion - Trackside SMTF[S] - SAB, Key Switch, Marker Board | 25/02/2021 | 03/03/2021 | 08/02/2021 | 25/08/2021 | 0 | TK_Complete | 1112893334 | 721 | 1112893334_721
C730D157BC###N949323 | TT_Task | CAD Conversion - Trackside City - PM, Key Switches, Marker Board | 25/05/2021 | 31/05/2021 | 23/04/2021 | 25/08/2021 | 0 | TK_Complete | 1112893334 | 721 | 1112893334_721
C730D157BC###N09473 | TT_Task | CAD Conversion - Trackside City - PPI, DCS | 26/04/2021 | 30/04/2021 | 09/04/2021 | 25/08/2021 | 0 | TK_Complete | 1112893334 | 720 | 1112893334_720
C730D157BC###N09483 | TT_Task | CAD Conversion - Trackside City - Axle Counter, Balise, SAB, Buffer Light | 25/03/2021 | 31/03/2021 | 25/02/2021 | 25/08/2021 | 0 | TK_Complete | 1112893334 | 720 | 1112893334_720
C730D157BC###N209503 | TT_Task | CAD Conversion - Trackside SMTF[S] - DCS | 26/04/2021 | 30/04/2021 | 06/04/2021 | 25/08/2021 | 0 | TK_Complete | 1112893334 | 720 | 1112893334_720
C730D157BC###N209523 | TT_Task | CAD Conversion - Trackside SMTF[S] - Buffer, Axle Counter, Balise | 25/02/2021 | 03/03/2021 | 01/02/2021 | 25/08/2021 | 0 | TK_Complete | 1112893334 | 720 | 1112893334_720
C730D157BC###N209533 | TT_Task | CAD Conversion -Trackside SMTF[S] - PM, PPI | 26/04/2021 | 30/04/2021 | 06/04/2021 | 25/08/2021 | 0 | TK_Complete | 1112893334 | 720 | 1112893334_720
C720P147CF###0030830 | TT_Task | BA Bogie Frame | 25/02/2020 | 19/03/2020 | 05/12/2019 | 08/01/2020 | 0 | TK_Complete | 1112893334 | 72 | 1112893334_72
C720P147CF###0031480 | TT_Task | PO Bogie Frame | 06/04/2020 | 12/05/2020 | 06/04/2020 | 27/04/2020 | 0 | TK_Complete | 1112893334 | 72 | 1112893334_72
C720P147CF###0031590 | TT_Task | Production Bogie Frame | 29/05/2020 | 10/02/2021 | 28/04/2020 | 21/12/2020 | 0 | TK_Complete | 1112893334 | 72 | 1112893334_72
C720P147CF###0032240 | TT_Task | DEL Bogie Frame | 11/01/2021 | 01/02/2021 | 30/11/2020 | 07/01/2021 | 0 | TK_Complete | 1112893334 | 72 | 1112893334_72
C730T018CB###N317000 | TT_Task | SMTF-[N] MS2 COM Visual Inspection Tests***N/A*** | 25/11/2021 | 25/11/2021 | 25/11/2021 | 25/11/2021 | 0 | TK_Complete | 1112893334 | 719 | 1112893334_719
C730T018CB###N317010 | TT_Task | SMTF-[N] MS2 COM Interface Functional Tests***N/A*** | 26/11/2021 | 30/11/2021 | 26/11/2021 | 26/11/2021 | 0 | TK_Complete | 1112893334 | 719 | 1112893334_719
C730T018CB###N317020 | TT_Task | SMTF-[N] MS4 COM Visual Inspection Tests ***N/A*** | 25/01/2022 | 25/01/2022 | 24/01/2022 | 24/01/2022 | 0 | TK_Complete | 1112893334 | 719 | 1112893334_719
C730T018CB###N317030 | TT_Task | SMTF-[N] MS4 COM Interface Functional Tests ***N/A*** | 26/01/2022 | 28/01/2022 | 24/01/2022 | 24/01/2022 | 0 | TK_Complete | 1112893334 | 719 | 1112893334_719
C720P147CF###D87080 | TT_Task | PO Detrainment doors [Covid-19 delay event - France/China] ***N/A*** | 25/03/2020 | 25/03/2020 | 27/01/2020 | 20/03/2020 | 0 | TK_Complete | 1112893334 | 718 | 1112893334_718
C720P147CF###D87100 | TT_Task | PO Seats [Covid-19 delay event - Germany/China] ***N/A*** | 25/03/2020 | 25/03/2020 | 27/01/2020 | 30/03/2020 | 0 | TK_Complete | 1112893334 | 718 | 1112893334_718
C730D157BC###N513923 | TT_Task | Removal of 21 Axle Counter at SMTF-N | 25/01/2021 | 04/02/2021 | 26/10/2020 | 06/11/2020 | 0 | TK_Complete | 1112893334 | 717 | 1112893334_717
C730D157BC###N949463 | TT_Task | Reinstatement of 21 Axle Counter at SMTF-N | 25/01/2021 | 03/02/2021 | 09/11/2020 | 19/11/2020 | 0 | TK_Complete | 1112893334 | 717 | 1112893334_717
C730T147BC###N501697 | TT_Task | Manufacturing ; Delivery Point Machines Acccessories (7 Nos.) | 27/01/2021 | 24/08/2021 | 27/11/2020 | 25/06/2021 | 0 | TK_Complete | 1112893334 | 716 | 1112893334_716
C730T147BC###N501747 | TT_Task | Sourcing (PO Issuance) Point Machines Acccessories (7 Nos.) | 25/01/2021 | 26/01/2021 | 25/11/2020 | 26/11/2020 | 0 | TK_Complete | 1112893334 | 716 | 1112893334_716
C730T147BC###N023850 | TT_Task | Manufacturing ; Delivery Point Machines (RTF41, RTF43) | 25/08/2020 | 31/05/2021 | 26/06/2020 | 25/06/2021 | 0 | TK_Complete | 1112893334 | 715 | 1112893334_715
C730T147BC###N501737 | TT_Task | Sourcing (PO Issuance) Point Machines (RTF41, RTF43) | 25/08/2020 | 26/08/2020 | 02/08/2020 | 04/08/2020 | 0 | TK_Complete | 1112893334 | 715 | 1112893334_715
C730T147BC###N023820 | TT_Task | Installation of Motors ; Accessories (RTF41,RTF43) - Possession Works | 25/12/2021 | 26/12/2021 | 28/06/2021 | 07/07/2021 | 0 | TK_Complete | 1112893334 | 715 | 1112893334_715
C730T147BC###N023823 | TT_Task | Installation of Point Machine Accessories (RTF32,RTF33,RTF34,RTF2,RTF10) | 23/12/2021 | 29/12/2021 | 28/06/2021 | 07/07/2021 | 0 | TK_Complete | 1112893334 | 715 | 1112893334_715
C730T147BC###N02425 | TT_Task | ETT T;C - PAT (WE Possession WE 10) | 26/10/2020 | 27/10/2020 | 05/09/2020 | 06/09/2020 | 0 | TK_Complete | 1112893334 | 714 | 1112893334_714
C730T147BC###N02435 | TT_Task | ETT T;C - SIT (WE Possession WE 10) | 27/10/2020 | 28/10/2020 | 05/09/2020 | 06/09/2020 | 0 | TK_Complete | 1112893334 | 714 | 1112893334_714
C730T147BC###N02405 | TT_Task | ETT T;C - PICO (Extended 5hr Night Shift) | 26/10/2020 | 26/10/2020 | 26/08/2020 | 28/08/2020 | 0 | TK_Complete | 1112893334 | 713 | 1112893334_713
C730T147BC###N02415 | TT_Task | As-Builts - Update ITCs, Scheme Plan, ; Circuit Books | 26/10/2020 | 06/11/2020 | 07/09/2020 | 18/09/2020 | 0 | TK_Complete | 1112893334 | 712 | 1112893334_712
C730T147BC###N02315 | TT_Task | CBTC/Stage-3 SMTF[N] - CBI Circuit Book for Staging works for False Feeding | 08/09/2020 | 21/09/2020 | 07/08/2020 | 14/08/2020 | 0 | TK_Complete | 1112893334 | 711 | 1112893334_711
C730T147BC###N02345 | TT_Task | CBTC/Stage-3 SMTF[N] - Flashcard preparation for alarm management | 22/09/2020 | 05/10/2020 | 18/08/2020 | 18/08/2020 | 0 | TK_Complete | 1112893334 | 711 | 1112893334_711
C730C147BC###D70502 | TT_Task | [DE] Site Survey/ITSP Checks as per Degree2 Access SMTF[N] Depot New Test Track | 27/07/2020 | 21/08/2020 | 15/07/2020 | 15/07/2020 | 0 | TK_Complete | 1112893334 | 710 | 1112893334_710
C730C147BC###D70512 | TT_Task | [DE] Site Survey/ITSP Checks as per Degree2 Access SMTF[N] Depot Stabling roads (30-35) | 27/07/2020 | 21/08/2020 | 15/07/2020 | 15/07/2020 | 0 | TK_Complete | 1112893334 | 710 | 1112893334_710
C730C147BC###D70522 | TT_Task | [DE] Site Survey/ITSP Checks as per Degree2 Access SMTF[N] Depot DSER2 | 27/07/2020 | 21/08/2020 | 15/07/2020 | 30/09/2020 | 0 | TK_Complete | 1112893334 | 710 | 1112893334_710
C730C147BC###D70532 | TT_Task | [DE] Site Survey/ITSP Checks as per Degree2 Access SMTF[N] Depot DSER1/MS1 | 27/07/2020 | 21/08/2020 | 15/07/2020 | 28/09/2020 | 0 | TK_Complete | 1112893334 | 710 | 1112893334_710
C720P147CF###0030800 | TT_Task | BA Secondary Suspension | 25/02/2020 | 25/03/2020 | 05/12/2019 | 24/04/2020 | 0 | TK_Complete | 1112893334 | 71 | 1112893334_71
C720P147CF###0030810 | TT_Task | BA Primary Suspension | 25/02/2020 | 24/03/2020 | 05/12/2019 | 15/05/2020 | 0 | TK_Complete | 1112893334 | 71 | 1112893334_71
C720P147CF###0031460 | TT_Task | PO Secondary Suspension | 25/05/2020 | 22/06/2020 | 04/05/2020 | 08/05/2020 | 0 | TK_Complete | 1112893334 | 71 | 1112893334_71
C720P147CF###0031470 | TT_Task | PO Primary Suspension | 25/05/2020 | 22/06/2020 | 15/05/2020 | 19/05/2020 | 0 | TK_Complete | 1112893334 | 71 | 1112893334_71
C720P147CF###0031550 | TT_Task | Production Secondary suspension | 25/06/2020 | 27/11/2020 | 15/05/2020 | 20/10/2020 | 0 | TK_Complete | 1112893334 | 71 | 1112893334_71
C720P147CF###0031580 | TT_Task | Production Primary suspension | 25/06/2020 | 27/11/2020 | 26/05/2020 | 09/10/2020 | 0 | TK_Complete | 1112893334 | 71 | 1112893334_71
C720P147CF###0032210 | TT_Task | DEL Secondary suspension | 02/11/2020 | 11/01/2021 | 27/10/2020 | 06/12/2020 | 0 | TK_Complete | 1112893334 | 71 | 1112893334_71
C720P147CF###0032230 | TT_Task | DEL Primary suspension | 30/10/2020 | 24/12/2020 | 12/10/2020 | 14/12/2020 | 0 | TK_Complete | 1112893334 | 71 | 1112893334_71
C720P147CF###D87260 | TT_Task | Production Bogie frame [Covid-19 delay event - India] | 18/05/2020 | 18/05/2020 | 25/03/2020 | 31/05/2020 | 0 | TK_Complete | 1112893334 | 709 | 1112893334_709
C720P147CF###D32760 | TT_Task | PO Bogie Frame [Covid-19 delay event - India] ***N/A*** | 06/04/2020 | 06/04/2020 | 25/03/2020 | 27/04/2020 | 0 | TK_Complete | 1112893334 | 709 | 1112893334_709
C720P147CF###D32780 | TT_Task | PO Long profile [Covid-19 delay event - India] ***N/A*** | 27/04/2020 | 27/04/2020 | 25/03/2020 | 30/04/2020 | 0 | TK_Complete | 1112893334 | 709 | 1112893334_709
C720P147CF###D87090 | TT_Task | PO Gangway [Covid-19 delay event - India] ***N/A*** | 27/04/2020 | 27/04/2020 | 26/03/2020 | 30/03/2020 | 0 | TK_Complete | 1112893334 | 709 | 1112893334_709
C720P147CF###D32830 | TT_Task | Production Gangway [Covid-19 delay event - India] | 18/05/2020 | 18/05/2020 | 25/03/2020 | 31/05/2020 | 0 | TK_Complete | 1112893334 | 708 | 1112893334_708
C720P147CF###D32880 | TT_Task | Production Cabinets [Covid-19 delay event - India] | 07/07/2020 | 07/07/2020 | 25/03/2020 | 31/05/2020 | 0 | TK_Complete | 1112893334 | 708 | 1112893334_708
C720P147CF###D87070 | TT_Task | Production EUF [Covid-19 delay event - India] | 25/03/2020 | 25/03/2020 | 25/03/2020 | 31/05/2020 | 0 | TK_Complete | 1112893334 | 708 | 1112893334_708
C720P147CF###D87210 | TT_Task | Production Long profile [Covid-19 delay event - India] | 25/03/2020 | 25/03/2020 | 25/03/2020 | 31/05/2020 | 0 | TK_Complete | 1112893334 | 708 | 1112893334_708
C720P147CF###D87220 | TT_Task | Production Coupler [Covid-19 delay event - India] | 18/05/2020 | 18/05/2020 | 25/03/2020 | 31/05/2020 | 0 | TK_Complete | 1112893334 | 708 | 1112893334_708
C720P147CF###D87240 | TT_Task | Production Brakes [Covid-19 delay event - India] | 18/05/2020 | 18/05/2020 | 25/03/2020 | 31/05/2020 | 0 | TK_Complete | 1112893334 | 708 | 1112893334_708
C720P147CF###D87150 | TT_Task | BA Obstacle detector [Covid-19 delay event - France] | 25/02/2020 | 25/02/2020 | 17/03/2020 | 08/04/2020 | 0 | TK_Complete | 1112893334 | 707 | 1112893334_707
C720P147CF###D87160 | TT_Task | Production Obstacle detector [Covid-19 delay event - France] | 27/04/2020 | 27/04/2020 | 17/03/2020 | 07/05/2020 | 0 | TK_Complete | 1112893334 | 707 | 1112893334_707
C720P147CF###D87060 | TT_Task | BA Traction motor [Covid-19 delay event - China] | 25/02/2020 | 25/02/2020 | 27/01/2020 | 25/02/2020 | 0 | TK_Complete | 1112893334 | 706 | 1112893334_706
C720P147CF###D87120 | TT_Task | Production Traction motor [Covid-19 delay event - China] | 27/04/2020 | 27/04/2020 | 27/01/2020 | 15/04/2020 | 0 | TK_Complete | 1112893334 | 706 | 1112893334_706
C720P147CF###D87190 | TT_Task | Production Traction converter [Covid-19 delay event - China] | 27/04/2020 | 27/04/2020 | 27/01/2020 | 30/03/2020 | 0 | TK_Complete | 1112893334 | 706 | 1112893334_706
C720P147CF###D87050 | TT_Task | BA Grabpoles and grab handles [Covid-19 delay event - China] | 25/02/2020 | 25/02/2020 | 27/01/2020 | 23/03/2020 | 0 | TK_Complete | 1112893334 | 705 | 1112893334_705
C720P147CF###D32860 | TT_Task | Production Grabpoles and grab handles [Covid-19 delay event - China] | 27/04/2020 | 27/04/2020 | 27/01/2020 | 28/05/2020 | 0 | TK_Complete | 1112893334 | 705 | 1112893334_705
C720P147CF###D32770 | TT_Task | BA Axle box ; bearing [Covid-19 delay event - India] | 25/02/2020 | 25/02/2020 | 25/03/2020 | 09/04/2020 | 0 | TK_Complete | 1112893334 | 704 | 1112893334_704
C720P147CF###D87270 | TT_Task | Production Axle box ; bearing [Covid-19 delay event - India] | 18/05/2020 | 18/05/2020 | 25/03/2020 | 31/05/2020 | 0 | TK_Complete | 1112893334 | 704 | 1112893334_704
C720P147CF###D32710 | TT_Task | BA Floor covering [Covid-19 delay event - UK] | 25/02/2020 | 25/02/2020 | 23/03/2020 | 30/04/2020 | 0 | TK_Complete | 1112893334 | 703 | 1112893334_703
C720P147CF###D32810 | TT_Task | Production Floor (Composite Material) [Covid-19 delay event - Italy] | 27/04/2020 | 27/04/2020 | 09/03/2020 | 26/03/2020 | 0 | TK_Complete | 1112893334 | 703 | 1112893334_703
C720P147CF###D32820 | TT_Task | Production Detrainment doors [Covid-19 delay event - France] | 27/04/2020 | 27/04/2020 | 17/03/2020 | 03/04/2020 | 0 | TK_Complete | 1112893334 | 703 | 1112893334_703
C720P147CF###D32870 | TT_Task | Production Seats [Covid-19 delay event - Germany] | 27/04/2020 | 27/04/2020 | 20/03/2020 | 24/04/2020 | 0 | TK_Complete | 1112893334 | 703 | 1112893334_703
C720P147CF###D32900 | TT_Task | Production PACIS [Covid-19 delay event - Australia] | 27/04/2020 | 27/04/2020 | 25/03/2020 | 24/04/2020 | 0 | TK_Complete | 1112893334 | 703 | 1112893334_703
C720P147CF###D32700 | TT_Task | BA Front mask [Covid-19 delay event - India] | 25/02/2020 | 25/02/2020 | 25/03/2020 | 30/04/2020 | 0 | TK_Complete | 1112893334 | 702 | 1112893334_702
C720P147CF###D87250 | TT_Task | Production Front mask [Covid-19 delay event - India] | 18/05/2020 | 18/05/2020 | 25/03/2020 | 31/05/2020 | 0 | TK_Complete | 1112893334 | 702 | 1112893334_702
C720P147CF###D32690 | TT_Task | BA Hand rails [Covid-19 delay event - China] | 25/02/2020 | 25/02/2020 | 27/01/2020 | 24/04/2020 | 0 | TK_Complete | 1112893334 | 701 | 1112893334_701
C720P147CF###D32750 | TT_Task | BA Axles [Covid-19 delay event - China] | 25/02/2020 | 25/02/2020 | 27/01/2020 | 30/03/2020 | 0 | TK_Complete | 1112893334 | 701 | 1112893334_701
C720P147CF###D87130 | TT_Task | BA Gearbox [Covid-19 delay event - China] | 25/02/2020 | 25/02/2020 | 27/01/2020 | 18/03/2020 | 0 | TK_Complete | 1112893334 | 701 | 1112893334_701
C720P147CF###D87170 | TT_Task | Production Gearbox [Covid-19 delay event - China] | 27/04/2020 | 27/04/2020 | 27/01/2020 | 14/04/2020 | 0 | TK_Complete | 1112893334 | 701 | 1112893334_701
C720D147CF###D87040 | TT_Task | Trains/Stage-2 - Interface freeze TSE [Covid-19 delay event - China] | 26/02/2020 | 26/02/2020 | 27/01/2020 | 25/02/2020 | 0 | TK_Complete | 1112893334 | 701 | 1112893334_701
C730P147CT###D33199 | TT_Task | Production (Trainborne Signalling ; CCTV) - Train 1, 2 ; 3 [Covid-19 delay event - China/Europe] | 27/04/2020 | 27/04/2020 | 27/01/2020 | 24/04/2020 | 0 | TK_Complete | 1112893334 | 701 | 1112893334_701
C720P147CF###D32680 | TT_Task | BA Pantograph [Covid-19 delay event - Austria] | 25/02/2020 | 25/02/2020 | 13/03/2020 | 13/04/2020 | 0 | TK_Complete | 1112893334 | 700 | 1112893334_700
C720P147CF###D32890 | TT_Task | Production Pantograph [Covid-19 delay event - Austria] | 20/04/2020 | 20/04/2020 | 13/03/2020 | 24/04/2020 | 0 | TK_Complete | 1112893334 | 700 | 1112893334_700
C720P147CF###0030770 | TT_Task | BA Wheels | 25/02/2020 | 23/03/2020 | 05/12/2019 | 16/01/2020 | 0 | TK_Complete | 1112893334 | 70 | 1112893334_70
C720P147CF###0030890 | TT_Task | BA Axles | 25/02/2020 | 23/03/2020 | 05/12/2019 | 30/03/2020 | 0 | TK_Complete | 1112893334 | 70 | 1112893334_70
C720P147CF###0032200 | TT_Task | DEL Wheels | 02/11/2020 | 27/11/2020 | 27/10/2020 | 05/12/2020 | 0 | TK_Complete | 1112893334 | 70 | 1112893334_70
C720P147CF###0032220 | TT_Task | DEL Axles | 18/11/2020 | 15/12/2020 | 28/10/2020 | 03/12/2020 | 0 | TK_Complete | 1112893334 | 70 | 1112893334_70
C720D147CF###0020160 | TT_Task | Trains/Stage-2 - PM activities to finalize and submit initial MCS (Material Control Schedule) for Trains scope | 18/10/2019 | 28/11/2019 | 18/10/2019 | 20/12/2019 | 0 | TK_Complete | 1112893334 | 7 | 1112893334_7
C720D147CF###0020210 | TT_Task | Trains/Stage-2 - PM activities to finalize and submit the MCS (Material Control Schedule) for Trains scope | 18/06/2020 | 15/07/2020 | 27/03/2020 | 28/04/2020 | 0 | TK_Complete | 1112893334 | 7 | 1112893334_7
C720D147CF###0021510 | TT_Task | Trains/Stage-2 - Activities to finalize and submit the final SOD (Schedule of Design) for Trains scope | 23/07/2019 | 05/08/2019 | 23/07/2019 | 14/08/2019 | 0 | TK_Complete | 1112893334 | 7 | 1112893334_7
C720D147CF###0021520 | TT_Task | Trains/Stage-2 - Preparation and submission of trains T;C (Testing and Commissioning) plan | 25/02/2020 | 06/04/2020 | 31/10/2019 | 11/12/2019 | 0 | TK_Complete | 1112893334 | 7 | 1112893334_7
C720P147CF###D32670 | TT_Task | BA Battery ; battery box [Covid-19 delay event - India] | 25/02/2020 | 25/02/2020 | 25/03/2020 | 07/04/2020 | 0 | TK_Complete | 1112893334 | 699 | 1112893334_699
C720P147CF###D87230 | TT_Task | Production Battery ; battery box [Covid-19 delay event - India] | 18/05/2020 | 18/05/2020 | 25/03/2020 | 31/05/2020 | 0 | TK_Complete | 1112893334 | 699 | 1112893334_699
C720P147CF###D32660 | TT_Task | BA Ceiling and lighting [Covid-19 delay event - China] | 25/02/2020 | 25/02/2020 | 27/01/2020 | 24/04/2020 | 0 | TK_Complete | 1112893334 | 698 | 1112893334_698
C720P147CF###D32790 | TT_Task | BA Secondary Suspension [Covid-19 delay event - China] | 25/02/2020 | 25/02/2020 | 27/01/2020 | 24/04/2020 | 0 | TK_Complete | 1112893334 | 698 | 1112893334_698
C720P147CF###D32800 | TT_Task | BA Primary Suspension [Covid-19 delay event - China] | 25/02/2020 | 25/02/2020 | 27/01/2020 | 15/05/2020 | 0 | TK_Complete | 1112893334 | 698 | 1112893334_698
C720P147CF###D87140 | TT_Task | BA Centre pivot [Covid-19 delay event - China] | 25/02/2020 | 25/02/2020 | 27/01/2020 | 13/04/2020 | 0 | TK_Complete | 1112893334 | 698 | 1112893334_698
C720P147CF###D87180 | TT_Task | Production Centre pivot [Covid-19 delay event - China] | 27/04/2020 | 27/04/2020 | 27/01/2020 | 19/05/2020 | 0 | TK_Complete | 1112893334 | 698 | 1112893334_698
C720P147CF###D32650 | TT_Task | BA Passenger doors [Covid-19 delay event - China] | 25/02/2020 | 25/02/2020 | 27/01/2020 | 27/03/2020 | 0 | TK_Complete | 1112893334 | 697 | 1112893334_697
C720P147CF###D32850 | TT_Task | Production Passenger doors [Covid-19 delay event - China] | 07/04/2020 | 07/04/2020 | 27/01/2020 | 27/04/2020 | 0 | TK_Complete | 1112893334 | 697 | 1112893334_697
C720P147CF###D32640 | TT_Task | BA Laser cut ; bend parts [Covid-19 delay event - India] | 27/04/2020 | 27/04/2020 | 25/03/2020 | 27/04/2020 | 0 | TK_Complete | 1112893334 | 696 | 1112893334_696
C720P147CF###D87110 | TT_Task | PO Laser cut ; bend parts [Covid-19 delay event - India] | 27/04/2020 | 27/04/2020 | 25/03/2020 | 29/05/2020 | 0 | TK_Complete | 1112893334 | 696 | 1112893334_696
C730D147CT###D35500 | TT_Task | INS SMTF(N) Alstom review CSR Route,Pits ; Conduits specs,local route,ULX ; OLX [New TT,ST Rd31-35] | 27/12/2021 | 07/01/2022 | 07/08/2020 | 18/08/2020 | 0 | TK_Complete | 1112893334 | 695 | 1112893334_695
C730D147CT###D35510 | TT_Task | INS SMTF(N) Alstom review CSR Route,Pits ; Conduits specs,local route,ULX ; OLX [Maintenance Road 5-8] | 27/12/2021 | 07/01/2022 | 20/04/2020 | 30/04/2020 | 0 | TK_Complete | 1112893334 | 695 | 1112893334_695
C730D147CT###D35520 | TT_Task | INS SMTF(N) Alstom review CSR Route,Pits ; Conduits specs,local route,ULX ; OLX [Stabling Road 24-30] | 27/12/2021 | 07/01/2022 | 21/12/2020 | 22/01/2021 | 0 | TK_Complete | 1112893334 | 695 | 1112893334_695
C720D147CF###D85060 | TT_Task | Stage3 Input On-going engagement with MTR/SMA on availability of Southwest Key Design Interface Inputs [Delay event] | 25/05/2020 | 25/05/2020 | 05/12/2019 | nan | 0 | TK_Active | 1112893334 | 694 | 1112893334_694
C720D147CF###D85100 | TT_Task | Stage3 Input Engagement with MTR/SMA on availability of finalized PS/SPR DOOR(s) extract [Delay event] | 25/05/2020 | 25/05/2020 | 05/12/2019 | 06/01/2020 | 0 | TK_Complete | 1112893334 | 694 | 1112893334_694
C720D147CF###D85110 | TT_Task | Stage3 Input Engagement with MTR/SMA on final DIS/DITP Inputs from Track/OHW Contractor [Delay event] | 25/05/2020 | 25/05/2020 | 10/01/2020 | 26/07/2021 | 0 | TK_Complete | 1112893334 | 694 | 1112893334_694
C720D147CF###D87060 | TT_Task | Stage3 Input On-going engagement with MTR/SMA on availability of City;SMTF[S] Key Design Interface Inputs [Delay event] | 25/08/2020 | 31/08/2020 | 28/01/2020 | 26/07/2021 | 0 | TK_Complete | 1112893334 | 694 | 1112893334_694
C720D147CF###N87110 | TT_Task | SMTF-N Depot Tracks Milling activity related delay from LWC [Delay event] | 25/05/2020 | 25/05/2020 | 05/07/2021 | 09/07/2021 | 0 | TK_Complete | 1112893334 | 693 | 1112893334_693
C730C157CP###N3250 | TT_Task | Delay in Site access date (SD-SYD Trackside) - As per MTR email recieved on 18-Jan-22 | 04/01/2022 | 10/01/2022 | 27/08/2021 | nan | 0 | TK_Active | 1112893334 | 692 | 1112893334_692
C730C157CP###N3260 | TT_Task | Delay in Site access date (SMTF(S) Trackside) - As per MTR email recieved on 14-Jan-22 | 01/08/2022 | 01/08/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 692 | 1112893334_692
C730C157CP###N3270 | TT_Task | Delay in Site access date (SMTF(S) DSER3) - As per MTR email recieved on 14-Jan-22 | 31/03/2022 | 31/03/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 692 | 1112893334_692
C730C157CP###N41255 | TT_Task | Delay in Site access date (SMTF(S) Trackside CSR ) - As per MTR email recieved on 17-Feb-22 | 01/08/2022 | 01/08/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 692 | 1112893334_692
C730C157CP###D41020 | TT_Task | Delay in TEI due to reprioritisation of Cable hauling and Up-tunnel works(SD-WLO Down Track) | 20/09/2021 | 18/10/2021 | 20/09/2021 | 04/11/2021 | 0 | TK_Complete | 1112893334 | 691 | 1112893334_691
C730C157CK###DE42170 | TT_Task | Delay due to closure of Blue Points Shaft prior to completion of installation | 27/09/2021 | 30/08/2022 | 24/09/2021 | nan | 0 | TK_Active | 1112893334 | 690 | 1112893334_690
C720P147CF###0031170 | TT_Task | BA Windows | 25/02/2020 | 23/03/2020 | 05/12/2019 | 09/03/2020 | 0 | TK_Complete | 1112893334 | 69 | 1112893334_69
C720P147CF###0031370 | TT_Task | PO Windows | 25/03/2020 | 30/03/2020 | 10/03/2020 | 17/03/2020 | 0 | TK_Complete | 1112893334 | 69 | 1112893334_69
C720P147CF###0031410 | TT_Task | Production Windows | 25/03/2020 | 12/10/2020 | 18/03/2020 | 11/09/2020 | 0 | TK_Complete | 1112893334 | 69 | 1112893334_69
C720P147CF###0031920 | TT_Task | DEL Windows | 06/11/2020 | 22/01/2021 | 12/09/2020 | 07/11/2020 | 0 | TK_Complete | 1112893334 | 69 | 1112893334_69
C730C157CK###DE40945 | TT_Task | Delay in Rail blocking Access/Fence blocking issue in BPS | 27/09/2021 | 30/09/2022 | 24/08/2021 | nan | 0 | TK_Active | 1112893334 | 689 | 1112893334_689
C720D147CF###N87090 | TT_Task | Delay in Low Speed CCB approval from MTR/MTS [Delay event] | 25/05/2020 | 25/05/2020 | 04/06/2021 | 02/07/2021 | 0 | TK_Complete | 1112893334 | 689 | 1112893334_689
C730C157CK###D40935 | TT_Task | Delay in Site access date - ePMS 16-Aug-21 (BZZ Xover- Blue Point Shaft Down Track) | 25/08/2021 | 25/08/2021 | 16/08/2021 | 20/08/2021 | 0 | TK_Complete | 1112893334 | 688 | 1112893334_688
C730C157CK###D42160 | TT_Task | Delay in Site access date - MIP 014 (22 Feb 21) (Central Station SER) | 25/08/2021 | 25/08/2021 | 29/12/2021 | 14/02/2022 | 0 | TK_Complete | 1112893334 | 688 | 1112893334_688
C730C157CP###D41120 | TT_Task | Delay in Site Acess date (CHW-Northen Dive Down Track) | 20/09/2021 | 29/09/2021 | 08/12/2021 | nan | 0 | TK_Active | 1112893334 | 688 | 1112893334_688
C720D147CF###N87070 | TT_Task | Public Health (COVID-19 Temporary Movement and Gathering Restrictions) Order2021 [Delay event] | 25/05/2020 | 05/06/2020 | 19/07/2021 | 30/07/2021 | 0 | TK_Complete | 1112893334 | 687 | 1112893334_687
C720D147CF###N87080 | TT_Task | LGAs - Public Health (COVID-19 Temporary Movement and Gathering Restrictions) Order2021 [Delay event] | 25/05/2020 | 05/06/2020 | 28/07/2021 | nan | 0 | TK_Active | 1112893334 | 687 | 1112893334_687
C720D147CF###N87100 | TT_Task | Public Health Order (NSW Covid Restrictions) 2021 - Impact to SMTF-N T;C activities [Delay event] | 25/05/2020 | 25/05/2020 | 19/07/2021 | 30/08/2021 | 0 | TK_Complete | 1112893334 | 687 | 1112893334_687
C730O157CT###N160040 | TT_Task | System RAM Monitoring and Demonstration Report - CSW Line (During DLP) | 28/07/2023 | 11/08/2023 | nan | nan | 5744 | TK_NotStart | 1112893334 | 686 | 1112893334_686
C730C157CT###0012700 | TT_Task | Warranty / Defects Liability Period (2 years) - SMTF (N) Stage 1 | 25/02/2022 | 24/02/2024 | 16/12/2021 | nan | 0 | TK_Active | 1112893334 | 685 | 1112893334_685
C730C157CT###0012705 | TT_Task | Warranty / Defects Liability Period (2 years) - SMTF (N) Stage 2 | 08/08/2022 | 06/08/2024 | nan | nan | 2856 | TK_NotStart | 1112893334 | 685 | 1112893334_685
C730O157CT###0060040 | TT_Task | Warranty / Defects Liability Period (2 years) - CSW Line (City only) | 28/07/2023 | 29/07/2025 | nan | nan | 0 | TK_NotStart | 1112893334 | 685 | 1112893334_685
C720O147CF###0060030 | TT_Task | DCP - Train 01 - Warranty Period | 08/08/2022 | 07/11/2025 | nan | nan | 0 | TK_NotStart | 1112893334 | 684 | 1112893334_684
C720O147CF###0060040 | TT_Task | DCP - Train 22 - Warranty Period | 01/05/2023 | 31/05/2025 | nan | nan | 1280 | TK_NotStart | 1112893334 | 684 | 1112893334_684
C720O147CF###0060050 | TT_Task | DCP - Train 21 - Warranty Period | 01/05/2023 | 31/05/2025 | nan | nan | 1280 | TK_NotStart | 1112893334 | 684 | 1112893334_684
C720O147CF###0060060 | TT_Task | DCP - Train 20 - Warranty Period | 01/05/2023 | 31/05/2025 | nan | nan | 1280 | TK_NotStart | 1112893334 | 684 | 1112893334_684
C720O147CF###0060070 | TT_Task | DCP - Train 19 - Warranty Period | 01/04/2023 | 31/05/2025 | nan | nan | 1280 | TK_NotStart | 1112893334 | 684 | 1112893334_684
C720O147CF###0060080 | TT_Task | DCP - Train 18 - Warranty Period | 01/04/2023 | 31/05/2025 | nan | nan | 1280 | TK_NotStart | 1112893334 | 684 | 1112893334_684
C720O147CF###0060090 | TT_Task | DCP - Train 17 - Warranty Period | 01/03/2023 | 31/05/2025 | nan | nan | 1280 | TK_NotStart | 1112893334 | 684 | 1112893334_684
C720O147CF###0060100 | TT_Task | DCP - Train 16 - Warranty Period | 01/02/2023 | 31/05/2025 | nan | nan | 1280 | TK_NotStart | 1112893334 | 684 | 1112893334_684
C720O147CF###0060110 | TT_Task | DCP - Train 15 - Warranty Period | 01/02/2023 | 31/05/2025 | nan | nan | 1280 | TK_NotStart | 1112893334 | 684 | 1112893334_684
C720O147CF###0060120 | TT_Task | DCP - Train 14 - Warranty Period | 01/01/2023 | 31/05/2025 | nan | nan | 1280 | TK_NotStart | 1112893334 | 684 | 1112893334_684
C720O147CF###0060130 | TT_Task | DCP - Train 13 - Warranty Period | 01/01/2023 | 31/05/2025 | nan | nan | 1280 | TK_NotStart | 1112893334 | 684 | 1112893334_684
C720O147CF###0060140 | TT_Task | DCP - Train 12 - Warranty Period | 01/01/2023 | 31/05/2025 | nan | nan | 1280 | TK_NotStart | 1112893334 | 684 | 1112893334_684
C720O147CF###0060150 | TT_Task | DCP - Train 11 - Warranty Period | 01/12/2022 | 31/05/2025 | nan | nan | 1280 | TK_NotStart | 1112893334 | 684 | 1112893334_684
C720O147CF###0060160 | TT_Task | DCP - Train 10 - Warranty Period | 01/11/2022 | 31/05/2025 | nan | nan | 1280 | TK_NotStart | 1112893334 | 684 | 1112893334_684
C720O147CF###0060170 | TT_Task | DCP - Train 09 - Warranty Period | 08/10/2022 | 07/06/2025 | nan | nan | 1224 | TK_NotStart | 1112893334 | 684 | 1112893334_684
C720O147CF###0060180 | TT_Task | DCP - Train 08 - Warranty Period | 01/10/2022 | 30/06/2025 | nan | nan | 1040 | TK_NotStart | 1112893334 | 684 | 1112893334_684
C720O147CF###0060190 | TT_Task | DCP - Train 07 - Warranty Period | 24/09/2022 | 24/07/2025 | nan | nan | 848 | TK_NotStart | 1112893334 | 684 | 1112893334_684
C720O147CF###0060200 | TT_Task | DCP - Train 06 - Warranty Period | 17/09/2022 | 17/08/2025 | nan | nan | 656 | TK_NotStart | 1112893334 | 684 | 1112893334_684
C720O147CF###0060210 | TT_Task | DCP - Train 05 - Warranty Period | 10/09/2022 | 10/08/2025 | nan | nan | 712 | TK_NotStart | 1112893334 | 684 | 1112893334_684
C720O147CF###0060220 | TT_Task | DCP - Train 04 - Warranty Period | 03/09/2022 | 03/08/2025 | nan | nan | 768 | TK_NotStart | 1112893334 | 684 | 1112893334_684
C720O147CF###0060230 | TT_Task | DCP - Train 03 - Warranty Period | 22/08/2022 | 21/08/2025 | nan | nan | 624 | TK_NotStart | 1112893334 | 684 | 1112893334_684
C720O147CF###0060240 | TT_Task | DCP - Train 02 - Warranty Period | 15/08/2022 | 15/09/2025 | nan | nan | 424 | TK_NotStart | 1112893334 | 684 | 1112893334_684
C720O147CF###0060250 | TT_Task | DCP - Train 23 - Warranty Period | 01/06/2023 | 31/05/2025 | nan | nan | 1280 | TK_NotStart | 1112893334 | 684 | 1112893334_684
C730T157CT###0056780 | TT_Task | City SAT 1 - CBTC functional | 22/03/2023 | 04/04/2023 | nan | nan | 0 | TK_NotStart | 1112893334 | 683 | 1112893334_683
C730T157CT###0056790 | TT_Task | City SAT 1 - CBTC functional (rework) | 25/04/2023 | 08/05/2023 | nan | nan | 0 | TK_NotStart | 1112893334 | 683 | 1112893334_683
C730T157CT###0056800 | TT_Task | City SAT 2 - CBTC performance ; operation | 05/04/2023 | 13/04/2023 | nan | nan | 0 | TK_NotStart | 1112893334 | 683 | 1112893334_683
C730T157CT###0056810 | TT_Task | City SAT 3 - MSS functional | 14/04/2023 | 24/04/2023 | nan | nan | 0 | TK_NotStart | 1112893334 | 683 | 1112893334_683
C730T157CT###0056130 | TT_Task | Low Speed City SIT 14 - ATO fine tunning test - T1 &gt; T4 | 15/02/2023 | 20/02/2023 | nan | nan | 0 | TK_NotStart | 1112893334 | 682 | 1112893334_682
C730T157CT###0056180 | TT_Task | High Speed City SIT 14 - ATO fine tunning test - T1 &gt; T4 | 20/03/2023 | 21/03/2023 | nan | nan | 0 | TK_NotStart | 1112893334 | 682 | 1112893334_682
C730T157CT###0056070 | TT_Task | Low Speed City SIT 12 - TDC dynamic test (Part 1) | 18/01/2023 | 20/01/2023 | nan | nan | 0 | TK_NotStart | 1112893334 | 681 | 1112893334_681
C730T157CT###0056110 | TT_Task | Low Speed City SIT 12 - Track Data Checking (Part 2) | 06/02/2023 | 07/02/2023 | nan | nan | 0 | TK_NotStart | 1112893334 | 681 | 1112893334_681
C730T157CT###0056120 | TT_Task | Low Speed City SIT 13 - System DB trackside dynamic test (Part 1) | 08/02/2023 | 14/02/2023 | nan | nan | 0 | TK_NotStart | 1112893334 | 681 | 1112893334_681
C730T157CT###0056160 | TT_Task | Low Speed City SIT 13 - System DB trackside dynamic test (Part 2) | 24/02/2023 | 28/02/2023 | nan | nan | 0 | TK_NotStart | 1112893334 | 681 | 1112893334_681
C730T157CT###0056170 | TT_Task | High Speed City SIT 13 - System DB trackside dynamic test | 15/03/2023 | 17/03/2023 | nan | nan | 0 | TK_NotStart | 1112893334 | 681 | 1112893334_681
C730T157CT###0056090 | TT_Task | All City Section SIT 2 - CLC / SMIO static route testing AxCo only | 11/01/2023 | 20/01/2023 | nan | nan | 0 | TK_NotStart | 1112893334 | 680 | 1112893334_680
C730T157CT###0056140 | TT_Task | All City Section SIT 4 SMIO/PSD integration tests | 21/02/2023 | 22/02/2023 | nan | nan | 0 | TK_NotStart | 1112893334 | 680 | 1112893334_680
C730T157CT###0056060 | TT_Task | Low Speed City SIT 2 - CLC/SMIO integration test | 18/01/2023 | 20/01/2023 | nan | nan | 80 | TK_NotStart | 1112893334 | 680 | 1112893334_680
C720P147CF###0031080 | TT_Task | BA Floor covering | 25/02/2020 | 17/03/2020 | 05/12/2019 | 30/04/2020 | 0 | TK_Complete | 1112893334 | 68 | 1112893334_68
C720P147CF###0031290 | TT_Task | PO Floor covering | 25/05/2020 | 15/06/2020 | 04/05/2020 | 04/05/2020 | 0 | TK_Complete | 1112893334 | 68 | 1112893334_68
C720P147CF###0031400 | TT_Task | Production Floor covering | 16/06/2020 | 11/02/2021 | 05/05/2020 | 06/09/2020 | 0 | TK_Complete | 1112893334 | 68 | 1112893334_68
C720P147CF###0032060 | TT_Task | DEL Floor covering | 04/02/2021 | 09/04/2021 | 08/09/2020 | 17/12/2020 | 0 | TK_Complete | 1112893334 | 68 | 1112893334_68
C730T157CT###0056020 | TT_Task | All City Section PAT 7 - ATS Workstation Static test @ Platforms | 20/12/2022 | 10/01/2023 | nan | nan | 0 | TK_NotStart | 1112893334 | 679 | 1112893334_679
C730T157CT###0055980 | TT_Task | All City Section SIT 18 - BTN / backbone integration - City SERs | 02/12/2022 | 19/12/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 678 | 1112893334_678
C730T157CT###0056820 | TT_Task | City SAT Integration (includes Migration) NW ; City | 09/05/2023 | 15/05/2023 | nan | nan | 0 | TK_NotStart | 1112893334 | 678 | 1112893334_678
C730T018CB###N316980 | TT_Task | RS Post Installation Test and CC Static Test for Train 23 | 14/03/2023 | 21/03/2023 | nan | nan | 0 | TK_NotStart | 1112893334 | 677 | 1112893334_677
C730T018CB###N317180 | TT_Task | RS Post Installation Test and CC Static Test for Train 01 | 14/06/2022 | 21/06/2022 | nan | nan | 1560 | TK_NotStart | 1112893334 | 677 | 1112893334_677
C730T018CB###N317190 | TT_Task | RS Post Installation Test and CC Static Test for Train 02 | 14/06/2022 | 21/06/2022 | nan | nan | 1560 | TK_NotStart | 1112893334 | 677 | 1112893334_677
C730T018CB###N317200 | TT_Task | RS Post Installation Test and CC Static Test for Train 03 | 14/06/2022 | 21/06/2022 | nan | nan | 1560 | TK_NotStart | 1112893334 | 677 | 1112893334_677
C730T018CB###N317210 | TT_Task | RS Post Installation Test and CC Static Test for Train 04 | 02/09/2022 | 09/09/2022 | nan | nan | 1096 | TK_NotStart | 1112893334 | 677 | 1112893334_677
C730T018CB###N317220 | TT_Task | RS Post Installation Test and CC Static Test for Train 05 | 09/09/2022 | 16/09/2022 | nan | nan | 1056 | TK_NotStart | 1112893334 | 677 | 1112893334_677
C730T018CB###N317230 | TT_Task | RS Post Installation Test and CC Static Test for Train 06 | 16/09/2022 | 23/09/2022 | nan | nan | 1016 | TK_NotStart | 1112893334 | 677 | 1112893334_677
C730T018CB###N317240 | TT_Task | RS Post Installation Test and CC Static Test for Train 07 | 23/09/2022 | 30/09/2022 | nan | nan | 976 | TK_NotStart | 1112893334 | 677 | 1112893334_677
C730T018CB###N317250 | TT_Task | RS Post Installation Test and CC Static Test for Train 08 | 30/09/2022 | 07/10/2022 | nan | nan | 936 | TK_NotStart | 1112893334 | 677 | 1112893334_677
C730T018CB###N317260 | TT_Task | RS Post Installation Test and CC Static Test for Train 09 | 07/10/2022 | 14/10/2022 | nan | nan | 896 | TK_NotStart | 1112893334 | 677 | 1112893334_677
C730T018CB###N317270 | TT_Task | RS Post Installation Test and CC Static Test for Train 10 | 14/10/2022 | 21/10/2022 | nan | nan | 856 | TK_NotStart | 1112893334 | 677 | 1112893334_677
C730T018CB###N317280 | TT_Task | RS Post Installation Test and CC Static Test for Train 11 | 21/10/2022 | 28/10/2022 | nan | nan | 816 | TK_NotStart | 1112893334 | 677 | 1112893334_677
C730T018CB###N317290 | TT_Task | RS Post Installation Test and CC Static Test for Train 12 | 28/10/2022 | 04/11/2022 | nan | nan | 776 | TK_NotStart | 1112893334 | 677 | 1112893334_677
C730T018CB###N317300 | TT_Task | RS Post Installation Test and CC Static Test for Train 13 | 04/11/2022 | 11/11/2022 | nan | nan | 736 | TK_NotStart | 1112893334 | 677 | 1112893334_677
C730T018CB###N317310 | TT_Task | RS Post Installation Test and CC Static Test for Train 14 | 11/11/2022 | 18/11/2022 | nan | nan | 696 | TK_NotStart | 1112893334 | 677 | 1112893334_677
C730T018CB###N317320 | TT_Task | RS Post Installation Test and CC Static Test for Train 15 | 18/11/2022 | 25/11/2022 | nan | nan | 656 | TK_NotStart | 1112893334 | 677 | 1112893334_677
C730T018CB###N317330 | TT_Task | RS Post Installation Test and CC Static Test for Train 16 | 25/11/2022 | 02/12/2022 | nan | nan | 616 | TK_NotStart | 1112893334 | 677 | 1112893334_677
C730T018CB###N317340 | TT_Task | RS Post Installation Test and CC Static Test for Train 17 | 02/12/2022 | 09/12/2022 | nan | nan | 576 | TK_NotStart | 1112893334 | 677 | 1112893334_677
C730T018CB###N317350 | TT_Task | RS Post Installation Test and CC Static Test for Train 18 | 12/12/2022 | 19/12/2022 | nan | nan | 528 | TK_NotStart | 1112893334 | 677 | 1112893334_677
C730T018CB###N317360 | TT_Task | RS Post Installation Test and CC Static Test for Train 19 | 19/12/2022 | 26/12/2022 | nan | nan | 488 | TK_NotStart | 1112893334 | 677 | 1112893334_677
C730T018CB###N317370 | TT_Task | RS Post Installation Test and CC Static Test for Train 20 | 16/01/2023 | 23/01/2023 | nan | nan | 328 | TK_NotStart | 1112893334 | 677 | 1112893334_677
C730T018CB###N317380 | TT_Task | RS Post Installation Test and CC Static Test for Train 21 | 06/02/2023 | 13/02/2023 | nan | nan | 208 | TK_NotStart | 1112893334 | 677 | 1112893334_677
C730T018CB###N317390 | TT_Task | RS Post Installation Test and CC Static Test for Train 22 | 20/02/2023 | 27/02/2023 | nan | nan | 128 | TK_NotStart | 1112893334 | 677 | 1112893334_677
C730T018CB###N317100 | TT_Task | SMTF-[N] MS2 CCS Visual Inspection Test | 25/11/2021 | 25/11/2021 | 25/11/2021 | 25/11/2021 | 0 | TK_Complete | 1112893334 | 676 | 1112893334_676
C730T018CB###N317110 | TT_Task | SMTF-[N] MS2 CCS Point to point Tests | 26/11/2021 | 26/11/2021 | 26/11/2021 | 26/11/2021 | 0 | TK_Complete | 1112893334 | 676 | 1112893334_676
C730T018CB###N317120 | TT_Task | SMTF-[N] MS2 CCS End to end tests | 29/11/2021 | 29/11/2021 | 29/11/2021 | 29/11/2021 | 0 | TK_Complete | 1112893334 | 676 | 1112893334_676
C730T018CB###N317130 | TT_Task | SMTF-[N] MS2 CCS Functional tests | 30/11/2021 | 02/12/2021 | 30/11/2021 | 02/12/2021 | 0 | TK_Complete | 1112893334 | 676 | 1112893334_676
C730T018CB###N317140 | TT_Task | SMTF-[N] MS4 CCS Visual Inspection Test | 25/02/2022 | 25/02/2022 | 24/02/2022 | 24/02/2022 | 0 | TK_Complete | 1112893334 | 676 | 1112893334_676
C730T018CB###N317150 | TT_Task | SMTF-[N] MS4 CCS Point to point Tests | 25/03/2022 | 25/03/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 676 | 1112893334_676
C730T018CB###N317160 | TT_Task | SMTF-[N] MS4 CCS End to end tests | 28/03/2022 | 28/03/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 676 | 1112893334_676
C730T018CB###N317170 | TT_Task | SMTF-[N] MS4 CCS Functional tests | 29/03/2022 | 31/03/2022 | nan | nan | 280 | TK_NotStart | 1112893334 | 676 | 1112893334_676
C730T018CB###N317060 | TT_Task | SMTF-[N] MS2 Post Installation Inspection and Test | 25/11/2021 | 25/11/2021 | 25/11/2021 | 25/11/2021 | 0 | TK_Complete | 1112893334 | 675 | 1112893334_675
C730T018CB###N317090 | TT_Task | SMTF-[N] MS4 Post Installation Inspection and Test | 08/12/2021 | 09/12/2021 | 08/12/2021 | 09/12/2021 | 0 | TK_Complete | 1112893334 | 675 | 1112893334_675
C730T018CB###N317040 | TT_Task | SMTF-[N] MS2 Integration test of RAD with train | 30/11/2021 | 02/12/2021 | 30/11/2021 | 02/12/2021 | 0 | TK_Complete | 1112893334 | 674 | 1112893334_674
C730T018CB###N317050 | TT_Task | SMTF-[N] MS2 Integration test of RAD without train | 26/11/2021 | 29/11/2021 | 26/11/2021 | 29/11/2021 | 0 | TK_Complete | 1112893334 | 674 | 1112893334_674
C730T018CB###N317070 | TT_Task | SMTF-[N] MS4 Integration test of RAD with train | 17/05/2022 | 20/05/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 674 | 1112893334_674
C730T018CB###N317080 | TT_Task | SMTF-[N] MS4 Integration test of RAD without train | 30/03/2022 | 01/04/2022 | nan | nan | 256 | TK_NotStart | 1112893334 | 674 | 1112893334_674
C730T018CB###N316910 | TT_Task | City RAD Post Installation Inspection and Test | 12/09/2022 | 13/09/2022 | nan | nan | 512 | TK_NotStart | 1112893334 | 673 | 1112893334_673
C730T018CB###N316920 | TT_Task | City RAD Integration test of RAD without train | 12/12/2022 | 14/12/2022 | nan | nan | 169 | TK_NotStart | 1112893334 | 673 | 1112893334_673
C730T018CB###N316930 | TT_Task | City RAD Integration test of RAD with train | 04/04/2023 | 07/04/2023 | nan | nan | 209 | TK_NotStart | 1112893334 | 673 | 1112893334_673
C730T018CB###N316900 | TT_Task | City COM Interface Functional Tests | 04/04/2023 | 07/04/2023 | nan | nan | 209 | TK_NotStart | 1112893334 | 672 | 1112893334_672
C730T018CB###N316950 | TT_Task | City CCS Point to point Tests | 10/01/2023 | 11/01/2023 | nan | nan | 0 | TK_NotStart | 1112893334 | 672 | 1112893334_672
C730T018CB###N316960 | TT_Task | City CCS End to end tests | 11/01/2023 | 12/01/2023 | nan | nan | 1 | TK_NotStart | 1112893334 | 672 | 1112893334_672
C730T018CB###N316970 | TT_Task | City CCS Functional tests | 04/04/2023 | 07/04/2023 | nan | nan | 209 | TK_NotStart | 1112893334 | 672 | 1112893334_672
C730T018CB###N316890 | TT_Task | City COM Visual Inspection Tests | 12/09/2022 | 13/09/2022 | nan | nan | 697 | TK_NotStart | 1112893334 | 671 | 1112893334_671
C730T018CB###N316940 | TT_Task | City CCS Visual Inspection Test | 12/09/2022 | 13/09/2022 | nan | nan | 680 | TK_NotStart | 1112893334 | 671 | 1112893334_671
C730T157CT###N357383 | TT_Task | Barangaroo PSD-SIG-IT-02 - Static Functional Test (without train) | 07/11/2022 | 07/11/2022 | nan | nan | 584 | TK_NotStart | 1112893334 | 670 | 1112893334_670
C730T157CT###N357393 | TT_Task | Martin Place PSD-SIG-IT-02 - Static Functional Test (without train) | 23/11/2022 | 23/11/2022 | nan | nan | 496 | TK_NotStart | 1112893334 | 670 | 1112893334_670
C730T157CT###N357403 | TT_Task | Pitt Street PSD-SIG-IT-02 - Static Functional Test (without train) | 30/11/2022 | 30/11/2022 | nan | nan | 464 | TK_NotStart | 1112893334 | 670 | 1112893334_670
C730T157CT###N357413 | TT_Task | Central PSD-SIG-IT-02 - Static Functional Test (without train) | 16/11/2022 | 16/11/2022 | nan | nan | 552 | TK_NotStart | 1112893334 | 670 | 1112893334_670
C730T157CT###N357423 | TT_Task | Waterloo PSD-SIG-IT-02 - Static Functional Test (without train) | 25/10/2022 | 25/10/2022 | nan | nan | 688 | TK_NotStart | 1112893334 | 670 | 1112893334_670
C730T157CT###N357433 | TT_Task | Sydenham PSD-SIG-IT-02 - Static Functional Test (without train) | 22/09/2022 | 22/09/2022 | nan | nan | 880 | TK_NotStart | 1112893334 | 670 | 1112893334_670
C730T157CT###N357463 | TT_Task | Barangaroo PSD-SIG-IT-03 Integrated Functional Test (with Train) | 17/02/2023 | 17/02/2023 | nan | nan | 0 | TK_NotStart | 1112893334 | 670 | 1112893334_670
C720P147CF###0031030 | TT_Task | BA PACIS | 25/02/2020 | 24/03/2020 | 05/12/2019 | 28/02/2020 | 0 | TK_Complete | 1112893334 | 67 | 1112893334_67
C720P147CF###0031640 | TT_Task | PO PACIS | 25/03/2020 | 30/04/2020 | 02/03/2020 | 06/04/2020 | 0 | TK_Complete | 1112893334 | 67 | 1112893334_67
C720P147CF###0031650 | TT_Task | Production PACIS | 25/05/2020 | 04/02/2021 | 27/04/2020 | 28/10/2020 | 0 | TK_Complete | 1112893334 | 67 | 1112893334_67
C720P147CF###0032280 | TT_Task | DEL PACIS | 11/11/2020 | 01/12/2020 | 03/11/2020 | 20/11/2020 | 0 | TK_Complete | 1112893334 | 67 | 1112893334_67
C730T157CT###N357363 | TT_Task | Crows Nest PSD-SIG-IT-02 - Static Functional Test (without train) | 25/10/2022 | 25/10/2022 | nan | nan | 640 | TK_NotStart | 1112893334 | 669 | 1112893334_669
C730T157CT###N357373 | TT_Task | Victoria Cross PSD-SIG-IT-02 - Static Functional Test (without train) | 02/12/2022 | 02/12/2022 | nan | nan | 424 | TK_NotStart | 1112893334 | 669 | 1112893334_669
C730T157CT###N357443 | TT_Task | Crows Nest PSD-SIG-IT-03 Integrated Functional Test (with Train) | 15/02/2023 | 15/02/2023 | nan | nan | 0 | TK_NotStart | 1112893334 | 669 | 1112893334_669
C730T157CT###N357453 | TT_Task | Victoria Cross PSD-SIG-IT-03 Integrated Functional Test (with Train) | 16/02/2023 | 16/02/2023 | nan | nan | 0 | TK_NotStart | 1112893334 | 669 | 1112893334_669
C730T157CT###N357473 | TT_Task | Martin Place PSD-SIG-IT-03 Integrated Functional Test (with Train) | 20/02/2023 | 20/02/2023 | nan | nan | 0 | TK_NotStart | 1112893334 | 669 | 1112893334_669
C730T157CT###N357483 | TT_Task | Pitt Street PSD-SIG-IT-03 Integrated Functional Test (with Train) | 21/02/2023 | 21/02/2023 | nan | nan | 0 | TK_NotStart | 1112893334 | 669 | 1112893334_669
C730T157CT###N357493 | TT_Task | Central PSD-SIG-IT-03 Integrated Functional Test (with Train) | 22/02/2023 | 22/02/2023 | nan | nan | 0 | TK_NotStart | 1112893334 | 669 | 1112893334_669
C730T157CT###N357503 | TT_Task | Waterloo PSD-SIG-IT-03 Integrated Functional Test (with Train) | 23/02/2023 | 23/02/2023 | nan | nan | 0 | TK_NotStart | 1112893334 | 669 | 1112893334_669
C730T157CT###N357513 | TT_Task | Sydenham PSD-SIG-IT-03 Integrated Functional Test (with Train) | 24/02/2023 | 24/02/2023 | nan | nan | 160 | TK_NotStart | 1112893334 | 669 | 1112893334_669
C730T157CT###N357283 | TT_Task | Crows Nest PSD-SIG-IT-01- Post-installation Check (power de-energized) | 10/08/2022 | 10/08/2022 | nan | nan | 424 | TK_NotStart | 1112893334 | 668 | 1112893334_668
C730T157CT###N357293 | TT_Task | Victoria Cross PSD-SIG-IT-01- Post-installation Check (power de-energized) | 23/11/2022 | 23/11/2022 | nan | nan | 48 | TK_NotStart | 1112893334 | 668 | 1112893334_668
C730T157CT###N357303 | TT_Task | Barangaroo PSD-SIG-IT-01- Post-installation Check (power de-energized) | 24/10/2022 | 24/10/2022 | nan | nan | 72 | TK_NotStart | 1112893334 | 668 | 1112893334_668
C730T157CT###N357313 | TT_Task | Martin Place PSD-SIG-IT-01- Post-installation Check (power de-energized) | 22/09/2022 | 22/09/2022 | nan | nan | 344 | TK_NotStart | 1112893334 | 668 | 1112893334_668
C730T157CT###N357323 | TT_Task | Pitt Street PSD-SIG-IT-01- Post-installation Check (power de-energized) | 22/09/2022 | 22/09/2022 | nan | nan | 384 | TK_NotStart | 1112893334 | 668 | 1112893334_668
C730T157CT###N357333 | TT_Task | Central PSD-SIG-IT-01- Post-installation Check (power de-energized) | 04/11/2022 | 04/11/2022 | nan | nan | 56 | TK_NotStart | 1112893334 | 668 | 1112893334_668
C730T157CT###N357343 | TT_Task | Waterloo PSD-SIG-IT-01- Post-installation Check (power de-energized) | 08/09/2022 | 08/09/2022 | nan | nan | 256 | TK_NotStart | 1112893334 | 668 | 1112893334_668
C730T157CT###N357353 | TT_Task | Sydenham PSD-SIG-IT-01- Post-installation Check (power de-energized) | 13/09/2022 | 13/09/2022 | nan | nan | 48 | TK_NotStart | 1112893334 | 668 | 1112893334_668
C730T157CS###0055170 | TT_Task | PAT 2.1 - Point Machine test (Waterloo to Sydenham) | 21/10/2022 | 26/10/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 667 | 1112893334_667
C730T157C5###0055790 | TT_Task | PAT 2.1 - Point Machine test (Victoria Cross to Barangaroo) | 07/11/2022 | 08/11/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 667 | 1112893334_667
C730T157CT###0056010 | TT_Task | PAT 2.1 - Point Machine test (Sydenham to SMTF-[S]) | 01/12/2022 | 08/12/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 667 | 1112893334_667
C730T157CT###0055050 | TT_Task | CER - City ; BOCC SIT 18 - DCS wired integration test | 18/07/2022 | 19/07/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 666 | 1112893334_666
C730T157CT###0056080 | TT_Task | Low Speed City SIT 19 - DCS/CCTV Radio coverage test | 18/01/2023 | 20/01/2023 | nan | nan | 0 | TK_NotStart | 1112893334 | 666 | 1112893334_666
C730T157CT###0056150 | TT_Task | Low Speed City SIT 20 - DCS/CCTV End to End communication test | 23/02/2023 | 23/02/2023 | nan | nan | 0 | TK_NotStart | 1112893334 | 666 | 1112893334_666
C730T157CT###0055010 | TT_Task | CER - City ; BOCC PAT 1 - PDC static test | 17/05/2022 | 23/05/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 665 | 1112893334_665
C730T157CT###0055020 | TT_Task | CER - City ; BOCC PAT 4 - CLC cubicle testing | 24/05/2022 | 26/05/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 665 | 1112893334_665
C730T157CT###0055040 | TT_Task | CER - City ; BOCC PAT 11 - CCTV CER/OCC Equipment test | 24/05/2022 | 25/05/2022 | nan | nan | 1312 | TK_NotStart | 1112893334 | 665 | 1112893334_665
C730T157CT###0055060 | TT_Task | CER - City ; BOCC PAT 5 - ZC/LC Static Test | 27/05/2022 | 31/05/2022 | nan | nan | 1344 | TK_NotStart | 1112893334 | 665 | 1112893334_665
C730T157CT###0055070 | TT_Task | CER - City ; BOCC PAT 7 - ATS Equipment static test | 20/07/2022 | 16/08/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 665 | 1112893334_665
C730T157CT###0055100 | TT_Task | CER - City ; BOCC PAT 8 - MSS Static Test | 17/08/2022 | 22/08/2022 | nan | nan | 792 | TK_NotStart | 1112893334 | 665 | 1112893334_665
C730T157C5###0055710 | TT_Task | Barangaroo Installation to T;C handover | 17/10/2022 | 21/10/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 664 | 1112893334_664
C730T157C4###0055840 | TT_Task | Victoria Cross PAT 3 - SMIO cubicle testing | 30/11/2022 | 01/12/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 663 | 1112893334_663
C730T157C4###0055820 | TT_Task | Victoria Cross Installation to T;C handover | 16/11/2022 | 22/11/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 662 | 1112893334_662
C730T157C6###0055210 | TT_Task | Martin Place Installation to T;C handover | 15/09/2022 | 21/09/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 662 | 1112893334_662
C730T157C7###0055430 | TT_Task | Pitt Street Installation to T;C handover | 15/09/2022 | 21/09/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 662 | 1112893334_662
C730T157CR###0055390 | TT_Task | Central Installation to T;C handover | 28/10/2022 | 03/11/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 662 | 1112893334_662
C730T157C8###0055220 | TT_Task | Waterloo Installation to T;C handover | 01/09/2022 | 07/09/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 662 | 1112893334_662
C730T157CT###0055000 | TT_Task | CER - City ; BOCC Installation to T;C handover | 10/05/2022 | 16/05/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 662 | 1112893334_662
C730T157CT###0055910 | TT_Task | CSW Depot SER Installation to T;C handover | 07/11/2022 | 11/11/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 662 | 1112893334_662
C730T157C3###0055610 | TT_Task | Crows Nest SIT 1 - SMIO/Wayside equipment correspondence test | 25/10/2022 | 02/11/2022 | nan | nan | 392 | TK_NotStart | 1112893334 | 661 | 1112893334_661
C730T157C4###0055900 | TT_Task | Victoria Cross SIT 1 - SMIO/Wayside equipment correspondence test | 02/12/2022 | 08/12/2022 | nan | nan | 184 | TK_NotStart | 1112893334 | 661 | 1112893334_661
C730T157C5###0055810 | TT_Task | Barangaroo SIT 1 - SMIO/Wayside equipment correspondence test | 09/11/2022 | 15/11/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 661 | 1112893334_661
C730T157C6###0055310 | TT_Task | Martin Place SIT 1 - SMIO/Wayside equipment correspondence test | 23/11/2022 | 29/11/2022 | nan | nan | 240 | TK_NotStart | 1112893334 | 661 | 1112893334_661
C730T157C7###0055720 | TT_Task | Pitt Street SIT 1 - SMIO/Wayside equipment correspondence test | 07/12/2022 | 13/12/2022 | nan | nan | 160 | TK_NotStart | 1112893334 | 661 | 1112893334_661
C730T157CR###0055560 | TT_Task | Central SIT 1 - SMIO/Wayside equipment correspondence test | 16/11/2022 | 22/11/2022 | nan | nan | 280 | TK_NotStart | 1112893334 | 661 | 1112893334_661
C730T157C8###0055380 | TT_Task | Waterloo SIT 1 - SMIO/Wayside equipment correspondence test | 21/10/2022 | 27/10/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 661 | 1112893334_661
C730T157CS###0055180 | TT_Task | Sydenham SIT 1 - SMIO/Wayside equipment correspondence test | 21/10/2022 | 07/11/2022 | nan | nan | 368 | TK_NotStart | 1112893334 | 661 | 1112893334_661
C730T157CT###0056000 | TT_Task | CSW Depot SER SIT 1 - SMIO/Wayside equipment correspondence test | 01/12/2022 | 10/01/2023 | nan | nan | 0 | TK_NotStart | 1112893334 | 661 | 1112893334_661
C730T157C3###0055520 | TT_Task | Crows Nest PAT 3 - SMIO static test | 21/10/2022 | 24/10/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 660 | 1112893334_660
C730T157C5###0055740 | TT_Task | Barangaroo PAT 3 - SMIO static test | 03/11/2022 | 04/11/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 660 | 1112893334_660
C730T157C6###0055250 | TT_Task | Martin Place PAT 3 - SMIO static test | 21/11/2022 | 22/11/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 660 | 1112893334_660
C730T157C7###0055620 | TT_Task | Pitt Street PAT 3 - SMIO static test | 28/11/2022 | 29/11/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 660 | 1112893334_660
C730T157CR###0055470 | TT_Task | Central PAT 3 - SMIO static test | 14/11/2022 | 15/11/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 660 | 1112893334_660
C730T157C8###0055320 | TT_Task | Waterloo PAT 3 - SMIO static test | 21/10/2022 | 24/10/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 660 | 1112893334_660
C730T157CS###0055110 | TT_Task | Sydenham PAT 3 - SMIO static test | 20/09/2022 | 21/09/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 660 | 1112893334_660
C730T157CT###0055960 | TT_Task | CSW Depot SER PAT 3 - SMIO static test | 21/11/2022 | 30/11/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 660 | 1112893334_660
C720P147CF###0031000 | TT_Task | BA Gangway | 25/02/2020 | 17/03/2020 | 05/12/2019 | 19/03/2020 | 0 | TK_Complete | 1112893334 | 66 | 1112893334_66
C720P147CF###0031180 | TT_Task | PO Gangway | 27/04/2020 | 15/05/2020 | 26/03/2020 | 30/03/2020 | 0 | TK_Complete | 1112893334 | 66 | 1112893334_66
C720P147CF###0031270 | TT_Task | Production Gangway | 18/05/2020 | 11/02/2021 | 09/04/2020 | 04/12/2020 | 0 | TK_Complete | 1112893334 | 66 | 1112893334_66
C720P147CF###0032070 | TT_Task | DEL Gangway | 11/01/2021 | 01/02/2021 | 04/12/2020 | 14/12/2020 | 0 | TK_Complete | 1112893334 | 66 | 1112893334_66
C730T157C3###0055450 | TT_Task | Crows Nest PAT 1 - PDC static test | 14/10/2022 | 20/10/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 659 | 1112893334_659
C730T157C4###0055830 | TT_Task | Victoria Cross PAT 1 - PDC static test | 23/11/2022 | 29/11/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 659 | 1112893334_659
C730T157C5###0055730 | TT_Task | Barangaroo PAT 1 - PDC static test | 27/10/2022 | 02/11/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 659 | 1112893334_659
C730T157C6###0055230 | TT_Task | Martin Place PAT 1 - PDC static test | 14/11/2022 | 18/11/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 659 | 1112893334_659
C730T157C7###0055460 | TT_Task | Pitt Street PAT 1 - PDC static test | 21/11/2022 | 25/11/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 659 | 1112893334_659
C730T157CR###0055440 | TT_Task | Central PAT 1 - PDC static test | 07/11/2022 | 11/11/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 659 | 1112893334_659
C730T157C8###0055240 | TT_Task | Waterloo PAT 1 - PDC static test | 14/10/2022 | 20/10/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 659 | 1112893334_659
C730T157CS###0055090 | TT_Task | Sydenham PAT 1 - PDC static test | 13/09/2022 | 19/09/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 659 | 1112893334_659
C730T157CT###0055920 | TT_Task | CSW Depot SER PAT 1 - PDC Testing | 14/11/2022 | 18/11/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 659 | 1112893334_659
C730T157BG###0055410 | TT_Task | Chatswood PAT 6.2 - DCS backbone static test | 06/09/2022 | 22/09/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 658 | 1112893334_658
C730T157C3###0055530 | TT_Task | Crows Nest PAT 6.2 - DCS backbone static test | 21/10/2022 | 24/10/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 658 | 1112893334_658
C730T157C4###0055850 | TT_Task | Victoria Cross PAT 6.2 - DCS backbone static test | 30/11/2022 | 01/12/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 658 | 1112893334_658
C730T157C5###0055750 | TT_Task | Barangaroo PAT 6.2 - DCS backbone static test | 03/11/2022 | 04/11/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 658 | 1112893334_658
C730T157C6###0055260 | TT_Task | Martin Place PAT 6.2 - DCS backbone static test | 21/11/2022 | 22/11/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 658 | 1112893334_658
C730T157C7###0055630 | TT_Task | Pitt Street PAT 6.2 - DCS backbone static test | 28/11/2022 | 29/11/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 658 | 1112893334_658
C730T157CR###0055480 | TT_Task | Central PAT 6.2 - DCS backbone static test | 14/11/2022 | 15/11/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 658 | 1112893334_658
C730T157C8###0055330 | TT_Task | Waterloo PAT 6.2 - DCS backbone static test | 21/10/2022 | 24/10/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 658 | 1112893334_658
C730T157CS###0055120 | TT_Task | Sydenham PAT 6.2 - DCS backbone static test | 20/09/2022 | 21/09/2022 | nan | nan | 168 | TK_NotStart | 1112893334 | 658 | 1112893334_658
C730T157CT###0055030 | TT_Task | CER - City ; BOCC PAT 6.2 - DCS backbone static test | 24/05/2022 | 25/05/2022 | nan | nan | 296 | TK_NotStart | 1112893334 | 658 | 1112893334_658
C730T157CT###0055940 | TT_Task | CSW Depot SER PAT 6.2 - DCS backbone static test | 21/11/2022 | 22/11/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 658 | 1112893334_658
C730C147BC###N070711 | TT_Task | SMTF[N] Stage2 - Static T;C [PATs] (Rd 5-8) | 01/12/2021 | 05/01/2022 | 22/06/2021 | 11/09/2021 | 0 | TK_Complete | 1112893334 | 657 | 1112893334_657
C730C147BC###N070713 | TT_Task | SMTF[N] Stage2 - Static T;C [SITs] (Rd 5-8) | 05/01/2022 | 27/01/2022 | 07/07/2021 | 18/02/2022 | 0 | TK_Complete | 1112893334 | 657 | 1112893334_657
C730C147BC###N070723 | TT_Task | SMTF[N] Stage2 - Dynamic - Low Speed T;C (Rd 5-8) | 29/03/2022 | 01/04/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 657 | 1112893334_657
C730C147BC###N070729 | TT_Task | SMTF[N] Stage2 - SIT19/SIT20 (Rd 5-8) | 29/03/2022 | 01/04/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 657 | 1112893334_657
C730T147BC###0050080 | TT_Task | SMTF[N] Stage2 - Static T;C (remaining expansion Rd24-30 - DCS/ATS) | 30/11/2021 | 31/12/2021 | 07/07/2021 | 18/02/2022 | 0 | TK_Complete | 1112893334 | 657 | 1112893334_657
C730T147BC###0050120 | TT_Task | SMTF[N] Stage2 - TDC (remaining expansion Rd24-30, including Rd5 to 8) | 23/12/2021 | 05/01/2022 | 25/09/2021 | 18/12/2021 | 0 | TK_Complete | 1112893334 | 657 | 1112893334_657
C730T147BC###0050140 | TT_Task | SMTF[N] Stage2 - Dynamic T;C- Low Speed (remaining expansion Rd24-30) | 29/03/2022 | 01/04/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 657 | 1112893334_657
C730T147BC###0050153 | TT_Task | SMTF[N] Stage2 - Static T;C (remaining expansion Rd24-30 - IXL/ATC) | 09/11/2021 | 01/12/2021 | 22/06/2021 | 11/09/2021 | 0 | TK_Complete | 1112893334 | 657 | 1112893334_657
C730T147BC###N501777 | TT_Task | SMTF[N] Stage1 - ATS/MSS SIT Integration Tests | 31/08/2021 | 02/09/2021 | 13/07/2021 | 15/07/2021 | 0 | TK_Complete | 1112893334 | 656 | 1112893334_656
C730T147BC###0050154 | TT_Task | SMTF[N] Stage1 - SAT (System Acceptance Tests) (Train is needed) includes Interface tests | 10/11/2021 | 15/12/2021 | 14/09/2021 | 11/11/2021 | 0 | TK_Complete | 1112893334 | 656 | 1112893334_656
C730T147BC###0050165 | TT_Task | SMTF[N] Stage2 - SAT+Interface Tests (System Acceptance Tests) (remaining expansion Rd24-30, including Rd5 to 8) | 07/04/2022 | 20/05/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 656 | 1112893334_656
C730T147BC###N501767 | TT_Task | SMTF[N] Stage1 - DCS - CCTV SIT Integration Tests | 09/06/2021 | 10/06/2021 | 19/05/2021 | 26/05/2021 | 0 | TK_Complete | 1112893334 | 655 | 1112893334_655
C730T147BC###N7565 | TT_Task | SMTF[N] Stage1 - DCS - CCTV PAT Static Tests | 01/06/2021 | 14/06/2021 | 11/05/2021 | 26/05/2021 | 0 | TK_Complete | 1112893334 | 655 | 1112893334_655
C730T147BC###0050070 | TT_Task | SMTF[N] Stage1 - Test Track and Stab 31-35 Track Survey | 25/01/2021 | 27/01/2021 | 15/01/2021 | 20/01/2021 | 0 | TK_Complete | 1112893334 | 654 | 1112893334_654
C730T147BC###0050090 | TT_Task | SMTF[N] Stage1 - Stab 31-35 TDC (Train is needed) | 01/06/2021 | 07/06/2021 | 16/05/2021 | 08/06/2021 | 0 | TK_Complete | 1112893334 | 654 | 1112893334_654
C730T147BC###0050100 | TT_Task | SMTF[N] Stage1 - Test track and Stab 31-35 Dynamic tests (Train is needed) low speed regression | 21/10/2021 | 10/11/2021 | 16/09/2021 | 17/09/2021 | 0 | TK_Complete | 1112893334 | 654 | 1112893334_654
C730T147BC###N50165 | TT_Task | SMTF[N] Stage1 - Stab 31-35 Radio coverage (Train is needed) (linked to delay caused by Covid lockdown) | 29/09/2021 | 21/10/2021 | 31/08/2021 | 10/09/2021 | 0 | TK_Complete | 1112893334 | 654 | 1112893334_654
C730T147BC###N501787 | TT_Task | SMTF[N] Stage1 - Stab 31-35 Radio coverage (Train is needed) (linked to delay caused by CCB and Track Milling issue) | 31/08/2021 | 22/09/2021 | 13/07/2021 | 15/07/2021 | 0 | TK_Complete | 1112893334 | 654 | 1112893334_654
C730T147BC###0050020 | TT_Task | SMTF[N] Stage1 - Test track Static tests | 25/03/2021 | 23/04/2021 | 22/03/2021 | 16/04/2021 | 0 | TK_Complete | 1112893334 | 653 | 1112893334_653
C730T147BC###0050030 | TT_Task | SMTF[N] Stage1 - CER2/DSER1 Static tests | 11/05/2021 | 24/05/2021 | 09/04/2021 | 31/05/2021 | 0 | TK_Complete | 1112893334 | 653 | 1112893334_653
C730T147BC###0050040 | TT_Task | SMTF[N] Stage1 - CER2/DSER1 Static tests - (Night works) | 18/05/2021 | 18/06/2021 | 09/04/2021 | 04/06/2021 | 0 | TK_Complete | 1112893334 | 653 | 1112893334_653
C730T147BC###0050050 | TT_Task | SMTF[N] Stage1 - DSER2 Static tests | 25/03/2021 | 16/04/2021 | 22/03/2021 | 16/04/2021 | 0 | TK_Complete | 1112893334 | 653 | 1112893334_653
C730T147BC###0050060 | TT_Task | SMTF[N] Stage1 - Stab 31-35 Static tests | 25/03/2021 | 23/04/2021 | 22/03/2021 | 16/04/2021 | 0 | TK_Complete | 1112893334 | 653 | 1112893334_653
C730T147BC###N501757 | TT_Task | SMTF[N] Stage1 - ATS/MSS PAT Static Tests | 01/06/2021 | 07/06/2021 | 19/05/2021 | 04/06/2021 | 0 | TK_Complete | 1112893334 | 653 | 1112893334_653
C730T147BC###N050165 | TT_Task | SMTF[N] Stage1 - SIAT Completion by MTR and Handover of New Test Track ; Stabling tracks 31-35 to MTS | 05/01/2022 | 09/01/2022 | 11/11/2021 | 06/02/2022 | 0 | TK_Complete | 1112893334 | 652 | 1112893334_652
C730T147BC###N050150 | TT_Task | SMTF[N] Stage2 - SIAT completion by MTR and final handover to MTS (Operator) | 15/06/2022 | 07/08/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 652 | 1112893334_652
C730T147BC###N501654 | TT_Task | SMTF[N] Stage1 - Testing ; Commissioning for MS1 IXL | 25/11/2020 | 24/12/2020 | 21/11/2020 | 06/12/2020 | 0 | TK_Complete | 1112893334 | 651 | 1112893334_651
C730T147BC###N501669 | TT_Task | SMTF[N] Stage1 - Testing ; Commissioning for MS1 ATC | 08/12/2020 | 06/01/2021 | 21/11/2020 | 06/12/2020 | 0 | TK_Complete | 1112893334 | 651 | 1112893334_651
C730T147BC###N501677 | TT_Task | SMTF[N] Stage1 - Testing ; Commissioning for MS1 ATS/MSS SIT3 | 29/12/2020 | 13/01/2021 | 05/12/2020 | 06/12/2020 | 0 | TK_Complete | 1112893334 | 651 | 1112893334_651
C730T147BC###N501687 | TT_Task | SMTF[N] Stage1 - Testing ; Commissioning for MS1 [Initial Works] - WE17 | 31/10/2020 | 01/11/2020 | 24/10/2020 | 24/10/2020 | 0 | TK_Complete | 1112893334 | 651 | 1112893334_651
C730C157CT###0040620 | TT_Task | CAB FO Backbone - Chatswood to Victoria Cross (incl. cable containment ; cable tests) (Scope Included in Detailed Act) | 28/03/2022 | 06/04/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 650 | 1112893334_650
C730C157CT###0040640 | TT_Task | CAB FO Backbone - Victoria Cross to Martin Place (incl. cable containment ; cable tests)(Scope Included in Detailed Act) | 07/04/2022 | 18/04/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 650 | 1112893334_650
C730C157CT###0040730 | TT_Task | CAB FO Backbone - Martin Place to Central (incl. cable containment ; cable tests)(Scope Included in Detailed Act) | 19/04/2022 | 28/04/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 650 | 1112893334_650
C730C157CT###0040750 | TT_Task | CAB FO Backbone - Central to Sydenham (incl. cable containment ; cable tests)(Scope Included in Detailed Act) | 29/04/2022 | 10/05/2022 | nan | nan | 1176 | TK_NotStart | 1112893334 | 650 | 1112893334_650
C730C157CT###0040630 | TT_Task | CAB FO Backbone - North Ryde to Crows Nest (incl. cable containment ; cable tests)(Scope Included in Detailed Act) | 11/08/2022 | 22/08/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 650 | 1112893334_650
C730C157CT###0040650 | TT_Task | CAB FO Backbone - Crows Nest to Barrangaroo (incl. cable containment ; cable tests)(Scope Included in Detailed Act) | 23/08/2022 | 01/09/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 650 | 1112893334_650
C730C157CT###0040740 | TT_Task | CAB FO Backbone - Barrangaroo to Pitt Street (incl. cable containment ; cable tests)(Scope Included in Detailed Act) | 02/09/2022 | 13/09/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 650 | 1112893334_650
C730C157CT###0040760 | TT_Task | CAB FO Backbone - Pitt Street to Waterloo (incl. cable containment ; cable tests)(Scope Included in Detailed Act) | 14/09/2022 | 23/09/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 650 | 1112893334_650
C730C157CT###0040770 | TT_Task | CAB FO Backbone - Waterloo to Sydenham (incl. cable containment ; cable tests)(Scope Included in Detailed Act) | 26/09/2022 | 05/10/2022 | nan | nan | 328 | TK_NotStart | 1112893334 | 650 | 1112893334_650
C720P147CF###0030970 | TT_Task | BA Brakes | 25/02/2020 | 20/03/2020 | 05/12/2019 | 23/03/2020 | 0 | TK_Complete | 1112893334 | 65 | 1112893334_65
C720P147CF###0031280 | TT_Task | PO Brakes | 25/03/2020 | 15/04/2020 | 24/03/2020 | 26/03/2020 | 0 | TK_Complete | 1112893334 | 65 | 1112893334_65
C720P147CF###0031360 | TT_Task | Production Brakes | 25/05/2020 | 18/02/2021 | 02/04/2020 | 04/12/2020 | 0 | TK_Complete | 1112893334 | 65 | 1112893334_65
C720P147CF###0032180 | TT_Task | DEL Brakes | 11/01/2021 | 01/02/2021 | 04/12/2020 | 17/12/2020 | 0 | TK_Complete | 1112893334 | 65 | 1112893334_65
C730C157CT###0040180 | TT_Task | CAB SMN Line Backbone - Terminate DOWN FO cable @ Chatswood(Scope Included in Detailed Act) | 12/05/2022 | 18/05/2022 | nan | nan | 624 | TK_NotStart | 1112893334 | 649 | 1112893334_649
C730C157CT###0040170 | TT_Task | CAB SMN Line Backbone - Terminate UP FO cable @ Chatswood(Scope Included in Detailed Act) | 11/08/2022 | 17/08/2022 | nan | nan | 104 | TK_NotStart | 1112893334 | 649 | 1112893334_649
C730C157CS###D40450 | TT_Task | Cable Installation SER to PIDS (SD-SYD Trackside) | 26/04/2022 | 26/04/2022 | nan | nan | 256 | TK_NotStart | 1112893334 | 648 | 1112893334_648
C730C157CP###TP3200 | TT_Task | Field Cable Termination - PPI (SD-SYD Trackside) | 03/05/2022 | 11/05/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 648 | 1112893334_648
C730C157CS###D40480 | TT_Task | Cable termination PIDS cable on SER end (SD-SYD Trackside) | 08/06/2022 | 09/06/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 648 | 1112893334_648
C730C157CP###TP2730 | TT_Task | Cable Haul - Up CSR (SD-SYD Trackside) | 25/03/2022 | 06/04/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 647 | 1112893334_647
C730C157CP###TP2740 | TT_Task | Cable Haul - Down CSR (SD-SYD Trackside) | 07/04/2022 | 21/04/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 647 | 1112893334_647
C730C157CS###D40460 | TT_Task | Key Switch Mechanical (SD-SYD Trackside) | 29/04/2022 | 02/05/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 646 | 1112893334_646
C730C157CS###D40470 | TT_Task | Key Switch Termination KS End (SD-SYD Trackside) | 03/06/2022 | 07/06/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 646 | 1112893334_646
C730C157CP###TP3230 | TT_Task | Buffer Stop - Mechanical (SD-SYD Trackside) | 28/04/2022 | 28/04/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 645 | 1112893334_645
C730C157CS###D40490 | TT_Task | Buffer Stop - Termination (SD-SYD Trackside) | 31/05/2022 | 02/06/2022 | nan | nan | 24 | TK_NotStart | 1112893334 | 645 | 1112893334_645
C730C157CP###TP3150 | TT_Task | Point Machine DB (SD-SYD Trackside) | 20/04/2022 | 27/04/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 644 | 1112893334_644
C730C157CP###TP3220 | TT_Task | Point Machine Motor (SD-SYD Trackside) | 28/04/2022 | 06/05/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 644 | 1112893334_644
C730C157CP###TP3210 | TT_Task | Point Machine DB Termination (SD-SYD Trackside) | 20/05/2022 | 30/05/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 644 | 1112893334_644
C730C157CP###TP3240 | TT_Task | Point Machine Motor Termination (SD-SYD Trackside) | 31/05/2022 | 02/06/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 644 | 1112893334_644
C730C157CP###TP2700 | TT_Task | DCS/Backbone splice box (SD-SYD Trackside) | 11/04/2022 | 12/04/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 643 | 1112893334_643
C730C157CP###TP2840 | TT_Task | Splice backbone Inline joint (SD-SYD Trackside) | 04/05/2022 | 05/05/2022 | nan | nan | 200 | TK_NotStart | 1112893334 | 643 | 1112893334_643
C730C157CP###TP2630 | TT_Task | Equipment set out (SD-SYD Trackside) | 25/03/2022 | 28/03/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 642 | 1112893334_642
C730C157CP###TP2650 | TT_Task | Balises (SD-SYD Trackside) | 03/05/2022 | 11/05/2022 | nan | nan | 168 | TK_NotStart | 1112893334 | 642 | 1112893334_642
C730C157CP###TP3140 | TT_Task | PPI Mechanical (SD-SYD Trackside) | 13/04/2022 | 19/04/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 642 | 1112893334_642
C730T157C3###55740 | TT_Task | PAT 10 - Beacon programming (Chatswood to Crows Nest) | 07/07/2022 | 20/07/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 641 | 1112893334_641
C730T157C7###0055660 | TT_Task | PAT 10 - Beacon programming (Martin Place to Pitt Street) | 08/06/2022 | 09/06/2022 | nan | nan | 1264 | TK_NotStart | 1112893334 | 641 | 1112893334_641
C730T157CR###0055510 | TT_Task | PAT 10 - Beacon programming (Pitt Street to Central) | 28/06/2022 | 29/06/2022 | nan | nan | 1152 | TK_NotStart | 1112893334 | 641 | 1112893334_641
C730T157C8###0055360 | TT_Task | PAT 10 - Beacon programming (Central to Waterloo) | 08/07/2022 | 11/07/2022 | nan | nan | 1088 | TK_NotStart | 1112893334 | 641 | 1112893334_641
C730T157C3###0055580 | TT_Task | PAT 10 - Beacon programming (Chatswood to Crows Nest) | 08/06/2022 | 09/06/2022 | nan | nan | 1264 | TK_NotStart | 1112893334 | 641 | 1112893334_641
C730T157C6###0055880 | TT_Task | PAT 10 - Beacon programming (Crows Nest to Victoria Cross) | 13/07/2022 | 14/07/2022 | nan | nan | 1064 | TK_NotStart | 1112893334 | 641 | 1112893334_641
C730T157CS###0055150 | TT_Task | PAT 10 - Beacon programming (Waterloo to Sydenham) | 21/06/2022 | 22/06/2022 | nan | nan | 1192 | TK_NotStart | 1112893334 | 641 | 1112893334_641
C730T157C5###0055780 | TT_Task | PAT 10 - Beacon programming (Victoria Cross to Barangaroo) | 18/10/2022 | 19/10/2022 | nan | nan | 512 | TK_NotStart | 1112893334 | 641 | 1112893334_641
C730T157C6###0055290 | TT_Task | PAT 10 - Beacon programming (Barangaroo to Martin Place) | 20/09/2022 | 21/09/2022 | nan | nan | 672 | TK_NotStart | 1112893334 | 641 | 1112893334_641
C730T157CT###0055930 | TT_Task | PAT 10 - Beacon programming (Sydenham to SMTF-[S]) | 14/11/2022 | 21/11/2022 | nan | nan | 328 | TK_NotStart | 1112893334 | 641 | 1112893334_641
C730T157C3###55730 | TT_Task | PAT 9 - Track survey measurement (Chatswood to Crows Nest) | 21/06/2022 | 07/07/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 640 | 1112893334_640
C730T157C7###0055640 | TT_Task | PAT 9 - Track survey measurement (Martin Place to Pitt Street) | 03/06/2022 | 07/06/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 640 | 1112893334_640
C730T157CR###0055490 | TT_Task | PAT 9 - Track survey measurement (Pitt Street to Central) | 23/06/2022 | 27/06/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 640 | 1112893334_640
C730T157C8###0055340 | TT_Task | PAT 9 - Track survey measurement (Central to Waterloo) | 05/07/2022 | 07/07/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 640 | 1112893334_640
C730T157C3###0055540 | TT_Task | PAT 9 - Track survey measurement (Chatswood to Crows Nest) | 03/06/2022 | 07/06/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 640 | 1112893334_640
C730T157C6###0055860 | TT_Task | PAT 9 - Track survey measurement (Crows Nest to Victoria Cross) | 08/07/2022 | 12/07/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 640 | 1112893334_640
C730T157CS###0055130 | TT_Task | PAT 9 - Track survey measurement (Waterloo to Sydenham) | 16/06/2022 | 20/06/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 640 | 1112893334_640
C730T157C5###0055760 | TT_Task | PAT 9 - Track survey measurement (Victoria Cross to Barangaroo) | 13/10/2022 | 17/10/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 640 | 1112893334_640
C730T157C6###0055270 | TT_Task | PAT 9 - Track survey measurement (Barangaroo to Martin Place) | 15/09/2022 | 19/09/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 640 | 1112893334_640
C730T157CT###0055950 | TT_Task | PAT 9 - Track survey measurement (Sydenham to SMTF-[S]) | 07/11/2022 | 11/11/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 640 | 1112893334_640
C720P147CF###0030960 | TT_Task | BA Coupler | 25/02/2020 | 17/03/2020 | 05/12/2019 | 11/03/2020 | 0 | TK_Complete | 1112893334 | 64 | 1112893334_64
C720P147CF###0031160 | TT_Task | PO Coupler | 25/03/2020 | 30/03/2020 | 11/03/2020 | 12/03/2020 | 0 | TK_Complete | 1112893334 | 64 | 1112893334_64
C720P147CF###0031260 | TT_Task | Production Coupler | 25/03/2020 | 14/12/2020 | 13/03/2020 | 30/11/2020 | 0 | TK_Complete | 1112893334 | 64 | 1112893334_64
C720P147CF###0032160 | TT_Task | DEL Coupler | 11/01/2021 | 01/02/2021 | 30/11/2020 | 21/12/2020 | 0 | TK_Complete | 1112893334 | 64 | 1112893334_64
C730T157C3###55710 | TT_Task | PAT 2.3 - Signals ; Station equipment static test (Chatswood to Crows Nest) | 09/11/2022 | 29/11/2022 | nan | nan | 8 | TK_NotStart | 1112893334 | 639 | 1112893334_639
C730T157C7###0055700 | TT_Task | PAT 2.3 - Signals ; Station equipment static test (Martin Place to Pitt Street) | 30/11/2022 | 06/12/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 639 | 1112893334_639
C730T157CR###0055550 | TT_Task | PAT 2.3 - Signals ; Station equipment static test (Pitt Street to Central) | 16/11/2022 | 18/11/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 639 | 1112893334_639
C730T157C8###0055370 | TT_Task | PAT 2.3 - Signals ; Station equipment static test (Central to Waterloo) | 21/10/2022 | 25/10/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 639 | 1112893334_639
C730T157C3###0055680 | TT_Task | PAT 2.3 - Signals ; Station equipment static test (Chatswood to Crows Nest) | 26/10/2022 | 28/10/2022 | nan | nan | 256 | TK_NotStart | 1112893334 | 639 | 1112893334_639
C730T157C4###0055890 | TT_Task | PAT 2.3 - Signals ; Station equipment static test (Crows Nest to Victoria Cross) | 02/12/2022 | 06/12/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 639 | 1112893334_639
C730T157CS###0055200 | TT_Task | PAT 2.3 - Signals ; Station equipment static test (Waterloo to Sydenham) | 02/11/2022 | 07/11/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 639 | 1112893334_639
C730T157C5###0055800 | TT_Task | PAT 2.3 - Signals ; Station equipment static test (Victoria Cross to Barangaroo) | 09/11/2022 | 11/11/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 639 | 1112893334_639
C730T157C6###0055300 | TT_Task | PAT 2.3 - Signals ; Station equipment static test (Barangaroo to Martin Place) | 23/11/2022 | 25/11/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 639 | 1112893334_639
C730T157CT###0056040 | TT_Task | PAT 2.3 - Signals ; Station equipment static test (Sydenham to SMTF-[S]) | 19/12/2022 | 06/01/2023 | nan | nan | 0 | TK_NotStart | 1112893334 | 639 | 1112893334_639
C730T157C3###55680 | TT_Task | PAT 2.2 - Axle Counter test (Chatswood to Crows Nest) | 07/09/2022 | 27/09/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 638 | 1112893334_638
C730T157C7###0055690 | TT_Task | PAT 2.2 - Axle Counter test (Martin Place to Pitt Street) | 28/11/2022 | 29/11/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 638 | 1112893334_638
C730T157C3###0055600 | TT_Task | PAT 2.2 - Axle Counter test (Chatswood to Crows Nest) | 21/10/2022 | 25/10/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 638 | 1112893334_638
C730T157CS###0055190 | TT_Task | PAT 2.2 - Axle Counter test (Waterloo to Sydenham) | 27/10/2022 | 01/11/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 638 | 1112893334_638
C730T157CT###0056030 | TT_Task | PAT 2.2 - Axle Counter test (Sydenham to SMTF-[S]) | 09/12/2022 | 16/12/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 638 | 1112893334_638
C730T157BG###55420 | TT_Task | PAT 6.1 - DCS Access Point static test (Chatswood to Crows Nest) | 20/07/2022 | 07/09/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 637 | 1112893334_637
C730T157C3###55720 | TT_Task | PAT 6.1 - DCS Access Point static test (Chatswood to Crows Nest) | 27/09/2022 | 09/11/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 637 | 1112893334_637
C730T157C7###0055650 | TT_Task | PAT 6.1 - DCS Access Point static test (Martin Place to Pitt Street) | 30/11/2022 | 08/12/2022 | nan | nan | 224 | TK_NotStart | 1112893334 | 637 | 1112893334_637
C730T157CR###0055500 | TT_Task | PAT 6.1 - DCS Access Point static test (Pitt Street to Central) | 16/11/2022 | 24/11/2022 | nan | nan | 96 | TK_NotStart | 1112893334 | 637 | 1112893334_637
C730T157C8###0055350 | TT_Task | PAT 6.1 - DCS Access Point static test (Central to Waterloo) | 25/10/2022 | 02/11/2022 | nan | nan | 224 | TK_NotStart | 1112893334 | 637 | 1112893334_637
C730T157BG###0055420 | TT_Task | PAT 6.1 - DCS Access Point static test (Chatswood to Crows Nest) | 22/09/2022 | 09/11/2022 | nan | nan | 42 | TK_NotStart | 1112893334 | 637 | 1112893334_637
C730T157C3###0055570 | TT_Task | PAT 6.1 - DCS Access Point static test (Chatswood to Crows Nest) | 25/10/2022 | 02/11/2022 | nan | nan | 432 | TK_NotStart | 1112893334 | 637 | 1112893334_637
C730T157C4###0055870 | TT_Task | PAT 6.1 - DCS Access Point static test (Crows Nest to Victoria Cross) | 02/12/2022 | 12/12/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 637 | 1112893334_637
C730T157CS###0055140 | TT_Task | PAT 6.1 - DCS Access Point static test (Waterloo to Sydenham) | 21/10/2022 | 31/10/2022 | nan | nan | 448 | TK_NotStart | 1112893334 | 637 | 1112893334_637
C730T157C5###0055770 | TT_Task | PAT 6.1 - DCS Access Point static test (Victoria Cross to Barangaroo) | 07/11/2022 | 15/11/2022 | nan | nan | 360 | TK_NotStart | 1112893334 | 637 | 1112893334_637
C730T157C6###0055280 | TT_Task | PAT 6.1 - DCS Access Point static test (Barangaroo to Martin Place) | 23/11/2022 | 01/12/2022 | nan | nan | 56 | TK_NotStart | 1112893334 | 637 | 1112893334_637
C730T157CT###0055970 | TT_Task | PAT 6.1 - DCS Access Point static test (Sydenham to SMTF-[S]) | 23/11/2022 | 30/11/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 637 | 1112893334_637
C730C157CP###TP2610 | TT_Task | Migration of SMNW with SMCSW both SER and Trackside (CHW-ND Up Track) | 07/05/2022 | 14/05/2022 | nan | nan | 110 | TK_NotStart | 1112893334 | 636 | 1112893334_636
C730C157CP###TP2590 | TT_Task | Migration of SMNW with SMCSW both SER and Trackside (CHW-ND Down Track) | 12/06/2022 | 19/06/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 636 | 1112893334_636
C730C157CP###TP2600 | TT_Task | Decommissioning and removal of certain equipment and cables in brownfield section (CHW-ND Up Track) | 07/05/2022 | 14/05/2022 | nan | nan | 330 | TK_NotStart | 1112893334 | 635 | 1112893334_635
C730C157CP###TP2580 | TT_Task | Decommissioning and removal of certain equipment and cables in brownfield section (CHW-ND Down Track) | 04/06/2022 | 11/06/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 635 | 1112893334_635
C730C157CP###TP2300 | TT_Task | TRE Power ; Earthing (CHW-ND Up Track) | 21/04/2022 | 21/04/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 634 | 1112893334_634
C730C157CP###TP2540 | TT_Task | TRE Power ; Earthing (CHW-ND Down Track) | 24/05/2022 | 24/05/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 634 | 1112893334_634
C730C157CP###TP2820 | TT_Task | TRE Power ; Earthing (SD-SYD Trackside) | 26/04/2022 | 02/05/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 634 | 1112893334_634
C730C157CP###TP2290 | TT_Task | SAB Terminations (CHW-ND Up Track) | 19/04/2022 | 20/04/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 633 | 1112893334_633
C730C157CP###TP2530 | TT_Task | SAB Terminations (CHW-ND Down Track) | 20/05/2022 | 23/05/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 633 | 1112893334_633
C730C157CP###TP2810 | TT_Task | SAB Terminations (SD-SYD Trackside) | 12/05/2022 | 16/05/2022 | nan | nan | 104 | TK_NotStart | 1112893334 | 633 | 1112893334_633
C730C157CP###TP2260 | TT_Task | Field cable pull within CHW station area (CHW-ND Up Track) | 12/04/2022 | 13/04/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 632 | 1112893334_632
C730C157CP###TP2500 | TT_Task | Field cable pull within CHW station area (CHW-ND Down Track) | 17/05/2022 | 18/05/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 632 | 1112893334_632
C730C157CP###TP2240 | TT_Task | TRE Fibre (CHW-ND Up Track) | 08/04/2022 | 08/04/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 631 | 1112893334_631
C730C157CP###TP2250 | TT_Task | Fibre Backbone (CHW-ND Up Track) | 11/04/2022 | 11/04/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 631 | 1112893334_631
C730C157CP###TP2480 | TT_Task | TRE Fibre (CHW-ND Down Track) | 13/05/2022 | 13/05/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 631 | 1112893334_631
C730C157CP###TP2490 | TT_Task | Fibre Backbone (CHW-ND Down Track) | 16/05/2022 | 16/05/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 631 | 1112893334_631
C730C157CP###TP2220 | TT_Task | SAB Cables (CHW-ND Up Track) | 07/04/2022 | 07/04/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 630 | 1112893334_630
C730C157CP###TP2460 | TT_Task | SAB Cables (CHW-ND Down Track) | 12/05/2022 | 12/05/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 630 | 1112893334_630
C720P147CF###0030950 | TT_Task | BA HVAC | 25/02/2020 | 20/03/2020 | 05/12/2019 | 05/03/2020 | 0 | TK_Complete | 1112893334 | 63 | 1112893334_63
C720P147CF###0031150 | TT_Task | PO HVAC | 25/03/2020 | 15/04/2020 | 06/03/2020 | 18/03/2020 | 0 | TK_Complete | 1112893334 | 63 | 1112893334_63
C720P147CF###0031310 | TT_Task | Production HVAC | 25/03/2020 | 23/11/2020 | 19/03/2020 | 20/10/2020 | 0 | TK_Complete | 1112893334 | 63 | 1112893334_63
C720P147CF###0032030 | TT_Task | DEL HVAC | 26/10/2020 | 20/11/2020 | 21/10/2020 | 12/11/2020 | 0 | TK_Complete | 1112893334 | 63 | 1112893334_63
C730C157CP###TP2210 | TT_Task | Cable installation Axco (CHW-ND Up Track) | 07/04/2022 | 07/04/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 629 | 1112893334_629
C730C157CP###TP2450 | TT_Task | Cable installation Axco (CHW-ND Down Track) | 12/05/2022 | 12/05/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 629 | 1112893334_629
C730C157CP###TP2160 | TT_Task | TRE Boxes (CHW-ND Up Track) | 04/04/2022 | 04/04/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 628 | 1112893334_628
C730C157CP###TP2400 | TT_Task | TRE Boxes (CHW-ND Down Track) | 10/05/2022 | 10/05/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 628 | 1112893334_628
C730C157CP###TP2150 | TT_Task | SAB Boxes (CHW-ND Up Track) | 04/04/2022 | 05/04/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 627 | 1112893334_627
C730C157CP###TP2390 | TT_Task | SAB Boxes (CHW-ND Down Track) | 06/05/2022 | 09/05/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 627 | 1112893334_627
C730C157CP###TP2130 | TT_Task | Balises (CHW-ND Up Track) | 31/03/2022 | 01/04/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 626 | 1112893334_626
C730C157CP###TP2370 | TT_Task | Balises (CHW-ND Down Track) | 06/05/2022 | 06/05/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 626 | 1112893334_626
C730C157CS###D40370 | TT_Task | Internal Cable Pull Batch1 SYD SER | 01/02/2022 | 18/02/2022 | 30/11/2021 | 10/01/2022 | 0 | TK_Complete | 1112893334 | 625 | 1112893334_625
C730C157CS###N40500 | TT_Task | Internal Cable Pull Batch2 SYD SER | 16/03/2022 | 04/04/2022 | 16/03/2022 | nan | 0 | TK_Active | 1112893334 | 625 | 1112893334_625
C730C157C3###D40540 | TT_Task | Cable termination PIDS cable on SER end CST SER | 13/07/2022 | 13/07/2022 | nan | nan | 140 | TK_NotStart | 1112893334 | 624 | 1112893334_624
C730C157C4###D40670 | TT_Task | Cable termination PIDS cable on SER end VIC SER | 13/09/2022 | 13/09/2022 | nan | nan | 150 | TK_NotStart | 1112893334 | 624 | 1112893334_624
C730C157C5###D40480 | TT_Task | Cable termination PIDS cable on SER end BZZ SER | 04/08/2022 | 04/08/2022 | nan | nan | 500 | TK_NotStart | 1112893334 | 624 | 1112893334_624
C730C157C6###D40460 | TT_Task | Cable termination PIDS cable on SER end MPL SER | 01/09/2022 | 01/09/2022 | nan | nan | 90 | TK_NotStart | 1112893334 | 624 | 1112893334_624
C730C157C7###D40460 | TT_Task | Cable termination PIDS cable on SER end PIT SER | 01/09/2022 | 01/09/2022 | nan | nan | 90 | TK_NotStart | 1112893334 | 624 | 1112893334_624
C730C157CR###D40380 | TT_Task | Cable termination PIDS cable on SER end CEN SER | 02/06/2022 | 02/06/2022 | nan | nan | 560 | TK_NotStart | 1112893334 | 624 | 1112893334_624
C730C157C8###D40520 | TT_Task | Cable termination PIDS cable on SER end WLO SER | 11/08/2022 | 11/08/2022 | nan | nan | 140 | TK_NotStart | 1112893334 | 624 | 1112893334_624
C730C157CS###D40360 | TT_Task | Cable termination PIDS cable on SER end SYD SER | 19/04/2022 | 19/04/2022 | nan | nan | 968 | TK_NotStart | 1112893334 | 624 | 1112893334_624
C730C157C3###D40450 | TT_Task | Cable Installation SER to PIDS CST SER | 10/06/2022 | 10/06/2022 | nan | nan | 210 | TK_NotStart | 1112893334 | 623 | 1112893334_623
C730C157C4###D40580 | TT_Task | Cable Installation SER to PIDS VIC SER | 12/09/2022 | 12/09/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 623 | 1112893334_623
C730C157C5###D40390 | TT_Task | Cable Installation SER to PIDS BZZ SER | 03/08/2022 | 03/08/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 623 | 1112893334_623
C730C157C6###D40360 | TT_Task | Cable Installation SER to PIDS MPL SER | 03/08/2022 | 03/08/2022 | nan | nan | 200 | TK_NotStart | 1112893334 | 623 | 1112893334_623
C730C157C7###D40370 | TT_Task | Cable Installation SER to PIDS PIT SER | 03/08/2022 | 03/08/2022 | nan | nan | 200 | TK_NotStart | 1112893334 | 623 | 1112893334_623
C730C157CR###D40290 | TT_Task | Cable Installation SER to PIDS CEN SER | 25/03/2022 | 25/03/2022 | nan | nan | 450 | TK_NotStart | 1112893334 | 623 | 1112893334_623
C730C157C8###D40430 | TT_Task | Cable Installation SER to PIDS WLO SER | 13/07/2022 | 13/07/2022 | nan | nan | 200 | TK_NotStart | 1112893334 | 623 | 1112893334_623
C730C157CS###D40270 | TT_Task | Cable Installation SER to PIDS SYD SER | 05/04/2022 | 05/04/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 623 | 1112893334_623
C730C157C3###D40550 | TT_Task | Internal Cable Pull CST SER | 13/07/2022 | 15/07/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 622 | 1112893334_622
C730C157C4###D40680 | TT_Task | Internal Cable Pull VIC SER | 17/05/2022 | 20/05/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 622 | 1112893334_622
C730C157C5###D40490 | TT_Task | Internal Cable Pull BZZ SER | 06/07/2022 | 13/07/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 622 | 1112893334_622
C730C157C6###D40470 | TT_Task | Internal Cable Pull MPL SER | 01/09/2022 | 02/09/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 622 | 1112893334_622
C730C157C7###D40470 | TT_Task | Internal Cable Pull PIT SER | 01/09/2022 | 02/09/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 622 | 1112893334_622
C730C157CR###D40390 | TT_Task | Internal Cable Pull CEN SER | 02/06/2022 | 09/06/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 622 | 1112893334_622
C730C157C8###D40530 | TT_Task | Internal Cable Pull WLO SER | 11/08/2022 | 16/08/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 622 | 1112893334_622
C730C157C3###D40500 | TT_Task | Underfloor Cable Tray CST SER | 10/06/2022 | 17/06/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 621 | 1112893334_621
C730C157C4###D40630 | TT_Task | Underfloor Cable Tray VIC SER | 25/02/2022 | 03/03/2022 | 23/03/2022 | nan | 0 | TK_Active | 1112893334 | 621 | 1112893334_621
C730C157C5###D40440 | TT_Task | Underfloor Cable Tray BZZ SER | 03/06/2022 | 09/06/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 621 | 1112893334_621
C730C157C6###D40410 | TT_Task | Underfloor Cable Tray MPL SER | 03/08/2022 | 09/08/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 621 | 1112893334_621
C730C157C7###D40420 | TT_Task | Underfloor Cable Tray PIT SER | 03/08/2022 | 09/08/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 621 | 1112893334_621
C730C157CR###D40340 | TT_Task | Underfloor Cable Tray CEN SER | 25/01/2022 | 01/02/2022 | 15/02/2022 | 21/02/2022 | 0 | TK_Complete | 1112893334 | 621 | 1112893334_621
C730C157C8###D40480 | TT_Task | Underfloor Cable Tray WLO SER | 13/07/2022 | 19/07/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 621 | 1112893334_621
C730C157CS###D40320 | TT_Task | Underfloor Cable Tray SYD SER | 29/09/2021 | 29/10/2021 | 18/10/2021 | 19/11/2021 | 0 | TK_Complete | 1112893334 | 621 | 1112893334_621
C730C157BG###D40420 | TT_Task | Chatswood Installation to T;C handover 1st migration stage | 20/08/2022 | 03/09/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 620 | 1112893334_620
C730T157C3###0055400 | TT_Task | Crows Nest Installation to T;C handover | 03/08/2022 | 09/08/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 620 | 1112893334_620
C730T157CS###0055080 | TT_Task | Sydenham Installation to T;C handover | 06/09/2022 | 12/09/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 620 | 1112893334_620
C720P147CF###0030940 | TT_Task | BA Passenger doors | 25/02/2020 | 17/03/2020 | 05/12/2019 | 27/03/2020 | 0 | TK_Complete | 1112893334 | 62 | 1112893334_62
C720P147CF###0031220 | TT_Task | PO Passenger doors | 27/04/2020 | 28/05/2020 | 30/03/2020 | 06/04/2020 | 0 | TK_Complete | 1112893334 | 62 | 1112893334_62
C720P147CF###0031420 | TT_Task | Production Passenger doors | 25/05/2020 | 08/12/2020 | 28/04/2020 | 14/10/2020 | 0 | TK_Complete | 1112893334 | 62 | 1112893334_62
C720P147CF###0031910 | TT_Task | DEL Passenger doors | 26/10/2020 | 11/01/2021 | 15/10/2020 | 27/10/2020 | 0 | TK_Complete | 1112893334 | 62 | 1112893334_62
C730C157BG###D40410 | TT_Task | Install/T;C changeover/patch in | 07/08/2022 | 14/08/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 619 | 1112893334_619
C730C157BG###D40450 | TT_Task | Key Switch Termination KS End CHW SER | 03/07/2022 | 03/07/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 618 | 1112893334_618
C730C157BG###D40460 | TT_Task | Key Switch Termination SER End CHW SER | 03/07/2022 | 03/07/2022 | nan | nan | 120 | TK_NotStart | 1112893334 | 618 | 1112893334_618
C730C157C3###D40490 | TT_Task | Key Switch Termination KS End CST SER | 17/06/2022 | 20/06/2022 | nan | nan | 310 | TK_NotStart | 1112893334 | 618 | 1112893334_618
C730C157C3###D40530 | TT_Task | Key Switch Termination SER End CST SER | 13/07/2022 | 14/07/2022 | nan | nan | 130 | TK_NotStart | 1112893334 | 618 | 1112893334_618
C730C157C4###D40620 | TT_Task | Key Switch Termination KS End VIC SER | 16/09/2022 | 19/09/2022 | nan | nan | 110 | TK_NotStart | 1112893334 | 618 | 1112893334_618
C730C157C4###D40660 | TT_Task | Key Switch Termination SER End VIC SER | 14/09/2022 | 15/09/2022 | nan | nan | 130 | TK_NotStart | 1112893334 | 618 | 1112893334_618
C730C157C5###D40430 | TT_Task | Key Switch Termination KS End BZZ SER | 09/08/2022 | 10/08/2022 | nan | nan | 460 | TK_NotStart | 1112893334 | 618 | 1112893334_618
C730C157C5###D40470 | TT_Task | Key Switch Termination SER End BZZ SER | 05/08/2022 | 08/08/2022 | nan | nan | 480 | TK_NotStart | 1112893334 | 618 | 1112893334_618
C730C157C6###D40400 | TT_Task | Key Switch Termination KS End MPL SER | 09/08/2022 | 10/08/2022 | nan | nan | 250 | TK_NotStart | 1112893334 | 618 | 1112893334_618
C730C157C6###D40440 | TT_Task | Key Switch Termination SER End MPL SER | 01/09/2022 | 02/09/2022 | nan | nan | 80 | TK_NotStart | 1112893334 | 618 | 1112893334_618
C730C157C7###D40410 | TT_Task | Key Switch Termination KS End PIT SER | 09/08/2022 | 10/08/2022 | nan | nan | 250 | TK_NotStart | 1112893334 | 618 | 1112893334_618
C730C157C7###D40450 | TT_Task | Key Switch Termination SER End PIT SER | 01/09/2022 | 02/09/2022 | nan | nan | 80 | TK_NotStart | 1112893334 | 618 | 1112893334_618
C730C157CR###D40330 | TT_Task | Key Switch Termination KS End CEN SER | 05/05/2022 | 09/05/2022 | nan | nan | 742 | TK_NotStart | 1112893334 | 618 | 1112893334_618
C730C157CR###D40370 | TT_Task | Key Switch Termination SER End CEN SER | 02/06/2022 | 03/06/2022 | nan | nan | 550 | TK_NotStart | 1112893334 | 618 | 1112893334_618
C730C157C8###D40470 | TT_Task | Key Switch Termination KS End WLO SER | 19/07/2022 | 20/07/2022 | nan | nan | 300 | TK_NotStart | 1112893334 | 618 | 1112893334_618
C730C157C8###D40510 | TT_Task | Key Switch Termination SER End WLOSER | 11/08/2022 | 12/08/2022 | nan | nan | 130 | TK_NotStart | 1112893334 | 618 | 1112893334_618
C730C157CS###D40300 | TT_Task | Key Switch Termination KS End SYD SER | 03/05/2022 | 05/05/2022 | nan | nan | 860 | TK_NotStart | 1112893334 | 618 | 1112893334_618
C730C157CS###D40350 | TT_Task | Key Switch Termination SER End SYD SER | 19/04/2022 | 20/04/2022 | nan | nan | 958 | TK_NotStart | 1112893334 | 618 | 1112893334_618
C730C157BG###D40440 | TT_Task | Key Switch Mechanical CHW SER | 05/06/2022 | 12/06/2022 | nan | nan | 40 | TK_NotStart | 1112893334 | 617 | 1112893334_617
C730C157C3###D40480 | TT_Task | Key Switch Mechanical CST SER | 10/06/2022 | 16/06/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 617 | 1112893334_617
C730C157C4###D40610 | TT_Task | Key Switch Mechanical VIC SER | 12/09/2022 | 15/09/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 617 | 1112893334_617
C730C157C5###D40420 | TT_Task | Key Switch Mechanical BZZ SER | 03/08/2022 | 08/08/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 617 | 1112893334_617
C730C157C6###D40390 | TT_Task | Key Switch Mechanical MPL SER | 03/08/2022 | 08/08/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 617 | 1112893334_617
C730C157C7###D40400 | TT_Task | Key Switch Mechanical PIT SER | 03/08/2022 | 08/08/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 617 | 1112893334_617
C730C157CR###D40320 | TT_Task | Key Switch Mechanical CEN SER | 29/04/2022 | 05/05/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 617 | 1112893334_617
C730C157C8###D40460 | TT_Task | Key Switch Mechanical WLO SER | 13/07/2022 | 18/07/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 617 | 1112893334_617
C730C157CS###D40280 | TT_Task | Key Switch Mechanical SYD SER | 29/04/2022 | 03/05/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 617 | 1112893334_617
C730C157BG###D40430 | TT_Task | Key Switch Cable Installation CHW SER | 02/07/2022 | 02/07/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 616 | 1112893334_616
C730C157C3###D40460 | TT_Task | Key Switch Cable Installation CST SER | 10/06/2022 | 14/06/2022 | nan | nan | 20 | TK_NotStart | 1112893334 | 616 | 1112893334_616
C730C157C4###D40600 | TT_Task | Key Switch Cable Installation VIC SER | 12/09/2022 | 13/09/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 616 | 1112893334_616
C730C157C5###D40410 | TT_Task | Key Switch Cable Installation BZZ SER | 03/08/2022 | 04/08/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 616 | 1112893334_616
C730C157C6###D40380 | TT_Task | Key Switch Cable Installation MPL SER | 03/08/2022 | 04/08/2022 | nan | nan | 20 | TK_NotStart | 1112893334 | 616 | 1112893334_616
C730C157C7###D40390 | TT_Task | Key Switch Cable Installation PIT SER | 03/08/2022 | 04/08/2022 | nan | nan | 20 | TK_NotStart | 1112893334 | 616 | 1112893334_616
C730C157CR###D40310 | TT_Task | Key Switch Cable Installation CEN SER | 25/03/2022 | 28/03/2022 | nan | nan | 248 | TK_NotStart | 1112893334 | 616 | 1112893334_616
C730C157C8###D40450 | TT_Task | Key Switch Cable Installation WLO SER | 13/07/2022 | 14/07/2022 | nan | nan | 20 | TK_NotStart | 1112893334 | 616 | 1112893334_616
C730C157CS###D40290 | TT_Task | Key Switch Cable Installation SYD SER | 05/04/2022 | 08/04/2022 | nan | nan | 40 | TK_NotStart | 1112893334 | 616 | 1112893334_616
C730C157BG###D40310 | TT_Task | Field Fibre Optic Splicing CHW SER | 03/07/2022 | 09/07/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 615 | 1112893334_615
C730C157BG###D40340 | TT_Task | Field Fibre Optic Splicing backbone CHW SER | 10/07/2022 | 10/07/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 615 | 1112893334_615
C730C157C3###D40440 | TT_Task | Field Fibre Optic Splicing backbone CST SER | 01/08/2022 | 01/08/2022 | nan | nan | 10 | TK_NotStart | 1112893334 | 615 | 1112893334_615
C730C157C3###D40570 | TT_Task | Field Fibre Optic Splicing CST SER | 27/07/2022 | 29/07/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 615 | 1112893334_615
C730C157C4###D40710 | TT_Task | Field Fibre Optic Splicing VIC SER | 29/09/2022 | 04/10/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 615 | 1112893334_615
C730C157C4###D40740 | TT_Task | Field Fibre Optic Splicing backbone VIC SER | 05/10/2022 | 05/10/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 615 | 1112893334_615
C730C157C5###D40520 | TT_Task | Field Fibre Optic Splicing BZZ SER | 04/10/2022 | 06/10/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 615 | 1112893334_615
C730C157C5###D40530 | TT_Task | Field Fibre Optic Splicing backbone BZZ SER | 07/10/2022 | 07/10/2022 | nan | nan | 50 | TK_NotStart | 1112893334 | 615 | 1112893334_615
C730C157C6###D40500 | TT_Task | Field Fibre Optic Splicing MPL SER | 12/09/2022 | 13/09/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 615 | 1112893334_615
C730C157C6###D40530 | TT_Task | Field Fibre Optic Splicing backbone MPL SER | 14/09/2022 | 14/09/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 615 | 1112893334_615
C730C157C7###D40510 | TT_Task | Field Fibre Optic Splicing PIT SER | 12/09/2022 | 13/09/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 615 | 1112893334_615
C730C157C7###D40540 | TT_Task | Field Fibre Optic Splicing backbone PIT SER | 14/09/2022 | 14/09/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 615 | 1112893334_615
C730C157CR###D40420 | TT_Task | Field Fibre Optic Splicing CEN SER | 15/08/2022 | 16/08/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 615 | 1112893334_615
C730C157CR###D40430 | TT_Task | Field Fibre Optic Splicing backbone CEN SER | 17/08/2022 | 17/08/2022 | nan | nan | 30 | TK_NotStart | 1112893334 | 615 | 1112893334_615
C730C157C8###D40570 | TT_Task | Field Fibre Optic Splicing WLO SER | 24/08/2022 | 26/08/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 615 | 1112893334_615
C730C157C8###D40600 | TT_Task | Field Fibre Optic Splicing backbone WLO SER | 29/08/2022 | 31/08/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 615 | 1112893334_615
C730C157CS###D40400 | TT_Task | Field Fibre Optic Splicing SYD SER | 26/04/2022 | 27/04/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 615 | 1112893334_615
C730C157CS###D40410 | TT_Task | Field Fibre Optic Splicing backbone SYD SER | 28/04/2022 | 02/05/2022 | nan | nan | 888 | TK_NotStart | 1112893334 | 615 | 1112893334_615
C730C157BG###D40300 | TT_Task | Field SER Copper Terminations CHW SER | 03/07/2022 | 10/07/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 614 | 1112893334_614
C730C157C3###D40580 | TT_Task | Field SER Copper Terminations CST SER | 27/07/2022 | 02/08/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 614 | 1112893334_614
C730C157C4###D40700 | TT_Task | Field SER Copper Terminations VIC SER | 29/09/2022 | 30/09/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 614 | 1112893334_614
C730C157C5###D40540 | TT_Task | Field SER Copper Terminations BZZ SER | 04/10/2022 | 14/10/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 614 | 1112893334_614
C730C157C6###D40490 | TT_Task | Field SER Copper Terminations MPL SER | 12/09/2022 | 13/09/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 614 | 1112893334_614
C730C157C7###D40500 | TT_Task | Field SER Copper Terminations PIT SER | 12/09/2022 | 13/09/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 614 | 1112893334_614
C730C157CR###D40440 | TT_Task | Field SER Copper Terminations CEN SER | 15/08/2022 | 22/08/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 614 | 1112893334_614
C730C157C8###D40560 | TT_Task | Field SER Copper Terminations WLO SER | 24/08/2022 | 24/08/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 614 | 1112893334_614
C730C157CS###D40420 | TT_Task | Field SER Copper Terminations SYD SER | 26/04/2022 | 11/05/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 614 | 1112893334_614
C730C157BG###D40290 | TT_Task | Internal SER Terminations CHW SER | 02/07/2022 | 02/07/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 613 | 1112893334_613
C730C157C3###D40560 | TT_Task | Internal SER Terminations CST SER | 18/07/2022 | 26/07/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 613 | 1112893334_613
C730C157C4###D40690 | TT_Task | Internal SER Terminations VIC SER | 23/05/2022 | 27/05/2022 | nan | nan | 870 | TK_NotStart | 1112893334 | 613 | 1112893334_613
C730C157C5###D40500 | TT_Task | Internal SER Terminations BZZ SER | 14/07/2022 | 28/07/2022 | nan | nan | 460 | TK_NotStart | 1112893334 | 613 | 1112893334_613
C730C157C6###D40480 | TT_Task | Internal SER Terminations MPL SER | 05/09/2022 | 09/09/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 613 | 1112893334_613
C730C157C7###D40490 | TT_Task | Internal SER Terminations PIT SER | 05/09/2022 | 09/09/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 613 | 1112893334_613
C730C157CR###D40400 | TT_Task | Internal SER Terminations CEN SER | 10/06/2022 | 22/06/2022 | nan | nan | 370 | TK_NotStart | 1112893334 | 613 | 1112893334_613
C730C157C8###D40550 | TT_Task | Internal SER Terminations WLO SER | 17/08/2022 | 23/08/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 613 | 1112893334_613
C730C157CS###D40380 | TT_Task | Internal SER Terminations SYD SER | 05/04/2022 | 22/04/2022 | 17/03/2022 | nan | 0 | TK_Active | 1112893334 | 613 | 1112893334_613
C730C157BG###D40280 | TT_Task | Internal Cable Pull to new cubicles CHW SER | 05/06/2022 | 05/06/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 612 | 1112893334_612
C730C157BG###D40370 | TT_Task | Internal Cable Pull to existing cubicles CHW SER | 11/06/2022 | 18/06/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 612 | 1112893334_612
C730C157BG###D40380 | TT_Task | Cable Pull within existing cubicles CHW SER | 19/06/2022 | 26/06/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 612 | 1112893334_612
C730C157BG###D40250 | TT_Task | Field Cable Pull Trackside Platform Area to SER CHW SER | 21/05/2022 | 29/05/2022 | nan | nan | 90 | TK_NotStart | 1112893334 | 611 | 1112893334_611
C730C157C3###D40470 | TT_Task | Field Cable Pull Trackside Platform Area to SER CST SER | 21/06/2022 | 24/06/2022 | nan | nan | 220 | TK_NotStart | 1112893334 | 611 | 1112893334_611
C730C157C4###D40570 | TT_Task | Field Cable Pull Trackside Platform Area to SER VIC SER | 23/09/2022 | 28/09/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 611 | 1112893334_611
C730C157C5###D40510 | TT_Task | Field Cable Pull Trackside Platform Area to SER BZZ SER | 23/09/2022 | 30/09/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 611 | 1112893334_611
C730C157C6###D40450 | TT_Task | Field Cable Pull Trackside Platform Area to SER MPL SER | 03/08/2022 | 04/08/2022 | nan | nan | 260 | TK_NotStart | 1112893334 | 611 | 1112893334_611
C730C157C7###D40480 | TT_Task | Field Cable Pull Trackside Platform Area to SER PIT SER | 03/08/2022 | 04/08/2022 | nan | nan | 260 | TK_NotStart | 1112893334 | 611 | 1112893334_611
C730C157CR###D40410 | TT_Task | Field Cable Pull Trackside Platform Area to SER CEN SER | 03/08/2022 | 12/08/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 611 | 1112893334_611
C730C157C8###D40540 | TT_Task | Field Cable Pull Trackside Platform Area to SER WLO SER | 13/07/2022 | 19/07/2022 | nan | nan | 250 | TK_NotStart | 1112893334 | 611 | 1112893334_611
C730C157BG###D40360 | TT_Task | Retrofit / upgrade of existing cubicles in CHW SER | 22/05/2022 | 04/06/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 610 | 1112893334_610
C730C157BG###D40390 | TT_Task | Retrofit / upgrade of existing cubicles Termination - CHW SER | 16/07/2022 | 24/07/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 610 | 1112893334_610
C720P147CF###0030930 | TT_Task | BA Floor (Composite Material) | 25/02/2020 | 17/03/2020 | 05/12/2019 | 17/03/2020 | 0 | TK_Complete | 1112893334 | 61 | 1112893334_61
C720P147CF###0031240 | TT_Task | PO Floor (Composite Material) | 25/03/2020 | 30/03/2020 | 18/03/2020 | 19/03/2020 | 0 | TK_Complete | 1112893334 | 61 | 1112893334_61
C720P147CF###0031340 | TT_Task | Production Floor (Composite Material) | 27/04/2020 | 02/11/2020 | 27/03/2020 | 20/10/2020 | 0 | TK_Complete | 1112893334 | 61 | 1112893334_61
C720P147CF###0031710 | TT_Task | DEL Floor (Composite Material) | 26/10/2020 | 20/11/2020 | 21/10/2020 | 09/11/2020 | 0 | TK_Complete | 1112893334 | 61 | 1112893334_61
C730C157BG###D40350 | TT_Task | Material Delivery/Distributaion to Site CHW SER | 30/04/2022 | 01/05/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 609 | 1112893334_609
C730C157BG###D40270 | TT_Task | Cubicles/Cabinets- Mechanical CHW SER | 14/05/2022 | 21/05/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 608 | 1112893334_608
C730C157C3###D40520 | TT_Task | Cubicles/Cabinets- Mechanical CST SER | 27/06/2022 | 12/07/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 608 | 1112893334_608
C730C157C4###D40650 | TT_Task | Cubicles/Cabinets- Mechanical VIC SER | 02/05/2022 | 16/05/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 608 | 1112893334_608
C730C157C5###D40460 | TT_Task | Cubicles/Cabinets- Mechanical BZZ SER | 20/06/2022 | 05/07/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 608 | 1112893334_608
C730C157C6###D40430 | TT_Task | Cubicles/Cabinets- Mechanical MPL SER | 17/08/2022 | 31/08/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 608 | 1112893334_608
C730C157C7###D40440 | TT_Task | Cubicles/Cabinets- Mechanical PIT SER | 17/08/2022 | 31/08/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 608 | 1112893334_608
C730C157CR###D40360 | TT_Task | Cubicles/Cabinets- Mechanical CEN SER | 17/05/2022 | 01/06/2022 | 28/02/2022 | nan | 0 | TK_Active | 1112893334 | 608 | 1112893334_608
C730C157C8###D40500 | TT_Task | Cubicles/Cabinets- Mechanical WLO SER | 27/07/2022 | 10/08/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 608 | 1112893334_608
C730C157CS###D40340 | TT_Task | Cubicles/Cabinets- Mechanical SYD SER | 16/03/2022 | 14/04/2022 | 03/02/2022 | nan | 0 | TK_Active | 1112893334 | 608 | 1112893334_608
C730C157BG###D40260 | TT_Task | Aerial Cable Tray CHW SER | 07/05/2022 | 08/05/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 607 | 1112893334_607
C730C157C3###D40510 | TT_Task | Aerial Cable Tray CST SER | 20/06/2022 | 24/06/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 607 | 1112893334_607
C730C157C4###D40640 | TT_Task | Aerial Cable Tray VIC SER | 30/03/2022 | 05/04/2022 | nan | nan | 150 | TK_NotStart | 1112893334 | 607 | 1112893334_607
C730C157C5###D40450 | TT_Task | Aerial Cable Tray BZZ SER | 10/06/2022 | 17/06/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 607 | 1112893334_607
C730C157C6###D40420 | TT_Task | Aerial Cable Tray MPL SER | 10/08/2022 | 16/08/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 607 | 1112893334_607
C730C157C7###D40430 | TT_Task | Aerial Cable Tray PIT SER | 10/08/2022 | 16/08/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 607 | 1112893334_607
C730C157CR###D40350 | TT_Task | Aerial Cable Tray CEN SER | 02/02/2022 | 08/02/2022 | 22/02/2022 | 28/02/2022 | 0 | TK_Complete | 1112893334 | 607 | 1112893334_607
C730C157C8###D40490 | TT_Task | Aerial Cable Tray WLO SER | 20/07/2022 | 26/07/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 607 | 1112893334_607
C730C157CS###D40330 | TT_Task | Aerial Cable Tray SYD SER | 29/11/2021 | 14/12/2021 | 25/10/2021 | 25/11/2021 | 0 | TK_Complete | 1112893334 | 607 | 1112893334_607
C730C157CP###D41260 | TT_Task | Outstanding Balises to be installed - Blocked(CST-ND Down Track) | 02/05/2022 | 02/05/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 606 | 1112893334_606
C730C157CI###D40380 | TT_Task | Splice backbone Inline joint (CST-ND Up Track) | 03/05/2022 | 04/05/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 605 | 1112893334_605
C730C157CI###D40570 | TT_Task | Splice backbone Inline joint (CST-ND Down Track) | 14/04/2022 | 20/04/2022 | 22/02/2022 | 23/02/2022 | 0 | TK_Complete | 1112893334 | 605 | 1112893334_605
C730C157CP###TP2320 | TT_Task | Splice backbone Inline joint (CHW-ND Up Track) | 22/04/2022 | 26/04/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 605 | 1112893334_605
C730C157CP###TP2560 | TT_Task | Splice backbone Inline joint (CHW-ND Down Track) | 25/05/2022 | 26/05/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 605 | 1112893334_605
C730C157CI###D40340 | TT_Task | Backbone Joint Box (CST-ND Up Track) | 11/11/2021 | 11/11/2021 | 16/11/2021 | 17/11/2021 | 0 | TK_Complete | 1112893334 | 604 | 1112893334_604
C730C157CI###D40530 | TT_Task | Backbone Joint (CST-ND Down Track) | 29/11/2021 | 29/11/2021 | 24/11/2021 | 25/11/2021 | 0 | TK_Complete | 1112893334 | 604 | 1112893334_604
C730C157CP###TP2190 | TT_Task | Backbone Joint Box (CHW-ND Up Track) | 06/04/2022 | 06/04/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 604 | 1112893334_604
C730C157CP###TP2430 | TT_Task | Backbone Joint Box (CHW-ND Down Track) | 11/05/2022 | 11/05/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 604 | 1112893334_604
C730C157CJ###D40320 | TT_Task | TRE Power (VIC-CST Up Track) | 09/06/2022 | 10/06/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 603 | 1112893334_603
C730C157CJ###D40460 | TT_Task | TRE Power (VIC-CST Down Track) | 09/06/2022 | 10/06/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 603 | 1112893334_603
C730C157CI###D40280 | TT_Task | TRE power (CST-ND Up Track) | 16/11/2021 | 19/11/2021 | 25/10/2021 | 03/11/2021 | 0 | TK_Complete | 1112893334 | 603 | 1112893334_603
C730C157CI###D40470 | TT_Task | TRE power (CST-ND Down Track) | 25/10/2021 | 28/10/2021 | 09/11/2021 | 12/11/2021 | 0 | TK_Complete | 1112893334 | 603 | 1112893334_603
C730C157CJ###D40310 | TT_Task | Field Cable - Installation - DCS Fibre (VIC-CST Up Track) | 09/06/2022 | 09/06/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 602 | 1112893334_602
C730C157CJ###D40340 | TT_Task | Field Cable - Installation - Fibre Backbone (VIC-CST Up Track) | 08/06/2022 | 08/06/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 602 | 1112893334_602
C730C157CJ###D40450 | TT_Task | Field Cable - Installation - DCS Fibre (VIC-CST Down Track) | 09/06/2022 | 09/06/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 602 | 1112893334_602
C730C157CJ###D40480 | TT_Task | Field Cable - Installation - Fibre Backbone (VIC-CST Down Track) | 14/06/2022 | 14/06/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 602 | 1112893334_602
C730C157CI###D40240 | TT_Task | Field Cable - Installation - DCS Fibre (CST-ND Up Track) | 16/11/2021 | 18/11/2021 | 02/11/2021 | 05/11/2021 | 0 | TK_Complete | 1112893334 | 602 | 1112893334_602
C730C157CI###D40250 | TT_Task | Field Cable - Installation - Fibre Backbone (CST-ND Up Track) | 12/11/2021 | 15/11/2021 | 29/10/2021 | 03/11/2021 | 0 | TK_Complete | 1112893334 | 602 | 1112893334_602
C730C157CI###D40430 | TT_Task | Field Cable - Installation - DCS Fibre (CST-ND Down Track) | 25/10/2021 | 27/10/2021 | 10/11/2021 | 26/11/2021 | 0 | TK_Complete | 1112893334 | 602 | 1112893334_602
C730C157CI###D40440 | TT_Task | Field Cable - Installation - Fibre Backbone (CST-ND Down Track) | 25/10/2021 | 26/10/2021 | 10/11/2021 | 26/11/2021 | 0 | TK_Complete | 1112893334 | 602 | 1112893334_602
C730C157CJ###D41460 | TT_Task | Site Inspection (VIC-CST Up Track) | 06/05/2022 | 06/05/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 601 | 1112893334_601
C730C157CJ###D41480 | TT_Task | Site Inspection (VIC-CST Down Track) | 06/05/2022 | 06/05/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 601 | 1112893334_601
C730C157CI###D40710 | TT_Task | Site Inspection (CST-ND Up Track) | 29/09/2021 | 30/09/2021 | 16/09/2021 | 16/09/2021 | 0 | TK_Complete | 1112893334 | 601 | 1112893334_601
C730C157CI###D40730 | TT_Task | Site Inspection (CST-ND Down Track) | 08/12/2021 | 08/12/2021 | 18/10/2021 | 18/10/2021 | 0 | TK_Complete | 1112893334 | 601 | 1112893334_601
C730C157CJ###D41370 | TT_Task | SAB - Mechanical (VIC-CST Up Track) | 17/05/2022 | 17/05/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 600 | 1112893334_600
C730C157CJ###D41390 | TT_Task | SAB - Mechanical (VIC-CST Down Track) | 17/05/2022 | 17/05/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 600 | 1112893334_600
C730C157CI###D40310 | TT_Task | SAB - Mechanical (CST-ND Up Track) | 26/11/2021 | 29/11/2021 | 15/11/2021 | 16/11/2021 | 0 | TK_Complete | 1112893334 | 600 | 1112893334_600
C730C157CI###D40500 | TT_Task | SAB - Mechanical (CST-ND Down Track) | 25/10/2021 | 26/10/2021 | 11/11/2021 | 11/11/2021 | 0 | TK_Complete | 1112893334 | 600 | 1112893334_600
C720P147CF###0030920 | TT_Task | BA Seats | 25/02/2020 | 20/03/2020 | 05/12/2019 | 27/01/2020 | 0 | TK_Complete | 1112893334 | 60 | 1112893334_60
C720P147CF###0031600 | TT_Task | PO Seats | 25/03/2020 | 23/04/2020 | 16/03/2020 | 30/03/2020 | 0 | TK_Complete | 1112893334 | 60 | 1112893334_60
C720P147CF###0031610 | TT_Task | Production Seats | 25/05/2020 | 22/12/2020 | 27/04/2020 | 09/11/2020 | 0 | TK_Complete | 1112893334 | 60 | 1112893334_60
C720P147CF###0032260 | TT_Task | DEL Seats | 06/11/2020 | 03/12/2020 | 12/11/2020 | 24/11/2020 | 0 | TK_Complete | 1112893334 | 60 | 1112893334_60
C720D147CF###0037040 | TT_Task | Radio - Review of Interface Test Specification (Preliminary) | 27/07/2020 | 14/08/2020 | 06/07/2020 | 22/07/2020 | 0 | TK_Complete | 1112893334 | 6 | 1112893334_6
C720D147CF###0037055 | TT_Task | Radio - Review of Interface Test Specification (Final) | 25/09/2020 | 16/10/2020 | 17/08/2020 | 31/08/2020 | 0 | TK_Complete | 1112893334 | 6 | 1112893334_6
C730C157CJ###D40370 | TT_Task | Antennas and Cabling (VIC-CST Up Track) | 26/05/2022 | 01/06/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 599 | 1112893334_599
C730C157CJ###D40510 | TT_Task | Antennas and Cabling (VIC-CST Down Track) | 26/05/2022 | 01/06/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 599 | 1112893334_599
C730C157CI###D40330 | TT_Task | Antennas and Cabling (CST-ND Up Track) | 25/11/2021 | 07/12/2021 | 06/12/2021 | 10/01/2022 | 0 | TK_Complete | 1112893334 | 599 | 1112893334_599
C730C157CI###D40520 | TT_Task | Antennas and Cabling (CST-ND Down Track) | 10/11/2021 | 22/11/2021 | 08/11/2021 | 18/12/2021 | 0 | TK_Complete | 1112893334 | 599 | 1112893334_599
C730C157CP###TP2170 | TT_Task | Antennas and Cabling (CHW-ND Up Track) | 05/04/2022 | 05/04/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 599 | 1112893334_599
C730C157CP###TP2410 | TT_Task | Antennas and Cabling (CHW-ND Down Track) | 10/05/2022 | 10/05/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 599 | 1112893334_599
C730C157CJ###D40360 | TT_Task | Material Distribution (VIC-CST Up Track) | 09/05/2022 | 11/05/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 598 | 1112893334_598
C730C157CJ###D40500 | TT_Task | Material Distribution (VIC-CST Down Track) | 09/05/2022 | 11/05/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 598 | 1112893334_598
C730C157CI###D40300 | TT_Task | Material Distribution (CST-ND Up Track) | 06/10/2021 | 13/10/2021 | 21/09/2021 | 24/09/2021 | 0 | TK_Complete | 1112893334 | 598 | 1112893334_598
C730C157CI###D40490 | TT_Task | Material Distribution (CST-ND Down Track) | 08/10/2021 | 15/10/2021 | 18/10/2021 | 22/10/2021 | 0 | TK_Complete | 1112893334 | 598 | 1112893334_598
C730C157CJ###D40350 | TT_Task | Equipment set out (VIC-CST Up Track) | 06/05/2022 | 06/05/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 597 | 1112893334_597
C730C157CJ###D40490 | TT_Task | Equipment set out (VIC-CST Down Track) | 06/05/2022 | 06/05/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 597 | 1112893334_597
C730C157CI###D40290 | TT_Task | Equipment set out (CST-ND Up Track) | 29/09/2021 | 06/10/2021 | 17/09/2021 | 20/09/2021 | 0 | TK_Complete | 1112893334 | 597 | 1112893334_597
C730C157CI###D40480 | TT_Task | Equipment set out (CST-ND Down Track) | 01/10/2021 | 07/10/2021 | 18/10/2021 | 21/10/2021 | 0 | TK_Complete | 1112893334 | 597 | 1112893334_597
C730C157CK###D41430 | TT_Task | Marker Boards (Blue Point Shaft to VIC Up Track) | 08/09/2022 | 09/09/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 596 | 1112893334_596
C730C157CK###D41370 | TT_Task | Marker Boards (Blue Point Shaft to VIC Down Track) | 31/08/2022 | 01/09/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 596 | 1112893334_596
C730C157CK###D40930 | TT_Task | Axle Counter - Terminations (BZZ Xover- Blue Point Shaft Up Track) | 16/09/2022 | 16/09/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 595 | 1112893334_595
C730C157CK###D40500 | TT_Task | Axle Counter - Terminations (BZZ Xover- Blue Point Shaft Down Track) | 16/09/2022 | 16/09/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 595 | 1112893334_595
C730C157CK###D40640 | TT_Task | Axle Counter - Terminations (Blue Point Shaft to VIC Up Track) | 28/09/2022 | 28/09/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 595 | 1112893334_595
C730C157CK###D40780 | TT_Task | Axle Counter - Terminations (Blue Point Shaft to VIC Down Track) | 13/09/2022 | 13/09/2022 | nan | nan | 50 | TK_NotStart | 1112893334 | 595 | 1112893334_595
C730C157CK###D40920 | TT_Task | Field Fibre Cable - Splicing - BTN (BZZ Xover- Blue Point Shaft Up Track) | 14/09/2022 | 15/09/2022 | nan | nan | 30 | TK_NotStart | 1112893334 | 594 | 1112893334_594
C730C157CK###D40480 | TT_Task | Field Fibre Cable - Splicing - DCS box FO Splice (BZZ Xover- Blue Point Shaft Down Track) | 14/09/2022 | 19/09/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 594 | 1112893334_594
C730C157CK###D40490 | TT_Task | Field Fibre Cable - Splicing - BTN (BZZ Xover- Blue Point Shaft Down Track) | 20/09/2022 | 21/09/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 594 | 1112893334_594
C730C157CK###D40630 | TT_Task | Field Fibre Cable - Splicing - DCS box FO Splice (Blue Point Shaft to VIC Up Track) | 23/09/2022 | 04/10/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 594 | 1112893334_594
C730C157CK###D41800 | TT_Task | Field Fibre Cable - Splicing - BTN (Blue Point Shaft to VIC Up Track) | 05/10/2022 | 05/10/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 594 | 1112893334_594
C730C157CK###D40680 | TT_Task | Field Fibre Cable - Splicing - BTN (Blue Point Shaft to VIC Down Track) | 01/09/2022 | 01/09/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 594 | 1112893334_594
C730C157CK###D40770 | TT_Task | Field Fibre Cable - Splicing - DCS (Blue Point Shaft to VIC Down Track) | 08/09/2022 | 16/09/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 594 | 1112893334_594
C730C157CK###D41470 | TT_Task | Field Fibre Cable - Splicing - BTN (Blue Point Shaft to VIC Down Track) | 19/09/2022 | 20/09/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 594 | 1112893334_594
C730C157CK###D40340 | TT_Task | Field Copper Cable - Termination - SAB (BZZ Xover- Blue Point Shaft Up Track) | 14/09/2022 | 15/09/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 593 | 1112893334_593
C730C157CK###D40350 | TT_Task | Field Copper Cable - Termination - TRE box FO Splice (BZZ Xover- Blue Point Shaft Up Track) | 14/09/2022 | 19/09/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 593 | 1112893334_593
C730C157CK###D40320 | TT_Task | Field Copper Cable - Termination - SAB (BZZ Xover- Blue Point Shaft Down Track) | 19/09/2022 | 19/09/2022 | nan | nan | 20 | TK_NotStart | 1112893334 | 593 | 1112893334_593
C730C157CK###D41790 | TT_Task | Field Copper Cable - Termination - SAB (Blue Point Shaft to VIC Up Track) | 28/09/2022 | 29/09/2022 | nan | nan | 30 | TK_NotStart | 1112893334 | 593 | 1112893334_593
C730C157CK###D41480 | TT_Task | Field Copper Cable - Termination - SAB (Blue Point Shaft to VIC Down Track) | 13/09/2022 | 14/09/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 593 | 1112893334_593
C730C157CK###D41720 | TT_Task | Field Cable - Tying in (BZZ Xover- Blue Point Shaft Up Track) | 12/09/2022 | 13/09/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 592 | 1112893334_592
C730C157CK###D41740 | TT_Task | Field Cable - Tying in (BZZ Xover- Blue Point Shaft Down Track) | 12/09/2022 | 13/09/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 592 | 1112893334_592
C730C157CK###D41780 | TT_Task | Field Cable - Tying in (Blue Point Shaft to VIC Up Track) | 19/09/2022 | 22/09/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 592 | 1112893334_592
C730C157CK###D41820 | TT_Task | Field Cable - Tying in (Blue Point Shaft to VIC Down Track) | 02/09/2022 | 07/09/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 592 | 1112893334_592
C730C157CK###D40850 | TT_Task | TRE power (BZZ Xover- Blue Point Shaft Up Track) | 08/09/2022 | 08/09/2022 | nan | nan | 80 | TK_NotStart | 1112893334 | 591 | 1112893334_591
C730C157CK###D40400 | TT_Task | TRE Power (BZZ Xover- Blue Point Shaft Down Track) | 02/12/2021 | 03/12/2021 | 03/09/2021 | 08/09/2021 | 0 | TK_Complete | 1112893334 | 591 | 1112893334_591
C730C157CK###D40560 | TT_Task | TRE power (Blue Point Shaft to VIC Up Track) | 13/09/2022 | 14/09/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 591 | 1112893334_591
C730C157CK###D40700 | TT_Task | TRE power (Blue Point Shaft to VIC Down Track) | 13/10/2021 | 14/10/2021 | 06/09/2021 | 08/09/2021 | 0 | TK_Complete | 1112893334 | 591 | 1112893334_591
C730C157CK###D40840 | TT_Task | Field Cable - Installation - AxCo (BZZ Xover- Blue Point Shaft Up Track) | 07/09/2022 | 07/09/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 590 | 1112893334_590
C730C157CK###D40390 | TT_Task | Field Cable - Installation - AxCo (BZZ Xover- Blue Point Shaft Down Track) | 30/08/2022 | 30/08/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 590 | 1112893334_590
C730C157CK###D40550 | TT_Task | Field Cable - Installation - AxCo (Blue Point Shaft to VIC Up Track) | 15/09/2022 | 16/09/2022 | nan | nan | 70 | TK_NotStart | 1112893334 | 590 | 1112893334_590
C730C157CK###D40690 | TT_Task | Field Cable - Installation - AxCo (Blue Point Shaft to VIC Down Track) | 31/08/2022 | 01/09/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 590 | 1112893334_590
C720P147CF###0030900 | TT_Task | BA Hand rails | 25/02/2020 | 19/03/2020 | 05/12/2019 | 24/04/2020 | 0 | TK_Complete | 1112893334 | 59 | 1112893334_59
C720P147CF###0031140 | TT_Task | PO Hand rails | 25/05/2020 | 29/06/2020 | 27/04/2020 | 22/05/2020 | 0 | TK_Complete | 1112893334 | 59 | 1112893334_59
C720P147CF###0031230 | TT_Task | Production Hand rails | 25/06/2020 | 08/02/2021 | 29/05/2020 | 14/10/2020 | 0 | TK_Complete | 1112893334 | 59 | 1112893334_59
C720P147CF###0031690 | TT_Task | DEL Hand rails | 11/11/2020 | 01/12/2020 | 15/10/2020 | 06/12/2020 | 0 | TK_Complete | 1112893334 | 59 | 1112893334_59
C730C157CK###D40810 | TT_Task | Field Cable - Installation -TRE Fibre (BZZ Xover- Blue Point Shaft Up Track) | 08/09/2022 | 08/09/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 589 | 1112893334_589
C730C157CK###D40820 | TT_Task | Field Cable - Installation -Fibre Backbone (BZZ Xover- Blue Point Shaft Up Track) | 09/09/2022 | 09/09/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 589 | 1112893334_589
C730C157CK###D40370 | TT_Task | Field Cable - Installation - DCS Fibre (BZZ Xover- Blue Point Shaft Down Track) | 08/09/2022 | 08/09/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 589 | 1112893334_589
C730C157CK###D40950 | TT_Task | Field Cable - Installation - Fibre Backbone (BZZ Xover- Blue Point Shaft Down Track) | 09/09/2022 | 09/09/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 589 | 1112893334_589
C730C157CK###D40530 | TT_Task | Field Cable - Installation - DCS Fibre (Blue Point Shaft to VIC Up Track) | 13/09/2022 | 14/09/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 589 | 1112893334_589
C730C157CK###D40540 | TT_Task | Field Cable - Installation - Fibre Backbone (Blue Point Shaft to VIC Up Track) | 15/09/2022 | 15/09/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 589 | 1112893334_589
C730C157CK###D40670 | TT_Task | Field Cable - Installation - DCS Fibre (Blue Point Shaft to VIC Down Track) | 02/09/2022 | 05/09/2022 | nan | nan | 20 | TK_NotStart | 1112893334 | 589 | 1112893334_589
C730C157CK###D41440 | TT_Task | DCS Splice Box (BZZ Xover- Blue Point Shaft Up Track) | 08/12/2021 | 09/12/2021 | 15/09/2021 | 16/09/2021 | 0 | TK_Complete | 1112893334 | 588 | 1112893334_588
C730C157CK###D41450 | TT_Task | BTN Splice Box (BZZ Xover- Blue Point Shaft Up Track) | 31/08/2022 | 31/08/2022 | nan | nan | 20 | TK_NotStart | 1112893334 | 588 | 1112893334_588
C730C157CK###D41390 | TT_Task | DCS Splice Box (BZZ Xover- Blue Point Shaft Down Track) | 07/09/2022 | 07/09/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 588 | 1112893334_588
C730C157CK###D41400 | TT_Task | BTN Splice Box (BZZ Xover- Blue Point Shaft Down Track) | 07/09/2022 | 07/09/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 588 | 1112893334_588
C730C157CK###D41410 | TT_Task | DCS Splice Box (Blue Point Shaft to VIC Up Track) | 25/02/2022 | 25/02/2022 | 03/03/2022 | 04/03/2022 | 0 | TK_Complete | 1112893334 | 588 | 1112893334_588
C730C157CK###D41350 | TT_Task | DCS Splice Box (Blue Point Shaft to VIC Down Track) | 09/09/2021 | 09/09/2021 | 20/08/2021 | 20/08/2021 | 0 | TK_Complete | 1112893334 | 588 | 1112893334_588
C730C157CK###D41360 | TT_Task | BTN Splice Box (Blue Point Shaft to VIC Down Track) | 02/09/2022 | 02/09/2022 | nan | nan | 100 | TK_NotStart | 1112893334 | 588 | 1112893334_588
C730C157CJ###D41070 | TT_Task | FO Backbone Splice (Blue Point Shaft to VIC Down Track) | 01/07/2022 | 01/07/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 588 | 1112893334_588
C730C157CK###D41420 | TT_Task | PPI Structure (BZZ Xover- Blue Point Shaft Up Track) | 05/09/2022 | 06/09/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 587 | 1112893334_587
C730C157CK###D41460 | TT_Task | PPI - Termination (BZZ Xover- Blue Point Shaft Up Track) | 14/09/2022 | 15/09/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 587 | 1112893334_587
C730C157CK###D41380 | TT_Task | PPI - Mechanical (BZZ Xover- Blue Point Shaft Down Track) | 05/09/2022 | 06/09/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 587 | 1112893334_587
C730C157CK###D41490 | TT_Task | PPI - Termination (BZZ Xover- Blue Point Shaft Down Track) | 16/09/2022 | 19/09/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 587 | 1112893334_587
C730C157CK###D40910 | TT_Task | Balise - Mechanical (BZZ Xover- Blue Point Shaft Up Track) | 30/08/2022 | 02/09/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 586 | 1112893334_586
C730C157CK###D40470 | TT_Task | Balise - Mechanical (BZZ Xover- Blue Point Shaft Down Track) | 15/10/2021 | 18/10/2021 | 23/08/2021 | 23/08/2021 | 0 | TK_Complete | 1112893334 | 586 | 1112893334_586
C730C157CK###N42170 | TT_Task | Balise - Mechanical - Final Work(BZZ Xover- Blue Point Shaft Down Track) | 30/08/2022 | 01/09/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 586 | 1112893334_586
C730C157CK###D40620 | TT_Task | Balise - Mechanical (Blue Point Shaft to VIC Up Track) | 02/09/2022 | 07/09/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 586 | 1112893334_586
C730C157CK###D40760 | TT_Task | Balise - Mechanical (Blue Point Shaft to VIC Down Track) | 01/09/2021 | 07/09/2021 | 08/08/2021 | 10/08/2021 | 0 | TK_Complete | 1112893334 | 586 | 1112893334_586
C730C157CK###N42190 | TT_Task | Balise - Mechanical - Final Work (Blue Point Shaft to VIC Down Track) | 30/08/2022 | 30/08/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 586 | 1112893334_586
C730C157CK###D40900 | TT_Task | DCS TRE Box - Mechanical (BZZ Xover- Blue Point Shaft Up Track) | 10/12/2021 | 16/12/2021 | 13/09/2021 | 20/09/2021 | 0 | TK_Complete | 1112893334 | 585 | 1112893334_585
C730C157CK###D40460 | TT_Task | DCS TRE Box - Mechanical (BZZ Xover- Blue Point Shaft Down Track) | 22/11/2021 | 26/11/2021 | 23/08/2021 | 31/08/2021 | 0 | TK_Complete | 1112893334 | 585 | 1112893334_585
C730C157CK###N42175 | TT_Task | DCS TRE Box - Mechanical - Final Work (BZZ Xover- Blue Point Shaft Down Track) | 30/08/2022 | 30/08/2022 | nan | nan | 20 | TK_NotStart | 1112893334 | 585 | 1112893334_585
C730C157CK###D40610 | TT_Task | DCS TRE Box - Mechanical (Blue Point Shaft to VIC Up Track)(Hi-Rail) | 25/02/2022 | 03/03/2022 | 28/02/2022 | 03/03/2022 | 0 | TK_Complete | 1112893334 | 585 | 1112893334_585
C730C157CK###D40750 | TT_Task | DCS TRE Box - Mechanical (Blue Point Shaft to VIC Down Track) | 09/09/2021 | 15/09/2021 | 10/08/2021 | 10/09/2021 | 0 | TK_Complete | 1112893334 | 585 | 1112893334_585
C730C157CK###D40890 | TT_Task | Antennas and Cabling (BZZ Xover- Blue Point Shaft Up Track) | 07/09/2022 | 09/09/2022 | 25/02/2022 | 11/03/2022 | 0 | TK_Complete | 1112893334 | 584 | 1112893334_584
C730C157CK###D40450 | TT_Task | Antennas and Cabling - Final Work (BZZ Xover- Blue Point Shaft Down Track) | 30/08/2022 | 31/08/2022 | 07/02/2022 | 18/02/2022 | 0 | TK_Complete | 1112893334 | 584 | 1112893334_584
C730C157CK###N42173 | TT_Task | Antennas and Cabling (BZZ Xover- Blue Point Shaft Down Track) | 26/11/2021 | 29/11/2021 | 01/09/2021 | 01/09/2021 | 0 | TK_Complete | 1112893334 | 584 | 1112893334_584
C730C157CK###D40600 | TT_Task | Antennas and Cabling (Blue Point Shaft to VIC Up Track)(Hi-Rail) | 25/02/2022 | 03/03/2022 | 21/02/2022 | 25/02/2022 | 0 | TK_Complete | 1112893334 | 584 | 1112893334_584
C730C157CK###D40740 | TT_Task | Antennas and Cabling - Final Work (Blue Point Shaft to VIC Down Track) | 05/09/2022 | 08/09/2022 | 14/02/2022 | 16/02/2022 | 0 | TK_Complete | 1112893334 | 584 | 1112893334_584
C730C157CK###N42180 | TT_Task | Antennas and Cabling (Blue Point Shaft to VIC Down Track) | 06/10/2021 | 06/10/2021 | 27/08/2021 | 30/08/2021 | 0 | TK_Complete | 1112893334 | 584 | 1112893334_584
C730C157CK###D40880 | TT_Task | Axle Counters - Mechanical (BZZ Xover- Blue Point Shaft Up Track) | 30/08/2022 | 30/08/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 583 | 1112893334_583
C730C157CK###D40440 | TT_Task | Axle Counters - Mechanical (BZZ Xover- Blue Point Shaft Down Track) | 02/09/2022 | 02/09/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 583 | 1112893334_583
C730C157CK###D40590 | TT_Task | Axle Counters - Mechanical (Blue Point Shaft to VIC Up Track) | 02/09/2022 | 05/09/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 583 | 1112893334_583
C730C157CK###D40730 | TT_Task | Axle Counters - Mechanical (Blue Point Shaft to VIC Down Track) | 25/08/2021 | 26/08/2021 | 16/08/2021 | 31/08/2021 | 0 | TK_Complete | 1112893334 | 583 | 1112893334_583
C730C157CK###D40870 | TT_Task | SAB - Mechanical (BZZ Xover- Blue Point Shaft Up Track) | 31/08/2022 | 01/09/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 582 | 1112893334_582
C730C157CK###D40430 | TT_Task | SAB - Mechanical (BZZ Xover- Blue Point Shaft Down Track) | 05/09/2022 | 05/09/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 582 | 1112893334_582
C730C157CK###D41750 | TT_Task | SAB - Mechanical (Blue Point Shaft to VIC Up Track) | 06/09/2022 | 07/09/2022 | nan | nan | 140 | TK_NotStart | 1112893334 | 582 | 1112893334_582
C730C157CK###D41760 | TT_Task | SPB - Mechanical - Backbone (Blue Point Shaft to VIC Up Track) | 12/09/2022 | 12/09/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 582 | 1112893334_582
C730C157CK###D41340 | TT_Task | SAB - Mechanical (Blue Point Shaft to VIC Down Track) | 27/08/2021 | 30/08/2021 | 18/08/2021 | 19/08/2021 | 0 | TK_Complete | 1112893334 | 582 | 1112893334_582
C730C157CK###D40860 | TT_Task | Material Distribution (BZZ Xover- Blue Point Shaft Up Track) | 02/12/2021 | 06/12/2021 | 13/09/2021 | 14/09/2021 | 0 | TK_Complete | 1112893334 | 581 | 1112893334_581
C730C157CK###D40420 | TT_Task | Material Distribution (BZZ Xover- Blue Point Shaft Down Track) | 21/09/2021 | 22/09/2021 | 20/08/2021 | 24/08/2021 | 0 | TK_Complete | 1112893334 | 581 | 1112893334_581
C730C157CK###D40580 | TT_Task | Material Distribution (Blue Point Shaft to VIC Up Track) | 31/08/2022 | 02/09/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 581 | 1112893334_581
C730C157CK###D40720 | TT_Task | Material Distribution (Blue Point Shaft to VIC Down Track) | 30/08/2021 | 02/09/2021 | 06/08/2021 | 16/08/2021 | 0 | TK_Complete | 1112893334 | 581 | 1112893334_581
C730C157CK###D40330 | TT_Task | Equipment set out (BZZ Xover- Blue Point Shaft Up Track) | 01/12/2021 | 02/12/2021 | 13/09/2021 | 13/09/2021 | 0 | TK_Complete | 1112893334 | 580 | 1112893334_580
C730C157CK###D40410 | TT_Task | Equipment set out (BZZ Xover- Blue Point Shaft Down Track) | 20/09/2021 | 20/09/2021 | 18/08/2021 | 20/08/2021 | 0 | TK_Complete | 1112893334 | 580 | 1112893334_580
C730C157CK###D40570 | TT_Task | Equipment set out (Blue Point Shaft to VIC Up Track) | 30/08/2022 | 30/08/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 580 | 1112893334_580
C730C157CK###D40710 | TT_Task | Equipment set out (Blue Point Shaft to VIC Down Track) | 27/08/2021 | 30/08/2021 | 04/08/2021 | 05/08/2021 | 0 | TK_Complete | 1112893334 | 580 | 1112893334_580
C720P147CF###0030880 | TT_Task | BA Traction converter | 25/02/2020 | 18/03/2020 | 05/12/2019 | 10/12/2019 | 0 | TK_Complete | 1112893334 | 58 | 1112893334_58
C720P147CF###0030740 | TT_Task | BA Traction motor | 25/02/2020 | 23/03/2020 | 05/12/2019 | 25/02/2020 | 0 | TK_Complete | 1112893334 | 58 | 1112893334_58
C720P147CF###0030980 | TT_Task | PO Traction converter | 25/02/2020 | 16/03/2020 | 11/12/2019 | 17/12/2019 | 0 | TK_Complete | 1112893334 | 58 | 1112893334_58
C720P147CF###0031010 | TT_Task | PO Traction motor | 25/03/2020 | 23/04/2020 | 23/03/2020 | 24/03/2020 | 0 | TK_Complete | 1112893334 | 58 | 1112893334_58
C720P147CF###0031060 | TT_Task | Production Traction converter | 27/04/2020 | 08/12/2020 | 31/03/2020 | 23/10/2020 | 0 | TK_Complete | 1112893334 | 58 | 1112893334_58
C720P147CF###0031050 | TT_Task | Production Traction motor | 27/04/2020 | 22/12/2020 | 16/04/2020 | 28/10/2020 | 0 | TK_Complete | 1112893334 | 58 | 1112893334_58
C720P147CF###0031880 | TT_Task | DEL Traction converter | 02/11/2020 | 27/11/2020 | 28/10/2020 | 08/12/2020 | 0 | TK_Complete | 1112893334 | 58 | 1112893334_58
C720P147CF###0031940 | TT_Task | DEL Traction motor | 18/11/2020 | 15/12/2020 | 30/10/2020 | 30/11/2020 | 0 | TK_Complete | 1112893334 | 58 | 1112893334_58
C730C157CK###D41620 | TT_Task | Field Copper Cable - Termination - DCS Power ; Earthing (BZZ X-over to BZZ Down) | 21/09/2022 | 21/09/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 579 | 1112893334_579
C730C157CK###D40940 | TT_Task | Field Copper Cable - Termination - DCS Power ; Earthing (BZZ Xover- Blue Point Shaft Up Track) | 19/09/2022 | 20/09/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 579 | 1112893334_579
C730C157CK###D40510 | TT_Task | Field Copper Cable - Termination - DCS Power ; Earthing (BZZ Xover- Blue Point Shaft Down Track) | 14/09/2022 | 15/09/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 579 | 1112893334_579
C730C157CK###D40650 | TT_Task | Field Copper Cable - Termination - DCS Power ; Earthing (Blue Point Shaft to VIC Up Track) | 23/09/2022 | 27/09/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 579 | 1112893334_579
C730C157CK###D40790 | TT_Task | Field Copper Cable - Termination - DCS Power ; Earthing (Blue Point Shaft to VIC Down Track) | 08/09/2022 | 12/09/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 579 | 1112893334_579
C730C157CK###D41150 | TT_Task | Completions, defect, rectification, final sweep (Hi-Rail) (BZZ X-over to BZZ Up) | 26/09/2022 | 26/09/2022 | nan | nan | 110 | TK_NotStart | 1112893334 | 578 | 1112893334_578
C730C157CK###D41240 | TT_Task | Completions, defect, rectification, final sweep (Hi-Rail) (BZZ X-over to BZZ Down) | 23/09/2022 | 23/09/2022 | nan | nan | 120 | TK_NotStart | 1112893334 | 578 | 1112893334_578
C730C157CK###D40360 | TT_Task | Completions, defect rectifacation, final sweep (BZZ Xover- Blue Point Shaft Up Track) | 21/09/2022 | 26/09/2022 | nan | nan | 110 | TK_NotStart | 1112893334 | 578 | 1112893334_578
C730C157CK###D40520 | TT_Task | Completions, defect rectifacation, final sweep (BZZ Xover- Blue Point Shaft Down Track) | 22/09/2022 | 27/09/2022 | nan | nan | 100 | TK_NotStart | 1112893334 | 578 | 1112893334_578
C730C157CK###D40660 | TT_Task | Completions, defect rectifacation, final sweep (Blue Point Shaft to VIC Up Track)(Hi-Rail) | 06/10/2022 | 12/10/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 578 | 1112893334_578
C730C157CK###D40800 | TT_Task | Completions, defect rectifacation, final sweep (Blue Point Shaft to VIC Down Track)(Hi-Rail) | 21/09/2022 | 27/09/2022 | nan | nan | 100 | TK_NotStart | 1112893334 | 578 | 1112893334_578
C730C157CK###D41280 | TT_Task | Points Machine - Electrical (BZZ X-over to BZZ Up) | 20/09/2022 | 22/09/2022 | nan | nan | 10 | TK_NotStart | 1112893334 | 577 | 1112893334_577
C730C157CK###D41320 | TT_Task | Points Machine - Electrical (BZZ X-over to BZZ Down) | 20/09/2022 | 22/09/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 577 | 1112893334_577
C730C157CK###D41270 | TT_Task | Field Cable - Installation - PPI Cables (BZZ X-over to BZZ Up) | 13/09/2022 | 13/09/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 576 | 1112893334_576
C730C157CK###D41200 | TT_Task | Field Cable - Installation -PPI Cables (BZZ X-over to BZZ Down) | 13/09/2022 | 13/09/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 576 | 1112893334_576
C730C157CK###D41710 | TT_Task | Field Cable - Installation - PPI (BZZ Xover- Blue Point Shaft Up Track) | 09/09/2022 | 09/09/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 576 | 1112893334_576
C730C157CK###D41730 | TT_Task | Field Cable - Installation - PPI (BZZ Xover- Blue Point Shaft Down Track) | 09/09/2022 | 09/09/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 576 | 1112893334_576
C730C157CK###D41110 | TT_Task | TRE Power ((BZZ X-over to BZZ Up) | 14/09/2022 | 14/09/2022 | nan | nan | 70 | TK_NotStart | 1112893334 | 575 | 1112893334_575
C730C157CK###D41310 | TT_Task | TRE Power (BZZ X-over to BZZ Down) | 14/09/2022 | 14/09/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 575 | 1112893334_575
C730C157CK###D41090 | TT_Task | Field Cable - Installation - SAB Cables (BZZ X-over to BZZ Up) | 16/09/2022 | 16/09/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 574 | 1112893334_574
C730C157CK###D41100 | TT_Task | Field Cable - Installation - AxCo (BZZ X-over to BZZ Up) | 16/09/2022 | 16/09/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 574 | 1112893334_574
C730C157CK###D41260 | TT_Task | Field Cable - Installation - Point Cables (BZZ X-over to BZZ Up) | 13/09/2022 | 13/09/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 574 | 1112893334_574
C730C157CK###D41640 | TT_Task | Field Cable - Tying in (BZZ X-over to BZZ Up) | 19/09/2022 | 19/09/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 574 | 1112893334_574
C730C157CK###D41180 | TT_Task | Field Cable - Installation -SAB Cables (BZZ X-over to BZZ Down) | 16/09/2022 | 16/09/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 574 | 1112893334_574
C730C157CK###D41190 | TT_Task | Field Cable - Installation - AxCo (BZZ X-over to BZZ Down) | 16/09/2022 | 16/09/2022 | nan | nan | 10 | TK_NotStart | 1112893334 | 574 | 1112893334_574
C730C157CK###D41300 | TT_Task | Field Cable - Installation -Point Cables (BZZ X-over to BZZ Down) | 13/09/2022 | 13/09/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 574 | 1112893334_574
C730C157CK###D41690 | TT_Task | Field Cable - Tying in (BZZ X-over to BZZ Down) | 19/09/2022 | 19/09/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 574 | 1112893334_574
C730C157CK###D41070 | TT_Task | Field Cable - Installation - TRE Fibre (BZZ X-over to BZZ Up) | 14/09/2022 | 14/09/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 573 | 1112893334_573
C730C157CK###D41080 | TT_Task | Field Cable - Installation - Fibre Backbone (BZZ X-over to BZZ Up) | 15/09/2022 | 15/09/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 573 | 1112893334_573
C730C157CK###D41160 | TT_Task | Field Cable - Installation -TRE Fibre (BZZ X-over to BZZ Down) | 14/09/2022 | 14/09/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 573 | 1112893334_573
C730C157CK###D41170 | TT_Task | Field Cable - Installation -Fibre Backbone (BZZ X-over to BZZ Down) | 15/09/2022 | 15/09/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 573 | 1112893334_573
C730C157CK###D41630 | TT_Task | SPB - Mechanical - Backbone (BZZ X-over to BZZ Up) | 02/09/2022 | 02/09/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 572 | 1112893334_572
C730C157CK###D41670 | TT_Task | SPB - Mechanical - Backbone (BZZ X-over to BZZ Down) | 05/09/2022 | 05/09/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 572 | 1112893334_572
C730C157CK###D41550 | TT_Task | Marker Boards - Mechanical (BZZ X-over to BZZ Up) | 31/08/2022 | 31/08/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 571 | 1112893334_571
C730C157CK###D41600 | TT_Task | Marker Boards (BZZ X-over to BZZ Down) | 31/08/2022 | 31/08/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 571 | 1112893334_571
C730C157CK###D41520 | TT_Task | DCS Splice Box (BZZ X-over to BZZ Up) | 02/09/2022 | 02/09/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 570 | 1112893334_570
C730C157CK###D41530 | TT_Task | DCS TRE Box - Mechanical (BZZ X-over to BZZ Up) | 01/09/2022 | 01/09/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 570 | 1112893334_570
C730C157CK###D41560 | TT_Task | DCS TRE Box - Mechanical (BZZ X-over to BZZ Down) | 01/09/2022 | 05/09/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 570 | 1112893334_570
C730C157CK###D41570 | TT_Task | DCS Splice Box (BZZ X-over to BZZ Down) | 05/09/2022 | 05/09/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 570 | 1112893334_570
C720P147CF###0030870 | TT_Task | BA Battery ; battery box | 25/02/2020 | 20/03/2020 | 05/12/2019 | 07/04/2020 | 0 | TK_Complete | 1112893334 | 57 | 1112893334_57
C720P147CF###0031100 | TT_Task | PO Battery ; battery box | 27/04/2020 | 14/05/2020 | 08/04/2020 | 17/04/2020 | 0 | TK_Complete | 1112893334 | 57 | 1112893334_57
C720P147CF###0031200 | TT_Task | Production Battery ; battery box | 15/06/2020 | 10/03/2021 | 27/04/2020 | 04/12/2020 | 0 | TK_Complete | 1112893334 | 57 | 1112893334_57
C720P147CF###0032020 | TT_Task | DEL Battery ; battery box | 11/01/2021 | 01/02/2021 | 04/12/2020 | 21/12/2020 | 0 | TK_Complete | 1112893334 | 57 | 1112893334_57
C730C157CK###D41510 | TT_Task | PMDB Box/Points Gear (BZZ X-over to BZZ Up) | 09/09/2022 | 12/09/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 569 | 1112893334_569
C730C157CK###D41540 | TT_Task | PMDB Box/Points Gear (BZZ X-over to BZZ Down) | 07/09/2022 | 08/09/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 569 | 1112893334_569
C730C157CK###D41500 | TT_Task | Equipment set out (BZZ X-over to BZZ Up) | 29/08/2022 | 29/08/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 568 | 1112893334_568
C730C157CK###D41020 | TT_Task | Equipment Set Out (BZZ X-over to BZZ Down) | 29/08/2022 | 29/08/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 568 | 1112893334_568
C730C157CK###D41250 | TT_Task | Point Fitting (BZZ X-over to BZZ Up) | 05/09/2022 | 08/09/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 567 | 1112893334_567
C730C157CK###D41290 | TT_Task | Point Fitting (BZZ X-over to BZZ Down) | 07/09/2022 | 12/09/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 567 | 1112893334_567
C730C157CK###D41000 | TT_Task | PPI Structure (BZZ X-over to BZZ Up) | 01/09/2022 | 02/09/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 566 | 1112893334_566
C730C157CK###D41140 | TT_Task | PPI - Termination (BZZ X-over to BZZ Up) | 21/09/2022 | 22/09/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 566 | 1112893334_566
C730C157CK###D41330 | TT_Task | PPI Structure (BZZ X-over to BZZ Down) | 05/09/2022 | 06/09/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 566 | 1112893334_566
C730C157CK###D41230 | TT_Task | PPI - Termination (BZZ X-over to BZZ Down) | 20/09/2022 | 21/09/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 566 | 1112893334_566
C730C157CK###D40980 | TT_Task | Axle Counters - Mechanical (BZZ X-over to BZZ Up) | 31/08/2022 | 31/08/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 565 | 1112893334_565
C730C157CK###D41130 | TT_Task | Axle Counter - Terminations (BZZ X-over to BZZ Up) | 21/09/2022 | 21/09/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 565 | 1112893334_565
C730C157CK###D41050 | TT_Task | Axle Counters - Mechanical (BZZ X-over to BZZ Down) | 30/08/2022 | 31/08/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 565 | 1112893334_565
C730C157CK###D41220 | TT_Task | Axle Counter - Terminations (BZZ X-over to BZZ Down) | 20/09/2022 | 20/09/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 565 | 1112893334_565
C730C157CK###D40970 | TT_Task | SAB - Mechanical (BZZ X-over to BZZ Up) | 01/09/2022 | 01/09/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 564 | 1112893334_564
C730C157CK###D41010 | TT_Task | Balise - Mechanical(BZZ X-over to BZZ Up) | 31/08/2022 | 31/08/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 564 | 1112893334_564
C730C157CK###D41040 | TT_Task | SAB - Mechanical (BZZ X-over to BZZ Down) | 31/08/2022 | 31/08/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 564 | 1112893334_564
C730C157CK###D41660 | TT_Task | Balise - Mechanical (BZZ X-over to BZZ Down) | 30/08/2022 | 30/08/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 564 | 1112893334_564
C730C157CK###D40960 | TT_Task | Material Distribution (BZZ X-over to BZZ Up) | 30/08/2022 | 30/08/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 563 | 1112893334_563
C730C157CK###D41030 | TT_Task | Material Distribution (BZZ X-over to BZZ Down) | 29/08/2022 | 29/08/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 563 | 1112893334_563
C730C157CL###D40420 | TT_Task | Field Copper Cable - Termination - SAB (MPL-BZZ Up Track) | 01/04/2022 | 04/04/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 562 | 1112893334_562
C730C157CL###D40460 | TT_Task | Field Copper Cable - Termination - SAB (MPL-BZZ Down Track) | 25/03/2022 | 28/03/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 562 | 1112893334_562
C730C157CK###D41120 | TT_Task | Field Copper Cable - Termination - SAB (BZZ X-over to BZZ Up) | 23/09/2022 | 23/09/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 562 | 1112893334_562
C730C157CK###D41210 | TT_Task | Field Copper Cable - Termination - SAB (BZZ X-over to BZZ Down) | 21/09/2022 | 21/09/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 562 | 1112893334_562
C730C157CL###D40320 | TT_Task | Field Cable - Installation - SAB Cables (MPL-BZZ Up Track) | 07/03/2022 | 07/03/2022 | 01/03/2022 | 02/03/2022 | 0 | TK_Complete | 1112893334 | 561 | 1112893334_561
C730C157CL###D40530 | TT_Task | Field Cable - Installation - SAB Cables (MPL-BZZ Down Track) | 10/03/2022 | 10/03/2022 | 10/03/2022 | 10/03/2022 | 0 | TK_Complete | 1112893334 | 561 | 1112893334_561
C730C157CK###D40830 | TT_Task | Field Cable - Installation -SAB Cables (BZZ Xover- Blue Point Shaft Up Track) | 07/09/2022 | 07/09/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 561 | 1112893334_561
C730C157CK###D40380 | TT_Task | Field Cable - Installation - SAB Cables (BZZ Xover- Blue Point Shaft Down Track) | 30/08/2022 | 30/08/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 561 | 1112893334_561
C730C157CK###D41770 | TT_Task | Field Cable - Installation - SAB Cables (Blue Point Shaft to VIC Up Track) | 16/09/2022 | 16/09/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 561 | 1112893334_561
C730C157CK###D41810 | TT_Task | Field Cable - Installation - SAB Cables (Blue Point Shaft to VIC Down Track) | 31/08/2022 | 31/08/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 561 | 1112893334_561
C730C157CL###D41020 | TT_Task | Delay in Balise installation due to Rail dragging to the section (MPL-BZZ Up Track) | 24/01/2022 | 24/01/2022 | 25/01/2022 | nan | 0 | TK_Active | 1112893334 | 560 | 1112893334_560
C730C157CL###D41030 | TT_Task | Delay in Balise installation due to Rail dragging to the section (MPL-BZZ Down Track) | 04/02/2022 | 12/04/2022 | 04/02/2022 | nan | 0 | TK_Active | 1112893334 | 560 | 1112893334_560
C730C157CP###D41250 | TT_Task | Delay in Balise installation due to Rail in 4ft area (CST-ND Down Track) | 27/01/2022 | 27/01/2022 | 18/12/2021 | nan | 0 | TK_Active | 1112893334 | 560 | 1112893334_560
C720P147CF###0030860 | TT_Task | BA Pantograph | 25/02/2020 | 17/03/2020 | 05/12/2019 | 13/04/2020 | 0 | TK_Complete | 1112893334 | 56 | 1112893334_56
C720P147CF###0031250 | TT_Task | PO Pantograph | 27/04/2020 | 05/06/2020 | 15/04/2020 | 17/04/2020 | 0 | TK_Complete | 1112893334 | 56 | 1112893334_56
C720P147CF###0031350 | TT_Task | Production Pantograph | 25/05/2020 | 04/02/2021 | 27/04/2020 | 30/09/2020 | 0 | TK_Complete | 1112893334 | 56 | 1112893334_56
C720P147CF###0032120 | TT_Task | DEL Pantograph | 11/11/2020 | 01/12/2020 | 01/10/2020 | 27/10/2020 | 0 | TK_Complete | 1112893334 | 56 | 1112893334_56
C730C157CL###D41010 | TT_Task | Delay in equipment installation due to access blocked (MPL-BZZ Up Track) | 14/02/2022 | 14/02/2022 | 25/01/2022 | nan | 0 | TK_Active | 1112893334 | 559 | 1112893334_559
C730C157CL###D41040 | TT_Task | Delay in equipment installation due to access blocked (MPL-BZZ Down Track) | 04/02/2022 | 01/04/2022 | 04/02/2022 | nan | 0 | TK_Active | 1112893334 | 559 | 1112893334_559
C730C157CL###D40380 | TT_Task | Antennas and Cabling (MPL-BZZ Up Track) | 04/01/2022 | 10/01/2022 | 17/01/2022 | 10/02/2022 | 0 | TK_Complete | 1112893334 | 558 | 1112893334_558
C730C157CL###D40580 | TT_Task | Antennas and Cabling (MPL-BZZ Down Track) | 03/02/2022 | 09/02/2022 | 03/02/2022 | 25/02/2022 | 0 | TK_Complete | 1112893334 | 558 | 1112893334_558
C730C157CL###D41090 | TT_Task | Antennas and Cabling - Mechanical - Remaining (MPL-BZZ Down Track) | 01/04/2022 | 01/04/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 558 | 1112893334_558
C730C157CK###D40990 | TT_Task | Antennas and Cabling (BZZ X-over to BZZ Up) | 02/09/2022 | 02/09/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 558 | 1112893334_558
C730C157CK###D41060 | TT_Task | Antennas and Cabling (BZZ X-over to BZZ Down) | 01/09/2022 | 02/09/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 558 | 1112893334_558
C730C157CL###D40280 | TT_Task | SAB - Mechanical (MPL-BZZ Up Track) | 25/03/2022 | 25/03/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 557 | 1112893334_557
C730C157CL###D40490 | TT_Task | SAB - Mechanical (MPL-BZZ Down Track) | 01/04/2022 | 01/04/2022 | nan | nan | 80 | TK_NotStart | 1112893334 | 557 | 1112893334_557
C730C157CM###D40540 | TT_Task | Completions, defect rectifacation, final sweep (PIT-MPL Up Track) | 03/05/2022 | 09/05/2022 | nan | nan | 180 | TK_NotStart | 1112893334 | 556 | 1112893334_556
C730C157CM###D40680 | TT_Task | Completions, defect rectifacation, final sweep (PIT-MPL Down Track) | 27/05/2022 | 02/06/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 556 | 1112893334_556
C730C157CL###D40370 | TT_Task | Completions, defect rectifacation, final sweep (MPL-BZZ Up Track) | 21/04/2022 | 28/04/2022 | nan | nan | 980 | TK_NotStart | 1112893334 | 556 | 1112893334_556
C730C157CL###D40500 | TT_Task | Completions, defect rectifacation, final sweep (MPL-BZZ Down Track) | 19/04/2022 | 26/04/2022 | nan | nan | 1000 | TK_NotStart | 1112893334 | 556 | 1112893334_556
C730C157CM###D41010 | TT_Task | Field Cable - Tying in (PIT-MPL Up Track) | 14/04/2022 | 22/04/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 555 | 1112893334_555
C730C157CM###D41020 | TT_Task | Field Cable - Tying in (PIT-MPL Up Track) | 13/05/2022 | 19/05/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 555 | 1112893334_555
C730C157CL###D40930 | TT_Task | Field Cable - Tying in (MPL-BZZ Up Track) | 11/03/2022 | 15/03/2022 | 03/03/2022 | 04/03/2022 | 0 | TK_Complete | 1112893334 | 555 | 1112893334_555
C730C157CL###D40940 | TT_Task | Field Cable - Tying in (MPL-BZZ Up Track) | 15/03/2022 | 17/03/2022 | 15/03/2022 | 17/03/2022 | 0 | TK_Complete | 1112893334 | 555 | 1112893334_555
C730C157CM###D40440 | TT_Task | TRE power (PIT-MPL Up Track) | 13/04/2022 | 13/04/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 554 | 1112893334_554
C730C157CM###D40580 | TT_Task | TRE power (PIT-MPL Down Track) | 11/05/2022 | 12/05/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 554 | 1112893334_554
C730C157CL###D40330 | TT_Task | TRE power (MPL-BZZ Up Track) | 09/03/2022 | 10/03/2022 | 28/02/2022 | 28/02/2022 | 0 | TK_Complete | 1112893334 | 554 | 1112893334_554
C730C157CL###D40450 | TT_Task | TRE power (MPL-BZZ Down Track) | 14/03/2022 | 14/03/2022 | 14/03/2022 | 14/03/2022 | 0 | TK_Complete | 1112893334 | 554 | 1112893334_554
C730C157CM###D40430 | TT_Task | Field Cable - Installation - AxCo (PIT-MPL Up Track) | 12/04/2022 | 12/04/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 553 | 1112893334_553
C730C157CM###D40570 | TT_Task | Field Cable - Installation - AxCo (PIT-MPL Down Track) | 10/05/2022 | 10/05/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 553 | 1112893334_553
C730C157CL###D40270 | TT_Task | Field Cable - Installation - AxCo (MPL-BZZ Up Track) | 07/03/2022 | 07/03/2022 | 01/03/2022 | 02/03/2022 | 0 | TK_Complete | 1112893334 | 553 | 1112893334_553
C730C157CL###D40540 | TT_Task | Field Cable - Installation - AxCo (MPL-BZZ Down Track) | 10/03/2022 | 10/03/2022 | 10/03/2022 | 10/03/2022 | 0 | TK_Complete | 1112893334 | 553 | 1112893334_553
C730C157CM###D40410 | TT_Task | Field Cable - Installation - DCS Fibre (PIT-MPL Up Track) | 13/04/2022 | 13/04/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 552 | 1112893334_552
C730C157CM###D40420 | TT_Task | Field Cable - Installation - Fibre Backbone (PIT-MPL Up Track) | 12/04/2022 | 12/04/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 552 | 1112893334_552
C730C157CM###D40550 | TT_Task | Field Cable - Installation - DCS Fibre (PIT-MPL Down Track) | 11/05/2022 | 11/05/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 552 | 1112893334_552
C730C157CM###D40560 | TT_Task | Field Cable - Installation - Fibre Backbone (PIT-MPL Down Track) | 10/05/2022 | 10/05/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 552 | 1112893334_552
C730C157CL###D40290 | TT_Task | Field Cable - Installation - DCS Fibre (MPL-BZZ Up Track) | 01/03/2022 | 01/03/2022 | 01/03/2022 | 03/03/2022 | 0 | TK_Complete | 1112893334 | 552 | 1112893334_552
C730C157CL###D40390 | TT_Task | Field Cable - Installation - Fibre Backbone (MPL-BZZ Up Track) | 08/03/2022 | 08/03/2022 | 02/03/2022 | 03/03/2022 | 0 | TK_Complete | 1112893334 | 552 | 1112893334_552
C730C157CL###D40430 | TT_Task | Field Cable - Installation - Fibre Backbone (MPL-BZZ Down Track) | 11/03/2022 | 11/03/2022 | 11/03/2022 | 11/03/2022 | 0 | TK_Complete | 1112893334 | 552 | 1112893334_552
C730C157CL###D40510 | TT_Task | Field Cable - Installation - DCS Fibre (MPL-BZZ Down Track) | 14/03/2022 | 14/03/2022 | 14/03/2022 | 14/03/2022 | 0 | TK_Complete | 1112893334 | 552 | 1112893334_552
C730C157CM###N41150 | TT_Task | Delay in Site Readiness of Rail Mounted Equipment (PIT-MPL Up Track) | 18/02/2022 | 18/02/2022 | 11/03/2022 | nan | 0 | TK_Active | 1112893334 | 551 | 1112893334_551
C730C157CM###D41170 | TT_Task | Delay in Site Readiness of Rail Mounted Equipment (PIT-MPL Down Track) | 18/02/2022 | 18/02/2022 | 11/03/2022 | nan | 0 | TK_Active | 1112893334 | 551 | 1112893334_551
C730C157CM###N41110 | TT_Task | MTR's direction to Prioritise MPL-BGU (PIT-MPL Up Track) | 18/02/2022 | 18/02/2022 | 08/02/2022 | 11/03/2022 | 0 | TK_Complete | 1112893334 | 550 | 1112893334_550
C730C157CM###D41120 | TT_Task | MTR's direction to Prioritise MPL-BGU (PIT-MPL Down Track) | 18/02/2022 | 18/02/2022 | 08/02/2022 | 11/03/2022 | 0 | TK_Complete | 1112893334 | 550 | 1112893334_550
C720P147CF###0030850 | TT_Task | BA Cabinets | 25/02/2020 | 17/03/2020 | 05/12/2019 | 14/01/2020 | 0 | TK_Complete | 1112893334 | 55 | 1112893334_55
C720P147CF###0031330 | TT_Task | PO Cabinets | 25/03/2020 | 31/03/2020 | 19/02/2020 | 25/02/2020 | 0 | TK_Complete | 1112893334 | 55 | 1112893334_55
C720P147CF###0031500 | TT_Task | Production Cabinets | 25/08/2020 | 11/02/2021 | 10/08/2020 | 30/11/2020 | 0 | TK_Complete | 1112893334 | 55 | 1112893334_55
C720P147CF###0031970 | TT_Task | DEL Cabinets | 11/01/2021 | 01/02/2021 | 30/11/2020 | 11/12/2020 | 0 | TK_Complete | 1112893334 | 55 | 1112893334_55
C730C157CM###D41060 | TT_Task | Site Inspection (PIT-MPL Up Track) | 18/03/2022 | 18/03/2022 | 04/02/2022 | 04/02/2022 | 0 | TK_Complete | 1112893334 | 549 | 1112893334_549
C730C157CM###D41080 | TT_Task | Site Inspection (PIT-MPL Down Track) | 25/01/2022 | 25/01/2022 | 07/02/2022 | 07/02/2022 | 0 | TK_Complete | 1112893334 | 549 | 1112893334_549
C730C157CL###D40980 | TT_Task | Site Inspection (MPL-BZZ Up Track) | 04/01/2022 | 04/01/2022 | 17/01/2022 | 17/01/2022 | 0 | TK_Complete | 1112893334 | 549 | 1112893334_549
C730C157CL###D41000 | TT_Task | Site Inspection (MPL-BZZ Down Track) | 20/01/2022 | 20/01/2022 | 21/01/2022 | 21/01/2022 | 0 | TK_Complete | 1112893334 | 549 | 1112893334_549
C730C157CM###D40710 | TT_Task | Marker Boards (PIT-MPL Up Track) | 11/04/2022 | 11/04/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 548 | 1112893334_548
C730C157CM###D40740 | TT_Task | Marker Boards (PIT-MPL Down Track) | 08/04/2022 | 08/04/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 548 | 1112893334_548
C730C157CL###D40660 | TT_Task | Marker Boards (MPL-BZZ Up Track) | 02/03/2022 | 03/03/2022 | 28/02/2022 | 01/03/2022 | 0 | TK_Complete | 1112893334 | 548 | 1112893334_548
C730C157CL###D40630 | TT_Task | Marker Boards (MPL-BZZ Down Track) | 07/03/2022 | 08/03/2022 | 28/02/2022 | 02/03/2022 | 0 | TK_Complete | 1112893334 | 548 | 1112893334_548
C730C157CM###D40690 | TT_Task | DCS Splice Box (PIT-MPL Up Track) | 22/03/2022 | 22/03/2022 | 15/03/2022 | 15/03/2022 | 0 | TK_Complete | 1112893334 | 547 | 1112893334_547
C730C157CM###D40720 | TT_Task | DCS Splice Box (PIT-MPL Down Track) | 22/03/2022 | 22/03/2022 | 16/03/2022 | 16/03/2022 | 0 | TK_Complete | 1112893334 | 547 | 1112893334_547
C730C157CL###D40640 | TT_Task | DCS Splice Box (MPL-BZZ Up Track) | 02/03/2022 | 03/03/2022 | 21/02/2022 | 22/02/2022 | 0 | TK_Complete | 1112893334 | 547 | 1112893334_547
C730C157CL###N41060 | TT_Task | DCS Splice Box - Remaining (MPL-BZZ Up Track) | 01/04/2022 | 01/04/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 547 | 1112893334_547
C730C157CL###D40610 | TT_Task | DCS Splice Box (MPL-BZZ Down Track) | 07/03/2022 | 08/03/2022 | 21/02/2022 | 21/02/2022 | 0 | TK_Complete | 1112893334 | 547 | 1112893334_547
C730C157CL###D41110 | TT_Task | DCS Splice Box - Remaining (MPL-BZZ Down Track) | 05/04/2022 | 05/04/2022 | nan | nan | 60 | TK_NotStart | 1112893334 | 547 | 1112893334_547
C730C157CM###D40500 | TT_Task | Balise - Mechanical (PIT-MPL Up Track) | 05/04/2022 | 06/04/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 546 | 1112893334_546
C730C157CM###D40640 | TT_Task | Balise - Mechanical (PIT-MPL Down Track) | 05/04/2022 | 06/04/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 546 | 1112893334_546
C730C157CL###D40400 | TT_Task | Balise - Mechanical (MPL-BZZ Up Track) | 12/04/2022 | 20/04/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 546 | 1112893334_546
C730C157CL###D40590 | TT_Task | Balise - Mechanical (MPL-BZZ Down Track) | 14/04/2022 | 22/04/2022 | nan | nan | 8788 | TK_NotStart | 1112893334 | 546 | 1112893334_546
C730C157CM###D40490 | TT_Task | DCS TRE Box - Mechanical (PIT-MPL Up Track) | 25/01/2022 | 25/01/2022 | 04/02/2022 | 04/02/2022 | 0 | TK_Complete | 1112893334 | 545 | 1112893334_545
C730C157CM###N41120 | TT_Task | DCS TRE Box - Mechanical outstanding (PIT-MPL Up Track) | 15/03/2022 | 15/03/2022 | 15/03/2022 | 15/03/2022 | 0 | TK_Complete | 1112893334 | 545 | 1112893334_545
C730C157CM###D40630 | TT_Task | DCS TRE Box - Mechanical (PIT-MPL Down Track) | 02/02/2022 | 03/02/2022 | 07/02/2022 | 07/02/2022 | 0 | TK_Complete | 1112893334 | 545 | 1112893334_545
C730C157CM###D41140 | TT_Task | DCS TRE Box - Mechanical - Outstanding(PIT-MPL Down Track) | 16/03/2022 | 16/03/2022 | 16/03/2022 | 22/03/2022 | 0 | TK_Complete | 1112893334 | 545 | 1112893334_545
C730C157CL###D40480 | TT_Task | DCS TRE Box - Mechanical (MPL-BZZ Up Track) | 28/01/2022 | 04/02/2022 | 04/02/2022 | 25/02/2022 | 0 | TK_Complete | 1112893334 | 545 | 1112893334_545
C730C157CL###N41050 | TT_Task | DCS TRE Box - Mechanical - Remaining (MPL-BZZ Up Track) | 04/04/2022 | 04/04/2022 | nan | nan | 50 | TK_NotStart | 1112893334 | 545 | 1112893334_545
C730C157CL###D40520 | TT_Task | DCS TRE Box - Mechanical (MPL-BZZ Down Track) | 25/01/2022 | 02/02/2022 | 04/02/2022 | 25/02/2022 | 0 | TK_Complete | 1112893334 | 545 | 1112893334_545
C730C157CL###D41100 | TT_Task | DCS TRE Box - Mechanical - Remaining (MPL-BZZ Down Track) | 04/04/2022 | 04/04/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 545 | 1112893334_545
C730C157CM###D40480 | TT_Task | Antennas and Cabling (PIT-MPL Up Track) | 27/01/2022 | 27/01/2022 | 04/02/2022 | 09/02/2022 | 0 | TK_Complete | 1112893334 | 544 | 1112893334_544
C730C157CM###N41130 | TT_Task | Antennas and Cabling - Outstanding (PIT-MPL Up Track) | 15/03/2022 | 15/03/2022 | 15/03/2022 | 15/03/2022 | 0 | TK_Complete | 1112893334 | 544 | 1112893334_544
C730C157CM###D40620 | TT_Task | Antennas and Cabling (PIT-MPL Down Track) | 04/02/2022 | 04/02/2022 | 07/02/2022 | 07/02/2022 | 0 | TK_Complete | 1112893334 | 544 | 1112893334_544
C730C157CM###D41130 | TT_Task | Antennas and Cabling - Outstanding (PIT-MPL Down Track) | 15/03/2022 | 15/03/2022 | 15/03/2022 | 15/03/2022 | 0 | TK_Complete | 1112893334 | 544 | 1112893334_544
C730C157CM###D40470 | TT_Task | Axle Counters (PIT-MPL Up Track) | 07/04/2022 | 08/04/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 543 | 1112893334_543
C730C157CM###D40520 | TT_Task | Axle Counters (PIT-MPL Up Track) | 26/04/2022 | 26/04/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 543 | 1112893334_543
C730C157CM###D40610 | TT_Task | Axle Counters (PIT-MPL Down Track) | 07/04/2022 | 07/04/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 543 | 1112893334_543
C730C157CL###D40300 | TT_Task | Axle Counters (MPL-BZZ Up Track) | 12/04/2022 | 12/04/2022 | nan | nan | 40 | TK_NotStart | 1112893334 | 543 | 1112893334_543
C730C157CL###D40410 | TT_Task | Axle Counters (MPL-BZZ Down Track) | 13/04/2022 | 13/04/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 543 | 1112893334_543
C730C157CM###D40460 | TT_Task | Material Distribution (PIT-MPL Up Track) | 22/03/2022 | 23/03/2022 | 04/02/2022 | 11/02/2022 | 0 | TK_Complete | 1112893334 | 542 | 1112893334_542
C730C157CM###D40600 | TT_Task | Material Distribution (PIT-MPL Down Track) | 28/01/2022 | 31/01/2022 | 07/02/2022 | 08/02/2022 | 0 | TK_Complete | 1112893334 | 542 | 1112893334_542
C730C157CL###D40310 | TT_Task | Material Distribution (MPL-BZZ Up Track) | 06/01/2022 | 11/01/2022 | 17/01/2022 | 27/01/2022 | 0 | TK_Complete | 1112893334 | 542 | 1112893334_542
C730C157CL###D40570 | TT_Task | Material Distribution (MPL-BZZ Down Track) | 25/01/2022 | 31/01/2022 | 25/01/2022 | 07/02/2022 | 0 | TK_Complete | 1112893334 | 542 | 1112893334_542
C730C157CM###D40450 | TT_Task | Equipment set out (PIT-MPL Up Track) | 18/03/2022 | 21/03/2022 | 04/02/2022 | 04/02/2022 | 0 | TK_Complete | 1112893334 | 541 | 1112893334_541
C730C157CM###D40590 | TT_Task | Equipment set out (PIT-MPL Down Track) | 25/01/2022 | 27/01/2022 | 07/02/2022 | 08/02/2022 | 0 | TK_Complete | 1112893334 | 541 | 1112893334_541
C730C157CL###D40350 | TT_Task | Equipment set out (MPL-BZZ Up Track) | 04/01/2022 | 05/01/2022 | 17/01/2022 | 21/01/2022 | 0 | TK_Complete | 1112893334 | 541 | 1112893334_541
C730C157CL###D40470 | TT_Task | Equipment set out (MPL-BZZ Down Track) | 20/01/2022 | 21/01/2022 | 21/01/2022 | 24/01/2022 | 0 | TK_Complete | 1112893334 | 541 | 1112893334_541
C730C157CN###D40830 | TT_Task | Field Cable - Installation - Fibre Backbone (PIT-MPL Up Track StationBox area) | 13/05/2022 | 13/05/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 540 | 1112893334_540
C730C157CN###D40930 | TT_Task | Field Cable - Installation - Fibre Backbone (PIT-MPL DN Track StationBox area) | 13/05/2022 | 13/05/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 540 | 1112893334_540
C730C157CM###D40850 | TT_Task | Field Cable - Installation - Fibre Backbone (MPL-BZZ Up Track StationBox area) | 23/05/2022 | 23/05/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 540 | 1112893334_540
C730C157CM###D40950 | TT_Task | Field Cable - Installation - Fibre Backbone (MPL-BZZ DN Track StationBox area) | 28/04/2022 | 28/04/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 540 | 1112893334_540
C730C157CL###D40770 | TT_Task | Field Cable - Installation - Fibre Backbone (BZZ-VIC Up Track StationBox area) | 05/09/2022 | 05/09/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 540 | 1112893334_540
C730C157CL###D40870 | TT_Task | Field Cable - Installation - Fibre Backbone (BZZ-VIC DN Track StationBox area) | 06/09/2022 | 06/09/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 540 | 1112893334_540
C730C157CK###D41960 | TT_Task | Field Cable - Installation - Fibre Backbone (VIC-CSTUp Track StationBox area) | 01/04/2022 | 01/04/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 540 | 1112893334_540
C730C157CK###D42060 | TT_Task | Field Cable - Installation - Fibre Backbone (VIC-CST DN Track StationBox area) | 04/04/2022 | 04/04/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 540 | 1112893334_540
C730C157CJ###D41180 | TT_Task | Field Cable - Installation - Fibre Backbone CST-ND Up Track StationBox area) | 13/05/2022 | 13/05/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 540 | 1112893334_540
C730C157CJ###D41280 | TT_Task | Field Cable - Installation - Fibre Backbone (CST-ND DN Track StationBox area) | 01/04/2022 | 01/04/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 540 | 1112893334_540
C720P147CF###0030820 | TT_Task | BA Front mask | 25/02/2020 | 18/03/2020 | 05/12/2019 | 30/04/2020 | 0 | TK_Complete | 1112893334 | 54 | 1112893334_54
C720P147CF###0031130 | TT_Task | PO Front mask | 25/05/2020 | 29/06/2020 | 04/05/2020 | 22/05/2020 | 0 | TK_Complete | 1112893334 | 54 | 1112893334_54
C720P147CF###0031210 | TT_Task | Production Front mask | 25/06/2020 | 01/03/2021 | 29/05/2020 | 30/10/2020 | 0 | TK_Complete | 1112893334 | 54 | 1112893334_54
C720P147CF###0031770 | TT_Task | DEL Front mask | 02/12/2020 | 22/12/2020 | 03/11/2020 | 23/11/2020 | 0 | TK_Complete | 1112893334 | 54 | 1112893334_54
C730C157CN###D40440 | TT_Task | Balise - Mechanical (CEN-PIT Up Track) | 30/03/2022 | 04/04/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 539 | 1112893334_539
C730C157CN###D40610 | TT_Task | Balise - Mechanical (CEN-PIT Down Track) | 11/05/2022 | 12/05/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 539 | 1112893334_539
C730C157CJ###D40400 | TT_Task | Balise - Mechanical (VIC-CST Up Track) | 11/05/2022 | 16/05/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 539 | 1112893334_539
C730C157CJ###D40540 | TT_Task | Balise - Mechanical (VIC-CST Down Track) | 11/05/2022 | 16/05/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 539 | 1112893334_539
C730C157CI###D40360 | TT_Task | Balise - Mechanical (CST-ND Up Track) | 29/09/2021 | 11/10/2021 | 27/09/2021 | 06/10/2021 | 0 | TK_Complete | 1112893334 | 539 | 1112893334_539
C730C157CI###D40550 | TT_Task | Balise - Mechanical (CST-ND Down Track) | 12/10/2021 | 21/10/2021 | 21/10/2021 | 26/10/2021 | 0 | TK_Complete | 1112893334 | 539 | 1112893334_539
C730C157CO###D40900 | TT_Task | Field Cable - Installation - DCS power (CEN-PIT Up Track StationBox area) | 12/04/2022 | 12/04/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 538 | 1112893334_538
C730C157CO###D40910 | TT_Task | Field Cable - Installation - DCS Fibre (CEN-PIT Up Track StationBox area) | 12/04/2022 | 12/04/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 538 | 1112893334_538
C730C157CO###D41000 | TT_Task | Field Cable - Installation - Fibre Backbone (CEN-PIT Up Track StationBox area) | 13/04/2022 | 13/04/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 538 | 1112893334_538
C730C157CO###D41040 | TT_Task | Field Fibre Cable - Splicing - DCS (CEN-PIT Up Track StationBox area) | 19/04/2022 | 20/04/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 538 | 1112893334_538
C730C157CO###D41150 | TT_Task | Field Cable - Installation - Fibre Backbone (CEN-PIT DN Track StationBox area) | 20/05/2022 | 20/05/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 538 | 1112893334_538
C730C157CN###D40330 | TT_Task | Field Cable - Installation - DCS Fibre (CEN-PIT Up Track) | 14/04/2022 | 14/04/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 538 | 1112893334_538
C730C157CN###D40340 | TT_Task | Field Cable - Installation - Fibre Backbone (CEN-PIT Up Track) | 19/04/2022 | 19/04/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 538 | 1112893334_538
C730C157CN###D40500 | TT_Task | Field Cable - Installation - DCS Fibre (CEN-PIT Down Track) | 01/06/2022 | 01/06/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 538 | 1112893334_538
C730C157CN###D40510 | TT_Task | Field Cable - Installation - Fibre Backbone (CEN-PIT Down Track) | 02/06/2022 | 03/06/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 538 | 1112893334_538
C730C157CO###D40880 | TT_Task | Field Cable - Installation - AxCo (CEN-PIT Up Track StationBox area) | 11/04/2022 | 11/04/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 537 | 1112893334_537
C730C157CO###D41130 | TT_Task | Field Cable - Installation - AxCo (CEN-PIT DN Track StationBox area) | 19/05/2022 | 19/05/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 537 | 1112893334_537
C730C157CN###D40360 | TT_Task | Field Cable - Installation - AxCo (CEN-PIT Up Track) | 13/04/2022 | 13/04/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 537 | 1112893334_537
C730C157CN###D40530 | TT_Task | Field Cable - Installation - AxCo (CEN-PIT Down Track) | 31/05/2022 | 31/05/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 537 | 1112893334_537
C730C157CO###D40950 | TT_Task | DCS TRE Box - Mechanical (CEN-PIT Up Track StationBox area) | 01/04/2022 | 01/04/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 536 | 1112893334_536
C730C157CO###D40960 | TT_Task | DCS Antenna - Mechanical (CEN-PIT Up Track StationBox area) | 04/04/2022 | 05/04/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 536 | 1112893334_536
C730C157CN###D40430 | TT_Task | DCS TRE Box - Mechanical (CEN-PIT Up Track) | 07/04/2022 | 07/04/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 536 | 1112893334_536
C730C157CN###D40570 | TT_Task | DCS TRE Box - Mechanical (CEN-PIT Down Track) | 17/05/2022 | 23/05/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 536 | 1112893334_536
C730C157CO###D40870 | TT_Task | Axle Counter - Mechanical (CEN-PIT Up Track StationBox area) | 31/03/2022 | 31/03/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 535 | 1112893334_535
C730C157CO###D40980 | TT_Task | Marker Board - Mechanical (CEN-PIT Up Track StationBox area) | 06/04/2022 | 07/04/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 535 | 1112893334_535
C730C157CO###D41100 | TT_Task | Axle Counter - Mechanical (CEN-PIT DN Track StationBox area) | 13/05/2022 | 13/05/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 535 | 1112893334_535
C730C157CO###D41120 | TT_Task | Marker Board - Mechanical (CEN-PIT DN Track StationBox area) | 17/05/2022 | 18/05/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 535 | 1112893334_535
C730C157CO###D40750 | TT_Task | Backbone Inline splice (WLO-CEN Up Track) | 26/05/2022 | 26/05/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 534 | 1112893334_534
C730C157CO###D40760 | TT_Task | Backbone Inline splice (WLO-CEN Down Track) | 27/06/2022 | 27/06/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 534 | 1112893334_534
C730C157CN###D40730 | TT_Task | Backbone Inline splice (CEN-PIT Up Track) | 29/04/2022 | 29/04/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 534 | 1112893334_534
C730C157CN###D40740 | TT_Task | Backbone Inline splice (CEN-PIT Down Track) | 16/06/2022 | 16/06/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 534 | 1112893334_534
C730C157CM###D40750 | TT_Task | Backbone Inline splice (PIT-MPL Up Track) | 29/04/2022 | 02/05/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 534 | 1112893334_534
C730C157CM###D40760 | TT_Task | Backbone Inline splice (PIT-MPL Down Track) | 25/05/2022 | 26/05/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 534 | 1112893334_534
C730C157CL###D40670 | TT_Task | Backbone Inline splice (MPL-BZZ Up Track) | 04/04/2022 | 04/04/2022 | nan | nan | 100 | TK_NotStart | 1112893334 | 534 | 1112893334_534
C730C157CL###D40680 | TT_Task | Backbone Inline splice (MPL-BZZ Up Track) | 13/04/2022 | 14/04/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 534 | 1112893334_534
C730C157CO###D40480 | TT_Task | TRE box FO Splice (WLO-CEN Up Track) | 23/05/2022 | 25/05/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 533 | 1112893334_533
C730C157CO###D40660 | TT_Task | TRE box FO Splice (WLO-CEN Down Track) | 21/06/2022 | 23/06/2022 | nan | nan | 20 | TK_NotStart | 1112893334 | 533 | 1112893334_533
C730C157CN###D40450 | TT_Task | TRE box FO Splice (CEN-PIT Up Track) | 27/04/2022 | 28/04/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 533 | 1112893334_533
C730C157CN###D40620 | TT_Task | TRE box FO Splice (CEN-PIT Down Track) | 10/06/2022 | 15/06/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 533 | 1112893334_533
C730C157CM###D40510 | TT_Task | TRE box FO Splice (PIT-MPL Up Track) | 26/04/2022 | 28/04/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 533 | 1112893334_533
C730C157CM###D40650 | TT_Task | TRE box FO Splice (PIT-MPL Down Track) | 20/05/2022 | 24/05/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 533 | 1112893334_533
C730C157CL###D40340 | TT_Task | TRE box FO Splice (MPL-BZZ Up Track) | 16/03/2022 | 25/03/2022 | 09/03/2022 | 15/03/2022 | 0 | TK_Complete | 1112893334 | 533 | 1112893334_533
C730C157CL###D40550 | TT_Task | TRE box FO Splice (MPL-BZZ Down Track) | 01/04/2022 | 12/04/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 533 | 1112893334_533
C730C157CJ###D40410 | TT_Task | TRE box FO Splice (VIC-CST Up Track) | 21/06/2022 | 30/06/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 533 | 1112893334_533
C730C157CJ###D40550 | TT_Task | TRE box FO Splice (VIC-CST Down Track) | 15/06/2022 | 21/06/2022 | nan | nan | 40 | TK_NotStart | 1112893334 | 533 | 1112893334_533
C730C157CI###D40370 | TT_Task | TRE box FO Splice (CST-ND Up Track) | 01/03/2022 | 17/03/2022 | 23/02/2022 | 11/03/2022 | 0 | TK_Complete | 1112893334 | 533 | 1112893334_533
C730C157CI###D40560 | TT_Task | TRE box FO Splice (CST-ND Down Track) | 29/03/2022 | 14/04/2022 | 14/02/2022 | 21/02/2022 | 0 | TK_Complete | 1112893334 | 533 | 1112893334_533
C730C157CP###TP2310 | TT_Task | TRE box FO Splice (CHW-ND Up Track) | 22/04/2022 | 22/04/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 533 | 1112893334_533
C730C157CP###TP2550 | TT_Task | TRE box FO Splice (CHW-ND U Down Track) | 25/05/2022 | 25/05/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 533 | 1112893334_533
C730C157CO###D40770 | TT_Task | Field Cable - Tying in (WLO-CEN Up Track) | 17/05/2022 | 20/05/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 532 | 1112893334_532
C730C157CO###D40780 | TT_Task | Field Cable - Tying in (WLO-CEN Down Track) | 15/06/2022 | 20/06/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 532 | 1112893334_532
C730C157CN###D40990 | TT_Task | Field Cable - Tying in (CEN-PIT Up Track) | 20/04/2022 | 26/04/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 532 | 1112893334_532
C730C157CN###D41000 | TT_Task | Field Cable - Tying in (CEN-PIT Up Track) | 06/06/2022 | 09/06/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 532 | 1112893334_532
C730C157CJ###D41340 | TT_Task | Field Cable - Tying in (VIC-CST Up Track) | 14/06/2022 | 20/06/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 532 | 1112893334_532
C730C157CJ###D41350 | TT_Task | Field Cable - Tying in (VIC-CST Up Track) | 15/06/2022 | 20/06/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 532 | 1112893334_532
C730C157CI###D40640 | TT_Task | Field Cable - Tying in (CST-ND Up Track) | 22/11/2021 | 01/12/2021 | 16/11/2021 | 03/12/2021 | 0 | TK_Complete | 1112893334 | 532 | 1112893334_532
C730C157CI###D40670 | TT_Task | Field Cable - Tying in (CST-ND Down Track) | 30/11/2021 | 09/12/2021 | 08/12/2021 | 21/01/2022 | 0 | TK_Complete | 1112893334 | 532 | 1112893334_532
C730C157CP###TP2270 | TT_Task | Field Cable - Tying in (CHW-ND Up Track) | 14/04/2022 | 14/04/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 532 | 1112893334_532
C730C157CP###TP2510 | TT_Task | Field Cable - Tying in (CHW-ND Down Track) | 19/05/2022 | 19/05/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 532 | 1112893334_532
C730C157CO###D40380 | TT_Task | TRE power (WLO-CEN Up Track) | 13/05/2022 | 16/05/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 531 | 1112893334_531
C730C157CO###D40550 | TT_Task | TRE power (WLO-CEN Down Track) | 10/06/2022 | 14/06/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 531 | 1112893334_531
C730C157CN###D40370 | TT_Task | TRE power (CEN-PIT Up Track) | 14/04/2022 | 19/04/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 531 | 1112893334_531
C730C157CN###D40540 | TT_Task | TRE power (CEN-PIT Down Track) | 01/06/2022 | 01/06/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 531 | 1112893334_531
C730C157CO###D40700 | TT_Task | Marker Boards (WLO-CEN Up Track) | 03/05/2022 | 03/05/2022 | nan | nan | 40 | TK_NotStart | 1112893334 | 530 | 1112893334_530
C730C157CO###D40740 | TT_Task | Marker Boards (WLO-CEN Down Track) | 06/06/2022 | 07/06/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 530 | 1112893334_530
C730C157CN###D40690 | TT_Task | Marker Boards (CEN-PIT Up Track) | 11/04/2022 | 11/04/2022 | nan | nan | 10 | TK_NotStart | 1112893334 | 530 | 1112893334_530
C730C157CN###D40720 | TT_Task | Marker Boards (CEN-PIT Down Track) | 30/05/2022 | 30/05/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 530 | 1112893334_530
C730C157CJ###D41040 | TT_Task | Marker Boards (VIC-CST Up Track) | 06/06/2022 | 07/06/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 530 | 1112893334_530
C730C157CJ###D41060 | TT_Task | Marker Boards (VIC-CST Down Track) | 06/06/2022 | 07/06/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 530 | 1112893334_530
C730C157CI###D40630 | TT_Task | Marker Boards (CST-ND Up Track) | 11/11/2021 | 12/11/2021 | 17/11/2021 | 17/11/2021 | 0 | TK_Complete | 1112893334 | 530 | 1112893334_530
C730C157CI###D40660 | TT_Task | Marker Boards (CST-ND Down Track) | 29/10/2021 | 01/11/2021 | 17/11/2021 | 17/11/2021 | 0 | TK_Complete | 1112893334 | 530 | 1112893334_530
C730C157CP###TP2200 | TT_Task | Marker Boards (CHW-ND Up Track) | 06/04/2022 | 06/04/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 530 | 1112893334_530
C730C157CP###TP2440 | TT_Task | Marker Boards (CHW-ND Down Track) | 11/05/2022 | 11/05/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 530 | 1112893334_530
C720P147CF###0030790 | TT_Task | BA Ceiling and lighting | 25/02/2020 | 19/03/2020 | 05/12/2019 | 24/04/2020 | 0 | TK_Complete | 1112893334 | 53 | 1112893334_53
C720P147CF###0031020 | TT_Task | PO Ceiling and lighting | 25/05/2020 | 29/06/2020 | 27/04/2020 | 22/05/2020 | 0 | TK_Complete | 1112893334 | 53 | 1112893334_53
C720P147CF###0031300 | TT_Task | Production Ceiling and lighting | 25/06/2020 | 08/02/2021 | 29/05/2020 | 14/10/2020 | 0 | TK_Complete | 1112893334 | 53 | 1112893334_53
C720P147CF###0031720 | TT_Task | DEL Ceiling and lighting | 11/11/2020 | 01/12/2020 | 15/10/2020 | 06/12/2020 | 0 | TK_Complete | 1112893334 | 53 | 1112893334_53
C730C157CO###D40690 | TT_Task | BTN Splice Box (WLO-CEN Up Track) | 02/05/2022 | 02/05/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 529 | 1112893334_529
C730C157CO###D40730 | TT_Task | BTN Splice Box (WLO-CEN Down Track) | 06/06/2022 | 06/06/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 529 | 1112893334_529
C730C157CN###D40680 | TT_Task | BTN Splice Box (CEN-PIT Up Track) | 12/04/2022 | 12/04/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 529 | 1112893334_529
C730C157CN###D40710 | TT_Task | BTN Splice Box (CEN-PIT Down Track) | 30/05/2022 | 30/05/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 529 | 1112893334_529
C730C157CM###D40700 | TT_Task | BTN Splice Box (PIT-MPL Up Track) | 11/04/2022 | 11/04/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 529 | 1112893334_529
C730C157CM###D40730 | TT_Task | BTN Splice Box (PIT-MPL Down Track) | 08/04/2022 | 08/04/2022 | nan | nan | 180 | TK_NotStart | 1112893334 | 529 | 1112893334_529
C730C157CL###D40650 | TT_Task | BTN Splice Box (MPL-BZZ Up Track) | 04/03/2022 | 04/03/2022 | 02/03/2022 | 02/03/2022 | 0 | TK_Complete | 1112893334 | 529 | 1112893334_529
C730C157CL###D40620 | TT_Task | BTN Splice Box (MPL-BZZ Down Track) | 09/03/2022 | 09/03/2022 | 02/03/2022 | 02/03/2022 | 0 | TK_Complete | 1112893334 | 529 | 1112893334_529
C730C157CJ###D41030 | TT_Task | BTN Splice Box (VIC-CST Up Track) | 06/06/2022 | 06/06/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 529 | 1112893334_529
C730C157CO###D40440 | TT_Task | Axle Counters (WLO-CEN Up Track) | 12/04/2022 | 14/04/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 528 | 1112893334_528
C730C157CO###D40590 | TT_Task | Axle Counters (WLO-CEN Down Track) | 18/05/2022 | 20/05/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 528 | 1112893334_528
C730C157CN###D40410 | TT_Task | Axle Counters (CEN-PIT Up Track) | 05/04/2022 | 06/04/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 528 | 1112893334_528
C730C157CN###D40590 | TT_Task | Axle Counters (CEN-PIT Down Track) | 13/05/2022 | 16/05/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 528 | 1112893334_528
C730C157CJ###D40390 | TT_Task | Axle Counters (VIC-CST Up Track) | 17/05/2022 | 17/05/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 528 | 1112893334_528
C730C157CJ###D40530 | TT_Task | Axle Counters (VIC-CST Down Track) | 17/05/2022 | 17/05/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 528 | 1112893334_528
C730C157CI###D40320 | TT_Task | Axle Counters (CST-ND Up Track) | 25/11/2021 | 26/11/2021 | 30/11/2021 | 01/12/2021 | 0 | TK_Complete | 1112893334 | 528 | 1112893334_528
C730C157CI###D40510 | TT_Task | Axle Counters (CST-ND Down Track) | 30/11/2021 | 01/12/2021 | 26/11/2021 | 26/11/2021 | 0 | TK_Complete | 1112893334 | 528 | 1112893334_528
C730C157CP###TP2140 | TT_Task | Axle Counters (CHW-ND Up Track) | 04/04/2022 | 04/04/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 528 | 1112893334_528
C730C157CP###TP2380 | TT_Task | Axle Counters (CHW-ND Down Track) | 06/05/2022 | 06/05/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 528 | 1112893334_528
C730C157CO###D40420 | TT_Task | Antennas and Cabling (WLO-CEN Up Track) | 27/04/2022 | 29/04/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 527 | 1112893334_527
C730C157CO###D40600 | TT_Task | Antennas and Cabling (WLO-CEN Down Track) | 30/05/2022 | 03/06/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 527 | 1112893334_527
C730C157CN###D40420 | TT_Task | Antennas and Cabling (CEN-PIT Up Track) | 08/04/2022 | 08/04/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 527 | 1112893334_527
C730C157CN###D40600 | TT_Task | Antennas and Cabling (CEN-PIT Down Track) | 24/05/2022 | 27/05/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 527 | 1112893334_527
C730C157CO###D40400 | TT_Task | Material Distribution (WLO-CEN Up Track) | 30/03/2022 | 01/04/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 526 | 1112893334_526
C730C157CO###D40570 | TT_Task | Material Distribution (WLO-CEN Down Track) | 11/05/2022 | 13/05/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 526 | 1112893334_526
C730C157CN###D40390 | TT_Task | Material Distribution (CEN-PIT Up Track) | 28/03/2022 | 29/03/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 526 | 1112893334_526
C730C157CN###D40560 | TT_Task | Material Distribution (CEN-PIT Down Track) | 09/05/2022 | 11/05/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 526 | 1112893334_526
C730C157CO###D40390 | TT_Task | Equipment set out (WLO-CEN Up Track) | 25/03/2022 | 29/03/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 525 | 1112893334_525
C730C157CO###D40560 | TT_Task | Equipment set out (WLO-CEN Down Track) | 06/05/2022 | 10/05/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 525 | 1112893334_525
C730C157CN###D40380 | TT_Task | Equipment set out (CEN-PIT Up Track) | 25/03/2022 | 25/03/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 525 | 1112893334_525
C730C157CN###D40550 | TT_Task | Equipment set out (CEN-PIT Down Track) | 06/05/2022 | 06/05/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 525 | 1112893334_525
C730C157CP###D040750 | TT_Task | Completions, defect rectifacation, final sweep (SD-WLO Up Track StationBox area) | 10/06/2022 | 10/06/2022 | nan | nan | 20 | TK_NotStart | 1112893334 | 524 | 1112893334_524
C730C157CP###D040870 | TT_Task | Completions, defect rectifacation, final sweep (SD-WLO DN Track StationBox area) | 19/05/2022 | 19/05/2022 | nan | nan | 180 | TK_NotStart | 1112893334 | 524 | 1112893334_524
C730C157CO###D40940 | TT_Task | Completions, defect rectifacation, final sweep (CEN-PIT Up Track StationBox area) | 26/04/2022 | 26/04/2022 | nan | nan | 400 | TK_NotStart | 1112893334 | 524 | 1112893334_524
C730C157CO###D41200 | TT_Task | Completions, defect rectifacation, final sweep (CEN-PIT DN Track StationBox area) | 26/05/2022 | 26/05/2022 | nan | nan | 180 | TK_NotStart | 1112893334 | 524 | 1112893334_524
C730C157CN###D40810 | TT_Task | Completions, defect rectifacation, final sweep (PIT-MPL Up Track StationBox area) | 24/05/2022 | 24/05/2022 | nan | nan | 70 | TK_NotStart | 1112893334 | 524 | 1112893334_524
C730C157CN###D40980 | TT_Task | Completions, defect rectifacation, final sweep (PIT-MPL DN Track StationBox area) | 19/05/2022 | 19/05/2022 | nan | nan | 100 | TK_NotStart | 1112893334 | 524 | 1112893334_524
C730C157CM###D40830 | TT_Task | Completions, defect rectifacation, final sweep (MPL-BZZ Up Track StationBox area) | 01/06/2022 | 01/06/2022 | nan | nan | 10 | TK_NotStart | 1112893334 | 524 | 1112893334_524
C730C157CM###D41000 | TT_Task | Completions, defect rectifacation, final sweep (MPL-BZZ DN Track StationBox area) | 04/05/2022 | 04/05/2022 | nan | nan | 210 | TK_NotStart | 1112893334 | 524 | 1112893334_524
C730C157CL###D40750 | TT_Task | Completions, defect rectifacation, final sweep (BZZ-VIC Up Track StationBox area) | 14/09/2022 | 14/09/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 524 | 1112893334_524
C730C157CL###D40920 | TT_Task | Completions, defect rectifacation, final sweep (BZZ-VIC DN Track StationBox area) | 13/09/2022 | 13/09/2022 | nan | nan | 10 | TK_NotStart | 1112893334 | 524 | 1112893334_524
C730C157CK###D41940 | TT_Task | Completions, defect rectifacation, final sweep (VIC-CST Up Track StationBox area) | 07/04/2022 | 07/04/2022 | nan | nan | 610 | TK_NotStart | 1112893334 | 524 | 1112893334_524
C730C157CK###D42110 | TT_Task | Completions, defect rectifacation, final sweep (VIC-CST DN Track StationBox area) | 11/04/2022 | 11/04/2022 | nan | nan | 590 | TK_NotStart | 1112893334 | 524 | 1112893334_524
C730C157CJ###D41160 | TT_Task | Completions, defect rectifacation, final sweep (CST-ND Up Track StationBox area) | 24/05/2022 | 24/05/2022 | nan | nan | 70 | TK_NotStart | 1112893334 | 524 | 1112893334_524
C730C157CJ###D41330 | TT_Task | Completions, defect rectifacation, final sweep (CST-ND DN Track StationBox area) | 08/04/2022 | 08/04/2022 | nan | nan | 360 | TK_NotStart | 1112893334 | 524 | 1112893334_524
C730C157CP###D040740 | TT_Task | Field Fibre Cable - Splicing - BTN (SD-WLO Up Track StationBox area) | 06/06/2022 | 09/06/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 523 | 1112893334_523
C730C157CP###D040860 | TT_Task | Field Fibre Cable - Splicing - BTN (SD-WLO DN Track StationBox area) | 18/05/2022 | 18/05/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 523 | 1112893334_523
C730C157CO###D41050 | TT_Task | Field Fibre Cable - Splicing - BTN (CEN-PIT Up Track StationBox area) | 21/04/2022 | 22/04/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 523 | 1112893334_523
C730C157CO###D41190 | TT_Task | Field Fibre Cable - Splicing - BTN (CEN-PIT DN Track StationBox area) | 24/05/2022 | 25/05/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 523 | 1112893334_523
C730C157CN###D40860 | TT_Task | Field Fibre Cable - Splicing - BTN (PIT-MPL Up Track StationBox area) | 18/05/2022 | 23/05/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 523 | 1112893334_523
C730C157CN###D40970 | TT_Task | Field Fibre Cable - Splicing - BTN (PIT-MPL DN Track StationBox area) | 18/05/2022 | 18/05/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 523 | 1112893334_523
C730C157CM###D40880 | TT_Task | Field Fibre Cable - Splicing - BTN (MPL-BZZ Up Track StationBox area) | 26/05/2022 | 31/05/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 523 | 1112893334_523
C730C157CM###D40990 | TT_Task | Field Fibre Cable - Splicing - BTN (MPL-BZZ DN Track StationBox area) | 03/05/2022 | 03/05/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 523 | 1112893334_523
C730C157CL###D40800 | TT_Task | Field Fibre Cable - Splicing - BTN (BZZ-VIC Up Track StationBox area) | 08/09/2022 | 13/09/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 523 | 1112893334_523
C730C157CL###D40910 | TT_Task | Field Fibre Cable - Splicing - BTN (BZZ-VIC DN Track StationBox area) | 12/09/2022 | 12/09/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 523 | 1112893334_523
C730C157CK###D41990 | TT_Task | Field Fibre Cable - Splicing - BTN (VIC-CST Up Track StationBox area) | 06/04/2022 | 06/04/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 523 | 1112893334_523
C730C157CK###D42100 | TT_Task | Field Fibre Cable - Splicing - BTN (VIC-CST DN Track StationBox area) | 07/04/2022 | 08/04/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 523 | 1112893334_523
C730C157CJ###D41210 | TT_Task | Field Fibre Cable - Splicing - BTN (CST-ND Up Track StationBox area) | 18/05/2022 | 23/05/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 523 | 1112893334_523
C730C157CJ###D41320 | TT_Task | Field Fibre Cable - Splicing - BTN (CST-ND DN Track StationBox area) | 06/04/2022 | 07/04/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 523 | 1112893334_523
C730C157CP###D040730 | TT_Task | Field Copper Cable - Termination - SAB (SD-WLO Up Track StationBox area) | 06/06/2022 | 06/06/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 522 | 1112893334_522
C730C157CP###D040850 | TT_Task | Field Copper Cable - Termination - SAB (SD-WLO DN Track StationBox area) | 18/05/2022 | 18/05/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 522 | 1112893334_522
C730C157CO###D40930 | TT_Task | Field Copper Cable - Termination - SAB (CEN-PIT Up Track StationBox area) | 19/04/2022 | 19/04/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 522 | 1112893334_522
C730C157CO###D41180 | TT_Task | Field Copper Cable - Termination - SAB (CEN-PIT DN Track StationBox area) | 24/05/2022 | 24/05/2022 | nan | nan | 10 | TK_NotStart | 1112893334 | 522 | 1112893334_522
C730C157CN###D40800 | TT_Task | Field Copper Cable - Termination - SAB (PIT-MPL Up Track StationBox area) | 18/05/2022 | 18/05/2022 | nan | nan | 30 | TK_NotStart | 1112893334 | 522 | 1112893334_522
C730C157CN###D40960 | TT_Task | Field Copper Cable - Termination - SAB (PIT-MPL DN Track StationBox area) | 18/05/2022 | 18/05/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 522 | 1112893334_522
C730C157CM###D40820 | TT_Task | Field Copper Cable - Termination - SAB (MPL-BZZ Up Track StationBox area) | 26/05/2022 | 26/05/2022 | nan | nan | 30 | TK_NotStart | 1112893334 | 522 | 1112893334_522
C730C157CM###D40980 | TT_Task | Field Copper Cable - Termination - SAB (MPL-BZZ DN Track StationBox area) | 03/05/2022 | 03/05/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 522 | 1112893334_522
C730C157CL###D40740 | TT_Task | Field Copper Cable - Termination - SAB (BZZ-VIC Up Track StationBox area) | 08/09/2022 | 08/09/2022 | nan | nan | 30 | TK_NotStart | 1112893334 | 522 | 1112893334_522
C730C157CL###D40900 | TT_Task | Field Copper Cable - Termination - SAB (BZZ-VIC DN Track StationBox area) | 12/09/2022 | 12/09/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 522 | 1112893334_522
C730C157CK###D41930 | TT_Task | Field Copper Cable - Termination - SAB (VIC-CST Up Track StationBox area) | 06/04/2022 | 06/04/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 522 | 1112893334_522
C730C157CK###D42090 | TT_Task | Field Copper Cable - Termination - SAB (VIC-CST DN Track StationBox area) | 07/04/2022 | 07/04/2022 | nan | nan | 10 | TK_NotStart | 1112893334 | 522 | 1112893334_522
C730C157CJ###D41150 | TT_Task | Field Copper Cable - Termination - SAB (CST-ND Up Track StationBox area) | 18/05/2022 | 18/05/2022 | nan | nan | 30 | TK_NotStart | 1112893334 | 522 | 1112893334_522
C730C157CJ###D41310 | TT_Task | Field Copper Cable - Termination - SAB (CST-ND DN Track StationBox area) | 06/04/2022 | 06/04/2022 | nan | nan | 10 | TK_NotStart | 1112893334 | 522 | 1112893334_522
C730C157CP###D040720 | TT_Task | Field Cable - Tying in (SD-WLO Up Track StationBox area) | 03/06/2022 | 03/06/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 521 | 1112893334_521
C730C157CP###D040840 | TT_Task | Field Cable - Tying in (SD-WLO DN Track StationBox area) | 17/05/2022 | 17/05/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 521 | 1112893334_521
C730C157CO###D41020 | TT_Task | Field Cable - Tying in (CEN-PIT Up Track StationBox area) | 14/04/2022 | 14/04/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 521 | 1112893334_521
C730C157CO###D41170 | TT_Task | Field Cable - Tying in (CEN-PIT DN Track StationBox area) | 23/05/2022 | 23/05/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 521 | 1112893334_521
C730C157CN###D40850 | TT_Task | Field Cable - Tying in (PIT-MPL Up Track StationBox area) | 17/05/2022 | 17/05/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 521 | 1112893334_521
C730C157CN###D40950 | TT_Task | Field Cable - Tying in (PIT-MPL DN Track StationBox area) | 17/05/2022 | 17/05/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 521 | 1112893334_521
C730C157CM###D40870 | TT_Task | Field Cable - Tying in (MPL-BZZ Up Track StationBox area) | 25/05/2022 | 25/05/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 521 | 1112893334_521
C730C157CM###D40970 | TT_Task | Field Cable - Tying in (MPL-BZZ DN Track StationBox area) | 02/05/2022 | 02/05/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 521 | 1112893334_521
C730C157CL###D40790 | TT_Task | Field Cable - Tying in (BZZ-VIC Up Track StationBox area) | 07/09/2022 | 07/09/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 521 | 1112893334_521
C730C157CL###D40890 | TT_Task | Field Cable - Tying in (BZZ-VIC DN Track StationBox area) | 09/09/2022 | 09/09/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 521 | 1112893334_521
C730C157CK###D41980 | TT_Task | Field Cable - Tying in (VIC-CST Up Track StationBox area) | 05/04/2022 | 05/04/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 521 | 1112893334_521
C730C157CK###D42080 | TT_Task | Field Cable - Tying in (VIC-CST DN Track StationBox area) | 06/04/2022 | 06/04/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 521 | 1112893334_521
C730C157CJ###D41200 | TT_Task | Field Cable - Tying in (CST-ND Up Track StationBox area) | 17/05/2022 | 17/05/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 521 | 1112893334_521
C730C157CJ###D41300 | TT_Task | Field Cable - Tying in (CST-ND DN Track StationBox area) | 05/04/2022 | 05/04/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 521 | 1112893334_521
C730C157CP###D040710 | TT_Task | Field - Cable pulling into platform area (SD-WLO Up Track StationBox area) | 02/06/2022 | 02/06/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 520 | 1112893334_520
C730C157CP###D040830 | TT_Task | Field - Cable pulling into platform area (SD-WLO DN Track StationBox area) | 16/05/2022 | 16/05/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 520 | 1112893334_520
C730C157CO###D41010 | TT_Task | Field - Cable pulling into platform area (CEN-PIT Up Track StationBox area) | 13/04/2022 | 13/04/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 520 | 1112893334_520
C730C157CO###D41160 | TT_Task | Field - Cable pulling into platform area (CEN-PIT DN Track StationBox area) | 20/05/2022 | 20/05/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 520 | 1112893334_520
C730C157CN###D40840 | TT_Task | Field - Cable pulling into platform area (PIT-MPL Up Track StationBox area) | 16/05/2022 | 16/05/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 520 | 1112893334_520
C730C157CN###D40940 | TT_Task | Field - Cable pulling into platform area (PIT-MPL DN Track StationBox area) | 16/05/2022 | 16/05/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 520 | 1112893334_520
C730C157CM###D40860 | TT_Task | Field - Cable pulling into platform area (MPL-BZZ Up Track StationBox area) | 24/05/2022 | 24/05/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 520 | 1112893334_520
C730C157CM###D40960 | TT_Task | Field - Cable pulling into platform area (MPL-BZZ DN Track StationBox area) | 29/04/2022 | 29/04/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 520 | 1112893334_520
C730C157CL###D40780 | TT_Task | Field - Cable pulling into platform area (BZZ-VIC Up Track StationBox area) | 06/09/2022 | 06/09/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 520 | 1112893334_520
C730C157CL###D40880 | TT_Task | Field - Cable pulling into platform area (BZZ-VIC DN Track StationBox area) | 07/09/2022 | 08/09/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 520 | 1112893334_520
C730C157CK###D41970 | TT_Task | Field - Cable pulling into platform area (VIC-CST Up Track StationBox area) | 04/04/2022 | 04/04/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 520 | 1112893334_520
C730C157CK###D42070 | TT_Task | Field - Cable pulling into platform area (VIC-CST DN Track StationBox area) | 05/04/2022 | 05/04/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 520 | 1112893334_520
C730C157CJ###D41190 | TT_Task | Field - Cable pulling into platform area (CST-ND Up Track StationBox area) | 16/05/2022 | 16/05/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 520 | 1112893334_520
C730C157CJ###D41290 | TT_Task | Field - Cable pulling into platform area (CST-ND DN Track StationBox area) | 04/04/2022 | 04/04/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 520 | 1112893334_520
C720P147CF###0030780 | TT_Task | BA Wind screen | 25/02/2020 | 19/03/2020 | 05/12/2019 | 09/03/2020 | 0 | TK_Complete | 1112893334 | 52 | 1112893334_52
C720P147CF###0031390 | TT_Task | PO Wind screen | 25/03/2020 | 30/03/2020 | 10/03/2020 | 17/03/2020 | 0 | TK_Complete | 1112893334 | 52 | 1112893334_52
C720P147CF###0031530 | TT_Task | Production Wind screen | 25/03/2020 | 19/10/2020 | 18/03/2020 | 11/09/2020 | 0 | TK_Complete | 1112893334 | 52 | 1112893334_52
C720P147CF###0031830 | TT_Task | DEL Wind screen | 13/11/2020 | 01/02/2021 | 12/09/2020 | 03/11/2020 | 0 | TK_Complete | 1112893334 | 52 | 1112893334_52
C730C157CP###D040700 | TT_Task | Fibre Backbone (SD-WLO Up Track StationBox area) | 01/06/2022 | 01/06/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 519 | 1112893334_519
C730C157CP###D040820 | TT_Task | Fibre Backbone (SD-WLO DN Track StationBox area) | 13/05/2022 | 13/05/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 519 | 1112893334_519
C730C157CP###D040690 | TT_Task | Field Cable - Installation - SAB Cables (SD-WLO Up Track StationBox area) | 01/06/2022 | 01/06/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 518 | 1112893334_518
C730C157CP###D040810 | TT_Task | Field Cable - Installation - SAB Cables (SD-WLO DN Track StationBox area) | 13/05/2022 | 13/05/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 518 | 1112893334_518
C730C157CO###D40890 | TT_Task | Field Cable - Installation - SAB Cables (CEN-PIT Up Track StationBox area) | 11/04/2022 | 11/04/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 518 | 1112893334_518
C730C157CO###D41140 | TT_Task | Field Cable - Installation - SAB Cables (CEN-PIT DN Track StationBox area) | 19/05/2022 | 19/05/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 518 | 1112893334_518
C730C157CN###D40790 | TT_Task | Field Cable - Installation - SAB Cables (PIT-MPL Up Track StationBox area) | 13/05/2022 | 13/05/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 518 | 1112893334_518
C730C157CN###D40920 | TT_Task | Field Cable - Installation - SAB Cables (PIT-MPL DN Track StationBox area) | 13/05/2022 | 13/05/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 518 | 1112893334_518
C730C157CM###D40810 | TT_Task | Field Cable - Installation - SAB Cables (MPL-BZZ Up Track StationBox area) | 23/05/2022 | 23/05/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 518 | 1112893334_518
C730C157CM###D40940 | TT_Task | Field Cable - Installation - SAB Cables (MPL-BZZ DN Track StationBox area) | 28/04/2022 | 28/04/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 518 | 1112893334_518
C730C157CL###D40730 | TT_Task | Field Cable - Installation - SAB Cables (BZZ-VIC Up Track StationBox area) | 05/09/2022 | 05/09/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 518 | 1112893334_518
C730C157CL###D40860 | TT_Task | Field Cable - Installation - SAB Cables (BZZ-VIC DN Track StationBox area) | 06/09/2022 | 06/09/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 518 | 1112893334_518
C730C157CK###D41920 | TT_Task | Field Cable - Installation - SAB Cables (VIC-CST Up Track StationBox area) | 01/04/2022 | 01/04/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 518 | 1112893334_518
C730C157CK###D42050 | TT_Task | Field Cable - Installation - SAB Cables (VIC-CST DN Track StationBox area) | 04/04/2022 | 04/04/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 518 | 1112893334_518
C730C157CJ###D41140 | TT_Task | Field Cable - Installation - SAB Cables (CST-ND Up Track StationBox area) | 13/05/2022 | 13/05/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 518 | 1112893334_518
C730C157CJ###D41270 | TT_Task | Field Cable - Installation - SAB Cables (CST-ND DN Track StationBox area) | 01/04/2022 | 01/04/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 518 | 1112893334_518
C730C157CP###D040680 | TT_Task | SPB - Mechanical - Backbone (SD-WLO Up Track StationBox area) | 31/05/2022 | 31/05/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 517 | 1112893334_517
C730C157CP###D040800 | TT_Task | SPB - Mechanical - Backbone (SD-WLO DN Track StationBox area) | 12/05/2022 | 12/05/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 517 | 1112893334_517
C730C157CO###D40990 | TT_Task | SPB - Mechanical - Backbone (CEN-PIT Up Track StationBox area) | 08/04/2022 | 08/04/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 517 | 1112893334_517
C730C157CO###D41110 | TT_Task | SPB - Mechanical - Backbone (CEN-PIT DN Track StationBox area) | 16/05/2022 | 16/05/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 517 | 1112893334_517
C730C157CN###D40820 | TT_Task | SPB - Mechanical - Backbone (PIT-MPL Up Track StationBox area) | 12/05/2022 | 12/05/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 517 | 1112893334_517
C730C157CN###D40910 | TT_Task | SPB - Mechanical - Backbone (PIT-MPL DN Track StationBox area) | 12/05/2022 | 12/05/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 517 | 1112893334_517
C730C157CM###D40840 | TT_Task | SPB - Mechanical - Backbone (MPL-BZZ Up Track StationBox area) | 20/05/2022 | 20/05/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 517 | 1112893334_517
C730C157CM###D40930 | TT_Task | SPB - Mechanical - Backbone (MPL-BZZ DN Track StationBox area) | 27/04/2022 | 27/04/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 517 | 1112893334_517
C730C157CL###D40760 | TT_Task | SPB - Mechanical - Backbone (BZZ-VIC Up Track StationBox area) | 02/09/2022 | 02/09/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 517 | 1112893334_517
C730C157CL###D40850 | TT_Task | SPB - Mechanical - Backbone (BZZ-VIC DN Track StationBox area) | 02/09/2022 | 02/09/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 517 | 1112893334_517
C730C157CK###D41950 | TT_Task | SPB - Mechanical - Backbone (VIC-CST Up Track StationBox area) | 31/03/2022 | 31/03/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 517 | 1112893334_517
C730C157CK###D42040 | TT_Task | SPB - Mechanical - Backbone (VIC-CST DN Track StationBox area) | 01/04/2022 | 01/04/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 517 | 1112893334_517
C730C157CJ###D41170 | TT_Task | SPB - Mechanical - Backbone (CST-ND Up Track StationBox area) | 12/05/2022 | 12/05/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 517 | 1112893334_517
C730C157CJ###D41260 | TT_Task | SPB - Mechanical - Backbone (CST-ND DN Track StationBox area) | 31/03/2022 | 31/03/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 517 | 1112893334_517
C730C157CP###D040670 | TT_Task | SAB Boxes (SD-WLO Up Track StationBox area) | 31/05/2022 | 31/05/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 516 | 1112893334_516
C730C157CP###D040790 | TT_Task | SAB Boxes (SD-WLO DN Track StationBox area) | 12/05/2022 | 12/05/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 516 | 1112893334_516
C730C157CO###D40860 | TT_Task | SAB Boxes (CEN-PIT Up Track StationBox area) | 31/03/2022 | 31/03/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 516 | 1112893334_516
C730C157CO###D41090 | TT_Task | SAB Boxes (CEN-PIT DN Track StationBox area) | 13/05/2022 | 13/05/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 516 | 1112893334_516
C730C157CN###D40780 | TT_Task | SAB Boxes (PIT-MPL Up Track StationBox area) | 12/05/2022 | 12/05/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 516 | 1112893334_516
C730C157CN###D40900 | TT_Task | SAB Boxes (PIT-MPL DN Track StationBox area) | 12/05/2022 | 12/05/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 516 | 1112893334_516
C730C157CM###D40800 | TT_Task | SAB Boxes (MPL-BZZ Up Track StationBox area) | 20/05/2022 | 20/05/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 516 | 1112893334_516
C730C157CM###D40920 | TT_Task | SAB Boxes (MPL-BZZ DN Track StationBox area) | 27/04/2022 | 27/04/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 516 | 1112893334_516
C730C157CL###D40720 | TT_Task | SAB Boxes (BZZ-VIC Up Track StationBox area) | 02/09/2022 | 02/09/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 516 | 1112893334_516
C730C157CL###D40840 | TT_Task | SAB Boxes (BZZ-VIC DN Track StationBox area) | 02/09/2022 | 02/09/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 516 | 1112893334_516
C730C157CK###D41910 | TT_Task | SAB Boxes (VIC-CST Up Track StationBox area) | 31/03/2022 | 31/03/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 516 | 1112893334_516
C730C157CK###D42030 | TT_Task | SAB Boxes (VIC-CST DN Track StationBox area) | 01/04/2022 | 01/04/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 516 | 1112893334_516
C730C157CJ###D41130 | TT_Task | SAB Boxes (CST-ND Up Track StationBox area) | 12/05/2022 | 12/05/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 516 | 1112893334_516
C730C157CJ###D41250 | TT_Task | SAB Boxes (CST-ND DN Track StationBox area) | 31/03/2022 | 31/03/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 516 | 1112893334_516
C730C157CP###D040660 | TT_Task | Balise - Mechanical (SD-WLO Up Track StationBox area) | 26/05/2022 | 30/05/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 515 | 1112893334_515
C730C157CP###D040780 | TT_Task | Balise - Mechanical (SD-WLO DN Track StationBox area) | 09/05/2022 | 11/05/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 515 | 1112893334_515
C730C157CO###D40850 | TT_Task | Balise - Mechanical (CEN-PIT Up Track StationBox area) | 25/03/2022 | 30/03/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 515 | 1112893334_515
C730C157CO###D41080 | TT_Task | Balise - Mechanical (CEN-PIT DN Track StationBox area) | 09/05/2022 | 12/05/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 515 | 1112893334_515
C730C157CN###D40770 | TT_Task | Balise - Mechanical (PIT-MPL Up Track StationBox area) | 09/05/2022 | 11/05/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 515 | 1112893334_515
C730C157CN###D40890 | TT_Task | Balise - Mechanical (PIT-MPL DN Track StationBox area) | 09/05/2022 | 11/05/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 515 | 1112893334_515
C730C157CM###D40790 | TT_Task | Balise - Mechanical (MPL-BZZ Up Track StationBox area) | 17/05/2022 | 19/05/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 515 | 1112893334_515
C730C157CM###D40910 | TT_Task | Balise - Mechanical (MPL-BZZ DN Track StationBox area) | 21/04/2022 | 26/04/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 515 | 1112893334_515
C730C157CL###D40710 | TT_Task | Balise - Mechanical (BZZ-VIC Up Track StationBox area) | 30/08/2022 | 01/09/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 515 | 1112893334_515
C730C157CL###D40830 | TT_Task | Balise - Mechanical (BZZ-VIC DN Track StationBox area) | 30/08/2022 | 01/09/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 515 | 1112893334_515
C730C157CK###D41900 | TT_Task | Balise - Mechanical (VIC-CST Up Track StationBox area) | 28/03/2022 | 30/03/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 515 | 1112893334_515
C730C157CK###D42020 | TT_Task | Balise - Mechanical (VIC-CST DN Track StationBox area) | 29/03/2022 | 31/03/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 515 | 1112893334_515
C730C157CJ###D41120 | TT_Task | Balise - Mechanical (CST-ND Up Track StationBox area) | 09/05/2022 | 11/05/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 515 | 1112893334_515
C730C157CJ###D41240 | TT_Task | Balise - Mechanical (CST-ND DN Track StationBox area) | 28/03/2022 | 30/03/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 515 | 1112893334_515
C730C157CP###D040650 | TT_Task | Material Distribution (SD-WLO Up Track StationBox area) | 25/05/2022 | 25/05/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 514 | 1112893334_514
C730C157CP###D040770 | TT_Task | Material Distribution (SD-WLO DN Track StationBox area) | 06/05/2022 | 06/05/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 514 | 1112893334_514
C730C157CO###D40840 | TT_Task | Material Distribution (CEN-PIT Up Track StationBox area) | 25/03/2022 | 25/03/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 514 | 1112893334_514
C730C157CO###D41070 | TT_Task | Material Distribution (CEN-PIT DN Track StationBox area) | 06/05/2022 | 06/05/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 514 | 1112893334_514
C730C157CN###D40760 | TT_Task | Material Distribution (PIT-MPL Up Track StationBox area) | 06/05/2022 | 06/05/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 514 | 1112893334_514
C730C157CN###D40880 | TT_Task | Material Distribution (PIT-MPL DN Track StationBox area) | 06/05/2022 | 06/05/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 514 | 1112893334_514
C730C157CM###D40780 | TT_Task | Material Distribution (MPL-BZZ Up Track StationBox area) | 16/05/2022 | 16/05/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 514 | 1112893334_514
C730C157CM###D40900 | TT_Task | Material Distribution (MPL-BZZ DN Track StationBox area) | 20/04/2022 | 20/04/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 514 | 1112893334_514
C730C157CL###D40700 | TT_Task | Material Distribution (BZZ-VIC Up Track StationBox area) | 29/08/2022 | 29/08/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 514 | 1112893334_514
C730C157CL###D40820 | TT_Task | Material Distribution (BZZ-VIC DN Track StationBox area) | 29/08/2022 | 29/08/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 514 | 1112893334_514
C730C157CK###D41890 | TT_Task | Material Distribution (VIC-CST Up Track StationBox area) | 25/03/2022 | 25/03/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 514 | 1112893334_514
C730C157CK###D42010 | TT_Task | Material Distribution (VIC-CST DN Track StationBox area) | 28/03/2022 | 28/03/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 514 | 1112893334_514
C730C157CJ###D41110 | TT_Task | Material Distribution (CST-ND Up Track StationBox area) | 06/05/2022 | 06/05/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 514 | 1112893334_514
C730C157CJ###D41230 | TT_Task | Material Distribution (CST-ND DN Track StationBox area) | 25/03/2022 | 25/03/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 514 | 1112893334_514
C730C157CP###D040640 | TT_Task | Equipment set out (SD-WLO Up Track StationBox area) | 25/05/2022 | 25/05/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 513 | 1112893334_513
C730C157CP###D040760 | TT_Task | Equipment set out (SD-WLO DN Track StationBox area) | 06/05/2022 | 06/05/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 513 | 1112893334_513
C730C157CO###0040835 | TT_Task | Equipment set out (CEN-PIT Up Track StationBox area) | 25/03/2022 | 25/03/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 513 | 1112893334_513
C730C157CO###D41060 | TT_Task | Equipment set out (CEN-PIT DN Track StationBox area) | 06/05/2022 | 06/05/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 513 | 1112893334_513
C730C157CN###D40750 | TT_Task | Equipment set out (PIT-MPL Up Track StationBox area) | 06/05/2022 | 06/05/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 513 | 1112893334_513
C730C157CN###D40870 | TT_Task | Equipment set out (PIT-MPL DN Track StationBox area) | 06/05/2022 | 06/05/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 513 | 1112893334_513
C730C157CM###D40770 | TT_Task | Equipment set out (MPL-BZZ Up Track StationBox area) | 16/05/2022 | 16/05/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 513 | 1112893334_513
C730C157CM###D40890 | TT_Task | Equipment set out (MPL-BZZ DN Track StationBox area) | 20/04/2022 | 20/04/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 513 | 1112893334_513
C730C157CL###D40690 | TT_Task | Equipment set out (BZZ-VIC Up Track StationBox area) | 29/08/2022 | 29/08/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 513 | 1112893334_513
C730C157CL###D40810 | TT_Task | Equipment set out (BZZ-VIC DN Track StationBox area) | 29/08/2022 | 29/08/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 513 | 1112893334_513
C730C157CK###D41880 | TT_Task | Equipment set out (VIC-CST Up Track StationBox area) | 25/03/2022 | 25/03/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 513 | 1112893334_513
C730C157CK###D42000 | TT_Task | Equipment set out (VIC-CST DN Track StationBox area) | 28/03/2022 | 28/03/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 513 | 1112893334_513
C730C157CJ###D41100 | TT_Task | Equipment set out (CST-ND Up Track StationBox area) | 06/05/2022 | 06/05/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 513 | 1112893334_513
C730C157CJ###D41220 | TT_Task | Equipment set out (CST-ND DN Track StationBox area) | 25/03/2022 | 25/03/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 513 | 1112893334_513
C730C157CP###D41060 | TT_Task | Balise Installation - Rework (SD-WLO Down Track) | 22/11/2021 | 01/12/2021 | 22/11/2021 | 30/11/2021 | 0 | TK_Complete | 1112893334 | 512 | 1112893334_512
C730C157CP###D41010 | TT_Task | Delay in Balise and AxCo installation due to track alignment (SD-WLO Up Track) | 23/09/2021 | 29/09/2021 | 23/09/2021 | 30/11/2021 | 0 | TK_Complete | 1112893334 | 512 | 1112893334_512
C730C157CP###D41050 | TT_Task | Delay in Balise and AxCo installation due to track alignment (SD-WLO Down Track) | 23/09/2021 | 29/09/2021 | 25/10/2021 | 19/11/2021 | 0 | TK_Complete | 1112893334 | 512 | 1112893334_512
C730C157CP###D040920 | TT_Task | Site Inspection (SD-WLO Down Track) | 20/10/2021 | 21/10/2021 | 31/08/2021 | 31/08/2021 | 0 | TK_Complete | 1112893334 | 511 | 1112893334_511
C730C157CO###D40810 | TT_Task | Site Inspection (WLO-CEN Up Track) | 25/03/2022 | 25/03/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 511 | 1112893334_511
C730C157CO###D40830 | TT_Task | Site Inspection (WLO-CEN Down Track) | 06/05/2022 | 06/05/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 511 | 1112893334_511
C730C157CN###D41030 | TT_Task | Site Inspection (CEN-PIT Up Track) | 25/03/2022 | 25/03/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 511 | 1112893334_511
C730C157CN###D41050 | TT_Task | Site Inspection (CEN-PIT Down Track) | 06/05/2022 | 06/05/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 511 | 1112893334_511
C730C157CP###D040360 | TT_Task | Completions, defect rectifacation, final sweep (SD-WLO Up Track) | 09/05/2022 | 13/05/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 510 | 1112893334_510
C730C157CP###D040530 | TT_Task | Completions, defect rectifacation, final sweep (SD-WLO Down Track) | 09/05/2022 | 13/05/2022 | nan | nan | 220 | TK_NotStart | 1112893334 | 510 | 1112893334_510
C730C157CO###D40500 | TT_Task | Completions, defect rectifacation, final sweep (WLO-CEN Up Track) | 27/05/2022 | 02/06/2022 | nan | nan | 210 | TK_NotStart | 1112893334 | 510 | 1112893334_510
C730C157CO###D40670 | TT_Task | Completions, defect rectifacation, final sweep (WLO-CEN Down Track) | 28/06/2022 | 04/07/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 510 | 1112893334_510
C730C157CN###D40490 | TT_Task | Completions, defect rectifacation, final sweep (CEN-PIT Up Track) | 02/05/2022 | 05/05/2022 | nan | nan | 330 | TK_NotStart | 1112893334 | 510 | 1112893334_510
C730C157CN###D40660 | TT_Task | Completions, defect rectifacation, final sweep (CEN-PIT Down Track) | 17/06/2022 | 22/06/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 510 | 1112893334_510
C730C157CJ###D40440 | TT_Task | Completions, defect rectifacation, final sweep (VIC-CST Up Track) | 04/07/2022 | 07/07/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 510 | 1112893334_510
C730C157CJ###D40580 | TT_Task | Completions, defect rectifacation, final sweep (VIC-CST Down Track) | 28/06/2022 | 01/07/2022 | nan | nan | 40 | TK_NotStart | 1112893334 | 510 | 1112893334_510
C730C157CI###D40420 | TT_Task | Completions, defect rectifacation, final sweep (CST-ND Up Track) | 13/05/2022 | 19/05/2022 | nan | nan | 100 | TK_NotStart | 1112893334 | 510 | 1112893334_510
C730C157CI###D40610 | TT_Task | Completions, defect rectifacation, final sweep (CST-ND Down Track) | 17/05/2022 | 23/05/2022 | nan | nan | 80 | TK_NotStart | 1112893334 | 510 | 1112893334_510
C730C157BG###D40400 | TT_Task | Completions, defect rectifacation, final sweep (CHW SER) | 30/07/2022 | 06/08/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 510 | 1112893334_510
C730C157CP###TP2330 | TT_Task | Completions, defect rectifacation, final sweep (CHW-ND Up Track) | 27/04/2022 | 03/05/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 510 | 1112893334_510
C730C157CP###TP2570 | TT_Task | Completions, defect rectifacation, final sweep (CHW-ND Down Track) | 27/05/2022 | 02/06/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 510 | 1112893334_510
C730C157CP###TP2850 | TT_Task | Completions, defect rectifacation, final sweep (SD-SYD Trackside) | 10/06/2022 | 15/06/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 510 | 1112893334_510
C720P147CF###0030760 | TT_Task | BA Detrainment doors | 25/02/2020 | 18/03/2020 | 05/12/2019 | 07/02/2020 | 0 | TK_Complete | 1112893334 | 51 | 1112893334_51
C720P147CF###0031440 | TT_Task | PO Detrainment doors | 25/03/2020 | 31/03/2020 | 11/03/2020 | 20/03/2020 | 0 | TK_Complete | 1112893334 | 51 | 1112893334_51
C720P147CF###0031520 | TT_Task | Production Detrainment doors | 27/04/2020 | 08/12/2020 | 06/04/2020 | 13/11/2020 | 0 | TK_Complete | 1112893334 | 51 | 1112893334_51
C720P147CF###0032050 | TT_Task | DEL Detrainment doors | 09/11/2020 | 04/12/2020 | 16/11/2020 | 02/12/2020 | 0 | TK_Complete | 1112893334 | 51 | 1112893334_51
C730C157CP###D040350 | TT_Task | Field Copper Cable - Termination - DCS Power ; Earthing (SD-WLO Up Track) | 16/11/2021 | 24/11/2021 | 09/11/2021 | 18/01/2022 | 0 | TK_Complete | 1112893334 | 509 | 1112893334_509
C730C157CP###D040520 | TT_Task | Field Copper Cable - Termination - DCS Power ; Earthing (SD-WLO Down Track) | 07/02/2022 | 15/02/2022 | 24/01/2022 | 09/02/2022 | 0 | TK_Complete | 1112893334 | 509 | 1112893334_509
C730C157CO###D40490 | TT_Task | Field Copper Cable - Termination - Power ; Earthing (WLO-CEN Up Track) | 24/05/2022 | 26/05/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 509 | 1112893334_509
C730C157CO###D40650 | TT_Task | Field Copper Cable - Termination - Power ; Earthing (WLO-CEN Down Track) | 22/06/2022 | 24/06/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 509 | 1112893334_509
C730C157CO###D41030 | TT_Task | Field Copper Cable - Termination - DCS Power ; Earthing (CEN-PIT Up Track StationBox area) | 20/04/2022 | 20/04/2022 | nan | nan | 20 | TK_NotStart | 1112893334 | 509 | 1112893334_509
C730C157CN###D40480 | TT_Task | Field Copper Cable - Termination - Power ; Earthing (CEN-PIT Up Track) | 28/04/2022 | 28/04/2022 | nan | nan | 10 | TK_NotStart | 1112893334 | 509 | 1112893334_509
C730C157CN###D40650 | TT_Task | Field Copper Cable - Termination - Power ; Earthing (CEN-PIT Down Track) | 14/06/2022 | 15/06/2022 | nan | nan | 10 | TK_NotStart | 1112893334 | 509 | 1112893334_509
C730C157CM###D40530 | TT_Task | Field Copper Cable - Termination - Power ; Earthing (PIT-MPL Up Track) | 27/04/2022 | 27/04/2022 | nan | nan | 30 | TK_NotStart | 1112893334 | 509 | 1112893334_509
C730C157CM###D40670 | TT_Task | Field Copper Cable - Termination - Power ; Earthing (PIT-MPL Down Track) | 23/05/2022 | 24/05/2022 | nan | nan | 20 | TK_NotStart | 1112893334 | 509 | 1112893334_509
C730C157CL###D40440 | TT_Task | Field Copper Cable - Termination - Power ; Earthing (MPL-BZZ Up Track) | 17/03/2022 | 22/03/2022 | 11/03/2022 | 16/03/2022 | 0 | TK_Complete | 1112893334 | 509 | 1112893334_509
C730C157CL###D40600 | TT_Task | Field Copper Cable - Termination - Power ; Earthing (MPL-BZZ Down Track) | 22/03/2022 | 25/03/2022 | 18/03/2022 | nan | 0 | TK_Active | 1112893334 | 509 | 1112893334_509
C730C157CK###D41590 | TT_Task | Field Copper Cable - Termination - DCS Power ; Earthing (MPL-BZZ Down Track) | 20/09/2022 | 20/09/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 509 | 1112893334_509
C730C157CJ###D40420 | TT_Task | Field Copper Cable - Termination - Power ; Earthing (VIC-CST Up Track) | 22/06/2022 | 27/06/2022 | nan | nan | 40 | TK_NotStart | 1112893334 | 509 | 1112893334_509
C730C157CJ###D40560 | TT_Task | Field Copper Cable - Termination - Power ; Earthing (VIC-CST Down Track) | 22/06/2022 | 27/06/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 509 | 1112893334_509
C730C157CI###D40410 | TT_Task | Field Copper Cable - Termination - Power ; Earthing (CST-ND Up Track) | 05/05/2022 | 10/05/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 509 | 1112893334_509
C730C157CI###D40600 | TT_Task | Field Copper Cable - Termination - Power ; Earthing (CST-ND Down Track) | 29/03/2022 | 06/04/2022 | 14/02/2022 | 21/02/2022 | 0 | TK_Complete | 1112893334 | 509 | 1112893334_509
C730C157CP###D040340 | TT_Task | Field Copper Cable - Termination - SAB (SD-WLO Up Track) | 31/01/2022 | 02/02/2022 | 10/02/2022 | 11/02/2022 | 0 | TK_Complete | 1112893334 | 508 | 1112893334_508
C730C157CP###D040510 | TT_Task | Field Copper Cable - Termination - SAB (SD-WLO Down Track) | 31/01/2022 | 03/02/2022 | 10/02/2022 | 11/02/2022 | 0 | TK_Complete | 1112893334 | 508 | 1112893334_508
C730C157CO###D40460 | TT_Task | Field Copper Cable - Termination - SAB (WLO-CEN Up Track) | 23/05/2022 | 23/05/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 508 | 1112893334_508
C730C157CO###D40630 | TT_Task | Field Copper Cable - Termination - SAB (WLO-CEN Down Track) | 21/06/2022 | 21/06/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 508 | 1112893334_508
C730C157CN###D40460 | TT_Task | Field Copper Cable - Termination - SAB (CEN-PIT Up Track) | 27/04/2022 | 27/04/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 508 | 1112893334_508
C730C157CN###D40630 | TT_Task | Field Copper Cable - Termination - SAB (CEN-PIT Down Track) | 10/06/2022 | 10/06/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 508 | 1112893334_508
C730C157CJ###D41080 | TT_Task | Field Copper Cable - Termination - SAB (VIC-CST Up Track) | 21/06/2022 | 22/06/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 508 | 1112893334_508
C730C157CJ###D41360 | TT_Task | Field Copper Cable - Termination - SAB (VIC-CST Down Track) | 21/06/2022 | 22/06/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 508 | 1112893334_508
C730C157CI###D40390 | TT_Task | Field Copper Cable - Termination - SAB (CST-ND Up Track) | 11/05/2022 | 12/05/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 508 | 1112893334_508
C730C157CI###D40580 | TT_Task | Field Copper Cable - Termination - SAB (CST-ND Down Track) | 06/04/2022 | 08/04/2022 | 22/02/2022 | 23/02/2022 | 0 | TK_Complete | 1112893334 | 508 | 1112893334_508
C730C157CP###D040330 | TT_Task | Axle Counter - Terminations (SD-WLO Up Track) | 28/01/2022 | 28/01/2022 | 10/02/2022 | 11/02/2022 | 0 | TK_Complete | 1112893334 | 507 | 1112893334_507
C730C157CP###D040500 | TT_Task | Axle Counter - Terminations (SD-WLO Down Track) | 28/01/2022 | 28/01/2022 | 10/02/2022 | 11/02/2022 | 0 | TK_Complete | 1112893334 | 507 | 1112893334_507
C730C157CO###D40470 | TT_Task | Axle Counters - Termination(WLO-CEN Up Track) | 23/05/2022 | 23/05/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 507 | 1112893334_507
C730C157CO###D40640 | TT_Task | Axle Counter - Terminations (WLO-CEN Down Track) | 21/06/2022 | 21/06/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 507 | 1112893334_507
C730C157CO###D40920 | TT_Task | Axle Counter - Terminations (CEN-PIT Up Track StationBox area) | 19/04/2022 | 19/04/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 507 | 1112893334_507
C730C157CN###D40470 | TT_Task | Axle Counter - Terminations (CEN-PIT Up Track) | 27/04/2022 | 27/04/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 507 | 1112893334_507
C730C157CN###D40640 | TT_Task | Axle Counter - Terminations (CEN-PIT Down Track) | 10/06/2022 | 10/06/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 507 | 1112893334_507
C730C157CM###D40660 | TT_Task | Axle Counter - Terminations (PIT-MPL Down Track) | 20/05/2022 | 20/05/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 507 | 1112893334_507
C730C157CL###D40360 | TT_Task | Axle Counter - Terminations (MPL-BZZ Up Track) | 01/04/2022 | 01/04/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 507 | 1112893334_507
C730C157CL###D40560 | TT_Task | Axle Counter - Terminations (MPL-BZZ Down Track) | 25/03/2022 | 25/03/2022 | nan | nan | 140 | TK_NotStart | 1112893334 | 507 | 1112893334_507
C730C157CJ###D40430 | TT_Task | Axle Counter - Terminations (VIC-CST Up Track) | 21/06/2022 | 21/06/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 507 | 1112893334_507
C730C157CJ###D40570 | TT_Task | Axle Counter - Terminations (VIC-CST Down Track) | 21/06/2022 | 21/06/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 507 | 1112893334_507
C730C157CI###D40400 | TT_Task | Axle Counter - Terminations (CST-ND Up Track) | 11/05/2022 | 12/05/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 507 | 1112893334_507
C730C157CI###D40590 | TT_Task | Axle Counter - Terminations (CST-ND Down Track) | 13/05/2022 | 16/05/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 507 | 1112893334_507
C730C157CP###TP2280 | TT_Task | Axle Counter - Termination (CHW-ND Up Track) | 19/04/2022 | 19/04/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 507 | 1112893334_507
C730C157CP###D040320 | TT_Task | Field Fibre Cable - Splicing - BTN (SD-WLO Up Track) | 04/05/2022 | 05/05/2022 | nan | nan | 10 | TK_NotStart | 1112893334 | 506 | 1112893334_506
C730C157CP###D040490 | TT_Task | Field Fibre Cable - Splicing - BTN (SD-WLO Down Track) | 02/05/2022 | 03/05/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 506 | 1112893334_506
C730C157CK###D41580 | TT_Task | Field Fibre Cable - Splicing - DCS (MPL-BZZ Down Track) | 20/09/2022 | 21/09/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 506 | 1112893334_506
C730C157CK###D41650 | TT_Task | Field Fibre Cable - Splicing - BTN (BZZ X-over to BZZ Up) | 22/09/2022 | 23/09/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 506 | 1112893334_506
C730C157CK###D41610 | TT_Task | Field Fibre Cable - Splicing - DCS (BZZ X-over to BZZ Down) | 20/09/2022 | 21/09/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 506 | 1112893334_506
C730C157CK###D41700 | TT_Task | Field Fibre Cable - Splicing - BTN (BZZ X-over to BZZ Down) | 22/09/2022 | 22/09/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 506 | 1112893334_506
C730C157CP###N41240 | TT_Task | Field Cable - Tying in Earthing into XP (SD-WLO Up Track) | 21/02/2022 | 28/02/2022 | 01/02/2022 | 09/02/2022 | 0 | TK_Complete | 1112893334 | 505 | 1112893334_505
C730C157CP###N41130 | TT_Task | Field Copper Cable - Termination - Earthing in XP (SD-WLO Up Track) | 28/01/2022 | 01/02/2022 | 07/02/2022 | 09/02/2022 | 0 | TK_Complete | 1112893334 | 505 | 1112893334_505
C730C157CP###N41190 | TT_Task | Field Cable - Outstanding works in Dive area (SD-WLO Up Track) | 02/05/2022 | 04/05/2022 | nan | nan | 20 | TK_NotStart | 1112893334 | 504 | 1112893334_504
C730C157CP###N41245 | TT_Task | Field Cable - Outstanding works in Dive area (SD-WLO Down Track) | 02/05/2022 | 04/05/2022 | nan | nan | 20 | TK_NotStart | 1112893334 | 504 | 1112893334_504
C730C157CP###D41070 | TT_Task | Field Cable - DCS Fiber Cable (SD-WLO Up Track) | 15/11/2021 | 15/11/2021 | 17/11/2021 | 17/11/2021 | 0 | TK_Complete | 1112893334 | 503 | 1112893334_503
C730C157CP###D040310 | TT_Task | Field Fibre Cable - Splicing - DCS (SD-WLO Up Track) | 10/11/2021 | 29/11/2021 | 10/11/2021 | 21/01/2022 | 0 | TK_Complete | 1112893334 | 503 | 1112893334_503
C730C157CP###D41080 | TT_Task | Field Cable - DCS Fiber Cable (SD-WLO Down Track) | 30/11/2021 | 30/11/2021 | 30/11/2021 | 30/11/2021 | 0 | TK_Complete | 1112893334 | 503 | 1112893334_503
C730C157CP###D040480 | TT_Task | Field Fibre Cable - Splicing - DCS (SD-WLO Down Track) | 19/01/2022 | 07/02/2022 | 19/01/2022 | 09/02/2022 | 0 | TK_Complete | 1112893334 | 503 | 1112893334_503
C730C157CP###D040620 | TT_Task | Field Cable - Tying in (SD-WLO Up Track) | 28/10/2021 | 09/11/2021 | 28/10/2021 | 09/11/2021 | 0 | TK_Complete | 1112893334 | 502 | 1112893334_502
C730C157CP###D41110 | TT_Task | Field Cable - Tying in Fiber (SD-WLO Up Track) | 03/12/2021 | 15/12/2021 | 26/11/2021 | 07/02/2022 | 0 | TK_Complete | 1112893334 | 502 | 1112893334_502
C730C157CP###D040630 | TT_Task | Field Cable - Tying in (SD-WLO Down Track) | 05/11/2021 | 17/11/2021 | 05/11/2021 | 26/11/2021 | 0 | TK_Complete | 1112893334 | 502 | 1112893334_502
C730C157CP###D41100 | TT_Task | Field Cable - Tying in Fiber (SD-WLO Down Track) | 11/01/2022 | 21/01/2022 | 10/01/2022 | 14/01/2022 | 0 | TK_Complete | 1112893334 | 502 | 1112893334_502
C730C157CP###TP2790 | TT_Task | Field Cable - Tying in (SD-SYD Trackside) | 22/04/2022 | 22/04/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 502 | 1112893334_502
C730C157CP###D040230 | TT_Task | TRE power (SD-WLO Up Track) | 30/09/2021 | 07/10/2021 | 11/10/2021 | 14/10/2021 | 0 | TK_Complete | 1112893334 | 501 | 1112893334_501
C730C157CP###D040400 | TT_Task | TRE power (SD-WLO Down Track) | 27/09/2021 | 01/10/2021 | 27/09/2021 | 29/09/2021 | 0 | TK_Complete | 1112893334 | 501 | 1112893334_501
C730C157CP###TP2230 | TT_Task | TRE power (CHW-ND Up Track) | 08/04/2022 | 08/04/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 501 | 1112893334_501
C730C157CP###TP2470 | TT_Task | TRE power (CHW-ND Down Track) | 13/05/2022 | 13/05/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 501 | 1112893334_501
C730C157CP###D040220 | TT_Task | Field Cable - Installation - SAB Cables (SD-WLO Up Track) | 27/09/2021 | 28/09/2021 | 19/10/2021 | 19/10/2021 | 0 | TK_Complete | 1112893334 | 500 | 1112893334_500
C730C157CP###D040390 | TT_Task | Field Cable - Installation - SAB Cables (SD-WLO Down Track) | 27/09/2021 | 28/09/2021 | 05/10/2021 | 06/10/2021 | 0 | TK_Complete | 1112893334 | 500 | 1112893334_500
C730C157CO###D40340 | TT_Task | Field Cable - Installation - SAB Cables (WLO-CEN Up Track) | 10/05/2022 | 10/05/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 500 | 1112893334_500
C730C157CO###D40510 | TT_Task | Field Cable - Installation - SAB Cables (WLO-CEN Down Track) | 08/06/2022 | 08/06/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 500 | 1112893334_500
C730C157CN###D40350 | TT_Task | Field Cable - Installation - SAB Cables (CEN-PIT Up Track) | 13/04/2022 | 13/04/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 500 | 1112893334_500
C730C157CN###D40520 | TT_Task | Field Cable - Installation - SAB Cables (CEN-PIT Down Track) | 31/05/2022 | 31/05/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 500 | 1112893334_500
C730C157CJ###D41380 | TT_Task | Field Cable - Installation - SAB (VIC-CST Up Track) | 07/06/2022 | 07/06/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 500 | 1112893334_500
C730C157CJ###D41400 | TT_Task | Filed Cable - Installation - SAB (VIC-CST Up Track) | 08/06/2022 | 08/06/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 500 | 1112893334_500
C730C157CI###D40260 | TT_Task | Field Cable - Installation - SAB Cables (CST-ND Up Track) | 11/11/2021 | 11/11/2021 | 05/11/2021 | 05/11/2021 | 0 | TK_Complete | 1112893334 | 500 | 1112893334_500
C730C157CI###D40450 | TT_Task | Field Cable - Installation - SAB Cables (CST-ND Down Track) | 29/11/2021 | 29/11/2021 | 24/11/2021 | 24/11/2021 | 0 | TK_Complete | 1112893334 | 500 | 1112893334_500
C720P147CF###0030750 | TT_Task | BA Grabpoles and grab handles | 25/02/2020 | 19/03/2020 | 05/12/2019 | 23/03/2020 | 0 | TK_Complete | 1112893334 | 50 | 1112893334_50
C720P147CF###0031120 | TT_Task | PO Grabpoles and grab handles | 27/04/2020 | 29/05/2020 | 24/03/2020 | 06/04/2020 | 0 | TK_Complete | 1112893334 | 50 | 1112893334_50
C720P147CF###0031380 | TT_Task | Production Grabpoles and grab handles | 25/06/2020 | 08/02/2021 | 29/05/2020 | 14/10/2020 | 0 | TK_Complete | 1112893334 | 50 | 1112893334_50
C720P147CF###0031740 | TT_Task | DEL Grabpoles and grab handles | 11/11/2020 | 01/12/2020 | 28/10/2020 | 06/12/2020 | 0 | TK_Complete | 1112893334 | 50 | 1112893334_50
C720D147CF###0037015 | TT_Task | Radio - Review of List of Spares | 27/07/2020 | 07/08/2020 | 13/07/2020 | 23/07/2020 | 0 | TK_Complete | 1112893334 | 5 | 1112893334_5
C730C157CP###D040210 | TT_Task | Field Cable - Installation - AxCo (SD-WLO Up Track) | 27/09/2021 | 27/09/2021 | 19/10/2021 | 19/10/2021 | 0 | TK_Complete | 1112893334 | 499 | 1112893334_499
C730C157CP###D040380 | TT_Task | Field Cable - Installation - AxCo (SD-WLO Down Track) | 27/09/2021 | 27/09/2021 | 05/10/2021 | 06/10/2021 | 0 | TK_Complete | 1112893334 | 499 | 1112893334_499
C730C157CO###D40350 | TT_Task | Field Cable - Installation - AxCo (WLO-CEN Up Track) | 10/05/2022 | 10/05/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 499 | 1112893334_499
C730C157CO###D40520 | TT_Task | Field Cable - Installation - AxCo (WLO-CEN Down Track) | 08/06/2022 | 08/06/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 499 | 1112893334_499
C730C157CJ###D40330 | TT_Task | Field Cable - Installation - AxCo (VIC-CST Up Track) | 07/06/2022 | 07/06/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 499 | 1112893334_499
C730C157CJ###D40470 | TT_Task | Field Cable - Installation - AxCo (VIC-CST Down Track) | 08/06/2022 | 08/06/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 499 | 1112893334_499
C730C157CI###D40270 | TT_Task | Field Cable - Installation - AxCo (CST-ND Up Track) | 12/11/2021 | 15/11/2021 | 04/11/2021 | 05/11/2021 | 0 | TK_Complete | 1112893334 | 499 | 1112893334_499
C730C157CI###D40460 | TT_Task | Field Cable - Installation - AxCo (CST-ND Down Track) | 29/11/2021 | 30/11/2021 | 25/11/2021 | 26/11/2021 | 0 | TK_Complete | 1112893334 | 499 | 1112893334_499
C730C157CP###D040190 | TT_Task | Field Cable - Installation - DCS Fibre (SD-WLO Up Track) | 30/09/2021 | 06/10/2021 | 15/10/2021 | 18/10/2021 | 0 | TK_Complete | 1112893334 | 498 | 1112893334_498
C730C157CP###D040200 | TT_Task | Field Cable - Installation - Fibre Backbone (SD-WLO Up Track) | 07/10/2021 | 11/10/2021 | 20/10/2021 | 22/10/2021 | 0 | TK_Complete | 1112893334 | 498 | 1112893334_498
C730C157CP###D040370 | TT_Task | Field Cable - Installation - Fibre Backbone (SD-WLO Down Track) | 01/10/2021 | 05/10/2021 | 06/10/2021 | 08/10/2021 | 0 | TK_Complete | 1112893334 | 498 | 1112893334_498
C730C157CP###D040540 | TT_Task | Field Cable - Installation - DCS Fibre (SD-WLO Down Track) | 27/09/2021 | 30/09/2021 | 05/10/2021 | 08/10/2021 | 0 | TK_Complete | 1112893334 | 498 | 1112893334_498
C730C157CO###D40360 | TT_Task | Field Cable - Installation - Fibre Backbone (WLO-CEN Up Track) | 11/05/2022 | 12/05/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 498 | 1112893334_498
C730C157CO###D40370 | TT_Task | Field Cable - Installation - DCS Fibre (WLO-CEN Up Track) | 13/05/2022 | 13/05/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 498 | 1112893334_498
C730C157CO###D40530 | TT_Task | Field Cable - Installation - Fibre Backbone (WLO-CEN Down Track) | 08/06/2022 | 09/06/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 498 | 1112893334_498
C730C157CO###D40540 | TT_Task | Field Cable - Installation - DCS Fibre (WLO-CEN Down Track) | 10/06/2022 | 10/06/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 498 | 1112893334_498
C730C157CP###N41180 | TT_Task | Outstanding equipment in Dive area- Blocked(SD-WLO Up Track) | 28/01/2022 | 31/01/2022 | 27/01/2022 | 28/01/2022 | 0 | TK_Complete | 1112893334 | 497 | 1112893334_497
C730C157CP###N41230 | TT_Task | Outstanding equipment in Dive area- Blocked(SD-WLO Down Track) | 28/01/2022 | 31/01/2022 | 27/01/2022 | 28/01/2022 | 0 | TK_Complete | 1112893334 | 497 | 1112893334_497
C730C157CP###N41170 | TT_Task | Delay in Mechanical installation in Dive area (SD-WLO Up Track) | 27/01/2022 | 27/01/2022 | 14/12/2021 | 26/01/2022 | 0 | TK_Complete | 1112893334 | 496 | 1112893334_496
C730C157CP###N41210 | TT_Task | Delay in Mechanical installation in Dive area (SD-WLO Up Down Track) | 27/01/2022 | 27/01/2022 | 18/12/2021 | 26/01/2022 | 0 | TK_Complete | 1112893334 | 496 | 1112893334_496
C730C157CP###N41140 | TT_Task | Delay in equipment installation due to access blocked (SD-WLO Up Track) | 27/01/2022 | 27/01/2022 | 14/12/2021 | nan | 0 | TK_Active | 1112893334 | 495 | 1112893334_495
C730C157CP###N41160 | TT_Task | Outstanding equipment to be installed - Blocked(SD-WLO Up Track) | 02/05/2022 | 06/05/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 495 | 1112893334_495
C730C157CP###N41200 | TT_Task | Delay in equipment installation due to access blocked (SD-WLO Down Track) | 27/01/2022 | 27/01/2022 | 18/12/2021 | nan | 0 | TK_Active | 1112893334 | 495 | 1112893334_495
C730C157CP###N41220 | TT_Task | Outstanding equipment to be installed - Blocked(SD-WLO Down Track) | 02/05/2022 | 06/05/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 495 | 1112893334_495
C730C157CP###D040890 | TT_Task | Site Inspction (SD-WLO Up Track) | 20/10/2021 | 21/10/2021 | 16/09/2021 | 16/09/2021 | 0 | TK_Complete | 1112893334 | 494 | 1112893334_494
C730C157CP###D040610 | TT_Task | Marker Boards - Mechanical (SD-WLO Up Track) | 25/11/2021 | 29/11/2021 | 10/11/2021 | 10/11/2021 | 0 | TK_Complete | 1112893334 | 493 | 1112893334_493
C730C157CP###D040580 | TT_Task | Marker Board - Mechanical (SD-WLO Down Track) | 30/11/2021 | 01/12/2021 | 17/12/2021 | 17/12/2021 | 0 | TK_Complete | 1112893334 | 493 | 1112893334_493
C730C157CP###TP2720 | TT_Task | Marker Boards (SD-SYD Trackside) | 09/05/2022 | 18/05/2022 | nan | nan | 128 | TK_NotStart | 1112893334 | 493 | 1112893334_493
C730C157CP###D040600 | TT_Task | Axle Counter - Mechanical (SD-WLO Up Track) | 07/12/2021 | 08/12/2021 | 10/12/2021 | 10/12/2021 | 0 | TK_Complete | 1112893334 | 492 | 1112893334_492
C730C157CP###D040560 | TT_Task | Axle Counter - Mechanical (SD-WLO Down Track) | 25/11/2021 | 26/11/2021 | 17/12/2021 | 17/12/2021 | 0 | TK_Complete | 1112893334 | 492 | 1112893334_492
C730C157CP###TP2660 | TT_Task | Axle Counters (SD-SYD Trackside) | 20/04/2022 | 28/04/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 492 | 1112893334_492
C730C157CP###TP2800 | TT_Task | Axle Counter - Termination (SD-SYD Trackside) | 12/05/2022 | 19/05/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 492 | 1112893334_492
C730C157CP###D040590 | TT_Task | DCS Splice Box (SD-WLO Up Track) | 07/02/2022 | 10/02/2022 | 17/09/2021 | 24/09/2021 | 0 | TK_Complete | 1112893334 | 491 | 1112893334_491
C730C157CP###D040550 | TT_Task | DCS Splice Box (SD-WLO Down Track) | 06/01/2022 | 11/01/2022 | 21/09/2021 | 24/09/2021 | 0 | TK_Complete | 1112893334 | 491 | 1112893334_491
C730C157CO###D40680 | TT_Task | DCS Splice Box (WLO-CEN Up Track) | 02/05/2022 | 02/05/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 491 | 1112893334_491
C730C157CO###D40720 | TT_Task | DCS Splice Box (WLO-CEN Down Track) | 07/06/2022 | 07/06/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 491 | 1112893334_491
C730C157CO###D40970 | TT_Task | DCS Splice Box (CEN-PIT Up Track StationBox area) | 06/04/2022 | 06/04/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 491 | 1112893334_491
C730C157CN###D40670 | TT_Task | DCS Splice Box (CEN-PIT Up Track) | 11/04/2022 | 11/04/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 491 | 1112893334_491
C730C157CN###D40700 | TT_Task | DCS Splice Box (CEN-PIT Down Track) | 30/05/2022 | 30/05/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 491 | 1112893334_491
C730C157CJ###D41020 | TT_Task | DCS Splice Box (VIC-CST Up Track) | 02/06/2022 | 03/06/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 491 | 1112893334_491
C730C157CJ###D41050 | TT_Task | DCS Splice Box (VIC-CST Down Track) | 02/06/2022 | 03/06/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 491 | 1112893334_491
C730C157CI###D40620 | TT_Task | DCS Splice Box (CST-ND Up Track) | 27/09/2021 | 29/09/2021 | 13/10/2021 | 15/10/2021 | 0 | TK_Complete | 1112893334 | 491 | 1112893334_491
C730C157CI###D40650 | TT_Task | DCS Splice Box (CST-ND Down Track) | 02/11/2021 | 04/11/2021 | 15/11/2021 | 17/11/2021 | 0 | TK_Complete | 1112893334 | 491 | 1112893334_491
C730C157CP###TP2180 | TT_Task | DCS Splice Box (CHW-ND Up Track) | 05/04/2022 | 05/04/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 491 | 1112893334_491
C730C157CP###TP2420 | TT_Task | DCS Splice Box (CHW-ND Down Track) | 10/05/2022 | 10/05/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 491 | 1112893334_491
C730C157CP###D040300 | TT_Task | Balise - Mechanical (SD-WLO Up Track) | 30/11/2021 | 06/12/2021 | 01/12/2021 | 13/12/2021 | 0 | TK_Complete | 1112893334 | 490 | 1112893334_490
C730C157CP###D040470 | TT_Task | Balise - Mechanical (SD-WLO Down Track) | 27/09/2021 | 07/10/2021 | 01/09/2021 | 09/09/2021 | 0 | TK_Complete | 1112893334 | 490 | 1112893334_490
C730C157CO###D40410 | TT_Task | Balise - Mechanical (WLO-CEN Up Track) | 01/04/2022 | 06/04/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 490 | 1112893334_490
C730C157CO###D40620 | TT_Task | Balise - Mechanical (WLO-CEN Down Track) | 13/05/2022 | 17/05/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 490 | 1112893334_490
C720P147CF###0031110 | TT_Task | BA EUF | 25/02/2020 | 17/03/2020 | 05/12/2019 | 20/01/2020 | 0 | TK_Complete | 1112893334 | 49 | 1112893334_49
C720P147CF###0031320 | TT_Task | PO EUF | 27/04/2020 | 15/05/2020 | 26/03/2020 | 13/04/2020 | 0 | TK_Complete | 1112893334 | 49 | 1112893334_49
C720P147CF###0031430 | TT_Task | Production EUF | 25/06/2020 | 22/01/2021 | 26/04/2020 | 20/10/2020 | 0 | TK_Complete | 1112893334 | 49 | 1112893334_49
C720P147CF###0032110 | TT_Task | DEL EUF | 17/11/2020 | 12/01/2021 | 21/10/2020 | 26/10/2020 | 0 | TK_Complete | 1112893334 | 49 | 1112893334_49
C730C157CP###D040290 | TT_Task | DCS TRE Box - Mechanical (SD-WLO Up Track) | 20/01/2022 | 07/02/2022 | 16/09/2021 | 24/09/2021 | 0 | TK_Complete | 1112893334 | 489 | 1112893334_489
C730C157CP###D040430 | TT_Task | DCS TRE Box - Mechanical (SD-WLO Down Track) | 24/11/2021 | 09/12/2021 | 08/09/2021 | 21/09/2021 | 0 | TK_Complete | 1112893334 | 489 | 1112893334_489
C730C157CO###D40430 | TT_Task | DCS TRE Box - Mechanical (WLO-CEN Up Track) | 19/04/2022 | 26/04/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 489 | 1112893334_489
C730C157CO###D40610 | TT_Task | DCS TRE Box - Mechanical (WLO-CEN Down Track) | 23/05/2022 | 27/05/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 489 | 1112893334_489
C730C157CJ###D40380 | TT_Task | DCS TRE Box - Mechanical (VIC-CST Up Track) | 18/05/2022 | 25/05/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 489 | 1112893334_489
C730C157CJ###D40520 | TT_Task | DCS TRE Box - Mechanical (VIC-CST Down Track) | 18/05/2022 | 25/05/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 489 | 1112893334_489
C730C157CI###D40350 | TT_Task | DCS TRE Box - Mechanical (CST-ND Up Track) | 29/09/2021 | 14/10/2021 | 05/10/2021 | 21/10/2021 | 0 | TK_Complete | 1112893334 | 489 | 1112893334_489
C730C157CI###D40980 | TT_Task | DCS TRE Box - Remaining Mechanical (CST-ND Up Track) | 10/11/2021 | 10/11/2021 | 05/11/2021 | 05/11/2021 | 0 | TK_Complete | 1112893334 | 489 | 1112893334_489
C730C157CI###D40540 | TT_Task | DCS TRE Box - Mechanical (CST-ND Down Track) | 27/10/2021 | 09/11/2021 | 27/10/2021 | 05/11/2021 | 0 | TK_Complete | 1112893334 | 489 | 1112893334_489
C730C157CP###D040280 | TT_Task | FO Backbone Inline Box (SD-WLO Up Track) | 25/10/2021 | 25/10/2021 | 11/11/2021 | 11/11/2021 | 0 | TK_Complete | 1112893334 | 488 | 1112893334_488
C730C157CP###D040450 | TT_Task | Backbone Inline Box (SD-WLO Down Track) | 22/11/2021 | 22/11/2021 | 12/11/2021 | 12/11/2021 | 0 | TK_Complete | 1112893334 | 488 | 1112893334_488
C730C157CP###D040270 | TT_Task | SAB - Mechanical (SD-WLO Up Track) | 27/09/2021 | 28/09/2021 | 01/10/2021 | 01/10/2021 | 0 | TK_Complete | 1112893334 | 487 | 1112893334_487
C730C157CP###D040460 | TT_Task | SAB - Mechanical (SD-WLO Down Track) | 12/10/2021 | 13/10/2021 | 11/10/2021 | 12/10/2021 | 0 | TK_Complete | 1112893334 | 487 | 1112893334_487
C730C157CO###D40450 | TT_Task | SAB - Mechanical (WLO-CEN Up Track) | 07/04/2022 | 11/04/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 487 | 1112893334_487
C730C157CO###D40580 | TT_Task | SAB - Mechanical (WLO-CEN Down Track) | 18/05/2022 | 20/05/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 487 | 1112893334_487
C730C157CN###D40400 | TT_Task | SAB - Mechanical (CEN-PIT Up Track) | 05/04/2022 | 06/04/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 487 | 1112893334_487
C730C157CN###D40580 | TT_Task | SAB - Mechanical (CEN-PIT Down Track) | 13/05/2022 | 16/05/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 487 | 1112893334_487
C730C157CP###D040260 | TT_Task | Antennas and Cabling (SD-WLO Up Track) | 28/10/2021 | 10/11/2021 | 11/10/2021 | 22/10/2021 | 0 | TK_Complete | 1112893334 | 486 | 1112893334_486
C730C157CP###D41090 | TT_Task | Antennas and Cabling - rework (SD-WLO Up Track) | 22/11/2021 | 26/11/2021 | 15/11/2021 | 26/11/2021 | 0 | TK_Complete | 1112893334 | 486 | 1112893334_486
C730C157CP###D040440 | TT_Task | Antennas and Cabling (SD-WLO Down Track) | 05/11/2021 | 17/11/2021 | 01/11/2021 | 09/11/2021 | 0 | TK_Complete | 1112893334 | 486 | 1112893334_486
C730C157CP###TP2690 | TT_Task | Antennas and Cabling (SD-SYD Trackside) | 06/04/2022 | 08/04/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 486 | 1112893334_486
C730C157CP###D040250 | TT_Task | Material Distribution (SD-WLO Up Track) | 16/12/2021 | 10/01/2022 | 16/09/2021 | 24/09/2021 | 0 | TK_Complete | 1112893334 | 485 | 1112893334_485
C730C157CP###D040420 | TT_Task | Material Distribution (SD-WLO Down Track) | 25/10/2021 | 02/11/2021 | 03/09/2021 | 17/09/2021 | 0 | TK_Complete | 1112893334 | 485 | 1112893334_485
C730C157CP###TP2120 | TT_Task | Material Distribution (CHW-ND Up Track) | 30/03/2022 | 30/03/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 485 | 1112893334_485
C730C157CP###TP2360 | TT_Task | Material Distribution (CHW-ND Down Track) | 05/05/2022 | 05/05/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 485 | 1112893334_485
C730C157CP###TP2640 | TT_Task | Material Distribution (SD-SYD Trackside) | 29/03/2022 | 30/03/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 485 | 1112893334_485
C730C157CP###D040240 | TT_Task | Equipment set out (SD-WLO Up Track) | 13/12/2021 | 16/12/2021 | 08/09/2021 | 22/09/2021 | 0 | TK_Complete | 1112893334 | 484 | 1112893334_484
C730C157CP###D040410 | TT_Task | Equipment set out (SD-WLO Down Track) | 20/10/2021 | 25/10/2021 | 31/08/2021 | 02/09/2021 | 0 | TK_Complete | 1112893334 | 484 | 1112893334_484
C730C157CP###TP2100 | TT_Task | Equipment set out (CHW-ND Up Track) | 28/03/2022 | 29/03/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 484 | 1112893334_484
C730C157CP###TP2350 | TT_Task | Equipment set out (CHW-ND Down Track) | 04/05/2022 | 04/05/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 484 | 1112893334_484
C730C157CD###0040770 | TT_Task | DCC2 South Depot (Equipment installation) | 20/07/2022 | 27/09/2022 | nan | nan | 224 | TK_NotStart | 1112893334 | 483 | 1112893334_483
C730C157CD###0040780 | TT_Task | BOCC SMNW+City (Station considered = Bellavista) | 05/04/2022 | 09/05/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 482 | 1112893334_482
C730C157CD###40790 | TT_Task | CAB South Depot - Cable termination to DSER | 17/10/2022 | 04/11/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 481 | 1112893334_481
C730C157CD###0040580 | TT_Task | SER South Depot - DSER3 (cubicles ; internal wiring) | 30/05/2022 | 27/09/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 481 | 1112893334_481
C730C157CD###0040790 | TT_Task | SER South Depot (Trackside Cable Termination to DSER3) | 10/10/2022 | 04/11/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 481 | 1112893334_481
C730C157CD###0040680 | TT_Task | CAB Cabling CER to Depot | 01/08/2022 | 12/08/2022 | nan | nan | 480 | TK_NotStart | 1112893334 | 480 | 1112893334_480
C730C157CD###0040690 | TT_Task | CAB South Depot - Cable Pulling | 01/08/2022 | 27/10/2022 | nan | nan | 48 | TK_NotStart | 1112893334 | 480 | 1112893334_480
C720P147CF###0030420 | TT_Task | BA Long profile | 25/03/2020 | 31/03/2020 | 02/03/2020 | 11/03/2020 | 0 | TK_Complete | 1112893334 | 48 | 1112893334_48
C720P147CF###0031090 | TT_Task | PO Long profile | 27/04/2020 | 15/05/2020 | 24/04/2020 | 30/04/2020 | 0 | TK_Complete | 1112893334 | 48 | 1112893334_48
C720P147CF###0031190 | TT_Task | Production Long profile | 15/06/2020 | 12/01/2021 | 04/05/2020 | 20/10/2020 | 0 | TK_Complete | 1112893334 | 48 | 1112893334_48
C720P147CF###0031800 | TT_Task | DEL Long profile | 17/11/2020 | 12/01/2021 | 21/10/2020 | 26/10/2020 | 0 | TK_Complete | 1112893334 | 48 | 1112893334_48
C730K147BC###0020784 | TT_Task | Site mobilization, permits obtain, review of handover docs Crows Nest Station/SER | 29/04/2022 | 09/06/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 479 | 1112893334_479
C730K147BC###0020160 | TT_Task | Site mobilization, permits obtain, review of handover docs Northern Dive to Crows Nest Station - UP/DN TRACK | 06/09/2021 | 15/10/2021 | 04/06/2021 | 13/10/2021 | 0 | TK_Complete | 1112893334 | 479 | 1112893334_479
C730K147BC###0020320 | TT_Task | Site mobilization, permits obtain, review of handover docs Crows Nest Station Trackway | 25/03/2022 | 05/05/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 479 | 1112893334_479
C730K147BC###0020328 | TT_Task | Site mobilization, permits obtain, review of handover docs Crows Nest Station to Victoria Cross Station - UP/DN TRACK | 25/03/2022 | 05/05/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 479 | 1112893334_479
C730K147BC###0020640 | TT_Task | Site mobilization, permits obtain, review of handover docs Barangaroo Station/SER | 03/03/2022 | 13/04/2022 | 03/03/2022 | nan | 0 | TK_Active | 1112893334 | 478 | 1112893334_478
C730K147BC###0020736 | TT_Task | Site mobilization, permits obtain, review of handover docs Barangaroo Station/SCR | 22/04/2022 | 02/06/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 478 | 1112893334_478
C730K147BC###0020248 | TT_Task | Site mobilization, permits obtain, review of handover docs Barangaroo Station Trackway | 25/03/2022 | 05/05/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 478 | 1112893334_478
C730K147BC###0020256 | TT_Task | Site mobilization, permits obtain, review of handover docs Barangaroo Station to Martin Place Station - UP/DN TRACK | 27/12/2021 | 04/02/2022 | 27/12/2021 | 17/01/2022 | 0 | TK_Complete | 1112893334 | 478 | 1112893334_478
C730K147BC###0020424 | TT_Task | Site mobilization, permits obtain, review of handover docs Victoria Cross Station to Barangaroo Station - UP/DN TRACK | 25/02/2022 | 07/04/2022 | 18/07/2021 | 04/08/2021 | 0 | TK_Complete | 1112893334 | 478 | 1112893334_478
C730K147BC###0020632 | TT_Task | Site mobilization, permits obtain, review of handover docs Pitt Street Station/SER | 03/03/2022 | 13/04/2022 | 03/03/2022 | nan | 0 | TK_Active | 1112893334 | 477 | 1112893334_477
C730K147BC###0020472 | TT_Task | Site mobilization, permits obtain, review of handover docs Pitt Street Station Trackway | 25/03/2022 | 05/05/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 477 | 1112893334_477
C730K147BC###0020480 | TT_Task | Site mobilization, permits obtain, review of handover docs Pitt Street Station to Central Station - UP/DN TRACK | 25/03/2022 | 05/05/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 477 | 1112893334_477
C730K147BC###0020688 | TT_Task | Site mobilization, permits obtain, review of handover docs Martin Place Station to Pitt Street Station - UP/DN TRACK | 25/02/2022 | 07/04/2022 | 09/01/2022 | 04/02/2022 | 0 | TK_Complete | 1112893334 | 477 | 1112893334_477
C730K147BC###0020584 | TT_Task | Site mobilization, permits obtain, review of handover docs Waterloo Station/SER | 01/03/2022 | 11/04/2022 | 01/03/2022 | nan | 0 | TK_Active | 1112893334 | 476 | 1112893334_476
C730K147BC###0020040 | TT_Task | Site mobilization, permits obtain, review of handover docs Waterloo Station to Southern Dive - UP/DN TRACK | 06/09/2021 | 15/10/2021 | 03/06/2021 | 16/09/2021 | 0 | TK_Complete | 1112893334 | 476 | 1112893334_476
C730K147BC###0020488 | TT_Task | Site mobilization, permits obtain, review of handover docs Central Station to Waterloo Station - UP/DN TRACK | 25/03/2022 | 05/05/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 476 | 1112893334_476
C730K147BC###0020496 | TT_Task | Site mobilization, permits obtain, review of handover docs Waterloo Station Trackway | 25/03/2022 | 05/05/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 476 | 1112893334_476
C730K147BC###0020016 | TT_Task | Site mobilization, permits obtain, review of handover docs Chatswood Station | 25/02/2022 | 07/04/2022 | 25/02/2022 | nan | 0 | TK_Active | 1112893334 | 475 | 1112893334_475
C730K147BC###0020104 | TT_Task | Site mobilization, permits obtain, review of handover docs Sydenham Station/S;TER | 25/08/2021 | 05/10/2021 | 27/05/2021 | 18/10/2021 | 0 | TK_Complete | 1112893334 | 475 | 1112893334_475
C730K147BC###0020112 | TT_Task | Site mobilization, permits obtain, review of handover docs City CER/BOCC | 25/08/2021 | 05/10/2021 | 28/05/2021 | nan | 0 | TK_Active | 1112893334 | 475 | 1112893334_475
C730K147BC###0020200 | TT_Task | Site mobilization, permits obtain, review of handover docs Central Station/SER | 25/01/2022 | 07/03/2022 | 25/01/2022 | 14/02/2022 | 0 | TK_Complete | 1112893334 | 475 | 1112893334_475
C730K147BC###0020520 | TT_Task | Site mobilization, permits obtain, review of handover docs SMTF[S] Depot DSER3 | 25/02/2022 | 07/04/2022 | 18/02/2022 | nan | 0 | TK_Active | 1112893334 | 475 | 1112893334_475
C730K147BC###0020608 | TT_Task | Site mobilization, permits obtain, review of handover docs Martin Place Station/SER | 25/02/2022 | 07/04/2022 | 03/03/2022 | nan | 0 | TK_Active | 1112893334 | 475 | 1112893334_475
C730K147BC###0020776 | TT_Task | Site mobilization, permits obtain, review of handover docs Victoria Cross Station/SER | 29/04/2022 | 09/06/2022 | 20/03/2022 | 23/03/2022 | 0 | TK_Complete | 1112893334 | 475 | 1112893334_475
C730K147BC###0020136 | TT_Task | Site mobilization, permits obtain, review of handover docs Sydenham Station Trackway | 25/08/2021 | 05/10/2021 | 27/05/2021 | 18/10/2021 | 0 | TK_Complete | 1112893334 | 475 | 1112893334_475
C730K147BC###0020144 | TT_Task | Site mobilization, permits obtain, review of handover docs Southern Dive to Sydenham Station - UP/DN TRACK | 25/08/2021 | 05/10/2021 | 27/05/2021 | nan | 0 | TK_Active | 1112893334 | 475 | 1112893334_475
C730K147BC###0020280 | TT_Task | Site mobilization, permits obtain, review of handover docs Chatswood to Northern Dive - UP/DN TRACK | 25/03/2022 | 05/05/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 475 | 1112893334_475
C730K147BC###0020416 | TT_Task | Site mobilization, permits obtain, review of handover docs Victoria Cross Station Trackway | 25/03/2022 | 05/05/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 475 | 1112893334_475
C730K147BC###0020504 | TT_Task | Site mobilization, permits obtain, review of handover docs Central Station Trackway | 25/03/2022 | 05/05/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 475 | 1112893334_475
C730K147BC###0020680 | TT_Task | Site mobilization, permits obtain, review of handover docs Martin Place Station Trackway | 04/04/2022 | 13/05/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 475 | 1112893334_475
C730K147BC###0020880 | TT_Task | Site mobilization, permits obtain, review of handover docs SMTF [S] Depot Trackside | 20/06/2022 | 29/07/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 475 | 1112893334_475
C730K147BC###0020712 | TT_Task | Site Survey Prior to Site Access - Crows Nest Station/SER | 29/04/2022 | 09/06/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 474 | 1112893334_474
C730K147BC###0020080 | TT_Task | Site Survey Prior to Site Access - Northern Dive to Crows Nest Station - UP/DN TRACK | 06/08/2021 | 02/09/2021 | 04/06/2021 | 13/10/2021 | 0 | TK_Complete | 1112893334 | 474 | 1112893334_474
C730K147BC###0020288 | TT_Task | Site Survey Prior to Site Access - Crows Nest Station Trackway | 25/03/2022 | 05/05/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 474 | 1112893334_474
C730K147BC###0020296 | TT_Task | Site Survey Prior to Site Access - Crows Nest Station to Victoria Cross Station - UP/DN TRACK | 25/03/2022 | 05/05/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 474 | 1112893334_474
C730K147BC###0020560 | TT_Task | Site Survey Prior to Site Access - Barangaroo Station/SER | 16/03/2022 | 26/04/2022 | 16/03/2022 | nan | 0 | TK_Active | 1112893334 | 473 | 1112893334_473
C730K147BC###0020696 | TT_Task | Site Survey Prior to Site Access - Barangaroo Station/SCR | 22/04/2022 | 02/06/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 473 | 1112893334_473
C730K147BC###0020216 | TT_Task | Site Survey Prior to Site Access - Barangaroo Station Trackway | 25/03/2022 | 05/05/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 473 | 1112893334_473
C730K147BC###0020224 | TT_Task | Site Survey Prior to Site Access - Barangaroo Station to Martin Place Station - UP/DN TRACK | 27/12/2021 | 04/02/2022 | 27/12/2021 | 12/01/2022 | 0 | TK_Complete | 1112893334 | 473 | 1112893334_473
C730K147BC###0020344 | TT_Task | Site Survey Prior to Site Access - Victoria Cross Station to Barangaroo Station - UP/DN TRACK | 25/02/2022 | 07/04/2022 | 02/08/2021 | 04/08/2021 | 0 | TK_Complete | 1112893334 | 473 | 1112893334_473
C730K147BC###0020552 | TT_Task | Site Survey Prior to Site Access - Pitt Street Station/SER | 16/03/2022 | 26/04/2022 | 16/03/2022 | nan | 0 | TK_Active | 1112893334 | 472 | 1112893334_472
C730K147BC###0020352 | TT_Task | Site Survey Prior to Site Access - Pitt Street Station Trackway | 25/03/2022 | 05/05/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 472 | 1112893334_472
C730K147BC###0020360 | TT_Task | Site Survey Prior to Site Access - Pitt Street Station to Central Station - UP/DN TRACK | 25/03/2022 | 05/05/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 472 | 1112893334_472
C730K147BC###0020656 | TT_Task | Site Survey Prior to Site Access - Martin Place Station to Pitt Street Station - UP/DN TRACK) | 25/02/2022 | 07/04/2022 | 23/01/2022 | 04/02/2022 | 0 | TK_Complete | 1112893334 | 472 | 1112893334_472
C730K147BC###0020048 | TT_Task | Site Survey Prior to Site Access - Sydenham Station/S;TER | 16/07/2021 | 26/08/2021 | 27/05/2021 | 18/10/2021 | 0 | TK_Complete | 1112893334 | 471 | 1112893334_471
C730K147BC###0020024 | TT_Task | Site Survey Prior to Site Access - Waterloo Station to Southern Dive - UP/DN TRACK | 06/08/2021 | 02/09/2021 | 03/06/2021 | 16/09/2021 | 0 | TK_Complete | 1112893334 | 471 | 1112893334_471
C730K147BC###0020064 | TT_Task | Site Survey Prior to Site Access - Sydenham Station Trackway | 25/08/2021 | 05/10/2021 | 27/05/2021 | 18/10/2021 | 0 | TK_Complete | 1112893334 | 471 | 1112893334_471
C730K147BC###0020072 | TT_Task | Site Survey Prior to Site Access - Southern Dive to Sydenham Station - UP/DN TRACK | 25/08/2021 | 05/10/2021 | 27/05/2021 | 04/01/2022 | 0 | TK_Complete | 1112893334 | 471 | 1112893334_471
C730K147BC###0020336 | TT_Task | Site Survey Prior to Site Access - Victoria Cross Station Trackway | 25/03/2022 | 05/05/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 471 | 1112893334_471
C730K147BC###0020368 | TT_Task | Site Survey Prior to Site Access - Central Station to Waterloo Station - UP/DN TRACK | 25/03/2022 | 05/05/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 471 | 1112893334_471
C730K147BC###0020376 | TT_Task | Site Survey Prior to Site Access - Waterloo Station Trackway | 25/03/2022 | 05/05/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 471 | 1112893334_471
C730K147BC###0020384 | TT_Task | Site Survey Prior to Site Access - Central Station Trackway | 25/03/2022 | 05/05/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 471 | 1112893334_471
C730K147BC###0020648 | TT_Task | Site Survey Prior to Site Access - Martin Place Station Trackway | 04/04/2022 | 13/05/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 471 | 1112893334_471
C730K147BC###0020000 | TT_Task | Site Survey Prior to Site Access - Chatswood Station (Program assumption) | 25/06/2021 | 05/08/2021 | 20/03/2021 | 01/10/2021 | 0 | TK_Complete | 1112893334 | 470 | 1112893334_470
C730K147BC###0020056 | TT_Task | Site Survey Prior to Site Access - City CER/BOCC | 16/07/2021 | 26/08/2021 | 28/05/2021 | nan | 0 | TK_Active | 1112893334 | 470 | 1112893334_470
C730K147BC###0020168 | TT_Task | Site Survey Prior to Site Access - Central Station/SER | 25/01/2022 | 07/03/2022 | 25/01/2022 | 11/02/2022 | 0 | TK_Complete | 1112893334 | 470 | 1112893334_470
C730K147BC###0020528 | TT_Task | Site Survey Prior to Site Access - Waterloo Station/SER | 09/03/2022 | 19/04/2022 | 09/03/2022 | 09/03/2022 | 0 | TK_Complete | 1112893334 | 470 | 1112893334_470
C730K147BC###0020544 | TT_Task | Site Survey Prior to Site Access - Martin Place Station/SER | 11/03/2022 | 21/04/2022 | 11/03/2022 | nan | 0 | TK_Active | 1112893334 | 470 | 1112893334_470
C730K147BC###0020704 | TT_Task | Site Survey Prior to Site Access - Victoria Cross Station/SER | 29/04/2022 | 09/06/2022 | 13/03/2022 | 17/03/2022 | 0 | TK_Complete | 1112893334 | 470 | 1112893334_470
C730K147BC###0020264 | TT_Task | Site Survey Prior to Site Access - Chatswood to Northern Dive - UP/DN TRACK (Program Assumption) | 25/03/2022 | 05/05/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 470 | 1112893334_470
C720P147CF###0030520 | TT_Task | RFQ for secondary suspension | 25/02/2020 | 23/03/2020 | 31/10/2019 | 27/11/2019 | 0 | TK_Complete | 1112893334 | 47 | 1112893334_47
C720P147CF###0030530 | TT_Task | RFQ for primary suspension | 25/02/2020 | 23/03/2020 | 31/10/2019 | 19/11/2019 | 0 | TK_Complete | 1112893334 | 47 | 1112893334_47
C730K147BC###N70890 | TT_Task | ITS Finalization Site Access Inspections Central Station Main Works Contractor' (SIG/CSM) | 25/03/2021 | 23/06/2021 | 17/12/2020 | 17/12/2020 | 0 | TK_Complete | 1112893334 | 469 | 1112893334_469
C730K147BC###N70920 | TT_Task | ITS Finalization Site Access Inspections Tunnel and Station Excavation Works Contractor' (SIG/TSE) | 25/06/2021 | 05/08/2021 | 04/06/2021 | nan | 0 | TK_Active | 1112893334 | 469 | 1112893334_469
C730K147BC###N70940 | TT_Task | ITS Finalization Site Access Inspections Sydenham Station ; Junction Contractor' (CBTC/SSJ) | 25/03/2021 | 23/06/2021 | 30/11/2020 | 30/11/2020 | 0 | TK_Complete | 1112893334 | 469 | 1112893334_469
C730K147BC###N70980 | TT_Task | ITS Finalization Site Access Inspections Signalling System' (LW/SIG) - Line Wide Tunnel Works | 25/06/2021 | 05/08/2021 | 04/06/2021 | nan | 0 | TK_Active | 1112893334 | 469 | 1112893334_469
C730K147BC###N70880 | TT_Task | ITS Finalization Site Access Inspections Martin Place Station (SIG/STME) | 25/02/2022 | 07/04/2022 | 22/02/2022 | 06/03/2022 | 0 | TK_Complete | 1112893334 | 468 | 1112893334_468
C730K147BC###N70900 | TT_Task | ITS Finalization Site Access Inspections Victoria Cross Station (SIG/STME) | 26/07/2021 | 03/09/2021 | 06/07/2021 | 04/08/2021 | 0 | TK_Complete | 1112893334 | 468 | 1112893334_468
C730K147BC###N70910 | TT_Task | ITS Finalization Site Access Inspections Barangaroo Station (SIG/STME) | 25/03/2021 | 23/06/2021 | 25/02/2021 | 25/02/2021 | 0 | TK_Complete | 1112893334 | 468 | 1112893334_468
C730K147BC###N70950 | TT_Task | ITS Finalization Site Access Inspections WLO Station (SIG/STME) | 25/06/2021 | 05/08/2021 | 03/06/2021 | nan | 0 | TK_Active | 1112893334 | 468 | 1112893334_468
C730K147BC###N70960 | TT_Task | ITS Finalization Site Access Inspections PITT St (SIG/STME) | 25/02/2022 | 07/04/2022 | 25/02/2022 | 06/03/2022 | 0 | TK_Complete | 1112893334 | 468 | 1112893334_468
C730K147BC###N70970 | TT_Task | ITS Finalization Site Access Inspections Crows Nest Station (SIG/STME) | 25/03/2022 | 05/05/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 468 | 1112893334_468
C730C147BC###0070344 | TT_Task | SMTF[N] - Decommissioning of existing test track [Refer to MOD007] - WE10 | 03/10/2020 | 04/10/2020 | 05/09/2020 | 06/09/2020 | 0 | TK_Complete | 1112893334 | 467 | 1112893334_467
C730T147BC###N02385 | TT_Task | INS SMTF[N] - Decommissioning of ETT (Existing Test Track) - WE10 | 25/10/2020 | 31/10/2020 | 05/09/2020 | 06/09/2020 | 0 | TK_Complete | 1112893334 | 467 | 1112893334_467
C730T147BC###N02395 | TT_Task | INS SMTF[N] - ETT assests removal and DCS03 ; DCS04 relocation works (WE10) | 25/10/2020 | 31/10/2020 | 05/09/2020 | 06/09/2020 | 0 | TK_Complete | 1112893334 | 467 | 1112893334_467
C730C147BC###N070714 | TT_Task | CAB SMTF[N] - New Test track - Trackside Cable Termination to DSER | 04/03/2021 | 17/03/2021 | 12/02/2021 | 12/02/2021 | 0 | TK_Complete | 1112893334 | 466 | 1112893334_466
C730C147BC###0070264 | TT_Task | SER SMTF[N] - Test Track and Stab 31-35 (Trackside Cable Termination to DSER2) | 17/03/2021 | 30/03/2021 | 08/02/2021 | 25/02/2021 | 0 | TK_Complete | 1112893334 | 466 | 1112893334_466
C730C147BC###0070267 | TT_Task | SER SMTF[N] - Stabling Track 30 - Trackside Cable Termination (moved to MS4) | 22/06/2021 | 05/07/2021 | 14/05/2021 | 28/05/2021 | 0 | TK_Complete | 1112893334 | 466 | 1112893334_466
C730C147BC###0070328 | TT_Task | SER SMTF[N] - Maintenance roads (Rd5-8) (Trackside Cable Termination to DSER1) | 19/08/2021 | 01/09/2021 | 21/06/2021 | 25/06/2021 | 0 | TK_Complete | 1112893334 | 466 | 1112893334_466
C730C147BC###0070392 | TT_Task | SER SMTF[N] - Stab 24-29 (Trackside Cable Termination to DSER2) | 10/11/2021 | 01/12/2021 | 07/05/2021 | 28/05/2021 | 0 | TK_Complete | 1112893334 | 466 | 1112893334_466
C730C147BC###70472 | TT_Task | CAB SMTF[N] - Scissors - Trackside Cable Pulling ; Term [WE12] | 26/09/2020 | 27/09/2020 | 19/09/2020 | 20/09/2020 | 0 | TK_Complete | 1112893334 | 465 | 1112893334_465
C730C147BC###0070192 | TT_Task | CAB SMTF[N] - New Test track - Trackside Cable Pulling ; Term | 08/09/2020 | 15/10/2020 | 20/08/2020 | 29/01/2021 | 0 | TK_Complete | 1112893334 | 465 | 1112893334_465
C730C147BC###0070104 | TT_Task | CAB SMTF[N] - Stab 31-35 - Trackside Cable Pulling ; Term | 26/08/2020 | 07/10/2020 | 13/08/2020 | 19/02/2021 | 0 | TK_Complete | 1112893334 | 465 | 1112893334_465
C730C147BC###0070320 | TT_Task | CAB SMTF[N] - Maintenance tracks (Rd5-8) - Trackside Cable Pulling | 08/06/2021 | 26/07/2021 | 03/05/2021 | 10/06/2021 | 0 | TK_Complete | 1112893334 | 465 | 1112893334_465
C730C147BC###N070722 | TT_Task | CAB SMTF[N] - Maintenance tracks (Rd5-8) - Trackside Cable Term (track) | 29/07/2021 | 18/08/2021 | 01/06/2021 | 24/06/2021 | 0 | TK_Complete | 1112893334 | 465 | 1112893334_465
C730C147BC###0070384 | TT_Task | CAB SMTF[N] - Stab 24-29 - Trackside Cable Pulling ; Term | 26/05/2021 | 29/06/2021 | 17/02/2021 | 07/06/2021 | 0 | TK_Complete | 1112893334 | 465 | 1112893334_465
C730C147BC###0070112 | TT_Task | INS SMTF[N] - Stab 31-35 Trackside Equipment Installation (Signals, AxCo, DCS/CCTV,Balise) | 25/08/2020 | 20/10/2020 | 29/07/2020 | 17/12/2020 | 0 | TK_Complete | 1112893334 | 464 | 1112893334_464
C730C147BC###0070208 | TT_Task | INS SMTF[N] - Stab 31-35 Trackside Equipment Installation (closing works/parts installation) | 21/12/2020 | 22/01/2021 | 16/11/2020 | 19/02/2021 | 0 | TK_Complete | 1112893334 | 464 | 1112893334_464
C730C147BC###N070794 | TT_Task | INS SMTF[N] - Stab 31-35 Trackside Equipment Installation (DCS/CCTV) | 09/11/2020 | 04/12/2020 | 30/09/2020 | 17/12/2020 | 0 | TK_Complete | 1112893334 | 464 | 1112893334_464
C730C147BC###N070795 | TT_Task | INS SMTF[N] - Stab 31-35 Trackside Equipment Installation (Signals, AxCo,Balise) | 25/08/2020 | 21/09/2020 | 29/07/2020 | 17/12/2020 | 0 | TK_Complete | 1112893334 | 464 | 1112893334_464
C730C147BC###N070799 | TT_Task | INS SMTF[N] - Stab 30 Trackside Equipment Installation [Moved to MS4] | 25/03/2021 | 21/04/2021 | 01/03/2021 | 13/05/2021 | 0 | TK_Complete | 1112893334 | 464 | 1112893334_464
C730C147BC###0070376 | TT_Task | INS SMTF[N] - Stab 24-29 - Trackside Equipment Installation | 12/05/2021 | 15/06/2021 | 17/02/2021 | 13/05/2021 | 0 | TK_Complete | 1112893334 | 464 | 1112893334_464
C730C147BC###N704725 | TT_Task | INS SMTF[N] - Scissors Trackside Equipment Installation SAB/AxCo/PM [WE12] | 26/09/2020 | 27/09/2020 | 19/09/2020 | 20/09/2020 | 0 | TK_Complete | 1112893334 | 463 | 1112893334_463
C730C147BC###0070152 | TT_Task | INS SMTF[N] - New test track - Trackside Equipment Installation | 25/08/2020 | 06/10/2020 | 03/08/2020 | 17/12/2020 | 0 | TK_Complete | 1112893334 | 463 | 1112893334_463
C730C147BC###N704920 | TT_Task | INS SMTF[N] - New Test Track Trackside (closing works/parts installation) | 07/05/2021 | 01/06/2021 | 08/03/2021 | 31/03/2021 | 0 | TK_Complete | 1112893334 | 463 | 1112893334_463
C730C147BC###0070312 | TT_Task | INS SMTF[N] - Maintenance tracks (Rd5-8) - Trackside Equipment Installation | 01/06/2021 | 19/07/2021 | 03/05/2021 | 07/07/2021 | 0 | TK_Complete | 1112893334 | 463 | 1112893334_463
C730C157CD###0040670 | TT_Task | INS South Depot - Trackside Equipment | 01/08/2022 | 04/11/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 463 | 1112893334_463
C730C147BC###0070248 | TT_Task | SER SMTF[N] - CER2 installation Summary | 07/01/2021 | 24/02/2021 | 01/12/2020 | 31/03/2021 | 0 | TK_Complete | 1112893334 | 462 | 1112893334_462
C730C147BC###N070745 | TT_Task | SER SMTF[N] - CER2 installation Containment works/preparation | 07/01/2021 | 27/01/2021 | 01/12/2020 | 11/12/2020 | 0 | TK_Complete | 1112893334 | 462 | 1112893334_462
C730C147BC###N070778 | TT_Task | SER SMTF[N] - CER2 installation Cubicles | 01/01/2021 | 28/01/2021 | 05/12/2020 | 26/03/2021 | 0 | TK_Complete | 1112893334 | 462 | 1112893334_462
C730C147BC###N070715 | TT_Task | SER SMTF[N] - CER2 installation Cable pull | 03/03/2021 | 18/03/2021 | 04/01/2021 | 31/03/2021 | 0 | TK_Complete | 1112893334 | 462 | 1112893334_462
C730C147BC###N070719 | TT_Task | SER SMTF[N] - CER2 installation Cable termination | 03/05/2021 | 14/05/2021 | 15/03/2021 | 31/03/2021 | 0 | TK_Complete | 1112893334 | 462 | 1112893334_462
C730C147BC###0070240 | TT_Task | SER SMTF[N] - DSER1/DCC1 Cabling Works (Partial) [Off-peak] | 26/10/2020 | 06/11/2020 | 02/10/2020 | 24/10/2020 | 0 | TK_Complete | 1112893334 | 461 | 1112893334_461
C730C147BC###70482 | TT_Task | CAB SMTF[N] - Scissors - Remaining MS1 Works | 26/10/2020 | 27/10/2020 | 17/10/2020 | 20/11/2020 | 0 | TK_Complete | 1112893334 | 461 | 1112893334_461
C730C147BC###N470482 | TT_Task | CAB SMTF[N] - New Test track - Preparation Works | 08/09/2020 | 15/10/2020 | 10/08/2020 | 12/08/2020 | 0 | TK_Complete | 1112893334 | 461 | 1112893334_461
C730C147BC###N070492 | TT_Task | CAB SMTF[N] - Stab 31-35 - Preparation Works | 16/10/2020 | 26/11/2020 | 10/08/2020 | 12/08/2020 | 0 | TK_Complete | 1112893334 | 461 | 1112893334_461
C730C147BC###N070759 | TT_Task | SER SMTF[N] - DSER1/DCC1 modification [WE08 Possession] Containment Works/preparation | 29/08/2020 | 13/09/2020 | 22/08/2020 | 23/08/2020 | 0 | TK_Complete | 1112893334 | 460 | 1112893334_460
C730C147BC###N870502 | TT_Task | SER SMTF[N] - DSER1/DCC1 Migration 0.1 works [WE10 Possession] | 26/09/2020 | 27/09/2020 | 05/09/2020 | 06/09/2020 | 0 | TK_Complete | 1112893334 | 460 | 1112893334_460
C730T147BC###0050130 | TT_Task | SMTF[N] Stage2 - Re-work ; testing of AxCo DSER-1 [WE35 possession works] | 25/02/2022 | 27/02/2022 | 25/02/2022 | 26/02/2022 | 0 | TK_Complete | 1112893334 | 460 | 1112893334_460
C720P147CF###0030680 | TT_Task | RFQ for auxilary converter (CVS) | 25/02/2020 | 02/03/2020 | 31/10/2019 | 06/11/2019 | 0 | TK_Complete | 1112893334 | 46 | 1112893334_46
C720P147CF###0030910 | TT_Task | BA Auxilary convertor (CVS) | 25/02/2020 | 18/03/2020 | 05/12/2019 | 10/12/2019 | 0 | TK_Complete | 1112893334 | 46 | 1112893334_46
C720P147CF###0030990 | TT_Task | PO Auxilary convertor (CVS) | 25/02/2020 | 16/03/2020 | 11/12/2019 | 17/12/2019 | 0 | TK_Complete | 1112893334 | 46 | 1112893334_46
C720P147CF###0031070 | TT_Task | Production Auxilary converter (CVS) | 27/04/2020 | 08/12/2020 | 31/03/2020 | 23/10/2020 | 0 | TK_Complete | 1112893334 | 46 | 1112893334_46
C730C147BC###0070176 | TT_Task | SER SMTF[N] - DSER2 (internal wiring) | 26/10/2020 | 18/12/2020 | 02/10/2020 | 19/02/2021 | 0 | TK_Complete | 1112893334 | 459 | 1112893334_459
C730C147BC###N070086 | TT_Task | SER SMTF[N] - DSER2 (internal wiring) MS1 Wiring (covered in DSER1 works) | 25/11/2020 | 08/12/2020 | 25/10/2020 | 25/10/2020 | 0 | TK_Complete | 1112893334 | 459 | 1112893334_459
C730C147BC###N070088 | TT_Task | SER SMTF[N] - DSER2 (internal wiring) FO Cable | 12/03/2021 | 25/03/2021 | 08/02/2021 | 19/02/2021 | 0 | TK_Complete | 1112893334 | 459 | 1112893334_459
C730C147BC###N070194 | TT_Task | SER SMTF[N] - DSER2 (internal wiring) MS4 Wiring/Cabling Works | 31/05/2021 | 11/06/2021 | 15/03/2021 | 28/05/2021 | 0 | TK_Complete | 1112893334 | 459 | 1112893334_459
C730C147BC###N070742 | TT_Task | SER SMTF[N] - DSER1/DCC1 modification wiring | 25/11/2020 | 26/11/2020 | 21/11/2020 | 22/11/2020 | 0 | TK_Complete | 1112893334 | 459 | 1112893334_459
C730C147BC###N870542 | TT_Task | SER SMTF[N] - DSER1 Internal MS4 Wiring works | 01/06/2021 | 02/06/2021 | 03/05/2021 | 07/07/2021 | 0 | TK_Complete | 1112893334 | 459 | 1112893334_459
C730C147BC###R070098 | TT_Task | SER SMTF[N] - ITSP Checks (Rework) | 19/08/2020 | 01/09/2020 | 15/07/2020 | 30/09/2020 | 0 | TK_Complete | 1112893334 | 458 | 1112893334_458
C730C147BC###R070088 | TT_Task | INS SMTF[N] - Stab 31-35 ITSP Checks (Rework) | 19/08/2020 | 01/09/2020 | 15/07/2020 | 28/07/2020 | 0 | TK_Complete | 1112893334 | 458 | 1112893334_458
C730C147BC###R070099 | TT_Task | INS SMTF[N] - New test track - ITSP Checks (Rework) | 15/10/2020 | 28/10/2020 | 15/07/2020 | 28/07/2020 | 0 | TK_Complete | 1112893334 | 458 | 1112893334_458
C730C147BC###N070482 | TT_Task | SER SMTF[N] - DSER2 Undefloor Cable Containment (pre-degree2) | 08/09/2020 | 01/12/2020 | 30/07/2020 | 07/08/2020 | 0 | TK_Complete | 1112893334 | 457 | 1112893334_457
C730C147BC###0070280 | TT_Task | INS SMTF[N] - DSER1 remaining cable termination - [Off-peak] | 25/11/2020 | 01/12/2020 | 21/11/2020 | 22/11/2020 | 0 | TK_Complete | 1112893334 | 457 | 1112893334_457
C730C147BC###N070755 | TT_Task | INS SMTF[N] - DSER1 Remaining cable pulling - [Off-peak] | 02/11/2020 | 06/11/2020 | 24/10/2020 | 20/11/2020 | 0 | TK_Complete | 1112893334 | 457 | 1112893334_457
C730C147BC###0070096 | TT_Task | SER SMTF[N] - DSER2 (cubicles) Summary activity | 26/10/2020 | 22/01/2021 | 01/10/2020 | 19/02/2021 | 0 | TK_Complete | 1112893334 | 456 | 1112893334_456
C730C147BC###0070256 | TT_Task | SER SMTF[N] - DSER2 - Remaining Works MS4 Cubicles | 25/03/2021 | 14/04/2021 | 01/03/2021 | 21/05/2021 | 0 | TK_Complete | 1112893334 | 456 | 1112893334_456
C730C147BC###N070092 | TT_Task | SER SMTF[N] - DSER2 (cubicles) preparation works (w/o Degree2) | 19/08/2020 | 03/09/2020 | 15/07/2020 | 21/07/2020 | 0 | TK_Complete | 1112893334 | 456 | 1112893334_456
C730C147BC###N070094 | TT_Task | SER SMTF[N] - DSER2 (cubicles) containment works/preparation | 26/10/2020 | 10/11/2020 | 01/10/2020 | 08/10/2020 | 0 | TK_Complete | 1112893334 | 456 | 1112893334_456
C730C147BC###N070095 | TT_Task | SER SMTF[N] - DSER2 (cubicles) Room Cubicles MS2 Cubicles | 26/10/2020 | 18/11/2020 | 02/10/2020 | 19/02/2021 | 0 | TK_Complete | 1112893334 | 456 | 1112893334_456
C730C147BC###N870482 | TT_Task | SER SMTF[N] - DSER1/DCC1 Cubicles/Containment for MS1 [Off-Peak] | 26/10/2020 | 13/11/2020 | 28/09/2020 | 20/11/2020 | 0 | TK_Complete | 1112893334 | 456 | 1112893334_456
C730C147BC###N870532 | TT_Task | SER SMTF[N] - DSER1 Remaining MS4 Cubicles | 25/03/2021 | 01/04/2021 | 01/03/2021 | 07/07/2021 | 0 | TK_Complete | 1112893334 | 456 | 1112893334_456
C730C147BC###0070336 | TT_Task | SMTF[N] - Maintenance roads readiness for first Train Static Test (link to RS) | 16/08/2021 | 16/08/2021 | 21/06/2021 | 21/06/2021 | 0 | TK_Complete | 1112893334 | 455 | 1112893334_455
C720T147CF###N51530 | TT_Task | Train 01 Validation tests (Scope transfer from Sri city to SMTF-N Depot) ***Mitigated as per EoT02 closure agreement*** | 30/12/2021 | 30/12/2021 | 25/08/2021 | 25/08/2021 | 0 | TK_Complete | 1112893334 | 455 | 1112893334_455
C730C147BC###0070048 | TT_Task | Work permit obtain, handover docs review for SMTF[N] Depot New Test Track | 27/07/2020 | 21/08/2020 | 15/06/2020 | 15/07/2020 | 0 | TK_Complete | 1112893334 | 454 | 1112893334_454
C730C147BC###0070056 | TT_Task | Work permit obtain, handover docs review for SMTF[N] Depot Stabling roads (30-35) | 27/07/2020 | 21/08/2020 | 15/06/2020 | 15/07/2020 | 0 | TK_Complete | 1112893334 | 454 | 1112893334_454
C730C147BC###0070064 | TT_Task | Work permit obtain, handover docs review for SMTF[N] Depot DSER2 | 27/07/2020 | 21/08/2020 | 15/06/2020 | 15/07/2020 | 0 | TK_Complete | 1112893334 | 454 | 1112893334_454
C730C147BC###0070232 | TT_Task | Work permit obtain, handover docs review for SMTF[N] Depot CER2 | 25/11/2020 | 22/12/2020 | 10/11/2020 | 30/11/2020 | 0 | TK_Complete | 1112893334 | 454 | 1112893334_454
C730C147BC###0070304 | TT_Task | Work permit obtain, handover docs review for SMTF[N] Depot Maintenance roads (5-8) | 26/04/2021 | 21/05/2021 | 20/04/2021 | 03/05/2021 | 0 | TK_Complete | 1112893334 | 454 | 1112893334_454
C730C147BC###0070368 | TT_Task | Work permit obtain, handover docs review for SMTF[N] Depot Stabling roads (24-29) | 25/02/2021 | 24/03/2021 | 04/02/2021 | 19/02/2021 | 0 | TK_Complete | 1112893334 | 454 | 1112893334_454
C730C147BC###0070040 | TT_Task | Site Survey prior to access + closure of issue (if needed) SMTF[N] Depot Stabling roads (30-35) | 25/06/2020 | 22/07/2020 | 15/06/2020 | 15/07/2020 | 0 | TK_Complete | 1112893334 | 453 | 1112893334_453
C730C147BC###0070296 | TT_Task | Site Survey prior to access + closure of issue (if needed) SMTF[N] Depot Maintenance roads (5-8) | 31/03/2021 | 27/04/2021 | 04/02/2021 | 16/04/2021 | 0 | TK_Complete | 1112893334 | 453 | 1112893334_453
C730C147BC###0070360 | TT_Task | Site Survey prior to access + closure of issue (if needed) SMTF[N] Depot Stabling roads (24-29) | 25/02/2021 | 24/03/2021 | 04/02/2021 | 26/02/2021 | 0 | TK_Complete | 1112893334 | 453 | 1112893334_453
C730C147BC###0070000 | TT_Task | Provision of work area + pre-requisites for SMTF[N] Depot DSER2 | 25/07/2020 | 25/07/2020 | 15/07/2020 | 15/07/2020 | 0 | TK_Complete | 1112893334 | 452 | 1112893334_452
C730C147BC###0070008 | TT_Task | Provision of work area + pre-requisites for SMTF[N] Depot New Test Track | 25/07/2020 | 25/07/2020 | 15/07/2020 | 15/07/2020 | 0 | TK_Complete | 1112893334 | 452 | 1112893334_452
C730C147BC###0070016 | TT_Task | Provision of work area + pre-requisites for SMTF[N] Depot Stabling roads (30-35) | 25/07/2020 | 25/07/2020 | 15/07/2020 | 15/07/2020 | 0 | TK_Complete | 1112893334 | 452 | 1112893334_452
C730C147BC###0070216 | TT_Task | Provision of work area + pre-requisites for SMTF[N] Depot CER2 | 25/01/2021 | 25/01/2021 | 01/12/2020 | 01/12/2020 | 0 | TK_Complete | 1112893334 | 452 | 1112893334_452
C730C147BC###0070288 | TT_Task | Provision of work area + pre-requisites for SMTF[N] Depot Maintenance roads (5-8) | 31/03/2021 | 31/03/2021 | 03/02/2021 | 03/02/2021 | 0 | TK_Complete | 1112893334 | 452 | 1112893334_452
C730C147BC###0070352 | TT_Task | Provision of work area + pre-requisites for SMTF[N] Depot Stabling roads (24-29) | 26/09/2021 | 26/09/2021 | 03/02/2021 | 03/02/2021 | 0 | TK_Complete | 1112893334 | 452 | 1112893334_452
C730P147CT###0031220 | TT_Task | Room Deliver Cable Sydenham- OCC / CER | 11/10/2021 | 03/12/2021 | 01/07/2021 | 25/08/2021 | 0 | TK_Complete | 1112893334 | 451 | 1112893334_451
C730P147CT###0031020 | TT_Task | Room Deliver Cable SMTF[S] - DSER | 11/10/2021 | 03/12/2021 | 28/07/2021 | 25/08/2021 | 0 | TK_Complete | 1112893334 | 451 | 1112893334_451
C730P147CT###N033269 | TT_Task | Room Delivery Category B Materials Chatswood Station SER ***N/A*** | 18/04/2022 | 27/05/2022 | 24/03/2022 | 24/03/2022 | 0 | TK_Complete | 1112893334 | 450 | 1112893334_450
C730P147CT###N033289 | TT_Task | Room Delivery Category B Materials CST SER | 02/05/2022 | 10/06/2022 | nan | nan | 320 | TK_NotStart | 1112893334 | 450 | 1112893334_450
C730P147CT###N333309 | TT_Task | Room Delivery Category B Materials Barangaroo Station SER | 02/05/2022 | 10/06/2022 | nan | nan | 280 | TK_NotStart | 1112893334 | 450 | 1112893334_450
C730P147CT###N333329 | TT_Task | Room Delivery Category B Materials MPL SER | 02/05/2022 | 10/06/2022 | nan | nan | 616 | TK_NotStart | 1112893334 | 450 | 1112893334_450
C730P147CT###N333349 | TT_Task | Room Delivery Category B Materials PIT SER | 02/05/2022 | 10/06/2022 | nan | nan | 376 | TK_NotStart | 1112893334 | 450 | 1112893334_450
C730P147CT###N533369 | TT_Task | Room Delivery Category B Materials CSM SER | 17/05/2022 | 27/06/2022 | nan | nan | 320 | TK_NotStart | 1112893334 | 450 | 1112893334_450
C730P147CT###N533389 | TT_Task | Room Delivery Category B Materials WLO SER | 02/05/2022 | 10/06/2022 | nan | nan | 496 | TK_NotStart | 1112893334 | 450 | 1112893334_450
C730P147CT###N633409 | TT_Task | Room Delivery Category B Materials SYD SER | 18/04/2022 | 27/05/2022 | nan | nan | 48 | TK_NotStart | 1112893334 | 450 | 1112893334_450
C730P147CT###N533429 | TT_Task | Room Delivery Category B Materials VIC SER | 02/05/2022 | 10/06/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 450 | 1112893334_450
C730P147CT###N233449 | TT_Task | Room Delivery Category B Materials SMTFS SER | 18/04/2022 | 27/05/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 450 | 1112893334_450
C720P147CF###0030650 | TT_Task | RFQ for traction converter | 25/02/2020 | 02/03/2020 | 31/10/2019 | 06/11/2019 | 0 | TK_Complete | 1112893334 | 45 | 1112893334_45
C720P147CF###0030450 | TT_Task | RFQ for traction motor | 25/02/2020 | 23/03/2020 | 31/10/2019 | 27/11/2019 | 0 | TK_Complete | 1112893334 | 45 | 1112893334_45
C720P147CF###0030490 | TT_Task | RFQ for wheels | 25/02/2020 | 23/03/2020 | 31/10/2019 | 03/12/2019 | 0 | TK_Complete | 1112893334 | 45 | 1112893334_45
C720P147CF###0030600 | TT_Task | RFQ for axle box ; bearing | 25/02/2020 | 23/03/2020 | 31/10/2019 | 03/12/2019 | 0 | TK_Complete | 1112893334 | 45 | 1112893334_45
C720P147CF###0030660 | TT_Task | RFQ for axles | 25/02/2020 | 23/03/2020 | 31/10/2019 | 21/11/2019 | 0 | TK_Complete | 1112893334 | 45 | 1112893334_45
C730P147CT###0031160 | TT_Task | Transportation to Work Area Trainborne Signalling ; CCTV- Train 1, 2 ; 3 | 25/11/2020 | 23/01/2021 | 30/10/2020 | 25/12/2020 | 0 | TK_Complete | 1112893334 | 449 | 1112893334_449
C730P147CT###0031240 | TT_Task | Transportation to Work Area Trainborne Signalling ; CCTV- Train 4 ; 5 | 09/04/2021 | 07/06/2021 | 22/02/2021 | 09/03/2021 | 0 | TK_Complete | 1112893334 | 449 | 1112893334_449
C730P147CT###0031440 | TT_Task | Transportation to Work Area Trainborne Signalling ; CCTV - Train 6 ; 7 | 12/06/2021 | 26/06/2021 | 10/05/2021 | 06/08/2021 | 0 | TK_Complete | 1112893334 | 449 | 1112893334_449
C730P147CT###0031530 | TT_Task | Transportation to Work Area Trainborne Signalling ; CCTV - Train 8 ; 9 | 25/08/2021 | 08/09/2021 | 09/08/2021 | 10/08/2021 | 0 | TK_Complete | 1112893334 | 449 | 1112893334_449
C730P147CT###0031610 | TT_Task | Transportation to Work Area Trainborne Signalling ; CCTV - Train 10 ; 11 | 25/12/2021 | 08/01/2022 | 18/10/2021 | 19/10/2021 | 0 | TK_Complete | 1112893334 | 449 | 1112893334_449
C730P147CT###0031730 | TT_Task | Transportation to Work Area Trainborne Signalling ; CCTV - Train 12 ; 13 | 24/01/2022 | 24/03/2022 | 28/09/2021 | 29/09/2021 | 0 | TK_Complete | 1112893334 | 449 | 1112893334_449
C730P147CT###0031800 | TT_Task | Transportation to Work Area Trainborne Signalling ; CCTV - Train 14 ; 15 | 23/02/2022 | 23/04/2022 | 19/10/2021 | 20/10/2021 | 0 | TK_Complete | 1112893334 | 449 | 1112893334_449
C730P147CT###0031850 | TT_Task | Transportation to Work Area Trainborne Signalling ; CCTV - Train 16 ; 17 | 25/03/2022 | 23/05/2022 | 20/10/2021 | 21/10/2021 | 0 | TK_Complete | 1112893334 | 449 | 1112893334_449
C730P147CT###0031940 | TT_Task | Transportation to Work Area Trainborne Signalling ; CCTV - Train 18 ; 19 | 24/04/2022 | 22/06/2022 | 26/10/2021 | 26/10/2021 | 0 | TK_Complete | 1112893334 | 449 | 1112893334_449
C730P147CT###0031980 | TT_Task | Transportation to Work Area Trainborne Signalling ; CCTV - Train 20 ; 21 | 24/05/2022 | 22/07/2022 | 23/12/2021 | 24/12/2021 | 0 | TK_Complete | 1112893334 | 449 | 1112893334_449
C730P147CT###0032020 | TT_Task | Transportation to Work Area Trainborne Signalling ; CCTV - Train 22 ; 23 | 25/03/2022 | 23/05/2022 | 28/02/2022 | 28/02/2022 | 0 | TK_Complete | 1112893334 | 449 | 1112893334_449
C730P147CT###0031170 | TT_Task | Warehousing Trainborne Signalling ; CCTV - Train 1, 2 ; 3 | 25/11/2020 | 02/12/2020 | 30/10/2020 | 06/11/2020 | 0 | TK_Complete | 1112893334 | 448 | 1112893334_448
C730P147CT###0031230 | TT_Task | Warehousing Trainborne Signalling ; CCTV - Train 4 ; 5 - ***N/A | 01/04/2021 | 08/04/2021 | 19/02/2021 | 19/02/2021 | 0 | TK_Complete | 1112893334 | 448 | 1112893334_448
C730P147CT###0031270 | TT_Task | Warehousing Trainborne Signalling ; CCTV - Train 6 ; 7 - ***N/A | 14/05/2021 | 21/05/2021 | 25/03/2021 | 25/03/2021 | 0 | TK_Complete | 1112893334 | 448 | 1112893334_448
C730P147CT###0031330 | TT_Task | Warehousing Trainborne Signalling ; CCTV - Train 8 ; 9 | 25/05/2021 | 01/06/2021 | 10/05/2021 | 14/05/2021 | 0 | TK_Complete | 1112893334 | 448 | 1112893334_448
C730P147CT###0031430 | TT_Task | Warehousing Trainborne Signalling ; CCTV - Train 10 ; 11 | 04/10/2021 | 11/10/2021 | 01/10/2021 | 15/10/2021 | 0 | TK_Complete | 1112893334 | 448 | 1112893334_448
C730P147CT###0031510 | TT_Task | Warehousing Trainborne Signalling ; CCTV - Train 12 ; 13 | 08/11/2021 | 15/11/2021 | 01/10/2021 | 15/10/2021 | 0 | TK_Complete | 1112893334 | 448 | 1112893334_448
C730P147CT###0031620 | TT_Task | Warehousing Trainborne Signalling ; CCTV - Train 14 ; 15 | 06/12/2021 | 13/12/2021 | 01/10/2021 | 15/10/2021 | 0 | TK_Complete | 1112893334 | 448 | 1112893334_448
C730P147CT###0031810 | TT_Task | Warehousing Trainborne Signalling ; CCTV - Train 16 ; 17 | 01/10/2021 | 08/10/2021 | 01/10/2021 | 15/10/2021 | 0 | TK_Complete | 1112893334 | 448 | 1112893334_448
C730P147CT###0031840 | TT_Task | Warehousing Trainborne Signalling ; CCTV - Train 18 ; 19 | 31/01/2022 | 07/02/2022 | 01/10/2021 | 15/10/2021 | 0 | TK_Complete | 1112893334 | 448 | 1112893334_448
C730P147CT###0031890 | TT_Task | Warehousing Trainborne Signalling ; CCTV - Train 20 ; 21 | 27/12/2021 | 03/01/2022 | 16/12/2021 | 23/12/2021 | 0 | TK_Complete | 1112893334 | 448 | 1112893334_448
C730P147CT###0031970 | TT_Task | Warehousing Trainborne Signalling ; CCTV - Train 22 ; 23 | 25/01/2022 | 01/02/2022 | 12/01/2022 | 12/01/2022 | 0 | TK_Complete | 1112893334 | 448 | 1112893334_448
C730P147CT###0031180 | TT_Task | FAT / FAI (Trainborne Signalling ; CCTV) - Train 1, 2 ; 3 | 26/10/2020 | 20/11/2020 | 28/09/2020 | 29/10/2020 | 0 | TK_Complete | 1112893334 | 447 | 1112893334_447
C730P147CT###0031200 | TT_Task | FAT (Trainborne Signalling ; CCTV) - Train 4 ; 5 | 25/02/2021 | 24/03/2021 | 10/02/2021 | 19/02/2021 | 0 | TK_Complete | 1112893334 | 447 | 1112893334_447
C730P147CT###0031260 | TT_Task | FAT (Trainborne Signalling ; CCTV) - Train 6 ; 7 | 17/05/2021 | 11/06/2021 | 23/04/2021 | 30/04/2021 | 0 | TK_Complete | 1112893334 | 447 | 1112893334_447
C730P147CT###0031290 | TT_Task | FAT (Trainborne Signalling ; CCTV) - Train 8 ; 9 | 19/07/2021 | 13/08/2021 | 23/04/2021 | 07/05/2021 | 0 | TK_Complete | 1112893334 | 447 | 1112893334_447
C730P147CT###0031340 | TT_Task | FAT (Trainborne Signalling ; CCTV) - Train 10 ; 11 | 25/05/2021 | 21/06/2021 | 24/05/2021 | 30/09/2021 | 0 | TK_Complete | 1112893334 | 447 | 1112893334_447
C730P147CT###0031420 | TT_Task | FAT (Trainborne Signalling ; CCTV) - Train 12 ; 13 | 11/10/2021 | 05/11/2021 | 28/09/2021 | 30/09/2021 | 0 | TK_Complete | 1112893334 | 447 | 1112893334_447
C730P147CT###0031600 | TT_Task | FAT (Trainborne Signalling ; CCTV) - Train 14 ; 15 | 21/10/2021 | 17/11/2021 | 28/09/2021 | 30/09/2021 | 0 | TK_Complete | 1112893334 | 447 | 1112893334_447
C730P147CT###0031750 | TT_Task | FAT (Trainborne Signalling ; CCTV) - Train 16 ; 17 | 28/10/2021 | 24/11/2021 | 28/09/2021 | 30/09/2021 | 0 | TK_Complete | 1112893334 | 447 | 1112893334_447
C730P147CT###0031830 | TT_Task | FAT (Trainborne Signalling ; CCTV) - Train 18 ; 19 | 25/10/2021 | 19/11/2021 | 25/10/2021 | 04/11/2021 | 0 | TK_Complete | 1112893334 | 447 | 1112893334_447
C730P147CT###0031880 | TT_Task | FAT (Trainborne Signalling ; CCTV) - Train 20 ; 21 | 01/11/2021 | 26/11/2021 | 01/11/2021 | 11/11/2021 | 0 | TK_Complete | 1112893334 | 447 | 1112893334_447
C730P147CT###0031950 | TT_Task | FAT (Trainborne Signalling ; CCTV) - Train 22 ; 23 | 25/01/2022 | 21/02/2022 | 24/12/2021 | 12/01/2022 | 0 | TK_Complete | 1112893334 | 447 | 1112893334_447
C730P147CT###0030350 | TT_Task | Production (Trainborne Signalling ; CCTV) - Train 1, 2 ; 3 | 25/05/2020 | 22/12/2020 | 27/04/2020 | 26/10/2020 | 0 | TK_Complete | 1112893334 | 446 | 1112893334_446
C730P147CT###0030640 | TT_Task | Production (Trainborne Signalling ; CCTV) - Train 4 ; 5 | 26/10/2020 | 28/05/2021 | 01/10/2020 | 09/12/2020 | 0 | TK_Complete | 1112893334 | 446 | 1112893334_446
C730P147CT###0030660 | TT_Task | Production (Trainborne Signalling ; CCTV) - Train 6 ; 7 | 25/01/2021 | 28/05/2021 | 01/01/2021 | 16/04/2021 | 0 | TK_Complete | 1112893334 | 446 | 1112893334_446
C730P147CT###0030670 | TT_Task | Production (Trainborne Signalling ; CCTV) - Train 8 ; 9 | 25/02/2021 | 30/06/2021 | 12/02/2021 | 23/04/2021 | 0 | TK_Complete | 1112893334 | 446 | 1112893334_446
C730P147CT###0030710 | TT_Task | Production (Trainborne Signalling ; CCTV) - Train 10 ; 11 | 26/04/2021 | 27/08/2021 | 05/04/2021 | 24/05/2021 | 0 | TK_Complete | 1112893334 | 446 | 1112893334_446
C730P147CT###0030720 | TT_Task | Production (Trainborne Signalling ; CCTV) - Train 12 ; 13 | 07/06/2021 | 08/10/2021 | 19/04/2021 | 27/09/2021 | 0 | TK_Complete | 1112893334 | 446 | 1112893334_446
C730P147CT###0030820 | TT_Task | Production (Trainborne Signalling ; CCTV) - Train 14 ; 15 | 31/05/2021 | 01/10/2021 | 17/05/2021 | 27/09/2021 | 0 | TK_Complete | 1112893334 | 446 | 1112893334_446
C730P147CT###0031210 | TT_Task | Production (Trainborne Signalling ; CCTV) - Train 16 ; 17 | 12/07/2021 | 12/11/2021 | 24/05/2021 | 27/09/2021 | 0 | TK_Complete | 1112893334 | 446 | 1112893334_446
C730P147CT###0031280 | TT_Task | Production (Trainborne Signalling ; CCTV) - Train 18 ; 19 | 26/07/2021 | 26/11/2021 | 05/07/2021 | 27/09/2021 | 0 | TK_Complete | 1112893334 | 446 | 1112893334_446
C730P147CT###0031410 | TT_Task | Production (Trainborne Signalling ; CCTV) - Train 20 ; 21 | 25/08/2021 | 28/12/2021 | 23/08/2021 | 26/10/2021 | 0 | TK_Complete | 1112893334 | 446 | 1112893334_446
C730P147CT###0031450 | TT_Task | Production (Trainborne Signalling ; CCTV) - Train 22 ; 23 | 25/10/2021 | 06/12/2021 | 25/10/2021 | 06/12/2021 | 0 | TK_Complete | 1112893334 | 446 | 1112893334_446
C730P147CT###0031100 | TT_Task | Room FAT Cable Barangaroo Station SER | 20/12/2021 | 14/01/2022 | 28/06/2021 | 30/06/2021 | 0 | TK_Complete | 1112893334 | 445 | 1112893334_445
C730P147CT###0031120 | TT_Task | Room FAT Cable Pitt Street Station SER | 20/12/2021 | 14/01/2022 | 28/06/2021 | 30/06/2021 | 0 | TK_Complete | 1112893334 | 445 | 1112893334_445
C730P147CT###0031320 | TT_Task | Room Deliver Cable Chatswood Station SER | 20/12/2021 | 11/02/2022 | 01/07/2021 | 25/08/2021 | 0 | TK_Complete | 1112893334 | 445 | 1112893334_445
C730P147CT###0031490 | TT_Task | Room Deliver Cable Barangaroo Station SER | 17/01/2022 | 11/03/2022 | 01/07/2021 | 25/08/2021 | 0 | TK_Complete | 1112893334 | 445 | 1112893334_445
C730P147CT###0031570 | TT_Task | Room Deliver Cable Martin Place Station SER | 17/01/2022 | 11/03/2022 | 01/07/2021 | 25/08/2021 | 0 | TK_Complete | 1112893334 | 445 | 1112893334_445
C730P147CT###0031580 | TT_Task | Room Deliver Cable Pitt Street Station SER | 17/01/2022 | 11/03/2022 | 01/07/2021 | 25/08/2021 | 0 | TK_Complete | 1112893334 | 445 | 1112893334_445
C730P147CT###0031670 | TT_Task | Room Deliver Cable Central Station SER | 24/01/2022 | 18/03/2022 | 01/07/2021 | 25/08/2021 | 0 | TK_Complete | 1112893334 | 445 | 1112893334_445
C730P147CT###0031680 | TT_Task | Room Deliver Cable Waterloo Station SER | 24/01/2022 | 18/03/2022 | 01/07/2021 | 25/08/2021 | 0 | TK_Complete | 1112893334 | 445 | 1112893334_445
C730P147CT###0031770 | TT_Task | Room Deliver Cable Sydenham Station SER | 11/10/2021 | 03/12/2021 | 01/07/2021 | 25/08/2021 | 0 | TK_Complete | 1112893334 | 445 | 1112893334_445
C730P147CT###0031480 | TT_Task | Room Deliver Cable VIC SER | 10/01/2022 | 04/03/2022 | 01/07/2021 | 25/08/2021 | 0 | TK_Complete | 1112893334 | 445 | 1112893334_445
C730P147CT###0031080 | TT_Task | Room FAT Cable Crows Nest Station SER | 06/12/2021 | 31/12/2021 | 28/06/2021 | 30/06/2021 | 0 | TK_Complete | 1112893334 | 444 | 1112893334_444
C730P147CT###0031350 | TT_Task | Room Deliver Cable Crows Nest Station SER (Category-A) | 03/01/2022 | 25/02/2022 | 01/07/2021 | 25/08/2021 | 0 | TK_Complete | 1112893334 | 444 | 1112893334_444
C730P147CT###0031380 | TT_Task | Room Production Work Station + Furnitures Barangaroo Station SCR | 25/02/2022 | 19/05/2022 | 07/02/2022 | 23/02/2022 | 0 | TK_Complete | 1112893334 | 443 | 1112893334_443
C730P147CT###0030650 | TT_Task | Room Production Work Station + Furnitures SMTF[S] - SCR | 25/08/2021 | 25/01/2022 | 20/08/2021 | 23/02/2022 | 0 | TK_Complete | 1112893334 | 443 | 1112893334_443
C730P147CT###0031710 | TT_Task | Room Deliver Work Station + Furnitures Barangaroo Station SCR | 25/02/2022 | 21/04/2022 | 23/02/2022 | nan | 0 | TK_Active | 1112893334 | 443 | 1112893334_443
C730P147CT###0032140 | TT_Task | Room Deliver Work Station + Furnitures SMTF[S] - SCR | 04/04/2022 | 27/05/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 443 | 1112893334_443
C730P147CT###N033469 | TT_Task | Room Production Cubicles Victoria Cross Station (Category B- ST3 driven) | 25/03/2022 | 01/09/2022 | 28/02/2022 | nan | 0 | TK_Active | 1112893334 | 442 | 1112893334_442
C730P147CT###N053469 | TT_Task | Room Production Cubicles Martin Place Station (Category B- ST3 driven) | 28/02/2022 | 05/08/2022 | 28/02/2022 | nan | 0 | TK_Active | 1112893334 | 442 | 1112893334_442
C730P147CT###N033479 | TT_Task | Room Production Cubicles Pitt Street Station (Category B- ST3 driven) | 28/02/2022 | 01/07/2022 | 28/02/2022 | nan | 0 | TK_Active | 1112893334 | 442 | 1112893334_442
C730P147CT###N233459 | TT_Task | Room Production Cubicles Central Station (Category B- ST3 driven) | 16/02/2022 | 26/07/2022 | 28/02/2022 | nan | 0 | TK_Active | 1112893334 | 442 | 1112893334_442
C730P147CT###33459 | TT_Task | Room Production Cubicles Waterloo Station (Category B- ST3 driven) | 28/02/2022 | 01/07/2022 | 28/02/2022 | nan | 0 | TK_Active | 1112893334 | 442 | 1112893334_442
C730P147CT###0030430 | TT_Task | Room Production All Cubicles Crows Nest Station SER (Category-A) | 26/07/2021 | 07/01/2022 | 28/06/2021 | 03/03/2022 | 0 | TK_Complete | 1112893334 | 441 | 1112893334_441
C730P147CT###N033459 | TT_Task | Room Production of Cubicles Crows Nest Station (Category B- ST3 driven) | 18/04/2022 | 19/08/2022 | 28/02/2022 | nan | 0 | TK_Active | 1112893334 | 441 | 1112893334_441
C730P147CT###0030900 | TT_Task | Room FAT All Cubicles Crows Nest Station SER | 25/02/2022 | 24/03/2022 | 03/03/2022 | 07/03/2022 | 0 | TK_Complete | 1112893334 | 441 | 1112893334_441
C730P147CT###0031310 | TT_Task | Room Deliver All Cubicles Crows Nest Station SER | 25/02/2022 | 21/04/2022 | 07/03/2022 | nan | 0 | TK_Active | 1112893334 | 441 | 1112893334_441
C730P147CT###0031060 | TT_Task | Trackside FAT Boxes | 26/08/2021 | 08/09/2021 | 03/04/2021 | 10/04/2021 | 0 | TK_Complete | 1112893334 | 440 | 1112893334_440
C730P147CT###0031250 | TT_Task | Trackside Deliver Boxes [First Batch] | 09/09/2021 | 03/11/2021 | 12/04/2021 | 21/05/2021 | 0 | TK_Complete | 1112893334 | 440 | 1112893334_440
C720P147CF###0030640 | TT_Task | RFQ for battery ; battery box | 25/02/2020 | 11/03/2020 | 31/10/2019 | 19/12/2019 | 0 | TK_Complete | 1112893334 | 44 | 1112893334_44
C730D157BC###0017840 | TT_Task | RFQ, BA, and PO SMTF[N] Depot DSER2 - Battery Cabinet | 27/04/2020 | 05/06/2020 | 20/09/2019 | 07/04/2020 | 0 | TK_Complete | 1112893334 | 44 | 1112893334_44
C730D157BC###0017850 | TT_Task | RFQ, BA, and PO SMTF[N] Depot DSER2 - Battery Fuse Box | 27/04/2020 | 05/06/2020 | 20/09/2019 | 07/04/2020 | 0 | TK_Complete | 1112893334 | 44 | 1112893334_44
C730P147CT###0030830 | TT_Task | Trackside FAT ATC (Balise) | 30/07/2021 | 12/08/2021 | 19/07/2021 | 19/07/2021 | 0 | TK_Complete | 1112893334 | 439 | 1112893334_439
C730P147CT###0031720 | TT_Task | Trackside Deliver ATC (Balise) [First Batch] | 27/07/2021 | 20/09/2021 | 20/07/2021 | 25/08/2021 | 0 | TK_Complete | 1112893334 | 439 | 1112893334_439
C730P147CT###N30380 | TT_Task | Trackside Production Sheet Metal related items | 27/07/2021 | 18/10/2021 | 05/07/2021 | 10/08/2021 | 0 | TK_Complete | 1112893334 | 438 | 1112893334_438
C730P147CT###N20380 | TT_Task | Trackside FAT Sheet Metal related items | 01/09/2021 | 14/09/2021 | 09/08/2021 | 10/08/2021 | 0 | TK_Complete | 1112893334 | 438 | 1112893334_438
C730P147CT###N031790 | TT_Task | Trackside Deliver Sheet Metal related items [First Batch] | 15/09/2021 | 05/10/2021 | 10/08/2021 | 12/08/2021 | 0 | TK_Complete | 1112893334 | 438 | 1112893334_438
C730P147CT###0030540 | TT_Task | Trackside Production Boxes (TRE/SAB) | 25/01/2021 | 20/08/2021 | 07/09/2020 | 03/04/2021 | 0 | TK_Complete | 1112893334 | 437 | 1112893334_437
C730C157CP###TP2670 | TT_Task | SAB Boxes (SD-SYD Trackside) | 20/04/2022 | 20/04/2022 | nan | nan | 88 | TK_NotStart | 1112893334 | 437 | 1112893334_437
C730C157CP###TP2680 | TT_Task | TRE Boxes (SD-SYD Trackside) | 31/03/2022 | 05/04/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 437 | 1112893334_437
C730C157CP###TP2830 | TT_Task | TRE box FO Splice (SD-SYD Trackside) | 26/04/2022 | 03/05/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 437 | 1112893334_437
C730P147CT###0030530 | TT_Task | Trackside Production Bracketries / Adaptors | 25/02/2021 | 14/09/2021 | 26/01/2021 | 24/08/2021 | 0 | TK_Complete | 1112893334 | 436 | 1112893334_436
C730P147CT###0031050 | TT_Task | Trackside FAT Bracketries / Adaptors | 25/08/2021 | 07/09/2021 | 24/08/2021 | 25/08/2021 | 0 | TK_Complete | 1112893334 | 436 | 1112893334_436
C730P147CT###0031190 | TT_Task | Trackside Deliver Bracketries / Adaptors [First Batch] | 07/09/2021 | 01/11/2021 | 25/08/2021 | 11/09/2021 | 0 | TK_Complete | 1112893334 | 436 | 1112893334_436
C730P147CT###0030520 | TT_Task | Trackside Production Marker Boards (Covered in sheet metals) *** N/A*** | 28/09/2020 | 03/05/2021 | 24/09/2020 | 24/09/2020 | 0 | TK_Complete | 1112893334 | 435 | 1112893334_435
C730P147CT###0031040 | TT_Task | Trackside FAT Marker Boards (covered in sheet metals) *** N/A*** | 28/09/2020 | 12/10/2020 | 24/09/2020 | 24/09/2020 | 0 | TK_Complete | 1112893334 | 435 | 1112893334_435
C730P147CT###0031860 | TT_Task | Trackside Deliver Marker Boards (covered in sheet metals) *** N/A*** | 13/10/2020 | 07/12/2020 | 24/09/2020 | 24/09/2020 | 0 | TK_Complete | 1112893334 | 435 | 1112893334_435
C730P147CT###0030510 | TT_Task | Trackside Production Cables (all types) | 25/03/2021 | 25/08/2021 | 26/02/2021 | 11/07/2021 | 0 | TK_Complete | 1112893334 | 434 | 1112893334_434
C730P147CT###0031030 | TT_Task | Trackside FAT Cables (all types) | 26/07/2021 | 06/08/2021 | 12/07/2021 | 23/07/2021 | 0 | TK_Complete | 1112893334 | 434 | 1112893334_434
C730P147CT###0031360 | TT_Task | Trackside Deliver Cables (all types) [First Batch] | 09/08/2021 | 01/10/2021 | 23/07/2021 | 24/08/2021 | 0 | TK_Complete | 1112893334 | 434 | 1112893334_434
C730P147CT###0030390 | TT_Task | Trackside Production Keyswitches | 04/03/2021 | 29/09/2021 | 16/06/2020 | 02/09/2021 | 0 | TK_Complete | 1112893334 | 433 | 1112893334_433
C730P147CT###0030860 | TT_Task | Trackside FAT Keyswitches | 28/09/2021 | 11/10/2021 | 27/08/2021 | 03/09/2021 | 0 | TK_Complete | 1112893334 | 433 | 1112893334_433
C730P147CT###0031790 | TT_Task | Trackside Deliver Keyswitches [First Batch] | 12/10/2021 | 06/12/2021 | 06/09/2021 | 16/11/2021 | 0 | TK_Complete | 1112893334 | 433 | 1112893334_433
C730P147CT###0030380 | TT_Task | Trackside Production CBI Trackside Materials (Signals/Pts/AxCo) | 28/09/2020 | 03/05/2021 | 30/04/2020 | 02/09/2021 | 0 | TK_Complete | 1112893334 | 432 | 1112893334_432
C730P147CT###0030850 | TT_Task | Trackside FAT CBI (Signals/Pts/AxCo) | 28/09/2021 | 11/10/2021 | 27/08/2021 | 03/09/2021 | 0 | TK_Complete | 1112893334 | 432 | 1112893334_432
C730P147CT###0031590 | TT_Task | Trackside Deliver CBI (Signals/Pts/AxCo) [First Batch] | 12/10/2021 | 06/12/2021 | 06/09/2021 | 16/12/2021 | 0 | TK_Complete | 1112893334 | 432 | 1112893334_432
C730P147CT###0030370 | TT_Task | Trackside Production DCS/CCTV | 04/08/2020 | 09/03/2021 | 14/02/2020 | 06/07/2021 | 0 | TK_Complete | 1112893334 | 431 | 1112893334_431
C730P147CT###0030840 | TT_Task | Trackside FAT DCS/CCTV | 26/07/2021 | 06/08/2021 | 05/07/2021 | 22/07/2021 | 0 | TK_Complete | 1112893334 | 431 | 1112893334_431
C730P147CT###0031500 | TT_Task | Trackside Deliver DCS/CCTV [First Batch] | 04/08/2021 | 28/09/2021 | 23/07/2021 | 24/08/2021 | 0 | TK_Complete | 1112893334 | 431 | 1112893334_431
C730P147CT###0031070 | TT_Task | Room FAT Cable Chatswood Station SER | 06/12/2021 | 17/12/2021 | 28/06/2021 | 30/06/2021 | 0 | TK_Complete | 1112893334 | 430 | 1112893334_430
C730P147CT###0031150 | TT_Task | Room FAT Cable Sydenham Station SER | 27/09/2021 | 08/10/2021 | 26/07/2021 | 27/07/2021 | 0 | TK_Complete | 1112893334 | 430 | 1112893334_430
C730P147CT###0031090 | TT_Task | Room FAT Cable Victoria Cross Station SER | 13/12/2021 | 07/01/2022 | 28/06/2021 | 30/06/2021 | 0 | TK_Complete | 1112893334 | 430 | 1112893334_430
C730P147CT###0031110 | TT_Task | Room FAT Cable Martin Place Station SER | 20/12/2021 | 14/01/2022 | 28/06/2021 | 30/06/2021 | 0 | TK_Complete | 1112893334 | 430 | 1112893334_430
C730P147CT###0031130 | TT_Task | Room FAT Cable Central Station SER | 27/12/2021 | 21/01/2022 | 28/06/2021 | 30/06/2021 | 0 | TK_Complete | 1112893334 | 430 | 1112893334_430
C730P147CT###0031140 | TT_Task | Room FAT Cable Waterloo Station SER | 27/12/2021 | 21/01/2022 | 28/06/2021 | 30/06/2021 | 0 | TK_Complete | 1112893334 | 430 | 1112893334_430
C720P147CF###0030630 | TT_Task | RFQ for pantograph | 25/02/2020 | 11/03/2020 | 31/10/2019 | 19/12/2019 | 0 | TK_Complete | 1112893334 | 43 | 1112893334_43
C720P147CF###0030720 | TT_Task | RFQ for seats | 25/02/2020 | 12/03/2020 | 31/10/2019 | 18/11/2019 | 0 | TK_Complete | 1112893334 | 43 | 1112893334_43
C720P147CF###32660 | TT_Task | RFQ for centre pivot | 31/10/2019 | 27/11/2019 | 31/10/2019 | 03/12/2019 | 0 | TK_Complete | 1112893334 | 43 | 1112893334_43
C730P147CT###0030890 | TT_Task | Room FAT All Cubicles Chatswood Station SER | 04/04/2022 | 15/04/2022 | 19/12/2021 | 23/02/2022 | 0 | TK_Complete | 1112893334 | 429 | 1112893334_429
C730P147CT###0030970 | TT_Task | Room FAT All Cubicles Sydenham Station SER | 01/02/2022 | 14/02/2022 | 01/02/2022 | 28/02/2022 | 0 | TK_Complete | 1112893334 | 429 | 1112893334_429
C730P147CT###0030910 | TT_Task | Room FAT All Cubicles Victoria Cross Station SER | 03/03/2022 | 30/03/2022 | 03/03/2022 | 07/03/2022 | 0 | TK_Complete | 1112893334 | 429 | 1112893334_429
C730P147CT###0030920 | TT_Task | Room FAT All Cubicles Barangaroo Station SER | 03/03/2022 | 30/03/2022 | 03/03/2022 | 07/03/2022 | 0 | TK_Complete | 1112893334 | 429 | 1112893334_429
C730P147CT###0030930 | TT_Task | Room FAT All Cubicles Martin Place Station SER | 03/03/2022 | 30/03/2022 | 03/03/2022 | 07/03/2022 | 0 | TK_Complete | 1112893334 | 429 | 1112893334_429
C730P147CT###0030940 | TT_Task | Room FAT All Cubicles Pitt Street Station SER | 03/03/2022 | 30/03/2022 | 03/03/2022 | 07/03/2022 | 0 | TK_Complete | 1112893334 | 429 | 1112893334_429
C730P147CT###0030950 | TT_Task | Room FAT All Cubicles Central Station SER | 25/01/2022 | 21/02/2022 | 08/02/2022 | 07/03/2022 | 0 | TK_Complete | 1112893334 | 429 | 1112893334_429
C730P147CT###0030960 | TT_Task | Room FAT All Cubicles Waterloo Station SER | 03/03/2022 | 07/03/2022 | 03/03/2022 | 07/03/2022 | 0 | TK_Complete | 1112893334 | 429 | 1112893334_429
C730P147CT###0030550 | TT_Task | Room Production All Cables Chatswood Station SER | 25/06/2021 | 20/01/2022 | 25/05/2021 | 23/07/2021 | 0 | TK_Complete | 1112893334 | 428 | 1112893334_428
C730P147CT###0030630 | TT_Task | Room Production All Cables Sydenham Station SER | 25/06/2021 | 11/11/2021 | 25/05/2021 | 23/07/2021 | 0 | TK_Complete | 1112893334 | 428 | 1112893334_428
C730P147CT###0030560 | TT_Task | Room Production All Cables Crows Nest Station SER | 25/06/2021 | 20/01/2022 | 25/05/2021 | 27/06/2021 | 0 | TK_Complete | 1112893334 | 428 | 1112893334_428
C730P147CT###0030570 | TT_Task | Room Production All Cables Victoria Cross Station SER | 25/05/2021 | 20/12/2021 | 25/05/2021 | 25/06/2021 | 0 | TK_Complete | 1112893334 | 428 | 1112893334_428
C730P147CT###0030580 | TT_Task | Room Production All Cables Barangaroo Station SER | 25/05/2021 | 20/12/2021 | 25/05/2021 | 25/06/2021 | 0 | TK_Complete | 1112893334 | 428 | 1112893334_428
C730P147CT###0030590 | TT_Task | Room Production All Cables Martin Place Station SER | 25/05/2021 | 20/12/2021 | 25/05/2021 | 25/06/2021 | 0 | TK_Complete | 1112893334 | 428 | 1112893334_428
C730P147CT###0030600 | TT_Task | Room Production All Cables Pitt Street Station SER | 25/05/2021 | 20/12/2021 | 25/05/2021 | 25/06/2021 | 0 | TK_Complete | 1112893334 | 428 | 1112893334_428
C730P147CT###0030610 | TT_Task | Room Production All Cables Central Station SER | 25/05/2021 | 20/12/2021 | 25/05/2021 | 25/06/2021 | 0 | TK_Complete | 1112893334 | 428 | 1112893334_428
C730P147CT###0030620 | TT_Task | Room Production All Cables Waterloo Station SER | 25/05/2021 | 20/12/2021 | 25/05/2021 | 25/06/2021 | 0 | TK_Complete | 1112893334 | 428 | 1112893334_428
C730P147CT###0030420 | TT_Task | Room Production All Cubicles Chatswood Station SER (Category-A) | 03/08/2020 | 19/04/2021 | 26/05/2020 | 03/03/2022 | 0 | TK_Complete | 1112893334 | 427 | 1112893334_427
C730P147CT###0030500 | TT_Task | Room Production All Cubicles Sydenham Station SER (Category-A) | 25/06/2020 | 25/03/2021 | 26/05/2020 | 12/12/2021 | 0 | TK_Complete | 1112893334 | 427 | 1112893334_427
C730P147CT###0030440 | TT_Task | Room Production All Cubicles Victoria Cross Station SER (Category-A) | 26/07/2021 | 07/01/2022 | 28/06/2021 | 03/03/2022 | 0 | TK_Complete | 1112893334 | 427 | 1112893334_427
C730P147CT###0030450 | TT_Task | Room Production All Cubicles Barangaroo Station SER (Category-A) | 26/07/2021 | 07/01/2022 | 28/06/2021 | 03/03/2022 | 0 | TK_Complete | 1112893334 | 427 | 1112893334_427
C730P147CT###N133459 | TT_Task | Room Production Cubicles Barangaroo Station (Category B- ST3 driven) | 25/03/2022 | 01/09/2022 | 28/02/2022 | nan | 0 | TK_Active | 1112893334 | 427 | 1112893334_427
C730P147CT###0030460 | TT_Task | Room Production All Cubicles Martin Place Station SER (Category-A) | 26/07/2021 | 07/01/2022 | 28/06/2021 | 03/03/2022 | 0 | TK_Complete | 1112893334 | 427 | 1112893334_427
C730P147CT###0030470 | TT_Task | Room Production All Cubicles Pitt Street Station SER (Category-A) | 26/07/2021 | 07/01/2022 | 28/06/2021 | 03/03/2022 | 0 | TK_Complete | 1112893334 | 427 | 1112893334_427
C730P147CT###0030480 | TT_Task | Room Production All Cubicles Central Station SER (Category-A) | 25/06/2021 | 07/10/2021 | 24/06/2021 | 11/02/2022 | 0 | TK_Complete | 1112893334 | 427 | 1112893334_427
C730P147CT###0030490 | TT_Task | Room Production All Cubicles Waterloo Station SER (Category-A) | 26/07/2021 | 07/01/2022 | 28/06/2021 | 03/03/2022 | 0 | TK_Complete | 1112893334 | 427 | 1112893334_427
C730P147CT###0031300 | TT_Task | Room Deliver All Cubicles Chatswood Station SER (Category-A) | 25/02/2022 | 21/04/2022 | 07/03/2022 | nan | 0 | TK_Active | 1112893334 | 427 | 1112893334_427
C730P147CT###0031470 | TT_Task | Room Deliver All Cubicles Barangaroo Station SER (Category-A) | 25/02/2022 | 21/04/2022 | 07/03/2022 | nan | 0 | TK_Active | 1112893334 | 427 | 1112893334_427
C730P147CT###0031550 | TT_Task | Room Deliver All Cubicles Martin Place Station SER (Category-A) | 25/02/2022 | 21/04/2022 | 07/03/2022 | nan | 0 | TK_Active | 1112893334 | 427 | 1112893334_427
C730P147CT###0031560 | TT_Task | Room Deliver All Cubicles Pitt Street Station SER (Category-A) | 25/02/2022 | 21/04/2022 | 07/03/2022 | nan | 0 | TK_Active | 1112893334 | 427 | 1112893334_427
C730P147CT###0031650 | TT_Task | Room Deliver All Cubicles Central Station SER (Category-A) | 25/02/2022 | 21/04/2022 | 07/03/2022 | nan | 0 | TK_Active | 1112893334 | 427 | 1112893334_427
C730P147CT###0031660 | TT_Task | Room Deliver All Cubicles Waterloo Station SER (Category-A) | 25/02/2022 | 21/04/2022 | 07/03/2022 | nan | 0 | TK_Active | 1112893334 | 427 | 1112893334_427
C730P147CT###0031760 | TT_Task | Room Deliver All Cubicles Sydenham Station SER (Category-A) | 01/03/2022 | 25/04/2022 | 01/02/2022 | nan | 0 | TK_Active | 1112893334 | 427 | 1112893334_427
C730P147CT###0031460 | TT_Task | Room Deliver All Cubicles VIC SER (Category-A) | 25/02/2022 | 21/04/2022 | 07/03/2022 | nan | 0 | TK_Active | 1112893334 | 427 | 1112893334_427
C730P147CT###N033209 | TT_Task | Room Production Cubicles SMTF[S] (Category B - stage3 driven) | 27/10/2021 | 15/02/2022 | 27/10/2021 | nan | 0 | TK_Active | 1112893334 | 426 | 1112893334_426
C730P147CT###N933229 | TT_Task | Room Production Cubicles Chatswood (Category B - stage3 driven) ***N/A*** | 27/10/2021 | 15/02/2022 | 24/03/2022 | 24/03/2022 | 0 | TK_Complete | 1112893334 | 426 | 1112893334_426
C730P147CT###N33249 | TT_Task | Room Production Cubicles Sydenham (Category B - stage3 driven) | 27/10/2021 | 15/02/2022 | 27/10/2021 | nan | 0 | TK_Active | 1112893334 | 426 | 1112893334_426
C730P147CT###0030400 | TT_Task | Room Production All Cubicles SMTF[S] - DSER3 (Category-A) | 25/06/2020 | 06/05/2021 | 26/05/2020 | 18/02/2022 | 0 | TK_Complete | 1112893334 | 425 | 1112893334_425
C730P147CT###0030410 | TT_Task | Room Production All Cubicles SMTF[S] - OCC / CER (Category-A) | 03/08/2020 | 03/05/2021 | 26/05/2020 | 31/01/2022 | 0 | TK_Complete | 1112893334 | 425 | 1112893334_425
C730P147CT###0030870 | TT_Task | Room FAT All Cubicles SMTF[S] - DSER3 | 25/02/2022 | 10/03/2022 | 19/02/2022 | 25/02/2022 | 0 | TK_Complete | 1112893334 | 425 | 1112893334_425
C730P147CT###0030880 | TT_Task | Room FAT All Cubicles Sydenham - OCC/CER | 25/01/2022 | 07/02/2022 | 15/01/2022 | 27/01/2022 | 0 | TK_Complete | 1112893334 | 425 | 1112893334_425
C730P147CT###0031010 | TT_Task | Room Deliver All Cubicles Sydenham - OCC / CER (Category-A) | 16/03/2022 | 10/05/2022 | 01/02/2022 | 08/03/2022 | 0 | TK_Complete | 1112893334 | 425 | 1112893334_425
C730P147CT###0031000 | TT_Task | Room Deliver All Cubicles SMTF[S] - (Category-A) | 25/02/2022 | 16/03/2022 | 10/12/2021 | nan | 0 | TK_Active | 1112893334 | 425 | 1112893334_425
C730P147CT###N33219 | TT_Task | RFQ, BA, and PO Room Equip Category B Materials | 30/04/2021 | 06/05/2021 | 23/04/2021 | 09/08/2021 | 0 | TK_Complete | 1112893334 | 424 | 1112893334_424
C730P147CT###N33229 | TT_Task | PBS rework for Category B Materials (for all rooms) | 30/04/2021 | 06/05/2021 | 23/04/2021 | 15/11/2021 | 0 | TK_Complete | 1112893334 | 424 | 1112893334_424
C730P147CT###N33469 | TT_Task | RFQ, BA, and PO Cyber Security Cubicles (CER3) | 25/05/2020 | 13/07/2020 | 26/07/2021 | nan | 0 | TK_Active | 1112893334 | 423 | 1112893334_423
C730P147CT###N33479 | TT_Task | Room Production Cyber Cubicles CER3 | 05/04/2022 | 27/06/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 423 | 1112893334_423
C730P147CT###N6469 | TT_Task | Room FAT Cyber Security Cubicles CER3 | 28/06/2022 | 11/07/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 423 | 1112893334_423
C730P147CT###N53469 | TT_Task | Room Deliver Cyber Security Cubicles CER3 | 12/07/2022 | 05/09/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 423 | 1112893334_423
C730P147CT###0030740 | TT_Task | RFQ, BA, and PO SMN Line Backbone Splice @ CHW - FO cable | 22/05/2020 | 10/07/2020 | 09/12/2019 | 27/05/2020 | 0 | TK_Complete | 1112893334 | 422 | 1112893334_422
C730P147CT###0030780 | TT_Task | SMN Line Backbone Splice @ CHW - production and FAT FO cable and materials | 26/07/2021 | 15/04/2022 | 25/06/2021 | 03/03/2022 | 0 | TK_Complete | 1112893334 | 422 | 1112893334_422
C730P147CT###0031400 | TT_Task | SMN Line Backbone Splice @ CHW - Deliver FO cable and materials | 25/02/2022 | 21/04/2022 | 03/03/2022 | nan | 0 | TK_Active | 1112893334 | 422 | 1112893334_422
C730P147CT###0030310 | TT_Task | RFQ, BA, and PO Trackside Bracketries and Adaptors (Sheet Metals) | 13/07/2020 | 28/08/2020 | 10/12/2019 | 22/01/2021 | 0 | TK_Complete | 1112893334 | 421 | 1112893334_421
C730P147CT###N030310 | TT_Task | RFQ, BA, and PO Trackside Category B (Sheet Metals ; PM Roddings) - ST3 Driven | 27/04/2021 | 10/05/2021 | 20/04/2021 | 15/06/2021 | 0 | TK_Complete | 1112893334 | 421 | 1112893334_421
C730P147CT###0030230 | TT_Task | RFQ, BA, and PO CBI materials ; equipment | 25/03/2020 | 14/05/2020 | 09/12/2019 | 29/04/2020 | 0 | TK_Complete | 1112893334 | 420 | 1112893334_420
C730P147CT###0030240 | TT_Task | RFQ, BA, and PO DCS materials ; equipment | 13/07/2020 | 28/08/2020 | 06/11/2019 | 22/06/2020 | 0 | TK_Complete | 1112893334 | 420 | 1112893334_420
C730P147CT###0030250 | TT_Task | RFQ, BA, and PO CCTV materials ; equipment | 16/06/2020 | 03/08/2020 | 14/05/2020 | 14/08/2020 | 0 | TK_Complete | 1112893334 | 420 | 1112893334_420
C730P147CT###0030260 | TT_Task | RFQ, BA, and PO PS (power supply) materials ; equipment | 25/05/2020 | 13/07/2020 | 30/04/2020 | 19/08/2021 | 0 | TK_Complete | 1112893334 | 420 | 1112893334_420
C730P147CT###0030340 | TT_Task | RFQ, BA, and PO ATS materials ; equipment | 25/05/2020 | 13/07/2020 | 04/12/2019 | 15/07/2020 | 0 | TK_Complete | 1112893334 | 420 | 1112893334_420
C730P147CT###0033190 | TT_Task | RFQ, BA, and PO ATC materials ; equipment trainborne | 25/02/2020 | 15/04/2020 | 18/12/2019 | 24/02/2020 | 0 | TK_Complete | 1112893334 | 420 | 1112893334_420
C720P147CF###0030550 | TT_Task | RFQ for floor (composite material) | 25/02/2020 | 12/03/2020 | 31/10/2019 | 18/11/2019 | 0 | TK_Complete | 1112893334 | 42 | 1112893334_42
C720P147CF###0030710 | TT_Task | RFQ for floor covering | 25/02/2020 | 12/03/2020 | 31/10/2019 | 19/11/2019 | 0 | TK_Complete | 1112893334 | 42 | 1112893334_42
C730D157BC###0009443 | TT_Task | RFQ, BA, and PO SMTF[N] Depot Trackside - Installation Sheet Metals | 25/03/2020 | 07/05/2020 | 26/05/2020 | 01/07/2020 | 0 | TK_Complete | 1112893334 | 419 | 1112893334_419
C730D157BC###0009453 | TT_Task | Manufacturing SMTF[N] Depot Trackside - Installation Sheet Metals | 10/08/2020 | 02/10/2020 | 22/06/2020 | 10/02/2021 | 0 | TK_Complete | 1112893334 | 419 | 1112893334_419
C730D157BC###0039473 | TT_Task | FAI/FAT SMTF[N] Depot Trackside - Installation Sheet Metals | 10/08/2020 | 11/08/2020 | 06/07/2020 | 15/02/2021 | 0 | TK_Complete | 1112893334 | 419 | 1112893334_419
C730D157BC###0059463 | TT_Task | Material Delivery SMTF[N] Depot Trackside - Installation Sheet Metals #batch 2.1.a (MS2) | 28/10/2020 | 16/11/2020 | 15/10/2020 | 06/11/2020 | 0 | TK_Complete | 1112893334 | 419 | 1112893334_419
C730D157BC###209443 | TT_Task | Material Delivery SMTF[N] Depot Trackside - Installation Sheet Metals #batch 2.1 (MS2) | 27/07/2020 | 04/08/2020 | 07/07/2020 | 14/07/2020 | 0 | TK_Complete | 1112893334 | 419 | 1112893334_419
C730D157BC###N209451 | TT_Task | Material Delivery SMTF[N] Depot Trackside - Installation Sheet Metals #batch 2.2 (MS4) | 29/04/2021 | 26/05/2021 | 15/02/2021 | 15/02/2021 | 0 | TK_Complete | 1112893334 | 419 | 1112893334_419
C730D157BC###0070056 | TT_Task | RFQ, BA, and PO SMTF[N] Depot Trackside - CBI Axle Counters | 25/03/2020 | 07/05/2020 | 02/12/2019 | 24/02/2020 | 0 | TK_Complete | 1112893334 | 418 | 1112893334_418
C730D157BC###0070120 | TT_Task | Manufacturing SMTF[N] Depot Trackside - CBI Axle Counters | 08/05/2020 | 17/07/2020 | 26/03/2020 | 12/03/2021 | 0 | TK_Complete | 1112893334 | 418 | 1112893334_418
C730D157BC###0070152 | TT_Task | FAI/FAT SMTF[N] Depot Trackside - CBI Axle Counters | 29/07/2020 | 29/07/2020 | 22/07/2020 | 12/03/2021 | 0 | TK_Complete | 1112893334 | 418 | 1112893334_418
C730D157BC###0070184 | TT_Task | Material Delivery SMTF[N] Depot Trackside - CBI Axle Counters | 30/07/2020 | 30/09/2020 | 24/07/2020 | 17/03/2021 | 0 | TK_Complete | 1112893334 | 418 | 1112893334_418
C730D157BC###0009243 | TT_Task | Material Delivery SMTF[N] Depot Trackside - CBI Axle Counters - #batch2.1 (MS2) | 30/07/2020 | 12/08/2020 | 24/07/2020 | 06/08/2020 | 0 | TK_Complete | 1112893334 | 418 | 1112893334_418
C730D157BC###0009283 | TT_Task | Material Delivery SMTF[N] Depot Trackside - CBI Axle Counters - #batch2.2 (MS4) | 14/04/2021 | 12/05/2021 | 03/03/2021 | 17/03/2021 | 0 | TK_Complete | 1112893334 | 418 | 1112893334_418
C730D157BC###0070136 | TT_Task | Manufacturing SMTF[N] Depot Trackside - CBI Switches | 03/08/2020 | 12/10/2020 | 16/06/2020 | 12/10/2020 | 0 | TK_Complete | 1112893334 | 417 | 1112893334_417
C730D157BC###0070168 | TT_Task | FAI/FAT SMTF[N] Depot Trackside - CBI Switches | 02/11/2020 | 04/11/2020 | 13/10/2020 | 14/10/2020 | 0 | TK_Complete | 1112893334 | 417 | 1112893334_417
C730D157BC###0070200 | TT_Task | Material Delivery SMTF[N] Depot Trackside - CBI Switches - #batch 2.1.a | 05/11/2020 | 18/11/2020 | 20/10/2020 | 06/11/2020 | 0 | TK_Complete | 1112893334 | 417 | 1112893334_417
C730D157BC###0070128 | TT_Task | Manufacturing SMTF[N] Depot Trackside - CBI Signals | 08/05/2020 | 17/07/2020 | 21/05/2020 | 26/02/2021 | 0 | TK_Complete | 1112893334 | 416 | 1112893334_416
C730D157BC###0070160 | TT_Task | FAI/FAT SMTF[N] Depot Trackside - CBI Signals | 31/08/2020 | 01/09/2020 | 11/08/2020 | 02/03/2021 | 0 | TK_Complete | 1112893334 | 416 | 1112893334_416
C730D157BC###0070192 | TT_Task | Material Delivery SMTF[N] Depot Trackside - CBI Signals | 09/09/2020 | 18/11/2020 | 13/08/2020 | 23/04/2021 | 0 | TK_Complete | 1112893334 | 416 | 1112893334_416
C730D157BC###0009313 | TT_Task | Material Delivery SMTF[N] Depot Trackside - CBI Signals - #batch 2.1 (MS2) | 09/09/2020 | 18/09/2020 | 13/08/2020 | 20/08/2020 | 0 | TK_Complete | 1112893334 | 416 | 1112893334_416
C730D157BC###0009343 | TT_Task | Material Delivery SMTF[N] Depot Trackside - CBI Signals - #batch 2.2 (MS2) | 25/08/2020 | 28/09/2020 | 21/08/2020 | 31/08/2020 | 0 | TK_Complete | 1112893334 | 416 | 1112893334_416
C730D157BC###0009373 | TT_Task | Material Delivery SMTF[N] Depot Trackside - CBI Signals - #batch 2.3 (MS4) | 29/03/2021 | 30/04/2021 | 03/03/2021 | 23/04/2021 | 0 | TK_Complete | 1112893334 | 416 | 1112893334_416
C730D157BC###0070064 | TT_Task | RFQ, BA, and PO SMTF[N] Depot Trackside - CBI Signals | 25/03/2020 | 07/05/2020 | 20/01/2020 | 10/02/2020 | 0 | TK_Complete | 1112893334 | 415 | 1112893334_415
C730D157BC###0070072 | TT_Task | RFQ, BA, and PO SMTF[N] Depot Trackside - CBI Switches | 27/04/2020 | 05/06/2020 | 13/04/2020 | 06/07/2020 | 0 | TK_Complete | 1112893334 | 415 | 1112893334_415
C730P147CT###0030270 | TT_Task | RFQ, BA, and PO ATC Trackside and ATC SMIO | 22/05/2020 | 10/07/2020 | 09/12/2019 | 28/05/2020 | 0 | TK_Complete | 1112893334 | 415 | 1112893334_415
C730D157BC###0070000 | TT_Task | RFQ, BA, and PO SMTF[N] Depot Trackside - CBI Point Machines | 15/10/2019 | 25/11/2019 | 23/09/2019 | 17/11/2019 | 0 | TK_Complete | 1112893334 | 414 | 1112893334_414
C730D157BC###0070048 | TT_Task | Manufacturing SMTF[N] Depot Trackside - CBI Point Machines | 23/04/2020 | 23/11/2020 | 13/12/2019 | 23/04/2021 | 0 | TK_Complete | 1112893334 | 414 | 1112893334_414
C730D157BC###0070280 | TT_Task | FAI/FAT SMTF[N] Depot Trackside - CBI Point Machines | 26/04/2021 | 27/04/2021 | 23/04/2021 | 26/04/2021 | 0 | TK_Complete | 1112893334 | 414 | 1112893334_414
C730D157BC###0070288 | TT_Task | Material Delivery SMTF[N] Depot Trackside - CBI Point Machines - #batch 2.1.a (MS2) | 27/01/2021 | 09/02/2021 | 11/01/2021 | 22/01/2021 | 0 | TK_Complete | 1112893334 | 414 | 1112893334_414
C730D157BC###N209453 | TT_Task | Material Delivery SMTF[N] Depot Trackside - CBI Point Machines - #batch 2.3 (MS4) | 05/05/2021 | 11/05/2021 | 16/04/2021 | 22/04/2021 | 0 | TK_Complete | 1112893334 | 414 | 1112893334_414
C730D157BC###0070024 | TT_Task | RFQ, BA, and PO SMTF[N] Depot Trackside - CBI Point Machines (D84M) | 25/03/2020 | 07/05/2020 | 23/09/2019 | 23/09/2019 | 0 | TK_Complete | 1112893334 | 414 | 1112893334_414
C730D157BC###0070104 | TT_Task | Manufacturing SMTF[N] Depot Trackside - CBI Point Machines (D84M) | 08/05/2020 | 18/09/2020 | 28/01/2020 | 28/01/2020 | 0 | TK_Complete | 1112893334 | 414 | 1112893334_414
C730D157BC###0070232 | TT_Task | FAI/FAT SMTF[N] Depot Trackside - CBI Point Machines (D84M) | 12/06/2020 | 19/06/2020 | 31/01/2020 | 31/01/2020 | 0 | TK_Complete | 1112893334 | 414 | 1112893334_414
C730D157BC###0070240 | TT_Task | Material Delivery SMTF[N] Depot Trackside - CBI Point Machines (D84M) - #batch 2.1.a | 22/06/2020 | 07/08/2020 | 24/02/2020 | 24/02/2020 | 0 | TK_Complete | 1112893334 | 414 | 1112893334_414
C730D157BC###0070032 | TT_Task | RFQ, BA, and PO SMTF[N] Depot DSER2 - DCS Track | 25/03/2020 | 30/04/2020 | 06/11/2019 | 18/11/2019 | 0 | TK_Complete | 1112893334 | 413 | 1112893334_413
C730D157BC###0070080 | TT_Task | Manufacturing SMTF[N] Trackside - DCS Track | 01/05/2020 | 21/08/2020 | 13/12/2019 | 30/07/2020 | 0 | TK_Complete | 1112893334 | 413 | 1112893334_413
C730D157BC###0070176 | TT_Task | FAI/FAT SMTF[N] Depot DSER2 - DCS Track | 26/08/2020 | 27/08/2020 | 31/07/2020 | 03/08/2020 | 0 | TK_Complete | 1112893334 | 413 | 1112893334_413
C730D157BC###0070216 | TT_Task | Material Delivery SMTF[N] Depot DSER2 - DCS Track - #batch 2.1 | 28/08/2020 | 10/09/2020 | 04/08/2020 | 17/08/2020 | 0 | TK_Complete | 1112893334 | 413 | 1112893334_413
C730D157BC###0070016 | TT_Task | RFQ, BA, and PO SMTF[N] Depot Trackside - ATC Trackside materials (Beacons) | 25/03/2020 | 07/05/2020 | 04/11/2019 | 02/12/2019 | 0 | TK_Complete | 1112893334 | 412 | 1112893334_412
C730D157BC###0070096 | TT_Task | Manufacturing SMTF[N] Depot Trackside - ATC Trackside materials (Beacons) | 25/03/2020 | 11/09/2020 | 13/12/2019 | 03/03/2021 | 0 | TK_Complete | 1112893334 | 412 | 1112893334_412
C730D157BC###0070264 | TT_Task | FAI/FAT SMTF[N] Depot Trackside - ATC Trackside materials (Beacons) | 09/07/2020 | 10/07/2020 | 27/05/2020 | 05/03/2021 | 0 | TK_Complete | 1112893334 | 412 | 1112893334_412
C730D157BC###0070272 | TT_Task | Material Delivery SMTF[N] Depot Trackside - ATC Trackside materials (Beacons) | 13/07/2020 | 03/11/2020 | 28/05/2020 | 23/04/2021 | 0 | TK_Complete | 1112893334 | 412 | 1112893334_412
C730D157BC###0009163 | TT_Task | Material Delivery SMTF[N] Depot Trackside - ATC Trackside materials (Beacons) - #batch 2.1 | 13/07/2020 | 24/07/2020 | 28/05/2020 | 14/07/2020 | 0 | TK_Complete | 1112893334 | 412 | 1112893334_412
C730D157BC###0009203 | TT_Task | Material Delivery SMTF[N] Depot Trackside - ATC Trackside materials (Beacons) - #batch 2.1.a | 25/03/2021 | 14/04/2021 | 08/03/2021 | 23/04/2021 | 0 | TK_Complete | 1112893334 | 412 | 1112893334_412
C730P147CT###0030360 | TT_Task | Trackside Production ATC (Beacons) | 08/07/2020 | 24/03/2021 | 14/02/2020 | 31/03/2021 | 0 | TK_Complete | 1112893334 | 412 | 1112893334_412
C730D157BC###0070088 | TT_Task | Manufacturing SMTF[N] Depot - Cables (12 wks) | 27/05/2020 | 19/08/2020 | 06/05/2020 | 22/01/2021 | 0 | TK_Complete | 1112893334 | 411 | 1112893334_411
C730D157BC###0070304 | TT_Task | Material Delivery SMTF[N] Depot - Cables | 17/08/2020 | 12/10/2020 | 23/07/2020 | 18/12/2020 | 0 | TK_Complete | 1112893334 | 411 | 1112893334_411
C730D157BC###0009083 | TT_Task | Material Delivery SMTF[N] Depot - Cables - #batch 2.1 (for MS2) | 17/08/2020 | 28/08/2020 | 23/07/2020 | 11/08/2020 | 0 | TK_Complete | 1112893334 | 411 | 1112893334_411
C730D157BC###0009123 | TT_Task | Material Delivery SMTF[N] Depot - Cables - #batch 2.2 (for MS4) | 25/01/2021 | 19/02/2021 | 28/12/2020 | 23/04/2021 | 0 | TK_Complete | 1112893334 | 411 | 1112893334_411
C730D157BC###0017770 | TT_Task | Manufacturing SMTF[N] Depot CER2 - CLC | 01/04/2020 | 16/11/2020 | 31/10/2019 | 15/10/2020 | 0 | TK_Complete | 1112893334 | 410 | 1112893334_410
C730D157BC###0018120 | TT_Task | Material Delivery SMTF[N] Depot CER2 - CLC (#batch 1.2) | 05/11/2020 | 09/12/2020 | 23/10/2020 | 06/11/2020 | 0 | TK_Complete | 1112893334 | 410 | 1112893334_410
C730D157BC###0070256 | TT_Task | Material Delivery SMTF[N] Depot CER2 - DCS BTN | 09/11/2020 | 11/12/2020 | 20/10/2020 | 29/11/2020 | 0 | TK_Complete | 1112893334 | 410 | 1112893334_410
C730D157BC###0070224 | TT_Task | Material Delivery SMTF[N] Depot CER2 - DCS ODF | 05/11/2020 | 09/12/2020 | 16/10/2020 | 23/11/2020 | 0 | TK_Complete | 1112893334 | 410 | 1112893334_410
C730D157BC###N209138 | TT_Task | Manufacturing SMTF[N] Depot CER2 - PDC/UPS/ZC/CCTV | 25/03/2020 | 17/07/2020 | 21/02/2020 | 13/10/2020 | 0 | TK_Complete | 1112893334 | 410 | 1112893334_410
C730D157BC###N209165 | TT_Task | Material Delivery SMTF[N] Depot CER2 - PDC/UPS/ZC/CCTV | 05/11/2020 | 16/12/2020 | 16/10/2020 | 18/12/2020 | 0 | TK_Complete | 1112893334 | 410 | 1112893334_410
C730D157BC###N949473 | TT_Task | Manufacturing and FAT SMTF[N] Depot CER2 - ATS Cubicles | 25/03/2020 | 30/04/2020 | 26/10/2020 | 22/01/2021 | 0 | TK_Complete | 1112893334 | 410 | 1112893334_410
C730D157BC###N949483 | TT_Task | Material Delivery SMTF[N] Depot CER2 - ATS Cubicles | 25/02/2021 | 24/03/2021 | 25/01/2021 | 12/03/2021 | 0 | TK_Complete | 1112893334 | 410 | 1112893334_410
C720P147CF###0030500 | TT_Task | RFQ for wind shield | 25/02/2020 | 12/03/2020 | 31/10/2019 | 18/11/2019 | 0 | TK_Complete | 1112893334 | 41 | 1112893334_41
C720P147CF###0030510 | TT_Task | RFQ for Ceiling and lighting | 25/02/2020 | 12/03/2020 | 31/10/2019 | 18/11/2019 | 0 | TK_Complete | 1112893334 | 41 | 1112893334_41
C720P147CF###0030540 | TT_Task | RFQ for front mask | 25/02/2020 | 12/03/2020 | 31/10/2019 | 18/11/2019 | 0 | TK_Complete | 1112893334 | 41 | 1112893334_41
C720P147CF###0030570 | TT_Task | RFQ for windows | 25/02/2020 | 12/03/2020 | 31/10/2019 | 18/11/2019 | 0 | TK_Complete | 1112893334 | 41 | 1112893334_41
C720P147CF###0030580 | TT_Task | RFQ for HVAC | 25/02/2020 | 12/03/2020 | 31/10/2019 | 18/11/2019 | 0 | TK_Complete | 1112893334 | 41 | 1112893334_41
C720P147CF###0030620 | TT_Task | RFQ for cabinets | 25/02/2020 | 02/03/2020 | 31/10/2019 | 06/11/2019 | 0 | TK_Complete | 1112893334 | 41 | 1112893334_41
C720P147CF###32670 | TT_Task | RFQ for obstacle detector | 31/10/2019 | 27/11/2019 | 31/10/2019 | 03/12/2019 | 0 | TK_Complete | 1112893334 | 41 | 1112893334_41
C730D157BC###0017740 | TT_Task | RFQ, BA, and PO SMTF[N] Depot CER2 - CLC (Central Logic Computer) | 15/10/2019 | 25/11/2019 | 25/09/2019 | 01/12/2019 | 0 | TK_Complete | 1112893334 | 409 | 1112893334_409
C730P147CT###0030280 | TT_Task | RFQ, BA, and PO MSS Workstation | 25/05/2020 | 13/07/2020 | 30/04/2020 | 23/11/2021 | 0 | TK_Complete | 1112893334 | 409 | 1112893334_409
C730D157BC###0017905 | TT_Task | Manufacturing SMTF[N] Depot DSER2 - Battery Fuse Box | 27/04/2020 | 20/07/2020 | 23/04/2020 | 12/10/2020 | 0 | TK_Complete | 1112893334 | 408 | 1112893334_408
C730D157BC###0018000 | TT_Task | FAI/FAT SMTF[N] Depot DSER2 - Battery Fuse Box | 28/10/2020 | 28/10/2020 | 13/10/2020 | 13/10/2020 | 0 | TK_Complete | 1112893334 | 408 | 1112893334_408
C730D157BC###0018060 | TT_Task | Material Delivery SMTF[N] Depot DSER2 - Battery Fuse Box - #batch 1.1.a | 29/10/2020 | 11/11/2020 | 13/10/2020 | 20/10/2020 | 0 | TK_Complete | 1112893334 | 408 | 1112893334_408
C730D157BC###0017900 | TT_Task | Manufacturing SMTF[N] Depot DSER2 - Incomer/Bypass | 09/06/2020 | 31/08/2020 | 23/04/2020 | 12/10/2020 | 0 | TK_Complete | 1112893334 | 407 | 1112893334_407
C730D157BC###0017995 | TT_Task | FAI/FAT SMTF[N] Depot DSER2 - Incomer/Bypass | 28/10/2020 | 28/10/2020 | 13/10/2020 | 13/10/2020 | 0 | TK_Complete | 1112893334 | 407 | 1112893334_407
C730D157BC###0017895 | TT_Task | Manufacturing SMTF[N] Depot DSER2 - Battery Cabinet | 09/06/2020 | 31/08/2020 | 23/04/2020 | 12/10/2020 | 0 | TK_Complete | 1112893334 | 406 | 1112893334_406
C730D157BC###0017990 | TT_Task | FAI/FAT SMTF[N] Depot DSER2 - Battery Cabinet | 28/10/2020 | 28/10/2020 | 13/10/2020 | 13/10/2020 | 0 | TK_Complete | 1112893334 | 406 | 1112893334_406
C730D157BC###0018050 | TT_Task | Material Delivery SMTF[N] Depot DSER2 - Battery Cabinet - #batch 1.1.a | 29/10/2020 | 11/11/2020 | 13/10/2020 | 20/10/2020 | 0 | TK_Complete | 1112893334 | 406 | 1112893334_406
C730D157BC###0069253 | TT_Task | RFQ, BA, and PO SMTF[N] Depot DSER2 - DCS ODF | 25/03/2020 | 30/04/2020 | 06/01/2020 | 09/02/2020 | 0 | TK_Complete | 1112893334 | 405 | 1112893334_405
C730D157BC###0069265 | TT_Task | Manufacturing SMTF[N] Depot DSER2 - DCS ODF | 01/05/2020 | 18/08/2020 | 11/02/2020 | 15/06/2020 | 0 | TK_Complete | 1112893334 | 405 | 1112893334_405
C730D157BC###0070040 | TT_Task | RFQ, BA, and PO SMTF[N] Depot CER2 - DCS ODF | 25/03/2020 | 30/04/2020 | 09/01/2020 | 20/02/2020 | 0 | TK_Complete | 1112893334 | 405 | 1112893334_405
C730D157BC###0070112 | TT_Task | Manufacturing SMTF[N] Depot CER2 - DCS ODF | 25/03/2020 | 17/07/2020 | 21/02/2020 | 13/10/2020 | 0 | TK_Complete | 1112893334 | 405 | 1112893334_405
C730D157BC###0017810 | TT_Task | RFQ, BA, and PO SMTF[N] Depot DSER2 - CBI AxCo Cubicle | 25/03/2020 | 30/04/2020 | 29/10/2019 | 23/02/2020 | 0 | TK_Complete | 1112893334 | 404 | 1112893334_404
C730D157BC###0017870 | TT_Task | Manufacturing SMTF[N] Depot DSER2 - CBI AxCo Cubicle | 01/05/2020 | 26/06/2020 | 26/03/2020 | 10/09/2020 | 0 | TK_Complete | 1112893334 | 404 | 1112893334_404
C730D157BC###0017970 | TT_Task | FAI/FAT SMTF[N] Depot DSER2 - CBI AxCo Cubicle | 03/08/2020 | 04/08/2020 | 29/06/2020 | 30/06/2020 | 0 | TK_Complete | 1112893334 | 404 | 1112893334_404
C730D157BC###0018030 | TT_Task | Material Delivery SMTF[N] Depot DSER2 - CBI AxCo Cubicle | 05/08/2020 | 18/08/2020 | 30/06/2020 | 18/12/2020 | 0 | TK_Complete | 1112893334 | 404 | 1112893334_404
C730D157BC###209423 | TT_Task | Material Delivery SMTF[N] Depot DSER2 - CBI AxCo Cubicle - #batch 1.1 (inc DSER1) | 05/08/2020 | 18/08/2020 | 30/06/2020 | 10/07/2020 | 0 | TK_Complete | 1112893334 | 404 | 1112893334_404
C730D157BC###209433 | TT_Task | Material Delivery SMTF[N] Depot DSER2 - CBI AxCo Cubicle - #batch 1.1.a | 26/10/2020 | 03/11/2020 | 20/10/2020 | 18/12/2020 | 0 | TK_Complete | 1112893334 | 404 | 1112893334_404
C730D157BC###0017730 | TT_Task | RFQ, BA, and PO SMTF[N] Depot DSER2 - CBI Relay Frame | 15/10/2019 | 25/11/2019 | 20/09/2019 | 29/12/2019 | 0 | TK_Complete | 1112893334 | 403 | 1112893334_403
C730D157BC###0017760 | TT_Task | Manufacturing SMTF[N] Depot DSER2 - CBI Relay Frame | 08/04/2020 | 28/08/2020 | 24/06/2020 | 09/09/2020 | 0 | TK_Complete | 1112893334 | 403 | 1112893334_403
C730D157BC###0017945 | TT_Task | FAI/FAT SMTF[N] Depot DSER2 - CBI Relay Frame | 14/10/2020 | 16/10/2020 | 10/09/2020 | 11/09/2020 | 0 | TK_Complete | 1112893334 | 403 | 1112893334_403
C730D157BC###0017955 | TT_Task | Material Delivery SMTF[N] Depot DSER2 - CBI Relay Frame - #batch 1.1.a | 19/10/2020 | 30/10/2020 | 12/09/2020 | 25/09/2020 | 0 | TK_Complete | 1112893334 | 403 | 1112893334_403
C730D157BC###0017825 | TT_Task | RFQ, BA, and PO SMTF[N] Depot DSER2 - CBI Relays | 01/11/2019 | 12/12/2019 | 23/09/2019 | 17/02/2020 | 0 | TK_Complete | 1112893334 | 403 | 1112893334_403
C730D157BC###0017880 | TT_Task | Manufacturing SMTF[N] Depot DSER2 - CBI Relays | 08/04/2020 | 21/08/2020 | 18/02/2020 | 22/06/2020 | 0 | TK_Complete | 1112893334 | 403 | 1112893334_403
C730D157BC###0018130 | TT_Task | FAI/FAT SMTF[N] Depot DSER2 - CBI Relays | 01/09/2020 | 03/09/2020 | 23/06/2020 | 23/06/2020 | 0 | TK_Complete | 1112893334 | 403 | 1112893334_403
C730D157BC###0018160 | TT_Task | Material Delivery SMTF[N] Depot DSER2 - CBI Relays - #batch 1.1.a | 04/09/2020 | 23/09/2020 | 29/06/2020 | 31/08/2020 | 0 | TK_Complete | 1112893334 | 403 | 1112893334_403
C730D157BC###0017965 | TT_Task | Material Delivery SMTF[N] Depot DSER2 - ATC SMIO #Batch 1.1 | 12/08/2020 | 25/08/2020 | 30/06/2020 | 15/07/2020 | 0 | TK_Complete | 1112893334 | 402 | 1112893334_402
C730D157BC###0018165 | TT_Task | Material Delivery SMTF[N] Depot DSER2 - CBI SMIO | 17/07/2020 | 10/09/2020 | 06/05/2020 | 25/09/2020 | 0 | TK_Complete | 1112893334 | 402 | 1112893334_402
C730D157BC###0009033 | TT_Task | Material Delivery SMTF[N] Depot DSER2 - CBI SMIO - #batch 1.1.a | 30/09/2020 | 20/10/2020 | 11/09/2020 | 25/09/2020 | 0 | TK_Complete | 1112893334 | 402 | 1112893334_402
C730D157BC###0209003 | TT_Task | Material Delivery SMTF[N] Depot DSER2 - CBI SMIO - #batch 1.1 | 13/07/2020 | 24/07/2020 | 06/05/2020 | 20/07/2020 | 0 | TK_Complete | 1112893334 | 402 | 1112893334_402
C730D157BC###0018155 | TT_Task | Material Delivery SMTF[N] Depot DSER2 - ATS BTN - #batch 1.1.a | 30/07/2020 | 18/08/2020 | 15/07/2020 | 15/10/2020 | 0 | TK_Complete | 1112893334 | 402 | 1112893334_402
C730D157BC###0018040 | TT_Task | Material Delivery SMTF[N] Depot DSER2 - DCS BTN - #batch 1.1.a | 30/11/2020 | 11/12/2020 | 03/11/2020 | 04/01/2021 | 0 | TK_Complete | 1112893334 | 402 | 1112893334_402
C730D157BC###0069272 | TT_Task | Material Delivery SMTF[N] Depot DSER2 - DCS ODF - #batch 1.1 | 25/06/2020 | 24/07/2020 | 19/06/2020 | 15/07/2020 | 0 | TK_Complete | 1112893334 | 402 | 1112893334_402
C730D157BC###0018045 | TT_Task | Material Delivery SMTF[N] Depot DSER2 - UPS - #batch 1.1.a | 29/10/2020 | 11/11/2020 | 13/10/2020 | 20/10/2020 | 0 | TK_Complete | 1112893334 | 402 | 1112893334_402
C730D157BC###0018055 | TT_Task | Material Delivery SMTF[N] Depot DSER2 - Incomer/Bypass - #batch 1.1.a | 29/10/2020 | 11/11/2020 | 13/10/2020 | 20/10/2020 | 0 | TK_Complete | 1112893334 | 402 | 1112893334_402
C730D157BC###0018065 | TT_Task | Material Delivery SMTF[N] Depot DSER2 - PDC #batch 1.1.a | 29/10/2020 | 11/11/2020 | 13/10/2020 | 20/10/2020 | 0 | TK_Complete | 1112893334 | 402 | 1112893334_402
C730D157BC###0017960 | TT_Task | FAI/FAT SMTF[N] Depot DSER2 - ATC SMIO | 10/08/2020 | 11/08/2020 | 27/06/2020 | 29/06/2020 | 0 | TK_Complete | 1112893334 | 401 | 1112893334_401
C730D157BC###0018140 | TT_Task | FAI/FAT SMTF[N] Depot DSER2 - CBI SMIO | 15/07/2020 | 23/07/2020 | 05/05/2020 | 10/09/2020 | 0 | TK_Complete | 1112893334 | 401 | 1112893334_401
C730D157BC###0018125 | TT_Task | FAI/FAT SMTF[N] Depot DSER2 - ATS BTN | 27/07/2020 | 29/07/2020 | 14/07/2020 | 14/07/2020 | 0 | TK_Complete | 1112893334 | 401 | 1112893334_401
C730D157BC###0017980 | TT_Task | FAI/FAT SMTF[N] Depot DSER2 - DCS BTN | 25/11/2020 | 27/11/2020 | 29/10/2020 | 30/10/2020 | 0 | TK_Complete | 1112893334 | 401 | 1112893334_401
C730D157BC###0069283 | TT_Task | FAI/FAT SMTF[N] Depot DSER2 - DCS ODF | 29/06/2020 | 01/07/2020 | 17/06/2020 | 17/06/2020 | 0 | TK_Complete | 1112893334 | 401 | 1112893334_401
C730D157BC###0017985 | TT_Task | FAI/FAT SMTF[N] Depot DSER2 - UPS | 28/10/2020 | 28/10/2020 | 13/10/2020 | 13/10/2020 | 0 | TK_Complete | 1112893334 | 401 | 1112893334_401
C730D157BC###0018005 | TT_Task | FAI/FAT SMTF[N] Depot DSER2 - PDC | 28/10/2020 | 28/10/2020 | 13/10/2020 | 13/10/2020 | 0 | TK_Complete | 1112893334 | 401 | 1112893334_401
C730D157BC###0018110 | TT_Task | FAI/FAT SMTF[N] Depot CER2 - CLC | 02/11/2020 | 04/11/2020 | 21/10/2020 | 22/10/2020 | 0 | TK_Complete | 1112893334 | 401 | 1112893334_401
C730D157BC###0070248 | TT_Task | FAI/FAT SMTF[N] Depot CER2 - DCS BTN | 02/11/2020 | 06/11/2020 | 16/10/2020 | 19/10/2020 | 0 | TK_Complete | 1112893334 | 401 | 1112893334_401
C730D157BC###0070208 | TT_Task | FAI/FAT SMTF[N] Depot CER2 - DCS ODF | 02/11/2020 | 04/11/2020 | 14/10/2020 | 15/10/2020 | 0 | TK_Complete | 1112893334 | 401 | 1112893334_401
C730D157BC###N209141 | TT_Task | FAI/FAT SMTF[N] Depot CER2 - PDC/UPS/ZC/CCTV | 02/11/2020 | 04/11/2020 | 14/10/2020 | 15/10/2020 | 0 | TK_Complete | 1112893334 | 401 | 1112893334_401
C730D157BC###0017745 | TT_Task | Manufacturing SMTF[N] Depot DSER2 - ATC SMIO | 08/04/2020 | 25/01/2021 | 13/12/2019 | 28/05/2020 | 0 | TK_Complete | 1112893334 | 400 | 1112893334_400
C730D157BC###0017750 | TT_Task | Manufacturing SMTF[N] Depot DSER2 - CBI SMIO | 08/04/2020 | 25/01/2021 | 13/12/2019 | 28/05/2020 | 0 | TK_Complete | 1112893334 | 400 | 1112893334_400
C730D157BC###0017865 | TT_Task | Manufacturing SMTF[N] Depot DSER2 - ATS BTN | 25/06/2020 | 28/09/2020 | 11/02/2020 | 13/07/2020 | 0 | TK_Complete | 1112893334 | 400 | 1112893334_400
C730D157BC###0017889 | TT_Task | Manufacturing SMTF[N] Depot DSER2 - DCS BTN | 01/05/2020 | 31/07/2020 | 11/02/2020 | 18/09/2020 | 0 | TK_Complete | 1112893334 | 400 | 1112893334_400
C730D157BC###0017890 | TT_Task | Manufacturing SMTF[N] Depot DSER2 - UPS | 27/04/2020 | 14/09/2020 | 24/04/2020 | 05/10/2020 | 0 | TK_Complete | 1112893334 | 400 | 1112893334_400
C730D157BC###0017910 | TT_Task | Manufacturing SMTF[N] Depot DSER2 - PDC | 09/06/2020 | 31/08/2020 | 23/04/2020 | 12/10/2020 | 0 | TK_Complete | 1112893334 | 400 | 1112893334_400
C730D157BC###0070144 | TT_Task | Manufacturing SMTF[N] Depot CER2 - DCS BTN | 25/03/2020 | 17/07/2020 | 12/02/2020 | 15/10/2020 | 0 | TK_Complete | 1112893334 | 400 | 1112893334_400
C720P147CF###0030470 | TT_Task | RFQ for detrainment doors | 25/02/2020 | 12/03/2020 | 31/10/2019 | 18/11/2019 | 0 | TK_Complete | 1112893334 | 40 | 1112893334_40
C720P147CF###0030560 | TT_Task | RFQ for passenger doors | 25/02/2020 | 12/03/2020 | 31/10/2019 | 18/11/2019 | 0 | TK_Complete | 1112893334 | 40 | 1112893334_40
C720D147CF###0037010 | TT_Task | Radio - Review of Training Plan | 25/08/2020 | 07/09/2020 | 17/08/2020 | 31/08/2020 | 0 | TK_Complete | 1112893334 | 4 | 1112893334_4
C720D147CF###0037030 | TT_Task | Radio - Review of Installation Procedure, Checklists and Verification Procedure | 26/10/2020 | 13/11/2020 | 01/10/2020 | 20/10/2020 | 0 | TK_Complete | 1112893334 | 4 | 1112893334_4
C730D157BC###0017715 | TT_Task | RFQ, BA, and PO SMTF[N] Depot DSER2 - ATC SMIO | 15/10/2019 | 25/11/2019 | 16/09/2019 | 03/11/2019 | 0 | TK_Complete | 1112893334 | 399 | 1112893334_399
C730D157BC###0017720 | TT_Task | RFQ, BA, and PO SMTF[N] Depot DSER2 - CBI SMIO | 15/10/2019 | 25/11/2019 | 24/09/2019 | 01/12/2019 | 0 | TK_Complete | 1112893334 | 399 | 1112893334_399
C730D157BC###0017805 | TT_Task | RFQ, BA, and PO SMTF[N] Depot DSER2 - ATS BTN | 27/04/2020 | 05/06/2020 | 04/12/2019 | 16/01/2020 | 0 | TK_Complete | 1112893334 | 399 | 1112893334_399
C730D157BC###0017830 | TT_Task | RFQ, BA, and PO SMTF[N] Depot DSER2 - DCS BTN | 25/03/2020 | 30/04/2020 | 30/10/2019 | 09/02/2020 | 0 | TK_Complete | 1112893334 | 399 | 1112893334_399
C730D157BC###0017835 | TT_Task | RFQ, BA, and PO SMTF[N] Depot DSER2 - UPS | 01/11/2019 | 12/12/2019 | 20/09/2019 | 07/04/2020 | 0 | TK_Complete | 1112893334 | 399 | 1112893334_399
C730D157BC###0017845 | TT_Task | RFQ, BA, and PO SMTF[N] Depot DSER2 - Incomer/Bypass | 27/04/2020 | 05/06/2020 | 20/09/2019 | 07/04/2020 | 0 | TK_Complete | 1112893334 | 399 | 1112893334_399
C730D157BC###0017855 | TT_Task | RFQ, BA, and PO SMTF[N] Depot DSER2 - PDC | 27/04/2020 | 05/06/2020 | 20/09/2019 | 07/04/2020 | 0 | TK_Complete | 1112893334 | 399 | 1112893334_399
C730D157BC###0010000 | TT_Task | RFQ, BA, and PO SMTF[N] Depot CER2 - DCS BTN | 01/05/2020 | 12/06/2020 | 09/12/2019 | 09/02/2020 | 0 | TK_Complete | 1112893334 | 399 | 1112893334_399
C730D157BC###N209132 | TT_Task | RFQ, BA, and PO SMTF[N] Depot CER2 - PDC/UPS/ZC/CCTV | 25/03/2020 | 30/04/2020 | 09/01/2020 | 20/02/2020 | 0 | TK_Complete | 1112893334 | 399 | 1112893334_399
C730D157BC###0017820 | TT_Task | RFQ, BA, and PO SMTF[N] Depot DSER2 - CCTV BTN | 27/04/2020 | 05/06/2020 | 04/12/2019 | 04/12/2019 | 0 | TK_Complete | 1112893334 | 399 | 1112893334_399
C730D157BC###0069193 | TT_Task | Manufacturing SMTF[N] Depot DSER1 - CBI Cable Frame | 01/05/2020 | 16/11/2020 | 24/02/2020 | 14/08/2020 | 0 | TK_Complete | 1112893334 | 398 | 1112893334_398
C730D157BC###0069214 | TT_Task | FAI/FAT SMTF[N] Depot DSER1 - CBI Cable Frame | 25/08/2020 | 27/08/2020 | 17/08/2020 | 17/08/2020 | 0 | TK_Complete | 1112893334 | 398 | 1112893334_398
C730D157BC###0069204 | TT_Task | Material Delivery SMTF[N] Depot DSER1 - CBI Cable Frame #Batch1.1.a | 25/08/2020 | 06/10/2020 | 18/08/2020 | 24/09/2020 | 0 | TK_Complete | 1112893334 | 398 | 1112893334_398
C730D157BC###0017755 | TT_Task | Manufacturing SMTF[N] Depot DSER2 - CBI Cable Frame | 01/05/2020 | 11/09/2020 | 24/06/2020 | 03/02/2021 | 0 | TK_Complete | 1112893334 | 398 | 1112893334_398
C730D157BC###0017940 | TT_Task | FAI/FAT SMTF[N] Depot DSER2 - CBI Cable Frame | 12/10/2020 | 14/10/2020 | 14/08/2020 | 17/08/2020 | 0 | TK_Complete | 1112893334 | 398 | 1112893334_398
C730D157BC###0017950 | TT_Task | Material Delivery SMTF[N] Depot DSER2 - CBI Cable Frame - #batch 1.1.a | 15/10/2020 | 23/10/2020 | 12/09/2020 | 10/02/2021 | 0 | TK_Complete | 1112893334 | 398 | 1112893334_398
C730D157BC###0070296 | TT_Task | FAI/FAT SMTF[N] Depot - Cables | 05/08/2020 | 06/08/2020 | 21/07/2020 | 29/01/2021 | 0 | TK_Complete | 1112893334 | 398 | 1112893334_398
C730D157BC###0069182 | TT_Task | RFQ, BA, and PO SMTF[N] Depot DSER1 - CBI Cable Frame | 15/10/2019 | 25/11/2019 | 24/09/2019 | 23/02/2020 | 0 | TK_Complete | 1112893334 | 397 | 1112893334_397
C730D157BC###0017725 | TT_Task | RFQ, BA, and PO SMTF[N] Depot DSER2 - CBI Cable Frame | 15/10/2019 | 25/11/2019 | 24/09/2019 | 23/02/2020 | 0 | TK_Complete | 1112893334 | 397 | 1112893334_397
C730D157BC###0070008 | TT_Task | RFQ, BA, and PO SMTF[N] Depot - Cables | 15/10/2019 | 25/11/2019 | 24/09/2019 | 26/06/2020 | 0 | TK_Complete | 1112893334 | 397 | 1112893334_397
C730P147CT###0030290 | TT_Task | RFQ, BA, and PO All Trackside Cables | 25/05/2020 | 13/07/2020 | 09/12/2019 | 27/05/2020 | 0 | TK_Complete | 1112893334 | 397 | 1112893334_397
C730P147CT###0030300 | TT_Task | RFQ, BA, and PO All Room Cables | 25/05/2020 | 13/07/2020 | 09/12/2019 | 24/05/2021 | 0 | TK_Complete | 1112893334 | 397 | 1112893334_397
C730D157BC###0069281 | TT_Task | RFQ, BA, and PO SMTF[N] Depot DSER2 - Room Cables (*redundant with trackside cables) | 01/11/2019 | 12/12/2019 | 24/09/2019 | 24/09/2019 | 0 | TK_Complete | 1112893334 | 397 | 1112893334_397
C730P147CT###0032650 | TT_Task | SMTF[N] - System BOQ (ST2) | 01/11/2019 | 01/11/2019 | 17/05/2019 | 17/05/2019 | 0 | TK_Complete | 1112893334 | 396 | 1112893334_396
C730D147CT###D87070 | TT_Task | Delay to SMTF-N MS#2 Go Live by the Integrator | 02/02/2022 | 19/03/2022 | 16/12/2021 | 06/02/2022 | 0 | TK_Complete | 1112893334 | 396 | 1112893334_396
C730D157BC###0065010 | TT_Task | T;C [Sytem-wide] Customer review Specification for Integrated Test | 26/10/2020 | 27/11/2020 | 12/10/2020 | 11/12/2020 | 0 | TK_Complete | 1112893334 | 395 | 1112893334_395
C730D157BC###0065030 | TT_Task | T;C [Sytem-wide] Customer review Specification for System Acceptance test | 02/12/2020 | 12/01/2021 | 26/10/2020 | 05/02/2021 | 0 | TK_Complete | 1112893334 | 395 | 1112893334_395
C730D157BC###0065035 | TT_Task | T;C [Sytem-wide] Customer review System Demonstration Testing Plan | 02/12/2020 | 12/01/2021 | 13/10/2020 | 11/12/2020 | 0 | TK_Complete | 1112893334 | 395 | 1112893334_395
C730D157BC###N569453 | TT_Task | T;C (System Wide) - PAT Plan | 28/09/2020 | 28/10/2020 | 05/10/2020 | 23/10/2020 | 0 | TK_Complete | 1112893334 | 394 | 1112893334_394
C730D157BC###N949433 | TT_Task | T;C (System Wide) - SAT Plan | 28/09/2020 | 28/10/2020 | 01/10/2020 | 12/10/2020 | 0 | TK_Complete | 1112893334 | 394 | 1112893334_394
C730D157BC###0045660 | TT_Task | T;C (System Wide) - Test Reports IFAT 2 Readiness | 25/03/2022 | 28/04/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 393 | 1112893334_393
C730D157BC###0065045 | TT_Task | T;C [Sytem-wide] Customer review Test Reports IFAT 2 Readiness | 29/04/2022 | 02/06/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 393 | 1112893334_393
C730D157BC###0045650 | TT_Task | T;C (System Wide) - Specification for Tests on Practicial Completion | 02/12/2020 | 06/01/2021 | 05/10/2020 | 23/10/2020 | 0 | TK_Complete | 1112893334 | 392 | 1112893334_392
C730D157BC###0065040 | TT_Task | T;C [Sytem-wide] Customer review Specification for Tests on Practicial Completion | 07/01/2021 | 10/02/2021 | 26/10/2020 | 29/01/2021 | 0 | TK_Complete | 1112893334 | 392 | 1112893334_392
C730D157BC###0045620 | TT_Task | T;C (System Wide) - Post Installation ; Test Procedures | 04/12/2020 | 11/01/2021 | 21/09/2020 | 12/10/2020 | 0 | TK_Complete | 1112893334 | 391 | 1112893334_391
C730D157BC###0065025 | TT_Task | T;C [Sytem-wide] Customer review Post Installation ; Test Procedures | 02/12/2020 | 12/01/2021 | 13/10/2020 | 27/11/2020 | 0 | TK_Complete | 1112893334 | 391 | 1112893334_391
C730D157BC###0045590 | TT_Task | T;C (System Wide) - Specification for Integrated Test | 28/09/2020 | 28/10/2020 | 07/09/2020 | 09/10/2020 | 0 | TK_Complete | 1112893334 | 390 | 1112893334_390
C730D157BC###0045630 | TT_Task | T;C (System Wide) - Specification for System Acceptance test | 02/11/2020 | 01/12/2020 | 05/10/2020 | 23/10/2020 | 0 | TK_Complete | 1112893334 | 390 | 1112893334_390
C730D157BC###0045640 | TT_Task | T;C (System Wide) - System Demonstration Testing Plan | 12/01/2021 | 10/02/2021 | 28/09/2020 | 12/10/2020 | 0 | TK_Complete | 1112893334 | 390 | 1112893334_390
C730D157BC###N949443 | TT_Task | T;C (System Wide) - Test Programme Plan | 28/09/2020 | 28/10/2020 | 05/10/2020 | 12/10/2020 | 0 | TK_Complete | 1112893334 | 390 | 1112893334_390
C720P147CF###0030460 | TT_Task | RFQ for grabpoles and grab handles | 25/02/2020 | 23/03/2020 | 31/10/2019 | 18/11/2019 | 0 | TK_Complete | 1112893334 | 39 | 1112893334_39
C720P147CF###0030670 | TT_Task | RFQ for hand rails | 25/02/2020 | 12/03/2020 | 31/10/2019 | 19/11/2019 | 0 | TK_Complete | 1112893334 | 39 | 1112893334_39
C730D157BC###0045580 | TT_Task | T;C (System Wide) - Specification for Commissioning | 28/09/2020 | 28/10/2020 | 14/09/2020 | 09/10/2020 | 0 | TK_Complete | 1112893334 | 389 | 1112893334_389
C730D157BC###N949453 | TT_Task | T;C (System Wide) - Testing and Commissioning (T;C) Plan | 28/09/2020 | 28/10/2020 | 02/08/2020 | 12/10/2020 | 0 | TK_Complete | 1112893334 | 389 | 1112893334_389
C730D157BC###0065005 | TT_Task | T;C [Sytem-wide] Customer review Specification for Commissioning | 26/10/2020 | 27/11/2020 | 12/10/2020 | 18/11/2020 | 0 | TK_Complete | 1112893334 | 389 | 1112893334_389
C730D157BC###0045570 | TT_Task | T;C (System Wide) - PAT procedures for CBTC Equipment | 28/09/2020 | 28/10/2020 | 20/08/2020 | 16/10/2020 | 0 | TK_Complete | 1112893334 | 388 | 1112893334_388
C730D157BC###0045600 | TT_Task | T;C (System Wide) - SIT procedures for CBTC Equipment | 04/11/2020 | 03/12/2020 | 12/10/2020 | 26/10/2020 | 0 | TK_Complete | 1112893334 | 388 | 1112893334_388
C730D157BC###0045610 | TT_Task | T;C (System Wide) - SAT procedures for CBTC Equipment | 02/11/2020 | 01/12/2020 | 12/10/2020 | 06/11/2020 | 0 | TK_Complete | 1112893334 | 388 | 1112893334_388
C730D157BC###0065000 | TT_Task | T;C [Sytem-wide] Customer review PAT procedures for CBTC Equipment | 26/10/2020 | 27/11/2020 | 19/10/2020 | 05/02/2021 | 0 | TK_Complete | 1112893334 | 388 | 1112893334_388
C730D157BC###0065015 | TT_Task | T;C [Sytem-wide] Customer review SIT procedures for CBTC Equipment | 02/11/2020 | 04/12/2020 | 20/10/2020 | 11/03/2021 | 0 | TK_Complete | 1112893334 | 388 | 1112893334_388
C730D157BC###0065020 | TT_Task | T;C [Sytem-wide] Customer review SAT procedures for CBTC Equipment | 02/12/2020 | 12/01/2021 | 09/11/2020 | 30/06/2021 | 0 | TK_Complete | 1112893334 | 388 | 1112893334_388
C730D156BC###0081955 | TT_Task | CBTC/As-Built SMCSW[City] - Chatswood - Room Layout | 09/05/2023 | 22/05/2023 | nan | nan | 0 | TK_NotStart | 1112893334 | 387 | 1112893334_387
C730D156BC###0081967 | TT_Task | CBTC/As-Built SMCSW[City] - Victoria Cross - Room Layout | 23/05/2023 | 05/06/2023 | nan | nan | 0 | TK_NotStart | 1112893334 | 387 | 1112893334_387
C730D156BC###0081970 | TT_Task | CBTC/As-Built SMCSW[City] - Barangaroo - Room Layout | 23/05/2023 | 05/06/2023 | nan | nan | 0 | TK_NotStart | 1112893334 | 387 | 1112893334_387
C730D156BC###0081973 | TT_Task | CBTC/As-Built SMCSW[City] - Martin Place - Room Layout | 23/05/2023 | 05/06/2023 | nan | nan | 0 | TK_NotStart | 1112893334 | 387 | 1112893334_387
C730D156BC###0081976 | TT_Task | CBTC/As-Built SMCSW[City] - Pitt Street - Room Layout | 06/06/2023 | 19/06/2023 | nan | nan | 0 | TK_NotStart | 1112893334 | 387 | 1112893334_387
C730D156BC###0081979 | TT_Task | CBTC/As-Built SMCSW[City] - Central - Room Layout | 06/06/2023 | 19/06/2023 | nan | nan | 0 | TK_NotStart | 1112893334 | 387 | 1112893334_387
C730D156BC###0081982 | TT_Task | CBTC/As-Built SMCSW[City] - Waterloo - Room Layout | 06/06/2023 | 19/06/2023 | nan | nan | 0 | TK_NotStart | 1112893334 | 387 | 1112893334_387
C730D156BC###0081985 | TT_Task | CBTC/As-Built SMCSW[City] - SMTF (South) - Room Layout | 06/06/2023 | 19/06/2023 | nan | nan | 0 | TK_NotStart | 1112893334 | 387 | 1112893334_387
C730D156BC###0081991 | TT_Task | CBTC/As-Built SMCSW[City] - Sydenham - Room Layout | 06/06/2023 | 19/06/2023 | nan | nan | 0 | TK_NotStart | 1112893334 | 387 | 1112893334_387
C730D156BC###0081871 | TT_Task | T;C (City+SMTF-S) - PAT Test Reports | 13/01/2023 | 09/02/2023 | nan | nan | 0 | TK_NotStart | 1112893334 | 386 | 1112893334_386
C730D156BC###0081904 | TT_Task | T;C (City+SMTF-S) - SIT Test Reports | 27/03/2023 | 21/04/2023 | nan | nan | 0 | TK_NotStart | 1112893334 | 386 | 1112893334_386
C730D156BC###0081940 | TT_Task | T;C (City+SMTF-S) - SAT Test Reports | 16/05/2023 | 12/06/2023 | nan | nan | 0 | TK_NotStart | 1112893334 | 386 | 1112893334_386
C730D156BC###N381991 | TT_Task | T;C (City+SMTF-S) - System Demonstration Test Reports | 23/05/2023 | 19/06/2023 | nan | nan | 0 | TK_NotStart | 1112893334 | 386 | 1112893334_386
C730D156BC###0081886 | TT_Task | T;C (City+SMTF-S) - PAT Test Reports customer review ; acceptance | 10/02/2023 | 02/03/2023 | nan | nan | 288 | TK_NotStart | 1112893334 | 386 | 1112893334_386
C730D156BC###0081913 | TT_Task | T;C (City+SMTF-S) - SIT Test Reports customer review ; acceptance | 24/04/2023 | 12/05/2023 | nan | nan | 168 | TK_NotStart | 1112893334 | 386 | 1112893334_386
C730D156BC###0081964 | TT_Task | T;C (City+SMTF-S) - SAT Test Reports customer review ; acceptance | 13/06/2023 | 03/07/2023 | nan | nan | 144 | TK_NotStart | 1112893334 | 386 | 1112893334_386
C730D156BC###82001 | TT_Task | T;C (City+SMTF-S) - System Demonstration Test Reports customer review ; acceptance | 20/06/2023 | 10/07/2023 | nan | nan | 104 | TK_NotStart | 1112893334 | 386 | 1112893334_386
C730D156BC###0081775 | TT_Task | SMCSW[City] - Baseline - 3.1.1.0 City Post Stage 3 - Baseline for Site Installation | 14/11/2022 | 09/12/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 385 | 1112893334_385
C730D156BC###0081850 | TT_Task | SMCSW[City] - Baseline - 3.2.1.3 City Post Stage 3 - Baseline for Site Testing - Static Testing - TDC1 | 12/12/2022 | 23/12/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 385 | 1112893334_385
C730D156BC###0081877 | TT_Task | SMCSW[City] - Baseline - 3.2.1.4 City Post Stage 3 - Baseline for Site Testing - Static Testing - TDC2 | 23/01/2023 | 03/02/2023 | nan | nan | 0 | TK_NotStart | 1112893334 | 385 | 1112893334_385
C730D156BC###0081880 | TT_Task | SMCSW[City] - Baseline - 3.2.1.5 City Post Stage 3 - Baseline for Site Testing - Low Speed Testing | 26/12/2022 | 06/01/2023 | nan | nan | 176 | TK_NotStart | 1112893334 | 385 | 1112893334_385
C730D156BC###0081889 | TT_Task | SMCSW[City] - Baseline - 3.2.1.6 City Post Stage 3 - Baseline for Site Testing - High Speed Testing | 01/03/2023 | 14/03/2023 | nan | nan | 0 | TK_NotStart | 1112893334 | 385 | 1112893334_385
C730D156BC###0081895 | TT_Task | SMCSW[City] - Baseline - 3.2.1.7 City Post Stage 3 - City Post Stage 3 - Baseline for Site Testing - Multiple Trains | 15/03/2023 | 28/03/2023 | nan | nan | 0 | TK_NotStart | 1112893334 | 385 | 1112893334_385
C730D156BC###0081898 | TT_Task | SMCSW[City] -Baseline - 3.2.1.8 City Post Stage 3 - City Post Stage 3 - Baseline for Site Testing - Trail Running | 29/03/2023 | 25/04/2023 | nan | nan | 536 | TK_NotStart | 1112893334 | 385 | 1112893334_385
C730D157BC###0012248 | TT_Task | CBTC/Stage-3 SMCSW[City] - Customer closure of comments Point Machine Installation | 31/08/2021 | 15/09/2021 | 02/08/2021 | 25/08/2021 | 0 | TK_Complete | 1112893334 | 384 | 1112893334_384
C730D157BC###0012260 | TT_Task | CBTC/Stage-3 SMCSW[City] - Customer closure of comments Boxes (SAB ; Point Machines) Installation | 31/08/2021 | 15/09/2021 | 02/08/2021 | 25/08/2021 | 0 | TK_Complete | 1112893334 | 384 | 1112893334_384
C730D157BC###0208973 | TT_Task | CBTC/Stage-3 SMCSW[City] - Customer closure of comments MB Installation | 31/08/2021 | 15/09/2021 | 04/08/2021 | 25/08/2021 | 0 | TK_Complete | 1112893334 | 384 | 1112893334_384
C730D156BC###0081793 | TT_Task | CBTC/Stage-3 SMCSW[SMTF-S] - Customer closure of comments Point Machine Installation - D84M | 02/09/2021 | 17/09/2021 | 09/08/2021 | 25/08/2021 | 0 | TK_Complete | 1112893334 | 384 | 1112893334_384
C730D156BC###0081799 | TT_Task | CBTC/Stage-3 SMCSW[SMTF-S] - Customer closure of comments Point Machine Installation - MATR | 02/09/2021 | 17/09/2021 | 09/08/2021 | 25/08/2021 | 0 | TK_Complete | 1112893334 | 384 | 1112893334_384
C730D157BC###N89453 | TT_Task | CBTC/Stage-3 SMCSW[City] - Final Drawings Buffer Light Installation -TBC - Temporary BS - Cancelled | 29/03/2021 | 16/04/2021 | 25/02/2021 | 25/02/2021 | 0 | TK_Complete | 1112893334 | 383 | 1112893334_383
C730D156BC###0081937 | TT_Task | CBTC/As-Built SMCSW[City] - PPI ; RI Installation Drawings | 25/04/2023 | 08/05/2023 | nan | nan | 0 | TK_NotStart | 1112893334 | 383 | 1112893334_383
C730D156BC###0081946 | TT_Task | CBTC/As-Built SMCSW[City] - SAB Installation Drawings | 09/05/2023 | 22/05/2023 | nan | nan | 0 | TK_NotStart | 1112893334 | 383 | 1112893334_383
C730D156BC###0081961 | TT_Task | CBTC/As-Built SMCSW[City] - Buffer Light Installation Drawings | 09/05/2023 | 22/05/2023 | nan | nan | 0 | TK_NotStart | 1112893334 | 383 | 1112893334_383
C730D157BC###0011030 | TT_Task | CBTC/Stage-3 SMCSW - Inital ITS 'Signalling System' (PSD/SIG) | 25/08/2020 | 07/09/2020 | 14/08/2020 | 04/09/2020 | 0 | TK_Complete | 1112893334 | 382 | 1112893334_382
C730D157BC###0011036 | TT_Task | CBTC/Stage-3 SMCSW - Inital ITS 'Signalling System' (CCS/SIG) | 08/05/2020 | 28/05/2020 | 13/01/2020 | 24/01/2020 | 0 | TK_Complete | 1112893334 | 382 | 1112893334_382
C730D157BC###0011039 | TT_Task | CBTC/Stage-3 SMCSW - Inital ITS 'Signalling System' (COM/SIG) | 25/08/2020 | 07/09/2020 | 11/08/2020 | 04/09/2020 | 0 | TK_Complete | 1112893334 | 382 | 1112893334_382
C730D157BC###0061748 | TT_Task | CBTC/Stage-3 SMCSW - Final ITS 'Signalling System' (PSD/SIG) | 13/10/2020 | 30/11/2020 | 14/08/2020 | 04/09/2020 | 0 | TK_Complete | 1112893334 | 382 | 1112893334_382
C730D157BC###0061766 | TT_Task | CBTC/Stage-3 SMCSW - Final ITS 'Signalling System' (CCS/SIG) | 25/08/2020 | 13/10/2020 | 03/08/2020 | 07/09/2020 | 0 | TK_Complete | 1112893334 | 382 | 1112893334_382
C730D157BC###0061775 | TT_Task | CBTC/Stage-3 SMCSW - Final ITS 'Signalling System' (COM/SIG) | 13/10/2020 | 30/11/2020 | 11/08/2020 | 04/09/2020 | 0 | TK_Complete | 1112893334 | 382 | 1112893334_382
C730D157BC###0031919 | TT_Task | CBTC/Stage-3 SMCSW - Procedure for Ergonomic Trials | 07/04/2021 | 19/05/2021 | 08/02/2021 | 23/04/2021 | 0 | TK_Complete | 1112893334 | 381 | 1112893334_381
C730D157BC###0031973 | TT_Task | CBTC/Stage-3 SMCSW - Results for Ergonomic Trials | 19/09/2022 | 28/10/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 381 | 1112893334_381
C730D157BC###0031703 | TT_Task | CBTC/Stage-3 SMCSW - Human Computer Assessment Report for ISM | 09/11/2020 | 18/12/2020 | 14/09/2020 | 13/01/2021 | 0 | TK_Complete | 1112893334 | 380 | 1112893334_380
C730D157BC###0031730 | TT_Task | CBTC/Stage-3 SMCSW - Human Computer Assessment Report for ATS | 05/03/2021 | 15/04/2021 | 28/12/2020 | 13/01/2021 | 0 | TK_Complete | 1112893334 | 380 | 1112893334_380
C720P147CF###0030440 | TT_Task | RFQ for EUF | 25/02/2020 | 12/03/2020 | 31/10/2019 | 18/11/2019 | 0 | TK_Complete | 1112893334 | 38 | 1112893334_38
C720P147CF###0030690 | TT_Task | RFQ for gangway | 25/02/2020 | 12/03/2020 | 31/10/2019 | 18/11/2019 | 0 | TK_Complete | 1112893334 | 38 | 1112893334_38
C720P147CF###0030700 | TT_Task | RFQ for PACIS | 25/02/2020 | 12/03/2020 | 31/10/2019 | 18/11/2019 | 0 | TK_Complete | 1112893334 | 38 | 1112893334_38
C720P147CF###0030590 | TT_Task | RFQ for bogie frame | 25/02/2020 | 23/03/2020 | 31/10/2019 | 27/11/2019 | 0 | TK_Complete | 1112893334 | 38 | 1112893334_38
C730D157BC###N27387 | TT_Task | CBTC/Stage-3 SMCSW - Intermediate - CBI Cable layout - Barangaroo Station (BGU) | 10/11/2020 | 16/11/2020 | 09/11/2020 | 13/11/2020 | 0 | TK_Complete | 1112893334 | 379 | 1112893334_379
C730D157BC###N27397 | TT_Task | CBTC/Stage-3 SMCSW - Intermediate - CBI Cable layout - Crows Nest Station (CST) | 10/11/2020 | 16/11/2020 | 09/11/2020 | 13/11/2020 | 0 | TK_Complete | 1112893334 | 379 | 1112893334_379
C730D157BC###N27407 | TT_Task | CBTC/Stage-3 SMCSW - Intermediate - CBI Cable layout - Victoria Cross Station (VIC) | 09/12/2020 | 15/12/2020 | 16/11/2020 | 19/11/2020 | 0 | TK_Complete | 1112893334 | 379 | 1112893334_379
C730D157BC###N27417 | TT_Task | CBTC/Stage-3 SMCSW - Intermediate - CBI Cable layout - Martin Place Station (MPL) | 23/12/2020 | 05/01/2021 | 16/11/2020 | 19/11/2020 | 0 | TK_Complete | 1112893334 | 379 | 1112893334_379
C730D157BC###N27437 | TT_Task | CBTC/Stage-3 SMCSW - Intermediate - CBI Cable layout - Waterloo Station (WLO) | 25/11/2020 | 01/12/2020 | 11/11/2020 | 17/11/2020 | 0 | TK_Complete | 1112893334 | 379 | 1112893334_379
C730D157BC###N27447 | TT_Task | CBTC/Stage-3 SMCSW - Intermediate - CBI Cable layout - Central Station (CEN) | 02/12/2020 | 08/12/2020 | 11/11/2020 | 17/11/2020 | 0 | TK_Complete | 1112893334 | 379 | 1112893334_379
C730D157BC###N27457 | TT_Task | CBTC/Stage-3 SMCSW - Intermediate - CBI Cable layout - Pitt Street Station (PIT) | 25/11/2020 | 01/12/2020 | 17/11/2020 | 23/11/2020 | 0 | TK_Complete | 1112893334 | 379 | 1112893334_379
C730D157BC###N27467 | TT_Task | CBTC/Stage-3 SMCSW - Intermediate - CBI Cable layout - Chatswood Station (CHW) | 12/01/2021 | 22/01/2021 | 25/11/2020 | 30/11/2020 | 0 | TK_Complete | 1112893334 | 379 | 1112893334_379
C730D157BC###N027387 | TT_Task | Internal BOQ to Facilitate the Procurement (City and SW) | 10/11/2020 | 19/11/2020 | 21/09/2020 | 30/09/2020 | 0 | TK_Complete | 1112893334 | 378 | 1112893334_378
C730D157BC###N509453 | TT_Task | CBTC/Stage-3 SMCSW - Information Security Plan | 26/10/2020 | 10/12/2020 | 10/09/2020 | 29/10/2020 | 0 | TK_Complete | 1112893334 | 377 | 1112893334_377
C730D157BC###N209093 | TT_Task | CBTC/Stage-3 SMCSW - Cyber Security Detail Design Specification | 04/10/2021 | 01/11/2021 | 06/09/2021 | nan | 0 | TK_Active | 1112893334 | 377 | 1112893334_377
C730D157BC###N209103 | TT_Task | CBTC/Stage-3 SMCSW - Cyber Security Preliminary Risk Assessment Register | 25/08/2021 | 30/09/2021 | 26/07/2021 | 25/02/2022 | 0 | TK_Complete | 1112893334 | 377 | 1112893334_377
C730D157BC###N209113 | TT_Task | CBTC/Stage-3 SMCSW - Cyber Security Detail Risk Assessment Register | 04/10/2021 | 01/11/2021 | 06/09/2021 | nan | 0 | TK_Active | 1112893334 | 377 | 1112893334_377
C730D157BC###N209133 | TT_Task | CBTC/Stage-3 SMCSW - Cyber Security Vulnerability Assessment Report | 25/03/2022 | 30/06/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 377 | 1112893334_377
C730D157BC###N209153 | TT_Task | CBTC/Stage-3 SMCSW - Cyber Security Testing Procedure | 10/06/2022 | 30/06/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 377 | 1112893334_377
C730D157BC###N209463 | TT_Task | CBTC/Stage-3 SMCSW - Cyber Security System Requirements and and Architecture Description | 10/05/2021 | 18/06/2021 | 22/03/2021 | 28/04/2021 | 0 | TK_Complete | 1112893334 | 377 | 1112893334_377
C730D157BC###N599473 | TT_Task | CBTC/Stage-3 SMCSW - Cyber Security Plan | 25/03/2021 | 31/03/2021 | 22/02/2021 | 26/02/2021 | 0 | TK_Complete | 1112893334 | 377 | 1112893334_377
C730D157BC###N629453 | TT_Task | CBTC/Stage-3 SMCSW - Cyber Security Preliminary Design Specification | 29/03/2021 | 07/05/2021 | 22/03/2021 | 28/04/2021 | 0 | TK_Complete | 1112893334 | 377 | 1112893334_377
C730D157BC###0027213 | TT_Task | CBTC/Stage-3 SMCSW - Scheme Plan - Mainline | 05/02/2021 | 04/03/2021 | 07/01/2021 | 15/02/2021 | 0 | TK_Complete | 1112893334 | 376 | 1112893334_376
C730D157BC###0027219 | TT_Task | CBTC/Stage-3 SMCSW - Scheme Plan[S] - Depot | 08/01/2021 | 04/02/2021 | 09/12/2020 | 02/02/2021 | 0 | TK_Complete | 1112893334 | 376 | 1112893334_376
C730D157BC###N529463 | TT_Task | CBTC/Stage-3 SMCSW - Scheme Plan - Mainline (Rework if/when required) | 25/10/2021 | 19/11/2021 | 25/10/2021 | 19/11/2021 | 0 | TK_Complete | 1112893334 | 376 | 1112893334_376
C730D157BC###N539453 | TT_Task | CBTC/Stage-3 SMCSW - Scheme Plan[S] - Depot (Rework) | 25/10/2021 | 19/11/2021 | 25/10/2021 | 19/11/2021 | 0 | TK_Complete | 1112893334 | 376 | 1112893334_376
C730D157BC###N654153 | TT_Task | CBTC/Stage-3 SMCSW - Scheme Plan - City Mainline Customer review comments | 25/02/2021 | 17/03/2021 | 15/02/2021 | 31/08/2021 | 0 | TK_Complete | 1112893334 | 376 | 1112893334_376
C730D157BC###0022297 | TT_Task | CBTC/Stage-3 SMCSW - Scheme Plan Verification | 19/09/2022 | 07/10/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 376 | 1112893334_376
C730D157BC###0027225 | TT_Task | CBTC/Stage-2 SMCSW [City] - Alstom closure of comments PPI Installation | 31/08/2020 | 15/09/2020 | 14/04/2020 | 14/04/2020 | 0 | TK_Complete | 1112893334 | 375 | 1112893334_375
C730D157BC###0027087 | TT_Task | CBTC/Stage-2 SMCSW [SMTF-S] - Alstom closure of comments PPI Installation | 30/06/2020 | 15/07/2020 | 01/05/2020 | 08/05/2020 | 0 | TK_Complete | 1112893334 | 375 | 1112893334_375
C730D157BC###0012242 | TT_Task | CBTC/Stage-3 SMCSW[City] - Customer closure of comments PPI Installation | 31/08/2021 | 15/09/2021 | 27/07/2021 | 25/08/2021 | 0 | TK_Complete | 1112893334 | 375 | 1112893334_375
C730D156BC###0081745 | TT_Task | CBTC/Stage-3 SMCSW[SMTF-S] - Customer closure of comments PPI Installation | 01/09/2021 | 16/09/2021 | 05/08/2021 | 25/08/2021 | 0 | TK_Complete | 1112893334 | 375 | 1112893334_375
C730D157BC###0027171 | TT_Task | CBTC/Stage-2 SMCSW [City] - Alstom closure of comments Point Machine Installation | 31/08/2020 | 15/09/2020 | 14/07/2020 | 14/07/2020 | 0 | TK_Complete | 1112893334 | 374 | 1112893334_374
C730D157BC###0027231 | TT_Task | CBTC/Stage-2 SMCSW [City] - Alstom closure of comments Marker Board Installation | 28/07/2020 | 12/08/2020 | 14/07/2020 | 14/07/2020 | 0 | TK_Complete | 1112893334 | 374 | 1112893334_374
C730D157BC###0027093 | TT_Task | CBTC/Stage-2 SMCSW [SMTF-S] - Alstom closure of comments Point Machine Installation - D84M | 16/07/2020 | 31/07/2020 | 01/05/2020 | 08/05/2020 | 0 | TK_Complete | 1112893334 | 374 | 1112893334_374
C730D157BC###0027147 | TT_Task | CBTC/Stage-2 SMCSW [SMTF-S] - Alstom closure of comments Buffer Stop Installation | 19/08/2020 | 03/09/2020 | 01/05/2020 | 08/05/2020 | 0 | TK_Complete | 1112893334 | 374 | 1112893334_374
C730D157BC###0027267 | TT_Task | CBTC/Stage-2 SMCSW [SMTF-S] - Alstom closure of comments Point Machine Installation - MATR | 22/09/2020 | 08/10/2020 | 11/05/2020 | 18/05/2020 | 0 | TK_Complete | 1112893334 | 374 | 1112893334_374
C730D157BC###0027363 | TT_Task | CBTC/Stage-2 SMCSW [SMTF-S] - Alstom closure of comments Marker Board Installation | 03/11/2020 | 18/11/2020 | 28/07/2020 | 28/07/2020 | 0 | TK_Complete | 1112893334 | 374 | 1112893334_374
C730D157BC###0027129 | TT_Task | CBTC/Stage-2 SMCSW [City] - Alstom closure of comments Balise Installation | 27/07/2020 | 11/08/2020 | 08/05/2020 | 08/05/2020 | 0 | TK_Complete | 1112893334 | 373 | 1112893334_373
C730D157BC###0027111 | TT_Task | CBTC/Stage-2 SMCSW [SMTF-S] - Alstom closure of comments Balise Installation | 03/08/2020 | 18/08/2020 | 01/05/2020 | 08/05/2020 | 0 | TK_Complete | 1112893334 | 373 | 1112893334_373
C730D157BC###0012239 | TT_Task | CBTC/Stage-3 SMCSW[City] - Customer closure of comments Balise Installation | 31/08/2021 | 15/09/2021 | 27/07/2021 | 25/08/2021 | 0 | TK_Complete | 1112893334 | 373 | 1112893334_373
C730D156BC###0081748 | TT_Task | CBTC/Stage-3 SMCSW[SMTF-S] - Customer closure of comments Balise Installation | 02/09/2021 | 17/09/2021 | 05/08/2021 | 25/08/2021 | 0 | TK_Complete | 1112893334 | 373 | 1112893334_373
C730D157BC###0027099 | TT_Task | CBTC/Stage-2 SMCSW [City] - Alstom closure of comments Boxes (SAB ; SPB) Installation | 27/07/2020 | 11/08/2020 | 16/04/2020 | 16/04/2020 | 0 | TK_Complete | 1112893334 | 372 | 1112893334_372
C730D157BC###0027279 | TT_Task | CBTC/Stage-2 SMCSW [SMTF-S] - Alstom closure of comments Boxes (SAB ; SPB) Installation | 29/09/2020 | 15/10/2020 | 01/06/2020 | 01/06/2020 | 0 | TK_Complete | 1112893334 | 372 | 1112893334_372
C730D156BC###0081742 | TT_Task | CBTC/Stage-3 SMCSW[SMTF-S] - Customer closure of comments Boxes (SAB ; SPB) Installation | 06/10/2021 | 21/10/2021 | 03/08/2021 | 25/08/2021 | 0 | TK_Complete | 1112893334 | 372 | 1112893334_372
C730D157BC###0027237 | TT_Task | CBTC/Stage-2 SMCSW [City] - Alstom closure of comments Northern Connection CHW SER | 31/08/2020 | 15/09/2020 | 17/07/2020 | 17/07/2020 | 0 | TK_Complete | 1112893334 | 371 | 1112893334_371
C730D157BC###0027243 | TT_Task | CBTC/Stage-2 SMCSW [City] - Alstom closure of comments Barangaroo Station SER | 31/08/2020 | 15/09/2020 | 17/07/2020 | 17/07/2020 | 0 | TK_Complete | 1112893334 | 371 | 1112893334_371
C730D157BC###0027249 | TT_Task | CBTC/Stage-2 SMCSW [City] - Alstom closure of comments Sydenham Station SER | 31/08/2020 | 15/09/2020 | 01/06/2020 | 01/06/2020 | 0 | TK_Complete | 1112893334 | 371 | 1112893334_371
C730D157BC###0027291 | TT_Task | CBTC/Stage-2 SMCSW [City] - Alstom closure of comments Martin Place Station SER | 31/08/2020 | 15/09/2020 | 01/07/2020 | 01/07/2020 | 0 | TK_Complete | 1112893334 | 371 | 1112893334_371
C730D157BC###0027297 | TT_Task | CBTC/Stage-2 SMCSW [City] - Alstom closure of comments Pitt St Station SER | 31/08/2020 | 15/09/2020 | 01/07/2020 | 01/07/2020 | 0 | TK_Complete | 1112893334 | 371 | 1112893334_371
C730D157BC###0027303 | TT_Task | CBTC/Stage-2 SMCSW [City] - Alstom closure of comments Central Station SER | 31/08/2020 | 15/09/2020 | 01/07/2020 | 01/07/2020 | 0 | TK_Complete | 1112893334 | 371 | 1112893334_371
C730D157BC###0027339 | TT_Task | CBTC/Stage-2 SMCSW [City] - Alstom closure of comments Crows Nest Station SER | 31/08/2020 | 15/09/2020 | 17/07/2020 | 17/07/2020 | 0 | TK_Complete | 1112893334 | 371 | 1112893334_371
C730D157BC###0027345 | TT_Task | CBTC/Stage-2 SMCSW [City] - Alstom closure of comments Victoria Cross Station SER | 31/08/2020 | 15/09/2020 | 17/07/2020 | 17/07/2020 | 0 | TK_Complete | 1112893334 | 371 | 1112893334_371
C730D157BC###0027351 | TT_Task | CBTC/Stage-2 SMCSW [City] - Alstom closure of comments Waterloo Station SER | 31/08/2020 | 15/09/2020 | 17/07/2020 | 17/07/2020 | 0 | TK_Complete | 1112893334 | 371 | 1112893334_371
C730D157BC###0012200 | TT_Task | CBTC/Stage-3 SMCSW[City] - Customer closure of comments Northern Connection CHW SER | 02/09/2021 | 17/09/2021 | 26/07/2021 | 25/08/2021 | 0 | TK_Complete | 1112893334 | 371 | 1112893334_371
C730D157BC###0012203 | TT_Task | CBTC/Stage-3 SMCSW[City] - Customer closure of comments Crows Nest Station SER | 02/09/2021 | 17/09/2021 | 26/07/2021 | 25/08/2021 | 0 | TK_Complete | 1112893334 | 371 | 1112893334_371
C730D157BC###0012206 | TT_Task | CBTC/Stage-3 SMCSW[City] - Customer closure of comments Victoria Cross Station SER | 02/09/2021 | 17/09/2021 | 26/07/2021 | 25/08/2021 | 0 | TK_Complete | 1112893334 | 371 | 1112893334_371
C730D157BC###0012209 | TT_Task | CBTC/Stage-3 SMCSW[City] - Customer closure of comments Barangaroo Station SER | 02/09/2021 | 17/09/2021 | 02/08/2021 | 25/08/2021 | 0 | TK_Complete | 1112893334 | 371 | 1112893334_371
C730D157BC###0012212 | TT_Task | CBTC/Stage-3 SMCSW[City] - Customer closure of comments Martin Place Station SER | 02/09/2021 | 17/09/2021 | 02/08/2021 | 25/08/2021 | 0 | TK_Complete | 1112893334 | 371 | 1112893334_371
C730D157BC###0012215 | TT_Task | CBTC/Stage-3 SMCSW[City] - Customer closure of comments Pitt St Station SER | 02/09/2021 | 17/09/2021 | 02/08/2021 | 25/08/2021 | 0 | TK_Complete | 1112893334 | 371 | 1112893334_371
C730D157BC###0012218 | TT_Task | CBTC/Stage-3 SMCSW[City] - Customer closure of comments Central Station SER | 02/09/2021 | 17/09/2021 | 04/08/2021 | 25/08/2021 | 0 | TK_Complete | 1112893334 | 371 | 1112893334_371
C730D157BC###0012221 | TT_Task | CBTC/Stage-3 SMCSW[City] - Customer closure of comments Waterloo Station SER | 02/09/2021 | 17/09/2021 | 04/08/2021 | 25/08/2021 | 0 | TK_Complete | 1112893334 | 371 | 1112893334_371
C730D157BC###0012227 | TT_Task | CBTC/Stage-3 SMCSW[City] - Customer closure of comments Sydenham Station SER | 02/09/2021 | 17/09/2021 | 04/08/2021 | 25/08/2021 | 0 | TK_Complete | 1112893334 | 371 | 1112893334_371
C730D157BC###0014060 | TT_Task | CBTC/Stage-2 SMCSW [City] - Design customer review Point Machine Installation | 27/07/2020 | 28/08/2020 | 14/07/2020 | 14/07/2020 | 0 | TK_Complete | 1112893334 | 370 | 1112893334_370
C730D157BC###0027057 | TT_Task | CBTC/Stage-2 SMCSW [SMTF-S] - Design customer review Point Machine Installation - D84M | 25/05/2020 | 29/06/2020 | 19/02/2020 | 08/05/2020 | 0 | TK_Complete | 1112893334 | 370 | 1112893334_370
C730D157BC###0081709 | TT_Task | CBTC/Stage-3 SMCSW[City] - Installation Design Customer review Boxes (SAB ; Point Machines) Installation | 29/04/2021 | 02/06/2021 | 23/04/2021 | 25/08/2021 | 0 | TK_Complete | 1112893334 | 370 | 1112893334_370
C730D157BC###0081724 | TT_Task | CBTC/Stage-3 SMCSW[City] - Installation Design Customer review Point Machine Installation | 19/05/2021 | 22/06/2021 | 23/04/2021 | 25/08/2021 | 0 | TK_Complete | 1112893334 | 370 | 1112893334_370
C730D157BC###0081727 | TT_Task | CBTC/Stage-3 SMCSW[City] - Installation Design Customer review MB Installation | 26/05/2021 | 29/06/2021 | 26/04/2021 | 25/08/2021 | 0 | TK_Complete | 1112893334 | 370 | 1112893334_370
C730D156BC###0081760 | TT_Task | CBTC/Stage-3 SMCSW[SMTF-S] - Installation Design Customer review Point Machine Installation - D84M | 19/05/2021 | 22/06/2021 | 21/04/2021 | 25/08/2021 | 0 | TK_Complete | 1112893334 | 370 | 1112893334_370
C720P147CF###0030430 | TT_Task | RFQ for laser cut ; bend parts | 27/04/2020 | 15/06/2020 | 26/03/2020 | 03/04/2020 | 0 | TK_Complete | 1112893334 | 37 | 1112893334_37
C720P147CF###0030730 | TT_Task | BA Laser cut ; bend parts | 25/05/2020 | 17/06/2020 | 06/04/2020 | 27/04/2020 | 0 | TK_Complete | 1112893334 | 37 | 1112893334_37
C720P147CF###0031040 | TT_Task | PO Laser cut ; bend parts | 25/06/2020 | 22/07/2020 | 26/05/2020 | 29/05/2020 | 0 | TK_Complete | 1112893334 | 37 | 1112893334_37
C720P147CF###0031660 | TT_Task | Production Laser cut ; bend parts | 25/08/2020 | 17/11/2020 | 25/08/2020 | 20/10/2020 | 0 | TK_Complete | 1112893334 | 37 | 1112893334_37
C720P147CF###0031790 | TT_Task | DEL Laser cut ; bend parts | 26/10/2020 | 20/11/2020 | 21/10/2020 | 05/11/2020 | 0 | TK_Complete | 1112893334 | 37 | 1112893334_37
C730D157BC###0014000 | TT_Task | CBTC/Stage-2 SMCSW [City] - Design customer review Northern Connection CHW SER | 27/07/2020 | 28/08/2020 | 17/07/2020 | 17/07/2020 | 0 | TK_Complete | 1112893334 | 369 | 1112893334_369
C730D157BC###0014005 | TT_Task | CBTC/Stage-2 SMCSW [City] - Design customer review Crows Nest Station SER | 27/07/2020 | 28/08/2020 | 29/05/2020 | 17/07/2020 | 0 | TK_Complete | 1112893334 | 369 | 1112893334_369
C730D157BC###0014010 | TT_Task | CBTC/Stage-2 SMCSW [City] - Design customer review Victoria Cross Station SER | 27/07/2020 | 28/08/2020 | 16/06/2020 | 17/07/2020 | 0 | TK_Complete | 1112893334 | 369 | 1112893334_369
C730D157BC###0014020 | TT_Task | CBTC/Stage-2 SMCSW [City] - Design customer review Martin Place Station SER | 27/07/2020 | 28/08/2020 | 01/07/2020 | 01/07/2020 | 0 | TK_Complete | 1112893334 | 369 | 1112893334_369
C730D157BC###0014025 | TT_Task | CBTC/Stage-2 SMCSW [City] - Design customer review Central Station SER | 27/07/2020 | 28/08/2020 | 01/07/2020 | 01/07/2020 | 0 | TK_Complete | 1112893334 | 369 | 1112893334_369
C730D157BC###0014035 | TT_Task | CBTC/Stage-2 SMCSW [City] - Design customer review Sydenham Station SER | 27/07/2020 | 28/08/2020 | 01/06/2020 | 01/06/2020 | 0 | TK_Complete | 1112893334 | 369 | 1112893334_369
C730D157BC###0014100 | TT_Task | CBTC/Stage-2 SMCSW [City] - Design customer review Pitt St Station SER | 27/07/2020 | 28/08/2020 | 01/07/2020 | 01/07/2020 | 0 | TK_Complete | 1112893334 | 369 | 1112893334_369
C730D157BC###0014105 | TT_Task | CBTC/Stage-2 SMCSW [City] - Design customer review Waterloo Station SER | 27/07/2020 | 28/08/2020 | 17/07/2020 | 17/07/2020 | 0 | TK_Complete | 1112893334 | 369 | 1112893334_369
C730D157BC###0200710 | TT_Task | CBTC/Stage-3 SMCSW[City] - Installation Design Customer review Northern Connection CHW SER | 13/05/2021 | 16/06/2021 | 01/04/2021 | 25/08/2021 | 0 | TK_Complete | 1112893334 | 369 | 1112893334_369
C730D157BC###0200720 | TT_Task | CBTC/Stage-3 SMCSW[City] - Installation Design Customer review Crows Nest Station SER | 20/05/2021 | 23/06/2021 | 01/04/2021 | 25/08/2021 | 0 | TK_Complete | 1112893334 | 369 | 1112893334_369
C730D157BC###0200730 | TT_Task | CBTC/Stage-3 SMCSW[City] - Installation Design Customer review Sydenham Station SER | 28/05/2021 | 01/07/2021 | 19/04/2021 | 25/08/2021 | 0 | TK_Complete | 1112893334 | 369 | 1112893334_369
C730D157BC###0200740 | TT_Task | CBTC/Stage-3 SMCSW[City] - Installation Design Customer review Victoria Cross Station SER | 19/04/2021 | 21/05/2021 | 09/03/2021 | 25/08/2021 | 0 | TK_Complete | 1112893334 | 369 | 1112893334_369
C730D157BC###0200760 | TT_Task | CBTC/Stage-3 SMCSW[City] - Installation Design Customer review Martin Place Station SER | 26/04/2021 | 28/05/2021 | 15/03/2021 | 25/08/2021 | 0 | TK_Complete | 1112893334 | 369 | 1112893334_369
C730D157BC###0200770 | TT_Task | CBTC/Stage-3 SMCSW[City] - Installation Design Customer review Central Station SER | 13/05/2021 | 16/06/2021 | 01/04/2021 | 25/08/2021 | 0 | TK_Complete | 1112893334 | 369 | 1112893334_369
C730D157BC###0200780 | TT_Task | CBTC/Stage-3 SMCSW[City] - Installation Design Customer review Pitt St Station SER | 26/04/2021 | 28/05/2021 | 09/03/2021 | 25/08/2021 | 0 | TK_Complete | 1112893334 | 369 | 1112893334_369
C730D157BC###0200790 | TT_Task | CBTC/Stage-3 SMCSW[City] - Installation Design Customer review Waterloo Station SER | 12/04/2021 | 14/05/2021 | 09/03/2021 | 25/08/2021 | 0 | TK_Complete | 1112893334 | 369 | 1112893334_369
C730D157BC###0070385 | TT_Task | CBTC/Stage-2 SMCSW [System-wide] - Initial SRS - Point machine Monitoring System | 25/06/2020 | 15/07/2020 | 22/06/2020 | 24/09/2020 | 0 | TK_Complete | 1112893334 | 368 | 1112893334_368
C730D157BC###0027177 | TT_Task | CBTC/Stage-2 SMCSW [System-wide] - Design customer review Initial SRS - PM Monitoring System | 26/10/2020 | 27/11/2020 | 28/09/2020 | 20/10/2020 | 0 | TK_Complete | 1112893334 | 368 | 1112893334_368
C730D157BC###0027285 | TT_Task | CBTC/Stage-2 SMCSW [System-wide] - Alstom closure of comments Point machine Monitoring System | 06/01/2021 | 21/01/2021 | 28/09/2020 | 20/10/2020 | 0 | TK_Complete | 1112893334 | 368 | 1112893334_368
C730D157BC###70385 | TT_Task | CBTC/Stage-3 SMCSW[System-wide] - Final SRS - Point machine Monitoring System | 29/04/2021 | 19/05/2021 | 12/04/2021 | 30/04/2021 | 0 | TK_Complete | 1112893334 | 368 | 1112893334_368
C730D157BC###208953 | TT_Task | CBTC/Stage-3 SMCSW[City] - Customer review final SRS - Point machine Monitoring System | 31/05/2021 | 02/07/2021 | 03/05/2021 | 25/08/2021 | 0 | TK_Complete | 1112893334 | 368 | 1112893334_368
C730D157BC###0208961 | TT_Task | CBTC/Stage-3 SMCSW[City] - Customer closure of comments SRS - Point machine Monitoring System | 02/09/2021 | 17/09/2021 | 04/08/2021 | 25/08/2021 | 0 | TK_Complete | 1112893334 | 368 | 1112893334_368
C730D156BC###0081988 | TT_Task | CBTC/As-Built SMCSW(System-Wide) - SRS - Point Machine Monitoring System | 06/06/2023 | 19/06/2023 | nan | nan | 0 | TK_NotStart | 1112893334 | 368 | 1112893334_368
C730D157BC###0097020 | TT_Task | CBTC/Stage-2 SMCSW [SMTF-S] - Initial Drawings Point Machine Installation - MATR | 22/05/2020 | 04/06/2020 | 09/03/2020 | 11/03/2020 | 0 | TK_Complete | 1112893334 | 367 | 1112893334_367
C730D157BC###0027081 | TT_Task | CBTC/Stage-2 SMCSW [SMTF-S] - Design customer review Point Machine Installation - MATR | 25/05/2020 | 29/06/2020 | 18/03/2020 | 18/05/2020 | 0 | TK_Complete | 1112893334 | 367 | 1112893334_367
C730D157BC###002080 | TT_Task | CBTC/Stage-3 SMCSW[SMTF-S] - Final Drawings Point Machine Installation - MATR | 03/05/2021 | 14/05/2021 | 06/04/2021 | 20/04/2021 | 0 | TK_Complete | 1112893334 | 367 | 1112893334_367
C730D156BC###0081766 | TT_Task | CBTC/Stage-3 SMCSW[SMTF-S] - Installation Design Customer review Point Machine Installation - MATR | 19/05/2021 | 22/06/2021 | 21/04/2021 | 25/08/2021 | 0 | TK_Complete | 1112893334 | 367 | 1112893334_367
C730D157BC###0097012 | TT_Task | CBTC/Stage-2 SMCSW [SMTF-S] - Initial Drawings Buffer Stop Installation | 08/05/2020 | 21/05/2020 | 04/02/2020 | 26/02/2020 | 0 | TK_Complete | 1112893334 | 366 | 1112893334_366
C730D157BC###0027069 | TT_Task | CBTC/Stage-2 SMCSW [SMTF-S] - Design customer review Buffer Stop Installation | 25/05/2020 | 29/06/2020 | 04/03/2020 | 08/05/2020 | 0 | TK_Complete | 1112893334 | 366 | 1112893334_366
C730D157BC###002010 | TT_Task | CBTC/Stage-3 SMCSW[SMTF-S] - Final Drawings Buffer Stop Installation [Depot Only] | 11/03/2021 | 24/03/2021 | 01/02/2021 | 12/02/2021 | 0 | TK_Complete | 1112893334 | 366 | 1112893334_366
C730D156BC###0081712 | TT_Task | CBTC/Stage-3 SMCSW[SMTF-S] - Installation Design Customer review Final Drawings Buffer Stop Installation [Depot Only] | 02/03/2021 | 05/04/2021 | 15/02/2021 | 25/08/2021 | 0 | TK_Complete | 1112893334 | 366 | 1112893334_366
C730D156BC###0081730 | TT_Task | CBTC/Stage-3 SMCSW[SMTF-S] - Customer closure of comments Final Drawings Buffer Stop Installation [Depot Only] | 20/09/2021 | 05/10/2021 | 03/08/2021 | 25/08/2021 | 0 | TK_Complete | 1112893334 | 366 | 1112893334_366
C730D156BC###0081796 | TT_Task | CBTC/Stage-3 SMCSW[SMTF-S] - Customer closure of comments Final Drawings Marker Board Installation | 02/09/2021 | 17/09/2021 | 09/08/2021 | 25/08/2021 | 0 | TK_Complete | 1112893334 | 366 | 1112893334_366
C730D157BC###0013030 | TT_Task | CBTC/Stage-2 SMCSW [SMTF-S] - Initial Room Layout Drawing SMTF[S] DSER | 01/09/2020 | 14/09/2020 | 03/01/2020 | 19/06/2020 | 0 | TK_Complete | 1112893334 | 365 | 1112893334_365
C730D157BC###0014030 | TT_Task | CBTC/Stage-2 SMCSW [City] - Design customer review SMTF[S] DSER | 27/07/2020 | 28/08/2020 | 17/07/2020 | 17/07/2020 | 0 | TK_Complete | 1112893334 | 365 | 1112893334_365
C730D157BC###0027255 | TT_Task | CBTC/Stage-2 SMCSW [SMTF-S] - Design customer review DSER [Depot-S] | 27/07/2020 | 28/08/2020 | 17/07/2020 | 17/07/2020 | 0 | TK_Complete | 1112893334 | 365 | 1112893334_365
C730D157BC###002090 | TT_Task | CBTC/Stage-3 SMCSW[SMTF-S] - Final Room Layout Drawing DSER3 (Depot) | 12/05/2021 | 25/05/2021 | 06/04/2021 | 19/04/2021 | 0 | TK_Complete | 1112893334 | 365 | 1112893334_365
C730D156BC###0081709 | TT_Task | CBTC/Stage-3 SMCSW[SMTF-S] - Installation Design Customer review Final Room Layout Drawing DSER3 (Depot) | 26/05/2021 | 29/06/2021 | 20/04/2021 | 25/08/2021 | 0 | TK_Complete | 1112893334 | 365 | 1112893334_365
C730D157BC###0013130 | TT_Task | CBTC/Stage-2 SMCSW [City] - Initial Drawings Marker Board Installation | 23/06/2020 | 06/07/2020 | 15/04/2020 | 28/04/2020 | 0 | TK_Complete | 1112893334 | 364 | 1112893334_364
C730D157BC###0097040 | TT_Task | CBTC/Stage-2 SMCSW [SMTF-S] - Initial Drawings Marker Board Installation | 16/07/2020 | 27/07/2020 | 27/05/2020 | 03/06/2020 | 0 | TK_Complete | 1112893334 | 364 | 1112893334_364
C730D157BC###0027117 | TT_Task | CBTC/Stage-2 SMCSW [City] - Design customer review Marker Board Installation | 09/07/2020 | 12/08/2020 | 27/05/2020 | 14/07/2020 | 0 | TK_Complete | 1112893334 | 364 | 1112893334_364
C730D157BC###0027195 | TT_Task | CBTC/Stage-2 SMCSW [SMTF-S] - Design customer review Marker Board Installation | 25/08/2020 | 28/09/2020 | 04/06/2020 | 28/07/2020 | 0 | TK_Complete | 1112893334 | 364 | 1112893334_364
C730D157BC###0012184 | TT_Task | CBTC/Stage-3 SMCSW[City] - Final Drawings Marker Board Installation (SM) | 28/04/2021 | 18/05/2021 | 07/04/2021 | 23/04/2021 | 0 | TK_Complete | 1112893334 | 364 | 1112893334_364
C730D157BC###002110 | TT_Task | CBTC/Stage-3 SMCSW[SMTF-S] - Final Drawings Marker Board Installation (SM) | 04/03/2021 | 17/03/2021 | 17/02/2021 | 24/03/2021 | 0 | TK_Complete | 1112893334 | 364 | 1112893334_364
C730D156BC###0081763 | TT_Task | CBTC/Stage-3 SMCSW[SMTF-S] - Installation Design Customer review Final Drawings Marker Board Installation | 19/05/2021 | 22/06/2021 | 29/03/2021 | 25/08/2021 | 0 | TK_Complete | 1112893334 | 364 | 1112893334_364
C730D156BC###0081931 | TT_Task | CBTC/As-Built SMCSW[City] - Marker Board Installation Drawings | 25/04/2023 | 08/05/2023 | nan | nan | 0 | TK_NotStart | 1112893334 | 364 | 1112893334_364
C730D157BC###0013105 | TT_Task | CBTC/Stage-2 SMCSW [City] - Initial Drawings Key Switches Installation | 25/05/2020 | 05/06/2020 | 06/04/2020 | 20/04/2020 | 0 | TK_Complete | 1112893334 | 363 | 1112893334_363
C730D157BC###0097036 | TT_Task | CBTC/Stage-2 SMCSW [SMTF-S] - Initial Drawings Key Switches Installation | 16/07/2020 | 27/07/2020 | 08/06/2020 | 19/06/2020 | 0 | TK_Complete | 1112893334 | 363 | 1112893334_363
C730D157BC###0014080 | TT_Task | CBTC/Stage-2 SMCSW [City] - Design customer review Key Switches Installation | 27/07/2020 | 28/08/2020 | 14/07/2020 | 14/07/2020 | 0 | TK_Complete | 1112893334 | 363 | 1112893334_363
C730D157BC###0027189 | TT_Task | CBTC/Stage-2 SMCSW [SMTF-S] - Design customer review Key Switches Installation | 25/08/2020 | 28/09/2020 | 22/06/2020 | 29/07/2020 | 0 | TK_Complete | 1112893334 | 363 | 1112893334_363
C730D157BC###0012169 | TT_Task | CBTC/Stage-3 SMCSW[City] - Final Drawings Key Switches Installation (SM) | 28/04/2021 | 18/05/2021 | 01/04/2021 | 16/04/2021 | 0 | TK_Complete | 1112893334 | 363 | 1112893334_363
C730D157BC###002100 | TT_Task | CBTC/Stage-3 SMCSW[SMTF-S] - Final Drawings Key Switches Installation (SM) | 04/03/2021 | 17/03/2021 | 08/02/2021 | 19/02/2021 | 0 | TK_Complete | 1112893334 | 363 | 1112893334_363
C730D157BC###0081712 | TT_Task | CBTC/Stage-3 SMCSW[City] - Installation Design Customer review Key Switches Installation | 19/05/2021 | 22/06/2021 | 19/04/2021 | 25/08/2021 | 0 | TK_Complete | 1112893334 | 363 | 1112893334_363
C730D156BC###0081736 | TT_Task | CBTC/Stage-3 SMCSW[SMTF-S] - Installation Design Customer review Final Drawings Key Switches Installation | 25/03/2021 | 28/04/2021 | 22/02/2021 | 25/08/2021 | 0 | TK_Complete | 1112893334 | 363 | 1112893334_363
C730D156BC###0081928 | TT_Task | CBTC/As-Built SMCSW[City] - Key Switch Installation Drawings | 25/04/2023 | 08/05/2023 | nan | nan | 0 | TK_NotStart | 1112893334 | 363 | 1112893334_363
C730D157BC###0013095 | TT_Task | CBTC/Stage-2 SMCSW [City] - Initial Drawings Boxes (SAB ; Point Machines) Installation | 22/05/2020 | 04/06/2020 | 04/03/2020 | 11/03/2020 | 0 | TK_Complete | 1112893334 | 362 | 1112893334_362
C730D157BC###0097032 | TT_Task | CBTC/Stage-2 SMCSW [SMTF-S] - Initial Drawings Boxes (SAB ; SPB) Installation | 02/07/2020 | 15/07/2020 | 26/05/2020 | 29/05/2020 | 0 | TK_Complete | 1112893334 | 362 | 1112893334_362
C730D157BC###0014085 | TT_Task | CBTC/Stage-2 SMCSW [City] - Design customer review Boxes (SAB ; SPB) Installation | 25/06/2020 | 29/07/2020 | 18/03/2020 | 15/04/2020 | 0 | TK_Complete | 1112893334 | 362 | 1112893334_362
C730D157BC###0027165 | TT_Task | CBTC/Stage-2 SMCSW [SMTF-S] - Design customer review Boxes (SAB ; SPB) Installation | 25/08/2020 | 28/09/2020 | 29/05/2020 | 01/06/2020 | 0 | TK_Complete | 1112893334 | 362 | 1112893334_362
C730D157BC###0012163 | TT_Task | CBTC/Stage-3 SMCSW[City] - Final Drawings Boxes (SAB ; SPB) Installation | 29/03/2021 | 16/04/2021 | 15/03/2021 | 22/04/2021 | 0 | TK_Complete | 1112893334 | 362 | 1112893334_362
C730D157BC###002030 | TT_Task | CBTC/Stage-3 SMCSW[SMTF-S] - Final Drawings Boxes (SAB ; SPB) Installation | 04/03/2021 | 17/03/2021 | 15/02/2021 | 23/02/2021 | 0 | TK_Complete | 1112893334 | 362 | 1112893334_362
C730D156BC###0081721 | TT_Task | CBTC/Stage-3 SMCSW[SMTF-S] - Installation Design Customer review Boxes (SAB ; SPB) Installation | 30/03/2021 | 03/05/2021 | 26/02/2021 | 25/08/2021 | 0 | TK_Complete | 1112893334 | 362 | 1112893334_362
C730D157BC###0013080 | TT_Task | CBTC/Stage-2 SMCSW [City] - Initial Drawings Point Machine Installation - D84M | 23/06/2020 | 06/07/2020 | 13/03/2020 | 01/06/2020 | 0 | TK_Complete | 1112893334 | 361 | 1112893334_361
C730D157BC###0097004 | TT_Task | CBTC/Stage-2 SMCSW [SMTF-S] - Initial Drawings Point Machine Installation - D84M | 24/04/2020 | 07/05/2020 | 05/02/2020 | 12/02/2020 | 0 | TK_Complete | 1112893334 | 361 | 1112893334_361
C730D157BC###0012151 | TT_Task | CBTC/Stage-3 SMCSW[City] - Final Drawings Point Machine Installation - D84M | 28/04/2021 | 18/05/2021 | 06/04/2021 | 22/04/2021 | 0 | TK_Complete | 1112893334 | 361 | 1112893334_361
C730D157BC###002070 | TT_Task | CBTC/Stage-3 SMCSW[SMTF-S] - Final Drawings Point Machine Installation - D84M - Discontunied | 03/05/2021 | 14/05/2021 | 20/04/2021 | 20/04/2021 | 0 | TK_Complete | 1112893334 | 361 | 1112893334_361
C730D156BC###0081934 | TT_Task | CBTC/As-Built SMCSW[City] - Point Machine (D84M) Installation Drawings | 25/04/2023 | 08/05/2023 | nan | nan | 0 | TK_NotStart | 1112893334 | 361 | 1112893334_361
C730D157BC###0013075 | TT_Task | CBTC/Stage-2 SMCSW [City] - Initial Drawings Axle Counter Installation | 25/05/2020 | 05/06/2020 | 09/03/2020 | 30/03/2020 | 0 | TK_Complete | 1112893334 | 360 | 1112893334_360
C730D157BC###0097016 | TT_Task | CBTC/Stage-2 SMCSW [SMTF-S] - Initial Drawings Axle Counter Installation | 22/05/2020 | 04/06/2020 | 04/02/2020 | 11/02/2020 | 0 | TK_Complete | 1112893334 | 360 | 1112893334_360
C730D157BC###0014055 | TT_Task | CBTC/Stage-2 SMCSW [City] - Design customer review Axle Counter Installation | 25/06/2020 | 29/07/2020 | 06/04/2020 | 26/05/2020 | 0 | TK_Complete | 1112893334 | 360 | 1112893334_360
C730D157BC###0027075 | TT_Task | CBTC/Stage-2 SMCSW [SMTF-S] - Design customer review Axle Counter Installation | 25/05/2020 | 29/06/2020 | 18/03/2020 | 12/05/2020 | 0 | TK_Complete | 1112893334 | 360 | 1112893334_360
C730D157BC###0012148 | TT_Task | CBTC/Stage-3 SMCSW[City] - Final Drawings Axle Counter Installation | 29/03/2021 | 16/04/2021 | 15/03/2021 | 31/03/2021 | 0 | TK_Complete | 1112893334 | 360 | 1112893334_360
C730D157BC###002060 | TT_Task | CBTC/Stage-3 SMCSW[SMTF-S] - Final Drawings Axle Counter Installation | 11/03/2021 | 24/03/2021 | 01/02/2021 | 12/02/2021 | 0 | TK_Complete | 1112893334 | 360 | 1112893334_360
C730D157BC###0081715 | TT_Task | CBTC/Stage-3 SMCSW[City] - Installation Design Customer review Axle Counter Installation | 29/04/2021 | 02/06/2021 | 01/04/2021 | 25/08/2021 | 0 | TK_Complete | 1112893334 | 360 | 1112893334_360
C730D156BC###0081733 | TT_Task | CBTC/Stage-3 SMCSW[SMTF-S] - Installation Design Customer review Final Drawings Axle Counter Installation | 22/03/2021 | 23/04/2021 | 15/02/2021 | 25/08/2021 | 0 | TK_Complete | 1112893334 | 360 | 1112893334_360
C730D156BC###0081922 | TT_Task | CBTC/As-Built SMCSW[City] - Axle Counter Installation Drawings | 25/04/2023 | 08/05/2023 | nan | nan | 0 | TK_NotStart | 1112893334 | 360 | 1112893334_360
C720P147CF###0030070 | TT_Task | RFQ for long profile parts | 25/02/2020 | 23/03/2020 | 31/10/2019 | 28/11/2019 | 0 | TK_Complete | 1112893334 | 36 | 1112893334_36
C720P147CF###0030480 | TT_Task | RFQ for coupler | 25/02/2020 | 12/03/2020 | 31/10/2019 | 18/11/2019 | 0 | TK_Complete | 1112893334 | 36 | 1112893334_36
C720P147CF###0030610 | TT_Task | RFQ for brakes | 25/02/2020 | 12/03/2020 | 31/10/2019 | 18/11/2019 | 0 | TK_Complete | 1112893334 | 36 | 1112893334_36
C720P147CF###32640 | TT_Task | RFQ for gearbox | 25/05/2020 | 22/06/2020 | 31/10/2019 | 03/12/2019 | 0 | TK_Complete | 1112893334 | 36 | 1112893334_36
C720P147CF###32650 | TT_Task | RFQ for couplings | 31/10/2019 | 27/11/2019 | 31/10/2019 | 03/12/2019 | 0 | TK_Complete | 1112893334 | 36 | 1112893334_36
C730D157BC###0013070 | TT_Task | CBTC/Stage-2 SMCSW [City] - Initial Drawings Balise Installation | 25/05/2020 | 05/06/2020 | 12/03/2020 | 01/04/2020 | 0 | TK_Complete | 1112893334 | 359 | 1112893334_359
C730D157BC###0097008 | TT_Task | CBTC/Stage-2 SMCSW [SMTF-S] - Initial Drawings Balise Installation | 08/05/2020 | 21/05/2020 | 03/02/2020 | 26/02/2020 | 0 | TK_Complete | 1112893334 | 359 | 1112893334_359
C730D157BC###0014065 | TT_Task | CBTC/Stage-2 SMCSW [City] - Design customer review Balise Installation | 25/06/2020 | 29/07/2020 | 08/04/2020 | 06/05/2020 | 0 | TK_Complete | 1112893334 | 359 | 1112893334_359
C730D157BC###0027063 | TT_Task | CBTC/Stage-2 SMCSW [SMTF-S] - Design customer review Balise Installation | 25/05/2020 | 29/06/2020 | 04/03/2020 | 08/05/2020 | 0 | TK_Complete | 1112893334 | 359 | 1112893334_359
C730D157BC###0012145 | TT_Task | CBTC/Stage-3 SMCSW[City] - Final Drawings Balise Installation | 29/03/2021 | 16/04/2021 | 15/03/2021 | 31/03/2021 | 0 | TK_Complete | 1112893334 | 359 | 1112893334_359
C730D157BC###002040 | TT_Task | CBTC/Stage-3 SMCSW[SMTF-S] - Final Drawings Balise Installation | 04/03/2021 | 17/03/2021 | 08/02/2021 | 18/02/2021 | 0 | TK_Complete | 1112893334 | 359 | 1112893334_359
C730D157BC###0081703 | TT_Task | CBTC/Stage-3 SMCSW[City] - Installation Design Customer review Balise Installation | 29/04/2021 | 02/06/2021 | 01/04/2021 | 25/08/2021 | 0 | TK_Complete | 1112893334 | 359 | 1112893334_359
C730D156BC###0081727 | TT_Task | CBTC/Stage-3 SMCSW[SMTF-S] - Installation Design Customer review Balise Installation | 22/03/2021 | 23/04/2021 | 22/02/2021 | 25/08/2021 | 0 | TK_Complete | 1112893334 | 359 | 1112893334_359
C730D156BC###0081925 | TT_Task | CBTC/As-Built SMCSW[City] - Balise Installation Drawings | 25/04/2023 | 08/05/2023 | nan | nan | 0 | TK_NotStart | 1112893334 | 359 | 1112893334_359
C730D157BC###0013065 | TT_Task | CBTC/Stage-2 SMCSW [City] - Initial Drawings PPI Installation | 22/05/2020 | 04/06/2020 | 03/03/2020 | 13/03/2020 | 0 | TK_Complete | 1112893334 | 358 | 1112893334_358
C730D157BC###0097000 | TT_Task | CBTC/Stage-2 SMCSW [SMTF-S] - Initial Drawings PPI Installation | 24/04/2020 | 07/05/2020 | 05/02/2020 | 12/02/2020 | 0 | TK_Complete | 1112893334 | 358 | 1112893334_358
C730D157BC###0014095 | TT_Task | CBTC/Stage-2 SMCSW [City] - Design customer review PPI Installation | 27/07/2020 | 28/08/2020 | 14/04/2020 | 14/04/2020 | 0 | TK_Complete | 1112893334 | 358 | 1112893334_358
C730D157BC###0027051 | TT_Task | CBTC/Stage-2 SMCSW [SMTF-S] - Design customer review PPI Installation | 25/05/2020 | 29/06/2020 | 19/02/2020 | 08/05/2020 | 0 | TK_Complete | 1112893334 | 358 | 1112893334_358
C730D157BC###0012142 | TT_Task | CBTC/Stage-3 SMCSW[City] - Final Drawings PPI Installation (SM) | 28/04/2021 | 18/05/2021 | 09/04/2021 | 23/04/2021 | 0 | TK_Complete | 1112893334 | 358 | 1112893334_358
C730D157BC###002050 | TT_Task | CBTC/Stage-3 SMCSW[SMTF-S] - Final Drawings PPI Installation (SM) | 03/05/2021 | 14/05/2021 | 06/04/2021 | 19/04/2021 | 0 | TK_Complete | 1112893334 | 358 | 1112893334_358
C730D157BC###0081706 | TT_Task | CBTC/Stage-3 SMCSW[City] - Installation Design Customer review PPI Installation | 26/05/2021 | 29/06/2021 | 26/04/2021 | 25/08/2021 | 0 | TK_Complete | 1112893334 | 358 | 1112893334_358
C730D156BC###0081724 | TT_Task | CBTC/Stage-3 SMCSW[SMTF-S] - Installation Design Customer review PPI Installation | 19/05/2021 | 22/06/2021 | 20/04/2021 | 25/08/2021 | 0 | TK_Complete | 1112893334 | 358 | 1112893334_358
C730D157BC###0013055 | TT_Task | CBTC/Stage-2 SMCSW [City] - Initial Drawings Track Plan ; Cable Duct Routes [ML] | 25/06/2020 | 08/07/2020 | 11/06/2020 | 26/06/2020 | 0 | TK_Complete | 1112893334 | 357 | 1112893334_357
C730D157BC###0097024 | TT_Task | CBTC/Stage-2 SMCSW [SMTF-S] - Initial Drawings Track Plan ; Cable Duct Routes [Depot] | 02/07/2020 | 15/07/2020 | 23/06/2020 | 26/06/2020 | 0 | TK_Complete | 1112893334 | 357 | 1112893334_357
C730D157BC###0027141 | TT_Task | CBTC/Stage-2 SMCSW [City] - Design customer review Track Plan ; Cable Duct Routes [ML] | 25/08/2020 | 28/09/2020 | 29/06/2020 | 29/07/2020 | 0 | TK_Complete | 1112893334 | 357 | 1112893334_357
C730D157BC###0027153 | TT_Task | CBTC/Stage-2 SMCSW [SMTF-S] - Design customer review Track Plan ; Cable Duct Routes [Depot] | 25/08/2020 | 28/09/2020 | 29/06/2020 | 30/07/2020 | 0 | TK_Complete | 1112893334 | 357 | 1112893334_357
C730D157BC###0012139 | TT_Task | CBTC/Stage-3 SMCSW[City] - Final Drawings Track Plan ; Cable Duct Routes (Closed, MTR 21-12-20:not for submission) | 18/05/2021 | 07/06/2021 | 25/12/2020 | 25/12/2020 | 0 | TK_Complete | 1112893334 | 357 | 1112893334_357
C730D157BC###002000 | TT_Task | CBTC/Stage-3 SMCSW[SMTF-S] - Final Drawings Track Plan ; Cable Duct Routes (Closed, MTR 21-12-20:not for submission) | 21/05/2021 | 03/06/2021 | 25/12/2020 | 25/12/2020 | 0 | TK_Complete | 1112893334 | 357 | 1112893334_357
C730D157BC###0081721 | TT_Task | CBTC/Stage-3 SMCSW[City] - Installation Design Customer review Track Plan ; Cable Duct Routes [ML] | 22/03/2021 | 23/04/2021 | 25/12/2020 | 25/12/2020 | 0 | TK_Complete | 1112893334 | 357 | 1112893334_357
C730D156BC###0081757 | TT_Task | CBTC/Stage-3 SMCSW[SMTF-S] - Installation Design Customer review Final Drawings Track Plan ; Cable Duct Routes [Depot] | 05/04/2021 | 07/05/2021 | 25/12/2020 | 25/12/2020 | 0 | TK_Complete | 1112893334 | 357 | 1112893334_357
C730D157BC###0013045 | TT_Task | CBTC/Stage-2 SMCSW [City] - Initial Drawings DCS Boxes/ Antenna / OLX Installation | 23/06/2020 | 13/07/2020 | 19/03/2020 | 11/06/2020 | 0 | TK_Complete | 1112893334 | 356 | 1112893334_356
C730D157BC###0097028 | TT_Task | CBTC/Stage-2 SMCSW [SMTF-S] - Initial Drawings DCS Boxes/ Antenna / OLX Installation | 02/07/2020 | 15/07/2020 | 01/06/2020 | 11/06/2020 | 0 | TK_Complete | 1112893334 | 356 | 1112893334_356
C730D157BC###0014075 | TT_Task | CBTC/Stage-2 SMCSW [City] - Design customer review DCS Boxes/ Antenna / OLX Installation | 25/08/2020 | 28/09/2020 | 02/07/2020 | 16/07/2020 | 0 | TK_Complete | 1112893334 | 356 | 1112893334_356
C730D157BC###0027159 | TT_Task | CBTC/Stage-2 SMCSW [SMTF-S] - Design customer review DCS Boxes/ Antenna / OLX Installation | 25/08/2020 | 28/09/2020 | 18/06/2020 | 16/07/2020 | 0 | TK_Complete | 1112893334 | 356 | 1112893334_356
C730D157BC###0012130 | TT_Task | CBTC/Stage-3 SMCSW[City] - Final Drawings DCS Boxes/ Antenna / OLX Installation (SM) | 29/03/2021 | 23/04/2021 | 24/03/2021 | 27/04/2021 | 0 | TK_Complete | 1112893334 | 356 | 1112893334_356
C730D157BC###002020 | TT_Task | CBTC/Stage-3 SMCSW[SMTF-S] - Final Drawings DCS Boxes/ Antenna / OLX Installation (SM) | 03/05/2021 | 14/05/2021 | 06/04/2021 | 19/04/2021 | 0 | TK_Complete | 1112893334 | 356 | 1112893334_356
C730D157BC###0081718 | TT_Task | CBTC/Stage-3 SMCSW[City] - Installation Design Customer review DCS Boxes/ Antenna / OLX | 26/05/2021 | 29/06/2021 | 03/05/2021 | 25/08/2021 | 0 | TK_Complete | 1112893334 | 356 | 1112893334_356
C730D156BC###0081739 | TT_Task | CBTC/Stage-3 SMCSW[SMTF-S] - Installation Design Customer review DCS Boxes/ Antenna / OLX Installation | 21/05/2021 | 24/06/2021 | 20/04/2021 | 25/08/2021 | 0 | TK_Complete | 1112893334 | 356 | 1112893334_356
C730D157BC###0013015 | TT_Task | CBTC/Stage-2 SMCSW [City] - Initial Room Layout Drawing Barangaroo Station SER | 21/07/2020 | 10/08/2020 | 09/01/2020 | 29/05/2020 | 0 | TK_Complete | 1112893334 | 355 | 1112893334_355
C730D157BC###0014015 | TT_Task | CBTC/Stage-2 SMCSW [City] - Design customer review Barangaroo Station SER | 27/07/2020 | 28/08/2020 | 17/07/2020 | 17/07/2020 | 0 | TK_Complete | 1112893334 | 355 | 1112893334_355
C730D157BC###0012109 | TT_Task | CBTC/Stage-3 SMCSW[City] - Final Room Layout Drawing Barangaroo Station SER | 03/05/2021 | 18/05/2021 | 02/04/2021 | 16/04/2021 | 0 | TK_Complete | 1112893334 | 355 | 1112893334_355
C730D157BC###N389483 | TT_Task | CBTC/Stage-3 SMCSW[City] - Final Room Layout Drawing Barangaroo Station SER [Post Stage 3] | 26/11/2021 | 13/12/2021 | 10/11/2021 | 14/01/2022 | 0 | TK_Complete | 1112893334 | 355 | 1112893334_355
C730D157BC###N949523 | TT_Task | CBTC/Stage-3 SMCSW[City] - Final Room Layout Drawing Customer review Barangaroo Station SER [Post Stage 3] | 27/12/2021 | 07/01/2022 | 17/01/2022 | 14/02/2022 | 0 | TK_Complete | 1112893334 | 355 | 1112893334_355
C730D157BC###0200750 | TT_Task | CBTC/Stage-3 SMCSW[City] - Installation Design Customer review Barangaroo Station SER | 19/05/2021 | 22/06/2021 | 19/04/2021 | 25/08/2021 | 0 | TK_Complete | 1112893334 | 355 | 1112893334_355
C730D157BC###0013005 | TT_Task | CBTC/Stage-2 SMCSW [City] - Initial Room Layout Drawing Crows Nest Station SER | 01/09/2020 | 21/09/2020 | 22/01/2020 | 29/05/2020 | 0 | TK_Complete | 1112893334 | 354 | 1112893334_354
C730D157BC###0012103 | TT_Task | CBTC/Stage-3 SMCSW[City] - Final Room Layout Drawing Crows Nest Station SER | 03/05/2021 | 18/05/2021 | 18/03/2021 | 31/03/2021 | 0 | TK_Complete | 1112893334 | 354 | 1112893334_354
C730D157BC###N369463 | TT_Task | CBTC/Stage-3 SMCSW[City] - Final Room Layout Drawing Crows Nest Station SER [Post Stage 3] | 26/11/2021 | 13/12/2021 | 10/11/2021 | 28/02/2022 | 0 | TK_Complete | 1112893334 | 354 | 1112893334_354
C730D157BC###N949503 | TT_Task | CBTC/Stage-3 SMCSW[City] -Final Room Layout Drawing Customer review Crows Nest Station SER [Post Stage 3] | 01/03/2022 | 14/03/2022 | 01/03/2022 | nan | 360 | TK_Active | 1112893334 | 354 | 1112893334_354
C730D156BC###0081958 | TT_Task | CBTC/As-Built SMCSW[City] - Crows Nest - Room Layout | 09/05/2023 | 22/05/2023 | nan | nan | 0 | TK_NotStart | 1112893334 | 354 | 1112893334_354
C730D157BC###0013000 | TT_Task | CBTC/Stage-2 SMCSW [City] - Initial Room Layout Drawing Northern Connection CHW SER | 25/06/2020 | 15/07/2020 | 09/06/2020 | 22/06/2020 | 0 | TK_Complete | 1112893334 | 353 | 1112893334_353
C730D157BC###0013010 | TT_Task | CBTC/Stage-2 SMCSW [City] - Initial Room Layout Drawing Victoria Cross Station SER | 25/05/2020 | 05/06/2020 | 18/05/2020 | 15/06/2020 | 0 | TK_Complete | 1112893334 | 353 | 1112893334_353
C730D157BC###0013020 | TT_Task | CBTC/Stage-2 SMCSW [City] - Initial Room Layout Drawing Martin Place Station SER | 25/06/2020 | 15/07/2020 | 02/06/2020 | 22/06/2020 | 0 | TK_Complete | 1112893334 | 353 | 1112893334_353
C730D157BC###0013025 | TT_Task | CBTC/Stage-2 SMCSW [City] - Initial Room Layout Drawing Central Station SER | 25/06/2020 | 15/07/2020 | 10/06/2020 | 22/06/2020 | 0 | TK_Complete | 1112893334 | 353 | 1112893334_353
C730D157BC###0013035 | TT_Task | CBTC/Stage-2 SMCSW [City] - Initial Room Layout Drawing Sydenham Station SER | 06/07/2020 | 24/07/2020 | 04/01/2020 | 29/05/2020 | 0 | TK_Complete | 1112893334 | 353 | 1112893334_353
C730D157BC###0013145 | TT_Task | CBTC/Stage-2 SMCSW [City] - Initial Room Layout Drawing Pitt St Station SER | 25/06/2020 | 15/07/2020 | 08/06/2020 | 22/06/2020 | 0 | TK_Complete | 1112893334 | 353 | 1112893334_353
C730D157BC###0013170 | TT_Task | CBTC/Stage-2 SMCSW [City] - Initial Room Layout Drawing Waterloo Station SER | 25/06/2020 | 08/07/2020 | 01/06/2020 | 15/06/2020 | 0 | TK_Complete | 1112893334 | 353 | 1112893334_353
C730D157BC###0012100 | TT_Task | CBTC/Stage-3 SMCSW[City] - Final Room Layout Drawings - Northern Connection CHW SER | 12/04/2021 | 27/04/2021 | 18/03/2021 | 31/03/2021 | 0 | TK_Complete | 1112893334 | 353 | 1112893334_353
C730D157BC###0012106 | TT_Task | CBTC/Stage-3 SMCSW[City] - Final Room Layout Drawing Victoria Cross Station SER | 07/04/2021 | 22/04/2021 | 01/03/2021 | 08/03/2021 | 0 | TK_Complete | 1112893334 | 353 | 1112893334_353
C730D157BC###0012112 | TT_Task | CBTC/Stage-3 SMCSW[City] - Final Room Layout Drawing Martin Place Station SER | 22/03/2021 | 06/04/2021 | 03/03/2021 | 12/03/2021 | 0 | TK_Complete | 1112893334 | 353 | 1112893334_353
C730D157BC###0012115 | TT_Task | CBTC/Stage-3 SMCSW[City] - Final Room Layout Drawing Pitt St Station SER | 07/04/2021 | 22/04/2021 | 26/02/2021 | 08/03/2021 | 0 | TK_Complete | 1112893334 | 353 | 1112893334_353
C730D157BC###0012118 | TT_Task | CBTC/Stage-3 SMCSW[City] - Final Room Layout Drawing Central Station SER | 12/04/2021 | 27/04/2021 | 18/03/2021 | 31/03/2021 | 0 | TK_Complete | 1112893334 | 353 | 1112893334_353
C730D157BC###0012121 | TT_Task | CBTC/Stage-3 SMCSW[City] - Final Room Layout Drawing Waterloo Station SER | 22/03/2021 | 06/04/2021 | 01/03/2021 | 08/03/2021 | 0 | TK_Complete | 1112893334 | 353 | 1112893334_353
C730D157BC###0012127 | TT_Task | CBTC/Stage-3 SMCSW[City] - Final Room Layout Drawing Sydenham Station SER | 12/05/2021 | 27/05/2021 | 07/04/2021 | 16/04/2021 | 0 | TK_Complete | 1112893334 | 353 | 1112893334_353
C730D157BC###N309543 | TT_Task | CBTC/Stage-3 SMCSW[City] - Final Room Layout Drawing Sydenham Station SER [Post Stage 3] | 01/12/2021 | 16/12/2021 | 11/10/2021 | 15/10/2021 | 0 | TK_Complete | 1112893334 | 353 | 1112893334_353
C730D157BC###N319513 | TT_Task | CBTC/Stage-3 SMCSW[City] - Final Room Layout Drawing Central Station SER [Post Stage 3] | 25/10/2021 | 09/11/2021 | 10/11/2021 | 24/12/2021 | 0 | TK_Complete | 1112893334 | 353 | 1112893334_353
C730D157BC###N329453 | TT_Task | CBTC/Stage-3 SMCSW[City] - Final Room Layout Drawings - Northern Connection CHW SER [Post Stage 3] | 25/10/2021 | 09/11/2021 | 10/11/2021 | nan | 0 | TK_Active | 1112893334 | 353 | 1112893334_353
C730D157BC###N339493 | TT_Task | CBTC/Stage-3 SMCSW[City] - Final Room Layout Drawing Martin Place Station SER [Post Stage 3] | 10/11/2021 | 25/11/2021 | 10/11/2021 | 04/02/2022 | 0 | TK_Complete | 1112893334 | 353 | 1112893334_353
C730D157BC###N349503 | TT_Task | CBTC/Stage-3 SMCSW[City] - Final Room Layout Drawing Pitt St Station SER [Post Stage 3] | 10/11/2021 | 25/11/2021 | 10/11/2021 | 21/01/2022 | 0 | TK_Complete | 1112893334 | 353 | 1112893334_353
C730D157BC###N359523 | TT_Task | CBTC/Stage-3 SMCSW[City] - Final Room Layout Drawing Waterloo Station SER [Post Stage 3] | 10/11/2021 | 25/11/2021 | 10/11/2021 | 27/12/2021 | 0 | TK_Complete | 1112893334 | 353 | 1112893334_353
C730D157BC###N379473 | TT_Task | CBTC/Stage-3 SMCSW[City] - Final Room Layout Drawing Victoria Cross Station SER [Post Stage 3] | 26/11/2021 | 13/12/2021 | 10/11/2021 | 21/01/2022 | 0 | TK_Complete | 1112893334 | 353 | 1112893334_353
C730D157BC###N949493 | TT_Task | CBTC/Stage-3 SMCSW[City] - Final Room Layout Drawings Customer review Northern Connection CHW SER [Post Stage 3] | 11/04/2022 | 11/04/2022 | nan | nan | 160 | TK_NotStart | 1112893334 | 353 | 1112893334_353
C730D157BC###N949513 | TT_Task | CBTC/Stage-3 SMCSW[City] - Final Room Layout Drawing Customer review Victoria Cross Station SER [Post Stage 3] | 31/01/2022 | 11/02/2022 | 31/01/2022 | 11/02/2022 | 0 | TK_Complete | 1112893334 | 353 | 1112893334_353
C730D157BC###N949533 | TT_Task | CBTC/Stage-3 SMCSW[City] - Final Room Layout Drawing Customer review Martin Place Station SER [Post Stage 3] | 07/02/2022 | 18/02/2022 | 07/02/2022 | 18/02/2022 | 0 | TK_Complete | 1112893334 | 353 | 1112893334_353
C730D157BC###N949543 | TT_Task | CBTC/Stage-3 SMCSW[City] - Final Room Layout Drawing Customer review Pitt St Station SER [Post Stage 3] | 27/12/2021 | 07/01/2022 | 24/01/2022 | 07/02/2022 | 0 | TK_Complete | 1112893334 | 353 | 1112893334_353
C730D157BC###N949553 | TT_Task | CBTC/Stage-3 SMCSW[City] - Final Room Layout Drawing Customer review Central Station SER [Post Stage 3] | 27/12/2021 | 07/01/2022 | 14/01/2022 | nan | 0 | TK_Active | 1112893334 | 353 | 1112893334_353
C730D157BC###N949563 | TT_Task | CBTC/Stage-3 SMCSW[City] - Final Room Layout Drawing Customer review Waterloo Station SER [Post Stage 3] | 27/12/2021 | 07/01/2022 | 14/01/2022 | nan | 0 | TK_Active | 1112893334 | 353 | 1112893334_353
C730D157BC###N949573 | TT_Task | CBTC/Stage-3 SMCSW[City] - Final Room Layout Drawing Customer review Sydenham Station SER [Post Stage 3] | 17/12/2021 | 30/12/2021 | 11/10/2021 | 15/10/2021 | 0 | TK_Complete | 1112893334 | 353 | 1112893334_353
C730D157BC###0012020 | TT_Task | CBTC/Stage-2 SMCSW - Provide initial inputs to FIW contractor of MP, VC and LW to undertake interface contractor design | 31/10/2019 | 27/11/2019 | 19/08/2019 | 30/08/2019 | 0 | TK_Complete | 1112893334 | 352 | 1112893334_352
C730D157BC###0012025 | TT_Task | CBTC/Stage-2 SMCSW - Provide initial inputs to FIW contractor of Crows Nest to undertake interface contractor design | 31/10/2019 | 27/11/2019 | 14/10/2019 | 30/10/2019 | 0 | TK_Complete | 1112893334 | 352 | 1112893334_352
C730D157BC###0012000 | TT_Task | CBTC/Stage-2 SMCSW - Complete mark-up for interface drawings for Sydenham station | 30/09/2019 | 28/10/2019 | 01/03/2019 | 07/06/2019 | 0 | TK_Complete | 1112893334 | 351 | 1112893334_351
C730D157BC###0012005 | TT_Task | CBTC/Stage-2 SMCSW - Complete mark-up for interface drawings for Barangaroo station | 01/07/2019 | 26/07/2019 | 01/03/2019 | 05/06/2019 | 0 | TK_Complete | 1112893334 | 351 | 1112893334_351
C730D157BC###0012010 | TT_Task | CBTC/Stage-2 SMCSW - Complete mark-up for interface drawings for Victoria Cross station | 01/07/2019 | 26/07/2019 | 14/05/2019 | 20/06/2019 | 0 | TK_Complete | 1112893334 | 351 | 1112893334_351
C730D157BC###0012015 | TT_Task | CBTC/Stage-2 SMCSW - Complete mark-up for interface drawings for Central station | 01/07/2019 | 26/07/2019 | 28/05/2019 | 20/06/2019 | 0 | TK_Complete | 1112893334 | 351 | 1112893334_351
C730D157BC###0012030 | TT_Task | CBTC/Stage-2 SMCSW - Complete mark-up for interface drawings for Crows Nest station | 25/03/2020 | 23/04/2020 | 02/12/2019 | 08/01/2020 | 0 | TK_Complete | 1112893334 | 351 | 1112893334_351
C730D157BC###0012035 | TT_Task | CBTC/Stage-2 SMCSW - Complete mark-up for interface drawings for SMTF(S) Administration building | 31/10/2019 | 27/11/2019 | 01/10/2019 | 07/02/2020 | 0 | TK_Complete | 1112893334 | 351 | 1112893334_351
C730D157BC###0012040 | TT_Task | CBTC/Stage-2 SMCSW - Complete mark-up for interface drawings for Martin Place station | 31/10/2019 | 27/11/2019 | 10/10/2019 | 13/11/2019 | 0 | TK_Complete | 1112893334 | 351 | 1112893334_351
C730D157BC###0012045 | TT_Task | CBTC/Stage-2 SMCSW - Complete mark-up for interface drawings for Pitt Street station | 25/03/2020 | 23/04/2020 | 02/12/2019 | 08/01/2020 | 0 | TK_Complete | 1112893334 | 351 | 1112893334_351
C730D157BC###0012050 | TT_Task | CBTC/Stage-2 SMCSW - Complete mark-up for interface drawings for Waterloo station | 25/03/2020 | 23/04/2020 | 05/12/2019 | 14/02/2020 | 0 | TK_Complete | 1112893334 | 351 | 1112893334_351
C730D157BC###0036140 | TT_Task | CBTC/Stage-2 SMCSW - Initial DIS ; DITP 'Trains' (SIG/RS) | 01/07/2019 | 20/09/2019 | 15/05/2019 | 30/06/2019 | 0 | TK_Complete | 1112893334 | 350 | 1112893334_350
C730D157BC###0037750 | TT_Task | CBTC/Stage-3 SMCSW - Final DIS ; DITP 'Trains' (RS) | 31/10/2019 | 06/01/2020 | 24/09/2019 | 11/12/2019 | 0 | TK_Complete | 1112893334 | 350 | 1112893334_350
C730D157BC###0068395 | TT_Task | CBTC/Stage-3 SMCSW - Final DIS ; DITP 'Trains' (SIG/SRS) ***Out of scope*** | 25/02/2020 | 11/03/2020 | 25/02/2020 | 25/02/2020 | 0 | TK_Complete | 1112893334 | 350 | 1112893334_350
C730D157BC###0011024 | TT_Task | CBTC/Stage-3 SMCSW - Inital ITS 'Trains' (SIG/RS) | 25/03/2020 | 16/04/2020 | 11/11/2019 | 02/12/2019 | 0 | TK_Complete | 1112893334 | 350 | 1112893334_350
C730D157BC###0061793 | TT_Task | CBTC/Stage-3 SMCSW - Inital ITS 'Trains' (SRS) - **not applicable | 29/05/2020 | 19/06/2020 | 23/03/2020 | 23/03/2020 | 0 | TK_Complete | 1112893334 | 350 | 1112893334_350
C730D157BC###0061721 | TT_Task | CBTC/Stage-3 SMCSW - Final ITS 'Trains' (RS) | 25/08/2020 | 13/10/2020 | 03/08/2020 | 04/09/2020 | 0 | TK_Complete | 1112893334 | 350 | 1112893334_350
C730D157BC###0061838 | TT_Task | CBTC/Stage-3 SMCSW - Final ITS 'Trains' SRS - **not applicable | 13/10/2020 | 30/11/2020 | 25/08/2020 | 25/08/2020 | 0 | TK_Complete | 1112893334 | 350 | 1112893334_350
C720D147CF###0020240 | TT_Task | Trains/Stage-3 - Design activities to prepare and submit final O;M manuals, as built drawings and test records- Batch1 | 15/03/2023 | 04/04/2023 | nan | nan | 0 | TK_NotStart | 1112893334 | 35 | 1112893334_35
C720D147CF###0021070 | TT_Task | Trains/Stage-3 - Design activities to prepare and submit final O;M manuals, as built drawings and test records- Batch2 | 05/04/2023 | 28/04/2023 | nan | nan | 0 | TK_NotStart | 1112893334 | 35 | 1112893334_35
C720D147CF###0021080 | TT_Task | Trains/Stage-3 - Design activities to prepare and submit final O;M manuals, as built drawings and test records- Batch3 | 01/05/2023 | 19/05/2023 | nan | nan | 0 | TK_NotStart | 1112893334 | 35 | 1112893334_35
C730D157BC###0036130 | TT_Task | CBTC/Stage-2 SMCSW - Initial DIS ; DITP 'Radio System' (SIG/RAD) - [achieved at A2 SMTF-N activity] | 01/07/2019 | 20/09/2019 | 15/05/2019 | 30/06/2019 | 0 | TK_Complete | 1112893334 | 349 | 1112893334_349
C730D157BC###0037740 | TT_Task | CBTC/Stage-3 SMCSW - Final DIS ; DITP 'Radio System' (SIG/RAD) - [same document @SMTF-N act.] | 31/10/2019 | 06/01/2020 | 24/09/2019 | 11/12/2019 | 0 | TK_Complete | 1112893334 | 349 | 1112893334_349
C730D157BC###0011033 | TT_Task | CBTC/Stage-3 SMCSW - Inital ITS 'Radio System' (SIG/RAD) | 17/04/2020 | 07/05/2020 | 11/11/2019 | 29/11/2019 | 0 | TK_Complete | 1112893334 | 349 | 1112893334_349
C730D157BC###0061757 | TT_Task | CBTC/Stage-3 SMCSW - Final ITS 'Radio System' (SIG/RAD) | 25/08/2020 | 13/10/2020 | 03/08/2020 | 04/09/2020 | 0 | TK_Complete | 1112893334 | 349 | 1112893334_349
C730D157BC###0035800 | TT_Task | CBTC/Stage-2 SMCSW - Initial DIS ; DITP 'Operation Control Centre' (SIG/OCC) | 01/07/2019 | 20/09/2019 | 15/05/2019 | 30/06/2019 | 0 | TK_Complete | 1112893334 | 348 | 1112893334_348
C730D157BC###0037870 | TT_Task | CBTC/Stage-3 SMCSW - Final DIS ; DITP 'Operation Control Centre' (SIG/OCC) | 04/02/2020 | 30/03/2020 | 04/02/2020 | 29/04/2020 | 0 | TK_Complete | 1112893334 | 348 | 1112893334_348
C730D157BC###0061829 | TT_Task | CBTC/Stage-3 SMCSW - Inital ITS 'Operation Control Centre' (SIG/OCC) | 13/10/2020 | 26/10/2020 | 17/08/2020 | 03/09/2020 | 0 | TK_Complete | 1112893334 | 348 | 1112893334_348
C730D157BC###0061874 | TT_Task | CBTC/Stage-3 SMCSW - Final ITS 'Operation Control Centre' (SIG/OCC) | 27/10/2020 | 14/12/2020 | 18/08/2020 | 03/09/2020 | 0 | TK_Complete | 1112893334 | 348 | 1112893334_348
C730D157BC###0035780 | TT_Task | CBTC/Stage-2 SMCSW - Initial DIS ; DITP 'Central Station Main Works Contractor' (SIG/CSM) | 01/07/2019 | 20/09/2019 | 15/05/2019 | 30/06/2019 | 0 | TK_Complete | 1112893334 | 347 | 1112893334_347
C730D157BC###0078132 | TT_Task | CBTC/Stage-2 SMCSW - Initial DIS ; DITP 'Crows Nest Contractor' (SIG/CST) | 24/04/2020 | 12/06/2020 | 26/02/2020 | 10/03/2020 | 0 | TK_Complete | 1112893334 | 347 | 1112893334_347
C730D157BC###0037850 | TT_Task | CBTC/Stage-3 SMCSW - Final DIS ; DITP 'Central Station Main Works Contractor' (SIG/CSM) | 31/10/2019 | 06/01/2020 | 10/10/2019 | 10/12/2019 | 0 | TK_Complete | 1112893334 | 347 | 1112893334_347
C730D157BC###0061820 | TT_Task | CBTC/Stage-3 SMCSW - Inital ITS 'Central Station Main Works Contractor' (SIG/CSM) | 13/10/2020 | 26/10/2020 | 25/08/2020 | 07/09/2020 | 0 | TK_Complete | 1112893334 | 347 | 1112893334_347
C730D157BC###0061865 | TT_Task | CBTC/Stage-3 SMCSW - Final ITS 'Central Station Main Works Contractor' (SIG/CSM) | 27/10/2020 | 14/12/2020 | 17/08/2020 | 07/09/2020 | 0 | TK_Complete | 1112893334 | 347 | 1112893334_347
C730D157BC###0035730 | TT_Task | CBTC/Stage-2 SMCSW - Initial DIS ; DITP 'Stations Contractor 4 stations' (SIG/STME) | 01/07/2019 | 20/09/2019 | 15/05/2019 | 30/06/2019 | 0 | TK_Complete | 1112893334 | 346 | 1112893334_346
C730D157BC###0066823 | TT_Task | CBTC/Stage-2 SMCSW - Initial DIS ; DITP 'Stations Contractor 2 stations PITT+WLO' (SIG/STME) | 24/04/2020 | 12/06/2020 | 26/02/2020 | 10/03/2020 | 0 | TK_Complete | 1112893334 | 346 | 1112893334_346
C730D157BC###0037810 | TT_Task | CBTC/Stage-3 SMCSW - Final DIS ; DITP 'Martin Place station' (SIG/STME) | 31/10/2019 | 06/01/2020 | 10/10/2019 | 10/12/2019 | 0 | TK_Complete | 1112893334 | 346 | 1112893334_346
C730D157BC###0066833 | TT_Task | CBTC/Stage-3 SMCSW - Final DIS ; DITP 'WLO Station' (SIG/STME) | 25/08/2020 | 14/09/2020 | 17/08/2020 | 10/09/2020 | 0 | TK_Complete | 1112893334 | 346 | 1112893334_346
C730D157BC###0068415 | TT_Task | CBTC/Stage-3 SMCSW - Final DIS ; DITP 'Crows Nest Station' (SIG/STME) | 25/08/2020 | 14/09/2020 | 17/08/2020 | 10/09/2020 | 0 | TK_Complete | 1112893334 | 346 | 1112893334_346
C730D157BC###0068422 | TT_Task | CBTC/Stage-3 SMCSW - Final DIS ; DITP 'Barangaroo Station' (SIG/STME) | 31/10/2019 | 06/01/2020 | 15/10/2019 | 10/12/2019 | 0 | TK_Complete | 1112893334 | 346 | 1112893334_346
C730D157BC###0068432 | TT_Task | CBTC/Stage-3 SMCSW - Final DIS ; DITP 'Victoria Cross Station' (SIG/STME) | 31/10/2019 | 06/01/2020 | 15/10/2019 | 10/12/2019 | 0 | TK_Complete | 1112893334 | 346 | 1112893334_346
C730D157BC###0068441 | TT_Task | CBTC/Stage-3 SMCSW - Final DIS ; DITP 'PITT St Station' (SIG/STME) | 25/08/2020 | 14/09/2020 | 17/08/2020 | 10/09/2020 | 0 | TK_Complete | 1112893334 | 346 | 1112893334_346
C730D157BC###0011012 | TT_Task | CBTC/Stage-3 SMCSW - Inital ITS 'Martin Place Station' (SIG/STME) | 25/08/2020 | 07/09/2020 | 10/08/2020 | 07/09/2020 | 0 | TK_Complete | 1112893334 | 346 | 1112893334_346
C730D157BC###0061802 | TT_Task | CBTC/Stage-3 SMCSW - Inital ITS 'Victoria Station' (SIG/STME) | 13/10/2020 | 26/10/2020 | 24/08/2020 | 08/09/2020 | 0 | TK_Complete | 1112893334 | 346 | 1112893334_346
C730D157BC###0061811 | TT_Task | CBTC/Stage-3 SMCSW - Inital ITS 'Barangaroo Station' (SIG/STME) | 13/10/2020 | 26/10/2020 | 18/08/2020 | 08/09/2020 | 0 | TK_Complete | 1112893334 | 346 | 1112893334_346
C730D157BC###0061883 | TT_Task | CBTC/Stage-3 SMCSW - Inital ITS 'Station Contractors Waterloo' (SIG/STME) | 25/02/2021 | 17/03/2021 | 26/08/2020 | 08/09/2020 | 0 | TK_Complete | 1112893334 | 346 | 1112893334_346
C730D157BC###0061892 | TT_Task | CBTC/Stage-3 SMCSW - Inital ITS 'Crows Nest Station' (SIG/STME) | 25/02/2021 | 17/03/2021 | 22/03/2021 | 20/04/2021 | 0 | TK_Complete | 1112893334 | 346 | 1112893334_346
C730D157BC###0061919 | TT_Task | CBTC/Stage-3 SMCSW - Inital ITS 'Station Contractors PITT St (SIG/STME) | 25/02/2021 | 17/03/2021 | 22/03/2021 | 19/04/2021 | 0 | TK_Complete | 1112893334 | 346 | 1112893334_346
C730D157BC###0061712 | TT_Task | CBTC/Stage-3 SMCSW - Final ITS 'Station Contractors Martin Place Station (SIG/STME) | 13/10/2020 | 16/11/2020 | 10/08/2020 | 07/09/2020 | 0 | TK_Complete | 1112893334 | 346 | 1112893334_346
C730D157BC###0061847 | TT_Task | CBTC/Stage-3 SMCSW - Final ITS 'Station Contractors Victoria Cross Station (SIG/STME) | 25/11/2020 | 19/01/2021 | 26/08/2020 | 08/09/2020 | 0 | TK_Complete | 1112893334 | 346 | 1112893334_346
C730D157BC###0061856 | TT_Task | CBTC/Stage-3 SMCSW - Final ITS 'Station Contractors Barangaroo Station (SIG/STME) | 25/11/2020 | 19/01/2021 | 26/08/2020 | 08/09/2020 | 0 | TK_Complete | 1112893334 | 346 | 1112893334_346
C730D157BC###0061901 | TT_Task | CBTC/Stage-3 SMCSW - Final ITS 'Station Contractors WLO Station (SIG/STME) | 20/10/2020 | 07/12/2020 | 26/08/2020 | 08/09/2020 | 0 | TK_Complete | 1112893334 | 346 | 1112893334_346
C730D157BC###0061937 | TT_Task | CBTC/Stage-3 SMCSW - Final ITS 'Station Contractors Crows Nest Station (SIG/STME) | 10/05/2021 | 25/06/2021 | 20/04/2021 | 07/06/2021 | 0 | TK_Complete | 1112893334 | 346 | 1112893334_346
C730D157BC###0061955 | TT_Task | CBTC/Stage-3 SMCSW - Final ITS 'Station Contractors PITT St (SIG/STME) | 12/05/2021 | 29/06/2021 | 20/04/2021 | 18/06/2021 | 0 | TK_Complete | 1112893334 | 346 | 1112893334_346
C730D157BC###0035720 | TT_Task | CBTC/Stage-2 SMCSW - Initial DIS ; DITP 'Sydenham Station ; Junction Contractor' (CBTC/SSJ) | 01/07/2019 | 20/09/2019 | 15/05/2019 | 30/06/2019 | 0 | TK_Complete | 1112893334 | 345 | 1112893334_345
C730D157BC###0037790 | TT_Task | CBTC/Stage-3 SMCSW - Final DIS ; DITP 'Sydenham Station ; Junction Contractor' (CBTC/SSJ) | 31/10/2019 | 06/01/2020 | 10/10/2019 | 10/12/2019 | 0 | TK_Complete | 1112893334 | 345 | 1112893334_345
C730D157BC###0011027 | TT_Task | CBTC/Stage-3 SMCSW - Inital ITS 'Sydenham Station ; Junction Contractor' (CBTC/SSJ) | 25/08/2020 | 07/09/2020 | 10/08/2020 | 08/09/2020 | 0 | TK_Complete | 1112893334 | 345 | 1112893334_345
C730D157BC###0061739 | TT_Task | CBTC/Stage-3 SMCSW - Final ITS 'Sydenham Station ; Junction Contractor' (CBTC/SSJ) | 13/10/2020 | 30/11/2020 | 10/08/2020 | 08/09/2020 | 0 | TK_Complete | 1112893334 | 345 | 1112893334_345
C730D157BC###0035713 | TT_Task | CBTC/Stage-2 SMCSW - Initial DIS ; DITP 'Tunnel and Station Excavation Works Contractor' (SIG/TSE) | 01/07/2019 | 20/09/2019 | 15/05/2019 | 30/06/2019 | 0 | TK_Complete | 1112893334 | 344 | 1112893334_344
C730D157BC###0037780 | TT_Task | CBTC/Stage-3 SMCSW - Final DIS ; DITP 'Tunnel and Station Excavation Works Contractor' (SIG/TSE) | 31/10/2019 | 06/01/2020 | 10/10/2019 | 10/12/2019 | 0 | TK_Complete | 1112893334 | 344 | 1112893334_344
C730D157BC###0011009 | TT_Task | CBTC/Stage-3 SMCSW - Inital ITS 'Tunnel and Station Excavation Works Contractor' (SIG/TSE) | 25/08/2020 | 07/09/2020 | 07/08/2020 | 08/09/2020 | 0 | TK_Complete | 1112893334 | 344 | 1112893334_344
C730D157BC###0061703 | TT_Task | CBTC/Stage-3 SMCSW - Final ITS 'Tunnel and Station Excavation Works Contractor' (SIG/TSE) | 13/10/2020 | 30/11/2020 | 07/08/2020 | 08/09/2020 | 0 | TK_Complete | 1112893334 | 344 | 1112893334_344
C730D157BC###0035690 | TT_Task | CBTC/Stage-2 SMCSW - Initial DIS ; DITP Sydney Metro Train Facility South (SIG/SMTF(South) | 01/07/2019 | 20/09/2019 | 15/05/2019 | 30/06/2019 | 0 | TK_Complete | 1112893334 | 343 | 1112893334_343
C730D157BC###0037710 | TT_Task | CBTC/Stage-3 SMCSW - Final DIS ; DITP Sydney Metro Train Facility South (SIG/SMTF(South) | 31/10/2019 | 06/01/2020 | 24/09/2019 | 10/12/2019 | 0 | TK_Complete | 1112893334 | 343 | 1112893334_343
C730D157BC###0011021 | TT_Task | CBTC/Stage-3 SMCSW - Inital ITS Sydney Metro Train Facility South (SIG/SMTF(South) | 02/11/2020 | 13/11/2020 | 25/08/2020 | 08/09/2020 | 0 | TK_Complete | 1112893334 | 343 | 1112893334_343
C730D157BC###0061730 | TT_Task | CBTC/Stage-3 SMCSW - Final ITS Sydney Metro Train Facility South (SIG/SMTF(South) | 17/11/2020 | 14/12/2020 | 10/08/2020 | 08/09/2020 | 0 | TK_Complete | 1112893334 | 343 | 1112893334_343
C730K147BC###N70930 | TT_Task | ITS Finalization Site Access Inspections Sydney Metro Train Facility South (SIG/SMTF(South) | 25/02/2022 | 07/04/2022 | 23/01/2022 | 07/03/2022 | 0 | TK_Complete | 1112893334 | 343 | 1112893334_343
C730D157BC###0035660 | TT_Task | CBTC/Stage-2 SMCSW - Initial DIS ; DITP Track ; Tunnel Services (SIG/Tunnel) | 01/07/2019 | 20/09/2019 | 15/05/2019 | 30/06/2019 | 0 | TK_Complete | 1112893334 | 342 | 1112893334_342
C730D157BC###0067603 | TT_Task | CBTC/Stage-3 SMCSW - Final DIS ; DITP 'Signalling System (SIG/LW) - Line Wide Tunnel Works | 31/10/2019 | 06/01/2020 | 15/10/2019 | 16/03/2020 | 0 | TK_Complete | 1112893334 | 342 | 1112893334_342
C730D157BC###0011042 | TT_Task | CBTC/Stage-3 SMCSW - Inital ITS 'Signalling System' (LW/SIG) - Line Wide Tunnel Works | 25/08/2020 | 07/09/2020 | 12/08/2020 | 08/09/2020 | 0 | TK_Complete | 1112893334 | 342 | 1112893334_342
C730D157BC###0061784 | TT_Task | CBTC/Stage-3 SMCSW - Final ITS 'Signalling System' (LW/SIG) - Line Wide Tunnel Works | 13/10/2020 | 30/11/2020 | 12/08/2020 | 08/09/2020 | 0 | TK_Complete | 1112893334 | 342 | 1112893334_342
C730D157BC###0037510 | TT_Task | CBTC/Stage-2 SMCSW - Application Engineering Risk Analysis - **N/A | 24/08/2020 | 26/08/2020 | 04/02/2020 | 24/02/2020 | 0 | TK_Complete | 1112893334 | 341 | 1112893334_341
C730D157BC###0031937 | TT_Task | CBTC/Stage-3 SMCSW - EMI Hazard Analysis (EMI Risk Analysis) | 08/02/2021 | 26/03/2021 | 10/09/2020 | 09/03/2021 | 0 | TK_Complete | 1112893334 | 341 | 1112893334_341
C730D157BC###0032027 | TT_Task | CBTC/Stage-3 SMCSW - Application Engineering Risk Analysis | 16/05/2022 | 03/06/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 341 | 1112893334_341
C730D157BC###0036420 | TT_Task | CBTC/Stage-2 SMCSW - WCR Hardware Safety Analysis - **N/A | 10/03/2020 | 12/03/2020 | 04/02/2020 | 24/02/2020 | 0 | TK_Complete | 1112893334 | 340 | 1112893334_340
C730D157BC###0036980 | TT_Task | CBTC/Stage-2 SMCSW - Car-borne Controller Hardware Hazard Analysis - **N/A | 26/03/2020 | 30/03/2020 | 04/02/2020 | 24/02/2020 | 0 | TK_Complete | 1112893334 | 340 | 1112893334_340
C730D157BC###0037420 | TT_Task | CBTC/Stage-2 SMCSW - Car-borne Controller Hardware Safety Verification and Validation Report - **N/A | 13/04/2020 | 14/04/2020 | 04/02/2020 | 24/02/2020 | 0 | TK_Complete | 1112893334 | 340 | 1112893334_340
C730D157BC###0038250 | TT_Task | CBTC/Stage-2 SMCSW - Wayside Interface HwSA? (Hardware Safety Analysis) - **N/A | 19/05/2020 | 21/05/2020 | 04/02/2020 | 24/02/2020 | 0 | TK_Complete | 1112893334 | 340 | 1112893334_340
C720D147CF###0020320 | TT_Task | Trains/Stage-3 - Bogie installations release - Batch 1 | 11/02/2021 | 24/03/2021 | 27/07/2020 | 24/08/2020 | 0 | TK_Complete | 1112893334 | 34 | 1112893334_34
C720D147CF###0021050 | TT_Task | Trains/Stage-3 - Bogie installations release - Batch 2 | 25/03/2021 | 07/05/2021 | 24/08/2020 | 14/09/2020 | 0 | TK_Complete | 1112893334 | 34 | 1112893334_34
C720D147CF###0021060 | TT_Task | Trains/Stage-3 - Bogie installations release - Batch 3 | 19/11/2020 | 14/01/2021 | 15/09/2020 | 25/11/2020 | 0 | TK_Complete | 1112893334 | 34 | 1112893334_34
C730D157BC###0037690 | TT_Task | CBTC/Stage-2 SMCSW - Earthing Installation Rules | 17/07/2020 | 13/08/2020 | 06/04/2020 | 17/04/2020 | 0 | TK_Complete | 1112893334 | 339 | 1112893334_339
C730D157BC###0031928 | TT_Task | CBTC/Stage-3 SMCSW - Earthing Installation Rules | 21/05/2021 | 02/07/2021 | 11/08/2020 | 20/10/2020 | 0 | TK_Complete | 1112893334 | 339 | 1112893334_339
C730D157BC###0037140 | TT_Task | CBTC/Stage-2 SMCSW - EMC Product Compliance Analysis - (*covered at stage 3) | 08/06/2020 | 03/07/2020 | 16/04/2020 | 16/04/2020 | 0 | TK_Complete | 1112893334 | 338 | 1112893334_338
C730D157BC###0031883 | TT_Task | CBTC/Stage-3 SMCSW - EMC Product Compliance Analysis | 09/04/2021 | 21/05/2021 | 10/08/2020 | 28/08/2020 | 0 | TK_Complete | 1112893334 | 338 | 1112893334_338
C730D157BC###0038500 | TT_Task | CBTC/Stage-2 SMCSW - Spare List (Draft) - (*covered at stage 3) | 13/07/2020 | 10/08/2020 | 18/05/2020 | 18/05/2020 | 0 | TK_Complete | 1112893334 | 337 | 1112893334_337
C730D157BC###0032036 | TT_Task | CBTC/Stage-3 SMCSW - Spare List (Final) | 25/03/2022 | 03/06/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 337 | 1112893334_337
C730D157BC###0036900 | TT_Task | CBTC/Stage-2 SMCSW - System Reliability Growth Plan | 29/05/2020 | 26/06/2020 | 30/03/2020 | 13/04/2020 | 0 | TK_Complete | 1112893334 | 336 | 1112893334_336
C730D157BC###0031892 | TT_Task | CBTC/Stage-3 SMCSW - System Reliability Growth Plan | 15/04/2021 | 19/05/2021 | 01/09/2020 | 14/09/2020 | 0 | TK_Complete | 1112893334 | 336 | 1112893334_336
C730D167BC###0037080 | TT_Task | CBTC/Stage-2 SMCSW - SyRTD - Test Description | 08/06/2020 | 26/06/2020 | 06/04/2020 | 05/06/2020 | 0 | TK_Complete | 1112893334 | 335 | 1112893334_335
C730D157BC###0022183 | TT_Task | CBTC/Stage-3 SMCSW - SyCR Verification | 25/07/2022 | 05/08/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 335 | 1112893334_335
C730D157BC###0022213 | TT_Task | CBTC/Stage-3 SMCSW - SyDT Verification | 08/08/2022 | 26/08/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 335 | 1112893334_335
C730D157BC###0022237 | TT_Task | CBTC/Stage-3 SMCSW - RTI Verification | 29/08/2022 | 16/09/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 335 | 1112893334_335
C730D157BC###0039850 | TT_Task | CBTC/Stage-3 SMCSW - SyRTD - Test Description | 07/09/2020 | 02/10/2020 | 27/07/2020 | 07/08/2020 | 0 | TK_Complete | 1112893334 | 335 | 1112893334_335
C730D167BC###0037040 | TT_Task | CBTC/Stage-2 SMCSW - In-saloon CCTV system - Operational Manual | 02/06/2020 | 22/06/2020 | 09/03/2020 | 24/03/2020 | 0 | TK_Complete | 1112893334 | 334 | 1112893334_334
C730D167BC###0037072 | TT_Task | CBTC/Stage-2 SMCSW - In-saloon CCTV system - Maintenance Manual | 18/05/2020 | 05/06/2020 | 06/04/2020 | 14/05/2020 | 0 | TK_Complete | 1112893334 | 334 | 1112893334_334
C730D157BC###0038470 | TT_Task | CBTC/Stage-3 SMCSW - In-saloon CCTV system - Operational Manual | 26/10/2020 | 20/11/2020 | 26/10/2020 | 09/12/2020 | 0 | TK_Complete | 1112893334 | 334 | 1112893334_334
C730D157BC###0038480 | TT_Task | CBTC/Stage-3 SMCSW - In-saloon CCTV system - Maintenance Manual | 25/11/2020 | 22/12/2020 | 26/10/2020 | 09/12/2020 | 0 | TK_Complete | 1112893334 | 334 | 1112893334_334
C730D157BC###0037060 | TT_Task | CBTC/Stage-2 SMCSW - ATS Alarms and Events Specification | 22/06/2020 | 10/07/2020 | 18/05/2020 | 08/06/2020 | 0 | TK_Complete | 1112893334 | 333 | 1112893334_333
C730D157BC###0038600 | TT_Task | CBTC/Stage-3 SMCSW - ATS Alarms ; Events | 04/03/2021 | 17/03/2021 | 21/12/2020 | 29/03/2021 | 0 | TK_Complete | 1112893334 | 333 | 1112893334_333
C730D157BC###0036810 | TT_Task | CBTC/Stage-2 SMCSW - Stations-ATS Equipment Drawings | 27/07/2020 | 14/08/2020 | 22/05/2020 | 30/06/2020 | 0 | TK_Complete | 1112893334 | 332 | 1112893334_332
C730D157BC###0036820 | TT_Task | CBTC/Stage-2 SMCSW - BOCC-ATS Equipment Drawing | 27/07/2020 | 28/08/2020 | 22/05/2020 | 30/06/2020 | 0 | TK_Complete | 1112893334 | 332 | 1112893334_332
C730D157BC###0036830 | TT_Task | CBTC/Stage-2 SMCSW - Depot-ATS Equipment Drawings | 27/07/2020 | 14/08/2020 | 22/05/2020 | 30/06/2020 | 0 | TK_Complete | 1112893334 | 332 | 1112893334_332
C730D157BC###0039060 | TT_Task | CBTC/Stage-3 SMCSW - Stations-ATS Equipment Drawings | 25/03/2021 | 21/04/2021 | 24/03/2021 | nan | 0 | TK_Active | 1112893334 | 332 | 1112893334_332
C730D157BC###0039070 | TT_Task | CBTC/Stage-3 SMCSW - BOCC-ATS Equipment Drawing | 03/05/2022 | 06/06/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 332 | 1112893334_332
C730D157BC###0039080 | TT_Task | CBTC/Stage-3 SMCSW - Depot-ATS Equipment Drawings | 17/05/2022 | 06/06/2022 | nan | nan | 40 | TK_NotStart | 1112893334 | 332 | 1112893334_332
C730D157BC###0036690 | TT_Task | CBTC/Stage-2 SMCSW - Offline Graphical Timetable (OGT) User Manual | 22/06/2020 | 31/07/2020 | 18/05/2020 | 02/06/2020 | 0 | TK_Complete | 1112893334 | 331 | 1112893334_331
C730D157BC###0038940 | TT_Task | CBTC/Stage-3 SMCSW - Offline Graphical Timetable (OGT) User Manual | 26/10/2020 | 04/12/2020 | 16/11/2020 | 15/12/2020 | 0 | TK_Complete | 1112893334 | 331 | 1112893334_331
C730D157BC###0087441 | TT_Task | CBTC/Stage-2 SMCSW - DCS Drawings - Chatswood- Crows Nest | 27/05/2020 | 02/06/2020 | 27/04/2020 | 07/05/2020 | 0 | TK_Complete | 1112893334 | 330 | 1112893334_330
C730D157BC###0087455 | TT_Task | CBTC/Stage-2 SMCSW - DCS Drawings - Crows Nest - Victoria Cross | 03/06/2020 | 09/06/2020 | 05/05/2020 | 19/05/2020 | 0 | TK_Complete | 1112893334 | 330 | 1112893334_330
C730D157BC###0040510 | TT_Task | CBTC/Stage-3 SMCSW - DCS Drawings - Chatswood- Crows Nest | 08/04/2021 | 02/06/2021 | 01/02/2021 | 19/02/2021 | 0 | TK_Complete | 1112893334 | 330 | 1112893334_330
C730D157BC###0071709 | TT_Task | CBTC/Stage-3 SMCSW - DCS Drawings - Crows Nest - Victoria Cross | 03/06/2021 | 16/06/2021 | 01/02/2021 | 19/02/2021 | 0 | TK_Complete | 1112893334 | 330 | 1112893334_330
C720D147CF###0020310 | TT_Task | Trains/Stage-3 - Fitting installations release - Batch 1 | 16/10/2020 | 12/11/2020 | 27/07/2020 | 24/08/2020 | 0 | TK_Complete | 1112893334 | 33 | 1112893334_33
C720D147CF###0021010 | TT_Task | Trains/Stage-3 - Fitting installations release - Batch 2 | 13/11/2020 | 10/12/2020 | 27/07/2020 | 24/08/2020 | 0 | TK_Complete | 1112893334 | 33 | 1112893334_33
C720D147CF###0021020 | TT_Task | Trains/Stage-3 - Fitting installations release - Batch 3 | 11/12/2020 | 22/01/2021 | 24/08/2020 | 14/09/2020 | 0 | TK_Complete | 1112893334 | 33 | 1112893334_33
C720D147CF###0021030 | TT_Task | Trains/Stage-3 - Fitting installations release - Batch 4 | 19/11/2020 | 16/12/2020 | 24/08/2020 | 14/09/2020 | 0 | TK_Complete | 1112893334 | 33 | 1112893334_33
C720D147CF###0021040 | TT_Task | Trains/Stage-3 - Fitting installations release - Batch 5 | 04/12/2020 | 15/01/2021 | 15/09/2020 | 25/11/2020 | 0 | TK_Complete | 1112893334 | 33 | 1112893334_33
C730D157BC###0087329 | TT_Task | CBTC/Stage-2 SMCSW - DCS Trackside Survey Procedure | 14/07/2020 | 20/07/2020 | 02/03/2020 | 16/03/2020 | 0 | TK_Complete | 1112893334 | 329 | 1112893334_329
C730D157BC###0087364 | TT_Task | CBTC/Stage-2 SMCSW - DCS Train Survey Procedure | 21/07/2020 | 27/07/2020 | 18/03/2020 | 25/03/2020 | 0 | TK_Complete | 1112893334 | 329 | 1112893334_329
C730D157BC###0087413 | TT_Task | CBTC/Stage-2 SMCSW - DCS Trackside Survey Report (Site Access) - (*covered at Stage 3) | 26/06/2020 | 02/07/2020 | 18/05/2020 | 18/05/2020 | 0 | TK_Complete | 1112893334 | 329 | 1112893334_329
C730D157BC###0087427 | TT_Task | CBTC/Stage-2 SMCSW - DCS Train Survey Report | 13/08/2020 | 19/08/2020 | 18/03/2020 | 25/03/2020 | 0 | TK_Complete | 1112893334 | 329 | 1112893334_329
C730D157BC###0071763 | TT_Task | CBTC/Stage-3 SMCSW - DCS Trackside Survey Report (Site Access) | 23/03/2022 | 29/03/2022 | 19/07/2021 | 23/07/2021 | 0 | TK_Complete | 1112893334 | 329 | 1112893334_329
C730D157BC###0087280 | TT_Task | CBTC/Stage-2 SMCSW - DCS Interference Survey Procedure | 07/07/2020 | 13/07/2020 | 24/02/2020 | 16/03/2020 | 0 | TK_Complete | 1112893334 | 328 | 1112893334_328
C730D157BC###0087378 | TT_Task | CBTC/Stage-2 SMCSW - DCS Interference Survey Report (Site Access) - (*covered at Stage 3) | 17/06/2020 | 25/06/2020 | 18/05/2020 | 18/05/2020 | 0 | TK_Complete | 1112893334 | 328 | 1112893334_328
C730D157BC###0071757 | TT_Task | CBTC/Stage-3 SMCSW - DCS Interference Survey Report (Site Access) | 14/03/2022 | 22/03/2022 | 19/07/2021 | 23/07/2021 | 0 | TK_Complete | 1112893334 | 328 | 1112893334_328
C730D157BC###0087217 | TT_Task | CBTC/Stage-2 SMCSW - DCS Wireless Products Datasheets book | 23/06/2020 | 29/06/2020 | 24/02/2020 | 16/03/2020 | 0 | TK_Complete | 1112893334 | 327 | 1112893334_327
C730D157BC###0087245 | TT_Task | CBTC/Stage-2 SMCSW - DCS Wireless Products Manuals and Maintenance book | 30/06/2020 | 06/07/2020 | 02/03/2020 | 16/03/2020 | 0 | TK_Complete | 1112893334 | 327 | 1112893334_327
C730D157BC###0039420 | TT_Task | CBTC/Stage-3 SMCSW - DCS Wireless Products Datasheets book | 12/03/2021 | 19/03/2021 | 27/07/2020 | 05/08/2020 | 0 | TK_Complete | 1112893334 | 327 | 1112893334_327
C730D157BC###0040630 | TT_Task | CBTC/Stage-3 SMCSW - DCS Wireless Products Manuals and Maintenance book | 30/11/2020 | 04/12/2020 | 26/10/2020 | 09/12/2020 | 0 | TK_Complete | 1112893334 | 327 | 1112893334_327
C730D157BC###0041140 | TT_Task | CBTC/Stage-3 SMCSW - DCS Installation Principles - DCS wireless Trackside | 25/10/2021 | 05/11/2021 | 25/10/2021 | 05/11/2021 | 0 | TK_Complete | 1112893334 | 327 | 1112893334_327
C730D157BC###0071703 | TT_Task | CBTC/Stage-3 SMCSW - DCS Installation Principles - DCS wireless Onboard | 10/08/2021 | 23/08/2021 | 19/07/2021 | 23/07/2021 | 0 | TK_Complete | 1112893334 | 327 | 1112893334_327
C730D157BC###0087105 | TT_Task | CBTC/Stage-2 SMCSW - DCS BTN Specification/SyHW (Internal) - City ; SW - (*covered at Stage 3) | 27/05/2020 | 09/06/2020 | 18/05/2020 | 18/05/2020 | 0 | TK_Complete | 1112893334 | 326 | 1112893334_326
C730D157BC###0087196 | TT_Task | CBTC/Stage-2 SMCSW - DCS BTN Specification/SyHW (Internal) -SW *repeat activitiy | 22/05/2020 | 04/06/2020 | 22/04/2020 | 22/04/2020 | 0 | TK_Complete | 1112893334 | 326 | 1112893334_326
C730D157BC###0087294 | TT_Task | CBTC/Stage-2 SMCSW - DCS BTN Products Manuals and Maintenance book | 07/07/2020 | 20/07/2020 | 02/03/2020 | 17/03/2020 | 0 | TK_Complete | 1112893334 | 326 | 1112893334_326
C730D157BC###0087357 | TT_Task | CBTC/Stage-2 SMCSW - DCS Operation Manual | 21/07/2020 | 27/07/2020 | 02/03/2020 | 16/03/2020 | 0 | TK_Complete | 1112893334 | 326 | 1112893334_326
C730D157BC###0087385 | TT_Task | CBTC/Stage-2 SMCSW - DCS BTN Products Datasheets book | 28/07/2020 | 03/08/2020 | 24/02/2020 | 16/03/2020 | 0 | TK_Complete | 1112893334 | 326 | 1112893334_326
C730D157BC###0021751 | TT_Task | CBTC/Stage-3 SMCSW - DCS BTN specification/SyHW | 01/04/2021 | 11/05/2021 | 01/04/2021 | 11/05/2021 | 0 | TK_Complete | 1112893334 | 326 | 1112893334_326
C730D157BC###0021757 | TT_Task | CBTC/Stage-3 SMCSW - DCS BTN Products Datasheets book | 16/10/2020 | 22/10/2020 | 27/07/2020 | 17/08/2020 | 0 | TK_Complete | 1112893334 | 326 | 1112893334_326
C730D157BC###0021763 | TT_Task | CBTC/Stage-3 SMCSW - DCS BTN Operational and Maintanance Manual | 09/11/2020 | 13/11/2020 | 26/10/2020 | 08/12/2020 | 0 | TK_Complete | 1112893334 | 326 | 1112893334_326
C730D157BC###0021781 | TT_Task | CBTC/Stage-3 SMCSW - DCS Operation Manual (Closed and Merged with DCS BTN Products Manuals and Maintenance Book ) | 11/03/2021 | 17/03/2021 | 26/01/2021 | 26/01/2021 | 0 | TK_Complete | 1112893334 | 326 | 1112893334_326
C730D157BC###0087063 | TT_Task | CBTC/Stage-2 SMCSW - DCS SMN Line Backbone - Detail Design | 26/05/2020 | 22/06/2020 | 23/03/2020 | 23/03/2020 | 0 | TK_Complete | 1112893334 | 325 | 1112893334_325
C730D157BC###0087112 | TT_Task | CBTC/Stage-2 SMCSW - DCS ATS Backbone Architecture document | 18/05/2020 | 29/05/2020 | 13/04/2020 | 13/05/2020 | 0 | TK_Complete | 1112893334 | 325 | 1112893334_325
C730D157BC###0021775 | TT_Task | CBTC/Stage-3 SMCSW - DCS SMN Line Backbone - Final Design | 08/03/2021 | 23/03/2021 | 08/03/2021 | 23/03/2021 | 0 | TK_Complete | 1112893334 | 325 | 1112893334_325
C730D157BC###0021811 | TT_Task | CBTC/Stage-3 SMCSW - DCS ATS Backbone Architecture document | 17/02/2021 | 03/03/2021 | 01/12/2020 | 11/12/2020 | 0 | TK_Complete | 1112893334 | 325 | 1112893334_325
C730D157BC###0087287 | TT_Task | CBTC/Stage-2 SMCSW - MSS Maintainer Manual | 08/06/2020 | 03/07/2020 | 03/02/2020 | 28/02/2020 | 0 | TK_Complete | 1112893334 | 324 | 1112893334_324
C730D157BC###0087406 | TT_Task | CBTC/Stage-2 SMCSW - MSS Products Manuals and Maintenance book | 06/07/2020 | 31/07/2020 | 05/02/2020 | 28/02/2020 | 0 | TK_Complete | 1112893334 | 324 | 1112893334_324
C730D157BC###0021895 | TT_Task | CBTC/Stage-3 SMCSW - MSS Maintainer Manual | 14/12/2020 | 08/01/2021 | 12/10/2020 | 01/02/2021 | 0 | TK_Complete | 1112893334 | 324 | 1112893334_324
C730D157BC###0022015 | TT_Task | CBTC/Stage-3 SMCSW - MSS Products Manuals and Maintenance book | 11/01/2021 | 26/02/2021 | 01/10/2020 | 01/02/2021 | 0 | TK_Complete | 1112893334 | 324 | 1112893334_324
C730D157BC###0087140 | TT_Task | CBTC/Stage-2 SMCSW - MSS-DCS Interface Specification | 12/05/2020 | 08/06/2020 | 02/03/2020 | 16/03/2020 | 0 | TK_Complete | 1112893334 | 323 | 1112893334_323
C730D157BC###0087238 | TT_Task | CBTC/Stage-2 SMCSW - DCS MSS-DCS Interface Specification | 13/07/2020 | 17/07/2020 | 02/03/2020 | 16/03/2020 | 0 | TK_Complete | 1112893334 | 323 | 1112893334_323
C730D157BC###0021835 | TT_Task | CBTC/Stage-3 SMCSW - MSS-DCS Interface Specification | 17/12/2020 | 03/02/2021 | 26/08/2020 | 26/11/2020 | 0 | TK_Complete | 1112893334 | 323 | 1112893334_323
C730D157BC###0021901 | TT_Task | CBTC/Stage-3 SMCSW - DCS MSS-DCS Interface Specification | 08/04/2021 | 21/04/2021 | 10/11/2020 | 26/11/2020 | 0 | TK_Complete | 1112893334 | 323 | 1112893334_323
C730D157BC###0087119 | TT_Task | CBTC/Stage-2 SMCSW - MSS Products Datasheets Book | 04/05/2020 | 29/05/2020 | 05/02/2020 | 28/02/2020 | 0 | TK_Complete | 1112893334 | 322 | 1112893334_322
C730D157BC###0036800 | TT_Task | CBTC/Stage-2 SMCSW - ATS Products Datasheets book | 15/06/2020 | 17/07/2020 | 13/05/2020 | 02/06/2020 | 0 | TK_Complete | 1112893334 | 322 | 1112893334_322
C730D157BC###0021829 | TT_Task | CBTC/Stage-3 SMCSW - MSS Products Datasheets Book | 30/11/2020 | 15/01/2021 | 11/08/2020 | 28/08/2020 | 0 | TK_Complete | 1112893334 | 322 | 1112893334_322
C730D157BC###0039050 | TT_Task | CBTC/Stage-3 SMCSW - ATS Products Datasheets book | 26/10/2020 | 20/11/2020 | 16/11/2020 | 15/12/2020 | 0 | TK_Complete | 1112893334 | 322 | 1112893334_322
C730D157BC###0087553 | TT_Task | CBTC/Stage-2 SMCSW - SMTF[S] - Depot Circuit Book - DSER Drawings - *N/A | 06/07/2020 | 24/07/2020 | 18/05/2020 | 18/05/2020 | 0 | TK_Complete | 1112893334 | 321 | 1112893334_321
C730D157BC###0022195 | TT_Task | CBTC/Stage-3 SMCSW - SMTF[S] - Depot Circuit Book - DSER Drawings | 28/04/2021 | 25/05/2021 | 05/04/2021 | 21/05/2021 | 0 | TK_Complete | 1112893334 | 321 | 1112893334_321
C730D156BC###0081820 | TT_Task | CBTC/As-Built SMCSW - Chatswood Circuit Book - SER Drawings | 21/03/2023 | 11/04/2023 | nan | nan | 480 | TK_NotStart | 1112893334 | 321 | 1112893334_321
C730D156BC###0081841 | TT_Task | CBTC/As-Built SMCSW - Waterloo Circuit Book - SER Drawings | 21/03/2023 | 11/04/2023 | nan | nan | 480 | TK_NotStart | 1112893334 | 321 | 1112893334_321
C730D156BC###0081859 | TT_Task | CBTC/As-Built SMCSW - Crowsnest Circuit Book - SER Drawings | 11/04/2023 | 02/05/2023 | nan | nan | 360 | TK_NotStart | 1112893334 | 321 | 1112893334_321
C730D156BC###0081874 | TT_Task | CBTC/As-Built SMCSW - Central Circuit Book - SER Drawings | 11/04/2023 | 02/05/2023 | nan | nan | 360 | TK_NotStart | 1112893334 | 321 | 1112893334_321
C730D156BC###0081901 | TT_Task | CBTC/As-Built SMCSW - Martin Place Circuit Book - SER Drawings | 02/05/2023 | 23/05/2023 | nan | nan | 240 | TK_NotStart | 1112893334 | 321 | 1112893334_321
C730D156BC###0081943 | TT_Task | CBTC/As-Built SMCSW - SMTF[S] - Depot Circuit Book - DSER Drawings | 13/06/2023 | 04/07/2023 | nan | nan | 0 | TK_NotStart | 1112893334 | 321 | 1112893334_321
C730D157BC###0087056 | TT_Task | CBTC/Stage-2 SMCSW - Waterloo Circuit Book - Cable layout | 02/03/2020 | 06/03/2020 | 01/05/2020 | 08/05/2020 | 0 | TK_Complete | 1112893334 | 320 | 1112893334_320
C730D157BC###0087077 | TT_Task | CBTC/Stage-2 SMCSW - Sydenham Circuit Book - Cable layout | 02/03/2020 | 10/03/2020 | 08/05/2020 | 27/05/2020 | 0 | TK_Complete | 1112893334 | 320 | 1112893334_320
C730D157BC###0087182 | TT_Task | CBTC/Stage-2 SMCSW - Chartswood Circuit Book - Cable layout | 30/06/2020 | 06/07/2020 | 27/05/2020 | 05/06/2020 | 0 | TK_Complete | 1112893334 | 320 | 1112893334_320
C730D157BC###0087203 | TT_Task | CBTC/Stage-2 SMCSW - Crowsnest Circuit Book - Cable layout | 27/07/2020 | 03/08/2020 | 18/05/2020 | 29/05/2020 | 0 | TK_Complete | 1112893334 | 320 | 1112893334_320
C730D157BC###0087224 | TT_Task | CBTC/Stage-2 SMCSW - Victoria Cross Circuit Book - Cable layout | 28/05/2020 | 03/06/2020 | 15/04/2020 | 28/04/2020 | 0 | TK_Complete | 1112893334 | 320 | 1112893334_320
C730D157BC###0087252 | TT_Task | CBTC/Stage-2 SMCSW - Barangaroo Circuit Book - Cable layout | 02/03/2020 | 09/03/2020 | 18/05/2020 | 29/05/2020 | 0 | TK_Complete | 1112893334 | 320 | 1112893334_320
C730D157BC###0087301 | TT_Task | CBTC/Stage-2 SMCSW - Martin Place Circuit Book - Cable layout | 12/06/2020 | 18/06/2020 | 20/04/2020 | 28/04/2020 | 0 | TK_Complete | 1112893334 | 320 | 1112893334_320
C730D157BC###0087336 | TT_Task | CBTC/Stage-2 SMCSW - Pitt Street Circuit Book - Cable layout | 02/03/2020 | 06/03/2020 | 28/04/2020 | 05/05/2020 | 0 | TK_Complete | 1112893334 | 320 | 1112893334_320
C730D157BC###0087371 | TT_Task | CBTC/Stage-2 SMCSW - Central Circuit Book - Cable layout | 02/03/2020 | 09/03/2020 | 12/05/2020 | 29/06/2020 | 0 | TK_Complete | 1112893334 | 320 | 1112893334_320
C730D157BC###0087308 | TT_Task | CBTC/Stage-2 SMCSW - SMTF[S] - Depot Circuit Book - Cable layout | 06/07/2020 | 24/07/2020 | 02/04/2020 | 13/05/2020 | 0 | TK_Complete | 1112893334 | 320 | 1112893334_320
C730D157BC###N27427 | TT_Task | CBTC/Stage-3 SMCSW - Intermediate - CBI Cable layout - Sydenham Station (SYD) | 02/12/2020 | 08/12/2020 | 23/11/2020 | 27/11/2020 | 0 | TK_Complete | 1112893334 | 320 | 1112893334_320
C730D157BC###0021931 | TT_Task | CBTC/Stage-3 SMCSW - Waterloo Circuit Book - Cable layout | 29/03/2021 | 02/04/2021 | 29/03/2021 | 07/04/2021 | 0 | TK_Complete | 1112893334 | 320 | 1112893334_320
C730D157BC###0021961 | TT_Task | CBTC/Stage-3 SMCSW - Sydenham Circuit Book - Cable layout | 29/03/2021 | 02/04/2021 | 22/03/2021 | 21/05/2021 | 0 | TK_Complete | 1112893334 | 320 | 1112893334_320
C730D157BC###0022003 | TT_Task | CBTC/Stage-3 SMCSW - Chartswood Circuit Book - Cable layout | 29/03/2021 | 02/04/2021 | 22/03/2021 | 26/04/2021 | 0 | TK_Complete | 1112893334 | 320 | 1112893334_320
C730D157BC###0022021 | TT_Task | CBTC/Stage-3 SMCSW - Crowsnest Circuit Book - Cable layout | 05/04/2021 | 09/04/2021 | 29/03/2021 | 06/04/2021 | 0 | TK_Complete | 1112893334 | 320 | 1112893334_320
C730D157BC###0022045 | TT_Task | CBTC/Stage-3 SMCSW - Victoria Cross Circuit Book - Cable layout | 05/04/2021 | 09/04/2021 | 29/03/2021 | 03/04/2021 | 0 | TK_Complete | 1112893334 | 320 | 1112893334_320
C730D157BC###0022051 | TT_Task | CBTC/Stage-3 SMCSW - Barangaroo Circuit Book - Cable layout | 05/04/2021 | 09/04/2021 | 29/03/2021 | 23/04/2021 | 0 | TK_Complete | 1112893334 | 320 | 1112893334_320
C730D157BC###0022069 | TT_Task | CBTC/Stage-3 SMCSW - Martin Place Circuit Book - Cable layout | 05/04/2021 | 09/04/2021 | 29/03/2021 | 31/03/2021 | 0 | TK_Complete | 1112893334 | 320 | 1112893334_320
C730D157BC###0022087 | TT_Task | CBTC/Stage-3 SMCSW - Pitt Street Circuit Book - Cable layout | 05/04/2021 | 09/04/2021 | 29/03/2021 | 07/04/2021 | 0 | TK_Complete | 1112893334 | 320 | 1112893334_320
C730D157BC###0022111 | TT_Task | CBTC/Stage-3 SMCSW - Central Circuit Book - Cable layout | 05/04/2021 | 09/04/2021 | 29/03/2021 | 21/04/2021 | 0 | TK_Complete | 1112893334 | 320 | 1112893334_320
C730D157BC###0022117 | TT_Task | CBTC/Stage-3 SMCSW - SMTF[S] - Depot Circuit Book - Cable layout | 28/04/2021 | 25/05/2021 | 01/04/2021 | 21/05/2021 | 0 | TK_Complete | 1112893334 | 320 | 1112893334_320
C730D156BC###0081808 | TT_Task | CBTC/As-Built SMCSW - Chartswood Circuit Book - Cable layout | 28/02/2023 | 21/03/2023 | nan | nan | 0 | TK_NotStart | 1112893334 | 320 | 1112893334_320
C730D156BC###0081811 | TT_Task | CBTC/As-Built SMCSW - Waterloo Circuit Book - Cable layout | 28/02/2023 | 21/03/2023 | nan | nan | 0 | TK_NotStart | 1112893334 | 320 | 1112893334_320
C730D156BC###0081814 | TT_Task | CBTC/As-Built SMCSW - Crowsnest Circuit Book - Cable layout | 21/03/2023 | 11/04/2023 | nan | nan | 0 | TK_NotStart | 1112893334 | 320 | 1112893334_320
C730D156BC###0081817 | TT_Task | CBTC/As-Built SMCSW - Sydenham Circuit Book - Cable layout | 07/02/2023 | 28/02/2023 | nan | nan | 0 | TK_NotStart | 1112893334 | 320 | 1112893334_320
C730D156BC###0081823 | TT_Task | CBTC/As-Built SMCSW - Central Circuit Book - Cable layout | 21/03/2023 | 11/04/2023 | nan | nan | 0 | TK_NotStart | 1112893334 | 320 | 1112893334_320
C730D156BC###0081829 | TT_Task | CBTC/As-Built SMCSW - Barangaroo Circuit Book - Cable layout | 11/04/2023 | 02/05/2023 | nan | nan | 0 | TK_NotStart | 1112893334 | 320 | 1112893334_320
C730D156BC###0081835 | TT_Task | CBTC/As-Built SMCSW - Martin Place Circuit Book - Cable layout | 11/04/2023 | 02/05/2023 | nan | nan | 0 | TK_NotStart | 1112893334 | 320 | 1112893334_320
C730D156BC###0081838 | TT_Task | CBTC/As-Built SMCSW - Pitt Street Circuit Book - Cable layout | 02/05/2023 | 23/05/2023 | nan | nan | 0 | TK_NotStart | 1112893334 | 320 | 1112893334_320
C730D156BC###0081853 | TT_Task | CBTC/As-Built SMCSW - Victoria Cross Circuit Book - Cable layout | 02/05/2023 | 23/05/2023 | nan | nan | 0 | TK_NotStart | 1112893334 | 320 | 1112893334_320
C730D156BC###0081862 | TT_Task | CBTC/As-Built SMCSW - SMTF[S] - Depot Circuit Book - Cable layout | 23/05/2023 | 13/06/2023 | nan | nan | 0 | TK_NotStart | 1112893334 | 320 | 1112893334_320
C720D147CF###0020300 | TT_Task | Trains/Stage-3 - CBS installations release - Batch 1 | 10/09/2020 | 08/10/2020 | 27/07/2020 | 24/08/2020 | 0 | TK_Complete | 1112893334 | 32 | 1112893334_32
C720D147CF###0020990 | TT_Task | Trains/Stage-3 - CBS installations release - Batch 2 | 09/10/2020 | 05/11/2020 | 24/08/2020 | 14/09/2020 | 0 | TK_Complete | 1112893334 | 32 | 1112893334_32
C720D147CF###0021000 | TT_Task | Trains/Stage-3 - CBS installations release - Batch 3 | 28/09/2020 | 26/10/2020 | 15/09/2020 | 09/11/2020 | 0 | TK_Complete | 1112893334 | 32 | 1112893334_32
C730D157BC###0087231 | TT_Task | CBTC/Stage-2 SMCSW - Chatswood Circuit Book - SER Drawings - **N/A | 27/05/2020 | 16/06/2020 | 25/05/2020 | 25/05/2020 | 0 | TK_Complete | 1112893334 | 319 | 1112893334_319
C730D157BC###0087322 | TT_Task | CBTC/Stage-2 SMCSW - Sydenham Circuit Book - SER Drawings - **N/A | 27/05/2020 | 16/06/2020 | 25/05/2020 | 25/05/2020 | 0 | TK_Complete | 1112893334 | 319 | 1112893334_319
C730D157BC###0087350 | TT_Task | CBTC/Stage-2 SMCSW - Barangaroo Circuit Book - SER Drawings - **N/A | 17/06/2020 | 07/07/2020 | 25/05/2020 | 25/05/2020 | 0 | TK_Complete | 1112893334 | 319 | 1112893334_319
C730D157BC###0087392 | TT_Task | CBTC/Stage-2 SMCSW - Central Circuit Book - SER Drawings - **N/A | 17/06/2020 | 14/07/2020 | 25/05/2020 | 25/05/2020 | 0 | TK_Complete | 1112893334 | 319 | 1112893334_319
C730D157BC###0087420 | TT_Task | CBTC/Stage-2 SMCSW - Pitt Street Circuit Book - SER Drawings - **N/A | 08/07/2020 | 28/07/2020 | 25/05/2020 | 25/05/2020 | 0 | TK_Complete | 1112893334 | 319 | 1112893334_319
C730D157BC###0087462 | TT_Task | CBTC/Stage-2 SMCSW - Martin Place Circuit Book - SER Drawings - **N/A | 15/07/2020 | 04/08/2020 | 25/05/2020 | 25/05/2020 | 0 | TK_Complete | 1112893334 | 319 | 1112893334_319
C730D157BC###0087469 | TT_Task | CBTC/Stage-2 SMCSW - Waterloo Circuit Book - SER Drawings - **N/A | 29/07/2020 | 18/08/2020 | 25/05/2020 | 25/05/2020 | 0 | TK_Complete | 1112893334 | 319 | 1112893334_319
C730D157BC###0087539 | TT_Task | CBTC/Stage-2 SMCSW - Crowsnest Circuit Book - SER Drawings - **N/A | 05/08/2020 | 25/08/2020 | 25/05/2020 | 25/05/2020 | 0 | TK_Complete | 1112893334 | 319 | 1112893334_319
C730D157BC###0087546 | TT_Task | CBTC/Stage-2 SMCSW - Victoria Cross Circuit Book - SER Drawings - **N/A | 19/08/2020 | 08/09/2020 | 25/05/2020 | 25/05/2020 | 0 | TK_Complete | 1112893334 | 319 | 1112893334_319
C730D157BC###0021937 | TT_Task | CBTC/Stage-3 SMCSW - Chatswood Circuit Book - SER Drawings | 29/03/2021 | 09/04/2021 | 22/03/2021 | 28/04/2021 | 0 | TK_Complete | 1112893334 | 319 | 1112893334_319
C730D157BC###0021943 | TT_Task | CBTC/Stage-3 SMCSW - Sydenham Circuit Book - SER Drawings | 29/03/2021 | 09/04/2021 | 22/03/2021 | 21/05/2021 | 0 | TK_Complete | 1112893334 | 319 | 1112893334_319
C730D157BC###0021997 | TT_Task | CBTC/Stage-3 SMCSW - Barangaroo Circuit Book - SER Drawings | 05/05/2021 | 18/05/2021 | 05/04/2021 | 23/04/2021 | 0 | TK_Complete | 1112893334 | 319 | 1112893334_319
C730D157BC###0022009 | TT_Task | CBTC/Stage-3 SMCSW - Central Circuit Book - SER Drawings | 29/03/2021 | 09/04/2021 | 22/03/2021 | 21/04/2021 | 0 | TK_Complete | 1112893334 | 319 | 1112893334_319
C730D157BC###0022039 | TT_Task | CBTC/Stage-3 SMCSW - Martin Place Circuit Book - SER Drawings | 05/05/2021 | 18/05/2021 | 26/03/2021 | 09/04/2021 | 0 | TK_Complete | 1112893334 | 319 | 1112893334_319
C730D157BC###0022081 | TT_Task | CBTC/Stage-3 SMCSW - Pitt Street Circuit Book - SER Drawings | 05/05/2021 | 18/05/2021 | 30/03/2021 | 07/04/2021 | 0 | TK_Complete | 1112893334 | 319 | 1112893334_319
C730D157BC###0022123 | TT_Task | CBTC/Stage-3 SMCSW - Crowsnest Circuit Book - SER Drawings | 05/05/2021 | 18/05/2021 | 05/04/2021 | 06/04/2021 | 0 | TK_Complete | 1112893334 | 319 | 1112893334_319
C730D157BC###0022129 | TT_Task | CBTC/Stage-3 SMCSW - Waterloo Circuit Book - SER Drawings | 05/05/2021 | 18/05/2021 | 30/03/2021 | 07/04/2021 | 0 | TK_Complete | 1112893334 | 319 | 1112893334_319
C730D157BC###0022165 | TT_Task | CBTC/Stage-3 SMCSW - Victoria Cross Circuit Book - SER Drawings | 05/05/2021 | 18/05/2021 | 29/03/2021 | 07/04/2021 | 0 | TK_Complete | 1112893334 | 319 | 1112893334_319
C730D156BC###0081832 | TT_Task | CBTC/As-Built SMCSW - Sydenham Circuit Book - SER Drawings | 28/02/2023 | 21/03/2023 | nan | nan | 600 | TK_NotStart | 1112893334 | 319 | 1112893334_319
C730D156BC###0081883 | TT_Task | CBTC/As-Built SMCSW - Barangaroo Circuit Book - SER Drawings | 02/05/2023 | 23/05/2023 | nan | nan | 240 | TK_NotStart | 1112893334 | 319 | 1112893334_319
C730D156BC###0081910 | TT_Task | CBTC/As-Built SMCSW - Pitt Street Circuit Book - SER Drawings | 23/05/2023 | 13/06/2023 | nan | nan | 120 | TK_NotStart | 1112893334 | 319 | 1112893334_319
C730D156BC###0081916 | TT_Task | CBTC/As-Built SMCSW - Victoria Cross Circuit Book - SER Drawings | 23/05/2023 | 13/06/2023 | nan | nan | 0 | TK_NotStart | 1112893334 | 319 | 1112893334_319
C730D157BC###0087175 | TT_Task | CBTC/Stage-2 SMCSW - Point Position Indicator ; Route Indicator Specification | 11/05/2020 | 22/05/2020 | 04/12/2019 | 17/02/2020 | 0 | TK_Complete | 1112893334 | 318 | 1112893334_318
C730D157BC###0021769 | TT_Task | CBTC/Stage-3 SMCSW - Point Position Indicator ; Route Indicator Specification | 06/11/2020 | 19/11/2020 | 28/07/2020 | 14/08/2020 | 0 | TK_Complete | 1112893334 | 318 | 1112893334_318
C730D157BC###0087168 | TT_Task | CBTC/Stage-2 SMCSW - CBI Product Data Sheet | 11/05/2020 | 22/05/2020 | 01/01/2020 | 12/02/2020 | 0 | TK_Complete | 1112893334 | 317 | 1112893334_317
C730D157BC###0087315 | TT_Task | CBTC/Stage-2 SMCSW - CBI Equipment List | 29/06/2020 | 03/07/2020 | 27/04/2020 | 30/04/2020 | 0 | TK_Complete | 1112893334 | 317 | 1112893334_317
C730D157BC###0021883 | TT_Task | CBTC/Stage-3 SMCSW - CBI Equipment List | 15/08/2022 | 26/08/2022 | nan | nan | 32 | TK_NotStart | 1112893334 | 317 | 1112893334_317
C730D157BC###0022105 | TT_Task | CBTC/Stage-3 SMCSW - CBI Control Tables | 27/06/2022 | 22/07/2022 | nan | nan | 232 | TK_NotStart | 1112893334 | 317 | 1112893334_317
C730D157BC###0021799 | TT_Task | CBTC/Stage-3 SMCSW - CBI Product Data Sheet [Updated] | 07/12/2020 | 11/12/2020 | 06/07/2020 | 21/07/2020 | 0 | TK_Complete | 1112893334 | 317 | 1112893334_317
C730D157BC###0087049 | TT_Task | CBTC/Stage-2 SMCSW - CBI Typical Drawings | 27/04/2020 | 22/05/2020 | 22/04/2020 | 22/04/2020 | 0 | TK_Complete | 1112893334 | 316 | 1112893334_316
C730D157BC###0087483 | TT_Task | CBTC/Stage-2 SMCSW - DCS Drawings - Victoria Cross - Barangaroo | 10/06/2020 | 16/06/2020 | 12/05/2020 | 02/06/2020 | 0 | TK_Complete | 1112893334 | 316 | 1112893334_316
C730D157BC###0087504 | TT_Task | CBTC/Stage-2 SMCSW - DCS Drawings - Barangaroo - Martin Place | 03/06/2020 | 09/06/2020 | 19/05/2020 | 02/06/2020 | 0 | TK_Complete | 1112893334 | 316 | 1112893334_316
C730D157BC###0087532 | TT_Task | CBTC/Stage-2 SMCSW - DCS Drawings - Martin Place - Pitt Street | 03/06/2020 | 09/06/2020 | 20/05/2020 | 02/06/2020 | 0 | TK_Complete | 1112893334 | 316 | 1112893334_316
C730D157BC###0087588 | TT_Task | CBTC/Stage-2 SMCSW - DCS Drawings - Pitt Street - Central | 03/06/2020 | 09/06/2020 | 20/05/2020 | 02/06/2020 | 0 | TK_Complete | 1112893334 | 316 | 1112893334_316
C730D157BC###0087602 | TT_Task | CBTC/Stage-2 SMCSW - DCS Drawings - Central - Waterloo | 01/07/2020 | 07/07/2020 | 28/05/2020 | 03/06/2020 | 0 | TK_Complete | 1112893334 | 316 | 1112893334_316
C730D157BC###0087609 | TT_Task | CBTC/Stage-2 SMCSW - DCS Drawings - Waterloo - Sydenham | 08/07/2020 | 14/07/2020 | 28/05/2020 | 03/06/2020 | 0 | TK_Complete | 1112893334 | 316 | 1112893334_316
C730D157BC###0022177 | TT_Task | CBTC/Stage-3 SMCSW - DCS BTN Cubicle Drawings | 18/07/2022 | 26/08/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 316 | 1112893334_316
C730D157BC###0071715 | TT_Task | CBTC/Stage-3 SMCSW - DCS Drawings - Victoria Cross - Barangaroo | 01/02/2021 | 12/02/2021 | 01/02/2021 | 19/02/2021 | 0 | TK_Complete | 1112893334 | 316 | 1112893334_316
C730D157BC###0071721 | TT_Task | CBTC/Stage-3 SMCSW - DCS Drawings - Barangaroo - Martin Place | 05/02/2021 | 18/02/2021 | 05/02/2021 | 19/02/2021 | 0 | TK_Complete | 1112893334 | 316 | 1112893334_316
C730D157BC###0071727 | TT_Task | CBTC/Stage-3 SMCSW - DCS Drawings - Martin Place - Pitt Street | 15/07/2021 | 28/07/2021 | 05/02/2021 | 19/02/2021 | 0 | TK_Complete | 1112893334 | 316 | 1112893334_316
C730D157BC###0071733 | TT_Task | CBTC/Stage-3 SMCSW - DCS Drawings - Pitt Street - Central | 29/07/2021 | 11/08/2021 | 08/02/2021 | 24/02/2021 | 0 | TK_Complete | 1112893334 | 316 | 1112893334_316
C730D157BC###0071739 | TT_Task | CBTC/Stage-3 SMCSW - DCS Drawings - Central - Waterloo | 12/08/2021 | 25/08/2021 | 15/02/2021 | 05/03/2021 | 0 | TK_Complete | 1112893334 | 316 | 1112893334_316
C730D157BC###0071745 | TT_Task | CBTC/Stage-3 SMCSW - DCS Drawings - Waterloo - Sydenham | 26/08/2021 | 08/09/2021 | 15/02/2021 | 05/03/2021 | 0 | TK_Complete | 1112893334 | 316 | 1112893334_316
C730D157BC###0031946 | TT_Task | CBTC/Stage-3 SMCSW - CBI SER Drawings Customer Review and Comments | 25/10/2021 | 26/11/2021 | 12/04/2021 | 19/07/2021 | 0 | TK_Complete | 1112893334 | 316 | 1112893334_316
C730D157BC###0087007 | TT_Task | CBTC/Stage-2 SMCSW - CBI Wayside Equipment SMIO Interface Document (SyID) (A8 Milestone) | 23/10/2019 | 29/10/2019 | 01/08/2019 | 10/09/2019 | 0 | TK_Complete | 1112893334 | 315 | 1112893334_315
C730D157BC###0087434 | TT_Task | CBTC/Stage-2 SMCSW - DCS SyID | 27/07/2020 | 31/07/2020 | 04/05/2020 | 26/06/2020 | 0 | TK_Complete | 1112893334 | 315 | 1112893334_315
C730D157BC###0021727 | TT_Task | CBTC/Stage-3 SMCSW - CBI Wayside Equipment SMIO Interface Document (SyID) [Updated] | 23/11/2020 | 27/11/2020 | 10/08/2020 | 19/08/2020 | 0 | TK_Complete | 1112893334 | 315 | 1112893334_315
C730D157BC###0021817 | TT_Task | CBTC/Stage-3 SMCSW - DCS SyID (Inetrnal) | 25/10/2021 | 25/11/2021 | 01/07/2020 | 30/07/2020 | 0 | TK_Complete | 1112893334 | 315 | 1112893334_315
C730D147BC###0010864 | TT_Task | CBTC/Stage-2 SMCSW - RS-ATS Interface Specification | 24/08/2020 | 04/09/2020 | 04/12/2019 | 17/12/2019 | 0 | TK_Complete | 1112893334 | 314 | 1112893334_314
C730D157BC###0087126 | TT_Task | CBTC/Stage-2 SMCSW - MSS-ATS Interface Specification | 04/05/2020 | 29/05/2020 | 12/02/2020 | 06/03/2020 | 0 | TK_Complete | 1112893334 | 314 | 1112893334_314
C730D167BC###0037024 | TT_Task | CBTC/Stage-2 SMCSW - ATS-UPS/PDC Detailed Interface Specification | 25/06/2020 | 05/08/2020 | 25/05/2020 | 30/06/2020 | 0 | TK_Complete | 1112893334 | 314 | 1112893334_314
C730D157BC###0021877 | TT_Task | CBTC/Stage-3 SMCSW - RS-ATS Interface Specification | 26/04/2021 | 04/06/2021 | 20/04/2021 | nan | 0 | TK_Active | 1112893334 | 314 | 1112893334_314
C730D157BC###0021985 | TT_Task | CBTC/Stage-3 SMCSW - MSS-ATS Interface Specification | 04/02/2021 | 31/03/2021 | 26/08/2020 | 05/11/2020 | 0 | TK_Complete | 1112893334 | 314 | 1112893334_314
C730D147BC###0010816 | TT_Task | CBTC/Stage-2 SMCSW - ATC Sub-system Requirements Specification and Architecture Description | 13/04/2020 | 24/04/2020 | 09/01/2020 | 13/04/2020 | 0 | TK_Complete | 1112893334 | 313 | 1112893334_313
C730D157BC###0087035 | TT_Task | CBTC/Stage-2 SMCSW - CBI System Requirements Specification and Architecture Description | 27/04/2020 | 22/05/2020 | 01/04/2020 | 13/04/2020 | 0 | TK_Complete | 1112893334 | 313 | 1112893334_313
C730D157BC###0087028 | TT_Task | CBTC/Stage-2 SMCSW - MSS Sub-system Requirements Specification and Architecture Description | 13/04/2020 | 01/05/2020 | 03/02/2020 | 28/02/2020 | 0 | TK_Complete | 1112893334 | 313 | 1112893334_313
C730D157BC###0087091 | TT_Task | CBTC/Stage-2 SMCSW - MSS Hardware specification | 27/04/2020 | 29/05/2020 | 22/04/2020 | 22/04/2020 | 0 | TK_Complete | 1112893334 | 313 | 1112893334_313
C730D157BC###0087042 | TT_Task | CBTC/Stage-2 SMCSW - DCS Sub-system Requirements Specification and Architecture Description | 12/05/2020 | 01/06/2020 | 17/03/2020 | 13/04/2020 | 0 | TK_Complete | 1112893334 | 313 | 1112893334_313
C730D157BC###0036250 | TT_Task | CBTC/Stage-2 SMCSW - ATS Requirements Specification and Architecture Description | 25/05/2020 | 12/06/2020 | 18/05/2020 | 26/06/2020 | 0 | TK_Complete | 1112893334 | 313 | 1112893334_313
C730D157BC###0021709 | TT_Task | CBTC/Stage-3 SMCSW - ATC Sub-system Requirements Specification and Architecture Description | 26/10/2020 | 25/12/2020 | 14/09/2020 | 04/12/2020 | 0 | TK_Complete | 1112893334 | 313 | 1112893334_313
C730D157BC###0021715 | TT_Task | CBTC/Stage-3 SMCSW - CBI System Requirements Specification and Architecture Description | 28/09/2020 | 02/10/2020 | 21/09/2020 | 25/09/2020 | 0 | TK_Complete | 1112893334 | 313 | 1112893334_313
C730D157BC###0021793 | TT_Task | CBTC/Stage-3 SMCSW - MSS Sub-system Requirements Specification and Architecture Description | 16/11/2020 | 27/11/2020 | 11/08/2020 | 21/04/2021 | 0 | TK_Complete | 1112893334 | 313 | 1112893334_313
C730D157BC###0021721 | TT_Task | CBTC/Stage-3 SMCSW - DCS Sub-system Requirements Specification and Architecture Description | 25/03/2021 | 07/04/2021 | 08/03/2021 | 23/03/2021 | 0 | TK_Complete | 1112893334 | 313 | 1112893334_313
C730D157BC###0038580 | TT_Task | CBTC/Stage-3 SMCSW - ATS Requirements Specification and Architecture Description | 03/02/2021 | 17/02/2021 | 16/11/2020 | 26/11/2020 | 0 | TK_Complete | 1112893334 | 313 | 1112893334_313
C730D147BC###0010802 | TT_Task | CBTC/Stage-2 SMCSW - SIG-RS Detailed Interface Specification | 27/04/2020 | 08/05/2020 | 04/12/2019 | 17/12/2019 | 0 | TK_Complete | 1112893334 | 312 | 1112893334_312
C730D157BC###0087133 | TT_Task | CBTC/Stage-2 SMCSW - MSS-CBI Interface Description | 04/05/2020 | 29/05/2020 | 12/02/2020 | 28/02/2020 | 0 | TK_Complete | 1112893334 | 312 | 1112893334_312
C730D157BC###0087147 | TT_Task | CBTC/Stage-2 SMCSW - MSS-LC Interface Specification | 04/05/2020 | 29/05/2020 | 14/02/2020 | 28/02/2020 | 0 | TK_Complete | 1112893334 | 312 | 1112893334_312
C730D157BC###0087154 | TT_Task | CBTC/Stage-2 SMCSW - MSS-ZC Interface Specification | 04/05/2020 | 29/05/2020 | 14/02/2020 | 28/02/2020 | 0 | TK_Complete | 1112893334 | 312 | 1112893334_312
C730D157BC###0087161 | TT_Task | CBTC/Stage-2 SMCSW - MSS-CC Interface Specification | 04/05/2020 | 29/05/2020 | 14/02/2020 | 28/02/2020 | 0 | TK_Complete | 1112893334 | 312 | 1112893334_312
C730D157BC###0021865 | TT_Task | CBTC/Stage-3 SMCSW - SIG-RS Detailed Interface Specification | 26/04/2021 | 07/05/2021 | 01/02/2021 | 18/02/2021 | 0 | TK_Complete | 1112893334 | 312 | 1112893334_312
C730D157BC###0021841 | TT_Task | CBTC/Stage-3 SMCSW - MSS-CC Interface Specification | 17/12/2020 | 03/02/2021 | 26/08/2020 | 04/12/2020 | 0 | TK_Complete | 1112893334 | 312 | 1112893334_312
C730D157BC###0021991 | TT_Task | CBTC/Stage-3 SMCSW - MSS-LC Interface Specification | 04/02/2021 | 31/03/2021 | 26/08/2020 | 14/09/2020 | 0 | TK_Complete | 1112893334 | 312 | 1112893334_312
C730D157BC###0022135 | TT_Task | CBTC/Stage-3 SMCSW - MSS-CBI Interface Description | 01/04/2021 | 19/05/2021 | 26/08/2020 | 10/12/2020 | 0 | TK_Complete | 1112893334 | 312 | 1112893334_312
C730D157BC###0022141 | TT_Task | CBTC/Stage-3 SMCSW - MSS-ZC Interface Specification | 01/04/2021 | 19/05/2021 | 03/08/2020 | 18/08/2020 | 0 | TK_Complete | 1112893334 | 312 | 1112893334_312
C730D157BC###N902453 | TT_Task | CBTC/Stage-3 SMCSW - SRS Detailed Interface Specification (DIS) | 31/10/2019 | 20/11/2019 | 01/10/2020 | 16/10/2020 | 0 | TK_Complete | 1112893334 | 312 | 1112893334_312
C730D147BC###0010766 | TT_Task | CBTC/Stage-2 SMCSW - ATC Trackside Products Manuals and Maintenance book (A8 Milestone) | 01/07/2019 | 05/09/2019 | 01/07/2019 | 10/09/2019 | 0 | TK_Complete | 1112893334 | 311 | 1112893334_311
C730D147BC###0010768 | TT_Task | CBTC/Stage-2 SMCSW - ATC On-board Products Manuals and Maintenance book (A8 Milestone) | 01/07/2019 | 05/09/2019 | 01/07/2019 | 10/09/2019 | 0 | TK_Complete | 1112893334 | 311 | 1112893334_311
C730D157BC###0087000 | TT_Task | CBTC/Stage-2 SMCSW - CBI Products Manuals and Maintenance book (A8 Milestone) | 01/07/2019 | 05/09/2019 | 01/07/2019 | 10/09/2019 | 0 | TK_Complete | 1112893334 | 311 | 1112893334_311
C730D157BC###0036680 | TT_Task | CBTC/Stage-2 SMCSW - ATS Products Manuals and Maintenance book | 15/06/2020 | 17/07/2020 | 13/05/2020 | 04/06/2020 | 0 | TK_Complete | 1112893334 | 311 | 1112893334_311
C730D157BC###0021703 | TT_Task | CBTC/Stage-3 SMCSW - ATC On-board Products Manuals and Maintenance book | 26/10/2020 | 20/11/2020 | 01/10/2020 | 04/12/2020 | 0 | TK_Complete | 1112893334 | 311 | 1112893334_311
C730D157BC###0021925 | TT_Task | CBTC/Stage-3 SMCSW - ATC Trackside Products Manuals and Maintenance book | 28/12/2020 | 22/01/2021 | 01/10/2020 | 14/12/2020 | 0 | TK_Complete | 1112893334 | 311 | 1112893334_311
C730D157BC###0021739 | TT_Task | CBTC/Stage-3 SMCSW - CBI Products Manuals and Maintenance book [Updated] | 26/10/2020 | 06/11/2020 | 23/10/2020 | 17/12/2020 | 0 | TK_Complete | 1112893334 | 311 | 1112893334_311
C730D157BC###0038930 | TT_Task | CBTC/Stage-3 SMCSW - ATS Products Manuals and Maintenance book | 26/10/2020 | 04/12/2020 | 16/11/2020 | 17/12/2020 | 0 | TK_Complete | 1112893334 | 311 | 1112893334_311
C730D147BC###0010764 | TT_Task | CBTC/Stage-2 SMCSW - Driver Manual (A8 Milestone) | 01/07/2019 | 05/09/2019 | 01/07/2019 | 10/09/2019 | 0 | TK_Complete | 1112893334 | 310 | 1112893334_310
C730D157BC###0036700 | TT_Task | CBTC/Stage-2 SMCSW - ATS Operator Manual | 01/06/2020 | 03/07/2020 | 18/05/2020 | 02/06/2020 | 0 | TK_Complete | 1112893334 | 310 | 1112893334_310
C730D157BC###0036710 | TT_Task | CBTC/Stage-2 SMCSW - ATS Simulator Manual | 01/06/2020 | 03/07/2020 | 18/05/2020 | 04/06/2020 | 0 | TK_Complete | 1112893334 | 310 | 1112893334_310
C730D157BC###0036840 | TT_Task | CBTC/Stage-2 SMCSW - ATS Function List | 01/06/2020 | 03/07/2020 | 18/05/2020 | 08/06/2020 | 0 | TK_Complete | 1112893334 | 310 | 1112893334_310
C730D157BC###0021859 | TT_Task | CBTC/Stage-3 SMCSW - Driver Manual | 11/01/2021 | 05/02/2021 | 10/08/2020 | 28/08/2020 | 0 | TK_Complete | 1112893334 | 310 | 1112893334_310
C730D157BC###0038950 | TT_Task | CBTC/Stage-3 SMCSW - ATS Operator Manual | 07/12/2020 | 15/01/2021 | 09/11/2020 | 15/12/2020 | 0 | TK_Complete | 1112893334 | 310 | 1112893334_310
C730D157BC###0038960 | TT_Task | CBTC/Stage-3 SMCSW - ATS Simulator Manual | 25/11/2020 | 05/01/2021 | 26/11/2020 | 15/12/2020 | 0 | TK_Complete | 1112893334 | 310 | 1112893334_310
C730D157BC###0039090 | TT_Task | CBTC/Stage-3 SMCSW - ATS Function List | 25/11/2020 | 22/12/2020 | 26/11/2020 | 15/12/2020 | 0 | TK_Complete | 1112893334 | 310 | 1112893334_310
C720D147CF###0087000 | TT_Task | Trains/Stage-3 - Design Lot 7202 resubmission (final) | 25/08/2020 | 09/09/2020 | 05/06/2020 | 24/07/2020 | 0 | TK_Complete | 1112893334 | 31 | 1112893334_31
C720D147CF###0087005 | TT_Task | Trains/Stage-3 - Design Lot 7204 resubmission (final) | 25/02/2021 | 12/03/2021 | 08/02/2021 | 14/06/2021 | 0 | TK_Complete | 1112893334 | 31 | 1112893334_31
C720D147CF###0087010 | TT_Task | Trains/Stage-3 - Design Lot 7209 resubmission (final) | 25/02/2021 | 12/03/2021 | 08/02/2021 | 14/06/2021 | 0 | TK_Complete | 1112893334 | 31 | 1112893334_31
C720D147CF###0087015 | TT_Task | Trains/Stage-3 - Design Lot 7210 resubmission (final) | 25/02/2021 | 12/03/2021 | 08/02/2021 | 24/06/2021 | 0 | TK_Complete | 1112893334 | 31 | 1112893334_31
C720D147CF###0087025 | TT_Task | Trains/Stage-3 - Design Lot 7201 resubmission (final) | 25/02/2021 | 12/03/2021 | 08/02/2021 | 10/07/2021 | 0 | TK_Complete | 1112893334 | 31 | 1112893334_31
C720D147CF###0087030 | TT_Task | Trains/Stage-3 - Design Lot 7206 resubmission (final) | 25/02/2021 | 12/03/2021 | 08/02/2021 | 13/07/2021 | 0 | TK_Complete | 1112893334 | 31 | 1112893334_31
C720D147CF###0087035 | TT_Task | Trains/Stage-3 - Design Lot 7207 resubmission (final) | 25/02/2021 | 12/03/2021 | 08/02/2021 | 21/06/2021 | 0 | TK_Complete | 1112893334 | 31 | 1112893334_31
C720D147CF###0087040 | TT_Task | Trains/Stage-3 - Design Lot 7205 resubmission (final) | 25/02/2021 | 12/03/2021 | 08/02/2021 | 16/06/2021 | 0 | TK_Complete | 1112893334 | 31 | 1112893334_31
C720D147CF###0087020 | TT_Task | Trains/Stage-3 - Design Lot 7208 resubmission (final) ***N/A*** | 25/02/2021 | 12/03/2021 | 08/02/2021 | 08/02/2021 | 0 | TK_Complete | 1112893334 | 31 | 1112893334_31
C730D147BC###0010760 | TT_Task | CBTC/Stage-2 SMCSW - ATC TrackSide Product Data Sheet (A8 Milestone) | 01/07/2019 | 05/09/2019 | 01/07/2019 | 10/09/2019 | 0 | TK_Complete | 1112893334 | 309 | 1112893334_309
C730D147BC###0010762 | TT_Task | CBTC/Stage-2 SMCSW - ATC Onboard Product Data Sheet (A8 Milestone) | 01/07/2019 | 05/09/2019 | 01/07/2019 | 10/09/2019 | 0 | TK_Complete | 1112893334 | 309 | 1112893334_309
C730D157BC###0021871 | TT_Task | CBTC/Stage-3 SMCSW - ATC TrackSide Product Data Sheet | 25/02/2021 | 10/03/2021 | 04/12/2020 | 21/12/2020 | 0 | TK_Complete | 1112893334 | 309 | 1112893334_309
C730D157BC###0021913 | TT_Task | CBTC/Stage-3 SMCSW - ATC Onboard Product Data Sheet | 11/03/2021 | 24/03/2021 | 22/12/2020 | 29/12/2020 | 0 | TK_Complete | 1112893334 | 309 | 1112893334_309
C730D147BC###0010880 | TT_Task | CBTC/Stage-2 SMCSW - RVT (Requirement Validation Table) | 09/11/2020 | 04/12/2020 | 17/03/2020 | 02/04/2020 | 0 | TK_Complete | 1112893334 | 308 | 1112893334_308
C730D157BC###0022333 | TT_Task | CBTC/Stage-3 SMCSW - RVT (Requirement Validation Table) | 30/09/2021 | 13/10/2021 | 01/03/2021 | 29/04/2021 | 0 | TK_Complete | 1112893334 | 308 | 1112893334_308
C730D157BC###N879453 | TT_Task | CBTC/Stage-3 SMCSW - RVT (Requirement Validation Table) Pre Final | 25/02/2021 | 17/03/2021 | 24/02/2021 | 29/04/2021 | 0 | TK_Complete | 1112893334 | 308 | 1112893334_308
C730D147BC###0010856 | TT_Task | CBTC/Stage-2 SMCSW - System Baseline Delivery Sheet | 25/05/2020 | 29/05/2020 | 19/05/2020 | 30/06/2020 | 0 | TK_Complete | 1112893334 | 307 | 1112893334_307
C730D147BC###0010872 | TT_Task | CBTC/Stage-2 SMCSW - ATC Baseline Delivery Sheet | 17/08/2020 | 21/08/2020 | 20/07/2020 | 28/08/2020 | 0 | TK_Complete | 1112893334 | 307 | 1112893334_307
C730D157BC###0087476 | TT_Task | CBTC/Stage-2 SMCSW - MSS Baseline Delivery Sheet | 27/07/2020 | 14/08/2020 | 27/07/2020 | 28/08/2020 | 0 | TK_Complete | 1112893334 | 307 | 1112893334_307
C730D157BC###0087574 | TT_Task | CBTC/Stage-2 SMCSW - DCS Baseline Delivery Sheet | 27/07/2020 | 31/07/2020 | 13/07/2020 | 28/08/2020 | 0 | TK_Complete | 1112893334 | 307 | 1112893334_307
C730D157BC###0022261 | TT_Task | CBTC/Stage-3 SMCSW - ATC Baseline Delivery Sheet | 05/09/2022 | 09/09/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 307 | 1112893334_307
C730D157BC###0022273 | TT_Task | CBTC/Stage-3 SMCSW - MSS Baseline Delivery Sheet | 12/09/2022 | 16/09/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 307 | 1112893334_307
C730D157BC###0022315 | TT_Task | CBTC/Stage-3 SMCSW - DCS Baseline Delivery Sheet | 10/10/2022 | 14/10/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 307 | 1112893334_307
C730D147BC###0010828 | TT_Task | CBTC/Stage-2 SMCSW - SyOCD (Operational and Contexts Description) | 04/05/2020 | 26/06/2020 | 15/04/2020 | 19/05/2020 | 0 | TK_Complete | 1112893334 | 306 | 1112893334_306
C730D157BC###0027135 | TT_Task | CBTC/Stage-3 SMCSW - SyOCD (Operational and Contexts Description) | 30/10/2020 | 26/11/2020 | 03/08/2020 | 14/09/2020 | 0 | TK_Complete | 1112893334 | 306 | 1112893334_306
C730D157BC###N09463 | TT_Task | CBTC/Stage-3 SMCSW - SyOCD (Operational and Contexts Description) Review and Updated Submission | 26/04/2021 | 21/05/2021 | 06/04/2021 | 28/04/2021 | 0 | TK_Complete | 1112893334 | 306 | 1112893334_306
C730D147BC###0010812 | TT_Task | CBTC/Stage-2 SMCSW - Initial System PBS / BOQ | 27/04/2020 | 08/05/2020 | 20/04/2020 | 15/05/2020 | 0 | TK_Complete | 1112893334 | 305 | 1112893334_305
C730D147BC###0010862 | TT_Task | CBTC/Stage-2 SMCSW - System Pre-Final PBS / BOQ | 28/05/2020 | 10/06/2020 | 18/05/2020 | 30/06/2020 | 0 | TK_Complete | 1112893334 | 305 | 1112893334_305
C730D147BC###0010844 | TT_Task | CBTC/Stage-2 SMCSW - ATC PBS / BOQ | 15/06/2020 | 26/06/2020 | 13/04/2020 | 23/04/2020 | 0 | TK_Complete | 1112893334 | 305 | 1112893334_305
C730D157BC###0087259 | TT_Task | CBTC/Stage-2 SMCSW - CBI PBS / BOQ | 01/06/2020 | 12/06/2020 | 13/04/2020 | 23/04/2020 | 0 | TK_Complete | 1112893334 | 305 | 1112893334_305
C730D157BC###0087273 | TT_Task | CBTC/Stage-2 SMCSW - MSS PBS / BOQ | 01/06/2020 | 26/06/2020 | 22/04/2020 | 22/04/2020 | 0 | TK_Complete | 1112893334 | 305 | 1112893334_305
C730D157BC###0087511 | TT_Task | CBTC/Stage-2 SMCSW - DCS PBS / BOQ City and SW | 03/08/2020 | 14/08/2020 | 13/04/2020 | 23/04/2020 | 0 | TK_Complete | 1112893334 | 305 | 1112893334_305
C730D157BC###0037990 | TT_Task | CBTC/Stage-2 SMCSW - ATS PBS / BOQ | 25/06/2020 | 10/07/2020 | 15/06/2020 | 30/06/2020 | 0 | TK_Complete | 1112893334 | 305 | 1112893334_305
C730D157BC###0027381 | TT_Task | CBTC/Stage-3 SMCSW - System PBS / BOQ | 25/03/2021 | 07/04/2021 | 08/02/2021 | 11/06/2021 | 0 | TK_Complete | 1112893334 | 305 | 1112893334_305
C730D157BC###0021847 | TT_Task | CBTC/Stage-3 SMCSW - ATC PBS / BOQ | 18/03/2021 | 07/04/2021 | 08/02/2021 | 11/06/2021 | 0 | TK_Complete | 1112893334 | 305 | 1112893334_305
C730D157BC###0021919 | TT_Task | CBTC/Stage-3 SMCSW - CBI PBS / BOQ | 01/03/2021 | 05/03/2021 | 01/02/2021 | 11/06/2021 | 0 | TK_Complete | 1112893334 | 305 | 1112893334_305
C730D157BC###0021973 | TT_Task | CBTC/Stage-3 SMCSW - MSS PBS / BOQ | 18/03/2021 | 24/03/2021 | 01/02/2021 | 11/06/2021 | 0 | TK_Complete | 1112893334 | 305 | 1112893334_305
C730D157BC###0022057 | TT_Task | CBTC/Stage-3 SMCSW - DCS PBS / BOQ | 25/02/2021 | 03/03/2021 | 08/02/2021 | 11/06/2021 | 0 | TK_Complete | 1112893334 | 305 | 1112893334_305
C730D157BC###0039120 | TT_Task | CBTC/Stage-3 SMCSW - ATS PBS / BOQ | 25/02/2021 | 07/04/2021 | 01/02/2021 | 11/06/2021 | 0 | TK_Complete | 1112893334 | 305 | 1112893334_305
C730D147BC###0010804 | TT_Task | CBTC/Stage-2 SMCSW - Application Condition | 25/02/2020 | 13/04/2020 | 06/01/2020 | 30/06/2020 | 0 | TK_Complete | 1112893334 | 304 | 1112893334_304
C730D147BC###0010826 | TT_Task | CBTC/Stage-2 SMCSW - List of Standards | 25/05/2020 | 05/06/2020 | 24/02/2020 | 08/03/2020 | 0 | TK_Complete | 1112893334 | 304 | 1112893334_304
C730D147BC###0010860 | TT_Task | CBTC/Stage-2 SMCSW - Design Baseline Verification | 25/08/2020 | 14/09/2020 | 27/07/2020 | 31/07/2020 | 0 | TK_Complete | 1112893334 | 304 | 1112893334_304
C730D157BC###0027021 | TT_Task | CBTC/Stage-3 SMCSW - Application Condition | 27/07/2020 | 07/08/2020 | 01/07/2020 | nan | 0 | TK_Active | 1112893334 | 304 | 1112893334_304
C730D157BC###0022309 | TT_Task | CBTC/Stage-3 SMCSW - Application Condition Verification | 10/10/2022 | 21/10/2022 | nan | nan | 120 | TK_NotStart | 1112893334 | 304 | 1112893334_304
C730D157BC###0040070 | TT_Task | CBTC/Stage-3 SMCSW - Design Baseline Verification | 27/06/2022 | 15/07/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 304 | 1112893334_304
C730D157BC###0022027 | TT_Task | CBTC/Stage-3 SMCSW - PT CC-TCMS Specification | 01/02/2021 | 18/02/2021 | 01/02/2021 | 18/02/2021 | 0 | TK_Complete | 1112893334 | 304 | 1112893334_304
C730D157BC###0031766 | TT_Task | CBTC/Stage-3 SMCSW - Operability Design Assessment Report (for new / modified tasks) | 16/11/2020 | 25/12/2020 | 14/09/2020 | 20/11/2020 | 0 | TK_Complete | 1112893334 | 304 | 1112893334_304
C730D157BC###0031802 | TT_Task | CBTC/Stage-3 SMCSW - Operability Conceptual Design | 30/04/2021 | 11/06/2021 | 16/11/2020 | 16/12/2020 | 0 | TK_Complete | 1112893334 | 304 | 1112893334_304
C730D157BC###0031856 | TT_Task | CBTC/Stage-3 SMCSW - Operability Acceptance Plan | 09/06/2021 | 21/07/2021 | 26/11/2020 | 16/12/2020 | 0 | TK_Complete | 1112893334 | 304 | 1112893334_304
C730D157BC###0031874 | TT_Task | CBTC/Stage-3 SMCSW - Operability Results of the Assessments | 19/09/2022 | 28/10/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 304 | 1112893334_304
C730D147BC###0010790 | TT_Task | CBTC/Stage-2 SMCSW - SyRSAD Customer Comments ***Mitigation*** | 15/10/2019 | 21/10/2019 | 24/02/2020 | 24/02/2020 | 0 | TK_Complete | 1112893334 | 303 | 1112893334_303
C730D157BC###0021823 | TT_Task | CBTC/Stage-3 SMCSW - MSS Hardware specification *Cancelled software change only | 25/02/2021 | 17/03/2021 | 25/01/2021 | 25/01/2021 | 0 | TK_Complete | 1112893334 | 303 | 1112893334_303
C730D157BC###0031793 | TT_Task | CBTC/Stage-3 SMCSW - Human Factors Issues Register | 08/02/2021 | 19/03/2021 | 10/09/2020 | 15/10/2020 | 0 | TK_Complete | 1112893334 | 303 | 1112893334_303
C730D147BC###0010788 | TT_Task | CBTC/Stage-2 SMCSW - SyCR | 31/10/2019 | 20/11/2019 | 11/09/2019 | 04/05/2020 | 0 | TK_Complete | 1112893334 | 302 | 1112893334_302
C730D147BC###0010846 | TT_Task | CBTC/Stage-2 SMCSW - SyDT | 02/07/2020 | 29/07/2020 | 01/06/2020 | 31/08/2020 | 0 | TK_Complete | 1112893334 | 302 | 1112893334_302
C730D147BC###0010852 | TT_Task | CBTC/Stage-2 SMCSW - PT CC SyPRS - (*covered in Stage 3) | 24/08/2020 | 04/09/2020 | 24/04/2020 | 24/04/2020 | 0 | TK_Complete | 1112893334 | 302 | 1112893334_302
C730D157BC###0087021 | TT_Task | CBTC/Stage-2 SMCSW - CBI SyHW | 27/04/2020 | 15/05/2020 | 22/04/2020 | 22/04/2020 | 0 | TK_Complete | 1112893334 | 302 | 1112893334_302
C730D157BC###0027015 | TT_Task | CBTC/Stage-3 SMCSW - SyCR | 24/08/2020 | 11/09/2020 | 01/07/2020 | nan | 0 | TK_Active | 1112893334 | 302 | 1112893334_302
C730D157BC###0027033 | TT_Task | CBTC/Stage-3 SMCSW - SyNR | 27/07/2020 | 07/08/2020 | 27/07/2020 | 21/08/2020 | 0 | TK_Complete | 1112893334 | 302 | 1112893334_302
C730D157BC###0027357 | TT_Task | CBTC/Stage-3 SMCSW - SyDT | 16/05/2022 | 03/06/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 302 | 1112893334_302
C730D157BC###0022171 | TT_Task | CBTC/Stage-3 SMCSW - SyNR Verification | 18/07/2022 | 22/07/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 302 | 1112893334_302
C730D157BC###0021967 | TT_Task | CBTC/Stage-3 SMCSW - PT CC SyPRS | 11/04/2022 | 22/04/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 302 | 1112893334_302
C730D157BC###0021889 | TT_Task | CBTC/Stage-3 SMCSW - CBI SyHW | 08/04/2021 | 21/04/2021 | 18/01/2021 | 28/01/2021 | 0 | TK_Complete | 1112893334 | 302 | 1112893334_302
C730D147BC###0010782 | TT_Task | CBTC/Stage-2 SMCSW - Requirement Allocation Table (A8 Milestone) | 01/07/2019 | 05/09/2019 | 01/07/2019 | 10/09/2019 | 0 | TK_Complete | 1112893334 | 301 | 1112893334_301
C730D147BC###0010798 | TT_Task | CBTC/Stage-2 SMCSW - PRD (Project Requirements Database) | 25/02/2020 | 09/03/2020 | 09/12/2019 | 31/01/2020 | 0 | TK_Complete | 1112893334 | 301 | 1112893334_301
C730D147BC###0010838 | TT_Task | CBTC/Stage-2 SMCSW - Requirement Allocation Table | 18/05/2020 | 05/06/2020 | 01/04/2020 | 17/04/2020 | 0 | TK_Complete | 1112893334 | 301 | 1112893334_301
C730D157BC###0027003 | TT_Task | CBTC/Stage-3 SMCSW - PRD (Project Requirements Database) | 27/07/2020 | 14/08/2020 | 01/07/2020 | 26/01/2021 | 0 | TK_Complete | 1112893334 | 301 | 1112893334_301
C730D157BC###0022075 | TT_Task | CBTC/Stage-3 SMCSW - Requirement Allocation Table | 26/04/2021 | 14/05/2021 | 01/03/2021 | 30/03/2021 | 0 | TK_Complete | 1112893334 | 301 | 1112893334_301
C730D147BC###0010780 | TT_Task | CBTC/Stage-2 SMCSW - Customer Clarification book Template (A8 Milestone) | 01/07/2019 | 05/09/2019 | 01/07/2019 | 10/09/2019 | 0 | TK_Complete | 1112893334 | 300 | 1112893334_300
C730D147BC###0010800 | TT_Task | CBTC/Stage-2 SMCSW - Customer Clarifications Book | 27/04/2020 | 08/05/2020 | 15/04/2020 | 30/06/2020 | 0 | TK_Complete | 1112893334 | 300 | 1112893334_300
C730D157BC###0027009 | TT_Task | CBTC/Stage-3 SMCSW - Customer Clarifications Book | 26/01/2021 | 08/02/2021 | 01/07/2020 | 29/04/2021 | 0 | TK_Complete | 1112893334 | 300 | 1112893334_300
C720D147CF###0021580 | TT_Task | Trains/Stage-3 - Design Lot 7208 customer review ; approval (part 1) | 25/11/2020 | 13/01/2021 | 22/06/2020 | 30/07/2020 | 0 | TK_Complete | 1112893334 | 30 | 1112893334_30
C720D147CF###0021590 | TT_Task | Trains/Stage-3 - Design Lot 7202 customer review ; approval (part 1) | 10/03/2020 | 15/04/2020 | 29/01/2020 | 13/03/2020 | 0 | TK_Complete | 1112893334 | 30 | 1112893334_30
C720D147CF###0021600 | TT_Task | Trains/Stage-3 - Design Lot 7205 customer review ; approval (part 1) | 25/02/2020 | 30/03/2020 | 28/01/2020 | 03/03/2020 | 0 | TK_Complete | 1112893334 | 30 | 1112893334_30
C720D147CF###0021610 | TT_Task | Trains/Stage-3 - Design Lot 7206 customer review ; approval (part 1) | 10/03/2020 | 15/04/2020 | 28/01/2020 | 06/03/2020 | 0 | TK_Complete | 1112893334 | 30 | 1112893334_30
C720D147CF###0021620 | TT_Task | Trains/Stage-3 - Design Lot 7204 customer review ; approval (part 1) | 25/02/2020 | 30/03/2020 | 29/01/2020 | 26/03/2020 | 0 | TK_Complete | 1112893334 | 30 | 1112893334_30
C720D147CF###0021630 | TT_Task | Trains/Stage-3 - Design Lot 7209 customer review ; approval (part 1) | 10/03/2020 | 15/04/2020 | 29/01/2020 | 27/03/2020 | 0 | TK_Complete | 1112893334 | 30 | 1112893334_30
C720D147CF###0021640 | TT_Task | Trains/Stage-3 - Design Lot 7210 customer review ; approval (part 1) | 10/03/2020 | 15/04/2020 | 30/01/2020 | 06/03/2020 | 0 | TK_Complete | 1112893334 | 30 | 1112893334_30
C720D147CF###0021650 | TT_Task | Trains/Stage-3 - Design Lot 7201 customer review ; approval (part 1) | 10/03/2020 | 15/04/2020 | 29/01/2020 | 03/03/2020 | 0 | TK_Complete | 1112893334 | 30 | 1112893334_30
C720D147CF###0021660 | TT_Task | Trains/Stage-3 - Design Lot 7207 customer review ; approval (part 1) | 30/04/2020 | 03/06/2020 | 29/01/2020 | 19/03/2020 | 0 | TK_Complete | 1112893334 | 30 | 1112893334_30
C720D147CF###0021680 | TT_Task | Trains/Stage-3 - Design Lot 7205 customer review ; approval (part 2) | 25/05/2020 | 29/06/2020 | 27/04/2020 | 28/05/2020 | 0 | TK_Complete | 1112893334 | 30 | 1112893334_30
C720D147CF###0021690 | TT_Task | Trains/Stage-3 - Design Lot 7204 customer review ; approval (part 2) | 25/05/2020 | 29/06/2020 | 27/04/2020 | 28/05/2020 | 0 | TK_Complete | 1112893334 | 30 | 1112893334_30
C720D147CF###0021700 | TT_Task | Trains/Stage-3 - Design Lot 7209 customer review ; approval (part 2) | 18/06/2020 | 22/07/2020 | 27/04/2020 | 01/06/2020 | 0 | TK_Complete | 1112893334 | 30 | 1112893334_30
C720D147CF###0021710 | TT_Task | Trains/Stage-3 - Design Lot 7210 customer review ; approval (part 2) | 25/05/2020 | 29/06/2020 | 22/04/2020 | 27/05/2020 | 0 | TK_Complete | 1112893334 | 30 | 1112893334_30
C720D147CF###0021720 | TT_Task | Trains/Stage-3 - Design Lot 7202 customer review ; approval (part 2) | 25/08/2020 | 28/09/2020 | 01/05/2020 | 04/06/2020 | 0 | TK_Complete | 1112893334 | 30 | 1112893334_30
C720D147CF###0021730 | TT_Task | Trains/Stage-3 - Design Lot 7201 customer review ; approval (part 2) | 25/05/2020 | 29/06/2020 | 29/04/2020 | 02/06/2020 | 0 | TK_Complete | 1112893334 | 30 | 1112893334_30
C720D147CF###0021740 | TT_Task | Trains/Stage-3 - Design Lot 7206 customer review ; approval (part 2) | 25/05/2020 | 29/06/2020 | 23/04/2020 | 27/05/2020 | 0 | TK_Complete | 1112893334 | 30 | 1112893334_30
C720D147CF###0021750 | TT_Task | Trains/Stage-3 - Design Lot 7207 customer review ; approval (part 2) | 25/05/2020 | 29/06/2020 | 24/04/2020 | 05/06/2020 | 0 | TK_Complete | 1112893334 | 30 | 1112893334_30
C720D147CF###507070 | TT_Task | Trains/Stage-3 - Design Lot 7202 customer review ; approval (part 3) | 05/10/2021 | 11/10/2021 | 30/06/2021 | 15/02/2022 | 0 | TK_Complete | 1112893334 | 30 | 1112893334_30
C720D147CF###507080 | TT_Task | Trains/Stage-3 - Design Lot 7206 customer review ; approval (part 3) | 27/09/2021 | 01/11/2021 | 12/07/2021 | 15/02/2022 | 0 | TK_Complete | 1112893334 | 30 | 1112893334_30
C720D147CF###507090 | TT_Task | Trains/Stage-3 - Design Lot 7207 customer review ; approval (part 3) | 27/09/2021 | 01/11/2021 | 21/07/2021 | 21/03/2022 | 0 | TK_Complete | 1112893334 | 30 | 1112893334_30
C720D147CF###0021670 | TT_Task | Trains/Stage-3 - Design Lot 7208 customer review ; approval (part 2) ***N/A*** | 01/10/2020 | 05/11/2020 | 31/07/2020 | 30/07/2021 | 0 | TK_Complete | 1112893334 | 30 | 1112893334_30
C720D147CF###0030980 | TT_Task | Verification - DIS ; DITP Inputs from Track Contractor for SMCSW (Initial) | 28/09/2020 | 07/10/2020 | 29/05/2020 | 12/06/2020 | 0 | TK_Complete | 1112893334 | 3 | 1112893334_3
C720D147CF###0030990 | TT_Task | Verification - DIS ; DITP Inputs from Track Contractor for SMCSW (Final) | 25/11/2020 | 08/12/2020 | 30/03/2020 | 02/04/2020 | 0 | TK_Complete | 1112893334 | 3 | 1112893334_3
C720D147CF###0031000 | TT_Task | Verification - DIS ; DITP Inputs from OHW Contractor for SMCSW (Initial) | 28/09/2020 | 07/10/2020 | 29/05/2020 | 12/06/2020 | 0 | TK_Complete | 1112893334 | 3 | 1112893334_3
C720D147CF###0031010 | TT_Task | Verification - DIS ; DITP Inputs from OHW Contractor for SMCSW (Final) | 25/11/2020 | 08/12/2020 | 30/03/2020 | 02/04/2020 | 0 | TK_Complete | 1112893334 | 3 | 1112893334_3
C730D147BC###0010772 | TT_Task | CBTC/Stage-2 SMCSW - SyOCD (A8 Milestone) | 01/07/2019 | 05/09/2019 | 01/07/2019 | 10/09/2019 | 0 | TK_Complete | 1112893334 | 299 | 1112893334_299
C730D147BC###0010774 | TT_Task | CBTC/Stage-2 SMCSW - SyNR (A8 Milestone) | 01/07/2019 | 05/09/2019 | 01/07/2019 | 10/09/2019 | 0 | TK_Complete | 1112893334 | 299 | 1112893334_299
C730D147BC###0010776 | TT_Task | CBTC/Stage-2 SMCSW - SyAP (A8 Milestone) | 01/07/2019 | 05/09/2019 | 01/07/2019 | 10/09/2019 | 0 | TK_Complete | 1112893334 | 299 | 1112893334_299
C730D147BC###0010778 | TT_Task | CBTC/Stage-2 SMCSW - TMS (A8 Milestone) | 01/07/2019 | 05/09/2019 | 01/07/2019 | 10/09/2019 | 0 | TK_Complete | 1112893334 | 299 | 1112893334_299
C730D147BC###0010784 | TT_Task | CBTC/Stage-2 SMCSW - ATC RSAD (A8 Milestone) | 01/07/2019 | 05/09/2019 | 01/07/2019 | 10/09/2019 | 0 | TK_Complete | 1112893334 | 299 | 1112893334_299
C730D147BC###0010752 | TT_Task | CBTC/Stage-2 SMCSW - Signalling Scheme Plan Depot - SMTF (South) | 18/02/2019 | 15/03/2019 | 18/02/2019 | 14/03/2019 | 0 | TK_Complete | 1112893334 | 298 | 1112893334_298
C730D147BC###0010754 | TT_Task | CBTC/Stage-2 SMCSW - Signalling Scheme Plan - Mainline | 18/02/2019 | 15/03/2019 | 18/02/2019 | 14/03/2019 | 0 | TK_Complete | 1112893334 | 298 | 1112893334_298
C730D147BC###0010792 | TT_Task | CBTC/Stage-2 SMCSW - Signalling Scheme Plan - Mainline Re work | 25/02/2020 | 22/04/2020 | 11/09/2019 | 27/02/2020 | 0 | TK_Complete | 1112893334 | 298 | 1112893334_298
C730D147BC###0010794 | TT_Task | CBTC/Stage-2 SMCSW - Signalling Scheme Plan Depot (South) - SMTF Re work | 25/02/2020 | 22/04/2020 | 11/09/2019 | 14/02/2020 | 0 | TK_Complete | 1112893334 | 298 | 1112893334_298
C730D157BC###0031757 | TT_Task | CBTC/Stage-3 SMCSW - Signalling Operability Plan | 28/12/2020 | 05/02/2021 | 11/08/2020 | 07/09/2020 | 0 | TK_Complete | 1112893334 | 298 | 1112893334_298
C730D156BC###0036079 | TT_Task | Stage3 (SSJ) Initial survey/desktop audit CSR Route, Pits and Conduits specs, local route, ULX and OLX | 25/08/2020 | 06/10/2020 | 27/07/2020 | 25/08/2020 | 0 | TK_Complete | 1112893334 | 297 | 1112893334_297
C730D156BC###0035833 | TT_Task | Stage3 (SMTF-S) Initial survey/desktop audit CSR Route, Pits and Conduits specs, local route, ULX and OLX | 25/08/2020 | 06/10/2020 | 20/08/2020 | 25/08/2020 | 0 | TK_Complete | 1112893334 | 297 | 1112893334_297
C730D156BC###0036124 | TT_Task | Stage3 (LW-T) Initial survey/desktop audit CSR Route, Pits and Conduits specs, local route, ULX and OLX | 25/11/2020 | 12/01/2021 | 27/10/2020 | 30/10/2020 | 0 | TK_Complete | 1112893334 | 297 | 1112893334_297
C730D156BC###0035818 | TT_Task | Stage3 (CST) Initial survey/desktop audit PSD pannel arrangement | 25/08/2020 | 06/10/2020 | 28/07/2020 | 25/08/2020 | 0 | TK_Complete | 1112893334 | 296 | 1112893334_296
C730D156BC###0036217 | TT_Task | Stage3 (VIC) Initial survey/desktop audit PSD pannel arrangement | 25/08/2020 | 06/10/2020 | 30/07/2020 | 26/08/2020 | 0 | TK_Complete | 1112893334 | 296 | 1112893334_296
C730D156BC###0036220 | TT_Task | Stage3 (BZZ) Initial survey/desktop audit PSD pannel arrangement | 25/08/2020 | 06/10/2020 | 04/08/2020 | 27/08/2020 | 0 | TK_Complete | 1112893334 | 296 | 1112893334_296
C730D156BC###0036223 | TT_Task | Stage3 (MPL) Initial survey/desktop audit PSD pannel arrangement | 25/08/2020 | 06/10/2020 | 06/08/2020 | 28/08/2020 | 0 | TK_Complete | 1112893334 | 296 | 1112893334_296
C730D156BC###0035776 | TT_Task | Stage3 (PIT) Initial survey/desktop audit PSD pannel arrangement | 24/08/2020 | 02/10/2020 | 24/08/2020 | 31/08/2020 | 0 | TK_Complete | 1112893334 | 296 | 1112893334_296
C730D156BC###0035797 | TT_Task | Stage3 (WLO) Initial survey/desktop audit PSD pannel arrangement | 25/11/2020 | 12/01/2021 | 23/11/2020 | 26/11/2020 | 0 | TK_Complete | 1112893334 | 296 | 1112893334_296
C730D156BC###0036184 | TT_Task | Stage3 (CSM) Initial survey/desktop audit PSD pannel arrangement | 25/08/2020 | 06/10/2020 | 27/07/2020 | 25/08/2020 | 0 | TK_Complete | 1112893334 | 296 | 1112893334_296
C730D156BC###0035815 | TT_Task | Stage3 (CST) Initial survey/desktop audit Locations / installation conditions for PEKS | 25/02/2021 | 07/04/2021 | 12/01/2021 | 12/01/2021 | 0 | TK_Complete | 1112893334 | 295 | 1112893334_295
C730D156BC###0036118 | TT_Task | Stage3 (VIC) Initial survey/desktop audit Locations / installation conditions for PEKS | 25/08/2020 | 06/10/2020 | 30/07/2020 | 25/08/2020 | 0 | TK_Complete | 1112893334 | 295 | 1112893334_295
C730D156BC###0036178 | TT_Task | Stage3 (BZZ) Initial survey/desktop audit Locations / installation conditions for PEKS | 25/08/2020 | 06/10/2020 | 04/08/2020 | 27/08/2020 | 0 | TK_Complete | 1112893334 | 295 | 1112893334_295
C730D156BC###0036166 | TT_Task | Stage3 (MPL) Initial survey/desktop audit Locations / installation conditions for PEKS | 25/08/2020 | 06/10/2020 | 06/08/2020 | 28/08/2020 | 0 | TK_Complete | 1112893334 | 295 | 1112893334_295
C730D156BC###0035773 | TT_Task | Stage3 (PIT) Initial survey/desktop audit Locations / installation conditions for PEKS | 24/08/2020 | 02/10/2020 | 24/08/2020 | 25/08/2020 | 0 | TK_Complete | 1112893334 | 295 | 1112893334_295
C730D156BC###0035794 | TT_Task | Stage3 (WLO) Initial survey/desktop audit Locations / installation conditions for PEKS | 25/02/2021 | 07/04/2021 | 15/12/2020 | 23/12/2020 | 0 | TK_Complete | 1112893334 | 295 | 1112893334_295
C730D156BC###0036121 | TT_Task | Stage3 (CSM) Initial survey/desktop audit Locations / installation conditions for PEKS | 25/08/2020 | 06/10/2020 | 27/07/2020 | 24/08/2020 | 0 | TK_Complete | 1112893334 | 295 | 1112893334_295
C730D156BC###0036181 | TT_Task | Stage3 (SSJ) Initial survey/desktop audit Locations / installation conditions for PEKS | 25/02/2021 | 07/04/2021 | 12/01/2021 | 12/01/2021 | 0 | TK_Complete | 1112893334 | 295 | 1112893334_295
C730D156BC###0035803 | TT_Task | Stage3 (CST) Initial survey/desktop audit Des. SIG Cable Contain. Sta Box In/from SER to SCR/PSD Room/TER/PF/Track | 25/08/2020 | 06/10/2020 | 27/07/2020 | 24/08/2020 | 0 | TK_Complete | 1112893334 | 294 | 1112893334_294
C730D156BC###0036331 | TT_Task | Stage3 (VIC) Initial survey/desktop audit Des. SIG Cable Contain. Sta Box In/from SER to SCR/PSD Room/TER/PF/Track | 25/08/2020 | 06/10/2020 | 29/07/2020 | 26/08/2020 | 0 | TK_Complete | 1112893334 | 294 | 1112893334_294
C730D156BC###0036376 | TT_Task | Stage3 (BZZ) Initial survey/desktop audit Des. SIG Cable Contain. Sta Box In/from SER to SCR/PSD Room/TER/PF/Track | 25/08/2020 | 06/10/2020 | 31/07/2020 | 27/08/2020 | 0 | TK_Complete | 1112893334 | 294 | 1112893334_294
C730D156BC###0036394 | TT_Task | Stage3 (MPL) Initial survey/desktop audit Des. SIG Cable Contain. Sta Box In/from SER to SCR/PSD Room/TER/PF/Track | 25/08/2020 | 06/10/2020 | 05/08/2020 | 28/08/2020 | 0 | TK_Complete | 1112893334 | 294 | 1112893334_294
C730D156BC###0035761 | TT_Task | Stage3 (PIT) Initial survey/desktop audit Des. SIG Cable Contain. Sta Box In/from SER to SCR/PSD Room/TER/PF/Track | 24/08/2020 | 02/10/2020 | 24/08/2020 | 03/09/2020 | 0 | TK_Complete | 1112893334 | 294 | 1112893334_294
C730D156BC###0035782 | TT_Task | Stage3 (WLO) Initial survey/desktop audit Des. SIG Cable Contain. Sta Box In/from SER to SCR/PSD Room/TER/PF/Track | 25/11/2020 | 12/01/2021 | 09/11/2020 | 19/11/2020 | 0 | TK_Complete | 1112893334 | 294 | 1112893334_294
C730D156BC###0036424 | TT_Task | Stage3 (CSM) Initial survey/desktop audit Des. SIG Cable Contain. Sta Box In/from SER to SCR/PSD Room/TER/PF/Track | 11/12/2020 | 28/01/2021 | 04/05/2020 | 22/05/2020 | 0 | TK_Complete | 1112893334 | 294 | 1112893334_294
C730D156BC###0036412 | TT_Task | Stage3 (SSJ) Initial survey/desktop audit Des. SIG Cable Contain. Sta Box In/from SER to SCR/PSD Room/TER/PF/Track | 25/02/2021 | 07/04/2021 | 12/01/2021 | 12/01/2021 | 0 | TK_Complete | 1112893334 | 294 | 1112893334_294
C730D156BC###0035902 | TT_Task | Stage3 (SMTF-S) alstom review Loc. of Bldg Services (AC, AC Nozzle, Lighting, Gas Surp., pipes, Control Panel | 25/08/2020 | 21/09/2020 | 03/07/2020 | 14/08/2020 | 0 | TK_Complete | 1112893334 | 293 | 1112893334_293
C730D156BC###0035809 | TT_Task | Stage3 (CST) Initial survey/desktop audit Loc. of Bldg Services (AC, AC Nozzle, Lighting,Gas Surp.,pipes,Control Panel) | 25/08/2020 | 06/10/2020 | 27/07/2020 | 24/08/2020 | 0 | TK_Complete | 1112893334 | 293 | 1112893334_293
C730D156BC###0036337 | TT_Task | Stage3 (VIC) Initial survey/desktop audit Loc. of Bldg Services (AC, AC Nozzle, Lighting,Gas Surp.,pipes,Control Panel) | 09/11/2020 | 18/12/2020 | 18/06/2020 | 30/06/2020 | 0 | TK_Complete | 1112893334 | 293 | 1112893334_293
C730D156BC###0036382 | TT_Task | Stage3 (BZZ) Initial survey/desktop audit Loc. of Bldg Services (AC, AC Nozzle, Lighting,Gas Surp.,pipes,Control Panel) | 25/08/2020 | 06/10/2020 | 03/08/2020 | 27/08/2020 | 0 | TK_Complete | 1112893334 | 293 | 1112893334_293
C730D156BC###0036400 | TT_Task | Stage3 (MPL) Initial survey/desktop audit Loc. of Bldg Services (AC, AC Nozzle, Lighting,Gas Surp.,pipes,Control Panel) | 25/08/2020 | 06/10/2020 | 05/08/2020 | 28/08/2020 | 0 | TK_Complete | 1112893334 | 293 | 1112893334_293
C730D156BC###0035767 | TT_Task | Stage3 (PIT) Initial survey/desktop audit Loc. of Bldg Services (AC, AC Nozzle, Lighting,Gas Surp.,pipes,Control Panel) | 24/08/2020 | 02/10/2020 | 24/08/2020 | 03/09/2020 | 0 | TK_Complete | 1112893334 | 293 | 1112893334_293
C730D156BC###0035788 | TT_Task | Stage3 (WLO) Initial survey/desktop audit Loc. of Bldg Services (AC, AC Nozzle, Lighting,Gas Surp.,pipes,Control Panel) | 25/02/2021 | 07/04/2021 | 15/12/2020 | 23/12/2020 | 0 | TK_Complete | 1112893334 | 293 | 1112893334_293
C730D156BC###0036430 | TT_Task | Stage3 (CSM) Initial survey/desktop audit Loc. of Bldg Services (AC, AC Nozzle, Lighting,Gas Surp.,pipes,Control Panel) | 11/12/2020 | 28/01/2021 | 24/02/2020 | 27/03/2020 | 0 | TK_Complete | 1112893334 | 293 | 1112893334_293
C730D156BC###0036418 | TT_Task | Stage3 (SSJ) Initial survey/desktop audit Loc. of Bldg Services (AC, AC Nozzle, Lighting,Gas Surp.,pipes,Control Panel) | 25/02/2021 | 07/04/2021 | 12/01/2021 | 12/01/2021 | 0 | TK_Complete | 1112893334 | 293 | 1112893334_293
C730D156BC###0035935 | TT_Task | Stage3 [SMTF-S] Initial survey Loc. of Bldg Services (AC, AC Nozzle, Lighting,Gas Surp.,pipes,Control Panel) | 25/09/2020 | 09/11/2020 | 03/08/2020 | 25/08/2020 | 0 | TK_Complete | 1112893334 | 293 | 1112893334_293
C730D156BC###0035713 | TT_Task | Stage3 [CST] Alstom review PSD pannel arrangement | 27/04/2020 | 22/05/2020 | 10/04/2020 | 23/04/2020 | 0 | TK_Complete | 1112893334 | 292 | 1112893334_292
C730D156BC###0036115 | TT_Task | Stage3 [VIC] Alstom review PSD pannel arrangement | 25/08/2020 | 21/09/2020 | 01/07/2020 | 06/07/2020 | 0 | TK_Complete | 1112893334 | 292 | 1112893334_292
C730D156BC###0036157 | TT_Task | Stage3 [BZZ] Alstom review PSD pannel arrangement | 25/08/2020 | 21/09/2020 | 01/06/2020 | 30/06/2020 | 0 | TK_Complete | 1112893334 | 292 | 1112893334_292
C730D156BC###0036160 | TT_Task | Stage3 [MPL] Alstom review PSD pannel arrangement | 25/08/2020 | 21/09/2020 | 23/06/2020 | 01/07/2020 | 0 | TK_Complete | 1112893334 | 292 | 1112893334_292
C730D156BC###0035650 | TT_Task | Stage3 [PIT] Alstom review PSD pannel arrangement | 25/08/2020 | 21/09/2020 | 03/07/2020 | 17/08/2020 | 0 | TK_Complete | 1112893334 | 292 | 1112893334_292
C730D156BC###0035671 | TT_Task | Stage3 [WLO] Alstom review PSD pannel arrangement | 25/11/2020 | 22/12/2020 | 23/11/2020 | 26/11/2020 | 0 | TK_Complete | 1112893334 | 292 | 1112893334_292
C730D156BC###0036109 | TT_Task | Stage3 [CSM] Alstom review PSD pannel arrangement | 25/08/2020 | 21/09/2020 | 01/06/2020 | 09/06/2020 | 0 | TK_Complete | 1112893334 | 292 | 1112893334_292
C730D156BC###0036163 | TT_Task | Stage3 [SSJ] Alstom review PSD pannel arrangement | 25/02/2021 | 24/03/2021 | 25/11/2020 | 12/01/2021 | 0 | TK_Complete | 1112893334 | 292 | 1112893334_292
C730D156BC###0035710 | TT_Task | Stage3 [CST] Alstom review Locations / installation conditions for PEKS(closed as per SoD Addendum Dt 120121) | 25/02/2021 | 24/03/2021 | 12/01/2021 | 12/01/2021 | 0 | TK_Complete | 1112893334 | 291 | 1112893334_291
C730D156BC###0036019 | TT_Task | Stage3 [VIC] Alstom review Locations / installation conditions for PEKS | 25/08/2020 | 21/09/2020 | 01/07/2020 | 06/07/2020 | 0 | TK_Complete | 1112893334 | 291 | 1112893334_291
C730D156BC###0036070 | TT_Task | Stage3 [BZZ] Alstom review Locations / installation conditions for PEKS | 25/08/2020 | 21/09/2020 | 08/06/2020 | 30/06/2020 | 0 | TK_Complete | 1112893334 | 291 | 1112893334_291
C730D156BC###0036055 | TT_Task | Stage3 [MPL] Alstom review Locations / installation conditions for PEKS | 25/08/2020 | 21/09/2020 | 23/06/2020 | 01/07/2020 | 0 | TK_Complete | 1112893334 | 291 | 1112893334_291
C730D156BC###0035647 | TT_Task | Stage3 [PIT] Alstom review Locations / installation conditions for PEKS | 25/08/2020 | 21/09/2020 | 03/07/2020 | 17/08/2020 | 0 | TK_Complete | 1112893334 | 291 | 1112893334_291
C730D156BC###0035668 | TT_Task | Stage3 [WLO] Alstom review Locations / installation conditions for PEKS | 01/01/2021 | 28/01/2021 | 15/12/2020 | 23/12/2020 | 0 | TK_Complete | 1112893334 | 291 | 1112893334_291
C730D156BC###0036022 | TT_Task | Stage3 [CSM] Alstom review Locations / installation conditions for PEKS | 25/08/2020 | 21/09/2020 | 01/06/2020 | 09/06/2020 | 0 | TK_Complete | 1112893334 | 291 | 1112893334_291
C730D156BC###0036073 | TT_Task | Stage3 [SSJ] Alstom review Locations / installation conditions for PEKS(closed as per SoD Addendum Dt 120121) | 25/02/2021 | 24/03/2021 | 12/01/2021 | 12/01/2021 | 0 | TK_Complete | 1112893334 | 291 | 1112893334_291
C730D156BC###N582031 | TT_Task | Stage3 (GEN) customer comments and approval Baselining of Inputs | 16/12/2020 | 05/01/2021 | 14/11/2020 | 25/11/2020 | 0 | TK_Complete | 1112893334 | 290 | 1112893334_290
C720147CF###0025130 | TT_Task | Trains/Stage-3 - Doors Design Review/ exchange with interface contractor | 04/06/2020 | 27/08/2020 | 24/02/2020 | 06/11/2020 | 0 | TK_Complete | 1112893334 | 29 | 1112893334_29
C720147CF###0025140 | TT_Task | Trains/Stage-3 - OHW Design Review/ Panto information exchange with interface contractor | 11/01/2021 | 07/04/2021 | 25/11/2020 | 25/06/2021 | 0 | TK_Complete | 1112893334 | 29 | 1112893334_29
C720147CF###0025150 | TT_Task | Trains/Stage-3 - DOORS - Requirement Management | 25/05/2020 | 17/08/2020 | 13/02/2020 | 29/04/2020 | 0 | TK_Complete | 1112893334 | 29 | 1112893334_29
C730D156BC###N582011 | TT_Task | Stage 3 [GEN] Alstom review SMCSW SMTF South Depot Operation Plan (RFI-00055)(closed as per SoD Addendum Dt 120121) | 25/02/2021 | 10/03/2021 | 25/11/2020 | 25/11/2020 | 0 | TK_Complete | 1112893334 | 289 | 1112893334_289
C730D156BC###NN8001 | TT_Task | Stage 3 [GEN] Alstom review SMCSW Overall Migration Strategy (RFI-00055)(closed as per SoD Addendum Dt 120121) | 25/02/2021 | 10/03/2021 | 12/01/2021 | 12/01/2021 | 0 | TK_Complete | 1112893334 | 289 | 1112893334_289
C730D156BC###N2011 | TT_Task | Stage3 (GEN) alstom review Baselining of Inputs | 25/11/2020 | 15/12/2020 | 27/10/2020 | 13/11/2020 | 0 | TK_Complete | 1112893334 | 288 | 1112893334_288
C730D156BC###N582071 | TT_Task | Stage3 (GEN) SoD Addendum Baselining of Inputs (Dt:12-Jan-21) | 16/12/2020 | 05/01/2021 | 25/11/2020 | 12/01/2021 | 0 | TK_Complete | 1112893334 | 288 | 1112893334_288
C730D156BC###0035404 | TT_Task | Stage2 (LW-T) alstom review Location of Cross Passage Doors | 25/05/2020 | 22/06/2020 | 10/02/2020 | 21/02/2020 | 0 | TK_Complete | 1112893334 | 287 | 1112893334_287
C730D156BC###0036034 | TT_Task | Stage3 (LW-T) alstom review Location of Cross Passage Doors | 25/08/2020 | 21/09/2020 | 14/07/2020 | 14/08/2020 | 0 | TK_Complete | 1112893334 | 287 | 1112893334_287
C730D156BC###0036136 | TT_Task | Stage3 (LW-T) Initial survey/desktop audit Location of Cross Passage Doors | 25/09/2020 | 09/11/2020 | 03/08/2020 | 14/08/2020 | 0 | TK_Complete | 1112893334 | 287 | 1112893334_287
C730D156BC###0035212 | TT_Task | Stage2 (LW-T) alstom review TVCS Section Plan (Ventilation Zones) | 27/04/2020 | 22/05/2020 | 13/01/2020 | 10/02/2020 | 0 | TK_Complete | 1112893334 | 286 | 1112893334_286
C730D156BC###0035737 | TT_Task | Stage3 (LW-T) alstom review TVCS Section Plan (Ventilation Zones) | 25/11/2020 | 22/12/2020 | 27/10/2020 | 10/01/2021 | 0 | TK_Complete | 1112893334 | 286 | 1112893334_286
C730D156BC###0035827 | TT_Task | Stage3 (LW-T) Initial survey/desktop audit TVCS Section Plan (Ventilation Zones) | 25/11/2020 | 12/01/2021 | 27/10/2020 | 10/01/2021 | 0 | TK_Complete | 1112893334 | 286 | 1112893334_286
C730D156BC###0035512 | TT_Task | Stage2 (SSJ) review Information about CSKS | 27/04/2020 | 22/05/2020 | 02/03/2020 | 27/03/2020 | 0 | TK_Complete | 1112893334 | 285 | 1112893334_285
C730D156BC###0035983 | TT_Task | Stage3 [SSJ] Alstom review Information about CSKS | 01/01/2021 | 28/01/2021 | 21/09/2020 | 21/09/2020 | 0 | TK_Complete | 1112893334 | 285 | 1112893334_285
C730D156BC###0036097 | TT_Task | Stage3 (SSJ) Initial survey/desktop audit Information about CSKS (**NA) | 25/02/2021 | 07/04/2021 | 21/09/2020 | 21/09/2020 | 0 | TK_Complete | 1112893334 | 285 | 1112893334_285
C730D156BC###0035509 | TT_Task | Stage2 (SSJ) review Details about mounting kit for OHW mounted DCS TRE/Antenna | 25/06/2020 | 22/07/2020 | 09/06/2020 | 17/06/2020 | 0 | TK_Complete | 1112893334 | 284 | 1112893334_284
C730D156BC###0036061 | TT_Task | Stage3 [SSJ] Alstom review Details about mounting kit for OHW mounted DCS TRE/Antenna | 01/01/2021 | 28/01/2021 | 07/10/2020 | 07/10/2020 | 0 | TK_Complete | 1112893334 | 284 | 1112893334_284
C730D156BC###0036169 | TT_Task | Stage3 (SSJ) Initial survey/desktop audit Details about mounting kit for OHW mounted DCS TRE/Antenna (**NA) | 25/02/2021 | 07/04/2021 | 07/10/2020 | 07/10/2020 | 0 | TK_Complete | 1112893334 | 284 | 1112893334_284
C730D156BC###0035371 | TT_Task | Stage2 (SSJ) review Brown Field Signalling Plan | 27/04/2020 | 22/05/2020 | 02/03/2020 | 27/03/2020 | 0 | TK_Complete | 1112893334 | 283 | 1112893334_283
C730D156BC###0035980 | TT_Task | Stage3 [SSJ] Alstom review Brown Field Signalling Plan | 25/08/2020 | 21/09/2020 | 06/07/2020 | 30/07/2020 | 0 | TK_Complete | 1112893334 | 283 | 1112893334_283
C730D156BC###0036094 | TT_Task | Stage3 (SSJ) Initial survey/desktop audit Brown Field Signalling Plan | 25/08/2020 | 06/10/2020 | 10/08/2020 | 24/08/2020 | 0 | TK_Complete | 1112893334 | 283 | 1112893334_283
C730D156BC###0035257 | TT_Task | Stage2 (CST) review PSD pannel arrangement | 27/04/2020 | 22/05/2020 | 08/01/2020 | 05/02/2020 | 0 | TK_Complete | 1112893334 | 282 | 1112893334_282
C730D156BC###0035446 | TT_Task | Stage2 (VIC) review PSD pannel arrangement | 27/04/2020 | 22/05/2020 | 12/03/2020 | 08/04/2020 | 0 | TK_Complete | 1112893334 | 282 | 1112893334_282
C730D156BC###0035458 | TT_Task | Stage2 (BZZ) review PSD pannel arrangement | 27/04/2020 | 22/05/2020 | 06/01/2020 | 03/02/2020 | 0 | TK_Complete | 1112893334 | 282 | 1112893334_282
C730D156BC###0035482 | TT_Task | Stage2 (MPL) review PSD pannel arrangement | 27/04/2020 | 22/05/2020 | 17/12/2019 | 23/01/2020 | 0 | TK_Complete | 1112893334 | 282 | 1112893334_282
C730D156BC###0035272 | TT_Task | Stage2 (PIT) review PSD pannel arrangement | 25/06/2020 | 22/07/2020 | 15/06/2020 | 19/06/2020 | 0 | TK_Complete | 1112893334 | 282 | 1112893334_282
C730D156BC###0035302 | TT_Task | Stage2 (WLO) review PSD pannel arrangement | 25/06/2020 | 22/07/2020 | 10/06/2020 | 16/06/2020 | 0 | TK_Complete | 1112893334 | 282 | 1112893334_282
C730D156BC###0035563 | TT_Task | Stage2 (CSM) review PSD pannel arrangement | 27/04/2020 | 22/05/2020 | 12/03/2020 | 08/04/2020 | 0 | TK_Complete | 1112893334 | 282 | 1112893334_282
C730D156BC###0035566 | TT_Task | Stage2 (SSJ) review PSD pannel arrangement | 27/04/2020 | 22/05/2020 | 28/11/2019 | 06/01/2020 | 0 | TK_Complete | 1112893334 | 282 | 1112893334_282
C730D156BC###0035254 | TT_Task | Stage2 (CST) review Locations / installation conditions for PEKS | 27/04/2020 | 22/05/2020 | 08/01/2020 | 05/02/2020 | 0 | TK_Complete | 1112893334 | 281 | 1112893334_281
C730D156BC###0035443 | TT_Task | Stage2 (VIC) review Locations / installation conditions for PEKS | 27/04/2020 | 22/05/2020 | 12/03/2020 | 08/04/2020 | 0 | TK_Complete | 1112893334 | 281 | 1112893334_281
C730D156BC###0035455 | TT_Task | Stage2 (BZZ) review Locations / installation conditions for PEKS | 27/04/2020 | 22/05/2020 | 06/01/2020 | 03/02/2020 | 0 | TK_Complete | 1112893334 | 281 | 1112893334_281
C730D156BC###0035479 | TT_Task | Stage2 (MPL) review Locations / installation conditions for PEKS | 25/06/2020 | 22/07/2020 | 12/03/2020 | 01/04/2020 | 0 | TK_Complete | 1112893334 | 281 | 1112893334_281
C730D156BC###0035269 | TT_Task | Stage2 (PIT) review Locations / installation conditions for PEKS | 25/06/2020 | 22/07/2020 | 02/06/2020 | 16/06/2020 | 0 | TK_Complete | 1112893334 | 281 | 1112893334_281
C730D156BC###0035299 | TT_Task | Stage2 (WLO) review Locations / installation conditions for PEKS | 25/06/2020 | 22/07/2020 | 09/06/2020 | 15/06/2020 | 0 | TK_Complete | 1112893334 | 281 | 1112893334_281
C730D156BC###0035506 | TT_Task | Stage2 (CSM) review Locations / installation conditions for PEKS | 25/06/2020 | 22/07/2020 | 03/06/2020 | 17/06/2020 | 0 | TK_Complete | 1112893334 | 281 | 1112893334_281
C730D156BC###0035518 | TT_Task | Stage2 (SSJ) review Locations / installation conditions for PEKS | 25/06/2020 | 22/07/2020 | 08/06/2020 | 17/06/2020 | 0 | TK_Complete | 1112893334 | 281 | 1112893334_281
C730D156BC###0035248 | TT_Task | Stage2 (CST) review Design of SIG Cable Containment in Sta Box In/from SER to SCR/PSD Room/TER Room/Platform/Track | 27/04/2020 | 22/05/2020 | 08/01/2020 | 05/02/2020 | 0 | TK_Complete | 1112893334 | 280 | 1112893334_280
C730D156BC###0035584 | TT_Task | Stage2 (VIC) review Design SIG Cable Containment in Sta. Box In/from SER to SCR/PSD Room/TER Room/Platform/Track | 27/04/2020 | 22/05/2020 | 12/03/2020 | 08/04/2020 | 0 | TK_Complete | 1112893334 | 280 | 1112893334_280
C730D156BC###0035449 | TT_Task | Stage2 (BZZ) review Design SIG Cable Containment in Sta. Box In/from SER to SCR/PSD Room/TER Room/Platform/Track | 27/04/2020 | 22/05/2020 | 06/01/2020 | 03/02/2020 | 0 | TK_Complete | 1112893334 | 280 | 1112893334_280
C730D156BC###0035473 | TT_Task | Stage2 (MPL) review Design SIG Cable Containment in Sta. Box In/from SER to SCR/PSD Room/TER Room/Platform/Track | 27/04/2020 | 22/05/2020 | 02/04/2020 | 21/04/2020 | 0 | TK_Complete | 1112893334 | 280 | 1112893334_280
C730D156BC###0035263 | TT_Task | Stage2 (PIT) review Design SIG Cable Containment in Sta. Box In/from SER to SCR/PSD Room/TER Room/Platform/Track | 27/04/2020 | 22/05/2020 | 01/04/2020 | 20/04/2020 | 0 | TK_Complete | 1112893334 | 280 | 1112893334_280
C730D156BC###0035293 | TT_Task | Stage2 (WLO) review Design SIG Cable Containment in Sta. Box In/from SER to SCR/PSD Room/TER Room/Platform/Track | 25/05/2020 | 22/06/2020 | 08/05/2020 | 12/05/2020 | 0 | TK_Complete | 1112893334 | 280 | 1112893334_280
C730D156BC###0035557 | TT_Task | Stage2 (CSM) review Design SIG Cable Containment in Sta. Box In/from SER to SCR/PSD Room/TER Room/Platform/Track | 27/04/2020 | 22/05/2020 | 02/04/2020 | 21/04/2020 | 0 | TK_Complete | 1112893334 | 280 | 1112893334_280
C730D156BC###0035488 | TT_Task | Stage2 (SSJ) review Design SIG Cable Containment in Sta. Box In/from SER to SCR/PSD Room/TER Room/Platform/Track | 27/04/2020 | 22/05/2020 | 26/03/2020 | 17/04/2020 | 0 | TK_Complete | 1112893334 | 280 | 1112893334_280
C730D156BC###0035698 | TT_Task | Stage3 [CST] Alstom review Des of SIG Cable Containment in Sta Box In/from SER to SCR/PSD Room/TER Room/Platform/Track | 25/08/2020 | 21/09/2020 | 04/05/2020 | 13/05/2020 | 0 | TK_Complete | 1112893334 | 280 | 1112893334_280
C730D156BC###0036205 | TT_Task | Stage3 [VIC] Alstom review Design SIG Cable Containment in Sta. Box In/from SER to SCR/PSD Room/TER Room/Platform/Track | 25/08/2020 | 21/09/2020 | 01/06/2020 | 18/06/2020 | 0 | TK_Complete | 1112893334 | 280 | 1112893334_280
C730D156BC###0036247 | TT_Task | Stage3 [BZZ] Alstom review Design SIG Cable Containment in Sta. Box In/from SER to SCR/PSD Room/TER Room/Platform/Track | 25/08/2020 | 21/09/2020 | 11/05/2020 | 29/05/2020 | 0 | TK_Complete | 1112893334 | 280 | 1112893334_280
C730D156BC###0036283 | TT_Task | Stage3 [MPL] Alstom review Design SIG Cable Containment in Sta. Box In/from SER to SCR/PSD Room/TER Room/Platform/Track | 25/08/2020 | 21/09/2020 | 13/07/2020 | 17/07/2020 | 0 | TK_Complete | 1112893334 | 280 | 1112893334_280
C730D156BC###0035635 | TT_Task | Stage3 [PIT] Alstom review Design SIG Cable Containment in Sta. Box In/from SER to SCR/PSD Room/TER Room/Platform/Track | 25/08/2020 | 21/09/2020 | 31/07/2020 | 06/08/2020 | 0 | TK_Complete | 1112893334 | 280 | 1112893334_280
C730D156BC###0035656 | TT_Task | Stage3 [WLO] Alstom review Design SIG Cable Containment in Sta. Box In/from SER to SCR/PSD Room/TER Room/Platform/Track | 25/11/2020 | 22/12/2020 | 09/11/2020 | 19/11/2020 | 0 | TK_Complete | 1112893334 | 280 | 1112893334_280
C730D156BC###0036361 | TT_Task | Stage3 [CSM] Alstom review Design SIG Cable Containment in Sta. Box In/from SER to SCR/PSD Room/TER Room/Platform/Track | 01/01/2021 | 28/01/2021 | 04/05/2020 | 22/05/2020 | 0 | TK_Complete | 1112893334 | 280 | 1112893334_280
C730D156BC###0036313 | TT_Task | Stage3 [SSJ] Alstom review Design SIG Cable Containment in Sta. Box In/from SER to SCR/PSD Room/TER Room/Platform/Track | 25/02/2021 | 24/03/2021 | 12/01/2021 | 12/01/2021 | 0 | TK_Complete | 1112893334 | 280 | 1112893334_280
C720147CF###0025080 | TT_Task | Trains/Stage-3 - KE analysis (with City+Southwest inputs) | 11/01/2021 | 07/04/2021 | 25/11/2020 | 17/06/2021 | 0 | TK_Complete | 1112893334 | 28 | 1112893334_28
C720147CF###0025090 | TT_Task | Trains/Stage-3 - Traction Calculations (with City+Southwest inputs) | 11/01/2021 | 07/04/2021 | 07/12/2020 | 22/01/2021 | 0 | TK_Complete | 1112893334 | 28 | 1112893334_28
C720147CF###0025100 | TT_Task | Trains/Stage-3 - Brake Calculations (with City+Southwest inputs) | 25/01/2021 | 21/04/2021 | 01/12/2020 | 22/01/2021 | 0 | TK_Complete | 1112893334 | 28 | 1112893334_28
C720147CF###0025110 | TT_Task | Trains/Stage-3 - Bogie Dynamic Calculations (with City+Southwest inputs) | 25/01/2021 | 21/04/2021 | 18/12/2020 | 01/06/2021 | 0 | TK_Complete | 1112893334 | 28 | 1112893334_28
C720147CF###0025120 | TT_Task | Trains/Stage-3 - Gangways Curving Calculations (with City+Southwest inputs) | 11/01/2021 | 07/04/2021 | 25/11/2020 | 17/06/2021 | 0 | TK_Complete | 1112893334 | 28 | 1112893334_28
C730D147BC###0015763 | TT_Task | As Built SMTF[N] - Trackside And Cable Ducts | 08/07/2022 | 21/07/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 279 | 1112893334_279
C730D156BC###0081952 | TT_Task | CBTC/As-Built SMCSW[City] - Trackside And Cable Ducts | 09/05/2023 | 22/05/2023 | nan | nan | 0 | TK_NotStart | 1112893334 | 279 | 1112893334_279
C730D147BC###0015756 | TT_Task | As Built SMTF[N] - DCS/CCTV Installation Drawings | 08/07/2022 | 21/07/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 278 | 1112893334_278
C730D157BC###0032000 | TT_Task | CBTC/Stage-3 SMCSW - DCS Mainline Detailed Drawings (8Station - City) Customer Review and Comments | 25/10/2021 | 26/11/2021 | 12/04/2021 | 19/07/2021 | 0 | TK_Complete | 1112893334 | 278 | 1112893334_278
C730D156BC###0081844 | TT_Task | CBTC/As-Built SMCSW - DCS Mainline Detailed Drawings (8Station - City) | 07/02/2023 | 07/03/2023 | nan | nan | 0 | TK_NotStart | 1112893334 | 278 | 1112893334_278
C730D156BC###0081865 | TT_Task | CBTC/As-Built SMCSW - DCS Depot Detailed Drawings | 07/03/2023 | 28/03/2023 | nan | nan | 560 | TK_NotStart | 1112893334 | 278 | 1112893334_278
C730D156BC###0081949 | TT_Task | CBTC/As-Built SMCSW[City] - DCS/CCTV Installation Drawings | 09/05/2023 | 22/05/2023 | nan | nan | 0 | TK_NotStart | 1112893334 | 278 | 1112893334_278
C730D147BC###0015693 | TT_Task | As Built SMTF[N] - Room Layout | 10/06/2022 | 23/06/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 277 | 1112893334_277
C730D147BC###0015700 | TT_Task | As Built SMTF[N] - Balise Installation Drawings | 10/06/2022 | 23/06/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 277 | 1112893334_277
C730D147BC###0015721 | TT_Task | As Built SMTF[N] - Marker Board Installation Drawings | 24/06/2022 | 07/07/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 277 | 1112893334_277
C730D147BC###0015728 | TT_Task | As Built SMTF[N] - Point Machine (D84M) Installation Drawings | 24/06/2022 | 07/07/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 277 | 1112893334_277
C730D147BC###0015735 | TT_Task | As Built SMTF[N] - Point Machine (MATR) Installation Drawings | 24/06/2022 | 07/07/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 277 | 1112893334_277
C730D147BC###0015742 | TT_Task | As Built SMTF[N] - PPI ; RI Installation Drawings | 24/06/2022 | 07/07/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 277 | 1112893334_277
C730D147BC###0015749 | TT_Task | As Built SMTF[N] - SAB Installation Drawings | 08/07/2022 | 21/07/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 277 | 1112893334_277
C730D156BC###0081826 | TT_Task | CBTC/Stage-3 SMTF[N] - CBI Wayside App Drawings for Axle counter Boundary DSER1 and CER1 | 05/11/2021 | 25/11/2021 | 23/09/2021 | 08/10/2021 | 0 | TK_Complete | 1112893334 | 276 | 1112893334_276
C730D156BC###0081856 | TT_Task | CBTC/Stage-3 SMTF[N] - CBI Wayside App Drawings for TT+ Road 30-35 + DSER2 and CER2 | 26/11/2021 | 06/01/2022 | 23/09/2021 | 08/10/2021 | 0 | TK_Complete | 1112893334 | 276 | 1112893334_276
C730D156BC###0081868 | TT_Task | CBTC/Stage-3 SMTF[N] - CBI Wayside App Drawings for Existing TT Decommissioning (Road 27) | 25/11/2021 | 15/12/2021 | 01/10/2021 | 07/10/2021 | 0 | TK_Complete | 1112893334 | 276 | 1112893334_276
C730D156BC###0081892 | TT_Task | CBTC/Stage-3 SMTF[N] - CBI Wayside App Drawings for Maintenance Roads 5-8 | 25/03/2022 | 07/04/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 276 | 1112893334_276
C730D156BC###0081907 | TT_Task | CBTC/Stage-3 SMTF[N] - CBI Wayside App Drawings for Remaining Stabling Roads 24-29 | 08/04/2022 | 05/05/2022 | nan | nan | 439 | TK_NotStart | 1112893334 | 276 | 1112893334_276
C730D147BC###0085000 | TT_Task | T;C (SMTF-N) - PAT Test Reports Stage 1 customer review ; acceptance | 04/10/2021 | 22/10/2021 | 09/07/2021 | 15/12/2021 | 0 | TK_Complete | 1112893334 | 275 | 1112893334_275
C730D147BC###0085021 | TT_Task | T;C (SMTF-N) - PAT Test Reports Stage 2 customer review ; acceptance | 19/04/2022 | 09/05/2022 | nan | nan | 7312 | TK_NotStart | 1112893334 | 275 | 1112893334_275
C730D147BC###0085007 | TT_Task | T;C (SMTF-N) - SIT Test Reports Stage 1 customer review ; acceptance | 09/11/2021 | 29/11/2021 | 09/11/2021 | 15/12/2021 | 0 | TK_Complete | 1112893334 | 275 | 1112893334_275
C730D147BC###0085028 | TT_Task | T;C (SMTF-N) - SIT Test Reports Stage 2 customer review ; acceptance | 06/05/2022 | 26/05/2022 | nan | nan | 104 | TK_NotStart | 1112893334 | 275 | 1112893334_275
C730D147BC###0085014 | TT_Task | T;C (SMTF-N) - SAT Test Reports Stage 1 customer review ; acceptance | 27/12/2021 | 14/01/2022 | 20/11/2021 | 30/11/2021 | 0 | TK_Complete | 1112893334 | 275 | 1112893334_275
C730D147BC###0085035 | TT_Task | T;C (SMTF-N) - SAT Test Reports Stage 2 customer review ; acceptance | 27/05/2022 | 16/06/2022 | nan | nan | 1024 | TK_NotStart | 1112893334 | 275 | 1112893334_275
C730D157BC###0045500 | TT_Task | T;C (SMTF-N) - PAT Test Reports Stage 1 | 25/05/2021 | 21/06/2021 | 26/04/2021 | 08/07/2021 | 0 | TK_Complete | 1112893334 | 274 | 1112893334_274
C730D157BC###0045510 | TT_Task | T;C (SMTF-N) - PAT Test Reports Stage 2 | 17/02/2022 | 16/03/2022 | 21/02/2022 | nan | 0 | TK_Active | 1112893334 | 274 | 1112893334_274
C730D157BC###0045520 | TT_Task | T;C (SMTF-N) - SIT Test Reports Stage 1 | 19/07/2021 | 13/08/2021 | 16/06/2021 | 30/11/2021 | 0 | TK_Complete | 1112893334 | 274 | 1112893334_274
C730D157BC###0045530 | TT_Task | T;C (SMTF-N) - SIT Test Reports Stage 2 | 01/04/2022 | 05/05/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 274 | 1112893334_274
C730D157BC###0045540 | TT_Task | T;C (SMTF-N) - SAT Test Reports Stage 1 | 20/10/2021 | 16/11/2021 | 15/10/2021 | 24/12/2021 | 0 | TK_Complete | 1112893334 | 274 | 1112893334_274
C730D157BC###0045550 | TT_Task | T;C (SMTF-N) - SAT Test Reports Stage 2 | 20/05/2022 | 26/05/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 274 | 1112893334_274
C730D157BC###N949363 | TT_Task | T;C (SMTF-N) - Test Procedures (CBI, ATS, ATC , DCS, MSS, CCTV) | 26/10/2020 | 06/11/2020 | 01/10/2020 | 16/10/2020 | 0 | TK_Complete | 1112893334 | 273 | 1112893334_273
C730D157BC###N949373 | TT_Task | T;C (SMTF-N) Stage 1 Test Report (CBI, ATS, ATC , DCS, MSS, CCTV) | 25/05/2021 | 07/06/2021 | 26/04/2021 | 30/11/2021 | 0 | TK_Complete | 1112893334 | 273 | 1112893334_273
C730D157BC###N949393 | TT_Task | T;C (SMTF-N) - Test Procedures (CBI, ATS, ATC , DCS, MSS, CCTV) customer review ; acceptance | 26/10/2020 | 13/11/2020 | 26/10/2020 | 08/06/2021 | 0 | TK_Complete | 1112893334 | 273 | 1112893334_273
C730D157BC###N949403 | TT_Task | T;C (SMTF-N) - Test Report (CBI, ATS, ATC , DCS, MSS, CCTV) customer review ; acceptance | 04/10/2021 | 22/10/2021 | 04/10/2021 | 15/12/2021 | 0 | TK_Complete | 1112893334 | 273 | 1112893334_273
C730D157BC###N309453 | TT_Task | T;C (SMTF-N) - T;C Plan for MS2 | 26/10/2020 | 06/11/2020 | 12/10/2020 | 23/10/2020 | 0 | TK_Complete | 1112893334 | 272 | 1112893334_272
C730D157BC###N949413 | TT_Task | T;C (SMTF-N) - T;C Plan for MS4 | 25/11/2020 | 08/12/2020 | 19/10/2020 | 22/04/2021 | 0 | TK_Complete | 1112893334 | 272 | 1112893334_272
C730D157BC###N949383 | TT_Task | T;C (SMTF-N) - T;C Plan for MS2 customer review ; acceptance | 26/10/2020 | 13/11/2020 | 26/10/2020 | 17/05/2021 | 0 | TK_Complete | 1112893334 | 272 | 1112893334_272
C730D157BC###N949423 | TT_Task | T;C (SMTF-N) - T;C Plan for MS4 customer review ; acceptance | 03/05/2021 | 21/05/2021 | 23/04/2021 | 24/05/2021 | 0 | TK_Complete | 1112893334 | 272 | 1112893334_272
C730D147BC###0015490 | TT_Task | SMTF(N) Stage 3 Baseline Migration state 1 - 4.0.1.0 Initial baseline (Minor) | 28/09/2020 | 26/10/2020 | 11/09/2020 | 18/09/2020 | 0 | TK_Complete | 1112893334 | 271 | 1112893334_271
C730D147BC###0015560 | TT_Task | SMTF (N) Stage 3 Baseline Migration state 1 - 4.0.1.1 Baseline Migration | 25/06/2021 | 15/07/2021 | 16/09/2020 | 20/09/2020 | 0 | TK_Complete | 1112893334 | 271 | 1112893334_271
C730D147BC###0015595 | TT_Task | SMTF (N) Stage 3 Baseline Migration state 1 - 4.0.1.3 Corrections from the previous Baseline | 16/07/2021 | 29/07/2021 | 01/12/2020 | 11/01/2021 | 0 | TK_Complete | 1112893334 | 271 | 1112893334_271
C730D147BC###0015630 | TT_Task | SMTF (N) Stage 3 Baseline Migration state 1 - 4.1.1.1 Migration state 1 - Site Installation Completion | 10/09/2021 | 10/09/2021 | 03/05/2021 | 06/06/2021 | 0 | TK_Complete | 1112893334 | 271 | 1112893334_271
C730D147BC###0015637 | TT_Task | SMTF (N) Stage 3 Baseline Migration state 1 - 4.2.1.3 Migration state 1 - Final for MS2 Safety Case | 25/11/2021 | 10/12/2021 | 12/11/2021 | 16/12/2021 | 0 | TK_Complete | 1112893334 | 271 | 1112893334_271
C730D147BC###0015644 | TT_Task | SMTF (N) Stage 3 Baseline Migration state 1 - 4.2.1.4 Migration state 1 - Site Dynamic Testing | 25/06/2021 | 08/07/2021 | 10/05/2021 | 11/06/2021 | 0 | TK_Complete | 1112893334 | 271 | 1112893334_271
C730D147BC###0015651 | TT_Task | SMTF (N) Stage 3 Baseline Migration state 1 - 4.2.1.6 Migration state 1 - Site Testing ***N/A*** | 26/07/2021 | 26/07/2021 | 25/06/2021 | 25/06/2021 | 0 | TK_Complete | 1112893334 | 271 | 1112893334_271
C730D147BC###0015658 | TT_Task | SMTF (N) Stage 3 Baseline Migration state 1 - 5.1.1.1 Migration state 2 - Site Installation completion ***N/A*** | 26/07/2021 | 26/07/2021 | 25/06/2021 | 25/06/2021 | 0 | TK_Complete | 1112893334 | 271 | 1112893334_271
C730D147BC###0015665 | TT_Task | SMTF (N) Stage 3 Baseline Migration state 1 - 5.2.1.3 Migration state 2 - Site Testing - TDC (Rd 24-30 and Rd 5-8) | 16/11/2021 | 13/12/2021 | 14/06/2021 | 09/07/2021 | 0 | TK_Complete | 1112893334 | 271 | 1112893334_271
C730D147BC###0015672 | TT_Task | SMTF (N) Stage 3 Baseline Migration state 1 - 4.3.1.0 Migration state 2 - Site Dynamic Testing (Rd 24-30 and Rd 5-8) | 07/02/2022 | 25/02/2022 | 07/02/2022 | 24/02/2022 | 0 | TK_Complete | 1112893334 | 271 | 1112893334_271
C730D147BC###0015679 | TT_Task | SMTF (N) Stage 3 Baseline Migration state 1 - 5.2.1.6 Migration state 2 - Site Testing (MS4 for Safety Case) | 20/05/2022 | 09/06/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 271 | 1112893334_271
C730D147BC###N885625 | TT_Task | CBTC/M4 SMTF[N] - CBI Data delivery on site *** N/A*** | 25/11/2021 | 01/12/2021 | 25/11/2021 | 25/11/2021 | 0 | TK_Complete | 1112893334 | 270 | 1112893334_270
C730D147BC###N885635 | TT_Task | CBTC/M4 SMTF[N] - ATS Data delivery on site *** N/A*** | 11/03/2022 | 17/03/2022 | 25/11/2021 | 25/11/2021 | 0 | TK_Complete | 1112893334 | 270 | 1112893334_270
C720D147CF###0020230 | TT_Task | Trains/Stage-3 - Interface test specifications (ITS) for RS to TRK/OHW/TRS/SMTF[S]/PSD/RAD/SIG - SMTF-[N] | 27/07/2020 | 04/09/2020 | 17/07/2020 | 31/07/2020 | 0 | TK_Complete | 1112893334 | 27 | 1112893334_27
C720D147CF###0021550 | TT_Task | Trains/Stage-3 - Interface test specifications (ITS) for RS to TRK/OHW/TRS/SMTF[S]/PSD/RAD/SIG - Phase 1 | 07/09/2020 | 30/11/2020 | 17/07/2020 | 25/01/2021 | 0 | TK_Complete | 1112893334 | 27 | 1112893334_27
C720D147CF###0021560 | TT_Task | Trains/Stage-3 - Interface test specifications (ITS) for RS to TRK/OHW/TRS/SMTF[S]/PSD/RAD/SIG - Phase 2 | 03/12/2020 | 12/03/2021 | 17/07/2020 | 25/01/2021 | 0 | TK_Complete | 1112893334 | 27 | 1112893334_27
C730D147BC###N85815 | TT_Task | CBTC/M2 SMTF[N] - CBTC System Safety Report (Intermediate) before MS#2 SAT | 27/09/2021 | 01/10/2021 | 01/06/2021 | 04/06/2021 | 0 | TK_Complete | 1112893334 | 269 | 1112893334_269
C730D147BC###N85825 | TT_Task | CBTC/M2 SMTF[N] - CBTC System Safety Case (Final - all incl SRAC from GP,GA) MS#2 | 05/11/2021 | 11/11/2021 | 29/10/2021 | 29/10/2021 | 0 | TK_Complete | 1112893334 | 269 | 1112893334_269
C730D147BC###N86175 | TT_Task | CBTC/Stage-3 SMTF[N] - CBTC System Safety Case (Final - all incl SRAC from GP,GA) MS#4 | 09/06/2022 | 14/06/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 269 | 1112893334_269
C730D147BC###N86165 | TT_Task | CBTC/M4 SMTF[N] - CBTC System Safety Case(Intermediate) before Dynamic Tests MS#4 ***N/A*** | 27/01/2022 | 31/01/2022 | 25/11/2021 | 25/11/2021 | 0 | TK_Complete | 1112893334 | 269 | 1112893334_269
C730D147BC###N85615 | TT_Task | CBTC/M2 SMTF[N] - Safety Report for Migration 2 - Track Data Checking | 25/05/2021 | 07/06/2021 | 12/05/2021 | 14/05/2021 | 0 | TK_Complete | 1112893334 | 268 | 1112893334_268
C730D147BC###N885645 | TT_Task | CBTC/M2 SMTF[N] - CBTC System Safety Report for Migration 2 - Dynamic Test (Low Speed) | 14/07/2021 | 28/07/2021 | 01/06/2021 | 04/06/2021 | 0 | TK_Complete | 1112893334 | 268 | 1112893334_268
C730D147BC###N885675 | TT_Task | CBTC/M2 SMTF[N] - CBTC System Safety Report for Migration 2 - Dynamic Test (High Speed Multiple Trains) | 01/11/2021 | 02/11/2021 | 18/10/2021 | 19/10/2021 | 0 | TK_Complete | 1112893334 | 268 | 1112893334_268
C730D147BC###N885655 | TT_Task | CBTC/M4 SMTF[N] - CBTC System Safety Report for Migration 4 - Dynamic Test (Low Speed) | 04/03/2022 | 04/03/2022 | 04/03/2022 | 04/03/2022 | 0 | TK_Complete | 1112893334 | 268 | 1112893334_268
C730D147BC###N885665 | TT_Task | CBTC/M4 SMTF[N] - CBTC System - Safety Report for Migration 4 - Dynamic Test (High Speed/Multiple Trains) | 05/04/2022 | 07/04/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 268 | 1112893334_268
C730D147BC###N86155 | TT_Task | CBTC/M4 SMTF[N] - Safety Report Migration 4 - Track Data Check ***N/A*** | 07/02/2022 | 09/02/2022 | 25/11/2021 | 25/11/2021 | 0 | TK_Complete | 1112893334 | 268 | 1112893334_268
C730D147BC###N85605 | TT_Task | CBTC/M2 SMTF[N] - V;V Report | 03/03/2021 | 05/03/2021 | 07/12/2020 | 09/12/2020 | 0 | TK_Complete | 1112893334 | 267 | 1112893334_267
C730D147BC###N86565 | TT_Task | CBTC/M2 SMTF[N] - V;V Report | 09/07/2021 | 09/07/2021 | 04/05/2021 | 10/05/2021 | 0 | TK_Complete | 1112893334 | 267 | 1112893334_267
C730D147BC###N86705 | TT_Task | CBTC/M2 SMTF[N] - System V;V Report (Including V;V Report of SYSDB and Subsystem V;V) MS#2 | 03/08/2021 | 05/08/2021 | 17/06/2021 | 17/06/2021 | 0 | TK_Complete | 1112893334 | 267 | 1112893334_267
C730D147BC###N87305 | TT_Task | CBTC/M2 SMTF[N] - V;V Report | 28/10/2021 | 29/10/2021 | 15/10/2021 | 18/10/2021 | 0 | TK_Complete | 1112893334 | 267 | 1112893334_267
C730D147BC###N86145 | TT_Task | CBTC/M4 SMTF[N] - V;V Report ***N/A*** | 15/02/2022 | 17/02/2022 | 25/01/2022 | 25/01/2022 | 0 | TK_Complete | 1112893334 | 267 | 1112893334_267
C730D147BC###N86945 | TT_Task | CBTC/M4 SMTF[N] - V;V Report | 01/03/2022 | 01/03/2022 | 01/03/2022 | 01/03/2022 | 0 | TK_Complete | 1112893334 | 267 | 1112893334_267
C730D147BC###N87095 | TT_Task | CBTC/M4 SMTF[N] - System V;V Report ( Including V;V Report of SYSDB and Subsystem V;V) MS#4 *** N/A*** | 08/04/2022 | 12/04/2022 | 25/11/2021 | 25/11/2021 | 0 | TK_Complete | 1112893334 | 267 | 1112893334_267
C730D147BC###N785595 | TT_Task | CBTC/M2 SMTF[N] - FIVP Report | 26/02/2021 | 02/03/2021 | 04/12/2020 | 08/12/2020 | 0 | TK_Complete | 1112893334 | 266 | 1112893334_266
C730D147BC###N86555 | TT_Task | CBTC/M2 SMTF[N] - FIVP Report | 07/07/2021 | 08/07/2021 | 04/05/2021 | 07/05/2021 | 0 | TK_Complete | 1112893334 | 266 | 1112893334_266
C730D147BC###N86695 | TT_Task | CBTC/M2 SMTF[N] - FIVP test report for SMTF N MS#2 | 29/07/2021 | 02/08/2021 | 16/06/2021 | 16/06/2021 | 0 | TK_Complete | 1112893334 | 266 | 1112893334_266
C730D147BC###N87295 | TT_Task | CBTC/M2 SMTF[N] - FIVP Report | 26/10/2021 | 27/10/2021 | 13/10/2021 | 14/10/2021 | 0 | TK_Complete | 1112893334 | 266 | 1112893334_266
C730D147BC###N86135 | TT_Task | CBTC/M4 SMTF[N] - FIVP Report ***N/A*** | 14/12/2021 | 16/12/2021 | 25/01/2022 | 25/01/2022 | 0 | TK_Complete | 1112893334 | 266 | 1112893334_266
C730D147BC###N86935 | TT_Task | CBTC/M4 SMTF[N] - FIVP Report | 25/02/2022 | 28/02/2022 | 25/02/2022 | 28/02/2022 | 0 | TK_Complete | 1112893334 | 266 | 1112893334_266
C730D147BC###N87085 | TT_Task | CBTC/M4 SMTF[N] - FIVP test report for SMTF N MS#4 *** N/A*** | 05/04/2022 | 07/04/2022 | 25/11/2021 | 25/11/2021 | 0 | TK_Complete | 1112893334 | 266 | 1112893334_266
C730D147BC###N185195 | TT_Task | CBTC/M2 SMTF[N] - Baseline Delivery to FIVP/ FIVP testing | 12/02/2021 | 25/02/2021 | 23/11/2020 | 04/12/2020 | 0 | TK_Complete | 1112893334 | 265 | 1112893334_265
C730D147BC###N86485 | TT_Task | CBTC/M2 SMTF[N] - Baseline Delivery to FIVP/ FIVP testing | 02/07/2021 | 06/07/2021 | 19/04/2021 | 03/05/2021 | 0 | TK_Complete | 1112893334 | 265 | 1112893334_265
C730D147BC###N86685 | TT_Task | CBTC/M2 SMTF[N] - Baseline Delivery to FIVP/ FIVP testing | 15/07/2021 | 28/07/2021 | 14/06/2021 | 16/06/2021 | 0 | TK_Complete | 1112893334 | 265 | 1112893334_265
C730D147BC###N87285 | TT_Task | CBTC/M2 SMTF[N] - Baseline Delivery to FIVP/ FIVP testing | 25/10/2021 | 27/10/2021 | 08/10/2021 | 12/10/2021 | 0 | TK_Complete | 1112893334 | 265 | 1112893334_265
C730D147BC###N86055 | TT_Task | CBTC/M4 SMTF[N] - Baseline Delivery to FIVP/ FIVP testing | 30/11/2021 | 13/12/2021 | 03/01/2022 | 24/01/2022 | 0 | TK_Complete | 1112893334 | 265 | 1112893334_265
C730D147BC###N86865 | TT_Task | CBTC/M4 SMTF[N] - Baseline Delivery to FIVP/ FIVP testing | 18/02/2022 | 24/02/2022 | 25/01/2022 | 24/02/2022 | 0 | TK_Complete | 1112893334 | 265 | 1112893334_265
C730D147BC###N87075 | TT_Task | CBTC/M4 SMTF[N] - Baseline Delivery to FIVP/ FIVP testing *** N/A*** | 22/03/2022 | 04/04/2022 | 25/11/2021 | 25/11/2021 | 0 | TK_Complete | 1112893334 | 265 | 1112893334_265
C730D147BC###N485525 | TT_Task | CBTC/M2 SMTF[N] - CCTV Data Preparation | 10/09/2020 | 16/09/2020 | 21/09/2020 | 26/10/2020 | 0 | TK_Complete | 1112893334 | 264 | 1112893334_264
C730D147BC###N785535 | TT_Task | CBTC/M2 SMTF[N] - CCTV Data Validation | 30/10/2020 | 05/11/2020 | 26/10/2020 | 30/10/2020 | 0 | TK_Complete | 1112893334 | 264 | 1112893334_264
C730D147BC###N86065 | TT_Task | CBTC/M4 SMTF[N] - CCTV Data Preparation | 05/11/2021 | 11/11/2021 | 23/09/2021 | 29/09/2021 | 0 | TK_Complete | 1112893334 | 264 | 1112893334_264
C730D147BC###N86075 | TT_Task | CBTC/M4 SMTF[N] - CCTV Data Validation | 05/11/2021 | 11/11/2021 | 30/09/2021 | 06/10/2021 | 0 | TK_Complete | 1112893334 | 264 | 1112893334_264
C730D147BC###N85095 | TT_Task | CBTC/M2 SMTF[N] - CBI Data Preparation | 10/09/2020 | 16/09/2020 | 21/09/2020 | 26/10/2020 | 0 | TK_Complete | 1112893334 | 263 | 1112893334_263
C730D147BC###N86385 | TT_Task | CBTC/M2 SMTF[N] - CBI Data Preparation | 25/02/2021 | 01/03/2021 | 05/03/2021 | 12/03/2021 | 0 | TK_Complete | 1112893334 | 263 | 1112893334_263
C730D147BC###N86585 | TT_Task | CBTC/M2 SMTF[N] - CBI Data Preparation | 02/03/2021 | 08/03/2021 | 01/03/2021 | 09/06/2021 | 0 | TK_Complete | 1112893334 | 263 | 1112893334_263
C730D147BC###N87185 | TT_Task | CBTC/M2 SMTF[N] - CBI Data Preparation | 29/09/2021 | 05/10/2021 | 30/08/2021 | 03/09/2021 | 0 | TK_Complete | 1112893334 | 263 | 1112893334_263
C730D147BC###N85955 | TT_Task | CBTC/M4 SMTF[N] - CBI Data Preparation | 11/10/2021 | 15/10/2021 | 16/09/2021 | 22/09/2021 | 0 | TK_Complete | 1112893334 | 263 | 1112893334_263
C730D147BC###N86765 | TT_Task | CBTC/M4 SMTF[N] - CBI Data Preparation | 18/02/2022 | 22/02/2022 | 20/12/2021 | 31/12/2021 | 0 | TK_Complete | 1112893334 | 263 | 1112893334_263
C730D147BC###N86975 | TT_Task | CBTC/M4 SMTF[N] - CBI Data Preparation *** N/A*** | 25/11/2021 | 01/12/2021 | 25/11/2021 | 25/11/2021 | 0 | TK_Complete | 1112893334 | 263 | 1112893334_263
C730D147BC###N5105 | TT_Task | CBTC/M2 SMTF[N] - CBI Data Validation | 30/10/2020 | 05/11/2020 | 26/10/2020 | 30/10/2020 | 0 | TK_Complete | 1112893334 | 262 | 1112893334_262
C730D147BC###N86395 | TT_Task | CBTC/M2 SMTF[N] - CBI Data Validation | 28/06/2021 | 29/06/2021 | 15/03/2021 | 19/03/2021 | 0 | TK_Complete | 1112893334 | 262 | 1112893334_262
C730D147BC###N86595 | TT_Task | CBTC/M2 SMTF[N] - CBI Data Validation | 29/06/2021 | 05/07/2021 | 09/06/2021 | 10/06/2021 | 0 | TK_Complete | 1112893334 | 262 | 1112893334_262
C730D147BC###N87195 | TT_Task | CBTC/M2 SMTF[N] - CBI Data Validation | 06/10/2021 | 12/10/2021 | 06/09/2021 | 10/09/2021 | 0 | TK_Complete | 1112893334 | 262 | 1112893334_262
C730D147BC###N85965 | TT_Task | CBTC/M4 SMTF[N] - CBI Data Validation | 12/11/2021 | 18/11/2021 | 23/09/2021 | 29/09/2021 | 0 | TK_Complete | 1112893334 | 262 | 1112893334_262
C730D147BC###N86775 | TT_Task | CBTC/M4 SMTF[N] - CBI Data Validation | 04/01/2022 | 06/01/2022 | 04/01/2022 | 07/01/2022 | 0 | TK_Complete | 1112893334 | 262 | 1112893334_262
C730D147BC###N86985 | TT_Task | CBTC/M4 SMTF[N] - CBI Data Validation *** N/A*** | 25/11/2021 | 01/12/2021 | 25/11/2021 | 25/11/2021 | 0 | TK_Complete | 1112893334 | 262 | 1112893334_262
C730D147BC###N87175 | TT_Task | CBTC/M2 SMTF[N] - Site Track Survey File Analysis for MS#2.0 Area | 26/07/2021 | 06/08/2021 | 05/07/2021 | 16/07/2021 | 0 | TK_Complete | 1112893334 | 261 | 1112893334_261
C730C147BC###0070024 | TT_Task | Site Survey prior to access + closure of issue (if needed) SMTF[N] Depot DSER2 | 26/06/2020 | 23/07/2020 | 15/06/2020 | 15/07/2020 | 0 | TK_Complete | 1112893334 | 261 | 1112893334_261
C730C147BC###0070032 | TT_Task | Site Survey prior to access + closure of issue (if needed) SMTF[N] Depot New Test Track | 25/06/2020 | 22/07/2020 | 15/06/2020 | 15/07/2020 | 0 | TK_Complete | 1112893334 | 261 | 1112893334_261
C730C147BC###0070224 | TT_Task | Site Survey prior to access + closure of issue (if needed) SMTF[N] Depot CER2 | 25/11/2020 | 22/12/2020 | 10/11/2020 | 30/11/2020 | 0 | TK_Complete | 1112893334 | 261 | 1112893334_261
C730K147BC###0020392 | TT_Task | Site Survey Prior to Site Access - SMTF[S] Depot DSER3 | 25/02/2022 | 07/04/2022 | 28/02/2022 | 06/03/2022 | 0 | TK_Complete | 1112893334 | 261 | 1112893334_261
C730K147BC###0020848 | TT_Task | Site Survey Prior to Site Access - SMTF [S] Depot Trackside | 20/06/2022 | 29/07/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 261 | 1112893334_261
C730D147BC###N85585 | TT_Task | CBTC/M2 SMTF[N] - SyDB-2 (After all DPDV @ All SSL) | 12/02/2021 | 16/02/2021 | 08/12/2020 | 09/12/2020 | 0 | TK_Complete | 1112893334 | 260 | 1112893334_260
C730D147BC###N86125 | TT_Task | CBTC/M4 SMTF[N] - SyDB (After all DPDV @ All SSL) ***N/A*** | 04/01/2022 | 06/01/2022 | 25/11/2021 | 25/11/2021 | 0 | TK_Complete | 1112893334 | 260 | 1112893334_260
C720D147CF###0030390 | TT_Task | Trains/Stage-2 - Design Lot 7210 submission (Speciality engineering-EMC, noise, fire, and weight) | 23/07/2019 | 02/09/2019 | 23/07/2019 | 15/08/2019 | 0 | TK_Complete | 1112893334 | 26 | 1112893334_26
C720D147CF###0021280 | TT_Task | Trains/Stage-3 - Design Lot 7210 submission (Speciality engineering-EMC, noise, fire, and weight) - Partial submission | 25/02/2020 | 06/04/2020 | 05/12/2019 | 29/01/2020 | 0 | TK_Complete | 1112893334 | 26 | 1112893334_26
C720D147CF###0021500 | TT_Task | Trains/Stage-3 - Design Lot 7210 submission (Speciality engineering-EMC, noise, fire, and weight) - Resubmission | 25/03/2020 | 28/05/2020 | 28/02/2020 | 21/04/2020 | 0 | TK_Complete | 1112893334 | 26 | 1112893334_26
C730D147BC###N85085 | TT_Task | CBTC/M2 SMTF[N] - SyDB-1 (for Iteration1) | 24/09/2020 | 08/10/2020 | 14/09/2020 | 18/09/2020 | 0 | TK_Complete | 1112893334 | 259 | 1112893334_259
C730D147BC###N85905 | TT_Task | CBTC/M2 SMTF[N] - SyDB-3 (After FIVP from Iteration1) - Cancelled | 25/01/2021 | 28/01/2021 | 21/01/2021 | 25/02/2021 | 0 | TK_Complete | 1112893334 | 259 | 1112893334_259
C730D147BC###N86575 | TT_Task | CBTC/M2 SMTF[N] - SyDB-4 (After FIVP from Iteration2/ For TDC) - Cancelled | 17/03/2021 | 18/03/2021 | 25/02/2021 | 25/02/2021 | 0 | TK_Complete | 1112893334 | 259 | 1112893334_259
C730D147BC###N86715 | TT_Task | CBTC/M2 SMTF[N] - SyDB-5 (After FIVP from Iteration3/ For Dynamic TDC) | 25/08/2021 | 27/08/2021 | 17/05/2021 | 31/05/2021 | 0 | TK_Complete | 1112893334 | 259 | 1112893334_259
C730D147BC###N85945 | TT_Task | CBTC/M4 SMTF[N] - SyDB-1 (for Iteration1) | 25/10/2021 | 05/11/2021 | 09/08/2021 | 20/08/2021 | 0 | TK_Complete | 1112893334 | 259 | 1112893334_259
C730D147BC###N86225 | TT_Task | CBTC/M4 SMTF[N] - SyDB (After FIVP from Iteration1) | 04/01/2022 | 06/01/2022 | 26/10/2021 | 29/10/2021 | 0 | TK_Complete | 1112893334 | 259 | 1112893334_259
C730D147BC###N86955 | TT_Task | CBTC/M4 SMTF[N] - SyDB (After FIVP from Iteration2/ For Dynamic Low Speed) | 01/03/2022 | 02/03/2022 | 01/03/2022 | 02/03/2022 | 0 | TK_Complete | 1112893334 | 259 | 1112893334_259
C730D147BC###N86965 | TT_Task | CBTC/M4 SMTF[N] - SyDB (After FIVP from Iteration2/ For Dynamic High Speed) | 01/04/2022 | 04/04/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 259 | 1112893334_259
C730D147BC###N85075 | TT_Task | CBTC/M2 SMTF[N] - SyDT | 10/09/2020 | 23/09/2020 | 01/09/2020 | 14/09/2020 | 0 | TK_Complete | 1112893334 | 258 | 1112893334_258
C730D147BC###N87155 | TT_Task | CBTC/M2 SMTF[N] - SyDT (for Iteration 4) | 25/08/2021 | 07/09/2021 | 26/07/2021 | 06/08/2021 | 0 | TK_Complete | 1112893334 | 258 | 1112893334_258
C730D147BC###N885565 | TT_Task | CBTC/M2 SMTF[N] - SPP Test for SMTF-N MS#2 | 25/06/2021 | 01/07/2021 | 12/05/2021 | 19/05/2021 | 0 | TK_Complete | 1112893334 | 258 | 1112893334_258
C730D147BC###N85935 | TT_Task | CBTC/M4 SMTF[N] - SyDT | 27/09/2021 | 19/10/2021 | 23/08/2021 | 17/12/2021 | 0 | TK_Complete | 1112893334 | 258 | 1112893334_258
C730D147BC###N885575 | TT_Task | CBTC/M4 SMTF[N] - Control Table for MS#4 *** N/A*** | 25/11/2021 | 01/12/2021 | 25/11/2021 | 25/11/2021 | 0 | TK_Complete | 1112893334 | 258 | 1112893334_258
C730D147BC###N885555 | TT_Task | CBTC/M4 SMTF[N] - SPP Test for SMTF-N MS#4 *** N/A*** | 04/03/2022 | 10/03/2022 | 25/11/2021 | 25/11/2021 | 0 | TK_Complete | 1112893334 | 258 | 1112893334_258
C730D147BC###0015623 | TT_Task | Stage3 [SMTF-N] Certificate of Compliance (not applicable as IC was not available prior to installation) | 25/08/2020 | 26/08/2020 | 15/07/2020 | 15/07/2020 | 0 | TK_Complete | 1112893334 | 257 | 1112893334_257
C730D157BC###201000 | TT_Task | CBTC/Stage-3 SMCSW[City] - Certificate of Compliance - Schedule 12A | 19/11/2021 | 25/11/2021 | 06/07/2021 | 07/07/2021 | 0 | TK_Complete | 1112893334 | 257 | 1112893334_257
C730D156BC###0081805 | TT_Task | CBTC/Stage-3 SMCSW[SMTF-S] - Certificate of Compliance [Phase 1] | 25/08/2021 | 31/08/2021 | 25/08/2021 | 25/08/2021 | 0 | TK_Complete | 1112893334 | 257 | 1112893334_257
C730D147BC###0015182 | TT_Task | Stage-3 SMTF[N] - Final drawings Buffer Light Installation | 04/06/2020 | 18/06/2020 | 10/02/2020 | 19/03/2020 | 0 | TK_Complete | 1112893334 | 256 | 1112893334_256
C730D147BC###0015707 | TT_Task | As Built SMTF[N] - Buffer Light Installation Drawings | 10/06/2022 | 23/06/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 256 | 1112893334_256
C730D147BC###0015007 | TT_Task | SMTF(N) - Initial ITS 'Signalling System' (COM/SIG) | 25/02/2020 | 23/03/2020 | 12/11/2019 | 11/12/2019 | 0 | TK_Complete | 1112893334 | 255 | 1112893334_255
C730D147BC###0015021 | TT_Task | SMTF(N) - Initial ITS 'Signalling System' (SMTF-N) | 25/02/2020 | 23/03/2020 | 14/11/2019 | 11/12/2019 | 0 | TK_Complete | 1112893334 | 255 | 1112893334_255
C730D147BC###0015028 | TT_Task | SMTF(N) - Initial ITS 'Signalling System' (CCS/SIG) | 25/02/2020 | 23/03/2020 | 21/11/2019 | 18/12/2019 | 0 | TK_Complete | 1112893334 | 255 | 1112893334_255
C730D147BC###0015042 | TT_Task | SMTF(N) - Final ITS 'Signalling System' (COM/SIG) | 26/08/2020 | 08/09/2020 | 12/11/2019 | 09/12/2019 | 0 | TK_Complete | 1112893334 | 255 | 1112893334_255
C730D147BC###0015056 | TT_Task | SMTF(N) - Final ITS 'Signalling System' (SMTF-N) | 25/02/2020 | 09/03/2020 | 14/11/2019 | 11/12/2019 | 0 | TK_Complete | 1112893334 | 255 | 1112893334_255
C730D147BC###0015063 | TT_Task | SMTF(N) - Final ITS 'Signalling System' (CCS/SIG) | 25/02/2020 | 09/03/2020 | 21/11/2019 | 18/12/2019 | 0 | TK_Complete | 1112893334 | 255 | 1112893334_255
C730D157BC###0000870 | TT_Task | CBTC/Stage-3 SMTF[N] - CBTC System Exported Constraints | 27/04/2020 | 15/05/2020 | 08/04/2020 | 10/06/2020 | 0 | TK_Complete | 1112893334 | 254 | 1112893334_254
C730D157BC###0036340 | TT_Task | CBTC/Stage-2 SMCSW - CBTC System Exported Constraints | 15/07/2020 | 20/07/2020 | 08/06/2020 | 30/06/2020 | 0 | TK_Complete | 1112893334 | 254 | 1112893334_254
C730D157BC###0032063 | TT_Task | CBTC/Stage-3 SMCSW - CBTC System Exported Constraints | 27/04/2021 | 10/05/2021 | 22/03/2021 | 23/04/2021 | 0 | TK_Complete | 1112893334 | 254 | 1112893334_254
C730D157BC###0000830 | TT_Task | CBTC/Stage-3 SMTF[N] - Quantitative Risk Assessment (FTA) | 27/04/2020 | 15/05/2020 | 02/04/2020 | 07/05/2020 | 0 | TK_Complete | 1112893334 | 253 | 1112893334_253
C730D157BC###0036610 | TT_Task | CBTC/Stage-2 SMCSW - Quantitative Risk Assessment (FTA) | 27/07/2020 | 30/07/2020 | 15/06/2020 | 30/06/2020 | 0 | TK_Complete | 1112893334 | 253 | 1112893334_253
C730D157BC###N094523 | TT_Task | CBTC/Stage-3 SMCSW - Quantitative Risk Assessment (FTA) | 31/05/2021 | 18/06/2021 | 05/04/2021 | 23/04/2021 | 0 | TK_Complete | 1112893334 | 253 | 1112893334_253
C730D157BC###0000221 | TT_Task | CBTC/Stage-3 SMTF[N] - CBTC System Safety Case (Design Phase) | 11/05/2020 | 05/06/2020 | 13/04/2020 | 15/06/2020 | 0 | TK_Complete | 1112893334 | 252 | 1112893334_252
C730D157BC###0000810 | TT_Task | CBTC/Stage-3 SMTF[N] - Safety Critical Item List | 27/04/2020 | 08/05/2020 | 01/04/2020 | 06/04/2020 | 0 | TK_Complete | 1112893334 | 252 | 1112893334_252
C730D157BC###0000820 | TT_Task | CBTC/Stage-3 SMTF[N] - Deterministic Safety Assessment | 27/04/2020 | 22/05/2020 | 08/04/2020 | 15/06/2020 | 0 | TK_Complete | 1112893334 | 252 | 1112893334_252
C730D157BC###0038060 | TT_Task | CBTC/Stage-2 SMCSW - Safety Critical Item List | 03/07/2020 | 07/07/2020 | 02/06/2020 | 30/06/2020 | 0 | TK_Complete | 1112893334 | 252 | 1112893334_252
C730D157BC###0039100 | TT_Task | CBTC/Stage-2 SMCSW - CBTC Safety Case (Design Phase) | 25/06/2020 | 30/06/2020 | 12/06/2020 | 30/06/2020 | 0 | TK_Complete | 1112893334 | 252 | 1112893334_252
C730D157BC###0032072 | TT_Task | CBTC/Stage-3 SMCSW - CBTC Safety Case (Design Phase) | 27/04/2021 | 10/05/2021 | 26/04/2021 | 29/04/2021 | 0 | TK_Complete | 1112893334 | 252 | 1112893334_252
C730D157BC###N549453 | TT_Task | CBTC/Stage-3 SMCSW -CBTC System Safety Case( Intermediate) before HS Tests | 28/02/2023 | 09/03/2023 | nan | nan | 25 | TK_NotStart | 1112893334 | 252 | 1112893334_252
C730T147BC###N02245 | TT_Task | CBTC/Stage-3 SMTF[N] - Specific Safety Study | 25/08/2020 | 07/09/2020 | 10/08/2020 | 21/08/2020 | 0 | TK_Complete | 1112893334 | 252 | 1112893334_252
C730T147BC###N02305 | TT_Task | CBTC/Stage-3 SMTF[N] - CBTC System Safety Report | 08/09/2020 | 21/09/2020 | 10/08/2020 | 21/08/2020 | 0 | TK_Complete | 1112893334 | 252 | 1112893334_252
C730D147BC###0075205 | TT_Task | CBTC/Stage-3 SMTF[N] - Mechanical drawing for power supply system | 22/06/2020 | 17/07/2020 | 04/05/2020 | 13/05/2020 | 0 | TK_Complete | 1112893334 | 251 | 1112893334_251
C730D157BC###0037680 | TT_Task | CBTC/Stage-2 SMCSW - Mechanical drawing for power supply system | 27/07/2020 | 28/08/2020 | 22/05/2020 | 30/06/2020 | 0 | TK_Complete | 1112893334 | 251 | 1112893334_251
C730D157BC###0031829 | TT_Task | CBTC/Stage-3 SMCSW - Mechanical drawing for power supply system | 26/08/2021 | 22/09/2021 | 20/08/2021 | 14/10/2021 | 0 | TK_Complete | 1112893334 | 251 | 1112893334_251
C730D147BC###0075040 | TT_Task | CBTC/Stage-3 SMTF[N] - Single Line Diagram for Power Supply System | 16/12/2019 | 10/01/2020 | 02/09/2019 | 01/10/2019 | 0 | TK_Complete | 1112893334 | 250 | 1112893334_250
C730D147BC###0075145 | TT_Task | CBTC/Stage-3 SMTF[N] - Wiring diagram of Power Supply distribution | 25/05/2020 | 19/06/2020 | 04/05/2020 | 13/05/2020 | 0 | TK_Complete | 1112893334 | 250 | 1112893334_250
C730D157BC###0037670 | TT_Task | CBTC/Stage-2 SMCSW - Wiring diagram of Power Supply distribution | 27/07/2020 | 28/08/2020 | 22/05/2020 | 30/06/2020 | 0 | TK_Complete | 1112893334 | 250 | 1112893334_250
C730D167BC###0037016 | TT_Task | CBTC/Stage-2 SMCSW - Single Line Diagram for Power Supply System | 25/06/2020 | 05/08/2020 | 25/05/2020 | 30/06/2020 | 0 | TK_Complete | 1112893334 | 250 | 1112893334_250
C730D157BC###0031811 | TT_Task | CBTC/Stage-3 SMCSW - Single Line Diagram for Power Supply System | 26/08/2021 | 22/09/2021 | 20/08/2021 | 14/10/2021 | 0 | TK_Complete | 1112893334 | 250 | 1112893334_250
C730D157BC###0031820 | TT_Task | CBTC/Stage-3 SMCSW - Wiring diagram of Power Supply distribution | 26/08/2021 | 22/09/2021 | 20/08/2021 | 14/10/2021 | 0 | TK_Complete | 1112893334 | 250 | 1112893334_250
C730D157BC###N153653 | TT_Task | CBTC/Stage-3 SMCSW - Power Supply RFQ/BA/PO | 16/03/2021 | 26/04/2021 | 05/02/2021 | 09/08/2021 | 0 | TK_Complete | 1112893334 | 250 | 1112893334_250
C720D147CF###0030370 | TT_Task | Trains/Stage-2 - Design Lot 7207 submission (Bogie ; suspension) - Partial submission | 23/07/2019 | 02/09/2019 | 23/07/2019 | 31/07/2019 | 0 | TK_Complete | 1112893334 | 25 | 1112893334_25
C720D147CF###0030560 | TT_Task | Trains/Stage-2 - Design Lot 7207 submission (Bogie ; suspension) | 30/04/2020 | 13/05/2020 | 14/01/2020 | 28/01/2020 | 0 | TK_Complete | 1112893334 | 25 | 1112893334_25
C720D147CF###0021260 | TT_Task | Trains/Stage-3 - Design Lot 7207 submission (Bogie ; suspension) - Partial submission | 30/04/2020 | 13/05/2020 | 14/01/2020 | 28/01/2020 | 0 | TK_Complete | 1112893334 | 25 | 1112893334_25
C720D147CF###0021390 | TT_Task | Trains/Stage-3 - Design Lot 7207 submission (Bogie ; suspension) - Resubmission | 25/08/2020 | 07/09/2020 | 26/03/2020 | 23/04/2020 | 0 | TK_Complete | 1112893334 | 25 | 1112893334_25
C720D147CF###R07040 | TT_Task | Trains/Stage-3 - Design Lot 7207 submission (Bogie ; suspension) - Re-work | 08/02/2021 | 21/06/2021 | 08/02/2021 | 21/06/2021 | 0 | TK_Complete | 1112893334 | 25 | 1112893334_25
C730D147BC###0075035 | TT_Task | CBTC/Stage-3 SMTF[N] - PS Specification and Load Calculation | 02/12/2019 | 13/12/2019 | 02/09/2019 | 01/10/2019 | 0 | TK_Complete | 1112893334 | 249 | 1112893334_249
C730D167BC###0037000 | TT_Task | CBTC/Stage-2 SMCSW - Power Supply Specification and Load Calculation | 27/04/2020 | 22/05/2020 | 23/04/2020 | 19/06/2020 | 0 | TK_Complete | 1112893334 | 249 | 1112893334_249
C730D157BC###0031748 | TT_Task | CBTC/Stage-3 SMCSW - Power Supply Sepcification and Load Calculation Pre Final | 08/04/2021 | 05/05/2021 | 25/01/2021 | 04/02/2021 | 0 | TK_Complete | 1112893334 | 249 | 1112893334_249
C730D157BC###N399453 | TT_Task | CBTC/Stage-3 SMCSW - Power Supply Sepcification and Load Calculation Final | 26/08/2021 | 08/09/2021 | 09/08/2021 | 19/08/2021 | 0 | TK_Complete | 1112893334 | 249 | 1112893334_249
C730D147BC###0075555 | TT_Task | CBTC/Stage-3 SMTF[N] - CCTV Coverage Studies | 27/07/2020 | 21/08/2020 | 26/06/2020 | 26/06/2020 | 0 | TK_Complete | 1112893334 | 248 | 1112893334_248
C730D147BC###N885545 | TT_Task | CBTC/M2 SMTF[N] - CCTV Baseline Delivery Sheet | 06/11/2020 | 09/11/2020 | 02/11/2020 | 03/11/2020 | 0 | TK_Complete | 1112893334 | 248 | 1112893334_248
C730D147BC###N86085 | TT_Task | CBTC/M4 SMTF[N] - CCTV Baseline Delivery Sheet | 12/11/2021 | 15/11/2021 | 07/10/2021 | 08/10/2021 | 0 | TK_Complete | 1112893334 | 248 | 1112893334_248
C730D167BC###0037056 | TT_Task | CBTC/Stage-2 SMCSW - CCTV Coverage Studies - (*covered at Stage 3) | 08/06/2020 | 26/06/2020 | 22/04/2020 | 22/04/2020 | 0 | TK_Complete | 1112893334 | 248 | 1112893334_248
C730D167BC###0037088 | TT_Task | CBTC/Stage-2 SMCSW - CCTV Baseline Delivery Sheet | 02/07/2020 | 08/07/2020 | 22/06/2020 | 28/08/2020 | 0 | TK_Complete | 1112893334 | 248 | 1112893334_248
C730D157BC###0031712 | TT_Task | CBTC/Stage-3 SMCSW - CCTV Baseline Delivery Sheet | 09/05/2022 | 13/05/2022 | nan | nan | 632 | TK_NotStart | 1112893334 | 248 | 1112893334_248
C730D157BC###0038810 | TT_Task | CBTC/Stage-3 SMCSW - CCTV Coverage Studies | 25/10/2021 | 19/11/2021 | 06/07/2020 | 07/08/2020 | 0 | TK_Complete | 1112893334 | 248 | 1112893334_248
C730D147BC###0075480 | TT_Task | CBTC/Stage-3 SMTF[N] - List of Materials - CCTV | 14/07/2020 | 24/07/2020 | 04/02/2020 | 24/02/2020 | 0 | TK_Complete | 1112893334 | 247 | 1112893334_247
C730D167BC###0037032 | TT_Task | CBTC/Stage-2 SMCSW - In-saloon CCTV List of Materials | 18/05/2020 | 05/06/2020 | 03/04/2020 | 23/04/2020 | 0 | TK_Complete | 1112893334 | 247 | 1112893334_247
C730D157BC###0038410 | TT_Task | CBTC/Stage-3 SMCSW - List of Materials - CCTV | 10/08/2020 | 04/09/2020 | 27/07/2020 | 07/08/2020 | 0 | TK_Complete | 1112893334 | 247 | 1112893334_247
C730D147BC###0075360 | TT_Task | CBTC/Stage-3 SMTF[N] - CCTV SyRSAD - Subsystem Specification ; Architecture | 02/06/2020 | 12/06/2020 | 04/02/2020 | 24/02/2020 | 0 | TK_Complete | 1112893334 | 246 | 1112893334_246
C730D157BC###0087189 | TT_Task | CBTC/Stage-2 SMCSW - DCS CCTV Backbone Architecture | 01/06/2020 | 12/06/2020 | 26/03/2020 | 26/03/2020 | 0 | TK_Complete | 1112893334 | 246 | 1112893334_246
C730D167BC###0037008 | TT_Task | CBTC/Stage-2 SMCSW - In-saloon CCTV Subsystem Specification ; Architecture | 27/04/2020 | 15/05/2020 | 17/03/2020 | 01/04/2020 | 0 | TK_Complete | 1112893334 | 246 | 1112893334_246
C730D167BC###0037048 | TT_Task | CBTC/Stage-2 SMCSW - MSS -CCTV Interface Specification | 27/07/2020 | 14/08/2020 | 26/06/2020 | 26/06/2020 | 0 | TK_Complete | 1112893334 | 246 | 1112893334_246
C730D167BC###0037064 | TT_Task | CBTC/Stage-2 SMCSW - In-saloon CCTV System MMI Specification | 23/06/2020 | 13/07/2020 | 09/03/2020 | 24/03/2020 | 0 | TK_Complete | 1112893334 | 246 | 1112893334_246
C730D157BC###0021853 | TT_Task | CBTC/Stage-3 SMCSW - DCS CCTV Backbone Architecture | 28/12/2020 | 08/01/2021 | 10/08/2020 | 09/09/2020 | 0 | TK_Complete | 1112893334 | 246 | 1112893334_246
C730D157BC###0038180 | TT_Task | CBTC/Stage-3 SMCSW - In-saloon CCTV Subsystem Specification ; Architecture | 26/10/2020 | 06/11/2020 | 10/09/2020 | 16/10/2020 | 0 | TK_Complete | 1112893334 | 246 | 1112893334_246
C730D157BC###0038420 | TT_Task | CBTC/Stage-3 SMCSW - CCTV MMI Specification | 09/10/2020 | 05/11/2020 | 26/08/2020 | 14/09/2020 | 0 | TK_Complete | 1112893334 | 246 | 1112893334_246
C730D147BC###0075470 | TT_Task | CBTC/Stage-3 SMTF[N] - ATS Data Validation | 07/09/2020 | 02/10/2020 | 26/06/2020 | 24/07/2020 | 0 | TK_Complete | 1112893334 | 245 | 1112893334_245
C730D147BC###N285175 | TT_Task | CBTC/M2 SMTF[N] - ATS Data Validation | 01/02/2021 | 09/02/2021 | 13/11/2020 | 20/11/2020 | 0 | TK_Complete | 1112893334 | 245 | 1112893334_245
C730D147BC###N86465 | TT_Task | CBTC/M2 SMTF[N] - ATS Data Validation | 28/06/2021 | 29/06/2021 | 01/04/2021 | 09/04/2021 | 0 | TK_Complete | 1112893334 | 245 | 1112893334_245
C730D147BC###N86665 | TT_Task | CBTC/M2 SMTF[N] - ATS Data Validation | 25/06/2021 | 01/07/2021 | 09/06/2021 | 10/06/2021 | 0 | TK_Complete | 1112893334 | 245 | 1112893334_245
C730D147BC###N87265 | TT_Task | CBTC/M2 SMTF[N] - ATS Data Validation | 15/10/2021 | 01/11/2021 | 20/09/2021 | 29/10/2021 | 0 | TK_Complete | 1112893334 | 245 | 1112893334_245
C730D147BC###N86035 | TT_Task | CBTC/M4 SMTF[N] - ATS Data Validation | 19/11/2021 | 25/11/2021 | 30/09/2021 | 06/10/2021 | 0 | TK_Complete | 1112893334 | 245 | 1112893334_245
C730D147BC###N86845 | TT_Task | CBTC/M4 SMTF[N] - ATS Data Validation | 23/02/2022 | 25/02/2022 | 04/01/2022 | 14/01/2022 | 0 | TK_Complete | 1112893334 | 245 | 1112893334_245
C730D147BC###N87055 | TT_Task | CBTC/M4 SMTF[N] - ATS Data Validation *** N/A*** | 04/03/2022 | 10/03/2022 | 25/11/2021 | 25/11/2021 | 0 | TK_Complete | 1112893334 | 245 | 1112893334_245
C730D147BC###0075295 | TT_Task | CBTC/Stage-3 SMTF[N] - ATS Data preparation and Integration | 27/07/2020 | 04/09/2020 | 26/06/2020 | 17/07/2020 | 0 | TK_Complete | 1112893334 | 244 | 1112893334_244
C730D147BC###N1165 | TT_Task | CBTC/M2 SMTF[N] - ATS Data preparation and Integration | 10/09/2020 | 08/10/2020 | 21/09/2020 | 13/11/2020 | 0 | TK_Complete | 1112893334 | 244 | 1112893334_244
C730D147BC###N86455 | TT_Task | CBTC/M2 SMTF[N] - ATS Data preparation and Integration | 25/02/2021 | 01/03/2021 | 05/03/2021 | 31/03/2021 | 0 | TK_Complete | 1112893334 | 244 | 1112893334_244
C730D147BC###N86655 | TT_Task | CBTC/M2 SMTF[N] - ATS Data preparation and Integration | 26/04/2021 | 07/05/2021 | 01/03/2021 | 31/03/2021 | 0 | TK_Complete | 1112893334 | 244 | 1112893334_244
C730D147BC###N87255 | TT_Task | CBTC/M2 SMTF[N] - ATS Data preparation and Integration | 29/09/2021 | 14/10/2021 | 30/08/2021 | 17/09/2021 | 0 | TK_Complete | 1112893334 | 244 | 1112893334_244
C730D147BC###N86025 | TT_Task | CBTC/M4 SMTF[N] - ATS Data preparation and Integration | 05/11/2021 | 18/11/2021 | 16/09/2021 | 29/09/2021 | 0 | TK_Complete | 1112893334 | 244 | 1112893334_244
C730D147BC###N86835 | TT_Task | CBTC/M4 SMTF[N] - ATS Data preparation and Integration | 18/02/2022 | 22/02/2022 | 20/12/2021 | 31/12/2021 | 0 | TK_Complete | 1112893334 | 244 | 1112893334_244
C730D147BC###N87045 | TT_Task | CBTC/M4 SMTF[N] - ATS Data preparation and Integration *** N/A*** | 18/02/2022 | 03/03/2022 | 25/11/2021 | 25/11/2021 | 0 | TK_Complete | 1112893334 | 244 | 1112893334_244
C730D147BC###0075420 | TT_Task | CBTC/Stage-3 SMTF[N] - DCS Drawings - Depot SMTF[N] | 21/05/2020 | 18/06/2020 | 17/02/2020 | 17/03/2020 | 0 | TK_Complete | 1112893334 | 243 | 1112893334_243
C730D156BC###N561152 | TT_Task | CBTC/As-Built SMTF[N] - SMTF (North) Depot CBI Circuit Books (MS#2) ***N/A*** | 27/12/2021 | 14/01/2022 | 24/12/2021 | 24/12/2021 | 0 | TK_Complete | 1112893334 | 243 | 1112893334_243
C730D156BC###0081919 | TT_Task | CBTC/Stage-3 SMTF[N] - DCS Preliminary DCS depot Drawings | 09/06/2022 | 30/06/2022 | nan | nan | 120 | TK_NotStart | 1112893334 | 243 | 1112893334_243
C730D156BC###N582041 | TT_Task | CBTC/As-Built SMTF[N] - DCS Drawings - Depot SMTF (N) (MS#2) ***N/A*** | 27/12/2021 | 14/01/2022 | 24/12/2021 | 24/12/2021 | 0 | TK_Complete | 1112893334 | 243 | 1112893334_243
C730D157BC###0087623 | TT_Task | CBTC/Stage-2 SMCSW - DCS Depot Drawings - Southwest | 15/07/2020 | 28/07/2020 | 01/06/2020 | 16/06/2020 | 0 | TK_Complete | 1112893334 | 243 | 1112893334_243
C730D157BC###0071751 | TT_Task | CBTC/Stage-3 SMCSW - DCS Depot Drawings - Southwest | 09/09/2021 | 29/09/2021 | 15/02/2021 | 05/03/2021 | 0 | TK_Complete | 1112893334 | 243 | 1112893334_243
C730T147BC###R02255 | TT_Task | CBTC/Stage-3 SMTF[N] - DCS Drawings - Depot SMTF[N] - Rework | 17/08/2020 | 28/08/2020 | 07/08/2020 | 14/08/2020 | 0 | TK_Complete | 1112893334 | 243 | 1112893334_243
C730D147BC###0075405 | TT_Task | CBTC/Stage-3 SMTF[N] - DCS NMS IP Specification | 13/05/2020 | 22/05/2020 | 04/02/2020 | 24/02/2020 | 0 | TK_Complete | 1112893334 | 242 | 1112893334_242
C730D157BC###0087497 | TT_Task | CBTC/Stage-2 SMCSW - DCS NMS IP Specification | 27/07/2020 | 31/07/2020 | 22/04/2020 | 22/04/2020 | 0 | TK_Complete | 1112893334 | 242 | 1112893334_242
C730D157BC###0021949 | TT_Task | CBTC/Stage-3 SMCSW - DCS NMS IP Specification | 28/07/2021 | 03/08/2021 | 25/06/2021 | 30/06/2021 | 0 | TK_Complete | 1112893334 | 242 | 1112893334_242
C730D147BC###0075365 | TT_Task | CBTC/Stage-3 SMTF[N] - DCS Ethernet Port Allocations | 22/04/2020 | 13/05/2020 | 17/03/2020 | 01/04/2020 | 0 | TK_Complete | 1112893334 | 241 | 1112893334_241
C730D157BC###0087399 | TT_Task | CBTC/Stage-2 SMCSW - DCS Ethernet Port Allocation for BTN ; CCTV | 25/06/2020 | 08/07/2020 | 25/05/2020 | 25/05/2020 | 0 | TK_Complete | 1112893334 | 241 | 1112893334_241
C730D157BC###0021805 | TT_Task | CBTC/Stage-3 SMCSW - DCS Ethernet Port Allocation for BTN ; CCTV | 25/05/2021 | 31/05/2021 | 01/04/2021 | 11/05/2021 | 0 | TK_Complete | 1112893334 | 241 | 1112893334_241
C730D147BC###0075350 | TT_Task | CBTC/Stage-3 SMTF[N] - DCS Radio Network Layout Specification | 22/04/2020 | 13/05/2020 | 16/01/2020 | 03/02/2020 | 0 | TK_Complete | 1112893334 | 240 | 1112893334_240
C730D157BC###0087098 | TT_Task | CBTC/Stage-2 SMCSW - DCS Radio Network Layout Specification | 08/05/2020 | 28/05/2020 | 13/04/2020 | 28/04/2020 | 0 | TK_Complete | 1112893334 | 240 | 1112893334_240
C730D157BC###0039350 | TT_Task | CBTC/Stage-3 SMCSW - DCS Radio Network Layout | 12/02/2021 | 05/03/2021 | 27/07/2020 | 18/08/2020 | 0 | TK_Complete | 1112893334 | 240 | 1112893334_240
C720D147CF###0030350 | TT_Task | Trains/Stage-2 - Design Lot 7206 submission (Traction, Pantograph, Auxiliary Supply ; Brakes) - Partial submission | 23/07/2019 | 02/09/2019 | 23/07/2019 | 15/08/2019 | 0 | TK_Complete | 1112893334 | 24 | 1112893334_24
C720D147CF###0030550 | TT_Task | Trains/Stage-2 - Design Lot 7206 submission (Traction, Pantograph, Auxiliary Supply ; Brakes) | 25/02/2020 | 09/03/2020 | 14/01/2020 | 28/01/2020 | 0 | TK_Complete | 1112893334 | 24 | 1112893334_24
C720D147CF###0021200 | TT_Task | Trains/Stage-3 - Design Lot 7206 submission (Traction, Pantograph, Auxiliary Supply ; Brakes) - Partial submission | 05/12/2019 | 24/01/2020 | 05/12/2019 | 24/01/2020 | 0 | TK_Complete | 1112893334 | 24 | 1112893334_24
C720D147CF###0021410 | TT_Task | Trains/Stage-3 - Design Lot 7206 submission (Traction, Pantograph, Auxiliary Supply ; Brakes) - Resubmission | 25/08/2020 | 07/09/2020 | 26/03/2020 | 22/04/2020 | 0 | TK_Complete | 1112893334 | 24 | 1112893334_24
C720D147CF###R07060 | TT_Task | Trains/Stage-3 - Design Lot 7206 submission (Traction, Pantograph, Auxiliary Supply ; Brakes) - Re-work | 08/02/2021 | 19/02/2021 | 08/02/2021 | 13/07/2021 | 0 | TK_Complete | 1112893334 | 24 | 1112893334_24
C730D147BC###0075520 | TT_Task | CBTC/Stage-3 SMTF[N] - MSS Data Validation | 06/07/2020 | 31/07/2020 | 22/04/2020 | 22/04/2020 | 0 | TK_Complete | 1112893334 | 239 | 1112893334_239
C730D147BC###0075510 | TT_Task | CBTC/Stage-3 SMTF[N] - DCS Data Validation | 17/08/2020 | 11/09/2020 | 30/06/2020 | 31/07/2020 | 0 | TK_Complete | 1112893334 | 239 | 1112893334_239
C730D147BC###N485565 | TT_Task | CBTC/M2 SMTF[N] - DCS Data Validation | 02/11/2020 | 06/11/2020 | 24/10/2020 | 10/11/2020 | 0 | TK_Complete | 1112893334 | 239 | 1112893334_239
C730D147BC###N86105 | TT_Task | CBTC/M4 SMTF[N] - DCS Data Validation | 12/11/2021 | 18/11/2021 | 23/09/2021 | 29/09/2021 | 0 | TK_Complete | 1112893334 | 239 | 1112893334_239
C730D147BC###N85505 | TT_Task | CBTC/M4 SMTF[N] - MSS Data Validation | 05/11/2021 | 11/11/2021 | 07/10/2021 | 13/10/2021 | 0 | TK_Complete | 1112893334 | 239 | 1112893334_239
C730D157BC###0022207 | TT_Task | CBTC/Stage-3 SMCSW - MSS Data Validation | 08/08/2022 | 12/08/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 239 | 1112893334_239
C730D147BC###0075450 | TT_Task | CBTC/Stage-3 SMTF[N] - MSS Server Configuration | 01/06/2020 | 03/07/2020 | 22/04/2020 | 22/04/2020 | 0 | TK_Complete | 1112893334 | 238 | 1112893334_238
C730D147BC###N085065 | TT_Task | CBTC/Stage-3 SMTF[N] - MSS Server Configuration (Internal) | 10/11/2021 | 30/11/2021 | 16/09/2021 | 06/10/2021 | 0 | TK_Complete | 1112893334 | 238 | 1112893334_238
C730D157BC###0022225 | TT_Task | CBTC/Stage-3 SMCSW - MSS Server Configuration | 15/08/2022 | 09/09/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 238 | 1112893334_238
C730D147BC###0075445 | TT_Task | CBTC/Stage-3 SMTF[N] - MSS Data Preparation | 01/06/2020 | 26/06/2020 | 22/04/2020 | 22/04/2020 | 0 | TK_Complete | 1112893334 | 237 | 1112893334_237
C730D147BC###0075415 | TT_Task | CBTC/Stage-3 SMTF[N] - DCS Data Preparation | 25/06/2020 | 15/07/2020 | 28/04/2020 | 27/07/2020 | 0 | TK_Complete | 1112893334 | 237 | 1112893334_237
C730D147BC###N385555 | TT_Task | CBTC/M2 SMTF[N] - DCS Data Preparation | 10/09/2020 | 16/09/2020 | 21/09/2020 | 23/10/2020 | 0 | TK_Complete | 1112893334 | 237 | 1112893334_237
C730D147BC###N86095 | TT_Task | CBTC/M4 SMTF[N] - DCS Data Preparation | 05/11/2021 | 11/11/2021 | 16/09/2021 | 22/09/2021 | 0 | TK_Complete | 1112893334 | 237 | 1112893334_237
C730D147BC###N85495 | TT_Task | CBTC/M4 SMTF[N] - MSS Data Preparation | 10/11/2021 | 16/11/2021 | 16/09/2021 | 22/09/2021 | 0 | TK_Complete | 1112893334 | 237 | 1112893334_237
C730D147BC###0010858 | TT_Task | CBTC/Stage-2 SMCSW - ATC Data Preparation | 24/08/2020 | 11/09/2020 | 22/04/2020 | 22/04/2020 | 0 | TK_Complete | 1112893334 | 237 | 1112893334_237
C730D157BC###0087518 | TT_Task | CBTC/Stage-2 SMCSW - DCS Data Prep | 27/07/2020 | 31/07/2020 | 25/06/2020 | 03/07/2020 | 0 | TK_Complete | 1112893334 | 237 | 1112893334_237
C730D157BC###0022153 | TT_Task | CBTC/Stage-3 SMCSW - MSS Data Preparation | 18/07/2022 | 05/08/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 237 | 1112893334_237
C730D157BC###0021979 | TT_Task | CBTC/Stage-3 SMCSW - DCS Data Preparation | 09/05/2022 | 03/06/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 237 | 1112893334_237
C730D157BC###0039700 | TT_Task | CBTC/Stage-3 SMCSW - ATS Data preparation and Integration | 03/05/2022 | 13/06/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 237 | 1112893334_237
C730D147BC###0075395 | TT_Task | CBTC/Stage-3 SMTF[N] - CBI Circuit Book for TT+ Road 30-35 + DSER2 and CER2 - Stage 1 (MS1; MS2) | 22/06/2020 | 17/08/2020 | 14/02/2020 | 02/04/2020 | 0 | TK_Complete | 1112893334 | 236 | 1112893334_236
C730D147BC###0075505 | TT_Task | CBTC/Stage-3 SMTF[N] - CBI Circuit Book for Axle counter Boundary DSER1 and CER1 - Stage 1 (MS1 ; MS2) | 27/07/2020 | 17/08/2020 | 02/04/2020 | 21/04/2020 | 0 | TK_Complete | 1112893334 | 236 | 1112893334_236
C730D147BC###0075540 | TT_Task | CBTC/Stage-3 SMTF[N] - CBI Circuit Book Cable Layout for MS3 ; MS4 | 27/07/2020 | 14/08/2020 | 22/06/2020 | 30/06/2020 | 0 | TK_Complete | 1112893334 | 236 | 1112893334_236
C730D147BC###0075575 | TT_Task | CBTC/Stage-3 SMTF[N] - CBI Circuit Book Cubicle Layout for MS4 | 17/08/2020 | 04/09/2020 | 01/07/2020 | 24/09/2020 | 0 | TK_Complete | 1112893334 | 236 | 1112893334_236
C730D147BC###0075590 | TT_Task | CBTC/Stage-3 SMTF[N] - CBI Circuit Book for Remaining Stabling Roads 24-29 - Stage 2 (*covered above) | 24/08/2020 | 21/09/2020 | 22/04/2020 | 22/04/2020 | 0 | TK_Complete | 1112893334 | 236 | 1112893334_236
C730T147BC###R02265 | TT_Task | CBTC/Stage-3 SMTF[N] - CBI Circuit Book for Existing TT Decommissioning (Road 27) - Rework | 17/08/2020 | 28/08/2020 | 07/08/2020 | 14/08/2020 | 0 | TK_Complete | 1112893334 | 236 | 1112893334_236
C730D147BC###0075495 | TT_Task | CBTC/Stage-3 SMTF[N] - CBI Baseline Delivery Sheet | 22/06/2020 | 29/06/2020 | 22/04/2020 | 28/08/2020 | 0 | TK_Complete | 1112893334 | 235 | 1112893334_235
C730D147BC###0075580 | TT_Task | CBTC/Stage-3 SMTF[N] - MSS Baseline Delivery Sheet | 03/08/2020 | 28/08/2020 | 22/04/2020 | 22/04/2020 | 0 | TK_Complete | 1112893334 | 235 | 1112893334_235
C730D147BC###0075545 | TT_Task | CBTC/Stage-3 SMTF[N] - DCS Baseline Delivery Sheet | 12/08/2020 | 18/08/2020 | 27/07/2020 | 28/08/2020 | 0 | TK_Complete | 1112893334 | 235 | 1112893334_235
C730D147BC###N85125 | TT_Task | CBTC/M2 SMTF[N] - CBI Baseline Delivery Sheet | 13/11/2020 | 16/11/2020 | 04/11/2020 | 06/11/2020 | 0 | TK_Complete | 1112893334 | 235 | 1112893334_235
C730D147BC###N585575 | TT_Task | CBTC/M2 SMTF[N] - DCS Baseline Delivery Sheet | 01/01/2021 | 07/01/2021 | 11/11/2020 | 12/11/2020 | 0 | TK_Complete | 1112893334 | 235 | 1112893334_235
C730D147BC###N86415 | TT_Task | CBTC/M2 SMTF[N] - CBI Baseline Delivery Sheet | 01/07/2021 | 01/07/2021 | 23/03/2021 | 26/03/2021 | 0 | TK_Complete | 1112893334 | 235 | 1112893334_235
C730D147BC###N86615 | TT_Task | CBTC/M2 SMTF[N] - CBI Baseline Delivery Sheet | 13/07/2021 | 14/07/2021 | 10/06/2021 | 11/06/2021 | 0 | TK_Complete | 1112893334 | 235 | 1112893334_235
C730D147BC###N87215 | TT_Task | CBTC/M2 SMTF[N] - CBI Baseline Delivery Sheet | 28/09/2021 | 29/09/2021 | 20/09/2021 | 24/09/2021 | 0 | TK_Complete | 1112893334 | 235 | 1112893334_235
C730D147BC###N85985 | TT_Task | CBTC/M4 SMTF[N] - CBI Baseline Delivery Sheet | 07/10/2021 | 08/10/2021 | 07/10/2021 | 08/10/2021 | 0 | TK_Complete | 1112893334 | 235 | 1112893334_235
C730D147BC###N86115 | TT_Task | CBTC/M4 SMTF[N] - DCS Baseline Delivery Sheet | 29/10/2021 | 04/11/2021 | 30/09/2021 | 01/10/2021 | 0 | TK_Complete | 1112893334 | 235 | 1112893334_235
C730D147BC###N85515 | TT_Task | CBTC/M4 SMTF[N] - MSS Baseline Delivery Sheet | 12/11/2021 | 15/11/2021 | 14/10/2021 | 15/10/2021 | 0 | TK_Complete | 1112893334 | 235 | 1112893334_235
C730D147BC###N86795 | TT_Task | CBTC/M4 SMTF[N] - CBI Baseline Delivery Sheet | 02/03/2022 | 03/03/2022 | 12/01/2022 | 14/01/2022 | 0 | TK_Complete | 1112893334 | 235 | 1112893334_235
C730D147BC###N87005 | TT_Task | CBTC/M4 SMTF[N] - CBI Baseline Delivery Sheet *** N/A*** | 25/11/2021 | 26/11/2021 | 25/11/2021 | 25/11/2021 | 0 | TK_Complete | 1112893334 | 235 | 1112893334_235
C730D157BC###0087595 | TT_Task | CBTC/Stage-2 SMCSW - CBI Baseline Delivery Sheet | 23/07/2020 | 29/07/2020 | 01/06/2020 | 28/08/2020 | 0 | TK_Complete | 1112893334 | 235 | 1112893334_235
C730D157BC###0022279 | TT_Task | CBTC/Stage-3 SMCSW - CBI Baseline Delivery Sheet | 13/09/2022 | 03/10/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 235 | 1112893334_235
C730D147BC###0075475 | TT_Task | CBTC/Stage-3 SMTF[N] - CBI Data Report Generation | 13/07/2020 | 20/07/2020 | 22/04/2020 | 23/04/2020 | 0 | TK_Complete | 1112893334 | 234 | 1112893334_234
C730D147BC###N85115 | TT_Task | CBTC/M2 SMTF[N] - CBI Data Report Generation | 06/11/2020 | 12/11/2020 | 30/10/2020 | 03/11/2020 | 0 | TK_Complete | 1112893334 | 234 | 1112893334_234
C730D147BC###N86405 | TT_Task | CBTC/M2 SMTF[N] - CBI Data Report Generation | 30/06/2021 | 30/06/2021 | 19/03/2021 | 23/03/2021 | 0 | TK_Complete | 1112893334 | 234 | 1112893334_234
C730D147BC###N86605 | TT_Task | CBTC/M2 SMTF[N] - CBI Data Report Generation | 06/07/2021 | 12/07/2021 | 10/06/2021 | 10/06/2021 | 0 | TK_Complete | 1112893334 | 234 | 1112893334_234
C730D147BC###N87205 | TT_Task | CBTC/M2 SMTF[N] - CBI Data Report Generation | 13/10/2021 | 15/10/2021 | 13/09/2021 | 16/09/2021 | 0 | TK_Complete | 1112893334 | 234 | 1112893334_234
C730D147BC###N85975 | TT_Task | CBTC/M4 SMTF[N] - CBI Data Report Generation | 05/11/2021 | 11/11/2021 | 30/09/2021 | 06/10/2021 | 0 | TK_Complete | 1112893334 | 234 | 1112893334_234
C730D147BC###N86785 | TT_Task | CBTC/M4 SMTF[N] - CBI Data Report Generation | 28/02/2022 | 01/03/2022 | 10/01/2022 | 11/01/2022 | 0 | TK_Complete | 1112893334 | 234 | 1112893334_234
C730D147BC###N86995 | TT_Task | CBTC/M4 SMTF[N] - CBI Data Report Generation *** N/A*** | 25/11/2021 | 01/12/2021 | 25/11/2021 | 25/11/2021 | 0 | TK_Complete | 1112893334 | 234 | 1112893334_234
C730D157BC###0087560 | TT_Task | CBTC/Stage-2 SMCSW - CBI Data Report Generation | 07/09/2020 | 11/09/2020 | 22/04/2020 | 22/04/2020 | 0 | TK_Complete | 1112893334 | 234 | 1112893334_234
C730D157BC###0022243 | TT_Task | CBTC/Stage-3 SMCSW - CBI Data Report Generation | 02/09/2022 | 12/09/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 234 | 1112893334_234
C730D147BC###0075370 | TT_Task | CBTC/Stage-2 SMTF[N] - CBI I/O Mapping | 22/06/2020 | 06/07/2020 | 06/04/2020 | 17/04/2020 | 0 | TK_Complete | 1112893334 | 233 | 1112893334_233
C730D147BC###N085075 | TT_Task | CBTC/Stage-2 SMTF[N] - CBI I/O Mapping | 25/09/2020 | 08/10/2020 | 25/09/2020 | 07/10/2020 | 0 | TK_Complete | 1112893334 | 233 | 1112893334_233
C730D157BC###0087343 | TT_Task | CBTC/Stage-2 SMCSW - CBI I/O Mapping | 15/06/2020 | 19/06/2020 | 22/04/2020 | 22/04/2020 | 0 | TK_Complete | 1112893334 | 233 | 1112893334_233
C730D157BC###0022189 | TT_Task | CBTC/Stage-3 SMCSW - CBI I/O Mapping | 01/08/2022 | 12/08/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 233 | 1112893334_233
C730D147BC###0075260 | TT_Task | CBTC/Stage-2 SMTF[N] - CBI I/O Matrix for Drawing | 22/04/2020 | 06/05/2020 | 31/01/2020 | 13/02/2020 | 0 | TK_Complete | 1112893334 | 232 | 1112893334_232
C730D157BC###0087266 | TT_Task | CBTC/Stage-2 SMCSW - CBI I/O Matrix for Drawing | 23/07/2020 | 29/07/2020 | 01/06/2020 | 30/06/2020 | 0 | TK_Complete | 1112893334 | 232 | 1112893334_232
C730D157BC###0022159 | TT_Task | CBTC/Stage-3 SMCSW - CBI I/O Matrix for Drawing | 18/07/2022 | 29/07/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 232 | 1112893334_232
C730D147BC###0075385 | TT_Task | CBTC/Stage-3 SMTF[N] - CBI Functional Gap Analysis | 21/05/2020 | 27/05/2020 | 09/03/2020 | 25/03/2020 | 0 | TK_Complete | 1112893334 | 231 | 1112893334_231
C730D147BC###0075455 | TT_Task | CBTC/Stage-3 SMTF[N] - CBI Detail Gap Analysis | 11/06/2020 | 17/06/2020 | 09/03/2020 | 25/03/2020 | 0 | TK_Complete | 1112893334 | 231 | 1112893334_231
C730D147BC###0010808 | TT_Task | CBTC/Stage-2 SMCSW - GAP Analysis | 27/04/2020 | 15/05/2020 | 15/04/2020 | 31/07/2020 | 0 | TK_Complete | 1112893334 | 231 | 1112893334_231
C730D157BC###0087070 | TT_Task | CBTC/Stage-2 SMCSW - CBI Functional Gap Analysis | 25/05/2020 | 12/06/2020 | 18/05/2020 | 30/06/2020 | 0 | TK_Complete | 1112893334 | 231 | 1112893334_231
C730D157BC###0087210 | TT_Task | CBTC/Stage-2 SMCSW - CBI Detailed Gap Analysis | 09/07/2020 | 22/07/2020 | 01/06/2020 | 30/06/2020 | 0 | TK_Complete | 1112893334 | 231 | 1112893334_231
C730D157BC###0031865 | TT_Task | CBTC/Stage-3 SMCSW - Operability Gap Analysis | 29/04/2021 | 09/06/2021 | 07/09/2020 | 18/09/2020 | 0 | TK_Complete | 1112893334 | 231 | 1112893334_231
C730D147BC###0075515 | TT_Task | CBTC/Stage-3 SMTF[N] - ATC Baseline Delivery Sheet | 15/06/2020 | 22/06/2020 | 22/04/2020 | 25/05/2020 | 0 | TK_Complete | 1112893334 | 230 | 1112893334_230
C730D147BC###N95155 | TT_Task | CBTC/M2 SMTF[N] - ATC Baseline Delivery Sheet | 26/10/2020 | 27/10/2020 | 12/10/2020 | 06/11/2020 | 0 | TK_Complete | 1112893334 | 230 | 1112893334_230
C730D147BC###N385185 | TT_Task | CBTC/M2 SMTF[N] - ATS Baseline Delivery Sheet | 10/02/2021 | 11/02/2021 | 16/11/2020 | 23/11/2020 | 0 | TK_Complete | 1112893334 | 230 | 1112893334_230
C730D147BC###N86445 | TT_Task | CBTC/M2 SMTF[N] - ATC Baseline Delivery Sheet | 29/06/2021 | 29/06/2021 | 26/03/2021 | 31/03/2021 | 0 | TK_Complete | 1112893334 | 230 | 1112893334_230
C730D147BC###N86475 | TT_Task | CBTC/M2 SMTF[N] - ATS Baseline Delivery Sheet | 30/06/2021 | 30/06/2021 | 12/04/2021 | 26/04/2021 | 0 | TK_Complete | 1112893334 | 230 | 1112893334_230
C730D147BC###N86645 | TT_Task | CBTC/M2 SMTF[N] - ATC Baseline Delivery Sheet | 25/06/2021 | 28/06/2021 | 10/06/2021 | 11/06/2021 | 0 | TK_Complete | 1112893334 | 230 | 1112893334_230
C730D147BC###N86675 | TT_Task | CBTC/M2 SMTF[N] - ATS Baseline Delivery Sheet | 02/07/2021 | 05/07/2021 | 10/06/2021 | 11/06/2021 | 0 | TK_Complete | 1112893334 | 230 | 1112893334_230
C730D147BC###N87245 | TT_Task | CBTC/M2 SMTF[N] - ATC Baseline Delivery Sheet | 14/10/2021 | 19/10/2021 | 13/09/2021 | 24/09/2021 | 0 | TK_Complete | 1112893334 | 230 | 1112893334_230
C730D147BC###N87275 | TT_Task | CBTC/M2 SMTF[N] - ATS Baseline Delivery Sheet | 27/10/2021 | 27/10/2021 | 27/10/2021 | 29/10/2021 | 0 | TK_Complete | 1112893334 | 230 | 1112893334_230
C730D147BC###N86015 | TT_Task | CBTC/M4 SMTF[N] - ATC Baseline Delivery Sheet | 03/11/2021 | 04/11/2021 | 30/09/2021 | 01/10/2021 | 0 | TK_Complete | 1112893334 | 230 | 1112893334_230
C730D147BC###N86045 | TT_Task | CBTC/M4 SMTF[N] - ATS Baseline Delivery Sheet | 26/11/2021 | 29/11/2021 | 07/10/2021 | 08/10/2021 | 0 | TK_Complete | 1112893334 | 230 | 1112893334_230
C730D147BC###N86825 | TT_Task | CBTC/M4 SMTF[N] - ATC Baseline Delivery Sheet | 24/02/2022 | 25/02/2022 | 12/01/2022 | 14/01/2022 | 0 | TK_Complete | 1112893334 | 230 | 1112893334_230
C730D147BC###N86855 | TT_Task | CBTC/M4 SMTF[N] - ATS Baseline Delivery Sheet | 28/02/2022 | 01/03/2022 | 17/01/2022 | 24/01/2022 | 0 | TK_Complete | 1112893334 | 230 | 1112893334_230
C730D147BC###N87035 | TT_Task | CBTC/M4 SMTF[N] - ATC Baseline Delivery Sheet *** N/A*** | 25/11/2021 | 26/11/2021 | 25/11/2021 | 25/11/2021 | 0 | TK_Complete | 1112893334 | 230 | 1112893334_230
C730D147BC###N87065 | TT_Task | CBTC/M4 SMTF[N] - ATS Baseline Delivery Sheet *** N/A*** | 11/03/2022 | 14/03/2022 | 25/11/2021 | 25/11/2021 | 0 | TK_Complete | 1112893334 | 230 | 1112893334_230
C720D147CF###0030340 | TT_Task | Trains/Stage-2 - Design Lot 7205 submission (Doors detrainment door ; HVAC) | 23/07/2019 | 02/09/2019 | 23/07/2019 | 16/08/2019 | 0 | TK_Complete | 1112893334 | 23 | 1112893334_23
C720D147CF###0021240 | TT_Task | Trains/Stage-3 - Design Lot 7205 submission (Doors, detrainment door ; HVAC) - Partial submission | 25/02/2020 | 06/04/2020 | 05/12/2019 | 27/01/2020 | 0 | TK_Complete | 1112893334 | 23 | 1112893334_23
C720D147CF###0021470 | TT_Task | Trains/Stage-3 - Design Lot 7205 submission (Doors, detrainment door ; HVAC) - Resubmission | 25/08/2020 | 07/09/2020 | 26/03/2020 | 22/04/2020 | 0 | TK_Complete | 1112893334 | 23 | 1112893334_23
C730D147BC###0075500 | TT_Task | CBTC/Stage-3 SMTF[N] - ATC Data Validation For Passengers Trains and Trackside | 27/07/2020 | 10/08/2020 | 22/04/2020 | 23/04/2020 | 0 | TK_Complete | 1112893334 | 229 | 1112893334_229
C730D147BC###N75145 | TT_Task | CBTC/M2 SMTF[N] - ATC Data Validation For Passengers Trains and Trackside | 30/09/2020 | 07/10/2020 | 30/09/2020 | 12/10/2020 | 0 | TK_Complete | 1112893334 | 229 | 1112893334_229
C730D147BC###N86435 | TT_Task | CBTC/M2 SMTF[N] - ATC Data Validation For Passengers Trains and Trackside | 28/06/2021 | 29/06/2021 | 16/03/2021 | 25/03/2021 | 0 | TK_Complete | 1112893334 | 229 | 1112893334_229
C730D147BC###N86635 | TT_Task | CBTC/M2 SMTF[N] - ATC Data Validation For Passengers Trains and Trackside | 03/05/2021 | 07/05/2021 | 01/03/2021 | 15/03/2021 | 0 | TK_Complete | 1112893334 | 229 | 1112893334_229
C730D147BC###N87235 | TT_Task | CBTC/M2 SMTF[N] - ATC Data Validation For Passengers Trains and Trackside | 07/10/2021 | 13/10/2021 | 06/09/2021 | 10/09/2021 | 0 | TK_Complete | 1112893334 | 229 | 1112893334_229
C730D147BC###N86005 | TT_Task | CBTC/M4 SMTF[N] - ATC Data Validation For Passengers Trains and Trackside | 12/11/2021 | 18/11/2021 | 23/09/2021 | 29/09/2021 | 0 | TK_Complete | 1112893334 | 229 | 1112893334_229
C730D147BC###N86815 | TT_Task | CBTC/M4 SMTF[N] - ATC Data Validation For Passengers Trains and Trackside | 23/02/2022 | 25/02/2022 | 04/01/2022 | 11/01/2022 | 0 | TK_Complete | 1112893334 | 229 | 1112893334_229
C730D147BC###N87025 | TT_Task | CBTC/M4 SMTF[N] - ATC Data Validation For Passengers Trains and Trackside *** N/A*** | 25/02/2022 | 03/03/2022 | 25/11/2021 | 25/11/2021 | 0 | TK_Complete | 1112893334 | 229 | 1112893334_229
C730D157BC###0022201 | TT_Task | CBTC/Stage-3 SMCSW - ATC Data Validation For Passengers Trains and Trackside | 08/08/2022 | 02/09/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 229 | 1112893334_229
C730D147BC###0075435 | TT_Task | CBTC/Stage-3 SMTF[N] - ATC Data Prep For Passengers Trains and Trackside | 06/07/2020 | 27/07/2020 | 22/04/2020 | 23/04/2020 | 0 | TK_Complete | 1112893334 | 228 | 1112893334_228
C730D147BC###N85135 | TT_Task | CBTC/M2 SMTF[N] - ATC Data Prep For Passengers Trains and Trackside | 10/09/2020 | 16/09/2020 | 21/09/2020 | 29/09/2020 | 0 | TK_Complete | 1112893334 | 228 | 1112893334_228
C730D147BC###N86425 | TT_Task | CBTC/M2 SMTF[N] - ATC Data Prep For Passengers Trains and Trackside | 05/03/2021 | 09/03/2021 | 05/03/2021 | 15/03/2021 | 0 | TK_Complete | 1112893334 | 228 | 1112893334_228
C730D147BC###N86625 | TT_Task | CBTC/M2 SMTF[N] - ATC Data Prep For Passengers Trains and Trackside | 26/04/2021 | 30/04/2021 | 01/03/2021 | 15/03/2021 | 0 | TK_Complete | 1112893334 | 228 | 1112893334_228
C730D147BC###N87225 | TT_Task | CBTC/M2 SMTF[N] - ATC Data Prep For Passengers Trains and Trackside | 29/09/2021 | 06/10/2021 | 30/08/2021 | 03/09/2021 | 0 | TK_Complete | 1112893334 | 228 | 1112893334_228
C730D147BC###N85995 | TT_Task | CBTC/M4 SMTF[N] - ATC Data Prep For Passengers Trains and Trackside | 05/11/2021 | 11/11/2021 | 16/09/2021 | 22/09/2021 | 0 | TK_Complete | 1112893334 | 228 | 1112893334_228
C730D147BC###N86805 | TT_Task | CBTC/M4 SMTF[N] - ATC Data Prep For Passengers Trains and Trackside | 18/02/2022 | 22/02/2022 | 20/12/2021 | 31/12/2021 | 0 | TK_Complete | 1112893334 | 228 | 1112893334_228
C730D147BC###N87015 | TT_Task | CBTC/M4 SMTF[N] - ATC Data Prep For Passengers Trains and Trackside *** N/A*** | 25/11/2021 | 01/12/2021 | 25/11/2021 | 25/11/2021 | 0 | TK_Complete | 1112893334 | 228 | 1112893334_228
C730D157BC###0022147 | TT_Task | CBTC/Stage-3 SMCSW - ATC Data Prep For Passengers Trains and Trackside | 18/07/2022 | 05/08/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 228 | 1112893334_228
C730D147BC###0075390 | TT_Task | CBTC/Stage-3 SMTF[N] - Beacons Layout | 22/06/2020 | 06/07/2020 | 13/03/2020 | 03/04/2020 | 0 | TK_Complete | 1112893334 | 227 | 1112893334_227
C730D147BC###0010840 | TT_Task | CBTC/Stage-2 SMCSW - Beacons Layout | 25/05/2020 | 12/06/2020 | 24/04/2020 | 30/06/2020 | 0 | TK_Complete | 1112893334 | 227 | 1112893334_227
C730D157BC###0021787 | TT_Task | CBTC/Stage-3 SMCSW - Beacons Layout | 25/02/2021 | 17/03/2021 | 28/01/2021 | 08/02/2021 | 0 | TK_Complete | 1112893334 | 227 | 1112893334_227
C730D147BC###0075325 | TT_Task | CBTC/Stage-3 SMTF[N] - ATC Beacons Subdivision Rules | 21/05/2020 | 04/06/2020 | 13/03/2020 | 22/04/2020 | 0 | TK_Complete | 1112893334 | 226 | 1112893334_226
C730D147BC###0010830 | TT_Task | CBTC/Stage-2 SMCSW - ATC Beacons Subdivision Rules | 11/05/2020 | 22/05/2020 | 13/03/2020 | 22/04/2020 | 0 | TK_Complete | 1112893334 | 226 | 1112893334_226
C730D157BC###0021745 | TT_Task | CBTC/Stage-3 SMCSW - ATC Beacons Subdivision Rules | 25/03/2021 | 14/04/2021 | 25/01/2021 | 26/01/2021 | 0 | TK_Complete | 1112893334 | 226 | 1112893334_226
C730D147BC###0075290 | TT_Task | CBTC/Stage-3 SMTF[N] - ZC and LC Parameters specification | 01/06/2020 | 12/06/2020 | 13/04/2020 | 22/04/2020 | 0 | TK_Complete | 1112893334 | 225 | 1112893334_225
C730D147BC###N485055 | TT_Task | CBTC/Stage-3 SMTF[N] - ZC and LC Parameters specification (Internal) | 25/09/2020 | 08/10/2020 | 25/09/2020 | 07/10/2020 | 0 | TK_Complete | 1112893334 | 225 | 1112893334_225
C730D147BC###0010854 | TT_Task | CBTC/Stage-2 SMCSW - ZC and LC Parameters specification (*covered in Stage 3) | 24/08/2020 | 04/09/2020 | 24/04/2020 | 24/04/2020 | 0 | TK_Complete | 1112893334 | 225 | 1112893334_225
C730D157BC###0022093 | TT_Task | CBTC/Stage-3 SMCSW - ZC and LC Parameters specification | 27/06/2022 | 15/07/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 225 | 1112893334_225
C730D147BC###0075125 | TT_Task | CBTC/Stage-3 SMTF[N] - ATC CC Requirement Specification SyPRS | 25/03/2020 | 14/04/2020 | 23/03/2020 | 23/04/2020 | 0 | TK_Complete | 1112893334 | 224 | 1112893334_224
C730D147BC###0075335 | TT_Task | CBTC/Stage-3 SMTF[N] - ATS Parameters Specification | 25/06/2020 | 22/07/2020 | 25/05/2020 | 25/05/2020 | 0 | TK_Complete | 1112893334 | 224 | 1112893334_224
C730D147BC###0075465 | TT_Task | CBTC/Stage-3 SMTF[N] - ATS HMI Specification | 13/07/2020 | 07/08/2020 | 20/04/2020 | 29/04/2020 | 0 | TK_Complete | 1112893334 | 224 | 1112893334_224
C730D157BC###0036240 | TT_Task | CBTC/Stage-2 SMCSW - ATS HMI Specification | 25/05/2020 | 19/06/2020 | 18/05/2020 | 25/05/2020 | 0 | TK_Complete | 1112893334 | 224 | 1112893334_224
C730D157BC###0037980 | TT_Task | CBTC/Stage-2 SMCSW - ATS Materials Specification | 27/07/2020 | 21/08/2020 | 18/05/2020 | 30/06/2020 | 0 | TK_Complete | 1112893334 | 224 | 1112893334_224
C730D157BC###0038050 | TT_Task | CBTC/Stage-2 SMCSW - ATS Parameters Specification | 02/07/2020 | 22/07/2020 | 15/06/2020 | 30/06/2020 | 0 | TK_Complete | 1112893334 | 224 | 1112893334_224
C730D157BC###N349453 | TT_Task | CBTC/Stage-3 SMCSW - A22 Milestone Design documentation submission of SoD Technical requirement for Phase 1 (See Steps) | 30/04/2021 | 05/10/2021 | 26/11/2020 | 30/04/2021 | 0 | TK_Complete | 1112893334 | 224 | 1112893334_224
C730D157BC###0038590 | TT_Task | CBTC/Stage-3 SMCSW - ATS HMI Specification | 14/01/2021 | 03/02/2021 | 01/12/2020 | 15/12/2020 | 0 | TK_Complete | 1112893334 | 224 | 1112893334_224
C730D157BC###0038620 | TT_Task | CBTC/Stage-3 SMCSW - ATS Matrials Specification (Closed, Merged with ATS Products Datasheets book) | 25/02/2021 | 24/03/2021 | 25/01/2021 | 25/01/2021 | 0 | TK_Complete | 1112893334 | 224 | 1112893334_224
C730D157BC###0039550 | TT_Task | CBTC/Stage-3 SMCSW - ATS Parameters Specification | 25/02/2021 | 17/03/2021 | 25/01/2021 | 29/01/2021 | 0 | TK_Complete | 1112893334 | 224 | 1112893334_224
C730D147BC###0075625 | TT_Task | CBTC/Stage-3 SMTF[N] - Verification and Validation Report | 28/09/2020 | 05/10/2020 | 26/06/2020 | 28/08/2020 | 0 | TK_Complete | 1112893334 | 223 | 1112893334_223
C730D147BC###0075460 | TT_Task | CBTC/Stage-3 SMTF[N] - CBI Data Validation | 06/07/2020 | 13/07/2020 | 22/04/2020 | 23/04/2020 | 0 | TK_Complete | 1112893334 | 223 | 1112893334_223
C730D147BC###0010882 | TT_Task | CBTC/Stage-2 SMCSW - Verification and Validation Report | 07/12/2020 | 18/12/2020 | 16/03/2020 | 30/03/2020 | 0 | TK_Complete | 1112893334 | 223 | 1112893334_223
C730D147BC###0010868 | TT_Task | CBTC/Stage-2 SMCSW - ATC Data Validation | 14/09/2020 | 25/09/2020 | 22/04/2020 | 22/04/2020 | 0 | TK_Complete | 1112893334 | 223 | 1112893334_223
C730D157BC###0087525 | TT_Task | CBTC/Stage-2 SMCSW - CBI Data Validation | 31/08/2020 | 04/09/2020 | 22/04/2020 | 22/04/2020 | 0 | TK_Complete | 1112893334 | 223 | 1112893334_223
C730D157BC###0087567 | TT_Task | CBTC/Stage-2 SMCSW - DCS Data Validation | 27/07/2020 | 31/07/2020 | 06/07/2020 | 31/07/2020 | 0 | TK_Complete | 1112893334 | 223 | 1112893334_223
C730D157BC###0022339 | TT_Task | CBTC/Stage-3 SMCSW - Verification and Validation Report | 08/11/2021 | 19/11/2021 | 01/02/2021 | 10/02/2021 | 0 | TK_Complete | 1112893334 | 223 | 1112893334_223
C730D157BC###0022231 | TT_Task | CBTC/Stage-3 SMCSW - CBI Data Validation | 24/08/2022 | 01/09/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 223 | 1112893334_223
C730D157BC###0022063 | TT_Task | CBTC/Stage-3 SMCSW - DCS Data Validation | 06/06/2022 | 15/07/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 223 | 1112893334_223
C730D157BC###0040230 | TT_Task | CBTC/Stage-3 SMCSW - ATS Data Validation | 14/06/2022 | 25/07/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 223 | 1112893334_223
C730D147BC###0075615 | TT_Task | CBTC/Stage-3 SMTF[N] - FIVP Testing | 17/08/2020 | 18/09/2020 | 26/06/2020 | 28/08/2020 | 0 | TK_Complete | 1112893334 | 222 | 1112893334_222
C730D147BC###0010866 | TT_Task | CBTC/Stage-2 SMCSW - FIVP Testing | 17/08/2020 | 11/09/2020 | 26/06/2020 | 10/07/2020 | 0 | TK_Complete | 1112893334 | 222 | 1112893334_222
C730D157BC###0022249 | TT_Task | CBTC/Stage-3 SMCSW - CC INV Testing - Ready for FIVP City | 05/09/2022 | 07/10/2022 | nan | nan | 40 | TK_NotStart | 1112893334 | 222 | 1112893334_222
C730D157BC###0022291 | TT_Task | CBTC/Stage-3 SMCSW - FIVP Testing - Ready for FIVP City | 13/09/2022 | 14/10/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 222 | 1112893334_222
C730D157BC###0022321 | TT_Task | CBTC/Stage-3 SMCSW - FIVP Testing - Ready for FIVP NW + City | 17/10/2022 | 11/11/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 222 | 1112893334_222
C730D156BC###0081769 | TT_Task | SMCSW[City] - Baseline - 2.0.1.3 City Stage 3 - Baseline for Data for FIVP Testing | 14/11/2022 | 09/12/2022 | 01/03/2021 | 31/03/2021 | 0 | TK_Complete | 1112893334 | 222 | 1112893334_222
C730D147BC###0075570 | TT_Task | CBTC/Stage-3 SMTF[N] - CC INV Testing | 17/08/2020 | 18/09/2020 | 26/06/2020 | 30/06/2020 | 0 | TK_Complete | 1112893334 | 221 | 1112893334_221
C730D147BC###0075600 | TT_Task | CBTC/Stage-3 SMTF[N] - CC INV Test Report | 21/09/2020 | 25/09/2020 | 26/06/2020 | 30/06/2020 | 0 | TK_Complete | 1112893334 | 221 | 1112893334_221
C730D147BC###0075425 | TT_Task | CBTC/Stage-3 SMTF[N] - DCS BTN INV Procedure | 21/05/2020 | 01/06/2020 | 25/02/2020 | 25/03/2020 | 0 | TK_Complete | 1112893334 | 221 | 1112893334_221
C730D147BC###0010876 | TT_Task | CBTC/Stage-2 SMCSW - CC INV Testing | 14/09/2020 | 09/10/2020 | 26/06/2020 | 10/07/2020 | 0 | TK_Complete | 1112893334 | 221 | 1112893334_221
C730D157BC###0087448 | TT_Task | CBTC/Stage-2 SMCSW - DCS INV Test Procedure | 25/08/2020 | 31/08/2020 | 24/08/2020 | 28/08/2020 | 0 | TK_Complete | 1112893334 | 221 | 1112893334_221
C730D157BC###0022255 | TT_Task | CBTC/Stage-3 SMCSW - DCS INV Functional Testing and Report | 29/08/2022 | 14/10/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 221 | 1112893334_221
C730D147BC###0075560 | TT_Task | CBTC/Stage-3 SMTF[N] - Factory Integration and Validation Platform Test Procedures (Draft) | 17/08/2020 | 28/08/2020 | 26/06/2020 | 26/06/2020 | 0 | TK_Complete | 1112893334 | 220 | 1112893334_220
C730D147BC###0075620 | TT_Task | CBTC/Stage-3 SMTF[N] - Factory Integration and Validation Platform Test Report | 21/09/2020 | 25/09/2020 | 26/06/2020 | 26/06/2020 | 0 | TK_Complete | 1112893334 | 220 | 1112893334_220
C730D147BC###0010818 | TT_Task | CBTC/Stage-2 SMCSW - Factory Integration and Validation Platform Test Plan | 13/04/2020 | 01/05/2020 | 03/02/2020 | 26/02/2020 | 0 | TK_Complete | 1112893334 | 220 | 1112893334_220
C730D147BC###0010836 | TT_Task | CBTC/Stage-2 SMCSW - Factory Integration and Validation Platform Test Procedures | 04/05/2020 | 22/05/2020 | 27/01/2020 | 20/02/2020 | 0 | TK_Complete | 1112893334 | 220 | 1112893334_220
C730D147BC###0010878 | TT_Task | CBTC/Stage-2 SMCSW - Factory Integration and Validation Platform Test Report | 27/10/2020 | 09/11/2020 | 09/03/2020 | 23/03/2020 | 0 | TK_Complete | 1112893334 | 220 | 1112893334_220
C730D157BC###0021907 | TT_Task | CBTC/Stage-3 SMCSW - Factory Integration and Validation Platform Test Plan [Updated] | 12/02/2021 | 05/03/2021 | 10/08/2020 | 25/08/2020 | 0 | TK_Complete | 1112893334 | 220 | 1112893334_220
C730D157BC###0021955 | TT_Task | CBTC/Stage-3 SMCSW - Factory Integration and Validation Platform Test Report | 05/03/2021 | 26/03/2021 | 17/08/2020 | 27/08/2020 | 0 | TK_Complete | 1112893334 | 220 | 1112893334_220
C730D157BC###0022033 | TT_Task | CBTC/Stage-3 SMCSW - Factory Integration and Validation Platform Test Procedures [Updated] | 25/03/2021 | 14/04/2021 | 27/07/2020 | 05/08/2020 | 0 | TK_Complete | 1112893334 | 220 | 1112893334_220
C720D147CF###0030330 | TT_Task | Trains/Stage-2 - Design Lot 7201 submission (Trains) - Partial submission | 23/07/2019 | 02/09/2019 | 23/07/2019 | 19/08/2019 | 0 | TK_Complete | 1112893334 | 22 | 1112893334_22
C720D147CF###0030360 | TT_Task | Trains/Stage-2 - Design Lot 7204 submission (TMS ; communication system) | 23/07/2019 | 02/09/2019 | 23/07/2019 | 15/08/2019 | 0 | TK_Complete | 1112893334 | 22 | 1112893334_22
C720D147CF###0030380 | TT_Task | Trains/Stage-2 - Design Lot 7209 submission (RAMS) | 23/07/2019 | 02/09/2019 | 23/07/2019 | 09/08/2019 | 0 | TK_Complete | 1112893334 | 22 | 1112893334_22
C720D147CF###0030400 | TT_Task | Trains/Stage-2 - Design Lot 7208 submission (System interface) | 23/07/2019 | 02/09/2019 | 23/07/2019 | 02/09/2019 | 0 | TK_Complete | 1112893334 | 22 | 1112893334_22
C720D147CF###0030540 | TT_Task | Trains/Stage-2 - Design Lot 7201 submission (Trains) | 25/02/2020 | 09/03/2020 | 14/01/2020 | 28/01/2020 | 0 | TK_Complete | 1112893334 | 22 | 1112893334_22
C720D147CF###0021190 | TT_Task | Trains/Stage-3 - Design Lot 7208 submission (System interface) - Partial submission | 18/03/2020 | 31/03/2020 | 17/01/2020 | 09/04/2020 | 0 | TK_Complete | 1112893334 | 22 | 1112893334_22
C720D147CF###0021230 | TT_Task | Trains/Stage-3 - Design Lot 7201 submission (Trains) - Partial submission | 25/02/2020 | 09/03/2020 | 14/01/2020 | 28/01/2020 | 0 | TK_Complete | 1112893334 | 22 | 1112893334_22
C720D147CF###0021250 | TT_Task | Trains/Stage-3 - Design Lot 7204 submission (TMS ; communication system) - Partial submission | 25/02/2020 | 06/04/2020 | 05/12/2019 | 28/01/2020 | 0 | TK_Complete | 1112893334 | 22 | 1112893334_22
C720D147CF###0021270 | TT_Task | Trains/Stage-3 - Design Lot 7209 submission (RAMS) - Partial submission | 25/02/2020 | 06/04/2020 | 05/12/2019 | 28/01/2020 | 0 | TK_Complete | 1112893334 | 22 | 1112893334_22
C720D147CF###0021380 | TT_Task | Trains/Stage-3 - Design Lot 7201 submission (Trains) - Resubmission | 25/08/2020 | 07/09/2020 | 26/03/2020 | 28/04/2020 | 0 | TK_Complete | 1112893334 | 22 | 1112893334_22
C720D147CF###0021420 | TT_Task | Trains/Stage-3 - Design Lot 7208 submission (System interface) - Resubmission | 17/09/2020 | 30/09/2020 | 31/07/2020 | 14/08/2020 | 0 | TK_Complete | 1112893334 | 22 | 1112893334_22
C720D147CF###0021480 | TT_Task | Trains/Stage-3 - Design Lot 7204 submission (TMS ; communication system) - Resubmission | 25/03/2020 | 28/05/2020 | 28/02/2020 | 24/04/2020 | 0 | TK_Complete | 1112893334 | 22 | 1112893334_22
C720D147CF###0021490 | TT_Task | Trains/Stage-3 - Design Lot 7209 submission (RAMS) - Resubmission | 25/03/2020 | 28/05/2020 | 14/02/2020 | 24/04/2020 | 0 | TK_Complete | 1112893334 | 22 | 1112893334_22
C730D147BC###0075195 | TT_Task | CBTC/Stage-3 SMTF[N] - SyDB - MS1 | 25/05/2020 | 26/06/2020 | 11/05/2020 | 21/05/2020 | 0 | TK_Complete | 1112893334 | 219 | 1112893334_219
C730D147BC###0075285 | TT_Task | CBTC/Stage-3 SMTF[N] - SyDB (System Database) - MS1 | 25/06/2020 | 15/07/2020 | 25/05/2020 | 11/09/2020 | 0 | TK_Complete | 1112893334 | 219 | 1112893334_219
C730D147BC###N87165 | TT_Task | CBTC/M2 SMTF[N] - SyDB-1 4.3.0.1 | 08/09/2021 | 21/09/2021 | 09/08/2021 | 27/08/2021 | 0 | TK_Complete | 1112893334 | 219 | 1112893334_219
C730D147BC###0010850 | TT_Task | CBTC/Stage-2 SMCSW - SyDB (System Database) | 25/08/2020 | 14/09/2020 | 27/07/2020 | 03/08/2020 | 0 | TK_Complete | 1112893334 | 219 | 1112893334_219
C730D157BC###0027369 | TT_Task | CBTC/Stage-3 SMCSW - SyDB (System Database) | 06/06/2022 | 24/06/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 219 | 1112893334_219
C730D147BC###0075060 | TT_Task | CBTC/Stage-3 SMTF[N] - Real Time Issues (RTI) | 25/02/2020 | 04/03/2020 | 31/10/2019 | 13/03/2020 | 0 | TK_Complete | 1112893334 | 218 | 1112893334_218
C730D147BC###0010842 | TT_Task | CBTC/Stage-2 SMCSW - Real Time Issues (RTI) | 08/06/2020 | 03/07/2020 | 16/04/2020 | 30/06/2020 | 0 | TK_Complete | 1112893334 | 218 | 1112893334_218
C730D157BC###0027315 | TT_Task | CBTC/Stage-3 SMCSW - Real Time Issues (RTI) | 18/04/2022 | 06/05/2022 | 14/03/2022 | nan | 0 | TK_Active | 1112893334 | 218 | 1112893334_218
C730D147BC###0075020 | TT_Task | CBTC/Stage-3 SMTF[N] - SyCR | 02/12/2019 | 27/12/2019 | 10/07/2019 | 06/04/2020 | 0 | TK_Complete | 1112893334 | 217 | 1112893334_217
C730D147BC###0075025 | TT_Task | CBTC/Stage-3 SMTF[N] - SyDT | 12/02/2020 | 10/03/2020 | 01/08/2019 | 09/04/2020 | 0 | TK_Complete | 1112893334 | 217 | 1112893334_217
C730D147BC###0075045 | TT_Task | CBTC/Stage-3 SMTF[N] - North Extension Specification (SyOCD, Test Track) Version D - Plan A | 11/03/2020 | 15/04/2020 | 16/09/2019 | 06/03/2020 | 0 | TK_Complete | 1112893334 | 217 | 1112893334_217
C730D147BC###0075255 | TT_Task | CBTC/Stage-3 SMTF[N] - CBI SyHW | 22/04/2020 | 06/05/2020 | 05/02/2020 | 10/02/2020 | 0 | TK_Complete | 1112893334 | 217 | 1112893334_217
C730D147BC###0075355 | TT_Task | CBTC/Stage-3 SMTF[N] - BTN specification/SyHW | 22/04/2020 | 01/05/2020 | 04/02/2020 | 24/02/2020 | 0 | TK_Complete | 1112893334 | 217 | 1112893334_217
C730T147BC###NR2335 | TT_Task | CBTC/Stage-3 SMTF[N] ? Depot Extension Specification - Rework | 26/10/2020 | 20/11/2020 | 10/09/2020 | 30/09/2020 | 0 | TK_Complete | 1112893334 | 217 | 1112893334_217
C730T147BC###R02275 | TT_Task | CBTC/Stage-3 SMTF[N] - System Operational Context Description - Rework | 17/08/2020 | 28/08/2020 | 07/08/2020 | 21/08/2020 | 0 | TK_Complete | 1112893334 | 217 | 1112893334_217
C730T147BC###R02325 | TT_Task | CBTC/Stage-3 SMTF[N] - Update of PRD - Rework | 08/09/2020 | 21/09/2020 | 10/08/2020 | 21/08/2020 | 0 | TK_Complete | 1112893334 | 217 | 1112893334_217
C730D147BC###0075015 | TT_Task | CBTC/Stage-3 SMTF[N] - SyPROs (Project Options) | 31/12/2019 | 08/01/2020 | 10/07/2019 | 10/07/2019 | 0 | TK_Complete | 1112893334 | 216 | 1112893334_216
C730D147BC###0010786 | TT_Task | CBTC/Stage-2 SMCSW - SyPROs (Project Options) | 18/11/2019 | 06/12/2019 | 11/09/2019 | 25/05/2020 | 0 | TK_Complete | 1112893334 | 216 | 1112893334_216
C730D157BC###0027027 | TT_Task | CBTC/Stage-3 SMCSW - SyPROs (Project Options) | 07/09/2020 | 18/09/2020 | 01/07/2020 | nan | 0 | TK_Active | 1112893334 | 216 | 1112893334_216
C730D157BC###0031775 | TT_Task | CBTC/Stage-3 SMCSW - REX on Existing Project | 16/04/2021 | 27/05/2021 | 28/12/2020 | 29/03/2021 | 0 | TK_Complete | 1112893334 | 216 | 1112893334_216
C730D147BC###0075010 | TT_Task | CBTC/Stage-3 SMTF[N] - PHA Tracability to RSAD (Draft Excel) | 15/10/2019 | 06/01/2020 | 01/07/2019 | 04/10/2019 | 0 | TK_Complete | 1112893334 | 215 | 1112893334_215
C730D147BC###0075400 | TT_Task | CBTC/Stage-3 SMTF[N] - CBI Data Definition | 22/06/2020 | 29/06/2020 | 22/04/2020 | 23/04/2020 | 0 | TK_Complete | 1112893334 | 215 | 1112893334_215
C730D147BC###0075430 | TT_Task | CBTC/Stage-3 SMTF[N] - CBI Data Preparation | 29/06/2020 | 06/07/2020 | 22/04/2020 | 23/04/2020 | 0 | TK_Complete | 1112893334 | 215 | 1112893334_215
C730D157BC###0087084 | TT_Task | CBTC/Stage-2 SMCSW - CBI Data Definition | 27/04/2020 | 01/05/2020 | 22/04/2020 | 22/04/2020 | 0 | TK_Complete | 1112893334 | 215 | 1112893334_215
C730D157BC###0087490 | TT_Task | CBTC/Stage-2 SMCSW - CBI Data Preparation | 24/08/2020 | 28/08/2020 | 22/04/2020 | 22/04/2020 | 0 | TK_Complete | 1112893334 | 215 | 1112893334_215
C730D157BC###0022219 | TT_Task | CBTC/Stage-3 SMCSW - CBI Data Preparation | 15/08/2022 | 23/08/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 215 | 1112893334_215
C730D147BC###0075375 | TT_Task | CBTC/Stage-3 SMTF[N] - CBI Discussion with Supplier - Axle counter (PT3 Frausher) | 22/06/2020 | 06/07/2020 | 17/04/2020 | 05/06/2020 | 0 | TK_Complete | 1112893334 | 214 | 1112893334_214
C730D147BC###0010824 | TT_Task | CBTC/Stage-2 SMCSW - CBI Discussion with Supplier - Axle counter (PT3 Frausher) | 27/07/2020 | 14/08/2020 | 26/06/2020 | 30/06/2020 | 0 | TK_Complete | 1112893334 | 214 | 1112893334_214
C730D147BC###0075065 | TT_Task | CBTC/Stage-3 SMTF[N] - PDC Cubicle Design Connections Terminals From Benning | 25/03/2020 | 05/05/2020 | 16/03/2020 | 08/05/2020 | 0 | TK_Complete | 1112893334 | 213 | 1112893334_213
C730D147BC###0075070 | TT_Task | CBTC/Stage-3 SMTF[N] - UPS Cubicle Design Connections Terminals From Benning | 25/03/2020 | 05/05/2020 | 16/03/2020 | 08/05/2020 | 0 | TK_Complete | 1112893334 | 213 | 1112893334_213
C730D147BC###0010832 | TT_Task | CBTC/Stage-2 SMCSW - PDC Cubicle Design Connections Terminals From Benning (8 Stations) | 27/07/2020 | 04/09/2020 | 22/05/2020 | 30/06/2020 | 0 | TK_Complete | 1112893334 | 213 | 1112893334_213
C730D147BC###0010834 | TT_Task | CBTC/Stage-2 SMCSW - UPS Cubicle Design Connection Terminals From Benning (8 Stations) | 27/07/2020 | 04/09/2020 | 22/05/2020 | 30/06/2020 | 0 | TK_Complete | 1112893334 | 213 | 1112893334_213
C730D147BC###0075275 | TT_Task | Stage2 SMTF[N] closure of comments Room Layout (DSER2) | 25/03/2020 | 09/04/2020 | 25/03/2020 | 13/04/2020 | 0 | TK_Complete | 1112893334 | 212 | 1112893334_212
C730D147BC###0015518 | TT_Task | Stage3 [SMTF-N] Customer closure of comments DSER2 | 10/08/2020 | 25/08/2020 | 30/06/2020 | 30/06/2020 | 0 | TK_Complete | 1112893334 | 212 | 1112893334_212
C730D147BC###0015588 | TT_Task | Stage3 [SMTF-N] Customer closure of comments DSER1 modification | 10/08/2020 | 25/08/2020 | 30/06/2020 | 30/06/2020 | 0 | TK_Complete | 1112893334 | 212 | 1112893334_212
C730D157BC###0027321 | TT_Task | CBTC/Stage-2 SMCSW [City] - Alstom closure of comments SMTF[S] DSER | 31/08/2020 | 15/09/2020 | 17/07/2020 | 17/07/2020 | 0 | TK_Complete | 1112893334 | 212 | 1112893334_212
C730D157BC###0027327 | TT_Task | CBTC/Stage-2 SMCSW [SMTF-S] - Alstom closure of comments DSER [Depot-S] | 31/08/2020 | 15/09/2020 | 17/07/2020 | 17/07/2020 | 0 | TK_Complete | 1112893334 | 212 | 1112893334_212
C730D156BC###0081718 | TT_Task | CBTC/Stage-3 SMCSW[SMTF-S] - Customer closure of comments Final Room Layout Drawing DSER3 (Depot) | 02/09/2021 | 17/09/2021 | 03/08/2021 | 25/08/2021 | 0 | TK_Complete | 1112893334 | 212 | 1112893334_212
C730D147BC###0075265 | TT_Task | Stage2 SMTF[N] closure of comments Key Switches Installation | 25/02/2020 | 11/03/2020 | 06/01/2020 | 22/05/2020 | 0 | TK_Complete | 1112893334 | 211 | 1112893334_211
C730D147BC###0015602 | TT_Task | Stage3 [SMTF-N] Customer closure of comments Key Switches Installation | 26/08/2020 | 10/09/2020 | 30/06/2020 | 30/06/2020 | 0 | TK_Complete | 1112893334 | 211 | 1112893334_211
C730D157BC###0027183 | TT_Task | CBTC/Stage-2 SMCSW [City] - Alstom closure of comments Key Switches Installation | 31/08/2020 | 15/09/2020 | 14/07/2020 | 14/07/2020 | 0 | TK_Complete | 1112893334 | 211 | 1112893334_211
C730D157BC###0027333 | TT_Task | CBTC/Stage-2 SMCSW [SMTF-S] - Alstom closure of comments Key Switches Installation | 25/08/2020 | 09/09/2020 | 30/07/2020 | 30/07/2020 | 0 | TK_Complete | 1112893334 | 211 | 1112893334_211
C730D157BC###0012257 | TT_Task | CBTC/Stage-3 SMCSW[City] - Customer closure of comments Key Switches Installation | 31/08/2021 | 15/09/2021 | 02/08/2021 | 25/08/2021 | 0 | TK_Complete | 1112893334 | 211 | 1112893334_211
C730D156BC###0081784 | TT_Task | CBTC/Stage-3 SMCSW[SMTF-S] - Customer closure of comments Final Drawings Key Switches Installation | 30/08/2021 | 14/09/2021 | 05/08/2021 | 25/08/2021 | 0 | TK_Complete | 1112893334 | 211 | 1112893334_211
C730D147BC###0075240 | TT_Task | Stage2 SMTF[N] closure of comments Track Plan ; Cable Duct Routes [Depot] | 25/02/2020 | 11/03/2020 | 03/02/2020 | 24/04/2020 | 0 | TK_Complete | 1112893334 | 210 | 1112893334_210
C730D147BC###0015609 | TT_Task | Stage3 [SMTF-N] Customer closure of comments Track Plan ; Cable Duct Routes [Depot] | 17/08/2020 | 01/09/2020 | 30/06/2020 | 30/06/2020 | 0 | TK_Complete | 1112893334 | 210 | 1112893334_210
C730D157BC###0027261 | TT_Task | CBTC/Stage-2 SMCSW [City] - Alstom closure of comments Track Plan ; Cable Duct Routes [ML] | 29/09/2020 | 15/10/2020 | 29/07/2020 | 29/07/2020 | 0 | TK_Complete | 1112893334 | 210 | 1112893334_210
C730D157BC###0027309 | TT_Task | CBTC/Stage-2 SMCSW [SMTF-S] - Alstom closure of comments Track Plan ; Cable Duct Routes [Depot] | 29/09/2020 | 15/10/2020 | 30/07/2020 | 30/07/2020 | 0 | TK_Complete | 1112893334 | 210 | 1112893334_210
C730D157BC###0012245 | TT_Task | CBTC/Stage-3 SMCSW[City] - Customer closure of comments Track Plan ; Cable Duct Routes [ML] | 26/04/2021 | 11/05/2021 | 25/12/2020 | 25/12/2020 | 0 | TK_Complete | 1112893334 | 210 | 1112893334_210
C730D156BC###0081790 | TT_Task | CBTC/Stage-3 SMCSW[SMTF-S] - Customer closure of comments Final Drawings Track Plan ; Cable Duct Routes [Depot] | 10/05/2021 | 25/05/2021 | 25/12/2020 | 25/12/2020 | 0 | TK_Complete | 1112893334 | 210 | 1112893334_210
C720D147CF###0030310 | TT_Task | Trains/Stage-2 - Design Lot 7202 submission (Carbody ; exterior, gangway, coupler) - Partial submission | 23/07/2019 | 02/09/2019 | 23/07/2019 | 01/08/2019 | 0 | TK_Complete | 1112893334 | 21 | 1112893334_21
C720D147CF###0030320 | TT_Task | Trains/Stage-2 - Design Lot 7203 submission (Saloon Interior, cab front ; train attendant desk) | 23/07/2019 | 02/09/2019 | 23/07/2019 | 01/08/2019 | 0 | TK_Complete | 1112893334 | 21 | 1112893334_21
C720D147CF###0030530 | TT_Task | Trains/Stage-2 - Design Lot 7202 submission (Carbody ; exterior, gangway, coupler) | 25/02/2020 | 09/03/2020 | 14/01/2020 | 28/01/2020 | 0 | TK_Complete | 1112893334 | 21 | 1112893334_21
C720D147CF###0021210 | TT_Task | Trains/Stage-3 - Design Lot 7202 submission (Carbody ; exterior, gangway, coupler) - Partial submission | 25/02/2020 | 06/04/2020 | 05/12/2019 | 28/01/2020 | 0 | TK_Complete | 1112893334 | 21 | 1112893334_21
C720D147CF###0021400 | TT_Task | Trains/Stage-3 - Design Lot 7202 submission (Carbody ; exterior, gangway, coupler) - Resubmission | 27/07/2020 | 07/08/2020 | 20/02/2020 | 29/04/2020 | 0 | TK_Complete | 1112893334 | 21 | 1112893334_21
C720D147CF###R07050 | TT_Task | Trains/Stage-3 - Design Lot 7202 submission (Carbody ; exterior, gangway, coupler) - Re-work | 30/06/2021 | 13/07/2021 | 08/02/2021 | 30/06/2021 | 0 | TK_Complete | 1112893334 | 21 | 1112893334_21
C730D147BC###0075210 | TT_Task | Stage2 SMTF[N] closure of comments DCS Antenna/Boxes Installation | 25/02/2020 | 11/03/2020 | 31/01/2020 | 22/05/2020 | 0 | TK_Complete | 1112893334 | 209 | 1112893334_209
C730D147BC###0015553 | TT_Task | Stage3 [SMTF-N] Customer closure of comments DCS antenna installation | 10/08/2020 | 25/08/2020 | 30/06/2020 | 30/06/2020 | 0 | TK_Complete | 1112893334 | 209 | 1112893334_209
C730D157BC###0027201 | TT_Task | CBTC/Stage-2 SMCSW [City] - Alstom closure of comments DCS Boxes/ Antenna / OLX Installation | 29/09/2020 | 15/10/2020 | 17/07/2020 | 20/07/2020 | 0 | TK_Complete | 1112893334 | 209 | 1112893334_209
C730D157BC###0027273 | TT_Task | CBTC/Stage-2 SMCSW [SMTF-S] - Alstom closure of comments DCS Boxes/ Antenna / OLX Installation | 29/09/2020 | 15/10/2020 | 17/07/2020 | 20/07/2020 | 0 | TK_Complete | 1112893334 | 209 | 1112893334_209
C730D157BC###0012254 | TT_Task | CBTC/Stage-3 SMCSW[City] - Customer closure of comments DCS Boxes/ Antenna / OLX | 31/08/2021 | 15/09/2021 | 27/07/2021 | 25/08/2021 | 0 | TK_Complete | 1112893334 | 209 | 1112893334_209
C730D156BC###0081787 | TT_Task | CBTC/Stage-3 SMCSW[SMTF-S] - Customer closure of comments DCS Boxes/ Antenna / OLX Installation | 30/08/2021 | 14/09/2021 | 03/08/2021 | 25/08/2021 | 0 | TK_Complete | 1112893334 | 209 | 1112893334_209
C730D147BC###0075170 | TT_Task | Stage2 SMTF[N] closure of comments Axle Counter Installation | 25/02/2020 | 11/03/2020 | 06/01/2020 | 27/01/2020 | 0 | TK_Complete | 1112893334 | 208 | 1112893334_208
C730D147BC###0015406 | TT_Task | Stage3 [SMTF-N] Customer closure of comments Axle Counter Installation | 11/06/2020 | 26/06/2020 | 06/04/2020 | 06/04/2020 | 0 | TK_Complete | 1112893334 | 208 | 1112893334_208
C730D157BC###0027123 | TT_Task | CBTC/Stage-2 SMCSW [City] - Alstom closure of comments Axle Counter Installation | 27/07/2020 | 11/08/2020 | 26/05/2020 | 26/05/2020 | 0 | TK_Complete | 1112893334 | 208 | 1112893334_208
C730D157BC###0027207 | TT_Task | CBTC/Stage-2 SMCSW [SMTF-S] - Alstom closure of comments Axle Counter Installation | 04/09/2020 | 21/09/2020 | 04/05/2020 | 12/05/2020 | 0 | TK_Complete | 1112893334 | 208 | 1112893334_208
C730D157BC###0012251 | TT_Task | CBTC/Stage-3 SMCSW[City] - Customer closure of comments Axle Counter Installation | 31/08/2021 | 15/09/2021 | 04/08/2021 | 25/08/2021 | 0 | TK_Complete | 1112893334 | 208 | 1112893334_208
C730D156BC###0081781 | TT_Task | CBTC/Stage-3 SMCSW[SMTF-S] - Customer closure of comments Final Drawings Axle Counter Installation | 02/09/2021 | 17/09/2021 | 05/08/2021 | 25/08/2021 | 0 | TK_Complete | 1112893334 | 208 | 1112893334_208
C730D147BC###0075165 | TT_Task | Stage2 SMTF[N] closure of comments Balise Installation | 25/02/2020 | 11/03/2020 | 06/01/2020 | 08/01/2020 | 0 | TK_Complete | 1112893334 | 207 | 1112893334_207
C730D147BC###0075175 | TT_Task | Stage2 SMTF[N] closure of comments Marker Board Installation | 25/02/2020 | 11/03/2020 | 06/01/2020 | 01/04/2020 | 0 | TK_Complete | 1112893334 | 207 | 1112893334_207
C730D147BC###0075180 | TT_Task | Stage2 SMTF[N] closure of comments Buffer Stop Installation | 25/02/2020 | 11/03/2020 | 06/01/2020 | 02/03/2020 | 0 | TK_Complete | 1112893334 | 207 | 1112893334_207
C730D147BC###0075230 | TT_Task | Stage2 SMTF[N] closure of comments SAB Installation | 25/03/2020 | 09/04/2020 | 25/03/2020 | 22/05/2020 | 0 | TK_Complete | 1112893334 | 207 | 1112893334_207
C730D147BC###0075235 | TT_Task | Stage2 SMTF[N] closure of comments Point Machines Installation | 25/02/2020 | 11/03/2020 | 10/01/2020 | 19/02/2020 | 0 | TK_Complete | 1112893334 | 207 | 1112893334_207
C730D147BC###0075270 | TT_Task | Stage2 SMTF[N] closure of comments PPI Installation | 24/01/2020 | 11/02/2020 | 24/01/2020 | 05/02/2020 | 0 | TK_Complete | 1112893334 | 207 | 1112893334_207
C730D147BC###0015266 | TT_Task | Stage3 [SMTF-N] Customer closure of comments Balise Installation | 01/06/2020 | 17/06/2020 | 06/05/2020 | 06/05/2020 | 0 | TK_Complete | 1112893334 | 207 | 1112893334_207
C730D147BC###0015392 | TT_Task | Stage3 [SMTF-N] Customer closure of comments BS Installation | 01/06/2020 | 17/06/2020 | 03/04/2020 | 03/04/2020 | 0 | TK_Complete | 1112893334 | 207 | 1112893334_207
C730D147BC###0015455 | TT_Task | Stage3 [SMTF-N] Customer closure of comments Point Machine Installation | 10/08/2020 | 25/08/2020 | 30/06/2020 | 30/06/2020 | 0 | TK_Complete | 1112893334 | 207 | 1112893334_207
C730D147BC###0015504 | TT_Task | Stage3 [SMTF-N] Customer closure of comments PPI Installation | 01/06/2020 | 17/06/2020 | 06/04/2020 | 06/04/2020 | 0 | TK_Complete | 1112893334 | 207 | 1112893334_207
C730D147BC###0015511 | TT_Task | Stage3 [SMTF-N] Customer closure of comments MB Installation | 10/08/2020 | 25/08/2020 | 30/06/2020 | 30/06/2020 | 0 | TK_Complete | 1112893334 | 207 | 1112893334_207
C730D147BC###0015616 | TT_Task | Stage3 [SMTF-N] Customer closure of comments SAB Installation | 10/08/2020 | 25/08/2020 | 30/06/2020 | 30/06/2020 | 0 | TK_Complete | 1112893334 | 207 | 1112893334_207
C730D147BC###0075115 | TT_Task | Stage2 SMTF[N] Installation Design customer review Point Machines Installation | 25/02/2020 | 30/03/2020 | 02/12/2019 | 09/01/2020 | 0 | TK_Complete | 1112893334 | 206 | 1112893334_206
C730D147BC###0075160 | TT_Task | Stage2 SMTF[N] Installation Design customer review Room Layout (DSER2) | 25/02/2020 | 30/03/2020 | 16/12/2019 | 13/02/2020 | 0 | TK_Complete | 1112893334 | 206 | 1112893334_206
C730D147BC###0015350 | TT_Task | Stage3 [SMTF-N] Installation design customer review Point Machine Installation | 25/05/2020 | 29/06/2020 | 12/05/2020 | 30/06/2020 | 0 | TK_Complete | 1112893334 | 206 | 1112893334_206
C730D147BC###0015441 | TT_Task | Stage3 [SMTF-N] Installation design customer review DSER2 | 25/05/2020 | 29/06/2020 | 19/05/2020 | 30/06/2020 | 0 | TK_Complete | 1112893334 | 206 | 1112893334_206
C730D147BC###0015497 | TT_Task | Stage3 [SMTF-N] Installation design customer review DSER1 modification | 25/05/2020 | 29/06/2020 | 19/05/2020 | 30/06/2020 | 0 | TK_Complete | 1112893334 | 206 | 1112893334_206
C730D147BC###0012184 | TT_Task | Stage2 [System-wide] Initial Method Statement Key Switches Installation | 04/05/2020 | 22/05/2020 | 16/12/2019 | 16/01/2020 | 0 | TK_Complete | 1112893334 | 205 | 1112893334_205
C730D147BC###0075315 | TT_Task | Stage2 System-wide Initial Method statement customer review Key Switches Installation | 25/02/2020 | 30/03/2020 | 17/01/2020 | 03/02/2020 | 0 | TK_Complete | 1112893334 | 205 | 1112893334_205
C730D147BC###0015210 | TT_Task | Stage-3 System-wide Final Method Statement Key Switches Installation | 25/03/2020 | 16/04/2020 | 17/02/2020 | 05/05/2020 | 0 | TK_Complete | 1112893334 | 205 | 1112893334_205
C730D147BC###0015322 | TT_Task | Stage-3 System-wide customer review Final Method Statement Key Switches Installation | 25/05/2020 | 29/06/2020 | 05/05/2020 | 25/05/2020 | 0 | TK_Complete | 1112893334 | 205 | 1112893334_205
C730D147BC###0012177 | TT_Task | Stage2 [System-wide] Initial Method Statement Drill ; Fix Installation | 04/05/2020 | 22/05/2020 | 16/12/2019 | 17/01/2020 | 0 | TK_Complete | 1112893334 | 204 | 1112893334_204
C730D147BC###0075310 | TT_Task | Stage2 System-wide Initial Method statement customer review Drill ; Fix Installation | 25/02/2020 | 30/03/2020 | 20/01/2020 | 03/02/2020 | 0 | TK_Complete | 1112893334 | 204 | 1112893334_204
C730D147BC###0015224 | TT_Task | Stage-3 System-wide Final Method Statement Drill ; Fix | 25/03/2020 | 16/04/2020 | 17/02/2020 | 22/05/2020 | 0 | TK_Complete | 1112893334 | 204 | 1112893334_204
C730D147BC###0015336 | TT_Task | Stage-3 System-wide customer review Final Method Statement Drill ; Fix | 25/05/2020 | 29/06/2020 | 25/05/2020 | 19/06/2020 | 0 | TK_Complete | 1112893334 | 204 | 1112893334_204
C730D147BC###0012170 | TT_Task | Stage2 [System-wide] Initial Method Statement PPI/MB/BS Installation | 09/04/2020 | 01/05/2020 | 16/12/2019 | 16/01/2020 | 0 | TK_Complete | 1112893334 | 203 | 1112893334_203
C730D147BC###0075215 | TT_Task | Stage2 System-wide Initial Method statement customer review PPI/MB/BS Installation | 25/02/2020 | 30/03/2020 | 17/01/2020 | 28/01/2020 | 0 | TK_Complete | 1112893334 | 203 | 1112893334_203
C730D147BC###0015140 | TT_Task | Stage-3 System-wide Final Method Statement PPI / MB / BS Installation | 25/03/2020 | 16/04/2020 | 29/01/2020 | 13/04/2020 | 0 | TK_Complete | 1112893334 | 203 | 1112893334_203
C730D147BC###0015231 | TT_Task | Stage-3 System-wide customer review Final Method Statement PPI / MB / BS Installation | 27/04/2020 | 29/05/2020 | 14/04/2020 | 19/05/2020 | 0 | TK_Complete | 1112893334 | 203 | 1112893334_203
C730D147BC###0012163 | TT_Task | Stage2 [System-wide] Initial Method Statement SER Wiring Installation | 09/04/2020 | 01/05/2020 | 16/12/2019 | 09/01/2020 | 0 | TK_Complete | 1112893334 | 202 | 1112893334_202
C730D147BC###0075225 | TT_Task | Stage2 System-wide Initial Method statement customer review SER Wiring Installation | 25/02/2020 | 30/03/2020 | 10/01/2020 | 28/01/2020 | 0 | TK_Complete | 1112893334 | 202 | 1112893334_202
C730D147BC###0015154 | TT_Task | Stage-3 System-wide Final Method Statement SER Wiring Installation | 25/03/2020 | 16/04/2020 | 10/02/2020 | 01/04/2020 | 0 | TK_Complete | 1112893334 | 202 | 1112893334_202
C730D147BC###0015245 | TT_Task | Stage-3 System-wide customer review Final Method Statement SER Wiring Installation | 27/04/2020 | 29/05/2020 | 06/04/2020 | 19/05/2020 | 0 | TK_Complete | 1112893334 | 202 | 1112893334_202
C730D147BC###0012156 | TT_Task | Stage2 [System-wide] Initial Method Statement MATR Point Machine Installation | 09/04/2020 | 01/05/2020 | 16/12/2019 | 09/01/2020 | 0 | TK_Complete | 1112893334 | 201 | 1112893334_201
C730D147BC###0075220 | TT_Task | Stage2 System-wide Initial Method statement customer review MATR Point Machine Installation | 25/02/2020 | 30/03/2020 | 10/01/2020 | 24/01/2020 | 0 | TK_Complete | 1112893334 | 201 | 1112893334_201
C730D147BC###0015147 | TT_Task | Stage-3 System-wide Final Method Statement Point Machine Installation - MATR | 25/03/2020 | 16/04/2020 | 05/02/2020 | 08/04/2020 | 0 | TK_Complete | 1112893334 | 201 | 1112893334_201
C730D147BC###0015238 | TT_Task | Stage-3 System-wide customer review Final Method Statement Point Machine Installation - MATR | 27/04/2020 | 29/05/2020 | 10/04/2020 | 19/05/2020 | 0 | TK_Complete | 1112893334 | 201 | 1112893334_201
C730D147BC###0012149 | TT_Task | Stage2 [System-wide] Initial Method Statement Axle Counter Installation | 12/03/2020 | 01/04/2020 | 18/11/2019 | 09/01/2020 | 0 | TK_Complete | 1112893334 | 200 | 1112893334_200
C730D147BC###0075140 | TT_Task | Stage2 System-wide Initial Method statement customer review Axle Counter Installation | 25/02/2020 | 30/03/2020 | 10/01/2020 | 24/01/2020 | 0 | TK_Complete | 1112893334 | 200 | 1112893334_200
C730D147BC###0015077 | TT_Task | Stage-3 System-wide Final Method Statement Axle Counter Installation | 25/03/2020 | 16/04/2020 | 28/01/2020 | 17/02/2020 | 0 | TK_Complete | 1112893334 | 200 | 1112893334_200
C730D147BC###0015112 | TT_Task | Stage-3 System-wide customer review Final Method Statement Axle Counter Installation | 27/04/2020 | 29/05/2020 | 25/02/2020 | 22/05/2020 | 0 | TK_Complete | 1112893334 | 200 | 1112893334_200
C720D147CF###0030590 | TT_Task | Trains/Stage-2 - Release of E-BOM for electrical parts | 02/09/2020 | 29/09/2020 | 27/07/2020 | 05/08/2020 | 0 | TK_Complete | 1112893334 | 20 | 1112893334_20
C720D147CF###0030600 | TT_Task | Trains/Stage-2 - Release of E-BOM for mechanical parts | 03/07/2020 | 30/07/2020 | 26/05/2020 | 18/06/2020 | 0 | TK_Complete | 1112893334 | 20 | 1112893334_20
C720D147CF###0030730 | TT_Task | Verification - Track parameters and track tolerances for SMCSW (Southwest/Brownfield) | 25/11/2020 | 29/11/2020 | 27/10/2020 | 25/11/2020 | 0 | TK_Complete | 1112893334 | 2 | 1112893334_2
C720D147CF###0030740 | TT_Task | Verification - OHE Parameters for SMCSW (Southwest/Brownfield) | 25/11/2020 | 29/11/2020 | 27/10/2020 | 25/11/2020 | 0 | TK_Complete | 1112893334 | 2 | 1112893334_2
C720D147CF###0030750 | TT_Task | Verification - Platform specifications for SMCSW (Southwest/Brownfield) | 25/11/2020 | 29/11/2020 | 27/10/2020 | 25/11/2020 | 0 | TK_Complete | 1112893334 | 2 | 1112893334_2
C720D147CF###0030760 | TT_Task | Verification - PSD ; PEB specifications for SMCSW (Southwest/Brownfield) | 25/03/2022 | 29/03/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 2 | 1112893334_2
C720D147CF###0030770 | TT_Task | Verification - Infrastructure Kinematic Envelope ; Structure gauge for SMCSW (Southwest/Brownfield) | 25/11/2020 | 29/11/2020 | 27/10/2020 | 25/11/2020 | 0 | TK_Complete | 1112893334 | 2 | 1112893334_2
C720D147CF###0030780 | TT_Task | Verification - Operational inputs/constraints for KE calculations for SMCSW (Southwest/Brownfield) | 25/11/2020 | 29/11/2020 | 27/10/2020 | 25/11/2020 | 0 | TK_Complete | 1112893334 | 2 | 1112893334_2
C730D147BC###0012142 | TT_Task | Stage2 [System-wide] Initial Method Statement D84M Point Machine Installation | 21/04/2020 | 11/05/2020 | 16/12/2019 | 09/01/2020 | 0 | TK_Complete | 1112893334 | 199 | 1112893334_199
C730D147BC###0075250 | TT_Task | Stage2 System-wide Initial Method statement customer review D84M Point Machine Installation | 25/02/2020 | 30/03/2020 | 10/01/2020 | 28/01/2020 | 0 | TK_Complete | 1112893334 | 199 | 1112893334_199
C730D147BC###0015161 | TT_Task | Stage-3 System-wide Final Method Statement Point Machine Installation - D84M | 25/03/2020 | 16/04/2020 | 03/02/2020 | 08/04/2020 | 0 | TK_Complete | 1112893334 | 199 | 1112893334_199
C730D147BC###0015252 | TT_Task | Stage-3 System-wide customer review Final Method Statement Point Machine Installation - D84M | 27/04/2020 | 29/05/2020 | 10/04/2020 | 19/05/2020 | 0 | TK_Complete | 1112893334 | 199 | 1112893334_199
C730D147BC###0012135 | TT_Task | Stage2 [System-wide] Initial Method Statement Balise Installation | 12/03/2020 | 01/04/2020 | 18/11/2019 | 09/01/2020 | 0 | TK_Complete | 1112893334 | 198 | 1112893334_198
C730D147BC###0075135 | TT_Task | Stage2 System-wide Initial Method statement customer review Balise Installation | 25/02/2020 | 30/03/2020 | 10/01/2020 | 24/01/2020 | 0 | TK_Complete | 1112893334 | 198 | 1112893334_198
C730D147BC###0015091 | TT_Task | Stage-3 System-wide Final Method Statement Balise Installation | 22/05/2020 | 12/06/2020 | 28/01/2020 | 17/02/2020 | 0 | TK_Complete | 1112893334 | 198 | 1112893334_198
C730D147BC###0015133 | TT_Task | Stage-3 System-wide customer review Final Method Statement Balise Installation | 23/06/2020 | 27/07/2020 | 18/02/2020 | 19/05/2020 | 0 | TK_Complete | 1112893334 | 198 | 1112893334_198
C730D147BC###0012128 | TT_Task | Stage2 [System-wide] Initial Method Statement Cable Testing | 04/05/2020 | 22/05/2020 | 16/12/2019 | 21/01/2020 | 0 | TK_Complete | 1112893334 | 197 | 1112893334_197
C730D147BC###0075320 | TT_Task | Stage2 System-wide Initial Method statement customer review Cable Testing | 25/02/2020 | 30/03/2020 | 22/01/2020 | 03/02/2020 | 0 | TK_Complete | 1112893334 | 197 | 1112893334_197
C730D147BC###0015217 | TT_Task | Stage-3 System-wide Final Method Statement Cable Testing | 25/03/2020 | 16/04/2020 | 17/02/2020 | 25/04/2020 | 0 | TK_Complete | 1112893334 | 197 | 1112893334_197
C730D147BC###0015329 | TT_Task | Stage-3 System-wide customer review Final Method Statement Cable Testing | 25/05/2020 | 29/06/2020 | 27/04/2020 | 18/05/2020 | 0 | TK_Complete | 1112893334 | 197 | 1112893334_197
C730D147BC###0012121 | TT_Task | Stage2 [System-wide] Initial Method Statement Track Cable Laying | 21/04/2020 | 11/05/2020 | 16/12/2019 | 16/01/2020 | 0 | TK_Complete | 1112893334 | 196 | 1112893334_196
C730D147BC###0075245 | TT_Task | Stage2 System-wide Initial Method statement customer review Track Cable Laying | 25/02/2020 | 30/03/2020 | 17/01/2020 | 03/02/2020 | 0 | TK_Complete | 1112893334 | 196 | 1112893334_196
C730D147BC###0015168 | TT_Task | Stage-3 System-wide Final Method Statement Track Cable Laying | 25/03/2020 | 16/04/2020 | 26/02/2020 | 22/05/2020 | 0 | TK_Complete | 1112893334 | 196 | 1112893334_196
C730D147BC###0015259 | TT_Task | Stage-3 System-wide customer review Final Method Statement Track Cable Laying | 25/05/2020 | 29/06/2020 | 22/05/2020 | 25/05/2020 | 0 | TK_Complete | 1112893334 | 196 | 1112893334_196
C730D147BC###0012114 | TT_Task | Stage2 [System-wide] Initial Method Statement Boxes (SAB ; SPB) | 27/03/2020 | 20/04/2020 | 03/12/2019 | 16/01/2020 | 0 | TK_Complete | 1112893334 | 195 | 1112893334_195
C730D147BC###0075185 | TT_Task | Stage2 System-wide Initial Method statement customer review Boxes (SAB ; SPB) | 25/02/2020 | 30/03/2020 | 17/01/2020 | 03/02/2020 | 0 | TK_Complete | 1112893334 | 195 | 1112893334_195
C730D147BC###0015105 | TT_Task | Stage-3 System-wide Final Method Statement Boxes (SAB ; SPB) | 25/03/2020 | 16/04/2020 | 20/02/2020 | 10/04/2020 | 0 | TK_Complete | 1112893334 | 195 | 1112893334_195
C730D147BC###0015175 | TT_Task | Stage-3 System-wide customer review Final Method Statement Boxes (SAB ; SPB) | 27/04/2020 | 29/05/2020 | 13/04/2020 | 19/05/2020 | 0 | TK_Complete | 1112893334 | 195 | 1112893334_195
C730D147BC###0012107 | TT_Task | Stage2 [System-wide] Initial Method Statement SER Mechanical Installation | 01/05/2020 | 21/05/2020 | 16/12/2019 | 10/01/2020 | 0 | TK_Complete | 1112893334 | 194 | 1112893334_194
C730D147BC###0075300 | TT_Task | Stage2 System-wide Initial Method statement customer review SER Mechanical Installation | 25/02/2020 | 30/03/2020 | 13/01/2020 | 28/01/2020 | 0 | TK_Complete | 1112893334 | 194 | 1112893334_194
C730D147BC###0015196 | TT_Task | Stage-3 System-wide Final Method Statement SER Mechanical Installation | 25/03/2020 | 16/04/2020 | 10/02/2020 | 08/05/2020 | 0 | TK_Complete | 1112893334 | 194 | 1112893334_194
C730D147BC###0015301 | TT_Task | Stage-3 System-wide customer review Final Method Statement SER Mechanical Installation | 25/05/2020 | 29/06/2020 | 11/05/2020 | 19/05/2020 | 0 | TK_Complete | 1112893334 | 194 | 1112893334_194
C730D147BC###0012100 | TT_Task | Stage2 [System-wide] Initial Method Statement DCS Antenna Installation | 04/05/2020 | 22/05/2020 | 16/12/2019 | 09/01/2020 | 0 | TK_Complete | 1112893334 | 193 | 1112893334_193
C730D147BC###0075305 | TT_Task | Stage2 System-wide Initial Method statement customer review DCS Antenna Installation | 25/02/2020 | 30/03/2020 | 10/01/2020 | 24/01/2020 | 0 | TK_Complete | 1112893334 | 193 | 1112893334_193
C730D147BC###0015203 | TT_Task | Stage-3 System-wide Final Method Statement DCS Antenna Installation | 25/03/2020 | 16/04/2020 | 03/02/2020 | 03/05/2020 | 0 | TK_Complete | 1112893334 | 193 | 1112893334_193
C730D147BC###0015315 | TT_Task | Stage-3 System-wide customer review Final Method Statement DCS Antenna Installation | 25/05/2020 | 29/06/2020 | 04/05/2020 | 19/05/2020 | 0 | TK_Complete | 1112893334 | 193 | 1112893334_193
C730D147BC###0026711 | TT_Task | Stage2 SMTF[N] - Initial Drawings Point Machines Installation - MATR | 05/11/2019 | 25/11/2019 | 25/09/2019 | 29/11/2019 | 0 | TK_Complete | 1112893334 | 192 | 1112893334_192
C730D147BC###0027091 | TT_Task | Stage2 SMTF[N] - Initial Drawings Point Machines Installation - D84M | 15/10/2019 | 04/11/2019 | 25/09/2019 | 29/11/2019 | 0 | TK_Complete | 1112893334 | 192 | 1112893334_192
C730D147BC###0015280 | TT_Task | Stage-3 SMTF[N] - Final Drawings Point Machine Installation - MATR | 26/06/2020 | 09/07/2020 | 10/02/2020 | 15/04/2020 | 0 | TK_Complete | 1112893334 | 192 | 1112893334_192
C730D147BC###0015294 | TT_Task | Stage-3 SMTF[N] - Final Drawings Point Machine Installation - D84M | 26/06/2020 | 09/07/2020 | 10/02/2020 | 05/05/2020 | 0 | TK_Complete | 1112893334 | 192 | 1112893334_192
C730D147BC###0012024 | TT_Task | Stage2 SMTF[N] - Initial Drawings Key Switches Installation | 01/11/2019 | 14/11/2019 | 04/10/2019 | 15/11/2019 | 0 | TK_Complete | 1112893334 | 191 | 1112893334_191
C730D147BC###0075150 | TT_Task | Stage2 SMTF[N] Installation Design customer review Key Switches Installation | 25/02/2020 | 30/03/2020 | 18/11/2019 | 03/01/2020 | 0 | TK_Complete | 1112893334 | 191 | 1112893334_191
C730D147BC###0015532 | TT_Task | Stage-3 SMTF[N] - Final Drawings Key Switches Installation | 10/09/2020 | 23/09/2020 | 10/02/2020 | 15/05/2020 | 0 | TK_Complete | 1112893334 | 191 | 1112893334_191
C730D147BC###0015567 | TT_Task | Stage3 [SMTF-N] Installation design customer review Key Switches Installation | 25/05/2020 | 29/06/2020 | 18/05/2020 | 30/06/2020 | 0 | TK_Complete | 1112893334 | 191 | 1112893334_191
C730D147BC###0015714 | TT_Task | As Built SMTF[N] - Key Switch Installation Drawings | 10/06/2022 | 23/06/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 191 | 1112893334_191
C730D147BC###0012021 | TT_Task | Stage2 SMTF[N] - Initial Drawings Marker Board Installation | 29/10/2019 | 11/11/2019 | 01/10/2019 | 15/11/2019 | 0 | TK_Complete | 1112893334 | 190 | 1112893334_190
C730D147BC###0075085 | TT_Task | Stage2 SMTF[N] Installation Design customer review Marker Board Installation | 25/02/2020 | 30/03/2020 | 18/11/2019 | 03/01/2020 | 0 | TK_Complete | 1112893334 | 190 | 1112893334_190
C730D147BC###0015413 | TT_Task | Stage3 [SMTF-N] Installation design customer review Marker Board Installation | 25/05/2020 | 29/06/2020 | 18/05/2020 | 30/06/2020 | 0 | TK_Complete | 1112893334 | 190 | 1112893334_190
C720D147CF###0030610 | TT_Task | Trains/Stage-2 - Release of wire to wire list update (preliminary) | 02/09/2020 | 29/09/2020 | 03/08/2020 | 07/08/2020 | 0 | TK_Complete | 1112893334 | 19 | 1112893334_19
C720D147CF###0030620 | TT_Task | Trains/Stage-3 - Release of wire to wire list update (final) | 30/09/2020 | 28/10/2020 | 03/08/2020 | 07/08/2020 | 0 | TK_Complete | 1112893334 | 19 | 1112893334_19
C730D147BC###0012018 | TT_Task | Stage2 SMTF[N] - Initial Drawings Buffer Stop Installation | 19/11/2019 | 09/12/2019 | 02/10/2019 | 14/11/2019 | 0 | TK_Complete | 1112893334 | 189 | 1112893334_189
C730D147BC###0075090 | TT_Task | Stage2 SMTF[N] Installation Design customer review Buffer Stop Installation | 25/02/2020 | 30/03/2020 | 15/11/2019 | 03/01/2020 | 0 | TK_Complete | 1112893334 | 189 | 1112893334_189
C730D147BC###0015273 | TT_Task | Stage3 [SMTF-N] Installation design customer review Buffer Stop Installation | 23/06/2020 | 27/07/2020 | 23/03/2020 | 03/04/2020 | 0 | TK_Complete | 1112893334 | 189 | 1112893334_189
C730D147BC###0012015 | TT_Task | Stage2 SMTF[N] - Initial Drawings PPI Installation | 05/11/2019 | 18/11/2019 | 01/10/2019 | 13/12/2019 | 0 | TK_Complete | 1112893334 | 188 | 1112893334_188
C730D147BC###0075155 | TT_Task | Stage2 SMTF[N] Installation Design customer review PPI Installation | 25/02/2020 | 30/03/2020 | 16/12/2019 | 23/01/2020 | 0 | TK_Complete | 1112893334 | 188 | 1112893334_188
C730D147BC###0015119 | TT_Task | Stage-3 SMTF[N] - Final Drawings PPI Installation | 14/05/2020 | 03/06/2020 | 10/02/2020 | 22/03/2020 | 0 | TK_Complete | 1112893334 | 188 | 1112893334_188
C730D147BC###0015399 | TT_Task | Stage3 [SMTF-N] Installation design customer review PPI Installation | 23/06/2020 | 27/07/2020 | 23/03/2020 | 06/04/2020 | 0 | TK_Complete | 1112893334 | 188 | 1112893334_188
C730D147BC###0012012 | TT_Task | Stage2 SMTF[N] - Initial Drawings Axle Counter Installation | 19/11/2019 | 02/12/2019 | 03/10/2019 | 15/11/2019 | 0 | TK_Complete | 1112893334 | 187 | 1112893334_187
C730D147BC###0075080 | TT_Task | Stage2 SMTF[N] Installation Design customer review Axle Counter Installation | 25/02/2020 | 30/03/2020 | 18/11/2019 | 03/01/2020 | 0 | TK_Complete | 1112893334 | 187 | 1112893334_187
C730D147BC###0015189 | TT_Task | Stage-3 SMTF[N] - Final Drawings Axle Counter Installation | 04/06/2020 | 25/06/2020 | 10/02/2020 | 01/04/2020 | 0 | TK_Complete | 1112893334 | 187 | 1112893334_187
C730D147BC###0015287 | TT_Task | Stage3 [SMTF-N] Installation design customer review Axle Counter Installation | 23/06/2020 | 27/07/2020 | 06/04/2020 | 06/04/2020 | 0 | TK_Complete | 1112893334 | 187 | 1112893334_187
C730D147BC###0015686 | TT_Task | As Built SMTF[N] - Axle Counter Installation Drawings | 10/06/2022 | 23/06/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 187 | 1112893334_187
C730D147BC###0012009 | TT_Task | Stage2 SMTF[N] - Initial Drawings Balise Installation | 05/11/2019 | 18/11/2019 | 03/10/2019 | 14/11/2019 | 0 | TK_Complete | 1112893334 | 186 | 1112893334_186
C730D147BC###0075075 | TT_Task | Stage2 SMTF[N] Installation Design customer review Balise Installation | 25/02/2020 | 30/03/2020 | 15/11/2019 | 03/01/2020 | 0 | TK_Complete | 1112893334 | 186 | 1112893334_186
C730D147BC###0015084 | TT_Task | Stage-3 SMTF[N] - Final Drawings Balise Installation | 23/04/2020 | 13/05/2020 | 10/02/2020 | 27/02/2020 | 0 | TK_Complete | 1112893334 | 186 | 1112893334_186
C730D147BC###0015126 | TT_Task | Stage3 [SMTF-N] Installation design customer review Balise Installation | 23/06/2020 | 27/07/2020 | 02/03/2020 | 06/05/2020 | 0 | TK_Complete | 1112893334 | 186 | 1112893334_186
C730D147BC###0012006 | TT_Task | Stage2 SMTF[N] - Initial Drawings Track Plan ; Cable Duct Routes [Depot] | 25/02/2020 | 31/03/2020 | 31/10/2019 | 23/12/2019 | 0 | TK_Complete | 1112893334 | 185 | 1112893334_185
C730D147BC###0075130 | TT_Task | Stage2 SMTF[N] Installation Design customer review Track Plan ; Cable Duct Routes [Depot] | 25/02/2020 | 30/03/2020 | 24/12/2019 | 31/01/2020 | 0 | TK_Complete | 1112893334 | 185 | 1112893334_185
C730D147BC###0015371 | TT_Task | Stage-3 SMTF[N] - Final Drawings Track Plan ; Cable Duct Routes [New TT ; Stabling Road 30-35] | 25/05/2020 | 05/06/2020 | 20/04/2020 | 04/05/2020 | 0 | TK_Complete | 1112893334 | 185 | 1112893334_185
C730D147BC###0015483 | TT_Task | Stage-3 SMTF[N] - Final Drawings Track Plan ; Cable Duct Routes [Maintenance Road 5-8] | 17/08/2020 | 28/08/2020 | 11/05/2020 | 15/05/2020 | 0 | TK_Complete | 1112893334 | 185 | 1112893334_185
C730D147BC###0015539 | TT_Task | Stage-3 SMTF[N] - Final Drawings Track Plan ; Cable Duct Routes [Stabling Road 24-29] | 31/08/2020 | 11/09/2020 | 11/05/2020 | 15/05/2020 | 0 | TK_Complete | 1112893334 | 185 | 1112893334_185
C730D147BC###0015574 | TT_Task | Stage3 [SMTF-N] Installation design customer review Track Plan ; Cable Duct Routes [Stabling Road 24-29] | 14/09/2020 | 19/10/2020 | 15/05/2020 | 20/05/2020 | 0 | TK_Complete | 1112893334 | 185 | 1112893334_185
C730D147BC###5085035 | TT_Task | Stage3 [SMTF-N] Installation design customer review Track Plan ; Cable Duct Routes [New TT ; Stabling Road 30-35] | 25/05/2020 | 29/06/2020 | 05/05/2020 | 30/06/2020 | 0 | TK_Complete | 1112893334 | 185 | 1112893334_185
C730D147BC###5085045 | TT_Task | Stage3 [SMTF-N] Installation design customer review Track Plan ; Cable Duct Routes [Maintenance Road 5-8] | 31/08/2020 | 02/10/2020 | 15/05/2020 | 20/05/2020 | 0 | TK_Complete | 1112893334 | 185 | 1112893334_185
C730D147BC###0012003 | TT_Task | Stage2 SMTF[N] - Initial Drawings SAB Installation | 12/11/2019 | 02/12/2019 | 20/09/2019 | 27/11/2019 | 0 | TK_Complete | 1112893334 | 184 | 1112893334_184
C730D147BC###0075110 | TT_Task | Stage2 SMTF[N] Installation Design customer review SAB Installation | 25/02/2020 | 30/03/2020 | 28/11/2019 | 20/01/2020 | 0 | TK_Complete | 1112893334 | 184 | 1112893334_184
C730D147BC###0015343 | TT_Task | Stage-3 SMTF[N] - Final Drawings MB Installation | 10/07/2020 | 30/07/2020 | 10/02/2020 | 15/05/2020 | 0 | TK_Complete | 1112893334 | 184 | 1112893334_184
C730D147BC###0015525 | TT_Task | Stage-3 SMTF[N] - Final Drawings SAB Installation | 10/09/2020 | 23/09/2020 | 10/02/2020 | 15/05/2020 | 0 | TK_Complete | 1112893334 | 184 | 1112893334_184
C730D147BC###0015581 | TT_Task | Stage3 [SMTF-N] Installation design customer review SAB Installation | 25/05/2020 | 29/06/2020 | 18/05/2020 | 30/06/2020 | 0 | TK_Complete | 1112893334 | 184 | 1112893334_184
C730D147BC###0012000 | TT_Task | Stage2 SMTF[N] - Initial Drawings DCS Antenna/Boxes Installation | 12/11/2019 | 02/12/2019 | 15/09/2019 | 20/12/2019 | 0 | TK_Complete | 1112893334 | 183 | 1112893334_183
C730D147BC###0075105 | TT_Task | Stage2 SMTF[N] Installation Design customer review DCS Antenna/Boxes Installation | 25/02/2020 | 30/03/2020 | 23/12/2019 | 30/01/2020 | 0 | TK_Complete | 1112893334 | 183 | 1112893334_183
C730D147BC###0015427 | TT_Task | Stage-3 SMTF[N] - Final Drawings DCS/CCTV antenna installation | 23/07/2020 | 05/08/2020 | 10/02/2020 | 25/05/2020 | 0 | TK_Complete | 1112893334 | 183 | 1112893334_183
C730D147BC###0015462 | TT_Task | Stage3 [SMTF-N] Installation design customer review DCS antenna installation | 25/06/2020 | 29/07/2020 | 27/05/2020 | 30/06/2020 | 0 | TK_Complete | 1112893334 | 183 | 1112893334_183
C730D147BC###0011000 | TT_Task | Stage2 SMTF[N] - Initial Drawings Room Layout (DSER2) | 15/10/2019 | 11/11/2019 | 09/09/2019 | 13/12/2019 | 0 | TK_Complete | 1112893334 | 182 | 1112893334_182
C730D147BC###0011003 | TT_Task | Stage2 SMTF[N] - Initial Drawings Room Layout (CER2) | 25/02/2020 | 23/03/2020 | 09/09/2019 | 13/12/2019 | 0 | TK_Complete | 1112893334 | 182 | 1112893334_182
C730D147BC###0015357 | TT_Task | Stage-3 SMTF[N] - Final drawings room layout - DSER2 | 25/05/2020 | 22/06/2020 | 04/05/2020 | 18/05/2020 | 0 | TK_Complete | 1112893334 | 182 | 1112893334_182
C730D147BC###0015448 | TT_Task | Stage-3 SMTF[N] - Final drawings room layout - DSER1 modification | 21/07/2020 | 10/08/2020 | 04/05/2020 | 18/05/2020 | 0 | TK_Complete | 1112893334 | 182 | 1112893334_182
C730D147BC###0015469 | TT_Task | Stage-3 SMTF[N] - Final drawings room layout - CER2 | 28/09/2020 | 19/10/2020 | 24/09/2020 | 04/12/2020 | 0 | TK_Complete | 1112893334 | 182 | 1112893334_182
C730D157BC###0049471 | TT_Task | CBTC/Stage-2 SMTF[N] - Stage 2 BoQ Installation | 01/11/2019 | 21/11/2019 | 02/09/2019 | 29/11/2019 | 0 | TK_Complete | 1112893334 | 181 | 1112893334_181
C730D147BC###0015378 | TT_Task | Stage-3 SMTF[N] - Final BoQ Installation | 25/05/2020 | 15/06/2020 | 08/05/2020 | 22/05/2020 | 0 | TK_Complete | 1112893334 | 181 | 1112893334_181
C730D157BC###0013060 | TT_Task | CBTC/Stage-2 SMCSW - Initial BoQ Installation | 11/05/2020 | 22/06/2020 | 01/03/2020 | 14/04/2020 | 0 | TK_Complete | 1112893334 | 181 | 1112893334_181
C730D157BC###0050511 | TT_Task | CBTC/Stage-3 SMCSW [City] - Final BoQ Installation | 27/07/2021 | 23/08/2021 | 23/07/2021 | 16/11/2021 | 0 | TK_Complete | 1112893334 | 181 | 1112893334_181
C730D157BC###0066383 | TT_Task | Stage 2 [SMTF-N] Initial DIS ; DITP 'Operation Control Center' (OCC/SIG) | 15/02/2019 | 18/04/2019 | 15/02/2019 | 30/04/2019 | 0 | TK_Complete | 1112893334 | 180 | 1112893334_180
C730D157BC###0066393 | TT_Task | Stage 3 SMTF(N) - Final DIS ; DITP 'Operation Control Center' (OCC/SIG) | 31/10/2019 | 13/01/2020 | 18/09/2019 | 29/04/2020 | 0 | TK_Complete | 1112893334 | 180 | 1112893334_180
C730D157BC###0068311 | TT_Task | Stage 3 SMTF(N) - Final DIS ; DITP - SMTF(N) | 31/10/2019 | 13/01/2020 | 07/10/2019 | 11/12/2019 | 0 | TK_Complete | 1112893334 | 180 | 1112893334_180
C730D147BC###0015014 | TT_Task | SMTF(N) - Initial ITS 'Operation Control Center' (OCC/SIG) | 25/05/2020 | 22/06/2020 | 04/05/2020 | 15/05/2020 | 0 | TK_Complete | 1112893334 | 180 | 1112893334_180
C730D147BC###0015049 | TT_Task | SMTF(N) - Final ITS 'Operation Control Center' (OCC/SIG) | 23/06/2020 | 06/07/2020 | 14/05/2020 | 20/05/2020 | 0 | TK_Complete | 1112893334 | 180 | 1112893334_180
C720D147CF###0030580 | TT_Task | Trains/Stage-2 - Release of cable principal schemes version0 | 24/04/2020 | 21/05/2020 | 04/05/2020 | 31/07/2020 | 0 | TK_Complete | 1112893334 | 18 | 1112893334_18
C720D147CF###D87050 | TT_Task | Trains/Stage-2 - Release of cable principal schemes [Covid-19 delay event - India] | 26/02/2020 | 26/02/2020 | 25/03/2020 | 30/04/2020 | 0 | TK_Complete | 1112893334 | 18 | 1112893334_18
C730D157BC###0066323 | TT_Task | Stage 2 [SMTF-N] Initial DIS ; DITP 'Signalling System' (COM/SIG) | 15/02/2019 | 18/04/2019 | 15/02/2019 | 30/04/2019 | 0 | TK_Complete | 1112893334 | 179 | 1112893334_179
C730D157BC###0066343 | TT_Task | Stage 2 [SMTF-N] Initial DIS ; DITP 'Signalling System' (CCS/SIG) | 15/02/2019 | 18/04/2019 | 15/02/2019 | 30/04/2019 | 0 | TK_Complete | 1112893334 | 179 | 1112893334_179
C730D157BC###0066333 | TT_Task | Stage 3 SMTF(N) - Final DIS ; DITP 'Signalling System' (COM/SIG) | 31/10/2019 | 13/01/2020 | 01/10/2019 | 11/12/2019 | 0 | TK_Complete | 1112893334 | 179 | 1112893334_179
C730D157BC###0066353 | TT_Task | Stage 3 SMTF(N) - Final DIS ; DITP 'Signalling System' (CCS/SIG) | 31/10/2019 | 13/01/2020 | 26/09/2019 | 11/12/2019 | 0 | TK_Complete | 1112893334 | 179 | 1112893334_179
C730D157BC###0036120 | TT_Task | CBTC/Stage-2 SMCSW - Initial DIS ; DITP 'Signalling System' (PSD/SIG) | 01/07/2019 | 20/09/2019 | 15/05/2019 | 30/06/2019 | 0 | TK_Complete | 1112893334 | 179 | 1112893334_179
C730D157BC###0036150 | TT_Task | CBTC/Stage-2 SMCSW - Initial DIS ; DITP 'Signalling System' (CCS/SIG) - [achieved at A2 SMTF-N activity] | 01/07/2019 | 20/09/2019 | 15/05/2019 | 30/06/2019 | 0 | TK_Complete | 1112893334 | 179 | 1112893334_179
C730D157BC###0036160 | TT_Task | CBTC/Stage-2 SMCSW - Initial DIS ; DITP 'Signalling System' (COM/SIG) - [achieved at A2 SMTF-N activity] | 01/07/2019 | 20/09/2019 | 15/05/2019 | 30/06/2019 | 0 | TK_Complete | 1112893334 | 179 | 1112893334_179
C730D157BC###0067593 | TT_Task | CBTC/Stage-2 SMCSW - Initial DIS ; DITP 'Signalling System' (SIG/LW) | 01/07/2019 | 20/09/2019 | 15/05/2019 | 30/06/2019 | 0 | TK_Complete | 1112893334 | 179 | 1112893334_179
C730D157BC###0037730 | TT_Task | CBTC/Stage-3 SMCSW - Final DIS ; DITP 'Signalling System' (SIG PSD/PEB) | 31/10/2019 | 06/01/2020 | 24/09/2019 | 10/12/2019 | 0 | TK_Complete | 1112893334 | 179 | 1112893334_179
C730D157BC###0037760 | TT_Task | CBTC/Stage-3 SMCSW - Final DIS ; DITP 'Signalling System' (CCS/SIG) - [same document @SMTF-N act.] | 31/10/2019 | 06/01/2020 | 24/09/2019 | 11/12/2019 | 0 | TK_Complete | 1112893334 | 179 | 1112893334_179
C730D157BC###0037770 | TT_Task | CBTC/Stage-3 SMCSW - Final DIS ; DITP 'Signalling System' (COM/SIG) - [same document @SMTF-N act.] | 31/10/2019 | 06/01/2020 | 10/10/2019 | 11/12/2019 | 0 | TK_Complete | 1112893334 | 179 | 1112893334_179
C730D157BC###0066013 | TT_Task | Stage 2 [SMTF-N] Initial DIS ; DITP 'Radio System' (SIG/RAD) | 01/07/2019 | 30/08/2019 | 15/02/2019 | 30/04/2019 | 0 | TK_Complete | 1112893334 | 178 | 1112893334_178
C730D157BC###0066023 | TT_Task | Stage 3 SMTF(N) - Final DIS ; DITP 'Radio System' (SIG/RAD) | 31/10/2019 | 13/01/2020 | 02/09/2019 | 11/12/2019 | 0 | TK_Complete | 1112893334 | 178 | 1112893334_178
C730D147BC###0015000 | TT_Task | SMTF(N) - Initial ITS 'Radio System' (SIG/RAD) | 25/02/2020 | 23/03/2020 | 07/11/2019 | 29/11/2019 | 0 | TK_Complete | 1112893334 | 178 | 1112893334_178
C730D147BC###0015035 | TT_Task | SMTF(N) - Final ITS 'Radio System' (SIG/RAD) | 25/02/2020 | 09/03/2020 | 07/11/2019 | 29/11/2019 | 0 | TK_Complete | 1112893334 | 178 | 1112893334_178
C730D157BC###0000500 | TT_Task | CBTC/Stage-2 SMTF[N] - Alstom CBTC Hazard Log (PHA) | 15/10/2019 | 28/10/2019 | 15/08/2019 | 21/01/2020 | 0 | TK_Complete | 1112893334 | 177 | 1112893334_177
C730D157BC###0000750 | TT_Task | CBTC/Stage-2 SMTF[N] - Alstom CBTC Hazard Log (SSS - Migration SMTF(N)) | 27/11/2019 | 04/12/2019 | 27/11/2019 | 27/11/2019 | 0 | TK_Complete | 1112893334 | 177 | 1112893334_177
C730D147BC###0075095 | TT_Task | CBTC/Stage-3 SMTF[N] - Alstom CBTC Hazard Log (SHA) | 25/02/2020 | 23/03/2020 | 07/02/2020 | 18/02/2020 | 0 | TK_Complete | 1112893334 | 177 | 1112893334_177
C730D147BC###0075100 | TT_Task | CBTC/Stage-3 SMTF[N] - Alstom CBTC Hazard Log (PHA) | 25/02/2020 | 09/03/2020 | 22/01/2020 | 14/02/2020 | 0 | TK_Complete | 1112893334 | 177 | 1112893334_177
C730D157BC###0000890 | TT_Task | CBTC/Stage-3 SMTF[N] - Alstom CBTC Hazard Log (IHA) | 08/04/2020 | 28/04/2020 | 11/03/2020 | 24/03/2020 | 0 | TK_Complete | 1112893334 | 177 | 1112893334_177
C730D157BC###0000900 | TT_Task | CBTC/Stage-3 SMTF[N] - Alstom CBTC Hazard Log (OSHA) | 25/03/2020 | 07/04/2020 | 24/03/2020 | 01/04/2020 | 0 | TK_Complete | 1112893334 | 177 | 1112893334_177
C730D157BC###0000909 | TT_Task | CBTC/Stage-3 SMTF[N] - Alstom CBTC Hazard Log (SSS) | 25/02/2020 | 23/03/2020 | 19/02/2020 | 24/03/2020 | 0 | TK_Complete | 1112893334 | 177 | 1112893334_177
C730D157BC###0036330 | TT_Task | CBTC/Stage-2 SMCSW - Alstom CBTC Hazard Log (PHA) | 25/02/2020 | 16/03/2020 | 20/12/2019 | 31/12/2019 | 0 | TK_Complete | 1112893334 | 177 | 1112893334_177
C730D157BC###0036620 | TT_Task | CBTC/Stage-2 SMCSW - Alstom CBTC Hazard Log (SHA) | 27/04/2020 | 15/05/2020 | 16/04/2020 | 26/06/2020 | 0 | TK_Complete | 1112893334 | 177 | 1112893334_177
C730D157BC###0037120 | TT_Task | CBTC/Stage-2 SMCSW - Alstom CBTC Hazard Log (SSS) | 29/06/2020 | 07/07/2020 | 15/06/2020 | 30/06/2020 | 0 | TK_Complete | 1112893334 | 177 | 1112893334_177
C730D157BC###0037650 | TT_Task | CBTC/Stage-2 SMCSW - Alstom CBTC Hazard Log (OSHA) | 08/07/2020 | 14/07/2020 | 25/05/2020 | 26/06/2020 | 0 | TK_Complete | 1112893334 | 177 | 1112893334_177
C730D157BC###0037880 | TT_Task | CBTC/Stage-2 SMCSW - Alstom CBTC Hazard Log (IHA) | 29/06/2020 | 02/07/2020 | 01/06/2020 | 26/06/2020 | 0 | TK_Complete | 1112893334 | 177 | 1112893334_177
C730D157BC###0032054 | TT_Task | CBTC/Stage-3 SMCSW - Alstom CBTC Hazard Log (Covering all Sheets) | 15/04/2021 | 28/04/2021 | 15/03/2021 | 29/04/2021 | 0 | TK_Complete | 1112893334 | 177 | 1112893334_177
C730T147BC###R02235 | TT_Task | CBTC/Stage-3 SMTF[N] - Alstom CBTC Hazard Log (SSS) - Rework | 28/09/2020 | 09/10/2020 | 10/09/2020 | 28/09/2020 | 0 | TK_Complete | 1112893334 | 177 | 1112893334_177
C730T147BC###R02295 | TT_Task | CBTC/Stage-3 SMTF[N] - Alstom CBTC Hazard Log (OSHA) - Rework | 12/10/2020 | 23/10/2020 | 10/09/2020 | 28/09/2020 | 0 | TK_Complete | 1112893334 | 177 | 1112893334_177
C730T147BC###R02335 | TT_Task | CBTC/Stage-3 SMTF[N] - Alstom CBTC Hazard Log (IHA) - Rework | 26/10/2020 | 06/11/2020 | 10/09/2020 | 28/09/2020 | 0 | TK_Complete | 1112893334 | 177 | 1112893334_177
C730D157BC###0049450 | TT_Task | CBTC/Stage-2 SMTF[N] - CBI Circuit Book (Cable Layout) | 01/07/2019 | 12/07/2019 | 24/06/2019 | 28/06/2019 | 0 | TK_Complete | 1112893334 | 176 | 1112893334_176
C730D147BC###0075055 | TT_Task | CBTC/Stage-3 SMTF[N] - CBI Discussion with Cable Supplier/ Data Sheets | 02/12/2019 | 10/01/2020 | 01/10/2019 | 24/04/2020 | 0 | TK_Complete | 1112893334 | 176 | 1112893334_176
C730D147BC###0075120 | TT_Task | CBTC/Stage-3 SMTF[N] - CBI Discussion with Supplier - Relay and Cable frames | 25/03/2020 | 21/04/2020 | 20/01/2020 | 06/03/2020 | 0 | TK_Complete | 1112893334 | 176 | 1112893334_176
C730D147BC###0075190 | TT_Task | CBTC/Stage-3 SMTF[N] - CBI Cable Specification Approval from Customer ***Mitigation*** | 25/02/2020 | 25/02/2020 | 25/02/2020 | 25/02/2020 | 0 | TK_Complete | 1112893334 | 176 | 1112893334_176
C730D147BC###0075050 | TT_Task | CBTC/Stage-3 SMTF[N] - CBI Cable Specfication | 13/01/2020 | 24/01/2020 | 01/10/2019 | 24/01/2020 | 0 | TK_Complete | 1112893334 | 176 | 1112893334_176
C730D147BC###0010806 | TT_Task | CBTC/Stage-2 SMCSW - CBI Discussion with Supplier - Relay and Cable frames | 25/03/2020 | 14/04/2020 | 20/01/2020 | 06/03/2020 | 0 | TK_Complete | 1112893334 | 176 | 1112893334_176
C730D157BC###0087014 | TT_Task | CBTC/Stage-2 SMCSW - CBI Cable Specification | 21/04/2020 | 04/05/2020 | 01/10/2019 | 24/01/2020 | 0 | TK_Complete | 1112893334 | 176 | 1112893334_176
C730D157BC###0021733 | TT_Task | CBTC/Stage-3 SMCSW - CBI Cable Specification [Updated] | 28/09/2020 | 09/10/2020 | 14/09/2020 | 23/09/2020 | 0 | TK_Complete | 1112893334 | 176 | 1112893334_176
C730D157BC###0031901 | TT_Task | CBTC/Stage-3 SMCSW - CBI Cable Layout Customer Review and Comments | 25/10/2021 | 26/11/2021 | 12/04/2021 | 19/07/2021 | 0 | TK_Complete | 1112893334 | 176 | 1112893334_176
C730D157BC###0025260 | TT_Task | CBTC/Stage-2 SMTF[N] - Headway Simulation report | 04/04/2019 | 02/05/2019 | 04/04/2019 | 29/04/2019 | 0 | TK_Complete | 1112893334 | 175 | 1112893334_175
C730D147BC###0075380 | TT_Task | CBTC/Stage-3 SMTF[N] - Headway Simulation Report (Depot Simulation Runs and Test Track) | 22/06/2020 | 10/08/2020 | 01/04/2020 | 21/04/2020 | 0 | TK_Complete | 1112893334 | 175 | 1112893334_175
C730D147BC###0010758 | TT_Task | CBTC/Stage-2 SMCSW - Headway Simulation Report | 18/02/2019 | 15/03/2019 | 18/02/2019 | 14/03/2019 | 0 | TK_Complete | 1112893334 | 175 | 1112893334_175
C730D147BC###0010848 | TT_Task | CBTC/Stage-2 SMCSW - Headway Simulation Report | 03/08/2020 | 28/08/2020 | 15/04/2020 | 19/06/2020 | 0 | TK_Complete | 1112893334 | 175 | 1112893334_175
C730D157BC###0027375 | TT_Task | CBTC/Stage-3 SMCSW - Headway and Simulation (Revision 02) | 08/04/2021 | 05/05/2021 | 15/03/2021 | 26/03/2021 | 0 | TK_Complete | 1112893334 | 175 | 1112893334_175
C730D157BC###0022860 | TT_Task | CBTC/Stage-2 SMTF[N] - TMS (Train Movements Specification) | 01/04/2019 | 01/05/2019 | 25/03/2019 | 29/04/2019 | 0 | TK_Complete | 1112893334 | 174 | 1112893334_174
C730D147BC###0075030 | TT_Task | CBTC/Stage-3 SMTF[N] - Train Movements Specification (TMS) | 09/04/2020 | 06/05/2020 | 12/08/2019 | 06/03/2020 | 0 | TK_Complete | 1112893334 | 174 | 1112893334_174
C730D147BC###0010756 | TT_Task | CBTC/Stage-2 SMCSW - Train Movement Specification (TMS) | 18/02/2019 | 15/03/2019 | 18/02/2019 | 14/03/2019 | 0 | TK_Complete | 1112893334 | 174 | 1112893334_174
C730D147BC###0010810 | TT_Task | CBTC/Stage-2 SMCSW - TMS (Train Movements Specification) | 23/04/2020 | 20/05/2020 | 25/09/2019 | 21/04/2020 | 0 | TK_Complete | 1112893334 | 174 | 1112893334_174
C730D157BC###0027105 | TT_Task | CBTC/Stage-3 SMCSW - TMS (Train Movements Specification) | 16/11/2020 | 27/11/2020 | 11/08/2020 | 14/09/2020 | 0 | TK_Complete | 1112893334 | 174 | 1112893334_174
C730D157BC###N09453 | TT_Task | CBTC/Stage-3 SMCSW - TMS (Train Movements Specification) Review and Updated Submission | 26/04/2021 | 07/05/2021 | 13/04/2021 | 14/09/2021 | 0 | TK_Complete | 1112893334 | 174 | 1112893334_174
C730T147BC###R02285 | TT_Task | CBTC/Stage-3 SMTF[N] - Train Movements Specification (TMS) - Rework | 19/08/2020 | 01/09/2020 | 07/08/2020 | 18/08/2020 | 0 | TK_Complete | 1112893334 | 174 | 1112893334_174
C730D157BC###0022838 | TT_Task | CBTC/Stage-2 SMTF[N] - (SyRSAD)System Requirements Specification and Architecture Description | 18/02/2019 | 15/03/2019 | 18/02/2019 | 14/03/2019 | 0 | TK_Complete | 1112893334 | 173 | 1112893334_173
C730D157BC###0022840 | TT_Task | CBTC/Stage-2 SMTF[N] - SyRSAD (Requirements Specification and Architecture Description) | 01/04/2019 | 29/04/2019 | 18/03/2019 | 26/04/2019 | 0 | TK_Complete | 1112893334 | 173 | 1112893334_173
C730D147BC###0010750 | TT_Task | CBTC/Stage-2 SMCSW - (SyRSAD)System Requirements Specification and Architecture Description | 18/02/2019 | 26/04/2019 | 18/02/2019 | 14/03/2019 | 0 | TK_Complete | 1112893334 | 173 | 1112893334_173
C730D147BC###0010770 | TT_Task | CBTC/Stage-2 SMCSW - SyRSAD (Requirements Specification and Architecture Description)(A8 Milestone) | 01/07/2019 | 05/09/2019 | 01/07/2019 | 10/09/2019 | 0 | TK_Complete | 1112893334 | 173 | 1112893334_173
C730D147BC###0010796 | TT_Task | CBTC/Stage-2 SMCSW - SyRSAD (Requirements Specification and Architecture Description) | 28/02/2020 | 30/04/2020 | 30/09/2019 | 14/04/2020 | 0 | TK_Complete | 1112893334 | 173 | 1112893334_173
C730D157BC###0027045 | TT_Task | CBTC/Stage-3 SMCSW - SyRSAD (Requirements Specification and Architecture Description) | 10/08/2020 | 15/10/2020 | 03/08/2020 | 07/09/2020 | 0 | TK_Complete | 1112893334 | 173 | 1112893334_173
C730D157BC###0022835 | TT_Task | CBTC/Stage-2 SMTF[N] - Signalling Scheme Plan Depot - SMTF (North) - First Release | 16/01/2019 | 15/02/2019 | 15/01/2019 | 14/02/2019 | 0 | TK_Complete | 1112893334 | 172 | 1112893334_172
C730D157BC###0023060 | TT_Task | CBTC/Stage-2 SMTF[N] - Signalling Scheme Plan Depot - SMTF (North) - Second Release | 04/04/2019 | 16/05/2019 | 18/03/2019 | 22/04/2019 | 0 | TK_Complete | 1112893334 | 172 | 1112893334_172
C730D157BC###0049460 | TT_Task | CBTC/Stage-2 SMTF[N] - Signalling Scheme Plan Depot - SMTF (North) - Third Release | 20/06/2019 | 28/06/2019 | 20/06/2019 | 28/06/2019 | 0 | TK_Complete | 1112893334 | 172 | 1112893334_172
C730D147BC###0075200 | TT_Task | CBTC/Stage-3 SMTF[N] - Signalling Scheme Plan Depot | 22/04/2020 | 13/05/2020 | 06/01/2020 | 07/02/2020 | 0 | TK_Complete | 1112893334 | 172 | 1112893334_172
C730D156BC###N582051 | TT_Task | As Built SMTF[N] - Signalling Scheme Plan Depot - SMTF (North) (MS#2) ***N/A*** | 25/11/2021 | 24/12/2021 | 24/12/2021 | 24/12/2021 | 0 | TK_Complete | 1112893334 | 172 | 1112893334_172
C730D156BC###N582061 | TT_Task | As Built SMTF[N] - Signalling Scheme Plan Depot - SMTF (North) (MS#4) | 20/05/2022 | 09/06/2022 | nan | nan | 239 | TK_NotStart | 1112893334 | 172 | 1112893334_172
C730T147BC###R02225 | TT_Task | CBTC/Stage-3 SMTF[N] - Signalling Scheme Plan - Rework | 10/08/2020 | 28/08/2020 | 09/07/2020 | 07/08/2020 | 0 | TK_Complete | 1112893334 | 172 | 1112893334_172
C730D157BC###0022720 | TT_Task | CBTC/Stage-2 SMTF[N] - System Naming Rules (SyNR) | 04/04/2019 | 03/05/2019 | 04/04/2019 | 30/04/2019 | 0 | TK_Complete | 1112893334 | 171 | 1112893334_171
C730D147BC###0075000 | TT_Task | CBTC/Stage-3 SMTF[N] - System Naming Rules (SyNR) | 15/10/2019 | 28/10/2019 | 01/11/2019 | 14/02/2020 | 0 | TK_Complete | 1112893334 | 171 | 1112893334_171
C730D157BC###0022640 | TT_Task | CBTC/Stage-2 SMTF[N] - System Addressing Plan (SyAP) | 01/04/2019 | 08/05/2019 | 18/03/2019 | 17/04/2019 | 0 | TK_Complete | 1112893334 | 170 | 1112893334_170
C730D147BC###0010820 | TT_Task | CBTC/Stage-2 SMCSW - System Addressing Plan (SyAP) | 12/05/2020 | 25/05/2020 | 16/03/2020 | 06/04/2020 | 0 | TK_Complete | 1112893334 | 170 | 1112893334_170
C720D147CF###0030440 | TT_Task | Trains/Stage-2 - KE analysis and report submission for SMCSW mainline | 25/02/2020 | 29/04/2020 | 08/11/2019 | 13/01/2020 | 0 | TK_Complete | 1112893334 | 17 | 1112893334_17
C720D147CF###0030450 | TT_Task | Trains/Stage-2 - Traction calculation for SMCSW mainline | 08/11/2019 | 13/01/2020 | 08/11/2019 | 13/01/2020 | 0 | TK_Complete | 1112893334 | 17 | 1112893334_17
C720D147CF###0030460 | TT_Task | Trains/Stage-2 - Bogie dynamic calculation for SMCSW mainline | 25/03/2020 | 28/05/2020 | 08/11/2019 | 17/12/2019 | 0 | TK_Complete | 1112893334 | 17 | 1112893334_17
C720D147CF###0030490 | TT_Task | Trains/Stage-2 - Brake calculation for SMCSW mainline ***Merged with Stage-3*** | 25/05/2020 | 29/06/2020 | 25/05/2020 | 25/05/2020 | 0 | TK_Complete | 1112893334 | 17 | 1112893334_17
C720D147CF###0030500 | TT_Task | Trains/Stage-2 - Gangway curving for SMCSW mainline ***Merged with Stage-3*** | 25/05/2020 | 29/06/2020 | 25/05/2020 | 25/05/2020 | 0 | TK_Complete | 1112893334 | 17 | 1112893334_17
C730D157BC###0022520 | TT_Task | CBTC/Stage-2 SMTF[N] - System PBS | 23/04/2019 | 14/05/2019 | 23/04/2019 | 16/05/2019 | 0 | TK_Complete | 1112893334 | 169 | 1112893334_169
C730D147BC###0075525 | TT_Task | CBTC/Stage-3 SMTF[N] - System PBS | 28/05/2020 | 10/06/2020 | 27/04/2020 | 08/05/2020 | 0 | TK_Complete | 1112893334 | 169 | 1112893334_169
C730D147BC###0075440 | TT_Task | CBTC/Stage-3 SMTF[N] - ATC PBS (Internal) | 06/07/2020 | 13/07/2020 | 06/04/2020 | 10/04/2020 | 0 | TK_Complete | 1112893334 | 169 | 1112893334_169
C730D147BC###0075345 | TT_Task | CBTC/Stage-3 SMTF[N] - CBI PBS | 22/04/2020 | 29/04/2020 | 05/02/2020 | 11/02/2020 | 0 | TK_Complete | 1112893334 | 169 | 1112893334_169
C730D147BC###0075340 | TT_Task | CBTC/Stage-3 SMTF[N] - MSS PBS | 04/05/2020 | 29/05/2020 | 06/04/2020 | 17/04/2020 | 0 | TK_Complete | 1112893334 | 169 | 1112893334_169
C730D147BC###0075410 | TT_Task | CBTC/Stage-3 SMTF[N] - DCS PBS | 22/04/2020 | 06/05/2020 | 04/02/2020 | 14/02/2020 | 0 | TK_Complete | 1112893334 | 169 | 1112893334_169
C730D147BC###0075330 | TT_Task | CBTC/Stage-3 SMTF[N] - ATS PBS | 04/05/2020 | 15/05/2020 | 01/04/2020 | 29/04/2020 | 0 | TK_Complete | 1112893334 | 169 | 1112893334_169
C730D147BC###0075485 | TT_Task | CBTC/Stage-3 SMTF[N] - CCTV MMI | 01/07/2020 | 13/07/2020 | 25/02/2020 | 25/03/2020 | 0 | TK_Complete | 1112893334 | 169 | 1112893334_169
C730D147BC###0075490 | TT_Task | CBTC/Stage-3 SMTF[N] - CCTV PBS | 26/06/2020 | 16/07/2020 | 13/04/2020 | 23/04/2020 | 0 | TK_Complete | 1112893334 | 169 | 1112893334_169
C730D157BC###0022510 | TT_Task | CBTC/Stage-2 SMTF[N] - Migration Plan | 01/04/2019 | 13/05/2019 | 18/03/2019 | 24/04/2019 | 0 | TK_Complete | 1112893334 | 168 | 1112893334_168
C730D147BC###0075005 | TT_Task | CBTC/Stage-3 SMTF[N] - Migration Plan | 31/12/2019 | 10/02/2020 | 01/07/2019 | 12/02/2020 | 0 | TK_Complete | 1112893334 | 168 | 1112893334_168
C730D147BC###0010814 | TT_Task | CBTC/Stage-2 SMCSW - Migration Plan for Phase1 | 27/04/2020 | 22/05/2020 | 13/04/2020 | 27/07/2020 | 0 | TK_Complete | 1112893334 | 168 | 1112893334_168
C730D157BC###0027039 | TT_Task | CBTC/Stage-3 SMCSW - Migration Plan | 14/01/2021 | 11/02/2021 | 15/12/2020 | 12/01/2021 | 0 | TK_Complete | 1112893334 | 168 | 1112893334_168
C730T147BC###R02205 | TT_Task | CBTC/Stage-3 SMTF[N] - Migration Plan - Rework | 27/07/2020 | 07/08/2020 | 16/06/2020 | 08/07/2020 | 0 | TK_Complete | 1112893334 | 168 | 1112893334_168
C730D147CT###0035440 | TT_Task | Stage3 SMTF(N) Initial survey/desktop audit As-built drawing - Room Layout - DSER1 | 25/05/2020 | 06/07/2020 | 04/05/2020 | 06/05/2020 | 0 | TK_Complete | 1112893334 | 167 | 1112893334_167
C730D156BC###0036388 | TT_Task | Stage3 (BZZ) Initial survey/desktop audit Layout for Station Control Room | 25/08/2020 | 06/10/2020 | 04/08/2020 | 27/08/2020 | 0 | TK_Complete | 1112893334 | 167 | 1112893334_167
C730D156BC###0036295 | TT_Task | Stage3 (CHW) Initial survey/desktop audit As-built drawing - Room Layout | 25/11/2020 | 12/01/2021 | 26/10/2020 | 06/11/2020 | 0 | TK_Complete | 1112893334 | 167 | 1112893334_167
C730D147CT###0035425 | TT_Task | Stage3 SMTF(N) Initial survey/desktop audit Delivery Route to signalling room / temporary storage | 27/04/2020 | 05/06/2020 | 11/12/2019 | 17/01/2020 | 0 | TK_Complete | 1112893334 | 166 | 1112893334_166
C730D147CT###0035470 | TT_Task | Stage3 SMTF(N) Initial survey/desktop audit Delivery Route to signalling room / temporary storage-OCC | 25/05/2020 | 06/07/2020 | 04/05/2020 | 06/05/2020 | 0 | TK_Complete | 1112893334 | 166 | 1112893334_166
C730D156BC###0035812 | TT_Task | Stage3 (CST) Initial survey/desktop audit Delivery Route to signalling room / temporary storage | 25/08/2020 | 06/10/2020 | 27/07/2020 | 24/08/2020 | 0 | TK_Complete | 1112893334 | 166 | 1112893334_166
C730D156BC###0036340 | TT_Task | Stage3 (VIC) Initial survey/desktop audit Delivery Route to signalling room / temporary storage | 25/08/2020 | 06/10/2020 | 29/07/2020 | 26/08/2020 | 0 | TK_Complete | 1112893334 | 166 | 1112893334_166
C730D156BC###0036385 | TT_Task | Stage3 (BZZ) Initial survey/desktop audit Delivery Route to signalling room / temporary storage | 25/08/2020 | 06/10/2020 | 03/08/2020 | 27/08/2020 | 0 | TK_Complete | 1112893334 | 166 | 1112893334_166
C730D156BC###0036403 | TT_Task | Stage3 (MPL) Initial survey/desktop audit Delivery Route to signalling room / temporary storage | 25/08/2020 | 06/10/2020 | 06/08/2020 | 28/08/2020 | 0 | TK_Complete | 1112893334 | 166 | 1112893334_166
C730D156BC###0035770 | TT_Task | Stage3 (PIT) Initial survey/desktop audit Delivery Route to signalling room / temporary storage | 24/08/2020 | 02/10/2020 | 24/08/2020 | 25/08/2020 | 0 | TK_Complete | 1112893334 | 166 | 1112893334_166
C730D156BC###0035791 | TT_Task | Stage3 (WLO) Initial survey/desktop audit Delivery Route to signalling room / temporary storage | 25/02/2021 | 07/04/2021 | 15/12/2020 | 23/12/2020 | 0 | TK_Complete | 1112893334 | 166 | 1112893334_166
C730D156BC###0036433 | TT_Task | Stage3 (CSM) Initial survey/desktop audit Delivery Route to signalling room / temporary storage | 11/12/2020 | 28/01/2021 | 18/05/2020 | 19/06/2020 | 0 | TK_Complete | 1112893334 | 166 | 1112893334_166
C730D156BC###0036409 | TT_Task | Stage3 (SSJ) Initial survey/desktop audit Delivery Route to signalling room / temporary storage | 25/08/2020 | 06/10/2020 | 28/07/2020 | 03/08/2020 | 0 | TK_Complete | 1112893334 | 166 | 1112893334_166
C730D156BC###0035914 | TT_Task | Stage3 (SMTF-S) Initial survey/desktop audit Delivery Route to signalling room / temporary storage | 25/09/2020 | 09/11/2020 | 03/08/2020 | 25/08/2020 | 0 | TK_Complete | 1112893334 | 166 | 1112893334_166
C730D147CT###0035415 | TT_Task | Stage3 SMTF(N) Initial survey Position and specs of Isolators, MET, False Floor, Drilling/non-drilling zone | 27/04/2020 | 05/06/2020 | 10/12/2019 | 09/01/2020 | 0 | TK_Complete | 1112893334 | 165 | 1112893334_165
C730D156BC###0035806 | TT_Task | Stage3 (CST) Initial survey/desktop audit Position and specs of Isolators, MET, False Floor, Drilling/non-drilling zone | 25/08/2020 | 06/10/2020 | 28/07/2020 | 24/08/2020 | 0 | TK_Complete | 1112893334 | 165 | 1112893334_165
C730D156BC###0036334 | TT_Task | Stage3 (VIC) Initial survey/desktop audit Position and specs of Isolators, MET, False Floor, Drilling/non-drilling zone | 25/08/2020 | 06/10/2020 | 30/07/2020 | 26/08/2020 | 0 | TK_Complete | 1112893334 | 165 | 1112893334_165
C730D156BC###0036379 | TT_Task | Stage3 (BZZ) Initial survey/desktop audit Position and specs of Isolators, MET, False Floor, Drilling/non-drilling zone | 25/08/2020 | 06/10/2020 | 03/08/2020 | 27/08/2020 | 0 | TK_Complete | 1112893334 | 165 | 1112893334_165
C730D156BC###0036397 | TT_Task | Stage3 (MPL) Initial survey/desktop audit Position and specs of Isolators, MET, False Floor, Drilling/non-drilling zone | 25/08/2020 | 06/10/2020 | 05/08/2020 | 28/08/2020 | 0 | TK_Complete | 1112893334 | 165 | 1112893334_165
C730D156BC###0035764 | TT_Task | Stage3 (PIT) Initial survey/desktop audit Position and specs of Isolators, MET, False Floor, Drilling/non-drilling zone | 24/08/2020 | 02/10/2020 | 24/08/2020 | 04/09/2020 | 0 | TK_Complete | 1112893334 | 165 | 1112893334_165
C730D156BC###0035785 | TT_Task | Stage3 (WLO) Initial survey/desktop audit Position and specs of Isolators, MET, False Floor, Drilling/non-drilling zone | 25/02/2021 | 07/04/2021 | 15/12/2020 | 23/12/2020 | 0 | TK_Complete | 1112893334 | 165 | 1112893334_165
C730D156BC###0036427 | TT_Task | Stage3 (CSM) Initial survey/desktop audit Position and specs of Isolators, MET, False Floor, Drilling/non-drilling zone | 11/12/2020 | 28/01/2021 | 24/02/2020 | 20/03/2020 | 0 | TK_Complete | 1112893334 | 165 | 1112893334_165
C730D156BC###0036415 | TT_Task | Stage3 (SSJ) Initial survey/desktop audit Position and specs of Isolators, MET, False Floor, Drilling/non-drilling zone | 25/02/2021 | 07/04/2021 | 12/01/2021 | 12/01/2021 | 0 | TK_Complete | 1112893334 | 165 | 1112893334_165
C730D156BC###0035932 | TT_Task | Stage3 [SMTF-S] Initial survey Position and specs of Isolators, MET, False Floor, Drilling/non-drilling zone | 25/09/2020 | 09/11/2020 | 03/08/2020 | 25/08/2020 | 0 | TK_Complete | 1112893334 | 165 | 1112893334_165
C730D147CT###0035410 | TT_Task | Stage3 SMTF(N) Initial survey/desktop audit Room Plan and location of SIG Room | 27/04/2020 | 05/06/2020 | 20/11/2019 | 10/12/2019 | 0 | TK_Complete | 1112893334 | 164 | 1112893334_164
C730D147CT###0035465 | TT_Task | Stage3 SMTF(N) Initial survey/desktop audit Room Plan and location of SIG Room-OCC | 25/05/2020 | 06/07/2020 | 04/05/2020 | 06/05/2020 | 0 | TK_Complete | 1112893334 | 164 | 1112893334_164
C730D156BC###0035800 | TT_Task | Stage3 (CST) Initial survey/desktop audit Room Plan and location of SIG Room | 25/08/2020 | 06/10/2020 | 27/07/2020 | 24/08/2020 | 0 | TK_Complete | 1112893334 | 164 | 1112893334_164
C730D156BC###0036328 | TT_Task | Stage3 (VIC) Initial survey/desktop audit Room Plan and location of SIG Room | 25/08/2020 | 06/10/2020 | 29/07/2020 | 26/08/2020 | 0 | TK_Complete | 1112893334 | 164 | 1112893334_164
C730D156BC###0036373 | TT_Task | Stage3 (BZZ) Initial survey/desktop audit Room Plan and location of SIG Room | 25/08/2020 | 06/10/2020 | 31/07/2020 | 27/08/2020 | 0 | TK_Complete | 1112893334 | 164 | 1112893334_164
C730D156BC###0036391 | TT_Task | Stage3 (MPL) Initial survey/desktop audit Room Plan and location of SIG Room | 25/08/2020 | 06/10/2020 | 05/08/2020 | 28/08/2020 | 0 | TK_Complete | 1112893334 | 164 | 1112893334_164
C730D156BC###0035758 | TT_Task | Stage3 (PIT) Initial survey/desktop audit Room Plan and location of SIG Room | 25/08/2020 | 06/10/2020 | 24/08/2020 | 31/08/2020 | 0 | TK_Complete | 1112893334 | 164 | 1112893334_164
C730D156BC###0035779 | TT_Task | Stage3 (WLO) Initial survey/desktop audit Room Plan and location of SIG Room | 25/11/2020 | 12/01/2021 | 23/11/2020 | 26/11/2020 | 0 | TK_Complete | 1112893334 | 164 | 1112893334_164
C730D156BC###0036421 | TT_Task | Stage3 (CSM) Initial survey/desktop audit Room Plan and location of SIG Room | 25/08/2020 | 06/10/2020 | 27/07/2020 | 25/08/2020 | 0 | TK_Complete | 1112893334 | 164 | 1112893334_164
C730D156BC###0036406 | TT_Task | Stage3 (SSJ) Initial survey/desktop audit Room Plan and location of SIG Room | 25/08/2020 | 06/10/2020 | 28/07/2020 | 03/08/2020 | 0 | TK_Complete | 1112893334 | 164 | 1112893334_164
C730D156BC###0035836 | TT_Task | Stage3 (SMTF-S) Initial survey/desktop audit Room Plan and location of SIG Room | 25/09/2020 | 09/11/2020 | 10/08/2020 | 25/08/2020 | 0 | TK_Complete | 1112893334 | 164 | 1112893334_164
C730D147CT###0035365 | TT_Task | Stage3 SMTF(N) Initial survey/desktop audit Architecture of buidlings in depot | 27/04/2020 | 05/06/2020 | 10/02/2020 | 06/03/2020 | 0 | TK_Complete | 1112893334 | 163 | 1112893334_163
C730D156BC###0035920 | TT_Task | Stage3 (SMTF-S) Initial survey/desktop audit Architecture of buidlings in depot | 25/09/2020 | 09/11/2020 | 03/08/2020 | 25/08/2020 | 0 | TK_Complete | 1112893334 | 163 | 1112893334_163
C730D147CT###0035350 | TT_Task | Stage3 SMTF(N) Initial survey/desktop audit Cross Section of Transit Space | 27/04/2020 | 05/06/2020 | 17/12/2019 | 09/01/2020 | 0 | TK_Complete | 1112893334 | 162 | 1112893334_162
C730D156BC###0036103 | TT_Task | Stage3 (SSJ) Initial survey/desktop audit Cross Section of Transit Space(closed as per SoD Addendum Dt 120121) | 25/02/2021 | 07/04/2021 | 12/01/2021 | 12/01/2021 | 0 | TK_Complete | 1112893334 | 162 | 1112893334_162
C730D156BC###0036226 | TT_Task | Stage3 (SSJ) Initial survey/desktop audit PSD pannel arrangement (closed as per SoD Addendum Dt 120121) | 25/02/2021 | 07/04/2021 | 12/01/2021 | 12/01/2021 | 0 | TK_Complete | 1112893334 | 162 | 1112893334_162
C730D156BC###0035929 | TT_Task | Stage3 (SMTF-S) Initial survey/desktop audit Cross Section of Transit Space | 25/09/2020 | 09/11/2020 | 03/08/2020 | 25/08/2020 | 0 | TK_Complete | 1112893334 | 162 | 1112893334_162
C730D156BC###0036139 | TT_Task | Stage3 (LW-T) Initial survey/desktop audit Cross Section of Transit Space | 25/02/2021 | 07/04/2021 | 12/01/2021 | 12/01/2021 | 0 | TK_Complete | 1112893334 | 162 | 1112893334_162
C730D147CT###0035345 | TT_Task | Stage3 SMTF(N) Initial survey/desktop audit Trackforms (type, specs, drill/non-drill) | 27/04/2020 | 05/06/2020 | 10/12/2019 | 09/01/2020 | 0 | TK_Complete | 1112893334 | 161 | 1112893334_161
C730D156BC###0036088 | TT_Task | Stage3 (SSJ) Initial survey/desktop audit Trackforms (type, specs, drill/non-drill) | 25/09/2020 | 09/11/2020 | 10/08/2020 | 24/08/2020 | 0 | TK_Complete | 1112893334 | 161 | 1112893334_161
C730D156BC###0035911 | TT_Task | Stage3 (SMTF-S) Initial survey/desktop audit Trackforms (type, specs, drill/non-drill) | 25/08/2020 | 06/10/2020 | 22/08/2020 | 26/08/2020 | 0 | TK_Complete | 1112893334 | 161 | 1112893334_161
C730D156BC###0036133 | TT_Task | Stage3 (LW-T) Initial survey/desktop audit Trackforms (type, specs, drill/non-drill) | 25/08/2020 | 06/10/2020 | 24/08/2020 | 25/08/2020 | 0 | TK_Complete | 1112893334 | 161 | 1112893334_161
C730D147CT###0035340 | TT_Task | Stage3 SMTF(N) Initial survey/desktop audit Corridor civil details (fencing, gates, bridge, drainage, walkway etc..) | 27/04/2020 | 05/06/2020 | 22/01/2020 | 19/02/2020 | 0 | TK_Complete | 1112893334 | 160 | 1112893334_160
C730D156BC###0036085 | TT_Task | Stage3 (SSJ) Initial survey/desktop audit Corridor civil details (fencing, gates, bridge, drainage, walkway etc..) | 25/08/2020 | 06/10/2020 | 27/07/2020 | 24/08/2020 | 0 | TK_Complete | 1112893334 | 160 | 1112893334_160
C730D156BC###0035908 | TT_Task | Stage3 (SMTF-S) Initial survey/desktop audit Corridor civil details (fencing, gates, bridge, drainage, walkway etc..) | 25/08/2020 | 06/10/2020 | 20/08/2020 | 26/08/2020 | 0 | TK_Complete | 1112893334 | 160 | 1112893334_160
C730D156BC###0036130 | TT_Task | Stage3 (LW-T) Initial survey/desktop audit Corridor civil details (fencing, gates, bridge, drainage, walkway etc..) | 25/02/2021 | 07/04/2021 | 12/01/2021 | 12/01/2021 | 0 | TK_Complete | 1112893334 | 160 | 1112893334_160
C720D147CF###0030510 | TT_Task | Trains/Stage-2 - Interface freeze TDE | 25/03/2020 | 07/05/2020 | 26/02/2020 | 24/03/2020 | 0 | TK_Complete | 1112893334 | 16 | 1112893334_16
C720D147CF###0030520 | TT_Task | Trains/Stage-2 - Interface freeze TSE | 26/02/2020 | 24/03/2020 | 26/02/2020 | 20/03/2020 | 0 | TK_Complete | 1112893334 | 16 | 1112893334_16
C720D147CF###0030570 | TT_Task | Trains/Stage-2 - Interface freeze TCE | 26/02/2020 | 07/04/2020 | 26/02/2020 | 24/03/2020 | 0 | TK_Complete | 1112893334 | 16 | 1112893334_16
C730D147CT###0035335 | TT_Task | Stage3 SMTF(N) Initial survey/desktop audit details about platform for stabling track | 27/04/2020 | 05/06/2020 | 13/01/2020 | 10/02/2020 | 0 | TK_Complete | 1112893334 | 159 | 1112893334_159
C730D156BC###0035572 | TT_Task | Stage3 [City] Initial survey for design/desktop audit TIDS and VIDS for SMCSW/GF mainline (Design Consideration) | 25/02/2021 | 07/04/2021 | 25/11/2020 | 25/11/2020 | 0 | TK_Complete | 1112893334 | 159 | 1112893334_159
C730D156BC###0035575 | TT_Task | Stage3 [SMTF-S] Initial survey for design/desktop audit Depot access and VIDS details for SMTF [S] | 25/02/2021 | 07/04/2021 | 12/01/2021 | 12/01/2021 | 0 | TK_Complete | 1112893334 | 159 | 1112893334_159
C730D156BC###0035926 | TT_Task | Stage3 (SMTF-S) Initial survey/desktop audit details about platform for stabling track | 25/09/2020 | 09/11/2020 | 03/08/2020 | 25/08/2020 | 0 | TK_Complete | 1112893334 | 159 | 1112893334_159
C730D147CT###0035325 | TT_Task | Stage3 SMTF(N) Initial survey/desktop audit Details about drilling zone (allowed size, depth) | 27/04/2020 | 05/06/2020 | 13/04/2020 | 22/04/2020 | 0 | TK_Complete | 1112893334 | 158 | 1112893334_158
C730D156BC###0036100 | TT_Task | Stage3 (SSJ) Initial survey/desktop audit Details about drilling zone (allowed size, depth?) (SoD Addendum Dt 120121) | 25/02/2021 | 07/04/2021 | 12/01/2021 | 12/01/2021 | 0 | TK_Complete | 1112893334 | 158 | 1112893334_158
C730D156BC###0035923 | TT_Task | Stage3 (SMTF-S) Initial survey/desktop audit Details about drilling zone (allowed size, depth?) | 25/09/2020 | 09/11/2020 | 03/08/2020 | 25/08/2020 | 0 | TK_Complete | 1112893334 | 158 | 1112893334_158
C730D156BC###0036142 | TT_Task | Stage3 (LW-T) Initial survey/desktop audit Details about drilling zone (allowed size, depth?) | 25/08/2020 | 06/10/2020 | 24/08/2020 | 25/08/2020 | 0 | TK_Complete | 1112893334 | 158 | 1112893334_158
C730D147CT###0035310 | TT_Task | Stage3 SMTF(N) Initial survey/desktop audit Horizontal/Vertical Track Alignment, Turnout Design | 25/05/2020 | 06/07/2020 | 04/05/2020 | 06/05/2020 | 0 | TK_Complete | 1112893334 | 157 | 1112893334_157
C730D156BC###0036076 | TT_Task | Stage3 (SSJ) Initial survey/desktop audit Horizontal/Vertical Track Alignment, Turnout design | 25/11/2020 | 12/01/2021 | 27/10/2020 | 28/11/2020 | 0 | TK_Complete | 1112893334 | 157 | 1112893334_157
C730D156BC###0035830 | TT_Task | Stage3 (SMTF-S) Initial survey/desktop audit Horizontal/Vertical Track Alignment, Turnout configuration | 25/08/2020 | 06/10/2020 | 20/08/2020 | 25/08/2020 | 0 | TK_Complete | 1112893334 | 157 | 1112893334_157
C730D156BC###0035821 | TT_Task | Stage3 (LW-T) Initial survey/desktop audit Horizontal/Vertical Track Alignment, Turnout configuration | 25/08/2020 | 06/10/2020 | 24/08/2020 | 25/08/2020 | 0 | TK_Complete | 1112893334 | 157 | 1112893334_157
C730D147CT###0035155 | TT_Task | Stage3 SMTF(N) Initial survey/desktop audit OHW Alignment / Traction Diagram | 31/10/2019 | 11/12/2019 | 08/07/2019 | 16/08/2019 | 0 | TK_Complete | 1112893334 | 156 | 1112893334_156
C730D156BC###0036091 | TT_Task | Stage3 (SSJ) Initial survey/desktop audit OHW Alignment / Traction Diagram | 25/08/2020 | 06/10/2020 | 27/07/2020 | 25/08/2020 | 0 | TK_Complete | 1112893334 | 156 | 1112893334_156
C730D156BC###0035569 | TT_Task | Stage3 (SMTF-S) Initial survey/desktop audit OHW Alignment / Traction Diagram | 25/08/2020 | 06/10/2020 | 22/08/2020 | 24/08/2020 | 0 | TK_Complete | 1112893334 | 156 | 1112893334_156
C730D156BC###0035824 | TT_Task | Stage3 (LW-T) Initial survey/desktop audit OHW Alignment / Traction Diagram | 25/08/2020 | 06/10/2020 | 24/08/2020 | 25/08/2020 | 0 | TK_Complete | 1112893334 | 156 | 1112893334_156
C730D147CT###0035435 | TT_Task | Stage3 SMTF(N) Alstom review As-built drawing - Room Layout - DSER1 | 25/05/2020 | 05/06/2020 | 29/04/2020 | 30/04/2020 | 0 | TK_Complete | 1112893334 | 155 | 1112893334_155
C730D156BC###0035530 | TT_Task | Stage2 (CHW) alstom review As-built drawing - Room Layout | 25/06/2020 | 01/07/2020 | 02/06/2020 | 09/06/2020 | 0 | TK_Complete | 1112893334 | 155 | 1112893334_155
C730D156BC###0036262 | TT_Task | Stage3 [BZZ] Alstom review Layout for Station Control Room | 25/08/2020 | 21/09/2020 | 08/06/2020 | 30/06/2020 | 0 | TK_Complete | 1112893334 | 155 | 1112893334_155
C730D156BC###0036175 | TT_Task | Stage3 (CHW) alstom review As-built drawing - Room Layout | 25/11/2020 | 22/12/2020 | 26/10/2020 | 06/11/2020 | 0 | TK_Complete | 1112893334 | 155 | 1112893334_155
C730D147CT###0035405 | TT_Task | Stage3 SMTF(N) Alstom review Delivery Route to signalling room / temporary storage | 25/02/2020 | 09/03/2020 | 21/10/2019 | 04/11/2019 | 0 | TK_Complete | 1112893334 | 154 | 1112893334_154
C730D147CT###0035460 | TT_Task | Stage3 SMTF(N) Alstom review Delivery Route to signalling room / temporary storage-OCC | 25/05/2020 | 05/06/2020 | 29/04/2020 | 30/04/2020 | 0 | TK_Complete | 1112893334 | 154 | 1112893334_154
C730D156BC###0035719 | TT_Task | Stage2 (SMTF-S) Alstom review Delivery Route to signalling room / temporary storage | 25/06/2020 | 08/07/2020 | 16/06/2020 | 22/06/2020 | 0 | TK_Complete | 1112893334 | 154 | 1112893334_154
C730D156BC###0035707 | TT_Task | Stage3 [CST] Alstom review Delivery Route to signalling room / temporary storage | 25/08/2020 | 21/09/2020 | 06/04/2020 | 22/05/2020 | 0 | TK_Complete | 1112893334 | 154 | 1112893334_154
C730D156BC###0036214 | TT_Task | Stage3 [VIC] Alstom review Delivery Route to signalling room / temporary storage | 25/08/2020 | 21/09/2020 | 01/07/2020 | 06/07/2020 | 0 | TK_Complete | 1112893334 | 154 | 1112893334_154
C730D156BC###0036256 | TT_Task | Stage3 [BZZ] Alstom review Delivery Route to signalling room / temporary storage | 25/08/2020 | 21/09/2020 | 08/06/2020 | 26/06/2020 | 0 | TK_Complete | 1112893334 | 154 | 1112893334_154
C730D156BC###0036292 | TT_Task | Stage3 [MPL] Alstom review Delivery Route to signalling room / temporary storage | 25/08/2020 | 21/09/2020 | 23/06/2020 | 01/07/2020 | 0 | TK_Complete | 1112893334 | 154 | 1112893334_154
C730D156BC###0035644 | TT_Task | Stage3 [PIT] Alstom review Delivery Route to signalling room / temporary storage | 25/08/2020 | 21/09/2020 | 02/07/2020 | 22/07/2020 | 0 | TK_Complete | 1112893334 | 154 | 1112893334_154
C730D156BC###0035665 | TT_Task | Stage3 [WLO] Alstom review Delivery Route to signalling room / temporary storage | 01/01/2021 | 28/01/2021 | 15/12/2020 | 23/12/2020 | 0 | TK_Complete | 1112893334 | 154 | 1112893334_154
C730D156BC###0036370 | TT_Task | Stage3 [CSM] Alstom review Delivery Route to signalling room / temporary storage | 01/01/2021 | 28/01/2021 | 18/05/2020 | 19/06/2020 | 0 | TK_Complete | 1112893334 | 154 | 1112893334_154
C730D156BC###0036310 | TT_Task | Stage3 [SSJ] Alstom review Delivery Route to signalling room / temporary storage | 25/08/2020 | 21/09/2020 | 10/02/2020 | 11/03/2020 | 0 | TK_Complete | 1112893334 | 154 | 1112893334_154
C730D156BC###0035860 | TT_Task | Stage3 (SMTF-S) alstom review Delivery Route to signalling room / temporary storage | 25/08/2020 | 21/09/2020 | 02/07/2020 | 25/08/2020 | 0 | TK_Complete | 1112893334 | 154 | 1112893334_154
C730D147CT###0035400 | TT_Task | Stage3 SMTF(N) Alstom review Location of Building Services (AC, AC Nozzle, Lighting, Gas Surp., pipes, Control Pannel..) | 25/02/2020 | 09/03/2020 | 21/10/2019 | 04/11/2019 | 0 | TK_Complete | 1112893334 | 153 | 1112893334_153
C730D147CT###0035420 | TT_Task | Stage3 SMTF(N) Initial survey Location of Building Services (AC, AC Nozzle, Lighting, Gas Surp., pipes, Control Pannel) | 27/04/2020 | 05/06/2020 | 14/11/2019 | 04/12/2019 | 0 | TK_Complete | 1112893334 | 153 | 1112893334_153
C730D156BC###0035704 | TT_Task | Stage3 [CST] Alstom review Location of Building Services (AC, AC Nozzle, Lighting, Gas Surp., pipes, Control Pannel..) | 25/08/2020 | 21/09/2020 | 06/04/2020 | 04/05/2020 | 0 | TK_Complete | 1112893334 | 153 | 1112893334_153
C730D156BC###0036211 | TT_Task | Stage3 [VIC] Alstom review Location of Building Services (AC, AC Nozzle, Lighting, Gas Surp., pipes, Control Pannel..) | 23/11/2020 | 18/12/2020 | 10/06/2020 | 18/06/2020 | 0 | TK_Complete | 1112893334 | 153 | 1112893334_153
C730D156BC###0036253 | TT_Task | Stage3 [BZZ] Alstom review Location of Building Services (AC, AC Nozzle, Lighting, Gas Surp., pipes, Control Pannel..) | 25/08/2020 | 21/09/2020 | 15/06/2020 | 29/06/2020 | 0 | TK_Complete | 1112893334 | 153 | 1112893334_153
C730D156BC###0036289 | TT_Task | Stage3 [MPL] Alstom review Location of Building Services (AC, AC Nozzle, Lighting, Gas Surp., pipes, Control Pannel..) | 25/08/2020 | 21/09/2020 | 13/07/2020 | 14/07/2020 | 0 | TK_Complete | 1112893334 | 153 | 1112893334_153
C730D156BC###0035641 | TT_Task | Stage3 [PIT] Alstom review Location of Building Services (AC, AC Nozzle, Lighting, Gas Surp., pipes, Control Pannel..) | 25/08/2020 | 21/09/2020 | 31/07/2020 | 17/08/2020 | 0 | TK_Complete | 1112893334 | 153 | 1112893334_153
C730D156BC###0035662 | TT_Task | Stage3 [WLO] Alstom review Location of Building Services (AC, AC Nozzle, Lighting, Gas Surp., pipes, Control Pannel..) | 01/01/2021 | 28/01/2021 | 15/12/2020 | 23/12/2020 | 0 | TK_Complete | 1112893334 | 153 | 1112893334_153
C730D156BC###0036367 | TT_Task | Stage3 [CSM] Alstom review Location of Building Services (AC, AC Nozzle, Lighting, Gas Surp., pipes, Control Pannel..) | 01/01/2021 | 28/01/2021 | 24/02/2020 | 27/03/2020 | 0 | TK_Complete | 1112893334 | 153 | 1112893334_153
C730D156BC###0036325 | TT_Task | Stage3 [SSJ] Alstom review Location of Building Services (AC, AC Nozzle, Lighting, Gas Surp., pipes, Control Pannel..) | 25/02/2021 | 24/03/2021 | 12/01/2021 | 12/01/2021 | 0 | TK_Complete | 1112893334 | 153 | 1112893334_153
C730D147CT###0035395 | TT_Task | Stage3 SMTF(N) Alstom review Position and specs of Isolators, MET, False Floor, Drilling/non-drilling zone | 25/02/2020 | 09/03/2020 | 21/10/2019 | 04/11/2019 | 0 | TK_Complete | 1112893334 | 152 | 1112893334_152
C730D156BC###0035701 | TT_Task | Stage3 [CST] Alstom review Position and specs of Isolators, MET, False Floor, Drilling/non-drilling zone | 25/08/2020 | 21/09/2020 | 30/04/2020 | 04/05/2020 | 0 | TK_Complete | 1112893334 | 152 | 1112893334_152
C730D156BC###0036208 | TT_Task | Stage3 [VIC] Alstom review Position and specs of Isolators, MET, False Floor, Drilling/non-drilling zone | 25/08/2020 | 21/09/2020 | 01/06/2020 | 18/06/2020 | 0 | TK_Complete | 1112893334 | 152 | 1112893334_152
C730D156BC###0036250 | TT_Task | Stage3 [BZZ] Alstom review Position and specs of Isolators, MET, False Floor, Drilling/non-drilling zone | 25/08/2020 | 21/09/2020 | 21/05/2020 | 29/05/2020 | 0 | TK_Complete | 1112893334 | 152 | 1112893334_152
C730D156BC###0036286 | TT_Task | Stage3 [MPL] Alstom review Position and specs of Isolators, MET, False Floor, Drilling/non-drilling zone | 25/08/2020 | 21/09/2020 | 13/07/2020 | 14/07/2020 | 0 | TK_Complete | 1112893334 | 152 | 1112893334_152
C730D156BC###0035638 | TT_Task | Stage3 [PIT] Alstom review Position and specs of Isolators, MET, False Floor, Drilling/non-drilling zone | 25/08/2020 | 21/09/2020 | 31/07/2020 | 17/08/2020 | 0 | TK_Complete | 1112893334 | 152 | 1112893334_152
C730D156BC###0035659 | TT_Task | Stage3 [WLO] Alstom review Position and specs of Isolators, MET, False Floor, Drilling/non-drilling zone | 01/01/2021 | 28/01/2021 | 15/12/2020 | 23/12/2020 | 0 | TK_Complete | 1112893334 | 152 | 1112893334_152
C730D156BC###0036364 | TT_Task | Stage3 [CSM] Alstom review Position and specs of Isolators, MET, False Floor, Drilling/non-drilling zone | 01/01/2021 | 28/01/2021 | 24/02/2020 | 20/03/2020 | 0 | TK_Complete | 1112893334 | 152 | 1112893334_152
C730D156BC###0036319 | TT_Task | Stage3 [SSJ] Alstom review Position and specs of Isolators, MET, False Floor, Drilling/non-drilling zone(Addendum) | 25/02/2021 | 24/03/2021 | 12/01/2021 | 12/01/2021 | 0 | TK_Complete | 1112893334 | 152 | 1112893334_152
C730D156BC###0035899 | TT_Task | Stage3 (SMTF-S) alstom review Position and specs of Isolators, MET, False Floor, Drilling/non-drilling zone | 25/08/2020 | 21/09/2020 | 03/07/2020 | 25/08/2020 | 0 | TK_Complete | 1112893334 | 152 | 1112893334_152
C730D147CT###0035390 | TT_Task | Stage3 SMTF(N) Alstom review Room Plan and location of SIG Room | 25/02/2020 | 09/03/2020 | 21/10/2019 | 04/11/2019 | 0 | TK_Complete | 1112893334 | 151 | 1112893334_151
C730D147CT###0035455 | TT_Task | Stage3 SMTF(N) Alstom review Room Plan and location of SIG Room-OCC | 25/05/2020 | 05/06/2020 | 29/04/2020 | 30/04/2020 | 0 | TK_Complete | 1112893334 | 151 | 1112893334_151
C730D156BC###0035413 | TT_Task | Stage2 (SMTF-S) Alstom review Room Plan and location of SIG Room | 27/04/2020 | 22/05/2020 | 04/02/2020 | 19/02/2020 | 0 | TK_Complete | 1112893334 | 151 | 1112893334_151
C730D156BC###0035695 | TT_Task | Stage3 [CST] Alstom review Room Plan and location of SIG Room | 25/08/2020 | 21/09/2020 | 04/05/2020 | 15/05/2020 | 0 | TK_Complete | 1112893334 | 151 | 1112893334_151
C730D156BC###0036202 | TT_Task | Stage3 [VIC] Alstom review Room Plan and location of SIG Room | 25/08/2020 | 21/09/2020 | 22/06/2020 | 06/07/2020 | 0 | TK_Complete | 1112893334 | 151 | 1112893334_151
C730D156BC###0036244 | TT_Task | Stage3 [BZZ] Alstom review Room Plan and location of SIG Room | 25/08/2020 | 21/09/2020 | 22/06/2020 | 30/06/2020 | 0 | TK_Complete | 1112893334 | 151 | 1112893334_151
C730D156BC###0036280 | TT_Task | Stage3 [MPL] Alstom review Room Plan and location of SIG Room | 25/08/2020 | 21/09/2020 | 23/06/2020 | 01/07/2020 | 0 | TK_Complete | 1112893334 | 151 | 1112893334_151
C730D156BC###0035632 | TT_Task | Stage3 [PIT] Alstom review Room Plan and location of SIG Room | 25/08/2020 | 21/09/2020 | 01/07/2020 | 17/08/2020 | 0 | TK_Complete | 1112893334 | 151 | 1112893334_151
C730D156BC###0035653 | TT_Task | Stage3 [WLO] Alstom review Room Plan and location of SIG Room | 25/11/2020 | 22/12/2020 | 23/11/2020 | 26/11/2020 | 0 | TK_Complete | 1112893334 | 151 | 1112893334_151
C730D156BC###0036358 | TT_Task | Stage3 [CSM] Alstom review Room Plan and location of SIG Room | 25/08/2020 | 21/09/2020 | 01/06/2020 | 09/06/2020 | 0 | TK_Complete | 1112893334 | 151 | 1112893334_151
C730D156BC###0036307 | TT_Task | Stage3 [SSJ] Alstom review Room Plan and location of SIG Room | 25/08/2020 | 21/09/2020 | 10/02/2020 | 11/03/2020 | 0 | TK_Complete | 1112893334 | 151 | 1112893334_151
C730D156BC###0035755 | TT_Task | Stage3 (SMTF-S) alstom review Room Plan and location of SIG Room | 25/08/2020 | 21/09/2020 | 01/07/2020 | 25/08/2020 | 0 | TK_Complete | 1112893334 | 151 | 1112893334_151
C730D147CT###0035360 | TT_Task | Stage3 SMTF(N) Alstom review Architecture of buidlings in depot | 25/02/2020 | 09/03/2020 | 01/10/2019 | 15/10/2019 | 0 | TK_Complete | 1112893334 | 150 | 1112893334_150
C730D156BC###0035887 | TT_Task | Stage3 (SMTF-S) alstom review Architecture of buidlings in depot | 25/08/2020 | 21/09/2020 | 02/07/2020 | 07/08/2020 | 0 | TK_Complete | 1112893334 | 150 | 1112893334_150
C720D147CF###0030160 | TT_Task | Trains/Stage-2 - Release of TPS for traction converter | 23/07/2019 | 19/08/2019 | 23/07/2019 | 19/08/2019 | 0 | TK_Complete | 1112893334 | 15 | 1112893334_15
C720D147CF###0030060 | TT_Task | Trains/Stage-2 - Release of TPS for wheels | 23/07/2019 | 19/08/2019 | 23/07/2019 | 19/08/2019 | 0 | TK_Complete | 1112893334 | 15 | 1112893334_15
C720D147CF###0030070 | TT_Task | Trains/Stage-2 - Release of TPS for axles | 23/07/2019 | 19/08/2019 | 23/07/2019 | 19/08/2019 | 0 | TK_Complete | 1112893334 | 15 | 1112893334_15
C720D147CF###0030080 | TT_Task | Trains/Stage-2 - Release of TPS for axle box ; bearing | 23/07/2019 | 19/08/2019 | 23/07/2019 | 19/08/2019 | 0 | TK_Complete | 1112893334 | 15 | 1112893334_15
C720D147CF###0030140 | TT_Task | Trains/Stage-2 - Release of TPS for traction motor | 23/07/2019 | 19/08/2019 | 23/07/2019 | 19/08/2019 | 0 | TK_Complete | 1112893334 | 15 | 1112893334_15
C730D147CT###0035285 | TT_Task | Stage3 SMTF(N) Alstom review Cross Section of Transit Space | 25/02/2020 | 09/03/2020 | 28/06/2019 | 12/07/2019 | 0 | TK_Complete | 1112893334 | 149 | 1112893334_149
C730D156BC###0035407 | TT_Task | Stage2 (LW-T) alstom review Cross Section of Transit Space | 25/06/2020 | 01/07/2020 | 08/06/2020 | 22/06/2020 | 0 | TK_Complete | 1112893334 | 149 | 1112893334_149
C730D156BC###0035995 | TT_Task | Stage3 [SSJ] Alstom review Cross Section of Transit Space(closed as per SoD Addendum Dt 120121) | 25/02/2021 | 24/03/2021 | 12/01/2021 | 12/01/2021 | 0 | TK_Complete | 1112893334 | 149 | 1112893334_149
C730D156BC###0035896 | TT_Task | Stage3 (SMTF-S) alstom review Cross Section of Transit Space | 25/08/2020 | 21/09/2020 | 03/07/2020 | 07/08/2020 | 0 | TK_Complete | 1112893334 | 149 | 1112893334_149
C730D156BC###0036037 | TT_Task | Stage3 (LW-T) alstom review Cross Section of Transit Space | 25/02/2021 | 24/03/2021 | 12/01/2021 | 12/01/2021 | 0 | TK_Complete | 1112893334 | 149 | 1112893334_149
C730D147CT###0035270 | TT_Task | Stage3 SMTF(N) Alstom review details about platform for stabling track | 25/02/2020 | 09/03/2020 | 28/06/2019 | 12/07/2019 | 0 | TK_Complete | 1112893334 | 148 | 1112893334_148
C730D156BC###0035893 | TT_Task | Stage3 (SMTF-S) alstom review details about platform for stabling track | 25/08/2020 | 21/09/2020 | 03/07/2020 | 14/08/2020 | 0 | TK_Complete | 1112893334 | 148 | 1112893334_148
C730D147CT###0035265 | TT_Task | Stage3 SMTF(N) Alstom review Spec. for noise attenuation panels in tunnel (4-foot and tunnel wall) *not applicable | 27/04/2020 | 08/05/2020 | 20/04/2020 | 20/04/2020 | 0 | TK_Complete | 1112893334 | 147 | 1112893334_147
C730D156BC###0035323 | TT_Task | Stage2 (SMTF-S) Alstom review Spec. for noise attenuation panels in tunnel (4-foot and tunnel wall) | 27/04/2020 | 22/05/2020 | 04/02/2020 | 19/02/2020 | 0 | TK_Complete | 1112893334 | 147 | 1112893334_147
C730D156BC###0035395 | TT_Task | Stage2 (LW-T) alstom review Spec. for noise attenuation panels in tunnel (4-foot and tunnel wall) | 25/06/2020 | 01/07/2020 | 16/06/2020 | 22/06/2020 | 0 | TK_Complete | 1112893334 | 147 | 1112893334_147
C730D156BC###0035968 | TT_Task | Stage3 [SSJ] Alstom review Spec. for noise attenuation panels in tunnel (4-foot and tunnel wall) | 01/01/2021 | 28/01/2021 | 26/10/2020 | 26/10/2020 | 0 | TK_Complete | 1112893334 | 147 | 1112893334_147
C730D156BC###0035851 | TT_Task | Stage3 (SMTF-S) alstom review Spec. for noise attenuation panels in tunnel (4-foot and tunnel wall) | 25/08/2020 | 21/09/2020 | 01/07/2020 | 31/07/2020 | 0 | TK_Complete | 1112893334 | 147 | 1112893334_147
C730D156BC###0036025 | TT_Task | Stage3 (LW-T) alstom review Spec. for noise attenuation panels in tunnel (4-foot and tunnel wall)SoD Addendum Dt 120121) | 25/02/2021 | 24/03/2021 | 12/01/2021 | 12/01/2021 | 0 | TK_Complete | 1112893334 | 147 | 1112893334_147
C730D156BC###0036049 | TT_Task | Stage3 (LW-T) alstom review Spec. for noise attenuation panels in tunnel (4-foot and tunnel wall) | 25/02/2021 | 24/03/2021 | 12/01/2021 | 12/01/2021 | 0 | TK_Complete | 1112893334 | 147 | 1112893334_147
C730D147CT###0035260 | TT_Task | Stage3 SMTF(N) Alstom review Details about drilling zone (allowed size, depth) - *not applicable | 27/04/2020 | 08/05/2020 | 13/04/2020 | 13/04/2020 | 0 | TK_Complete | 1112893334 | 146 | 1112893334_146
C730D156BC###0035989 | TT_Task | Stage3 [SSJ] Alstom review Details about drilling zone (allowed size, depth?)(closed as per SoD Addendum Dt 120121) | 25/02/2021 | 24/03/2021 | 12/01/2021 | 12/01/2021 | 0 | TK_Complete | 1112893334 | 146 | 1112893334_146
C730D156BC###0035890 | TT_Task | Stage3 (SMTF-S) alstom review Details about drilling zone (allowed size, depth?) | 25/08/2020 | 21/09/2020 | 02/07/2020 | 07/08/2020 | 0 | TK_Complete | 1112893334 | 146 | 1112893334_146
C730D156BC###0036046 | TT_Task | Stage3 (LW-T) alstom review Details about drilling zone (allowed size, depth?) | 25/08/2020 | 21/09/2020 | 14/07/2020 | 31/07/2020 | 0 | TK_Complete | 1112893334 | 146 | 1112893334_146
C730D147CT###0035255 | TT_Task | Stage3 SMTF(N) Review Specs and loc. of foundation for GAK/TRE/Antenna Mast/PMDB/PM/PPI/SAB/BS/Earth Pit/Earth Bar | 25/05/2020 | 05/06/2020 | 29/04/2020 | 30/04/2020 | 0 | TK_Complete | 1112893334 | 145 | 1112893334_145
C730D147CT###0035320 | TT_Task | Stage3 SMTF(N) Initial survey Specs and loc. of foundation for GAK/TRE/Antenna/PMDB/PM/PPI/SAB/BS/Earth Pit/Earth Bar | 25/05/2020 | 06/07/2020 | 04/05/2020 | 06/05/2020 | 0 | TK_Complete | 1112893334 | 145 | 1112893334_145
C730D156BC###0035866 | TT_Task | Stage3 (SMTF-S) alstom review Spec ; loc. of foundation GAK/TRE/Antenna Mast/PMDB/PM/PPI/SAB/BS/Earth Pit/Earth Bar | 25/08/2020 | 21/09/2020 | 02/07/2020 | 03/08/2020 | 0 | TK_Complete | 1112893334 | 145 | 1112893334_145
C730D156BC###0035917 | TT_Task | Stage3 [SMTF-S] Initial survey Spec ; loc. of foundation GAK/TRE/Antenna/PMDB/PM/PPI/SAB/BS/Earth Pit/Earth Bar | 25/09/2020 | 09/11/2020 | 03/08/2020 | 25/08/2020 | 0 | TK_Complete | 1112893334 | 145 | 1112893334_145
C730D147CT###0035190 | TT_Task | Stage3 SMTF(N) Alstom review Depot access and VIDS details for SMTF[N] | 25/05/2020 | 05/06/2020 | 29/04/2020 | 30/04/2020 | 0 | TK_Complete | 1112893334 | 144 | 1112893334_144
C730D156BC###0035140 | TT_Task | Stage2 [City] Alstom review Station names/Abbreviations details for SMCSW/GF | 30/08/2019 | 03/09/2019 | 15/01/2019 | 17/01/2019 | 0 | TK_Complete | 1112893334 | 144 | 1112893334_144
C730D156BC###0035206 | TT_Task | Stage2 [City] Alstom review TIDS and VIDS for SMCSW/GF mainline | 31/10/2019 | 27/11/2019 | 07/10/2019 | 25/10/2019 | 0 | TK_Complete | 1112893334 | 144 | 1112893334_144
C730D156BC###0035200 | TT_Task | Stage2 (SMTF-S) Alstom review Depot access and VIDS details for SMTF [S]/GF | 31/10/2019 | 04/11/2019 | 02/10/2019 | 04/10/2019 | 0 | TK_Complete | 1112893334 | 144 | 1112893334_144
C730D156BC###0035539 | TT_Task | Stage3 [GEN] Alstom review TIDS and VIDS for SMCSW/GF mainline(closed as per Design Consideration) | 25/02/2021 | 24/03/2021 | 25/11/2020 | 25/11/2020 | 0 | TK_Complete | 1112893334 | 144 | 1112893334_144
C730D156BC###0035542 | TT_Task | Stage3 [GEN] Alstom review Depot access and VIDS details for SMTF [S](closed as per SoD Addendum Dt 120121) | 25/02/2021 | 24/03/2021 | 12/01/2021 | 12/01/2021 | 0 | TK_Complete | 1112893334 | 144 | 1112893334_144
C730D147CT###0035185 | TT_Task | Stage3 SMTF(N) Alstom review Location and size of CER2 for SMTF[N] *not applicable | 27/04/2020 | 08/05/2020 | 01/04/2020 | 07/04/2020 | 0 | TK_Complete | 1112893334 | 143 | 1112893334_143
C730D147CT###0035300 | TT_Task | Stage3 SMTF(N) preliminary design survey for Location and size of CER2 for SMTF[N] | 27/04/2020 | 05/06/2020 | 08/04/2020 | 23/04/2020 | 0 | TK_Complete | 1112893334 | 143 | 1112893334_143
C730D147CT###0035150 | TT_Task | Stage3 SMTF(N) Alstom review PWAY Drwg withKP details of tracks/points/platforms/ramp/viaduct | 31/10/2019 | 13/11/2019 | 01/07/2019 | 05/07/2019 | 0 | TK_Complete | 1112893334 | 142 | 1112893334_142
C730D147CT###0035160 | TT_Task | Stage3 SMTF(N) preliminary design survey for PWAY Drwg with KP details of tracks/points/platforms/ramp/viaduct | 31/10/2019 | 11/12/2019 | 05/08/2019 | 13/09/2019 | 0 | TK_Complete | 1112893334 | 142 | 1112893334_142
C730D147CT###0035140 | TT_Task | Stage2 SMTF(N) review of inputs OHW Alignment / Traction Diagram | 31/10/2019 | 04/11/2019 | 03/06/2019 | 05/06/2019 | 0 | TK_Complete | 1112893334 | 141 | 1112893334_141
C730D147CT###0035290 | TT_Task | Stage3 SMTF(N) Alstom review OHW Alignment / Traction Diagram | 25/02/2020 | 09/03/2020 | 21/05/2019 | 04/06/2019 | 0 | TK_Complete | 1112893334 | 141 | 1112893334_141
C730D156BC###0035368 | TT_Task | Stage2 (SSJ) review OHW Alignment / Traction Diagram | 27/04/2020 | 22/05/2020 | 02/03/2020 | 27/03/2020 | 0 | TK_Complete | 1112893334 | 141 | 1112893334_141
C730D156BC###0035197 | TT_Task | Stage2 (SMTF-S) Alstom review OHW Alignment / Traction Diagram | 31/10/2019 | 06/11/2019 | 01/10/2019 | 08/10/2019 | 0 | TK_Complete | 1112893334 | 141 | 1112893334_141
C730D156BC###0035164 | TT_Task | Stage2 (LW-T) alstom review OHW Alignment / Traction Diagram | 31/10/2019 | 06/11/2019 | 12/08/2019 | 14/08/2019 | 0 | TK_Complete | 1112893334 | 141 | 1112893334_141
C730D156BC###0035977 | TT_Task | Stage3 [SSJ] Alstom review OHW Alignment / Traction Diagram | 25/08/2020 | 21/09/2020 | 01/06/2020 | 01/07/2020 | 0 | TK_Complete | 1112893334 | 141 | 1112893334_141
C730D156BC###0035524 | TT_Task | Stage3 (SMTF-S) alstom review OHW Alignment / Traction Diagram | 25/08/2020 | 21/09/2020 | 01/06/2020 | 30/06/2020 | 0 | TK_Complete | 1112893334 | 141 | 1112893334_141
C730D156BC###0035734 | TT_Task | Stage3 (LW-T) alstom review OHW Alignment / Traction Diagram | 25/08/2020 | 21/09/2020 | 01/06/2020 | 30/06/2020 | 0 | TK_Complete | 1112893334 | 141 | 1112893334_141
C730D147CT###0035110 | TT_Task | Stage2 SMTF(N) review of inputs Delivery Route to signalling room / temporary storage | 31/10/2019 | 04/11/2019 | 25/03/2019 | 29/03/2019 | 0 | TK_Complete | 1112893334 | 140 | 1112893334_140
C730D147CT###0035125 | TT_Task | Stage2 SMTF(N) review of inputs Delivery Route to signalling room / temporary storage-OCC | 31/10/2019 | 04/11/2019 | 25/03/2019 | 29/03/2019 | 0 | TK_Complete | 1112893334 | 140 | 1112893334_140
C730D156BC###0035251 | TT_Task | Stage2 (CST) review Delivery Route to signalling room / temporary storage | 27/04/2020 | 22/05/2020 | 08/01/2020 | 05/02/2020 | 0 | TK_Complete | 1112893334 | 140 | 1112893334_140
C730D156BC###0035587 | TT_Task | Stage2 (VIC) review Delivery Route to signalling room / temporary storage | 27/04/2020 | 22/05/2020 | 12/03/2020 | 08/04/2020 | 0 | TK_Complete | 1112893334 | 140 | 1112893334_140
C730D156BC###0035452 | TT_Task | Stage2 (BZZ) review Delivery Route to signalling room / temporary storage | 27/04/2020 | 22/05/2020 | 06/01/2020 | 03/02/2020 | 0 | TK_Complete | 1112893334 | 140 | 1112893334_140
C730D156BC###0035476 | TT_Task | Stage2 (MPL) review Delivery Route to signalling room / temporary storage | 27/04/2020 | 22/05/2020 | 02/04/2020 | 21/04/2020 | 0 | TK_Complete | 1112893334 | 140 | 1112893334_140
C730D156BC###0035266 | TT_Task | Stage2 (PIT) review Delivery Route to signalling room / temporary storage | 27/04/2020 | 22/05/2020 | 01/04/2020 | 20/04/2020 | 0 | TK_Complete | 1112893334 | 140 | 1112893334_140
C730D156BC###0035296 | TT_Task | Stage2 (WLO) review Delivery Route to signalling room / temporary storage | 25/06/2020 | 22/07/2020 | 08/06/2020 | 15/06/2020 | 0 | TK_Complete | 1112893334 | 140 | 1112893334_140
C730D156BC###0035560 | TT_Task | Stage2 (CSM) review Delivery Route to signalling room / temporary storage | 27/04/2020 | 22/05/2020 | 22/01/2020 | 19/02/2020 | 0 | TK_Complete | 1112893334 | 140 | 1112893334_140
C730D156BC###0035515 | TT_Task | Stage2 (SSJ) review Delivery Route to signalling room / temporary storage | 27/04/2020 | 22/05/2020 | 02/03/2020 | 27/03/2020 | 0 | TK_Complete | 1112893334 | 140 | 1112893334_140
C720D147CF###0030150 | TT_Task | Trains/Stage-2 - Release of TPS for wind shield | 23/07/2019 | 19/08/2019 | 23/07/2019 | 19/08/2019 | 0 | TK_Complete | 1112893334 | 14 | 1112893334_14
C720D147CF###0030280 | TT_Task | Trains/Stage-2 - Release of TPS for HVAC | 23/07/2019 | 19/08/2019 | 23/07/2019 | 19/08/2019 | 0 | TK_Complete | 1112893334 | 14 | 1112893334_14
C720D147CF###0030040 | TT_Task | Trains/Stage-2 - Release of TPS for primary suspension | 23/07/2019 | 19/08/2019 | 23/07/2019 | 19/08/2019 | 0 | TK_Complete | 1112893334 | 14 | 1112893334_14
C720D147CF###0030050 | TT_Task | Trains/Stage-2 - Release of TPS for secondary suspension | 23/07/2019 | 19/08/2019 | 23/07/2019 | 19/08/2019 | 0 | TK_Complete | 1112893334 | 14 | 1112893334_14
C730D147CT###0035105 | TT_Task | Stage2 SMTF(N) review of inputs Room Plan and location of SIG Room | 31/10/2019 | 04/11/2019 | 25/03/2019 | 29/03/2019 | 0 | TK_Complete | 1112893334 | 139 | 1112893334_139
C730D147CT###0035120 | TT_Task | Stage2 SMTF(N) review of inputs Room Plan and location of SIG Room-OCC | 31/10/2019 | 04/11/2019 | 25/03/2019 | 29/03/2019 | 0 | TK_Complete | 1112893334 | 139 | 1112893334_139
C730D156BC###0035245 | TT_Task | Stage2 (CST) review Room Plan and location of SIG Room | 27/04/2020 | 22/05/2020 | 08/01/2020 | 05/02/2020 | 0 | TK_Complete | 1112893334 | 139 | 1112893334_139
C730D156BC###0035179 | TT_Task | Stage2 (VIC) review Room Plan and location of SIG Room | 31/10/2019 | 06/11/2019 | 01/10/2019 | 08/10/2019 | 0 | TK_Complete | 1112893334 | 139 | 1112893334_139
C730D156BC###0035182 | TT_Task | Stage2 (BZZ) review Room Plan and location of SIG Room | 31/10/2019 | 06/11/2019 | 01/10/2019 | 08/10/2019 | 0 | TK_Complete | 1112893334 | 139 | 1112893334_139
C730D156BC###0035185 | TT_Task | Stage2 (MPL) review Room Plan and location of SIG Room | 31/10/2019 | 06/11/2019 | 01/10/2019 | 08/10/2019 | 0 | TK_Complete | 1112893334 | 139 | 1112893334_139
C730D156BC###0035260 | TT_Task | Stage2 (PIT) review Room Plan and location of SIG Room | 27/04/2020 | 22/05/2020 | 01/04/2020 | 20/04/2020 | 0 | TK_Complete | 1112893334 | 139 | 1112893334_139
C730D156BC###0035290 | TT_Task | Stage2 (WLO) review Room Plan and location of SIG Room | 25/05/2020 | 22/06/2020 | 08/05/2020 | 12/05/2020 | 0 | TK_Complete | 1112893334 | 139 | 1112893334_139
C730D156BC###0035188 | TT_Task | Stage2 (CSM) review Room Plan and location of SIG Room | 31/10/2019 | 06/11/2019 | 01/10/2019 | 08/10/2019 | 0 | TK_Complete | 1112893334 | 139 | 1112893334_139
C730D156BC###0035191 | TT_Task | Stage2 (SSJ) review Room Plan and location of SIG Room | 31/10/2019 | 06/11/2019 | 01/10/2019 | 08/10/2019 | 0 | TK_Complete | 1112893334 | 139 | 1112893334_139
C730D147CT###0035100 | TT_Task | Stage2 SMTF(N) review of inputs Trackforms (type, specs, drill/non-drill) | 31/10/2019 | 04/11/2019 | 25/03/2019 | 29/03/2019 | 0 | TK_Complete | 1112893334 | 138 | 1112893334_138
C730D147CT###0035280 | TT_Task | Stage3 SMTF(N) Alstom review Trackforms (type, specs, drill/non-drill) | 25/02/2020 | 09/03/2020 | 28/06/2019 | 12/07/2019 | 0 | TK_Complete | 1112893334 | 138 | 1112893334_138
C730D156BC###0035365 | TT_Task | Stage2 (SSJ) review Trackforms (type, specs, drill/non-drill) | 27/04/2020 | 22/05/2020 | 02/03/2020 | 27/03/2020 | 0 | TK_Complete | 1112893334 | 138 | 1112893334_138
C730D156BC###0035329 | TT_Task | Stage2 (SMTF-S) Alstom review Trackforms (type, specs, drill/non-drill) | 27/04/2020 | 22/05/2020 | 04/02/2020 | 19/02/2020 | 0 | TK_Complete | 1112893334 | 138 | 1112893334_138
C730D156BC###0035401 | TT_Task | Stage2 (LW-T) alstom review Trackforms (type, specs, drill/non-drill) | 27/04/2020 | 22/05/2020 | 13/01/2020 | 10/02/2020 | 0 | TK_Complete | 1112893334 | 138 | 1112893334_138
C730D156BC###0035974 | TT_Task | Stage3 [SSJ] Alstom review Trackforms (type, specs, drill/non-drill) | 25/08/2020 | 21/09/2020 | 10/07/2020 | 24/08/2020 | 0 | TK_Complete | 1112893334 | 138 | 1112893334_138
C730D156BC###0035857 | TT_Task | Stage3 (SMTF-S) alstom review Trackforms (type, specs, drill/non-drill) | 25/08/2020 | 21/09/2020 | 01/07/2020 | 27/07/2020 | 0 | TK_Complete | 1112893334 | 138 | 1112893334_138
C730D156BC###0036031 | TT_Task | Stage3 (LW-T) alstom review Trackforms (type, specs, drill/non-drill) | 25/08/2020 | 21/09/2020 | 01/06/2020 | 30/06/2020 | 0 | TK_Complete | 1112893334 | 138 | 1112893334_138
C730D147CT###0035095 | TT_Task | Stage2 SMTF(N) review of inputs Corridor civil details (fencing, gates, bridge, drainage, walkway etc..) | 31/10/2019 | 04/11/2019 | 25/03/2019 | 29/03/2019 | 0 | TK_Complete | 1112893334 | 137 | 1112893334_137
C730D147CT###0035275 | TT_Task | Stage3 SMTF(N) Alstom review Corridor civil details (fencing, gates, bridge, drainage, walkway etc..) | 25/02/2020 | 09/03/2020 | 05/07/2019 | 19/07/2019 | 0 | TK_Complete | 1112893334 | 137 | 1112893334_137
C730D156BC###0035362 | TT_Task | Stage2 (SSJ) review Corridor civil details (fencing, gates, bridge, drainage, walkway etc..) | 27/04/2020 | 22/05/2020 | 02/03/2020 | 27/03/2020 | 0 | TK_Complete | 1112893334 | 137 | 1112893334_137
C730D156BC###0035326 | TT_Task | Stage2 (SMTF-S) Alstom review Corridor civil details (fencing, gates, bridge, drainage, walkway etc..) | 27/04/2020 | 22/05/2020 | 04/02/2020 | 19/02/2020 | 0 | TK_Complete | 1112893334 | 137 | 1112893334_137
C730D156BC###0035398 | TT_Task | Stage2 (LW-T) alstom review Corridor civil details (fencing, gates, bridge, drainage, walkway etc..) | 27/04/2020 | 22/05/2020 | 13/01/2020 | 10/02/2020 | 0 | TK_Complete | 1112893334 | 137 | 1112893334_137
C730D156BC###0035971 | TT_Task | Stage3 [SSJ] Alstom review Corridor civil details (fencing, gates, bridge, drainage, walkway etc..) | 25/08/2020 | 21/09/2020 | 25/05/2020 | 12/06/2020 | 0 | TK_Complete | 1112893334 | 137 | 1112893334_137
C730D156BC###0035854 | TT_Task | Stage3 (SMTF-S) alstom review Corridor civil details (fencing, gates, bridge, drainage, walkway etc..) | 27/04/2020 | 22/05/2020 | 17/03/2020 | 15/04/2020 | 0 | TK_Complete | 1112893334 | 137 | 1112893334_137
C730D156BC###0036028 | TT_Task | Stage3 (LW-T) alstom review Corridor civil details (fencing, gates, bridge, drainage, walkway etc..)(Addendum) | 25/02/2021 | 24/03/2021 | 12/01/2021 | 12/01/2021 | 0 | TK_Complete | 1112893334 | 137 | 1112893334_137
C730D147CT###0035090 | TT_Task | Stage2 SMTF(N) review of inputs Spec. for noise attenuation panels in tunnel (4-foot and tunnel wall) | 31/10/2019 | 04/11/2019 | 25/03/2019 | 29/03/2019 | 0 | TK_Complete | 1112893334 | 136 | 1112893334_136
C730D147CT###0035330 | TT_Task | Stage3 SMTF(N) Initial survey/desktop audit Spec. for noise attenuation panels in tunnel (4-foot and tunnel wall) | 27/04/2020 | 05/06/2020 | 21/04/2020 | 21/04/2020 | 0 | TK_Complete | 1112893334 | 136 | 1112893334_136
C730D156BC###0035359 | TT_Task | Stage2 (SSJ) review Spec. for noise attenuation panels in tunnel (4-foot and tunnel wall) | 27/04/2020 | 22/05/2020 | 02/03/2020 | 27/03/2020 | 0 | TK_Complete | 1112893334 | 136 | 1112893334_136
C730D156BC###0036082 | TT_Task | Stage3 (SSJ) Initial survey/desktop audit Spec. for noise attenuation panels in tunnel (4-foot and tunnel wall) (**NA) | 25/02/2021 | 07/04/2021 | 26/10/2020 | 26/10/2020 | 0 | TK_Complete | 1112893334 | 136 | 1112893334_136
C730D156BC###0035905 | TT_Task | Stage3 (SMTF-S) Initial survey/desktop audit Spec. for noise attenuation panels in tunnel (4-foot and tunnel wall) | 25/08/2020 | 06/10/2020 | 20/08/2020 | 26/08/2020 | 0 | TK_Complete | 1112893334 | 136 | 1112893334_136
C730D156BC###0036127 | TT_Task | Stage3 (LW-T) Initial survey/desktop audit Spec. for noise attenuation panels in tunnel (4-foot and tunnel wall) | 25/02/2021 | 07/04/2021 | 12/01/2021 | 12/01/2021 | 0 | TK_Complete | 1112893334 | 136 | 1112893334_136
C730D156BC###0036145 | TT_Task | Stage3 (LW-T) Initial survey/desktop audit Spec. for noise attenuation panels in tunnel (4-foot and tunnel wall) | 25/02/2021 | 07/04/2021 | 12/01/2021 | 12/01/2021 | 0 | TK_Complete | 1112893334 | 136 | 1112893334_136
C730D147CT###0035085 | TT_Task | Stage2 SMTF(N) review of inputs CSR Route, Pits and Conduits specs, local route, ULX and OLX | 31/10/2019 | 04/11/2019 | 25/03/2019 | 29/03/2019 | 0 | TK_Complete | 1112893334 | 135 | 1112893334_135
C730D147CT###0035115 | TT_Task | Stage2 SMTF(N) review of inputs As-built CSR Route, Pits and Conduits specs, local route, ULX and OLX | 31/10/2019 | 04/11/2019 | 25/03/2019 | 29/03/2019 | 0 | TK_Complete | 1112893334 | 135 | 1112893334_135
C730D147CT###0020032 | TT_Task | Stage3 SMTF(N) Alstom review CSR Route, Pits and Conduits specs, local route, ULX and OLX (Rework) | 27/04/2020 | 08/05/2020 | 06/04/2020 | 21/04/2020 | 0 | TK_Complete | 1112893334 | 135 | 1112893334_135
C730D147CT###0035250 | TT_Task | Stage3 SMTF(N) Alstom review CSR Route, Pits and Conduits specs, local route, ULX and OLX | 25/02/2020 | 09/03/2020 | 05/07/2019 | 19/07/2019 | 0 | TK_Complete | 1112893334 | 135 | 1112893334_135
C730D147CT###0035315 | TT_Task | Stage3 SMTF(N) Initial survey/desktop audit Alstom review CSR Route, Pits and Conduits specs, local route, ULX and OLX | 27/04/2020 | 05/06/2020 | 09/03/2020 | 03/04/2020 | 0 | TK_Complete | 1112893334 | 135 | 1112893334_135
C730D156BC###0035356 | TT_Task | Stage2 (SSJ) review CSR Route, Pits and Conduits specs, local route, ULX and OLX | 27/04/2020 | 22/05/2020 | 02/03/2020 | 27/03/2020 | 0 | TK_Complete | 1112893334 | 135 | 1112893334_135
C730D156BC###0035320 | TT_Task | Stage2 (SMTF-S) Alstom review CSR Route, Pits and Conduits specs, local route, ULX and OLX | 27/04/2020 | 22/05/2020 | 04/02/2020 | 19/02/2020 | 0 | TK_Complete | 1112893334 | 135 | 1112893334_135
C730D156BC###0035392 | TT_Task | Stage2 (LW-T) alstom review CSR Route, Pits and Conduits specs, local route, ULX and OLX | 27/04/2020 | 22/05/2020 | 13/01/2020 | 10/02/2020 | 0 | TK_Complete | 1112893334 | 135 | 1112893334_135
C730D156BC###0035965 | TT_Task | Stage3 [SSJ] Alstom review CSR Route, Pits and Conduits specs, local route, ULX and OLX | 25/08/2020 | 21/09/2020 | 15/06/2020 | 15/07/2020 | 0 | TK_Complete | 1112893334 | 135 | 1112893334_135
C730D156BC###0035752 | TT_Task | Stage3 (SMTF-S) alstom review CSR Route, Pits and Conduits specs, local route, ULX and OLX | 27/04/2020 | 22/05/2020 | 17/03/2020 | 15/04/2020 | 0 | TK_Complete | 1112893334 | 135 | 1112893334_135
C730D156BC###0035419 | TT_Task | Stage3 (LW-T) alstom review CSR Route, Pits and Conduits specs, local route, ULX and OLX | 25/11/2020 | 22/12/2020 | 27/10/2020 | 30/10/2020 | 0 | TK_Complete | 1112893334 | 135 | 1112893334_135
C730D147CT###0035080 | TT_Task | Stage2 SMTF(N) review of inputs Horizontal/Vertical Track Alignment, Turnout configuration | 31/10/2019 | 04/11/2019 | 25/03/2019 | 29/03/2019 | 0 | TK_Complete | 1112893334 | 134 | 1112893334_134
C730D147CT###0035245 | TT_Task | Stage3 SMTF(N) Alstom review Horizontal/Vertical Track Alignment, Turnout Design | 25/05/2020 | 05/06/2020 | 29/04/2020 | 30/04/2020 | 0 | TK_Complete | 1112893334 | 134 | 1112893334_134
C730D156BC###0035353 | TT_Task | Stage2 (SSJ) review Horizontal/Vertical Track Alignment, Turnout design | 27/04/2020 | 22/05/2020 | 02/03/2020 | 27/03/2020 | 0 | TK_Complete | 1112893334 | 134 | 1112893334_134
C730D156BC###0035194 | TT_Task | Stage2 (SMTF-S) Alstom review Horizontal/Vertical Track Alignment, Turnout configuration | 31/10/2019 | 06/11/2019 | 01/10/2019 | 03/10/2019 | 0 | TK_Complete | 1112893334 | 134 | 1112893334_134
C730D156BC###0035209 | TT_Task | Stage2 (LW-T) alstom review Horizontal/Vertical Track Alignment, Turnout configuration | 27/04/2020 | 22/05/2020 | 13/01/2020 | 10/02/2020 | 0 | TK_Complete | 1112893334 | 134 | 1112893334_134
C730D156BC###0035962 | TT_Task | Stage3 [SSJ] Alstom review Horizontal/Vertical Track Alignment, Turnout design | 25/11/2020 | 22/12/2020 | 27/10/2020 | 28/11/2020 | 0 | TK_Complete | 1112893334 | 134 | 1112893334_134
C730D156BC###0035749 | TT_Task | Stage3 (SMTF-S) alstom review Horizontal/Vertical Track Alignment, Turnout configuration | 25/08/2020 | 21/09/2020 | 01/07/2020 | 30/07/2020 | 0 | TK_Complete | 1112893334 | 134 | 1112893334_134
C730D156BC###0035725 | TT_Task | Stage3 (LW-T) alstom review Horizontal/Vertical Track Alignment, Turnout configuration | 25/08/2020 | 21/09/2020 | 01/06/2020 | 30/06/2020 | 0 | TK_Complete | 1112893334 | 134 | 1112893334_134
C730D147CT###0035025 | TT_Task | Stage2 SMTF(N) review of inputs Non-stopping zones details for SMTF[N] | 01/07/2019 | 03/07/2019 | 05/03/2019 | 07/03/2019 | 0 | TK_Complete | 1112893334 | 133 | 1112893334_133
C730D147CT###0035180 | TT_Task | Stage3 SMTF(N) Alstom review Non-stopping zones details for SMTF[N] | 25/02/2020 | 09/03/2020 | 21/05/2019 | 04/06/2019 | 0 | TK_Complete | 1112893334 | 133 | 1112893334_133
C730D147CT###0035295 | TT_Task | Stage3 SMTF(N) preliminary design survey for Non-stopping zones details for SMTF[N] | 27/04/2020 | 05/06/2020 | 09/03/2020 | 20/03/2020 | 0 | TK_Complete | 1112893334 | 133 | 1112893334_133
C730D147CT###0035020 | TT_Task | Stage2 SMTF(N) review of inputs PWAY drawings for SMTF [N] with KP details | 01/07/2019 | 03/07/2019 | 05/03/2019 | 07/03/2019 | 0 | TK_Complete | 1112893334 | 132 | 1112893334_132
C730D147CT###0035135 | TT_Task | Stage2 SMTF(N) review of inputs Depot access and VIDS details for SMTF[N] | 01/07/2019 | 03/07/2019 | 04/04/2019 | 08/04/2019 | 0 | TK_Complete | 1112893334 | 132 | 1112893334_132
C730D147CT###0035305 | TT_Task | Stage3 SMTF(N) preliminary design survey for Depot access and VIDS details for SMTF[N] | 25/05/2020 | 06/07/2020 | 04/05/2020 | 06/05/2020 | 0 | TK_Complete | 1112893334 | 132 | 1112893334_132
C730D147BC###0065010 | TT_Task | SMCSW [System-wide] Customer Review and acceptance Initial Maintenance plan | 04/04/2022 | 06/05/2022 | nan | nan | 1040 | TK_NotStart | 1112893334 | 131 | 1112893334_131
C730D147BC###0065025 | TT_Task | SMCSW [System-wide] Customer Review and acceptance Initial Training Plan | 25/03/2022 | 31/05/2022 | 28/06/2021 | nan | 0 | TK_Active | 1112893334 | 131 | 1112893334_131
C730D147BC###0065040 | TT_Task | SMCSW [System-wide] Customer Review and acceptance Initial O;M Manuals | 09/11/2022 | 13/12/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 131 | 1112893334_131
C730D147BC###0065005 | TT_Task | SMCSW[System-wide Final] customer review ; acceptance Software quality plan | 25/05/2020 | 29/06/2020 | 27/03/2020 | 19/05/2020 | 0 | TK_Complete | 1112893334 | 131 | 1112893334_131
C730D147BC###0065035 | TT_Task | SMCSW[System-wide Final] customer review ; acceptance Training Plan | 27/07/2022 | 30/08/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 131 | 1112893334_131
C730D147BC###0065055 | TT_Task | SMCSW[System-wide Final] customer review ; acceptance O;M Manuals Part 1 | 25/01/2023 | 28/02/2023 | nan | nan | 480 | TK_NotStart | 1112893334 | 131 | 1112893334_131
C730D147BC###0065065 | TT_Task | SMCSW[System-wide Final] customer review ; acceptance O;M Manuals Part 2 | 08/03/2023 | 11/04/2023 | nan | nan | 240 | TK_NotStart | 1112893334 | 131 | 1112893334_131
C730D147BC###0065075 | TT_Task | SMCSW[System-wide Final] customer review ; acceptance O;M Manuals Part 3 | 19/04/2023 | 23/05/2023 | nan | nan | 0 | TK_NotStart | 1112893334 | 131 | 1112893334_131
C730D147BC###0065080 | TT_Task | SMCSW[System-wide Final] customer review ; acceptance Maintenance Plan | 19/12/2022 | 20/01/2023 | nan | nan | 696 | TK_NotStart | 1112893334 | 131 | 1112893334_131
C730D147BC###0065095 | TT_Task | SMCSW[System-wide Final] customer review ; acceptance As-built drawings, test records, safety case | 20/06/2023 | 10/07/2023 | nan | nan | 104 | TK_NotStart | 1112893334 | 131 | 1112893334_131
C730D147BC###0027090 | TT_Task | CBTC SMCSW[System-wide] Initial O;M Manuals | 31/08/2022 | 08/11/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 130 | 1112893334_130
C730D147BC###0065045 | TT_Task | CBTC SMCSW[System-wide Final] O;M Manuals Part 1 | 14/12/2022 | 24/01/2023 | nan | nan | 0 | TK_NotStart | 1112893334 | 130 | 1112893334_130
C730D147BC###0065050 | TT_Task | CBTC SMCSW[System-wide Final] O;M Manuals Part 2 | 25/01/2023 | 07/03/2023 | nan | nan | 0 | TK_NotStart | 1112893334 | 130 | 1112893334_130
C730D147BC###0065060 | TT_Task | CBTC SMCSW[System-wide Final] O;M Manuals Part 3 | 08/03/2023 | 18/04/2023 | nan | nan | 0 | TK_NotStart | 1112893334 | 130 | 1112893334_130
C720D147CF###0030130 | TT_Task | Trains/Stage-2 - Release of TPS for detrainment doors | 23/07/2019 | 19/08/2019 | 23/07/2019 | 19/08/2019 | 0 | TK_Complete | 1112893334 | 13 | 1112893334_13
C720D147CF###0030230 | TT_Task | Trains/Stage-2 - Release of TPS for floor covering | 23/07/2019 | 19/08/2019 | 23/07/2019 | 19/08/2019 | 0 | TK_Complete | 1112893334 | 13 | 1112893334_13
C720D147CF###0030260 | TT_Task | Trains/Stage-2 - Release of TPS for floor composite material | 23/07/2019 | 19/08/2019 | 23/07/2019 | 19/08/2019 | 0 | TK_Complete | 1112893334 | 13 | 1112893334_13
C720D147CF###0030290 | TT_Task | Trains/Stage-2 - Release of TPS for passenger doors | 23/07/2019 | 19/08/2019 | 23/07/2019 | 19/08/2019 | 0 | TK_Complete | 1112893334 | 13 | 1112893334_13
C720D147CF###0030470 | TT_Task | Trains/Stage-2 - Release of TPS for cabinets | 17/09/2019 | 15/10/2019 | 17/09/2019 | 15/10/2019 | 0 | TK_Complete | 1112893334 | 13 | 1112893334_13
C730D147BC###0027050 | TT_Task | CBTC SMCSW[System-wide] Initial Training Plan | 06/10/2020 | 14/12/2020 | 01/09/2020 | 19/11/2020 | 0 | TK_Complete | 1112893334 | 129 | 1112893334_129
C730D147BC###0065015 | TT_Task | CBTC SMCSW[System-wide Final] CBTC Signalling System training plan | 12/02/2021 | 18/03/2021 | 01/09/2020 | 20/11/2020 | 0 | TK_Complete | 1112893334 | 129 | 1112893334_129
C730D147BC###0065030 | TT_Task | CBTC SMCSW[System-wide Final] Training Plan | 01/06/2022 | 26/07/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 129 | 1112893334_129
C730D147BC###0065090 | TT_Task | CBTC SMCSW[System-wide Final] Complete all training with approved training plans | 16/05/2023 | 26/06/2023 | nan | nan | 48 | TK_NotStart | 1112893334 | 129 | 1112893334_129
C730D147BC###0065020 | TT_Task | SMCSW[System-wide Final] customer review ; acceptance CBTC Signalling System training plan | 19/03/2021 | 22/04/2021 | 23/11/2020 | nan | 0 | TK_Active | 1112893334 | 129 | 1112893334_129
C730D147BC###0026700 | TT_Task | CBTC SMCSW[System-wide] Initial Maintenance plan | 25/08/2020 | 28/09/2020 | 24/08/2020 | nan | 0 | TK_Active | 1112893334 | 128 | 1112893334_128
C730D147BC###0065070 | TT_Task | CBTC SMCSW[System-wide Final] Maintenance Plan | 07/11/2022 | 16/12/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 128 | 1112893334_128
C730D157BC###0031910 | TT_Task | CBTC/Stage-3 SMCSW - Maintenance Assessment Report | 09/07/2021 | 19/08/2021 | 04/01/2021 | 23/04/2021 | 0 | TK_Complete | 1112893334 | 128 | 1112893334_128
C730D157BC###0031964 | TT_Task | CBTC/Stage-3 SMCSW - Recommendations for Training for Maintenance Activities | 20/08/2021 | 30/09/2021 | 05/01/2021 | 23/04/2021 | 0 | TK_Complete | 1112893334 | 128 | 1112893334_128
C730D147BC###0010020 | TT_Task | Preperation ; submission of initial MCS (material control schedule) for all CBTC materials [Phase 1] | 31/10/2019 | 27/11/2019 | 21/10/2019 | 20/12/2019 | 0 | TK_Complete | 1112893334 | 127 | 1112893334_127
C730P147CT###N933239 | TT_Task | Completion of Batch 2 First Deliveries [Trackside Materials] (B8) - Phase1-City | 08/12/2021 | 28/12/2021 | 08/12/2021 | 16/12/2021 | 0 | TK_Complete | 1112893334 | 127 | 1112893334_127
C730D147BC###0010000 | TT_Task | Creation and submission of the final SoD (Schedule of Design) document | 01/07/2019 | 26/07/2019 | 13/05/2019 | 20/12/2019 | 0 | TK_Complete | 1112893334 | 126 | 1112893334_126
C730D147BC###0027422 | TT_Task | Customer review and acceptance Final Final Installation Management Plan | 25/08/2020 | 28/09/2020 | 26/06/2020 | 27/07/2020 | 0 | TK_Complete | 1112893334 | 125 | 1112893334_125
C730D147BC###0027431 | TT_Task | Customer review and acceptance Final Engineering management plan | 25/05/2020 | 29/06/2020 | 01/04/2020 | 01/04/2021 | 0 | TK_Complete | 1112893334 | 125 | 1112893334_125
C730D147BC###0027442 | TT_Task | Customer review and acceptance Final Configuration management plan | 25/05/2020 | 29/06/2020 | 24/04/2020 | 06/05/2020 | 0 | TK_Complete | 1112893334 | 125 | 1112893334_125
C730D147BC###0027451 | TT_Task | Customer review and acceptance Final Requirement management plan | 25/05/2020 | 29/06/2020 | 02/02/2020 | 25/03/2020 | 0 | TK_Complete | 1112893334 | 125 | 1112893334_125
C730D147BC###0027461 | TT_Task | Customer review and acceptance Final Verification and Validation management plan | 25/05/2020 | 29/06/2020 | 05/05/2020 | 05/05/2020 | 0 | TK_Complete | 1112893334 | 125 | 1112893334_125
C730D147BC###0027471 | TT_Task | Customer review and acceptance Final Quality management plan | 25/05/2020 | 29/06/2020 | 28/02/2020 | 28/09/2020 | 0 | TK_Complete | 1112893334 | 125 | 1112893334_125
C730D147BC###0027482 | TT_Task | Customer review and acceptance Final Document management plan | 25/05/2020 | 29/06/2020 | 28/02/2020 | 14/07/2020 | 0 | TK_Complete | 1112893334 | 125 | 1112893334_125
C730D147BC###0027492 | TT_Task | Customer review and acceptance Final Interface management plan | 25/08/2020 | 28/09/2020 | 27/07/2020 | 07/08/2020 | 0 | TK_Complete | 1112893334 | 125 | 1112893334_125
C730D147BC###0027505 | TT_Task | Customer review and acceptance Final RAM management plan | 25/05/2020 | 29/06/2020 | 31/03/2020 | 28/09/2020 | 0 | TK_Complete | 1112893334 | 125 | 1112893334_125
C730D147BC###0027513 | TT_Task | Customer review and acceptance Final Obsolecense management plan | 29/09/2020 | 03/11/2020 | 26/08/2020 | 26/08/2020 | 0 | TK_Complete | 1112893334 | 125 | 1112893334_125
C730D147BC###0027522 | TT_Task | Customer review and acceptance Final EMC plan | 25/05/2020 | 29/06/2020 | 23/03/2020 | 19/08/2020 | 0 | TK_Complete | 1112893334 | 125 | 1112893334_125
C730D147BC###0027533 | TT_Task | Customer review and acceptance Final Safety assurance plan | 25/05/2020 | 29/06/2020 | 10/03/2020 | 07/04/2020 | 0 | TK_Complete | 1112893334 | 125 | 1112893334_125
C730D157BC###0012670 | TT_Task | Customer review and acceptance Final Testing ; Commissioning Plan | 25/08/2020 | 28/09/2020 | 02/07/2020 | 02/07/2020 | 0 | TK_Complete | 1112893334 | 125 | 1112893334_125
C730D147BC###0026260 | TT_Task | CBTC SMCSW[System-wide] Initial EMC plan | 01/04/2019 | 08/05/2019 | 18/03/2019 | 31/05/2019 | 0 | TK_Complete | 1112893334 | 124 | 1112893334_124
C730D147BC###0027406 | TT_Task | CBTC SMCSW[System-wide] Final EMC plan | 08/04/2020 | 07/05/2020 | 02/03/2020 | 20/03/2020 | 0 | TK_Complete | 1112893334 | 124 | 1112893334_124
C730D157BC###0036430 | TT_Task | CBTC/Stage-2 SMCSW - EMC Installation Design Guidelines | 10/08/2020 | 04/09/2020 | 06/04/2020 | 17/04/2020 | 0 | TK_Complete | 1112893334 | 124 | 1112893334_124
C730D157BC###0031739 | TT_Task | CBTC/Stage-3 SMCSW - EMC Installation Design Guidelines | 16/10/2020 | 26/11/2020 | 27/07/2020 | 07/08/2020 | 0 | TK_Complete | 1112893334 | 124 | 1112893334_124
C730D157BC###0031784 | TT_Task | CBTC/Stage-3 SMCSW - EMC Design Review | 25/03/2021 | 05/05/2021 | 20/03/2021 | 23/04/2021 | 0 | TK_Complete | 1112893334 | 124 | 1112893334_124
C730D157BC###0031982 | TT_Task | CBTC/Stage-3 SMCSW - EMC on-Site Test Specifications | 08/04/2021 | 19/05/2021 | 25/01/2021 | 29/01/2021 | 0 | TK_Complete | 1112893334 | 124 | 1112893334_124
C730D147BC###0025710 | TT_Task | CBTC SMCSW[System-wide] Initial Safety assurance plan | 27/05/2019 | 12/06/2019 | 27/05/2019 | 17/07/2019 | 0 | TK_Complete | 1112893334 | 123 | 1112893334_123
C730D147BC###0027416 | TT_Task | CBTC SMCSW[System-wide] Final Safety assurance plan | 08/04/2020 | 07/05/2020 | 24/02/2020 | 09/03/2020 | 0 | TK_Complete | 1112893334 | 123 | 1112893334_123
C730D157BC###0038270 | TT_Task | CBTC/Stage-2 SMCSW - Deterministic Safety Assessment | 21/07/2020 | 24/07/2020 | 08/06/2020 | 30/06/2020 | 0 | TK_Complete | 1112893334 | 123 | 1112893334_123
C730D157BC###0032045 | TT_Task | CBTC/Stage-3 SMCSW - Deterministic Safety Assessment | 15/04/2021 | 28/04/2021 | 08/03/2021 | 27/04/2021 | 0 | TK_Complete | 1112893334 | 123 | 1112893334_123
C730D147BC###0025690 | TT_Task | CBTC SMCSW[System-wide] Initial RAM management plan | 01/04/2019 | 13/05/2019 | 18/03/2019 | 31/05/2019 | 0 | TK_Complete | 1112893334 | 122 | 1112893334_122
C730D147BC###0027386 | TT_Task | CBTC SMCSW[System-wide] Final RAM management plan | 01/04/2020 | 30/04/2020 | 06/03/2020 | 30/03/2020 | 0 | TK_Complete | 1112893334 | 122 | 1112893334_122
C730D157BC###0036220 | TT_Task | CBTC/Stage-2 SMCSW - System RAM Analysis Preliminary Report (Including FMECA) | 01/05/2020 | 29/05/2020 | 02/04/2020 | 25/06/2020 | 0 | TK_Complete | 1112893334 | 122 | 1112893334_122
C730D157BC###0037520 | TT_Task | CBTC/Stage-2 SMCSW - System RAM Analysis Report - (*covered at stage 3) | 26/06/2020 | 24/07/2020 | 02/04/2020 | 02/04/2020 | 0 | TK_Complete | 1112893334 | 122 | 1112893334_122
C730D157BC###0037970 | TT_Task | CBTC/Stage-2 SMCSW - System RAM Monitoring and Demonstration Test Plan | 23/07/2020 | 20/08/2020 | 09/03/2020 | 30/03/2020 | 0 | TK_Complete | 1112893334 | 122 | 1112893334_122
C730D157BC###0031847 | TT_Task | CBTC/Stage-3 SMCSW - System RAM Analysis Preliminary Report (Including FMECA) | 15/07/2021 | 18/08/2021 | 26/01/2021 | 08/02/2021 | 0 | TK_Complete | 1112893334 | 122 | 1112893334_122
C730D157BC###0031955 | TT_Task | CBTC/Stage-3 SMCSW - System RAM Analysis Report | 19/08/2021 | 22/09/2021 | 15/02/2021 | 01/04/2021 | 0 | TK_Complete | 1112893334 | 122 | 1112893334_122
C730D157BC###0031991 | TT_Task | CBTC/Stage-3 SMCSW - System RAM Monitoring and Demonstration Test Plan | 24/06/2021 | 28/07/2021 | 01/09/2020 | 15/09/2020 | 0 | TK_Complete | 1112893334 | 122 | 1112893334_122
C730D147BC###0025670 | TT_Task | CBTC SMCSW[System-wide] Initial Document management plan | 01/04/2019 | 13/05/2019 | 18/03/2019 | 30/06/2019 | 0 | TK_Complete | 1112893334 | 121 | 1112893334_121
C730D147BC###0027366 | TT_Task | CBTC SMCSW[System-wide] Final Document management plan | 01/04/2020 | 30/04/2020 | 13/01/2020 | 27/02/2020 | 0 | TK_Complete | 1112893334 | 121 | 1112893334_121
C730D147BC###0025660 | TT_Task | CBTC SMCSW[System-wide] Initial Quality management plan | 01/04/2019 | 08/05/2019 | 18/03/2019 | 30/06/2019 | 0 | TK_Complete | 1112893334 | 120 | 1112893334_120
C730D147BC###0027356 | TT_Task | CBTC SMCSW[System-wide] Final Quality management plan | 01/04/2020 | 30/04/2020 | 13/01/2020 | 27/02/2020 | 0 | TK_Complete | 1112893334 | 120 | 1112893334_120
C730D147BC###0065000 | TT_Task | CBTC SMCSW[System-wide Final] Software quality plan | 25/03/2020 | 23/04/2020 | 20/01/2020 | 26/03/2020 | 0 | TK_Complete | 1112893334 | 120 | 1112893334_120
C720D147CF###0030420 | TT_Task | Trains/Stage-2 - Release of TPS for long profile parts | 23/07/2019 | 19/08/2019 | 23/07/2019 | 19/08/2019 | 0 | TK_Complete | 1112893334 | 12 | 1112893334_12
C720D147CF###0030430 | TT_Task | Trains/Stage-2 - Release of TPS for laser cut ; bend parts | 23/07/2019 | 19/08/2019 | 23/07/2019 | 19/08/2019 | 0 | TK_Complete | 1112893334 | 12 | 1112893334_12
C720D147CF###0030100 | TT_Task | Trains/Stage-2 - Release of TPS for grabpoles and grab handles | 23/07/2019 | 19/08/2019 | 23/07/2019 | 19/08/2019 | 0 | TK_Complete | 1112893334 | 12 | 1112893334_12
C720D147CF###0030110 | TT_Task | Trains/Stage-2 - Release of TPS for hand rails | 23/07/2019 | 19/08/2019 | 23/07/2019 | 19/08/2019 | 0 | TK_Complete | 1112893334 | 12 | 1112893334_12
C720D147CF###0030120 | TT_Task | Trains/Stage-2 - Release of TPS for ceiling with lights | 23/07/2019 | 19/08/2019 | 23/07/2019 | 19/08/2019 | 0 | TK_Complete | 1112893334 | 12 | 1112893334_12
C720D147CF###0030170 | TT_Task | Trains/Stage-2 - Release of TPS for auxiliary converter | 23/07/2019 | 19/08/2019 | 23/07/2019 | 19/08/2019 | 0 | TK_Complete | 1112893334 | 12 | 1112893334_12
C720D147CF###0030180 | TT_Task | Trains/Stage-2 - Release of TPS for coupler | 23/07/2019 | 19/08/2019 | 23/07/2019 | 19/08/2019 | 0 | TK_Complete | 1112893334 | 12 | 1112893334_12
C720D147CF###0030210 | TT_Task | Trains/Stage-2 - Release of TPS for battery ; battery box | 23/07/2019 | 19/08/2019 | 23/07/2019 | 19/08/2019 | 0 | TK_Complete | 1112893334 | 12 | 1112893334_12
C720D147CF###0030220 | TT_Task | Trains/Stage-2 - Release of TPS for brakes | 23/07/2019 | 19/08/2019 | 23/07/2019 | 19/08/2019 | 0 | TK_Complete | 1112893334 | 12 | 1112893334_12
C720D147CF###0030240 | TT_Task | Trains/Stage-2 - Release of TPS for seats | 23/07/2019 | 19/08/2019 | 23/07/2019 | 19/08/2019 | 0 | TK_Complete | 1112893334 | 12 | 1112893334_12
C730D147BC###0025650 | TT_Task | CBTC SMCSW[System-wide] Initial Verification and Validation management plan | 01/04/2019 | 13/05/2019 | 18/03/2019 | 31/05/2019 | 0 | TK_Complete | 1112893334 | 119 | 1112893334_119
C730D147BC###0027346 | TT_Task | CBTC SMCSW[System-wide] Final Verification and Validation management plan | 25/03/2020 | 23/04/2020 | 09/03/2020 | 04/05/2020 | 0 | TK_Complete | 1112893334 | 119 | 1112893334_119
C730D157BC###0045560 | TT_Task | CBTC SMCSW[System-wide] Final Testing ; Commissioning Plan | 25/05/2020 | 22/06/2020 | 03/03/2020 | 02/07/2020 | 0 | TK_Complete | 1112893334 | 119 | 1112893334_119
C730D147BC###0065085 | TT_Task | CBTC SMCSW[System-wide Final] As-built drawings, test records, safety case (A29) | 20/06/2023 | 20/06/2023 | nan | nan | 0 | TK_NotStart | 1112893334 | 119 | 1112893334_119
C730D147BC###0010822 | TT_Task | CBTC/Stage-2 SMCSW - Design Requirement Coverage Verification Report | 07/07/2020 | 27/07/2020 | 26/05/2020 | 19/06/2020 | 0 | TK_Complete | 1112893334 | 119 | 1112893334_119
C730D157BC###0022099 | TT_Task | CBTC/Stage-3 SMCSW - Design Requirement Coverage Verification Report | 13/05/2021 | 02/06/2021 | 01/03/2021 | 26/03/2021 | 0 | TK_Complete | 1112893334 | 119 | 1112893334_119
C730D157BC###N029453 | TT_Task | CBTC/Stage-3 SMCSW - Software Proofing Platform (SPP) Test for City | 26/07/2022 | 01/08/2022 | nan | nan | 239 | TK_NotStart | 1112893334 | 119 | 1112893334_119
C730D147BC###0025620 | TT_Task | CBTC SMCSW[System-wide] Initial Engineering management plan | 01/04/2019 | 29/04/2019 | 18/03/2019 | 31/05/2019 | 0 | TK_Complete | 1112893334 | 118 | 1112893334_118
C730D147BC###0025630 | TT_Task | CBTC SMCSW[System-wide] Initial Configuration management plan | 01/04/2019 | 13/05/2019 | 18/03/2019 | 31/05/2019 | 0 | TK_Complete | 1112893334 | 118 | 1112893334_118
C730D147BC###0025640 | TT_Task | CBTC SMCSW[System-wide] Initial Requirement management plan | 04/04/2019 | 16/05/2019 | 18/03/2019 | 31/05/2019 | 0 | TK_Complete | 1112893334 | 118 | 1112893334_118
C730D147BC###0025680 | TT_Task | CBTC SMCSW[System-wide] Initial Interface management plan | 04/04/2019 | 16/05/2019 | 18/03/2019 | 30/06/2019 | 0 | TK_Complete | 1112893334 | 118 | 1112893334_118
C730D147BC###0025700 | TT_Task | CBTC SMCSW[System-wide] Initial Obsolecense management plan | 01/04/2019 | 08/05/2019 | 18/03/2019 | 31/05/2019 | 0 | TK_Complete | 1112893334 | 118 | 1112893334_118
C730D147BC###0027113 | TT_Task | CBTC SMCSW[System-wide] Final Installation Management Plan | 25/05/2020 | 22/06/2020 | 10/03/2020 | 25/06/2020 | 0 | TK_Complete | 1112893334 | 118 | 1112893334_118
C730D147BC###0027312 | TT_Task | CBTC SMCSW[System-wide] Final Engineering management plan | 25/03/2020 | 16/04/2020 | 20/01/2020 | 30/03/2020 | 0 | TK_Complete | 1112893334 | 118 | 1112893334_118
C730D147BC###0027322 | TT_Task | CBTC SMCSW[System-wide] Final Configuration management plan | 25/03/2020 | 23/04/2020 | 27/01/2020 | 06/05/2020 | 0 | TK_Complete | 1112893334 | 118 | 1112893334_118
C730D147BC###0027336 | TT_Task | CBTC SMCSW[System-wide] Final Requirement management plan | 25/03/2020 | 07/05/2020 | 03/02/2020 | 20/02/2020 | 0 | TK_Complete | 1112893334 | 118 | 1112893334_118
C730D147BC###0027376 | TT_Task | CBTC SMCSW[System-wide] Final Interface management plan | 25/05/2020 | 15/06/2020 | 01/02/2020 | 20/07/2020 | 0 | TK_Complete | 1112893334 | 118 | 1112893334_118
C730D147BC###0027396 | TT_Task | CBTC SMCSW[System-wide] Final Obsolecense management plan | 25/08/2020 | 31/08/2020 | 24/08/2020 | 25/08/2020 | 0 | TK_Complete | 1112893334 | 118 | 1112893334_118
C730K147CT###0020370 | TT_Task | Completion of Collabration Events - SMTF[N] ; City (Schedule 25) | 28/04/2023 | 04/05/2023 | nan | nan | 479 | TK_NotStart | 1112893334 | 117 | 1112893334_117
C730C157CK###D42130 | TT_Task | *TRIP 7.1 Revised Site Access (VIC-CST DN Track StationBox area) (S61,T5,I5) | 25/03/2022 | 25/03/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 116 | 1112893334_116
C730K147C4###DE10610 | TT_Task | Revised Site Access Date - Victoria Cross Station/SER as per (S61,T6,I9) | 10/06/2022 | 27/06/2022 | 05/03/2022 | 22/03/2022 | 0 | TK_Complete | 1112893334 | 116 | 1112893334_116
C730K147C5###DE10650 | TT_Task | Revised Site Access Date - Barangaroo Station/SER as per (S61,T6,I13) | 27/04/2022 | 03/05/2022 | nan | nan | 0 | TK_NotStart | 1112893334 | 116 | 1112893334_116
C730K147C6###DE10690 | TT_Task | Revised Site Access Date - Martin Place Station/SER as per (S61,T6,I16) | 23/03/2022 | 27/03/2022 | 23/03/2022 | nan | 0 | TK_Active | 1112893334 | 116 | 1112893334_116
C730K147C7###DE10700 | TT_Task | Revised Site Access Date - Pitt Street Station/SER as per (S61,T6,I25) | 27/04/2022 | 13/05/2022 | 08/03/2022 | nan | 0 | TK_Active | 1112893334 | 116 | 1112893334_116
C720T147CF###N10710 | TT_Task | Interface Test (City Section) : Integration Test Run | 19/05/2023 | 24/05/2023 | nan | nan | 24 | TK_NotStart | 1112893334 | 115 | 1112893334_115
C720T147CF###N10720 | TT_Task | Interface Test (City Section) : Integration Run | 06/04/2023 | 29/05/2023 | nan | nan | 55 | TK_NotStart | 1112893334 | 115 | 1112893334_115
C730T157CT###0056050 | TT_Task | All City Section SIT 15 - MSS integration test | 11/01/2023 | 17/01/2023 | nan | nan | 0 | TK_NotStart | 1112893334 | 115 | 1112893334_115
C730T157CT###0056100 | TT_Task | All City Section SIT 3 - ATS integration test | 23/01/2023 | 03/02/2023 | nan | nan | 0 | TK_NotStart | 1112893334 | 115 | 1112893334_115
C720T147CF###N10590 | TT_Task | Interface Test (City Section) : RS/PSD PSD-RS-IT-01 Platform Gap Test | 08/02/2023 | 14/02/2023 | nan | nan | 0 | TK_NotStart | 1112893334 | 114 | 1112893334_114
C720T147CF###N10600 | TT_Task | Interface Test (City Section) : RS/PSD PSD-RS-IT-02 Door Pitch Test | 08/02/2023 | 14/02/2023 | nan | nan | 0 | TK_NotStart | 1112893334 | 114 | 1112893334_114
C720T147CF###N10610 | TT_Task | Interface Test (City Section) : RS/PSD PSD-RS-IT-03 Emergency Door Release Test | 08/02/2023 | 14/02/2023 | nan | nan | 0 | TK_NotStart | 1112893334 | 114 | 1112893334_114
C720T147CF###N10680 | TT_Task | Interface Test (City Section) : RS/PSD PSD-RS-IT-04 Synchronisation of Door Operation Test | 11/05/2023 | 18/05/2023 | nan | nan | 0 | TK_NotStart | 1112893334 | 114 | 1112893334_114
C720T147CF###N10690 | TT_Task | Interface Test (City Section) : RS/PSD PSD-RS-IT-06 Synchronisation of Inhibit Door Operation Test | 11/05/2023 | 18/05/2023 | nan | nan | 0 | TK_NotStart | 1112893334 | 114 | 1112893334_114
C720T147CF###N10700 | TT_Task | Interface Test (City Section) : RS/PSD PSD-RS-IT-04 Train movement inhibition Test (PSD Fault) | 11/05/2023 | 18/05/2023 | nan | nan | 0 | TK_NotStart | 1112893334 | 114 | 1112893334_114
C720T147CF###N10570 | TT_Task | Interface Test (City Section) : RS/TRK Kinematic Envelope Test | 06/01/2023 | 19/01/2023 | nan | nan | 0 | TK_NotStart | 1112893334 | 113 | 1112893334_113
C720T147CF###N10580 | TT_Task | Interface Test (City Section) : RS/TRK Train Running Safety and Ride Index | 25/01/2023 | 07/02/2023 | nan | nan | 0 | TK_NotStart | 1112893334 | 113 | 1112893334_113
C720T147CF###N10620 | TT_Task | Interface Test (City Section) : RS/RAD Test | 15/02/2023 | 21/02/2023 | nan | nan | 0 | TK_NotStart | 1112893334 | 113 | 1112893334_113
C720T147CF###N10660 | TT_Task | Interface Test (City Section) : RS/SIG Test ***N/A*** | 25/10/2021 | 02/11/2021 | 25/10/2021 | 25/10/2021 | 0 | TK_Complete | 1112893334 | 113 | 1112893334_113
C720T147CF###N10370 | TT_Task | City Section Group 7 : PACIS Dynamic Test (Campaign 1) | 22/02/2023 | 07/03/2023 | nan | nan | 0 | TK_NotStart | 1112893334 | 112 | 1112893334_112
C720T147CF###N10380 | TT_Task | City Section Group 7 : PACIS Dynamic Test (Campaign 2) | 06/04/2023 | 19/04/2023 | nan | nan | 0 | TK_NotStart | 1112893334 | 112 | 1112893334_112
C720T147CF###N10330 | TT_Task | City Section Group 5 : Dynamic Noise Test | 08/03/2023 | 16/03/2023 | nan | nan | 0 | TK_NotStart | 1112893334 | 111 | 1112893334_111
C720T147CF###N10630 | TT_Task | Interface Test (City Section) : RS/TRK Dynamic Noise Test (Internal and External) | 08/03/2023 | 16/03/2023 | nan | nan | 0 | TK_NotStart | 1112893334 | 111 | 1112893334_111
C720T147CF###N10390 | TT_Task | City Section Group 4 : Car-Car Clearance | 20/01/2023 | 24/01/2023 | nan | nan | 0 | TK_NotStart | 1112893334 | 110 | 1112893334_110
C720D147CF###0030410 | TT_Task | Trains/Stage-2 - Release of TPS for EUF | 23/07/2019 | 19/08/2019 | 23/07/2019 | 19/08/2019 | 0 | TK_Complete | 1112893334 | 11 | 1112893334_11
C720D147CF###0030090 | TT_Task | Trains/Stage-2 - Release of TPS for front mask | 23/07/2019 | 19/08/2019 | 23/07/2019 | 19/08/2019 | 0 | TK_Complete | 1112893334 | 11 | 1112893334_11
C720D147CF###0030190 | TT_Task | Trains/Stage-2 - Release of TPS for gangway | 23/07/2019 | 19/08/2019 | 23/07/2019 | 19/08/2019 | 0 | TK_Complete | 1112893334 | 11 | 1112893334_11
C720D147CF###0030200 | TT_Task | Trains/Stage-2 - Release of TPS for pantograph | 23/07/2019 | 19/08/2019 | 23/07/2019 | 19/08/2019 | 0 | TK_Complete | 1112893334 | 11 | 1112893334_11
C720D147CF###0030270 | TT_Task | Trains/Stage-2 - Release of TPS for windows | 23/07/2019 | 19/08/2019 | 23/07/2019 | 19/08/2019 | 0 | TK_Complete | 1112893334 | 11 | 1112893334_11
C720D147CF###0030480 | TT_Task | Trains/Stage-2 - Release of TPS for PACIS | 17/09/2019 | 15/10/2019 | 17/09/2019 | 15/10/2019 | 0 | TK_Complete | 1112893334 | 11 | 1112893334_11
C720D147CF###0030030 | TT_Task | Trains/Stage-2 - Release of TPS for bogie frame | 23/07/2019 | 19/08/2019 | 23/07/2019 | 19/08/2019 | 0 | TK_Complete | 1112893334 | 11 | 1112893334_11
C720T147CF###N10340 | TT_Task | City Section Group 4 : Current Collector Test | 20/04/2023 | 03/05/2023 | nan | nan | 0 | TK_NotStart | 1112893334 | 109 | 1112893334_109
C720T147CF###N10360 | TT_Task | City Section Group 6 : EMC Test | 23/03/2023 | 05/04/2023 | nan | nan | 0 | TK_NotStart | 1112893334 | 109 | 1112893334_109
C720T147CF###N10640 | TT_Task | Interface Test (City Section) : RS/OHW EMC Compatibility Test | 23/03/2023 | 05/04/2023 | nan | nan | 0 | TK_NotStart | 1112893334 | 109 | 1112893334_109
C720T147CF###N10650 | TT_Task | Interface Test (City Section) : RS/OHW Current Collector Dynamic Test | 20/04/2023 | 03/05/2023 | nan | nan | 0 | TK_NotStart | 1112893334 | 109 | 1112893334_109
C720T147CF###N10670 | TT_Task | Interface Test (City Section) : RS/OHW Current and Voltage Test | 04/05/2023 | 10/05/2023 | nan | nan | 0 | TK_NotStart | 1112893334 | 109 | 1112893334_109
C720T147CF###N10300 | TT_Task | City Section Group 4 : Accelerated Traction Braking performance verification (1st Campaign) | 08/02/2023 | 08/02/2023 | nan | nan | 0 | TK_NotStart | 1112893334 | 108 | 1112893334_108
C720T147CF###N10320 | TT_Task | City Section Group 4 : Accelerated Traction Braking performance verification (2nd Campaign) | 06/04/2023 | 06/04/2023 | nan | nan | 0 | TK_NotStart | 1112893334 | 108 | 1112893334_108
C720T147CF###N10290 | TT_Task | City Section Group 4 : Kinematic Gauge Test | 06/01/2023 | 19/01/2023 | nan | nan | 0 | TK_NotStart | 1112893334 | 107 | 1112893334_107
C720T147CF###N10350 | TT_Task | City Section Group 6 : Alstom on track test specification (ride Index) | 25/01/2023 | 07/02/2023 | nan | nan | 0 | TK_NotStart | 1112893334 | 107 | 1112893334_107
C720T147CF###N10280 | TT_Task | City Section Group 4 : Parking Brake Holding Type Test | 22/02/2023 | 01/03/2023 | nan | nan | 32 | TK_NotStart | 1112893334 | 106 | 1112893334_106
C720T147CF###N10310 | TT_Task | City Section Group 4 : Rescue Type Test Procedure | 17/03/2023 | 22/03/2023 | nan | nan | 0 | TK_NotStart | 1112893334 | 106 | 1112893334_106
C720T147CF###0051490 | TT_Task | Group 5 validation tests in City mainline | 08/03/2023 | 16/03/2023 | nan | nan | 272 | TK_NotStart | 1112893334 | 105 | 1112893334_105
C720T157CT###0065010 | TT_Task | Report Submission - Group 4 validation tests in City mainline | 04/05/2023 | 17/05/2023 | nan | nan | 0 | TK_NotStart | 1112893334 | 105 | 1112893334_105
C720T157CT###0065020 | TT_Task | Report Submission - Group 5 validation tests in City mainline | 04/05/2023 | 17/05/2023 | nan | nan | 0 | TK_NotStart | 1112893334 | 105 | 1112893334_105
C720T157CT###0065030 | TT_Task | Report Submission - Group 6 validation tests in City mainline | 06/04/2023 | 19/04/2023 | nan | nan | 0 | TK_NotStart | 1112893334 | 105 | 1112893334_105
C720T157CT###0065040 | TT_Task | Report Submission - Group 7 validation tests in City mainline | 20/04/2023 | 03/05/2023 | nan | nan | 0 | TK_NotStart | 1112893334 | 105 | 1112893334_105
C720T157CT###0065015 | TT_Task | Report Acceptance - Group 4 validation tests in City mainline | 18/05/2023 | 07/06/2023 | nan | nan | 0 | TK_NotStart | 1112893334 | 105 | 1112893334_105
C720T157CT###0065025 | TT_Task | Report Acceptance - Group 5 validation tests in City mainline | 18/05/2023 | 07/06/2023 | nan | nan | 0 | TK_NotStart | 1112893334 | 105 | 1112893334_105
C720T157CT###0065035 | TT_Task | Report Acceptance - Group 6 validation tests in City mainline | 20/04/2023 | 10/05/2023 | nan | nan | 160 | TK_NotStart | 1112893334 | 105 | 1112893334_105
C720T157CT###0065045 | TT_Task | Report Acceptance - Group 7 validation tests in City mainline | 04/05/2023 | 24/05/2023 | nan | nan | 80 | TK_NotStart | 1112893334 | 105 | 1112893334_105
C720T147CF###0051470 | TT_Task | Group 1 validation tests in City mainline ***N/A*** | 25/10/2021 | 26/10/2021 | 25/10/2021 | 25/10/2021 | 0 | TK_Complete | 1112893334 | 105 | 1112893334_105
C720T157CT###0065000 | TT_Task | Report Submission - Group 1 validation tests in City mainline ***N/A*** | 27/10/2021 | 09/11/2021 | 25/10/2021 | 25/10/2021 | 0 | TK_Complete | 1112893334 | 105 | 1112893334_105
C720T157CT###0065005 | TT_Task | Report Acceptance - Group 1 validation tests in City mainline ***N/A*** | 25/10/2021 | 12/11/2021 | 25/10/2021 | 25/10/2021 | 0 | TK_Complete | 1112893334 | 105 | 1112893334_105
C720O147CF###0060000 | TT_Task | Train 1 MFO (Outside Alstom Scope) | 08/08/2022 | 22/05/2024 | nan | nan | 0 | TK_NotStart | 1112893334 | 104 | 1112893334_104
C720O147CF###60250 | TT_Task | Train 2 MFO (Outside Alstom Scope) | 15/08/2022 | 30/03/2024 | nan | nan | 0 | TK_NotStart | 1112893334 | 104 | 1112893334_104
C720O147CF###60260 | TT_Task | Train 3 MFO (Outside Alstom Scope) | 22/08/2022 | 05/03/2024 | nan | nan | 0 | TK_NotStart | 1112893334 | 104 | 1112893334_104
C720O147CF###60270 | TT_Task | Train 4 MFO (Outside Alstom Scope) | 03/09/2022 | 16/02/2024 | nan | nan | 0 | TK_NotStart | 1112893334 | 104 | 1112893334_104
C720O147CF###60280 | TT_Task | Train 5 MFO (Outside Alstom Scope) | 10/09/2022 | 23/02/2024 | nan | nan | 0 | TK_NotStart | 1112893334 | 104 | 1112893334_104
C720O147CF###60290 | TT_Task | Train 6 MFO (Outside Alstom Scope) | 17/09/2022 | 01/03/2024 | nan | nan | 0 | TK_NotStart | 1112893334 | 104 | 1112893334_104
C720O147CF###60300 | TT_Task | Train 7 MFO (Outside Alstom Scope) | 24/09/2022 | 06/02/2024 | nan | nan | 0 | TK_NotStart | 1112893334 | 104 | 1112893334_104
C720O147CF###60310 | TT_Task | Train 8 MFO (Outside Alstom Scope) | 01/10/2022 | 13/01/2024 | nan | nan | 0 | TK_NotStart | 1112893334 | 104 | 1112893334_104
C720O147CF###60320 | TT_Task | Train 9 MFO (Outside Alstom Scope) | 08/10/2022 | 21/12/2023 | nan | nan | 0 | TK_NotStart | 1112893334 | 104 | 1112893334_104
C720O147CF###60330 | TT_Task | Train 10 MFO (Outside Alstom Scope) | 01/11/2022 | 14/12/2023 | nan | nan | 0 | TK_NotStart | 1112893334 | 104 | 1112893334_104
C720O147CF###60340 | TT_Task | Train 11 MFO (Outside Alstom Scope) | 01/12/2022 | 14/12/2023 | nan | nan | 0 | TK_NotStart | 1112893334 | 104 | 1112893334_104
C720O147CF###60350 | TT_Task | Train 12 MFO (Outside Alstom Scope) | 01/01/2023 | 14/12/2023 | nan | nan | 0 | TK_NotStart | 1112893334 | 104 | 1112893334_104
C720O147CF###60360 | TT_Task | Train 13 MFO (Outside Alstom Scope) | 01/01/2023 | 14/12/2023 | nan | nan | 0 | TK_NotStart | 1112893334 | 104 | 1112893334_104
C720O147CF###60370 | TT_Task | Train 14 MFO (Outside Alstom Scope) | 01/01/2023 | 14/12/2023 | nan | nan | 0 | TK_NotStart | 1112893334 | 104 | 1112893334_104
C720O147CF###60380 | TT_Task | Train 15 MFO (Outside Alstom Scope) | 01/02/2023 | 14/12/2023 | nan | nan | 0 | TK_NotStart | 1112893334 | 104 | 1112893334_104
C720O147CF###60390 | TT_Task | Train 16 MFO (Outside Alstom Scope) | 01/02/2023 | 14/12/2023 | nan | nan | 0 | TK_NotStart | 1112893334 | 104 | 1112893334_104
C720O147CF###60400 | TT_Task | Train 17 MFO (Outside Alstom Scope) | 01/03/2023 | 14/12/2023 | nan | nan | 0 | TK_NotStart | 1112893334 | 104 | 1112893334_104
C720O147CF###60410 | TT_Task | Train 18 MFO (Outside Alstom Scope) | 01/04/2023 | 14/12/2023 | nan | nan | 0 | TK_NotStart | 1112893334 | 104 | 1112893334_104
C720O147CF###60420 | TT_Task | Train 19 MFO (Outside Alstom Scope) | 01/04/2023 | 14/12/2023 | nan | nan | 0 | TK_NotStart | 1112893334 | 104 | 1112893334_104
C720O147CF###60430 | TT_Task | Train 20 MFO (Outside Alstom Scope) | 01/05/2023 | 14/12/2023 | nan | nan | 0 | TK_NotStart | 1112893334 | 104 | 1112893334_104
C720O147CF###60440 | TT_Task | Train 21 MFO (Outside Alstom Scope) | 01/05/2023 | 14/12/2023 | nan | nan | 0 | TK_NotStart | 1112893334 | 104 | 1112893334_104
C720O147CF###60450 | TT_Task | Train 22 MFO (Outside Alstom Scope) | 01/05/2023 | 14/12/2023 | nan | nan | 0 | TK_NotStart | 1112893334 | 104 | 1112893334_104
C720O147CF###60460 | TT_Task | Train 23 MFO (Outside Alstom Scope) | 01/06/2023 | 14/12/2023 | nan | nan | 0 | TK_NotStart | 1112893334 | 104 | 1112893334_104
C730T157CT###0056420 | TT_Task | Train integration run @ City Section CSW-T2 | 28/06/2023 | 28/06/2023 | nan | nan | 0 | TK_NotStart | 1112893334 | 103 | 1112893334_103
C730T157CT###0056430 | TT_Task | Train integration run @ City Section CSW-T3 | 29/06/2023 | 29/06/2023 | nan | nan | 0 | TK_NotStart | 1112893334 | 103 | 1112893334_103
C730T157CT###0056440 | TT_Task | Train integration run @ City Section CSW-T4 | 30/06/2023 | 30/06/2023 | nan | nan | 0 | TK_NotStart | 1112893334 | 103 | 1112893334_103
C730T157CT###0056450 | TT_Task | Train integration run @ City Section CSW-T5 | 03/07/2023 | 03/07/2023 | nan | nan | 0 | TK_NotStart | 1112893334 | 103 | 1112893334_103
C730T157CT###0056460 | TT_Task | Train integration run @ City Section CSW-T6 | 04/07/2023 | 04/07/2023 | nan | nan | 0 | TK_NotStart | 1112893334 | 103 | 1112893334_103
C730T157CT###0056470 | TT_Task | Train integration run @ City Section CSW-T7 | 05/07/2023 | 05/07/2023 | nan | nan | 0 | TK_NotStart | 1112893334 | 103 | 1112893334_103
C730T157CT###0056480 | TT_Task | Train integration run @ City Section CSW-T8 | 06/07/2023 | 06/07/2023 | nan | nan | 0 | TK_NotStart | 1112893334 | 103 | 1112893334_103
C730T157CT###0056490 | TT_Task | Train integration run @ City Section CSW-T9 | 07/07/2023 | 07/07/2023 | nan | nan | 0 | TK_NotStart | 1112893334 | 103 | 1112893334_103
C730T157CT###0056500 | TT_Task | Train integration run @ City Section CSW-T10 | 10/07/2023 | 10/07/2023 | nan | nan | 0 | TK_NotStart | 1112893334 | 103 | 1112893334_103
C730T157CT###0056510 | TT_Task | Train integration run @ City Section CSW-T11 | 11/07/2023 | 11/07/2023 | nan | nan | 0 | TK_NotStart | 1112893334 | 103 | 1112893334_103
C730T157CT###0056520 | TT_Task | Train integration run @ City Section CSW-T13 | 13/07/2023 | 13/07/2023 | nan | nan | 0 | TK_NotStart | 1112893334 | 103 | 1112893334_103
C730T157CT###0056530 | TT_Task | Train integration run @ City Section CSW-T12 | 12/07/2023 | 12/07/2023 | nan | nan | 0 | TK_NotStart | 1112893334 | 103 | 1112893334_103
C730T157CT###0056540 | TT_Task | Train integration run @ City Section CSW-T14 | 14/07/2023 | 14/07/2023 | nan | nan | 0 | TK_NotStart | 1112893334 | 103 | 1112893334_103
C730T157CT###0056550 | TT_Task | Train integration run @ City Section CSW-T15 | 17/07/2023 | 17/07/2023 | nan | nan | 0 | TK_NotStart | 1112893334 | 103 | 1112893334_103
C730T157CT###0056560 | TT_Task | Train integration run @ City Section CSW-T16 | 18/07/2023 | 18/07/2023 | nan | nan | 0 | TK_NotStart | 1112893334 | 103 | 1112893334_103
C730T157CT###0056570 | TT_Task | Train integration run @ City Section CSW-T17 | 19/07/2023 | 19/07/2023 | nan | nan | 0 | TK_NotStart | 1112893334 | 103 | 1112893334_103
C730T157CT###0056580 | TT_Task | Train integration run @ City Section CSW-T18 | 20/07/2023 | 20/07/2023 | nan | nan | 0 | TK_NotStart | 1112893334 | 103 | 1112893334_103
C730T157CT###0056590 | TT_Task | Train integration run @ City Section CSW-T19 | 21/07/2023 | 21/07/2023 | nan | nan | 0 | TK_NotStart | 1112893334 | 103 | 1112893334_103
C730T157CT###0056600 | TT_Task | Train integration run @ City Section CSW-T20 | 24/07/2023 | 24/07/2023 | nan | nan | 0 | TK_NotStart | 1112893334 | 103 | 1112893334_103
C730T157CT###0056610 | TT_Task | Train integration run @ City Section CSW-T21 | 25/07/2023 | 25/07/2023 | nan | nan | 0 | TK_NotStart | 1112893334 | 103 | 1112893334_103
C730T157CT###0056620 | TT_Task | Train integration run @ City Section CSW-T22 | 26/07/2023 | 26/07/2023 | nan | nan | 0 | TK_NotStart | 1112893334 | 103 | 1112893334_103
C730T157CT###0056630 | TT_Task | Train integration run @ City Section CSW-T23 | 27/07/2023 | 27/07/2023 | nan | nan | 0 | TK_NotStart | 1112893334 | 103 | 1112893334_103
C730T157CT###0056200 | TT_Task | Train integration run @ City Section NW-T2 | 30/05/2023 | 30/05/2023 | nan | nan | 0 | TK_NotStart | 1112893334 | 102 | 1112893334_102
C730T157CT###0056210 | TT_Task | Train integration run @ City Section NW-T3 | 31/05/2023 | 31/05/2023 | nan | nan | 0 | TK_NotStart | 1112893334 | 102 | 1112893334_102
C730T157CT###0056220 | TT_Task | Train integration run @ City Section NW-T4 | 01/06/2023 | 01/06/2023 | nan | nan | 0 | TK_NotStart | 1112893334 | 102 | 1112893334_102
C730T157CT###0056230 | TT_Task | Train integration run @ City Section NW-T5 | 02/06/2023 | 02/06/2023 | nan | nan | 0 | TK_NotStart | 1112893334 | 102 | 1112893334_102
C730T157CT###0056240 | TT_Task | Train integration run @ City Section NW-T6 | 05/06/2023 | 05/06/2023 | nan | nan | 0 | TK_NotStart | 1112893334 | 102 | 1112893334_102
C730T157CT###0056250 | TT_Task | Train integration run @ City Section NW-T7 | 06/06/2023 | 06/06/2023 | nan | nan | 0 | TK_NotStart | 1112893334 | 102 | 1112893334_102
C730T157CT###0056260 | TT_Task | Train integration run @ City Section NW-T8 | 07/06/2023 | 07/06/2023 | nan | nan | 0 | TK_NotStart | 1112893334 | 102 | 1112893334_102
C730T157CT###0056270 | TT_Task | Train integration run @ City Section NW-T9 | 08/06/2023 | 08/06/2023 | nan | nan | 0 | TK_NotStart | 1112893334 | 102 | 1112893334_102
C730T157CT###0056280 | TT_Task | Train integration run @ City Section NW-T10 | 09/06/2023 | 09/06/2023 | nan | nan | 0 | TK_NotStart | 1112893334 | 102 | 1112893334_102
C730T157CT###0056290 | TT_Task | Train integration run @ City Section NW-T11 | 12/06/2023 | 12/06/2023 | nan | nan | 0 | TK_NotStart | 1112893334 | 102 | 1112893334_102
C730T157CT###0056300 | TT_Task | Train integration run @ City Section NW-T12 | 13/06/2023 | 13/06/2023 | nan | nan | 0 | TK_NotStart | 1112893334 | 102 | 1112893334_102
C730T157CT###0056310 | TT_Task | Train integration run @ City Section NW-T13 | 14/06/2023 | 14/06/2023 | nan | nan | 0 | TK_NotStart | 1112893334 | 102 | 1112893334_102
C730T157CT###0056320 | TT_Task | Train integration run @ City Section NW-T14 | 15/06/2023 | 15/06/2023 | nan | nan | 0 | TK_NotStart | 1112893334 | 102 | 1112893334_102
C730T157CT###0056330 | TT_Task | Train integration run @ City Section NW-T15 | 16/06/2023 | 16/06/2023 | nan | nan | 0 | TK_NotStart | 1112893334 | 102 | 1112893334_102
C730T157CT###0056340 | TT_Task | Train integration run @ City Section NW-T16 | 19/06/2023 | 19/06/2023 | nan | nan | 0 | TK_NotStart | 1112893334 | 102 | 1112893334_102
C730T157CT###0056350 | TT_Task | Train integration run @ City Section NW-T17 | 20/06/2023 | 20/06/2023 | nan | nan | 0 | TK_NotStart | 1112893334 | 102 | 1112893334_102
C730T157CT###0056360 | TT_Task | Train integration run @ City Section NW-T18 | 21/06/2023 | 21/06/2023 | nan | nan | 0 | TK_NotStart | 1112893334 | 102 | 1112893334_102
C730T157CT###0056370 | TT_Task | Train integration run @ City Section NW-T19 | 22/06/2023 | 22/06/2023 | nan | nan | 0 | TK_NotStart | 1112893334 | 102 | 1112893334_102
C730T157CT###0056380 | TT_Task | Train integration run @ City Section NW-T20 | 23/06/2023 | 23/06/2023 | nan | nan | 0 | TK_NotStart | 1112893334 | 102 | 1112893334_102
C730T157CT###0056390 | TT_Task | Train integration run @ City Section NW-T21 | 26/06/2023 | 26/06/2023 | nan | nan | 0 | TK_NotStart | 1112893334 | 102 | 1112893334_102
C730T157CT###0056400 | TT_Task | Train integration run @ City Section NW-T22 | 27/06/2023 | 27/06/2023 | nan | nan | 0 | TK_NotStart | 1112893334 | 102 | 1112893334_102
C730T157CT###0015055 | TT_Task | Train integration test run @ City Section CSW-T1 Report Acceptance | 13/06/2023 | 03/07/2023 | nan | nan | 144 | TK_NotStart | 1112893334 | 101 | 1112893334_101
C730T157CT###0015060 | TT_Task | Train integration test run @ City Section NW -T1 Report Acceptance | 13/06/2023 | 03/07/2023 | nan | nan | 0 | TK_NotStart | 1112893334 | 101 | 1112893334_101
C730T157CT###0056821 | TT_Task | Train integration test run @ City Section NW-T1 | 16/05/2023 | 29/05/2023 | nan | nan | 0 | TK_NotStart | 1112893334 | 101 | 1112893334_101
C730T157CT###0057041 | TT_Task | Train integration test run @ City Section CSW-T1 | 16/05/2023 | 29/05/2023 | nan | nan | 0 | TK_NotStart | 1112893334 | 101 | 1112893334_101
C730T157CT###0057272 | TT_Task | Train integration test run @ City Section NW -T1 Report Submission | 30/05/2023 | 12/06/2023 | nan | nan | 0 | TK_NotStart | 1112893334 | 101 | 1112893334_101
C730T157CT###0057283 | TT_Task | Train integration test run @ City Section CSW-T1 Report Submission | 30/05/2023 | 12/06/2023 | nan | nan | 0 | TK_NotStart | 1112893334 | 101 | 1112893334_101
C720T147CF###N51542 | TT_Task | Train 01 Reliability Test Run | 27/12/2021 | 31/12/2021 | 12/01/2022 | 28/01/2022 | 0 | TK_Complete | 1112893334 | 100 | 1112893334_100
C730T018CB###N316990 | TT_Task | RS Dynamic test for Train 01 to Train 23 | 21/03/2023 | 24/03/2023 | nan | nan | 1 | TK_NotStart | 1112893334 | 100 | 1112893334_100
C720D147CF###0020270 | TT_Task | Trains/Stage-2 - RSAD L1 for TDE | 01/07/2019 | 20/09/2019 | 10/05/2019 | 23/08/2019 | 0 | TK_Complete | 1112893334 | 10 | 1112893334_10
C720D147CF###0020280 | TT_Task | Trains/Stage-2 - RSAD L1 for TSE | 01/07/2019 | 20/09/2019 | 10/05/2019 | 23/08/2019 | 0 | TK_Complete | 1112893334 | 10 | 1112893334_10
C720D147CF###0030010 | TT_Task | Trains/Stage-2 - RSAD L2 for TDE | 01/07/2019 | 23/08/2019 | 27/05/2019 | 23/07/2019 | 0 | TK_Complete | 1112893334 | 10 | 1112893334_10
C720D147CF###0030020 | TT_Task | Trains/Stage-2 - RSAD L2 for TSE | 01/07/2019 | 23/08/2019 | 27/05/2019 | 23/07/2019 | 0 | TK_Complete | 1112893334 | 10 | 1112893334_10
C720D147CF###0030300 | TT_Task | Trains/Stage-2 - RSAD L2 for TCE | 23/07/2019 | 16/09/2019 | 23/07/2019 | 16/09/2019 | 0 | TK_Complete | 1112893334 | 10 | 1112893334_10
C720D147CF###0030720 | TT_Task | Verification - Finalized PS/SPR DOOR(s) extract for modifications made during UAP-B | 25/03/2020 | 29/03/2020 | 07/01/2020 | 13/01/2020 | 0 | TK_Complete | 1112893334 | 1 | 1112893334_1