## Sheet1
ID | TaskType | Label | PlannedStart | PlannedEnd | ActualStart | ActualEnd | Float | Status
A3920 | TT_Mile | ENVIRONMENTAL PERMIT ISSUED | 28/06/2021 | 28/06/2021 | 14/06/2016 | 14/06/2016 | 0 | TK_Complete
A3930 | TT_Mile | PNTP TO OEM (START ENGINEERING) | 28/06/2021 | 28/06/2021 | 03/11/2016 | 03/11/2016 | 0 | TK_Complete
A3940 | TT_Mile | PNTP TO ADVANCED WORKS CONTRACTOR FOR TRIAL PILES | 28/06/2021 | 28/06/2021 | 07/11/2016 | 07/11/2016 | 0 | TK_Complete
A3950 | TT_Mile | HONG KONG GOVERNMENT APPROVAL / NTP | 28/06/2021 | 28/06/2021 | 13/12/2016 | 13/12/2016 | 0 | TK_Complete
A3960 | TT_Mile | ADVANCED WORKS CONTRACT AWARD | 28/06/2021 | 28/06/2021 | 15/12/2016 | 15/12/2016 | 0 | TK_Complete
A3970 | TT_Mile | OEM CONTRACT AWARD / BOP CONTRACT AWARD | 28/06/2021 | 28/06/2021 | 19/12/2016 | 19/12/2016 | 0 | TK_Complete
A3980 | TT_Mile | MAIN CIVIL WORKS CONTRACT AWARD | 28/06/2021 | 28/06/2021 | 29/05/2017 | 29/05/2017 | 0 | TK_Complete
A3990 | TT_Mile | SITE ESTABLISHMENT CONTRACT AWARD | 28/06/2021 | 28/06/2021 | 05/06/2017 | 05/06/2017 | 0 | TK_Complete
A4000 | TT_Mile | E&amp;M INSTALLATION CONTRACT AWARD | 28/06/2021 | 28/06/2021 | 22/09/2017 | 22/09/2017 | 0 | TK_Complete
A4130 | TT_Mile | START OF MAIN CIVIL WORKS ON SITE | 01/06/2021 | 01/06/2021 | 19/06/2017 | 19/06/2017 | 0 | TK_Complete
A4140 | TT_Mile | START OF E&amp;M WORKS ON SITE | 01/06/2021 | 01/06/2021 | 19/02/2018 | 19/02/2018 | 0 | TK_Complete
A4150 | TT_Mile | START OF COLD COMMISSIONING | 01/06/2021 | 01/06/2021 | 29/07/2019 | 29/07/2019 | 0 | TK_Complete
A4160 | TT_Mile | Back Energisation | 01/06/2021 | 01/06/2021 | 01/12/2019 | 01/12/2019 | 0 | TK_Complete
A4170 | TT_Mile | START CHEMICAL CLEANING | 01/06/2021 | 01/06/2021 | 14/12/2019 | 14/12/2019 | 0 | TK_Complete
A4180 | TT_Mile | FIRST FIRE | 01/06/2021 | 01/06/2021 | 24/01/2020 | 24/01/2020 | 0 | TK_Complete
A4190 | TT_Mile | START HOT COMMISSIONING (PART 1 - GAS) | 01/06/2021 | 01/06/2021 | 24/01/2020 | 24/01/2020 | 0 | TK_Complete
A4200 | TT_Mile | STEAM BLOW | 01/06/2021 | 01/06/2021 | 28/01/2020 | 28/01/2020 | 0 | TK_Complete
A4210 | TT_Mile | UNIT UNDER OPERATIONAL CONTROL | 01/06/2021 | 01/06/2021 | 28/09/2020 | 28/09/2020 | 0 | TK_Complete
A4220 | TT_Mile | PART 1 COMMISSIONING CLEARANCE CERTIFICATE (CCC) ISSUED: UNIT UNDER OPERATION) | 01/06/2021 | 01/06/2021 | 28/09/2020 | 28/09/2020 | 0 | TK_Complete
A4230 | TT_Mile | D1 OP PERMIT | 01/06/2021 | 01/06/2021 | 29/09/2020 | 29/09/2020 | 0 | TK_Complete
A4240 | TT_Mile | START OF TB2 OUTAGE RECTIFICATION WORKS (SIEMENS) | 01/06/2021 | 01/06/2021 | 22/02/2021 | 22/02/2021 | 0 | TK_Complete
A4250 | TT_Mile | START HOT COMMISSIONING (PART 2 - OIL) | 01/06/2021 | 01/06/2021 | 23/03/2021 | 23/03/2021 | 0 | TK_Complete
A4260 | TT_FinMile | COMPLETION OF ALL COMMISSIONING WORKS &amp; HANDOVER to OPERATIONS | 01/06/2021 | 01/06/2021 | 31/05/2021 | 31/05/2021 | 0 | TK_Complete
S1030 | TT_FinMile | Turbine Hall Over Head Crane Ready | 01/06/2021 | 01/06/2021 | 31/08/2018 | 31/08/2018 | 0 | TK_Complete
S1070 | TT_Mile | Start first Hydro Test | 01/06/2021 | 01/06/2021 | 13/05/2019 | 13/05/2019 | 0 | TK_Complete
S1080 | TT_Mile | Start Chemical Clean | 01/06/2021 | 01/06/2021 | 14/12/2019 | 14/12/2019 | 0 | TK_Complete
S1095 | TT_Mile | 400KV Commencement | 01/06/2021 | 01/06/2021 | 17/07/2017 | 17/07/2017 | 0 | TK_Complete
S1110 | TT_FinMile | Back Energisation | 01/06/2021 | 01/06/2021 | 01/12/2019 | 01/12/2019 | 0 | TK_Complete
S1130 | TT_Mile | First Fire | 02/06/2021 | 02/06/2021 | 24/01/2020 | 24/01/2020 | 0 | TK_Complete
A3400 | TT_FinMile | CP 1 Conceptual Study | 09/09/2020 | 09/09/2020 | 14/11/2014 | 14/11/2014 | 0 | TK_Complete
A3410 | TT_FinMile | Advance Notice Guide | 09/09/2020 | 09/09/2020 | 01/04/2015 | 01/04/2015 | 0 | TK_Complete
A3420 | TT_FinMile | CP2 Project Basis | 09/09/2020 | 09/09/2020 | 21/07/2016 | 21/07/2016 | 0 | TK_Complete
A3430 | TT_FinMile | CP3 Project Strategy | 09/09/2020 | 09/09/2020 | 21/07/2016 | 21/07/2016 | 0 | TK_Complete
A3440 | TT_FinMile | Final Investment Decision Guide | 09/09/2020 | 09/09/2020 | 27/07/2016 | 27/07/2016 | 0 | TK_Complete
A3450 | TT_FinMile | CP4 Design | 09/09/2020 | 09/09/2020 | 26/09/2016 | 26/09/2016 | 0 | TK_Complete
A3460 | TT_FinMile | Construction | 09/09/2020 | 09/09/2020 | 26/09/2016 | 26/09/2016 | 0 | TK_Complete
A3470 | TT_FinMile | CP Commissioning &amp; Start Up | 09/09/2020 | 09/09/2020 | 21/01/2020 | 21/01/2020 | 0 | TK_Complete
A3480 | TT_FinMile | Project Acceptance Gate | 09/09/2020 | 09/09/2020 | 31/05/2021 | 31/05/2021 | 0 | TK_Complete
A4010 | TT_Mile | Access to Site | 28/06/2021 | 28/06/2021 | 03/11/2016 | 03/11/2016 | 0 | TK_Complete
A4020 | TT_Mile | Pile Characteristics and Pile Load capacity supplien to OEM | 28/06/2021 | 28/06/2021 | 03/11/2016 | 03/11/2016 | 0 | TK_Complete
A4030 | TT_Mile | Raw Water Available | 28/06/2021 | 28/06/2021 | 26/07/2019 | 26/07/2019 | 0 | TK_Complete
A4040 | TT_Mile | Demineralized water available (For Construction) | 28/06/2021 | 28/06/2021 | 19/05/2019 | 19/05/2019 | 0 | TK_Complete
A4050 | TT_Mile | HV Grid Available | 29/06/2021 | 29/06/2021 | 08/01/2020 | 08/01/2020 | 0 | TK_Complete
A4060 | TT_FinMile | MV Available (Back Energizing) | 01/06/2021 | 01/06/2021 | 01/12/2019 | 01/12/2019 | 0 | TK_Complete
A4070 | TT_Mile | Fuel Gas Required | 29/06/2021 | 29/06/2021 | 08/01/2020 | 08/01/2020 | 0 | TK_Complete
A4080 | TT_Mile | Fuel Oil Required | 28/06/2021 | 28/06/2021 | 17/06/2020 | 17/06/2020 | 0 | TK_Complete
SS.3170 | TT_Task | Prepare Drainage Diversion Submission | 31/03/2016 | 27/04/2016 | 31/03/2016 | 23/04/2016 | 0 | TK_Complete
SS.3140 | TT_Task | Drainage Diversion 1st Submission | 01/06/2016 | 17/08/2016 | 26/05/2016 | 20/07/2016 | 0 | TK_Complete
SS.3200 | TT_Task | Drainage Diversion GBP | 15/09/2016 | 05/12/2016 | 15/09/2016 | 11/11/2016 | 0 | TK_Complete
SS.3210 | TT_Task | Drainage Diversion - Consent | 01/12/2016 | 09/01/2017 | 01/12/2016 | 28/12/2016 | 0 | TK_Complete
SS.3320 | TT_Task | Drainage Diversion Resubmission (Structural) | 15/09/2016 | 17/11/2016 | 15/09/2016 | 09/11/2016 | 0 | TK_Complete
SS.3340 | TT_Task | Drainage Diversion Resubmission (Drainage Plans) | 15/09/2016 | 17/11/2016 | 15/09/2016 | 09/11/2016 | 0 | TK_Complete
SS.3400 | TT_Task | Drainage Diversion 1st Amendment (Structural) | 19/05/2017 | 19/06/2017 | 19/05/2017 | 14/06/2017 | 0 | TK_Complete
SS.3420 | TT_Task | Drainage Diversion ELS 1st Submission | 18/01/2017 | 23/03/2017 | 18/01/2017 | 16/03/2017 | 0 | TK_Complete
SS.3430 | TT_Task | Drainage Diversion ELS 1st Amendment | 21/04/2017 | 23/05/2017 | 21/04/2017 | 19/05/2017 | 0 | TK_Complete
SS.3180 | TT_Task | Prepare warehouse demolition and A&amp;A works | 29/07/2015 | 03/11/2015 | 29/07/2015 | 02/11/2015 | 0 | TK_Complete
SS.3190 | TT_Task | Prepare warehouse demolition and A&amp;A works amendment | 04/07/2016 | 05/09/2016 | 02/07/2016 | 24/08/2016 | 0 | TK_Complete
SS.3000 | TT_Task | Warehouse demolition and A&amp;A works (GBP &amp; Structural) - 1st Submission | 03/11/2015 | 05/01/2016 | 03/11/2015 | 28/12/2015 | 0 | TK_Complete
SS.3060 | TT_Task | Warehouse demolition and A&amp;A works (GBP) - Amendment Submission | 01/09/2016 | 12/10/2016 | 25/08/2016 | 04/10/2016 | 0 | TK_Complete
SS.3061 | TT_Task | Warehouse demolition and A&amp;A works (Structural)- Amendment Submission | 01/09/2016 | 12/10/2016 | 05/04/2017 | 28/04/2017 | 0 | TK_Complete
SS.3070 | TT_Task | Warehouse demolition and A&amp;A works - Consent | 26/09/2016 | 03/11/2016 | 20/10/2016 | 21/11/2016 | 0 | TK_Complete
SS.3220 | TT_Task | Prepare Power Island Piling Submission | 01/12/2015 | 19/02/2016 | 01/12/2015 | 28/01/2016 | 0 | TK_Complete
SS.3010 | TT_Task | Power Island Piling - 1st Submission | 01/02/2016 | 18/04/2016 | 29/01/2016 | 24/03/2016 | 0 | TK_Complete
SS.3050 | TT_Task | Power Island Piling - Amendment | 09/08/2016 | 21/09/2016 | 09/08/2016 | 09/09/2016 | 0 | TK_Complete
SS.3080 | TT_Task | Power Island Piling - Consent | 12/09/2016 | 11/11/2016 | 09/09/2016 | 25/10/2016 | 0 | TK_Complete
SS.3110 | TT_Task | BA14 submission &amp; pile test | 25/05/2017 | 03/07/2017 | 25/05/2017 | 21/06/2017 | 0 | TK_Complete
SS.3120 | TT_Task | Piling 1st Submission | 29/01/2016 | 28/03/2016 | 29/01/2016 | 24/03/2016 | 0 | TK_Complete
SS.3130 | TT_Task | Piling 1st Amendment | 09/08/2016 | 15/09/2016 | 09/08/2016 | 09/09/2016 | 0 | TK_Complete
SS.3230 | TT_Task | Piling 2nd Amendment | 07/11/2016 | 07/12/2016 | 07/11/2016 | 02/12/2016 | 0 | TK_Complete
SS.3250 | TT_Task | Piling 3rd Amendment | 21/02/2017 | 24/03/2017 | 21/02/2017 | 21/03/2017 | 0 | TK_Complete
SS.3270 | TT_Task | Piling 4th Amendment | 21/03/2017 | 14/04/2017 | 21/03/2017 | 12/04/2017 | 0 | TK_Complete
SS.3300 | TT_Task | Piling 5th Amendment | 02/05/2017 | 22/05/2017 | 02/05/2017 | 19/05/2017 | 0 | TK_Complete
CS.1060 | TT_Task | Warehouse Demolition works | 01/06/2021 | 05/07/2021 | 16/12/2016 | 17/01/2017 | 0 | TK_Complete
CS.1070 | TT_Task | Warehouse A&amp;A Works, ready for main contract fitout (150 Days - 14/5/2017) | 01/06/2021 | 09/09/2021 | 18/01/2017 | 21/04/2017 | 0 | TK_Complete
A4090 | TT_Task | Turbine Hall (Driven Piles) | 01/06/2021 | 14/10/2021 | 20/12/2016 | 04/05/2017 | 0 | TK_Complete
A4095 | TT_Task | Site Drainage A&amp;A works &amp; Site Demob | 01/06/2021 | 07/06/2021 | 20/12/2016 | 30/09/2017 | 0 | TK_Complete
A4100 | TT_Task | Turbine Hall (Pre-Bore Socket H-Piles) | 01/06/2021 | 12/07/2021 | 20/12/2016 | 06/05/2017 | 0 | TK_Complete
A4110 | TT_Task | HRSG (Driven H-Piles) | 01/06/2021 | 09/07/2021 | 20/12/2016 | 04/05/2017 | 0 | TK_Complete
A4120 | TT_Task | Post Drilling / BD Selection / Load Tests / BD Consent for Pile Cap | 01/06/2021 | 23/07/2021 | 09/05/2017 | 30/06/2017 | 0 | TK_Complete
CS.1075 | TT_Task | Construct Trials &amp; Test for BD inspection and acknowledgement | 01/06/2021 | 18/06/2021 | 08/11/2016 | 23/11/2016 | 0 | TK_Complete
A3490 | TT_Task | Bulk excavation | 01/06/2021 | 05/07/2021 | 14/06/2017 | 19/07/2017 | 0 | TK_Complete
SI----2-005 | TT_Mile | PRE-NOTICE TO PROCEED (PNTP) | 03/11/2016 | 03/11/2016 | 03/11/2016 | 03/11/2016 | 0 | TK_Complete
SI----2-007 | TT_Mile | NOTICE TO PROCEED (NTP) | 14/01/2017 | 14/01/2017 | 19/12/2016 | 19/12/2016 | 0 | TK_Complete
SI----2C00 | TT_Mile | START ENGINEERING | 26/11/2016 | 26/11/2016 | 03/11/2016 | 03/11/2016 | 0 | TK_Complete
SI----2D00 | TT_Mile | START PRODUCTS (GT, ST, GENERATOR, CONDENSER) | 03/11/2016 | 03/11/2016 | 03/11/2016 | 03/11/2016 | 0 | TK_Complete
SI-3412-32 | TT_Mile | GENERAL LAYOUT ACCEPTED FROM CLIENT (AS BASIS OF CONTRACT SIGNING) | 03/11/2016 | 03/11/2016 | 03/11/2016 | 03/11/2016 | 0 | TK_Complete
SI-U--5-015 | TT_Mile | PILE CHARACTERISTICS AND PILE LOAD CAPACITY RELEASED BY CLP | 03/11/2016 | 03/11/2016 | 03/11/2016 | 03/11/2016 | 0 | TK_Complete
SI1---2-00 | TT_Mile | COMMENCEMENT OF AGREEMENT FOR ADVANCED ENGINEERING CONTRACT DATED 26-APR-2016 | 11/08/2019 | 11/08/2019 | 16/04/2016 | 16/04/2016 | 0 | TK_Complete
SI1---2-05 | TT_FinMile | (1a) COMPLETION AND SUBMISSION OF DATA FOR BD SUBMISSION | 11/08/2019 | 11/08/2019 | 18/06/2016 | 18/06/2016 | 0 | TK_Complete
SI1---2-10 | TT_FinMile | (1b) COMPLETION AND SUBMISSION OF ALL OTHER DATA IN ATTACHMENT 1B | 11/08/2019 | 11/08/2019 | 18/06/2016 | 18/06/2016 | 0 | TK_Complete
SI1---2-15 | TT_FinMile | (2) COMPLETION AND SUBMISSION OF ALL ENGINEERING FOR HRSG FOR BD SUBMISSION | 31/01/2017 | 31/01/2017 | 28/01/2017 | 28/01/2017 | 0 | TK_Complete
SI1---2-20 | TT_FinMile | (5a) COMPLETION OF INSURANCE CERTIFICATE / NOMINATION OF TFA ETC. | 31/05/2017 | 31/05/2017 | 03/05/2017 | 03/05/2017 | 0 | TK_Complete
SI1---2-25 | TT_FinMile | (5b) COMPLETION OF MOBILIZATION OF TFA FOR CIVIL WORKS | 25/11/2017 | 25/11/2017 | 30/10/2017 | 30/10/2017 | 0 | TK_Complete
SI1---2-30 | TT_FinMile | (6a) COMPLETION OF NOMINATION OF TFA / COMMISSIONING PROCEDURE AND ETC. | 11/08/2018 | 11/08/2018 | 11/08/2018 | 11/08/2018 | 0 | TK_Complete
SI1---2-35 | TT_FinMile | (6b) COMPLETION AND SIGN OFF OF ALL CHECK SHEET TO ALLOW 1ST FIRE | 16/03/2019 | 16/03/2019 | 23/01/2020 | 23/01/2020 | 0 | TK_Complete
SI1---3-00 | TT_FinMile | (3a) DELIVERY (ON-SITE) OF CAST-IN-PLACE EMBEDS FOR TURBINE TABLE AND TURBINE HALL | 25/08/2017 | 25/08/2017 | 20/07/2017 | 20/07/2017 | 0 | TK_Complete
SI1---3-05 | TT_FinMile | (3b) DELIVERY (ON-SITE) OF CAST-IN-PLACE EMBEDS FOR HRSG AND STACK | 25/09/2017 | 25/09/2017 | 28/08/2017 | 28/08/2017 | 0 | TK_Complete
SI1---3-10 | TT_FinMile | (3c) DELIVERY (ON-SITE) OF CAST-IN-PLACE EMBEDS FOR REMAINING PLANT | 26/02/2018 | 26/02/2018 | 26/01/2018 | 26/01/2018 | 0 | TK_Complete
SI1---3-15 | TT_FinMile | (4a) DELIVERY (ON-SITE) OF UMC CRANE / PRELIMINARY O&amp;M MANUAL AND HRSG STEEL / CASING | 26/02/2018 | 26/02/2018 | 01/01/2018 | 01/01/2018 | 0 | TK_Complete
SI1---3-20 | TT_FinMile | (4b1) DELIVERY (ON-SITE) OF STEAM TURBINE AND GENERATOR | 01/04/2018 | 01/04/2018 | 01/04/2018 | 01/04/2018 | 0 | TK_Complete
SI1---3-25 | TT_FinMile | (4c) DELIVERY (ON-SITE) OF GAS TURBINE AND CONDENSER | 01/04/2018 | 01/04/2018 | 01/04/2018 | 01/04/2018 | 0 | TK_Complete
SI1---3-30 | TT_FinMile | (4d) DELIVERY (ON-SITE) OF HRSG PIPING AND BALANCE OF HRSG EQUIPMENT | 30/07/2018 | 30/07/2018 | 18/08/2018 | 18/08/2018 | 0 | TK_Complete
SI1---3-35 | TT_FinMile | (4e) DELIVERY (ON-SITE) OF BALANCE OF ALL SIEMENS SUPPLIED EQUIPMENT | 01/12/2018 | 01/12/2018 | 01/12/2018 | 01/12/2018 | 0 | TK_Complete
SI1---3-37 | TT_FinMile | (4b2) DELIVERY (ON-SITE) OF HRSG MODULES / DRUMS | 21/04/2018 | 21/04/2018 | 08/04/2018 | 08/04/2018 | 0 | TK_Complete
SI1---3-39 | TT_FinMile | (BOP2) FUEL GAS SUPPLY PIPEWORK SYSTEM | 08/06/2018 | 08/06/2018 | 08/06/2018 | 08/06/2018 | 0 | TK_Complete
SI1---3-43 | TT_FinMile | (BOP3) 6.6kV CONNECTION &amp; HYDROGEN / CO2 / SUPPLY PIPEWORK &amp; FUEL OIL FORWARDING SYSTEM | 05/08/2018 | 05/08/2018 | 05/08/2018 | 05/08/2018 | 0 | TK_Complete
SI1---3-47 | TT_FinMile | (BOP1) FIRE FIGHTING CONNECTION PIPEWORK SYSTEM | 26/03/2018 | 26/03/2018 | 28/02/2018 | 28/02/2018 | 0 | TK_Complete
SI1---3-49 | TT_FinMile | (BOP4) DELIVERY OF ALL BALANCE EQUIPMENT FOR CONNECTION WORKS | 09/09/2018 | 09/09/2018 | 25/10/2018 | 25/10/2018 | 0 | TK_Complete
SI1---3-51 | TT_FinMile | (BOP5) COMPLETION AND SIGN OFF OF ALL CHECK SHEET TO ALLOW 1ST FIRE | 16/03/2019 | 16/03/2019 | 23/01/2020 | 23/01/2020 | 0 | TK_Complete
SI-HA-2-85&amp; | TT_Mile | PARTIAL ORDER PLACED HRSG | 03/11/2016 | 03/11/2016 | 03/11/2016 | 03/11/2016 | 0 | TK_Complete
SI-HA-2-87&amp; | TT_Mile | ORDER PLACED HRSG | 14/01/2017 | 14/01/2017 | 19/12/2016 | 19/12/2016 | 0 | TK_Complete
SI-1102-15 | TT_FinMile | PRELIMINARY OPERATING AND MAINTENANCE DOCUMENTATION (O&amp;M) | 07/12/2018 | 07/12/2018 | 07/12/2018 | 07/12/2018 | 0 | TK_Complete
SI-3512-40 | TT_FinMile | STEAM BLOWING INSTRUCTION | 09/02/2019 | 09/02/2019 | 31/10/2019 | 31/10/2019 | 0 | TK_Complete
SI-3512E40 | TT_FinMile | COMMISSIONING MANUAL (TC) ON SITE/ CLIENT | 28/10/2018 | 28/10/2018 | 30/09/2018 | 30/09/2018 | 0 | TK_Complete
SI-MAV2-01 | TT_FinMile | CLEANING INSTRUCTION TURBOSET LUBE AND LIFTING OIL SYSTEM | 06/09/2018 | 06/09/2018 | 06/09/2018 | 06/09/2018 | 0 | TK_Complete
SI-M--2C20 | TT_FinMile | LAYOUT DOCUMENTS [external interfaces final] | 01/04/2017 | 01/04/2017 | 31/03/2017 | 31/03/2017 | 0 | TK_Complete
SI-MB-2-20 | TT_FinMile | LAYOUT DOCUMENTS AIR INTAKE, EXHAUST GAS SYSTEM [external interfaces final] | 31/03/2017 | 31/03/2017 | 31/03/2017 | 31/03/2017 | 0 | TK_Complete
SI-M--2D20 | TT_FinMile | SYSTEM DOCUMENTS [external interfaces final] | 31/03/2017 | 31/03/2017 | 31/03/2017 | 31/03/2017 | 0 | TK_Complete
SI-3412-50 | TT_Task | SEISMIC REPORT | 09/07/2016 | 04/08/2016 | 09/07/2016 | 05/08/2016 | 0 | TK_Complete
SI-3022-39 | TT_Task | GENERAL DESIGN CRITERIA (SIEMENS SCOPE ONLY) | 03/11/2016 | 14/12/2016 | 03/11/2016 | 14/12/2016 | 0 | TK_Complete
SI-SG-2-26 | TT_FinMile | DESIGN REVIEW - EXPLOSION PROTECTION (ATEX / IEC60079) | 31/03/2017 | 31/03/2017 | 20/03/2017 | 20/03/2017 | 0 | TK_Complete
SI-SG-2-35 | TT_Task | PREPARATION FINAL FIRE- / EXPLOSION PROT. CONCEPT AND ESCAPE ROUTE/FIRE PROTECTION DWGs | 14/02/2017 | 13/03/2017 | 01/02/2017 | 08/03/2017 | 0 | TK_Complete
SI-SG-2-50 | TT_FinMile | FINAL ESCAPE ROUTE AND FIRE PROTECTION DWGS AVAILABLE | 18/03/2017 | 18/03/2017 | 08/03/2017 | 08/03/2017 | 0 | TK_Complete
SI-3412-40 | TT_Task | NOISE PROTECTION CONCEPT | 01/10/2016 | 05/04/2017 | 11/06/2016 | 26/12/2016 | 0 | TK_Complete
SI-U--2B10 | TT_Mile | RFQ STEEL WORKS (excl.EMBEDDED PARTS) | 14/02/2017 | 14/02/2017 | 18/01/2017 | 18/01/2017 | 0 | TK_Complete
SI-U--2B85 | TT_Mile | ORDER PLACED STEEL WORKS (excl.EMBEDDED PARTS) | 18/05/2017 | 18/05/2017 | 24/04/2017 | 24/04/2017 | 0 | TK_Complete
SI-U--2B87 | TT_Task | QUOTATION STAGE STEEL WORKS (excl.EMBEDDED PARTS) | 14/02/2017 | 12/04/2017 | 18/01/2017 | 23/04/2017 | 0 | TK_Complete
CP-3412-35 | TT_Task | REVIEW BY CLIENT FOR CONCEPT DESIGN DOCUMENTS | 01/03/2017 | 21/03/2017 | 28/02/2017 | 20/03/2017 | 0 | TK_Complete
SI-3412-07 | TT_FinMile | PRELIMINARY EXTERNAL WORKS DESIGN AVAILABLE | 28/10/2016 | 28/10/2016 | 16/09/2016 | 16/09/2016 | 0 | TK_Complete
SI-3412A00 | TT_Task | CONCEPT DESIGN (part I) PLOT PLAN | 01/10/2016 | 27/10/2016 | 20/08/2016 | 16/09/2016 | 0 | TK_Complete
SI-3412D30 | TT_FinMile | FINAL HYDRAULIC DESIGN AVAILABLE | 30/04/2017 | 30/04/2017 | 28/04/2017 | 28/04/2017 | 0 | TK_Complete
SI-3022-05 | TT_FinMile | GENERAL DESIGN CRITERIA FOR STRUCTURAL ENGINEERING FINALISED FOR HRSG ORDER (Phase 1) | 01/10/2016 | 01/10/2016 | 05/08/2016 | 05/08/2016 | 0 | TK_Complete
SI-3412-09 | TT_FinMile | FINAL AND COMPLETE ROOM NUMBERS ASSIGNED TO EQUIPMENT | 25/07/2017 | 25/07/2017 | 25/06/2017 | 25/06/2017 | 0 | TK_Complete
SI-3412-11 | TT_FinMile | LIST OF ALL ROOM NUMBERS AVAILABLE | 23/03/2017 | 23/03/2017 | 08/03/2017 | 08/03/2017 | 0 | TK_Complete
SI-3412-20 | TT_FinMile | (C) BASIC DESIGN PLANT LAYOUT DWGS AVAILABLE FOR UMC BUILDING | 21/02/2017 | 21/02/2017 | 16/01/2017 | 16/01/2017 | 0 | TK_Complete
SI-3412A15 | TT_Task | BASIC DESIGN PLANT LAYOUT | 19/01/2017 | 11/03/2017 | 15/12/2016 | 08/03/2017 | 0 | TK_Complete
SI---P2J75 | TT_Task | PREPARATION RFQ PREFAB. MODULES | 26/11/2016 | 04/03/2017 | 03/11/2016 | 28/02/2017 | 0 | TK_Complete
SI---P2J80 | TT_Task | QUOTATION STAGE PREFAB. MODULES | 16/03/2017 | 18/05/2017 | 01/03/2017 | 30/04/2017 | 0 | TK_Complete
SI---P2J85 | TT_Mile | ORDER PLACED PREFAB. MODULES | 01/06/2017 | 01/06/2017 | 30/04/2017 | 30/04/2017 | 0 | TK_Complete
SI-GM-3B25 | TT_Task | DETAIL DESIGN, MANUFACTURING, SHOP TEST SUMP PUMP GM/UGU | 26/11/2017 | 25/04/2018 | 26/10/2017 | 05/10/2018 | 0 | TK_Complete
SI-GM-3B80 | TT_FinMile | (RFS) READY FOR SHIPMENT SUMP PUMP GM/UGU | 15/06/2018 | 15/06/2018 | 12/10/2018 | 12/10/2018 | 0 | TK_Complete
SI-GM-4B25 | TT_Task | TRANSPORT SUMP PUMP GM/UGU | 16/06/2018 | 14/08/2018 | 21/11/2018 | 25/11/2018 | 0 | TK_Complete
SI-GM-4B27 | TT_FinMile | (OTD-OS) ON SITE SUMP PUMP GM/UGU | 14/08/2018 | 14/08/2018 | 25/11/2018 | 25/11/2018 | 0 | TK_Complete
SI-SGA3A25 | TT_Task | DETAIL DESIGN, MANUFACTURING, SHOP TEST FIRE FIGHTING RING MAIN SGA | 30/08/2017 | 27/12/2017 | 18/08/2017 | 15/11/2018 | 0 | TK_Complete
SI-SGA3A80 | TT_FinMile | (RFS) READY FOR SHIPMENT FIRE FIGHTING RING MAIN SGA | 29/05/2018 | 29/05/2018 | 20/11/2018 | 20/11/2018 | 0 | TK_Complete
SI-SGA4A40 | TT_FinMile | (OTD-OS) ON SITE FIRE FIGHTING RING MAIN SGA | 24/07/2018 | 24/07/2018 | 29/11/2018 | 29/11/2018 | 0 | TK_Complete
SI-SGA4A42 | TT_Task | TRANSPORT FIRE FIGHTING RING MAIN SGA | 30/05/2018 | 24/07/2018 | 21/11/2018 | 29/11/2018 | 0 | TK_Complete
SI-3062-17 | TT_FinMile | FINAL EL.SPECS. (BLACK BOXES, MOTORS) | 13/01/2017 | 13/01/2017 | 14/12/2016 | 14/12/2016 | 0 | TK_Complete
SI-B--2A50 | TT_FinMile | (ELV2) PRELIMINARY EL. LOAD DATA FOR LV | 28/02/2017 | 28/02/2017 | 17/02/2017 | 17/02/2017 | 0 | TK_Complete
SI-B--2A55 | TT_FinMile | (ELV3) FINAL EL. LOAD DATA FOR LV | 25/06/2017 | 25/06/2017 | 12/06/2017 | 12/06/2017 | 0 | TK_Complete
SI-BF-2-55 | TT_FinMile | LV- SWITCHGEAR DATA FINAL | 27/10/2017 | 27/10/2017 | 27/09/2017 | 27/09/2017 | 0 | TK_Complete
SP-B--2-56 | TT_Mile | CONSUMER LIST (VEL) COMPLETED (FINAL) | 01/04/2017 | 01/04/2017 | 23/03/2017 | 23/03/2017 | 0 | TK_Complete
SP-B--2-58 | TT_Mile | E-CONSUMER LIST WITH MOUNTING LOCATION GT TO GT I&amp;C (VEL) | 25/07/2017 | 25/07/2017 | 11/07/2017 | 11/07/2017 | 0 | TK_Complete
SI-B--2-13 | TT_Task | PREPARATION OF LENGTH MATRIX | 11/04/2017 | 24/04/2017 | 28/03/2017 | 10/04/2017 | 0 | TK_Complete
SI-B--2-14 | TT_FinMile | 1ST. ROOM TO ROOM MATRIX | 10/04/2017 | 10/04/2017 | 27/03/2017 | 27/03/2017 | 0 | TK_Complete
SI-B--2-15 | TT_Task | DESIGN POWER / CONTROL CABLES | 11/05/2017 | 27/10/2017 | 11/04/2017 | 27/09/2017 | 0 | TK_Complete
SI-B--2-19 | TT_FinMile | 1ST. LENGTH MATRIX AVAILABLE | 10/05/2017 | 10/05/2017 | 10/04/2017 | 10/04/2017 | 0 | TK_Complete
SI-B--2-30 | TT_Task | DETAIL DESIGN CABLE ROUTING | 26/06/2017 | 03/01/2018 | 13/06/2017 | 21/12/2017 | 0 | TK_Complete
SI-B--2-54 | TT_FinMile | BINDING ELECTRICAL AND I&amp;C CABLE LIST DATA AVAILABLE | 16/12/2017 | 16/12/2017 | 27/11/2017 | 27/11/2017 | 0 | TK_Complete
SI-B--4-54 | TT_FinMile | CABLE PULLING DATA TRANSFER TO SITE | 30/04/2018 | 30/04/2018 | 29/06/2018 | 29/06/2018 | 0 | TK_Complete
SI-BZK3-25 | TT_Task | MANUFACTURING, SHOP TEST MV/LV CABLES BZK (1ST SET 30%) | 26/08/2017 | 09/02/2018 | 25/08/2017 | 06/03/2018 | 0 | TK_Complete
SI-BZK3-80 | TT_FinMile | (RFS) READY FOR SHIPMENT MV/LV CABLES BZK (1ST SET 30%) | 28/03/2018 | 28/03/2018 | 28/03/2018 | 28/03/2018 | 0 | TK_Complete
SI-BZK3-90 | TT_Task | MANUFACTURING, SHOP TEST MV/LV CABLES BZK (2ND SET 80%) | 29/03/2018 | 27/05/2018 | 15/05/2018 | 10/07/2018 | 0 | TK_Complete
SI-BZK3-92 | TT_FinMile | (RFS) READY FOR SHIPMENT MV/LV CABLES BZK (2ND SET 80%) | 27/05/2018 | 27/05/2018 | 10/07/2018 | 10/07/2018 | 0 | TK_Complete
SI-BZK4-64 | TT_Task | TRANSPORT MV/LV CABLES BZK (1ST SET 30%) | 29/03/2018 | 27/04/2018 | 14/04/2018 | 24/04/2018 | 0 | TK_Complete
SI-BZK4-66 | TT_Task | TRANSPORT MV/LV CABLES BZK (2ND SET 80%) | 28/05/2018 | 15/07/2018 | 21/07/2018 | 26/07/2018 | 0 | TK_Complete
SI-BZP3-25 | TT_Task | MANUFACTURING, SHOP TEST FIRST CABLE SUPPORT SYSTEM BZP (FOR PRE-FAB MODULES) | 26/06/2017 | 18/08/2017 | 02/06/2017 | 01/09/2017 | 0 | TK_Complete
SI-BZP3-80 | TT_FinMile | (RFS) READY FOR SHIPMENT CABLE SUPPORT SYSTEM BZP (FOR PRE-FAB MODULES) | 02/10/2017 | 02/10/2017 | 01/09/2017 | 01/09/2017 | 0 | TK_Complete
SI-BZP3-82 | TT_Task | MANUFACTURING, SHOP TEST CABLE SUPPORT SYSTEM BZP (MAIN) | 16/10/2017 | 10/12/2017 | 15/09/2017 | 08/03/2018 | 0 | TK_Complete
SI-BZP3-84 | TT_FinMile | (RFS) READY FOR SHIPMENT FIRST CABLE SUPPORT SYSTEM BZP (MAIN) | 08/04/2018 | 08/04/2018 | 08/04/2018 | 08/04/2018 | 0 | TK_Complete
SI-BZP3B25 | TT_Task | MANUFACTURING, SHOP TEST CABLE SUPPORT SYSTEM BZP (BOP) | 26/11/2017 | 20/01/2018 | 17/11/2017 | 31/05/2018 | 0 | TK_Complete
SI-BZP3B80 | TT_FinMile | (RFS) READY FOR SHIPMENT CABLE SUPPORT SYSTEM BZP (BOP) | 23/04/2018 | 23/04/2018 | 31/05/2018 | 31/05/2018 | 0 | TK_Complete
SI-BZP4-29 | TT_Task | TRANSPORT FIRST CABLE SUPPORT SYSTEM BZP (MAIN) | 09/04/2018 | 07/06/2018 | 09/04/2018 | 21/04/2018 | 0 | TK_Complete
SI-BZP4-31 | TT_Task | TRANSPORT FIRST CABLE SUPPORT SYSTEM BZP (FOR PRE-FAB MODULES) | 26/10/2017 | 12/12/2017 | 29/09/2017 | 29/12/2017 | 0 | TK_Complete
SI-BZP4B27 | TT_Task | TRANSPORT SECOND CABLE SUPPORT SYSTEM BZP (BOP) | 24/04/2018 | 22/06/2018 | 01/06/2018 | 20/06/2018 | 0 | TK_Complete
SI-CYA3-25 | TT_Task | MANUFACTURING, SHOP TEST TELECOMMUNICATION CYA | 26/10/2017 | 09/02/2018 | 29/09/2017 | 25/06/2018 | 0 | TK_Complete
SI-CYA3-80 | TT_FinMile | (RFS) READY FOR SHIPMENT TELECOMMUNICATION CYA | 14/05/2018 | 14/05/2018 | 28/06/2018 | 28/06/2018 | 0 | TK_Complete
SI-CYA4-27 | TT_Task | TRANSPORT TELECOMMUNICATION CYA | 15/05/2018 | 06/07/2018 | 29/06/2018 | 13/07/2018 | 0 | TK_Complete
SI-CYP3-25 | TT_Task | MANUFACTURING, SHOP TEST SECURITY CYP | 26/10/2017 | 09/02/2018 | 29/09/2017 | 25/06/2018 | 0 | TK_Complete
SI-CYP3-80 | TT_FinMile | (RFS) READY FOR SHIPMENT SECURITY CYP | 14/05/2018 | 14/05/2018 | 28/06/2018 | 28/06/2018 | 0 | TK_Complete
SI-CYP4-27 | TT_Task | TRANSPORT SECURITY CYP | 15/05/2018 | 06/07/2018 | 29/06/2018 | 13/07/2018 | 0 | TK_Complete
SI1C--4-27 | TT_Task | ST I&amp;C TRANSPORT TO SITE FIELD INSTRUMENTATION | 26/03/2018 | 24/05/2018 | 16/03/2018 | 13/05/2018 | 0 | TK_Complete
SI-HA-2-10 | TT_Task | ENGINEERING P&amp;IDs, SYSTEM DESCRIPTION HRSG-SYSTEMS | 14/01/2017 | 20/01/2017 | 10/12/2016 | 16/12/2016 | 0 | TK_Complete
SI-HA-2-11 | TT_FinMile | P&amp;IDs, DATA SHEETS, LIFE TIME DESIGN CRITERIA FOR INQUIRY AND ORDERING HRSG AVAILABLE | 30/09/2016 | 30/09/2016 | 08/07/2016 | 08/07/2016 | 0 | TK_Complete
SI-HA-2-59 | TT_Task | DESIGN REVIEW INCL. SIL-STUDY HRSG-SYSTEMS | 21/01/2017 | 24/02/2017 | 17/12/2016 | 31/03/2017 | 0 | TK_Complete
SI-HA-2-65 | TT_FinMile | (DF) PROCESS FINAL HRSG-SYSTEMS | 31/03/2017 | 31/03/2017 | 31/03/2017 | 31/03/2017 | 0 | TK_Complete
SI-HA-2-68&amp; | TT_FinMile | DATA INPUT HRSG COMPLETED FOR I&amp;C DESIGN | 26/01/2018 | 26/01/2018 | 08/02/2017 | 08/02/2017 | 0 | TK_Complete
SI-HA-2-75 | TT_Task | PREPARING DOCUMENTS INQUIRY/ CONTRACT ODER FOR HRSG | 01/10/2016 | 10/11/2016 | 11/06/2016 | 22/07/2016 | 0 | TK_Complete
SI-HA-2-86 | TT_Task | SYSTEM MEETINGS WITH HRSG SUPPLIERS | 03/11/2016 | 15/12/2016 | 03/11/2016 | 15/12/2016 | 0 | TK_Complete
SI-L--2-05 | TT_Task | PREPARATION P&amp;IDs L- SYSTEMS (FIRST ISSUE) | 10/12/2016 | 21/01/2017 | 17/11/2016 | 28/12/2016 | 0 | TK_Complete
SI-L--2-10 | TT_Task | ENGINEERING P&amp;IDs, SYSTEM DESCRIPTION L- SYSTEMS | 03/02/2017 | 23/03/2017 | 29/12/2016 | 15/02/2017 | 0 | TK_Complete
SI-L--2-25 | TT_Task | DESIGN REVIEW INTERFACE ST / L- SYSTEMS | 14/01/2017 | 03/02/2017 | 13/01/2017 | 15/02/2017 | 0 | TK_Complete
SI-L--2-30 | TT_Task | REVISION P&amp;IDs AFTER 3D DRV L- SYSTEMS | 08/09/2017 | 05/10/2017 | 07/08/2017 | 09/09/2017 | 0 | TK_Complete
SI-L--2-35 | TT_Task | DESIGN DATA SHEETS L- COMPONENTS | 26/11/2016 | 11/03/2017 | 03/11/2016 | 16/02/2017 | 0 | TK_Complete
SI-L--2-45 | TT_FinMile | DESIGN DATA SHEETS FOR ALL L- COMPONENTS AVAILABLE | 28/02/2017 | 28/02/2017 | 16/02/2017 | 16/02/2017 | 0 | TK_Complete
SI-L--2-50 | TT_FinMile | (DF) MECHANICAL ENGINEERING, PLANT LAYOUT L- SYSTEMS | 10/10/2017 | 10/10/2017 | 09/09/2017 | 09/09/2017 | 0 | TK_Complete
SI-L--2-65 | TT_FinMile | (DF) PROCESS FINAL L- SYSTEMS | 08/04/2017 | 08/04/2017 | 10/03/2017 | 10/03/2017 | 0 | TK_Complete
SI-L--2-70 | TT_FinMile | (DF) I&amp;C DATA L- SYSTEMS | 08/10/2017 | 08/10/2017 | 07/09/2017 | 07/09/2017 | 0 | TK_Complete
SI-L--2-75 | TT_Task | DESIGN REVIEW INCL. SIL-STUDY L- SYSTEMS | 01/03/2017 | 04/04/2017 | 17/02/2017 | 10/03/2017 | 0 | TK_Complete
SI-L--2I45 | TT_FinMile | DESIGN DATA SHEETS SAFETY, CONTROL VALVES L- SYSTEMS | 10/05/2017 | 10/05/2017 | 09/04/2017 | 09/04/2017 | 0 | TK_Complete
SI-P--2-05 | TT_Task | PREPARATION P&amp;IDs P-SYSTEMS (FIRST ISSUE) | 10/12/2016 | 21/01/2017 | 17/11/2016 | 29/12/2016 | 0 | TK_Complete
SI-P--2-10 | TT_Task | ENGINEERING P&amp;IDs, SYSTEM DESCRIPTION P-SYSTEMS | 14/01/2017 | 03/03/2017 | 30/12/2016 | 16/02/2017 | 0 | TK_Complete
SI-P--2-28 | TT_Task | SUMMARY DATA MANAGEMENT P-SYSTEMS | 01/04/2017 | 12/08/2017 | 11/03/2017 | 29/07/2017 | 0 | TK_Complete
SI-P--2-30 | TT_Task | REVISION P&amp;IDs AFTER 3D DRV P-SYSTEM | 26/09/2017 | 23/10/2017 | 05/09/2017 | 29/09/2017 | 0 | TK_Complete
SI-P--2-35 | TT_Task | DESIGN DATA SHEETS P-COMPONENTS | 26/11/2016 | 25/02/2017 | 03/11/2016 | 15/02/2017 | 0 | TK_Complete
SI-P--2-45 | TT_FinMile | DESIGN DATA SHEETS FOR ALL P-COMPONENTS AVAILABLE | 28/02/2017 | 28/02/2017 | 15/02/2017 | 15/02/2017 | 0 | TK_Complete
SI-P--2-50 | TT_FinMile | (DF) MECHANICAL ENGINEERING, PLANT LAYOUT P-SYSTEMS | 01/11/2017 | 01/11/2017 | 29/09/2017 | 29/09/2017 | 0 | TK_Complete
SI-P--2-65 | TT_FinMile | (DF) PROCESS FINAL P-SYSTEMS | 08/04/2017 | 08/04/2017 | 10/03/2017 | 10/03/2017 | 0 | TK_Complete
SI-P--2-70 | TT_FinMile | (DF) I&amp;C DATA P-SYSTEMS | 25/09/2017 | 25/09/2017 | 25/08/2017 | 25/08/2017 | 0 | TK_Complete
SI-P--2-75 | TT_Task | DESIGN REVIEW INCL. SIL-STUDY P-SYSTEMS | 01/03/2017 | 04/04/2017 | 17/02/2017 | 10/03/2017 | 0 | TK_Complete
SI-P--2I45 | TT_FinMile | DESIGN DATA SHEETS SAFETY, CONTROL VALVES P-SYSTEMS | 28/02/2017 | 28/02/2017 | 15/02/2017 | 15/02/2017 | 0 | TK_Complete
SI-PAC2B45 | TT_FinMile | DESIGN DATA SHEETS FOR CW PUMP PAC | 13/01/2017 | 13/01/2017 | 15/12/2016 | 15/12/2016 | 0 | TK_Complete
SI-G--2-05 | TT_Task | PREPARATION P&amp;IDs GA-/GHC/GM-/MBU20 - SYSTEMS (FIRST ISSUE) AND WATER BALANCE | 10/12/2016 | 21/01/2017 | 17/11/2016 | 26/12/2016 | 0 | TK_Complete
SI-G--2-10 | TT_Task | ENGINEERING P&amp;IDs, SYSTEM DESCRIPTION G-/S-/MBU20 - SYSTEMS | 03/02/2017 | 20/04/2017 | 27/12/2016 | 13/03/2017 | 0 | TK_Complete
SI-G--2-30 | TT_Task | REVISION P&amp;IDs AFTER 3D DRV G-/S-/MBU20 | 27/10/2017 | 09/11/2017 | 27/09/2017 | 12/10/2017 | 0 | TK_Complete
SI-G--2-35 | TT_Task | DESIGN DATA SHEETS G-/MBU20 - COMPONENTS | 03/11/2016 | 09/02/2017 | 03/11/2016 | 09/02/2017 | 0 | TK_Complete
SI-G--2-50 | TT_FinMile | (DF) MECHANICAL ENGINEERING, PLANT LAYOUT G-/S-/MBU20-SYSTEMS | 09/11/2017 | 09/11/2017 | 12/10/2017 | 12/10/2017 | 0 | TK_Complete
SI-G--2-65 | TT_FinMile | (DF) PROCESS FINAL G-/S-/MBU20 -SYSTEM | 30/04/2017 | 30/04/2017 | 24/04/2017 | 24/04/2017 | 0 | TK_Complete
SI-G--2-70 | TT_FinMile | (DF) I&amp;C DATA G/-S-/MBU20-SYSTEMS | 08/10/2017 | 08/10/2017 | 07/09/2017 | 07/09/2017 | 0 | TK_Complete
SI-G--2-75 | TT_Task | DESIGN REVIEW INCL. SIL-STUDY G-/S-/MBU20-SYSTEMS | 16/03/2017 | 26/04/2017 | 14/03/2017 | 24/04/2017 | 0 | TK_Complete
SI-G--2A05 | TT_Task | PREPARATION P&amp;IDs GHD/GKB/SCB - SYSTEMS (FIRST ISSUE) | 10/12/2016 | 18/02/2017 | 17/11/2016 | 09/01/2017 | 0 | TK_Complete
SI-G--2A45 | TT_FinMile | DESIGN DATA SHEETS FOR ALL G-/MBU20 - COMPONENTS AVAILABLE | 14/02/2017 | 14/02/2017 | 09/02/2017 | 09/02/2017 | 0 | TK_Complete
SI-G--2B45 | TT_FinMile | DESIGN DATA SHEETS SAFETY, CONTROL VALVES G-, MBU2-SYSTEMS | 14/02/2017 | 14/02/2017 | 09/02/2017 | 09/02/2017 | 0 | TK_Complete
SI-C--2-15 | TT_Task | BASIC DESIGN, SPECIFICATION BOP I&amp;C | 03/11/2016 | 18/01/2017 | 03/11/2016 | 18/01/2017 | 0 | TK_Complete
SI-C--2-50 | TT_FinMile | (ICSY2) PRELIMINARY FUNCTION DESCRIPTIONS, LOGICS AND HMI GRAPHICS | 28/08/2017 | 28/08/2017 | 27/07/2017 | 27/07/2017 | 0 | TK_Complete
SI-C--2A40 | TT_Task | HW ENGINEERING BOP I&amp;C | 15/02/2017 | 26/09/2017 | 02/02/2017 | 13/09/2017 | 0 | TK_Complete
SI-C--2A70 | TT_FinMile | (DF) BOP I&amp;C HW FOR FIELD EQUIPMENT AND CABINETS | 25/09/2017 | 25/09/2017 | 13/09/2017 | 13/09/2017 | 0 | TK_Complete
SI-C--2B00 | TT_Mile | SETUP T3000 DB | 01/05/2017 | 01/05/2017 | 07/04/2017 | 07/04/2017 | 0 | TK_Complete
SI-C--2B35 | TT_Task | SW ENGINEERING BOP I&amp;C, T3000 DB MERGING | 01/05/2017 | 19/11/2017 | 07/04/2017 | 24/01/2018 | 0 | TK_Complete
SI-C--2B40 | TT_FinMile | (DF) T3000 DB | 25/02/2018 | 25/02/2018 | 24/01/2018 | 24/01/2018 | 0 | TK_Complete
SI-C--2B41 | TT_Task | SW ENGINEERING BOP I&amp;C, T3000 DB MERGING, PROXIE GENERATION | 26/01/2018 | 08/03/2018 | 25/01/2018 | 24/03/2018 | 0 | TK_Complete
SI-C--2B70 | TT_FinMile | HANDOVER T3000 DB FOR TEST | 26/03/2018 | 26/03/2018 | 24/03/2018 | 24/03/2018 | 0 | TK_Complete
SI-C--2C50 | TT_FinMile | (ICBB2) PRELIMINARY MEASUREMENT LIST, SIGNAL LIST AND BB INTERFACE SHEETS | 15/03/2017 | 15/03/2017 | 01/03/2017 | 01/03/2017 | 0 | TK_Complete
SI-C--2C55 | TT_FinMile | (ICBB3) FINAL MEASUREMENT LIST, SIGNAL LIST AND BB INTERFACE SHEETS | 25/08/2017 | 25/08/2017 | 29/07/2017 | 29/07/2017 | 0 | TK_Complete
SI-CJJ2-38 | TT_FinMile | ST INPUT FOR I&amp;C UNIT COORDINATION | 25/08/2017 | 25/08/2017 | 02/08/2017 | 02/08/2017 | 0 | TK_Complete
SI-CJP2-38 | TT_FinMile | GT INPUT FOR I&amp;C UNIT COORDINATION | 25/08/2017 | 25/08/2017 | 17/08/2017 | 17/08/2017 | 0 | TK_Complete
SI-C--2-55 | TT_FinMile | (ICSY3) FINAL LOGICS AND HMI GRAPHICS | 22/10/2017 | 22/10/2017 | 22/09/2017 | 22/09/2017 | 0 | TK_Complete
SI1CJ-2-50 | TT_FinMile | (DF) BOP I&amp;C HARDWARE FOR PLANT SHOP TEST AND I&amp;C FOR UQA ELEC. ROOM | 26/09/2017 | 26/09/2017 | 08/09/2017 | 08/09/2017 | 0 | TK_Complete
SI1CJ-3-20 | TT_Task | DETAIL DESIGN HW ENGINEERING BOP I&amp;C CABINETS FOR PLANT SHOP TEST AND I&amp;C FOR UQA ELEC. ROOM | 21/06/2017 | 26/09/2017 | 21/05/2017 | 26/08/2017 | 0 | TK_Complete
SI1CJ-3-25 | TT_Task | MANUFACTURING BOP I&amp;C CABINETS FOR PLANT SHOP TEST AND I&amp;C FOR UQA ELEC. ROOM | 27/09/2017 | 26/12/2017 | 14/09/2017 | 25/12/2017 | 0 | TK_Complete
SI1CJ-3-80 | TT_FinMile | (RFS) READY FOR SHIPMENT BOP I&amp;C CABINETS FOR PLANT SHOP TEST AND I&amp;C FOR UQA ELEC. ROOM | 18/02/2018 | 18/02/2018 | 08/01/2018 | 08/01/2018 | 0 | TK_Complete
SI1CJ-4-25 | TT_Task | TRANSPORT TO WORKSHOP BOP I&amp;C CABINETS FOR PLANT SHOP TEST AND I&amp;C FOR UQA ELEC. ROOM | 19/02/2018 | 04/03/2018 | 09/01/2018 | 22/01/2018 | 0 | TK_Complete
SI-C--3-80 | TT_FinMile | (RFS) READY FOR SHIPMENT BOP I&amp;C FIELD CABINETS | 19/06/2018 | 19/06/2018 | 06/07/2018 | 06/07/2018 | 0 | TK_Complete
SI-C--3B25 | TT_Task | DETAIL DESIGN, MANUFACTURING, SHOP TEST FOR BOP I&amp;C FIELD DEVICES AND ERECTION MATERIAL | 26/08/2017 | 02/03/2018 | 29/07/2017 | 06/07/2018 | 0 | TK_Complete
SI-C--3B80 | TT_FinMile | (RFS) READY FOR SHIPMENT BOP I&amp;C FIELD DEVICES AND ERECTION MATERIAL | 19/06/2018 | 19/06/2018 | 25/07/2018 | 25/07/2018 | 0 | TK_Complete
SI-C--4B25 | TT_Task | TRANSPORT TO SITE BOP I&amp;C FIELD DEVICES AND ERECTION MATERIAL | 20/06/2018 | 18/08/2018 | 25/07/2018 | 25/08/2018 | 0 | TK_Complete
SI-C--4B42 | TT_FinMile | (OTD-OS) ON SITE BOP I&amp;C FIELD DEVICES AND ERECTION MATERIAL | 18/08/2018 | 18/08/2018 | 25/08/2018 | 25/08/2018 | 0 | TK_Complete
SI-CP-3-25 | TT_Task | DETAIL DESIGN, MANUFACTURING, SHOP TEST FOR BOP I&amp;C FIELD CABINETS | 01/06/2017 | 14/02/2018 | 20/05/2017 | 24/07/2018 | 0 | TK_Complete
SI-CP-4-25 | TT_Task | TRANSPORT TO SITE BOP I&amp;C FIELD CABINETS | 20/06/2018 | 18/08/2018 | 25/07/2018 | 25/08/2018 | 0 | TK_Complete
SI-CP-4-42 | TT_FinMile | (OTD-OS) ON SITE BOP I&amp;C FIELD CABINETS | 18/08/2018 | 18/08/2018 | 25/08/2018 | 25/08/2018 | 0 | TK_Complete
SI-C--3C25 | TT_Task | DETAIL DESIGN, MANUFACTURING, SHOP TEST FOR BOP I&amp;C CABLES | 26/09/2017 | 12/02/2018 | 16/09/2017 | 30/06/2018 | 0 | TK_Complete
SI-C--3C80 | TT_FinMile | (RFS) READY FOR SHIPMENT BOP I&amp;C CABLES | 19/06/2018 | 19/06/2018 | 30/06/2018 | 30/06/2018 | 0 | TK_Complete
SI-C--4C25 | TT_Task | TRANSPORT TO SITE FOR BOP I&amp;C CABLES | 20/06/2018 | 18/08/2018 | 01/07/2018 | 06/08/2018 | 0 | TK_Complete
SI-C--4C40 | TT_FinMile | (OTD-OS) ON SITE BOP I&amp;C CABLES | 18/08/2018 | 18/08/2018 | 06/08/2018 | 06/08/2018 | 0 | TK_Complete
SI-CR-3-25 | TT_Task | DETAIL DESIGN, MANUFACTURING/ SHOP TEST FOR CCR HMI EQUIPMENT | 01/06/2017 | 17/01/2018 | 18/05/2017 | 22/08/2018 | 0 | TK_Complete
SI-CR-3-26 | TT_FinMile | CENTRAL CONTROL ROOM I&amp;C EQUIPMENT CONCEPT PLAN READY | 12/12/2021 | 12/12/2021 | 17/05/2017 | 17/05/2017 | 0 | TK_Complete
SI-CR-3-80 | TT_FinMile | (RFS) READY FOR SHIPMENT CCR HMI EQUIPMENT | 19/06/2018 | 19/06/2018 | 23/08/2018 | 23/08/2018 | 0 | TK_Complete
SI-CR-4-25 | TT_Task | TRANSPORT TO SITE CCR HMI EQUIPMENT | 20/06/2018 | 18/08/2018 | 07/10/2018 | 12/11/2018 | 0 | TK_Complete
SI-CR-4-42 | TT_FinMile | (OTD-OS) ON SITE CCR HMI EQUIPMENT | 18/08/2018 | 18/08/2018 | 12/11/2018 | 12/11/2018 | 0 | TK_Complete
SI-CFE3-25 | TT_Task | DETAIL DESIGN, MANUFACTURING/ SHOP TEST FOR EMISSION MONITORING SYSTEM | 01/05/2017 | 18/02/2018 | 15/04/2017 | 24/05/2018 | 0 | TK_Complete
SI-CFE3-80 | TT_FinMile | (RFS) READY FOR SHIPMENT EMISSION MONITORING SYSTEM - CONTAINER | 30/06/2018 | 30/06/2018 | 31/10/2019 | 31/10/2019 | 0 | TK_Complete
SI-CFE4-25 | TT_Task | TRANSPORT TO SITE EMISSION MONITORING SYSTEM | 01/07/2018 | 29/08/2018 | 31/10/2019 | 14/11/2019 | 0 | TK_Complete
SI-CFE4-42 | TT_FinMile | (OTD-OS) ON SITE EMISSION MONITORING SYSTEM | 29/08/2018 | 29/08/2018 | 14/11/2019 | 14/11/2019 | 0 | TK_Complete
SI1UMC2A60 | TT_FinMile | (MS3) CONCRETE STRUCTURE FINAL DIMENSIONS AND LOADS AVAILABLE TS FOUNDATION UMC | 30/04/2017 | 30/04/2017 | 18/04/2017 | 18/04/2017 | 0 | TK_Complete
SI1UMC2A65 | TT_FinMile | (MS4) CONCRETE STRUCTURE FINAL INPUT EMBEDDED PARTS TS FOUNDATION UMC | 30/04/2017 | 30/04/2017 | 18/04/2017 | 18/04/2017 | 0 | TK_Complete
SI1UMC2A70 | TT_Task | DETAIL DESIGN / CHECKER CONCRETE STRUCTURE TS FOUNDATION UMC | 14/02/2017 | 15/05/2017 | 02/02/2017 | 13/10/2017 | 0 | TK_Complete
SI1UMC3B27 | TT_Task | FABRICATION DESIGN, FABRICATION, TRANSPORT EMBEDDED PARTS FOR TURBOSET FDN UMC | 01/05/2017 | 01/08/2017 | 01/04/2017 | 11/07/2017 | 0 | TK_Complete
SI1UMC4A50 | TT_Mile | EMBEDDED PARTS FOR TURBOSET FOUNDATION UMC ON-SITE | 21/08/2017 | 21/08/2017 | 20/07/2017 | 20/07/2017 | 0 | TK_Complete
SI1UMC2Y45 | TT_Task | PREPARATION BASIC BUILDING DWGS COND. PIT UMC | 14/02/2017 | 20/03/2017 | 05/02/2017 | 22/02/2017 | 0 | TK_Complete
SI1UMC2Y60 | TT_FinMile | (MS3) CONCRETE STRUCTURE FINAL DIMENSIONS LOADS AVAILABLE COND.PIT UMC 3a | 28/02/2017 | 28/02/2017 | 18/02/2017 | 18/02/2017 | 0 | TK_Complete
SI1UMC2-45 | TT_Task | PREPARATION BASIC BUILDING DWGS UMC | 29/03/2017 | 02/05/2017 | 14/03/2017 | 29/03/2017 | 0 | TK_Complete
SI1UMC2-60 | TT_FinMile | (MS3) CONCRETE STRUCTURE, FINAL DIMENSIONS AND LOADS AVAILABLE UMC | 10/04/2017 | 10/04/2017 | 21/03/2017 | 21/03/2017 | 0 | TK_Complete
SI1UMC2B60 | TT_FinMile | (MS3) CRANE WALKWAY FINAL DIMENSIONS AND LOADS AVAILABLE UMC | 07/04/2017 | 07/04/2017 | 29/03/2017 | 29/03/2017 | 0 | TK_Complete
SI1UMC2B70 | TT_Task | DETAIL DESIGN / CHECKER CRANE WALKWAY UMC | 01/04/2017 | 23/06/2017 | 16/03/2017 | 24/07/2017 | 0 | TK_Complete
SI1UMC2B75 | TT_Mile | (F) DETAIL DESIGN CRANE WALKWAY WITH CONTRACTOR UMC | 26/11/2017 | 26/11/2017 | 09/11/2017 | 09/11/2017 | 0 | TK_Complete
SI1UMC2G60 | TT_FinMile | (MS3) STEEL PLATFORM LUBE OIL, FINAL DIMENSIONS AND LOADS AVAILABLE UMC | 25/06/2017 | 25/06/2017 | 01/06/2017 | 01/06/2017 | 0 | TK_Complete
SI1UMC2G70 | TT_Task | DETAIL DESIGN / CHECKER STEEL PLATFORM LUBE OIL UMC | 26/06/2017 | 11/08/2017 | 02/06/2017 | 24/07/2017 | 0 | TK_Complete
SI1UMC2G75 | TT_Mile | (F) DETAIL DESIGN STEEL PLATFORM LUBE OIL DWGS WITH CONTRACTOR UMC | 26/11/2017 | 26/11/2017 | 09/11/2017 | 09/11/2017 | 0 | TK_Complete
SI1UMC3B25 | TT_Task | FABRICATION DESIGN, FABRICATION, TRANSPORT, ON SITE CRANE WALKWAY UMC | 31/10/2017 | 18/01/2018 | 10/11/2017 | 23/04/2018 | 0 | TK_Complete
SI1UMC3G25 | TT_Task | FABRICATION DESIGN, FABRICATION, TRANSPORT, ON SITE STEEL PLATFORM LUBE OIL UMC | 31/10/2017 | 18/01/2018 | 10/11/2017 | 23/04/2018 | 0 | TK_Complete
SI1UMC2I113 | TT_FinMile | (MS3) STEEL PLATFORM CRANE RAILS FINAL DIMENSIONS AND LOADS AVAILABLE UMC | 01/07/2017 | 01/07/2017 | 01/06/2017 | 01/06/2017 | 0 | TK_Complete
SI1UMC2I115 | TT_Task | DETAIL DESIGN / CHECKER STEEL PLATFORM CRANE RAILS UMC | 02/07/2017 | 02/09/2017 | 02/06/2017 | 07/08/2017 | 0 | TK_Complete
SI1UMC2I117 | TT_Mile | (F) DETAIL DESIGN STEEL PLATFORM CRANE RAILS DWGS WITH CONTRACTOR UMC | 31/10/2017 | 31/10/2017 | 25/11/2017 | 25/11/2017 | 0 | TK_Complete
SI1UMC3I39 | TT_Task | FABRICATION DESIGN, FABRICATION, TRANSPORT STEEL PLATFORM CRANE RAILS UMC | 31/10/2017 | 18/01/2018 | 25/11/2017 | 14/02/2018 | 0 | TK_Complete
SI1UMC2F60 | TT_FinMile | (MS3) STEEL PLATFORM ENTRANCE, FINAL DIMENSIONS AND LOADS AVAILABLE UMC | 31/05/2017 | 31/05/2017 | 25/05/2017 | 25/05/2017 | 0 | TK_Complete
SI1UMC2F70 | TT_Task | DETAIL DESIGN / CHECKER STEEL PLATFORM ENTRANCE UMC | 01/06/2017 | 26/07/2017 | 26/05/2017 | 25/07/2017 | 0 | TK_Complete
SI1UMC2F75 | TT_Mile | (F) DETAIL DESIGN STEEL PLATFORM ENTRANCE DWGS WITH CONTRACTOR UMC | 26/11/2017 | 26/11/2017 | 24/11/2017 | 24/11/2017 | 0 | TK_Complete
SI1UMC3F25 | TT_Task | FABRICATION DESIGN, FABRICATION, TRANSPORT, ON SITE STEEL PLATFORM ENTRANCE UMC | 21/11/2017 | 08/02/2018 | 24/11/2017 | 27/06/2018 | 0 | TK_Complete
SI1UMC2E60 | TT_FinMile | (MS3) STEEL PLATFORM COND. PIT, FINAL DIMENSIONS AND LOADS AVAILABLE UMC | 30/04/2017 | 30/04/2017 | 18/04/2017 | 18/04/2017 | 0 | TK_Complete
SI1UMC2E70 | TT_Task | DETAIL DESIGN / CHECKER STEEL PLATFORM COND. PIT UMC | 01/05/2017 | 02/07/2017 | 09/04/2017 | 30/05/2017 | 0 | TK_Complete
SI1UMC2E75 | TT_Mile | (F) DETAIL DESIGN STEEL PLATFORM COND. PIT DWGS WITH CONTRACTOR UMC | 31/10/2017 | 31/10/2017 | 25/11/2017 | 25/11/2017 | 0 | TK_Complete
SI1UMC3E25 | TT_Task | FABRICATION DESIGN, FABRICATION, TRANSPORT, ON SITE STEEL PLATFORM COND. PIT UMC | 26/11/2017 | 18/01/2018 | 25/11/2017 | 23/04/2018 | 0 | TK_Complete
SI1UMC2L60 | TT_FinMile | (MS3) STEEL PLATFORM ST, FINAL DIMENSIONS AND LOADS AVAILABLE UMC | 25/06/2017 | 25/06/2017 | 01/06/2017 | 01/06/2017 | 0 | TK_Complete
SI1UMC2L70 | TT_Task | DETAIL DESIGN / CHECKER STEEL PLATFORM ST UMC | 26/06/2017 | 17/08/2017 | 02/06/2017 | 26/07/2017 | 0 | TK_Complete
SI1UMC2L75 | TT_Mile | (F) DETAIL DESIGN STEEL PLATFORM ST DWGS WITH CONTRACTOR UMC | 26/11/2017 | 26/11/2017 | 25/11/2017 | 25/11/2017 | 0 | TK_Complete
SI1UMC3L25 | TT_Task | FABRICATION DESIGN, FABRICATION, TRANSPORT, ON SITE STEEL PLATFORM GENERATOR UMC | 26/11/2017 | 09/03/2018 | 25/11/2017 | 30/08/2018 | 0 | TK_Complete
SI1UMC2J60 | TT_FinMile | (MS3) STEEL PLATFORM GT, FINAL DIMENSIONS AND LOADS AVAILABLE UMC | 31/05/2017 | 31/05/2017 | 19/05/2017 | 19/05/2017 | 0 | TK_Complete
SI1UMC2J70 | TT_Task | DETAIL DESIGN / CHECKER STEEL PLATFORM GT UMC | 01/06/2017 | 02/08/2017 | 01/05/2017 | 24/05/2017 | 0 | TK_Complete
SI1UMC2J75 | TT_Mile | (F) DETAIL DESIGN STEEL PLATFORM GT DWGS WITH CONTRACTOR UMC | 31/10/2017 | 31/10/2017 | 31/10/2017 | 31/10/2017 | 0 | TK_Complete
SI1UMC3J25 | TT_Task | FABRICATION DESIGN, FABRICATION, TRANSPORT, ON SITE STEEL PLATFORM GT UMC | 26/11/2017 | 13/02/2018 | 01/11/2017 | 23/04/2018 | 0 | TK_Complete
SI1UMC2I83 | TT_FinMile | (MS3) STEEL PLATFORM CONDENSER MANHOLE ACCESS FINAL DIMENSIONS AND LOADS AVAILABLE UMC | 25/06/2017 | 25/06/2017 | 01/06/2017 | 01/06/2017 | 0 | TK_Complete
SI1UMC2I85 | TT_Task | DETAIL DESIGN / CHECKER STEEL PLATFORM CONDENSER MANHOLE ACCESS UMC | 26/06/2017 | 16/09/2017 | 02/06/2017 | 14/11/2017 | 0 | TK_Complete
SI1UMC2I87 | TT_Mile | (F) DETAIL DESIGN STEEL PLATFORM CONDENSER MANHOLE ACCESS DWGS WITH CONTRACTOR UMC | 26/01/2018 | 26/01/2018 | 24/01/2018 | 24/01/2018 | 0 | TK_Complete
SI1UMC3I29 | TT_Task | FABRICATION DESIGN, FABRICATION, TRANSPORT, ON SITE STEEL PLATFORM CONDENSER MANHOLE ACCESS UMC | 26/01/2018 | 05/04/2018 | 24/01/2018 | 27/06/2018 | 0 | TK_Complete
SI1UMC2I101 | TT_FinMile | (MS3) STEEL PLATFORM OVER TG FDN FINAL DIMENSIONS AND LOADS AVAILABLE UMC | 02/07/2017 | 02/07/2017 | 08/06/2017 | 08/06/2017 | 0 | TK_Complete
SI1UMC2I103 | TT_Task | DETAIL DESIGN / CHECKER STEEL PLATFORM OVER TG FDN UMC | 03/07/2017 | 16/09/2017 | 09/06/2017 | 15/09/2017 | 0 | TK_Complete
SI1UMC2I105 | TT_Mile | (F) DETAIL DESIGN STEEL PLATFORM OVER TG FDN DWGS WITH CONTRACTOR UMC | 26/01/2018 | 26/01/2018 | 20/01/2018 | 20/01/2018 | 0 | TK_Complete
SI1UMC3I35 | TT_Task | FABRICATION DESIGN, FABRICATION, TRANSPORT, ON SITE STEEL PLATFORM OVER TG FDN UMC | 26/01/2018 | 06/06/2018 | 20/01/2018 | 15/11/2018 | 0 | TK_Complete
SI1UMC2I107 | TT_FinMile | (MS3) STEEL MISC. PLATFORM FINAL DIMENSIONS AND LOADS AVAILABLE UMC | 02/07/2017 | 02/07/2017 | 08/06/2017 | 08/06/2017 | 0 | TK_Complete
SI1UMC2I109 | TT_Task | DETAIL DESIGN / CHECKER STEEL MISC. PLATFORM UMC | 03/07/2017 | 16/09/2017 | 09/06/2017 | 04/01/2018 | 0 | TK_Complete
SI1UMC2I111 | TT_Mile | (F) DETAIL DESIGN STEEL MISC. PLATFORM DWGS WITH CONTRACTOR UMC | 02/03/2018 | 02/03/2018 | 20/01/2018 | 20/01/2018 | 0 | TK_Complete
SI1UMC3I37 | TT_Task | FABRICATION DESIGN, FABRICATION, TRANSPORT, ON SITE STEEL MISC. PLATFORM UMC | 02/03/2018 | 10/07/2018 | 20/01/2018 | 15/11/2018 | 0 | TK_Complete
SI1UMC2I60 | TT_FinMile | (MS3) STEEL PLATFORM BEARING ACCESS FINAL DIMENSIONS AND LOADS AVAILABLE UMC | 25/06/2017 | 25/06/2017 | 01/06/2017 | 01/06/2017 | 0 | TK_Complete
SI1UMC2I70 | TT_Task | DETAIL DESIGN / CHECKER STEEL PLATFORM BEARING ACCESS UMC | 26/06/2017 | 16/09/2017 | 02/06/2017 | 15/09/2017 | 0 | TK_Complete
SI1UMC2I75 | TT_Mile | (F) DETAIL DESIGN STEEL PLATFORM BEARING ACCESS DWGS WITH CONTRACTOR UMC | 26/01/2018 | 26/01/2018 | 20/01/2018 | 20/01/2018 | 0 | TK_Complete
SI1UMC3I25 | TT_Task | FABRICATION DESIGN, FABRICATION, TRANSPORT, ON SITE STEEL PLATFORM BEARING ACCESS UMC | 26/01/2018 | 05/06/2018 | 20/01/2018 | 15/11/2018 | 0 | TK_Complete
SI1UMC2I89 | TT_FinMile | (MS3) STEEL PLATFORM PIPE ACCESS NEAR CEP FINAL DIMENSIONS AND LOADS AVAILABLE UMC | 31/03/2017 | 31/03/2017 | 15/03/2017 | 15/03/2017 | 0 | TK_Complete
SI1UMC2I91 | TT_Task | DETAIL DESIGN / CHECKER STEEL PLATFORM PIPE ACCESS NEAR CEP UMC | 01/04/2017 | 02/06/2017 | 16/03/2017 | 12/05/2017 | 0 | TK_Complete
SI1UMC2I93 | TT_Mile | (F) DETAIL DESIGN STEEL PLATFORM PIPE ACCESS NEAR CEP DWGS WITH CONTRACTOR UMC | 26/11/2017 | 26/11/2017 | 21/11/2017 | 21/11/2017 | 0 | TK_Complete
SI1UMC3I31 | TT_Task | FABRICATION DESIGN, FABRICATION, TRANSPORT, ON SITE STEEL PLATFORM PIPE ACCESS NEAR CEP UMC | 26/11/2017 | 09/03/2018 | 21/11/2017 | 30/08/2018 | 0 | TK_Complete
SI1UMC2I95 | TT_FinMile | (MS3) STEEL PLATFORM LP BY-PASS FINAL DIMENSIONS AND LOADS AVAILABLE UMC | 25/06/2017 | 25/06/2017 | 01/06/2017 | 01/06/2017 | 0 | TK_Complete
SI1UMC2I97 | TT_Task | DETAIL DESIGN / CHECKER STEEL PLATFORM LP BY-PASS UMC | 26/06/2017 | 17/08/2017 | 02/06/2017 | 26/07/2017 | 0 | TK_Complete
SI1UMC2I99 | TT_Mile | (F) DETAIL DESIGN STEEL PLATFORM LP BY-PASS DWGS WITH CONTRACTOR UMC | 21/11/2017 | 21/11/2017 | 21/11/2017 | 21/11/2017 | 0 | TK_Complete
SI1UMC3I33 | TT_Task | FABRICATION DESIGN, FABRICATION, TRANSPORT, ON SITE STEEL PLATFORM LP BY-PASS UMC | 26/11/2017 | 03/02/2018 | 21/11/2017 | 30/08/2018 | 0 | TK_Complete
SI1UMC2I77 | TT_FinMile | (MS3) STEEL PLATFORM BUS DUCT SUPPORT FINAL DIMENSIONS AND LOADS AVAILABLE UMC | 25/06/2017 | 25/06/2017 | 01/06/2017 | 01/06/2017 | 0 | TK_Complete
SI1UMC2I79 | TT_Task | DETAIL DESIGN / CHECKER STEEL PLATFORM BUS DUCT SUPPORT UMC | 26/06/2017 | 16/09/2017 | 02/06/2017 | 14/11/2017 | 0 | TK_Complete
SI1UMC2I81 | TT_Mile | (F) DETAIL DESIGN STEEL PLATFORM BUS DUCT SUPPORT DWGS WITH CONTRACTOR UMC | 26/01/2018 | 26/01/2018 | 20/01/2018 | 20/01/2018 | 0 | TK_Complete
SI1UMC3I27 | TT_Task | FABRICATION DESIGN, FABRICATION, TRANSPORT, ON SITE STEEL PLATFORM BUS DUCT SUPPORT UMC | 26/01/2018 | 06/06/2018 | 20/01/2018 | 15/11/2018 | 0 | TK_Complete
SI1UMC2P60 | TT_FinMile | (MS3) STEEL ATTACHED TO MAIN FRAME, FINAL DIMENSIONS AND LOADS AVAILABLE UMC | 25/08/2017 | 25/08/2017 | 03/08/2017 | 03/08/2017 | 0 | TK_Complete
SI1UMC2P70 | TT_Task | DETAIL DESIGN / CHECKER STEEL ATTACHED TO MAIN FRAME | 26/08/2017 | 20/10/2017 | 04/08/2017 | 14/11/2017 | 0 | TK_Complete
SI1UMC2P75 | TT_Mile | (F) DETAIL DESIGN STEEL ATTACHED TO MAIN FRAME DWGS WITH CONTRACTOR UMC | 26/01/2018 | 26/01/2018 | 20/01/2018 | 20/01/2018 | 0 | TK_Complete
SI1UMC3P25 | TT_Task | FABRICATION DESIGN, FABRICATION, TRANSPORT, ON SITE STEEL ATTACHED TO MAIN FRAME | 26/01/2018 | 06/06/2018 | 20/01/2018 | 27/06/2018 | 0 | TK_Complete
SI1UMC2O77 | TT_FinMile | (MS3) UMCM1Y MODULE PIPE RACK, FINAL DIMENSIONS AND LOADS AVAILABLE UMC | 14/02/2017 | 14/02/2017 | 13/02/2017 | 13/02/2017 | 0 | TK_Complete
SI1UMC2X10 | TT_Task | DETAIL DESIGN UMCM1Y MODULE PIPE RACK | 01/03/2017 | 12/09/2017 | 14/02/2017 | 28/08/2017 | 0 | TK_Complete
SI1UMC3X10 | TT_Task | DELIVERY OF SKID FRAME STEEL, PIPING MATERIAL UMCM1Y MODULE PIPE RACK | 29/09/2017 | 13/12/2017 | 29/08/2017 | 12/11/2017 | 0 | TK_Complete
SI1UMC3X25 | TT_Task | MANUFACTURING UMCM1Y MODULE PIPE RACK | 26/10/2017 | 02/02/2018 | 02/10/2017 | 26/04/2018 | 0 | TK_Complete
SI1UMC4X25 | TT_Task | TRANSPORT UMCM1Y MODULE PIPE RACK | 15/04/2018 | 27/04/2018 | 23/05/2018 | 29/05/2018 | 0 | TK_Complete
SI1UMC4X42 | TT_FinMile | (OTD-OS) ON SITE UMCM1Y MODULE PIPE RACK | 27/04/2018 | 27/04/2018 | 29/05/2018 | 29/05/2018 | 0 | TK_Complete
SI1UMC2O60 | TT_FinMile | (MS3) UMCL1Y MODULE PIPE RACK, FINAL DIMENSIONS AND LOADS AVAILABLE UMC | 14/02/2017 | 14/02/2017 | 06/02/2017 | 06/02/2017 | 0 | TK_Complete
SI1UMC2Y10 | TT_Task | DETAIL DESIGN UMCL1Y MODULE PIPE RACK | 14/02/2017 | 17/07/2017 | 07/02/2017 | 10/07/2017 | 0 | TK_Complete
SI1UMC3Y10 | TT_Task | DELIVERY OF SKID FRAME STEEL, PIPING MATERIAL UMCL1Y MODULE PIPE RACK | 09/08/2017 | 19/11/2017 | 11/07/2017 | 21/10/2017 | 0 | TK_Complete
SI1UMC3Y25 | TT_Task | MANUFACTURING UMCL1Y MODULE PIPE RACK | 21/11/2017 | 08/02/2018 | 22/10/2017 | 01/03/2018 | 0 | TK_Complete
SI1UMC4Y25 | TT_Task | TRANSPORT UMCL1Y MODULE PIPE RACK | 15/04/2018 | 27/04/2018 | 17/04/2018 | 27/04/2018 | 0 | TK_Complete
SI1UMC4Y42 | TT_FinMile | (OTD-OS) ON SITE UMCL1Y MODULE PIPE RACK | 27/04/2018 | 27/04/2018 | 27/04/2018 | 27/04/2018 | 0 | TK_Complete
SI1BZP2K30 | TT_Task | DETAIL DESIGN CABLE SUPPORT SYSTEM STEEL PLATFOR UMC | 25/07/2017 | 18/09/2017 | 30/06/2017 | 24/08/2017 | 0 | TK_Complete
SI1MAL2-10 | TT_Task | DETAIL DESIGN MAL00Y MODULE | 16/03/2017 | 23/08/2017 | 02/03/2017 | 27/07/2017 | 0 | TK_Complete
SI1MAL2O79 | TT_FinMile | (MS3) MAL00Y MODULE FINAL DIMENSIONS AND LOADS AVAILABLE UMC | 31/03/2017 | 31/03/2017 | 15/03/2017 | 15/03/2017 | 0 | TK_Complete
SI1MAL3-10 | TT_Task | DELIVERY OF SKID FRAME STEEL, PIPING MATERIAL MAL00Y MODULE | 11/09/2017 | 06/12/2017 | 28/07/2017 | 04/11/2017 | 0 | TK_Complete
SI1MAL3-25 | TT_Task | MANUFACTURING MAL00Y MODULE | 06/12/2017 | 09/02/2018 | 05/11/2017 | 15/03/2018 | 0 | TK_Complete
SI1MAL4-42 | TT_Task | TRANSPORT MAL00Y MODULE | 15/04/2018 | 27/04/2018 | 17/04/2018 | 27/04/2018 | 0 | TK_Complete
SI1MAL4-44 | TT_FinMile | (OTD-OS) ON SITE MAL00Y MODULE | 27/04/2018 | 27/04/2018 | 27/04/2018 | 27/04/2018 | 0 | TK_Complete
SI1SMM2-60 | TT_FinMile | (DF) FINAL INPUT FOR MS3 CRANE SMM01/02 FOR UMC | 31/03/2017 | 31/03/2017 | 15/03/2017 | 15/03/2017 | 0 | TK_Complete
SI1SMM2-75 | TT_Task | CONTRACT REVIEW, PREPARATION RFQ CRANE SMM01/02 FOR UMC | 14/01/2017 | 12/02/2017 | 12/12/2016 | 30/12/2016 | 0 | TK_Complete
SI1SMM2-80 | TT_Task | QUOTATION STAGE CRANE SMM01/02 FOR UMC | 13/02/2017 | 19/03/2017 | 31/12/2016 | 27/02/2017 | 0 | TK_Complete
SI1SMM2-85 | TT_Mile | ORDER PLACED CRANE SMM01/02 FOR UMC | 01/03/2017 | 01/03/2017 | 28/02/2017 | 28/02/2017 | 0 | TK_Complete
SI1SMM3-25 | TT_Task | FABRICATION DESIGN, MANUFACTURING, SHOP TEST CRANE SMM01, 02 FOR UMC | 16/03/2017 | 21/12/2017 | 01/03/2017 | 30/11/2017 | 0 | TK_Complete
SI1SMM3-80 | TT_FinMile | (RFS) READY FOR SHIPMENT CRANE SMM01/02 FOR UMC | 20/12/2017 | 20/12/2017 | 30/11/2017 | 30/11/2017 | 0 | TK_Complete
SI1SMM4-27 | TT_Task | TRANSPORT CRANE SMM01/02 FOR UMC | 16/12/2017 | 14/01/2018 | 13/12/2017 | 01/01/2018 | 0 | TK_Complete
SI1SMM4-40 | TT_FinMile | (OTD-OS) ON SITE CRANE SMM01/02 FOR UMC | 08/02/2018 | 08/02/2018 | 01/01/2018 | 01/01/2018 | 0 | TK_Complete
SI1SMM3A25 | TT_Task | FABRICATION DESIGN, MANUFACTURING, SHOP TEST CRANE SMM03 FOR UMC | 01/06/2017 | 29/11/2017 | 30/05/2017 | 15/12/2017 | 0 | TK_Complete
SI1SMM3A80 | TT_FinMile | (RFS) READY FOR SHIPMENT CRANES SMM03 FOR UMC | 26/01/2018 | 26/01/2018 | 14/12/2017 | 14/12/2017 | 0 | TK_Complete
SI1SMM4A27 | TT_Task | TRANSPORT CRANES SMM03 FOR UMC | 26/01/2018 | 24/02/2018 | 15/12/2017 | 15/01/2018 | 0 | TK_Complete
SI1SMM4A40 | TT_FinMile | (OTD-OS) ON SITE CRANES SMM03 FOR UMC | 25/02/2018 | 25/02/2018 | 15/01/2018 | 15/01/2018 | 0 | TK_Complete
SP1MA-3-25 | TT_Task | DETAIL DESIGN / MANUFACTURING / ASSEMBLY HP/IP-LP ST &amp; ST-AUXILIARIES MA | 26/11/2016 | 24/01/2018 | 20/11/2016 | 21/11/2017 | 0 | TK_Complete
SI1MAD4-27 | TT_Task | TRANSPORT ST BEARINGS MAD | 16/12/2017 | 21/01/2018 | 03/12/2017 | 08/01/2018 | 0 | TK_Complete
SP1MAD3-80 | TT_Mile | DELIVERY ST BEARINGS MAD EX WORKS | 26/10/2017 | 26/10/2017 | 06/10/2017 | 06/10/2017 | 0 | TK_Complete
SP1MAD4-15 | TT_Task | TRANSPORT ST BEARINGS MAD TO NORTH SEA PORT | 26/10/2017 | 01/11/2017 | 06/10/2017 | 12/10/2017 | 0 | TK_Complete
SI1MA-4-63 | TT_Task | TRANSPORT STEAM TURBINE MA- (HP/IP) (incl. FCA) | 26/01/2018 | 31/03/2018 | 18/01/2018 | 01/04/2018 | 0 | TK_Complete
SP1MA-3-82 | TT_Mile | DELIVERY STEAM TURBINE MA- (HP/IP) EX WORKS | 26/01/2018 | 26/01/2018 | 12/12/2017 | 12/12/2017 | 0 | TK_Complete
SP1MA-4-15 | TT_Task | TRANSPORT STEAM TURBINE MA- (HP/IP) TO NORTH SEA PORT | 26/01/2018 | 01/02/2018 | 12/01/2018 | 15/01/2018 | 0 | TK_Complete
SI1MA-4-65 | TT_Task | TRANSPORT ST MA- (LP OUTER CASING) | 26/03/2018 | 12/04/2018 | 07/03/2018 | 04/04/2018 | 0 | TK_Complete
SI1MA-4-67 | TT_Task | TRANSPORT ST MA- (LP-ROTOR, INNER CASING) | 26/01/2018 | 05/04/2018 | 18/01/2018 | 01/04/2018 | 0 | TK_Complete
SP1MA-3-84 | TT_Mile | DELIVERY ST MA- (LP OUTER CASING) EX WORKS | 26/11/2017 | 26/11/2017 | 27/10/2017 | 27/10/2017 | 0 | TK_Complete
SP1MA-3-86 | TT_Mile | DELIVERY ST MA- (LP ROTOR, INNERCASING) EX WORKS | 26/01/2018 | 26/01/2018 | 14/12/2017 | 14/12/2017 | 0 | TK_Complete
SP1MA-4-22 | TT_Task | TRANSPORT ST MA- (LP OUTER CASING) TO BANTEN PORT | 26/01/2018 | 01/02/2018 | 30/11/2017 | 06/12/2017 | 0 | TK_Complete
SP1MA-4-26 | TT_Task | TRANSPORT ST MA- (LP-ROTOR, INNER CASING) TO NORTH SEA PORT | 26/01/2018 | 01/02/2018 | 28/12/2017 | 03/01/2018 | 0 | TK_Complete
SI1MA-4-57 | TT_Task | TRANSPORT ST VALVES (for MAL00Y MODULE) TO MODULE ASSEMBLY SHOP | 26/09/2017 | 13/11/2017 | 15/09/2017 | 24/10/2017 | 0 | TK_Complete
SP1MA-3-88 | TT_Mile | DELIVERY ST VALVES (for MAL00Y MODULE) EX WORKS | 26/09/2017 | 26/09/2017 | 15/09/2017 | 15/09/2017 | 0 | TK_Complete
SI1MAG4-25 | TT_Task | TRANSPORT CONDENSER MAG | 07/03/2018 | 24/03/2018 | 07/03/2018 | 04/04/2018 | 0 | TK_Complete
SI1MAG4-42 | TT_FinMile | (OTD-OS) ON SITE CONDENSER MAG | 31/03/2018 | 31/03/2018 | 04/04/2018 | 04/04/2018 | 0 | TK_Complete
SP1MAG3-25 | TT_Task | DESIGN / MANUFACTURING ST CONDENSER MAG | 01/03/2017 | 23/02/2018 | 22/02/2017 | 03/01/2018 | 0 | TK_Complete
SP1MAG3-80 | TT_Mile | DELIVERY ST CONDENSER MAG EX WORKS | 26/01/2018 | 26/01/2018 | 03/01/2018 | 03/01/2018 | 0 | TK_Complete
SP1MAG4-15 | TT_Task | TRANSPORT ST CONDENSER MAG TO PORT OF EXPORT | 26/03/2018 | 01/04/2018 | 26/02/2018 | 28/02/2018 | 0 | TK_Complete
SI1MA-4-61 | TT_Task | TRANSPORT REMOVAL SYSTEM MAJ (China factory to Site) | 04/03/2018 | 18/03/2018 | 04/03/2018 | 23/03/2018 | 0 | TK_Complete
SI1MAJ4-46 | TT_FinMile | (OTD-OS) ON SITE REMOVAL SYSTEM MAJ | 26/03/2018 | 26/03/2018 | 23/03/2018 | 23/03/2018 | 0 | TK_Complete
SP1MAJ3-80 | TT_Mile | DELIVERY AIR REMOVAL SYSTEM MAJ EX WORKS | 26/03/2018 | 26/03/2018 | 02/03/2018 | 02/03/2018 | 0 | TK_Complete
SI1MAV4-25 | TT_Task | TRANSPORT LUBE OIL MODUL MAV | 26/01/2018 | 15/03/2018 | 18/01/2018 | 01/04/2018 | 0 | TK_Complete
SI1MAV4-42 | TT_FinMile | (OTD-OS) ON SITE LUBE OIL MODUL MAV | 31/03/2018 | 31/03/2018 | 01/04/2018 | 01/04/2018 | 0 | TK_Complete
SP1MAV3-80 | TT_Mile | DELIVERY ST LUBE OIL MODULE MAV EX WORKS | 19/02/2018 | 19/02/2018 | 04/01/2018 | 04/01/2018 | 0 | TK_Complete
SP1MAV4-15 | TT_Task | TRANSPORT ST LUBE OIL MODULE MAV TO NORTH SEA PORT | 26/01/2018 | 01/02/2018 | 08/01/2018 | 14/01/2018 | 0 | TK_Complete
SI1MAW4-25 | TT_Task | TRANSPORT TO SITE ST GLAND STEAM CONDENSER MAW | 18/01/2018 | 28/03/2018 | 18/01/2018 | 01/04/2018 | 0 | TK_Complete
SI1MAW4-42 | TT_FinMile | (OTD-OS) ON SITE ST GLAND STEAM CONDENSER MAW | 31/03/2018 | 31/03/2018 | 01/04/2018 | 01/04/2018 | 0 | TK_Complete
SP1MAW3-80 | TT_Mile | DELIVERY ST GLAND STEAM CONDENSER MAW EX WORKS | 05/01/2018 | 05/01/2018 | 04/12/2017 | 04/12/2017 | 0 | TK_Complete
SP1MAW4-15 | TT_Task | TRANSPORT ST GLAND STEAM CONDENSER MAW TO NORTH SEA PORT | 26/01/2018 | 01/02/2018 | 08/01/2018 | 14/01/2018 | 0 | TK_Complete
SI1MAX4-25 | TT_Task | TRANSPORT TO SITE HYDRAULIC SYSTEM MAX | 26/01/2018 | 26/03/2018 | 18/01/2018 | 01/04/2018 | 0 | TK_Complete
SI1MAX4-42 | TT_FinMile | (OTD-OS) ON SITE HYDRAULIC SYSTEM MAX | 31/03/2018 | 31/03/2018 | 01/04/2018 | 01/04/2018 | 0 | TK_Complete
SP1MAX3-80 | TT_Mile | DELIVERY ST HYDRAULIC SYSTEM MAX EX WORKS | 17/12/2017 | 17/12/2017 | 16/11/2017 | 16/11/2017 | 0 | TK_Complete
SP1MAX4-15 | TT_Task | TRANSPORT ST HYDRAULIC SYSTEM MAX TO NORTH SEA PORT | 26/01/2018 | 01/02/2018 | 08/01/2018 | 14/01/2018 | 0 | TK_Complete
SI1MPB4-27 | TT_Task | TRANSPORT ST NOISE PROTECTION SYSTEM MPB20 | 15/02/2018 | 18/04/2018 | 15/02/2018 | 21/03/2018 | 0 | TK_Complete
SP1MPB3-80 | TT_Mile | DELIVERY ST ENCLOSURE MPB20 EX WORKS | 26/01/2018 | 26/01/2018 | 19/01/2018 | 19/01/2018 | 0 | TK_Complete
SP1MPB4-15 | TT_Task | TRANSPORT ST ENCLOSURE MPB20 TO NORTH SEA PORT | 26/01/2018 | 01/02/2018 | 19/01/2018 | 25/01/2018 | 0 | TK_Complete
SI1MKA4-27 | TT_Task | TRANSPORT GENERATOR MK | 26/01/2018 | 05/04/2018 | 18/01/2018 | 01/04/2018 | 0 | TK_Complete
SP1MKA2-85 | TT_Mile | ORDER PLACED ST GENERATOR MKA INCL. COOLER MKA70 | 26/11/2016 | 26/11/2016 | 24/11/2016 | 24/11/2016 | 0 | TK_Complete
SP1MKA3-25 | TT_Task | MANUFACTURING ST GENERATOR MKA INCL. COOLER MKA70 | 24/11/2016 | 13/01/2018 | 24/11/2016 | 14/12/2017 | 0 | TK_Complete
SP1MKA3-80 | TT_Mile | DELIVERY ST GENERATOR MKA INCL. COOLER MKA70 EX WORKS | 26/01/2018 | 26/01/2018 | 02/01/2018 | 02/01/2018 | 0 | TK_Complete
SP1MKA4-15 | TT_Task | TRANSPORT ST GENERATOR MKA INCL. COOLER MKA70 TO PORT OF EXPORT | 26/01/2018 | 01/02/2018 | 02/01/2018 | 10/01/2018 | 0 | TK_Complete
SI1MKA4E27 | TT_Task | TRANSPORT GENERATOR SKIDS MKA | 26/03/2018 | 08/05/2018 | 18/03/2018 | 13/05/2018 | 0 | TK_Complete
SI1MB-4E31 | TT_Task | TRANSPORT GT INTERCONNECTING PIPING MB- | 26/02/2018 | 06/05/2018 | 15/02/2018 | 21/03/2018 | 0 | TK_Complete
SP1MB-3A80 | TT_Mile | DELIVERY GT INTERCONNECTING PIPING MB- EX WORKS | 26/02/2018 | 26/02/2018 | 14/02/2018 | 14/02/2018 | 0 | TK_Complete
SI1MBA4-27 | TT_Task | TRANSPORT GAS TURBINE MB | 02/02/2018 | 12/04/2018 | 18/01/2018 | 01/04/2018 | 0 | TK_Complete
SP1MB-2G75 | TT_Task | PREPARATION OF RFQ GT INSULATION MB- | 01/05/2017 | 14/05/2017 | 16/04/2017 | 29/04/2017 | 0 | TK_Complete
SP1MB-2G80 | TT_Task | QUOTATION STAGE GT INSULATION MB- | 15/05/2017 | 28/05/2017 | 30/04/2017 | 13/05/2017 | 0 | TK_Complete
SP1MB-2G85 | TT_Mile | ORDER PLACED GT INSULATION MB- | 01/06/2017 | 01/06/2017 | 14/05/2017 | 14/05/2017 | 0 | TK_Complete
SP1MB-3-25 | TT_Task | DESIGN / PROCUREMENT / MANUFACTURING GAS TURBINE | 14/01/2017 | 12/03/2018 | 18/12/2016 | 14/12/2017 | 0 | TK_Complete
SP1MB-3-80 | TT_Mile | DELIVERY GAS TURBINE MB- EX WORKS | 26/01/2018 | 26/01/2018 | 02/01/2018 | 02/01/2018 | 0 | TK_Complete
SP1MB-3G25 | TT_Task | DESIGN / MANUFACTURING GT INSULATION MB- | 01/06/2017 | 01/01/2018 | 14/05/2017 | 14/12/2017 | 0 | TK_Complete
SP1MB-3G80 | TT_Mile | DELIVERY GT INSULATION MB- EX WORKS | 26/01/2018 | 26/01/2018 | 15/12/2017 | 15/12/2017 | 0 | TK_Complete
SP1MB-4-15 | TT_Task | TRANSPORT GAS TURBINE MB- TO NORTH SEA PORT | 26/01/2018 | 01/02/2018 | 02/01/2018 | 10/01/2018 | 0 | TK_Complete
SI1MB-4E29 | TT_Task | TRANSPORT GT AUXILIARIES MB- | 26/03/2018 | 08/05/2018 | 18/03/2018 | 13/05/2018 | 0 | TK_Complete
SI1MBL4-25 | TT_Task | TRANSPORT AIR INTAKE SYSTEM MBL | 09/02/2018 | 19/04/2018 | 18/01/2018 | 01/04/2018 | 0 | TK_Complete
SI1MBL4-42 | TT_FinMile | (OTD-OS) ON SITE AIR INTAKE SYSTEM MBL | 31/03/2018 | 31/03/2018 | 01/04/2018 | 01/04/2018 | 0 | TK_Complete
SP1MBL3-25 | TT_Task | DETAIL DESIGN / MANUFACTURING AIR INTAKE SYSTEM MBL | 16/03/2017 | 07/12/2017 | 02/03/2017 | 23/11/2017 | 0 | TK_Complete
SP1MBL3-80 | TT_Mile | DELIVERY AIR INTAKE SYSTEM MBL EX WORKS | 16/12/2017 | 16/12/2017 | 15/12/2017 | 15/12/2017 | 0 | TK_Complete
SP1MBL4-15 | TT_Task | TRANSPORT AIR INTAKE SYSTEM MBL TO PORT OF EXPORT | 26/01/2018 | 08/02/2018 | 02/01/2018 | 10/01/2018 | 0 | TK_Complete
SI1MPB4E27 | TT_Task | TRANSPORT GT ENCLOSURE INCL.VENT.MPB/SAM | 26/02/2018 | 06/05/2018 | 14/01/2018 | 22/02/2018 | 0 | TK_Complete
SI1SGJ4-27 | TT_Task | TRANSPORT ECONOPAC FIRE PROT.SYSTEM CYE/SGJ | 26/03/2018 | 08/05/2018 | 18/03/2018 | 13/05/2018 | 0 | TK_Complete
SP1SGJ3-25 | TT_Task | DETAIL DESIGN / MANUFACTURING FIRE FIGHTING / GAS DETECTION SGJ / CYQ / CYE | 01/04/2017 | 22/12/2017 | 16/03/2017 | 25/11/2017 | 0 | TK_Complete
SP1SGJ3-80 | TT_Mile | DELIVERY FIRE FIGHTING / GAS DETECTION SGJ / CYQ / CYE EX WORKS | 16/12/2017 | 16/12/2017 | 04/12/2017 | 04/12/2017 | 0 | TK_Complete
SI1LBG3C25 | TT_Task | FABRICATION DESIGN, PROCUREMENT, PRE-FABRICATION EL.SUPERHEATER LBG | 01/05/2017 | 07/10/2017 | 29/04/2017 | 08/12/2017 | 0 | TK_Complete
SI1LBG3C80 | TT_FinMile | (RFS) READY FOR SHIPMENT EL.SUPERHEATER LBG | 26/02/2018 | 26/02/2018 | 26/01/2018 | 26/01/2018 | 0 | TK_Complete
SI1LBG4C25 | TT_Task | TRANSPORT ELECTRICAL SUPERHEATER LBG | 08/03/2018 | 12/04/2018 | 08/02/2018 | 15/03/2018 | 0 | TK_Complete
SI1LBG4C42 | TT_FinMile | (OTD-OS) ON SITE ELECTRICAL SUPERHEATER LBG | 13/04/2018 | 13/04/2018 | 15/03/2018 | 15/03/2018 | 0 | TK_Complete
SI1LCB2B14 | TT_Mile | CONFIRMED PUMP CURVES CONDENSATE EXTRACTION PUMP LCB | 20/03/2017 | 20/03/2017 | 16/03/2017 | 16/03/2017 | 0 | TK_Complete
SI1LCB2B60 | TT_FinMile | (DF) FINAL INPUT FOR MS3 CONDENSATE EXTRACTION PUMP LCB | 30/04/2017 | 30/04/2017 | 11/04/2017 | 11/04/2017 | 0 | TK_Complete
SI1LCB2B65 | TT_FinMile | (DF) FINAL INPUT FOR M2 CONDENSATE EXTRACTION PUMP LCB | 30/04/2017 | 30/04/2017 | 11/04/2017 | 11/04/2017 | 0 | TK_Complete
SI1LCB2B75 | TT_Task | CONTRACT REVIEW, PREPARATION RFQ CONDENSATE EXTRACTION PUMP LCB | 26/11/2016 | 14/01/2017 | 10/11/2016 | 29/12/2016 | 0 | TK_Complete
SI1LCB2B80 | TT_Task | QUOTATION STAGE CONDENSATE EXTRACTION PUMP LCB | 03/02/2017 | 14/04/2017 | 30/12/2016 | 14/03/2017 | 0 | TK_Complete
SI1LCB2B85 | TT_Mile | ORDER PLACED CONDENSATE EXTRACTION PUMP LCB | 26/03/2017 | 26/03/2017 | 15/03/2017 | 15/03/2017 | 0 | TK_Complete
SI1LCB3B25 | TT_Task | DETAIL DESIGN, MANUFACTURING, SHOP TEST CONDENSATE EXTRACTION PUMP LCB | 26/08/2017 | 14/06/2018 | 08/08/2017 | 24/04/2018 | 0 | TK_Complete
SI1LCB3B80 | TT_FinMile | (RFS) READY FOR SHIPMENT CONDENSATE EXTRACTION PUMP LCB | 27/04/2018 | 27/04/2018 | 25/05/2018 | 25/05/2018 | 0 | TK_Complete
SI1LCB4B25 | TT_Task | TRANSPORT CONDENSATE EXTRACTION PUMP LCB | 28/04/2018 | 08/06/2018 | 25/05/2018 | 01/06/2018 | 0 | TK_Complete
SI1LCB4B42 | TT_FinMile | (OTD-OS) ON SITE CONDENSATE EXTRACTION PUMP LCB | 08/06/2018 | 08/06/2018 | 01/06/2018 | 01/06/2018 | 0 | TK_Complete
SI1PAH2-60 | TT_FinMile | (DF) FINAL INPUT FOR MS3 CONCRETE CONDENSER TUBE CLEANING SYSTEM PAH | 05/05/2017 | 05/05/2017 | 21/04/2017 | 21/04/2017 | 0 | TK_Complete
SI1PAH2-65 | TT_FinMile | (DF) FINAL INPUT FOR M2 CONDENSER TUBE CLEANING SYSTEM PAH | 05/05/2017 | 05/05/2017 | 21/04/2017 | 21/04/2017 | 0 | TK_Complete
SI1PAH2-75 | TT_Task | PREPARATION RFQ CONDENSER TUBE CLEANING SYSTEM PAH | 10/12/2016 | 30/12/2016 | 09/12/2016 | 29/12/2016 | 0 | TK_Complete
SI1PAH2-80 | TT_Task | QUOTATION STAGE CONDENSER TUBE CLEANING SYSTEM PAH | 14/01/2017 | 14/03/2017 | 30/12/2016 | 21/04/2017 | 0 | TK_Complete
SI1PAH2-85 | TT_Mile | ORDER PLACED CONDENSER TUBE CLEANING SYSTEM PAH | 08/05/2017 | 08/05/2017 | 22/04/2017 | 22/04/2017 | 0 | TK_Complete
SI1PAH2A60 | TT_FinMile | (DF) FINAL INPUT FOR MS3 STEEL CONDENSER TUBE CLEANING SYSTEM PAH | 31/05/2017 | 31/05/2017 | 05/05/2017 | 05/05/2017 | 0 | TK_Complete
SI1PAH3-25 | TT_Task | DETAIL DESIGN, MANUFACTURING CONDENSER TUBE CLEANING SYSTEM PAH | 01/05/2017 | 14/01/2018 | 23/04/2017 | 18/12/2017 | 0 | TK_Complete
SI1PAH3-80 | TT_FinMile | (RFS) READY FOR SHIPMENT CONDENSER TUBE CLEANING SYSTEM PAH | 26/01/2018 | 26/01/2018 | 16/12/2017 | 16/12/2017 | 0 | TK_Complete
SI1PAH4-27 | TT_Task | TRANSPORT CONDENSER TUBE CLEANING SYSTEM PAH | 26/01/2018 | 15/03/2018 | 16/12/2017 | 17/01/2018 | 0 | TK_Complete
SI1PCB2B60 | TT_FinMile | (DF) FINAL INPUT FOR MS3 IN UMC SERVICE COOLING WATER PUMP PCB | 31/03/2017 | 31/03/2017 | 30/03/2017 | 30/03/2017 | 0 | TK_Complete
SI1PCB2B65 | TT_FinMile | (DF) FINAL INPUT FOR M2 SERVICE COOLING WATER PUMP PCB | 31/03/2017 | 31/03/2017 | 30/03/2017 | 30/03/2017 | 0 | TK_Complete
SI1PCB2B75 | TT_Task | CONTRACT REVIEW, PREPARATION RFQ SERVICE COOLING WATER PUMP PCB | 17/12/2016 | 08/01/2017 | 24/11/2016 | 16/12/2016 | 0 | TK_Complete
SI1PCB2B80 | TT_Task | QUOTATION STAGE SERVICE COOLING WATER PUMP PCB | 02/02/2017 | 08/03/2017 | 29/12/2016 | 02/03/2017 | 0 | TK_Complete
SI1PCB2B85 | TT_Mile | ORDER PLACED SERVICE COOLING WATER PUMP PCB | 19/03/2017 | 19/03/2017 | 03/03/2017 | 03/03/2017 | 0 | TK_Complete
SI1PCB3B25 | TT_Task | DETAIL DESIGN, MANUFACTURING, SHOP TEST SERVICE COOLING WATER PUMP PCB | 19/03/2017 | 04/11/2017 | 04/03/2017 | 06/12/2017 | 0 | TK_Complete
SI1PCB3B80 | TT_FinMile | (RFS) READY FOR SHIPMENT SERVICE COOLING WATER PUMP PCB | 26/01/2018 | 26/01/2018 | 15/12/2017 | 15/12/2017 | 0 | TK_Complete
SI1PCB4B27 | TT_Task | TRANSPORT SERVICE COOLING WATER PUMP PCB | 26/01/2018 | 15/03/2018 | 31/01/2018 | 14/03/2018 | 0 | TK_Complete
SI1PDB2-60 | TT_FinMile | (DF) FINAL INPUT FOR MS3 CONCRETE DEBRIS FILTER PDB | 31/05/2017 | 31/05/2017 | 12/05/2017 | 12/05/2017 | 0 | TK_Complete
SI1PDB2-65 | TT_FinMile | (DF) FINAL INPUT FOR M2 DEBRIS FILTER PDB | 31/05/2017 | 31/05/2017 | 12/05/2017 | 12/05/2017 | 0 | TK_Complete
SI1PDB2-75 | TT_Task | PREPARATION RFQ DEBRIS FILTER PDB | 10/12/2016 | 30/12/2016 | 09/12/2016 | 29/12/2016 | 0 | TK_Complete
SI1PDB2-80 | TT_Task | QUOTATION STAGE DEBRIS FILTER PDB | 03/02/2017 | 09/03/2017 | 30/12/2016 | 21/04/2017 | 0 | TK_Complete
SI1PDB2-85 | TT_Mile | ORDER PLACED DEBRIS FILTER PDB | 15/05/2017 | 15/05/2017 | 22/04/2017 | 22/04/2017 | 0 | TK_Complete
SI1PDB2A60 | TT_FinMile | (DF) FINAL INPUT FOR MS3 STEEL DEBRIS FILTER PDB | 31/05/2017 | 31/05/2017 | 19/05/2017 | 19/05/2017 | 0 | TK_Complete
SI1PDB3-25 | TT_Task | DETAIL DESIGN, MANUFACTURING DEBRIS FILTER PDB | 15/05/2017 | 04/02/2018 | 23/04/2017 | 04/01/2018 | 0 | TK_Complete
SI1PDB3-80 | TT_FinMile | (RFS) READY FOR SHIPMENT DEBRIS FILTER PDB | 14/02/2018 | 14/02/2018 | 04/01/2018 | 04/01/2018 | 0 | TK_Complete
SI1PDB4-27 | TT_Task | TRANSPORT DEBRIS FILTER PDB | 15/02/2018 | 28/03/2018 | 08/02/2018 | 20/03/2018 | 0 | TK_Complete
SI1PGB2B60 | TT_FinMile | (DF) FINAL INPUT FOR MS3 CCW PUMP PGB | 31/03/2017 | 31/03/2017 | 27/03/2017 | 27/03/2017 | 0 | TK_Complete
SI1PGB2B65 | TT_FinMile | (DF) FINAL INPUT FOR M2 CCW PUMP PGB | 31/03/2017 | 31/03/2017 | 27/03/2017 | 27/03/2017 | 0 | TK_Complete
SI1PGB2B75 | TT_Task | CONTRACT REVIEW, PREPARATION RFQ CCW PUMP PGB | 26/11/2016 | 30/12/2016 | 24/11/2016 | 28/12/2016 | 0 | TK_Complete
SI1PGB2B80 | TT_Task | QUOTATION STAGE CCW PUMP PGB | 02/02/2017 | 05/04/2017 | 29/12/2016 | 02/03/2017 | 0 | TK_Complete
SI1PGB2B85 | TT_Mile | ORDER PLACED CCW PUMP PGB | 17/03/2017 | 17/03/2017 | 03/03/2017 | 03/03/2017 | 0 | TK_Complete
SI1PGB3B25 | TT_Task | DETAIL DESIGN, MANUFACTURING, SHOP TEST CCW PUMP PGB | 17/03/2017 | 12/12/2017 | 04/03/2017 | 06/12/2017 | 0 | TK_Complete
SI1PGB3B80 | TT_FinMile | (RFS) READY FOR SHIPMENT CCW PUMP PGB | 26/01/2018 | 26/01/2018 | 15/12/2017 | 15/12/2017 | 0 | TK_Complete
SI1PGB4B27 | TT_Task | TRANSPORT CCW PUMP PGB | 26/01/2018 | 15/03/2018 | 31/01/2018 | 13/03/2018 | 0 | TK_Complete
SI1PGB2C60 | TT_FinMile | (DF) FINAL INPUT FOR MS3 HEAT EXCHANGER PGB | 03/06/2017 | 03/06/2017 | 31/05/2017 | 31/05/2017 | 0 | TK_Complete
SI1PGB2C65 | TT_FinMile | (DF) FINAL INPUT FOR M2 HEAT EXCHANGER PGB | 25/06/2017 | 25/06/2017 | 13/06/2017 | 13/06/2017 | 0 | TK_Complete
SI1PGB2C75 | TT_Task | PREPARATION RFQ HEAT EXCHANGER PGB | 01/02/2017 | 28/02/2017 | 19/01/2017 | 15/03/2017 | 0 | TK_Complete
SI1PGB2C80 | TT_Task | QUOTATION STAGE HEAT EXCHANGER PGB | 01/04/2017 | 26/04/2017 | 16/03/2017 | 16/05/2017 | 0 | TK_Complete
SI1PGB2C85 | TT_Mile | ORDER PLACED HEAT EXCHANGER PGB | 02/06/2017 | 02/06/2017 | 17/05/2017 | 17/05/2017 | 0 | TK_Complete
SI1PGB3C25 | TT_Task | FABRICATION DESIGN, PROCUREMENT, PRE-FABRICATION HEAT EXCHANGER PGB | 02/06/2017 | 18/12/2017 | 18/05/2017 | 15/12/2017 | 0 | TK_Complete
SI1PGB3C80 | TT_FinMile | (RFS) READY FOR SHIPMENT HEAT EXCHANGER PGB | 15/12/2017 | 15/12/2017 | 15/12/2017 | 15/12/2017 | 0 | TK_Complete
SI1PGB4C27 | TT_Task | TRANSPORT HEAT EXCHANGER PGB | 26/01/2018 | 15/03/2018 | 31/01/2018 | 13/03/2018 | 0 | TK_Complete
SI1PGB2D60 | TT_FinMile | (DF) FINAL INPUT FOR MS3 EXPANSION TANK PGB | 25/08/2017 | 25/08/2017 | 29/07/2017 | 29/07/2017 | 0 | TK_Complete
SI1PGB2D65 | TT_FinMile | (DF) FINAL INPUT FOR M2 EXPANSION TANK PGB | 25/08/2017 | 25/08/2017 | 08/08/2017 | 08/08/2017 | 0 | TK_Complete
SI1PGB2D75 | TT_Task | PREPARATION RFQ EXPANSION TANK PGB | 01/02/2017 | 28/02/2017 | 23/01/2017 | 15/03/2017 | 0 | TK_Complete
SI1PGB2D80 | TT_Task | QUOTATION STAGE EXPANSION TANK PGB | 01/04/2017 | 26/04/2017 | 16/03/2017 | 11/07/2017 | 0 | TK_Complete
SI1PGB2D85 | TT_Mile | ORDER PLACED EXPANSION TANK PGB | 26/07/2017 | 26/07/2017 | 12/07/2017 | 12/07/2017 | 0 | TK_Complete
SI1PGB3D25 | TT_Task | FABRICATION DESIGN, PROCUREMENT, PRE-FABRICATION EXPANSION TANK PGB | 26/07/2017 | 23/01/2018 | 12/07/2017 | 15/12/2017 | 0 | TK_Complete
SI1PGB3D80 | TT_FinMile | (RFS) READY FOR SHIPMENT EXPANSION TANK PGB | 26/01/2018 | 26/01/2018 | 04/12/2017 | 04/12/2017 | 0 | TK_Complete
SI1PGB4D27 | TT_Task | TRANSPORT EXPANSION TANK PGB | 26/01/2018 | 15/03/2018 | 08/02/2018 | 20/03/2018 | 0 | TK_Complete
SI1PXB2-10 | TT_Task | DETAIL DESIGN PXB00Y MODULE | 13/06/2017 | 21/11/2017 | 13/05/2017 | 09/10/2017 | 0 | TK_Complete
SI1PXB2N60 | TT_FinMile | (MS3) PXB00Y MODULE FINAL DIMENSIONS AND LOADS AVAILABLE | 14/07/2017 | 14/07/2017 | 19/06/2017 | 19/06/2017 | 0 | TK_Complete
SI1PXB3-10 | TT_Task | DELIVERY OF SKID FRAME STEEL, PIPING MATERIAL PXB00Y MODULE | 09/11/2017 | 12/02/2018 | 10/10/2017 | 13/01/2018 | 0 | TK_Complete
SI1PXB3-20 | TT_FinMile | DELIVERY OF COMPONENTS PXB00Y MODULE | 18/03/2018 | 18/03/2018 | 15/02/2018 | 15/02/2018 | 0 | TK_Complete
SI1PXB3-25 | TT_Task | MANUFACTURING PXB00Y MODULE | 26/01/2018 | 08/04/2018 | 14/01/2018 | 31/05/2018 | 0 | TK_Complete
SI1PXB4-25 | TT_Task | TRANSPORT PXB00Y MODULE | 15/05/2018 | 30/05/2018 | 18/06/2018 | 25/06/2018 | 0 | TK_Complete
SI1PXB4-42 | TT_FinMile | (OTD-OS) ON SITE PXB00Y MODULE | 30/05/2018 | 30/05/2018 | 25/06/2018 | 25/06/2018 | 0 | TK_Complete
SI1CJT4-27 | TT_Task | TRANSPORT TO SITE SFC/SEE CUBICLE CJT | 26/03/2018 | 08/05/2018 | 18/03/2018 | 13/05/2018 | 0 | TK_Complete
SI1SCA3-80 | TT_FinMile | (RFS) READY FOR SHIPMENT COMPRESSOR MAIN BODY SCA | 13/07/2018 | 13/07/2018 | 28/09/2018 | 28/09/2018 | 0 | TK_Complete
SI1SCA3-82 | TT_FinMile | (RFS) READY FOR SHIPMENT RECEIVER TANKS SCA | 31/08/2018 | 31/08/2018 | 28/09/2018 | 28/09/2018 | 0 | TK_Complete
SI1SCA4-25 | TT_Task | TRANSPORT COMPRESSOR MAIN BODY SCA | 14/07/2018 | 11/09/2018 | 24/11/2018 | 02/01/2019 | 0 | TK_Complete
SI1SCA4-42 | TT_Task | TRANSPORT RECEIVER TANKS SCA | 01/09/2018 | 30/10/2018 | 24/11/2018 | 02/01/2019 | 0 | TK_Complete
SI1SCA4-44 | TT_FinMile | (OTD-OS) ON SITE RECEIVER TANKS SCA | 30/10/2018 | 30/10/2018 | 02/01/2019 | 02/01/2019 | 0 | TK_Complete
SI1SCA4-46 | TT_FinMile | (OTD-OS) ON SITE COMPRESSOR MAIN BODY SCA | 11/09/2018 | 11/09/2018 | 02/01/2019 | 02/01/2019 | 0 | TK_Complete
SI1UBA2-60 | TT_FinMile | (MS3) CONCRETE STRUCTURE FINAL DIMENSIONS LOADS AVAILABLE 10UBA BUILDING or 10UBD | 12/12/2021 | 12/12/2021 | 16/02/2017 | 16/02/2017 | 0 | TK_Complete
SI1UBA2-77 | TT_Task | PREPARATION BASIC BUILDING DWGS UBA BUILDING | 14/02/2017 | 20/03/2017 | 03/02/2017 | 22/02/2017 | 0 | TK_Complete
SI1UBA2B60 | TT_FinMile | (MS3) STEEL STRUCTURE, FINAL DIMENSIONS AND LOADS AVAILABLE 10UBA BUILDING or 10UBD | 25/08/2017 | 25/08/2017 | 11/08/2017 | 11/08/2017 | 0 | TK_Complete
SI1BZP2C30 | TT_Task | DETAIL DESIGN CABLE SUPPORT SYSTEM UBA/UBD | 01/03/2017 | 23/05/2017 | 21/02/2017 | 30/04/2017 | 0 | TK_Complete
SI1BBA3-25 | TT_Task | MANUFACTURING, SHOP TEST MV-SWITCHGEAR BBA | 02/09/2017 | 23/02/2018 | 01/08/2017 | 30/03/2018 | 0 | TK_Complete
SI1BBA3-80 | TT_FinMile | (RFS) READY FOR SHIPMENT MV-SWITCHGEAR BBA | 01/04/2018 | 01/04/2018 | 12/04/2018 | 12/04/2018 | 0 | TK_Complete
SI1BBA4-12 | TT_Task | TRANSPORT TO SITE MV-SWITCHGEAR BBA | 02/04/2018 | 30/04/2018 | 17/06/2018 | 23/07/2018 | 0 | TK_Complete
SI1BFA3-25 | TT_Task | MANUFACTURING, SHOP TEST LV-/DC-SWITCHGEAR BFA | 30/10/2017 | 25/02/2018 | 30/09/2017 | 25/06/2018 | 0 | TK_Complete
SI1BFA3-80 | TT_FinMile | (RFS) READY FOR SHIPMENT LV-/DC-SWITCHGEAR BFA | 16/05/2018 | 16/05/2018 | 27/06/2018 | 27/06/2018 | 0 | TK_Complete
SI1BFA4-12 | TT_Task | TRANSPORT TO SITE LV-/DC-SWITCHGEAR BFA | 17/05/2018 | 15/07/2018 | 14/08/2018 | 20/09/2018 | 0 | TK_Complete
SI1UBA3G58 | TT_Mile | CABINET AT WORKSHOP FOR SHOP TEST CABINET 10UBA BUILDING | 26/02/2018 | 26/02/2018 | 23/01/2018 | 23/01/2018 | 0 | TK_Complete
SI1UBA3G60 | TT_Task | PREPARATION, SHOP TEST, DISMANTLING CABINET 10UBA BUILDING | 26/03/2018 | 03/06/2018 | 03/03/2018 | 30/06/2018 | 0 | TK_Complete
SI1UBA3G80 | TT_FinMile | (RFS) READY FOR SHIPMENT CABINET 10UBA BUILDING | 05/06/2018 | 05/06/2018 | 25/07/2018 | 25/07/2018 | 0 | TK_Complete
SI1UBA4G27 | TT_Task | TRANSPORT TO SITE CABINET 10UBA BUILDING | 06/06/2018 | 04/08/2018 | 25/07/2018 | 25/08/2018 | 0 | TK_Complete
SI1CHA3-25 | TT_Task | MANUFACTURING, SHOP TEST PROT./SYNCHR./METERING CHA | 26/08/2017 | 05/03/2018 | 15/08/2017 | 13/04/2018 | 0 | TK_Complete
SI1CHA3-80 | TT_FinMile | (RFS) READY FOR SHIPMENT PROT./SYNCHR./METERING CHA | 26/04/2018 | 26/04/2018 | 25/04/2018 | 25/04/2018 | 0 | TK_Complete
SI1CHA4-12 | TT_Task | TRANSPORT TO SITE PROT., SYNCHR., METERING CHA | 27/04/2018 | 07/06/2018 | 27/05/2018 | 30/06/2018 | 0 | TK_Complete
SI1MBJ4-25 | TT_Task | TRANSPORT TO SITE SFC TRANSFORMER MBJ | 01/03/2018 | 09/05/2018 | 18/01/2018 | 01/04/2018 | 0 | TK_Complete
SI1MBJ4-27 | TT_Task | PREPARATION FOR DISPATCH TO SITE SEE/SFC TRANSFORMER MBJ | 26/01/2018 | 11/03/2018 | 15/12/2017 | 15/01/2018 | 0 | TK_Complete
SI1MKC4-27 | TT_Task | TRANSPORT TO SITE SEE TRANSFORMER MKC | 26/03/2018 | 26/04/2018 | 23/03/2018 | 01/05/2018 | 0 | TK_Complete
SP1MKC2-80 | TT_Task | ORDERING / NEGOTIATIONS SEE/SFC TRANSFORMER MKC / MBJ | 14/02/2017 | 01/03/2017 | 01/02/2017 | 01/03/2017 | 0 | TK_Complete
SP1MKC2-85 | TT_Mile | ORDER PLACED SEE/SFC TRANSFORMER MKC / MBJ | 17/03/2017 | 17/03/2017 | 02/03/2017 | 02/03/2017 | 0 | TK_Complete
SP1MKC3-25 | TT_Task | MANUFACTURING SEE/SFC TRANSFORMER MKC / MBJ | 17/03/2017 | 22/12/2017 | 02/03/2017 | 12/12/2017 | 0 | TK_Complete
SP1MKC3-65 | TT_Task | FINAL CHECK &amp; DISPATCH SEE/SFC TRANSFORMER MKC / MBJ | 16/12/2017 | 22/12/2017 | 13/12/2017 | 19/12/2017 | 0 | TK_Complete
SP1MKC3-80 | TT_Mile | DELIVERY SEE/SFC TRANSFORMER GT MKC / MBJ EX WORKS | 30/01/2018 | 30/01/2018 | 20/12/2017 | 20/12/2017 | 0 | TK_Complete
SI1UBD2-45 | TT_Task | PREPARATION BASIC BUILDING DWGS UBD01/02/03/04 | 01/06/2017 | 05/07/2017 | 10/05/2017 | 09/06/2017 | 0 | TK_Complete
SI1UBD2-60 | TT_FinMile | (MS3) CONCRETE STRUCTURE FINAL DIMENSIONS LOADS AVAILABLE UBD01/02/03/04 | 31/05/2017 | 31/05/2017 | 23/05/2017 | 23/05/2017 | 0 | TK_Complete
SI1UBD2-70 | TT_Task | DETAIL DESIGN / CHECKER CONCRETE STRUCTURE UBD01/02/03/04 | 09/07/2017 | 10/09/2017 | 10/06/2017 | 30/06/2017 | 0 | TK_Complete
SI1UBD3-70 | TT_Task | FABRICATION DESIGN, FABRICATION, TRANSPORT, ON SITE STEEL PLATFORM UBD | 26/01/2018 | 07/05/2018 | 29/12/2017 | 27/06/2018 | 0 | TK_Complete
SI1UBF2-45 | TT_Task | PREPARATION BASIC BUILDING DWGS UBF/UBE | 01/06/2017 | 05/07/2017 | 04/05/2017 | 24/05/2017 | 0 | TK_Complete
SI1UBF2-60 | TT_FinMile | (MS3) CONCRETE STRUCTURE FINAL DIMENSIONS LOADS AVAILABLE UBF/UBE | 15/06/2017 | 15/06/2017 | 17/05/2017 | 17/05/2017 | 0 | TK_Complete
SI1UBF2B60 | TT_FinMile | (MS3) STEEL STRUCTURE, FINAL DIMENSIONS AND LOADS AVAILABLE UBF/UBE | 25/07/2017 | 25/07/2017 | 18/07/2017 | 18/07/2017 | 0 | TK_Complete
SI1UBF2B70 | TT_Task | DETAIL DESIGN / CHECKER STEEL STRUCTURE UBF/UBE | 25/07/2017 | 18/09/2017 | 19/07/2017 | 09/10/2017 | 0 | TK_Complete
SI1UBF3B70 | TT_Task | FABRICATION DESIGN, FABRICATION, TRANSPORT, ON SITE STEEL PLATFORM UBF | 26/01/2018 | 07/05/2018 | 29/12/2017 | 27/06/2018 | 0 | TK_Complete
SI1UBL2-45 | TT_Task | PREPARATION BASIC BUILDING DWGS UBL | 26/06/2017 | 30/07/2017 | 01/05/2017 | 24/05/2017 | 0 | TK_Complete
SI1UBL2-60 | TT_FinMile | (MS3) CONCRETE STRUCTURE FINAL DIMENSIONS LOADS AVAILABLE UBL | 25/06/2017 | 25/06/2017 | 15/05/2017 | 15/05/2017 | 0 | TK_Complete
SI1UBL3-60 | TT_Task | FABRICATION DESIGN, FABRICATION, TRANSPORT, ON SITE STEEL PLATFORM UBL | 26/01/2018 | 27/05/2018 | 29/12/2017 | 27/06/2018 | 0 | TK_Complete
SI1BAA3-25 | TT_Task | MANUFACTURING, SHOP TEST IPB BAA | 01/09/2017 | 01/03/2018 | 31/07/2017 | 27/02/2018 | 0 | TK_Complete
SI1BAA3-80 | TT_FinMile | (RFS) READY FOR SHIPMENT IPB BAA | 27/03/2018 | 27/03/2018 | 27/02/2018 | 27/02/2018 | 0 | TK_Complete
SI1BAA4-27 | TT_Task | TRANSPORT IPB BAA | 26/08/2020 | 05/10/2020 | 07/05/2018 | 20/06/2018 | 0 | TK_Complete
SI1BAT3-25 | TT_Task | MANUFACTURING, SHOP TEST MAIN TRANSFORMER BAT | 01/02/2017 | 27/12/2017 | 24/01/2017 | 02/03/2018 | 0 | TK_Complete
SI1BAT3-80 | TT_FinMile | (RFS) READY FOR SHIPMENT MAIN TRANSFORMER BAT | 26/08/2020 | 26/08/2020 | 30/04/2018 | 30/04/2018 | 0 | TK_Complete
SI1BAT4-27 | TT_Task | TRANSPORT MAIN TRANSFORMER BAT | 02/05/2018 | 16/05/2018 | 03/05/2018 | 05/05/2018 | 0 | TK_Complete
SI1BBT3-25 | TT_Task | MANUFACTURING, SHOP TEST AUXILIARY TRANSFORMER BBT | 01/02/2017 | 27/12/2017 | 24/01/2017 | 27/12/2017 | 0 | TK_Complete
SI1BBT3-80 | TT_FinMile | (RFS) READY FOR SHIPMENT AUXILIARY TRANSFORMER BBT | 13/02/2018 | 13/02/2018 | 03/01/2018 | 03/01/2018 | 0 | TK_Complete
SI1BBT4-27 | TT_Task | TRANSPORT AUXILIARY TRANSFORMER BBT | 26/02/2018 | 28/02/2018 | 31/01/2018 | 03/02/2018 | 0 | TK_Complete
SI1BZP2I30 | TT_Task | DETAIL DESIGN CABLE SUPPORT SYSTEM UBE/UBF | 01/07/2017 | 11/08/2017 | 08/06/2017 | 28/08/2017 | 0 | TK_Complete
SI1ULD2-45 | TT_Task | PREPARATION BASIC BUILDING DWGS ULD | 12/04/2017 | 16/05/2017 | 27/03/2017 | 25/04/2017 | 0 | TK_Complete
SI1ULD2-60 | TT_FinMile | (MS3) CONCRETE STRUCTURE FINAL DIMENSIONS LOADS AVAILABLE ULD | 15/05/2017 | 15/05/2017 | 18/04/2017 | 18/04/2017 | 0 | TK_Complete
SI1ULD2E75 | TT_Mile | (F) DETAIL DESIGN STEEL PLATFORM ULD DWGS WITH CONTRACTOR | 26/11/2017 | 26/11/2017 | 31/10/2017 | 31/10/2017 | 0 | TK_Complete
SI1LD-3-25 | TT_Task | DESIGN, MANUFACTURING, SHOP TEST CONDENSATE POLISHING PLANT LD | 16/03/2017 | 12/01/2018 | 01/03/2017 | 20/07/2018 | 0 | TK_Complete
SI1LD-3-80 | TT_FinMile | (RFS) READY FOR SHIPMENT CONDENSATE POLISHING PLANT LD | 06/06/2018 | 06/06/2018 | 21/09/2018 | 21/09/2018 | 0 | TK_Complete
SI1LD-4-25 | TT_Task | TRANSPORT CONDENSATE POLISHING PLANT LD | 07/06/2018 | 25/07/2018 | 02/10/2018 | 06/11/2018 | 0 | TK_Complete
SI1LD-4-42 | TT_FinMile | (OTD-OS) ON SITE CONDENSATE POLISHING PLANT LD | 25/07/2018 | 25/07/2018 | 06/11/2018 | 06/11/2018 | 0 | TK_Complete
SI1LDK3B25 | TT_Task | DETAIL DESIGN, MANUFACTURING, SHOP TEST CONDENSATE POLISHING PUMP LDK | 15/06/2017 | 10/04/2018 | 20/05/2017 | 15/12/2017 | 0 | TK_Complete
SI1LDK3B80 | TT_FinMile | (RFS) READY FOR SHIPMENT CONDENSATE POLISHING PUMP LDK | 26/01/2018 | 26/01/2018 | 02/01/2018 | 02/01/2018 | 0 | TK_Complete
SI1LDK4B25 | TT_Task | TRANSPORT CONDENSATE POLISHING PUMP LDK | 26/02/2018 | 17/04/2018 | 25/02/2018 | 06/04/2018 | 0 | TK_Complete
SI1LDK4B42 | TT_FinMile | (OTD-OS) ON SITE CONDENSATE POLISHING PUMP LDK | 31/05/2018 | 31/05/2018 | 06/04/2018 | 06/04/2018 | 0 | TK_Complete
SI1UEZ2-45 | TT_Task | PREPARATION BASIC BUILDING DWGS UEZ01/02 | 26/06/2017 | 30/07/2017 | 17/06/2017 | 07/08/2017 | 0 | TK_Complete
SI1UEZ2-60 | TT_FinMile | (MS3) CONCRETE STRUCTURE FINAL DIMENSIONS LOADS AVAILABLE UEZ01/02 | 25/07/2017 | 25/07/2017 | 10/07/2017 | 10/07/2017 | 0 | TK_Complete
SI1UEZ2-70 | TT_Task | DETAIL DESIGN / CHECKER CONCRETE STRUCTURE UEZ01/02 | 05/09/2017 | 06/11/2017 | 08/08/2017 | 04/11/2017 | 0 | TK_Complete
SI1BAC2-75 | TT_Mile | RFQ GENERATOR CIRCUIT BREAKER BAC | 08/05/2017 | 08/05/2017 | 08/04/2017 | 08/04/2017 | 0 | TK_Complete
SI1BAC2-80 | TT_Task | QUOTATION STAGE GENERATOR CIRCUIT BREAKER BAC | 08/05/2017 | 04/06/2017 | 08/04/2017 | 05/05/2017 | 0 | TK_Complete
SI1BAC2-85 | TT_Mile | ORDER PLACED GENERATOR CIRCUIT BREAKER BAC | 01/06/2017 | 01/06/2017 | 06/05/2017 | 06/05/2017 | 0 | TK_Complete
SI1BAC3-25 | TT_Task | MANUFACTURING, SHOP TEST GENERATOR CIRCUIT BREAKER BAC | 01/06/2017 | 13/03/2018 | 06/05/2017 | 20/12/2017 | 0 | TK_Complete
SI1BAC3-80 | TT_FinMile | (RFS) READY FOR SHIPMENT GENERATOR .CIRCUIT BREAKER BAC | 28/03/2018 | 28/03/2018 | 20/12/2017 | 20/12/2017 | 0 | TK_Complete
SI1BAC4-27 | TT_Task | TRANSPORT GENERATOR CIRCUIT BREAKER BAC | 05/02/2018 | 06/03/2018 | 05/02/2018 | 16/03/2018 | 0 | TK_Complete
SI0UBN2-45 | TT_Task | PREPARATION BASIC BUILDING DWGS UBN | 01/06/2017 | 05/07/2017 | 10/05/2017 | 25/07/2017 | 0 | TK_Complete
SI0UBN2-60 | TT_FinMile | (MS3) CONCRETE STRUCTURE FINAL DIMENSIONS LOADS AVAILABLE UBN | 31/05/2017 | 31/05/2017 | 23/05/2017 | 23/05/2017 | 0 | TK_Complete
SI0XKA2-15 | TT_Task | BASIC DESIGN, SPECIFICATION EMERGENCY DIESEL GENERATOR SET XKA | 01/06/2017 | 28/06/2017 | 16/05/2017 | 12/06/2017 | 0 | TK_Complete
SI0XKA2-75 | TT_Mile | RFQ EMERGENCY DIESEL GENERATOR SET XKA | 26/06/2017 | 26/06/2017 | 13/06/2017 | 13/06/2017 | 0 | TK_Complete
SI0XKA2-80 | TT_Task | QUOTATION STAGE EMERGENCY DIESEL GENERATOR SET XKA | 08/07/2017 | 04/08/2017 | 13/06/2017 | 31/07/2017 | 0 | TK_Complete
SI0XKA2-85 | TT_Mile | ORDER PLACED EMERGENCY DIESEL GENERATOR SET XKA | 02/09/2017 | 02/09/2017 | 01/08/2017 | 01/08/2017 | 0 | TK_Complete
SI0XKA3-25 | TT_Task | MANUFACTURING, SHOP TEST EMERGENCY DIESEL GENERATOR SET XKA | 02/09/2017 | 18/05/2018 | 01/08/2017 | 31/05/2018 | 0 | TK_Complete
SI0XKA3-80 | TT_FinMile | (RFS) READY FOR SHIPMENT EMERGENCY DIESEL GENERATOR SET XKA | 23/05/2018 | 23/05/2018 | 25/09/2018 | 25/09/2018 | 0 | TK_Complete
SI0XKA4-27 | TT_Task | TRANSPORT EMERGENCY DIESEL GENERATOR .SET XKA | 24/05/2018 | 22/07/2018 | 15/10/2018 | 17/11/2018 | 0 | TK_Complete
SI0BZP2H30 | TT_Task | DETAIL DESIGN CABLE SUPPORT SYSTEM UBN | 25/07/2017 | 04/09/2017 | 01/07/2017 | 24/08/2017 | 0 | TK_Complete
SI1BFT3-25 | TT_Task | MANUFACTURING, SHOP TEST LV-TRANSFORMERS BFT | 25/07/2017 | 22/01/2018 | 20/07/2017 | 21/02/2018 | 0 | TK_Complete
SI1BFT3-80 | TT_FinMile | (RFS) READY FOR SHIPMENT LV-TRANSFORMERS BFT | 24/03/2018 | 24/03/2018 | 21/02/2018 | 21/02/2018 | 0 | TK_Complete
SI1BFT4-27 | TT_Task | TRANSPORT LV-TRANSFORMERS BFT | 25/03/2018 | 23/05/2018 | 08/04/2018 | 15/05/2018 | 0 | TK_Complete
SI0UBH2-60 | TT_FinMile | (MS3) CONCRETE STRUCTURE FINAL DIMENSIONS LOADS AVAILABLE UBH01 | 31/05/2017 | 31/05/2017 | 17/05/2017 | 17/05/2017 | 0 | TK_Complete
SI1UMX2-45 | TT_Task | PREPARATION BASIC BUILDING DWGS UMX | 01/05/2017 | 04/06/2017 | 08/04/2017 | 12/05/2017 | 0 | TK_Complete
SI1UMX2-60 | TT_FinMile | (MS3) CONCRETE STRUCTURE FINAL DIMENSIONS LOADS AVAILABLE UMX | 30/04/2017 | 30/04/2017 | 21/04/2017 | 21/04/2017 | 0 | TK_Complete
SI1MBR4-25 | TT_Task | TRANSPORT DIFFUSER MBR | 26/03/2018 | 27/03/2018 | 28/02/2018 | 02/03/2018 | 0 | TK_Complete
SI1MBR4-44 | TT_FinMile | (OTD-OS) ON SITE EXHAUST GAS SYSTEM TURBINE EXHAUST MANIFOLD MBR | 26/03/2018 | 26/03/2018 | 10/03/2018 | 10/03/2018 | 0 | TK_Complete
SI1MBR4-46 | TT_FinMile | (OTD-OS) ON SITE EXHAUST GAS SYSTEM DIFFUSER MBR | 26/03/2018 | 26/03/2018 | 02/03/2018 | 02/03/2018 | 0 | TK_Complete
SI1MBR4A42 | TT_Task | TRANSPORT TURBINE EXHAUST MANIFOLD MBR | 26/03/2018 | 01/04/2018 | 02/03/2018 | 10/03/2018 | 0 | TK_Complete
SP1MBR3-25 | TT_Task | DETAIL DESIGN / MANUFACTURING DIFFUSER MBR | 16/03/2017 | 06/12/2017 | 10/03/2017 | 30/11/2017 | 0 | TK_Complete
SP1MBR3-80 | TT_Mile | DELIVERY DIFFUSER MBR EX WORKS | 26/01/2018 | 26/01/2018 | 15/12/2017 | 15/12/2017 | 0 | TK_Complete
SP1MBR3A25 | TT_Task | DETAIL DESIGN / MANUFACTURING TURBINE EXHAUST MANIFOLD MBR | 09/04/2017 | 30/12/2017 | 24/03/2017 | 14/12/2017 | 0 | TK_Complete
SP1MBR3A80 | TT_Mile | DELIVERY TURBINE EXHAUST MANIFOLD MBR EX WORKS | 26/01/2018 | 26/01/2018 | 15/12/2017 | 15/12/2017 | 0 | TK_Complete
SP1MBR4-15 | TT_Task | TRANSPORT DIFFUSER MBR TO PORT OF EXPORT | 26/01/2018 | 08/02/2018 | 15/12/2017 | 28/12/2017 | 0 | TK_Complete
SP1MBR4A15 | TT_Task | TRANSPORT TURBINE EXHAUST MANIFOLD MBR TO PORT OF EXPORT | 26/01/2018 | 08/02/2018 | 15/12/2017 | 28/12/2017 | 0 | TK_Complete
SI1USX2-60 | TT_Mile | (MS3) CONCRETE STRUCTURE FINAL DIMENSIONS LOADS AVAILABLE USX | 26/11/2017 | 26/11/2017 | 23/11/2017 | 23/11/2017 | 0 | TK_Complete
SI1UEN2-45 | TT_Task | PREPARATION BASIC BUILDING DWGS 10UEN | 26/06/2017 | 30/07/2017 | 17/06/2017 | 30/06/2017 | 0 | TK_Complete
SI1UEN2-60 | TT_FinMile | (MS3) CONCRETE STRUCTURE FINAL DIMENSIONS LOADS AVAILABLE 10UEN | 25/07/2017 | 25/07/2017 | 25/06/2017 | 25/06/2017 | 0 | TK_Complete
SI1BZP2F30 | TT_Task | DETAIL DESIGN CABLE SUPPORT SYSTEM 10UEN | 25/07/2017 | 04/09/2017 | 22/07/2017 | 01/09/2017 | 0 | TK_Complete
SI-EK-2-04 | TT_Mile | P&amp;IDs INPUT AGREED WITH BOP-PIPING GAS SYSTEM EK/EKC | 01/02/2017 | 01/02/2017 | 21/01/2017 | 21/01/2017 | 0 | TK_Complete
SI-EK-2-60 | TT_FinMile | (DF) FINAL INPUT FOR MS3 FUEL GAS SUPPLY SYSTEM EK/EKC | 25/06/2017 | 25/06/2017 | 09/06/2017 | 09/06/2017 | 0 | TK_Complete
SI-EK-2-65 | TT_FinMile | (DF) FINAL INPUT FOR M2 GAS SYSTEM EK/EKC | 31/05/2017 | 31/05/2017 | 28/04/2017 | 28/04/2017 | 0 | TK_Complete
SI-EK-2-80 | TT_Task | QUOTATION STAGE FUEL GAS SUPPLY SYSTEM EK/EKC | 01/02/2017 | 28/03/2017 | 21/01/2017 | 27/04/2017 | 0 | TK_Complete
SI-EK-2-85 | TT_Mile | ORDER PLACED FUEL GAS SUPPLY SYSTEM EK/EKC | 14/05/2017 | 14/05/2017 | 28/04/2017 | 28/04/2017 | 0 | TK_Complete
SI-EK-3-25 | TT_Task | DETAIL DESIGN, MANUFACTURING FUEL GAS SUPPLY SYSTEM EK/EKC | 01/05/2017 | 25/10/2017 | 28/04/2017 | 24/12/2017 | 0 | TK_Complete
SI-EK-3-55 | TT_Task | PRE ERECTION GAS SYSTEM/ PREHEATER EK/EKC | 16/02/2018 | 02/07/2018 | 06/01/2018 | 29/03/2018 | 0 | TK_Complete
SI-EK-3-80 | TT_FinMile | (RFS) READY FOR SHIPMENT GAS SYSTEM EK/EKC | 05/05/2018 | 05/05/2018 | 29/03/2018 | 29/03/2018 | 0 | TK_Complete
SI-EK-4-25 | TT_Task | TRANSPORT FUEL GAS SUPPLY SYSTEM EK/EKC | 06/05/2018 | 04/07/2018 | 22/04/2018 | 29/05/2018 | 0 | TK_Complete
SI-EK-4-46 | TT_FinMile | (OTD-OS) ON SITE FUEL GAS SUPPLY SYSTEM EK/EKC | 04/07/2018 | 04/07/2018 | 29/05/2018 | 29/05/2018 | 0 | TK_Complete
SI1UHA2-45 | TT_Task | PREPARATION BASIC BUILDING DWGS UHA | 15/02/2017 | 21/03/2017 | 02/02/2017 | 03/03/2017 | 0 | TK_Complete
SI1UHA2-60 | TT_FinMile | (MS3) CONCRETE STRUCTURE FINAL DIMENSIONS LOADS AVAILABLE UHA | 02/03/2017 | 02/03/2017 | 15/02/2017 | 15/02/2017 | 0 | TK_Complete
SI1HA-2-00 | TT_Mile | PRELIMINARY ERECTION CONCEPT HRSG | 01/04/2017 | 01/04/2017 | 18/03/2017 | 18/03/2017 | 0 | TK_Complete
SI1HA-2-01 | TT_Mile | FINAL ERECTION CONCEPT HRSG | 01/06/2017 | 01/06/2017 | 13/05/2017 | 13/05/2017 | 0 | TK_Complete
SI1HA-2-10 | TT_Task | TECHNICAL CLARIFICATION WITH HRSG SUPPLIER | 05/11/2016 | 24/11/2016 | 10/09/2016 | 30/09/2016 | 0 | TK_Complete
SI1HA-2-72 | TT_Task | PROJECT SPECIFIC ADAPTION OF HRSG SPECIFICATION | 02/07/2016 | 28/07/2016 | 09/07/2016 | 05/08/2016 | 0 | TK_Complete
SI1HA-2-73 | TT_FinMile | COATING INSTRUCTION | 28/10/2016 | 28/10/2016 | 02/09/2016 | 02/09/2016 | 0 | TK_Complete
SI1HA-2-77 | TT_Task | OFFER PREPARATION BY HRSG SUPPLIER | 01/10/2016 | 03/11/2016 | 06/08/2016 | 09/09/2016 | 0 | TK_Complete
SI1HA-2-78 | TT_Mile | HRSG OFFER AVAILABLE | 05/11/2016 | 05/11/2016 | 10/09/2016 | 10/09/2016 | 0 | TK_Complete
SI1HA-2-85 | TT_Mile | PARTIAL ORDER PLACED HRSG | 03/11/2016 | 03/11/2016 | 03/11/2016 | 03/11/2016 | 0 | TK_Complete
SI1HA-2-87 | TT_Mile | ORDER PLACED HRSG | 14/01/2017 | 14/01/2017 | 19/12/2016 | 19/12/2016 | 0 | TK_Complete
SI1HA-2A05 | TT_Mile | GENERAL ARRANGMENT DWGS PRELIMINARY UHA | 03/11/2016 | 03/11/2016 | 03/11/2016 | 03/11/2016 | 0 | TK_Complete
SI1HA-2A15 | TT_FinMile | (MH3) FINAL DIMENSIONS AND LOADS AVAILABLE FOR HRSG | 14/02/2017 | 14/02/2017 | 31/01/2017 | 31/01/2017 | 0 | TK_Complete
SI1HA-2A60 | TT_FinMile | (DF) FINAL INPUT FOR MS3 HRSG | 28/02/2017 | 28/02/2017 | 15/02/2017 | 15/02/2017 | 0 | TK_Complete
SI1HB-3A05 | TT_Task | BASIC DESIGN MAIN STEEL STRUCTURE HRSG | 03/11/2016 | 07/02/2017 | 03/11/2016 | 15/02/2017 | 0 | TK_Complete
SI1HB-3A25 | TT_Task | DETAIL DESIGN, MANUFACTURING MAIN STEEL STRUCTURE HRSG (Main Frame/Casing) | 01/03/2017 | 30/12/2017 | 16/02/2017 | 30/01/2018 | 0 | TK_Complete
SI1HB-3A80 | TT_Mile | (RFS) READY FOR SHIPMENT MAIN STEEL STRUCTURE HRSG (Main Frame/Casing) | 03/03/2018 | 03/03/2018 | 31/01/2018 | 31/01/2018 | 0 | TK_Complete
SI1HB-3A85 | TT_Mile | EMBEDDED PARTS READY FOR SHIPMENT (Incl. STACK) | 26/08/2017 | 26/08/2017 | 16/08/2017 | 16/08/2017 | 0 | TK_Complete
SI1HB-3A90 | TT_FinMile | (OTD-OS) HRSG EMBEDDED PARTS ON SITE (Incl. STACK) | 26/09/2017 | 26/09/2017 | 28/08/2017 | 28/08/2017 | 0 | TK_Complete
SI1HB-4A42 | TT_Task | TRANSPORT MAIN STEEL STRUCTURE HRSG (Main Frame/Casing)) | 26/03/2018 | 30/03/2018 | 01/03/2018 | 08/03/2018 | 0 | TK_Complete
SI1HB-4A44 | TT_FinMile | (OTD-OS) ON SITE MAIN STEEL STRUCTURE HRSG (Main Frame/Casing) | 30/03/2018 | 30/03/2018 | 08/03/2018 | 08/03/2018 | 0 | TK_Complete
SI1HB-3C25 | TT_Task | BASIC AND DETAIL DESIGN, MANUFACTURING STEEL STRUCTURE HRSG - SECONDARY STEEL | 26/06/2017 | 25/12/2017 | 15/06/2017 | 04/04/2018 | 0 | TK_Complete
SI1HB-3C80 | TT_Mile | (RFS) READY FOR SHIPMENT STEEL STRUCTURE HRSG - SECONDARY STEEL | 06/06/2018 | 06/06/2018 | 13/04/2018 | 13/04/2018 | 0 | TK_Complete
SI1HB-4C40 | TT_FinMile | (OTD-OS) ON SITE STEEL STRUCTURE HRSG - SECONDARY STEEL | 13/06/2018 | 13/06/2018 | 31/05/2018 | 31/05/2018 | 0 | TK_Complete
SI1HB-4C42 | TT_Task | TRANSPORT STEEL STRUCTURE HRSG - SECONDARY STEEL | 06/06/2018 | 13/06/2018 | 12/05/2018 | 31/05/2018 | 0 | TK_Complete
SI1HB-2D60 | TT_FinMile | FINAL INPUT FOR (MS3) STACK | 02/03/2017 | 02/03/2017 | 15/02/2017 | 15/02/2017 | 0 | TK_Complete
SI1HB-3D05 | TT_Task | BASIC AND DETAIL DESIGN / ORDERING STEEL STRUCTURE HRSG - STACK | 24/11/2016 | 15/02/2017 | 24/11/2016 | 28/07/2017 | 0 | TK_Complete
SI1HB-3D25 | TT_Task | MANUFACTURING STEEL STRUCTURE HRSG - STACK | 16/12/2017 | 13/06/2018 | 30/11/2017 | 17/08/2018 | 0 | TK_Complete
SI1HB-3D80 | TT_Mile | (RFS) READY FOR SHIPMENT STEEL STRUCTURE HRSG - STACK | 06/08/2018 | 06/08/2018 | 18/08/2018 | 18/08/2018 | 0 | TK_Complete
SI1HB-4D40 | TT_FinMile | (OTD-OS) ON SITE EXHAUST STACK HRSG | 24/08/2018 | 24/08/2018 | 30/08/2018 | 30/08/2018 | 0 | TK_Complete
SI1HB-4D42 | TT_Task | TRANSPORT STEEL STRUCTURE HRSG - STACK | 06/08/2018 | 24/08/2018 | 21/08/2018 | 30/08/2018 | 0 | TK_Complete
SI1HB-3E80 | TT_Mile | (RFS) READY FOR SHIPMENT INLET &amp; OUTLET DUCT | 26/03/2018 | 26/03/2018 | 30/01/2018 | 30/01/2018 | 0 | TK_Complete
SI1HB-4E40 | TT_FinMile | (OTD-OS) ON SITE INLET &amp; OUTLET DUCT | 30/03/2018 | 30/03/2018 | 08/03/2018 | 08/03/2018 | 0 | TK_Complete
SI1HB-4E42 | TT_Task | TRANSPORT INLET &amp; OUTLET DUCT | 26/03/2018 | 30/03/2018 | 01/03/2018 | 08/03/2018 | 0 | TK_Complete
SI1HA-3C80 | TT_Mile | (RFS) READY FOR SHIPMENT MODULES | 26/01/2018 | 26/01/2018 | 13/01/2018 | 13/01/2018 | 0 | TK_Complete
SI1HA-4C42 | TT_FinMile | (OTD-OS) ON SITE MODULES | 06/05/2018 | 06/05/2018 | 08/04/2018 | 08/04/2018 | 0 | TK_Complete
SI1HA-4C44 | TT_Task | TRANSPORT MODULES | 26/03/2018 | 06/04/2018 | 14/03/2018 | 08/04/2018 | 0 | TK_Complete
SI1HA-3D25 | TT_Task | DESIGN, MANUFACTURING, DELIVERY HRSG DRUMS | 03/11/2016 | 23/01/2018 | 03/11/2016 | 09/04/2018 | 0 | TK_Complete
SI1HA-3D80 | TT_Mile | (RFS) READY FOR SHIPMENT HRSG DRUMS | 17/05/2018 | 17/05/2018 | 17/04/2018 | 17/04/2018 | 0 | TK_Complete
SI1HA-4D42 | TT_Task | TRANSPORT HRSG DRUMS | 17/05/2018 | 27/05/2018 | 17/04/2018 | 26/04/2018 | 0 | TK_Complete
SI1HA-4D44 | TT_FinMile | (OTD-OS) ON SITE HRSG DRUMS | 27/05/2018 | 27/05/2018 | 26/04/2018 | 26/04/2018 | 0 | TK_Complete
SI1HA-2A11 | TT_Task | PROJECT SPECIFIC PRELIMINARY PIPE ROUTING AND SUPPORT CONCEPT HRSG | 03/11/2016 | 31/01/2017 | 03/11/2016 | 31/01/2017 | 0 | TK_Complete
SI1HA-2A40 | TT_Mile | AGREED PIPING DESIGN BASIC REPORT (PDBR) | 14/02/2017 | 14/02/2017 | 01/02/2017 | 01/02/2017 | 0 | TK_Complete
SI1HA-2A54 | TT_Task | STRESS ANALYSIS BY MTEC FOR HRSG-SYSTEMS LAB/LBA10/LBB/C | 14/02/2017 | 18/04/2017 | 01/02/2017 | 28/04/2017 | 0 | TK_Complete
SI1HA-2A55 | TT_FinMile | PIPE STRESS ANALYSIS AND REPORT FOR HRSG SYSTEMS LAB/LBA10/LBB/LBC AVAILABLE | 30/04/2017 | 30/04/2017 | 28/04/2017 | 28/04/2017 | 0 | TK_Complete
SI1HA-2A56 | TT_Task | REVIEW PIPE STRESS CALCULATION FOR HRSG SYSTEMS LAB/LBA10/LBB/LBC | 01/05/2017 | 21/05/2017 | 29/04/2017 | 03/08/2017 | 0 | TK_Complete
SI1HA-2A65 | TT_FinMile | (DF) FINAL INPUT FOR M2 HRSG | 05/08/2017 | 05/08/2017 | 07/07/2017 | 07/07/2017 | 0 | TK_Complete
SI1HA-2E15 | TT_FinMile | PRELIMINARY PIPING DESIGN BASIC REPORT HRSG | 31/01/2017 | 31/01/2017 | 15/01/2017 | 15/01/2017 | 0 | TK_Complete
SI1HA-2E20 | TT_FinMile | (DF) BASIC DESIGN PIPE ROUTING FOR HRSG SYSTEMS LAB/LBA10/LBB/LBC | 05/08/2017 | 05/08/2017 | 07/07/2017 | 07/07/2017 | 0 | TK_Complete
SI1HAD3E25 | TT_Task | BASIC DESIGN, DETAIL DESIGN, ORDERING, DELIVERY, MANUFACTURING PIPING MATERIAL HRSG | 14/02/2017 | 01/05/2018 | 01/02/2017 | 25/06/2018 | 0 | TK_Complete
SI1HAD3E80 | TT_Mile | (RFS) READY FOR SHIPMENT PIPING MATERIAL HRSG | 06/07/2018 | 06/07/2018 | 26/06/2018 | 26/06/2018 | 0 | TK_Complete
SI1HAD4E42 | TT_Task | TRANSPORT PIPING MATERIAL HRSG | 06/07/2018 | 25/07/2018 | 23/07/2018 | 18/08/2018 | 0 | TK_Complete
SI1HAD4E44 | TT_FinMile | (OTD-OS) ON SITE PIPING MATERIAL HRSG | 25/07/2018 | 25/07/2018 | 18/08/2018 | 18/08/2018 | 0 | TK_Complete
SI1CJF2-80 | TT_Task | BASIC DESIGN,QUOTATION STAGE, ODERING ELECTRICAL AND I&amp;C-EQUIPMENT FOR HRSG | 10/06/2017 | 09/10/2017 | 07/05/2017 | 02/10/2017 | 0 | TK_Complete
SI1CJF3-25 | TT_Task | DETAIL DESIGN, MANUFACTURING ELECTRICAL AND I&amp;C-EQUIPMENT FOR HRSG | 02/11/2017 | 29/04/2018 | 03/10/2017 | 15/06/2018 | 0 | TK_Complete
SI1CJF3-80 | TT_Mile | (RFS) READY FOR SHIPMENT ELECTRICAL AND I&amp;C-EQUIPMENT FOR HRSG | 06/07/2018 | 06/07/2018 | 16/06/2018 | 16/06/2018 | 0 | TK_Complete
SI1CJF4-40 | TT_FinMile | (OTD-OS) ON SITE ELECTRICAL AND I&amp;C-EQUIPMENT FOR HRSG | 08/08/2018 | 08/08/2018 | 31/07/2018 | 31/07/2018 | 0 | TK_Complete
SI1CJF4-42 | TT_Task | TRANSPORT ELECTRICAL AND I&amp;C-EQUIPMENT FOR HRSG | 06/07/2018 | 08/08/2018 | 25/06/2018 | 31/07/2018 | 0 | TK_Complete
SI1HA-2-31 | TT_FinMile | DATA INPUT HRSG COMPLETED FOR I&amp;C DESIGN | 25/06/2017 | 25/06/2017 | 09/06/2017 | 09/06/2017 | 0 | TK_Complete
SI1HA-2-70 | TT_FinMile | (DF) I&amp;C DATA FOR HRSG | 02/10/2017 | 02/10/2017 | 05/09/2017 | 05/09/2017 | 0 | TK_Complete
SI1UHW2-45 | TT_Task | PREPARATION BASIC BUILDING DWGS UHW | 10/03/2017 | 13/04/2017 | 23/02/2017 | 29/03/2017 | 0 | TK_Complete
SI1UHW2-60 | TT_FinMile | (MS3) CONCRETE STRUCTURE FINAL DIMENSIONS LOADS AVAILABLE UHW | 28/04/2017 | 28/04/2017 | 21/03/2017 | 21/03/2017 | 0 | TK_Complete
SI1UHW2B60 | TT_Mile | (MS3) STEEL STRUCTURE, FINAL DIMENSIONS AND LOADS AVAILABLE UHW | 25/07/2017 | 25/07/2017 | 24/07/2017 | 24/07/2017 | 0 | TK_Complete
SI1UHW2B70 | TT_Task | DETAIL DESIGN / CHECKER STEEL STRUCTURE UHW | 25/07/2017 | 18/09/2017 | 24/07/2017 | 09/10/2017 | 0 | TK_Complete
SI1UHW2B75 | TT_Mile | (F) DETAIL DESIGN STEEL STRUCTURE WITH CONTRACTOR UHW | 26/01/2018 | 26/01/2018 | 29/12/2017 | 29/12/2017 | 0 | TK_Complete
SI1UHW3B27 | TT_Task | FABRICATION DESIGN, FABRICATION, TRANSPORT, ON SITE STEEL STRUCTURE UHW | 26/01/2018 | 27/05/2018 | 29/12/2017 | 27/06/2018 | 0 | TK_Complete
SI1LBH2D80 | TT_Task | BASIC DESIGN, QUOTATION STAGE, ORDERING CLEAN DRAIN FLASH TANK LBH | 26/11/2016 | 17/03/2017 | 17/11/2016 | 28/04/2017 | 0 | TK_Complete
SI1LBH3D25 | TT_Task | DETAIL DESIGN, MANUFTURING CLEAN DRAIN FLASH TANK LBH | 29/05/2017 | 10/04/2018 | 29/04/2017 | 12/06/2018 | 0 | TK_Complete
SI1LBH3D80 | TT_FinMile | (RFS) READY FOR SHIPMENT CLEAN DRAIN FLASH TANK LBH | 26/05/2018 | 26/05/2018 | 13/06/2018 | 13/06/2018 | 0 | TK_Complete
SI1LBH4D40 | TT_FinMile | (OTD-OS) ON SITE CLEAN DRAIN FLASH TANK LBH | 22/07/2018 | 22/07/2018 | 25/07/2018 | 25/07/2018 | 0 | TK_Complete
SI1LBH4D42 | TT_Task | TRANSPORT CLEAN DRAIN FLASH TANK LBH | 27/05/2018 | 22/07/2018 | 14/06/2018 | 25/07/2018 | 0 | TK_Complete
SI1LCL3B25 | TT_Task | DETAIL DESIGN, MANUFACTURING, SHOP TEST STEAM GENERATOR DRAIN PUMP LCL | 26/06/2017 | 09/02/2018 | 02/06/2017 | 11/12/2017 | 0 | TK_Complete
SI1LCL3B80 | TT_FinMile | (RFS) READY FOR SHIPMENT STEAM GENERATOR DRAIN PUMP LCL | 25/02/2018 | 25/02/2018 | 15/01/2018 | 15/01/2018 | 0 | TK_Complete
SI1LCL4B25 | TT_Task | TRANSPORT STEAM GENERATOR DRAIN PUMP LCL | 26/02/2018 | 02/04/2018 | 08/02/2018 | 15/03/2018 | 0 | TK_Complete
SI1LCL4B42 | TT_FinMile | (OTD-OS) ON SITE STEAM GENERATOR DRAIN PUMP LCL | 13/04/2018 | 13/04/2018 | 15/03/2018 | 15/03/2018 | 0 | TK_Complete
SI1ULA2-45 | TT_Task | PREPARATION BASIC BUILDING DWGS ULA | 15/05/2017 | 18/06/2017 | 10/04/2017 | 30/05/2017 | 0 | TK_Complete
SI1ULA2-60 | TT_FinMile | (MS3) CONCRETE STRUCTURE FINAL DIMENSIONS LOADS AVAILABLE ULA | 29/05/2017 | 29/05/2017 | 23/04/2017 | 23/04/2017 | 0 | TK_Complete
SI1ULA2B60 | TT_FinMile | (MS3) STEEL STRUCTURE, FINAL DIMENSIONS AND LOADS AVAILABLE ULA | 25/06/2017 | 25/06/2017 | 02/06/2017 | 02/06/2017 | 0 | TK_Complete
SI1ULA2B70 | TT_Task | DETAIL DESIGN / CHECKER STEEL STRUCTURE ULA | 26/06/2017 | 27/08/2017 | 02/06/2017 | 27/07/2017 | 0 | TK_Complete
SI1ULA2B75 | TT_Mile | (F) DETAIL DESIGN STEEL STRUCTURE WITH CONTRACTOR ULA | 26/01/2018 | 26/01/2018 | 29/12/2017 | 29/12/2017 | 0 | TK_Complete
SI1ULA3B27 | TT_Task | FABRICATION DESIGN, FABRICATION, TRANSPORT, ON SITE STEEL STRUCTURE ULA | 26/01/2018 | 12/06/2018 | 29/12/2017 | 30/09/2018 | 0 | TK_Complete
SI1BZP2E30 | TT_Task | DETAIL DESIGN CABLE SUPPORT SYSTEM ULA | 17/07/2017 | 10/09/2017 | 23/06/2017 | 24/08/2017 | 0 | TK_Complete
SI1LCA2B14 | TT_Mile | CONFIRMED PUMP CURVES COND.RECIRC.PUMP LCA51 | 01/06/2017 | 01/06/2017 | 19/05/2017 | 19/05/2017 | 0 | TK_Complete
SI1LCA2B60 | TT_FinMile | (DF) FINAL INPUT FOR MS3 COND. RECIRC.PUMP LCA51 | 25/06/2017 | 25/06/2017 | 08/06/2017 | 08/06/2017 | 0 | TK_Complete
SI1LCA2B65 | TT_FinMile | (DF) FINAL INPUT FOR M2 COND.RECIRC.PUMP LCA51 | 25/06/2017 | 25/06/2017 | 08/06/2017 | 08/06/2017 | 0 | TK_Complete
SI1LCA2B75 | TT_Task | CONTRACT REVIEW, PREPARATION RFQ CONDENSATE RECIRC.PUMP LCA51 | 14/01/2017 | 28/02/2017 | 15/12/2016 | 23/01/2017 | 0 | TK_Complete
SI1LCA2B80 | TT_Task | QUOTATION STAGE CONDENSATE RECIRC.PUMP LCA51 | 01/02/2017 | 17/03/2017 | 24/01/2017 | 18/05/2017 | 0 | TK_Complete
SI1LCA2B85 | TT_Mile | ORDER PLACED CONDENSATE RECIRCULATING PUMP LCA51 (MPA) | 15/06/2017 | 15/06/2017 | 19/05/2017 | 19/05/2017 | 0 | TK_Complete
SI1LCA3B25 | TT_Task | MANUFACTURING, SHOP TEST CONDENSATE RECIRCULATION PUMP LCA51 | 01/06/2017 | 08/01/2018 | 19/05/2017 | 15/12/2017 | 0 | TK_Complete
SI1LCA3B80 | TT_FinMile | (RFS) READY FOR SHIPMENT COND.RECIRC. PUMP LCA51 | 26/01/2018 | 26/01/2018 | 02/01/2018 | 02/01/2018 | 0 | TK_Complete
SI1LCA4B27 | TT_Task | TRANSPORT CONDENSATE RECIRCULATING PUMP LCA51 | 26/01/2018 | 15/03/2018 | 02/01/2018 | 10/02/2018 | 0 | TK_Complete
SI1LCA2-10 | TT_Task | DETAIL DESIGN LCA50Y MODULE | 01/06/2017 | 09/11/2017 | 20/05/2017 | 28/10/2017 | 0 | TK_Complete
SI1LCA3-10 | TT_Task | DELIVERY OF SKID FRAME STEEL, PIPING MATERIAL LCA50Y MODULE | 29/11/2017 | 04/03/2018 | 29/10/2017 | 01/02/2018 | 0 | TK_Complete
SI1LCA3-20 | TT_FinMile | DELIVERY OF COMPONENTS LCA50Y MODULE | 22/03/2018 | 22/03/2018 | 19/02/2018 | 19/02/2018 | 0 | TK_Complete
SI1LCA3-25 | TT_Task | MANUFACTURING LCA50Y MODULE | 05/03/2018 | 16/05/2018 | 02/02/2018 | 31/05/2018 | 0 | TK_Complete
SI1LCA4-25 | TT_Task | TRANSPORT LCA50Y MODULE | 20/09/2018 | 05/10/2018 | 18/06/2018 | 25/06/2018 | 0 | TK_Complete
SI1LCA4-42 | TT_FinMile | (OTD-OS) ON SITE LCA50Y MODULE | 05/10/2018 | 05/10/2018 | 25/06/2018 | 25/06/2018 | 0 | TK_Complete
SI1LAC2B14 | TT_Mile | CONFIRMED PUMP CURVES FEEDWATER PUMP LAC | 26/11/2016 | 26/11/2016 | 03/11/2016 | 03/11/2016 | 0 | TK_Complete
SI1LAC2B60 | TT_FinMile | (DF) FINAL INPUT FOR MS3 FEEDWATER PUMP LAC | 31/03/2017 | 31/03/2017 | 15/03/2017 | 15/03/2017 | 0 | TK_Complete
SI1LAC2B65 | TT_FinMile | (DF) FINAL INPUT FOR M2 FEEDWATER PUMP LAC | 31/03/2017 | 31/03/2017 | 15/03/2017 | 15/03/2017 | 0 | TK_Complete
SI1LAC2B75 | TT_Task | CONTRACT REVIEW, PREPARATION RFQ FEEDWATER PUMP LAC | 26/11/2016 | 08/01/2017 | 03/11/2016 | 16/12/2016 | 0 | TK_Complete
SI1LAC2B80 | TT_Task | QUOTATION STAGE FEEDWATER PUMP LAC (MPA) | 21/01/2017 | 17/02/2017 | 17/12/2016 | 13/01/2017 | 0 | TK_Complete
SI1LAC2B85 | TT_Mile | ORDER PLACED FEEDWATER PUMP LAC | 17/02/2017 | 17/02/2017 | 14/02/2017 | 14/02/2017 | 0 | TK_Complete
SI1LAC3B25 | TT_Task | DETAIL DESIGN, MANUFACTURING, SHOP TEST FEEDWATER PUMP LAC | 01/03/2017 | 04/12/2017 | 14/02/2017 | 19/11/2017 | 0 | TK_Complete
SI1LAC3B80 | TT_FinMile | (RFS) READY FOR SHIPMENT FEEDWATER PUMP LAC | 25/11/2017 | 25/11/2017 | 24/11/2017 | 24/11/2017 | 0 | TK_Complete
SI1LAC4B25 | TT_Task | TRANSPORT FEEDWATER PUMP LAC | 26/11/2017 | 13/01/2018 | 12/12/2017 | 05/02/2018 | 0 | TK_Complete
SI1LAC2-10 | TT_Task | DETAIL DESIGN LAC10Y MODULE | 16/03/2017 | 28/08/2017 | 14/03/2017 | 26/08/2017 | 0 | TK_Complete
SI1LAC3-10 | TT_Task | DELIVERY OF SKID FRAME STEEL, PIPING MATERIAL LAC10Y MODULE | 27/09/2017 | 20/12/2017 | 27/08/2017 | 19/11/2017 | 0 | TK_Complete
SI1LAC3-20 | TT_FinMile | DELIVERY OF COMPONENTS LAC10Y MODULE | 05/03/2018 | 05/03/2018 | 02/02/2018 | 02/02/2018 | 0 | TK_Complete
SI1LAC3-25 | TT_Task | MANUFACTURING LAC10Y MODULE | 17/12/2017 | 12/05/2018 | 16/11/2017 | 31/05/2018 | 0 | TK_Complete
SI1LAC4-25 | TT_Task | TRANSPORT LAC10Y MODULE | 20/09/2018 | 05/10/2018 | 18/06/2018 | 25/06/2018 | 0 | TK_Complete
SI1LAC4-42 | TT_FinMile | (OTD-OS) ON SITE LAC10Y MODULE | 05/10/2018 | 05/10/2018 | 25/06/2018 | 25/06/2018 | 0 | TK_Complete
SI1QC-3-25 | TT_Task | DESIGN, MANUFACTURING, SHOP TEST DOSING CONTAINER QC | 04/06/2017 | 11/10/2017 | 11/05/2017 | 17/04/2018 | 0 | TK_Complete
SI1QC-3-80 | TT_FinMile | (RFS) READY FOR SHIPMENT DOSING CONTAINER QC | 24/08/2018 | 24/08/2018 | 18/05/2018 | 18/05/2018 | 0 | TK_Complete
SI1QC-4-25 | TT_Task | TRANSPORT DOSING CONTAINER QC | 25/08/2018 | 12/10/2018 | 25/05/2018 | 07/07/2018 | 0 | TK_Complete
SI1QC-4-42 | TT_FinMile | (OTD-OS) ON SITE DOSING CONTAINER QC | 12/10/2018 | 12/10/2018 | 07/07/2018 | 07/07/2018 | 0 | TK_Complete
SI1QU-3-25 | TT_Task | DESIGN, MANUFACTURING, SHOP TEST SAMPLING CONTAINER QU | 05/06/2017 | 21/11/2017 | 11/05/2017 | 06/06/2018 | 0 | TK_Complete
SI1QU-3-80 | TT_FinMile | (RFS) READY FOR SHIPMENT SAMPLING CONTAINER QU | 04/10/2018 | 04/10/2018 | 31/08/2018 | 31/08/2018 | 0 | TK_Complete
SI1QU-4-25 | TT_Task | TRANSPORT SAMPLING CONTAINER QU | 05/10/2018 | 22/11/2018 | 02/09/2018 | 06/10/2018 | 0 | TK_Complete
SI1QU-4-42 | TT_FinMile | (OTD-OS) ON SITE SAMPLING CONTAINER QU | 22/11/2018 | 22/11/2018 | 06/10/2018 | 06/10/2018 | 0 | TK_Complete
SI1UMY2-45 | TT_Task | PREPARATION BASIC BUILDING DWGS UMY | 26/06/2017 | 30/07/2017 | 02/06/2017 | 21/06/2017 | 0 | TK_Complete
SI1UMY2-60 | TT_FinMile | (MS3) CONCRETE STRUCTURE FINAL DIMENSIONS LOADS AVAILABLE UMY | 25/06/2017 | 25/06/2017 | 15/06/2017 | 15/06/2017 | 0 | TK_Complete
SI1UMY3-60 | TT_Task | FABRICATION DESIGN, FABRICATION, TRANSPORT, ON SITE STEEL STRUCTURE UMY | 26/01/2018 | 27/05/2018 | 29/12/2017 | 15/09/2018 | 0 | TK_Complete
SI1UMY2B60 | TT_FinMile | (MS3) STEEL STRUCTURE, FINAL DIMENSIONS AND LOADS AVAILABLE UMY00Y | 31/05/2017 | 31/05/2017 | 12/05/2017 | 12/05/2017 | 0 | TK_Complete
SI1UMY2B70 | TT_Task | DETAIL DESIGN / CHECKER STEEL STRUCTURE UMY00Y | 02/06/2017 | 25/11/2017 | 13/05/2017 | 25/12/2017 | 0 | TK_Complete
SI1UMY3-29 | TT_Task | MANUFACTURING UMY00Y MODULE | 01/08/2018 | 06/10/2018 | 26/04/2018 | 06/10/2018 | 0 | TK_Complete
SI1UMY3B25 | TT_Task | DELIVERY OF SKID FRAME STEEL, PIPING MATERIAL UMY00Y MODULE | 05/02/2018 | 02/05/2018 | 26/12/2017 | 23/05/2018 | 0 | TK_Complete
SI1UMY4-44 | TT_FinMile | (OTD-OS) ON SITE UMY00Y MODULE | 05/11/2018 | 05/11/2018 | 05/11/2018 | 05/11/2018 | 0 | TK_Complete
SI1UMY4B30 | TT_Task | TRANSPORT STEEL STRUCTURE UMY00Y | 22/10/2018 | 05/11/2018 | 17/10/2018 | 05/11/2018 | 0 | TK_Complete
SI1BZP2D30 | TT_Task | DETAIL DESIGN CABLE SUPPORT SYSTEM UMY | 23/10/2017 | 17/12/2017 | 22/09/2017 | 16/11/2017 | 0 | TK_Complete
SI1UHX2-45 | TT_Task | PREPARATION BASIC BUILDING DWGS UHX | 26/08/2017 | 29/09/2017 | 25/08/2017 | 24/09/2017 | 0 | TK_Complete
SI1UHX2-60 | TT_FinMile | (MS3) CONCRETE STRUCTURE FINAL DIMENSIONS LOADS AVAILABLE UHX | 25/09/2017 | 25/09/2017 | 30/08/2017 | 30/08/2017 | 0 | TK_Complete
SI1UTX2-45 | TT_Task | PREPARATION BASIC BUILDING DWGS UTX | 02/11/2017 | 06/12/2017 | 25/09/2017 | 18/10/2017 | 0 | TK_Complete
SI1UTX2-60 | TT_Mile | (MS3) CONCRETE STRUCTURE FINAL DIMENSIONS LOADS AVAILABLE UTX | 16/11/2017 | 16/11/2017 | 30/09/2017 | 30/09/2017 | 0 | TK_Complete
SI1UVM2-45 | TT_Task | PREPARATION BASIC BUILDING DWGS SCR UNIT | 01/05/2017 | 04/06/2017 | 29/04/2017 | 30/06/2017 | 0 | TK_Complete
SI1UVM2-50 | TT_Task | PREPARATION FOUNDATION GROUNDING DWGS SCR UNIT | 01/05/2017 | 14/05/2017 | 29/04/2017 | 12/05/2017 | 0 | TK_Complete
SI1UVM2-60 | TT_FinMile | (MS3) CONCRETE STRUCTURE FINAL DIMENSIONS LOADS AVAILABLE SCR UNIT | 16/06/2017 | 16/06/2017 | 12/05/2017 | 12/05/2017 | 0 | TK_Complete
SI1HSJ3-25 | TT_Task | DESIGN, MANUFACTURING, SHOP TEST SCR UNIT | 15/05/2017 | 08/03/2018 | 15/04/2017 | 15/06/2018 | 0 | TK_Complete
SI1HSJ3-80 | TT_FinMile | (RFS) READY FOR SHIPMENT SCR UNIT | 04/09/2018 | 04/09/2018 | 16/06/2018 | 16/06/2018 | 0 | TK_Complete
SI1HSJ3-85 | TT_FinMile | (RFS) READY FOR SHIPMENT SCR CATALYST | 04/11/2018 | 04/11/2018 | 30/08/2018 | 30/08/2018 | 0 | TK_Complete
SI1HSJ4-40 | TT_FinMile | (OTD-OS) ON SITE SCR UNIT | 03/11/2018 | 03/11/2018 | 26/10/2018 | 26/10/2018 | 0 | TK_Complete
SI1HSJ4-44 | TT_Task | TRANSPORT SCR UNIT | 05/09/2018 | 03/11/2018 | 18/07/2018 | 26/10/2018 | 0 | TK_Complete
SI1HSJ4-46 | TT_Task | TRANSPORT SCR CATALYST | 05/11/2018 | 03/01/2019 | 27/01/2019 | 21/02/2019 | 0 | TK_Complete
SI1HSJ4-48 | TT_FinMile | (OTD-OS) ON SITE SCR CATALYST | 03/01/2019 | 03/01/2019 | 21/02/2019 | 21/02/2019 | 0 | TK_Complete
SI1--P3-25 | TT_Task | DETAIL DESIGN, SUPPLY, PREFAB., SHOP TEST STANDARD PIPING SUPPORT PARTS ALL SIZES | 26/08/2017 | 05/02/2018 | 04/08/2017 | 14/01/2018 | 0 | TK_Complete
SI1--P3A35 | TT_Task | PREFABRICATION, SHOP TEST ALLOYED AND OTHER PIPING MATERIAL (DN&gt;=80) ALL SIZES | 29/11/2017 | 23/01/2018 | 20/11/2017 | 02/03/2018 | 0 | TK_Complete
SI1--P3A50 | TT_Mile | ON SITE FINAL ISOs &gt;= 80 / SUPPORT PARTS ALL SIZES | 26/03/2018 | 26/03/2018 | 03/03/2018 | 03/03/2018 | 0 | TK_Complete
SI1--P4A25 | TT_Task | TRANSPORT (1ST) PIPING (DN &gt;=80) AND STANDARD SUPPORT PARTS ALL SIZES | 26/03/2018 | 08/04/2018 | 20/03/2018 | 10/04/2018 | 0 | TK_Complete
SI1--P4A42 | TT_Task | TRANSPORT (2ND) PIPING (DN &gt;=80) AND STANDARD SUPPORT PARTS ALL SIZES | 12/03/2019 | 25/03/2019 | 20/04/2018 | 02/05/2018 | 0 | TK_Complete
SI1--P4A44 | TT_Mile | ON SITE (2ND) PIPES (DN &gt;=80) AND STANDARD SUPPORT PARTS ALL SIZES | 02/05/2018 | 02/05/2018 | 02/05/2018 | 02/05/2018 | 0 | TK_Complete
SI1--P4A46 | TT_Task | TRANSPORT (3RD) PIPING (DN &gt;=80) AND STANDARD SUPPORT PARTS ALL SIZES | 14/05/2018 | 27/05/2018 | 04/07/2018 | 13/07/2018 | 0 | TK_Complete
SI1--P4A48 | TT_Mile | ON SITE (3RD) PIPES (DN &gt;=80) AND STANDARD SUPPORT PARTS ALL SIZES | 28/05/2018 | 28/05/2018 | 13/07/2018 | 13/07/2018 | 0 | TK_Complete
SI1--P4A50 | TT_Task | TRANSPORT (4TH) PIPING (DN &gt;=80) AND STANDARD SUPPORT PARTS ALL SIZES | 03/06/2018 | 16/06/2018 | 16/07/2018 | 20/07/2018 | 0 | TK_Complete
SI1--P4A52 | TT_Mile | ON SITE (4TH) PIPES (DN &gt;=80) AND STANDARD SUPPORT PARTS ALL SIZES | 17/06/2018 | 17/06/2018 | 20/07/2018 | 20/07/2018 | 0 | TK_Complete
SI1--P4A54 | TT_Mile | ON SITE (1ST) PIPES (DN &gt;=80) AND STANDARD SUPPORT PARTS ALL SIZES | 12/03/2019 | 12/03/2019 | 10/04/2018 | 10/04/2018 | 0 | TK_Complete
SI1--P3H25 | TT_Task | DETAIL DESIGN, SUPPLY, SHOP TEST PIPING (DN &lt;80) AND SECONDARY STEEL ALL SIZES | 26/08/2017 | 28/01/2018 | 26/07/2017 | 29/12/2017 | 0 | TK_Complete
SI1--P3H50 | TT_Mile | ON SITE FINAL ISOs &lt; 80 | 26/02/2018 | 26/02/2018 | 18/02/2018 | 18/02/2018 | 0 | TK_Complete
SI1--P4H25 | TT_Task | TRANSPORT (1ST) PIPING (DN &lt;80) | 02/05/2018 | 08/05/2018 | 30/03/2018 | 10/04/2018 | 0 | TK_Complete
SI1--P4H42 | TT_Task | TRANSPORT (2ND) PIPING (DN &lt;80) | 14/05/2018 | 27/05/2018 | 22/04/2018 | 02/05/2018 | 0 | TK_Complete
SI1--P4H44 | TT_Mile | ON SITE PIPES (2ND) (DN &lt;80) | 28/05/2018 | 28/05/2018 | 02/05/2018 | 02/05/2018 | 0 | TK_Complete
SI1--P4H46 | TT_Mile | ON SITE PIPES (1ST) (DN &lt;80) | 09/05/2018 | 09/05/2018 | 10/04/2018 | 10/04/2018 | 0 | TK_Complete
SI0--P4E10 | TT_Task | TRANSPORT TO PREFABRICATION SHOP (ALLOYED MATERIAL) | 31/10/2017 | 27/11/2017 | 01/10/2017 | 28/10/2017 | 0 | TK_Complete
SI0--P4A10 | TT_Task | TRANSPORT TO PREFABRICATION SHOP (NON-ALLOYED MATERIALS) | 09/10/2017 | 12/11/2017 | 08/09/2017 | 12/10/2017 | 0 | TK_Complete
SI0--P4A15 | TT_Task | TRANSPORT TO PREFABRICATION SHOP (GRP MATERIALS) | 17/11/2017 | 04/01/2018 | 18/10/2017 | 25/12/2017 | 0 | TK_Complete
SI---P4I25 | TT_Task | TRANSPORT VALVES | 05/03/2018 | 18/03/2018 | 02/02/2018 | 23/02/2018 | 0 | TK_Complete
SI---P4I42 | TT_FinMile | (OTD-OS) ON SITE VALVES | 11/03/2018 | 11/03/2018 | 23/02/2018 | 23/02/2018 | 0 | TK_Complete
SI-ZTB4A27 | TT_Task | TRANSPORT PIPING FOR STEAM BLOWING SYSTEM ZTB | 02/05/2018 | 19/06/2018 | 16/11/2018 | 23/11/2018 | 0 | TK_Complete
SI1UPY2-10 | TT_Task | DETAIL DESIGN UPY00Y MODULE | 26/06/2017 | 03/12/2017 | 05/06/2017 | 17/11/2017 | 0 | TK_Complete
SI1UPY2B77 | TT_FinMile | (MS3) STEEL STRUCTURE, FINAL DIMENSIONS AND LOADS AVAILABLE UPY00Y | 25/06/2017 | 25/06/2017 | 07/06/2017 | 07/06/2017 | 0 | TK_Complete
SI1UPY3-10 | TT_Task | DELIVERY OF SKID FRAME STEEL, PIPING MATERIAL UPY00Y MODULE | 19/12/2017 | 24/03/2018 | 18/11/2017 | 21/02/2018 | 0 | TK_Complete
SI1UPY3-20 | TT_FinMile | DELIVERY OF COMPONENTS UPY00Y MODULE | 26/02/2018 | 26/02/2018 | 26/01/2018 | 26/01/2018 | 0 | TK_Complete
SI1UPY3-25 | TT_Task | MANUFACTURING UPY00Y MODULE | 25/03/2018 | 01/07/2018 | 22/02/2018 | 15/11/2018 | 0 | TK_Complete
SI1UPY4-25 | TT_Task | TRANSPORT UPY00Y MODULE | 23/07/2018 | 06/08/2018 | 23/11/2018 | 30/11/2018 | 0 | TK_Complete
SI1UPY4-42 | TT_FinMile | (OTD-OS) ON SITE UPY00Y MODULE | 06/08/2018 | 06/08/2018 | 30/11/2018 | 30/11/2018 | 0 | TK_Complete
SI1BZP2G30 | TT_Task | DETAIL DESIGN CABLE SUPPORT SYSTEM UQA ELECTRICAL ROOM | 26/06/2017 | 06/08/2017 | 02/06/2017 | 24/08/2017 | 0 | TK_Complete
SI1UQA2E77 | TT_Task | PREPARATION BASIC BUILDING DWGS 10UQA | 03/05/2017 | 06/06/2017 | 01/04/2017 | 28/04/2017 | 0 | TK_Complete
SI1UQA2E79 | TT_FinMile | (MS3) CONCRETE STRUCTURE FINAL DIMENSIONS LOADS AVAILABLE 10UQA | 16/05/2017 | 16/05/2017 | 15/04/2017 | 15/04/2017 | 0 | TK_Complete
SI1PBB2B100 | TT_Mile | ORDER PLACED DEBRIS FILTER PBB | 15/05/2017 | 15/05/2017 | 22/04/2017 | 22/04/2017 | 0 | TK_Complete
SI1PBB2B105 | TT_FinMile | (DF) FINAL INPUT FOR M2 DEBRIS FILTER PBB | 31/05/2017 | 31/05/2017 | 06/05/2017 | 06/05/2017 | 0 | TK_Complete
SI1PBB2B110 | TT_FinMile | (DF) FINAL INPUT FOR MS3 DEBRIS FILTER PBB | 06/05/2017 | 06/05/2017 | 29/04/2017 | 29/04/2017 | 0 | TK_Complete
SI1PBB2B90 | TT_Task | CONTRACT REVIEW, PREPARATION RFQ DEBRIS FILTER PBB | 14/01/2017 | 10/02/2017 | 19/12/2016 | 15/01/2017 | 0 | TK_Complete
SI1PBB2B95 | TT_Task | QUOTATION STAGE DEBRIS FILTER PBB | 05/03/2017 | 18/03/2017 | 26/01/2017 | 21/04/2017 | 0 | TK_Complete
SI1PBB3B85 | TT_Task | DETAIL DESIGN, MANUFACTURING, SHOP TEST DEBRIS FILTER PBB | 15/05/2017 | 05/02/2018 | 23/04/2017 | 18/12/2017 | 0 | TK_Complete
SI1PBB3B90 | TT_FinMile | (RFS) READY FOR SHIPMENT DEBRIS FILTER PBB | 26/01/2018 | 26/01/2018 | 18/12/2017 | 18/12/2017 | 0 | TK_Complete
SI1PBB4B47 | TT_Task | TRANSPORT DEBRIS FILTER PBB | 26/01/2018 | 15/03/2018 | 19/12/2017 | 17/01/2018 | 0 | TK_Complete
SI1PAC3B25 | TT_Task | DETAIL DESIGN, MANUFACTURING, SHOP TEST CIRC. CW PUMP PAC | 06/05/2017 | 23/06/2018 | 16/04/2017 | 22/04/2018 | 0 | TK_Complete
SI1PAC3B80 | TT_FinMile | (RFS) READY FOR SHIPMENT CIRC. CW PUMP PAC | 30/06/2018 | 30/06/2018 | 30/05/2018 | 30/05/2018 | 0 | TK_Complete
SI1PAC4B25 | TT_Task | TRANSPORT CIRC. CW PUMP PAC | 01/07/2018 | 18/08/2018 | 09/06/2018 | 07/07/2018 | 0 | TK_Complete
SI1PAC4B42 | TT_FinMile | (OTD-OS) ON SITE CIRC. CW PUMP PAC | 18/08/2018 | 18/08/2018 | 07/07/2018 | 07/07/2018 | 0 | TK_Complete
SI1PAC4E42 | TT_FinMile | (OTD-OS) ON SITE EMBEDDED PARTS PUMP PAC | 18/08/2018 | 18/08/2018 | 07/07/2018 | 07/07/2018 | 0 | TK_Complete
SI1SMQ3A85 | TT_Task | FABRICATION DESIGN, MANUFACTURING, SHOP TEST CRANE SMQ FOR UQA | 25/07/2017 | 22/01/2018 | 19/07/2017 | 28/02/2018 | 0 | TK_Complete
SI1SMQ3A90 | TT_FinMile | (RFS) READY FOR SHIPMENT CRANE SMQ FOR UQA | 28/03/2018 | 28/03/2018 | 28/02/2018 | 28/02/2018 | 0 | TK_Complete
SI1SMQ4A47 | TT_Task | TRANSPORT CRANE SMQ FOR UQA | 17/04/2018 | 10/05/2018 | 22/03/2018 | 23/04/2018 | 0 | TK_Complete
SI1SMQ4A50 | TT_FinMile | (OTD-OS) ON SITE CRANE SMQ FOR UQA | 25/05/2018 | 25/05/2018 | 23/04/2018 | 23/04/2018 | 0 | TK_Complete
SI1PAA3-25 | TT_Task | DETAIL DESIGN, MANUFACTURING CW BAR SCREEN FOR PAB SYSTEM | 26/11/2017 | 23/04/2018 | 26/10/2017 | 23/03/2018 | 0 | TK_Complete
SI1PAA3-80 | TT_FinMile | (RFS) READY FOR SHIPMENT CW BAR SCREEN FOR PAB SYSTEM | 26/03/2018 | 26/03/2018 | 23/03/2018 | 23/03/2018 | 0 | TK_Complete
SI1PAA4-52 | TT_Task | TRANSPORT CW BAR SCREEN FOR PAB SYSTEM | 02/05/2018 | 15/05/2018 | 23/05/2018 | 28/05/2018 | 0 | TK_Complete
SI1PAA4-54 | TT_FinMile | (OTD-OS) ON SITE CW BAR SCREEN FOR PAB SYSTEM | 15/05/2018 | 15/05/2018 | 28/05/2018 | 28/05/2018 | 0 | TK_Complete
SI0GN-3B82 | TT_Task | DETAIL DESIGN, MANUFACTURING, SHOP TEST PROCESS DRAINS TREATMENT GN- | 08/08/2017 | 29/03/2018 | 12/07/2017 | 18/04/2018 | 0 | TK_Complete
SI0GN-3B84 | TT_FinMile | (RFS) READY FOR SHIPMENT PROCESS DRAINS TREATMENT GN- | 25/05/2018 | 25/05/2018 | 30/05/2018 | 30/05/2018 | 0 | TK_Complete
SI0GN-4B42 | TT_Task | TRANSPORT PROCESS DRAINS TREATMENT GN- | 26/05/2018 | 24/07/2018 | 10/06/2018 | 16/07/2018 | 0 | TK_Complete
SI0GN-4B46 | TT_FinMile | (OTD-OS) ON SITE PROCESS DRAINS TREATMENT GN- | 24/07/2018 | 24/07/2018 | 16/07/2018 | 16/07/2018 | 0 | TK_Complete
SI1USV2-79 | TT_Mile | (MS3) CONCRETE STRUCTURE FINAL DIMENSIONS LOADS AVAILABLE USV | 03/07/2017 | 03/07/2017 | 02/06/2017 | 02/06/2017 | 0 | TK_Complete
SI1STG-3-82 | TT_Task | DESIGN, MANUFACTURING, SHOP TEST LABORATORY CONTAINER STG | 26/10/2017 | 08/04/2018 | 25/09/2017 | 07/06/2018 | 0 | TK_Complete
SI1STG-3-84 | TT_FinMile | (RFS) READY FOR SHIPMENT LABORATORY CONTAINER STG | 01/07/2018 | 01/07/2018 | 25/08/2018 | 25/08/2018 | 0 | TK_Complete
SI1STG-4-42 | TT_Task | TRANSPORT LABORATORY CONTAINER STG | 02/07/2018 | 19/08/2018 | 26/08/2018 | 08/10/2018 | 0 | TK_Complete
SI1STG-4-46 | TT_FinMile | (OTD-OS) ON SITE LABORATORY CONTAINER STG | 19/08/2018 | 19/08/2018 | 08/10/2018 | 08/10/2018 | 0 | TK_Complete
SI0UEN2-45 | TT_Task | PREPARATION BASIC BUILDING DWGS 00UEN | 26/06/2017 | 30/07/2017 | 17/06/2017 | 30/06/2017 | 0 | TK_Complete
SI0UEN2-60 | TT_FinMile | (MS3) CONCRETE STRUCTURE FINAL DIMENSIONS LOADS AVAILABLE 00UEN | 25/07/2017 | 25/07/2017 | 25/06/2017 | 25/06/2017 | 0 | TK_Complete
SI0UGY2-45 | TT_Task | PREPARATION BASIC BUILDING DWGS UGY | 26/08/2017 | 29/09/2017 | 25/08/2017 | 24/09/2017 | 0 | TK_Complete
SI0UGY2-60 | TT_FinMile | (MS3) CONCRETE STRUCTURE FINAL DIMENSIONS LOADS AVAILABLE UGY | 25/09/2017 | 25/09/2017 | 27/08/2017 | 27/08/2017 | 0 | TK_Complete
SI0UGY2B60 | TT_FinMile | (MS3) STEEL STRUCTURE, FINAL DIMENSIONS AND LOADS AVAILABLE UGY | 25/06/2017 | 25/06/2017 | 01/06/2017 | 01/06/2017 | 0 | TK_Complete
SI0UGY2B70 | TT_Task | DETAIL DESIGN / CHECKER STEEL STRUCTURE UGY | 08/08/2017 | 02/10/2017 | 10/07/2017 | 15/11/2017 | 0 | TK_Complete
SI0BZP2B30 | TT_Task | DETAIL DESIGN CABLE SUPPORT SYSTEM UCA | 01/03/2017 | 11/04/2017 | 21/02/2017 | 03/04/2017 | 0 | TK_Complete
SI0ACA3-25 | TT_Task | MANUFACTURING, SHOP TEST HV-SWITCHGEAR GIL | 14/04/2017 | 30/03/2018 | 30/03/2017 | 09/03/2018 | 0 | TK_Complete
SI0ACA3-85 | TT_FinMile | (RFS) READY FOR SHIPMENT HV-SWITCHGEAR GIL | 06/05/2018 | 06/05/2018 | 30/03/2018 | 30/03/2018 | 0 | TK_Complete
SI0ACA3-87 | TT_Task | PACKING HV-SWITCHGEAR GIL | 07/04/2018 | 06/05/2018 | 10/03/2018 | 30/03/2018 | 0 | TK_Complete
SI0ACA4-57 | TT_Task | TRANSPORT HV-SWITCHGEAR GIL | 07/05/2018 | 04/06/2018 | 01/06/2018 | 10/07/2018 | 0 | TK_Complete
SI0ACA4-59 | TT_FinMile | (OTD-OS) ON SITE HV-SWITCHGEAR GIL | 05/06/2018 | 05/06/2018 | 10/07/2018 | 10/07/2018 | 0 | TK_Complete
SI-CYE2-20 | TT_Task | (BOP) TECHNICAL CLARIFICATION FIRE ALARM SYSTEM CYE | 14/01/2017 | 10/02/2017 | 10/12/2016 | 06/01/2017 | 0 | TK_Complete
SI-CYE2-25 | TT_Task | (BOP) BASIC DESIGN, SPECIFICATION FIRE ALARM SYSTEM CYE | 14/01/2017 | 10/02/2017 | 07/01/2017 | 22/03/2017 | 0 | TK_Complete
SI-CYE2-30 | TT_FinMile | (BOP) RFQ FIRE ALARM SYSTEM CYE | 30/04/2017 | 30/04/2017 | 31/03/2017 | 31/03/2017 | 0 | TK_Complete
SI-CYE2-35 | TT_Task | (BOP) QUOTATION STAGE FIRE ALARM SYSTEM CYE | 17/05/2017 | 25/06/2017 | 01/04/2017 | 19/06/2017 | 0 | TK_Complete
SI-CYE2-40 | TT_Mile | (BOP) ORDER PLACED FIRE ALARM SYSTEM CYE | 26/08/2017 | 26/08/2017 | 18/08/2017 | 18/08/2017 | 0 | TK_Complete
SI-CYE3-90 | TT_Task | (BOP) MANUFACTURING, SHOP TEST FIRE ALARM SYSTEM CYE | 26/08/2017 | 07/01/2018 | 18/08/2017 | 17/02/2018 | 0 | TK_Complete
SI-CYE3-92 | TT_FinMile | (BOP) (RFS) READY FOR SHIPMENT FIRE ALARM SYSTEM CYE | 01/03/2018 | 01/03/2018 | 23/02/2018 | 23/02/2018 | 0 | TK_Complete
SI-CYE4-60 | TT_Task | (BOP) TRANSPORT FIRE ALARM SYSTEM CYE | 02/03/2018 | 06/03/2018 | 24/02/2018 | 28/02/2018 | 0 | TK_Complete
SI-SG-2-10 | TT_Mile | (BOP) ORDER PLACED FIRE FIGHTING SYSTEM SG | 26/08/2017 | 26/08/2017 | 18/08/2017 | 18/08/2017 | 0 | TK_Complete
SI-SG-2-95 | TT_Task | (BOP) TECHNICAL CLARIFICATION FIRE FIGHTING SYSTEM SG | 01/03/2017 | 28/03/2017 | 25/02/2017 | 24/03/2017 | 0 | TK_Complete
SI-SG-2-96 | TT_Task | (BOP) BASIC DESIGN, SPECIFICATION FIRE FIGHTING SYSTEM SG | 01/04/2017 | 14/04/2017 | 25/03/2017 | 07/04/2017 | 0 | TK_Complete
SI-SG-2-97 | TT_FinMile | (BOP) RFQ FIRE FIGHTING SYSTEM SG | 21/05/2017 | 21/05/2017 | 31/03/2017 | 31/03/2017 | 0 | TK_Complete
SI-SG-2-99 | TT_Task | (BOP) QUOTATION STAGE FIRE FIGHTING SYSTEM SG | 22/05/2017 | 30/06/2017 | 01/04/2017 | 19/06/2017 | 0 | TK_Complete
SI-SG-3-86 | TT_Task | (BOP) MANUFACTURING, SHOP TEST FIRE FIGHTING SYSTEM SG | 26/08/2017 | 07/01/2018 | 18/08/2017 | 15/08/2018 | 0 | TK_Complete
SI-SG-3-88 | TT_FinMile | (BOP) (RFS) READY FOR SHIPMENT FIRE FIGHTING SYSTEM SG | 05/07/2018 | 05/07/2018 | 16/08/2018 | 16/08/2018 | 0 | TK_Complete
SI-SG-4-58 | TT_Task | (BOP) TRANSPORT FIRE FIGHTING SYSTEM SG | 06/07/2018 | 30/08/2018 | 17/08/2018 | 21/08/2018 | 0 | TK_Complete
SI-EK-2-87 | TT_Task | (BOP) BASIC DESIGN, PREPARATION RFQ FUEL GAS SUPPLY SYSTEM EK (Add. ISOLATING VALVES ONLY) | 01/04/2017 | 26/05/2017 | 18/03/2017 | 12/05/2017 | 0 | TK_Complete
SI-EK-2-89 | TT_Task | (BOP) QUOTATION STAGE FUEL GAS SUPPLY SYSTEM EK (Add. ISOLATING VALVES ONLY) | 13/06/2017 | 03/07/2017 | 13/05/2017 | 02/06/2017 | 0 | TK_Complete
SI-EK-2-91 | TT_Mile | (BOP) ORDER PLACED FUEL GAS SUPPLY SYSTEM EK (Add. ISOLATING VALVES ONLY) | 28/06/2017 | 28/06/2017 | 03/06/2017 | 03/06/2017 | 0 | TK_Complete
SI-EK-2-97 | TT_Task | (BOP) TECHNICAL CLARIFICATION FUEL GAS SUPPLY SYSTEM EK (Add. ISOLATING VALVES ONLY) | 01/02/2017 | 28/03/2017 | 21/01/2017 | 17/03/2017 | 0 | TK_Complete
SI-EK-3-82 | TT_Task | (BOP) DETAIL DESIGN, MANUFACTURING FUEL GAS SUPPLY SYSTEM EK (Add. ISOLATING VALVES ONLY) | 26/06/2017 | 21/04/2018 | 03/06/2017 | 23/03/2018 | 0 | TK_Complete
SI-EK-3-86 | TT_FinMile | (BOP) (RFS) READY FOR SHIPMENT GAS SYSTEM EK (Add. ISOLATING VALVES ONLY) | 05/05/2018 | 05/05/2018 | 29/03/2018 | 29/03/2018 | 0 | TK_Complete
SI-EK-4-42 | TT_Task | (BOP) TRANSPORT FUEL GAS SUPPLY SYSTEM EK (Add. ISOLATING VALVES ONLY) | 06/05/2018 | 04/07/2018 | 22/04/2018 | 29/05/2018 | 0 | TK_Complete
SI-EK-4-48 | TT_FinMile | (OTD-OS) (BOP) ON SITE FUEL GAS SUPPLY SYSTEM EK (Add. ISOLATING VALVES ONLY) | 04/07/2018 | 04/07/2018 | 29/05/2018 | 29/05/2018 | 0 | TK_Complete
SI-BZK2-135 | TT_Task | (BOP) BASIC DESIGN, SPECIFICATION MV CABLES BZK | 20/05/2017 | 16/06/2017 | 20/04/2017 | 17/05/2017 | 0 | TK_Complete
SI-BZK2-87 | TT_Task | (BOP) TECHNICAL CLARIFICATION MV CABLES BZK | 01/04/2017 | 28/04/2017 | 23/03/2017 | 19/04/2017 | 0 | TK_Complete
SI-BZK2-89 | TT_FinMile | (BOP) RFQ MV CABLES BZK | 17/06/2017 | 17/06/2017 | 17/05/2017 | 17/05/2017 | 0 | TK_Complete
SI-BZK2-91 | TT_Task | (BOP) QUOTATION STAGE MV CABLES BZK | 18/06/2017 | 29/07/2017 | 18/05/2017 | 24/08/2017 | 0 | TK_Complete
SI-BZK2-93 | TT_Mile | (BOP) ORDER PLACED MV CABLES BZK | 26/08/2017 | 26/08/2017 | 25/08/2017 | 25/08/2017 | 0 | TK_Complete
SI-BZK3-82 | TT_Task | (BOP) MANUFACTURING, SHOP TEST MV CABLES BZK | 26/08/2017 | 12/05/2018 | 25/08/2017 | 10/07/2018 | 0 | TK_Complete
SI-BZK3-84 | TT_FinMile | (BOP) (RFS) READY FOR SHIPMENT MV CABLES BZK | 01/07/2018 | 01/07/2018 | 31/07/2018 | 31/07/2018 | 0 | TK_Complete
SI-BZK3-86 | TT_Task | (BOP) FINAL CHECK BEFORE SHIPMENT MV CABLES BZK | 18/06/2018 | 01/07/2018 | 27/06/2018 | 10/07/2018 | 0 | TK_Complete
SI-BZK4-62 | TT_Task | (BOP) TRANSPORT MV CABLES BZK | 02/07/2018 | 30/08/2018 | 03/08/2018 | 20/08/2018 | 0 | TK_Complete
SI-MBH2-10 | TT_Task | (BOP) TECHNICAL CLARIFICATION HYDROGEN SUPPLY SYSTEM | 01/05/2017 | 11/06/2017 | 22/04/2017 | 02/06/2017 | 0 | TK_Complete
SI-MBH2-15 | TT_Task | (BOP) BASIC DESIGN, SPECIFICATION HYDROGEN SUPPLY SYSTEM (incl. FSD COMPLIANCE CHECK) | 28/06/2017 | 07/09/2017 | 03/06/2017 | 13/08/2017 | 0 | TK_Complete
SI-MBH2-20 | TT_FinMile | (BOP) RFQ HYDROGEN SUPPLY SYSTEM | 14/09/2017 | 14/09/2017 | 13/08/2017 | 13/08/2017 | 0 | TK_Complete
SI-MBH2-25 | TT_Task | (BOP) QUOTATION STAGE HYDROGEN SUPPLY SYSTEM | 15/09/2017 | 26/10/2017 | 14/08/2017 | 24/09/2017 | 0 | TK_Complete
SI-MBH2-30 | TT_Mile | (BOP) ORDER PLACED HYDROGEN SUPPLY SYSTEM | 26/09/2017 | 26/09/2017 | 25/09/2017 | 25/09/2017 | 0 | TK_Complete
SI-MBH3-90 | TT_Task | (BOP) MANUFACTURING, SHOP TEST HYDROGEN SUPPLY SYSTEM | 26/09/2017 | 02/06/2018 | 25/09/2017 | 11/05/2018 | 0 | TK_Complete
SI-MBH3-92 | TT_FinMile | (BOP) (RFS) READY FOR SHIPMENT HYDROGEN SUPPLY SYSTEM | 08/07/2018 | 08/07/2018 | 11/05/2018 | 11/05/2018 | 0 | TK_Complete
SI-MBH4-60 | TT_Task | (BOP) TRANSPORT HYDROGEN SUPPLY SYSTEM | 09/07/2018 | 06/09/2018 | 12/05/2018 | 13/07/2018 | 0 | TK_Complete
SI-MKG2-32 | TT_Task | (BOP) TECHNICAL CLARIFICATION CO2 SUPPLY SYSTEM | 01/05/2017 | 11/06/2017 | 22/04/2017 | 02/06/2017 | 0 | TK_Complete
SI-MKG2-35 | TT_Task | (BOP) BASIC DESIGN, SPECIFICATION CO2 SUPPLY SYSTEM (incl. FSD COMPLIANCE CHECK) | 28/06/2017 | 07/09/2017 | 03/06/2017 | 13/08/2017 | 0 | TK_Complete
SI-MKG2-40 | TT_FinMile | (BOP) RFQ CO2 SUPPLY SYSTEM | 14/09/2017 | 14/09/2017 | 13/08/2017 | 13/08/2017 | 0 | TK_Complete
SI-MKG2-45 | TT_Task | (BOP) QUOTATION STAGE CO2 SUPPLY SYSTEM | 15/09/2017 | 26/10/2017 | 14/08/2017 | 24/09/2017 | 0 | TK_Complete
SI-MKG2-50 | TT_Mile | (BOP) ORDER PLACED CO2 SUPPLY SYSTEM | 26/09/2017 | 26/09/2017 | 25/09/2017 | 25/09/2017 | 0 | TK_Complete
SI-MKG3-94 | TT_Task | (BOP) MANUFACTURING, SHOP TEST CO2 SUPPLY SYSTEM | 26/09/2017 | 02/06/2018 | 25/09/2017 | 11/05/2018 | 0 | TK_Complete
SI-MKG3-96 | TT_FinMile | (BOP) (RFS) READY FOR SHIPMENT CO2 SUPPLY SYSTEM | 08/07/2018 | 08/07/2018 | 11/05/2018 | 11/05/2018 | 0 | TK_Complete
SI-MKG4-62 | TT_Task | (BOP) TRANSPORT CO2 SUPPLY SYSTEM | 09/07/2018 | 06/09/2018 | 12/05/2018 | 13/07/2018 | 0 | TK_Complete
SI0EG-2-87 | TT_Task | (BOP) TECHNICAL CLARIFICATION FUEL OIL FORWARDING SYSTEM EG (incl. PUMPS) | 14/02/2017 | 20/03/2017 | 04/02/2017 | 10/03/2017 | 0 | TK_Complete
SI0EG-2-89 | TT_Task | (BOP) QUOTATION STAGE FUEL OIL FORWARDING SYSTEM EG (incl. PUMPS) | 20/06/2017 | 14/08/2017 | 26/05/2017 | 20/08/2017 | 0 | TK_Complete
SI0EG-2-93 | TT_Mile | (BOP) ORDER PLACED FUEL OIL FORWARDING SYSTEM EG (incl. PUMPS) | 13/09/2017 | 13/09/2017 | 21/08/2017 | 21/08/2017 | 0 | TK_Complete
SI0EG-2-99 | TT_Task | (BOP) BASIC DESIGN, PREPARATION RFQ FUEL OIL FORWARDING SYSTEM EG (incl. PUMPS) | 26/03/2017 | 13/05/2017 | 11/03/2017 | 25/05/2017 | 0 | TK_Complete
SI0EG-3-82 | TT_Task | (BOP) DETAIL DESIGN, MANUFACTURING, SHOP TEST FUEL OIL FORWARDING SYSTEM EG (incl. PUMPS) | 13/09/2017 | 27/06/2018 | 21/08/2017 | 28/03/2018 | 0 | TK_Complete
SI0EG-3-84 | TT_FinMile | (BOP) (RFS) READY FOR SHIPMENT FUEL OIL FORWARDING SYSTEM EG (incl. PUMPS) | 02/07/2018 | 02/07/2018 | 26/05/2018 | 26/05/2018 | 0 | TK_Complete
SI0EG-4-42 | TT_Task | (BOP) TRANSPORT FUEL OIL FORWARDING SYSTEM EG (incl. PUMPS) | 03/07/2018 | 31/08/2018 | 27/05/2018 | 30/06/2018 | 0 | TK_Complete
SI0EG-4-46 | TT_FinMile | (OTD-OS) (BOP) ON SITE FUEL FUEL OIL FORWARDING SYSTEM EG (incl. PUMPS) | 31/08/2018 | 31/08/2018 | 30/06/2018 | 30/06/2018 | 0 | TK_Complete
SI0PUN2-20 | TT_Task | (BOP) BASIC DESIGN, PREPARATION RFQ SEAWATER BOOSTER PUMP | 03/05/2017 | 04/07/2017 | 03/04/2017 | 04/06/2017 | 0 | TK_Complete
SI0PUN2-25 | TT_Task | (BOP) QUOTATION STAGE SEAWATER BOOSTER PUMP | 30/06/2017 | 24/08/2017 | 05/06/2017 | 31/08/2017 | 0 | TK_Complete
SI0PUN2-40 | TT_Mile | (BOP) ORDER PLACED SEAWATER BOOSTER PUMP | 26/03/2018 | 26/03/2018 | 26/02/2018 | 26/02/2018 | 0 | TK_Complete
SI0PUN2-47 | TT_Task | (BOP) TECHNICAL CLARIFICATION SEAWATER BOOSTER PUMP | 01/03/2017 | 04/04/2017 | 27/02/2017 | 02/04/2017 | 0 | TK_Complete
SI0PUN3-35 | TT_Task | (BOP) DETAIL DESIGN, MANUFACTURING, SHOP TESTSEAWATER BOOSTER PUMP | 26/03/2018 | 09/08/2018 | 26/02/2018 | 15/11/2018 | 0 | TK_Complete
SI0PUN3-50 | TT_FinMile | (BOP) (RFS) READY FOR SHIPMENT SEAWATER BOOSTER PUMP | 18/08/2018 | 18/08/2018 | 22/11/2018 | 22/11/2018 | 0 | TK_Complete
SI0PUN4-55 | TT_Task | (BOP) TRANSPORT SEAWATER BOOSTER PUMP | 19/08/2018 | 06/10/2018 | 23/11/2018 | 27/11/2018 | 0 | TK_Complete
SI0PUN4-62 | TT_FinMile | (OTD-OS) (BOP) ON SITE SEAWATER BOOSTER PUMP | 06/10/2018 | 06/10/2018 | 27/11/2018 | 27/11/2018 | 0 | TK_Complete
SI-SCB2-20 | TT_Task | (BOP) BASIC DESIGN, SPECIFICATION COMPRESSED AIR INTERCONNECTION SYSTEM | 19/07/2017 | 29/08/2017 | 24/06/2017 | 04/08/2017 | 0 | TK_Complete
SI-SCB2-25 | TT_Task | (BOP) TECHNICAL CLARIFICATION COMPRESSED AIR INTERCONNECTION SYSTEM | 01/06/2017 | 12/07/2017 | 13/05/2017 | 23/06/2017 | 0 | TK_Complete
SI-SCB2-30 | TT_FinMile | (BOP) RFQ COMPRESSED AIR INTERCONNECTION SYSTEM | 05/09/2017 | 05/09/2017 | 04/08/2017 | 04/08/2017 | 0 | TK_Complete
SI-SCB2-35 | TT_Task | (BOP) QUOTATION STAGE COMPRESSED AIR INTERCONNECTION SYSTEM | 06/09/2017 | 17/10/2017 | 05/08/2017 | 24/09/2017 | 0 | TK_Complete
SI-SCB2-40 | TT_Mile | (BOP) ORDER PLACED COMPRESSED AIR INTERCONNECTION SYSTEM | 26/09/2017 | 26/09/2017 | 25/09/2017 | 25/09/2017 | 0 | TK_Complete
SI-SCB3-45 | TT_Task | (BOP) MANUFACTURING, SHOP TEST COMPRESSED AIR INTERCONNECTION SYSTEM | 26/09/2017 | 07/07/2018 | 25/09/2017 | 31/07/2018 | 0 | TK_Complete
SI-SCB3-50 | TT_FinMile | (BOP) (RFS) READY FOR SHIPMENT COMPRESSED AIR INTERCONNECTION SYSTEM | 03/08/2018 | 03/08/2018 | 31/07/2018 | 31/07/2018 | 0 | TK_Complete
SI-SCB4-66 | TT_Task | (BOP) TRANSPORT COMPRESSED AIR INTERCONNECTION SYSTEM | 04/08/2018 | 02/10/2018 | 01/08/2018 | 15/08/2018 | 0 | TK_Complete
SI-GHD2-20 | TT_Task | (BOP) BASIC DESIGN, SPECIFICATION WATER PIPEWORK SYSTEM | 08/05/2017 | 02/07/2017 | 08/04/2017 | 27/06/2017 | 0 | TK_Complete
SI-GHD2-25 | TT_FinMile | (BOP) RFQ WATER PIPEWORK SYSTEM | 26/07/2017 | 26/07/2017 | 27/06/2017 | 27/06/2017 | 0 | TK_Complete
SI-GHD2-30 | TT_Task | (BOP) QUOTATION STAGE WATER PIPEWORK SYSTEM | 27/07/2017 | 06/09/2017 | 28/06/2017 | 24/09/2017 | 0 | TK_Complete
SI-GHD2-35 | TT_Mile | (BOP) ORDER PLACED WATER PIPEWORK SYSTEM | 26/09/2017 | 26/09/2017 | 25/09/2017 | 25/09/2017 | 0 | TK_Complete
SI-GHD2-37 | TT_Task | (BOP) TECHNICAL CLARIFICATION WATER PIPEWORK SYSTEM | 01/03/2017 | 11/04/2017 | 25/02/2017 | 07/04/2017 | 0 | TK_Complete
SI-GHD3-40 | TT_Task | (BOP) MANUFACTURING, SHOP TEST WATER PIPEWORK SYSTEM | 26/09/2017 | 03/07/2018 | 25/09/2017 | 11/05/2018 | 0 | TK_Complete
SI-GHD3-50 | TT_FinMile | (BOP) (RFS) READY FOR SHIPMENT WATER PIPEWORK SYSTEM | 14/07/2018 | 14/07/2018 | 11/05/2018 | 11/05/2018 | 0 | TK_Complete
SI-GHD4-64 | TT_Task | (BOP) TRANSPORT WATER PIPEWORK SYSTEM | 15/07/2018 | 12/09/2018 | 12/05/2018 | 13/07/2018 | 0 | TK_Complete
SI-PAS2-39 | TT_Task | (BOP) TECHNICAL CLARIFICATION NOX WATER INJECTION PUMP | 01/03/2017 | 11/04/2017 | 25/02/2017 | 07/04/2017 | 0 | TK_Complete
SI-PAS2-41 | TT_Task | (BOP) BASIC DESIGN, SPECIFICATION NOX WATER INJECTION PUMP | 08/05/2017 | 02/07/2017 | 08/04/2017 | 02/06/2017 | 0 | TK_Complete
SI-PAS2-43 | TT_FinMile | (BOP) RFQ NOX WATER INJECTION PUMP | 27/06/2017 | 27/06/2017 | 02/06/2017 | 02/06/2017 | 0 | TK_Complete
SI-PAS2-45 | TT_Task | (BOP) QUOTATION STAGE NOX WATER INJECTION PUMP | 28/06/2017 | 08/08/2017 | 03/06/2017 | 31/08/2017 | 0 | TK_Complete
SI-PAS2-47 | TT_Mile | (BOP) ORDER PLACED NOX WATER INJECTION PUMP | 26/01/2018 | 26/01/2018 | 27/12/2017 | 27/12/2017 | 0 | TK_Complete
SI-PAS3-52 | TT_Task | (BOP) MANUFACTURING, SHOP TEST NOX WATER INJECTION PUMP | 26/01/2018 | 11/08/2018 | 27/12/2017 | 15/10/2018 | 0 | TK_Complete
SI-PAS3-54 | TT_FinMile | (BOP) (RFS) READY FOR SHIPMENT NOX WATER INJECTION PUMP | 18/08/2018 | 18/08/2018 | 15/10/2018 | 15/10/2018 | 0 | TK_Complete
SI-PAS4-64 | TT_Task | (BOP) TRANSPORT NOX WATER INJECTION PUMP | 19/08/2018 | 06/10/2018 | 19/10/2018 | 25/10/2018 | 0 | TK_Complete
SI-PAS4-68 | TT_FinMile | (OTD-OS) (BOP) ON SITE NOX WATER INJECTION PUMP | 06/10/2018 | 06/10/2018 | 25/10/2018 | 25/10/2018 | 0 | TK_Complete
COMM | TT_Mile | Commencement of Works (Day 1) | 29/05/2017 | 29/05/2017 | 29/05/2017 | 29/05/2017 | 0 | TK_Complete
COMP | TT_FinMile | Completion of Works (Day 947) (SA1) | 01/01/2020 | 01/01/2020 | 31/12/2019 | 31/12/2019 | 0 | TK_Complete
_LOI | TT_Mile | Letter of Intent (LOI) | 23/05/2017 | 23/05/2017 | 23/05/2017 | 23/05/2017 | 0 | TK_Complete
CW1.3 | TT_FinMile | Complete Removal of Temp. Bulk head at Seawall Outfall | 01/01/2020 | 01/01/2020 | 23/12/2019 | 23/12/2019 | 0 | TK_Complete
KD_A02XX | TT_FinMile | A2 - Complete Site Clearance and Establishment Works | 11/09/2017 | 11/09/2017 | 08/09/2017 | 08/09/2017 | 0 | TK_Complete
KD_A99XX | TT_FinMile | Completion of Section A of the Works (Day 90) | 16/10/2017 | 16/10/2017 | 08/09/2017 | 08/09/2017 | 0 | TK_Complete
CW1.1 | TT_FinMile | Pump Station Structural Completion (= M&amp;E Access) | 02/06/2019 | 02/06/2019 | 12/05/2019 | 12/05/2019 | 0 | TK_Complete
KD_B01XX | TT_FinMile | B1 - Complete Foundation Structures and Pile Caps for Stack, Diffuser and HRSG Main Plant with Lift and Staircase Towers | 15/03/2018 | 15/03/2018 | 31/01/2018 | 31/01/2018 | 0 | TK_Complete
KD_B04XX | TT_FinMile | B4 - Install Southern Section of UG large diameter Intake &amp; Discharge CWP and finish ground surface for machinery access | 09/04/2019 | 09/04/2019 | 12/02/2019 | 12/02/2019 | 0 | TK_Complete
KD_B05XX | TT_FinMile | B5 - Construct Condensate Pit | 26/11/2018 | 26/11/2018 | 22/11/2018 | 22/11/2018 | 0 | TK_Complete
KD_B06XX | TT_FinMile | B6 - Construct Turboset foundation and supporting pile cap | 23/04/2018 | 23/04/2018 | 20/04/2018 | 20/04/2018 | 0 | TK_Complete
KD_B07XX | TT_FinMile | B7 - Construct pile caps, tie beams and G/F slab for Turbine Hall Building | 26/11/2018 | 26/11/2018 | 30/09/2018 | 30/09/2018 | 0 | TK_Complete
KD_B08XX | TT_FinMile | B8 - Construct supporting structure for O/H Cranes of Turbine Hall incl. associated roof structures &amp; partial side walls | 26/06/2018 | 26/06/2018 | 27/05/2018 | 27/05/2018 | 0 | TK_Complete
KD_B09XX | TT_FinMile | B9 - Complete Underground Earthing and Lightning Protection Installation inside the Turbine Hall | 26/11/2018 | 26/11/2018 | 09/09/2018 | 09/09/2018 | 0 | TK_Complete
KD_B10XX | TT_FinMile | B10 - Complete Underground Drainage Works inside the Turbine Hall | 26/01/2019 | 26/01/2019 | 22/11/2018 | 22/11/2018 | 0 | TK_Complete
KD_B99XX | TT_FinMile | Completion of Section B of the Works (Day 255) | 09/04/2019 | 09/04/2019 | 12/02/2019 | 12/02/2019 | 0 | TK_Complete
CW1.2 | TT_FinMile | Cooling Water System Ready to Provide Water | 01/01/2020 | 01/01/2020 | 24/12/2019 | 24/12/2019 | 0 | TK_Complete
KD_C01XX | TT_FinMile | C1 - Construct Crane Walkway, Condensate Pit and Condenser Platforms within Turbine Hall Building | 31/03/2019 | 31/03/2019 | 19/03/2019 | 19/03/2019 | 0 | TK_Complete
KD_C03XX | TT_FinMile | C3 - Construct Polishing Pit , ALL foundations, G/F slab for Condensate Polishing Plant area of Turbine Hall | 26/11/2018 | 26/11/2018 | 30/09/2018 | 30/09/2018 | 0 | TK_Complete
KD_C04XX | TT_FinMile | C4 - Install and T&amp;C two 250t O/H cranes within Turbine Hall and H/O to M&amp;E Contractor | 26/11/2018 | 26/11/2018 | 31/08/2018 | 31/08/2018 | 0 | TK_Complete
KD_C05XX | TT_FinMile | C5 - Construct trench between Condenser and Condensate Polishing Pit | 26/11/2018 | 26/11/2018 | 30/09/2018 | 30/09/2018 | 0 | TK_Complete
KD_C06XX | TT_FinMile | C6 - Construct foundations &amp; plinths for support steel structure for A/G sections of CWP to the south of Turbine Hall | 09/04/2019 | 09/04/2019 | 07/03/2019 | 07/03/2019 | 0 | TK_Complete
KD_C07XX | TT_FinMile | C7 - Complete ALL civil works incl. foundations, pile cap, fire walls &amp; hard standings for Generator Transformer Area | 09/04/2019 | 09/04/2019 | 18/02/2019 | 18/02/2019 | 0 | TK_Complete
KD_C08XX | TT_FinMile | C8 - Install Middle Section of U/G large diameter Intake &amp; Discharge CWP and finish surface ground for machinery access | 03/09/2018 | 03/09/2018 | 03/09/2018 | 03/09/2018 | 0 | TK_Complete
1.2 | TT_FinMile | Utilites Trench | 31/03/2019 | 31/03/2019 | 14/02/2019 | 14/02/2019 | 0 | TK_Complete
1.3 | TT_FinMile | Gas Pipeline Trench | 31/03/2019 | 31/03/2019 | 14/02/2019 | 14/02/2019 | 0 | TK_Complete
1.4 | TT_FinMile | Gas Blending Skid Area Foundation | 31/03/2019 | 31/03/2019 | 29/01/2019 | 29/01/2019 | 0 | TK_Complete
1.5 | TT_FinMile | Utilities Trench | 31/03/2019 | 31/03/2019 | 14/02/2019 | 14/02/2019 | 0 | TK_Complete
3.1 | TT_FinMile | Underground Cable Corridor incl. LV Transformer Fdn | 31/03/2019 | 31/03/2019 | 12/02/2019 | 12/02/2019 | 0 | TK_Complete
3.2 | TT_FinMile | Neutralization Pit | 26/01/2019 | 26/01/2019 | 31/12/2018 | 31/12/2018 | 0 | TK_Complete
3.3a | TT_FinMile | Generator Transformer Foundation | 04/02/2019 | 04/02/2019 | 25/01/2019 | 25/01/2019 | 0 | TK_Complete
3.3b | TT_FinMile | Generator Transformer Blast Wall | 09/04/2019 | 09/04/2019 | 12/02/2019 | 12/02/2019 | 0 | TK_Complete
3.4 | TT_FinMile | Excitation Transfomer Foundation | 31/03/2019 | 31/03/2019 | 30/01/2019 | 30/01/2019 | 0 | TK_Complete
3.5 | TT_FinMile | Unit Transformer Foundation | 31/03/2019 | 31/03/2019 | 04/02/2019 | 04/02/2019 | 0 | TK_Complete
KD_D04XX | TT_FinMile | D4 - Construct Duct Bank between Switchgear Building and Generator Transformer Area | 31/03/2019 | 31/03/2019 | 12/02/2019 | 12/02/2019 | 0 | TK_Complete
KD_D05XX | TT_FinMile | D5 - Construct Boiler Blow Down Pit | 26/11/2018 | 26/11/2018 | 17/08/2018 | 17/08/2018 | 0 | TK_Complete
KD_D06XX | TT_FinMile | D6 - Complete foundations and plinths for ALL equipment, pipe bridge and sleeper way to the west of HRSG Area | 26/01/2019 | 26/01/2019 | 31/12/2018 | 31/12/2018 | 0 | TK_Complete
KD_D08XX | TT_FinMile | D8 - Complete foundations and plinths for LV Auxiliary Power Transformers | 31/03/2019 | 31/03/2019 | 04/02/2019 | 04/02/2019 | 0 | TK_Complete
KD_D11XX | TT_FinMile | D11 - Complete foundations and plinths for Close Cooling Water Structure | 09/04/2019 | 09/04/2019 | 04/03/2019 | 04/03/2019 | 0 | TK_Complete
KD_E02XX | TT_FinMile | E2 - Complete ALL outdoor pipe trenches including 10UEZ01, 10UEZ02 and 10UGZ | 31/03/2019 | 31/03/2019 | 14/02/2019 | 14/02/2019 | 0 | TK_Complete
KD_E04XX | TT_FinMile | E4 - Complete foundation &amp; plinths for Fuel Gas Pruge Air, Gas Receiving Station, Fuel Gas Blending System | 31/03/2019 | 31/03/2019 | 29/01/2019 | 29/01/2019 | 0 | TK_Complete
KD_E08XX | TT_FinMile | E8 - Deferred Works Item 01 (p.r.t. Act ID DEF_WK01) | 26/11/2018 | 26/11/2018 | 05/08/2018 | 05/08/2018 | 0 | TK_Complete
TH1.3 | TT_FinMile | Turbine Hall all round inner skin (GL.1-5) | 31/03/2019 | 31/03/2019 | 31/01/2019 | 31/01/2019 | 0 | TK_Complete
TH2.2 | TT_FinMile | North Elevation (GL1-5) | 31/03/2019 | 31/03/2019 | 29/01/2019 | 29/01/2019 | 0 | TK_Complete
KD_F02XX | TT_FinMile | F2 - Complete Oil Contaminated Drainage System incl' external drainage, oil interceptor and pipe trenches | 09/04/2019 | 09/04/2019 | 14/02/2019 | 14/02/2019 | 0 | TK_Complete
KD_F08bXX | TT_FinMile | F8b - Deferred Works Item 03 (p.r.t. Act ID DEF_WK03) | 26/01/2019 | 26/01/2019 | 14/11/2018 | 14/11/2018 | 0 | TK_Complete
KD_F08eXX | TT_FinMile | F8e - Deferred Works Item 07 (p.r.t. Act ID DEF_WK07) | 26/01/2019 | 26/01/2019 | 15/12/2018 | 15/12/2018 | 0 | TK_Complete
TH2.3 | TT_FinMile | Kalzip (Dog House &amp; Curved Areas) | 01/08/2019 | 01/08/2019 | 14/06/2019 | 14/06/2019 | 0 | TK_Complete
TH2.4 | TT_FinMile | West Elevation (GL5) | 31/03/2019 | 31/03/2019 | 28/02/2019 | 28/02/2019 | 0 | TK_Complete
TH2.5 | TT_FinMile | East side elevation GL1 | 01/05/2019 | 01/05/2019 | 30/04/2019 | 30/04/2019 | 0 | TK_Complete
TH2.6 | TT_FinMile | South Elevation (GL1-5) | 31/03/2019 | 31/03/2019 | 28/02/2019 | 28/02/2019 | 0 | TK_Complete
TH3.1 | TT_FinMile | North Elevation (GL5-10) | 01/05/2019 | 01/05/2019 | 01/04/2019 | 01/04/2019 | 0 | TK_Complete
TH3.2 | TT_FinMile | West Elevation (GL10) | 01/08/2019 | 01/08/2019 | 30/03/2019 | 30/03/2019 | 0 | TK_Complete
TH3.6 | TT_FinMile | Kalzip Roof (GL7-10) | 01/01/2020 | 01/01/2020 | 21/10/2019 | 21/10/2019 | 0 | TK_Complete
KD_G07bXX | TT_FinMile | G7b - Deferred Works Item 09 (p.r.t. Act ID DEF_WK09) | 26/01/2019 | 26/01/2019 | 31/12/2018 | 31/12/2018 | 0 | TK_Complete
TH3.3 | TT_FinMile | West Elevation (GL7) | 01/01/2020 | 01/01/2020 | 25/10/2019 | 25/10/2019 | 0 | TK_Complete
TH3.3A | TT_FinMile | West Elevation water tight (GL7) | 31/03/2019 | 31/03/2019 | 31/03/2019 | 31/03/2019 | 0 | TK_Complete
TH3.4 | TT_FinMile | South Elevation (GL5-10) | 01/05/2019 | 01/05/2019 | 29/03/2019 | 29/03/2019 | 0 | TK_Complete
TH3.4A | TT_FinMile | South Elevation water tight (GL5-10) | 31/03/2019 | 31/03/2019 | 14/03/2019 | 14/03/2019 | 0 | TK_Complete
SW1.1 | TT_FinMile | Completion of all site works | 22/02/2020 | 22/02/2020 | 08/09/2020 | 08/09/2020 | 0 | TK_Complete
1.1 | TT_FinMile | Urea Plant Area | 26/01/2019 | 26/01/2019 | 11/01/2019 | 11/01/2019 | 0 | TK_Complete
2.1 | TT_FinMile | Remaining Feedwater Pump Foundation | 26/01/2019 | 26/01/2019 | 31/12/2018 | 31/12/2018 | 0 | TK_Complete
2.2 | TT_FinMile | Condensate Recirculating Pump Foundation | 26/01/2019 | 26/01/2019 | 31/12/2018 | 31/12/2018 | 0 | TK_Complete
2.3 | TT_FinMile | Remaining HRSG West Foundation | 26/01/2019 | 26/01/2019 | 31/12/2018 | 31/12/2018 | 0 | TK_Complete
2.4 | TT_FinMile | Diesel Generator Foundation (Shaft F Area) | 01/08/2019 | 01/08/2019 | 02/07/2019 | 02/07/2019 | 0 | TK_Complete
2.5 | TT_FinMile | Gas Preheating Skid Area Foundation | 05/08/2019 | 05/08/2019 | 04/05/2019 | 04/05/2019 | 0 | TK_Complete
3.6 | TT_FinMile | Main CW collection piece (UPY00Y) and Cooling Water Pump Foundations (PxB00Y) | 09/04/2019 | 09/04/2019 | 07/03/2019 | 07/03/2019 | 0 | TK_Complete
3.7 | TT_FinMile | Rain Collection Pump Station Structural Completion (Top Slab) | 26/01/2019 | 26/01/2019 | 07/01/2019 | 07/01/2019 | 0 | TK_Complete
4.1 | TT_FinMile | HRSG South Remaining Foundations and Drainage | 01/05/2019 | 01/05/2019 | 12/04/2019 | 12/04/2019 | 0 | TK_Complete
4.2 | TT_FinMile | HRSG East Remaining Foundation (incl. Fdn for Urea Decomposition Chamber) | 01/08/2019 | 01/08/2019 | 29/06/2019 | 29/06/2019 | 0 | TK_Complete
P1_Rooms | TT_FinMile | Priority 1 Rooms | 26/01/2019 | 26/01/2019 | 01/01/2019 | 01/01/2019 | 0 | TK_Complete
P2_Rooms | TT_FinMile | Priority 2 Rooms | 31/03/2019 | 31/03/2019 | 05/02/2019 | 05/02/2019 | 0 | TK_Complete
P3_Rooms | TT_FinMile | Priority 3 Rooms | 31/03/2019 | 31/03/2019 | 30/03/2019 | 30/03/2019 | 0 | TK_Complete
TH1.1 | TT_FinMile | GL5-7 [Mechanical Annex] - Access for E&amp;M | 25/02/2019 | 25/02/2019 | 18/12/2018 | 18/12/2018 | 0 | TK_Complete
TH1.2 | TT_FinMile | GL7-10 [SwitchGear Block] - Concrete roof (under air intake) GL E-L poured | 26/01/2019 | 26/01/2019 | 29/12/2018 | 29/12/2018 | 0 | TK_Complete
TH2.1 | TT_FinMile | Kalzip Roof | 26/01/2019 | 26/01/2019 | 29/12/2018 | 29/12/2018 | 0 | TK_Complete
TH3.1A | TT_FinMile | North Elevation water tight (GL5-10) | 26/01/2019 | 26/01/2019 | 19/01/2019 | 19/01/2019 | 0 | TK_Complete
TH3.2A | TT_FinMile | West Elevation water tight (GL10) - Elect Rooms | 31/03/2019 | 31/03/2019 | 04/02/2019 | 04/02/2019 | 0 | TK_Complete
TH3.5 | TT_FinMile | Kalzip Roof (GL5-7) | 26/01/2019 | 26/01/2019 | 15/01/2019 | 15/01/2019 | 0 | TK_Complete
TH4.1 | TT_FinMile | Turbine Hall Lift operational with EMSD lift certificate | 30/01/2020 | 30/01/2020 | 12/03/2020 | 12/03/2020 | 0 | TK_Complete
MS-01-1XX | TT_FinMile | MS-01-1 / Execute Contract | 29/05/2017 | 29/05/2017 | 29/05/2017 | 29/05/2017 | 0 | TK_Complete
MS_01XX | TT_FinMile | MS-01 / Achievement of Milestone Requirements | 31/05/2017 | 31/05/2017 | 31/05/2017 | 31/05/2017 | 0 | TK_Complete
MS-02-1XX | TT_FinMile | MS-02-1 / Excute Articles of Agreement | 07/12/2017 | 07/12/2017 | 06/12/2017 | 06/12/2017 | 0 | TK_Complete
MS-02-2XX | TT_FinMile | MS-02-2 / Submit to CLP Temp. Works for Shaft A, Pump Station, Diversion Culvert (Wall Only) | 02/11/2017 | 02/11/2017 | 16/11/2017 | 16/11/2017 | 0 | TK_Complete
MS-02-3XX | TT_FinMile | MS-02-3 / Submit to CLP Temp. Works for Shaft D (Wall, Excav &amp; ELS) | 15/06/2017 | 15/06/2017 | 15/06/2017 | 15/06/2017 | 0 | TK_Complete
MS-02-4XX | TT_FinMile | MS-02-4 / Submit to CLP Temp. Works for Shaft F (Skin Wall) &amp; Double Pipe Trench (Southern Sheet Pile) | 21/06/2017 | 21/06/2017 | 21/06/2017 | 21/06/2017 | 0 | TK_Complete
MS-02-5XX | TT_FinMile | MS-02-5 / Submit to CLP Temp. Works for Shaft F &amp; Doble Pipe Trench (Open Cut Alternative) | 21/06/2017 | 21/06/2017 | 21/06/2017 | 21/06/2017 | 0 | TK_Complete
MS-02-6XX | TT_FinMile | MS-02-6 / Submit to CLP Temp. Works for Power Island (Open Cut Amendment) | 21/06/2017 | 21/06/2017 | 21/06/2017 | 21/06/2017 | 0 | TK_Complete
MS_02XX | TT_FinMile | MS-02 / Achievement of Milestone Requirements | 28/08/2017 | 28/08/2017 | 08/08/2017 | 08/08/2017 | 0 | TK_Complete
MS-03-1XX | TT_FinMile | MS-03-1 / Submit to CLP Temp. Works for Shaft A, Pump Station, Diversion Culvert (Excav. &amp; ELS) | 29/11/2017 | 29/11/2017 | 05/12/2017 | 05/12/2017 | 0 | TK_Complete
MS-03-2XX | TT_FinMile | MS-03-2 / Submit to CLP Temp. Works for Shaft E &amp; Discharge Culvert (Wall, Excav. &amp; ELS) | 15/08/2017 | 15/08/2017 | 20/07/2017 | 20/07/2017 | 0 | TK_Complete
MS-03-3XX | TT_FinMile | MS-03-3 / Submit to CLP Temp. Bulkhead Design for Outfall Apron Modification | 06/01/2018 | 06/01/2018 | 16/11/2017 | 16/11/2017 | 0 | TK_Complete
MS_03XX | TT_FinMile | MS-03 / Achievement of Milestone Requirements | 23/04/2018 | 23/04/2018 | 16/11/2017 | 16/11/2017 | 0 | TK_Complete
MS-04-1XX | TT_FinMile | MS-04-1 / Complete Section A Works | 23/10/2017 | 23/10/2017 | 08/09/2017 | 08/09/2017 | 0 | TK_Complete
MS-04-2XX | TT_FinMile | MS-04-2 / Award Subcontract - Excavation &amp; ELS | 15/12/2017 | 15/12/2017 | 22/12/2017 | 22/12/2017 | 0 | TK_Complete
MS-04-3XX | TT_FinMile | MS-04-3 / Award Subcontract - Grouting and Sheet / Pipe Piling | 28/08/2017 | 28/08/2017 | 26/08/2017 | 26/08/2017 | 0 | TK_Complete
MS-04-4XX | TT_FinMile | MS-04-4 / Award Subcontract - Steel Structures &amp; Heaving Lifting | 24/10/2017 | 24/10/2017 | 24/10/2017 | 24/10/2017 | 0 | TK_Complete
MS-04-5XX | TT_FinMile | MS-04-5 / Award Subcontract - Standing Seam Roof, Aluminium Cladding &amp; Curtain Wall | 23/04/2018 | 23/04/2018 | 20/12/2017 | 20/12/2017 | 0 | TK_Complete
MS-04-6XX | TT_FinMile | MS-04-6 / Award Subcontract - CWP Installation | 26/05/2018 | 26/05/2018 | 04/04/2018 | 04/04/2018 | 0 | TK_Complete
MS-04-7XX | TT_FinMile | MS-04-7 / Issue Purchase Order - CW Pipes | 23/04/2018 | 23/04/2018 | 25/01/2018 | 25/01/2018 | 0 | TK_Complete
MS-04-8XX | TT_FinMile | MS-04-8 / Award Subcontract - Building Services | 23/04/2018 | 23/04/2018 | 20/02/2018 | 20/02/2018 | 0 | TK_Complete
MS_04XX | TT_FinMile | MS-04 / Achievement of Milestone Requirements | 26/05/2018 | 26/05/2018 | 04/04/2018 | 04/04/2018 | 0 | TK_Complete
MS-05-1XX | TT_FinMile | MS-05-1 / Submit to CLP Temp. Works for SCW &amp; Intake Culvert Modification (Wall only) | 11/09/2017 | 11/09/2017 | 19/09/2017 | 19/09/2017 | 0 | TK_Complete
MS-05-2XX | TT_FinMile | MS-05-2 / Submit to CLP Temp. Works for SCW &amp; Intake Culvert Modification (Excav. &amp; ELS) | 11/09/2017 | 11/09/2017 | 19/09/2017 | 19/09/2017 | 0 | TK_Complete
MS-05-3XX | TT_FinMile | MS-05-3 / Issue Purchase Order - CW Pipes | 23/04/2018 | 23/04/2018 | 25/01/2018 | 25/01/2018 | 0 | TK_Complete
MS_05XX | TT_FinMile | MS-05 / Achievement of Milestone Requirements | 23/04/2018 | 23/04/2018 | 25/01/2018 | 25/01/2018 | 0 | TK_Complete
MS-06-1XX | TT_FinMile | MS-06-1 / Delivery of All CWP for Southern Section | 26/05/2018 | 26/05/2018 | 27/04/2018 | 27/04/2018 | 0 | TK_Complete
MS-06-2XX | TT_FinMile | MS-06-2 / First Delivery of Turbine Hall Structural Steelwork | 09/12/2017 | 09/12/2017 | 08/12/2017 | 08/12/2017 | 0 | TK_Complete
MS_06XX | TT_FinMile | MS-06 / Achievement of Milestone Requirements | 26/05/2018 | 26/05/2018 | 27/04/2018 | 27/04/2018 | 0 | TK_Complete
MS-06aXX | TT_FinMile | MS-06a-1/ First Delivery of Turbine Hall Roof / Wall Cladding | 23/04/2018 | 23/04/2018 | 21/03/2018 | 21/03/2018 | 0 | TK_Complete
MS_06aXX | TT_FinMile | MS-06a / Achievement of Milestone Requirements | 23/04/2018 | 23/04/2018 | 21/03/2018 | 21/03/2018 | 0 | TK_Complete
MS-06bXX | TT_FinMile | MS-06b-1 / First Delivery of Turbine Hall Curtain Wall / Glazing | 26/01/2019 | 26/01/2019 | 10/01/2019 | 10/01/2019 | 0 | TK_Complete
MS_06bXX | TT_FinMile | MS-06b / Achievement of Milestone Requirements | 26/01/2019 | 26/01/2019 | 10/01/2019 | 10/01/2019 | 0 | TK_Complete
MS-06c-1XX | TT_FinMile | MS-06c-1 / Pumping Station (Complete Pumping Test and Report Submission to BD) | 26/01/2019 | 26/01/2019 | 31/12/2018 | 31/12/2018 | 0 | TK_Complete
MS-06c-2XX | TT_FinMile | MS-06c-2 / Shaft F Excavation to -11mPD | 26/01/2019 | 26/01/2019 | 20/01/2019 | 20/01/2019 | 0 | TK_Complete
MS_06cXX | TT_FinMile | MS-06c / Achievement of Milestone Requirements | 26/01/2019 | 26/01/2019 | 20/01/2019 | 20/01/2019 | 0 | TK_Complete
MS-07-1XX | TT_FinMile | MS-07-1 / Complete Turboset Foundation and Supporting Pile Cap | 23/04/2018 | 23/04/2018 | 20/04/2018 | 20/04/2018 | 0 | TK_Complete
MS-07-2XX | TT_FinMile | MS-07-2 / Complete All Foundation for Stack, Diffuser and HRSG | 26/05/2018 | 26/05/2018 | 31/01/2018 | 31/01/2018 | 0 | TK_Complete
MS_07XX | TT_FinMile | MS-07 / Achievement of Milestone Requirements | 23/04/2018 | 23/04/2018 | 20/04/2018 | 20/04/2018 | 0 | TK_Complete
MS-08XX | TT_FinMile | MS08-1 / Complete Supporting Structures for Overhead Cranes of Turbine Hall Building incl. Associated Roof Structures | 26/07/2018 | 26/07/2018 | 12/07/2018 | 12/07/2018 | 0 | TK_Complete
MS_08XX | TT_FinMile | MS-08 / Achievement of Milestone Requirements | 26/07/2018 | 26/07/2018 | 12/07/2018 | 12/07/2018 | 0 | TK_Complete
MS-09-1XX | TT_FinMile | MS-09-1 / Complete Southern Section of CW Trench | 04/02/2019 | 04/02/2019 | 02/01/2019 | 02/01/2019 | 0 | TK_Complete
MS-09-2XX | TT_FinMile | MS-09-2 / Complete Condensate Pit | 26/11/2018 | 26/11/2018 | 09/09/2018 | 09/09/2018 | 0 | TK_Complete
MS-09-3XX | TT_FinMile | MS-09-3 / Pile Caps, Tie Beams and Ground Floor Slab for Turbine Hall Bldg | 29/11/2018 | 29/11/2018 | 30/09/2018 | 30/09/2018 | 0 | TK_Complete
MS_09XX | TT_FinMile | MS-09 / Achievement of Milestone Requirements | 04/02/2019 | 04/02/2019 | 02/01/2019 | 02/01/2019 | 0 | TK_Complete
MS-10-1XX | TT_FinMile | MS-10-1 / Complete Crane Walkway and Platforms within Turbine Hall | 31/03/2019 | 31/03/2019 | 19/03/2019 | 19/03/2019 | 0 | TK_Complete
MS-10-3XX | TT_FinMile | MS-10-3 / Complete Condensate Polishing Pit | 26/11/2018 | 26/11/2018 | 09/09/2018 | 09/09/2018 | 0 | TK_Complete
MS-10-4XX | TT_FinMile | MS-10-4 / Install 2 nos of 250t Overhead Crane | 26/11/2018 | 26/11/2018 | 31/08/2018 | 31/08/2018 | 0 | TK_Complete
MS-10-5XX | TT_FinMile | MS-10-5 / Complete All Civil Works for Generator Transformer Area | 09/04/2019 | 09/04/2019 | 18/02/2019 | 18/02/2019 | 0 | TK_Complete
MS-12-1XX | TT_FinMile | MS-12-1 / TBM Delivery to Site | 26/11/2018 | 26/11/2018 | 26/08/2018 | 26/08/2018 | 0 | TK_Complete
CWS-2BA5 | TT_Task | BA5 - Approval to GBP Amendment CW System - Diversion Culvert, Pump Station, Discharge Culvert, Shaft F, etc {4a1} | 06/07/2017 | 04/08/2017 | 27/06/2017 | 25/07/2017 | 0 | TK_Complete
CWS-2BA8XX | TT_FinMile | BA8 - Consent to GBP Amendment Cooling Water System Part 1 - Diversion Culvert, Pump Station | 01/01/2020 | 01/01/2020 | 22/10/2019 | 22/10/2019 | 0 | TK_Complete
CWS_2BA5XX | TT_FinMile | BA5 - Approval to GBP Amendment Cooling Water System Part 2 - Shaft F, Seal Pit, Discharge Culvert | 05/07/2017 | 05/07/2017 | 05/07/2017 | 05/07/2017 | 0 | TK_Complete
CWS_2BA8XX | TT_FinMile | BA8 - Consent to GBP Amendment Cooling Water System Part 2 - Shaft F, Seal Pit, Discharge Culvert | 01/01/2020 | 01/01/2020 | 10/05/2019 | 10/05/2019 | 0 | TK_Complete
CWSd1BA5 | TT_Task | BA5 - (1st) BD Approval to Cooling Water System Permanent Drainage Plan {4d} | 09/08/2017 | 08/10/2017 | 26/06/2017 | 22/08/2017 | 0 | TK_Complete
CWSd1BA8 | TT_Task | BA8 - (1st) BD Consent to Cooling Water System Permanent Drainage Plan {4d} - actual dates TBC | 26/08/2017 | 24/09/2017 | 23/08/2017 | 21/09/2017 | 0 | TK_Complete
CWSd2BA5 | TT_Task | BA5 - Approval to (Minor) Amendment for Cooling Water System Permanent Drainage Plan {4di} | 01/03/2018 | 30/04/2018 | 29/03/2018 | 18/04/2018 | 0 | TK_Complete
CWSd2BA8 | TT_FinMile | BA8 - Consent to (Minor) Amendment for Cooling Water System Permanent Drainage Plan {4di} [WITHDRAWN] | 01/06/2019 | 01/06/2019 | 27/03/2019 | 27/03/2019 | 0 | TK_Complete
CWSd3BA5 | TT_Task | BA5 - Approval to 2nd (Minor) Amendment for Cooling Water System Permanent Drainage Plan {4dii} | 01/06/2019 | 01/06/2019 | 02/05/2019 | 27/05/2019 | 0 | TK_Complete
CWSd3BA8 | TT_Task | BA8 - Consent to 2nd (Minor) Amendment for Cooling Water System Permanent Drainage Plan {4dii} | 02/08/2019 | 29/08/2019 | 13/06/2019 | 22/07/2019 | 0 | TK_Complete
DBCp1BA5 | TT_Task | BA5 - (1st) BD Approval for Permanent Works for Discharge Box Culvert {4c1} | 23/08/2017 | 22/10/2017 | 14/07/2017 | 12/09/2017 | 0 | TK_Complete
DBCp1BA8 | TT_Task | BA8 - (1st) BD Consent to Permanent Works for Discharge Box Culvert {4c1} - actual dates TBC | 13/09/2017 | 12/10/2017 | 13/09/2017 | 12/10/2017 | 0 | TK_Complete
DBCp2BA5 | TT_Task | BA5 - Approval to (Minor) Amendment for Permanent Works for Discharge Box Culvert {4c1i}[WITHDRAWN] | 08/12/2017 | 02/01/2018 | 08/12/2017 | 02/01/2018 | 0 | TK_Complete
DBCp2BA5a | TT_Task | BA5 - Approval to (Minor) Amendment for Permanent Works for Discharge Box Culvert {4c1i(r1)}[RESUBMISSION#1] | 06/03/2018 | 05/04/2018 | 02/01/2018 | 25/01/2018 | 0 | TK_Complete
DBCp2BA8 | TT_Task | BA8 - Consent to (Major) Amendment for Permanent Works for Discharge Box Culvert {4c1i(r1)} - actual date TBC | 06/04/2018 | 05/05/2018 | 26/01/2018 | 24/02/2018 | 0 | TK_Complete
PPSp1BA5 | TT_Task | BA5 - (1st) BD Approval to Permanent Works for Pump Station, Diversion Culvert {4c1} | 07/08/2017 | 06/10/2017 | 14/07/2017 | 12/09/2017 | 0 | TK_Complete
PPSp1BA8 | TT_Task | BA8 - (1st) BD Consent to Permanent Works for Pump Station, Diversion Culvert {4c1} - actual dates TBC | 13/09/2017 | 12/10/2017 | 13/09/2017 | 12/10/2017 | 0 | TK_Complete
PPSp2BA5 | TT_Task | BA5 - Approval to (Minor) Amendment for Permanent Works for Pump Station, Diversion Culvert {4c1i}[WITHDRAWN] | 08/12/2017 | 07/01/2018 | 08/12/2017 | 02/01/2018 | 0 | TK_Complete
PPSp2BA5a | TT_Task | BA5 - Approval to (Minor) Amendment for Permanent Works for Pump Sttn, Diver.Culvert {4c1i(r1)}[RESUMIT#1] | 26/02/2018 | 28/03/2018 | 02/01/2018 | 25/01/2018 | 0 | TK_Complete
PPSp2BA8 | TT_Task | BA8 - Consent to (Major) Amendment for Permanent Works for Pump Station, Diversion Culvert {4c1i(r1)} | 26/02/2018 | 27/03/2018 | 26/01/2018 | 24/02/2018 | 0 | TK_Complete
SEAp1BA5 | TT_Task | BA5 - (1st) BD Aprpoval to Permanent works for Seal Pit (4c2} | 23/08/2017 | 22/10/2017 | 18/08/2017 | 16/10/2017 | 0 | TK_Complete
SEAp1BA8 | TT_Task | BA8 - (1st) BD Consent to Permanent works for Seal Pit {4c2} - actual dates TBC | 18/10/2017 | 16/11/2017 | 17/10/2017 | 15/11/2017 | 0 | TK_Complete
SEAp2BA5 | TT_Task | BA5 - Approval to (Major) Amendment for Permanent works for Seal Pit {4c2i} | 26/02/2018 | 28/03/2018 | 19/01/2018 | 13/02/2018 | 0 | TK_Complete
SEAp2BA8 | TT_Task | BA8 - Consent to (Major) Amendment for Permanent works for Seal Pit {4c2i} - actual dates TBC | 29/03/2018 | 27/04/2018 | 14/02/2018 | 15/03/2018 | 0 | TK_Complete
SFFp1BA5 | TT_Task | BA5 - (1st) BD Approval to Permanent works for Shaft F {4c2} | 23/08/2017 | 22/10/2017 | 18/08/2017 | 16/10/2017 | 0 | TK_Complete
SFFp1BA8 | TT_Task | BA8 - (1st) BD Consent to Permanent works for Shaft F {4c2} - actual dates TBC | 18/10/2017 | 16/11/2017 | 17/10/2017 | 15/11/2017 | 0 | TK_Complete
SFFp2BA5 | TT_Task | BA5 - Approval to (Major) Amendment for Permanent works for Shaft F {4c2i} | 26/02/2018 | 28/03/2018 | 19/01/2018 | 13/02/2018 | 0 | TK_Complete
SFFp2BA8 | TT_Task | BA8 - Consent to (Major) Amendment for Permanent works for Shaft F {4c2i} | 29/03/2018 | 27/04/2018 | 14/02/2018 | 15/03/2018 | 0 | TK_Complete
SFAt1BA5 | TT_Task | BA5 - (1st) BD Approval to Temporary works for Shaft A, Pump Station, Diversion Culvert (Wall Only) {4b4} | 11/06/2017 | 09/08/2017 | 11/04/2017 | 15/06/2017 | 0 | TK_Complete
SFAt1BA8 | TT_Task | BA8 - (1st) BD Consent toTemporary works for Shaft A, Pump Station, Diversion Culvert (Wall Only) {4b4} | 07/08/2017 | 03/09/2017 | 16/06/2017 | 13/07/2017 | 0 | TK_Complete
SFAt1BA8a | TT_Task | BA5 &amp; BA8 - BD Amendment (Type II) - Shaft A Location Shift {4b4-1} | 07/08/2017 | 03/09/2017 | 10/07/2017 | 07/08/2017 | 0 | TK_Complete
SFDt1BA5 | TT_Task | BA5 - (1st) BD Approval to Temporary works for Shaft D (with LCAL's proposal incorporated) [DISAPPROVED] {4b3(r1)} | 16/08/2017 | 15/10/2017 | 21/06/2017 | 16/08/2017 | 0 | TK_Complete
SFEt1BA5 | TT_FinMile | BA5 - (1st) BD Approval toTemporary works for Shaft E and Discharge Culvert {4b2(r)} | 22/04/2017 | 22/04/2017 | 02/05/2017 | 02/05/2017 | 0 | TK_Complete
SFFt1BA5 | TT_FinMile | BA5 - (1st) BD Approval to Temporary works for Shaft F and Double Pipe Trench {4b1(r)} | 22/04/2017 | 22/04/2017 | 04/05/2017 | 04/05/2017 | 0 | TK_Complete
SFFt1BA8 | TT_Task | BA8 - (1st) BD Consent to Temporary works for Shaft F and Double Pipe Trench (for Shaft F Wall only) {4b1(r)} | 03/07/2017 | 03/07/2017 | 05/05/2017 | 21/06/2017 | 0 | TK_Complete
SFFtABA5 | TT_FinMile | BA5 - (1st) BD Approval to Temp works for Shaft F &amp; Double Pipe Trench (Alternative for Zone A Sheet Pile) {4b1-alt A} | 24/05/2017 | 24/05/2017 | 23/05/2017 | 23/05/2017 | 0 | TK_Complete
SFFtABA8 | TT_Task | BA8 - (1st) BD Consent to Temp works for Shaft F &amp; Double Pipe Trench (Alternative for Zone A Sheet Pile) {4b1-alt A} | 03/07/2017 | 03/07/2017 | 24/05/2017 | 21/06/2017 | 0 | TK_Complete
SFJt1BA5 | TT_Task | BA5 - Amendment to Temp works for Shaft F &amp; Double Pipe Trench - Pipe Jacking [DISAPPROVED] {4b1-1} | 03/07/2017 | 31/08/2017 | 19/05/2017 | 10/07/2017 | 0 | TK_Complete
SFJt1BA5a | TT_Task | BA5 - Resubmission of Amendment (Type II) for Shaft F &amp; DPT master construction sequence {4b1-1(r)} | 22/06/2017 | 21/08/2017 | 24/07/2017 | 22/08/2017 | 0 | TK_Complete
SFJt2BA5 | TT_Task | BA5 - Resubmission for Shaft F(Ring Beam) &amp; Double Pipe Trench Amendment - Pipe Jacking {4b1-2} | 07/09/2017 | 06/11/2017 | 18/09/2017 | 22/11/2017 | 0 | TK_Complete
SFJt2BA8 | TT_Task | BA8 - Consent for Shaft F(Ring Beam) &amp; Double Pipe Trench Amendment - Pipe Jacking {4b1-2} | 05/12/2017 | 04/01/2018 | 28/11/2017 | 28/12/2017 | 0 | TK_Complete
SCW_1BA5 | TT_FinMile | BA5 - (1st) BD Approval to GBP for SCW Pump Sump A&amp;A {5a} | 29/04/2017 | 29/04/2017 | 04/05/2017 | 04/05/2017 | 0 | TK_Complete
SCW_2BA5 | TT_Task | BA5 - Approval to (Major) Amendment for GBP for SCW Pump Sump A&amp;A {5a1} AF-TBC | 23/04/2018 | 23/05/2018 | 06/03/2018 | 05/04/2018 | 0 | TK_Complete
SCWd1BA5 | TT_Task | BA5 - (1st) BD Approval to Drainage Plan for SCW and Culvert Modification {5d} | 09/08/2017 | 08/10/2017 | 26/06/2017 | 22/08/2017 | 0 | TK_Complete
SCWd1BA8 | TT_Task | BA8 - (1st) BD Consent to Draiange Plan for SCW and Culvert Modification {5d} - actual dates TBC | 28/08/2017 | 24/09/2017 | 08/03/2018 | 06/04/2018 | 0 | TK_Complete
SCWd2BA5XX | TT_Task | BA5 - Approval to (Major) Amendment for Drainage Plan for SCW and Culvert Modification {5di} actual dates TBC | 10/12/2017 | 08/02/2018 | 30/03/2018 |  | 2920 | TK_Active
SCWp1BA5 | TT_Task | BA5 - (1st) BD Approval to Permanent works for SCW and Culvert Modification {5c} [DISAPPROVED] | 10/11/2017 | 09/01/2018 | 01/12/2017 | 22/01/2018 | 0 | TK_Complete
SCWp1BA8 | TT_Task | BA8 - (1st) BD Consent to Permanent works for SCW and Culvert Modification {5c} [CANCELLED] | 30/04/2018 | 29/05/2018 | 22/01/2018 | 22/01/2018 | 0 | TK_Complete
SCWp2BA5 | TT_Task | BA5 - Approval to (Major) Amendment for Permanent works for SCW and Culvert Modification {5c(r)} [RESUBMISSION] | 23/04/2018 | 22/06/2018 | 05/03/2018 | 11/05/2018 | 0 | TK_Complete
SCWp2BA8 | TT_Task | BA8 - Consent to (Major) Amendment for Permanent works for SCW and Culvert Modification {5c(r)} [RESUBMISSION] | 31/03/2019 | 29/04/2019 | 23/11/2018 | 19/12/2018 | 0 | TK_Complete
SCWt1BA5 | TT_Task | BA5 - (1st) BD Approval to Temporary works for SCW and Culvert Modification (Wall only) [DISAPPROVED] {5b1} | 31/05/2017 | 18/07/2017 | 24/05/2017 | 11/07/2017 | 0 | TK_Complete
SCWtaBA5 | TT_Task | BA5 - (1st) BD Approval to Temp works for SCW &amp; Culvert Modification (Resubmit incl wall, excav.&amp; anchor)(Wet){5b1(r)} | 29/08/2017 | 28/10/2017 | 20/09/2017 | 24/11/2017 | 0 | TK_Complete
SCWtaBA8 | TT_Task | BA8 - (1st) BD Consent to Temp works for SCW &amp; Culvert Modification (Resubmit incl wall, excav.&amp; anchor)(Wet){5b1(r)} | 26/02/2018 | 27/03/2018 | 29/01/2018 | 26/02/2018 | 0 | TK_Complete
ICM_1BA5 | TT_Task | BA5 - (1st) BD Approval to GBP for Outfall Modification (incl' works outside lot boundary) [p.r.t.Act.ID.CWS-2BA5] {6a} | 07/08/2017 | 04/09/2017 | 27/06/2017 | 25/07/2017 | 0 | TK_Complete
ICMp1BA5 | TT_Task | BA5 - (1st) BD Approval to Permenent Works for Outfall Modification (incl' works outside lot boundary) {6c} [WITHDRAWN] | 08/12/2017 | 06/02/2018 | 02/01/2018 | 25/01/2018 | 0 | TK_Complete
ICMp1BA8 | TT_Task | BA8 - (1st) BD Consent to Permanent Works for Outfall Modification (incl' works outside lot boundary) {6c} | 26/02/2018 | 27/03/2018 | 26/01/2018 | 24/02/2018 | 0 | TK_Complete
ICMp2BA5 | TT_Task | BA5 - Approval to (Major) Amendment for Permenent Works for Outfall Modif (incl' works outside lot boundary){6ci} AD-TBC | 28/04/2018 | 27/06/2018 | 08/03/2018 | 07/05/2018 | 0 | TK_Complete
ICMp2BA8 | TT_Task | BA8 - Consent to (Major) Amendment for Permanent Works for Outfall Modif (incl' works outside lot boundary) {6ci} AD-TBC | 10/06/2018 | 09/07/2018 | 08/05/2018 | 06/08/2018 | 0 | TK_Complete
ICMt1BA5 | TT_Task | BA5 - (1st) BD Approval to Temp.Works for Outfall Modif (incl' works outside lot boundary) {6b incl in 4b2-2}[APPROVED] | 26/02/2018 | 27/04/2018 | 14/02/2018 | 24/04/2018 | 0 | TK_Complete
ICMt1BA8 | TT_Task | BA8 - (1st) BD Consent to Temp.Works for Outfall Modif (incl' works outside lot boundary) {6b incl in 4b2-2} | 11/06/2018 | 08/07/2018 | 04/05/2018 | 06/07/2018 | 0 | TK_Complete
POW-1BA5 | TT_FinMile | BA5 - (1st) BD Approval to GBP Amendment for Turbine Hall and HRSG incl' outdoor equipment structures {7a1} | 15/08/2017 | 15/08/2017 | 04/05/2017 | 04/05/2017 | 0 | TK_Complete
POWd1BA5 | TT_Task | BA5 - (1st) BD Approval to Drainage Plans for Power Island Areas {8a} | 10/07/2017 | 30/08/2017 | 10/05/2017 | 30/06/2017 | 0 | TK_Complete
POWd1BA8 | TT_Task | BA8 - (1st) BD Consent to Drainage Plans for Power Island Areas {8a} | 07/08/2017 | 05/09/2017 | 01/08/2017 | 31/08/2017 | 0 | TK_Complete
SBHS2BA5 | TT_FinMile | BA5 - Approval to 1st Amendment (Major) for substructures of HRSG and Stack {7b1} | 31/03/2017 | 31/03/2017 | 19/04/2017 | 19/04/2017 | 0 | TK_Complete
SBHS2BA8 | TT_FinMile | BA8 - Consent to 1st Amendment for (Major) substructures of HRSG and Stack {7b1} | 02/07/2017 | 02/07/2017 | 27/06/2017 | 27/06/2017 | 0 | TK_Complete
SBHS3BA5 | TT_Task | BA5 - Approval to 2nd Amendment (Type II) for substructures of HRSG and Stack {7b2} | 07/08/2017 | 06/09/2017 | 30/06/2017 | 26/07/2017 | 0 | TK_Complete
SBHS3BA8 | TT_Task | BA8 - Consent to 2nd Amendment (Type II) for substructures of HRSG and Stack {7b2} | 06/09/2017 | 05/10/2017 | 30/06/2017 | 26/07/2017 | 0 | TK_Complete
SBOE1BA5 | TT_FinMile | BA5 - BD Approval to Structural Plan (Package 1) for Outdoor Equipment foundations and plinths [WITHDRAWN] {7f} | 26/05/2017 | 26/05/2017 | 19/05/2017 | 19/05/2017 | 0 | TK_Complete
SBOE2BA5 | TT_Task | BA5 - Approval to Resubmission of Structural Plan (Package 1) for Outdoor Equipment foundations and plinths {7f(r)} | 07/08/2017 | 06/10/2017 | 31/07/2017 | 27/09/2017 | 0 | TK_Complete
SBOE2BA8 | TT_Task | BA8 - (1st) BD Consent to Structural Plan (Package 1) for Outdoor Equipment foundations and plinths {7f(r)} | 30/09/2017 | 29/10/2017 | 08/02/2018 | 07/03/2018 | 0 | TK_Complete
SBOE3BA5 | TT_Task | BA5 - BD Approval to Structural Plan (Package 2) for Outdoor Equipment foundations and plinths {7g} | 30/10/2017 | 29/12/2017 | 30/10/2017 | 29/12/2017 | 0 | TK_Complete
SBOE3BA8 | TT_Task | BA8 - BD Consent to Structural Plan (Package 2) for Outdoor Equipment foundations and plinths {7g} | 03/04/2018 | 02/05/2018 | 08/02/2018 | 07/03/2018 | 0 | TK_Complete
SBTH2BA5 | TT_FinMile | BA5 - Approval to 1st Amendment (Major) for pile caps and tie beams within Turbine Hall {7b1} | 31/03/2017 | 31/03/2017 | 19/04/2017 | 19/04/2017 | 0 | TK_Complete
SBTH2BA8 | TT_FinMile | BA8 - Consent to 1st Amendment (Major) for pile caps and tie beams within Turbine Hall {7b1} | 02/07/2017 | 02/07/2017 | 27/06/2017 | 27/06/2017 | 0 | TK_Complete
SBTH3BA5 | TT_Task | BA5 - Approval to 2nd Amendment (Type II) for pile caps and tie beams within Turbine Hall {7b2} | 07/08/2017 | 06/09/2017 | 30/06/2017 | 26/07/2017 | 0 | TK_Complete
SBTH3BA8 | TT_Task | BA8 - Consent to 2nd Amendment (Type II) for pile caps and tie beams within Turbine Hall {7b2} | 07/08/2017 | 05/09/2017 | 30/06/2017 | 26/07/2017 | 0 | TK_Complete
SPHS1BA5XX | TT_FinMile | BA5 - (1st) BD Approval to Structural Plan for superstructures of HRSG, Stack, Stair Towers, Rack &amp; Platforms | 02/07/2017 | 02/07/2017 | 30/06/2017 | 30/06/2017 | 0 | TK_Complete
SPSB2BA5 | TT_Task | BA5 - Approval to (2nd) Amendment for superstructures for Turbine Hall {7d2} | 15/06/2017 | 14/07/2017 | 19/06/2017 | 18/07/2017 | 0 | TK_Complete
SPTH2BA5 | TT_Task | BA5 - Approval to (1st) Amendment for superstructures for Turbine Hall {7d1} | 26/05/2017 | 24/06/2017 | 25/04/2017 | 24/05/2017 | 0 | TK_Complete
SPTH3BA5XX | TT_FinMile | BA5 - Approval to (Minor) Amendment for superstructures for Turbine Hall {7d1} | 02/07/2017 | 02/07/2017 | 01/07/2017 | 01/07/2017 | 0 | TK_Complete
SPTH3BA8 | TT_Task | BA8 - Consent to Amendment for superstructures for Turbine Hall {7d2} | 07/08/2017 | 05/09/2017 | 19/07/2017 | 01/08/2017 | 0 | TK_Complete
SPTHaBA5XX | TT_FinMile | BA5 - (1st) BD Approval to Structural Plan for maintenance platforms and pipe racks within Turbine Hall | 14/07/2017 | 14/07/2017 | 14/07/2017 | 14/07/2017 | 0 | TK_Complete
THCL1BA5 | TT_Task | BA5 - (1st) BD Approval to Cladding Plan for Turbine Hall (incl' Switchgear Block) [DISAPPROVED] {7e} | 07/08/2017 | 05/10/2017 | 09/05/2017 | 04/07/2017 | 0 | TK_Complete
THCL2BA5 | TT_Task | BA5 - Approval to Resubmission of Cladding Plan for Turbine Hall (incl' Switchgear Block) [WITHDRWN] {7e(r1)} | 11/08/2017 | 10/10/2017 | 15/08/2017 | 12/10/2017 | 0 | TK_Complete
THCL2BA5a | TT_Task | BA5 - Approval to Resubmission of Cladding Plan for Turbine Hall (incl' Switchgear Block) {7e(r2)} | 11/08/2017 | 10/10/2017 | 12/10/2017 | 05/12/2017 | 0 | TK_Complete
THCL2BA5b | TT_Task | BA5 - Approval to 1st Amendment of Cladding Plan for Turbine Hall (incl' Switchgear Block) {7e(r2)(i)} | 11/08/2017 | 10/10/2017 | 15/02/2018 | 15/03/2018 | 0 | TK_Complete
THCL2BA8 | TT_Task | BA8 - (1st) BD Consent to Cladding Plan for Turbine Hall (incl' Switchgear Block) {7e(r2)} AD-TBC | 16/03/2018 | 14/04/2018 | 16/03/2018 | 14/04/2018 | 0 | TK_Complete
POWe1BA5 | TT_FinMile | BA5 - (1st) BD Approval to ELS Plans for substructures {7c2} | 21/05/2017 | 21/05/2017 | 19/05/2017 | 19/05/2017 | 0 | TK_Complete
POWe1BA8 | TT_FinMile | BA8 - (1st) BD Consent to ELS Plans for substructures {7c2} | 25/06/2017 | 25/06/2017 | 14/07/2017 | 14/07/2017 | 0 | TK_Complete
SFA-BA58 | TT_Task | BA5 - Amendment (Minor) for Temporary works for Shaft A, Pump Station, Diversion Culvert (Wall Only){4b4-2}[WITHDRAWN] | 03/11/2017 | 01/01/2018 | 16/11/2017 | 11/12/2017 | 0 | TK_Complete
SFA-BA58a | TT_Task | BA5 - Amendment (Minor) for Temp.works for Shaft A, Pump Station, Diversion Culvert (Wall Only){4b4-2(r1)} [WITHDRAWN] | 27/11/2017 | 25/12/2017 | 21/12/2017 | 02/01/2018 | 0 | TK_Complete
SFA-BA58a1 | TT_Task | BA5 - Amendment (Minor) for Temp.works for Shaft A, Pump Sttn, Div. Culvert (Wall Only){4b4-2(r2)} | 27/11/2017 | 25/12/2017 | 02/01/2018 | 30/01/2018 | 0 | TK_Complete
SFA-BA58b | TT_Task | BA8 - Consent for Temporary works for Shaft A, Pump Station, Diversion Culvert (Wall Only){4b4-2(r1)} [N.A.] | 26/02/2018 | 25/03/2018 | 30/01/2018 | 30/01/2018 | 0 | TK_Complete
SFA_BA58 | TT_Task | BA5 - Amendment (Major) for Temporary works for Shaft A, Pump Station, Diversion Culvert (Excav &amp; ELS) {4b5}[WITHDRAWN] | 30/11/2017 | 28/02/2018 | 05/12/2017 | 11/12/2017 | 0 | TK_Complete
SFA_BA58a | TT_Task | BA5 - Amendment (Major) for Temp.works for Shaft A, Pump Station, Diversion Culvert (Excav &amp; ELS) {4b4-3} [WITHDRAWN] | 12/03/2018 | 11/05/2018 | 14/02/2018 | 23/03/2018 | 0 | TK_Complete
SFA_BA58a1 | TT_Task | BA5 - Amendment (Minor) for Temp.works for Shaft A, Pump Station, Diversion Culvert (Excav &amp; ELS) {4b4-3(r1)} [APPROVED] | 12/03/2018 | 10/04/2018 | 23/03/2018 | 24/04/2018 | 0 | TK_Complete
SFA_BA58b | TT_Task | BA5 - Consent for Temporary works for Shaft A, Pump Station, Diversion Culvert (Excav &amp; ELS) {4b4-4} | 26/05/2018 | 22/06/2018 | 28/06/2018 | 25/07/2018 | 0 | TK_Complete
SFD_BA05 | TT_Task | BA5 - Resubmission of Temp works for Shaft D (Wall Only) {4b3(r2)} | 06/10/2017 | 04/12/2017 | 09/10/2017 | 15/12/2017 | 0 | TK_Complete
SFD_BA05a | TT_Task | BA5 - Resubmission of Temp works for Shaft D (Excav &amp; ELS) {4b3(r2)-1} | 23/04/2018 | 21/06/2018 | 13/03/2018 | 15/05/2018 | 0 | TK_Complete
SFDt1BA8 | TT_Task | BA8 - (1st) Consent for Shaft D (Pipe Pile Wall &amp; Grout Curtain) {4b3(r2)} | 26/02/2018 | 27/03/2018 | 19/01/2018 | 12/02/2018 | 0 | TK_Complete
SFDt1BA8a | TT_Task | BA8 - Consent for Shaft D (Excav &amp; ELS) {4b3a(r2)-1}[WITHDRAWN] | 14/06/2018 | 11/07/2018 | 21/05/2018 | 18/06/2018 | 0 | TK_Complete
SFE-BA58 | TT_Task | BA5 &amp; BA8 - Amendment (Major) for Temp.works for Shaft E &amp; Discharge Culvert (alt sheet pile)[WITHDRAWN]{4b2-1} | 04/11/2017 | 03/12/2017 | 21/07/2017 | 08/09/2017 | 0 | TK_Complete
SFE_BA58 | TT_Task | BA5 &amp; BA8 - Amendment (Type II) for Temp.works for Shaft E &amp; Discharge Culvert (Wall only){4b2-1(r)} | 06/10/2017 | 04/12/2017 | 06/10/2017 | 03/11/2017 | 0 | TK_Complete
SFE_BA58a | TT_Task | BA5 - Amendment (pipe jacking) for Temp.works for Shaft E &amp; Discharge Culvert (Excav. &amp; ELS){4b2-2) [WITHDRAWN] | 26/02/2018 | 27/04/2018 | 14/02/2018 | 23/03/2018 | 0 | TK_Complete
SFE_BA58a1 | TT_Task | BA5 - Amendment (pipe jacking) for Temp.works for Shaft E &amp; Discharge Culvert (Excav. &amp; ELS){4b2-2(r1)} {APPROVED] | 26/02/2018 | 27/03/2018 | 23/03/2018 | 24/04/2018 | 0 | TK_Complete
SFE_BA58b | TT_Task | BA8 - Consent (pipe jacking) for Temp.works for Shaft E &amp; Discharge Culvert (Excav. &amp; ELS){4b2-2(r1)} | 11/06/2018 | 08/07/2018 | 04/05/2018 | 06/07/2018 | 0 | TK_Complete
SFF-BA58 | TT_Task | BA5 &amp; BA8 - Amendment to Zone A Sheet Pile Alternative [WITHDRA WN] {4b1i} | 22/06/2017 | 21/07/2017 | 23/06/2017 | 07/07/2017 | 0 | TK_Complete
SFF-BA58a | TT_Task | BA5 - Resub.of (Type II) Amendment for Zone A Sheet Pile Alternative {4b1-alt A-1} [APPROVED AS TYPE I] | 27/11/2017 | 26/12/2017 | 24/07/2017 | 22/08/2017 | 0 | TK_Complete
SFF-BA58b | TT_Task | BA8 - Consnet for Zone A Sheet Pile Alternative {4b1-alt A-1} | 22/06/2017 | 19/07/2017 | 29/08/2017 | 25/09/2017 | 0 | TK_Complete
SFF-BA58b1 | TT_Task | BA5 &amp; BA8 - Shaft F (Type II) Amendment - Delink Effluent Pit {4b1-4} [APPROVED] | 23/04/2018 | 22/05/2018 | 08/03/2018 | 10/04/2018 | 0 | TK_Complete
SFF-BA58b2 | TT_Task | BA5 &amp; BA8 - Shaft F (Type II) Amendment - Increase AAA Level and Pumping Test {4b1-5} [WITHDRAWAL] | 27/05/2018 | 23/06/2018 | 26/04/2018 | 18/05/2018 | 0 | TK_Complete
SFF-BA58b3 | TT_Task | BA5 &amp; BA8 - Shaft F (Type II) Amendment - Increase AAA Level and Pumping Test {4b1-5(r1)} | 27/05/2018 | 25/06/2018 | 18/05/2018 | 22/06/2018 | 0 | TK_Complete
SFF-BA58c | TT_Task | BA5 - Submission of Zone C / Resequencing (originally an Alternative but resubmitted &amp; approved as a Major Rev) {4b1-?} | 26/01/2019 | 26/03/2019 | 24/12/2018 | 06/03/2019 | 0 | TK_Complete
SFF-BA58d | TT_Task | BA8 - Consent for Zone C / Resequencing {4b1-?} | 27/04/2019 | 24/05/2019 | 25/02/2019 | 22/03/2019 | 0 | TK_Complete
SFF_BA58 | TT_Task | BA5 - Submission of Zone B Open Cut Alternative {4b1-alt B} [APPROVED] | 22/06/2017 | 19/09/2017 | 22/06/2017 | 18/08/2017 | 0 | TK_Complete
SFF_BA58a | TT_Task | BA8 - Consent for Zone B Open Cut Alternative {4b1-alt B} | 26/06/2018 | 23/07/2018 | 04/05/2018 | 26/06/2018 | 0 | TK_Complete
SCW-BA58 | TT_Task | BA5 - Alternative for Temp works for SCW &amp; Culvert Modifi (Wall Only)(Dry){5b1-alt} [DISAPPROVED] | 28/11/2017 | 26/01/2018 | 21/12/2017 | 06/02/2018 | 0 | TK_Complete
SCW_BA58 | TT_Task | BA5 - Alternative for Temp works for SCW &amp; Culvert Modif (Excav)(Dry){5b1-alt} [DISAPPROVED] | 28/11/2017 | 26/01/2018 | 21/12/2017 | 06/02/2018 | 0 | TK_Complete
POW_BA58 | TT_Task | BA5 &amp; BA8 - Amendment for Excav &amp; ELS Plan for Power Island Area (Open Cut)(Phase 1 &amp; 2){7c2i} | 22/06/2017 | 19/09/2017 | 22/06/2017 | 25/09/2017 | 0 | TK_Complete
POW_BA58_1 | TT_Task | BA8 - Consent for Excav &amp; ELS Plan for Power Island Area (Open Cut)(Phase 3){7c2i} | 22/06/2017 | 19/09/2017 | 26/09/2017 | 20/10/2017 | 0 | TK_Complete
POW_BA58_2 | TT_Task | BA5 &amp; BA8 -Type II Amendment Power Island Open Cut (Phase 1,2,3) {7c2ii} | 22/06/2017 | 19/09/2017 | 26/10/2017 | 23/11/2017 | 0 | TK_Complete
POW_BA58_3 | TT_Task | BA5 &amp; BA8 -Type II Amendment (for grout curtain) Power Island Open Cut (Phase 1,2,3){7c2iii} | 22/06/2017 | 19/09/2017 | 15/12/2017 | 09/01/2018 | 0 | TK_Complete
POW_BA58_4 | TT_Task | BA8 -Consent for Power Island Open Cut (Phase 4){7c2iii}[WITHDRAWN] | 23/04/2018 | 20/05/2018 | 04/05/2018 | 30/05/2018 | 0 | TK_Complete
GENSUB05 | TT_Task | Supervision Plans - Preparation and Submission to RO | 29/05/2017 | 11/06/2017 | 29/05/2017 | 11/06/2017 | 0 | TK_Complete
GENSUB06 | TT_Task | Supervision Plans - RO Review and Comment | 12/06/2017 | 18/06/2017 | 12/06/2017 | 18/06/2017 | 0 | TK_Complete
GENSUB10 | TT_Task | Structural Steel Shop Drawing &amp; Calculation - Preparation and Submission to RO (1st round) | 01/09/2017 | 28/09/2017 | 01/09/2017 | 02/11/2017 | 0 | TK_Complete
GENSUB11 | TT_Task | Structural Steel Shop Drawing &amp; Calculation - RO Review and Comment (1st round) | 13/11/2017 | 26/11/2017 | 03/11/2017 | 23/11/2017 | 0 | TK_Complete
GENSUB15 | TT_Task | Roof Cladding Shop Drawing &amp; Calculation - RO Review and Comment | 26/02/2018 | 11/03/2018 | 27/01/2018 | 05/02/2018 | 0 | TK_Complete
GENSUB16 | TT_Task | Roof Cladding Shop Drawing &amp; Calculation - RO Comment and Approval | 26/03/2018 | 08/04/2018 | 10/02/2018 | 13/02/2018 | 0 | TK_Complete
GENSUB20 | TT_Task | Irrigation Shop Drawing - RO Review and Comment | 08/03/2019 | 04/04/2019 | 24/03/2018 | 10/10/2018 | 0 | TK_Complete
GENSUB21 | TT_Task | Irrigation Shop Drawing - RO Comment and Approval | 19/04/2019 | 02/05/2019 | 20/07/2018 | 12/02/2019 | 0 | TK_Complete
GENSUB25 | TT_Task | Lift Shop Drawing - RO Review and Comment (AD TBC) | 14/06/2018 | 27/06/2018 | 14/06/2018 | 27/06/2018 | 0 | TK_Complete
GENSUB26 | TT_Task | Lift Shop Drawing - RO Comment and Approval (AD TBC) | 04/08/2018 | 10/08/2018 | 05/07/2018 | 11/07/2018 | 0 | TK_Complete
GENSUB30 | TT_Task | CWP Manufacturing Drawing - Preparation and Submission to RO | 26/02/2018 | 16/03/2018 | 31/12/2017 | 18/01/2018 | 0 | TK_Complete
GENSUB31 | TT_Task | CWP Manufacturing Drawing - RO Review and Comment | 17/03/2018 | 23/03/2018 | 19/01/2018 | 25/01/2018 | 0 | TK_Complete
GENSUB35 | TT_Task | Precast Concrete Intake Chamber - Submission of Quality Plan and Inspection Plan (Approval status TBC) | 26/11/2018 | 09/12/2018 | 03/08/2018 | 19/11/2018 | 0 | TK_Complete
GENSUB36 | TT_Task | Precast Concrete Intake Chamber Fabrication Drawing - Preparation and Submission to RO | 26/12/2018 | 24/01/2019 | 04/12/2018 | 31/12/2018 | 0 | TK_Complete
GENSUB37 | TT_Task | Precast Concrete Intake Chamber Fabrication Drawing - RO Review and Comment | 27/01/2019 | 25/02/2019 | 01/01/2019 | 31/01/2019 | 0 | TK_Complete
GENSUB40 | TT_Task | TTM for Pumping Station - Preparation and Submission to RO | 08/08/2017 | 21/08/2017 | 08/08/2017 | 07/09/2017 | 0 | TK_Complete
GENSUB40a | TT_Task | TTM for Pumping Station - RO Review and Comment [APPROVED] | 27/11/2017 | 10/12/2017 | 08/09/2017 | 29/11/2017 | 0 | TK_Complete
GENSUB40b | TT_Task | TTM for Pumping Station - Issue of LWC for barricading the areas | 27/11/2017 | 27/11/2017 | 30/11/2017 | 05/12/2017 | 0 | TK_Complete
GENSUB40c | TT_Task | TTM for Pumping Station - Barrication as per approved site layout and TTM | 27/11/2017 | 27/11/2017 | 05/12/2017 | 05/12/2017 | 0 | TK_Complete
GENSUB41 | TT_Task | TTM for Pumping Station - Declaration of unplanted area | 11/09/2017 | 24/09/2017 | 06/12/2017 | 16/12/2017 | 0 | TK_Complete
GENSUB50 | TT_Task | TTM for Shaft D - Preparation and Submission to RO | 16/12/2017 | 29/12/2017 | 08/08/2017 | 07/09/2017 | 0 | TK_Complete
GENSUB50a | TT_Task | TTM for Shaft D - RO Review and Comment [APPROVED] | 27/11/2017 | 10/12/2017 | 08/09/2017 | 27/12/2017 | 0 | TK_Complete
GENSUB50b | TT_Task | TTM for Shaft D - Issue of LWC to barricade the proposed temp. EVA location | 01/03/2018 | 01/03/2018 | 28/12/2017 | 28/12/2017 | 0 | TK_Complete
GENSUB50b1 | TT_Task | TTM for Shaft D - LWC 14 day expiry period | 01/03/2018 | 14/03/2018 | 29/12/2017 | 11/01/2018 | 0 | TK_Complete
GENSUB50c | TT_Task | TTM for Shaft D - Barrication as per approved temporary EVA location | 02/03/2018 | 07/03/2018 | 29/12/2017 | 03/01/2018 | 0 | TK_Complete
GENSUB50d | TT_Task | TTM for Shaft D - Issue of XP for EVA diversion | 08/03/2018 | 08/03/2018 | 04/01/2018 | 26/01/2018 | 0 | TK_Complete
GENSUB50d1 | TT_Task | TTM for Shaft D - Extend expired LWC | 08/03/2018 | 08/03/2018 | 27/01/2018 | 29/01/2018 | 0 | TK_Complete
GENSUB50e | TT_Task | TTM for Shaft D - Construct temporary EVA | 23/04/2018 | 26/04/2018 | 26/02/2018 | 01/03/2018 | 0 | TK_Complete
GENSUB50f | TT_Task | TTM for Shaft D - Issue of LWC to barricade the proposed site area | 27/04/2018 | 30/04/2018 | 02/03/2018 | 06/03/2018 | 0 | TK_Complete
GENSUB51 | TT_Task | TTM for Shaft D - Declaration of unplanted area | 01/05/2018 | 07/05/2018 | 07/03/2018 | 18/03/2018 | 0 | TK_Complete
GENSUB60 | TT_Task | TTM for Sea Bank Road - Preparation and Submission to RO | 31/08/2017 | 13/09/2017 | 08/08/2017 | 07/09/2017 | 0 | TK_Complete
GENSUB60a | TT_Task | TTM for Sea Bank Road - RO Review and Comment [APPROVED] | 27/11/2017 | 10/12/2017 | 08/09/2017 | 27/12/2017 | 0 | TK_Complete
GENSUB60b | TT_Task | TTM for Sea Bank Road - Issue of LWC to barricade the proposed hammer head locations | 01/03/2018 | 01/03/2018 | 28/12/2017 | 28/12/2017 | 0 | TK_Complete
GENSUB60b1 | TT_Task | TTM for Sea Bank Road - LWC 14 day expiry period | 01/03/2018 | 14/03/2018 | 29/12/2017 | 11/01/2018 | 0 | TK_Complete
GENSUB60c | TT_Task | TTM for Sea Bank Road - Barrication as per approved hammer head locations | 02/03/2018 | 07/03/2018 | 29/12/2017 | 03/01/2018 | 0 | TK_Complete
GENSUB60d | TT_Task | TTM for Sea Bank Road - Issue of XP for hammer heads construction | 08/03/2018 | 08/03/2018 | 04/01/2018 | 26/01/2018 | 0 | TK_Complete
GENSUB60d1 | TT_Task | TTM for Sea Bank Road - Extend expired LWC | 08/03/2018 | 08/03/2018 | 27/01/2018 | 29/01/2018 | 0 | TK_Complete
GENSUB60e | TT_Task | TTM for Sea Bank Road - Hammer heads construction | 01/03/2018 | 09/03/2018 | 29/01/2018 | 24/02/2018 | 0 | TK_Complete
GENSUB60f | TT_Task | TTM for Sea Bank Road - Issue of LWC to barricade the proposed site area | 23/04/2018 | 26/04/2018 | 02/03/2018 | 06/03/2018 | 0 | TK_Complete
GENSUB61 | TT_Task | TTM for Sea Bank Road - Declaration of unplanted area | 27/04/2018 | 03/05/2018 | 07/03/2018 | 18/03/2018 | 0 | TK_Complete
GENSUB80 | TT_Task | Wall Cladding Shop Drawing &amp; Calculation - RO Review and Comment | 23/04/2018 | 20/05/2018 | 24/02/2018 | 23/03/2018 | 0 | TK_Complete
GENSUB82 | TT_Task | Wall Cladding Shop Drawing &amp; Calculation - RO Comment and Approval (= ready for BD submission) | 23/04/2018 | 06/05/2018 | 14/04/2018 | 24/05/2018 | 0 | TK_Complete
GENSUB84 | TT_Task | Wall Cladding - BD Approval | 26/05/2018 | 24/07/2018 | 25/05/2018 | 23/07/2018 | 0 | TK_Complete
GENSUB86 | TT_Task | Wall Cladding - BD Consent | 26/08/2018 | 22/09/2018 | 24/08/2018 | 20/09/2018 | 0 | TK_Complete
GENSUB88 | TT_Task | Glazing - BD Approval | 26/06/2018 | 24/08/2018 | 20/06/2018 | 21/08/2018 | 0 | TK_Complete
GENSUB90 | TT_Task | Glazing - BD Consent | 26/11/2018 | 23/12/2018 | 18/10/2018 | 06/11/2018 | 0 | TK_Complete
GENSUB92 | TT_Task | Louvre - BD Approval | 26/11/2018 | 24/01/2019 | 19/11/2018 | 15/01/2019 | 0 | TK_Complete
GENSUB94 | TT_Task | Louvre - BD Consent | 26/01/2019 | 22/02/2019 | 06/12/2018 | 18/01/2019 | 0 | TK_Complete
GENSUB96 | TT_Task | Lift Shaft Glazing - BD Approval | 26/11/2018 | 24/01/2019 | 09/11/2018 | 07/01/2019 | 0 | TK_Complete
GENSUB98 | TT_Task | Lift Shaft Glazing - BD Consent | 26/01/2019 | 22/02/2019 | 06/12/2018 | 11/01/2019 | 0 | TK_Complete
GENSUB9A | TT_Task | Aluminum - BD Approval | 26/11/2018 | 24/01/2019 | 08/11/2018 | 07/01/2019 | 0 | TK_Complete
GENSUB9B | TT_Task | Aluminum - BD Consent | 26/01/2019 | 22/02/2019 | 06/12/2018 | 11/01/2019 | 0 | TK_Complete
SFAtSA10 | TT_Task | Submission and approval of temporary works for Shaft A, Pump Station, Diversion Culvert (Wall Only) {4b4-2} | 04/07/2017 | 17/07/2017 | 04/07/2017 | 20/12/2017 | 0 | TK_Complete
SFAtSA20 | TT_Task | Submission and approval of temporary works for Shaft A, Pump Station, Diversion Culvert (Excav. &amp; ELS) - for MS-03 {4b5} | 07/08/2017 | 15/08/2017 | 07/08/2017 | 05/12/2017 | 0 | TK_Complete
SFAtSA21 | TT_Task | Submission and approval of temporary works for Shaft A, Pump Station, Diversion Culvert (Excav. &amp; ELS) {4b5} | 05/09/2017 | 18/09/2017 | 05/09/2017 | 12/02/2018 | 0 | TK_Complete
SFDtSA10 | TT_Task | Submission and approval of temporary works for Shaft D (Wall, Excav. &amp; ELS) {4b3(r1)} | 02/06/2017 | 15/06/2017 | 08/06/2017 | 20/06/2017 | 0 | TK_Complete
SFEtSA09 | TT_Task | Submission and approval of temporary works for Shaft E and Discharge Culvert (Wall, Excav. &amp; ELS) - for MS-03 {4b2i-1} | 07/08/2017 | 15/08/2017 | 03/07/2017 | 20/07/2017 | 0 | TK_Complete
SFEtSA10 | TT_Task | Submission and approval of temporary works for Shaft E and Discharge Culvert (Wall, Excav. &amp; ELS) {4b2-1} | 05/10/2017 | 03/11/2017 | 03/07/2017 | 20/07/2017 | 0 | TK_Complete
SFFtSA10 | TT_Task | Submission and approval of temporary works for Shaft F (Skin Wall) &amp; Double Pipe (Southern Sheet Pile) {4b1i} | 10/06/2017 | 21/06/2017 | 09/06/2017 | 22/06/2017 | 0 | TK_Complete
SFFtSA10a | TT_Task | Resubmission and approval of temporary works for Shaft F (Skin Wall) only {4b1-1(r)} | 10/06/2017 | 21/06/2017 | 18/07/2017 | 23/07/2017 | 0 | TK_Complete
SFFtSA10b | TT_Task | Resubmission and approval of Zone A (Southern Sheet Pile) {4b1-alt A-1} | 10/06/2017 | 21/06/2017 | 19/07/2017 | 23/07/2017 | 0 | TK_Complete
SFFtSA20 | TT_Task | Submission and approval of temporary works for Shaft F and Double Pipe Trench (Open Cut) {4b1-alt B} | 10/06/2017 | 21/06/2017 | 09/06/2017 | 22/06/2017 | 0 | TK_Complete
SCWtSA09 | TT_Task | Submission and approval of temporary works for SCW and Intake Culvert Modification (Wall Only) - for MS-05 {5b1(r)} | 17/08/2017 | 30/08/2017 | 17/08/2017 | 19/09/2017 | 0 | TK_Complete
SCWtSA10 | TT_Task | Submission and approval of temporary works for SCW and Intake Culvert Modification (Wall Only) {5b1-alt} | 17/08/2017 | 30/08/2017 | 17/08/2017 | 19/12/2017 | 0 | TK_Complete
SCWtSA19 | TT_Task | Submission and approval of temporary works for SCW and Intake Culvert Modification (Excav &amp; ELS) - for MS-05 {5b1(r)} | 17/08/2017 | 30/08/2017 | 17/08/2017 | 19/09/2017 | 0 | TK_Complete
SCWtSA20 | TT_Task | Submission and approval of temporary works for SCW and Intake Culvert Modification (Excav &amp; ELS) {5b1-alt} | 17/08/2017 | 30/08/2017 | 17/08/2017 | 19/12/2017 | 0 | TK_Complete
OAMtSA10 | TT_Task | Submission and approval of temporary works for Outfall Apron Modification | 07/01/2018 | 03/02/2018 | 16/11/2017 | 10/01/2018 | 0 | TK_Complete
POWtSA10 | TT_Task | Submission and approval of temporary works for Power Island Area (Open Cut) {7c2i} | 10/06/2017 | 21/06/2017 | 10/06/2017 | 21/06/2017 | 0 | TK_Complete
TWORK010XX | TT_FinMile | Temporary Works designed by Contractor - Batch 1 ready for submission | 11/06/2017 | 11/06/2017 | 11/06/2017 | 11/06/2017 | 0 | TK_Complete
TWORK020XX | TT_FinMile | Temporary Works designed by Contractor - Batch 2 ready for submission | 27/06/2017 | 27/06/2017 | 27/06/2017 | 27/06/2017 | 0 | TK_Complete
SFAtDN10 | TT_Task | Review and design temporary works for Shaft A, Pump Station, Diversion Culvert (Wall Only) {4b4-2} | 04/06/2017 | 03/07/2017 | 04/06/2017 | 03/07/2017 | 0 | TK_Complete
SFAtDN19 | TT_Task | Review and design temporary works for Shaft A, Pump Station, Diversion Culvert (Excavation &amp; ELS) - for MS-03 {4b5} | 28/06/2017 | 11/07/2017 | 28/06/2017 | 25/07/2017 | 0 | TK_Complete
SFAtDN20 | TT_Task | Review and design temporary works for Shaft A, Pump Station, Diversion Culvert (Excavation &amp; ELS) {4b5} | 07/07/2017 | 04/09/2017 | 07/07/2017 | 04/09/2017 | 0 | TK_Complete
SFDtDN10 | TT_Task | Review and design temporary works for Shaft D (Wall, Excav. &amp; ELS) {4b3(r1)} | 23/05/2017 | 01/06/2017 | 23/05/2017 | 01/06/2017 | 0 | TK_Complete
SFEtDN09 | TT_Task | Review and design temporary works for Shaft E and Discharge Culvert (Wall, Excav. &amp; ELS) - for MS-03 {4b2-1} | 28/06/2017 | 11/07/2017 | 12/06/2017 | 02/07/2017 | 0 | TK_Complete
SFEtDN10 | TT_Task | Review and design temporary works for Shaft E and Discharge Culvert (Wall, Excav. &amp; ELS) {4b2-1} | 05/09/2017 | 04/10/2017 | 12/06/2017 | 02/07/2017 | 0 | TK_Complete
SFFtDN20 | TT_Task | Review and design temp works for Shaft F &amp; Double Pipe Trench - Shaft F (Skin Wall) &amp; Southern Section Sheet Pile {4b1i} | 27/05/2017 | 09/06/2017 | 27/05/2017 | 09/06/2017 | 0 | TK_Complete
SFFtDN30 | TT_Task | Review and design temp works for Shaft F &amp; Double Pipe Trench - Open Cut {4b1-alt B} | 27/05/2017 | 09/06/2017 | 27/05/2017 | 09/06/2017 | 0 | TK_Complete
ICMtDN09 | TT_Task | Review and design temporary works for SCW and Intake Culvert Modification (Wall Only) - for MS-05 {5b1(r)} | 07/08/2017 | 20/08/2017 | 28/07/2017 | 10/08/2017 | 0 | TK_Complete
ICMtDN10 | TT_Task | Review and design temporary works for SCW and Intake Culvert Modification (Wall Only) {5b1-alt} | 11/08/2017 | 09/09/2017 | 28/07/2017 | 16/08/2017 | 0 | TK_Complete
ICMtDN19 | TT_Task | Review and design temporary works for SCW and Intake Culvert Modification (Excavation &amp; ELS) - for MS-05 {5b1(r)} | 07/08/2017 | 20/08/2017 | 28/07/2017 | 10/08/2017 | 0 | TK_Complete
ICMtDN20 | TT_Task | Review and design temporary works for SCW and Intake Culvert Modification (Excavation &amp; ELS) {5b1-alt} | 10/09/2017 | 09/10/2017 | 28/07/2017 | 16/08/2017 | 0 | TK_Complete
OAMtDN10 | TT_Task | Review and design a temporary bulkhead for Outfall Apron Modification | 29/05/2017 | 27/06/2017 | 12/07/2017 | 06/01/2018 | 0 | TK_Complete
POWtDN10 | TT_Task | Review and design temporary works for Power Island Area (Open Cut) {7c2i} | 27/05/2017 | 09/06/2017 | 27/05/2017 | 09/06/2017 | 0 | TK_Complete
MCGZDN10 | TT_Task | Roof Cladding - Review engineer's drawings and prepare design | 16/10/2017 | 12/11/2017 | 16/10/2017 | 26/01/2018 | 0 | TK_Complete
MCGZDN20 | TT_Task | Roof Cladding - ICE Check and Issue Cert | 26/07/2018 | 08/08/2018 | 10/07/2018 | 23/07/2018 | 0 | TK_Complete
MCGZDN30 | TT_Task | Roof Cladding - Performance mock-up test (by approved laboratory) | 09/08/2018 | 05/09/2018 | 24/07/2018 | 20/08/2018 | 0 | TK_Complete
MCGZDN40 | TT_Task | Roof Cladding - Address engineer's comment and prepare resubmission | 12/03/2018 | 25/03/2018 | 06/02/2018 | 09/02/2018 | 0 | TK_Complete
MCGZDN50 | TT_Task | Roof Cladding - Review engineer's drawings and prepare design | 23/04/2018 | 20/05/2018 | 27/01/2018 | 23/02/2018 | 0 | TK_Complete
MCGZDN60 | TT_Task | Roof Cladding - Address engineer's comment and prepare resubmission | 23/04/2018 | 20/05/2018 | 24/03/2018 | 13/04/2018 | 0 | TK_Complete
IRRIDN10 | TT_Task | Irrigation System - Review engineer's drawings and prepare design | 08/02/2019 | 07/03/2019 | 21/02/2018 | 21/09/2018 | 0 | TK_Complete
IRRIDN20 | TT_Task | Irrigation System - Address engineer's comment and prepare resubmission | 05/04/2019 | 18/04/2019 | 14/06/2018 | 18/01/2019 | 0 | TK_Complete
LIFTDN10 | TT_Task | Lifts - Review engineer's drawings and prepare design (AD TBC) | 21/12/2017 | 17/01/2018 | 21/12/2017 | 13/06/2018 | 0 | TK_Complete
LIFTDN20 | TT_Task | Lifts - Address engineer's comment and prepare resubmission (AD TBC) | 28/07/2018 | 03/08/2018 | 28/06/2018 | 04/07/2018 | 0 | TK_Complete
EV005010 | TT_Task | Event 005 - New Requirements on Lift No.1 | 27/11/2017 | 26/12/2017 | 16/11/2017 | 20/12/2017 | 0 | TK_Complete
EV005020 | TT_FinMile | Event 005 - Award Lift Subcontract | 15/12/2017 | 15/12/2017 | 20/12/2017 | 20/12/2017 | 0 | TK_Complete
PROSC010 | TT_Task | Procurement of Subcontract - Excavation &amp; ELS (and other civil works) | 03/07/2017 | 31/08/2017 | 29/05/2017 | 22/12/2017 | 0 | TK_Complete
PROSC020 | TT_Task | Procurement of Subcontract - Grouting &amp; Sheet /Pipe Piling | 03/07/2017 | 31/08/2017 | 29/05/2017 | 26/08/2017 | 0 | TK_Complete
PROSC030 | TT_Task | Procurement of Subcontract - Steel Structure &amp; Heavy Lifting | 03/07/2017 | 15/09/2017 | 29/05/2017 | 24/10/2017 | 0 | TK_Complete
PROSC040 | TT_Task | Procurement of Subcontract - Standing Seam Roof, Aluminium Cladding &amp; Curtain Wall | 03/07/2017 | 15/09/2017 | 29/05/2017 | 20/12/2017 | 0 | TK_Complete
PROSC050 | TT_Task | Procurement of Subcontract - CWP Installation (Jacking / TBM) | 03/07/2017 | 15/09/2017 | 29/05/2017 | 19/04/2018 | 0 | TK_Complete
PROSC051 | TT_Task | Procurement of Subcontract - CWP Installation (Laying in trench) | 27/11/2017 | 09/02/2018 | 29/05/2017 | 04/04/2018 | 0 | TK_Complete
PROSC060 | TT_Task | Procurement of Subcontract - Building Service Installation (i.e., Elect, ACMV, FS, P&amp;D) | 04/09/2017 | 27/10/2017 | 04/09/2017 | 20/02/2018 | 0 | TK_Complete
PROSC070 | TT_Task | Procurement of Subcontract - Lift Installation (once awarded to Otis) | 07/08/2017 | 25/09/2017 | 07/08/2017 | 17/10/2017 | 0 | TK_Complete
PROSC080 | TT_Task | Procurement of Subcontract - Supply of Precast Concrete Structure (i.e. Diversion Culvert) | 26/02/2018 | 14/04/2018 | 05/02/2018 | 01/06/2018 | 0 | TK_Complete
PROPE010 | TT_Task | Sourcing, Reconditioning and Delivery of TBM (AD TBC) | 16/06/2018 | 05/10/2018 | 07/05/2018 | 26/08/2018 | 0 | TK_Complete
PROPE015 | TT_Mile | TBM On Site (early date) (AD TBC) | 26/11/2018 | 26/11/2018 | 26/08/2018 | 26/08/2018 | 0 | TK_Complete
PROPE020 | TT_Task | Fabrication and Delivery of Lifts (AS / EF TBC) | 11/08/2018 | 25/01/2019 | 12/07/2018 | 22/09/2019 | 0 | TK_Complete
PROMA009 | TT_Task | Manufacturing and Delivery of CWP materials (1st Batch) (Zone B prioritized) | 26/02/2018 | 20/05/2018 | 22/12/2017 | 27/04/2018 | 0 | TK_Complete
PROMA010 | TT_Mile | CWP Installation start on site (1st Batch) (Zone A) | 26/11/2018 | 26/11/2018 | 03/11/2018 | 03/11/2018 | 0 | TK_Complete
PROMA011 | TT_Task | Manufacturing and Delivery of CWP materials (2nd Batch) | 26/05/2018 | 09/07/2018 | 28/04/2018 | 27/05/2018 | 0 | TK_Complete
PROMA012 | TT_Task | Manufacturing and Delivery of CWP materials (3rd Batch) | 28/06/2018 | 25/09/2018 | 28/05/2018 | 16/12/2018 | 0 | TK_Complete
PROMA013 | TT_Task | Manufacturing and Delivery of CWP materials (4th Batch) | 26/01/2019 | 25/04/2019 | 17/12/2018 | 25/05/2019 | 0 | TK_Complete
PROMA014 | TT_Mile | CWP Pipe Jacking start on site (using 3rd Batch Pipe Mtl) | 01/09/2019 | 01/09/2019 | 09/07/2019 | 09/07/2019 | 0 | TK_Complete
PROMA020 | TT_Task | Manufacturing and Delivery of Structural Steels (Early Delivery) | 06/11/2017 | 10/12/2017 | 24/11/2017 | 08/12/2017 | 0 | TK_Complete
PROMA025 | TT_Task | Manufacturing and Delivery of Structural Steels (1st Batch) | 06/03/2018 | 06/03/2018 | 24/11/2017 | 27/03/2018 | 0 | TK_Complete
PROMA030 | TT_Task | Manufacturing and Delivery Roof /Wall Cladding (1st Batch) | 26/02/2018 | 15/04/2018 | 18/01/2018 | 21/03/2018 | 0 | TK_Complete
PROMA040 | TT_Task | Manufacturing and Delivery of Curtain Wall /Glazing (1st Batch) | 26/11/2018 | 23/02/2019 | 09/11/2018 | 10/01/2019 | 0 | TK_Complete
PROMA050 | TT_Task | Fabrication and Delivery of Precast Concrete Intake Chamber | 01/05/2019 | 23/07/2019 | 26/03/2019 | 01/10/2019 | 0 | TK_Complete
PROMA060 | TT_Task | Procurement and Delivery of Conductor Materials for Earth Mat | 03/07/2017 | 11/08/2017 | 03/07/2017 | 08/09/2017 | 0 | TK_Complete
PROMA080 | TT_Task | Fabrication and Delivery of Temporary Bulkhead | 14/03/2018 | 17/04/2018 | 19/01/2018 | 12/02/2018 | 0 | TK_Complete
CLPSUP05 | TT_FinMile | OFCI Item No.1 - Cast-in Embedded Items for Turbine Hall and Turbine Table (AD TBC) | 30/07/2017 | 30/07/2017 | 18/07/2017 | 18/07/2017 | 0 | TK_Complete
CLPSUP10 | TT_FinMile | OFCI Item No.2 - Cast-in Embedded Items for HRSG and Stack (AD TBC) | 25/09/2017 | 25/09/2017 | 29/08/2017 | 29/08/2017 | 0 | TK_Complete
CLPSUP15 | TT_FinMile | OFCI Item No.3 - Cast-in Embedded Items for Remaining Plant (AD TBC) | 26/02/2018 | 26/02/2018 | 01/02/2018 | 01/02/2018 | 0 | TK_Complete
CLPSUP20 | TT_FinMile | OFCI Item No.4 - Overhead Cranes (AD TBC) | 26/02/2018 | 26/02/2018 | 04/01/2018 | 04/01/2018 | 0 | TK_Complete
CLPSUP45 | TT_FinMile | OFCI Item No.9 - Crane Walkway (actual dates TBC) | 17/12/2017 | 17/12/2017 | 17/12/2017 | 17/12/2017 | 0 | TK_Complete
CLPSUP50 | TT_Task | OFCI Item No.,10 - Platforms (actual dates TBC) | 03/11/2017 | 06/04/2018 | 03/11/2017 | 30/04/2018 | 0 | TK_Complete
ESTAB010 | TT_Task | Site Establishment - Erect Hoarding | 25/09/2017 | 16/10/2017 | 25/09/2017 | 16/10/2017 | 0 | TK_Complete
ESTAB020 | TT_Task | Site Establishment - Site Clearance (incl. Fencing, Wheel Washing Facilities and Hard Standings for Area 2c, 4a, 4b &amp; 5) | 17/07/2017 | 18/08/2017 | 17/07/2017 | 08/09/2017 | 0 | TK_Complete
ESTAB030 | TT_Task | Site Establishment - Conduct Survey to Existing Structures and Structural Survey to Cooling Water Outfall Structure | 03/07/2017 | 04/08/2017 | 01/06/2017 | 23/10/2017 | 0 | TK_Complete
ESTAB040 | TT_Task | Site Establishment - Site Mobilisation Works | 04/07/2017 | 05/08/2017 | 19/06/2017 | 16/10/2017 | 0 | TK_Complete
GEOT0010 | TT_Task | Site Establishment - Install Instrumentation to Monitor Building Settlment, Ground/Utility Settlement and Vibrations | 28/06/2017 | 25/09/2017 | 26/06/2017 | 11/02/2018 | 0 | TK_Complete
EV001010 | TT_Task | Event 001 - SCW Penstock Repair 10~16 Sep 2017 | 10/09/2017 | 16/09/2017 | 10/09/2017 | 16/09/2017 | 0 | TK_Complete
EV007010 | TT_Task | Event 007 - Approval of Site Arrangement and TTA | 23/10/2017 | 23/10/2017 | 07/09/2017 | 29/11/2017 | 0 | TK_Complete
EV007010a | TT_Task | Event 007 - Issue of LWC for barricading the areas | 27/11/2017 | 27/11/2017 | 30/11/2017 | 05/12/2017 | 0 | TK_Complete
EV007010b | TT_Task | Event 007 - Barrication as per approved site layout and TTM | 27/11/2017 | 27/11/2017 | 05/12/2017 | 05/12/2017 | 0 | TK_Complete
EV008010 | TT_Task | Event 008 - Declaration of unplanted area / Isolation of SCWP(?) | 13/12/2017 | 05/01/2018 | 06/12/2017 | 16/12/2017 | 0 | TK_Complete
EV008010a | TT_Task | Event 008 - Excavation Permit | 27/11/2017 | 27/11/2017 | 15/12/2017 | 29/12/2017 | 0 | TK_Complete
EV009002 | TT_Task | Event 009 - 2 nos Pre-drill abortive | 03/03/2018 | 31/03/2018 | 30/12/2017 | 26/01/2018 | 0 | TK_Complete
EV009010 | TT_Task | Event 009 - Additional Pre-drill (2 out of 4 nos.) | 23/04/2018 | 28/05/2018 | 20/04/2018 | 04/05/2018 | 0 | TK_Complete
EV009015 | TT_Task | Event 009 - 3rd pre-drill encountered unchartered UU and rigs demob to help out inclinometer and SPT at Shaft F | 26/05/2018 | 11/06/2018 | 05/05/2018 | 28/05/2018 | 0 | TK_Complete
EV009020 | TT_Task | Event 009 - Additional Pre-drill (remaining 2 nos.) | 29/06/2018 | 16/07/2018 | 29/05/2018 | 23/06/2018 | 0 | TK_Complete
EV017510 | TT_Task | Event 017(I) - Advanced Precautionary Grouting | 26/01/2019 | 08/03/2019 | 27/12/2018 | 09/02/2019 | 0 | TK_Complete
EV026010 | TT_Task | Event 026 - Tie beam amendment (i.e. steel tie beam, phased consent for excav below +3.5, delete TAM &amp; CS4)[WITHDRAWN] | 26/08/2018 | 30/08/2018 | 24/08/2018 | 28/08/2018 | 0 | TK_Complete
EV026020 | TT_Task | Event 026 - Resubmission of tie beam amendment | 13/12/2018 | 11/01/2019 | 13/09/2018 | 14/11/2018 | 0 | TK_Complete
EV026030 | TT_Task | Event 026 - BA8 consent for APG | 26/12/2018 | 22/01/2019 | 14/11/2018 | 14/12/2018 | 0 | TK_Complete
EV043010 | TT_Task | Event 043 - RP11 encounter underground obstruction | 26/11/2018 | 09/12/2018 | 29/09/2018 | 12/10/2018 | 0 | TK_Complete
EV043020 | TT_Task | Event 043 - RP14, 15, 16 encounter underground obstruction | 26/11/2018 | 23/12/2018 | 01/11/2018 | 29/11/2018 | 0 | TK_Complete
EV043030 | TT_Task | Event 043 - Socketed H-pile amendment (Type II) [APPROVAL DEEMED] | 26/01/2019 | 24/02/2019 | 27/12/2018 | 25/01/2019 | 0 | TK_Complete
ICM00010 | TT_Task | Intake Culvert Modif - Utilities Diversion | 26/05/2018 | 29/06/2018 | 25/04/2018 | 21/06/2018 | 0 | TK_Complete
ICM00020 | TT_Task | Intake Culvert Modif - Remove parts of existing gantry crane | 01/06/2018 | 16/06/2018 | 06/04/2018 | 21/04/2018 | 0 | TK_Complete
ICM00022 | TT_Task | Intake Culvert Modif - Remove tie beams of existing gantry foundations | 01/04/2019 | 09/04/2019 | 18/03/2019 | 23/03/2019 | 0 | TK_Complete
ICM00025 | TT_Task | Intake Culvert Modif - Install socket H-pile (All except RP14-16) | 27/08/2018 | 13/10/2018 | 09/08/2018 | 10/11/2018 | 0 | TK_Complete
ICM00030 | TT_Task | Intake Culvert Modif - Install socket H-pile (RP14, RP15, RP16) | 08/02/2019 | 22/02/2019 | 12/01/2019 | 31/01/2019 | 0 | TK_Complete
ICM00032 | TT_Task | Intake Culvert Modif - CS3 Pipe Pile Wall | 26/01/2019 | 31/01/2019 | 08/01/2019 | 12/01/2019 | 0 | TK_Complete
ICM00033 | TT_Task | Intake Culvert Modif - Grout Curtain (behind CS3) | 01/04/2019 | 12/04/2019 | 09/02/2019 | 18/02/2019 | 0 | TK_Complete
ICM00035 | TT_Task | Intake Culvert Modif - BA8 consent for excavation below +3.5 and above +2.425 mPD (Zone 1 for Tie Back )(AD TBC) | 03/04/2019 | 30/04/2019 | 31/01/2019 | 29/03/2019 | 0 | TK_Complete
ICM00036 | TT_Task | Intake Culvert Modif - Zone 1 excavation to +2.425 mPD | 03/04/2019 | 09/04/2019 | 28/02/2019 | 29/03/2019 | 0 | TK_Complete
ICM00040 | TT_Task | Intake Culvert Modif - Construct Tie-back system | 10/04/2019 | 21/05/2019 | 25/03/2019 | 15/04/2019 | 0 | TK_Complete
ICM00050 | TT_Task | Intake Culvert Modif - Remove parts of existing crest wall and fence | 10/09/2018 | 29/09/2018 | 10/09/2018 | 09/10/2018 | 0 | TK_Complete
ICM00060 | TT_Task | Intake Culvert Modif - Install silt curtain | 27/08/2018 | 28/08/2018 | 21/08/2018 | 23/08/2018 | 0 | TK_Complete
ICM00070 | TT_Task | Intake Culvert Modif - Remove rock armour | 26/11/2018 | 01/12/2018 | 10/10/2018 | 14/10/2018 | 0 | TK_Complete
ICM00080 | TT_Task | Intake Culvert Modif - Rock fill to form a working platform at +3.5mPD | 03/12/2018 | 05/12/2018 | 15/10/2018 | 14/11/2018 | 0 | TK_Complete
ICM10010 | TT_Task | Intake Culvert Modif - 406 Dia. Pipe Pile Walls (CS2) | 26/11/2018 | 21/01/2019 | 24/11/2018 | 14/01/2019 | 0 | TK_Complete
ICM10020 | TT_Task | Intake Culvert Modif - Grout Curtain (behind CS2) | 26/01/2019 | 08/03/2019 | 16/01/2019 | 23/02/2019 | 0 | TK_Complete
ICM10029 | TT_Task | Intake Culvert Modif - BA8 consent for excavation below +3.5 and above +2.425 mPD (Zone 2 for Intake Chamber)(AD TBC) | 31/03/2019 | 27/04/2019 | 28/02/2019 | 29/03/2019 | 0 | TK_Complete
ICM10030 | TT_Task | Intake Culvert Modif - Zone 2 Excavate to +2.425mPD | 01/05/2019 | 07/05/2019 | 10/04/2019 | 18/04/2019 | 0 | TK_Complete
ICM10040 | TT_Task | Intake Culvert Modif - Install twin batten waling frame | 01/05/2019 | 07/05/2019 | 22/04/2019 | 26/04/2019 | 0 | TK_Complete
ICM10045 | TT_Task | Intake Culvert Modif - BA8 consent for excavation below +2.425 mPD (AD TBC) | 31/03/2019 | 27/04/2019 | 28/02/2019 | 29/03/2019 | 0 | TK_Complete
ICM10050 | TT_Task | Intake Culvert Modif - Excavate to top of existing intake culvert | 01/05/2019 | 07/05/2019 | 27/04/2019 | 29/05/2019 | 0 | TK_Complete
ICM10060 | TT_Task | Intake Culvert Modif - Install staging platform | 06/06/2019 | 11/07/2019 | 29/05/2019 | 21/06/2019 | 0 | TK_Complete
ICM10070 | TT_Task | Intake Culvert Modif - Saw cut and remove the existing box culvert at the location of proposed diversion chamber | 01/08/2019 | 24/08/2019 | 18/07/2019 | 24/09/2019 | 0 | TK_Complete
ICM10080 | TT_Task | Intake Culvert Modif - Excavate either side of culvert to -5.4mPD | 10/08/2019 | 11/08/2019 | 22/06/2019 | 17/07/2019 | 0 | TK_Complete
ICM10090 | TT_Task | Intake Culvert Modif - Prepare bedding and leveling | 01/11/2019 | 06/11/2019 | 25/09/2019 | 15/10/2019 | 0 | TK_Complete
ICM10100 | TT_Task | Intake Culvert Modif - Install precast segments for the base slab | 01/11/2019 | 01/11/2019 | 16/10/2019 | 17/10/2019 | 0 | TK_Complete
ICM10110 | TT_Task | Intake Culvert Modif - Tremie concrete to segment joints of base slab | 01/11/2019 | 01/11/2019 | 21/10/2019 | 25/10/2019 | 0 | TK_Complete
ICM10120 | TT_Task | Intake Culvert Modif - Install precast segments for the columns and side walls | 03/11/2019 | 04/11/2019 | 18/10/2019 | 19/10/2019 | 0 | TK_Complete
ICM10130 | TT_Task | Intake Culvert Modif - Tremie concrete to segment joints of columns and side walls | 02/11/2019 | 03/11/2019 | 21/10/2019 | 15/11/2019 | 0 | TK_Complete
ICM10140 | TT_Task | Intake Culvert Modif - Install precast segments for top slab and beams | 07/11/2019 | 07/11/2019 | 20/10/2019 | 20/10/2019 | 0 | TK_Complete
ICM10150 | TT_Task | Intake Culvert Modif - Tremie concrete to segment joints of top slab | 04/11/2019 | 04/11/2019 | 22/10/2019 | 28/10/2019 | 0 | TK_Complete
ICM10170 | TT_Task | Intake Culvert Modif - Backfill between the proposed chamber and pipe pile walls | 23/11/2019 | 04/12/2019 | 21/10/2019 | 15/11/2019 | 0 | TK_Complete
ICM10180 | TT_Task | Intake Culvert Modif - Reinstate the seawall and rock armour to 0.5m below the shoring | 09/01/2020 | 11/01/2020 | 11/12/2019 | 13/12/2019 | 0 | TK_Complete
ICM10190 | TT_Task | Intake Culvert Modif - Remove twin batten waling frame | 09/01/2020 | 13/01/2020 | 16/11/2019 | 20/11/2019 | 0 | TK_Complete
ICM10200 | TT_Task | Intake Culvert Modif - Backfill and reinstate the crest wall and fence | 16/01/2020 | 22/01/2020 | 16/01/2020 | 22/01/2020 | 0 | TK_Complete
ICM10210 | TT_Task | Intake Culvert Modif - Install temporary penstock at the connection with Diversion Culvert | 24/11/2019 | 26/11/2019 | 16/10/2019 | 20/10/2019 | 0 | TK_Complete
ICM10220 | TT_Task | Intake Culvert Modif - Observe and repair leaks | 06/01/2020 | 09/01/2020 | 06/11/2019 | 09/11/2019 | 0 | TK_Complete
ICM10230 | TT_Task | Intake Culvert Modif - Make good interior surface | 24/01/2020 | 30/01/2020 | 21/10/2019 | 15/11/2019 | 0 | TK_Complete
ICM10240 | TT_Task | Intake Culvert Modif - Remove temporary penstock | 15/02/2020 | 16/02/2020 | 19/12/2019 | 20/12/2019 | 0 | TK_Complete
ICM10250 | TT_Task | Intake Culvert Modif - Reinstate existing utilities and gantry crane | 09/01/2020 | 22/01/2020 | 16/12/2019 | 28/02/2020 | 0 | TK_Complete
EV007011 | TT_Task | Event 007 - Approval of Site Arrangement and TTA | 23/10/2017 | 23/10/2017 | 07/09/2017 | 29/11/2017 | 0 | TK_Complete
EV007011a | TT_Task | Event 007 - Issue of LWC for barricading the areas | 27/11/2017 | 27/11/2017 | 30/11/2017 | 05/12/2017 | 0 | TK_Complete
EV007011b | TT_Task | Event 007 - Barrication as per approved site layout and TTM | 27/11/2017 | 27/11/2017 | 05/12/2017 | 05/12/2017 | 0 | TK_Complete
EV008011 | TT_Task | Event 008 - Declaration of unplanted area | 13/12/2017 | 30/12/2017 | 06/12/2017 | 16/12/2017 | 0 | TK_Complete
EV008011a | TT_Task | Event 008 - Excavation Permit | 27/11/2017 | 27/11/2017 | 15/12/2017 | 29/12/2017 | 0 | TK_Complete
EV017110 | TT_Task | Event 017 - Diversion Culvert APG | 06/12/2018 | 03/01/2019 | 11/10/2018 | 27/11/2018 | 0 | TK_Complete
EV019120 | TT_Task | Event 019 - Diversion Culvert C1 plate load test | 01/11/2019 | 05/11/2019 | 04/10/2019 | 08/10/2019 | 0 | TK_Complete
IBC00010 | TT_Task | Diversion Culvert - Utilities Diversion Stage 1 | 27/08/2018 | 31/08/2018 | 14/08/2018 | 18/08/2018 | 0 | TK_Complete
IBC00020 | TT_Task | Diversion Culvert - Utilities Diversion Stage 2 | 26/01/2019 | 18/02/2019 | 30/12/2018 | 21/01/2019 | 0 | TK_Complete
IBC00030 | TT_Task | Diversion Culvert - Utilities Diversion Stage 3 | 26/01/2019 | 18/02/2019 | 22/01/2019 | 12/02/2019 | 0 | TK_Complete
IBC10010 | TT_Task | Diversion Culvert - Pipe pile along the inner cofferdam wall alignment | 26/12/2018 | 06/02/2019 | 12/12/2018 | 30/04/2019 | 0 | TK_Complete
IBC10030 | TT_Task | Diversion Culvert - Grout curtain along the inner cofferdam wall alignment | 08/04/2019 | 11/05/2019 | 28/03/2019 | 24/05/2019 | 0 | TK_Complete
IBC10050 | TT_Task | Diversion Culvert - Install silt curtain | 27/08/2018 | 28/08/2018 | 21/08/2018 | 23/08/2018 | 0 | TK_Complete
IBC10060 | TT_Task | Diversion Culvert - Remove parts of crest wall and fence | 26/11/2018 | 08/12/2018 | 03/09/2018 | 08/09/2018 | 0 | TK_Complete
IBC10070 | TT_Task | Diversion Culvert - Remove rock armour from the existing seawall | 03/12/2018 | 08/12/2018 | 10/09/2018 | 22/09/2018 | 0 | TK_Complete
IBC10080 | TT_Task | Diversion Culvert - Rock fill to +4mPD to form temporary piling platform | 10/12/2018 | 12/12/2018 | 24/09/2018 | 06/10/2018 | 0 | TK_Complete
IBC10090 | TT_Task | Diversion Culvert - Pipe pile along the outer cofferdam wall alignment | 26/12/2018 | 01/02/2019 | 01/12/2018 | 11/04/2019 | 0 | TK_Complete
IBC10100 | TT_Task | Diversion Culvert - Grout curtain along the outer cofferdam wall alignment | 01/04/2019 | 04/05/2019 | 04/03/2019 | 24/05/2019 | 0 | TK_Complete
IBC10110 | TT_Task | Diversion Culvert - Pumping Test and Report Submission (C1) | 01/08/2019 | 21/08/2019 | 01/06/2019 | 13/06/2019 | 0 | TK_Complete
IBC10115 | TT_Task | Diversion Culvert - Pumping Test and Report Submission (C2) | 01/08/2019 | 21/08/2019 | 08/06/2019 | 11/07/2019 | 0 | TK_Complete
IBC10120 | TT_Task | Diversion Culvert - BD Consent for Commencement of Excavation &amp; ELS (C1) | 15/08/2019 | 11/09/2019 | 06/06/2019 | 16/07/2019 | 0 | TK_Complete
IBC10125 | TT_Task | Diversion Culvert - BD Consent for Commencement of Excavation &amp; ELS (C2) [APPROVAL DEEMED] | 01/08/2019 | 28/08/2019 | 12/07/2019 | 04/09/2019 | 0 | TK_Complete
IBC10140 | TT_Task | Diversion Culvert - Excavate to 0.5m below 1st layer of struts | 01/08/2019 | 05/08/2019 | 17/06/2019 | 24/06/2019 | 0 | TK_Complete
IBC10150 | TT_Task | Diversion Culvert - Install 1st layer of struts and temporary support to existing utilities | 01/08/2019 | 05/08/2019 | 25/06/2019 | 26/07/2019 | 0 | TK_Complete
IBC10160 | TT_Task | Diversion Culvert - Excavate to 0.5m below 2nd layer of struts | 01/08/2019 | 04/08/2019 | 27/07/2019 | 25/08/2019 | 0 | TK_Complete
IBC10170 | TT_Task | Diversion Culvert - Install 2nd layer of struts | 09/09/2019 | 20/09/2019 | 15/08/2019 | 29/08/2019 | 0 | TK_Complete
IBC10180 | TT_Task | Diversion Culvert - Excavate to 0.5m below 3rd layer of struts | 01/09/2019 | 08/09/2019 | 27/08/2019 | 04/09/2019 | 0 | TK_Complete
IBC10190 | TT_Task | Diversion Culvert - Install 3rd layer of struts | 02/11/2019 | 09/11/2019 | 02/09/2019 | 13/09/2019 | 0 | TK_Complete
IBC10200 | TT_Task | Diversion Culvert - Excavate to 0.5m below 4th layer struts | 01/11/2019 | 09/11/2019 | 14/09/2019 | 28/09/2019 | 0 | TK_Complete
IBC10210 | TT_Task | Diversion Culvert - Install 4th layer of struts | 01/11/2019 | 08/11/2019 | 26/09/2019 | 10/10/2019 | 0 | TK_Complete
IBC10220 | TT_Task | Diversion Culvert - Excavate to final excavation level -5.5 mPD | 01/11/2019 | 08/11/2019 | 01/10/2019 | 22/10/2019 | 0 | TK_Complete
IBC10230 | TT_Task | Diversion Culvert (C1) - Cast base slab and walls to 0.5m below 4th layer of struts | 01/11/2019 | 06/11/2019 | 23/10/2019 | 04/11/2019 | 0 | TK_Complete
IBC10240 | TT_Task | Diversion Culvert - Backfill void between culvert and pipe pile wall to 0.5m below 4th layer of struts | 04/01/2020 | 04/01/2020 | 04/11/2019 | 04/11/2019 | 0 | TK_Complete
IBC10250 | TT_Task | Diversion Culvert - Remove 4th layer of struts | 05/01/2020 | 07/01/2020 | 05/11/2019 | 06/11/2019 | 0 | TK_Complete
IBC10270 | TT_Task | Diversion Culvert (C1) - Cast remaining walls and top slab | 08/01/2020 | 18/01/2020 | 07/11/2019 | 28/11/2019 | 0 | TK_Complete
IBC10280 | TT_Task | Diversion Culvert - Trim the interfacing sheet pile wall adjoining Pumping Station to -5.5 mPD | 17/01/2020 | 18/01/2020 | 07/11/2019 | 21/11/2019 | 0 | TK_Complete
IBC10290 | TT_Task | Diversion Culvert (C1) - Connect Diversion Culvert to Pumping Station | 18/01/2020 | 18/01/2020 | 28/11/2019 | 28/11/2019 | 0 | TK_Complete
IBC10300 | TT_Task | Diversion Culvert - Backfill and reinstate quay wall concrete block to 0.5m below 3rd layer of struts | 02/01/2020 | 06/01/2020 | 03/12/2019 | 24/12/2019 | 0 | TK_Complete
IBC10310 | TT_Task | Diversion Culvert - Remove 3rd layer of struts | 07/01/2020 | 08/01/2020 | 07/12/2019 | 24/12/2019 | 0 | TK_Complete
IBC10320 | TT_Task | Diversion Culvert - Backfill and reinstate quay wall concrete block to 0.5m below 2nd layer of struts | 09/01/2020 | 13/01/2020 | 08/12/2019 | 28/12/2019 | 0 | TK_Complete
IBC10330 | TT_Task | Diversion Culvert - Remove 2nd layer of struts | 14/01/2020 | 15/01/2020 | 11/12/2019 | 28/12/2019 | 0 | TK_Complete
IBC10340 | TT_Task | Diversion Culvert - Backfill and reinstate quay wall concrete block to 0.5m below 1st layer of struts (incl' utilities) | 02/01/2020 | 06/01/2020 | 30/12/2019 | 15/02/2020 | 0 | TK_Complete
IBC10350 | TT_Task | Diversion Culvert - Remove 1st layer of struts | 17/02/2020 | 18/02/2020 | 17/02/2020 | 18/02/2020 | 0 | TK_Complete
IBC10355 | TT_Task | Diversion Culvert (C2) - Construction of Diversion Culvert including excavation &amp; ELS | 10/01/2020 | 15/02/2020 | 02/11/2019 | 15/12/2019 | 0 | TK_Complete
IBC10360 | TT_Task | Diversion Culvert - Backfill and reinstate to ground level including crest wall and fence | 19/02/2020 | 25/02/2020 | 19/02/2020 | 25/02/2020 | 0 | TK_Complete
EV016035 | TT_Task | Event 016 - Bund Wall Settlement / Preventive grouting (50 nos.) | 26/02/2018 | 22/03/2018 | 02/04/2018 | 03/05/2018 | 0 | TK_Complete
EV017035 | TT_Task | Event 017P - Advanced Preventive Grouting as per AAA amendment (Part 1 - 66 out of 86) | 26/06/2018 | 24/08/2018 | 02/06/2018 | 25/07/2018 | 0 | TK_Complete
EV017045 | TT_Task | Event 017P - Advanced Preventive Grouting as per AAA amendment (Part 2 - 20 out of 86) | 26/11/2018 | 05/12/2018 | 30/08/2018 | 07/09/2018 | 0 | TK_Complete
EV025100 | TT_Task | Event 025P - Preventive grouting stopped as it's being legalized via AAA amendment | 26/06/2018 | 29/06/2018 | 23/06/2018 | 26/06/2018 | 0 | TK_Complete
EV027010 | TT_Task | Event 027 - Finalizing strategy and preparing for resubmission of re-sequencing amendment | 26/08/2018 | 15/09/2018 | 24/08/2018 | 27/09/2018 | 0 | TK_Complete
EV027020 | TT_Task | Event 027 - BA5 Re-sequencing alternative(by ARUP) prioritizing Pump Station | 15/12/2018 | 12/02/2019 | 28/09/2018 | 13/12/2018 | 0 | TK_Complete
EV044010 | TT_Task | Event 044 - Plate Load Test PL2 at stratum of Pump Station | 31/03/2019 | 06/04/2019 | 13/03/2019 | 18/03/2019 | 0 | TK_Complete
PPS10015 | TT_Task | CWPS - Pipe Piles | 26/07/2018 | 04/10/2018 | 19/07/2018 | 12/10/2018 | 0 | TK_Complete
PPS10020 | TT_Task | CWPS - Grout Curtain | 09/01/2019 | 19/02/2019 | 18/10/2018 | 28/11/2018 | 0 | TK_Complete
PPS10040 | TT_Task | CWPS - Pumping Test and Report Submission | 26/12/2018 | 15/01/2019 | 06/12/2018 | 31/12/2018 | 0 | TK_Complete
PPS10045 | TT_Task | CWPS - BD Consent for Commencement of Excavation &amp; ELS | 26/01/2019 | 22/02/2019 | 31/12/2018 | 01/02/2019 | 0 | TK_Complete
PPS10050 | TT_Task | CWPS - Excavate to 0.5m below 1st layer of struts | 28/01/2019 | 16/02/2019 | 28/12/2018 | 17/01/2019 | 0 | TK_Complete
PPS10060 | TT_Task | CWPS - Install 1st layer of struts | 26/01/2019 | 02/02/2019 | 17/01/2019 | 31/01/2019 | 0 | TK_Complete
PPS10070 | TT_Task | CWPS - Excavate to 0.5m below 2nd layer of struts | 01/04/2019 | 05/04/2019 | 31/01/2019 | 14/02/2019 | 0 | TK_Complete
PPS10080 | TT_Task | CWPS - Install 2nd layer of struts | 01/04/2019 | 08/04/2019 | 15/02/2019 | 21/02/2019 | 0 | TK_Complete
PPS10090 | TT_Task | CWPS - Excavate to 0.5m below 3rd layer of struts | 01/04/2019 | 04/04/2019 | 22/02/2019 | 25/02/2019 | 0 | TK_Complete
PPS10100 | TT_Task | CWPS - Install 3rd layer of struts | 01/04/2019 | 06/04/2019 | 26/02/2019 | 02/03/2019 | 0 | TK_Complete
PPS10110 | TT_Task | CWPS - Excavate to 0.5m below 4th layer struts | 08/04/2019 | 11/04/2019 | 03/03/2019 | 12/03/2019 | 0 | TK_Complete
PPS10120 | TT_Task | CWPS - Install 4th layer of struts | 01/04/2019 | 06/04/2019 | 11/03/2019 | 18/03/2019 | 0 | TK_Complete
PPS10250 | TT_Task | CWPS - Excavate to final excavation level -6.5 mPD | 01/04/2019 | 02/04/2019 | 11/03/2019 | 23/03/2019 | 0 | TK_Complete
PPS10260 | TT_Task | CWPS - Cast base slab | 01/04/2019 | 06/04/2019 | 24/03/2019 | 27/03/2019 | 0 | TK_Complete
PPS10270 | TT_Task | CWPS - Remove 4th layer of struts | 01/04/2019 | 06/04/2019 | 28/03/2019 | 30/03/2019 | 0 | TK_Complete
PPS10280 | TT_Task | CWPS - Construct pumping station RC structures to 0.5m below 3rd layer of strut | 01/05/2019 | 05/05/2019 | 30/03/2019 | 05/04/2019 | 0 | TK_Complete
PPS10290 | TT_Task | CWPS - Backfill the void between RC wall and pipe pile wall to 0.5m below 3rd layer of strut | 01/05/2019 | 02/05/2019 | 05/04/2019 | 06/04/2019 | 0 | TK_Complete
PPS10300 | TT_Task | CWPS - Remove 3rd layer of struts | 03/05/2019 | 04/05/2019 | 06/04/2019 | 10/04/2019 | 0 | TK_Complete
PPS10310 | TT_Task | CWPS - Construct pumping station RC structures to 0.5m below 2nd layer of strut | 05/05/2019 | 10/05/2019 | 09/04/2019 | 18/04/2019 | 0 | TK_Complete
PPS10320 | TT_Task | CWPS - Backfill the void between RC wall and pipe pile wall to 0.5m below 2nd layer of strut | 01/05/2019 | 02/05/2019 | 19/04/2019 | 19/04/2019 | 0 | TK_Complete
PPS10330 | TT_Task | CWPS - Remove 2nd layer of struts | 02/05/2019 | 03/05/2019 | 13/04/2019 | 23/04/2019 | 0 | TK_Complete
PPS10340 | TT_Task | CWPS - Construct pumping station RC structures to 0.5m below 1st layer of strut | 01/05/2019 | 03/05/2019 | 14/04/2019 | 30/04/2019 | 0 | TK_Complete
PPS10350 | TT_Task | CWPS - Install CW pipes between Valve Chamber and Shaft A | 01/01/2020 | 04/01/2020 | 10/12/2019 | 17/12/2019 | 0 | TK_Complete
PPS10360 | TT_Task | CWPS - Backfill the void between RC wall and pipe pile wall to 0.5m below 1st layer of strut | 01/08/2019 | 02/08/2019 | 01/05/2019 | 01/05/2019 | 0 | TK_Complete
PPS10370 | TT_Task | CWPS - Remove 1st layer of struts | 03/05/2019 | 04/05/2019 | 25/04/2019 | 06/05/2019 | 0 | TK_Complete
PPS10380 | TT_Task | CWPS - Cast top slab of Pumping Station | 03/05/2019 | 11/05/2019 | 25/04/2019 | 18/05/2019 | 0 | TK_Complete
PPS10390 | TT_Task | CWPS - Trim pipe piles | 03/06/2019 | 04/06/2019 | 07/05/2019 | 20/05/2019 | 0 | TK_Complete
PPS10400 | TT_Task | CWPS - Backfill to ground level | 08/06/2019 | 08/06/2019 | 21/05/2019 | 21/05/2019 | 0 | TK_Complete
PPS10410 | TT_Task | CWPS - Construct misc RC structures (i.e. footings, trenches, staircase and switchroom) | 10/06/2019 | 29/06/2019 | 14/05/2019 | 10/08/2019 | 0 | TK_Complete
PPS10420 | TT_Task | CWPS - ABWF works | 01/08/2019 | 13/09/2019 | 21/06/2019 | 21/12/2019 | 0 | TK_Complete
PPS10430 | TT_Task | CWPS - Building Service installation | 10/08/2019 | 23/09/2019 | 13/06/2019 | 19/12/2019 | 0 | TK_Complete
EV003010 | TT_Task | Event 003 - 6.6kVA Cable Strike at Shaft A | 24/10/2017 | 06/11/2017 | 24/10/2017 | 24/11/2017 | 0 | TK_Complete
EV004010 | TT_Task | Event 004 - Trial trench prior to pre-drill | 07/11/2017 | 09/11/2017 | 25/11/2017 | 30/11/2017 | 0 | TK_Complete
EV004020 | TT_Task | Event 004 - Pre-drill to verifiy rock head level of Shaft A | 02/12/2017 | 21/12/2017 | 01/12/2017 | 20/12/2017 | 0 | TK_Complete
EV004030 | TT_Task | Event 004 - Trial trench prior to piling | 27/11/2017 | 17/12/2017 | 21/12/2017 | 10/01/2018 | 0 | TK_Complete
EV004040 | TT_Task | Event 004a - Protection to existing cables and removal of existing light post | 26/02/2018 | 10/03/2018 | 08/01/2018 | 20/01/2018 | 0 | TK_Complete
EV011070 | TT_FinMile | Event 011A - Trial jet grout consent condition imposed on shaft excavation | 23/04/2018 | 23/04/2018 | 26/02/2018 | 26/02/2018 | 0 | TK_Complete
EV011080 | TT_Task | Event 011A - Install trial jet grout ( x3 nos.) | 27/08/2018 | 30/08/2018 | 27/07/2018 | 31/07/2018 | 0 | TK_Complete
EV011090 | TT_Task | Event 011A - Core sample after 21 days from grout installed | 26/11/2018 | 03/12/2018 | 03/09/2018 | 12/10/2018 | 0 | TK_Complete
EV011100 | TT_Task | Event 011A - Test to early achievement of 28 day strength | 04/12/2018 | 06/12/2018 | 02/10/2018 | 11/10/2018 | 0 | TK_Complete
EV011110 | TT_Task | Event 011A - Formal test report issued for submission in 7 calendar days | 26/11/2018 | 02/12/2018 | 13/11/2018 | 30/11/2018 | 0 | TK_Complete
EV011120 | TT_Task | Event 011A - Shaft A - BA8 for full scale grout block and excav below -4.6 mPD | 21/02/2019 | 20/03/2019 | 30/11/2018 | 24/12/2018 | 0 | TK_Complete
EV013010 | TT_Mile | Event 013 - Moblization for piling works start | 26/02/2018 | 26/02/2018 | 16/01/2018 | 16/01/2018 | 0 | TK_Complete
EV013020 | TT_Task | Event 013 - Crane damaged and repaired | 27/02/2018 | 07/03/2018 | 19/01/2018 | 27/01/2018 | 0 | TK_Complete
EV013030 | TT_FinMile | Event 013 - Mobilization for piling works complete | 26/02/2018 | 26/02/2018 | 03/02/2018 | 03/02/2018 | 0 | TK_Complete
EV013040 | TT_Task | Event 014 - Clarifying extent of monitoring and instrumentation prerequisite to start of Shaft A piling works | 26/02/2018 | 05/03/2018 | 04/02/2018 | 11/02/2018 | 0 | TK_Complete
EV016010 | TT_Mile | Event 016 - Settlement oberved at adjacent bund wall and piling suspended | 26/02/2018 | 26/02/2018 | 19/03/2018 | 19/03/2018 | 0 | TK_Complete
EV016020 | TT_Task | Event 016 - Piling rigs demobilized and site clear for preventive grouting | 26/02/2018 | 04/03/2018 | 19/03/2018 | 25/03/2018 | 0 | TK_Complete
EV016030 | TT_Task | Event 016 - Preventive grouting (18 nos. out of 20 critical completed) | 26/02/2018 | 06/03/2018 | 26/03/2018 | 03/04/2018 | 0 | TK_Complete
EV016040 | TT_Mile | Event 016 - Further settlement oberved and grouting suspended | 26/02/2018 | 26/02/2018 | 04/04/2018 | 04/04/2018 | 0 | TK_Complete
EV016045 | TT_Task | Event 016 - Awaiting engineering solution and management direction | 17/04/2018 | 25/04/2018 | 04/04/2018 | 16/04/2018 | 0 | TK_Complete
EV016050 | TT_Task | Event 016 - Remedial grouting to bund wall (5 nos.) | 17/04/2018 | 25/04/2018 | 17/04/2018 | 19/04/2018 | 0 | TK_Complete
EV016060 | TT_Task | Event 016 - Preventive grouting (the last remaining 2 nos.) | 30/05/2018 | 31/05/2018 | 21/04/2018 | 23/04/2018 | 0 | TK_Complete
EV016070 | TT_Task | Event 016 - Remobilize piling rig | 31/03/2019 | 02/04/2019 | 26/01/2019 | 28/01/2019 | 0 | TK_Complete
EV016080 | TT_Mile | Event 016 - Resume Shaft A piling works | 29/08/2018 | 29/08/2018 | 30/07/2018 | 30/07/2018 | 0 | TK_Complete
EV017080 | TT_Task | Event 017A - Advanced Preventive Grouting (42 nos.) | 26/06/2018 | 27/07/2018 | 29/05/2018 | 29/06/2018 | 0 | TK_Complete
EV021010 | TT_Task | Event 021A - AAA amendment for Shaft A /Pump Station/ Diversion Culvert | 01/06/2018 | 30/06/2018 | 23/05/2018 | 03/07/2018 | 0 | TK_Complete
EV021015 | TT_Task | Event 021A - Additional monitoring points hand-marked on approval drawings by BD | 26/06/2018 | 08/07/2018 | 23/06/2018 | 03/07/2018 | 0 | TK_Complete
EV023010 | TT_Task | Event 023 - Re-seqeuncing Submission (Alternative) for Shaft A /Pump Station/ Diversion Culvert (BA5)[WITHDRAWN] | 26/07/2018 | 23/09/2018 | 29/06/2018 | 23/08/2018 | 0 | TK_Complete
EV025000 | TT_Task | Event 025A - Preventive grouting stopped as it's being legalized via AAA amendment | 26/06/2018 | 29/06/2018 | 23/06/2018 | 26/06/2018 | 0 | TK_Complete
EV028002 | TT_Task | Event 028 - Redo PPA#39 - 5th amendment (Type II) | 26/11/2018 | 25/12/2018 | 13/07/2018 | 13/08/2018 | 0 | TK_Complete
EV028004 | TT_Task | Event 028 - Redo PPA #39 - install 508 dia. pile [FAILED] | 26/11/2018 | 26/11/2018 | 13/10/2018 | 13/10/2018 | 0 | TK_Complete
EV028006 | TT_Task | Event 028 - Redo PPA#39 - remedial proposal added to 6th amendment | 27/11/2018 | 08/12/2018 | 15/10/2018 | 26/10/2018 | 0 | TK_Complete
EV028008 | TT_FinMile | Event 028 - Redo PPA#39 - 6th amendment due by 03Nov18; approval deemed | 26/11/2018 | 26/11/2018 | 03/11/2018 | 03/11/2018 | 0 | TK_Complete
EV028010 | TT_Task | Event 028 - Redo PPA#39 - install replacement pile #42, 43 | 29/11/2018 | 05/12/2018 | 14/11/2018 | 17/11/2018 | 0 | TK_Complete
SFA10010 | TT_Task | Shaft A - Grout Blocks (at receiving area) (total drilling 830m) | 26/01/2019 | 27/03/2019 | 11/01/2019 | 02/02/2019 | 0 | TK_Complete
SFA10011 | TT_FinMile | Shaft A /Grout Block - Complete grout at pre-determined core locations | 01/04/2019 | 01/04/2019 | 21/01/2019 | 21/01/2019 | 0 | TK_Complete
SFA10012 | TT_Task | Shaft A /Grout Block - Full core samples | 01/04/2019 | 15/04/2019 | 22/01/2019 | 18/02/2019 | 0 | TK_Complete
SFA10013 | TT_Task | Shaf A /Grout Block - Grout test to 28 day strength | 31/03/2019 | 02/04/2019 | 08/02/2019 | 02/03/2019 | 0 | TK_Complete
SFA10014 | TT_Task | Shaft A/ Grout Block - Jet grout assessment report | 31/03/2019 | 06/04/2019 | 03/03/2019 | 08/05/2019 | 0 | TK_Complete
SFA10015 | TT_Task | Shaft A - BA8 consent for pile wall opening | 01/06/2019 | 28/06/2019 | 11/05/2019 | 05/06/2019 | 0 | TK_Complete
SFA10020 | TT_Task | Shaft A - 610 Dia. Pipe Pile Wall @ 750 c/c (41nos, total driving 1558m) | 15/03/2018 | 26/04/2018 | 12/02/2018 | 04/10/2018 | 0 | TK_Complete
SFA10030 | TT_Task | Shaft A - Grout Curtain (behind pipe pile wall) (total drilling 1271m) | 29/11/2018 | 20/12/2018 | 03/11/2018 | 18/12/2018 | 0 | TK_Complete
SFA10035 | TT_Task | Shaft A - Dewatering / observation wells (x 6 nos.) | 10/01/2019 | 12/01/2019 | 19/12/2018 | 20/12/2018 | 0 | TK_Complete
SFA10040 | TT_Task | Shaft A - Pumping Test and Report Submission | 29/12/2018 | 18/01/2019 | 22/12/2018 | 23/01/2019 | 0 | TK_Complete
SFA10045 | TT_Task | Shaft A - BD Consent for Excavation &amp; ELS | 26/01/2019 | 22/02/2019 | 23/01/2019 | 18/02/2019 | 0 | TK_Complete
SFA10050 | TT_Task | Shaft A - Excavate to below 1st layer of ring beam / install lagging plate | 01/04/2019 | 06/04/2019 | 06/02/2019 | 10/02/2019 | 0 | TK_Complete
SFA10060 | TT_Task | Shaft A - Intstall 1st layer of ring beam | 08/04/2019 | 10/04/2019 | 11/02/2019 | 19/02/2019 | 0 | TK_Complete
SFA10070 | TT_Task | Shaft A - Excavate to below 2nd layer of ring beam | 01/04/2019 | 06/04/2019 | 19/02/2019 | 25/02/2019 | 0 | TK_Complete
SFA10080 | TT_Task | Shaft A - Intstall lagging plates and 2nd layer of ring beam | 01/04/2019 | 06/04/2019 | 26/02/2019 | 03/03/2019 | 0 | TK_Complete
SFA10090 | TT_Task | Shaft A - Excavate to below 3rd layer of ring beam | 01/04/2019 | 05/04/2019 | 04/03/2019 | 12/03/2019 | 0 | TK_Complete
SFA10100 | TT_Task | Shaft A - Intstall lagging plates and 3rd layer of ring beam | 02/04/2019 | 06/04/2019 | 13/03/2019 | 17/03/2019 | 0 | TK_Complete
SFA10110 | TT_Task | Shaft A - Excavate to below 4th layer of ring beam | 01/04/2019 | 05/04/2019 | 18/03/2019 | 26/03/2019 | 0 | TK_Complete
SFA10120 | TT_Task | Shaft A - Intstall lagging plates and 4th layer of ring beam | 02/04/2019 | 06/04/2019 | 26/03/2019 | 05/04/2019 | 0 | TK_Complete
SFA10130 | TT_Task | Shaft A - Excavate to below 5th layer of ring beam | 01/05/2019 | 06/05/2019 | 11/04/2019 | 21/04/2019 | 0 | TK_Complete
SFA10140 | TT_Task | Shaft A - Intstall lagging plates and 5th layer of ring beam | 02/05/2019 | 07/05/2019 | 21/04/2019 | 23/04/2019 | 0 | TK_Complete
SFA10150 | TT_Task | Shaft A - Excavate to below 6th layer of ring beam | 08/05/2019 | 13/05/2019 | 24/04/2019 | 29/04/2019 | 0 | TK_Complete
SFA10160 | TT_Task | Shaft A - Intstall lagging plates and 6th layer of ring beam | 09/05/2019 | 14/05/2019 | 29/04/2019 | 02/05/2019 | 0 | TK_Complete
SFA10170 | TT_Task | Shaft A - Excavate to below 7th layer of ring beam | 04/06/2019 | 08/06/2019 | 03/05/2019 | 09/05/2019 | 0 | TK_Complete
SFA10180 | TT_Task | Shaft A - Intstall lagging plates and 7th layer of ring beam | 05/06/2019 | 10/06/2019 | 09/05/2019 | 10/05/2019 | 0 | TK_Complete
SFA10190 | TT_Task | Shaft A - Excavate to below 8th layer of ring beam | 11/06/2019 | 14/06/2019 | 11/05/2019 | 15/05/2019 | 0 | TK_Complete
SFA10200 | TT_Task | Shaft A - Intstall lagging plates and 8thnd layer of ring beam | 12/06/2019 | 15/06/2019 | 15/05/2019 | 19/05/2019 | 0 | TK_Complete
SFA10205 | TT_Task | Shaft A - Excavate to below 9th layer of ring beam | 17/06/2019 | 22/06/2019 | 20/05/2019 | 25/05/2019 | 0 | TK_Complete
SFA10210 | TT_Task | Shaft A - Intstall lagging plates and 9th layer of ring beam | 18/06/2019 | 24/06/2019 | 25/05/2019 | 28/05/2019 | 0 | TK_Complete
SFA10212XX | TT_Task | Shaft A - 9th layer of skin wall achieve required strength | 01/09/2019 | 01/09/2019 | 29/05/2019 | 29/05/2019 | 0 | TK_Complete
SFA10215 | TT_Task | Shaft A - Excavate to below 10th layer of ring beam | 01/06/2019 | 05/06/2019 | 28/05/2019 | 30/05/2019 | 0 | TK_Complete
SFA10215XX | TT_Task | Shaft A - Excavate 10th layer further down 2m | 02/09/2019 | 02/09/2019 | 29/05/2019 | 29/05/2019 | 0 | TK_Complete
SFA10217XX | TT_Task | Shaft A - Construct 10th layer of 250mm skin wall | 02/09/2019 | 02/09/2019 | 29/05/2019 | 29/05/2019 | 0 | TK_Complete
SFA10220 | TT_Task | Shaft A - Intstall lagging plates and 10th layer of ring beam | 01/06/2019 | 05/06/2019 | 01/06/2019 | 09/06/2019 | 0 | TK_Complete
SFA10220XX | TT_Task | Shaft A - Excavate 11th layer further down 2m | 02/09/2019 | 02/09/2019 | 29/05/2019 | 29/05/2019 | 0 | TK_Complete
SFA10222XX | TT_Task | Shaft A - Construct 11th layer of 250mm skin wall | 02/09/2019 | 02/09/2019 | 29/05/2019 | 29/05/2019 | 0 | TK_Complete
SFA10223XX | TT_Task | Shaft A - 11th layer of skin wall achieve required strength | 02/09/2019 | 02/09/2019 | 29/05/2019 | 29/05/2019 | 0 | TK_Complete
SFA10225XX | TT_Task | Shaft A - Excavate 12th layer further down 2m | 02/09/2019 | 02/09/2019 | 29/05/2019 | 29/05/2019 | 0 | TK_Complete
SFA10227XX | TT_Task | Shaft A - Construct 12th layer of 250mm skin wall | 02/09/2019 | 02/09/2019 | 29/05/2019 | 29/05/2019 | 0 | TK_Complete
SFA10230XX | TT_Task | Shaft A - Excavate 13th layer further down 2m | 02/09/2019 | 02/09/2019 | 29/05/2019 | 29/05/2019 | 0 | TK_Complete
SFA10232XX | TT_Task | Shaft A - Construct 13th layer of 250mm skin wall | 02/09/2019 | 02/09/2019 | 29/05/2019 | 29/05/2019 | 0 | TK_Complete
SFA10233XX | TT_Task | Shaft A - 13th layer of skin wall achieve required strength | 02/09/2019 | 02/09/2019 | 29/05/2019 | 29/05/2019 | 0 | TK_Complete
SFA10250 | TT_Task | Shaft A - Excavate to final excavation level -22 mPD / Install lagging plate | 06/06/2019 | 06/06/2019 | 31/05/2019 | 31/05/2019 | 0 | TK_Complete
SFA10260 | TT_Task | Shaft A - Cast bottom skin wall, base slab and receiving platform | 01/08/2019 | 14/08/2019 | 03/06/2019 | 11/07/2019 | 0 | TK_Complete
SFA10280 | TT_Task | Shaft A - Break through pipe pile wall and at the TBM receiving areas | 06/09/2019 | 10/09/2019 | 05/08/2019 | 09/08/2019 | 0 | TK_Complete
SFA10282 | TT_Task | Shaft A - Get the shaft ready for receiving TBM | 01/08/2019 | 05/08/2019 | 12/07/2019 | 04/08/2019 | 0 | TK_Complete
SFA10284 | TT_Task | Shaft A - Cement mortar and with flooding with water | 11/09/2019 | 12/09/2019 | 10/08/2019 | 11/08/2019 | 0 | TK_Complete
SFA20010 | TT_Task | Shaft A - Receive TBM and demob off site | 01/11/2019 | 09/11/2019 | 22/08/2019 | 24/09/2019 | 0 | TK_Complete
SFA20020 | TT_Task | Shaft A - Install 1st vertical CW pipe section | 01/11/2019 | 06/11/2019 | 10/10/2019 | 13/10/2019 | 0 | TK_Complete
SFA20030 | TT_Task | Shaft A - Backfill to -18 mPD approx. 1m below the next pipe joint | 01/11/2019 | 05/11/2019 | 14/10/2019 | 14/10/2019 | 0 | TK_Complete
SFA20050 | TT_Task | Shaft A - Install remaining vertiicle CW pipe sections / fittings / headers | 01/11/2019 | 18/11/2019 | 24/10/2019 | 09/11/2019 | 0 | TK_Complete
SFA20060 | TT_Task | Shaft A - Backfill from -18 to +0.4 mPD | 01/11/2019 | 18/11/2019 | 28/10/2019 | 12/11/2019 | 0 | TK_Complete
SFA20210 | TT_Task | Shaft A - Construct rocket slab &amp; open pipe pile wall | 01/01/2020 | 07/01/2020 | 13/11/2019 | 09/12/2019 | 0 | TK_Complete
SFA20220 | TT_Task | Shaft A - Backfill to ground level | 01/01/2020 | 02/01/2020 | 18/12/2019 | 19/12/2019 | 0 | TK_Complete
EV002010 | TT_Task | Event 002 - Shaft F Pre-drilling (5 nos.) | 06/10/2017 | 14/10/2017 | 06/10/2017 | 17/10/2017 | 0 | TK_Complete
EV002020 | TT_Task | Event 002a - Shaft F Pre-drilling (4 nos. additional) | 19/10/2017 | 01/11/2017 | 19/10/2017 | 01/11/2017 | 0 | TK_Complete
EV003020 | TT_Task | Event 003a - 6.6kVA cable strike at Shaft A | 23/10/2017 | 23/10/2017 | 24/10/2017 | 17/11/2017 | 0 | TK_Complete
EV003021 | TT_FinMile | Event 003a - Permit to excavation granted | 23/10/2017 | 23/10/2017 | 17/11/2017 | 17/11/2017 | 0 | TK_Complete
EV003022 | TT_Task | Event 003a - Additional trial trenhes prior to pipe piling | 23/10/2017 | 23/10/2017 | 18/11/2017 | 23/11/2017 | 0 | TK_Complete
EV011010 | TT_FinMile | Event 011F - Trial jet grout consent condition imposed on shaft excavation | 23/04/2018 | 23/04/2018 | 26/02/2018 | 26/02/2018 | 0 | TK_Complete
EV011020 | TT_Task | Event 011F - Install trial get grout ( x3 nos.) | 23/04/2018 | 25/04/2018 | 07/03/2018 | 09/03/2018 | 0 | TK_Complete
EV011030 | TT_Task | Event 011F - Core sample after 21 days from grout installed | 07/05/2018 | 19/05/2018 | 29/03/2018 | 24/05/2018 | 0 | TK_Complete
EV011040 | TT_Task | Event 011F - Test to early achievement of 28 day strength | 26/07/2018 | 28/07/2018 | 12/07/2018 | 14/07/2018 | 0 | TK_Complete
EV011050 | TT_Task | Event 011F - Formal test report issued for submission in 7 calendar days | 02/08/2018 | 08/08/2018 | 15/07/2018 | 28/07/2018 | 0 | TK_Complete
EV011052 | TT_Task | Event 011F - BD interview on trial jet grout assessment report | 01/12/2018 | 01/12/2018 | 04/09/2018 | 04/09/2018 | 0 | TK_Complete
EV011060 | TT_Task | Event 011F - Shaft F - BA8 for full scale grout block and excav below -9.6 mPD | 11/12/2018 | 07/01/2019 | 05/10/2018 | 22/11/2018 | 0 | TK_Complete
EV012010 | TT_FinMile | Event 012F - Settlement Assessment - BD monitoring team visit to site | 23/04/2018 | 23/04/2018 | 01/03/2018 | 01/03/2018 | 0 | TK_Complete
EV012020 | TT_Task | Event 012F - Settlement Assessment - Report preparation and submission to BD | 23/04/2018 | 03/05/2018 | 02/03/2018 | 13/03/2018 | 0 | TK_Complete
EV012030 | TT_Task | Event 012F - Settlement Assessment - Report review by BD | 04/05/2018 | 17/05/2018 | 14/03/2018 | 22/06/2018 | 0 | TK_Complete
EV012035 | TT_FinMile | Event 012F - Settlement Assessment - BD accept the report and resume to handle BA8 consent application | 15/07/2018 | 15/07/2018 | 22/06/2018 | 22/06/2018 | 0 | TK_Complete
EV012040 | TT_Task | Event 012F - Request and Issue of ROI for screen wall and other precautionary measures | 23/04/2018 | 27/04/2018 | 14/03/2018 | 28/03/2018 | 0 | TK_Complete
EV012050 | TT_Task | Event 012F - Settlement Assessment - Install screen wall as precautionary measure (i.e. JCG x17 nos.) | 28/04/2018 | 19/05/2018 | 29/03/2018 | 13/04/2018 | 0 | TK_Complete
EV012060 | TT_Task | Event 012F - Settlement Assessment - Install TAM grout in between screen wall and Shaft F pile wall | 28/04/2018 | 08/05/2018 | 19/04/2018 | 27/04/2018 | 0 | TK_Complete
EV012065 | TT_Task | Event 012F - Settlement Assessment - ADMS to existing CWP (x32) | 28/04/2018 | 29/05/2018 | 02/05/2018 | 15/06/2018 | 0 | TK_Complete
EV012070 | TT_Task | Event 012F - Settlement Assessment - SPT (x3) | 28/04/2018 | 26/05/2018 | 05/05/2018 | 01/06/2018 | 0 | TK_Complete
EV012075 | TT_Task | Event 012F - Settlement Assessment - Trial Pile (x3) | 28/04/2018 | 14/05/2018 | 17/05/2018 | 31/05/2018 | 0 | TK_Complete
EV012080 | TT_Task | Event 012F - Settlement Assessment - Exposing CWP pipe crown (x7) | 28/04/2018 | 08/05/2018 | 21/05/2018 | 28/05/2018 | 0 | TK_Complete
EV012085 | TT_Task | Event 012F - Settlement Assessment - Full core sample (x1) of jet grout screen wall | 26/06/2018 | 04/07/2018 | 26/05/2018 | 08/06/2018 | 0 | TK_Complete
EV022006 | TT_Task | Event 022 - Additional monitoring points hand-marked by BD during AAA amendement | 26/06/2018 | 15/07/2018 | 23/06/2018 | 04/07/2018 | 0 | TK_Complete
EV022008 | TT_Task | Event 022 - Re-do Stage 1 pump test as per AAA amendment | 28/06/2018 | 09/07/2018 | 28/06/2018 | 22/07/2018 | 0 | TK_Complete
EV022010 | TT_Task | Event 022 - Stage 2 pump test as per AAA amendment | 26/07/2018 | 09/08/2018 | 23/07/2018 | 15/08/2018 | 0 | TK_Complete
EV022012 | TT_Task | Event 022 - Re-do Stage 2 pump test at -9.6 mPD | 26/12/2018 | 15/01/2019 | 15/12/2018 | 08/01/2019 | 0 | TK_Complete
EV024010 | TT_Task | Event 024 - Re-do full core of trial jet grout x1 no. as per AAA amendment | 26/07/2018 | 01/08/2018 | 09/07/2018 | 11/07/2018 | 0 | TK_Complete
EV024020 | TT_Task | Event 024 - Re-do full core / backfill grout to core hole | 26/07/2018 | 26/07/2018 | 12/07/2018 | 12/07/2018 | 0 | TK_Complete
EV024030 | TT_Task | Event 024 - Re-do full core / curing grout cube for 28 days | 26/07/2018 | 22/08/2018 | 13/07/2018 | 09/08/2018 | 0 | TK_Complete
EV024040 | TT_Task | Event 024 - Redo full core / cube test and lab report | 26/11/2018 | 30/11/2018 | 03/08/2018 | 11/08/2018 | 0 | TK_Complete
EV029010 | TT_Task | Event 029 - MC grouting note amendment (Type II) | 26/07/2018 | 24/08/2018 | 13/07/2018 | 13/08/2018 | 0 | TK_Complete
EV029020 | TT_Task | Event 029 - Resubmit BA14 for grout curtain | 26/08/2018 | 26/08/2018 | 13/08/2018 | 13/08/2018 | 0 | TK_Complete
EV030010 | TT_Task | Event 030 - Additional Tests / Agree and finalize test method and location | 26/07/2018 | 23/09/2018 | 23/06/2018 | 23/08/2018 | 0 | TK_Complete
EV030020 | TT_Task | Event 030 - Additional Tests / Carry out the additional tests | 26/08/2018 | 14/09/2018 | 24/08/2018 | 14/09/2018 | 0 | TK_Complete
EV030030 | TT_Task | Event 030 - Additional tests / (Type II) Amendment | 26/08/2018 | 24/09/2018 | 23/08/2018 | 19/09/2018 | 0 | TK_Complete
EV030040 | TT_Task | Event 030 - Additional tests / Prepare and submit assessment report to BD 1 week prior to excavation below +3.2 | 26/11/2018 | 02/12/2018 | 19/09/2018 | 25/09/2018 | 0 | TK_Complete
SFF10010 | TT_Task | Shaft F - Grout Blocks (at launching areas) (total drilling 1822m) | 27/12/2018 | 23/01/2019 | 26/11/2018 | 27/02/2019 | 0 | TK_Complete
SFF10011 | TT_FinMile | Shaft F /Grout Block - Complete grout at pre-determined core locations (AD TBC) | 31/03/2019 | 31/03/2019 | 25/02/2019 | 25/02/2019 | 0 | TK_Complete
SFF10012 | TT_Task | Shaft F /Grout Block - Core sample after 21 days from grout installed (AD TBC) | 18/04/2019 | 15/05/2019 | 26/02/2019 | 18/03/2019 | 0 | TK_Complete
SFF10013 | TT_Task | Shaf F /Grout Block - Test to early achievement of 28 day strength (AD TBC) | 16/05/2019 | 18/05/2019 | 19/03/2019 | 21/03/2019 | 0 | TK_Complete
SFF10014 | TT_Task | Shaft F/ Grout Block - Formal test report issued for submission in 7 calendar days (AD TBC) | 19/05/2019 | 25/05/2019 | 22/03/2019 | 28/03/2019 | 0 | TK_Complete
SFF10015 | TT_Task | Shaft F - BA8 consent for pile wall opening | 01/05/2019 | 28/05/2019 | 18/04/2019 | 31/05/2019 | 0 | TK_Complete
SFF10020 | TT_Task | Shaft F - 610 Dia. Pipe Pile Wall @ 750 c/c (57 nos., total driving 2223m) | 01/11/2017 | 14/12/2017 | 24/11/2017 | 02/03/2018 | 0 | TK_Complete
SFF10025 | TT_Task | Shaft F - BD Consent for Commencement of Excavation &amp; ELS (above +3.2 mPD) | 15/06/2018 | 12/07/2018 | 03/05/2018 | 06/07/2018 | 0 | TK_Complete
SFF10030 | TT_Task | Shaft F - Grout Curtain (behind pipe pile wall) (total drilling 1950m) | 01/03/2018 | 09/04/2018 | 23/02/2018 | 26/03/2018 | 0 | TK_Complete
SFF10035 | TT_Task | Shaft F - Install pump well and observation well | 23/04/2018 | 03/05/2018 | 17/03/2018 | 26/03/2018 | 0 | TK_Complete
SFF10040 | TT_Task | Shaft F - Pumping Test (Stage 1) [not accepted by BD] | 06/05/2018 | 14/05/2018 | 29/03/2018 | 30/04/2018 | 0 | TK_Complete
SFF10041 | TT_Task | Shaft F - Prepare and submit Stage 1 pumping test report | 26/07/2018 | 30/07/2018 | 23/07/2018 | 07/08/2018 | 0 | TK_Complete
SFF10043 | TT_Task | Shaft F - BD Consent for Commencement of Excavation &amp; ELS (from +3.2 to -9.6 mPD)[WITHDRAWN] | 26/08/2018 | 08/09/2018 | 30/07/2018 | 12/08/2018 | 0 | TK_Complete
SFF10045 | TT_Task | Shaft F - BD Consent for Commencement of Excavation &amp; ELS (from +3.2 to -9.6 mPD)[RESUBMIT] | 09/09/2018 | 06/10/2018 | 13/08/2018 | 07/09/2018 | 0 | TK_Complete
SFF10050 | TT_Task | Shaft F - Excavate to below 1st layer of ring beam / Install lagging plates | 27/08/2018 | 06/09/2018 | 16/08/2018 | 07/09/2018 | 0 | TK_Complete
SFF10055 | TT_Task | Shaft F - BD Consent for Commencement of Excavation &amp; ELS below -17 mPD | 26/01/2019 | 22/02/2019 | 08/01/2019 | 13/02/2019 | 0 | TK_Complete
SFF10060 | TT_Task | Shaft F - Intstall 1st layer of ring beam | 27/11/2018 | 05/12/2018 | 08/09/2018 | 29/09/2018 | 0 | TK_Complete
SFF10070 | TT_Task | Shaft F - Excavate to below 2nd layer of ring beam | 26/11/2018 | 29/11/2018 | 02/10/2018 | 06/10/2018 | 0 | TK_Complete
SFF10080 | TT_Task | Shaft F - Intstall lagging plates and 2nd layer of ring beam | 27/11/2018 | 30/11/2018 | 04/10/2018 | 11/10/2018 | 0 | TK_Complete
SFF10090 | TT_Task | Shaft F - Excavate to below 3rd layer of ring beam | 01/12/2018 | 05/12/2018 | 11/10/2018 | 17/10/2018 | 0 | TK_Complete
SFF10100 | TT_Task | Shaft F - Intstall lagging plates and 3rd layer of ring beam | 03/12/2018 | 06/12/2018 | 12/10/2018 | 28/10/2018 | 0 | TK_Complete
SFF10110 | TT_Task | Shaft F - Excavate to below 4th layer of ring beam | 07/12/2018 | 11/12/2018 | 29/10/2018 | 03/11/2018 | 0 | TK_Complete
SFF10120 | TT_Task | Shaft F - Intstall lagging plates and 4th layer of ring beam | 08/12/2018 | 12/12/2018 | 31/10/2018 | 08/11/2018 | 0 | TK_Complete
SFF10130 | TT_Task | Shaft F - Excavate to below 5th layer of ring beam | 26/11/2018 | 30/11/2018 | 09/11/2018 | 14/11/2018 | 0 | TK_Complete
SFF10140 | TT_Task | Shaft F - Intstall lagging plates and 5th layer of ring beam (AF TBC) | 26/11/2018 | 29/11/2018 | 10/11/2018 | 20/11/2018 | 0 | TK_Complete
SFF10150 | TT_Task | Shaft F - Excavate to below 6th layer of ring beam (AS TBC) | 26/11/2018 | 29/11/2018 | 21/11/2018 | 27/11/2018 | 0 | TK_Complete
SFF10160 | TT_Task | Shaft F - Intstall lagging plates and 6th layer of ring beam | 26/11/2018 | 28/11/2018 | 23/11/2018 | 03/12/2018 | 0 | TK_Complete
SFF10170 | TT_Task | Shaft F - Excavate to below 7th layer of ring beam | 31/01/2019 | 06/02/2019 | 01/01/2019 | 07/01/2019 | 0 | TK_Complete
SFF10180 | TT_Task | Shaft F - Intstall lagging plates and 7th layer of ring beam | 26/01/2019 | 05/02/2019 | 03/01/2019 | 15/01/2019 | 0 | TK_Complete
SFF10190 | TT_Task | Shaft F - Excavate to below 8th layer of ring beam | 26/01/2019 | 01/02/2019 | 15/01/2019 | 20/01/2019 | 0 | TK_Complete
SFF10200 | TT_Task | Shaft F - Intstall lagging plates and 8th layer of ring beam | 26/01/2019 | 05/02/2019 | 16/01/2019 | 25/01/2019 | 0 | TK_Complete
SFF10205 | TT_Task | Shaft F - Excavate to below 9th layer of ring beam | 01/04/2019 | 06/04/2019 | 26/01/2019 | 01/02/2019 | 0 | TK_Complete
SFF10210 | TT_Task | Shaft F - Intstall lagging plates and 9th layer of ring beam | 01/04/2019 | 10/04/2019 | 27/01/2019 | 08/02/2019 | 0 | TK_Complete
SFF10215 | TT_Task | Shaft F - Excavate to below 10th layer of ring beam | 11/04/2019 | 16/04/2019 | 08/02/2019 | 14/02/2019 | 0 | TK_Complete
SFF10217 | TT_Task | Shaft F - Intstall lagging plates and 10th layer of ring beam | 01/04/2019 | 05/04/2019 | 09/02/2019 | 21/02/2019 | 0 | TK_Complete
SFF10220 | TT_Task | Shaft F - Excavate to below 11th layer of ring beam | 06/04/2019 | 11/04/2019 | 22/02/2019 | 28/02/2019 | 0 | TK_Complete
SFF10222 | TT_Task | Shaft F - Intstall lagging plates and 11th layer of ring beam | 08/04/2019 | 12/04/2019 | 23/02/2019 | 08/03/2019 | 0 | TK_Complete
SFF10225 | TT_Task | Shaft F - Excavate to below 12th layer of ring beam | 01/04/2019 | 16/04/2019 | 09/03/2019 | 07/04/2019 | 0 | TK_Complete
SFF10227 | TT_Task | Shaft F - Intstall lagging plates and 12th layer of ring beam | 04/04/2019 | 05/04/2019 | 16/03/2019 | 09/04/2019 | 0 | TK_Complete
SFF10230 | TT_Task | Shaft F - Excavate to below 13th layer of ring beam | 09/05/2019 | 17/05/2019 | 10/04/2019 | 06/05/2019 | 0 | TK_Complete
SFF10232 | TT_Task | Shaft F - Intstall lagging plates and 13th layer of ring beam | 01/06/2019 | 10/06/2019 | 01/05/2019 | 09/05/2019 | 0 | TK_Complete
SFF10250 | TT_Task | Shaft F - BD inspection on stratum | 11/06/2019 | 11/06/2019 | 10/05/2019 | 10/05/2019 | 0 | TK_Complete
SFF10260 | TT_Task | Shaft F - Cast base slab and bottom skin wall | 01/06/2019 | 14/06/2019 | 11/05/2019 | 07/06/2019 | 0 | TK_Complete
SFF10280 | TT_Task | Shaft F - Break through pipe pile wall for TBM driving to Shaft A | 05/08/2019 | 15/08/2019 | 08/06/2019 | 25/06/2019 | 0 | TK_Complete
SFF10290 | TT_Task | Shaft F - Break through pipe pile wall for TBM driving from Shaft E | 07/11/2019 | 17/11/2019 | 09/09/2019 | 24/09/2019 | 0 | TK_Complete
SFF10300 | TT_Task | Shaft F - Install bulkhead and flooding the shaft (E drive) | 18/11/2019 | 19/11/2019 | 09/10/2019 | 13/10/2019 | 0 | TK_Complete
SFF20010 | TT_Task | Shaft F - Set up and launch micro TBM to Shaft A | 01/08/2019 | 25/08/2019 | 15/06/2019 | 08/07/2019 | 0 | TK_Complete
SFF20020 | TT_Task | Shaft F - Micro tunneling and pipe jacking to Shaft A | 01/08/2019 | 18/08/2019 | 09/07/2019 | 21/08/2019 | 0 | TK_Complete
SFF20022 | TT_Task | Shaft F - Grouting and Welding CWP between Shaft A and Shaft F | 10/11/2019 | 29/11/2019 | 05/09/2019 | 10/10/2019 | 0 | TK_Complete
SFF20023XX | TT_Task | Shaft F - Testing to CWP between Shaft A and Shaft F | 01/01/2020 | 01/01/2020 | 07/12/2019 | 07/12/2019 | 0 | TK_Complete
SFF20030 | TT_Task | Shaft F - Micro tunneling and pipe jacking from Shaft E (Part 2 of 2) | 01/11/2019 | 11/11/2019 | 19/09/2019 | 17/10/2019 | 0 | TK_Complete
SFF20032 | TT_Task | Grouting and Welding CWP between Shaft E and Shaft F (Part 2 of 2) | 01/01/2020 | 06/01/2020 | 09/11/2019 | 15/11/2019 | 0 | TK_Complete
SFF20033XX | TT_Task | Testing to CWP between Shaft E and Shaft F (Part 2 of 2) | 01/01/2020 | 07/01/2020 | 07/12/2019 | 07/12/2019 | 0 | TK_Complete
SFF20035 | TT_Task | Shaft F - Demob launching rails (F drive) and install retrieval rails (E drive) | 01/01/2020 | 06/01/2020 | 08/09/2019 | 08/09/2019 | 0 | TK_Complete
SFF20040 | TT_Task | Shaft F - Receive TBM and demob off site | 01/01/2020 | 06/01/2020 | 18/10/2019 | 29/10/2019 | 0 | TK_Complete
SFF30010XX | TT_Task | Shaft F - Construct permanent shaft wall (Pour 1 of 8 / standard lift 3m) | 01/01/2020 | 01/01/2020 | 07/12/2019 | 07/12/2019 | 0 | TK_Complete
SFF30040XX | TT_Task | Shaft F - Construct permanent shaft wall (Pour 2 of 8) | 01/01/2020 | 01/01/2020 | 07/12/2019 | 07/12/2019 | 0 | TK_Complete
SFF30070XX | TT_Task | Shaft F - Construct permanent shaft wall (Pour 3 of 8) | 01/01/2020 | 01/01/2020 | 07/12/2019 | 07/12/2019 | 0 | TK_Complete
SFF30100XX | TT_Task | Shaft F - Construct permanent shaft wall (Pour 4 of 8) | 01/01/2020 | 01/01/2020 | 07/12/2019 | 07/12/2019 | 0 | TK_Complete
SFF30130XX | TT_Task | Shaft F - Construct permanent shaft wall (Pour 5 of 8) | 01/01/2020 | 01/01/2020 | 07/12/2019 | 07/12/2019 | 0 | TK_Complete
SFF30160XX | TT_Task | Shaft F - Construct permanent shaft wall (Pour 6 of 8) | 01/01/2020 | 01/01/2020 | 07/12/2019 | 07/12/2019 | 0 | TK_Complete
SFF30190XX | TT_Task | Shaft F - Construct permanent shaft wall (Pour 7 of 8) | 01/01/2020 | 01/01/2020 | 07/12/2019 | 07/12/2019 | 0 | TK_Complete
SFF30250XX | TT_Task | Shaft F - Construct the top slab of permanent shaft (with temporary opening for material delivery) | 01/01/2020 | 01/01/2020 | 07/12/2019 | 07/12/2019 | 0 | TK_Complete
SFF30260XX | TT_Task | Shaft F - Construct Maintenance Access Shaft and Emergency Access Shaft | 01/01/2020 | 01/01/2020 | 07/12/2019 | 07/12/2019 | 0 | TK_Complete
SFF30262 | TT_Task | Shaft F - Install vertical sections and precast stair wells including mass fill | 01/01/2020 | 08/02/2020 | 30/10/2019 | 06/12/2019 | 0 | TK_Complete
SFF30264 | TT_Task | Shaft F - Install CW pipe bends / horizontal section of supply pipeline above the top landing unit of staircase | 07/01/2020 | 09/01/2020 | 07/12/2019 | 23/12/2019 | 0 | TK_Complete
SFF30265XX | TT_Task | Shaft F - Install CW pipe bends / horizontal section of discharge pipeline above the top slab | 01/01/2020 | 07/01/2020 | 07/12/2019 | 07/12/2019 | 0 | TK_Complete
SFF30266XX | TT_Task | Shaft F - Seal up pipe penetrations through the top slab | 10/01/2020 | 10/01/2020 | 07/12/2019 | 07/12/2019 | 0 | TK_Complete
SFF30290 | TT_Task | Shaft F - Backfill to 2m existing ground level | 26/03/2020 | 01/04/2020 | 26/03/2020 | 01/04/2020 | 0 | TK_Complete
SFF30310 | TT_Task | Shaft F - Trim pipe pile wall to 2m below ground level | 02/04/2020 | 03/04/2020 | 02/04/2020 | 03/04/2020 | 0 | TK_Complete
SFF30320 | TT_Task | Shaft F - Backfill and reinstate to ground level | 04/04/2020 | 10/04/2020 | 04/04/2020 | 10/04/2020 | 0 | TK_Complete
SFF30330 | TT_Task | Shaft F - ABWF (i.e. finishes, metal works, etc) | 26/03/2020 | 21/04/2020 | 26/03/2020 | 21/04/2020 | 0 | TK_Complete
SFF30340 | TT_Task | Shaft F - Building Services installation | 26/03/2020 | 21/04/2020 | 26/03/2020 | 21/04/2020 | 0 | TK_Complete
DPT10010 | TT_Task | DPT /Zone A (Southern Section) - Pre-boring for sheet pile wall | 17/10/2017 | 15/11/2017 | 13/10/2017 | 14/01/2018 | 0 | TK_Complete
DPT10020 | TT_Task | DPT /Zone A (Southern Section) - Sheet Piling | 02/11/2017 | 27/11/2017 | 02/11/2017 | 31/01/2018 | 0 | TK_Complete
DPT10040 | TT_Task | DPT /Zone A (Southern Section) - Pumping Test and Report Submission | 10/04/2018 | 21/04/2018 | 09/02/2018 | 24/02/2018 | 0 | TK_Complete
DPT10045 | TT_Task | DPT /Zone A (Southern Section) - BD Consent for Commencement of Excavation &amp; ELS | 18/06/2018 | 15/07/2018 | 18/05/2018 | 22/06/2018 | 0 | TK_Complete
DPT10050 | TT_Task | DPT /Zone A (Southern Section) - Excavate to 0.5m below 1st layer of struts | 26/07/2018 | 03/08/2018 | 26/06/2018 | 06/07/2018 | 0 | TK_Complete
DPT10060 | TT_Task | DPT /Zone A (Southern Section) - Install 1st layer of struts | 02/08/2018 | 16/08/2018 | 05/07/2018 | 13/08/2018 | 0 | TK_Complete
DPT10070 | TT_Task | DPT /Zone A (Southern Section) - Excavate to 0.5m below 2nd layer of struts | 07/09/2018 | 24/09/2018 | 09/08/2018 | 25/08/2018 | 0 | TK_Complete
DPT10080 | TT_Task | DPT /Zone A (Southern Section) - Install 2nd layer of struts | 27/08/2018 | 20/09/2018 | 25/08/2018 | 05/10/2018 | 0 | TK_Complete
DPT10090 | TT_Task | DPT /Zone A (Southern Section) - Excavate to final excavation level -1.4 mPD | 26/11/2018 | 04/12/2018 | 24/09/2018 | 16/10/2018 | 0 | TK_Complete
DPT10100 | TT_Task | DPT /Zone A (Southern Section) - Cast base slab | 26/11/2018 | 04/12/2018 | 15/10/2018 | 08/11/2018 | 0 | TK_Complete
DPT10110 | TT_Task | DPT /Zone A (Southern Section) - Remove 2nd layer of struts | 01/12/2018 | 10/12/2018 | 25/10/2018 | 16/11/2018 | 0 | TK_Complete
DPT10120 | TT_Task | DPT /Zone A (Southern Section) - Install Cooling Water Pipe (39 nos.) | 26/11/2018 | 22/12/2018 | 03/11/2018 | 31/12/2018 | 0 | TK_Complete
DPT10125XX | TT_Task | DPT /Zone A (Southern Section) - Testing to Cooling Water Pipe (TBC) | 01/01/2020 | 10/01/2020 | 01/01/2019 | 01/01/2019 | 0 | TK_Complete
DPT10130 | TT_Task | DPT /Zone A (Southern Section) - Backfill to 0.5m below 1st layer of struts | 23/02/2019 | 28/02/2019 | 17/12/2018 | 22/12/2018 | 0 | TK_Complete
DPT10135 | TT_Task | DPT /Zone A (Southern Section) - Concrete surround | 02/02/2019 | 22/02/2019 | 01/12/2018 | 15/12/2018 | 0 | TK_Complete
DPT10140 | TT_Task | DPT /Zone A (Southern Section) - Remove 1st layer of struts | 18/02/2019 | 02/03/2019 | 28/12/2018 | 31/12/2018 | 0 | TK_Complete
DPT10150 | TT_Task | DPT /Zone A (Southern Section) - Trim down sheet pile 2m | 01/03/2019 | 07/03/2019 | 30/12/2018 | 02/01/2019 | 0 | TK_Complete
DPT10160 | TT_Task | DPT /Zone A (Southern Section) - Backfill and form slope to the formation of Generator Transformer | 11/03/2019 | 11/03/2019 | 28/12/2018 | 02/01/2019 | 0 | TK_Complete
DPT20010 | TT_Task | DPT /Zone B (Middle Section) - Grouting to the eastern side of double pipe trench | 25/09/2017 | 02/11/2017 | 23/09/2017 | 07/02/2018 | 0 | TK_Complete
DPT20030 | TT_Task | DPT /Zone B (Middle Section) - Grouting to the western side of double pipe trench | 03/10/2017 | 06/11/2017 | 02/10/2017 | 07/02/2018 | 0 | TK_Complete
DPT20092 | TT_Task | DPT/ Zone B Central - Open cut excavation | 26/01/2019 | 14/02/2019 | 29/11/2018 | 18/12/2018 | 0 | TK_Complete
DPT20094 | TT_Task | DPT/ Zone B South (i.e. Zone A Interface) - Open cut excavation | 26/01/2019 | 08/02/2019 | 31/12/2018 | 12/01/2019 | 0 | TK_Complete
DPT20096 | TT_Task | DPT/ Zone B North (i.e. KSS Interface) - Open cut excavation | 26/01/2019 | 06/02/2019 | 24/01/2019 | 08/02/2019 | 0 | TK_Complete
DPT20098 | TT_Task | DPT/ Zone B North (i.e. KSS Crane Access) - Open cut excavation | 01/04/2019 | 11/04/2019 | 09/03/2019 | 11/03/2019 | 0 | TK_Complete
DPT20102 | TT_Task | DPT/ Zone B Central - Base slab | 26/01/2019 | 31/01/2019 | 18/12/2018 | 22/12/2018 | 0 | TK_Complete
DPT20104 | TT_Task | DPT/ Zone B South (i.e. Zone A Interface) - Base slab | 26/01/2019 | 30/01/2019 | 13/01/2019 | 17/01/2019 | 0 | TK_Complete
DPT20106 | TT_Task | DPT/ Zone B North (i.e. KSS Interface) - Base slab | 01/04/2019 | 04/04/2019 | 09/02/2019 | 12/02/2019 | 0 | TK_Complete
DPT20108 | TT_Task | DPT/ Zone B North (i.e. KSS Crane Access) - Base slab | 01/04/2019 | 04/04/2019 | 13/03/2019 | 15/03/2019 | 0 | TK_Complete
DPT20122 | TT_Task | DPT/ Zone B Central - CW pipe installation | 26/01/2019 | 05/02/2019 | 24/12/2018 | 03/01/2019 | 0 | TK_Complete
DPT20124 | TT_Task | DPT/ Zone B South (i.e. Zone A Interface) - CW pipe installation | 26/01/2019 | 01/02/2019 | 17/01/2019 | 23/01/2019 | 0 | TK_Complete
DPT20126 | TT_Task | DPT/ Zone B North (i.e. KSS Interface) - CW pipe installation | 31/03/2019 | 01/04/2019 | 13/02/2019 | 15/02/2019 | 0 | TK_Complete
DPT20128 | TT_Task | DPT/ Zone B North (i.e. KSS Crane Access) - CW pipe installation | 31/03/2019 | 05/04/2019 | 16/03/2019 | 21/03/2019 | 0 | TK_Complete
DPT20130XX | TT_Task | DPT /Zone B (Middle Section) - Testing to Cooling Water Pipe (TBC) | 01/01/2020 | 11/01/2020 | 03/04/2019 | 03/04/2019 | 0 | TK_Complete
DPT20162 | TT_Task | DPT/ Zone B Central - Concrete surround &amp; backfill | 26/01/2019 | 08/02/2019 | 07/01/2019 | 19/01/2019 | 0 | TK_Complete
DPT20164 | TT_Task | DPT/ Zone B South (i.e. Zone A Interface) - Concrete surround &amp; backfill | 26/01/2019 | 08/02/2019 | 17/01/2019 | 30/01/2019 | 0 | TK_Complete
DPT20166 | TT_Task | DPT/ Zone B North (i.e. KSS Interface) - Concrete surround &amp; backfill | 02/04/2019 | 17/04/2019 | 16/02/2019 | 25/02/2019 | 0 | TK_Complete
DPT20168 | TT_Task | DPT/ Zone B North (i.e. KSS Crane Access) - Concrete surround &amp; backfill | 06/04/2019 | 27/04/2019 | 15/03/2019 | 02/04/2019 | 0 | TK_Complete
DPT30010 | TT_Task | DPT /Zone C (Northern Section) - Pipe Piles adjoining Shaft F (13 nos) | 23/04/2018 | 05/05/2018 | 03/03/2018 | 13/03/2018 | 0 | TK_Complete
DPT30015 | TT_Task | DPT /Zone C (Northern Section) - Remaining Eastern Pipe Pile (60 nos) | 07/05/2018 | 25/06/2018 | 14/03/2018 | 02/05/2018 | 0 | TK_Complete
DPT30020 | TT_Task | DPT /Zone C (Northern Section) - Remaining Western Pipe Pile (50 nos) | 13/06/2018 | 24/07/2018 | 07/04/2018 | 28/04/2018 | 0 | TK_Complete
DPT30030 | TT_Task | DPT /Zone C (Northern Section) - Grout Curtain East | 26/05/2018 | 30/06/2018 | 27/04/2018 | 07/06/2018 | 0 | TK_Complete
DPT30035 | TT_Task | DPT /Zone C (Northern Section) - Grout Curtain West | 16/06/2018 | 19/07/2018 | 27/04/2018 | 07/06/2018 | 0 | TK_Complete
DPT30040 | TT_Task | DPT /Zone C (Northern Section) - Pumping Test and Report Submission | 02/05/2019 | 22/05/2019 | 26/04/2019 | 03/07/2019 | 0 | TK_Complete
DPT30045 | TT_Task | DPT /Zone C (Northern Section) - BD Consent for Commencement of Excavation &amp; ELS | 21/08/2019 | 17/09/2019 | 25/06/2019 | 22/07/2019 | 0 | TK_Complete
DPT30082 | TT_Task | DPT /Zone C (Northern Section) - Excavation to 0.5m below 1st layer struts | 01/08/2019 | 14/08/2019 | 12/07/2019 | 22/07/2019 | 0 | TK_Complete
DPT30084 | TT_Task | DPT /Zone C (Northern Section) - Install 1st layer of struts | 15/08/2019 | 28/08/2019 | 22/07/2019 | 27/07/2019 | 0 | TK_Complete
DPT30086 | TT_Task | DPT /Zone C (Northern Section) - Excavation to 0.5m below 2nd layer struts | 01/08/2019 | 14/08/2019 | 31/07/2019 | 24/08/2019 | 0 | TK_Complete
DPT30088 | TT_Task | DPT /Zone C (Northern Section) - Install 2nd layer of struts | 15/09/2019 | 21/09/2019 | 22/08/2019 | 03/09/2019 | 0 | TK_Complete
DPT30090 | TT_Task | DPT /Zone C (Northern Section) - Excavation to formation level | 04/11/2019 | 10/11/2019 | 04/09/2019 | 12/09/2019 | 0 | TK_Complete
DPT30100 | TT_Task | DPT /Zone C (Northern Section) - Plate load test x2 sets | 01/11/2019 | 06/11/2019 | 13/09/2019 | 16/09/2019 | 0 | TK_Complete
DPT30120 | TT_Task | DPT /Zone C (Northern Section) - Install Cooling Water Pipe | 17/09/2019 | 05/10/2019 | 24/08/2019 | 15/10/2019 | 0 | TK_Complete
DPT30125XX | TT_Task | DPT /Zone C (Northern Section) - Testing to Cooling Water Pipe | 01/01/2020 | 01/01/2020 | 16/10/2019 | 16/10/2019 | 0 | TK_Complete
DPT30130 | TT_Task | DPT /Zone C (Northern Section) - Break Shaft F pipe pile wall at the supply pipeline interface | 01/01/2020 | 03/01/2020 | 14/12/2019 | 16/12/2019 | 0 | TK_Complete
DPT30140 | TT_Task | DPT /Zone C (Northern Section) - Connect CW supply pipeline to Shaft F | 13/01/2020 | 15/01/2020 | 07/12/2019 | 23/12/2019 | 0 | TK_Complete
DPT30150 | TT_Task | DPT /Seal Pit - Stitch connection of Seal Pit between Shaft F and Zone C | 24/02/2020 | 06/03/2020 | 08/12/2019 | 22/12/2019 | 0 | TK_Complete
DPT30200 | TT_Task | DPT /Zone C (Northern Section) - Trim top 2m pipe piles | 13/01/2020 | 18/01/2020 | 13/01/2020 | 18/01/2020 | 0 | TK_Complete
DPT30210 | TT_Task | DPT /Zone C (Northern Section) - Backfill and reinstate to ground level | 20/01/2020 | 05/02/2020 | 20/01/2020 | 05/02/2020 | 0 | TK_Complete
DPT40010 | TT_Task | DPT /Seal Pit - Construct parts of structure within Zone C | 01/01/2020 | 23/02/2020 | 19/09/2019 | 19/12/2019 | 0 | TK_Complete
DPT40020 | TT_Task | DPT /Seal Pit - Connect CW pipes to the discharge line at Zone C | 01/01/2020 | 06/01/2020 | 26/11/2019 | 26/11/2019 | 0 | TK_Complete
DPT40030 | TT_Task | DPT /Seal Pit - Construct balance of structure in Shaft F / Zone C | 01/01/2020 | 21/01/2020 | 07/12/2019 | 07/12/2019 | 0 | TK_Complete
DPT40040 | TT_Task | DPT /Seal Pit - ABWF | 13/01/2020 | 30/01/2020 | 13/01/2020 | 30/01/2020 | 0 | TK_Complete
DPT40050 | TT_Task | DPT /Seal Pit - Building Services Installation | 13/01/2020 | 30/01/2020 | 13/01/2020 | 30/01/2020 | 0 | TK_Complete
EV006010 | TT_Task | Event 006 - Unchartered UU found at Zone A (slow down pre-boring progress) | 23/10/2017 | 23/10/2017 | 09/11/2017 | 29/12/2017 | 0 | TK_Complete
EV012100 | TT_FinMile | Event 012ZA - Settlement Assessment - BD monitoring team visit to site | 23/04/2018 | 23/04/2018 | 01/03/2018 | 01/03/2018 | 0 | TK_Complete
EV012110 | TT_Task | Event 012ZA - Settlement Assessment - Report preparation and submission to BD | 23/04/2018 | 28/04/2018 | 05/03/2018 | 17/05/2018 | 0 | TK_Complete
EV012120 | TT_Task | Event 012ZA - Settlement Assessment - Report review and comment by BD | 29/04/2018 | 12/05/2018 | 16/03/2018 | 22/06/2018 | 0 | TK_Complete
EV012130 | TT_FinMile | Event 012ZA - Settlement Assessment - BD accept the report and resume to handle BA8 consent application | 17/07/2018 | 17/07/2018 | 22/06/2018 | 22/06/2018 | 0 | TK_Complete
EV012140 | TT_Task | Event 012ZA - Request and Issue of ROI for Post Grouting to Transformer Rd and other precautionary measures | 29/04/2018 | 03/05/2018 | 08/03/2018 | 18/03/2018 | 0 | TK_Complete
EV012150 | TT_Task | Event 012ZA - Settlement Assessment - Post remedial grouting to Transformer Rd (36 nos. +4 SPT) | 05/05/2018 | 25/05/2018 | 19/03/2018 | 04/04/2018 | 0 | TK_Complete
EV012160 | TT_Task | Event 012ZA - Settlement Assessment - Instruction of additional remedial grouting (24 nos. - ROI #72) | 05/05/2018 | 10/05/2018 | 05/04/2018 | 11/04/2018 | 0 | TK_Complete
EV012170 | TT_Task | Event 012ZA - Settlement Assessment - Post remedial grouting to Transformer Rd (24 nos.) | 05/05/2018 | 16/05/2018 | 12/04/2018 | 23/04/2018 | 0 | TK_Complete
EV012180 | TT_Task | Event 012ZA - Settlement Assessment - Awaiting confirmation on locations of 2 nos,. additional SPT | 27/05/2018 | 01/06/2018 | 24/04/2018 | 25/04/2018 | 0 | TK_Complete
EV012190 | TT_Task | Event 012ZA - Settlement Assessment - 2 nos. additional SPT | 02/06/2018 | 08/06/2018 | 26/04/2018 | 05/05/2018 | 0 | TK_Complete
EV012200 | TT_Task | Event 012ZA - Settlement Assessment - Preparation and submission of supplementary information | 26/05/2018 | 08/06/2018 | 06/05/2018 | 17/05/2018 | 0 | TK_Complete
EV020020 | TT_Mile | Event 020 - Crane Access to Gas Filer across Zone B for M&amp;E (KSS) - Access Date | 26/11/2018 | 26/11/2018 | 03/09/2018 | 03/09/2018 | 0 | TK_Complete
EV020030 | TT_FinMile | Event 020 - KSS handover back the area | 31/03/2019 | 31/03/2019 | 08/03/2019 | 08/03/2019 | 0 | TK_Complete
EV021810 | TT_Task | Event 021(ZA) - AAA amendment for Zone A {4b1-alt A-2} [WITHDRAWN] | 26/05/2018 | 24/06/2018 | 16/03/2018 | 04/04/2018 | 0 | TK_Complete
EV021820 | TT_Task | Event 021(ZA) - AAA amendment for Zone A {4b1-alt A-2(r1)} [WITHDRAWN] | 26/05/2018 | 24/06/2018 | 24/04/2018 | 18/05/2018 | 0 | TK_Complete
EV021830 | TT_Task | Event 021(ZA) - AAA amendment for Zone A {4b1-alt A-2(r2)} | 26/05/2018 | 24/06/2018 | 18/05/2018 | 22/06/2018 | 0 | TK_Complete
EV039010 | TT_Task | Event 039(ZA) - Transformer Generator resequencing amendment (Part 1) | 26/07/2018 | 24/08/2018 | 29/06/2018 | 27/07/2018 | 0 | TK_Complete
EV039020 | TT_Task | Event 039(ZA) - Transformer Generator resequencing amendment (Part 2) | 26/08/2018 | 24/09/2018 | 24/08/2018 | 20/09/2018 | 0 | TK_Complete
EV042010 | TT_Task | Event 042 - Zone B FEL amendment (Type II) | 26/01/2019 | 24/02/2019 | 30/11/2018 | 28/12/2018 | 0 | TK_Complete
EV042020 | TT_Task | Event 042 - BA8 consent for Zone B FEL amendment | 26/01/2019 | 24/02/2019 | 30/11/2018 | 28/12/2018 | 0 | TK_Complete
EV045000 | TT_Task | Event 045 - Shaft F / Zone C Re-sequencing - Additional pipe piles | 26/01/2019 | 26/01/2019 | 11/01/2019 | 23/01/2019 | 0 | TK_Complete
EV045010 | TT_Task | Event 045 - Shaft F / Zone C Re-sequencing - Additional TAM grout | 01/04/2019 | 13/04/2019 | 23/03/2019 | 01/04/2019 | 0 | TK_Complete
EV011130 | TT_FinMile | Event 011D - Trial jet grout consent condition imposed on shaft excavation | 23/04/2018 | 23/04/2018 | 26/02/2018 | 26/02/2018 | 0 | TK_Complete
EV011140 | TT_Task | Event 011D - Install trial jet grout | 26/07/2018 | 28/07/2018 | 25/07/2018 | 28/07/2018 | 0 | TK_Complete
EV017010 | TT_Task | Event 017D - Shaft D Advanced Precautionary Grouting (32 out of 53) | 06/06/2018 | 05/07/2018 | 05/05/2018 | 09/06/2018 | 0 | TK_Complete
EV017012 | TT_Task | Event 017D - Shaft D Advanced Precautionary Grouting (1 out of 53) | 26/07/2018 | 26/07/2018 | 21/06/2018 | 22/06/2018 | 0 | TK_Complete
EV017014 | TT_Task | Event 017D - Shaft D Advanced Precautionary Grouting (9 out of 53) | 26/07/2018 | 26/07/2018 | 26/06/2018 | 03/07/2018 | 0 | TK_Complete
EV017016 | TT_Task | Event 017D - Shaft D Advanced Precautionary Grouting (11 out of 53) | 26/08/2018 | 30/08/2018 | 29/07/2018 | 02/08/2018 | 0 | TK_Complete
EV021310 | TT_Task | Event 021D - Shaft D AAA amendment (Type II) / submission &amp; approval | 26/06/2018 | 25/07/2018 | 30/05/2018 | 03/07/2018 | 0 | TK_Complete
EV021320 | TT_Task | Event 021D - Shaft D AAA amendment / consent for APG &amp; trial jet grout | 26/07/2018 | 22/08/2018 | 18/06/2018 | 25/07/2018 | 0 | TK_Complete
EV031010 | TT_Task | Event 031D - Works suspended after FS main stirke in Diversion Culvet works area | 26/07/2018 | 26/07/2018 | 04/07/2018 | 09/07/2018 | 0 | TK_Complete
EV032010 | TT_Task | Event 032D - Works suspension instructed to await BD consent | 26/07/2018 | 26/07/2018 | 12/07/2018 | 23/07/2018 | 0 | TK_Complete
EV032020 | TT_FinMile | Event 032D - Site Memo 383 suggesting works can be resumed as 28d consent statutory time overdue since 15/7/18 | 26/07/2018 | 26/07/2018 | 23/07/2018 | 23/07/2018 | 0 | TK_Complete
EV033010 | TT_FinMile | Event 033 - ROI #144 / date of issuance | 26/08/2018 | 26/08/2018 | 24/08/2018 | 24/08/2018 | 0 | TK_Complete
SFD00010 | TT_Task | Shaft D - Utilities Diversion | 23/04/2018 | 14/06/2018 | 07/03/2018 | 20/06/2018 | 0 | TK_Complete
SFD10302 | TT_Task | Grouting and Welding to CWP between Shaft E and Shaft F (Part 1 of 2) | 01/01/2020 | 09/01/2020 | 31/10/2019 | 08/11/2019 | 0 | TK_Complete
EV011190 | TT_FinMile | Event 011E - Trial jet grout consent condition imposed on shaft excavation | 23/04/2018 | 23/04/2018 | 26/02/2018 | 26/02/2018 | 0 | TK_Complete
EV011200 | TT_Task | Event 011E - Install trial get grout ( x3 nos.) | 27/08/2018 | 30/08/2018 | 04/08/2018 | 07/08/2018 | 0 | TK_Complete
EV011210 | TT_Task | Event 011E - Permeability Test + Core sample after 21 days from grout installed | 06/12/2018 | 19/12/2018 | 07/09/2018 | 20/09/2018 | 0 | TK_Complete
EV011220 | TT_Task | Event 011E - Test to early achievement of 28 day strength | 06/12/2018 | 08/12/2018 | 13/09/2018 | 21/09/2018 | 0 | TK_Complete
EV011225 | TT_Task | Event 011E - Curing and cube test to backfill grout | 06/12/2018 | 02/01/2019 | 21/09/2018 | 18/10/2018 | 0 | TK_Complete
EV011230 | TT_Task | Event 011E - Formal test report issued for submission in 7 calendar days | 06/12/2018 | 12/12/2018 | 03/11/2018 | 04/12/2018 | 0 | TK_Complete
EV011240 | TT_Task | Event 011E - Shaft E - BA8 for full scale grout block and excav below -1.6 mPD | 05/01/2019 | 01/02/2019 | 30/11/2018 | 24/12/2018 | 0 | TK_Complete
EV017020 | TT_Task | Event 017E - Shaft E - Preventive Grouting | 06/06/2018 | 05/07/2018 | 10/05/2018 | 25/05/2018 | 0 | TK_Complete
EV021610 | TT_Task | Event 021E - AAA amendment (and cofferdam enlargement) for Shaft E | 26/07/2018 | 24/08/2018 | 29/06/2018 | 27/07/2018 | 0 | TK_Complete
EV021620 | TT_Task | Event 021E - Consent for pipe piles (incl' APG) and grout curtain further to AAA amendment | 26/08/2018 | 05/09/2018 | 27/07/2018 | 06/08/2018 | 0 | TK_Complete
EV034010 | TT_FinMile | Event 034 - ROI #113 Crest Wall Removal / date of issuance | 16/07/2018 | 16/07/2018 | 16/07/2018 | 16/07/2018 | 0 | TK_Complete
EV034020 | TT_Task | Event 034 - ROI #113 Crest Wall Removal / method statement, mobilize subcon, etc | 26/07/2018 | 24/08/2018 | 17/07/2018 | 14/08/2018 | 0 | TK_Complete
EV034030 | TT_Task | Event 034 - ROI #113 Crest Wall Removal / site works | 15/09/2018 | 05/10/2018 | 15/08/2018 | 10/09/2018 | 0 | TK_Complete
EV060010 | TT_Task | Event 060E - Probing test to jet grout block | 01/06/2019 | 02/06/2019 | 16/05/2019 | 16/05/2019 | 0 | TK_Complete
SFE00010 | TT_Task | Shaft E - Utilities Diversion | 04/05/2018 | 25/06/2018 | 19/03/2018 | 30/05/2018 | 0 | TK_Complete
SFE10025 | TT_Mile | Shaft E - Implement TTM on Sea Bank Road | 04/05/2018 | 04/05/2018 | 19/03/2018 | 19/03/2018 | 0 | TK_Complete
SFE10029 | TT_Task | Shaft E - Grout Block (at lunching area) | 10/04/2019 | 11/05/2019 | 12/02/2019 | 16/03/2019 | 0 | TK_Complete
SFE10029a | TT_FinMile | Shaft E /Grout Block - Complete grout at pre-determined core locations | 29/04/2019 | 29/04/2019 | 27/02/2019 | 27/02/2019 | 0 | TK_Complete
SFE10029b | TT_Task | Shaft E /Grout Block - Core sample | 17/05/2019 | 06/06/2019 | 27/02/2019 | 15/03/2019 | 0 | TK_Complete
SFE10029c | TT_Task | Shaf E /Grout Block - Test to early achievement of 28 day strength | 29/04/2019 | 01/05/2019 | 12/03/2019 | 29/03/2019 | 0 | TK_Complete
SFE10029d | TT_Task | Shaft E/ Grout Block - Jet grout assessment report (AF TBC) | 04/05/2019 | 10/05/2019 | 30/03/2019 | 23/04/2019 | 0 | TK_Complete
SFE10029e | TT_Task | Shaft E - BA8 consent for pile wall opening | 04/05/2019 | 31/05/2019 | 18/04/2019 | 12/06/2019 | 0 | TK_Complete
SFE10030 | TT_Task | Shaft E - 610 Dia. Pipe Pile Wall @ 750 c/c (52 nos) | 03/07/2018 | 12/09/2018 | 04/06/2018 | 16/11/2018 | 0 | TK_Complete
SFE10032 | TT_Task | Shaft E - BD Consent for Excavation &amp; ELS above +4.7 mPD | 26/12/2018 | 22/01/2019 | 18/12/2018 | 25/02/2019 | 0 | TK_Complete
SFE10035 | TT_Task | Shaft E - Grout Curtain (behind pipe pile wall) (total drilling 1490m) | 26/11/2018 | 17/12/2018 | 20/11/2018 | 10/12/2018 | 0 | TK_Complete
SFE10045 | TT_Task | Shaft E - Pumping Test and Report Submission | 26/12/2018 | 15/01/2019 | 15/12/2018 | 28/01/2019 | 0 | TK_Complete
SFE10046 | TT_Task | Shaft E - BD Consent for Excavation &amp; ELS from +4.7 to -1.6 mPD | 02/04/2019 | 29/04/2019 | 29/01/2019 | 25/02/2019 | 0 | TK_Complete
SFE10050 | TT_Task | Shaft E - Excavate to 0.5m below 1st layer of struts / Install lagging plate | 13/02/2019 | 19/02/2019 | 15/01/2019 | 19/01/2019 | 0 | TK_Complete
SFE10060 | TT_Task | Shaft E - Install 1st layer of struts (22 t) | 20/02/2019 | 23/02/2019 | 20/01/2019 | 23/01/2019 | 0 | TK_Complete
SFE10070 | TT_Task | Shaft E - Excavate to below 2nd layer of strut | 01/04/2019 | 05/04/2019 | 01/03/2019 | 05/03/2019 | 0 | TK_Complete
SFE10080 | TT_Task | Shaft E - Intstall lagging plates and 2nd layer of strut | 02/04/2019 | 06/04/2019 | 02/03/2019 | 08/03/2019 | 0 | TK_Complete
SFE10090 | TT_Task | Shaft E - Excavate to below 3rd layer of strut | 01/04/2019 | 05/04/2019 | 09/03/2019 | 10/03/2019 | 0 | TK_Complete
SFE10100 | TT_Task | Shaft E - Intstall lagging plates and 3rd layer of strut | 02/04/2019 | 06/04/2019 | 11/03/2019 | 15/03/2019 | 0 | TK_Complete
SFE10110 | TT_Task | Shaft E - Excavate to below 4th layer of strut | 01/04/2019 | 05/04/2019 | 16/03/2019 | 17/03/2019 | 0 | TK_Complete
SFE10120 | TT_Task | Shaft E - Intstall lagging plates and 4th layer of strut | 02/04/2019 | 06/04/2019 | 17/03/2019 | 26/03/2019 | 0 | TK_Complete
SFE10130 | TT_Task | Shaft E - Excavate to below 5th layer of strut | 01/04/2019 | 05/04/2019 | 27/03/2019 | 28/03/2019 | 0 | TK_Complete
SFE10140 | TT_Task | Shaft E - Intstall lagging plates and 5th layer of strut | 01/04/2019 | 05/04/2019 | 28/03/2019 | 02/04/2019 | 0 | TK_Complete
SFE10150 | TT_Task | Shaft E - Excavate to below 6th layer of strut | 01/05/2019 | 06/05/2019 | 03/04/2019 | 05/04/2019 | 0 | TK_Complete
SFE10160 | TT_Task | Shaft E - Intstall lagging plates and 6th layer of strut | 02/05/2019 | 07/05/2019 | 06/04/2019 | 09/04/2019 | 0 | TK_Complete
SFE10170 | TT_Task | Shaft E - Excavate to below 7th layer of strut | 08/05/2019 | 13/05/2019 | 11/04/2019 | 13/04/2019 | 0 | TK_Complete
SFE10180 | TT_Task | Shaft E - Intstall lagging plates and 7th layer of strut | 01/05/2019 | 06/05/2019 | 14/04/2019 | 24/04/2019 | 0 | TK_Complete
SFE10190 | TT_Task | Shaft E - Excavate to below 8th layer of strut | 01/05/2019 | 06/05/2019 | 25/04/2019 | 01/05/2019 | 0 | TK_Complete
SFE10200 | TT_Task | Shaft E - Intstall lagging plates and 8th layer of strut | 03/06/2019 | 06/06/2019 | 02/05/2019 | 05/05/2019 | 0 | TK_Complete
SFE10250 | TT_Task | Shaft E - Excavate to final excavation level -18 mPD /install lagging plate/ S9 at FEL | 01/06/2019 | 12/06/2019 | 06/05/2019 | 22/05/2019 | 0 | TK_Complete
SFE10260 | TT_Task | Shaft E - Cast base slab /skin wall | 03/06/2019 | 12/06/2019 | 19/05/2019 | 11/06/2019 | 0 | TK_Complete
SFE10270 | TT_Task | Shaft E - Cast-in bottom layers of struts with base slab | 01/06/2019 | 01/06/2019 | 22/05/2019 | 22/05/2019 | 0 | TK_Complete
SFE10275 | TT_Task | Shaft E - Break through the pipe pile wall for launching TBM | 05/08/2019 | 15/08/2019 | 12/06/2019 | 27/06/2019 | 0 | TK_Complete
SFE10277 | TT_Task | Shaft E - Set up and launch TBM to Shaft F | 01/08/2019 | 25/08/2019 | 12/06/2019 | 16/08/2019 | 0 | TK_Complete
SFE10278 | TT_Task | Shaft E - Micro tunneling and pipe jacking to Shaft F (Part 1 of 2) | 18/09/2019 | 02/10/2019 | 17/08/2019 | 18/09/2019 | 0 | TK_Complete
SFE10280 | TT_Task | Shaft E - Remove jacking frame, thrust block and etc | 01/01/2020 | 01/01/2020 | 30/10/2019 | 12/11/2019 | 0 | TK_Complete
SFE30045 | TT_Task | Shaft E - Install CW pipe to 0.5m above 7th layer of strut and mass fill | 01/01/2020 | 02/01/2020 | 13/11/2019 | 16/11/2019 | 0 | TK_Complete
SFE30065 | TT_Task | Shaft E - Install CW pipe to 0.5m above 6th layer of strut and mass fill | 03/01/2020 | 04/01/2020 | 18/11/2019 | 20/11/2019 | 0 | TK_Complete
SFE30085 | TT_Task | Shaft E - Install CW pipe to 0.5m above 5th layer of strut and mass fill | 01/01/2020 | 02/01/2020 | 21/11/2019 | 22/11/2019 | 0 | TK_Complete
SFE30105 | TT_Task | Shaft E - Install CW pipe to 0.5m above 4th layer of strut and mass fill | 03/01/2020 | 04/01/2020 | 23/11/2019 | 23/11/2019 | 0 | TK_Complete
SFE30115 | TT_Task | Shaft E - Install CW pipe to 0.5m above 3rd layer of strut and mass fill | 05/01/2020 | 06/01/2020 | 24/11/2019 | 26/11/2019 | 0 | TK_Complete
SFE30125 | TT_Task | Shaft E - Install CW pipe to 0.5m above 2nd layer of strut and mass fill | 07/01/2020 | 08/01/2020 | 27/11/2019 | 28/11/2019 | 0 | TK_Complete
SFE30127XX | TT_Task | Testing to CWP between Shaft E and Shaft F (Part 1 of 2) | 01/01/2020 | 07/01/2020 | 29/11/2019 | 29/11/2019 | 0 | TK_Complete
SFE30128 | TT_Task | Shaft E - Connect CW pipe to Discharge Culvert | 12/01/2020 | 13/01/2020 | 10/12/2019 | 18/12/2019 | 0 | TK_Complete
SFE30165 | TT_Task | Shaft E - Trim pipe piles | 01/01/2020 | 04/01/2020 | 01/01/2020 | 04/01/2020 | 0 | TK_Complete
SFE30170 | TT_Task | Shaft E - Backfill and reinstate to ground level | 05/01/2020 | 10/01/2020 | 05/01/2020 | 10/01/2020 | 0 | TK_Complete
SFE30180 | TT_FinMile | Shaft E - All stages of TTM ended; traffic resumed to normal at Shaft E location | 10/01/2020 | 10/01/2020 | 10/01/2020 | 10/01/2020 | 0 | TK_Complete
DBC00010 | TT_Task | Discharge Culvert - Utilities Diversion along Sea Bank Road | 04/05/2018 | 25/06/2018 | 25/04/2018 | 20/06/2018 | 0 | TK_Complete
DBC10010 | TT_Task | Discharge Culvert /Zone A (Eastern Section) - Pipe Pile (PPS080-240, PPS330-490 excl' 1800 culvert) | 05/12/2018 | 17/01/2019 | 28/08/2018 | 12/11/2018 | 0 | TK_Complete
DBC10020 | TT_Task | Discharge Culvert /Zone A (Eastern Section) - Grout curtain behind pile wall - excl' 1800 drainage area | 26/11/2018 | 08/01/2019 | 19/09/2018 | 12/01/2019 | 0 | TK_Complete
DBC10030 | TT_Task | Discharge Culvert /Zone A (Eastern Section) - all remaining works held up by the issue of 1800 culvert | 31/03/2019 | 28/06/2019 | 26/01/2019 | 10/07/2019 | 0 | TK_Complete
DBC10040 | TT_Task | Discharge Culvert /Zone A1 (Eastern Section) - Pumping Test &amp; Assessment Report to BD | 01/05/2019 | 21/05/2019 | 01/04/2019 | 22/05/2019 | 0 | TK_Complete
DBC10045 | TT_Task | Discharge Culvert /Zone A1 (Eastern Section) - BD Consent for Commencement of Excavation &amp; ELS | 09/06/2019 | 06/07/2019 | 16/05/2019 | 12/06/2019 | 0 | TK_Complete
DBC10050 | TT_Task | Discharge Culvert /Zone A1 (Eastern Section) - Excavate to 0.5m below 1st layer of struts | 01/08/2019 | 03/08/2019 | 26/05/2019 | 28/05/2019 | 0 | TK_Complete
DBC10060 | TT_Task | Discharge Culvert /Zone A1 (Eastern Section) - Install 1st layer of struts | 05/08/2019 | 09/08/2019 | 29/05/2019 | 01/06/2019 | 0 | TK_Complete
DBC10070 | TT_Task | Discharge Culvert /Zone A1 (Eastern Section) - Excavate below 1st layer of struts to FEL | 01/08/2019 | 10/08/2019 | 14/06/2019 | 24/06/2019 | 0 | TK_Complete
DBC10080 | TT_Task | Discharge Culvert /Zone A1 (Eastern Section) - Lagging plate below 1st layer of struts to FEL | 01/08/2019 | 05/08/2019 | 25/06/2019 | 04/07/2019 | 0 | TK_Complete
DBC10090 | TT_Task | Discharge Culvert /Zone A1 (Eastern Section) - Blinding concrete | 01/08/2019 | 06/08/2019 | 05/07/2019 | 09/07/2019 | 0 | TK_Complete
DBC10100 | TT_Task | Discharge Culvert /Zone A1 (Eastern Section) - Cast base slab and kicker | 01/08/2019 | 22/08/2019 | 10/07/2019 | 17/07/2019 | 0 | TK_Complete
DBC10110 | TT_Task | Discharge Culvert /Zone A1 (Eastern Section) - Construct manholes | 02/01/2020 | 22/01/2020 | 26/08/2019 | 14/11/2019 | 0 | TK_Complete
DBC10115 | TT_Task | Discharge Culvert /Zone A1 (Eastern Section) - Install drainage pipes | 23/01/2020 | 05/02/2020 | 26/08/2019 | 14/11/2019 | 0 | TK_Complete
DBC10120 | TT_Task | Discharge Culvert /Zone A1 (Eastern Section) - Cast side walls and top slab | 12/08/2019 | 02/09/2019 | 17/07/2019 | 06/08/2019 | 0 | TK_Complete
DBC10125 | TT_Task | Discharge Culvert /Zone A1 (Eastern Section) - Backfill to 0.5m below 1st layer of struts | 02/01/2020 | 04/01/2020 | 07/08/2019 | 10/08/2019 | 0 | TK_Complete
DBC10140 | TT_Task | Discharge Culvert /Zone A1 (Eastern Section) - Remove 1st layer of struts | 06/01/2020 | 06/01/2020 | 12/08/2019 | 12/08/2019 | 0 | TK_Complete
DBC10150 | TT_Task | Discharge Culvert /Zone A1 (Eastern Section) - Trim pipe piles | 07/01/2020 | 13/01/2020 | 13/08/2019 | 20/08/2019 | 0 | TK_Complete
DBC10160 | TT_Task | Discharge Culvert /Zone A1 (Eastern Section) - Backfill and reinstate to ground level | 14/01/2020 | 20/01/2020 | 18/11/2019 | 23/11/2019 | 0 | TK_Complete
DBC20010 | TT_Task | Discharge Culvert /Zone B(&amp;A3) (Western Section) - Pipe Pile (PPS001-079, PPS491-570) - excl' 1800 drainage area | 18/01/2019 | 06/03/2019 | 22/10/2018 | 29/11/2018 | 0 | TK_Complete
DBC20020 | TT_Task | Discharge Culvert / Grout Curtain (as a temporary cut off from Zone A2) | 07/05/2019 | 17/05/2019 | 06/03/2019 | 19/03/2019 | 0 | TK_Complete
DBC20030 | TT_Task | Discharge Culvert /Zone B(&amp;A3) (Western Section) - Grout curtain behind pipe pile wall | 26/01/2019 | 04/03/2019 | 21/11/2018 | 10/01/2019 | 0 | TK_Complete
DBC20040 | TT_Task | Discharge Culvert /Zone A3 (Western Section) - Pumping Test &amp; Assessment Report to BD | 01/06/2019 | 21/06/2019 | 27/05/2019 | 12/06/2019 | 0 | TK_Complete
DBC20045 | TT_Task | Discharge Culvert /Zone A3 (Western Section) - BD Consent for Commencement of Excavation &amp; ELS | 01/08/2019 | 28/08/2019 | 06/06/2019 | 03/07/2019 | 0 | TK_Complete
DBC20050 | TT_Task | Discharge Culvert /Zone A3 (Western Section) - Excavate to 0.5m below 1st layer of struts | 01/08/2019 | 03/08/2019 | 18/07/2019 | 20/07/2019 | 0 | TK_Complete
DBC20055 | TT_Task | Discharge Culvert /Zone B (Shaft E Interface Section) - Pumping Test &amp; Assessment Report to BD | 01/08/2019 | 21/08/2019 | 11/06/2019 | 26/06/2019 | 0 | TK_Complete
DBC20060 | TT_Task | Discharge Culvert /Zone A3 (Western Section) - Install 1st layer of struts | 01/08/2019 | 05/08/2019 | 22/07/2019 | 26/07/2019 | 0 | TK_Complete
DBC20065 | TT_Task | Discharge Culvert /Zone B (Shaft E Interface Section) - BD Consent for Commencement of Excavation &amp; ELS | 01/01/2020 | 28/01/2020 | 15/11/2019 | 12/12/2019 | 0 | TK_Complete
DBC20070 | TT_Task | Discharge Culvert /Zone A3 (Western Section) - Excavate below 1st layer of struts to FEL | 01/08/2019 | 10/08/2019 | 27/07/2019 | 06/08/2019 | 0 | TK_Complete
DBC20080 | TT_Task | Discharge Culvert /Zone A3 (Western Section) - Lagging plate below 1st layer of struts to FEL | 09/09/2019 | 13/09/2019 | 08/08/2019 | 12/08/2019 | 0 | TK_Complete
DBC20090 | TT_Task | Discharge Culvert /Zone A3 (Western Section) - Blinding concrete | 02/01/2020 | 07/01/2020 | 12/11/2019 | 12/11/2019 | 0 | TK_Complete
DBC20100 | TT_Task | Discharge Culvert /Zone A3 (Western Section) - Cast base slab and kicker | 08/01/2020 | 16/01/2020 | 13/11/2019 | 20/11/2019 | 0 | TK_Complete
DBC20110 | TT_Task | Discharge Culvert /Zone A3 (Western Section) - Construct manholes | 02/01/2020 | 22/01/2020 | 16/12/2019 | 24/01/2020 | 0 | TK_Complete
DBC20115 | TT_Task | Discharge Culvert /Zone A3 (Western Section) - Install drainage pipes | 16/01/2020 | 22/01/2020 | 16/12/2019 | 24/01/2020 | 0 | TK_Complete
DBC20120 | TT_Task | Discharge Culvert /Zone A3 (Western Section) - Cast side walls and top slab | 17/01/2020 | 01/02/2020 | 21/11/2019 | 15/12/2019 | 0 | TK_Complete
DBC20125 | TT_Task | Discharge Culvert /Zone A3 (Western Section) - Backfill to 0.5m below 1st layer of struts | 02/01/2020 | 04/01/2020 | 16/12/2019 | 18/12/2019 | 0 | TK_Complete
DBC20140 | TT_Task | Discharge Culvert /Zone A3 (Western Section) - Remove 1st layer of struts | 06/01/2020 | 06/01/2020 | 19/12/2019 | 19/12/2019 | 0 | TK_Complete
DBC20150 | TT_Task | Discharge Culvert /Zone A3 (Western Section) - Trim pipe piles | 07/01/2020 | 13/01/2020 | 20/12/2019 | 28/12/2019 | 0 | TK_Complete
DBC20160 | TT_Task | Discharge Culvert /Zone A3 (Western Section) - Backfill and reinstate to ground level | 01/02/2020 | 07/02/2020 | 01/02/2020 | 07/02/2020 | 0 | TK_Complete
DBC30005 | TT_Task | Discharge Culvert /Zone B (Shaft E Interface Section) - 1st layer excavation and ELS | 01/01/2020 | 07/01/2020 | 18/11/2019 | 21/11/2019 | 0 | TK_Complete
DBC30010 | TT_Task | Discharge Culvert /Zone B (Shaft E Interface Section) - Excavation below 1st layer of strut to FEL | 08/01/2020 | 11/01/2020 | 22/11/2019 | 26/11/2019 | 0 | TK_Complete
DBC30020 | TT_Task | Discharge Culvert /Shaft E Interface - Install CW pipe between Shaft E and Discharge Culvert | 03/01/2020 | 11/01/2020 | 06/12/2019 | 15/12/2019 | 0 | TK_Complete
DBC30030 | TT_Task | Discharge Culvert /Zone B (Shaft E Interface Section) - Remaining drainage works and backfill | 01/01/2020 | 30/01/2020 | 19/12/2019 | 24/01/2020 | 0 | TK_Complete
DBC30100 | TT_Task | Discharge Culvert /Zone B (Shaft E Interface Section) - RC works | 12/01/2020 | 26/01/2020 | 27/11/2019 | 15/12/2019 | 0 | TK_Complete
DBC30110 | TT_Task | Discharge Culvert /Zone B (Shaft E Interface Section) - Strip internal space | 12/01/2020 | 14/01/2020 | 17/12/2019 | 18/12/2019 | 0 | TK_Complete
DBC40010 | TT_Task | Discharge Culvert /Zone A2 (1800 Drainage Section) - Remaining drainage works and backfill | 01/01/2020 | 30/01/2020 | 26/11/2019 | 24/01/2020 | 0 | TK_Complete
EV017030 | TT_Task | Event 017S - Sea Bank Road (Zone A and Zone B excl' 1800 culvert) - Advanced Precautionary Grouting | 02/06/2018 | 31/07/2018 | 25/05/2018 | 30/08/2018 | 0 | TK_Complete
EV017040 | TT_Task | Event 017S - Sea Bank Road (Zone C) - Advanced Precautionary Grouting inside creast wall | 26/11/2018 | 30/11/2018 | 04/09/2018 | 08/09/2018 | 0 | TK_Complete
EV017050 | TT_Task | Event 017S - Sea Bank Road (Zone C) - Advanced Precautionary Grouting outside creast wall | 26/11/2018 | 30/11/2018 | 16/10/2018 | 20/10/2018 | 0 | TK_Complete
EV025900 | TT_Task | Event 025S - Preventive grouting stopped as it's being legalized via AAA amendment | 27/06/2018 | 02/08/2018 | 22/06/2018 | 29/07/2018 | 0 | TK_Complete
EV037000 | TT_Task | Event 037a - Discharge Culvert / Zone A &amp; B amendment (Type II) | 26/01/2019 | 24/02/2019 | 02/01/2019 | 31/01/2019 | 0 | TK_Complete
EV037005 | TT_Task | Event 037b - Discharge Culvert / 1800 drainage amendment (Type II) | 26/01/2019 | 24/02/2019 | 02/01/2019 | 31/01/2019 | 0 | TK_Complete
EV037008 | TT_Task | Event 037d - Discharge Culvert / 1800 drainage &amp; TBM alignment (Type II) | 31/03/2019 | 29/04/2019 | 26/03/2019 | 30/04/2019 | 0 | TK_Complete
EV044020 | TT_Task | Event 044 - Set up and conduct plate load test PL4 at SBR Zone A3 | 01/11/2019 | 06/11/2019 | 06/09/2019 | 09/09/2019 | 0 | TK_Complete
EV055010 | TT_Task | Event 055 - 1800 drainage pipe at SBR / Pumping test and assessment report to BD (Zone A2) | 01/08/2019 | 17/08/2019 | 17/07/2019 | 26/07/2019 | 0 | TK_Complete
EV055020 | TT_Task | Event 055 - 1800 drainage pipe at SBR / Excavation consent (Zone A2) | 11/08/2019 | 07/09/2019 | 31/07/2019 | 28/08/2019 | 0 | TK_Complete
EV055030 | TT_Task | Event 055 - 1800 drainage pipe at SBR / Excavation and construction of Discharge Culvert (Zone A2) | 01/11/2019 | 27/01/2020 | 07/09/2019 | 25/11/2019 | 0 | TK_Complete
EV062010 | TT_Task | Event 062 - Construct temporary mucking pit at SBR Zone A3 | 14/09/2019 | 18/09/2019 | 13/08/2019 | 17/08/2019 | 0 | TK_Complete
CNY_2018 | TT_Task | Outfall Apron Modif - Bulkhead Installation | 18/04/2018 | 21/04/2018 | 22/02/2018 | 25/02/2018 | 0 | TK_Complete
CNY_2019 | TT_Task | Outfall Apron Modif - Bulkhead Modification (fixing method) - during CNY shutdown | 31/03/2019 | 03/04/2019 | 08/02/2019 | 09/02/2019 | 0 | TK_Complete
EV036010 | TT_Task | Event 036 - Dicharge Culvert / Outfall portion amendment (Type II) | 26/11/2018 | 25/12/2018 | 12/09/2018 | 10/10/2018 | 0 | TK_Complete
EV056010 | TT_Task | Event 056 - Bulkhead Modification (fixing method) - pre CNY | 26/01/2019 | 26/01/2019 | 24/01/2019 | 30/01/2019 | 0 | TK_Complete
EV059010 | TT_Task | Event 059 - Discharge Culvert / Zone C /Plate Load Test | 30/05/2019 | 05/06/2019 | 02/03/2019 | 18/03/2019 | 0 | TK_Complete
OAM10010 | TT_Task | Outfall Apron Modif /behind the crest wall - Remove rock armour and crest wall | 27/08/2018 | 03/09/2018 | 08/10/2018 | 10/10/2018 | 0 | TK_Complete
OAM10020 | TT_Task | Outfall Apron Modif /behind the crest wall - Rock fill to +5.7mPD to form temporary working platform | 27/08/2018 | 30/08/2018 | 10/10/2018 | 12/10/2018 | 0 | TK_Complete
OAM10030 | TT_Task | Outfall Apron Modif /behind the crest wall - Pipe Piles (PPS271-280) | 26/11/2018 | 28/11/2018 | 22/10/2018 | 24/10/2018 | 0 | TK_Complete
OAM10040 | TT_Task | Outfall Apron Modif /on Sea Bank Road - Pile Piles (PPS241-270, PPS281-329) | 29/11/2018 | 04/12/2018 | 17/09/2018 | 03/10/2018 | 0 | TK_Complete
OAM10050 | TT_Task | Outfall Apron Modif /behind the crest wall - Grout Curtain | 26/11/2018 | 04/12/2018 | 27/10/2018 | 05/11/2018 | 0 | TK_Complete
OAM10060 | TT_Task | Outfall Apron Modif /on Sea Bank Road - Grout Curtain | 05/12/2018 | 12/12/2018 | 04/10/2018 | 05/11/2018 | 0 | TK_Complete
OAM10070 | TT_Task | Outfall Apron Modif - Grout Curtain (as temporary cut off from Zone B and behind Outfall side wall) | 26/11/2018 | 03/12/2018 | 25/10/2018 | 01/11/2018 | 0 | TK_Complete
OAM10080 | TT_Task | Outfall Apron Modif - Pumping Test and assessment report to BD | 26/11/2018 | 13/12/2018 | 08/11/2018 | 21/12/2018 | 0 | TK_Complete
OAM10085 | TT_Task | Outfall Apron Modif - BD Consent for Commencement of Excavation &amp; ELS | 27/01/2019 | 23/02/2019 | 21/12/2018 | 01/02/2019 | 0 | TK_Complete
OAM10090 | TT_Task | Outfall Apron Modif - Excavate to 0.5m below the shoring layer | 26/01/2019 | 28/01/2019 | 04/01/2019 | 12/01/2019 | 0 | TK_Complete
OAM10100 | TT_Task | Outfall Apron Modif - Install the shoring | 29/01/2019 | 31/01/2019 | 14/01/2019 | 22/01/2019 | 0 | TK_Complete
OAM10110 | TT_Task | Outfall Apron Modif - Excavate to final excavation level +1.5 mPD (Zone C) | 01/04/2019 | 02/04/2019 | 14/02/2019 | 01/03/2019 | 0 | TK_Complete
OAM10115 | TT_Task | Outfall Apron Modif - Construct the box culvert section in Zone C | 01/06/2019 | 29/06/2019 | 08/05/2019 | 12/08/2019 | 0 | TK_Complete
OAM10120 | TT_Task | Outfall Apron Modif - Construct the box culvert to 0.5 m below the shoring | 01/11/2019 | 14/11/2019 | 24/08/2019 | 02/09/2019 | 0 | TK_Complete
OAM10130 | TT_Task | Outfall Apron Modif - Form the designed opening on apron wing wall (after stop logs installed) | 01/11/2019 | 04/11/2019 | 06/09/2019 | 24/09/2019 | 0 | TK_Complete
OAM10140 | TT_Task | Outfall Apron Modif - Backfill to 0.5m below the shoring | 02/01/2020 | 03/01/2020 | 31/10/2019 | 01/11/2019 | 0 | TK_Complete
OAM10150 | TT_Task | Outfall Apron Modif - Remove the shoring | 04/01/2020 | 04/01/2020 | 02/11/2019 | 04/11/2019 | 0 | TK_Complete
OAM10160 | TT_Task | Outfall Apron Modif - Construct the remaining box culvert structure | 05/11/2019 | 11/11/2019 | 25/09/2019 | 30/10/2019 | 0 | TK_Complete
OAM10170 | TT_Task | Outfall Apron Modif - Trim pipe pile | 13/01/2020 | 14/01/2020 | 02/11/2019 | 04/11/2019 | 0 | TK_Complete
OAM10180 | TT_Task | Outfall Apron Modif - Backfill and reinstate crest wall and rock armour | 15/01/2020 | 21/01/2020 | 05/11/2019 | 09/11/2019 | 0 | TK_Complete
THTT0010 | TT_Task | Turbine Table - Further excavate from +4.1 to +3.0 | 04/08/2017 | 22/08/2017 | 04/08/2017 | 28/08/2017 | 0 | TK_Complete
THTT0020 | TT_Task | Turbine Table - Cast blinding concrete | 27/11/2017 | 28/11/2017 | 23/10/2017 | 24/10/2017 | 0 | TK_Complete
THTT1010 | TT_Task | Turbine Table TT1 - Trim pile and prepare pile head | 25/09/2017 | 29/09/2017 | 25/09/2017 | 29/09/2017 | 0 | TK_Complete
THTT1020 | TT_Task | Turbine Table TT1 - Capping plate and rebar starter | 30/09/2017 | 07/10/2017 | 30/09/2017 | 07/10/2017 | 0 | TK_Complete
THTT1030 | TT_Task | Turbine Table TT1 Bottom Half - Erect side formwork (if any) | 26/10/2017 | 27/10/2017 | 26/10/2017 | 27/10/2017 | 0 | TK_Complete
THTT1040 | TT_Task | Turbine Table TT1 Bottom Half - Fix rebar | 30/10/2017 | 01/11/2017 | 30/10/2017 | 01/11/2017 | 0 | TK_Complete
THTT1050 | TT_Task | Turbine Table TT1 Bottom Half - Close formwork (if any) | 02/11/2017 | 02/11/2017 | 02/11/2017 | 02/11/2017 | 0 | TK_Complete
THTT1060 | TT_Task | Turbine Table TT1 Bottom Half - Pour concrete (mono pour) | 02/12/2017 | 02/12/2017 | 02/12/2017 | 02/12/2017 | 0 | TK_Complete
THTT1090 | TT_Task | Turbine Table TT1 - Install cast-in / embed items | 03/11/2017 | 06/11/2017 | 03/11/2017 | 06/11/2017 | 0 | TK_Complete
THTT1100 | TT_Task | Turbine Table TT1 Upper Half - Fix rebar | 04/11/2017 | 07/11/2017 | 04/11/2017 | 07/11/2017 | 0 | TK_Complete
THTT1110 | TT_Task | Turbine Table TT1 Upper Half - Close formwork (if any) | 08/11/2017 | 08/11/2017 | 08/11/2017 | 08/11/2017 | 0 | TK_Complete
THTT1120 | TT_Task | Turbine Table TT1 Upper Half - Pour concrete (mono pour) | 02/12/2017 | 02/12/2017 | 02/12/2017 | 02/12/2017 | 0 | TK_Complete
THTT1200 | TT_Task | Turbine Table TT1 - Construct Plinth PL1, PL2 with cast-in / embed items | 29/12/2017 | 19/01/2018 | 20/12/2017 | 25/01/2018 | 0 | TK_Complete
THTT2010 | TT_Task | Turbine Table TT2 - Trim pile and prepare pile head | 30/09/2017 | 07/10/2017 | 30/09/2017 | 07/10/2017 | 0 | TK_Complete
THTT2020 | TT_Task | Turbine Table TT2 - Capping plate and rebar starter | 09/10/2017 | 13/10/2017 | 09/10/2017 | 13/10/2017 | 0 | TK_Complete
THTT2030 | TT_Task | Turbine Table TT2 Bottom Half - Erect side formwork (if any) | 03/11/2017 | 04/11/2017 | 03/11/2017 | 04/11/2017 | 0 | TK_Complete
THTT2040 | TT_Task | Turbine Table TT2 Bottom Half - Fix rebar | 06/11/2017 | 08/11/2017 | 06/11/2017 | 08/11/2017 | 0 | TK_Complete
THTT2050 | TT_Task | Turbine Table TT2 Bottom Half - Close formwork (if any) | 09/11/2017 | 09/11/2017 | 09/11/2017 | 09/11/2017 | 0 | TK_Complete
THTT2060 | TT_Task | Turbine Table TT2 Bottom Half - Pour concrete (mono pour) | 02/12/2017 | 02/12/2017 | 02/12/2017 | 02/12/2017 | 0 | TK_Complete
THTT2090 | TT_Task | Turbine Table TT2 - Install cast-in / embed items | 10/11/2017 | 13/11/2017 | 10/11/2017 | 13/11/2017 | 0 | TK_Complete
THTT2100 | TT_Task | Turbine Table TT2 Upper Half - Fix rebar | 11/11/2017 | 14/11/2017 | 11/11/2017 | 14/11/2017 | 0 | TK_Complete
THTT2110 | TT_Task | Turbine Table TT2 Upper Half - Close formwork (if any) | 15/11/2017 | 15/11/2017 | 15/11/2017 | 15/11/2017 | 0 | TK_Complete
THTT2120 | TT_Task | Turbine Table TT2 Upper Half - Pour concrete (mono pour) | 02/12/2017 | 02/12/2017 | 02/12/2017 | 02/12/2017 | 0 | TK_Complete
THTT2200 | TT_Task | Turbine Table TT2 - Construct Plinth PL3 with cast-in / embed items | 28/02/2018 | 15/03/2018 | 29/12/2017 | 29/01/2018 | 0 | TK_Complete
THTT3010 | TT_Task | Turbine Table TT3 - Trim pile and prepare pile head | 09/10/2017 | 13/10/2017 | 09/10/2017 | 13/10/2017 | 0 | TK_Complete
THTT3020 | TT_Task | Turbine Table TT3 - Capping plate and rebar starter | 14/10/2017 | 19/10/2017 | 14/10/2017 | 19/10/2017 | 0 | TK_Complete
THTT3030 | TT_Task | Turbine Table TT3 Bottom Half - Erect side formwork (if any) | 10/11/2017 | 11/11/2017 | 10/11/2017 | 11/11/2017 | 0 | TK_Complete
THTT3040 | TT_Task | Turbine Table TT3 Bottom Half - Fix rebar | 13/11/2017 | 15/11/2017 | 13/11/2017 | 15/11/2017 | 0 | TK_Complete
THTT3050 | TT_Task | Turbine Table TT3 Bottom Half - Close formwork (if any) | 16/11/2017 | 16/11/2017 | 16/11/2017 | 16/11/2017 | 0 | TK_Complete
THTT3060 | TT_Task | Turbine Table TT3 Bottom Half - Pour concrete (mono pour) | 02/12/2017 | 02/12/2017 | 02/12/2017 | 02/12/2017 | 0 | TK_Complete
THTT3090 | TT_Task | Turbine Table TT3 - Install cast-in / embed items | 17/11/2017 | 20/11/2017 | 17/11/2017 | 20/11/2017 | 0 | TK_Complete
THTT3100 | TT_Task | Turbine Table TT3 Upper Half - Fix rebar | 18/11/2017 | 21/11/2017 | 18/11/2017 | 21/11/2017 | 0 | TK_Complete
THTT3110 | TT_Task | Turbine Table TT3 Upper Half - Close formwork (if any) | 22/11/2017 | 22/11/2017 | 22/11/2017 | 22/11/2017 | 0 | TK_Complete
THTT3120 | TT_Task | Turbine Table TT3 Upper Half - Pour concrete (mono pour) | 02/12/2017 | 02/12/2017 | 02/12/2017 | 02/12/2017 | 0 | TK_Complete
THTT3200 | TT_Task | Turbine Table TT3 - Construct Plinth PL4, 5, 6, 7, 8, 8a with cast-in / embed items | 28/02/2018 | 27/03/2018 | 29/12/2017 | 20/04/2018 | 0 | TK_Complete
THTT4010 | TT_Task | Turbine Table TT4 - Trim pile and prepare pile head | 14/10/2017 | 19/10/2017 | 14/10/2017 | 19/10/2017 | 0 | TK_Complete
THTT4020 | TT_Task | Turbine Table TT4 - Capping plate and rebar starter | 20/10/2017 | 24/10/2017 | 20/10/2017 | 23/10/2017 | 0 | TK_Complete
THTT4030 | TT_Task | Turbine Table TT4 - Erect side formwork (if any) | 24/11/2017 | 25/11/2017 | 24/11/2017 | 25/11/2017 | 0 | TK_Complete
THTT4040 | TT_Task | Turbine Table TT4 - Fix rebar and cast-in / embed items | 29/11/2017 | 01/12/2017 | 29/11/2017 | 01/12/2017 | 0 | TK_Complete
THTT4050 | TT_Task | Turbine Table TT4 - Close formwork (if any) | 01/12/2017 | 01/12/2017 | 01/12/2017 | 01/12/2017 | 0 | TK_Complete
THTT4060 | TT_Task | Turbine Table TT4 - Pour concrete (mono pour) | 02/12/2017 | 02/12/2017 | 02/12/2017 | 02/12/2017 | 0 | TK_Complete
THTT4200 | TT_Task | Turbine Table TT4 - Construct Plinth CEPL1, CEPL2 with cast-in / embed items | 16/03/2018 | 27/03/2018 | 16/01/2018 | 27/01/2018 | 0 | TK_Complete
THTT5010 | TT_Task | Turbine Table TT5 - Trim pile and prepare pile head | 20/10/2017 | 24/10/2017 | 20/10/2017 | 24/10/2017 | 0 | TK_Complete
THTT5020 | TT_Task | Turbine Table TT5 - Capping plate and rebar starter | 26/10/2017 | 31/10/2017 | 26/10/2017 | 31/10/2017 | 0 | TK_Complete
THTT5030 | TT_Task | Turbine Table TT5 Bottom Half - Erect side formwork (if any) | 17/11/2017 | 18/11/2017 | 17/11/2017 | 18/11/2017 | 0 | TK_Complete
THTT5040 | TT_Task | Turbine Table TT5 Bottom Half - Fix rebar | 20/11/2017 | 22/11/2017 | 20/11/2017 | 22/11/2017 | 0 | TK_Complete
THTT5050 | TT_Task | Turbine Table TT5 Bottom Half - Close formwork (if any) | 23/11/2017 | 23/11/2017 | 23/11/2017 | 23/11/2017 | 0 | TK_Complete
THTT5060 | TT_Task | Turbine Table TT5 Bottom Half - Pour concrete (mono pour) | 02/12/2017 | 02/12/2017 | 02/12/2017 | 02/12/2017 | 0 | TK_Complete
THTT5090 | TT_Task | Turbine Table TT5 - Install cast-in / embed items | 24/11/2017 | 27/11/2017 | 24/11/2017 | 29/11/2017 | 0 | TK_Complete
THTT5100 | TT_Task | Turbine Table TT5 Upper Half - Fix rebar | 25/11/2017 | 28/11/2017 | 25/11/2017 | 30/11/2017 | 0 | TK_Complete
THTT5110 | TT_Task | Turbine Table TT5 Upper Half - Close formwork (if any) | 29/11/2017 | 29/11/2017 | 29/11/2017 | 29/11/2017 | 0 | TK_Complete
THTT5120 | TT_Task | Turbine Table TT5 Upper Half - Pour concrete (mono pour) | 02/12/2017 | 02/12/2017 | 02/12/2017 | 02/12/2017 | 0 | TK_Complete
THTT5130 | TT_Task | Turbine Table TT5 - Construct Plinth PL9, 10, 11, 12, 13 with cast-in / embed items | 28/03/2018 | 17/04/2018 | 19/01/2018 | 10/02/2018 | 0 | TK_Complete
THGF0020 | TT_Task | Ground Slab TH1 - Blinding to the profile of pile caps and ground beams | 06/10/2017 | 09/10/2017 | 08/09/2017 | 04/12/2017 | 0 | TK_Complete
THGF0030 | TT_Task | Ground Slab TH1 - Trim pile and prepare pile head | 10/10/2017 | 14/10/2017 | 05/09/2017 | 06/10/2017 | 0 | TK_Complete
THGF0040 | TT_Task | Ground Slab TH1 - Capping plate and rebar starter | 25/09/2017 | 07/10/2017 | 14/09/2017 | 07/10/2017 | 0 | TK_Complete
THGF0050 | TT_Task | Ground Slab TH1 - Erect side formwork | 09/10/2017 | 10/10/2017 | 22/09/2017 | 13/02/2018 | 0 | TK_Complete
THGF0060 | TT_Task | Ground Slab TH1 - Fix rebar for pile caps and ground beams and install cast-in / embed items | 12/10/2017 | 16/10/2017 | 20/09/2017 | 13/02/2018 | 0 | TK_Complete
THGF0070 | TT_Task | Ground Slab TH1 - Pour caps and beams to the level of ground floor slab underside | 17/10/2017 | 17/10/2017 | 23/09/2017 | 14/02/2018 | 0 | TK_Complete
THGF0080 | TT_Task | Ground Slab TH1 - Prepare CJ | 15/03/2018 | 15/03/2018 | 08/02/2018 | 13/02/2018 | 0 | TK_Complete
THGF0090 | TT_Task | Ground Slab TH1 - Fix ground floor slab rebar | 16/03/2018 | 21/03/2018 | 08/02/2018 | 13/02/2018 | 0 | TK_Complete
THGF0100 | TT_Task | Ground Slab TH1 - Pour ground slab | 22/03/2018 | 22/03/2018 | 14/02/2018 | 14/02/2018 | 0 | TK_Complete
THGF0110 | TT_Task | Ground Slab TH1 - Strike formwork (if any) | 23/03/2018 | 23/03/2018 | 20/02/2018 | 21/02/2018 | 0 | TK_Complete
THGF1020 | TT_Task | Ground Slab TH2 - Blinding to the profile of pile caps and ground beams | 19/03/2018 | 21/03/2018 | 18/01/2018 | 20/01/2018 | 0 | TK_Complete
THGF1030 | TT_Task | Ground Slab TH2 - Trim pile and prepare pile head | 10/10/2017 | 14/10/2017 | 05/09/2017 | 15/01/2018 | 0 | TK_Complete
THGF1040 | TT_Task | Ground Slab TH2 - Capping plate and rebar starter | 14/03/2018 | 17/03/2018 | 13/01/2018 | 17/01/2018 | 0 | TK_Complete
THGF1050 | TT_Task | Ground Slab TH2 - Erect side formwork | 22/03/2018 | 23/03/2018 | 02/02/2018 | 03/03/2018 | 0 | TK_Complete
THGF1060 | TT_Task | Ground Slab TH2 - Fix rebar for pile caps and ground beams install cast-in / embed items | 02/03/2018 | 07/03/2018 | 02/02/2018 | 03/03/2018 | 0 | TK_Complete
THGF1070 | TT_Task | Ground Slab TH2 - Pour caps and beams to the level of ground floor slab underside | 03/05/2018 | 03/05/2018 | 05/03/2018 | 05/03/2018 | 0 | TK_Complete
THGF1080 | TT_Task | Ground Slab TH2 - Prepare CJ | 06/03/2018 | 07/03/2018 | 24/02/2018 | 03/03/2018 | 0 | TK_Complete
THGF1090 | TT_Task | Ground Slab TH2 - Fix ground floor slab rebar | 26/02/2018 | 08/03/2018 | 24/02/2018 | 03/03/2018 | 0 | TK_Complete
THGF1100 | TT_Task | Ground Slab TH2 - Pour ground slab | 03/05/2018 | 03/05/2018 | 05/03/2018 | 05/03/2018 | 0 | TK_Complete
THGF1110 | TT_Task | Ground Slab TH2 - Strike formwork (if any) | 04/05/2018 | 04/05/2018 | 06/03/2018 | 06/03/2018 | 0 | TK_Complete
THGF2020 | TT_Task | Ground Slab TH3 - Blinding to the profile of pile caps and ground beams | 16/10/2017 | 19/10/2017 | 08/09/2017 | 04/12/2017 | 0 | TK_Complete
THGF2030 | TT_Task | Ground Slab TH3 - Trim pile and prepare pile head | 20/10/2017 | 24/10/2017 | 05/09/2017 | 13/10/2017 | 0 | TK_Complete
THGF2040 | TT_Task | Ground Slab TH3 - Capping plate and rebar starter | 10/10/2017 | 14/10/2017 | 10/10/2017 | 14/10/2017 | 0 | TK_Complete
THGF2050 | TT_Task | Ground Slab TH3 - Erect side formwork | 27/12/2017 | 30/12/2017 | 05/12/2017 | 13/02/2018 | 0 | TK_Complete
THGF2060 | TT_Task | Ground Slab TH3 - Fix rebar for pile caps and ground beams install cast-in / embed items | 02/01/2018 | 08/01/2018 | 09/12/2017 | 13/02/2018 | 0 | TK_Complete
THGF2070 | TT_Task | Ground Slab TH3 - Pour caps and beams to the level of ground floor slab underside | 14/03/2018 | 14/03/2018 | 20/01/2018 | 14/02/2018 | 0 | TK_Complete
THGF2080 | TT_Task | Ground Slab TH3 - Prepare CJ | 15/03/2018 | 15/03/2018 | 08/02/2018 | 13/02/2018 | 0 | TK_Complete
THGF2090 | TT_Task | Ground Slab TH3 - Fix ground floor slab rebar | 16/03/2018 | 21/03/2018 | 08/02/2018 | 13/02/2018 | 0 | TK_Complete
THGF2100 | TT_Task | Ground Slab TH3 - Pour ground slab | 22/03/2018 | 22/03/2018 | 14/02/2018 | 14/02/2018 | 0 | TK_Complete
THGF2110 | TT_Task | Ground Slab TH3 - Strike formwork (if any) | 23/03/2018 | 23/03/2018 | 20/02/2018 | 21/02/2018 | 0 | TK_Complete
THGF3010 | TT_Task | Ground Slab TH4 - Backfill the interface area between Turbine Table to +4.2 mPD | 06/12/2018 | 08/12/2018 | 07/09/2018 | 09/09/2018 | 0 | TK_Complete
THGF3020 | TT_Task | Ground Slab TH4 - Blinding to the profile of pile caps and ground beams | 26/11/2018 | 28/11/2018 | 07/09/2018 | 09/09/2018 | 0 | TK_Complete
THGF3030 | TT_Task | Ground Slab TH4 - Trim pile and prepare pile head | 27/12/2017 | 30/12/2017 | 18/12/2017 | 21/12/2017 | 0 | TK_Complete
THGF3040 | TT_Task | Ground Slab TH4 - Capping plate and rebar starter | 28/12/2017 | 02/01/2018 | 19/12/2017 | 22/12/2017 | 0 | TK_Complete
THGF3050 | TT_Task | Ground Slab TH4 - Erect side formwork | 26/11/2018 | 27/11/2018 | 10/09/2018 | 29/09/2018 | 0 | TK_Complete
THGF3060 | TT_Task | Ground Slab TH4 - Fix rebar for pile caps and ground beams install cast-in / embed items | 26/11/2018 | 29/11/2018 | 10/09/2018 | 29/09/2018 | 0 | TK_Complete
THGF3070 | TT_Task | Ground Slab TH4 - Pour caps and beams to the level of ground floor slab underside | 05/12/2018 | 05/12/2018 | 30/09/2018 | 30/09/2018 | 0 | TK_Complete
THGF3080 | TT_Task | Ground Slab TH4 - Prepare CJ | 30/11/2018 | 30/11/2018 | 30/09/2018 | 30/09/2018 | 0 | TK_Complete
THGF3090 | TT_Task | Ground Slab TH4 - Fix ground floor slab rebar | 01/12/2018 | 04/12/2018 | 10/09/2018 | 29/09/2018 | 0 | TK_Complete
THGF3100 | TT_Task | Ground Slab TH4 - Pour ground slab | 05/12/2018 | 05/12/2018 | 30/09/2018 | 30/09/2018 | 0 | TK_Complete
THGF4020 | TT_Task | Ground Slab TH5 - Blinding to the profile of pile caps and ground beams | 09/10/2017 | 12/10/2017 | 08/09/2017 | 06/02/2018 | 0 | TK_Complete
THGF4030 | TT_Task | Ground Slab TH5 - Trim pile and prepare pile head | 13/10/2017 | 17/10/2017 | 05/09/2017 | 20/10/2017 | 0 | TK_Complete
THGF4040 | TT_Task | Ground Slab TH5 - Capping plate and rebar starter | 17/10/2017 | 21/10/2017 | 17/10/2017 | 21/10/2017 | 0 | TK_Complete
THGF4050 | TT_Task | Ground Slab TH5 - Erect side formwork | 06/03/2018 | 09/03/2018 | 07/02/2018 | 06/03/2018 | 0 | TK_Complete
THGF4060 | TT_Task | Ground Slab TH5 - Fix rebar for pile caps and ground beams install cast-in / embed items | 02/03/2018 | 09/03/2018 | 07/02/2018 | 06/03/2018 | 0 | TK_Complete
THGF4070 | TT_Task | Ground Slab TH5 - Pour caps and beams to the level of ground floor slab underside | 08/05/2018 | 08/05/2018 | 07/03/2018 | 07/03/2018 | 0 | TK_Complete
THGF4080 | TT_Task | Ground Slab TH5 - Prepare CJ | 23/04/2018 | 04/05/2018 | 26/02/2018 | 06/03/2018 | 0 | TK_Complete
THGF4090 | TT_Task | Ground Slab TH5 - Fix ground floor slab rebar | 24/04/2018 | 04/05/2018 | 27/02/2018 | 06/03/2018 | 0 | TK_Complete
THGF4100 | TT_Task | Ground Slab TH5 - Pour ground slab | 08/05/2018 | 08/05/2018 | 07/03/2018 | 07/03/2018 | 0 | TK_Complete
THGF4110 | TT_Task | Ground Slab TH5 - Strike formwork (if any) | 10/05/2018 | 10/05/2018 | 08/03/2018 | 08/03/2018 | 0 | TK_Complete
THGF5010 | TT_Task | Ground Slab TH6 - Backfill the interface area between Turbine Table to +4.2 mPD | 06/12/2018 | 08/12/2018 | 07/09/2018 | 09/09/2018 | 0 | TK_Complete
THGF5020 | TT_Task | Ground Slab TH6 - Blinding to the profile of pile caps and ground beams | 29/11/2018 | 01/12/2018 | 07/09/2018 | 09/09/2018 | 0 | TK_Complete
THGF5030 | TT_Task | Ground Slab TH6 - Trim pile and prepare pile head | 27/12/2017 | 30/12/2017 | 11/12/2017 | 14/12/2017 | 0 | TK_Complete
THGF5040 | TT_Task | Ground Slab TH6 - Capping plate and rebar starter | 28/12/2017 | 02/01/2018 | 12/12/2017 | 15/12/2017 | 0 | TK_Complete
THGF5050 | TT_Task | Ground Slab TH6 - Erect side formwork | 26/11/2018 | 27/11/2018 | 10/09/2018 | 29/09/2018 | 0 | TK_Complete
THGF5060 | TT_Task | Ground Slab TH6 - Fix rebar for pile caps and ground beams install cast-in / embed items | 26/11/2018 | 29/11/2018 | 10/09/2018 | 29/09/2018 | 0 | TK_Complete
THGF5070 | TT_Task | Ground Slab TH6 - Pour caps and beams to the level of ground floor slab underside | 05/12/2018 | 05/12/2018 | 30/09/2018 | 30/09/2018 | 0 | TK_Complete
THGF5080 | TT_Task | Ground Slab TH6 - Prepare CJ | 30/11/2018 | 30/11/2018 | 30/09/2018 | 30/09/2018 | 0 | TK_Complete
THGF5090 | TT_Task | Ground Slab TH6 - Fix ground floor slab rebar | 01/12/2018 | 04/12/2018 | 10/09/2018 | 30/09/2018 | 0 | TK_Complete
THGF5100 | TT_Task | Ground Slab TH6 - Pour ground slab | 05/12/2018 | 05/12/2018 | 30/09/2018 | 30/09/2018 | 0 | TK_Complete
THGF6020 | TT_Task | Ground Slab TH7 - Blinding to the profile of pile caps and ground beams | 02/03/2018 | 05/03/2018 | 22/02/2018 | 24/02/2018 | 0 | TK_Complete
THGF6030 | TT_Task | Ground Slab TH7 - Trim pile and prepare pile head | 21/10/2017 | 27/10/2017 | 21/10/2017 | 10/01/2018 | 0 | TK_Complete
THGF6040 | TT_Task | Ground Slab TH7 - Capping plate and rebar starter | 06/03/2018 | 09/03/2018 | 08/01/2018 | 21/02/2018 | 0 | TK_Complete
THGF6050 | TT_Task | Ground Slab TH7 - Erect side formwork | 06/03/2018 | 07/03/2018 | 07/02/2018 | 27/04/2018 | 0 | TK_Complete
THGF6060 | TT_Task | Ground Slab TH7 - Fix rebar for pile caps and ground beams install cast-in / embed items | 06/03/2018 | 09/03/2018 | 07/02/2018 | 27/04/2018 | 0 | TK_Complete
THGF6070 | TT_Task | Ground Slab TH7 - Pour caps and beams to the level of ground floor slab underside | 29/05/2018 | 29/05/2018 | 29/03/2018 | 28/04/2018 | 0 | TK_Complete
THGF6080 | TT_Task | Ground Slab TH7 - Prepare CJ | 23/04/2018 | 30/04/2018 | 17/04/2018 | 27/04/2018 | 0 | TK_Complete
THGF6090 | TT_Task | Ground Slab TH7 - Fix ground floor slab rebar | 23/04/2018 | 30/04/2018 | 17/04/2018 | 27/04/2018 | 0 | TK_Complete
THGF6100 | TT_Task | Ground Slab TH7 - Pour ground slab | 29/05/2018 | 29/05/2018 | 28/04/2018 | 28/04/2018 | 0 | TK_Complete
THGF6110 | TT_Task | Ground Slab TH7 - Strike formwork (if any) | 31/05/2018 | 31/05/2018 | 30/04/2018 | 30/04/2018 | 0 | TK_Complete
THGF7020 | TT_Task | Ground Slab TH8 - Blinding to the profile of pile caps and ground beams | 20/03/2018 | 22/03/2018 | 19/01/2018 | 22/01/2018 | 0 | TK_Complete
THGF7030 | TT_Task | Ground Slab TH8 - Trim pile and prepare pile head | 14/03/2018 | 17/03/2018 | 13/01/2018 | 17/01/2018 | 0 | TK_Complete
THGF7040 | TT_Task | Ground Slab TH8 - Capping plate and rebar starter | 15/03/2018 | 19/03/2018 | 15/01/2018 | 18/01/2018 | 0 | TK_Complete
THGF7050 | TT_Task | Ground Slab TH8 - Erect side formwork | 23/04/2018 | 12/05/2018 | 26/02/2018 | 23/03/2018 | 0 | TK_Complete
THGF7060 | TT_Task | Ground Slab TH8 - Fix rebar for pile caps and ground beams install cast-in / embed items | 23/04/2018 | 12/05/2018 | 26/02/2018 | 23/03/2018 | 0 | TK_Complete
THGF7070 | TT_Task | Ground Slab TH8 - Pour caps and beams to the level of ground floor slab underside | 14/05/2018 | 14/05/2018 | 24/03/2018 | 24/03/2018 | 0 | TK_Complete
THGF7080 | TT_Task | Ground Slab TH8 - Prepare CJ | 07/05/2018 | 12/05/2018 | 14/03/2018 | 23/03/2018 | 0 | TK_Complete
THGF7090 | TT_Task | Ground Slab TH8 - Fix ground floor slab rebar | 07/05/2018 | 12/05/2018 | 14/03/2018 | 23/03/2018 | 0 | TK_Complete
THGF7100 | TT_Task | Ground Slab TH8 - Pour ground slab | 14/05/2018 | 14/05/2018 | 24/03/2018 | 24/03/2018 | 0 | TK_Complete
THGF7110 | TT_Task | Ground Slab TH8 - Strike formwork (if any) | 15/05/2018 | 15/05/2018 | 25/03/2018 | 25/03/2018 | 0 | TK_Complete
THGF8020 | TT_Task | Ground Slab TH9 - Blinding to the profile of pile caps and ground beams | 20/03/2018 | 22/03/2018 | 19/01/2018 | 22/01/2018 | 0 | TK_Complete
THGF8030 | TT_Task | Ground Slab TH9 - Trim pile and prepare pile head | 14/03/2018 | 17/03/2018 | 13/01/2018 | 17/01/2018 | 0 | TK_Complete
THGF8040 | TT_Task | Ground Slab TH9 - Capping plate and rebar starter | 15/03/2018 | 19/03/2018 | 15/01/2018 | 18/01/2018 | 0 | TK_Complete
THGF8050 | TT_Task | Ground Slab TH9 - Erect side formwork | 23/04/2018 | 12/05/2018 | 26/02/2018 | 23/03/2018 | 0 | TK_Complete
THGF8060 | TT_Task | Ground Slab TH9 - Fix rebar for pile caps and ground beams install cast-in / embed items | 23/04/2018 | 12/05/2018 | 26/02/2018 | 23/03/2018 | 0 | TK_Complete
THGF8070 | TT_Task | Ground Slab TH9 - Pour caps and beams to the level of ground floor slab underside | 14/05/2018 | 14/05/2018 | 24/03/2018 | 24/03/2018 | 0 | TK_Complete
THGF8080 | TT_Task | Ground Slab TH9 - Prepare CJ | 07/05/2018 | 12/05/2018 | 14/03/2018 | 23/03/2018 | 0 | TK_Complete
THGF8090 | TT_Task | Ground Slab TH9 - Fix ground floor slab rebar | 07/05/2018 | 12/05/2018 | 14/03/2018 | 23/03/2018 | 0 | TK_Complete
THGF8100 | TT_Task | Ground Slab TH9 - Pour ground slab | 14/05/2018 | 14/05/2018 | 24/03/2018 | 24/03/2018 | 0 | TK_Complete
THGF8110 | TT_Task | Ground Slab TH9 - Strike formwork (if any) | 26/11/2018 | 26/11/2018 | 25/03/2018 | 25/03/2018 | 0 | TK_Complete
THGF9010 | TT_Task | Ground Slab TH10 - Backfill the interface area between Cond.Polishing Pit | 06/12/2018 | 08/12/2018 | 07/09/2018 | 09/09/2018 | 0 | TK_Complete
THGF9020 | TT_Task | Ground Slab TH10 - Blinding to the profile of pile caps and ground beams | 26/11/2018 | 28/11/2018 | 07/09/2018 | 09/09/2018 | 0 | TK_Complete
THGF9030 | TT_Task | Ground Slab TH10 - Trim pile and prepare pile head | 27/12/2017 | 30/12/2017 | 04/12/2017 | 07/12/2017 | 0 | TK_Complete
THGF9040 | TT_Task | Ground Slab TH10 - Capping plate and rebar starter | 28/12/2017 | 02/01/2018 | 05/12/2017 | 08/12/2017 | 0 | TK_Complete
THGF9050 | TT_Task | Ground Slab TH10 - Erect side formwork | 26/11/2018 | 27/11/2018 | 10/09/2018 | 29/09/2018 | 0 | TK_Complete
THGF9060 | TT_Task | Ground Slab TH10 - Fix rebar for pile caps and ground beams install cast-in / embed items | 26/11/2018 | 29/11/2018 | 10/09/2018 | 29/09/2018 | 0 | TK_Complete
THGF9070 | TT_Task | Ground Slab TH10 - Pour caps and beams to the level of ground floor slab underside | 05/12/2018 | 05/12/2018 | 30/09/2018 | 30/09/2018 | 0 | TK_Complete
THGF9080 | TT_Task | Ground Slab TH10 - Prepare CJ | 26/11/2018 | 26/11/2018 | 30/09/2018 | 30/09/2018 | 0 | TK_Complete
THGF9090 | TT_Task | Ground Slab TH10 - Fix ground floor slab rebar | 01/12/2018 | 04/12/2018 | 10/09/2018 | 29/09/2018 | 0 | TK_Complete
THGF9100 | TT_Task | Ground Slab TH10 - Pour ground slab | 05/12/2018 | 05/12/2018 | 30/09/2018 | 30/09/2018 | 0 | TK_Complete
THGF9110 | TT_Task | Ground Slab TH10 - Strike formwork (if any) | 27/11/2018 | 27/11/2018 | 02/10/2018 | 02/10/2018 | 0 | TK_Complete
THCP0010 | TT_Task | Condensate Pit - Further excavate from +4.1 mPD to the pit formation level | 26/02/2018 | 27/02/2018 | 15/01/2018 | 27/01/2018 | 0 | TK_Complete
THCP0015 | TT_Task | Condensate Pit - Sheet piling adjoining Turbine Table | 28/09/2017 | 24/10/2017 | 30/09/2017 | 21/10/2017 | 0 | TK_Complete
THCP0020 | TT_Task | Condensate Pit - Sheet piling for the sump pit | 27/12/2017 | 08/01/2018 | 21/12/2017 | 14/01/2018 | 0 | TK_Complete
THCP0030 | TT_Task | Condensate Pit - Excavation and construct the sump pit to the underside level of pit slab | 26/11/2018 | 04/12/2018 | 08/10/2018 | 09/11/2018 | 0 | TK_Complete
THCP0040 | TT_Task | Condensate Pit - Trim sheet pile head (pump pit) | 05/12/2018 | 06/12/2018 | 25/06/2018 | 05/07/2018 | 0 | TK_Complete
THCP0042 | TT_Task | Condensate Pit - Complete the slab around the sump pit (previosuly left out) | 07/12/2018 | 10/12/2018 | 12/11/2018 | 22/11/2018 | 0 | TK_Complete
THCP0050 | TT_Task | Condensate Pit - Trim pile and prepare pile head | 28/02/2018 | 01/03/2018 | 29/01/2018 | 16/06/2018 | 0 | TK_Complete
THCP0060 | TT_Task | Condensate Pit - Capping plate and rebar starter | 01/03/2018 | 03/03/2018 | 30/01/2018 | 19/06/2018 | 0 | TK_Complete
THCP0070 | TT_Task | Condensate Pit - Vertical blinding to the profile of pile caps, ground beams and shallow pits | 12/05/2018 | 15/05/2018 | 13/03/2018 | 14/07/2018 | 0 | TK_Complete
THCP0075 | TT_Task | Condensate Pit - Install waterproofing | 15/05/2018 | 15/05/2018 | 20/03/2018 | 27/07/2018 | 0 | TK_Complete
THCP0080 | TT_Task | Condensate Pit - Fix rebar for pile caps, ground beams and shallow pits | 18/05/2018 | 21/05/2018 | 21/03/2018 | 06/08/2018 | 0 | TK_Complete
THCP0090 | TT_Task | Condensate Pit - Close formwork | 24/05/2018 | 24/05/2018 | 16/04/2018 | 06/08/2018 | 0 | TK_Complete
THCP0100 | TT_Task | Condensate Pit - Pour caps, beams and shallow pits to the underside level of pit slab | 25/05/2018 | 25/05/2018 | 18/04/2018 | 07/08/2018 | 0 | TK_Complete
THCP0110 | TT_Task | Condensate Pit - Prepare CJ | 26/05/2018 | 26/05/2018 | 19/04/2018 | 10/08/2018 | 0 | TK_Complete
THCP0120 | TT_Task | Condensate Pit - Fix pit slab rebar | 28/05/2018 | 29/05/2018 | 21/03/2018 | 06/08/2018 | 0 | TK_Complete
THCP0130 | TT_Task | Condensate Pit - Pour pit slab and kicker | 31/05/2018 | 31/05/2018 | 18/04/2018 | 07/08/2018 | 0 | TK_Complete
THCP0140 | TT_Task | Condensate Pit - Erect wall formwork | 01/06/2018 | 02/06/2018 | 19/04/2018 | 31/08/2018 | 0 | TK_Complete
THCP0150 | TT_Task | Condensate Pit - Fix wall and column rebar | 04/06/2018 | 07/06/2018 | 19/04/2018 | 31/08/2018 | 0 | TK_Complete
THCP0160 | TT_Task | Condensate Pit - Close wall formwork | 07/06/2018 | 07/06/2018 | 22/04/2018 | 02/09/2018 | 0 | TK_Complete
THCP0170 | TT_Task | Condensate Pit - Pour walls and columns to the underside of Turbine Hall ground slab | 31/07/2018 | 31/07/2018 | 04/05/2018 | 03/09/2018 | 0 | TK_Complete
THCP0180 | TT_Task | Condensate Pit - Curing | 02/12/2018 | 04/12/2018 | 04/09/2018 | 06/09/2018 | 0 | TK_Complete
THCP0190 | TT_Task | Condensate Pit - Apply waterproofing to the external face of pit wall | 26/11/2018 | 27/11/2018 | 07/09/2018 | 07/09/2018 | 0 | TK_Complete
THCP0200 | TT_Task | Condensate Pit - Backfill againt basement wall | 26/11/2018 | 28/11/2018 | 07/09/2018 | 09/09/2018 | 0 | TK_Complete
THPP0010 | TT_Task | Cond.Polishing Pit - Further excavate from +4.1 mPD to the pit formation level | 26/02/2018 | 02/03/2018 | 15/01/2018 | 27/01/2018 | 0 | TK_Complete
THPP0050 | TT_Task | Cond.Polishing Pit - Trim pile and prepare pile head | 03/03/2018 | 05/03/2018 | 29/01/2018 | 21/05/2018 | 0 | TK_Complete
THPP0060 | TT_Task | Cond.Polishing Pit - Capping plate and rebar starter | 05/03/2018 | 07/03/2018 | 30/01/2018 | 22/05/2018 | 0 | TK_Complete
THPP0070 | TT_Task | Cond.Polishing Pit - Vertical blinding to the profile of pile caps, ground beams and shallow pits | 14/05/2018 | 17/05/2018 | 12/04/2018 | 31/05/2018 | 0 | TK_Complete
THPP0075 | TT_Task | Cond.Polishing Pit - Install waterproofing | 18/05/2018 | 18/05/2018 | 16/04/2018 | 26/07/2018 | 0 | TK_Complete
THPP0080 | TT_Task | Cond.Polishing Pit - Fix rebar for pile caps, ground beams and shallow pits | 01/06/2018 | 04/06/2018 | 03/05/2018 | 22/06/2018 | 0 | TK_Complete
THPP0090 | TT_Task | Cond.Polishing Pit - Close formwork | 04/06/2018 | 04/06/2018 | 23/05/2018 | 30/06/2018 | 0 | TK_Complete
THPP0100 | TT_Task | Cond.Polishing Pit - Pour caps, beams and shallow pits to the underside level of pit slab | 05/06/2018 | 05/06/2018 | 24/05/2018 | 01/07/2018 | 0 | TK_Complete
THPP0110 | TT_Task | Cond.Polishing Pit - Prepare CJ | 07/06/2018 | 07/06/2018 | 25/05/2018 | 04/07/2018 | 0 | TK_Complete
THPP0120 | TT_Task | Cond.Polishing Pit - Fix pit slab rebar | 05/07/2018 | 06/07/2018 | 22/05/2018 | 22/06/2018 | 0 | TK_Complete
THPP0130 | TT_Task | Cond.Polishing Pit - Pour pit slab | 30/06/2018 | 30/06/2018 | 24/05/2018 | 01/07/2018 | 0 | TK_Complete
THPP0140 | TT_Task | Cond.Polishing Pit - Erect wall formwork | 03/07/2018 | 07/07/2018 | 12/06/2018 | 18/07/2018 | 0 | TK_Complete
THPP0150 | TT_Task | Cond.Polishing Pit - Fix wall and column rebar | 26/06/2018 | 17/07/2018 | 09/06/2018 | 24/07/2018 | 0 | TK_Complete
THPP0160 | TT_Task | Cond.Polishing Pit - Close wall formwork | 30/06/2018 | 19/07/2018 | 12/06/2018 | 04/08/2018 | 0 | TK_Complete
THPP0170 | TT_Task | Cond.Polishing Pit - Pour walls and columns to the underside of Turbine Hall ground slab | 26/07/2018 | 10/08/2018 | 01/07/2018 | 07/08/2018 | 0 | TK_Complete
THPP0180 | TT_Task | Cond.Polishing Pit - Curing | 09/09/2018 | 11/09/2018 | 08/08/2018 | 10/08/2018 | 0 | TK_Complete
THPP0190 | TT_Task | Cond.Polishing Pit - Apply waterproofing to the external face of pit wall | 10/09/2018 | 11/09/2018 | 09/08/2018 | 10/08/2018 | 0 | TK_Complete
THPP0200 | TT_Task | Cond.Polishing Pit - Backfill againt basement wall | 26/11/2018 | 28/11/2018 | 07/09/2018 | 09/09/2018 | 0 | TK_Complete
THSS0010 | TT_Task | Turbine Hall GL1~5 - Erect steel columns SC1(SC2) (w/ Overhead Crane support columns) at GL.1-5 /H | 23/04/2018 | 10/05/2018 | 29/03/2018 | 13/04/2018 | 0 | TK_Complete
THSS0020 | TT_Task | Turbine Hall GL1~5 - Erect steel columns SC1 (w/ Overhead Crane support columns) at GL.1 /G2-C | 28/04/2018 | 07/05/2018 | 31/03/2018 | 07/04/2018 | 0 | TK_Complete
THSS0030 | TT_Task | Turbine Hall GL1~5 - Erect steel columns SC1 (w/ Overhead Crane support columns) at GL.5 /G | 08/05/2018 | 09/05/2018 | 09/04/2018 | 10/04/2018 | 0 | TK_Complete
THSS0040 | TT_Task | Turbine Hall GL1~5 - Erect steel columns SC1 (w/ Overhead Crane support columns) at GL.5 /F | 08/05/2018 | 09/05/2018 | 09/04/2018 | 10/04/2018 | 0 | TK_Complete
THSS0050 | TT_Task | Turbine Hall GL1~5 - Erect steel columns SC1 (w/ Overhead Crane support columns) at GL.5 /E | 26/05/2018 | 26/05/2018 | 03/05/2018 | 03/05/2018 | 0 | TK_Complete
THSS0060 | TT_Task | Turbine Hall GL1~5 - Erect steel columns SC1 (w/ Overhead Crane support columns) at GL.5 /D | 28/05/2018 | 28/05/2018 | 05/05/2018 | 05/05/2018 | 0 | TK_Complete
THSS0070 | TT_Task | Turbine Hall GL1~5 - Erect steel columns SC1 (w/ Overhead Crane support columns) at GL.5 /C | 29/05/2018 | 29/05/2018 | 07/05/2018 | 07/05/2018 | 0 | TK_Complete
THSS0080 | TT_Task | Turbine Hall GL1~5 - Erect steel columns SC1 (w/ Overhead Crane support columns) at GL.1 /B | 04/06/2018 | 04/06/2018 | 02/05/2018 | 02/05/2018 | 0 | TK_Complete
THSS0090 | TT_Task | Turbine Hall GL1~5 - Erect steel columns SC1(SC2)(w/ Overhead Crane support columns) at GL.1-4 /A | 05/06/2018 | 08/06/2018 | 03/05/2018 | 08/05/2018 | 0 | TK_Complete
THSS0100 | TT_Task | Turbine Hall GL1~5 - Erect steel columns SC1 (w/ Overhead Crane support columns) at GL.5 /A | 09/06/2018 | 13/06/2018 | 09/05/2018 | 12/05/2018 | 0 | TK_Complete
THSS0110 | TT_Task | Turbine Hall GL.1-5 /H-G2/G1 (Bay 1a) - Connect erected columns by beams and bracing to +37.26 | 11/05/2018 | 14/05/2018 | 14/04/2018 | 17/04/2018 | 0 | TK_Complete
THSS0120 | TT_Task | Turbine Hall GL.1-5 /G2/G1-G (Bay 2a) - Connect erected columns by beams and bracing to +37.26 | 14/05/2018 | 16/05/2018 | 17/04/2018 | 19/04/2018 | 0 | TK_Complete
THSS0130 | TT_Task | Turbine Hall GL.1-5 /G-F (Bay 3a) - Connect erected columns by beams and bracing to +37.26 | 16/05/2018 | 18/05/2018 | 19/04/2018 | 21/04/2018 | 0 | TK_Complete
THSS0140 | TT_Task | Turbine Hall GL.1-5 /F-E (Bay 4a) - Connect erected columns by beams and bracing to +37.26 | 28/05/2018 | 30/05/2018 | 05/05/2018 | 08/05/2018 | 0 | TK_Complete
THSS0150 | TT_Task | Turbine Hall GL.1-5 /E-D (Bay 5a) - Connect erected columns by beams and bracing to +37.26 | 30/05/2018 | 02/06/2018 | 08/05/2018 | 10/05/2018 | 0 | TK_Complete
THSS0160 | TT_Task | Turbine Hall GL.1-5 /D-C (Bay 6a) - Connect erected columns by beams and bracing to +37.26 | 02/06/2018 | 05/06/2018 | 10/05/2018 | 12/05/2018 | 0 | TK_Complete
THSS0170 | TT_Task | Turbine Hall GL.1-5 /C-B (Bay 7a) - Connect erected columns by beams and bracing to +37.26 | 05/06/2018 | 07/06/2018 | 12/05/2018 | 15/05/2018 | 0 | TK_Complete
THSS0180 | TT_Task | Turbine Hall GL.1-5 /B-A (Bay 8a) - Connect erected columns by beams and bracing to +37.26 | 14/06/2018 | 16/06/2018 | 15/05/2018 | 17/05/2018 | 0 | TK_Complete
THSS0210 | TT_Task | Turbine Hall GL.1-5 - Install main beams to the steel columns at GL.1-5 /H, +37.26 | 15/05/2018 | 16/05/2018 | 18/04/2018 | 19/04/2018 | 0 | TK_Complete
THSS0220 | TT_Task | Turbine Hall GL.1-5 - Install main trusses to the steel columns at GL.1-5 /G2-G1, +37.26 | 17/05/2018 | 18/05/2018 | 12/04/2018 | 13/04/2018 | 0 | TK_Complete
THSS0230 | TT_Task | Turbine Hall GL.1-5 - Install main trusses to the steel columns at GL.1-5 /G, +37.26 | 19/05/2018 | 21/05/2018 | 17/04/2018 | 18/04/2018 | 0 | TK_Complete
THSS0240 | TT_Task | Turbine Hall GL.1-5 - Install main trusses to the steel columns at GL.1-5 /F, +37.26 | 26/05/2018 | 28/05/2018 | 23/04/2018 | 24/04/2018 | 0 | TK_Complete
THSS0250 | TT_Task | Turbine Hall GL.1-5 - Install main trusses to the steel columns at GL.1-5 /E, +37.26 | 04/06/2018 | 05/06/2018 | 11/05/2018 | 12/05/2018 | 0 | TK_Complete
THSS0260 | TT_Task | Turbine Hall GL.1-5 - Install main trusses to the steel columns at GL.1-5 /D, +37.26 | 06/06/2018 | 07/06/2018 | 14/05/2018 | 15/05/2018 | 0 | TK_Complete
THSS0270 | TT_Task | Turbine Hall GL.1-5 - Install main trusses to the steel columns at GL.1-5 /C, +37.26 | 08/06/2018 | 09/06/2018 | 16/05/2018 | 17/05/2018 | 0 | TK_Complete
THSS0280 | TT_Task | Turbine Hall GL.1-5 - Install main trusses to the steel columns at GL.1-5 /B, +37.26 | 16/06/2018 | 19/06/2018 | 17/05/2018 | 18/05/2018 | 0 | TK_Complete
THSS0290 | TT_Task | Turbine Hall GL.1-5 - Install main beams to the steel columns at GL.1-5 /A, +37.26 | 19/06/2018 | 20/06/2018 | 18/05/2018 | 19/05/2018 | 0 | TK_Complete
THSS0310 | TT_Task | Turbine Hall GL.1-5 /H-G2/G1 (Bay 1a) - Connect installed trusses by secondary beams and bracing | 26/05/2018 | 29/05/2018 | 23/04/2018 | 25/04/2018 | 0 | TK_Complete
THSS0320 | TT_Task | Turbine Hall GL.1-5 /G2/G1-G (Bay 2a) - Connect installed trusses by secondary beams and bracing | 26/05/2018 | 29/05/2018 | 23/04/2018 | 25/04/2018 | 0 | TK_Complete
THSS0330 | TT_Task | Turbine Hall GL.1-5 /G-F (Bay 3a) - Connect installed trusses by secondary beams and bracing | 29/05/2018 | 31/05/2018 | 25/04/2018 | 27/04/2018 | 0 | TK_Complete
THSS0340 | TT_Task | Turbine Hall GL.1-5 /F-E (Bay 4a) - Connect installed trusses by secondary beams and bracing | 06/06/2018 | 08/06/2018 | 14/05/2018 | 16/05/2018 | 0 | TK_Complete
THSS0350 | TT_Task | Turbine Hall GL.1-5 /E-D (Bay 5a) - Connect installed trusses by secondary beams and bracing | 08/06/2018 | 11/06/2018 | 16/05/2018 | 18/05/2018 | 0 | TK_Complete
THSS0360 | TT_Task | Turbine Hall GL.1-5 /D-C (Bay 6a) - Connect installed trusses by secondary beams and bracing | 11/06/2018 | 13/06/2018 | 18/05/2018 | 21/05/2018 | 0 | TK_Complete
THSS0370XX | TT_Task | Turbine Hall GL.1-5 /C-B (Bay 7a) - Connect installed trusses by secondary beams and bracing [Deferred Works] | 02/01/2020 | 02/01/2020 | 19/05/2018 | 19/05/2018 | 0 | TK_Complete
THSS0380 | TT_Task | Turbine Hall GL.1-5 /B-A (Bay 8a) - Connect installed trusses by secondary beams and bracing | 21/06/2018 | 23/06/2018 | 21/05/2018 | 24/05/2018 | 0 | TK_Complete
THSS0420 | TT_Task | Turbine Hall GL.2-4 /G2/G1-G (Bay 2a) - Install upper roof steel structure | 30/05/2018 | 31/05/2018 | 26/04/2018 | 27/04/2018 | 0 | TK_Complete
THSS0430 | TT_Task | Turbine Hall GL.2-4 /G-F (Bay 3a) - Install upper roof steel structure | 02/06/2018 | 04/06/2018 | 28/04/2018 | 30/04/2018 | 0 | TK_Complete
THSS0440 | TT_Task | Turbine Hall GL.2-4 /F-E (Bay 4a) - Install upper roof steel structure | 05/06/2018 | 06/06/2018 | 02/05/2018 | 03/05/2018 | 0 | TK_Complete
THSS0450 | TT_Task | Turbine Hall GL.2-4 /E-D (Bay 5a) - Install upper roof steel structure | 12/06/2018 | 13/06/2018 | 19/05/2018 | 21/05/2018 | 0 | TK_Complete
THSS0460 | TT_Task | Turbine Hall GL.2-4 /D-C (Bay 6a) - Install upper roof steel structure | 14/06/2018 | 15/06/2018 | 23/05/2018 | 24/05/2018 | 0 | TK_Complete
THSS0470XX | TT_Task | Turbine Hall GL.2-4 /C-B (Bay 7a) - Install upper roof steel structure [Deferred Works] | 02/01/2020 | 02/01/2020 | 19/05/2018 | 19/05/2018 | 0 | TK_Complete
THSS1010 | TT_Task | Turbine Hall GL5-7 - Erect steel columns SC3(SC2) at GL.6-7 /H | 26/06/2018 | 27/06/2018 | 11/06/2018 | 16/06/2018 | 0 | TK_Complete
THSS1020 | TT_Task | Turbine Hall GL5-7 - Erect steel columns SC3 at GL.7 /G2-G1 | 28/06/2018 | 30/06/2018 | 14/06/2018 | 20/06/2018 | 0 | TK_Complete
THSS1030 | TT_Task | Turbine Hall GL5-7 - Erect steel columns SC3 at GL.7 /F1 | 26/11/2018 | 26/11/2018 | 26/09/2018 | 26/09/2018 | 0 | TK_Complete
THSS1040 | TT_Task | Turbine Hall GL5-7 - Erect steel columns SC3 at GL.7 /F | 26/11/2018 | 26/11/2018 | 27/09/2018 | 27/09/2018 | 0 | TK_Complete
THSS1050 | TT_Task | Turbine Hall GL5-7 - Erect steel columns SC3 at GL.7 /E | 27/11/2018 | 27/11/2018 | 28/09/2018 | 28/09/2018 | 0 | TK_Complete
THSS1060 | TT_Task | Turbine Hall GL5-7 - Erect steel columns SC3 at GL.7 /D | 28/11/2018 | 28/11/2018 | 29/09/2018 | 29/09/2018 | 0 | TK_Complete
THSS1070 | TT_Task | Turbine Hall GL5-7 - Erect steel columns SC3 at GL.7 /C | 29/11/2018 | 29/11/2018 | 02/10/2018 | 02/10/2018 | 0 | TK_Complete
THSS1080 | TT_Task | Turbine Hall GL5-7 - Erect steel columns SC3 at GL.7 /B | 30/11/2018 | 30/11/2018 | 03/10/2018 | 03/10/2018 | 0 | TK_Complete
THSS1090 | TT_Task | Turbine Hall GL5-7 - Erect steel columns SC3 at GL.7 /A | 26/11/2018 | 28/11/2018 | 04/10/2018 | 06/10/2018 | 0 | TK_Complete
THSS1110 | TT_Task | Turbine Hall GL5-7 /H-G1 (Bay 1b) - Connect erected columns by beams and bracing to +32.26 | 26/06/2018 | 28/06/2018 | 21/06/2018 | 23/06/2018 | 0 | TK_Complete
THSS1120 | TT_Task | Turbine Hall GL5-7 /G1 -F (Bay 2b) - Connect erected columns by beams and bracing to +32.26 | 26/11/2018 | 28/11/2018 | 28/09/2018 | 02/10/2018 | 0 | TK_Complete
THSS1130 | TT_Task | Turbine Hall GL5-7 /F-E (Bay 3b) - Connect erected columns by beams and bracing to +32.26 | 26/11/2018 | 28/11/2018 | 03/10/2018 | 05/10/2018 | 0 | TK_Complete
THSS1140 | TT_Task | Turbine Hall GL5-7 /E-D (Bay 4b) - Connect erected columns by beams and bracing to +32.26 | 29/11/2018 | 01/12/2018 | 06/10/2018 | 09/10/2018 | 0 | TK_Complete
THSS1150 | TT_Task | Turbine Hall GL5-7 /D-C (Bay 5b) - Connect erected columns by beams and bracing to +32.26 | 03/12/2018 | 05/12/2018 | 10/10/2018 | 12/10/2018 | 0 | TK_Complete
THSS1160 | TT_Task | Turbine Hall GL5-7 /C-B (Bay 6b) - Connect erected columns by beams and bracing to +32.26 | 06/12/2018 | 08/12/2018 | 13/10/2018 | 16/10/2018 | 0 | TK_Complete
THSS1170 | TT_Task | Turbine Hall GL5-7 /B-A (Bay 7b) - Connect erected columns by beams and bracing to +32.26 | 10/12/2018 | 12/12/2018 | 17/10/2018 | 23/10/2018 | 0 | TK_Complete
THSS1210 | TT_Task | Turbine Hall GL.5-7 - Install main beams to the steel columns at GL.5-7 /H, +32.26 | 03/07/2018 | 03/07/2018 | 25/06/2018 | 25/06/2018 | 0 | TK_Complete
THSS1220 | TT_Task | Turbine Hall GL.5-7 - Install main beams to the steel columns at GL.5-7 /G1, +32.26 | 26/11/2018 | 26/11/2018 | 03/10/2018 | 03/10/2018 | 0 | TK_Complete
THSS1230 | TT_Task | Turbine Hall GL.5-7 - Install main beams to the steel columns at GL.5-7 /F, +32.26 | 29/11/2018 | 29/11/2018 | 06/10/2018 | 06/10/2018 | 0 | TK_Complete
THSS1240 | TT_Task | Turbine Hall GL.5-7 - Install main beams to the steel columns at GL.5-7 /E, +32.26 | 03/12/2018 | 03/12/2018 | 10/10/2018 | 10/10/2018 | 0 | TK_Complete
THSS1250 | TT_Task | Turbine Hall GL.5-7 - Install main beams to the steel columns at GL.5-7 /D, +32.26 | 06/12/2018 | 06/12/2018 | 13/10/2018 | 13/10/2018 | 0 | TK_Complete
THSS1260 | TT_Task | Turbine Hall GL.5-7 - Install main beams to the steel columns at GL.5-7 /C, +32.26 | 10/12/2018 | 10/12/2018 | 17/10/2018 | 17/10/2018 | 0 | TK_Complete
THSS1270 | TT_Task | Turbine Hall GL.5-7 - Install main beams to the steel columns at GL.5-7 /B, +32.26 | 13/12/2018 | 13/12/2018 | 24/10/2018 | 24/10/2018 | 0 | TK_Complete
THSS1280 | TT_Task | Turbine Hall GL.5-7 - Install main beams to the steel columns at GL.5-7 /A, +32.26 | 13/12/2018 | 13/12/2018 | 25/10/2018 | 25/10/2018 | 0 | TK_Complete
THSS1310 | TT_Task | Turbine Hall GL5-7 /H-G1 (Bay 1b) - Connect installed trusses by secondary beams and bracing (Event 046 - ROI #199) | 26/11/2018 | 26/11/2018 | 30/10/2018 | 03/11/2018 | 0 | TK_Complete
THSS1320 | TT_Task | Turbine Hall GL5-7 /G1 -F (Bay 2b) - Connect installed trusses by secondary beams and bracing | 26/11/2018 | 27/11/2018 | 08/10/2018 | 09/10/2018 | 0 | TK_Complete
THSS1330 | TT_Task | Turbine Hall GL5-7 /F-E (Bay 3b) - Connect installed trusses by secondary beams and bracing | 28/11/2018 | 29/11/2018 | 11/10/2018 | 12/10/2018 | 0 | TK_Complete
THSS1340 | TT_Task | Turbine Hall GL5-7 /E-D (Bay 4b) - Connect installed trusses by secondary beams and bracing | 30/11/2018 | 01/12/2018 | 15/10/2018 | 16/10/2018 | 0 | TK_Complete
THSS1350 | TT_Task | Turbine Hall GL5-7 /D-C (Bay 5b) - Connect installed trusses by secondary beams and bracing | 03/12/2018 | 04/12/2018 | 18/10/2018 | 19/10/2018 | 0 | TK_Complete
THSS1360 | TT_Task | Turbine Hall GL5-7 /C-B (Bay 6b) - Connect installed trusses by 2ndary beams &amp; bracing [DEF_WK07 not required] | 26/11/2018 | 27/11/2018 | 25/10/2018 | 26/10/2018 | 0 | TK_Complete
THSS1370 | TT_Task | Turbine Hall GL5-7 /B-A (Bay 7b) - Connect installed trusses by secondary beams and bracing | 14/12/2018 | 15/12/2018 | 27/10/2018 | 29/10/2018 | 0 | TK_Complete
THSS2010 | TT_Task | Turbine Hall GL.7-10 (Bay 1c) - Erect steel columns and bracing SC4 at GL.7-10 /K1-G1 | 28/06/2018 | 30/06/2018 | 21/06/2018 | 10/07/2018 | 0 | TK_Complete
THSS2020 | TT_Task | Turbine Hall GL.7-10 (Bay 2c) - Erect steel columns and bracing SC4 at GL.7-10 /G1-F | 26/11/2018 | 28/11/2018 | 28/09/2018 | 02/10/2018 | 0 | TK_Complete
THSS2030 | TT_Task | Turbine Hall GL.7-10 (Bay 3c) - Erect steel columns and bracing SC4 at GL.7-10 /F-C | 26/11/2018 | 28/11/2018 | 30/10/2018 | 01/11/2018 | 0 | TK_Complete
THSS2040 | TT_Task | Turbine Hall GL.7-10 (Bay 4c) - Erect steel columns and bracing SC4 at GL.7-10 /C-A | 29/11/2018 | 01/12/2018 | 06/11/2018 | 08/11/2018 | 0 | TK_Complete
THSS2110 | TT_Task | Turbine Hall GL.7-10 (Bay 1c) - Install steel main and secondary beams at level +10.8 | 03/07/2018 | 05/07/2018 | 25/06/2018 | 12/07/2018 | 0 | TK_Complete
THSS2120 | TT_Task | Turbine Hall GL.7-10 (Bay 2c) - Install steel main and secondary beams at to level +10.8 | 06/12/2018 | 08/12/2018 | 03/10/2018 | 05/10/2018 | 0 | TK_Complete
THSS2130 | TT_Task | Turbine Hall GL.7-10 (Bay 3c) - Install steel main and secondary beams at to level +10.8 | 26/11/2018 | 28/11/2018 | 02/11/2018 | 05/11/2018 | 0 | TK_Complete
THSS2210 | TT_Task | Turbine Hall GL.7-10 (Bay 1c) - Construct floor slab at level +10.8 | 27/08/2018 | 29/08/2018 | 23/07/2018 | 06/09/2018 | 0 | TK_Complete
THSS2220 | TT_Task | Turbine Hall GL.7-10 (Bay 2c) - Construct floor slab at to level +10.8 | 26/11/2018 | 28/11/2018 | 02/11/2018 | 18/11/2018 | 0 | TK_Complete
THSS2230 | TT_Task | Turbine Hall GL.7-10 (Bay 3c) - Construct floor slab at level +10.8 | 26/01/2019 | 13/02/2019 | 28/11/2018 | 14/12/2018 | 0 | TK_Complete
THSS2240 | TT_FinMile | Turbine Hall GL.7-10 - Complete floor slab at level +10.8 | 13/02/2019 | 13/02/2019 | 14/12/2018 | 14/12/2018 | 0 | TK_Complete
THSS2310 | TT_Task | Turbine Hall GL.7-10 (Bay 1c) - Install steel beams and bracing at level +14.85 | 26/07/2018 | 08/08/2018 | 29/06/2018 | 14/07/2018 | 0 | TK_Complete
THSS2320 | TT_Task | Turbine Hall GL.7-10 (Bay 2c) - Install steel beams and bracing at level +14.85 | 13/12/2018 | 17/12/2018 | 06/10/2018 | 10/10/2018 | 0 | TK_Complete
THSS2330 | TT_Task | Turbine Hall GL.7-10 (Bay 3c) - Install steel beams and bracing at level +14.85 | 26/11/2018 | 29/11/2018 | 09/11/2018 | 13/11/2018 | 0 | TK_Complete
THSS2340 | TT_Task | Turbine Hall GL.7-10 (Bay 4c) - Install steel beams and bracing at level +14.85 | 30/11/2018 | 04/12/2018 | 14/11/2018 | 19/11/2018 | 0 | TK_Complete
THSS2400 | TT_Task | Turbine Hall GL.7-10 (Bay 1c) - Construct roof slab at level +14.85 | 26/11/2018 | 18/12/2018 | 27/09/2018 | 23/10/2018 | 0 | TK_Complete
THSS2410 | TT_Task | Turbine Hall GL.7-10 (Bay 2c) - Construct roof slab at level +14.85 | 26/01/2019 | 13/02/2019 | 24/11/2018 | 14/12/2018 | 0 | TK_Complete
THSS2420 | TT_Task | Turbine Hall GL.7-10 (Bay 3c) - Construct roof slab at level +14.85 | 26/01/2019 | 15/02/2019 | 16/12/2018 | 29/12/2018 | 0 | TK_Complete
THSS2430 | TT_FinMile | Turbine Hall GL.7-10 - Complete roof slab at level +14.85 | 26/01/2019 | 26/01/2019 | 29/12/2018 | 29/12/2018 | 0 | TK_Complete
DEF_WK01 | TT_Task | DW01 - Construct Roof of Turbine Hall (GL.B~C /1-5) after installation of main OH crane | 26/07/2018 | 31/08/2018 | 23/07/2018 | 05/08/2018 | 0 | TK_Complete
THRF0510 | TT_Task | Turbine Hall GL.1-5 /H-G2/G1 (Bay 1a) - Kalbau | 26/06/2018 | 28/06/2018 | 07/06/2018 | 26/06/2018 | 0 | TK_Complete
THRF0520 | TT_Task | Turbine Hall GL.1-5 /G2/G1-G (Bay 2a) - Kalbau | 29/06/2018 | 03/07/2018 | 20/06/2018 | 29/06/2018 | 0 | TK_Complete
THRF0530 | TT_Task | Turbine Hall GL.1-5 /G-F (Bay 3a) - Kalbau | 31/07/2018 | 02/08/2018 | 29/06/2018 | 03/07/2018 | 0 | TK_Complete
THRF0540 | TT_Task | Turbine Hall GL.1-5 /F-E (Bay 4a) - Kalbau | 04/08/2018 | 07/08/2018 | 03/07/2018 | 07/07/2018 | 0 | TK_Complete
THRF0550 | TT_Task | Turbine Hall GL.1-5 /E-D (Bay 5a) - Kalbau | 08/08/2018 | 10/08/2018 | 07/07/2018 | 09/07/2018 | 0 | TK_Complete
THRF0560 | TT_Task | Turbine Hall GL.1-5 /D-C (Bay 6a) - Kalbau | 11/08/2018 | 14/08/2018 | 09/07/2018 | 10/07/2018 | 0 | TK_Complete
THRF0570XX | TT_Task | Turbine Hall GL.1-5 /C-B (Bay 7a) - Install standing seam roof cladding [Deferred Works] | 02/01/2020 | 02/01/2020 | 19/05/2018 | 19/05/2018 | 0 | TK_Complete
THRF0580 | TT_Task | Turbine Hall GL.1-5 /B-A (Bay 8a) - Kalbau | 19/07/2018 | 21/07/2018 | 13/06/2018 | 12/07/2018 | 0 | TK_Complete
THRF0590 | TT_FinMile | Turbine Hall GL.1-5 - Weathertight (i.e. Kalbau installed with temporary measures) | 05/09/2018 | 05/09/2018 | 05/08/2018 | 05/08/2018 | 0 | TK_Complete
THRF0610 | TT_Task | Turbine Hall GL.1-5 - Vapour barrier &amp; ST clips | 26/11/2018 | 28/12/2018 | 27/10/2018 | 14/11/2018 | 0 | TK_Complete
THRF0620 | TT_Task | Turbine Hall GL.1-5 - Insulation &amp; Kalzip | 26/11/2018 | 12/12/2018 | 23/11/2018 | 29/12/2018 | 0 | TK_Complete
THRF0630 | TT_Task | Turbine Hall GL.1-5 - Remaining works related to dog houses | 02/05/2019 | 22/05/2019 | 11/02/2019 | 14/06/2019 | 0 | TK_Complete
DEF_WK08 | TT_Task | DW08 - Construct Roof of Turbine Hall(GL.F~G1 /5-7) after equip.installation on platfrom at +12.15 | 01/06/2019 | 29/06/2019 | 04/05/2019 | 09/09/2019 | 0 | TK_Complete
THRF1410 | TT_Task | Turbine Hall GL5-7 - Cleats, purlins, bridging, bracing, etc | 03/07/2018 | 23/08/2018 | 25/06/2018 | 09/12/2018 | 0 | TK_Complete
THRF1420 | TT_Task | Turbine Hall GL5-7 /H-G1 (Bay 1b) - Kalbau | 26/11/2018 | 28/11/2018 | 10/11/2018 | 12/12/2018 | 0 | TK_Complete
THRF1430 | TT_Task | Turbine Hall GL5-7 /F-E (Bay 3b) - Kalbau | 29/11/2018 | 01/12/2018 | 12/11/2018 | 14/11/2018 | 0 | TK_Complete
THRF1440 | TT_Task | Turbine Hall GL5-7 /E-D (Bay 4b) - Kalbau | 29/11/2018 | 01/12/2018 | 14/11/2018 | 16/11/2018 | 0 | TK_Complete
THRF1450 | TT_Task | Turbine Hall GL5-7 /D-C (Bay 5b) - Kalbau | 03/12/2018 | 05/12/2018 | 16/11/2018 | 19/11/2018 | 0 | TK_Complete
THRF1460 | TT_Task | Turbine Hall GL5-7 /C-B (Bay 6b) - Kalbau (DEF_WK07 confirmed not required) | 26/01/2019 | 29/01/2019 | 13/12/2018 | 15/12/2018 | 0 | TK_Complete
THRF1470 | TT_Task | Turbine Hall GL5-7 /B-A (Bay 7b) - Kalbau | 29/01/2019 | 31/01/2019 | 16/12/2018 | 18/12/2018 | 0 | TK_Complete
THRF1480 | TT_FinMile | Turbine Hall GL5-7 - Weathertight (i.e. Kalbau installed with temporary measures) | 31/01/2019 | 31/01/2019 | 18/12/2018 | 18/12/2018 | 0 | TK_Complete
THRF5085 | TT_Task | West Elevation / GL.7 / Gutter subframe | 01/04/2019 | 05/05/2019 | 22/03/2019 | 04/09/2019 | 0 | TK_Complete
THRF5090 | TT_Task | West Elevation / GL.7 / Gutter Installation | 10/07/2019 | 27/07/2019 | 15/05/2019 | 25/10/2019 | 0 | TK_Complete
THRF5160 | TT_Task | Turbine Hall GL.5-7 - Vapour barrier &amp; ST clips | 26/01/2019 | 15/02/2019 | 23/12/2018 | 12/01/2019 | 0 | TK_Complete
THRF5170 | TT_Task | Turbine Hall GL.5-7 - Insulation &amp; Kalzip | 02/02/2019 | 22/02/2019 | 04/01/2019 | 15/01/2019 | 0 | TK_Complete
EV058010 | TT_FinMile | Air Intake &amp; Bus Duct Installation / M&amp;E access available | 26/01/2019 | 26/01/2019 | 19/01/2019 | 19/01/2019 | 0 | TK_Complete
EV058020 | TT_Task | Air Intake &amp; Bus Duct Installation / Construction period | 26/01/2019 | 25/04/2019 | 20/01/2019 | 08/09/2019 | 0 | TK_Complete
THRF2400 | TT_Task | Turbine Hall GL.7-10 - Cleats, purlins, bridging, etc | 26/01/2019 | 05/03/2019 | 15/11/2018 | 19/01/2019 | 0 | TK_Complete
THRF2410 | TT_Task | Turbine Hall GL.7-10 (Bay 1c) - embeds and subframe | 01/09/2019 | 07/09/2019 | 05/08/2019 | 11/08/2019 | 0 | TK_Complete
THRF2420 | TT_Task | Turbine Hall GL.7-10 (Bay 2c) - Embeds and subframe | 07/09/2019 | 13/09/2019 | 11/08/2019 | 17/08/2019 | 0 | TK_Complete
THRF2430 | TT_Task | Turbine Hall GL.7-10 (Bay 3c) - Embeds and subframe | 01/01/2020 | 31/01/2020 | 09/09/2019 | 04/10/2019 | 0 | TK_Complete
THRF2440 | TT_Task | Turbine Hall GL.7-10 (Bay 4c) - Kalbau | 06/03/2019 | 22/03/2019 | 12/01/2019 | 19/01/2019 | 0 | TK_Complete
THRF2450 | TT_FinMile | Turbine Hall GL.7-10 - Weathertight (i.e. Kalbau installed with temporary measures) | 26/01/2019 | 26/01/2019 | 19/01/2019 | 19/01/2019 | 0 | TK_Complete
THRF2452 | TT_Task | Turbine Hall GL.7-10 (Bay 4c) - Deferred Opening | 01/08/2019 | 16/08/2019 | 01/03/2019 | 16/03/2019 | 0 | TK_Complete
THRF2454 | TT_Task | Turbine Hall GL.7-10 (Bay 4c) - Kalzip | 01/08/2019 | 20/08/2019 | 06/03/2019 | 25/03/2019 | 0 | TK_Complete
THRF2470 | TT_Task | Turbine Hall GL.7-10 / F-K - Kalbau/ VB/ ST clip/ Insul./ Kalzip | 01/09/2019 | 17/09/2019 | 14/08/2019 | 25/09/2019 | 0 | TK_Complete
THRF2480 | TT_Task | Turbine Hall GL.7-10 / A-F - Kalbau/ VB/ ST clip/ Insul./ Kalzip | 01/02/2020 | 21/02/2020 | 05/10/2019 | 21/10/2019 | 0 | TK_Complete
THRF5110 | TT_Task | West Elevation / GL.10, K -E / Gutter subframe | 06/05/2019 | 10/05/2019 | 28/03/2019 | 09/05/2019 | 0 | TK_Complete
THRF5120 | TT_Task | West Elevation / GL. 10, E -A / Gutter subframe | 08/04/2019 | 12/04/2019 | 28/03/2019 | 09/05/2019 | 0 | TK_Complete
THRF5130 | TT_Task | West Elevation / GL. 10, K -E / Gutter Installation | 13/09/2019 | 27/09/2019 | 17/06/2019 | 27/07/2019 | 0 | TK_Complete
THRF5140 | TT_Task | West Elevation / GL. 10, E -A / Gutter Installation | 13/09/2019 | 27/09/2019 | 17/06/2019 | 27/07/2019 | 0 | TK_Complete
THRF5010 | TT_Task | East Elevation / GL.1, A-E / Gutter subframe | 02/05/2019 | 08/05/2019 | 04/04/2019 | 14/05/2019 | 0 | TK_Complete
THRF5020 | TT_Task | East Elevation / GL.1, E -K / Gutter subframe | 09/05/2019 | 15/05/2019 | 04/04/2019 | 14/05/2019 | 0 | TK_Complete
THRF5040 | TT_Task | East Elevation / GL. 1, A-E / Gutter Installation | 19/06/2019 | 02/07/2019 | 17/05/2019 | 22/06/2019 | 0 | TK_Complete
THRF5050 | TT_Task | East Elevation / GL. 1, E-K / Gutter Installation | 19/06/2019 | 02/07/2019 | 17/05/2019 | 22/06/2019 | 0 | TK_Complete
THRF5060 | TT_Task | West Elevation / GL.5, A-E / Gutter subframe | 01/04/2019 | 15/04/2019 | 26/03/2019 | 15/05/2019 | 0 | TK_Complete
THRF5070 | TT_Task | West Elevation / GL.5, E-K / Gutter subframe | 02/05/2019 | 14/05/2019 | 26/03/2019 | 15/05/2019 | 0 | TK_Complete
THRF5100 | TT_Task | West Elevation / GL.5, A-E / Gutter Installation | 01/06/2019 | 15/06/2019 | 11/05/2019 | 10/08/2019 | 0 | TK_Complete
THRF5105 | TT_Task | West Elevation / GL.5, E-K / Gutter Installation | 01/06/2019 | 15/06/2019 | 11/05/2019 | 10/08/2019 | 0 | TK_Complete
DEF_WK03 | TT_Task | DW03 - Construct Walls of Turbine Hall below +12.0(GL.K /5-7) after erection of Condensate Pipe Rack &amp; associated equip | 01/04/2019 | 01/06/2019 | 07/11/2018 | 14/11/2018 | 0 | TK_Complete
RCWL0010 | TT_Task | Perimeter RC Wall / North Elevation - GL.1 -5 | 30/10/2018 | 09/11/2018 | 02/07/2018 | 19/07/2018 | 0 | TK_Complete
RCWL0030 | TT_Task | Perimeter RC Wall / North Elevation - GL.7 -10 | 21/08/2018 | 24/08/2018 | 12/04/2018 | 12/05/2018 | 0 | TK_Complete
RCWL0040 | TT_Task | Perimeter RC Wall / East Elevation - GL.A -C | 12/07/2018 | 16/07/2018 | 21/06/2018 | 27/07/2018 | 0 | TK_Complete
RCWL0050 | TT_Task | Perimeter RC Wall / East Elevation - GL.C -E | 07/07/2018 | 11/07/2018 | 21/06/2018 | 27/07/2018 | 0 | TK_Complete
RCWL0060 | TT_Task | Perimeter RC Wall / East Elevation - GL.E -G | 30/06/2018 | 05/07/2018 | 02/06/2018 | 16/06/2018 | 0 | TK_Complete
RCWL0070 | TT_Task | Perimeter RC Wall / East Elevation - GL.G -K | 26/06/2018 | 29/06/2018 | 02/06/2018 | 16/06/2018 | 0 | TK_Complete
RCWL0080 | TT_Task | Perimeter RC Wall / South Elevation - GL.10 -7 | 26/11/2018 | 30/11/2018 | 19/10/2018 | 28/10/2018 | 0 | TK_Complete
RCWL0090 | TT_Task | Perimeter RC Wall / South Elevation - GL.7 -5 [Deferred Works] | 26/11/2018 | 26/11/2018 | 19/10/2018 | 28/10/2018 | 0 | TK_Complete
RCWL0100 | TT_Task | Perimeter RC Wall / South Elevation - GL.5 -2 | 27/08/2018 | 31/08/2018 | 11/07/2018 | 25/07/2018 | 0 | TK_Complete
RCWL0110 | TT_Task | Perimeter RC Wall / West Elevation - GL.K -G | 06/08/2018 | 09/08/2018 | 12/04/2018 | 12/05/2018 | 0 | TK_Complete
RCWL0120 | TT_Task | Perimeter RC Wall / West Elevation - GL.G -E | 26/11/2018 | 29/11/2018 | 20/10/2018 | 24/11/2018 | 0 | TK_Complete
RCWL0130 | TT_Task | Perimeter RC Wall / West Elevation - GL.E -C | 30/11/2018 | 04/12/2018 | 20/10/2018 | 04/11/2018 | 0 | TK_Complete
RCWL0140 | TT_Task | Perimeter RC Wall / West Elevation - GL.C -A | 26/11/2018 | 29/11/2018 | 19/10/2018 | 28/10/2018 | 0 | TK_Complete
DEF_WK05 | TT_Task | DW05 - Construct Int.Structural Steel Members of Turbine Hall below +23.9 (GL.A-C/11) | 01/08/2019 | 30/08/2019 | 18/04/2019 | 16/05/2019 | 0 | TK_Complete
DEF_WK11 | TT_Task | DW11 - Capping of all cladding openings required by / following the installation of all items of plant and equip (TBC) | 01/06/2019 | 15/08/2019 | 13/05/2019 | 24/01/2020 | 0 | TK_Complete
LIFT1020 | TT_Task | Lift No.1 - Glazing panel to lift shaft | 02/05/2019 | 29/05/2019 | 27/03/2019 | 15/05/2019 | 0 | TK_Complete
MCGZ0010 | TT_Task | North Elevation GL.1-5 / Cleats, purlins, bridging, bracing, etc | 26/11/2018 | 08/12/2018 | 27/09/2018 | 15/01/2019 | 0 | TK_Complete
MCGZ0020 | TT_Task | North Elevation GL.1-5 / Kalbau | 23/02/2019 | 09/03/2019 | 25/12/2018 | 19/01/2019 | 0 | TK_Complete
MCGZ0030 | TT_Task | North Elevation GL.1-5 / Vapour barrier &amp; ST clips | 01/02/2019 | 28/02/2019 | 14/01/2019 | 24/01/2019 | 0 | TK_Complete
MCGZ0040 | TT_Task | East Elevation at GL.1 / Mullion &amp; transom | 26/01/2019 | 09/03/2019 | 13/12/2018 | 14/02/2019 | 0 | TK_Complete
MCGZ0050 | TT_Task | East Elevation at GL.1 / Glazing panels | 11/03/2019 | 02/05/2019 | 24/01/2019 | 03/03/2019 | 0 | TK_Complete
MCGZ0070 | TT_Task | East Elevation at GL.1 / Subframe for aluminum features | 04/04/2019 | 24/04/2019 | 11/02/2019 | 31/05/2019 | 0 | TK_Complete
MCGZ0080 | TT_Task | South Elevation GL.1-5 / Cleats, purlins, bridging, bracing, etc | 26/11/2018 | 23/02/2019 | 03/10/2018 | 16/01/2019 | 0 | TK_Complete
MCGZ0090 | TT_Task | South Elevation GL.1-5 / Kalbau | 25/02/2019 | 23/03/2019 | 20/11/2018 | 31/01/2019 | 0 | TK_Complete
MCGZ0100 | TT_Task | South Elevation GL.1-5 / Vapour barrier &amp; ST clips | 31/01/2019 | 27/02/2019 | 02/01/2019 | 28/02/2019 | 0 | TK_Complete
MCGZ0105 | TT_Task | South Elevation GL.1-5 / Insulation &amp; Kalzip | 15/04/2019 | 02/05/2019 | 13/02/2019 | 28/02/2019 | 0 | TK_Complete
MCGZ0110 | TT_Task | West Elevation at GL.5 / Mullion &amp; transom | 26/01/2019 | 12/02/2019 | 07/01/2019 | 22/02/2019 | 0 | TK_Complete
MCGZ0120 | TT_Task | West Elevation at GL.5 / Glazing panels | 27/04/2019 | 02/05/2019 | 20/02/2019 | 28/02/2019 | 0 | TK_Complete
MCGZ0140 | TT_Task | West Elevation at GL.5 / Subframe for aluminum features | 02/05/2019 | 20/05/2019 | 01/04/2019 | 10/08/2019 | 0 | TK_Complete
MCGZ0150 | TT_Task | West Elevation at GL.5 / Aluminum featured claddings | 16/08/2019 | 28/08/2019 | 03/07/2019 | 15/08/2019 | 0 | TK_Complete
MCGZ1010 | TT_Task | North Elevation GL.1-5 / Insulation &amp; Kalzip | 02/02/2019 | 01/03/2019 | 21/01/2019 | 29/01/2019 | 0 | TK_Complete
MCGZ1015 | TT_Task | North Elevation GL.5-10 / Cleats, purlins, bridging, bracing, etc | 26/01/2019 | 04/03/2019 | 23/11/2018 | 24/12/2018 | 0 | TK_Complete
MCGZ1030 | TT_Task | North Elevation GL.5-10 / Kalbau | 22/02/2019 | 04/03/2019 | 17/12/2018 | 19/01/2019 | 0 | TK_Complete
MCGZ1040 | TT_Task | East Elevation at GL.1 / Aluminum featured claddings | 01/08/2019 | 19/08/2019 | 25/06/2019 | 30/11/2019 | 0 | TK_Complete
MCGZ1050 | TT_Task | East Elevation at GL.1 / Cleats, purlins, bridging, bracing, etc | 26/11/2018 | 12/01/2019 | 31/08/2018 | 20/10/2018 | 0 | TK_Complete
MCGZ1060 | TT_Task | East Elevation at GL.1 / Subframe for wall claddings | 26/01/2019 | 01/02/2019 | 30/11/2018 | 05/12/2018 | 0 | TK_Complete
MCGZ1070 | TT_Task | Eest Elevation at GL.1 / Remaining cleats, purlins, bracing, etc. | 02/02/2019 | 22/02/2019 | 03/12/2018 | 09/12/2018 | 0 | TK_Complete
MCGZ1080 | TT_Task | South Elevation GL.5-10 / Cleats, purlins, bridging, bracing, etc | 26/01/2019 | 15/03/2019 | 28/11/2018 | 13/03/2019 | 0 | TK_Complete
MCGZ1090 | TT_Task | South Elevation GL.5-10 / Kalbau | 02/03/2019 | 15/03/2019 | 07/01/2019 | 14/03/2019 | 0 | TK_Complete
MCGZ1100 | TT_Task | South Elevation GL.5-10 / Vapour barrier &amp; ST clips | 04/05/2019 | 25/05/2019 | 08/03/2019 | 31/03/2019 | 0 | TK_Complete
MCGZ1105 | TT_Task | South Elevation GL.5-10 / Insulation &amp; Kalzip | 20/05/2019 | 01/06/2019 | 15/03/2019 | 29/03/2019 | 0 | TK_Complete
MCGZ1110 | TT_Task | West Elevation at GL.7 / Mullion &amp; transom | 01/04/2019 | 04/05/2019 | 15/02/2019 | 20/03/2019 | 0 | TK_Complete
MCGZ1120 | TT_Task | West Elevation at GL.7 / Glazing panels | 29/04/2019 | 11/05/2019 | 12/03/2019 | 30/03/2019 | 0 | TK_Complete
MCGZ1122 | TT_FinMile | West Elevation at GL.7 / Access to Air Intake [EVENT063] | 01/08/2019 | 01/08/2019 | 19/07/2019 | 19/07/2019 | 0 | TK_Complete
MCGZ1124 | TT_Task | West Elevation at GL.7 / Erect PERI bridge over scaffold [EVENT063] | 01/08/2019 | 15/08/2019 | 20/07/2019 | 03/08/2019 | 0 | TK_Complete
MCGZ1126 | TT_Task | West Elevation at GL.7 / Complete remaining glazing [EVENT063] | 05/09/2019 | 28/09/2019 | 05/08/2019 | 28/08/2019 | 0 | TK_Complete
MCGZ1140 | TT_Task | West Elevation at GL.7 / Subframe for aluminum features | 02/05/2019 | 13/05/2019 | 01/04/2019 | 12/10/2019 | 0 | TK_Complete
MCGZ1150 | TT_Task | West Elevation at GL.7 / Aluminum featured claddings | 23/08/2019 | 02/09/2019 | 15/07/2019 | 25/10/2019 | 0 | TK_Complete
MCGZ1160 | TT_Task | West Elevation at GL.7 / Cleats, purlins, bridging, bracing, etc | 26/01/2019 | 27/04/2019 | 29/11/2018 | 28/03/2019 | 0 | TK_Complete
MCGZ1170 | TT_Task | West Elevation at GL.7 / Kalbau | 25/04/2019 | 10/05/2019 | 21/03/2019 | 31/03/2019 | 0 | TK_Complete
MCGZ1172 | TT_Mile | West Elevation at GL.7 / Vent pipe support frame handed over to KSS [EVENT / ROI] | 02/01/2020 | 02/01/2020 | 05/09/2019 | 05/09/2019 | 0 | TK_Complete
MCGZ1174 | TT_Task | West Elevation at GL.7 / KSS mounting vent pipe onto support frame [EVENT] | 02/01/2020 | 14/01/2020 | 05/09/2019 | 27/09/2019 | 0 | TK_Complete
MCGZ1176 | TT_Task | West Elevation at GL.7 / KSS place vent pipe and support frame in position, bolt fixing by LCAL [EVENT / ROI] | 15/01/2020 | 15/01/2020 | 28/09/2019 | 28/09/2019 | 0 | TK_Complete
MCGZ1180 | TT_Task | West Elevation at GL.7 / Vapour barrier &amp; ST clips | 02/05/2019 | 24/05/2019 | 01/04/2019 | 03/10/2019 | 0 | TK_Complete
MCGZ1190 | TT_Task | West Elevation at GL.7 / Insulation &amp; Kalzip | 18/05/2019 | 31/05/2019 | 29/04/2019 | 10/10/2019 | 0 | TK_Complete
MCGZ2010 | TT_Task | North Elevation GL.5-10 / Vapour barrier &amp; ST clips | 31/12/2018 | 14/01/2019 | 31/12/2018 | 28/03/2019 | 0 | TK_Complete
MCGZ2020 | TT_Task | North Elevation GL.5-10 / Insulation &amp; Kalzip | 02/02/2019 | 22/02/2019 | 08/01/2019 | 01/04/2019 | 0 | TK_Complete
MCGZ2040 | TT_Task | East Elevation at GL.1 / Kalbau | 26/11/2018 | 29/12/2018 | 09/11/2018 | 09/12/2018 | 0 | TK_Complete
MCGZ2050 | TT_Task | East Elevation at GL.1 / Vapour barrier &amp; ST clips | 01/04/2019 | 25/04/2019 | 28/03/2019 | 20/04/2019 | 0 | TK_Complete
MCGZ2060 | TT_Task | East Elevation at GL.1 / Insulation &amp; Kalzip | 07/05/2019 | 28/05/2019 | 20/04/2019 | 30/04/2019 | 0 | TK_Complete
MCGZ2070 | TT_Task | East Elevation at GL.1 / Louvres (incl' those at the Loft) | 12/04/2019 | 16/05/2019 | 16/01/2019 | 01/03/2019 | 0 | TK_Complete
MCGZ2078 | TT_FinMile | South Elevation GL.7-10 / KSS handover the area [EVENT] | 01/01/2020 | 01/01/2020 | 15/09/2019 | 15/09/2019 | 0 | TK_Complete
MCGZ2090 | TT_Task | North Elevation GL.1-10 / Aluminum features claddings | 02/09/2019 | 18/10/2019 | 16/08/2019 | 16/11/2019 | 0 | TK_Complete
MCGZ2100 | TT_Task | South Elevation GL.1-10 / Aluminum features claddings | 02/01/2020 | 03/02/2020 | 24/09/2019 | 21/10/2019 | 0 | TK_Complete
MCGZ2110 | TT_Task | West Elevation at GL.10 / Mullion &amp; transom | 01/04/2019 | 08/04/2019 | 18/03/2019 | 25/03/2019 | 0 | TK_Complete
MCGZ2120 | TT_Task | West Elevation at GL.10 / Glazing panels | 09/04/2019 | 15/04/2019 | 25/03/2019 | 30/03/2019 | 0 | TK_Complete
MCGZ2140 | TT_Task | West Elevation at GL.10 / Subframe for aluminum features | 02/05/2019 | 18/05/2019 | 25/03/2019 | 15/08/2019 | 0 | TK_Complete
MCGZ2150 | TT_Task | West Elevation at GL.10 / Aluminum featured claddings | 16/08/2019 | 29/08/2019 | 18/07/2019 | 22/08/2019 | 0 | TK_Complete
MCGZ2160 | TT_Task | West Elevation at GL.10 / Cleats, purlins, bridging, bracing, etc | 01/06/2019 | 15/06/2019 | 02/05/2019 | 18/07/2019 | 0 | TK_Complete
MCGZ2170 | TT_Task | West Elevation at GL.10 / Aluminum wall cladding | 22/08/2019 | 03/09/2019 | 23/05/2019 | 31/10/2019 | 0 | TK_Complete
MCGZ2180 | TT_Task | West Elevation at GL.10 / Louvres to 1st floor rooms | 02/05/2019 | 14/05/2019 | 27/04/2019 | 13/06/2019 | 0 | TK_Complete
MCGZ2190 | TT_Task | West Elevation at GL.10 / Louvres to ground floor rooms | 15/05/2019 | 24/05/2019 | 27/04/2019 | 19/10/2019 | 0 | TK_Complete
MCGZ2200 | TT_Task | North Elevation GL.1-10 / Louvres | 02/05/2019 | 13/07/2019 | 04/04/2019 | 25/09/2019 | 0 | TK_Complete
MCGZ2210 | TT_Task | South Elevation GL.1-10 / Louvres | 01/04/2019 | 15/06/2019 | 11/03/2019 | 20/04/2019 | 0 | TK_Complete
PLAT0060 | TT_Task | Crane Walkway, Steel Platforms and Staircases | 26/01/2019 | 22/02/2019 | 13/08/2018 | 19/03/2019 | 0 | TK_Complete
PLAT0070 | TT_Task | GMS grating at Loft Level at +37.8 | 01/08/2019 | 29/09/2019 | 20/06/2019 | 11/09/2019 | 0 | TK_Complete
BDWK0010 | TT_Task | Lube Oil Module - Construct 1m high bund wall | 16/10/2018 | 26/10/2018 | 15/08/2018 | 24/08/2018 | 0 | TK_Complete
BDWK0015 | TT_Task | Switchgear Block - Construct internal concrete wall G/F | 27/10/2018 | 16/11/2018 | 10/05/2018 | 08/01/2019 | 0 | TK_Complete
BDWK0020 | TT_Task | Switchgear Block - Construct internal concrete wall 1/F | 26/01/2019 | 22/02/2019 | 24/10/2018 | 12/01/2019 | 0 | TK_Complete
BDWK0030 | TT_Task | Turbine Building (GL001) - ABWF works | 26/01/2019 | 22/02/2019 | 01/09/2018 | 27/02/2020 | 0 | TK_Complete
BDWK0040 | TT_Task | Condensate Polishing Plant (GL002) - ABWF works | 23/02/2019 | 01/03/2019 | 07/12/2018 | 27/02/2020 | 0 | TK_Complete
BDWK0050 | TT_Task | Switchgear Block G/F - ABWF works | 26/01/2019 | 01/03/2019 | 04/10/2018 | 30/03/2019 | 0 | TK_Complete
BDWK0060 | TT_Task | Switchgear Block 1/F - ABWF works | 26/01/2019 | 01/03/2019 | 28/11/2018 | 30/03/2019 | 0 | TK_Complete
BDWK0070 | TT_Task | Raised floor to Electronic Equipment and Control Room | 02/05/2019 | 17/05/2019 | 08/04/2019 | 11/05/2019 | 0 | TK_Complete
BDWK0080XX | TT_Task | Suespended ceiling to Control Room and ELV Room [descoped; TBC] | 02/05/2019 | 17/05/2019 | 08/04/2019 | 11/05/2019 | 0 | TK_Complete
BDWK0100 | TT_Task | Doors, louvre, roller shutters, handrails, etc | 01/04/2019 | 13/08/2019 | 18/03/2019 | 27/02/2020 | 0 | TK_Complete
BDWK0110 | TT_Task | Finishes to perimeter concrete walls (i.e. tiling) | 02/01/2020 | 25/02/2020 | 06/11/2019 | 24/12/2019 | 0 | TK_Complete
OHCN0005 | TT_Task | Overhead Crane - Unpack and Checking | 01/05/2018 | 14/05/2018 | 08/01/2018 | 19/01/2018 | 0 | TK_Complete
OHCN0006 | TT_Task | Overhead Crane - Pre-assembly at Green Lawn | 23/04/2018 | 23/05/2018 | 02/03/2018 | 29/03/2018 | 0 | TK_Complete
OHCN0006a | TT_Mile | Overhead Crane / Event - Crane rail hold down bolt on site (supplied nby Siemens) | 26/05/2018 | 26/05/2018 | 26/05/2018 | 26/05/2018 | 0 | TK_Complete
OHCN0006b | TT_Task | Overhead Crane / Event - Bolt inspection and handover | 26/06/2018 | 29/06/2018 | 26/05/2018 | 29/05/2018 | 0 | TK_Complete
OHCN0006c | TT_Task | Overhead Crane / Event - Rail installation / Weld on ground | 26/06/2018 | 10/07/2018 | 30/05/2018 | 13/06/2018 | 0 | TK_Complete
OHCN0006d | TT_Task | Overhead Crane / Event - Rail installation / Lift-up | 26/06/2018 | 29/06/2018 | 14/06/2018 | 17/06/2018 | 0 | TK_Complete
OHCN0006e | TT_Task | Overhead Crane / Event - Rail installation / Re-delivery of bolts | 26/06/2018 | 04/07/2018 | 18/06/2018 | 26/06/2018 | 0 | TK_Complete
OHCN0006f | TT_Task | Overhead Crane / Event - Rail installation / Clip down | 26/07/2018 | 05/08/2018 | 27/06/2018 | 13/07/2018 | 0 | TK_Complete
OHCN0007 | TT_Task | Overhead Crane - Lift up and sit on position 1 of 2 | 06/08/2018 | 08/08/2018 | 14/07/2018 | 16/07/2018 | 0 | TK_Complete
OHCN0008 | TT_Task | Overhead Crane - Lift up and sit on position 2 of 2 | 08/08/2018 | 10/08/2018 | 17/07/2018 | 19/07/2018 | 0 | TK_Complete
OHCN0010 | TT_Task | Overhead Crane - E&amp;M Fit-out and T&amp;C | 26/07/2018 | 04/09/2018 | 20/07/2018 | 31/08/2018 | 0 | TK_Complete
THEL0012 | TT_Task | Turbine Hall Area - Lightning Pit and Earth Pit | 02/01/2020 | 20/01/2020 | 22/07/2019 | 18/12/2019 | 0 | TK_Complete
THEL0020 | TT_Task | Turbine Hall Area (GL.1-5) - Cable containment (Elect) | 06/06/2019 | 08/07/2019 | 18/03/2019 | 07/11/2019 | 0 | TK_Complete
THEL0030 | TT_Task | Turbine Hall Area (GL.5-7) - Cable containment (Elect) | 22/06/2019 | 15/07/2019 | 22/04/2019 | 21/11/2019 | 0 | TK_Complete
THEL0040 | TT_Task | Turbine Hall Area (GL.8-10) - Cable containment (Elect) | 04/07/2019 | 22/07/2019 | 27/05/2019 | 31/10/2019 | 0 | TK_Complete
THEL0050 | TT_Task | Turbine Hall Area (High/ Roof Level) - Cable containmen (Elect) | 09/10/2018 | 15/10/2018 | 28/05/2018 | 17/10/2019 | 0 | TK_Complete
THEL0055 | TT_Task | Turbine Hall Area (incl' Switchgear Block) - Major Electrical Equipment on site | 01/06/2019 | 30/06/2019 | 01/04/2019 | 30/04/2019 | 0 | TK_Complete
THEL0060 | TT_Task | Switchgear Block - Installation of LV Switchboard, Transformers, UPS, DBs, etc | 02/07/2019 | 27/08/2019 | 12/11/2018 | 31/05/2019 | 0 | TK_Complete
THEL1020 | TT_Task | Turbine Hall Area (GL.1-5) - Light fitting, power point, earting point incl. final termination | 02/01/2020 | 22/02/2020 | 08/11/2019 | 07/02/2020 | 0 | TK_Complete
THEL1030 | TT_Task | Turbine Hall Area (GL.5-7) - Light fitting, power point, earthing point incl. final termination | 02/01/2020 | 22/02/2020 | 06/12/2019 | 07/02/2020 | 0 | TK_Complete
THEL1040 | TT_Task | Turbine Hall Area (GL.8-10) - Light fitting, power point, earthing point incl. final termination | 21/01/2020 | 12/03/2020 | 01/11/2019 | 07/02/2020 | 0 | TK_Complete
THEL1050 | TT_Task | Turbine Hall Area / Roof Level - Installation of Photovoltaic Power System | 02/01/2020 | 04/03/2020 | 12/10/2019 | 14/11/2019 | 0 | TK_Complete
THAC0010 | TT_Mile | Turbine Hall Area (incl' Switchgear Block) - Major ACMV Equipment on site | 01/04/2019 | 01/04/2019 | 01/02/2019 | 01/02/2019 | 0 | TK_Complete
THAC0015 | TT_Task | Turbine Hall Area / GL.1-5 - Ductwork and fan installation (ACMV) | 01/06/2019 | 26/06/2019 | 02/05/2019 | 29/11/2019 | 0 | TK_Complete
THAC0020 | TT_Task | Turbine Hall Area / GL.5-7 - Ductwork and fan installation (ACMV) | 02/09/2019 | 07/11/2019 | 26/08/2019 | 06/12/2019 | 0 | TK_Complete
THAC0050 | TT_Task | Switchgear Block - Installation of Indoor Unit (VEUs) | 01/04/2019 | 26/04/2019 | 04/02/2019 | 30/03/2019 | 0 | TK_Complete
THAC0060 | TT_Task | Switchgear Block (Turbine Hall Roof Level GL.7-10) - Installation of Outdoor Unit (VCUs) | 02/09/2019 | 15/10/2019 | 19/08/2019 | 15/11/2019 | 0 | TK_Complete
THAC0070 | TT_Task | Turbine Hall Area / Loft Level - Installation of Roof Extraction Fan | 02/09/2019 | 28/10/2019 | 15/08/2019 | 01/11/2019 | 0 | TK_Complete
THAC0080 | TT_Task | Turbine Hall Area - Final ductwork and air grille / diffuser | 02/01/2020 | 19/02/2020 | 26/10/2019 | 06/12/2019 | 0 | TK_Complete
THFS0110 | TT_Task | Turbine Hall - Installation of fire alarm panels | 02/01/2020 | 15/01/2020 | 01/11/2019 | 14/11/2019 | 0 | TK_Complete
THFS0120 | TT_Task | Turbine Hall - Installation of detectors incl' wiring and termination | 02/01/2020 | 15/01/2020 | 01/11/2019 | 14/11/2019 | 0 | TK_Complete
THFS0122 | TT_Task | Turbine Hall - Lift No.1 detector installation | 02/01/2020 | 15/01/2020 | 01/11/2019 | 14/11/2019 | 0 | TK_Complete
THFS0124 | TT_Task | Turbine Hall - Loft Platform detector installation | 02/01/2020 | 15/01/2020 | 01/11/2019 | 14/11/2019 | 0 | TK_Complete
THFS0130 | TT_Task | Turbine Hall - Installation of portable fire fighting equipment | 08/01/2020 | 09/01/2020 | 09/03/2020 | 10/03/2020 | 0 | TK_Complete
THFS0140 | TT_Task | Turbine Hall - Testing and Commisisoning to FS installation | 16/01/2020 | 22/01/2020 | 15/11/2019 | 21/11/2019 | 0 | TK_Complete
LIFT1030 | TT_Task | Lift No.1 - Lift Installation incl' T&amp;C | 01/11/2019 | 01/01/2020 | 23/09/2019 | 31/12/2019 | 0 | TK_Complete
LIFT1040 | TT_Task | Lift No.1 - Submit Form LE5 and EMSD Inspection | 02/01/2020 | 21/01/2020 | 19/02/2020 | 04/03/2020 | 0 | TK_Complete
LIFT1050 | TT_Task | Lift No.1 - Obtain Use Permit | 22/01/2020 | 30/01/2020 | 05/03/2020 | 12/03/2020 | 0 | TK_Complete
STCK0010 | TT_Task | Exhaust Stack - Further excavation from +4.2 mPD to the required formation level | 16/11/2017 | 17/11/2017 | 16/11/2017 | 17/11/2017 | 0 | TK_Complete
STCK0015 | TT_Task | Exhaust Stack - Cast blinding concrete | 10/01/2018 | 13/01/2018 | 13/12/2017 | 14/12/2017 | 0 | TK_Complete
STCK0020 | TT_Task | Exhaust Stack - Trim pile and prepare pile head | 29/09/2017 | 12/10/2017 | 26/09/2017 | 19/11/2017 | 0 | TK_Complete
STCK0030 | TT_Task | Exhaust Stack - Capping plate and rebar starter | 21/11/2017 | 29/11/2017 | 21/11/2017 | 08/12/2017 | 0 | TK_Complete
STCK0040 | TT_Task | Exhaust Stack - Erect side formwork | 06/01/2018 | 12/01/2018 | 21/12/2017 | 06/01/2018 | 0 | TK_Complete
STCK0050 | TT_Task | Exhaust Stack - Fix rebar and install cast-in /embed items | 15/01/2018 | 27/01/2018 | 21/12/2017 | 10/01/2018 | 0 | TK_Complete
STCK0060 | TT_Task | Exhaust Stack - Pour pile cap (incl' Lift Pit No.2) | 12/03/2018 | 12/03/2018 | 12/01/2018 | 12/01/2018 | 0 | TK_Complete
STCK0070 | TT_Task | Exhaust Stack - Strike formwork | 13/03/2018 | 13/03/2018 | 13/01/2018 | 13/01/2018 | 0 | TK_Complete
HRSG0015 | TT_Task | HRSG - Cast vertical blinding to the profile of caps and beams | 28/12/2017 | 02/01/2018 | 02/12/2017 | 08/12/2017 | 0 | TK_Complete
HRSG0020 | TT_Task | HRSG - Trim pile and prepare pile head | 24/11/2017 | 12/12/2017 | 26/09/2017 | 19/11/2017 | 0 | TK_Complete
HRSG0030 | TT_Task | HRSG - Capping plate and rebar starter | 25/11/2017 | 13/12/2017 | 29/09/2017 | 30/11/2017 | 0 | TK_Complete
HRSG0050 | TT_Task | HRSG - Fix rebar and install cast-in /embed items (Part 1 of 2) | 03/01/2018 | 12/01/2018 | 02/12/2017 | 13/01/2018 | 0 | TK_Complete
HRSG0060 | TT_Task | HRSG - Pour pile cap (Part 1 of 2) | 13/03/2018 | 13/03/2018 | 15/01/2018 | 15/01/2018 | 0 | TK_Complete
HRSG0070 | TT_Task | HRSG - Fix rebar and install cast-in /embed items (Part 2 of 2) | 13/03/2018 | 14/03/2018 | 24/01/2018 | 30/01/2018 | 0 | TK_Complete
HRSG0080 | TT_Task | HRSG - Pour pile cap (Part 2 of 2) | 15/03/2018 | 15/03/2018 | 31/01/2018 | 31/01/2018 | 0 | TK_Complete
PR010010 | TT_Task | Pipe Rack 01 - Foundation and Plinths | 09/04/2019 | 07/05/2019 | 23/02/2019 | 07/03/2019 | 0 | TK_Complete
DEF_WK06 | TT_Task | DW06 - Construct Metal Fence and Removal Shelter at Transformer Area | 10/01/2020 | 10/03/2020 | 15/10/2019 | 20/12/2019 | 0 | TK_Complete
EV039110 | TT_Task | Event 039(TX) - Power Island Phase 4 /5 resequencing amendment | 26/11/2018 | 25/12/2018 | 15/10/2018 | 12/11/2018 | 0 | TK_Complete
EV039120 | TT_Task | Event 039(TX) - BA8 consent for Phase 5 excavation [APPROVAL DEEMED] | 26/01/2019 | 22/02/2019 | 11/12/2018 | 07/01/2019 | 0 | TK_Complete
EV039210 | TT_Task | Event 039(TX) - MV Aux.TX / open cut to the required formation level w/ a berm 5m wide at Zone A north PPW | 26/01/2019 | 30/01/2019 | 30/11/2018 | 02/12/2018 | 0 | TK_Complete
EV039220 | TT_Task | Event 039(TX) - MV Aux.TX / conduct plate load test PL4 | 31/01/2019 | 15/02/2019 | 03/12/2018 | 13/12/2018 | 0 | TK_Complete
EV039230 | TT_Task | Event 039(TX) - MV Aux.TX / construct foundation CT11-FT1 (Part 1 of 2) | 16/02/2019 | 26/02/2019 | 14/12/2018 | 12/01/2019 | 0 | TK_Complete
EV039240 | TT_Task | Event 039(TX) - MV Aux.TX / construct pit wall to +6.15 and plinth PL3 | 27/02/2019 | 08/03/2019 | 13/01/2019 | 24/01/2019 | 0 | TK_Complete
EV039250 | TT_Task | Event 039(TX) - MV Aux.TX / construct fire wall to +11.55 and corbels at G.L.AA | 31/01/2019 | 20/02/2019 | 25/01/2019 | 04/02/2019 | 0 | TK_Complete
EV039260 | TT_Task | Event 039(TX) - MV Aux.TX / apply hardener | 01/04/2019 | 02/04/2019 | 16/02/2019 | 18/02/2019 | 0 | TK_Complete
EV039270 | TT_Mile | Event 039(TX) - MV Aux.TX / access for M&amp;E | 03/04/2019 | 03/04/2019 | 19/02/2019 | 19/02/2019 | 0 | TK_Complete
EV039310 | TT_Task | Event 039(TX) - Start-up TX / backfill to the required formation | 31/01/2019 | 04/02/2019 | 02/01/2019 | 07/01/2019 | 0 | TK_Complete
EV039320 | TT_Task | Event 039(TX) - Start-up TX / construct foundation CT12-FT1 | 26/01/2019 | 12/02/2019 | 12/01/2019 | 22/01/2019 | 0 | TK_Complete
EV039330 | TT_Task | Event 039(TX) - Start-up TX / construct plinth PL1 &amp; PL2 | 13/02/2019 | 22/02/2019 | 24/01/2019 | 30/01/2019 | 0 | TK_Complete
EV039340 | TT_Task | Event 039(TX) - Start-up TX / apply hardener | 01/04/2019 | 02/04/2019 | 12/02/2019 | 13/02/2019 | 0 | TK_Complete
EV039350 | TT_Mile | Event 039(TX) - Start-up TX / access for M&amp;E | 03/04/2019 | 03/04/2019 | 14/02/2019 | 14/02/2019 | 0 | TK_Complete
GNTX0010 | TT_Task | Generator TX - Further excavate from +4.2 to the required formation level | 04/02/2019 | 12/02/2019 | 07/01/2019 | 07/01/2019 | 0 | TK_Complete
GNTX0020 | TT_Task | Generator TX - Cast vertical blinding | 04/02/2019 | 14/02/2019 | 05/01/2019 | 07/01/2019 | 0 | TK_Complete
GNTX0030 | TT_Task | Generator TX - Construct base slabs | 15/02/2019 | 28/02/2019 | 08/01/2019 | 12/01/2019 | 0 | TK_Complete
GNTX0040 | TT_Task | Generator TX - Construct equipment plinths | 04/02/2019 | 13/02/2019 | 13/01/2019 | 25/01/2019 | 0 | TK_Complete
GNTX0050 | TT_Task | Generator TX - Construct concrete blast walls | 04/02/2019 | 20/02/2019 | 22/01/2019 | 12/02/2019 | 0 | TK_Complete
M&amp;E_WK08 | TT_Task | M&amp;E Works by Others #8 - Erect Transformers and dress out (indicative only) | 02/05/2019 | 31/08/2019 | 11/03/2019 | 14/10/2019 | 0 | TK_Complete
DBSG0010 | TT_Task | Duct Bank between Switchgear Blk &amp; Gen.TX - Construct drawpit BS01, BS03, BS04, BS05 | 08/03/2019 | 14/03/2019 | 12/10/2018 | 25/01/2019 | 0 | TK_Complete
DBSG0020 | TT_Task | Duct Bank between Switchgear Blk &amp; Gen.TX - Install cable ducting with concrete surround | 15/03/2019 | 28/03/2019 | 06/11/2018 | 12/02/2019 | 0 | TK_Complete
BBDP0010 | TT_Task | Boiler Blow Down Pit - Further excavate from +4.2 to the final formation level | 26/06/2018 | 28/06/2018 | 28/05/2018 | 02/06/2018 | 0 | TK_Complete
BBDP0070 | TT_Task | Boiler Blow Down Pit - Cast vertical blinding to the profile of base slab and shallow ppit | 02/08/2018 | 06/08/2018 | 04/07/2018 | 14/07/2018 | 0 | TK_Complete
BBDP0075 | TT_Task | Boiler Blow Down Pit - Install waterproofing | 26/07/2018 | 27/07/2018 | 12/07/2018 | 14/07/2018 | 0 | TK_Complete
BBDP0080 | TT_Task | Boiler Blow Down Pit - Fix bottom layer rebar | 28/07/2018 | 07/08/2018 | 16/07/2018 | 21/07/2018 | 0 | TK_Complete
BBDP0090 | TT_Task | Boiler Blow Down Pit - Close formwork (if any) | 03/09/2018 | 03/09/2018 | 09/08/2018 | 09/08/2018 | 0 | TK_Complete
BBDP0100 | TT_Task | Boiler Blow Down Pit - Pour base slab and shallow pit | 04/09/2018 | 04/09/2018 | 10/08/2018 | 10/08/2018 | 0 | TK_Complete
BBDP0110 | TT_Task | Boiler Blow Down Pit - Prepare CJ | 06/09/2018 | 06/09/2018 | 11/08/2018 | 11/08/2018 | 0 | TK_Complete
BBDP0140 | TT_Task | Boiler Blow Down Pit - Erect wall and column formwork | 27/08/2018 | 30/08/2018 | 26/07/2018 | 28/07/2018 | 0 | TK_Complete
BBDP0150 | TT_Task | Boiler Blow Down Pit - Fix upper layer rebar | 30/08/2018 | 01/09/2018 | 04/08/2018 | 07/08/2018 | 0 | TK_Complete
BBDP0160 | TT_Task | Boiler Blow Down Pit - Close wall formwork | 31/08/2018 | 03/09/2018 | 06/08/2018 | 09/08/2018 | 0 | TK_Complete
BBDP0170 | TT_Task | Boiler Blow Down Pit- Pour walls and columns to the underside of Feedwater Platform slab | 04/09/2018 | 04/09/2018 | 10/08/2018 | 10/08/2018 | 0 | TK_Complete
BBDP0180 | TT_Task | Boiler Blow Down Pit - Curing | 05/09/2018 | 11/09/2018 | 11/08/2018 | 17/08/2018 | 0 | TK_Complete
BBDP0190 | TT_Task | Boiler Blow Down Pit - Apply waterproofing to the external face of pit wall | 21/08/2018 | 23/08/2018 | 12/07/2018 | 14/07/2018 | 0 | TK_Complete
BBDP0200 | TT_Task | Boiler Blow Down Pit - Backfill againt basement wall | 26/07/2018 | 27/07/2018 | 30/06/2018 | 03/07/2018 | 0 | TK_Complete
EV015010 | TT_Task | Event 015 - HRSG West occupied by M&amp;E Contract for HRSG Erection | 23/04/2018 | 03/06/2018 | 07/03/2018 | 25/05/2018 | 0 | TK_Complete
EV015020 | TT_Task | Event 015 - Remob, excavation, earthing, backfill to formation levels, set-up for plate load test | 26/06/2018 | 10/07/2018 | 26/05/2018 | 09/06/2018 | 0 | TK_Complete
EV015030 | TT_Task | Event 015 - Clarification on plate load test requirements and invitation for BD inspection | 26/06/2018 | 26/06/2018 | 10/06/2018 | 20/06/2018 | 0 | TK_Complete
EV019010 | TT_Task | Event 019 - Plate Load Test Set Up | 28/02/2018 | 06/03/2018 | 09/02/2018 | 13/02/2018 | 0 | TK_Complete
EV019030 | TT_Task | Event 019 - Plate Load Test ( x2 nos) | 01/08/2018 | 14/08/2018 | 21/06/2018 | 25/06/2018 | 0 | TK_Complete
EV019040 | TT_Task | Event 019 - Photo records for foundation dimension set-out | 26/07/2018 | 29/07/2018 | 26/06/2018 | 29/06/2018 | 0 | TK_Complete
EV035010 | TT_Task | Event 035 - CLP allocated space for relocation of rebar yard | 26/07/2018 | 26/07/2018 | 16/07/2018 | 25/07/2018 | 0 | TK_Complete
EV040001 | TT_Mile | Event 040 - Balance of Feedwater Platform area handed back by KSS | 26/11/2018 | 26/11/2018 | 04/09/2018 | 04/09/2018 | 0 | TK_Complete
FWPT0010 | TT_Task | FW Platform - Construct base slab GL.K-S (= Pipe Bridge) | 26/07/2018 | 27/09/2018 | 30/06/2018 | 23/08/2018 | 0 | TK_Complete
FWPT0020 | TT_Task | FW Platform - Construct base slab GL.S-V (= Feedwater Platform) | 31/08/2018 | 11/10/2018 | 30/07/2018 | 08/10/2018 | 0 | TK_Complete
FWPT0030 | TT_Task | FW Platform - Construct plinths for FW Pump, Con.Recirculation Pump, Sampling Skid, Amonnia &amp; Phosphate Dosing Container | 27/08/2018 | 13/09/2018 | 24/08/2018 | 27/10/2018 | 0 | TK_Complete
FWPT0040 | TT_Task | FW Platform - Construct of remaining Feedwater Platform foundation and plinth | 26/11/2018 | 15/12/2018 | 15/11/2018 | 31/12/2018 | 0 | TK_Complete
APTX0010 | TT_Task | LV Aux. Power TX - Construct 600mm deep foundation | 01/04/2019 | 09/04/2019 | 29/01/2019 | 04/02/2019 | 0 | TK_Complete
EV047010 | TT_Task | RW Collection Pump Rm - Stratum Requirement (ROI#182) | 26/11/2018 | 12/12/2018 | 10/10/2018 | 26/10/2018 | 0 | TK_Complete
EV048010 | TT_Task | RW Collection Pump Rm - Install re-prop below S1 as per Zone A (4th) amendment | 16/02/2019 | 22/02/2019 | 05/12/2018 | 15/12/2018 | 0 | TK_Complete
RWPR0020 | TT_Task | RW Collection Pump Rm - Vertical blinding to the profile of base slab and shallow sump pit | 26/11/2018 | 28/11/2018 | 31/10/2018 | 31/10/2018 | 0 | TK_Complete
RWPR0030 | TT_Task | RW Collection Pump Rm - Install waterproofing [confirmed not required] | 26/11/2018 | 27/11/2018 | 31/10/2018 | 31/10/2018 | 0 | TK_Complete
RWPR0040 | TT_Task | RW Collection Pump Rm - Fix rebar for base slab and shallow pits | 28/11/2018 | 01/12/2018 | 01/11/2018 | 07/11/2018 | 0 | TK_Complete
RWPR0050 | TT_Task | RW Collection Pump Rm - Close formwork (if any) | 03/12/2018 | 03/12/2018 | 03/11/2018 | 07/11/2018 | 0 | TK_Complete
RWPR0060 | TT_Task | RW Collection Pump Rm - Pour base slab and shallow pit | 04/12/2018 | 04/12/2018 | 08/11/2018 | 08/11/2018 | 0 | TK_Complete
RWPR0070 | TT_Task | RW Collection Pump Rm - Prepare CJ | 28/11/2018 | 28/11/2018 | 09/11/2018 | 09/11/2018 | 0 | TK_Complete
RWPR0080 | TT_Task | RW Collection Pump Rm - Erect formwork for basement wall and staircase (Part 1 of 2) | 29/11/2018 | 03/12/2018 | 14/11/2018 | 16/11/2018 | 0 | TK_Complete
RWPR0090 | TT_Task | RW Collection Pump Rm - Fix rebar for basement wall and staircase (Part 1 of 2) | 01/12/2018 | 05/12/2018 | 16/11/2018 | 22/11/2018 | 0 | TK_Complete
RWPR0100 | TT_Task | RW Collection Pump Rm - Close wall formwork (Part 1 of 2) | 26/11/2018 | 26/11/2018 | 23/11/2018 | 28/11/2018 | 0 | TK_Complete
RWPR0110 | TT_Task | RW Collection Pump Rm - Pour basement wall and staircase (Part 1 of 2) | 28/01/2019 | 28/01/2019 | 29/11/2018 | 29/11/2018 | 0 | TK_Complete
RWPR0120 | TT_Task | RW Collection Pump Rm - Erect formwork for basement wall and staircase (Part 2 of 2) | 15/02/2019 | 19/02/2019 | 16/12/2018 | 23/12/2018 | 0 | TK_Complete
RWPR0130 | TT_Task | RW Collection Pump Rm - Fix rebar for basement wall and staircase (Part 2 of 2) | 18/02/2019 | 21/02/2019 | 21/12/2018 | 05/01/2019 | 0 | TK_Complete
RWPR0140 | TT_Task | RW Collection Pump Rm - Close wall formwork (Part 2 of 2) | 21/02/2019 | 22/02/2019 | 04/01/2019 | 06/01/2019 | 0 | TK_Complete
RWPR0150 | TT_Task | RW Collection Pump Rm - Pour basement wall and staircase (Part 2 of 2) | 23/02/2019 | 23/02/2019 | 07/01/2019 | 07/01/2019 | 0 | TK_Complete
RWPR0160 | TT_Task | RW Collection Pump Rm - Curing | 26/01/2019 | 01/02/2019 | 08/01/2019 | 14/01/2019 | 0 | TK_Complete
RWPR0170 | TT_Task | RW Collection Pump Rm - Apply waterproofing to the external face of basement wall [confirmed not required] | 01/04/2019 | 02/04/2019 | 29/11/2018 | 29/11/2018 | 0 | TK_Complete
RWPR0180 | TT_Task | RW Collection Pump Rm - Backfill againt basement wall | 04/02/2019 | 14/02/2019 | 17/12/2018 | 22/12/2018 | 0 | TK_Complete
RWPR0185 | TT_Task | RW Collection Pump Rm - Construct Irrigation Tank and Rainwater Collection Tank structure | 01/04/2019 | 27/05/2019 | 09/03/2019 | 17/08/2019 | 0 | TK_Complete
RWPR0190 | TT_Task | RW Collection Pump Rm - Falsework and formwork to top slab | 16/03/2019 | 18/03/2019 | 16/12/2018 | 23/12/2018 | 0 | TK_Complete
RWPR0200 | TT_Task | RW Collection Pump Rm - Fix rebar | 19/03/2019 | 21/03/2019 | 21/12/2018 | 05/01/2019 | 0 | TK_Complete
RWPR0210 | TT_Task | RW Collection Pump Rm - Pour top slab | 22/03/2019 | 22/03/2019 | 07/01/2019 | 07/01/2019 | 0 | TK_Complete
RWPR0220 | TT_Task | RW Collection Pump Rm - Construct remaining staircase structure abovehground | 16/09/2019 | 14/10/2019 | 19/08/2019 | 24/09/2019 | 0 | TK_Complete
RWPR0230 | TT_Task | RW Collection Pump Rm - Construct footing for Emergency Power Generator on top slab (relocated to adj. Shaft F) | 01/04/2019 | 18/04/2019 | 18/03/2019 | 02/07/2019 | 0 | TK_Complete
RWPR0240 | TT_Task | RW Collection Pump Rm - ABWF works to pump room and water tanks | 02/01/2020 | 17/02/2020 | 25/09/2019 | 31/12/2019 | 0 | TK_Complete
RWPR0250 | TT_Task | RW Collection Pump Rm - Building Services installation | 02/01/2020 | 17/02/2020 | 22/08/2019 | 24/01/2020 | 0 | TK_Complete
IRRI0010 | TT_Task | Irrigation System - Plant room installation inside RW Collection Pump Rm | 04/02/2020 | 12/03/2020 | 20/10/2019 | 24/01/2020 | 0 | TK_Complete
IRRI0015 | TT_Task | Irrigation System - Water supply pipeline from the water cabinet | 09/08/2019 | 05/09/2019 | 29/04/2019 | 30/09/2019 | 0 | TK_Complete
IRRI0020 | TT_Task | Irrigation System - Distribution pipeline installation along the east perimeter of HRSG Area | 02/01/2020 | 15/01/2020 | 19/12/2019 | 17/01/2020 | 0 | TK_Complete
IRRI0030 | TT_Task | Irrigation System - Distribution pipeline installation along the perimeter of Turbine Hall | 19/02/2020 | 03/03/2020 | 22/07/2019 | 18/12/2019 | 0 | TK_Complete
IRRI0040 | TT_Task | Irrigation System - Distribution pipeline installation to the northern side of HRSG Area | 15/01/2020 | 24/01/2020 | 15/01/2020 | 24/01/2020 | 0 | TK_Complete
EV041010 | TT_Task | Event 041 - Crane access for KSS (original thought was three months) | 26/11/2018 | 23/02/2019 | 07/09/2018 | 15/04/2019 | 0 | TK_Complete
GFFE0010 | TT_Task | Gas Final Filter Equip - Construct 1.1m deep foundation | 02/05/2019 | 27/05/2019 | 18/04/2019 | 04/05/2019 | 0 | TK_Complete
GFFE0020 | TT_Task | Gas Final Filter Equip - Construct 1m high bund wall all around | 05/06/2019 | 20/06/2019 | 06/05/2019 | 02/09/2019 | 0 | TK_Complete
GFFE0030 | TT_Task | Gas Final Filter Equip - Erect wire mesh security fence after filter install | 02/01/2020 | 15/01/2020 | 12/10/2019 | 18/10/2019 | 0 | TK_Complete
CCWS0010 | TT_Task | Close Cooling Water Structure - Construct foundation and plinths | 09/04/2019 | 29/04/2019 | 25/02/2019 | 04/03/2019 | 0 | TK_Complete
EV051010 | TT_FinMile | Event 051 / Utilities Trench / KSS hand back over the area | 26/01/2019 | 26/01/2019 | 04/01/2019 | 04/01/2019 | 0 | TK_Complete
ODPT0010 | TT_Task | Outdoor Pipe Trench - Construct pipe trench | 01/04/2019 | 13/04/2019 | 02/02/2019 | 14/02/2019 | 0 | TK_Complete
EV052010 | TT_FinMile | Event 052 / Foundation to the South of HRSG / KSS hand back over the area | 31/03/2019 | 31/03/2019 | 19/03/2019 | 19/03/2019 | 0 | TK_Complete
EV053010 | TT_FinMile | Event 053 / Foundation to the East of HRSG / KSS hand back over the area | 31/03/2019 | 31/03/2019 | 19/03/2019 | 19/03/2019 | 0 | TK_Complete
FTP10005 | TT_Task | Construct footings of False Start &amp; GT Water Tank to the South of HRSG | 01/04/2019 | 18/05/2019 | 20/03/2019 | 12/04/2019 | 0 | TK_Complete
FTP10010 | TT_Task | Construct footings of Urea Decomposition Chamber to the East of HRSG | 01/08/2019 | 26/08/2019 | 03/06/2019 | 29/06/2019 | 0 | TK_Complete
EV050010 | TT_FinMile | Event 050 / Gas Blending / KSS hand back over the area | 26/01/2019 | 26/01/2019 | 04/01/2019 | 04/01/2019 | 0 | TK_Complete
FTP20005 | TT_Task | Fuel Gas Purger Air, GRS &amp; Fuel Gas Blending - Underground drainage | 26/01/2019 | 15/02/2019 | 05/01/2019 | 16/01/2019 | 0 | TK_Complete
FTP20010 | TT_Task | Fuel Gas Purge Air System - Construct foundation | 16/02/2019 | 01/03/2019 | 17/01/2019 | 29/01/2019 | 0 | TK_Complete
FTP20020 | TT_Task | Gas Receiving &amp; Fuel Gas Blending Station - Construct foundation | 28/01/2019 | 09/02/2019 | 17/01/2019 | 29/01/2019 | 0 | TK_Complete
FTP20030 | TT_Task | Gas Receiving &amp; Fuel Gas Blending Station - Construct fire wall | 26/01/2019 | 08/02/2019 | 17/01/2019 | 29/01/2019 | 0 | TK_Complete
FTP20040 | TT_Task | Gas Receiving &amp; Fuel Gas Blending Station - Erect wire mech fence | 02/01/2020 | 11/01/2020 | 28/10/2019 | 30/10/2019 | 0 | TK_Complete
EV049010 | TT_FinMile | Event 049 / Urea Facilities / KSS hand back over the area | 26/01/2019 | 26/01/2019 | 08/12/2018 | 08/12/2018 | 0 | TK_Complete
EV049020 | TT_Task | Event 049 / Urea Facilities / Set up and conduct plate load test no. PL1 | 26/01/2019 | 26/01/2019 | 09/12/2018 | 13/12/2018 | 0 | TK_Complete
FTP30010 | TT_Task | Construct footings for Chemical Unloading Bay and Urea Factilities | 26/01/2019 | 22/02/2019 | 14/12/2018 | 11/01/2019 | 0 | TK_Complete
CLPCCR10 | TT_Task | Works in Existing Central Control Room in Control Block Building and Associated Works (indicative only, TBC) | 03/02/2020 | 22/02/2020 | 03/02/2020 | 22/02/2020 | 0 | TK_Complete
DEF_WK09 | TT_Task | DW09 - Construct UG Neutralization Tank | 26/11/2018 | 31/12/2018 | 15/11/2018 | 31/12/2018 | 0 | TK_Complete
DEF_WK10 | TT_Task | DW10 - Final Reinstatement of Access Roads and Pavement at Turbine Hall and HRSG Area (i.e. wearing course) | 23/05/2020 | 28/05/2020 | 23/05/2020 | 28/05/2020 | 0 | TK_Complete
13584 | TT_Task | Provide/Extend/Relocate Sitewide Drainage System | 01/04/2019 | 13/08/2019 | 16/07/2018 | 24/01/2020 | 0 | TK_Complete
EXCL0020 | TT_Task | Roadworks - Concrete Pavements | 01/08/2019 | 20/09/2019 | 22/07/2019 | 09/09/2019 | 0 | TK_Complete
EXCL0030 | TT_Task | Roadworks - Road Marking and signs | 04/06/2020 | 11/06/2020 | 04/06/2020 | 11/06/2020 | 0 | TK_Complete
EXCL0040 | TT_Task | Roadworks - Install Directonal Signage | 12/06/2020 | 30/06/2020 | 12/06/2020 | 30/06/2020 | 0 | TK_Complete
EXCL0050 | TT_Task | Roadworks - Install Street Furniture | 12/06/2020 | 30/06/2020 | 12/06/2020 | 30/06/2020 | 0 | TK_Complete
LAND0010 | TT_Task | Irrigation Points | 01/02/2020 | 14/02/2020 | 01/02/2020 | 14/02/2020 | 0 | TK_Complete
LAND0020XX | TT_Task | Grasscrete Around Building | 02/01/2020 | 12/02/2020 | 22/07/2019 | 18/12/2019 | 0 | TK_Complete
EV057010 | TT_FinMile | Event 057 /Utility and Gas Trenches - Chimney Road closed with TTM implemented | 26/01/2019 | 26/01/2019 | 08/12/2018 | 08/12/2018 | 0 | TK_Complete
EV057020 | TT_Mile | Event 057 /Utility and Gas Trenches - Excavation permit issued | 26/01/2019 | 26/01/2019 | 12/12/2018 | 12/12/2018 | 0 | TK_Complete
PTA10010 | TT_Task | Utility and Gas Trenches (as per drawing ref. BPB /OARU /GA /1 /VAA /D1 /161 Rev.4) | 26/01/2019 | 13/04/2019 | 12/12/2018 | 14/02/2019 | 0 | TK_Complete
PTA10020 | TT_Task | Sleeperways (as per drawing ref. BPB /OARU /GA /1 /VAA /D1 /161 Rev.4) | 01/08/2019 | 20/08/2019 | 06/07/2019 | 22/08/2019 | 0 | TK_Complete
A1010 | TT_Mile | Date for Commencement of the Works | 30/11/2017 | 30/11/2017 | 22/09/2017 | 22/09/2017 | 0 | TK_Complete
SC1040 | TT_FinMile | Section 04 - Completion of grouting required for the foundations and support for shaftline equipment | 09/05/2019 | 09/05/2019 | 07/03/2019 | 07/03/2019 | 0 | TK_Complete
SC1060-1 | TT_FinMile | Section 06.1 - Completion of TOP'S and successfully pass TOP Tests for Generator &amp; Auxiliaries Systems | 31/12/2019 | 31/12/2019 | 20/11/2019 | 20/11/2019 | 0 | TK_Complete
SC1060-2 | TT_FinMile | Section 06.2 - Completion of TOP'S and successfully pass TOP Tests for Gas Turbine &amp; Auxiliaries | 17/12/2019 | 17/12/2019 | 21/11/2019 | 21/11/2019 | 0 | TK_Complete
SC1070 | TT_FinMile | Section 07 - Completion of TOP'S and successfully pass TOP Tests for Steam Turbine &amp; Auxiliaries | 28/03/2020 | 28/03/2020 | 28/03/2020 | 28/03/2020 | 0 | TK_Complete
SC1080 | TT_FinMile | Section 08 - Completion of TOP'S and successfully pass TOP Tests for Circulating Water Area | 08/04/2020 | 08/04/2020 | 17/12/2019 | 17/12/2019 | 0 | TK_Complete
SC1110 | TT_FinMile | Section 11 - Mechanical Completion 100% of TOP and pass TOP tests, for piping systems to allow chemical clean of HRSG | 11/12/2019 | 11/12/2019 | 30/11/2019 | 30/11/2019 | 0 | TK_Complete
SC1120 | TT_FinMile | Section 12 - Completion of the HRSG systems, incl. all tests to prove integrity of the HRSG | 30/11/2019 | 30/11/2019 | 30/11/2019 | 30/11/2019 | 0 | TK_Complete
SC1160 | TT_FinMile | Section 16 - Mechanical Completion of gas supply pipework with the issuance of the User App. from GSO | 28/03/2020 | 28/03/2020 | 28/11/2019 | 28/11/2019 | 0 | TK_Complete
SC1170 | TT_FinMile | Section 17 - Mechanical Completion of 100% of TOP and successfully pass TOP Tests for all piping systems and Module Skid | 28/03/2020 | 28/03/2020 | 15/02/2020 | 15/02/2020 | 0 | TK_Complete
SC1180 | TT_FinMile | Section 18 - Completion of the following TOP's and pass TOP test (refer to list) | 02/12/2019 | 02/12/2019 | 20/11/2019 | 20/11/2019 | 0 | TK_Complete
SC1190 | TT_FinMile | Section 19 - Completion of Installation of 100% of TOP and successfully pass TOP Tests for EC&amp;I systems | 28/03/2020 | 28/03/2020 | 15/02/2020 | 15/02/2020 | 0 | TK_Complete
SC1200 | TT_FinMile | Section 20 - Completion of all terminations of 6.6kV system and construction completion of the generator isolated ph.BD | 28/03/2020 | 28/03/2020 | 27/11/2019 | 27/11/2019 | 0 | TK_Complete
SC1210 | TT_FinMile | Section 21 - Completion of all works and TOP's to enable back-energization from CLP 400kV System | 06/12/2019 | 06/12/2019 | 20/11/2019 | 20/11/2019 | 0 | TK_Complete
SC1220 | TT_FinMile | Section 22 - Construction Completion of CO2 systems including completion of NFPA leakage test | 14/04/2020 | 14/04/2020 | 06/01/2020 | 06/01/2020 | 0 | TK_Complete
SC1230 | TT_FinMile | Section 23 - Completion of all TOP's associated with works and successfully pass TOP tests | 14/04/2020 | 14/04/2020 | 20/01/2020 | 20/01/2020 | 0 | TK_Complete
SC1240 | TT_FinMile | Section 24 - Completion of all completion documentation | 14/04/2020 | 14/04/2020 | 15/06/2020 | 15/06/2020 | 0 | TK_Complete
SC1250 | TT_FinMile | Section 25 - Completion of all support to OEM during cold commissioning to allow first fire and first steam blow | 14/04/2020 | 14/04/2020 | 20/01/2020 | 20/01/2020 | 0 | TK_Complete
SC1260 | TT_FinMile | Section 26 - Completion of all support to the OEM during hot commissioning and testing to allow commencement of operate | 24/06/2020 | 24/06/2020 | 30/06/2020 | 30/06/2020 | 0 | TK_Complete
SC1350 | TT_FinMile | Section 20 - Partial 6.6Kv Ready for Station Feed | 31/08/2019 | 31/08/2019 | 17/08/2019 | 17/08/2019 | 0 | TK_Complete
SC1010-1 | TT_FinMile | Section 01.1 - Completion of the submission of unpriced PO to confirm the placement of Crane barge(s) &gt; 300t | 12/02/2018 | 12/02/2018 | 12/01/2018 | 12/01/2018 | 0 | TK_Complete
SC1010-2 | TT_FinMile | Section 01.2 - Completion of the submission of unpriced PO to confirm the placement of Land based cranes (50-300T) | 12/02/2018 | 12/02/2018 | 15/01/2018 | 15/01/2018 | 0 | TK_Complete
SC1020-1 | TT_FinMile | Section 02.1 - Completion of submission of Insurance certificates and policy documentation | 15/02/2018 | 15/02/2018 | 17/11/2017 | 17/11/2017 | 0 | TK_Complete
SC1020-2 | TT_FinMile | Section 02.2 - Completion of submission of Construction Execution Plan | 15/02/2018 | 15/02/2018 | 17/11/2017 | 17/11/2017 | 0 | TK_Complete
SC1020-3 | TT_FinMile | Section 02.3 - Completion of submission of SHE Plans | 15/02/2018 | 15/02/2018 | 17/11/2017 | 17/11/2017 | 0 | TK_Complete
SC1020-4 | TT_FinMile | Section 02.4 - Completion of submission of Material Management Plan | 15/02/2018 | 15/02/2018 | 11/01/2018 | 11/01/2018 | 0 | TK_Complete
SC1020-5 | TT_FinMile | Section 02.5 - Completion of submission of Project Quality Plan, Quality Assurance System Manual, etc | 15/02/2018 | 15/02/2018 | 08/01/2018 | 08/01/2018 | 0 | TK_Complete
SC1030 | TT_FinMile | Section 03 - Completion of Mobilization of the crane barge to site, necessary to commence lifting | 01/03/2018 | 01/03/2018 | 15/03/2018 | 15/03/2018 | 0 | TK_Complete
SC1050 | TT_FinMile | Section 05 - Completion of alignment checks of Steam Turbines, Generator, Compressor/ Gas Turbine | 09/05/2019 | 09/05/2019 | 12/04/2019 | 12/04/2019 | 0 | TK_Complete
SC1090 | TT_FinMile | Section 09 - Mechanical Completion of the HRSG Supporting frames: Structure Ready for loading of Module HRSG | 26/07/2018 | 26/07/2018 | 26/07/2018 | 26/07/2018 | 0 | TK_Complete
SC1100 | TT_FinMile | Section 10 - Mech. Compl. of all PP incl. Heating Modules, drums, evaporators. - HRSG Ready for HP Piping | 31/10/2018 | 31/10/2018 | 24/10/2018 | 24/10/2018 | 0 | TK_Complete
SC1130 | TT_FinMile | Section 13 - Construction Completion of the Steam Turbine Drain Skid MAL00Y | 29/09/2018 | 29/09/2018 | 22/09/2018 | 22/09/2018 | 0 | TK_Complete
SC1140 | TT_FinMile | Section 14 - Construction completion of the Module Pipe Racks UMCM1Y &amp; UMCL1Y | 12/04/2019 | 12/04/2019 | 30/03/2019 | 30/03/2019 | 0 | TK_Complete
SC1150 | TT_FinMile | Section 15 A - Construction completion of the condenser and cooling water connection to the Bonna cooling water pipes | 02/12/2019 | 02/12/2019 | 14/11/2019 | 14/11/2019 | 0 | TK_Complete
SC1270 | TT_FinMile | New Section A (Formerly Sec. 20) 6.6Kv Completion | 09/09/2019 | 09/09/2019 | 17/08/2019 | 17/08/2019 | 0 | TK_Complete
SC1280 | TT_FinMile | New Section B (Formerly Sec. 11 &amp; 12) Chemical Cleaning | 30/11/2019 | 30/11/2019 | 22/11/2019 | 22/11/2019 | 0 | TK_Complete
SC1290 | TT_FinMile | New Section C (Formerly Sec. 18 &amp; 21) Back Energization | 06/12/2019 | 06/12/2019 | 20/11/2019 | 20/11/2019 | 0 | TK_Complete
SC1300 | TT_FinMile | New Section D (Formerly Sec. 6A, 6B, 7, 8, 16, 17,19, 22 &amp; 23) Pre-mechanical completion (Initial fire) | 14/04/2020 | 14/04/2020 | 29/03/2020 | 29/03/2020 | 0 | TK_Complete
SC1310 | TT_FinMile | New Section E (Formerly Sec. 24) Documentation complete | 14/04/2020 | 14/04/2020 | 16/06/2020 | 16/06/2020 | 0 | TK_Complete
SC1320 | TT_FinMile | New Section F (Formerly Sec. 25) Mechanical Completion (Cold commissioning) | 14/04/2020 | 14/04/2020 | 21/01/2020 | 21/01/2020 | 0 | TK_Complete
SC1330 | TT_FinMile | New Section G (Formerly Sec. 26) Commercial operation (Hot Commissioning) | 14/04/2020 | 14/04/2020 | 01/07/2020 | 01/07/2020 | 0 | TK_Complete
SC1340 | TT_FinMile | Section 15 B - Demin Water Available | 10/07/2019 | 10/07/2019 | 22/05/2019 | 22/05/2019 | 0 | TK_Complete
TOP1030 | TT_FinMile | (TOP-10BZL-03) L&amp;SP Incl. BMZ in UBA and UBF and UBE | 17/12/2019 | 17/12/2019 | 05/02/2020 | 05/02/2020 | 0 | TK_Complete
TOP1040 | TT_FinMile | (TOP-10CY) Communication / Security Systems 10 (Is it same as TOP-00CY-02 and TOP-00CY-01) | 31/12/2019 | 31/12/2019 | 19/01/2020 | 19/01/2020 | 0 | TK_Complete
TOP1060 | TT_FinMile | (TOP-10GM-03) Plant Drainage System Pump for UGD (incl. UGU) | 03/04/2020 | 03/04/2020 | 20/12/2019 | 20/12/2019 | 0 | TK_Complete
TOP1070 | TT_FinMile | (TOP-10GHD-02) Service Water Distribution Inside Power Block | 30/03/2020 | 30/03/2020 | 21/02/2020 | 21/02/2020 | 0 | TK_Complete
TOP1080 | TT_FinMile | (TOP-10GKB-02) Drinking Water Distribution Inside Power Block | 30/03/2020 | 30/03/2020 | 21/02/2020 | 21/02/2020 | 0 | TK_Complete
TOP1090 | TT_FinMile | (TOP-10GM-02) Plant Drainage System for 10U MC *LCAL | 17/12/2019 | 17/12/2019 | 20/12/2019 | 20/12/2019 | 0 | TK_Complete
TOP1100 | TT_FinMile | (TOP-10MA-01) HP / IP / LP Turbine 10MAA/MAB/MAC | 17/12/2019 | 17/12/2019 | 16/11/2019 | 16/11/2019 | 0 | TK_Complete
TOP1110 | TT_FinMile | (TOP-10MAD) ST Bearing System | 18/09/2019 | 18/09/2019 | 06/09/2019 | 06/09/2019 | 0 | TK_Complete
TOP1120 | TT_FinMile | (TOP-10MAL) ST Drain System | 11/11/2019 | 11/11/2019 | 11/11/2019 | 11/11/2019 | 0 | TK_Complete
TOP1130 | TT_FinMile | (TOP-10MAN) ST Bypass System | 21/10/2019 | 21/10/2019 | 26/10/2019 | 26/10/2019 | 0 | TK_Complete
TOP1140 | TT_FinMile | (TOP-10MA-02) HP / IP / LP Steam Turbine Emergency Stop Valves and Control Valves | 04/11/2019 | 04/11/2019 | 09/11/2019 | 09/11/2019 | 0 | TK_Complete
TOP1150 | TT_FinMile | (TOP-10MAG) Condensing System | 11/11/2019 | 11/11/2019 | 14/11/2019 | 14/11/2019 | 0 | TK_Complete
TOP1160 | TT_FinMile | (TOP-10MAV) Lube and Lifting Oil system Incl. Generator and GT(10MAV01_16Aug19 / 10MAV02_05Sep19 / 10MAV03_27Mar20) | 05/09/2019 | 05/09/2019 | 27/03/2020 | 27/03/2020 | 0 | TK_Complete
TOP1170 | TT_FinMile | (TOP-10MAW) Gland / Leakage Steam System | 21/10/2019 | 21/10/2019 | 26/10/2019 | 26/10/2019 | 0 | TK_Complete
TOP1180 | TT_FinMile | (TOP-10MAX) ST Hydraulic System | 21/10/2019 | 21/10/2019 | 12/10/2019 | 12/10/2019 | 0 | TK_Complete
TOP1190 | TT_FinMile | (TOP-10QFB) Control Air System for ST (10QFB01_11Nov19 / 10QFB02_05Dec19 / 10QFB03_12Feb20) | 11/11/2019 | 11/11/2019 | 12/02/2020 | 12/02/2020 | 0 | TK_Complete
TOP1200 | TT_FinMile | (TOP-10MKA) Generator Incl. Bearing System 10MKD | 11/11/2019 | 11/11/2019 | 18/11/2019 | 18/11/2019 | 0 | TK_Complete
TOP1210 | TT_FinMile | (TOP-10MKF) Generator Primary Water Cooling System | 28/10/2019 | 28/10/2019 | 25/10/2019 | 25/10/2019 | 0 | TK_Complete
TOP1220 | TT_FinMile | (TOP-10MKG) Hydrogen Gas Supply System | 08/11/2019 | 08/11/2019 | 01/11/2019 | 01/11/2019 | 0 | TK_Complete
TOP1230 | TT_FinMile | (TOP-10MKQ) Waste Gas System | 14/10/2019 | 14/10/2019 | 03/10/2019 | 03/10/2019 | 0 | TK_Complete
TOP1240 | TT_FinMile | (TOP-10MKW) Seal Oil Supply System | 24/09/2019 | 24/09/2019 | 26/08/2019 | 26/08/2019 | 0 | TK_Complete
TOP1250 | TT_FinMile | (TOP-10MBV) GT Lube Oil / Lifting Oil System | 17/09/2019 | 17/09/2019 | 06/09/2019 | 06/09/2019 | 0 | TK_Complete
TOP1260 | TT_FinMile | (TOP-10MBA) GT Including Combustion Chamber | 21/11/2019 | 21/11/2019 | 21/11/2019 | 21/11/2019 | 0 | TK_Complete
TOP1270 | TT_FinMile | (TOP-10MBX) GT Hydraulic Oil | 14/10/2019 | 14/10/2019 | 28/10/2019 | 28/10/2019 | 0 | TK_Complete
TOP1280 | TT_FinMile | (TOP-10MBP) GT Natural Gas incl. Draining System MBP40 | 05/11/2019 | 05/11/2019 | 21/11/2019 | 21/11/2019 | 0 | TK_Complete
TOP1290 | TT_FinMile | (TOP-10MBN) GT Fuel Oil Injection System | 11/11/2019 | 11/11/2019 | 05/11/2019 | 05/11/2019 | 0 | TK_Complete
TOP1300 | TT_FinMile | (TOP-10MBH) GT Cooling Air System | 23/09/2019 | 23/09/2019 | 23/09/2019 | 23/09/2019 | 0 | TK_Complete
TOP1310 | TT_FinMile | (TOP-10MBA18) Compressor Cleaning Package | 23/09/2019 | 23/09/2019 | 13/09/2019 | 13/09/2019 | 0 | TK_Complete
TOP1320 | TT_FinMile | (TOP-10MBA5x) GT Hydraulic Clearance Optimization Supply System | 16/10/2019 | 16/10/2019 | 23/08/2019 | 23/08/2019 | 0 | TK_Complete
TOP1330 | TT_FinMile | (TOP-10MBX2x) GT Pneumatic System | 14/10/2019 | 14/10/2019 | 29/09/2019 | 29/09/2019 | 0 | TK_Complete
TOP1340 | TT_FinMile | (TOP-10MBA4X) Blow Off System | 14/10/2019 | 14/10/2019 | 12/10/2019 | 12/10/2019 | 0 | TK_Complete
TOP1350 | TT_FinMile | (TOP-00QFB) Instrument Air Distribution system | 11/11/2019 | 11/11/2019 | 29/11/2019 | 29/11/2019 | 0 | TK_Complete
TOP1360 | TT_FinMile | (TOP-10MBL) Air Intake System | 21/10/2019 | 21/10/2019 | 10/10/2019 | 10/10/2019 | 0 | TK_Complete
TOP1370 | TT_FinMile | (TOP-10MBU) GT NOX Water Injection System (10MBU01_12Oct19 /10MBU02_17Oct19) | 14/10/2019 | 14/10/2019 | 17/10/2019 | 17/10/2019 | 0 | TK_Complete
TOP1380 | TT_FinMile | (TOP-10SAM30) Ventilation System for GT Enclosure and Skid Enclosures | 15/11/2019 | 15/11/2019 | 02/11/2019 | 02/11/2019 | 0 | TK_Complete
TOP1390 | TT_FinMile | (TOP-10SGJ-02) FF CO2 System CYE/SGJ for GT Noise Enclosure and Gas Skid | 07/04/2020 | 07/04/2020 | 06/01/2020 | 06/01/2020 | 0 | TK_Complete
TOP1400 | TT_FinMile | (TOP-10CYQ) Gas Detection System | 15/04/2020 | 15/04/2020 | 09/01/2020 | 09/01/2020 | 0 | TK_Complete
TOP1410 | TT_FinMile | (TOP-10LCA) Main Condensate Pumps and Supply system for Min. Flow Operation | 30/03/2020 | 30/03/2020 | 28/11/2019 | 28/11/2019 | 0 | TK_Complete
TOP1420 | TT_FinMile | (TOP-10PGB) CCW System | 21/10/2019 | 21/10/2019 | 30/09/2019 | 30/09/2019 | 0 | TK_Complete
TOP1430 | TT_FinMile | (TOP-10PCB) Service Cooling Water System Incl. 10PDB | 30/03/2020 | 30/03/2020 | 02/01/2020 | 02/01/2020 | 0 | TK_Complete
TOP1440 | TT_FinMile | (TOP-10PAB-02) Circulating Water System - Power Island Part | 30/03/2020 | 30/03/2020 | 21/12/2019 | 21/12/2019 | 0 | TK_Complete
TOP1460 | TT_FinMile | (TOP-00SCA) Compressed Air Station | 01/11/2019 | 01/11/2019 | 11/10/2019 | 11/10/2019 | 0 | TK_Complete
TOP1470 | TT_FinMile | (TOP-10SGA) FF Indoor Hydrants 10SGA Inside 10ULA, 10UHA, 10UMC | 09/04/2020 | 09/04/2020 | 18/01/2020 | 18/01/2020 | 0 | TK_Complete
TOP1480 | TT_FinMile | (TOP-10SGC-02) FF Spray Deluge System 10SGC for Lube Oil / Seal Oil System | 09/04/2020 | 09/04/2020 | 15/01/2020 | 15/01/2020 | 0 | TK_Complete
TOP1490 | TT_FinMile | (TOP-10BBA) MV Switchgear 10BBA | 31/07/2019 | 31/07/2019 | 19/07/2019 | 19/07/2019 | 0 | TK_Complete
TOP1500 | TT_FinMile | (TOP-10BF) LV Switchgear 10BFE/10BMA | 03/06/2019 | 03/06/2019 | 29/07/2019 | 29/07/2019 | 0 | TK_Complete
TOP1520 | TT_FinMile | (TOP-10BT) DC-SWITCHGEAR 10BU | 29/07/2019 | 29/07/2019 | 29/07/2019 | 29/07/2019 | 0 | TK_Complete
TOP1530 | TT_FinMile | (TOP-10CHA) Generator Protection 10CHA | 16/09/2019 | 16/09/2019 | 12/08/2019 | 12/08/2019 | 0 | TK_Complete
TOP1560 | TT_FinMile | (TOP-10CJ) Automation System 10CJ | 17/10/2019 | 17/10/2019 | 17/08/2019 | 17/08/2019 | 0 | TK_Complete
TOP1570 | TT_FinMile | (TOP-10CP-AA) ET200 Stations in Function Area 10 Auxiliary and Ancillary | 11/11/2019 | 11/11/2019 | 17/08/2019 | 17/08/2019 | 0 | TK_Complete
TOP1580 | TT_FinMile | (TOP-10CP-HR) ET200 Stations in Function Area 10 HRSG | 04/09/2019 | 04/09/2019 | 04/09/2019 | 04/09/2019 | 0 | TK_Complete
TOP1590 | TT_FinMile | (TOP-10CP-WS) ET200 Stations in Function Area 10 Water / Steam Cycle | 02/09/2019 | 02/09/2019 | 17/08/2019 | 17/08/2019 | 0 | TK_Complete
TOP1620 | TT_FinMile | (TOP-10CP-ST) ET200 Stations in Function Area 10ST | 06/09/2019 | 06/09/2019 | 15/08/2019 | 15/08/2019 | 0 | TK_Complete
TOP1640 | TT_FinMile | (TOP-10CP-GT) ET200 Stations in Function Area 10GT | 12/09/2019 | 12/09/2019 | 08/08/2019 | 08/08/2019 | 0 | TK_Complete
TOP1650 | TT_FinMile | (TOP-10SGJ-01) FF CO2 System for PCC 10SGJ | 15/04/2020 | 15/04/2020 | 06/01/2020 | 06/01/2020 | 0 | TK_Complete
TOP1660 | TT_FinMile | (TOP-10BAT) Main Transformer 10BAT01/10BBT01 | 16/09/2019 | 16/09/2019 | 17/08/2019 | 17/08/2019 | 0 | TK_Complete
TOP1670 | TT_FinMile | (TOP-10GM-01) Plant Drainage System for 10UBE/10UBF | 04/11/2019 | 04/11/2019 | 22/11/2019 | 22/11/2019 | 0 | TK_Complete
TOP1680 | TT_FinMile | (TOP-10MKC) SEE/SFC Equipment, Excitation Transformer MKC; SFC Transformer MBJ | 28/10/2019 | 28/10/2019 | 25/10/2019 | 25/10/2019 | 0 | TK_Complete
TOP1690 | TT_FinMile | (TOP-10SGC-01) FF Spray Deluge System for BAT/ BBT SGC | 14/04/2020 | 14/04/2020 | 18/03/2020 | 18/03/2020 | 0 | TK_Complete
TOP1700 | TT_FinMile | (TOP-10LD) Condensate Polishing Plant | 30/03/2020 | 30/03/2020 | 15/02/2020 | 15/02/2020 | 0 | TK_Complete
TOP1710 | TT_FinMile | (TOP-10LDK) Condensate Polishing System | 11/11/2019 | 11/11/2019 | 26/11/2019 | 26/11/2019 | 0 | TK_Complete
TOP1720 | TT_FinMile | (TOP-10BA) Isolated Generator Busduct 10BAA Incl. 10BAB, BAC | 13/11/2019 | 13/11/2019 | 05/11/2019 | 05/11/2019 | 0 | TK_Complete
TOP1730 | TT_FinMile | (TOP-00XKA) Emergency Diesel Generator Set | 07/11/2019 | 07/11/2019 | 22/11/2019 | 22/11/2019 | 0 | TK_Complete
TOP1740 | TT_FinMile | (TOP-00SGM) FF Protection System for UBN | 02/04/2020 | 02/04/2020 | 13/03/2020 | 13/03/2020 | 0 | TK_Complete
TOP1750 | TT_FinMile | (TOP-10BFT01) LV Transformer BFT01 (BHT) | 16/09/2019 | 16/09/2019 | 18/09/2019 | 18/09/2019 | 0 | TK_Complete
TOP1760 | TT_FinMile | (TOP-10BFT02) LV Transformer BFT02 (BHT) | 09/09/2019 | 09/09/2019 | 29/08/2019 | 29/08/2019 | 0 | TK_Complete
TOP1770 | TT_FinMile | (TOP-10BBT) MV Transformer BBT01 | 13/09/2019 | 13/09/2019 | 07/09/2019 | 07/09/2019 | 0 | TK_Complete
TOP1790 | TT_FinMile | (TOP-10MBR) GT Exhaust Gas System | 18/11/2019 | 18/11/2019 | 01/11/2019 | 01/11/2019 | 0 | TK_Complete
TOP1800 | TT_FinMile | (TOP-10EK) FUEL GAS SUPPLY SYSTEM FOR GT10 | 30/03/2020 | 30/03/2020 | 09/01/2020 | 09/01/2020 | 0 | TK_Complete
TOP1810 | TT_FinMile | (TOP-10BZL-02) L&amp;SP incl. BMZ at 10UHA Area | 30/03/2020 | 30/03/2020 | 05/02/2020 | 05/02/2020 | 0 | TK_Complete
TOP1820 | TT_FinMile | (TOP-10CFE) CEMS | 31/03/2020 | 31/03/2020 | 06/01/2020 | 06/01/2020 | 0 | TK_Complete
TOP1830 | TT_FinMile | (TOP-10HAD10) HRSG HP Steam | 18/11/2019 | 18/11/2019 | 22/11/2019 | 22/11/2019 | 0 | TK_Complete
TOP1840 | TT_FinMile | (TOP-10HAD50) HRSG IP Steam | 07/11/2019 | 07/11/2019 | 22/11/2019 | 22/11/2019 | 0 | TK_Complete
TOP1850 | TT_FinMile | (TOP-10HAD80) HRSG LP Steam | 18/11/2019 | 18/11/2019 | 22/11/2019 | 22/11/2019 | 0 | TK_Complete
TOP1860 | TT_FinMile | (TOP-10HAA) HRSG Condensate Preheating System | 11/11/2019 | 11/11/2019 | 11/11/2019 | 11/11/2019 | 0 | TK_Complete
TOP1870 | TT_FinMile | (TOP-10HBK) HRSG Exhaust Gas System | 08/11/2019 | 08/11/2019 | 21/11/2019 | 21/11/2019 | 0 | TK_Complete
TOP1880 | TT_FinMile | (TOP-00LBG) Auxiliary Steam System Common Area | 06/11/2019 | 06/11/2019 | 26/11/2019 | 26/11/2019 | 0 | TK_Complete
TOP1890 | TT_FinMile | (TOP-10GM-02) Plant Drainage System for 10U HW | 07/04/2020 | 07/04/2020 | 20/12/2019 | 20/12/2019 | 0 | TK_Complete
TOP1900 | TT_FinMile | (TOP-10LBH) Start-up and Shutdown Steam System incl. Drains System | 04/11/2019 | 04/11/2019 | 19/11/2019 | 19/11/2019 | 0 | TK_Complete
TOP1910 | TT_FinMile | (TOP-10LCL) HRSG Drains System | 07/11/2019 | 07/11/2019 | 15/11/2019 | 15/11/2019 | 0 | TK_Complete
TOP1920 | TT_FinMile | (TOP-10LCA-02) Condensate Supply System incl. Preheater 10HAA10 | 11/11/2019 | 11/11/2019 | 11/11/2019 | 11/11/2019 | 0 | TK_Complete
TOP1930 | TT_FinMile | (TOP-10LAB) HP/IP Feedwater Supply System | 11/11/2019 | 11/11/2019 | 04/11/2019 | 04/11/2019 | 0 | TK_Complete
TOP1940 | TT_FinMile | (TOP-10LAC) Feedwater Pump | 11/11/2019 | 11/11/2019 | 14/11/2019 | 14/11/2019 | 0 | TK_Complete
TOP1950 | TT_FinMile | (TOP-10QCB) Hydrazine Dosing QC | 11/11/2019 | 11/11/2019 | 26/11/2019 | 26/11/2019 | 0 | TK_Complete
TOP1960 | TT_FinMile | (TOP-10QCC) Trisodiumphosphate Dosing QC | 07/04/2020 | 07/04/2020 | 03/12/2019 | 03/12/2019 | 0 | TK_Complete
TOP1970 | TT_FinMile | (TOP-10QCD) Ammonia Dosing QC | 07/04/2020 | 07/04/2020 | 03/12/2019 | 03/12/2019 | 0 | TK_Complete
TOP1980 | TT_FinMile | (TOP-10QU) Sampling Container QU | 07/04/2020 | 07/04/2020 | 20/01/2020 | 20/01/2020 | 0 | TK_Complete
TOP2000 | TT_FinMile | (TOP-10HSJ) Reduction Agent Supply System for SCR | 13/04/2020 | 13/04/2020 | 19/01/2020 | 19/01/2020 | 0 | TK_Complete
TOP2010 | TT_FinMile | (TOP-10EKT20) Fuel Gas Preheating System 10EKT20 | 11/11/2019 | 11/11/2019 | 27/11/2019 | 27/11/2019 | 0 | TK_Complete
TOP2020 | TT_FinMile | (TOP-10GHC) Demineralised Water Distribution System Inside 10UMC | 30/09/2019 | 30/09/2019 | 12/09/2019 | 12/09/2019 | 0 | TK_Complete
TOP2050 | TT_FinMile | (TOP-10LBA10) HP Main Steam System | 05/11/2019 | 05/11/2019 | 28/11/2019 | 28/11/2019 | 0 | TK_Complete
TOP2060 | TT_FinMile | (TOP-10LBA80) LP Main Steam System | 11/11/2019 | 11/11/2019 | 28/11/2019 | 28/11/2019 | 0 | TK_Complete
TOP2070 | TT_FinMile | (TOP-10LBB) Cold and Hot Reheat System 10LBB / 10LBC | 15/11/2019 | 15/11/2019 | 29/11/2019 | 29/11/2019 | 0 | TK_Complete
TOP2080 | TT_FinMile | (TOP-00LBG) Auxiliary Steam System | 08/11/2019 | 08/11/2019 | 28/11/2019 | 28/11/2019 | 0 | TK_Complete
TOP2090 | TT_FinMile | (TOP-10MAJ) ST Evacuation System | 04/11/2019 | 04/11/2019 | 22/10/2019 | 22/10/2019 | 0 | TK_Complete
TOP2100 | TT_FinMile | (TOP-10PAH) Condenser Tube Cleaning System | 09/04/2020 | 09/04/2020 | 18/12/2019 | 18/12/2019 | 0 | TK_Complete
TOP2110 | TT_FinMile | (TOP-00BZL-01) L&amp;SP Iincl. BMZ 00 IN UBA 81 Area (Civil Contractor) | 30/03/2020 | 30/03/2020 | 05/02/2020 | 05/02/2020 | 0 | TK_Complete
TOP2120 | TT_FinMile | (TOP-10PAB-01) Circulating Water System incl. Cooling Water Pumps | 08/04/2020 | 08/04/2020 | 13/12/2019 | 13/12/2019 | 0 | TK_Complete
TOP2130 | TT_FinMile | (TOP-00PAA) Cooling Water Screening Plant | 30/03/2020 | 30/03/2020 | 05/12/2019 | 05/12/2019 | 0 | TK_Complete
TOP2140 | TT_FinMile | (TOP-00PUR) Cathodic Protection System for Cooling Water Inlet | 30/03/2020 | 30/03/2020 | 16/12/2019 | 16/12/2019 | 0 | TK_Complete
TOP2160 | TT_FinMile | (TOP-10PUR) Cathodic Protection System for Cooling Water Side of Condenser | 30/03/2020 | 30/03/2020 | 09/12/2019 | 09/12/2019 | 0 | TK_Complete
TOP2190 | TT_FinMile | (TOP-00GHC-02) Demineralised Water Supply System up to UMC | 30/09/2019 | 30/09/2019 | 12/09/2019 | 12/09/2019 | 0 | TK_Complete
TOP2250 | TT_FinMile | (TOP-00SGA-01) Fire Pump Station, Ring Main, Outdoor Hydrants TEMP FIRE SUPPLY (REQUIRED DATE TO BE CLARIFIED) | 14/04/2020 | 14/04/2020 | 18/01/2020 | 18/01/2020 | 0 | TK_Complete
TOP2260 | TT_FinMile | (TOP-00STG) Laboratory Container STG | 07/04/2020 | 07/04/2020 | 11/12/2019 | 11/12/2019 | 0 | TK_Complete
TOP2270 | TT_FinMile | (TOP-00EK) Fuel Gas Conditioning System EKD (incl. Fuel Gas Supply for QHA) | 30/03/2020 | 30/03/2020 | 28/12/2019 | 28/12/2019 | 0 | TK_Complete
TOP2280 | TT_FinMile | (TOP-10SGC-02) FF Spray Deluge System for BOP Systems | 09/04/2020 | 09/04/2020 | 15/01/2020 | 15/01/2020 | 0 | TK_Complete
TOP2290 | TT_FinMile | (TOP-00SCB) Compressed air Distribution System Overall Plant | 31/10/2019 | 31/10/2019 | 04/10/2019 | 04/10/2019 | 0 | TK_Complete
TOP2300 | TT_FinMile | (TOP-00EG-01) Fuel Oil Forwarding Station and Storage Tank | 11/11/2019 | 11/11/2019 | 26/10/2019 | 26/10/2019 | 0 | TK_Complete
TOP2310 | TT_FinMile | (TOP-00EG-02) Fuel Oil Forwarding System incl. Supply Lines up to Fuel Oil | 30/03/2020 | 30/03/2020 | 27/03/2020 | 27/03/2020 | 0 | TK_Complete
TOP2330 | TT_FinMile | (TOP-00CR) Control Room Equipment | 31/07/2019 | 31/07/2019 | 16/07/2019 | 16/07/2019 | 0 | TK_Complete
TOP2350 | TT_FinMile | (TOP-00CY) Communication System in 00UCA (00CY-01_19Jan20 / 00CY-02_27Feb20) | 30/03/2020 | 30/03/2020 | 27/02/2020 | 27/02/2020 | 0 | TK_Complete
TOP2360 | TT_FinMile | (TOP-10AC) HV Switchgear Including Cable Connection and Lighting and Small | 02/09/2019 | 02/09/2019 | 07/08/2019 | 07/08/2019 | 0 | TK_Complete
TOP2370 | TT_FinMile | (TOP-10CYE) Fire Detection System for GT Noise Enclosure MPB | 13/04/2020 | 13/04/2020 | 09/01/2020 | 09/01/2020 | 0 | TK_Complete
TOP2340 | TT_FinMile | (TOP-10CJ-ST) Automation Panel in Function Area Steam Turbine | 05/09/2019 | 05/09/2019 | 15/08/2019 | 15/08/2019 | 0 | TK_Complete
TOP2390 | TT_FinMile | (TOP-10CJ-GT) Automation Panel in Function Area Gas Turbine | 31/08/2019 | 31/08/2019 | 06/08/2019 | 06/08/2019 | 0 | TK_Complete
TOP2400 | TT_FinMile | (TOP-10BA-03) Generator Circuit Breaker | 17/09/2019 | 17/09/2019 | 01/08/2019 | 01/08/2019 | 0 | TK_Complete
TOP2410 | TT_FinMile | (TOP-10BFT-03) LV-Transformer BFT03 | 06/09/2019 | 06/09/2019 | 28/08/2019 | 28/08/2019 | 0 | TK_Complete
TOP2420 | TT_FinMile | (TOP-10BFT-02) LV-Transformer BFT02 | 06/09/2019 | 06/09/2019 | 29/08/2019 | 29/08/2019 | 0 | TK_Complete
TOP2430 | TT_FinMile | (TOP-10CJ-BOP) Automation Panel in Function Area BOP | 16/09/2019 | 16/09/2019 | 19/08/2019 | 19/08/2019 | 0 | TK_Complete
TOP2440 | TT_FinMile | (TOP-10CJ-HR) Automation Panel in Function Area HRSG | 04/09/2019 | 04/09/2019 | 03/09/2019 | 03/09/2019 | 0 | TK_Complete
TOP2450 | TT_FinMile | (TOP-10CP-BOP-01) CPC Interface Panels ET200 in Function Area BOP (UBA area) | 10/09/2019 | 10/09/2019 | 17/08/2019 | 17/08/2019 | 0 | TK_Complete
TOP2460 | TT_FinMile | (TOP-10CP-BOP-02) CPD Interface Panels ET200 in Function Area BOP | 10/09/2019 | 10/09/2019 | 19/08/2019 | 19/08/2019 | 0 | TK_Complete
TOP2470 | TT_FinMile | (TOP-10BT-03) DC-Switchgear BUC/BUD | 11/11/2019 | 11/11/2019 | 18/11/2019 | 18/11/2019 | 0 | TK_Complete
TOP2480 | TT_FinMile | (TOP-10BF-03) LV Switchgear BFD | 11/11/2019 | 11/11/2019 | 20/11/2019 | 20/11/2019 | 0 | TK_Complete
TOP2490 | TT_FinMile | (TOP-10BF-02) LV Switchgear BFB/ BFC | 05/09/2019 | 05/09/2019 | 04/09/2019 | 04/09/2019 | 0 | TK_Complete
TOP2500 | TT_FinMile | (TOP-10BMT-01) LV-Transformer BMT01 | 06/09/2019 | 06/09/2019 | 16/08/2019 | 16/08/2019 | 0 | TK_Complete
TOP2520 | TT_FinMile | (TOP-10CP-BOP-03) CPC Interface Panels ET200 in Function Area BOP (UQA area) | 30/11/2019 | 30/11/2019 | 22/11/2019 | 22/11/2019 | 0 | TK_Complete
TOP2530 | TT_FinMile | (TOP-10CP-BOP-04) CPC Interface Panels ET200 in Function Area BOP (UTR0500 CPC91) | 11/09/2019 | 11/09/2019 | 05/09/2019 | 05/09/2019 | 0 | TK_Complete
TOP2540 | TT_FinMile | (TOP-10CP-BOP-05) CPC Interface Panels ET200 in Function Area BOP (UTR0500 CPC92) | 30/09/2019 | 30/09/2019 | 25/09/2019 | 25/09/2019 | 0 | TK_Complete
TOP2550 | TT_FinMile | (TOP-10BT-01) 220 V Batteries | 31/08/2019 | 31/08/2019 | 16/08/2019 | 16/08/2019 | 0 | TK_Complete
TOP2560 | TT_FinMile | (TOP-10MBU-01) Reserve feedwater pumps and distribution system | 21/10/2019 | 21/10/2019 | 10/10/2019 | 10/10/2019 | 0 | TK_Complete
TOP2570 | TT_FinMile | (TOP-10CKA) Partial Discharge &amp; Shaft voltage/current Monitoring System | 21/10/2019 | 21/10/2019 | 20/10/2019 | 20/10/2019 | 0 | TK_Complete
TOP2580 | TT_FinMile | (TOP-10CJT) SEE / SFC Equipment | 21/10/2019 | 21/10/2019 | 24/10/2019 | 24/10/2019 | 0 | TK_Complete
TOP2590 | TT_FinMile | (TOP-10BAB) Generator Neutral point and auxilaries | 12/11/2019 | 12/11/2019 | 14/11/2019 | 14/11/2019 | 0 | TK_Complete
TOP2600 | TT_FinMile | (TOP-01AC) HV Switchgear interface | 16/09/2019 | 16/09/2019 | 12/09/2019 | 12/09/2019 | 0 | TK_Complete
TOP2610 | TT_FinMile | (TOP-10BA-01) Isolated Phase Busduct Section BAT-BAC | 05/10/2019 | 05/10/2019 | 29/09/2019 | 29/09/2019 | 0 | TK_Complete
TOP2620 | TT_FinMile | (TOP-10BA-02) Isolated Phase Busduct Section BAC-MKA | 12/11/2019 | 12/11/2019 | 04/11/2019 | 04/11/2019 | 0 | TK_Complete
TOP2630 | TT_FinMile | (TOP-00CY-01) CCTV | 08/04/2020 | 08/04/2020 | 19/01/2020 | 19/01/2020 | 0 | TK_Complete
TOP2640 | TT_FinMile | (TOP-00CY-02) Telephone System | 28/03/2020 | 28/03/2020 | 27/02/2020 | 27/02/2020 | 0 | TK_Complete
TOP2650 | TT_FinMile | (TOP-10CR-01) Central Control Room Equipment | 31/07/2019 | 31/07/2019 | 15/07/2019 | 15/07/2019 | 0 | TK_Complete
TOP2660 | TT_FinMile | (TOP-10CR-02) Central Control Room Equipment | 31/07/2019 | 31/07/2019 | 04/07/2019 | 04/07/2019 | 0 | TK_Complete
TOP2670 | TT_FinMile | (TOP-10BF-01) LV Switchgear BFA/ BMA/BLA | 31/07/2019 | 31/07/2019 | 29/07/2019 | 29/07/2019 | 0 | TK_Complete
TOP2680 | TT_FinMile | (TOP-10AC) GIL | 31/07/2019 | 31/07/2019 | 24/07/2019 | 24/07/2019 | 0 | TK_Complete
TOP2690 | TT_FinMile | (TOP-10SMQ) 18t Gantry Crane at CWPS | 31/07/2019 | 31/07/2019 | 28/07/2019 | 28/07/2019 | 0 | TK_Complete
TOP2700 | TT_FinMile | (TOP-10PUS) Electro Chlorination System | 28/03/2020 | 28/03/2020 | 15/02/2020 | 15/02/2020 | 0 | TK_Complete
TOP2710 | TT_FinMile | (TOP-10MBU-02) GT De-NOx-Water Forwarding and Injection System | 14/10/2019 | 14/10/2019 | 12/10/2019 | 12/10/2019 | 0 | TK_Complete
TOP2720 | TT_FinMile | (TOP-10PUR-20) Cathodic Protection System for Condenser | 28/03/2020 | 28/03/2020 | 09/12/2019 | 09/12/2019 | 0 | TK_Complete
TOP2730 | TT_FinMile | (TOP-10PUR-50) Cathodic Protection System for Fuel Gas System (EKG) | 28/03/2020 | 28/03/2020 | 04/12/2019 | 04/12/2019 | 0 | TK_Complete
TOP2740 | TT_FinMile | (TOP-10SGA-10) FF Outdoor Hydrants indluding Ring Main Line (10sga-10-01_18Jan20 / 10sga10-02_18Jan20) | 02/04/2020 | 02/04/2020 | 18/01/2020 | 18/01/2020 | 0 | TK_Complete
TOP2750 | TT_FinMile | (TOP-10SGA-20) FF Indoor Hydrants indluding Ring Main Line (10sga-20-01_18Nov19 / 10sga20-02_18Jan20) | 02/04/2020 | 02/04/2020 | 18/01/2020 | 18/01/2020 | 0 | TK_Complete
TOP2760 | TT_FinMile | (TOP-10LBG) Auxiliary Steam System for Power Island | 08/11/2019 | 08/11/2019 | 29/11/2019 | 29/11/2019 | 0 | TK_Complete
TOP2770 | TT_FinMile | (TOP-10SGM-01) Inert gas system inside UBA | 01/04/2020 | 01/04/2020 | 13/03/2020 | 13/03/2020 | 0 | TK_Complete
TOP2780 | TT_FinMile | (TOP-10SGM-02) Inert gas system inside UBN container | 01/04/2020 | 01/04/2020 | 13/03/2020 | 13/03/2020 | 0 | TK_Complete
TOP2790 | TT_FinMile | (TOP-10SGM-03) Inert gas system inside CPP Control room | 01/04/2020 | 01/04/2020 | 13/03/2020 | 13/03/2020 | 0 | TK_Complete
TOP2800 | TT_FinMile | (TOP-10GM-05) Plant Drainage System for UGH Area | 02/04/2020 | 02/04/2020 | 20/12/2019 | 20/12/2019 | 0 | TK_Complete
TOP2810 | TT_FinMile | (TOP-10GM-04) Plant Drainage System for UGU/UTS/UVM Area | 02/04/2020 | 02/04/2020 | 27/03/2020 | 27/03/2020 | 0 | TK_Complete
TOP2820 | TT_FinMile | (TOP-10GM-06) Plant Drainage System from UGH to Seal Pit Area | 02/04/2020 | 02/04/2020 | 20/12/2019 | 20/12/2019 | 0 | TK_Complete
TOP2830 | TT_FinMile | (TOP-10GNR) Centralized Chemical Drain System | 28/03/2020 | 28/03/2020 | 15/01/2020 | 15/01/2020 | 0 | TK_Complete
TOP2840 | TT_FinMile | (TOP-10QJA10) Carbon Dioxide Distribution System | 08/04/2020 | 08/04/2020 | 24/12/2019 | 24/12/2019 | 0 | TK_Complete
TOP2850 | TT_FinMile | (TOP-10QJA20) Hydrogen Distribution System | 01/04/2020 | 01/04/2020 | 07/01/2020 | 07/01/2020 | 0 | TK_Complete
TOP2860 | TT_FinMile | (TOP-10GHC-01) Demin water supply system - Pump skid | 16/09/2019 | 16/09/2019 | 12/09/2019 | 12/09/2019 | 0 | TK_Complete
TOP2870 | TT_FinMile | (TOP-10GHC-02) Demineralized Water Distribution Pump skid - D5 terminal point | 16/09/2019 | 16/09/2019 | 12/09/2019 | 12/09/2019 | 0 | TK_Complete
TOP2880 | TT_FinMile | (TOP-10GHC-03) Demineralized Water Distribution System Power Island | 16/09/2019 | 16/09/2019 | 12/09/2019 | 12/09/2019 | 0 | TK_Complete
TOP2890 | TT_FinMile | (TOP-10CX) Weather Station and other minor auxiliaries | 14/04/2020 | 14/04/2020 | 09/12/2019 | 09/12/2019 | 0 | TK_Complete
TOP2910 | TT_FinMile | (TOP-10GM-03) Plant Drainage System for UBH Area | 02/04/2020 | 02/04/2020 | 20/12/2019 | 20/12/2019 | 0 | TK_Complete
TOP2920 | TT_FinMile | TOP-10BT-02 DC-Switchgear BUA/BUB, Chargers and DC-DC converters | 31/07/2019 | 31/07/2019 | 29/07/2019 | 29/07/2019 | 0 | TK_Complete
MWS01.1000 | TT_Task | Submission and Approval - Purchase Orders to Sub-contractors of Crane Barges (e.g. for lifts greater than 300t) | 01/03/2018 | 16/03/2018 | 30/01/2018 | 14/02/2018 | 0 | TK_Complete
MWS01.1010 | TT_Task | Submission and Approval - Purchase Orders to Sub-contractors of Land based cranes (e.g. for large lifts between 50-300t) | 01/03/2018 | 16/03/2018 | 30/01/2018 | 09/02/2018 | 0 | TK_Complete
MWS02.1010 | TT_Task | Submission and Approval - Insurance certificates and policy documentation | 01/02/2018 | 21/02/2018 | 01/11/2017 | 17/11/2017 | 0 | TK_Complete
MWS02.1020 | TT_Task | Submission and Approval - Construction Execution Plan | 01/02/2018 | 21/02/2018 | 17/11/2017 | 26/02/2018 | 0 | TK_Complete
MWS02.1030 | TT_Task | Submission and Approval - SHHE Plans | 01/02/2018 | 21/02/2018 | 17/11/2017 | 26/02/2018 | 0 | TK_Complete
MWS02.1040 | TT_Task | Submission and Approval - Material Management Plan | 01/02/2018 | 21/02/2018 | 17/12/2017 | 17/12/2017 | 0 | TK_Complete
MWS02.1050 | TT_Task | Submission and Approval - Project Quality Plan | 01/02/2018 | 21/02/2018 | 08/01/2018 | 08/01/2018 | 0 | TK_Complete
MWS02.1060 | TT_Task | Submission and Approval - Quality Assurance System Manual | 01/02/2018 | 21/02/2018 | 08/01/2018 | 08/01/2018 | 0 | TK_Complete
ENG0000 | TT_FinMile | Engineering complete - Start delivering engineering systems | 01/03/2018 | 01/03/2018 | 31/10/2017 | 31/10/2017 | 0 | TK_Complete
ENG1000 | TT_FinMile | Engineering complete - (00BAW-01) Earthing Grid for back-energizing | 01/03/2018 | 01/03/2018 | 22/01/2018 | 22/01/2018 | 0 | TK_Complete
ENG1010 | TT_FinMile | Engineering complete - (00BAW-02) Earthing Grid Complete | 01/03/2018 | 01/03/2018 | 05/02/2018 | 05/02/2018 | 0 | TK_Complete
ENG1020 | TT_FinMile | Engineering complete - (00BAW-03) Lightening Protection | 01/03/2018 | 01/03/2018 | 22/01/2018 | 22/01/2018 | 0 | TK_Complete
ENG1030 | TT_FinMile | Engineering complete - (10MA-01) HP / IP / LP Turbine 10MAA/MAB/MAC | 01/03/2018 | 01/03/2018 | 23/02/2018 | 23/02/2018 | 0 | TK_Complete
ENG1040 | TT_FinMile | Engineering complete - (10MAL) ST Drain System | 01/03/2018 | 01/03/2018 | 19/03/2018 | 19/03/2018 | 0 | TK_Complete
ENG1060 | TT_FinMile | Engineering complete - (10MA-02) HP / IP / LP Steam Turbine Emergency Stop Valves and Control Valves | 01/03/2018 | 01/03/2018 | 19/03/2018 | 19/03/2018 | 0 | TK_Complete
ENG1070 | TT_FinMile | Engineering complete - (10MAG) Condensing System | 01/03/2018 | 01/03/2018 | 23/01/2018 | 23/01/2018 | 0 | TK_Complete
ENG1080 | TT_FinMile | Engineering complete - (10MAV) Lube and Lifting Oil System Incl. Generator and GT | 19/03/2018 | 19/03/2018 | 19/03/2018 | 19/03/2018 | 0 | TK_Complete
ENG1090 | TT_FinMile | Engineering complete - (10MAW) Gland / Leakage Steam System | 01/03/2018 | 01/03/2018 | 19/03/2018 | 19/03/2018 | 0 | TK_Complete
ENG1100 | TT_FinMile | Engineering complete - (10MAX) ST Hydraulic System | 01/03/2018 | 01/03/2018 | 19/03/2018 | 19/03/2018 | 0 | TK_Complete
ENG1120 | TT_FinMile | Engineering complete - (10MKA) Generator Incl. Bearing System 10 MKD | 01/03/2018 | 01/03/2018 | 30/11/2017 | 30/11/2017 | 0 | TK_Complete
ENG1170 | TT_FinMile | Engineering complete - (10MBV) GT Lube Oil / Lifting Oil System | 01/03/2018 | 01/03/2018 | 16/03/2018 | 16/03/2018 | 0 | TK_Complete
ENG1180 | TT_FinMile | Engineering complete - (10MBA) GT Including Combustion Chamber | 01/03/2018 | 01/03/2018 | 12/02/2018 | 12/02/2018 | 0 | TK_Complete
ENG1190 | TT_FinMile | Engineering complete - (10MBX) GT Hydraulic Oil | 01/03/2018 | 01/03/2018 | 16/02/2018 | 16/02/2018 | 0 | TK_Complete
ENG1200 | TT_FinMile | Engineering complete - (10MBP) GT Natural Gas Incl. Draining System MBP40 | 01/03/2018 | 01/03/2018 | 16/03/2018 | 16/03/2018 | 0 | TK_Complete
ENG1210 | TT_FinMile | Engineering complete - (10MBN) GT Fuel Oil Injection System | 01/03/2018 | 01/03/2018 | 16/03/2018 | 16/03/2018 | 0 | TK_Complete
ENG1220 | TT_FinMile | Engineering complete - (10MBH) GT Cooling Air System | 01/03/2018 | 01/03/2018 | 12/02/2018 | 12/02/2018 | 0 | TK_Complete
ENG1250 | TT_FinMile | Engineering complete - (10MBX2x) GT Pneumatic System | 01/03/2018 | 01/03/2018 | 12/02/2018 | 12/02/2018 | 0 | TK_Complete
ENG1280 | TT_FinMile | Engineering complete - (10MBL) Air Intake System | 01/03/2018 | 01/03/2018 | 19/03/2018 | 19/03/2018 | 0 | TK_Complete
ENG1290 | TT_FinMile | Engineering complete - (10MBU) GT NOX Water Injection System | 01/03/2018 | 01/03/2018 | 16/03/2018 | 16/03/2018 | 0 | TK_Complete
ENG1300 | TT_FinMile | Engineering complete - (10SAM30) Ventilation System For GT Enclosure and Skid Enclosures | 01/03/2018 | 01/03/2018 | 12/03/2018 | 12/03/2018 | 0 | TK_Complete
ENG1330 | TT_FinMile | Engineering complete - (10LCA) Main Condensate Pumps and Supply System for Min. Flow Operation Incl. | 01/03/2018 | 01/03/2018 | 19/03/2018 | 19/03/2018 | 0 | TK_Complete
ENG1340 | TT_FinMile | Engineering complete - (10PGB) Closed Cooling Water System | 01/03/2018 | 01/03/2018 | 12/03/2018 | 12/03/2018 | 0 | TK_Complete
ENG1350 | TT_FinMile | Engineering complete - (10PCB) Service Cooling Water System Incl. 10PDB | 01/03/2018 | 01/03/2018 | 12/03/2018 | 12/03/2018 | 0 | TK_Complete
ENG1390 | TT_FinMile | Engineering complete - (10SGA) FF Indoor Hydrants 10SGA Inside 10ULA, 10UHA, 10UMC | 01/03/2018 | 01/03/2018 | 19/03/2018 | 19/03/2018 | 0 | TK_Complete
ENG1600 | TT_FinMile | Engineering complete - (10MKC) SEE/SFC Equipment Excitation Transformer MKC; SFC Transformer MBJ | 01/03/2018 | 01/03/2018 | 07/03/2018 | 07/03/2018 | 0 | TK_Complete
ENG1610 | TT_FinMile | Engineering complete - (10SGC-01) FF Spary Deluge System for BAT/ BBT SGC | 01/03/2018 | 01/03/2018 | 19/03/2018 | 19/03/2018 | 0 | TK_Complete
ENG1620 | TT_FinMile | Engineering complete - (10LD) Condensate Polishing Plant | 01/03/2018 | 01/03/2018 | 12/03/2018 | 12/03/2018 | 0 | TK_Complete
ENG1630 | TT_FinMile | Engineering complete - (10LDK) Condensate Polishing System | 01/03/2018 | 01/03/2018 | 12/03/2018 | 12/03/2018 | 0 | TK_Complete
ENG1710 | TT_FinMile | Engineering complete - (10MBR) Exhaust Gas System | 01/03/2018 | 01/03/2018 | 12/03/2018 | 12/03/2018 | 0 | TK_Complete
ENG1720 | TT_FinMile | Engineering complete - (10EK) Fuel Gas Supply System for GT10 | 28/05/2018 | 28/05/2018 | 31/05/2018 | 31/05/2018 | 0 | TK_Complete
ENG1750 | TT_FinMile | Engineering complete - (10HAD10) HRSG HP Steam | 01/03/2018 | 01/03/2018 | 22/01/2018 | 22/01/2018 | 0 | TK_Complete
ENG1760 | TT_FinMile | Engineering complete - (10HAD50) HRSG IP Steam | 01/03/2018 | 01/03/2018 | 22/01/2018 | 22/01/2018 | 0 | TK_Complete
ENG1770 | TT_FinMile | Engineering complete - (10HAD80) HRSG LP Steam | 01/03/2018 | 01/03/2018 | 22/01/2018 | 22/01/2018 | 0 | TK_Complete
ENG1780 | TT_FinMile | Engineering complete - (10HAA) HRSG Condensate Preheating System | 01/03/2018 | 01/03/2018 | 22/01/2018 | 22/01/2018 | 0 | TK_Complete
ENG1790 | TT_FinMile | Engineering complete - (10HBK) HRSG Exhaust Gas System | 01/03/2018 | 01/03/2018 | 05/02/2018 | 05/02/2018 | 0 | TK_Complete
ENG1800 | TT_FinMile | Engineering complete - (00LBG) Auxiliary Steam System Common Area | 02/12/2019 | 02/12/2019 | 31/10/2017 | 31/10/2017 | 0 | TK_Complete
ENG1810 | TT_FinMile | Engineering complete - (10GM-02) Plant Drainage System for 10U HW | 02/12/2019 | 02/12/2019 | 31/10/2017 | 31/10/2017 | 0 | TK_Complete
ENG1820 | TT_FinMile | Engineering complete - (10LBH) Start-up and Shutdown Steam System incl Drains System | 01/03/2018 | 01/03/2018 | 05/02/2018 | 05/02/2018 | 0 | TK_Complete
ENG1830 | TT_FinMile | Engineering complete - (10LCL) HRSG Drains System | 01/03/2018 | 01/03/2018 | 12/03/2018 | 12/03/2018 | 0 | TK_Complete
ENG1840 | TT_FinMile | Engineering complete - (10LCA-02) Condensate Supply System incl. Preheater 10HAA10 | 01/03/2018 | 01/03/2018 | 19/03/2018 | 19/03/2018 | 0 | TK_Complete
ENG1850 | TT_FinMile | Engineering complete - (10LAB) HP/IP Feedwater Supply System | 02/12/2019 | 02/12/2019 | 31/10/2017 | 31/10/2017 | 0 | TK_Complete
ENG1860 | TT_FinMile | Engineering complete - (10LAC) Feedwater Pump | 01/03/2018 | 01/03/2018 | 19/03/2018 | 19/03/2018 | 0 | TK_Complete
ENG1870 | TT_FinMile | Engineering complete - (10QCB) Hydrazine Dosing QC | 02/12/2019 | 02/12/2019 | 31/10/2017 | 31/10/2017 | 0 | TK_Complete
ENG1880 | TT_FinMile | Engineering complete - (10QCC) Trisodium Phosphate Dosing QC | 02/12/2019 | 02/12/2019 | 31/10/2017 | 31/10/2017 | 0 | TK_Complete
ENG1890 | TT_FinMile | Engineering complete - (10QCD) Ammonia Dosing QC | 02/12/2019 | 02/12/2019 | 31/10/2017 | 31/10/2017 | 0 | TK_Complete
ENG1900 | TT_FinMile | Engineering complete - (10QU) Sampling Container QC | 01/03/2018 | 01/03/2018 | 02/03/2018 | 02/03/2018 | 0 | TK_Complete
ENG1920 | TT_FinMile | Engineering complete - (10HSJ) Reduction Agent Supply System for SCR | 02/12/2019 | 02/12/2019 | 31/10/2017 | 31/10/2017 | 0 | TK_Complete
ENG1930 | TT_FinMile | Engineering complete - (10EKT20) Fuel Gas Preheating System 10EKT20 | 02/12/2019 | 02/12/2019 | 31/10/2017 | 31/10/2017 | 0 | TK_Complete
ENG1940 | TT_FinMile | Engineering complete - (10GHC) Demineralised Water Distribution System inside 10 UMC | 02/12/2019 | 02/12/2019 | 31/10/2017 | 31/10/2017 | 0 | TK_Complete
ENG1950 | TT_FinMile | Engineering complete - (00GHD-01) Service Water Distribution System | 02/12/2019 | 02/12/2019 | 31/10/2017 | 31/10/2017 | 0 | TK_Complete
ENG1960 | TT_FinMile | Engineering complete - (00GKB-01) Drinking Water Distribution System | 02/12/2019 | 02/12/2019 | 31/10/2017 | 31/10/2017 | 0 | TK_Complete
ENG1970 | TT_FinMile | Engineering complete - (10LBA10) HP Main Steam System | 02/12/2019 | 02/12/2019 | 31/10/2017 | 31/10/2017 | 0 | TK_Complete
ENG1980 | TT_FinMile | Engineering complete - (10LBA80) LP Main Steam System | 02/12/2019 | 02/12/2019 | 31/10/2017 | 31/10/2017 | 0 | TK_Complete
ENG1990 | TT_FinMile | Engineering complete - (10LBB) Cold and Hot Reheat System 10LBB / 10LBC | 02/12/2019 | 02/12/2019 | 31/10/2017 | 31/10/2017 | 0 | TK_Complete
ENG2000 | TT_FinMile | Engineering complete - (00LBG) Auxiliary Steam System | 02/12/2019 | 02/12/2019 | 31/10/2017 | 31/10/2017 | 0 | TK_Complete
ENG2010 | TT_FinMile | Engineering complete - (10MAJ) ST Evacuation System | 01/03/2018 | 01/03/2018 | 19/03/2018 | 19/03/2018 | 0 | TK_Complete
ENG2020 | TT_FinMile | Engineering complete - (10PAH) Condenser Tube Cleaning System | 01/03/2018 | 01/03/2018 | 23/01/2018 | 23/01/2018 | 0 | TK_Complete
ENG2030 | TT_FinMile | Engineering complete - (00BZL-01) L&amp;SP incl BMZ 00 IN UBA 81 Area | 02/12/2019 | 02/12/2019 | 31/10/2017 | 31/10/2017 | 0 | TK_Complete
ENG2040 | TT_FinMile | Engineering complete - (10PAB-01) Circulating Water System incl. Cooling Water Pumps | 02/12/2019 | 02/12/2019 | 31/10/2017 | 31/10/2017 | 0 | TK_Complete
ENG2050 | TT_FinMile | Engineering complete - (00PAA) Cooling Water Screening Plant | 01/03/2018 | 01/03/2018 | 02/03/2018 | 02/03/2018 | 0 | TK_Complete
ENG2060 | TT_FinMile | Engineering complete - (00PUR) Cathodic Protection System for Cooling Water Inlet | 02/12/2019 | 02/12/2019 | 31/10/2017 | 31/10/2017 | 0 | TK_Complete
ENG2070 | TT_FinMile | Engineering complete - (00PUN) Biocide Dosing System for Cooling Water | 02/12/2019 | 02/12/2019 | 31/10/2017 | 31/10/2017 | 0 | TK_Complete
ENG2080 | TT_FinMile | Engineering complete - (10PUR) Cathodic Protection System for Cooling Water Side of Condenser | 02/12/2019 | 02/12/2019 | 31/10/2017 | 31/10/2017 | 0 | TK_Complete
ENG2100 | TT_FinMile | Engineering complete - (00GM-02) Plant Drainage System for Surface Water | 02/12/2019 | 02/12/2019 | 31/10/2017 | 31/10/2017 | 0 | TK_Complete
ENG2110 | TT_FinMile | Engineering complete - (00GHC-02) Demineralised Water Supply System up to UMC | 02/12/2019 | 02/12/2019 | 31/10/2017 | 31/10/2017 | 0 | TK_Complete
ENG2130 | TT_FinMile | Engineering complete - (00MBU) NOX Water Forwarding System incl. Supply Lines to GT Skid | 01/03/2018 | 01/03/2018 | 16/03/2018 | 16/03/2018 | 0 | TK_Complete
ENG2140 | TT_FinMile | Engineering complete - (00GHC-01) Demineralised Water Storage System | 02/12/2019 | 02/12/2019 | 31/10/2017 | 31/10/2017 | 0 | TK_Complete
ENG2150 | TT_FinMile | Engineering complete - (00GA) Raw Water Supply and Storage Tank 00GAC/GAD | 02/12/2019 | 02/12/2019 | 31/10/2017 | 31/10/2017 | 0 | TK_Complete
ENG2160 | TT_FinMile | Engineering complete - (00BZL-03) L&amp;SP incl. BMZ 00 IN USG Area | 02/12/2019 | 02/12/2019 | 31/10/2017 | 31/10/2017 | 0 | TK_Complete
ENG2170 | TT_FinMile | Engineering complete - (00SGA-01) Fire Pump Station, Ring Main, Outdoors Hydrants | 01/03/2018 | 01/03/2018 | 19/03/2018 | 19/03/2018 | 0 | TK_Complete
ENG2180 | TT_FinMile | Engineering complete - (00STG) Laboratory Container STG | 01/03/2018 | 01/03/2018 | 12/03/2018 | 12/03/2018 | 0 | TK_Complete
ENG2190 | TT_FinMile | Engineering complete - (00EK) Fuel Gas Conditioning System EKD (incl. Fuel Gas Supply for QHA) | 02/12/2019 | 02/12/2019 | 31/10/2017 | 31/10/2017 | 0 | TK_Complete
ENG2200 | TT_FinMile | Engineering complete - (10SGC-02) FF Spray Deluge Systems for 00UEH/UEJ/UEK Area | 02/12/2019 | 02/12/2019 | 31/10/2017 | 31/10/2017 | 0 | TK_Complete
ENG2210 | TT_FinMile | Engineering complete - (00SCB) Comprssed Air Distribution System Overall Plant | 02/12/2019 | 02/12/2019 | 31/10/2017 | 31/10/2017 | 0 | TK_Complete
ENG2220 | TT_FinMile | Engineering complete - (00EG-01) Fuel Oil Forwarding Station and Storage Tank | 02/12/2019 | 02/12/2019 | 31/10/2017 | 31/10/2017 | 0 | TK_Complete
ENG2230 | TT_FinMile | Engineering complete - (00EG-02) Fuel Oil Forwarding System incl. Supply Lines up to Fuel Oil | 02/12/2019 | 02/12/2019 | 31/10/2017 | 31/10/2017 | 0 | TK_Complete
ENG2240 | TT_FinMile | Engineering complete - (00BZL-02) L&amp;SP in UCA | 02/12/2019 | 02/12/2019 | 31/10/2017 | 31/10/2017 | 0 | TK_Complete
ENG2250 | TT_FinMile | Engineering complete - (00CR) Control Room Equipment | 02/12/2019 | 02/12/2019 | 31/10/2017 | 31/10/2017 | 0 | TK_Complete
ENG2270 | TT_FinMile | Engineering complete - (00CY) Communication System in 00UCA | 02/12/2019 | 02/12/2019 | 31/10/2017 | 31/10/2017 | 0 | TK_Complete
ENG2280 | TT_FinMile | Engineering complete - (10AC) HV Swictchgear Including Cable Connection and Lighting and Small Power | 02/12/2019 | 02/12/2019 | 31/10/2017 | 31/10/2017 | 0 | TK_Complete
ENG2290 | TT_FinMile | Engineering complete - (10CYE) Fire Detection System for GT Noise Enlcosure MPB | 02/12/2019 | 02/12/2019 | 31/10/2017 | 31/10/2017 | 0 | TK_Complete
ENG2300 | TT_FinMile | Engineering complete - (00PUS) Electro Chlorination System | 02/12/2019 | 02/12/2019 | 31/10/2017 | 31/10/2017 | 0 | TK_Complete
ENG2310 | TT_FinMile | Engineering complete - (10BZL-03) L&amp;SP incl. BMZ in UBA and UBF and UBE | 02/12/2019 | 02/12/2019 | 31/10/2017 | 31/10/2017 | 0 | TK_Complete
ENG2320 | TT_FinMile | Engineering complete - (10BZL-01) L&amp;SP incl BMZ inside 10UMC | 02/12/2019 | 02/12/2019 | 31/10/2017 | 31/10/2017 | 0 | TK_Complete
ENG2330 | TT_FinMile | Engineering complete - (00GM-03) Plant Drainage System Pump for UGD (incl. UGU) | 02/12/2019 | 02/12/2019 | 31/10/2017 | 31/10/2017 | 0 | TK_Complete
ENG2340 | TT_FinMile | Engineering complete - (00GHD-02) Service Water Distribution Inside Power Block | 02/12/2019 | 02/12/2019 | 31/10/2017 | 31/10/2017 | 0 | TK_Complete
ENG2350 | TT_FinMile | Engineering complete - (00GKB-02) Drinking Water Distribution Inside Power Block | 02/12/2019 | 02/12/2019 | 31/10/2017 | 31/10/2017 | 0 | TK_Complete
ENG2360 | TT_FinMile | Engineering complete - (10MAD) ST Bearing System | 02/12/2019 | 02/12/2019 | 31/10/2017 | 31/10/2017 | 0 | TK_Complete
ENG2370 | TT_FinMile | Engineering complete - (10CY) Communication / Security Systems 10 | 02/12/2019 | 02/12/2019 | 31/10/2017 | 31/10/2017 | 0 | TK_Complete
ENG2380 | TT_FinMile | Engineering complete - (10GM-02) Plant Drainage System for 10U MC | 02/12/2019 | 02/12/2019 | 31/10/2017 | 31/10/2017 | 0 | TK_Complete
Sub-GTST-100 | TT_Task | Prepare RFQ Documentation | 28/02/2018 | 28/02/2018 | 28/02/2018 | 20/03/2018 | 0 | TK_Complete
Sub-GTST-110 | TT_FinMile | Issue RFQ Documentation | 01/03/2018 | 01/03/2018 | 28/02/2018 | 28/02/2018 | 0 | TK_Complete
Sub-GTST-120 | TT_Task | RFQ Process | 01/03/2018 | 01/03/2018 | 28/02/2018 | 28/02/2018 | 0 | TK_Complete
Sub-GTST-130 | TT_Task | Bid Technical Evaluation/Review Process | 01/03/2018 | 01/03/2018 | 28/02/2018 | 28/02/2018 | 0 | TK_Complete
Sub-GTST-140 | TT_Task | Negoitiations with Selected Sub-Contractor | 15/03/2018 | 15/03/2018 | 28/02/2018 | 28/02/2018 | 0 | TK_Complete
Sub-GTST-150 | TT_FinMile | Award Sub-Contract Package | 28/03/2018 | 28/03/2018 | 28/02/2018 | 28/02/2018 | 0 | TK_Complete
Sub-GTST-160 | TT_Task | Subcontractor Site Mobilization | 29/03/2018 | 29/03/2018 | 28/02/2018 | 28/02/2018 | 0 | TK_Complete
Sub-GTST-170 | TT_Task | Subcontractor Submittal/Approval of Required Documentation (QA/QC, Weld Procedures, HSE, Schedules) | 29/03/2018 | 29/03/2018 | 28/02/2018 | 28/02/2018 | 0 | TK_Complete
Sub-GTST-180 | TT_Mile | GT/ST/Generator Mobilized @ Site - Commencement of Work | 26/06/2018 | 26/06/2018 | 04/06/2018 | 04/06/2018 | 0 | TK_Complete
SUB-CON-100 | TT_Task | Prepare RFQ Documentation | 01/03/2018 | 21/03/2018 | 24/01/2018 | 13/02/2018 | 0 | TK_Complete
SUB-CON-110 | TT_FinMile | Issue RFQ Documentation | 21/03/2018 | 21/03/2018 | 14/02/2018 | 14/02/2018 | 0 | TK_Complete
SUB-CON-120 | TT_Task | RFQ Process | 01/03/2018 | 21/03/2018 | 15/02/2018 | 01/03/2018 | 0 | TK_Complete
SUB-CON-130 | TT_Task | Bid Technical Evaluation/Review Process | 22/03/2018 | 09/04/2018 | 02/03/2018 | 07/03/2018 | 0 | TK_Complete
SUB-CON-140 | TT_Task | Negoitiations with Selected Sub-Contractor | 10/04/2018 | 20/04/2018 | 08/03/2018 | 12/03/2018 | 0 | TK_Complete
SUB-CON-150 | TT_FinMile | Award Sub-Contract Package | 13/04/2018 | 13/04/2018 | 13/03/2018 | 13/03/2018 | 0 | TK_Complete
SUB-CON-160 | TT_Task | Subcontractor Site Mobilization | 24/04/2018 | 30/05/2018 | 14/03/2018 | 31/03/2018 | 0 | TK_Complete
SUB-CON-170 | TT_Task | Subcontractor Submittal/Approval of Required Documentation (QA/QC, Weld Procedures, HSE, Schedules) | 01/03/2018 | 28/03/2018 | 14/03/2018 | 28/03/2018 | 0 | TK_Complete
SUB-CON-180 | TT_Mile | Condenser Contractor Mobilized @ Site - Commencement of Work | 02/05/2018 | 02/05/2018 | 29/03/2018 | 29/03/2018 | 0 | TK_Complete
SUB-HRSG-100 | TT_Task | Prepare RFQ Documentation | 01/02/2018 | 24/02/2018 | 06/11/2017 | 24/11/2017 | 0 | TK_Complete
SUB-HRSG-110 | TT_FinMile | Issue RFQ Documentation | 24/02/2018 | 24/02/2018 | 27/11/2017 | 27/11/2017 | 0 | TK_Complete
SUB-HRSG-120 | TT_Task | RFQ Process | 26/02/2018 | 17/03/2018 | 28/11/2017 | 15/12/2017 | 0 | TK_Complete
SUB-HRSG-130 | TT_Task | Bid Technical Evaluation/Review Process | 13/02/2018 | 01/03/2018 | 18/12/2017 | 03/01/2018 | 0 | TK_Complete
SUB-HRSG-140 | TT_Task | Negoitiations with Selected Sub-Contractor | 02/03/2018 | 15/03/2018 | 04/01/2018 | 17/01/2018 | 0 | TK_Complete
SUB-HRSG-150 | TT_FinMile | Award Sub-Contract Package | 01/02/2018 | 01/02/2018 | 18/01/2018 | 18/01/2018 | 0 | TK_Complete
SUB-HRSG-160 | TT_Task | HRSG Subcontractor Site Mobilization | 16/03/2018 | 21/03/2018 | 19/02/2018 | 07/03/2018 | 0 | TK_Complete
SUB-HRSG-170 | TT_Task | HRSG Subcontractor Submittal/Approval of Required Documentation (QA/QC, Weld Procedures, HSE, Schedules) | 01/02/2018 | 10/03/2018 | 18/01/2018 | 23/03/2018 | 0 | TK_Complete
SUB-HRSG-180 | TT_Mile | HSRG Contractor Mobilized @ Site - Commencement of Work | 02/03/2018 | 02/03/2018 | 08/03/2018 | 08/03/2018 | 0 | TK_Complete
SUB-BOP-160 | TT_Task | Site Mobilization (Pipe Fitter + Welder) | 05/09/2018 | 11/10/2018 | 28/06/2018 | 28/06/2018 | 0 | TK_Complete
SUB-EIC-100 | TT_Task | Prepare RFQ Documentation | 26/06/2018 | 17/07/2018 | 16/04/2018 | 21/04/2018 | 0 | TK_Complete
SUB-EIC-110 | TT_FinMile | Issue RFQ Documentation | 17/07/2018 | 17/07/2018 | 23/04/2018 | 23/04/2018 | 0 | TK_Complete
SUB-EIC-120 | TT_Task | RFQ Process | 18/07/2018 | 07/08/2018 | 23/04/2018 | 26/05/2018 | 0 | TK_Complete
SUB-EIC-130 | TT_Task | Bid Technical Evaluation/Review Process | 08/08/2018 | 21/08/2018 | 07/05/2018 | 16/05/2018 | 0 | TK_Complete
SUB-EIC-140 | TT_Task | Negotiations with Selected Sub-Contractor | 22/08/2018 | 04/09/2018 | 16/05/2018 | 26/05/2018 | 0 | TK_Complete
SUB-EIC-150 | TT_FinMile | Award Sub-Contract Package | 30/08/2018 | 30/08/2018 | 31/08/2018 | 31/08/2018 | 0 | TK_Complete
SUB-EIC-160 | TT_Task | Subcontractor Site Mobilization | 02/10/2018 | 05/11/2018 | 26/09/2018 | 10/10/2018 | 0 | TK_Complete
SUB-EIC-170 | TT_Task | Subcontractor Submittal/Approval of Required Documentation (QA/QC, Weld Procedures, HSE, Schedules) | 06/09/2018 | 13/10/2018 | 05/09/2018 | 05/12/2018 | 0 | TK_Complete
SUB-EIC-180 | TT_Mile | EI&amp;C Contractor Mobilized @ Site - Commencement of Work | 29/09/2018 | 29/09/2018 | 29/09/2018 | 29/09/2018 | 0 | TK_Complete
ECS18.1130 | TT_Task | Delivery of LV Transformer BFT01 (BHT) | 02/12/2019 | 03/12/2019 | 27/03/2019 | 27/03/2019 | 0 | TK_Complete
ECS18.1170 | TT_Task | Delivery of LV Transformer BFT02 (BHT) | 02/12/2019 | 03/12/2019 | 27/03/2019 | 27/03/2019 | 0 | TK_Complete
ECS18.1210 | TT_Task | Delivery of LV Transformer BFT03 | 02/12/2019 | 03/12/2019 | 27/03/2019 | 27/03/2019 | 0 | TK_Complete
ECS18.1330 | TT_Task | Delivery of LV Switchgear 10BFE/10BMA | 02/12/2019 | 09/12/2019 | 05/04/2019 | 10/04/2019 | 0 | TK_Complete
ECS18.1370 | TT_Task | Delivery of PCC UBA81 &amp; Cabinet 10UBA Building | 30/03/2020 | 06/04/2020 | 28/03/2020 | 28/03/2020 | 0 | TK_Complete
ECS21.1010 | TT_Task | Delivery of SEE/ SFC Transformer | 26/04/2018 | 03/05/2018 | 26/04/2018 | 02/05/2018 | 0 | TK_Complete
EDKS.1000 | TT_Mile | Equipment Purchasing - Switchboard of fuel oil system | 30/11/2019 | 30/11/2019 | 08/06/2019 | 08/06/2019 | 0 | TK_Complete
EDKS.1010 | TT_Mile | Equipment Purchasing - Switchboard of reserved feed water system | 30/11/2019 | 30/11/2019 | 08/06/2019 | 08/06/2019 | 0 | TK_Complete
EDS.1000 | TT_Mile | Equipment Delivery by Siemens - Lighting Fixture | 30/11/2019 | 30/11/2019 | 31/05/2019 | 31/05/2019 | 0 | TK_Complete
EDS.1010 | TT_Mile | Equipment Delivery by Siemens - Batteries, Battery Charger, Converter &amp; Inverter and UPS System | 26/04/2018 | 26/04/2018 | 28/03/2018 | 28/03/2018 | 0 | TK_Complete
EDS.1020 | TT_Mile | Equipment Delivery by Siemens - Filter House System | 30/11/2019 | 30/11/2019 | 20/04/2019 | 20/04/2019 | 0 | TK_Complete
EDS.1030 | TT_Mile | Equipment Delivery by Siemens - Cathodic Corrosion Protection System | 30/11/2019 | 30/11/2019 | 19/09/2019 | 19/09/2019 | 0 | TK_Complete
EDS.1040 | TT_Mile | Equipment Delivery by Siemens - Central Control Room Furniture and Equipment | 30/11/2019 | 30/11/2019 | 15/03/2019 | 15/03/2019 | 0 | TK_Complete
EDS.1050 | TT_Mile | Equipment Delivery by Siemens - Continuous Emission Monitoring System Equipment | 30/11/2019 | 30/11/2019 | 20/05/2019 | 20/05/2019 | 0 | TK_Complete
EDS.1060 | TT_Mile | Equipment Delivery by Siemens - Electrical, Control &amp; Instrumentation (for Gas Turbine &amp; Auxiliaries) | 30/11/2019 | 30/11/2019 | 22/03/2019 | 22/03/2019 | 0 | TK_Complete
EDS.1070 | TT_Mile | Equipment Delivery by Siemens - Electrical, Control &amp; Instrumentation (for HRSG) | 30/11/2019 | 30/11/2019 | 15/05/2019 | 15/05/2019 | 0 | TK_Complete
EDS.1080 | TT_Mile | Equipment Delivery by Siemens - Electrical, Control &amp; Instrumentation (for Generator Steam Turbine) | 30/11/2019 | 30/11/2019 | 13/04/2019 | 13/04/2019 | 0 | TK_Complete
EDS.1090 | TT_Mile | Equipment Delivery by Siemens - Electrical, Control &amp; Instrumentation (for BOP) | 30/11/2019 | 30/11/2019 | 24/04/2019 | 24/04/2019 | 0 | TK_Complete
P1010 | TT_FinMile | ST LP Outer Casing on-site | 26/04/2018 | 26/04/2018 | 02/04/2018 | 02/04/2018 | 0 | TK_Complete
SI---P4I40 | TT_FinMile | BOP Valves on-site | 23/04/2018 | 23/04/2018 | 23/02/2018 | 23/02/2018 | 0 | TK_Complete
SI-BZK4-25 | TT_FinMile | MV/LV Cables (BZK) (1ST SET 30%) on-site | 30/11/2019 | 30/11/2019 | 20/02/2019 | 20/02/2019 | 0 | TK_Complete
SI-BZK4-52 | TT_FinMile | MV Cables (BZK) on-site | 30/11/2019 | 30/11/2019 | 20/02/2019 | 20/02/2019 | 0 | TK_Complete
SI-BZK4-58 | TT_FinMile | MV / LV Cables (BZK) (2ND SET 80%) on-site | 30/11/2019 | 30/11/2019 | 11/03/2019 | 11/03/2019 | 0 | TK_Complete
SI-BZK4-60 | TT_FinMile | MV/LV Cables (BZK) (3RD SET 100%) on-site | 30/11/2019 | 30/11/2019 | 01/04/2019 | 01/04/2019 | 0 | TK_Complete
SI-BZP4-25 | TT_FinMile | First Cables Support System (BZP) (for Pre-Fab Modules) on-site | 14/05/2018 | 14/05/2018 | 29/12/2017 | 29/12/2017 | 0 | TK_Complete
SI-BZP4-27 | TT_FinMile | First Cables Support System (BZP) (Main) on-site | 30/11/2019 | 30/11/2019 | 22/10/2018 | 22/10/2018 | 0 | TK_Complete
SI-BZP4B25 | TT_FinMile | Second Cable Support System (BZP) (Main) on-site | 30/11/2019 | 30/11/2019 | 22/10/2018 | 22/10/2018 | 0 | TK_Complete
SI-C--4B40 | TT_FinMile | BOP I&amp;C Field Devices and Erection Material on-site | 30/11/2019 | 30/11/2019 | 10/05/2019 | 10/05/2019 | 0 | TK_Complete
SI-C-4C40 | TT_FinMile | BOP I&amp;C Cables on-site | 30/11/2019 | 30/11/2019 | 24/04/2019 | 24/04/2019 | 0 | TK_Complete
SI-CFE4-40 | TT_FinMile | CEMS on-site | 30/11/2019 | 30/11/2019 | 20/05/2019 | 20/05/2019 | 0 | TK_Complete
SI-CP-4-40 | TT_FinMile | BOP I&amp;C Field Cabinets on-site | 30/11/2019 | 30/11/2019 | 10/10/2018 | 10/10/2018 | 0 | TK_Complete
SI-CR-4-40 | TT_FinMile | CCR Furniture and HMI Equipment on-site | 30/11/2019 | 30/11/2019 | 10/10/2018 | 10/10/2018 | 0 | TK_Complete
SI-CYA4-25 | TT_Mile | Equipment Delivery by Siemens - TELECOMMUNICATION CYA | 30/11/2019 | 30/11/2019 | 16/04/2019 | 16/04/2019 | 0 | TK_Complete
SI-CYE4-58 | TT_FinMile | Fire Alarm System (CYE) on-site | 01/03/2018 | 01/03/2018 | 28/02/2018 | 28/02/2018 | 0 | TK_Complete
SI-CYP4-25 | TT_FinMile | Security System (CYP) on-site | 30/11/2019 | 30/11/2019 | 16/04/2019 | 16/04/2019 | 0 | TK_Complete
SI-EK-4-40 | TT_FinMile | Fuel Gas Supply System (EK/EKC) on-site | 28/05/2018 | 28/05/2018 | 26/05/2018 | 26/05/2018 | 0 | TK_Complete
SI-EK-4-44 | TT_FinMile | Fuel Gas Supply System EK (Add. Isolating Valves Only) | 30/11/2019 | 30/11/2019 | 10/06/2019 | 10/06/2019 | 0 | TK_Complete
SI-GHD4-62 | TT_FinMile | Water Pipework System on-site | 30/11/2019 | 30/11/2019 | 31/10/2018 | 31/10/2018 | 0 | TK_Complete
SI-GM-4B40 | TT_FinMile | Sump Pump (GM/GKB/GHD/UGU) on-site | 30/11/2019 | 30/11/2019 | 01/04/2019 | 01/04/2019 | 0 | TK_Complete
SI-MBH4-58 | TT_FinMile | Hydrogen Supply Sytsem on site | 30/11/2019 | 30/11/2019 | 17/10/2018 | 17/10/2018 | 0 | TK_Complete
SI-MKG4-60 | TT_FinMile | CO2 Supply System on-site | 30/11/2019 | 30/11/2019 | 01/04/2019 | 01/04/2019 | 0 | TK_Complete
SI-PAS4-66 | TT_FinMile | Make-up Water Pumps (PAS) / NOX Control Water Pump on-site | 30/11/2019 | 30/11/2019 | 15/12/2018 | 15/12/2018 | 0 | TK_Complete
SI-SCB4-64 | TT_FinMile | Compressed Air Interconnection system on-site | 30/11/2019 | 30/11/2019 | 02/01/2019 | 02/01/2019 | 0 | TK_Complete
SI-SG-4-56 | TT_FinMile | Fire Fighting Systems (SG) on-site | 30/11/2019 | 30/11/2019 | 15/02/2019 | 15/02/2019 | 0 | TK_Complete
SI-SGA4A25 | TT_FinMile | Fire Fighting Ring Main (SGA) on-site | 30/11/2019 | 30/11/2019 | 23/05/2019 | 23/05/2019 | 0 | TK_Complete
SI-ZTB4A25 | TT_FinMile | Steam Blow pipework (ZTB) on-site | 28/03/2020 | 28/03/2020 | 15/06/2018 | 15/06/2018 | 0 | TK_Complete
SI0ACA4-25 | TT_FinMile | HV Switchgear (GIL) on-site | 30/11/2019 | 30/11/2019 | 10/04/2019 | 10/04/2019 | 0 | TK_Complete
SI0ACA4-45 | TT_Mile | Equipment Delivery by Siemens - HV Switchgear GIL | 30/11/2019 | 30/11/2019 | 10/04/2019 | 10/04/2019 | 0 | TK_Complete
SI0ACA4-55 | TT_Mile | Equip Delivery - Feedwater Pumps LAC | 30/11/2019 | 30/11/2019 | 15/02/2019 | 15/02/2019 | 0 | TK_Complete
SI0EG-4-44 | TT_FinMile | Fuel Oil Forwarding System (EG) (incl. Pumps) on-site | 30/11/2019 | 30/11/2019 | 15/09/2018 | 15/09/2018 | 0 | TK_Complete
SI0GN-4B44 | TT_FinMile | Process Drains Treatment (GN) on-site | 30/11/2019 | 30/11/2019 | 01/04/2019 | 01/04/2019 | 0 | TK_Complete
SI0PUN4-60 | TT_FinMile | Electrochlorination System on-site | 28/03/2020 | 28/03/2020 | 30/08/2018 | 30/08/2018 | 0 | TK_Complete
SI0XKA4-25 | TT_Mile | Equipment Delivery by Siemens - EMERGENCY DIESEL GENERATOR SET XKA | 30/11/2019 | 30/11/2019 | 22/07/2019 | 22/07/2019 | 0 | TK_Complete
SI1--P4A40 | TT_Mile | Equipment Delivery by Siemens - Supply Piping DN &gt;=80 | 30/11/2019 | 30/11/2019 | 15/09/2018 | 15/09/2018 | 0 | TK_Complete
SI1--P4H40 | TT_Mile | Equipment Delivery by Siemens - Supply Piping DN &lt;80 | 30/11/2019 | 30/11/2019 | 15/09/2018 | 15/09/2018 | 0 | TK_Complete
SI1BAA4-25 | TT_Mile | Equipment Delivery by Siemens - Isolated Generator Busduct 10BAA | 30/11/2019 | 30/11/2019 | 01/04/2019 | 01/04/2019 | 0 | TK_Complete
SI1BAC4-25 | TT_FinMile | Generator Circuit Breaker (BAC) on-site | 16/03/2018 | 16/03/2018 | 15/03/2018 | 15/03/2018 | 0 | TK_Complete
SI1BAT4-25 | TT_Mile | Equipment Delivery by Siemens - Main Transformer BAT | 15/05/2018 | 15/05/2018 | 05/05/2018 | 05/05/2018 | 0 | TK_Complete
SI1BBA4-10 | TT_Mile | Equipment Delivery by Siemens - MV Switchgear BBA | 30/11/2019 | 30/11/2019 | 10/03/2019 | 10/03/2019 | 0 | TK_Complete
SI1BBT4-25 | TT_Mile | Equipment Delivery by Siemens - Main Transformer BBT | 21/03/2018 | 21/03/2018 | 03/02/2018 | 03/02/2018 | 0 | TK_Complete
SI1BFA4-10 | TT_Mile | Equipment Delivery by Siemens - LV/DC Switchgear BFA | 30/11/2019 | 30/11/2019 | 09/04/2019 | 09/04/2019 | 0 | TK_Complete
SI1BFT4-25 | TT_Mile | Equipment Delivery by Siemens - LV Transformer BFT | 26/05/2018 | 26/05/2018 | 15/05/2018 | 15/05/2018 | 0 | TK_Complete
SI1C--4-25 | TT_FinMile | ST I&amp;C Field Instrumentation on-site | 30/11/2019 | 30/11/2019 | 15/04/2019 | 15/04/2019 | 0 | TK_Complete
SI1CHA4-10 | TT_FinMile | Protection., Synchronising., Metering (CHA) on-site | 30/11/2019 | 30/11/2019 | 30/04/2019 | 30/04/2019 | 0 | TK_Complete
SI1CJF4-25 | TT_FinMile | HRSG Electrical &amp; I&amp;C Equipment on-site | 30/11/2019 | 30/11/2019 | 14/01/2019 | 14/01/2019 | 0 | TK_Complete
SI1CJT4-25 | TT_FinMile | SFC/SEE Cubicle (CJT) on-site | 30/11/2019 | 30/11/2019 | 27/03/2019 | 27/03/2019 | 0 | TK_Complete
SI1HA-4C25 | TT_FinMile | HRSG Modules on-site | 26/04/2018 | 26/04/2018 | 30/03/2018 | 30/03/2018 | 0 | TK_Complete
SI1HA-4C40 | TT_Mile | Equipment Delivery by Siemens - HRSG Modules | 26/04/2018 | 26/04/2018 | 30/03/2018 | 30/03/2018 | 0 | TK_Complete
SI1HA-4D25 | TT_FinMile | HRSG Drums on-site | 26/04/2018 | 26/04/2018 | 27/04/2018 | 27/04/2018 | 0 | TK_Complete
SI1HA-4D40 | TT_Mile | Equipment Delivery by Siemens - Drums of HRSG | 26/04/2018 | 26/04/2018 | 27/04/2018 | 27/04/2018 | 0 | TK_Complete
SI1HAD4E25 | TT_FinMile | HRSG Piping Material on-site | 06/11/2018 | 06/11/2018 | 01/11/2018 | 01/11/2018 | 0 | TK_Complete
SI1HAD4E40 | TT_Mile | Equipment Delivery by Siemens - Piping Material HRSG | 06/11/2018 | 06/11/2018 | 01/10/2018 | 01/10/2018 | 0 | TK_Complete
SI1HB-4A25 | TT_FinMile | HRSG Main Steel Structure (Main Frame/Casing) on-site | 03/03/2018 | 03/03/2018 | 08/03/2018 | 08/03/2018 | 0 | TK_Complete
SI1HB-4A40 | TT_Mile | Equipment Delivery by Siemens - Main Steel Structure HRSG | 05/03/2018 | 05/03/2018 | 03/03/2018 | 03/03/2018 | 0 | TK_Complete
SI1HB-4C25 | TT_FinMile | HRSG Steel Structure - Secondary Steel on-site | 18/05/2018 | 18/05/2018 | 19/05/2018 | 19/05/2018 | 0 | TK_Complete
SI1HB-4D25 | TT_FinMile | HRSG Steel Structure - Stack on-site | 30/08/2018 | 30/08/2018 | 29/08/2018 | 29/08/2018 | 0 | TK_Complete
SI1HB-4E25 | TT_FinMile | HRSG Inlet Duct on-site | 01/03/2018 | 01/03/2018 | 03/03/2018 | 03/03/2018 | 0 | TK_Complete
SI1HSJ4-25 | TT_FinMile | SCR Unit on-site | 30/11/2019 | 30/11/2019 | 04/11/2019 | 04/11/2019 | 0 | TK_Complete
SI1HSJ4-42 | TT_FinMile | SCR Catalyst on-site | 28/03/2020 | 28/03/2020 | 20/01/2020 | 20/01/2020 | 0 | TK_Complete
SI1LAC4-40 | TT_FinMile | LAC10Y Module on-site | 30/11/2019 | 30/11/2019 | 15/02/2019 | 15/02/2019 | 0 | TK_Complete
SI1LBG4C40 | TT_FinMile | Electrical Superheater LBG on-site | 16/03/2018 | 16/03/2018 | 15/03/2018 | 15/03/2018 | 0 | TK_Complete
SI1LBH4D25 | TT_FinMile | Clean Drain Flush Tank (LBH) on-site | 28/03/2020 | 28/03/2020 | 15/06/2018 | 15/06/2018 | 0 | TK_Complete
SI1LCA4-40 | TT_FinMile | LCA50Y Module on-site | 28/03/2020 | 28/03/2020 | 27/02/2019 | 27/02/2019 | 0 | TK_Complete
SI1LCA4B25 | TT_FinMile | Condensate Recirculating Pump (LCA51) on-site | 01/03/2018 | 01/03/2018 | 10/02/2018 | 10/02/2018 | 0 | TK_Complete
SI1LCB4B40 | TT_FinMile | Condensate Extraction Pump (LCB) on-site (arrived on June 1) | 30/11/2019 | 30/11/2019 | 10/01/2019 | 10/01/2019 | 0 | TK_Complete
SI1LCL4B40 | TT_FinMile | Steam Generator Drain Pump (LCL) on-site | 16/03/2018 | 16/03/2018 | 15/03/2018 | 15/03/2018 | 0 | TK_Complete
SI1LD-4-40 | TT_FinMile | Condensate Polishing Plant (LD) on-site | 28/03/2020 | 28/03/2020 | 30/04/2018 | 30/04/2018 | 0 | TK_Complete
SI1LDK4B40 | TT_FinMile | Condensate Polishing Pump (LDK) on-site | 26/04/2018 | 26/04/2018 | 30/04/2018 | 30/04/2018 | 0 | TK_Complete
SI1MA-4-25 | TT_Mile | Equipment Delivery by Siemens - STEAM TURBINE MA- (HP/IP) (incl. FCA) | 26/04/2018 | 26/04/2018 | 28/03/2018 | 28/03/2018 | 0 | TK_Complete
SI1MA-4-45 | TT_Mile | Equipment Delivery by Siemens - ST MA- (LP OUTER CASING) | 26/04/2018 | 26/04/2018 | 28/03/2018 | 28/03/2018 | 0 | TK_Complete
SI1MA-4-55 | TT_Mile | Equipment Delivery by Siemens - ST MA- (LP-ROTOR, INNERCASING) | 26/04/2018 | 26/04/2018 | 28/03/2018 | 28/03/2018 | 0 | TK_Complete
SI1MA-4-59 | TT_Mile | Equipment Delivery by Siemens - Steam Turbine MA- (HP/IP) AUX. (Incl. FCA) | 30/08/2018 | 30/08/2018 | 31/07/2018 | 31/07/2018 | 0 | TK_Complete
SI1MAD4-25 | TT_Mile | Equipment Delivery by Siemens - Steam Turbine Bearings MAD | 01/03/2018 | 01/03/2018 | 09/01/2018 | 09/01/2018 | 0 | TK_Complete
SI1MAG4-40 | TT_Mile | Equipment Delivery by Siemens - Steam Condenser MAG | 02/04/2018 | 02/04/2018 | 02/04/2018 | 02/04/2018 | 0 | TK_Complete
SI1MAJ4-44 | TT_FinMile | Removal System (MAJ) on-site | 02/04/2018 | 02/04/2018 | 23/03/2018 | 23/03/2018 | 0 | TK_Complete
SI1MAL4-25 | TT_FinMile | MAL00Y Module on-site | 27/04/2018 | 27/04/2018 | 27/04/2018 | 27/04/2018 | 0 | TK_Complete
SI1MAL4-40 | TT_Mile | Equipment Delivery by Siemens - Steam Turbine Drain Skid MAL00Y Module | 26/04/2018 | 26/04/2018 | 27/04/2018 | 27/04/2018 | 0 | TK_Complete
SI1MAV4-40 | TT_Mile | Equipment Delivery by Siemens - ST Lube oil Module MAV | 26/04/2018 | 26/04/2018 | 31/03/2018 | 31/03/2018 | 0 | TK_Complete
SI1MAW4-40 | TT_Mile | Equipment Delivery by Siemens - ST GLAND STEAM CONDENSER MAW | 26/04/2018 | 26/04/2018 | 28/03/2018 | 28/03/2018 | 0 | TK_Complete
SI1MAX4-40 | TT_Mile | Equipment Delivery by Siemens - ST Hydraulic System MAX | 26/04/2018 | 26/04/2018 | 28/03/2018 | 28/03/2018 | 0 | TK_Complete
SI1MB-4E25 | TT_Mile | Equipment Delivery by Siemens - Gas Turbine Auxiliaries MB | 30/08/2018 | 30/08/2018 | 31/07/2018 | 31/07/2018 | 0 | TK_Complete
SI1MB-4E27 | TT_FinMile | GT Interconnection Piping (MB) on-site | 02/04/2018 | 02/04/2018 | 24/03/2018 | 24/03/2018 | 0 | TK_Complete
SI1MBA4-25 | TT_Mile | Equipment Delivery by Siemens - Gas Turbine MB | 26/04/2018 | 26/04/2018 | 27/03/2018 | 27/03/2018 | 0 | TK_Complete
SI1MBL4-40 | TT_Mile | Equipment Delivery by Siemens - GT Air Intake System MBL | 23/03/2018 | 23/03/2018 | 31/03/2018 | 31/03/2018 | 0 | TK_Complete
SI1MBR4-40 | TT_FinMile | Exhaust Gas Diffuser (MBR) on-site | 01/03/2018 | 01/03/2018 | 02/03/2018 | 02/03/2018 | 0 | TK_Complete
SI1MBR4-42 | TT_FinMile | Exhaust Gas Manifold (MBR) on-site | 07/03/2018 | 07/03/2018 | 10/03/2018 | 10/03/2018 | 0 | TK_Complete
SI1MKA4-25 | TT_Mile | Equipment Delivery by Siemens - Generator MK | 26/04/2018 | 26/04/2018 | 28/03/2018 | 28/03/2018 | 0 | TK_Complete
SI1MKA4E25 | TT_Mile | Equipment Delivery by Siemens - Generator Skids MKA | 29/09/2018 | 29/09/2018 | 01/08/2018 | 01/08/2018 | 0 | TK_Complete
SI1MKC4-25 | TT_Mile | Equipment Delivery by Siemens - SEE TRANSFORMER MKC / SFC TRANSFORMER MBJ | 26/04/2018 | 26/04/2018 | 02/05/2018 | 02/05/2018 | 0 | TK_Complete
SI1MPB4-25 | TT_FinMile | Noise Protection System (MPB20) on-site | 30/04/2018 | 30/04/2018 | 21/03/2018 | 21/03/2018 | 0 | TK_Complete
SI1MPB4E25 | TT_Mile | Equipment Delivery by Siemens - GT Enclosure Incl. Ventilation MPB/SAM | 01/03/2018 | 01/03/2018 | 22/02/2018 | 22/02/2018 | 0 | TK_Complete
SI1PAA4-25 | TT_FinMile | CW Bar Screen for (PAB) on-site | 26/05/2018 | 26/05/2018 | 29/05/2018 | 29/05/2018 | 0 | TK_Complete
SI1PAA4-40 | TT_Mile | Equipment Delivery by Siemens - Cooling Water Bar Screen for PAB System | 26/05/2018 | 26/05/2018 | 29/05/2018 | 29/05/2018 | 0 | TK_Complete
SI1PAA4-50 | TT_Mile | Equipment Delivery UMC Crane | 26/04/2018 | 26/04/2018 | 01/01/2018 | 01/01/2018 | 0 | TK_Complete
SI1PAC4B40 | TT_FinMile | Circ CW Pump (PAC) on-site | 30/11/2019 | 30/11/2019 | 06/07/2019 | 06/07/2019 | 0 | TK_Complete
SI1PAC4E40 | TT_FinMile | Embedded Parts Pump (PAC) on-site | 30/11/2019 | 30/11/2019 | 06/07/2019 | 06/07/2019 | 0 | TK_Complete
SI1PAH4-25 | TT_Mile | Equipment Delivery by Siemens - Condenser Tube Cleaning System PAH/PCH | 01/03/2018 | 01/03/2018 | 17/01/2018 | 17/01/2018 | 0 | TK_Complete
SI1PBB4B45 | TT_FinMile | Debris Filter (PBB) on-site | 01/03/2018 | 01/03/2018 | 17/01/2018 | 17/01/2018 | 0 | TK_Complete
SI1PCB4B25 | TT_FinMile | Service Cooling Water Pump (PCB) on-site | 12/03/2018 | 12/03/2018 | 14/03/2018 | 14/03/2018 | 0 | TK_Complete
SI1PDB4-25 | TT_FinMile | Debris Filer (PDB) on-site | 02/04/2018 | 02/04/2018 | 20/03/2018 | 20/03/2018 | 0 | TK_Complete
SI1PGB4B25 | TT_FinMile | CCW Pumps (PGB) on-site | 02/04/2018 | 02/04/2018 | 13/03/2018 | 13/03/2018 | 0 | TK_Complete
SI1PGB4C25 | TT_FinMile | Heat Exchanger (PGB) on-site | 02/04/2018 | 02/04/2018 | 13/03/2018 | 13/03/2018 | 0 | TK_Complete
SI1PGB4D25 | TT_FinMile | Expansion Tank (PGB) on-site | 02/04/2018 | 02/04/2018 | 20/03/2018 | 20/03/2018 | 0 | TK_Complete
SI1PXB4-40 | TT_FinMile | PXB00Y Module on-site | 30/11/2019 | 30/11/2019 | 04/09/2019 | 04/09/2019 | 0 | TK_Complete
SI1QC-4-40 | TT_FinMile | Dosing Container (QC) on-site | 30/11/2019 | 30/11/2019 | 26/02/2019 | 26/02/2019 | 0 | TK_Complete
SI1QU-4-40 | TT_FinMile | Sampling Container (QU) on-site | 30/11/2019 | 30/11/2019 | 26/02/2019 | 26/02/2019 | 0 | TK_Complete
SI1SCA4-40 | TT_FinMile | Compressed Air System (SCA) on-site | 30/11/2019 | 30/11/2019 | 02/01/2019 | 02/01/2019 | 0 | TK_Complete
SI1SGJ4-25 | TT_Mile | Equipment Delivery by Siemens - Econopac fire Protection System CYE/ SGJ | 30/11/2019 | 30/11/2019 | 07/03/2019 | 07/03/2019 | 0 | TK_Complete
SI1SMM4-25 | TT_FinMile | Cranes SMM01/ 02 for (UMC) on-site | 01/03/2018 | 01/03/2018 | 01/01/2018 | 01/01/2018 | 0 | TK_Complete
SI1SMM4A25 | TT_FinMile | Cranes SMM03 for (UMC) on-site | 01/03/2018 | 01/03/2018 | 15/01/2018 | 15/01/2018 | 0 | TK_Complete
SI1SMQ4A45 | TT_FinMile | Crane SMQ for UQA on-site | 30/11/2019 | 30/11/2019 | 18/05/2019 | 18/05/2019 | 0 | TK_Complete
SI1STG-4-44 | TT_FinMile | Laboratory Container on-site STG | 30/11/2019 | 30/11/2019 | 30/04/2019 | 30/04/2019 | 0 | TK_Complete
SI1UBA4G25 | TT_Mile | Equipment Delivery by Siemens - Cabinets for I&amp;C 10UBA Building | 28/03/2020 | 28/03/2020 | 20/02/2019 | 20/02/2019 | 0 | TK_Complete
SI1UHW3B25 | TT_FinMile | Steel Structure (UHW) on-site | 30/11/2019 | 30/11/2019 | 05/10/2019 | 05/10/2019 | 0 | TK_Complete
SI1ULA3B25 | TT_FinMile | Steel Structure (ULA) on-site | 30/11/2019 | 30/11/2019 | 15/02/2019 | 15/02/2019 | 0 | TK_Complete
SI1UMC4X40 | TT_Mile | Equipment Delivery by Siemens - Module Pipe Rack UMCM1Y | 26/05/2018 | 26/05/2018 | 28/05/2018 | 28/05/2018 | 0 | TK_Complete
SI1UMC4Y40 | TT_Mile | Equipment Delivery by Siemens - Module Pipe Rack UMCL1Y | 27/04/2018 | 27/04/2018 | 27/04/2018 | 27/04/2018 | 0 | TK_Complete
SI1UMY4-42 | TT_FinMile | UMY00Y Module on-site | 29/09/2018 | 29/09/2018 | 06/09/2018 | 06/09/2018 | 0 | TK_Complete
SI1UPY4-40 | TT_Mile | Equipment Delivery by Siemens - Condenser Tube Cleaning System PAH - Module UPY00Y | 30/11/2019 | 30/11/2019 | 15/11/2018 | 15/11/2018 | 0 | TK_Complete
SP1MA-3-80 | TT_Mile | Equipment Delivery by Siemens - STEAM TURBINE MA- (HP/IP) EX WORKS | 19/03/2018 | 19/03/2018 | 12/12/2017 | 12/12/2017 | 0 | TK_Complete
MWS03.1010 | TT_Task | Mobilisation of the Crane Barge to Site | 13/03/2018 | 10/07/2018 | 14/02/2018 | 15/03/2018 | 0 | TK_Complete
MWS03.1020 | TT_Task | Mobilisation of the Land based cranes to Site | 01/03/2018 | 08/03/2018 | 19/03/2018 | 23/03/2018 | 0 | TK_Complete
ITP1000 | TT_Task | ITP for - (00BAW-01) Earthing Grid for back-energizing | 30/08/2018 | 24/09/2018 | 23/08/2018 | 30/11/2019 | 0 | TK_Complete
ITP1010 | TT_Task | ITP for - (00BAW-02) Earthing Grid Complete | 30/08/2018 | 24/09/2018 | 23/08/2018 | 30/11/2019 | 0 | TK_Complete
ITP1020 | TT_Task | ITP for - (00BAW-03) Lightening Protection | 30/08/2018 | 24/09/2018 | 23/08/2018 | 30/11/2019 | 0 | TK_Complete
ITP1030 | TT_Task | ITP for - (10MA-01) HP-/ IP-/ LP-Turbine 10MAA/MAB/MAC | 02/12/2019 | 25/12/2019 | 07/05/2019 | 14/06/2019 | 0 | TK_Complete
ITP1050 | TT_Task | ITP for - (10MAN) ST Bypass System | 30/08/2018 | 24/09/2018 | 07/06/2018 | 29/08/2018 | 0 | TK_Complete
ITP1070 | TT_Task | ITP for - (10MAG) Condensing System | 10/04/2018 | 04/05/2018 | 28/02/2018 | 23/03/2018 | 0 | TK_Complete
ITP1080 | TT_Task | ITP for - (10MAV) Lube and Lifting Oil System Incl. Generator and GT | 05/07/2018 | 31/07/2018 | 09/05/2018 | 30/05/2018 | 0 | TK_Complete
ITP1090 | TT_Task | ITP for - (10MAW) Gland / Leakage Steam System | 03/09/2018 | 26/09/2018 | 25/06/2018 | 17/07/2018 | 0 | TK_Complete
ITP1100 | TT_Task | ITP for - (10MAX) ST Hydraulic System | 03/09/2018 | 26/09/2018 | 25/06/2018 | 17/07/2018 | 0 | TK_Complete
ITP1120 | TT_Task | ITP for - (10MKA) Generator Incl. Bearing System 10 MKD | 02/12/2019 | 25/12/2019 | 08/05/2018 | 05/06/2018 | 0 | TK_Complete
ITP1130 | TT_Task | ITP for - (10MKF) Generator Primary Water Cooling System | 03/07/2019 | 29/07/2019 | 12/05/2018 | 05/06/2018 | 0 | TK_Complete
ITP1140 | TT_Task | ITP for - (10MKG) Gas Supply System | 01/08/2018 | 27/08/2018 | 12/05/2018 | 05/06/2018 | 0 | TK_Complete
ITP1150 | TT_Task | ITP for - (10MKQ) Waste Gas System | 03/07/2019 | 29/07/2019 | 31/05/2018 | 14/07/2018 | 0 | TK_Complete
ITP1160 | TT_Task | ITP for - (10MKW) Seal Oil Supply System | 02/07/2018 | 26/07/2018 | 11/05/2018 | 30/06/2018 | 0 | TK_Complete
ITP1180 | TT_Task | ITP for - (10MBA) GT Including Combustion Chamber | 02/12/2019 | 25/12/2019 | 08/05/2018 | 14/06/2018 | 0 | TK_Complete
ITP1190 | TT_Task | ITP for - (10MBX) GT Hydraulic Oil | 11/07/2018 | 03/08/2018 | 19/05/2018 | 28/06/2018 | 0 | TK_Complete
ITP1200 | TT_Task | ITP for - (10MBP) GT Natural Gas Incl. Draining System MBP40 | 03/07/2019 | 29/07/2019 | 01/06/2018 | 13/07/2018 | 0 | TK_Complete
ITP1210 | TT_Task | ITP for - (10MBN) GT Fuel Oil Injection System | 03/07/2019 | 29/07/2019 | 19/05/2018 | 16/07/2018 | 0 | TK_Complete
ITP1220 | TT_Task | ITP for - (10MBH) GT Cooling Air System | 05/07/2018 | 31/07/2018 | 19/05/2018 | 15/06/2018 | 0 | TK_Complete
ITP1230 | TT_Task | ITP for - (10MBA18) Compressor Cleaning Package | 02/12/2019 | 25/12/2019 | 13/06/2018 | 21/06/2018 | 0 | TK_Complete
ITP1240 | TT_Task | ITP for - (10MBA5x) GT Hydraulic Clearance Optimization Supply System | 02/12/2019 | 25/12/2019 | 02/06/2018 | 12/07/2018 | 0 | TK_Complete
ITP1250 | TT_Task | ITP for - (10MBX2x) GT Pneumatic System | 26/06/2018 | 19/07/2018 | 19/05/2018 | 28/06/2018 | 0 | TK_Complete
ITP1280 | TT_Task | ITP for - (10MBL) Air Intake System | 02/12/2019 | 25/12/2019 | 07/05/2018 | 14/06/2018 | 0 | TK_Complete
ITP1290 | TT_Task | ITP for - (10MBU) GT NOX Water Injection System | 02/12/2019 | 25/12/2019 | 19/05/2018 | 15/06/2018 | 0 | TK_Complete
ITP1330 | TT_Task | ITP for - (10LCA) Main Condensate Pumps and Supply System for Min. Flow Operation Incl. | 17/09/2018 | 10/10/2018 | 04/06/2018 | 16/07/2018 | 0 | TK_Complete
ITP1340 | TT_Task | ITP for - (10PGB) Closed Cooling Water System | 02/12/2019 | 25/12/2019 | 04/06/2018 | 09/08/2018 | 0 | TK_Complete
ITP1350 | TT_Task | ITP for - (10PCB) Service Cooling Water System Incl. 10PDB | 12/11/2018 | 06/12/2018 | 04/06/2018 | 06/08/2018 | 0 | TK_Complete
ITP1390 | TT_Task | ITP for - (10SGA) FF Indoor Hydrants 10SGA Inside 10ULA, 10UHA, 10UMC | 22/11/2018 | 18/12/2018 | 09/07/2018 | 27/07/2018 | 0 | TK_Complete
ITP1400 | TT_Task | ITP for - (10SGC-02) FF Spray Deluge System 10SGC for Lube Oil / Seal Oil System | 13/11/2018 | 07/12/2018 | 19/07/2018 | 03/08/2018 | 0 | TK_Complete
ITP1580 | TT_Task | ITP for - (10BAT) Main Transformer 10BAT01/10BBT01 | 30/08/2018 | 24/09/2018 | 16/08/2018 | 30/11/2019 | 0 | TK_Complete
ITP1600 | TT_Task | ITP for - (10MKC) SEE/SFC Equipment Excitation Transformer MKC; SFC Transformer MBJ | 13/11/2018 | 06/12/2018 | 17/08/2018 | 28/08/2018 | 0 | TK_Complete
ITP1610 | TT_Task | ITP for - (10SGC-01) FF Spary Deluge System for BAT/ BBT SGC | 20/03/2019 | 12/04/2019 | 19/07/2018 | 03/08/2018 | 0 | TK_Complete
ITP1620 | TT_Task | ITP for - (10LD) Condensate Polishing Plant | 30/08/2018 | 24/09/2018 | 04/06/2018 | 16/07/2018 | 0 | TK_Complete
ITP1630 | TT_Task | ITP for - (10LDK) Condensate Polishing System | 01/08/2018 | 27/08/2018 | 04/06/2018 | 16/07/2018 | 0 | TK_Complete
ITP1660 | TT_Task | ITP for - (00SGM) FF Protection System for UBN | 28/11/2018 | 21/12/2018 | 19/07/2018 | 01/08/2018 | 0 | TK_Complete
ITP1670 | TT_Task | ITP for - (10BFT01) LV-Transformer BFT01 (BHT) | 06/07/2018 | 31/07/2018 | 06/07/2018 | 18/07/2018 | 0 | TK_Complete
ITP1680 | TT_Task | ITP for - (10BFT02) LV-Transformer BFT02 (BHT) | 27/11/2018 | 20/12/2018 | 03/08/2018 | 30/11/2019 | 0 | TK_Complete
ITP1690 | TT_Task | ITP for - (00BBT) MV Transformer BBT01 | 27/11/2018 | 20/12/2018 | 29/08/2018 | 30/11/2019 | 0 | TK_Complete
ITP1710 | TT_Task | ITP for - (10MBR) Exhaust Gas System | 10/08/2018 | 04/09/2018 | 11/05/2018 | 05/06/2018 | 0 | TK_Complete
ITP1720 | TT_Task | ITP for - (10EK) Fuel Gas Supply System for GT10 | 11/07/2018 | 03/08/2018 | 22/06/2018 | 31/07/2018 | 0 | TK_Complete
ITP1750 | TT_Task | ITP for - (10HAD10) HRSG HP Steam | 17/10/2018 | 09/11/2018 | 23/02/2018 | 28/06/2018 | 0 | TK_Complete
ITP1760 | TT_Task | ITP for - (10HAD50) HRSG IP Steam | 17/10/2018 | 09/11/2018 | 23/02/2018 | 28/06/2018 | 0 | TK_Complete
ITP1770 | TT_Task | ITP for - (10HAD80) HRSG LP Steam | 17/10/2018 | 09/11/2018 | 23/02/2018 | 28/06/2018 | 0 | TK_Complete
ITP1790 | TT_Task | ITP for - (10HBK) HRSG Exhaust Gas System | 30/08/2018 | 24/09/2018 | 12/03/2018 | 28/06/2018 | 0 | TK_Complete
ITP1830 | TT_Task | ITP for - (10LCL) HRSG Drains System | 15/08/2018 | 07/09/2018 | 04/06/2018 | 28/06/2018 | 0 | TK_Complete
ITP1840 | TT_Task | ITP for - (10LCA-02) Condensate Supply System incl. Preheater 10HAA10 | 01/08/2018 | 27/08/2018 | 02/06/2018 | 16/07/2018 | 0 | TK_Complete
ITP1860 | TT_Task | ITP for - (10LAC) Feedwater Pump | 03/07/2019 | 29/07/2019 | 02/06/2018 | 30/07/2018 | 0 | TK_Complete
ITP1870 | TT_Task | ITP for - (10QCB) Hydrazine Dosing QC | 19/09/2018 | 12/10/2018 | 29/06/2018 | 07/08/2018 | 0 | TK_Complete
ITP1880 | TT_Task | ITP for - (10QCC) Trisodium Phosphate Dosing QC | 19/09/2018 | 12/10/2018 | 29/06/2018 | 07/08/2018 | 0 | TK_Complete
ITP1890 | TT_Task | ITP for - (10QCD) Ammonia Dosing QC | 11/10/2018 | 05/11/2018 | 29/06/2018 | 07/08/2018 | 0 | TK_Complete
ITP1900 | TT_Task | ITP for - (10QU) Sampling Container QC | 19/09/2018 | 12/10/2018 | 20/08/2018 | 11/09/2018 | 0 | TK_Complete
ITP2000 | TT_Task | ITP for - (00LBG) Auxiliary Steam System | 30/08/2018 | 24/09/2018 | 03/07/2018 | 08/08/2018 | 0 | TK_Complete
ITP2020 | TT_Task | ITP for - (10PAH) Condenser Tube Cleaning System | 01/08/2018 | 27/08/2018 | 12/05/2018 | 06/06/2018 | 0 | TK_Complete
ITP2040 | TT_Task | ITP for - (10PAB-01) Circulating Water System incl. Cooling Water Pumps | 26/06/2018 | 19/07/2018 | 04/06/2018 | 17/07/2018 | 0 | TK_Complete
ITP2050 | TT_Task | ITP for - (00PAA) Cooling Water Screening Plant | 30/08/2018 | 24/09/2018 | 03/08/2018 | 10/08/2018 | 0 | TK_Complete
ITP2060 | TT_Task | ITP for - (00PUR) Cathodic Protection System for Cooling Water Inlet | 12/09/2018 | 05/10/2018 | 01/06/2018 | 13/07/2018 | 0 | TK_Complete
ITP2080 | TT_Task | ITP for - (10PUR) Cathodic Protection System for Cooling Water Side of Condenser | 12/09/2018 | 05/10/2018 | 01/06/2018 | 13/07/2018 | 0 | TK_Complete
ITP2130 | TT_Task | ITP for - (00MBU) NOX Water Forwarding System incl. Supply Lines to GT Skid | 06/08/2018 | 29/08/2018 | 19/05/2018 | 15/06/2018 | 0 | TK_Complete
ITP2180 | TT_Task | ITP for - (00STG) Laboratory Container STG | 01/08/2018 | 27/08/2018 | 04/06/2018 | 17/07/2018 | 0 | TK_Complete
ITP2200 | TT_Task | ITP for - (10SGC-02) FF Spray Deluge Systems for 00UEH/UEJ/UEK Area | 13/11/2018 | 07/12/2018 | 19/07/2018 | 03/08/2018 | 0 | TK_Complete
ITP2220 | TT_Task | ITP for - (00EG-01) Fuel Oil Forwarding Station and Storage Tank | 12/09/2018 | 05/10/2018 | 25/05/2018 | 14/06/2018 | 0 | TK_Complete
ITP2230 | TT_Task | ITP for - (00EG-02) Fuel Oil Forwarding System incl. Supply Lines up to Fuel Oil | 26/06/2018 | 19/07/2018 | 25/05/2018 | 25/07/2018 | 0 | TK_Complete
ITP2360 | TT_Task | ITP for - (10MAD) ST Bearing System | 30/08/2018 | 24/09/2018 | 07/05/2018 | 29/08/2018 | 0 | TK_Complete
ITP2390 | TT_Task | ITP for - (10HAA) HRSG | 09/02/2018 | 06/03/2018 | 10/01/2018 | 23/03/2018 | 0 | TK_Complete
MS1050 | TT_Task | Method Statement - (10MAN) ST Bypass System | 30/08/2018 | 24/09/2018 | 08/06/2018 | 06/08/2018 | 0 | TK_Complete
MS1070 | TT_Task | Method Statement - (10MAG) Condensing System | 10/04/2018 | 04/05/2018 | 02/03/2018 | 30/03/2018 | 0 | TK_Complete
MS1120 | TT_Task | Method Statement - (10MKA) Generator Incl. Bearing System 10 MKD | 26/07/2018 | 20/08/2018 | 11/06/2018 | 26/06/2018 | 0 | TK_Complete
MS1790 | TT_Task | Method Statement - (10HBK) HRSG Exhaust Gas System | 30/08/2018 | 24/09/2018 | 02/07/2018 | 14/07/2018 | 0 | TK_Complete
MS2390 | TT_Task | Method Statement - (10HAA) HRSG | 09/02/2018 | 22/02/2018 | 10/01/2018 | 07/03/2018 | 0 | TK_Complete
10MKB90 | TT_Task | Erect Annex Hall D5/D9/D12 Secondary Steel Structure | 21/01/2019 | 22/03/2019 | 21/01/2019 | 15/05/2019 | 0 | TK_Complete
CP1HB-6A25 | TT_FinMile | Foundations for HRSG | 01/03/2018 | 01/03/2018 | 08/03/2018 | 08/03/2018 | 0 | TK_Complete
CP1UMC5A45 | TT_FinMile | Turboset Foundation (UMC) (Completion of Foundatio Repair) | 26/06/2018 | 26/06/2018 | 14/06/2018 | 14/06/2018 | 0 | TK_Complete
KD_B01 | TT_FinMile | B1 - Complete Foundation Structures and Pile Caps for Stack, Diffuser and HRSG Main Plant with Lift and Staircase | 05/03/2018 | 05/03/2018 | 08/03/2018 | 08/03/2018 | 0 | TK_Complete
KD_B02 | TT_FinMile | B2 - Construct Duct Bank Underneath the Diffuser | 02/04/2018 | 02/04/2018 | 07/02/2018 | 07/02/2018 | 0 | TK_Complete
KD_B03 | TT_FinMile | B3 - Construct temp.pad foundation for heavy lift crane &amp; temp.H/O Area1a for M&amp;E Contractor (Test Complete by KSS) | 26/06/2018 | 26/06/2018 | 07/06/2018 | 07/06/2018 | 0 | TK_Complete
KD_B05 | TT_FinMile | B5 - Construct Condensate Pit | 31/12/2018 | 31/12/2018 | 28/12/2018 | 28/12/2018 | 0 | TK_Complete
KD_B06 | TT_FinMile | B6 - Construct Turboset foundation and supporting pile cap (Completion of Foundation Repair by Civil Contractor) | 01/06/2018 | 01/06/2018 | 14/06/2018 | 14/06/2018 | 0 | TK_Complete
KD_B07 | TT_FinMile | B7 - Construct Pile Caps, Tie Beams&amp; GF Slab of Turbine Hall Building | 31/10/2018 | 31/10/2018 | 31/08/2018 | 31/08/2018 | 0 | TK_Complete
KD_B12 | TT_FinMile | HRSG East Side Urea Decomposition Chamber Foundation | 02/07/2020 | 02/07/2020 | 28/10/2019 | 28/10/2019 | 0 | TK_Complete
KD_C02 | TT_FinMile | C2 - Complete ALL building works incl. roof &amp; cladding surrounding &amp; above Turboset main equipment area | 02/07/2020 | 02/07/2020 | 30/04/2019 | 30/04/2019 | 0 | TK_Complete
KD_C03 | TT_FinMile | C3 - Construct Polishing Pit, G/F Slab for Condensate Polishing Plant area of T/H | 02/07/2020 | 02/07/2020 | 30/09/2018 | 30/09/2018 | 0 | TK_Complete
KD_C04 | TT_FinMile | C4 - Install and T&amp;C two 250t O/H cranes within Turbine Hall and H/O to M&amp;E Contractor | 31/08/2018 | 31/08/2018 | 31/08/2018 | 31/08/2018 | 0 | TK_Complete
KD_C06 | TT_FinMile | C6 - Construct Foundations &amp; Plinths for Support Steel for A/G Sections of CWP South of T/H | 02/07/2020 | 02/07/2020 | 07/03/2019 | 07/03/2019 | 0 | TK_Complete
KD_C07 | TT_FinMile | C7 - Complete ALL civil works incl. foundations, pile cap, blast walls &amp; hard standings for Generator Transformer Area | 01/04/2019 | 01/04/2019 | 16/02/2019 | 16/02/2019 | 0 | TK_Complete
KD_C17 | TT_FinMile | Turbine Bldg. GL 5-7 Mechanical Annex | 31/12/2018 | 31/12/2018 | 28/12/2018 | 28/12/2018 | 0 | TK_Complete
KD_C27 | TT_FinMile | Turbine Bldg. GL 7-10 Condensate Polishing Plant | 02/07/2020 | 02/07/2020 | 15/02/2019 | 15/02/2019 | 0 | TK_Complete
KD_D01 | TT_FinMile | D1 - Complete ALL remaining platforms within Turbine Hall Building (civil scope) | 31/12/2018 | 31/12/2018 | 31/12/2018 | 31/12/2018 | 0 | TK_Complete
KD_D02 | TT_FinMile | D2 - Complete ALL building works for Switchgear Block | 02/07/2020 | 02/07/2020 | 14/02/2019 | 14/02/2019 | 0 | TK_Complete
KD_D04 | TT_FinMile | D4 - Construct Duct Bank between Switchgear Building and Generator Transformer Area | 02/07/2020 | 02/07/2020 | 12/02/2019 | 12/02/2019 | 0 | TK_Complete
KD_D05 | TT_FinMile | D5 - Construct Boiler Blow Down Pit | 31/12/2018 | 31/12/2018 | 10/11/2018 | 10/11/2018 | 0 | TK_Complete
KD_D06 | TT_FinMile | D6 - Complete foundations and plinths for ALL equipment, pipe bridge and sleeper way to the west of HRSG Area | 31/10/2018 | 31/10/2018 | 31/10/2018 | 31/10/2018 | 0 | TK_Complete
KD_D07 | TT_FinMile | D7 - Complete foundations and bund walls for Outdoor Dirty and Clean Oil Tanks | 02/07/2020 | 02/07/2020 | 25/04/2019 | 25/04/2019 | 0 | TK_Complete
KD_D08 | TT_FinMile | D8 - Complete foundations and plinths for LV Auxiliary Power Transformers | 02/07/2020 | 02/07/2020 | 04/02/2019 | 04/02/2019 | 0 | TK_Complete
KD_D09 | TT_FinMile | D9 - Complete foundation and plinths for Emergency Power Generator | 02/07/2020 | 02/07/2020 | 16/07/2019 | 16/07/2019 | 0 | TK_Complete
KD_D10 | TT_FinMile | D10 - Complete foundation and plinths for Gas Final Filter Equipment | 02/07/2020 | 02/07/2020 | 30/04/2019 | 30/04/2019 | 0 | TK_Complete
KD_D11 | TT_FinMile | D11 - Complete foundations and plinths for Close Cooling Water Structure | 02/07/2020 | 02/07/2020 | 04/03/2019 | 04/03/2019 | 0 | TK_Complete
KD_E01 | TT_FinMile | E1 - Complete foundations and plinths for Effluent Storage Tanks | 02/07/2020 | 02/07/2020 | 25/04/2019 | 25/04/2019 | 0 | TK_Complete
KD_E02 | TT_FinMile | E2 - Complete ALL outdoor pipe trenches including 10UEZ01, 10UEZ02 and 10UGZ | 02/07/2020 | 02/07/2020 | 14/02/2019 | 14/02/2019 | 0 | TK_Complete
KD_E03 | TT_FinMile | E3 - Complete foundation &amp; plinths for CEMS Panels, Compressed Air Sys, N2 Blanket Sys, struc.for emerg.CO2 &amp; | 31/12/2018 | 31/12/2018 | 31/12/2018 | 31/12/2018 | 0 | TK_Complete
KD_E04 | TT_FinMile | E4 - Complete foundation &amp; plinths for Fuel Gas Purge Air, Gas Receiving Station, Fuel Gas Blending System | 02/07/2020 | 02/07/2020 | 14/02/2019 | 14/02/2019 | 0 | TK_Complete
KD_E05 | TT_FinMile | E5 - Complete Foundations &amp; Plinths for Chemical Unloading Bay, Urea StorageTank, Ammonia, | 31/12/2018 | 31/12/2018 | 21/01/2019 | 21/01/2019 | 0 | TK_Complete
KD_E07 | TT_FinMile | E7 - Complete ALL building services for Switchgear Block incl' T&amp;C | 02/07/2020 | 02/07/2020 | 14/02/2019 | 14/02/2019 | 0 | TK_Complete
KD_F01 | TT_FinMile | F1 - Complete Chem.Contaminated Drainage Sys incl. pipe trenches, Effluent Disposal U/G struc, Neutralization Sys | 02/07/2020 | 02/07/2020 | 25/04/2019 | 25/04/2019 | 0 | TK_Complete
KD_F02 | TT_FinMile | F2 - Complete Oil Contaminated Drainage System incl' external drainage, oil interceptor and pipe trecnhes | 02/07/2020 | 02/07/2020 | 14/02/2019 | 14/02/2019 | 0 | TK_Complete
KD_F07 | TT_FinMile | F6 - Complete Cooling Water Pumping Station and Diversion Culvert (temp access available per CLP 27 Apr 18) | 02/07/2020 | 02/07/2020 | 15/04/2019 | 15/04/2019 | 0 | TK_Complete
KD_F7 | TT_FinMile | F5-Install North Section of UGP Large Dia. Intake&amp;Discharge CWP &amp; Finish Grid. for Machinery | 02/07/2020 | 02/07/2020 | 07/06/2019 | 07/06/2019 | 0 | TK_Complete
KD_G01 | TT_FinMile | G1 - Complete Existing Supplementary Cooling Water (SCW) Intake Culvert Modification | 02/07/2020 | 02/07/2020 | 26/12/2019 | 26/12/2019 | 0 | TK_Complete
KD_H01 | TT_FinMile | Completion of West of HRSG Foundations (incl. Condenstae Recirc Pumps) | 31/12/2018 | 31/12/2018 | 31/12/2018 | 31/12/2018 | 0 | TK_Complete
KD_H02 | TT_FinMile | Complete GT Diffuser Area Foundations | 02/07/2020 | 02/07/2020 | 28/02/2019 | 28/02/2019 | 0 | TK_Complete
KD_H03 | TT_FinMile | Completion of Neutralization Tank | 02/07/2020 | 02/07/2020 | 31/12/2018 | 31/12/2018 | 0 | TK_Complete
TPAD0010 | TT_FinMile | Temp Pad Foundation - Construct pad foundation for HRSG Heavy lift crane | 01/03/2018 | 01/03/2018 | 16/03/2018 | 16/03/2018 | 0 | TK_Complete
10MAA-1000 | TT_Task | HP/IP - Clean HP Turbine and Prepare for Assembly | 04/10/2018 | 09/10/2018 | 12/09/2018 | 18/09/2018 | 0 | TK_Complete
10MAA-1010 | TT_Task | HP/IP - Set Down Turbine on Bearing Pedestals &amp; Provisionaly Align | 10/10/2018 | 18/10/2018 | 18/09/2018 | 12/10/2018 | 0 | TK_Complete
10MAA-1020 | TT_Task | HP/IP - Establish the Radial &amp; Axial Check Dimensions for the Shaft in Bearing Pedestals | 09/10/2018 | 09/10/2018 | 29/09/2018 | 12/10/2018 | 0 | TK_Complete
10MAA-1040 | TT_Task | HP/IP - Clean Main &amp; Auxiliary Bearings, Prepare for Assembly &amp; Install | 11/12/2018 | 13/12/2018 | 26/11/2018 | 07/12/2018 | 0 | TK_Complete
10MAA-1050 | TT_Task | HP/IP - Set Down Shaft in Bearings &amp; Align Shaft | 03/12/2018 | 11/12/2018 | 08/12/2018 | 17/12/2018 | 0 | TK_Complete
10MAA-1060 | TT_Task | HP/IP Perform Radial &amp; Axial Clearance Checks on Turbine | 12/12/2018 | 13/12/2018 | 22/12/2018 | 15/01/2019 | 0 | TK_Complete
10MA-1110 | TT_Task | Clean Turbine &amp; Generator Foundations &amp; Confirm Survey Acceptance | 08/08/2018 | 10/08/2018 | 23/07/2018 | 26/07/2018 | 0 | TK_Complete
10MA-1130 | TT_Task | Markout Reference Points for Turbine Floor Elev., Longitudinal &amp; Transverse Axis | 14/08/2018 | 16/08/2018 | 16/07/2018 | 26/07/2018 | 0 | TK_Complete
10MA-1140 | TT_Task | Install Anchor Bolts - Front HP Bearing Pedestal | 17/08/2018 | 17/08/2018 | 23/07/2018 | 25/07/2018 | 0 | TK_Complete
10MA-1150 | TT_Task | Clean Front HP Bearing Pedestal, Prepare for Assembly and Set Down on Adjusting Screws | 17/08/2018 | 20/08/2018 | 23/07/2018 | 26/07/2018 | 0 | TK_Complete
10MA-1170 | TT_Task | Install Anchor Bolts - Rear HP Bearing Pedestal | 17/08/2018 | 17/08/2018 | 23/07/2018 | 25/07/2018 | 0 | TK_Complete
10MA-1180 | TT_Task | Clean Rear HP Bearing Pedestal, Prepare for Assembly and Set Down on Adjusting Screws | 17/08/2018 | 24/08/2018 | 23/07/2018 | 26/07/2018 | 0 | TK_Complete
10MA-1200 | TT_Task | Install Anchor Bolts - Rear LP-1 Bearing Pedestal | 17/08/2018 | 17/08/2018 | 23/07/2018 | 26/07/2018 | 0 | TK_Complete
10MA-1210 | TT_Task | Clean Rear LP-1 Bearing Pedestal, Prepare for Assembly and Set Down on Adjusting Screws | 26/07/2018 | 01/08/2018 | 23/07/2018 | 24/08/2018 | 0 | TK_Complete
10MA-1220 | TT_Task | Align Front &amp; Rear HP Bearing Pedestals | 01/08/2018 | 06/08/2018 | 01/08/2018 | 06/08/2018 | 0 | TK_Complete
10MA-1230 | TT_Task | Align Rear LP-1 Bearing Pedestals | 30/08/2018 | 04/09/2018 | 10/08/2018 | 24/08/2018 | 0 | TK_Complete
10MA-1240 | TT_Task | Set-up Formwork for Grouting Front &amp; Rear HP Bearing Pedestals | 06/08/2018 | 08/08/2018 | 06/08/2018 | 08/08/2018 | 0 | TK_Complete
10MA-1250 | TT_Task | Set-up Formwork for Grouting Rear LP-1 Bearing Pedestal | 04/09/2018 | 07/09/2018 | 17/08/2018 | 24/08/2018 | 0 | TK_Complete
10MA-1260 | TT_Task | Align Check of Pedestals before Grouting | 25/08/2018 | 28/08/2018 | 25/08/2018 | 27/08/2018 | 0 | TK_Complete
10MA-1270 | TT_Task | Grout Pedestals | 12/09/2018 | 14/09/2018 | 25/08/2018 | 30/08/2018 | 0 | TK_Complete
10MA-1280 | TT_Task | Align Check of Bearing Casings &amp; Baseplates After Grouting | 23/08/2018 | 25/08/2018 | 23/08/2018 | 24/08/2018 | 0 | TK_Complete
10MA-1290 | TT_Task | Install &amp; Prealign Steel Bars for LP-1 Casing Centering Guiders in Foundation | 29/09/2018 | 08/10/2018 | 08/09/2018 | 19/10/2018 | 0 | TK_Complete
10MA-1300 | TT_Task | Fill in Voids in Casing Centering Guides with Grout | 08/10/2018 | 10/10/2018 | 08/10/2018 | 19/10/2018 | 0 | TK_Complete
10MAC-1000 | TT_Task | Install &amp; Prealign Steel Bar for LP-1 Casing Guider in Foundation | 10/10/2018 | 11/10/2018 | 08/09/2018 | 19/10/2018 | 0 | TK_Complete
10MAC-1010 | TT_Task | LP-1 - Clean LP1 Side Casing &amp; End Walls, Prepare for Assembly | 12/10/2018 | 15/10/2018 | 06/10/2018 | 19/10/2018 | 0 | TK_Complete
10MAC-1020 | TT_Task | LP-1 - LP1 Side End Walls on Supporting Arms, Align &amp; Secure, Prepare for Assembly | 15/10/2018 | 17/10/2018 | 22/10/2018 | 23/10/2018 | 0 | TK_Complete
10MAC-1030 | TT_Task | LP-1 - Fit Bottom Plate, Align &amp; Tack Weld | 17/10/2018 | 22/10/2018 | 26/10/2018 | 30/10/2018 | 0 | TK_Complete
10MAC-1040 | TT_Task | LP-1 - Prepare &amp; Install Side Wall | 31/10/2018 | 03/11/2018 | 22/10/2018 | 27/10/2018 | 0 | TK_Complete
10MAC-1050 | TT_Task | LP-1 - Fit &amp; Weld Bracing Pipes for LP-1 Casing | 06/11/2018 | 13/11/2018 | 13/11/2018 | 26/11/2018 | 0 | TK_Complete
10MAC-1070 | TT_Task | LP-1 - Align, Mount &amp; Bolt Down the LP-1 Casing | 10/11/2018 | 15/11/2018 | 24/11/2018 | 21/12/2018 | 0 | TK_Complete
10MAC-1080 | TT_Task | LP-1 - Weld Entire LP-1 Outer Casing | 03/12/2018 | 12/12/2018 | 30/11/2018 | 12/12/2018 | 0 | TK_Complete
10MAC-1090 | TT_Task | LP-1 - Remove Top Half Outer Casing, Clean, Weld &amp; Finish Joints on Joint Plane | 13/12/2018 | 31/12/2018 | 14/12/2018 | 14/12/2018 | 0 | TK_Complete
10MAC-1100 | TT_Task | LP-1 - Align Bottom Half Outer Casing to Longitunal &amp; Transverse Axes &amp; Vertically | 14/12/2018 | 03/01/2019 | 05/11/2018 | 21/11/2018 | 0 | TK_Complete
10MAC-1110 | TT_Task | LP-1 - Align Steel Bar for Outer Casing Guider &amp; Fill Voids w/ Grout | 03/01/2019 | 07/01/2019 | 24/11/2018 | 21/12/2018 | 0 | TK_Complete
10MAC-1120 | TT_Task | LP-1 - Provisionally Mount Exp. Joints for Supporting Arm &amp; Centering Guide | 03/01/2019 | 09/01/2019 | 15/12/2018 | 29/12/2018 | 0 | TK_Complete
10MAC-1130 | TT_Task | LP-1 - Set Down Bottom Half Inner Casing in Bottom Outer Casing | 09/01/2019 | 14/01/2019 | 21/12/2018 | 21/12/2018 | 0 | TK_Complete
10MAC-1140 | TT_Task | LP-1 - Align Elevation &amp; Centerline of Bottom Half of Inner Casing | 14/01/2019 | 18/01/2019 | 22/12/2018 | 28/12/2018 | 0 | TK_Complete
10MAC-1150 | TT_Task | LP-1 - Fix the Inner Casing Radially &amp; Axially, Check Guide Rods | 02/01/2019 | 08/01/2019 | 26/12/2018 | 02/01/2019 | 0 | TK_Complete
10MAC-1160 | TT_Task | LP-1 - Clean Botton Half Shaft Seal Casing &amp; Attach to Bearing Pedestal | 22/01/2019 | 23/01/2019 | 31/12/2018 | 31/12/2018 | 0 | TK_Complete
10MAC-1170 | TT_Task | LP-1 - Clean LP-1 Shaft &amp; Prepare for Assembly | 18/01/2019 | 21/01/2019 | 29/12/2018 | 15/01/2019 | 0 | TK_Complete
10MAC-1180 | TT_Task | LP-1 - Clean Main &amp; Auxiliary Bearing, Prepare for Assembly &amp; Install | 24/01/2019 | 25/01/2019 | 31/12/2018 | 31/12/2018 | 0 | TK_Complete
10MAC-1190 | TT_Task | LP-1 - Slide Bellow Type Expansion Joints onto LP-1 Shaft | 02/01/2019 | 05/01/2019 | 29/12/2018 | 29/12/2018 | 0 | TK_Complete
10MAC-1200 | TT_Task | LP-1 - Install Turbine Shaft in Main &amp; Auxiliary Bearings &amp; Align | 05/01/2019 | 08/01/2019 | 04/01/2019 | 05/01/2019 | 0 | TK_Complete
10MAC-1210 | TT_Task | LP-1 - Take Actual Radial &amp; Axial Shaft Dimensions in the Bearing Pedestals | 08/01/2019 | 10/01/2019 | 08/01/2019 | 14/01/2019 | 0 | TK_Complete
10MAC-1220 | TT_Task | LP-1 - Provisionally Align Lower Section of Shaft Seal Casing to Shaft | 10/01/2019 | 12/01/2019 | 14/01/2019 | 22/01/2019 | 0 | TK_Complete
10MAC-1230 | TT_Task | LP-1 - Radially &amp; Axially Align Bottom Half Inner Casing to Turbine Shaft | 12/01/2019 | 18/01/2019 | 14/01/2019 | 21/01/2019 | 0 | TK_Complete
10MAC-1240 | TT_Task | LP-1 - Perform Radially &amp; Axially Blading Clearance Checks | 19/01/2019 | 23/01/2019 | 14/01/2019 | 21/01/2019 | 0 | TK_Complete
10MAC-1250 | TT_Task | LP-1 - Install Guide Blade Carrier &amp; Stationary Blade Ring Upper Part | 24/01/2019 | 26/01/2019 | 20/01/2019 | 21/01/2019 | 0 | TK_Complete
10MAC-1260 | TT_Task | LP-1 - Mount Outer Shell of Inner Casing &amp; Tighten Casing Joint Bolts | 21/01/2019 | 24/01/2019 | 15/02/2019 | 17/03/2019 | 0 | TK_Complete
10MAC-1270 | TT_Task | LP-1 - Check Axial Displacement of Inner Casing | 01/04/2019 | 01/04/2019 | 01/04/2019 | 01/04/2019 | 0 | TK_Complete
10MAC-1290 | TT_Task | LP-1 - Drill &amp; Ream Holes for Fitting Bolts in Joint Plane of Outer Casing | 01/04/2019 | 03/04/2019 | 09/03/2019 | 17/03/2019 | 0 | TK_Complete
10MAC-1300 | TT_Task | LP-1 - Install Atmospheric Relief Diaphragm into Top Half Outer Casing | 18/02/2019 | 22/02/2019 | 13/12/2018 | 14/12/2018 | 0 | TK_Complete
10MAC-1320 | TT_Task | LP-1 - Mount Top Half Cover &amp; Tighten Casing Joint Bolts | 04/04/2019 | 09/04/2019 | 20/03/2019 | 12/09/2019 | 0 | TK_Complete
10MAC-1330 | TT_Task | LP-1 - Pre-assemble Cross Over Pipe | 01/04/2019 | 29/04/2019 | 01/04/2019 | 02/09/2019 | 0 | TK_Complete
10MAC-1340 | TT_Task | LP-1 - Assemble Cross Over Pipe | 20/06/2019 | 24/06/2019 | 20/06/2019 | 19/09/2019 | 0 | TK_Complete
10MAC-1350 | TT_Task | LP-1 - Insulate Cross Over Pipe &amp; Turbine | 31/08/2019 | 20/09/2019 | 17/08/2019 | 04/10/2019 | 0 | TK_Complete
10MA-1410 | TT_Task | Perform Preliminary Alignment of Shaft Assembly in Operating Position | 28/01/2019 | 31/01/2019 | 09/01/2019 | 12/01/2019 | 0 | TK_Complete
10MA-1420 | TT_Task | Alignment - Generator to Steam Turbine/Gas Turbine to Generator | 01/02/2019 | 08/02/2019 | 14/01/2019 | 12/04/2019 | 0 | TK_Complete
10MA-1430 | TT_Task | Assembly of Shifting Clutch | 26/01/2019 | 30/01/2019 | 30/01/2019 | 01/02/2019 | 0 | TK_Complete
10MA-1440 | TT_Task | Common Coupling Alignment at Steam Turbine/Generator/Gas Turbine | 30/01/2019 | 08/02/2019 | 11/02/2019 | 03/04/2019 | 0 | TK_Complete
10MA-1450 | TT_Task | Draw Together HP/LP Coupling, Ream &amp; Hone Coupling Holes, Finish Grind Coupling Holes | 08/02/2019 | 14/02/2019 | 18/02/2019 | 02/03/2019 | 0 | TK_Complete
10MA-1460 | TT_Task | Couple HP &amp; LP1 Shafts Checking Radial Run-Out of Coupling Flanges | 14/02/2019 | 16/02/2019 | 02/03/2019 | 07/03/2019 | 0 | TK_Complete
10MA-1470 | TT_Task | Check The Radial Clearance of the LP1 Inner Casing by Means of Adjusting Screws | 30/01/2019 | 01/02/2019 | 30/01/2019 | 04/04/2019 | 0 | TK_Complete
10MA-1480 | TT_Task | Check Radial Run-Out of FInal Stage of Outer Shell of LP Casing | 01/02/2019 | 02/02/2019 | 09/03/2019 | 11/03/2019 | 0 | TK_Complete
10MA-1490 | TT_Task | Correct the Alignment of LP Inner Casing if Necessary &amp; Mount Fitted Keys for Casing Support | 01/02/2019 | 09/02/2019 | 01/02/2019 | 09/04/2019 | 0 | TK_Complete
10MA-1500 | TT_Task | Align LP1 Bottom Half Shaft Seal Casing to Coupled Shaft Assembly | 09/02/2019 | 12/02/2019 | 20/03/2019 | 11/04/2019 | 0 | TK_Complete
10MA-1510 | TT_Task | Check Radial Clearance of LP1 Shaft Seal | 30/04/2019 | 30/04/2019 | 10/04/2019 | 24/04/2019 | 0 | TK_Complete
10MA-1520 | TT_Task | Place Cover on LP Shaft Seal Casing Ready for Operations - Fabricate to Size &amp; Insert Fitted Keys | 02/05/2019 | 06/05/2019 | 20/05/2019 | 21/08/2019 | 0 | TK_Complete
10MA-1530 | TT_Task | If Necessary - Realign HP Casing to Coupled Shaft Assembly, Level off Brack Supports | 17/04/2019 | 20/04/2019 | 17/04/2019 | 24/04/2019 | 0 | TK_Complete
10MA-1540 | TT_Task | Install &amp; Align Shaft Turning Gear (Electric Motor) | 07/05/2019 | 08/05/2019 | 29/04/2019 | 30/04/2019 | 0 | TK_Complete
10MA-1550 | TT_Task | Machine to Size &amp; Install Fitted Keys for HP Casing Guide | 07/05/2019 | 09/05/2019 | 20/05/2019 | 28/06/2019 | 0 | TK_Complete
10MA-1560 | TT_Task | Machine to Size &amp; Install Shim Plates for HP Turbine Bracket &amp; Support | 10/05/2019 | 11/05/2019 | 10/05/2019 | 31/08/2019 | 0 | TK_Complete
10MA-1570 | TT_Task | Establish Clearance @ Front HP Bearing Pedestal | 13/05/2019 | 14/05/2019 | 13/05/2019 | 14/05/2019 | 0 | TK_Complete
10MA-1580 | TT_Task | Install Vibration Sensors in Bearing Pedestals | 01/08/2019 | 16/08/2019 | 19/07/2019 | 27/08/2019 | 0 | TK_Complete
10MA-1590 | TT_Task | Install Sealing Rings in Front/Rear HP &amp; Rear LP1 Bearing Pedestals | 20/05/2019 | 23/05/2019 | 30/04/2019 | 02/05/2019 | 0 | TK_Complete
10MA-1600 | TT_Task | Prepare Front/Rear HP &amp; Rear LP1 Bearing Pedestals for Flushing | 25/04/2019 | 03/05/2019 | 25/04/2019 | 07/05/2019 | 0 | TK_Complete
10MA-1605 | TT_FinMile | Power Available for Oil Flushing | 30/04/2019 | 30/04/2019 | 30/04/2019 | 30/04/2019 | 0 | TK_Complete
10MA-1610 | TT_Task | Steam Turbine Ready for Oil FLushing | 07/06/2019 | 07/06/2019 | 20/05/2019 | 20/05/2019 | 0 | TK_Complete
10MA-1620 | TT_Task | Steam Turbine Lube Oil Flushing | 08/06/2019 | 02/07/2019 | 29/05/2019 | 21/06/2019 | 0 | TK_Complete
10MA-1630 | TT_Task | Re-assembly after Lube Oil Flush | 17/06/2019 | 26/06/2019 | 22/06/2019 | 06/07/2019 | 0 | TK_Complete
10MA-1650 | TT_Task | Closing of Bearing Pedestals | 09/07/2019 | 19/07/2019 | 13/07/2019 | 27/08/2019 | 0 | TK_Complete
10MA-1660 | TT_Task | E &amp; IC Installation | 03/06/2019 | 13/07/2019 | 13/05/2019 | 07/09/2019 | 0 | TK_Complete
10MA-1670 | TT_Task | Pre-Commissioning - (10MA-01) HP/IP/LP Turbine | 09/09/2019 | 17/09/2019 | 06/09/2019 | 16/11/2019 | 0 | TK_Complete
10MAV10 | TT_Task | Install Equipment/Skids/Pumps | 29/09/2018 | 11/10/2018 | 14/09/2018 | 30/09/2018 | 0 | TK_Complete
10MAV1001 | TT_Task | Set Lube Oil Module into Position - Skid | 29/09/2018 | 05/10/2018 | 14/09/2018 | 30/09/2018 | 0 | TK_Complete
10MAV20 | TT_Task | Install Large Bore Pipe/Valves/Supports | 12/01/2019 | 08/03/2019 | 07/01/2019 | 30/04/2019 | 0 | TK_Complete
10MAV30 | TT_Task | Install Small Bore Pipe/Valves/Supports | 08/02/2019 | 01/04/2019 | 08/02/2019 | 23/05/2019 | 0 | TK_Complete
10MAV40 | TT_Task | NDE | 01/03/2019 | 10/04/2019 | 01/03/2019 | 28/05/2019 | 0 | TK_Complete
10MAV50 | TT_Task | EC+I | 05/06/2019 | 02/07/2019 | 21/05/2019 | 06/09/2019 | 0 | TK_Complete
10MAV60 | TT_Task | Line Inspection | 31/05/2019 | 04/06/2019 | 12/06/2019 | 15/06/2019 | 0 | TK_Complete
10MAV70 | TT_Task | Hydro Test | 29/06/2019 | 02/07/2019 | 20/07/2019 | 19/08/2019 | 0 | TK_Complete
10MAV75 | TT_FinMile | Lube Oil System Ready for Flushing | 06/06/2019 | 06/06/2019 | 27/05/2019 | 27/05/2019 | 0 | TK_Complete
10MAV80 | TT_Task | Painting/Insulation | 08/06/2019 | 18/06/2019 | 08/05/2019 | 28/08/2019 | 0 | TK_Complete
10MAV90 | TT_Task | Pre-Commissioning | 31/08/2019 | 12/09/2019 | 20/08/2019 | 28/08/2019 | 0 | TK_Complete
10MAX10 | TT_Task | Install Equipment/Skids/Pumps | 31/10/2018 | 05/11/2018 | 03/10/2018 | 05/10/2018 | 0 | TK_Complete
10MAX100 | TT_Task | Flush ST Hydraulic Piping | 09/09/2019 | 16/09/2019 | 09/09/2019 | 14/09/2019 | 0 | TK_Complete
10MAX110 | TT_Task | Reconfigure ST Hydraulic Piping after Flushing] | 30/09/2019 | 08/10/2019 | 05/10/2019 | 12/10/2019 | 0 | TK_Complete
10MAX20 | TT_Task | Install Large Bore Pipe/Valves/Supports | 08/02/2019 | 15/03/2019 | 15/12/2018 | 25/04/2019 | 0 | TK_Complete
10MAX30 | TT_Task | Install Small Bore Pipe/Valves/Supports | 08/04/2019 | 17/05/2019 | 08/04/2019 | 04/09/2019 | 0 | TK_Complete
10MAX40 | TT_Task | NDE | 08/04/2019 | 17/05/2019 | 17/04/2019 | 16/09/2019 | 0 | TK_Complete
10MAX50 | TT_Task | EC+I | 30/04/2019 | 08/06/2019 | 07/05/2019 | 21/09/2019 | 0 | TK_Complete
10MAX60 | TT_Task | Line Inspection | 31/07/2019 | 05/08/2019 | 26/08/2019 | 29/08/2019 | 0 | TK_Complete
10MAX70 | TT_Task | Hydro Test | 04/09/2019 | 07/09/2019 | 04/09/2019 | 07/09/2019 | 0 | TK_Complete
10MAX80 | TT_Task | Painting/Insulation | 11/06/2019 | 29/06/2019 | 07/05/2019 | 09/11/2019 | 0 | TK_Complete
10MAX90 | TT_Task | Pre-Commissioning/Flushing/Cleaning | 24/09/2019 | 28/09/2019 | 24/09/2019 | 09/11/2019 | 0 | TK_Complete
10MA1400 | TT_Task | Install &amp; Align Main Stop &amp; Control Valves | 04/04/2019 | 24/04/2019 | 09/04/2019 | 17/06/2019 | 0 | TK_Complete
10MA1410 | TT_Task | Install &amp; Align RH Stop &amp; Control Valves | 13/04/2019 | 04/05/2019 | 13/04/2019 | 21/06/2019 | 0 | TK_Complete
10MA1420 | TT_Task | Install &amp; Align Steam Supply Valves &amp; Bolt | 10/06/2019 | 28/06/2019 | 15/06/2019 | 22/06/2019 | 0 | TK_Complete
10MA1430 | TT_Task | Installation of all Actuators for MS, RH, LP | 18/06/2019 | 15/07/2019 | 11/06/2019 | 22/06/2019 | 0 | TK_Complete
10MA1450 | TT_Task | E&amp;IC Installation ST Stop and Control Valves | 26/06/2019 | 05/08/2019 | 21/06/2019 | 31/08/2019 | 0 | TK_Complete
10MA1460 | TT_Task | Pre-Commissioning | 31/08/2019 | 11/09/2019 | 02/09/2019 | 11/09/2019 | 0 | TK_Complete
10MAN1000 | TT_Task | Attach Spring Supports for By Pass Valve | 31/05/2019 | 05/06/2019 | 10/06/2019 | 21/06/2019 | 0 | TK_Complete
10MAN1010 | TT_Task | Install By Pass Valves | 06/06/2019 | 14/06/2019 | 21/06/2019 | 31/08/2019 | 0 | TK_Complete
10MAN1020 | TT_Task | Install Large Bore Pipe/Valves/Supports | 25/04/2019 | 24/05/2019 | 25/04/2019 | 31/08/2019 | 0 | TK_Complete
10MAN1050 | TT_Task | NDE | 30/04/2019 | 29/05/2019 | 15/05/2019 | 28/09/2019 | 0 | TK_Complete
10MAN1060 | TT_Task | EC+I | 07/06/2019 | 06/07/2019 | 24/05/2019 | 25/09/2019 | 0 | TK_Complete
10MAN1070 | TT_Task | Line Inspection &amp; Preparation for Neutral Float Welds | 02/08/2019 | 09/08/2019 | 10/08/2019 | 24/08/2019 | 0 | TK_Complete
10MAN1075 | TT_Task | Neutral Float &amp; Final Weld Connections to Bypass Control Valves | 11/07/2019 | 24/07/2019 | 22/07/2019 | 31/08/2019 | 0 | TK_Complete
10MAN1080 | TT_Task | Hydro Test | 21/08/2019 | 02/09/2019 | 31/08/2019 | 07/09/2019 | 0 | TK_Complete
10MAN1085 | TT_Task | Close-out Insulation after Neutral Float Welds | 07/09/2019 | 18/09/2019 | 07/09/2019 | 07/11/2019 | 0 | TK_Complete
10MAN1090 | TT_Task | Painting/Insulation | 29/06/2019 | 20/07/2019 | 25/06/2019 | 26/10/2019 | 0 | TK_Complete
10MAN110 | TT_Task | Pre-Commissioning/Flushing/Cleaning | 18/09/2019 | 30/09/2019 | 07/09/2019 | 26/10/2019 | 0 | TK_Complete
10MAW10 | TT_Task | Install Gland Steam Condenser (MAW) | 01/04/2019 | 04/04/2019 | 12/04/2019 | 15/05/2019 | 0 | TK_Complete
10MAW100 | TT_Task | Pre-Commissioning/Flushing/Cleaning | 11/09/2019 | 19/09/2019 | 11/09/2019 | 12/11/2019 | 0 | TK_Complete
10MAW30 | TT_Task | Install Large Bore Pipe/Valves/Supports | 30/04/2019 | 11/05/2019 | 10/05/2019 | 17/08/2019 | 0 | TK_Complete
10MAW40 | TT_Task | Install Small Bore Pipe/Valves/Supports | 18/04/2019 | 23/05/2019 | 18/04/2019 | 17/08/2019 | 0 | TK_Complete
10MAW50 | TT_Task | NDE | 25/05/2019 | 18/06/2019 | 14/05/2019 | 24/09/2019 | 0 | TK_Complete
10MAW60 | TT_Task | EC+I | 05/06/2019 | 11/07/2019 | 27/06/2019 | 24/09/2019 | 0 | TK_Complete
10MAW70 | TT_Task | Line Inpsection | 14/08/2019 | 21/08/2019 | 23/08/2019 | 30/08/2019 | 0 | TK_Complete
10MAW80 | TT_Task | Hydro Test | 22/08/2019 | 29/08/2019 | 24/08/2019 | 31/08/2019 | 0 | TK_Complete
10MAW90 | TT_Task | Painting/Insulation | 05/06/2019 | 22/06/2019 | 18/06/2019 | 12/11/2019 | 0 | TK_Complete
10MAL10 | TT_Task | Install Steam Turbine Drain Module (MAL00Y) | 24/10/2018 | 29/10/2018 | 01/08/2018 | 22/09/2018 | 0 | TK_Complete
10MAL10a | TT_Task | Resolution of Foundation Embedment problem (Civil Issue) | 29/09/2018 | 23/10/2018 | 29/09/2018 | 20/10/2018 | 0 | TK_Complete
10MAL20 | TT_Task | Install Large Bore Pipe/Valves/Supports | 06/04/2019 | 11/05/2019 | 09/04/2019 | 28/08/2019 | 0 | TK_Complete
10MAL30 | TT_Task | Install Small Bore Pipe/Valves/Supports | 27/04/2019 | 01/06/2019 | 27/04/2019 | 28/08/2019 | 0 | TK_Complete
10MAL40 | TT_Task | NDE | 28/05/2019 | 26/06/2019 | 21/05/2019 | 25/09/2019 | 0 | TK_Complete
10MAL50 | TT_Task | EC+I | 12/06/2019 | 03/07/2019 | 12/06/2019 | 27/09/2019 | 0 | TK_Complete
10MAL60 | TT_Task | Line Inspection | 31/08/2019 | 04/09/2019 | 10/09/2019 | 14/09/2019 | 0 | TK_Complete
10MAL70 | TT_Task | Hydro Test | 30/09/2019 | 04/10/2019 | 05/10/2019 | 12/10/2019 | 0 | TK_Complete
10MAL80 | TT_Task | Painting/Insulation | 05/06/2019 | 19/07/2019 | 23/05/2019 | 12/11/2019 | 0 | TK_Complete
10MAL90 | TT_Task | Pre-Commissioning/Flushing/Cleaning | 10/09/2019 | 19/09/2019 | 10/09/2019 | 12/11/2019 | 0 | TK_Complete
10MAJ10 | TT_Task | Install Equipment/Skids/Pumps | 06/04/2019 | 13/04/2019 | 08/04/2019 | 07/06/2019 | 0 | TK_Complete
10MAJ20 | TT_Task | Install Large Bore Pipe/Valves/Supports | 13/04/2019 | 08/05/2019 | 15/04/2019 | 17/08/2019 | 0 | TK_Complete
10MAJ30 | TT_Task | Install Small Bore Pipe/Valves/Supports | 23/04/2019 | 17/05/2019 | 23/04/2019 | 17/08/2019 | 0 | TK_Complete
10MAJ40 | TT_Task | NDE | 11/05/2019 | 07/06/2019 | 11/05/2019 | 25/09/2019 | 0 | TK_Complete
10MAJ50 | TT_Task | EC+I | 28/05/2019 | 19/06/2019 | 15/05/2019 | 28/09/2019 | 0 | TK_Complete
10MAJ60 | TT_Task | Line Inspection | 14/08/2019 | 20/08/2019 | 21/08/2019 | 31/08/2019 | 0 | TK_Complete
10MAJ70 | TT_Task | Hydro Test | 30/09/2019 | 08/10/2019 | 05/10/2019 | 12/10/2019 | 0 | TK_Complete
10MAJ80 | TT_Task | Painting/Insulation | 14/06/2019 | 28/06/2019 | 17/06/2019 | 07/11/2019 | 0 | TK_Complete
10MAJ90 | TT_Task | Pre-Commissioning/Flushing/Cleaning | 11/09/2019 | 19/09/2019 | 11/09/2019 | 07/11/2019 | 0 | TK_Complete
A1620 | TT_Task | Set up and Check Condenser Foundations | 18/04/2018 | 21/04/2018 | 16/04/2018 | 18/04/2018 | 0 | TK_Complete
A1630 | TT_Task | Placing and Alignment of Support Plates | 02/04/2019 | 04/04/2019 | 02/04/2019 | 04/04/2019 | 0 | TK_Complete
A1640 | TT_Task | Fitting and Welding of Fixing and Guide Points | 07/05/2018 | 09/05/2018 | 28/04/2018 | 04/05/2018 | 0 | TK_Complete
A1650 | TT_Task | Placing Hotwell | 07/05/2018 | 07/05/2018 | 05/05/2018 | 19/05/2018 | 0 | TK_Complete
A1660 | TT_Task | Assembly and Welding of Condensate Drain Tank | 04/06/2018 | 08/06/2018 | 02/06/2018 | 05/06/2018 | 0 | TK_Complete
A1670 | TT_Task | Placing Steam Shell (lower part) and Connection Weld | 23/05/2018 | 02/06/2018 | 22/05/2018 | 23/05/2018 | 0 | TK_Complete
A1680 | TT_Task | Placing, Aligning and Grouting of Vacuum Pumps | 01/04/2019 | 12/04/2019 | 04/04/2019 | 07/06/2019 | 0 | TK_Complete
A1690 | TT_Task | Installing Protective Covers for Cooling Tubes | 26/07/2018 | 28/07/2018 | 11/06/2018 | 13/06/2018 | 0 | TK_Complete
A1700 | TT_Task | Alignment of Condenser Steam Shell | 16/08/2018 | 17/08/2018 | 22/05/2018 | 25/05/2018 | 0 | TK_Complete
A1710 | TT_Mile | Condenser Ready for Preassembling Piping | 29/09/2018 | 29/09/2018 | 31/08/2018 | 31/08/2018 | 0 | TK_Complete
A1720 | TT_Task | Assembly and Welding of Condenser Neck | 17/08/2018 | 13/09/2018 | 15/06/2018 | 31/08/2018 | 0 | TK_Complete
A1730 | TT_Task | Fitting and Welding of Guide Bolts and Stiffening Plates | 13/09/2018 | 26/09/2018 | 17/06/2018 | 21/01/2019 | 0 | TK_Complete
A1740 | TT_Task | Installing and Wedling of Seismic Tie Down | 04/04/2019 | 09/04/2019 | 04/04/2019 | 10/04/2019 | 0 | TK_Complete
A1750 | TT_Task | Assemble and Weld Nozzles into Steam Dome | 29/09/2018 | 13/10/2018 | 03/09/2018 | 15/10/2018 | 0 | TK_Complete
A1760 | TT_Task | Vacuum Test Water Side | 31/12/2018 | 02/01/2019 | 11/12/2018 | 09/01/2019 | 0 | TK_Complete
A1770 | TT_Task | Check Corrosion Protection on CW Side | 02/01/2019 | 19/01/2019 | 14/01/2019 | 21/01/2019 | 0 | TK_Complete
A1780 | TT_Task | Fitting and Bolting of Front and Rear Coverwith Seal | 12/10/2018 | 20/10/2018 | 03/06/2018 | 13/06/2018 | 0 | TK_Complete
A1790 | TT_Task | Connection and Welding of Rear Cover | 01/04/2019 | 09/04/2019 | 03/04/2019 | 11/04/2019 | 0 | TK_Complete
A1800 | TT_Mile | Condenser Ready for PAB Piping | 04/05/2019 | 04/05/2019 | 04/05/2019 | 04/05/2019 | 0 | TK_Complete
A1810 | TT_Task | Fitting of Condenser to LP Turbine | 30/01/2019 | 18/02/2019 | 30/01/2019 | 04/05/2019 | 0 | TK_Complete
A1820 | TT_Task | Welding of Condenser to LP Turbine | 19/02/2019 | 22/02/2019 | 19/02/2019 | 22/02/2019 | 0 | TK_Complete
A1830 | TT_Task | Floating of Bypass Station | 31/05/2019 | 11/06/2019 | 22/06/2019 | 07/09/2019 | 0 | TK_Complete
A1840 | TT_Task | Assembly and Welding of Condenser Neck Structure | 03/09/2018 | 13/09/2018 | 15/06/2018 | 30/07/2018 | 0 | TK_Complete
A1850 | TT_Task | Grouting of Condenser Shell Support Structure Seismic Tie | 02/02/2019 | 12/02/2019 | 26/03/2019 | 11/04/2019 | 0 | TK_Complete
A1860 | TT_Task | Final Works and Cleaning | 11/04/2019 | 16/04/2019 | 11/04/2019 | 29/06/2019 | 0 | TK_Complete
A1870 | TT_Task | Final Inspection | 12/07/2019 | 15/07/2019 | 20/07/2019 | 05/10/2019 | 0 | TK_Complete
A1880 | TT_Task | Insulation Condenser | 15/07/2019 | 24/08/2019 | 13/07/2019 | 14/11/2019 | 0 | TK_Complete
A1890 | TT_Task | Placing and Alignment of Sliding Supports | 26/01/2019 | 29/01/2019 | 15/03/2019 | 03/05/2019 | 0 | TK_Complete
A2590 | TT_Task | Piping Installation MAG | 04/05/2019 | 08/06/2019 | 04/05/2019 | 14/09/2019 | 0 | TK_Complete
A3350 | TT_Task | Prepare ground to South of Condenser for 750T crane | 25/04/2018 | 03/05/2018 | 26/04/2018 | 03/05/2018 | 0 | TK_Complete
A3360 | TT_Mile | Hand back area South of Condenser to Civil Contractor | 15/06/2018 | 15/06/2018 | 25/06/2018 | 25/06/2018 | 0 | TK_Complete
A3370 | TT_FinMile | Turbine Hall Grid Line 8-10 made available by Civil Contractor | 30/04/2019 | 30/04/2019 | 03/05/2019 | 03/05/2019 | 0 | TK_Complete
A3380 | TT_Task | Pressure Test Condenser | 18/10/2019 | 29/10/2019 | 18/10/2019 | 29/10/2019 | 0 | TK_Complete
10LCA10 | TT_Task | Installation of Condensate Extraction Pump - Skid | 02/01/2019 | 12/01/2019 | 10/01/2019 | 06/05/2019 | 0 | TK_Complete
10LCA100 | TT_Task | Pre-Commissioning/Flushing/Cleaning | 31/08/2019 | 11/09/2019 | 07/09/2019 | 05/12/2019 | 0 | TK_Complete
10LCA20 | TT_Task | Install Condensate Recirculation Pump Skid (LCA50Y Module) | 28/02/2019 | 13/03/2019 | 27/02/2019 | 28/02/2019 | 0 | TK_Complete
10LCA30 | TT_Task | Install Large Bore Pipe/Valves/Supports | 12/01/2019 | 03/04/2019 | 12/01/2019 | 17/07/2019 | 0 | TK_Complete
10LCA40 | TT_Task | Install Small Bore Pipe/Valves/Supports | 30/04/2019 | 05/06/2019 | 06/05/2019 | 17/08/2019 | 0 | TK_Complete
10LCA50 | TT_Task | NDE | 30/04/2019 | 05/06/2019 | 08/04/2019 | 21/09/2019 | 0 | TK_Complete
10LCA60 | TT_Task | E &amp;IC Erection Cond Recirc Pump | 01/04/2019 | 17/05/2019 | 15/04/2019 | 07/09/2019 | 0 | TK_Complete
10LCA70 | TT_Task | Line Inspection | 03/08/2019 | 13/08/2019 | 05/08/2019 | 10/08/2019 | 0 | TK_Complete
10LCA80 | TT_Task | Hydro Test | 13/08/2019 | 23/08/2019 | 17/08/2019 | 17/08/2019 | 0 | TK_Complete
10LCA90 | TT_Task | Painting/Insulation | 19/06/2019 | 08/07/2019 | 07/06/2019 | 05/12/2019 | 0 | TK_Complete
10LCA-02-10 | TT_Task | Install Equipment/Skids/Pumps | 01/04/2019 | 08/05/2019 | 02/04/2019 | 10/06/2019 | 0 | TK_Complete
10LCA-02-20 | TT_Task | Install Large Bore Pipe/Valves/Supports | 22/03/2019 | 29/06/2019 | 07/01/2019 | 24/07/2019 | 0 | TK_Complete
10LCA-02-30 | TT_Task | Install Small Bore Pipe/Valves/Supports | 21/06/2019 | 16/07/2019 | 07/05/2019 | 25/07/2019 | 0 | TK_Complete
10LCA-02-40 | TT_Task | NDE | 08/07/2019 | 16/07/2019 | 13/05/2019 | 21/09/2019 | 0 | TK_Complete
10LCA-02-50 | TT_Task | EC+I | 27/05/2019 | 06/06/2019 | 26/04/2019 | 21/09/2019 | 0 | TK_Complete
10LCA-02-60 | TT_Task | Line Inspection | 31/07/2019 | 10/08/2019 | 05/07/2019 | 10/08/2019 | 0 | TK_Complete
10LCA-02-70 | TT_Task | Hydro Test | 12/08/2019 | 22/08/2019 | 15/08/2019 | 17/08/2019 | 0 | TK_Complete
10LCA-02-80 | TT_Task | Painting/Insulation | 31/05/2019 | 29/06/2019 | 18/06/2019 | 11/11/2019 | 0 | TK_Complete
10LCA-02-90 | TT_Task | Pre-Commissioning/Flushing/Cleaning | 07/09/2019 | 20/09/2019 | 07/09/2019 | 11/11/2019 | 0 | TK_Complete
10LD-10 | TT_Task | Install Equipment/Skids/Pumps | 16/02/2019 | 22/03/2019 | 25/03/2019 | 30/04/2019 | 0 | TK_Complete
10LD-20 | TT_Task | Install Large Bore Pipe/Valves/Supports | 16/04/2019 | 06/06/2019 | 16/04/2019 | 24/07/2019 | 0 | TK_Complete
10LD-30 | TT_Task | Install Small Bore Pipe/Valves/Supports | 15/05/2019 | 29/06/2019 | 26/04/2019 | 24/07/2019 | 0 | TK_Complete
10LD-40 | TT_Task | NDE | 10/05/2019 | 26/06/2019 | 10/05/2019 | 21/09/2019 | 0 | TK_Complete
10LD-50 | TT_Task | EC+I | 03/07/2019 | 25/07/2019 | 30/04/2019 | 21/09/2019 | 0 | TK_Complete
10LD-60 | TT_Task | Line Inspection | 14/08/2019 | 22/08/2019 | 24/08/2019 | 14/09/2019 | 0 | TK_Complete
10LD-70 | TT_Task | Hydro Test | 30/09/2019 | 04/10/2019 | 19/10/2019 | 19/10/2019 | 0 | TK_Complete
10LD-80 | TT_Task | Painting/Insulation | 10/07/2019 | 07/08/2019 | 20/07/2019 | 09/12/2019 | 0 | TK_Complete
10LD-90 | TT_Task | Pre-Commissioning/Flushing/Cleaning | 12/09/2019 | 21/09/2019 | 12/09/2019 | 09/12/2019 | 0 | TK_Complete
10LDK-10 | TT_Task | Install Equipment/Skids/Pumps | 16/02/2019 | 04/03/2019 | 25/03/2019 | 15/04/2019 | 0 | TK_Complete
10LDK-20 | TT_Task | Install Large Bore Pipe/Valves/Supports | 15/04/2019 | 31/05/2019 | 15/04/2019 | 22/07/2019 | 0 | TK_Complete
10LDK-30 | TT_Task | Install Small Bore Pipe/Valves/Supports | 29/05/2019 | 28/06/2019 | 14/05/2019 | 22/07/2019 | 0 | TK_Complete
10LDK-40 | TT_Task | NDE | 30/05/2019 | 06/07/2019 | 16/05/2019 | 21/09/2019 | 0 | TK_Complete
10LDK-50 | TT_Task | EC+I | 21/06/2019 | 02/08/2019 | 14/06/2019 | 21/09/2019 | 0 | TK_Complete
10LDK-60 | TT_Task | Line Inspection | 05/08/2019 | 13/08/2019 | 24/08/2019 | 12/09/2019 | 0 | TK_Complete
10LDK-70 | TT_Task | Hydro Test | 30/09/2019 | 04/10/2019 | 25/10/2019 | 04/11/2019 | 0 | TK_Complete
10LDK-80 | TT_Task | Painting/Insulation | 18/07/2019 | 05/08/2019 | 20/07/2019 | 26/11/2019 | 0 | TK_Complete
10LDK-90 | TT_Task | Pre-Commissioning/Flushing/Cleaning | 21/09/2019 | 30/09/2019 | 14/09/2019 | 26/11/2019 | 0 | TK_Complete
10MBL1000 | TT_Task | Pre-assemble of Air Intake System | 15/02/2019 | 04/03/2019 | 25/03/2019 | 26/04/2019 | 0 | TK_Complete
10MBL1010 | TT_Task | Installation of Air Inlet Duct (Inlet Plenum Damper and Transition piece) | 15/05/2019 | 06/06/2019 | 13/05/2019 | 22/06/2019 | 0 | TK_Complete
10MBL1020 | TT_Task | Set Air Inlet Duct Lower Plenum on Foundation MBL | 15/04/2019 | 27/04/2019 | 15/04/2019 | 03/05/2019 | 0 | TK_Complete
10MBL1030 | TT_Task | Installation of Air Inlet Duct (Remaining) | 06/06/2019 | 02/07/2019 | 15/05/2019 | 31/08/2019 | 0 | TK_Complete
10MBL1040 | TT_Task | Installation of Air Intake Cone and Filters | 01/06/2019 | 26/06/2019 | 20/04/2019 | 17/08/2019 | 0 | TK_Complete
10MBL1050 | TT_Task | Insulation Anti Icing MBL | 12/07/2019 | 06/08/2019 | 03/06/2019 | 24/07/2019 | 0 | TK_Complete
10MBL1060 | TT_Task | E&amp;IC MBL | 29/04/2019 | 14/06/2019 | 29/04/2019 | 14/09/2019 | 0 | TK_Complete
10MBL1070 | TT_Task | Pre-Commissioning/Flushing/Cleaning | 31/08/2019 | 19/09/2019 | 07/09/2019 | 10/10/2019 | 0 | TK_Complete
10MBL1080 | TT_Task | Install Filter House Support Steel | 01/04/2019 | 10/05/2019 | 23/01/2019 | 28/02/2019 | 0 | TK_Complete
10MBL1090 | TT_Task | Install Filter House | 01/04/2019 | 10/05/2019 | 01/04/2019 | 17/08/2019 | 0 | TK_Complete
10MBL1100 | TT_Task | Installation of Inlet Air Duct Support Platform | 01/04/2019 | 18/04/2019 | 01/04/2019 | 11/06/2019 | 0 | TK_Complete
10MBL1110 | TT_Task | Lower Half Secondary Air Piping | 27/04/2019 | 04/05/2019 | 27/04/2019 | 06/05/2019 | 0 | TK_Complete
10MBL1120 | TT_Task | Set Exhaust Manifold | 26/10/2018 | 31/10/2018 | 05/09/2018 | 27/09/2018 | 0 | TK_Complete
10MBL1130 | TT_Task | Complete Steel Work for Inlet Air System | 01/04/2019 | 27/04/2019 | 01/03/2019 | 06/05/2019 | 0 | TK_Complete
10MBA1000 | TT_Task | Check Foundation | 30/08/2018 | 03/09/2018 | 08/08/2018 | 08/09/2018 | 0 | TK_Complete
10MBA1020 | TT_Task | Lower Support Block Centering Guide to Foundation Pit | 11/10/2018 | 15/10/2018 | 15/09/2018 | 15/09/2018 | 0 | TK_Complete
10MBA1030 | TT_Task | Install &amp; Grout Compressor Supports | 16/10/2018 | 20/10/2018 | 13/09/2018 | 29/09/2018 | 0 | TK_Complete
10MBA1035 | TT_Task | Position Support Bridge | 17/10/2018 | 17/10/2018 | 17/09/2018 | 29/09/2018 | 0 | TK_Complete
10MBA1040 | TT_Task | Install &amp; Grout Turbine Supports Blocks | 22/10/2018 | 26/10/2018 | 17/09/2018 | 29/09/2018 | 0 | TK_Complete
10MBA1050 | TT_Task | Install Turbine Supports | 23/10/2018 | 24/10/2018 | 17/09/2018 | 29/09/2018 | 0 | TK_Complete
10MBA1060 | TT_Task | Set Combustion Turbine | 03/11/2018 | 07/11/2018 | 03/10/2018 | 06/10/2018 | 0 | TK_Complete
10MBA1067 | TT_Task | GT Enclosure Installation | 21/01/2019 | 16/04/2019 | 21/01/2019 | 21/11/2019 | 0 | TK_Complete
10MBA1070 | TT_Task | Align Support Block Centering Guide | 07/11/2018 | 09/11/2018 | 14/09/2018 | 15/09/2018 | 0 | TK_Complete
10MBA1080 | TT_Task | Grout Support Block Centering Guide | 09/11/2018 | 12/11/2018 | 09/10/2018 | 10/10/2018 | 0 | TK_Complete
10MBA1090 | TT_Task | Align Combustion Turbine to Foundation Axis | 12/11/2018 | 15/11/2018 | 06/10/2018 | 10/10/2018 | 0 | TK_Complete
10MBA1100 | TT_FinMile | Generator in Position - Interface Date | 08/10/2018 | 08/10/2018 | 04/10/2018 | 04/10/2018 | 0 | TK_Complete
10MBA1110 | TT_Task | Install Weld Support Bridge &amp; Clamps for Fuel Gas Manifolds | 27/04/2019 | 03/05/2019 | 20/04/2019 | 26/06/2019 | 0 | TK_Complete
10MBA1120 | TT_Task | Install Intermediate Shaft &amp; Center to Combustion Turbine | 28/12/2018 | 31/12/2018 | 16/11/2018 | 21/11/2018 | 0 | TK_Complete
10MBA1130 | TT_Task | Install Clamps for Fuel Gas Manifolds | 28/12/2018 | 04/01/2019 | 26/10/2018 | 15/11/2018 | 0 | TK_Complete
10MBA1140 | TT_Task | Install Secondary Air Piping System | 18/04/2019 | 27/04/2019 | 30/11/2018 | 12/01/2019 | 0 | TK_Complete
10MBA1150 | TT_Task | Install Fuel Gas Manifold Pilot Gas | 04/01/2019 | 09/01/2019 | 06/11/2018 | 16/11/2018 | 0 | TK_Complete
10MBA1160 | TT_Mile | Ready for Pre-assembling Pipework MBA/MBP/ MBX/ EKG Piping | 25/03/2019 | 25/03/2019 | 01/01/2019 | 01/01/2019 | 0 | TK_Complete
10MBA1170 | TT_Task | Install Fuel Gas Manifold Stages A/B/C/D | 09/01/2019 | 15/01/2019 | 06/11/2018 | 16/11/2018 | 0 | TK_Complete
10MBA1180 | TT_Task | E &amp; IC Erection of GT | 02/04/2019 | 06/06/2019 | 22/03/2019 | 11/09/2019 | 0 | TK_Complete
10MBA1190 | TT_Task | Common Coupling Alignment GT/GEN/ST | 27/04/2019 | 10/05/2019 | 05/03/2019 | 12/04/2019 | 0 | TK_Complete
10MBA1200 | TT_Task | Align &amp; Welding Spur of the Support Block of Centering Guide | 30/01/2019 | 01/02/2019 | 10/10/2018 | 11/10/2018 | 0 | TK_Complete
10MBA1210 | TT_Task | Insulate Compressor Vane Carrier | 31/07/2019 | 06/08/2019 | 24/08/2019 | 03/09/2019 | 0 | TK_Complete
10MBA1220 | TT_Task | Weld Lugs of Compressor Supports | 01/04/2019 | 08/04/2019 | 26/03/2019 | 08/04/2019 | 0 | TK_Complete
10MBA1230 | TT_Task | Weld &amp; Pretension Turbine Supports | 08/04/2019 | 11/04/2019 | 08/04/2019 | 11/04/2019 | 0 | TK_Complete
10MBA1260 | TT_Task | Connect Exhaust Gas Line to Exhaust Gas Diffuser | 11/04/2019 | 16/04/2019 | 15/03/2019 | 23/03/2019 | 0 | TK_Complete
10MBA1270 | TT_Task | Install Actuators for Vane Pitch Controllers (IGV/VGv1/2/3) | 07/06/2019 | 14/06/2019 | 12/06/2019 | 25/07/2019 | 0 | TK_Complete
10MBA1280 | TT_Task | Check Alignment of Shaft Assembly | 11/04/2019 | 15/04/2019 | 25/03/2019 | 11/04/2019 | 0 | TK_Complete
10MBA1290 | TT_Task | Complete Insulation Installation | 30/04/2019 | 23/07/2019 | 24/05/2019 | 12/09/2019 | 0 | TK_Complete
10MBA1300 | TT_Task | Position &amp; Align Coupling Flanges, Bore Out &amp; Hone Bolt Holes | 12/04/2019 | 23/04/2019 | 12/04/2019 | 26/04/2019 | 0 | TK_Complete
10MBA1310 | TT_Task | Install Compressor Bearing Cover &amp; Shaft Turning Gear Unit | 27/04/2019 | 30/04/2019 | 26/03/2019 | 31/08/2019 | 0 | TK_Complete
10MBA1320 | TT_Task | Install Shaft Position Sensors for HCO System | 31/07/2019 | 01/08/2019 | 24/08/2019 | 24/08/2019 | 0 | TK_Complete
10MBA1330 | TT_Task | Install Speed Measuring Facilities | 01/08/2019 | 02/08/2019 | 28/08/2019 | 31/08/2019 | 0 | TK_Complete
10MBA1340 | TT_Task | Install Vibration Sensors | 02/08/2019 | 05/08/2019 | 28/08/2019 | 28/08/2019 | 0 | TK_Complete
10MBA1350 | TT_Task | GT Encl E&amp;IC Installation Incl Lighting | 20/05/2019 | 06/06/2019 | 20/05/2019 | 12/09/2019 | 0 | TK_Complete
10MBA1360 | TT_Task | Gas Turbine FInal Check | 03/10/2019 | 12/10/2019 | 14/09/2019 | 30/11/2019 | 0 | TK_Complete
10MBA1370 | TT_Task | Completion of Gas Turbine | 26/10/2019 | 04/11/2019 | 28/09/2019 | 21/11/2019 | 0 | TK_Complete
10MBR1000 | TT_Task | Installation of Exhaust Gas Support /Steelwork | 01/03/2019 | 23/03/2019 | 01/03/2019 | 23/04/2019 | 0 | TK_Complete
10MBR1010 | TT_Task | Installation of Exhaust Gas System Diffuser Casing &amp; Transition Piece | 06/05/2019 | 30/05/2019 | 16/05/2019 | 23/07/2019 | 0 | TK_Complete
10MBR1020 | TT_Task | Final Installation of Exhaust Gas Diffuser Expansion Jt (After Final Train Alignment) | 18/04/2019 | 28/05/2019 | 18/03/2019 | 17/08/2019 | 0 | TK_Complete
10MBR1030 | TT_Task | Grout Exhaust Gas Diffuser Supports | 31/08/2019 | 04/09/2019 | 24/09/2019 | 05/10/2019 | 0 | TK_Complete
10MBH10 | TT_Task | Install Equipment/Skids/Pumps | 01/04/2019 | 09/04/2019 | 08/04/2019 | 10/06/2019 | 0 | TK_Complete
10MBH20 | TT_Task | Install Large Bore Pipe/Valves/Supports | 01/04/2019 | 06/05/2019 | 01/04/2019 | 06/09/2019 | 0 | TK_Complete
10MBH30 | TT_Task | Install Small Bore Pipe/Valves/Supports | 09/05/2019 | 01/06/2019 | 09/05/2019 | 06/09/2019 | 0 | TK_Complete
10MBH40 | TT_Task | NDE | 15/05/2019 | 13/06/2019 | 15/05/2019 | 12/09/2019 | 0 | TK_Complete
10MBH50 | TT_Task | EC+I | 24/06/2019 | 15/07/2019 | 01/06/2019 | 13/09/2019 | 0 | TK_Complete
10MBH60 | TT_Task | Line Inspection | 06/09/2019 | 11/09/2019 | 16/09/2019 | 21/09/2019 | 0 | TK_Complete
10MBH70 | TT_Task | Hydro Test | 30/09/2019 | 04/10/2019 | 21/09/2019 | 04/10/2019 | 0 | TK_Complete
10MBH80 | TT_Task | Painting/Insulation | 16/08/2019 | 21/08/2019 | 10/08/2019 | 29/11/2019 | 0 | TK_Complete
10MBH90 | TT_Task | Pre-Commissioning/Flushing/Cleaning | 17/09/2019 | 23/09/2019 | 07/09/2019 | 29/11/2019 | 0 | TK_Complete
10MBN10 | TT_Task | Install Equipment/Skids/Pumps | 08/04/2019 | 25/04/2019 | 06/04/2019 | 07/06/2019 | 0 | TK_Complete
10MBN20 | TT_Task | Install Large Bore Pipe/Valves/Supports | 21/01/2019 | 11/03/2019 | 21/01/2019 | 22/04/2019 | 0 | TK_Complete
10MBN30 | TT_Task | Install Small Bore Pipe/Valves/Supports | 01/04/2019 | 06/05/2019 | 04/04/2019 | 03/09/2019 | 0 | TK_Complete
10MBN40 | TT_Task | NDE | 23/04/2019 | 22/05/2019 | 23/04/2019 | 17/09/2019 | 0 | TK_Complete
10MBN50 | TT_Task | EC+I | 30/04/2019 | 04/06/2019 | 08/05/2019 | 14/09/2019 | 0 | TK_Complete
10MBN60 | TT_Task | Line Inspection | 04/09/2019 | 07/09/2019 | 14/09/2019 | 19/09/2019 | 0 | TK_Complete
10MBN70 | TT_Task | Hydro Test | 30/09/2019 | 04/10/2019 | 26/10/2019 | 26/10/2019 | 0 | TK_Complete
10MBN80 | TT_Task | Painting/Insulation | 21/06/2019 | 10/07/2019 | 13/06/2019 | 06/11/2019 | 0 | TK_Complete
10MBN90 | TT_Task | Pre-Commissioning/Flushing/Cleaning | 17/09/2019 | 24/09/2019 | 07/09/2019 | 06/11/2019 | 0 | TK_Complete
10MBP10 | TT_Task | Install Fuel Gas Equipment/Skids | 06/04/2019 | 25/04/2019 | 09/04/2019 | 23/07/2019 | 0 | TK_Complete
10MBP20 | TT_Task | Install Large Bore Pipe/Valves/Supports | 23/05/2019 | 19/06/2019 | 15/05/2019 | 25/07/2019 | 0 | TK_Complete
10MBP30 | TT_Task | Install Small Bore Pipe/Valves/Supports | 07/06/2019 | 26/06/2019 | 24/05/2019 | 25/07/2019 | 0 | TK_Complete
10MBP40 | TT_Task | NDE | 22/05/2019 | 26/06/2019 | 22/05/2019 | 21/09/2019 | 0 | TK_Complete
10MBP50 | TT_Task | EC+I | 25/06/2019 | 19/07/2019 | 24/06/2019 | 12/09/2019 | 0 | TK_Complete
10MBP60 | TT_Task | Line Inspection | 07/09/2019 | 12/09/2019 | 17/09/2019 | 20/09/2019 | 0 | TK_Complete
10MBP70 | TT_Task | Hydro Test | 30/09/2019 | 04/10/2019 | 22/10/2019 | 24/10/2019 | 0 | TK_Complete
10MBP80 | TT_Task | Painting/Insulation | 25/06/2019 | 13/07/2019 | 13/06/2019 | 21/11/2019 | 0 | TK_Complete
10MBP90 | TT_Task | Pre-Commissioning/Flushing/Cleaning | 18/09/2019 | 24/09/2019 | 14/09/2019 | 21/11/2019 | 0 | TK_Complete
10MBX05 | TT_Task | Set Equipment/Skids/Pumps | 08/04/2019 | 09/04/2019 | 06/04/2019 | 05/06/2019 | 0 | TK_Complete
10MBX10 | TT_Task | Final nstall Equipment/Skids/Pumps | 14/06/2019 | 18/06/2019 | 01/06/2019 | 26/07/2019 | 0 | TK_Complete
10MBX100 | TT_Task | Final Pipe Connections to Skid | 17/06/2019 | 19/06/2019 | 17/06/2019 | 03/09/2019 | 0 | TK_Complete
10MBX20 | TT_Task | Install Large Bore Pipe/Valves/Supports | 01/04/2019 | 27/04/2019 | 02/04/2019 | 04/09/2019 | 0 | TK_Complete
10MBX30 | TT_Task | Install Small Bore Pipe/Valves/Supports | 23/04/2019 | 17/05/2019 | 23/04/2019 | 06/09/2019 | 0 | TK_Complete
10MBX40 | TT_Task | NDE | 16/04/2019 | 13/05/2019 | 16/04/2019 | 10/09/2019 | 0 | TK_Complete
10MBX50 | TT_Task | EC+I | 31/05/2019 | 26/06/2019 | 01/06/2019 | 14/09/2019 | 0 | TK_Complete
10MBX60 | TT_Task | Line Inspection | 12/08/2019 | 16/08/2019 | 27/08/2019 | 04/09/2019 | 0 | TK_Complete
10MBX70 | TT_Task | Hydro Test | 16/08/2019 | 28/08/2019 | 29/08/2019 | 07/09/2019 | 0 | TK_Complete
10MBX80 | TT_Task | Painting/Insulation | 30/04/2019 | 24/05/2019 | 06/05/2019 | 13/09/2019 | 0 | TK_Complete
10MBX90 | TT_Task | Pre-Commissioning/Flushing/Cleaning | 28/08/2019 | 11/09/2019 | 31/08/2019 | 13/09/2019 | 0 | TK_Complete
10MBV1000 | TT_Task | Set GT Lube Oil Package into Position - Skid | 29/09/2018 | 29/09/2018 | 14/09/2018 | 29/09/2018 | 0 | TK_Complete
10MBV1010 | TT_Task | Install Equipment/Skids/Pumps | 30/11/2018 | 07/12/2018 | 10/10/2018 | 11/10/2018 | 0 | TK_Complete
10MBV1020 | TT_Task | Install Large Bore Pipe/Valves/Supports | 19/02/2019 | 08/05/2019 | 07/01/2019 | 20/06/2019 | 0 | TK_Complete
10MBV1030 | TT_Task | Install Small Bore Pipe/Valves/Supports | 08/02/2019 | 26/03/2019 | 18/03/2019 | 25/05/2019 | 0 | TK_Complete
10MBV1040 | TT_Task | NDE | 03/04/2019 | 25/04/2019 | 03/04/2019 | 25/06/2019 | 0 | TK_Complete
10MBV1050 | TT_Task | EC+I | 27/05/2019 | 18/06/2019 | 27/05/2019 | 14/09/2019 | 0 | TK_Complete
10MBV1060 | TT_Task | Line Inspection | 10/06/2019 | 13/06/2019 | 04/06/2019 | 08/06/2019 | 0 | TK_Complete
10MBV1080 | TT_Task | Painting/Insulation | 31/05/2019 | 18/06/2019 | 21/05/2019 | 12/10/2019 | 0 | TK_Complete
10MBV1083 | TT_Mile | Temporary Power Available for GT Lube Oil Flush &amp; Restore | 31/05/2019 | 31/05/2019 | 24/05/2019 | 24/05/2019 | 0 | TK_Complete
10MBV1085 | TT_Task | GT Lube Oil/Lifting Flush &amp; Restore | 31/05/2019 | 22/06/2019 | 20/06/2019 | 13/07/2019 | 0 | TK_Complete
10MBV1090 | TT_Task | Pre-Commissioning/Cleaning | 06/09/2019 | 17/09/2019 | 06/09/2019 | 12/10/2019 | 0 | TK_Complete
10MBX2x05 | TT_Task | Set Pneumatic Skid Package into Position | 01/04/2019 | 02/04/2019 | 03/04/2019 | 11/06/2019 | 0 | TK_Complete
10MBX2x10 | TT_Task | Install Equipment/Skids/Pumps | 03/06/2019 | 11/06/2019 | 15/05/2019 | 25/07/2019 | 0 | TK_Complete
10MBX2x20 | TT_Task | Install Large Bore Pipe/Valves/Supports | 02/04/2019 | 30/04/2019 | 02/04/2019 | 14/09/2019 | 0 | TK_Complete
10MBX2x30 | TT_Task | Install Small Bore Pipe/Valves/Supports | 09/04/2019 | 08/05/2019 | 09/04/2019 | 14/09/2019 | 0 | TK_Complete
10MBX2x40 | TT_Task | NDE | 25/05/2019 | 12/06/2019 | 25/05/2019 | 21/09/2019 | 0 | TK_Complete
10MBX2x50 | TT_Task | EC+I | 24/06/2019 | 24/07/2019 | 01/06/2019 | 14/09/2019 | 0 | TK_Complete
10MBX2x60 | TT_Task | Line Inspection | 04/09/2019 | 09/09/2019 | 04/09/2019 | 19/09/2019 | 0 | TK_Complete
10MBX2x70 | TT_Task | Hydro Test | 09/09/2019 | 17/09/2019 | 21/09/2019 | 27/09/2019 | 0 | TK_Complete
10MBX2x80 | TT_Task | Painting/Insulation | 16/07/2019 | 08/08/2019 | 26/07/2019 | 11/10/2019 | 0 | TK_Complete
10MBX2x90 | TT_Task | Pre-Commissioning/Flushing/Cleaning | 17/09/2019 | 24/09/2019 | 14/09/2019 | 11/10/2019 | 0 | TK_Complete
10MBA5x05 | TT_Task | Set Hydraulic Clearance Optimization Package into Position | 08/04/2019 | 09/04/2019 | 06/04/2019 | 06/05/2019 | 0 | TK_Complete
10MBA5x10 | TT_Task | Install Equipment/Skids/Pumps | 08/04/2019 | 16/04/2019 | 08/04/2019 | 04/05/2019 | 0 | TK_Complete
10MBA5x20 | TT_Task | Install Large Bore Pipe/Valves/Supports | 13/04/2019 | 07/05/2019 | 13/04/2019 | 24/08/2019 | 0 | TK_Complete
10MBA5x30 | TT_Task | Install Small Bore Pipe/Valves/Supports | 13/04/2019 | 07/05/2019 | 13/04/2019 | 24/08/2019 | 0 | TK_Complete
10MBA5x40 | TT_Task | NDE | 10/05/2019 | 28/05/2019 | 10/05/2019 | 27/08/2019 | 0 | TK_Complete
10MBA5x50 | TT_Task | EC+I | 21/05/2019 | 13/06/2019 | 21/05/2019 | 13/09/2019 | 0 | TK_Complete
10MBA5x60 | TT_Task | Line Inspection | 31/08/2019 | 04/09/2019 | 07/09/2019 | 19/09/2019 | 0 | TK_Complete
10MBA5x70 | TT_Task | Hydro Test | 30/09/2019 | 15/10/2019 | 30/09/2019 | 05/10/2019 | 0 | TK_Complete
10MBA5x80 | TT_Task | Painting/Insulation | 01/06/2019 | 26/06/2019 | 20/05/2019 | 12/10/2019 | 0 | TK_Complete
10MBA5x90 | TT_Task | Pre-Commissioning/Flushing/Cleaning | 19/09/2019 | 09/10/2019 | 07/09/2019 | 12/10/2019 | 0 | TK_Complete
10MBA4x10 | TT_Task | Install Equipment/Skids/Pumps | 31/12/2018 | 15/01/2019 | 31/12/2018 | 11/01/2019 | 0 | TK_Complete
10MBA4x20 | TT_Task | Install Large Bore Pipe/Valves/Supports | 01/04/2019 | 23/04/2019 | 01/04/2019 | 10/07/2019 | 0 | TK_Complete
10MBA4x30 | TT_Task | Install Small Bore Pipe/Valves/Supports | 15/05/2019 | 25/05/2019 | 15/05/2019 | 10/07/2019 | 0 | TK_Complete
10MBA4x40 | TT_Task | NDE | 21/05/2019 | 31/05/2019 | 21/05/2019 | 13/07/2019 | 0 | TK_Complete
10MBA4x50 | TT_Task | EC+I | 10/07/2019 | 20/07/2019 | 10/07/2019 | 20/07/2019 | 0 | TK_Complete
10MBA4x60 | TT_Task | Line Inspection | 22/07/2019 | 31/07/2019 | 22/07/2019 | 31/07/2019 | 0 | TK_Complete
10MBA4x70 | TT_Task | Hydro Test | 31/07/2019 | 09/08/2019 | 01/06/2019 | 15/06/2019 | 0 | TK_Complete
10MBA4x80 | TT_Task | Painting/Insulation | 10/07/2019 | 30/07/2019 | 11/05/2019 | 23/07/2019 | 0 | TK_Complete
10MBA4x90 | TT_Task | Pre-Commissioning/Flushing/Cleaning | 10/08/2019 | 20/08/2019 | 15/06/2019 | 22/08/2019 | 0 | TK_Complete
00MBU10 | TT_Task | Install Equipment/Skids/Pumps | 24/01/2019 | 08/02/2019 | 15/12/2018 | 20/12/2018 | 0 | TK_Complete
00MBU20 | TT_Task | Install Large Bore Pipe/Valves/Supports | 18/02/2019 | 12/04/2019 | 12/02/2019 | 06/07/2019 | 0 | TK_Complete
00MBU30 | TT_Task | Install Small Bore Pipe/Valves/Supports | 27/05/2019 | 21/06/2019 | 27/05/2019 | 08/07/2019 | 0 | TK_Complete
00MBU40 | TT_Task | NDE | 10/06/2019 | 21/06/2019 | 28/05/2019 | 13/07/2019 | 0 | TK_Complete
00MBU50 | TT_Task | E&amp;IC Installation MBU | 08/07/2019 | 18/07/2019 | 08/07/2019 | 18/07/2019 | 0 | TK_Complete
00MBU60 | TT_Task | Line Inspection | 31/07/2019 | 08/08/2019 | 01/06/2019 | 08/06/2019 | 0 | TK_Complete
00MBU70 | TT_Task | Hydro Test | 09/08/2019 | 19/08/2019 | 15/06/2019 | 22/06/2019 | 0 | TK_Complete
00MBU80 | TT_Task | Painting/Insulation | 31/07/2019 | 08/08/2019 | 01/06/2019 | 08/06/2019 | 0 | TK_Complete
00MBU90 | TT_Task | Pre-Commissioning/Flushing/Cleaning | 20/08/2019 | 30/08/2019 | 22/06/2019 | 13/07/2019 | 0 | TK_Complete
10MBU10 | TT_Task | Install Equipment/Skids/Pumps | 01/03/2019 | 02/04/2019 | 15/12/2018 | 23/04/2019 | 0 | TK_Complete
10MBU20 | TT_Task | Install Large Bore Pipe/Valves/Supports | 24/04/2019 | 14/05/2019 | 24/04/2019 | 06/07/2019 | 0 | TK_Complete
10MBU30 | TT_Task | Install Small Bore Pipe/Valves/Supports | 25/04/2019 | 16/05/2019 | 25/04/2019 | 08/07/2019 | 0 | TK_Complete
10MBU40 | TT_Task | NDE | 10/05/2019 | 15/05/2019 | 10/05/2019 | 10/07/2019 | 0 | TK_Complete
10MBU50 | TT_Task | EC+I | 08/07/2019 | 24/07/2019 | 08/07/2019 | 24/07/2019 | 0 | TK_Complete
10MBU60 | TT_Task | Line Inspection | 10/07/2019 | 20/07/2019 | 10/07/2019 | 12/07/2019 | 0 | TK_Complete
10MBU70 | TT_Task | Hydro Test | 20/07/2019 | 02/08/2019 | 13/07/2019 | 17/07/2019 | 0 | TK_Complete
10MBU80 | TT_Task | Painting/Insulation | 05/07/2019 | 13/07/2019 | 05/07/2019 | 24/07/2019 | 0 | TK_Complete
10MBU90 | TT_Task | Pre-Commissioning/Flushing/Cleaning | 31/07/2019 | 13/08/2019 | 08/06/2019 | 15/06/2019 | 0 | TK_Complete
10MBA18-100 | TT_Task | Set Compressor Cleaning Package into Position -Skid | 31/10/2018 | 05/11/2018 | 26/10/2018 | 30/10/2018 | 0 | TK_Complete
10MBA18-110 | TT_Task | Final Align Compressor Cleaning Package and final pipe connections | 18/06/2019 | 26/06/2019 | 08/06/2019 | 03/10/2019 | 0 | TK_Complete
10MBA18-120 | TT_Task | Install Large Bore Pipe/Valves/Supports | 01/04/2019 | 06/05/2019 | 01/04/2019 | 05/09/2019 | 0 | TK_Complete
10MBA18-130 | TT_Task | Install Small Bore Pipe/Valves/Supports | 23/04/2019 | 22/05/2019 | 23/04/2019 | 05/09/2019 | 0 | TK_Complete
10MBA18-140 | TT_Task | NDE | 06/05/2019 | 29/05/2019 | 06/05/2019 | 21/09/2019 | 0 | TK_Complete
10MBA18-150 | TT_Task | EC+I | 29/05/2019 | 12/06/2019 | 23/05/2019 | 11/09/2019 | 0 | TK_Complete
10MBA18-160 | TT_Task | Line Inspection | 04/09/2019 | 05/09/2019 | 16/09/2019 | 18/09/2019 | 0 | TK_Complete
10MBA18-170 | TT_Task | Hydro Test | 06/09/2019 | 09/09/2019 | 19/09/2019 | 21/09/2019 | 0 | TK_Complete
10MBA18-180 | TT_Task | Painting/Insulation | 29/05/2019 | 03/06/2019 | 23/05/2019 | 12/10/2019 | 0 | TK_Complete
10MBA18-190 | TT_Task | Pre-Commissioning/Flushing/Cleaning | 10/09/2019 | 12/09/2019 | 21/09/2019 | 12/10/2019 | 0 | TK_Complete
10QFB10 | TT_Task | Install Equipment/Skids/Pumps | 29/06/2019 | 05/07/2019 | 29/06/2019 | 05/07/2019 | 0 | TK_Complete
10QFB20 | TT_Task | Install Large Bore Pipe/Valves/Supports | 04/05/2019 | 22/06/2019 | 02/01/2019 | 06/07/2019 | 0 | TK_Complete
10QFB30 | TT_Task | Install Small Bore Pipe/Valves/Supports | 04/07/2019 | 17/07/2019 | 04/07/2019 | 17/07/2019 | 0 | TK_Complete
10QFB40 | TT_Task | NDE | 10/07/2019 | 17/07/2019 | 10/07/2019 | 19/07/2019 | 0 | TK_Complete
10QFB50 | TT_Task | EC+I | 18/07/2019 | 09/08/2019 | 10/07/2019 | 27/07/2019 | 0 | TK_Complete
10QFB60 | TT_Task | Line Inspection | 10/07/2019 | 17/07/2019 | 10/07/2019 | 17/07/2019 | 0 | TK_Complete
10QFB70 | TT_Task | Hydro Test | 31/07/2019 | 03/08/2019 | 22/06/2019 | 29/06/2019 | 0 | TK_Complete
10QFB80 | TT_Task | Painting/Insulation | 13/07/2019 | 26/07/2019 | 13/07/2019 | 26/07/2019 | 0 | TK_Complete
10QFB90 | TT_Task | Pre-Commissioning/Flushing/Cleaning | 05/08/2019 | 12/08/2019 | 29/06/2019 | 12/11/2019 | 0 | TK_Complete
TWS06.2520 | TT_Task | Installation of Ventilation System for Gas Turbine Enclosure and Skid Enclosures | 30/04/2019 | 28/06/2019 | 09/05/2019 | 26/09/2019 | 0 | TK_Complete
FSS22.1180 | TT_Task | Installation of Fire Detection System for GT Noise Enclosure MPB | 01/07/2019 | 11/09/2019 | 13/07/2019 | 08/01/2020 | 0 | TK_Complete
A1900 | TT_Task | Set on Base Boiler Blowdown Vessel | 13/11/2018 | 13/11/2018 | 06/11/2018 | 08/11/2018 | 0 | TK_Complete
A1910 | TT_Task | Tie In Works to BD Vessel | 06/05/2019 | 28/05/2019 | 06/05/2019 | 13/06/2019 | 0 | TK_Complete
A2380 | TT_Task | Erection Main Piperack Structure (UMY00Y Modules) | 20/11/2018 | 07/12/2018 | 07/11/2018 | 30/11/2018 | 0 | TK_Complete
ECS20.1100 | TT_Task | Erection of Boiler Platforms and Ladders | 17/10/2018 | 28/12/2018 | 15/09/2018 | 25/03/2019 | 0 | TK_Complete
ECS20.1180 | TT_Task | Erection of Inlet Duct | 11/10/2018 | 09/01/2019 | 16/10/2018 | 29/03/2019 | 0 | TK_Complete
ECS20.1200 | TT_Task | Pressure Test Walkdowns and Prep | 14/06/2019 | 27/06/2019 | 14/05/2019 | 19/10/2019 | 0 | TK_Complete
ECS20.1220 | TT_Task | PWHT HRSG Casing roof beams | 26/06/2018 | 12/07/2018 | 23/06/2018 | 14/07/2018 | 0 | TK_Complete
ECS20.1230 | TT_Task | Completion Works at Roof Beams - NDE, Roof Beam Seam Welds, Painting, Insulation + Liner Plates, Modify | 09/07/2018 | 19/07/2018 | 15/07/2018 | 26/07/2018 | 0 | TK_Complete
HRS09.1020 | TT_Task | Installation of Main Steel Structure HRSG (Main Frame / Casing) without PWHT of roof beams | 03/04/2018 | 13/06/2018 | 06/04/2018 | 22/06/2018 | 0 | TK_Complete
HRS09.1030 | TT_Task | Preparation of Foundations and installation of Sole Plates | 06/03/2018 | 15/03/2018 | 12/03/2018 | 23/04/2018 | 0 | TK_Complete
HRS10.1010 | TT_Mile | First Del to pad of Modules (Heating Surfaces) | 20/07/2018 | 20/07/2018 | 24/07/2018 | 24/07/2018 | 0 | TK_Complete
HRS10.1020 | TT_Task | Alignment and Installation of Modules (Heating Surfaces) | 20/07/2018 | 20/08/2018 | 27/07/2018 | 08/09/2018 | 0 | TK_Complete
HRS10.1020a | TT_Task | Resolve Row 2 Support Beam Issue / SPMT Working on Stack Delivery | 30/08/2018 | 15/09/2018 | 18/08/2018 | 31/08/2018 | 0 | TK_Complete
HRS10.1050 | TT_Task | Installation of Supports &amp; Drums of HRSG | 15/10/2018 | 25/10/2018 | 20/09/2018 | 27/10/2018 | 0 | TK_Complete
HRS10.1060 | TT_Mile | HRSG Structure Ready for Modules &amp; Drums | 26/06/2018 | 26/06/2018 | 26/06/2018 | 26/06/2018 | 0 | TK_Complete
HRS10.1070 | TT_Task | Modules Welding | 06/11/2018 | 28/11/2018 | 01/11/2018 | 30/11/2018 | 0 | TK_Complete
HRS10.1080 | TT_FinMile | Civil Contractor H/O West Side of HRSG back | 06/11/2018 | 06/11/2018 | 06/11/2018 | 06/11/2018 | 0 | TK_Complete
HRS10.1090 | TT_FinMile | Punchlist &amp; Final Completion of HRSG Foundation Works - Prepare Pockets for GL11 Sole Plates | 24/07/2018 | 24/07/2018 | 18/04/2018 | 18/04/2018 | 0 | TK_Complete
HRS10.1100 | TT_Task | Erect Stair Towers | 26/05/2018 | 19/07/2018 | 11/06/2018 | 29/10/2018 | 0 | TK_Complete
HRS10.1110 | TT_FinMile | Civil Contractor H/O Inlet Duct Foundation | 06/11/2018 | 06/11/2018 | 15/10/2018 | 15/10/2018 | 0 | TK_Complete
HRS11.1170 | TT_Task | Installation of HRSG Piping | 06/11/2018 | 13/05/2019 | 07/11/2018 | 28/05/2019 | 0 | TK_Complete
HRS11.1200 | TT_Task | Reconfigure Post Hydro Test | 02/10/2019 | 24/10/2019 | 19/10/2019 | 29/11/2019 | 0 | TK_Complete
HRS12.1000 | TT_Task | Completion of the HRSG ready to start Piping | 19/10/2018 | 24/10/2018 | 12/10/2018 | 24/10/2018 | 0 | TK_Complete
10HAD80-20 | TT_Task | Install Large Bore Pipe/Valves/Supports | 10/12/2018 | 05/04/2019 | 23/11/2018 | 25/05/2019 | 0 | TK_Complete
10HAD80-30 | TT_Task | Install Small Bore Pipe/Valves/Supports | 21/02/2019 | 07/05/2019 | 21/02/2019 | 14/06/2019 | 0 | TK_Complete
10HAD80-40 | TT_Task | NDE | 25/01/2019 | 07/05/2019 | 23/11/2018 | 18/06/2019 | 0 | TK_Complete
10HAD80-50 | TT_Task | EC+I | 15/06/2019 | 22/07/2019 | 18/05/2019 | 21/09/2019 | 0 | TK_Complete
10HAD80-60 | TT_Task | Line Inspection | 07/06/2019 | 12/06/2019 | 13/05/2019 | 17/05/2019 | 0 | TK_Complete
10HAD80-70 | TT_Task | Hydro Test with HRSG | 27/06/2019 | 04/07/2019 | 18/05/2019 | 25/05/2019 | 0 | TK_Complete
10HAD80-80 | TT_Task | Painting/Insulation | 15/06/2019 | 17/07/2019 | 18/05/2019 | 22/11/2019 | 0 | TK_Complete
10HAD80-90 | TT_Task | Pre-Commissioning/Flushing/Cleaning | 25/09/2019 | 09/10/2019 | 07/09/2019 | 22/11/2019 | 0 | TK_Complete
10HAD50-20 | TT_Task | Install Large Bore Pipe/Valves/Supports | 10/12/2018 | 05/04/2019 | 09/11/2018 | 22/05/2019 | 0 | TK_Complete
10HAD50-30 | TT_Task | Install Small Bore Pipe/Valves/Supports | 12/02/2019 | 26/04/2019 | 09/11/2018 | 14/06/2019 | 0 | TK_Complete
10HAD50-40 | TT_Task | NDE | 05/03/2019 | 24/04/2019 | 09/11/2018 | 18/06/2019 | 0 | TK_Complete
10HAD50-50 | TT_Task | EC+I | 15/06/2019 | 27/07/2019 | 15/05/2019 | 21/09/2019 | 0 | TK_Complete
10HAD50-60 | TT_Task | Line Inspection | 15/06/2019 | 25/06/2019 | 15/06/2019 | 25/06/2019 | 0 | TK_Complete
10HAD50-70 | TT_Task | Hydro Test with HRSG | 28/06/2019 | 13/07/2019 | 21/06/2019 | 13/07/2019 | 0 | TK_Complete
10HAD50-80 | TT_Task | Painting/Insulation | 15/06/2019 | 17/07/2019 | 13/05/2019 | 22/11/2019 | 0 | TK_Complete
10HAD50-90 | TT_Task | Pre-Commissioning/Flushing/Cleaning | 06/09/2019 | 21/09/2019 | 07/09/2019 | 22/11/2019 | 0 | TK_Complete
10HAD10-20 | TT_Task | Install Large Bore Pipe/Valves/Supports | 10/12/2018 | 30/04/2019 | 08/11/2018 | 17/05/2019 | 0 | TK_Complete
10HAD10-30 | TT_Task | Install Small Bore Pipe/Valves/Supports | 23/02/2019 | 26/04/2019 | 08/11/2018 | 14/05/2019 | 0 | TK_Complete
10HAD10-40 | TT_Task | NDE | 01/02/2019 | 22/03/2019 | 30/04/2019 | 20/05/2019 | 0 | TK_Complete
10HAD10-50 | TT_Task | EC+I | 15/06/2019 | 20/07/2019 | 20/05/2019 | 28/09/2019 | 0 | TK_Complete
10HAD10-60 | TT_Task | Line Inspection | 27/06/2019 | 16/07/2019 | 27/06/2019 | 06/07/2019 | 0 | TK_Complete
10HAD10-70 | TT_Task | Hydro Test with HRSG | 02/09/2019 | 12/09/2019 | 30/08/2019 | 26/10/2019 | 0 | TK_Complete
10HAD10-80 | TT_Task | Painting/Insulation | 31/05/2019 | 29/06/2019 | 31/05/2019 | 22/11/2019 | 0 | TK_Complete
10HAD10-90 | TT_Task | Pre-Commissioning/Flushing/Cleaning | 24/10/2019 | 05/11/2019 | 05/10/2019 | 22/11/2019 | 0 | TK_Complete
10HAA10 | TT_Task | Install Equipment/Skids/Pumps | 24/05/2019 | 04/06/2019 | 23/05/2019 | 10/06/2019 | 0 | TK_Complete
10HAA20 | TT_Task | Install Large Bore Pipe/Valves/Supports | 10/12/2018 | 02/02/2019 | 10/12/2018 | 21/05/2019 | 0 | TK_Complete
10HAA30 | TT_Task | Install Small Bore Pipe/Valves/Supports | 17/04/2019 | 28/05/2019 | 17/01/2019 | 25/06/2019 | 0 | TK_Complete
10HAA40 | TT_Task | NDE | 17/04/2019 | 28/05/2019 | 10/12/2018 | 27/06/2019 | 0 | TK_Complete
10HAA50 | TT_Task | EC+I | 28/06/2019 | 22/07/2019 | 15/05/2019 | 28/09/2019 | 0 | TK_Complete
10HAA60 | TT_Task | Line Inspection | 25/06/2019 | 08/07/2019 | 25/06/2019 | 20/07/2019 | 0 | TK_Complete
10HAA70 | TT_Task | Hydro Test | 11/07/2019 | 24/07/2019 | 13/07/2019 | 07/09/2019 | 0 | TK_Complete
10HAA80 | TT_Task | Painting/Insulation | 28/06/2019 | 23/07/2019 | 17/05/2019 | 11/11/2019 | 0 | TK_Complete
10HAA90 | TT_Task | Pre-Commissioning/Flushing/Cleaning | 17/09/2019 | 30/09/2019 | 09/09/2019 | 11/11/2019 | 0 | TK_Complete
ADD_BY_CLP_01 | TT_Task | Insulation of Stack + Complete Outlet Duct | 30/04/2019 | 06/08/2019 | 13/05/2019 | 21/11/2019 | 0 | TK_Complete
ECS20.1190 | TT_Task | Erection of Stack | 15/10/2018 | 15/04/2019 | 31/08/2018 | 20/06/2019 | 0 | TK_Complete
10LCL20 | TT_Task | Install Large Bore Pipe/Valves/Supports | 08/02/2019 | 06/05/2019 | 08/02/2019 | 27/07/2019 | 0 | TK_Complete
10LCL30 | TT_Task | Install Small Bore Pipe/Valves/Supports | 04/03/2019 | 30/05/2019 | 04/03/2019 | 25/07/2019 | 0 | TK_Complete
10LCL40 | TT_Task | NDE | 25/03/2019 | 11/06/2019 | 25/03/2019 | 10/08/2019 | 0 | TK_Complete
10LCL50 | TT_Task | EC+I | 18/06/2019 | 23/07/2019 | 08/06/2019 | 21/09/2019 | 0 | TK_Complete
10LCL60 | TT_Task | Line Inspection | 08/07/2019 | 17/07/2019 | 03/08/2019 | 07/08/2019 | 0 | TK_Complete
10LCL70 | TT_Task | Hydro Test | 05/08/2019 | 15/08/2019 | 05/08/2019 | 10/08/2019 | 0 | TK_Complete
10LCL80 | TT_Task | Painting/Insulation | 21/05/2019 | 22/06/2019 | 21/05/2019 | 15/11/2019 | 0 | TK_Complete
10LCL90 | TT_Task | Pre-Commissioning/Flushing/Cleaning | 05/09/2019 | 18/09/2019 | 07/09/2019 | 15/11/2019 | 0 | TK_Complete
10CFE10 | TT_Task | Skid/Panels/Cabinets Installation | 18/06/2019 | 05/07/2019 | 20/05/2019 | 14/06/2019 | 0 | TK_Complete
10CFE100 | TT_Task | Cable Raceway | 28/03/2019 | 18/04/2019 | 15/03/2019 | 20/06/2019 | 0 | TK_Complete
10CFE110 | TT_Task | Cable | 20/06/2019 | 09/07/2019 | 01/06/2019 | 10/06/2019 | 0 | TK_Complete
10CFE120 | TT_Task | Tubing | 14/06/2019 | 06/07/2019 | 14/06/2019 | 17/08/2019 | 0 | TK_Complete
10CFE130 | TT_Task | Instrumentation | 31/07/2019 | 19/08/2019 | 20/07/2019 | 20/09/2019 | 0 | TK_Complete
10CFE150 | TT_Task | Installation CEMS equiptment on Stack | 14/06/2019 | 26/07/2019 | 14/06/2019 | 06/09/2019 | 0 | TK_Complete
ECS20.1050 | TT_Task | Installation of Cable Support Structure for HRSG | 24/04/2019 | 20/07/2019 | 24/04/2019 | 29/06/2019 | 0 | TK_Complete
ECS20.1060 | TT_Task | Installation &amp; Termination of Power &amp; Control Cable for HRSG | 24/05/2019 | 12/08/2019 | 24/05/2019 | 26/06/2019 | 0 | TK_Complete
ECS20.1070 | TT_Task | Installation of Distribution Panel &amp; Control Panel and Racks for HRSG | 24/04/2019 | 10/06/2019 | 24/04/2019 | 22/06/2019 | 0 | TK_Complete
ECS20.1080 | TT_Task | Installation of Instrumentation for HRSG | 01/04/2019 | 10/06/2019 | 22/04/2019 | 28/06/2019 | 0 | TK_Complete
ECS20.1110 | TT_Task | Installation &amp; Termination of Cable for Lighting Fittings for HRSG | 25/02/2019 | 24/04/2019 | 14/01/2019 | 27/06/2019 | 0 | TK_Complete
10MKA1000 | TT_Task | Set Up Equipment on Site | 29/09/2018 | 08/10/2018 | 20/08/2018 | 22/08/2018 | 0 | TK_Complete
10MKA1010 | TT_Task | Check and Prep of Foundation | 30/08/2018 | 12/09/2018 | 22/08/2018 | 23/08/2018 | 0 | TK_Complete
10MKA1020 | TT_Task | Prepare Generator and Lower onto Foundation | 23/10/2018 | 29/10/2018 | 22/09/2018 | 24/09/2018 | 0 | TK_Complete
10MKA1030 | TT_Mile | Commence Weekly Winding Insulation Resistance Checks | 31/10/2018 | 31/10/2018 | 25/10/2018 | 25/10/2018 | 0 | TK_Complete
10MKA1050 | TT_Task | Shift Generator into Position | 23/10/2018 | 24/10/2018 | 26/09/2018 | 04/10/2018 | 0 | TK_Complete
10MKA1070 | TT_Task | Recording the Axial Adjustment of the Shaft System | 31/12/2018 | 17/01/2019 | 14/01/2019 | 28/02/2019 | 0 | TK_Complete
10MKA1080 | TT_Task | Installation and Coupling of Collector Rotor, Swing Check, Decoupling | 01/04/2019 | 12/04/2019 | 05/04/2019 | 27/04/2019 | 0 | TK_Complete
10MKA1090 | TT_FinMile | Inspections, Electrical Installations &amp; Tests Begin | 12/04/2019 | 12/04/2019 | 12/04/2019 | 12/04/2019 | 0 | TK_Complete
10MKA1095 | TT_Task | EC&amp;I | 13/04/2019 | 25/05/2019 | 15/04/2019 | 04/09/2019 | 0 | TK_Complete
10MKA1100 | TT_FinMile | Checking Instrumentaion and Commissioning Seal Oil System Begin | 12/04/2019 | 12/04/2019 | 12/04/2019 | 12/04/2019 | 0 | TK_Complete
10MKA1105 | TT_FinMile | Release for Connection of Piping to The Generator | 10/04/2019 | 10/04/2019 | 10/04/2019 | 10/04/2019 | 0 | TK_Complete
10MKA1120 | TT_Task | Install Isophase Supports | 31/12/2018 | 08/01/2019 | 03/01/2019 | 08/01/2019 | 0 | TK_Complete
10MKA1130 | TT_Task | Install Bushings | 09/01/2019 | 19/01/2019 | 21/01/2019 | 01/02/2019 | 0 | TK_Complete
10MKA1140 | TT_FinMile | Release for Bus Bar Interface at the Terminal Bushing | 01/04/2019 | 01/04/2019 | 01/04/2019 | 01/04/2019 | 0 | TK_Complete
10MKA1150 | TT_Task | Removal of Transport Covers, Installation of Frame Covers | 16/03/2019 | 19/03/2019 | 20/10/2018 | 25/10/2018 | 0 | TK_Complete
10MKA1160 | TT_Task | Install H2 Shaft Seals | 07/11/2018 | 24/11/2018 | 19/11/2018 | 20/12/2018 | 0 | TK_Complete
10MKA1170 | TT_Task | Common Coupling Alignment GT/Gen/ST (with Installed Clutch) | 02/02/2019 | 13/03/2019 | 14/01/2019 | 12/04/2019 | 0 | TK_Complete
10MKA1190 | TT_Task | Fix Generator into Position | 11/02/2019 | 21/02/2019 | 11/02/2019 | 21/02/2019 | 0 | TK_Complete
10MKA1200 | TT_Task | Grouting the Generator Foundation Beams | 25/02/2019 | 06/03/2019 | 07/03/2019 | 07/03/2019 | 0 | TK_Complete
10MKA1210 | TT_Task | Coupling of Collector Rotor | 22/02/2019 | 25/02/2019 | 15/02/2019 | 09/04/2019 | 0 | TK_Complete
10MKA1220 | TT_FinMile | Release for Coupling of the Gas Turbine | 11/04/2019 | 11/04/2019 | 11/04/2019 | 11/04/2019 | 0 | TK_Complete
10MKA1230 | TT_Task | Assembling of Collector | 10/04/2019 | 26/04/2019 | 10/04/2019 | 12/04/2019 | 0 | TK_Complete
10MKA1240 | TT_Task | Removal of Dessicant Bags (Timing to Start - TBE) | 31/08/2019 | 02/09/2019 | 15/06/2019 | 15/06/2019 | 0 | TK_Complete
10MKA1250 | TT_Task | Generator Leak Test | 04/10/2019 | 08/10/2019 | 07/09/2019 | 14/09/2019 | 0 | TK_Complete
10MKA1260 | TT_Task | Install Bearing Bracket Oil Seals TE/EE | 03/05/2019 | 06/05/2019 | 03/05/2019 | 06/05/2019 | 0 | TK_Complete
10MKA1270 | TT_Task | Install Grounding Brushes | 07/05/2019 | 07/05/2019 | 10/08/2019 | 28/08/2019 | 0 | TK_Complete
10MKA1280 | TT_Task | Install Coupling Cover | 03/06/2019 | 04/06/2019 | 25/06/2019 | 08/10/2019 | 0 | TK_Complete
10MKA1290 | TT_Task | Pre-Commissioning/Cleaning | 09/10/2019 | 16/10/2019 | 14/09/2019 | 25/10/2019 | 0 | TK_Complete
10MKW10 | TT_Task | Install Equipment/Skids/Pumps | 15/12/2018 | 24/12/2018 | 19/10/2018 | 26/10/2018 | 0 | TK_Complete
10MKW20 | TT_Task | Install Large Bore Pipe/Valves/Supports | 06/03/2019 | 28/03/2019 | 15/10/2018 | 23/05/2019 | 0 | TK_Complete
10MKW30 | TT_Task | Install Small Bore Pipe/Valves/Supports | 16/04/2019 | 10/05/2019 | 20/03/2019 | 13/04/2019 | 0 | TK_Complete
10MKW40 | TT_Task | NDE | 30/04/2019 | 14/05/2019 | 11/04/2019 | 23/05/2019 | 0 | TK_Complete
10MKW50 | TT_Task | EC+I | 13/04/2019 | 26/04/2019 | 13/04/2019 | 07/08/2019 | 0 | TK_Complete
10MKW60 | TT_Task | Line Inspection | 31/05/2019 | 03/06/2019 | 03/06/2019 | 29/06/2019 | 0 | TK_Complete
10MKW70 | TT_Task | Hydro Test | 31/07/2019 | 05/08/2019 | 03/08/2019 | 17/08/2019 | 0 | TK_Complete
10MKW80 | TT_Task | Painting/Insulation | 12/06/2019 | 21/06/2019 | 13/05/2019 | 26/08/2019 | 0 | TK_Complete
10MKW90 | TT_Task | Pre-Commissioning/Flushing/Cleaning | 30/09/2019 | 16/10/2019 | 30/09/2019 | 05/10/2019 | 0 | TK_Complete
10MKF10 | TT_Task | Install Equipment/Skids/Pumps | 31/10/2018 | 07/11/2018 | 02/10/2018 | 10/10/2018 | 0 | TK_Complete
10MKF20 | TT_Task | Install Large Bore Pipe/Valves/Supports | 31/01/2019 | 16/03/2019 | 15/10/2018 | 26/05/2019 | 0 | TK_Complete
10MKF30 | TT_Task | Install Small Bore Pipe/Valves/Supports | 07/05/2019 | 06/06/2019 | 20/03/2019 | 20/07/2019 | 0 | TK_Complete
10MKF40 | TT_Task | NDE | 01/06/2019 | 06/07/2019 | 22/05/2019 | 20/09/2019 | 0 | TK_Complete
10MKF50 | TT_Task | EC+I | 25/06/2019 | 23/07/2019 | 17/05/2019 | 18/09/2019 | 0 | TK_Complete
10MKF60 | TT_Task | Line Inspection | 19/08/2019 | 24/08/2019 | 10/08/2019 | 17/08/2019 | 0 | TK_Complete
10MKF70 | TT_Task | Hydro Test | 15/10/2019 | 18/10/2019 | 05/10/2019 | 12/10/2019 | 0 | TK_Complete
10MKF80 | TT_Task | Painting/Insulation | 13/06/2019 | 03/07/2019 | 27/06/2019 | 28/10/2019 | 0 | TK_Complete
10MKF90 | TT_Task | Pre-Commissioning/Flushing/Cleaning | 22/10/2019 | 25/10/2019 | 28/10/2019 | 20/11/2019 | 0 | TK_Complete
10MKQ10 | TT_Task | Install Equipment/Skids/Pumps | 01/04/2019 | 09/04/2019 | 08/04/2019 | 11/06/2019 | 0 | TK_Complete
10MKQ20 | TT_Task | Install Large Bore Pipe/Valves/Supports | 14/03/2019 | 06/04/2019 | 07/01/2019 | 28/08/2019 | 0 | TK_Complete
10MKQ30 | TT_Task | Install Small Bore Pipe/Valves/Supports | 25/04/2019 | 20/05/2019 | 20/03/2019 | 28/08/2019 | 0 | TK_Complete
10MKQ40 | TT_Task | NDE | 09/04/2019 | 20/04/2019 | 09/04/2019 | 19/09/2019 | 0 | TK_Complete
10MKQ50 | TT_Task | EC+I | 24/04/2019 | 08/05/2019 | 24/04/2019 | 21/09/2019 | 0 | TK_Complete
10MKQ60 | TT_Task | Line Inspection | 31/08/2019 | 09/09/2019 | 07/09/2019 | 17/09/2019 | 0 | TK_Complete
10MKQ70 | TT_Task | Hydro Test | 30/09/2019 | 05/10/2019 | 05/10/2019 | 11/10/2019 | 0 | TK_Complete
10MKQ90 | TT_Task | Pre-Commissioning/Flushing/Cleaning | 08/10/2019 | 12/10/2019 | 07/10/2019 | 12/10/2019 | 0 | TK_Complete
10MKG10 | TT_Task | Install Equipment/Skids/Pumps | 01/11/2018 | 12/11/2018 | 17/10/2018 | 27/10/2018 | 0 | TK_Complete
10MKG20 | TT_Task | Install Large Bore Pipe/Valves/Supports | 01/04/2019 | 07/05/2019 | 01/11/2018 | 10/08/2019 | 0 | TK_Complete
10MKG30 | TT_Task | Install Small Bore Pipe/Valves/Supports | 08/05/2019 | 04/06/2019 | 05/11/2018 | 10/08/2019 | 0 | TK_Complete
10MKG40 | TT_Task | NDE | 30/04/2019 | 24/05/2019 | 17/05/2019 | 21/09/2019 | 0 | TK_Complete
10MKG50 | TT_Task | EC+I | 30/04/2019 | 23/05/2019 | 17/05/2019 | 21/09/2019 | 0 | TK_Complete
10MKG60 | TT_Task | Line Inspection | 07/08/2019 | 12/08/2019 | 05/08/2019 | 10/08/2019 | 0 | TK_Complete
10MKG70 | TT_Task | Hydro Test | 30/09/2019 | 09/10/2019 | 12/10/2019 | 19/10/2019 | 0 | TK_Complete
10MKG80 | TT_Task | Painting/Insulation | 04/07/2019 | 27/07/2019 | 24/07/2019 | 01/11/2019 | 0 | TK_Complete
10MKG90 | TT_Task | Pre-Commissioning/Flushing/Cleaning | 10/10/2019 | 18/10/2019 | 14/10/2019 | 01/11/2019 | 0 | TK_Complete
10LAC05 | TT_Task | Preparation of Feed Water Pump Foundations | 11/02/2019 | 14/02/2019 | 29/01/2019 | 07/02/2019 | 0 | TK_Complete
10LAC10 | TT_Task | Install Feedwater Pump Skid (LAC10Y) | 15/02/2019 | 28/02/2019 | 15/02/2019 | 08/05/2019 | 0 | TK_Complete
10LAC20 | TT_Task | Install Large Bore Pipe/Valves/Supports | 13/04/2019 | 04/06/2019 | 13/04/2019 | 20/07/2019 | 0 | TK_Complete
10LAC30 | TT_Task | Install Small Bore Pipe/Valves/Supports | 23/05/2019 | 05/07/2019 | 20/05/2019 | 20/07/2019 | 0 | TK_Complete
10LAC40 | TT_Task | NDE | 16/05/2019 | 05/07/2019 | 16/05/2019 | 20/09/2019 | 0 | TK_Complete
10LAC50 | TT_Task | EC+I | 10/06/2019 | 16/07/2019 | 22/05/2019 | 21/09/2019 | 0 | TK_Complete
10LAC60 | TT_Task | Line Inspection | 04/07/2019 | 12/07/2019 | 27/07/2019 | 24/08/2019 | 0 | TK_Complete
10LAC70 | TT_Task | Hydro Test | 31/08/2019 | 07/09/2019 | 14/09/2019 | 14/09/2019 | 0 | TK_Complete
10LAC80 | TT_Task | Painting/Insulation | 27/06/2019 | 16/07/2019 | 21/06/2019 | 14/11/2019 | 0 | TK_Complete
10LAC90 | TT_Task | Pre-Commissioning/Flushing/Cleaning | 30/09/2019 | 17/10/2019 | 03/10/2019 | 14/11/2019 | 0 | TK_Complete
10LAB10 | TT_Task | Install Equipment/Skids/Pumps/ | 01/04/2019 | 08/05/2019 | 01/03/2019 | 18/06/2019 | 0 | TK_Complete
10LAB100 | TT_Task | Insulation of FInal Weld Connections | 31/08/2019 | 17/09/2019 | 21/09/2019 | 14/11/2019 | 0 | TK_Complete
10LAB20 | TT_Task | Install Large Bore Pipe/Valves/Supports | 28/02/2019 | 10/05/2019 | 28/02/2019 | 20/07/2019 | 0 | TK_Complete
10LAB30 | TT_Task | Install Small Bore Pipe/Valves/Supports | 14/05/2019 | 22/06/2019 | 14/05/2019 | 20/07/2019 | 0 | TK_Complete
10LAB40 | TT_Task | NDE | 04/05/2019 | 22/06/2019 | 04/05/2019 | 21/09/2019 | 0 | TK_Complete
10LAB50 | TT_Task | EC+I | 31/05/2019 | 06/07/2019 | 24/05/2019 | 19/09/2019 | 0 | TK_Complete
10LAB60 | TT_Task | Line Inspection &amp; Preparation for Neutral Float Welds | 10/06/2019 | 21/06/2019 | 18/06/2019 | 27/07/2019 | 0 | TK_Complete
10LAB65 | TT_Task | Neural Float &amp; Final Weld Connections to FW Pump | 29/06/2019 | 11/07/2019 | 27/07/2019 | 21/09/2019 | 0 | TK_Complete
10LAB70 | TT_Task | Hydro Test | 30/09/2019 | 12/10/2019 | 02/10/2019 | 08/10/2019 | 0 | TK_Complete
10LAB80 | TT_Task | Insulation of Pipework Prior to Neutral Float | 07/06/2019 | 02/07/2019 | 14/06/2019 | 14/09/2019 | 0 | TK_Complete
10LAB90 | TT_Task | Pre-Commissioning/Flushing/Cleaning | 14/10/2019 | 24/10/2019 | 03/10/2019 | 14/11/2019 | 0 | TK_Complete
00LAB10 | TT_Task | Install Make-up Water/NOx Pumps &amp; Pressure System (Tank/Controls) | 21/01/2019 | 21/02/2019 | 15/01/2019 | 07/05/2019 | 0 | TK_Complete
00LAB20 | TT_Task | Install NOx Piping from Existing Demin Tank to GT NOx Control Pump including Recir Line | 24/04/2019 | 16/07/2019 | 24/04/2019 | 10/08/2019 | 0 | TK_Complete
00LAB30 | TT_Task | Install Make-up Water Piping from Existing Demin Tank to Connection Points of New CCGT | 30/04/2019 | 22/07/2019 | 15/05/2019 | 17/08/2019 | 0 | TK_Complete
00LAB40 | TT_Task | NDE | 22/06/2019 | 29/07/2019 | 14/05/2019 | 20/09/2019 | 0 | TK_Complete
00LAB50 | TT_Task | EC+I | 23/07/2019 | 06/09/2019 | 23/05/2019 | 19/09/2019 | 0 | TK_Complete
00LAB60 | TT_Task | Line Inspection | 20/07/2019 | 29/07/2019 | 11/07/2019 | 13/07/2019 | 0 | TK_Complete
00LAB70 | TT_Task | Hydro Test | 30/09/2019 | 09/10/2019 | 11/10/2019 | 19/10/2019 | 0 | TK_Complete
00LAB80 | TT_Task | Painting/Insulation | 13/08/2019 | 20/09/2019 | 10/08/2019 | 15/10/2019 | 0 | TK_Complete
00LAB90 | TT_Task | Pre-Commissioning/Flushing/Cleaning | 15/10/2019 | 23/10/2019 | 15/10/2019 | 04/11/2019 | 0 | TK_Complete
00EG-01-10 | TT_Task | Install Equipment/Skids/Pumps | 18/02/2019 | 06/03/2019 | 15/09/2018 | 25/09/2018 | 0 | TK_Complete
00EG-01-20 | TT_Task | Install Large Bore Pipe/Valves/Supports | 06/03/2019 | 03/05/2019 | 15/09/2018 | 27/07/2019 | 0 | TK_Complete
00EG-01-30 | TT_Task | Install Small Bore Pipe/Valves/Supports | 03/04/2019 | 03/05/2019 | 05/04/2019 | 27/07/2019 | 0 | TK_Complete
00EG-01-50 | TT_Task | EC+I | 10/06/2019 | 04/07/2019 | 10/05/2019 | 27/09/2019 | 0 | TK_Complete
00EG-01-60 | TT_Task | Line Inspection | 23/07/2019 | 05/08/2019 | 24/07/2019 | 10/08/2019 | 0 | TK_Complete
00EG-01-70 | TT_Task | Hydro Test | 07/08/2019 | 21/08/2019 | 10/08/2019 | 17/08/2019 | 0 | TK_Complete
00EG-01-80 | TT_Task | Painting/Insulation | 03/05/2019 | 15/06/2019 | 03/05/2019 | 28/09/2019 | 0 | TK_Complete
00EG-01-90 | TT_Task | Pre-Commissioning/Flushing/Cleaning | 16/09/2019 | 30/09/2019 | 28/09/2019 | 08/11/2019 | 0 | TK_Complete
00EG-02-10 | TT_Task | Install Equipment/Skids/Pumps | 15/02/2019 | 01/03/2019 | 15/09/2018 | 25/09/2018 | 0 | TK_Complete
00EG-02-20 | TT_Task | Install Large Bore Pipe/Valves/Supports | 16/11/2018 | 28/01/2019 | 01/09/2018 | 21/05/2019 | 0 | TK_Complete
00EG-02-30 | TT_Task | Install Small Bore Pipe/Valves/Supports | 10/06/2019 | 08/07/2019 | 10/05/2019 | 20/07/2019 | 0 | TK_Complete
00EG-02-40 | TT_Task | EC+I | 04/07/2019 | 17/07/2019 | 08/06/2019 | 28/09/2019 | 0 | TK_Complete
00EG-02-50 | TT_Task | Line Inspection | 02/07/2019 | 15/07/2019 | 20/07/2019 | 27/07/2019 | 0 | TK_Complete
00EG-02-60 | TT_Task | Hydro Test | 31/07/2019 | 14/08/2019 | 10/08/2019 | 17/08/2019 | 0 | TK_Complete
00EG-02-70 | TT_Task | Painting/Insulation | 04/07/2019 | 26/07/2019 | 04/06/2019 | 30/11/2019 | 0 | TK_Complete
00EG-02-80 | TT_Task | Pre-Commissioning/Flushing/Cleaning | 31/08/2019 | 13/09/2019 | 28/09/2019 | 30/11/2019 | 0 | TK_Complete
10EK10 | TT_Task | Install Equipment/Skids/Pumps | 31/05/2019 | 18/06/2019 | 10/06/2019 | 20/07/2019 | 0 | TK_Complete
10EK30 | TT_Task | Install Pipe/Valves/Supports (Inside+Outside) | 06/04/2019 | 13/05/2019 | 06/04/2019 | 24/08/2019 | 0 | TK_Complete
10EK40 | TT_Task | EC+I | 03/07/2019 | 25/07/2019 | 22/05/2019 | 25/09/2019 | 0 | TK_Complete
10EK50 | TT_Task | Line Inspection | 30/09/2019 | 18/10/2019 | 03/10/2019 | 18/10/2019 | 0 | TK_Complete
10EK60 | TT_Task | Hydro Test | 19/10/2019 | 30/10/2019 | 19/10/2019 | 21/10/2019 | 0 | TK_Complete
10EK70 | TT_Task | Painting/Insulation | 08/06/2019 | 04/07/2019 | 16/05/2019 | 10/12/2019 | 0 | TK_Complete
10EK80 | TT_Task | Pre-Commissioning/Flushing/Cleaning | 31/10/2019 | 11/11/2019 | 08/10/2019 | 10/12/2019 | 0 | TK_Complete
10EK90 | TT_Task | Install Fuel Gas Piping from Plant to Tie-in to Existing Line | 30/08/2018 | 17/10/2018 | 13/08/2018 | 06/05/2019 | 0 | TK_Complete
00EK09 | TT_Task | Erection of Blending Station | 30/04/2019 | 22/05/2019 | 25/05/2019 | 27/07/2019 | 0 | TK_Complete
00EK10 | TT_Task | Install Equipment/Skids/Pumps | 30/04/2019 | 05/06/2019 | 07/05/2019 | 20/07/2019 | 0 | TK_Complete
00EK20 | TT_Task | Install Large Bore Pipe/Valves/Supports | 03/04/2019 | 06/06/2019 | 01/03/2019 | 14/09/2019 | 0 | TK_Complete
00EK30 | TT_Task | Install Small Bore Pipe/Valves/Supports | 06/04/2019 | 16/05/2019 | 10/04/2019 | 14/09/2019 | 0 | TK_Complete
00EK35 | TT_Task | NDE | 08/05/2019 | 15/06/2019 | 08/05/2019 | 28/09/2019 | 0 | TK_Complete
00EK40 | TT_Task | EC+I | 23/05/2019 | 05/07/2019 | 23/05/2019 | 26/09/2019 | 0 | TK_Complete
00EK50 | TT_Task | Line Inspection | 02/09/2019 | 11/09/2019 | 28/09/2019 | 17/10/2019 | 0 | TK_Complete
00EK60 | TT_Task | Hydro Test | 10/10/2019 | 19/10/2019 | 21/10/2019 | 25/10/2019 | 0 | TK_Complete
00EK70 | TT_Task | Painting/Insulation | 26/07/2019 | 06/08/2019 | 15/06/2019 | 16/12/2019 | 0 | TK_Complete
00EK80 | TT_Task | Pre-Commissioning/Flushing/Cleaning | 19/10/2019 | 31/10/2019 | 07/10/2019 | 16/12/2019 | 0 | TK_Complete
10EKT20-10 | TT_Task | Install Equipment/Skids/Pumps | 30/04/2019 | 05/06/2019 | 08/05/2019 | 20/07/2019 | 0 | TK_Complete
10EKT20-20 | TT_Task | Install Large Bore Pipe/Valves/Supports | 30/04/2019 | 05/06/2019 | 06/05/2019 | 14/09/2019 | 0 | TK_Complete
10EKT20-30 | TT_Task | Install Small Bore Pipe/Valves/Supports | 13/05/2019 | 07/06/2019 | 13/05/2019 | 12/09/2019 | 0 | TK_Complete
10EKT20-40 | TT_Task | EC+I | 30/04/2019 | 05/06/2019 | 15/05/2019 | 27/09/2019 | 0 | TK_Complete
10EKT20-50 | TT_Task | Line Inspection | 09/09/2019 | 16/09/2019 | 28/09/2019 | 16/10/2019 | 0 | TK_Complete
10EKT20-60 | TT_Task | Hydro Test | 05/10/2019 | 15/10/2019 | 11/10/2019 | 16/10/2019 | 0 | TK_Complete
10EKT20-70 | TT_Task | Painting/Insulation | 25/06/2019 | 17/07/2019 | 14/06/2019 | 27/11/2019 | 0 | TK_Complete
10EKT20-80 | TT_Task | Pre-Commissioning/Flushing/Cleaning | 15/10/2019 | 23/10/2019 | 05/10/2019 | 27/11/2019 | 0 | TK_Complete
10EKT20-90 | TT_Task | NDE | 08/05/2019 | 13/06/2019 | 08/05/2019 | 02/10/2019 | 0 | TK_Complete
00PAA10 | TT_Task | Install Equipment - Skid | 22/06/2019 | 06/07/2019 | 18/05/2019 | 17/10/2019 | 0 | TK_Complete
00PAA11 | TT_Task | Installation of Bar Screen - Skid | 31/07/2019 | 22/08/2019 | 03/08/2019 | 15/10/2019 | 0 | TK_Complete
00PAA20 | TT_Task | Install Large Bore Pipe/Valves/Supports | 22/07/2019 | 09/08/2019 | 13/07/2019 | 19/10/2019 | 0 | TK_Complete
00PAA30 | TT_Task | Install Small Bore Pipe/Valves/Supports | 10/08/2019 | 29/08/2019 | 13/07/2019 | 23/10/2019 | 0 | TK_Complete
00PAA40 | TT_Task | NDE | 15/08/2019 | 31/08/2019 | 24/08/2019 | 26/10/2019 | 0 | TK_Complete
00PAA50 | TT_Task | EC+I | 02/09/2019 | 17/09/2019 | 24/08/2019 | 20/11/2019 | 0 | TK_Complete
00PAA60 | TT_Task | Line Inspection | 30/10/2019 | 04/11/2019 | 30/10/2019 | 04/11/2019 | 0 | TK_Complete
00PAA70 | TT_Task | Hydro Test | 05/11/2019 | 08/11/2019 | 05/11/2019 | 15/11/2019 | 0 | TK_Complete
00PAA80 | TT_Task | Painting/Insulation | 21/09/2019 | 30/09/2019 | 28/09/2019 | 10/12/2019 | 0 | TK_Complete
00PAA90 | TT_Task | Pre-Commissioning/Flushing/Cleaning | 30/11/2019 | 07/12/2019 | 30/11/2019 | 10/12/2019 | 0 | TK_Complete
10PAB-02-10 | TT_Task | Install Cooling Water Piperack (UPY00Y Module) | 01/04/2019 | 15/04/2019 | 01/04/2019 | 23/07/2019 | 0 | TK_Complete
10PAB-02-20 | TT_Task | Install Large Bore Pipe/Valves/Supports from Civil U/G TP to Condenser | 09/05/2019 | 06/06/2019 | 09/05/2019 | 04/11/2019 | 0 | TK_Complete
10PAB-02-30 | TT_Task | Install Small Bore Pipe/Valves/Supports from Civil U/G TP to Condenser | 01/04/2019 | 04/06/2019 | 09/04/2019 | 05/10/2019 | 0 | TK_Complete
10PAB-02-40 | TT_Task | NDE | 24/06/2019 | 02/07/2019 | 04/06/2019 | 05/10/2019 | 0 | TK_Complete
10PAB-02-50 | TT_Task | EC+I | 28/06/2019 | 30/07/2019 | 13/06/2019 | 05/11/2019 | 0 | TK_Complete
10PAB-02-60 | TT_Task | Line Inspection | 26/10/2019 | 31/10/2019 | 04/10/2019 | 22/10/2019 | 0 | TK_Complete
10PAB-02-70 | TT_Task | Hydro Test | 04/11/2019 | 13/11/2019 | 04/11/2019 | 23/11/2019 | 0 | TK_Complete
10PAB-02-80 | TT_Task | Painting/Insulation | 15/10/2019 | 29/10/2019 | 25/09/2019 | 16/12/2019 | 0 | TK_Complete
10PAB-02-90 | TT_Task | Pre-Commissioning/Flushing/Cleaning | 04/12/2019 | 10/12/2019 | 04/12/2019 | 16/12/2019 | 0 | TK_Complete
10PAB-01-10 | TT_Task | Install Circulating Water Pumps | 08/07/2019 | 22/07/2019 | 06/07/2019 | 14/09/2019 | 0 | TK_Complete
10PAB-01-110 | TT_Task | Prepare Circulating Water Pumps Foundations | 31/05/2019 | 14/06/2019 | 29/06/2019 | 19/07/2019 | 0 | TK_Complete
10PAB-01-20 | TT_Task | Install Large Bore Pipe/Valves/Supports from CW Pumps to U/G Piping Terminal Point | 11/07/2019 | 05/08/2019 | 13/07/2019 | 25/10/2019 | 0 | TK_Complete
10PAB-01-30 | TT_Task | Install Small Bore Pipe/Valves/Supports from CW Pump to U/G Piping Terminal Point | 15/07/2019 | 07/08/2019 | 13/07/2019 | 25/10/2019 | 0 | TK_Complete
10PAB-01-40 | TT_Task | NDE | 09/08/2019 | 20/08/2019 | 24/08/2019 | 25/10/2019 | 0 | TK_Complete
10PAB-01-50 | TT_Task | EC+I | 02/09/2019 | 03/10/2019 | 02/09/2019 | 23/11/2019 | 0 | TK_Complete
10PAB-01-60 | TT_Task | Line Inspection | 30/11/2019 | 04/12/2019 | 30/11/2019 | 01/12/2019 | 0 | TK_Complete
10PAB-01-70 | TT_Task | Hydro Test | 30/03/2020 | 02/04/2020 | 02/12/2019 | 06/12/2019 | 0 | TK_Complete
10PAB-01-80 | TT_Task | Painting/Insulation | 26/09/2019 | 05/10/2019 | 26/09/2019 | 12/12/2019 | 0 | TK_Complete
10PAB-01-90 | TT_Task | Pre-Commissioning/Flushing/Cleaning | 03/04/2020 | 08/04/2020 | 07/12/2019 | 12/12/2019 | 0 | TK_Complete
10PGB1010 | TT_Task | Install Closed Cooling/Service Water Pump Module (PXB00Y) | 30/04/2019 | 06/06/2019 | 03/05/2019 | 03/08/2019 | 0 | TK_Complete
10PGB1020 | TT_Task | Install Large Bore Pipe/Valves/Supports | 03/04/2019 | 27/06/2019 | 18/10/2018 | 02/09/2019 | 0 | TK_Complete
10PGB1030 | TT_Task | Install Small Bore Pipe/Valves/Supports | 16/04/2019 | 25/05/2019 | 08/03/2019 | 07/09/2019 | 0 | TK_Complete
10PGB1040 | TT_Task | NDE | 15/05/2019 | 06/07/2019 | 15/05/2019 | 14/09/2019 | 0 | TK_Complete
10PGB1050 | TT_Task | EC+I | 13/07/2019 | 12/08/2019 | 06/06/2019 | 26/09/2019 | 0 | TK_Complete
10PGB1060 | TT_Task | Line Inspection | 08/08/2019 | 16/08/2019 | 29/06/2019 | 13/07/2019 | 0 | TK_Complete
10PGB1070 | TT_Task | Hydro Test | 22/08/2019 | 30/08/2019 | 10/07/2019 | 13/07/2019 | 0 | TK_Complete
10PGB1080 | TT_Task | Painting/Insulation | 13/07/2019 | 06/08/2019 | 08/06/2019 | 17/10/2019 | 0 | TK_Complete
10PGB1090 | TT_Task | Pre-Commissioning/Flushing/Cleaning | 11/10/2019 | 18/10/2019 | 05/10/2019 | 10/10/2019 | 0 | TK_Complete
10PCB10 | TT_FinMile | Service Cooling Water Pumps Installed w/PXB00Y Module (See Activity 10PGB1010) | 02/09/2019 | 02/09/2019 | 04/09/2019 | 04/09/2019 | 0 | TK_Complete
10PCB20 | TT_Task | Install Large Bore Pipe/Valves/Supports | 26/07/2019 | 28/08/2019 | 12/07/2019 | 04/09/2019 | 0 | TK_Complete
10PCB30 | TT_Task | Install Small Bore Pipe/Valves/Supports | 24/07/2019 | 19/08/2019 | 11/07/2019 | 03/09/2019 | 0 | TK_Complete
10PCB40 | TT_Task | NDE | 06/08/2019 | 12/08/2019 | 10/08/2019 | 03/10/2019 | 0 | TK_Complete
10PCB50 | TT_Task | EC+I | 10/08/2019 | 20/08/2019 | 15/07/2019 | 25/09/2019 | 0 | TK_Complete
10PCB60 | TT_Task | Line Inspection | 30/09/2019 | 08/10/2019 | 10/10/2019 | 09/11/2019 | 0 | TK_Complete
10PCB70 | TT_Task | Hydro Test | 01/11/2019 | 08/11/2019 | 25/11/2019 | 29/11/2019 | 0 | TK_Complete
10PCB80 | TT_Task | Painting/Insulation | 20/08/2019 | 02/09/2019 | 24/08/2019 | 15/11/2019 | 0 | TK_Complete
10PCB90 | TT_Task | Pre-Commissioning/Flushing/Cleaning | 09/11/2019 | 15/11/2019 | 09/11/2019 | 15/11/2019 | 0 | TK_Complete
10PAH10 | TT_Task | Install Equipment/Skids/Pumps | 19/02/2019 | 25/02/2019 | 15/11/2018 | 20/11/2018 | 0 | TK_Complete
10PAH15 | TT_Task | Install Control Cabinet &amp; Junction Box for Tube Cleaning Systen | 31/05/2019 | 03/06/2019 | 25/06/2019 | 17/07/2019 | 0 | TK_Complete
10PAH20 | TT_Task | Install Large Bore Pipe/Valves/Supports | 06/04/2019 | 09/05/2019 | 06/04/2019 | 03/09/2019 | 0 | TK_Complete
10PAH30 | TT_Task | Install Small Bore Pipe/Valves/Supports | 26/04/2019 | 14/05/2019 | 26/04/2019 | 07/09/2019 | 0 | TK_Complete
10PAH40 | TT_Task | NDE | 23/05/2019 | 05/06/2019 | 23/05/2019 | 27/09/2019 | 0 | TK_Complete
10PAH50 | TT_Task | EC+I | 30/05/2019 | 29/06/2019 | 21/05/2019 | 26/09/2019 | 0 | TK_Complete
10PAH60 | TT_Task | Line Inspection | 04/09/2019 | 17/09/2019 | 28/09/2019 | 05/10/2019 | 0 | TK_Complete
10PAH70 | TT_Task | Hydro Test | 28/03/2020 | 02/04/2020 | 04/12/2019 | 09/12/2019 | 0 | TK_Complete
10PAH80 | TT_Task | Painting/Insulation | 23/09/2019 | 10/10/2019 | 23/09/2019 | 17/12/2019 | 0 | TK_Complete
10PAH90 | TT_Task | Pre-Commissioning/Flushing/Cleaning | 01/04/2020 | 08/04/2020 | 10/12/2019 | 17/12/2019 | 0 | TK_Complete
00PUN10 | TT_Task | Install Equipment/Skids/Pumps - Skid | 22/05/2019 | 01/06/2019 | 23/04/2019 | 10/09/2019 | 0 | TK_Complete
00PUN11 | TT_Task | Install Containers - Skid | 08/06/2019 | 13/06/2019 | 27/06/2019 | 21/09/2019 | 0 | TK_Complete
00PUN12 | TT_Task | Install Interconnection Lines to Process | 02/08/2019 | 07/08/2019 | 17/08/2019 | 30/11/2019 | 0 | TK_Complete
00PUN20 | TT_Task | Install Pipe/Valves/Supports - Skid | 08/06/2019 | 06/07/2019 | 14/06/2019 | 02/10/2019 | 0 | TK_Complete
00PUN40 | TT_Task | EC+I | 20/08/2019 | 29/08/2019 | 17/08/2019 | 30/11/2019 | 0 | TK_Complete
00PUN50 | TT_Task | Line Inspection | 30/10/2019 | 08/11/2019 | 30/10/2019 | 08/11/2019 | 0 | TK_Complete
00PUN60 | TT_Task | Hydro Test/Leak Test | 01/11/2019 | 11/11/2019 | 01/11/2019 | 11/11/2019 | 0 | TK_Complete
00PUN80 | TT_Task | Pre-Commissioning/Flushing/Cleaning | 11/11/2019 | 20/11/2019 | 11/11/2019 | 20/11/2019 | 0 | TK_Complete
00PUN90 | TT_Task | NDE | 16/07/2019 | 29/07/2019 | 16/07/2019 | 03/10/2019 | 0 | TK_Complete
10PUR10 | TT_Task | Anode Installation | 02/09/2019 | 11/09/2019 | 19/09/2019 | 04/10/2019 | 0 | TK_Complete
10PUR20 | TT_Task | Rectifier Installation | 07/09/2019 | 18/09/2019 | 21/09/2019 | 10/10/2019 | 0 | TK_Complete
10PUR30 | TT_Task | Junction Box Installion | 13/09/2019 | 24/09/2019 | 21/09/2019 | 05/10/2019 | 0 | TK_Complete
10PUR40 | TT_Task | Test Station | 20/09/2019 | 30/09/2019 | 20/09/2019 | 30/10/2019 | 0 | TK_Complete
10PUR50 | TT_Task | Cable Pulling/Termination | 02/10/2019 | 12/10/2019 | 20/09/2019 | 30/10/2019 | 0 | TK_Complete
10PUR60 | TT_Task | Precommissioning | 30/10/2019 | 09/11/2019 | 30/10/2019 | 09/11/2019 | 0 | TK_Complete
00UPR10 | TT_Task | Anode Installation | 02/09/2019 | 10/09/2019 | 20/09/2019 | 05/10/2019 | 0 | TK_Complete
00UPR20 | TT_Task | Rectifier Installation | 11/09/2019 | 21/09/2019 | 19/09/2019 | 11/10/2019 | 0 | TK_Complete
00UPR30 | TT_Task | Junction Box Installion | 23/09/2019 | 02/10/2019 | 19/09/2019 | 05/10/2019 | 0 | TK_Complete
00UPR40 | TT_Task | Test Station | 03/10/2019 | 12/10/2019 | 21/09/2019 | 30/10/2019 | 0 | TK_Complete
00UPR50 | TT_Task | Cable Pulling/Termination | 14/10/2019 | 22/10/2019 | 18/09/2019 | 30/10/2019 | 0 | TK_Complete
00UPR60 | TT_Task | Precommissioning | 30/10/2019 | 08/11/2019 | 30/10/2019 | 08/11/2019 | 0 | TK_Complete
00SCA10 | TT_Task | Install Equipment/Skids/Pumps | 15/03/2019 | 17/04/2019 | 15/03/2019 | 22/06/2019 | 0 | TK_Complete
00SCA20 | TT_Task | Install Large Bore Pipe/Valves/Supports | 01/04/2019 | 10/05/2019 | 03/04/2019 | 17/08/2019 | 0 | TK_Complete
00SCA30 | TT_Task | Install Small Bore Pipe/Valves/Supports | 13/04/2019 | 23/05/2019 | 13/04/2019 | 17/08/2019 | 0 | TK_Complete
00SCA40 | TT_Task | NDE | 29/05/2019 | 17/06/2019 | 07/05/2019 | 28/09/2019 | 0 | TK_Complete
00SCA50 | TT_Task | EC+I | 05/06/2019 | 28/06/2019 | 17/05/2019 | 26/09/2019 | 0 | TK_Complete
00SCA60 | TT_Task | Line Inspection | 01/08/2019 | 05/08/2019 | 28/08/2019 | 21/09/2019 | 0 | TK_Complete
00SCA70 | TT_Task | Hydro Test | 30/09/2019 | 03/10/2019 | 05/10/2019 | 09/10/2019 | 0 | TK_Complete
00SCA80 | TT_Task | Painting/Insulation | 24/06/2019 | 03/07/2019 | 03/06/2019 | 19/10/2019 | 0 | TK_Complete
00SCA90 | TT_Task | Pre-Commissioning/Flushing/Cleaning | 04/10/2019 | 08/10/2019 | 12/10/2019 | 30/10/2019 | 0 | TK_Complete
00SCB20 | TT_Task | Install Large Bore Pipe/Valves/Supports | 17/04/2019 | 10/06/2019 | 15/03/2019 | 19/09/2019 | 0 | TK_Complete
00SCB30 | TT_Task | Install Small Bore Pipe/Valves/Supports | 24/04/2019 | 06/06/2019 | 24/04/2019 | 19/09/2019 | 0 | TK_Complete
00SCB40 | TT_Task | NDE | 31/05/2019 | 08/06/2019 | 05/06/2019 | 28/09/2019 | 0 | TK_Complete
00SCB50 | TT_Task | EC+I | 30/04/2019 | 10/06/2019 | 08/05/2019 | 28/09/2019 | 0 | TK_Complete
00SCB60 | TT_Task | Line Inspection | 02/08/2019 | 10/08/2019 | 28/08/2019 | 18/09/2019 | 0 | TK_Complete
00SCB70 | TT_Task | Hydro Test | 30/09/2019 | 04/10/2019 | 05/10/2019 | 10/10/2019 | 0 | TK_Complete
00SCB80 | TT_Task | Painting | 21/06/2019 | 20/07/2019 | 03/06/2019 | 10/10/2019 | 0 | TK_Complete
00SCB90 | TT_Task | Pre-Commissioning/Flushing/Cleaning | 05/10/2019 | 11/10/2019 | 05/10/2019 | 11/10/2019 | 0 | TK_Complete
00SCA110 | TT_Task | Install Large Bore Pipe/Valves/Supports | 18/02/2019 | 14/05/2019 | 02/01/2019 | 21/09/2019 | 0 | TK_Complete
00SCA120 | TT_Task | Install Small Bore Pipe/Valves/Supports | 08/05/2019 | 14/06/2019 | 08/05/2019 | 20/09/2019 | 0 | TK_Complete
00SCA130 | TT_Task | NDE | 01/04/2019 | 17/06/2019 | 01/04/2019 | 28/09/2019 | 0 | TK_Complete
00SCA140 | TT_Task | EC+I | 29/06/2019 | 24/07/2019 | 03/06/2019 | 26/09/2019 | 0 | TK_Complete
00SCA150 | TT_Task | Line Inspection | 12/08/2019 | 20/08/2019 | 28/08/2019 | 19/09/2019 | 0 | TK_Complete
00SCA160 | TT_Task | Hydro Test | 30/09/2019 | 04/10/2019 | 11/10/2019 | 17/10/2019 | 0 | TK_Complete
00SCA170 | TT_Task | Painting/Insulation | 29/06/2019 | 24/07/2019 | 04/06/2019 | 15/11/2019 | 0 | TK_Complete
00SCA180 | TT_Task | Pre-Commissioning/Flushing/Cleaning | 05/10/2019 | 14/10/2019 | 12/10/2019 | 23/11/2019 | 0 | TK_Complete
GKB10 | TT_Task | Install Equipment/Skids/Pumps | 01/04/2019 | 15/04/2019 | 01/04/2019 | 24/08/2019 | 0 | TK_Complete
GKB20 | TT_Task | Install Large Bore Pipe/Valves/Supports | 15/04/2019 | 25/05/2019 | 15/04/2019 | 12/10/2019 | 0 | TK_Complete
GKB30 | TT_Task | Install Small Bore Pipe/Valves/Supports | 18/06/2019 | 08/07/2019 | 05/06/2019 | 09/10/2019 | 0 | TK_Complete
GKB40 | TT_Task | EC+I | 08/07/2019 | 19/07/2019 | 06/06/2019 | 08/10/2019 | 0 | TK_Complete
GKB50 | TT_Task | Line Inspection | 30/09/2019 | 09/10/2019 | 10/10/2019 | 07/11/2019 | 0 | TK_Complete
GKB60 | TT_Task | Hydro Test | 05/12/2019 | 17/12/2019 | 08/11/2019 | 19/11/2019 | 0 | TK_Complete
GKB70 | TT_Task | Painting/Insulation | 03/07/2019 | 20/07/2019 | 07/06/2019 | 19/11/2019 | 0 | TK_Complete
GKB80 | TT_Task | Pre-Commissioning/Flushing/Cleaning | 23/10/2019 | 29/10/2019 | 12/10/2019 | 30/11/2019 | 0 | TK_Complete
00GKB-02-10 | TT_Task | Install Equipment/Skids/Pumps | 01/04/2019 | 15/04/2019 | 01/04/2019 | 24/08/2019 | 0 | TK_Complete
00GKB-02-20 | TT_Task | Install Large Bore Pipe/Valves/Supports | 15/04/2019 | 25/05/2019 | 15/04/2019 | 08/10/2019 | 0 | TK_Complete
00GKB-02-30 | TT_Task | Install Small Bore Pipe/Valves/Supports | 24/06/2019 | 12/07/2019 | 01/06/2019 | 11/10/2019 | 0 | TK_Complete
00GKB-02-40 | TT_Task | EC+I | 05/06/2019 | 05/07/2019 | 07/06/2019 | 11/10/2019 | 0 | TK_Complete
00GKB-02-50 | TT_Task | Line Inspection | 30/09/2019 | 11/10/2019 | 08/10/2019 | 31/10/2019 | 0 | TK_Complete
00GKB-02-60 | TT_Task | Hydro Test | 06/12/2019 | 13/12/2019 | 01/11/2019 | 08/11/2019 | 0 | TK_Complete
00GKB-02-70 | TT_Task | Painting/Insulation | 06/07/2019 | 24/07/2019 | 14/06/2019 | 08/11/2019 | 0 | TK_Complete
00GKB-02-80 | TT_Task | Pre-Commissioning/Flushing/Cleaning | 10/12/2019 | 13/12/2019 | 20/11/2019 | 25/11/2019 | 0 | TK_Complete
00GHD-02-10 | TT_Task | Install Equipment/Skids/Pumps | 01/04/2019 | 12/04/2019 | 01/04/2019 | 17/08/2019 | 0 | TK_Complete
00GHD-02-20 | TT_Task | Install Large Bore Pipe/Valves/Supports (Inside+Outside) | 11/03/2019 | 30/04/2019 | 22/03/2019 | 08/10/2019 | 0 | TK_Complete
00GHD-02-30 | TT_Task | Install Small Bore Pipe/Valves/Supports (Inside+Outside) | 17/05/2019 | 11/06/2019 | 17/05/2019 | 11/10/2019 | 0 | TK_Complete
00GHD-02-40 | TT_Task | EC+I | 12/06/2019 | 08/07/2019 | 12/06/2019 | 11/10/2019 | 0 | TK_Complete
00GHD-02-50 | TT_Task | Line Inspection | 30/09/2019 | 04/10/2019 | 19/10/2019 | 30/10/2019 | 0 | TK_Complete
00GHD-02-60 | TT_Task | Hydro Test | 06/12/2019 | 10/12/2019 | 01/11/2019 | 08/11/2019 | 0 | TK_Complete
00GHD-02-70 | TT_Task | Painting/Insulation | 10/06/2019 | 05/07/2019 | 03/06/2019 | 08/11/2019 | 0 | TK_Complete
00GHD-02-80 | TT_Task | Pre-Commissioning/Flushing/Cleaning | 06/12/2019 | 10/12/2019 | 20/11/2019 | 25/11/2019 | 0 | TK_Complete
00GHD-02-90 | TT_Task | NDE | 24/05/2019 | 18/06/2019 | 24/05/2019 | 12/10/2019 | 0 | TK_Complete
00GHD-110 | TT_Task | Install Equipment/Skids/Pumps | 01/04/2019 | 12/04/2019 | 01/04/2019 | 24/08/2019 | 0 | TK_Complete
00GHD-120 | TT_Task | Install Large Bore Pipe/Valves/Supports | 26/02/2019 | 24/04/2019 | 22/02/2019 | 09/10/2019 | 0 | TK_Complete
00GHD-130 | TT_Task | Install Small Bore Pipe/Valves/Supports | 07/05/2019 | 12/06/2019 | 07/05/2019 | 11/10/2019 | 0 | TK_Complete
00GHD-140 | TT_Task | EC+I | 10/07/2019 | 22/07/2019 | 12/06/2019 | 11/10/2019 | 0 | TK_Complete
00GHD-150 | TT_Task | Line Inspection | 04/10/2019 | 10/10/2019 | 18/10/2019 | 22/10/2019 | 0 | TK_Complete
00GHD-160 | TT_Task | Hydro Test | 30/11/2019 | 03/12/2019 | 01/11/2019 | 08/11/2019 | 0 | TK_Complete
00GHD-170 | TT_Task | Painting/Insulation | 29/06/2019 | 24/07/2019 | 14/06/2019 | 08/11/2019 | 0 | TK_Complete
00GHD-180 | TT_Task | Pre-Commissioning/Flushing/Cleaning | 14/10/2019 | 18/10/2019 | 10/10/2019 | 25/11/2019 | 0 | TK_Complete
00GHD-190 | TT_Task | NDE | 30/04/2019 | 12/06/2019 | 22/05/2019 | 12/10/2019 | 0 | TK_Complete
00GHC-02-20 | TT_Task | Install Large Bore Pipe/Valves/Supports | 21/02/2019 | 06/04/2019 | 31/10/2018 | 07/06/2019 | 0 | TK_Complete
00GHC-02-30 | TT_Task | Install Small Bore Pipe/Valves/Supports | 17/06/2019 | 24/06/2019 | 08/05/2019 | 08/06/2019 | 0 | TK_Complete
00GHC-02-40 | TT_Task | EC+I | 22/06/2019 | 23/07/2019 | 15/05/2019 | 21/09/2019 | 0 | TK_Complete
00GHC-02-50 | TT_Task | Line Inspection | 31/05/2019 | 11/06/2019 | 01/06/2019 | 17/06/2019 | 0 | TK_Complete
00GHC-02-60 | TT_Task | Hydro Test | 20/06/2019 | 25/06/2019 | 22/06/2019 | 05/07/2019 | 0 | TK_Complete
00GHC-02-70 | TT_Task | Painting/Insulation | 24/06/2019 | 12/07/2019 | 16/05/2019 | 24/08/2019 | 0 | TK_Complete
00GHC-02-80 | TT_Task | Pre-Commissioning/Flushing/Cleaning | 02/09/2019 | 06/09/2019 | 02/09/2019 | 12/10/2019 | 0 | TK_Complete
00GHC-01-10 | TT_Task | Install Equipment/Skids/Pumps | 01/04/2019 | 10/05/2019 | 17/02/2019 | 28/02/2019 | 0 | TK_Complete
00GHC-01-20 | TT_Task | Install Large Bore Pipe/Valves/Supports | 01/04/2019 | 10/05/2019 | 16/02/2019 | 15/05/2019 | 0 | TK_Complete
00GHC-01-30 | TT_Task | Install Small Bore Pipe/Valves/Supports | 08/04/2019 | 23/04/2019 | 08/04/2019 | 08/05/2019 | 0 | TK_Complete
00GHC-01-40 | TT_Task | EC+I | 15/05/2019 | 08/06/2019 | 15/05/2019 | 19/09/2019 | 0 | TK_Complete
00GHC-01-50 | TT_Task | Line Inspection | 08/05/2019 | 13/05/2019 | 08/05/2019 | 13/05/2019 | 0 | TK_Complete
00GHC-01-60 | TT_Task | Hydro Test | 13/05/2019 | 17/05/2019 | 13/05/2019 | 23/05/2019 | 0 | TK_Complete
00GHC-01-70 | TT_Task | Painting/Insulation | 15/05/2019 | 01/06/2019 | 15/05/2019 | 24/08/2019 | 0 | TK_Complete
00GHC-01-80 | TT_Task | Pre-Commissioning/Flushing/Cleaning | 31/08/2019 | 04/09/2019 | 07/09/2019 | 12/10/2019 | 0 | TK_Complete
10GHC10 | TT_Task | Install Equipment/Skids/Pumps | 01/04/2019 | 12/04/2019 | 01/04/2019 | 10/06/2019 | 0 | TK_Complete
10GHC20 | TT_Task | Install Large Bore Pipe/Valves/Supports | 22/02/2019 | 29/03/2019 | 31/10/2018 | 30/04/2019 | 0 | TK_Complete
10GHC30 | TT_Task | Install Small Bore Pipe/Valves/Supports | 27/04/2019 | 07/06/2019 | 27/04/2019 | 15/06/2019 | 0 | TK_Complete
10GHC40 | TT_Task | EC+I | 05/06/2019 | 22/06/2019 | 07/06/2019 | 20/09/2019 | 0 | TK_Complete
10GHC50 | TT_Task | Line Inspection | 13/06/2019 | 25/06/2019 | 22/06/2019 | 10/07/2019 | 0 | TK_Complete
10GHC60 | TT_Task | Hydro Test | 11/07/2019 | 22/07/2019 | 24/07/2019 | 10/08/2019 | 0 | TK_Complete
10GHC70 | TT_Task | Painting/Insulation | 13/06/2019 | 02/07/2019 | 13/06/2019 | 24/08/2019 | 0 | TK_Complete
10GHC80 | TT_Task | Pre-Commissioning/Flushing/Cleaning | 12/08/2019 | 21/08/2019 | 17/08/2019 | 28/09/2019 | 0 | TK_Complete
10QU20 | TT_Task | Install Containers | 01/04/2019 | 08/04/2019 | 01/04/2019 | 12/09/2019 | 0 | TK_Complete
10QU30 | TT_Task | Install Interconnecting Lines To Process | 09/04/2019 | 27/06/2019 | 09/04/2019 | 11/10/2019 | 0 | TK_Complete
10QU40 | TT_Task | Hydro/Leak Test | 13/09/2019 | 10/10/2019 | 28/09/2019 | 08/10/2019 | 0 | TK_Complete
10QU50 | TT_Task | EC+I | 08/07/2019 | 07/08/2019 | 04/06/2019 | 10/10/2019 | 0 | TK_Complete
10QU60 | TT_Task | Precommissioning | 21/10/2019 | 07/11/2019 | 18/10/2019 | 19/01/2020 | 0 | TK_Complete
10QCD20 | TT_Task | Install Containers | 13/02/2019 | 20/02/2019 | 26/02/2019 | 03/05/2019 | 0 | TK_Complete
10QCD30 | TT_Task | Install Interconnecting Lines To Process | 07/06/2019 | 09/07/2019 | 01/06/2019 | 09/10/2019 | 0 | TK_Complete
10QCD40 | TT_Task | Hydro/Leak Test | 05/09/2019 | 30/09/2019 | 28/09/2019 | 10/10/2019 | 0 | TK_Complete
10QCD50 | TT_Task | EC+I | 09/07/2019 | 01/08/2019 | 08/06/2019 | 08/10/2019 | 0 | TK_Complete
10QCD60 | TT_Task | Precommissioning | 05/10/2019 | 26/10/2019 | 19/10/2019 | 02/12/2019 | 0 | TK_Complete
10QCC20 | TT_Task | Install Containers | 11/03/2019 | 16/03/2019 | 26/03/2019 | 03/05/2019 | 0 | TK_Complete
10QCC30 | TT_Task | Install Interconnecting Lines To Process | 20/06/2019 | 20/07/2019 | 10/05/2019 | 11/10/2019 | 0 | TK_Complete
10QCC40 | TT_Task | Hydro/Leak Test | 05/09/2019 | 30/09/2019 | 28/09/2019 | 10/10/2019 | 0 | TK_Complete
10QCC50 | TT_Task | EC+I | 27/06/2019 | 26/07/2019 | 22/06/2019 | 11/10/2019 | 0 | TK_Complete
10QCC60 | TT_Task | Precommissioning | 11/10/2019 | 04/11/2019 | 18/10/2019 | 02/12/2019 | 0 | TK_Complete
10QCB20 | TT_Task | Install Containers | 01/04/2019 | 18/04/2019 | 26/03/2019 | 07/10/2019 | 0 | TK_Complete
10QCB30 | TT_Task | Install Interconnecting Lines To Process | 31/05/2019 | 23/07/2019 | 01/06/2019 | 10/10/2019 | 0 | TK_Complete
10QCB40 | TT_Task | Hydro/Leak Test | 11/09/2019 | 24/09/2019 | 28/09/2019 | 12/10/2019 | 0 | TK_Complete
10QCB50 | TT_Task | EC+I | 30/04/2019 | 08/06/2019 | 09/05/2019 | 11/10/2019 | 0 | TK_Complete
10QCB60 | TT_Task | Precommissioning | 04/10/2019 | 21/10/2019 | 19/10/2019 | 26/11/2019 | 0 | TK_Complete
00STG20 | TT_Task | Install Containers | 11/03/2019 | 16/03/2019 | 30/04/2019 | 24/05/2019 | 0 | TK_Complete
00STG30 | TT_Task | Install Interconnecting Lines To Process | 31/05/2019 | 06/07/2019 | 03/06/2019 | 08/10/2019 | 0 | TK_Complete
00STG40 | TT_Task | Hydro/Leak Test | 10/09/2019 | 16/09/2019 | 28/09/2019 | 12/10/2019 | 0 | TK_Complete
00STG50 | TT_Task | EC+I | 08/07/2019 | 13/08/2019 | 04/06/2019 | 10/10/2019 | 0 | TK_Complete
00STG60 | TT_Task | Precommissioning | 03/10/2019 | 22/10/2019 | 17/10/2019 | 10/12/2019 | 0 | TK_Complete
PMS14.1020 | TT_Task | Installation Aux. System Pipe Racks (UMCM1Y Modules) | 06/11/2018 | 07/12/2018 | 18/10/2018 | 20/11/2018 | 0 | TK_Complete
PMS14.1050 | TT_Task | Installation Water System Pipe Racks (UMCL1Y Modules) | 12/02/2019 | 22/02/2019 | 21/01/2019 | 11/05/2019 | 0 | TK_Complete
10LBA80-20 | TT_Task | Install Large Bore Pipe/Valves/Supports | 11/03/2019 | 30/04/2019 | 11/03/2019 | 03/08/2019 | 0 | TK_Complete
10LBA80-30 | TT_Task | Install Small Bore Pipe/Valves/Supports | 16/04/2019 | 03/06/2019 | 16/04/2019 | 03/08/2019 | 0 | TK_Complete
10LBA80-40 | TT_Task | NDE | 16/04/2019 | 08/06/2019 | 16/04/2019 | 27/09/2019 | 0 | TK_Complete
10LBA80-50 | TT_Task | EC+I | 20/05/2019 | 18/06/2019 | 20/05/2019 | 26/09/2019 | 0 | TK_Complete
10LBA80-60 | TT_Task | Line Inspection | 04/09/2019 | 17/09/2019 | 28/09/2019 | 21/10/2019 | 0 | TK_Complete
10LBA80-70 | TT_Task | Hydro Test | 22/10/2019 | 26/10/2019 | 22/10/2019 | 25/10/2019 | 0 | TK_Complete
10LBA80-80 | TT_Task | Painting/Insulation of Pipework | 20/05/2019 | 25/06/2019 | 20/05/2019 | 04/11/2019 | 0 | TK_Complete
10LBA80-90 | TT_Task | Pre-Commissioning/Flushing/Cleaning | 17/10/2019 | 22/10/2019 | 26/10/2019 | 04/11/2019 | 0 | TK_Complete
10LBA10-20 | TT_Task | Install Large Bore Pipe/Valves/Supports | 28/02/2019 | 09/05/2019 | 11/03/2019 | 05/09/2019 | 0 | TK_Complete
10LBA10-30 | TT_Task | Install Small Bore Pipe/Valves/Supports | 09/05/2019 | 17/06/2019 | 09/05/2019 | 03/09/2019 | 0 | TK_Complete
10LBA10-40 | TT_Task | NDE | 04/04/2019 | 10/06/2019 | 04/04/2019 | 26/09/2019 | 0 | TK_Complete
10LBA10-50 | TT_Task | EC+I | 27/05/2019 | 02/07/2019 | 14/05/2019 | 24/09/2019 | 0 | TK_Complete
10LBA10-55 | TT_Task | Insulation of Pipework Prior to Neutral Float | 17/06/2019 | 11/07/2019 | 17/06/2019 | 25/09/2019 | 0 | TK_Complete
10LBA10-60 | TT_Task | Line Inspection &amp; Preparation for Neutral Float | 01/08/2019 | 13/08/2019 | 10/08/2019 | 26/08/2019 | 0 | TK_Complete
10LBA10-65 | TT_Task | Neutral Float of LBA and FInal Weld to Turbine Stop Valve | 26/07/2019 | 07/08/2019 | 17/07/2019 | 28/09/2019 | 0 | TK_Complete
10LBA10-70 | TT_Task | Hydro Test | 30/09/2019 | 04/10/2019 | 23/10/2019 | 26/10/2019 | 0 | TK_Complete
10LBA10-80 | TT_Task | Insulation of Neutral Float Weld | 05/10/2019 | 11/10/2019 | 05/10/2019 | 30/10/2019 | 0 | TK_Complete
10LBA10-90 | TT_Task | Pre-Commissioning/Flushing/Cleaning | 12/10/2019 | 17/10/2019 | 26/10/2019 | 05/11/2019 | 0 | TK_Complete
10LBB20 | TT_Task | Install Large Bore Pipe/Valves/Supports | 11/03/2019 | 07/05/2019 | 11/03/2019 | 07/09/2019 | 0 | TK_Complete
10LBB30 | TT_Task | Install Small Bore Pipe/Valves/Supports | 08/05/2019 | 15/06/2019 | 08/05/2019 | 07/09/2019 | 0 | TK_Complete
10LBB40 | TT_Task | NDE | 09/05/2019 | 15/06/2019 | 09/05/2019 | 26/09/2019 | 0 | TK_Complete
10LBB50 | TT_Task | EC+I | 25/05/2019 | 12/07/2019 | 25/05/2019 | 28/09/2019 | 0 | TK_Complete
10LBB55 | TT_Task | Insulation of Pipework Prior to Neutral Float | 20/06/2019 | 03/07/2019 | 20/06/2019 | 28/09/2019 | 0 | TK_Complete
10LBB60 | TT_Task | Line Inspection &amp; Preparation for Neutral Float | 03/08/2019 | 15/08/2019 | 03/08/2019 | 28/08/2019 | 0 | TK_Complete
10LBB65 | TT_Task | Neutral Float of LBB and FInal Weld to Turbine Stop Valve | 19/07/2019 | 01/08/2019 | 18/07/2019 | 05/10/2019 | 0 | TK_Complete
10LBB70 | TT_Task | Hydro Test | 30/09/2019 | 16/10/2019 | 24/09/2019 | 25/10/2019 | 0 | TK_Complete
10LBB80 | TT_Task | Insulation of Neutral Float Weld | 30/09/2019 | 12/10/2019 | 04/10/2019 | 02/11/2019 | 0 | TK_Complete
10LBB90 | TT_Task | Pre-Commissioning/Flushing/Cleaning | 16/10/2019 | 30/10/2019 | 26/10/2019 | 15/11/2019 | 0 | TK_Complete
10LBC20 | TT_Task | Install Large Bore Pipe/Valves/Supports | 18/02/2019 | 27/04/2019 | 14/01/2019 | 05/09/2019 | 0 | TK_Complete
10LBC30 | TT_Task | Install Small Bore Pipe/Valves/Supports | 30/04/2019 | 10/06/2019 | 15/05/2019 | 07/09/2019 | 0 | TK_Complete
10LBC40 | TT_Task | NDE | 03/05/2019 | 10/06/2019 | 03/05/2019 | 25/09/2019 | 0 | TK_Complete
10LBC50 | TT_Task | EC+I | 18/05/2019 | 22/06/2019 | 18/05/2019 | 25/09/2019 | 0 | TK_Complete
10LBC55 | TT_Task | Insulation of Pipework Prior to Neutral Float | 17/06/2019 | 28/06/2019 | 17/06/2019 | 28/09/2019 | 0 | TK_Complete
10LBC60 | TT_Task | Line Inspection &amp; Preparation for Neutral Float | 05/08/2019 | 09/08/2019 | 03/08/2019 | 28/08/2019 | 0 | TK_Complete
10LBC65 | TT_Task | Neutral Float of LBC and FInal Weld to Turbine Stop Valve | 09/08/2019 | 15/08/2019 | 24/08/2019 | 28/08/2019 | 0 | TK_Complete
10LBC70 | TT_Task | Hydro Test | 30/09/2019 | 04/10/2019 | 18/10/2019 | 25/10/2019 | 0 | TK_Complete
10LBC80 | TT_Task | Insulation of Neutral Float Weld | 05/10/2019 | 11/10/2019 | 05/10/2019 | 31/10/2019 | 0 | TK_Complete
10LBC90 | TT_Task | Pre-Commissioning/Flushing/Cleaning | 05/10/2019 | 11/10/2019 | 26/10/2019 | 04/11/2019 | 0 | TK_Complete
10LBG20 | TT_Task | Install Large Bore Pipe/Valves/Supports | 01/04/2019 | 04/05/2019 | 04/04/2019 | 25/07/2019 | 0 | TK_Complete
10LBG30 | TT_Task | Install Small Bore Pipe/Valves/Supports | 24/05/2019 | 19/06/2019 | 24/05/2019 | 26/07/2019 | 0 | TK_Complete
10LBG40 | TT_Task | NDE | 08/06/2019 | 26/06/2019 | 09/05/2019 | 20/09/2019 | 0 | TK_Complete
10LBG50 | TT_Task | EC+I | 24/05/2019 | 21/06/2019 | 24/05/2019 | 26/09/2019 | 0 | TK_Complete
10LBG60 | TT_Task | Line Inspection | 31/07/2019 | 10/08/2019 | 10/08/2019 | 31/08/2019 | 0 | TK_Complete
10LBG70 | TT_Task | Hydro Test | 30/09/2019 | 12/10/2019 | 07/10/2019 | 10/10/2019 | 0 | TK_Complete
10LBG80 | TT_Task | Insulation | 24/06/2019 | 12/07/2019 | 14/06/2019 | 08/11/2019 | 0 | TK_Complete
10LBG90 | TT_Task | Pre-Commissioning/Flushing/Cleaning | 14/10/2019 | 24/10/2019 | 12/10/2019 | 08/11/2019 | 0 | TK_Complete
00LBG10 | TT_Task | Install Equipment/Skids/Pumps | 01/04/2019 | 04/04/2019 | 08/04/2019 | 11/06/2019 | 0 | TK_Complete
00LBG20 | TT_Task | Install Large Bore Pipe/Valves/Supports | 15/04/2019 | 12/06/2019 | 15/04/2019 | 07/09/2019 | 0 | TK_Complete
00LBG30 | TT_Task | Install Small Bore Pipe/Valves/Supports | 31/05/2019 | 29/06/2019 | 15/05/2019 | 07/09/2019 | 0 | TK_Complete
00LBG40 | TT_Task | NDE | 22/06/2019 | 11/07/2019 | 08/06/2019 | 21/09/2019 | 0 | TK_Complete
00LBG50 | TT_Task | EC+I | 18/06/2019 | 18/07/2019 | 17/05/2019 | 26/09/2019 | 0 | TK_Complete
00LBG60 | TT_Task | Line Inspection | 31/07/2019 | 10/08/2019 | 10/08/2019 | 02/09/2019 | 0 | TK_Complete
00LBG70 | TT_Task | Hydro Test | 30/09/2019 | 12/10/2019 | 07/10/2019 | 11/10/2019 | 0 | TK_Complete
00LBG80 | TT_Task | Insulation | 09/07/2019 | 01/08/2019 | 15/06/2019 | 06/11/2019 | 0 | TK_Complete
00LBG90 | TT_Task | Pre-Commissioning/Flushing/Cleaning | 14/10/2019 | 25/10/2019 | 12/10/2019 | 06/11/2019 | 0 | TK_Complete
10GM-02-10 | TT_Task | Install Equipment/Skids/Pumps | 01/04/2019 | 15/04/2019 | 10/04/2019 | 17/07/2019 | 0 | TK_Complete
10GM-02-20 | TT_Task | Erection of Oil Separator Pumps GM - Skid | 07/06/2019 | 17/06/2019 | 07/06/2019 | 20/07/2019 | 0 | TK_Complete
10GM-02-30 | TT_Task | Install Large Bore Pipe/Valves/Supports | 15/04/2019 | 25/05/2019 | 15/04/2019 | 03/08/2019 | 0 | TK_Complete
10GM-02-40 | TT_Task | Install Small Bore Pipe/Valves/Supports | 30/04/2019 | 24/05/2019 | 08/05/2019 | 03/08/2019 | 0 | TK_Complete
10GM-02-50 | TT_Task | E&amp;IC of Oil Separator Pumps GM | 25/05/2019 | 13/06/2019 | 25/05/2019 | 07/08/2019 | 0 | TK_Complete
10GM-02-60 | TT_Task | Line Inspection | 01/08/2019 | 06/08/2019 | 24/08/2019 | 03/09/2019 | 0 | TK_Complete
10GM-02-70 | TT_Task | Hydro Test | 03/09/2019 | 10/09/2019 | 25/09/2019 | 05/10/2019 | 0 | TK_Complete
10GM-02-80 | TT_Task | Painting/Insulation | 25/05/2019 | 04/06/2019 | 15/05/2019 | 31/10/2019 | 0 | TK_Complete
10GM-02-90 | TT_Task | Pre-Commissioning/Flushing/Cleaning | 31/10/2019 | 07/11/2019 | 10/10/2019 | 04/11/2019 | 0 | TK_Complete
00GM-03-10 | TT_Task | Install Equipment/Skids/Pumps | 17/04/2019 | 02/05/2019 | 19/04/2019 | 10/07/2019 | 0 | TK_Complete
00GM-03-20 | TT_Task | Install Large Bore Pipe/Valves/Supports | 14/05/2019 | 07/06/2019 | 14/05/2019 | 23/07/2019 | 0 | TK_Complete
00GM-03-30 | TT_Task | Install Small Bore Pipe/Valves/Supports | 07/06/2019 | 19/06/2019 | 21/05/2019 | 25/07/2019 | 0 | TK_Complete
00GM-03-40 | TT_Task | EC+I | 14/05/2019 | 01/06/2019 | 14/05/2019 | 21/09/2019 | 0 | TK_Complete
00GM-03-50 | TT_Task | Line Inspection | 31/07/2019 | 07/08/2019 | 10/07/2019 | 24/08/2019 | 0 | TK_Complete
00GM-03-60 | TT_Task | Hydro Test | 02/09/2019 | 12/09/2019 | 28/09/2019 | 05/10/2019 | 0 | TK_Complete
00GM-03-70 | TT_Task | Painting/Insulation | 08/06/2019 | 20/06/2019 | 21/05/2019 | 26/03/2020 | 0 | TK_Complete
00GM-03-80 | TT_Task | Pre-Commissioning/Flushing/Cleaning | 05/10/2019 | 15/10/2019 | 12/10/2019 | 26/03/2020 | 0 | TK_Complete
00GM-03-90 | TT_FinMile | Assumption Underground System Available | 21/12/2019 | 21/12/2019 | 22/11/2019 | 22/11/2019 | 0 | TK_Complete
00GM-02-10 | TT_Task | Install Equipment/Skids/Pumps | 15/04/2019 | 11/05/2019 | 15/04/2019 | 09/07/2019 | 0 | TK_Complete
00GM-02-20 | TT_Task | Install Large Bore Pipe/Valves/Supports | 30/04/2019 | 24/05/2019 | 09/05/2019 | 23/07/2019 | 0 | TK_Complete
00GM-02-30 | TT_Task | Install Small Bore Pipe/Valves/Supports | 14/05/2019 | 05/06/2019 | 14/05/2019 | 24/07/2019 | 0 | TK_Complete
00GM-02-40 | TT_Task | EC+I | 24/05/2019 | 17/06/2019 | 24/05/2019 | 21/09/2019 | 0 | TK_Complete
00GM-02-50 | TT_Task | Line Inspection | 02/08/2019 | 06/08/2019 | 10/08/2019 | 17/08/2019 | 0 | TK_Complete
00GM-02-60 | TT_Task | Hydro Test | 31/08/2019 | 09/09/2019 | 28/09/2019 | 04/10/2019 | 0 | TK_Complete
00GM-02-70 | TT_Task | Painting/Insulation | 13/05/2019 | 11/06/2019 | 13/05/2019 | 05/11/2019 | 0 | TK_Complete
00GM-02-80 | TT_Task | Pre-Commissioning/Flushing/Cleaning | 04/10/2019 | 14/10/2019 | 09/10/2019 | 05/11/2019 | 0 | TK_Complete
00GM-01-100 | TT_Task | Install Effluent Transfer Pump Station incl Canopy | 17/06/2019 | 27/06/2019 | 14/06/2019 | 11/07/2019 | 0 | TK_Complete
00GM-01-120 | TT_Task | Install Large Bore Pipe/Valves on Sleepers | 07/06/2019 | 03/07/2019 | 19/06/2019 | 08/07/2019 | 0 | TK_Complete
00GM-01-130 | TT_Task | Install Small Bore Pipe/Valves on Sleepers | 20/06/2019 | 15/07/2019 | 05/06/2019 | 10/07/2019 | 0 | TK_Complete
00GM-01-140 | TT_Task | EC+I | 12/06/2019 | 02/07/2019 | 21/05/2019 | 12/07/2019 | 0 | TK_Complete
00GM-01-150 | TT_Task | Line Inspection | 31/07/2019 | 08/08/2019 | 17/08/2019 | 07/09/2019 | 0 | TK_Complete
00GM-01-160 | TT_Task | Hydro Test | 31/08/2019 | 06/09/2019 | 28/09/2019 | 03/10/2019 | 0 | TK_Complete
00GM-01-170 | TT_Task | Painting/Insulation | 15/06/2019 | 05/07/2019 | 20/05/2019 | 11/07/2019 | 0 | TK_Complete
00GM-01-180 | TT_Task | Pre-Commissioning/Flushing/Cleaning | 03/10/2019 | 12/10/2019 | 09/10/2019 | 10/02/2020 | 0 | TK_Complete
00GM-01-190 | TT_Task | Install Effluent Tanks incl Stairs/Platforms - Skid | 30/04/2019 | 18/05/2019 | 13/05/2019 | 26/06/2019 | 0 | TK_Complete
00GM-01-200 | TT_Task | Install Effluent Treatment Dispossal to Existing Station | 30/10/2019 | 09/12/2019 | 14/10/2019 | 23/11/2019 | 0 | TK_Complete
00GM-01-210 | TT_Task | Install Sump Pumps | 01/04/2019 | 23/05/2019 | 01/04/2019 | 28/06/2019 | 0 | TK_Complete
00GM-01-220 | TT_Task | Install Piping Support Steelwork at Effluent Plant | 13/04/2019 | 25/04/2019 | 13/04/2019 | 10/07/2019 | 0 | TK_Complete
00GM-01-240 | TT_Task | Install Effluent Chemical (Caustic/Sulfuric Acid) Equipment | 30/04/2019 | 17/05/2019 | 20/05/2019 | 27/06/2019 | 0 | TK_Complete
00GM-01-250 | TT_Task | Install Large Bore Pipe/Valves - Remaining Sections to Pumps &amp; U/G TP | 25/05/2019 | 19/06/2019 | 25/05/2019 | 27/06/2019 | 0 | TK_Complete
00GM-01-260 | TT_Task | Install Small Bore Pipe/Valves - Remaining Sections to Pumps &amp; U/G TP | 25/05/2019 | 19/06/2019 | 25/05/2019 | 12/07/2019 | 0 | TK_Complete
10GM-01-10 | TT_Task | Install Equipment/Skids/Pumps | 15/04/2019 | 06/05/2019 | 15/04/2019 | 17/07/2019 | 0 | TK_Complete
10GM-01-20 | TT_Task | Install Large Bore Pipe/Valves/Supports | 02/04/2019 | 06/05/2019 | 02/04/2019 | 24/07/2019 | 0 | TK_Complete
10GM-01-30 | TT_Task | Install Small Bore Pipe/Valves/Supports | 27/05/2019 | 05/06/2019 | 16/05/2019 | 23/07/2019 | 0 | TK_Complete
10GM-01-50 | TT_Task | Line Inspection | 31/07/2019 | 07/08/2019 | 10/08/2019 | 02/09/2019 | 0 | TK_Complete
10GM-01-60 | TT_Task | Hydro Test | 02/09/2019 | 10/09/2019 | 28/09/2019 | 04/10/2019 | 0 | TK_Complete
10GM-01-80 | TT_Task | Pre-Commissioning/Flushing/Cleaning | 04/10/2019 | 10/10/2019 | 08/10/2019 | 31/10/2019 | 0 | TK_Complete
10GM-01-90 | TT_FinMile | Assumption Underground System Available | 28/03/2020 | 28/03/2020 | 21/11/2019 | 21/11/2019 | 0 | TK_Complete
10GM-02-100 | TT_Task | Install Equipment/Skids/Pumps | 15/04/2019 | 06/05/2019 | 17/04/2019 | 09/07/2019 | 0 | TK_Complete
10GM-02-110 | TT_Task | Install Large Bore Pipe/Valves/Supports | 30/04/2019 | 23/05/2019 | 15/05/2019 | 03/08/2019 | 0 | TK_Complete
10GM-02-120 | TT_Task | Install Small Bore Pipe/Valves/Supports | 13/05/2019 | 21/05/2019 | 13/05/2019 | 03/08/2019 | 0 | TK_Complete
10GM-02-130 | TT_Task | EC+I | 21/05/2019 | 04/06/2019 | 21/05/2019 | 27/09/2019 | 0 | TK_Complete
10GM-02-140 | TT_Task | Line Inspection | 31/07/2019 | 08/08/2019 | 10/08/2019 | 07/09/2019 | 0 | TK_Complete
10GM-02-150 | TT_Task | Hydro Test | 31/08/2019 | 09/09/2019 | 28/09/2019 | 05/10/2019 | 0 | TK_Complete
10GM-02-160 | TT_Task | Painting/Insulation | 04/07/2019 | 12/07/2019 | 25/07/2019 | 18/12/2019 | 0 | TK_Complete
10GM-02-170 | TT_Task | Pre-Commissioning/Flushing/Cleaning | 04/10/2019 | 14/10/2019 | 09/10/2019 | 18/12/2019 | 0 | TK_Complete
00GA10 | TT_Task | Install Equipment/Skids/Pumps | 16/04/2019 | 30/04/2019 | 18/04/2019 | 10/07/2019 | 0 | TK_Complete
00GA20 | TT_Task | Install Large Bore Pipe/Valves/Supports | 30/04/2019 | 21/05/2019 | 14/05/2019 | 03/08/2019 | 0 | TK_Complete
00GA30 | TT_Task | Install Small Bore Pipe/Valves/Supports | 10/05/2019 | 31/05/2019 | 10/05/2019 | 03/08/2019 | 0 | TK_Complete
00GA40 | TT_Task | EC+I | 22/05/2019 | 01/06/2019 | 22/05/2019 | 27/09/2019 | 0 | TK_Complete
00GA60 | TT_Task | Hydro Test | 28/03/2020 | 02/04/2020 | 04/08/2019 | 09/08/2019 | 0 | TK_Complete
00GA70 | TT_Task | Painting/Insulation | 22/05/2019 | 01/06/2019 | 22/05/2019 | 03/10/2019 | 0 | TK_Complete
00GA80 | TT_Task | Pre-Commissioning/Flushing/Cleaning | 03/04/2020 | 08/04/2020 | 10/08/2019 | 15/08/2019 | 0 | TK_Complete
00MBH20 | TT_Task | Install Large Bore Pipe/Valves/Supports | 01/04/2019 | 27/04/2019 | 01/04/2019 | 03/09/2019 | 0 | TK_Complete
00MBH30 | TT_Task | Install Small Bore Pipe/Valves/Supports | 13/04/2019 | 07/05/2019 | 13/04/2019 | 03/09/2019 | 0 | TK_Complete
00MBH40 | TT_Task | NDE | 13/04/2019 | 10/05/2019 | 13/04/2019 | 19/09/2019 | 0 | TK_Complete
00MBH50 | TT_Task | EC+I | 22/05/2019 | 14/06/2019 | 22/05/2019 | 21/09/2019 | 0 | TK_Complete
00MBH60 | TT_Task | Line Inspection | 03/09/2019 | 09/09/2019 | 26/09/2019 | 08/10/2019 | 0 | TK_Complete
00MBH70 | TT_Task | Hydro Test | 04/10/2019 | 12/10/2019 | 30/09/2019 | 04/10/2019 | 0 | TK_Complete
00MBH80 | TT_Task | Painting/Insulation | 29/07/2019 | 14/08/2019 | 26/07/2019 | 12/08/2019 | 0 | TK_Complete
00MBH90 | TT_Task | Pre-Commissioning/Flushing/Cleaning | 21/10/2019 | 29/10/2019 | 05/10/2019 | 14/10/2019 | 0 | TK_Complete
00MKG20 | TT_Task | Install Large Bore Pipe/Valves/Supports | 01/04/2019 | 02/05/2019 | 01/04/2019 | 26/07/2019 | 0 | TK_Complete
00MKG30 | TT_Task | Install Small Bore Pipe/Valves/Supports | 13/03/2019 | 06/04/2019 | 01/03/2019 | 25/07/2019 | 0 | TK_Complete
00MKG40 | TT_Task | NDE | 02/04/2019 | 07/05/2019 | 02/04/2019 | 21/09/2019 | 0 | TK_Complete
00MKG50 | TT_Task | EC+I | 14/05/2019 | 06/06/2019 | 14/05/2019 | 25/09/2019 | 0 | TK_Complete
00MKG60 | TT_Task | Line Inspection | 03/08/2019 | 12/08/2019 | 22/08/2019 | 24/08/2019 | 0 | TK_Complete
00MKG70 | TT_Task | Hydro Test | 30/09/2019 | 09/10/2019 | 18/10/2019 | 22/10/2019 | 0 | TK_Complete
00MKG80 | TT_Task | Painting/Insulation | 14/05/2019 | 06/06/2019 | 14/05/2019 | 23/12/2019 | 0 | TK_Complete
00MKG90 | TT_Task | Pre-Commissioning/Flushing/Cleaning | 03/10/2019 | 12/10/2019 | 25/10/2019 | 23/12/2019 | 0 | TK_Complete
10BAT10 | TT_Task | Cable Raceway | 01/04/2019 | 25/04/2019 | 03/04/2019 | 02/05/2019 | 0 | TK_Complete
10BAT120 | TT_Task | Precommissioning | 02/08/2019 | 14/08/2019 | 12/08/2019 | 19/08/2019 | 0 | TK_Complete
10BAT20 | TT_Task | BAT Transformer Installation Programme | 21/02/2019 | 20/05/2019 | 06/02/2019 | 26/06/2019 | 0 | TK_Complete
10BAT30 | TT_Task | Install, grout 30 Support Plates in Foundation | 30/04/2019 | 06/05/2019 | 30/04/2019 | 07/05/2019 | 0 | TK_Complete
10BAT50 | TT_Task | Cable Pulling | 02/05/2019 | 06/06/2019 | 02/05/2019 | 26/06/2019 | 0 | TK_Complete
10BAT90 | TT_Task | Cable Termination | 25/05/2019 | 06/06/2019 | 14/05/2019 | 17/08/2019 | 0 | TK_Complete
10BFT100 | TT_Task | Hi Pot Testing | 26/06/2019 | 06/07/2019 | 29/06/2019 | 10/08/2019 | 0 | TK_Complete
10SFC-10 | TT_Task | Cable Raceway | 02/04/2019 | 16/04/2019 | 02/04/2019 | 16/04/2019 | 0 | TK_Complete
10SFC-20 | TT_Task | SFC Transformer Installation Programme | 25/03/2019 | 11/04/2019 | 27/03/2019 | 04/06/2019 | 0 | TK_Complete
10SFC-40 | TT_Task | Cable Pulling | 11/04/2019 | 15/05/2019 | 11/03/2019 | 17/06/2019 | 0 | TK_Complete
10SFC-50 | TT_Task | Cable Termination | 05/06/2019 | 17/06/2019 | 25/05/2019 | 20/09/2019 | 0 | TK_Complete
10SFC-70 | TT_Task | Hi Pot Testing | 28/06/2019 | 04/07/2019 | 25/06/2019 | 10/08/2019 | 0 | TK_Complete
10SFC-80 | TT_Task | Precommissioning | 03/08/2019 | 15/08/2019 | 24/08/2019 | 12/10/2019 | 0 | TK_Complete
101BBT20 | TT_Task | BBT Transformer Installation Programme | 11/03/2019 | 30/04/2019 | 20/03/2019 | 03/06/2019 | 0 | TK_Complete
10BBT10 | TT_Task | Cable Raceway | 02/04/2019 | 16/04/2019 | 02/04/2019 | 03/05/2019 | 0 | TK_Complete
10BBT50 | TT_Task | Cable Termination | 07/05/2019 | 24/05/2019 | 07/05/2019 | 20/09/2019 | 0 | TK_Complete
10BBT60 | TT_Task | Cable Pulling | 25/03/2019 | 26/04/2019 | 11/03/2019 | 07/06/2019 | 0 | TK_Complete
10BBT70 | TT_Task | Hi Pot Testing | 06/06/2019 | 20/06/2019 | 28/06/2019 | 10/08/2019 | 0 | TK_Complete
10BBT90 | TT_Task | Precommissioning | 12/08/2019 | 26/08/2019 | 28/08/2019 | 11/10/2019 | 0 | TK_Complete
10SEE-10 | TT_Task | Cable Raceway | 02/04/2019 | 16/04/2019 | 02/04/2019 | 14/05/2019 | 0 | TK_Complete
10SEE-20 | TT_Task | SEE Transformer Installation Programme | 25/03/2019 | 11/04/2019 | 27/03/2019 | 04/06/2019 | 0 | TK_Complete
10SEE-40 | TT_Task | Cable Pulling | 11/04/2019 | 25/05/2019 | 11/03/2019 | 27/06/2019 | 0 | TK_Complete
10SEE-50 | TT_Task | Cable Termination | 25/06/2019 | 11/07/2019 | 10/05/2019 | 21/09/2019 | 0 | TK_Complete
10SEE-70 | TT_Task | Hi Pot Testing | 08/07/2019 | 17/07/2019 | 16/07/2019 | 10/08/2019 | 0 | TK_Complete
10SEE2-80 | TT_Task | Precommissioning | 02/09/2019 | 13/09/2019 | 02/09/2019 | 19/10/2019 | 0 | TK_Complete
10BHT-10 | TT_Task | Cable Raceway | 22/02/2019 | 15/03/2019 | 01/03/2019 | 13/03/2019 | 0 | TK_Complete
10BHT-20 | TT_Task | LV Transformer Installation Programme (7 days x 4 transformers) | 11/03/2019 | 03/04/2019 | 27/03/2019 | 12/06/2019 | 0 | TK_Complete
10BHT-40 | TT_Task | Cable Pulling | 18/04/2019 | 16/05/2019 | 13/03/2019 | 20/03/2019 | 0 | TK_Complete
10BHT-50 | TT_Task | Cable Termination | 03/05/2019 | 13/05/2019 | 03/05/2019 | 17/08/2019 | 0 | TK_Complete
10BHT-70 | TT_Task | Hi Pot Testing | 15/06/2019 | 27/06/2019 | 15/06/2019 | 23/07/2019 | 0 | TK_Complete
10BHT-80 | TT_Task | Precommissioning | 31/07/2019 | 12/08/2019 | 24/07/2019 | 12/10/2019 | 0 | TK_Complete
10BAC10 | TT_Task | Install Generator Circuit Breaker (GCB) onto Support Steel | 18/06/2019 | 04/07/2019 | 14/05/2019 | 26/07/2019 | 0 | TK_Complete
10BAC20 | TT_Task | Install Control Panel | 05/07/2019 | 11/07/2019 | 06/05/2019 | 27/07/2019 | 0 | TK_Complete
10BAC30 | TT_Task | Precommissioning | 31/07/2019 | 10/08/2019 | 27/07/2019 | 01/08/2019 | 0 | TK_Complete
10BAC40 | TT_Task | Test | 12/08/2019 | 22/08/2019 | 02/08/2019 | 03/09/2019 | 0 | TK_Complete
10BA10 | TT_Task | Installation of IPB Cabinet (Neut. Grd, Sec CT, Earthing, Pressure Red., H2 Purge) | 13/05/2019 | 29/05/2019 | 13/05/2019 | 06/11/2019 | 0 | TK_Complete
10BA100 | TT_Task | IPB Connection to Generator &amp; Generator Breaker after HI Voltage Test | 12/07/2019 | 16/07/2019 | 13/05/2019 | 07/11/2019 | 0 | TK_Complete
10BA110 | TT_Task | IPB Connection at Main Transformer &amp; Auxiliary Transformers after HI Voltage Test | 29/08/2019 | 31/08/2019 | 13/07/2019 | 24/10/2019 | 0 | TK_Complete
10BA120 | TT_Task | Installation of Surge Arrestor | 18/07/2019 | 23/07/2019 | 06/07/2019 | 28/08/2019 | 0 | TK_Complete
10BA130 | TT_Task | IPB Connection at ExcitationTransformer &amp; SFC Transformer after HI Voltage Test | 02/09/2019 | 04/09/2019 | 17/08/2019 | 07/11/2019 | 0 | TK_Complete
10BA140 | TT_Task | IPB Connection at Main Transformer &amp; Auxiliary Transformers after HI Voltage Test | 02/09/2019 | 04/09/2019 | 15/08/2019 | 07/11/2019 | 0 | TK_Complete
10BA150 | TT_Task | Close Inspection Cover | 08/11/2019 | 08/11/2019 | 08/11/2019 | 08/11/2019 | 0 | TK_Complete
10BA160 | TT_Task | Air Leakage Test | 10/09/2019 | 13/09/2019 | 21/09/2019 | 25/09/2019 | 0 | TK_Complete
10BA170 | TT_Task | Precommissioning | 09/11/2019 | 12/11/2019 | 09/11/2019 | 12/11/2019 | 0 | TK_Complete
10BA20 | TT_Task | Install Steel Structure @ Generator Area | 01/04/2019 | 23/05/2019 | 01/04/2019 | 23/07/2019 | 0 | TK_Complete
10BA30 | TT_Task | Install/Align/Weld IPB | 01/06/2019 | 03/07/2019 | 16/05/2019 | 14/09/2019 | 0 | TK_Complete
10BA40 | TT_Task | NDE | 04/06/2019 | 10/07/2019 | 20/05/2019 | 14/09/2019 | 0 | TK_Complete
10BA50 | TT_Task | Install Support Steel Transformer Area | 26/04/2019 | 10/05/2019 | 26/04/2019 | 24/07/2019 | 0 | TK_Complete
10BA60 | TT_Task | Install Air Piping from Pressure Reducing Cubicle to Taps @ IPB Enclosure | 14/05/2019 | 22/05/2019 | 14/05/2019 | 07/11/2019 | 0 | TK_Complete
10BA70 | TT_Task | Install Air Piping from Pressure Reducing Cubicle to Taps @ IPB Enclosure | 18/07/2019 | 22/07/2019 | 27/07/2019 | 07/11/2019 | 0 | TK_Complete
10BA80 | TT_Task | Installation of Short Circuit Devise | 26/06/2019 | 03/07/2019 | 15/06/2019 | 20/09/2019 | 0 | TK_Complete
10BA90 | TT_Task | Hi Potential Test | 02/09/2019 | 07/09/2019 | 02/09/2019 | 07/09/2019 | 0 | TK_Complete
10CHA30 | TT_Task | Set Generator Protection Panel, Align &amp; Bolt | 30/04/2019 | 08/05/2019 | 30/04/2019 | 06/05/2019 | 0 | TK_Complete
10CHA40 | TT_Task | Install Generator Protection Panel Relays | 04/06/2019 | 11/06/2019 | 07/05/2019 | 24/07/2019 | 0 | TK_Complete
10CHA50 | TT_Task | Install Cable Tray | 30/04/2019 | 25/05/2019 | 30/04/2019 | 13/05/2019 | 0 | TK_Complete
10CHA60 | TT_Task | Cable Pulling &amp; Terminations | 25/05/2019 | 15/06/2019 | 15/05/2019 | 02/08/2019 | 0 | TK_Complete
10CHA70 | TT_Task | Hi Pot | 13/06/2019 | 20/06/2019 | 26/06/2019 | 03/08/2019 | 0 | TK_Complete
10CHA80 | TT_Task | Precommissioning | 02/08/2019 | 12/08/2019 | 24/08/2019 | 30/08/2019 | 0 | TK_Complete
10MKB30 | TT_Task | Set Excitation Control &amp; Circuit Breaker Panels, Align &amp; Bolt | 04/06/2019 | 12/06/2019 | 20/05/2019 | 17/07/2019 | 0 | TK_Complete
10MKB40 | TT_Task | Install Relays | 12/06/2019 | 19/06/2019 | 21/05/2019 | 26/07/2019 | 0 | TK_Complete
10MKB50 | TT_Task | Install Cable Tray | 04/06/2019 | 22/06/2019 | 07/05/2019 | 21/05/2019 | 0 | TK_Complete
10MKB60 | TT_Task | Cable Puling &amp; Terminations | 22/06/2019 | 17/07/2019 | 22/05/2019 | 17/08/2019 | 0 | TK_Complete
10MKB70 | TT_Task | Hi Pot | 18/06/2019 | 24/06/2019 | 27/06/2019 | 20/07/2019 | 0 | TK_Complete
10MKB80 | TT_Task | Precommissioning | 03/08/2019 | 08/08/2019 | 28/08/2019 | 10/10/2019 | 0 | TK_Complete
10MKB200 | TT_Task | Set Static Start-up Panel &amp; Switichgear, Align &amp; Bolt | 15/04/2019 | 25/04/2019 | 27/03/2019 | 23/07/2019 | 0 | TK_Complete
10MKB210 | TT_Task | Install Relays | 17/06/2019 | 24/06/2019 | 14/05/2019 | 26/07/2019 | 0 | TK_Complete
10MKB220 | TT_Task | Install Cable Tray | 03/05/2019 | 25/05/2019 | 11/03/2019 | 08/05/2019 | 0 | TK_Complete
10MKB230 | TT_Task | Cable Puling &amp; Terminations | 25/05/2019 | 17/06/2019 | 11/03/2019 | 03/08/2019 | 0 | TK_Complete
10MKB240 | TT_Task | Hi Pot | 10/07/2019 | 17/07/2019 | 17/07/2019 | 10/08/2019 | 0 | TK_Complete
10MKB250 | TT_Task | Precommissioning | 06/08/2019 | 10/08/2019 | 06/08/2019 | 08/10/2019 | 0 | TK_Complete
10BH10 | TT_Task | Switchgear Cubicles Installation/ Bolting | 08/04/2019 | 16/05/2019 | 10/04/2019 | 09/05/2019 | 0 | TK_Complete
10BH20 | TT_Task | Cable Raceway | 02/04/2019 | 16/04/2019 | 01/03/2019 | 30/04/2019 | 0 | TK_Complete
10BH30 | TT_Task | Protection Panel | 09/05/2019 | 24/05/2019 | 09/05/2019 | 24/05/2019 | 0 | TK_Complete
10BH40 | TT_Task | UPS/DC Cable Pulling | 24/05/2019 | 10/06/2019 | 20/05/2019 | 26/07/2019 | 0 | TK_Complete
10BH41 | TT_Task | Distribution Panel | 10/06/2019 | 25/06/2019 | 14/05/2019 | 16/05/2019 | 0 | TK_Complete
10BH50 | TT_Task | Bus Torquing/Connection | 25/06/2019 | 09/07/2019 | 20/05/2019 | 10/08/2019 | 0 | TK_Complete
10BH60 | TT_Task | Hi Pot Testing | 16/07/2019 | 31/07/2019 | 16/07/2019 | 24/08/2019 | 0 | TK_Complete
00BHV10 | TT_Task | Switchgear Cubicles Installation/ Bolting | 08/04/2019 | 03/05/2019 | 10/04/2019 | 03/08/2019 | 0 | TK_Complete
00BHV20 | TT_Task | Cable Raceway | 27/02/2019 | 21/03/2019 | 11/02/2019 | 27/04/2019 | 0 | TK_Complete
00BHV30 | TT_Task | Protection Panel | 11/05/2019 | 15/05/2019 | 11/05/2019 | 03/08/2019 | 0 | TK_Complete
00BHV40 | TT_Task | UPS/DC Cable Pulling | 16/05/2019 | 01/06/2019 | 16/05/2019 | 24/08/2019 | 0 | TK_Complete
00BHV50 | TT_Task | Distribution Panel | 03/06/2019 | 06/06/2019 | 12/05/2019 | 10/08/2019 | 0 | TK_Complete
00BHV60 | TT_Task | Bus Torquing/Connection | 06/06/2019 | 11/06/2019 | 17/05/2019 | 17/08/2019 | 0 | TK_Complete
00BHV70 | TT_Task | Hi Pot Testing | 22/07/2019 | 26/07/2019 | 15/06/2019 | 03/08/2019 | 0 | TK_Complete
10BF10 | TT_Task | Switchgear Cubicles Installation/ Bolting | 02/04/2019 | 24/05/2019 | 10/03/2019 | 03/05/2019 | 0 | TK_Complete
10BF20 | TT_Task | Cable Raceway | 02/04/2019 | 06/04/2019 | 01/03/2019 | 17/04/2019 | 0 | TK_Complete
10BF30 | TT_Task | Protection Panel | 16/04/2019 | 20/04/2019 | 16/04/2019 | 04/05/2019 | 0 | TK_Complete
10BF40 | TT_Task | UPS/DC Cable Pulling | 04/05/2019 | 09/05/2019 | 04/05/2019 | 17/05/2019 | 0 | TK_Complete
10BF50 | TT_Task | Distribution Panel | 09/05/2019 | 14/05/2019 | 09/05/2019 | 14/05/2019 | 0 | TK_Complete
10BF60 | TT_Task | Bus Torquing/Connection | 14/05/2019 | 18/05/2019 | 14/05/2019 | 18/05/2019 | 0 | TK_Complete
10BF70 | TT_Task | Hi Pot Testing | 18/05/2019 | 23/05/2019 | 18/05/2019 | 25/05/2019 | 0 | TK_Complete
10BBE10 | TT_Task | Switchgear Cubicles Installation/ Bolting | 01/04/2019 | 26/04/2019 | 10/03/2019 | 02/05/2019 | 0 | TK_Complete
10BBE20 | TT_Task | Cable Raceway | 01/04/2019 | 18/04/2019 | 01/03/2019 | 14/05/2019 | 0 | TK_Complete
10BBE30 | TT_Task | Protection Panel | 15/04/2019 | 02/05/2019 | 15/04/2019 | 09/05/2019 | 0 | TK_Complete
10BBE40 | TT_Task | UPS/DC Cable Pulling | 13/04/2019 | 03/05/2019 | 13/04/2019 | 27/07/2019 | 0 | TK_Complete
10BBE50 | TT_Task | Bus Torquing | 29/04/2019 | 08/05/2019 | 29/04/2019 | 20/05/2019 | 0 | TK_Complete
10BBE60 | TT_Task | Hi Pot Testing | 18/06/2019 | 03/07/2019 | 04/06/2019 | 13/07/2019 | 0 | TK_Complete
10BBE70 | TT_Task | Install &amp; Test 6.6kV Switchgear Panel x 2 | 01/03/2018 | 06/03/2018 | 22/02/2018 | 26/02/2018 | 0 | TK_Complete
10BBE80 | TT_FinMile | Ready for Energization from Temp. Feed | 09/09/2019 | 09/09/2019 | 17/08/2019 | 17/08/2019 | 0 | TK_Complete
10BBE90 | TT_Task | Pull Temp. MV Cable from Existing Station MV | 31/07/2019 | 20/08/2019 | 03/06/2019 | 20/08/2019 | 0 | TK_Complete
10AC10 | TT_Task | Installation of Gas Insulated Line - GIL | 08/04/2019 | 03/05/2019 | 10/04/2019 | 20/05/2019 | 0 | TK_Complete
10AC20 | TT_Task | Cable Raceway | 21/05/2019 | 24/05/2019 | 14/05/2019 | 20/06/2019 | 0 | TK_Complete
10AC30 | TT_Task | Protection Panel | 18/06/2019 | 22/06/2019 | 17/05/2019 | 24/05/2019 | 0 | TK_Complete
10AC40 | TT_Task | UPS/DC Cable Pulling | 22/06/2019 | 27/06/2019 | 22/05/2019 | 31/07/2019 | 0 | TK_Complete
10AC50 | TT_Task | Bus Torquing | 27/06/2019 | 03/07/2019 | 23/05/2019 | 03/08/2019 | 0 | TK_Complete
10AC60 | TT_Task | Hi Pot Testing | 27/06/2019 | 03/07/2019 | 27/06/2019 | 02/08/2019 | 0 | TK_Complete
10AC70 | TT_Task | Connection of HV Cable to 400Kv Building | 20/06/2019 | 29/06/2019 | 20/06/2019 | 10/08/2019 | 0 | TK_Complete
10BT10 | TT_Task | Switchgear Cubicles Installation/ Bolting | 01/04/2019 | 17/04/2019 | 09/04/2019 | 08/05/2019 | 0 | TK_Complete
10BT20 | TT_Task | Cable Raceway | 30/04/2019 | 13/05/2019 | 30/04/2019 | 13/05/2019 | 0 | TK_Complete
10BT30 | TT_Task | Protection Panel | 13/04/2019 | 17/04/2019 | 13/04/2019 | 17/05/2019 | 0 | TK_Complete
10BT40 | TT_Task | UPS/DC Cable Pulling | 14/05/2019 | 30/05/2019 | 14/05/2019 | 24/07/2019 | 0 | TK_Complete
10BT50 | TT_Task | Distribution Panel | 31/05/2019 | 04/06/2019 | 21/05/2019 | 24/05/2019 | 0 | TK_Complete
10BT60 | TT_Task | Bus Torquing/Connection | 05/06/2019 | 12/06/2019 | 21/05/2019 | 20/07/2019 | 0 | TK_Complete
10BT70 | TT_Task | Hi Pot Testing | 12/06/2019 | 15/06/2019 | 23/05/2019 | 25/07/2019 | 0 | TK_Complete
ECS19.1210 | TT_Task | Installation of Batteries, Battery Charger, Converter &amp; Inverter and UPS System | 09/05/2019 | 05/06/2019 | 09/05/2019 | 18/06/2019 | 0 | TK_Complete
00BAW-01-10 | TT_Task | Install Cabling | 18/06/2019 | 13/07/2019 | 24/05/2019 | 14/09/2019 | 0 | TK_Complete
00BAW-01-20 | TT_Task | Install Accessories/Supports | 01/04/2019 | 23/04/2019 | 01/04/2019 | 18/05/2019 | 0 | TK_Complete
00BAW-01-30 | TT_Task | Install equipment | 20/05/2019 | 08/06/2019 | 13/05/2019 | 29/06/2019 | 0 | TK_Complete
00BAW-01-40 | TT_Task | Install Primary Containment | 10/06/2019 | 13/06/2019 | 15/05/2019 | 16/07/2019 | 0 | TK_Complete
00BAW-01-50 | TT_Task | Install Secondary Containment | 13/06/2019 | 18/06/2019 | 24/05/2019 | 17/07/2019 | 0 | TK_Complete
00BAW-01-60 | TT_Task | Test | 02/08/2019 | 07/08/2019 | 17/08/2019 | 24/08/2019 | 0 | TK_Complete
00BAW-02-10 | TT_Task | Lay the Earthing Conductors from the Equipment to Designated Earth Pit | 17/06/2019 | 23/07/2019 | 21/05/2019 | 23/07/2019 | 0 | TK_Complete
00BAW-02-20 | TT_Task | Install Accessories/Supports/Mounting Fitting | 01/04/2019 | 12/04/2019 | 10/04/2019 | 10/05/2019 | 0 | TK_Complete
00BAW-02-30 | TT_Task | Install equipment | 12/04/2019 | 27/04/2019 | 12/04/2019 | 19/06/2019 | 0 | TK_Complete
00BAW-02-40 | TT_Task | Install Secondary Containment | 31/05/2019 | 05/07/2019 | 22/05/2019 | 18/07/2019 | 0 | TK_Complete
00BAW-02-50 | TT_Task | Install Primary Containment | 23/05/2019 | 27/06/2019 | 20/05/2019 | 20/07/2019 | 0 | TK_Complete
00BAW-02-60 | TT_Task | Test | 10/09/2019 | 16/09/2019 | 07/09/2019 | 12/10/2019 | 0 | TK_Complete
00BAW-02-80 | TT_Task | Complete all Terminations | 06/06/2019 | 29/06/2019 | 15/06/2019 | 10/10/2019 | 0 | TK_Complete
00BAW-03-10 | TT_Task | Install Cabling | 31/05/2019 | 24/06/2019 | 22/06/2019 | 12/09/2019 | 0 | TK_Complete
00BAW-03-20 | TT_Task | Install Accessories/Supports/Mounting/Fittings | 01/04/2019 | 06/05/2019 | 08/04/2019 | 17/05/2019 | 0 | TK_Complete
00BAW-03-30 | TT_Task | Install Equipment | 15/05/2019 | 15/06/2019 | 15/05/2019 | 03/07/2019 | 0 | TK_Complete
00BAW-03-40 | TT_Task | Install Primary Containment | 29/05/2019 | 27/06/2019 | 20/05/2019 | 16/07/2019 | 0 | TK_Complete
00BAW-03-50 | TT_Task | Install Secondary Containment | 15/06/2019 | 10/07/2019 | 20/05/2019 | 20/07/2019 | 0 | TK_Complete
00BAW-03-60 | TT_Task | Test | 09/08/2019 | 14/08/2019 | 28/08/2019 | 08/10/2019 | 0 | TK_Complete
00BAW-03-70 | TT_Task | Install All Termination Rods | 21/06/2019 | 06/07/2019 | 23/05/2019 | 31/07/2019 | 0 | TK_Complete
00BAW-03-80 | TT_Task | Install Downcomers | 31/05/2019 | 27/06/2019 | 22/06/2019 | 22/08/2019 | 0 | TK_Complete
00BAW-03-90 | TT_FinMile | Assumption Underground Grid Complete | 17/12/2019 | 17/12/2019 | 28/08/2019 | 28/08/2019 | 0 | TK_Complete
A2220 | TT_Task | Installation of Gas Detection and System | 30/04/2019 | 03/06/2019 | 07/05/2019 | 22/05/2019 | 0 | TK_Complete
ECS20.1030 | TT_Task | Installation of instrument, equipment and cable for gas detection system for Gas Turbine &amp; Auxiliaries | 23/05/2019 | 15/06/2019 | 23/05/2019 | 17/10/2019 | 0 | TK_Complete
FSS22.1140 | TT_Task | Installation of Gas Detection System for BOP | 30/04/2019 | 01/08/2019 | 07/03/2019 | 08/01/2020 | 0 | TK_Complete
A2330 | TT_Task | Lighting and Small Power Installation &amp; Commissioning FW Area | 31/05/2019 | 12/06/2019 | 31/05/2019 | 10/10/2019 | 0 | TK_Complete
A3320 | TT_Task | Installation Lighting and Small Power | 01/04/2019 | 04/05/2019 | 01/04/2019 | 28/09/2019 | 0 | TK_Complete
CP-BZL7-60 | TT_Task | Remaining Lighting and Small Power Finished | 30/09/2019 | 30/09/2019 | 11/10/2019 | 12/10/2019 | 0 | TK_Complete
CP1BZL7A15 | TT_Task | Lighting and Small Power Installation (10UBA) | 22/06/2019 | 10/07/2019 | 22/05/2019 | 24/09/2019 | 0 | TK_Complete
10BZL-03-10 | TT_Task | Install Accessories/Supports | 22/08/2019 | 07/09/2019 | 01/06/2019 | 03/07/2019 | 0 | TK_Complete
10BZL-03-20 | TT_Task | Install Primary Containment | 09/09/2019 | 03/10/2019 | 03/07/2019 | 20/07/2019 | 0 | TK_Complete
10BZL-03-30 | TT_Task | Install Secondary Containment | 04/10/2019 | 25/10/2019 | 20/07/2019 | 28/08/2019 | 0 | TK_Complete
10BZL-03-40 | TT_Task | Install Cabling | 04/10/2019 | 01/11/2019 | 14/08/2019 | 28/08/2019 | 0 | TK_Complete
10BZL-03-50 | TT_FinMile | Assumption Civil Contractor L&amp;SP Complete | 28/03/2020 | 28/03/2020 | 05/02/2020 | 05/02/2020 | 0 | TK_Complete
10BZL-01-10 | TT_Task | Install Accessories/Supports | 30/09/2019 | 16/10/2019 | 07/10/2019 | 19/10/2019 | 0 | TK_Complete
10BZL-01-20 | TT_Task | Install Primary Containment | 08/10/2019 | 22/10/2019 | 12/10/2019 | 17/10/2019 | 0 | TK_Complete
10BZL-01-30 | TT_Task | Install Secondary Containment | 11/10/2019 | 22/10/2019 | 11/10/2019 | 17/10/2019 | 0 | TK_Complete
10BZL-01-40 | TT_Task | Install Cabling | 17/10/2019 | 28/10/2019 | 11/10/2019 | 19/10/2019 | 0 | TK_Complete
10BZL-02-10 | TT_Task | Install Accessories/Supports | 30/09/2019 | 18/10/2019 | 02/07/2019 | 30/07/2019 | 0 | TK_Complete
10BZL-02-20 | TT_Task | Install Primary Containment | 11/10/2019 | 28/10/2019 | 02/07/2019 | 30/07/2019 | 0 | TK_Complete
10BZL-02-30 | TT_Task | Install Secondary Containment | 21/10/2019 | 09/11/2019 | 23/09/2019 | 12/10/2019 | 0 | TK_Complete
10BZL-02-40 | TT_Task | Install Cabling | 05/11/2019 | 25/11/2019 | 03/10/2019 | 12/10/2019 | 0 | TK_Complete
00BZL-01-10 | TT_Task | Install Accessories/Supports | 15/10/2019 | 26/10/2019 | 05/10/2019 | 11/10/2019 | 0 | TK_Complete
00BZL-01-30 | TT_Task | Install Secondary Containment | 26/10/2019 | 09/11/2019 | 05/10/2019 | 12/10/2019 | 0 | TK_Complete
00BZL-01-40 | TT_Task | Install Cabling | 09/11/2019 | 23/11/2019 | 05/10/2019 | 12/10/2019 | 0 | TK_Complete
00BZL-03-10 | TT_Task | Install Accessories/Supports | 30/09/2019 | 14/10/2019 | 04/10/2019 | 12/10/2019 | 0 | TK_Complete
00BZL-03-20 | TT_Task | Install Primary Containment | 09/10/2019 | 25/10/2019 | 04/10/2019 | 12/10/2019 | 0 | TK_Complete
00BZL-03-30 | TT_Task | Install Secondary Containment | 21/10/2019 | 06/11/2019 | 04/10/2019 | 12/10/2019 | 0 | TK_Complete
00BZL-03-40 | TT_Task | Install Cabling | 07/11/2019 | 26/11/2019 | 04/10/2019 | 12/10/2019 | 0 | TK_Complete
00BZL-02-10 | TT_Task | Install Accessories/Supports | 30/09/2019 | 12/10/2019 | 02/10/2019 | 12/10/2019 | 0 | TK_Complete
00BZL-02-30 | TT_Task | Install Secondary Containment | 03/10/2019 | 12/10/2019 | 02/10/2019 | 12/10/2019 | 0 | TK_Complete
00BZL-02-40 | TT_Task | Install Cabling | 05/10/2019 | 15/10/2019 | 02/10/2019 | 12/10/2019 | 0 | TK_Complete
00XKA10 | TT_Task | Installation of Emergency Diesel Generator Set ( XKA) | 16/07/2019 | 01/08/2019 | 22/07/2019 | 02/10/2019 | 0 | TK_Complete
00XKA30 | TT_Task | Install Pipework | 26/06/2019 | 17/07/2019 | 01/06/2019 | 19/10/2019 | 0 | TK_Complete
00XKA40 | TT_Task | Cable Raceway | 12/07/2019 | 29/07/2019 | 04/06/2019 | 22/06/2019 | 0 | TK_Complete
00XKA50 | TT_Task | Pull Cables &amp; Terminate | 18/07/2019 | 03/08/2019 | 06/06/2019 | 30/11/2019 | 0 | TK_Complete
00XKA60 | TT_Task | Precommissioning | 05/10/2019 | 18/10/2019 | 15/10/2019 | 26/11/2019 | 0 | TK_Complete
10CP-ST-10 | TT_Task | ET200 Cabinet Installation including Supports | 13/04/2019 | 25/04/2019 | 13/04/2019 | 10/05/2019 | 0 | TK_Complete
10CP-ST-20 | TT_Task | Grounding Supports | 01/04/2019 | 11/04/2019 | 01/04/2019 | 10/08/2019 | 0 | TK_Complete
10CP-ST-30 | TT_Task | AC/DC Installation | 07/06/2019 | 24/06/2019 | 15/06/2019 | 10/08/2019 | 0 | TK_Complete
10CP-ST-40 | TT_Task | Cable Installation | 28/05/2019 | 11/06/2019 | 28/05/2019 | 07/08/2019 | 0 | TK_Complete
10CP-ST-50 | TT_Task | Communication Cable Installation | 28/05/2019 | 07/06/2019 | 28/05/2019 | 07/08/2019 | 0 | TK_Complete
10CP-ST-60 | TT_Task | Primary and Secondary Containment Installation | 10/05/2019 | 27/05/2019 | 10/05/2019 | 10/07/2019 | 0 | TK_Complete
10CP-ST-70 | TT_Task | Test System | 02/08/2019 | 16/08/2019 | 12/08/2019 | 14/08/2019 | 0 | TK_Complete
10CP-GT10 | TT_Task | ET200 Cabinet Installation including Supports | 01/04/2019 | 11/04/2019 | 05/04/2019 | 15/05/2019 | 0 | TK_Complete
10CP-GT20 | TT_Task | Grounding Supports | 13/04/2019 | 24/04/2019 | 13/04/2019 | 10/08/2019 | 0 | TK_Complete
10CP-GT30 | TT_Task | AC/DC Installation | 16/05/2019 | 27/05/2019 | 16/05/2019 | 07/08/2019 | 0 | TK_Complete
10CP-GT40 | TT_Task | Cable Installation | 16/05/2019 | 27/05/2019 | 16/05/2019 | 08/08/2019 | 0 | TK_Complete
10CP-GT50 | TT_Task | Communication Cable Installation | 28/05/2019 | 07/06/2019 | 28/05/2019 | 08/08/2019 | 0 | TK_Complete
10CP-GT60 | TT_Task | Primary and Secondary Containment Installation | 13/04/2019 | 24/04/2019 | 13/04/2019 | 10/07/2019 | 0 | TK_Complete
10CP-GT70 | TT_Task | Test System | 05/08/2019 | 15/08/2019 | 09/08/2019 | 13/08/2019 | 0 | TK_Complete
10CP-WS10 | TT_Task | ET200 Cabinet Installation including Supports | 17/04/2019 | 27/04/2019 | 17/04/2019 | 15/05/2019 | 0 | TK_Complete
10CP-WS20 | TT_Task | Grounding Supports | 26/04/2019 | 02/05/2019 | 26/04/2019 | 09/08/2019 | 0 | TK_Complete
10CP-WS30 | TT_Task | AC/DC Installation | 11/05/2019 | 22/05/2019 | 11/05/2019 | 23/08/2019 | 0 | TK_Complete
10CP-WS40 | TT_Task | Cable Installation | 23/05/2019 | 03/06/2019 | 23/05/2019 | 03/08/2019 | 0 | TK_Complete
10CP-WS50 | TT_Task | Communication Cable Installation | 23/05/2019 | 03/06/2019 | 23/05/2019 | 03/08/2019 | 0 | TK_Complete
10CP-WS60 | TT_Task | Primary and Secondary Containment Installation | 06/05/2019 | 16/05/2019 | 06/05/2019 | 10/07/2019 | 0 | TK_Complete
10CP-WS70 | TT_Task | Test System | 05/08/2019 | 16/08/2019 | 06/08/2019 | 17/08/2019 | 0 | TK_Complete
10CP-HR10 | TT_Task | ET200 Cabinet Installation including Supports | 31/08/2019 | 07/09/2019 | 06/08/2019 | 13/08/2019 | 0 | TK_Complete
10CP-HR20 | TT_Task | Grounding Supports | 31/05/2019 | 11/06/2019 | 20/05/2019 | 30/05/2019 | 0 | TK_Complete
10CP-HR30 | TT_Task | AC/DC Installation | 04/09/2019 | 10/09/2019 | 14/08/2019 | 20/08/2019 | 0 | TK_Complete
10CP-HR40 | TT_Task | Cable Installation | 31/08/2019 | 06/09/2019 | 22/08/2019 | 23/08/2019 | 0 | TK_Complete
10CP-HR50 | TT_Task | Communication Cable Installation | 31/08/2019 | 06/09/2019 | 22/08/2019 | 24/08/2019 | 0 | TK_Complete
10CP-HR60 | TT_Task | Primary and Secondary Containment Installation | 31/08/2019 | 06/09/2019 | 06/08/2019 | 13/08/2019 | 0 | TK_Complete
10CP-HR70 | TT_Task | Test System | 31/08/2019 | 03/09/2019 | 26/08/2019 | 26/08/2019 | 0 | TK_Complete
10CP-AA10 | TT_Task | ET200 Cabinet Installation including Supports | 30/09/2019 | 10/10/2019 | 25/07/2019 | 31/07/2019 | 0 | TK_Complete
10CP-AA20 | TT_Task | Grounding Supports | 30/09/2019 | 10/10/2019 | 25/07/2019 | 31/07/2019 | 0 | TK_Complete
10CP-AA30 | TT_Task | AC/DC Installation | 03/10/2019 | 09/10/2019 | 31/07/2019 | 07/08/2019 | 0 | TK_Complete
10CP-AA40 | TT_Task | Cable Installation | 30/09/2019 | 09/10/2019 | 01/08/2019 | 09/08/2019 | 0 | TK_Complete
10CP-AA50 | TT_Task | Communication Cable Installation | 30/09/2019 | 11/10/2019 | 01/08/2019 | 09/08/2019 | 0 | TK_Complete
10CP-AA60 | TT_Task | Primary and Secondary Containment Installation | 30/09/2019 | 11/10/2019 | 25/07/2019 | 31/07/2019 | 0 | TK_Complete
10CP-AA70 | TT_Task | Test System | 30/09/2019 | 08/10/2019 | 10/08/2019 | 13/08/2019 | 0 | TK_Complete
CP-BZP7A15 | TT_Task | Erection Cable Trays Between UEY/UGY01 to UGD/USG/UGA/UGC/UEN | 01/04/2019 | 23/05/2019 | 01/04/2019 | 05/06/2019 | 0 | TK_Complete
CP-BZP7B15 | TT_Task | Erection Cable Trays Between 10UBA Building to UEY/10UEN | 21/01/2019 | 27/02/2019 | 21/01/2019 | 08/05/2019 | 0 | TK_Complete
CP1BZP7A15 | TT_Task | Erection Cable Trays UMC to Generator (1f) | 02/01/2019 | 22/02/2019 | 13/11/2018 | 15/05/2019 | 0 | TK_Complete
CP1BZP7C15 | TT_Task | Erection Cable Trays 10UBA Building to UBX/UBE/UBF | 02/01/2019 | 20/02/2019 | 22/10/2018 | 15/05/2019 | 0 | TK_Complete
CP1BZP7C25 | TT_Task | Cable Support Installation | 01/04/2019 | 27/06/2019 | 01/04/2019 | 19/06/2019 | 0 | TK_Complete
CP1BZP7D15 | TT_Task | Erection Cable Trays 10UBA Building to USA01-03 | 01/04/2019 | 23/05/2019 | 01/04/2019 | 14/06/2019 | 0 | TK_Complete
CP1BZP7F15 | TT_Task | Erection Cable Trays UMC to ST AND PUMPS (1d) | 01/04/2019 | 17/05/2019 | 01/04/2019 | 15/06/2019 | 0 | TK_Complete
CP1BZP7G15 | TT_Task | Erection Cable Trays UMC to GT (1e) | 12/02/2019 | 25/03/2019 | 15/01/2019 | 21/05/2019 | 0 | TK_Complete
CP-BZK7A25 | TT_Task | Cabling From 10UBA Building to UCA / UYC | 03/06/2019 | 02/07/2019 | 03/05/2019 | 07/09/2019 | 0 | TK_Complete
CP-BZK7B2 | TT_Task | Cabling From 10UBA Building to UAA | 30/04/2019 | 04/06/2019 | 06/05/2019 | 07/09/2019 | 0 | TK_Complete
CP-BZK7C25 | TT_Task | Cabling 10UBA Building to 00UGD/UGA/UGC | 27/05/2019 | 02/07/2019 | 02/05/2019 | 31/05/2019 | 0 | TK_Complete
CP-BZK7E25 | TT_Task | Cabling 10UBA Building to USG | 30/04/2019 | 04/06/2019 | 08/05/2019 | 07/09/2019 | 0 | TK_Complete
CP-BZK7F25 | TT_Task | Cabling 10UBA Building to UEL/UEH/UEJ | 30/04/2019 | 10/06/2019 | 03/05/2019 | 07/09/2019 | 0 | TK_Complete
CP-BZK7G25 | TT_Task | Cabling From 10UBA (Switchgear) Building to 10UBN Diesel Generator | 18/07/2019 | 21/08/2019 | 01/06/2019 | 06/09/2019 | 0 | TK_Complete
CP-BZK7H25 | TT_Task | Cabling From 10UBA Building to ULA (FW Pumps)/UHA (HRSG) AND UHW (Blow Down Tank) | 24/05/2019 | 10/07/2019 | 24/05/2019 | 06/09/2019 | 0 | TK_Complete
CP-BZK7I25 | TT_Task | Cabling From 10UBA Building to UST | 01/04/2019 | 06/05/2019 | 08/04/2019 | 05/09/2019 | 0 | TK_Complete
CP1BZK7A25 | TT_Task | Cabling From 10UBA (Switchgear) Building to UBX/UBE/UBF (Transformers) | 16/04/2019 | 27/05/2019 | 16/04/2019 | 07/09/2019 | 0 | TK_Complete
CP1BZK7B25 | TT_Task | Cabling Between 10UBA Building | 14/02/2019 | 18/03/2019 | 20/02/2019 | 31/05/2019 | 0 | TK_Complete
CP1BZK7B35 | TT_Task | MV and LV Cable Pulling | 30/04/2019 | 21/09/2019 | 10/05/2019 | 09/09/2019 | 0 | TK_Complete
CP1BZK7D25 | TT_Task | Cabling 10UBA (Switchgear) Building to 10UEN (Gas Filter/Preheating) | 17/06/2019 | 12/07/2019 | 17/05/2019 | 02/09/2019 | 0 | TK_Complete
CP1BZK7J25 | TT_Task | Cabling From 10UBA Building to USA01-03 | 05/06/2019 | 11/07/2019 | 14/06/2019 | 07/09/2019 | 0 | TK_Complete
CP-CYP7A15 | TT_Task | Erection Security Other Buildings (Except UCA) | 30/11/2019 | 28/12/2019 | 04/11/2019 | 18/01/2020 | 0 | TK_Complete
CP-CYP7A25 | TT_Task | Install Equipment | 31/08/2019 | 30/09/2019 | 20/08/2019 | 13/01/2020 | 0 | TK_Complete
CP-CYP7A35 | TT_Task | EC+I | 25/09/2019 | 19/10/2019 | 20/08/2019 | 30/11/2019 | 0 | TK_Complete
CP-CYP7A45 | TT_Task | Precommissioning | 04/04/2020 | 08/04/2020 | 14/01/2020 | 18/01/2020 | 0 | TK_Complete
00SGA-01-10 | TT_Task | Install Skids/Euipment (Firehouse) | 30/09/2019 | 17/10/2019 | 12/10/2019 | 19/10/2019 | 0 | TK_Complete
00SGA-01-20 | TT_Task | Install LB Pipework/Valves/Supports (Firehouse) | 18/10/2019 | 29/10/2019 | 09/10/2019 | 30/11/2019 | 0 | TK_Complete
00SGA-01-30 | TT_Task | Install SB Pipework/Valves/Supports (Firehouse) | 24/10/2019 | 04/11/2019 | 11/10/2019 | 30/11/2019 | 0 | TK_Complete
00SGA-01-40 | TT_Task | Install Ring Main | 09/02/2019 | 13/06/2019 | 15/01/2019 | 17/01/2020 | 0 | TK_Complete
00SGA-01-50 | TT_Task | Install all Hydrants/Supports | 14/10/2019 | 30/10/2019 | 14/10/2019 | 06/01/2020 | 0 | TK_Complete
00SGA-01-60 | TT_Task | EC+I | 12/10/2019 | 06/11/2019 | 09/10/2019 | 18/10/2019 | 0 | TK_Complete
00SGA-01-70 | TT_Task | Hydro Test | 02/04/2020 | 14/04/2020 | 07/01/2020 | 17/01/2020 | 0 | TK_Complete
00SGA-01-80 | TT_Task | Precommissioning/Flush/Clean | 08/04/2020 | 14/04/2020 | 12/01/2020 | 17/01/2020 | 0 | TK_Complete
00SGA-01-90 | TT_Task | Paint | 05/11/2019 | 15/11/2019 | 12/10/2019 | 17/01/2020 | 0 | TK_Complete
10SGC-02-10 | TT_Task | Install Deluge Pipework/Valves/Sprinklers | 31/07/2019 | 28/08/2019 | 05/08/2019 | 11/10/2019 | 0 | TK_Complete
10SGC-02-20 | TT_Task | Install Supports | 29/08/2019 | 09/09/2019 | 07/08/2019 | 12/10/2019 | 0 | TK_Complete
10SGC-02-30 | TT_Task | Hydro Test | 25/10/2019 | 30/10/2019 | 10/10/2019 | 12/10/2019 | 0 | TK_Complete
10SGC-02-40 | TT_Task | Precommissioning/Flush/Clean | 30/10/2019 | 04/11/2019 | 10/10/2019 | 14/10/2019 | 0 | TK_Complete
10SGC-02-50 | TT_Task | Spray Test | 04/11/2019 | 08/11/2019 | 12/10/2019 | 14/01/2020 | 0 | TK_Complete
10SGA-02-10 | TT_Task | Install Deluge Pipework/Valves/Sprinklers | 08/08/2019 | 28/08/2019 | 08/08/2019 | 11/10/2019 | 0 | TK_Complete
10SGA-02-20 | TT_Task | Install Supports | 31/07/2019 | 20/08/2019 | 05/08/2019 | 09/10/2019 | 0 | TK_Complete
10SGA-02-30 | TT_Task | Hydro Test | 17/10/2019 | 26/10/2019 | 08/10/2019 | 12/10/2019 | 0 | TK_Complete
10SGA-02-40 | TT_Task | Precommissioning/Flush/Clean | 26/10/2019 | 05/11/2019 | 11/10/2019 | 19/10/2019 | 0 | TK_Complete
10SGA-02-50 | TT_Task | Spray Test | 31/03/2020 | 08/04/2020 | 04/01/2020 | 14/01/2020 | 0 | TK_Complete
10SGA-02-60 | TT_Task | Provide TEMP Fire Water Supply | 30/11/2019 | 20/12/2019 | 20/11/2019 | 03/01/2020 | 0 | TK_Complete
10SGA10 | TT_Task | Install LB Pipework/Valves/Supports | 30/09/2019 | 24/10/2019 | 17/09/2019 | 12/10/2019 | 0 | TK_Complete
10SGA20 | TT_Task | Install SB Pipework/Valves/Supports | 30/09/2019 | 18/10/2019 | 17/09/2019 | 14/10/2019 | 0 | TK_Complete
10SGA30 | TT_Task | Install all Hydrants/Supports | 30/09/2019 | 12/10/2019 | 17/09/2019 | 10/10/2019 | 0 | TK_Complete
10SGA40 | TT_Task | Hydro Test | 14/10/2019 | 18/10/2019 | 14/10/2019 | 18/10/2019 | 0 | TK_Complete
10SGA50 | TT_Task | Precommissioning/Flush/Clean | 18/10/2019 | 23/10/2019 | 19/10/2019 | 17/01/2020 | 0 | TK_Complete
10SGA60 | TT_Task | Provide TEMP Fire Water Supply | 30/11/2019 | 11/12/2019 | 20/11/2019 | 30/11/2019 | 0 | TK_Complete
00SGM-01-10 | TT_Task | Install Pipework/Valves/Sprinklers | 08/10/2019 | 05/11/2019 | 23/05/2019 | 12/10/2019 | 0 | TK_Complete
00SGM-01-20 | TT_Task | Install Supports | 19/10/2019 | 11/11/2019 | 23/05/2019 | 10/10/2019 | 0 | TK_Complete
00SGM-01-30 | TT_Task | Hydro Test | 11/10/2019 | 15/10/2019 | 11/10/2019 | 15/10/2019 | 0 | TK_Complete
00SGM-01-40 | TT_Task | Precommissioning/Flush/Clean | 16/10/2019 | 19/10/2019 | 16/10/2019 | 19/10/2019 | 0 | TK_Complete
00SGM-01-50 | TT_Task | Spray Test | 28/03/2020 | 01/04/2020 | 07/03/2020 | 12/03/2020 | 0 | TK_Complete
10SGC-01-10 | TT_Task | Install Deluge Pipework/Valves/Sprinklers | 25/10/2019 | 16/11/2019 | 19/08/2019 | 12/10/2019 | 0 | TK_Complete
10SGC-01-20 | TT_Task | Install Supports | 30/09/2019 | 24/10/2019 | 27/05/2019 | 17/10/2019 | 0 | TK_Complete
10SGC-01-30 | TT_Task | Hydro Test | 01/11/2019 | 05/11/2019 | 09/10/2019 | 11/10/2019 | 0 | TK_Complete
10SGC-01-40 | TT_Task | Precommissioning/Flush/Clean | 06/11/2019 | 09/11/2019 | 12/10/2019 | 17/10/2019 | 0 | TK_Complete
10SGC-01-50 | TT_Task | Spray Test | 09/04/2020 | 13/04/2020 | 14/03/2020 | 17/03/2020 | 0 | TK_Complete
10SGJ-02-10 | TT_Task | Install Skid+Auxiliaries | 30/09/2019 | 15/10/2019 | 08/10/2019 | 19/10/2019 | 0 | TK_Complete
10SGJ-02-20 | TT_Task | Install all pipepwork and Supports | 31/07/2019 | 12/09/2019 | 05/07/2019 | 12/10/2019 | 0 | TK_Complete
10SGJ-02-30 | TT_Task | EC+I | 16/10/2019 | 12/11/2019 | 14/10/2019 | 30/11/2019 | 0 | TK_Complete
10SGJ-02-40 | TT_Task | Hydro Test | 28/03/2020 | 06/04/2020 | 26/12/2019 | 04/01/2020 | 0 | TK_Complete
10SGJ-02-50 | TT_Task | Precommissioning/Flush/Clean | 28/03/2020 | 06/04/2020 | 26/12/2019 | 04/01/2020 | 0 | TK_Complete
FSS22.1060 | TT_Task | Installation of Fire Fighting CO2 System for PCC 10SGJ | 11/10/2019 | 27/11/2019 | 05/07/2019 | 05/01/2020 | 0 | TK_Complete
A3220 | TT_Task | Installation Fire Detection System (SGY) | 15/02/2019 | 19/06/2019 | 15/02/2019 | 20/01/2020 | 0 | TK_Complete
00CY10 | TT_Task | Equipment Installation | 01/04/2019 | 17/04/2019 | 16/04/2019 | 03/08/2019 | 0 | TK_Complete
00CY20 | TT_Task | Cable Raceways | 23/04/2019 | 18/05/2019 | 23/04/2019 | 27/06/2019 | 0 | TK_Complete
00CY30 | TT_Task | Cable Pulling | 07/06/2019 | 03/07/2019 | 30/05/2019 | 10/08/2019 | 0 | TK_Complete
00CY40 | TT_Task | Cable Termination | 12/07/2019 | 05/08/2019 | 12/06/2019 | 02/09/2019 | 0 | TK_Complete
00CY50 | TT_Task | Precommissioning | 03/09/2019 | 13/09/2019 | 03/09/2019 | 20/11/2019 | 0 | TK_Complete
10CY10 | TT_Task | Erection Telecommunication Other Buildings (Except UCA) | 24/04/2019 | 30/05/2019 | 24/04/2019 | 03/08/2019 | 0 | TK_Complete
10CY20 | TT_Task | Cable Raceways | 06/06/2019 | 08/07/2019 | 25/05/2019 | 26/06/2019 | 0 | TK_Complete
10CY30 | TT_Task | Cable Pulling | 18/06/2019 | 12/07/2019 | 13/06/2019 | 10/08/2019 | 0 | TK_Complete
10CY40 | TT_Task | Cable Termination | 29/06/2019 | 24/07/2019 | 29/06/2019 | 05/09/2019 | 0 | TK_Complete
10CY50 | TT_Task | Precommissioning | 31/08/2019 | 12/09/2019 | 06/09/2019 | 18/01/2020 | 0 | TK_Complete
00CR10 | TT_Task | Cable Tray Installation (Under Floor) | 06/11/2018 | 04/12/2018 | 20/11/2018 | 31/01/2019 | 0 | TK_Complete
00CR100 | TT_Task | Printer Installation | 01/06/2019 | 04/06/2019 | 22/06/2019 | 20/07/2019 | 0 | TK_Complete
00CR15 | TT_Task | Install Floor | 01/04/2019 | 13/04/2019 | 03/04/2019 | 07/05/2019 | 0 | TK_Complete
00CR20 | TT_Task | I/O Cabinet Installation | 29/01/2019 | 01/03/2019 | 10/10/2018 | 04/03/2019 | 0 | TK_Complete
00CR30 | TT_Task | Control Cabinet Installation | 27/02/2019 | 15/03/2019 | 10/10/2018 | 12/03/2019 | 0 | TK_Complete
00CR40 | TT_Task | Engineer Work Station Installation | 12/03/2019 | 26/03/2019 | 15/03/2019 | 21/05/2019 | 0 | TK_Complete
00CR50 | TT_Task | Operator Work Station Installation | 29/06/2019 | 04/07/2019 | 04/07/2019 | 25/07/2019 | 0 | TK_Complete
00CR60 | TT_Task | Network/Cabinet Installation | 18/06/2019 | 21/06/2019 | 10/05/2019 | 25/06/2019 | 0 | TK_Complete
00CR70 | TT_Task | AC/DC System Installation | 18/06/2019 | 20/06/2019 | 14/05/2019 | 28/06/2019 | 0 | TK_Complete
00CR80 | TT_Task | Hardwire Switches Installation | 07/06/2019 | 13/06/2019 | 22/06/2019 | 27/06/2019 | 0 | TK_Complete
00CR90 | TT_Task | Furniture Installation | 09/03/2019 | 14/03/2019 | 15/03/2019 | 29/04/2019 | 0 | TK_Complete
A3300 | TT_Task | Control Room Equipment Installation | 14/06/2019 | 26/06/2019 | 07/05/2019 | 06/07/2019 | 0 | TK_Complete
A3310 | TT_Task | Installation of Telecommunication System | 22/06/2019 | 02/07/2019 | 13/05/2019 | 06/07/2019 | 0 | TK_Complete
ECS19.1420 | TT_Task | Cable Laying of Local Control Room | 18/04/2019 | 14/05/2019 | 18/04/2019 | 26/06/2019 | 0 | TK_Complete
00PUS10 | TT_Task | Equipment Installation | 16/04/2019 | 27/04/2019 | 17/04/2019 | 24/07/2019 | 0 | TK_Complete
00PUS100 | TT_Task | EC+I | 16/07/2019 | 25/07/2019 | 13/06/2019 | 27/07/2019 | 0 | TK_Complete
00PUS110 | TT_Task | Precommissioning | 31/07/2019 | 09/08/2019 | 15/06/2019 | 07/09/2019 | 0 | TK_Complete
00PUS20 | TT_Task | Booster Pump Install | 11/06/2019 | 20/06/2019 | 11/06/2019 | 23/07/2019 | 0 | TK_Complete
00PUS30 | TT_Task | Auto Wash Strainer Install | 15/06/2019 | 26/06/2019 | 15/06/2019 | 26/07/2019 | 0 | TK_Complete
00PUS40 | TT_Task | Chlorinated Cell Module Install | 20/06/2019 | 02/07/2019 | 15/06/2019 | 27/07/2019 | 0 | TK_Complete
00PUS50 | TT_Task | Fresh Air Blower Install | 26/06/2019 | 06/07/2019 | 12/06/2019 | 23/07/2019 | 0 | TK_Complete
00PUS60 | TT_Task | XXX and Contineous Dosing Install | 02/07/2019 | 12/07/2019 | 11/06/2019 | 24/07/2019 | 0 | TK_Complete
00PUS70 | TT_Task | Fume Scrubber Install | 08/07/2019 | 17/07/2019 | 15/06/2019 | 26/07/2019 | 0 | TK_Complete
00PUS80 | TT_Task | Acid Tank and Acid Cleaning Install | 15/07/2019 | 25/07/2019 | 15/06/2019 | 26/07/2019 | 0 | TK_Complete
00PUS90 | TT_Task | Sump Pump Install | 10/07/2019 | 20/07/2019 | 13/06/2019 | 25/07/2019 | 0 | TK_Complete
10HSJ100 | TT_Task | Equipment Installation | 06/12/2019 | 13/12/2019 | 04/11/2019 | 19/11/2019 | 0 | TK_Complete
10HSJ110 | TT_Task | EC+I | 09/12/2019 | 16/12/2019 | 04/11/2019 | 23/11/2019 | 0 | TK_Complete
10HSJ120 | TT_Task | Precommissioning | 06/12/2019 | 14/12/2019 | 25/11/2019 | 18/01/2020 | 0 | TK_Complete
10HSJ130 | TT_Task | Function Test | 03/04/2020 | 11/04/2020 | 11/01/2020 | 18/01/2020 | 0 | TK_Complete
CCOM1000 | TT_Mile | Demin Water available for Construction | 23/05/2019 | 23/05/2019 | 22/05/2019 | 22/05/2019 | 0 | TK_Complete
CCOM1310 | TT_Task | LUN to CLP for Energisation of Electrical cabinet 10GHC10GH001/2 on 30-Aug | 28/08/2019 | 02/09/2019 | 28/08/2019 | 29/08/2019 | 0 | TK_Complete
CCOM1350 | TT_Task | Energisation of Electrical Cabinet 10GHC10GH001/2 | 31/08/2019 | 05/09/2019 | 03/09/2019 | 03/09/2019 | 0 | TK_Complete
CCOM1400 | TT_Task | Cold Commissioning of Electrical Cabinet and Pump Motors | 31/08/2019 | 05/09/2019 | 04/09/2019 | 07/09/2019 | 0 | TK_Complete
CCOM1420 | TT_Task | Preparation for System Flushing | 04/09/2019 | 09/09/2019 | 04/09/2019 | 07/09/2019 | 0 | TK_Complete
CCOM1520 | TT_Task | System flushing | 31/08/2019 | 05/09/2019 | 09/09/2019 | 09/09/2019 | 0 | TK_Complete
CCOM1560 | TT_Task | System restoration post flush | 31/08/2019 | 05/09/2019 | 10/09/2019 | 14/09/2019 | 0 | TK_Complete
CCOM1590 | TT_FinMile | Handover of TOP-10GHC-01 | 12/09/2019 | 12/09/2019 | 12/09/2019 | 12/09/2019 | 0 | TK_Complete
CCOM1600 | TT_FinMile | Handover of TOP-10GHC-02 | 12/09/2019 | 12/09/2019 | 12/09/2019 | 12/09/2019 | 0 | TK_Complete
CCOM1610 | TT_FinMile | Handover of TOP-10GHC-03 | 12/09/2019 | 12/09/2019 | 12/09/2019 | 12/09/2019 | 0 | TK_Complete
CCOM1630 | TT_Task | System Commissioning | 31/08/2019 | 05/09/2019 | 16/09/2019 | 16/09/2019 | 0 | TK_Complete
CCOM3020 | TT_Task | Draining of system for finalising the tie-in works for dosing system | 31/08/2019 | 05/09/2019 | 13/11/2019 | 22/11/2019 | 0 | TK_Complete
CCOM1830 | TT_FinMile | Handover of TOP 10PGB | 31/08/2019 | 31/08/2019 | 30/09/2019 | 30/09/2019 | 0 | TK_Complete
CCOM1840 | TT_Task | Rotation checks and motor solo runs incl re-coupling in preparation for flushing | 31/08/2019 | 05/09/2019 | 30/09/2019 | 30/09/2019 | 0 | TK_Complete
CCOM1880 | TT_Task | Investigation works on elevated vibrations during motor solo runs for PGB11&amp;12AP001 | 31/08/2019 | 05/09/2019 | 02/10/2019 | 02/10/2019 | 0 | TK_Complete
CCOM1910 | TT_Task | Prep for additional grouting works for baseframe of PGB11&amp;12AP001 | 31/08/2019 | 05/09/2019 | 03/10/2019 | 03/10/2019 | 0 | TK_Complete
CCOM1930 | TT_Task | Additional grouting works for baseframe of PGB11&amp;12AP001 | 31/08/2019 | 05/09/2019 | 04/10/2019 | 04/10/2019 | 0 | TK_Complete
CCOM1990 | TT_Task | Re-testing of motor solo run after grouting | 31/08/2019 | 05/09/2019 | 09/10/2019 | 09/10/2019 | 0 | TK_Complete
CCOM2050 | TT_Task | Coupling of pump &amp; setup for initial pump operation | 31/08/2019 | 05/09/2019 | 10/10/2019 | 10/10/2019 | 0 | TK_Complete
CCOM2100 | TT_Task | Filling of baseframe with concrete and preparation for final grouting | 31/08/2019 | 05/09/2019 | 11/10/2019 | 12/10/2019 | 0 | TK_Complete
CCOM2170 | TT_Task | Curing time for concrete grouting ongoing | 31/08/2019 | 05/09/2019 | 14/10/2019 | 14/10/2019 | 0 | TK_Complete
CCOM2210 | TT_Task | Motor solo run and coupling / fist flushing operation | 31/08/2019 | 05/09/2019 | 15/10/2019 | 15/10/2019 | 0 | TK_Complete
CCOM2260 | TT_Task | System flushing | 31/08/2019 | 05/09/2019 | 16/10/2019 | 24/10/2019 | 0 | TK_Complete
CCOM2440 | TT_Task | Oil draining | 31/08/2019 | 05/09/2019 | 24/10/2019 | 28/10/2019 | 0 | TK_Complete
CCOM2590 | TT_Task | Restoration ongoing, prepare for filling | 31/08/2019 | 05/09/2019 | 29/10/2019 | 13/11/2019 | 0 | TK_Complete
CCOM3480 | TT_Task | Refilling System, adjusting flowrates (pending finalization of reinstatements) | 02/07/2020 | 07/07/2020 | 12/11/2019 | 16/11/2019 | 0 | TK_Complete
CCOM3490 | TT_Task | Refilling System, adjusting flowrates (pending finalization of reinstatements) | 02/07/2020 | 07/07/2020 | 19/11/2019 | 23/11/2019 | 0 | TK_Complete
CCOM3500 | TT_Task | System in operation, adjusting flowrates | 02/07/2020 | 07/07/2020 | 27/11/2019 | 30/11/2019 | 0 | TK_Complete
CCOM3510 | TT_Task | System in service for flushing | 02/07/2020 | 07/07/2020 | 09/12/2019 | 21/12/2019 | 0 | TK_Complete
CCOM1110 | TT_FinMile | Handover of TOP 10-CP-ST | 15/08/2019 | 15/08/2019 | 15/08/2019 | 15/08/2019 | 0 | TK_Complete
CCOM1200 | TT_Task | Loading of APs for ST | 20/08/2019 | 20/08/2019 | 20/08/2019 | 20/08/2019 | 0 | TK_Complete
CCOM1390 | TT_Task | Cold Commissioning | 03/09/2019 | 07/09/2019 | 03/09/2019 | 09/09/2019 | 0 | TK_Complete
CCOM3300 | TT_Task | cold commissioning MA-01 | 02/07/2020 | 07/07/2020 | 21/11/2019 | 30/11/2019 | 0 | TK_Complete
CCOM1130 | TT_FinMile | Handover of TOP 10MAV-01 | 16/08/2019 | 16/08/2019 | 16/08/2019 | 16/08/2019 | 0 | TK_Complete
CCOM1240 | TT_Task | Preparation for Loop checking | 21/08/2019 | 26/08/2019 | 21/08/2019 | 24/08/2019 | 0 | TK_Complete
CCOM1270 | TT_Task | Loop Checking | 26/08/2019 | 30/08/2019 | 26/08/2019 | 05/09/2019 | 0 | TK_Complete
CCOM1380 | TT_Task | Preparation for flushing | 03/09/2019 | 07/09/2019 | 03/09/2019 | 05/09/2019 | 0 | TK_Complete
CCOM1450 | TT_FinMile | Handover of TOP 10MAV-02 | 05/09/2019 | 05/09/2019 | 05/09/2019 | 05/09/2019 | 0 | TK_Complete
CCOM1455 | TT_FinMile | Handover of TOP 10MAV-03 | 05/09/2019 | 05/09/2019 | 27/03/2020 | 27/03/2020 | 0 | TK_Complete
CCOM1465 | TT_Task | Turning gear operation &amp; adjustment of oil system tosupport GT turning gear | 02/07/2020 | 07/07/2020 | 18/11/2019 | 21/12/2019 | 0 | TK_Complete
CCOM1475 | TT_Task | Topping up of main oil tank to normal operation Level | 02/07/2020 | 07/07/2020 | 18/11/2019 | 23/11/2019 | 0 | TK_Complete
CCOM1485 | TT_Task | System offline for HCO inspection | 02/07/2020 | 07/07/2020 | 06/01/2020 | 06/01/2020 | 0 | TK_Complete
CCOM1490 | TT_Task | Setup for Commissioning Oil Flushing | 31/08/2019 | 05/09/2019 | 06/09/2019 | 07/09/2019 | 0 | TK_Complete
CCOM1530 | TT_Task | Commissioning Oil flushing | 31/08/2019 | 05/09/2019 | 10/09/2019 | 13/09/2019 | 0 | TK_Complete
CCOM1580 | TT_Task | Connection of DC Lube Oil Pump for flushing | 31/08/2019 | 05/09/2019 | 12/09/2019 | 12/09/2019 | 0 | TK_Complete
CCOM1620 | TT_Task | Electrical commissioning of DC oil pump | 31/08/2019 | 05/09/2019 | 13/09/2019 | 17/09/2019 | 0 | TK_Complete
CCOM1820 | TT_Task | Preparation for installation of new feeder for MAV24AP001 | 31/08/2019 | 05/09/2019 | 30/09/2019 | 30/09/2019 | 0 | TK_Complete
CCOM1870 | TT_Task | Removal of current feeder &amp; Preparation for installation of new feeder MAV24AP001 | 31/08/2019 | 05/09/2019 | 02/10/2019 | 04/10/2019 | 0 | TK_Complete
CCOM1980 | TT_Task | Finalisation of Cabling Works for new feeder for DC Pump | 31/08/2019 | 05/09/2019 | 09/10/2019 | 12/10/2019 | 0 | TK_Complete
CCOM2160 | TT_Task | Test Run of MAV24AP001 after feeder exchange | 31/08/2019 | 05/09/2019 | 14/10/2019 | 14/10/2019 | 0 | TK_Complete
CCOM2200 | TT_Task | Preparation works for draining oil from main lube oil tank (construction activity) | 31/08/2019 | 05/09/2019 | 15/10/2019 | 15/10/2019 | 0 | TK_Complete
CCOM2250 | TT_Task | Continuation of oil draining from tank (construction) | 31/08/2019 | 05/09/2019 | 16/10/2019 | 18/10/2019 | 0 | TK_Complete
CCOM2370 | TT_Task | Preparation for inspection/cleaning works (Construction) | 21/10/2019 | 25/10/2019 | 21/10/2019 | 22/10/2019 | 0 | TK_Complete
CCOM2400 | TT_Task | Inspection of Oil tank | 31/08/2019 | 05/09/2019 | 23/10/2019 | 25/10/2019 | 0 | TK_Complete
CCOM2510 | TT_Task | Oil Tank refilling, pending cleanliness inspection | 31/08/2019 | 05/09/2019 | 28/10/2019 | 28/10/2019 | 0 | TK_Complete
CCOM2580 | TT_Task | Oil Tank cleanliness inspection | 31/08/2019 | 05/09/2019 | 29/10/2019 | 29/10/2019 | 0 | TK_Complete
CCOM2610 | TT_Task | Oil Tank refilling ongoing | 31/08/2019 | 05/09/2019 | 30/10/2019 | 31/10/2019 | 0 | TK_Complete
CCOM2670 | TT_Task | Normalization of system | 31/08/2019 | 05/09/2019 | 02/11/2019 | 02/11/2019 | 0 | TK_Complete
CCOM2730 | TT_Task | lube oil flushing ongoing | 31/08/2019 | 05/09/2019 | 04/11/2019 | 13/11/2019 | 0 | TK_Complete
CCOM2990 | TT_Task | Restoration ongoing | 31/08/2019 | 05/09/2019 | 13/11/2019 | 16/11/2019 | 0 | TK_Complete
CCOM4970 | TT_Task | System operation | 02/07/2020 | 07/07/2020 | 13/01/2020 | 18/01/2020 | 0 | TK_Complete
CCOM1430 | TT_Task | System setup for lube oil flushing | 31/08/2019 | 05/09/2019 | 05/09/2019 | 10/09/2019 | 0 | TK_Complete
CCOM1460 | TT_FinMile | Handover of TOP 10MAD | 31/08/2019 | 31/08/2019 | 06/09/2019 | 06/09/2019 | 0 | TK_Complete
CCOM2480 | TT_FinMile | Handover of TOP 10MAW | 31/08/2019 | 31/08/2019 | 26/10/2019 | 26/10/2019 | 0 | TK_Complete
CCOM3030 | TT_Task | Pneumatic valve commissioning | 31/08/2019 | 05/09/2019 | 14/11/2019 | 18/11/2019 | 0 | TK_Complete
CCOM3360 | TT_Task | Valve commissioning | 02/07/2020 | 07/07/2020 | 18/11/2019 | 30/11/2019 | 0 | TK_Complete
CCOM4980 | TT_Task | Seal steam commissioning | 02/07/2020 | 07/07/2020 | 16/01/2020 | 18/01/2020 | 0 | TK_Complete
CCOM1090 | TT_FinMile | Handover of TOP 10CP-GT | 08/08/2019 | 08/08/2019 | 08/08/2019 | 08/08/2019 | 0 | TK_Complete
CCOM1210 | TT_Task | Loading of APs for GT | 20/08/2019 | 24/08/2019 | 20/08/2019 | 22/08/2019 | 0 | TK_Complete
CCOM1340 | TT_Task | Cold Commissioning | 31/08/2019 | 05/09/2019 | 03/09/2019 | 02/10/2019 | 0 | TK_Complete
CCOM1920 | TT_Task | Engineering updates for GT system | 31/08/2019 | 05/09/2019 | 03/10/2019 | 04/10/2019 | 0 | TK_Complete
CCOM3290 | TT_Task | cold commissioning (MBP/MBA) | 02/07/2020 | 07/07/2020 | 18/11/2019 | 23/11/2019 | 0 | TK_Complete
CCOM3310 | TT_Task | cold commissioning (VGV/IGV) | 02/07/2020 | 07/07/2020 | 25/11/2019 | 30/11/2019 | 0 | TK_Complete
CCOM3320 | TT_Task | cold commissioning MBA50 | 02/07/2020 | 07/07/2020 | 09/12/2019 | 21/12/2019 | 0 | TK_Complete
CCOM1260 | TT_Task | Energisation of motor &amp; loop checks to support construction flushing | 26/08/2019 | 30/08/2019 | 26/08/2019 | 27/08/2019 | 0 | TK_Complete
CCOM2360 | TT_Task | Cold commissioning in preparation for first pressurization | 31/08/2019 | 05/09/2019 | 21/10/2019 | 29/10/2019 | 0 | TK_Complete
CCOM2560 | TT_FinMile | Handover of TOP 10MBX | 28/10/2019 | 28/10/2019 | 28/10/2019 | 28/10/2019 | 0 | TK_Complete
CCOM2790 | TT_Task | Initial pressurization of system, valve commissioning | 31/08/2019 | 05/09/2019 | 05/11/2019 | 08/11/2019 | 0 | TK_Complete
CCOM1440 | TT_Task | System setup for lube oil flushing | 31/08/2019 | 05/09/2019 | 05/09/2019 | 09/09/2019 | 0 | TK_Complete
CCOM1470 | TT_FinMile | Handover of TOP 10MBV | 31/08/2019 | 31/08/2019 | 06/09/2019 | 06/09/2019 | 0 | TK_Complete
CCOM1640 | TT_Task | Operation of lifting oil system to support construction works | 31/08/2019 | 05/09/2019 | 16/09/2019 | 19/09/2019 | 0 | TK_Complete
CCOM3410 | TT_Task | Commissioning of turning gear system | 02/07/2020 | 07/07/2020 | 21/11/2019 | 14/12/2019 | 0 | TK_Complete
CCOM3420 | TT_Task | First GT turning Gear | 02/07/2020 | 07/07/2020 | 23/11/2019 | 23/11/2019 | 0 | TK_Complete
CCOM3430 | TT_Task | System in operation for air leak test ( if required) | 02/07/2020 | 07/07/2020 | 16/12/2019 | 21/12/2019 | 0 | TK_Complete
CCOM2780 | TT_Task | IGV/VGV comissioning | 31/08/2019 | 05/09/2019 | 05/11/2019 | 08/11/2019 | 0 | TK_Complete
CCOM3100 | TT_FinMile | Handover of TOP 10MBA | 31/08/2019 | 31/08/2019 | 21/11/2019 | 21/11/2019 | 0 | TK_Complete
CCOM3380 | TT_Task | IGV/VGV | 02/07/2020 | 07/07/2020 | 13/11/2019 | 16/11/2019 | 0 | TK_Complete
CCOM3390 | TT_Task | IGV/VGV | 02/07/2020 | 07/07/2020 | 20/11/2019 | 30/11/2019 | 0 | TK_Complete
CCOM3400 | TT_Task | Commissioning of HCO system | 02/07/2020 | 07/07/2020 | 09/12/2019 | 21/12/2019 | 0 | TK_Complete
CCOM4710 | TT_Task | Commissioning of HCO system - system restored | 02/07/2020 | 07/07/2020 | 06/01/2020 | 09/01/2020 | 0 | TK_Complete
CCOM4720 | TT_Task | GT protection testing | 02/07/2020 | 07/07/2020 | 06/01/2020 | 08/01/2020 | 0 | TK_Complete
CCOM1780 | TT_FinMile | Handover of 10MBX2x | 31/08/2019 | 31/08/2019 | 29/09/2019 | 29/09/2019 | 0 | TK_Complete
CCOM3040 | TT_Task | Pneumatic valve commisioning | 31/08/2019 | 05/09/2019 | 14/11/2019 | 19/11/2019 | 0 | TK_Complete
CCOM2300 | TT_Task | Motor rotation checks | 31/08/2019 | 05/09/2019 | 17/10/2019 | 18/10/2019 | 0 | TK_Complete
CCOM2460 | TT_FinMile | Handover of TOP 10MKF | 31/08/2019 | 31/08/2019 | 25/10/2019 | 25/10/2019 | 0 | TK_Complete
CCOM2530 | TT_Task | Initial filling &amp; flushing of system | 31/08/2019 | 05/09/2019 | 28/10/2019 | 07/11/2019 | 0 | TK_Complete
CCOM2860 | TT_Task | Flushing on HOLD | 31/08/2019 | 05/09/2019 | 08/11/2019 | 13/11/2019 | 0 | TK_Complete
CCOM3440 | TT_Task | System flushing | 02/07/2020 | 07/07/2020 | 11/11/2019 | 13/11/2019 | 0 | TK_Complete
CCOM3450 | TT_Task | System flushing pending filter delivery | 02/07/2020 | 07/07/2020 | 20/11/2019 | 23/11/2019 | 0 | TK_Complete
CCOM3460 | TT_Task | System flushing pending filter delivery | 02/07/2020 | 07/07/2020 | 27/11/2019 | 30/11/2019 | 0 | TK_Complete
CCOM3470 | TT_Task | System restoration | 02/07/2020 | 07/07/2020 | 09/12/2019 | 11/12/2019 | 0 | TK_Complete
CCOM1700 | TT_Task | Prep of Pumps for Construction oil flushing | 31/08/2019 | 05/09/2019 | 20/09/2019 | 20/09/2019 | 0 | TK_Complete
CCOM1730 | TT_Task | Support prep for Construction oil flushing | 31/08/2019 | 05/09/2019 | 23/09/2019 | 26/09/2019 | 0 | TK_Complete
CCOM1760 | TT_Task | Restoration Works after Construction Flushing completion | 31/08/2019 | 05/09/2019 | 27/09/2019 | 04/10/2019 | 0 | TK_Complete
CCOM2110 | TT_FinMile | Handover of TOP 10MAX | 31/08/2019 | 31/08/2019 | 12/10/2019 | 12/10/2019 | 0 | TK_Complete
CCOM1940 | TT_FinMile | Handover of TOP 00SCB | 31/08/2019 | 31/08/2019 | 04/10/2019 | 04/10/2019 | 0 | TK_Complete
CCOM2000 | TT_Task | Initial pressurizing of compressed air skid | 31/08/2019 | 05/09/2019 | 09/10/2019 | 11/10/2019 | 0 | TK_Complete
CCOM2060 | TT_Task | Preparation for piping service test and air blow | 31/08/2019 | 05/09/2019 | 10/10/2019 | 11/10/2019 | 0 | TK_Complete
CCOM2180 | TT_Task | System operation and preparation for air blow of system piping | 31/08/2019 | 05/09/2019 | 14/10/2019 | 14/10/2019 | 0 | TK_Complete
CCOM2310 | TT_FinMile | Handover of TOP 10SCB | 31/08/2019 | 31/08/2019 | 19/10/2019 | 19/10/2019 | 0 | TK_Complete
CCOM2380 | TT_Task | Preparation for air blow out | 31/08/2019 | 05/09/2019 | 22/10/2019 | 23/10/2019 | 0 | TK_Complete
CCOM2430 | TT_Task | Initial air blow out @12.00 | 31/08/2019 | 05/09/2019 | 24/10/2019 | 25/10/2019 | 0 | TK_Complete
CCOM2550 | TT_Task | Service test completed, system normalised | 31/08/2019 | 05/09/2019 | 28/10/2019 | 31/10/2019 | 0 | TK_Complete
CCOM2220 | TT_Task | Rotation check and motor solo run for vibration check (LCA51/52AP001) | 31/08/2019 | 05/09/2019 | 15/10/2019 | 18/10/2019 | 0 | TK_Complete
CCOM3110 | TT_FinMile | Handover of TOP 10LCA | 31/08/2019 | 31/08/2019 | 28/11/2019 | 28/11/2019 | 0 | TK_Complete
CCOM3330 | TT_Task | cold commissioning, preparation for oil flushing (pending TOP) | 02/07/2020 | 07/07/2020 | 20/11/2019 | 23/11/2019 | 0 | TK_Complete
CCOM3340 | TT_Task | cold commissioning, preparation for oil flushing (pending TOP) | 02/07/2020 | 07/07/2020 | 27/11/2019 | 30/11/2019 | 0 | TK_Complete
CCOM3350 | TT_Task | System in service for flushing | 02/07/2020 | 07/07/2020 | 09/12/2019 | 13/12/2019 | 0 | TK_Complete
CCOM2740 | TT_FinMile | Handover of TOP 10LAB | 31/08/2019 | 31/08/2019 | 04/11/2019 | 04/11/2019 | 0 | TK_Complete
CCOM2800 | TT_Task | Cold commissioning | 31/08/2019 | 05/09/2019 | 05/11/2019 | 30/11/2019 | 0 | TK_Complete
CCOM2840 | TT_Task | Check of interlocks, commissioning of components | 31/08/2019 | 05/09/2019 | 07/11/2019 | 11/11/2019 | 0 | TK_Complete
CCOM2920 | TT_Task | Blow out of sysem branch lines, service test | 31/08/2019 | 05/09/2019 | 12/11/2019 | 13/11/2019 | 0 | TK_Complete
CCOM3050 | TT_Mile | System in service | 31/08/2019 | 31/08/2019 | 14/11/2019 | 14/11/2019 | 0 | TK_Complete
CCOM2910 | TT_FinMile | Handover of TOP 10QFB-01 | 31/08/2019 | 31/08/2019 | 11/11/2019 | 11/11/2019 | 0 | TK_Complete
CCOM3520 | TT_Task | system commissioning, leakage check and air blow | 02/07/2020 | 07/07/2020 | 31/10/2019 | 02/11/2019 | 0 | TK_Complete
CCOM3530 | TT_Task | system commissioning, leakage check and air blow | 02/07/2020 | 07/07/2020 | 12/11/2019 | 16/11/2019 | 0 | TK_Complete
CCOM3120 | TT_FinMile | Handover of TOP 10QFB-02 | 02/09/2019 | 02/09/2019 | 05/12/2019 | 05/12/2019 | 0 | TK_Complete
CCOM3540 | TT_Task | system commissioning, leakage check and air blow (pending TOP) | 02/07/2020 | 07/07/2020 | 11/11/2019 | 23/11/2019 | 0 | TK_Complete
CCOM3550 | TT_Task | system commissioning, leakage check and air blow (pending TOP) | 02/07/2020 | 07/07/2020 | 26/11/2019 | 30/11/2019 | 0 | TK_Complete
CCOM3560 | TT_Task | System blow out | 02/07/2020 | 07/07/2020 | 09/12/2019 | 10/12/2019 | 0 | TK_Complete
CCOM3130 | TT_FinMile | Handover of TOP 10QFB-03 | 02/07/2020 | 02/07/2020 | 12/02/2020 | 12/02/2020 | 0 | TK_Complete
CCOM1120 | TT_FinMile | Handover of TOP 10BT-01 | 16/08/2019 | 16/08/2019 | 16/08/2019 | 16/08/2019 | 0 | TK_Complete
CCOM1160 | TT_Task | Acid Filling UBA-0104 | 20/08/2019 | 20/08/2019 | 20/08/2019 | 20/08/2019 | 0 | TK_Complete
CCOM1230 | TT_Task | Battery charging (First Bank) | 21/08/2019 | 26/08/2019 | 21/08/2019 | 22/08/2019 | 0 | TK_Complete
CCOM1250 | TT_Task | Preparation for Battery charging (Second Bank) | 26/08/2019 | 30/08/2019 | 26/08/2019 | 26/08/2019 | 0 | TK_Complete
CCOM1290 | TT_Task | Battery charging (Second Bank) | 27/08/2019 | 28/08/2019 | 27/08/2019 | 28/08/2019 | 0 | TK_Complete
CCOM1950 | TT_Task | Discharge test from 1st Bank | 31/08/2019 | 05/09/2019 | 09/10/2019 | 09/10/2019 | 0 | TK_Complete
CCOM2020 | TT_Task | Preparation for 2nd Discharge test | 31/08/2019 | 05/09/2019 | 10/10/2019 | 10/10/2019 | 0 | TK_Complete
CCOM2080 | TT_Task | 2nd Discharge test | 31/08/2019 | 05/09/2019 | 11/10/2019 | 16/10/2019 | 0 | TK_Complete
CCOM1050 | TT_FinMile | Handover of TOP 10BBA | 19/07/2019 | 19/07/2019 | 19/07/2019 | 19/07/2019 | 0 | TK_Complete
CCOM1060 | TT_Task | Cold Commissioning | 29/07/2019 | 02/08/2019 | 29/07/2019 | 24/08/2019 | 0 | TK_Complete
CCOM1280 | TT_Task | Initial Interlock testing | 26/08/2019 | 30/08/2019 | 26/08/2019 | 28/08/2019 | 0 | TK_Complete
CCOM1330 | TT_Task | Interlock testing with CLP | 31/08/2019 | 05/09/2019 | 30/08/2019 | 30/08/2019 | 0 | TK_Complete
CCOM1360 | TT_Task | Feeder commissioning | 03/09/2019 | 07/09/2019 | 03/09/2019 | 10/09/2019 | 0 | TK_Complete
CCOM1510 | TT_FinMile | Energisation of BMT01 | 31/08/2019 | 31/08/2019 | 09/09/2019 | 09/09/2019 | 0 | TK_Complete
CCOM2340 | TT_Task | Feeder commissioning - 10MBU25AP001 | 31/08/2019 | 05/09/2019 | 21/10/2019 | 25/10/2019 | 0 | TK_Complete
CCOM2500 | TT_Task | Feeder commissioning - 10LCB11/12AP001 | 31/08/2019 | 05/09/2019 | 28/10/2019 | 04/11/2019 | 0 | TK_Complete
CCOM2640 | TT_Task | Rotation check - 10MBU25AP001 | 31/08/2019 | 05/09/2019 | 31/10/2019 | 31/10/2019 | 0 | TK_Complete
CCOM2770 | TT_Task | De-energization of BBA for LCAL works inside MV room | 31/08/2019 | 05/09/2019 | 05/11/2019 | 12/11/2019 | 0 | TK_Complete
CCOM2970 | TT_Task | Primary injection start planned at 9am | 31/08/2019 | 05/09/2019 | 13/11/2019 | 14/11/2019 | 0 | TK_Complete
CCOM3070 | TT_Task | MV feeder commissioning | 31/08/2019 | 05/09/2019 | 15/11/2019 | 20/11/2019 | 0 | TK_Complete
CCOM3210 | TT_Task | Feeder commissioning 10LAC11/12AP001,10PAC11/12AP001 | 02/07/2020 | 07/07/2020 | 18/11/2019 | 30/11/2019 | 0 | TK_Complete
CCOM3240 | TT_Task | Supporting MV motor test runs | 02/07/2020 | 07/07/2020 | 09/12/2019 | 14/12/2019 | 0 | TK_Complete
CCOM4570 | TT_Task | De-energization of BBB for civil completion works inside room 206 | 02/07/2020 | 07/07/2020 | 06/01/2020 | 07/01/2020 | 0 | TK_Complete
CCOM4580 | TT_Task | Re-energization of BBB busbar | 02/07/2020 | 07/07/2020 | 08/01/2020 | 08/01/2020 | 0 | TK_Complete
CCOM1150 | TT_FinMile | Handover of TOP 10CP-BOP-01 | 17/08/2019 | 17/08/2019 | 17/08/2019 | 17/08/2019 | 0 | TK_Complete
CCOM1550 | TT_Task | Cold Commissioning | 31/08/2019 | 05/09/2019 | 10/09/2019 | 28/09/2019 | 0 | TK_Complete
CCOM1850 | TT_Task | Cold Commissioning - PGB Signal checks | 31/08/2019 | 05/09/2019 | 30/09/2019 | 04/10/2019 | 0 | TK_Complete
CCOM3570 | TT_Task | I&amp;C Commissioning EK,EG and PA System | 02/07/2020 | 07/07/2020 | 16/12/2019 | 21/12/2019 | 0 | TK_Complete
CCOM4600 | TT_Task | I&amp;C Commissioning EK,EG and PA System | 02/07/2020 | 07/07/2020 | 06/01/2020 | 11/01/2020 | 0 | TK_Complete
CCOM4850 | TT_Task | I&amp;C Commissioning EK,EG and PA System | 02/07/2020 | 07/07/2020 | 13/01/2020 | 16/01/2020 | 0 | TK_Complete
CCOM1650 | TT_FinMile | Handover of TOP 10BFT-01 | 31/08/2019 | 31/08/2019 | 18/09/2019 | 18/09/2019 | 0 | TK_Complete
CCOM1660 | TT_Task | Commissioning Works | 31/08/2019 | 05/09/2019 | 18/09/2019 | 23/09/2019 | 0 | TK_Complete
CCOM1680 | TT_Task | Energization | 31/08/2019 | 05/09/2019 | 19/09/2019 | 24/09/2019 | 0 | TK_Complete
CCOM1300 | TT_FinMile | Handover of TOP 10BFT-03 | 31/08/2019 | 31/08/2019 | 28/08/2019 | 28/08/2019 | 0 | TK_Complete
CCOM1810 | TT_Task | Prep for Energisation (Final checks) | 31/08/2019 | 05/09/2019 | 30/09/2019 | 30/09/2019 | 0 | TK_Complete
CCOM1860 | TT_Task | Energisation | 31/08/2019 | 05/09/2019 | 02/10/2019 | 05/10/2019 | 0 | TK_Complete
CCOM1320 | TT_FinMile | Handover of TOP 10BFT-02 | 31/08/2019 | 31/08/2019 | 29/08/2019 | 29/08/2019 | 0 | TK_Complete
CCOM2030 | TT_Task | Preparation for Energization | 31/08/2019 | 05/09/2019 | 10/10/2019 | 10/10/2019 | 0 | TK_Complete
CCOM2090 | TT_Task | Energization | 31/08/2019 | 05/09/2019 | 11/10/2019 | 16/10/2019 | 0 | TK_Complete
CCOM2150 | TT_Task | Review of Interlcok with CLP / ARUP | 31/08/2019 | 05/09/2019 | 14/10/2019 | 14/10/2019 | 0 | TK_Complete
CCOM2190 | TT_Task | Energization of BFT04 &amp; BFT05 | 31/08/2019 | 05/09/2019 | 15/10/2019 | 15/10/2019 | 0 | TK_Complete
CCOM2240 | TT_Task | De-Energization of BFT04 &amp; BFT05 for completion of | 31/08/2019 | 05/09/2019 | 16/10/2019 | 16/10/2019 | 0 | TK_Complete
CCOM2280 | TT_Task | BFT04 / BFT05 Energized | 31/08/2019 | 05/09/2019 | 17/10/2019 | 17/10/2019 | 0 | TK_Complete
CCOM2820 | TT_FinMile | Handover of TOP 10BHV-01 | 31/08/2019 | 31/08/2019 | 07/11/2019 | 07/11/2019 | 0 | TK_Complete
CCOM1070 | TT_FinMile | Handover of TOP 10BF-01 | 29/07/2019 | 29/07/2019 | 29/07/2019 | 29/07/2019 | 0 | TK_Complete
CCOM1080 | TT_FinMile | Handover of TOP-10BF-01 | 29/07/2019 | 29/07/2019 | 29/07/2019 | 29/07/2019 | 0 | TK_Complete
CCOM1190 | TT_Task | System Commissioning &amp; Energisation of Components (UBA-0204,0205) | 20/08/2019 | 24/08/2019 | 20/08/2019 | 23/08/2019 | 0 | TK_Complete
CCOM1370 | TT_Task | Prep work for LV Board Energization via BMT01 | 03/09/2019 | 07/09/2019 | 03/09/2019 | 05/09/2019 | 0 | TK_Complete
CCOM1480 | TT_FinMile | LV Board ready for energisation via BMT01 | 31/08/2019 | 31/08/2019 | 06/09/2019 | 06/09/2019 | 0 | TK_Complete
CCOM1540 | TT_FinMile | BMT01 Energized | 31/08/2019 | 31/08/2019 | 10/09/2019 | 10/09/2019 | 0 | TK_Complete
CCOM3250 | TT_Task | Energisation of first components upon requirements | 18/11/2019 | 21/12/2019 | 18/11/2019 | 21/12/2019 | 0 | TK_Complete
CCOM4590 | TT_Task | Energisation of first components upon requirements | 02/07/2020 | 07/07/2020 | 06/01/2020 | 11/01/2020 | 0 | TK_Complete
CCOM1140 | TT_FinMile | Handover of TOP 10BAT | 31/08/2019 | 31/08/2019 | 17/08/2019 | 17/08/2019 | 0 | TK_Complete
CCOM1670 | TT_Task | Partial draining of oil for inspection at bushings | 31/08/2019 | 05/09/2019 | 19/09/2019 | 19/09/2019 | 0 | TK_Complete
CCOM1690 | TT_Task | Inspection of Internal bushing connection to Phase B | 31/08/2019 | 05/09/2019 | 20/09/2019 | 21/09/2019 | 0 | TK_Complete
CCOM1710 | TT_Task | Preparation for rectification works | 31/08/2019 | 05/09/2019 | 23/09/2019 | 27/09/2019 | 0 | TK_Complete
CCOM1740 | TT_Task | Inspection with Client Consultant Engineer | 31/08/2019 | 05/09/2019 | 25/09/2019 | 28/09/2019 | 0 | TK_Complete
CCOM1790 | TT_Task | FRA Test with STGZ | 31/08/2019 | 05/09/2019 | 30/09/2019 | 30/09/2019 | 0 | TK_Complete
CCOM1890 | TT_Task | Prep Work - awaiting material delivery confirmation) | 31/08/2019 | 05/09/2019 | 02/10/2019 | 09/10/2019 | 0 | TK_Complete
CCOM2010 | TT_Task | Start Rectification Works - exchange of insulation boards and installaiton of spacer | 31/08/2019 | 05/09/2019 | 10/10/2019 | 10/10/2019 | 0 | TK_Complete
CCOM2070 | TT_Task | Exchange of flange on neutral bushing &amp; preparation for transformer testing prior to final close up | 31/08/2019 | 05/09/2019 | 11/10/2019 | 12/10/2019 | 0 | TK_Complete
CCOM2130 | TT_Task | Vacuum pulling ongoing in preparation for oil filling | 31/08/2019 | 05/09/2019 | 14/10/2019 | 16/10/2019 | 0 | TK_Complete
CCOM2270 | TT_Task | 24hr vacuum hold prior to oil filling | 31/08/2019 | 05/09/2019 | 17/10/2019 | 18/10/2019 | 0 | TK_Complete
CCOM2330 | TT_Task | Oil Circulation and sampling | 31/08/2019 | 05/09/2019 | 21/10/2019 | 23/10/2019 | 0 | TK_Complete
CCOM2410 | TT_Task | Cool down of oil in preparation for testing - Dirana test scheduled | 31/08/2019 | 05/09/2019 | 24/10/2019 | 25/10/2019 | 0 | TK_Complete
CCOM2490 | TT_Task | Continuation of transformer testing - Winding resistance test | 31/08/2019 | 05/09/2019 | 28/10/2019 | 28/10/2019 | 0 | TK_Complete
CCOM2570 | TT_Task | Dirana Test | 31/08/2019 | 05/09/2019 | 29/10/2019 | 30/10/2019 | 0 | TK_Complete
CCOM2630 | TT_Task | Signal checks | 31/08/2019 | 05/09/2019 | 30/10/2019 | 02/11/2019 | 0 | TK_Complete
CCOM2700 | TT_Task | Finalization of commissioning | 31/08/2019 | 05/09/2019 | 04/11/2019 | 04/11/2019 | 0 | TK_Complete
CCOM2750 | TT_Task | Preparation for primary injection test | 31/08/2019 | 05/09/2019 | 05/11/2019 | 09/11/2019 | 0 | TK_Complete
CCOM2870 | TT_Task | Final check for readiness | 31/08/2019 | 05/09/2019 | 11/11/2019 | 11/11/2019 | 0 | TK_Complete
CCOM2930 | TT_Task | Ready for Primary injection test | 31/08/2019 | 05/09/2019 | 12/11/2019 | 12/11/2019 | 0 | TK_Complete
CCOM2950 | TT_Task | Primary injection planned at 9am | 31/08/2019 | 05/09/2019 | 13/11/2019 | 13/11/2019 | 0 | TK_Complete
CCOM3060 | TT_Task | Signal checks oil analyzer (DGA) | 31/08/2019 | 05/09/2019 | 15/11/2019 | 19/11/2019 | 0 | TK_Complete
CCOM3065 | TT_Task | 400V Injection from GIS side (pending release from CLP) | 02/07/2020 | 07/07/2020 | 18/11/2019 | 19/11/2019 | 0 | TK_Complete
CCOM3075 | TT_Task | final check for readiness for BE / walkdown | 02/07/2020 | 07/07/2020 | 28/11/2019 | 29/11/2019 | 0 | TK_Complete
CCOM3085 | TT_Task | Outage works | 02/07/2020 | 07/07/2020 | 11/12/2019 | 21/12/2019 | 0 | TK_Complete
CCOM3140 | TT_Task | DGA Signal exchange CCR-LDC | 02/07/2020 | 07/07/2020 | 19/11/2019 | 21/11/2019 | 0 | TK_Complete
CCOM3150 | TT_Task | Interlock/Intertrip for BE | 19/11/2019 | 23/11/2019 | 20/11/2019 | 22/11/2019 | 0 | TK_Complete
CCOM3160 | TT_Task | Re-Energization | 02/07/2020 | 07/07/2020 | 14/12/2019 | 15/12/2019 | 0 | TK_Complete
CCOM3170 | TT_Task | Re-Energization | 02/07/2020 | 07/07/2020 | 21/12/2019 | 22/12/2019 | 0 | TK_Complete
CCOM3190 | TT_Task | final check for readiness for BE | 02/07/2020 | 07/07/2020 | 21/11/2019 | 22/11/2019 | 0 | TK_Complete
CCOM1100 | TT_FinMile | Handover of TOP 10CHA | 31/08/2019 | 31/08/2019 | 12/08/2019 | 12/08/2019 | 0 | TK_Complete
CCOM1750 | TT_Task | Cold Commissioning (Software loading) | 26/09/2019 | 02/10/2019 | 26/09/2019 | 30/09/2019 | 0 | TK_Complete
CCOM1800 | TT_Task | Preparation for Interlock testing | 31/08/2019 | 05/09/2019 | 30/09/2019 | 02/10/2019 | 0 | TK_Complete
CCOM1900 | TT_Task | Interlock testing &amp; prep for sec injection | 31/08/2019 | 05/09/2019 | 03/10/2019 | 04/10/2019 | 0 | TK_Complete
CCOM1960 | TT_Task | Interlock testing &amp; sec injection | 31/08/2019 | 05/09/2019 | 09/10/2019 | 18/10/2019 | 0 | TK_Complete
CCOM2350 | TT_Task | Signal exchange SCB | 31/08/2019 | 05/09/2019 | 21/10/2019 | 21/10/2019 | 0 | TK_Complete
CCOM2890 | TT_Task | Preparation for primary injection test | 31/08/2019 | 05/09/2019 | 11/11/2019 | 12/11/2019 | 0 | TK_Complete
CCOM3000 | TT_Task | Primary injection test | 31/08/2019 | 05/09/2019 | 13/11/2019 | 14/11/2019 | 0 | TK_Complete
CCOM3080 | TT_Task | Implementing requested changes from CLP | 31/08/2019 | 05/09/2019 | 15/11/2019 | 19/11/2019 | 0 | TK_Complete
CCOM3270 | TT_Task | Interlock/Intertrip for BE | 02/07/2020 | 07/07/2020 | 18/11/2019 | 23/11/2019 | 0 | TK_Complete
CCOM1770 | TT_FinMile | Handover of TOP 10BA-01 | 31/08/2019 | 31/08/2019 | 29/09/2019 | 29/09/2019 | 0 | TK_Complete
CCOM2690 | TT_FinMile | Handover of TOP 10BA-02 | 31/08/2019 | 31/08/2019 | 04/11/2019 | 04/11/2019 | 0 | TK_Complete
CCOM1500 | TT_FinMile | Handover of TOP 10BBT | 31/08/2019 | 31/08/2019 | 07/09/2019 | 07/09/2019 | 0 | TK_Complete
CCOM2390 | TT_Task | Fans/Pumps cold commissioning | 31/08/2019 | 05/09/2019 | 23/10/2019 | 23/10/2019 | 0 | TK_Complete
CCOM2420 | TT_Task | Signal checks | 31/08/2019 | 05/09/2019 | 24/10/2019 | 31/10/2019 | 0 | TK_Complete
CCOM2650 | TT_Task | Commissioning test | 31/08/2019 | 05/09/2019 | 01/11/2019 | 02/11/2019 | 0 | TK_Complete
CCOM2710 | TT_Task | Finalization of Commissioning | 31/08/2019 | 05/09/2019 | 04/11/2019 | 04/11/2019 | 0 | TK_Complete
CCOM2760 | TT_Task | Preparation for primary injection test | 31/08/2019 | 05/09/2019 | 05/11/2019 | 09/11/2019 | 0 | TK_Complete
CCOM2880 | TT_Task | Final check for readiness | 31/08/2019 | 05/09/2019 | 11/11/2019 | 11/11/2019 | 0 | TK_Complete
CCOM2940 | TT_Task | Ready for Primary injection test | 31/08/2019 | 05/09/2019 | 12/11/2019 | 12/11/2019 | 0 | TK_Complete
CCOM2960 | TT_Task | Primary injection test planned at 9am | 31/08/2019 | 05/09/2019 | 13/11/2019 | 13/11/2019 | 0 | TK_Complete
CCOM3180 | TT_Task | 400V Injection from GIS side (pending release from CLP) | 02/07/2020 | 07/07/2020 | 18/11/2019 | 19/11/2019 | 0 | TK_Complete
CCOM3200 | TT_Task | final check for readiness for BE | 02/07/2020 | 07/07/2020 | 21/11/2019 | 22/11/2019 | 0 | TK_Complete
CCOM3220 | TT_Task | final check for readiness for BE / walkdown | 02/07/2020 | 07/07/2020 | 28/11/2019 | 29/11/2019 | 0 | TK_Complete
CCOM3230 | TT_Task | Outage works | 02/07/2020 | 07/07/2020 | 11/12/2019 | 21/12/2019 | 0 | TK_Complete
CCOM2450 | TT_FinMile | Handover of TOP 10CJT | 31/08/2019 | 31/08/2019 | 24/10/2019 | 24/10/2019 | 0 | TK_Complete
CCOM2520 | TT_Task | Cold commissioning | 31/08/2019 | 05/09/2019 | 28/10/2019 | 31/10/2019 | 0 | TK_Complete
CCOM3010 | TT_Task | Cold commissioning - primary injection test | 31/08/2019 | 05/09/2019 | 13/11/2019 | 16/11/2019 | 0 | TK_Complete
CCOM4860 | TT_Task | First SFC test runs | 02/07/2020 | 07/07/2020 | 15/01/2020 | 16/01/2020 | 0 | TK_Complete
CCOM2470 | TT_FinMile | Handover of TOP 10MKC | 31/08/2019 | 31/08/2019 | 25/10/2019 | 25/10/2019 | 0 | TK_Complete
CCOM2600 | TT_Task | Cold comm - energization of cabinet | 31/08/2019 | 05/09/2019 | 30/10/2019 | 01/11/2019 | 0 | TK_Complete
CCOM2660 | TT_Task | Cold comm - isolation test, ratio test | 31/08/2019 | 05/09/2019 | 02/11/2019 | 02/11/2019 | 0 | TK_Complete
CCOM2720 | TT_Task | Cold comm - current trafo test, voltage trafo test | 31/08/2019 | 05/09/2019 | 04/11/2019 | 06/11/2019 | 0 | TK_Complete
CCOM2830 | TT_Task | Finalizing cold comm - torquing of connections | 31/08/2019 | 05/09/2019 | 07/11/2019 | 07/11/2019 | 0 | TK_Complete
CCOM2850 | TT_Task | Ready for primary injection test | 31/08/2019 | 05/09/2019 | 08/11/2019 | 12/11/2019 | 0 | TK_Complete
CCOM2980 | TT_Task | Primary injection test planned at 9am | 31/08/2019 | 05/09/2019 | 13/11/2019 | 14/11/2019 | 0 | TK_Complete
CCOM2320 | TT_FinMile | Handover of TOP 10CKA | 31/08/2019 | 31/08/2019 | 20/10/2019 | 20/10/2019 | 0 | TK_Complete
CCOM3280 | TT_Task | CLP Training on the job &amp; commissioning of CKA-03 | 02/07/2020 | 07/07/2020 | 18/11/2019 | 18/11/2019 | 0 | TK_Complete
A4270 | TT_Task | Back Engergization | 01/06/2021 | 07/06/2021 | 01/12/2019 | 01/12/2019 | 0 | TK_Complete
A4280 | TT_FinMile | Back Engergization Achieved | 01/06/2021 | 01/06/2021 | 01/12/2019 | 01/12/2019 | 0 | TK_Complete
CCOM2680 | TT_FinMile | Handover of TOP 10SAM30 | 31/08/2019 | 31/08/2019 | 02/11/2019 | 02/11/2019 | 0 | TK_Complete
CCOM2900 | TT_Task | Cold commissioning, rotation checks, commossioning of components | 31/08/2019 | 05/09/2019 | 11/11/2019 | 14/11/2019 | 0 | TK_Complete
CCOM1010 | TT_FinMile | Handover of TOP 10CR-02 | 04/07/2019 | 04/07/2019 | 04/07/2019 | 04/07/2019 | 0 | TK_Complete
CCOM1020 | TT_FinMile | Handover of TOP-10CR-02 | 04/07/2019 | 04/07/2019 | 04/07/2019 | 04/07/2019 | 0 | TK_Complete
CCOM1030 | TT_FinMile | Handover of TOP 10CR-01 | 15/07/2019 | 15/07/2019 | 15/07/2019 | 15/07/2019 | 0 | TK_Complete
CCOM1040 | TT_FinMile | Handover of TOP-10CR-01 | 15/07/2019 | 15/07/2019 | 15/07/2019 | 15/07/2019 | 0 | TK_Complete
CCOM1170 | TT_Task | Server Commissioning CCR (CRY-01) | 20/08/2019 | 24/08/2019 | 20/08/2019 | 23/08/2019 | 0 | TK_Complete
CCOM1180 | TT_Task | Server Commissioning LCR UBA-0202 (CRY-02) | 20/08/2019 | 24/08/2019 | 20/08/2019 | 23/08/2019 | 0 | TK_Complete
CCOM1220 | TT_Task | Simulator Commissioning (CRQ) | 20/08/2019 | 24/08/2019 | 20/08/2019 | 23/08/2019 | 0 | TK_Complete
CCOM1410 | TT_FinMile | Handover of TOP 10BF-02 | 31/08/2019 | 31/08/2019 | 04/09/2019 | 04/09/2019 | 0 | TK_Complete
CCOM1570 | TT_Task | Initial commissioning of LV Busbars | 31/08/2019 | 05/09/2019 | 12/09/2019 | 19/09/2019 | 0 | TK_Complete
CCOM1720 | TT_Task | Commissioning of LV Busbars | 31/08/2019 | 05/09/2019 | 23/09/2019 | 27/09/2019 | 0 | TK_Complete
CCOM1970 | TT_Task | Feeder commissioning - BFTGT002 | 31/08/2019 | 05/09/2019 | 09/10/2019 | 14/10/2019 | 0 | TK_Complete
CCOM2140 | TT_Task | Testing of automatic transfer system (ATS) | 31/08/2019 | 05/09/2019 | 14/10/2019 | 17/10/2019 | 0 | TK_Complete
CCOM3260 | TT_Task | Energisation of first components upon requirements | 18/11/2019 | 21/12/2019 | 18/11/2019 | 21/12/2019 | 0 | TK_Complete
CCOM2040 | TT_Task | Preparation for system flushing, rotation check of water transfer pumps | 31/08/2019 | 05/09/2019 | 10/10/2019 | 14/10/2019 | 0 | TK_Complete
CCOM2120 | TT_FinMile | Handover of TOP 10MBU-01 | 31/08/2019 | 31/08/2019 | 12/10/2019 | 12/10/2019 | 0 | TK_Complete
CCOM2230 | TT_Task | Finalisation of piping by Wai Leun to complete last flushing step | 31/08/2019 | 05/09/2019 | 16/10/2019 | 16/10/2019 | 0 | TK_Complete
CCOM2290 | TT_Task | System flushing (discharge piping) | 31/08/2019 | 05/09/2019 | 17/10/2019 | 18/10/2019 | 0 | TK_Complete
CCOM2540 | TT_Task | Borescope inspection of piping system | 31/08/2019 | 05/09/2019 | 28/10/2019 | 29/10/2019 | 0 | TK_Complete
CCOM2620 | TT_Task | Blow out of gas ring lines | 31/08/2019 | 05/09/2019 | 30/10/2019 | 04/11/2019 | 0 | TK_Complete
CCOM2810 | TT_Task | Valve commissioning | 31/08/2019 | 05/09/2019 | 06/11/2019 | 11/11/2019 | 0 | TK_Complete
CCOM3090 | TT_FinMile | Handover of TOP 10MBP | 31/08/2019 | 31/08/2019 | 21/11/2019 | 21/11/2019 | 0 | TK_Complete
CCOM3370 | TT_Task | Valve commissioning | 02/07/2020 | 07/07/2020 | 13/11/2019 | 30/11/2019 | 0 | TK_Complete
CCOM4940 | TT_Task | System line up | 02/07/2020 | 07/07/2020 | 15/01/2020 | 17/01/2020 | 0 | TK_Complete
CCOM4930 | TT_Task | Ammonia dosing system line up and chemical filling | 02/07/2020 | 07/07/2020 | 13/01/2020 | 15/01/2020 | 0 | TK_Complete
CCOM4470 | TT_Task | Outage initiation post chem clean, setup of all system isolations | 02/07/2020 | 07/07/2020 | 19/12/2019 | 21/12/2019 | 0 | TK_Complete
CCOM5100 | TT_Task | Preparation and line up of all systems for first fire | 02/07/2020 | 07/07/2020 | 17/01/2020 | 19/01/2020 | 0 | TK_Complete
CCOM4440 | TT_Task | cold commissioning of hydraulic flaps incl system flushing | 02/07/2020 | 07/07/2020 | 17/12/2019 | 21/12/2019 | 0 | TK_Complete
CCOM4450 | TT_Task | preparation for filling of PAB system | 02/07/2020 | 07/07/2020 | 19/12/2019 | 21/12/2019 | 0 | TK_Complete
CCOM4790 | TT_Task | preparation for filling of PAB system at condenser | 02/07/2020 | 07/07/2020 | 07/01/2020 | 08/01/2020 | 0 | TK_Complete
CCOM4800 | TT_Task | system final line up &amp; first pump operation | 02/07/2020 | 07/07/2020 | 09/01/2020 | 11/01/2020 | 0 | TK_Complete
CCOM5080 | TT_Task | PAB System commissioning | 02/07/2020 | 07/07/2020 | 14/01/2020 | 18/01/2020 | 0 | TK_Complete
CCOM5090 | TT_Task | PAB System - First 2 pump operation | 02/07/2020 | 07/07/2020 | 16/01/2020 | 16/01/2020 | 0 | TK_Complete
CCOM4250 | TT_Task | Energization of cabinets/components and I&amp;C checks | 02/07/2020 | 07/07/2020 | 09/12/2019 | 14/12/2019 | 0 | TK_Complete
CCOM4420 | TT_Task | cold commissioning of intake system | 02/07/2020 | 07/07/2020 | 16/12/2019 | 21/12/2019 | 0 | TK_Complete
CCOM4430 | TT_Task | testing of PAC chamber stoplog - dry and wet testing | 02/07/2020 | 07/07/2020 | 18/12/2019 | 21/12/2019 | 0 | TK_Complete
CCOM4760 | TT_Task | cold commissioning of intake system | 02/07/2020 | 07/07/2020 | 06/01/2020 | 11/01/2020 | 0 | TK_Complete
CCOM4770 | TT_Task | flooding of cooling water intake structure and removal of stoplogs | 02/07/2020 | 07/07/2020 | 07/01/2020 | 08/01/2020 | 0 | TK_Complete
CCOM4780 | TT_Task | wet commissioning of intake systems | 02/07/2020 | 07/07/2020 | 08/01/2020 | 11/01/2020 | 0 | TK_Complete
CCOM5070 | TT_Task | wet commissioning of intake systems | 02/07/2020 | 07/07/2020 | 15/01/2020 | 18/01/2020 | 0 | TK_Complete
CCOM4320 | TT_Task | Support motor solo runs in fuel oil pumphouse | 02/07/2020 | 07/07/2020 | 09/12/2019 | 12/12/2019 | 0 | TK_Complete
CCOM4410 | TT_Task | Finalisation of temporary piping works and system line up for flushing | 02/07/2020 | 07/07/2020 | 18/12/2019 | 21/12/2019 | 0 | TK_Complete
CCOM4750 | TT_Task | Finalisation of temporary piping works and system line up for flushing (after FSD inspection) | 02/07/2020 | 07/07/2020 | 09/01/2020 | 11/01/2020 | 0 | TK_Complete
CCOM5060 | TT_Task | Finalisation of temporary piping works and system line up for flushing (after FSD inspection) | 02/07/2020 | 07/07/2020 | 16/01/2020 | 18/01/2020 | 0 | TK_Complete
CCOM3710 | TT_Task | Filling, Service test | 02/07/2020 | 07/07/2020 | 29/11/2019 | 30/11/2019 | 0 | TK_Complete
CCOM4270 | TT_Task | Flushing/Chem clean as per schedule | 02/07/2020 | 07/07/2020 | 10/12/2019 | 12/12/2019 | 0 | TK_Complete
CCOM4480 | TT_Task | Chem clean as per schedule | 02/07/2020 | 07/07/2020 | 17/12/2019 | 18/12/2019 | 0 | TK_Complete
CCOM4490 | TT_Task | Steam rinsing | 02/07/2020 | 07/07/2020 | 17/12/2019 | 18/12/2019 | 0 | TK_Complete
CCOM4500 | TT_Task | initial inspections post chem clean | 02/07/2020 | 07/07/2020 | 19/12/2019 | 21/12/2019 | 0 | TK_Complete
CCOM3700 | TT_Task | Spray deluge test for UBE/UBF/UBG | 02/07/2020 | 07/07/2020 | 18/11/2019 | 18/11/2019 | 0 | TK_Complete
CCOM4080 | TT_Task | final paint check and touch up where required | 02/07/2020 | 07/07/2020 | 25/11/2019 | 26/11/2019 | 0 | TK_Complete
CCOM3690 | TT_Task | Hot commissioning of Aux Boilers and safety valve testing | 02/07/2020 | 07/07/2020 | 18/11/2019 | 23/11/2019 | 0 | TK_Complete
CCOM4070 | TT_Task | ready for operation, pending operational licence | 02/07/2020 | 07/07/2020 | 25/11/2019 | 30/11/2019 | 0 | TK_Complete
CCOM4260 | TT_Task | Operation for heating up during chemical clean | 02/07/2020 | 07/07/2020 | 12/12/2019 | 14/12/2019 | 0 | TK_Complete
CCOM4460 | TT_Task | Operation for heating up during chemical clean | 02/07/2020 | 07/07/2020 | 16/12/2019 | 21/12/2019 | 0 | TK_Complete
CCOM4170 | TT_Task | High velocity flushing as per schedule incl heat up and Chem Clean | 02/07/2020 | 07/07/2020 | 09/12/2019 | 18/12/2019 | 0 | TK_Complete
CCOM4340 | TT_Task | Chemical cleaning as per schedule | 02/07/2020 | 07/07/2020 | 16/12/2019 | 18/12/2019 | 0 | TK_Complete
CCOM4620 | TT_Task | Inspections post chem clean | 02/07/2020 | 07/07/2020 | 06/01/2020 | 09/01/2020 | 0 | TK_Complete
CCOM4640 | TT_Task | I&amp;C commissionin of components restored after chem clean | 02/07/2020 | 07/07/2020 | 06/01/2020 | 11/01/2020 | 0 | TK_Complete
CCOM4670 | TT_Task | System line up for filling | 02/07/2020 | 07/07/2020 | 09/01/2020 | 11/01/2020 | 0 | TK_Complete
CCOM4880 | TT_Task | System line up for filling (with QCD) | 02/07/2020 | 07/07/2020 | 13/01/2020 | 15/01/2020 | 0 | TK_Complete
CCOM4900 | TT_Task | Re-filling of HRSG/Water steam | 02/07/2020 | 07/07/2020 | 16/01/2020 | 18/01/2020 | 0 | TK_Complete
CCOM4920 | TT_Task | I&amp;C commissionin of components restored after chem clean | 02/07/2020 | 07/07/2020 | 13/01/2020 | 18/01/2020 | 0 | TK_Complete
CCOM3680 | TT_Task | cold commissioning/system line up for chemical cleaning | 02/07/2020 | 07/07/2020 | 18/11/2019 | 23/11/2019 | 0 | TK_Complete
CCOM3930 | TT_Task | initial I&amp;C commissioning | 02/07/2020 | 07/07/2020 | 20/11/2019 | 23/11/2019 | 0 | TK_Complete
CCOM4050 | TT_Task | initial I&amp;C commissioning | 02/07/2020 | 07/07/2020 | 25/11/2019 | 30/11/2019 | 0 | TK_Complete
CCOM4060 | TT_Task | cold commissioning/system line up for chemical cleaning | 02/07/2020 | 07/07/2020 | 25/11/2019 | 30/11/2019 | 0 | TK_Complete
CCOM4160 | TT_Task | High velocity flushing as per schedule incl heat up and Chem Clean | 02/07/2020 | 07/07/2020 | 09/12/2019 | 15/12/2019 | 0 | TK_Complete
CCOM4330 | TT_Task | Chemical cleaning as per schedule | 02/07/2020 | 07/07/2020 | 16/12/2019 | 18/12/2019 | 0 | TK_Complete
CCOM4610 | TT_Task | Inspections post chem clean | 02/07/2020 | 07/07/2020 | 06/01/2020 | 09/01/2020 | 0 | TK_Complete
CCOM4630 | TT_Task | I&amp;C commissionin of components restored after chem clean | 02/07/2020 | 07/07/2020 | 06/01/2020 | 11/01/2020 | 0 | TK_Complete
CCOM4650 | TT_Task | HRSG protection testing | 02/07/2020 | 07/07/2020 | 09/01/2020 | 11/01/2020 | 0 | TK_Complete
CCOM4660 | TT_Task | System line up for filling | 02/07/2020 | 07/07/2020 | 09/01/2020 | 11/01/2020 | 0 | TK_Complete
CCOM4870 | TT_Task | System line up for filling (with QCD) | 02/07/2020 | 07/07/2020 | 13/01/2020 | 15/01/2020 | 0 | TK_Complete
CCOM4890 | TT_Task | Re-filling of HRSG/Water steam | 02/07/2020 | 07/07/2020 | 16/01/2020 | 18/01/2020 | 0 | TK_Complete
CCOM4910 | TT_Task | I&amp;C commissionin of components restored after chem clean | 02/07/2020 | 07/07/2020 | 13/01/2020 | 18/01/2020 | 0 | TK_Complete
CCOM4400 | TT_Task | Cold commissioning, I&amp;C checks with vendor TFA | 02/07/2020 | 07/07/2020 | 17/12/2019 | 21/12/2019 | 0 | TK_Complete
CCOM4740 | TT_Task | Cold commissioning, I&amp;C checks with vendor TFA | 02/07/2020 | 07/07/2020 | 07/01/2020 | 11/01/2020 | 0 | TK_Complete
CCOM5040 | TT_Task | Cold commissioning, I&amp;C checks with vendor TFA | 02/07/2020 | 07/07/2020 | 13/01/2020 | 18/01/2020 | 0 | TK_Complete
CCOM5050 | TT_Task | System line up for purging/gas charging | 02/07/2020 | 07/07/2020 | 16/01/2020 | 18/01/2020 | 0 | TK_Complete
CCOM3670 | TT_Task | TOP Walkdowns as per IFIs | 02/07/2020 | 07/07/2020 | 19/11/2019 | 23/11/2019 | 0 | TK_Complete
CCOM4040 | TT_Task | TOP Walkdowns as per IFIs | 02/07/2020 | 07/07/2020 | 25/11/2019 | 30/11/2019 | 0 | TK_Complete
CCOM4230 | TT_Task | TOP Walkdowns as per IFIs | 02/07/2020 | 07/07/2020 | 09/12/2019 | 14/12/2019 | 0 | TK_Complete
CCOM4390 | TT_Task | TOP Walkdowns as per IFIs | 02/07/2020 | 07/07/2020 | 16/12/2019 | 21/12/2019 | 0 | TK_Complete
CCOM4730 | TT_Task | TOP Walkdowns as per IFIs | 02/07/2020 | 07/07/2020 | 06/01/2020 | 11/01/2020 | 0 | TK_Complete
CCOM5030 | TT_Task | TOP Walkdowns as per IFIs | 02/07/2020 | 07/07/2020 | 13/01/2020 | 18/01/2020 | 0 | TK_Complete
CCOM4380 | TT_Task | Continuatuion of air leak testing | 02/07/2020 | 07/07/2020 | 17/12/2019 | 21/12/2019 | 0 | TK_Complete
CCOM3650 | TT_Task | System operation to support GT turning gear | 02/07/2020 | 07/07/2020 | 20/11/2019 | 23/11/2019 | 0 | TK_Complete
CCOM4030 | TT_Task | System operation to support GT turning gear | 02/07/2020 | 07/07/2020 | 27/11/2019 | 30/11/2019 | 0 | TK_Complete
CCOM4220 | TT_Task | System operation to support GT turning gear and fact finding on MKW12AP001 | 02/07/2020 | 07/07/2020 | 09/12/2019 | 14/12/2019 | 0 | TK_Complete
CCOM4370 | TT_Task | System operation to support GT turning gear and fact finding on MKW12AP001 | 02/07/2020 | 07/07/2020 | 16/12/2019 | 21/12/2019 | 0 | TK_Complete
CCOM3660 | TT_Task | Preparation and system line up for CO2 purging | 02/07/2020 | 07/07/2020 | 09/01/2020 | 11/01/2020 | 0 | TK_Complete
CCOM5010 | TT_Task | Preparation and system line up for CO2 purging | 02/07/2020 | 07/07/2020 | 13/01/2020 | 14/01/2020 | 0 | TK_Complete
CCOM5020 | TT_Task | H2 Charging (Date TBC) | 02/07/2020 | 07/07/2020 | 18/01/2020 | 18/01/2020 | 0 | TK_Complete
CCOM3640 | TT_Task | cold commissioning and first filling | 02/07/2020 | 07/07/2020 | 18/11/2019 | 23/11/2019 | 0 | TK_Complete
CCOM4020 | TT_Task | cold commissioning and first filling | 02/07/2020 | 07/07/2020 | 25/11/2019 | 30/11/2019 | 0 | TK_Complete
CCOM4690 | TT_Task | Condenser cleaning | 02/07/2020 | 07/07/2020 | 06/01/2020 | 08/01/2020 | 0 | TK_Complete
CCOM4700 | TT_Task | Condenser protection testing | 02/07/2020 | 07/07/2020 | 06/01/2020 | 07/01/2020 | 0 | TK_Complete
CCOM4990 | TT_Task | Condenser filling | 02/07/2020 | 07/07/2020 | 15/01/2020 | 15/01/2020 | 0 | TK_Complete
CCOM5000 | TT_Task | First vacuum pulling | 02/07/2020 | 07/07/2020 | 16/01/2020 | 18/01/2020 | 0 | TK_Complete
CCOM3630 | TT_Task | Initial cold commissioning - signal checks | 02/07/2020 | 07/07/2020 | 20/11/2019 | 23/11/2019 | 0 | TK_Complete
CCOM4000 | TT_Task | Initial cold commissioning, signal checks, system line up for aux. Steam blow (pending TOP) | 02/07/2020 | 07/07/2020 | 27/11/2019 | 30/11/2019 | 0 | TK_Complete
CCOM4010 | TT_Task | Aux. Steam Blow | 02/07/2020 | 07/07/2020 | 30/11/2019 | 01/12/2019 | 0 | TK_Complete
CCOM4200 | TT_Task | System restoration after steam blow | 02/07/2020 | 07/07/2020 | 09/12/2019 | 11/12/2019 | 0 | TK_Complete
CCOM4210 | TT_Task | System operation for heat up prior to chemical cleaning | 02/07/2020 | 07/07/2020 | 12/12/2019 | 14/12/2019 | 0 | TK_Complete
CCOM4360 | TT_Task | System restoration after steam blow | 02/07/2020 | 07/07/2020 | 16/12/2019 | 18/12/2019 | 0 | TK_Complete
CCOM4680 | TT_Task | System restoration | 02/07/2020 | 07/07/2020 | 06/01/2020 | 08/01/2020 | 0 | TK_Complete
CCOM4960 | TT_Task | System operation with Aux Boiler for seal steam comm | 02/07/2020 | 07/07/2020 | 16/01/2020 | 18/01/2020 | 0 | TK_Complete
CCOM3620 | TT_Task | cold commissioning and system setup for filling of condenser | 02/07/2020 | 07/07/2020 | 20/11/2019 | 23/11/2019 | 0 | TK_Complete
CCOM3990 | TT_Task | cold commissioning and system setup for filling of condenser (pending TOP) | 02/07/2020 | 07/07/2020 | 27/11/2019 | 30/11/2019 | 0 | TK_Complete
CCOM3900 | TT_Task | TOP pending - cold commissioning | 02/07/2020 | 07/07/2020 | 30/10/2019 | 31/10/2019 | 0 | TK_Complete
CCOM3910 | TT_Task | cold commissioning (pending TOP) | 02/07/2020 | 07/07/2020 | 11/11/2019 | 16/11/2019 | 0 | TK_Complete
CCOM3920 | TT_Task | cold commissioning incl motor solo runs incl first pump operation | 02/07/2020 | 07/07/2020 | 18/11/2019 | 23/11/2019 | 0 | TK_Complete
CCOM3980 | TT_Task | cold commissioning incl motor solo runs incl first pump operation | 02/07/2020 | 07/07/2020 | 25/11/2019 | 30/11/2019 | 0 | TK_Complete
CCOM4190 | TT_Task | System in service for flushing | 02/07/2020 | 07/07/2020 | 09/12/2019 | 14/12/2019 | 0 | TK_Complete
CCOM4350 | TT_Task | System in service | 02/07/2020 | 07/07/2020 | 17/12/2019 | 21/12/2019 | 0 | TK_Complete
CCOM3610 | TT_Task | min flow run (pending TOP) | 02/07/2020 | 07/07/2020 | 15/11/2019 | 16/11/2019 | 0 | TK_Complete
CCOM3870 | TT_Task | min flow run (pending TOP) | 02/07/2020 | 07/07/2020 | 22/11/2019 | 23/11/2019 | 0 | TK_Complete
CCOM3880 | TT_Task | preparation for min flow run, cold comissioning (pending TOP) | 02/07/2020 | 07/07/2020 | 11/11/2019 | 14/11/2019 | 0 | TK_Complete
CCOM3890 | TT_Task | preparation for min flow run, cold comissioning (pending TOP) | 02/07/2020 | 07/07/2020 | 18/11/2019 | 21/11/2019 | 0 | TK_Complete
CCOM3960 | TT_Task | preparation for min flow run, cold comissioning (pending TOP) | 02/07/2020 | 07/07/2020 | 25/11/2019 | 28/11/2019 | 0 | TK_Complete
CCOM3970 | TT_Task | min flow run (pending TOP) | 02/07/2020 | 07/07/2020 | 28/11/2019 | 30/11/2019 | 0 | TK_Complete
CCOM4180 | TT_Task | Pump operation for high velocity flushing | 02/07/2020 | 07/07/2020 | 09/12/2019 | 14/12/2019 | 0 | TK_Complete
CCOM3600 | TT_Task | cold commissioning, preparation for oil flushing (pending TOP) | 02/07/2020 | 07/07/2020 | 12/11/2019 | 23/11/2019 | 0 | TK_Complete
CCOM3950 | TT_Task | cold commissioning, oil flushing, motor rotation checks, motor solo run | 02/07/2020 | 07/07/2020 | 25/11/2019 | 30/11/2019 | 0 | TK_Complete
CCOM4950 | TT_Task | First FWP operation | 02/07/2020 | 07/07/2020 | 17/01/2020 | 18/01/2020 | 0 | TK_Complete
CCOM3590 | TT_Task | Commissioning of GM-01 system (pending TOP) | 02/07/2020 | 07/07/2020 | 14/11/2019 | 16/11/2019 | 0 | TK_Complete
CCOM3860 | TT_Task | Commissioning of GM-01 system (pending TOP) | 02/07/2020 | 07/07/2020 | 19/11/2019 | 23/11/2019 | 0 | TK_Complete
CCOM4150 | TT_Task | Commissioning of GM-01 system | 02/07/2020 | 07/07/2020 | 09/12/2019 | 10/12/2019 | 0 | TK_Complete
CCOM3800 | TT_Task | Initial electrical cold commissioning | 02/07/2020 | 07/07/2020 | 19/11/2019 | 30/11/2019 | 0 | TK_Complete
CCOM3810 | TT_Task | Synchronization tests | 02/07/2020 | 07/07/2020 | 09/12/2019 | 12/12/2019 | 0 | TK_Complete
CCOM3820 | TT_Task | Synchronization tests | 02/07/2020 | 07/07/2020 | 16/12/2019 | 19/12/2019 | 0 | TK_Complete
CCOM3830 | TT_Task | UVTS internal testing/logic checks | 02/07/2020 | 07/07/2020 | 06/01/2020 | 14/01/2020 | 0 | TK_Complete
CCOM3840 | TT_Task | Initial ATS internal testing | 02/07/2020 | 07/07/2020 | 11/01/2020 | 11/01/2020 | 0 | TK_Complete
CCOM3850 | TT_Task | ATS official testing | 02/07/2020 | 07/07/2020 | 14/01/2020 | 15/01/2020 | 0 | TK_Complete
CCOM5150 | TT_Task | ATS Test | 02/07/2020 | 07/07/2020 | 14/01/2020 | 14/01/2020 | 0 | TK_Complete
CCOM3580 | TT_Task | pressurisation of bus duct (pressure test for constrcution) | 02/07/2020 | 07/07/2020 | 19/11/2019 | 21/11/2019 | 0 | TK_Complete
CCOM3940 | TT_Task | pressurisation of bus duct (pressure test for constrcution) | 02/07/2020 | 07/07/2020 | 25/11/2019 | 27/11/2019 | 0 | TK_Complete
CCOM3575 | TT_Task | End- to End test: D1 - LDC | 02/07/2020 | 07/07/2020 | 20/11/2019 | 22/11/2019 | 0 | TK_Complete
CCOM3770 | TT_Task | 400V Injection from GIS side (pending release from CLP) | 02/07/2020 | 07/07/2020 | 18/11/2019 | 19/11/2019 | 0 | TK_Complete
CCOM3780 | TT_Task | Exchange of gasket on GIL &amp; refilling of SF6 | 02/07/2020 | 07/07/2020 | 19/11/2019 | 20/11/2019 | 0 | TK_Complete
CCOM3790 | TT_Task | Exchange of gasket on GIL &amp; refilling of SF6 | 02/07/2020 | 07/07/2020 | 26/11/2019 | 27/11/2019 | 0 | TK_Complete
CCOM3720 | TT_Task | MEP System Commissioining | 02/07/2020 | 07/07/2020 | 18/11/2019 | 23/11/2019 | 0 | TK_Complete
CCOM4090 | TT_Task | MEP System Commissioining | 02/07/2020 | 07/07/2020 | 25/11/2019 | 30/11/2019 | 0 | TK_Complete
CCOM4280 | TT_Task | MEP System Commissioining | 02/07/2020 | 07/07/2020 | 09/12/2019 | 14/12/2019 | 0 | TK_Complete
CCOM4510 | TT_Task | MEP System Commissioining | 02/07/2020 | 07/07/2020 | 16/12/2019 | 21/12/2019 | 0 | TK_Complete
CCOM4810 | TT_Task | MEP System Commissioining | 02/07/2020 | 07/07/2020 | 06/01/2020 | 11/01/2020 | 0 | TK_Complete
CCOM5110 | TT_Task | MEP System Commissioining | 02/07/2020 | 07/07/2020 | 13/01/2020 | 19/01/2020 | 0 | TK_Complete
CCOM3730 | TT_Task | Station interface walkdowns for all upcoming terminal points (flushing/cleaning preparation) | 02/07/2020 | 07/07/2020 | 18/11/2019 | 22/11/2019 | 0 | TK_Complete
CCOM4110 | TT_Task | 400kV Backfeed @ 1/12 02:00 | 02/07/2020 | 07/07/2020 | 01/12/2019 | 01/12/2019 | 0 | TK_Complete
CCOM3740 | TT_Task | Backfeed Coordination (HV injection &amp; interlock/intertrip tests) | 02/07/2020 | 07/07/2020 | 18/11/2019 | 21/11/2019 | 0 | TK_Complete
CCOM4100 | TT_Task | Backfeed Coordination (Document review) | 02/07/2020 | 07/07/2020 | 25/11/2019 | 29/11/2019 | 0 | TK_Complete
CCOM4310 | TT_Task | Issue for BAT re-energization after outage | 09/12/2019 | 13/12/2019 | 10/12/2019 | 13/12/2019 | 0 | TK_Complete
CCOM4540 | TT_Task | Issue for BAT re-energization after outage | 02/07/2020 | 07/07/2020 | 17/12/2019 | 20/12/2019 | 0 | TK_Complete
CCOM4550 | TT_Task | Transformer re-energization work | 02/07/2020 | 07/07/2020 | 22/12/2019 | 22/12/2019 | 0 | TK_Complete
CCOM3750 | TT_Task | Fresh water fire fight system preparation and spray test | 02/07/2020 | 07/07/2020 | 18/11/2019 | 18/11/2019 | 0 | TK_Complete
CCOM5140 | TT_Task | Fire Fighting System flushing coordination | 02/07/2020 | 07/07/2020 | 13/01/2020 | 17/01/2020 | 0 | TK_Complete
CCOM3760 | TT_Task | GHD Tie-in work coordination | 02/07/2020 | 07/07/2020 | 19/11/2019 | 22/11/2019 | 0 | TK_Complete
CCOM4120 | TT_Task | GHD Tie-in work coordination | 02/07/2020 | 07/07/2020 | 25/11/2019 | 26/11/2019 | 0 | TK_Complete
CCOM4130 | TT_Task | QJA10 / QJA20 Tie-in work coordination | 02/07/2020 | 07/07/2020 | 25/11/2019 | 29/11/2019 | 0 | TK_Complete
CCOM4290 | TT_Task | QJA10 / QJA20 Tie-in work coordination | 02/07/2020 | 07/07/2020 | 09/12/2019 | 13/12/2019 | 0 | TK_Complete
CCOM4520 | TT_Task | QJA10 / QJA20 Tie-in work coordination | 02/07/2020 | 07/07/2020 | 16/12/2019 | 20/12/2019 | 0 | TK_Complete
CCOM4140 | TT_Task | EG Tie-in work coordination | 02/07/2020 | 07/07/2020 | 25/11/2019 | 29/11/2019 | 0 | TK_Complete
CCOM4300 | TT_Task | EG Tie-in work coordination | 02/07/2020 | 07/07/2020 | 09/12/2019 | 13/12/2019 | 0 | TK_Complete
CCOM4530 | TT_Task | EG Tie-in work coordination | 02/07/2020 | 07/07/2020 | 16/12/2019 | 20/12/2019 | 0 | TK_Complete
CCOM4820 | TT_Task | EG Tie-in work coordination | 02/07/2020 | 07/07/2020 | 06/01/2020 | 10/01/2020 | 0 | TK_Complete
CCOM5120 | TT_Task | EG Tie-in work coordination | 02/07/2020 | 07/07/2020 | 13/01/2020 | 17/01/2020 | 0 | TK_Complete
CCOM4240 | TT_Task | Rotation checks &amp; motor solo runs for Fuel oil forwarding pumps | 02/07/2020 | 07/07/2020 | 11/12/2019 | 12/12/2019 | 0 | TK_Complete
CCOM4560 | TT_Task | Chemical clean effluent coordination | 02/07/2020 | 07/07/2020 | 16/12/2019 | 21/12/2019 | 0 | TK_Complete
CCOM4830 | TT_Task | EK purging procedure review | 02/07/2020 | 07/07/2020 | 06/01/2020 | 10/01/2020 | 0 | TK_Complete
CCOM5130 | TT_Task | EK purging procedure review | 02/07/2020 | 07/07/2020 | 13/01/2020 | 17/01/2020 | 0 | TK_Complete
CCOM4840 | TT_Task | Primary protection test discussion | 02/07/2020 | 07/07/2020 | 06/01/2020 | 06/01/2020 | 0 | TK_Complete
HCOM1360 | TT_Rsrc | YOC &amp; PCI Gas Outage [No Gas Available] | 05/02/2020 | 12/02/2020 | 05/02/2020 | 10/02/2020 | 0 | TK_Complete
HCOM1370 | TT_Rsrc | BPPS Station Outage | 05/02/2020 | 10/02/2020 | 05/02/2020 | 08/02/2020 | 0 | TK_Complete
HCOM1420 | TT_Rsrc | Oil Available | 10/02/2020 | 14/02/2020 | 09/02/2020 | 13/02/2020 | 0 | TK_Complete
HCOM1450 | TT_Rsrc | YOC Gas Available | 11/02/2020 | 13/02/2020 | 11/02/2020 | 13/02/2020 | 0 | TK_Complete
HCOM1460 | TT_Rsrc | PCI Gas Available | 13/02/2020 | 13/02/2020 | 13/02/2020 | 13/02/2020 | 0 | TK_Complete
HCOM1000 | TT_Rsrc | Final Boxing up of HRSG and removal of SCR scaffolding | 25/11/2019 | 29/11/2019 | 25/11/2019 | 29/11/2019 | 0 | TK_Complete
HCOM1010 | TT_Rsrc | Scaffolding Dismantling | 25/11/2019 | 29/11/2019 | 25/11/2019 | 29/11/2019 | 0 | TK_Complete
HCOM1020 | TT_Rsrc | All Remaining TOPs for Chemical Clean Handed Over | 25/11/2019 | 29/11/2019 | 25/11/2019 | 29/11/2019 | 0 | TK_Complete
HCOM1030 | TT_Rsrc | ZTB across road to be in place | 25/11/2019 | 29/11/2019 | 25/11/2019 | 29/11/2019 | 0 | TK_Complete
HCOM1060 | TT_Rsrc | ZXB pressure test | 27/11/2019 | 27/11/2019 | 27/11/2019 | 27/11/2019 | 0 | TK_Complete
HCOM1080 | TT_Rsrc | ZTA Leak check | 29/11/2019 | 29/11/2019 | 29/11/2019 | 29/11/2019 | 0 | TK_Complete
HCOM1070 | TT_Rsrc | MAG / LCA condensate system recirculation run | 28/11/2019 | 28/11/2019 | 28/11/2019 | 28/11/2019 | 0 | TK_Complete
HCOM1090 | TT_Rsrc | Auxiliary Boiler Steam Blow | 02/12/2019 | 02/12/2019 | 30/11/2019 | 30/11/2019 | 0 | TK_Complete
HCOM1100 | TT_Rsrc | Commissioning of Systems to Support Chemical Clean | 02/12/2019 | 06/12/2019 | 01/12/2019 | 05/12/2019 | 0 | TK_Complete
HCOM1120 | TT_Rsrc | High Velocity Flushing | 06/12/2019 | 12/12/2019 | 06/12/2019 | 10/12/2019 | 0 | TK_Complete
HCOM1130 | TT_Rsrc | Heating Phase &amp; Other Remaining Commissioning | 11/12/2019 | 16/12/2019 | 11/12/2019 | 14/12/2019 | 0 | TK_Complete
HCOM1140 | TT_Rsrc | Chemical Cleaning | 16/12/2019 | 18/12/2019 | 14/12/2019 | 16/12/2019 | 0 | TK_Complete
HCOM1150 | TT_Rsrc | Cooldown, Draining &amp; Rinsing | 16/12/2019 | 18/12/2019 | 16/12/2019 | 18/12/2019 | 0 | TK_Complete
HCOM1160 | TT_Rsrc | Work on affected component list | 19/12/2019 | 08/01/2020 | 19/12/2019 | 03/01/2020 | 0 | TK_Complete
HCOM1180 | TT_Rsrc | Dosing Commissioning (automatic Operation) | 03/01/2020 | 07/01/2020 | 03/01/2020 | 05/01/2020 | 0 | TK_Complete
HCOM1190 | TT_Rsrc | Commissioning MOVs | 06/01/2020 | 24/01/2020 | 04/01/2020 | 18/01/2020 | 0 | TK_Complete
HCOM1210 | TT_Rsrc | Sampling System Commissioning (automatic operation) | 06/01/2020 | 08/01/2020 | 06/01/2020 | 08/01/2020 | 0 | TK_Complete
HCOM1220 | TT_Rsrc | Commissioning LAB | 10/01/2020 | 20/01/2020 | 10/01/2020 | 16/01/2020 | 0 | TK_Complete
HCOM1230 | TT_Rsrc | Filling HRSG | 17/01/2020 | 20/01/2020 | 17/01/2020 | 18/01/2020 | 0 | TK_Complete
HCOM1170 | TT_Rsrc | Dismantle ZTA &amp; all temporary equipment | 19/12/2019 | 16/01/2020 | 19/12/2019 | 09/01/2020 | 0 | TK_Complete
HCOM1200 | TT_Rsrc | Reinstatement LAB System &amp; Issue ECC | 06/01/2020 | 10/01/2020 | 05/01/2020 | 09/01/2020 | 0 | TK_Complete
HCOM1040 | TT_Rsrc | Cold Commissioning Activites for First Fire | 25/11/2019 | 13/02/2020 | 25/11/2019 | 23/01/2020 | 0 | TK_Complete
HCOM1050 | TT_Rsrc | All Construction Activities Required for FF (inc. TOPS &amp; P/Ls) | 25/11/2019 | 10/02/2020 | 25/11/2019 | 20/01/2020 | 0 | TK_Complete
HCOM1240 | TT_Rsrc | Construction Completion / PL 'B's Cleared and handover of all TOPs required for FF | 21/01/2020 | 21/01/2020 | 20/01/2020 | 20/01/2020 | 0 | TK_Complete
HCOM1270 | TT_Rsrc | Required Dangerous Good Licenses in Place | 23/01/2020 | 23/01/2020 | 23/01/2020 | 23/01/2020 | 0 | TK_Complete
HCOM1280 | TT_Rsrc | Completion of all Cold Commissioning required for FF | 24/01/2020 | 24/01/2020 | 23/01/2020 | 23/01/2020 | 0 | TK_Complete
HCOM1110 | TT_Rsrc | CLP First Fire Review &amp; Green Light to Proceed | 02/12/2019 | 06/12/2019 | 02/12/2019 | 06/12/2019 | 0 | TK_Complete
HCOM1250 | TT_Rsrc | Siemens First Fire Readiness Review &amp; Green Light to Proceed | 22/01/2020 | 23/01/2020 | 22/01/2020 | 23/01/2020 | 0 | TK_Complete
HCOM1260 | TT_Rsrc | CLP Green Light of Start Up review to proceed to First Fire | 22/01/2020 | 23/01/2020 | 22/01/2020 | 23/01/2020 | 0 | TK_Complete
HCOM1290 | TT_Rsrc | First Fire | 27/01/2020 | 27/01/2020 | 24/01/2020 | 24/01/2020 | 0 | TK_Complete
HCOM1300 | TT_Rsrc | GT FSNL Testing | 27/01/2020 | 27/01/2020 | 25/01/2020 | 25/01/2020 | 0 | TK_Complete
HCOM1310 | TT_Rsrc | Generator Protection | 27/01/2020 | 28/01/2020 | 26/01/2020 | 27/01/2020 | 0 | TK_Complete
HCOM1320 | TT_Rsrc | Generator Syncronisation | 27/01/2020 | 27/01/2020 | 27/01/2020 | 27/01/2020 | 0 | TK_Complete
HCOM1330 | TT_Rsrc | Steam Blow | 28/01/2020 | 06/02/2020 | 28/01/2020 | 04/02/2020 | 0 | TK_Complete
HCOM1340 | TT_Rsrc | Reinstatement of ZTB | 05/02/2020 | 06/02/2020 | 05/02/2020 | 06/02/2020 | 0 | TK_Complete
HCOM1350 | TT_Rsrc | Reinstatement of LBC40 | 05/02/2020 | 06/02/2020 | 05/02/2020 | 06/02/2020 | 0 | TK_Complete
HCOM1390 | TT_Rsrc | Reinstatement of MAX System | 07/02/2020 | 07/02/2020 | 07/02/2020 | 07/02/2020 | 0 | TK_Complete
HCOM1410 | TT_Rsrc | Valve Commissioing LBC412, LBC40, MAA, MAB MAC | 10/02/2020 | 12/02/2020 | 08/02/2020 | 10/02/2020 | 0 | TK_Complete
HCOM1430 | TT_Rsrc | SIL Test HP, LP, CRH | 10/02/2020 | 11/02/2020 | 10/02/2020 | 11/02/2020 | 0 | TK_Complete
HCOM1440 | TT_Rsrc | ATT Standsill / TGO | 11/02/2020 | 11/02/2020 | 11/02/2020 | 11/02/2020 | 0 | TK_Complete
HCOM1470 | TT_Rsrc | Preparation for unit start and Close all Construction Permits | 02/03/2020 | 02/03/2020 | 02/03/2020 | 02/03/2020 | 0 | TK_Complete
HCOM1380 | TT_Rsrc | Unit cooldown | 05/02/2020 | 06/02/2020 | 05/02/2020 | 06/02/2020 | 0 | TK_Complete
HCOM1400 | TT_Rsrc | Installation of SCR | 07/02/2020 | 11/03/2020 | 07/02/2020 | 01/03/2020 | 0 | TK_Complete
HCOM1480 | TT_Rsrc | Bypass operation &amp; Trevi Tests | 03/03/2020 | 05/03/2020 | 03/03/2020 | 05/03/2020 | 0 | TK_Complete
HCOM1490 | TT_Rsrc | Event: Unit S/D due to bearing 1 lift oil leak | 05/03/2020 | 09/03/2020 | 05/03/2020 | 07/03/2020 | 0 | TK_Complete
HCOM1500 | TT_Rsrc | Unit Startup | 09/03/2020 | 09/03/2020 | 08/03/2020 | 08/03/2020 | 0 | TK_Complete
HCOM1510 | TT_Rsrc | Event: Unit Trip: Unit Trip - HP Bypass failed to full open | 09/03/2020 | 09/03/2020 | 09/03/2020 | 09/03/2020 | 0 | TK_Complete
HCOM1520 | TT_Rsrc | Event: Forced Outage for HP Bypass Valve Damage Repair | 10/03/2020 | 27/04/2020 | 10/03/2020 | 13/04/2020 | 0 | TK_Complete
HCOM1530 | TT_Rsrc | Unit Restart - Bypass Operation | 14/04/2020 | 15/04/2020 | 14/04/2020 | 15/04/2020 | 0 | TK_Complete
HCOM1540 | TT_Rsrc | First Steam to ST &amp; ramp up to warm up speed | 16/04/2020 | 16/04/2020 | 16/04/2020 | 16/04/2020 | 0 | TK_Complete
HCOM1550 | TT_Rsrc | Steam Turbine ramp up to nominal speed &amp; initial loading | 17/04/2020 | 20/04/2020 | 17/04/2020 | 18/04/2020 | 0 | TK_Complete
HCOM1560 | TT_Rsrc | First CC Baseload operation | 20/04/2020 | 20/04/2020 | 18/04/2020 | 18/04/2020 | 0 | TK_Complete
HCOM1570 | TT_Rsrc | Outage - Combustor cold spot | 20/04/2020 | 21/04/2020 | 19/04/2020 | 26/04/2020 | 0 | TK_Complete
HCOM1580 | TT_Task | Unit on Load | 01/06/2021 | 07/06/2021 | 27/04/2020 | 30/04/2020 | 0 | TK_Complete
HCOM1590 | TT_Task | Vibration trip test | 01/06/2021 | 07/06/2021 | 01/05/2020 | 01/05/2020 | 0 | TK_Complete
HCOM1600 | TT_Task | Unit Shutdown | 01/06/2021 | 07/06/2021 | 02/05/2020 | 03/05/2020 | 0 | TK_Complete
HCOM1610 | TT_Task | Unit on Load | 01/06/2021 | 07/06/2021 | 04/05/2020 | 04/05/2020 | 0 | TK_Complete
HCOM1620 | TT_Task | Unit CC Base Load | 01/06/2021 | 07/06/2021 | 05/05/2020 | 10/05/2020 | 0 | TK_Complete
HCOM1630 | TT_Task | Unit Trip @ 16 MW | 01/06/2021 | 07/06/2021 | 11/05/2020 | 11/05/2020 | 0 | TK_Complete
HCOM1640 | TT_Task | Unit CC Base Load | 01/06/2021 | 07/06/2021 | 11/05/2020 | 12/05/2020 | 0 | TK_Complete
HCOM1650 | TT_Task | Shut down outage for FSD Inspection | 01/06/2021 | 07/06/2021 | 13/05/2020 | 04/06/2020 | 0 | TK_Complete
HCOM1660 | TT_Task | Fuel Gas Line flushing Outage (Flushing cleaning I/P) | 01/06/2021 | 07/06/2021 | 05/06/2020 | 14/06/2020 | 0 | TK_Complete
HCOM1670 | TT_Task | Cold start / Load / shutdown | 01/06/2021 | 07/06/2021 | 15/06/2020 | 15/06/2020 | 0 | TK_Complete
HCOM1680 | TT_Task | Hot start / Load / SCR system testing / shutdown | 01/06/2021 | 07/06/2021 | 16/06/2020 | 17/06/2020 | 0 | TK_Complete
HCOM1690 | TT_Task | Shutdown (GT Offline Washing ) | 01/06/2021 | 07/06/2021 | 18/06/2020 | 18/06/2020 | 0 | TK_Complete
HCOM1700 | TT_Task | Offline washing / Warm start / Trip test/ Hot start/ Shutdown | 27/09/2021 | 01/10/2021 | 19/06/2020 | 19/06/2020 | 0 | TK_Complete
HCOM1710 | TT_Task | Hot start / shutdown / Hot start on the fly | 27/09/2021 | 01/10/2021 | 20/06/2020 | 20/06/2020 | 0 | TK_Complete
HCOM1720 | TT_Task | Unit on Load / shutdown | 27/09/2021 | 01/10/2021 | 21/06/2020 | 21/06/2020 | 0 | TK_Complete
HCOM1730 | TT_Task | Hot start/ Unit on Load | 27/09/2021 | 01/10/2021 | 22/06/2020 | 22/06/2020 | 0 | TK_Complete
HCOM1740 | TT_Task | Unit Minimum Load Operation | 27/09/2021 | 01/10/2021 | 23/06/2020 | 23/06/2020 | 0 | TK_Complete
HCOM1750 | TT_Task | Unit on Load / Excitation Test | 27/09/2021 | 01/10/2021 | 24/06/2020 | 24/06/2020 | 0 | TK_Complete
HCOM1760 | TT_Task | Unit on Load / Emergency Shutdown (FF Ring main water leak inside turbine hall) | 27/09/2021 | 01/10/2021 | 25/06/2020 | 26/06/2020 | 0 | TK_Complete
HCOM1770 | TT_Task | Warm Test / Excitation Test | 27/09/2021 | 01/10/2021 | 27/06/2020 | 27/06/2020 | 0 | TK_Complete
HCOM1780 | TT_Task | Unit on Load / Excitation test/ SCR Load Testing | 27/09/2021 | 01/10/2021 | 28/06/2020 | 28/06/2020 | 0 | TK_Complete
HCOM1790 | TT_Task | Load / SCR Load Testing | 27/09/2021 | 01/10/2021 | 29/06/2020 | 01/07/2020 | 0 | TK_Complete
HCOM1800 | TT_Task | SCR Load Testing | 27/09/2021 | 01/10/2021 | 02/07/2020 | 02/07/2020 | 0 | TK_Complete
HCOM1810 | TT_Task | Shutdown | 27/09/2021 | 01/10/2021 | 02/07/2020 | 02/07/2020 | 0 | TK_Complete
HCOM1820 | TT_Task | Automatic Hot Start on the Fly and verification of SCR system | 27/09/2021 | 01/10/2021 | 03/07/2020 | 03/07/2020 | 0 | TK_Complete
HCOM1830 | TT_Task | Unit on Load / Emissiong QAL2 Test | 27/09/2021 | 01/10/2021 | 04/07/2020 | 04/07/2020 | 0 | TK_Complete
HCOM1840 | TT_Task | Unit on Load / Emissiong QAL2 Test / Operational Reliability test Running | 27/09/2021 | 01/10/2021 | 05/07/2020 | 07/07/2020 | 0 | TK_Complete
HCOM1850 | TT_Task | shutdown for defect clearance before contractual RTR | 27/09/2021 | 01/10/2021 | 08/07/2020 | 10/07/2020 | 0 | TK_Complete
HCOM1860 | TT_Task | Cold Start / Load | 27/09/2021 | 01/10/2021 | 11/07/2020 | 11/07/2020 | 0 | TK_Complete
HCOM1870 | TT_Task | Unit on Load | 27/09/2021 | 01/10/2021 | 12/07/2020 | 12/07/2020 | 0 | TK_Complete
HCOM1880 | TT_Task | Contractual Reliability test Running | 27/09/2021 | 01/10/2021 | 13/07/2020 | 23/07/2020 | 0 | TK_Complete
HCOM1890 | TT_Task | Forced Outage - SCR Blower failure | 27/09/2021 | 01/10/2021 | 24/07/2020 | 25/07/2020 | 0 | TK_Complete
HCOM1900 | TT_Task | Phase 1 - Cold Start / Contractual Reliability test Running - (Start) | 27/09/2021 | 01/10/2021 | 26/07/2020 | 26/07/2020 | 0 | TK_Complete
HCOM1905 | TT_Task | Phase 1 - Contractual Reliability test Running | 27/09/2021 | 01/10/2021 | 27/07/2020 | 28/07/2020 | 0 | TK_Complete
HCOM1910 | TT_Task | Phase 1 - Contractual Reliability test Running / AGC test | 27/09/2021 | 01/10/2021 | 29/07/2020 | 30/07/2020 | 0 | TK_Complete
HCOM1920 | TT_Task | Phase 1 - Contractual Reliability test Running - (Complete) | 27/09/2021 | 01/10/2021 | 31/07/2020 | 05/08/2020 | 0 | TK_Complete
HCOM1930 | TT_Task | Phase 2 - Contractual Reliability test Running - (Start) | 27/09/2021 | 01/10/2021 | 06/08/2020 | 12/08/2020 | 0 | TK_Complete
HCOM1940 | TT_Task | Phase 2 - Contractual Reliability test Running / shutdown - (Complete) | 27/09/2021 | 01/10/2021 | 13/08/2020 | 13/08/2020 | 0 | TK_Complete
HCOM1950 | TT_Task | Shutdown - defect clearance | 01/06/2021 | 07/06/2021 | 14/08/2020 | 15/08/2020 | 0 | TK_Complete
HCOM1960 | TT_Task | Shutdown - IGV cleaning / calibration | 01/06/2021 | 07/06/2021 | 16/08/2020 | 16/08/2020 | 0 | TK_Complete
HCOM1970 | TT_Task | Shutdown - defect clearance | 01/06/2021 | 07/06/2021 | 17/08/2020 | 17/08/2020 | 0 | TK_Complete
HCOM1980 | TT_Task | Phase 3 - Cold Start / Contractual Reliability test Running (Start) | 01/06/2021 | 07/06/2021 | 18/08/2020 | 18/08/2020 | 0 | TK_Complete
HCOM1990 | TT_Task | Phase 3 - Contractual Reliability test Running / internal Performance Test | 01/06/2021 | 07/06/2021 | 19/08/2020 | 20/08/2020 | 0 | TK_Complete
HCOM2000 | TT_Task | Phase 3 - Contractual Reliability test Running / Contracual Performance Test | 01/06/2021 | 07/06/2021 | 21/08/2020 | 22/08/2020 | 0 | TK_Complete
HCOM2010 | TT_Task | Phase 3 - Contractual Reliability test Running | 01/06/2021 | 07/06/2021 | 23/08/2020 | 27/06/2021 | 0 | TK_Complete
HCOM2020 | TT_Task | Phase 3 - Contractual Reliability test Running / shutdown (complete) | 01/06/2021 | 07/06/2021 | 28/08/2020 | 28/08/2020 | 0 | TK_Complete
HCOM2030 | TT_Task | Shutdown - defect clearance | 01/06/2021 | 07/06/2021 | 29/08/2020 | 31/08/2020 | 0 | TK_Complete
HCOM2040 | TT_Task | Cold start test, internal Pefromance Test @ 50%CC | 01/06/2021 | 07/06/2021 | 01/09/2020 | 01/09/2020 | 0 | TK_Complete
HCOM2050 | TT_Task | Hot start on YOC Gas / shutdown | 01/06/2021 | 07/06/2021 | 02/09/2020 | 04/09/2020 | 0 | TK_Complete
HCOM2060 | TT_Task | Shutdown | 01/06/2021 | 07/06/2021 | 05/09/2020 | 05/09/2020 | 0 | TK_Complete
HCOM2070 | TT_Task | Shutdown / Preparation for Performance Test | 01/06/2021 | 07/06/2021 | 06/09/2020 | 09/09/2020 | 0 | TK_Complete
HCOM2080 | TT_Task | Shutdown | 08/06/2021 | 14/06/2021 | 10/09/2020 | 11/09/2020 | 0 | TK_Complete
HCOM2090 | TT_Task | Offline washing / cold start | 15/06/2021 | 21/06/2021 | 12/09/2020 | 12/09/2020 | 0 | TK_Complete
HCOM2100 | TT_Task | Unit on Load / internal Performance Test | 22/06/2021 | 28/06/2021 | 13/09/2020 | 14/09/2020 | 0 | TK_Complete
HCOM2110 | TT_Task | Unit on Load / Contractual Performance Test | 29/06/2021 | 05/07/2021 | 15/09/2020 | 16/09/2020 | 0 | TK_Complete
HCOM2120 | TT_Task | Shutdown / hot start / Contractual Performance Test | 06/07/2021 | 12/07/2021 | 17/09/2020 | 17/09/2020 | 0 | TK_Complete
HCOM2130 | TT_Task | Unit on Load / Contractual Performance Test | 13/07/2021 | 19/07/2021 | 18/09/2020 | 18/09/2020 | 0 | TK_Complete
HCOM2140 | TT_Task | Unit Load / Contractual Performance Test / shutdown | 20/07/2021 | 26/07/2021 | 19/09/2020 | 19/09/2020 | 0 | TK_Complete
HCOM2150 | TT_Task | Shutdown | 27/07/2021 | 02/08/2021 | 20/09/2020 | 20/09/2020 | 0 | TK_Complete
HCOM2160 | TT_Task | Cold Start / YOC gas commissioning | 03/08/2021 | 09/08/2021 | 21/09/2020 | 21/09/2020 | 0 | TK_Complete
HCOM2170 | TT_Task | YOC gas commissioning | 10/08/2021 | 16/08/2021 | 22/09/2020 | 24/09/2020 | 0 | TK_Complete
A3900 | TT_Task | Unit under Operation Control | 01/06/2021 | 07/06/2021 | 28/09/2020 | 18/02/2021 | 0 | TK_Complete
A3500 | TT_Task | Unit Cool down | 01/06/2021 | 07/06/2021 | 19/02/2021 | 20/02/2021 | 0 | TK_Complete
A3510 | TT_Task | Unit offline and Issue PTW's | 01/06/2021 | 07/06/2021 | 21/02/2021 | 21/02/2021 | 0 | TK_Complete
A3520 | TT_Task | TB2 Handover to Siemens | 01/06/2021 | 07/06/2021 | 22/02/2021 | 22/02/2021 | 0 | TK_Complete
A3530 | TT_Task | TB2 Blade Rectification Works outage | 01/06/2021 | 07/06/2021 | 22/02/2021 | 23/03/2021 | 0 | TK_Complete
A3540 | TT_Task | GT Fuel Oil Barrel / Bucket testing | 01/06/2021 | 07/06/2021 | 14/03/2021 | 23/03/2021 | 0 | TK_Complete
A3550 | TT_Task | H/O to Commissioning Team - GT TGO | 01/06/2021 | 07/06/2021 | 23/03/2021 | 23/03/2021 | 0 | TK_Complete
A3560 | TT_Task | Unit Start -up Verification on fuel gas operation incl initial testing of SCR System | 01/06/2021 | 07/06/2021 | 24/03/2021 | 24/03/2021 | 0 | TK_Complete
A3570 | TT_Task | SCR Testing | 01/06/2021 | 07/06/2021 | 25/03/2021 | 29/03/2021 | 0 | TK_Complete
A3580 | TT_Task | SCR Testing -RTR Phase 1- Fuel Gas emissions (Nox &amp; NH3) and noise testing @ HRSG (with plant instrumentation) | 01/06/2021 | 07/06/2021 | 30/03/2021 | 30/03/2021 | 0 | TK_Complete
A3590 | TT_Task | SCR Testing - RTR Phase 1 | 01/06/2021 | 07/06/2021 | 31/03/2021 | 06/04/2021 | 0 | TK_Complete
A3600 | TT_Task | Fuel oil commissioning - Water purge testing | 01/06/2021 | 07/06/2021 | 07/04/2021 | 08/04/2021 | 0 | TK_Complete
A3610 | TT_Task | Fuel oil commissioning - Start up Testing &amp; Initial Change over testing @20% | 01/06/2021 | 07/06/2021 | 09/04/2021 | 09/04/2021 | 0 | TK_Complete
A3620 | TT_Task | Fuel oil commissioning - Partload combustion tuning (incl NoX Water Tuning) | 01/06/2021 | 07/06/2021 | 10/04/2021 | 11/04/2021 | 0 | TK_Complete
A3630 | TT_Task | Fuel oil commissioning - Baseload combustion tuning (incl NoX Water Tuning) | 01/06/2021 | 07/06/2021 | 12/04/2021 | 12/04/2021 | 0 | TK_Complete
A3640 | TT_Task | Fuel oil commissioning - inspection after initial Fuel Oil preparation (burner filters, MBN,MBU,EG) | 01/06/2021 | 07/06/2021 | 13/04/2021 | 13/04/2021 | 0 | TK_Complete
A3650 | TT_Task | Fuel oil commissioning - Start up testing &amp; Initial Change over testing @ 20% | 01/06/2021 | 07/06/2021 | 14/04/2021 | 14/04/2021 | 0 | TK_Complete
A3660 | TT_Task | Fuel oil commissioning - Start up testing &amp; Initial Change over testing @ 30% | 01/06/2021 | 07/06/2021 | 15/04/2021 | 15/04/2021 | 0 | TK_Complete
A3670 | TT_Task | Fuel oil commissioning - Change over testing @ 40% | 01/06/2021 | 07/06/2021 | 16/04/2021 | 16/04/2021 | 0 | TK_Complete
A3680 | TT_Task | Fuel oil commissioning - Change over testing @ 50% | 01/06/2021 | 07/06/2021 | 17/04/2021 | 17/04/2021 | 0 | TK_Complete
A3690 | TT_Task | Fuel oil commissioning - Change over testing @ 60% | 01/06/2021 | 07/06/2021 | 18/04/2021 | 18/04/2021 | 0 | TK_Complete
A3700 | TT_Task | Fuel oil commissioning - Change over testing @ 70% | 01/06/2021 | 07/06/2021 | 19/04/2021 | 19/04/2021 | 0 | TK_Complete
A3710 | TT_Task | Fuel oil commissioning - Change over testing @ 70% | 01/06/2021 | 07/06/2021 | 20/04/2021 | 20/04/2021 | 0 | TK_Complete
A3720 | TT_Task | Fuel oil commissioning - Inspection of Fuel oil System | 01/06/2021 | 07/06/2021 | 21/04/2021 | 21/04/2021 | 0 | TK_Complete
A3730 | TT_Task | Fuel oil commissioning - Start-up optimisation - high load transfer testing | 01/06/2021 | 07/06/2021 | 22/04/2021 | 23/04/2021 | 0 | TK_Complete
A3740 | TT_Task | Fuel oil commissioning - GT Fuel Gas Baseload operation and automatic changeover to fuel oil operation | 01/06/2021 | 07/06/2021 | 24/04/2021 | 26/04/2021 | 0 | TK_Complete
A3750 | TT_Task | Fuel oil commissioning - Unit Start up and loading to baseload | 01/06/2021 | 07/06/2021 | 27/04/2021 | 27/04/2021 | 0 | TK_Complete
A3760 | TT_Task | Fuel oil commissioning - Phase - C 910 Automatic Start-up of the unit with secondary fuel | 01/06/2021 | 07/06/2021 | 28/04/2021 | 28/04/2021 | 0 | TK_Complete
A3770 | TT_Task | Fuel oil commissioning - Phase - C 932 Load change rates of unit with secondary fuel | 01/06/2021 | 07/06/2021 | 29/04/2021 | 29/04/2021 | 0 | TK_Complete
A3780 | TT_Task | Fuel oil commissioning - Phase - C 966 Fuel changeover in combined cycle mode | 01/06/2021 | 07/06/2021 | 30/04/2021 | 30/04/2021 | 0 | TK_Complete
A3790 | TT_Task | Fuel oil commissioning - Unit Shutdown | 01/06/2021 | 07/06/2021 | 01/05/2021 | 01/05/2021 | 0 | TK_Complete
A3800 | TT_Task | Fuel oil commissioning - Phase - C 910 Automatic Start-up of the unit with secondary fuel | 01/06/2021 | 07/06/2021 | 02/05/2021 | 02/05/2021 | 0 | TK_Complete
A3810 | TT_Task | Fuel oil commissioning - Phase - C 932 Load change rates of unit with secondary fuel | 01/06/2021 | 07/06/2021 | 03/05/2021 | 03/05/2021 | 0 | TK_Complete
A3820 | TT_Task | Fuel oil commissioning - Phase - C 966 Fuel changeover in combined cycle mode | 01/06/2021 | 07/06/2021 | 04/05/2021 | 04/05/2021 | 0 | TK_Complete
A3830 | TT_Task | Performance Test on Oil - Phase - C 956 maximum caoacity of the unit with secondary fuel | 01/06/2021 | 07/06/2021 | 05/05/2021 | 06/05/2021 | 0 | TK_Complete
A3840 | TT_Task | S/D outage - PT and FO Burner Removal | 01/06/2021 | 07/06/2021 | 07/05/2021 | 10/05/2021 | 0 | TK_Complete
A3850 | TT_Task | S/U for PT - Fuel Oil Performance Testing (@100%) | 01/06/2021 | 07/06/2021 | 11/05/2021 | 11/05/2021 | 0 | TK_Complete
A3860 | TT_Task | Restart of Unit - Start SCR RTR - Phase 2 | 01/06/2021 | 07/06/2021 | 12/05/2021 | 12/05/2021 | 0 | TK_Complete
A3870 | TT_Task | SCR RTR Phase 2 | 01/06/2021 | 07/06/2021 | 13/05/2021 | 22/05/2021 | 0 | TK_Complete
A3880 | TT_Task | SCR RTR Phase 3 | 01/06/2021 | 07/06/2021 | 23/05/2021 | 30/05/2021 | 0 | TK_Complete
A3890 | TT_Task | SCR RTR Phase 3 - Handover tp CPL - Section 6 part 2 | 01/06/2021 | 07/06/2021 | 31/05/2021 | 31/05/2021 | 0 | TK_Complete
SI1---2-40 | TT_FinMile | (6c) COMPLETION AND SIGN OFF OF ALL CHECK SHEET TO CONFIRM COMPLETION OF HOT COMMISSIONING | 31/05/2021 | 31/05/2021 | 31/05/2021 | 31/05/2021 | 0 | TK_Complete
SI1---2-45 | TT_FinMile | (6d) COMPLETION OF O&amp;M MANUALS | 16/07/2021 | 16/07/2021 |  |  | 0 | TK_NotStart
SI1---2-50 | TT_FinMile | (6e) COMPLETION OF AS-BUILT DRAWINGS AND OTHER COMPLETION DOCUMENTS | 16/07/2021 | 16/07/2021 |  |  | 0 | TK_NotStart
SI1---3-53 | TT_FinMile | (BOP6) COMPLETION AND SIGN OFF OF ALL CHECK SHEET TO CONFIRM COMPLETION OF HOT COMMISSIONING | 16/07/2021 | 16/07/2021 |  |  | 0 | TK_NotStart
SI-1102-40 | TT_FinMile | FINAL OPERATING AND MAINTENANCE DOCUMENTATION (O&amp;M) | 16/07/2021 | 16/07/2021 |  |  | 0 | TK_NotStart
SI-92-2-96 | TT_FinMile | MARK-UPS FROM SITE AVAILABLE | 16/07/2021 | 16/07/2021 |  |  | 0 | TK_NotStart
SP-92-2-45 | TT_Mile | AS BUILT DOCUMENTATION [submittal to customer] | 16/07/2021 | 16/07/2021 |  |  | 8 | TK_NotStart
PCS00010 | TT_FinMile | Post TB2 P/L | 31/05/2022 | 31/05/2022 |  |  | 0 | TK_NotStart