## Sheet1
ID | TaskType | Label | PlannedStart | PlannedEnd | ActualStart | ActualEnd | Float | Status
THRF1460 | TT_Task | Turbine Hall GL5-7 /C-B (Bay 6b) - Kalbau (DEF_WK07 confirmed not required) | 26/01/2019 | 29/01/2019 | 13/12/2018 | 15/12/2018 | 0 | TK_Complete
CCOM2650 | TT_Task | Commissioning test | 31/08/2019 | 05/09/2019 | 01/11/2019 | 02/11/2019 | 0 | TK_Complete
IBC10320 | TT_Task | Diversion Culvert - Backfill and reinstate quay wall concrete block to 0.5m below 2nd layer of struts | 09/01/2020 | 13/01/2020 | 08/12/2019 | 28/12/2019 | 0 | TK_Complete
SI-GHD2-20 | TT_Task | (BOP) BASIC DESIGN, SPECIFICATION WATER PIPEWORK SYSTEM | 08/05/2017 | 02/07/2017 | 08/04/2017 | 27/06/2017 | 0 | TK_Complete
EV009002 | TT_Task | Event 009 - 2 nos Pre-drill abortive | 03/03/2018 | 31/03/2018 | 30/12/2017 | 26/01/2018 | 0 | TK_Complete
DBC20150 | TT_Task | Discharge Culvert /Zone A3 (Western Section) - Trim pipe piles | 07/01/2020 | 13/01/2020 | 20/12/2019 | 28/12/2019 | 0 | TK_Complete
10MAC-1270 | TT_Task | LP-1 - Check Axial Displacement of Inner Casing | 01/04/2019 | 01/04/2019 | 01/04/2019 | 01/04/2019 | 0 | TK_Complete
SFF30070XX | TT_Task | Shaft F - Construct permanent shaft wall (Pour 3 of 8) | 01/01/2020 | 01/01/2020 | 07/12/2019 | 07/12/2019 | 0 | TK_Complete
00STG20 | TT_Task | Install Containers | 11/03/2019 | 16/03/2019 | 30/04/2019 | 24/05/2019 | 0 | TK_Complete
SFE30165 | TT_Task | Shaft E - Trim pipe piles | 01/01/2020 | 04/01/2020 | 01/01/2020 | 04/01/2020 | 0 | TK_Complete
10MA-1280 | TT_Task | Align Check of Bearing Casings &amp; Baseplates After Grouting | 23/08/2018 | 25/08/2018 | 23/08/2018 | 24/08/2018 | 0 | TK_Complete
10CP-AA20 | TT_Task | Grounding Supports | 30/09/2019 | 10/10/2019 | 25/07/2019 | 31/07/2019 | 0 | TK_Complete
00SGM-01-30 | TT_Task | Hydro Test | 11/10/2019 | 15/10/2019 | 11/10/2019 | 15/10/2019 | 0 | TK_Complete
CCOM2880 | TT_Task | Final check for readiness | 31/08/2019 | 05/09/2019 | 11/11/2019 | 11/11/2019 | 0 | TK_Complete
10GM-02-100 | TT_Task | Install Equipment/Skids/Pumps | 15/04/2019 | 06/05/2019 | 17/04/2019 | 09/07/2019 | 0 | TK_Complete
SI1LCB3B25 | TT_Task | DETAIL DESIGN, MANUFACTURING, SHOP TEST CONDENSATE EXTRACTION PUMP LCB | 26/08/2017 | 14/06/2018 | 08/08/2017 | 24/04/2018 | 0 | TK_Complete
EV008011 | TT_Task | Event 008 - Declaration of unplanted area | 13/12/2017 | 30/12/2017 | 06/12/2017 | 16/12/2017 | 0 | TK_Complete
THSS0460 | TT_Task | Turbine Hall GL.2-4 /D-C (Bay 6a) - Install upper roof steel structure | 14/06/2018 | 15/06/2018 | 23/05/2018 | 24/05/2018 | 0 | TK_Complete
00EK09 | TT_Task | Erection of Blending Station | 30/04/2019 | 22/05/2019 | 25/05/2019 | 27/07/2019 | 0 | TK_Complete
RCWL0110 | TT_Task | Perimeter RC Wall / West Elevation - GL.K -G | 06/08/2018 | 09/08/2018 | 12/04/2018 | 12/05/2018 | 0 | TK_Complete
SI1UMC2I109 | TT_Task | DETAIL DESIGN / CHECKER STEEL MISC. PLATFORM UMC | 03/07/2017 | 16/09/2017 | 09/06/2017 | 04/01/2018 | 0 | TK_Complete
SCWtaBA8 | TT_Task | BA8 - (1st) BD Consent to Temp works for SCW &amp; Culvert Modification (Resubmit incl wall, excav.&amp; anchor)(Wet){5b1(r)} | 26/02/2018 | 27/03/2018 | 29/01/2018 | 26/02/2018 | 0 | TK_Complete
SI1PAH2-80 | TT_Task | QUOTATION STAGE CONDENSER TUBE CLEANING SYSTEM PAH | 14/01/2017 | 14/03/2017 | 30/12/2016 | 21/04/2017 | 0 | TK_Complete
MCGZ0050 | TT_Task | East Elevation at GL.1 / Glazing panels | 11/03/2019 | 02/05/2019 | 24/01/2019 | 03/03/2019 | 0 | TK_Complete
THTT4050 | TT_Task | Turbine Table TT4 - Close formwork (if any) | 01/12/2017 | 01/12/2017 | 01/12/2017 | 01/12/2017 | 0 | TK_Complete
10BZL-01-20 | TT_Task | Install Primary Containment | 08/10/2019 | 22/10/2019 | 12/10/2019 | 17/10/2019 | 0 | TK_Complete
EV017510 | TT_Task | Event 017(I) - Advanced Precautionary Grouting | 26/01/2019 | 08/03/2019 | 27/12/2018 | 09/02/2019 | 0 | TK_Complete
CCOM5080 | TT_Task | PAB System commissioning | 02/07/2020 | 07/07/2020 | 14/01/2020 | 18/01/2020 | 0 | TK_Complete
10SGJ-02-10 | TT_Task | Install Skid+Auxiliaries | 30/09/2019 | 15/10/2019 | 08/10/2019 | 19/10/2019 | 0 | TK_Complete
00EG-02-60 | TT_Task | Hydro Test | 31/07/2019 | 14/08/2019 | 10/08/2019 | 17/08/2019 | 0 | TK_Complete
00GM-02-10 | TT_Task | Install Equipment/Skids/Pumps | 15/04/2019 | 11/05/2019 | 15/04/2019 | 09/07/2019 | 0 | TK_Complete
SI1C--4-27 | TT_Task | ST I&amp;C TRANSPORT TO SITE FIELD INSTRUMENTATION | 26/03/2018 | 24/05/2018 | 16/03/2018 | 13/05/2018 | 0 | TK_Complete
THRF0570XX | TT_Task | Turbine Hall GL.1-5 /C-B (Bay 7a) - Install standing seam roof cladding [Deferred Works] | 02/01/2020 | 02/01/2020 | 19/05/2018 | 19/05/2018 | 0 | TK_Complete
SFF20030 | TT_Task | Shaft F - Micro tunneling and pipe jacking from Shaft E (Part 2 of 2) | 01/11/2019 | 11/11/2019 | 19/09/2019 | 17/10/2019 | 0 | TK_Complete
10MKQ40 | TT_Task | NDE | 09/04/2019 | 20/04/2019 | 09/04/2019 | 19/09/2019 | 0 | TK_Complete
A1900 | TT_Task | Set on Base Boiler Blowdown Vessel | 13/11/2018 | 13/11/2018 | 06/11/2018 | 08/11/2018 | 0 | TK_Complete
EV011110 | TT_Task | Event 011A - Formal test report issued for submission in 7 calendar days | 26/11/2018 | 02/12/2018 | 13/11/2018 | 30/11/2018 | 0 | TK_Complete
A1650 | TT_Task | Placing Hotwell | 07/05/2018 | 07/05/2018 | 05/05/2018 | 19/05/2018 | 0 | TK_Complete
DPT10045 | TT_Task | DPT /Zone A (Southern Section) - BD Consent for Commencement of Excavation &amp; ELS | 18/06/2018 | 15/07/2018 | 18/05/2018 | 22/06/2018 | 0 | TK_Complete
00PUN11 | TT_Task | Install Containers - Skid | 08/06/2019 | 13/06/2019 | 27/06/2019 | 21/09/2019 | 0 | TK_Complete
ITP2130 | TT_Task | ITP for - (00MBU) NOX Water Forwarding System incl. Supply Lines to GT Skid | 06/08/2018 | 29/08/2018 | 19/05/2018 | 15/06/2018 | 0 | TK_Complete
THSS0340 | TT_Task | Turbine Hall GL.1-5 /F-E (Bay 4a) - Connect installed trusses by secondary beams and bracing | 06/06/2018 | 08/06/2018 | 14/05/2018 | 16/05/2018 | 0 | TK_Complete
10LBA80-40 | TT_Task | NDE | 16/04/2019 | 08/06/2019 | 16/04/2019 | 27/09/2019 | 0 | TK_Complete
CCOM2390 | TT_Task | Fans/Pumps cold commissioning | 31/08/2019 | 05/09/2019 | 23/10/2019 | 23/10/2019 | 0 | TK_Complete
SI-BZK3-86 | TT_Task | (BOP) FINAL CHECK BEFORE SHIPMENT MV CABLES BZK | 18/06/2018 | 01/07/2018 | 27/06/2018 | 10/07/2018 | 0 | TK_Complete
RWPR0110 | TT_Task | RW Collection Pump Rm - Pour basement wall and staircase (Part 1 of 2) | 28/01/2019 | 28/01/2019 | 29/11/2018 | 29/11/2018 | 0 | TK_Complete
DPT30140 | TT_Task | DPT /Zone C (Northern Section) - Connect CW supply pipeline to Shaft F | 13/01/2020 | 15/01/2020 | 07/12/2019 | 23/12/2019 | 0 | TK_Complete
CCOM4070 | TT_Task | ready for operation, pending operational licence | 02/07/2020 | 07/07/2020 | 25/11/2019 | 30/11/2019 | 0 | TK_Complete
LIFTDN10 | TT_Task | Lifts - Review engineer's drawings and prepare design (AD TBC) | 21/12/2017 | 17/01/2018 | 21/12/2017 | 13/06/2018 | 0 | TK_Complete
ITP1120 | TT_Task | ITP for - (10MKA) Generator Incl. Bearing System 10 MKD | 02/12/2019 | 25/12/2019 | 08/05/2018 | 05/06/2018 | 0 | TK_Complete
SI1UBF2-45 | TT_Task | PREPARATION BASIC BUILDING DWGS UBF/UBE | 01/06/2017 | 05/07/2017 | 04/05/2017 | 24/05/2017 | 0 | TK_Complete
10MKG40 | TT_Task | NDE | 30/04/2019 | 24/05/2019 | 17/05/2019 | 21/09/2019 | 0 | TK_Complete
00BAW-01-20 | TT_Task | Install Accessories/Supports | 01/04/2019 | 23/04/2019 | 01/04/2019 | 18/05/2019 | 0 | TK_Complete
00LAB80 | TT_Task | Painting/Insulation | 13/08/2019 | 20/09/2019 | 10/08/2019 | 15/10/2019 | 0 | TK_Complete
CCOM4430 | TT_Task | testing of PAC chamber stoplog - dry and wet testing | 02/07/2020 | 07/07/2020 | 18/12/2019 | 21/12/2019 | 0 | TK_Complete
10LCL30 | TT_Task | Install Small Bore Pipe/Valves/Supports | 04/03/2019 | 30/05/2019 | 04/03/2019 | 25/07/2019 | 0 | TK_Complete
BBDP0140 | TT_Task | Boiler Blow Down Pit - Erect wall and column formwork | 27/08/2018 | 30/08/2018 | 26/07/2018 | 28/07/2018 | 0 | TK_Complete
MCGZ0070 | TT_Task | East Elevation at GL.1 / Subframe for aluminum features | 04/04/2019 | 24/04/2019 | 11/02/2019 | 31/05/2019 | 0 | TK_Complete
10MBA1370 | TT_Task | Completion of Gas Turbine | 26/10/2019 | 04/11/2019 | 28/09/2019 | 21/11/2019 | 0 | TK_Complete
ITP1330 | TT_Task | ITP for - (10LCA) Main Condensate Pumps and Supply System for Min. Flow Operation Incl. | 17/09/2018 | 10/10/2018 | 04/06/2018 | 16/07/2018 | 0 | TK_Complete
SFA_BA58b | TT_Task | BA5 - Consent for Temporary works for Shaft A, Pump Station, Diversion Culvert (Excav &amp; ELS) {4b4-4} | 26/05/2018 | 22/06/2018 | 28/06/2018 | 25/07/2018 | 0 | TK_Complete
GENSUB9A | TT_Task | Aluminum - BD Approval | 26/11/2018 | 24/01/2019 | 08/11/2018 | 07/01/2019 | 0 | TK_Complete
POW_BA58_1 | TT_Task | BA8 - Consent for Excav &amp; ELS Plan for Power Island Area (Open Cut)(Phase 3){7c2i} | 22/06/2017 | 19/09/2017 | 26/09/2017 | 20/10/2017 | 0 | TK_Complete
SFA10217XX | TT_Task | Shaft A - Construct 10th layer of 250mm skin wall | 02/09/2019 | 02/09/2019 | 29/05/2019 | 29/05/2019 | 0 | TK_Complete
SFE10200 | TT_Task | Shaft E - Intstall lagging plates and 8th layer of strut | 03/06/2019 | 06/06/2019 | 02/05/2019 | 05/05/2019 | 0 | TK_Complete
SI1MAV4-25 | TT_Task | TRANSPORT LUBE OIL MODUL MAV | 26/01/2018 | 15/03/2018 | 18/01/2018 | 01/04/2018 | 0 | TK_Complete
THRF2452 | TT_Task | Turbine Hall GL.7-10 (Bay 4c) - Deferred Opening | 01/08/2019 | 16/08/2019 | 01/03/2019 | 16/03/2019 | 0 | TK_Complete
10BZL-03-40 | TT_Task | Install Cabling | 04/10/2019 | 01/11/2019 | 14/08/2019 | 28/08/2019 | 0 | TK_Complete
SFF-BA58a | TT_Task | BA5 - Resub.of (Type II) Amendment for Zone A Sheet Pile Alternative {4b1-alt A-1} [APPROVED AS TYPE I] | 27/11/2017 | 26/12/2017 | 24/07/2017 | 22/08/2017 | 0 | TK_Complete
10HSJ120 | TT_Task | Precommissioning | 06/12/2019 | 14/12/2019 | 25/11/2019 | 18/01/2020 | 0 | TK_Complete
RWPR0020 | TT_Task | RW Collection Pump Rm - Vertical blinding to the profile of base slab and shallow sump pit | 26/11/2018 | 28/11/2018 | 31/10/2018 | 31/10/2018 | 0 | TK_Complete
ECS20.1050 | TT_Task | Installation of Cable Support Structure for HRSG | 24/04/2019 | 20/07/2019 | 24/04/2019 | 29/06/2019 | 0 | TK_Complete
Sub-GTST-130 | TT_Task | Bid Technical Evaluation/Review Process | 01/03/2018 | 01/03/2018 | 28/02/2018 | 28/02/2018 | 0 | TK_Complete
ITP1900 | TT_Task | ITP for - (10QU) Sampling Container QC | 19/09/2018 | 12/10/2018 | 20/08/2018 | 11/09/2018 | 0 | TK_Complete
CCWS0010 | TT_Task | Close Cooling Water Structure - Construct foundation and plinths | 09/04/2019 | 29/04/2019 | 25/02/2019 | 04/03/2019 | 0 | TK_Complete