## Sheet1
ID | Label | PlannedStart | PlannedEnd
2 | General | Sat Jan 08 08:00:00 IST 2011 | Tue Jan 26 17:00:00 IST 2016
3 | Schedule of Key Dates | Sat Jan 08 08:00:00 IST 2011 | Tue Jan 26 17:00:00 IST 2016
4 | General | Sat Jan 08 08:00:00 IST 2011 | Tue Jan 26 17:00:00 IST 2016
5 | Letter of Acceptance | Sat Jan 08 08:00:00 IST 2011 | Sat Jan 08 08:00:00 IST 2011
6 | Date of Commencement | Sat Jan 08 08:00:00 IST 2011 | Sat Jan 08 08:00:00 IST 2011
7 | Completion whole of the Works (Excluding Options I3 & I4) | Sun May 10 17:00:00 IDT 2015 | Sun May 10 17:00:00 IDT 2015
8 | Completion whole of the Works (Including Options I3 & I4) | Tue Jan 26 17:00:00 IST 2016 | Tue Jan 26 17:00:00 IST 2016
9 | Table 4 - Specified Degress of completion of the Works | Sun Aug 18 17:00:00 IDT 2013 | Sun Apr 19 17:00:00 IDT 2015
10 | Target Dates for Supplementary Agreement No.3 | Sun May 18 17:00:00 IDT 2014 | Sun Apr 19 17:00:00 IDT 2015
11 | Deg.1 Completion (Target Dates) | Sun May 18 17:00:00 IDT 2014 | Sun Apr 19 17:00:00 IDT 2015
12 | Ref.4A(ii): D/TTunnel from CH137+860 to Southern Contract Limit & 811A D/T C&C Section(Deg.1:20-Jul-14&Target:18-May-14) | Sun May 18 17:00:00 IDT 2014 | Sun May 18 17:00:00 IDT 2014
13 | Ref.4B(i): Up Track tunnel from the Northern Contract Limit to CH137+860 (Deg.1: 29-Jun-14 & Target: 1-Jun-14) | Sun Jun 29 08:00:00 IDT 2014 | Sun Jun 29 08:00:00 IDT 2014
14 | Ref.4B(ii): U/T South Tunnel from CH137+860 to 950m from the Southern Contract Limit (Deg.1: 8Mar15 & Target: 21Dec14) | Tue Dec 16 17:00:00 IST 2014 | Tue Dec 16 17:00:00 IST 2014
15 | Ref.4B(iii): U/T Tunnel from CH137+860 to Southern Contract Limit & 811A U/T C&C Section(Deg.1: 12Apr15&Target: 25Jan15) | Fri Mar 13 17:00:00 IST 2015 | Fri Mar 13 17:00:00 IST 2015
16 | Ref.4D: Closure of Temp. Access Opening & Central Opening Structure within NAC Shaft (Deg.1: 3May15 & Target: 19Apr15) | Sun Apr 19 17:00:00 IDT 2015 | Sun Apr 19 17:00:00 IDT 2015
17 | Completion of Specified Degrees of Completion of the Works | Sun Aug 18 17:00:00 IDT 2013 | Sun Apr 19 17:00:00 IDT 2015
18 | Deg.1 Completion | Sun Aug 18 17:00:00 IDT 2013 | Sun Apr 19 17:00:00 IDT 2015
19 | Ref.4A(i): Down Track tunnel from the Northern Contract Limit to CH137+860 incl. provision of Temp. access opening | Sun Aug 18 17:00:00 IDT 2013 | Sun Aug 18 17:00:00 IDT 2013
20 | Ref.4C(i): All Rooms and Common Areas at Level L2, UL2, L1 and UL1 (Excl. staircases, Lift shaft & CLP risers) | Sun Dec 22 17:00:00 IST 2013 | Sun Dec 22 17:00:00 IST 2013
21 | Ref.4C(ii): All Rooms and Common Areas at Track level and Above Track level(Excl. staircases, Lift shaft & CLP risers) | Sun Mar 02 17:00:00 IST 2014 | Sun Mar 02 17:00:00 IST 2014
22 | Ref.4C(iii): All Rooms and Common Areas within VB7 [Excl. the parts of the VB7 under Ref. 4C(i) & 4C(ii)] | Sat May 31 17:00:00 IDT 2014 | Sat May 31 17:00:00 IDT 2014
23 | Ref.4B(i): Up Track tunnel from the Northern Contract Limit to CH137+860 (Deg.1: 29-Jun-14 & Target: 1-Jun-14) | Sun Jun 29 17:00:00 IDT 2014 | Sun Jun 29 17:00:00 IDT 2014
24 | Ref.4A(ii): D/TTunnel from CH137+860 to Southern Contract Limit & 811A D/T C&C Section(Deg.1:20-Jul-14&Target:18-May-14) | Sun May 18 17:00:00 IDT 2014 | Sun May 18 17:00:00 IDT 2014
25 | Ref.4B(ii): U/T South Tunnel from CH137+860 to 950m from the Southern Contract Limit (Deg.1: 8Mar15 & Target: 21Dec14) | Tue Dec 16 17:00:00 IST 2014 | Tue Dec 16 17:00:00 IST 2014
26 | Ref.4B(iii): U/T Tunnel from CH137+860 to Southern Contract Limit & 811A U/T C&C Section(Deg.1: 12Apr15&Target: 25Jan15) | Fri Mar 13 17:00:00 IST 2015 | Fri Mar 13 17:00:00 IST 2015
27 | Ref.4D: Closure of Temp. Access Opening & Central Opening Structure within NAC Shaft (Deg.1: 3May15 & Target: 19Apr15) | Sun Apr 19 17:00:00 IDT 2015 | Sun Apr 19 17:00:00 IDT 2015
28 | Deg.2 Completion | Sun Feb 23 17:00:00 IST 2014 | Wed Jul 23 17:00:00 IDT 2014
29 | Ref.4C(i) Deg.2: All Rooms and Common Areas at Level L2, UL2, L1 and UL1 (Excl. staircases, Lift shaft & CLP risers) | Sun Feb 23 17:00:00 IST 2014 | Sun Feb 23 17:00:00 IST 2014
30 | Ref.4C(ii) Deg.2: All Rooms and Common Areas at Track level and AT level(Excl. staircases, Lift shaft & CLP risers) | Sun Mar 23 17:00:00 IST 2014 | Sun Mar 23 17:00:00 IST 2014
31 | Ref.4C(iii) Deg.2: All Rooms and Common Areas within VB7 [Excl. the parts of the VB7 under Ref. 4C(i) & 4C(ii)] | Wed Jul 23 17:00:00 IDT 2014 | Wed Jul 23 17:00:00 IDT 2014
32 | Deg.3 Completion | Sun Apr 20 17:00:00 IDT 2014 | Thu Sep 18 17:00:00 IDT 2014
33 | Ref.4C(i) Deg.3: All Rooms and Common Areas at Level L1, UL2, L1 and UL1 (Excl. staircases, Lift shaft & CLP risers) | Sun Apr 20 17:00:00 IDT 2014 | Sun Apr 20 17:00:00 IDT 2014
34 | Ref.4C(ii) Deg.3: All Rooms and Common Areas at Track level and AT level(Excl. staircases, Lift shaft & CLP risers) | Sun May 18 17:00:00 IDT 2014 | Sun May 18 17:00:00 IDT 2014
35 | Ref.4C(iii) Deg.3: All Rooms and Common Areas within VB7 [Excl. the parts of the VB7 under Ref. 4C(i) & 4C(ii)] | Thu Sep 18 17:00:00 IDT 2014 | Thu Sep 18 17:00:00 IDT 2014
36 | Schedule of Access Dates and Vacation Dates | Sat May 15 08:00:00 IDT 2010 | Tue May 10 17:00:00 IDT 2016
37 | Access Date | Sat May 15 08:00:00 IDT 2010 | Mon Jan 21 08:00:00 IST 2013
38 | General | Sat May 15 08:00:00 IDT 2010 | Mon Jan 21 08:00:00 IST 2013
39 | Works Area 10.1 (Subject to SLG Approval) | Sat Jan 08 08:00:00 IST 2011 | Sat Jan 08 08:00:00 IST 2011
40 | Works Area 10.2 | Sat Jan 08 08:00:00 IST 2011 | Sat Jan 08 08:00:00 IST 2011
41 | Works Area 10.3 | Sat Jan 08 08:00:00 IST 2011 | Sat Jan 08 08:00:00 IST 2011
42 | Works Area 10.3U subject to MTR Railway Operation Approval | Thu Sep 29 08:00:00 IDT 2011 | Thu Sep 29 08:00:00 IDT 2011
43 | Works Area 10.4 | Sat Jan 08 08:00:00 IST 2011 | Sat Jan 08 08:00:00 IST 2011
44 | Works Area 11.1 | Mon Apr 09 08:00:00 IDT 2012 | Mon Apr 09 08:00:00 IDT 2012
45 | Works Area 11.2 | Mon Apr 09 08:00:00 IDT 2012 | Mon Apr 09 08:00:00 IDT 2012
46 | Works Area 11.10A | Mon Feb 06 08:00:00 IST 2012 | Mon Feb 06 08:00:00 IST 2012
47 | Works Area 11.10B | Mon Feb 06 08:00:00 IST 2012 | Mon Feb 06 08:00:00 IST 2012
48 | Works Area 11.12 (Subject to SLG Approval) | Sat Jan 08 08:00:00 IST 2011 | Sat Jan 08 08:00:00 IST 2011
49 | Works Area 11.13 (conform by Engineer) | Mon Dec 31 08:00:00 IST 2012 | Mon Dec 31 08:00:00 IST 2012
50 | Works Area 11.14 | Mon Dec 10 08:00:00 IST 2012 | Mon Dec 10 08:00:00 IST 2012
51 | Works Area 11.15 (Subject to SLG Approval) | Sat Jan 08 08:00:00 IST 2011 | Sat Jan 08 08:00:00 IST 2011
52 | Works Area 11.21 (Subject to SLG Approval) | Sat Jan 08 08:00:00 IST 2011 | Sat Jan 08 08:00:00 IST 2011
53 | Works Area 11.21A (Subject to SLG Approval) | Wed Aug 31 08:00:00 IDT 2011 | Wed Aug 31 08:00:00 IDT 2011
54 | Works Area 11.22 | Sat Jan 08 08:00:00 IST 2011 | Sat Jan 08 08:00:00 IST 2011
55 | Works Area 11.23 | Sat Jan 08 08:00:00 IST 2011 | Sat Jan 08 08:00:00 IST 2011
56 | Works Area 11.23A | Sat Jan 08 08:00:00 IST 2011 | Sat Jan 08 08:00:00 IST 2011
57 | Works Area 11.23B | Sat Jan 08 08:00:00 IST 2011 | Sat Jan 08 08:00:00 IST 2011
58 | Works Area 11.24 (1st Possession) | Sat Jan 08 08:00:00 IST 2011 | Sat Jan 08 08:00:00 IST 2011
59 | Works Area 11.25 (1st Posssession) | Sat Jan 08 08:00:00 IST 2011 | Sat Jan 08 08:00:00 IST 2011
60 | Works Area 11.26A | Sat Jan 08 08:00:00 IST 2011 | Sat Jan 08 08:00:00 IST 2011
61 | Works Area 11.26B | Sat Jan 08 08:00:00 IST 2011 | Sat Jan 08 08:00:00 IST 2011
62 | Works Area 11.26C | Sat Jan 08 08:00:00 IST 2011 | Sat Jan 08 08:00:00 IST 2011
63 | Works Area 11.27 (Subject to SLG Approval) | Sat Jan 08 08:00:00 IST 2011 | Sat Jan 08 08:00:00 IST 2011
64 | Wks Area 11.28-180day from Contractor's Confirm | Mon Jan 21 08:00:00 IST 2013 | Mon Jan 21 08:00:00 IST 2013
65 | Works Area 11.29A | Sat Jan 08 08:00:00 IST 2011 | Sat Jan 08 08:00:00 IST 2011
66 | Works Area 11.29B | Sat Jan 08 08:00:00 IST 2011 | Sat Jan 08 08:00:00 IST 2011
67 | Works Area 11.29C | Sat May 15 08:00:00 IDT 2010 | Sat May 15 08:00:00 IDT 2010
68 | Works Area 11.29D | Sat May 15 08:00:00 IDT 2010 | Sat May 15 08:00:00 IDT 2010
69 | Works Area 11.29E | Sat May 15 08:00:00 IDT 2010 | Sat May 15 08:00:00 IDT 2010
70 | Works Area 11.29F | Sat May 15 08:00:00 IDT 2010 | Sat May 15 08:00:00 IDT 2010
71 | Works Area 11.29G | Sat May 15 08:00:00 IDT 2010 | Sat May 15 08:00:00 IDT 2010
72 | Works Area 11.30 | Sat May 15 08:00:00 IDT 2010 | Sat May 15 08:00:00 IDT 2010
73 | Works Area 11.31 | Sat May 15 08:00:00 IDT 2010 | Sat May 15 08:00:00 IDT 2010
74 | Works Area 11.32 | Sat May 15 08:00:00 IDT 2010 | Sat May 15 08:00:00 IDT 2010
75 | Works Area 11.33A | Sat May 15 08:00:00 IDT 2010 | Sat May 15 08:00:00 IDT 2010
76 | Works Area 11.33B | Sat May 15 08:00:00 IDT 2010 | Sat May 15 08:00:00 IDT 2010
77 | Works Area 12.1 (Subject to SLG Approval) | Sat Jan 08 08:00:00 IST 2011 | Sat Jan 08 08:00:00 IST 2011
78 | Works Area 12.2 | Fri Nov 30 08:00:00 IST 2012 | Fri Nov 30 08:00:00 IST 2012
79 | Proposed Return Date | Sun May 31 08:00:00 IDT 2015 | Thu Dec 24 17:00:00 IST 2015
80 | Site 6 | Thu Dec 24 17:00:00 IST 2015 | Thu Dec 24 17:00:00 IST 2015
81 | Proposed Return date of Works Area 11.23 (820 Site Office & Site 6) | Thu Dec 24 17:00:00 IST 2015 | Thu Dec 24 17:00:00 IST 2015
82 | Proposed Return date of Works Area 11.23A (Site 6) | Thu Dec 24 17:00:00 IST 2015 | Thu Dec 24 17:00:00 IST 2015
83 | Proposed Return date of Works Area 11.23B (Site 6) | Thu Dec 24 17:00:00 IST 2015 | Thu Dec 24 17:00:00 IST 2015
84 | Proposed Return date of Works Area 11.24 (Site 6) | Thu Dec 24 17:00:00 IST 2015 | Thu Dec 24 17:00:00 IST 2015
85 | Barging Point | Sun May 31 08:00:00 IDT 2015 | Sun May 31 08:00:00 IDT 2015
86 | Proposed Return date of Works Area 11.29A (Barging point) | Sun May 31 08:00:00 IDT 2015 | Sun May 31 08:00:00 IDT 2015
87 | Proposed Return date of Works Area 11.29D (Barging point) | Sun May 31 08:00:00 IDT 2015 | Sun May 31 08:00:00 IDT 2015
88 | Proposed Return date of Works Area 11.29E (Barging point) | Sun May 31 08:00:00 IDT 2015 | Sun May 31 08:00:00 IDT 2015
89 | Proposed Return date of Works Area 11.29F (Barging point) | Sun May 31 08:00:00 IDT 2015 | Sun May 31 08:00:00 IDT 2015
90 | 811A Shaft | Thu Aug 27 17:00:00 IDT 2015 | Thu Aug 27 17:00:00 IDT 2015
91 | Proposed Return date of Works Area 12.2 (811A shaft area) | Thu Aug 27 17:00:00 IDT 2015 | Thu Aug 27 17:00:00 IDT 2015
92 | Return date | Mon Feb 28 08:00:00 IST 2011 | Tue May 10 17:00:00 IDT 2016
93 | General | Mon Feb 28 08:00:00 IST 2011 | Tue May 10 17:00:00 IDT 2016
94 | Works Area 10.1 (Subject to SLG Approval) | Sun May 31 08:00:00 IDT 2015 | Sun May 31 08:00:00 IDT 2015
95 | Works Area 10.2 | Sun May 31 08:00:00 IDT 2015 | Sun May 31 08:00:00 IDT 2015
96 | Works Area 10.3 | Sun May 31 08:00:00 IDT 2015 | Sun May 31 08:00:00 IDT 2015
97 | Works Area 10.3U subject to MTR Approval | Sun May 31 08:00:00 IDT 2015 | Sun May 31 08:00:00 IDT 2015
98 | Works Area 10.4 | Sun May 31 08:00:00 IDT 2015 | Sun May 31 08:00:00 IDT 2015
99 | Works Area 11.1 (Nan cheong Station - by XRL802) | Sun Dec 30 17:00:00 IST 2012 | Sun Dec 30 17:00:00 IST 2012
100 | Works Area 11.2 (Nan cheong Station - by XRL802) | Sun Dec 30 17:00:00 IST 2012 | Sun Dec 30 17:00:00 IST 2012
101 | Works Area 11.10A | Tue Sep 10 17:00:00 IDT 2013 | Tue Sep 10 17:00:00 IDT 2013
102 | Works Area 11.10B | Sun May 31 08:00:00 IDT 2015 | Sun May 31 08:00:00 IDT 2015
103 | Works Area 11.12 (Subject to SLG Approval) | Sun May 31 08:00:00 IDT 2015 | Sun May 31 08:00:00 IDT 2015
104 | Works Area 11.13 (Earliest) | Sun Dec 29 17:00:00 IST 2013 | Sun Dec 29 17:00:00 IST 2013
105 | Works Area 11.13 (Latest) | Sun May 31 08:00:00 IDT 2015 | Sun May 31 08:00:00 IDT 2015
106 | Works Area 11.14 | Sun May 31 08:00:00 IDT 2015 | Sun May 31 08:00:00 IDT 2015
107 | Works Area 11.15 (Subject to SLG Approval) | Sun May 31 08:00:00 IDT 2015 | Sun May 31 08:00:00 IDT 2015
108 | Works Area 11.21 (Subject to SLG Approval) | Sun May 31 08:00:00 IDT 2015 | Sun May 31 08:00:00 IDT 2015
109 | Works Area 11.21A (Subject to SLG Approval) | Sun May 31 08:00:00 IDT 2015 | Sun May 31 08:00:00 IDT 2015
110 | Works Area 11.22 | Sun Dec 27 17:00:00 IST 2015 | Sun Dec 27 17:00:00 IST 2015
111 | Works Area 11.23 (Site 6) | Sun May 31 08:00:00 IDT 2015 | Sun May 31 08:00:00 IDT 2015
112 | Works Area 11.23A (Site 6) (excl. Optional Works I3 & I4) | Mon Aug 24 17:00:00 IDT 2015 | Mon Aug 24 17:00:00 IDT 2015
113 | Works Area 11.23B (Site 6) (excl. Optional Works I3 & I4) | Mon Aug 24 17:00:00 IDT 2015 | Mon Aug 24 17:00:00 IDT 2015
114 | Works Area 11.24 (Site 6) (Earliest) | Sun Mar 31 17:00:00 IDT 2013 | Sun Mar 31 17:00:00 IDT 2013
115 | Works Area 11.24 (Site 6) (Latest) | Mon Aug 24 17:00:00 IDT 2015 | Mon Aug 24 17:00:00 IDT 2015
116 | Works Area 11.25 (Site 6) (Earliest) | Sun Mar 31 17:00:00 IDT 2013 | Sun Mar 31 17:00:00 IDT 2013
117 | Works Area 11.25 (Latest) | Sun Apr 03 17:00:00 IDT 2016 | Sun Apr 03 17:00:00 IDT 2016
118 | Works Area 11.26A (excl. Optional Works I3 & I4) | Sun Apr 03 17:00:00 IDT 2016 | Sun Apr 03 17:00:00 IDT 2016
119 | Works Area 11.26B | Sun Apr 03 17:00:00 IDT 2016 | Sun Apr 03 17:00:00 IDT 2016
120 | Works Area 11.26C | Sun Apr 03 17:00:00 IDT 2016 | Sun Apr 03 17:00:00 IDT 2016
121 | Works Area 11.27 (Subject to SLG Approval) | Tue Aug 11 17:00:00 IDT 2015 | Tue Aug 11 17:00:00 IDT 2015
122 | Wks Area 11.28 | Sun May 31 08:00:00 IDT 2015 | Sun May 31 08:00:00 IDT 2015
123 | Works Area 11.29A | Sun May 31 08:00:00 IDT 2015 | Sun May 31 08:00:00 IDT 2015
124 | Works Area 11.29B | Mon Feb 28 08:00:00 IST 2011 | Mon Feb 28 08:00:00 IST 2011
125 | Works Area 11.29C | Mon Feb 28 08:00:00 IST 2011 | Mon Feb 28 08:00:00 IST 2011
126 | Works Area 11.29D | Sun May 31 08:00:00 IDT 2015 | Sun May 31 08:00:00 IDT 2015
127 | Works Area 11.29E | Sun May 31 08:00:00 IDT 2015 | Sun May 31 08:00:00 IDT 2015
128 | Works Area 11.29F | Sun May 31 08:00:00 IDT 2015 | Sun May 31 08:00:00 IDT 2015
129 | Works Area 11.29G | Mon Feb 28 08:00:00 IST 2011 | Mon Feb 28 08:00:00 IST 2011
130 | Works Area 11.30 | Sun Dec 29 17:00:00 IST 2013 | Sun Dec 29 17:00:00 IST 2013
131 | Works Area 11.31 | Sun May 31 08:00:00 IDT 2015 | Sun May 31 08:00:00 IDT 2015
132 | Works Area 11.32 | Sun May 31 08:00:00 IDT 2015 | Sun May 31 08:00:00 IDT 2015
133 | Works Area 11.33A | Tue May 10 17:00:00 IDT 2016 | Tue May 10 17:00:00 IDT 2016
134 | Works Area 11.33B | Tue May 10 17:00:00 IDT 2016 | Tue May 10 17:00:00 IDT 2016
135 | Works Area 12.1 (Subject to SLG Approval) | Tue May 10 17:00:00 IDT 2016 | Tue May 10 17:00:00 IDT 2016
136 | Works Area 12.2 (811A shaft area) | Sun May 31 08:00:00 IDT 2015 | Sun May 31 08:00:00 IDT 2015
137 | Access & Return Dates for Option I3 & I4 | Sat Jan 08 08:00:00 IST 2011 | Sun Apr 03 17:00:00 IDT 2016
138 | General | Sat Jan 08 08:00:00 IST 2011 | Sun Apr 03 17:00:00 IDT 2016
139 | Works Area 11.23B | Sat Jan 08 08:00:00 IST 2011 | Sat Jan 08 08:00:00 IST 2011
140 | Works Area 11.26A | Sat Jan 08 08:00:00 IST 2011 | Sat Jan 08 08:00:00 IST 2011
141 | Works Area 11.26B | Sat Jan 08 08:00:00 IST 2011 | Sat Jan 08 08:00:00 IST 2011
142 | Works Area 11.23B | Sun Nov 22 17:00:00 IST 2015 | Sun Nov 22 17:00:00 IST 2015
143 | Works Area 11.26A | Sun Apr 03 17:00:00 IDT 2016 | Sun Apr 03 17:00:00 IDT 2016
144 | Works Area 11.26B | Sun Apr 03 17:00:00 IDT 2016 | Sun Apr 03 17:00:00 IDT 2016
145 | Programme Data | Mon Feb 28 08:00:00 IST 2011 | Fri Jul 24 17:00:00 IDT 2015
146 | Schedule of Power On Dates | Thu Feb 05 17:00:00 IST 2015 | Thu Feb 05 17:00:00 IST 2015
147 | Permanent LV Power On | Thu Feb 05 17:00:00 IST 2015 | Thu Feb 05 17:00:00 IST 2015
148 | General
149 | Works Required for Statutory Inspection | Fri Jul 24 17:00:00 IDT 2015 | Fri Jul 24 17:00:00 IDT 2015
150 | Complete all External Water works within the Site and Connect to Governemnt Water Mains | Fri Jul 24 17:00:00 IDT 2015 | Fri Jul 24 17:00:00 IDT 2015
151 | Complete all External Telephone Drawpits and Ducts within the Site | Fri Jul 24 17:00:00 IDT 2015 | Fri Jul 24 17:00:00 IDT 2015
152 | General
153 | Temporary Access Opening for Designated Contractors | Mon Aug 26 08:00:00 IDT 2013 | Sun Jan 04 17:00:00 IST 2015
154 | Access Central Opening within Launching Shaft | Mon Aug 26 08:00:00 IDT 2013 | Sun Jan 04 17:00:00 IST 2015
155 | General
156 | Close out Temporary Access Opening & Structure within Launching Shaft | Sun Dec 01 08:00:00 IST 2013 | Sun May 31 08:00:00 IDT 2015
157 | Area 1 - South Opening, South D/T | Sun Dec 01 08:00:00 IST 2013 | Sun May 18 17:00:00 IDT 2014
158 | Area 1 - Walkway, Side Walls and Above-Track Roof Slab | Sun Dec 01 08:00:00 IST 2013 | Sun May 18 17:00:00 IDT 2014
159 | Area 2 - Central Opening, South D/T | Mon May 19 08:00:00 IDT 2014 | Sun Jun 15 17:00:00 IDT 2014
160 | Area 2 - 1st cast for Walkway and External wall (Dkb137+850 to 137+885) | Mon May 19 08:00:00 IDT 2014 | Sun Jun 15 17:00:00 IDT 2014
161 | Area 3 - South Opening, South U/T | Mon Sep 01 08:00:00 IDT 2014 | Sun Dec 21 17:00:00 IST 2014
162 | Area 3 - 1st cast for Walkway, External wall and Internal wall | Mon Sep 01 08:00:00 IDT 2014 | Sun Dec 21 17:00:00 IST 2014
163 | Area 3 - 2nd cast for Above-Track Roof Slab | Sat Nov 15 08:00:00 IST 2014 | Fri Dec 19 17:00:00 IST 2014
164 | Area 4A - Central Opening, South U/T | Mon Dec 29 08:00:00 IST 2014 | Sun Jan 25 17:00:00 IST 2015
165 | Area 4A - Walkway and External wall (Dkb137+850 to 137+885) | Mon Dec 29 08:00:00 IST 2014 | Sun Jan 25 17:00:00 IST 2015
166 | Area 4B - Central Opening | Mon Dec 29 08:00:00 IST 2014 | Sun Feb 08 17:00:00 IST 2015
167 | Area 4B - 2nd cast for Internal walls and Central portion of Above-Track Roof Slab with falsework | Mon Dec 29 08:00:00 IST 2014 | Sun Feb 08 17:00:00 IST 2015
168 | Area 4C - Central Opening and Access for 830 Works Train | Mon Dec 29 08:00:00 IST 2014 | Sun Apr 19 17:00:00 IDT 2015
169 | Area 4C - Close remaining Above-Track Roof Slab & RC duct btw Dkb137+850 to 137+885 | Mon Dec 29 08:00:00 IST 2014 | Sun Apr 19 17:00:00 IDT 2015
170 | Site 6 - Surafce Works Area under 30T Gantry Crane at Central Opening | Sun May 31 08:00:00 IDT 2015 | Sun May 31 08:00:00 IDT 2015
171 | Site 6 - Access to works area under 30T gantry to be given to 830 | Sun May 31 08:00:00 IDT 2015 | Sun May 31 08:00:00 IDT 2015
172 | Area 5 - 811A C&C Tunnel
173 | TBM Retrieval Shaft at Hoi Ting Road | Mon Feb 28 08:00:00 IST 2011 | Sun Jun 19 17:00:00 IDT 2011
174 | General | Mon Feb 28 08:00:00 IST 2011 | Sun Jun 19 17:00:00 IDT 2011
175 | Completion D-Wall of TBM Retrieval Shaft at Hoi Ting Rd. by 811A | Mon Feb 28 08:00:00 IST 2011 | Mon Feb 28 08:00:00 IST 2011
176 | Earliest Access Date - Ground Level of Works Area 12.2 | Mon Feb 28 08:00:00 IST 2011 | Mon Feb 28 08:00:00 IST 2011
177 | Ground Treatment Completion by 820 | Sun Jun 19 17:00:00 IDT 2011 | Sun Jun 19 17:00:00 IDT 2011
178 | Obstruction Removed by Other Project Contractor | Sun Jan 15 08:00:00 IST 2012 | Tue Apr 30 17:00:00 IDT 2013
179 | General | Sun Jan 15 08:00:00 IST 2012 | Tue Apr 30 17:00:00 IDT 2013
180 | D/T Remove Obstructions Below Nam Cheong Property Development (by XRL 802) | Mon Apr 30 17:00:00 IDT 2012 | Mon Apr 30 17:00:00 IDT 2012
181 | U/T Remove Obstructions Below Nam Cheong Property Development (by XRL 802) | Tue Apr 30 17:00:00 IDT 2013 | Tue Apr 30 17:00:00 IDT 2013
182 | Remove Obstructions Below CLP Equipment Building (by XRL 805) | Sun Jan 15 08:00:00 IST 2012 | Sun Jan 15 08:00:00 IST 2012
183 | Engineer's Office | Sun Apr 17 17:00:00 IDT 2011 | Sun Apr 17 17:00:00 IDT 2011
184 | General | Sun Apr 17 17:00:00 IDT 2011 | Sun Apr 17 17:00:00 IDT 2011
185 | Engineer's Office Completion with Furniture | Sun Apr 17 17:00:00 IDT 2011 | Sun Apr 17 17:00:00 IDT 2011
186 | Access Dates for Designated Contractors | Mon Aug 19 08:00:00 IDT 2013 | Mon Apr 27 08:00:00 IDT 2015
187 | 827 - Supply and Installation of Cross Passage Doors | Mon Aug 26 08:00:00 IDT 2013 | Mon Jan 26 08:00:00 IST 2015
188 | 827 - D/T All Cross Passages for Door Frame & Door Installation, from CH137+860 to Southern contract limit | Mon May 19 08:00:00 IDT 2014 | Mon May 19 08:00:00 IDT 2014
189 | 827 - D/T All Cross Passages for Door Frame and Door installation, from northern contract limit to CH137+860 | Mon Aug 26 08:00:00 IDT 2013 | Mon Aug 26 08:00:00 IDT 2013
190 | 827 - U/T All Cross Passages for Door Frame & Door Installation, from Northern contract limit to CH137+860 | Mon Jun 02 08:00:00 IDT 2014 | Mon Jun 02 08:00:00 IDT 2014
191 | 827 - U/T All Cross Passages for Door Frame & Door Installation, from CH137+860 to 950m from the Southern contract limit | Mon Dec 22 08:00:00 IST 2014 | Mon Dec 22 08:00:00 IST 2014
192 | 827 - U/T All Cross Passages for Door Frame & Door Installation, from CH137+860 to the Southern contract limit | Mon Jan 26 08:00:00 IST 2015 | Mon Jan 26 08:00:00 IST 2015
193 | 830 - Trackwork and Overhead Line System | Mon Aug 19 08:00:00 IDT 2013 | Mon Jan 26 08:00:00 IST 2015
194 | 830 - D/T Tunnel from the Northern contract limit to CH137+860 | Mon Aug 19 08:00:00 IDT 2013 | Mon Aug 19 08:00:00 IDT 2013
195 | 830 - D/T Tunnel from CH137+860 to Southern contract limit and C&C section within Hoi Ting Road Shaft | Mon May 19 08:00:00 IDT 2014 | Mon May 19 08:00:00 IDT 2014
196 | 830 - U/T Tunnel from the Northern contract limit to CH137+860 | Mon Jun 02 08:00:00 IDT 2014 | Mon Jun 02 08:00:00 IDT 2014
197 | 830 - U/T Tunnel from CH137+860 to 950m from the Southern contract limit | Mon Dec 22 08:00:00 IST 2014 | Mon Dec 22 08:00:00 IST 2014
198 | 830 - U/T Tunnel from CH137+860 to the Southern contract limit and C&C section within Hoi Ting Road Shaft | Mon Jan 26 08:00:00 IST 2015 | Mon Jan 26 08:00:00 IST 2015
199 | 841A - Signalling System - Trackside Equipment | Mon Apr 21 08:00:00 IDT 2014 | Mon Apr 27 08:00:00 IDT 2015
200 | 841A - U/T Tunnel from CH137+860 to the Southern contract limit and C&C section within Hoi Ting Road Shaft | Mon Apr 27 08:00:00 IDT 2015 | Mon Apr 27 08:00:00 IDT 2015
201 | 841A - U/T Tunnel from the Northern contract limit to CH137+860 | Sun Nov 30 08:00:00 IST 2014 | Sun Nov 30 08:00:00 IST 2014
202 | 841A - Nam Cheong Ventilation Building (VB7) - SER (Signalling-Trackside) | Mon Apr 21 08:00:00 IDT 2014 | Mon Apr 21 08:00:00 IDT 2014
203 | 841A - D/T Tunnel from the Northern contract limit to CH137+860 | Mon Jun 02 08:00:00 IDT 2014 | Mon Jun 02 08:00:00 IDT 2014
204 | 841A - D/T Tunnel from CH137+860 to the Southern contract limit and C&C section within Hoi Ting Road Shaft | Mon Sep 29 08:00:00 IDT 2014 | Mon Sep 29 08:00:00 IDT 2014
205 | 841B - Signalling System - Train Borne Equipment (Rolling Stock + Works / Rescue Trains) | Mon Apr 21 08:00:00 IDT 2014 | Mon Apr 27 08:00:00 IDT 2015
206 | 841B - U/T Tunnel from the Northern contract limit to CH137+860 (Signalling-Train Borne) | Mon Sep 29 08:00:00 IDT 2014 | Mon Sep 29 08:00:00 IDT 2014
207 | 841B - D/T Tunnel from the Northern contract limit to CH137+860 (Signalling-Train Borne) | Mon Jun 02 08:00:00 IDT 2014 | Mon Jun 02 08:00:00 IDT 2014
208 | 841B - Nam Cheong Ventilation Building (VB7) - SER (Signalling-Train Borne) | Mon Apr 21 08:00:00 IDT 2014 | Mon Apr 21 08:00:00 IDT 2014
209 | 841B - U/T Tunnel from CH137+860 to the Southern contract limit and C&C section within Hoi Ting Road Shaft | Mon Apr 27 08:00:00 IDT 2015 | Mon Apr 27 08:00:00 IDT 2015
210 | 841B - D/T Tunnel from CH137+860 to the Southern contract limit and C&C section within Hoi Ting Road Shaft | Mon Sep 29 08:00:00 IDT 2014 | Mon Sep 29 08:00:00 IDT 2014
211 | 843 - Tunnel Environmental Control System | Mon Feb 24 08:00:00 IST 2014 | Mon Apr 20 08:00:00 IDT 2015
212 | 843 - Nam Cheong Ventilation Building (VB7) - TVF Room and Compressed & Receiver Air Room | Mon Feb 24 08:00:00 IST 2014 | Mon Feb 24 08:00:00 IST 2014
213 | 843 - Nam Cheong Ventilation Building (VB7) - Tunnel ECS Control Room | Mon Jul 14 08:00:00 IDT 2014 | Mon Jul 14 08:00:00 IDT 2014
214 | 843 - Nam Cheong Ventilation Building (VB7) - Above track slab at both up and down tracks btw GL 1-9 | Mon Mar 24 08:00:00 IST 2014 | Mon Mar 24 08:00:00 IST 2014
215 | 843 - Nam Cheong Shaft C & C tunnels - Above track slab at both up and down tracks btw GL 9-16 | Mon Apr 20 08:00:00 IDT 2015 | Mon Apr 20 08:00:00 IDT 2015
216 | 844 - 11kV Power Distribution | Mon Jun 02 08:00:00 IDT 2014 | Mon Apr 27 08:00:00 IDT 2015
217 | 844 - D/T Tunnel from the Northern contract limit to CH137+860 (11kV Power) | Mon Jun 02 08:00:00 IDT 2014 | Mon Jun 02 08:00:00 IDT 2014
218 | 844 - D/T Tunnel from CH137+860 to Southern contract limit and C&C section within Hoi Ting Road Shaft (11kV Power) | Mon Sep 29 08:00:00 IDT 2014 | Mon Sep 29 08:00:00 IDT 2014
219 | 844 - U/T Tunnel from the Northern contract limit to CH137+860 (11kV Power) | Mon Sep 29 08:00:00 IDT 2014 | Mon Sep 29 08:00:00 IDT 2014
220 | 844 - U/T Tunnel from CH137+860 to the Southern contract limit and C&C section within Hoi Ting Road Shaft (11kV Power) | Mon Apr 27 08:00:00 IDT 2015 | Mon Apr 27 08:00:00 IDT 2015
221 | 844 - Nam Cheong Ventilation Building (VB7) - Power Supply Electrical Rooms (11kV Power) | Mon Sep 08 08:00:00 IDT 2014 | Mon Sep 08 08:00:00 IDT 2014
222 | 846 - Trackside Auxililaries | Mon Feb 24 08:00:00 IST 2014 | Mon Apr 27 08:00:00 IDT 2015
223 | 846 - D/T Tunnel from the Northern contract limit to CH137+860 (Trackside Aux.) | Mon Jun 02 08:00:00 IDT 2014 | Mon Jun 02 08:00:00 IDT 2014
224 | 846 - D/T Tunnel from CH137+860 to Southern contract limit and C&C section within Hoi Ting Road Shaft (Trackside Aux.) | Mon Sep 29 08:00:00 IDT 2014 | Mon Sep 29 08:00:00 IDT 2014
225 | 846 - U/T Tunnel from the Northern contract limit to CH137+860 (Trackside Aux.) | Mon Sep 29 08:00:00 IDT 2014 | Mon Sep 29 08:00:00 IDT 2014
226 | 846 - U/T Tunnel from CH137+860 to the Southern contract limit and C&C section within Hoi Ting Road Shaft | Mon Apr 27 08:00:00 IDT 2015 | Mon Apr 27 08:00:00 IDT 2015
227 | 846 - Nam Cheong Ventilation Building (VB7) Trackside LV Switch Room | Mon Feb 24 08:00:00 IST 2014 | Mon Feb 24 08:00:00 IST 2014
228 | 847 - Lifts | Mon Jul 14 08:00:00 IDT 2014 | Mon Jul 14 08:00:00 IDT 2014
229 | 847 - Nam Cheong Ventilation Building (VB7) - Lift Shaft adn Lift Machine Room | Mon Jul 14 08:00:00 IDT 2014 | Mon Jul 14 08:00:00 IDT 2014
230 | 849 - Radio Communications System | Mon Feb 24 08:00:00 IST 2014 | Mon Apr 27 08:00:00 IDT 2015
231 | 849 - Nam Cheong Ventilation Building (VB7) - TER and CTER (Radio Communications) | Mon Feb 24 08:00:00 IST 2014 | Mon Feb 24 08:00:00 IST 2014
232 | 849 - U/T Tunnel from the Northern contract limit to CH137+860 (Radio Communications) | Mon Sep 29 08:00:00 IDT 2014 | Mon Sep 29 08:00:00 IDT 2014
233 | 849 - U/T Tunnel from CH137+860 to the Southern contract limit and C&C section within Hoi Ting Road Shaft | Mon Apr 27 08:00:00 IDT 2015 | Mon Apr 27 08:00:00 IDT 2015
234 | 849 - Nam Cheong Ventilation Building (VB7) - SER (Radio Communications) | Mon Apr 21 08:00:00 IDT 2014 | Mon Apr 21 08:00:00 IDT 2014
235 | 849 - Nam Cheong Ventilation Building (VB7) - Corridors and Roof (Radio Communications) | Mon Jul 14 08:00:00 IDT 2014 | Mon Jul 14 08:00:00 IDT 2014
236 | 849 - D/T Tunnel from the Northern contract limit to CH137+860 (Radio Communications) | Mon Jun 02 08:00:00 IDT 2014 | Mon Jun 02 08:00:00 IDT 2014
237 | 849 - D/T Tunnel from CH137+860 to the Southern contract limit and C&C section within Hoi Ting Road Shaft | Mon Sep 29 08:00:00 IDT 2014 | Mon Sep 29 08:00:00 IDT 2014
238 | 850 - Passenger Mobile Communication System | Mon Feb 24 08:00:00 IST 2014 | Mon Apr 27 08:00:00 IDT 2015
239 | 850 - Nam Cheong Ventilation Building (VB7) - TER and CTER (Passenger Mobile Communication) | Mon Feb 24 08:00:00 IST 2014 | Mon Feb 24 08:00:00 IST 2014
240 | 850 - D/T Tunnel from the Northern contract limit to CH137+860 (Passenger Mobile Communication) | Mon Jun 02 08:00:00 IDT 2014 | Mon Jun 02 08:00:00 IDT 2014
241 | 850 - U/T Tunnel from the Northern contract limit to CH137+860 (Passenger Mobile Communication) | Mon Sep 29 08:00:00 IDT 2014 | Mon Sep 29 08:00:00 IDT 2014
242 | 850 - U/T Tunnel from CH137+860 to the Southern contract limit and C&C section within Hoi Ting Road Shaft | Mon Apr 27 08:00:00 IDT 2015 | Mon Apr 27 08:00:00 IDT 2015
243 | 850 - D/T Tunnel from CH137+860 to the Southern contract limit and C&C section within Hoi Ting Road Shaft | Mon Sep 29 08:00:00 IDT 2014 | Mon Sep 29 08:00:00 IDT 2014
244 | 851 - Fixed Communication System | Mon Feb 24 08:00:00 IST 2014 | Mon Apr 27 08:00:00 IDT 2015
245 | 851- Nam Cheong Ventilation Building (VB7) - TER and CTER (Fixed Communication) | Mon Feb 24 08:00:00 IST 2014 | Mon Feb 24 08:00:00 IST 2014
246 | 851 - D/T Tunnel from the Northern contract limit to CH137+860 (Fixed Communication) | Mon Jun 02 08:00:00 IDT 2014 | Mon Jun 02 08:00:00 IDT 2014
247 | 851 - U/T Tunnel from the Northern contract limit to CH137+860 (Fixed Communication) | Mon Sep 29 08:00:00 IDT 2014 | Mon Sep 29 08:00:00 IDT 2014
248 | 851 - U/T Tunnel from CH137+860 to the Southern contract limit and C&C section within Hoi Ting Road Shaft | Mon Apr 27 08:00:00 IDT 2015 | Mon Apr 27 08:00:00 IDT 2015
249 | 851 - D/T Tunnel from CH137+860 to Southern contract limit and C&C section within Hoi Ting Road Shaft | Mon Sep 29 08:00:00 IDT 2014 | Mon Sep 29 08:00:00 IDT 2014
250 | 853 - Main Control System | Mon Feb 24 08:00:00 IST 2014 | Mon Feb 24 08:00:00 IST 2014
251 | 853- Nam Cheong Ventilation Building (VB7) - TER and CTER (Main Control) | Mon Feb 24 08:00:00 IST 2014 | Mon Feb 24 08:00:00 IST 2014
252 | 854 - Security Access Management System (SAMS) | Mon Aug 18 08:00:00 IDT 2014 | Mon Aug 18 08:00:00 IDT 2014
253 | 854 - The doors with SAMS | Mon Aug 18 08:00:00 IDT 2014 | Mon Aug 18 08:00:00 IDT 2014
254 | 855 - Building Services for Tunnel Ventilation Buildings & Emergency Rescue Station | Mon Dec 23 08:00:00 IST 2013 | Mon May 12 08:00:00 IDT 2014
255 | 855-All rooms and common areas - corridors, lobbies etc within VB7 Excl. the parts of the VB7 under Ref. 4C(i) & 4C(ii) | Mon May 12 08:00:00 IDT 2014 | Mon May 12 08:00:00 IDT 2014
256 | 855 - VB7 - All rooms and common areas at track level and above track level(Excl. staircases, Lift shaft & CLP risers) | Mon Mar 03 08:00:00 IST 2014 | Mon Mar 03 08:00:00 IST 2014
257 | 855 - VB7 - All rooms and common areas at Level L1, UL2, L1 and UL1 (Excl. staircases, Lift shaft & CLP risers) | Mon Dec 23 08:00:00 IST 2013 | Mon Dec 23 08:00:00 IST 2013
258 | System Assurance Schedule | Mon Jul 05 17:00:00 IDT 2010 | Sat Jan 08 08:00:00 IST 2011
259 | System Assurance Schedule | Mon Jul 05 17:00:00 IDT 2010 | Sat Jan 08 08:00:00 IST 2011
260 | General | Mon Jul 05 17:00:00 IDT 2010 | Sat Jan 08 08:00:00 IST 2011
261 | System Assurance Plan | Sat Jan 08 08:00:00 IST 2011 | Sat Jan 08 08:00:00 IST 2011
262 | HAZOP Workshop | Mon Jul 05 17:00:00 IDT 2010 | Mon Jul 05 17:00:00 IDT 2010
263 | PHA Activity | Mon Jul 05 17:00:00 IDT 2010 | Mon Jul 05 17:00:00 IDT 2010
264 | Establish Hazard Log | Mon Jul 05 17:00:00 IDT 2010 | Mon Jul 05 17:00:00 IDT 2010
265 | System Hazard Analysis | Sat Jan 08 08:00:00 IST 2011 | Sat Jan 08 08:00:00 IST 2011
266 | Interface Hazard Analysis | Mon Nov 29 17:00:00 IST 2010 | Mon Nov 29 17:00:00 IST 2010
267 | Operating & Support Hazard Analysis | Mon Nov 29 17:00:00 IST 2010 | Mon Nov 29 17:00:00 IST 2010
268 | Hazard Analysis Report | Mon Nov 29 17:00:00 IST 2010 | Mon Nov 29 17:00:00 IST 2010
269 | Determination Safety Assessment | Sat Jan 08 08:00:00 IST 2011 | Sat Jan 08 08:00:00 IST 2011
270 | Cost Centre A - Preliminaries | Tue May 25 17:00:00 IDT 2010 | Fri Jun 26 17:00:00 IDT 2015
271 | IPS Milestones | Sat Jan 08 08:00:00 IST 2011 | Fri Jun 26 17:00:00 IDT 2015
272 | General | Sat Jan 08 08:00:00 IST 2011 | Fri Jun 26 17:00:00 IDT 2015
273 | Approval of Contractor's Submissions | Sat Jan 08 08:00:00 IST 2011 | Sat Jan 08 08:00:00 IST 2011
274 | Submit Contamination Assessment Report & RAP | Wed Apr 13 17:00:00 IDT 2011 | Wed Apr 13 17:00:00 IDT 2011
275 | Complete Engineer's Office+Satisfy Implem. Plans | Sun Apr 17 17:00:00 IDT 2011 | Sun Apr 17 17:00:00 IDT 2011
276 | Implem. Specified Plan&Programming Management System | Tue May 31 08:00:00 IDT 2011 | Tue May 31 08:00:00 IDT 2011
277 | Approval of Interface Specification&Specify Plan | Sun Jan 15 08:00:00 IST 2012 | Sun Jan 15 08:00:00 IST 2012
278 | 1st TBM - Complete Assembly, T&C & Start D/T Drive | Fri Jan 20 17:00:00 IST 2012 | Fri Jan 20 17:00:00 IST 2012
279 | Implem. Specified Plan&Programming Managem't System | Sun May 27 17:00:00 IDT 2012 | Sun May 27 17:00:00 IDT 2012
280 | Confirmation of Satisfactory Implementation of Specified Plan | Fri Nov 30 08:00:00 IST 2012 | Fri Nov 30 08:00:00 IST 2012
281 | TBM - Complete Assembly, T&C & Start U/T Drive | Fri Mar 29 17:00:00 IDT 2013 | Fri Mar 29 17:00:00 IDT 2013
282 | Confirmation of Satisfy Implement Specified Plan & Programming Mgmt. System | Sun May 26 17:00:00 IDT 2013 | Sun May 26 17:00:00 IDT 2013
283 | Confirmation of Satisfy Implement Specified Plan | Sun Nov 24 17:00:00 IST 2013 | Sun Nov 24 17:00:00 IST 2013
284 | Deg.1 Complete Entire Length Tunnel - Both Tracks | Tue Mar 31 17:00:00 IDT 2015 | Tue Mar 31 17:00:00 IDT 2015
285 | Approval of Draft O&M Manuals & As-built Drawing | Wed Mar 25 17:00:00 IST 2015 | Wed Mar 25 17:00:00 IST 2015
286 | Approval of O&M Manuals & As-built Drawings | Fri Jun 26 17:00:00 IDT 2015 | Fri Jun 26 17:00:00 IDT 2015
287 | Submission | Tue May 25 17:00:00 IDT 2010 | Sun Jan 15 08:00:00 IST 2012
288 | General | Tue May 25 17:00:00 IDT 2010 | Sun Jan 15 08:00:00 IST 2012
289 | Submission of Three Month Rolling Programme | Sat Jan 08 08:00:00 IST 2011 | Sat Jan 08 08:00:00 IST 2011
290 | Submission of Preliminary Design Programme | Sat Jan 08 08:00:00 IST 2011 | Sat Jan 08 08:00:00 IST 2011
291 | Submission of Contractor Submission Schedule | Sat Jan 08 08:00:00 IST 2011 | Sat Jan 08 08:00:00 IST 2011
292 | Submission of Schedule of Design | Sat Jan 08 08:00:00 IST 2011 | Sat Jan 08 08:00:00 IST 2011
293 | Submission Environment Management Plan | Sat Jan 08 08:00:00 IST 2011 | Sat Jan 08 08:00:00 IST 2011
294 | Submission of Quality Plan | Sat Jan 08 08:00:00 IST 2011 | Sat Jan 08 08:00:00 IST 2011
295 | Submission of Sub-contract Management Plan | Sat Jan 08 08:00:00 IST 2011 | Sat Jan 08 08:00:00 IST 2011
296 | Submission of Supply Survey Equipment Listed in App. A1 | Sat Jan 08 08:00:00 IST 2011 | Sat Jan 08 08:00:00 IST 2011
297 | Apply a Billing Account in EPD for Disposal of Construction Waste | Sat Jan 08 08:00:00 IST 2011 | Sat Jan 08 08:00:00 IST 2011
298 | Submission of Monitoring Emergency Response Plan(impact on Ecological & Fishers Resources) | Sat Jan 08 08:00:00 IST 2011 | Sat Jan 08 08:00:00 IST 2011
299 | Submission of Bond in form of App.B | Sat Jan 08 08:00:00 IST 2011 | Sat Jan 08 08:00:00 IST 2011
300 | Submission of Guarantee in Form of App.C | Sat Jan 08 08:00:00 IST 2011 | Sat Jan 08 08:00:00 IST 2011
301 | Submission of Guarantee in Form of App.D | Sat Jan 08 08:00:00 IST 2011 | Sat Jan 08 08:00:00 IST 2011
302 | Submission of Preliminary Master Programme | Wed Jun 02 17:00:00 IDT 2010 | Wed Jun 02 17:00:00 IDT 2010
303 | Submission of Time Chainage Programme | Wed Jun 02 17:00:00 IDT 2010 | Wed Jun 02 17:00:00 IDT 2010
304 | Confirmation for Conveyor System from Nam CheongShaft to Nam Cheong Barging Pt. | Wed Jun 02 17:00:00 IDT 2010 | Wed Jun 02 17:00:00 IDT 2010
305 | Submission of Survey Control Network | Wed Jun 02 17:00:00 IDT 2010 | Wed Jun 02 17:00:00 IDT 2010
306 | Submission for Approval Survey Control | Sun Jul 11 17:00:00 IDT 2010 | Sun Jul 11 17:00:00 IDT 2010
307 | Submission of Proposal for Repositioning of Traffic Signals & Control | Wed Jul 07 17:00:00 IDT 2010 | Wed Jul 07 17:00:00 IDT 2010
308 | Submission of Schedule of Utility Services Arrangement | Wed Jun 02 17:00:00 IDT 2010 | Wed Jun 02 17:00:00 IDT 2010
309 | Submission DIA to DSD for Approval | Wed Jun 02 17:00:00 IDT 2010 | Wed Jun 02 17:00:00 IDT 2010
310 | Submission of Health & Safety Plan | Wed Jun 02 17:00:00 IDT 2010 | Wed Jun 02 17:00:00 IDT 2010
311 | Completion of Initial Site Survey Submission | Wed Jun 02 17:00:00 IDT 2010 | Wed Jun 02 17:00:00 IDT 2010
312 | Submit Initial Site Survey Report to Engineer | Wed Jun 02 17:00:00 IDT 2010 | Wed Jun 02 17:00:00 IDT 2010
313 | Review Tree Removal Application & Confirmation to Engineer | Tue May 25 17:00:00 IDT 2010 | Tue May 25 17:00:00 IDT 2010
314 | Submit Full Details of TBMs to Engineer | Sun Jan 15 08:00:00 IST 2012 | Sun Jan 15 08:00:00 IST 2012
315 | MS/TTm proposal & Risk Register for Conveyor System at Barging Point | Sat Jan 08 08:00:00 IST 2011 | Sat Jan 08 08:00:00 IST 2011
316 | Submit Survey Method Statement for Tunnelling Works | Sat Jan 08 08:00:00 IST 2011 | Sat Jan 08 08:00:00 IST 2011
317 | Submit Managem't & Operat'n Plan of Barging Facility | Sat Jan 08 08:00:00 IST 2011 | Sat Jan 08 08:00:00 IST 2011
318 | TTM Schemes Submission for Engineer Review & SLG Approval | Sat Jan 08 08:00:00 IST 2011 | Sat Jan 08 08:00:00 IST 2011
319 | RemediationActionPlan forAreas11.29A to11.29-EPD | Sat Jan 08 08:00:00 IST 2011 | Sat Jan 08 08:00:00 IST 2011
320 | Condition Survey Submission for EBS | Mon Feb 28 08:00:00 IST 2011 | Mon Feb 28 08:00:00 IST 2011
321 | All Instrumentation Installation | Mon Feb 28 08:00:00 IST 2011 | Mon Feb 28 08:00:00 IST 2011
322 | Tree Protection Plan | Mon Feb 28 08:00:00 IST 2011 | Mon Feb 28 08:00:00 IST 2011
323 | Site Supervision Plan | Mon Feb 28 08:00:00 IST 2011 | Mon Feb 28 08:00:00 IST 2011
324 | Emergency Action Plan/Crisis Management Plan | Mon Feb 28 08:00:00 IST 2011 | Mon Feb 28 08:00:00 IST 2011
325 | Soil Disposal Management Plan | Mon Feb 28 08:00:00 IST 2011 | Mon Feb 28 08:00:00 IST 2011
326 | Segmental Lining Design Submission | Mon Feb 28 08:00:00 IST 2011 | Mon Feb 28 08:00:00 IST 2011
327 | Method Statement for Geotechnical Instrumentation Installation | Mon Feb 28 08:00:00 IST 2011 | Mon Feb 28 08:00:00 IST 2011
328 | Method Statement for Hoarding Erection | Mon Feb 28 08:00:00 IST 2011 | Mon Feb 28 08:00:00 IST 2011
329 | Emergency Response Plan to Groundwater Drawdown & Noise/Vibration | Mon Feb 28 08:00:00 IST 2011 | Mon Feb 28 08:00:00 IST 2011
330 | Site Office | Sat Jan 08 08:00:00 IST 2011 | Mon Mar 14 17:00:00 IST 2011
331 | Construction | Sat Jan 08 08:00:00 IST 2011 | Mon Mar 14 17:00:00 IST 2011
332 | Site Office Establish at Works Area 11.22 | Sat Jan 08 08:00:00 IST 2011 | Mon Mar 14 17:00:00 IST 2011
333 | Training Centre | Tue Jun 21 08:00:00 IDT 2011 | Wed Jul 13 17:00:00 IDT 2011
334 | Construction | Tue Jun 21 08:00:00 IDT 2011 | Wed Jul 13 17:00:00 IDT 2011
335 | Base Slab Construction | Thu Jun 23 08:00:00 IDT 2011 | Mon Jun 27 17:00:00 IDT 2011
336 | Erection of Building Structure | Tue Jun 21 08:00:00 IDT 2011 | Wed Jul 13 17:00:00 IDT 2011
337 | Internal Fitting Out | Tue Jun 21 08:00:00 IDT 2011 | Wed Jul 13 17:00:00 IDT 2011
338 | External Works | Tue Jun 21 08:00:00 IDT 2011 | Tue Jul 05 17:00:00 IDT 2011
339 | External Slab Construction | Tue Jun 21 08:00:00 IDT 2011 | Tue Jul 05 17:00:00 IDT 2011
340 | External U-channel | Tue Jun 21 08:00:00 IDT 2011 | Thu Jun 30 17:00:00 IDT 2011
341 | Sewer and Manholes | Tue Jun 21 08:00:00 IDT 2011 | Mon Jun 27 17:00:00 IDT 2011
342 | Hoarding Erection | Tue Jun 21 08:00:00 IDT 2011 | Sat Jul 02 17:00:00 IDT 2011
343 | Main Gate Installation | Tue Jun 21 08:00:00 IDT 2011 | Mon Jun 27 17:00:00 IDT 2011
344 | Sign Board Installation | Tue Jun 21 08:00:00 IDT 2011 | Mon Jun 27 17:00:00 IDT 2011
345 | Barging Point | Sat Jan 08 08:00:00 IST 2011 | Mon Mar 02 17:00:00 IST 2015
346 | General | Sat Jan 08 08:00:00 IST 2011 | Sat Jul 23 17:00:00 IDT 2011
347 | Barging Point Design Preparation | Sat Jan 08 08:00:00 IST 2011 | Sat Jul 23 17:00:00 IDT 2011
348 | Barging Point Design Comment and Approval by MTR | Sat Mar 05 08:00:00 IST 2011 | Sat Apr 02 17:00:00 IDT 2011
349 | Contamination | Sat Jan 08 08:00:00 IST 2011 | Sat May 21 17:00:00 IDT 2011
350 | Submission of Revised CAP (by MTR) | Sat Jan 08 08:00:00 IST 2011 | Thu Jan 20 17:00:00 IST 2011
351 | Approval Time of CAP from EPD | Tue Jan 18 08:00:00 IST 2011 | Sat Feb 19 17:00:00 IST 2011
352 | Preparation & Submission of M.S for Drilling | Mon Feb 21 08:00:00 IST 2011 | Tue Mar 01 17:00:00 IST 2011
353 | Site Investigation & Sample Locations Survey | Mon Feb 28 08:00:00 IST 2011 | Mon Mar 07 17:00:00 IST 2011
354 | Drilling & Sampling | Mon Mar 07 08:00:00 IST 2011 | Fri Mar 25 17:00:00 IST 2011
355 | Sampling Analysis | Fri Mar 18 08:00:00 IST 2011 | Wed Apr 13 17:00:00 IDT 2011
356 | Submission of CAR | Fri Apr 01 08:00:00 IDT 2011 | Wed May 04 17:00:00 IDT 2011
357 | Submission of RAP | Fri Apr 01 08:00:00 IDT 2011 | Wed May 04 17:00:00 IDT 2011
358 | Comments from EPD | Tue Apr 19 08:00:00 IDT 2011 | Sat May 21 17:00:00 IDT 2011
359 | Approved CAR & RAP Report Handover to 811B & 821 | Wed May 11 17:00:00 IDT 2011 | Wed May 11 17:00:00 IDT 2011
360 | Construction | Sat Jan 08 08:00:00 IST 2011 | Fri Jul 29 17:00:00 IDT 2011
361 | Works Area 11.29A | Sat Jan 08 08:00:00 IST 2011 | Sat Jan 08 08:00:00 IST 2011
362 | Works Area 11.29D | Sat Jan 08 08:00:00 IST 2011 | Sat Jan 08 08:00:00 IST 2011
363 | Works Area 11.29E | Sat Jan 08 08:00:00 IST 2011 | Sat Jan 08 08:00:00 IST 2011
364 | Works Area 11.29F | Sat Jan 08 08:00:00 IST 2011 | Sat Jan 08 08:00:00 IST 2011
365 | Site Mobilization | Sat Jan 08 08:00:00 IST 2011 | Fri Jan 28 17:00:00 IST 2011
366 | Hydographic/Condition Survey | Sat Jan 29 08:00:00 IST 2011 | Sat Mar 26 17:00:00 IST 2011
367 | Site Clearance | Sat Jun 11 08:00:00 IDT 2011 | Mon Jul 11 17:00:00 IDT 2011
368 | Site Formation fro Barging Point | Wed Jun 22 08:00:00 IDT 2011 | Mon Jul 11 17:00:00 IDT 2011
369 | Construction of Loading Ramps and Associated Facilities | Mon Feb 28 08:00:00 IST 2011 | Fri Jul 29 17:00:00 IDT 2011
370 | Storage Treatment Plant | Mon May 21 08:00:00 IDT 2012 | Sat Sep 01 17:00:00 IDT 2012
371 | Storage Treatment Plant Setup | Mon May 21 08:00:00 IDT 2012 | Sat Sep 01 17:00:00 IDT 2012
372 | Slurry Treatment Plant | Thu Jun 30 08:00:00 IDT 2011 | Mon Mar 02 17:00:00 IST 2015
373 | Begininning of Material Delivery for Slurry Treatment Plants | Thu Jun 30 08:00:00 IDT 2011 | Thu Jun 30 08:00:00 IDT 2011
374 | Treatment Tanks Erection | Thu Jun 30 08:00:00 IDT 2011 | Sat Sep 10 17:00:00 IDT 2011
375 | Silos Erection | Mon Jan 16 08:00:00 IST 2012 | Fri Jan 27 17:00:00 IST 2012
376 | Filter Press | Mon Jan 16 08:00:00 IST 2012 | Wed Feb 29 17:00:00 IST 2012
377 | Slurry Treatment Plant (STP1) Construction | Wed Aug 31 08:00:00 IDT 2011 | Thu Oct 13 17:00:00 IST 2011
378 | STP2 Construciton | Mon Jan 16 08:00:00 IST 2012 | Thu Feb 09 17:00:00 IST 2012
379 | Water Commissioning of STP1 | Mon Jan 16 08:00:00 IST 2012 | Fri Jan 20 17:00:00 IST 2012
380 | Water Commissioning of STP2 | Mon Jan 16 08:00:00 IST 2012 | Fri Jan 20 17:00:00 IST 2012
381 | Dismantle Slurry Treatment Plant and Equipments (after South U/T TBM (S630-1) Backup removal) | Wed Oct 15 08:00:00 IDT 2014 | Mon Jan 19 17:00:00 IST 2015
382 | Re-instatement | Fri Jan 02 08:00:00 IST 2015 | Mon Mar 02 17:00:00 IST 2015
383 | Cost Centre B - Specialised Construction Machinery & Site Assembly (TBMs) | Sat Jan 08 08:00:00 IST 2011 | Wed Nov 19 17:00:00 IST 2014
384 | IPS Milestones | Mon Jan 31 08:00:00 IST 2011 | Wed Nov 19 17:00:00 IST 2014
385 | General | Mon Jan 31 08:00:00 IST 2011 | Wed Nov 19 17:00:00 IST 2014
386 | Confirmation of Order of TBM | Mon Jan 31 08:00:00 IST 2011 | Mon Jan 31 08:00:00 IST 2011
387 | TBM - Commencement of the 1st TBM Final Assembly at Factory | Tue Aug 30 08:00:00 IDT 2011 | Tue Aug 30 08:00:00 IDT 2011
388 | TBM - Complete Fabrication & Ready Ship to HK | Sun Jan 15 08:00:00 IST 2012 | Sun Jan 15 08:00:00 IST 2012
389 | TBM - Complete Assembly,T&C+Start D/T Drive | Sun Feb 05 17:00:00 IST 2012 | Sun Feb 05 17:00:00 IST 2012
390 | TBM - Complete Assembly,T&C+Start U/T Drive (North) | Fri Mar 29 17:00:00 IDT 2013 | Fri Mar 29 17:00:00 IDT 2013
391 | TBM - Complete Assembly,T&C+Start Remain U/T Drive (South) | Thu Dec 12 08:00:00 IST 2013 | Thu Dec 12 08:00:00 IST 2013
392 | TBM - Complete Dismantle of TBM | Wed Nov 19 17:00:00 IST 2014 | Wed Nov 19 17:00:00 IST 2014
393 | Procurement | Sat Jan 08 08:00:00 IST 2011 | Mon Jan 07 17:00:00 IST 2013
394 | TBM (S630-1) Procurement & Delivery | Mon Feb 28 08:00:00 IST 2011 | Wed Nov 07 17:00:00 IST 2012
395 | TBM (S631-1) Procurement & Delivery | Mon Feb 28 08:00:00 IST 2011 | Mon Jan 07 17:00:00 IST 2013
396 | TBM (S630-1) Procurement | Sat Jan 08 08:00:00 IST 2011 | Wed Mar 21 17:00:00 IST 2012
397 | TBM(S630-1) - Procurement | Sat Jan 08 08:00:00 IST 2011 | Sat Feb 26 17:00:00 IST 2011
398 | TBM(S630-1) - Ordering | Sat Feb 26 17:00:00 IST 2011 | Sat Feb 26 17:00:00 IST 2011
399 | TBM(S630-1) - Detailed Design | Mon Jan 31 08:00:00 IST 2011 | Sun Apr 17 17:00:00 IDT 2011
400 | Ergonomy Study | Thu Feb 10 08:00:00 IST 2011 | Fri Apr 15 17:00:00 IDT 2011
401 | Purchase Parts | Mon Jan 31 08:00:00 IST 2011 | Thu Aug 18 17:00:00 IDT 2011
402 | Manufacturing of Drive Unit (in Europe) | Sun Mar 20 08:00:00 IST 2011 | Mon Sep 12 17:00:00 IDT 2011
403 | Commencement of TBM1 Final Assembly at Factory | Wed Aug 03 08:00:00 IDT 2011 | Wed Aug 03 08:00:00 IDT 2011
404 | Pre-assembly Drive Unit, Erector, Hydraulics, Slurry Pumps in Schwanau | Wed Aug 03 08:00:00 IDT 2011 | Sun Oct 23 17:00:00 IST 2011
405 | Transport (Europe to China) | Mon Mar 28 08:00:00 IST 2011 | Tue May 03 17:00:00 IDT 2011
406 | Manufacturing of Shield, Cutterhead, Back-up (in China) | Mon Feb 28 08:00:00 IST 2011 | Tue Sep 06 17:00:00 IDT 2011
407 | Design Review for TBM (S631-1) Modification | Sun Jun 19 08:00:00 IDT 2011 | Wed Jul 13 17:00:00 IDT 2011
408 | EI issue for TBM (S630-1) Modification | Thu Jun 30 08:00:00 IDT 2011 | Thu Jun 30 08:00:00 IDT 2011
409 | TBM (S630-1) Modification | Thu Jun 30 08:00:00 IDT 2011 | Thu Sep 08 17:00:00 IDT 2011
410 | Final Assembly in Workshop | Sun Jun 19 08:00:00 IDT 2011 | Sat Nov 19 17:00:00 IST 2011
411 | Factory Acceptance Tests | Sun Jan 15 08:00:00 IST 2012 | Tue Feb 07 17:00:00 IST 2012
412 | Disassembly & Ready Ship to HK | Sun Jan 15 08:00:00 IST 2012 | Sat Feb 11 17:00:00 IST 2012
413 | TBM (S630-1) Available for delivery to HK | Sun Jan 15 08:00:00 IST 2012 | Sun Jan 15 08:00:00 IST 2012
414 | TBM(S630-1) - TBM Storage | Sun Jan 15 08:00:00 IST 2012 | Wed Feb 29 17:00:00 IST 2012
415 | TBM(S630-1) - Transport & Delivery to HK | Thu Mar 01 08:00:00 IST 2012 | Wed Mar 21 17:00:00 IST 2012
416 | TBM (S631-1) Procurement | Sat Jan 08 08:00:00 IST 2011 | Sat Feb 11 17:00:00 IST 2012
417 | TBM(S631-1) - Procurement | Mon Jan 31 08:00:00 IST 2011 | Sun Mar 20 17:00:00 IST 2011
418 | TBM(S631-1) - Ordering | Sat Feb 26 17:00:00 IST 2011 | Sat Feb 26 17:00:00 IST 2011
419 | TBM(S631-1) - Detailed Design | Sun Feb 27 08:00:00 IST 2011 | Wed May 25 17:00:00 IDT 2011
420 | Ergonomy Study | Thu Jan 20 08:00:00 IST 2011 | Sat Mar 26 17:00:00 IST 2011
421 | Purchase Parts | Sat Jan 08 08:00:00 IST 2011 | Thu Sep 15 17:00:00 IDT 2011
422 | Manufacturing of Drive Unit (in Europe) | Sun Mar 27 08:00:00 IST 2011 | Wed Sep 28 17:00:00 IDT 2011
423 | Pre-assembly Drive Unit,erector,Hydraulics, Slurry Pumps in Schwanau | Sun Jun 19 08:00:00 IDT 2011 | Sat Jul 16 17:00:00 IDT 2011
424 | Transport (Europe to China) | Tue Apr 19 08:00:00 IDT 2011 | Mon Jun 27 17:00:00 IDT 2011
425 | Manufacturing on Shield, Cutterhead,Back-up (in China) | Fri Mar 11 08:00:00 IST 2011 | Thu Oct 06 17:00:00 IST 2011
426 | Design Review for TBM (S631-1) Modification | Sun Jun 19 08:00:00 IDT 2011 | Wed Jul 13 17:00:00 IDT 2011
427 | EI issue for TBM631.1 Modification | Thu Jun 30 08:00:00 IDT 2011 | Thu Jun 30 08:00:00 IDT 2011
428 | TBM (S631-1) Modification | Sun Jun 19 08:00:00 IDT 2011 | Sun Aug 28 17:00:00 IDT 2011
429 | Final Assembly in Workshop | Sun Jun 19 08:00:00 IDT 2011 | Fri Oct 21 17:00:00 IST 2011
430 | Factory Acceptance Tests | Wed Aug 31 08:00:00 IDT 2011 | Fri Sep 23 17:00:00 IDT 2011
431 | Disassembly | Sun Jan 15 08:00:00 IST 2012 | Sat Feb 11 17:00:00 IST 2012
432 | TBM (S631-1) Available for delivery to HK | Sun Jan 15 08:00:00 IST 2012 | Sun Jan 15 08:00:00 IST 2012
433 | TBM(S631-1) - Transport & Delivery to HK | Sun Jan 15 08:00:00 IST 2012 | Fri Feb 03 17:00:00 IST 2012
434 | Cost Centre C - Mei Lai Road - Hoi Ting Road Tunnel | Thu Oct 21 08:00:00 IST 2010 | Tue Sep 29 17:00:00 IDT 2015
435 | IPS Milestones | Mon Feb 28 08:00:00 IST 2011 | Sun May 10 17:00:00 IDT 2015
436 | General | Mon Feb 28 08:00:00 IST 2011 | Sun May 10 17:00:00 IDT 2015
437 | Approval of Tunnel Lining Design | Mon Jul 18 17:00:00 IDT 2011 | Mon Jul 18 17:00:00 IDT 2011
438 | Approval of Tunnel Segment Mould Design | Mon Feb 28 08:00:00 IST 2011 | Mon Feb 28 08:00:00 IST 2011
439 | Confirmation of the Order of Segment Mould | Thu Jun 30 08:00:00 IDT 2011 | Thu Jun 30 08:00:00 IDT 2011
440 | Complete Ground Improvement Wk Outside Hoi Ting Shaft | Sun Jun 19 17:00:00 IDT 2011 | Sun Jun 19 17:00:00 IDT 2011
441 | Complete 30% of Pre-cast Segment Manufacturing | Thu Dec 20 17:00:00 IST 2012 | Thu Dec 20 17:00:00 IST 2012
442 | Complete 45% of Pre-cast Segment Manufacturing | Fri Apr 19 17:00:00 IDT 2013 | Fri Apr 19 17:00:00 IDT 2013
443 | Complete 30% of Tunnel Drive | Fri Aug 31 08:00:00 IDT 2012 | Fri Aug 31 08:00:00 IDT 2012
444 | Complete 50% of Tunnel Drive | Thu Jan 31 17:00:00 IST 2013 | Thu Jan 31 17:00:00 IST 2013
445 | Complete 60% of Tunnel Drive | Wed Jul 31 17:00:00 IDT 2013 | Wed Jul 31 17:00:00 IDT 2013
446 | Deg. 1 Completion for D/T Tunnel | Sun May 18 17:00:00 IDT 2014 | Sun May 18 17:00:00 IDT 2014
447 | Complete 100% of Tunnel Drive | Sun Sep 28 17:00:00 IDT 2014 | Sun Sep 28 17:00:00 IDT 2014
448 | Deg. 1 Completion for U/T Tunnel | Sat Feb 28 17:00:00 IST 2015 | Sat Feb 28 17:00:00 IST 2015
449 | Complete All Works | Sun May 10 17:00:00 IDT 2015 | Sun May 10 17:00:00 IDT 2015
450 | Critical Dates | Mon Feb 28 08:00:00 IST 2011 | Mon Sep 30 08:00:00 IDT 2013
451 | Critical Dates | Mon Feb 28 08:00:00 IST 2011 | Mon Sep 30 08:00:00 IDT 2013
452 | Earliest Access Date- Works Area 12.2 | Mon Feb 28 08:00:00 IST 2011 | Mon Feb 28 08:00:00 IST 2011
453 | Ground Treatment Completion at Works Area 12.2 | Sun Jun 19 17:00:00 IDT 2011 | Sun Jun 19 17:00:00 IDT 2011
454 | Hoi Ting Road - TBM Retrieval Shaft Ready | Mon Sep 30 08:00:00 IDT 2013 | Mon Sep 30 08:00:00 IDT 2013
455 | Method Statement Submission and Approval | Mon Feb 28 08:00:00 IST 2011 | Thu Jan 19 17:00:00 IST 2012
456 | Method Stattement Submission and Approval | Mon Feb 28 08:00:00 IST 2011 | Thu Jan 19 17:00:00 IST 2012
457 | MS Submission Preparation for CLP/IVESchool Grouting | Thu Jun 30 08:00:00 IDT 2011 | Thu Jan 19 17:00:00 IST 2012
458 | MS Submission to MTR | Thu Jun 30 08:00:00 IDT 2011 | Thu Jun 30 08:00:00 IDT 2011
459 | MS Comment by MTR | Thu Jun 30 08:00:00 IDT 2011 | Thu Aug 04 17:00:00 IDT 2011
460 | MS Re-submission Preparation | Thu Jun 30 08:00:00 IDT 2011 | Sat Jul 09 17:00:00 IDT 2011
461 | MS Comment & Approval by MTR | Thu Jun 30 08:00:00 IDT 2011 | Tue Aug 16 17:00:00 IDT 2011
462 | Issue for Construction (CLP/IVE) | Wed Jul 27 17:00:00 IDT 2011 | Wed Jul 27 17:00:00 IDT 2011
463 | MS Submission Preparation for Cross Passage | Mon Feb 28 08:00:00 IST 2011 | Tue Jun 07 17:00:00 IDT 2011
464 | MS Submission to MTR | Thu Jun 30 08:00:00 IDT 2011 | Thu Jun 30 08:00:00 IDT 2011
465 | MS Comment by MTR | Thu Jun 30 08:00:00 IDT 2011 | Sat Jul 16 17:00:00 IDT 2011
466 | MS Re-Submission Preparation | Wed Aug 31 08:00:00 IDT 2011 | Wed Sep 21 17:00:00 IDT 2011
467 | MS Comment & Approval by MTR | Wed Aug 31 08:00:00 IDT 2011 | Sat Sep 17 17:00:00 IDT 2011
468 | Issue for Construction (Cross Passage) | Wed Aug 31 08:00:00 IDT 2011 | Wed Aug 31 08:00:00 IDT 2011
469 | MS Submission Preparation for HoiFu Estate/Charming Bldgs.& YMT School | Thu Jun 30 08:00:00 IDT 2011 | Tue Jul 26 17:00:00 IDT 2011
470 | MS Submission to MTR | Thu Jun 30 08:00:00 IDT 2011 | Thu Jun 30 08:00:00 IDT 2011
471 | MS Comment & Approoval by MTR | Thu Jun 30 08:00:00 IDT 2011 | Thu Jul 21 17:00:00 IDT 2011
472 | MS Re-submission Preparation | Thu Jun 30 08:00:00 IDT 2011 | Thu Jul 28 17:00:00 IDT 2011
473 | MS Approval by MTR | Wed Aug 31 08:00:00 IDT 2011 | Sun Sep 11 17:00:00 IDT 2011
474 | Issue for Construction (HoiFu Estate/Charming Bldgs & YMT School) | Wed Aug 31 08:00:00 IDT 2011 | Wed Aug 31 08:00:00 IDT 2011
475 | TTMS Submission and Approval | Tue Feb 01 08:00:00 IST 2011 | Sun Sep 11 17:00:00 IDT 2011
476 | TTM Scheme Submission & Approval | Tue Feb 01 08:00:00 IST 2011 | Sun Sep 11 17:00:00 IDT 2011
477 | Prepare TTM for grouting works for Existing Bldg | Tue Feb 01 08:00:00 IST 2011 | Sat Mar 05 17:00:00 IST 2011
478 | TTM reviewed by SLG | Sun Mar 06 08:00:00 IST 2011 | Thu May 05 17:00:00 IDT 2011
479 | Resubmit TTM | Mon May 23 08:00:00 IDT 2011 | Mon May 23 17:00:00 IDT 2011
480 | TTM reviewed by SLG | Sun May 29 08:00:00 IDT 2011 | Sun May 29 17:00:00 IDT 2011
481 | Notification to RMO (for Ch140 +080 & +150 & +200) | Sun Jun 19 08:00:00 IDT 2011 | Sun Jun 26 17:00:00 IDT 2011
482 | XP Application & Approval | Mon Jun 20 08:00:00 IDT 2011 | Thu Aug 18 17:00:00 IDT 2011
483 | Implement TTM (Initial Stage) | Mon Feb 28 08:00:00 IST 2011 | Mon Jul 25 17:00:00 IDT 2011
484 | Notification to RMO (for Ch140 +340) | Wed Aug 31 08:00:00 IDT 2011 | Sun Sep 11 17:00:00 IDT 2011
485 | Implement TTM | Wed Aug 31 08:00:00 IDT 2011 | Wed Aug 31 08:00:00 IDT 2011
486 | SP License Application and Approval | Sun Jan 15 08:00:00 IST 2012 | Sun Jun 17 17:00:00 IDT 2012
487 | SP License application | Sun Jan 15 08:00:00 IST 2012 | Sun Jun 17 17:00:00 IDT 2012
488 | SP License application | Sun Jan 15 17:00:00 IST 2012 | Sun Jan 15 17:00:00 IST 2012
489 | TBM (S631-1) Excavation with Deg.1 Works | Sun Jan 15 08:00:00 IST 2012 | Thu May 29 17:00:00 IDT 2014
490 | TBM (S631-1) North -UT Excavation | Fri Mar 29 08:00:00 IDT 2013 | Thu Nov 14 17:00:00 IST 2013
491 | Access Available for Works Area 11.10A &11.10B (IVE School) (DT) (Contractual Handover Date) | Wed Feb 06 08:00:00 IST 2013 | Wed Feb 06 08:00:00 IST 2013
492 | Ground Treatment for IVE School (DT) | Mon Jan 16 08:00:00 IST 2012 | Tue Jun 12 17:00:00 IDT 2012
493 | TBM (S631-1) North-DT Excavation | Fri Jan 20 08:00:00 IST 2012 | Tue Oct 30 17:00:00 IST 2012
494 | TBM (S631-1) Dismantle & Re-assembly | Mon Dec 17 08:00:00 IST 2012 | Tue Feb 26 17:00:00 IST 2013
495 | Piles Removal@CLP Equipment Bldg.& Footbridges KF-118 by 805 (NDT) | Sun Jan 15 08:00:00 IST 2012 | Sun Jan 15 08:00:00 IST 2012
496 | Access Available for Works Area 11.10A &11.10B (IVE School) (DT) (Contractual Handover Date) | Wed Feb 06 08:00:00 IST 2013 | Wed Feb 06 08:00:00 IST 2013
497 | Ground Treatment for HKIVE School (NDT) | Mon Jan 16 08:00:00 IST 2012 | Mon Mar 26 17:00:00 IST 2012
498 | Grouting Wk@N/B Ch137+570: Building Foundation (Hoi Lai Shopping Centre) (NUT) | Sat Mar 24 08:00:00 IST 2012 | Fri Aug 31 17:00:00 IDT 2012
499 | General | Sun Jan 15 08:00:00 IST 2012 | Fri Mar 30 17:00:00 IDT 2012
500 | TBM (S631-1) Delivery on Site | Sun Jan 15 08:00:00 IST 2012 | Sun Jan 15 08:00:00 IST 2012
501 | TBM (S631-1) Assembly and T&C | Sun Jan 15 08:00:00 IST 2012 | Fri Mar 30 17:00:00 IDT 2012
502 | Downtrack Construction (North) | Sun Jan 15 08:00:00 IST 2012 | Sat Aug 17 17:00:00 IDT 2013
503 | TBM Excavation (North-DT) | Sun Jan 15 08:00:00 IST 2012 | Sat Aug 17 17:00:00 IDT 2013
504 | D/T TBM (S631-1) Break-in &Excavation Ch137+783-137+730 | Fri Jan 20 08:00:00 IST 2012 | Fri Feb 10 17:00:00 IST 2012
505 | Reach Cheung Sha Wan Cargo Pier Pile Obstruction | Fri Feb 10 17:00:00 IST 2012 | Fri Feb 10 17:00:00 IST 2012
506 | D/T Excavation Ch137+730-137+640 | Sat Feb 11 08:00:00 IST 2012 | Sun Mar 18 17:00:00 IST 2012
507 | D/T Excavation Ch137+640-137+530 | Mon Mar 19 08:00:00 IST 2012 | Mon Apr 02 17:00:00 IDT 2012
508 | Reach CP88 (CH137+565) | Thu Mar 29 08:00:00 IST 2012 | Thu Mar 29 08:00:00 IST 2012
509 | D/T Excavation Ch137+530-137+420 | Tue Apr 03 08:00:00 IDT 2012 | Thu Apr 12 17:00:00 IDT 2012
510 | D/T Excavation Ch137+420-137+345 | Fri Apr 13 08:00:00 IDT 2012 | Thu Apr 19 17:00:00 IDT 2012
511 | Reach CP87 (CH137+369) | Wed Apr 18 17:00:00 IDT 2012 | Wed Apr 18 17:00:00 IDT 2012
512 | Piles Removal@CLP Equipment Bldg.& Footbridges KF-118 by 805 | Sun Jan 15 08:00:00 IST 2012 | Sun Jan 15 08:00:00 IST 2012
513 | Reach Footbridge KF118 (Pile removed by 805) | Thu Apr 19 17:00:00 IDT 2012 | Thu Apr 19 17:00:00 IDT 2012
514 | D/T Excavation Ch137+345-137+280 | Fri Apr 20 08:00:00 IDT 2012 | Wed Apr 25 17:00:00 IDT 2012
515 | D/T Excavation Ch137+280-137+265 | Thu Apr 26 08:00:00 IDT 2012 | Fri Apr 27 17:00:00 IDT 2012
516 | Reach IVE Haking Wong Waterfont Annex (advanced work:Grouting) | Fri Apr 27 17:00:00 IDT 2012 | Fri Apr 27 17:00:00 IDT 2012
517 | D/T Excavation Ch137+265-137+240 | Sat Apr 28 08:00:00 IDT 2012 | Mon Apr 30 17:00:00 IDT 2012
518 | D/T Excavation Ch137+240-137+190 | Tue May 01 08:00:00 IDT 2012 | Sat May 05 17:00:00 IDT 2012
519 | D/T Excavation Ch137+190-137+080 | Sun May 06 08:00:00 IDT 2012 | Fri May 25 17:00:00 IDT 2012
520 | Reach CP86 (CH137+119) | Sat May 19 08:00:00 IDT 2012 | Sat May 19 08:00:00 IDT 2012
521 | Reach WD1 DSD Obstruction & 1800dia.Sewer | Fri May 25 17:00:00 IDT 2012 | Fri May 25 17:00:00 IDT 2012
522 | D/T Excavation Ch137+080-136+960 | Sat May 26 08:00:00 IDT 2012 | Fri Jun 15 17:00:00 IDT 2012
523 | Reach Lai Chi Kok DSD Obstruction | Fri Jun 15 17:00:00 IDT 2012 | Fri Jun 15 17:00:00 IDT 2012
524 | D/T Excavation Ch136+960-136+945 | Sat Jun 16 08:00:00 IDT 2012 | Mon Jun 18 17:00:00 IDT 2012
525 | D/T Excavation Ch136+945-136+920 | Tue Jun 19 08:00:00 IDT 2012 | Sun Jun 24 17:00:00 IDT 2012
526 | Reach TWL Sump Pit Ch136+920 | Sun Jun 24 17:00:00 IDT 2012 | Sun Jun 24 17:00:00 IDT 2012
527 | D/T Excavation Ch136+920-136+820 | Mon Jun 25 08:00:00 IDT 2012 | Tue Jul 03 17:00:00 IDT 2012
528 | Reach CP85 (CH136+860) | Sat Jun 30 08:00:00 IDT 2012 | Sat Jun 30 08:00:00 IDT 2012
529 | D/T Excavation Ch136+820-136+640 | Wed Jul 04 08:00:00 IDT 2012 | Tue Jul 24 17:00:00 IDT 2012
530 | D/T Excavation Ch136+640-136+583 - XRL821 | Wed Jul 25 08:00:00 IDT 2012 | Mon Jul 30 17:00:00 IDT 2012
531 | Reach CP84(CH136+601) - XRL821 | Sun Jul 29 08:00:00 IDT 2012 | Sun Jul 29 08:00:00 IDT 2012
532 | D/T Excavation Ch136+583-136+351 - XRL821 | Tue Jul 31 08:00:00 IDT 2012 | Tue Aug 28 17:00:00 IDT 2012
533 | Reach CP83 (CH136+351) XRL- 821 | Mon Sep 17 17:00:00 IDT 2012 | Mon Sep 17 17:00:00 IDT 2012
534 | D/T Excavation Ch136+351-136+101 - XRL821 | Tue Sep 18 08:00:00 IDT 2012 | Fri Oct 12 17:00:00 IST 2012
535 | Reach CP82 (CH136+101) - XRL821 | Sun Oct 07 17:00:00 IST 2012 | Sun Oct 07 17:00:00 IST 2012
536 | D/T Excavation Ch136+101-135+972 - XRL821 | Mon Oct 08 08:00:00 IST 2012 | Thu Oct 18 17:00:00 IST 2012
537 | D/T Excavation Ch135+972-135+772 - XRL821 | Fri Oct 19 08:00:00 IST 2012 | Mon Nov 05 17:00:00 IST 2012
538 | Reach CP81 (CH135+851) - XRL821 | Mon Nov 05 08:00:00 IST 2012 | Mon Nov 05 08:00:00 IST 2012
539 | D/T Excavation Ch135+772-135+737 - XRL 821 (235m) Break-in | Sat Dec 08 08:00:00 IST 2012 | Tue Dec 11 17:00:00 IST 2012
540 | D/T exit inside TBM Cavern (XRL821) | Sat Dec 15 08:00:00 IST 2012 | Wed Dec 19 17:00:00 IST 2012
541 | TBM (S631-1) Backup pull back | Mon Jan 07 08:00:00 IST 2013 | Wed Jan 16 17:00:00 IST 2013
542 | TBM (S631-1) Shield Dismantle & Removal | Mon Dec 17 08:00:00 IST 2012 | Wed Jan 30 17:00:00 IST 2013
543 | Set up Equipment for Invert Construction (Ch135+737-XRL821 to Ch137+784) | Thu Jan 31 08:00:00 IST 2013 | Sat Feb 16 17:00:00 IST 2013
544 | Tunnel Invert & Walkway (North DT- Ch135+737-XRL821 to Ch137+784) | Thu Feb 14 08:00:00 IST 2013 | Mon Aug 05 17:00:00 IDT 2013
545 | Deg. 1 Works (incl. XRL821) | Sat Jun 01 08:00:00 IDT 2013 | Sat Aug 17 17:00:00 IDT 2013
546 | Uptrack Construction (North) | Sat Mar 24 08:00:00 IST 2012 | Thu May 29 17:00:00 IDT 2014
547 | Ground Treatment (North-UT) | Sat Mar 24 08:00:00 IST 2012 | Wed Oct 03 17:00:00 IST 2012
548 | TTMS & Site Set up for Building Foundation Grouting Works | Sat Mar 24 08:00:00 IST 2012 | Mon Apr 30 17:00:00 IDT 2012
549 | Install Sleeve Pipe (Hoi Lai Shopping Centre) (UT) | Wed May 02 08:00:00 IDT 2012 | Thu May 31 17:00:00 IDT 2012
550 | Grouting Wk@N/B Ch137+570: Building Foundation (Hoi Lai Shopping Centre) (UT) | Fri Jun 01 08:00:00 IDT 2012 | Fri Aug 31 17:00:00 IDT 2012
551 | Reinstatement@N/B Ch137+570:(Hoi Lai Shopping Centre) (UT) | Sat Sep 01 08:00:00 IDT 2012 | Wed Oct 03 17:00:00 IST 2012
552 | TBM Excavation (North-UT) | Tue Jan 08 08:00:00 IST 2013 | Thu May 29 17:00:00 IDT 2014
553 | TBM (S631-1) Re-assembly | Tue Jan 08 08:00:00 IST 2013 | Wed Mar 20 17:00:00 IST 2013
554 | U/T Excavation Ch137+810-137+710 (Break-in) | Fri Mar 29 08:00:00 IDT 2013 | Sat Apr 20 17:00:00 IDT 2013
555 | Reach Cheung Sha Wan Cargo Pier Pile Obstruction | Sun Apr 07 17:00:00 IDT 2013 | Sun Apr 07 17:00:00 IDT 2013
556 | U/T Excavation Ch137+710-137+580 | Sun Apr 07 08:00:00 IDT 2013 | Wed May 01 17:00:00 IDT 2013
557 | Reach CP88(CH137+591) | Tue Apr 16 17:00:00 IDT 2013 | Tue Apr 16 17:00:00 IDT 2013
558 | U/T Excavation Ch137+580-137+550 | Fri Apr 19 08:00:00 IDT 2013 | Sat Apr 20 17:00:00 IDT 2013
559 | Reach Hoi Lai Shopping Centre (advanced work:Grouting) | Fri Apr 19 17:00:00 IDT 2013 | Fri Apr 19 17:00:00 IDT 2013
560 | U/T Excavation Ch137+550-137+200 | Sat Apr 20 08:00:00 IDT 2013 | Tue May 14 17:00:00 IDT 2013
561 | Reach CP87(CH137+393) | Sat Apr 27 17:00:00 IDT 2013 | Sat Apr 27 17:00:00 IDT 2013
562 | U/T Excavation Ch137+200-137+080 | Tue May 14 08:00:00 IDT 2013 | Sat Jun 01 17:00:00 IDT 2013
563 | Reach CP86(CH137+141) | Sun May 19 17:00:00 IDT 2013 | Sun May 19 17:00:00 IDT 2013
564 | Reach Culvert WD1 Pile Obstruction &1100dia. Foul Drain | Sun May 26 17:00:00 IDT 2013 | Sun May 26 17:00:00 IDT 2013
565 | U/T Excavation Ch137+080-136+975 | Sat May 25 08:00:00 IDT 2013 | Mon Jun 10 17:00:00 IDT 2013
566 | U/T Excavation Ch136+975-136+910 | Wed Jun 05 08:00:00 IDT 2013 | Thu Jun 20 17:00:00 IDT 2013
567 | Reach Lai Chi Kok DSD Obstructions | Fri Jun 07 17:00:00 IDT 2013 | Fri Jun 07 17:00:00 IDT 2013
568 | U/T Excavation Ch136+910-136+836 | Wed Jun 12 08:00:00 IDT 2013 | Tue Jun 18 17:00:00 IDT 2013
569 | Reach CP85(CH136+879) | Mon Jun 17 17:00:00 IDT 2013 | Mon Jun 17 17:00:00 IDT 2013
570 | U/T Excavation Ch136+836-136+656 | Wed Jun 26 08:00:00 IDT 2013 | Sat Jul 13 17:00:00 IDT 2013
571 | U/T Excavation Ch136+656-136+601-XRL821 | Wed Jul 24 08:00:00 IDT 2013 | Mon Jul 29 17:00:00 IDT 2013
572 | Reach CP84 (CH136+616)- XRL821 | Sat Jul 27 17:00:00 IDT 2013 | Sat Jul 27 17:00:00 IDT 2013
573 | U/T Excavation Ch136+601-136+365-XRL821 | Sun Jul 28 08:00:00 IDT 2013 | Tue Aug 13 17:00:00 IDT 2013
574 | Reach CP83 (CH136+365)- XRL821 | Fri Aug 23 17:00:00 IDT 2013 | Fri Aug 23 17:00:00 IDT 2013
575 | U/T Excavation Ch136+365-136+114-XRL821 | Fri Aug 23 08:00:00 IDT 2013 | Wed Sep 18 17:00:00 IDT 2013
576 | Reach CP82 (CH136+114)- XRL821 | Tue Sep 17 17:00:00 IDT 2013 | Tue Sep 17 17:00:00 IDT 2013
577 | U/T Excavation Ch136+114 -135+985-XRL821 | Tue Sep 17 08:00:00 IDT 2013 | Sat Sep 28 17:00:00 IDT 2013
578 | U/T Excavation Ch135+985-135+750-XRL821 (+235m) (Break-out) | Sun Oct 06 08:00:00 IDT 2013 | Sun Oct 27 17:00:00 IST 2013
579 | Reach CP81 (CH135+863)- XRL821 | Tue Oct 22 17:00:00 IDT 2013 | Tue Oct 22 17:00:00 IDT 2013
580 | U/T exit inside TBM Cavern - XRL821 | Sun Nov 10 08:00:00 IST 2013 | Thu Nov 14 17:00:00 IST 2013
581 | TBM (S631-1) Dismantling & Backup pull back | Fri Nov 15 08:00:00 IST 2013 | Sun Dec 29 17:00:00 IST 2013
582 | Set up Equipment for Invert Construction (Ch137+810 to Ch135+750-XRL821 ) | Mon Jan 06 08:00:00 IST 2014 | Sat Jan 18 17:00:00 IST 2014
583 | 820 section - Tunnel Invert & Walkway (UT-Northbound) (Ch137+810 to Ch136+640) | Mon Jan 20 08:00:00 IST 2014 | Wed Apr 16 17:00:00 IDT 2014
584 | 821 section - Tunnel Invert & Walkway (UT-Northbound) (Ch136+640 to Ch135+750) | Wed Feb 19 08:00:00 IST 2014 | Fri Apr 25 17:00:00 IDT 2014
585 | 821 Deg. 1 Works Ch136+640 to Ch135+750 (SA#3: 29-Jun-14) | Mon Mar 10 08:00:00 IST 2014 | Wed Apr 30 17:00:00 IDT 2014
586 | 820 Deg. 1 Works Ch137+810 to Ch136+640 (4B(i) Target: 1-Jun-14) | Sat Mar 01 08:00:00 IST 2014 | Thu May 29 17:00:00 IDT 2014
587 | TBM (S630-1) Excavation with Deg.1 Works | Tue Feb 01 08:00:00 IST 2011 | Tue Sep 29 17:00:00 IDT 2015
588 | Ground Treatment Wk at 811A Retrieval Shaft | Mon Jun 20 08:00:00 IDT 2011 | Fri Sep 23 17:00:00 IDT 2011
589 | Ground Wks for Buildings Protection (DT) - Hoi Wang Road | Mon Aug 01 08:00:00 IDT 2011 | Sat Sep 22 17:00:00 IDT 2012
590 | Ground Wks for Convergence Zones | Mon Jan 16 08:00:00 IST 2012 | Tue Nov 27 17:00:00 IST 2012
591 | Piles Removal@CLP Equipment Bldg.& Footbridges KF-119 by 805 | Sun Jan 15 08:00:00 IST 2012 | Sun Jan 15 08:00:00 IST 2012
592 | Pile Removal for Nam Cheong Property Development by 802 | Mon Apr 30 17:00:00 IDT 2012 | Mon Apr 30 17:00:00 IDT 2012
593 | TBM (S630-1) South-DT Excavation | Fri Mar 30 08:00:00 IDT 2012 | Sun Jan 06 17:00:00 IST 2013
594 | TBM (S630-1) South -UT Excavation | Sun Jan 12 08:00:00 IST 2014 | Sun Sep 14 17:00:00 IDT 2014
595 | Ground Treatment Wk at 811A Retrieval Shaft (SDT & SUT) | Wed Aug 31 08:00:00 IDT 2011 | Sun Dec 04 17:00:00 IST 2011
596 | Ground Wks for Buildings Protection (SDT) - Hoi Wang Road | Mon Aug 01 08:00:00 IDT 2011 | Mon Sep 17 17:00:00 IDT 2012
597 | Ground Wks for Convergence Zones (SDT & SUT) | Mon Jan 16 08:00:00 IST 2012 | Mon Jan 28 17:00:00 IST 2013
598 | Piles Removal@CLP Equipment Bldg.& Footbridges KF-119 by 805 (SDT & SUT) | Sun Nov 13 17:00:00 IST 2011 | Sun Nov 13 17:00:00 IST 2011
599 | Grouting Wk@N/B Ch140+340: Bldg. Foundation (Y.M.T.School) (SUT) | Thu Feb 02 08:00:00 IST 2012 | Tue Jun 12 17:00:00 IDT 2012
600 | Pile Removal for Nam Cheong Property Development by 802 (SDT & SUT) | Sun Jan 15 08:00:00 IST 2012 | Sun Jan 15 08:00:00 IST 2012
601 | TKT Grouting Works - Zone 1 | Mon Feb 13 08:00:00 IST 2012 | Fri Jul 20 17:00:00 IDT 2012
602 | TKT Grouting Works - Zone 2 | Mon Jan 16 08:00:00 IST 2012 | Mon Aug 20 17:00:00 IDT 2012
603 | TKT Grouting Works - Zone 4 | Mon Mar 26 08:00:00 IST 2012 | Mon Nov 05 17:00:00 IST 2012
604 | TKT Grouting Works - Zone 5 | Tue Oct 09 08:00:00 IST 2012 | Mon Apr 22 17:00:00 IDT 2013
605 | Downtrack Construction (South) | Tue Feb 01 08:00:00 IST 2011 | Tue Sep 29 17:00:00 IDT 2015
606 | TBM (S630-1) South-DT Excavation | Thu Apr 12 08:00:00 IDT 2012 | Tue Mar 19 17:00:00 IST 2013
607 | Ground Treatment (South-DT) | Tue Feb 01 08:00:00 IST 2011 | Mon Mar 18 17:00:00 IST 2013
608 | Access Date- Works Area 12.2 | Mon Feb 28 08:00:00 IST 2011 | Mon Feb 28 08:00:00 IST 2011
609 | Site Set up for Ground Treatment at 811A Retrieval Shaft | Sun Jun 19 08:00:00 IDT 2011 | Fri Jul 01 17:00:00 IDT 2011
610 | Ground Treatment Wk at 811A Retrieval Shaft | Sun Jun 19 08:00:00 IDT 2011 | Wed Oct 05 17:00:00 IST 2011
611 | TTMS for Building Foundation Grouting Works (Stage 1) | Mon Feb 28 08:00:00 IST 2011 | Wed Jun 15 17:00:00 IDT 2011
612 | Accesss Date for Wk Area 12.1 (Subject to SLG Approval) | Thu Jul 21 08:00:00 IDT 2011 | Thu Jul 21 08:00:00 IDT 2011
613 | Grouting Wk@Ch140+150: Bldg.Foundation (Charming Garden Blk.8) | Thu Jul 21 08:00:00 IDT 2011 | Wed Aug 31 17:00:00 IDT 2011
614 | Suspension of Grouting Wk@S/B Ch140+150(Charming Garden Blk.8) | Thu Jun 30 08:00:00 IDT 2011 | Thu Jun 30 08:00:00 IDT 2011
615 | Suspension Period for Grouting Wk in (Charming Garden Blk.8) | Mon Aug 01 08:00:00 IDT 2011 | Tue Aug 09 17:00:00 IDT 2011
616 | Re-mobilization for Grouting Wk in (Charming Garden Blk.8) | Mon Aug 01 08:00:00 IDT 2011 | Tue Aug 02 17:00:00 IDT 2011
617 | Grouting Wk@ Ch140+150:(Charming Garden Blk.8) remaining | Thu Jul 21 08:00:00 IDT 2011 | Wed Aug 31 17:00:00 IDT 2011
618 | Reinstatement@ Ch140+150:(Charming Garden Blk.8) & TTMs Stage 2 | Wed Aug 31 08:00:00 IDT 2011 | Thu Sep 15 17:00:00 IDT 2011
619 | Grouting Wk@S/B Ch140+080: Bldg.Foundation (Hoi Fu Court) | Tue Aug 09 08:00:00 IDT 2011 | Mon Dec 12 17:00:00 IST 2011
620 | Reinstatement @ Hoi Fu Court | Wed Aug 31 08:00:00 IDT 2011 | Wed Nov 16 17:00:00 IST 2011
621 | TTMS for Building Foundation Grouting Works (Stage 2) & Site Setup | Wed Feb 22 16:08:00 IST 2012 | Wed Mar 21 16:08:00 IST 2012
622 | Install Sleeve for Grouting works (Charming Garden Blk.9) | Fri Aug 31 08:00:00 IDT 2012 | Sat Sep 29 17:00:00 IST 2012
623 | Grouting Wk@S/B Ch140+200: Bldg.Foundation (Charming Garden Blk.9) | Wed Oct 03 08:00:00 IST 2012 | Mon Oct 29 17:00:00 IST 2012
624 | Reinstatement @ Charming Garden Blk.9 | Wed Jan 09 08:00:00 IST 2013 | Mon Feb 18 17:00:00 IST 2013
625 | GI works for Hoi Wang Road | Tue Feb 01 08:00:00 IST 2011 | Thu Jun 23 17:00:00 IDT 2011
626 | GI works for Tai Kok Tsui | Tue Feb 01 08:00:00 IST 2011 | Thu Dec 01 17:00:00 IST 2011
627 | Design of Ground Treatment for Tunneling (Ch140+080-Ch140+200) | Fri Apr 08 08:00:00 IDT 2011 | Sun Jun 26 17:00:00 IDT 2011
628 | MTR's Review & Comments for Design of Ground Treatment for Tunneling | Sun Jun 19 08:00:00 IDT 2011 | Sun Jun 19 08:00:00 IDT 2011
629 | MTR's Comments & Approval | Sun Jun 19 08:00:00 IDT 2011 | Fri Jul 08 17:00:00 IDT 2011
630 | Prepared Re-submission of Ground Treatment for Tunneling | Sun Jun 19 08:00:00 IDT 2011 | Thu Jun 30 17:00:00 IDT 2011
631 | Design Approval & Issue Construction Instruction MTR | Sun Jun 19 08:00:00 IDT 2011 | Sun Jul 03 17:00:00 IDT 2011
632 | TTMS for Convergence Zone (Stage 2 & 3) | Wed Aug 31 08:00:00 IDT 2011 | Sat Sep 17 17:00:00 IDT 2011
633 | Install Sleeve Pipe (Zone B) | Mon Jan 16 08:00:00 IST 2012 | Sat Mar 03 17:00:00 IST 2012
634 | Convergence Zone Grouting Wk@ Ch140+330 to Ch140+342 (Zone B) | Mon Jan 16 08:00:00 IST 2012 | Tue May 22 17:00:00 IDT 2012
635 | Reinstatement@ Ch140+330 to Ch140+342 (Zone B) | Mon Dec 03 08:00:00 IST 2012 | Wed Jan 02 17:00:00 IST 2013
636 | Install Sleeve Pipe (Zones D) | Mon Jan 16 08:00:00 IST 2012 | Fri Mar 02 17:00:00 IST 2012
637 | Convergence Zone Grouting Wk@ Ch140+361 to Ch140+380 (Zones D) | Mon Jan 16 08:00:00 IST 2012 | Sat Apr 21 17:00:00 IDT 2012
638 | Convergence Zone Grouting Wk@ Ch140+361 to Ch140+380 (Zones E) | Wed Oct 03 08:00:00 IST 2012 | Thu Jan 17 17:00:00 IST 2013
639 | Install Sleeve Pipe (Zone A) | Wed Feb 01 08:00:00 IST 2012 | Tue Feb 28 17:00:00 IST 2012
640 | Convergence Zone Grouting Wk@ Ch140+287 to Ch140+330 (Zone A) | Mon Apr 02 08:00:00 IDT 2012 | Mon Jul 09 17:00:00 IDT 2012
641 | Enlarge for TTMs Stage 4 | Wed Oct 03 08:00:00 IST 2012 | Wed Oct 24 17:00:00 IST 2012
642 | Install Sleeve Pipe (Zone C) | Sat Jun 02 08:00:00 IDT 2012 | Wed Jul 04 17:00:00 IDT 2012
643 | Convergence Zone Grouting Wk@ Ch140+342 to Ch140+361 (Zone C) | Thu Jul 05 08:00:00 IDT 2012 | Sat Nov 03 17:00:00 IST 2012
644 | Reinstatement for Convergence Zone | Fri Feb 01 08:00:00 IST 2013 | Mon Mar 18 17:00:00 IST 2013
645 | Tai Kok Tsui Grouting Works | Mon Jan 16 08:00:00 IST 2012 | Fri Nov 30 08:00:00 IST 2012
646 | Zone 1 | Fri Feb 10 08:00:00 IST 2012 | Fri Aug 31 08:00:00 IDT 2012
647 | TKT Zone 1 - TGLA granted | Fri Feb 10 08:00:00 IST 2012 | Fri Feb 10 08:00:00 IST 2012
648 | TKT Zone 1 - Access Date of works area | Sat Feb 11 08:00:00 IST 2012 | Sat Feb 11 08:00:00 IST 2012
649 | TKT Zone 1 - Trial Pit | Mon Feb 13 08:00:00 IST 2012 | Sat Feb 18 17:00:00 IST 2012
650 | TKT Zone 1 - Site Clearance + Tree Transplant | Mon Feb 20 08:00:00 IST 2012 | Thu Mar 01 17:00:00 IST 2012
651 | TKT Zone 1 - TTMS & Prepare Working platform | Fri Mar 02 08:00:00 IST 2012 | Mon Mar 26 17:00:00 IST 2012
652 | TKT Zone 1 - Install sleeve pipes | Tue Mar 27 08:00:00 IST 2012 | Mon Apr 16 17:00:00 IDT 2012
653 | TKT Zone 1 - Ground Treatment Works (TAM grouting) | Tue Apr 17 08:00:00 IDT 2012 | Mon Jul 16 17:00:00 IDT 2012
654 | TKT Zone 1 - Permeability Test | Tue Jul 17 08:00:00 IDT 2012 | Fri Jul 20 17:00:00 IDT 2012
655 | TKT Zone 1 - TBM Reach Zone 1 | Fri Aug 31 08:00:00 IDT 2012 | Fri Aug 31 08:00:00 IDT 2012
656 | Zone 2 | Mon Jan 16 08:00:00 IST 2012 | Fri Aug 31 08:00:00 IDT 2012
657 | TKT Zone 2 - TTMS (Part 1) | Mon Jan 16 08:00:00 IST 2012 | Mon Jan 16 17:00:00 IST 2012
658 | TKT Zone 2 - Trial pit | Tue Jan 17 08:00:00 IST 2012 | Sat Feb 11 17:00:00 IST 2012
659 | TKT Zone 2 - Site preparation works | Mon Feb 13 08:00:00 IST 2012 | Sat Feb 18 17:00:00 IST 2012
660 | TKT Zone 2 - Install sleeve pipes (Part 1) | Mon Feb 20 08:00:00 IST 2012 | Tue Feb 28 17:00:00 IST 2012
661 | TKT Zone 2 - TTMS (Part 2) | Wed Feb 29 08:00:00 IST 2012 | Tue Mar 13 17:00:00 IST 2012
662 | TKT Zone 2 - Trial pit (Part 2) | Wed Mar 14 08:00:00 IST 2012 | Sat Mar 24 17:00:00 IST 2012
663 | TKT Zone 2 - Site preparation works | Mon Mar 26 08:00:00 IST 2012 | Thu Mar 29 17:00:00 IST 2012
664 | TKT Zone 2 - Install sleeve pipes (Part 2) | Fri Mar 30 08:00:00 IDT 2012 | Fri Apr 13 17:00:00 IDT 2012
665 | TKT Zone 2 - Ground Treatment Works (TAM grouting) (Part 2) | Sat Apr 14 08:00:00 IDT 2012 | Mon May 28 17:00:00 IDT 2012
666 | TKT Zone 2 - Re-arrange TTMS (Part 1) | Tue May 29 08:00:00 IDT 2012 | Thu Jun 07 17:00:00 IDT 2012
667 | TKT Zone 2 - Ground Treatment Works (TAM grouting) (Part 1) | Sat Jun 09 08:00:00 IDT 2012 | Wed Aug 15 17:00:00 IDT 2012
668 | TKT Zone 2 - Permeability Test | Thu Aug 16 08:00:00 IDT 2012 | Mon Aug 20 17:00:00 IDT 2012
669 | TKT Zone 2 - Temporary reinstatement | Tue Aug 21 08:00:00 IDT 2012 | Wed Aug 29 17:00:00 IDT 2012
670 | TKT Zone 2 - TBM Reach Zone 2 | Fri Aug 31 08:00:00 IDT 2012 | Fri Aug 31 08:00:00 IDT 2012
671 | Zone 3 | Mon Jan 16 08:00:00 IST 2012 | Fri Nov 30 08:00:00 IST 2012
672 | TKT Zone 3 - TTMS (Part 1) | Mon Jan 16 08:00:00 IST 2012 | Mon Jan 16 17:00:00 IST 2012
673 | TKT Zone 3 - Trial pit + grout pattern design | Tue Jan 17 08:00:00 IST 2012 | Thu Feb 09 17:00:00 IST 2012
674 | TKT Zone 3 - Install sleeve pipes (Part 1) | Fri Feb 10 08:00:00 IST 2012 | Sat Feb 18 17:00:00 IST 2012
675 | TKT Zone 3 - TTMS (Part 2) + site preparation + Install sleeve pipes (Part 2) | Mon Feb 20 08:00:00 IST 2012 | Tue Mar 20 17:00:00 IST 2012
676 | TKT Zone 3 - Site setup | Wed Mar 21 08:00:00 IST 2012 | Tue Mar 27 17:00:00 IST 2012
677 | TKT Zone 3 - Drilling for Ground treatment works | Wed Mar 28 08:00:00 IST 2012 | Mon Apr 30 17:00:00 IDT 2012
678 | TKT Zone 3 - Further soil investigation to review ground treatment requirement | Sat Apr 14 08:00:00 IDT 2012 | Mon Apr 30 17:00:00 IDT 2012
679 | TKT Zone 3 - Decision to confirm ground treatment requirement | Mon Apr 30 17:00:00 IDT 2012 | Mon Apr 30 17:00:00 IDT 2012
680 | TKT Zone 3 - TBM Reach Zone 3 | Fri Nov 30 08:00:00 IST 2012 | Fri Nov 30 08:00:00 IST 2012
681 | TBM Excavation (South-DT) | Sun Jan 15 08:00:00 IST 2012 | Tue Sep 29 17:00:00 IDT 2015
682 | D/T Excavation Ch139+872-139+875 | Thu Aug 15 08:00:00 IDT 2013 | Sat Aug 17 17:00:00 IDT 2013
683 | TBM resume at Ch139+875 | Fri Aug 16 08:00:00 IDT 2013 | Fri Aug 16 08:00:00 IDT 2013
684 | TBM (S630-1) Delivery on Site | Sun Jan 15 08:00:00 IST 2012 | Sun Jan 15 08:00:00 IST 2012
685 | TBM (S630-1) Assembly, and T&C | Fri Mar 16 08:00:00 IST 2012 | Wed May 30 17:00:00 IDT 2012
686 | D/T TBM (S630-1) Break-in & Excavation Ch137+941-137+967 | Wed Mar 21 08:00:00 IST 2012 | Thu Mar 29 17:00:00 IST 2012
687 | Reach Rising Main & FMO Pier A Obstruction | Thu Mar 29 17:00:00 IST 2012 | Thu Mar 29 17:00:00 IST 2012
688 | D/T Excavation Ch137+967-138+025 | Fri Mar 30 08:00:00 IDT 2012 | Wed Apr 18 17:00:00 IDT 2012
689 | D/T Excavation Ch138+025-138+043 | Thu Apr 19 08:00:00 IDT 2012 | Fri Apr 20 17:00:00 IDT 2012
690 | Reach FMO Pier B Pile Obstruction Ch138+043 | Fri Apr 20 17:00:00 IDT 2012 | Fri Apr 20 17:00:00 IDT 2012
691 | D/T Excavation Ch138+043-138+109 | Sat Apr 21 08:00:00 IDT 2012 | Fri Apr 27 17:00:00 IDT 2012
692 | Reach CP89 (CH138+055) | Sun Apr 22 08:00:00 IDT 2012 | Sun Apr 22 08:00:00 IDT 2012
693 | D/T Excavation Ch138+109-138+149 | Sat Apr 28 08:00:00 IDT 2012 | Mon Apr 30 17:00:00 IDT 2012
694 | Obstructions Removal Below Nam Cheong Property/802 (11Dec2011-Contract) | Sun Jan 15 08:00:00 IST 2012 | Sun Jan 15 08:00:00 IST 2012
695 | Unobstructed Passage Available (30April2012) | Mon Apr 30 08:00:00 IDT 2012 | Mon Apr 30 08:00:00 IDT 2012
696 | Reach Nam Cheong Property Development (Pile removed by 802) | Mon Apr 30 17:00:00 IDT 2012 | Mon Apr 30 17:00:00 IDT 2012
697 | Obstructions Removal Below Nam Cheong Property by 802 (30Apr12) | Mon Apr 30 17:00:00 IDT 2012 | Mon Apr 30 17:00:00 IDT 2012
698 | D/T Excavation Ch138+149-Ch138+170 | Tue May 01 08:00:00 IDT 2012 | Wed May 02 17:00:00 IDT 2012
699 | D/T Excavation Ch138+170-138+420 | Thu May 03 08:00:00 IDT 2012 | Tue May 29 17:00:00 IDT 2012
700 | Reach CP90 (CH138+315) | Sat May 19 08:00:00 IDT 2012 | Sat May 19 08:00:00 IDT 2012
701 | D/T Excavation Ch138+420-138+457 | Wed May 30 08:00:00 IDT 2012 | Fri Jun 01 17:00:00 IDT 2012
702 | Reach Shum Shui Po Pier Pile Obstruction Ch138+457 | Fri Jun 01 17:00:00 IDT 2012 | Fri Jun 01 17:00:00 IDT 2012
703 | D/T Excavation Ch138+457-138+480 | Sat Jun 02 08:00:00 IDT 2012 | Sun Jun 03 17:00:00 IDT 2012
704 | D/T Excavation Ch138+480-138+590 | Mon Jun 04 08:00:00 IDT 2012 | Tue Jun 12 17:00:00 IDT 2012
705 | Reach CP91 (CH138+521) | Thu Jun 07 08:00:00 IDT 2012 | Thu Jun 07 08:00:00 IDT 2012
706 | Reach YC2 Culvert Pile Obstruction Ch138+590 | Tue Jun 12 17:00:00 IDT 2012 | Tue Jun 12 17:00:00 IDT 2012
707 | D/T Excavation Ch138+590-138+771 | Wed Jun 13 08:00:00 IDT 2012 | Wed Jun 27 17:00:00 IDT 2012
708 | Reach CP92 (CH138+771) | Wed Jun 27 17:00:00 IDT 2012 | Wed Jun 27 17:00:00 IDT 2012
709 | D/T Excavation Ch138+771-138+950 | Thu Jun 28 08:00:00 IDT 2012 | Tue Jul 10 17:00:00 IDT 2012
710 | Reach NC1 Culvert Pile Obstruction Ch138+950 | Tue Jul 10 17:00:00 IDT 2012 | Tue Jul 10 17:00:00 IDT 2012
711 | D/T Excavation Ch138+950-139+044 | Wed Jul 11 08:00:00 IDT 2012 | Tue Jul 17 17:00:00 IDT 2012
712 | Reach CP93 (CH138+996) | Sat Jul 14 08:00:00 IDT 2012 | Sat Jul 14 08:00:00 IDT 2012
713 | Piles Removal@CLP Equipment Bldg.& Footbridges KF-119 by 805 | Sun Jan 15 08:00:00 IST 2012 | Sun Jan 15 08:00:00 IST 2012
714 | Reach Footbridge KF119 (Pile removed by 805) | Fri Aug 31 08:00:00 IDT 2012 | Fri Aug 31 08:00:00 IDT 2012
715 | D/T Excavation Ch139+044-139+100 | Fri Aug 31 08:00:00 IDT 2012 | Wed Sep 05 17:00:00 IDT 2012
716 | D/T Excavation Ch139+100-139+120 | Thu Sep 06 08:00:00 IDT 2012 | Sun Sep 09 17:00:00 IDT 2012
717 | D/T Excavation Ch139+120-139+350 | Mon Sep 10 08:00:00 IDT 2012 | Wed Nov 07 17:00:00 IST 2012
718 | Reach CP94(CH139+265) | Wed Oct 24 17:00:00 IST 2012 | Wed Oct 24 17:00:00 IST 2012
719 | D/T Excavation Ch139+350-139+450 | Thu Nov 15 08:00:00 IST 2012 | Wed Nov 28 17:00:00 IST 2012
720 | D/T Excavation Ch139+450-139+825 | Tue Nov 13 08:00:00 IST 2012 | Sat Dec 15 17:00:00 IST 2012
721 | Reach CP95(CH139+504) | Sun Nov 18 08:00:00 IST 2012 | Sun Nov 18 08:00:00 IST 2012
722 | Reach CP96(CH139+711) | Fri Dec 28 17:00:00 IST 2012 | Fri Dec 28 17:00:00 IST 2012
723 | D/T Excavation Ch139+825-139+872 | Mon Jan 21 08:00:00 IST 2013 | Wed Jan 30 17:00:00 IST 2013
724 | **HWR H-pile Obstruction Removal | Tue Jan 22 08:00:00 IST 2013 | Thu Aug 15 17:00:00 IDT 2013
725 | D/T Excavation Ch139+875 -139+920 | Fri Aug 16 08:00:00 IDT 2013 | Mon Aug 19 17:00:00 IDT 2013
726 | D/T Excavation Ch139+920-139+950 | Sat Aug 24 08:00:00 IDT 2013 | Sun Aug 25 17:00:00 IDT 2013
727 | D/T Excavation Ch139+950-140+010 | Mon Aug 26 08:00:00 IDT 2013 | Thu Aug 29 17:00:00 IDT 2013
728 | Reach CP97 (CH139+961) | Mon Aug 26 17:00:00 IDT 2013 | Mon Aug 26 17:00:00 IDT 2013
729 | D/T Excavation Ch140+010-140+180 | Sat Aug 31 08:00:00 IDT 2013 | Tue Sep 10 17:00:00 IDT 2013
730 | Reach Hoi Fu Court (CH140+063) | Tue Sep 03 17:00:00 IDT 2013 | Tue Sep 03 17:00:00 IDT 2013
731 | Reach Charming Garden No.8 (CH140+139) | Sun Sep 08 17:00:00 IDT 2013 | Sun Sep 08 17:00:00 IDT 2013
732 | D/T Excavation Ch140+180-140+270 | Wed Sep 11 08:00:00 IDT 2013 | Wed Sep 18 17:00:00 IDT 2013
733 | Reach CP98(CH140+211) | Fri Sep 13 17:00:00 IDT 2013 | Fri Sep 13 17:00:00 IDT 2013
734 | Reach Charming Garden No.9 (CH140+207) | Fri Sep 13 17:00:00 IDT 2013 | Fri Sep 13 17:00:00 IDT 2013
735 | Advance Noice to Contract 811A for TBM Break In (30d) | Fri Aug 16 17:00:00 IDT 2013 | Fri Aug 16 17:00:00 IDT 2013
736 | D/T Excavation Ch140+270-140+385-Shaft 811A | Tue Sep 17 08:00:00 IDT 2013 | Sat Sep 28 17:00:00 IDT 2013
737 | Exit Convergence Zone (Ch140+287~) | Wed Sep 18 17:00:00 IDT 2013 | Wed Sep 18 17:00:00 IDT 2013
738 | D/T exit Box Cleaning for TBM Dismantling | Fri Sep 25 08:00:00 IDT 2015 | Tue Sep 29 17:00:00 IDT 2015
739 | Advance Noice to Contract 811A for Set Up of TBM Retrieval (60d) | Thu Aug 01 17:00:00 IDT 2013 | Thu Aug 01 17:00:00 IDT 2013
740 | D/T Preparation Works inside Exit Shaft 811A | Mon Aug 26 08:00:00 IDT 2013 | Sat Sep 28 17:00:00 IDT 2013
741 | TBM (S630-1) Backup pull back | Mon Oct 07 08:00:00 IDT 2013 | Wed Oct 16 17:00:00 IDT 2013
742 | TBM (S630-1) Shield Dismantle & Removal | Mon Sep 30 08:00:00 IDT 2013 | Sun Nov 10 17:00:00 IST 2013
743 | Setup Equipment for Invert & Walkway Construction (Ch140+385-811A Shaft to Ch139+224-CP94) | Mon Nov 18 08:00:00 IST 2013 | Sat Nov 30 17:00:00 IST 2013
744 | Tunnel Invert & Walkway (811A side - Ch140+385-811A Shaft to Ch139+224-CP94) | Mon Dec 02 08:00:00 IST 2013 | Wed Mar 05 17:00:00 IST 2014
745 | Setup Equipment for Invert & Walkway Construction (Ch137+941-NAC Shaft to Ch139+224-CP94) | Tue Feb 04 08:00:00 IST 2014 | Fri Feb 14 17:00:00 IST 2014
746 | Tunnel Invert & Walkway (820 side - Ch137+941-NAC Shaft to Ch139+224-CP94) | Wed Feb 12 08:00:00 IST 2014 | Mon May 19 17:00:00 IDT 2014
747 | Deg. 1 Works (4A(ii) Target: 18-May-14) | Sat Mar 01 08:00:00 IST 2014 | Mon Jun 23 17:00:00 IDT 2014
748 | Uptrack Construction (South) | Wed Aug 31 08:00:00 IDT 2011 | Mon Jan 26 17:00:00 IST 2015
749 | Ground Treatment (South-UT) | Wed Aug 31 08:00:00 IDT 2011 | Wed Nov 20 17:00:00 IST 2013
750 | Works Area 12.1 (Subject to SLG Approval) | Wed Aug 31 08:00:00 IDT 2011 | Wed Aug 31 08:00:00 IDT 2011
751 | Site Set up for Y.M.T School Grouting Works | Wed Aug 31 08:00:00 IDT 2011 | Mon Oct 31 17:00:00 IST 2011
752 | Install Sleeve Pipe (Y.M.T. Catholic Primary School) (UT) | Mon Jan 16 08:00:00 IST 2012 | Tue Feb 14 17:00:00 IST 2012
753 | Grouting Wk@N/B Ch140+340: Bldg. Foundation (Y.M.T. Catholic Primary School) (UT) | Mon Jan 16 08:00:00 IST 2012 | Thu Apr 19 17:00:00 IDT 2012
754 | Reinstatement Works for Y.M.T. School | Fri Aug 31 08:00:00 IDT 2012 | Sat Sep 29 17:00:00 IST 2012
755 | Tai Kok Tsui Grouting Works | Mon Mar 26 08:00:00 IST 2012 | Wed Nov 20 17:00:00 IST 2013
756 | Zone 4 | Mon Mar 26 08:00:00 IST 2012 | Wed Nov 20 17:00:00 IST 2013
757 | TKT Zone 4 - Trial pit | Mon Mar 26 08:00:00 IST 2012 | Wed Apr 11 17:00:00 IDT 2012
758 | TKT Zone 4 - Sleeves installation | Wed Oct 03 08:00:00 IST 2012 | Thu Oct 11 17:00:00 IST 2012
759 | TKT Zone 4 - Ground Treatment Works (TAM grouting) | Fri Oct 12 08:00:00 IST 2012 | Wed Jan 09 17:00:00 IST 2013
760 | TKT Zone 4 - Permeability Test | Mon Apr 15 08:00:00 IDT 2013 | Thu Apr 18 17:00:00 IDT 2013
761 | TKT Zone 4 - Reinstatement | Mon Aug 12 08:00:00 IDT 2013 | Wed Nov 20 17:00:00 IST 2013
762 | Zone 5 | Fri Nov 09 08:00:00 IST 2012 | Thu Jul 04 17:00:00 IDT 2013
763 | TKT Zone 5 - Trial pit | Fri Nov 30 08:00:00 IST 2012 | Sat Dec 22 17:00:00 IST 2012
764 | TKT Zone 5 - Install guide sleeves (Stage 1) | Mon Dec 24 08:00:00 IST 2012 | Fri Jan 11 17:00:00 IST 2013
765 | TKT Zone 5 - TTMS (Part 2) + Trial pit | Fri Nov 09 08:00:00 IST 2012 | Sat Dec 15 17:00:00 IST 2012
766 | TKT Zone 5 - Install guide sleeves (Stage 2) | Wed Jan 02 08:00:00 IST 2013 | Wed Jan 16 17:00:00 IST 2013
767 | TKT Zone 5 - Ground Treatment Works (TAM grouting) Part 2 | Thu Jan 17 08:00:00 IST 2013 | Mon Mar 18 17:00:00 IST 2013
768 | TKT Zone 5 - Rearrange TTMS (Part 1) | Thu Jan 10 08:00:00 IST 2013 | Wed Jan 23 17:00:00 IST 2013
769 | TKT Zone 5 - Ground Treatment Works (TAM grouting) Part 1 | Fri Jan 11 08:00:00 IST 2013 | Mon Mar 04 17:00:00 IST 2013
770 | TKT Zone 5 - Permeability Test | Mon Mar 25 08:00:00 IST 2013 | Thu Mar 28 17:00:00 IST 2013
771 | TKT Zone 5 - Reinstatement | Tue Apr 30 08:00:00 IDT 2013 | Thu Jul 04 17:00:00 IDT 2013
772 | Zone 6 | Sat Apr 14 08:00:00 IDT 2012 | Mon Apr 30 17:00:00 IDT 2012
773 | TKT Zone 6 - Further soil investigation to review ground treatment requirement | Sat Apr 14 08:00:00 IDT 2012 | Mon Apr 30 17:00:00 IDT 2012
774 | TKT Zone 6 - Decision to confirm ground treatment requirement | Mon Apr 30 17:00:00 IDT 2012 | Mon Apr 30 17:00:00 IDT 2012
775 | TBM Excavation (South-UT) | Sun Jan 15 08:00:00 IST 2012 | Mon Jan 26 17:00:00 IST 2015
776 | TBM S630-1 Re-assembly | Tue Oct 15 08:00:00 IDT 2013 | Fri Dec 06 17:00:00 IST 2013
777 | U/T Excavation Ch137+968-137+993 (Break-in) | Sat Dec 14 08:00:00 IST 2013 | Thu Dec 19 17:00:00 IST 2013
778 | Reach Rising Main & FMO Pier A Obstruction | Thu Dec 19 17:00:00 IST 2013 | Thu Dec 19 17:00:00 IST 2013
779 | U/T Excavation Ch137+993-138+040 | Thu Dec 19 08:00:00 IST 2013 | Mon Dec 30 17:00:00 IST 2013
780 | U/T Excavation Ch138+040-138+070 | Wed Dec 25 08:00:00 IST 2013 | Thu Dec 26 17:00:00 IST 2013
781 | Reach FMO Pier B Pile Obstruction Ch138+070 | Thu Dec 26 17:00:00 IST 2013 | Thu Dec 26 17:00:00 IST 2013
782 | U/T Excavation Ch138+070-138+175 | Thu Dec 26 08:00:00 IST 2013 | Thu Jan 02 17:00:00 IST 2014
783 | Reach CP89 (CH138+081) | Fri Dec 27 17:00:00 IST 2013 | Fri Dec 27 17:00:00 IST 2013
784 | Obstructions Removal BelowNamCheong Property/ 802 (11Dec2011-Contract) | Sun Jan 15 08:00:00 IST 2012 | Sun Jan 15 08:00:00 IST 2012
785 | Unobstructed Pasage Available (30 April 2013) (further confirm by MTR) | Tue Apr 30 17:00:00 IDT 2013 | Tue Apr 30 17:00:00 IDT 2013
786 | Reach Nam Cheong Property Property / 802 | Mon Dec 30 17:00:00 IST 2013 | Mon Dec 30 17:00:00 IST 2013
787 | Obstructions Removal Below Nam Cheong Property by 802 | Tue Apr 30 17:00:00 IDT 2013 | Tue Apr 30 17:00:00 IDT 2013
788 | U/T Excavation Ch138+175 -138+450 | Sat Jan 04 08:00:00 IST 2014 | Sun Jan 26 17:00:00 IST 2014
789 | Reach CP90 (CH138+341) | Fri Apr 04 17:00:00 IDT 2014 | Fri Apr 04 17:00:00 IDT 2014
790 | U/T Excavation Ch138+450-138+490 | Wed Apr 09 08:00:00 IDT 2014 | Fri Apr 11 17:00:00 IDT 2014
791 | Reach Shum Shui Po Pier Pile Obstruction Ch138+490 | Fri Apr 11 17:00:00 IDT 2014 | Fri Apr 11 17:00:00 IDT 2014
792 | U/T Excavation Ch138+490-138+610 | Fri Apr 11 08:00:00 IDT 2014 | Fri Apr 18 17:00:00 IDT 2014
793 | Reach CP91 (CH138+546) | Mon Apr 14 17:00:00 IDT 2014 | Mon Apr 14 17:00:00 IDT 2014
794 | Reach YC2 Culvert Pile Obstruction Ch138+610 | Thu Apr 17 17:00:00 IDT 2014 | Thu Apr 17 17:00:00 IDT 2014
795 | U/T Excavation Ch138+610-138+670 | Thu Apr 17 08:00:00 IDT 2014 | Sun Apr 20 17:00:00 IDT 2014
796 | Reach NC1 Culvert Pile Obstruction Ch138+670 | Tue Apr 22 17:00:00 IDT 2014 | Tue Apr 22 17:00:00 IDT 2014
797 | U/T Excavation Ch138+670-139+026 | Tue Apr 22 08:00:00 IDT 2014 | Fri May 16 17:00:00 IDT 2014
798 | Reach CP92 (CH138+796) | Tue Apr 29 17:00:00 IDT 2014 | Tue Apr 29 17:00:00 IDT 2014
799 | Reach CP93 (CH139+021) | Sun May 11 17:00:00 IDT 2014 | Sun May 11 17:00:00 IDT 2014
800 | Piles Removal@CLP Equipment Bldg.& Footbridges KF-119 by 805 | Sun Jan 15 08:00:00 IST 2012 | Sun Jan 15 08:00:00 IST 2012
801 | Reach Footbridge KF119 (Piles removed by 805) | Wed Mar 12 17:00:00 IST 2014 | Wed Mar 12 17:00:00 IST 2014
802 | U/T Excavation Ch139+026-139+150 | Mon May 12 08:00:00 IDT 2014 | Tue May 20 17:00:00 IDT 2014
803 | U/T Excavation Ch139+150-139+360 | Thu May 22 08:00:00 IDT 2014 | Wed Jul 09 17:00:00 IDT 2014
804 | Reach CP94 (CH139+287) | Fri Jun 27 17:00:00 IDT 2014 | Fri Jun 27 17:00:00 IDT 2014
805 | U/T Excavation Ch139+360-139+530 | Fri Jun 27 08:00:00 IDT 2014 | Mon Jul 14 17:00:00 IDT 2014
806 | Reach CP95 (CH139+524) | Wed Jul 23 17:00:00 IDT 2014 | Wed Jul 23 17:00:00 IDT 2014
807 | U/T Excavation Ch139+530-139+825 | Thu Jul 24 08:00:00 IDT 2014 | Sat Aug 16 17:00:00 IDT 2014
808 | Reach CP96 (CH139+729) | Sat Aug 16 17:00:00 IDT 2014 | Sat Aug 16 17:00:00 IDT 2014
809 | U/T Excavation Ch139+825-139+875 | Sat Aug 30 08:00:00 IDT 2014 | Mon Sep 08 17:00:00 IDT 2014
810 | U/T Excavation Ch139+875-139+950 | Thu Sep 04 08:00:00 IDT 2014 | Wed Sep 10 17:00:00 IDT 2014
811 | U/T Excavation Ch139+950-140+010 | Mon Sep 08 08:00:00 IDT 2014 | Thu Sep 11 17:00:00 IDT 2014
812 | Reach CP97 (CH139+977) | Tue Sep 09 17:00:00 IDT 2014 | Tue Sep 09 17:00:00 IDT 2014
813 | Advance Noice to Contract 811A for Set Up of TBM Retrieval (60d) | Fri Jun 27 17:00:00 IDT 2014 | Fri Jun 27 17:00:00 IDT 2014
814 | Advance Noice to Contract 811A for TBM Break-out (30d) | Fri Aug 15 17:00:00 IDT 2014 | Fri Aug 15 17:00:00 IDT 2014
815 | U/T Excavation Ch140+010-140+394-Shaft 811A (Break-out) | Wed Sep 10 08:00:00 IDT 2014 | Wed Oct 08 17:00:00 IDT 2014
816 | Reach CP98 (CH140+226) | Fri Sep 19 17:00:00 IDT 2014 | Fri Sep 19 17:00:00 IDT 2014
817 | Reach YMT School (CH140+335) | Wed Sep 24 17:00:00 IDT 2014 | Wed Sep 24 17:00:00 IDT 2014
818 | U/T exit Box Cleaning for TBM Dismantling | Tue Sep 30 08:00:00 IDT 2014 | Sat Oct 04 17:00:00 IDT 2014
819 | U/T Preparation Works inside Exit Shaft 811A | Mon Sep 01 08:00:00 IDT 2014 | Sat Oct 04 17:00:00 IDT 2014
820 | TBM (S630-1) Shield Dismantle & Removal | Mon Oct 06 08:00:00 IDT 2014 | Mon Nov 10 17:00:00 IST 2014
821 | TBM (S630-1) Backup Removal | Sat Nov 01 08:00:00 IST 2014 | Mon Nov 10 17:00:00 IST 2014
822 | Setup Equipment for Invert & Walkway Construction (Ch137+941-NAC Shaft to Ch139+435) (7 working days) | Thu Oct 16 08:00:00 IDT 2014 | Mon Oct 20 17:00:00 IDT 2014
823 | Setup Equipment for Invert & Walkway Construction (Ch140+385-811A Shaft to Ch139+435) | Mon Nov 03 08:00:00 IST 2014 | Thu Nov 13 17:00:00 IST 2014
824 | 820 side - Tunnel Invert & Walkway (Ch137+941-NAC Shaft to Ch139+435, 1494m) (7 working days) | Tue Oct 21 08:00:00 IDT 2014 | Sat Jan 03 17:00:00 IST 2015
825 | 820 side - Deg. 1 Works (Ch137+941-Shaft to Ch139+435) (4B(ii) Target: 21-Dec-14) (7 working days) | Mon Nov 03 08:00:00 IST 2014 | Sat Dec 27 17:00:00 IST 2014
826 | 811A side -Tunnel Invert & Walkway (Ch139+435 to Ch140+385-811A Shaft, 950m) | Mon Nov 10 08:00:00 IST 2014 | Mon Jan 19 17:00:00 IST 2015
827 | 811A side - Deg. 1 Works ( Ch140+385-811A Shaft to Ch139+435) (4B(iii) Target: 25-Jan-15) | Mon Dec 01 08:00:00 IST 2014 | Mon Jan 26 17:00:00 IST 2015
828 | Tunnel Alignment Design/Submission/Approval | Mon Jan 31 08:00:00 IST 2011 | Thu Jul 07 17:00:00 IDT 2011
829 | Design | Mon Jan 31 08:00:00 IST 2011 | Thu Jul 07 17:00:00 IDT 2011
830 | AIP Submission Preparation - Tunnel Alignment | Mon Jan 31 08:00:00 IST 2011 | Mon Feb 21 17:00:00 IST 2011
831 | AIP Submission to MTR (RDO/GEO consultation) | Sat Mar 12 17:00:00 IST 2011 | Sat Mar 12 17:00:00 IST 2011
832 | AIP Comment by MTR (RDO/GEO consultation) | Sun Mar 13 08:00:00 IST 2011 | Sun Mar 27 17:00:00 IST 2011
833 | AIP ReSubmission Preparation - Tunnel Alignment | Wed Apr 06 08:00:00 IDT 2011 | Mon Apr 18 17:00:00 IDT 2011
834 | AIP ReSubmission to MTR (RDO/GEO consultation) | Sat May 07 17:00:00 IDT 2011 | Sat May 07 17:00:00 IDT 2011
835 | AIP Approval by MTR (RDO/GEO consultation) | Sun May 08 08:00:00 IDT 2011 | Thu Jul 07 17:00:00 IDT 2011
836 | DD Submission MTR/RDO for Record | Tue May 31 17:00:00 IDT 2011 | Tue May 31 17:00:00 IDT 2011
837 | Cross Passages | Thu Oct 21 08:00:00 IST 2010 | Tue Jan 13 17:00:00 IST 2015
838 | CP81 (XRL821) | Mon Mar 04 08:00:00 IST 2013 | Tue Apr 02 17:00:00 IDT 2013
839 | CP82 (XRL821) | Tue Jul 23 08:00:00 IDT 2013 | Tue Mar 18 17:00:00 IST 2014
840 | CP83 (XRL821) | Sat May 11 08:00:00 IDT 2013 | Wed Jan 22 17:00:00 IST 2014
841 | CP84 (XRL821) | Sat Apr 06 08:00:00 IDT 2013 | Wed Jan 08 17:00:00 IST 2014
842 | CP85 | Tue Jan 15 08:00:00 IST 2013 | Fri Sep 13 17:00:00 IDT 2013
843 | CP86 Jet / Fissure Grouting from Surface | Mon Jan 16 08:00:00 IST 2012 | Sat Oct 20 17:00:00 IST 2012
844 | CP86 | Sat Dec 15 08:00:00 IST 2012 | Mon Aug 12 17:00:00 IDT 2013
845 | CP87 | Fri Aug 31 08:00:00 IDT 2012 | Thu Sep 26 17:00:00 IDT 2013
846 | CP88 Jet Grouting from Surface | Wed Aug 31 08:00:00 IDT 2011 | Mon Dec 12 17:00:00 IST 2011
847 | CP88 | Fri Aug 31 08:00:00 IDT 2012 | Wed Sep 11 17:00:00 IDT 2013
848 | CP89 Grouting from Surface | Wed Aug 31 08:00:00 IDT 2011 | Thu Mar 29 17:00:00 IST 2012
849 | CP89 | Fri Sep 07 08:00:00 IDT 2012 | Sat Oct 26 17:00:00 IDT 2013
850 | CP90 | Fri Aug 31 08:00:00 IDT 2012 | Sat Dec 28 17:00:00 IST 2013
851 | CP91 Grouting from Surface | Mon Sep 12 08:00:00 IDT 2011 | Wed Mar 21 17:00:00 IST 2012
852 | CP91 | Wed Oct 31 08:00:00 IST 2012 | Thu Oct 17 17:00:00 IDT 2013
853 | CP92 Grouting from Surface | Wed Aug 31 08:00:00 IDT 2011 | Wed Mar 28 17:00:00 IST 2012
854 | CP92 | Wed Oct 31 08:00:00 IST 2012 | Mon Nov 04 17:00:00 IST 2013
855 | CP93 Grouting from Surface | Mon Jan 16 08:00:00 IST 2012 | Thu Oct 04 17:00:00 IST 2012
856 | CP93 | Tue Nov 27 08:00:00 IST 2012 | Mon Nov 18 17:00:00 IST 2013
857 | CP94 Fissure Grouting from Tunnel | Mon Dec 31 08:00:00 IST 2012 | Tue May 14 17:00:00 IDT 2013
858 | CP94 | Sat May 25 08:00:00 IDT 2013 | Tue Jan 21 13:38:00 IST 2014
859 | CP95 & pump Sump | Wed Jul 24 08:00:00 IDT 2013 | Fri Mar 21 13:38:00 IST 2014
860 | CP96 | Tue Sep 30 08:00:00 IDT 2014 | Thu Nov 20 17:00:00 IST 2014
861 | CP97 Jet Grouting from Surface | Mon Jan 16 08:00:00 IST 2012 | Wed Oct 31 17:00:00 IST 2012
862 | CP97 | Sun Nov 30 08:00:00 IST 2014 | Tue Dec 09 17:00:00 IST 2014
863 | CP98 | Sat Nov 30 08:00:00 IST 2013 | Sat Nov 30 08:00:00 IST 2013
864 | TTM Scheme Submission & Approval | Mon Jan 31 08:00:00 IST 2011 | Tue Jul 19 17:00:00 IDT 2011
865 | Prepare Temporary Traffic Management | Mon Jan 31 08:00:00 IST 2011 | Tue Mar 01 17:00:00 IST 2011
866 | TTM reviewed by SLG | Wed Mar 02 08:00:00 IST 2011 | Tue Mar 08 17:00:00 IST 2011
867 | Notification to RMO | Sun Jun 19 08:00:00 IDT 2011 | Wed Jul 06 17:00:00 IDT 2011
868 | XP Application & Approval | Sun Jun 19 08:00:00 IDT 2011 | Tue Jul 19 17:00:00 IDT 2011
869 | Implement TTM | Sun Jun 19 17:00:00 IDT 2011 | Sun Jun 19 17:00:00 IDT 2011
870 | CP81 (XRL821) | Sat Feb 23 08:00:00 IST 2013 | Tue Jan 13 17:00:00 IST 2015
871 | CP81 Preparation works for Grouting | Mon Mar 04 08:00:00 IST 2013 | Tue Apr 02 17:00:00 IDT 2013
872 | CP81 Fissure Grouting from Tunnel | Mon Mar 04 08:00:00 IST 2013 | Thu May 16 17:00:00 IDT 2013
873 | Probing/Drainage (from DT) | Mon Mar 11 08:00:00 IST 2013 | Wed Mar 13 17:00:00 IST 2013
874 | Segment Dismantle (DT) | Mon Mar 11 08:00:00 IST 2013 | Sat Mar 16 17:00:00 IST 2013
875 | Tunnel Frame Support (DT) | Mon Mar 11 08:00:00 IST 2013 | Sat Mar 16 17:00:00 IST 2013
876 | Mobilization (UT) | Mon Nov 11 08:00:00 IST 2013 | Wed Nov 13 17:00:00 IST 2013
877 | Probing/Drainage (from UT) | Wed Nov 13 08:00:00 IST 2013 | Tue Nov 19 17:00:00 IST 2013
878 | Segment Dismantle (UT) | Fri Nov 15 08:00:00 IST 2013 | Thu Nov 21 17:00:00 IST 2013
879 | Cross Passage Excavation & Temp.Support (from UT) | Sat Feb 23 08:00:00 IST 2013 | Fri Mar 01 17:00:00 IST 2013
880 | Waterproofing | Tue Nov 19 08:00:00 IST 2013 | Thu Nov 28 17:00:00 IST 2013
881 | Permanent Beam | Sat Jan 04 08:00:00 IST 2014 | Tue Jan 14 17:00:00 IST 2014
882 | Permanent Lining | Wed Jan 07 08:00:00 IST 2015 | Tue Jan 13 17:00:00 IST 2015
883 | Permanent Slab | Mon Nov 25 08:00:00 IST 2013 | Sat Nov 30 17:00:00 IST 2013
884 | CP82 (XRL821) | Sat Dec 15 08:00:00 IST 2012 | Tue Mar 18 17:00:00 IST 2014
885 | CP82 (XRL821) | Tue Jul 23 08:00:00 IDT 2013 | Tue Mar 18 17:00:00 IST 2014
886 | CP82 Preparation works for Grouting | Sat Dec 15 08:00:00 IST 2012 | Wed Jan 16 17:00:00 IST 2013
887 | CP82 Fissure Grouting from Tunnel | Sat Dec 15 08:00:00 IST 2012 | Tue Mar 05 17:00:00 IST 2013
888 | Probing/Drainage (DT) | Sat Dec 15 08:00:00 IST 2012 | Sat Dec 22 17:00:00 IST 2012
889 | Segment Dismantle (DT) | Sat Dec 15 08:00:00 IST 2012 | Sat Dec 22 17:00:00 IST 2012
890 | Cross Passage Excavation & Temp.Support (from DT) | Tue Mar 12 08:00:00 IST 2013 | Mon Mar 25 17:00:00 IST 2013
891 | Waterproofing (DT) | Mon Mar 25 08:00:00 IST 2013 | Sat Apr 06 17:00:00 IDT 2013
892 | Permanent Beam (DT) | Mon Apr 08 08:00:00 IDT 2013 | Thu Apr 18 17:00:00 IDT 2013
893 | Probing/Drainage (UT) | Thu Nov 21 08:00:00 IST 2013 | Wed Nov 27 17:00:00 IST 2013
894 | Segment Dismantle (UT) | Thu Nov 21 08:00:00 IST 2013 | Wed Nov 27 17:00:00 IST 2013
895 | Cross Passage Excavation & Temp.Support (from UT) | Tue Mar 12 08:00:00 IST 2013 | Wed Mar 20 17:00:00 IST 2013
896 | Waterproofing (UT) | Thu Nov 21 08:00:00 IST 2013 | Sat Nov 30 17:00:00 IST 2013
897 | Permanent Beam (UT) | Thu Nov 21 08:00:00 IST 2013 | Sat Nov 30 17:00:00 IST 2013
898 | Permanent Lining | Thu Nov 21 08:00:00 IST 2013 | Wed Nov 27 17:00:00 IST 2013
899 | Permanent Slab | Thu Nov 21 08:00:00 IST 2013 | Wed Nov 27 17:00:00 IST 2013
900 | CP83 (XRL821) | Wed Oct 03 08:00:00 IST 2012 | Wed Jan 22 17:00:00 IST 2014
901 | CP83 (XRL821) | Sat May 11 08:00:00 IDT 2013 | Wed Jan 22 17:00:00 IST 2014
902 | CP83 Preparation works for Grouting | Wed Oct 03 08:00:00 IST 2012 | Sat Dec 15 17:00:00 IST 2012
903 | CP83 Re-setup for Grouting | Mon Oct 08 08:00:00 IST 2012 | Wed Oct 10 17:00:00 IST 2012
904 | CP83 Fissure Grouting from Tunnel Part I | Thu Oct 11 08:00:00 IST 2012 | Wed Jan 23 17:00:00 IST 2013
905 | CP83 Fissure Grouting from Tunnel Part II | Thu Oct 11 08:00:00 IST 2012 | Sat Oct 27 17:00:00 IST 2012
906 | Probing/Drainage (DT) | Thu Oct 18 08:00:00 IST 2012 | Thu Oct 25 17:00:00 IST 2012
907 | Segment Dismantle (DT) | Thu Oct 18 08:00:00 IST 2012 | Thu Oct 25 17:00:00 IST 2012
908 | Cross Passage Excavation & Temp.Support (from DT) | Fri Oct 19 08:00:00 IST 2012 | Thu Jan 31 17:00:00 IST 2013
909 | Waterproofing (DT) | Mon Mar 18 08:00:00 IST 2013 | Sat Mar 23 17:00:00 IST 2013
910 | Permanent Beam (DT) | Mon Mar 25 08:00:00 IST 2013 | Sat Apr 06 17:00:00 IDT 2013
911 | Probing/Drainage (UT) | Wed Oct 02 08:00:00 IDT 2013 | Fri Nov 22 17:00:00 IST 2013
912 | Segment Dismantle (UT) | Thu Nov 21 08:00:00 IST 2013 | Wed Nov 27 17:00:00 IST 2013
913 | Cross Passage Excavation & Temp.Support (from UT) | Sat Feb 23 08:00:00 IST 2013 | Mon Mar 04 17:00:00 IST 2013
914 | Waterproofing (UT) | Thu Nov 21 08:00:00 IST 2013 | Sat Nov 30 17:00:00 IST 2013
915 | Permanent Beam (UT) | Thu Nov 21 08:00:00 IST 2013 | Sat Nov 30 17:00:00 IST 2013
916 | Permanent Lining | Thu Nov 21 08:00:00 IST 2013 | Wed Nov 27 17:00:00 IST 2013
917 | Permanent Slab | Thu Nov 21 08:00:00 IST 2013 | Wed Nov 27 17:00:00 IST 2013
918 | CP84 (XRL821) | Mon Sep 03 08:00:00 IDT 2012 | Mon Sep 22 17:00:00 IDT 2014
919 | CP84 (XRL821) | Sat Apr 06 08:00:00 IDT 2013 | Wed Jan 08 17:00:00 IST 2014
920 | CP84 Preparation works for Grouting | Mon Sep 03 08:00:00 IDT 2012 | Thu Oct 04 17:00:00 IST 2012
921 | CP84 Fissure Grouting from Tunnel | Tue Sep 11 08:00:00 IDT 2012 | Sat Jan 12 17:00:00 IST 2013
922 | Probing/Drainage (DT) | Tue Sep 11 08:00:00 IDT 2012 | Mon Sep 17 17:00:00 IDT 2012
923 | Segment Dismantle (DT) | Wed Sep 19 08:00:00 IDT 2012 | Wed Sep 26 17:00:00 IST 2012
924 | Cross Passage Excavation & Temp.Support (from DT) | Wed Sep 26 08:00:00 IST 2012 | Sat Dec 29 17:00:00 IST 2012
925 | Waterproofing (DT) | Mon Mar 18 08:00:00 IST 2013 | Wed Mar 27 17:00:00 IST 2013
926 | Permanent Beam (DT) | Mon Mar 25 08:00:00 IST 2013 | Sat Apr 06 17:00:00 IDT 2013
927 | Probing/Drainage (UT) | Mon Aug 26 08:00:00 IDT 2013 | Tue Sep 03 17:00:00 IDT 2013
928 | Segment Dismantle (UT) | Mon Sep 02 08:00:00 IDT 2013 | Sat Sep 07 17:00:00 IDT 2013
929 | Cross Passage Excavation & Temp.Support (from U/T) | Wed Sep 04 08:00:00 IDT 2013 | Fri Sep 13 17:00:00 IDT 2013
930 | Waterproofing (UT) | Thu Sep 11 08:00:00 IDT 2014 | Mon Sep 22 17:00:00 IDT 2014
931 | Permanent Beam (UT) | Sat Sep 14 08:00:00 IDT 2013 | Thu Sep 26 17:00:00 IDT 2013
932 | Permanent Lining | Fri Sep 13 08:00:00 IDT 2013 | Sat Sep 21 17:00:00 IDT 2013
933 | Permanent Slab | Mon Sep 16 08:00:00 IDT 2013 | Tue Sep 24 17:00:00 IDT 2013
934 | CP85 | Tue Feb 01 08:00:00 IST 2011 | Thu Sep 26 17:00:00 IDT 2013
935 | GI works for CP85 | Tue Feb 01 08:00:00 IST 2011 | Tue Feb 15 17:00:00 IST 2011
936 | CP85 Preparation for Grouting works | Fri Jul 27 08:00:00 IDT 2012 | Thu Aug 23 17:00:00 IDT 2012
937 | CP85 Fissure Grouting from Tunnel | Fri Aug 24 08:00:00 IDT 2012 | Mon Jan 14 17:00:00 IST 2013
938 | Probing/Drainage (DT) | Tue Jan 15 08:00:00 IST 2013 | Mon Jan 21 17:00:00 IST 2013
939 | Segment Dismantle (DT) | Tue Jan 22 08:00:00 IST 2013 | Mon Jan 28 17:00:00 IST 2013
940 | Cross Passage Excavation & Temp.Support (from DT) | Fri Aug 31 08:00:00 IDT 2012 | Wed Sep 26 17:00:00 IST 2012
941 | Waterproofing (DT) | Thu Sep 27 08:00:00 IST 2012 | Tue Oct 09 17:00:00 IST 2012
942 | Permanent Beam (DT) | Wed Dec 19 08:00:00 IST 2012 | Wed Jan 02 17:00:00 IST 2013
943 | Probing/Drainage | Mon Jul 15 08:00:00 IDT 2013 | Mon Jul 22 17:00:00 IDT 2013
944 | Segment Dismantle | Tue Jul 23 08:00:00 IDT 2013 | Mon Jul 29 17:00:00 IDT 2013
945 | Cross Passage Excavation & Temp.Support (from UT) | Fri Jul 26 08:00:00 IDT 2013 | Sat Aug 03 17:00:00 IDT 2013
946 | Waterproofing (UT) | Sat Aug 24 08:00:00 IDT 2013 | Thu Sep 05 17:00:00 IDT 2013
947 | Permanent Beam (UT) | Fri Sep 06 08:00:00 IDT 2013 | Tue Sep 17 17:00:00 IDT 2013
948 | Permanent Lining | Wed Sep 18 08:00:00 IDT 2013 | Thu Sep 26 17:00:00 IDT 2013
949 | Permanent Slab | Mon Sep 09 08:00:00 IDT 2013 | Mon Sep 16 17:00:00 IDT 2013
950 | CP85 | Tue Jan 15 08:00:00 IST 2013 | Fri Jun 21 17:00:00 IDT 2013
951 | CP86 | Thu Oct 21 08:00:00 IST 2010 | Thu Oct 03 17:00:00 IDT 2013
952 | GI works for CP86 | Thu Oct 21 08:00:00 IST 2010 | Fri Oct 29 17:00:00 IST 2010
953 | Access Works Area 10.1 for Cross Passages CP86 | Tue Jun 21 08:00:00 IDT 2011 | Tue Jun 21 08:00:00 IDT 2011
954 | TTMS & Site Set up | Wed Aug 31 08:00:00 IDT 2011 | Fri Sep 30 17:00:00 IDT 2011
955 | Install Sleeve Pipes | Mon Jan 16 08:00:00 IST 2012 | Fri Feb 24 17:00:00 IST 2012
956 | CP86 Jet Grouting from Surface for Down Track Tunnel | Mon Jan 16 08:00:00 IST 2012 | Tue May 08 17:00:00 IDT 2012
957 | CP86 TAM Grouting from Surface for Down Track Tunnel | Thu Mar 01 08:00:00 IST 2012 | Mon Apr 30 17:00:00 IDT 2012
958 | Discussion with DSD for Sewage Pumping Station | Thu May 03 08:00:00 IDT 2012 | Tue Jul 31 17:00:00 IDT 2012
959 | CP86 Jet Grouting from Surface for Up Track Tunnel | Wed Aug 01 08:00:00 IDT 2012 | Wed Oct 03 17:00:00 IST 2012
960 | CP86 TAM Grouting from Surface for Up Track Tunnel | Thu Oct 04 08:00:00 IST 2012 | Fri Nov 30 17:00:00 IST 2012
961 | Reinstatement | Mon Sep 02 08:00:00 IDT 2013 | Thu Oct 03 17:00:00 IDT 2013
962 | Probing/Drainage (DT) | Sat Dec 15 08:00:00 IST 2012 | Sat Dec 22 17:00:00 IST 2012
963 | Segment Dismantle (DT) | Mon Dec 24 08:00:00 IST 2012 | Wed Jan 02 17:00:00 IST 2013
964 | Cross Passage Excavation & Temp.Support (from DT) | Sat Dec 15 08:00:00 IST 2012 | Sat Dec 29 17:00:00 IST 2012
965 | Waterproofing (DT) | Mon Dec 31 08:00:00 IST 2012 | Thu Jan 10 17:00:00 IST 2013
966 | Permanent Beam (DT) | Fri Jan 11 08:00:00 IST 2013 | Mon Jan 21 17:00:00 IST 2013
967 | Probing/Drainage (UT) | Sat Jun 08 08:00:00 IDT 2013 | Mon Jun 17 17:00:00 IDT 2013
968 | Segment Dismantle (UT) | Tue Jun 18 08:00:00 IDT 2013 | Tue Jun 25 17:00:00 IDT 2013
969 | Cross Passage Excavation & Temp.Support (from UT) | Wed Jun 26 08:00:00 IDT 2013 | Fri Jul 05 17:00:00 IDT 2013
970 | Waterproofing (UT) | Mon Aug 19 08:00:00 IDT 2013 | Thu Aug 29 17:00:00 IDT 2013
971 | Permanent Beam (UT) | Mon Sep 02 08:00:00 IDT 2013 | Thu Sep 12 17:00:00 IDT 2013
972 | Permanent Lining | Sat Sep 14 08:00:00 IDT 2013 | Mon Sep 23 17:00:00 IDT 2013
973 | Permanent Slab | Fri Sep 13 08:00:00 IDT 2013 | Sat Sep 21 17:00:00 IDT 2013
974 | CP86 Jet Grouting from Surface | Mon Jan 16 08:00:00 IST 2012 | Mon Jan 16 08:00:00 IST 2012
975 | CP86 | Mon Jan 07 08:00:00 IST 2013 | Mon Aug 12 17:00:00 IDT 2013
976 | CP87 | Sun Jun 19 17:00:00 IDT 2011 | Thu Sep 26 17:00:00 IDT 2013
977 | GI works for CP87 | Tue Jun 21 08:00:00 IDT 2011 | Mon Jun 27 17:00:00 IDT 2011
978 | Access Works Area 11.12 for Cross Passages CP87 | Sun Jun 19 17:00:00 IDT 2011 | Sun Jun 19 17:00:00 IDT 2011
979 | TTA Implemetation | Wed Aug 31 08:00:00 IDT 2011 | Thu Nov 24 17:00:00 IST 2011
980 | Install Steeve Pipe (for DT area) | Mon Jan 16 08:00:00 IST 2012 | Tue Feb 21 17:00:00 IST 2012
981 | CP87 Jet Grouting from Surface for Down Track Tunnel | Mon Jan 16 08:00:00 IST 2012 | Tue May 08 17:00:00 IDT 2012
982 | Tam Grouting from Surface for Down Track Tunnel | Thu Feb 16 08:00:00 IST 2012 | Wed Apr 18 17:00:00 IDT 2012
983 | Reinstatement & TTMS | Thu Apr 19 08:00:00 IDT 2012 | Thu May 17 17:00:00 IDT 2012
984 | Install Steeve Pipe (for UT area) | Sat May 19 08:00:00 IDT 2012 | Sat Jun 30 17:00:00 IDT 2012
985 | CP87 Jet Grouting from Surface for Up Track Tunnel | Tue Jul 03 08:00:00 IDT 2012 | Fri Aug 31 17:00:00 IDT 2012
986 | Tam Grouting from Surface for Up Track Tunnel | Sat Sep 01 08:00:00 IDT 2012 | Wed Oct 03 17:00:00 IST 2012
987 | Probing/Drainage (DT) | Fri Aug 31 08:00:00 IDT 2012 | Thu Sep 06 17:00:00 IDT 2012
988 | Segment Dismantle (DT) | Fri Sep 07 08:00:00 IDT 2012 | Fri Sep 14 17:00:00 IDT 2012
989 | Cross Passage Excavation & Temp.Support (from DT) | Sat Sep 15 08:00:00 IDT 2012 | Wed Sep 19 17:00:00 IDT 2012
990 | Waterproofing (DT) | Fri Sep 21 08:00:00 IDT 2012 | Wed Oct 03 17:00:00 IST 2012
991 | Permanent Beam (DT) | Thu Oct 04 08:00:00 IST 2012 | Sat Oct 13 17:00:00 IST 2012
992 | Probing/Drainage (UT) | Sat May 25 08:00:00 IDT 2013 | Fri May 31 17:00:00 IDT 2013
993 | Segment Dismantle (UT) | Sat Jun 01 08:00:00 IDT 2013 | Fri Jun 07 17:00:00 IDT 2013
994 | Cross Passage Excavation & Temp.Support (from UT) | Sat Jun 08 08:00:00 IDT 2013 | Wed Jun 19 17:00:00 IDT 2013
995 | Waterproofing (UT) | Fri Jun 21 08:00:00 IDT 2013 | Tue Jul 02 17:00:00 IDT 2013
996 | Permanent Beam (UT) | Wed Jul 03 08:00:00 IDT 2013 | Sat Jul 13 17:00:00 IDT 2013
997 | Permanent Lining | Mon Jul 15 08:00:00 IDT 2013 | Mon Jul 22 17:00:00 IDT 2013
998 | Permanent Slab | Tue Jul 23 08:00:00 IDT 2013 | Mon Jul 29 17:00:00 IDT 2013
999 | CP87 | Fri Aug 31 08:00:00 IDT 2012 | Thu Sep 26 17:00:00 IDT 2013
1000 | CP88 | Tue Feb 01 08:00:00 IST 2011 | Wed Sep 11 17:00:00 IDT 2013
1001 | GI works for CP88 | Tue Feb 01 08:00:00 IST 2011 | Mon Feb 07 17:00:00 IST 2011
1002 | Access Works Area 11.21 for Cross Passages CP88 | Wed Aug 31 08:00:00 IDT 2011 | Wed Aug 31 08:00:00 IDT 2011
1003 | Site Set up & Preparation | Tue Jun 21 08:00:00 IDT 2011 | Tue Aug 02 17:00:00 IDT 2011
1004 | CP88 Jet Grouting from Surface | Tue Aug 09 08:00:00 IDT 2011 | Sat Aug 20 17:00:00 IDT 2011
1005 | Suspension of Grouting Works | Sun Jun 19 08:00:00 IDT 2011 | Sun Jun 19 08:00:00 IDT 2011
1006 | Suspension Period for CP88 Jet Grouting Works | Sun Jun 19 08:00:00 IDT 2011 | Wed Jun 22 17:00:00 IDT 2011
1007 | Suspension Lifting | Tue Jun 21 08:00:00 IDT 2011 | Tue Jun 21 08:00:00 IDT 2011
1008 | Re-mobilization | Thu Aug 18 08:00:00 IDT 2011 | Sat Aug 20 17:00:00 IDT 2011
1009 | CP88 Jet Grouting from Surface (Remaining) | Thu Aug 18 08:00:00 IDT 2011 | Mon Dec 19 17:00:00 IST 2011
1010 | Probing/Drainage (DT) | Fri Aug 31 08:00:00 IDT 2012 | Thu Sep 06 17:00:00 IDT 2012
1011 | Segment Dismantle (DT) | Fri Sep 07 08:00:00 IDT 2012 | Fri Sep 14 17:00:00 IDT 2012
1012 | Cross Passage Excavation & Temp.Support (from DT) | Sat Sep 15 08:00:00 IDT 2012 | Mon Sep 17 17:00:00 IDT 2012
1013 | Waterproofing (DT) | Tue Sep 18 08:00:00 IDT 2012 | Fri Sep 28 17:00:00 IST 2012
1014 | Permanent Beam (DT) | Sat Sep 29 08:00:00 IST 2012 | Thu Oct 11 17:00:00 IST 2012
1015 | Probing/Drainage (UT) | Thu May 23 08:00:00 IDT 2013 | Wed May 29 17:00:00 IDT 2013
1016 | Segment Dismantle (UT) | Thu May 30 08:00:00 IDT 2013 | Wed Jun 05 17:00:00 IDT 2013
1017 | Cross Passage Excavation & Temp.Support (from UT) | Thu Jun 06 08:00:00 IDT 2013 | Mon Jun 17 17:00:00 IDT 2013
1018 | Waterproofing (UT) | Tue Jun 18 08:00:00 IDT 2013 | Fri Jun 28 17:00:00 IDT 2013
1019 | Permanent Beam (UT) | Sat Jun 29 08:00:00 IDT 2013 | Thu Jul 11 17:00:00 IDT 2013
1020 | Permanent Lining | Fri Jul 12 08:00:00 IDT 2013 | Thu Jul 18 17:00:00 IDT 2013
1021 | Permanent Slab | Sat Jul 20 08:00:00 IDT 2013 | Fri Jul 26 17:00:00 IDT 2013
1022 | CP88 | Fri Aug 31 08:00:00 IDT 2012 | Wed Sep 11 17:00:00 IDT 2013
1023 | CP89 | Tue Feb 01 08:00:00 IST 2011 | Tue Feb 18 17:00:00 IST 2014
1024 | GI works for CP89 | Tue Feb 01 08:00:00 IST 2011 | Sat Feb 12 17:00:00 IST 2011
1025 | Access Works Area 11.27 for Cross Passages CP89 | Sat May 28 17:00:00 IDT 2011 | Sat May 28 17:00:00 IDT 2011
1026 | Setup & Install Sleeve pipes | Wed Aug 31 08:00:00 IDT 2011 | Fri Sep 30 17:00:00 IDT 2011
1027 | Jet Grouting from Surface (DT) | Wed Aug 31 08:00:00 IDT 2011 | Tue Mar 13 17:00:00 IST 2012
1028 | Jet Grouting from Surface (UT) | Thu Mar 15 08:00:00 IST 2012 | Mon Apr 30 17:00:00 IDT 2012
1029 | Probing/Drainage (DT) | Fri Aug 31 08:00:00 IDT 2012 | Thu Sep 06 17:00:00 IDT 2012
1030 | Tunnel Frame Support | Fri Sep 07 08:00:00 IDT 2012 | Fri Sep 14 17:00:00 IDT 2012
1031 | Segment Dismantle (DT) | Sat Sep 15 08:00:00 IDT 2012 | Sat Sep 22 17:00:00 IDT 2012
1032 | Cross Passage Excavation & Temp.Support (from DT) | Mon Sep 24 08:00:00 IST 2012 | Tue Sep 25 17:00:00 IST 2012
1033 | Waterproofing (DT) | Wed Sep 26 08:00:00 IST 2012 | Mon Oct 08 17:00:00 IST 2012
1034 | Permanent Beam (DT) | Tue Oct 09 08:00:00 IST 2012 | Thu Oct 18 17:00:00 IST 2012
1035 | Probing/Drainage (from DT) | Tue Jan 07 08:00:00 IST 2014 | Mon Jan 13 17:00:00 IST 2014
1036 | Cross Passage Excavation & Temp.Support (from DT) | Sat Jan 11 08:00:00 IST 2014 | Mon Jan 20 17:00:00 IST 2014
1037 | Segment Dismantle (UT) | Wed Jan 08 08:00:00 IST 2014 | Tue Jan 14 17:00:00 IST 2014
1038 | Waterproofing (UT) | Tue Feb 04 08:00:00 IST 2014 | Thu Feb 13 17:00:00 IST 2014
1039 | Permanent Beam (UT) | Sat Feb 08 08:00:00 IST 2014 | Tue Feb 18 17:00:00 IST 2014
1040 | Permanent Lining | Tue Feb 11 08:00:00 IST 2014 | Mon Feb 17 17:00:00 IST 2014
1041 | Permanent Slab | Fri Feb 07 08:00:00 IST 2014 | Thu Feb 13 17:00:00 IST 2014
1042 | CP89 | Fri Sep 07 08:00:00 IDT 2012 | Sat Oct 26 17:00:00 IDT 2013
1043 | CP90 | Tue Feb 01 08:00:00 IST 2011 | Thu May 08 17:00:00 IDT 2014
1044 | GI works for CP90 | Tue Feb 01 08:00:00 IST 2011 | Wed Feb 09 17:00:00 IST 2011
1045 | Access Works Area 11.21 for Cross Passages CP90 | Sun Jun 19 17:00:00 IDT 2011 | Sun Jun 19 17:00:00 IDT 2011
1046 | TTA Implementation | Mon Jan 16 08:00:00 IST 2012 | Wed Feb 15 17:00:00 IST 2012
1047 | Installl Sleeve Pipes | Mon Jan 16 08:00:00 IST 2012 | Thu Feb 16 17:00:00 IST 2012
1048 | CP90 Jet Grouting from Surface (DT) | Mon Jan 16 08:00:00 IST 2012 | Fri Jun 15 17:00:00 IDT 2012
1049 | CP90 Jet Grouting from Surface (UT) | Wed May 02 08:00:00 IDT 2012 | Sat Sep 01 17:00:00 IDT 2012
1050 | Probing/Drainage (DT) | Fri Aug 31 08:00:00 IDT 2012 | Thu Sep 06 17:00:00 IDT 2012
1051 | Segment Dismantle (DT) | Fri Sep 07 08:00:00 IDT 2012 | Fri Sep 14 17:00:00 IDT 2012
1052 | Cross Passage Excavation & Temp.Support (from DT) | Sat Sep 15 08:00:00 IDT 2012 | Sat Sep 22 17:00:00 IDT 2012
1053 | Waterproofing (DT) | Mon Sep 24 08:00:00 IST 2012 | Fri Oct 05 17:00:00 IST 2012
1054 | Permanent Beam (DT) | Sat Oct 06 08:00:00 IST 2012 | Tue Oct 16 17:00:00 IST 2012
1055 | Probing/Drainage (UT) | Wed Apr 09 08:00:00 IDT 2014 | Wed Apr 16 17:00:00 IDT 2014
1056 | Cross Passage Excavation & Temp.Support (UT) | Sat Apr 12 08:00:00 IDT 2014 | Thu Apr 24 17:00:00 IDT 2014
1057 | Segment Dismantle (UT) | Fri Apr 11 08:00:00 IDT 2014 | Sat Apr 19 17:00:00 IDT 2014
1058 | Waterproofing (UT) | Tue Apr 22 08:00:00 IDT 2014 | Wed Apr 30 17:00:00 IDT 2014
1059 | Permanent Beam (UT) | Mon Apr 28 08:00:00 IDT 2014 | Thu May 08 17:00:00 IDT 2014
1060 | Permanent Lining | Wed Apr 30 08:00:00 IDT 2014 | Thu May 08 17:00:00 IDT 2014
1061 | Permanent Slab | Thu Apr 24 08:00:00 IDT 2014 | Wed Apr 30 17:00:00 IDT 2014
1062 | CP90 | Fri Aug 31 08:00:00 IDT 2012 | Sat Dec 28 17:00:00 IST 2013
1063 | CP91 | Tue Feb 01 08:00:00 IST 2011 | Thu May 22 17:00:00 IDT 2014
1064 | GI works for CP91 | Tue Feb 01 08:00:00 IST 2011 | Sat Feb 12 17:00:00 IST 2011
1065 | Access Works Area 11.21 for Cross Passages CP91 | Sun Jun 19 17:00:00 IDT 2011 | Sun Jun 19 17:00:00 IDT 2011
1066 | TTMS & Site Set up | Wed Aug 31 08:00:00 IDT 2011 | Mon Oct 17 17:00:00 IST 2011
1067 | Install Sleeve Pipes (DT) | Mon Jan 16 08:00:00 IST 2012 | Wed Feb 01 17:00:00 IST 2012
1068 | Jet Grouting from Surface for Down Track Tunnel | Mon Jan 16 08:00:00 IST 2012 | Tue Jun 05 17:00:00 IDT 2012
1069 | TTMS Rearrangement | Mon Apr 16 08:00:00 IDT 2012 | Mon May 14 17:00:00 IDT 2012
1070 | Install Sleeve Pipes (UT) | Tue May 15 08:00:00 IDT 2012 | Wed Jun 13 17:00:00 IDT 2012
1071 | Jet Grouting from Surface for Up Track Tunnel | Thu Jun 14 08:00:00 IDT 2012 | Fri Sep 14 17:00:00 IDT 2012
1072 | Probing/Drainage (DT) | Wed Oct 31 08:00:00 IST 2012 | Tue Nov 06 17:00:00 IST 2012
1073 | Tunnel Frame Support | Fri Nov 30 08:00:00 IST 2012 | Thu Dec 06 17:00:00 IST 2012
1074 | Segment Dismantle (DT) | Fri Dec 07 08:00:00 IST 2012 | Thu Dec 13 17:00:00 IST 2012
1075 | Cross Passage Excavation & Temp.Support (from DT) | Fri Dec 14 08:00:00 IST 2012 | Thu Dec 27 17:00:00 IST 2012
1076 | Waterproofing (DT) | Sat Dec 15 08:00:00 IST 2012 | Fri Dec 28 17:00:00 IST 2012
1077 | Permanent Beam (DT) | Fri Feb 01 08:00:00 IST 2013 | Sat Feb 16 17:00:00 IST 2013
1078 | Probing/Drainage (from DT) | Fri Apr 25 08:00:00 IDT 2014 | Fri May 02 17:00:00 IDT 2014
1079 | Segment Dismantle (UT) | Fri Apr 25 08:00:00 IDT 2014 | Fri May 02 17:00:00 IDT 2014
1080 | Waterproofing (UT) | Mon May 05 08:00:00 IDT 2014 | Fri May 16 17:00:00 IDT 2014
1081 | Permanent Beam (UT) | Mon May 12 08:00:00 IDT 2014 | Thu May 22 17:00:00 IDT 2014
1082 | Permanent Lining | Wed May 14 08:00:00 IDT 2014 | Wed May 21 17:00:00 IDT 2014
1083 | Permanent Slab | Thu May 08 08:00:00 IDT 2014 | Thu May 15 17:00:00 IDT 2014
1084 | CP91 Grouting from Surface | Mon Jan 16 08:00:00 IST 2012 | Wed Aug 01 17:00:00 IDT 2012
1085 | CP91 | Wed Oct 31 08:00:00 IST 2012 | Thu Oct 17 17:00:00 IDT 2013
1086 | CP92 | Sun Jun 19 17:00:00 IDT 2011 | Sat Jun 07 17:00:00 IDT 2014
1087 | GI works for CP92 | Tue Jun 21 08:00:00 IDT 2011 | Mon Jun 27 17:00:00 IDT 2011
1088 | Access Works Area 11.21 for Cross Passages CP92 | Sun Jun 19 17:00:00 IDT 2011 | Sun Jun 19 17:00:00 IDT 2011
1089 | TTMS & Site Set up | Tue Jun 21 08:00:00 IDT 2011 | Wed Aug 17 17:00:00 IDT 2011
1090 | Install Sleeve Pipes | Mon Jan 16 08:00:00 IST 2012 | Wed Feb 01 17:00:00 IST 2012
1091 | Jet Grouting from Surface for Up Track Tunnel | Mon Jan 16 08:00:00 IST 2012 | Tue Mar 27 17:00:00 IST 2012
1092 | TTMS Rearrangement | Mon Jan 16 08:00:00 IST 2012 | Thu Feb 16 17:00:00 IST 2012
1093 | Insall Sleeve Pipes | Sat Feb 04 08:00:00 IST 2012 | Fri Feb 17 17:00:00 IST 2012
1094 | Jet Grouting from Surface for Down Track Tunnel | Sat Feb 18 08:00:00 IST 2012 | Fri Jun 15 17:00:00 IDT 2012
1095 | Road Reinstatment | Sat Jun 16 08:00:00 IDT 2012 | Wed Jul 18 17:00:00 IDT 2012
1096 | Probing/Drainage (DT) | Wed Oct 31 08:00:00 IST 2012 | Tue Nov 06 17:00:00 IST 2012
1097 | Segment Dismantle (DT) | Wed Nov 07 08:00:00 IST 2012 | Tue Nov 13 17:00:00 IST 2012
1098 | Cross Passage Excavation & Temp.Support (from DT) | Fri Nov 30 08:00:00 IST 2012 | Thu Dec 06 17:00:00 IST 2012
1099 | Waterproofing (DT) | Sat Dec 15 08:00:00 IST 2012 | Fri Dec 28 17:00:00 IST 2012
1100 | Permanent Beam (DT) | Sat Dec 15 08:00:00 IST 2012 | Fri Dec 28 17:00:00 IST 2012
1101 | Probing/Drainage (from DT) | Sat May 10 08:00:00 IDT 2014 | Fri May 16 17:00:00 IDT 2014
1102 | Cross Passage Excavation & Temp.Support (from DT) | Mon May 12 08:00:00 IDT 2014 | Wed May 21 17:00:00 IDT 2014
1103 | Segment Dismantle (UT) | Sat May 10 08:00:00 IDT 2014 | Thu May 15 17:00:00 IDT 2014
1104 | Waterproofing (UT) | Wed May 21 08:00:00 IDT 2014 | Thu May 29 17:00:00 IDT 2014
1105 | Permanent Beam (UT) | Thu May 29 08:00:00 IDT 2014 | Sat Jun 07 17:00:00 IDT 2014
1106 | Permanent Lining | Sat May 31 08:00:00 IDT 2014 | Sat Jun 07 17:00:00 IDT 2014
1107 | Permanent Slab | Mon May 26 08:00:00 IDT 2014 | Sat May 31 17:00:00 IDT 2014
1108 | CP92 | Wed Oct 31 08:00:00 IST 2012 | Mon Nov 04 17:00:00 IST 2013
1109 | CP93 | Tue Feb 01 08:00:00 IST 2011 | Sat Jun 21 17:00:00 IDT 2014
1110 | GI works for CP93 | Tue Feb 01 08:00:00 IST 2011 | Thu Feb 10 17:00:00 IST 2011
1111 | Access Works Area 11.15 for Cross Passages CP93 | Wed Aug 31 08:00:00 IDT 2011 | Wed Aug 31 08:00:00 IDT 2011
1112 | TTMS & Site Set up | Wed Feb 01 08:00:00 IST 2012 | Fri Mar 02 17:00:00 IST 2012
1113 | Install Sleeve Pipes | Mon Jan 16 08:00:00 IST 2012 | Mon Feb 13 17:00:00 IST 2012
1114 | Jet Grouting from Surface | Mon Jan 16 08:00:00 IST 2012 | Thu Jul 12 17:00:00 IDT 2012
1115 | Probing/Drainage (DT) | Tue Nov 27 08:00:00 IST 2012 | Mon Dec 03 17:00:00 IST 2012
1116 | Segment Dismantle (DT) | Tue Dec 04 08:00:00 IST 2012 | Mon Dec 10 17:00:00 IST 2012
1117 | Cross Passage Excavation & Temp.Support (from DT) | Tue Dec 11 08:00:00 IST 2012 | Tue Dec 18 17:00:00 IST 2012
1118 | Waterproofing (DT) | Sat Dec 15 08:00:00 IST 2012 | Fri Dec 28 17:00:00 IST 2012
1119 | Permanent Beam (DT) | Sat Dec 29 08:00:00 IST 2012 | Wed Jan 09 17:00:00 IST 2013
1120 | Probing/Drainage (from UT) | Wed May 21 08:00:00 IDT 2014 | Tue May 27 17:00:00 IDT 2014
1121 | Cross Passage Excavation & Temp.Support (from DT) | Sat May 24 08:00:00 IDT 2014 | Tue Jun 03 17:00:00 IDT 2014
1122 | Segment Dismantle (UT) | Fri May 23 08:00:00 IDT 2014 | Wed May 28 17:00:00 IDT 2014
1123 | Waterproofing (UT) | Sat May 31 08:00:00 IDT 2014 | Mon Jun 09 17:00:00 IDT 2014
1124 | Permanent Beam (UT) | Thu Jun 12 08:00:00 IDT 2014 | Sat Jun 21 17:00:00 IDT 2014
1125 | Permanent Lining | Sat Jun 14 08:00:00 IDT 2014 | Thu Jun 19 17:00:00 IDT 2014
1126 | Permanent Slab | Mon Jun 09 08:00:00 IDT 2014 | Sat Jun 14 17:00:00 IDT 2014
1127 | CP93 | Tue Nov 27 08:00:00 IST 2012 | Mon Nov 18 17:00:00 IST 2013
1128 | CP94 | Tue Feb 01 08:00:00 IST 2011 | Sat Aug 09 17:00:00 IDT 2014
1129 | GI works for CP94 | Tue Feb 01 08:00:00 IST 2011 | Thu Feb 17 17:00:00 IST 2011
1130 | Access for Cross Passages CP94 | Mon Sep 03 17:00:00 IDT 2012 | Mon Sep 03 17:00:00 IDT 2012
1131 | Preparation for Grouting | Wed Oct 03 08:00:00 IST 2012 | Wed Oct 31 17:00:00 IST 2012
1132 | CP94 Fissure Grouting from Tunnel | Thu Nov 01 08:00:00 IST 2012 | Mon Dec 31 17:00:00 IST 2012
1133 | Probing/Drainage (DT) | Mon Dec 02 08:00:00 IST 2013 | Mon Dec 30 17:00:00 IST 2013
1134 | Segment Dismantle (DT) | Tue Dec 04 08:00:00 IST 2012 | Mon Dec 10 17:00:00 IST 2012
1135 | Cross Passage Excavation/ Temp.Support (from DT) | Tue Dec 11 08:00:00 IST 2012 | Tue Dec 18 17:00:00 IST 2012
1136 | Waterproofing (DT) | Tue Jul 02 08:00:00 IDT 2013 | Fri Jul 12 17:00:00 IDT 2013
1137 | Permanent Beam (DT) | Sat Jul 13 08:00:00 IDT 2013 | Wed Jul 24 17:00:00 IDT 2013
1138 | Probing/Drainage (from DT) | Mon Jul 14 08:00:00 IDT 2014 | Mon Jul 21 17:00:00 IDT 2014
1139 | Cross Passage Excavation /Temp.Support (from DT) | Sat Jul 19 08:00:00 IDT 2014 | Mon Jul 28 17:00:00 IDT 2014
1140 | Segment Dismantle (UT) | Mon Jul 14 08:00:00 IDT 2014 | Sat Jul 19 17:00:00 IDT 2014
1141 | Waterproofing (UT) | Fri Jul 25 08:00:00 IDT 2014 | Sat Aug 02 17:00:00 IDT 2014
1142 | Permanent Beam (UT) | Thu Jul 31 08:00:00 IDT 2014 | Sat Aug 09 17:00:00 IDT 2014
1143 | Permanent Lining | Sat Aug 02 08:00:00 IDT 2014 | Thu Aug 07 17:00:00 IDT 2014
1144 | Permanent Slab | Wed Jul 30 08:00:00 IDT 2014 | Mon Aug 04 17:00:00 IDT 2014
1145 | CP94 | Mon Dec 31 08:00:00 IST 2012 | Mon Dec 31 08:00:00 IST 2012
1146 | CP95 & Pump Sump | Tue Feb 01 08:00:00 IST 2011 | Mon Sep 08 17:00:00 IDT 2014
1147 | GI works for CP95 & Sump | Tue Feb 01 08:00:00 IST 2011 | Thu Feb 17 17:00:00 IST 2011
1148 | Preparation for Grouting | Sat Nov 24 08:00:00 IST 2012 | Mon Dec 24 17:00:00 IST 2012
1149 | CP95 Fissure Grouting from Tunnel | Sat Dec 08 08:00:00 IST 2012 | Mon May 27 17:00:00 IDT 2013
1150 | Probing/Drainage (DT) | Mon Dec 24 08:00:00 IST 2012 | Wed Jan 02 17:00:00 IST 2013
1151 | Segment Dismantle (DT) | Mon Dec 31 08:00:00 IST 2012 | Thu Feb 14 17:00:00 IST 2013
1152 | Cross Passage & Sump pit Excavation/ Temp.Support (from DT) | Thu Feb 14 08:00:00 IST 2013 | Thu Feb 21 17:00:00 IST 2013
1153 | Waterproofing (DT) | Mon Sep 02 08:00:00 IDT 2013 | Thu Sep 12 17:00:00 IDT 2013
1154 | Permanent Beam (DT) | Fri Sep 13 08:00:00 IDT 2013 | Wed Sep 25 17:00:00 IDT 2013
1155 | Cross Passage Excavation/Temp.Support U/T (from DT) | Mon Aug 18 08:00:00 IDT 2014 | Wed Aug 27 17:00:00 IDT 2014
1156 | Segment Dismantle (UT) | Tue Aug 12 08:00:00 IDT 2014 | Mon Aug 18 17:00:00 IDT 2014
1157 | Waterproofing (UT) | Tue Aug 26 08:00:00 IDT 2014 | Wed Sep 03 17:00:00 IDT 2014
1158 | Sump pit Concreting | Thu Sep 05 08:00:00 IDT 2013 | Fri Oct 04 17:00:00 IDT 2013
1159 | Permanet Beam, Lining& Slab (UT) | Thu Aug 28 08:00:00 IDT 2014 | Mon Sep 08 17:00:00 IDT 2014
1160 | CP96 | Tue Feb 01 08:00:00 IST 2011 | Tue Sep 30 17:00:00 IDT 2014
1161 | Segment Dismantle (DT) | Tue May 14 08:00:00 IDT 2013 | Wed May 22 17:00:00 IDT 2013
1162 | Cross Passage Excavation & Temp.Support (DT) | Tue May 21 08:00:00 IDT 2013 | Mon May 27 17:00:00 IDT 2013
1163 | Waterproofing (DT) | Tue Sep 24 08:00:00 IDT 2013 | Wed Oct 02 17:00:00 IDT 2013
1164 | Permanent Beam (DT) | Fri Sep 27 08:00:00 IDT 2013 | Mon Oct 07 17:00:00 IDT 2013
1165 | Permanent Lining (DT) | Fri Sep 27 08:00:00 IDT 2013 | Thu Oct 03 17:00:00 IDT 2013
1166 | Permanent Slab (DT) | Thu Sep 26 08:00:00 IDT 2013 | Wed Oct 02 17:00:00 IDT 2013
1167 | GI works for CP96 | Tue Feb 01 08:00:00 IST 2011 | Tue Feb 15 17:00:00 IST 2011
1168 | Preparation works for Grouting | Mon Feb 18 08:00:00 IST 2013 | Tue Mar 19 17:00:00 IST 2013
1169 | CP96 Fissure Grouting from Tunnel | Fri Mar 01 08:00:00 IST 2013 | Fri Jun 07 17:00:00 IDT 2013
1170 | Probing/Drainage (from UT) | Wed Sep 03 08:00:00 IDT 2014 | Thu Sep 11 17:00:00 IDT 2014
1171 | Segment Dismantle (UT) | Thu Sep 04 08:00:00 IDT 2014 | Fri Sep 12 17:00:00 IDT 2014
1172 | Cross Passage Excavation & Temp.Support (from UT) | Thu Sep 11 08:00:00 IDT 2014 | Wed Sep 17 17:00:00 IDT 2014
1173 | Waterproofing | Wed Sep 17 08:00:00 IDT 2014 | Thu Sep 25 17:00:00 IDT 2014
1174 | Permanent Beam | Mon Sep 22 08:00:00 IDT 2014 | Tue Sep 30 17:00:00 IDT 2014
1175 | Permanent Lining | Wed Sep 24 08:00:00 IDT 2014 | Mon Sep 29 17:00:00 IDT 2014
1176 | Permanent Slab | Sat Sep 20 08:00:00 IDT 2014 | Thu Sep 25 17:00:00 IDT 2014
1177 | Probing/Drainage (DT) | Sat May 11 08:00:00 IDT 2013 | Sat May 18 17:00:00 IDT 2013
1178 | CP97 | Tue Feb 01 08:00:00 IST 2011 | Thu Dec 18 17:00:00 IST 2014
1179 | CP97 Jet Grouting from Surface | Mon Jan 16 08:00:00 IST 2012 | Wed Oct 31 17:00:00 IST 2012
1180 | GI works for CP97 | Tue Feb 01 08:00:00 IST 2011 | Thu Feb 10 17:00:00 IST 2011
1181 | Access Works Area 12.1 for Cross Passages CP97 | Sun Jan 15 08:00:00 IST 2012 | Sun Jan 15 08:00:00 IST 2012
1182 | TTMS (Stage 1) | Mon Jan 16 08:00:00 IST 2012 | Wed Feb 15 17:00:00 IST 2012
1183 | Install Sleeve Pipes | Mon Jan 16 08:00:00 IST 2012 | Wed Feb 15 17:00:00 IST 2012
1184 | Jet Grouting from Surface for Down Track Tunnel | Thu Feb 16 08:00:00 IST 2012 | Thu May 31 17:00:00 IDT 2012
1185 | TTMS (Stage 2) Reinstate TTMS for Stage 4 | Fri Jun 01 08:00:00 IDT 2012 | Tue Jul 17 17:00:00 IDT 2012
1186 | Install Sleeve Pipes | Fri Jun 01 08:00:00 IDT 2012 | Thu Jun 14 17:00:00 IDT 2012
1187 | Jet Grouting from Surface for Up Track Tunnel | Sat Sep 21 08:00:00 IDT 2013 | Mon Dec 16 17:00:00 IST 2013
1188 | Probing/Drainage (UT) (after TBM removal) | Mon Nov 17 08:00:00 IST 2014 | Wed Nov 19 17:00:00 IST 2014
1189 | Segment Dismantle (UT) | Wed Nov 19 08:00:00 IST 2014 | Fri Nov 21 17:00:00 IST 2014
1190 | Cross Passage Excavation & Temp.Support (from UT) | Thu Nov 20 08:00:00 IST 2014 | Tue Nov 25 17:00:00 IST 2014
1191 | Waterproofing | Tue Dec 02 08:00:00 IST 2014 | Thu Dec 04 17:00:00 IST 2014
1192 | Permanent Beam | Thu Dec 11 08:00:00 IST 2014 | Sat Dec 13 17:00:00 IST 2014
1193 | Permanent Lining | Tue Dec 16 08:00:00 IST 2014 | Thu Dec 18 17:00:00 IST 2014
1194 | Permanent Slab | Mon Dec 08 08:00:00 IST 2014 | Wed Dec 10 17:00:00 IST 2014
1195 | Additional Jet Grout of CP97 U/T | Tue Jan 21 08:00:00 IST 2014 | Fri Aug 01 17:00:00 IDT 2014
1196 | Mobilization | Tue Jan 21 08:00:00 IST 2014 | Tue Jan 21 17:00:00 IST 2014
1197 | Steel Sleeve pipe installation | Tue Jan 21 08:00:00 IST 2014 | Thu Feb 06 17:00:00 IST 2014
1198 | Mobilization of Pre-drilling rig and mixing plant | Fri Feb 07 08:00:00 IST 2014 | Mon Feb 10 17:00:00 IST 2014
1199 | Pre-drilling (2 Rigs) | Tue Feb 11 08:00:00 IST 2014 | Wed Apr 30 17:00:00 IDT 2014
1200 | Trial pit for re-location of air release hole P2 | Mon May 12 08:00:00 IDT 2014 | Mon May 12 17:00:00 IDT 2014
1201 | Pre-drilling for air release hole P2 | Tue May 13 08:00:00 IDT 2014 | Wed May 14 17:00:00 IDT 2014
1202 | Demobilization of Pre-drilling plant | Thu May 15 08:00:00 IDT 2014 | Fri May 16 17:00:00 IDT 2014
1203 | Mobilization and Set up of Jet grouting plant | Sat May 17 08:00:00 IDT 2014 | Sat May 24 17:00:00 IDT 2014
1204 | Jet grouting (56 columns) | Wed May 21 08:00:00 IDT 2014 | Tue Jul 08 17:00:00 IDT 2014
1205 | Demobilization of Jet grout plant | Tue Jun 24 08:00:00 IDT 2014 | Mon Jun 30 17:00:00 IDT 2014
1206 | Mobilization and drilling rig for Proof Coring | Thu Jul 31 08:00:00 IDT 2014 | Fri Aug 01 17:00:00 IDT 2014
1207 | Proof Coring | Mon Jul 07 08:00:00 IDT 2014 | Mon Jul 14 17:00:00 IDT 2014
1208 | Demobilization of drilling rig | Mon Jul 28 08:00:00 IDT 2014 | Tue Jul 29 17:00:00 IDT 2014
1209 | CP98 | Tue Feb 01 08:00:00 IST 2011 | Fri Dec 19 17:00:00 IST 2014
1210 | Probing/Drainage (DT) | Sat May 11 08:00:00 IDT 2013 | Sat May 18 17:00:00 IDT 2013
1211 | Segment Dismantle (DT) | Tue May 14 08:00:00 IDT 2013 | Wed May 22 17:00:00 IDT 2013
1212 | Cross Passage Excavation & Temp.Support (DT) | Tue May 21 08:00:00 IDT 2013 | Mon May 27 17:00:00 IDT 2013
1213 | Waterproofing (DT) | Tue Sep 24 08:00:00 IDT 2013 | Wed Oct 02 17:00:00 IDT 2013
1214 | Permanent Slab (DT) | Thu Sep 26 08:00:00 IDT 2013 | Wed Oct 02 17:00:00 IDT 2013
1215 | Permanent Beam (DT) | Fri Sep 27 08:00:00 IDT 2013 | Mon Oct 07 17:00:00 IDT 2013
1216 | Permanent Lining (DT) | Fri Sep 27 08:00:00 IDT 2013 | Thu Oct 03 17:00:00 IDT 2013
1217 | GI works for CP98 | Tue Feb 01 08:00:00 IST 2011 | Mon Feb 14 17:00:00 IST 2011
1218 | Access Works Area 12.1 for Cross Passages CP98 | Sun Jan 15 08:00:00 IST 2012 | Sun Jan 15 08:00:00 IST 2012
1219 | TTA Implementation & Site Setup | Mon Jan 16 08:00:00 IST 2012 | Sat Mar 10 17:00:00 IST 2012
1220 | Install Sleeve Pipe | Wed Oct 03 08:00:00 IST 2012 | Wed Oct 31 17:00:00 IST 2012
1221 | CP98 Jet Grouting from Surface | Thu Nov 01 08:00:00 IST 2012 | Wed Feb 27 17:00:00 IST 2013
1222 | Road Reinstatement | Mon Dec 17 08:00:00 IST 2012 | Fri Jan 25 17:00:00 IST 2013
1223 | Probing/Drainage (UT) (after TBM removal) | Thu Nov 20 08:00:00 IST 2014 | Sat Nov 22 17:00:00 IST 2014
1224 | Segment Dismantle (UT) | Sat Nov 22 08:00:00 IST 2014 | Tue Nov 25 17:00:00 IST 2014
1225 | Cross Passage Excavation & Temp.Support (from UT) | Sat Nov 29 08:00:00 IST 2014 | Thu Dec 04 17:00:00 IST 2014
1226 | Segment Dismantle (DT) | Sat Nov 22 08:00:00 IST 2014 | Tue Nov 25 17:00:00 IST 2014
1227 | Waterproofing | Tue Dec 02 08:00:00 IST 2014 | Thu Dec 04 17:00:00 IST 2014
1228 | Permanent Beam | Mon Dec 15 08:00:00 IST 2014 | Wed Dec 17 17:00:00 IST 2014
1229 | Permanent Lining | Wed Dec 17 08:00:00 IST 2014 | Fri Dec 19 17:00:00 IST 2014
1230 | Permanent Slab | Wed Dec 10 08:00:00 IST 2014 | Fri Dec 12 17:00:00 IST 2014
1231 | Tunnel Lining Design/Submission/Approval | Mon Jan 31 08:00:00 IST 2011 | Wed Nov 30 17:00:00 IST 2011
1232 | Design | Mon Jan 31 08:00:00 IST 2011 | Wed Nov 30 17:00:00 IST 2011
1233 | AIP Submission Preparation - Tunnel Lining | Mon Jan 31 08:00:00 IST 2011 | Mon Feb 21 17:00:00 IST 2011
1234 | AIP Submission to MTR | Mon Feb 21 17:00:00 IST 2011 | Mon Feb 21 17:00:00 IST 2011
1235 | AIP Comment by MTR | Tue Feb 22 08:00:00 IST 2011 | Sun Mar 06 17:00:00 IST 2011
1236 | AIP ReSubmission Preparation - Tunnel Lining | Sat Mar 19 08:00:00 IST 2011 | Thu Mar 31 17:00:00 IST 2011
1237 | AIP ReSubmission to MTR | Mon Apr 04 17:00:00 IDT 2011 | Mon Apr 04 17:00:00 IDT 2011
1238 | AIP Approval by MTR | Tue Apr 05 08:00:00 IDT 2011 | Fri Apr 29 17:00:00 IDT 2011
1239 | DD Submission Preparation - Tunnel Lining | Tue Apr 26 08:00:00 IDT 2011 | Sat Jun 04 17:00:00 IDT 2011
1240 | DD Submission to MTR (RDO/GEO consultation) | Fri May 20 17:00:00 IDT 2011 | Fri May 20 17:00:00 IDT 2011
1241 | DD Comment by MTR (RDO/GEO consultation) | Sat May 21 08:00:00 IDT 2011 | Wed Jun 15 17:00:00 IDT 2011
1242 | DD ReSubmission Preparation - Tunnel Lining | Tue Jun 07 08:00:00 IDT 2011 | Mon Jun 20 17:00:00 IDT 2011
1243 | DD ReSubmission to MTR (RDO/GEO consultation) | Mon Jun 20 17:00:00 IDT 2011 | Mon Jun 20 17:00:00 IDT 2011
1244 | DD Approval by MTR (RDO/GEO consultation) | Tue Jun 21 08:00:00 IDT 2011 | Wed Nov 30 17:00:00 IST 2011
1245 | Tunnel Segment Fabrication | Wed May 18 08:00:00 IDT 2011 | Tue Jun 24 17:00:00 IDT 2014
1246 | Segment mould & Tunnel Segment Fabrication | Wed May 18 08:00:00 IDT 2011 | Fri Jun 28 17:00:00 IDT 2013
1247 | Fabrication | Wed May 18 08:00:00 IDT 2011 | Tue Jun 24 17:00:00 IDT 2014
1248 | Placing Order of Segment Moulds | Tue Jul 19 08:00:00 IDT 2011 | Tue Jul 19 08:00:00 IDT 2011
1249 | Segment Mould Fabrication | Tue Jul 19 08:00:00 IDT 2011 | Thu Mar 22 17:00:00 IST 2012
1250 | Fabrication of Precast Segments - 1st batch | Wed Aug 10 08:00:00 IDT 2011 | Wed Dec 28 17:00:00 IST 2011
1251 | Fabrication of Precast Segments - 2nd batch | Mon Jan 16 08:00:00 IST 2012 | Sat Sep 22 17:00:00 IDT 2012
1252 | 30% Precast Segments (Mil.C5) | Thu Dec 20 17:00:00 IST 2012 | Thu Dec 20 17:00:00 IST 2012
1253 | Fabrication of Precast Segments - 3rd batch | Fri Dec 21 08:00:00 IST 2012 | Fri Apr 19 17:00:00 IDT 2013
1254 | 45% Precast Segments (Mil.C6) | Fri Apr 19 17:00:00 IDT 2013 | Fri Apr 19 17:00:00 IDT 2013
1255 | Fabrication of Precast Segments (Remaining) | Sat Apr 20 08:00:00 IDT 2013 | Tue Jun 24 17:00:00 IDT 2014
1256 | Segment mould & Tunnel Segment Fabrication | Wed May 18 08:00:00 IDT 2011 | Sat Mar 01 17:00:00 IST 2014
1257 | Tunnelling Works
1258 | Submission | Mon Feb 02 08:00:00 IST 2015 | Thu Apr 30 17:00:00 IDT 2015
1259 | Completion | Mon Feb 02 08:00:00 IST 2015 | Thu Apr 30 17:00:00 IDT 2015
1260 | Prepare & Submit Draft As-built Drawings | Mon Feb 02 08:00:00 IST 2015 | Sat Mar 28 17:00:00 IDT 2015
1261 | Prepare & Submit As-built Drawings | Mon Mar 02 08:00:00 IST 2015 | Thu Apr 30 17:00:00 IDT 2015
1262 | Cost Centre D - Nam Cheong Building Cut & Cover Tunnel | Mon Jan 31 08:00:00 IST 2011 | Sun May 10 17:00:00 IDT 2015
1263 | IPS Milestones | Sun Mar 31 17:00:00 IDT 2013 | Sun May 10 17:00:00 IDT 2015
1264 | General | Sun Mar 31 17:00:00 IDT 2013 | Sun May 10 17:00:00 IDT 2015
1265 | Complete D/T Cut & Cover Tunnel - Track Slab | Sun Mar 31 17:00:00 IDT 2013 | Sun Mar 31 17:00:00 IDT 2013
1266 | Deg. 1 Completion for D/T Tunnel | Sun Jun 15 17:00:00 IDT 2014 | Sun Jun 15 17:00:00 IDT 2014
1267 | Complete 40% U/T Cut & Cover Tunnel Structure | Sun Jun 15 17:00:00 IDT 2014 | Sun Jun 15 17:00:00 IDT 2014
1268 | Deg. 1 Completion for U/T Tunnel | Fri Mar 13 17:00:00 IST 2015 | Fri Mar 13 17:00:00 IST 2015
1269 | Closure of Access Opening in Tunnel Roof | Mon Mar 30 17:00:00 IDT 2015 | Mon Mar 30 17:00:00 IDT 2015
1270 | Complete All Works | Sun May 10 17:00:00 IDT 2015 | Sun May 10 17:00:00 IDT 2015
1271 | Design Preparation/Submission/Approval | Mon Jan 31 08:00:00 IST 2011 | Thu Sep 27 17:00:00 IST 2012
1272 | Design | Mon Jan 31 08:00:00 IST 2011 | Thu Sep 27 17:00:00 IST 2012
1273 | Prepare AIP Submission for Cut & Cover Tunnels | Mon Jan 31 08:00:00 IST 2011 | Wed May 25 17:00:00 IDT 2011
1274 | Submit AIP Submission for Cut & Cover Tunnels | Sat Mar 05 17:00:00 IST 2011 | Sat Mar 05 17:00:00 IST 2011
1275 | AIP Comment & Approval for Cut & Cover Tunnels by MTR | Sun Mar 06 08:00:00 IST 2011 | Tue Apr 05 17:00:00 IDT 2011
1276 | Prepare 1st DDA for Cut & Cover Tunnels | Mon Mar 07 08:00:00 IST 2011 | Wed Jul 13 17:00:00 IDT 2011
1277 | Submit 1st DDA for Cut & Cover Tunnels | Mon Apr 11 17:00:00 IDT 2011 | Mon Apr 11 17:00:00 IDT 2011
1278 | 1st DDA Comment & Approval by MTR (RDO/GEO consultation) | Tue Apr 12 08:00:00 IDT 2011 | Sun Jun 19 17:00:00 IDT 2011
1279 | Prepare 2nd DDA for Cut & Cover Tunnels | Mon Jan 16 08:00:00 IST 2012 | Tue Feb 21 17:00:00 IST 2012
1280 | Submit 2nd DDA for Cut & Cover Tunnels | Mon Jan 16 08:00:00 IST 2012 | Mon Jan 16 08:00:00 IST 2012
1281 | 2nd DDA for Cut & Cover Tunnels Comment & Approval by MTR | Fri Aug 31 08:00:00 IDT 2012 | Thu Sep 27 17:00:00 IST 2012
1282 | Method Statement Submission and Approval | Sun Jan 15 08:00:00 IST 2012 | Thu Oct 25 17:00:00 IST 2012
1283 | Method Statement Submission and Approval | Sun Jan 15 08:00:00 IST 2012 | Thu Oct 25 17:00:00 IST 2012
1284 | MS Submission Preparation for Cut & Cover Tunnel | Mon Jan 16 08:00:00 IST 2012 | Thu Feb 16 17:00:00 IST 2012
1285 | MS Submission to MTR | Mon Jan 16 08:00:00 IST 2012 | Mon Jan 16 08:00:00 IST 2012
1286 | MS Comment by MTR | Sun Jan 15 08:00:00 IST 2012 | Sat Feb 11 17:00:00 IST 2012
1287 | MS Re-submission Preparation | Mon Jan 16 08:00:00 IST 2012 | Wed Feb 15 17:00:00 IST 2012
1288 | MS Comment & Approval by MTR | Fri Sep 28 08:00:00 IST 2012 | Thu Oct 25 17:00:00 IST 2012
1289 | Issue for Construction | Thu Oct 25 17:00:00 IST 2012 | Thu Oct 25 17:00:00 IST 2012
1290 | Construction | Sat May 05 08:00:00 IDT 2012 | Sat Apr 18 17:00:00 IDT 2015
1291 | Cut & Cover Tunnel - Track Level | Sat May 05 08:00:00 IDT 2012 | Wed Jul 17 17:00:00 IDT 2013
1292 | D/T: Cut & Cover Tunnel - Wall AW1 | Fri Oct 12 08:00:00 IST 2012 | Tue Nov 06 17:00:00 IST 2012
1293 | D/T: Cut & Cover Tunnel - Wall AW1a | Tue Nov 20 08:00:00 IST 2012 | Wed Dec 05 17:00:00 IST 2012
1294 | D/T: Cut & Cover Tunnel - Wall AW2 | Thu Dec 06 08:00:00 IST 2012 | Mon Dec 31 17:00:00 IST 2012
1295 | D/T: Cut & Cover Tunnel - Wall AD0 | Wed Nov 07 08:00:00 IST 2012 | Thu Nov 22 17:00:00 IST 2012
1296 | U/T: Cut & Cover Tunnel - Slab ATS1 | Thu Dec 20 08:00:00 IST 2012 | Wed Jan 16 17:00:00 IST 2013
1297 | U/T: Cut & Cover Tunnel - Slab ATS2 | Wed Jan 09 08:00:00 IST 2013 | Thu Jan 31 17:00:00 IST 2013
1298 | D/T: Cut & Cover Tunnel - Removal of S4 Struts 2-P1 to P3 | Mon Nov 12 08:00:00 IST 2012 | Sat Nov 24 17:00:00 IST 2012
1299 | D/T: Cut & Cover Tunnel - Wall AD1 | Sat Jun 29 08:00:00 IDT 2013 | Wed Jul 17 17:00:00 IDT 2013
1300 | D/T: Cut & Cover Tunnel - Wall AD2 | Sat May 05 08:00:00 IDT 2012 | Wed May 23 17:00:00 IDT 2012
1301 | Shaft Box B (Northern Portion) | Mon Jan 28 08:00:00 IST 2013 | Wed Jun 11 17:00:00 IDT 2014
1302 | G/L 1 - 5 | Mon Jan 28 08:00:00 IST 2013 | Wed Jun 11 17:00:00 IDT 2014
1303 | Construction of Above Track Slab D/T | Mon Jan 28 08:00:00 IST 2013 | Sat Apr 13 17:00:00 IDT 2013
1304 | Construction of Above Track Slab U/T (Part 1) | Mon Jan 28 08:00:00 IST 2013 | Wed Apr 17 17:00:00 IDT 2013
1305 | Steel Bell & False Tunnel Dismantling | Tue Apr 22 08:00:00 IDT 2014 | Thu May 08 17:00:00 IDT 2014
1306 | Construction of Above Track Slab U/T (Part 2) | Wed May 07 08:00:00 IDT 2014 | Wed Jun 11 17:00:00 IDT 2014
1307 | G/L 1 - 9 | Tue Dec 31 08:00:00 IST 2013 | Thu Feb 13 17:00:00 IST 2014
1308 | North D/T: Construction of Walkway (Dkb137+783 to Dkb 137+850) | Wed Jan 15 08:00:00 IST 2014 | Thu Jan 30 17:00:00 IST 2014
1309 | North U/T: Construction of C & C Tunnel (GL 1 - 9) & Deg. 1 works | Tue Dec 31 08:00:00 IST 2013 | Thu Feb 13 17:00:00 IST 2014
1310 | South Opening at NAC (Dkb137+907 to Dkb137+941) | Mon Dec 02 08:00:00 IST 2013 | Sat Jan 24 17:00:00 IST 2015
1311 | Area 1 - South D/T: Construction of Walkway, External wall, Internal wall, End wall & Above Track Slab (Target dates) | Mon Dec 02 08:00:00 IST 2013 | Sat May 17 17:00:00 IDT 2014
1312 | Area 3 - South U/T: Construction of Walkway, External wall & Internal wall( Target dates) | Mon Sep 01 08:00:00 IDT 2014 | Sat Dec 20 17:00:00 IST 2014
1313 | Area 3 - South U/T: Construction of Above-Track Roof Slab (Closure of Opening) (Target dates) | Mon Dec 22 08:00:00 IST 2014 | Sat Jan 24 17:00:00 IST 2015
1314 | NAC Shaft - Central Opening Structure (Dkb137+850 to Dkb137+885) | Mon May 19 08:00:00 IDT 2014 | Sat Apr 18 17:00:00 IDT 2015
1315 | G/L 9 - 13 (Dkb137+850 to Dkb137+885) | Mon May 19 08:00:00 IDT 2014 | Sat Apr 18 17:00:00 IDT 2015
1316 | Area 2 - D/T Construction of External wall & Walkways | Mon May 19 08:00:00 IDT 2014 | Sat Jun 14 17:00:00 IDT 2014
1317 | Area 4B - Construction of Internal walls and Central portion of Above-Track Roof Slab with falsework | Mon Dec 29 08:00:00 IST 2014 | Sat Feb 07 17:00:00 IST 2015
1318 | Area 4A - U/T Construction of External wall & Walkways (Target dates) | Mon Dec 29 08:00:00 IST 2014 | Sat Jan 24 17:00:00 IST 2015
1319 | Area 4C - Close remaining Above-Track Roof Slab & RC duct btw Dkb137+850 to 137+885 (Target dates) | Mon Dec 29 08:00:00 IST 2014 | Sat Apr 18 17:00:00 IDT 2015
1320 | Cut and Cover Tunnel works
1321 | Access Dates for Designated Contractor
1322 | Submission | Mon Mar 02 08:00:00 IST 2015 | Thu Apr 16 17:00:00 IDT 2015
1323 | Completion | Mon Mar 02 08:00:00 IST 2015 | Thu Apr 16 17:00:00 IDT 2015
1324 | Prepare & Submit Draft As-built Drawings | Mon Mar 02 08:00:00 IST 2015 | Thu Apr 16 17:00:00 IDT 2015
1325 | Prepare & Submit As-built Drawings | Mon Mar 02 08:00:00 IST 2015 | Thu Apr 16 17:00:00 IDT 2015
1326 | Cost Centre E - Nam Cheong Ventilation Building | Wed May 12 08:00:00 IDT 2010 | Mon Aug 24 17:00:00 IDT 2015
1327 | IPS Milestones | Mon Feb 28 08:00:00 IST 2011 | Mon Aug 24 17:00:00 IDT 2015
1328 | General | Mon Feb 28 08:00:00 IST 2011 | Mon Aug 24 17:00:00 IDT 2015
1329 | Complete 20% of Diaphragm Wall | Mon Feb 28 08:00:00 IST 2011 | Mon Feb 28 08:00:00 IST 2011
1330 | Complete 90% Diaphragm Wall | Sun Jun 19 17:00:00 IDT 2011 | Sun Jun 19 17:00:00 IDT 2011
1331 | Complete 100% Diaphragm Wall | Sun Jun 19 17:00:00 IDT 2011 | Sun Jun 19 17:00:00 IDT 2011
1332 | Complete 45% of Excavation | Wed Aug 31 08:00:00 IDT 2011 | Wed Aug 31 08:00:00 IDT 2011
1333 | Complete Excavation | Sun Jan 15 08:00:00 IST 2012 | Sun Jan 15 08:00:00 IST 2012
1334 | Complete 70% Nam Cheong Vent. Building Structure | Sat Sep 14 17:00:00 IDT 2013 | Sat Sep 14 17:00:00 IDT 2013
1335 | Deg.1 Completion for Nam Cheong Vent. Building (VB7), except Track level and Above Track level | Sat May 31 17:00:00 IDT 2014 | Sat May 31 17:00:00 IDT 2014
1336 | All Permanent Doors Installed | Tue Mar 31 17:00:00 IDT 2015 | Tue Mar 31 17:00:00 IDT 2015
1337 | All Work Completed & Statutory Inspection Successfully Undertaken | Mon Aug 24 17:00:00 IDT 2015 | Mon Aug 24 17:00:00 IDT 2015
1338 | Design Preparation/Submission/Approval | Mon Jan 31 08:00:00 IST 2011 | Fri Apr 01 17:00:00 IDT 2011
1339 | Temp.Works Design Submission | Mon Jan 31 08:00:00 IST 2011 | Fri Apr 01 17:00:00 IDT 2011
1340 | Temp. Wokrs Desgn for DW | Mon Jan 31 08:00:00 IST 2011 | Tue Feb 22 17:00:00 IST 2011
1341 | Temp. Works Design Submit to MTR | Thu Mar 03 17:00:00 IST 2011 | Thu Mar 03 17:00:00 IST 2011
1342 | Temp. Works Design Reviewed by MTR | Fri Mar 04 08:00:00 IST 2011 | Tue Mar 29 17:00:00 IST 2011
1343 | Issue for Construction | Fri Apr 01 17:00:00 IDT 2011 | Fri Apr 01 17:00:00 IDT 2011
1344 | Diaphragm Wall Design/submission/Approval | Sat Jan 08 08:00:00 IST 2011 | Tue Nov 29 17:00:00 IST 2011
1345 | Design | Sat Jan 08 08:00:00 IST 2011 | Tue Nov 29 17:00:00 IST 2011
1346 | Prepare Zone A - D-Wall General Arrangement Dwgs & Calculations Part 1 | Sat Jan 08 08:00:00 IST 2011 | Fri Feb 25 17:00:00 IST 2011
1347 | Submit Zone A - D-Wall General Arrangement to MTR (RDO/GEO consultation) | Mon Jan 31 08:00:00 IST 2011 | Mon Jan 31 08:00:00 IST 2011
1348 | Zone A- D-Wall General Arrangement Comments & Approval by MTR (RDO/GEO consultation) | Mon Jan 31 08:00:00 IST 2011 | Sun Feb 13 17:00:00 IST 2011
1349 | Prepare Zone A - D-Wall R.C Details Dwgs.& Calculation Part 2 | Mon Jan 31 08:00:00 IST 2011 | Fri Mar 25 17:00:00 IST 2011
1350 | Submit Zone A - D-Wall R.C Details to MTR | Fri Mar 11 17:00:00 IST 2011 | Fri Mar 11 17:00:00 IST 2011
1351 | Zone A - D-Wall R.C Details Comment & Approval by MTR | Sat Mar 12 08:00:00 IST 2011 | Tue Mar 29 17:00:00 IST 2011
1352 | Prepare Zone A - D-Wall ELS | Sat Mar 12 08:00:00 IST 2011 | Wed Aug 03 17:00:00 IDT 2011
1353 | Submit Zone A - D-Wall ELS to MTR | Wed Apr 27 17:00:00 IDT 2011 | Wed Apr 27 17:00:00 IDT 2011
1354 | Zone A - D-Wall ELS Comment & Approval by MTR | Thu Apr 28 08:00:00 IDT 2011 | Wed Jul 13 17:00:00 IDT 2011
1355 | Prepare Zone B - D-Wall General Arrangement Dwgs & Calculations Part 1 | Sat Jan 08 08:00:00 IST 2011 | Tue Mar 22 17:00:00 IST 2011
1356 | Submit Zone B - D-Wall General Arrangement to MTR (RDO/GEO consultation) | Wed Feb 09 17:00:00 IST 2011 | Wed Feb 09 17:00:00 IST 2011
1357 | Zone B - D-Wall General Arrangement Comments & Approval by MTR (RDO/GEO consultation) | Thu Feb 10 08:00:00 IST 2011 | Thu Mar 10 17:00:00 IST 2011
1358 | Prepare Zone B - D-Wall R.C Details Dwgs.& Calculation Part 2 | Sat Mar 12 08:00:00 IST 2011 | Mon May 16 17:00:00 IDT 2011
1359 | Submit Zone B - D-Wall R.C Details to MTR | Tue Apr 26 17:00:00 IDT 2011 | Tue Apr 26 17:00:00 IDT 2011
1360 | Zone B - D-Wall R.C Details Comments & Approval by MTR | Wed Apr 27 08:00:00 IDT 2011 | Sat May 14 17:00:00 IDT 2011
1361 | Prepare Zone B- D-Wall ELS | Wed Apr 06 08:00:00 IDT 2011 | Tue Nov 29 17:00:00 IST 2011
1362 | Submit Zone B - D-Wall ELS to MTR | Mon Jun 20 08:00:00 IDT 2011 | Mon Jun 20 08:00:00 IDT 2011
1363 | Zone B - D-Wall ELS Comment & Approval by MTR | Sun Jun 19 08:00:00 IDT 2011 | Tue Jul 19 17:00:00 IDT 2011
1364 | Method Statement Submission and Approval | Mon Jan 31 08:00:00 IST 2011 | Sat Apr 02 17:00:00 IDT 2011
1365 | Method Statement Submission and Approval | Mon Jan 31 08:00:00 IST 2011 | Sat Apr 02 17:00:00 IDT 2011
1366 | MS Preparation for Diaphragm wall | Mon Jan 31 08:00:00 IST 2011 | Wed Mar 16 17:00:00 IST 2011
1367 | MS Submission to MTR | Fri Mar 04 17:00:00 IST 2011 | Fri Mar 04 17:00:00 IST 2011
1368 | MS Comment & Approval by MTR | Sat Mar 05 08:00:00 IST 2011 | Wed Mar 23 17:00:00 IST 2011
1369 | Issue for Construction | Sat Apr 02 17:00:00 IDT 2011 | Sat Apr 02 17:00:00 IDT 2011
1370 | TTM Submission and Approval | Wed May 12 08:00:00 IDT 2010 | Sat Feb 12 17:00:00 IST 2011
1371 | TTM Scheme Submission & Approval | Wed May 12 08:00:00 IDT 2010 | Sat Feb 12 17:00:00 IST 2011
1372 | Prepare Temporary Traffic Management (Main Road) | Wed May 12 08:00:00 IDT 2010 | Tue Jun 08 17:00:00 IDT 2010
1373 | TTM reviewed by SLG | Wed May 12 08:00:00 IDT 2010 | Fri Jul 09 17:00:00 IDT 2010
1374 | Approved TTMS | Wed May 12 08:00:00 IDT 2010 | Wed May 12 08:00:00 IDT 2010
1375 | Issue Endorsed Drawings | Wed May 12 08:00:00 IDT 2010 | Tue May 18 17:00:00 IDT 2010
1376 | Notification to RMO | Wed May 12 08:00:00 IDT 2010 | Tue May 18 17:00:00 IDT 2010
1377 | XP Application & Approval (Main Road) | Sat Jan 08 08:00:00 IST 2011 | Sat Feb 12 17:00:00 IST 2011
1378 | Implement TTM (Main Road) | Fri Aug 06 17:00:00 IDT 2010 | Fri Aug 06 17:00:00 IDT 2010
1379 | Prepare TTM (Footpath Closure) | Wed May 12 08:00:00 IDT 2010 | Tue Jun 08 17:00:00 IDT 2010
1380 | TTM Reviewed by SLG | Wed May 12 08:00:00 IDT 2010 | Fri Jul 09 17:00:00 IDT 2010
1381 | Approved TTMS | Wed May 12 08:00:00 IDT 2010 | Wed May 12 08:00:00 IDT 2010
1382 | Issue Endorsed Drawings | Wed May 12 08:00:00 IDT 2010 | Tue May 18 17:00:00 IDT 2010
1383 | Notification to RMO | Wed May 12 08:00:00 IDT 2010 | Tue May 18 17:00:00 IDT 2010
1384 | Implement TTM (Footpath Closure) | Wed May 12 08:00:00 IDT 2010 | Wed May 12 08:00:00 IDT 2010
1385 | Site Establishment | Mon Jan 31 08:00:00 IST 2011 | Wed Apr 06 17:00:00 IDT 2011
1386 | General | Mon Jan 31 08:00:00 IST 2011 | Wed Apr 06 17:00:00 IDT 2011
1387 | Site Establishment for Works Areas 11.23,11.23A, 11.23B &11.26A | Tue Feb 01 08:00:00 IST 2011 | Thu Mar 03 17:00:00 IST 2011
1388 | Installation of Instrumentation for D-wall Construction | Fri Mar 04 08:00:00 IST 2011 | Wed Mar 16 17:00:00 IST 2011
1389 | Preparation of CNP for Shaft Works | Mon Jan 31 08:00:00 IST 2011 | Thu Mar 17 17:00:00 IST 2011
1390 | CNP Submission Approval by EPD | Mon Mar 21 08:00:00 IST 2011 | Wed Apr 06 17:00:00 IDT 2011
1391 | Zone A | Sat Jan 08 08:00:00 IST 2011 | Fri Aug 30 17:00:00 IDT 2013
1392 | D-wall Construction 38nos. & Pump Test | Mon Jan 07 08:00:00 IST 2013 | Sun Aug 25 17:00:00 IDT 2013
1393 | ELS | Mon Jan 07 08:00:00 IST 2013 | Fri Aug 23 17:00:00 IDT 2013
1394 | General | Tue Feb 01 08:00:00 IST 2011 | Mon Mar 28 17:00:00 IST 2011
1395 | Close Footpath (Zone 1) | Tue Feb 01 08:00:00 IST 2011 | Mon Feb 07 17:00:00 IST 2011
1396 | Trial Trench for Gas Main | Tue Feb 08 08:00:00 IST 2011 | Mon Feb 14 17:00:00 IST 2011
1397 | Gas Min Diversion (GAS210) | Tue Feb 15 08:00:00 IST 2011 | Mon Mar 28 17:00:00 IST 2011
1398 | Zone A Construction | Sat Jan 08 08:00:00 IST 2011 | Fri Aug 30 17:00:00 IDT 2013
1399 | Pre-Drilling | Sat Jan 08 08:00:00 IST 2011 | Fri Apr 01 17:00:00 IDT 2011
1400 | Ground Treatment to Previous Seawall Zone (for D1 to D15) | Sat Apr 09 08:00:00 IDT 2011 | Thu Jun 16 17:00:00 IDT 2011
1401 | Guide Wall Installation/Predrilling | Sat Mar 12 08:00:00 IST 2011 | Tue Aug 02 17:00:00 IDT 2011
1402 | Temp.D-Wall Installation (38 Panels) | Fri Mar 25 08:00:00 IST 2011 | Thu Aug 25 17:00:00 IDT 2011
1403 | Shear Pin Installation | Tue Feb 01 08:00:00 IST 2011 | Wed Mar 30 17:00:00 IST 2011
1404 | Toe Grouting | Mon Feb 21 08:00:00 IST 2011 | Sat May 07 17:00:00 IDT 2011
1405 | Capping Beam | Tue Feb 01 08:00:00 IST 2011 | Wed Mar 09 17:00:00 IST 2011
1406 | Installation of instrumentation and Pumping Test | Mon Feb 28 08:00:00 IST 2011 | Sat Apr 16 17:00:00 IDT 2011
1407 | King Post & Gantry Post Installation (KP-4nos. & GP-6nos.) | Tue Feb 01 08:00:00 IST 2011 | Thu Mar 03 17:00:00 IST 2011
1408 | D-wall Construction 38nos. & Pump Test | Mon Jan 07 08:00:00 IST 2013 | Fri Aug 30 17:00:00 IDT 2013
1409 | Stell Bell Installation | Fri Mar 09 08:00:00 IST 2012 | Thu Apr 19 17:00:00 IDT 2012
1410 | Zone A Excavation | Mon Mar 28 08:00:00 IST 2011 | Thu May 31 17:00:00 IDT 2012
1411 | VER.B
1412 | Shaft A ELS | Mon Mar 28 08:00:00 IST 2011 | Thu May 31 17:00:00 IDT 2012
1413 | Surface Levelling to +3.80mPD (for Capping Beam & S1 Strutting) | Mon Mar 28 08:00:00 IST 2011 | Sat Jun 04 17:00:00 IDT 2011
1414 | ELS for Box A (for Steel Bell installation) | Tue Jun 21 08:00:00 IDT 2011 | Thu Jan 26 17:00:00 IST 2012
1415 | ELS for Box A (Remaining) | Mon Jan 16 08:00:00 IST 2012 | Wed Mar 07 17:00:00 IST 2012
1416 | Base Slab Part 1 | Mon Jan 16 08:00:00 IST 2012 | Wed Feb 22 17:00:00 IST 2012
1417 | Strutting Removal for S5 & S6 | Mon Jan 16 08:00:00 IST 2012 | Mon Jan 30 17:00:00 IST 2012
1418 | Base Slab Part 2 | Mon Jan 16 08:00:00 IST 2012 | Thu Mar 15 17:00:00 IST 2012
1419 | Brackets Installation | Mon Jan 16 08:00:00 IST 2012 | Wed Jan 18 17:00:00 IST 2012
1420 | Steel Bell Installation | Mon Jan 16 08:00:00 IST 2012 | Tue Jan 31 17:00:00 IST 2012
1421 | Tympanum Drilling & Steel Fixing | Mon Jan 16 08:00:00 IST 2012 | Thu May 31 17:00:00 IDT 2012
1422 | Zone B | Wed May 12 08:00:00 IDT 2010 | Wed May 23 17:00:00 IDT 2012
1423 | D-wall Construction 13+20nos. & Pump Test | Mon Aug 15 08:00:00 IDT 2011 | Wed May 23 17:00:00 IDT 2012
1424 | ELS | Sun Jun 26 08:00:00 IDT 2011 | Thu Dec 22 17:00:00 IST 2011
1425 | General | Wed May 12 08:00:00 IDT 2010 | Thu Jun 23 17:00:00 IDT 2011
1426 | Tree Transplant by 801 Designated Contractor | Tue Sep 14 08:00:00 IST 2010 | Tue Sep 14 08:00:00 IST 2010
1427 | TTM Implementation (Footpath Closure) | Wed May 12 08:00:00 IDT 2010 | Wed May 12 17:00:00 IDT 2010
1428 | TTM Implementation (Main Road) | Sat Aug 07 08:00:00 IDT 2010 | Sat Aug 07 17:00:00 IDT 2010
1429 | Trial Trench to Expose Utilities @ Footpath | Sat Jan 08 08:00:00 IST 2011 | Fri Jan 21 17:00:00 IST 2011
1430 | Trial Trench for CLP Cable208&209 | Sat Jan 08 08:00:00 IST 2011 | Wed Jan 26 17:00:00 IST 2011
1431 | Excavate Trench for Utilities Diversion | Sat Jan 08 08:00:00 IST 2011 | Sat Jan 22 17:00:00 IST 2011
1432 | Gas Main Diversion (GAS209&GAS208) | Tue Jan 18 08:00:00 IST 2011 | Tue Feb 08 17:00:00 IST 2011
1433 | Preparation works & Excavation for Utilities Diversion | Wed May 12 08:00:00 IDT 2010 | Sat Jul 31 17:00:00 IDT 2010
1434 | Expose and Protect Saltwater Main (SW203) | Sat Jan 08 08:00:00 IST 2011 | Tue Jan 25 17:00:00 IST 2011
1435 | Slew HGC+Cable TV Cable (HGC204+CATV208) | Sat Jan 08 08:00:00 IST 2011 | Sat Feb 12 17:00:00 IST 2011
1436 | Slew WTT+PCCW Cable (WTT205+PCCW205) | Sat Jan 08 08:00:00 IST 2011 | Sat Feb 12 17:00:00 IST 2011
1437 | Slew CLP 11kV Cable | Thu Feb 17 08:00:00 IST 2011 | Thu Feb 24 17:00:00 IST 2011
1438 | Slew 400kV Cable (CLP208) | Sat Aug 07 08:00:00 IDT 2010 | Sat Oct 02 17:00:00 IST 2010
1439 | SlewTelecomCable(HGC204+CATV208)to UtilityTrough | Tue May 31 08:00:00 IDT 2011 | Thu Jun 23 17:00:00 IDT 2011
1440 | SlewTelecomCable(WTT205+PCCW205)to UtilityTrough | Tue May 31 08:00:00 IDT 2011 | Thu Jun 23 17:00:00 IDT 2011
1441 | Backfill & Protection for Utilities | Mon Feb 28 08:00:00 IST 2011 | Wed May 04 17:00:00 IDT 2011
1442 | Zone B West (Not within Utilities Zone) | Mon Feb 28 08:00:00 IST 2011 | Wed May 23 17:00:00 IDT 2012
1443 | Pre-drilling/Guide Wall Installation | Sat Mar 12 08:00:00 IST 2011 | Sat Apr 09 17:00:00 IDT 2011
1444 | Temp.D-Wall Installation (13Panels) | Thu Apr 28 08:00:00 IDT 2011 | Tue Aug 16 17:00:00 IDT 2011
1445 | Shear Pin Installation | Mon Feb 28 08:00:00 IST 2011 | Thu Jun 23 17:00:00 IDT 2011
1446 | Toe Grouting | Fri Apr 01 08:00:00 IDT 2011 | Wed Jul 27 17:00:00 IDT 2011
1447 | Stitch Grouting btn D-Wall & FS1 Culvert | Tue Jun 21 08:00:00 IDT 2011 | Mon Jul 18 17:00:00 IDT 2011
1448 | D-wall Construction 13+20nos. & Pump Test | Mon Aug 15 08:00:00 IDT 2011 | Wed May 23 17:00:00 IDT 2012
1449 | Zone B Remaining | Tue Feb 01 08:00:00 IST 2011 | Wed Feb 01 17:00:00 IST 2012
1450 | Ground Treatment to Previous Seawall Zone | Tue Feb 01 08:00:00 IST 2011 | Wed Jun 01 17:00:00 IDT 2011
1451 | Pre-drilling/ Guide Wall Installation | Tue Feb 01 08:00:00 IST 2011 | Mon Mar 21 17:00:00 IST 2011
1452 | Temp.D-Wall Installation ( 20 Panels) | Mon Mar 21 08:00:00 IST 2011 | Sat Oct 08 17:00:00 IST 2011
1453 | Shear Pin Installation | Thu Jul 14 11:00:00 IDT 2011 | Fri Sep 02 11:00:00 IDT 2011
1454 | Toe Grouting | Fri Jul 29 08:00:00 IDT 2011 | Tue Aug 30 17:00:00 IDT 2011
1455 | Stitch Grouting between D-Wall & FS1 Culvert | Wed Jul 06 08:00:00 IDT 2011 | Thu Aug 25 17:00:00 IDT 2011
1456 | Capping Beam | Tue Jun 21 08:00:00 IDT 2011 | Tue Aug 09 17:00:00 IDT 2011
1457 | Install Instrumentation+Pumping Test | Thu Aug 04 08:00:00 IDT 2011 | Wed Sep 21 17:00:00 IDT 2011
1458 | Utilities Common Trough | Mon Jan 16 08:00:00 IST 2012 | Wed Feb 01 17:00:00 IST 2012
1459 | Setup & Install Four Prebored H-piles (adjacent to Existing B17) | Fri Jul 08 08:00:00 IDT 2011 | Mon Jul 25 17:00:00 IDT 2011
1460 | King Post & Gantry Post Installation (7KP & 2GP) | Tue Jun 21 08:00:00 IDT 2011 | Tue Aug 02 17:00:00 IDT 2011
1461 | Zone B Excavation | Tue Jun 21 08:00:00 IDT 2011 | Tue Apr 03 17:00:00 IDT 2012
1462 | ELS | Sun Jun 26 08:00:00 IDT 2011 | Thu Dec 22 17:00:00 IST 2011
1463 | Steel Bell Installation | Sun Jan 15 08:00:00 IST 2012 | Sun Jan 15 08:00:00 IST 2012
1464 | Shaft B ELS | Tue Jun 21 08:00:00 IDT 2011 | Tue Apr 03 17:00:00 IDT 2012
1465 | Surface Levelling to +3.80mPD (for Capping Beam & S1 Strutting) | Wed Aug 24 08:00:00 IDT 2011 | Wed Sep 28 17:00:00 IDT 2011
1466 | ELS for Box B (for Steel Bell Installation) | Tue Jun 21 08:00:00 IDT 2011 | Thu Nov 10 17:00:00 IST 2011
1467 | ELS for Box B (Remaining) | Mon Jan 16 08:00:00 IST 2012 | Thu Mar 01 17:00:00 IST 2012
1468 | Base Slab Part 1 | Mon Jan 16 08:00:00 IST 2012 | Tue Feb 21 17:00:00 IST 2012
1469 | Strutting Removal for S5 & S6 | Mon Jan 16 08:00:00 IST 2012 | Thu Jan 26 17:00:00 IST 2012
1470 | Base Slab Part 2 | Mon Jan 16 08:00:00 IST 2012 | Wed Feb 29 17:00:00 IST 2012
1471 | Brackets Installation | Mon Jan 16 08:00:00 IST 2012 | Tue Jan 17 17:00:00 IST 2012
1472 | Steel Bell Installation | Mon Jan 16 08:00:00 IST 2012 | Wed Feb 01 17:00:00 IST 2012
1473 | Tympanum Drilling & Steel Fixing | Mon Jan 16 08:00:00 IST 2012 | Tue Apr 03 17:00:00 IDT 2012
1474 | Ventilation Building | Sat Sep 01 08:00:00 IDT 2012 | Mon Aug 24 17:00:00 IDT 2015
1475 | Access Dates for Designated Contractors | Mon Apr 28 08:00:00 IDT 2014 | Mon Apr 28 08:00:00 IDT 2014
1476 | *815 - Ironmongery Delivery to Site | Mon Apr 28 08:00:00 IDT 2014 | Mon Apr 28 08:00:00 IDT 2014
1477 | Reinforced Concrete Structure | Sat Sep 01 08:00:00 IDT 2012 | Thu Aug 13 17:00:00 IDT 2015
1478 | Shaft Box B (Northern Portion) | Sat Sep 01 08:00:00 IDT 2012 | Fri Jun 06 17:00:00 IDT 2014
1479 | G/L 1 - 5 | Fri Jan 04 08:00:00 IST 2013 | Sat Jul 06 17:00:00 IDT 2013
1480 | Construction of L2 Slab | Fri Jan 04 08:00:00 IST 2013 | Sat Feb 02 17:00:00 IST 2013
1481 | Construction of L1 Slab | Wed Feb 20 08:00:00 IST 2013 | Thu Mar 21 17:00:00 IST 2013
1482 | Construction of L0 Slab | Mon Jun 03 08:00:00 IDT 2013 | Sat Jul 06 17:00:00 IDT 2013
1483 | G/L 5 - 9 | Sat Sep 01 08:00:00 IDT 2012 | Thu Jul 11 17:00:00 IDT 2013
1484 | Construction of L2 Slab | Sat Sep 01 08:00:00 IDT 2012 | Wed Nov 28 17:00:00 IST 2012
1485 | Construction of L1 Slab (including 2 FS Tank) | Thu Nov 29 08:00:00 IST 2012 | Fri Mar 08 17:00:00 IST 2013
1486 | Construction of L0 Slab | Mon Apr 29 08:00:00 IDT 2013 | Thu Jul 11 17:00:00 IDT 2013
1487 | G/L 1 - 6 | Mon Nov 11 08:00:00 IST 2013 | Fri Jun 06 17:00:00 IDT 2014
1488 | Construction of G/L Slab | Tue Mar 04 08:00:00 IST 2014 | Wed Mar 26 17:00:00 IST 2014
1489 | Construction of U1 Slab | Mon Apr 14 08:00:00 IDT 2014 | Mon May 05 17:00:00 IDT 2014
1490 | Construction of Service Slab | Fri May 23 08:00:00 IDT 2014 | Fri Jun 06 17:00:00 IDT 2014
1491 | Construction of Roof Slab | Mon May 19 08:00:00 IDT 2014 | Wed Jun 04 17:00:00 IDT 2014
1492 | Gantry impact from TBM Re-assembly and False Tunnel Dismantling | Mon Nov 11 08:00:00 IST 2013 | Thu Jan 23 17:00:00 IST 2014
1493 | Ch137+968 to Ch138+328 (200 Ring nos.) | Sat Dec 14 08:00:00 IST 2013 | Tue Jan 21 17:00:00 IST 2014
1494 | Shaft Box A (Southern Portion)
1495 | G/L 13 - 15
1496 | G/L 11 - 13
1497 | FS1 Works at Shaft Central Portion | Mon Jun 15 08:00:00 IDT 2015 | Thu Aug 13 17:00:00 IDT 2015
1498 | G/L 9 - 11 | Mon Jun 15 08:00:00 IDT 2015 | Thu Aug 13 17:00:00 IDT 2015
1499 | Construction of column & cantilver slab under FS1 (after closure of opening) | Mon Jun 15 08:00:00 IDT 2015 | Thu Jul 09 17:00:00 IDT 2015
1500 | Backfilling & Reinstatement of FS1 | Sat Jul 11 08:00:00 IDT 2015 | Thu Aug 13 17:00:00 IDT 2015
1501 | Track Level
1502 | Above Track Level
1503 | L2 Level
1504 | L1 Level
1505 | L0 Level
1506 | G/F Level
1507 | U1 Level
1508 | Backfilling, Strut removal & Reinstatement | Mon Aug 05 08:00:00 IDT 2013 | Thu Jul 30 09:36:00 IDT 2015
1509 | Backfilling and Strut Removal | Mon Aug 05 08:00:00 IDT 2013 | Wed Jul 15 17:00:00 IDT 2015
1510 | GL 1 - 8 (works concurrently to VB7 construction) | Mon Aug 05 08:00:00 IDT 2013 | Fri Nov 22 17:00:00 IST 2013
1511 | GL 15 - 20 | Thu Apr 02 08:00:00 IDT 2015 | Mon Jun 08 17:00:00 IDT 2015
1512 | GL 8 - 15 | Mon May 18 08:00:00 IDT 2015 | Wed Jul 15 17:00:00 IDT 2015
1513 | Housing Car park and Podium Shop | Sat Jul 11 09:36:00 IDT 2015 | Thu Jul 30 09:36:00 IDT 2015
1514 | Concrete breaking of last 2m of D-wall (Option) | Sat Jul 11 09:36:00 IDT 2015 | Thu Jul 30 09:36:00 IDT 2015
1515 | ABWF works | Wed Sep 11 08:00:00 IDT 2013 | Mon Aug 24 17:00:00 IDT 2015
1516 | Degree 1 works | Wed Sep 11 08:00:00 IDT 2013 | Mon Jul 28 17:00:00 IDT 2014
1517 | Ref.4C (i) (Deg.1): All Rms within VB7 at Level L2, UL2, L1 and UL1 | Wed Sep 11 08:00:00 IDT 2013 | Fri Nov 29 17:00:00 IST 2013
1518 | Floor Screeding (L2) | Wed Sep 11 08:00:00 IDT 2013 | Fri Oct 25 17:00:00 IDT 2013
1519 | Floor Screeding (L1) | Fri Nov 01 08:00:00 IST 2013 | Fri Nov 29 17:00:00 IST 2013
1520 | Ref.4C (ii) (Deg.1): All Rms within VB7 at Track Level & Above Track Level | Mon Dec 02 08:00:00 IST 2013 | Sat Mar 01 17:00:00 IST 2014
1521 | Floor Screeding (Track Level & Above Track Level) | Mon Dec 02 08:00:00 IST 2013 | Wed Jan 15 17:00:00 IST 2014
1522 | Degree 1 works for 4C(ii) | Wed Jan 15 08:00:00 IST 2014 | Sat Mar 01 17:00:00 IST 2014
1523 | Ref.4C (iii) (Deg.1): All Rms within VB7 (excluding Ref.4C (i) & 4C (ii)) | Mon Apr 07 08:00:00 IDT 2014 | Mon Jul 28 17:00:00 IDT 2014
1524 | Floor Screeding (G/F) | Fri May 02 08:00:00 IDT 2014 | Fri May 16 17:00:00 IDT 2014
1525 | Degree 1 works for 4C (iii) | Mon Apr 07 08:00:00 IDT 2014 | Wed May 28 17:00:00 IDT 2014
1526 | Floor Screeding (U1/F) | Tue May 27 08:00:00 IDT 2014 | Tue Jun 10 17:00:00 IDT 2014
1527 | Floor Screeding & Waterproofing (Roof) | Wed Jul 23 08:00:00 IDT 2014 | Mon Jul 28 17:00:00 IDT 2014
1528 | Degree 2 works | Mon Nov 04 08:00:00 IST 2013 | Sat Jul 12 17:00:00 IDT 2014
1529 | Deg. 2 Works for Level L1, UL2, L1 and UL1 | Mon Nov 04 08:00:00 IST 2013 | Tue Feb 11 17:00:00 IST 2014
1530 | Deg. 2 Works for Track level and Above Track level | Tue Dec 31 08:00:00 IST 2013 | Sat Mar 22 17:00:00 IST 2014
1531 | Deg. 2 Works for Level L0, Ground Floor, U1, Service level & Roof | Mon Mar 24 08:00:00 IST 2014 | Sat Jul 12 17:00:00 IDT 2014
1532 | Degree 3 works | Mon Feb 24 08:00:00 IST 2014 | Fri Sep 05 17:00:00 IDT 2014
1533 | Deg. 3 Works for Level L1, UL2, L1 and UL1 | Mon Feb 24 08:00:00 IST 2014 | Thu Apr 17 17:00:00 IDT 2014
1534 | Deg. 3 Works for Track level and Above Track level | Mon Mar 24 08:00:00 IST 2014 | Sat May 17 17:00:00 IDT 2014
1535 | Deg. 3 Works for Level L0, Ground Floor, U1, Service level & Roof | Mon Jul 14 08:00:00 IDT 2014 | Fri Sep 05 17:00:00 IDT 2014
1536 | External Works | Fri May 23 08:00:00 IDT 2014 | Mon Aug 24 17:00:00 IDT 2015
1537 | Start External works | Fri May 23 08:00:00 IDT 2014 | Fri May 23 08:00:00 IDT 2014
1538 | Site Formation Works | Fri May 23 08:00:00 IDT 2014 | Thu Aug 07 17:00:00 IDT 2014
1539 | Roadworks and External Works | Fri Jun 13 08:00:00 IDT 2014 | Thu Aug 28 17:00:00 IDT 2014
1540 | Landscaping | Mon Dec 15 08:00:00 IST 2014 | Mon Mar 23 08:24:00 IST 2015
1541 | Paving | Thu Aug 14 08:00:00 IDT 2014 | Sat Oct 25 08:48:00 IDT 2014
1542 | Statutory Inspection | Sat Jul 25 08:00:00 IDT 2015 | Mon Aug 24 17:00:00 IDT 2015
1543 | Complete Ext. Water Works & Connect to Watermains | Fri Jul 24 17:00:00 IDT 2015 | Fri Jul 24 17:00:00 IDT 2015
1544 | Completion Ext. Telephone Drawpits & Ducts | Fri Jul 24 17:00:00 IDT 2015 | Fri Jul 24 17:00:00 IDT 2015
1545 | Submission | Mon Jan 12 08:00:00 IST 2015 | Thu Apr 30 17:00:00 IDT 2015
1546 | Completion | Mon Jan 12 08:00:00 IST 2015 | Thu Apr 30 17:00:00 IDT 2015
1547 | Prepare & Submit Draft As-built Drawings | Mon Jan 12 08:00:00 IST 2015 | Sat Feb 07 17:00:00 IST 2015
1548 | Prepare & Submit As-built Drawings | Mon Mar 02 08:00:00 IST 2015 | Thu Apr 30 17:00:00 IDT 2015
1549 | Prepare & Submit Draft O&M Manuals | Fri Jan 16 08:00:00 IST 2015 | Thu Feb 12 17:00:00 IST 2015
1550 | Prepare & Submit O&M Manuals | Mon Mar 02 08:00:00 IST 2015 | Thu Apr 30 17:00:00 IDT 2015
1551 | Cost Centre F - Obstruction removal & Reinstate Works | Sat Jan 08 08:00:00 IST 2011 | Sun May 10 17:00:00 IDT 2015
1552 | IPS Milestones | Mon Feb 28 08:00:00 IST 2011 | Sun May 10 17:00:00 IDT 2015
1553 | General | Mon Feb 28 08:00:00 IST 2011 | Sun May 10 17:00:00 IDT 2015
1554 | Obtain SLG Approval for Confirm Old CheungShaWan Cargo Pier Pile Locat'n | Mon Feb 28 08:00:00 IST 2011 | Mon Feb 28 08:00:00 IST 2011
1555 | Complete Removal of 3 nos. Existing Piles | Wed Sep 07 17:00:00 IDT 2011 | Wed Sep 07 17:00:00 IDT 2011
1556 | Complete 10% Mini-piles for Lai Chi Kok Overpass | Wed Aug 31 08:00:00 IDT 2011 | Wed Aug 31 08:00:00 IDT 2011
1557 | Complete Backfilling Works for Demolished FMO Maket Pier B | Sun Jan 15 08:00:00 IST 2012 | Sun Jan 15 08:00:00 IST 2012
1558 | Removal of Obstruction Piles for Demolished Sham Shui Po Pier (DT) | Tue Nov 13 17:00:00 IST 2012 | Tue Nov 13 17:00:00 IST 2012
1559 | Removal of Obstruction Piles for Old Cheung Sha Wan Cargo Pier(DT) | Fri Aug 31 08:00:00 IDT 2012 | Fri Aug 31 08:00:00 IDT 2012
1560 | Complete Reinstatement of TWL Sump | Tue Jan 15 17:00:00 IST 2013 | Tue Jan 15 17:00:00 IST 2013
1561 | Complete U/G Services & Reinstatement for Lai Chi Kok Overpass | Sun Sep 29 17:00:00 IDT 2013 | Sun Sep 29 17:00:00 IDT 2013
1562 | Complete All Works | Sun May 10 17:00:00 IDT 2015 | Sun May 10 17:00:00 IDT 2015
1563 | F1 Complete TWL New Sump Provision | Mon Feb 28 08:00:00 IST 2011 | Mon Jul 29 17:00:00 IDT 2013
1564 | Method Statement Submission and Approval | Mon May 16 08:00:00 IDT 2011 | Fri Nov 25 17:00:00 IST 2011
1565 | MS Preparation for TWL Sump Pit Modification | Mon May 16 08:00:00 IDT 2011 | Wed Oct 12 17:00:00 IST 2011
1566 | MS Submission to MTR | Wed Aug 31 08:00:00 IDT 2011 | Wed Aug 31 08:00:00 IDT 2011
1567 | MS Comment by MTR | Wed Aug 31 08:00:00 IDT 2011 | Tue Sep 27 17:00:00 IDT 2011
1568 | MS Re-submission Preparation | Wed Aug 31 08:00:00 IDT 2011 | Wed Sep 14 17:00:00 IDT 2011
1569 | MS Comment & Approval by MTR | Wed Aug 31 08:00:00 IDT 2011 | Tue Sep 27 17:00:00 IDT 2011
1570 | Issue for Construction | Fri Nov 25 17:00:00 IST 2011 | Fri Nov 25 17:00:00 IST 2011
1571 | Design Submission & Approval | Mon Feb 28 08:00:00 IST 2011 | Fri Oct 21 17:00:00 IST 2011
1572 | AIP Submission of Temp.& Permanent Sump Modification | Wed Jun 08 08:00:00 IDT 2011 | Thu Jul 07 17:00:00 IDT 2011
1573 | MTR's Comment for AIP of Temp.& Permanent Sump Modification | Mon Feb 28 08:00:00 IST 2011 | Sat Mar 12 17:00:00 IST 2011
1574 | AIP Re-submission of Temp.&Permanent Sump Modification | Mon Feb 28 08:00:00 IST 2011 | Wed Mar 30 17:00:00 IST 2011
1575 | MTR's Comment & Approval for AIP of Temp.Work Design for Sump Modification | Mon Feb 28 08:00:00 IST 2011 | Sun Jul 17 17:00:00 IDT 2011
1576 | DDA Submission of Temp.Shaft Design | Wed Jun 08 08:00:00 IDT 2011 | Wed Jul 06 17:00:00 IDT 2011
1577 | MTR's Comment & Approval for DDA of Temp.Shaft Design | Mon Feb 28 08:00:00 IST 2011 | Mon Aug 01 17:00:00 IDT 2011
1578 | DDA Submission of Permanent Sump Modification | Wed Aug 31 08:00:00 IDT 2011 | Wed Sep 28 17:00:00 IDT 2011
1579 | MTR's Comment & Approval for DDA of Permanent Sump Modification | Thu Sep 29 08:00:00 IDT 2011 | Fri Oct 21 17:00:00 IST 2011
1580 | AIP Submission of TWL Protection Works | Wed May 25 08:00:00 IDT 2011 | Tue Jun 21 17:00:00 IDT 2011
1581 | MTR's Comment for AIP of TWL Protection Works | Mon Feb 28 08:00:00 IST 2011 | Sun Mar 13 17:00:00 IST 2011
1582 | 1st AIP Re-submission of TWL Protection Works | Mon Feb 28 08:00:00 IST 2011 | Tue Mar 29 17:00:00 IST 2011
1583 | MTR's Comment & Approval for 1st AIP of TWL Protection Works | Mon Feb 28 08:00:00 IST 2011 | Tue Mar 22 17:00:00 IST 2011
1584 | 2nd AIP Re-submission of TWL Protection Works | Mon Feb 28 08:00:00 IST 2011 | Wed Jul 20 17:00:00 IDT 2011
1585 | MTR's Approval for 2nd AIP of TWL Protection Works | Thu Sep 01 08:00:00 IDT 2011 | Wed Sep 28 17:00:00 IDT 2011
1586 | DDA Submission of TWL Protection Works | Wed Aug 31 08:00:00 IDT 2011 | Wed Sep 28 17:00:00 IDT 2011
1587 | MTR's Approval for DDA of TWL Protection Works | Wed Aug 31 08:00:00 IDT 2011 | Tue Sep 27 17:00:00 IDT 2011
1588 | EDOC (TWL) Submission of Temp.Sump Modification | Wed Jun 08 08:00:00 IDT 2011 | Fri Jul 08 17:00:00 IDT 2011
1589 | MTR's Comment for EDOC (TWL)Temp.Sump Modification | Mon Feb 28 08:00:00 IST 2011 | Wed Mar 23 17:00:00 IST 2011
1590 | EDOC (TWL) Re-submission of Temp.Sump Modification | Mon Feb 28 08:00:00 IST 2011 | Wed May 11 17:00:00 IDT 2011
1591 | MTR's Comment & Approval for EDOC of Temp.Work Design for Sump Modification | Mon Feb 28 08:00:00 IST 2011 | Sun Jul 17 17:00:00 IDT 2011
1592 | EDOC (TWL) Submission of Protection Works | Wed Jun 08 08:00:00 IDT 2011 | Fri Jul 08 17:00:00 IDT 2011
1593 | MTR's Comment for EDOC (TWL) Protection Works | Mon Feb 28 08:00:00 IST 2011 | Sat Sep 24 17:00:00 IDT 2011
1594 | EDOC (TWL) Re-submission of Protection Works | Wed Aug 31 08:00:00 IDT 2011 | Thu Sep 29 17:00:00 IDT 2011
1595 | MTR's Comment & Approval for EDOC of Protection Works | Wed Aug 31 08:00:00 IDT 2011 | Fri Sep 23 17:00:00 IDT 2011
1596 | Circular Shaft Construction | Mon Feb 28 08:00:00 IST 2011 | Wed Jan 16 17:00:00 IST 2013
1597 | Area 37.3 Tree Transplant by 801 Designated Contrator | Mon Feb 28 08:00:00 IST 2011 | Mon Feb 28 08:00:00 IST 2011
1598 | Site Possession (Area 10.3) | Mon Mar 28 08:00:00 IST 2011 | Mon Mar 28 08:00:00 IST 2011
1599 | Set-up Plan & Hoarding Plan Submn & Approval | Mon Feb 28 08:00:00 IST 2011 | Tue Apr 12 17:00:00 IDT 2011
1600 | Site Setup & Hoarding Erection | Mon Feb 28 08:00:00 IST 2011 | Tue Mar 22 17:00:00 IST 2011
1601 | Install Instruments/Monitoring Stations | Mon Feb 28 08:00:00 IST 2011 | Sat Mar 19 17:00:00 IST 2011
1602 | Trial Trench to Locate Exist'g 400kV & StormDrain | Mon Mar 21 08:00:00 IST 2011 | Tue Apr 12 17:00:00 IDT 2011
1603 | Protection for 400kV & 600 dia.Storm Drain | Tue Jul 19 08:00:00 IDT 2011 | Sat Aug 20 17:00:00 IDT 2011
1604 | Drilling for Jet Grouting | Mon Aug 08 08:00:00 IDT 2011 | Thu Oct 27 17:00:00 IST 2011
1605 | Ground Treatment by Jet Grout | Wed Aug 31 08:00:00 IDT 2011 | Fri Sep 30 17:00:00 IDT 2011
1606 | Drilling for Fissure Grout | Wed Aug 31 08:00:00 IDT 2011 | Thu Sep 29 17:00:00 IDT 2011
1607 | Ground Treatment by Fissure Grout | Wed Aug 31 08:00:00 IDT 2011 | Wed Sep 28 17:00:00 IDT 2011
1608 | Bored Pile | Mon Jan 16 08:00:00 IST 2012 | Sat Feb 18 17:00:00 IST 2012
1609 | Install Internal Casing | Mon Jan 16 08:00:00 IST 2012 | Fri Jan 27 17:00:00 IST 2012
1610 | Concrete Water Plug | Mon Jan 16 08:00:00 IST 2012 | Tue Jan 17 17:00:00 IST 2012
1611 | Grouting & Extract External Casing | Mon Jan 16 08:00:00 IST 2012 | Tue Jan 17 17:00:00 IST 2012
1612 | Dewatering/ Pumping System | Mon Jan 16 08:00:00 IST 2012 | Fri Jan 20 17:00:00 IST 2012
1613 | Ventilation, Lighting System | Mon Jan 16 08:00:00 IST 2012 | Fri Jan 20 17:00:00 IST 2012
1614 | Setup Access Shaft | Mon Jan 16 08:00:00 IST 2012 | Fri Jan 20 17:00:00 IST 2012
1615 | Circular Shaft Const'n & Install Temp.Pumping System | Mon Aug 15 08:00:00 IDT 2011 | Wed Jan 16 17:00:00 IST 2013
1616 | Adit Construction | Mon Jan 16 08:00:00 IST 2012 | Tue Oct 09 17:00:00 IST 2012
1617 | Post Form Adit Opening | Mon Jan 16 08:00:00 IST 2012 | Fri Jan 20 17:00:00 IST 2012
1618 | Adit Excavation | Mon Jan 16 08:00:00 IST 2012 | Wed Feb 29 17:00:00 IST 2012
1619 | Lining for Adit | Wed Oct 03 08:00:00 IST 2012 | Tue Oct 09 17:00:00 IST 2012
1620 | Construction of Pipe Canopy | Wed Oct 10 08:00:00 IST 2012 | Fri Dec 21 17:00:00 IST 2012
1621 | Concrete Coring & Saw Cut for Sump Pit Wall | Wed Oct 10 08:00:00 IST 2012 | Tue Oct 16 17:00:00 IST 2012
1622 | Erection Temp. Props Support | Wed Oct 17 08:00:00 IST 2012 | Thu Oct 18 17:00:00 IST 2012
1623 | Enlarge Sump Pit Opening | Fri Oct 19 08:00:00 IST 2012 | Mon Oct 22 17:00:00 IST 2012
1624 | Erect Temporary Props | Wed Oct 24 08:00:00 IST 2012 | Tue Oct 30 17:00:00 IST 2012
1625 | Setup Pumping System | Wed Oct 31 08:00:00 IST 2012 | Tue Nov 06 17:00:00 IST 2012
1626 | Remove Existing Pumping System | Wed Nov 07 08:00:00 IST 2012 | Thu Nov 08 17:00:00 IST 2012
1627 | Mass Concrete for Drilling rig Platform | Fri Nov 09 08:00:00 IST 2012 | Mon Nov 12 17:00:00 IST 2012
1628 | Delivery and Setup Drillilng Rig | Tue Nov 13 08:00:00 IST 2012 | Mon Nov 19 17:00:00 IST 2012
1629 | Construction of Pipe Canopy | Tue Nov 20 08:00:00 IST 2012 | Fri Dec 21 17:00:00 IST 2012
1630 | Pipe Canopy Construction | Wed Oct 10 08:00:00 IST 2012 | Fri Dec 21 17:00:00 IST 2012
1631 | Modification of Existing Sump | Sat Dec 22 08:00:00 IST 2012 | Tue Jan 15 17:00:00 IST 2013
1632 | Strengthen Adit & Sump Opening Connection | Sat Dec 22 08:00:00 IST 2012 | Sat Dec 29 17:00:00 IST 2012
1633 | Install Prop above Slab Cut Line | Sat Dec 22 08:00:00 IST 2012 | Mon Dec 24 17:00:00 IST 2012
1634 | Saw Cut Pit Wall above Base Slab | Thu Dec 27 08:00:00 IST 2012 | Wed Jan 02 17:00:00 IST 2013
1635 | RC Base Slab Construction | Thu Jan 03 08:00:00 IST 2013 | Tue Jan 15 17:00:00 IST 2013
1636 | Modification of Existing Sump | Sat Dec 22 08:00:00 IST 2012 | Tue Jan 15 17:00:00 IST 2013
1637 | Reinstatement | Tue Nov 06 08:00:00 IST 2012 | Mon Apr 08 17:00:00 IDT 2013
1638 | Make Good Pit Wall | Wed Jan 16 08:00:00 IST 2013 | Tue Jan 22 17:00:00 IST 2013
1639 | GI at Sump Pit for TWL | Wed Jan 23 08:00:00 IST 2013 | Mon Feb 04 17:00:00 IST 2013
1640 | Reinstate Permanent Pump system | Tue Feb 05 08:00:00 IST 2013 | Tue Mar 05 17:00:00 IST 2013
1641 | Reinstate Pit Wall | Wed Mar 06 08:00:00 IST 2013 | Mon Mar 18 17:00:00 IST 2013
1642 | Backfill Adit & Shaft by Lean Concrete | Tue Nov 06 08:00:00 IST 2012 | Wed Nov 21 17:00:00 IST 2012
1643 | TWL Reinstatement | Wed Jan 16 08:00:00 IST 2013 | Mon Apr 08 17:00:00 IDT 2013
1644 | Completion | Tue Jul 02 08:00:00 IDT 2013 | Mon Jul 29 17:00:00 IDT 2013
1645 | Prepare & Submit Draft As-built Drawings | Tue Jul 02 08:00:00 IDT 2013 | Mon Jul 29 17:00:00 IDT 2013
1646 | Prepare & Submit As-built Drawings | Tue Jul 02 08:00:00 IDT 2013 | Mon Jul 29 17:00:00 IDT 2013
1647 | F2 Complete Lai Chi Kok Overpass New Concrete Beam | Mon Feb 28 08:00:00 IST 2011 | Wed Sep 25 17:00:00 IDT 2013
1648 | Method Statement Submission and Approval | Sun Jun 19 08:00:00 IDT 2011 | Tue Oct 04 17:00:00 IST 2011
1649 | MS Preparation for Underpinning | Sun Jun 19 08:00:00 IDT 2011 | Tue Oct 04 17:00:00 IST 2011
1650 | MS Submission to MTR/DSD | Wed Aug 31 08:00:00 IDT 2011 | Wed Aug 31 08:00:00 IDT 2011
1651 | MS Comment by MTR | Wed Aug 31 08:00:00 IDT 2011 | Fri Sep 23 17:00:00 IDT 2011
1652 | MS Re-submission Preparation | Wed Aug 31 08:00:00 IDT 2011 | Thu Sep 29 17:00:00 IDT 2011
1653 | MS Comment & Approval by MTR | Wed Aug 31 08:00:00 IDT 2011 | Tue Sep 27 17:00:00 IDT 2011
1654 | Issue for Construction | Wed Sep 28 17:00:00 IDT 2011 | Wed Sep 28 17:00:00 IDT 2011
1655 | TTM Scheme Submission & Approval | Mon Feb 28 08:00:00 IST 2011 | Thu Sep 29 17:00:00 IDT 2011
1656 | Prepare Temporary Traffic Management | Mon Feb 28 08:00:00 IST 2011 | Fri Mar 25 17:00:00 IST 2011
1657 | TTM reviewed by SLG | Sat Mar 26 08:00:00 IST 2011 | Sat Jun 18 17:00:00 IDT 2011
1658 | Resubmit TTM | Tue Jun 21 08:00:00 IDT 2011 | Mon Jun 27 17:00:00 IDT 2011
1659 | TTM reviewed by SLG | Tue Jun 28 08:00:00 IDT 2011 | Wed Jul 27 17:00:00 IDT 2011
1660 | Notification to RMO | Tue Jul 26 08:00:00 IDT 2011 | Mon Aug 01 17:00:00 IDT 2011
1661 | XP Application & Approval | Thu Jun 02 08:00:00 IDT 2011 | Fri Jun 17 17:00:00 IDT 2011
1662 | Implement TTM | Fri Aug 12 17:00:00 IDT 2011 | Fri Aug 12 17:00:00 IDT 2011
1663 | Traffic Diversion Works | Sat Aug 13 08:00:00 IDT 2011 | Thu Sep 29 17:00:00 IDT 2011
1664 | Design Submission & Approval | Mon Feb 28 08:00:00 IST 2011 | Wed Oct 12 17:00:00 IST 2011
1665 | Site Investigation | Wed Jun 01 08:00:00 IDT 2011 | Wed Oct 12 17:00:00 IST 2011
1666 | Prepare Temp.Work Design for Underpinning | Mon Feb 28 08:00:00 IST 2011 | Tue Jul 26 17:00:00 IDT 2011
1667 | Comment for Temp.Work Design Submission | Sun Jun 19 08:00:00 IDT 2011 | Thu Jul 07 17:00:00 IDT 2011
1668 | Proposed Temp.Work Design Re-submission | Wed Aug 31 08:00:00 IDT 2011 | Tue Sep 06 17:00:00 IDT 2011
1669 | Proposed Temp.Work Design Approval | Wed Aug 31 08:00:00 IDT 2011 | Wed Sep 21 17:00:00 IDT 2011
1670 | Utilities Coordination | Mon Feb 28 08:00:00 IST 2011 | Tue Jan 31 17:00:00 IST 2012
1671 | Prepare & Submit Utilities Diversion Scheme | Mon Feb 28 08:00:00 IST 2011 | Thu Mar 31 17:00:00 IST 2011
1672 | Comment of Utilities Diversion Scheme | Fri Apr 01 08:00:00 IDT 2011 | Mon May 23 17:00:00 IDT 2011
1673 | Utilities Diversion Scheme Re-submission | Fri Apr 29 08:00:00 IDT 2011 | Tue Jan 31 17:00:00 IST 2012
1674 | Utilities Diversion Scheme Approval | Wed Aug 31 08:00:00 IDT 2011 | Tue Sep 27 17:00:00 IDT 2011
1675 | Preparation Excavation Permit | Mon Apr 11 08:00:00 IDT 2011 | Fri Jun 17 17:00:00 IDT 2011
1676 | Excavation Permit Issue | Mon Jun 13 08:00:00 IDT 2011 | Mon Jun 13 08:00:00 IDT 2011
1677 | Site Possession Application | Mon Feb 28 08:00:00 IST 2011 | Tue Mar 29 17:00:00 IST 2011
1678 | Prepare Site Possession to SLG | Mon Feb 28 08:00:00 IST 2011 | Wed Mar 09 17:00:00 IST 2011
1679 | SLG Comments and Approval | Mon Feb 28 08:00:00 IST 2011 | Tue Mar 29 17:00:00 IST 2011
1680 | Site Possession | Mon Feb 28 08:00:00 IST 2011 | Mon Feb 28 08:00:00 IST 2011
1681 | Utilities Diversion | Wed Aug 31 08:00:00 IDT 2011 | Mon Feb 13 17:00:00 IST 2012
1682 | Trial Trench & Record | Wed Aug 31 08:00:00 IDT 2011 | Fri Sep 23 17:00:00 IDT 2011
1683 | Permanently Divert Existing Storm Drain (SD201-SD205) | Sat Sep 24 08:00:00 IDT 2011 | Mon Nov 21 17:00:00 IST 2011
1684 | Permanently Divert Existing DN150 (FW201) | Tue Nov 22 08:00:00 IST 2011 | Mon Dec 19 17:00:00 IST 2011
1685 | Temp. Relocation of Fire Hydrant (FH1643) | Tue Dec 20 08:00:00 IST 2011 | Thu Jan 12 17:00:00 IST 2012
1686 | Temp.Slew 3nos. 400kV Cable w/Temp.Support (CLP201) | Fri Jan 13 08:00:00 IST 2012 | Mon Feb 13 17:00:00 IST 2012
1687 | Utilities Diversion | Wed Aug 31 08:00:00 IDT 2011 | Wed Aug 31 08:00:00 IDT 2011
1688 | Underpinning Works for Pile Cap at Grid 3 | Mon Feb 28 08:00:00 IST 2011 | Mon Sep 16 17:00:00 IDT 2013
1689 | Tree Transplant (by 801) | Mon Feb 28 08:00:00 IST 2011 | Mon Mar 14 17:00:00 IST 2011
1690 | Site Mobilization | Sat Sep 24 08:00:00 IDT 2011 | Fri Sep 30 17:00:00 IDT 2011
1691 | Const.Raking Mini-piles 23 nos. | Wed Aug 31 08:00:00 IDT 2011 | Fri Dec 16 17:00:00 IST 2011
1692 | Sheetpile Driving | Mon Jan 16 08:00:00 IST 2012 | Wed Feb 01 17:00:00 IST 2012
1693 | Waling Installation | Mon Jan 16 08:00:00 IST 2012 | Sat Jan 21 17:00:00 IST 2012
1694 | Excavation to FormationLevel(Underneath Exist'gPileCap) | Mon Jan 16 08:00:00 IST 2012 | Sat Jan 28 17:00:00 IST 2012
1695 | Pile Head Exposure | Mon Jan 16 08:00:00 IST 2012 | Wed Feb 15 17:00:00 IST 2012
1696 | Pile Cap & Column Construction | Mon Jan 16 08:00:00 IST 2012 | Tue Jan 31 17:00:00 IST 2012
1697 | Portal Beam Construction | Fri Aug 31 08:00:00 IDT 2012 | Thu Sep 06 17:00:00 IDT 2012
1698 | Concrete Curing | Fri Sep 07 08:00:00 IDT 2012 | Sat Oct 20 17:00:00 IST 2012
1699 | Install Shear Key | Sat Oct 20 08:00:00 IST 2012 | Mon Oct 29 17:00:00 IST 2012
1700 | Install Flat Jack | Sat Oct 20 08:00:00 IST 2012 | Mon Nov 12 17:00:00 IST 2012
1701 | Load Transfer | Tue Nov 13 08:00:00 IST 2012 | Mon Dec 03 17:00:00 IST 2012
1702 | Disconnect Existing Pier | Mon Dec 03 08:00:00 IST 2012 | Sat Dec 22 17:00:00 IST 2012
1703 | Adjust Jacking Force | Fri Aug 31 08:00:00 IDT 2012 | Fri Sep 14 17:00:00 IDT 2012
1704 | Infill grout for pier head and existing pile cap | Mon Sep 24 08:00:00 IST 2012 | Sat Sep 29 17:00:00 IST 2012
1705 | Backfilling & Reinstatement | Mon Sep 02 08:00:00 IDT 2013 | Mon Sep 16 17:00:00 IDT 2013
1706 | Grid 3 Underpinning, Loading Transfer & Disconnection (DT) | Sat Sep 24 08:00:00 IDT 2011 | Tue Jul 03 17:00:00 IDT 2012
1707 | Underpinning Works for Pile Cap at Grid 2 | Mon Jan 16 08:00:00 IST 2012 | Mon Sep 16 17:00:00 IDT 2013
1708 | Const.Raking Mini-piles 21nos. | Mon Jan 16 08:00:00 IST 2012 | Fri May 11 17:00:00 IDT 2012
1709 | Sheetpile Driving | Mon Jan 16 08:00:00 IST 2012 | Wed Feb 01 17:00:00 IST 2012
1710 | Waling Installation | Mon Jan 16 08:00:00 IST 2012 | Sat Jan 21 17:00:00 IST 2012
1711 | Excavation | Mon Jan 16 08:00:00 IST 2012 | Sat Jan 28 17:00:00 IST 2012
1712 | Pile Head Exposure | Sat Jan 28 08:00:00 IST 2012 | Fri Feb 24 17:00:00 IST 2012
1713 | Pile Cap Construciton | Mon Jan 16 08:00:00 IST 2012 | Wed Feb 01 17:00:00 IST 2012
1714 | Coulumns Construction (2nos.) | Mon Jan 16 08:00:00 IST 2012 | Mon Jan 30 17:00:00 IST 2012
1715 | Falsework Erection | Tue Sep 11 08:00:00 IDT 2012 | Fri Sep 21 17:00:00 IDT 2012
1716 | Portal Beam Construction | Fri Sep 21 08:00:00 IDT 2012 | Sat Oct 06 17:00:00 IST 2012
1717 | Concrete Curing | Sat Oct 06 08:00:00 IST 2012 | Fri Oct 19 17:00:00 IST 2012
1718 | Install Shear Key | Sat Oct 20 08:00:00 IST 2012 | Sat Oct 27 17:00:00 IST 2012
1719 | Install Flat Jack | Sat Oct 27 08:00:00 IST 2012 | Fri Nov 16 17:00:00 IST 2012
1720 | Load Transfer | Fri Nov 16 08:00:00 IST 2012 | Thu Dec 06 17:00:00 IST 2012
1721 | Disconnect Existing pier | Thu Dec 06 08:00:00 IST 2012 | Fri Dec 28 17:00:00 IST 2012
1722 | Adjust Jacking Force | Fri Aug 31 08:00:00 IDT 2012 | Fri Sep 14 17:00:00 IDT 2012
1723 | Infill grout for pier head and existing pile cap | Mon Sep 24 08:00:00 IST 2012 | Sat Sep 29 17:00:00 IST 2012
1724 | Backfilling & Reinstatement | Mon Sep 02 08:00:00 IDT 2013 | Mon Sep 16 17:00:00 IDT 2013
1725 | Grid 2 Underpinning,Loading Transfer & Disconnection (UT) | Mon Jan 16 08:00:00 IST 2012 | Wed Aug 08 17:00:00 IDT 2012
1726 | Underpinning Works for Pile Cap at Grid 1 | Mon Jan 16 08:00:00 IST 2012 | Wed Sep 25 17:00:00 IDT 2013
1727 | Const piles | Mon Jan 16 08:00:00 IST 2012 | Tue May 15 17:00:00 IDT 2012
1728 | Loading Test | Mon Jan 16 08:00:00 IST 2012 | Wed Feb 15 17:00:00 IST 2012
1729 | Sheetpile Driving | Mon Jan 16 08:00:00 IST 2012 | Tue Feb 14 17:00:00 IST 2012
1730 | Waling Installation | Mon Jan 16 08:00:00 IST 2012 | Wed Feb 08 17:00:00 IST 2012
1731 | Excavation | Fri Aug 31 08:00:00 IDT 2012 | Fri Sep 14 17:00:00 IDT 2012
1732 | Shotcrete | Sat Sep 15 08:00:00 IDT 2012 | Tue Oct 09 17:00:00 IST 2012
1733 | Pile Head Exposure | Wed Oct 10 08:00:00 IST 2012 | Wed Nov 07 17:00:00 IST 2012
1734 | Pile Cap & Cantilever Corbel Construction | Thu Nov 08 08:00:00 IST 2012 | Wed Dec 05 17:00:00 IST 2012
1735 | Concrete Curing (28d) | Wed Dec 05 08:00:00 IST 2012 | Tue Jan 01 17:00:00 IST 2013
1736 | Install Flat Jack | Wed Jan 02 08:00:00 IST 2013 | Tue Jan 22 17:00:00 IST 2013
1737 | Load Transfer | Tue Jan 22 08:00:00 IST 2013 | Thu Jan 31 17:00:00 IST 2013
1738 | Disconnect Existing Piles 6nos. | Thu Jan 31 08:00:00 IST 2013 | Sat Mar 02 17:00:00 IST 2013
1739 | Adjust Jacking Force | Sat Mar 02 08:00:00 IST 2013 | Fri Mar 22 17:00:00 IST 2013
1740 | Cast remaining part of pile cap | Sat Mar 23 08:00:00 IST 2013 | Thu Apr 18 17:00:00 IDT 2013
1741 | Backfilling & Reinstatement | Mon Sep 02 08:00:00 IDT 2013 | Wed Sep 25 17:00:00 IDT 2013
1742 | Grid 1 Underpinning,Loading Transfer & Disconnection (UT) | Mon Jan 16 08:00:00 IST 2012 | Wed Aug 01 17:00:00 IDT 2012
1743 | Completion | Tue Mar 06 08:00:00 IST 2012 | Mon Apr 02 17:00:00 IDT 2012
1744 | Prepare & Submit Draft As-built Drawings | Tue Mar 06 08:00:00 IST 2012 | Mon Apr 02 17:00:00 IDT 2012
1745 | Prepare & Submit As-built Drawings | Tue Mar 06 08:00:00 IST 2012 | Mon Apr 02 17:00:00 IDT 2012
1746 | RD1 Pile Removal | Mon Jan 16 08:00:00 IST 2012 | Fri Feb 03 17:00:00 IST 2012
1747 | RD1 Parallel Seismic | Mon Jan 16 08:00:00 IST 2012 | Tue Jan 17 17:00:00 IST 2012
1748 | Issuance of EI21 - Additional Investigation Drill hole above Nullah Deck at LCK | Mon Jan 16 17:00:00 IST 2012 | Mon Jan 16 17:00:00 IST 2012
1749 | Pile A - 1st Investigation Campaign | Mon Jan 16 08:00:00 IST 2012 | Thu Jan 19 17:00:00 IST 2012
1750 | Issuance of EI24 - Additional Investigation Drillhole at existing pile above Nullah Deck at LCK | Mon Jan 16 17:00:00 IST 2012 | Mon Jan 16 17:00:00 IST 2012
1751 | Pile B - 1st Investigation Campaign | Mon Jan 16 08:00:00 IST 2012 | Tue Jan 17 17:00:00 IST 2012
1752 | Issuance of EI31 - Additional attempts of vertical drillholes and inclined drillholes at existing Pile of RD1 | Mon Jan 16 17:00:00 IST 2012 | Mon Jan 16 17:00:00 IST 2012
1753 | Pile B - 2nd Investigation Campaign | Mon Jan 16 08:00:00 IST 2012 | Sat Jan 21 17:00:00 IST 2012
1754 | Pile B - 3rd Investigation Campaign (inclined holes) | Mon Jan 16 08:00:00 IST 2012 | Fri Feb 03 17:00:00 IST 2012
1755 | F3 Ground Treatment Works for HKIVE (Haking Wong) School | Wed Aug 31 08:00:00 IDT 2011 | Wed Oct 31 17:00:00 IST 2012
1756 | Method Statement Submission and Approval | Wed Aug 31 08:00:00 IDT 2011 | Wed Sep 28 17:00:00 IDT 2011
1757 | MS Preparation | Wed Aug 31 08:00:00 IDT 2011 | Fri Sep 23 17:00:00 IDT 2011
1758 | MS Submission to MTR | Wed Aug 31 08:00:00 IDT 2011 | Wed Aug 31 08:00:00 IDT 2011
1759 | MS Comment by MTR | Wed Aug 31 08:00:00 IDT 2011 | Tue Sep 27 17:00:00 IDT 2011
1760 | MS Re-submission Preparation | Wed Aug 31 08:00:00 IDT 2011 | Wed Sep 28 17:00:00 IDT 2011
1761 | MS Comment & Approval by MTR | Wed Aug 31 08:00:00 IDT 2011 | Tue Sep 27 17:00:00 IDT 2011
1762 | Issue for Construction | Wed Aug 31 08:00:00 IDT 2011 | Wed Aug 31 08:00:00 IDT 2011
1763 | Construction | Sun Jan 15 08:00:00 IST 2012 | Wed Oct 31 17:00:00 IST 2012
1764 | Access for HKIVE | Sun Jan 15 08:00:00 IST 2012 | Sun Jan 15 08:00:00 IST 2012
1765 | Site Preparation | Mon Jan 16 08:00:00 IST 2012 | Sat Jan 21 17:00:00 IST 2012
1766 | Sleeve Pipe Installation and Verticality Check | Mon Jan 16 08:00:00 IST 2012 | Fri Feb 10 17:00:00 IST 2012
1767 | Set up Grouting Machine | Mon Jan 16 08:00:00 IST 2012 | Wed Jan 18 17:00:00 IST 2012
1768 | Jet Grouting for HKIVE (Haking Wong) School | Mon Jan 16 08:00:00 IST 2012 | Fri Feb 10 17:00:00 IST 2012
1769 | De-mobilization | Fri Aug 31 08:00:00 IDT 2012 | Fri Sep 14 17:00:00 IDT 2012
1770 | Reinstatment (subjected to IVE) | Sat Sep 15 08:00:00 IDT 2012 | Wed Oct 31 17:00:00 IST 2012
1771 | F4 Cheung Sha Wan Cargo Pier-Remvoe Obstruct Pile | Sat Jan 08 08:00:00 IST 2011 | Wed May 08 17:00:00 IDT 2013
1772 | Method Statement Submission and Approval | Mon Feb 28 08:00:00 IST 2011 | Tue Jun 21 17:00:00 IDT 2011
1773 | MS Preparation | Mon Feb 28 08:00:00 IST 2011 | Tue Apr 05 17:00:00 IDT 2011
1774 | MS Submission to MTR | Wed Mar 23 17:00:00 IST 2011 | Wed Mar 23 17:00:00 IST 2011
1775 | MS Comment by MTR | Thu Mar 24 08:00:00 IST 2011 | Wed Apr 20 17:00:00 IDT 2011
1776 | MS Re-submission Preparation | Thu Apr 21 08:00:00 IDT 2011 | Sat May 14 17:00:00 IDT 2011
1777 | MS Comment & Approval by MTR | Wed May 25 08:00:00 IDT 2011 | Wed Jun 15 17:00:00 IDT 2011
1778 | Issue for Construction | Tue Jun 21 17:00:00 IDT 2011 | Tue Jun 21 17:00:00 IDT 2011
1779 | TTM Scheme Submission & Approval | Sat Jan 08 08:00:00 IST 2011 | Sun Aug 14 17:00:00 IDT 2011
1780 | Prepare TTM for footpah closure | Sat Jan 08 08:00:00 IST 2011 | Mon Feb 07 17:00:00 IST 2011
1781 | TTM Comment & Approval by Relevant Authorities | Sat Feb 12 08:00:00 IST 2011 | Sun Apr 10 17:00:00 IDT 2011
1782 | Notification to RMO | Mon Feb 28 08:00:00 IST 2011 | Sun Mar 06 17:00:00 IST 2011
1783 | XP Application & Approval | Mon Feb 28 08:00:00 IST 2011 | Wed Apr 06 17:00:00 IDT 2011
1784 | Implement TTM (Footpath) | Wed May 18 17:00:00 IDT 2011 | Wed May 18 17:00:00 IDT 2011
1785 | Prepare Temporary Traffic Management | Mon Feb 28 08:00:00 IST 2011 | Thu Mar 24 17:00:00 IST 2011
1786 | TTM reviewed by SLG | Sun Mar 27 08:00:00 IST 2011 | Mon May 23 17:00:00 IDT 2011
1787 | XP Application & Approval | Sat Apr 23 08:00:00 IDT 2011 | Fri Apr 29 17:00:00 IDT 2011
1788 | Notification to RMO | Tue Aug 09 08:00:00 IDT 2011 | Sun Aug 14 17:00:00 IDT 2011
1789 | Implement TTM (Road) | Wed Jul 06 17:00:00 IDT 2011 | Wed Jul 06 17:00:00 IDT 2011
1790 | Utilities Diversion (DT) | Sat Jan 29 08:00:00 IST 2011 | Mon Oct 17 17:00:00 IST 2011
1791 | Implement TTM | Sat Jan 29 08:00:00 IST 2011 | Wed Mar 09 17:00:00 IST 2011
1792 | Trial Trench to Expose Pile Head & Utilities | Tue Jun 21 08:00:00 IDT 2011 | Fri Jul 22 17:00:00 IDT 2011
1793 | Divert Existing 1400D Watermain (FW204) | Tue Jun 21 08:00:00 IDT 2011 | Wed Sep 07 17:00:00 IDT 2011
1794 | Divert 450D Saltwater Main (SW201) | Tue Jun 21 08:00:00 IDT 2011 | Mon Jul 18 17:00:00 IDT 2011
1795 | Divert 1200D Stormwater Main (SD207) | Wed Aug 31 08:00:00 IDT 2011 | Mon Oct 17 17:00:00 IST 2011
1796 | Divert 225D Stormwater Drain (SD208) | Tue Jun 21 08:00:00 IDT 2011 | Fri Aug 26 17:00:00 IDT 2011
1797 | Stage 1 | Sat Jan 08 08:00:00 IST 2011 | Mon Mar 19 17:00:00 IST 2012
1798 | Access Date for Works Area 11.22 | Mon Feb 28 08:00:00 IST 2011 | Mon Feb 28 08:00:00 IST 2011
1799 | Tree Transplant Complete by 801 Designated Contractor | Mon Feb 28 08:00:00 IST 2011 | Mon Feb 28 08:00:00 IST 2011
1800 | Survey Existing Piles & Underground Utilities | Sat Jan 08 08:00:00 IST 2011 | Fri May 13 17:00:00 IDT 2011
1801 | Expose the Existing Pile Head | Sat May 21 08:00:00 IDT 2011 | Fri Nov 25 17:00:00 IST 2011
1802 | Expose and Verification of Pile 24E (DT) | Fri Jan 20 08:00:00 IST 2012 | Sat Jan 28 17:00:00 IST 2012
1803 | Remove Existing Vertical Pile 24H (DT) | Tue Jun 21 08:00:00 IDT 2011 | Mon Aug 29 17:00:00 IDT 2011
1804 | Backfill Existing Pile 24H | Sat Jul 16 08:00:00 IDT 2011 | Thu Jul 21 17:00:00 IDT 2011
1805 | Remove Existing Raking Pile 24G (DT) | Tue Jun 21 08:00:00 IDT 2011 | Wed Jul 27 17:00:00 IDT 2011
1806 | Backfill Existing Pile 24G | Wed Aug 31 08:00:00 IDT 2011 | Fri Sep 02 17:00:00 IDT 2011
1807 | Remove Existing Raking Pile 23F (DT) | Wed Aug 31 08:00:00 IDT 2011 | Fri Oct 07 17:00:00 IST 2011
1808 | Backfill Existing Pile 23F | Fri Jan 27 08:00:00 IST 2012 | Sat Jan 28 17:00:00 IST 2012
1809 | Remove Existing Vertical Pile 23E (DT) | Mon Sep 12 08:00:00 IDT 2011 | Sat Jan 14 17:00:00 IST 2012
1810 | Backfill Existing Pile 23E | Tue Feb 07 08:00:00 IST 2012 | Wed Feb 08 17:00:00 IST 2012
1811 | Remove Existing Raking Pile 24F (DT) | Fri Feb 10 08:00:00 IST 2012 | Tue Mar 06 17:00:00 IST 2012
1812 | Backfill Existing Pile 24F | Sat Mar 17 08:00:00 IST 2012 | Mon Mar 19 17:00:00 IST 2012
1813 | Utilities Diversion (UT) | Sat Jan 08 08:00:00 IST 2011 | Fri Dec 21 17:00:00 IST 2012
1814 | Implement TTM (Footpath Closure) | Sat Jan 08 08:00:00 IST 2011 | Mon Feb 21 17:00:00 IST 2011
1815 | Trial Trench to Expose U/G Utilities | Tue Jun 21 08:00:00 IDT 2011 | Thu Jul 07 17:00:00 IDT 2011
1816 | Divert Existing Gas Main 315D & 400D (GAS204&205) | Wed Aug 31 08:00:00 IDT 2011 | Fri Sep 23 17:00:00 IDT 2011
1817 | Slew TelecomCable(CATV205+HGC203+WTT204+PCCW202) | Fri Jan 27 08:00:00 IST 2012 | Tue Feb 07 17:00:00 IST 2012
1818 | Slew CLP Cable (11kV-CLP213) | Fri Jan 27 08:00:00 IST 2012 | Thu Feb 09 17:00:00 IST 2012
1819 | Slew CLP Cable (400kV-CLP214) | Thu Nov 22 08:00:00 IST 2012 | Fri Dec 21 17:00:00 IST 2012
1820 | Stage 2 | Tue Jun 21 08:00:00 IDT 2011 | Wed May 08 17:00:00 IDT 2013
1821 | Remove Existing Pile 23G (UT) | Tue Jun 21 08:00:00 IDT 2011 | Mon Jul 04 17:00:00 IDT 2011
1822 | Backfill Existing Pile 23G | Wed Aug 31 08:00:00 IDT 2011 | Thu Sep 01 17:00:00 IDT 2011
1823 | Remove Existing Pile 20E (UT) | Thu Dec 13 08:00:00 IST 2012 | Fri Jan 18 17:00:00 IST 2013
1824 | Backfill Existing Pile 20E | Sat Jan 19 08:00:00 IST 2013 | Mon Jan 21 17:00:00 IST 2013
1825 | Remove Existing Pile 23H (UT) | Thu Nov 22 08:00:00 IST 2012 | Sat Dec 08 17:00:00 IST 2012
1826 | Backfill Existing Pile 23H | Mon Dec 10 08:00:00 IST 2012 | Tue Dec 11 17:00:00 IST 2012
1827 | Remove Existing Pile 21L (UT) | Sat Apr 14 08:00:00 IDT 2012 | Tue Jul 17 17:00:00 IDT 2012
1828 | Backfill Existing Pile 21L | Mon Nov 19 08:00:00 IST 2012 | Tue Nov 20 17:00:00 IST 2012
1829 | Remove Existing Pile 20J (UT) | Wed Jan 23 08:00:00 IST 2013 | Thu Feb 28 17:00:00 IST 2013
1830 | Backfill Existing Pile 20J | Fri Mar 01 08:00:00 IST 2013 | Sat Mar 02 17:00:00 IST 2013
1831 | Remove Existing Pile 19E (UT) | Tue Mar 05 08:00:00 IST 2013 | Sat Apr 13 17:00:00 IDT 2013
1832 | Backfill Existing Pile 19E | Mon Apr 15 08:00:00 IDT 2013 | Tue Apr 16 17:00:00 IDT 2013
1833 | Reinstatement of Slewed CLP Cable (400kV - CLP214) | Tue Apr 02 08:00:00 IDT 2013 | Wed May 08 17:00:00 IDT 2013
1834 | Reinstatement works
1835 | Completion | Fri Jan 13 08:00:00 IST 2012 | Mon Feb 13 17:00:00 IST 2012
1836 | Prepare & Submit Draft As-built Drawings | Fri Jan 13 08:00:00 IST 2012 | Mon Feb 13 17:00:00 IST 2012
1837 | Prepare & Submit As-built Drawings | Fri Jan 13 08:00:00 IST 2012 | Mon Feb 13 17:00:00 IST 2012
1838 | F5 Pile Removal for Demolished FMO Market Pier B | Mon Feb 28 08:00:00 IST 2011 | Thu Jun 05 17:00:00 IDT 2014
1839 | Temp. Works Design Submission | Mon Jun 20 08:00:00 IDT 2011 | Mon Jul 18 08:00:00 IDT 2011
1840 | Temp. Works Design Preparation | Mon Jun 20 08:00:00 IDT 2011 | Sun Jul 17 17:00:00 IDT 2011
1841 | Temp. Works Design Submit to MTR | Mon Jul 18 08:00:00 IDT 2011 | Mon Jul 18 08:00:00 IDT 2011
1842 | Temp. Works Design Comment by MTR | Mon Jun 20 08:00:00 IDT 2011 | Sun Jul 17 17:00:00 IDT 2011
1843 | Temp. Works Design Re-submission Preparation | Mon Jun 20 08:00:00 IDT 2011 | Mon Jul 11 17:00:00 IDT 2011
1844 | Temp. Works Design Comment & Approval by MTR | Mon Jun 20 08:00:00 IDT 2011 | Sun Jul 17 17:00:00 IDT 2011
1845 | Issue for Construction | Mon Jun 20 08:00:00 IDT 2011 | Mon Jun 20 08:00:00 IDT 2011
1846 | Method Statement Submission and Approval | Mon Feb 28 08:00:00 IST 2011 | Tue Jun 14 17:00:00 IDT 2011
1847 | MS Preparation | Mon Feb 28 08:00:00 IST 2011 | Thu Mar 31 17:00:00 IST 2011
1848 | MS Submission to MTR | Wed Mar 23 17:00:00 IST 2011 | Wed Mar 23 17:00:00 IST 2011
1849 | MS Comment by MTR | Thu Mar 24 08:00:00 IST 2011 | Sun Apr 03 17:00:00 IDT 2011
1850 | MS Re-submission Preparation | Thu Apr 21 08:00:00 IDT 2011 | Fri Apr 29 17:00:00 IDT 2011
1851 | MS Comment & Approval by MTR | Wed May 18 08:00:00 IDT 2011 | Mon May 30 17:00:00 IDT 2011
1852 | Issue for Construction | Tue Jun 14 17:00:00 IDT 2011 | Tue Jun 14 17:00:00 IDT 2011
1853 | TTM Scheme Submission & Approval | Mon Feb 28 08:00:00 IST 2011 | Sun May 29 17:00:00 IDT 2011
1854 | Prepare Temporary Traffic Management | Mon Feb 28 08:00:00 IST 2011 | Mon Mar 14 17:00:00 IST 2011
1855 | TTM reviewed by SLG | Sat Mar 26 08:00:00 IST 2011 | Sun Apr 24 17:00:00 IDT 2011
1856 | Resubmit TTM | Mon Feb 28 08:00:00 IST 2011 | Mon Feb 28 17:00:00 IST 2011
1857 | TTM reviewed by SLG | Sat Apr 30 08:00:00 IDT 2011 | Sun May 29 17:00:00 IDT 2011
1858 | Notification to RMO | Tue May 24 08:00:00 IDT 2011 | Fri May 27 17:00:00 IDT 2011
1859 | XP Application & Approval | Mon Apr 25 08:00:00 IDT 2011 | Tue May 24 17:00:00 IDT 2011
1860 | Implement TTM | Mon Feb 28 08:00:00 IST 2011 | Mon Feb 28 08:00:00 IST 2011
1861 | Construction | Mon Feb 28 08:00:00 IST 2011 | Thu Jun 05 17:00:00 IDT 2014
1862 | Acccess Dates for Works Area 11.27 | Mon Feb 28 08:00:00 IST 2011 | Mon Feb 28 08:00:00 IST 2011
1863 | TTM Implementation | Mon Feb 28 08:00:00 IST 2011 | Mon Mar 28 17:00:00 IST 2011
1864 | Relocation of Toilet/Bus Operator Office | Mon Feb 28 08:00:00 IST 2011 | Sat Mar 26 17:00:00 IST 2011
1865 | Bus Stop Modification Stage 1 | Mon Feb 28 08:00:00 IST 2011 | Mon Mar 14 17:00:00 IST 2011
1866 | Bus Stop Modification Stage 2 | Mon Feb 28 08:00:00 IST 2011 | Fri Mar 04 17:00:00 IST 2011
1867 | Road Kerb Removal | Mon Feb 28 08:00:00 IST 2011 | Fri Mar 11 17:00:00 IST 2011
1868 | Trial Trench for Expose U/G Utilities | Mon Feb 28 08:00:00 IST 2011 | Tue Mar 22 17:00:00 IST 2011
1869 | Expose the Existing Pile Heads | Thu Apr 21 08:00:00 IDT 2011 | Wed May 18 17:00:00 IDT 2011
1870 | Backfill | Mon Feb 28 08:00:00 IST 2011 | Sat Mar 05 17:00:00 IST 2011
1871 | 1 Vertical Pile Removal UT(3G) | Mon Feb 28 08:00:00 IST 2011 | Wed Mar 02 17:00:00 IST 2011
1872 | 1 Vertical Pile Removal UT(1G) | Mon Feb 28 08:00:00 IST 2011 | Thu Mar 03 17:00:00 IST 2011
1873 | 1 Vertical Pile Removal UT(3H) | Wed Aug 31 08:00:00 IDT 2011 | Thu Sep 15 17:00:00 IDT 2011
1874 | 1 Vertical Pile Removal UT(1H) | Wed Aug 31 08:00:00 IDT 2011 | Thu Sep 15 17:00:00 IDT 2011
1875 | 1 Raking Pile Removal UT (2Fa) | Wed Aug 31 08:00:00 IDT 2011 | Mon Sep 26 17:00:00 IDT 2011
1876 | 4 Raking Pile Removal DT(2Ja,2Ha,2Hb & 2Gb) | Wed Aug 31 08:00:00 IDT 2011 | Wed Dec 07 17:00:00 IST 2011
1877 | PTI Reinstatement | Fri Feb 21 08:00:00 IST 2014 | Thu Jun 05 17:00:00 IDT 2014
1878 | FMO Pier B Piles Removal (4nos.) (DT) | Fri May 27 08:00:00 IDT 2011 | Sun Jun 24 17:00:00 IDT 2012
1879 | FMO Pier B Piles Removal (5nos.) (UT) | Fri May 27 08:00:00 IDT 2011 | Fri Feb 17 17:00:00 IST 2012
1880 | Completion | Thu Mar 15 08:00:00 IST 2012 | Mon Apr 16 17:00:00 IDT 2012
1881 | Prepare & Submit Draft As-built Drawings (PTI) | Thu Mar 15 08:00:00 IST 2012 | Mon Apr 16 17:00:00 IDT 2012
1882 | Prepare & Submit As-built Drawings (PTI) | Thu Mar 15 08:00:00 IST 2012 | Mon Apr 16 17:00:00 IDT 2012
1883 | F6 Sham Shui Po Ferry Pier - Pile removal | Mon Feb 28 08:00:00 IST 2011 | Thu Nov 07 17:00:00 IST 2013
1884 | Temp. Works Design Submission | Mon Feb 28 08:00:00 IST 2011 | Tue Jul 19 17:00:00 IDT 2011
1885 | Temp. Works Design Preparation | Mon Feb 28 08:00:00 IST 2011 | Wed Mar 30 17:00:00 IST 2011
1886 | Temp. Works Design Submit to MTR | Mon Mar 28 08:00:00 IST 2011 | Mon Mar 28 08:00:00 IST 2011
1887 | Temp. Works Design Comment by MTR | Mon Mar 28 08:00:00 IST 2011 | Tue Jul 19 17:00:00 IDT 2011
1888 | Temp. Works Design Re-submission Preparation | Tue Apr 26 08:00:00 IDT 2011 | Fri May 20 17:00:00 IDT 2011
1889 | Temp. Works Design Comment & Approval by MTR | Thu May 19 08:00:00 IDT 2011 | Sat Jun 04 17:00:00 IDT 2011
1890 | Issue for Construction | Wed Jun 15 17:00:00 IDT 2011 | Wed Jun 15 17:00:00 IDT 2011
1891 | Method Statement Submission and Approval | Mon Feb 28 08:00:00 IST 2011 | Wed Aug 31 08:00:00 IDT 2011
1892 | MS Submission Preparation | Wed Mar 16 08:00:00 IST 2011 | Wed Apr 06 17:00:00 IDT 2011
1893 | MS Submission to MTR | Wed Apr 13 17:00:00 IDT 2011 | Wed Apr 13 17:00:00 IDT 2011
1894 | MS Comment by MTR | Mon Feb 28 08:00:00 IST 2011 | Wed Mar 09 17:00:00 IST 2011
1895 | MS Re-submission Preparation | Mon Feb 28 08:00:00 IST 2011 | Sat Apr 16 17:00:00 IDT 2011
1896 | MS Comment & Approval by MTR | Mon Feb 28 08:00:00 IST 2011 | Mon Aug 01 17:00:00 IDT 2011
1897 | Issue for Construction | Wed Aug 31 08:00:00 IDT 2011 | Wed Aug 31 08:00:00 IDT 2011
1898 | TTM Scheme Submission & Approval | Mon Feb 28 08:00:00 IST 2011 | Mon Aug 08 17:00:00 IDT 2011
1899 | Prepare Temp.Traffic Mgmt for Tree Transplant | Mon Feb 28 08:00:00 IST 2011 | Wed Apr 13 17:00:00 IDT 2011
1900 | TTM Comment & Approval by Relevant Authorities | Thu Apr 14 08:00:00 IDT 2011 | Fri May 13 17:00:00 IDT 2011
1901 | Notification to RMO | Fri Jul 08 08:00:00 IDT 2011 | Mon Aug 08 17:00:00 IDT 2011
1902 | Implement TTM | Tue Jul 19 17:00:00 IDT 2011 | Tue Jul 19 17:00:00 IDT 2011
1903 | Stage 0 | Mon Feb 28 08:00:00 IST 2011 | Thu Nov 10 17:00:00 IST 2011
1904 | Group B TreeTransplant(T9746,U0019-24)Preparat'n | Wed Jul 20 08:00:00 IDT 2011 | Mon Aug 29 17:00:00 IDT 2011
1905 | Group D Tree Transplant (U0023) Preparation | Wed Jul 20 08:00:00 IDT 2011 | Mon Aug 29 17:00:00 IDT 2011
1906 | Access Date for Works Area 11.21 | Mon Feb 28 08:00:00 IST 2011 | Mon Feb 28 08:00:00 IST 2011
1907 | Stage 0 TTA | Mon Feb 28 08:00:00 IST 2011 | Wed Mar 30 17:00:00 IST 2011
1908 | Tree Transplanting | Thu Oct 06 08:00:00 IST 2011 | Thu Nov 10 17:00:00 IST 2011
1909 | Kerb & Footpath Removal | Tue Mar 29 08:00:00 IST 2011 | Wed May 11 17:00:00 IDT 2011
1910 | Pavement Excavation and Expose Underground Utilities | Wed Apr 06 08:00:00 IDT 2011 | Wed May 18 17:00:00 IDT 2011
1911 | Agree Diversion Scheme with CLP for 132kV | Mon Jun 20 08:00:00 IDT 2011 | Fri Jun 24 17:00:00 IDT 2011
1912 | Stage 0 Enabling Work | Mon Feb 28 08:00:00 IST 2011 | Mon Aug 29 17:00:00 IDT 2011
1913 | Stage 1 | Sun Jun 19 08:00:00 IDT 2011 | Sat Nov 02 17:00:00 IST 2013
1914 | Extended TTMs Application & Approval | Mon Jun 20 08:00:00 IDT 2011 | Thu Jun 30 17:00:00 IDT 2011
1915 | Stage 1 Extended TTMs Implementation | Sun Jun 19 08:00:00 IDT 2011 | Fri Jul 15 17:00:00 IDT 2011
1916 | Remove Retaining Wall for Watermain Diversion | Tue Jun 21 08:00:00 IDT 2011 | Tue Aug 09 17:00:00 IDT 2011
1917 | Prepare Trench for 132kV Diversion | Sat Jul 02 08:00:00 IDT 2011 | Fri Aug 12 17:00:00 IDT 2011
1918 | Divert 1400D Fresh Watermain (FW205) | Wed Aug 31 08:00:00 IDT 2011 | Thu Dec 22 17:00:00 IST 2011
1919 | Divert 600D Salt Watermain (SW202) | Sun Jan 15 08:00:00 IST 2012 | Tue Mar 13 17:00:00 IST 2012
1920 | Joint Bay Construction & Laying New Cable by CLP (132kV Diversion) | Sun Jan 15 08:00:00 IST 2012 | Fri Feb 17 17:00:00 IST 2012
1921 | Power Outage & Connection by CLP (132kV Diversion) | Sun Jan 15 08:00:00 IST 2012 | Wed Mar 07 17:00:00 IST 2012
1922 | Mobilization for Pile Removal | Fri Aug 31 08:00:00 IDT 2012 | Tue Sep 04 17:00:00 IDT 2012
1923 | Remove the Existing Vertical Piles @ GL.1 - DT(11nos.) | Mon Sep 03 08:00:00 IDT 2012 | Sat Nov 10 17:00:00 IST 2012
1924 | Remove the Existing Vertical Piles @ GL.2 - DT(11nos.) | Wed Sep 05 08:00:00 IDT 2012 | Tue Nov 13 17:00:00 IST 2012
1925 | Agree with WSD for reinstatement of diverted 1400D FW main (FW205) | Wed Nov 14 08:00:00 IST 2012 | Mon Feb 04 17:00:00 IST 2013
1926 | Reinstate diverted 1400D FW main (FW205) | Thu Feb 28 08:00:00 IST 2013 | Wed Mar 27 17:00:00 IST 2013
1927 | Temporary Road Reinstatement | Sat Oct 12 08:00:00 IDT 2013 | Sat Nov 02 17:00:00 IST 2013
1928 | Stage 1 Piles Removal (22nos.) (DT) | Sun Jun 19 08:00:00 IDT 2011 | Sat May 26 17:00:00 IDT 2012
1929 | Stage 2 | Wed Nov 28 08:00:00 IST 2012 | Thu Nov 07 17:00:00 IST 2013
1930 | Stage 2 TTM Implementation | Fri Mar 29 08:00:00 IDT 2013 | Sun Apr 14 17:00:00 IDT 2013
1931 | Divert 1200D Foul Sewer Drain (FD202) | Mon Apr 15 08:00:00 IDT 2013 | Mon May 13 17:00:00 IDT 2013
1932 | Remove the Existing 12 Piles (UT) @GL.4 | Tue May 14 08:00:00 IDT 2013 | Wed Jul 31 17:00:00 IDT 2013
1933 | Divert 900D Stormwater Drain (SD214) | Mon Aug 05 08:00:00 IDT 2013 | Wed Sep 04 17:00:00 IDT 2013
1934 | Remove the Existing 10 Piles (UT) @GL.5 | Wed Nov 28 08:00:00 IST 2012 | Mon Jan 28 17:00:00 IST 2013
1935 | Permanent Road Reinstatement | Mon Jan 07 08:00:00 IST 2013 | Thu May 09 17:00:00 IDT 2013
1936 | Stage 2 Piles Removal (20nos.) (UT) | Fri Mar 29 08:00:00 IDT 2013 | Thu Nov 07 17:00:00 IST 2013
1937 | Completion | Wed May 02 08:00:00 IDT 2012 | Tue May 29 17:00:00 IDT 2012
1938 | Prepare & Submit Draft As-built Drawings | Wed May 02 08:00:00 IDT 2012 | Tue May 29 17:00:00 IDT 2012
1939 | Prepare & Submit As-built Drawings | Wed May 02 08:00:00 IDT 2012 | Tue May 29 17:00:00 IDT 2012
1940 | Cost Centre G - Utility Diversion Works | Sat Aug 14 08:00:00 IDT 2010 | Sat Oct 10 17:00:00 IDT 2015
1941 | IPS Milestones | Sun Mar 27 17:00:00 IST 2011 | Tue Oct 29 17:00:00 IST 2013
1942 | General | Sun Mar 27 17:00:00 IST 2011 | Tue Oct 29 17:00:00 IST 2013
1943 | Complete Temp. Diversion of Box Culvert FS1 | Fri Sep 30 17:00:00 IDT 2011 | Fri Sep 30 17:00:00 IDT 2011
1944 | Complete Thrust Block for North Temp.DSD Rising Main | Sun Mar 27 17:00:00 IST 2011 | Sun Mar 27 17:00:00 IST 2011
1945 | Remove Pile for DSD Rising Main adj. TBM Launch Shaft | Sun Jan 15 08:00:00 IST 2012 | Sun Jan 15 08:00:00 IST 2012
1946 | Complete Removal of 60% of Obstruction Piles for WD1 | Fri Aug 31 08:00:00 IDT 2012 | Fri Aug 31 08:00:00 IDT 2012
1947 | Remove Barrettes for DSD Culvert NC1 | Fri Mar 23 17:00:00 IST 2012 | Fri Mar 23 17:00:00 IST 2012
1948 | Complete Box Culvert WD1 Reinstate Wk & Handover | Tue Oct 29 17:00:00 IST 2013 | Tue Oct 29 17:00:00 IST 2013
1949 | G4 DSD Culvert WD1 Potential Obstruction | Tue Dec 14 08:00:00 IST 2010 | Tue Oct 29 17:00:00 IST 2013
1950 | Obstruction Removal at 1.1m Dia.Sewer Pipe Area (UT) | Tue Dec 14 08:00:00 IST 2010 | Tue Dec 14 08:00:00 IST 2010
1951 | Obstruction Removal at 1.1m Dia.Sewer Pipe Area (DT) | Fri Jul 22 08:00:00 IDT 2011 | Wed Apr 18 17:00:00 IDT 2012
1952 | Obstruction Removal at 1.8m Dia.Sewer Pipe Area (DT) | Wed Aug 31 08:00:00 IDT 2011 | Mon May 28 17:00:00 IDT 2012
1953 | WD1 Piles Removal (P1,P3 & P9) (UT) | Sun Mar 13 08:00:00 IST 2011 | Thu Jul 07 17:00:00 IDT 2011
1954 | WD1Pre-bored Socket H-piles & Pile Cap (5nos..) | Tue Jun 21 08:00:00 IDT 2011 | Sun Oct 23 17:00:00 IST 2011
1955 | WD1 Piles Removal (P4,P6,P7 & P8) (UT) | Fri Apr 13 08:00:00 IDT 2012 | Wed Feb 27 17:00:00 IST 2013
1956 | Diversion Scheme Submission | Mon Feb 28 08:00:00 IST 2011 | Mon Aug 01 17:00:00 IDT 2011
1957 | Prepare Diversion Scheme Proposal | Mon Feb 28 08:00:00 IST 2011 | Tue Apr 26 17:00:00 IDT 2011
1958 | Comment of Diversion Scheme by DSD | Tue Apr 12 08:00:00 IDT 2011 | Sun Apr 17 17:00:00 IDT 2011
1959 | Proposed Diversion Scheme Re-subm'n | Wed May 11 08:00:00 IDT 2011 | Thu Jun 02 17:00:00 IDT 2011
1960 | Proposed Diversion Scheme Approval by DSD | Wed May 25 08:00:00 IDT 2011 | Mon Aug 01 17:00:00 IDT 2011
1961 | Method Statement Submission and Approval | Sat Jan 08 08:00:00 IST 2011 | Fri May 13 17:00:00 IDT 2011
1962 | MS Preparation for WDI Obstruction Removal | Sat Jan 08 08:00:00 IST 2011 | Tue Feb 08 17:00:00 IST 2011
1963 | MS Submission to MTR | Thu Mar 03 17:00:00 IST 2011 | Thu Mar 03 17:00:00 IST 2011
1964 | MS Comment by MTR | Fri Mar 04 08:00:00 IST 2011 | Tue Mar 22 17:00:00 IST 2011
1965 | MS Re-submission Preparation | Fri Apr 01 08:00:00 IDT 2011 | Fri Apr 08 17:00:00 IDT 2011
1966 | MS Comment & Approval by MTR | Sat Apr 16 08:00:00 IDT 2011 | Sun May 08 17:00:00 IDT 2011
1967 | Issue for Construction | Fri May 13 17:00:00 IDT 2011 | Fri May 13 17:00:00 IDT 2011
1968 | Temp.works Design Submission | Mon Feb 28 08:00:00 IST 2011 | Mon Aug 01 17:00:00 IDT 2011
1969 | Prepare Temp.Gate & Working Platform Proposal | Mon Feb 28 08:00:00 IST 2011 | Tue Apr 26 17:00:00 IDT 2011
1970 | Comment of Temp.Gate& Working Platform byRDO/DSD | Tue Apr 12 08:00:00 IDT 2011 | Sun Apr 17 17:00:00 IDT 2011
1971 | Proposed Temp.Gate & Working Platform Re-subm'n | Wed May 11 08:00:00 IDT 2011 | Thu Jun 02 17:00:00 IDT 2011
1972 | Proposed Temp.Gate& WorkingPlatf'mApp'l /RDO&DSD | Wed May 25 08:00:00 IDT 2011 | Mon Aug 01 17:00:00 IDT 2011
1973 | TTM Scheme Submission & Approval | Sat Jan 08 08:00:00 IST 2011 | Sat Jul 09 17:00:00 IDT 2011
1974 | Prepare Temp.Pedestrian Walkway Diversion Scheme | Sat Jan 08 08:00:00 IST 2011 | Fri Jan 21 17:00:00 IST 2011
1975 | Temp.Pedestrian Walkway Approval by SLG/HyD/etc. | Sat Jan 22 08:00:00 IST 2011 | Sun Apr 03 17:00:00 IDT 2011
1976 | Notification to RMO | Sat Apr 16 08:00:00 IDT 2011 | Thu Apr 21 17:00:00 IDT 2011
1977 | Implement for Temp.Pederstrian Walkway | Wed Apr 27 17:00:00 IDT 2011 | Wed Apr 27 17:00:00 IDT 2011
1978 | Prepare Temporary Traffic Management | Sat Jan 08 08:00:00 IST 2011 | Tue Feb 08 17:00:00 IST 2011
1979 | TTM reviewed by SLG | Wed Feb 09 08:00:00 IST 2011 | Thu Mar 03 17:00:00 IST 2011
1980 | Resubmit TTM | Wed May 04 08:00:00 IDT 2011 | Wed May 11 17:00:00 IDT 2011
1981 | TTM reviewed by SLG | Fri May 13 08:00:00 IDT 2011 | Sat Jun 11 17:00:00 IDT 2011
1982 | Notification to RMO | Sat Jun 11 08:00:00 IDT 2011 | Sat Jul 09 17:00:00 IDT 2011
1983 | XP Application & Approval | Mon Feb 28 08:00:00 IST 2011 | Mon Mar 14 17:00:00 IST 2011
1984 | Implement TTM | Tue Jun 28 17:00:00 IDT 2011 | Tue Jun 28 17:00:00 IDT 2011
1985 | Prepare Temp.TrafficManagem't for TreeTransplant | Sat Jan 08 08:00:00 IST 2011 | Tue Feb 08 17:00:00 IST 2011
1986 | TTM reviewed by SLG | Wed Feb 09 08:00:00 IST 2011 | Mon May 23 17:00:00 IDT 2011
1987 | Notification to RMO | Thu May 05 08:00:00 IDT 2011 | Sun May 08 17:00:00 IDT 2011
1988 | Proposed Culvert New Founding System | Mon Feb 28 08:00:00 IST 2011 | Tue Sep 27 17:00:00 IDT 2011
1989 | Prepare & Submit Culvert New Founding System | Mon Feb 28 08:00:00 IST 2011 | Fri Mar 11 17:00:00 IST 2011
1990 | Comment of Culvert New Founding System byRDO/DSD | Tue Apr 12 08:00:00 IDT 2011 | Tue Apr 26 17:00:00 IDT 2011
1991 | Culvert New Founding System Re-submission | Tue May 24 08:00:00 IDT 2011 | Tue Sep 27 17:00:00 IDT 2011
1992 | Culvert New Founding System Approval by RDO/DSD | Wed Jun 08 08:00:00 IDT 2011 | Wed Jul 27 17:00:00 IDT 2011
1993 | Site Possession Application | Mon Feb 28 08:00:00 IST 2011 | Mon Jun 06 08:00:00 IDT 2011
1994 | Apply Site Possession to SLG | Mon Feb 28 08:00:00 IST 2011 | Sat Mar 05 17:00:00 IST 2011
1995 | SLG Comments & Approval | Sun Mar 06 08:00:00 IST 2011 | Tue Mar 29 17:00:00 IST 2011
1996 | TGLA Comments & Approval | Tue Mar 29 08:00:00 IST 2011 | Sat Jun 04 17:00:00 IDT 2011
1997 | Site Possession | Mon Jun 06 08:00:00 IDT 2011 | Mon Jun 06 08:00:00 IDT 2011
1998 | Utilities Coordination | Mon Feb 28 08:00:00 IST 2011 | Thu Jun 30 17:00:00 IDT 2011
1999 | Prepare & Submit Utilities Diversion Scheme | Mon Feb 28 08:00:00 IST 2011 | Thu Mar 31 17:00:00 IST 2011
2000 | Comment of Utilities Diversion Scheme | Fri Apr 01 08:00:00 IDT 2011 | Thu Apr 28 17:00:00 IDT 2011
2001 | Utilities Diversion Scheme Re-submission | Fri Apr 29 08:00:00 IDT 2011 | Sat May 14 17:00:00 IDT 2011
2002 | Utilities Diversion Scheme Approval | Sun May 15 08:00:00 IDT 2011 | Thu Jun 30 17:00:00 IDT 2011
2003 | Preparation Excavation Permit | Mon Apr 11 08:00:00 IDT 2011 | Fri Jun 10 17:00:00 IDT 2011
2004 | Excavation Permit Issue | Mon Jun 13 08:00:00 IDT 2011 | Mon Jun 13 08:00:00 IDT 2011
2005 | Power Cable & Fresh Water Main | Sat Jan 08 08:00:00 IST 2011 | Wed Oct 31 17:00:00 IST 2012
2006 | GI works for WD1 | Sat Jan 08 08:00:00 IST 2011 | Wed Jun 01 17:00:00 IDT 2011
2007 | Site Mobilization | Tue Jun 07 08:00:00 IDT 2011 | Wed Jul 06 17:00:00 IDT 2011
2008 | Temp.Working Platform | Thu Jun 23 08:00:00 IDT 2011 | Tue Aug 23 17:00:00 IDT 2011
2009 | Temp.Traffic Diversion(Pedestrian Walkway) | Mon Feb 28 08:00:00 IST 2011 | Fri Mar 11 17:00:00 IST 2011
2010 | Trial Trench & Record | Mon Jun 13 08:00:00 IDT 2011 | Sat Aug 20 17:00:00 IDT 2011
2011 | Slew 400KV Cable(CLP204)& 2Sets of 11KV(CLP205) | Sat Jul 02 08:00:00 IDT 2011 | Mon Oct 10 17:00:00 IST 2011
2012 | Slew Tele Cables (PCCW204+HKBN201) | Wed Aug 24 08:00:00 IDT 2011 | Mon Aug 29 17:00:00 IDT 2011
2013 | Cosnt.Temp.300mm dia.WaterMain (FW203) | Mon Feb 20 08:00:00 IST 2012 | Tue Mar 27 17:00:00 IST 2012
2014 | Water Main Diversion (FW203) | Mon Jan 16 08:00:00 IST 2012 | Mon Jan 16 08:00:00 IST 2012
2015 | Slew 400KV & 2 Sets 11KV Cables Reinstatement | Sat Sep 01 08:00:00 IDT 2012 | Wed Oct 17 17:00:00 IST 2012
2016 | Remove Temp.Support for 400KV &11KV Cables | Wed Oct 17 08:00:00 IST 2012 | Wed Oct 31 17:00:00 IST 2012
2017 | Reinstate 300mmdia Fresh Water Main (FW203) | Sat Sep 01 08:00:00 IDT 2012 | Wed Oct 10 17:00:00 IST 2012
2018 | Remove Temp.300mm dia.Fresh Water Meter (FW203) | Thu Oct 11 08:00:00 IST 2012 | Thu Oct 25 17:00:00 IST 2012
2019 | Remove Temp.Support for Temp.Fresh Water Main | Thu Oct 25 08:00:00 IST 2012 | Wed Oct 31 17:00:00 IST 2012
2020 | 1.1m Dia. Sewer Pipe Diversion | Tue Dec 14 08:00:00 IST 2010 | Fri Mar 01 17:00:00 IST 2013
2021 | Coord'n w/DSD forTemp.Removal ofOverflow Pipe | Mon Jan 16 08:00:00 IST 2012 | Mon Jan 16 08:00:00 IST 2012
2022 | Trial Trench & Record | Wed Aug 31 08:00:00 IDT 2011 | Fri Sep 30 17:00:00 IDT 2011
2023 | Sheet Piles Cofferdam 1A | Fri Jul 22 08:00:00 IDT 2011 | Mon Oct 03 17:00:00 IST 2011
2024 | Expose and Protect 400mm dia.Gas Main (GAS211) | Thu Sep 08 08:00:00 IDT 2011 | Tue Oct 11 17:00:00 IST 2011
2025 | Drilling | Mon Jan 16 08:00:00 IST 2012 | Tue Jan 31 17:00:00 IST 2012
2026 | Grouting for MH-1 | Mon Jan 16 08:00:00 IST 2012 | Sat Jan 21 17:00:00 IST 2012
2027 | Excavate for dewatering well and place blinding | Mon Jan 16 08:00:00 IST 2012 | Thu Jan 19 17:00:00 IST 2012
2028 | Excavate for MH-1 Construction & Shoring Installation | Thu Mar 01 08:00:00 IST 2012 | Sat Mar 24 17:00:00 IST 2012
2029 | Construct MH-1 Stage 1 & pump test | Mon Sep 17 08:00:00 IDT 2012 | Fri Sep 28 17:00:00 IST 2012
2030 | Insert DN800 temp pipe and fill gap between temp pipe & DN1800 | Sat Sep 29 08:00:00 IST 2012 | Sat Oct 06 17:00:00 IST 2012
2031 | Installation of by-pass pipe, benching & Inspection | Mon Oct 08 08:00:00 IST 2012 | Mon Oct 15 17:00:00 IST 2012
2032 | Drilling | Mon Jan 16 08:00:00 IST 2012 | Sat Jan 21 17:00:00 IST 2012
2033 | Grouting for MH-2 | Mon Jan 16 08:00:00 IST 2012 | Sat Jan 28 17:00:00 IST 2012
2034 | Excavate for dewatering well and place blinding | Mon Jan 16 08:00:00 IST 2012 | Fri Jan 20 17:00:00 IST 2012
2035 | Excavate for MH-2 Construction & Shoring Installation | Mon Jan 16 08:00:00 IST 2012 | Fri Feb 17 17:00:00 IST 2012
2036 | Construct MH-2 Stage 1 & pump test | Thu Oct 04 08:00:00 IST 2012 | Mon Oct 15 17:00:00 IST 2012
2037 | Insert DN800 temp pipe and fill gap between temp pipe & DN1800 | Tue Oct 16 08:00:00 IST 2012 | Sat Oct 20 17:00:00 IST 2012
2038 | Installation of by-pass pipe, benching & Inspection | Sat Oct 20 08:00:00 IST 2012 | Mon Oct 29 17:00:00 IST 2012
2039 | Excavate for pipe laying between MH-1 to MH-2 & Shoring Installation | Tue Mar 06 08:00:00 IST 2012 | Thu Apr 19 17:00:00 IDT 2012
2040 | Pipe Laying, air test and concrete surround | Fri Oct 12 08:00:00 IST 2012 | Fri Oct 26 17:00:00 IST 2012
2041 | Diversion | Tue Oct 30 08:00:00 IST 2012 | Fri Nov 02 17:00:00 IST 2012
2042 | Backfill to 2nd layer waling and construct remaining part of manholes MH-1 & MH-2 | Fri Nov 02 08:00:00 IST 2012 | Tue Nov 20 17:00:00 IST 2012
2043 | Remove 1st layer waling and backfill to ground level | Wed Nov 21 08:00:00 IST 2012 | Sat Nov 24 17:00:00 IST 2012
2044 | Install Casing & Remove Piles (3nos at D/T) | Mon Nov 26 08:00:00 IST 2012 | Mon Dec 24 17:00:00 IST 2012
2045 | Install Casing & Remove Piles (4nos at U/T) | Fri Jan 11 08:00:00 IST 2013 | Fri Mar 01 17:00:00 IST 2013
2046 | Backfilling & Reinstate Road Surface | Fri Nov 23 08:00:00 IST 2012 | Mon Jan 07 17:00:00 IST 2013
2047 | Obstruction Removal at 1.1m Dia.Sewer Pipe Area (DT) | Fri Jul 22 08:00:00 IDT 2011 | Wed Apr 18 17:00:00 IDT 2012
2048 | Obstruction Removal at 1.1m Dia.Sewer Pipe Area (UT) | Tue Dec 14 08:00:00 IST 2010 | Tue Dec 14 08:00:00 IST 2010
2049 | 1.8m Dia. Sewer Pipe Diversion | Sat Jan 08 08:00:00 IST 2011 | Sat Nov 10 17:00:00 IST 2012
2050 | Group E Tree Transplant (T9605) Preparation Works | Sat Jan 08 08:00:00 IST 2011 | Sat Jul 02 17:00:00 IDT 2011
2051 | Group D Tree Transplant (T9603 & T9604) Preparation Works | Sat Jan 08 08:00:00 IST 2011 | Wed Jun 22 17:00:00 IDT 2011
2052 | Group B Tree Transplant (U0010) Preparation Works | Mon Feb 28 08:00:00 IST 2011 | Mon May 23 17:00:00 IDT 2011
2053 | Group D Tree Transplant (U0018) Preparation Works | Mon Feb 28 08:00:00 IST 2011 | Thu Aug 11 17:00:00 IDT 2011
2054 | Group E Tree Transplant (T9601&T9602)Preparation Works | Mon Feb 28 08:00:00 IST 2011 | Mon Aug 22 17:00:00 IDT 2011
2055 | Trial Trench & Record | Wed Aug 31 08:00:00 IDT 2011 | Fri Sep 30 17:00:00 IDT 2011
2056 | Construct Cofferdam 2: MH-4, excavate to formation level and place blinding layer | Wed Aug 31 08:00:00 IDT 2011 | Mon Dec 05 17:00:00 IST 2011
2057 | Slew 400KV (CLP221)+11kV (CLP222) w/Temp.Support | Mon Jan 16 08:00:00 IST 2012 | Sat Jan 21 17:00:00 IST 2012
2058 | Pipe Formation preparation | Thu Feb 09 08:00:00 IST 2012 | Wed Feb 15 17:00:00 IST 2012
2059 | Sewage Pipe Laying with concrete surround (btw MH-3 to MH-4) | Wed Feb 01 08:00:00 IST 2012 | Thu Feb 09 17:00:00 IST 2012
2060 | Construct Manhole - Stage 1 | Mon Jan 16 08:00:00 IST 2012 | Fri Jan 20 17:00:00 IST 2012
2061 | BreakDN1800 pipe top | Sat Jan 28 08:00:00 IST 2012 | Mon Jan 30 17:00:00 IST 2012
2062 | Construct Manhole - Stage 2 & pump test | Wed Feb 01 08:00:00 IST 2012 | Thu Feb 02 17:00:00 IST 2012
2063 | Insert Temp Pipe and Filling gap between temp pipe & DN1800 | Wed Feb 22 08:00:00 IST 2012 | Sat Feb 25 17:00:00 IST 2012
2064 | Installation of by-pass pipe, benching & inspection | Wed Feb 22 08:00:00 IST 2012 | Tue Feb 28 17:00:00 IST 2012
2065 | Diversion | Wed Jan 18 08:00:00 IST 2012 | Sat Jan 21 17:00:00 IST 2012
2066 | Make good manhole wall at original pipe opening | Fri Aug 31 08:00:00 IDT 2012 | Tue Sep 04 17:00:00 IDT 2012
2067 | Demolish pile cap and expose existing obstruction pile | Wed Sep 05 08:00:00 IDT 2012 | Fri Sep 07 17:00:00 IDT 2012
2068 | Backfill to 2nd layer waling and construct remaining part of manhole | Sat Sep 08 08:00:00 IDT 2012 | Tue Sep 25 17:00:00 IST 2012
2069 | Remove 1st layer waling and backfill to ground level | Wed Sep 26 08:00:00 IST 2012 | Fri Oct 05 17:00:00 IST 2012
2070 | Remove 1 no. of dia. 500 pile | Sat Oct 06 08:00:00 IST 2012 | Wed Oct 17 17:00:00 IST 2012
2071 | Construct Cofferdam 1B: MH-3, excavate to formation level and place blinding layer | Wed Aug 31 08:00:00 IDT 2011 | Mon Dec 05 17:00:00 IST 2011
2072 | Construct Manhole - Stage 1 & pump test | Wed Feb 01 08:00:00 IST 2012 | Mon Feb 13 17:00:00 IST 2012
2073 | Insert Temp Pipe and Filling gap between temp pipe & DN1800 | Wed Feb 01 08:00:00 IST 2012 | Sat Feb 04 17:00:00 IST 2012
2074 | Installation of by-pass pipe, benching & inspection | Wed Feb 22 08:00:00 IST 2012 | Tue Feb 28 17:00:00 IST 2012
2075 | Diversion | Wed Jan 18 08:00:00 IST 2012 | Sat Jan 21 17:00:00 IST 2012
2076 | Make good manhole wall at original pipe opening | Fri Aug 31 08:00:00 IDT 2012 | Tue Sep 04 17:00:00 IDT 2012
2077 | Demolish pile cap and expose existing obstruction pile | Wed Sep 05 08:00:00 IDT 2012 | Fri Sep 07 17:00:00 IDT 2012
2078 | Install guide steel liner | Sat Sep 08 08:00:00 IDT 2012 | Wed Sep 12 17:00:00 IDT 2012
2079 | Backfill to 2nd layer waling and construct remaining part of manhole | Thu Sep 13 08:00:00 IDT 2012 | Sat Sep 29 17:00:00 IST 2012
2080 | Remove 1st layer waling and backfill to ground level | Wed Oct 03 08:00:00 IST 2012 | Sat Oct 13 17:00:00 IST 2012
2081 | Remove 2 no. of dia. 500 pile | Thu Oct 18 08:00:00 IST 2012 | Sat Nov 10 17:00:00 IST 2012
2082 | Obstruction Removal at 1.8m Dia.Sewer Pipe Area (DT) | Wed Aug 31 08:00:00 IDT 2011 | Mon May 28 17:00:00 IDT 2012
2083 | Removal of Piles: P1 to P3 & P9 | Sat Mar 12 08:00:00 IST 2011 | Thu Mar 08 17:00:00 IST 2012
2084 | Open Cut to Expose Top Slab of Culvert Partially | Tue Nov 01 08:00:00 IST 2011 | Thu Nov 03 17:00:00 IST 2011
2085 | Break Top Slab of Box Culvert | Fri Nov 04 08:00:00 IST 2011 | Tue Jan 31 17:00:00 IST 2012
2086 | Install Temp.Working Platform & Cofferdam | Tue Jun 21 08:00:00 IDT 2011 | Tue Jul 05 17:00:00 IDT 2011
2087 | Mobilization | Mon Nov 07 08:00:00 IST 2011 | Fri Jan 13 17:00:00 IST 2012
2088 | Install Casing & Remove Pile: P1 | Tue Nov 01 08:00:00 IST 2011 | Wed Nov 16 17:00:00 IST 2011
2089 | Fill LeanConcrete &Reinstate BottomSlab for P1 | Tue Nov 01 08:00:00 IST 2011 | Sat Nov 26 17:00:00 IST 2011
2090 | Shift Temp.Cofferdam & Remove Pile: P2 | Sat Mar 12 08:00:00 IST 2011 | Tue Apr 12 17:00:00 IDT 2011
2091 | Fill Lean Concrete & Reinstate BottomSlab for P2 | Tue Nov 01 08:00:00 IST 2011 | Tue Dec 06 17:00:00 IST 2011
2092 | Install Temp. Cofferdam & Remove Pile: P3 | Thu Jan 19 08:00:00 IST 2012 | Wed Feb 01 17:00:00 IST 2012
2093 | Fill Lean Concrete & Reinstate BottomSlab for P3 | Thu Feb 09 08:00:00 IST 2012 | Thu Mar 08 17:00:00 IST 2012
2094 | Implement TTM | Tue Jun 28 17:00:00 IDT 2011 | Tue Jun 28 17:00:00 IDT 2011
2095 | Modification Works for Temp.Traffic Diversion | Wed Jun 29 08:00:00 IDT 2011 | Tue Nov 01 17:00:00 IST 2011
2096 | Install Casing & Remove Pile: P9 | Mon Mar 14 08:00:00 IST 2011 | Fri Nov 25 17:00:00 IST 2011
2097 | Fill Lean Concrete & Reinstate BottomSlab for P9 | Tue Nov 01 08:00:00 IST 2011 | Fri Nov 18 17:00:00 IST 2011
2098 | WD1 Piles Removal (P1,P3 & P9) (UT) | Sun Mar 13 08:00:00 IST 2011 | Thu Jul 07 17:00:00 IDT 2011
2099 | Removal of Piles: P4 to P6 & P7 &P8 | Tue Jun 21 08:00:00 IDT 2011 | Wed Feb 27 17:00:00 IST 2013
2100 | Working Platform for Prebore H Piles | Tue Jun 21 08:00:00 IDT 2011 | Thu Jul 14 17:00:00 IDT 2011
2101 | Install 5 nos.Pre-bored Socket H-piles | Tue Jun 21 08:00:00 IDT 2011 | Tue Jul 12 17:00:00 IDT 2011
2102 | Sheet Pile for Cofferdam | Fri Jul 22 08:00:00 IDT 2011 | Thu Aug 18 17:00:00 IDT 2011
2103 | Bulk Excqavation to Expose Top Slab of Culvert | Tue Jun 21 08:00:00 IDT 2011 | Sat Jul 02 17:00:00 IDT 2011
2104 | Place Concrete Block Wall | Tue Jun 21 08:00:00 IDT 2011 | Wed Jun 22 17:00:00 IDT 2011
2105 | Waling Installtion | Wed Aug 31 08:00:00 IDT 2011 | Wed Sep 21 17:00:00 IDT 2011
2106 | Blinding Slab | Wed Aug 31 08:00:00 IDT 2011 | Fri Sep 02 17:00:00 IDT 2011
2107 | Demolish TopSlab above PilesP1~ P3 & P9 | Wed Aug 31 08:00:00 IDT 2011 | Wed Sep 14 17:00:00 IDT 2011
2108 | Formwork & Planking | Wed Aug 31 08:00:00 IDT 2011 | Thu Sep 08 17:00:00 IDT 2011
2109 | Reinstate Top Slab and Corbel Beams | Wed Aug 31 08:00:00 IDT 2011 | Thu Oct 06 17:00:00 IST 2011
2110 | Concrete Curing | Sat Jan 28 08:00:00 IST 2012 | Fri Feb 24 17:00:00 IST 2012
2111 | Installation of Jacks | Sat Feb 25 08:00:00 IST 2012 | Sat Mar 03 17:00:00 IST 2012
2112 | Slew 400kV Cable to P1 to P3 | Mon Feb 06 08:00:00 IST 2012 | Thu Feb 16 17:00:00 IST 2012
2113 | Divert Watermain (FW203) | Mon Feb 20 08:00:00 IST 2012 | Sat Feb 25 17:00:00 IST 2012
2114 | Water Suspension & Connection | Sat Feb 25 08:00:00 IST 2012 | Fri Mar 02 17:00:00 IST 2012
2115 | Backfilling | Fri Mar 02 08:00:00 IST 2012 | Thu Mar 08 17:00:00 IST 2012
2116 | Excavation to Expose P4 to P8 | Thu Mar 08 08:00:00 IST 2012 | Wed Mar 21 17:00:00 IST 2012
2117 | Installation of Concrete Block Wall | Wed Mar 21 08:00:00 IST 2012 | Wed Apr 11 17:00:00 IDT 2012
2118 | Saw Cut Roof over P4 to P6, P7 & P8 | Fri Apr 13 08:00:00 IDT 2012 | Sat May 05 17:00:00 IDT 2012
2119 | Install Temp.Working Platform & Cofferdam of Work Area | Mon Jan 16 08:00:00 IST 2012 | Thu Jan 26 17:00:00 IST 2012
2120 | Install Casing & Remove Piles: P5 | Thu Nov 01 08:00:00 IST 2012 | Wed Dec 05 17:00:00 IST 2012
2121 | Fill Lean Concrete& Reinstate BottomSlab forP5 | Thu Nov 29 08:00:00 IST 2012 | Sat Dec 01 17:00:00 IST 2012
2122 | Shift Temp.Cofferdam & Remove Pile: P4 | Sat Dec 01 08:00:00 IST 2012 | Wed Dec 19 17:00:00 IST 2012
2123 | Fill Lean Concrete & Reinstate BottomSlab for P4 | Mon Nov 19 08:00:00 IST 2012 | Wed Nov 21 17:00:00 IST 2012
2124 | Shift Temp.Cofferdam & Remove Piles: P8 | Mon Dec 17 08:00:00 IST 2012 | Mon Jan 14 17:00:00 IST 2013
2125 | Fill Lean Concrete & Reinstate BottomSlab for P8 | Thu Jan 17 08:00:00 IST 2013 | Sat Jan 19 17:00:00 IST 2013
2126 | Shift Temp.Cofferdam & Remove Piles: P6 | Sat Jan 05 08:00:00 IST 2013 | Mon Feb 04 17:00:00 IST 2013
2127 | Fill Lean Concrete & Reinstate BottomSlab for P6 | Sat Feb 02 08:00:00 IST 2013 | Tue Feb 05 17:00:00 IST 2013
2128 | Shift Temp.Cofferdam & Remove Piles: P7 | Mon Jan 21 08:00:00 IST 2013 | Fri Feb 01 17:00:00 IST 2013
2129 | Fill Lean Concrete & Reinstate BottomSlab for P7 | Mon Feb 25 08:00:00 IST 2013 | Wed Feb 27 17:00:00 IST 2013
2130 | WD1Pre-bored Socket H-piles & Pile Cap (5nos..) | Tue Jun 21 08:00:00 IDT 2011 | Sun Oct 23 17:00:00 IST 2011
2131 | WD1 Piles Removal (P4,P6,P7 & P8) (UT) | Fri Apr 13 08:00:00 IDT 2012 | Sat Jan 19 17:00:00 IST 2013
2132 | Reinstatement | Fri Aug 31 08:00:00 IDT 2012 | Tue Oct 29 17:00:00 IST 2013
2133 | Reinstate Box Culvert (Invert & Roof) | Fri Aug 31 08:00:00 IDT 2012 | Mon Feb 04 17:00:00 IST 2013
2134 | Reinstate Road & Utilities | Thu Aug 01 08:00:00 IDT 2013 | Fri Aug 30 17:00:00 IDT 2013
2135 | DSD Inspection and Hand Over | Wed Oct 23 08:00:00 IDT 2013 | Tue Oct 29 17:00:00 IST 2013
2136 | Completion | Fri Jun 01 08:00:00 IDT 2012 | Fri Jun 29 17:00:00 IDT 2012
2137 | Prepare & Submit Draft As-built Drawings | Fri Jun 01 08:00:00 IDT 2012 | Fri Jun 29 17:00:00 IDT 2012
2138 | Prepare & Submit As-built Drawings | Fri Jun 01 08:00:00 IDT 2012 | Fri Jun 29 17:00:00 IDT 2012
2139 | G5 Rising Main Diversion & FMO Pier A Pile Remvoal | Mon Feb 28 08:00:00 IST 2011 | Fri Jul 31 17:00:00 IDT 2015
2140 | Rising Main & FMO Pier A Pile Removal (DT) | Sun Mar 13 08:00:00 IST 2011 | Sat Jan 05 17:00:00 IST 2013
2141 | Rising Main & FMO Pier A Pile Removal (UT) | Sun Mar 13 08:00:00 IST 2011 | Sat Sep 07 17:00:00 IDT 2013
2142 | Method Statement Submission and Approval | Mon Apr 04 08:00:00 IDT 2011 | Fri May 13 17:00:00 IDT 2011
2143 | MS Preparation | Mon Apr 04 08:00:00 IDT 2011 | Wed May 04 17:00:00 IDT 2011
2144 | MS Submission to MTR | Fri Apr 15 17:00:00 IDT 2011 | Fri Apr 15 17:00:00 IDT 2011
2145 | MS Comment & Approval by MTR | Sat Apr 16 08:00:00 IDT 2011 | Sat May 07 17:00:00 IDT 2011
2146 | Issue for Construction | Fri May 13 17:00:00 IDT 2011 | Fri May 13 17:00:00 IDT 2011
2147 | Temp. Works Design Submission | Mon Feb 28 08:00:00 IST 2011 | Wed Oct 05 17:00:00 IST 2011
2148 | Prepare Diversion Scheme to DSD | Mon Feb 28 08:00:00 IST 2011 | Sun Apr 03 17:00:00 IDT 2011
2149 | Propose Diversion Scheme to DSD | Mon Apr 04 08:00:00 IDT 2011 | Mon Apr 04 08:00:00 IDT 2011
2150 | No objection from DSD | Mon Apr 04 08:00:00 IDT 2011 | Fri Jul 08 17:00:00 IDT 2011
2151 | Prepare Temporary Work Design for Cofferdam | Sat Mar 12 08:00:00 IST 2011 | Mon May 16 17:00:00 IDT 2011
2152 | Temp. Works Design Comment & Approval by MTR/DSD | Tue Apr 19 08:00:00 IDT 2011 | Sat Jun 18 17:00:00 IDT 2011
2153 | Issue for Construction (Cofferdam) | Mon May 16 17:00:00 IDT 2011 | Mon May 16 17:00:00 IDT 2011
2154 | Prepare Design for DSD Main Support/Detailed Scheme | Fri Apr 08 08:00:00 IDT 2011 | Sat May 14 17:00:00 IDT 2011
2155 | DSD Main Support Approval by MTR/DSD | Sat May 14 08:00:00 IDT 2011 | Fri Jul 08 17:00:00 IDT 2011
2156 | Issue for Construction | Fri Jun 10 17:00:00 IDT 2011 | Fri Jun 10 17:00:00 IDT 2011
2157 | Pipe/Fitting Procurement | Sat Jun 11 08:00:00 IDT 2011 | Wed Oct 05 17:00:00 IST 2011
2158 | Construction | Mon Feb 28 08:00:00 IST 2011 | Fri Jul 31 17:00:00 IDT 2015
2159 | Cofferdam Reinstatement | Sat Mar 29 08:00:00 IDT 2014 | Thu Jun 19 17:00:00 IDT 2014
2160 | GI works for Rising Main Pile Removal | Mon Feb 28 08:00:00 IST 2011 | Sat Mar 19 17:00:00 IST 2011
2161 | Trial Trench for Existing Utilities | Tue Apr 19 08:00:00 IDT 2011 | Wed May 18 17:00:00 IDT 2011
2162 | Slew Telecom Cable (PCCW702+CATV704) | Sat Apr 30 08:00:00 IDT 2011 | Thu May 12 17:00:00 IDT 2011
2163 | Ground Treatment for Existing Seawall, if any | Tue May 17 08:00:00 IDT 2011 | Wed May 25 17:00:00 IDT 2011
2164 | Sheetpile Installation | Sat May 21 08:00:00 IDT 2011 | Sat Jun 04 17:00:00 IDT 2011
2165 | Northern Rising Main: Install Prebored H-pile (10nos.) | Tue Jun 14 08:00:00 IDT 2011 | Sat Jul 23 17:00:00 IDT 2011
2166 | Southern Rising Main: install Prebored H-pile (10nos.) | Tue Jun 14 08:00:00 IDT 2011 | Sat Jul 23 17:00:00 IDT 2011
2167 | Pile Testing | Mon Aug 01 08:00:00 IDT 2011 | Sat Aug 06 17:00:00 IDT 2011
2168 | Excavate & Expose Bottom of Rising Main (Trial Trench) | Mon Aug 01 08:00:00 IDT 2011 | Mon Aug 22 17:00:00 IDT 2011
2169 | Locate Existing Rising Main & FMO (A) Piles | Mon Aug 08 08:00:00 IDT 2011 | Sat Aug 20 17:00:00 IDT 2011
2170 | Removal FMO Pier A Vertical Piles D/T & Backfilling | Tue Aug 16 08:00:00 IDT 2011 | Thu Aug 25 17:00:00 IDT 2011
2171 | Removal Pier A Vertical Piles U/T & Backfilling | Thu Aug 25 08:00:00 IDT 2011 | Wed Aug 31 17:00:00 IDT 2011
2172 | Excavate to Capping Beam Formation Level | Mon Sep 12 08:00:00 IDT 2011 | Tue Oct 04 17:00:00 IST 2011
2173 | North Temp.Rising Main:Capping Beam | Fri Oct 07 08:00:00 IST 2011 | Sat Oct 29 17:00:00 IST 2011
2174 | South Temp.Rising Main:Capping Beam | Fri Oct 07 08:00:00 IST 2011 | Sat Oct 29 17:00:00 IST 2011
2175 | South Temp.Rising Main Installation+Thrust Block | Mon Oct 31 08:00:00 IST 2011 | Sat Nov 12 17:00:00 IST 2011
2176 | Expose Existing South Pipe | Thu Mar 24 08:00:00 IST 2011 | Wed Nov 02 17:00:00 IST 2011
2177 | Notification for South Rising Main & Flow Stop from DSD Station | Sat Nov 12 17:00:00 IST 2011 | Sat Nov 12 17:00:00 IST 2011
2178 | Diversion Works for Rising Main (South Pipe) | Mon Feb 28 08:00:00 IST 2011 | Fri Mar 11 17:00:00 IST 2011
2179 | North Temp.Rising Main Installation+Thrust Block | Mon Feb 28 08:00:00 IST 2011 | Wed Mar 30 17:00:00 IST 2011
2180 | Expose Existing North Pipe | Mon Mar 14 08:00:00 IST 2011 | Tue Dec 06 17:00:00 IST 2011
2181 | Notification for North Rising Main & Flow Stop from DSD Station | Thu Dec 15 17:00:00 IST 2011 | Thu Dec 15 17:00:00 IST 2011
2182 | Diversion Works for Rising Main (North Pipe) | Tue Nov 01 08:00:00 IST 2011 | Fri Nov 11 17:00:00 IST 2011
2183 | Dismantle Existing Rising Mains | Sat Nov 12 08:00:00 IST 2011 | Fri Nov 18 17:00:00 IST 2011
2184 | Form WorkingPlatform | Tue Jun 21 08:00:00 IDT 2011 | Thu Jul 21 17:00:00 IDT 2011
2185 | Locate Existing Rising Main & FMO (A) Piles | Tue Jun 21 08:00:00 IDT 2011 | Thu Jul 21 17:00:00 IDT 2011
2186 | Removal FMO Pier A Raking Piles DT & Backfilling | Wed Aug 31 08:00:00 IDT 2011 | Mon Nov 14 17:00:00 IST 2011
2187 | Remove Rising Mains Vertical Piles Clash D/T Tunnel & Backfilling | Wed Aug 31 08:00:00 IDT 2011 | Thu Dec 22 17:00:00 IST 2011
2188 | Removal FMO Pier A Raking Piles UT & Backfilling | Sat Oct 29 08:00:00 IST 2011 | Tue May 08 17:00:00 IDT 2012
2189 | Remove Rising Main Vertical Piles Clash U/T Tunnel & Backfilling | Wed Nov 30 08:00:00 IST 2011 | Thu Mar 22 17:00:00 IST 2012
2190 | Remove Working Platform | Tue Apr 17 08:00:00 IDT 2012 | Thu May 03 17:00:00 IDT 2012
2191 | Tie Beams Construction for New Rising Main | Mon Jan 16 08:00:00 IST 2012 | Mon Feb 27 17:00:00 IST 2012
2192 | Notification for South Rising Main & Flow Stop from DSD Station | Mon Oct 07 17:00:00 IDT 2013 | Mon Oct 07 17:00:00 IDT 2013
2193 | Reinstatement Works for Rising Mains (South pipe) | Fri Nov 01 08:00:00 IST 2013 | Tue Dec 31 17:00:00 IST 2013
2194 | Notification for North Rising Main & Flow Stop from DSD Station | Mon Dec 23 17:00:00 IST 2013 | Mon Dec 23 17:00:00 IST 2013
2195 | Reinstatement Works for Rising Mains (North pipe) | Tue Dec 24 08:00:00 IST 2013 | Thu Jan 23 17:00:00 IST 2014
2196 | Place Concrete Surround | Tue Jan 27 08:00:00 IST 2015 | Mon Feb 23 17:00:00 IST 2015
2197 | Utilities Reinstatement | Mon Jun 01 08:00:00 IDT 2015 | Fri Jul 31 17:00:00 IDT 2015
2198 | Rising Main & FMO Pier A Pile Removal (DT) | Sun Mar 13 08:00:00 IST 2011 | Sat Jan 05 17:00:00 IST 2013
2199 | Rising Main & FMO Pier A Pile Removal (UT) | Sun Mar 13 08:00:00 IST 2011 | Sat Sep 07 17:00:00 IDT 2013
2200 | Completion | Thu Sep 01 08:00:00 IDT 2011 | Thu Sep 29 17:00:00 IDT 2011
2201 | Prepare & Submit Draft As-built Drawings | Thu Sep 01 08:00:00 IDT 2011 | Thu Sep 29 17:00:00 IDT 2011
2202 | Prepare & Submit As-built Drawings | Thu Sep 01 08:00:00 IDT 2011 | Thu Sep 29 17:00:00 IDT 2011
2203 | G2 YC2 Culvet - Remove Barrette & Modify Foundation | Mon Feb 28 08:00:00 IST 2011 | Sat Aug 23 17:00:00 IDT 2014
2204 | Stage 1: YC2 Cofferdam Installation | Sun Mar 13 08:00:00 IST 2011 | Wed Aug 17 17:00:00 IDT 2011
2205 | Stage 2: YC2 Barrettes Removal (B15 - DT) | Sun Jun 19 08:00:00 IDT 2011 | Sat Mar 03 17:00:00 IST 2012
2206 | Stage 3: YC2 Barrettes Removal (B13 - UT) | Wed Nov 07 08:00:00 IST 2012 | Wed Nov 21 17:00:00 IST 2012
2207 | Temp.Works Design Submission | Mon Feb 28 08:00:00 IST 2011 | Thu Jun 23 17:00:00 IDT 2011
2208 | Temp. Works Design Preparation | Mon Feb 28 08:00:00 IST 2011 | Mon Apr 25 17:00:00 IDT 2011
2209 | Temp. Works Design Submit to MTR | Wed Mar 23 17:00:00 IST 2011 | Wed Mar 23 17:00:00 IST 2011
2210 | Temp. Works Design Comment by MTR/DSD | Thu Mar 24 08:00:00 IST 2011 | Thu Apr 07 17:00:00 IDT 2011
2211 | Temp. Works Design Re-submission Preparation | Thu Apr 21 08:00:00 IDT 2011 | Thu Jun 23 17:00:00 IDT 2011
2212 | Temp. Works Design Comment & Approval by MTR/DSD | Tue May 10 08:00:00 IDT 2011 | Sun May 22 17:00:00 IDT 2011
2213 | Issue for Construction | Tue Jun 07 08:00:00 IDT 2011 | Tue Jun 07 08:00:00 IDT 2011
2214 | Method Statement Submission and Approval | Mon Feb 28 08:00:00 IST 2011 | Tue Jun 21 17:00:00 IDT 2011
2215 | MS Preparation | Mon Feb 28 08:00:00 IST 2011 | Mon Apr 04 17:00:00 IDT 2011
2216 | MS Submission to MTR | Mon Mar 28 17:00:00 IST 2011 | Mon Mar 28 17:00:00 IST 2011
2217 | MS Comment by MTR/DSD | Tue Mar 29 08:00:00 IST 2011 | Sun May 01 17:00:00 IDT 2011
2218 | MS Re-submission Preparation | Tue Apr 26 08:00:00 IDT 2011 | Wed Jun 01 17:00:00 IDT 2011
2219 | MS Submission to MTR | Wed May 18 17:00:00 IDT 2011 | Wed May 18 17:00:00 IDT 2011
2220 | MS Comment & Approval by MTR/DSD | Thu May 19 08:00:00 IDT 2011 | Tue Jun 21 17:00:00 IDT 2011
2221 | Issue for Construction | Wed Jun 15 17:00:00 IDT 2011 | Wed Jun 15 17:00:00 IDT 2011
2222 | TTM Scheme Submission & Approval | Mon Feb 28 08:00:00 IST 2011 | Sun Aug 21 17:00:00 IDT 2011
2223 | Prepare Temporary Traffic Management | Mon Feb 28 08:00:00 IST 2011 | Wed Mar 23 17:00:00 IST 2011
2224 | TTM reviewed by SLG | Fri Mar 25 08:00:00 IST 2011 | Mon Jun 06 17:00:00 IDT 2011
2225 | Resubmit TTM | Sat Jun 18 08:00:00 IDT 2011 | Mon Jul 25 17:00:00 IDT 2011
2226 | TTM reviewed by SLG | Sun Jun 26 08:00:00 IDT 2011 | Mon Jul 25 17:00:00 IDT 2011
2227 | Notification to RMO | Sun Jul 24 08:00:00 IDT 2011 | Sun Aug 21 17:00:00 IDT 2011
2228 | XP Application & Approval | Sun May 01 08:00:00 IDT 2011 | Fri May 20 17:00:00 IDT 2011
2229 | Implement TTM | Fri Aug 05 17:00:00 IDT 2011 | Fri Aug 05 17:00:00 IDT 2011
2230 | Stage 1 | Mon Feb 28 08:00:00 IST 2011 | Wed Oct 26 17:00:00 IST 2011
2231 | GI works for YC2 Barrette Removal | Mon Feb 28 08:00:00 IST 2011 | Mon Mar 07 17:00:00 IST 2011
2232 | Area 40.4: Tree Transplant by 801 Designated Contractor | Mon Feb 28 08:00:00 IST 2011 | Mon Feb 28 08:00:00 IST 2011
2233 | Shum Mong Rd: Tree Transplant by 801 Designated | Mon Feb 28 08:00:00 IST 2011 | Mon Feb 28 08:00:00 IST 2011
2234 | TTA Stage 0 and 1 for YC2 and Shum Shui Po Pier | Sat Aug 06 08:00:00 IDT 2011 | Tue Sep 06 17:00:00 IDT 2011
2235 | Cofferdam: Sheetpile Installation | Tue Sep 06 08:00:00 IDT 2011 | Thu Sep 22 17:00:00 IDT 2011
2236 | Cofferdam: Excavation + Shoring | Mon Oct 03 08:00:00 IST 2011 | Wed Oct 26 17:00:00 IST 2011
2237 | Backfilling for Cofferdam | Tue Jun 21 08:00:00 IDT 2011 | Tue Jul 26 17:00:00 IDT 2011
2238 | Construct Temp. Pavement | Tue Jun 21 08:00:00 IDT 2011 | Wed Jul 13 17:00:00 IDT 2011
2239 | Stage 1: YC2 Cofferdam Installation | Sun Mar 13 08:00:00 IST 2011 | Wed Aug 17 17:00:00 IDT 2011
2240 | Stage 2 | Sun Jun 19 08:00:00 IDT 2011 | Tue Feb 05 17:00:00 IST 2013
2241 | GI works for YC2 Barrette Removal (Stage 2) | Tue Jun 21 08:00:00 IDT 2011 | Tue Jul 05 17:00:00 IDT 2011
2242 | TTA Stage 2 for Culvert YC2 and Shum Shui Po Pie | Sun Jun 19 08:00:00 IDT 2011 | Wed Jul 06 17:00:00 IDT 2011
2243 | Cofferdam: Sheetpile Installation | Wed Aug 31 08:00:00 IDT 2011 | Mon Oct 24 17:00:00 IST 2011
2244 | Compensation Grout for Culvert | Wed Aug 31 08:00:00 IDT 2011 | Fri Oct 21 17:00:00 IST 2011
2245 | Cofferdam: Excavation + Shoring | Mon Jan 16 08:00:00 IST 2012 | Wed Feb 01 17:00:00 IST 2012
2246 | Remove Culvert Top Slab (saw cut) | Thu Feb 02 08:00:00 IST 2012 | Wed Feb 08 17:00:00 IST 2012
2247 | Install Working Platform & Mini Cofferdam for 1st Cut | Thu Feb 02 08:00:00 IST 2012 | Sat Feb 04 17:00:00 IST 2012
2248 | Barrette Removal (B15) 1st Cut | Sat Feb 11 08:00:00 IST 2012 | Wed Mar 07 17:00:00 IST 2012
2249 | Temp. Base Slab Reinstatement (1st Cut) | Sat Mar 10 08:00:00 IST 2012 | Sat Mar 10 17:00:00 IST 2012
2250 | Remove & Re-install WP Cofferdam for 2nd Cut | Sat Mar 10 08:00:00 IST 2012 | Wed Mar 14 17:00:00 IST 2012
2251 | Barrette Removal (B15) 2nd Cut | Sat Mar 17 08:00:00 IST 2012 | Tue Nov 06 17:00:00 IST 2012
2252 | Barrette Backfilling | Mon Jan 16 08:00:00 IST 2012 | Wed Jan 18 17:00:00 IST 2012
2253 | Culvert Base & Top Slabs Reinstatement | Thu Jan 19 08:00:00 IST 2012 | Wed Nov 07 17:00:00 IST 2012
2254 | Backfill and Road Reinstatement | Wed Jan 09 08:00:00 IST 2013 | Tue Feb 05 17:00:00 IST 2013
2255 | Stage 2: YC2 Barrettes Removal (B15 - DT) | Sun Jun 19 08:00:00 IDT 2011 | Sat Mar 03 17:00:00 IST 2012
2256 | Stage 3 | Wed Oct 31 08:00:00 IST 2012 | Sat Aug 23 17:00:00 IDT 2014
2257 | Compensation grout (after TBM U/T pass through) | Tue Apr 22 08:00:00 IDT 2014 | Fri May 23 17:00:00 IDT 2014
2258 | TTMs Stage 3 for Barrette B13 Removal | Wed Oct 31 08:00:00 IST 2012 | Tue Nov 06 17:00:00 IST 2012
2259 | Remove Culvert Top Slab | Wed Nov 07 08:00:00 IST 2012 | Tue Nov 13 17:00:00 IST 2012
2260 | Install Working Platform & Mini Cofferdam for 1st Cut | Fri Nov 30 08:00:00 IST 2012 | Sat Dec 08 17:00:00 IST 2012
2261 | Barrette Removal (B13) 1st Cut | Sat Nov 10 08:00:00 IST 2012 | Tue Nov 27 17:00:00 IST 2012
2262 | Install Working Platform & Mini Cofferdam for 2nd Cut | Tue Dec 18 08:00:00 IST 2012 | Fri Dec 28 17:00:00 IST 2012
2263 | Barrette Removal (B13) 2nd Cut | Wed Dec 05 08:00:00 IST 2012 | Fri Dec 21 17:00:00 IST 2012
2264 | Barrette Backfill | Fri Dec 21 08:00:00 IST 2012 | Mon Dec 24 17:00:00 IST 2012
2265 | Culvert Base Slab Reinstatement | Thu Dec 27 08:00:00 IST 2012 | Mon Feb 04 17:00:00 IST 2013
2266 | Culvert Top Slab Temp. Reinstatement | Mon Jan 28 08:00:00 IST 2013 | Sat Mar 09 17:00:00 IST 2013
2267 | Top Slab Reinstatement | Sat May 10 08:00:00 IDT 2014 | Wed Jun 25 17:00:00 IDT 2014
2268 | Road Reinstatement / Final TTA | Mon Jun 16 08:00:00 IDT 2014 | Sat Aug 23 17:00:00 IDT 2014
2269 | Stage 3: YC2 Barrettes Removal (B13 - UT) | Wed Nov 07 08:00:00 IST 2012 | Tue Jun 25 17:00:00 IDT 2013
2270 | Completion | Wed May 02 08:00:00 IDT 2012 | Tue May 29 17:00:00 IDT 2012
2271 | Prepare & Submit Draft As-built Drawings | Wed May 02 08:00:00 IDT 2012 | Tue May 29 17:00:00 IDT 2012
2272 | Prepare & Submit As-built Drawings | Wed May 02 08:00:00 IDT 2012 | Tue May 29 17:00:00 IDT 2012
2273 | G3 NC1 DSD Culvert - Remove Barrette | Sat Aug 14 08:00:00 IDT 2010 | Tue Sep 17 17:00:00 IDT 2013
2274 | Barrette Removal B28 & B27 (DT) | Sat Apr 16 08:00:00 IDT 2011 | Wed Aug 08 17:00:00 IDT 2012
2275 | Barrette Removal B24,B21 & B22 (UT) | Sat Apr 16 08:00:00 IDT 2011 | Thu Sep 06 17:00:00 IDT 2012
2276 | Method Statement Submission and Approval | Sat Aug 14 08:00:00 IDT 2010 | Tue Jun 21 17:00:00 IDT 2011
2277 | MS Preparation | Mon Feb 28 08:00:00 IST 2011 | Wed Mar 09 17:00:00 IST 2011
2278 | MS Submission to MTR/DSD | Sat Mar 26 17:00:00 IST 2011 | Sat Mar 26 17:00:00 IST 2011
2279 | MS Comment by MTR/DSD | Sun Mar 27 08:00:00 IST 2011 | Fri Apr 29 17:00:00 IDT 2011
2280 | MS Re-submission Preparation | Sat Aug 14 08:00:00 IDT 2010 | Tue Aug 24 17:00:00 IDT 2010
2281 | MS Submission to MTR/DSD | Wed May 18 17:00:00 IDT 2011 | Wed May 18 17:00:00 IDT 2011
2282 | MS Comment & Approval by MTR/DSD | Thu May 19 08:00:00 IDT 2011 | Tue Jun 21 17:00:00 IDT 2011
2283 | Issue for Construction | Wed Jun 15 17:00:00 IDT 2011 | Wed Jun 15 17:00:00 IDT 2011
2284 | Tree Transplant Application Preparation | Mon Feb 28 08:00:00 IST 2011 | Thu Jun 09 17:00:00 IDT 2011
2285 | Application Submit to LandS Department | Sat Mar 26 17:00:00 IST 2011 | Sat Mar 26 17:00:00 IST 2011
2286 | Application Approval by LandS Department | Sun Mar 27 08:00:00 IST 2011 | Sun Apr 17 17:00:00 IDT 2011
2287 | TTM Scheme Submisssion & Approval | Mon Feb 28 08:00:00 IST 2011 | Sun Aug 21 17:00:00 IDT 2011
2288 | Prepare Temp.Traffic Management (for S.2 &S.2.1) | Mon Feb 28 08:00:00 IST 2011 | Thu Mar 24 17:00:00 IST 2011
2289 | TTM reviewed by SLG | Fri Mar 25 08:00:00 IST 2011 | Mon Jun 06 17:00:00 IDT 2011
2290 | Resubmit TTM | Sat Jun 18 08:00:00 IDT 2011 | Wed Jul 13 17:00:00 IDT 2011
2291 | TTM reviewed by SLG | Sun Jun 26 08:00:00 IDT 2011 | Mon Jul 25 17:00:00 IDT 2011
2292 | Notification to RMO | Sun Jul 24 08:00:00 IDT 2011 | Sun Aug 21 17:00:00 IDT 2011
2293 | XP Application & Approval | Tue May 31 08:00:00 IDT 2011 | Tue Jun 21 17:00:00 IDT 2011
2294 | Implement TTM | Thu Aug 11 17:00:00 IDT 2011 | Thu Aug 11 17:00:00 IDT 2011
2295 | Prepare Temp.Traffic Management(for U/T Group) | Mon Feb 28 08:00:00 IST 2011 | Sat Mar 12 17:00:00 IST 2011
2296 | TTM reviewed by SLG (S.2) | Sun Mar 13 08:00:00 IST 2011 | Sat May 21 17:00:00 IDT 2011
2297 | Notification to RMO | Sun May 22 08:00:00 IDT 2011 | Thu Jun 02 17:00:00 IDT 2011
2298 | Prepare TTMS for Tree Transplant(for D/T Group) | Mon Feb 28 08:00:00 IST 2011 | Fri Jun 17 17:00:00 IDT 2011
2299 | TTM reviewed by SLG (S.2.1) | Sun Mar 13 08:00:00 IST 2011 | Sat May 21 17:00:00 IDT 2011
2300 | Notification to RMO | Sun May 22 08:00:00 IDT 2011 | Thu Jun 02 17:00:00 IDT 2011
2301 | TBM D/T Culvert | Mon Feb 28 08:00:00 IST 2011 | Sat Jan 12 17:00:00 IST 2013
2302 | Works Area 11.21 (Subject to SLG Approval) | Mon Feb 28 08:00:00 IST 2011 | Mon Feb 28 08:00:00 IST 2011
2303 | Works Area 11.31 | Mon Feb 28 08:00:00 IST 2011 | Mon Feb 28 08:00:00 IST 2011
2304 | Works Area 11.32 | Mon Feb 28 08:00:00 IST 2011 | Mon Feb 28 08:00:00 IST 2011
2305 | GI works for NC1 Barrette Removal | Mon Feb 28 08:00:00 IST 2011 | Thu Jun 02 17:00:00 IDT 2011
2306 | Group B Tree Transplant (T9752-54, UC0009-10) Preparation & Transplant | Mon Feb 28 08:00:00 IST 2011 | Sat Apr 30 17:00:00 IDT 2011
2307 | TTA Stage 1 and 2.1 | Thu Apr 14 08:00:00 IDT 2011 | Fri Jun 03 17:00:00 IDT 2011
2308 | ELS Works to Culvert Level | Sat May 07 08:00:00 IDT 2011 | Thu May 26 17:00:00 IDT 2011
2309 | Probing for Existing Barrettes | Thu Apr 14 08:00:00 IDT 2011 | Thu Apr 14 17:00:00 IDT 2011
2310 | Remove Top Slab of Culvert | Tue Nov 01 08:00:00 IST 2011 | Fri Nov 04 17:00:00 IST 2011
2311 | Cofferdam installation and Excavation at B27 | Mon Feb 27 08:00:00 IST 2012 | Sat Mar 17 17:00:00 IST 2012
2312 | Saw Cut Culvert Top Slab at B27 | Mon Mar 19 08:00:00 IST 2012 | Sat Mar 24 17:00:00 IST 2012
2313 | Temp. Working Platform for Barrette Removal | Mon Mar 26 08:00:00 IST 2012 | Sat Apr 14 17:00:00 IDT 2012
2314 | Barrette Removal (B27) | Wed Nov 14 08:00:00 IST 2012 | Wed Jan 02 17:00:00 IST 2013
2315 | Barrette Backfilling | Thu Jan 03 08:00:00 IST 2013 | Sat Jan 05 17:00:00 IST 2013
2316 | Reinstate Culvert Base Slab | Thu Nov 15 08:00:00 IST 2012 | Sat Jan 12 17:00:00 IST 2013
2317 | Barrette Removal (B28) | Wed Jan 04 08:00:00 IST 2012 | Wed Feb 22 17:00:00 IST 2012
2318 | Barrette Backfilling | Tue Nov 01 08:00:00 IST 2011 | Thu Nov 03 17:00:00 IST 2011
2319 | Reinstate Culvert Base Slab | Sat Nov 26 08:00:00 IST 2011 | Wed Dec 28 17:00:00 IST 2011
2320 | Install Temp.Cover at Culvert Top Slab | Tue Nov 01 08:00:00 IST 2011 | Wed Nov 30 17:00:00 IST 2011
2321 | Temp.Backfill & Reinstate Pavement | Tue Jun 21 08:00:00 IDT 2011 | Mon Jul 04 17:00:00 IDT 2011
2322 | TTA Stage 3 | Tue Jun 21 08:00:00 IDT 2011 | Wed Jun 22 17:00:00 IDT 2011
2323 | TBM U/T Culvert | Mon Feb 28 08:00:00 IST 2011 | Tue Sep 17 17:00:00 IDT 2013
2324 | Group B Tree Transplant (T9752-54,T8836-37, UC0009-10)Preparation & Transplant | Mon Feb 28 08:00:00 IST 2011 | Thu Apr 28 17:00:00 IDT 2011
2325 | Group D Tree Transplant (T8838,T8843-44) Preparation & Transplant | Mon Feb 28 08:00:00 IST 2011 | Wed Jun 29 17:00:00 IDT 2011
2326 | Tree Transplant Complete by 801 Designated Contractor | Mon Feb 28 08:00:00 IST 2011 | Mon Feb 28 08:00:00 IST 2011
2327 | TTMS Implementation | Mon Feb 28 08:00:00 IST 2011 | Sat Mar 05 17:00:00 IST 2011
2328 | Trial Trench to Expose Existing U/G Utiltiies | Mon Mar 07 08:00:00 IST 2011 | Sat Mar 19 17:00:00 IST 2011
2329 | Slew 132kV Cable (CLP207) | Thu Apr 21 08:00:00 IDT 2011 | Mon Aug 08 17:00:00 IDT 2011
2330 | Slew Telecom Cable (CATV206&PCCW203) | Tue May 03 08:00:00 IDT 2011 | Wed May 18 17:00:00 IDT 2011
2331 | Probing for Existing Barrettes | Mon Apr 11 08:00:00 IDT 2011 | Mon Apr 11 17:00:00 IDT 2011
2332 | ELS for Roof Access | Thu May 19 08:00:00 IDT 2011 | Wed Jun 15 17:00:00 IDT 2011
2333 | Remove Top Slab of Culvert | Mon Mar 28 08:00:00 IST 2011 | Sat Nov 05 17:00:00 IST 2011
2334 | Temp. Working Platform for Barrette Removal | Tue Nov 08 08:00:00 IST 2011 | Sat Nov 12 17:00:00 IST 2011
2335 | Barrette Removal (B24) | Tue Dec 06 08:00:00 IST 2011 | Fri Jan 13 17:00:00 IST 2012
2336 | Barrette Backfilling | Tue Nov 01 08:00:00 IST 2011 | Wed Nov 02 17:00:00 IST 2011
2337 | Reinstate Culvert Base Slab | Tue Nov 01 08:00:00 IST 2011 | Tue Nov 29 17:00:00 IST 2011
2338 | Remove Crane Platform & Reinstate Culvert Top Slab | Tue Jun 21 08:00:00 IDT 2011 | Mon Aug 08 17:00:00 IDT 2011
2339 | Slew 11kV Cable & Connection (CLP219) | Tue Jun 21 08:00:00 IDT 2011 | Mon Aug 01 17:00:00 IDT 2011
2340 | Divert 400D&315D Low Pressure Gas Main (GAS206&207) | Tue Jun 21 08:00:00 IDT 2011 | Thu Jul 14 17:00:00 IDT 2011
2341 | Divert 200D Freshwater Main (FW211) | Tue Jun 21 08:00:00 IDT 2011 | Wed Aug 03 17:00:00 IDT 2011
2342 | Divert 150D Saltwater Main (SW207) | Tue Jun 21 08:00:00 IDT 2011 | Mon Jun 27 17:00:00 IDT 2011
2343 | Slew 400kV Cable Group | Fri Jan 20 08:00:00 IST 2012 | Mon Jan 30 17:00:00 IST 2012
2344 | Preparation Work for TTMS Stage 4 | Mon Jan 30 08:00:00 IST 2012 | Thu Feb 09 17:00:00 IST 2012
2345 | Implement TTMS Stage 4 | Sat Feb 25 08:00:00 IST 2012 | Sat Feb 25 17:00:00 IST 2012
2346 | Drive Sheetpile for Barrette Removal (B21 & B22) | Sat Feb 25 08:00:00 IST 2012 | Fri Mar 02 17:00:00 IST 2012
2347 | ELS to Top Slab of Culvert | Sat Mar 17 08:00:00 IST 2012 | Thu Mar 29 17:00:00 IST 2012
2348 | Barrette Removal (B21) | Thu Nov 01 08:00:00 IST 2012 | Mon Nov 26 17:00:00 IST 2012
2349 | Barrette Backfilling | Wed Dec 19 08:00:00 IST 2012 | Wed Dec 19 17:00:00 IST 2012
2350 | Reinstate Culvert Base Slab | Tue Dec 11 08:00:00 IST 2012 | Sat Jan 12 17:00:00 IST 2013
2351 | Barrette Removal (B22) | Thu Nov 01 08:00:00 IST 2012 | Wed Dec 05 17:00:00 IST 2012
2352 | Barrette Backfilling | Thu Dec 06 08:00:00 IST 2012 | Fri Dec 07 17:00:00 IST 2012
2353 | Reinstate Culvert Base Slab | Tue Dec 11 08:00:00 IST 2012 | Sat Jan 12 17:00:00 IST 2013
2354 | 4nos.Pre-bored H Pile Installallation | Mon Jan 14 08:00:00 IST 2013 | Thu Feb 28 17:00:00 IST 2013
2355 | Band Beam Construction for Connect Pile & Box Culvert | Fri Mar 01 08:00:00 IST 2013 | Thu Mar 28 17:00:00 IST 2013
2356 | Tie-beam Curing & Load Transfer from Box Culvert to Temp.Pile | Tue Apr 02 08:00:00 IDT 2013 | Mon Apr 29 17:00:00 IDT 2013
2357 | Permanent Reinstate Culvert Top Slab | Tue Apr 30 08:00:00 IDT 2013 | Fri Aug 02 17:00:00 IDT 2013
2358 | Permanent Reinstatement for DN200 FW Main | Wed Nov 28 08:00:00 IST 2012 | Sat Jan 05 17:00:00 IST 2013
2359 | Permanent Reinstatement for DN400 Gas Main | Sat Dec 01 08:00:00 IST 2012 | Sat Dec 22 17:00:00 IST 2012
2360 | Permanent Reinstatement for CLP 11kV Cables | Mon Dec 24 08:00:00 IST 2012 | Wed Jan 23 17:00:00 IST 2013
2361 | Permanent Reinstatement for CLP 400kV Cables | Thu Jan 24 08:00:00 IST 2013 | Thu Feb 07 17:00:00 IST 2013
2362 | Permanent Reinstatement for Telecom Cables | Mon Mar 18 08:00:00 IST 2013 | Thu Mar 28 17:00:00 IST 2013
2363 | Backfilling & Road Reinstatement | Sat Aug 17 08:00:00 IDT 2013 | Tue Sep 17 17:00:00 IDT 2013
2364 | Completion | Fri Jun 01 08:00:00 IDT 2012 | Fri Jun 29 17:00:00 IDT 2012
2365 | Prepare & Submit Draft As-built Drawings | Fri Jun 01 08:00:00 IDT 2012 | Fri Jun 29 17:00:00 IDT 2012
2366 | Prepare & Submit As-built Drawings | Fri Jun 01 08:00:00 IDT 2012 | Fri Jun 29 17:00:00 IDT 2012
2367 | Box Culvert FS1 Barrettes Removal | Mon Feb 28 08:00:00 IST 2011 | Sat Oct 10 17:00:00 IDT 2015
2368 | Underpinning Works for FS1 / Barrettes Removal | Wed Aug 31 08:00:00 IDT 2011 | Tue Dec 06 17:00:00 IST 2011
2369 | Temp. Works Design Submission | Mon Feb 28 08:00:00 IST 2011 | Sun Jul 17 17:00:00 IDT 2011
2370 | Temp. Works Design Preparation | Mon Feb 28 08:00:00 IST 2011 | Wed Apr 13 17:00:00 IDT 2011
2371 | Temp. Works Design Submit to MTR | Mon Mar 28 08:00:00 IST 2011 | Mon Mar 28 08:00:00 IST 2011
2372 | Temp. Works Design Comment by MTR/DSD | Mon Mar 28 08:00:00 IST 2011 | Mon Apr 11 17:00:00 IDT 2011
2373 | Temp. Works Design Re-submission Preparation | Tue Apr 26 08:00:00 IDT 2011 | Sat May 14 17:00:00 IDT 2011
2374 | Temp. Works Design Comment & Approval by MTR/DSD | Thu May 19 08:00:00 IDT 2011 | Sun Jul 17 17:00:00 IDT 2011
2375 | Issue for Construction | Wed Jun 15 17:00:00 IDT 2011 | Wed Jun 15 17:00:00 IDT 2011
2376 | Method Statement Submission and Approval | Mon Feb 28 08:00:00 IST 2011 | Wed Jun 15 17:00:00 IDT 2011
2377 | MS Preparation | Mon Feb 28 08:00:00 IST 2011 | Wed Mar 30 17:00:00 IST 2011
2378 | MS Submission to MTR | Sat Mar 26 17:00:00 IST 2011 | Sat Mar 26 17:00:00 IST 2011
2379 | MS Comment by MTR/DSD | Sun Mar 27 08:00:00 IST 2011 | Fri Apr 22 17:00:00 IDT 2011
2380 | MS Re-submission Preparation | Tue Apr 26 08:00:00 IDT 2011 | Sat May 28 17:00:00 IDT 2011
2381 | MS Submission to MTR | Wed May 18 17:00:00 IDT 2011 | Wed May 18 17:00:00 IDT 2011
2382 | MS Comment & Approval by MTR/DSD | Thu May 19 08:00:00 IDT 2011 | Tue Jun 14 17:00:00 IDT 2011
2383 | Issue for Construction | Wed Jun 15 17:00:00 IDT 2011 | Wed Jun 15 17:00:00 IDT 2011
2384 | Utilities Diversion
2385 | Underpinning Works for FS1 | Fri May 06 17:00:00 IDT 2011 | Thu Aug 13 17:00:00 IDT 2015
2386 | Area 39.1 Tree Transplant by 801 Designated Contractor | Fri May 06 17:00:00 IDT 2011 | Fri May 06 17:00:00 IDT 2011
2387 | Soft Excavation to S1 (~+4.5mPD) | Tue Oct 18 08:00:00 IST 2011 | Fri Oct 21 17:00:00 IST 2011
2388 | Soft Excavation & Expose Culvert FS1(~-2.0mPD) | Wed Aug 31 08:00:00 IDT 2011 | Wed Sep 14 17:00:00 IDT 2011
2389 | Cast in-situ RC Wall to Support Existing Ground (adjacent B14 & B19) | Wed Aug 31 08:00:00 IDT 2011 | Mon Sep 05 17:00:00 IDT 2011
2390 | Setup & Install Four Prebored H-piles (adjacent to Existing B17) | Wed Aug 31 08:00:00 IDT 2011 | Thu Sep 15 17:00:00 IDT 2011
2391 | Soft Excavation to 2m underneath Culvert | Tue Sep 06 08:00:00 IDT 2011 | Mon Sep 19 17:00:00 IDT 2011
2392 | Installation of Corbel Beams either Side of Culvert | Wed Aug 31 08:00:00 IDT 2011 | Tue Sep 06 17:00:00 IDT 2011
2393 | Steel Beam Installation underneath Corbel Beams & Connect to H-pile | Wed Aug 31 08:00:00 IDT 2011 | Tue Sep 06 17:00:00 IDT 2011
2394 | Loading Transfer with Jacks | Wed Aug 31 08:00:00 IDT 2011 | Wed Aug 31 17:00:00 IDT 2011
2395 | Excavation to foundation level for B19 | Wed Aug 31 08:00:00 IDT 2011 | Fri Dec 16 17:00:00 IST 2011
2396 | Excavation to foundation level for B14 | Fri Feb 17 08:00:00 IST 2012 | Sat Jun 16 17:00:00 IDT 2012
2397 | Barettes Breaking (B15-B18) | Wed Aug 31 08:00:00 IDT 2011 | Wed Dec 14 17:00:00 IST 2011
2398 | Install Lagging Wall (at West & East D-wall) | Wed Aug 31 08:00:00 IDT 2011 | Fri Nov 11 17:00:00 IST 2011
2399 | Backfilling, Compaction & Testing | Sat Jul 11 08:00:00 IDT 2015 | Wed Aug 05 17:00:00 IDT 2015
2400 | Disconnected Steel H-pile inside Tunnel Box | Thu Aug 06 08:00:00 IDT 2015 | Thu Aug 13 17:00:00 IDT 2015
2401 | Completion | Fri Aug 14 08:00:00 IDT 2015 | Sat Oct 10 17:00:00 IDT 2015
2402 | Prepare & Submit Draft As-built Drawings | Fri Aug 14 08:00:00 IDT 2015 | Thu Sep 10 17:00:00 IDT 2015
2403 | Prepare & Submit As-built Drawings | Fri Sep 11 08:00:00 IDT 2015 | Sat Oct 10 17:00:00 IDT 2015
2404 | Cost Centre H - Piling Works to Footbridges | Mon Feb 28 08:00:00 IST 2011 | Mon Nov 23 17:00:00 IST 2015
2405 | IPS Milestones | Mon Feb 28 08:00:00 IST 2011 | Thu Sep 24 17:00:00 IDT 2015
2406 | General | Mon Feb 28 08:00:00 IST 2011 | Thu Sep 24 17:00:00 IDT 2015
2407 | Obtain SLG of TTMS for Footbridge Piling Start | Mon Feb 28 08:00:00 IST 2011 | Mon Feb 28 08:00:00 IST 2011
2408 | Complete 9% of Piles | Fri Nov 30 08:00:00 IST 2012 | Fri Nov 30 08:00:00 IST 2012
2409 | Complete 60% of Piles | Sat May 18 17:00:00 IDT 2013 | Sat May 18 17:00:00 IDT 2013
2410 | Complete 70% of Piles | Mon Jul 27 17:00:00 IDT 2015 | Mon Jul 27 17:00:00 IDT 2015
2411 | Complete 100% Piles except Pile cap 28 | Fri Jun 26 17:00:00 IDT 2015 | Fri Jun 26 17:00:00 IDT 2015
2412 | Complete All Works | Thu Sep 24 17:00:00 IDT 2015 | Thu Sep 24 17:00:00 IDT 2015
2413 | Construction | Mon Feb 28 08:00:00 IST 2011 | Mon Nov 23 17:00:00 IST 2015
2414 | Footbridge No.1 (Hing Wai St. West) | Fri Aug 31 08:00:00 IDT 2012 | Sat Sep 07 17:00:00 IDT 2013
2415 | Footbridge No.2 (Tonkin St. West) (2 out of 17 nos.) | Wed Sep 12 08:00:00 IDT 2012 | Wed Feb 13 17:00:00 IST 2013
2416 | Footbridge No.3 (Yen Chow St. West) | Mon May 06 08:00:00 IDT 2013 | Wed Dec 11 17:00:00 IST 2013
2417 | Method Statement Submission and Approval | Mon Feb 28 08:00:00 IST 2011 | Fri Jan 04 17:00:00 IST 2013
2418 | MS Preparation | Mon Feb 28 08:00:00 IST 2011 | Fri Mar 25 17:00:00 IST 2011
2419 | MS Submission to CEDD | Mon Mar 28 17:00:00 IST 2011 | Mon Mar 28 17:00:00 IST 2011
2420 | MS Comment by CEDD / Alt. Design Review with CEDD | Tue Mar 29 08:00:00 IST 2011 | Fri Apr 29 17:00:00 IDT 2011
2421 | MS Re-submission Preparation | Thu Nov 08 08:00:00 IST 2012 | Thu Dec 06 17:00:00 IST 2012
2422 | MS Submission to CEDD | Thu Dec 06 17:00:00 IST 2012 | Thu Dec 06 17:00:00 IST 2012
2423 | MS Comment & Approval by CEDD | Fri Dec 07 08:00:00 IST 2012 | Thu Jan 03 17:00:00 IST 2013
2424 | Issue for Construction | Fri Jan 04 17:00:00 IST 2013 | Fri Jan 04 17:00:00 IST 2013
2425 | TTM Scheme Submission & Approval | Mon Feb 28 08:00:00 IST 2011 | Mon Aug 22 17:00:00 IDT 2011
2426 | Prepare Temporary Traffic Management | Mon Feb 28 08:00:00 IST 2011 | Wed Mar 23 17:00:00 IST 2011
2427 | TTM reviewed by SLG | Sat Mar 26 08:00:00 IST 2011 | Fri Apr 29 17:00:00 IDT 2011
2428 | Resubmit TTM | Mon Feb 28 08:00:00 IST 2011 | Sat Apr 02 17:00:00 IDT 2011
2429 | TTM reviewed by SLG | Mon Feb 28 08:00:00 IST 2011 | Fri Apr 08 17:00:00 IDT 2011
2430 | Notification to RMO | Mon Feb 28 08:00:00 IST 2011 | Sun Aug 07 17:00:00 IDT 2011
2431 | XP Application & Approval | Thu Jun 02 08:00:00 IDT 2011 | Wed Jul 27 17:00:00 IDT 2011
2432 | Implement TTM | Mon Aug 22 17:00:00 IDT 2011 | Mon Aug 22 17:00:00 IDT 2011
2433 | Footbridge No.1 (Hing Wai St. West) | Mon Feb 28 08:00:00 IST 2011 | Fri May 24 17:00:00 IDT 2013
2434 | Temp.Traffic Diversion | Mon Feb 28 08:00:00 IST 2011 | Mon Mar 07 17:00:00 IST 2011
2435 | Temp. Pedestrians Barriers Erection | Mon Feb 28 08:00:00 IST 2011 | Mon Mar 07 17:00:00 IST 2011
2436 | Trial Trench & Record | Mon Feb 28 08:00:00 IST 2011 | Tue Aug 23 17:00:00 IDT 2011
2437 | Area A PC6, PC7 & PC8 | Fri Aug 31 08:00:00 IDT 2012 | Mon Apr 22 17:00:00 IDT 2013
2438 | Trial Pit | Fri Aug 31 08:00:00 IDT 2012 | Fri Sep 21 17:00:00 IDT 2012
2439 | Utilities Diversion | Sat Sep 22 08:00:00 IDT 2012 | Fri Sep 28 17:00:00 IST 2012
2440 | Confirmation of design by CEDD | Sat Jan 05 08:00:00 IST 2013 | Fri Jan 11 17:00:00 IST 2013
2441 | Implementation of TTMS & Site setup | Fri Jan 11 08:00:00 IST 2013 | Mon Jan 21 17:00:00 IST 2013
2442 | Piling works (18 nos. Pre-bored H-piles) | Mon Jan 21 08:00:00 IST 2013 | Mon Apr 22 17:00:00 IDT 2013
2443 | Area B PC4, PC5, PC10 & PC11 | Fri Dec 14 08:00:00 IST 2012 | Fri May 24 17:00:00 IDT 2013
2444 | Trial Pit | Fri Dec 14 08:00:00 IST 2012 | Fri Dec 21 17:00:00 IST 2012
2445 | Utilities Diversion | Sat Dec 22 08:00:00 IST 2012 | Wed Jan 02 17:00:00 IST 2013
2446 | Site setup | Thu Jan 03 08:00:00 IST 2013 | Sat Jan 05 17:00:00 IST 2013
2447 | Piling works (26 nos. Pre-bored H-piles) | Mon Jan 07 08:00:00 IST 2013 | Fri May 24 17:00:00 IDT 2013
2448 | Footbridge No.2 (Tonkin St. West) | Mon Feb 28 08:00:00 IST 2011 | Tue May 19 17:00:00 IDT 2015
2449 | Temp.Traffic Diversion | Mon Feb 28 08:00:00 IST 2011 | Tue Mar 08 17:00:00 IST 2011
2450 | Temp. Pedestrians Barriers Erection | Mon Feb 28 08:00:00 IST 2011 | Mon Mar 07 17:00:00 IST 2011
2451 | Trial Trench & Record | Mon Feb 28 08:00:00 IST 2011 | Sat Mar 12 17:00:00 IST 2011
2452 | Area C PC22, PC23 & PC24 | Wed Sep 12 08:00:00 IDT 2012 | Tue May 19 17:00:00 IDT 2015
2453 | Implementation of TTMS & Site Clearance | Wed Sep 12 08:00:00 IDT 2012 | Fri Sep 21 17:00:00 IDT 2012
2454 | Trial Pit | Fri Sep 21 08:00:00 IDT 2012 | Mon Oct 08 17:00:00 IST 2012
2455 | Utilities Diversion & Protection | Mon Oct 08 08:00:00 IST 2012 | Fri Oct 26 17:00:00 IST 2012
2456 | Site formation | Thu Nov 01 08:00:00 IST 2012 | Wed Nov 14 17:00:00 IST 2012
2457 | Site Setup | Wed Nov 14 08:00:00 IST 2012 | Tue Nov 20 17:00:00 IST 2012
2458 | FB2 - Piling works (2 nos. Pre-bored H-piles) | Sat Dec 01 08:00:00 IST 2012 | Fri Dec 14 17:00:00 IST 2012
2459 | FB2 - Piling works (6 nos. Pre-bored H-piles) | Mon Feb 09 08:00:00 IST 2015 | Tue May 19 17:00:00 IDT 2015
2460 | Footbridge No.3 (Yen Chow St.West) | Mon Feb 28 08:00:00 IST 2011 | Thu Sep 24 17:00:00 IDT 2015
2461 | Temp.Traffic Diversion | Mon Feb 28 08:00:00 IST 2011 | Mon Mar 07 17:00:00 IST 2011
2462 | Temp. Steel Decking & Barrier for Pedestrians | Mon Feb 28 08:00:00 IST 2011 | Mon Mar 07 17:00:00 IST 2011
2463 | Trial Trench & Record | Mon Feb 28 08:00:00 IST 2011 | Tue Jul 05 17:00:00 IDT 2011
2464 | Area D PC25, PC26 & PC27 | Mon Nov 12 08:00:00 IST 2012 | Fri May 31 17:00:00 IDT 2013
2465 | Implementation of TTMS & Site Clearance | Mon Nov 12 08:00:00 IST 2012 | Sat Nov 17 17:00:00 IST 2012
2466 | Trial pit to expose utilities | Mon Nov 19 08:00:00 IST 2012 | Sat Nov 24 17:00:00 IST 2012
2467 | Utilities Diversion & Protection | Fri Feb 15 08:00:00 IST 2013 | Sat Mar 02 17:00:00 IST 2013
2468 | Implementation of TTMS | Fri Feb 08 08:00:00 IST 2013 | Mon Mar 25 17:00:00 IST 2013
2469 | Site Setup | Fri Mar 01 08:00:00 IST 2013 | Fri Mar 08 17:00:00 IST 2013
2470 | FB3a - Piling works (8 nos. Pre-bored H-piles) | Tue Apr 02 08:00:00 IDT 2013 | Fri May 31 17:00:00 IDT 2013
2471 | Area E PC28 | Thu Aug 22 08:00:00 IDT 2013 | Thu Sep 24 17:00:00 IDT 2015
2472 | Implementation of TTMS | Thu Aug 22 08:00:00 IDT 2013 | Thu Aug 22 17:00:00 IDT 2013
2473 | Trial Pit | Fri Aug 23 08:00:00 IDT 2013 | Fri Sep 06 17:00:00 IDT 2013
2474 | Utilities Diversion & Protection | Sat Sep 07 08:00:00 IDT 2013 | Tue Sep 24 17:00:00 IDT 2013
2475 | Site formation [Pending for further instruction by MTR] | Mon Jun 01 08:00:00 IDT 2015 | Sat Jun 06 17:00:00 IDT 2015
2476 | Site Setup [Pending for further instruction by MTR] | Sat Jun 06 08:00:00 IDT 2015 | Mon Jun 15 17:00:00 IDT 2015
2477 | FB3b - Piling works (18 nos. Pre-bored H-piles) [Pending for further instruction by MTR] | Mon Jun 15 08:00:00 IDT 2015 | Thu Sep 24 17:00:00 IDT 2015
2478 | Completion | Fri Sep 25 08:00:00 IDT 2015 | Mon Nov 23 17:00:00 IST 2015
2479 | Prepare & Submit Draft As-built Drawings | Fri Sep 25 08:00:00 IDT 2015 | Mon Oct 26 17:00:00 IST 2015
2480 | Prepare & Submit As-built Drawings | Tue Oct 27 08:00:00 IST 2015 | Mon Nov 23 17:00:00 IST 2015
2481 | Cost Centre I3 (Option) HD's Entrustment Works - Carpark/Welfare Block | Sun May 31 08:00:00 IDT 2015 | Thu Apr 07 17:00:00 IDT 2016
2482 | IPS Milestones | Wed Nov 18 17:00:00 IST 2015 | Thu Feb 04 17:00:00 IST 2016
2483 | General | Wed Nov 18 17:00:00 IST 2015 | Thu Feb 04 17:00:00 IST 2016
2484 | Complete 50% Carpark/Welfare Facilities Podium Foundation | Wed Nov 18 17:00:00 IST 2015 | Wed Nov 18 17:00:00 IST 2015
2485 | Complete All Works | Thu Feb 04 17:00:00 IST 2016 | Thu Feb 04 17:00:00 IST 2016
2486 | Method Statement Submission and Approval | Tue Jun 30 08:00:00 IDT 2015 | Thu Oct 29 17:00:00 IST 2015
2487 | Method Statement Submission and Approval | Tue Jun 30 08:00:00 IDT 2015 | Thu Oct 29 17:00:00 IST 2015
2488 | MS Preparation | Tue Jun 30 08:00:00 IDT 2015 | Fri Jul 31 17:00:00 IDT 2015
2489 | MS Submission to MTR | Fri Jul 31 17:00:00 IDT 2015 | Fri Jul 31 17:00:00 IDT 2015
2490 | MS Comment by MTR | Sat Aug 01 08:00:00 IDT 2015 | Fri Aug 28 17:00:00 IDT 2015
2491 | MS Re-submission Preparation | Sat Aug 29 08:00:00 IDT 2015 | Wed Sep 30 17:00:00 IDT 2015
2492 | MS Submission to MTR | Wed Sep 30 17:00:00 IDT 2015 | Wed Sep 30 17:00:00 IDT 2015
2493 | MS Comment & Approval by MTR | Thu Oct 01 08:00:00 IDT 2015 | Wed Oct 28 17:00:00 IST 2015
2494 | Issue for Construction | Thu Oct 29 17:00:00 IST 2015 | Thu Oct 29 17:00:00 IST 2015
2495 | Construction | Sun May 31 08:00:00 IDT 2015 | Thu Apr 07 17:00:00 IDT 2016
2496 | Raft Footing Construction | Sun May 31 08:00:00 IDT 2015 | Thu Feb 04 17:00:00 IST 2016
2497 | Latest Exercising Date - Carpark/Welfare Block | Sun May 31 08:00:00 IDT 2015 | Sun May 31 08:00:00 IDT 2015
2498 | Raft Footing Construction | Fri Oct 30 08:00:00 IST 2015 | Thu Dec 10 17:00:00 IST 2015
2499 | U/G Drainage /Utilities | Fri Dec 11 08:00:00 IST 2015 | Sat Jan 09 17:00:00 IST 2016
2500 | Backfilling & Compaction (up to ground level +5.5mPD) | Mon Jan 11 08:00:00 IST 2016 | Thu Feb 04 17:00:00 IST 2016
2501 | Completion | Fri Feb 05 08:00:00 IST 2016 | Thu Apr 07 17:00:00 IDT 2016
2502 | Prepare & Submit Draft As-built Drawings | Fri Feb 05 08:00:00 IST 2016 | Mon Mar 07 17:00:00 IST 2016
2503 | Prepare & Submit As-built Drawings | Tue Mar 08 08:00:00 IST 2016 | Thu Apr 07 17:00:00 IDT 2016
2504 | Cost Centre I4 (Option) HD's Entrustment Works - Podium Shop | Sun May 31 08:00:00 IDT 2015 | Thu Feb 25 17:00:00 IST 2016
2505 | IPS Milestones | Sun Aug 02 17:00:00 IDT 2015 | Thu Dec 24 17:00:00 IST 2015
2506 | General | Sun Aug 02 17:00:00 IDT 2015 | Thu Dec 24 17:00:00 IST 2015
2507 | Complete 50% Podium Shop Foundation | Sun Aug 02 17:00:00 IDT 2015 | Sun Aug 02 17:00:00 IDT 2015
2508 | Complete All Works | Thu Dec 24 17:00:00 IST 2015 | Thu Dec 24 17:00:00 IST 2015
2509 | Method Statement Submission and Approval | Tue Jun 30 08:00:00 IDT 2015 | Thu Oct 29 17:00:00 IST 2015
2510 | Method Statement Submission and Approval | Tue Jun 30 08:00:00 IDT 2015 | Thu Oct 29 17:00:00 IST 2015
2511 | MS Preparation | Tue Jun 30 08:00:00 IDT 2015 | Fri Jul 31 17:00:00 IDT 2015
2512 | MS Submission to HD/ICU | Fri Jul 31 17:00:00 IDT 2015 | Fri Jul 31 17:00:00 IDT 2015
2513 | MS Comment by HD/ICU | Sat Aug 01 08:00:00 IDT 2015 | Fri Aug 28 17:00:00 IDT 2015
2514 | MS Re-submission Preparation | Sat Aug 29 08:00:00 IDT 2015 | Wed Sep 30 17:00:00 IDT 2015
2515 | MS Submission to HD/ICU | Wed Sep 30 17:00:00 IDT 2015 | Wed Sep 30 17:00:00 IDT 2015
2516 | MS Comment & Approval by HD/ICU | Thu Oct 01 08:00:00 IDT 2015 | Wed Oct 28 17:00:00 IST 2015
2517 | Issue for Construction | Thu Oct 29 17:00:00 IST 2015 | Thu Oct 29 17:00:00 IST 2015
2518 | Construction | Sun May 31 08:00:00 IDT 2015 | Thu Feb 25 17:00:00 IST 2016
2519 | General | Sun May 31 08:00:00 IDT 2015 | Thu Dec 24 17:00:00 IST 2015
2520 | Latest Exercising Date - Podium Shop | Sun May 31 08:00:00 IDT 2015 | Sun May 31 08:00:00 IDT 2015
2521 | Foundation Construction | Fri Oct 30 08:00:00 IST 2015 | Thu Nov 19 17:00:00 IST 2015
2522 | U/G Drainage /Utilities | Fri Nov 20 08:00:00 IST 2015 | Thu Dec 10 17:00:00 IST 2015
2523 | Backfilling & Compaction (up to ground level +5.5mPD) | Fri Dec 11 08:00:00 IST 2015 | Thu Dec 24 17:00:00 IST 2015
2524 | Completion | Mon Dec 28 08:00:00 IST 2015 | Thu Feb 25 17:00:00 IST 2016
2525 | Prepare & Submit Draft As-built Drawings | Mon Dec 28 08:00:00 IST 2015 | Mon Jan 25 17:00:00 IST 2016
2526 | Prepare & Submit As-built Drawings | Tue Jan 26 08:00:00 IST 2016 | Thu Feb 25 17:00:00 IST 2016
2527 | Cost Centre I5 (Option) HD's Entrustment Works - Bored Piles to Elevated Walkway | Mon Feb 28 08:00:00 IST 2011 | Thu May 01 17:00:00 IDT 2014
2528 | IPS Milestones | Tue Oct 08 17:00:00 IDT 2013 | Thu Oct 24 17:00:00 IDT 2013
2529 | General | Tue Oct 08 17:00:00 IDT 2013 | Thu Oct 24 17:00:00 IDT 2013
2530 | Complete 4 nos. of Bored Piles (4 of 5 piles) | Tue Oct 08 17:00:00 IDT 2013 | Tue Oct 08 17:00:00 IDT 2013
2531 | Complete All Works | Thu Oct 24 17:00:00 IDT 2013 | Thu Oct 24 17:00:00 IDT 2013
2532 | Method Statement Submission and Approval | Mon May 06 08:00:00 IDT 2013 | Thu Jul 25 17:00:00 IDT 2013
2533 | Method Statement Submission and Approval | Mon May 06 08:00:00 IDT 2013 | Thu Jul 25 17:00:00 IDT 2013
2534 | MS Preparation | Mon May 06 08:00:00 IDT 2013 | Wed Jun 05 17:00:00 IDT 2013
2535 | MS Submission to HD/ICU | Wed Jun 05 17:00:00 IDT 2013 | Wed Jun 05 17:00:00 IDT 2013
2536 | MS Comment by HD/ICU | Thu Jun 06 08:00:00 IDT 2013 | Wed Jul 03 17:00:00 IDT 2013
2537 | MS Re-submission Preparation | Fri Jun 14 08:00:00 IDT 2013 | Tue Jul 16 17:00:00 IDT 2013
2538 | MS Submission to HD/ICU | Thu Jun 27 17:00:00 IDT 2013 | Thu Jun 27 17:00:00 IDT 2013
2539 | MS Comment & Approval by HD/ICU | Fri Jun 28 08:00:00 IDT 2013 | Thu Jul 25 17:00:00 IDT 2013
2540 | Issue for Construction | Sat Jun 29 17:00:00 IDT 2013 | Sat Jun 29 17:00:00 IDT 2013
2541 | Construction | Mon Feb 28 08:00:00 IST 2011 | Thu May 01 17:00:00 IDT 2014
2542 | General | Mon Feb 28 08:00:00 IST 2011 | Thu May 01 17:00:00 IDT 2014
2543 | Latest Exercising Date - Bored Piles | Mon Feb 28 08:00:00 IST 2011 | Mon Feb 28 08:00:00 IST 2011
2544 | Diversion of existing drain | Mon May 06 08:00:00 IDT 2013 | Wed Jun 05 17:00:00 IDT 2013
2545 | 1st no. Bored Pile P6 Construction | Tue Jul 02 08:00:00 IDT 2013 | Wed Jul 31 17:00:00 IDT 2013
2546 | 2nd no. Bored Pile P3 Construction | Wed Jul 24 08:00:00 IDT 2013 | Thu Aug 22 17:00:00 IDT 2013
2547 | 3rd no. Bored Pile P5 Construction | Fri Aug 23 08:00:00 IDT 2013 | Mon Sep 23 17:00:00 IDT 2013
2548 | 4th no. Bored Pile P2 Construction | Fri Sep 06 08:00:00 IDT 2013 | Tue Oct 08 17:00:00 IDT 2013
2549 | Pile Testing | Tue Jul 02 08:00:00 IDT 2013 | Wed Oct 02 17:00:00 IDT 2013
2550 | 5th no. Bored Pile P4 Construction | Sat Sep 28 08:00:00 IDT 2013 | Mon Oct 28 17:00:00 IST 2013
2551 | Bored Piles & Pile Testing | Mon Oct 28 08:00:00 IST 2013 | Thu May 01 17:00:00 IDT 2014
2552 | Completion | Mon Dec 02 08:00:00 IST 2013 | Tue Dec 31 17:00:00 IST 2013
2553 | Prepare & Submit Draft As-built Drawings | Mon Dec 02 08:00:00 IST 2013 | Tue Dec 31 17:00:00 IST 2013
2554 | Prepare & Submit As-built Drawings | Mon Dec 02 08:00:00 IST 2013 | Tue Dec 31 17:00:00 IST 2013
2555 | Cost Centre J - Cut & Cover Tunnels At Hoi Ting Road Retrieval Shaft | Thu Nov 07 08:00:00 IST 2013 | Thu Aug 06 17:00:00 IDT 2015
2556 | Underground Drainage & Utilities | Mon Jul 07 08:00:00 IDT 2014 | Mon Sep 22 17:00:00 IDT 2014
2557 | IPS Milestones | Tue Apr 01 17:00:00 IDT 2014 | Thu Aug 06 17:00:00 IDT 2015
2558 | Complete Roof slab of Down track cut and cover tunnel | Tue Apr 01 17:00:00 IDT 2014 | Tue Apr 01 17:00:00 IDT 2014
2559 | Achieve Degree 1 completion for the Down track cut and cover tunnel | Thu May 15 17:00:00 IDT 2014 | Thu May 15 17:00:00 IDT 2014
2560 | Complete Roof slab of Up track cut and cover tunnel | Thu Feb 05 17:00:00 IST 2015 | Thu Feb 05 17:00:00 IST 2015
2561 | Achieve Degree 1 completion for the Up track cut and cover tunnel | Fri Mar 13 17:00:00 IST 2015 | Fri Mar 13 17:00:00 IST 2015
2562 | Complete backfill and reinstatement at Works Areas 12.2 and 13.48 | Thu Aug 06 17:00:00 IDT 2015 | Thu Aug 06 17:00:00 IDT 2015
2563 | Construction | Thu Nov 07 08:00:00 IST 2013 | Thu Aug 06 17:00:00 IDT 2015
2564 | Down Track Cut & Cover Tunnel | Thu Nov 07 08:00:00 IST 2013 | Thu May 22 17:00:00 IDT 2014
2565 | TBM (S630-1) Backup Removal D/T | Sun Nov 10 17:00:00 IST 2013 | Sun Nov 10 17:00:00 IST 2013
2566 | Mobilization and Site Preparation works | Thu Nov 07 08:00:00 IST 2013 | Sat Nov 30 17:00:00 IST 2013
2567 | Clear Backfilled B5 and Trim to Formation Level | Thu Nov 07 08:00:00 IST 2013 | Mon Nov 18 17:00:00 IST 2013
2568 | Drill holes for mass infill wall | Mon Nov 18 08:00:00 IST 2013 | Fri Nov 22 17:00:00 IST 2013
2569 | Construction of Mass Infill Wall | Sat Nov 23 08:00:00 IST 2013 | Fri Dec 13 17:00:00 IST 2013
2570 | Waterproofing to Interface of TBM Tunnel & 811A | Thu Dec 19 08:00:00 IST 2013 | Sat Dec 21 17:00:00 IST 2013
2571 | Construction of Base Slab | Tue Dec 24 08:00:00 IST 2013 | Tue Jan 14 17:00:00 IST 2014
2572 | Curing, CJ preparation & Dismantle base slab formwork | Sat Jan 25 08:00:00 IST 2014 | Thu Jan 30 17:00:00 IST 2014
2573 | Construction of Lower Portion Wall | Sat Jan 25 08:00:00 IST 2014 | Wed Feb 05 17:00:00 IST 2014
2574 | Curing, CJ preparation & Dismantle wall formwork | Fri Mar 07 08:00:00 IST 2014 | Wed Mar 12 17:00:00 IST 2014
2575 | Construction of Upper Portion Wall & Roof Slab | Fri Mar 07 08:00:00 IST 2014 | Sat Mar 29 17:00:00 IDT 2014
2576 | Curing for Upper Portion Wall & Roof Slab | Wed Apr 02 08:00:00 IDT 2014 | Tue Apr 15 17:00:00 IDT 2014
2577 | Dismantle falsework and formwork | Wed Apr 09 08:00:00 IDT 2014 | Mon Apr 14 17:00:00 IDT 2014
2578 | Construction of Walkway | Fri May 02 08:00:00 IDT 2014 | Thu May 22 17:00:00 IDT 2014
2579 | 811A C&C D/T- Degree 1 works | Wed Apr 09 08:00:00 IDT 2014 | Wed Apr 30 17:00:00 IDT 2014
2580 | Up Track Cut & Cover Tunnel | Wed Jul 02 08:00:00 IDT 2014 | Fri Mar 06 17:00:00 IST 2015
2581 | TBM (S630-1) & Backup Removal U/T | Wed Nov 19 17:00:00 IST 2014 | Wed Nov 19 17:00:00 IST 2014
2582 | Re-mobilization and Site Preparation works | Thu Nov 20 08:00:00 IST 2014 | Wed Nov 26 17:00:00 IST 2014
2583 | Clear Backfilled B5 and Trim to Formation Level | Wed Jul 02 08:00:00 IDT 2014 | Tue Jul 08 17:00:00 IDT 2014
2584 | Drill holes for mass infill wall | Thu Nov 27 08:00:00 IST 2014 | Tue Dec 02 17:00:00 IST 2014
2585 | Construction of Mass Infill Wall | Sat Jan 03 08:00:00 IST 2015 | Fri Jan 16 17:00:00 IST 2015
2586 | Waterproofing to Interface of TBM Tunnel & 811A | Wed Dec 17 08:00:00 IST 2014 | Fri Dec 19 17:00:00 IST 2014
2587 | Construction of Base Slab | Sat Dec 20 08:00:00 IST 2014 | Sat Jan 03 17:00:00 IST 2015
2588 | Curing, CJ preparation & Dismantle base slab formwork | Mon Jan 05 08:00:00 IST 2015 | Fri Jan 09 17:00:00 IST 2015
2589 | Construction of Lower Portion Wall | Fri Jan 09 08:00:00 IST 2015 | Thu Jan 15 17:00:00 IST 2015
2590 | Curing, CJ preparation & Dismantle wall formwork | Fri Jan 16 08:00:00 IST 2015 | Wed Jan 21 17:00:00 IST 2015
2591 | Construction of Upper Portion Wall & Roof Slab | Thu Jan 22 08:00:00 IST 2015 | Fri Feb 13 17:00:00 IST 2015
2592 | Curing for Upper Portion Wall & Roof Slab | Sat Jan 31 08:00:00 IST 2015 | Wed Feb 11 17:00:00 IST 2015
2593 | Dismantle falsework and formwork | Fri Feb 06 08:00:00 IST 2015 | Tue Feb 10 17:00:00 IST 2015
2594 | Construction of Walkway | Wed Feb 11 08:00:00 IST 2015 | Mon Mar 02 17:00:00 IST 2015
2595 | 811A C&C U/T- Degree 1 works (Target: 25Jan15) | Mon Feb 16 08:00:00 IST 2015 | Fri Mar 06 17:00:00 IST 2015
2596 | Backfilling & Re-instatement | Wed Mar 25 08:00:00 IST 2015 | Thu Aug 06 17:00:00 IDT 2015
2597 | D/T & U/T: Second Cast Concrete | Tue Jun 16 08:00:00 IDT 2015 | Wed Jul 08 17:00:00 IDT 2015
2598 | Backfilling to +4.5mPD | Wed Mar 25 08:00:00 IST 2015 | Sat May 16 17:00:00 IDT 2015
2599 | Re-instatement and Make Good | Sat Jul 25 08:00:00 IDT 2015 | Thu Aug 06 17:00:00 IDT 2015
2600 | Injection of PU grouting at the interface of TBM & C&C tunnel (both D/T & U/T) | Sat Jul 25 08:00:00 IDT 2015 | Thu Aug 06 17:00:00 IDT 2015
2601 | Backfilling from +4.5mPD to Ground Level | Thu Jul 09 08:00:00 IDT 2015 | Fri Jul 24 17:00:00 IDT 2015
1 | 820 As-built Programme | Wed May 12 08:00:00 IDT 2010 | Tue May 10 17:00:00 IDT 2016
2 | General | Sat Jan 08 08:00:00 IST 2011 | Tue Jan 26 17:00:00 IST 2016
3 | Schedule of Key Dates | Sat Jan 08 08:00:00 IST 2011 | Tue Jan 26 17:00:00 IST 2016
4 | General | Sat Jan 08 08:00:00 IST 2011 | Tue Jan 26 17:00:00 IST 2016
5 | Letter of Acceptance | Sat Jan 08 08:00:00 IST 2011 | Sat Jan 08 08:00:00 IST 2011
6 | Date of Commencement | Sat Jan 08 08:00:00 IST 2011 | Sat Jan 08 08:00:00 IST 2011
7 | Completion whole of the Works (Excluding Options I3 & I4) | Sun May 10 17:00:00 IDT 2015 | Sun May 10 17:00:00 IDT 2015
8 | Completion whole of the Works (Including Options I3 & I4) | Tue Jan 26 17:00:00 IST 2016 | Tue Jan 26 17:00:00 IST 2016
9 | Table 4 - Specified Degress of completion of the Works | Sun Aug 18 17:00:00 IDT 2013 | Sun Apr 19 17:00:00 IDT 2015
10 | Target Dates for Supplementary Agreement No.3 | Sun May 18 17:00:00 IDT 2014 | Sun Apr 19 17:00:00 IDT 2015
11 | Deg.1 Completion (Target Dates) | Sun May 18 17:00:00 IDT 2014 | Sun Apr 19 17:00:00 IDT 2015
12 | Ref.4A(ii): D/TTunnel from CH137+860 to Southern Contract Limit & 811A D/T C&C Section(Deg.1:20-Jul-14&Target:18-May-14) | Sun May 18 17:00:00 IDT 2014 | Sun May 18 17:00:00 IDT 2014
13 | Ref.4B(i): Up Track tunnel from the Northern Contract Limit to CH137+860 (Deg.1: 29-Jun-14 & Target: 1-Jun-14) | Sun Jun 29 08:00:00 IDT 2014 | Sun Jun 29 08:00:00 IDT 2014
14 | Ref.4B(ii): U/T South Tunnel from CH137+860 to 950m from the Southern Contract Limit (Deg.1: 8Mar15 & Target: 21Dec14) | Tue Dec 16 17:00:00 IST 2014 | Tue Dec 16 17:00:00 IST 2014
15 | Ref.4B(iii): U/T Tunnel from CH137+860 to Southern Contract Limit & 811A U/T C&C Section(Deg.1: 12Apr15&Target: 25Jan15) | Fri Mar 13 17:00:00 IST 2015 | Fri Mar 13 17:00:00 IST 2015
16 | Ref.4D: Closure of Temp. Access Opening & Central Opening Structure within NAC Shaft (Deg.1: 3May15 & Target: 19Apr15) | Sun Apr 19 17:00:00 IDT 2015 | Sun Apr 19 17:00:00 IDT 2015
17 | Completion of Specified Degrees of Completion of the Works | Sun Aug 18 17:00:00 IDT 2013 | Sun Apr 19 17:00:00 IDT 2015
18 | Deg.1 Completion | Sun Aug 18 17:00:00 IDT 2013 | Sun Apr 19 17:00:00 IDT 2015
19 | Ref.4A(i): Down Track tunnel from the Northern Contract Limit to CH137+860 incl. provision of Temp. access opening | Sun Aug 18 17:00:00 IDT 2013 | Sun Aug 18 17:00:00 IDT 2013
20 | Ref.4C(i): All Rooms and Common Areas at Level L2, UL2, L1 and UL1 (Excl. staircases, Lift shaft & CLP risers) | Sun Dec 22 17:00:00 IST 2013 | Sun Dec 22 17:00:00 IST 2013
21 | Ref.4C(ii): All Rooms and Common Areas at Track level and Above Track level(Excl. staircases, Lift shaft & CLP risers) | Sun Mar 02 17:00:00 IST 2014 | Sun Mar 02 17:00:00 IST 2014
22 | Ref.4C(iii): All Rooms and Common Areas within VB7 [Excl. the parts of the VB7 under Ref. 4C(i) & 4C(ii)] | Sat May 31 17:00:00 IDT 2014 | Sat May 31 17:00:00 IDT 2014
23 | Ref.4B(i): Up Track tunnel from the Northern Contract Limit to CH137+860 (Deg.1: 29-Jun-14 & Target: 1-Jun-14) | Sun Jun 29 17:00:00 IDT 2014 | Sun Jun 29 17:00:00 IDT 2014
24 | Ref.4A(ii): D/TTunnel from CH137+860 to Southern Contract Limit & 811A D/T C&C Section(Deg.1:20-Jul-14&Target:18-May-14) | Sun May 18 17:00:00 IDT 2014 | Sun May 18 17:00:00 IDT 2014
25 | Ref.4B(ii): U/T South Tunnel from CH137+860 to 950m from the Southern Contract Limit (Deg.1: 8Mar15 & Target: 21Dec14) | Tue Dec 16 17:00:00 IST 2014 | Tue Dec 16 17:00:00 IST 2014
26 | Ref.4B(iii): U/T Tunnel from CH137+860 to Southern Contract Limit & 811A U/T C&C Section(Deg.1: 12Apr15&Target: 25Jan15) | Fri Mar 13 17:00:00 IST 2015 | Fri Mar 13 17:00:00 IST 2015
27 | Ref.4D: Closure of Temp. Access Opening & Central Opening Structure within NAC Shaft (Deg.1: 3May15 & Target: 19Apr15) | Sun Apr 19 17:00:00 IDT 2015 | Sun Apr 19 17:00:00 IDT 2015
28 | Deg.2 Completion | Sun Feb 23 17:00:00 IST 2014 | Wed Jul 23 17:00:00 IDT 2014
29 | Ref.4C(i) Deg.2: All Rooms and Common Areas at Level L2, UL2, L1 and UL1 (Excl. staircases, Lift shaft & CLP risers) | Sun Feb 23 17:00:00 IST 2014 | Sun Feb 23 17:00:00 IST 2014
30 | Ref.4C(ii) Deg.2: All Rooms and Common Areas at Track level and AT level(Excl. staircases, Lift shaft & CLP risers) | Sun Mar 23 17:00:00 IST 2014 | Sun Mar 23 17:00:00 IST 2014
31 | Ref.4C(iii) Deg.2: All Rooms and Common Areas within VB7 [Excl. the parts of the VB7 under Ref. 4C(i) & 4C(ii)] | Wed Jul 23 17:00:00 IDT 2014 | Wed Jul 23 17:00:00 IDT 2014
32 | Deg.3 Completion | Sun Apr 20 17:00:00 IDT 2014 | Thu Sep 18 17:00:00 IDT 2014
33 | Ref.4C(i) Deg.3: All Rooms and Common Areas at Level L1, UL2, L1 and UL1 (Excl. staircases, Lift shaft & CLP risers) | Sun Apr 20 17:00:00 IDT 2014 | Sun Apr 20 17:00:00 IDT 2014
34 | Ref.4C(ii) Deg.3: All Rooms and Common Areas at Track level and AT level(Excl. staircases, Lift shaft & CLP risers) | Sun May 18 17:00:00 IDT 2014 | Sun May 18 17:00:00 IDT 2014
35 | Ref.4C(iii) Deg.3: All Rooms and Common Areas within VB7 [Excl. the parts of the VB7 under Ref. 4C(i) & 4C(ii)] | Thu Sep 18 17:00:00 IDT 2014 | Thu Sep 18 17:00:00 IDT 2014
36 | Schedule of Access Dates and Vacation Dates | Sat May 15 08:00:00 IDT 2010 | Tue May 10 17:00:00 IDT 2016
37 | Access Date | Sat May 15 08:00:00 IDT 2010 | Mon Jan 21 08:00:00 IST 2013
38 | General | Sat May 15 08:00:00 IDT 2010 | Mon Jan 21 08:00:00 IST 2013
39 | Works Area 10.1 (Subject to SLG Approval) | Sat Jan 08 08:00:00 IST 2011 | Sat Jan 08 08:00:00 IST 2011
40 | Works Area 10.2 | Sat Jan 08 08:00:00 IST 2011 | Sat Jan 08 08:00:00 IST 2011
41 | Works Area 10.3 | Sat Jan 08 08:00:00 IST 2011 | Sat Jan 08 08:00:00 IST 2011
42 | Works Area 10.3U subject to MTR Railway Operation Approval | Thu Sep 29 08:00:00 IDT 2011 | Thu Sep 29 08:00:00 IDT 2011
43 | Works Area 10.4 | Sat Jan 08 08:00:00 IST 2011 | Sat Jan 08 08:00:00 IST 2011
44 | Works Area 11.1 | Mon Apr 09 08:00:00 IDT 2012 | Mon Apr 09 08:00:00 IDT 2012
45 | Works Area 11.2 | Mon Apr 09 08:00:00 IDT 2012 | Mon Apr 09 08:00:00 IDT 2012
46 | Works Area 11.10A | Mon Feb 06 08:00:00 IST 2012 | Mon Feb 06 08:00:00 IST 2012
47 | Works Area 11.10B | Mon Feb 06 08:00:00 IST 2012 | Mon Feb 06 08:00:00 IST 2012
48 | Works Area 11.12 (Subject to SLG Approval) | Sat Jan 08 08:00:00 IST 2011 | Sat Jan 08 08:00:00 IST 2011
49 | Works Area 11.13 (conform by Engineer) | Mon Dec 31 08:00:00 IST 2012 | Mon Dec 31 08:00:00 IST 2012
50 | Works Area 11.14 | Mon Dec 10 08:00:00 IST 2012 | Mon Dec 10 08:00:00 IST 2012
51 | Works Area 11.15 (Subject to SLG Approval) | Sat Jan 08 08:00:00 IST 2011 | Sat Jan 08 08:00:00 IST 2011
52 | Works Area 11.21 (Subject to SLG Approval) | Sat Jan 08 08:00:00 IST 2011 | Sat Jan 08 08:00:00 IST 2011
53 | Works Area 11.21A (Subject to SLG Approval) | Wed Aug 31 08:00:00 IDT 2011 | Wed Aug 31 08:00:00 IDT 2011
54 | Works Area 11.22 | Sat Jan 08 08:00:00 IST 2011 | Sat Jan 08 08:00:00 IST 2011
55 | Works Area 11.23 | Sat Jan 08 08:00:00 IST 2011 | Sat Jan 08 08:00:00 IST 2011
56 | Works Area 11.23A | Sat Jan 08 08:00:00 IST 2011 | Sat Jan 08 08:00:00 IST 2011
57 | Works Area 11.23B | Sat Jan 08 08:00:00 IST 2011 | Sat Jan 08 08:00:00 IST 2011
58 | Works Area 11.24 (1st Possession) | Sat Jan 08 08:00:00 IST 2011 | Sat Jan 08 08:00:00 IST 2011
59 | Works Area 11.25 (1st Posssession) | Sat Jan 08 08:00:00 IST 2011 | Sat Jan 08 08:00:00 IST 2011
60 | Works Area 11.26A | Sat Jan 08 08:00:00 IST 2011 | Sat Jan 08 08:00:00 IST 2011
61 | Works Area 11.26B | Sat Jan 08 08:00:00 IST 2011 | Sat Jan 08 08:00:00 IST 2011
62 | Works Area 11.26C | Sat Jan 08 08:00:00 IST 2011 | Sat Jan 08 08:00:00 IST 2011
63 | Works Area 11.27 (Subject to SLG Approval) | Sat Jan 08 08:00:00 IST 2011 | Sat Jan 08 08:00:00 IST 2011
64 | Wks Area 11.28-180day from Contractor's Confirm | Mon Jan 21 08:00:00 IST 2013 | Mon Jan 21 08:00:00 IST 2013
65 | Works Area 11.29A | Sat Jan 08 08:00:00 IST 2011 | Sat Jan 08 08:00:00 IST 2011
66 | Works Area 11.29B | Sat Jan 08 08:00:00 IST 2011 | Sat Jan 08 08:00:00 IST 2011
67 | Works Area 11.29C | Sat May 15 08:00:00 IDT 2010 | Sat May 15 08:00:00 IDT 2010
68 | Works Area 11.29D | Sat May 15 08:00:00 IDT 2010 | Sat May 15 08:00:00 IDT 2010
69 | Works Area 11.29E | Sat May 15 08:00:00 IDT 2010 | Sat May 15 08:00:00 IDT 2010
70 | Works Area 11.29F | Sat May 15 08:00:00 IDT 2010 | Sat May 15 08:00:00 IDT 2010
71 | Works Area 11.29G | Sat May 15 08:00:00 IDT 2010 | Sat May 15 08:00:00 IDT 2010
72 | Works Area 11.30 | Sat May 15 08:00:00 IDT 2010 | Sat May 15 08:00:00 IDT 2010
73 | Works Area 11.31 | Sat May 15 08:00:00 IDT 2010 | Sat May 15 08:00:00 IDT 2010
74 | Works Area 11.32 | Sat May 15 08:00:00 IDT 2010 | Sat May 15 08:00:00 IDT 2010
75 | Works Area 11.33A | Sat May 15 08:00:00 IDT 2010 | Sat May 15 08:00:00 IDT 2010
76 | Works Area 11.33B | Sat May 15 08:00:00 IDT 2010 | Sat May 15 08:00:00 IDT 2010
77 | Works Area 12.1 (Subject to SLG Approval) | Sat Jan 08 08:00:00 IST 2011 | Sat Jan 08 08:00:00 IST 2011
78 | Works Area 12.2 | Fri Nov 30 08:00:00 IST 2012 | Fri Nov 30 08:00:00 IST 2012
79 | Proposed Return Date | Sun May 31 08:00:00 IDT 2015 | Thu Dec 24 17:00:00 IST 2015
80 | Site 6 | Thu Dec 24 17:00:00 IST 2015 | Thu Dec 24 17:00:00 IST 2015
81 | Proposed Return date of Works Area 11.23 (820 Site Office & Site 6) | Thu Dec 24 17:00:00 IST 2015 | Thu Dec 24 17:00:00 IST 2015
82 | Proposed Return date of Works Area 11.23A (Site 6) | Thu Dec 24 17:00:00 IST 2015 | Thu Dec 24 17:00:00 IST 2015
83 | Proposed Return date of Works Area 11.23B (Site 6) | Thu Dec 24 17:00:00 IST 2015 | Thu Dec 24 17:00:00 IST 2015
84 | Proposed Return date of Works Area 11.24 (Site 6) | Thu Dec 24 17:00:00 IST 2015 | Thu Dec 24 17:00:00 IST 2015
85 | Barging Point | Sun May 31 08:00:00 IDT 2015 | Sun May 31 08:00:00 IDT 2015
86 | Proposed Return date of Works Area 11.29A (Barging point) | Sun May 31 08:00:00 IDT 2015 | Sun May 31 08:00:00 IDT 2015
87 | Proposed Return date of Works Area 11.29D (Barging point) | Sun May 31 08:00:00 IDT 2015 | Sun May 31 08:00:00 IDT 2015
88 | Proposed Return date of Works Area 11.29E (Barging point) | Sun May 31 08:00:00 IDT 2015 | Sun May 31 08:00:00 IDT 2015
89 | Proposed Return date of Works Area 11.29F (Barging point) | Sun May 31 08:00:00 IDT 2015 | Sun May 31 08:00:00 IDT 2015
90 | 811A Shaft | Thu Aug 27 17:00:00 IDT 2015 | Thu Aug 27 17:00:00 IDT 2015
91 | Proposed Return date of Works Area 12.2 (811A shaft area) | Thu Aug 27 17:00:00 IDT 2015 | Thu Aug 27 17:00:00 IDT 2015
92 | Return date | Mon Feb 28 08:00:00 IST 2011 | Tue May 10 17:00:00 IDT 2016
93 | General | Mon Feb 28 08:00:00 IST 2011 | Tue May 10 17:00:00 IDT 2016
94 | Works Area 10.1 (Subject to SLG Approval) | Sun May 31 08:00:00 IDT 2015 | Sun May 31 08:00:00 IDT 2015
95 | Works Area 10.2 | Sun May 31 08:00:00 IDT 2015 | Sun May 31 08:00:00 IDT 2015
96 | Works Area 10.3 | Sun May 31 08:00:00 IDT 2015 | Sun May 31 08:00:00 IDT 2015
97 | Works Area 10.3U subject to MTR Approval | Sun May 31 08:00:00 IDT 2015 | Sun May 31 08:00:00 IDT 2015
98 | Works Area 10.4 | Sun May 31 08:00:00 IDT 2015 | Sun May 31 08:00:00 IDT 2015
99 | Works Area 11.1 (Nan cheong Station - by XRL802) | Sun Dec 30 17:00:00 IST 2012 | Sun Dec 30 17:00:00 IST 2012
100 | Works Area 11.2 (Nan cheong Station - by XRL802) | Sun Dec 30 17:00:00 IST 2012 | Sun Dec 30 17:00:00 IST 2012
101 | Works Area 11.10A | Tue Sep 10 17:00:00 IDT 2013 | Tue Sep 10 17:00:00 IDT 2013
102 | Works Area 11.10B | Sun May 31 08:00:00 IDT 2015 | Sun May 31 08:00:00 IDT 2015
103 | Works Area 11.12 (Subject to SLG Approval) | Sun May 31 08:00:00 IDT 2015 | Sun May 31 08:00:00 IDT 2015
104 | Works Area 11.13 (Earliest) | Sun Dec 29 17:00:00 IST 2013 | Sun Dec 29 17:00:00 IST 2013
105 | Works Area 11.13 (Latest) | Sun May 31 08:00:00 IDT 2015 | Sun May 31 08:00:00 IDT 2015
106 | Works Area 11.14 | Sun May 31 08:00:00 IDT 2015 | Sun May 31 08:00:00 IDT 2015
107 | Works Area 11.15 (Subject to SLG Approval) | Sun May 31 08:00:00 IDT 2015 | Sun May 31 08:00:00 IDT 2015
108 | Works Area 11.21 (Subject to SLG Approval) | Sun May 31 08:00:00 IDT 2015 | Sun May 31 08:00:00 IDT 2015
109 | Works Area 11.21A (Subject to SLG Approval) | Sun May 31 08:00:00 IDT 2015 | Sun May 31 08:00:00 IDT 2015
110 | Works Area 11.22 | Sun Dec 27 17:00:00 IST 2015 | Sun Dec 27 17:00:00 IST 2015
111 | Works Area 11.23 (Site 6) | Sun May 31 08:00:00 IDT 2015 | Sun May 31 08:00:00 IDT 2015
112 | Works Area 11.23A (Site 6) (excl. Optional Works I3 & I4) | Mon Aug 24 17:00:00 IDT 2015 | Mon Aug 24 17:00:00 IDT 2015
113 | Works Area 11.23B (Site 6) (excl. Optional Works I3 & I4) | Mon Aug 24 17:00:00 IDT 2015 | Mon Aug 24 17:00:00 IDT 2015
114 | Works Area 11.24 (Site 6) (Earliest) | Sun Mar 31 17:00:00 IDT 2013 | Sun Mar 31 17:00:00 IDT 2013
115 | Works Area 11.24 (Site 6) (Latest) | Mon Aug 24 17:00:00 IDT 2015 | Mon Aug 24 17:00:00 IDT 2015
116 | Works Area 11.25 (Site 6) (Earliest) | Sun Mar 31 17:00:00 IDT 2013 | Sun Mar 31 17:00:00 IDT 2013
117 | Works Area 11.25 (Latest) | Sun Apr 03 17:00:00 IDT 2016 | Sun Apr 03 17:00:00 IDT 2016
118 | Works Area 11.26A (excl. Optional Works I3 & I4) | Sun Apr 03 17:00:00 IDT 2016 | Sun Apr 03 17:00:00 IDT 2016
119 | Works Area 11.26B | Sun Apr 03 17:00:00 IDT 2016 | Sun Apr 03 17:00:00 IDT 2016
120 | Works Area 11.26C | Sun Apr 03 17:00:00 IDT 2016 | Sun Apr 03 17:00:00 IDT 2016
121 | Works Area 11.27 (Subject to SLG Approval) | Tue Aug 11 17:00:00 IDT 2015 | Tue Aug 11 17:00:00 IDT 2015
122 | Wks Area 11.28 | Sun May 31 08:00:00 IDT 2015 | Sun May 31 08:00:00 IDT 2015
123 | Works Area 11.29A | Sun May 31 08:00:00 IDT 2015 | Sun May 31 08:00:00 IDT 2015
124 | Works Area 11.29B | Mon Feb 28 08:00:00 IST 2011 | Mon Feb 28 08:00:00 IST 2011
125 | Works Area 11.29C | Mon Feb 28 08:00:00 IST 2011 | Mon Feb 28 08:00:00 IST 2011
126 | Works Area 11.29D | Sun May 31 08:00:00 IDT 2015 | Sun May 31 08:00:00 IDT 2015
127 | Works Area 11.29E | Sun May 31 08:00:00 IDT 2015 | Sun May 31 08:00:00 IDT 2015
128 | Works Area 11.29F | Sun May 31 08:00:00 IDT 2015 | Sun May 31 08:00:00 IDT 2015
129 | Works Area 11.29G | Mon Feb 28 08:00:00 IST 2011 | Mon Feb 28 08:00:00 IST 2011
130 | Works Area 11.30 | Sun Dec 29 17:00:00 IST 2013 | Sun Dec 29 17:00:00 IST 2013
131 | Works Area 11.31 | Sun May 31 08:00:00 IDT 2015 | Sun May 31 08:00:00 IDT 2015
132 | Works Area 11.32 | Sun May 31 08:00:00 IDT 2015 | Sun May 31 08:00:00 IDT 2015
133 | Works Area 11.33A | Tue May 10 17:00:00 IDT 2016 | Tue May 10 17:00:00 IDT 2016
134 | Works Area 11.33B | Tue May 10 17:00:00 IDT 2016 | Tue May 10 17:00:00 IDT 2016
135 | Works Area 12.1 (Subject to SLG Approval) | Tue May 10 17:00:00 IDT 2016 | Tue May 10 17:00:00 IDT 2016
136 | Works Area 12.2 (811A shaft area) | Sun May 31 08:00:00 IDT 2015 | Sun May 31 08:00:00 IDT 2015
137 | Access & Return Dates for Option I3 & I4 | Sat Jan 08 08:00:00 IST 2011 | Sun Apr 03 17:00:00 IDT 2016
138 | General | Sat Jan 08 08:00:00 IST 2011 | Sun Apr 03 17:00:00 IDT 2016
139 | Works Area 11.23B | Sat Jan 08 08:00:00 IST 2011 | Sat Jan 08 08:00:00 IST 2011
140 | Works Area 11.26A | Sat Jan 08 08:00:00 IST 2011 | Sat Jan 08 08:00:00 IST 2011
141 | Works Area 11.26B | Sat Jan 08 08:00:00 IST 2011 | Sat Jan 08 08:00:00 IST 2011
142 | Works Area 11.23B | Sun Nov 22 17:00:00 IST 2015 | Sun Nov 22 17:00:00 IST 2015
143 | Works Area 11.26A | Sun Apr 03 17:00:00 IDT 2016 | Sun Apr 03 17:00:00 IDT 2016
144 | Works Area 11.26B | Sun Apr 03 17:00:00 IDT 2016 | Sun Apr 03 17:00:00 IDT 2016
145 | Programme Data | Mon Feb 28 08:00:00 IST 2011 | Fri Jul 24 17:00:00 IDT 2015
146 | Schedule of Power On Dates | Thu Feb 05 17:00:00 IST 2015 | Thu Feb 05 17:00:00 IST 2015
147 | Permanent LV Power On | Thu Feb 05 17:00:00 IST 2015 | Thu Feb 05 17:00:00 IST 2015
148 | General
149 | Works Required for Statutory Inspection | Fri Jul 24 17:00:00 IDT 2015 | Fri Jul 24 17:00:00 IDT 2015
150 | Complete all External Water works within the Site and Connect to Governemnt Water Mains | Fri Jul 24 17:00:00 IDT 2015 | Fri Jul 24 17:00:00 IDT 2015
151 | Complete all External Telephone Drawpits and Ducts within the Site | Fri Jul 24 17:00:00 IDT 2015 | Fri Jul 24 17:00:00 IDT 2015
152 | General
153 | Temporary Access Opening for Designated Contractors | Mon Aug 26 08:00:00 IDT 2013 | Sun Jan 04 17:00:00 IST 2015
154 | Access Central Opening within Launching Shaft | Mon Aug 26 08:00:00 IDT 2013 | Sun Jan 04 17:00:00 IST 2015
155 | General
156 | Close out Temporary Access Opening & Structure within Launching Shaft | Sun Dec 01 08:00:00 IST 2013 | Sun May 31 08:00:00 IDT 2015
157 | Area 1 - South Opening, South D/T | Sun Dec 01 08:00:00 IST 2013 | Sun May 18 17:00:00 IDT 2014
158 | Area 1 - Walkway, Side Walls and Above-Track Roof Slab | Sun Dec 01 08:00:00 IST 2013 | Sun May 18 17:00:00 IDT 2014
159 | Area 2 - Central Opening, South D/T | Mon May 19 08:00:00 IDT 2014 | Sun Jun 15 17:00:00 IDT 2014
160 | Area 2 - 1st cast for Walkway and External wall (Dkb137+850 to 137+885) | Mon May 19 08:00:00 IDT 2014 | Sun Jun 15 17:00:00 IDT 2014
161 | Area 3 - South Opening, South U/T | Mon Sep 01 08:00:00 IDT 2014 | Sun Dec 21 17:00:00 IST 2014
162 | Area 3 - 1st cast for Walkway, External wall and Internal wall | Mon Sep 01 08:00:00 IDT 2014 | Sun Dec 21 17:00:00 IST 2014
163 | Area 3 - 2nd cast for Above-Track Roof Slab | Sat Nov 15 08:00:00 IST 2014 | Fri Dec 19 17:00:00 IST 2014
164 | Area 4A - Central Opening, South U/T | Mon Dec 29 08:00:00 IST 2014 | Sun Jan 25 17:00:00 IST 2015
165 | Area 4A - Walkway and External wall (Dkb137+850 to 137+885) | Mon Dec 29 08:00:00 IST 2014 | Sun Jan 25 17:00:00 IST 2015
166 | Area 4B - Central Opening | Mon Dec 29 08:00:00 IST 2014 | Sun Feb 08 17:00:00 IST 2015
167 | Area 4B - 2nd cast for Internal walls and Central portion of Above-Track Roof Slab with falsework | Mon Dec 29 08:00:00 IST 2014 | Sun Feb 08 17:00:00 IST 2015
168 | Area 4C - Central Opening and Access for 830 Works Train | Mon Dec 29 08:00:00 IST 2014 | Sun Apr 19 17:00:00 IDT 2015
169 | Area 4C - Close remaining Above-Track Roof Slab & RC duct btw Dkb137+850 to 137+885 | Mon Dec 29 08:00:00 IST 2014 | Sun Apr 19 17:00:00 IDT 2015
170 | Site 6 - Surafce Works Area under 30T Gantry Crane at Central Opening | Sun May 31 08:00:00 IDT 2015 | Sun May 31 08:00:00 IDT 2015
171 | Site 6 - Access to works area under 30T gantry to be given to 830 | Sun May 31 08:00:00 IDT 2015 | Sun May 31 08:00:00 IDT 2015
172 | Area 5 - 811A C&C Tunnel
173 | TBM Retrieval Shaft at Hoi Ting Road | Mon Feb 28 08:00:00 IST 2011 | Sun Jun 19 17:00:00 IDT 2011
174 | General | Mon Feb 28 08:00:00 IST 2011 | Sun Jun 19 17:00:00 IDT 2011
175 | Completion D-Wall of TBM Retrieval Shaft at Hoi Ting Rd. by 811A | Mon Feb 28 08:00:00 IST 2011 | Mon Feb 28 08:00:00 IST 2011
176 | Earliest Access Date - Ground Level of Works Area 12.2 | Mon Feb 28 08:00:00 IST 2011 | Mon Feb 28 08:00:00 IST 2011
177 | Ground Treatment Completion by 820 | Sun Jun 19 17:00:00 IDT 2011 | Sun Jun 19 17:00:00 IDT 2011
178 | Obstruction Removed by Other Project Contractor | Sun Jan 15 08:00:00 IST 2012 | Tue Apr 30 17:00:00 IDT 2013
179 | General | Sun Jan 15 08:00:00 IST 2012 | Tue Apr 30 17:00:00 IDT 2013
180 | D/T Remove Obstructions Below Nam Cheong Property Development (by XRL 802) | Mon Apr 30 17:00:00 IDT 2012 | Mon Apr 30 17:00:00 IDT 2012
181 | U/T Remove Obstructions Below Nam Cheong Property Development (by XRL 802) | Tue Apr 30 17:00:00 IDT 2013 | Tue Apr 30 17:00:00 IDT 2013
182 | Remove Obstructions Below CLP Equipment Building (by XRL 805) | Sun Jan 15 08:00:00 IST 2012 | Sun Jan 15 08:00:00 IST 2012
183 | Engineer's Office | Sun Apr 17 17:00:00 IDT 2011 | Sun Apr 17 17:00:00 IDT 2011
184 | General | Sun Apr 17 17:00:00 IDT 2011 | Sun Apr 17 17:00:00 IDT 2011
185 | Engineer's Office Completion with Furniture | Sun Apr 17 17:00:00 IDT 2011 | Sun Apr 17 17:00:00 IDT 2011
186 | Access Dates for Designated Contractors | Mon Aug 19 08:00:00 IDT 2013 | Mon Apr 27 08:00:00 IDT 2015
187 | 827 - Supply and Installation of Cross Passage Doors | Mon Aug 26 08:00:00 IDT 2013 | Mon Jan 26 08:00:00 IST 2015
188 | 827 - D/T All Cross Passages for Door Frame & Door Installation, from CH137+860 to Southern contract limit | Mon May 19 08:00:00 IDT 2014 | Mon May 19 08:00:00 IDT 2014
189 | 827 - D/T All Cross Passages for Door Frame and Door installation, from northern contract limit to CH137+860 | Mon Aug 26 08:00:00 IDT 2013 | Mon Aug 26 08:00:00 IDT 2013
190 | 827 - U/T All Cross Passages for Door Frame & Door Installation, from Northern contract limit to CH137+860 | Mon Jun 02 08:00:00 IDT 2014 | Mon Jun 02 08:00:00 IDT 2014
191 | 827 - U/T All Cross Passages for Door Frame & Door Installation, from CH137+860 to 950m from the Southern contract limit | Mon Dec 22 08:00:00 IST 2014 | Mon Dec 22 08:00:00 IST 2014
192 | 827 - U/T All Cross Passages for Door Frame & Door Installation, from CH137+860 to the Southern contract limit | Mon Jan 26 08:00:00 IST 2015 | Mon Jan 26 08:00:00 IST 2015
193 | 830 - Trackwork and Overhead Line System | Mon Aug 19 08:00:00 IDT 2013 | Mon Jan 26 08:00:00 IST 2015
194 | 830 - D/T Tunnel from the Northern contract limit to CH137+860 | Mon Aug 19 08:00:00 IDT 2013 | Mon Aug 19 08:00:00 IDT 2013
195 | 830 - D/T Tunnel from CH137+860 to Southern contract limit and C&C section within Hoi Ting Road Shaft | Mon May 19 08:00:00 IDT 2014 | Mon May 19 08:00:00 IDT 2014
196 | 830 - U/T Tunnel from the Northern contract limit to CH137+860 | Mon Jun 02 08:00:00 IDT 2014 | Mon Jun 02 08:00:00 IDT 2014
197 | 830 - U/T Tunnel from CH137+860 to 950m from the Southern contract limit | Mon Dec 22 08:00:00 IST 2014 | Mon Dec 22 08:00:00 IST 2014
198 | 830 - U/T Tunnel from CH137+860 to the Southern contract limit and C&C section within Hoi Ting Road Shaft | Mon Jan 26 08:00:00 IST 2015 | Mon Jan 26 08:00:00 IST 2015
199 | 841A - Signalling System - Trackside Equipment | Mon Apr 21 08:00:00 IDT 2014 | Mon Apr 27 08:00:00 IDT 2015
200 | 841A - U/T Tunnel from CH137+860 to the Southern contract limit and C&C section within Hoi Ting Road Shaft | Mon Apr 27 08:00:00 IDT 2015 | Mon Apr 27 08:00:00 IDT 2015
201 | 841A - U/T Tunnel from the Northern contract limit to CH137+860 | Sun Nov 30 08:00:00 IST 2014 | Sun Nov 30 08:00:00 IST 2014
202 | 841A - Nam Cheong Ventilation Building (VB7) - SER (Signalling-Trackside) | Mon Apr 21 08:00:00 IDT 2014 | Mon Apr 21 08:00:00 IDT 2014
203 | 841A - D/T Tunnel from the Northern contract limit to CH137+860 | Mon Jun 02 08:00:00 IDT 2014 | Mon Jun 02 08:00:00 IDT 2014
204 | 841A - D/T Tunnel from CH137+860 to the Southern contract limit and C&C section within Hoi Ting Road Shaft | Mon Sep 29 08:00:00 IDT 2014 | Mon Sep 29 08:00:00 IDT 2014
205 | 841B - Signalling System - Train Borne Equipment (Rolling Stock + Works / Rescue Trains) | Mon Apr 21 08:00:00 IDT 2014 | Mon Apr 27 08:00:00 IDT 2015
206 | 841B - U/T Tunnel from the Northern contract limit to CH137+860 (Signalling-Train Borne) | Mon Sep 29 08:00:00 IDT 2014 | Mon Sep 29 08:00:00 IDT 2014
207 | 841B - D/T Tunnel from the Northern contract limit to CH137+860 (Signalling-Train Borne) | Mon Jun 02 08:00:00 IDT 2014 | Mon Jun 02 08:00:00 IDT 2014
208 | 841B - Nam Cheong Ventilation Building (VB7) - SER (Signalling-Train Borne) | Mon Apr 21 08:00:00 IDT 2014 | Mon Apr 21 08:00:00 IDT 2014
209 | 841B - U/T Tunnel from CH137+860 to the Southern contract limit and C&C section within Hoi Ting Road Shaft | Mon Apr 27 08:00:00 IDT 2015 | Mon Apr 27 08:00:00 IDT 2015
210 | 841B - D/T Tunnel from CH137+860 to the Southern contract limit and C&C section within Hoi Ting Road Shaft | Mon Sep 29 08:00:00 IDT 2014 | Mon Sep 29 08:00:00 IDT 2014
211 | 843 - Tunnel Environmental Control System | Mon Feb 24 08:00:00 IST 2014 | Mon Apr 20 08:00:00 IDT 2015
212 | 843 - Nam Cheong Ventilation Building (VB7) - TVF Room and Compressed & Receiver Air Room | Mon Feb 24 08:00:00 IST 2014 | Mon Feb 24 08:00:00 IST 2014
213 | 843 - Nam Cheong Ventilation Building (VB7) - Tunnel ECS Control Room | Mon Jul 14 08:00:00 IDT 2014 | Mon Jul 14 08:00:00 IDT 2014
214 | 843 - Nam Cheong Ventilation Building (VB7) - Above track slab at both up and down tracks btw GL 1-9 | Mon Mar 24 08:00:00 IST 2014 | Mon Mar 24 08:00:00 IST 2014
215 | 843 - Nam Cheong Shaft C & C tunnels - Above track slab at both up and down tracks btw GL 9-16 | Mon Apr 20 08:00:00 IDT 2015 | Mon Apr 20 08:00:00 IDT 2015
216 | 844 - 11kV Power Distribution | Mon Jun 02 08:00:00 IDT 2014 | Mon Apr 27 08:00:00 IDT 2015
217 | 844 - D/T Tunnel from the Northern contract limit to CH137+860 (11kV Power) | Mon Jun 02 08:00:00 IDT 2014 | Mon Jun 02 08:00:00 IDT 2014
218 | 844 - D/T Tunnel from CH137+860 to Southern contract limit and C&C section within Hoi Ting Road Shaft (11kV Power) | Mon Sep 29 08:00:00 IDT 2014 | Mon Sep 29 08:00:00 IDT 2014
219 | 844 - U/T Tunnel from the Northern contract limit to CH137+860 (11kV Power) | Mon Sep 29 08:00:00 IDT 2014 | Mon Sep 29 08:00:00 IDT 2014
220 | 844 - U/T Tunnel from CH137+860 to the Southern contract limit and C&C section within Hoi Ting Road Shaft (11kV Power) | Mon Apr 27 08:00:00 IDT 2015 | Mon Apr 27 08:00:00 IDT 2015
221 | 844 - Nam Cheong Ventilation Building (VB7) - Power Supply Electrical Rooms (11kV Power) | Mon Sep 08 08:00:00 IDT 2014 | Mon Sep 08 08:00:00 IDT 2014
222 | 846 - Trackside Auxililaries | Mon Feb 24 08:00:00 IST 2014 | Mon Apr 27 08:00:00 IDT 2015
223 | 846 - D/T Tunnel from the Northern contract limit to CH137+860 (Trackside Aux.) | Mon Jun 02 08:00:00 IDT 2014 | Mon Jun 02 08:00:00 IDT 2014
224 | 846 - D/T Tunnel from CH137+860 to Southern contract limit and C&C section within Hoi Ting Road Shaft (Trackside Aux.) | Mon Sep 29 08:00:00 IDT 2014 | Mon Sep 29 08:00:00 IDT 2014
225 | 846 - U/T Tunnel from the Northern contract limit to CH137+860 (Trackside Aux.) | Mon Sep 29 08:00:00 IDT 2014 | Mon Sep 29 08:00:00 IDT 2014
226 | 846 - U/T Tunnel from CH137+860 to the Southern contract limit and C&C section within Hoi Ting Road Shaft | Mon Apr 27 08:00:00 IDT 2015 | Mon Apr 27 08:00:00 IDT 2015
227 | 846 - Nam Cheong Ventilation Building (VB7) Trackside LV Switch Room | Mon Feb 24 08:00:00 IST 2014 | Mon Feb 24 08:00:00 IST 2014
228 | 847 - Lifts | Mon Jul 14 08:00:00 IDT 2014 | Mon Jul 14 08:00:00 IDT 2014
229 | 847 - Nam Cheong Ventilation Building (VB7) - Lift Shaft adn Lift Machine Room | Mon Jul 14 08:00:00 IDT 2014 | Mon Jul 14 08:00:00 IDT 2014
230 | 849 - Radio Communications System | Mon Feb 24 08:00:00 IST 2014 | Mon Apr 27 08:00:00 IDT 2015
231 | 849 - Nam Cheong Ventilation Building (VB7) - TER and CTER (Radio Communications) | Mon Feb 24 08:00:00 IST 2014 | Mon Feb 24 08:00:00 IST 2014
232 | 849 - U/T Tunnel from the Northern contract limit to CH137+860 (Radio Communications) | Mon Sep 29 08:00:00 IDT 2014 | Mon Sep 29 08:00:00 IDT 2014
233 | 849 - U/T Tunnel from CH137+860 to the Southern contract limit and C&C section within Hoi Ting Road Shaft | Mon Apr 27 08:00:00 IDT 2015 | Mon Apr 27 08:00:00 IDT 2015
234 | 849 - Nam Cheong Ventilation Building (VB7) - SER (Radio Communications) | Mon Apr 21 08:00:00 IDT 2014 | Mon Apr 21 08:00:00 IDT 2014
235 | 849 - Nam Cheong Ventilation Building (VB7) - Corridors and Roof (Radio Communications) | Mon Jul 14 08:00:00 IDT 2014 | Mon Jul 14 08:00:00 IDT 2014
236 | 849 - D/T Tunnel from the Northern contract limit to CH137+860 (Radio Communications) | Mon Jun 02 08:00:00 IDT 2014 | Mon Jun 02 08:00:00 IDT 2014
237 | 849 - D/T Tunnel from CH137+860 to the Southern contract limit and C&C section within Hoi Ting Road Shaft | Mon Sep 29 08:00:00 IDT 2014 | Mon Sep 29 08:00:00 IDT 2014
238 | 850 - Passenger Mobile Communication System | Mon Feb 24 08:00:00 IST 2014 | Mon Apr 27 08:00:00 IDT 2015
239 | 850 - Nam Cheong Ventilation Building (VB7) - TER and CTER (Passenger Mobile Communication) | Mon Feb 24 08:00:00 IST 2014 | Mon Feb 24 08:00:00 IST 2014
240 | 850 - D/T Tunnel from the Northern contract limit to CH137+860 (Passenger Mobile Communication) | Mon Jun 02 08:00:00 IDT 2014 | Mon Jun 02 08:00:00 IDT 2014
241 | 850 - U/T Tunnel from the Northern contract limit to CH137+860 (Passenger Mobile Communication) | Mon Sep 29 08:00:00 IDT 2014 | Mon Sep 29 08:00:00 IDT 2014
242 | 850 - U/T Tunnel from CH137+860 to the Southern contract limit and C&C section within Hoi Ting Road Shaft | Mon Apr 27 08:00:00 IDT 2015 | Mon Apr 27 08:00:00 IDT 2015
243 | 850 - D/T Tunnel from CH137+860 to the Southern contract limit and C&C section within Hoi Ting Road Shaft | Mon Sep 29 08:00:00 IDT 2014 | Mon Sep 29 08:00:00 IDT 2014
244 | 851 - Fixed Communication System | Mon Feb 24 08:00:00 IST 2014 | Mon Apr 27 08:00:00 IDT 2015
245 | 851- Nam Cheong Ventilation Building (VB7) - TER and CTER (Fixed Communication) | Mon Feb 24 08:00:00 IST 2014 | Mon Feb 24 08:00:00 IST 2014
246 | 851 - D/T Tunnel from the Northern contract limit to CH137+860 (Fixed Communication) | Mon Jun 02 08:00:00 IDT 2014 | Mon Jun 02 08:00:00 IDT 2014
247 | 851 - U/T Tunnel from the Northern contract limit to CH137+860 (Fixed Communication) | Mon Sep 29 08:00:00 IDT 2014 | Mon Sep 29 08:00:00 IDT 2014
248 | 851 - U/T Tunnel from CH137+860 to the Southern contract limit and C&C section within Hoi Ting Road Shaft | Mon Apr 27 08:00:00 IDT 2015 | Mon Apr 27 08:00:00 IDT 2015
249 | 851 - D/T Tunnel from CH137+860 to Southern contract limit and C&C section within Hoi Ting Road Shaft | Mon Sep 29 08:00:00 IDT 2014 | Mon Sep 29 08:00:00 IDT 2014
250 | 853 - Main Control System | Mon Feb 24 08:00:00 IST 2014 | Mon Feb 24 08:00:00 IST 2014
251 | 853- Nam Cheong Ventilation Building (VB7) - TER and CTER (Main Control) | Mon Feb 24 08:00:00 IST 2014 | Mon Feb 24 08:00:00 IST 2014
252 | 854 - Security Access Management System (SAMS) | Mon Aug 18 08:00:00 IDT 2014 | Mon Aug 18 08:00:00 IDT 2014
253 | 854 - The doors with SAMS | Mon Aug 18 08:00:00 IDT 2014 | Mon Aug 18 08:00:00 IDT 2014
254 | 855 - Building Services for Tunnel Ventilation Buildings & Emergency Rescue Station | Mon Dec 23 08:00:00 IST 2013 | Mon May 12 08:00:00 IDT 2014
255 | 855-All rooms and common areas - corridors, lobbies etc within VB7 Excl. the parts of the VB7 under Ref. 4C(i) & 4C(ii) | Mon May 12 08:00:00 IDT 2014 | Mon May 12 08:00:00 IDT 2014
256 | 855 - VB7 - All rooms and common areas at track level and above track level(Excl. staircases, Lift shaft & CLP risers) | Mon Mar 03 08:00:00 IST 2014 | Mon Mar 03 08:00:00 IST 2014
257 | 855 - VB7 - All rooms and common areas at Level L1, UL2, L1 and UL1 (Excl. staircases, Lift shaft & CLP risers) | Mon Dec 23 08:00:00 IST 2013 | Mon Dec 23 08:00:00 IST 2013
258 | System Assurance Schedule | Mon Jul 05 17:00:00 IDT 2010 | Sat Jan 08 08:00:00 IST 2011
259 | System Assurance Schedule | Mon Jul 05 17:00:00 IDT 2010 | Sat Jan 08 08:00:00 IST 2011
260 | General | Mon Jul 05 17:00:00 IDT 2010 | Sat Jan 08 08:00:00 IST 2011
261 | System Assurance Plan | Sat Jan 08 08:00:00 IST 2011 | Sat Jan 08 08:00:00 IST 2011
262 | HAZOP Workshop | Mon Jul 05 17:00:00 IDT 2010 | Mon Jul 05 17:00:00 IDT 2010
263 | PHA Activity | Mon Jul 05 17:00:00 IDT 2010 | Mon Jul 05 17:00:00 IDT 2010
264 | Establish Hazard Log | Mon Jul 05 17:00:00 IDT 2010 | Mon Jul 05 17:00:00 IDT 2010
265 | System Hazard Analysis | Sat Jan 08 08:00:00 IST 2011 | Sat Jan 08 08:00:00 IST 2011
266 | Interface Hazard Analysis | Mon Nov 29 17:00:00 IST 2010 | Mon Nov 29 17:00:00 IST 2010
267 | Operating & Support Hazard Analysis | Mon Nov 29 17:00:00 IST 2010 | Mon Nov 29 17:00:00 IST 2010
268 | Hazard Analysis Report | Mon Nov 29 17:00:00 IST 2010 | Mon Nov 29 17:00:00 IST 2010
269 | Determination Safety Assessment | Sat Jan 08 08:00:00 IST 2011 | Sat Jan 08 08:00:00 IST 2011
270 | Cost Centre A - Preliminaries | Tue May 25 17:00:00 IDT 2010 | Fri Jun 26 17:00:00 IDT 2015
271 | IPS Milestones | Sat Jan 08 08:00:00 IST 2011 | Fri Jun 26 17:00:00 IDT 2015
272 | General | Sat Jan 08 08:00:00 IST 2011 | Fri Jun 26 17:00:00 IDT 2015
273 | Approval of Contractor's Submissions | Sat Jan 08 08:00:00 IST 2011 | Sat Jan 08 08:00:00 IST 2011
274 | Submit Contamination Assessment Report & RAP | Wed Apr 13 17:00:00 IDT 2011 | Wed Apr 13 17:00:00 IDT 2011
275 | Complete Engineer's Office+Satisfy Implem. Plans | Sun Apr 17 17:00:00 IDT 2011 | Sun Apr 17 17:00:00 IDT 2011
276 | Implem. Specified Plan&Programming Management System | Tue May 31 08:00:00 IDT 2011 | Tue May 31 08:00:00 IDT 2011
277 | Approval of Interface Specification&Specify Plan | Sun Jan 15 08:00:00 IST 2012 | Sun Jan 15 08:00:00 IST 2012
278 | 1st TBM - Complete Assembly, T&C & Start D/T Drive | Fri Jan 20 17:00:00 IST 2012 | Fri Jan 20 17:00:00 IST 2012
279 | Implem. Specified Plan&Programming Managem't System | Sun May 27 17:00:00 IDT 2012 | Sun May 27 17:00:00 IDT 2012
280 | Confirmation of Satisfactory Implementation of Specified Plan | Fri Nov 30 08:00:00 IST 2012 | Fri Nov 30 08:00:00 IST 2012
281 | TBM - Complete Assembly, T&C & Start U/T Drive | Fri Mar 29 17:00:00 IDT 2013 | Fri Mar 29 17:00:00 IDT 2013
282 | Confirmation of Satisfy Implement Specified Plan & Programming Mgmt. System | Sun May 26 17:00:00 IDT 2013 | Sun May 26 17:00:00 IDT 2013
283 | Confirmation of Satisfy Implement Specified Plan | Sun Nov 24 17:00:00 IST 2013 | Sun Nov 24 17:00:00 IST 2013
284 | Deg.1 Complete Entire Length Tunnel - Both Tracks | Tue Mar 31 17:00:00 IDT 2015 | Tue Mar 31 17:00:00 IDT 2015
285 | Approval of Draft O&M Manuals & As-built Drawing | Wed Mar 25 17:00:00 IST 2015 | Wed Mar 25 17:00:00 IST 2015
286 | Approval of O&M Manuals & As-built Drawings | Fri Jun 26 17:00:00 IDT 2015 | Fri Jun 26 17:00:00 IDT 2015
287 | Submission | Tue May 25 17:00:00 IDT 2010 | Sun Jan 15 08:00:00 IST 2012
288 | General | Tue May 25 17:00:00 IDT 2010 | Sun Jan 15 08:00:00 IST 2012
289 | Submission of Three Month Rolling Programme | Sat Jan 08 08:00:00 IST 2011 | Sat Jan 08 08:00:00 IST 2011
290 | Submission of Preliminary Design Programme | Sat Jan 08 08:00:00 IST 2011 | Sat Jan 08 08:00:00 IST 2011
291 | Submission of Contractor Submission Schedule | Sat Jan 08 08:00:00 IST 2011 | Sat Jan 08 08:00:00 IST 2011
292 | Submission of Schedule of Design | Sat Jan 08 08:00:00 IST 2011 | Sat Jan 08 08:00:00 IST 2011
293 | Submission Environment Management Plan | Sat Jan 08 08:00:00 IST 2011 | Sat Jan 08 08:00:00 IST 2011
294 | Submission of Quality Plan | Sat Jan 08 08:00:00 IST 2011 | Sat Jan 08 08:00:00 IST 2011
295 | Submission of Sub-contract Management Plan | Sat Jan 08 08:00:00 IST 2011 | Sat Jan 08 08:00:00 IST 2011
296 | Submission of Supply Survey Equipment Listed in App. A1 | Sat Jan 08 08:00:00 IST 2011 | Sat Jan 08 08:00:00 IST 2011
297 | Apply a Billing Account in EPD for Disposal of Construction Waste | Sat Jan 08 08:00:00 IST 2011 | Sat Jan 08 08:00:00 IST 2011
298 | Submission of Monitoring Emergency Response Plan(impact on Ecological & Fishers Resources) | Sat Jan 08 08:00:00 IST 2011 | Sat Jan 08 08:00:00 IST 2011
299 | Submission of Bond in form of App.B | Sat Jan 08 08:00:00 IST 2011 | Sat Jan 08 08:00:00 IST 2011
300 | Submission of Guarantee in Form of App.C | Sat Jan 08 08:00:00 IST 2011 | Sat Jan 08 08:00:00 IST 2011
301 | Submission of Guarantee in Form of App.D | Sat Jan 08 08:00:00 IST 2011 | Sat Jan 08 08:00:00 IST 2011
302 | Submission of Preliminary Master Programme | Wed Jun 02 17:00:00 IDT 2010 | Wed Jun 02 17:00:00 IDT 2010
303 | Submission of Time Chainage Programme | Wed Jun 02 17:00:00 IDT 2010 | Wed Jun 02 17:00:00 IDT 2010
304 | Confirmation for Conveyor System from Nam CheongShaft to Nam Cheong Barging Pt. | Wed Jun 02 17:00:00 IDT 2010 | Wed Jun 02 17:00:00 IDT 2010
305 | Submission of Survey Control Network | Wed Jun 02 17:00:00 IDT 2010 | Wed Jun 02 17:00:00 IDT 2010
306 | Submission for Approval Survey Control | Sun Jul 11 17:00:00 IDT 2010 | Sun Jul 11 17:00:00 IDT 2010
307 | Submission of Proposal for Repositioning of Traffic Signals & Control | Wed Jul 07 17:00:00 IDT 2010 | Wed Jul 07 17:00:00 IDT 2010
308 | Submission of Schedule of Utility Services Arrangement | Wed Jun 02 17:00:00 IDT 2010 | Wed Jun 02 17:00:00 IDT 2010
309 | Submission DIA to DSD for Approval | Wed Jun 02 17:00:00 IDT 2010 | Wed Jun 02 17:00:00 IDT 2010
310 | Submission of Health & Safety Plan | Wed Jun 02 17:00:00 IDT 2010 | Wed Jun 02 17:00:00 IDT 2010
311 | Completion of Initial Site Survey Submission | Wed Jun 02 17:00:00 IDT 2010 | Wed Jun 02 17:00:00 IDT 2010
312 | Submit Initial Site Survey Report to Engineer | Wed Jun 02 17:00:00 IDT 2010 | Wed Jun 02 17:00:00 IDT 2010
313 | Review Tree Removal Application & Confirmation to Engineer | Tue May 25 17:00:00 IDT 2010 | Tue May 25 17:00:00 IDT 2010
314 | Submit Full Details of TBMs to Engineer | Sun Jan 15 08:00:00 IST 2012 | Sun Jan 15 08:00:00 IST 2012
315 | MS/TTm proposal & Risk Register for Conveyor System at Barging Point | Sat Jan 08 08:00:00 IST 2011 | Sat Jan 08 08:00:00 IST 2011
316 | Submit Survey Method Statement for Tunnelling Works | Sat Jan 08 08:00:00 IST 2011 | Sat Jan 08 08:00:00 IST 2011
317 | Submit Managem't & Operat'n Plan of Barging Facility | Sat Jan 08 08:00:00 IST 2011 | Sat Jan 08 08:00:00 IST 2011
318 | TTM Schemes Submission for Engineer Review & SLG Approval | Sat Jan 08 08:00:00 IST 2011 | Sat Jan 08 08:00:00 IST 2011
319 | RemediationActionPlan forAreas11.29A to11.29-EPD | Sat Jan 08 08:00:00 IST 2011 | Sat Jan 08 08:00:00 IST 2011
320 | Condition Survey Submission for EBS | Mon Feb 28 08:00:00 IST 2011 | Mon Feb 28 08:00:00 IST 2011
321 | All Instrumentation Installation | Mon Feb 28 08:00:00 IST 2011 | Mon Feb 28 08:00:00 IST 2011
322 | Tree Protection Plan | Mon Feb 28 08:00:00 IST 2011 | Mon Feb 28 08:00:00 IST 2011
323 | Site Supervision Plan | Mon Feb 28 08:00:00 IST 2011 | Mon Feb 28 08:00:00 IST 2011
324 | Emergency Action Plan/Crisis Management Plan | Mon Feb 28 08:00:00 IST 2011 | Mon Feb 28 08:00:00 IST 2011
325 | Soil Disposal Management Plan | Mon Feb 28 08:00:00 IST 2011 | Mon Feb 28 08:00:00 IST 2011
326 | Segmental Lining Design Submission | Mon Feb 28 08:00:00 IST 2011 | Mon Feb 28 08:00:00 IST 2011
327 | Method Statement for Geotechnical Instrumentation Installation | Mon Feb 28 08:00:00 IST 2011 | Mon Feb 28 08:00:00 IST 2011
328 | Method Statement for Hoarding Erection | Mon Feb 28 08:00:00 IST 2011 | Mon Feb 28 08:00:00 IST 2011
329 | Emergency Response Plan to Groundwater Drawdown & Noise/Vibration | Mon Feb 28 08:00:00 IST 2011 | Mon Feb 28 08:00:00 IST 2011
330 | Site Office | Sat Jan 08 08:00:00 IST 2011 | Mon Mar 14 17:00:00 IST 2011
331 | Construction | Sat Jan 08 08:00:00 IST 2011 | Mon Mar 14 17:00:00 IST 2011
332 | Site Office Establish at Works Area 11.22 | Sat Jan 08 08:00:00 IST 2011 | Mon Mar 14 17:00:00 IST 2011
333 | Training Centre | Tue Jun 21 08:00:00 IDT 2011 | Wed Jul 13 17:00:00 IDT 2011
334 | Construction | Tue Jun 21 08:00:00 IDT 2011 | Wed Jul 13 17:00:00 IDT 2011
335 | Base Slab Construction | Thu Jun 23 08:00:00 IDT 2011 | Mon Jun 27 17:00:00 IDT 2011
336 | Erection of Building Structure | Tue Jun 21 08:00:00 IDT 2011 | Wed Jul 13 17:00:00 IDT 2011
337 | Internal Fitting Out | Tue Jun 21 08:00:00 IDT 2011 | Wed Jul 13 17:00:00 IDT 2011
338 | External Works | Tue Jun 21 08:00:00 IDT 2011 | Tue Jul 05 17:00:00 IDT 2011
339 | External Slab Construction | Tue Jun 21 08:00:00 IDT 2011 | Tue Jul 05 17:00:00 IDT 2011
340 | External U-channel | Tue Jun 21 08:00:00 IDT 2011 | Thu Jun 30 17:00:00 IDT 2011
341 | Sewer and Manholes | Tue Jun 21 08:00:00 IDT 2011 | Mon Jun 27 17:00:00 IDT 2011
342 | Hoarding Erection | Tue Jun 21 08:00:00 IDT 2011 | Sat Jul 02 17:00:00 IDT 2011
343 | Main Gate Installation | Tue Jun 21 08:00:00 IDT 2011 | Mon Jun 27 17:00:00 IDT 2011
344 | Sign Board Installation | Tue Jun 21 08:00:00 IDT 2011 | Mon Jun 27 17:00:00 IDT 2011
345 | Barging Point | Sat Jan 08 08:00:00 IST 2011 | Mon Mar 02 17:00:00 IST 2015
346 | General | Sat Jan 08 08:00:00 IST 2011 | Sat Jul 23 17:00:00 IDT 2011
347 | Barging Point Design Preparation | Sat Jan 08 08:00:00 IST 2011 | Sat Jul 23 17:00:00 IDT 2011
348 | Barging Point Design Comment and Approval by MTR | Sat Mar 05 08:00:00 IST 2011 | Sat Apr 02 17:00:00 IDT 2011
349 | Contamination | Sat Jan 08 08:00:00 IST 2011 | Sat May 21 17:00:00 IDT 2011
350 | Submission of Revised CAP (by MTR) | Sat Jan 08 08:00:00 IST 2011 | Thu Jan 20 17:00:00 IST 2011
351 | Approval Time of CAP from EPD | Tue Jan 18 08:00:00 IST 2011 | Sat Feb 19 17:00:00 IST 2011
352 | Preparation & Submission of M.S for Drilling | Mon Feb 21 08:00:00 IST 2011 | Tue Mar 01 17:00:00 IST 2011
353 | Site Investigation & Sample Locations Survey | Mon Feb 28 08:00:00 IST 2011 | Mon Mar 07 17:00:00 IST 2011
354 | Drilling & Sampling | Mon Mar 07 08:00:00 IST 2011 | Fri Mar 25 17:00:00 IST 2011
355 | Sampling Analysis | Fri Mar 18 08:00:00 IST 2011 | Wed Apr 13 17:00:00 IDT 2011
356 | Submission of CAR | Fri Apr 01 08:00:00 IDT 2011 | Wed May 04 17:00:00 IDT 2011
357 | Submission of RAP | Fri Apr 01 08:00:00 IDT 2011 | Wed May 04 17:00:00 IDT 2011
358 | Comments from EPD | Tue Apr 19 08:00:00 IDT 2011 | Sat May 21 17:00:00 IDT 2011
359 | Approved CAR & RAP Report Handover to 811B & 821 | Wed May 11 17:00:00 IDT 2011 | Wed May 11 17:00:00 IDT 2011
360 | Construction | Sat Jan 08 08:00:00 IST 2011 | Fri Jul 29 17:00:00 IDT 2011
361 | Works Area 11.29A | Sat Jan 08 08:00:00 IST 2011 | Sat Jan 08 08:00:00 IST 2011
362 | Works Area 11.29D | Sat Jan 08 08:00:00 IST 2011 | Sat Jan 08 08:00:00 IST 2011
363 | Works Area 11.29E | Sat Jan 08 08:00:00 IST 2011 | Sat Jan 08 08:00:00 IST 2011
364 | Works Area 11.29F | Sat Jan 08 08:00:00 IST 2011 | Sat Jan 08 08:00:00 IST 2011
365 | Site Mobilization | Sat Jan 08 08:00:00 IST 2011 | Fri Jan 28 17:00:00 IST 2011
366 | Hydographic/Condition Survey | Sat Jan 29 08:00:00 IST 2011 | Sat Mar 26 17:00:00 IST 2011
367 | Site Clearance | Sat Jun 11 08:00:00 IDT 2011 | Mon Jul 11 17:00:00 IDT 2011
368 | Site Formation fro Barging Point | Wed Jun 22 08:00:00 IDT 2011 | Mon Jul 11 17:00:00 IDT 2011
369 | Construction of Loading Ramps and Associated Facilities | Mon Feb 28 08:00:00 IST 2011 | Fri Jul 29 17:00:00 IDT 2011
370 | Storage Treatment Plant | Mon May 21 08:00:00 IDT 2012 | Sat Sep 01 17:00:00 IDT 2012
371 | Storage Treatment Plant Setup | Mon May 21 08:00:00 IDT 2012 | Sat Sep 01 17:00:00 IDT 2012
372 | Slurry Treatment Plant | Thu Jun 30 08:00:00 IDT 2011 | Mon Mar 02 17:00:00 IST 2015
373 | Begininning of Material Delivery for Slurry Treatment Plants | Thu Jun 30 08:00:00 IDT 2011 | Thu Jun 30 08:00:00 IDT 2011
374 | Treatment Tanks Erection | Thu Jun 30 08:00:00 IDT 2011 | Sat Sep 10 17:00:00 IDT 2011
375 | Silos Erection | Mon Jan 16 08:00:00 IST 2012 | Fri Jan 27 17:00:00 IST 2012
376 | Filter Press | Mon Jan 16 08:00:00 IST 2012 | Wed Feb 29 17:00:00 IST 2012
377 | Slurry Treatment Plant (STP1) Construction | Wed Aug 31 08:00:00 IDT 2011 | Thu Oct 13 17:00:00 IST 2011
378 | STP2 Construciton | Mon Jan 16 08:00:00 IST 2012 | Thu Feb 09 17:00:00 IST 2012
379 | Water Commissioning of STP1 | Mon Jan 16 08:00:00 IST 2012 | Fri Jan 20 17:00:00 IST 2012
380 | Water Commissioning of STP2 | Mon Jan 16 08:00:00 IST 2012 | Fri Jan 20 17:00:00 IST 2012
381 | Dismantle Slurry Treatment Plant and Equipments (after South U/T TBM (S630-1) Backup removal) | Wed Oct 15 08:00:00 IDT 2014 | Mon Jan 19 17:00:00 IST 2015
382 | Re-instatement | Fri Jan 02 08:00:00 IST 2015 | Mon Mar 02 17:00:00 IST 2015
383 | Cost Centre B - Specialised Construction Machinery & Site Assembly (TBMs) | Sat Jan 08 08:00:00 IST 2011 | Wed Nov 19 17:00:00 IST 2014
384 | IPS Milestones | Mon Jan 31 08:00:00 IST 2011 | Wed Nov 19 17:00:00 IST 2014
385 | General | Mon Jan 31 08:00:00 IST 2011 | Wed Nov 19 17:00:00 IST 2014
386 | Confirmation of Order of TBM | Mon Jan 31 08:00:00 IST 2011 | Mon Jan 31 08:00:00 IST 2011
387 | TBM - Commencement of the 1st TBM Final Assembly at Factory | Tue Aug 30 08:00:00 IDT 2011 | Tue Aug 30 08:00:00 IDT 2011
388 | TBM - Complete Fabrication & Ready Ship to HK | Sun Jan 15 08:00:00 IST 2012 | Sun Jan 15 08:00:00 IST 2012
389 | TBM - Complete Assembly,T&C+Start D/T Drive | Sun Feb 05 17:00:00 IST 2012 | Sun Feb 05 17:00:00 IST 2012
390 | TBM - Complete Assembly,T&C+Start U/T Drive (North) | Fri Mar 29 17:00:00 IDT 2013 | Fri Mar 29 17:00:00 IDT 2013
391 | TBM - Complete Assembly,T&C+Start Remain U/T Drive (South) | Thu Dec 12 08:00:00 IST 2013 | Thu Dec 12 08:00:00 IST 2013
392 | TBM - Complete Dismantle of TBM | Wed Nov 19 17:00:00 IST 2014 | Wed Nov 19 17:00:00 IST 2014
393 | Procurement | Sat Jan 08 08:00:00 IST 2011 | Mon Jan 07 17:00:00 IST 2013
394 | TBM (S630-1) Procurement & Delivery | Mon Feb 28 08:00:00 IST 2011 | Wed Nov 07 17:00:00 IST 2012
395 | TBM (S631-1) Procurement & Delivery | Mon Feb 28 08:00:00 IST 2011 | Mon Jan 07 17:00:00 IST 2013
396 | TBM (S630-1) Procurement | Sat Jan 08 08:00:00 IST 2011 | Wed Mar 21 17:00:00 IST 2012
397 | TBM(S630-1) - Procurement | Sat Jan 08 08:00:00 IST 2011 | Sat Feb 26 17:00:00 IST 2011
398 | TBM(S630-1) - Ordering | Sat Feb 26 17:00:00 IST 2011 | Sat Feb 26 17:00:00 IST 2011
399 | TBM(S630-1) - Detailed Design | Mon Jan 31 08:00:00 IST 2011 | Sun Apr 17 17:00:00 IDT 2011
400 | Ergonomy Study | Thu Feb 10 08:00:00 IST 2011 | Fri Apr 15 17:00:00 IDT 2011
401 | Purchase Parts | Mon Jan 31 08:00:00 IST 2011 | Thu Aug 18 17:00:00 IDT 2011
402 | Manufacturing of Drive Unit (in Europe) | Sun Mar 20 08:00:00 IST 2011 | Mon Sep 12 17:00:00 IDT 2011
403 | Commencement of TBM1 Final Assembly at Factory | Wed Aug 03 08:00:00 IDT 2011 | Wed Aug 03 08:00:00 IDT 2011
404 | Pre-assembly Drive Unit, Erector, Hydraulics, Slurry Pumps in Schwanau | Wed Aug 03 08:00:00 IDT 2011 | Sun Oct 23 17:00:00 IST 2011
405 | Transport (Europe to China) | Mon Mar 28 08:00:00 IST 2011 | Tue May 03 17:00:00 IDT 2011
406 | Manufacturing of Shield, Cutterhead, Back-up (in China) | Mon Feb 28 08:00:00 IST 2011 | Tue Sep 06 17:00:00 IDT 2011
407 | Design Review for TBM (S631-1) Modification | Sun Jun 19 08:00:00 IDT 2011 | Wed Jul 13 17:00:00 IDT 2011
408 | EI issue for TBM (S630-1) Modification | Thu Jun 30 08:00:00 IDT 2011 | Thu Jun 30 08:00:00 IDT 2011
409 | TBM (S630-1) Modification | Thu Jun 30 08:00:00 IDT 2011 | Thu Sep 08 17:00:00 IDT 2011
410 | Final Assembly in Workshop | Sun Jun 19 08:00:00 IDT 2011 | Sat Nov 19 17:00:00 IST 2011
411 | Factory Acceptance Tests | Sun Jan 15 08:00:00 IST 2012 | Tue Feb 07 17:00:00 IST 2012
412 | Disassembly & Ready Ship to HK | Sun Jan 15 08:00:00 IST 2012 | Sat Feb 11 17:00:00 IST 2012
413 | TBM (S630-1) Available for delivery to HK | Sun Jan 15 08:00:00 IST 2012 | Sun Jan 15 08:00:00 IST 2012
414 | TBM(S630-1) - TBM Storage | Sun Jan 15 08:00:00 IST 2012 | Wed Feb 29 17:00:00 IST 2012
415 | TBM(S630-1) - Transport & Delivery to HK | Thu Mar 01 08:00:00 IST 2012 | Wed Mar 21 17:00:00 IST 2012
416 | TBM (S631-1) Procurement | Sat Jan 08 08:00:00 IST 2011 | Sat Feb 11 17:00:00 IST 2012
417 | TBM(S631-1) - Procurement | Mon Jan 31 08:00:00 IST 2011 | Sun Mar 20 17:00:00 IST 2011
418 | TBM(S631-1) - Ordering | Sat Feb 26 17:00:00 IST 2011 | Sat Feb 26 17:00:00 IST 2011
419 | TBM(S631-1) - Detailed Design | Sun Feb 27 08:00:00 IST 2011 | Wed May 25 17:00:00 IDT 2011
420 | Ergonomy Study | Thu Jan 20 08:00:00 IST 2011 | Sat Mar 26 17:00:00 IST 2011
421 | Purchase Parts | Sat Jan 08 08:00:00 IST 2011 | Thu Sep 15 17:00:00 IDT 2011
422 | Manufacturing of Drive Unit (in Europe) | Sun Mar 27 08:00:00 IST 2011 | Wed Sep 28 17:00:00 IDT 2011
423 | Pre-assembly Drive Unit,erector,Hydraulics, Slurry Pumps in Schwanau | Sun Jun 19 08:00:00 IDT 2011 | Sat Jul 16 17:00:00 IDT 2011
424 | Transport (Europe to China) | Tue Apr 19 08:00:00 IDT 2011 | Mon Jun 27 17:00:00 IDT 2011
425 | Manufacturing on Shield, Cutterhead,Back-up (in China) | Fri Mar 11 08:00:00 IST 2011 | Thu Oct 06 17:00:00 IST 2011
426 | Design Review for TBM (S631-1) Modification | Sun Jun 19 08:00:00 IDT 2011 | Wed Jul 13 17:00:00 IDT 2011
427 | EI issue for TBM631.1 Modification | Thu Jun 30 08:00:00 IDT 2011 | Thu Jun 30 08:00:00 IDT 2011
428 | TBM (S631-1) Modification | Sun Jun 19 08:00:00 IDT 2011 | Sun Aug 28 17:00:00 IDT 2011
429 | Final Assembly in Workshop | Sun Jun 19 08:00:00 IDT 2011 | Fri Oct 21 17:00:00 IST 2011
430 | Factory Acceptance Tests | Wed Aug 31 08:00:00 IDT 2011 | Fri Sep 23 17:00:00 IDT 2011
431 | Disassembly | Sun Jan 15 08:00:00 IST 2012 | Sat Feb 11 17:00:00 IST 2012
432 | TBM (S631-1) Available for delivery to HK | Sun Jan 15 08:00:00 IST 2012 | Sun Jan 15 08:00:00 IST 2012
433 | TBM(S631-1) - Transport & Delivery to HK | Sun Jan 15 08:00:00 IST 2012 | Fri Feb 03 17:00:00 IST 2012
434 | Cost Centre C - Mei Lai Road - Hoi Ting Road Tunnel | Thu Oct 21 08:00:00 IST 2010 | Tue Sep 29 17:00:00 IDT 2015
435 | IPS Milestones | Mon Feb 28 08:00:00 IST 2011 | Sun May 10 17:00:00 IDT 2015
436 | General | Mon Feb 28 08:00:00 IST 2011 | Sun May 10 17:00:00 IDT 2015
437 | Approval of Tunnel Lining Design | Mon Jul 18 17:00:00 IDT 2011 | Mon Jul 18 17:00:00 IDT 2011
438 | Approval of Tunnel Segment Mould Design | Mon Feb 28 08:00:00 IST 2011 | Mon Feb 28 08:00:00 IST 2011
439 | Confirmation of the Order of Segment Mould | Thu Jun 30 08:00:00 IDT 2011 | Thu Jun 30 08:00:00 IDT 2011
440 | Complete Ground Improvement Wk Outside Hoi Ting Shaft | Sun Jun 19 17:00:00 IDT 2011 | Sun Jun 19 17:00:00 IDT 2011
441 | Complete 30% of Pre-cast Segment Manufacturing | Thu Dec 20 17:00:00 IST 2012 | Thu Dec 20 17:00:00 IST 2012
442 | Complete 45% of Pre-cast Segment Manufacturing | Fri Apr 19 17:00:00 IDT 2013 | Fri Apr 19 17:00:00 IDT 2013
443 | Complete 30% of Tunnel Drive | Fri Aug 31 08:00:00 IDT 2012 | Fri Aug 31 08:00:00 IDT 2012
444 | Complete 50% of Tunnel Drive | Thu Jan 31 17:00:00 IST 2013 | Thu Jan 31 17:00:00 IST 2013
445 | Complete 60% of Tunnel Drive | Wed Jul 31 17:00:00 IDT 2013 | Wed Jul 31 17:00:00 IDT 2013
446 | Deg. 1 Completion for D/T Tunnel | Sun May 18 17:00:00 IDT 2014 | Sun May 18 17:00:00 IDT 2014
447 | Complete 100% of Tunnel Drive | Sun Sep 28 17:00:00 IDT 2014 | Sun Sep 28 17:00:00 IDT 2014
448 | Deg. 1 Completion for U/T Tunnel | Sat Feb 28 17:00:00 IST 2015 | Sat Feb 28 17:00:00 IST 2015
449 | Complete All Works | Sun May 10 17:00:00 IDT 2015 | Sun May 10 17:00:00 IDT 2015
450 | Critical Dates | Mon Feb 28 08:00:00 IST 2011 | Mon Sep 30 08:00:00 IDT 2013
451 | Critical Dates | Mon Feb 28 08:00:00 IST 2011 | Mon Sep 30 08:00:00 IDT 2013
452 | Earliest Access Date- Works Area 12.2 | Mon Feb 28 08:00:00 IST 2011 | Mon Feb 28 08:00:00 IST 2011
453 | Ground Treatment Completion at Works Area 12.2 | Sun Jun 19 17:00:00 IDT 2011 | Sun Jun 19 17:00:00 IDT 2011
454 | Hoi Ting Road - TBM Retrieval Shaft Ready | Mon Sep 30 08:00:00 IDT 2013 | Mon Sep 30 08:00:00 IDT 2013
455 | Method Statement Submission and Approval | Mon Feb 28 08:00:00 IST 2011 | Thu Jan 19 17:00:00 IST 2012
456 | Method Stattement Submission and Approval | Mon Feb 28 08:00:00 IST 2011 | Thu Jan 19 17:00:00 IST 2012
457 | MS Submission Preparation for CLP/IVESchool Grouting | Thu Jun 30 08:00:00 IDT 2011 | Thu Jan 19 17:00:00 IST 2012
458 | MS Submission to MTR | Thu Jun 30 08:00:00 IDT 2011 | Thu Jun 30 08:00:00 IDT 2011
459 | MS Comment by MTR | Thu Jun 30 08:00:00 IDT 2011 | Thu Aug 04 17:00:00 IDT 2011
460 | MS Re-submission Preparation | Thu Jun 30 08:00:00 IDT 2011 | Sat Jul 09 17:00:00 IDT 2011
461 | MS Comment & Approval by MTR | Thu Jun 30 08:00:00 IDT 2011 | Tue Aug 16 17:00:00 IDT 2011
462 | Issue for Construction (CLP/IVE) | Wed Jul 27 17:00:00 IDT 2011 | Wed Jul 27 17:00:00 IDT 2011
463 | MS Submission Preparation for Cross Passage | Mon Feb 28 08:00:00 IST 2011 | Tue Jun 07 17:00:00 IDT 2011
464 | MS Submission to MTR | Thu Jun 30 08:00:00 IDT 2011 | Thu Jun 30 08:00:00 IDT 2011
465 | MS Comment by MTR | Thu Jun 30 08:00:00 IDT 2011 | Sat Jul 16 17:00:00 IDT 2011
466 | MS Re-Submission Preparation | Wed Aug 31 08:00:00 IDT 2011 | Wed Sep 21 17:00:00 IDT 2011
467 | MS Comment & Approval by MTR | Wed Aug 31 08:00:00 IDT 2011 | Sat Sep 17 17:00:00 IDT 2011
468 | Issue for Construction (Cross Passage) | Wed Aug 31 08:00:00 IDT 2011 | Wed Aug 31 08:00:00 IDT 2011
469 | MS Submission Preparation for HoiFu Estate/Charming Bldgs.& YMT School | Thu Jun 30 08:00:00 IDT 2011 | Tue Jul 26 17:00:00 IDT 2011
470 | MS Submission to MTR | Thu Jun 30 08:00:00 IDT 2011 | Thu Jun 30 08:00:00 IDT 2011
471 | MS Comment & Approoval by MTR | Thu Jun 30 08:00:00 IDT 2011 | Thu Jul 21 17:00:00 IDT 2011
472 | MS Re-submission Preparation | Thu Jun 30 08:00:00 IDT 2011 | Thu Jul 28 17:00:00 IDT 2011
473 | MS Approval by MTR | Wed Aug 31 08:00:00 IDT 2011 | Sun Sep 11 17:00:00 IDT 2011
474 | Issue for Construction (HoiFu Estate/Charming Bldgs & YMT School) | Wed Aug 31 08:00:00 IDT 2011 | Wed Aug 31 08:00:00 IDT 2011
475 | TTMS Submission and Approval | Tue Feb 01 08:00:00 IST 2011 | Sun Sep 11 17:00:00 IDT 2011
476 | TTM Scheme Submission & Approval | Tue Feb 01 08:00:00 IST 2011 | Sun Sep 11 17:00:00 IDT 2011
477 | Prepare TTM for grouting works for Existing Bldg | Tue Feb 01 08:00:00 IST 2011 | Sat Mar 05 17:00:00 IST 2011
478 | TTM reviewed by SLG | Sun Mar 06 08:00:00 IST 2011 | Thu May 05 17:00:00 IDT 2011
479 | Resubmit TTM | Mon May 23 08:00:00 IDT 2011 | Mon May 23 17:00:00 IDT 2011
480 | TTM reviewed by SLG | Sun May 29 08:00:00 IDT 2011 | Sun May 29 17:00:00 IDT 2011
481 | Notification to RMO (for Ch140 +080 & +150 & +200) | Sun Jun 19 08:00:00 IDT 2011 | Sun Jun 26 17:00:00 IDT 2011
482 | XP Application & Approval | Mon Jun 20 08:00:00 IDT 2011 | Thu Aug 18 17:00:00 IDT 2011
483 | Implement TTM (Initial Stage) | Mon Feb 28 08:00:00 IST 2011 | Mon Jul 25 17:00:00 IDT 2011
484 | Notification to RMO (for Ch140 +340) | Wed Aug 31 08:00:00 IDT 2011 | Sun Sep 11 17:00:00 IDT 2011
485 | Implement TTM | Wed Aug 31 08:00:00 IDT 2011 | Wed Aug 31 08:00:00 IDT 2011
486 | SP License Application and Approval | Sun Jan 15 08:00:00 IST 2012 | Sun Jun 17 17:00:00 IDT 2012
487 | SP License application | Sun Jan 15 08:00:00 IST 2012 | Sun Jun 17 17:00:00 IDT 2012
488 | SP License application | Sun Jan 15 17:00:00 IST 2012 | Sun Jan 15 17:00:00 IST 2012
489 | TBM (S631-1) Excavation with Deg.1 Works | Sun Jan 15 08:00:00 IST 2012 | Thu May 29 17:00:00 IDT 2014
490 | TBM (S631-1) North -UT Excavation | Fri Mar 29 08:00:00 IDT 2013 | Thu Nov 14 17:00:00 IST 2013
491 | Access Available for Works Area 11.10A &11.10B (IVE School) (DT) (Contractual Handover Date) | Wed Feb 06 08:00:00 IST 2013 | Wed Feb 06 08:00:00 IST 2013
492 | Ground Treatment for IVE School (DT) | Mon Jan 16 08:00:00 IST 2012 | Tue Jun 12 17:00:00 IDT 2012
493 | TBM (S631-1) North-DT Excavation | Fri Jan 20 08:00:00 IST 2012 | Tue Oct 30 17:00:00 IST 2012
494 | TBM (S631-1) Dismantle & Re-assembly | Mon Dec 17 08:00:00 IST 2012 | Tue Feb 26 17:00:00 IST 2013
495 | Piles Removal@CLP Equipment Bldg.& Footbridges KF-118 by 805 (NDT) | Sun Jan 15 08:00:00 IST 2012 | Sun Jan 15 08:00:00 IST 2012
496 | Access Available for Works Area 11.10A &11.10B (IVE School) (DT) (Contractual Handover Date) | Wed Feb 06 08:00:00 IST 2013 | Wed Feb 06 08:00:00 IST 2013
497 | Ground Treatment for HKIVE School (NDT) | Mon Jan 16 08:00:00 IST 2012 | Mon Mar 26 17:00:00 IST 2012
498 | Grouting Wk@N/B Ch137+570: Building Foundation (Hoi Lai Shopping Centre) (NUT) | Sat Mar 24 08:00:00 IST 2012 | Fri Aug 31 17:00:00 IDT 2012
499 | General | Sun Jan 15 08:00:00 IST 2012 | Fri Mar 30 17:00:00 IDT 2012
500 | TBM (S631-1) Delivery on Site | Sun Jan 15 08:00:00 IST 2012 | Sun Jan 15 08:00:00 IST 2012
501 | TBM (S631-1) Assembly and T&C | Sun Jan 15 08:00:00 IST 2012 | Fri Mar 30 17:00:00 IDT 2012
502 | Downtrack Construction (North) | Sun Jan 15 08:00:00 IST 2012 | Sat Aug 17 17:00:00 IDT 2013
503 | TBM Excavation (North-DT) | Sun Jan 15 08:00:00 IST 2012 | Sat Aug 17 17:00:00 IDT 2013
504 | D/T TBM (S631-1) Break-in &Excavation Ch137+783-137+730 | Fri Jan 20 08:00:00 IST 2012 | Fri Feb 10 17:00:00 IST 2012
505 | Reach Cheung Sha Wan Cargo Pier Pile Obstruction | Fri Feb 10 17:00:00 IST 2012 | Fri Feb 10 17:00:00 IST 2012
506 | D/T Excavation Ch137+730-137+640 | Sat Feb 11 08:00:00 IST 2012 | Sun Mar 18 17:00:00 IST 2012
507 | D/T Excavation Ch137+640-137+530 | Mon Mar 19 08:00:00 IST 2012 | Mon Apr 02 17:00:00 IDT 2012
508 | Reach CP88 (CH137+565) | Thu Mar 29 08:00:00 IST 2012 | Thu Mar 29 08:00:00 IST 2012
509 | D/T Excavation Ch137+530-137+420 | Tue Apr 03 08:00:00 IDT 2012 | Thu Apr 12 17:00:00 IDT 2012
510 | D/T Excavation Ch137+420-137+345 | Fri Apr 13 08:00:00 IDT 2012 | Thu Apr 19 17:00:00 IDT 2012
511 | Reach CP87 (CH137+369) | Wed Apr 18 17:00:00 IDT 2012 | Wed Apr 18 17:00:00 IDT 2012
512 | Piles Removal@CLP Equipment Bldg.& Footbridges KF-118 by 805 | Sun Jan 15 08:00:00 IST 2012 | Sun Jan 15 08:00:00 IST 2012
513 | Reach Footbridge KF118 (Pile removed by 805) | Thu Apr 19 17:00:00 IDT 2012 | Thu Apr 19 17:00:00 IDT 2012
514 | D/T Excavation Ch137+345-137+280 | Fri Apr 20 08:00:00 IDT 2012 | Wed Apr 25 17:00:00 IDT 2012
515 | D/T Excavation Ch137+280-137+265 | Thu Apr 26 08:00:00 IDT 2012 | Fri Apr 27 17:00:00 IDT 2012
516 | Reach IVE Haking Wong Waterfont Annex (advanced work:Grouting) | Fri Apr 27 17:00:00 IDT 2012 | Fri Apr 27 17:00:00 IDT 2012
517 | D/T Excavation Ch137+265-137+240 | Sat Apr 28 08:00:00 IDT 2012 | Mon Apr 30 17:00:00 IDT 2012
518 | D/T Excavation Ch137+240-137+190 | Tue May 01 08:00:00 IDT 2012 | Sat May 05 17:00:00 IDT 2012
519 | D/T Excavation Ch137+190-137+080 | Sun May 06 08:00:00 IDT 2012 | Fri May 25 17:00:00 IDT 2012
520 | Reach CP86 (CH137+119) | Sat May 19 08:00:00 IDT 2012 | Sat May 19 08:00:00 IDT 2012
521 | Reach WD1 DSD Obstruction & 1800dia.Sewer | Fri May 25 17:00:00 IDT 2012 | Fri May 25 17:00:00 IDT 2012
522 | D/T Excavation Ch137+080-136+960 | Sat May 26 08:00:00 IDT 2012 | Fri Jun 15 17:00:00 IDT 2012
523 | Reach Lai Chi Kok DSD Obstruction | Fri Jun 15 17:00:00 IDT 2012 | Fri Jun 15 17:00:00 IDT 2012
524 | D/T Excavation Ch136+960-136+945 | Sat Jun 16 08:00:00 IDT 2012 | Mon Jun 18 17:00:00 IDT 2012
525 | D/T Excavation Ch136+945-136+920 | Tue Jun 19 08:00:00 IDT 2012 | Sun Jun 24 17:00:00 IDT 2012
526 | Reach TWL Sump Pit Ch136+920 | Sun Jun 24 17:00:00 IDT 2012 | Sun Jun 24 17:00:00 IDT 2012
527 | D/T Excavation Ch136+920-136+820 | Mon Jun 25 08:00:00 IDT 2012 | Tue Jul 03 17:00:00 IDT 2012
528 | Reach CP85 (CH136+860) | Sat Jun 30 08:00:00 IDT 2012 | Sat Jun 30 08:00:00 IDT 2012
529 | D/T Excavation Ch136+820-136+640 | Wed Jul 04 08:00:00 IDT 2012 | Tue Jul 24 17:00:00 IDT 2012
530 | D/T Excavation Ch136+640-136+583 - XRL821 | Wed Jul 25 08:00:00 IDT 2012 | Mon Jul 30 17:00:00 IDT 2012
531 | Reach CP84(CH136+601) - XRL821 | Sun Jul 29 08:00:00 IDT 2012 | Sun Jul 29 08:00:00 IDT 2012
532 | D/T Excavation Ch136+583-136+351 - XRL821 | Tue Jul 31 08:00:00 IDT 2012 | Tue Aug 28 17:00:00 IDT 2012
533 | Reach CP83 (CH136+351) XRL- 821 | Mon Sep 17 17:00:00 IDT 2012 | Mon Sep 17 17:00:00 IDT 2012
534 | D/T Excavation Ch136+351-136+101 - XRL821 | Tue Sep 18 08:00:00 IDT 2012 | Fri Oct 12 17:00:00 IST 2012
535 | Reach CP82 (CH136+101) - XRL821 | Sun Oct 07 17:00:00 IST 2012 | Sun Oct 07 17:00:00 IST 2012
536 | D/T Excavation Ch136+101-135+972 - XRL821 | Mon Oct 08 08:00:00 IST 2012 | Thu Oct 18 17:00:00 IST 2012
537 | D/T Excavation Ch135+972-135+772 - XRL821 | Fri Oct 19 08:00:00 IST 2012 | Mon Nov 05 17:00:00 IST 2012
538 | Reach CP81 (CH135+851) - XRL821 | Mon Nov 05 08:00:00 IST 2012 | Mon Nov 05 08:00:00 IST 2012
539 | D/T Excavation Ch135+772-135+737 - XRL 821 (235m) Break-in | Sat Dec 08 08:00:00 IST 2012 | Tue Dec 11 17:00:00 IST 2012
540 | D/T exit inside TBM Cavern (XRL821) | Sat Dec 15 08:00:00 IST 2012 | Wed Dec 19 17:00:00 IST 2012
541 | TBM (S631-1) Backup pull back | Mon Jan 07 08:00:00 IST 2013 | Wed Jan 16 17:00:00 IST 2013
542 | TBM (S631-1) Shield Dismantle & Removal | Mon Dec 17 08:00:00 IST 2012 | Wed Jan 30 17:00:00 IST 2013
543 | Set up Equipment for Invert Construction (Ch135+737-XRL821 to Ch137+784) | Thu Jan 31 08:00:00 IST 2013 | Sat Feb 16 17:00:00 IST 2013
544 | Tunnel Invert & Walkway (North DT- Ch135+737-XRL821 to Ch137+784) | Thu Feb 14 08:00:00 IST 2013 | Mon Aug 05 17:00:00 IDT 2013
545 | Deg. 1 Works (incl. XRL821) | Sat Jun 01 08:00:00 IDT 2013 | Sat Aug 17 17:00:00 IDT 2013
546 | Uptrack Construction (North) | Sat Mar 24 08:00:00 IST 2012 | Thu May 29 17:00:00 IDT 2014
547 | Ground Treatment (North-UT) | Sat Mar 24 08:00:00 IST 2012 | Wed Oct 03 17:00:00 IST 2012
548 | TTMS & Site Set up for Building Foundation Grouting Works | Sat Mar 24 08:00:00 IST 2012 | Mon Apr 30 17:00:00 IDT 2012
549 | Install Sleeve Pipe (Hoi Lai Shopping Centre) (UT) | Wed May 02 08:00:00 IDT 2012 | Thu May 31 17:00:00 IDT 2012
550 | Grouting Wk@N/B Ch137+570: Building Foundation (Hoi Lai Shopping Centre) (UT) | Fri Jun 01 08:00:00 IDT 2012 | Fri Aug 31 17:00:00 IDT 2012
551 | Reinstatement@N/B Ch137+570:(Hoi Lai Shopping Centre) (UT) | Sat Sep 01 08:00:00 IDT 2012 | Wed Oct 03 17:00:00 IST 2012
552 | TBM Excavation (North-UT) | Tue Jan 08 08:00:00 IST 2013 | Thu May 29 17:00:00 IDT 2014
553 | TBM (S631-1) Re-assembly | Tue Jan 08 08:00:00 IST 2013 | Wed Mar 20 17:00:00 IST 2013
554 | U/T Excavation Ch137+810-137+710 (Break-in) | Fri Mar 29 08:00:00 IDT 2013 | Sat Apr 20 17:00:00 IDT 2013
555 | Reach Cheung Sha Wan Cargo Pier Pile Obstruction | Sun Apr 07 17:00:00 IDT 2013 | Sun Apr 07 17:00:00 IDT 2013
556 | U/T Excavation Ch137+710-137+580 | Sun Apr 07 08:00:00 IDT 2013 | Wed May 01 17:00:00 IDT 2013
557 | Reach CP88(CH137+591) | Tue Apr 16 17:00:00 IDT 2013 | Tue Apr 16 17:00:00 IDT 2013
558 | U/T Excavation Ch137+580-137+550 | Fri Apr 19 08:00:00 IDT 2013 | Sat Apr 20 17:00:00 IDT 2013
559 | Reach Hoi Lai Shopping Centre (advanced work:Grouting) | Fri Apr 19 17:00:00 IDT 2013 | Fri Apr 19 17:00:00 IDT 2013
560 | U/T Excavation Ch137+550-137+200 | Sat Apr 20 08:00:00 IDT 2013 | Tue May 14 17:00:00 IDT 2013
561 | Reach CP87(CH137+393) | Sat Apr 27 17:00:00 IDT 2013 | Sat Apr 27 17:00:00 IDT 2013
562 | U/T Excavation Ch137+200-137+080 | Tue May 14 08:00:00 IDT 2013 | Sat Jun 01 17:00:00 IDT 2013
563 | Reach CP86(CH137+141) | Sun May 19 17:00:00 IDT 2013 | Sun May 19 17:00:00 IDT 2013
564 | Reach Culvert WD1 Pile Obstruction &1100dia. Foul Drain | Sun May 26 17:00:00 IDT 2013 | Sun May 26 17:00:00 IDT 2013
565 | U/T Excavation Ch137+080-136+975 | Sat May 25 08:00:00 IDT 2013 | Mon Jun 10 17:00:00 IDT 2013
566 | U/T Excavation Ch136+975-136+910 | Wed Jun 05 08:00:00 IDT 2013 | Thu Jun 20 17:00:00 IDT 2013
567 | Reach Lai Chi Kok DSD Obstructions | Fri Jun 07 17:00:00 IDT 2013 | Fri Jun 07 17:00:00 IDT 2013
568 | U/T Excavation Ch136+910-136+836 | Wed Jun 12 08:00:00 IDT 2013 | Tue Jun 18 17:00:00 IDT 2013
569 | Reach CP85(CH136+879) | Mon Jun 17 17:00:00 IDT 2013 | Mon Jun 17 17:00:00 IDT 2013
570 | U/T Excavation Ch136+836-136+656 | Wed Jun 26 08:00:00 IDT 2013 | Sat Jul 13 17:00:00 IDT 2013
571 | U/T Excavation Ch136+656-136+601-XRL821 | Wed Jul 24 08:00:00 IDT 2013 | Mon Jul 29 17:00:00 IDT 2013
572 | Reach CP84 (CH136+616)- XRL821 | Sat Jul 27 17:00:00 IDT 2013 | Sat Jul 27 17:00:00 IDT 2013
573 | U/T Excavation Ch136+601-136+365-XRL821 | Sun Jul 28 08:00:00 IDT 2013 | Tue Aug 13 17:00:00 IDT 2013
574 | Reach CP83 (CH136+365)- XRL821 | Fri Aug 23 17:00:00 IDT 2013 | Fri Aug 23 17:00:00 IDT 2013
575 | U/T Excavation Ch136+365-136+114-XRL821 | Fri Aug 23 08:00:00 IDT 2013 | Wed Sep 18 17:00:00 IDT 2013
576 | Reach CP82 (CH136+114)- XRL821 | Tue Sep 17 17:00:00 IDT 2013 | Tue Sep 17 17:00:00 IDT 2013
577 | U/T Excavation Ch136+114 -135+985-XRL821 | Tue Sep 17 08:00:00 IDT 2013 | Sat Sep 28 17:00:00 IDT 2013
578 | U/T Excavation Ch135+985-135+750-XRL821 (+235m) (Break-out) | Sun Oct 06 08:00:00 IDT 2013 | Sun Oct 27 17:00:00 IST 2013
579 | Reach CP81 (CH135+863)- XRL821 | Tue Oct 22 17:00:00 IDT 2013 | Tue Oct 22 17:00:00 IDT 2013
580 | U/T exit inside TBM Cavern - XRL821 | Sun Nov 10 08:00:00 IST 2013 | Thu Nov 14 17:00:00 IST 2013
581 | TBM (S631-1) Dismantling & Backup pull back | Fri Nov 15 08:00:00 IST 2013 | Sun Dec 29 17:00:00 IST 2013
582 | Set up Equipment for Invert Construction (Ch137+810 to Ch135+750-XRL821 ) | Mon Jan 06 08:00:00 IST 2014 | Sat Jan 18 17:00:00 IST 2014
583 | 820 section - Tunnel Invert & Walkway (UT-Northbound) (Ch137+810 to Ch136+640) | Mon Jan 20 08:00:00 IST 2014 | Wed Apr 16 17:00:00 IDT 2014
584 | 821 section - Tunnel Invert & Walkway (UT-Northbound) (Ch136+640 to Ch135+750) | Wed Feb 19 08:00:00 IST 2014 | Fri Apr 25 17:00:00 IDT 2014
585 | 821 Deg. 1 Works Ch136+640 to Ch135+750 (SA#3: 29-Jun-14) | Mon Mar 10 08:00:00 IST 2014 | Wed Apr 30 17:00:00 IDT 2014
586 | 820 Deg. 1 Works Ch137+810 to Ch136+640 (4B(i) Target: 1-Jun-14) | Sat Mar 01 08:00:00 IST 2014 | Thu May 29 17:00:00 IDT 2014
587 | TBM (S630-1) Excavation with Deg.1 Works | Tue Feb 01 08:00:00 IST 2011 | Tue Sep 29 17:00:00 IDT 2015
588 | Ground Treatment Wk at 811A Retrieval Shaft | Mon Jun 20 08:00:00 IDT 2011 | Fri Sep 23 17:00:00 IDT 2011
589 | Ground Wks for Buildings Protection (DT) - Hoi Wang Road | Mon Aug 01 08:00:00 IDT 2011 | Sat Sep 22 17:00:00 IDT 2012
590 | Ground Wks for Convergence Zones | Mon Jan 16 08:00:00 IST 2012 | Tue Nov 27 17:00:00 IST 2012
591 | Piles Removal@CLP Equipment Bldg.& Footbridges KF-119 by 805 | Sun Jan 15 08:00:00 IST 2012 | Sun Jan 15 08:00:00 IST 2012
592 | Pile Removal for Nam Cheong Property Development by 802 | Mon Apr 30 17:00:00 IDT 2012 | Mon Apr 30 17:00:00 IDT 2012
593 | TBM (S630-1) South-DT Excavation | Fri Mar 30 08:00:00 IDT 2012 | Sun Jan 06 17:00:00 IST 2013
594 | TBM (S630-1) South -UT Excavation | Sun Jan 12 08:00:00 IST 2014 | Sun Sep 14 17:00:00 IDT 2014
595 | Ground Treatment Wk at 811A Retrieval Shaft (SDT & SUT) | Wed Aug 31 08:00:00 IDT 2011 | Sun Dec 04 17:00:00 IST 2011
596 | Ground Wks for Buildings Protection (SDT) - Hoi Wang Road | Mon Aug 01 08:00:00 IDT 2011 | Mon Sep 17 17:00:00 IDT 2012
597 | Ground Wks for Convergence Zones (SDT & SUT) | Mon Jan 16 08:00:00 IST 2012 | Mon Jan 28 17:00:00 IST 2013
598 | Piles Removal@CLP Equipment Bldg.& Footbridges KF-119 by 805 (SDT & SUT) | Sun Nov 13 17:00:00 IST 2011 | Sun Nov 13 17:00:00 IST 2011
599 | Grouting Wk@N/B Ch140+340: Bldg. Foundation (Y.M.T.School) (SUT) | Thu Feb 02 08:00:00 IST 2012 | Tue Jun 12 17:00:00 IDT 2012
600 | Pile Removal for Nam Cheong Property Development by 802 (SDT & SUT) | Sun Jan 15 08:00:00 IST 2012 | Sun Jan 15 08:00:00 IST 2012
601 | TKT Grouting Works - Zone 1 | Mon Feb 13 08:00:00 IST 2012 | Fri Jul 20 17:00:00 IDT 2012
602 | TKT Grouting Works - Zone 2 | Mon Jan 16 08:00:00 IST 2012 | Mon Aug 20 17:00:00 IDT 2012
603 | TKT Grouting Works - Zone 4 | Mon Mar 26 08:00:00 IST 2012 | Mon Nov 05 17:00:00 IST 2012
604 | TKT Grouting Works - Zone 5 | Tue Oct 09 08:00:00 IST 2012 | Mon Apr 22 17:00:00 IDT 2013
605 | Downtrack Construction (South) | Tue Feb 01 08:00:00 IST 2011 | Tue Sep 29 17:00:00 IDT 2015
606 | TBM (S630-1) South-DT Excavation | Thu Apr 12 08:00:00 IDT 2012 | Tue Mar 19 17:00:00 IST 2013
607 | Ground Treatment (South-DT) | Tue Feb 01 08:00:00 IST 2011 | Mon Mar 18 17:00:00 IST 2013
608 | Access Date- Works Area 12.2 | Mon Feb 28 08:00:00 IST 2011 | Mon Feb 28 08:00:00 IST 2011
609 | Site Set up for Ground Treatment at 811A Retrieval Shaft | Sun Jun 19 08:00:00 IDT 2011 | Fri Jul 01 17:00:00 IDT 2011
610 | Ground Treatment Wk at 811A Retrieval Shaft | Sun Jun 19 08:00:00 IDT 2011 | Wed Oct 05 17:00:00 IST 2011
611 | TTMS for Building Foundation Grouting Works (Stage 1) | Mon Feb 28 08:00:00 IST 2011 | Wed Jun 15 17:00:00 IDT 2011
612 | Accesss Date for Wk Area 12.1 (Subject to SLG Approval) | Thu Jul 21 08:00:00 IDT 2011 | Thu Jul 21 08:00:00 IDT 2011
613 | Grouting Wk@Ch140+150: Bldg.Foundation (Charming Garden Blk.8) | Thu Jul 21 08:00:00 IDT 2011 | Wed Aug 31 17:00:00 IDT 2011
614 | Suspension of Grouting Wk@S/B Ch140+150(Charming Garden Blk.8) | Thu Jun 30 08:00:00 IDT 2011 | Thu Jun 30 08:00:00 IDT 2011
615 | Suspension Period for Grouting Wk in (Charming Garden Blk.8) | Mon Aug 01 08:00:00 IDT 2011 | Tue Aug 09 17:00:00 IDT 2011
616 | Re-mobilization for Grouting Wk in (Charming Garden Blk.8) | Mon Aug 01 08:00:00 IDT 2011 | Tue Aug 02 17:00:00 IDT 2011
617 | Grouting Wk@ Ch140+150:(Charming Garden Blk.8) remaining | Thu Jul 21 08:00:00 IDT 2011 | Wed Aug 31 17:00:00 IDT 2011
618 | Reinstatement@ Ch140+150:(Charming Garden Blk.8) & TTMs Stage 2 | Wed Aug 31 08:00:00 IDT 2011 | Thu Sep 15 17:00:00 IDT 2011
619 | Grouting Wk@S/B Ch140+080: Bldg.Foundation (Hoi Fu Court) | Tue Aug 09 08:00:00 IDT 2011 | Mon Dec 12 17:00:00 IST 2011
620 | Reinstatement @ Hoi Fu Court | Wed Aug 31 08:00:00 IDT 2011 | Wed Nov 16 17:00:00 IST 2011
621 | TTMS for Building Foundation Grouting Works (Stage 2) & Site Setup | Wed Feb 22 16:08:00 IST 2012 | Wed Mar 21 16:08:00 IST 2012
622 | Install Sleeve for Grouting works (Charming Garden Blk.9) | Fri Aug 31 08:00:00 IDT 2012 | Sat Sep 29 17:00:00 IST 2012
623 | Grouting Wk@S/B Ch140+200: Bldg.Foundation (Charming Garden Blk.9) | Wed Oct 03 08:00:00 IST 2012 | Mon Oct 29 17:00:00 IST 2012
624 | Reinstatement @ Charming Garden Blk.9 | Wed Jan 09 08:00:00 IST 2013 | Mon Feb 18 17:00:00 IST 2013
625 | GI works for Hoi Wang Road | Tue Feb 01 08:00:00 IST 2011 | Thu Jun 23 17:00:00 IDT 2011
626 | GI works for Tai Kok Tsui | Tue Feb 01 08:00:00 IST 2011 | Thu Dec 01 17:00:00 IST 2011
627 | Design of Ground Treatment for Tunneling (Ch140+080-Ch140+200) | Fri Apr 08 08:00:00 IDT 2011 | Sun Jun 26 17:00:00 IDT 2011
628 | MTR's Review & Comments for Design of Ground Treatment for Tunneling | Sun Jun 19 08:00:00 IDT 2011 | Sun Jun 19 08:00:00 IDT 2011
629 | MTR's Comments & Approval | Sun Jun 19 08:00:00 IDT 2011 | Fri Jul 08 17:00:00 IDT 2011
630 | Prepared Re-submission of Ground Treatment for Tunneling | Sun Jun 19 08:00:00 IDT 2011 | Thu Jun 30 17:00:00 IDT 2011
631 | Design Approval & Issue Construction Instruction MTR | Sun Jun 19 08:00:00 IDT 2011 | Sun Jul 03 17:00:00 IDT 2011
632 | TTMS for Convergence Zone (Stage 2 & 3) | Wed Aug 31 08:00:00 IDT 2011 | Sat Sep 17 17:00:00 IDT 2011
633 | Install Sleeve Pipe (Zone B) | Mon Jan 16 08:00:00 IST 2012 | Sat Mar 03 17:00:00 IST 2012
634 | Convergence Zone Grouting Wk@ Ch140+330 to Ch140+342 (Zone B) | Mon Jan 16 08:00:00 IST 2012 | Tue May 22 17:00:00 IDT 2012
635 | Reinstatement@ Ch140+330 to Ch140+342 (Zone B) | Mon Dec 03 08:00:00 IST 2012 | Wed Jan 02 17:00:00 IST 2013
636 | Install Sleeve Pipe (Zones D) | Mon Jan 16 08:00:00 IST 2012 | Fri Mar 02 17:00:00 IST 2012
637 | Convergence Zone Grouting Wk@ Ch140+361 to Ch140+380 (Zones D) | Mon Jan 16 08:00:00 IST 2012 | Sat Apr 21 17:00:00 IDT 2012
638 | Convergence Zone Grouting Wk@ Ch140+361 to Ch140+380 (Zones E) | Wed Oct 03 08:00:00 IST 2012 | Thu Jan 17 17:00:00 IST 2013
639 | Install Sleeve Pipe (Zone A) | Wed Feb 01 08:00:00 IST 2012 | Tue Feb 28 17:00:00 IST 2012
640 | Convergence Zone Grouting Wk@ Ch140+287 to Ch140+330 (Zone A) | Mon Apr 02 08:00:00 IDT 2012 | Mon Jul 09 17:00:00 IDT 2012
641 | Enlarge for TTMs Stage 4 | Wed Oct 03 08:00:00 IST 2012 | Wed Oct 24 17:00:00 IST 2012
642 | Install Sleeve Pipe (Zone C) | Sat Jun 02 08:00:00 IDT 2012 | Wed Jul 04 17:00:00 IDT 2012
643 | Convergence Zone Grouting Wk@ Ch140+342 to Ch140+361 (Zone C) | Thu Jul 05 08:00:00 IDT 2012 | Sat Nov 03 17:00:00 IST 2012
644 | Reinstatement for Convergence Zone | Fri Feb 01 08:00:00 IST 2013 | Mon Mar 18 17:00:00 IST 2013
645 | Tai Kok Tsui Grouting Works | Mon Jan 16 08:00:00 IST 2012 | Fri Nov 30 08:00:00 IST 2012
646 | Zone 1 | Fri Feb 10 08:00:00 IST 2012 | Fri Aug 31 08:00:00 IDT 2012
647 | TKT Zone 1 - TGLA granted | Fri Feb 10 08:00:00 IST 2012 | Fri Feb 10 08:00:00 IST 2012
648 | TKT Zone 1 - Access Date of works area | Sat Feb 11 08:00:00 IST 2012 | Sat Feb 11 08:00:00 IST 2012
649 | TKT Zone 1 - Trial Pit | Mon Feb 13 08:00:00 IST 2012 | Sat Feb 18 17:00:00 IST 2012
650 | TKT Zone 1 - Site Clearance + Tree Transplant | Mon Feb 20 08:00:00 IST 2012 | Thu Mar 01 17:00:00 IST 2012
651 | TKT Zone 1 - TTMS & Prepare Working platform | Fri Mar 02 08:00:00 IST 2012 | Mon Mar 26 17:00:00 IST 2012
652 | TKT Zone 1 - Install sleeve pipes | Tue Mar 27 08:00:00 IST 2012 | Mon Apr 16 17:00:00 IDT 2012
653 | TKT Zone 1 - Ground Treatment Works (TAM grouting) | Tue Apr 17 08:00:00 IDT 2012 | Mon Jul 16 17:00:00 IDT 2012
654 | TKT Zone 1 - Permeability Test | Tue Jul 17 08:00:00 IDT 2012 | Fri Jul 20 17:00:00 IDT 2012
655 | TKT Zone 1 - TBM Reach Zone 1 | Fri Aug 31 08:00:00 IDT 2012 | Fri Aug 31 08:00:00 IDT 2012
656 | Zone 2 | Mon Jan 16 08:00:00 IST 2012 | Fri Aug 31 08:00:00 IDT 2012
657 | TKT Zone 2 - TTMS (Part 1) | Mon Jan 16 08:00:00 IST 2012 | Mon Jan 16 17:00:00 IST 2012
658 | TKT Zone 2 - Trial pit | Tue Jan 17 08:00:00 IST 2012 | Sat Feb 11 17:00:00 IST 2012
659 | TKT Zone 2 - Site preparation works | Mon Feb 13 08:00:00 IST 2012 | Sat Feb 18 17:00:00 IST 2012
660 | TKT Zone 2 - Install sleeve pipes (Part 1) | Mon Feb 20 08:00:00 IST 2012 | Tue Feb 28 17:00:00 IST 2012
661 | TKT Zone 2 - TTMS (Part 2) | Wed Feb 29 08:00:00 IST 2012 | Tue Mar 13 17:00:00 IST 2012
662 | TKT Zone 2 - Trial pit (Part 2) | Wed Mar 14 08:00:00 IST 2012 | Sat Mar 24 17:00:00 IST 2012
663 | TKT Zone 2 - Site preparation works | Mon Mar 26 08:00:00 IST 2012 | Thu Mar 29 17:00:00 IST 2012
664 | TKT Zone 2 - Install sleeve pipes (Part 2) | Fri Mar 30 08:00:00 IDT 2012 | Fri Apr 13 17:00:00 IDT 2012
665 | TKT Zone 2 - Ground Treatment Works (TAM grouting) (Part 2) | Sat Apr 14 08:00:00 IDT 2012 | Mon May 28 17:00:00 IDT 2012
666 | TKT Zone 2 - Re-arrange TTMS (Part 1) | Tue May 29 08:00:00 IDT 2012 | Thu Jun 07 17:00:00 IDT 2012
667 | TKT Zone 2 - Ground Treatment Works (TAM grouting) (Part 1) | Sat Jun 09 08:00:00 IDT 2012 | Wed Aug 15 17:00:00 IDT 2012
668 | TKT Zone 2 - Permeability Test | Thu Aug 16 08:00:00 IDT 2012 | Mon Aug 20 17:00:00 IDT 2012
669 | TKT Zone 2 - Temporary reinstatement | Tue Aug 21 08:00:00 IDT 2012 | Wed Aug 29 17:00:00 IDT 2012
670 | TKT Zone 2 - TBM Reach Zone 2 | Fri Aug 31 08:00:00 IDT 2012 | Fri Aug 31 08:00:00 IDT 2012
671 | Zone 3 | Mon Jan 16 08:00:00 IST 2012 | Fri Nov 30 08:00:00 IST 2012
672 | TKT Zone 3 - TTMS (Part 1) | Mon Jan 16 08:00:00 IST 2012 | Mon Jan 16 17:00:00 IST 2012
673 | TKT Zone 3 - Trial pit + grout pattern design | Tue Jan 17 08:00:00 IST 2012 | Thu Feb 09 17:00:00 IST 2012
674 | TKT Zone 3 - Install sleeve pipes (Part 1) | Fri Feb 10 08:00:00 IST 2012 | Sat Feb 18 17:00:00 IST 2012
675 | TKT Zone 3 - TTMS (Part 2) + site preparation + Install sleeve pipes (Part 2) | Mon Feb 20 08:00:00 IST 2012 | Tue Mar 20 17:00:00 IST 2012
676 | TKT Zone 3 - Site setup | Wed Mar 21 08:00:00 IST 2012 | Tue Mar 27 17:00:00 IST 2012
677 | TKT Zone 3 - Drilling for Ground treatment works | Wed Mar 28 08:00:00 IST 2012 | Mon Apr 30 17:00:00 IDT 2012
678 | TKT Zone 3 - Further soil investigation to review ground treatment requirement | Sat Apr 14 08:00:00 IDT 2012 | Mon Apr 30 17:00:00 IDT 2012
679 | TKT Zone 3 - Decision to confirm ground treatment requirement | Mon Apr 30 17:00:00 IDT 2012 | Mon Apr 30 17:00:00 IDT 2012
680 | TKT Zone 3 - TBM Reach Zone 3 | Fri Nov 30 08:00:00 IST 2012 | Fri Nov 30 08:00:00 IST 2012
681 | TBM Excavation (South-DT) | Sun Jan 15 08:00:00 IST 2012 | Tue Sep 29 17:00:00 IDT 2015
682 | D/T Excavation Ch139+872-139+875 | Thu Aug 15 08:00:00 IDT 2013 | Sat Aug 17 17:00:00 IDT 2013
683 | TBM resume at Ch139+875 | Fri Aug 16 08:00:00 IDT 2013 | Fri Aug 16 08:00:00 IDT 2013
684 | TBM (S630-1) Delivery on Site | Sun Jan 15 08:00:00 IST 2012 | Sun Jan 15 08:00:00 IST 2012
685 | TBM (S630-1) Assembly, and T&C | Fri Mar 16 08:00:00 IST 2012 | Wed May 30 17:00:00 IDT 2012
686 | D/T TBM (S630-1) Break-in & Excavation Ch137+941-137+967 | Wed Mar 21 08:00:00 IST 2012 | Thu Mar 29 17:00:00 IST 2012
687 | Reach Rising Main & FMO Pier A Obstruction | Thu Mar 29 17:00:00 IST 2012 | Thu Mar 29 17:00:00 IST 2012
688 | D/T Excavation Ch137+967-138+025 | Fri Mar 30 08:00:00 IDT 2012 | Wed Apr 18 17:00:00 IDT 2012
689 | D/T Excavation Ch138+025-138+043 | Thu Apr 19 08:00:00 IDT 2012 | Fri Apr 20 17:00:00 IDT 2012
690 | Reach FMO Pier B Pile Obstruction Ch138+043 | Fri Apr 20 17:00:00 IDT 2012 | Fri Apr 20 17:00:00 IDT 2012
691 | D/T Excavation Ch138+043-138+109 | Sat Apr 21 08:00:00 IDT 2012 | Fri Apr 27 17:00:00 IDT 2012
692 | Reach CP89 (CH138+055) | Sun Apr 22 08:00:00 IDT 2012 | Sun Apr 22 08:00:00 IDT 2012
693 | D/T Excavation Ch138+109-138+149 | Sat Apr 28 08:00:00 IDT 2012 | Mon Apr 30 17:00:00 IDT 2012
694 | Obstructions Removal Below Nam Cheong Property/802 (11Dec2011-Contract) | Sun Jan 15 08:00:00 IST 2012 | Sun Jan 15 08:00:00 IST 2012
695 | Unobstructed Passage Available (30April2012) | Mon Apr 30 08:00:00 IDT 2012 | Mon Apr 30 08:00:00 IDT 2012
696 | Reach Nam Cheong Property Development (Pile removed by 802) | Mon Apr 30 17:00:00 IDT 2012 | Mon Apr 30 17:00:00 IDT 2012
697 | Obstructions Removal Below Nam Cheong Property by 802 (30Apr12) | Mon Apr 30 17:00:00 IDT 2012 | Mon Apr 30 17:00:00 IDT 2012
698 | D/T Excavation Ch138+149-Ch138+170 | Tue May 01 08:00:00 IDT 2012 | Wed May 02 17:00:00 IDT 2012
699 | D/T Excavation Ch138+170-138+420 | Thu May 03 08:00:00 IDT 2012 | Tue May 29 17:00:00 IDT 2012
700 | Reach CP90 (CH138+315) | Sat May 19 08:00:00 IDT 2012 | Sat May 19 08:00:00 IDT 2012
701 | D/T Excavation Ch138+420-138+457 | Wed May 30 08:00:00 IDT 2012 | Fri Jun 01 17:00:00 IDT 2012
702 | Reach Shum Shui Po Pier Pile Obstruction Ch138+457 | Fri Jun 01 17:00:00 IDT 2012 | Fri Jun 01 17:00:00 IDT 2012
703 | D/T Excavation Ch138+457-138+480 | Sat Jun 02 08:00:00 IDT 2012 | Sun Jun 03 17:00:00 IDT 2012
704 | D/T Excavation Ch138+480-138+590 | Mon Jun 04 08:00:00 IDT 2012 | Tue Jun 12 17:00:00 IDT 2012
705 | Reach CP91 (CH138+521) | Thu Jun 07 08:00:00 IDT 2012 | Thu Jun 07 08:00:00 IDT 2012
706 | Reach YC2 Culvert Pile Obstruction Ch138+590 | Tue Jun 12 17:00:00 IDT 2012 | Tue Jun 12 17:00:00 IDT 2012
707 | D/T Excavation Ch138+590-138+771 | Wed Jun 13 08:00:00 IDT 2012 | Wed Jun 27 17:00:00 IDT 2012
708 | Reach CP92 (CH138+771) | Wed Jun 27 17:00:00 IDT 2012 | Wed Jun 27 17:00:00 IDT 2012
709 | D/T Excavation Ch138+771-138+950 | Thu Jun 28 08:00:00 IDT 2012 | Tue Jul 10 17:00:00 IDT 2012
710 | Reach NC1 Culvert Pile Obstruction Ch138+950 | Tue Jul 10 17:00:00 IDT 2012 | Tue Jul 10 17:00:00 IDT 2012
711 | D/T Excavation Ch138+950-139+044 | Wed Jul 11 08:00:00 IDT 2012 | Tue Jul 17 17:00:00 IDT 2012
712 | Reach CP93 (CH138+996) | Sat Jul 14 08:00:00 IDT 2012 | Sat Jul 14 08:00:00 IDT 2012
713 | Piles Removal@CLP Equipment Bldg.& Footbridges KF-119 by 805 | Sun Jan 15 08:00:00 IST 2012 | Sun Jan 15 08:00:00 IST 2012
714 | Reach Footbridge KF119 (Pile removed by 805) | Fri Aug 31 08:00:00 IDT 2012 | Fri Aug 31 08:00:00 IDT 2012
715 | D/T Excavation Ch139+044-139+100 | Fri Aug 31 08:00:00 IDT 2012 | Wed Sep 05 17:00:00 IDT 2012
716 | D/T Excavation Ch139+100-139+120 | Thu Sep 06 08:00:00 IDT 2012 | Sun Sep 09 17:00:00 IDT 2012
717 | D/T Excavation Ch139+120-139+350 | Mon Sep 10 08:00:00 IDT 2012 | Wed Nov 07 17:00:00 IST 2012
718 | Reach CP94(CH139+265) | Wed Oct 24 17:00:00 IST 2012 | Wed Oct 24 17:00:00 IST 2012
719 | D/T Excavation Ch139+350-139+450 | Thu Nov 15 08:00:00 IST 2012 | Wed Nov 28 17:00:00 IST 2012
720 | D/T Excavation Ch139+450-139+825 | Tue Nov 13 08:00:00 IST 2012 | Sat Dec 15 17:00:00 IST 2012
721 | Reach CP95(CH139+504) | Sun Nov 18 08:00:00 IST 2012 | Sun Nov 18 08:00:00 IST 2012
722 | Reach CP96(CH139+711) | Fri Dec 28 17:00:00 IST 2012 | Fri Dec 28 17:00:00 IST 2012
723 | D/T Excavation Ch139+825-139+872 | Mon Jan 21 08:00:00 IST 2013 | Wed Jan 30 17:00:00 IST 2013
724 | **HWR H-pile Obstruction Removal | Tue Jan 22 08:00:00 IST 2013 | Thu Aug 15 17:00:00 IDT 2013
725 | D/T Excavation Ch139+875 -139+920 | Fri Aug 16 08:00:00 IDT 2013 | Mon Aug 19 17:00:00 IDT 2013
726 | D/T Excavation Ch139+920-139+950 | Sat Aug 24 08:00:00 IDT 2013 | Sun Aug 25 17:00:00 IDT 2013
727 | D/T Excavation Ch139+950-140+010 | Mon Aug 26 08:00:00 IDT 2013 | Thu Aug 29 17:00:00 IDT 2013
728 | Reach CP97 (CH139+961) | Mon Aug 26 17:00:00 IDT 2013 | Mon Aug 26 17:00:00 IDT 2013
729 | D/T Excavation Ch140+010-140+180 | Sat Aug 31 08:00:00 IDT 2013 | Tue Sep 10 17:00:00 IDT 2013
730 | Reach Hoi Fu Court (CH140+063) | Tue Sep 03 17:00:00 IDT 2013 | Tue Sep 03 17:00:00 IDT 2013
731 | Reach Charming Garden No.8 (CH140+139) | Sun Sep 08 17:00:00 IDT 2013 | Sun Sep 08 17:00:00 IDT 2013
732 | D/T Excavation Ch140+180-140+270 | Wed Sep 11 08:00:00 IDT 2013 | Wed Sep 18 17:00:00 IDT 2013
733 | Reach CP98(CH140+211) | Fri Sep 13 17:00:00 IDT 2013 | Fri Sep 13 17:00:00 IDT 2013
734 | Reach Charming Garden No.9 (CH140+207) | Fri Sep 13 17:00:00 IDT 2013 | Fri Sep 13 17:00:00 IDT 2013
735 | Advance Noice to Contract 811A for TBM Break In (30d) | Fri Aug 16 17:00:00 IDT 2013 | Fri Aug 16 17:00:00 IDT 2013
736 | D/T Excavation Ch140+270-140+385-Shaft 811A | Tue Sep 17 08:00:00 IDT 2013 | Sat Sep 28 17:00:00 IDT 2013
737 | Exit Convergence Zone (Ch140+287~) | Wed Sep 18 17:00:00 IDT 2013 | Wed Sep 18 17:00:00 IDT 2013
738 | D/T exit Box Cleaning for TBM Dismantling | Fri Sep 25 08:00:00 IDT 2015 | Tue Sep 29 17:00:00 IDT 2015
739 | Advance Noice to Contract 811A for Set Up of TBM Retrieval (60d) | Thu Aug 01 17:00:00 IDT 2013 | Thu Aug 01 17:00:00 IDT 2013
740 | D/T Preparation Works inside Exit Shaft 811A | Mon Aug 26 08:00:00 IDT 2013 | Sat Sep 28 17:00:00 IDT 2013
741 | TBM (S630-1) Backup pull back | Mon Oct 07 08:00:00 IDT 2013 | Wed Oct 16 17:00:00 IDT 2013
742 | TBM (S630-1) Shield Dismantle & Removal | Mon Sep 30 08:00:00 IDT 2013 | Sun Nov 10 17:00:00 IST 2013
743 | Setup Equipment for Invert & Walkway Construction (Ch140+385-811A Shaft to Ch139+224-CP94) | Mon Nov 18 08:00:00 IST 2013 | Sat Nov 30 17:00:00 IST 2013
744 | Tunnel Invert & Walkway (811A side - Ch140+385-811A Shaft to Ch139+224-CP94) | Mon Dec 02 08:00:00 IST 2013 | Wed Mar 05 17:00:00 IST 2014
745 | Setup Equipment for Invert & Walkway Construction (Ch137+941-NAC Shaft to Ch139+224-CP94) | Tue Feb 04 08:00:00 IST 2014 | Fri Feb 14 17:00:00 IST 2014
746 | Tunnel Invert & Walkway (820 side - Ch137+941-NAC Shaft to Ch139+224-CP94) | Wed Feb 12 08:00:00 IST 2014 | Mon May 19 17:00:00 IDT 2014
747 | Deg. 1 Works (4A(ii) Target: 18-May-14) | Sat Mar 01 08:00:00 IST 2014 | Mon Jun 23 17:00:00 IDT 2014
748 | Uptrack Construction (South) | Wed Aug 31 08:00:00 IDT 2011 | Mon Jan 26 17:00:00 IST 2015
749 | Ground Treatment (South-UT) | Wed Aug 31 08:00:00 IDT 2011 | Wed Nov 20 17:00:00 IST 2013
750 | Works Area 12.1 (Subject to SLG Approval) | Wed Aug 31 08:00:00 IDT 2011 | Wed Aug 31 08:00:00 IDT 2011
751 | Site Set up for Y.M.T School Grouting Works | Wed Aug 31 08:00:00 IDT 2011 | Mon Oct 31 17:00:00 IST 2011
752 | Install Sleeve Pipe (Y.M.T. Catholic Primary School) (UT) | Mon Jan 16 08:00:00 IST 2012 | Tue Feb 14 17:00:00 IST 2012
753 | Grouting Wk@N/B Ch140+340: Bldg. Foundation (Y.M.T. Catholic Primary School) (UT) | Mon Jan 16 08:00:00 IST 2012 | Thu Apr 19 17:00:00 IDT 2012
754 | Reinstatement Works for Y.M.T. School | Fri Aug 31 08:00:00 IDT 2012 | Sat Sep 29 17:00:00 IST 2012
755 | Tai Kok Tsui Grouting Works | Mon Mar 26 08:00:00 IST 2012 | Wed Nov 20 17:00:00 IST 2013
756 | Zone 4 | Mon Mar 26 08:00:00 IST 2012 | Wed Nov 20 17:00:00 IST 2013
757 | TKT Zone 4 - Trial pit | Mon Mar 26 08:00:00 IST 2012 | Wed Apr 11 17:00:00 IDT 2012
758 | TKT Zone 4 - Sleeves installation | Wed Oct 03 08:00:00 IST 2012 | Thu Oct 11 17:00:00 IST 2012
759 | TKT Zone 4 - Ground Treatment Works (TAM grouting) | Fri Oct 12 08:00:00 IST 2012 | Wed Jan 09 17:00:00 IST 2013
760 | TKT Zone 4 - Permeability Test | Mon Apr 15 08:00:00 IDT 2013 | Thu Apr 18 17:00:00 IDT 2013
761 | TKT Zone 4 - Reinstatement | Mon Aug 12 08:00:00 IDT 2013 | Wed Nov 20 17:00:00 IST 2013
762 | Zone 5 | Fri Nov 09 08:00:00 IST 2012 | Thu Jul 04 17:00:00 IDT 2013
763 | TKT Zone 5 - Trial pit | Fri Nov 30 08:00:00 IST 2012 | Sat Dec 22 17:00:00 IST 2012
764 | TKT Zone 5 - Install guide sleeves (Stage 1) | Mon Dec 24 08:00:00 IST 2012 | Fri Jan 11 17:00:00 IST 2013
765 | TKT Zone 5 - TTMS (Part 2) + Trial pit | Fri Nov 09 08:00:00 IST 2012 | Sat Dec 15 17:00:00 IST 2012
766 | TKT Zone 5 - Install guide sleeves (Stage 2) | Wed Jan 02 08:00:00 IST 2013 | Wed Jan 16 17:00:00 IST 2013
767 | TKT Zone 5 - Ground Treatment Works (TAM grouting) Part 2 | Thu Jan 17 08:00:00 IST 2013 | Mon Mar 18 17:00:00 IST 2013
768 | TKT Zone 5 - Rearrange TTMS (Part 1) | Thu Jan 10 08:00:00 IST 2013 | Wed Jan 23 17:00:00 IST 2013
769 | TKT Zone 5 - Ground Treatment Works (TAM grouting) Part 1 | Fri Jan 11 08:00:00 IST 2013 | Mon Mar 04 17:00:00 IST 2013
770 | TKT Zone 5 - Permeability Test | Mon Mar 25 08:00:00 IST 2013 | Thu Mar 28 17:00:00 IST 2013
771 | TKT Zone 5 - Reinstatement | Tue Apr 30 08:00:00 IDT 2013 | Thu Jul 04 17:00:00 IDT 2013
772 | Zone 6 | Sat Apr 14 08:00:00 IDT 2012 | Mon Apr 30 17:00:00 IDT 2012
773 | TKT Zone 6 - Further soil investigation to review ground treatment requirement | Sat Apr 14 08:00:00 IDT 2012 | Mon Apr 30 17:00:00 IDT 2012
774 | TKT Zone 6 - Decision to confirm ground treatment requirement | Mon Apr 30 17:00:00 IDT 2012 | Mon Apr 30 17:00:00 IDT 2012
775 | TBM Excavation (South-UT) | Sun Jan 15 08:00:00 IST 2012 | Mon Jan 26 17:00:00 IST 2015
776 | TBM S630-1 Re-assembly | Tue Oct 15 08:00:00 IDT 2013 | Fri Dec 06 17:00:00 IST 2013
777 | U/T Excavation Ch137+968-137+993 (Break-in) | Sat Dec 14 08:00:00 IST 2013 | Thu Dec 19 17:00:00 IST 2013
778 | Reach Rising Main & FMO Pier A Obstruction | Thu Dec 19 17:00:00 IST 2013 | Thu Dec 19 17:00:00 IST 2013
779 | U/T Excavation Ch137+993-138+040 | Thu Dec 19 08:00:00 IST 2013 | Mon Dec 30 17:00:00 IST 2013
780 | U/T Excavation Ch138+040-138+070 | Wed Dec 25 08:00:00 IST 2013 | Thu Dec 26 17:00:00 IST 2013
781 | Reach FMO Pier B Pile Obstruction Ch138+070 | Thu Dec 26 17:00:00 IST 2013 | Thu Dec 26 17:00:00 IST 2013
782 | U/T Excavation Ch138+070-138+175 | Thu Dec 26 08:00:00 IST 2013 | Thu Jan 02 17:00:00 IST 2014
783 | Reach CP89 (CH138+081) | Fri Dec 27 17:00:00 IST 2013 | Fri Dec 27 17:00:00 IST 2013
784 | Obstructions Removal BelowNamCheong Property/ 802 (11Dec2011-Contract) | Sun Jan 15 08:00:00 IST 2012 | Sun Jan 15 08:00:00 IST 2012
785 | Unobstructed Pasage Available (30 April 2013) (further confirm by MTR) | Tue Apr 30 17:00:00 IDT 2013 | Tue Apr 30 17:00:00 IDT 2013
786 | Reach Nam Cheong Property Property / 802 | Mon Dec 30 17:00:00 IST 2013 | Mon Dec 30 17:00:00 IST 2013
787 | Obstructions Removal Below Nam Cheong Property by 802 | Tue Apr 30 17:00:00 IDT 2013 | Tue Apr 30 17:00:00 IDT 2013
788 | U/T Excavation Ch138+175 -138+450 | Sat Jan 04 08:00:00 IST 2014 | Sun Jan 26 17:00:00 IST 2014
789 | Reach CP90 (CH138+341) | Fri Apr 04 17:00:00 IDT 2014 | Fri Apr 04 17:00:00 IDT 2014
790 | U/T Excavation Ch138+450-138+490 | Wed Apr 09 08:00:00 IDT 2014 | Fri Apr 11 17:00:00 IDT 2014
791 | Reach Shum Shui Po Pier Pile Obstruction Ch138+490 | Fri Apr 11 17:00:00 IDT 2014 | Fri Apr 11 17:00:00 IDT 2014
792 | U/T Excavation Ch138+490-138+610 | Fri Apr 11 08:00:00 IDT 2014 | Fri Apr 18 17:00:00 IDT 2014
793 | Reach CP91 (CH138+546) | Mon Apr 14 17:00:00 IDT 2014 | Mon Apr 14 17:00:00 IDT 2014
794 | Reach YC2 Culvert Pile Obstruction Ch138+610 | Thu Apr 17 17:00:00 IDT 2014 | Thu Apr 17 17:00:00 IDT 2014
795 | U/T Excavation Ch138+610-138+670 | Thu Apr 17 08:00:00 IDT 2014 | Sun Apr 20 17:00:00 IDT 2014
796 | Reach NC1 Culvert Pile Obstruction Ch138+670 | Tue Apr 22 17:00:00 IDT 2014 | Tue Apr 22 17:00:00 IDT 2014
797 | U/T Excavation Ch138+670-139+026 | Tue Apr 22 08:00:00 IDT 2014 | Fri May 16 17:00:00 IDT 2014
798 | Reach CP92 (CH138+796) | Tue Apr 29 17:00:00 IDT 2014 | Tue Apr 29 17:00:00 IDT 2014
799 | Reach CP93 (CH139+021) | Sun May 11 17:00:00 IDT 2014 | Sun May 11 17:00:00 IDT 2014
800 | Piles Removal@CLP Equipment Bldg.& Footbridges KF-119 by 805 | Sun Jan 15 08:00:00 IST 2012 | Sun Jan 15 08:00:00 IST 2012
801 | Reach Footbridge KF119 (Piles removed by 805) | Wed Mar 12 17:00:00 IST 2014 | Wed Mar 12 17:00:00 IST 2014
802 | U/T Excavation Ch139+026-139+150 | Mon May 12 08:00:00 IDT 2014 | Tue May 20 17:00:00 IDT 2014
803 | U/T Excavation Ch139+150-139+360 | Thu May 22 08:00:00 IDT 2014 | Wed Jul 09 17:00:00 IDT 2014
804 | Reach CP94 (CH139+287) | Fri Jun 27 17:00:00 IDT 2014 | Fri Jun 27 17:00:00 IDT 2014
805 | U/T Excavation Ch139+360-139+530 | Fri Jun 27 08:00:00 IDT 2014 | Mon Jul 14 17:00:00 IDT 2014
806 | Reach CP95 (CH139+524) | Wed Jul 23 17:00:00 IDT 2014 | Wed Jul 23 17:00:00 IDT 2014
807 | U/T Excavation Ch139+530-139+825 | Thu Jul 24 08:00:00 IDT 2014 | Sat Aug 16 17:00:00 IDT 2014
808 | Reach CP96 (CH139+729) | Sat Aug 16 17:00:00 IDT 2014 | Sat Aug 16 17:00:00 IDT 2014
809 | U/T Excavation Ch139+825-139+875 | Sat Aug 30 08:00:00 IDT 2014 | Mon Sep 08 17:00:00 IDT 2014
810 | U/T Excavation Ch139+875-139+950 | Thu Sep 04 08:00:00 IDT 2014 | Wed Sep 10 17:00:00 IDT 2014
811 | U/T Excavation Ch139+950-140+010 | Mon Sep 08 08:00:00 IDT 2014 | Thu Sep 11 17:00:00 IDT 2014
812 | Reach CP97 (CH139+977) | Tue Sep 09 17:00:00 IDT 2014 | Tue Sep 09 17:00:00 IDT 2014
813 | Advance Noice to Contract 811A for Set Up of TBM Retrieval (60d) | Fri Jun 27 17:00:00 IDT 2014 | Fri Jun 27 17:00:00 IDT 2014
814 | Advance Noice to Contract 811A for TBM Break-out (30d) | Fri Aug 15 17:00:00 IDT 2014 | Fri Aug 15 17:00:00 IDT 2014
815 | U/T Excavation Ch140+010-140+394-Shaft 811A (Break-out) | Wed Sep 10 08:00:00 IDT 2014 | Wed Oct 08 17:00:00 IDT 2014
816 | Reach CP98 (CH140+226) | Fri Sep 19 17:00:00 IDT 2014 | Fri Sep 19 17:00:00 IDT 2014
817 | Reach YMT School (CH140+335) | Wed Sep 24 17:00:00 IDT 2014 | Wed Sep 24 17:00:00 IDT 2014
818 | U/T exit Box Cleaning for TBM Dismantling | Tue Sep 30 08:00:00 IDT 2014 | Sat Oct 04 17:00:00 IDT 2014
819 | U/T Preparation Works inside Exit Shaft 811A | Mon Sep 01 08:00:00 IDT 2014 | Sat Oct 04 17:00:00 IDT 2014
820 | TBM (S630-1) Shield Dismantle & Removal | Mon Oct 06 08:00:00 IDT 2014 | Mon Nov 10 17:00:00 IST 2014
821 | TBM (S630-1) Backup Removal | Sat Nov 01 08:00:00 IST 2014 | Mon Nov 10 17:00:00 IST 2014
822 | Setup Equipment for Invert & Walkway Construction (Ch137+941-NAC Shaft to Ch139+435) (7 working days) | Thu Oct 16 08:00:00 IDT 2014 | Mon Oct 20 17:00:00 IDT 2014
823 | Setup Equipment for Invert & Walkway Construction (Ch140+385-811A Shaft to Ch139+435) | Mon Nov 03 08:00:00 IST 2014 | Thu Nov 13 17:00:00 IST 2014
824 | 820 side - Tunnel Invert & Walkway (Ch137+941-NAC Shaft to Ch139+435, 1494m) (7 working days) | Tue Oct 21 08:00:00 IDT 2014 | Sat Jan 03 17:00:00 IST 2015
825 | 820 side - Deg. 1 Works (Ch137+941-Shaft to Ch139+435) (4B(ii) Target: 21-Dec-14) (7 working days) | Mon Nov 03 08:00:00 IST 2014 | Sat Dec 27 17:00:00 IST 2014
826 | 811A side -Tunnel Invert & Walkway (Ch139+435 to Ch140+385-811A Shaft, 950m) | Mon Nov 10 08:00:00 IST 2014 | Mon Jan 19 17:00:00 IST 2015
827 | 811A side - Deg. 1 Works ( Ch140+385-811A Shaft to Ch139+435) (4B(iii) Target: 25-Jan-15) | Mon Dec 01 08:00:00 IST 2014 | Mon Jan 26 17:00:00 IST 2015
828 | Tunnel Alignment Design/Submission/Approval | Mon Jan 31 08:00:00 IST 2011 | Thu Jul 07 17:00:00 IDT 2011
829 | Design | Mon Jan 31 08:00:00 IST 2011 | Thu Jul 07 17:00:00 IDT 2011
830 | AIP Submission Preparation - Tunnel Alignment | Mon Jan 31 08:00:00 IST 2011 | Mon Feb 21 17:00:00 IST 2011
831 | AIP Submission to MTR (RDO/GEO consultation) | Sat Mar 12 17:00:00 IST 2011 | Sat Mar 12 17:00:00 IST 2011
832 | AIP Comment by MTR (RDO/GEO consultation) | Sun Mar 13 08:00:00 IST 2011 | Sun Mar 27 17:00:00 IST 2011
833 | AIP ReSubmission Preparation - Tunnel Alignment | Wed Apr 06 08:00:00 IDT 2011 | Mon Apr 18 17:00:00 IDT 2011
834 | AIP ReSubmission to MTR (RDO/GEO consultation) | Sat May 07 17:00:00 IDT 2011 | Sat May 07 17:00:00 IDT 2011
835 | AIP Approval by MTR (RDO/GEO consultation) | Sun May 08 08:00:00 IDT 2011 | Thu Jul 07 17:00:00 IDT 2011
836 | DD Submission MTR/RDO for Record | Tue May 31 17:00:00 IDT 2011 | Tue May 31 17:00:00 IDT 2011
837 | Cross Passages | Thu Oct 21 08:00:00 IST 2010 | Tue Jan 13 17:00:00 IST 2015
838 | CP81 (XRL821) | Mon Mar 04 08:00:00 IST 2013 | Tue Apr 02 17:00:00 IDT 2013
839 | CP82 (XRL821) | Tue Jul 23 08:00:00 IDT 2013 | Tue Mar 18 17:00:00 IST 2014
840 | CP83 (XRL821) | Sat May 11 08:00:00 IDT 2013 | Wed Jan 22 17:00:00 IST 2014
841 | CP84 (XRL821) | Sat Apr 06 08:00:00 IDT 2013 | Wed Jan 08 17:00:00 IST 2014
842 | CP85 | Tue Jan 15 08:00:00 IST 2013 | Fri Sep 13 17:00:00 IDT 2013
843 | CP86 Jet / Fissure Grouting from Surface | Mon Jan 16 08:00:00 IST 2012 | Sat Oct 20 17:00:00 IST 2012
844 | CP86 | Sat Dec 15 08:00:00 IST 2012 | Mon Aug 12 17:00:00 IDT 2013
845 | CP87 | Fri Aug 31 08:00:00 IDT 2012 | Thu Sep 26 17:00:00 IDT 2013
846 | CP88 Jet Grouting from Surface | Wed Aug 31 08:00:00 IDT 2011 | Mon Dec 12 17:00:00 IST 2011
847 | CP88 | Fri Aug 31 08:00:00 IDT 2012 | Wed Sep 11 17:00:00 IDT 2013
848 | CP89 Grouting from Surface | Wed Aug 31 08:00:00 IDT 2011 | Thu Mar 29 17:00:00 IST 2012
849 | CP89 | Fri Sep 07 08:00:00 IDT 2012 | Sat Oct 26 17:00:00 IDT 2013
850 | CP90 | Fri Aug 31 08:00:00 IDT 2012 | Sat Dec 28 17:00:00 IST 2013
851 | CP91 Grouting from Surface | Mon Sep 12 08:00:00 IDT 2011 | Wed Mar 21 17:00:00 IST 2012
852 | CP91 | Wed Oct 31 08:00:00 IST 2012 | Thu Oct 17 17:00:00 IDT 2013
853 | CP92 Grouting from Surface | Wed Aug 31 08:00:00 IDT 2011 | Wed Mar 28 17:00:00 IST 2012
854 | CP92 | Wed Oct 31 08:00:00 IST 2012 | Mon Nov 04 17:00:00 IST 2013
855 | CP93 Grouting from Surface | Mon Jan 16 08:00:00 IST 2012 | Thu Oct 04 17:00:00 IST 2012
856 | CP93 | Tue Nov 27 08:00:00 IST 2012 | Mon Nov 18 17:00:00 IST 2013
857 | CP94 Fissure Grouting from Tunnel | Mon Dec 31 08:00:00 IST 2012 | Tue May 14 17:00:00 IDT 2013
858 | CP94 | Sat May 25 08:00:00 IDT 2013 | Tue Jan 21 13:38:00 IST 2014
859 | CP95 & pump Sump | Wed Jul 24 08:00:00 IDT 2013 | Fri Mar 21 13:38:00 IST 2014
860 | CP96 | Tue Sep 30 08:00:00 IDT 2014 | Thu Nov 20 17:00:00 IST 2014
861 | CP97 Jet Grouting from Surface | Mon Jan 16 08:00:00 IST 2012 | Wed Oct 31 17:00:00 IST 2012
862 | CP97 | Sun Nov 30 08:00:00 IST 2014 | Tue Dec 09 17:00:00 IST 2014
863 | CP98 | Sat Nov 30 08:00:00 IST 2013 | Sat Nov 30 08:00:00 IST 2013
864 | TTM Scheme Submission & Approval | Mon Jan 31 08:00:00 IST 2011 | Tue Jul 19 17:00:00 IDT 2011
865 | Prepare Temporary Traffic Management | Mon Jan 31 08:00:00 IST 2011 | Tue Mar 01 17:00:00 IST 2011
866 | TTM reviewed by SLG | Wed Mar 02 08:00:00 IST 2011 | Tue Mar 08 17:00:00 IST 2011
867 | Notification to RMO | Sun Jun 19 08:00:00 IDT 2011 | Wed Jul 06 17:00:00 IDT 2011
868 | XP Application & Approval | Sun Jun 19 08:00:00 IDT 2011 | Tue Jul 19 17:00:00 IDT 2011
869 | Implement TTM | Sun Jun 19 17:00:00 IDT 2011 | Sun Jun 19 17:00:00 IDT 2011
870 | CP81 (XRL821) | Sat Feb 23 08:00:00 IST 2013 | Tue Jan 13 17:00:00 IST 2015
871 | CP81 Preparation works for Grouting | Mon Mar 04 08:00:00 IST 2013 | Tue Apr 02 17:00:00 IDT 2013
872 | CP81 Fissure Grouting from Tunnel | Mon Mar 04 08:00:00 IST 2013 | Thu May 16 17:00:00 IDT 2013
873 | Probing/Drainage (from DT) | Mon Mar 11 08:00:00 IST 2013 | Wed Mar 13 17:00:00 IST 2013
874 | Segment Dismantle (DT) | Mon Mar 11 08:00:00 IST 2013 | Sat Mar 16 17:00:00 IST 2013
875 | Tunnel Frame Support (DT) | Mon Mar 11 08:00:00 IST 2013 | Sat Mar 16 17:00:00 IST 2013
876 | Mobilization (UT) | Mon Nov 11 08:00:00 IST 2013 | Wed Nov 13 17:00:00 IST 2013
877 | Probing/Drainage (from UT) | Wed Nov 13 08:00:00 IST 2013 | Tue Nov 19 17:00:00 IST 2013
878 | Segment Dismantle (UT) | Fri Nov 15 08:00:00 IST 2013 | Thu Nov 21 17:00:00 IST 2013
879 | Cross Passage Excavation & Temp.Support (from UT) | Sat Feb 23 08:00:00 IST 2013 | Fri Mar 01 17:00:00 IST 2013
880 | Waterproofing | Tue Nov 19 08:00:00 IST 2013 | Thu Nov 28 17:00:00 IST 2013
881 | Permanent Beam | Sat Jan 04 08:00:00 IST 2014 | Tue Jan 14 17:00:00 IST 2014
882 | Permanent Lining | Wed Jan 07 08:00:00 IST 2015 | Tue Jan 13 17:00:00 IST 2015
883 | Permanent Slab | Mon Nov 25 08:00:00 IST 2013 | Sat Nov 30 17:00:00 IST 2013
884 | CP82 (XRL821) | Sat Dec 15 08:00:00 IST 2012 | Tue Mar 18 17:00:00 IST 2014
885 | CP82 (XRL821) | Tue Jul 23 08:00:00 IDT 2013 | Tue Mar 18 17:00:00 IST 2014
886 | CP82 Preparation works for Grouting | Sat Dec 15 08:00:00 IST 2012 | Wed Jan 16 17:00:00 IST 2013
887 | CP82 Fissure Grouting from Tunnel | Sat Dec 15 08:00:00 IST 2012 | Tue Mar 05 17:00:00 IST 2013
888 | Probing/Drainage (DT) | Sat Dec 15 08:00:00 IST 2012 | Sat Dec 22 17:00:00 IST 2012
889 | Segment Dismantle (DT) | Sat Dec 15 08:00:00 IST 2012 | Sat Dec 22 17:00:00 IST 2012
890 | Cross Passage Excavation & Temp.Support (from DT) | Tue Mar 12 08:00:00 IST 2013 | Mon Mar 25 17:00:00 IST 2013
891 | Waterproofing (DT) | Mon Mar 25 08:00:00 IST 2013 | Sat Apr 06 17:00:00 IDT 2013
892 | Permanent Beam (DT) | Mon Apr 08 08:00:00 IDT 2013 | Thu Apr 18 17:00:00 IDT 2013
893 | Probing/Drainage (UT) | Thu Nov 21 08:00:00 IST 2013 | Wed Nov 27 17:00:00 IST 2013
894 | Segment Dismantle (UT) | Thu Nov 21 08:00:00 IST 2013 | Wed Nov 27 17:00:00 IST 2013
895 | Cross Passage Excavation & Temp.Support (from UT) | Tue Mar 12 08:00:00 IST 2013 | Wed Mar 20 17:00:00 IST 2013
896 | Waterproofing (UT) | Thu Nov 21 08:00:00 IST 2013 | Sat Nov 30 17:00:00 IST 2013
897 | Permanent Beam (UT) | Thu Nov 21 08:00:00 IST 2013 | Sat Nov 30 17:00:00 IST 2013
898 | Permanent Lining | Thu Nov 21 08:00:00 IST 2013 | Wed Nov 27 17:00:00 IST 2013
899 | Permanent Slab | Thu Nov 21 08:00:00 IST 2013 | Wed Nov 27 17:00:00 IST 2013
900 | CP83 (XRL821) | Wed Oct 03 08:00:00 IST 2012 | Wed Jan 22 17:00:00 IST 2014
901 | CP83 (XRL821) | Sat May 11 08:00:00 IDT 2013 | Wed Jan 22 17:00:00 IST 2014
902 | CP83 Preparation works for Grouting | Wed Oct 03 08:00:00 IST 2012 | Sat Dec 15 17:00:00 IST 2012
903 | CP83 Re-setup for Grouting | Mon Oct 08 08:00:00 IST 2012 | Wed Oct 10 17:00:00 IST 2012
904 | CP83 Fissure Grouting from Tunnel Part I | Thu Oct 11 08:00:00 IST 2012 | Wed Jan 23 17:00:00 IST 2013
905 | CP83 Fissure Grouting from Tunnel Part II | Thu Oct 11 08:00:00 IST 2012 | Sat Oct 27 17:00:00 IST 2012
906 | Probing/Drainage (DT) | Thu Oct 18 08:00:00 IST 2012 | Thu Oct 25 17:00:00 IST 2012
907 | Segment Dismantle (DT) | Thu Oct 18 08:00:00 IST 2012 | Thu Oct 25 17:00:00 IST 2012
908 | Cross Passage Excavation & Temp.Support (from DT) | Fri Oct 19 08:00:00 IST 2012 | Thu Jan 31 17:00:00 IST 2013
909 | Waterproofing (DT) | Mon Mar 18 08:00:00 IST 2013 | Sat Mar 23 17:00:00 IST 2013
910 | Permanent Beam (DT) | Mon Mar 25 08:00:00 IST 2013 | Sat Apr 06 17:00:00 IDT 2013
911 | Probing/Drainage (UT) | Wed Oct 02 08:00:00 IDT 2013 | Fri Nov 22 17:00:00 IST 2013
912 | Segment Dismantle (UT) | Thu Nov 21 08:00:00 IST 2013 | Wed Nov 27 17:00:00 IST 2013
913 | Cross Passage Excavation & Temp.Support (from UT) | Sat Feb 23 08:00:00 IST 2013 | Mon Mar 04 17:00:00 IST 2013
914 | Waterproofing (UT) | Thu Nov 21 08:00:00 IST 2013 | Sat Nov 30 17:00:00 IST 2013
915 | Permanent Beam (UT) | Thu Nov 21 08:00:00 IST 2013 | Sat Nov 30 17:00:00 IST 2013
916 | Permanent Lining | Thu Nov 21 08:00:00 IST 2013 | Wed Nov 27 17:00:00 IST 2013
917 | Permanent Slab | Thu Nov 21 08:00:00 IST 2013 | Wed Nov 27 17:00:00 IST 2013
918 | CP84 (XRL821) | Mon Sep 03 08:00:00 IDT 2012 | Mon Sep 22 17:00:00 IDT 2014
919 | CP84 (XRL821) | Sat Apr 06 08:00:00 IDT 2013 | Wed Jan 08 17:00:00 IST 2014
920 | CP84 Preparation works for Grouting | Mon Sep 03 08:00:00 IDT 2012 | Thu Oct 04 17:00:00 IST 2012
921 | CP84 Fissure Grouting from Tunnel | Tue Sep 11 08:00:00 IDT 2012 | Sat Jan 12 17:00:00 IST 2013
922 | Probing/Drainage (DT) | Tue Sep 11 08:00:00 IDT 2012 | Mon Sep 17 17:00:00 IDT 2012
923 | Segment Dismantle (DT) | Wed Sep 19 08:00:00 IDT 2012 | Wed Sep 26 17:00:00 IST 2012
924 | Cross Passage Excavation & Temp.Support (from DT) | Wed Sep 26 08:00:00 IST 2012 | Sat Dec 29 17:00:00 IST 2012
925 | Waterproofing (DT) | Mon Mar 18 08:00:00 IST 2013 | Wed Mar 27 17:00:00 IST 2013
926 | Permanent Beam (DT) | Mon Mar 25 08:00:00 IST 2013 | Sat Apr 06 17:00:00 IDT 2013
927 | Probing/Drainage (UT) | Mon Aug 26 08:00:00 IDT 2013 | Tue Sep 03 17:00:00 IDT 2013
928 | Segment Dismantle (UT) | Mon Sep 02 08:00:00 IDT 2013 | Sat Sep 07 17:00:00 IDT 2013
929 | Cross Passage Excavation & Temp.Support (from U/T) | Wed Sep 04 08:00:00 IDT 2013 | Fri Sep 13 17:00:00 IDT 2013
930 | Waterproofing (UT) | Thu Sep 11 08:00:00 IDT 2014 | Mon Sep 22 17:00:00 IDT 2014
931 | Permanent Beam (UT) | Sat Sep 14 08:00:00 IDT 2013 | Thu Sep 26 17:00:00 IDT 2013
932 | Permanent Lining | Fri Sep 13 08:00:00 IDT 2013 | Sat Sep 21 17:00:00 IDT 2013
933 | Permanent Slab | Mon Sep 16 08:00:00 IDT 2013 | Tue Sep 24 17:00:00 IDT 2013
934 | CP85 | Tue Feb 01 08:00:00 IST 2011 | Thu Sep 26 17:00:00 IDT 2013
935 | GI works for CP85 | Tue Feb 01 08:00:00 IST 2011 | Tue Feb 15 17:00:00 IST 2011
936 | CP85 Preparation for Grouting works | Fri Jul 27 08:00:00 IDT 2012 | Thu Aug 23 17:00:00 IDT 2012
937 | CP85 Fissure Grouting from Tunnel | Fri Aug 24 08:00:00 IDT 2012 | Mon Jan 14 17:00:00 IST 2013
938 | Probing/Drainage (DT) | Tue Jan 15 08:00:00 IST 2013 | Mon Jan 21 17:00:00 IST 2013
939 | Segment Dismantle (DT) | Tue Jan 22 08:00:00 IST 2013 | Mon Jan 28 17:00:00 IST 2013
940 | Cross Passage Excavation & Temp.Support (from DT) | Fri Aug 31 08:00:00 IDT 2012 | Wed Sep 26 17:00:00 IST 2012
941 | Waterproofing (DT) | Thu Sep 27 08:00:00 IST 2012 | Tue Oct 09 17:00:00 IST 2012
942 | Permanent Beam (DT) | Wed Dec 19 08:00:00 IST 2012 | Wed Jan 02 17:00:00 IST 2013
943 | Probing/Drainage | Mon Jul 15 08:00:00 IDT 2013 | Mon Jul 22 17:00:00 IDT 2013
944 | Segment Dismantle | Tue Jul 23 08:00:00 IDT 2013 | Mon Jul 29 17:00:00 IDT 2013
945 | Cross Passage Excavation & Temp.Support (from UT) | Fri Jul 26 08:00:00 IDT 2013 | Sat Aug 03 17:00:00 IDT 2013
946 | Waterproofing (UT) | Sat Aug 24 08:00:00 IDT 2013 | Thu Sep 05 17:00:00 IDT 2013
947 | Permanent Beam (UT) | Fri Sep 06 08:00:00 IDT 2013 | Tue Sep 17 17:00:00 IDT 2013
948 | Permanent Lining | Wed Sep 18 08:00:00 IDT 2013 | Thu Sep 26 17:00:00 IDT 2013
949 | Permanent Slab | Mon Sep 09 08:00:00 IDT 2013 | Mon Sep 16 17:00:00 IDT 2013
950 | CP85 | Tue Jan 15 08:00:00 IST 2013 | Fri Jun 21 17:00:00 IDT 2013
951 | CP86 | Thu Oct 21 08:00:00 IST 2010 | Thu Oct 03 17:00:00 IDT 2013
952 | GI works for CP86 | Thu Oct 21 08:00:00 IST 2010 | Fri Oct 29 17:00:00 IST 2010
953 | Access Works Area 10.1 for Cross Passages CP86 | Tue Jun 21 08:00:00 IDT 2011 | Tue Jun 21 08:00:00 IDT 2011
954 | TTMS & Site Set up | Wed Aug 31 08:00:00 IDT 2011 | Fri Sep 30 17:00:00 IDT 2011
955 | Install Sleeve Pipes | Mon Jan 16 08:00:00 IST 2012 | Fri Feb 24 17:00:00 IST 2012
956 | CP86 Jet Grouting from Surface for Down Track Tunnel | Mon Jan 16 08:00:00 IST 2012 | Tue May 08 17:00:00 IDT 2012
957 | CP86 TAM Grouting from Surface for Down Track Tunnel | Thu Mar 01 08:00:00 IST 2012 | Mon Apr 30 17:00:00 IDT 2012
958 | Discussion with DSD for Sewage Pumping Station | Thu May 03 08:00:00 IDT 2012 | Tue Jul 31 17:00:00 IDT 2012
959 | CP86 Jet Grouting from Surface for Up Track Tunnel | Wed Aug 01 08:00:00 IDT 2012 | Wed Oct 03 17:00:00 IST 2012
960 | CP86 TAM Grouting from Surface for Up Track Tunnel | Thu Oct 04 08:00:00 IST 2012 | Fri Nov 30 17:00:00 IST 2012
961 | Reinstatement | Mon Sep 02 08:00:00 IDT 2013 | Thu Oct 03 17:00:00 IDT 2013
962 | Probing/Drainage (DT) | Sat Dec 15 08:00:00 IST 2012 | Sat Dec 22 17:00:00 IST 2012
963 | Segment Dismantle (DT) | Mon Dec 24 08:00:00 IST 2012 | Wed Jan 02 17:00:00 IST 2013
964 | Cross Passage Excavation & Temp.Support (from DT) | Sat Dec 15 08:00:00 IST 2012 | Sat Dec 29 17:00:00 IST 2012
965 | Waterproofing (DT) | Mon Dec 31 08:00:00 IST 2012 | Thu Jan 10 17:00:00 IST 2013
966 | Permanent Beam (DT) | Fri Jan 11 08:00:00 IST 2013 | Mon Jan 21 17:00:00 IST 2013
967 | Probing/Drainage (UT) | Sat Jun 08 08:00:00 IDT 2013 | Mon Jun 17 17:00:00 IDT 2013
968 | Segment Dismantle (UT) | Tue Jun 18 08:00:00 IDT 2013 | Tue Jun 25 17:00:00 IDT 2013
969 | Cross Passage Excavation & Temp.Support (from UT) | Wed Jun 26 08:00:00 IDT 2013 | Fri Jul 05 17:00:00 IDT 2013
970 | Waterproofing (UT) | Mon Aug 19 08:00:00 IDT 2013 | Thu Aug 29 17:00:00 IDT 2013
971 | Permanent Beam (UT) | Mon Sep 02 08:00:00 IDT 2013 | Thu Sep 12 17:00:00 IDT 2013
972 | Permanent Lining | Sat Sep 14 08:00:00 IDT 2013 | Mon Sep 23 17:00:00 IDT 2013
973 | Permanent Slab | Fri Sep 13 08:00:00 IDT 2013 | Sat Sep 21 17:00:00 IDT 2013
974 | CP86 Jet Grouting from Surface | Mon Jan 16 08:00:00 IST 2012 | Mon Jan 16 08:00:00 IST 2012
975 | CP86 | Mon Jan 07 08:00:00 IST 2013 | Mon Aug 12 17:00:00 IDT 2013
976 | CP87 | Sun Jun 19 17:00:00 IDT 2011 | Thu Sep 26 17:00:00 IDT 2013
977 | GI works for CP87 | Tue Jun 21 08:00:00 IDT 2011 | Mon Jun 27 17:00:00 IDT 2011
978 | Access Works Area 11.12 for Cross Passages CP87 | Sun Jun 19 17:00:00 IDT 2011 | Sun Jun 19 17:00:00 IDT 2011
979 | TTA Implemetation | Wed Aug 31 08:00:00 IDT 2011 | Thu Nov 24 17:00:00 IST 2011
980 | Install Steeve Pipe (for DT area) | Mon Jan 16 08:00:00 IST 2012 | Tue Feb 21 17:00:00 IST 2012
981 | CP87 Jet Grouting from Surface for Down Track Tunnel | Mon Jan 16 08:00:00 IST 2012 | Tue May 08 17:00:00 IDT 2012
982 | Tam Grouting from Surface for Down Track Tunnel | Thu Feb 16 08:00:00 IST 2012 | Wed Apr 18 17:00:00 IDT 2012
983 | Reinstatement & TTMS | Thu Apr 19 08:00:00 IDT 2012 | Thu May 17 17:00:00 IDT 2012
984 | Install Steeve Pipe (for UT area) | Sat May 19 08:00:00 IDT 2012 | Sat Jun 30 17:00:00 IDT 2012
985 | CP87 Jet Grouting from Surface for Up Track Tunnel | Tue Jul 03 08:00:00 IDT 2012 | Fri Aug 31 17:00:00 IDT 2012
986 | Tam Grouting from Surface for Up Track Tunnel | Sat Sep 01 08:00:00 IDT 2012 | Wed Oct 03 17:00:00 IST 2012
987 | Probing/Drainage (DT) | Fri Aug 31 08:00:00 IDT 2012 | Thu Sep 06 17:00:00 IDT 2012
988 | Segment Dismantle (DT) | Fri Sep 07 08:00:00 IDT 2012 | Fri Sep 14 17:00:00 IDT 2012
989 | Cross Passage Excavation & Temp.Support (from DT) | Sat Sep 15 08:00:00 IDT 2012 | Wed Sep 19 17:00:00 IDT 2012
990 | Waterproofing (DT) | Fri Sep 21 08:00:00 IDT 2012 | Wed Oct 03 17:00:00 IST 2012
991 | Permanent Beam (DT) | Thu Oct 04 08:00:00 IST 2012 | Sat Oct 13 17:00:00 IST 2012
992 | Probing/Drainage (UT) | Sat May 25 08:00:00 IDT 2013 | Fri May 31 17:00:00 IDT 2013
993 | Segment Dismantle (UT) | Sat Jun 01 08:00:00 IDT 2013 | Fri Jun 07 17:00:00 IDT 2013
994 | Cross Passage Excavation & Temp.Support (from UT) | Sat Jun 08 08:00:00 IDT 2013 | Wed Jun 19 17:00:00 IDT 2013
995 | Waterproofing (UT) | Fri Jun 21 08:00:00 IDT 2013 | Tue Jul 02 17:00:00 IDT 2013
996 | Permanent Beam (UT) | Wed Jul 03 08:00:00 IDT 2013 | Sat Jul 13 17:00:00 IDT 2013
997 | Permanent Lining | Mon Jul 15 08:00:00 IDT 2013 | Mon Jul 22 17:00:00 IDT 2013
998 | Permanent Slab | Tue Jul 23 08:00:00 IDT 2013 | Mon Jul 29 17:00:00 IDT 2013
999 | CP87 | Fri Aug 31 08:00:00 IDT 2012 | Thu Sep 26 17:00:00 IDT 2013
1000 | CP88 | Tue Feb 01 08:00:00 IST 2011 | Wed Sep 11 17:00:00 IDT 2013
1001 | GI works for CP88 | Tue Feb 01 08:00:00 IST 2011 | Mon Feb 07 17:00:00 IST 2011
1002 | Access Works Area 11.21 for Cross Passages CP88 | Wed Aug 31 08:00:00 IDT 2011 | Wed Aug 31 08:00:00 IDT 2011
1003 | Site Set up & Preparation | Tue Jun 21 08:00:00 IDT 2011 | Tue Aug 02 17:00:00 IDT 2011
1004 | CP88 Jet Grouting from Surface | Tue Aug 09 08:00:00 IDT 2011 | Sat Aug 20 17:00:00 IDT 2011
1005 | Suspension of Grouting Works | Sun Jun 19 08:00:00 IDT 2011 | Sun Jun 19 08:00:00 IDT 2011
1006 | Suspension Period for CP88 Jet Grouting Works | Sun Jun 19 08:00:00 IDT 2011 | Wed Jun 22 17:00:00 IDT 2011
1007 | Suspension Lifting | Tue Jun 21 08:00:00 IDT 2011 | Tue Jun 21 08:00:00 IDT 2011
1008 | Re-mobilization | Thu Aug 18 08:00:00 IDT 2011 | Sat Aug 20 17:00:00 IDT 2011
1009 | CP88 Jet Grouting from Surface (Remaining) | Thu Aug 18 08:00:00 IDT 2011 | Mon Dec 19 17:00:00 IST 2011
1010 | Probing/Drainage (DT) | Fri Aug 31 08:00:00 IDT 2012 | Thu Sep 06 17:00:00 IDT 2012
1011 | Segment Dismantle (DT) | Fri Sep 07 08:00:00 IDT 2012 | Fri Sep 14 17:00:00 IDT 2012
1012 | Cross Passage Excavation & Temp.Support (from DT) | Sat Sep 15 08:00:00 IDT 2012 | Mon Sep 17 17:00:00 IDT 2012
1013 | Waterproofing (DT) | Tue Sep 18 08:00:00 IDT 2012 | Fri Sep 28 17:00:00 IST 2012
1014 | Permanent Beam (DT) | Sat Sep 29 08:00:00 IST 2012 | Thu Oct 11 17:00:00 IST 2012
1015 | Probing/Drainage (UT) | Thu May 23 08:00:00 IDT 2013 | Wed May 29 17:00:00 IDT 2013
1016 | Segment Dismantle (UT) | Thu May 30 08:00:00 IDT 2013 | Wed Jun 05 17:00:00 IDT 2013
1017 | Cross Passage Excavation & Temp.Support (from UT) | Thu Jun 06 08:00:00 IDT 2013 | Mon Jun 17 17:00:00 IDT 2013
1018 | Waterproofing (UT) | Tue Jun 18 08:00:00 IDT 2013 | Fri Jun 28 17:00:00 IDT 2013
1019 | Permanent Beam (UT) | Sat Jun 29 08:00:00 IDT 2013 | Thu Jul 11 17:00:00 IDT 2013
1020 | Permanent Lining | Fri Jul 12 08:00:00 IDT 2013 | Thu Jul 18 17:00:00 IDT 2013
1021 | Permanent Slab | Sat Jul 20 08:00:00 IDT 2013 | Fri Jul 26 17:00:00 IDT 2013
1022 | CP88 | Fri Aug 31 08:00:00 IDT 2012 | Wed Sep 11 17:00:00 IDT 2013
1023 | CP89 | Tue Feb 01 08:00:00 IST 2011 | Tue Feb 18 17:00:00 IST 2014
1024 | GI works for CP89 | Tue Feb 01 08:00:00 IST 2011 | Sat Feb 12 17:00:00 IST 2011
1025 | Access Works Area 11.27 for Cross Passages CP89 | Sat May 28 17:00:00 IDT 2011 | Sat May 28 17:00:00 IDT 2011
1026 | Setup & Install Sleeve pipes | Wed Aug 31 08:00:00 IDT 2011 | Fri Sep 30 17:00:00 IDT 2011
1027 | Jet Grouting from Surface (DT) | Wed Aug 31 08:00:00 IDT 2011 | Tue Mar 13 17:00:00 IST 2012
1028 | Jet Grouting from Surface (UT) | Thu Mar 15 08:00:00 IST 2012 | Mon Apr 30 17:00:00 IDT 2012
1029 | Probing/Drainage (DT) | Fri Aug 31 08:00:00 IDT 2012 | Thu Sep 06 17:00:00 IDT 2012
1030 | Tunnel Frame Support | Fri Sep 07 08:00:00 IDT 2012 | Fri Sep 14 17:00:00 IDT 2012
1031 | Segment Dismantle (DT) | Sat Sep 15 08:00:00 IDT 2012 | Sat Sep 22 17:00:00 IDT 2012
1032 | Cross Passage Excavation & Temp.Support (from DT) | Mon Sep 24 08:00:00 IST 2012 | Tue Sep 25 17:00:00 IST 2012
1033 | Waterproofing (DT) | Wed Sep 26 08:00:00 IST 2012 | Mon Oct 08 17:00:00 IST 2012
1034 | Permanent Beam (DT) | Tue Oct 09 08:00:00 IST 2012 | Thu Oct 18 17:00:00 IST 2012
1035 | Probing/Drainage (from DT) | Tue Jan 07 08:00:00 IST 2014 | Mon Jan 13 17:00:00 IST 2014
1036 | Cross Passage Excavation & Temp.Support (from DT) | Sat Jan 11 08:00:00 IST 2014 | Mon Jan 20 17:00:00 IST 2014
1037 | Segment Dismantle (UT) | Wed Jan 08 08:00:00 IST 2014 | Tue Jan 14 17:00:00 IST 2014
1038 | Waterproofing (UT) | Tue Feb 04 08:00:00 IST 2014 | Thu Feb 13 17:00:00 IST 2014
1039 | Permanent Beam (UT) | Sat Feb 08 08:00:00 IST 2014 | Tue Feb 18 17:00:00 IST 2014
1040 | Permanent Lining | Tue Feb 11 08:00:00 IST 2014 | Mon Feb 17 17:00:00 IST 2014
1041 | Permanent Slab | Fri Feb 07 08:00:00 IST 2014 | Thu Feb 13 17:00:00 IST 2014
1042 | CP89 | Fri Sep 07 08:00:00 IDT 2012 | Sat Oct 26 17:00:00 IDT 2013
1043 | CP90 | Tue Feb 01 08:00:00 IST 2011 | Thu May 08 17:00:00 IDT 2014
1044 | GI works for CP90 | Tue Feb 01 08:00:00 IST 2011 | Wed Feb 09 17:00:00 IST 2011
1045 | Access Works Area 11.21 for Cross Passages CP90 | Sun Jun 19 17:00:00 IDT 2011 | Sun Jun 19 17:00:00 IDT 2011
1046 | TTA Implementation | Mon Jan 16 08:00:00 IST 2012 | Wed Feb 15 17:00:00 IST 2012
1047 | Installl Sleeve Pipes | Mon Jan 16 08:00:00 IST 2012 | Thu Feb 16 17:00:00 IST 2012
1048 | CP90 Jet Grouting from Surface (DT) | Mon Jan 16 08:00:00 IST 2012 | Fri Jun 15 17:00:00 IDT 2012
1049 | CP90 Jet Grouting from Surface (UT) | Wed May 02 08:00:00 IDT 2012 | Sat Sep 01 17:00:00 IDT 2012
1050 | Probing/Drainage (DT) | Fri Aug 31 08:00:00 IDT 2012 | Thu Sep 06 17:00:00 IDT 2012
1051 | Segment Dismantle (DT) | Fri Sep 07 08:00:00 IDT 2012 | Fri Sep 14 17:00:00 IDT 2012
1052 | Cross Passage Excavation & Temp.Support (from DT) | Sat Sep 15 08:00:00 IDT 2012 | Sat Sep 22 17:00:00 IDT 2012
1053 | Waterproofing (DT) | Mon Sep 24 08:00:00 IST 2012 | Fri Oct 05 17:00:00 IST 2012
1054 | Permanent Beam (DT) | Sat Oct 06 08:00:00 IST 2012 | Tue Oct 16 17:00:00 IST 2012
1055 | Probing/Drainage (UT) | Wed Apr 09 08:00:00 IDT 2014 | Wed Apr 16 17:00:00 IDT 2014
1056 | Cross Passage Excavation & Temp.Support (UT) | Sat Apr 12 08:00:00 IDT 2014 | Thu Apr 24 17:00:00 IDT 2014
1057 | Segment Dismantle (UT) | Fri Apr 11 08:00:00 IDT 2014 | Sat Apr 19 17:00:00 IDT 2014
1058 | Waterproofing (UT) | Tue Apr 22 08:00:00 IDT 2014 | Wed Apr 30 17:00:00 IDT 2014
1059 | Permanent Beam (UT) | Mon Apr 28 08:00:00 IDT 2014 | Thu May 08 17:00:00 IDT 2014
1060 | Permanent Lining | Wed Apr 30 08:00:00 IDT 2014 | Thu May 08 17:00:00 IDT 2014
1061 | Permanent Slab | Thu Apr 24 08:00:00 IDT 2014 | Wed Apr 30 17:00:00 IDT 2014
1062 | CP90 | Fri Aug 31 08:00:00 IDT 2012 | Sat Dec 28 17:00:00 IST 2013
1063 | CP91 | Tue Feb 01 08:00:00 IST 2011 | Thu May 22 17:00:00 IDT 2014
1064 | GI works for CP91 | Tue Feb 01 08:00:00 IST 2011 | Sat Feb 12 17:00:00 IST 2011
1065 | Access Works Area 11.21 for Cross Passages CP91 | Sun Jun 19 17:00:00 IDT 2011 | Sun Jun 19 17:00:00 IDT 2011
1066 | TTMS & Site Set up | Wed Aug 31 08:00:00 IDT 2011 | Mon Oct 17 17:00:00 IST 2011
1067 | Install Sleeve Pipes (DT) | Mon Jan 16 08:00:00 IST 2012 | Wed Feb 01 17:00:00 IST 2012
1068 | Jet Grouting from Surface for Down Track Tunnel | Mon Jan 16 08:00:00 IST 2012 | Tue Jun 05 17:00:00 IDT 2012
1069 | TTMS Rearrangement | Mon Apr 16 08:00:00 IDT 2012 | Mon May 14 17:00:00 IDT 2012
1070 | Install Sleeve Pipes (UT) | Tue May 15 08:00:00 IDT 2012 | Wed Jun 13 17:00:00 IDT 2012
1071 | Jet Grouting from Surface for Up Track Tunnel | Thu Jun 14 08:00:00 IDT 2012 | Fri Sep 14 17:00:00 IDT 2012
1072 | Probing/Drainage (DT) | Wed Oct 31 08:00:00 IST 2012 | Tue Nov 06 17:00:00 IST 2012
1073 | Tunnel Frame Support | Fri Nov 30 08:00:00 IST 2012 | Thu Dec 06 17:00:00 IST 2012
1074 | Segment Dismantle (DT) | Fri Dec 07 08:00:00 IST 2012 | Thu Dec 13 17:00:00 IST 2012
1075 | Cross Passage Excavation & Temp.Support (from DT) | Fri Dec 14 08:00:00 IST 2012 | Thu Dec 27 17:00:00 IST 2012
1076 | Waterproofing (DT) | Sat Dec 15 08:00:00 IST 2012 | Fri Dec 28 17:00:00 IST 2012
1077 | Permanent Beam (DT) | Fri Feb 01 08:00:00 IST 2013 | Sat Feb 16 17:00:00 IST 2013
1078 | Probing/Drainage (from DT) | Fri Apr 25 08:00:00 IDT 2014 | Fri May 02 17:00:00 IDT 2014
1079 | Segment Dismantle (UT) | Fri Apr 25 08:00:00 IDT 2014 | Fri May 02 17:00:00 IDT 2014
1080 | Waterproofing (UT) | Mon May 05 08:00:00 IDT 2014 | Fri May 16 17:00:00 IDT 2014
1081 | Permanent Beam (UT) | Mon May 12 08:00:00 IDT 2014 | Thu May 22 17:00:00 IDT 2014
1082 | Permanent Lining | Wed May 14 08:00:00 IDT 2014 | Wed May 21 17:00:00 IDT 2014
1083 | Permanent Slab | Thu May 08 08:00:00 IDT 2014 | Thu May 15 17:00:00 IDT 2014
1084 | CP91 Grouting from Surface | Mon Jan 16 08:00:00 IST 2012 | Wed Aug 01 17:00:00 IDT 2012
1085 | CP91 | Wed Oct 31 08:00:00 IST 2012 | Thu Oct 17 17:00:00 IDT 2013
1086 | CP92 | Sun Jun 19 17:00:00 IDT 2011 | Sat Jun 07 17:00:00 IDT 2014
1087 | GI works for CP92 | Tue Jun 21 08:00:00 IDT 2011 | Mon Jun 27 17:00:00 IDT 2011
1088 | Access Works Area 11.21 for Cross Passages CP92 | Sun Jun 19 17:00:00 IDT 2011 | Sun Jun 19 17:00:00 IDT 2011
1089 | TTMS & Site Set up | Tue Jun 21 08:00:00 IDT 2011 | Wed Aug 17 17:00:00 IDT 2011
1090 | Install Sleeve Pipes | Mon Jan 16 08:00:00 IST 2012 | Wed Feb 01 17:00:00 IST 2012
1091 | Jet Grouting from Surface for Up Track Tunnel | Mon Jan 16 08:00:00 IST 2012 | Tue Mar 27 17:00:00 IST 2012
1092 | TTMS Rearrangement | Mon Jan 16 08:00:00 IST 2012 | Thu Feb 16 17:00:00 IST 2012
1093 | Insall Sleeve Pipes | Sat Feb 04 08:00:00 IST 2012 | Fri Feb 17 17:00:00 IST 2012
1094 | Jet Grouting from Surface for Down Track Tunnel | Sat Feb 18 08:00:00 IST 2012 | Fri Jun 15 17:00:00 IDT 2012
1095 | Road Reinstatment | Sat Jun 16 08:00:00 IDT 2012 | Wed Jul 18 17:00:00 IDT 2012
1096 | Probing/Drainage (DT) | Wed Oct 31 08:00:00 IST 2012 | Tue Nov 06 17:00:00 IST 2012
1097 | Segment Dismantle (DT) | Wed Nov 07 08:00:00 IST 2012 | Tue Nov 13 17:00:00 IST 2012
1098 | Cross Passage Excavation & Temp.Support (from DT) | Fri Nov 30 08:00:00 IST 2012 | Thu Dec 06 17:00:00 IST 2012
1099 | Waterproofing (DT) | Sat Dec 15 08:00:00 IST 2012 | Fri Dec 28 17:00:00 IST 2012
1100 | Permanent Beam (DT) | Sat Dec 15 08:00:00 IST 2012 | Fri Dec 28 17:00:00 IST 2012
1101 | Probing/Drainage (from DT) | Sat May 10 08:00:00 IDT 2014 | Fri May 16 17:00:00 IDT 2014
1102 | Cross Passage Excavation & Temp.Support (from DT) | Mon May 12 08:00:00 IDT 2014 | Wed May 21 17:00:00 IDT 2014
1103 | Segment Dismantle (UT) | Sat May 10 08:00:00 IDT 2014 | Thu May 15 17:00:00 IDT 2014
1104 | Waterproofing (UT) | Wed May 21 08:00:00 IDT 2014 | Thu May 29 17:00:00 IDT 2014
1105 | Permanent Beam (UT) | Thu May 29 08:00:00 IDT 2014 | Sat Jun 07 17:00:00 IDT 2014
1106 | Permanent Lining | Sat May 31 08:00:00 IDT 2014 | Sat Jun 07 17:00:00 IDT 2014
1107 | Permanent Slab | Mon May 26 08:00:00 IDT 2014 | Sat May 31 17:00:00 IDT 2014
1108 | CP92 | Wed Oct 31 08:00:00 IST 2012 | Mon Nov 04 17:00:00 IST 2013
1109 | CP93 | Tue Feb 01 08:00:00 IST 2011 | Sat Jun 21 17:00:00 IDT 2014
1110 | GI works for CP93 | Tue Feb 01 08:00:00 IST 2011 | Thu Feb 10 17:00:00 IST 2011
1111 | Access Works Area 11.15 for Cross Passages CP93 | Wed Aug 31 08:00:00 IDT 2011 | Wed Aug 31 08:00:00 IDT 2011
1112 | TTMS & Site Set up | Wed Feb 01 08:00:00 IST 2012 | Fri Mar 02 17:00:00 IST 2012
1113 | Install Sleeve Pipes | Mon Jan 16 08:00:00 IST 2012 | Mon Feb 13 17:00:00 IST 2012
1114 | Jet Grouting from Surface | Mon Jan 16 08:00:00 IST 2012 | Thu Jul 12 17:00:00 IDT 2012
1115 | Probing/Drainage (DT) | Tue Nov 27 08:00:00 IST 2012 | Mon Dec 03 17:00:00 IST 2012
1116 | Segment Dismantle (DT) | Tue Dec 04 08:00:00 IST 2012 | Mon Dec 10 17:00:00 IST 2012
1117 | Cross Passage Excavation & Temp.Support (from DT) | Tue Dec 11 08:00:00 IST 2012 | Tue Dec 18 17:00:00 IST 2012
1118 | Waterproofing (DT) | Sat Dec 15 08:00:00 IST 2012 | Fri Dec 28 17:00:00 IST 2012
1119 | Permanent Beam (DT) | Sat Dec 29 08:00:00 IST 2012 | Wed Jan 09 17:00:00 IST 2013
1120 | Probing/Drainage (from UT) | Wed May 21 08:00:00 IDT 2014 | Tue May 27 17:00:00 IDT 2014
1121 | Cross Passage Excavation & Temp.Support (from DT) | Sat May 24 08:00:00 IDT 2014 | Tue Jun 03 17:00:00 IDT 2014
1122 | Segment Dismantle (UT) | Fri May 23 08:00:00 IDT 2014 | Wed May 28 17:00:00 IDT 2014
1123 | Waterproofing (UT) | Sat May 31 08:00:00 IDT 2014 | Mon Jun 09 17:00:00 IDT 2014
1124 | Permanent Beam (UT) | Thu Jun 12 08:00:00 IDT 2014 | Sat Jun 21 17:00:00 IDT 2014
1125 | Permanent Lining | Sat Jun 14 08:00:00 IDT 2014 | Thu Jun 19 17:00:00 IDT 2014
1126 | Permanent Slab | Mon Jun 09 08:00:00 IDT 2014 | Sat Jun 14 17:00:00 IDT 2014
1127 | CP93 | Tue Nov 27 08:00:00 IST 2012 | Mon Nov 18 17:00:00 IST 2013
1128 | CP94 | Tue Feb 01 08:00:00 IST 2011 | Sat Aug 09 17:00:00 IDT 2014
1129 | GI works for CP94 | Tue Feb 01 08:00:00 IST 2011 | Thu Feb 17 17:00:00 IST 2011
1130 | Access for Cross Passages CP94 | Mon Sep 03 17:00:00 IDT 2012 | Mon Sep 03 17:00:00 IDT 2012
1131 | Preparation for Grouting | Wed Oct 03 08:00:00 IST 2012 | Wed Oct 31 17:00:00 IST 2012
1132 | CP94 Fissure Grouting from Tunnel | Thu Nov 01 08:00:00 IST 2012 | Mon Dec 31 17:00:00 IST 2012
1133 | Probing/Drainage (DT) | Mon Dec 02 08:00:00 IST 2013 | Mon Dec 30 17:00:00 IST 2013
1134 | Segment Dismantle (DT) | Tue Dec 04 08:00:00 IST 2012 | Mon Dec 10 17:00:00 IST 2012
1135 | Cross Passage Excavation/ Temp.Support (from DT) | Tue Dec 11 08:00:00 IST 2012 | Tue Dec 18 17:00:00 IST 2012
1136 | Waterproofing (DT) | Tue Jul 02 08:00:00 IDT 2013 | Fri Jul 12 17:00:00 IDT 2013
1137 | Permanent Beam (DT) | Sat Jul 13 08:00:00 IDT 2013 | Wed Jul 24 17:00:00 IDT 2013
1138 | Probing/Drainage (from DT) | Mon Jul 14 08:00:00 IDT 2014 | Mon Jul 21 17:00:00 IDT 2014
1139 | Cross Passage Excavation /Temp.Support (from DT) | Sat Jul 19 08:00:00 IDT 2014 | Mon Jul 28 17:00:00 IDT 2014
1140 | Segment Dismantle (UT) | Mon Jul 14 08:00:00 IDT 2014 | Sat Jul 19 17:00:00 IDT 2014
1141 | Waterproofing (UT) | Fri Jul 25 08:00:00 IDT 2014 | Sat Aug 02 17:00:00 IDT 2014
1142 | Permanent Beam (UT) | Thu Jul 31 08:00:00 IDT 2014 | Sat Aug 09 17:00:00 IDT 2014
1143 | Permanent Lining | Sat Aug 02 08:00:00 IDT 2014 | Thu Aug 07 17:00:00 IDT 2014
1144 | Permanent Slab | Wed Jul 30 08:00:00 IDT 2014 | Mon Aug 04 17:00:00 IDT 2014
1145 | CP94 | Mon Dec 31 08:00:00 IST 2012 | Mon Dec 31 08:00:00 IST 2012
1146 | CP95 & Pump Sump | Tue Feb 01 08:00:00 IST 2011 | Mon Sep 08 17:00:00 IDT 2014
1147 | GI works for CP95 & Sump | Tue Feb 01 08:00:00 IST 2011 | Thu Feb 17 17:00:00 IST 2011
1148 | Preparation for Grouting | Sat Nov 24 08:00:00 IST 2012 | Mon Dec 24 17:00:00 IST 2012
1149 | CP95 Fissure Grouting from Tunnel | Sat Dec 08 08:00:00 IST 2012 | Mon May 27 17:00:00 IDT 2013
1150 | Probing/Drainage (DT) | Mon Dec 24 08:00:00 IST 2012 | Wed Jan 02 17:00:00 IST 2013
1151 | Segment Dismantle (DT) | Mon Dec 31 08:00:00 IST 2012 | Thu Feb 14 17:00:00 IST 2013
1152 | Cross Passage & Sump pit Excavation/ Temp.Support (from DT) | Thu Feb 14 08:00:00 IST 2013 | Thu Feb 21 17:00:00 IST 2013
1153 | Waterproofing (DT) | Mon Sep 02 08:00:00 IDT 2013 | Thu Sep 12 17:00:00 IDT 2013
1154 | Permanent Beam (DT) | Fri Sep 13 08:00:00 IDT 2013 | Wed Sep 25 17:00:00 IDT 2013
1155 | Cross Passage Excavation/Temp.Support U/T (from DT) | Mon Aug 18 08:00:00 IDT 2014 | Wed Aug 27 17:00:00 IDT 2014
1156 | Segment Dismantle (UT) | Tue Aug 12 08:00:00 IDT 2014 | Mon Aug 18 17:00:00 IDT 2014
1157 | Waterproofing (UT) | Tue Aug 26 08:00:00 IDT 2014 | Wed Sep 03 17:00:00 IDT 2014
1158 | Sump pit Concreting | Thu Sep 05 08:00:00 IDT 2013 | Fri Oct 04 17:00:00 IDT 2013
1159 | Permanet Beam, Lining& Slab (UT) | Thu Aug 28 08:00:00 IDT 2014 | Mon Sep 08 17:00:00 IDT 2014
1160 | CP96 | Tue Feb 01 08:00:00 IST 2011 | Tue Sep 30 17:00:00 IDT 2014
1161 | Segment Dismantle (DT) | Tue May 14 08:00:00 IDT 2013 | Wed May 22 17:00:00 IDT 2013
1162 | Cross Passage Excavation & Temp.Support (DT) | Tue May 21 08:00:00 IDT 2013 | Mon May 27 17:00:00 IDT 2013
1163 | Waterproofing (DT) | Tue Sep 24 08:00:00 IDT 2013 | Wed Oct 02 17:00:00 IDT 2013
1164 | Permanent Beam (DT) | Fri Sep 27 08:00:00 IDT 2013 | Mon Oct 07 17:00:00 IDT 2013
1165 | Permanent Lining (DT) | Fri Sep 27 08:00:00 IDT 2013 | Thu Oct 03 17:00:00 IDT 2013
1166 | Permanent Slab (DT) | Thu Sep 26 08:00:00 IDT 2013 | Wed Oct 02 17:00:00 IDT 2013
1167 | GI works for CP96 | Tue Feb 01 08:00:00 IST 2011 | Tue Feb 15 17:00:00 IST 2011
1168 | Preparation works for Grouting | Mon Feb 18 08:00:00 IST 2013 | Tue Mar 19 17:00:00 IST 2013
1169 | CP96 Fissure Grouting from Tunnel | Fri Mar 01 08:00:00 IST 2013 | Fri Jun 07 17:00:00 IDT 2013
1170 | Probing/Drainage (from UT) | Wed Sep 03 08:00:00 IDT 2014 | Thu Sep 11 17:00:00 IDT 2014
1171 | Segment Dismantle (UT) | Thu Sep 04 08:00:00 IDT 2014 | Fri Sep 12 17:00:00 IDT 2014
1172 | Cross Passage Excavation & Temp.Support (from UT) | Thu Sep 11 08:00:00 IDT 2014 | Wed Sep 17 17:00:00 IDT 2014
1173 | Waterproofing | Wed Sep 17 08:00:00 IDT 2014 | Thu Sep 25 17:00:00 IDT 2014
1174 | Permanent Beam | Mon Sep 22 08:00:00 IDT 2014 | Tue Sep 30 17:00:00 IDT 2014
1175 | Permanent Lining | Wed Sep 24 08:00:00 IDT 2014 | Mon Sep 29 17:00:00 IDT 2014
1176 | Permanent Slab | Sat Sep 20 08:00:00 IDT 2014 | Thu Sep 25 17:00:00 IDT 2014
1177 | Probing/Drainage (DT) | Sat May 11 08:00:00 IDT 2013 | Sat May 18 17:00:00 IDT 2013
1178 | CP97 | Tue Feb 01 08:00:00 IST 2011 | Thu Dec 18 17:00:00 IST 2014
1179 | CP97 Jet Grouting from Surface | Mon Jan 16 08:00:00 IST 2012 | Wed Oct 31 17:00:00 IST 2012
1180 | GI works for CP97 | Tue Feb 01 08:00:00 IST 2011 | Thu Feb 10 17:00:00 IST 2011
1181 | Access Works Area 12.1 for Cross Passages CP97 | Sun Jan 15 08:00:00 IST 2012 | Sun Jan 15 08:00:00 IST 2012
1182 | TTMS (Stage 1) | Mon Jan 16 08:00:00 IST 2012 | Wed Feb 15 17:00:00 IST 2012
1183 | Install Sleeve Pipes | Mon Jan 16 08:00:00 IST 2012 | Wed Feb 15 17:00:00 IST 2012
1184 | Jet Grouting from Surface for Down Track Tunnel | Thu Feb 16 08:00:00 IST 2012 | Thu May 31 17:00:00 IDT 2012
1185 | TTMS (Stage 2) Reinstate TTMS for Stage 4 | Fri Jun 01 08:00:00 IDT 2012 | Tue Jul 17 17:00:00 IDT 2012
1186 | Install Sleeve Pipes | Fri Jun 01 08:00:00 IDT 2012 | Thu Jun 14 17:00:00 IDT 2012
1187 | Jet Grouting from Surface for Up Track Tunnel | Sat Sep 21 08:00:00 IDT 2013 | Mon Dec 16 17:00:00 IST 2013
1188 | Probing/Drainage (UT) (after TBM removal) | Mon Nov 17 08:00:00 IST 2014 | Wed Nov 19 17:00:00 IST 2014
1189 | Segment Dismantle (UT) | Wed Nov 19 08:00:00 IST 2014 | Fri Nov 21 17:00:00 IST 2014
1190 | Cross Passage Excavation & Temp.Support (from UT) | Thu Nov 20 08:00:00 IST 2014 | Tue Nov 25 17:00:00 IST 2014
1191 | Waterproofing | Tue Dec 02 08:00:00 IST 2014 | Thu Dec 04 17:00:00 IST 2014
1192 | Permanent Beam | Thu Dec 11 08:00:00 IST 2014 | Sat Dec 13 17:00:00 IST 2014
1193 | Permanent Lining | Tue Dec 16 08:00:00 IST 2014 | Thu Dec 18 17:00:00 IST 2014
1194 | Permanent Slab | Mon Dec 08 08:00:00 IST 2014 | Wed Dec 10 17:00:00 IST 2014
1195 | Additional Jet Grout of CP97 U/T | Tue Jan 21 08:00:00 IST 2014 | Fri Aug 01 17:00:00 IDT 2014
1196 | Mobilization | Tue Jan 21 08:00:00 IST 2014 | Tue Jan 21 17:00:00 IST 2014
1197 | Steel Sleeve pipe installation | Tue Jan 21 08:00:00 IST 2014 | Thu Feb 06 17:00:00 IST 2014
1198 | Mobilization of Pre-drilling rig and mixing plant | Fri Feb 07 08:00:00 IST 2014 | Mon Feb 10 17:00:00 IST 2014
1199 | Pre-drilling (2 Rigs) | Tue Feb 11 08:00:00 IST 2014 | Wed Apr 30 17:00:00 IDT 2014
1200 | Trial pit for re-location of air release hole P2 | Mon May 12 08:00:00 IDT 2014 | Mon May 12 17:00:00 IDT 2014
1201 | Pre-drilling for air release hole P2 | Tue May 13 08:00:00 IDT 2014 | Wed May 14 17:00:00 IDT 2014
1202 | Demobilization of Pre-drilling plant | Thu May 15 08:00:00 IDT 2014 | Fri May 16 17:00:00 IDT 2014
1203 | Mobilization and Set up of Jet grouting plant | Sat May 17 08:00:00 IDT 2014 | Sat May 24 17:00:00 IDT 2014
1204 | Jet grouting (56 columns) | Wed May 21 08:00:00 IDT 2014 | Tue Jul 08 17:00:00 IDT 2014
1205 | Demobilization of Jet grout plant | Tue Jun 24 08:00:00 IDT 2014 | Mon Jun 30 17:00:00 IDT 2014
1206 | Mobilization and drilling rig for Proof Coring | Thu Jul 31 08:00:00 IDT 2014 | Fri Aug 01 17:00:00 IDT 2014
1207 | Proof Coring | Mon Jul 07 08:00:00 IDT 2014 | Mon Jul 14 17:00:00 IDT 2014
1208 | Demobilization of drilling rig | Mon Jul 28 08:00:00 IDT 2014 | Tue Jul 29 17:00:00 IDT 2014
1209 | CP98 | Tue Feb 01 08:00:00 IST 2011 | Fri Dec 19 17:00:00 IST 2014
1210 | Probing/Drainage (DT) | Sat May 11 08:00:00 IDT 2013 | Sat May 18 17:00:00 IDT 2013
1211 | Segment Dismantle (DT) | Tue May 14 08:00:00 IDT 2013 | Wed May 22 17:00:00 IDT 2013
1212 | Cross Passage Excavation & Temp.Support (DT) | Tue May 21 08:00:00 IDT 2013 | Mon May 27 17:00:00 IDT 2013
1213 | Waterproofing (DT) | Tue Sep 24 08:00:00 IDT 2013 | Wed Oct 02 17:00:00 IDT 2013
1214 | Permanent Slab (DT) | Thu Sep 26 08:00:00 IDT 2013 | Wed Oct 02 17:00:00 IDT 2013
1215 | Permanent Beam (DT) | Fri Sep 27 08:00:00 IDT 2013 | Mon Oct 07 17:00:00 IDT 2013
1216 | Permanent Lining (DT) | Fri Sep 27 08:00:00 IDT 2013 | Thu Oct 03 17:00:00 IDT 2013
1217 | GI works for CP98 | Tue Feb 01 08:00:00 IST 2011 | Mon Feb 14 17:00:00 IST 2011
1218 | Access Works Area 12.1 for Cross Passages CP98 | Sun Jan 15 08:00:00 IST 2012 | Sun Jan 15 08:00:00 IST 2012
1219 | TTA Implementation & Site Setup | Mon Jan 16 08:00:00 IST 2012 | Sat Mar 10 17:00:00 IST 2012
1220 | Install Sleeve Pipe | Wed Oct 03 08:00:00 IST 2012 | Wed Oct 31 17:00:00 IST 2012
1221 | CP98 Jet Grouting from Surface | Thu Nov 01 08:00:00 IST 2012 | Wed Feb 27 17:00:00 IST 2013
1222 | Road Reinstatement | Mon Dec 17 08:00:00 IST 2012 | Fri Jan 25 17:00:00 IST 2013
1223 | Probing/Drainage (UT) (after TBM removal) | Thu Nov 20 08:00:00 IST 2014 | Sat Nov 22 17:00:00 IST 2014
1224 | Segment Dismantle (UT) | Sat Nov 22 08:00:00 IST 2014 | Tue Nov 25 17:00:00 IST 2014
1225 | Cross Passage Excavation & Temp.Support (from UT) | Sat Nov 29 08:00:00 IST 2014 | Thu Dec 04 17:00:00 IST 2014
1226 | Segment Dismantle (DT) | Sat Nov 22 08:00:00 IST 2014 | Tue Nov 25 17:00:00 IST 2014
1227 | Waterproofing | Tue Dec 02 08:00:00 IST 2014 | Thu Dec 04 17:00:00 IST 2014
1228 | Permanent Beam | Mon Dec 15 08:00:00 IST 2014 | Wed Dec 17 17:00:00 IST 2014
1229 | Permanent Lining | Wed Dec 17 08:00:00 IST 2014 | Fri Dec 19 17:00:00 IST 2014
1230 | Permanent Slab | Wed Dec 10 08:00:00 IST 2014 | Fri Dec 12 17:00:00 IST 2014
1231 | Tunnel Lining Design/Submission/Approval | Mon Jan 31 08:00:00 IST 2011 | Wed Nov 30 17:00:00 IST 2011
1232 | Design | Mon Jan 31 08:00:00 IST 2011 | Wed Nov 30 17:00:00 IST 2011
1233 | AIP Submission Preparation - Tunnel Lining | Mon Jan 31 08:00:00 IST 2011 | Mon Feb 21 17:00:00 IST 2011
1234 | AIP Submission to MTR | Mon Feb 21 17:00:00 IST 2011 | Mon Feb 21 17:00:00 IST 2011
1235 | AIP Comment by MTR | Tue Feb 22 08:00:00 IST 2011 | Sun Mar 06 17:00:00 IST 2011
1236 | AIP ReSubmission Preparation - Tunnel Lining | Sat Mar 19 08:00:00 IST 2011 | Thu Mar 31 17:00:00 IST 2011
1237 | AIP ReSubmission to MTR | Mon Apr 04 17:00:00 IDT 2011 | Mon Apr 04 17:00:00 IDT 2011
1238 | AIP Approval by MTR | Tue Apr 05 08:00:00 IDT 2011 | Fri Apr 29 17:00:00 IDT 2011
1239 | DD Submission Preparation - Tunnel Lining | Tue Apr 26 08:00:00 IDT 2011 | Sat Jun 04 17:00:00 IDT 2011
1240 | DD Submission to MTR (RDO/GEO consultation) | Fri May 20 17:00:00 IDT 2011 | Fri May 20 17:00:00 IDT 2011
1241 | DD Comment by MTR (RDO/GEO consultation) | Sat May 21 08:00:00 IDT 2011 | Wed Jun 15 17:00:00 IDT 2011
1242 | DD ReSubmission Preparation - Tunnel Lining | Tue Jun 07 08:00:00 IDT 2011 | Mon Jun 20 17:00:00 IDT 2011
1243 | DD ReSubmission to MTR (RDO/GEO consultation) | Mon Jun 20 17:00:00 IDT 2011 | Mon Jun 20 17:00:00 IDT 2011
1244 | DD Approval by MTR (RDO/GEO consultation) | Tue Jun 21 08:00:00 IDT 2011 | Wed Nov 30 17:00:00 IST 2011
1245 | Tunnel Segment Fabrication | Wed May 18 08:00:00 IDT 2011 | Tue Jun 24 17:00:00 IDT 2014
1246 | Segment mould & Tunnel Segment Fabrication | Wed May 18 08:00:00 IDT 2011 | Fri Jun 28 17:00:00 IDT 2013
1247 | Fabrication | Wed May 18 08:00:00 IDT 2011 | Tue Jun 24 17:00:00 IDT 2014
1248 | Placing Order of Segment Moulds | Tue Jul 19 08:00:00 IDT 2011 | Tue Jul 19 08:00:00 IDT 2011
1249 | Segment Mould Fabrication | Tue Jul 19 08:00:00 IDT 2011 | Thu Mar 22 17:00:00 IST 2012
1250 | Fabrication of Precast Segments - 1st batch | Wed Aug 10 08:00:00 IDT 2011 | Wed Dec 28 17:00:00 IST 2011
1251 | Fabrication of Precast Segments - 2nd batch | Mon Jan 16 08:00:00 IST 2012 | Sat Sep 22 17:00:00 IDT 2012
1252 | 30% Precast Segments (Mil.C5) | Thu Dec 20 17:00:00 IST 2012 | Thu Dec 20 17:00:00 IST 2012
1253 | Fabrication of Precast Segments - 3rd batch | Fri Dec 21 08:00:00 IST 2012 | Fri Apr 19 17:00:00 IDT 2013
1254 | 45% Precast Segments (Mil.C6) | Fri Apr 19 17:00:00 IDT 2013 | Fri Apr 19 17:00:00 IDT 2013
1255 | Fabrication of Precast Segments (Remaining) | Sat Apr 20 08:00:00 IDT 2013 | Tue Jun 24 17:00:00 IDT 2014
1256 | Segment mould & Tunnel Segment Fabrication | Wed May 18 08:00:00 IDT 2011 | Sat Mar 01 17:00:00 IST 2014
1257 | Tunnelling Works
1258 | Submission | Mon Feb 02 08:00:00 IST 2015 | Thu Apr 30 17:00:00 IDT 2015
1259 | Completion | Mon Feb 02 08:00:00 IST 2015 | Thu Apr 30 17:00:00 IDT 2015
1260 | Prepare & Submit Draft As-built Drawings | Mon Feb 02 08:00:00 IST 2015 | Sat Mar 28 17:00:00 IDT 2015
1261 | Prepare & Submit As-built Drawings | Mon Mar 02 08:00:00 IST 2015 | Thu Apr 30 17:00:00 IDT 2015
1262 | Cost Centre D - Nam Cheong Building Cut & Cover Tunnel | Mon Jan 31 08:00:00 IST 2011 | Sun May 10 17:00:00 IDT 2015
1263 | IPS Milestones | Sun Mar 31 17:00:00 IDT 2013 | Sun May 10 17:00:00 IDT 2015
1264 | General | Sun Mar 31 17:00:00 IDT 2013 | Sun May 10 17:00:00 IDT 2015
1265 | Complete D/T Cut & Cover Tunnel - Track Slab | Sun Mar 31 17:00:00 IDT 2013 | Sun Mar 31 17:00:00 IDT 2013
1266 | Deg. 1 Completion for D/T Tunnel | Sun Jun 15 17:00:00 IDT 2014 | Sun Jun 15 17:00:00 IDT 2014
1267 | Complete 40% U/T Cut & Cover Tunnel Structure | Sun Jun 15 17:00:00 IDT 2014 | Sun Jun 15 17:00:00 IDT 2014
1268 | Deg. 1 Completion for U/T Tunnel | Fri Mar 13 17:00:00 IST 2015 | Fri Mar 13 17:00:00 IST 2015
1269 | Closure of Access Opening in Tunnel Roof | Mon Mar 30 17:00:00 IDT 2015 | Mon Mar 30 17:00:00 IDT 2015
1270 | Complete All Works | Sun May 10 17:00:00 IDT 2015 | Sun May 10 17:00:00 IDT 2015
1271 | Design Preparation/Submission/Approval | Mon Jan 31 08:00:00 IST 2011 | Thu Sep 27 17:00:00 IST 2012
1272 | Design | Mon Jan 31 08:00:00 IST 2011 | Thu Sep 27 17:00:00 IST 2012
1273 | Prepare AIP Submission for Cut & Cover Tunnels | Mon Jan 31 08:00:00 IST 2011 | Wed May 25 17:00:00 IDT 2011
1274 | Submit AIP Submission for Cut & Cover Tunnels | Sat Mar 05 17:00:00 IST 2011 | Sat Mar 05 17:00:00 IST 2011
1275 | AIP Comment & Approval for Cut & Cover Tunnels by MTR | Sun Mar 06 08:00:00 IST 2011 | Tue Apr 05 17:00:00 IDT 2011
1276 | Prepare 1st DDA for Cut & Cover Tunnels | Mon Mar 07 08:00:00 IST 2011 | Wed Jul 13 17:00:00 IDT 2011
1277 | Submit 1st DDA for Cut & Cover Tunnels | Mon Apr 11 17:00:00 IDT 2011 | Mon Apr 11 17:00:00 IDT 2011
1278 | 1st DDA Comment & Approval by MTR (RDO/GEO consultation) | Tue Apr 12 08:00:00 IDT 2011 | Sun Jun 19 17:00:00 IDT 2011
1279 | Prepare 2nd DDA for Cut & Cover Tunnels | Mon Jan 16 08:00:00 IST 2012 | Tue Feb 21 17:00:00 IST 2012
1280 | Submit 2nd DDA for Cut & Cover Tunnels | Mon Jan 16 08:00:00 IST 2012 | Mon Jan 16 08:00:00 IST 2012
1281 | 2nd DDA for Cut & Cover Tunnels Comment & Approval by MTR | Fri Aug 31 08:00:00 IDT 2012 | Thu Sep 27 17:00:00 IST 2012
1282 | Method Statement Submission and Approval | Sun Jan 15 08:00:00 IST 2012 | Thu Oct 25 17:00:00 IST 2012
1283 | Method Statement Submission and Approval | Sun Jan 15 08:00:00 IST 2012 | Thu Oct 25 17:00:00 IST 2012
1284 | MS Submission Preparation for Cut & Cover Tunnel | Mon Jan 16 08:00:00 IST 2012 | Thu Feb 16 17:00:00 IST 2012
1285 | MS Submission to MTR | Mon Jan 16 08:00:00 IST 2012 | Mon Jan 16 08:00:00 IST 2012
1286 | MS Comment by MTR | Sun Jan 15 08:00:00 IST 2012 | Sat Feb 11 17:00:00 IST 2012
1287 | MS Re-submission Preparation | Mon Jan 16 08:00:00 IST 2012 | Wed Feb 15 17:00:00 IST 2012
1288 | MS Comment & Approval by MTR | Fri Sep 28 08:00:00 IST 2012 | Thu Oct 25 17:00:00 IST 2012
1289 | Issue for Construction | Thu Oct 25 17:00:00 IST 2012 | Thu Oct 25 17:00:00 IST 2012
1290 | Construction | Sat May 05 08:00:00 IDT 2012 | Sat Apr 18 17:00:00 IDT 2015
1291 | Cut & Cover Tunnel - Track Level | Sat May 05 08:00:00 IDT 2012 | Wed Jul 17 17:00:00 IDT 2013
1292 | D/T: Cut & Cover Tunnel - Wall AW1 | Fri Oct 12 08:00:00 IST 2012 | Tue Nov 06 17:00:00 IST 2012
1293 | D/T: Cut & Cover Tunnel - Wall AW1a | Tue Nov 20 08:00:00 IST 2012 | Wed Dec 05 17:00:00 IST 2012
1294 | D/T: Cut & Cover Tunnel - Wall AW2 | Thu Dec 06 08:00:00 IST 2012 | Mon Dec 31 17:00:00 IST 2012
1295 | D/T: Cut & Cover Tunnel - Wall AD0 | Wed Nov 07 08:00:00 IST 2012 | Thu Nov 22 17:00:00 IST 2012
1296 | U/T: Cut & Cover Tunnel - Slab ATS1 | Thu Dec 20 08:00:00 IST 2012 | Wed Jan 16 17:00:00 IST 2013
1297 | U/T: Cut & Cover Tunnel - Slab ATS2 | Wed Jan 09 08:00:00 IST 2013 | Thu Jan 31 17:00:00 IST 2013
1298 | D/T: Cut & Cover Tunnel - Removal of S4 Struts 2-P1 to P3 | Mon Nov 12 08:00:00 IST 2012 | Sat Nov 24 17:00:00 IST 2012
1299 | D/T: Cut & Cover Tunnel - Wall AD1 | Sat Jun 29 08:00:00 IDT 2013 | Wed Jul 17 17:00:00 IDT 2013
1300 | D/T: Cut & Cover Tunnel - Wall AD2 | Sat May 05 08:00:00 IDT 2012 | Wed May 23 17:00:00 IDT 2012
1301 | Shaft Box B (Northern Portion) | Mon Jan 28 08:00:00 IST 2013 | Wed Jun 11 17:00:00 IDT 2014
1302 | G/L 1 - 5 | Mon Jan 28 08:00:00 IST 2013 | Wed Jun 11 17:00:00 IDT 2014
1303 | Construction of Above Track Slab D/T | Mon Jan 28 08:00:00 IST 2013 | Sat Apr 13 17:00:00 IDT 2013
1304 | Construction of Above Track Slab U/T (Part 1) | Mon Jan 28 08:00:00 IST 2013 | Wed Apr 17 17:00:00 IDT 2013
1305 | Steel Bell & False Tunnel Dismantling | Tue Apr 22 08:00:00 IDT 2014 | Thu May 08 17:00:00 IDT 2014
1306 | Construction of Above Track Slab U/T (Part 2) | Wed May 07 08:00:00 IDT 2014 | Wed Jun 11 17:00:00 IDT 2014
1307 | G/L 1 - 9 | Tue Dec 31 08:00:00 IST 2013 | Thu Feb 13 17:00:00 IST 2014
1308 | North D/T: Construction of Walkway (Dkb137+783 to Dkb 137+850) | Wed Jan 15 08:00:00 IST 2014 | Thu Jan 30 17:00:00 IST 2014
1309 | North U/T: Construction of C & C Tunnel (GL 1 - 9) & Deg. 1 works | Tue Dec 31 08:00:00 IST 2013 | Thu Feb 13 17:00:00 IST 2014
1310 | South Opening at NAC (Dkb137+907 to Dkb137+941) | Mon Dec 02 08:00:00 IST 2013 | Sat Jan 24 17:00:00 IST 2015
1311 | Area 1 - South D/T: Construction of Walkway, External wall, Internal wall, End wall & Above Track Slab (Target dates) | Mon Dec 02 08:00:00 IST 2013 | Sat May 17 17:00:00 IDT 2014
1312 | Area 3 - South U/T: Construction of Walkway, External wall & Internal wall( Target dates) | Mon Sep 01 08:00:00 IDT 2014 | Sat Dec 20 17:00:00 IST 2014
1313 | Area 3 - South U/T: Construction of Above-Track Roof Slab (Closure of Opening) (Target dates) | Mon Dec 22 08:00:00 IST 2014 | Sat Jan 24 17:00:00 IST 2015
1314 | NAC Shaft - Central Opening Structure (Dkb137+850 to Dkb137+885) | Mon May 19 08:00:00 IDT 2014 | Sat Apr 18 17:00:00 IDT 2015
1315 | G/L 9 - 13 (Dkb137+850 to Dkb137+885) | Mon May 19 08:00:00 IDT 2014 | Sat Apr 18 17:00:00 IDT 2015
1316 | Area 2 - D/T Construction of External wall & Walkways | Mon May 19 08:00:00 IDT 2014 | Sat Jun 14 17:00:00 IDT 2014
1317 | Area 4B - Construction of Internal walls and Central portion of Above-Track Roof Slab with falsework | Mon Dec 29 08:00:00 IST 2014 | Sat Feb 07 17:00:00 IST 2015
1318 | Area 4A - U/T Construction of External wall & Walkways (Target dates) | Mon Dec 29 08:00:00 IST 2014 | Sat Jan 24 17:00:00 IST 2015
1319 | Area 4C - Close remaining Above-Track Roof Slab & RC duct btw Dkb137+850 to 137+885 (Target dates) | Mon Dec 29 08:00:00 IST 2014 | Sat Apr 18 17:00:00 IDT 2015
1320 | Cut and Cover Tunnel works
1321 | Access Dates for Designated Contractor
1322 | Submission | Mon Mar 02 08:00:00 IST 2015 | Thu Apr 16 17:00:00 IDT 2015
1323 | Completion | Mon Mar 02 08:00:00 IST 2015 | Thu Apr 16 17:00:00 IDT 2015
1324 | Prepare & Submit Draft As-built Drawings | Mon Mar 02 08:00:00 IST 2015 | Thu Apr 16 17:00:00 IDT 2015
1325 | Prepare & Submit As-built Drawings | Mon Mar 02 08:00:00 IST 2015 | Thu Apr 16 17:00:00 IDT 2015
1326 | Cost Centre E - Nam Cheong Ventilation Building | Wed May 12 08:00:00 IDT 2010 | Mon Aug 24 17:00:00 IDT 2015
1327 | IPS Milestones | Mon Feb 28 08:00:00 IST 2011 | Mon Aug 24 17:00:00 IDT 2015
1328 | General | Mon Feb 28 08:00:00 IST 2011 | Mon Aug 24 17:00:00 IDT 2015
1329 | Complete 20% of Diaphragm Wall | Mon Feb 28 08:00:00 IST 2011 | Mon Feb 28 08:00:00 IST 2011
1330 | Complete 90% Diaphragm Wall | Sun Jun 19 17:00:00 IDT 2011 | Sun Jun 19 17:00:00 IDT 2011
1331 | Complete 100% Diaphragm Wall | Sun Jun 19 17:00:00 IDT 2011 | Sun Jun 19 17:00:00 IDT 2011
1332 | Complete 45% of Excavation | Wed Aug 31 08:00:00 IDT 2011 | Wed Aug 31 08:00:00 IDT 2011
1333 | Complete Excavation | Sun Jan 15 08:00:00 IST 2012 | Sun Jan 15 08:00:00 IST 2012
1334 | Complete 70% Nam Cheong Vent. Building Structure | Sat Sep 14 17:00:00 IDT 2013 | Sat Sep 14 17:00:00 IDT 2013
1335 | Deg.1 Completion for Nam Cheong Vent. Building (VB7), except Track level and Above Track level | Sat May 31 17:00:00 IDT 2014 | Sat May 31 17:00:00 IDT 2014
1336 | All Permanent Doors Installed | Tue Mar 31 17:00:00 IDT 2015 | Tue Mar 31 17:00:00 IDT 2015
1337 | All Work Completed & Statutory Inspection Successfully Undertaken | Mon Aug 24 17:00:00 IDT 2015 | Mon Aug 24 17:00:00 IDT 2015
1338 | Design Preparation/Submission/Approval | Mon Jan 31 08:00:00 IST 2011 | Fri Apr 01 17:00:00 IDT 2011
1339 | Temp.Works Design Submission | Mon Jan 31 08:00:00 IST 2011 | Fri Apr 01 17:00:00 IDT 2011
1340 | Temp. Wokrs Desgn for DW | Mon Jan 31 08:00:00 IST 2011 | Tue Feb 22 17:00:00 IST 2011
1341 | Temp. Works Design Submit to MTR | Thu Mar 03 17:00:00 IST 2011 | Thu Mar 03 17:00:00 IST 2011
1342 | Temp. Works Design Reviewed by MTR | Fri Mar 04 08:00:00 IST 2011 | Tue Mar 29 17:00:00 IST 2011
1343 | Issue for Construction | Fri Apr 01 17:00:00 IDT 2011 | Fri Apr 01 17:00:00 IDT 2011
1344 | Diaphragm Wall Design/submission/Approval | Sat Jan 08 08:00:00 IST 2011 | Tue Nov 29 17:00:00 IST 2011
1345 | Design | Sat Jan 08 08:00:00 IST 2011 | Tue Nov 29 17:00:00 IST 2011
1346 | Prepare Zone A - D-Wall General Arrangement Dwgs & Calculations Part 1 | Sat Jan 08 08:00:00 IST 2011 | Fri Feb 25 17:00:00 IST 2011
1347 | Submit Zone A - D-Wall General Arrangement to MTR (RDO/GEO consultation) | Mon Jan 31 08:00:00 IST 2011 | Mon Jan 31 08:00:00 IST 2011
1348 | Zone A- D-Wall General Arrangement Comments & Approval by MTR (RDO/GEO consultation) | Mon Jan 31 08:00:00 IST 2011 | Sun Feb 13 17:00:00 IST 2011
1349 | Prepare Zone A - D-Wall R.C Details Dwgs.& Calculation Part 2 | Mon Jan 31 08:00:00 IST 2011 | Fri Mar 25 17:00:00 IST 2011
1350 | Submit Zone A - D-Wall R.C Details to MTR | Fri Mar 11 17:00:00 IST 2011 | Fri Mar 11 17:00:00 IST 2011
1351 | Zone A - D-Wall R.C Details Comment & Approval by MTR | Sat Mar 12 08:00:00 IST 2011 | Tue Mar 29 17:00:00 IST 2011
1352 | Prepare Zone A - D-Wall ELS | Sat Mar 12 08:00:00 IST 2011 | Wed Aug 03 17:00:00 IDT 2011
1353 | Submit Zone A - D-Wall ELS to MTR | Wed Apr 27 17:00:00 IDT 2011 | Wed Apr 27 17:00:00 IDT 2011
1354 | Zone A - D-Wall ELS Comment & Approval by MTR | Thu Apr 28 08:00:00 IDT 2011 | Wed Jul 13 17:00:00 IDT 2011
1355 | Prepare Zone B - D-Wall General Arrangement Dwgs & Calculations Part 1 | Sat Jan 08 08:00:00 IST 2011 | Tue Mar 22 17:00:00 IST 2011
1356 | Submit Zone B - D-Wall General Arrangement to MTR (RDO/GEO consultation) | Wed Feb 09 17:00:00 IST 2011 | Wed Feb 09 17:00:00 IST 2011
1357 | Zone B - D-Wall General Arrangement Comments & Approval by MTR (RDO/GEO consultation) | Thu Feb 10 08:00:00 IST 2011 | Thu Mar 10 17:00:00 IST 2011
1358 | Prepare Zone B - D-Wall R.C Details Dwgs.& Calculation Part 2 | Sat Mar 12 08:00:00 IST 2011 | Mon May 16 17:00:00 IDT 2011
1359 | Submit Zone B - D-Wall R.C Details to MTR | Tue Apr 26 17:00:00 IDT 2011 | Tue Apr 26 17:00:00 IDT 2011
1360 | Zone B - D-Wall R.C Details Comments & Approval by MTR | Wed Apr 27 08:00:00 IDT 2011 | Sat May 14 17:00:00 IDT 2011
1361 | Prepare Zone B- D-Wall ELS | Wed Apr 06 08:00:00 IDT 2011 | Tue Nov 29 17:00:00 IST 2011
1362 | Submit Zone B - D-Wall ELS to MTR | Mon Jun 20 08:00:00 IDT 2011 | Mon Jun 20 08:00:00 IDT 2011
1363 | Zone B - D-Wall ELS Comment & Approval by MTR | Sun Jun 19 08:00:00 IDT 2011 | Tue Jul 19 17:00:00 IDT 2011
1364 | Method Statement Submission and Approval | Mon Jan 31 08:00:00 IST 2011 | Sat Apr 02 17:00:00 IDT 2011
1365 | Method Statement Submission and Approval | Mon Jan 31 08:00:00 IST 2011 | Sat Apr 02 17:00:00 IDT 2011
1366 | MS Preparation for Diaphragm wall | Mon Jan 31 08:00:00 IST 2011 | Wed Mar 16 17:00:00 IST 2011
1367 | MS Submission to MTR | Fri Mar 04 17:00:00 IST 2011 | Fri Mar 04 17:00:00 IST 2011
1368 | MS Comment & Approval by MTR | Sat Mar 05 08:00:00 IST 2011 | Wed Mar 23 17:00:00 IST 2011
1369 | Issue for Construction | Sat Apr 02 17:00:00 IDT 2011 | Sat Apr 02 17:00:00 IDT 2011
1370 | TTM Submission and Approval | Wed May 12 08:00:00 IDT 2010 | Sat Feb 12 17:00:00 IST 2011
1371 | TTM Scheme Submission & Approval | Wed May 12 08:00:00 IDT 2010 | Sat Feb 12 17:00:00 IST 2011
1372 | Prepare Temporary Traffic Management (Main Road) | Wed May 12 08:00:00 IDT 2010 | Tue Jun 08 17:00:00 IDT 2010
1373 | TTM reviewed by SLG | Wed May 12 08:00:00 IDT 2010 | Fri Jul 09 17:00:00 IDT 2010
1374 | Approved TTMS | Wed May 12 08:00:00 IDT 2010 | Wed May 12 08:00:00 IDT 2010
1375 | Issue Endorsed Drawings | Wed May 12 08:00:00 IDT 2010 | Tue May 18 17:00:00 IDT 2010
1376 | Notification to RMO | Wed May 12 08:00:00 IDT 2010 | Tue May 18 17:00:00 IDT 2010
1377 | XP Application & Approval (Main Road) | Sat Jan 08 08:00:00 IST 2011 | Sat Feb 12 17:00:00 IST 2011
1378 | Implement TTM (Main Road) | Fri Aug 06 17:00:00 IDT 2010 | Fri Aug 06 17:00:00 IDT 2010
1379 | Prepare TTM (Footpath Closure) | Wed May 12 08:00:00 IDT 2010 | Tue Jun 08 17:00:00 IDT 2010
1380 | TTM Reviewed by SLG | Wed May 12 08:00:00 IDT 2010 | Fri Jul 09 17:00:00 IDT 2010
1381 | Approved TTMS | Wed May 12 08:00:00 IDT 2010 | Wed May 12 08:00:00 IDT 2010
1382 | Issue Endorsed Drawings | Wed May 12 08:00:00 IDT 2010 | Tue May 18 17:00:00 IDT 2010
1383 | Notification to RMO | Wed May 12 08:00:00 IDT 2010 | Tue May 18 17:00:00 IDT 2010
1384 | Implement TTM (Footpath Closure) | Wed May 12 08:00:00 IDT 2010 | Wed May 12 08:00:00 IDT 2010
1385 | Site Establishment | Mon Jan 31 08:00:00 IST 2011 | Wed Apr 06 17:00:00 IDT 2011
1386 | General | Mon Jan 31 08:00:00 IST 2011 | Wed Apr 06 17:00:00 IDT 2011
1387 | Site Establishment for Works Areas 11.23,11.23A, 11.23B &11.26A | Tue Feb 01 08:00:00 IST 2011 | Thu Mar 03 17:00:00 IST 2011
1388 | Installation of Instrumentation for D-wall Construction | Fri Mar 04 08:00:00 IST 2011 | Wed Mar 16 17:00:00 IST 2011
1389 | Preparation of CNP for Shaft Works | Mon Jan 31 08:00:00 IST 2011 | Thu Mar 17 17:00:00 IST 2011
1390 | CNP Submission Approval by EPD | Mon Mar 21 08:00:00 IST 2011 | Wed Apr 06 17:00:00 IDT 2011
1391 | Zone A | Sat Jan 08 08:00:00 IST 2011 | Fri Aug 30 17:00:00 IDT 2013
1392 | D-wall Construction 38nos. & Pump Test | Mon Jan 07 08:00:00 IST 2013 | Sun Aug 25 17:00:00 IDT 2013
1393 | ELS | Mon Jan 07 08:00:00 IST 2013 | Fri Aug 23 17:00:00 IDT 2013
1394 | General | Tue Feb 01 08:00:00 IST 2011 | Mon Mar 28 17:00:00 IST 2011
1395 | Close Footpath (Zone 1) | Tue Feb 01 08:00:00 IST 2011 | Mon Feb 07 17:00:00 IST 2011
1396 | Trial Trench for Gas Main | Tue Feb 08 08:00:00 IST 2011 | Mon Feb 14 17:00:00 IST 2011
1397 | Gas Min Diversion (GAS210) | Tue Feb 15 08:00:00 IST 2011 | Mon Mar 28 17:00:00 IST 2011
1398 | Zone A Construction | Sat Jan 08 08:00:00 IST 2011 | Fri Aug 30 17:00:00 IDT 2013
1399 | Pre-Drilling | Sat Jan 08 08:00:00 IST 2011 | Fri Apr 01 17:00:00 IDT 2011
1400 | Ground Treatment to Previous Seawall Zone (for D1 to D15) | Sat Apr 09 08:00:00 IDT 2011 | Thu Jun 16 17:00:00 IDT 2011
1401 | Guide Wall Installation/Predrilling | Sat Mar 12 08:00:00 IST 2011 | Tue Aug 02 17:00:00 IDT 2011
1402 | Temp.D-Wall Installation (38 Panels) | Fri Mar 25 08:00:00 IST 2011 | Thu Aug 25 17:00:00 IDT 2011
1403 | Shear Pin Installation | Tue Feb 01 08:00:00 IST 2011 | Wed Mar 30 17:00:00 IST 2011
1404 | Toe Grouting | Mon Feb 21 08:00:00 IST 2011 | Sat May 07 17:00:00 IDT 2011
1405 | Capping Beam | Tue Feb 01 08:00:00 IST 2011 | Wed Mar 09 17:00:00 IST 2011
1406 | Installation of instrumentation and Pumping Test | Mon Feb 28 08:00:00 IST 2011 | Sat Apr 16 17:00:00 IDT 2011
1407 | King Post & Gantry Post Installation (KP-4nos. & GP-6nos.) | Tue Feb 01 08:00:00 IST 2011 | Thu Mar 03 17:00:00 IST 2011
1408 | D-wall Construction 38nos. & Pump Test | Mon Jan 07 08:00:00 IST 2013 | Fri Aug 30 17:00:00 IDT 2013
1409 | Stell Bell Installation | Fri Mar 09 08:00:00 IST 2012 | Thu Apr 19 17:00:00 IDT 2012
1410 | Zone A Excavation | Mon Mar 28 08:00:00 IST 2011 | Thu May 31 17:00:00 IDT 2012
1411 | VER.B
1412 | Shaft A ELS | Mon Mar 28 08:00:00 IST 2011 | Thu May 31 17:00:00 IDT 2012
1413 | Surface Levelling to +3.80mPD (for Capping Beam & S1 Strutting) | Mon Mar 28 08:00:00 IST 2011 | Sat Jun 04 17:00:00 IDT 2011
1414 | ELS for Box A (for Steel Bell installation) | Tue Jun 21 08:00:00 IDT 2011 | Thu Jan 26 17:00:00 IST 2012
1415 | ELS for Box A (Remaining) | Mon Jan 16 08:00:00 IST 2012 | Wed Mar 07 17:00:00 IST 2012
1416 | Base Slab Part 1 | Mon Jan 16 08:00:00 IST 2012 | Wed Feb 22 17:00:00 IST 2012
1417 | Strutting Removal for S5 & S6 | Mon Jan 16 08:00:00 IST 2012 | Mon Jan 30 17:00:00 IST 2012
1418 | Base Slab Part 2 | Mon Jan 16 08:00:00 IST 2012 | Thu Mar 15 17:00:00 IST 2012
1419 | Brackets Installation | Mon Jan 16 08:00:00 IST 2012 | Wed Jan 18 17:00:00 IST 2012
1420 | Steel Bell Installation | Mon Jan 16 08:00:00 IST 2012 | Tue Jan 31 17:00:00 IST 2012
1421 | Tympanum Drilling & Steel Fixing | Mon Jan 16 08:00:00 IST 2012 | Thu May 31 17:00:00 IDT 2012
1422 | Zone B | Wed May 12 08:00:00 IDT 2010 | Wed May 23 17:00:00 IDT 2012
1423 | D-wall Construction 13+20nos. & Pump Test | Mon Aug 15 08:00:00 IDT 2011 | Wed May 23 17:00:00 IDT 2012
1424 | ELS | Sun Jun 26 08:00:00 IDT 2011 | Thu Dec 22 17:00:00 IST 2011
1425 | General | Wed May 12 08:00:00 IDT 2010 | Thu Jun 23 17:00:00 IDT 2011
1426 | Tree Transplant by 801 Designated Contractor | Tue Sep 14 08:00:00 IST 2010 | Tue Sep 14 08:00:00 IST 2010
1427 | TTM Implementation (Footpath Closure) | Wed May 12 08:00:00 IDT 2010 | Wed May 12 17:00:00 IDT 2010
1428 | TTM Implementation (Main Road) | Sat Aug 07 08:00:00 IDT 2010 | Sat Aug 07 17:00:00 IDT 2010
1429 | Trial Trench to Expose Utilities @ Footpath | Sat Jan 08 08:00:00 IST 2011 | Fri Jan 21 17:00:00 IST 2011
1430 | Trial Trench for CLP Cable208&209 | Sat Jan 08 08:00:00 IST 2011 | Wed Jan 26 17:00:00 IST 2011
1431 | Excavate Trench for Utilities Diversion | Sat Jan 08 08:00:00 IST 2011 | Sat Jan 22 17:00:00 IST 2011
1432 | Gas Main Diversion (GAS209&GAS208) | Tue Jan 18 08:00:00 IST 2011 | Tue Feb 08 17:00:00 IST 2011
1433 | Preparation works & Excavation for Utilities Diversion | Wed May 12 08:00:00 IDT 2010 | Sat Jul 31 17:00:00 IDT 2010
1434 | Expose and Protect Saltwater Main (SW203) | Sat Jan 08 08:00:00 IST 2011 | Tue Jan 25 17:00:00 IST 2011
1435 | Slew HGC+Cable TV Cable (HGC204+CATV208) | Sat Jan 08 08:00:00 IST 2011 | Sat Feb 12 17:00:00 IST 2011
1436 | Slew WTT+PCCW Cable (WTT205+PCCW205) | Sat Jan 08 08:00:00 IST 2011 | Sat Feb 12 17:00:00 IST 2011
1437 | Slew CLP 11kV Cable | Thu Feb 17 08:00:00 IST 2011 | Thu Feb 24 17:00:00 IST 2011
1438 | Slew 400kV Cable (CLP208) | Sat Aug 07 08:00:00 IDT 2010 | Sat Oct 02 17:00:00 IST 2010
1439 | SlewTelecomCable(HGC204+CATV208)to UtilityTrough | Tue May 31 08:00:00 IDT 2011 | Thu Jun 23 17:00:00 IDT 2011
1440 | SlewTelecomCable(WTT205+PCCW205)to UtilityTrough | Tue May 31 08:00:00 IDT 2011 | Thu Jun 23 17:00:00 IDT 2011
1441 | Backfill & Protection for Utilities | Mon Feb 28 08:00:00 IST 2011 | Wed May 04 17:00:00 IDT 2011
1442 | Zone B West (Not within Utilities Zone) | Mon Feb 28 08:00:00 IST 2011 | Wed May 23 17:00:00 IDT 2012
1443 | Pre-drilling/Guide Wall Installation | Sat Mar 12 08:00:00 IST 2011 | Sat Apr 09 17:00:00 IDT 2011
1444 | Temp.D-Wall Installation (13Panels) | Thu Apr 28 08:00:00 IDT 2011 | Tue Aug 16 17:00:00 IDT 2011
1445 | Shear Pin Installation | Mon Feb 28 08:00:00 IST 2011 | Thu Jun 23 17:00:00 IDT 2011
1446 | Toe Grouting | Fri Apr 01 08:00:00 IDT 2011 | Wed Jul 27 17:00:00 IDT 2011
1447 | Stitch Grouting btn D-Wall & FS1 Culvert | Tue Jun 21 08:00:00 IDT 2011 | Mon Jul 18 17:00:00 IDT 2011
1448 | D-wall Construction 13+20nos. & Pump Test | Mon Aug 15 08:00:00 IDT 2011 | Wed May 23 17:00:00 IDT 2012
1449 | Zone B Remaining | Tue Feb 01 08:00:00 IST 2011 | Wed Feb 01 17:00:00 IST 2012
1450 | Ground Treatment to Previous Seawall Zone | Tue Feb 01 08:00:00 IST 2011 | Wed Jun 01 17:00:00 IDT 2011
1451 | Pre-drilling/ Guide Wall Installation | Tue Feb 01 08:00:00 IST 2011 | Mon Mar 21 17:00:00 IST 2011
1452 | Temp.D-Wall Installation ( 20 Panels) | Mon Mar 21 08:00:00 IST 2011 | Sat Oct 08 17:00:00 IST 2011
1453 | Shear Pin Installation | Thu Jul 14 11:00:00 IDT 2011 | Fri Sep 02 11:00:00 IDT 2011
1454 | Toe Grouting | Fri Jul 29 08:00:00 IDT 2011 | Tue Aug 30 17:00:00 IDT 2011
1455 | Stitch Grouting between D-Wall & FS1 Culvert | Wed Jul 06 08:00:00 IDT 2011 | Thu Aug 25 17:00:00 IDT 2011
1456 | Capping Beam | Tue Jun 21 08:00:00 IDT 2011 | Tue Aug 09 17:00:00 IDT 2011
1457 | Install Instrumentation+Pumping Test | Thu Aug 04 08:00:00 IDT 2011 | Wed Sep 21 17:00:00 IDT 2011
1458 | Utilities Common Trough | Mon Jan 16 08:00:00 IST 2012 | Wed Feb 01 17:00:00 IST 2012
1459 | Setup & Install Four Prebored H-piles (adjacent to Existing B17) | Fri Jul 08 08:00:00 IDT 2011 | Mon Jul 25 17:00:00 IDT 2011
1460 | King Post & Gantry Post Installation (7KP & 2GP) | Tue Jun 21 08:00:00 IDT 2011 | Tue Aug 02 17:00:00 IDT 2011
1461 | Zone B Excavation | Tue Jun 21 08:00:00 IDT 2011 | Tue Apr 03 17:00:00 IDT 2012
1462 | ELS | Sun Jun 26 08:00:00 IDT 2011 | Thu Dec 22 17:00:00 IST 2011
1463 | Steel Bell Installation | Sun Jan 15 08:00:00 IST 2012 | Sun Jan 15 08:00:00 IST 2012
1464 | Shaft B ELS | Tue Jun 21 08:00:00 IDT 2011 | Tue Apr 03 17:00:00 IDT 2012
1465 | Surface Levelling to +3.80mPD (for Capping Beam & S1 Strutting) | Wed Aug 24 08:00:00 IDT 2011 | Wed Sep 28 17:00:00 IDT 2011
1466 | ELS for Box B (for Steel Bell Installation) | Tue Jun 21 08:00:00 IDT 2011 | Thu Nov 10 17:00:00 IST 2011
1467 | ELS for Box B (Remaining) | Mon Jan 16 08:00:00 IST 2012 | Thu Mar 01 17:00:00 IST 2012
1468 | Base Slab Part 1 | Mon Jan 16 08:00:00 IST 2012 | Tue Feb 21 17:00:00 IST 2012
1469 | Strutting Removal for S5 & S6 | Mon Jan 16 08:00:00 IST 2012 | Thu Jan 26 17:00:00 IST 2012
1470 | Base Slab Part 2 | Mon Jan 16 08:00:00 IST 2012 | Wed Feb 29 17:00:00 IST 2012
1471 | Brackets Installation | Mon Jan 16 08:00:00 IST 2012 | Tue Jan 17 17:00:00 IST 2012
1472 | Steel Bell Installation | Mon Jan 16 08:00:00 IST 2012 | Wed Feb 01 17:00:00 IST 2012
1473 | Tympanum Drilling & Steel Fixing | Mon Jan 16 08:00:00 IST 2012 | Tue Apr 03 17:00:00 IDT 2012
1474 | Ventilation Building | Sat Sep 01 08:00:00 IDT 2012 | Mon Aug 24 17:00:00 IDT 2015
1475 | Access Dates for Designated Contractors | Mon Apr 28 08:00:00 IDT 2014 | Mon Apr 28 08:00:00 IDT 2014
1476 | *815 - Ironmongery Delivery to Site | Mon Apr 28 08:00:00 IDT 2014 | Mon Apr 28 08:00:00 IDT 2014
1477 | Reinforced Concrete Structure | Sat Sep 01 08:00:00 IDT 2012 | Thu Aug 13 17:00:00 IDT 2015
1478 | Shaft Box B (Northern Portion) | Sat Sep 01 08:00:00 IDT 2012 | Fri Jun 06 17:00:00 IDT 2014
1479 | G/L 1 - 5 | Fri Jan 04 08:00:00 IST 2013 | Sat Jul 06 17:00:00 IDT 2013
1480 | Construction of L2 Slab | Fri Jan 04 08:00:00 IST 2013 | Sat Feb 02 17:00:00 IST 2013
1481 | Construction of L1 Slab | Wed Feb 20 08:00:00 IST 2013 | Thu Mar 21 17:00:00 IST 2013
1482 | Construction of L0 Slab | Mon Jun 03 08:00:00 IDT 2013 | Sat Jul 06 17:00:00 IDT 2013
1483 | G/L 5 - 9 | Sat Sep 01 08:00:00 IDT 2012 | Thu Jul 11 17:00:00 IDT 2013
1484 | Construction of L2 Slab | Sat Sep 01 08:00:00 IDT 2012 | Wed Nov 28 17:00:00 IST 2012
1485 | Construction of L1 Slab (including 2 FS Tank) | Thu Nov 29 08:00:00 IST 2012 | Fri Mar 08 17:00:00 IST 2013
1486 | Construction of L0 Slab | Mon Apr 29 08:00:00 IDT 2013 | Thu Jul 11 17:00:00 IDT 2013
1487 | G/L 1 - 6 | Mon Nov 11 08:00:00 IST 2013 | Fri Jun 06 17:00:00 IDT 2014
1488 | Construction of G/L Slab | Tue Mar 04 08:00:00 IST 2014 | Wed Mar 26 17:00:00 IST 2014
1489 | Construction of U1 Slab | Mon Apr 14 08:00:00 IDT 2014 | Mon May 05 17:00:00 IDT 2014
1490 | Construction of Service Slab | Fri May 23 08:00:00 IDT 2014 | Fri Jun 06 17:00:00 IDT 2014
1491 | Construction of Roof Slab | Mon May 19 08:00:00 IDT 2014 | Wed Jun 04 17:00:00 IDT 2014
1492 | Gantry impact from TBM Re-assembly and False Tunnel Dismantling | Mon Nov 11 08:00:00 IST 2013 | Thu Jan 23 17:00:00 IST 2014
1493 | Ch137+968 to Ch138+328 (200 Ring nos.) | Sat Dec 14 08:00:00 IST 2013 | Tue Jan 21 17:00:00 IST 2014
1494 | Shaft Box A (Southern Portion)
1495 | G/L 13 - 15
1496 | G/L 11 - 13
1497 | FS1 Works at Shaft Central Portion | Mon Jun 15 08:00:00 IDT 2015 | Thu Aug 13 17:00:00 IDT 2015
1498 | G/L 9 - 11 | Mon Jun 15 08:00:00 IDT 2015 | Thu Aug 13 17:00:00 IDT 2015
1499 | Construction of column & cantilver slab under FS1 (after closure of opening) | Mon Jun 15 08:00:00 IDT 2015 | Thu Jul 09 17:00:00 IDT 2015
1500 | Backfilling & Reinstatement of FS1 | Sat Jul 11 08:00:00 IDT 2015 | Thu Aug 13 17:00:00 IDT 2015
1501 | Track Level
1502 | Above Track Level
1503 | L2 Level
1504 | L1 Level
1505 | L0 Level
1506 | G/F Level
1507 | U1 Level
1508 | Backfilling, Strut removal & Reinstatement | Mon Aug 05 08:00:00 IDT 2013 | Thu Jul 30 09:36:00 IDT 2015
1509 | Backfilling and Strut Removal | Mon Aug 05 08:00:00 IDT 2013 | Wed Jul 15 17:00:00 IDT 2015
1510 | GL 1 - 8 (works concurrently to VB7 construction) | Mon Aug 05 08:00:00 IDT 2013 | Fri Nov 22 17:00:00 IST 2013
1511 | GL 15 - 20 | Thu Apr 02 08:00:00 IDT 2015 | Mon Jun 08 17:00:00 IDT 2015
1512 | GL 8 - 15 | Mon May 18 08:00:00 IDT 2015 | Wed Jul 15 17:00:00 IDT 2015
1513 | Housing Car park and Podium Shop | Sat Jul 11 09:36:00 IDT 2015 | Thu Jul 30 09:36:00 IDT 2015
1514 | Concrete breaking of last 2m of D-wall (Option) | Sat Jul 11 09:36:00 IDT 2015 | Thu Jul 30 09:36:00 IDT 2015
1515 | ABWF works | Wed Sep 11 08:00:00 IDT 2013 | Mon Aug 24 17:00:00 IDT 2015
1516 | Degree 1 works | Wed Sep 11 08:00:00 IDT 2013 | Mon Jul 28 17:00:00 IDT 2014
1517 | Ref.4C (i) (Deg.1): All Rms within VB7 at Level L2, UL2, L1 and UL1 | Wed Sep 11 08:00:00 IDT 2013 | Fri Nov 29 17:00:00 IST 2013
1518 | Floor Screeding (L2) | Wed Sep 11 08:00:00 IDT 2013 | Fri Oct 25 17:00:00 IDT 2013
1519 | Floor Screeding (L1) | Fri Nov 01 08:00:00 IST 2013 | Fri Nov 29 17:00:00 IST 2013
1520 | Ref.4C (ii) (Deg.1): All Rms within VB7 at Track Level & Above Track Level | Mon Dec 02 08:00:00 IST 2013 | Sat Mar 01 17:00:00 IST 2014
1521 | Floor Screeding (Track Level & Above Track Level) | Mon Dec 02 08:00:00 IST 2013 | Wed Jan 15 17:00:00 IST 2014
1522 | Degree 1 works for 4C(ii) | Wed Jan 15 08:00:00 IST 2014 | Sat Mar 01 17:00:00 IST 2014
1523 | Ref.4C (iii) (Deg.1): All Rms within VB7 (excluding Ref.4C (i) & 4C (ii)) | Mon Apr 07 08:00:00 IDT 2014 | Mon Jul 28 17:00:00 IDT 2014
1524 | Floor Screeding (G/F) | Fri May 02 08:00:00 IDT 2014 | Fri May 16 17:00:00 IDT 2014
1525 | Degree 1 works for 4C (iii) | Mon Apr 07 08:00:00 IDT 2014 | Wed May 28 17:00:00 IDT 2014
1526 | Floor Screeding (U1/F) | Tue May 27 08:00:00 IDT 2014 | Tue Jun 10 17:00:00 IDT 2014
1527 | Floor Screeding & Waterproofing (Roof) | Wed Jul 23 08:00:00 IDT 2014 | Mon Jul 28 17:00:00 IDT 2014
1528 | Degree 2 works | Mon Nov 04 08:00:00 IST 2013 | Sat Jul 12 17:00:00 IDT 2014
1529 | Deg. 2 Works for Level L1, UL2, L1 and UL1 | Mon Nov 04 08:00:00 IST 2013 | Tue Feb 11 17:00:00 IST 2014
1530 | Deg. 2 Works for Track level and Above Track level | Tue Dec 31 08:00:00 IST 2013 | Sat Mar 22 17:00:00 IST 2014
1531 | Deg. 2 Works for Level L0, Ground Floor, U1, Service level & Roof | Mon Mar 24 08:00:00 IST 2014 | Sat Jul 12 17:00:00 IDT 2014
1532 | Degree 3 works | Mon Feb 24 08:00:00 IST 2014 | Fri Sep 05 17:00:00 IDT 2014
1533 | Deg. 3 Works for Level L1, UL2, L1 and UL1 | Mon Feb 24 08:00:00 IST 2014 | Thu Apr 17 17:00:00 IDT 2014
1534 | Deg. 3 Works for Track level and Above Track level | Mon Mar 24 08:00:00 IST 2014 | Sat May 17 17:00:00 IDT 2014
1535 | Deg. 3 Works for Level L0, Ground Floor, U1, Service level & Roof | Mon Jul 14 08:00:00 IDT 2014 | Fri Sep 05 17:00:00 IDT 2014
1536 | External Works | Fri May 23 08:00:00 IDT 2014 | Mon Aug 24 17:00:00 IDT 2015
1537 | Start External works | Fri May 23 08:00:00 IDT 2014 | Fri May 23 08:00:00 IDT 2014
1538 | Site Formation Works | Fri May 23 08:00:00 IDT 2014 | Thu Aug 07 17:00:00 IDT 2014
1539 | Roadworks and External Works | Fri Jun 13 08:00:00 IDT 2014 | Thu Aug 28 17:00:00 IDT 2014
1540 | Landscaping | Mon Dec 15 08:00:00 IST 2014 | Mon Mar 23 08:24:00 IST 2015
1541 | Paving | Thu Aug 14 08:00:00 IDT 2014 | Sat Oct 25 08:48:00 IDT 2014
1542 | Statutory Inspection | Sat Jul 25 08:00:00 IDT 2015 | Mon Aug 24 17:00:00 IDT 2015
1543 | Complete Ext. Water Works & Connect to Watermains | Fri Jul 24 17:00:00 IDT 2015 | Fri Jul 24 17:00:00 IDT 2015
1544 | Completion Ext. Telephone Drawpits & Ducts | Fri Jul 24 17:00:00 IDT 2015 | Fri Jul 24 17:00:00 IDT 2015
1545 | Submission | Mon Jan 12 08:00:00 IST 2015 | Thu Apr 30 17:00:00 IDT 2015
1546 | Completion | Mon Jan 12 08:00:00 IST 2015 | Thu Apr 30 17:00:00 IDT 2015
1547 | Prepare & Submit Draft As-built Drawings | Mon Jan 12 08:00:00 IST 2015 | Sat Feb 07 17:00:00 IST 2015
1548 | Prepare & Submit As-built Drawings | Mon Mar 02 08:00:00 IST 2015 | Thu Apr 30 17:00:00 IDT 2015
1549 | Prepare & Submit Draft O&M Manuals | Fri Jan 16 08:00:00 IST 2015 | Thu Feb 12 17:00:00 IST 2015
1550 | Prepare & Submit O&M Manuals | Mon Mar 02 08:00:00 IST 2015 | Thu Apr 30 17:00:00 IDT 2015
1551 | Cost Centre F - Obstruction removal & Reinstate Works | Sat Jan 08 08:00:00 IST 2011 | Sun May 10 17:00:00 IDT 2015
1552 | IPS Milestones | Mon Feb 28 08:00:00 IST 2011 | Sun May 10 17:00:00 IDT 2015
1553 | General | Mon Feb 28 08:00:00 IST 2011 | Sun May 10 17:00:00 IDT 2015
1554 | Obtain SLG Approval for Confirm Old CheungShaWan Cargo Pier Pile Locat'n | Mon Feb 28 08:00:00 IST 2011 | Mon Feb 28 08:00:00 IST 2011
1555 | Complete Removal of 3 nos. Existing Piles | Wed Sep 07 17:00:00 IDT 2011 | Wed Sep 07 17:00:00 IDT 2011
1556 | Complete 10% Mini-piles for Lai Chi Kok Overpass | Wed Aug 31 08:00:00 IDT 2011 | Wed Aug 31 08:00:00 IDT 2011
1557 | Complete Backfilling Works for Demolished FMO Maket Pier B | Sun Jan 15 08:00:00 IST 2012 | Sun Jan 15 08:00:00 IST 2012
1558 | Removal of Obstruction Piles for Demolished Sham Shui Po Pier (DT) | Tue Nov 13 17:00:00 IST 2012 | Tue Nov 13 17:00:00 IST 2012
1559 | Removal of Obstruction Piles for Old Cheung Sha Wan Cargo Pier(DT) | Fri Aug 31 08:00:00 IDT 2012 | Fri Aug 31 08:00:00 IDT 2012
1560 | Complete Reinstatement of TWL Sump | Tue Jan 15 17:00:00 IST 2013 | Tue Jan 15 17:00:00 IST 2013
1561 | Complete U/G Services & Reinstatement for Lai Chi Kok Overpass | Sun Sep 29 17:00:00 IDT 2013 | Sun Sep 29 17:00:00 IDT 2013
1562 | Complete All Works | Sun May 10 17:00:00 IDT 2015 | Sun May 10 17:00:00 IDT 2015
1563 | F1 Complete TWL New Sump Provision | Mon Feb 28 08:00:00 IST 2011 | Mon Jul 29 17:00:00 IDT 2013
1564 | Method Statement Submission and Approval | Mon May 16 08:00:00 IDT 2011 | Fri Nov 25 17:00:00 IST 2011
1565 | MS Preparation for TWL Sump Pit Modification | Mon May 16 08:00:00 IDT 2011 | Wed Oct 12 17:00:00 IST 2011
1566 | MS Submission to MTR | Wed Aug 31 08:00:00 IDT 2011 | Wed Aug 31 08:00:00 IDT 2011
1567 | MS Comment by MTR | Wed Aug 31 08:00:00 IDT 2011 | Tue Sep 27 17:00:00 IDT 2011
1568 | MS Re-submission Preparation | Wed Aug 31 08:00:00 IDT 2011 | Wed Sep 14 17:00:00 IDT 2011
1569 | MS Comment & Approval by MTR | Wed Aug 31 08:00:00 IDT 2011 | Tue Sep 27 17:00:00 IDT 2011
1570 | Issue for Construction | Fri Nov 25 17:00:00 IST 2011 | Fri Nov 25 17:00:00 IST 2011
1571 | Design Submission & Approval | Mon Feb 28 08:00:00 IST 2011 | Fri Oct 21 17:00:00 IST 2011
1572 | AIP Submission of Temp.& Permanent Sump Modification | Wed Jun 08 08:00:00 IDT 2011 | Thu Jul 07 17:00:00 IDT 2011
1573 | MTR's Comment for AIP of Temp.& Permanent Sump Modification | Mon Feb 28 08:00:00 IST 2011 | Sat Mar 12 17:00:00 IST 2011
1574 | AIP Re-submission of Temp.&Permanent Sump Modification | Mon Feb 28 08:00:00 IST 2011 | Wed Mar 30 17:00:00 IST 2011
1575 | MTR's Comment & Approval for AIP of Temp.Work Design for Sump Modification | Mon Feb 28 08:00:00 IST 2011 | Sun Jul 17 17:00:00 IDT 2011
1576 | DDA Submission of Temp.Shaft Design | Wed Jun 08 08:00:00 IDT 2011 | Wed Jul 06 17:00:00 IDT 2011
1577 | MTR's Comment & Approval for DDA of Temp.Shaft Design | Mon Feb 28 08:00:00 IST 2011 | Mon Aug 01 17:00:00 IDT 2011
1578 | DDA Submission of Permanent Sump Modification | Wed Aug 31 08:00:00 IDT 2011 | Wed Sep 28 17:00:00 IDT 2011
1579 | MTR's Comment & Approval for DDA of Permanent Sump Modification | Thu Sep 29 08:00:00 IDT 2011 | Fri Oct 21 17:00:00 IST 2011
1580 | AIP Submission of TWL Protection Works | Wed May 25 08:00:00 IDT 2011 | Tue Jun 21 17:00:00 IDT 2011
1581 | MTR's Comment for AIP of TWL Protection Works | Mon Feb 28 08:00:00 IST 2011 | Sun Mar 13 17:00:00 IST 2011
1582 | 1st AIP Re-submission of TWL Protection Works | Mon Feb 28 08:00:00 IST 2011 | Tue Mar 29 17:00:00 IST 2011
1583 | MTR's Comment & Approval for 1st AIP of TWL Protection Works | Mon Feb 28 08:00:00 IST 2011 | Tue Mar 22 17:00:00 IST 2011
1584 | 2nd AIP Re-submission of TWL Protection Works | Mon Feb 28 08:00:00 IST 2011 | Wed Jul 20 17:00:00 IDT 2011
1585 | MTR's Approval for 2nd AIP of TWL Protection Works | Thu Sep 01 08:00:00 IDT 2011 | Wed Sep 28 17:00:00 IDT 2011
1586 | DDA Submission of TWL Protection Works | Wed Aug 31 08:00:00 IDT 2011 | Wed Sep 28 17:00:00 IDT 2011
1587 | MTR's Approval for DDA of TWL Protection Works | Wed Aug 31 08:00:00 IDT 2011 | Tue Sep 27 17:00:00 IDT 2011
1588 | EDOC (TWL) Submission of Temp.Sump Modification | Wed Jun 08 08:00:00 IDT 2011 | Fri Jul 08 17:00:00 IDT 2011
1589 | MTR's Comment for EDOC (TWL)Temp.Sump Modification | Mon Feb 28 08:00:00 IST 2011 | Wed Mar 23 17:00:00 IST 2011
1590 | EDOC (TWL) Re-submission of Temp.Sump Modification | Mon Feb 28 08:00:00 IST 2011 | Wed May 11 17:00:00 IDT 2011
1591 | MTR's Comment & Approval for EDOC of Temp.Work Design for Sump Modification | Mon Feb 28 08:00:00 IST 2011 | Sun Jul 17 17:00:00 IDT 2011
1592 | EDOC (TWL) Submission of Protection Works | Wed Jun 08 08:00:00 IDT 2011 | Fri Jul 08 17:00:00 IDT 2011
1593 | MTR's Comment for EDOC (TWL) Protection Works | Mon Feb 28 08:00:00 IST 2011 | Sat Sep 24 17:00:00 IDT 2011
1594 | EDOC (TWL) Re-submission of Protection Works | Wed Aug 31 08:00:00 IDT 2011 | Thu Sep 29 17:00:00 IDT 2011
1595 | MTR's Comment & Approval for EDOC of Protection Works | Wed Aug 31 08:00:00 IDT 2011 | Fri Sep 23 17:00:00 IDT 2011
1596 | Circular Shaft Construction | Mon Feb 28 08:00:00 IST 2011 | Wed Jan 16 17:00:00 IST 2013
1597 | Area 37.3 Tree Transplant by 801 Designated Contrator | Mon Feb 28 08:00:00 IST 2011 | Mon Feb 28 08:00:00 IST 2011
1598 | Site Possession (Area 10.3) | Mon Mar 28 08:00:00 IST 2011 | Mon Mar 28 08:00:00 IST 2011
1599 | Set-up Plan & Hoarding Plan Submn & Approval | Mon Feb 28 08:00:00 IST 2011 | Tue Apr 12 17:00:00 IDT 2011
1600 | Site Setup & Hoarding Erection | Mon Feb 28 08:00:00 IST 2011 | Tue Mar 22 17:00:00 IST 2011
1601 | Install Instruments/Monitoring Stations | Mon Feb 28 08:00:00 IST 2011 | Sat Mar 19 17:00:00 IST 2011
1602 | Trial Trench to Locate Exist'g 400kV & StormDrain | Mon Mar 21 08:00:00 IST 2011 | Tue Apr 12 17:00:00 IDT 2011
1603 | Protection for 400kV & 600 dia.Storm Drain | Tue Jul 19 08:00:00 IDT 2011 | Sat Aug 20 17:00:00 IDT 2011
1604 | Drilling for Jet Grouting | Mon Aug 08 08:00:00 IDT 2011 | Thu Oct 27 17:00:00 IST 2011
1605 | Ground Treatment by Jet Grout | Wed Aug 31 08:00:00 IDT 2011 | Fri Sep 30 17:00:00 IDT 2011
1606 | Drilling for Fissure Grout | Wed Aug 31 08:00:00 IDT 2011 | Thu Sep 29 17:00:00 IDT 2011
1607 | Ground Treatment by Fissure Grout | Wed Aug 31 08:00:00 IDT 2011 | Wed Sep 28 17:00:00 IDT 2011
1608 | Bored Pile | Mon Jan 16 08:00:00 IST 2012 | Sat Feb 18 17:00:00 IST 2012
1609 | Install Internal Casing | Mon Jan 16 08:00:00 IST 2012 | Fri Jan 27 17:00:00 IST 2012
1610 | Concrete Water Plug | Mon Jan 16 08:00:00 IST 2012 | Tue Jan 17 17:00:00 IST 2012
1611 | Grouting & Extract External Casing | Mon Jan 16 08:00:00 IST 2012 | Tue Jan 17 17:00:00 IST 2012
1612 | Dewatering/ Pumping System | Mon Jan 16 08:00:00 IST 2012 | Fri Jan 20 17:00:00 IST 2012
1613 | Ventilation, Lighting System | Mon Jan 16 08:00:00 IST 2012 | Fri Jan 20 17:00:00 IST 2012
1614 | Setup Access Shaft | Mon Jan 16 08:00:00 IST 2012 | Fri Jan 20 17:00:00 IST 2012
1615 | Circular Shaft Const'n & Install Temp.Pumping System | Mon Aug 15 08:00:00 IDT 2011 | Wed Jan 16 17:00:00 IST 2013
1616 | Adit Construction | Mon Jan 16 08:00:00 IST 2012 | Tue Oct 09 17:00:00 IST 2012
1617 | Post Form Adit Opening | Mon Jan 16 08:00:00 IST 2012 | Fri Jan 20 17:00:00 IST 2012
1618 | Adit Excavation | Mon Jan 16 08:00:00 IST 2012 | Wed Feb 29 17:00:00 IST 2012
1619 | Lining for Adit | Wed Oct 03 08:00:00 IST 2012 | Tue Oct 09 17:00:00 IST 2012
1620 | Construction of Pipe Canopy | Wed Oct 10 08:00:00 IST 2012 | Fri Dec 21 17:00:00 IST 2012
1621 | Concrete Coring & Saw Cut for Sump Pit Wall | Wed Oct 10 08:00:00 IST 2012 | Tue Oct 16 17:00:00 IST 2012
1622 | Erection Temp. Props Support | Wed Oct 17 08:00:00 IST 2012 | Thu Oct 18 17:00:00 IST 2012
1623 | Enlarge Sump Pit Opening | Fri Oct 19 08:00:00 IST 2012 | Mon Oct 22 17:00:00 IST 2012
1624 | Erect Temporary Props | Wed Oct 24 08:00:00 IST 2012 | Tue Oct 30 17:00:00 IST 2012
1625 | Setup Pumping System | Wed Oct 31 08:00:00 IST 2012 | Tue Nov 06 17:00:00 IST 2012
1626 | Remove Existing Pumping System | Wed Nov 07 08:00:00 IST 2012 | Thu Nov 08 17:00:00 IST 2012
1627 | Mass Concrete for Drilling rig Platform | Fri Nov 09 08:00:00 IST 2012 | Mon Nov 12 17:00:00 IST 2012
1628 | Delivery and Setup Drillilng Rig | Tue Nov 13 08:00:00 IST 2012 | Mon Nov 19 17:00:00 IST 2012
1629 | Construction of Pipe Canopy | Tue Nov 20 08:00:00 IST 2012 | Fri Dec 21 17:00:00 IST 2012
1630 | Pipe Canopy Construction | Wed Oct 10 08:00:00 IST 2012 | Fri Dec 21 17:00:00 IST 2012
1631 | Modification of Existing Sump | Sat Dec 22 08:00:00 IST 2012 | Tue Jan 15 17:00:00 IST 2013
1632 | Strengthen Adit & Sump Opening Connection | Sat Dec 22 08:00:00 IST 2012 | Sat Dec 29 17:00:00 IST 2012
1633 | Install Prop above Slab Cut Line | Sat Dec 22 08:00:00 IST 2012 | Mon Dec 24 17:00:00 IST 2012
1634 | Saw Cut Pit Wall above Base Slab | Thu Dec 27 08:00:00 IST 2012 | Wed Jan 02 17:00:00 IST 2013
1635 | RC Base Slab Construction | Thu Jan 03 08:00:00 IST 2013 | Tue Jan 15 17:00:00 IST 2013
1636 | Modification of Existing Sump | Sat Dec 22 08:00:00 IST 2012 | Tue Jan 15 17:00:00 IST 2013
1637 | Reinstatement | Tue Nov 06 08:00:00 IST 2012 | Mon Apr 08 17:00:00 IDT 2013
1638 | Make Good Pit Wall | Wed Jan 16 08:00:00 IST 2013 | Tue Jan 22 17:00:00 IST 2013
1639 | GI at Sump Pit for TWL | Wed Jan 23 08:00:00 IST 2013 | Mon Feb 04 17:00:00 IST 2013
1640 | Reinstate Permanent Pump system | Tue Feb 05 08:00:00 IST 2013 | Tue Mar 05 17:00:00 IST 2013
1641 | Reinstate Pit Wall | Wed Mar 06 08:00:00 IST 2013 | Mon Mar 18 17:00:00 IST 2013
1642 | Backfill Adit & Shaft by Lean Concrete | Tue Nov 06 08:00:00 IST 2012 | Wed Nov 21 17:00:00 IST 2012
1643 | TWL Reinstatement | Wed Jan 16 08:00:00 IST 2013 | Mon Apr 08 17:00:00 IDT 2013
1644 | Completion | Tue Jul 02 08:00:00 IDT 2013 | Mon Jul 29 17:00:00 IDT 2013
1645 | Prepare & Submit Draft As-built Drawings | Tue Jul 02 08:00:00 IDT 2013 | Mon Jul 29 17:00:00 IDT 2013
1646 | Prepare & Submit As-built Drawings | Tue Jul 02 08:00:00 IDT 2013 | Mon Jul 29 17:00:00 IDT 2013
1647 | F2 Complete Lai Chi Kok Overpass New Concrete Beam | Mon Feb 28 08:00:00 IST 2011 | Wed Sep 25 17:00:00 IDT 2013
1648 | Method Statement Submission and Approval | Sun Jun 19 08:00:00 IDT 2011 | Tue Oct 04 17:00:00 IST 2011
1649 | MS Preparation for Underpinning | Sun Jun 19 08:00:00 IDT 2011 | Tue Oct 04 17:00:00 IST 2011
1650 | MS Submission to MTR/DSD | Wed Aug 31 08:00:00 IDT 2011 | Wed Aug 31 08:00:00 IDT 2011
1651 | MS Comment by MTR | Wed Aug 31 08:00:00 IDT 2011 | Fri Sep 23 17:00:00 IDT 2011
1652 | MS Re-submission Preparation | Wed Aug 31 08:00:00 IDT 2011 | Thu Sep 29 17:00:00 IDT 2011
1653 | MS Comment & Approval by MTR | Wed Aug 31 08:00:00 IDT 2011 | Tue Sep 27 17:00:00 IDT 2011
1654 | Issue for Construction | Wed Sep 28 17:00:00 IDT 2011 | Wed Sep 28 17:00:00 IDT 2011
1655 | TTM Scheme Submission & Approval | Mon Feb 28 08:00:00 IST 2011 | Thu Sep 29 17:00:00 IDT 2011
1656 | Prepare Temporary Traffic Management | Mon Feb 28 08:00:00 IST 2011 | Fri Mar 25 17:00:00 IST 2011
1657 | TTM reviewed by SLG | Sat Mar 26 08:00:00 IST 2011 | Sat Jun 18 17:00:00 IDT 2011
1658 | Resubmit TTM | Tue Jun 21 08:00:00 IDT 2011 | Mon Jun 27 17:00:00 IDT 2011
1659 | TTM reviewed by SLG | Tue Jun 28 08:00:00 IDT 2011 | Wed Jul 27 17:00:00 IDT 2011
1660 | Notification to RMO | Tue Jul 26 08:00:00 IDT 2011 | Mon Aug 01 17:00:00 IDT 2011
1661 | XP Application & Approval | Thu Jun 02 08:00:00 IDT 2011 | Fri Jun 17 17:00:00 IDT 2011
1662 | Implement TTM | Fri Aug 12 17:00:00 IDT 2011 | Fri Aug 12 17:00:00 IDT 2011
1663 | Traffic Diversion Works | Sat Aug 13 08:00:00 IDT 2011 | Thu Sep 29 17:00:00 IDT 2011
1664 | Design Submission & Approval | Mon Feb 28 08:00:00 IST 2011 | Wed Oct 12 17:00:00 IST 2011
1665 | Site Investigation | Wed Jun 01 08:00:00 IDT 2011 | Wed Oct 12 17:00:00 IST 2011
1666 | Prepare Temp.Work Design for Underpinning | Mon Feb 28 08:00:00 IST 2011 | Tue Jul 26 17:00:00 IDT 2011
1667 | Comment for Temp.Work Design Submission | Sun Jun 19 08:00:00 IDT 2011 | Thu Jul 07 17:00:00 IDT 2011
1668 | Proposed Temp.Work Design Re-submission | Wed Aug 31 08:00:00 IDT 2011 | Tue Sep 06 17:00:00 IDT 2011
1669 | Proposed Temp.Work Design Approval | Wed Aug 31 08:00:00 IDT 2011 | Wed Sep 21 17:00:00 IDT 2011
1670 | Utilities Coordination | Mon Feb 28 08:00:00 IST 2011 | Tue Jan 31 17:00:00 IST 2012
1671 | Prepare & Submit Utilities Diversion Scheme | Mon Feb 28 08:00:00 IST 2011 | Thu Mar 31 17:00:00 IST 2011
1672 | Comment of Utilities Diversion Scheme | Fri Apr 01 08:00:00 IDT 2011 | Mon May 23 17:00:00 IDT 2011
1673 | Utilities Diversion Scheme Re-submission | Fri Apr 29 08:00:00 IDT 2011 | Tue Jan 31 17:00:00 IST 2012
1674 | Utilities Diversion Scheme Approval | Wed Aug 31 08:00:00 IDT 2011 | Tue Sep 27 17:00:00 IDT 2011
1675 | Preparation Excavation Permit | Mon Apr 11 08:00:00 IDT 2011 | Fri Jun 17 17:00:00 IDT 2011
1676 | Excavation Permit Issue | Mon Jun 13 08:00:00 IDT 2011 | Mon Jun 13 08:00:00 IDT 2011
1677 | Site Possession Application | Mon Feb 28 08:00:00 IST 2011 | Tue Mar 29 17:00:00 IST 2011
1678 | Prepare Site Possession to SLG | Mon Feb 28 08:00:00 IST 2011 | Wed Mar 09 17:00:00 IST 2011
1679 | SLG Comments and Approval | Mon Feb 28 08:00:00 IST 2011 | Tue Mar 29 17:00:00 IST 2011
1680 | Site Possession | Mon Feb 28 08:00:00 IST 2011 | Mon Feb 28 08:00:00 IST 2011
1681 | Utilities Diversion | Wed Aug 31 08:00:00 IDT 2011 | Mon Feb 13 17:00:00 IST 2012
1682 | Trial Trench & Record | Wed Aug 31 08:00:00 IDT 2011 | Fri Sep 23 17:00:00 IDT 2011
1683 | Permanently Divert Existing Storm Drain (SD201-SD205) | Sat Sep 24 08:00:00 IDT 2011 | Mon Nov 21 17:00:00 IST 2011
1684 | Permanently Divert Existing DN150 (FW201) | Tue Nov 22 08:00:00 IST 2011 | Mon Dec 19 17:00:00 IST 2011
1685 | Temp. Relocation of Fire Hydrant (FH1643) | Tue Dec 20 08:00:00 IST 2011 | Thu Jan 12 17:00:00 IST 2012
1686 | Temp.Slew 3nos. 400kV Cable w/Temp.Support (CLP201) | Fri Jan 13 08:00:00 IST 2012 | Mon Feb 13 17:00:00 IST 2012
1687 | Utilities Diversion | Wed Aug 31 08:00:00 IDT 2011 | Wed Aug 31 08:00:00 IDT 2011
1688 | Underpinning Works for Pile Cap at Grid 3 | Mon Feb 28 08:00:00 IST 2011 | Mon Sep 16 17:00:00 IDT 2013
1689 | Tree Transplant (by 801) | Mon Feb 28 08:00:00 IST 2011 | Mon Mar 14 17:00:00 IST 2011
1690 | Site Mobilization | Sat Sep 24 08:00:00 IDT 2011 | Fri Sep 30 17:00:00 IDT 2011
1691 | Const.Raking Mini-piles 23 nos. | Wed Aug 31 08:00:00 IDT 2011 | Fri Dec 16 17:00:00 IST 2011
1692 | Sheetpile Driving | Mon Jan 16 08:00:00 IST 2012 | Wed Feb 01 17:00:00 IST 2012
1693 | Waling Installation | Mon Jan 16 08:00:00 IST 2012 | Sat Jan 21 17:00:00 IST 2012
1694 | Excavation to FormationLevel(Underneath Exist'gPileCap) | Mon Jan 16 08:00:00 IST 2012 | Sat Jan 28 17:00:00 IST 2012
1695 | Pile Head Exposure | Mon Jan 16 08:00:00 IST 2012 | Wed Feb 15 17:00:00 IST 2012
1696 | Pile Cap & Column Construction | Mon Jan 16 08:00:00 IST 2012 | Tue Jan 31 17:00:00 IST 2012
1697 | Portal Beam Construction | Fri Aug 31 08:00:00 IDT 2012 | Thu Sep 06 17:00:00 IDT 2012
1698 | Concrete Curing | Fri Sep 07 08:00:00 IDT 2012 | Sat Oct 20 17:00:00 IST 2012
1699 | Install Shear Key | Sat Oct 20 08:00:00 IST 2012 | Mon Oct 29 17:00:00 IST 2012
1700 | Install Flat Jack | Sat Oct 20 08:00:00 IST 2012 | Mon Nov 12 17:00:00 IST 2012
1701 | Load Transfer | Tue Nov 13 08:00:00 IST 2012 | Mon Dec 03 17:00:00 IST 2012
1702 | Disconnect Existing Pier | Mon Dec 03 08:00:00 IST 2012 | Sat Dec 22 17:00:00 IST 2012
1703 | Adjust Jacking Force | Fri Aug 31 08:00:00 IDT 2012 | Fri Sep 14 17:00:00 IDT 2012
1704 | Infill grout for pier head and existing pile cap | Mon Sep 24 08:00:00 IST 2012 | Sat Sep 29 17:00:00 IST 2012
1705 | Backfilling & Reinstatement | Mon Sep 02 08:00:00 IDT 2013 | Mon Sep 16 17:00:00 IDT 2013
1706 | Grid 3 Underpinning, Loading Transfer & Disconnection (DT) | Sat Sep 24 08:00:00 IDT 2011 | Tue Jul 03 17:00:00 IDT 2012
1707 | Underpinning Works for Pile Cap at Grid 2 | Mon Jan 16 08:00:00 IST 2012 | Mon Sep 16 17:00:00 IDT 2013
1708 | Const.Raking Mini-piles 21nos. | Mon Jan 16 08:00:00 IST 2012 | Fri May 11 17:00:00 IDT 2012
1709 | Sheetpile Driving | Mon Jan 16 08:00:00 IST 2012 | Wed Feb 01 17:00:00 IST 2012
1710 | Waling Installation | Mon Jan 16 08:00:00 IST 2012 | Sat Jan 21 17:00:00 IST 2012
1711 | Excavation | Mon Jan 16 08:00:00 IST 2012 | Sat Jan 28 17:00:00 IST 2012
1712 | Pile Head Exposure | Sat Jan 28 08:00:00 IST 2012 | Fri Feb 24 17:00:00 IST 2012
1713 | Pile Cap Construciton | Mon Jan 16 08:00:00 IST 2012 | Wed Feb 01 17:00:00 IST 2012
1714 | Coulumns Construction (2nos.) | Mon Jan 16 08:00:00 IST 2012 | Mon Jan 30 17:00:00 IST 2012
1715 | Falsework Erection | Tue Sep 11 08:00:00 IDT 2012 | Fri Sep 21 17:00:00 IDT 2012
1716 | Portal Beam Construction | Fri Sep 21 08:00:00 IDT 2012 | Sat Oct 06 17:00:00 IST 2012
1717 | Concrete Curing | Sat Oct 06 08:00:00 IST 2012 | Fri Oct 19 17:00:00 IST 2012
1718 | Install Shear Key | Sat Oct 20 08:00:00 IST 2012 | Sat Oct 27 17:00:00 IST 2012
1719 | Install Flat Jack | Sat Oct 27 08:00:00 IST 2012 | Fri Nov 16 17:00:00 IST 2012
1720 | Load Transfer | Fri Nov 16 08:00:00 IST 2012 | Thu Dec 06 17:00:00 IST 2012
1721 | Disconnect Existing pier | Thu Dec 06 08:00:00 IST 2012 | Fri Dec 28 17:00:00 IST 2012
1722 | Adjust Jacking Force | Fri Aug 31 08:00:00 IDT 2012 | Fri Sep 14 17:00:00 IDT 2012
1723 | Infill grout for pier head and existing pile cap | Mon Sep 24 08:00:00 IST 2012 | Sat Sep 29 17:00:00 IST 2012
1724 | Backfilling & Reinstatement | Mon Sep 02 08:00:00 IDT 2013 | Mon Sep 16 17:00:00 IDT 2013
1725 | Grid 2 Underpinning,Loading Transfer & Disconnection (UT) | Mon Jan 16 08:00:00 IST 2012 | Wed Aug 08 17:00:00 IDT 2012
1726 | Underpinning Works for Pile Cap at Grid 1 | Mon Jan 16 08:00:00 IST 2012 | Wed Sep 25 17:00:00 IDT 2013
1727 | Const piles | Mon Jan 16 08:00:00 IST 2012 | Tue May 15 17:00:00 IDT 2012
1728 | Loading Test | Mon Jan 16 08:00:00 IST 2012 | Wed Feb 15 17:00:00 IST 2012
1729 | Sheetpile Driving | Mon Jan 16 08:00:00 IST 2012 | Tue Feb 14 17:00:00 IST 2012
1730 | Waling Installation | Mon Jan 16 08:00:00 IST 2012 | Wed Feb 08 17:00:00 IST 2012
1731 | Excavation | Fri Aug 31 08:00:00 IDT 2012 | Fri Sep 14 17:00:00 IDT 2012
1732 | Shotcrete | Sat Sep 15 08:00:00 IDT 2012 | Tue Oct 09 17:00:00 IST 2012
1733 | Pile Head Exposure | Wed Oct 10 08:00:00 IST 2012 | Wed Nov 07 17:00:00 IST 2012
1734 | Pile Cap & Cantilever Corbel Construction | Thu Nov 08 08:00:00 IST 2012 | Wed Dec 05 17:00:00 IST 2012
1735 | Concrete Curing (28d) | Wed Dec 05 08:00:00 IST 2012 | Tue Jan 01 17:00:00 IST 2013
1736 | Install Flat Jack | Wed Jan 02 08:00:00 IST 2013 | Tue Jan 22 17:00:00 IST 2013
1737 | Load Transfer | Tue Jan 22 08:00:00 IST 2013 | Thu Jan 31 17:00:00 IST 2013
1738 | Disconnect Existing Piles 6nos. | Thu Jan 31 08:00:00 IST 2013 | Sat Mar 02 17:00:00 IST 2013
1739 | Adjust Jacking Force | Sat Mar 02 08:00:00 IST 2013 | Fri Mar 22 17:00:00 IST 2013
1740 | Cast remaining part of pile cap | Sat Mar 23 08:00:00 IST 2013 | Thu Apr 18 17:00:00 IDT 2013
1741 | Backfilling & Reinstatement | Mon Sep 02 08:00:00 IDT 2013 | Wed Sep 25 17:00:00 IDT 2013
1742 | Grid 1 Underpinning,Loading Transfer & Disconnection (UT) | Mon Jan 16 08:00:00 IST 2012 | Wed Aug 01 17:00:00 IDT 2012
1743 | Completion | Tue Mar 06 08:00:00 IST 2012 | Mon Apr 02 17:00:00 IDT 2012
1744 | Prepare & Submit Draft As-built Drawings | Tue Mar 06 08:00:00 IST 2012 | Mon Apr 02 17:00:00 IDT 2012
1745 | Prepare & Submit As-built Drawings | Tue Mar 06 08:00:00 IST 2012 | Mon Apr 02 17:00:00 IDT 2012
1746 | RD1 Pile Removal | Mon Jan 16 08:00:00 IST 2012 | Fri Feb 03 17:00:00 IST 2012
1747 | RD1 Parallel Seismic | Mon Jan 16 08:00:00 IST 2012 | Tue Jan 17 17:00:00 IST 2012
1748 | Issuance of EI21 - Additional Investigation Drill hole above Nullah Deck at LCK | Mon Jan 16 17:00:00 IST 2012 | Mon Jan 16 17:00:00 IST 2012
1749 | Pile A - 1st Investigation Campaign | Mon Jan 16 08:00:00 IST 2012 | Thu Jan 19 17:00:00 IST 2012
1750 | Issuance of EI24 - Additional Investigation Drillhole at existing pile above Nullah Deck at LCK | Mon Jan 16 17:00:00 IST 2012 | Mon Jan 16 17:00:00 IST 2012
1751 | Pile B - 1st Investigation Campaign | Mon Jan 16 08:00:00 IST 2012 | Tue Jan 17 17:00:00 IST 2012
1752 | Issuance of EI31 - Additional attempts of vertical drillholes and inclined drillholes at existing Pile of RD1 | Mon Jan 16 17:00:00 IST 2012 | Mon Jan 16 17:00:00 IST 2012
1753 | Pile B - 2nd Investigation Campaign | Mon Jan 16 08:00:00 IST 2012 | Sat Jan 21 17:00:00 IST 2012
1754 | Pile B - 3rd Investigation Campaign (inclined holes) | Mon Jan 16 08:00:00 IST 2012 | Fri Feb 03 17:00:00 IST 2012
1755 | F3 Ground Treatment Works for HKIVE (Haking Wong) School | Wed Aug 31 08:00:00 IDT 2011 | Wed Oct 31 17:00:00 IST 2012
1756 | Method Statement Submission and Approval | Wed Aug 31 08:00:00 IDT 2011 | Wed Sep 28 17:00:00 IDT 2011
1757 | MS Preparation | Wed Aug 31 08:00:00 IDT 2011 | Fri Sep 23 17:00:00 IDT 2011
1758 | MS Submission to MTR | Wed Aug 31 08:00:00 IDT 2011 | Wed Aug 31 08:00:00 IDT 2011
1759 | MS Comment by MTR | Wed Aug 31 08:00:00 IDT 2011 | Tue Sep 27 17:00:00 IDT 2011
1760 | MS Re-submission Preparation | Wed Aug 31 08:00:00 IDT 2011 | Wed Sep 28 17:00:00 IDT 2011
1761 | MS Comment & Approval by MTR | Wed Aug 31 08:00:00 IDT 2011 | Tue Sep 27 17:00:00 IDT 2011
1762 | Issue for Construction | Wed Aug 31 08:00:00 IDT 2011 | Wed Aug 31 08:00:00 IDT 2011
1763 | Construction | Sun Jan 15 08:00:00 IST 2012 | Wed Oct 31 17:00:00 IST 2012
1764 | Access for HKIVE | Sun Jan 15 08:00:00 IST 2012 | Sun Jan 15 08:00:00 IST 2012
1765 | Site Preparation | Mon Jan 16 08:00:00 IST 2012 | Sat Jan 21 17:00:00 IST 2012
1766 | Sleeve Pipe Installation and Verticality Check | Mon Jan 16 08:00:00 IST 2012 | Fri Feb 10 17:00:00 IST 2012
1767 | Set up Grouting Machine | Mon Jan 16 08:00:00 IST 2012 | Wed Jan 18 17:00:00 IST 2012
1768 | Jet Grouting for HKIVE (Haking Wong) School | Mon Jan 16 08:00:00 IST 2012 | Fri Feb 10 17:00:00 IST 2012
1769 | De-mobilization | Fri Aug 31 08:00:00 IDT 2012 | Fri Sep 14 17:00:00 IDT 2012
1770 | Reinstatment (subjected to IVE) | Sat Sep 15 08:00:00 IDT 2012 | Wed Oct 31 17:00:00 IST 2012
1771 | F4 Cheung Sha Wan Cargo Pier-Remvoe Obstruct Pile | Sat Jan 08 08:00:00 IST 2011 | Wed May 08 17:00:00 IDT 2013
1772 | Method Statement Submission and Approval | Mon Feb 28 08:00:00 IST 2011 | Tue Jun 21 17:00:00 IDT 2011
1773 | MS Preparation | Mon Feb 28 08:00:00 IST 2011 | Tue Apr 05 17:00:00 IDT 2011
1774 | MS Submission to MTR | Wed Mar 23 17:00:00 IST 2011 | Wed Mar 23 17:00:00 IST 2011
1775 | MS Comment by MTR | Thu Mar 24 08:00:00 IST 2011 | Wed Apr 20 17:00:00 IDT 2011
1776 | MS Re-submission Preparation | Thu Apr 21 08:00:00 IDT 2011 | Sat May 14 17:00:00 IDT 2011
1777 | MS Comment & Approval by MTR | Wed May 25 08:00:00 IDT 2011 | Wed Jun 15 17:00:00 IDT 2011
1778 | Issue for Construction | Tue Jun 21 17:00:00 IDT 2011 | Tue Jun 21 17:00:00 IDT 2011
1779 | TTM Scheme Submission & Approval | Sat Jan 08 08:00:00 IST 2011 | Sun Aug 14 17:00:00 IDT 2011
1780 | Prepare TTM for footpah closure | Sat Jan 08 08:00:00 IST 2011 | Mon Feb 07 17:00:00 IST 2011
1781 | TTM Comment & Approval by Relevant Authorities | Sat Feb 12 08:00:00 IST 2011 | Sun Apr 10 17:00:00 IDT 2011
1782 | Notification to RMO | Mon Feb 28 08:00:00 IST 2011 | Sun Mar 06 17:00:00 IST 2011
1783 | XP Application & Approval | Mon Feb 28 08:00:00 IST 2011 | Wed Apr 06 17:00:00 IDT 2011
1784 | Implement TTM (Footpath) | Wed May 18 17:00:00 IDT 2011 | Wed May 18 17:00:00 IDT 2011
1785 | Prepare Temporary Traffic Management | Mon Feb 28 08:00:00 IST 2011 | Thu Mar 24 17:00:00 IST 2011
1786 | TTM reviewed by SLG | Sun Mar 27 08:00:00 IST 2011 | Mon May 23 17:00:00 IDT 2011
1787 | XP Application & Approval | Sat Apr 23 08:00:00 IDT 2011 | Fri Apr 29 17:00:00 IDT 2011
1788 | Notification to RMO | Tue Aug 09 08:00:00 IDT 2011 | Sun Aug 14 17:00:00 IDT 2011
1789 | Implement TTM (Road) | Wed Jul 06 17:00:00 IDT 2011 | Wed Jul 06 17:00:00 IDT 2011
1790 | Utilities Diversion (DT) | Sat Jan 29 08:00:00 IST 2011 | Mon Oct 17 17:00:00 IST 2011
1791 | Implement TTM | Sat Jan 29 08:00:00 IST 2011 | Wed Mar 09 17:00:00 IST 2011
1792 | Trial Trench to Expose Pile Head & Utilities | Tue Jun 21 08:00:00 IDT 2011 | Fri Jul 22 17:00:00 IDT 2011
1793 | Divert Existing 1400D Watermain (FW204) | Tue Jun 21 08:00:00 IDT 2011 | Wed Sep 07 17:00:00 IDT 2011
1794 | Divert 450D Saltwater Main (SW201) | Tue Jun 21 08:00:00 IDT 2011 | Mon Jul 18 17:00:00 IDT 2011
1795 | Divert 1200D Stormwater Main (SD207) | Wed Aug 31 08:00:00 IDT 2011 | Mon Oct 17 17:00:00 IST 2011
1796 | Divert 225D Stormwater Drain (SD208) | Tue Jun 21 08:00:00 IDT 2011 | Fri Aug 26 17:00:00 IDT 2011
1797 | Stage 1 | Sat Jan 08 08:00:00 IST 2011 | Mon Mar 19 17:00:00 IST 2012
1798 | Access Date for Works Area 11.22 | Mon Feb 28 08:00:00 IST 2011 | Mon Feb 28 08:00:00 IST 2011
1799 | Tree Transplant Complete by 801 Designated Contractor | Mon Feb 28 08:00:00 IST 2011 | Mon Feb 28 08:00:00 IST 2011
1800 | Survey Existing Piles & Underground Utilities | Sat Jan 08 08:00:00 IST 2011 | Fri May 13 17:00:00 IDT 2011
1801 | Expose the Existing Pile Head | Sat May 21 08:00:00 IDT 2011 | Fri Nov 25 17:00:00 IST 2011
1802 | Expose and Verification of Pile 24E (DT) | Fri Jan 20 08:00:00 IST 2012 | Sat Jan 28 17:00:00 IST 2012
1803 | Remove Existing Vertical Pile 24H (DT) | Tue Jun 21 08:00:00 IDT 2011 | Mon Aug 29 17:00:00 IDT 2011
1804 | Backfill Existing Pile 24H | Sat Jul 16 08:00:00 IDT 2011 | Thu Jul 21 17:00:00 IDT 2011
1805 | Remove Existing Raking Pile 24G (DT) | Tue Jun 21 08:00:00 IDT 2011 | Wed Jul 27 17:00:00 IDT 2011
1806 | Backfill Existing Pile 24G | Wed Aug 31 08:00:00 IDT 2011 | Fri Sep 02 17:00:00 IDT 2011
1807 | Remove Existing Raking Pile 23F (DT) | Wed Aug 31 08:00:00 IDT 2011 | Fri Oct 07 17:00:00 IST 2011
1808 | Backfill Existing Pile 23F | Fri Jan 27 08:00:00 IST 2012 | Sat Jan 28 17:00:00 IST 2012
1809 | Remove Existing Vertical Pile 23E (DT) | Mon Sep 12 08:00:00 IDT 2011 | Sat Jan 14 17:00:00 IST 2012
1810 | Backfill Existing Pile 23E | Tue Feb 07 08:00:00 IST 2012 | Wed Feb 08 17:00:00 IST 2012
1811 | Remove Existing Raking Pile 24F (DT) | Fri Feb 10 08:00:00 IST 2012 | Tue Mar 06 17:00:00 IST 2012
1812 | Backfill Existing Pile 24F | Sat Mar 17 08:00:00 IST 2012 | Mon Mar 19 17:00:00 IST 2012
1813 | Utilities Diversion (UT) | Sat Jan 08 08:00:00 IST 2011 | Fri Dec 21 17:00:00 IST 2012
1814 | Implement TTM (Footpath Closure) | Sat Jan 08 08:00:00 IST 2011 | Mon Feb 21 17:00:00 IST 2011
1815 | Trial Trench to Expose U/G Utilities | Tue Jun 21 08:00:00 IDT 2011 | Thu Jul 07 17:00:00 IDT 2011
1816 | Divert Existing Gas Main 315D & 400D (GAS204&205) | Wed Aug 31 08:00:00 IDT 2011 | Fri Sep 23 17:00:00 IDT 2011
1817 | Slew TelecomCable(CATV205+HGC203+WTT204+PCCW202) | Fri Jan 27 08:00:00 IST 2012 | Tue Feb 07 17:00:00 IST 2012
1818 | Slew CLP Cable (11kV-CLP213) | Fri Jan 27 08:00:00 IST 2012 | Thu Feb 09 17:00:00 IST 2012
1819 | Slew CLP Cable (400kV-CLP214) | Thu Nov 22 08:00:00 IST 2012 | Fri Dec 21 17:00:00 IST 2012
1820 | Stage 2 | Tue Jun 21 08:00:00 IDT 2011 | Wed May 08 17:00:00 IDT 2013
1821 | Remove Existing Pile 23G (UT) | Tue Jun 21 08:00:00 IDT 2011 | Mon Jul 04 17:00:00 IDT 2011
1822 | Backfill Existing Pile 23G | Wed Aug 31 08:00:00 IDT 2011 | Thu Sep 01 17:00:00 IDT 2011
1823 | Remove Existing Pile 20E (UT) | Thu Dec 13 08:00:00 IST 2012 | Fri Jan 18 17:00:00 IST 2013
1824 | Backfill Existing Pile 20E | Sat Jan 19 08:00:00 IST 2013 | Mon Jan 21 17:00:00 IST 2013
1825 | Remove Existing Pile 23H (UT) | Thu Nov 22 08:00:00 IST 2012 | Sat Dec 08 17:00:00 IST 2012
1826 | Backfill Existing Pile 23H | Mon Dec 10 08:00:00 IST 2012 | Tue Dec 11 17:00:00 IST 2012
1827 | Remove Existing Pile 21L (UT) | Sat Apr 14 08:00:00 IDT 2012 | Tue Jul 17 17:00:00 IDT 2012
1828 | Backfill Existing Pile 21L | Mon Nov 19 08:00:00 IST 2012 | Tue Nov 20 17:00:00 IST 2012
1829 | Remove Existing Pile 20J (UT) | Wed Jan 23 08:00:00 IST 2013 | Thu Feb 28 17:00:00 IST 2013
1830 | Backfill Existing Pile 20J | Fri Mar 01 08:00:00 IST 2013 | Sat Mar 02 17:00:00 IST 2013
1831 | Remove Existing Pile 19E (UT) | Tue Mar 05 08:00:00 IST 2013 | Sat Apr 13 17:00:00 IDT 2013
1832 | Backfill Existing Pile 19E | Mon Apr 15 08:00:00 IDT 2013 | Tue Apr 16 17:00:00 IDT 2013
1833 | Reinstatement of Slewed CLP Cable (400kV - CLP214) | Tue Apr 02 08:00:00 IDT 2013 | Wed May 08 17:00:00 IDT 2013
1834 | Reinstatement works
1835 | Completion | Fri Jan 13 08:00:00 IST 2012 | Mon Feb 13 17:00:00 IST 2012
1836 | Prepare & Submit Draft As-built Drawings | Fri Jan 13 08:00:00 IST 2012 | Mon Feb 13 17:00:00 IST 2012
1837 | Prepare & Submit As-built Drawings | Fri Jan 13 08:00:00 IST 2012 | Mon Feb 13 17:00:00 IST 2012
1838 | F5 Pile Removal for Demolished FMO Market Pier B | Mon Feb 28 08:00:00 IST 2011 | Thu Jun 05 17:00:00 IDT 2014
1839 | Temp. Works Design Submission | Mon Jun 20 08:00:00 IDT 2011 | Mon Jul 18 08:00:00 IDT 2011
1840 | Temp. Works Design Preparation | Mon Jun 20 08:00:00 IDT 2011 | Sun Jul 17 17:00:00 IDT 2011
1841 | Temp. Works Design Submit to MTR | Mon Jul 18 08:00:00 IDT 2011 | Mon Jul 18 08:00:00 IDT 2011
1842 | Temp. Works Design Comment by MTR | Mon Jun 20 08:00:00 IDT 2011 | Sun Jul 17 17:00:00 IDT 2011
1843 | Temp. Works Design Re-submission Preparation | Mon Jun 20 08:00:00 IDT 2011 | Mon Jul 11 17:00:00 IDT 2011
1844 | Temp. Works Design Comment & Approval by MTR | Mon Jun 20 08:00:00 IDT 2011 | Sun Jul 17 17:00:00 IDT 2011
1845 | Issue for Construction | Mon Jun 20 08:00:00 IDT 2011 | Mon Jun 20 08:00:00 IDT 2011
1846 | Method Statement Submission and Approval | Mon Feb 28 08:00:00 IST 2011 | Tue Jun 14 17:00:00 IDT 2011
1847 | MS Preparation | Mon Feb 28 08:00:00 IST 2011 | Thu Mar 31 17:00:00 IST 2011
1848 | MS Submission to MTR | Wed Mar 23 17:00:00 IST 2011 | Wed Mar 23 17:00:00 IST 2011
1849 | MS Comment by MTR | Thu Mar 24 08:00:00 IST 2011 | Sun Apr 03 17:00:00 IDT 2011
1850 | MS Re-submission Preparation | Thu Apr 21 08:00:00 IDT 2011 | Fri Apr 29 17:00:00 IDT 2011
1851 | MS Comment & Approval by MTR | Wed May 18 08:00:00 IDT 2011 | Mon May 30 17:00:00 IDT 2011
1852 | Issue for Construction | Tue Jun 14 17:00:00 IDT 2011 | Tue Jun 14 17:00:00 IDT 2011
1853 | TTM Scheme Submission & Approval | Mon Feb 28 08:00:00 IST 2011 | Sun May 29 17:00:00 IDT 2011
1854 | Prepare Temporary Traffic Management | Mon Feb 28 08:00:00 IST 2011 | Mon Mar 14 17:00:00 IST 2011
1855 | TTM reviewed by SLG | Sat Mar 26 08:00:00 IST 2011 | Sun Apr 24 17:00:00 IDT 2011
1856 | Resubmit TTM | Mon Feb 28 08:00:00 IST 2011 | Mon Feb 28 17:00:00 IST 2011
1857 | TTM reviewed by SLG | Sat Apr 30 08:00:00 IDT 2011 | Sun May 29 17:00:00 IDT 2011
1858 | Notification to RMO | Tue May 24 08:00:00 IDT 2011 | Fri May 27 17:00:00 IDT 2011
1859 | XP Application & Approval | Mon Apr 25 08:00:00 IDT 2011 | Tue May 24 17:00:00 IDT 2011
1860 | Implement TTM | Mon Feb 28 08:00:00 IST 2011 | Mon Feb 28 08:00:00 IST 2011
1861 | Construction | Mon Feb 28 08:00:00 IST 2011 | Thu Jun 05 17:00:00 IDT 2014
1862 | Acccess Dates for Works Area 11.27 | Mon Feb 28 08:00:00 IST 2011 | Mon Feb 28 08:00:00 IST 2011
1863 | TTM Implementation | Mon Feb 28 08:00:00 IST 2011 | Mon Mar 28 17:00:00 IST 2011
1864 | Relocation of Toilet/Bus Operator Office | Mon Feb 28 08:00:00 IST 2011 | Sat Mar 26 17:00:00 IST 2011
1865 | Bus Stop Modification Stage 1 | Mon Feb 28 08:00:00 IST 2011 | Mon Mar 14 17:00:00 IST 2011
1866 | Bus Stop Modification Stage 2 | Mon Feb 28 08:00:00 IST 2011 | Fri Mar 04 17:00:00 IST 2011
1867 | Road Kerb Removal | Mon Feb 28 08:00:00 IST 2011 | Fri Mar 11 17:00:00 IST 2011
1868 | Trial Trench for Expose U/G Utilities | Mon Feb 28 08:00:00 IST 2011 | Tue Mar 22 17:00:00 IST 2011
1869 | Expose the Existing Pile Heads | Thu Apr 21 08:00:00 IDT 2011 | Wed May 18 17:00:00 IDT 2011
1870 | Backfill | Mon Feb 28 08:00:00 IST 2011 | Sat Mar 05 17:00:00 IST 2011
1871 | 1 Vertical Pile Removal UT(3G) | Mon Feb 28 08:00:00 IST 2011 | Wed Mar 02 17:00:00 IST 2011
1872 | 1 Vertical Pile Removal UT(1G) | Mon Feb 28 08:00:00 IST 2011 | Thu Mar 03 17:00:00 IST 2011
1873 | 1 Vertical Pile Removal UT(3H) | Wed Aug 31 08:00:00 IDT 2011 | Thu Sep 15 17:00:00 IDT 2011
1874 | 1 Vertical Pile Removal UT(1H) | Wed Aug 31 08:00:00 IDT 2011 | Thu Sep 15 17:00:00 IDT 2011
1875 | 1 Raking Pile Removal UT (2Fa) | Wed Aug 31 08:00:00 IDT 2011 | Mon Sep 26 17:00:00 IDT 2011
1876 | 4 Raking Pile Removal DT(2Ja,2Ha,2Hb & 2Gb) | Wed Aug 31 08:00:00 IDT 2011 | Wed Dec 07 17:00:00 IST 2011
1877 | PTI Reinstatement | Fri Feb 21 08:00:00 IST 2014 | Thu Jun 05 17:00:00 IDT 2014
1878 | FMO Pier B Piles Removal (4nos.) (DT) | Fri May 27 08:00:00 IDT 2011 | Sun Jun 24 17:00:00 IDT 2012
1879 | FMO Pier B Piles Removal (5nos.) (UT) | Fri May 27 08:00:00 IDT 2011 | Fri Feb 17 17:00:00 IST 2012
1880 | Completion | Thu Mar 15 08:00:00 IST 2012 | Mon Apr 16 17:00:00 IDT 2012
1881 | Prepare & Submit Draft As-built Drawings (PTI) | Thu Mar 15 08:00:00 IST 2012 | Mon Apr 16 17:00:00 IDT 2012
1882 | Prepare & Submit As-built Drawings (PTI) | Thu Mar 15 08:00:00 IST 2012 | Mon Apr 16 17:00:00 IDT 2012
1883 | F6 Sham Shui Po Ferry Pier - Pile removal | Mon Feb 28 08:00:00 IST 2011 | Thu Nov 07 17:00:00 IST 2013
1884 | Temp. Works Design Submission | Mon Feb 28 08:00:00 IST 2011 | Tue Jul 19 17:00:00 IDT 2011
1885 | Temp. Works Design Preparation | Mon Feb 28 08:00:00 IST 2011 | Wed Mar 30 17:00:00 IST 2011
1886 | Temp. Works Design Submit to MTR | Mon Mar 28 08:00:00 IST 2011 | Mon Mar 28 08:00:00 IST 2011
1887 | Temp. Works Design Comment by MTR | Mon Mar 28 08:00:00 IST 2011 | Tue Jul 19 17:00:00 IDT 2011
1888 | Temp. Works Design Re-submission Preparation | Tue Apr 26 08:00:00 IDT 2011 | Fri May 20 17:00:00 IDT 2011
1889 | Temp. Works Design Comment & Approval by MTR | Thu May 19 08:00:00 IDT 2011 | Sat Jun 04 17:00:00 IDT 2011
1890 | Issue for Construction | Wed Jun 15 17:00:00 IDT 2011 | Wed Jun 15 17:00:00 IDT 2011
1891 | Method Statement Submission and Approval | Mon Feb 28 08:00:00 IST 2011 | Wed Aug 31 08:00:00 IDT 2011
1892 | MS Submission Preparation | Wed Mar 16 08:00:00 IST 2011 | Wed Apr 06 17:00:00 IDT 2011
1893 | MS Submission to MTR | Wed Apr 13 17:00:00 IDT 2011 | Wed Apr 13 17:00:00 IDT 2011
1894 | MS Comment by MTR | Mon Feb 28 08:00:00 IST 2011 | Wed Mar 09 17:00:00 IST 2011
1895 | MS Re-submission Preparation | Mon Feb 28 08:00:00 IST 2011 | Sat Apr 16 17:00:00 IDT 2011
1896 | MS Comment & Approval by MTR | Mon Feb 28 08:00:00 IST 2011 | Mon Aug 01 17:00:00 IDT 2011
1897 | Issue for Construction | Wed Aug 31 08:00:00 IDT 2011 | Wed Aug 31 08:00:00 IDT 2011
1898 | TTM Scheme Submission & Approval | Mon Feb 28 08:00:00 IST 2011 | Mon Aug 08 17:00:00 IDT 2011
1899 | Prepare Temp.Traffic Mgmt for Tree Transplant | Mon Feb 28 08:00:00 IST 2011 | Wed Apr 13 17:00:00 IDT 2011
1900 | TTM Comment & Approval by Relevant Authorities | Thu Apr 14 08:00:00 IDT 2011 | Fri May 13 17:00:00 IDT 2011
1901 | Notification to RMO | Fri Jul 08 08:00:00 IDT 2011 | Mon Aug 08 17:00:00 IDT 2011
1902 | Implement TTM | Tue Jul 19 17:00:00 IDT 2011 | Tue Jul 19 17:00:00 IDT 2011
1903 | Stage 0 | Mon Feb 28 08:00:00 IST 2011 | Thu Nov 10 17:00:00 IST 2011
1904 | Group B TreeTransplant(T9746,U0019-24)Preparat'n | Wed Jul 20 08:00:00 IDT 2011 | Mon Aug 29 17:00:00 IDT 2011
1905 | Group D Tree Transplant (U0023) Preparation | Wed Jul 20 08:00:00 IDT 2011 | Mon Aug 29 17:00:00 IDT 2011
1906 | Access Date for Works Area 11.21 | Mon Feb 28 08:00:00 IST 2011 | Mon Feb 28 08:00:00 IST 2011
1907 | Stage 0 TTA | Mon Feb 28 08:00:00 IST 2011 | Wed Mar 30 17:00:00 IST 2011
1908 | Tree Transplanting | Thu Oct 06 08:00:00 IST 2011 | Thu Nov 10 17:00:00 IST 2011
1909 | Kerb & Footpath Removal | Tue Mar 29 08:00:00 IST 2011 | Wed May 11 17:00:00 IDT 2011
1910 | Pavement Excavation and Expose Underground Utilities | Wed Apr 06 08:00:00 IDT 2011 | Wed May 18 17:00:00 IDT 2011
1911 | Agree Diversion Scheme with CLP for 132kV | Mon Jun 20 08:00:00 IDT 2011 | Fri Jun 24 17:00:00 IDT 2011
1912 | Stage 0 Enabling Work | Mon Feb 28 08:00:00 IST 2011 | Mon Aug 29 17:00:00 IDT 2011
1913 | Stage 1 | Sun Jun 19 08:00:00 IDT 2011 | Sat Nov 02 17:00:00 IST 2013
1914 | Extended TTMs Application & Approval | Mon Jun 20 08:00:00 IDT 2011 | Thu Jun 30 17:00:00 IDT 2011
1915 | Stage 1 Extended TTMs Implementation | Sun Jun 19 08:00:00 IDT 2011 | Fri Jul 15 17:00:00 IDT 2011
1916 | Remove Retaining Wall for Watermain Diversion | Tue Jun 21 08:00:00 IDT 2011 | Tue Aug 09 17:00:00 IDT 2011
1917 | Prepare Trench for 132kV Diversion | Sat Jul 02 08:00:00 IDT 2011 | Fri Aug 12 17:00:00 IDT 2011
1918 | Divert 1400D Fresh Watermain (FW205) | Wed Aug 31 08:00:00 IDT 2011 | Thu Dec 22 17:00:00 IST 2011
1919 | Divert 600D Salt Watermain (SW202) | Sun Jan 15 08:00:00 IST 2012 | Tue Mar 13 17:00:00 IST 2012
1920 | Joint Bay Construction & Laying New Cable by CLP (132kV Diversion) | Sun Jan 15 08:00:00 IST 2012 | Fri Feb 17 17:00:00 IST 2012
1921 | Power Outage & Connection by CLP (132kV Diversion) | Sun Jan 15 08:00:00 IST 2012 | Wed Mar 07 17:00:00 IST 2012
1922 | Mobilization for Pile Removal | Fri Aug 31 08:00:00 IDT 2012 | Tue Sep 04 17:00:00 IDT 2012
1923 | Remove the Existing Vertical Piles @ GL.1 - DT(11nos.) | Mon Sep 03 08:00:00 IDT 2012 | Sat Nov 10 17:00:00 IST 2012
1924 | Remove the Existing Vertical Piles @ GL.2 - DT(11nos.) | Wed Sep 05 08:00:00 IDT 2012 | Tue Nov 13 17:00:00 IST 2012
1925 | Agree with WSD for reinstatement of diverted 1400D FW main (FW205) | Wed Nov 14 08:00:00 IST 2012 | Mon Feb 04 17:00:00 IST 2013
1926 | Reinstate diverted 1400D FW main (FW205) | Thu Feb 28 08:00:00 IST 2013 | Wed Mar 27 17:00:00 IST 2013
1927 | Temporary Road Reinstatement | Sat Oct 12 08:00:00 IDT 2013 | Sat Nov 02 17:00:00 IST 2013
1928 | Stage 1 Piles Removal (22nos.) (DT) | Sun Jun 19 08:00:00 IDT 2011 | Sat May 26 17:00:00 IDT 2012
1929 | Stage 2 | Wed Nov 28 08:00:00 IST 2012 | Thu Nov 07 17:00:00 IST 2013
1930 | Stage 2 TTM Implementation | Fri Mar 29 08:00:00 IDT 2013 | Sun Apr 14 17:00:00 IDT 2013
1931 | Divert 1200D Foul Sewer Drain (FD202) | Mon Apr 15 08:00:00 IDT 2013 | Mon May 13 17:00:00 IDT 2013
1932 | Remove the Existing 12 Piles (UT) @GL.4 | Tue May 14 08:00:00 IDT 2013 | Wed Jul 31 17:00:00 IDT 2013
1933 | Divert 900D Stormwater Drain (SD214) | Mon Aug 05 08:00:00 IDT 2013 | Wed Sep 04 17:00:00 IDT 2013
1934 | Remove the Existing 10 Piles (UT) @GL.5 | Wed Nov 28 08:00:00 IST 2012 | Mon Jan 28 17:00:00 IST 2013
1935 | Permanent Road Reinstatement | Mon Jan 07 08:00:00 IST 2013 | Thu May 09 17:00:00 IDT 2013
1936 | Stage 2 Piles Removal (20nos.) (UT) | Fri Mar 29 08:00:00 IDT 2013 | Thu Nov 07 17:00:00 IST 2013
1937 | Completion | Wed May 02 08:00:00 IDT 2012 | Tue May 29 17:00:00 IDT 2012
1938 | Prepare & Submit Draft As-built Drawings | Wed May 02 08:00:00 IDT 2012 | Tue May 29 17:00:00 IDT 2012
1939 | Prepare & Submit As-built Drawings | Wed May 02 08:00:00 IDT 2012 | Tue May 29 17:00:00 IDT 2012
1940 | Cost Centre G - Utility Diversion Works | Sat Aug 14 08:00:00 IDT 2010 | Sat Oct 10 17:00:00 IDT 2015
1941 | IPS Milestones | Sun Mar 27 17:00:00 IST 2011 | Tue Oct 29 17:00:00 IST 2013
1942 | General | Sun Mar 27 17:00:00 IST 2011 | Tue Oct 29 17:00:00 IST 2013
1943 | Complete Temp. Diversion of Box Culvert FS1 | Fri Sep 30 17:00:00 IDT 2011 | Fri Sep 30 17:00:00 IDT 2011
1944 | Complete Thrust Block for North Temp.DSD Rising Main | Sun Mar 27 17:00:00 IST 2011 | Sun Mar 27 17:00:00 IST 2011
1945 | Remove Pile for DSD Rising Main adj. TBM Launch Shaft | Sun Jan 15 08:00:00 IST 2012 | Sun Jan 15 08:00:00 IST 2012
1946 | Complete Removal of 60% of Obstruction Piles for WD1 | Fri Aug 31 08:00:00 IDT 2012 | Fri Aug 31 08:00:00 IDT 2012
1947 | Remove Barrettes for DSD Culvert NC1 | Fri Mar 23 17:00:00 IST 2012 | Fri Mar 23 17:00:00 IST 2012
1948 | Complete Box Culvert WD1 Reinstate Wk & Handover | Tue Oct 29 17:00:00 IST 2013 | Tue Oct 29 17:00:00 IST 2013
1949 | G4 DSD Culvert WD1 Potential Obstruction | Tue Dec 14 08:00:00 IST 2010 | Tue Oct 29 17:00:00 IST 2013
1950 | Obstruction Removal at 1.1m Dia.Sewer Pipe Area (UT) | Tue Dec 14 08:00:00 IST 2010 | Tue Dec 14 08:00:00 IST 2010
1951 | Obstruction Removal at 1.1m Dia.Sewer Pipe Area (DT) | Fri Jul 22 08:00:00 IDT 2011 | Wed Apr 18 17:00:00 IDT 2012
1952 | Obstruction Removal at 1.8m Dia.Sewer Pipe Area (DT) | Wed Aug 31 08:00:00 IDT 2011 | Mon May 28 17:00:00 IDT 2012
1953 | WD1 Piles Removal (P1,P3 & P9) (UT) | Sun Mar 13 08:00:00 IST 2011 | Thu Jul 07 17:00:00 IDT 2011
1954 | WD1Pre-bored Socket H-piles & Pile Cap (5nos..) | Tue Jun 21 08:00:00 IDT 2011 | Sun Oct 23 17:00:00 IST 2011
1955 | WD1 Piles Removal (P4,P6,P7 & P8) (UT) | Fri Apr 13 08:00:00 IDT 2012 | Wed Feb 27 17:00:00 IST 2013
1956 | Diversion Scheme Submission | Mon Feb 28 08:00:00 IST 2011 | Mon Aug 01 17:00:00 IDT 2011
1957 | Prepare Diversion Scheme Proposal | Mon Feb 28 08:00:00 IST 2011 | Tue Apr 26 17:00:00 IDT 2011
1958 | Comment of Diversion Scheme by DSD | Tue Apr 12 08:00:00 IDT 2011 | Sun Apr 17 17:00:00 IDT 2011
1959 | Proposed Diversion Scheme Re-subm'n | Wed May 11 08:00:00 IDT 2011 | Thu Jun 02 17:00:00 IDT 2011
1960 | Proposed Diversion Scheme Approval by DSD | Wed May 25 08:00:00 IDT 2011 | Mon Aug 01 17:00:00 IDT 2011
1961 | Method Statement Submission and Approval | Sat Jan 08 08:00:00 IST 2011 | Fri May 13 17:00:00 IDT 2011
1962 | MS Preparation for WDI Obstruction Removal | Sat Jan 08 08:00:00 IST 2011 | Tue Feb 08 17:00:00 IST 2011
1963 | MS Submission to MTR | Thu Mar 03 17:00:00 IST 2011 | Thu Mar 03 17:00:00 IST 2011
1964 | MS Comment by MTR | Fri Mar 04 08:00:00 IST 2011 | Tue Mar 22 17:00:00 IST 2011
1965 | MS Re-submission Preparation | Fri Apr 01 08:00:00 IDT 2011 | Fri Apr 08 17:00:00 IDT 2011
1966 | MS Comment & Approval by MTR | Sat Apr 16 08:00:00 IDT 2011 | Sun May 08 17:00:00 IDT 2011
1967 | Issue for Construction | Fri May 13 17:00:00 IDT 2011 | Fri May 13 17:00:00 IDT 2011
1968 | Temp.works Design Submission | Mon Feb 28 08:00:00 IST 2011 | Mon Aug 01 17:00:00 IDT 2011
1969 | Prepare Temp.Gate & Working Platform Proposal | Mon Feb 28 08:00:00 IST 2011 | Tue Apr 26 17:00:00 IDT 2011
1970 | Comment of Temp.Gate& Working Platform byRDO/DSD | Tue Apr 12 08:00:00 IDT 2011 | Sun Apr 17 17:00:00 IDT 2011
1971 | Proposed Temp.Gate & Working Platform Re-subm'n | Wed May 11 08:00:00 IDT 2011 | Thu Jun 02 17:00:00 IDT 2011
1972 | Proposed Temp.Gate& WorkingPlatf'mApp'l /RDO&DSD | Wed May 25 08:00:00 IDT 2011 | Mon Aug 01 17:00:00 IDT 2011
1973 | TTM Scheme Submission & Approval | Sat Jan 08 08:00:00 IST 2011 | Sat Jul 09 17:00:00 IDT 2011
1974 | Prepare Temp.Pedestrian Walkway Diversion Scheme | Sat Jan 08 08:00:00 IST 2011 | Fri Jan 21 17:00:00 IST 2011
1975 | Temp.Pedestrian Walkway Approval by SLG/HyD/etc. | Sat Jan 22 08:00:00 IST 2011 | Sun Apr 03 17:00:00 IDT 2011
1976 | Notification to RMO | Sat Apr 16 08:00:00 IDT 2011 | Thu Apr 21 17:00:00 IDT 2011
1977 | Implement for Temp.Pederstrian Walkway | Wed Apr 27 17:00:00 IDT 2011 | Wed Apr 27 17:00:00 IDT 2011
1978 | Prepare Temporary Traffic Management | Sat Jan 08 08:00:00 IST 2011 | Tue Feb 08 17:00:00 IST 2011
1979 | TTM reviewed by SLG | Wed Feb 09 08:00:00 IST 2011 | Thu Mar 03 17:00:00 IST 2011
1980 | Resubmit TTM | Wed May 04 08:00:00 IDT 2011 | Wed May 11 17:00:00 IDT 2011
1981 | TTM reviewed by SLG | Fri May 13 08:00:00 IDT 2011 | Sat Jun 11 17:00:00 IDT 2011
1982 | Notification to RMO | Sat Jun 11 08:00:00 IDT 2011 | Sat Jul 09 17:00:00 IDT 2011
1983 | XP Application & Approval | Mon Feb 28 08:00:00 IST 2011 | Mon Mar 14 17:00:00 IST 2011
1984 | Implement TTM | Tue Jun 28 17:00:00 IDT 2011 | Tue Jun 28 17:00:00 IDT 2011
1985 | Prepare Temp.TrafficManagem't for TreeTransplant | Sat Jan 08 08:00:00 IST 2011 | Tue Feb 08 17:00:00 IST 2011
1986 | TTM reviewed by SLG | Wed Feb 09 08:00:00 IST 2011 | Mon May 23 17:00:00 IDT 2011
1987 | Notification to RMO | Thu May 05 08:00:00 IDT 2011 | Sun May 08 17:00:00 IDT 2011
1988 | Proposed Culvert New Founding System | Mon Feb 28 08:00:00 IST 2011 | Tue Sep 27 17:00:00 IDT 2011
1989 | Prepare & Submit Culvert New Founding System | Mon Feb 28 08:00:00 IST 2011 | Fri Mar 11 17:00:00 IST 2011
1990 | Comment of Culvert New Founding System byRDO/DSD | Tue Apr 12 08:00:00 IDT 2011 | Tue Apr 26 17:00:00 IDT 2011
1991 | Culvert New Founding System Re-submission | Tue May 24 08:00:00 IDT 2011 | Tue Sep 27 17:00:00 IDT 2011
1992 | Culvert New Founding System Approval by RDO/DSD | Wed Jun 08 08:00:00 IDT 2011 | Wed Jul 27 17:00:00 IDT 2011
1993 | Site Possession Application | Mon Feb 28 08:00:00 IST 2011 | Mon Jun 06 08:00:00 IDT 2011
1994 | Apply Site Possession to SLG | Mon Feb 28 08:00:00 IST 2011 | Sat Mar 05 17:00:00 IST 2011
1995 | SLG Comments & Approval | Sun Mar 06 08:00:00 IST 2011 | Tue Mar 29 17:00:00 IST 2011
1996 | TGLA Comments & Approval | Tue Mar 29 08:00:00 IST 2011 | Sat Jun 04 17:00:00 IDT 2011
1997 | Site Possession | Mon Jun 06 08:00:00 IDT 2011 | Mon Jun 06 08:00:00 IDT 2011
1998 | Utilities Coordination | Mon Feb 28 08:00:00 IST 2011 | Thu Jun 30 17:00:00 IDT 2011
1999 | Prepare & Submit Utilities Diversion Scheme | Mon Feb 28 08:00:00 IST 2011 | Thu Mar 31 17:00:00 IST 2011
2000 | Comment of Utilities Diversion Scheme | Fri Apr 01 08:00:00 IDT 2011 | Thu Apr 28 17:00:00 IDT 2011
2001 | Utilities Diversion Scheme Re-submission | Fri Apr 29 08:00:00 IDT 2011 | Sat May 14 17:00:00 IDT 2011
2002 | Utilities Diversion Scheme Approval | Sun May 15 08:00:00 IDT 2011 | Thu Jun 30 17:00:00 IDT 2011
2003 | Preparation Excavation Permit | Mon Apr 11 08:00:00 IDT 2011 | Fri Jun 10 17:00:00 IDT 2011
2004 | Excavation Permit Issue | Mon Jun 13 08:00:00 IDT 2011 | Mon Jun 13 08:00:00 IDT 2011
2005 | Power Cable & Fresh Water Main | Sat Jan 08 08:00:00 IST 2011 | Wed Oct 31 17:00:00 IST 2012
2006 | GI works for WD1 | Sat Jan 08 08:00:00 IST 2011 | Wed Jun 01 17:00:00 IDT 2011
2007 | Site Mobilization | Tue Jun 07 08:00:00 IDT 2011 | Wed Jul 06 17:00:00 IDT 2011
2008 | Temp.Working Platform | Thu Jun 23 08:00:00 IDT 2011 | Tue Aug 23 17:00:00 IDT 2011
2009 | Temp.Traffic Diversion(Pedestrian Walkway) | Mon Feb 28 08:00:00 IST 2011 | Fri Mar 11 17:00:00 IST 2011
2010 | Trial Trench & Record | Mon Jun 13 08:00:00 IDT 2011 | Sat Aug 20 17:00:00 IDT 2011
2011 | Slew 400KV Cable(CLP204)& 2Sets of 11KV(CLP205) | Sat Jul 02 08:00:00 IDT 2011 | Mon Oct 10 17:00:00 IST 2011
2012 | Slew Tele Cables (PCCW204+HKBN201) | Wed Aug 24 08:00:00 IDT 2011 | Mon Aug 29 17:00:00 IDT 2011
2013 | Cosnt.Temp.300mm dia.WaterMain (FW203) | Mon Feb 20 08:00:00 IST 2012 | Tue Mar 27 17:00:00 IST 2012
2014 | Water Main Diversion (FW203) | Mon Jan 16 08:00:00 IST 2012 | Mon Jan 16 08:00:00 IST 2012
2015 | Slew 400KV & 2 Sets 11KV Cables Reinstatement | Sat Sep 01 08:00:00 IDT 2012 | Wed Oct 17 17:00:00 IST 2012
2016 | Remove Temp.Support for 400KV &11KV Cables | Wed Oct 17 08:00:00 IST 2012 | Wed Oct 31 17:00:00 IST 2012
2017 | Reinstate 300mmdia Fresh Water Main (FW203) | Sat Sep 01 08:00:00 IDT 2012 | Wed Oct 10 17:00:00 IST 2012
2018 | Remove Temp.300mm dia.Fresh Water Meter (FW203) | Thu Oct 11 08:00:00 IST 2012 | Thu Oct 25 17:00:00 IST 2012
2019 | Remove Temp.Support for Temp.Fresh Water Main | Thu Oct 25 08:00:00 IST 2012 | Wed Oct 31 17:00:00 IST 2012
2020 | 1.1m Dia. Sewer Pipe Diversion | Tue Dec 14 08:00:00 IST 2010 | Fri Mar 01 17:00:00 IST 2013
2021 | Coord'n w/DSD forTemp.Removal ofOverflow Pipe | Mon Jan 16 08:00:00 IST 2012 | Mon Jan 16 08:00:00 IST 2012
2022 | Trial Trench & Record | Wed Aug 31 08:00:00 IDT 2011 | Fri Sep 30 17:00:00 IDT 2011
2023 | Sheet Piles Cofferdam 1A | Fri Jul 22 08:00:00 IDT 2011 | Mon Oct 03 17:00:00 IST 2011
2024 | Expose and Protect 400mm dia.Gas Main (GAS211) | Thu Sep 08 08:00:00 IDT 2011 | Tue Oct 11 17:00:00 IST 2011
2025 | Drilling | Mon Jan 16 08:00:00 IST 2012 | Tue Jan 31 17:00:00 IST 2012
2026 | Grouting for MH-1 | Mon Jan 16 08:00:00 IST 2012 | Sat Jan 21 17:00:00 IST 2012
2027 | Excavate for dewatering well and place blinding | Mon Jan 16 08:00:00 IST 2012 | Thu Jan 19 17:00:00 IST 2012
2028 | Excavate for MH-1 Construction & Shoring Installation | Thu Mar 01 08:00:00 IST 2012 | Sat Mar 24 17:00:00 IST 2012
2029 | Construct MH-1 Stage 1 & pump test | Mon Sep 17 08:00:00 IDT 2012 | Fri Sep 28 17:00:00 IST 2012
2030 | Insert DN800 temp pipe and fill gap between temp pipe & DN1800 | Sat Sep 29 08:00:00 IST 2012 | Sat Oct 06 17:00:00 IST 2012
2031 | Installation of by-pass pipe, benching & Inspection | Mon Oct 08 08:00:00 IST 2012 | Mon Oct 15 17:00:00 IST 2012
2032 | Drilling | Mon Jan 16 08:00:00 IST 2012 | Sat Jan 21 17:00:00 IST 2012
2033 | Grouting for MH-2 | Mon Jan 16 08:00:00 IST 2012 | Sat Jan 28 17:00:00 IST 2012
2034 | Excavate for dewatering well and place blinding | Mon Jan 16 08:00:00 IST 2012 | Fri Jan 20 17:00:00 IST 2012
2035 | Excavate for MH-2 Construction & Shoring Installation | Mon Jan 16 08:00:00 IST 2012 | Fri Feb 17 17:00:00 IST 2012
2036 | Construct MH-2 Stage 1 & pump test | Thu Oct 04 08:00:00 IST 2012 | Mon Oct 15 17:00:00 IST 2012
2037 | Insert DN800 temp pipe and fill gap between temp pipe & DN1800 | Tue Oct 16 08:00:00 IST 2012 | Sat Oct 20 17:00:00 IST 2012
2038 | Installation of by-pass pipe, benching & Inspection | Sat Oct 20 08:00:00 IST 2012 | Mon Oct 29 17:00:00 IST 2012
2039 | Excavate for pipe laying between MH-1 to MH-2 & Shoring Installation | Tue Mar 06 08:00:00 IST 2012 | Thu Apr 19 17:00:00 IDT 2012
2040 | Pipe Laying, air test and concrete surround | Fri Oct 12 08:00:00 IST 2012 | Fri Oct 26 17:00:00 IST 2012
2041 | Diversion | Tue Oct 30 08:00:00 IST 2012 | Fri Nov 02 17:00:00 IST 2012
2042 | Backfill to 2nd layer waling and construct remaining part of manholes MH-1 & MH-2 | Fri Nov 02 08:00:00 IST 2012 | Tue Nov 20 17:00:00 IST 2012
2043 | Remove 1st layer waling and backfill to ground level | Wed Nov 21 08:00:00 IST 2012 | Sat Nov 24 17:00:00 IST 2012
2044 | Install Casing & Remove Piles (3nos at D/T) | Mon Nov 26 08:00:00 IST 2012 | Mon Dec 24 17:00:00 IST 2012
2045 | Install Casing & Remove Piles (4nos at U/T) | Fri Jan 11 08:00:00 IST 2013 | Fri Mar 01 17:00:00 IST 2013
2046 | Backfilling & Reinstate Road Surface | Fri Nov 23 08:00:00 IST 2012 | Mon Jan 07 17:00:00 IST 2013
2047 | Obstruction Removal at 1.1m Dia.Sewer Pipe Area (DT) | Fri Jul 22 08:00:00 IDT 2011 | Wed Apr 18 17:00:00 IDT 2012
2048 | Obstruction Removal at 1.1m Dia.Sewer Pipe Area (UT) | Tue Dec 14 08:00:00 IST 2010 | Tue Dec 14 08:00:00 IST 2010
2049 | 1.8m Dia. Sewer Pipe Diversion | Sat Jan 08 08:00:00 IST 2011 | Sat Nov 10 17:00:00 IST 2012
2050 | Group E Tree Transplant (T9605) Preparation Works | Sat Jan 08 08:00:00 IST 2011 | Sat Jul 02 17:00:00 IDT 2011
2051 | Group D Tree Transplant (T9603 & T9604) Preparation Works | Sat Jan 08 08:00:00 IST 2011 | Wed Jun 22 17:00:00 IDT 2011
2052 | Group B Tree Transplant (U0010) Preparation Works | Mon Feb 28 08:00:00 IST 2011 | Mon May 23 17:00:00 IDT 2011
2053 | Group D Tree Transplant (U0018) Preparation Works | Mon Feb 28 08:00:00 IST 2011 | Thu Aug 11 17:00:00 IDT 2011
2054 | Group E Tree Transplant (T9601&T9602)Preparation Works | Mon Feb 28 08:00:00 IST 2011 | Mon Aug 22 17:00:00 IDT 2011
2055 | Trial Trench & Record | Wed Aug 31 08:00:00 IDT 2011 | Fri Sep 30 17:00:00 IDT 2011
2056 | Construct Cofferdam 2: MH-4, excavate to formation level and place blinding layer | Wed Aug 31 08:00:00 IDT 2011 | Mon Dec 05 17:00:00 IST 2011
2057 | Slew 400KV (CLP221)+11kV (CLP222) w/Temp.Support | Mon Jan 16 08:00:00 IST 2012 | Sat Jan 21 17:00:00 IST 2012
2058 | Pipe Formation preparation | Thu Feb 09 08:00:00 IST 2012 | Wed Feb 15 17:00:00 IST 2012
2059 | Sewage Pipe Laying with concrete surround (btw MH-3 to MH-4) | Wed Feb 01 08:00:00 IST 2012 | Thu Feb 09 17:00:00 IST 2012
2060 | Construct Manhole - Stage 1 | Mon Jan 16 08:00:00 IST 2012 | Fri Jan 20 17:00:00 IST 2012
2061 | BreakDN1800 pipe top | Sat Jan 28 08:00:00 IST 2012 | Mon Jan 30 17:00:00 IST 2012
2062 | Construct Manhole - Stage 2 & pump test | Wed Feb 01 08:00:00 IST 2012 | Thu Feb 02 17:00:00 IST 2012
2063 | Insert Temp Pipe and Filling gap between temp pipe & DN1800 | Wed Feb 22 08:00:00 IST 2012 | Sat Feb 25 17:00:00 IST 2012
2064 | Installation of by-pass pipe, benching & inspection | Wed Feb 22 08:00:00 IST 2012 | Tue Feb 28 17:00:00 IST 2012
2065 | Diversion | Wed Jan 18 08:00:00 IST 2012 | Sat Jan 21 17:00:00 IST 2012
2066 | Make good manhole wall at original pipe opening | Fri Aug 31 08:00:00 IDT 2012 | Tue Sep 04 17:00:00 IDT 2012
2067 | Demolish pile cap and expose existing obstruction pile | Wed Sep 05 08:00:00 IDT 2012 | Fri Sep 07 17:00:00 IDT 2012
2068 | Backfill to 2nd layer waling and construct remaining part of manhole | Sat Sep 08 08:00:00 IDT 2012 | Tue Sep 25 17:00:00 IST 2012
2069 | Remove 1st layer waling and backfill to ground level | Wed Sep 26 08:00:00 IST 2012 | Fri Oct 05 17:00:00 IST 2012
2070 | Remove 1 no. of dia. 500 pile | Sat Oct 06 08:00:00 IST 2012 | Wed Oct 17 17:00:00 IST 2012
2071 | Construct Cofferdam 1B: MH-3, excavate to formation level and place blinding layer | Wed Aug 31 08:00:00 IDT 2011 | Mon Dec 05 17:00:00 IST 2011
2072 | Construct Manhole - Stage 1 & pump test | Wed Feb 01 08:00:00 IST 2012 | Mon Feb 13 17:00:00 IST 2012
2073 | Insert Temp Pipe and Filling gap between temp pipe & DN1800 | Wed Feb 01 08:00:00 IST 2012 | Sat Feb 04 17:00:00 IST 2012
2074 | Installation of by-pass pipe, benching & inspection | Wed Feb 22 08:00:00 IST 2012 | Tue Feb 28 17:00:00 IST 2012
2075 | Diversion | Wed Jan 18 08:00:00 IST 2012 | Sat Jan 21 17:00:00 IST 2012
2076 | Make good manhole wall at original pipe opening | Fri Aug 31 08:00:00 IDT 2012 | Tue Sep 04 17:00:00 IDT 2012
2077 | Demolish pile cap and expose existing obstruction pile | Wed Sep 05 08:00:00 IDT 2012 | Fri Sep 07 17:00:00 IDT 2012
2078 | Install guide steel liner | Sat Sep 08 08:00:00 IDT 2012 | Wed Sep 12 17:00:00 IDT 2012
2079 | Backfill to 2nd layer waling and construct remaining part of manhole | Thu Sep 13 08:00:00 IDT 2012 | Sat Sep 29 17:00:00 IST 2012
2080 | Remove 1st layer waling and backfill to ground level | Wed Oct 03 08:00:00 IST 2012 | Sat Oct 13 17:00:00 IST 2012
2081 | Remove 2 no. of dia. 500 pile | Thu Oct 18 08:00:00 IST 2012 | Sat Nov 10 17:00:00 IST 2012
2082 | Obstruction Removal at 1.8m Dia.Sewer Pipe Area (DT) | Wed Aug 31 08:00:00 IDT 2011 | Mon May 28 17:00:00 IDT 2012
2083 | Removal of Piles: P1 to P3 & P9 | Sat Mar 12 08:00:00 IST 2011 | Thu Mar 08 17:00:00 IST 2012
2084 | Open Cut to Expose Top Slab of Culvert Partially | Tue Nov 01 08:00:00 IST 2011 | Thu Nov 03 17:00:00 IST 2011
2085 | Break Top Slab of Box Culvert | Fri Nov 04 08:00:00 IST 2011 | Tue Jan 31 17:00:00 IST 2012
2086 | Install Temp.Working Platform & Cofferdam | Tue Jun 21 08:00:00 IDT 2011 | Tue Jul 05 17:00:00 IDT 2011
2087 | Mobilization | Mon Nov 07 08:00:00 IST 2011 | Fri Jan 13 17:00:00 IST 2012
2088 | Install Casing & Remove Pile: P1 | Tue Nov 01 08:00:00 IST 2011 | Wed Nov 16 17:00:00 IST 2011
2089 | Fill LeanConcrete &Reinstate BottomSlab for P1 | Tue Nov 01 08:00:00 IST 2011 | Sat Nov 26 17:00:00 IST 2011
2090 | Shift Temp.Cofferdam & Remove Pile: P2 | Sat Mar 12 08:00:00 IST 2011 | Tue Apr 12 17:00:00 IDT 2011
2091 | Fill Lean Concrete & Reinstate BottomSlab for P2 | Tue Nov 01 08:00:00 IST 2011 | Tue Dec 06 17:00:00 IST 2011
2092 | Install Temp. Cofferdam & Remove Pile: P3 | Thu Jan 19 08:00:00 IST 2012 | Wed Feb 01 17:00:00 IST 2012
2093 | Fill Lean Concrete & Reinstate BottomSlab for P3 | Thu Feb 09 08:00:00 IST 2012 | Thu Mar 08 17:00:00 IST 2012
2094 | Implement TTM | Tue Jun 28 17:00:00 IDT 2011 | Tue Jun 28 17:00:00 IDT 2011
2095 | Modification Works for Temp.Traffic Diversion | Wed Jun 29 08:00:00 IDT 2011 | Tue Nov 01 17:00:00 IST 2011
2096 | Install Casing & Remove Pile: P9 | Mon Mar 14 08:00:00 IST 2011 | Fri Nov 25 17:00:00 IST 2011
2097 | Fill Lean Concrete & Reinstate BottomSlab for P9 | Tue Nov 01 08:00:00 IST 2011 | Fri Nov 18 17:00:00 IST 2011
2098 | WD1 Piles Removal (P1,P3 & P9) (UT) | Sun Mar 13 08:00:00 IST 2011 | Thu Jul 07 17:00:00 IDT 2011
2099 | Removal of Piles: P4 to P6 & P7 &P8 | Tue Jun 21 08:00:00 IDT 2011 | Wed Feb 27 17:00:00 IST 2013
2100 | Working Platform for Prebore H Piles | Tue Jun 21 08:00:00 IDT 2011 | Thu Jul 14 17:00:00 IDT 2011
2101 | Install 5 nos.Pre-bored Socket H-piles | Tue Jun 21 08:00:00 IDT 2011 | Tue Jul 12 17:00:00 IDT 2011
2102 | Sheet Pile for Cofferdam | Fri Jul 22 08:00:00 IDT 2011 | Thu Aug 18 17:00:00 IDT 2011
2103 | Bulk Excqavation to Expose Top Slab of Culvert | Tue Jun 21 08:00:00 IDT 2011 | Sat Jul 02 17:00:00 IDT 2011
2104 | Place Concrete Block Wall | Tue Jun 21 08:00:00 IDT 2011 | Wed Jun 22 17:00:00 IDT 2011
2105 | Waling Installtion | Wed Aug 31 08:00:00 IDT 2011 | Wed Sep 21 17:00:00 IDT 2011
2106 | Blinding Slab | Wed Aug 31 08:00:00 IDT 2011 | Fri Sep 02 17:00:00 IDT 2011
2107 | Demolish TopSlab above PilesP1~ P3 & P9 | Wed Aug 31 08:00:00 IDT 2011 | Wed Sep 14 17:00:00 IDT 2011
2108 | Formwork & Planking | Wed Aug 31 08:00:00 IDT 2011 | Thu Sep 08 17:00:00 IDT 2011
2109 | Reinstate Top Slab and Corbel Beams | Wed Aug 31 08:00:00 IDT 2011 | Thu Oct 06 17:00:00 IST 2011
2110 | Concrete Curing | Sat Jan 28 08:00:00 IST 2012 | Fri Feb 24 17:00:00 IST 2012
2111 | Installation of Jacks | Sat Feb 25 08:00:00 IST 2012 | Sat Mar 03 17:00:00 IST 2012
2112 | Slew 400kV Cable to P1 to P3 | Mon Feb 06 08:00:00 IST 2012 | Thu Feb 16 17:00:00 IST 2012
2113 | Divert Watermain (FW203) | Mon Feb 20 08:00:00 IST 2012 | Sat Feb 25 17:00:00 IST 2012
2114 | Water Suspension & Connection | Sat Feb 25 08:00:00 IST 2012 | Fri Mar 02 17:00:00 IST 2012
2115 | Backfilling | Fri Mar 02 08:00:00 IST 2012 | Thu Mar 08 17:00:00 IST 2012
2116 | Excavation to Expose P4 to P8 | Thu Mar 08 08:00:00 IST 2012 | Wed Mar 21 17:00:00 IST 2012
2117 | Installation of Concrete Block Wall | Wed Mar 21 08:00:00 IST 2012 | Wed Apr 11 17:00:00 IDT 2012
2118 | Saw Cut Roof over P4 to P6, P7 & P8 | Fri Apr 13 08:00:00 IDT 2012 | Sat May 05 17:00:00 IDT 2012
2119 | Install Temp.Working Platform & Cofferdam of Work Area | Mon Jan 16 08:00:00 IST 2012 | Thu Jan 26 17:00:00 IST 2012
2120 | Install Casing & Remove Piles: P5 | Thu Nov 01 08:00:00 IST 2012 | Wed Dec 05 17:00:00 IST 2012
2121 | Fill Lean Concrete& Reinstate BottomSlab forP5 | Thu Nov 29 08:00:00 IST 2012 | Sat Dec 01 17:00:00 IST 2012
2122 | Shift Temp.Cofferdam & Remove Pile: P4 | Sat Dec 01 08:00:00 IST 2012 | Wed Dec 19 17:00:00 IST 2012
2123 | Fill Lean Concrete & Reinstate BottomSlab for P4 | Mon Nov 19 08:00:00 IST 2012 | Wed Nov 21 17:00:00 IST 2012
2124 | Shift Temp.Cofferdam & Remove Piles: P8 | Mon Dec 17 08:00:00 IST 2012 | Mon Jan 14 17:00:00 IST 2013
2125 | Fill Lean Concrete & Reinstate BottomSlab for P8 | Thu Jan 17 08:00:00 IST 2013 | Sat Jan 19 17:00:00 IST 2013
2126 | Shift Temp.Cofferdam & Remove Piles: P6 | Sat Jan 05 08:00:00 IST 2013 | Mon Feb 04 17:00:00 IST 2013
2127 | Fill Lean Concrete & Reinstate BottomSlab for P6 | Sat Feb 02 08:00:00 IST 2013 | Tue Feb 05 17:00:00 IST 2013
2128 | Shift Temp.Cofferdam & Remove Piles: P7 | Mon Jan 21 08:00:00 IST 2013 | Fri Feb 01 17:00:00 IST 2013
2129 | Fill Lean Concrete & Reinstate BottomSlab for P7 | Mon Feb 25 08:00:00 IST 2013 | Wed Feb 27 17:00:00 IST 2013
2130 | WD1Pre-bored Socket H-piles & Pile Cap (5nos..) | Tue Jun 21 08:00:00 IDT 2011 | Sun Oct 23 17:00:00 IST 2011
2131 | WD1 Piles Removal (P4,P6,P7 & P8) (UT) | Fri Apr 13 08:00:00 IDT 2012 | Sat Jan 19 17:00:00 IST 2013
2132 | Reinstatement | Fri Aug 31 08:00:00 IDT 2012 | Tue Oct 29 17:00:00 IST 2013
2133 | Reinstate Box Culvert (Invert & Roof) | Fri Aug 31 08:00:00 IDT 2012 | Mon Feb 04 17:00:00 IST 2013
2134 | Reinstate Road & Utilities | Thu Aug 01 08:00:00 IDT 2013 | Fri Aug 30 17:00:00 IDT 2013
2135 | DSD Inspection and Hand Over | Wed Oct 23 08:00:00 IDT 2013 | Tue Oct 29 17:00:00 IST 2013
2136 | Completion | Fri Jun 01 08:00:00 IDT 2012 | Fri Jun 29 17:00:00 IDT 2012
2137 | Prepare & Submit Draft As-built Drawings | Fri Jun 01 08:00:00 IDT 2012 | Fri Jun 29 17:00:00 IDT 2012
2138 | Prepare & Submit As-built Drawings | Fri Jun 01 08:00:00 IDT 2012 | Fri Jun 29 17:00:00 IDT 2012
2139 | G5 Rising Main Diversion & FMO Pier A Pile Remvoal | Mon Feb 28 08:00:00 IST 2011 | Fri Jul 31 17:00:00 IDT 2015
2140 | Rising Main & FMO Pier A Pile Removal (DT) | Sun Mar 13 08:00:00 IST 2011 | Sat Jan 05 17:00:00 IST 2013
2141 | Rising Main & FMO Pier A Pile Removal (UT) | Sun Mar 13 08:00:00 IST 2011 | Sat Sep 07 17:00:00 IDT 2013
2142 | Method Statement Submission and Approval | Mon Apr 04 08:00:00 IDT 2011 | Fri May 13 17:00:00 IDT 2011
2143 | MS Preparation | Mon Apr 04 08:00:00 IDT 2011 | Wed May 04 17:00:00 IDT 2011
2144 | MS Submission to MTR | Fri Apr 15 17:00:00 IDT 2011 | Fri Apr 15 17:00:00 IDT 2011
2145 | MS Comment & Approval by MTR | Sat Apr 16 08:00:00 IDT 2011 | Sat May 07 17:00:00 IDT 2011
2146 | Issue for Construction | Fri May 13 17:00:00 IDT 2011 | Fri May 13 17:00:00 IDT 2011
2147 | Temp. Works Design Submission | Mon Feb 28 08:00:00 IST 2011 | Wed Oct 05 17:00:00 IST 2011
2148 | Prepare Diversion Scheme to DSD | Mon Feb 28 08:00:00 IST 2011 | Sun Apr 03 17:00:00 IDT 2011
2149 | Propose Diversion Scheme to DSD | Mon Apr 04 08:00:00 IDT 2011 | Mon Apr 04 08:00:00 IDT 2011
2150 | No objection from DSD | Mon Apr 04 08:00:00 IDT 2011 | Fri Jul 08 17:00:00 IDT 2011
2151 | Prepare Temporary Work Design for Cofferdam | Sat Mar 12 08:00:00 IST 2011 | Mon May 16 17:00:00 IDT 2011
2152 | Temp. Works Design Comment & Approval by MTR/DSD | Tue Apr 19 08:00:00 IDT 2011 | Sat Jun 18 17:00:00 IDT 2011
2153 | Issue for Construction (Cofferdam) | Mon May 16 17:00:00 IDT 2011 | Mon May 16 17:00:00 IDT 2011
2154 | Prepare Design for DSD Main Support/Detailed Scheme | Fri Apr 08 08:00:00 IDT 2011 | Sat May 14 17:00:00 IDT 2011
2155 | DSD Main Support Approval by MTR/DSD | Sat May 14 08:00:00 IDT 2011 | Fri Jul 08 17:00:00 IDT 2011
2156 | Issue for Construction | Fri Jun 10 17:00:00 IDT 2011 | Fri Jun 10 17:00:00 IDT 2011
2157 | Pipe/Fitting Procurement | Sat Jun 11 08:00:00 IDT 2011 | Wed Oct 05 17:00:00 IST 2011
2158 | Construction | Mon Feb 28 08:00:00 IST 2011 | Fri Jul 31 17:00:00 IDT 2015
2159 | Cofferdam Reinstatement | Sat Mar 29 08:00:00 IDT 2014 | Thu Jun 19 17:00:00 IDT 2014
2160 | GI works for Rising Main Pile Removal | Mon Feb 28 08:00:00 IST 2011 | Sat Mar 19 17:00:00 IST 2011
2161 | Trial Trench for Existing Utilities | Tue Apr 19 08:00:00 IDT 2011 | Wed May 18 17:00:00 IDT 2011
2162 | Slew Telecom Cable (PCCW702+CATV704) | Sat Apr 30 08:00:00 IDT 2011 | Thu May 12 17:00:00 IDT 2011
2163 | Ground Treatment for Existing Seawall, if any | Tue May 17 08:00:00 IDT 2011 | Wed May 25 17:00:00 IDT 2011
2164 | Sheetpile Installation | Sat May 21 08:00:00 IDT 2011 | Sat Jun 04 17:00:00 IDT 2011
2165 | Northern Rising Main: Install Prebored H-pile (10nos.) | Tue Jun 14 08:00:00 IDT 2011 | Sat Jul 23 17:00:00 IDT 2011
2166 | Southern Rising Main: install Prebored H-pile (10nos.) | Tue Jun 14 08:00:00 IDT 2011 | Sat Jul 23 17:00:00 IDT 2011
2167 | Pile Testing | Mon Aug 01 08:00:00 IDT 2011 | Sat Aug 06 17:00:00 IDT 2011
2168 | Excavate & Expose Bottom of Rising Main (Trial Trench) | Mon Aug 01 08:00:00 IDT 2011 | Mon Aug 22 17:00:00 IDT 2011
2169 | Locate Existing Rising Main & FMO (A) Piles | Mon Aug 08 08:00:00 IDT 2011 | Sat Aug 20 17:00:00 IDT 2011
2170 | Removal FMO Pier A Vertical Piles D/T & Backfilling | Tue Aug 16 08:00:00 IDT 2011 | Thu Aug 25 17:00:00 IDT 2011
2171 | Removal Pier A Vertical Piles U/T & Backfilling | Thu Aug 25 08:00:00 IDT 2011 | Wed Aug 31 17:00:00 IDT 2011
2172 | Excavate to Capping Beam Formation Level | Mon Sep 12 08:00:00 IDT 2011 | Tue Oct 04 17:00:00 IST 2011
2173 | North Temp.Rising Main:Capping Beam | Fri Oct 07 08:00:00 IST 2011 | Sat Oct 29 17:00:00 IST 2011
2174 | South Temp.Rising Main:Capping Beam | Fri Oct 07 08:00:00 IST 2011 | Sat Oct 29 17:00:00 IST 2011
2175 | South Temp.Rising Main Installation+Thrust Block | Mon Oct 31 08:00:00 IST 2011 | Sat Nov 12 17:00:00 IST 2011
2176 | Expose Existing South Pipe | Thu Mar 24 08:00:00 IST 2011 | Wed Nov 02 17:00:00 IST 2011
2177 | Notification for South Rising Main & Flow Stop from DSD Station | Sat Nov 12 17:00:00 IST 2011 | Sat Nov 12 17:00:00 IST 2011
2178 | Diversion Works for Rising Main (South Pipe) | Mon Feb 28 08:00:00 IST 2011 | Fri Mar 11 17:00:00 IST 2011
2179 | North Temp.Rising Main Installation+Thrust Block | Mon Feb 28 08:00:00 IST 2011 | Wed Mar 30 17:00:00 IST 2011
2180 | Expose Existing North Pipe | Mon Mar 14 08:00:00 IST 2011 | Tue Dec 06 17:00:00 IST 2011
2181 | Notification for North Rising Main & Flow Stop from DSD Station | Thu Dec 15 17:00:00 IST 2011 | Thu Dec 15 17:00:00 IST 2011
2182 | Diversion Works for Rising Main (North Pipe) | Tue Nov 01 08:00:00 IST 2011 | Fri Nov 11 17:00:00 IST 2011
2183 | Dismantle Existing Rising Mains | Sat Nov 12 08:00:00 IST 2011 | Fri Nov 18 17:00:00 IST 2011
2184 | Form WorkingPlatform | Tue Jun 21 08:00:00 IDT 2011 | Thu Jul 21 17:00:00 IDT 2011
2185 | Locate Existing Rising Main & FMO (A) Piles | Tue Jun 21 08:00:00 IDT 2011 | Thu Jul 21 17:00:00 IDT 2011
2186 | Removal FMO Pier A Raking Piles DT & Backfilling | Wed Aug 31 08:00:00 IDT 2011 | Mon Nov 14 17:00:00 IST 2011
2187 | Remove Rising Mains Vertical Piles Clash D/T Tunnel & Backfilling | Wed Aug 31 08:00:00 IDT 2011 | Thu Dec 22 17:00:00 IST 2011
2188 | Removal FMO Pier A Raking Piles UT & Backfilling | Sat Oct 29 08:00:00 IST 2011 | Tue May 08 17:00:00 IDT 2012
2189 | Remove Rising Main Vertical Piles Clash U/T Tunnel & Backfilling | Wed Nov 30 08:00:00 IST 2011 | Thu Mar 22 17:00:00 IST 2012
2190 | Remove Working Platform | Tue Apr 17 08:00:00 IDT 2012 | Thu May 03 17:00:00 IDT 2012
2191 | Tie Beams Construction for New Rising Main | Mon Jan 16 08:00:00 IST 2012 | Mon Feb 27 17:00:00 IST 2012
2192 | Notification for South Rising Main & Flow Stop from DSD Station | Mon Oct 07 17:00:00 IDT 2013 | Mon Oct 07 17:00:00 IDT 2013
2193 | Reinstatement Works for Rising Mains (South pipe) | Fri Nov 01 08:00:00 IST 2013 | Tue Dec 31 17:00:00 IST 2013
2194 | Notification for North Rising Main & Flow Stop from DSD Station | Mon Dec 23 17:00:00 IST 2013 | Mon Dec 23 17:00:00 IST 2013
2195 | Reinstatement Works for Rising Mains (North pipe) | Tue Dec 24 08:00:00 IST 2013 | Thu Jan 23 17:00:00 IST 2014
2196 | Place Concrete Surround | Tue Jan 27 08:00:00 IST 2015 | Mon Feb 23 17:00:00 IST 2015
2197 | Utilities Reinstatement | Mon Jun 01 08:00:00 IDT 2015 | Fri Jul 31 17:00:00 IDT 2015
2198 | Rising Main & FMO Pier A Pile Removal (DT) | Sun Mar 13 08:00:00 IST 2011 | Sat Jan 05 17:00:00 IST 2013
2199 | Rising Main & FMO Pier A Pile Removal (UT) | Sun Mar 13 08:00:00 IST 2011 | Sat Sep 07 17:00:00 IDT 2013
2200 | Completion | Thu Sep 01 08:00:00 IDT 2011 | Thu Sep 29 17:00:00 IDT 2011
2201 | Prepare & Submit Draft As-built Drawings | Thu Sep 01 08:00:00 IDT 2011 | Thu Sep 29 17:00:00 IDT 2011
2202 | Prepare & Submit As-built Drawings | Thu Sep 01 08:00:00 IDT 2011 | Thu Sep 29 17:00:00 IDT 2011
2203 | G2 YC2 Culvet - Remove Barrette & Modify Foundation | Mon Feb 28 08:00:00 IST 2011 | Sat Aug 23 17:00:00 IDT 2014
2204 | Stage 1: YC2 Cofferdam Installation | Sun Mar 13 08:00:00 IST 2011 | Wed Aug 17 17:00:00 IDT 2011
2205 | Stage 2: YC2 Barrettes Removal (B15 - DT) | Sun Jun 19 08:00:00 IDT 2011 | Sat Mar 03 17:00:00 IST 2012
2206 | Stage 3: YC2 Barrettes Removal (B13 - UT) | Wed Nov 07 08:00:00 IST 2012 | Wed Nov 21 17:00:00 IST 2012
2207 | Temp.Works Design Submission | Mon Feb 28 08:00:00 IST 2011 | Thu Jun 23 17:00:00 IDT 2011
2208 | Temp. Works Design Preparation | Mon Feb 28 08:00:00 IST 2011 | Mon Apr 25 17:00:00 IDT 2011
2209 | Temp. Works Design Submit to MTR | Wed Mar 23 17:00:00 IST 2011 | Wed Mar 23 17:00:00 IST 2011
2210 | Temp. Works Design Comment by MTR/DSD | Thu Mar 24 08:00:00 IST 2011 | Thu Apr 07 17:00:00 IDT 2011
2211 | Temp. Works Design Re-submission Preparation | Thu Apr 21 08:00:00 IDT 2011 | Thu Jun 23 17:00:00 IDT 2011
2212 | Temp. Works Design Comment & Approval by MTR/DSD | Tue May 10 08:00:00 IDT 2011 | Sun May 22 17:00:00 IDT 2011
2213 | Issue for Construction | Tue Jun 07 08:00:00 IDT 2011 | Tue Jun 07 08:00:00 IDT 2011
2214 | Method Statement Submission and Approval | Mon Feb 28 08:00:00 IST 2011 | Tue Jun 21 17:00:00 IDT 2011
2215 | MS Preparation | Mon Feb 28 08:00:00 IST 2011 | Mon Apr 04 17:00:00 IDT 2011
2216 | MS Submission to MTR | Mon Mar 28 17:00:00 IST 2011 | Mon Mar 28 17:00:00 IST 2011
2217 | MS Comment by MTR/DSD | Tue Mar 29 08:00:00 IST 2011 | Sun May 01 17:00:00 IDT 2011
2218 | MS Re-submission Preparation | Tue Apr 26 08:00:00 IDT 2011 | Wed Jun 01 17:00:00 IDT 2011
2219 | MS Submission to MTR | Wed May 18 17:00:00 IDT 2011 | Wed May 18 17:00:00 IDT 2011
2220 | MS Comment & Approval by MTR/DSD | Thu May 19 08:00:00 IDT 2011 | Tue Jun 21 17:00:00 IDT 2011
2221 | Issue for Construction | Wed Jun 15 17:00:00 IDT 2011 | Wed Jun 15 17:00:00 IDT 2011
2222 | TTM Scheme Submission & Approval | Mon Feb 28 08:00:00 IST 2011 | Sun Aug 21 17:00:00 IDT 2011
2223 | Prepare Temporary Traffic Management | Mon Feb 28 08:00:00 IST 2011 | Wed Mar 23 17:00:00 IST 2011
2224 | TTM reviewed by SLG | Fri Mar 25 08:00:00 IST 2011 | Mon Jun 06 17:00:00 IDT 2011
2225 | Resubmit TTM | Sat Jun 18 08:00:00 IDT 2011 | Mon Jul 25 17:00:00 IDT 2011
2226 | TTM reviewed by SLG | Sun Jun 26 08:00:00 IDT 2011 | Mon Jul 25 17:00:00 IDT 2011
2227 | Notification to RMO | Sun Jul 24 08:00:00 IDT 2011 | Sun Aug 21 17:00:00 IDT 2011
2228 | XP Application & Approval | Sun May 01 08:00:00 IDT 2011 | Fri May 20 17:00:00 IDT 2011
2229 | Implement TTM | Fri Aug 05 17:00:00 IDT 2011 | Fri Aug 05 17:00:00 IDT 2011
2230 | Stage 1 | Mon Feb 28 08:00:00 IST 2011 | Wed Oct 26 17:00:00 IST 2011
2231 | GI works for YC2 Barrette Removal | Mon Feb 28 08:00:00 IST 2011 | Mon Mar 07 17:00:00 IST 2011
2232 | Area 40.4: Tree Transplant by 801 Designated Contractor | Mon Feb 28 08:00:00 IST 2011 | Mon Feb 28 08:00:00 IST 2011
2233 | Shum Mong Rd: Tree Transplant by 801 Designated | Mon Feb 28 08:00:00 IST 2011 | Mon Feb 28 08:00:00 IST 2011
2234 | TTA Stage 0 and 1 for YC2 and Shum Shui Po Pier | Sat Aug 06 08:00:00 IDT 2011 | Tue Sep 06 17:00:00 IDT 2011
2235 | Cofferdam: Sheetpile Installation | Tue Sep 06 08:00:00 IDT 2011 | Thu Sep 22 17:00:00 IDT 2011
2236 | Cofferdam: Excavation + Shoring | Mon Oct 03 08:00:00 IST 2011 | Wed Oct 26 17:00:00 IST 2011
2237 | Backfilling for Cofferdam | Tue Jun 21 08:00:00 IDT 2011 | Tue Jul 26 17:00:00 IDT 2011
2238 | Construct Temp. Pavement | Tue Jun 21 08:00:00 IDT 2011 | Wed Jul 13 17:00:00 IDT 2011
2239 | Stage 1: YC2 Cofferdam Installation | Sun Mar 13 08:00:00 IST 2011 | Wed Aug 17 17:00:00 IDT 2011
2240 | Stage 2 | Sun Jun 19 08:00:00 IDT 2011 | Tue Feb 05 17:00:00 IST 2013
2241 | GI works for YC2 Barrette Removal (Stage 2) | Tue Jun 21 08:00:00 IDT 2011 | Tue Jul 05 17:00:00 IDT 2011
2242 | TTA Stage 2 for Culvert YC2 and Shum Shui Po Pie | Sun Jun 19 08:00:00 IDT 2011 | Wed Jul 06 17:00:00 IDT 2011
2243 | Cofferdam: Sheetpile Installation | Wed Aug 31 08:00:00 IDT 2011 | Mon Oct 24 17:00:00 IST 2011
2244 | Compensation Grout for Culvert | Wed Aug 31 08:00:00 IDT 2011 | Fri Oct 21 17:00:00 IST 2011
2245 | Cofferdam: Excavation + Shoring | Mon Jan 16 08:00:00 IST 2012 | Wed Feb 01 17:00:00 IST 2012
2246 | Remove Culvert Top Slab (saw cut) | Thu Feb 02 08:00:00 IST 2012 | Wed Feb 08 17:00:00 IST 2012
2247 | Install Working Platform & Mini Cofferdam for 1st Cut | Thu Feb 02 08:00:00 IST 2012 | Sat Feb 04 17:00:00 IST 2012
2248 | Barrette Removal (B15) 1st Cut | Sat Feb 11 08:00:00 IST 2012 | Wed Mar 07 17:00:00 IST 2012
2249 | Temp. Base Slab Reinstatement (1st Cut) | Sat Mar 10 08:00:00 IST 2012 | Sat Mar 10 17:00:00 IST 2012
2250 | Remove & Re-install WP Cofferdam for 2nd Cut | Sat Mar 10 08:00:00 IST 2012 | Wed Mar 14 17:00:00 IST 2012
2251 | Barrette Removal (B15) 2nd Cut | Sat Mar 17 08:00:00 IST 2012 | Tue Nov 06 17:00:00 IST 2012
2252 | Barrette Backfilling | Mon Jan 16 08:00:00 IST 2012 | Wed Jan 18 17:00:00 IST 2012
2253 | Culvert Base & Top Slabs Reinstatement | Thu Jan 19 08:00:00 IST 2012 | Wed Nov 07 17:00:00 IST 2012
2254 | Backfill and Road Reinstatement | Wed Jan 09 08:00:00 IST 2013 | Tue Feb 05 17:00:00 IST 2013
2255 | Stage 2: YC2 Barrettes Removal (B15 - DT) | Sun Jun 19 08:00:00 IDT 2011 | Sat Mar 03 17:00:00 IST 2012
2256 | Stage 3 | Wed Oct 31 08:00:00 IST 2012 | Sat Aug 23 17:00:00 IDT 2014
2257 | Compensation grout (after TBM U/T pass through) | Tue Apr 22 08:00:00 IDT 2014 | Fri May 23 17:00:00 IDT 2014
2258 | TTMs Stage 3 for Barrette B13 Removal | Wed Oct 31 08:00:00 IST 2012 | Tue Nov 06 17:00:00 IST 2012
2259 | Remove Culvert Top Slab | Wed Nov 07 08:00:00 IST 2012 | Tue Nov 13 17:00:00 IST 2012
2260 | Install Working Platform & Mini Cofferdam for 1st Cut | Fri Nov 30 08:00:00 IST 2012 | Sat Dec 08 17:00:00 IST 2012
2261 | Barrette Removal (B13) 1st Cut | Sat Nov 10 08:00:00 IST 2012 | Tue Nov 27 17:00:00 IST 2012
2262 | Install Working Platform & Mini Cofferdam for 2nd Cut | Tue Dec 18 08:00:00 IST 2012 | Fri Dec 28 17:00:00 IST 2012
2263 | Barrette Removal (B13) 2nd Cut | Wed Dec 05 08:00:00 IST 2012 | Fri Dec 21 17:00:00 IST 2012
2264 | Barrette Backfill | Fri Dec 21 08:00:00 IST 2012 | Mon Dec 24 17:00:00 IST 2012
2265 | Culvert Base Slab Reinstatement | Thu Dec 27 08:00:00 IST 2012 | Mon Feb 04 17:00:00 IST 2013
2266 | Culvert Top Slab Temp. Reinstatement | Mon Jan 28 08:00:00 IST 2013 | Sat Mar 09 17:00:00 IST 2013
2267 | Top Slab Reinstatement | Sat May 10 08:00:00 IDT 2014 | Wed Jun 25 17:00:00 IDT 2014
2268 | Road Reinstatement / Final TTA | Mon Jun 16 08:00:00 IDT 2014 | Sat Aug 23 17:00:00 IDT 2014
2269 | Stage 3: YC2 Barrettes Removal (B13 - UT) | Wed Nov 07 08:00:00 IST 2012 | Tue Jun 25 17:00:00 IDT 2013
2270 | Completion | Wed May 02 08:00:00 IDT 2012 | Tue May 29 17:00:00 IDT 2012
2271 | Prepare & Submit Draft As-built Drawings | Wed May 02 08:00:00 IDT 2012 | Tue May 29 17:00:00 IDT 2012
2272 | Prepare & Submit As-built Drawings | Wed May 02 08:00:00 IDT 2012 | Tue May 29 17:00:00 IDT 2012
2273 | G3 NC1 DSD Culvert - Remove Barrette | Sat Aug 14 08:00:00 IDT 2010 | Tue Sep 17 17:00:00 IDT 2013
2274 | Barrette Removal B28 & B27 (DT) | Sat Apr 16 08:00:00 IDT 2011 | Wed Aug 08 17:00:00 IDT 2012
2275 | Barrette Removal B24,B21 & B22 (UT) | Sat Apr 16 08:00:00 IDT 2011 | Thu Sep 06 17:00:00 IDT 2012
2276 | Method Statement Submission and Approval | Sat Aug 14 08:00:00 IDT 2010 | Tue Jun 21 17:00:00 IDT 2011
2277 | MS Preparation | Mon Feb 28 08:00:00 IST 2011 | Wed Mar 09 17:00:00 IST 2011
2278 | MS Submission to MTR/DSD | Sat Mar 26 17:00:00 IST 2011 | Sat Mar 26 17:00:00 IST 2011
2279 | MS Comment by MTR/DSD | Sun Mar 27 08:00:00 IST 2011 | Fri Apr 29 17:00:00 IDT 2011
2280 | MS Re-submission Preparation | Sat Aug 14 08:00:00 IDT 2010 | Tue Aug 24 17:00:00 IDT 2010
2281 | MS Submission to MTR/DSD | Wed May 18 17:00:00 IDT 2011 | Wed May 18 17:00:00 IDT 2011
2282 | MS Comment & Approval by MTR/DSD | Thu May 19 08:00:00 IDT 2011 | Tue Jun 21 17:00:00 IDT 2011
2283 | Issue for Construction | Wed Jun 15 17:00:00 IDT 2011 | Wed Jun 15 17:00:00 IDT 2011
2284 | Tree Transplant Application Preparation | Mon Feb 28 08:00:00 IST 2011 | Thu Jun 09 17:00:00 IDT 2011
2285 | Application Submit to LandS Department | Sat Mar 26 17:00:00 IST 2011 | Sat Mar 26 17:00:00 IST 2011
2286 | Application Approval by LandS Department | Sun Mar 27 08:00:00 IST 2011 | Sun Apr 17 17:00:00 IDT 2011
2287 | TTM Scheme Submisssion & Approval | Mon Feb 28 08:00:00 IST 2011 | Sun Aug 21 17:00:00 IDT 2011
2288 | Prepare Temp.Traffic Management (for S.2 &S.2.1) | Mon Feb 28 08:00:00 IST 2011 | Thu Mar 24 17:00:00 IST 2011
2289 | TTM reviewed by SLG | Fri Mar 25 08:00:00 IST 2011 | Mon Jun 06 17:00:00 IDT 2011
2290 | Resubmit TTM | Sat Jun 18 08:00:00 IDT 2011 | Wed Jul 13 17:00:00 IDT 2011
2291 | TTM reviewed by SLG | Sun Jun 26 08:00:00 IDT 2011 | Mon Jul 25 17:00:00 IDT 2011
2292 | Notification to RMO | Sun Jul 24 08:00:00 IDT 2011 | Sun Aug 21 17:00:00 IDT 2011
2293 | XP Application & Approval | Tue May 31 08:00:00 IDT 2011 | Tue Jun 21 17:00:00 IDT 2011
2294 | Implement TTM | Thu Aug 11 17:00:00 IDT 2011 | Thu Aug 11 17:00:00 IDT 2011
2295 | Prepare Temp.Traffic Management(for U/T Group) | Mon Feb 28 08:00:00 IST 2011 | Sat Mar 12 17:00:00 IST 2011
2296 | TTM reviewed by SLG (S.2) | Sun Mar 13 08:00:00 IST 2011 | Sat May 21 17:00:00 IDT 2011
2297 | Notification to RMO | Sun May 22 08:00:00 IDT 2011 | Thu Jun 02 17:00:00 IDT 2011
2298 | Prepare TTMS for Tree Transplant(for D/T Group) | Mon Feb 28 08:00:00 IST 2011 | Fri Jun 17 17:00:00 IDT 2011
2299 | TTM reviewed by SLG (S.2.1) | Sun Mar 13 08:00:00 IST 2011 | Sat May 21 17:00:00 IDT 2011
2300 | Notification to RMO | Sun May 22 08:00:00 IDT 2011 | Thu Jun 02 17:00:00 IDT 2011
2301 | TBM D/T Culvert | Mon Feb 28 08:00:00 IST 2011 | Sat Jan 12 17:00:00 IST 2013
2302 | Works Area 11.21 (Subject to SLG Approval) | Mon Feb 28 08:00:00 IST 2011 | Mon Feb 28 08:00:00 IST 2011
2303 | Works Area 11.31 | Mon Feb 28 08:00:00 IST 2011 | Mon Feb 28 08:00:00 IST 2011
2304 | Works Area 11.32 | Mon Feb 28 08:00:00 IST 2011 | Mon Feb 28 08:00:00 IST 2011
2305 | GI works for NC1 Barrette Removal | Mon Feb 28 08:00:00 IST 2011 | Thu Jun 02 17:00:00 IDT 2011
2306 | Group B Tree Transplant (T9752-54, UC0009-10) Preparation & Transplant | Mon Feb 28 08:00:00 IST 2011 | Sat Apr 30 17:00:00 IDT 2011
2307 | TTA Stage 1 and 2.1 | Thu Apr 14 08:00:00 IDT 2011 | Fri Jun 03 17:00:00 IDT 2011
2308 | ELS Works to Culvert Level | Sat May 07 08:00:00 IDT 2011 | Thu May 26 17:00:00 IDT 2011
2309 | Probing for Existing Barrettes | Thu Apr 14 08:00:00 IDT 2011 | Thu Apr 14 17:00:00 IDT 2011
2310 | Remove Top Slab of Culvert | Tue Nov 01 08:00:00 IST 2011 | Fri Nov 04 17:00:00 IST 2011
2311 | Cofferdam installation and Excavation at B27 | Mon Feb 27 08:00:00 IST 2012 | Sat Mar 17 17:00:00 IST 2012
2312 | Saw Cut Culvert Top Slab at B27 | Mon Mar 19 08:00:00 IST 2012 | Sat Mar 24 17:00:00 IST 2012
2313 | Temp. Working Platform for Barrette Removal | Mon Mar 26 08:00:00 IST 2012 | Sat Apr 14 17:00:00 IDT 2012
2314 | Barrette Removal (B27) | Wed Nov 14 08:00:00 IST 2012 | Wed Jan 02 17:00:00 IST 2013
2315 | Barrette Backfilling | Thu Jan 03 08:00:00 IST 2013 | Sat Jan 05 17:00:00 IST 2013
2316 | Reinstate Culvert Base Slab | Thu Nov 15 08:00:00 IST 2012 | Sat Jan 12 17:00:00 IST 2013
2317 | Barrette Removal (B28) | Wed Jan 04 08:00:00 IST 2012 | Wed Feb 22 17:00:00 IST 2012
2318 | Barrette Backfilling | Tue Nov 01 08:00:00 IST 2011 | Thu Nov 03 17:00:00 IST 2011
2319 | Reinstate Culvert Base Slab | Sat Nov 26 08:00:00 IST 2011 | Wed Dec 28 17:00:00 IST 2011
2320 | Install Temp.Cover at Culvert Top Slab | Tue Nov 01 08:00:00 IST 2011 | Wed Nov 30 17:00:00 IST 2011
2321 | Temp.Backfill & Reinstate Pavement | Tue Jun 21 08:00:00 IDT 2011 | Mon Jul 04 17:00:00 IDT 2011
2322 | TTA Stage 3 | Tue Jun 21 08:00:00 IDT 2011 | Wed Jun 22 17:00:00 IDT 2011
2323 | TBM U/T Culvert | Mon Feb 28 08:00:00 IST 2011 | Tue Sep 17 17:00:00 IDT 2013
2324 | Group B Tree Transplant (T9752-54,T8836-37, UC0009-10)Preparation & Transplant | Mon Feb 28 08:00:00 IST 2011 | Thu Apr 28 17:00:00 IDT 2011
2325 | Group D Tree Transplant (T8838,T8843-44) Preparation & Transplant | Mon Feb 28 08:00:00 IST 2011 | Wed Jun 29 17:00:00 IDT 2011
2326 | Tree Transplant Complete by 801 Designated Contractor | Mon Feb 28 08:00:00 IST 2011 | Mon Feb 28 08:00:00 IST 2011
2327 | TTMS Implementation | Mon Feb 28 08:00:00 IST 2011 | Sat Mar 05 17:00:00 IST 2011
2328 | Trial Trench to Expose Existing U/G Utiltiies | Mon Mar 07 08:00:00 IST 2011 | Sat Mar 19 17:00:00 IST 2011
2329 | Slew 132kV Cable (CLP207) | Thu Apr 21 08:00:00 IDT 2011 | Mon Aug 08 17:00:00 IDT 2011
2330 | Slew Telecom Cable (CATV206&PCCW203) | Tue May 03 08:00:00 IDT 2011 | Wed May 18 17:00:00 IDT 2011
2331 | Probing for Existing Barrettes | Mon Apr 11 08:00:00 IDT 2011 | Mon Apr 11 17:00:00 IDT 2011
2332 | ELS for Roof Access | Thu May 19 08:00:00 IDT 2011 | Wed Jun 15 17:00:00 IDT 2011
2333 | Remove Top Slab of Culvert | Mon Mar 28 08:00:00 IST 2011 | Sat Nov 05 17:00:00 IST 2011
2334 | Temp. Working Platform for Barrette Removal | Tue Nov 08 08:00:00 IST 2011 | Sat Nov 12 17:00:00 IST 2011
2335 | Barrette Removal (B24) | Tue Dec 06 08:00:00 IST 2011 | Fri Jan 13 17:00:00 IST 2012
2336 | Barrette Backfilling | Tue Nov 01 08:00:00 IST 2011 | Wed Nov 02 17:00:00 IST 2011
2337 | Reinstate Culvert Base Slab | Tue Nov 01 08:00:00 IST 2011 | Tue Nov 29 17:00:00 IST 2011
2338 | Remove Crane Platform & Reinstate Culvert Top Slab | Tue Jun 21 08:00:00 IDT 2011 | Mon Aug 08 17:00:00 IDT 2011
2339 | Slew 11kV Cable & Connection (CLP219) | Tue Jun 21 08:00:00 IDT 2011 | Mon Aug 01 17:00:00 IDT 2011
2340 | Divert 400D&315D Low Pressure Gas Main (GAS206&207) | Tue Jun 21 08:00:00 IDT 2011 | Thu Jul 14 17:00:00 IDT 2011
2341 | Divert 200D Freshwater Main (FW211) | Tue Jun 21 08:00:00 IDT 2011 | Wed Aug 03 17:00:00 IDT 2011
2342 | Divert 150D Saltwater Main (SW207) | Tue Jun 21 08:00:00 IDT 2011 | Mon Jun 27 17:00:00 IDT 2011
2343 | Slew 400kV Cable Group | Fri Jan 20 08:00:00 IST 2012 | Mon Jan 30 17:00:00 IST 2012
2344 | Preparation Work for TTMS Stage 4 | Mon Jan 30 08:00:00 IST 2012 | Thu Feb 09 17:00:00 IST 2012
2345 | Implement TTMS Stage 4 | Sat Feb 25 08:00:00 IST 2012 | Sat Feb 25 17:00:00 IST 2012
2346 | Drive Sheetpile for Barrette Removal (B21 & B22) | Sat Feb 25 08:00:00 IST 2012 | Fri Mar 02 17:00:00 IST 2012
2347 | ELS to Top Slab of Culvert | Sat Mar 17 08:00:00 IST 2012 | Thu Mar 29 17:00:00 IST 2012
2348 | Barrette Removal (B21) | Thu Nov 01 08:00:00 IST 2012 | Mon Nov 26 17:00:00 IST 2012
2349 | Barrette Backfilling | Wed Dec 19 08:00:00 IST 2012 | Wed Dec 19 17:00:00 IST 2012
2350 | Reinstate Culvert Base Slab | Tue Dec 11 08:00:00 IST 2012 | Sat Jan 12 17:00:00 IST 2013
2351 | Barrette Removal (B22) | Thu Nov 01 08:00:00 IST 2012 | Wed Dec 05 17:00:00 IST 2012
2352 | Barrette Backfilling | Thu Dec 06 08:00:00 IST 2012 | Fri Dec 07 17:00:00 IST 2012
2353 | Reinstate Culvert Base Slab | Tue Dec 11 08:00:00 IST 2012 | Sat Jan 12 17:00:00 IST 2013
2354 | 4nos.Pre-bored H Pile Installallation | Mon Jan 14 08:00:00 IST 2013 | Thu Feb 28 17:00:00 IST 2013
2355 | Band Beam Construction for Connect Pile & Box Culvert | Fri Mar 01 08:00:00 IST 2013 | Thu Mar 28 17:00:00 IST 2013
2356 | Tie-beam Curing & Load Transfer from Box Culvert to Temp.Pile | Tue Apr 02 08:00:00 IDT 2013 | Mon Apr 29 17:00:00 IDT 2013
2357 | Permanent Reinstate Culvert Top Slab | Tue Apr 30 08:00:00 IDT 2013 | Fri Aug 02 17:00:00 IDT 2013
2358 | Permanent Reinstatement for DN200 FW Main | Wed Nov 28 08:00:00 IST 2012 | Sat Jan 05 17:00:00 IST 2013
2359 | Permanent Reinstatement for DN400 Gas Main | Sat Dec 01 08:00:00 IST 2012 | Sat Dec 22 17:00:00 IST 2012
2360 | Permanent Reinstatement for CLP 11kV Cables | Mon Dec 24 08:00:00 IST 2012 | Wed Jan 23 17:00:00 IST 2013
2361 | Permanent Reinstatement for CLP 400kV Cables | Thu Jan 24 08:00:00 IST 2013 | Thu Feb 07 17:00:00 IST 2013
2362 | Permanent Reinstatement for Telecom Cables | Mon Mar 18 08:00:00 IST 2013 | Thu Mar 28 17:00:00 IST 2013
2363 | Backfilling & Road Reinstatement | Sat Aug 17 08:00:00 IDT 2013 | Tue Sep 17 17:00:00 IDT 2013
2364 | Completion | Fri Jun 01 08:00:00 IDT 2012 | Fri Jun 29 17:00:00 IDT 2012
2365 | Prepare & Submit Draft As-built Drawings | Fri Jun 01 08:00:00 IDT 2012 | Fri Jun 29 17:00:00 IDT 2012
2366 | Prepare & Submit As-built Drawings | Fri Jun 01 08:00:00 IDT 2012 | Fri Jun 29 17:00:00 IDT 2012
2367 | Box Culvert FS1 Barrettes Removal | Mon Feb 28 08:00:00 IST 2011 | Sat Oct 10 17:00:00 IDT 2015
2368 | Underpinning Works for FS1 / Barrettes Removal | Wed Aug 31 08:00:00 IDT 2011 | Tue Dec 06 17:00:00 IST 2011
2369 | Temp. Works Design Submission | Mon Feb 28 08:00:00 IST 2011 | Sun Jul 17 17:00:00 IDT 2011
2370 | Temp. Works Design Preparation | Mon Feb 28 08:00:00 IST 2011 | Wed Apr 13 17:00:00 IDT 2011
2371 | Temp. Works Design Submit to MTR | Mon Mar 28 08:00:00 IST 2011 | Mon Mar 28 08:00:00 IST 2011
2372 | Temp. Works Design Comment by MTR/DSD | Mon Mar 28 08:00:00 IST 2011 | Mon Apr 11 17:00:00 IDT 2011
2373 | Temp. Works Design Re-submission Preparation | Tue Apr 26 08:00:00 IDT 2011 | Sat May 14 17:00:00 IDT 2011
2374 | Temp. Works Design Comment & Approval by MTR/DSD | Thu May 19 08:00:00 IDT 2011 | Sun Jul 17 17:00:00 IDT 2011
2375 | Issue for Construction | Wed Jun 15 17:00:00 IDT 2011 | Wed Jun 15 17:00:00 IDT 2011
2376 | Method Statement Submission and Approval | Mon Feb 28 08:00:00 IST 2011 | Wed Jun 15 17:00:00 IDT 2011
2377 | MS Preparation | Mon Feb 28 08:00:00 IST 2011 | Wed Mar 30 17:00:00 IST 2011
2378 | MS Submission to MTR | Sat Mar 26 17:00:00 IST 2011 | Sat Mar 26 17:00:00 IST 2011
2379 | MS Comment by MTR/DSD | Sun Mar 27 08:00:00 IST 2011 | Fri Apr 22 17:00:00 IDT 2011
2380 | MS Re-submission Preparation | Tue Apr 26 08:00:00 IDT 2011 | Sat May 28 17:00:00 IDT 2011
2381 | MS Submission to MTR | Wed May 18 17:00:00 IDT 2011 | Wed May 18 17:00:00 IDT 2011
2382 | MS Comment & Approval by MTR/DSD | Thu May 19 08:00:00 IDT 2011 | Tue Jun 14 17:00:00 IDT 2011
2383 | Issue for Construction | Wed Jun 15 17:00:00 IDT 2011 | Wed Jun 15 17:00:00 IDT 2011
2384 | Utilities Diversion
2385 | Underpinning Works for FS1 | Fri May 06 17:00:00 IDT 2011 | Thu Aug 13 17:00:00 IDT 2015
2386 | Area 39.1 Tree Transplant by 801 Designated Contractor | Fri May 06 17:00:00 IDT 2011 | Fri May 06 17:00:00 IDT 2011
2387 | Soft Excavation to S1 (~+4.5mPD) | Tue Oct 18 08:00:00 IST 2011 | Fri Oct 21 17:00:00 IST 2011
2388 | Soft Excavation & Expose Culvert FS1(~-2.0mPD) | Wed Aug 31 08:00:00 IDT 2011 | Wed Sep 14 17:00:00 IDT 2011
2389 | Cast in-situ RC Wall to Support Existing Ground (adjacent B14 & B19) | Wed Aug 31 08:00:00 IDT 2011 | Mon Sep 05 17:00:00 IDT 2011
2390 | Setup & Install Four Prebored H-piles (adjacent to Existing B17) | Wed Aug 31 08:00:00 IDT 2011 | Thu Sep 15 17:00:00 IDT 2011
2391 | Soft Excavation to 2m underneath Culvert | Tue Sep 06 08:00:00 IDT 2011 | Mon Sep 19 17:00:00 IDT 2011
2392 | Installation of Corbel Beams either Side of Culvert | Wed Aug 31 08:00:00 IDT 2011 | Tue Sep 06 17:00:00 IDT 2011
2393 | Steel Beam Installation underneath Corbel Beams & Connect to H-pile | Wed Aug 31 08:00:00 IDT 2011 | Tue Sep 06 17:00:00 IDT 2011
2394 | Loading Transfer with Jacks | Wed Aug 31 08:00:00 IDT 2011 | Wed Aug 31 17:00:00 IDT 2011
2395 | Excavation to foundation level for B19 | Wed Aug 31 08:00:00 IDT 2011 | Fri Dec 16 17:00:00 IST 2011
2396 | Excavation to foundation level for B14 | Fri Feb 17 08:00:00 IST 2012 | Sat Jun 16 17:00:00 IDT 2012
2397 | Barettes Breaking (B15-B18) | Wed Aug 31 08:00:00 IDT 2011 | Wed Dec 14 17:00:00 IST 2011
2398 | Install Lagging Wall (at West & East D-wall) | Wed Aug 31 08:00:00 IDT 2011 | Fri Nov 11 17:00:00 IST 2011
2399 | Backfilling, Compaction & Testing | Sat Jul 11 08:00:00 IDT 2015 | Wed Aug 05 17:00:00 IDT 2015
2400 | Disconnected Steel H-pile inside Tunnel Box | Thu Aug 06 08:00:00 IDT 2015 | Thu Aug 13 17:00:00 IDT 2015
2401 | Completion | Fri Aug 14 08:00:00 IDT 2015 | Sat Oct 10 17:00:00 IDT 2015
2402 | Prepare & Submit Draft As-built Drawings | Fri Aug 14 08:00:00 IDT 2015 | Thu Sep 10 17:00:00 IDT 2015
2403 | Prepare & Submit As-built Drawings | Fri Sep 11 08:00:00 IDT 2015 | Sat Oct 10 17:00:00 IDT 2015
2404 | Cost Centre H - Piling Works to Footbridges | Mon Feb 28 08:00:00 IST 2011 | Mon Nov 23 17:00:00 IST 2015
2405 | IPS Milestones | Mon Feb 28 08:00:00 IST 2011 | Thu Sep 24 17:00:00 IDT 2015
2406 | General | Mon Feb 28 08:00:00 IST 2011 | Thu Sep 24 17:00:00 IDT 2015
2407 | Obtain SLG of TTMS for Footbridge Piling Start | Mon Feb 28 08:00:00 IST 2011 | Mon Feb 28 08:00:00 IST 2011
2408 | Complete 9% of Piles | Fri Nov 30 08:00:00 IST 2012 | Fri Nov 30 08:00:00 IST 2012
2409 | Complete 60% of Piles | Sat May 18 17:00:00 IDT 2013 | Sat May 18 17:00:00 IDT 2013
2410 | Complete 70% of Piles | Mon Jul 27 17:00:00 IDT 2015 | Mon Jul 27 17:00:00 IDT 2015
2411 | Complete 100% Piles except Pile cap 28 | Fri Jun 26 17:00:00 IDT 2015 | Fri Jun 26 17:00:00 IDT 2015
2412 | Complete All Works | Thu Sep 24 17:00:00 IDT 2015 | Thu Sep 24 17:00:00 IDT 2015
2413 | Construction | Mon Feb 28 08:00:00 IST 2011 | Mon Nov 23 17:00:00 IST 2015
2414 | Footbridge No.1 (Hing Wai St. West) | Fri Aug 31 08:00:00 IDT 2012 | Sat Sep 07 17:00:00 IDT 2013
2415 | Footbridge No.2 (Tonkin St. West) (2 out of 17 nos.) | Wed Sep 12 08:00:00 IDT 2012 | Wed Feb 13 17:00:00 IST 2013
2416 | Footbridge No.3 (Yen Chow St. West) | Mon May 06 08:00:00 IDT 2013 | Wed Dec 11 17:00:00 IST 2013
2417 | Method Statement Submission and Approval | Mon Feb 28 08:00:00 IST 2011 | Fri Jan 04 17:00:00 IST 2013
2418 | MS Preparation | Mon Feb 28 08:00:00 IST 2011 | Fri Mar 25 17:00:00 IST 2011
2419 | MS Submission to CEDD | Mon Mar 28 17:00:00 IST 2011 | Mon Mar 28 17:00:00 IST 2011
2420 | MS Comment by CEDD / Alt. Design Review with CEDD | Tue Mar 29 08:00:00 IST 2011 | Fri Apr 29 17:00:00 IDT 2011
2421 | MS Re-submission Preparation | Thu Nov 08 08:00:00 IST 2012 | Thu Dec 06 17:00:00 IST 2012
2422 | MS Submission to CEDD | Thu Dec 06 17:00:00 IST 2012 | Thu Dec 06 17:00:00 IST 2012
2423 | MS Comment & Approval by CEDD | Fri Dec 07 08:00:00 IST 2012 | Thu Jan 03 17:00:00 IST 2013
2424 | Issue for Construction | Fri Jan 04 17:00:00 IST 2013 | Fri Jan 04 17:00:00 IST 2013
2425 | TTM Scheme Submission & Approval | Mon Feb 28 08:00:00 IST 2011 | Mon Aug 22 17:00:00 IDT 2011
2426 | Prepare Temporary Traffic Management | Mon Feb 28 08:00:00 IST 2011 | Wed Mar 23 17:00:00 IST 2011
2427 | TTM reviewed by SLG | Sat Mar 26 08:00:00 IST 2011 | Fri Apr 29 17:00:00 IDT 2011
2428 | Resubmit TTM | Mon Feb 28 08:00:00 IST 2011 | Sat Apr 02 17:00:00 IDT 2011
2429 | TTM reviewed by SLG | Mon Feb 28 08:00:00 IST 2011 | Fri Apr 08 17:00:00 IDT 2011
2430 | Notification to RMO | Mon Feb 28 08:00:00 IST 2011 | Sun Aug 07 17:00:00 IDT 2011
2431 | XP Application & Approval | Thu Jun 02 08:00:00 IDT 2011 | Wed Jul 27 17:00:00 IDT 2011
2432 | Implement TTM | Mon Aug 22 17:00:00 IDT 2011 | Mon Aug 22 17:00:00 IDT 2011
2433 | Footbridge No.1 (Hing Wai St. West) | Mon Feb 28 08:00:00 IST 2011 | Fri May 24 17:00:00 IDT 2013
2434 | Temp.Traffic Diversion | Mon Feb 28 08:00:00 IST 2011 | Mon Mar 07 17:00:00 IST 2011
2435 | Temp. Pedestrians Barriers Erection | Mon Feb 28 08:00:00 IST 2011 | Mon Mar 07 17:00:00 IST 2011
2436 | Trial Trench & Record | Mon Feb 28 08:00:00 IST 2011 | Tue Aug 23 17:00:00 IDT 2011
2437 | Area A PC6, PC7 & PC8 | Fri Aug 31 08:00:00 IDT 2012 | Mon Apr 22 17:00:00 IDT 2013
2438 | Trial Pit | Fri Aug 31 08:00:00 IDT 2012 | Fri Sep 21 17:00:00 IDT 2012
2439 | Utilities Diversion | Sat Sep 22 08:00:00 IDT 2012 | Fri Sep 28 17:00:00 IST 2012
2440 | Confirmation of design by CEDD | Sat Jan 05 08:00:00 IST 2013 | Fri Jan 11 17:00:00 IST 2013
2441 | Implementation of TTMS & Site setup | Fri Jan 11 08:00:00 IST 2013 | Mon Jan 21 17:00:00 IST 2013
2442 | Piling works (18 nos. Pre-bored H-piles) | Mon Jan 21 08:00:00 IST 2013 | Mon Apr 22 17:00:00 IDT 2013
2443 | Area B PC4, PC5, PC10 & PC11 | Fri Dec 14 08:00:00 IST 2012 | Fri May 24 17:00:00 IDT 2013
2444 | Trial Pit | Fri Dec 14 08:00:00 IST 2012 | Fri Dec 21 17:00:00 IST 2012
2445 | Utilities Diversion | Sat Dec 22 08:00:00 IST 2012 | Wed Jan 02 17:00:00 IST 2013
2446 | Site setup | Thu Jan 03 08:00:00 IST 2013 | Sat Jan 05 17:00:00 IST 2013
2447 | Piling works (26 nos. Pre-bored H-piles) | Mon Jan 07 08:00:00 IST 2013 | Fri May 24 17:00:00 IDT 2013
2448 | Footbridge No.2 (Tonkin St. West) | Mon Feb 28 08:00:00 IST 2011 | Tue May 19 17:00:00 IDT 2015
2449 | Temp.Traffic Diversion | Mon Feb 28 08:00:00 IST 2011 | Tue Mar 08 17:00:00 IST 2011
2450 | Temp. Pedestrians Barriers Erection | Mon Feb 28 08:00:00 IST 2011 | Mon Mar 07 17:00:00 IST 2011
2451 | Trial Trench & Record | Mon Feb 28 08:00:00 IST 2011 | Sat Mar 12 17:00:00 IST 2011
2452 | Area C PC22, PC23 & PC24 | Wed Sep 12 08:00:00 IDT 2012 | Tue May 19 17:00:00 IDT 2015
2453 | Implementation of TTMS & Site Clearance | Wed Sep 12 08:00:00 IDT 2012 | Fri Sep 21 17:00:00 IDT 2012
2454 | Trial Pit | Fri Sep 21 08:00:00 IDT 2012 | Mon Oct 08 17:00:00 IST 2012
2455 | Utilities Diversion & Protection | Mon Oct 08 08:00:00 IST 2012 | Fri Oct 26 17:00:00 IST 2012
2456 | Site formation | Thu Nov 01 08:00:00 IST 2012 | Wed Nov 14 17:00:00 IST 2012
2457 | Site Setup | Wed Nov 14 08:00:00 IST 2012 | Tue Nov 20 17:00:00 IST 2012
2458 | FB2 - Piling works (2 nos. Pre-bored H-piles) | Sat Dec 01 08:00:00 IST 2012 | Fri Dec 14 17:00:00 IST 2012
2459 | FB2 - Piling works (6 nos. Pre-bored H-piles) | Mon Feb 09 08:00:00 IST 2015 | Tue May 19 17:00:00 IDT 2015
2460 | Footbridge No.3 (Yen Chow St.West) | Mon Feb 28 08:00:00 IST 2011 | Thu Sep 24 17:00:00 IDT 2015
2461 | Temp.Traffic Diversion | Mon Feb 28 08:00:00 IST 2011 | Mon Mar 07 17:00:00 IST 2011
2462 | Temp. Steel Decking & Barrier for Pedestrians | Mon Feb 28 08:00:00 IST 2011 | Mon Mar 07 17:00:00 IST 2011
2463 | Trial Trench & Record | Mon Feb 28 08:00:00 IST 2011 | Tue Jul 05 17:00:00 IDT 2011
2464 | Area D PC25, PC26 & PC27 | Mon Nov 12 08:00:00 IST 2012 | Fri May 31 17:00:00 IDT 2013
2465 | Implementation of TTMS & Site Clearance | Mon Nov 12 08:00:00 IST 2012 | Sat Nov 17 17:00:00 IST 2012
2466 | Trial pit to expose utilities | Mon Nov 19 08:00:00 IST 2012 | Sat Nov 24 17:00:00 IST 2012
2467 | Utilities Diversion & Protection | Fri Feb 15 08:00:00 IST 2013 | Sat Mar 02 17:00:00 IST 2013
2468 | Implementation of TTMS | Fri Feb 08 08:00:00 IST 2013 | Mon Mar 25 17:00:00 IST 2013
2469 | Site Setup | Fri Mar 01 08:00:00 IST 2013 | Fri Mar 08 17:00:00 IST 2013
2470 | FB3a - Piling works (8 nos. Pre-bored H-piles) | Tue Apr 02 08:00:00 IDT 2013 | Fri May 31 17:00:00 IDT 2013
2471 | Area E PC28 | Thu Aug 22 08:00:00 IDT 2013 | Thu Sep 24 17:00:00 IDT 2015
2472 | Implementation of TTMS | Thu Aug 22 08:00:00 IDT 2013 | Thu Aug 22 17:00:00 IDT 2013
2473 | Trial Pit | Fri Aug 23 08:00:00 IDT 2013 | Fri Sep 06 17:00:00 IDT 2013
2474 | Utilities Diversion & Protection | Sat Sep 07 08:00:00 IDT 2013 | Tue Sep 24 17:00:00 IDT 2013
2475 | Site formation [Pending for further instruction by MTR] | Mon Jun 01 08:00:00 IDT 2015 | Sat Jun 06 17:00:00 IDT 2015
2476 | Site Setup [Pending for further instruction by MTR] | Sat Jun 06 08:00:00 IDT 2015 | Mon Jun 15 17:00:00 IDT 2015
2477 | FB3b - Piling works (18 nos. Pre-bored H-piles) [Pending for further instruction by MTR] | Mon Jun 15 08:00:00 IDT 2015 | Thu Sep 24 17:00:00 IDT 2015
2478 | Completion | Fri Sep 25 08:00:00 IDT 2015 | Mon Nov 23 17:00:00 IST 2015
2479 | Prepare & Submit Draft As-built Drawings | Fri Sep 25 08:00:00 IDT 2015 | Mon Oct 26 17:00:00 IST 2015
2480 | Prepare & Submit As-built Drawings | Tue Oct 27 08:00:00 IST 2015 | Mon Nov 23 17:00:00 IST 2015
2481 | Cost Centre I3 (Option) HD's Entrustment Works - Carpark/Welfare Block | Sun May 31 08:00:00 IDT 2015 | Thu Apr 07 17:00:00 IDT 2016
2482 | IPS Milestones | Wed Nov 18 17:00:00 IST 2015 | Thu Feb 04 17:00:00 IST 2016
2483 | General | Wed Nov 18 17:00:00 IST 2015 | Thu Feb 04 17:00:00 IST 2016
2484 | Complete 50% Carpark/Welfare Facilities Podium Foundation | Wed Nov 18 17:00:00 IST 2015 | Wed Nov 18 17:00:00 IST 2015
2485 | Complete All Works | Thu Feb 04 17:00:00 IST 2016 | Thu Feb 04 17:00:00 IST 2016
2486 | Method Statement Submission and Approval | Tue Jun 30 08:00:00 IDT 2015 | Thu Oct 29 17:00:00 IST 2015
2487 | Method Statement Submission and Approval | Tue Jun 30 08:00:00 IDT 2015 | Thu Oct 29 17:00:00 IST 2015
2488 | MS Preparation | Tue Jun 30 08:00:00 IDT 2015 | Fri Jul 31 17:00:00 IDT 2015
2489 | MS Submission to MTR | Fri Jul 31 17:00:00 IDT 2015 | Fri Jul 31 17:00:00 IDT 2015
2490 | MS Comment by MTR | Sat Aug 01 08:00:00 IDT 2015 | Fri Aug 28 17:00:00 IDT 2015
2491 | MS Re-submission Preparation | Sat Aug 29 08:00:00 IDT 2015 | Wed Sep 30 17:00:00 IDT 2015
2492 | MS Submission to MTR | Wed Sep 30 17:00:00 IDT 2015 | Wed Sep 30 17:00:00 IDT 2015
2493 | MS Comment & Approval by MTR | Thu Oct 01 08:00:00 IDT 2015 | Wed Oct 28 17:00:00 IST 2015
2494 | Issue for Construction | Thu Oct 29 17:00:00 IST 2015 | Thu Oct 29 17:00:00 IST 2015
2495 | Construction | Sun May 31 08:00:00 IDT 2015 | Thu Apr 07 17:00:00 IDT 2016
2496 | Raft Footing Construction | Sun May 31 08:00:00 IDT 2015 | Thu Feb 04 17:00:00 IST 2016
2497 | Latest Exercising Date - Carpark/Welfare Block | Sun May 31 08:00:00 IDT 2015 | Sun May 31 08:00:00 IDT 2015
2498 | Raft Footing Construction | Fri Oct 30 08:00:00 IST 2015 | Thu Dec 10 17:00:00 IST 2015
2499 | U/G Drainage /Utilities | Fri Dec 11 08:00:00 IST 2015 | Sat Jan 09 17:00:00 IST 2016
2500 | Backfilling & Compaction (up to ground level +5.5mPD) | Mon Jan 11 08:00:00 IST 2016 | Thu Feb 04 17:00:00 IST 2016
2501 | Completion | Fri Feb 05 08:00:00 IST 2016 | Thu Apr 07 17:00:00 IDT 2016
2502 | Prepare & Submit Draft As-built Drawings | Fri Feb 05 08:00:00 IST 2016 | Mon Mar 07 17:00:00 IST 2016
2503 | Prepare & Submit As-built Drawings | Tue Mar 08 08:00:00 IST 2016 | Thu Apr 07 17:00:00 IDT 2016
2504 | Cost Centre I4 (Option) HD's Entrustment Works - Podium Shop | Sun May 31 08:00:00 IDT 2015 | Thu Feb 25 17:00:00 IST 2016
2505 | IPS Milestones | Sun Aug 02 17:00:00 IDT 2015 | Thu Dec 24 17:00:00 IST 2015
2506 | General | Sun Aug 02 17:00:00 IDT 2015 | Thu Dec 24 17:00:00 IST 2015
2507 | Complete 50% Podium Shop Foundation | Sun Aug 02 17:00:00 IDT 2015 | Sun Aug 02 17:00:00 IDT 2015
2508 | Complete All Works | Thu Dec 24 17:00:00 IST 2015 | Thu Dec 24 17:00:00 IST 2015
2509 | Method Statement Submission and Approval | Tue Jun 30 08:00:00 IDT 2015 | Thu Oct 29 17:00:00 IST 2015
2510 | Method Statement Submission and Approval | Tue Jun 30 08:00:00 IDT 2015 | Thu Oct 29 17:00:00 IST 2015
2511 | MS Preparation | Tue Jun 30 08:00:00 IDT 2015 | Fri Jul 31 17:00:00 IDT 2015
2512 | MS Submission to HD/ICU | Fri Jul 31 17:00:00 IDT 2015 | Fri Jul 31 17:00:00 IDT 2015
2513 | MS Comment by HD/ICU | Sat Aug 01 08:00:00 IDT 2015 | Fri Aug 28 17:00:00 IDT 2015
2514 | MS Re-submission Preparation | Sat Aug 29 08:00:00 IDT 2015 | Wed Sep 30 17:00:00 IDT 2015
2515 | MS Submission to HD/ICU | Wed Sep 30 17:00:00 IDT 2015 | Wed Sep 30 17:00:00 IDT 2015
2516 | MS Comment & Approval by HD/ICU | Thu Oct 01 08:00:00 IDT 2015 | Wed Oct 28 17:00:00 IST 2015
2517 | Issue for Construction | Thu Oct 29 17:00:00 IST 2015 | Thu Oct 29 17:00:00 IST 2015
2518 | Construction | Sun May 31 08:00:00 IDT 2015 | Thu Feb 25 17:00:00 IST 2016
2519 | General | Sun May 31 08:00:00 IDT 2015 | Thu Dec 24 17:00:00 IST 2015
2520 | Latest Exercising Date - Podium Shop | Sun May 31 08:00:00 IDT 2015 | Sun May 31 08:00:00 IDT 2015
2521 | Foundation Construction | Fri Oct 30 08:00:00 IST 2015 | Thu Nov 19 17:00:00 IST 2015
2522 | U/G Drainage /Utilities | Fri Nov 20 08:00:00 IST 2015 | Thu Dec 10 17:00:00 IST 2015
2523 | Backfilling & Compaction (up to ground level +5.5mPD) | Fri Dec 11 08:00:00 IST 2015 | Thu Dec 24 17:00:00 IST 2015
2524 | Completion | Mon Dec 28 08:00:00 IST 2015 | Thu Feb 25 17:00:00 IST 2016
2525 | Prepare & Submit Draft As-built Drawings | Mon Dec 28 08:00:00 IST 2015 | Mon Jan 25 17:00:00 IST 2016
2526 | Prepare & Submit As-built Drawings | Tue Jan 26 08:00:00 IST 2016 | Thu Feb 25 17:00:00 IST 2016
2527 | Cost Centre I5 (Option) HD's Entrustment Works - Bored Piles to Elevated Walkway | Mon Feb 28 08:00:00 IST 2011 | Thu May 01 17:00:00 IDT 2014
2528 | IPS Milestones | Tue Oct 08 17:00:00 IDT 2013 | Thu Oct 24 17:00:00 IDT 2013
2529 | General | Tue Oct 08 17:00:00 IDT 2013 | Thu Oct 24 17:00:00 IDT 2013
2530 | Complete 4 nos. of Bored Piles (4 of 5 piles) | Tue Oct 08 17:00:00 IDT 2013 | Tue Oct 08 17:00:00 IDT 2013
2531 | Complete All Works | Thu Oct 24 17:00:00 IDT 2013 | Thu Oct 24 17:00:00 IDT 2013
2532 | Method Statement Submission and Approval | Mon May 06 08:00:00 IDT 2013 | Thu Jul 25 17:00:00 IDT 2013
2533 | Method Statement Submission and Approval | Mon May 06 08:00:00 IDT 2013 | Thu Jul 25 17:00:00 IDT 2013
2534 | MS Preparation | Mon May 06 08:00:00 IDT 2013 | Wed Jun 05 17:00:00 IDT 2013
2535 | MS Submission to HD/ICU | Wed Jun 05 17:00:00 IDT 2013 | Wed Jun 05 17:00:00 IDT 2013
2536 | MS Comment by HD/ICU | Thu Jun 06 08:00:00 IDT 2013 | Wed Jul 03 17:00:00 IDT 2013
2537 | MS Re-submission Preparation | Fri Jun 14 08:00:00 IDT 2013 | Tue Jul 16 17:00:00 IDT 2013
2538 | MS Submission to HD/ICU | Thu Jun 27 17:00:00 IDT 2013 | Thu Jun 27 17:00:00 IDT 2013
2539 | MS Comment & Approval by HD/ICU | Fri Jun 28 08:00:00 IDT 2013 | Thu Jul 25 17:00:00 IDT 2013
2540 | Issue for Construction | Sat Jun 29 17:00:00 IDT 2013 | Sat Jun 29 17:00:00 IDT 2013
2541 | Construction | Mon Feb 28 08:00:00 IST 2011 | Thu May 01 17:00:00 IDT 2014
2542 | General | Mon Feb 28 08:00:00 IST 2011 | Thu May 01 17:00:00 IDT 2014
2543 | Latest Exercising Date - Bored Piles | Mon Feb 28 08:00:00 IST 2011 | Mon Feb 28 08:00:00 IST 2011
2544 | Diversion of existing drain | Mon May 06 08:00:00 IDT 2013 | Wed Jun 05 17:00:00 IDT 2013
2545 | 1st no. Bored Pile P6 Construction | Tue Jul 02 08:00:00 IDT 2013 | Wed Jul 31 17:00:00 IDT 2013
2546 | 2nd no. Bored Pile P3 Construction | Wed Jul 24 08:00:00 IDT 2013 | Thu Aug 22 17:00:00 IDT 2013
2547 | 3rd no. Bored Pile P5 Construction | Fri Aug 23 08:00:00 IDT 2013 | Mon Sep 23 17:00:00 IDT 2013
2548 | 4th no. Bored Pile P2 Construction | Fri Sep 06 08:00:00 IDT 2013 | Tue Oct 08 17:00:00 IDT 2013
2549 | Pile Testing | Tue Jul 02 08:00:00 IDT 2013 | Wed Oct 02 17:00:00 IDT 2013
2550 | 5th no. Bored Pile P4 Construction | Sat Sep 28 08:00:00 IDT 2013 | Mon Oct 28 17:00:00 IST 2013
2551 | Bored Piles & Pile Testing | Mon Oct 28 08:00:00 IST 2013 | Thu May 01 17:00:00 IDT 2014
2552 | Completion | Mon Dec 02 08:00:00 IST 2013 | Tue Dec 31 17:00:00 IST 2013
2553 | Prepare & Submit Draft As-built Drawings | Mon Dec 02 08:00:00 IST 2013 | Tue Dec 31 17:00:00 IST 2013
2554 | Prepare & Submit As-built Drawings | Mon Dec 02 08:00:00 IST 2013 | Tue Dec 31 17:00:00 IST 2013
2555 | Cost Centre J - Cut & Cover Tunnels At Hoi Ting Road Retrieval Shaft | Thu Nov 07 08:00:00 IST 2013 | Thu Aug 06 17:00:00 IDT 2015
2556 | Underground Drainage & Utilities | Mon Jul 07 08:00:00 IDT 2014 | Mon Sep 22 17:00:00 IDT 2014
2557 | IPS Milestones | Tue Apr 01 17:00:00 IDT 2014 | Thu Aug 06 17:00:00 IDT 2015
2558 | Complete Roof slab of Down track cut and cover tunnel | Tue Apr 01 17:00:00 IDT 2014 | Tue Apr 01 17:00:00 IDT 2014
2559 | Achieve Degree 1 completion for the Down track cut and cover tunnel | Thu May 15 17:00:00 IDT 2014 | Thu May 15 17:00:00 IDT 2014
2560 | Complete Roof slab of Up track cut and cover tunnel | Thu Feb 05 17:00:00 IST 2015 | Thu Feb 05 17:00:00 IST 2015
2561 | Achieve Degree 1 completion for the Up track cut and cover tunnel | Fri Mar 13 17:00:00 IST 2015 | Fri Mar 13 17:00:00 IST 2015
2562 | Complete backfill and reinstatement at Works Areas 12.2 and 13.48 | Thu Aug 06 17:00:00 IDT 2015 | Thu Aug 06 17:00:00 IDT 2015
2563 | Construction | Thu Nov 07 08:00:00 IST 2013 | Thu Aug 06 17:00:00 IDT 2015
2564 | Down Track Cut & Cover Tunnel | Thu Nov 07 08:00:00 IST 2013 | Thu May 22 17:00:00 IDT 2014
2565 | TBM (S630-1) Backup Removal D/T | Sun Nov 10 17:00:00 IST 2013 | Sun Nov 10 17:00:00 IST 2013
2566 | Mobilization and Site Preparation works | Thu Nov 07 08:00:00 IST 2013 | Sat Nov 30 17:00:00 IST 2013
2567 | Clear Backfilled B5 and Trim to Formation Level | Thu Nov 07 08:00:00 IST 2013 | Mon Nov 18 17:00:00 IST 2013
2568 | Drill holes for mass infill wall | Mon Nov 18 08:00:00 IST 2013 | Fri Nov 22 17:00:00 IST 2013
2569 | Construction of Mass Infill Wall | Sat Nov 23 08:00:00 IST 2013 | Fri Dec 13 17:00:00 IST 2013
2570 | Waterproofing to Interface of TBM Tunnel & 811A | Thu Dec 19 08:00:00 IST 2013 | Sat Dec 21 17:00:00 IST 2013
2571 | Construction of Base Slab | Tue Dec 24 08:00:00 IST 2013 | Tue Jan 14 17:00:00 IST 2014
2572 | Curing, CJ preparation & Dismantle base slab formwork | Sat Jan 25 08:00:00 IST 2014 | Thu Jan 30 17:00:00 IST 2014
2573 | Construction of Lower Portion Wall | Sat Jan 25 08:00:00 IST 2014 | Wed Feb 05 17:00:00 IST 2014
2574 | Curing, CJ preparation & Dismantle wall formwork | Fri Mar 07 08:00:00 IST 2014 | Wed Mar 12 17:00:00 IST 2014
2575 | Construction of Upper Portion Wall & Roof Slab | Fri Mar 07 08:00:00 IST 2014 | Sat Mar 29 17:00:00 IDT 2014
2576 | Curing for Upper Portion Wall & Roof Slab | Wed Apr 02 08:00:00 IDT 2014 | Tue Apr 15 17:00:00 IDT 2014
2577 | Dismantle falsework and formwork | Wed Apr 09 08:00:00 IDT 2014 | Mon Apr 14 17:00:00 IDT 2014
2578 | Construction of Walkway | Fri May 02 08:00:00 IDT 2014 | Thu May 22 17:00:00 IDT 2014
2579 | 811A C&C D/T- Degree 1 works | Wed Apr 09 08:00:00 IDT 2014 | Wed Apr 30 17:00:00 IDT 2014
2580 | Up Track Cut & Cover Tunnel | Wed Jul 02 08:00:00 IDT 2014 | Fri Mar 06 17:00:00 IST 2015
2581 | TBM (S630-1) & Backup Removal U/T | Wed Nov 19 17:00:00 IST 2014 | Wed Nov 19 17:00:00 IST 2014
2582 | Re-mobilization and Site Preparation works | Thu Nov 20 08:00:00 IST 2014 | Wed Nov 26 17:00:00 IST 2014
2583 | Clear Backfilled B5 and Trim to Formation Level | Wed Jul 02 08:00:00 IDT 2014 | Tue Jul 08 17:00:00 IDT 2014
2584 | Drill holes for mass infill wall | Thu Nov 27 08:00:00 IST 2014 | Tue Dec 02 17:00:00 IST 2014
2585 | Construction of Mass Infill Wall | Sat Jan 03 08:00:00 IST 2015 | Fri Jan 16 17:00:00 IST 2015
2586 | Waterproofing to Interface of TBM Tunnel & 811A | Wed Dec 17 08:00:00 IST 2014 | Fri Dec 19 17:00:00 IST 2014
2587 | Construction of Base Slab | Sat Dec 20 08:00:00 IST 2014 | Sat Jan 03 17:00:00 IST 2015
2588 | Curing, CJ preparation & Dismantle base slab formwork | Mon Jan 05 08:00:00 IST 2015 | Fri Jan 09 17:00:00 IST 2015
2589 | Construction of Lower Portion Wall | Fri Jan 09 08:00:00 IST 2015 | Thu Jan 15 17:00:00 IST 2015
2590 | Curing, CJ preparation & Dismantle wall formwork | Fri Jan 16 08:00:00 IST 2015 | Wed Jan 21 17:00:00 IST 2015
2591 | Construction of Upper Portion Wall & Roof Slab | Thu Jan 22 08:00:00 IST 2015 | Fri Feb 13 17:00:00 IST 2015
2592 | Curing for Upper Portion Wall & Roof Slab | Sat Jan 31 08:00:00 IST 2015 | Wed Feb 11 17:00:00 IST 2015
2593 | Dismantle falsework and formwork | Fri Feb 06 08:00:00 IST 2015 | Tue Feb 10 17:00:00 IST 2015
2594 | Construction of Walkway | Wed Feb 11 08:00:00 IST 2015 | Mon Mar 02 17:00:00 IST 2015
2595 | 811A C&C U/T- Degree 1 works (Target: 25Jan15) | Mon Feb 16 08:00:00 IST 2015 | Fri Mar 06 17:00:00 IST 2015
2596 | Backfilling & Re-instatement | Wed Mar 25 08:00:00 IST 2015 | Thu Aug 06 17:00:00 IDT 2015
2597 | D/T & U/T: Second Cast Concrete | Tue Jun 16 08:00:00 IDT 2015 | Wed Jul 08 17:00:00 IDT 2015
2598 | Backfilling to +4.5mPD | Wed Mar 25 08:00:00 IST 2015 | Sat May 16 17:00:00 IDT 2015
2599 | Re-instatement and Make Good | Sat Jul 25 08:00:00 IDT 2015 | Thu Aug 06 17:00:00 IDT 2015
2600 | Injection of PU grouting at the interface of TBM & C&C tunnel (both D/T & U/T) | Sat Jul 25 08:00:00 IDT 2015 | Thu Aug 06 17:00:00 IDT 2015
2601 | Backfilling from +4.5mPD to Ground Level | Thu Jul 09 08:00:00 IDT 2015 | Fri Jul 24 17:00:00 IDT 2015
1 | 820 As-built Programme | Wed May 12 08:00:00 IDT 2010 | Tue May 10 17:00:00 IDT 2016
2 | General | Sat Jan 08 08:00:00 IST 2011 | Tue Jan 26 17:00:00 IST 2016
3 | Schedule of Key Dates | Sat Jan 08 08:00:00 IST 2011 | Tue Jan 26 17:00:00 IST 2016
4 | General | Sat Jan 08 08:00:00 IST 2011 | Tue Jan 26 17:00:00 IST 2016
5 | Letter of Acceptance | Sat Jan 08 08:00:00 IST 2011 | Sat Jan 08 08:00:00 IST 2011
6 | Date of Commencement | Sat Jan 08 08:00:00 IST 2011 | Sat Jan 08 08:00:00 IST 2011
7 | Completion whole of the Works (Excluding Options I3 & I4) | Sun May 10 17:00:00 IDT 2015 | Sun May 10 17:00:00 IDT 2015
8 | Completion whole of the Works (Including Options I3 & I4) | Tue Jan 26 17:00:00 IST 2016 | Tue Jan 26 17:00:00 IST 2016
9 | Table 4 - Specified Degress of completion of the Works | Sun Aug 18 17:00:00 IDT 2013 | Sun Apr 19 17:00:00 IDT 2015
10 | Target Dates for Supplementary Agreement No.3 | Sun May 18 17:00:00 IDT 2014 | Sun Apr 19 17:00:00 IDT 2015
11 | Deg.1 Completion (Target Dates) | Sun May 18 17:00:00 IDT 2014 | Sun Apr 19 17:00:00 IDT 2015
12 | Ref.4A(ii): D/TTunnel from CH137+860 to Southern Contract Limit & 811A D/T C&C Section(Deg.1:20-Jul-14&Target:18-May-14) | Sun May 18 17:00:00 IDT 2014 | Sun May 18 17:00:00 IDT 2014
13 | Ref.4B(i): Up Track tunnel from the Northern Contract Limit to CH137+860 (Deg.1: 29-Jun-14 & Target: 1-Jun-14) | Sun Jun 29 08:00:00 IDT 2014 | Sun Jun 29 08:00:00 IDT 2014
14 | Ref.4B(ii): U/T South Tunnel from CH137+860 to 950m from the Southern Contract Limit (Deg.1: 8Mar15 & Target: 21Dec14) | Tue Dec 16 17:00:00 IST 2014 | Tue Dec 16 17:00:00 IST 2014
15 | Ref.4B(iii): U/T Tunnel from CH137+860 to Southern Contract Limit & 811A U/T C&C Section(Deg.1: 12Apr15&Target: 25Jan15) | Fri Mar 13 17:00:00 IST 2015 | Fri Mar 13 17:00:00 IST 2015
16 | Ref.4D: Closure of Temp. Access Opening & Central Opening Structure within NAC Shaft (Deg.1: 3May15 & Target: 19Apr15) | Sun Apr 19 17:00:00 IDT 2015 | Sun Apr 19 17:00:00 IDT 2015
17 | Completion of Specified Degrees of Completion of the Works | Sun Aug 18 17:00:00 IDT 2013 | Sun Apr 19 17:00:00 IDT 2015
18 | Deg.1 Completion | Sun Aug 18 17:00:00 IDT 2013 | Sun Apr 19 17:00:00 IDT 2015
19 | Ref.4A(i): Down Track tunnel from the Northern Contract Limit to CH137+860 incl. provision of Temp. access opening | Sun Aug 18 17:00:00 IDT 2013 | Sun Aug 18 17:00:00 IDT 2013
20 | Ref.4C(i): All Rooms and Common Areas at Level L2, UL2, L1 and UL1 (Excl. staircases, Lift shaft & CLP risers) | Sun Dec 22 17:00:00 IST 2013 | Sun Dec 22 17:00:00 IST 2013
21 | Ref.4C(ii): All Rooms and Common Areas at Track level and Above Track level(Excl. staircases, Lift shaft & CLP risers) | Sun Mar 02 17:00:00 IST 2014 | Sun Mar 02 17:00:00 IST 2014
22 | Ref.4C(iii): All Rooms and Common Areas within VB7 [Excl. the parts of the VB7 under Ref. 4C(i) & 4C(ii)] | Sat May 31 17:00:00 IDT 2014 | Sat May 31 17:00:00 IDT 2014
23 | Ref.4B(i): Up Track tunnel from the Northern Contract Limit to CH137+860 (Deg.1: 29-Jun-14 & Target: 1-Jun-14) | Sun Jun 29 17:00:00 IDT 2014 | Sun Jun 29 17:00:00 IDT 2014
24 | Ref.4A(ii): D/TTunnel from CH137+860 to Southern Contract Limit & 811A D/T C&C Section(Deg.1:20-Jul-14&Target:18-May-14) | Sun May 18 17:00:00 IDT 2014 | Sun May 18 17:00:00 IDT 2014
25 | Ref.4B(ii): U/T South Tunnel from CH137+860 to 950m from the Southern Contract Limit (Deg.1: 8Mar15 & Target: 21Dec14) | Tue Dec 16 17:00:00 IST 2014 | Tue Dec 16 17:00:00 IST 2014
26 | Ref.4B(iii): U/T Tunnel from CH137+860 to Southern Contract Limit & 811A U/T C&C Section(Deg.1: 12Apr15&Target: 25Jan15) | Fri Mar 13 17:00:00 IST 2015 | Fri Mar 13 17:00:00 IST 2015
27 | Ref.4D: Closure of Temp. Access Opening & Central Opening Structure within NAC Shaft (Deg.1: 3May15 & Target: 19Apr15) | Sun Apr 19 17:00:00 IDT 2015 | Sun Apr 19 17:00:00 IDT 2015
28 | Deg.2 Completion | Sun Feb 23 17:00:00 IST 2014 | Wed Jul 23 17:00:00 IDT 2014
29 | Ref.4C(i) Deg.2: All Rooms and Common Areas at Level L2, UL2, L1 and UL1 (Excl. staircases, Lift shaft & CLP risers) | Sun Feb 23 17:00:00 IST 2014 | Sun Feb 23 17:00:00 IST 2014
30 | Ref.4C(ii) Deg.2: All Rooms and Common Areas at Track level and AT level(Excl. staircases, Lift shaft & CLP risers) | Sun Mar 23 17:00:00 IST 2014 | Sun Mar 23 17:00:00 IST 2014
31 | Ref.4C(iii) Deg.2: All Rooms and Common Areas within VB7 [Excl. the parts of the VB7 under Ref. 4C(i) & 4C(ii)] | Wed Jul 23 17:00:00 IDT 2014 | Wed Jul 23 17:00:00 IDT 2014
32 | Deg.3 Completion | Sun Apr 20 17:00:00 IDT 2014 | Thu Sep 18 17:00:00 IDT 2014
33 | Ref.4C(i) Deg.3: All Rooms and Common Areas at Level L1, UL2, L1 and UL1 (Excl. staircases, Lift shaft & CLP risers) | Sun Apr 20 17:00:00 IDT 2014 | Sun Apr 20 17:00:00 IDT 2014
34 | Ref.4C(ii) Deg.3: All Rooms and Common Areas at Track level and AT level(Excl. staircases, Lift shaft & CLP risers) | Sun May 18 17:00:00 IDT 2014 | Sun May 18 17:00:00 IDT 2014
35 | Ref.4C(iii) Deg.3: All Rooms and Common Areas within VB7 [Excl. the parts of the VB7 under Ref. 4C(i) & 4C(ii)] | Thu Sep 18 17:00:00 IDT 2014 | Thu Sep 18 17:00:00 IDT 2014
36 | Schedule of Access Dates and Vacation Dates | Sat May 15 08:00:00 IDT 2010 | Tue May 10 17:00:00 IDT 2016
37 | Access Date | Sat May 15 08:00:00 IDT 2010 | Mon Jan 21 08:00:00 IST 2013
38 | General | Sat May 15 08:00:00 IDT 2010 | Mon Jan 21 08:00:00 IST 2013
39 | Works Area 10.1 (Subject to SLG Approval) | Sat Jan 08 08:00:00 IST 2011 | Sat Jan 08 08:00:00 IST 2011
40 | Works Area 10.2 | Sat Jan 08 08:00:00 IST 2011 | Sat Jan 08 08:00:00 IST 2011
41 | Works Area 10.3 | Sat Jan 08 08:00:00 IST 2011 | Sat Jan 08 08:00:00 IST 2011
42 | Works Area 10.3U subject to MTR Railway Operation Approval | Thu Sep 29 08:00:00 IDT 2011 | Thu Sep 29 08:00:00 IDT 2011
43 | Works Area 10.4 | Sat Jan 08 08:00:00 IST 2011 | Sat Jan 08 08:00:00 IST 2011
44 | Works Area 11.1 | Mon Apr 09 08:00:00 IDT 2012 | Mon Apr 09 08:00:00 IDT 2012
45 | Works Area 11.2 | Mon Apr 09 08:00:00 IDT 2012 | Mon Apr 09 08:00:00 IDT 2012
46 | Works Area 11.10A | Mon Feb 06 08:00:00 IST 2012 | Mon Feb 06 08:00:00 IST 2012
47 | Works Area 11.10B | Mon Feb 06 08:00:00 IST 2012 | Mon Feb 06 08:00:00 IST 2012
48 | Works Area 11.12 (Subject to SLG Approval) | Sat Jan 08 08:00:00 IST 2011 | Sat Jan 08 08:00:00 IST 2011
49 | Works Area 11.13 (conform by Engineer) | Mon Dec 31 08:00:00 IST 2012 | Mon Dec 31 08:00:00 IST 2012
50 | Works Area 11.14 | Mon Dec 10 08:00:00 IST 2012 | Mon Dec 10 08:00:00 IST 2012
51 | Works Area 11.15 (Subject to SLG Approval) | Sat Jan 08 08:00:00 IST 2011 | Sat Jan 08 08:00:00 IST 2011
52 | Works Area 11.21 (Subject to SLG Approval) | Sat Jan 08 08:00:00 IST 2011 | Sat Jan 08 08:00:00 IST 2011
53 | Works Area 11.21A (Subject to SLG Approval) | Wed Aug 31 08:00:00 IDT 2011 | Wed Aug 31 08:00:00 IDT 2011
54 | Works Area 11.22 | Sat Jan 08 08:00:00 IST 2011 | Sat Jan 08 08:00:00 IST 2011
55 | Works Area 11.23 | Sat Jan 08 08:00:00 IST 2011 | Sat Jan 08 08:00:00 IST 2011
56 | Works Area 11.23A | Sat Jan 08 08:00:00 IST 2011 | Sat Jan 08 08:00:00 IST 2011
57 | Works Area 11.23B | Sat Jan 08 08:00:00 IST 2011 | Sat Jan 08 08:00:00 IST 2011
58 | Works Area 11.24 (1st Possession) | Sat Jan 08 08:00:00 IST 2011 | Sat Jan 08 08:00:00 IST 2011
59 | Works Area 11.25 (1st Posssession) | Sat Jan 08 08:00:00 IST 2011 | Sat Jan 08 08:00:00 IST 2011
60 | Works Area 11.26A | Sat Jan 08 08:00:00 IST 2011 | Sat Jan 08 08:00:00 IST 2011
61 | Works Area 11.26B | Sat Jan 08 08:00:00 IST 2011 | Sat Jan 08 08:00:00 IST 2011
62 | Works Area 11.26C | Sat Jan 08 08:00:00 IST 2011 | Sat Jan 08 08:00:00 IST 2011
63 | Works Area 11.27 (Subject to SLG Approval) | Sat Jan 08 08:00:00 IST 2011 | Sat Jan 08 08:00:00 IST 2011
64 | Wks Area 11.28-180day from Contractor's Confirm | Mon Jan 21 08:00:00 IST 2013 | Mon Jan 21 08:00:00 IST 2013
65 | Works Area 11.29A | Sat Jan 08 08:00:00 IST 2011 | Sat Jan 08 08:00:00 IST 2011
66 | Works Area 11.29B | Sat Jan 08 08:00:00 IST 2011 | Sat Jan 08 08:00:00 IST 2011
67 | Works Area 11.29C | Sat May 15 08:00:00 IDT 2010 | Sat May 15 08:00:00 IDT 2010
68 | Works Area 11.29D | Sat May 15 08:00:00 IDT 2010 | Sat May 15 08:00:00 IDT 2010
69 | Works Area 11.29E | Sat May 15 08:00:00 IDT 2010 | Sat May 15 08:00:00 IDT 2010
70 | Works Area 11.29F | Sat May 15 08:00:00 IDT 2010 | Sat May 15 08:00:00 IDT 2010
71 | Works Area 11.29G | Sat May 15 08:00:00 IDT 2010 | Sat May 15 08:00:00 IDT 2010
72 | Works Area 11.30 | Sat May 15 08:00:00 IDT 2010 | Sat May 15 08:00:00 IDT 2010
73 | Works Area 11.31 | Sat May 15 08:00:00 IDT 2010 | Sat May 15 08:00:00 IDT 2010
74 | Works Area 11.32 | Sat May 15 08:00:00 IDT 2010 | Sat May 15 08:00:00 IDT 2010
75 | Works Area 11.33A | Sat May 15 08:00:00 IDT 2010 | Sat May 15 08:00:00 IDT 2010
76 | Works Area 11.33B | Sat May 15 08:00:00 IDT 2010 | Sat May 15 08:00:00 IDT 2010
77 | Works Area 12.1 (Subject to SLG Approval) | Sat Jan 08 08:00:00 IST 2011 | Sat Jan 08 08:00:00 IST 2011
78 | Works Area 12.2 | Fri Nov 30 08:00:00 IST 2012 | Fri Nov 30 08:00:00 IST 2012
79 | Proposed Return Date | Sun May 31 08:00:00 IDT 2015 | Thu Dec 24 17:00:00 IST 2015
80 | Site 6 | Thu Dec 24 17:00:00 IST 2015 | Thu Dec 24 17:00:00 IST 2015
81 | Proposed Return date of Works Area 11.23 (820 Site Office & Site 6) | Thu Dec 24 17:00:00 IST 2015 | Thu Dec 24 17:00:00 IST 2015
82 | Proposed Return date of Works Area 11.23A (Site 6) | Thu Dec 24 17:00:00 IST 2015 | Thu Dec 24 17:00:00 IST 2015
83 | Proposed Return date of Works Area 11.23B (Site 6) | Thu Dec 24 17:00:00 IST 2015 | Thu Dec 24 17:00:00 IST 2015
84 | Proposed Return date of Works Area 11.24 (Site 6) | Thu Dec 24 17:00:00 IST 2015 | Thu Dec 24 17:00:00 IST 2015
85 | Barging Point | Sun May 31 08:00:00 IDT 2015 | Sun May 31 08:00:00 IDT 2015
86 | Proposed Return date of Works Area 11.29A (Barging point) | Sun May 31 08:00:00 IDT 2015 | Sun May 31 08:00:00 IDT 2015
87 | Proposed Return date of Works Area 11.29D (Barging point) | Sun May 31 08:00:00 IDT 2015 | Sun May 31 08:00:00 IDT 2015
88 | Proposed Return date of Works Area 11.29E (Barging point) | Sun May 31 08:00:00 IDT 2015 | Sun May 31 08:00:00 IDT 2015
89 | Proposed Return date of Works Area 11.29F (Barging point) | Sun May 31 08:00:00 IDT 2015 | Sun May 31 08:00:00 IDT 2015
90 | 811A Shaft | Thu Aug 27 17:00:00 IDT 2015 | Thu Aug 27 17:00:00 IDT 2015
91 | Proposed Return date of Works Area 12.2 (811A shaft area) | Thu Aug 27 17:00:00 IDT 2015 | Thu Aug 27 17:00:00 IDT 2015
92 | Return date | Mon Feb 28 08:00:00 IST 2011 | Tue May 10 17:00:00 IDT 2016
93 | General | Mon Feb 28 08:00:00 IST 2011 | Tue May 10 17:00:00 IDT 2016
94 | Works Area 10.1 (Subject to SLG Approval) | Sun May 31 08:00:00 IDT 2015 | Sun May 31 08:00:00 IDT 2015
95 | Works Area 10.2 | Sun May 31 08:00:00 IDT 2015 | Sun May 31 08:00:00 IDT 2015
96 | Works Area 10.3 | Sun May 31 08:00:00 IDT 2015 | Sun May 31 08:00:00 IDT 2015
97 | Works Area 10.3U subject to MTR Approval | Sun May 31 08:00:00 IDT 2015 | Sun May 31 08:00:00 IDT 2015
98 | Works Area 10.4 | Sun May 31 08:00:00 IDT 2015 | Sun May 31 08:00:00 IDT 2015
99 | Works Area 11.1 (Nan cheong Station - by XRL802) | Sun Dec 30 17:00:00 IST 2012 | Sun Dec 30 17:00:00 IST 2012
100 | Works Area 11.2 (Nan cheong Station - by XRL802) | Sun Dec 30 17:00:00 IST 2012 | Sun Dec 30 17:00:00 IST 2012
101 | Works Area 11.10A | Tue Sep 10 17:00:00 IDT 2013 | Tue Sep 10 17:00:00 IDT 2013
102 | Works Area 11.10B | Sun May 31 08:00:00 IDT 2015 | Sun May 31 08:00:00 IDT 2015
103 | Works Area 11.12 (Subject to SLG Approval) | Sun May 31 08:00:00 IDT 2015 | Sun May 31 08:00:00 IDT 2015
104 | Works Area 11.13 (Earliest) | Sun Dec 29 17:00:00 IST 2013 | Sun Dec 29 17:00:00 IST 2013
105 | Works Area 11.13 (Latest) | Sun May 31 08:00:00 IDT 2015 | Sun May 31 08:00:00 IDT 2015
106 | Works Area 11.14 | Sun May 31 08:00:00 IDT 2015 | Sun May 31 08:00:00 IDT 2015
107 | Works Area 11.15 (Subject to SLG Approval) | Sun May 31 08:00:00 IDT 2015 | Sun May 31 08:00:00 IDT 2015
108 | Works Area 11.21 (Subject to SLG Approval) | Sun May 31 08:00:00 IDT 2015 | Sun May 31 08:00:00 IDT 2015
109 | Works Area 11.21A (Subject to SLG Approval) | Sun May 31 08:00:00 IDT 2015 | Sun May 31 08:00:00 IDT 2015
110 | Works Area 11.22 | Sun Dec 27 17:00:00 IST 2015 | Sun Dec 27 17:00:00 IST 2015
111 | Works Area 11.23 (Site 6) | Sun May 31 08:00:00 IDT 2015 | Sun May 31 08:00:00 IDT 2015
112 | Works Area 11.23A (Site 6) (excl. Optional Works I3 & I4) | Mon Aug 24 17:00:00 IDT 2015 | Mon Aug 24 17:00:00 IDT 2015
113 | Works Area 11.23B (Site 6) (excl. Optional Works I3 & I4) | Mon Aug 24 17:00:00 IDT 2015 | Mon Aug 24 17:00:00 IDT 2015
114 | Works Area 11.24 (Site 6) (Earliest) | Sun Mar 31 17:00:00 IDT 2013 | Sun Mar 31 17:00:00 IDT 2013
115 | Works Area 11.24 (Site 6) (Latest) | Mon Aug 24 17:00:00 IDT 2015 | Mon Aug 24 17:00:00 IDT 2015
116 | Works Area 11.25 (Site 6) (Earliest) | Sun Mar 31 17:00:00 IDT 2013 | Sun Mar 31 17:00:00 IDT 2013
117 | Works Area 11.25 (Latest) | Sun Apr 03 17:00:00 IDT 2016 | Sun Apr 03 17:00:00 IDT 2016
118 | Works Area 11.26A (excl. Optional Works I3 & I4) | Sun Apr 03 17:00:00 IDT 2016 | Sun Apr 03 17:00:00 IDT 2016
119 | Works Area 11.26B | Sun Apr 03 17:00:00 IDT 2016 | Sun Apr 03 17:00:00 IDT 2016
120 | Works Area 11.26C | Sun Apr 03 17:00:00 IDT 2016 | Sun Apr 03 17:00:00 IDT 2016
121 | Works Area 11.27 (Subject to SLG Approval) | Tue Aug 11 17:00:00 IDT 2015 | Tue Aug 11 17:00:00 IDT 2015
122 | Wks Area 11.28 | Sun May 31 08:00:00 IDT 2015 | Sun May 31 08:00:00 IDT 2015
123 | Works Area 11.29A | Sun May 31 08:00:00 IDT 2015 | Sun May 31 08:00:00 IDT 2015
124 | Works Area 11.29B | Mon Feb 28 08:00:00 IST 2011 | Mon Feb 28 08:00:00 IST 2011
125 | Works Area 11.29C | Mon Feb 28 08:00:00 IST 2011 | Mon Feb 28 08:00:00 IST 2011
126 | Works Area 11.29D | Sun May 31 08:00:00 IDT 2015 | Sun May 31 08:00:00 IDT 2015
127 | Works Area 11.29E | Sun May 31 08:00:00 IDT 2015 | Sun May 31 08:00:00 IDT 2015
128 | Works Area 11.29F | Sun May 31 08:00:00 IDT 2015 | Sun May 31 08:00:00 IDT 2015
129 | Works Area 11.29G | Mon Feb 28 08:00:00 IST 2011 | Mon Feb 28 08:00:00 IST 2011
130 | Works Area 11.30 | Sun Dec 29 17:00:00 IST 2013 | Sun Dec 29 17:00:00 IST 2013
131 | Works Area 11.31 | Sun May 31 08:00:00 IDT 2015 | Sun May 31 08:00:00 IDT 2015
132 | Works Area 11.32 | Sun May 31 08:00:00 IDT 2015 | Sun May 31 08:00:00 IDT 2015
133 | Works Area 11.33A | Tue May 10 17:00:00 IDT 2016 | Tue May 10 17:00:00 IDT 2016
134 | Works Area 11.33B | Tue May 10 17:00:00 IDT 2016 | Tue May 10 17:00:00 IDT 2016
135 | Works Area 12.1 (Subject to SLG Approval) | Tue May 10 17:00:00 IDT 2016 | Tue May 10 17:00:00 IDT 2016
136 | Works Area 12.2 (811A shaft area) | Sun May 31 08:00:00 IDT 2015 | Sun May 31 08:00:00 IDT 2015
137 | Access & Return Dates for Option I3 & I4 | Sat Jan 08 08:00:00 IST 2011 | Sun Apr 03 17:00:00 IDT 2016
138 | General | Sat Jan 08 08:00:00 IST 2011 | Sun Apr 03 17:00:00 IDT 2016
139 | Works Area 11.23B | Sat Jan 08 08:00:00 IST 2011 | Sat Jan 08 08:00:00 IST 2011
140 | Works Area 11.26A | Sat Jan 08 08:00:00 IST 2011 | Sat Jan 08 08:00:00 IST 2011
141 | Works Area 11.26B | Sat Jan 08 08:00:00 IST 2011 | Sat Jan 08 08:00:00 IST 2011
142 | Works Area 11.23B | Sun Nov 22 17:00:00 IST 2015 | Sun Nov 22 17:00:00 IST 2015
143 | Works Area 11.26A | Sun Apr 03 17:00:00 IDT 2016 | Sun Apr 03 17:00:00 IDT 2016
144 | Works Area 11.26B | Sun Apr 03 17:00:00 IDT 2016 | Sun Apr 03 17:00:00 IDT 2016
145 | Programme Data | Mon Feb 28 08:00:00 IST 2011 | Fri Jul 24 17:00:00 IDT 2015
146 | Schedule of Power On Dates | Thu Feb 05 17:00:00 IST 2015 | Thu Feb 05 17:00:00 IST 2015
147 | Permanent LV Power On | Thu Feb 05 17:00:00 IST 2015 | Thu Feb 05 17:00:00 IST 2015
148 | General
149 | Works Required for Statutory Inspection | Fri Jul 24 17:00:00 IDT 2015 | Fri Jul 24 17:00:00 IDT 2015
150 | Complete all External Water works within the Site and Connect to Governemnt Water Mains | Fri Jul 24 17:00:00 IDT 2015 | Fri Jul 24 17:00:00 IDT 2015
151 | Complete all External Telephone Drawpits and Ducts within the Site | Fri Jul 24 17:00:00 IDT 2015 | Fri Jul 24 17:00:00 IDT 2015
152 | General
153 | Temporary Access Opening for Designated Contractors | Mon Aug 26 08:00:00 IDT 2013 | Sun Jan 04 17:00:00 IST 2015
154 | Access Central Opening within Launching Shaft | Mon Aug 26 08:00:00 IDT 2013 | Sun Jan 04 17:00:00 IST 2015
155 | General
156 | Close out Temporary Access Opening & Structure within Launching Shaft | Sun Dec 01 08:00:00 IST 2013 | Sun May 31 08:00:00 IDT 2015
157 | Area 1 - South Opening, South D/T | Sun Dec 01 08:00:00 IST 2013 | Sun May 18 17:00:00 IDT 2014
158 | Area 1 - Walkway, Side Walls and Above-Track Roof Slab | Sun Dec 01 08:00:00 IST 2013 | Sun May 18 17:00:00 IDT 2014
159 | Area 2 - Central Opening, South D/T | Mon May 19 08:00:00 IDT 2014 | Sun Jun 15 17:00:00 IDT 2014
160 | Area 2 - 1st cast for Walkway and External wall (Dkb137+850 to 137+885) | Mon May 19 08:00:00 IDT 2014 | Sun Jun 15 17:00:00 IDT 2014
161 | Area 3 - South Opening, South U/T | Mon Sep 01 08:00:00 IDT 2014 | Sun Dec 21 17:00:00 IST 2014
162 | Area 3 - 1st cast for Walkway, External wall and Internal wall | Mon Sep 01 08:00:00 IDT 2014 | Sun Dec 21 17:00:00 IST 2014
163 | Area 3 - 2nd cast for Above-Track Roof Slab | Sat Nov 15 08:00:00 IST 2014 | Fri Dec 19 17:00:00 IST 2014
164 | Area 4A - Central Opening, South U/T | Mon Dec 29 08:00:00 IST 2014 | Sun Jan 25 17:00:00 IST 2015
165 | Area 4A - Walkway and External wall (Dkb137+850 to 137+885) | Mon Dec 29 08:00:00 IST 2014 | Sun Jan 25 17:00:00 IST 2015
166 | Area 4B - Central Opening | Mon Dec 29 08:00:00 IST 2014 | Sun Feb 08 17:00:00 IST 2015
167 | Area 4B - 2nd cast for Internal walls and Central portion of Above-Track Roof Slab with falsework | Mon Dec 29 08:00:00 IST 2014 | Sun Feb 08 17:00:00 IST 2015
168 | Area 4C - Central Opening and Access for 830 Works Train | Mon Dec 29 08:00:00 IST 2014 | Sun Apr 19 17:00:00 IDT 2015
169 | Area 4C - Close remaining Above-Track Roof Slab & RC duct btw Dkb137+850 to 137+885 | Mon Dec 29 08:00:00 IST 2014 | Sun Apr 19 17:00:00 IDT 2015
170 | Site 6 - Surafce Works Area under 30T Gantry Crane at Central Opening | Sun May 31 08:00:00 IDT 2015 | Sun May 31 08:00:00 IDT 2015
171 | Site 6 - Access to works area under 30T gantry to be given to 830 | Sun May 31 08:00:00 IDT 2015 | Sun May 31 08:00:00 IDT 2015
172 | Area 5 - 811A C&C Tunnel
173 | TBM Retrieval Shaft at Hoi Ting Road | Mon Feb 28 08:00:00 IST 2011 | Sun Jun 19 17:00:00 IDT 2011
174 | General | Mon Feb 28 08:00:00 IST 2011 | Sun Jun 19 17:00:00 IDT 2011
175 | Completion D-Wall of TBM Retrieval Shaft at Hoi Ting Rd. by 811A | Mon Feb 28 08:00:00 IST 2011 | Mon Feb 28 08:00:00 IST 2011
176 | Earliest Access Date - Ground Level of Works Area 12.2 | Mon Feb 28 08:00:00 IST 2011 | Mon Feb 28 08:00:00 IST 2011
177 | Ground Treatment Completion by 820 | Sun Jun 19 17:00:00 IDT 2011 | Sun Jun 19 17:00:00 IDT 2011
178 | Obstruction Removed by Other Project Contractor | Sun Jan 15 08:00:00 IST 2012 | Tue Apr 30 17:00:00 IDT 2013
179 | General | Sun Jan 15 08:00:00 IST 2012 | Tue Apr 30 17:00:00 IDT 2013
180 | D/T Remove Obstructions Below Nam Cheong Property Development (by XRL 802) | Mon Apr 30 17:00:00 IDT 2012 | Mon Apr 30 17:00:00 IDT 2012
181 | U/T Remove Obstructions Below Nam Cheong Property Development (by XRL 802) | Tue Apr 30 17:00:00 IDT 2013 | Tue Apr 30 17:00:00 IDT 2013
182 | Remove Obstructions Below CLP Equipment Building (by XRL 805) | Sun Jan 15 08:00:00 IST 2012 | Sun Jan 15 08:00:00 IST 2012
183 | Engineer's Office | Sun Apr 17 17:00:00 IDT 2011 | Sun Apr 17 17:00:00 IDT 2011
184 | General | Sun Apr 17 17:00:00 IDT 2011 | Sun Apr 17 17:00:00 IDT 2011
185 | Engineer's Office Completion with Furniture | Sun Apr 17 17:00:00 IDT 2011 | Sun Apr 17 17:00:00 IDT 2011
186 | Access Dates for Designated Contractors | Mon Aug 19 08:00:00 IDT 2013 | Mon Apr 27 08:00:00 IDT 2015
187 | 827 - Supply and Installation of Cross Passage Doors | Mon Aug 26 08:00:00 IDT 2013 | Mon Jan 26 08:00:00 IST 2015
188 | 827 - D/T All Cross Passages for Door Frame & Door Installation, from CH137+860 to Southern contract limit | Mon May 19 08:00:00 IDT 2014 | Mon May 19 08:00:00 IDT 2014
189 | 827 - D/T All Cross Passages for Door Frame and Door installation, from northern contract limit to CH137+860 | Mon Aug 26 08:00:00 IDT 2013 | Mon Aug 26 08:00:00 IDT 2013
190 | 827 - U/T All Cross Passages for Door Frame & Door Installation, from Northern contract limit to CH137+860 | Mon Jun 02 08:00:00 IDT 2014 | Mon Jun 02 08:00:00 IDT 2014
191 | 827 - U/T All Cross Passages for Door Frame & Door Installation, from CH137+860 to 950m from the Southern contract limit | Mon Dec 22 08:00:00 IST 2014 | Mon Dec 22 08:00:00 IST 2014
192 | 827 - U/T All Cross Passages for Door Frame & Door Installation, from CH137+860 to the Southern contract limit | Mon Jan 26 08:00:00 IST 2015 | Mon Jan 26 08:00:00 IST 2015
193 | 830 - Trackwork and Overhead Line System | Mon Aug 19 08:00:00 IDT 2013 | Mon Jan 26 08:00:00 IST 2015
194 | 830 - D/T Tunnel from the Northern contract limit to CH137+860 | Mon Aug 19 08:00:00 IDT 2013 | Mon Aug 19 08:00:00 IDT 2013
195 | 830 - D/T Tunnel from CH137+860 to Southern contract limit and C&C section within Hoi Ting Road Shaft | Mon May 19 08:00:00 IDT 2014 | Mon May 19 08:00:00 IDT 2014
196 | 830 - U/T Tunnel from the Northern contract limit to CH137+860 | Mon Jun 02 08:00:00 IDT 2014 | Mon Jun 02 08:00:00 IDT 2014
197 | 830 - U/T Tunnel from CH137+860 to 950m from the Southern contract limit | Mon Dec 22 08:00:00 IST 2014 | Mon Dec 22 08:00:00 IST 2014
198 | 830 - U/T Tunnel from CH137+860 to the Southern contract limit and C&C section within Hoi Ting Road Shaft | Mon Jan 26 08:00:00 IST 2015 | Mon Jan 26 08:00:00 IST 2015
199 | 841A - Signalling System - Trackside Equipment | Mon Apr 21 08:00:00 IDT 2014 | Mon Apr 27 08:00:00 IDT 2015
200 | 841A - U/T Tunnel from CH137+860 to the Southern contract limit and C&C section within Hoi Ting Road Shaft | Mon Apr 27 08:00:00 IDT 2015 | Mon Apr 27 08:00:00 IDT 2015
201 | 841A - U/T Tunnel from the Northern contract limit to CH137+860 | Sun Nov 30 08:00:00 IST 2014 | Sun Nov 30 08:00:00 IST 2014
202 | 841A - Nam Cheong Ventilation Building (VB7) - SER (Signalling-Trackside) | Mon Apr 21 08:00:00 IDT 2014 | Mon Apr 21 08:00:00 IDT 2014
203 | 841A - D/T Tunnel from the Northern contract limit to CH137+860 | Mon Jun 02 08:00:00 IDT 2014 | Mon Jun 02 08:00:00 IDT 2014
204 | 841A - D/T Tunnel from CH137+860 to the Southern contract limit and C&C section within Hoi Ting Road Shaft | Mon Sep 29 08:00:00 IDT 2014 | Mon Sep 29 08:00:00 IDT 2014
205 | 841B - Signalling System - Train Borne Equipment (Rolling Stock + Works / Rescue Trains) | Mon Apr 21 08:00:00 IDT 2014 | Mon Apr 27 08:00:00 IDT 2015
206 | 841B - U/T Tunnel from the Northern contract limit to CH137+860 (Signalling-Train Borne) | Mon Sep 29 08:00:00 IDT 2014 | Mon Sep 29 08:00:00 IDT 2014
207 | 841B - D/T Tunnel from the Northern contract limit to CH137+860 (Signalling-Train Borne) | Mon Jun 02 08:00:00 IDT 2014 | Mon Jun 02 08:00:00 IDT 2014
208 | 841B - Nam Cheong Ventilation Building (VB7) - SER (Signalling-Train Borne) | Mon Apr 21 08:00:00 IDT 2014 | Mon Apr 21 08:00:00 IDT 2014
209 | 841B - U/T Tunnel from CH137+860 to the Southern contract limit and C&C section within Hoi Ting Road Shaft | Mon Apr 27 08:00:00 IDT 2015 | Mon Apr 27 08:00:00 IDT 2015
210 | 841B - D/T Tunnel from CH137+860 to the Southern contract limit and C&C section within Hoi Ting Road Shaft | Mon Sep 29 08:00:00 IDT 2014 | Mon Sep 29 08:00:00 IDT 2014
211 | 843 - Tunnel Environmental Control System | Mon Feb 24 08:00:00 IST 2014 | Mon Apr 20 08:00:00 IDT 2015
212 | 843 - Nam Cheong Ventilation Building (VB7) - TVF Room and Compressed & Receiver Air Room | Mon Feb 24 08:00:00 IST 2014 | Mon Feb 24 08:00:00 IST 2014
213 | 843 - Nam Cheong Ventilation Building (VB7) - Tunnel ECS Control Room | Mon Jul 14 08:00:00 IDT 2014 | Mon Jul 14 08:00:00 IDT 2014
214 | 843 - Nam Cheong Ventilation Building (VB7) - Above track slab at both up and down tracks btw GL 1-9 | Mon Mar 24 08:00:00 IST 2014 | Mon Mar 24 08:00:00 IST 2014
215 | 843 - Nam Cheong Shaft C & C tunnels - Above track slab at both up and down tracks btw GL 9-16 | Mon Apr 20 08:00:00 IDT 2015 | Mon Apr 20 08:00:00 IDT 2015
216 | 844 - 11kV Power Distribution | Mon Jun 02 08:00:00 IDT 2014 | Mon Apr 27 08:00:00 IDT 2015
217 | 844 - D/T Tunnel from the Northern contract limit to CH137+860 (11kV Power) | Mon Jun 02 08:00:00 IDT 2014 | Mon Jun 02 08:00:00 IDT 2014
218 | 844 - D/T Tunnel from CH137+860 to Southern contract limit and C&C section within Hoi Ting Road Shaft (11kV Power) | Mon Sep 29 08:00:00 IDT 2014 | Mon Sep 29 08:00:00 IDT 2014
219 | 844 - U/T Tunnel from the Northern contract limit to CH137+860 (11kV Power) | Mon Sep 29 08:00:00 IDT 2014 | Mon Sep 29 08:00:00 IDT 2014
220 | 844 - U/T Tunnel from CH137+860 to the Southern contract limit and C&C section within Hoi Ting Road Shaft (11kV Power) | Mon Apr 27 08:00:00 IDT 2015 | Mon Apr 27 08:00:00 IDT 2015
221 | 844 - Nam Cheong Ventilation Building (VB7) - Power Supply Electrical Rooms (11kV Power) | Mon Sep 08 08:00:00 IDT 2014 | Mon Sep 08 08:00:00 IDT 2014
222 | 846 - Trackside Auxililaries | Mon Feb 24 08:00:00 IST 2014 | Mon Apr 27 08:00:00 IDT 2015
223 | 846 - D/T Tunnel from the Northern contract limit to CH137+860 (Trackside Aux.) | Mon Jun 02 08:00:00 IDT 2014 | Mon Jun 02 08:00:00 IDT 2014
224 | 846 - D/T Tunnel from CH137+860 to Southern contract limit and C&C section within Hoi Ting Road Shaft (Trackside Aux.) | Mon Sep 29 08:00:00 IDT 2014 | Mon Sep 29 08:00:00 IDT 2014
225 | 846 - U/T Tunnel from the Northern contract limit to CH137+860 (Trackside Aux.) | Mon Sep 29 08:00:00 IDT 2014 | Mon Sep 29 08:00:00 IDT 2014
226 | 846 - U/T Tunnel from CH137+860 to the Southern contract limit and C&C section within Hoi Ting Road Shaft | Mon Apr 27 08:00:00 IDT 2015 | Mon Apr 27 08:00:00 IDT 2015
227 | 846 - Nam Cheong Ventilation Building (VB7) Trackside LV Switch Room | Mon Feb 24 08:00:00 IST 2014 | Mon Feb 24 08:00:00 IST 2014
228 | 847 - Lifts | Mon Jul 14 08:00:00 IDT 2014 | Mon Jul 14 08:00:00 IDT 2014
229 | 847 - Nam Cheong Ventilation Building (VB7) - Lift Shaft adn Lift Machine Room | Mon Jul 14 08:00:00 IDT 2014 | Mon Jul 14 08:00:00 IDT 2014
230 | 849 - Radio Communications System | Mon Feb 24 08:00:00 IST 2014 | Mon Apr 27 08:00:00 IDT 2015
231 | 849 - Nam Cheong Ventilation Building (VB7) - TER and CTER (Radio Communications) | Mon Feb 24 08:00:00 IST 2014 | Mon Feb 24 08:00:00 IST 2014
232 | 849 - U/T Tunnel from the Northern contract limit to CH137+860 (Radio Communications) | Mon Sep 29 08:00:00 IDT 2014 | Mon Sep 29 08:00:00 IDT 2014
233 | 849 - U/T Tunnel from CH137+860 to the Southern contract limit and C&C section within Hoi Ting Road Shaft | Mon Apr 27 08:00:00 IDT 2015 | Mon Apr 27 08:00:00 IDT 2015
234 | 849 - Nam Cheong Ventilation Building (VB7) - SER (Radio Communications) | Mon Apr 21 08:00:00 IDT 2014 | Mon Apr 21 08:00:00 IDT 2014
235 | 849 - Nam Cheong Ventilation Building (VB7) - Corridors and Roof (Radio Communications) | Mon Jul 14 08:00:00 IDT 2014 | Mon Jul 14 08:00:00 IDT 2014
236 | 849 - D/T Tunnel from the Northern contract limit to CH137+860 (Radio Communications) | Mon Jun 02 08:00:00 IDT 2014 | Mon Jun 02 08:00:00 IDT 2014
237 | 849 - D/T Tunnel from CH137+860 to the Southern contract limit and C&C section within Hoi Ting Road Shaft | Mon Sep 29 08:00:00 IDT 2014 | Mon Sep 29 08:00:00 IDT 2014
238 | 850 - Passenger Mobile Communication System | Mon Feb 24 08:00:00 IST 2014 | Mon Apr 27 08:00:00 IDT 2015
239 | 850 - Nam Cheong Ventilation Building (VB7) - TER and CTER (Passenger Mobile Communication) | Mon Feb 24 08:00:00 IST 2014 | Mon Feb 24 08:00:00 IST 2014
240 | 850 - D/T Tunnel from the Northern contract limit to CH137+860 (Passenger Mobile Communication) | Mon Jun 02 08:00:00 IDT 2014 | Mon Jun 02 08:00:00 IDT 2014
241 | 850 - U/T Tunnel from the Northern contract limit to CH137+860 (Passenger Mobile Communication) | Mon Sep 29 08:00:00 IDT 2014 | Mon Sep 29 08:00:00 IDT 2014
242 | 850 - U/T Tunnel from CH137+860 to the Southern contract limit and C&C section within Hoi Ting Road Shaft | Mon Apr 27 08:00:00 IDT 2015 | Mon Apr 27 08:00:00 IDT 2015
243 | 850 - D/T Tunnel from CH137+860 to the Southern contract limit and C&C section within Hoi Ting Road Shaft | Mon Sep 29 08:00:00 IDT 2014 | Mon Sep 29 08:00:00 IDT 2014
244 | 851 - Fixed Communication System | Mon Feb 24 08:00:00 IST 2014 | Mon Apr 27 08:00:00 IDT 2015
245 | 851- Nam Cheong Ventilation Building (VB7) - TER and CTER (Fixed Communication) | Mon Feb 24 08:00:00 IST 2014 | Mon Feb 24 08:00:00 IST 2014
246 | 851 - D/T Tunnel from the Northern contract limit to CH137+860 (Fixed Communication) | Mon Jun 02 08:00:00 IDT 2014 | Mon Jun 02 08:00:00 IDT 2014
247 | 851 - U/T Tunnel from the Northern contract limit to CH137+860 (Fixed Communication) | Mon Sep 29 08:00:00 IDT 2014 | Mon Sep 29 08:00:00 IDT 2014
248 | 851 - U/T Tunnel from CH137+860 to the Southern contract limit and C&C section within Hoi Ting Road Shaft | Mon Apr 27 08:00:00 IDT 2015 | Mon Apr 27 08:00:00 IDT 2015
249 | 851 - D/T Tunnel from CH137+860 to Southern contract limit and C&C section within Hoi Ting Road Shaft | Mon Sep 29 08:00:00 IDT 2014 | Mon Sep 29 08:00:00 IDT 2014
250 | 853 - Main Control System | Mon Feb 24 08:00:00 IST 2014 | Mon Feb 24 08:00:00 IST 2014
251 | 853- Nam Cheong Ventilation Building (VB7) - TER and CTER (Main Control) | Mon Feb 24 08:00:00 IST 2014 | Mon Feb 24 08:00:00 IST 2014
252 | 854 - Security Access Management System (SAMS) | Mon Aug 18 08:00:00 IDT 2014 | Mon Aug 18 08:00:00 IDT 2014
253 | 854 - The doors with SAMS | Mon Aug 18 08:00:00 IDT 2014 | Mon Aug 18 08:00:00 IDT 2014
254 | 855 - Building Services for Tunnel Ventilation Buildings & Emergency Rescue Station | Mon Dec 23 08:00:00 IST 2013 | Mon May 12 08:00:00 IDT 2014
255 | 855-All rooms and common areas - corridors, lobbies etc within VB7 Excl. the parts of the VB7 under Ref. 4C(i) & 4C(ii) | Mon May 12 08:00:00 IDT 2014 | Mon May 12 08:00:00 IDT 2014
256 | 855 - VB7 - All rooms and common areas at track level and above track level(Excl. staircases, Lift shaft & CLP risers) | Mon Mar 03 08:00:00 IST 2014 | Mon Mar 03 08:00:00 IST 2014
257 | 855 - VB7 - All rooms and common areas at Level L1, UL2, L1 and UL1 (Excl. staircases, Lift shaft & CLP risers) | Mon Dec 23 08:00:00 IST 2013 | Mon Dec 23 08:00:00 IST 2013
258 | System Assurance Schedule | Mon Jul 05 17:00:00 IDT 2010 | Sat Jan 08 08:00:00 IST 2011
259 | System Assurance Schedule | Mon Jul 05 17:00:00 IDT 2010 | Sat Jan 08 08:00:00 IST 2011
260 | General | Mon Jul 05 17:00:00 IDT 2010 | Sat Jan 08 08:00:00 IST 2011
261 | System Assurance Plan | Sat Jan 08 08:00:00 IST 2011 | Sat Jan 08 08:00:00 IST 2011
262 | HAZOP Workshop | Mon Jul 05 17:00:00 IDT 2010 | Mon Jul 05 17:00:00 IDT 2010
263 | PHA Activity | Mon Jul 05 17:00:00 IDT 2010 | Mon Jul 05 17:00:00 IDT 2010
264 | Establish Hazard Log | Mon Jul 05 17:00:00 IDT 2010 | Mon Jul 05 17:00:00 IDT 2010
265 | System Hazard Analysis | Sat Jan 08 08:00:00 IST 2011 | Sat Jan 08 08:00:00 IST 2011
266 | Interface Hazard Analysis | Mon Nov 29 17:00:00 IST 2010 | Mon Nov 29 17:00:00 IST 2010
267 | Operating & Support Hazard Analysis | Mon Nov 29 17:00:00 IST 2010 | Mon Nov 29 17:00:00 IST 2010
268 | Hazard Analysis Report | Mon Nov 29 17:00:00 IST 2010 | Mon Nov 29 17:00:00 IST 2010
269 | Determination Safety Assessment | Sat Jan 08 08:00:00 IST 2011 | Sat Jan 08 08:00:00 IST 2011
270 | Cost Centre A - Preliminaries | Tue May 25 17:00:00 IDT 2010 | Fri Jun 26 17:00:00 IDT 2015
271 | IPS Milestones | Sat Jan 08 08:00:00 IST 2011 | Fri Jun 26 17:00:00 IDT 2015
272 | General | Sat Jan 08 08:00:00 IST 2011 | Fri Jun 26 17:00:00 IDT 2015
273 | Approval of Contractor's Submissions | Sat Jan 08 08:00:00 IST 2011 | Sat Jan 08 08:00:00 IST 2011
274 | Submit Contamination Assessment Report & RAP | Wed Apr 13 17:00:00 IDT 2011 | Wed Apr 13 17:00:00 IDT 2011
275 | Complete Engineer's Office+Satisfy Implem. Plans | Sun Apr 17 17:00:00 IDT 2011 | Sun Apr 17 17:00:00 IDT 2011
276 | Implem. Specified Plan&Programming Management System | Tue May 31 08:00:00 IDT 2011 | Tue May 31 08:00:00 IDT 2011
277 | Approval of Interface Specification&Specify Plan | Sun Jan 15 08:00:00 IST 2012 | Sun Jan 15 08:00:00 IST 2012
278 | 1st TBM - Complete Assembly, T&C & Start D/T Drive | Fri Jan 20 17:00:00 IST 2012 | Fri Jan 20 17:00:00 IST 2012
279 | Implem. Specified Plan&Programming Managem't System | Sun May 27 17:00:00 IDT 2012 | Sun May 27 17:00:00 IDT 2012
280 | Confirmation of Satisfactory Implementation of Specified Plan | Fri Nov 30 08:00:00 IST 2012 | Fri Nov 30 08:00:00 IST 2012
281 | TBM - Complete Assembly, T&C & Start U/T Drive | Fri Mar 29 17:00:00 IDT 2013 | Fri Mar 29 17:00:00 IDT 2013
282 | Confirmation of Satisfy Implement Specified Plan & Programming Mgmt. System | Sun May 26 17:00:00 IDT 2013 | Sun May 26 17:00:00 IDT 2013
283 | Confirmation of Satisfy Implement Specified Plan | Sun Nov 24 17:00:00 IST 2013 | Sun Nov 24 17:00:00 IST 2013
284 | Deg.1 Complete Entire Length Tunnel - Both Tracks | Tue Mar 31 17:00:00 IDT 2015 | Tue Mar 31 17:00:00 IDT 2015
285 | Approval of Draft O&M Manuals & As-built Drawing | Wed Mar 25 17:00:00 IST 2015 | Wed Mar 25 17:00:00 IST 2015
286 | Approval of O&M Manuals & As-built Drawings | Fri Jun 26 17:00:00 IDT 2015 | Fri Jun 26 17:00:00 IDT 2015
287 | Submission | Tue May 25 17:00:00 IDT 2010 | Sun Jan 15 08:00:00 IST 2012
288 | General | Tue May 25 17:00:00 IDT 2010 | Sun Jan 15 08:00:00 IST 2012
289 | Submission of Three Month Rolling Programme | Sat Jan 08 08:00:00 IST 2011 | Sat Jan 08 08:00:00 IST 2011
290 | Submission of Preliminary Design Programme | Sat Jan 08 08:00:00 IST 2011 | Sat Jan 08 08:00:00 IST 2011
291 | Submission of Contractor Submission Schedule | Sat Jan 08 08:00:00 IST 2011 | Sat Jan 08 08:00:00 IST 2011
292 | Submission of Schedule of Design | Sat Jan 08 08:00:00 IST 2011 | Sat Jan 08 08:00:00 IST 2011
293 | Submission Environment Management Plan | Sat Jan 08 08:00:00 IST 2011 | Sat Jan 08 08:00:00 IST 2011
294 | Submission of Quality Plan | Sat Jan 08 08:00:00 IST 2011 | Sat Jan 08 08:00:00 IST 2011
295 | Submission of Sub-contract Management Plan | Sat Jan 08 08:00:00 IST 2011 | Sat Jan 08 08:00:00 IST 2011
296 | Submission of Supply Survey Equipment Listed in App. A1 | Sat Jan 08 08:00:00 IST 2011 | Sat Jan 08 08:00:00 IST 2011
297 | Apply a Billing Account in EPD for Disposal of Construction Waste | Sat Jan 08 08:00:00 IST 2011 | Sat Jan 08 08:00:00 IST 2011
298 | Submission of Monitoring Emergency Response Plan(impact on Ecological & Fishers Resources) | Sat Jan 08 08:00:00 IST 2011 | Sat Jan 08 08:00:00 IST 2011
299 | Submission of Bond in form of App.B | Sat Jan 08 08:00:00 IST 2011 | Sat Jan 08 08:00:00 IST 2011
300 | Submission of Guarantee in Form of App.C | Sat Jan 08 08:00:00 IST 2011 | Sat Jan 08 08:00:00 IST 2011
301 | Submission of Guarantee in Form of App.D | Sat Jan 08 08:00:00 IST 2011 | Sat Jan 08 08:00:00 IST 2011
302 | Submission of Preliminary Master Programme | Wed Jun 02 17:00:00 IDT 2010 | Wed Jun 02 17:00:00 IDT 2010
303 | Submission of Time Chainage Programme | Wed Jun 02 17:00:00 IDT 2010 | Wed Jun 02 17:00:00 IDT 2010
304 | Confirmation for Conveyor System from Nam CheongShaft to Nam Cheong Barging Pt. | Wed Jun 02 17:00:00 IDT 2010 | Wed Jun 02 17:00:00 IDT 2010
305 | Submission of Survey Control Network | Wed Jun 02 17:00:00 IDT 2010 | Wed Jun 02 17:00:00 IDT 2010
306 | Submission for Approval Survey Control | Sun Jul 11 17:00:00 IDT 2010 | Sun Jul 11 17:00:00 IDT 2010
307 | Submission of Proposal for Repositioning of Traffic Signals & Control | Wed Jul 07 17:00:00 IDT 2010 | Wed Jul 07 17:00:00 IDT 2010
308 | Submission of Schedule of Utility Services Arrangement | Wed Jun 02 17:00:00 IDT 2010 | Wed Jun 02 17:00:00 IDT 2010
309 | Submission DIA to DSD for Approval | Wed Jun 02 17:00:00 IDT 2010 | Wed Jun 02 17:00:00 IDT 2010
310 | Submission of Health & Safety Plan | Wed Jun 02 17:00:00 IDT 2010 | Wed Jun 02 17:00:00 IDT 2010
311 | Completion of Initial Site Survey Submission | Wed Jun 02 17:00:00 IDT 2010 | Wed Jun 02 17:00:00 IDT 2010
312 | Submit Initial Site Survey Report to Engineer | Wed Jun 02 17:00:00 IDT 2010 | Wed Jun 02 17:00:00 IDT 2010
313 | Review Tree Removal Application & Confirmation to Engineer | Tue May 25 17:00:00 IDT 2010 | Tue May 25 17:00:00 IDT 2010
314 | Submit Full Details of TBMs to Engineer | Sun Jan 15 08:00:00 IST 2012 | Sun Jan 15 08:00:00 IST 2012
315 | MS/TTm proposal & Risk Register for Conveyor System at Barging Point | Sat Jan 08 08:00:00 IST 2011 | Sat Jan 08 08:00:00 IST 2011
316 | Submit Survey Method Statement for Tunnelling Works | Sat Jan 08 08:00:00 IST 2011 | Sat Jan 08 08:00:00 IST 2011
317 | Submit Managem't & Operat'n Plan of Barging Facility | Sat Jan 08 08:00:00 IST 2011 | Sat Jan 08 08:00:00 IST 2011
318 | TTM Schemes Submission for Engineer Review & SLG Approval | Sat Jan 08 08:00:00 IST 2011 | Sat Jan 08 08:00:00 IST 2011
319 | RemediationActionPlan forAreas11.29A to11.29-EPD | Sat Jan 08 08:00:00 IST 2011 | Sat Jan 08 08:00:00 IST 2011
320 | Condition Survey Submission for EBS | Mon Feb 28 08:00:00 IST 2011 | Mon Feb 28 08:00:00 IST 2011
321 | All Instrumentation Installation | Mon Feb 28 08:00:00 IST 2011 | Mon Feb 28 08:00:00 IST 2011
322 | Tree Protection Plan | Mon Feb 28 08:00:00 IST 2011 | Mon Feb 28 08:00:00 IST 2011
323 | Site Supervision Plan | Mon Feb 28 08:00:00 IST 2011 | Mon Feb 28 08:00:00 IST 2011
324 | Emergency Action Plan/Crisis Management Plan | Mon Feb 28 08:00:00 IST 2011 | Mon Feb 28 08:00:00 IST 2011
325 | Soil Disposal Management Plan | Mon Feb 28 08:00:00 IST 2011 | Mon Feb 28 08:00:00 IST 2011
326 | Segmental Lining Design Submission | Mon Feb 28 08:00:00 IST 2011 | Mon Feb 28 08:00:00 IST 2011
327 | Method Statement for Geotechnical Instrumentation Installation | Mon Feb 28 08:00:00 IST 2011 | Mon Feb 28 08:00:00 IST 2011
328 | Method Statement for Hoarding Erection | Mon Feb 28 08:00:00 IST 2011 | Mon Feb 28 08:00:00 IST 2011
329 | Emergency Response Plan to Groundwater Drawdown & Noise/Vibration | Mon Feb 28 08:00:00 IST 2011 | Mon Feb 28 08:00:00 IST 2011
330 | Site Office | Sat Jan 08 08:00:00 IST 2011 | Mon Mar 14 17:00:00 IST 2011
331 | Construction | Sat Jan 08 08:00:00 IST 2011 | Mon Mar 14 17:00:00 IST 2011
332 | Site Office Establish at Works Area 11.22 | Sat Jan 08 08:00:00 IST 2011 | Mon Mar 14 17:00:00 IST 2011
333 | Training Centre | Tue Jun 21 08:00:00 IDT 2011 | Wed Jul 13 17:00:00 IDT 2011
334 | Construction | Tue Jun 21 08:00:00 IDT 2011 | Wed Jul 13 17:00:00 IDT 2011
335 | Base Slab Construction | Thu Jun 23 08:00:00 IDT 2011 | Mon Jun 27 17:00:00 IDT 2011
336 | Erection of Building Structure | Tue Jun 21 08:00:00 IDT 2011 | Wed Jul 13 17:00:00 IDT 2011
337 | Internal Fitting Out | Tue Jun 21 08:00:00 IDT 2011 | Wed Jul 13 17:00:00 IDT 2011
338 | External Works | Tue Jun 21 08:00:00 IDT 2011 | Tue Jul 05 17:00:00 IDT 2011
339 | External Slab Construction | Tue Jun 21 08:00:00 IDT 2011 | Tue Jul 05 17:00:00 IDT 2011
340 | External U-channel | Tue Jun 21 08:00:00 IDT 2011 | Thu Jun 30 17:00:00 IDT 2011
341 | Sewer and Manholes | Tue Jun 21 08:00:00 IDT 2011 | Mon Jun 27 17:00:00 IDT 2011
342 | Hoarding Erection | Tue Jun 21 08:00:00 IDT 2011 | Sat Jul 02 17:00:00 IDT 2011
343 | Main Gate Installation | Tue Jun 21 08:00:00 IDT 2011 | Mon Jun 27 17:00:00 IDT 2011
344 | Sign Board Installation | Tue Jun 21 08:00:00 IDT 2011 | Mon Jun 27 17:00:00 IDT 2011
345 | Barging Point | Sat Jan 08 08:00:00 IST 2011 | Mon Mar 02 17:00:00 IST 2015
346 | General | Sat Jan 08 08:00:00 IST 2011 | Sat Jul 23 17:00:00 IDT 2011
347 | Barging Point Design Preparation | Sat Jan 08 08:00:00 IST 2011 | Sat Jul 23 17:00:00 IDT 2011
348 | Barging Point Design Comment and Approval by MTR | Sat Mar 05 08:00:00 IST 2011 | Sat Apr 02 17:00:00 IDT 2011
349 | Contamination | Sat Jan 08 08:00:00 IST 2011 | Sat May 21 17:00:00 IDT 2011
350 | Submission of Revised CAP (by MTR) | Sat Jan 08 08:00:00 IST 2011 | Thu Jan 20 17:00:00 IST 2011
351 | Approval Time of CAP from EPD | Tue Jan 18 08:00:00 IST 2011 | Sat Feb 19 17:00:00 IST 2011
352 | Preparation & Submission of M.S for Drilling | Mon Feb 21 08:00:00 IST 2011 | Tue Mar 01 17:00:00 IST 2011
353 | Site Investigation & Sample Locations Survey | Mon Feb 28 08:00:00 IST 2011 | Mon Mar 07 17:00:00 IST 2011
354 | Drilling & Sampling | Mon Mar 07 08:00:00 IST 2011 | Fri Mar 25 17:00:00 IST 2011
355 | Sampling Analysis | Fri Mar 18 08:00:00 IST 2011 | Wed Apr 13 17:00:00 IDT 2011
356 | Submission of CAR | Fri Apr 01 08:00:00 IDT 2011 | Wed May 04 17:00:00 IDT 2011
357 | Submission of RAP | Fri Apr 01 08:00:00 IDT 2011 | Wed May 04 17:00:00 IDT 2011
358 | Comments from EPD | Tue Apr 19 08:00:00 IDT 2011 | Sat May 21 17:00:00 IDT 2011
359 | Approved CAR & RAP Report Handover to 811B & 821 | Wed May 11 17:00:00 IDT 2011 | Wed May 11 17:00:00 IDT 2011
360 | Construction | Sat Jan 08 08:00:00 IST 2011 | Fri Jul 29 17:00:00 IDT 2011
361 | Works Area 11.29A | Sat Jan 08 08:00:00 IST 2011 | Sat Jan 08 08:00:00 IST 2011
362 | Works Area 11.29D | Sat Jan 08 08:00:00 IST 2011 | Sat Jan 08 08:00:00 IST 2011
363 | Works Area 11.29E | Sat Jan 08 08:00:00 IST 2011 | Sat Jan 08 08:00:00 IST 2011
364 | Works Area 11.29F | Sat Jan 08 08:00:00 IST 2011 | Sat Jan 08 08:00:00 IST 2011
365 | Site Mobilization | Sat Jan 08 08:00:00 IST 2011 | Fri Jan 28 17:00:00 IST 2011
366 | Hydographic/Condition Survey | Sat Jan 29 08:00:00 IST 2011 | Sat Mar 26 17:00:00 IST 2011
367 | Site Clearance | Sat Jun 11 08:00:00 IDT 2011 | Mon Jul 11 17:00:00 IDT 2011
368 | Site Formation fro Barging Point | Wed Jun 22 08:00:00 IDT 2011 | Mon Jul 11 17:00:00 IDT 2011
369 | Construction of Loading Ramps and Associated Facilities | Mon Feb 28 08:00:00 IST 2011 | Fri Jul 29 17:00:00 IDT 2011
370 | Storage Treatment Plant | Mon May 21 08:00:00 IDT 2012 | Sat Sep 01 17:00:00 IDT 2012
371 | Storage Treatment Plant Setup | Mon May 21 08:00:00 IDT 2012 | Sat Sep 01 17:00:00 IDT 2012
372 | Slurry Treatment Plant | Thu Jun 30 08:00:00 IDT 2011 | Mon Mar 02 17:00:00 IST 2015
373 | Begininning of Material Delivery for Slurry Treatment Plants | Thu Jun 30 08:00:00 IDT 2011 | Thu Jun 30 08:00:00 IDT 2011
374 | Treatment Tanks Erection | Thu Jun 30 08:00:00 IDT 2011 | Sat Sep 10 17:00:00 IDT 2011
375 | Silos Erection | Mon Jan 16 08:00:00 IST 2012 | Fri Jan 27 17:00:00 IST 2012
376 | Filter Press | Mon Jan 16 08:00:00 IST 2012 | Wed Feb 29 17:00:00 IST 2012
377 | Slurry Treatment Plant (STP1) Construction | Wed Aug 31 08:00:00 IDT 2011 | Thu Oct 13 17:00:00 IST 2011
378 | STP2 Construciton | Mon Jan 16 08:00:00 IST 2012 | Thu Feb 09 17:00:00 IST 2012
379 | Water Commissioning of STP1 | Mon Jan 16 08:00:00 IST 2012 | Fri Jan 20 17:00:00 IST 2012
380 | Water Commissioning of STP2 | Mon Jan 16 08:00:00 IST 2012 | Fri Jan 20 17:00:00 IST 2012
381 | Dismantle Slurry Treatment Plant and Equipments (after South U/T TBM (S630-1) Backup removal) | Wed Oct 15 08:00:00 IDT 2014 | Mon Jan 19 17:00:00 IST 2015
382 | Re-instatement | Fri Jan 02 08:00:00 IST 2015 | Mon Mar 02 17:00:00 IST 2015
383 | Cost Centre B - Specialised Construction Machinery & Site Assembly (TBMs) | Sat Jan 08 08:00:00 IST 2011 | Wed Nov 19 17:00:00 IST 2014
384 | IPS Milestones | Mon Jan 31 08:00:00 IST 2011 | Wed Nov 19 17:00:00 IST 2014
385 | General | Mon Jan 31 08:00:00 IST 2011 | Wed Nov 19 17:00:00 IST 2014
386 | Confirmation of Order of TBM | Mon Jan 31 08:00:00 IST 2011 | Mon Jan 31 08:00:00 IST 2011
387 | TBM - Commencement of the 1st TBM Final Assembly at Factory | Tue Aug 30 08:00:00 IDT 2011 | Tue Aug 30 08:00:00 IDT 2011
388 | TBM - Complete Fabrication & Ready Ship to HK | Sun Jan 15 08:00:00 IST 2012 | Sun Jan 15 08:00:00 IST 2012
389 | TBM - Complete Assembly,T&C+Start D/T Drive | Sun Feb 05 17:00:00 IST 2012 | Sun Feb 05 17:00:00 IST 2012
390 | TBM - Complete Assembly,T&C+Start U/T Drive (North) | Fri Mar 29 17:00:00 IDT 2013 | Fri Mar 29 17:00:00 IDT 2013
391 | TBM - Complete Assembly,T&C+Start Remain U/T Drive (South) | Thu Dec 12 08:00:00 IST 2013 | Thu Dec 12 08:00:00 IST 2013
392 | TBM - Complete Dismantle of TBM | Wed Nov 19 17:00:00 IST 2014 | Wed Nov 19 17:00:00 IST 2014
393 | Procurement | Sat Jan 08 08:00:00 IST 2011 | Mon Jan 07 17:00:00 IST 2013
394 | TBM (S630-1) Procurement & Delivery | Mon Feb 28 08:00:00 IST 2011 | Wed Nov 07 17:00:00 IST 2012
395 | TBM (S631-1) Procurement & Delivery | Mon Feb 28 08:00:00 IST 2011 | Mon Jan 07 17:00:00 IST 2013
396 | TBM (S630-1) Procurement | Sat Jan 08 08:00:00 IST 2011 | Wed Mar 21 17:00:00 IST 2012
397 | TBM(S630-1) - Procurement | Sat Jan 08 08:00:00 IST 2011 | Sat Feb 26 17:00:00 IST 2011
398 | TBM(S630-1) - Ordering | Sat Feb 26 17:00:00 IST 2011 | Sat Feb 26 17:00:00 IST 2011
399 | TBM(S630-1) - Detailed Design | Mon Jan 31 08:00:00 IST 2011 | Sun Apr 17 17:00:00 IDT 2011
400 | Ergonomy Study | Thu Feb 10 08:00:00 IST 2011 | Fri Apr 15 17:00:00 IDT 2011
401 | Purchase Parts | Mon Jan 31 08:00:00 IST 2011 | Thu Aug 18 17:00:00 IDT 2011
402 | Manufacturing of Drive Unit (in Europe) | Sun Mar 20 08:00:00 IST 2011 | Mon Sep 12 17:00:00 IDT 2011
403 | Commencement of TBM1 Final Assembly at Factory | Wed Aug 03 08:00:00 IDT 2011 | Wed Aug 03 08:00:00 IDT 2011
404 | Pre-assembly Drive Unit, Erector, Hydraulics, Slurry Pumps in Schwanau | Wed Aug 03 08:00:00 IDT 2011 | Sun Oct 23 17:00:00 IST 2011
405 | Transport (Europe to China) | Mon Mar 28 08:00:00 IST 2011 | Tue May 03 17:00:00 IDT 2011
406 | Manufacturing of Shield, Cutterhead, Back-up (in China) | Mon Feb 28 08:00:00 IST 2011 | Tue Sep 06 17:00:00 IDT 2011
407 | Design Review for TBM (S631-1) Modification | Sun Jun 19 08:00:00 IDT 2011 | Wed Jul 13 17:00:00 IDT 2011
408 | EI issue for TBM (S630-1) Modification | Thu Jun 30 08:00:00 IDT 2011 | Thu Jun 30 08:00:00 IDT 2011
409 | TBM (S630-1) Modification | Thu Jun 30 08:00:00 IDT 2011 | Thu Sep 08 17:00:00 IDT 2011
410 | Final Assembly in Workshop | Sun Jun 19 08:00:00 IDT 2011 | Sat Nov 19 17:00:00 IST 2011
411 | Factory Acceptance Tests | Sun Jan 15 08:00:00 IST 2012 | Tue Feb 07 17:00:00 IST 2012
412 | Disassembly & Ready Ship to HK | Sun Jan 15 08:00:00 IST 2012 | Sat Feb 11 17:00:00 IST 2012
413 | TBM (S630-1) Available for delivery to HK | Sun Jan 15 08:00:00 IST 2012 | Sun Jan 15 08:00:00 IST 2012
414 | TBM(S630-1) - TBM Storage | Sun Jan 15 08:00:00 IST 2012 | Wed Feb 29 17:00:00 IST 2012
415 | TBM(S630-1) - Transport & Delivery to HK | Thu Mar 01 08:00:00 IST 2012 | Wed Mar 21 17:00:00 IST 2012
416 | TBM (S631-1) Procurement | Sat Jan 08 08:00:00 IST 2011 | Sat Feb 11 17:00:00 IST 2012
417 | TBM(S631-1) - Procurement | Mon Jan 31 08:00:00 IST 2011 | Sun Mar 20 17:00:00 IST 2011
418 | TBM(S631-1) - Ordering | Sat Feb 26 17:00:00 IST 2011 | Sat Feb 26 17:00:00 IST 2011
419 | TBM(S631-1) - Detailed Design | Sun Feb 27 08:00:00 IST 2011 | Wed May 25 17:00:00 IDT 2011
420 | Ergonomy Study | Thu Jan 20 08:00:00 IST 2011 | Sat Mar 26 17:00:00 IST 2011
421 | Purchase Parts | Sat Jan 08 08:00:00 IST 2011 | Thu Sep 15 17:00:00 IDT 2011
422 | Manufacturing of Drive Unit (in Europe) | Sun Mar 27 08:00:00 IST 2011 | Wed Sep 28 17:00:00 IDT 2011
423 | Pre-assembly Drive Unit,erector,Hydraulics, Slurry Pumps in Schwanau | Sun Jun 19 08:00:00 IDT 2011 | Sat Jul 16 17:00:00 IDT 2011
424 | Transport (Europe to China) | Tue Apr 19 08:00:00 IDT 2011 | Mon Jun 27 17:00:00 IDT 2011
425 | Manufacturing on Shield, Cutterhead,Back-up (in China) | Fri Mar 11 08:00:00 IST 2011 | Thu Oct 06 17:00:00 IST 2011
426 | Design Review for TBM (S631-1) Modification | Sun Jun 19 08:00:00 IDT 2011 | Wed Jul 13 17:00:00 IDT 2011
427 | EI issue for TBM631.1 Modification | Thu Jun 30 08:00:00 IDT 2011 | Thu Jun 30 08:00:00 IDT 2011
428 | TBM (S631-1) Modification | Sun Jun 19 08:00:00 IDT 2011 | Sun Aug 28 17:00:00 IDT 2011
429 | Final Assembly in Workshop | Sun Jun 19 08:00:00 IDT 2011 | Fri Oct 21 17:00:00 IST 2011
430 | Factory Acceptance Tests | Wed Aug 31 08:00:00 IDT 2011 | Fri Sep 23 17:00:00 IDT 2011
431 | Disassembly | Sun Jan 15 08:00:00 IST 2012 | Sat Feb 11 17:00:00 IST 2012
432 | TBM (S631-1) Available for delivery to HK | Sun Jan 15 08:00:00 IST 2012 | Sun Jan 15 08:00:00 IST 2012
433 | TBM(S631-1) - Transport & Delivery to HK | Sun Jan 15 08:00:00 IST 2012 | Fri Feb 03 17:00:00 IST 2012
434 | Cost Centre C - Mei Lai Road - Hoi Ting Road Tunnel | Thu Oct 21 08:00:00 IST 2010 | Tue Sep 29 17:00:00 IDT 2015
435 | IPS Milestones | Mon Feb 28 08:00:00 IST 2011 | Sun May 10 17:00:00 IDT 2015
436 | General | Mon Feb 28 08:00:00 IST 2011 | Sun May 10 17:00:00 IDT 2015
437 | Approval of Tunnel Lining Design | Mon Jul 18 17:00:00 IDT 2011 | Mon Jul 18 17:00:00 IDT 2011
438 | Approval of Tunnel Segment Mould Design | Mon Feb 28 08:00:00 IST 2011 | Mon Feb 28 08:00:00 IST 2011
439 | Confirmation of the Order of Segment Mould | Thu Jun 30 08:00:00 IDT 2011 | Thu Jun 30 08:00:00 IDT 2011
440 | Complete Ground Improvement Wk Outside Hoi Ting Shaft | Sun Jun 19 17:00:00 IDT 2011 | Sun Jun 19 17:00:00 IDT 2011
441 | Complete 30% of Pre-cast Segment Manufacturing | Thu Dec 20 17:00:00 IST 2012 | Thu Dec 20 17:00:00 IST 2012
442 | Complete 45% of Pre-cast Segment Manufacturing | Fri Apr 19 17:00:00 IDT 2013 | Fri Apr 19 17:00:00 IDT 2013
443 | Complete 30% of Tunnel Drive | Fri Aug 31 08:00:00 IDT 2012 | Fri Aug 31 08:00:00 IDT 2012
444 | Complete 50% of Tunnel Drive | Thu Jan 31 17:00:00 IST 2013 | Thu Jan 31 17:00:00 IST 2013
445 | Complete 60% of Tunnel Drive | Wed Jul 31 17:00:00 IDT 2013 | Wed Jul 31 17:00:00 IDT 2013
446 | Deg. 1 Completion for D/T Tunnel | Sun May 18 17:00:00 IDT 2014 | Sun May 18 17:00:00 IDT 2014
447 | Complete 100% of Tunnel Drive | Sun Sep 28 17:00:00 IDT 2014 | Sun Sep 28 17:00:00 IDT 2014
448 | Deg. 1 Completion for U/T Tunnel | Sat Feb 28 17:00:00 IST 2015 | Sat Feb 28 17:00:00 IST 2015
449 | Complete All Works | Sun May 10 17:00:00 IDT 2015 | Sun May 10 17:00:00 IDT 2015
450 | Critical Dates | Mon Feb 28 08:00:00 IST 2011 | Mon Sep 30 08:00:00 IDT 2013
451 | Critical Dates | Mon Feb 28 08:00:00 IST 2011 | Mon Sep 30 08:00:00 IDT 2013
452 | Earliest Access Date- Works Area 12.2 | Mon Feb 28 08:00:00 IST 2011 | Mon Feb 28 08:00:00 IST 2011
453 | Ground Treatment Completion at Works Area 12.2 | Sun Jun 19 17:00:00 IDT 2011 | Sun Jun 19 17:00:00 IDT 2011
454 | Hoi Ting Road - TBM Retrieval Shaft Ready | Mon Sep 30 08:00:00 IDT 2013 | Mon Sep 30 08:00:00 IDT 2013
455 | Method Statement Submission and Approval | Mon Feb 28 08:00:00 IST 2011 | Thu Jan 19 17:00:00 IST 2012
456 | Method Stattement Submission and Approval | Mon Feb 28 08:00:00 IST 2011 | Thu Jan 19 17:00:00 IST 2012
457 | MS Submission Preparation for CLP/IVESchool Grouting | Thu Jun 30 08:00:00 IDT 2011 | Thu Jan 19 17:00:00 IST 2012
458 | MS Submission to MTR | Thu Jun 30 08:00:00 IDT 2011 | Thu Jun 30 08:00:00 IDT 2011
459 | MS Comment by MTR | Thu Jun 30 08:00:00 IDT 2011 | Thu Aug 04 17:00:00 IDT 2011
460 | MS Re-submission Preparation | Thu Jun 30 08:00:00 IDT 2011 | Sat Jul 09 17:00:00 IDT 2011
461 | MS Comment & Approval by MTR | Thu Jun 30 08:00:00 IDT 2011 | Tue Aug 16 17:00:00 IDT 2011
462 | Issue for Construction (CLP/IVE) | Wed Jul 27 17:00:00 IDT 2011 | Wed Jul 27 17:00:00 IDT 2011
463 | MS Submission Preparation for Cross Passage | Mon Feb 28 08:00:00 IST 2011 | Tue Jun 07 17:00:00 IDT 2011
464 | MS Submission to MTR | Thu Jun 30 08:00:00 IDT 2011 | Thu Jun 30 08:00:00 IDT 2011
465 | MS Comment by MTR | Thu Jun 30 08:00:00 IDT 2011 | Sat Jul 16 17:00:00 IDT 2011
466 | MS Re-Submission Preparation | Wed Aug 31 08:00:00 IDT 2011 | Wed Sep 21 17:00:00 IDT 2011
467 | MS Comment & Approval by MTR | Wed Aug 31 08:00:00 IDT 2011 | Sat Sep 17 17:00:00 IDT 2011
468 | Issue for Construction (Cross Passage) | Wed Aug 31 08:00:00 IDT 2011 | Wed Aug 31 08:00:00 IDT 2011
469 | MS Submission Preparation for HoiFu Estate/Charming Bldgs.& YMT School | Thu Jun 30 08:00:00 IDT 2011 | Tue Jul 26 17:00:00 IDT 2011
470 | MS Submission to MTR | Thu Jun 30 08:00:00 IDT 2011 | Thu Jun 30 08:00:00 IDT 2011
471 | MS Comment & Approoval by MTR | Thu Jun 30 08:00:00 IDT 2011 | Thu Jul 21 17:00:00 IDT 2011
472 | MS Re-submission Preparation | Thu Jun 30 08:00:00 IDT 2011 | Thu Jul 28 17:00:00 IDT 2011
473 | MS Approval by MTR | Wed Aug 31 08:00:00 IDT 2011 | Sun Sep 11 17:00:00 IDT 2011
474 | Issue for Construction (HoiFu Estate/Charming Bldgs & YMT School) | Wed Aug 31 08:00:00 IDT 2011 | Wed Aug 31 08:00:00 IDT 2011
475 | TTMS Submission and Approval | Tue Feb 01 08:00:00 IST 2011 | Sun Sep 11 17:00:00 IDT 2011
476 | TTM Scheme Submission & Approval | Tue Feb 01 08:00:00 IST 2011 | Sun Sep 11 17:00:00 IDT 2011
477 | Prepare TTM for grouting works for Existing Bldg | Tue Feb 01 08:00:00 IST 2011 | Sat Mar 05 17:00:00 IST 2011
478 | TTM reviewed by SLG | Sun Mar 06 08:00:00 IST 2011 | Thu May 05 17:00:00 IDT 2011
479 | Resubmit TTM | Mon May 23 08:00:00 IDT 2011 | Mon May 23 17:00:00 IDT 2011
480 | TTM reviewed by SLG | Sun May 29 08:00:00 IDT 2011 | Sun May 29 17:00:00 IDT 2011
481 | Notification to RMO (for Ch140 +080 & +150 & +200) | Sun Jun 19 08:00:00 IDT 2011 | Sun Jun 26 17:00:00 IDT 2011
482 | XP Application & Approval | Mon Jun 20 08:00:00 IDT 2011 | Thu Aug 18 17:00:00 IDT 2011
483 | Implement TTM (Initial Stage) | Mon Feb 28 08:00:00 IST 2011 | Mon Jul 25 17:00:00 IDT 2011
484 | Notification to RMO (for Ch140 +340) | Wed Aug 31 08:00:00 IDT 2011 | Sun Sep 11 17:00:00 IDT 2011
485 | Implement TTM | Wed Aug 31 08:00:00 IDT 2011 | Wed Aug 31 08:00:00 IDT 2011
486 | SP License Application and Approval | Sun Jan 15 08:00:00 IST 2012 | Sun Jun 17 17:00:00 IDT 2012
487 | SP License application | Sun Jan 15 08:00:00 IST 2012 | Sun Jun 17 17:00:00 IDT 2012
488 | SP License application | Sun Jan 15 17:00:00 IST 2012 | Sun Jan 15 17:00:00 IST 2012
489 | TBM (S631-1) Excavation with Deg.1 Works | Sun Jan 15 08:00:00 IST 2012 | Thu May 29 17:00:00 IDT 2014
490 | TBM (S631-1) North -UT Excavation | Fri Mar 29 08:00:00 IDT 2013 | Thu Nov 14 17:00:00 IST 2013
491 | Access Available for Works Area 11.10A &11.10B (IVE School) (DT) (Contractual Handover Date) | Wed Feb 06 08:00:00 IST 2013 | Wed Feb 06 08:00:00 IST 2013
492 | Ground Treatment for IVE School (DT) | Mon Jan 16 08:00:00 IST 2012 | Tue Jun 12 17:00:00 IDT 2012
493 | TBM (S631-1) North-DT Excavation | Fri Jan 20 08:00:00 IST 2012 | Tue Oct 30 17:00:00 IST 2012
494 | TBM (S631-1) Dismantle & Re-assembly | Mon Dec 17 08:00:00 IST 2012 | Tue Feb 26 17:00:00 IST 2013
495 | Piles Removal@CLP Equipment Bldg.& Footbridges KF-118 by 805 (NDT) | Sun Jan 15 08:00:00 IST 2012 | Sun Jan 15 08:00:00 IST 2012
496 | Access Available for Works Area 11.10A &11.10B (IVE School) (DT) (Contractual Handover Date) | Wed Feb 06 08:00:00 IST 2013 | Wed Feb 06 08:00:00 IST 2013
497 | Ground Treatment for HKIVE School (NDT) | Mon Jan 16 08:00:00 IST 2012 | Mon Mar 26 17:00:00 IST 2012
498 | Grouting Wk@N/B Ch137+570: Building Foundation (Hoi Lai Shopping Centre) (NUT) | Sat Mar 24 08:00:00 IST 2012 | Fri Aug 31 17:00:00 IDT 2012
499 | General | Sun Jan 15 08:00:00 IST 2012 | Fri Mar 30 17:00:00 IDT 2012
500 | TBM (S631-1) Delivery on Site | Sun Jan 15 08:00:00 IST 2012 | Sun Jan 15 08:00:00 IST 2012
501 | TBM (S631-1) Assembly and T&C | Sun Jan 15 08:00:00 IST 2012 | Fri Mar 30 17:00:00 IDT 2012
502 | Downtrack Construction (North) | Sun Jan 15 08:00:00 IST 2012 | Sat Aug 17 17:00:00 IDT 2013
503 | TBM Excavation (North-DT) | Sun Jan 15 08:00:00 IST 2012 | Sat Aug 17 17:00:00 IDT 2013
504 | D/T TBM (S631-1) Break-in &Excavation Ch137+783-137+730 | Fri Jan 20 08:00:00 IST 2012 | Fri Feb 10 17:00:00 IST 2012
505 | Reach Cheung Sha Wan Cargo Pier Pile Obstruction | Fri Feb 10 17:00:00 IST 2012 | Fri Feb 10 17:00:00 IST 2012
506 | D/T Excavation Ch137+730-137+640 | Sat Feb 11 08:00:00 IST 2012 | Sun Mar 18 17:00:00 IST 2012
507 | D/T Excavation Ch137+640-137+530 | Mon Mar 19 08:00:00 IST 2012 | Mon Apr 02 17:00:00 IDT 2012
508 | Reach CP88 (CH137+565) | Thu Mar 29 08:00:00 IST 2012 | Thu Mar 29 08:00:00 IST 2012
509 | D/T Excavation Ch137+530-137+420 | Tue Apr 03 08:00:00 IDT 2012 | Thu Apr 12 17:00:00 IDT 2012
510 | D/T Excavation Ch137+420-137+345 | Fri Apr 13 08:00:00 IDT 2012 | Thu Apr 19 17:00:00 IDT 2012
511 | Reach CP87 (CH137+369) | Wed Apr 18 17:00:00 IDT 2012 | Wed Apr 18 17:00:00 IDT 2012
512 | Piles Removal@CLP Equipment Bldg.& Footbridges KF-118 by 805 | Sun Jan 15 08:00:00 IST 2012 | Sun Jan 15 08:00:00 IST 2012
513 | Reach Footbridge KF118 (Pile removed by 805) | Thu Apr 19 17:00:00 IDT 2012 | Thu Apr 19 17:00:00 IDT 2012
514 | D/T Excavation Ch137+345-137+280 | Fri Apr 20 08:00:00 IDT 2012 | Wed Apr 25 17:00:00 IDT 2012
515 | D/T Excavation Ch137+280-137+265 | Thu Apr 26 08:00:00 IDT 2012 | Fri Apr 27 17:00:00 IDT 2012
516 | Reach IVE Haking Wong Waterfont Annex (advanced work:Grouting) | Fri Apr 27 17:00:00 IDT 2012 | Fri Apr 27 17:00:00 IDT 2012
517 | D/T Excavation Ch137+265-137+240 | Sat Apr 28 08:00:00 IDT 2012 | Mon Apr 30 17:00:00 IDT 2012
518 | D/T Excavation Ch137+240-137+190 | Tue May 01 08:00:00 IDT 2012 | Sat May 05 17:00:00 IDT 2012
519 | D/T Excavation Ch137+190-137+080 | Sun May 06 08:00:00 IDT 2012 | Fri May 25 17:00:00 IDT 2012
520 | Reach CP86 (CH137+119) | Sat May 19 08:00:00 IDT 2012 | Sat May 19 08:00:00 IDT 2012
521 | Reach WD1 DSD Obstruction & 1800dia.Sewer | Fri May 25 17:00:00 IDT 2012 | Fri May 25 17:00:00 IDT 2012
522 | D/T Excavation Ch137+080-136+960 | Sat May 26 08:00:00 IDT 2012 | Fri Jun 15 17:00:00 IDT 2012
523 | Reach Lai Chi Kok DSD Obstruction | Fri Jun 15 17:00:00 IDT 2012 | Fri Jun 15 17:00:00 IDT 2012
524 | D/T Excavation Ch136+960-136+945 | Sat Jun 16 08:00:00 IDT 2012 | Mon Jun 18 17:00:00 IDT 2012
525 | D/T Excavation Ch136+945-136+920 | Tue Jun 19 08:00:00 IDT 2012 | Sun Jun 24 17:00:00 IDT 2012
526 | Reach TWL Sump Pit Ch136+920 | Sun Jun 24 17:00:00 IDT 2012 | Sun Jun 24 17:00:00 IDT 2012
527 | D/T Excavation Ch136+920-136+820 | Mon Jun 25 08:00:00 IDT 2012 | Tue Jul 03 17:00:00 IDT 2012
528 | Reach CP85 (CH136+860) | Sat Jun 30 08:00:00 IDT 2012 | Sat Jun 30 08:00:00 IDT 2012
529 | D/T Excavation Ch136+820-136+640 | Wed Jul 04 08:00:00 IDT 2012 | Tue Jul 24 17:00:00 IDT 2012
530 | D/T Excavation Ch136+640-136+583 - XRL821 | Wed Jul 25 08:00:00 IDT 2012 | Mon Jul 30 17:00:00 IDT 2012
531 | Reach CP84(CH136+601) - XRL821 | Sun Jul 29 08:00:00 IDT 2012 | Sun Jul 29 08:00:00 IDT 2012
532 | D/T Excavation Ch136+583-136+351 - XRL821 | Tue Jul 31 08:00:00 IDT 2012 | Tue Aug 28 17:00:00 IDT 2012
533 | Reach CP83 (CH136+351) XRL- 821 | Mon Sep 17 17:00:00 IDT 2012 | Mon Sep 17 17:00:00 IDT 2012
534 | D/T Excavation Ch136+351-136+101 - XRL821 | Tue Sep 18 08:00:00 IDT 2012 | Fri Oct 12 17:00:00 IST 2012
535 | Reach CP82 (CH136+101) - XRL821 | Sun Oct 07 17:00:00 IST 2012 | Sun Oct 07 17:00:00 IST 2012
536 | D/T Excavation Ch136+101-135+972 - XRL821 | Mon Oct 08 08:00:00 IST 2012 | Thu Oct 18 17:00:00 IST 2012
537 | D/T Excavation Ch135+972-135+772 - XRL821 | Fri Oct 19 08:00:00 IST 2012 | Mon Nov 05 17:00:00 IST 2012
538 | Reach CP81 (CH135+851) - XRL821 | Mon Nov 05 08:00:00 IST 2012 | Mon Nov 05 08:00:00 IST 2012
539 | D/T Excavation Ch135+772-135+737 - XRL 821 (235m) Break-in | Sat Dec 08 08:00:00 IST 2012 | Tue Dec 11 17:00:00 IST 2012
540 | D/T exit inside TBM Cavern (XRL821) | Sat Dec 15 08:00:00 IST 2012 | Wed Dec 19 17:00:00 IST 2012
541 | TBM (S631-1) Backup pull back | Mon Jan 07 08:00:00 IST 2013 | Wed Jan 16 17:00:00 IST 2013
542 | TBM (S631-1) Shield Dismantle & Removal | Mon Dec 17 08:00:00 IST 2012 | Wed Jan 30 17:00:00 IST 2013
543 | Set up Equipment for Invert Construction (Ch135+737-XRL821 to Ch137+784) | Thu Jan 31 08:00:00 IST 2013 | Sat Feb 16 17:00:00 IST 2013
544 | Tunnel Invert & Walkway (North DT- Ch135+737-XRL821 to Ch137+784) | Thu Feb 14 08:00:00 IST 2013 | Mon Aug 05 17:00:00 IDT 2013
545 | Deg. 1 Works (incl. XRL821) | Sat Jun 01 08:00:00 IDT 2013 | Sat Aug 17 17:00:00 IDT 2013
546 | Uptrack Construction (North) | Sat Mar 24 08:00:00 IST 2012 | Thu May 29 17:00:00 IDT 2014
547 | Ground Treatment (North-UT) | Sat Mar 24 08:00:00 IST 2012 | Wed Oct 03 17:00:00 IST 2012
548 | TTMS & Site Set up for Building Foundation Grouting Works | Sat Mar 24 08:00:00 IST 2012 | Mon Apr 30 17:00:00 IDT 2012
549 | Install Sleeve Pipe (Hoi Lai Shopping Centre) (UT) | Wed May 02 08:00:00 IDT 2012 | Thu May 31 17:00:00 IDT 2012
550 | Grouting Wk@N/B Ch137+570: Building Foundation (Hoi Lai Shopping Centre) (UT) | Fri Jun 01 08:00:00 IDT 2012 | Fri Aug 31 17:00:00 IDT 2012
551 | Reinstatement@N/B Ch137+570:(Hoi Lai Shopping Centre) (UT) | Sat Sep 01 08:00:00 IDT 2012 | Wed Oct 03 17:00:00 IST 2012
552 | TBM Excavation (North-UT) | Tue Jan 08 08:00:00 IST 2013 | Thu May 29 17:00:00 IDT 2014
553 | TBM (S631-1) Re-assembly | Tue Jan 08 08:00:00 IST 2013 | Wed Mar 20 17:00:00 IST 2013
554 | U/T Excavation Ch137+810-137+710 (Break-in) | Fri Mar 29 08:00:00 IDT 2013 | Sat Apr 20 17:00:00 IDT 2013
555 | Reach Cheung Sha Wan Cargo Pier Pile Obstruction | Sun Apr 07 17:00:00 IDT 2013 | Sun Apr 07 17:00:00 IDT 2013
556 | U/T Excavation Ch137+710-137+580 | Sun Apr 07 08:00:00 IDT 2013 | Wed May 01 17:00:00 IDT 2013
557 | Reach CP88(CH137+591) | Tue Apr 16 17:00:00 IDT 2013 | Tue Apr 16 17:00:00 IDT 2013
558 | U/T Excavation Ch137+580-137+550 | Fri Apr 19 08:00:00 IDT 2013 | Sat Apr 20 17:00:00 IDT 2013
559 | Reach Hoi Lai Shopping Centre (advanced work:Grouting) | Fri Apr 19 17:00:00 IDT 2013 | Fri Apr 19 17:00:00 IDT 2013
560 | U/T Excavation Ch137+550-137+200 | Sat Apr 20 08:00:00 IDT 2013 | Tue May 14 17:00:00 IDT 2013
561 | Reach CP87(CH137+393) | Sat Apr 27 17:00:00 IDT 2013 | Sat Apr 27 17:00:00 IDT 2013
562 | U/T Excavation Ch137+200-137+080 | Tue May 14 08:00:00 IDT 2013 | Sat Jun 01 17:00:00 IDT 2013
563 | Reach CP86(CH137+141) | Sun May 19 17:00:00 IDT 2013 | Sun May 19 17:00:00 IDT 2013
564 | Reach Culvert WD1 Pile Obstruction &1100dia. Foul Drain | Sun May 26 17:00:00 IDT 2013 | Sun May 26 17:00:00 IDT 2013
565 | U/T Excavation Ch137+080-136+975 | Sat May 25 08:00:00 IDT 2013 | Mon Jun 10 17:00:00 IDT 2013
566 | U/T Excavation Ch136+975-136+910 | Wed Jun 05 08:00:00 IDT 2013 | Thu Jun 20 17:00:00 IDT 2013
567 | Reach Lai Chi Kok DSD Obstructions | Fri Jun 07 17:00:00 IDT 2013 | Fri Jun 07 17:00:00 IDT 2013
568 | U/T Excavation Ch136+910-136+836 | Wed Jun 12 08:00:00 IDT 2013 | Tue Jun 18 17:00:00 IDT 2013
569 | Reach CP85(CH136+879) | Mon Jun 17 17:00:00 IDT 2013 | Mon Jun 17 17:00:00 IDT 2013
570 | U/T Excavation Ch136+836-136+656 | Wed Jun 26 08:00:00 IDT 2013 | Sat Jul 13 17:00:00 IDT 2013
571 | U/T Excavation Ch136+656-136+601-XRL821 | Wed Jul 24 08:00:00 IDT 2013 | Mon Jul 29 17:00:00 IDT 2013
572 | Reach CP84 (CH136+616)- XRL821 | Sat Jul 27 17:00:00 IDT 2013 | Sat Jul 27 17:00:00 IDT 2013
573 | U/T Excavation Ch136+601-136+365-XRL821 | Sun Jul 28 08:00:00 IDT 2013 | Tue Aug 13 17:00:00 IDT 2013
574 | Reach CP83 (CH136+365)- XRL821 | Fri Aug 23 17:00:00 IDT 2013 | Fri Aug 23 17:00:00 IDT 2013
575 | U/T Excavation Ch136+365-136+114-XRL821 | Fri Aug 23 08:00:00 IDT 2013 | Wed Sep 18 17:00:00 IDT 2013
576 | Reach CP82 (CH136+114)- XRL821 | Tue Sep 17 17:00:00 IDT 2013 | Tue Sep 17 17:00:00 IDT 2013
577 | U/T Excavation Ch136+114 -135+985-XRL821 | Tue Sep 17 08:00:00 IDT 2013 | Sat Sep 28 17:00:00 IDT 2013
578 | U/T Excavation Ch135+985-135+750-XRL821 (+235m) (Break-out) | Sun Oct 06 08:00:00 IDT 2013 | Sun Oct 27 17:00:00 IST 2013
579 | Reach CP81 (CH135+863)- XRL821 | Tue Oct 22 17:00:00 IDT 2013 | Tue Oct 22 17:00:00 IDT 2013
580 | U/T exit inside TBM Cavern - XRL821 | Sun Nov 10 08:00:00 IST 2013 | Thu Nov 14 17:00:00 IST 2013
581 | TBM (S631-1) Dismantling & Backup pull back | Fri Nov 15 08:00:00 IST 2013 | Sun Dec 29 17:00:00 IST 2013
582 | Set up Equipment for Invert Construction (Ch137+810 to Ch135+750-XRL821 ) | Mon Jan 06 08:00:00 IST 2014 | Sat Jan 18 17:00:00 IST 2014
583 | 820 section - Tunnel Invert & Walkway (UT-Northbound) (Ch137+810 to Ch136+640) | Mon Jan 20 08:00:00 IST 2014 | Wed Apr 16 17:00:00 IDT 2014
584 | 821 section - Tunnel Invert & Walkway (UT-Northbound) (Ch136+640 to Ch135+750) | Wed Feb 19 08:00:00 IST 2014 | Fri Apr 25 17:00:00 IDT 2014
585 | 821 Deg. 1 Works Ch136+640 to Ch135+750 (SA#3: 29-Jun-14) | Mon Mar 10 08:00:00 IST 2014 | Wed Apr 30 17:00:00 IDT 2014
586 | 820 Deg. 1 Works Ch137+810 to Ch136+640 (4B(i) Target: 1-Jun-14) | Sat Mar 01 08:00:00 IST 2014 | Thu May 29 17:00:00 IDT 2014
587 | TBM (S630-1) Excavation with Deg.1 Works | Tue Feb 01 08:00:00 IST 2011 | Tue Sep 29 17:00:00 IDT 2015
588 | Ground Treatment Wk at 811A Retrieval Shaft | Mon Jun 20 08:00:00 IDT 2011 | Fri Sep 23 17:00:00 IDT 2011
589 | Ground Wks for Buildings Protection (DT) - Hoi Wang Road | Mon Aug 01 08:00:00 IDT 2011 | Sat Sep 22 17:00:00 IDT 2012
590 | Ground Wks for Convergence Zones | Mon Jan 16 08:00:00 IST 2012 | Tue Nov 27 17:00:00 IST 2012
591 | Piles Removal@CLP Equipment Bldg.& Footbridges KF-119 by 805 | Sun Jan 15 08:00:00 IST 2012 | Sun Jan 15 08:00:00 IST 2012
592 | Pile Removal for Nam Cheong Property Development by 802 | Mon Apr 30 17:00:00 IDT 2012 | Mon Apr 30 17:00:00 IDT 2012
593 | TBM (S630-1) South-DT Excavation | Fri Mar 30 08:00:00 IDT 2012 | Sun Jan 06 17:00:00 IST 2013
594 | TBM (S630-1) South -UT Excavation | Sun Jan 12 08:00:00 IST 2014 | Sun Sep 14 17:00:00 IDT 2014
595 | Ground Treatment Wk at 811A Retrieval Shaft (SDT & SUT) | Wed Aug 31 08:00:00 IDT 2011 | Sun Dec 04 17:00:00 IST 2011
596 | Ground Wks for Buildings Protection (SDT) - Hoi Wang Road | Mon Aug 01 08:00:00 IDT 2011 | Mon Sep 17 17:00:00 IDT 2012
597 | Ground Wks for Convergence Zones (SDT & SUT) | Mon Jan 16 08:00:00 IST 2012 | Mon Jan 28 17:00:00 IST 2013
598 | Piles Removal@CLP Equipment Bldg.& Footbridges KF-119 by 805 (SDT & SUT) | Sun Nov 13 17:00:00 IST 2011 | Sun Nov 13 17:00:00 IST 2011
599 | Grouting Wk@N/B Ch140+340: Bldg. Foundation (Y.M.T.School) (SUT) | Thu Feb 02 08:00:00 IST 2012 | Tue Jun 12 17:00:00 IDT 2012
600 | Pile Removal for Nam Cheong Property Development by 802 (SDT & SUT) | Sun Jan 15 08:00:00 IST 2012 | Sun Jan 15 08:00:00 IST 2012
601 | TKT Grouting Works - Zone 1 | Mon Feb 13 08:00:00 IST 2012 | Fri Jul 20 17:00:00 IDT 2012
602 | TKT Grouting Works - Zone 2 | Mon Jan 16 08:00:00 IST 2012 | Mon Aug 20 17:00:00 IDT 2012
603 | TKT Grouting Works - Zone 4 | Mon Mar 26 08:00:00 IST 2012 | Mon Nov 05 17:00:00 IST 2012
604 | TKT Grouting Works - Zone 5 | Tue Oct 09 08:00:00 IST 2012 | Mon Apr 22 17:00:00 IDT 2013
605 | Downtrack Construction (South) | Tue Feb 01 08:00:00 IST 2011 | Tue Sep 29 17:00:00 IDT 2015
606 | TBM (S630-1) South-DT Excavation | Thu Apr 12 08:00:00 IDT 2012 | Tue Mar 19 17:00:00 IST 2013
607 | Ground Treatment (South-DT) | Tue Feb 01 08:00:00 IST 2011 | Mon Mar 18 17:00:00 IST 2013
608 | Access Date- Works Area 12.2 | Mon Feb 28 08:00:00 IST 2011 | Mon Feb 28 08:00:00 IST 2011
609 | Site Set up for Ground Treatment at 811A Retrieval Shaft | Sun Jun 19 08:00:00 IDT 2011 | Fri Jul 01 17:00:00 IDT 2011
610 | Ground Treatment Wk at 811A Retrieval Shaft | Sun Jun 19 08:00:00 IDT 2011 | Wed Oct 05 17:00:00 IST 2011
611 | TTMS for Building Foundation Grouting Works (Stage 1) | Mon Feb 28 08:00:00 IST 2011 | Wed Jun 15 17:00:00 IDT 2011
612 | Accesss Date for Wk Area 12.1 (Subject to SLG Approval) | Thu Jul 21 08:00:00 IDT 2011 | Thu Jul 21 08:00:00 IDT 2011
613 | Grouting Wk@Ch140+150: Bldg.Foundation (Charming Garden Blk.8) | Thu Jul 21 08:00:00 IDT 2011 | Wed Aug 31 17:00:00 IDT 2011
614 | Suspension of Grouting Wk@S/B Ch140+150(Charming Garden Blk.8) | Thu Jun 30 08:00:00 IDT 2011 | Thu Jun 30 08:00:00 IDT 2011
615 | Suspension Period for Grouting Wk in (Charming Garden Blk.8) | Mon Aug 01 08:00:00 IDT 2011 | Tue Aug 09 17:00:00 IDT 2011
616 | Re-mobilization for Grouting Wk in (Charming Garden Blk.8) | Mon Aug 01 08:00:00 IDT 2011 | Tue Aug 02 17:00:00 IDT 2011
617 | Grouting Wk@ Ch140+150:(Charming Garden Blk.8) remaining | Thu Jul 21 08:00:00 IDT 2011 | Wed Aug 31 17:00:00 IDT 2011
618 | Reinstatement@ Ch140+150:(Charming Garden Blk.8) & TTMs Stage 2 | Wed Aug 31 08:00:00 IDT 2011 | Thu Sep 15 17:00:00 IDT 2011
619 | Grouting Wk@S/B Ch140+080: Bldg.Foundation (Hoi Fu Court) | Tue Aug 09 08:00:00 IDT 2011 | Mon Dec 12 17:00:00 IST 2011
620 | Reinstatement @ Hoi Fu Court | Wed Aug 31 08:00:00 IDT 2011 | Wed Nov 16 17:00:00 IST 2011
621 | TTMS for Building Foundation Grouting Works (Stage 2) & Site Setup | Wed Feb 22 16:08:00 IST 2012 | Wed Mar 21 16:08:00 IST 2012
622 | Install Sleeve for Grouting works (Charming Garden Blk.9) | Fri Aug 31 08:00:00 IDT 2012 | Sat Sep 29 17:00:00 IST 2012
623 | Grouting Wk@S/B Ch140+200: Bldg.Foundation (Charming Garden Blk.9) | Wed Oct 03 08:00:00 IST 2012 | Mon Oct 29 17:00:00 IST 2012
624 | Reinstatement @ Charming Garden Blk.9 | Wed Jan 09 08:00:00 IST 2013 | Mon Feb 18 17:00:00 IST 2013
625 | GI works for Hoi Wang Road | Tue Feb 01 08:00:00 IST 2011 | Thu Jun 23 17:00:00 IDT 2011
626 | GI works for Tai Kok Tsui | Tue Feb 01 08:00:00 IST 2011 | Thu Dec 01 17:00:00 IST 2011
627 | Design of Ground Treatment for Tunneling (Ch140+080-Ch140+200) | Fri Apr 08 08:00:00 IDT 2011 | Sun Jun 26 17:00:00 IDT 2011
628 | MTR's Review & Comments for Design of Ground Treatment for Tunneling | Sun Jun 19 08:00:00 IDT 2011 | Sun Jun 19 08:00:00 IDT 2011
629 | MTR's Comments & Approval | Sun Jun 19 08:00:00 IDT 2011 | Fri Jul 08 17:00:00 IDT 2011
630 | Prepared Re-submission of Ground Treatment for Tunneling | Sun Jun 19 08:00:00 IDT 2011 | Thu Jun 30 17:00:00 IDT 2011
631 | Design Approval & Issue Construction Instruction MTR | Sun Jun 19 08:00:00 IDT 2011 | Sun Jul 03 17:00:00 IDT 2011
632 | TTMS for Convergence Zone (Stage 2 & 3) | Wed Aug 31 08:00:00 IDT 2011 | Sat Sep 17 17:00:00 IDT 2011
633 | Install Sleeve Pipe (Zone B) | Mon Jan 16 08:00:00 IST 2012 | Sat Mar 03 17:00:00 IST 2012
634 | Convergence Zone Grouting Wk@ Ch140+330 to Ch140+342 (Zone B) | Mon Jan 16 08:00:00 IST 2012 | Tue May 22 17:00:00 IDT 2012
635 | Reinstatement@ Ch140+330 to Ch140+342 (Zone B) | Mon Dec 03 08:00:00 IST 2012 | Wed Jan 02 17:00:00 IST 2013
636 | Install Sleeve Pipe (Zones D) | Mon Jan 16 08:00:00 IST 2012 | Fri Mar 02 17:00:00 IST 2012
637 | Convergence Zone Grouting Wk@ Ch140+361 to Ch140+380 (Zones D) | Mon Jan 16 08:00:00 IST 2012 | Sat Apr 21 17:00:00 IDT 2012
638 | Convergence Zone Grouting Wk@ Ch140+361 to Ch140+380 (Zones E) | Wed Oct 03 08:00:00 IST 2012 | Thu Jan 17 17:00:00 IST 2013
639 | Install Sleeve Pipe (Zone A) | Wed Feb 01 08:00:00 IST 2012 | Tue Feb 28 17:00:00 IST 2012
640 | Convergence Zone Grouting Wk@ Ch140+287 to Ch140+330 (Zone A) | Mon Apr 02 08:00:00 IDT 2012 | Mon Jul 09 17:00:00 IDT 2012
641 | Enlarge for TTMs Stage 4 | Wed Oct 03 08:00:00 IST 2012 | Wed Oct 24 17:00:00 IST 2012
642 | Install Sleeve Pipe (Zone C) | Sat Jun 02 08:00:00 IDT 2012 | Wed Jul 04 17:00:00 IDT 2012
643 | Convergence Zone Grouting Wk@ Ch140+342 to Ch140+361 (Zone C) | Thu Jul 05 08:00:00 IDT 2012 | Sat Nov 03 17:00:00 IST 2012
644 | Reinstatement for Convergence Zone | Fri Feb 01 08:00:00 IST 2013 | Mon Mar 18 17:00:00 IST 2013
645 | Tai Kok Tsui Grouting Works | Mon Jan 16 08:00:00 IST 2012 | Fri Nov 30 08:00:00 IST 2012
646 | Zone 1 | Fri Feb 10 08:00:00 IST 2012 | Fri Aug 31 08:00:00 IDT 2012
647 | TKT Zone 1 - TGLA granted | Fri Feb 10 08:00:00 IST 2012 | Fri Feb 10 08:00:00 IST 2012
648 | TKT Zone 1 - Access Date of works area | Sat Feb 11 08:00:00 IST 2012 | Sat Feb 11 08:00:00 IST 2012
649 | TKT Zone 1 - Trial Pit | Mon Feb 13 08:00:00 IST 2012 | Sat Feb 18 17:00:00 IST 2012
650 | TKT Zone 1 - Site Clearance + Tree Transplant | Mon Feb 20 08:00:00 IST 2012 | Thu Mar 01 17:00:00 IST 2012
651 | TKT Zone 1 - TTMS & Prepare Working platform | Fri Mar 02 08:00:00 IST 2012 | Mon Mar 26 17:00:00 IST 2012
652 | TKT Zone 1 - Install sleeve pipes | Tue Mar 27 08:00:00 IST 2012 | Mon Apr 16 17:00:00 IDT 2012
653 | TKT Zone 1 - Ground Treatment Works (TAM grouting) | Tue Apr 17 08:00:00 IDT 2012 | Mon Jul 16 17:00:00 IDT 2012
654 | TKT Zone 1 - Permeability Test | Tue Jul 17 08:00:00 IDT 2012 | Fri Jul 20 17:00:00 IDT 2012
655 | TKT Zone 1 - TBM Reach Zone 1 | Fri Aug 31 08:00:00 IDT 2012 | Fri Aug 31 08:00:00 IDT 2012
656 | Zone 2 | Mon Jan 16 08:00:00 IST 2012 | Fri Aug 31 08:00:00 IDT 2012
657 | TKT Zone 2 - TTMS (Part 1) | Mon Jan 16 08:00:00 IST 2012 | Mon Jan 16 17:00:00 IST 2012
658 | TKT Zone 2 - Trial pit | Tue Jan 17 08:00:00 IST 2012 | Sat Feb 11 17:00:00 IST 2012
659 | TKT Zone 2 - Site preparation works | Mon Feb 13 08:00:00 IST 2012 | Sat Feb 18 17:00:00 IST 2012
660 | TKT Zone 2 - Install sleeve pipes (Part 1) | Mon Feb 20 08:00:00 IST 2012 | Tue Feb 28 17:00:00 IST 2012
661 | TKT Zone 2 - TTMS (Part 2) | Wed Feb 29 08:00:00 IST 2012 | Tue Mar 13 17:00:00 IST 2012
662 | TKT Zone 2 - Trial pit (Part 2) | Wed Mar 14 08:00:00 IST 2012 | Sat Mar 24 17:00:00 IST 2012
663 | TKT Zone 2 - Site preparation works | Mon Mar 26 08:00:00 IST 2012 | Thu Mar 29 17:00:00 IST 2012
664 | TKT Zone 2 - Install sleeve pipes (Part 2) | Fri Mar 30 08:00:00 IDT 2012 | Fri Apr 13 17:00:00 IDT 2012
665 | TKT Zone 2 - Ground Treatment Works (TAM grouting) (Part 2) | Sat Apr 14 08:00:00 IDT 2012 | Mon May 28 17:00:00 IDT 2012
666 | TKT Zone 2 - Re-arrange TTMS (Part 1) | Tue May 29 08:00:00 IDT 2012 | Thu Jun 07 17:00:00 IDT 2012
667 | TKT Zone 2 - Ground Treatment Works (TAM grouting) (Part 1) | Sat Jun 09 08:00:00 IDT 2012 | Wed Aug 15 17:00:00 IDT 2012
668 | TKT Zone 2 - Permeability Test | Thu Aug 16 08:00:00 IDT 2012 | Mon Aug 20 17:00:00 IDT 2012
669 | TKT Zone 2 - Temporary reinstatement | Tue Aug 21 08:00:00 IDT 2012 | Wed Aug 29 17:00:00 IDT 2012
670 | TKT Zone 2 - TBM Reach Zone 2 | Fri Aug 31 08:00:00 IDT 2012 | Fri Aug 31 08:00:00 IDT 2012
671 | Zone 3 | Mon Jan 16 08:00:00 IST 2012 | Fri Nov 30 08:00:00 IST 2012
672 | TKT Zone 3 - TTMS (Part 1) | Mon Jan 16 08:00:00 IST 2012 | Mon Jan 16 17:00:00 IST 2012
673 | TKT Zone 3 - Trial pit + grout pattern design | Tue Jan 17 08:00:00 IST 2012 | Thu Feb 09 17:00:00 IST 2012
674 | TKT Zone 3 - Install sleeve pipes (Part 1) | Fri Feb 10 08:00:00 IST 2012 | Sat Feb 18 17:00:00 IST 2012
675 | TKT Zone 3 - TTMS (Part 2) + site preparation + Install sleeve pipes (Part 2) | Mon Feb 20 08:00:00 IST 2012 | Tue Mar 20 17:00:00 IST 2012
676 | TKT Zone 3 - Site setup | Wed Mar 21 08:00:00 IST 2012 | Tue Mar 27 17:00:00 IST 2012
677 | TKT Zone 3 - Drilling for Ground treatment works | Wed Mar 28 08:00:00 IST 2012 | Mon Apr 30 17:00:00 IDT 2012
678 | TKT Zone 3 - Further soil investigation to review ground treatment requirement | Sat Apr 14 08:00:00 IDT 2012 | Mon Apr 30 17:00:00 IDT 2012
679 | TKT Zone 3 - Decision to confirm ground treatment requirement | Mon Apr 30 17:00:00 IDT 2012 | Mon Apr 30 17:00:00 IDT 2012
680 | TKT Zone 3 - TBM Reach Zone 3 | Fri Nov 30 08:00:00 IST 2012 | Fri Nov 30 08:00:00 IST 2012
681 | TBM Excavation (South-DT) | Sun Jan 15 08:00:00 IST 2012 | Tue Sep 29 17:00:00 IDT 2015
682 | D/T Excavation Ch139+872-139+875 | Thu Aug 15 08:00:00 IDT 2013 | Sat Aug 17 17:00:00 IDT 2013
683 | TBM resume at Ch139+875 | Fri Aug 16 08:00:00 IDT 2013 | Fri Aug 16 08:00:00 IDT 2013
684 | TBM (S630-1) Delivery on Site | Sun Jan 15 08:00:00 IST 2012 | Sun Jan 15 08:00:00 IST 2012
685 | TBM (S630-1) Assembly, and T&C | Fri Mar 16 08:00:00 IST 2012 | Wed May 30 17:00:00 IDT 2012
686 | D/T TBM (S630-1) Break-in & Excavation Ch137+941-137+967 | Wed Mar 21 08:00:00 IST 2012 | Thu Mar 29 17:00:00 IST 2012
687 | Reach Rising Main & FMO Pier A Obstruction | Thu Mar 29 17:00:00 IST 2012 | Thu Mar 29 17:00:00 IST 2012
688 | D/T Excavation Ch137+967-138+025 | Fri Mar 30 08:00:00 IDT 2012 | Wed Apr 18 17:00:00 IDT 2012
689 | D/T Excavation Ch138+025-138+043 | Thu Apr 19 08:00:00 IDT 2012 | Fri Apr 20 17:00:00 IDT 2012
690 | Reach FMO Pier B Pile Obstruction Ch138+043 | Fri Apr 20 17:00:00 IDT 2012 | Fri Apr 20 17:00:00 IDT 2012
691 | D/T Excavation Ch138+043-138+109 | Sat Apr 21 08:00:00 IDT 2012 | Fri Apr 27 17:00:00 IDT 2012
692 | Reach CP89 (CH138+055) | Sun Apr 22 08:00:00 IDT 2012 | Sun Apr 22 08:00:00 IDT 2012
693 | D/T Excavation Ch138+109-138+149 | Sat Apr 28 08:00:00 IDT 2012 | Mon Apr 30 17:00:00 IDT 2012
694 | Obstructions Removal Below Nam Cheong Property/802 (11Dec2011-Contract) | Sun Jan 15 08:00:00 IST 2012 | Sun Jan 15 08:00:00 IST 2012
695 | Unobstructed Passage Available (30April2012) | Mon Apr 30 08:00:00 IDT 2012 | Mon Apr 30 08:00:00 IDT 2012
696 | Reach Nam Cheong Property Development (Pile removed by 802) | Mon Apr 30 17:00:00 IDT 2012 | Mon Apr 30 17:00:00 IDT 2012
697 | Obstructions Removal Below Nam Cheong Property by 802 (30Apr12) | Mon Apr 30 17:00:00 IDT 2012 | Mon Apr 30 17:00:00 IDT 2012
698 | D/T Excavation Ch138+149-Ch138+170 | Tue May 01 08:00:00 IDT 2012 | Wed May 02 17:00:00 IDT 2012
699 | D/T Excavation Ch138+170-138+420 | Thu May 03 08:00:00 IDT 2012 | Tue May 29 17:00:00 IDT 2012
700 | Reach CP90 (CH138+315) | Sat May 19 08:00:00 IDT 2012 | Sat May 19 08:00:00 IDT 2012
701 | D/T Excavation Ch138+420-138+457 | Wed May 30 08:00:00 IDT 2012 | Fri Jun 01 17:00:00 IDT 2012
702 | Reach Shum Shui Po Pier Pile Obstruction Ch138+457 | Fri Jun 01 17:00:00 IDT 2012 | Fri Jun 01 17:00:00 IDT 2012
703 | D/T Excavation Ch138+457-138+480 | Sat Jun 02 08:00:00 IDT 2012 | Sun Jun 03 17:00:00 IDT 2012
704 | D/T Excavation Ch138+480-138+590 | Mon Jun 04 08:00:00 IDT 2012 | Tue Jun 12 17:00:00 IDT 2012
705 | Reach CP91 (CH138+521) | Thu Jun 07 08:00:00 IDT 2012 | Thu Jun 07 08:00:00 IDT 2012
706 | Reach YC2 Culvert Pile Obstruction Ch138+590 | Tue Jun 12 17:00:00 IDT 2012 | Tue Jun 12 17:00:00 IDT 2012
707 | D/T Excavation Ch138+590-138+771 | Wed Jun 13 08:00:00 IDT 2012 | Wed Jun 27 17:00:00 IDT 2012
708 | Reach CP92 (CH138+771) | Wed Jun 27 17:00:00 IDT 2012 | Wed Jun 27 17:00:00 IDT 2012
709 | D/T Excavation Ch138+771-138+950 | Thu Jun 28 08:00:00 IDT 2012 | Tue Jul 10 17:00:00 IDT 2012
710 | Reach NC1 Culvert Pile Obstruction Ch138+950 | Tue Jul 10 17:00:00 IDT 2012 | Tue Jul 10 17:00:00 IDT 2012
711 | D/T Excavation Ch138+950-139+044 | Wed Jul 11 08:00:00 IDT 2012 | Tue Jul 17 17:00:00 IDT 2012
712 | Reach CP93 (CH138+996) | Sat Jul 14 08:00:00 IDT 2012 | Sat Jul 14 08:00:00 IDT 2012
713 | Piles Removal@CLP Equipment Bldg.& Footbridges KF-119 by 805 | Sun Jan 15 08:00:00 IST 2012 | Sun Jan 15 08:00:00 IST 2012
714 | Reach Footbridge KF119 (Pile removed by 805) | Fri Aug 31 08:00:00 IDT 2012 | Fri Aug 31 08:00:00 IDT 2012
715 | D/T Excavation Ch139+044-139+100 | Fri Aug 31 08:00:00 IDT 2012 | Wed Sep 05 17:00:00 IDT 2012
716 | D/T Excavation Ch139+100-139+120 | Thu Sep 06 08:00:00 IDT 2012 | Sun Sep 09 17:00:00 IDT 2012
717 | D/T Excavation Ch139+120-139+350 | Mon Sep 10 08:00:00 IDT 2012 | Wed Nov 07 17:00:00 IST 2012
718 | Reach CP94(CH139+265) | Wed Oct 24 17:00:00 IST 2012 | Wed Oct 24 17:00:00 IST 2012
719 | D/T Excavation Ch139+350-139+450 | Thu Nov 15 08:00:00 IST 2012 | Wed Nov 28 17:00:00 IST 2012
720 | D/T Excavation Ch139+450-139+825 | Tue Nov 13 08:00:00 IST 2012 | Sat Dec 15 17:00:00 IST 2012
721 | Reach CP95(CH139+504) | Sun Nov 18 08:00:00 IST 2012 | Sun Nov 18 08:00:00 IST 2012
722 | Reach CP96(CH139+711) | Fri Dec 28 17:00:00 IST 2012 | Fri Dec 28 17:00:00 IST 2012
723 | D/T Excavation Ch139+825-139+872 | Mon Jan 21 08:00:00 IST 2013 | Wed Jan 30 17:00:00 IST 2013
724 | **HWR H-pile Obstruction Removal | Tue Jan 22 08:00:00 IST 2013 | Thu Aug 15 17:00:00 IDT 2013
725 | D/T Excavation Ch139+875 -139+920 | Fri Aug 16 08:00:00 IDT 2013 | Mon Aug 19 17:00:00 IDT 2013
726 | D/T Excavation Ch139+920-139+950 | Sat Aug 24 08:00:00 IDT 2013 | Sun Aug 25 17:00:00 IDT 2013
727 | D/T Excavation Ch139+950-140+010 | Mon Aug 26 08:00:00 IDT 2013 | Thu Aug 29 17:00:00 IDT 2013
728 | Reach CP97 (CH139+961) | Mon Aug 26 17:00:00 IDT 2013 | Mon Aug 26 17:00:00 IDT 2013
729 | D/T Excavation Ch140+010-140+180 | Sat Aug 31 08:00:00 IDT 2013 | Tue Sep 10 17:00:00 IDT 2013
730 | Reach Hoi Fu Court (CH140+063) | Tue Sep 03 17:00:00 IDT 2013 | Tue Sep 03 17:00:00 IDT 2013
731 | Reach Charming Garden No.8 (CH140+139) | Sun Sep 08 17:00:00 IDT 2013 | Sun Sep 08 17:00:00 IDT 2013
732 | D/T Excavation Ch140+180-140+270 | Wed Sep 11 08:00:00 IDT 2013 | Wed Sep 18 17:00:00 IDT 2013
733 | Reach CP98(CH140+211) | Fri Sep 13 17:00:00 IDT 2013 | Fri Sep 13 17:00:00 IDT 2013
734 | Reach Charming Garden No.9 (CH140+207) | Fri Sep 13 17:00:00 IDT 2013 | Fri Sep 13 17:00:00 IDT 2013
735 | Advance Noice to Contract 811A for TBM Break In (30d) | Fri Aug 16 17:00:00 IDT 2013 | Fri Aug 16 17:00:00 IDT 2013
736 | D/T Excavation Ch140+270-140+385-Shaft 811A | Tue Sep 17 08:00:00 IDT 2013 | Sat Sep 28 17:00:00 IDT 2013
737 | Exit Convergence Zone (Ch140+287~) | Wed Sep 18 17:00:00 IDT 2013 | Wed Sep 18 17:00:00 IDT 2013
738 | D/T exit Box Cleaning for TBM Dismantling | Fri Sep 25 08:00:00 IDT 2015 | Tue Sep 29 17:00:00 IDT 2015
739 | Advance Noice to Contract 811A for Set Up of TBM Retrieval (60d) | Thu Aug 01 17:00:00 IDT 2013 | Thu Aug 01 17:00:00 IDT 2013
740 | D/T Preparation Works inside Exit Shaft 811A | Mon Aug 26 08:00:00 IDT 2013 | Sat Sep 28 17:00:00 IDT 2013
741 | TBM (S630-1) Backup pull back | Mon Oct 07 08:00:00 IDT 2013 | Wed Oct 16 17:00:00 IDT 2013
742 | TBM (S630-1) Shield Dismantle & Removal | Mon Sep 30 08:00:00 IDT 2013 | Sun Nov 10 17:00:00 IST 2013
743 | Setup Equipment for Invert & Walkway Construction (Ch140+385-811A Shaft to Ch139+224-CP94) | Mon Nov 18 08:00:00 IST 2013 | Sat Nov 30 17:00:00 IST 2013
744 | Tunnel Invert & Walkway (811A side - Ch140+385-811A Shaft to Ch139+224-CP94) | Mon Dec 02 08:00:00 IST 2013 | Wed Mar 05 17:00:00 IST 2014
745 | Setup Equipment for Invert & Walkway Construction (Ch137+941-NAC Shaft to Ch139+224-CP94) | Tue Feb 04 08:00:00 IST 2014 | Fri Feb 14 17:00:00 IST 2014
746 | Tunnel Invert & Walkway (820 side - Ch137+941-NAC Shaft to Ch139+224-CP94) | Wed Feb 12 08:00:00 IST 2014 | Mon May 19 17:00:00 IDT 2014
747 | Deg. 1 Works (4A(ii) Target: 18-May-14) | Sat Mar 01 08:00:00 IST 2014 | Mon Jun 23 17:00:00 IDT 2014
748 | Uptrack Construction (South) | Wed Aug 31 08:00:00 IDT 2011 | Mon Jan 26 17:00:00 IST 2015
749 | Ground Treatment (South-UT) | Wed Aug 31 08:00:00 IDT 2011 | Wed Nov 20 17:00:00 IST 2013
750 | Works Area 12.1 (Subject to SLG Approval) | Wed Aug 31 08:00:00 IDT 2011 | Wed Aug 31 08:00:00 IDT 2011
751 | Site Set up for Y.M.T School Grouting Works | Wed Aug 31 08:00:00 IDT 2011 | Mon Oct 31 17:00:00 IST 2011
752 | Install Sleeve Pipe (Y.M.T. Catholic Primary School) (UT) | Mon Jan 16 08:00:00 IST 2012 | Tue Feb 14 17:00:00 IST 2012
753 | Grouting Wk@N/B Ch140+340: Bldg. Foundation (Y.M.T. Catholic Primary School) (UT) | Mon Jan 16 08:00:00 IST 2012 | Thu Apr 19 17:00:00 IDT 2012
754 | Reinstatement Works for Y.M.T. School | Fri Aug 31 08:00:00 IDT 2012 | Sat Sep 29 17:00:00 IST 2012
755 | Tai Kok Tsui Grouting Works | Mon Mar 26 08:00:00 IST 2012 | Wed Nov 20 17:00:00 IST 2013
756 | Zone 4 | Mon Mar 26 08:00:00 IST 2012 | Wed Nov 20 17:00:00 IST 2013
757 | TKT Zone 4 - Trial pit | Mon Mar 26 08:00:00 IST 2012 | Wed Apr 11 17:00:00 IDT 2012
758 | TKT Zone 4 - Sleeves installation | Wed Oct 03 08:00:00 IST 2012 | Thu Oct 11 17:00:00 IST 2012
759 | TKT Zone 4 - Ground Treatment Works (TAM grouting) | Fri Oct 12 08:00:00 IST 2012 | Wed Jan 09 17:00:00 IST 2013
760 | TKT Zone 4 - Permeability Test | Mon Apr 15 08:00:00 IDT 2013 | Thu Apr 18 17:00:00 IDT 2013
761 | TKT Zone 4 - Reinstatement | Mon Aug 12 08:00:00 IDT 2013 | Wed Nov 20 17:00:00 IST 2013
762 | Zone 5 | Fri Nov 09 08:00:00 IST 2012 | Thu Jul 04 17:00:00 IDT 2013
763 | TKT Zone 5 - Trial pit | Fri Nov 30 08:00:00 IST 2012 | Sat Dec 22 17:00:00 IST 2012
764 | TKT Zone 5 - Install guide sleeves (Stage 1) | Mon Dec 24 08:00:00 IST 2012 | Fri Jan 11 17:00:00 IST 2013
765 | TKT Zone 5 - TTMS (Part 2) + Trial pit | Fri Nov 09 08:00:00 IST 2012 | Sat Dec 15 17:00:00 IST 2012
766 | TKT Zone 5 - Install guide sleeves (Stage 2) | Wed Jan 02 08:00:00 IST 2013 | Wed Jan 16 17:00:00 IST 2013
767 | TKT Zone 5 - Ground Treatment Works (TAM grouting) Part 2 | Thu Jan 17 08:00:00 IST 2013 | Mon Mar 18 17:00:00 IST 2013
768 | TKT Zone 5 - Rearrange TTMS (Part 1) | Thu Jan 10 08:00:00 IST 2013 | Wed Jan 23 17:00:00 IST 2013
769 | TKT Zone 5 - Ground Treatment Works (TAM grouting) Part 1 | Fri Jan 11 08:00:00 IST 2013 | Mon Mar 04 17:00:00 IST 2013
770 | TKT Zone 5 - Permeability Test | Mon Mar 25 08:00:00 IST 2013 | Thu Mar 28 17:00:00 IST 2013
771 | TKT Zone 5 - Reinstatement | Tue Apr 30 08:00:00 IDT 2013 | Thu Jul 04 17:00:00 IDT 2013
772 | Zone 6 | Sat Apr 14 08:00:00 IDT 2012 | Mon Apr 30 17:00:00 IDT 2012
773 | TKT Zone 6 - Further soil investigation to review ground treatment requirement | Sat Apr 14 08:00:00 IDT 2012 | Mon Apr 30 17:00:00 IDT 2012
774 | TKT Zone 6 - Decision to confirm ground treatment requirement | Mon Apr 30 17:00:00 IDT 2012 | Mon Apr 30 17:00:00 IDT 2012
775 | TBM Excavation (South-UT) | Sun Jan 15 08:00:00 IST 2012 | Mon Jan 26 17:00:00 IST 2015
776 | TBM S630-1 Re-assembly | Tue Oct 15 08:00:00 IDT 2013 | Fri Dec 06 17:00:00 IST 2013
777 | U/T Excavation Ch137+968-137+993 (Break-in) | Sat Dec 14 08:00:00 IST 2013 | Thu Dec 19 17:00:00 IST 2013
778 | Reach Rising Main & FMO Pier A Obstruction | Thu Dec 19 17:00:00 IST 2013 | Thu Dec 19 17:00:00 IST 2013
779 | U/T Excavation Ch137+993-138+040 | Thu Dec 19 08:00:00 IST 2013 | Mon Dec 30 17:00:00 IST 2013
780 | U/T Excavation Ch138+040-138+070 | Wed Dec 25 08:00:00 IST 2013 | Thu Dec 26 17:00:00 IST 2013
781 | Reach FMO Pier B Pile Obstruction Ch138+070 | Thu Dec 26 17:00:00 IST 2013 | Thu Dec 26 17:00:00 IST 2013
782 | U/T Excavation Ch138+070-138+175 | Thu Dec 26 08:00:00 IST 2013 | Thu Jan 02 17:00:00 IST 2014
783 | Reach CP89 (CH138+081) | Fri Dec 27 17:00:00 IST 2013 | Fri Dec 27 17:00:00 IST 2013
784 | Obstructions Removal BelowNamCheong Property/ 802 (11Dec2011-Contract) | Sun Jan 15 08:00:00 IST 2012 | Sun Jan 15 08:00:00 IST 2012
785 | Unobstructed Pasage Available (30 April 2013) (further confirm by MTR) | Tue Apr 30 17:00:00 IDT 2013 | Tue Apr 30 17:00:00 IDT 2013
786 | Reach Nam Cheong Property Property / 802 | Mon Dec 30 17:00:00 IST 2013 | Mon Dec 30 17:00:00 IST 2013
787 | Obstructions Removal Below Nam Cheong Property by 802 | Tue Apr 30 17:00:00 IDT 2013 | Tue Apr 30 17:00:00 IDT 2013
788 | U/T Excavation Ch138+175 -138+450 | Sat Jan 04 08:00:00 IST 2014 | Sun Jan 26 17:00:00 IST 2014
789 | Reach CP90 (CH138+341) | Fri Apr 04 17:00:00 IDT 2014 | Fri Apr 04 17:00:00 IDT 2014
790 | U/T Excavation Ch138+450-138+490 | Wed Apr 09 08:00:00 IDT 2014 | Fri Apr 11 17:00:00 IDT 2014
791 | Reach Shum Shui Po Pier Pile Obstruction Ch138+490 | Fri Apr 11 17:00:00 IDT 2014 | Fri Apr 11 17:00:00 IDT 2014
792 | U/T Excavation Ch138+490-138+610 | Fri Apr 11 08:00:00 IDT 2014 | Fri Apr 18 17:00:00 IDT 2014
793 | Reach CP91 (CH138+546) | Mon Apr 14 17:00:00 IDT 2014 | Mon Apr 14 17:00:00 IDT 2014
794 | Reach YC2 Culvert Pile Obstruction Ch138+610 | Thu Apr 17 17:00:00 IDT 2014 | Thu Apr 17 17:00:00 IDT 2014
795 | U/T Excavation Ch138+610-138+670 | Thu Apr 17 08:00:00 IDT 2014 | Sun Apr 20 17:00:00 IDT 2014
796 | Reach NC1 Culvert Pile Obstruction Ch138+670 | Tue Apr 22 17:00:00 IDT 2014 | Tue Apr 22 17:00:00 IDT 2014
797 | U/T Excavation Ch138+670-139+026 | Tue Apr 22 08:00:00 IDT 2014 | Fri May 16 17:00:00 IDT 2014
798 | Reach CP92 (CH138+796) | Tue Apr 29 17:00:00 IDT 2014 | Tue Apr 29 17:00:00 IDT 2014
799 | Reach CP93 (CH139+021) | Sun May 11 17:00:00 IDT 2014 | Sun May 11 17:00:00 IDT 2014
800 | Piles Removal@CLP Equipment Bldg.& Footbridges KF-119 by 805 | Sun Jan 15 08:00:00 IST 2012 | Sun Jan 15 08:00:00 IST 2012
801 | Reach Footbridge KF119 (Piles removed by 805) | Wed Mar 12 17:00:00 IST 2014 | Wed Mar 12 17:00:00 IST 2014
802 | U/T Excavation Ch139+026-139+150 | Mon May 12 08:00:00 IDT 2014 | Tue May 20 17:00:00 IDT 2014
803 | U/T Excavation Ch139+150-139+360 | Thu May 22 08:00:00 IDT 2014 | Wed Jul 09 17:00:00 IDT 2014
804 | Reach CP94 (CH139+287) | Fri Jun 27 17:00:00 IDT 2014 | Fri Jun 27 17:00:00 IDT 2014
805 | U/T Excavation Ch139+360-139+530 | Fri Jun 27 08:00:00 IDT 2014 | Mon Jul 14 17:00:00 IDT 2014
806 | Reach CP95 (CH139+524) | Wed Jul 23 17:00:00 IDT 2014 | Wed Jul 23 17:00:00 IDT 2014
807 | U/T Excavation Ch139+530-139+825 | Thu Jul 24 08:00:00 IDT 2014 | Sat Aug 16 17:00:00 IDT 2014
808 | Reach CP96 (CH139+729) | Sat Aug 16 17:00:00 IDT 2014 | Sat Aug 16 17:00:00 IDT 2014
809 | U/T Excavation Ch139+825-139+875 | Sat Aug 30 08:00:00 IDT 2014 | Mon Sep 08 17:00:00 IDT 2014
810 | U/T Excavation Ch139+875-139+950 | Thu Sep 04 08:00:00 IDT 2014 | Wed Sep 10 17:00:00 IDT 2014
811 | U/T Excavation Ch139+950-140+010 | Mon Sep 08 08:00:00 IDT 2014 | Thu Sep 11 17:00:00 IDT 2014
812 | Reach CP97 (CH139+977) | Tue Sep 09 17:00:00 IDT 2014 | Tue Sep 09 17:00:00 IDT 2014
813 | Advance Noice to Contract 811A for Set Up of TBM Retrieval (60d) | Fri Jun 27 17:00:00 IDT 2014 | Fri Jun 27 17:00:00 IDT 2014
814 | Advance Noice to Contract 811A for TBM Break-out (30d) | Fri Aug 15 17:00:00 IDT 2014 | Fri Aug 15 17:00:00 IDT 2014
815 | U/T Excavation Ch140+010-140+394-Shaft 811A (Break-out) | Wed Sep 10 08:00:00 IDT 2014 | Wed Oct 08 17:00:00 IDT 2014
816 | Reach CP98 (CH140+226) | Fri Sep 19 17:00:00 IDT 2014 | Fri Sep 19 17:00:00 IDT 2014
817 | Reach YMT School (CH140+335) | Wed Sep 24 17:00:00 IDT 2014 | Wed Sep 24 17:00:00 IDT 2014
818 | U/T exit Box Cleaning for TBM Dismantling | Tue Sep 30 08:00:00 IDT 2014 | Sat Oct 04 17:00:00 IDT 2014
819 | U/T Preparation Works inside Exit Shaft 811A | Mon Sep 01 08:00:00 IDT 2014 | Sat Oct 04 17:00:00 IDT 2014
820 | TBM (S630-1) Shield Dismantle & Removal | Mon Oct 06 08:00:00 IDT 2014 | Mon Nov 10 17:00:00 IST 2014
821 | TBM (S630-1) Backup Removal | Sat Nov 01 08:00:00 IST 2014 | Mon Nov 10 17:00:00 IST 2014
822 | Setup Equipment for Invert & Walkway Construction (Ch137+941-NAC Shaft to Ch139+435) (7 working days) | Thu Oct 16 08:00:00 IDT 2014 | Mon Oct 20 17:00:00 IDT 2014
823 | Setup Equipment for Invert & Walkway Construction (Ch140+385-811A Shaft to Ch139+435) | Mon Nov 03 08:00:00 IST 2014 | Thu Nov 13 17:00:00 IST 2014
824 | 820 side - Tunnel Invert & Walkway (Ch137+941-NAC Shaft to Ch139+435, 1494m) (7 working days) | Tue Oct 21 08:00:00 IDT 2014 | Sat Jan 03 17:00:00 IST 2015
825 | 820 side - Deg. 1 Works (Ch137+941-Shaft to Ch139+435) (4B(ii) Target: 21-Dec-14) (7 working days) | Mon Nov 03 08:00:00 IST 2014 | Sat Dec 27 17:00:00 IST 2014
826 | 811A side -Tunnel Invert & Walkway (Ch139+435 to Ch140+385-811A Shaft, 950m) | Mon Nov 10 08:00:00 IST 2014 | Mon Jan 19 17:00:00 IST 2015
827 | 811A side - Deg. 1 Works ( Ch140+385-811A Shaft to Ch139+435) (4B(iii) Target: 25-Jan-15) | Mon Dec 01 08:00:00 IST 2014 | Mon Jan 26 17:00:00 IST 2015
828 | Tunnel Alignment Design/Submission/Approval | Mon Jan 31 08:00:00 IST 2011 | Thu Jul 07 17:00:00 IDT 2011
829 | Design | Mon Jan 31 08:00:00 IST 2011 | Thu Jul 07 17:00:00 IDT 2011
830 | AIP Submission Preparation - Tunnel Alignment | Mon Jan 31 08:00:00 IST 2011 | Mon Feb 21 17:00:00 IST 2011
831 | AIP Submission to MTR (RDO/GEO consultation) | Sat Mar 12 17:00:00 IST 2011 | Sat Mar 12 17:00:00 IST 2011
832 | AIP Comment by MTR (RDO/GEO consultation) | Sun Mar 13 08:00:00 IST 2011 | Sun Mar 27 17:00:00 IST 2011
833 | AIP ReSubmission Preparation - Tunnel Alignment | Wed Apr 06 08:00:00 IDT 2011 | Mon Apr 18 17:00:00 IDT 2011
834 | AIP ReSubmission to MTR (RDO/GEO consultation) | Sat May 07 17:00:00 IDT 2011 | Sat May 07 17:00:00 IDT 2011
835 | AIP Approval by MTR (RDO/GEO consultation) | Sun May 08 08:00:00 IDT 2011 | Thu Jul 07 17:00:00 IDT 2011
836 | DD Submission MTR/RDO for Record | Tue May 31 17:00:00 IDT 2011 | Tue May 31 17:00:00 IDT 2011
837 | Cross Passages | Thu Oct 21 08:00:00 IST 2010 | Tue Jan 13 17:00:00 IST 2015
838 | CP81 (XRL821) | Mon Mar 04 08:00:00 IST 2013 | Tue Apr 02 17:00:00 IDT 2013
839 | CP82 (XRL821) | Tue Jul 23 08:00:00 IDT 2013 | Tue Mar 18 17:00:00 IST 2014
840 | CP83 (XRL821) | Sat May 11 08:00:00 IDT 2013 | Wed Jan 22 17:00:00 IST 2014
841 | CP84 (XRL821) | Sat Apr 06 08:00:00 IDT 2013 | Wed Jan 08 17:00:00 IST 2014
842 | CP85 | Tue Jan 15 08:00:00 IST 2013 | Fri Sep 13 17:00:00 IDT 2013
843 | CP86 Jet / Fissure Grouting from Surface | Mon Jan 16 08:00:00 IST 2012 | Sat Oct 20 17:00:00 IST 2012
844 | CP86 | Sat Dec 15 08:00:00 IST 2012 | Mon Aug 12 17:00:00 IDT 2013
845 | CP87 | Fri Aug 31 08:00:00 IDT 2012 | Thu Sep 26 17:00:00 IDT 2013
846 | CP88 Jet Grouting from Surface | Wed Aug 31 08:00:00 IDT 2011 | Mon Dec 12 17:00:00 IST 2011
847 | CP88 | Fri Aug 31 08:00:00 IDT 2012 | Wed Sep 11 17:00:00 IDT 2013
848 | CP89 Grouting from Surface | Wed Aug 31 08:00:00 IDT 2011 | Thu Mar 29 17:00:00 IST 2012
849 | CP89 | Fri Sep 07 08:00:00 IDT 2012 | Sat Oct 26 17:00:00 IDT 2013
850 | CP90 | Fri Aug 31 08:00:00 IDT 2012 | Sat Dec 28 17:00:00 IST 2013
851 | CP91 Grouting from Surface | Mon Sep 12 08:00:00 IDT 2011 | Wed Mar 21 17:00:00 IST 2012
852 | CP91 | Wed Oct 31 08:00:00 IST 2012 | Thu Oct 17 17:00:00 IDT 2013
853 | CP92 Grouting from Surface | Wed Aug 31 08:00:00 IDT 2011 | Wed Mar 28 17:00:00 IST 2012
854 | CP92 | Wed Oct 31 08:00:00 IST 2012 | Mon Nov 04 17:00:00 IST 2013
855 | CP93 Grouting from Surface | Mon Jan 16 08:00:00 IST 2012 | Thu Oct 04 17:00:00 IST 2012
856 | CP93 | Tue Nov 27 08:00:00 IST 2012 | Mon Nov 18 17:00:00 IST 2013
857 | CP94 Fissure Grouting from Tunnel | Mon Dec 31 08:00:00 IST 2012 | Tue May 14 17:00:00 IDT 2013
858 | CP94 | Sat May 25 08:00:00 IDT 2013 | Tue Jan 21 13:38:00 IST 2014
859 | CP95 & pump Sump | Wed Jul 24 08:00:00 IDT 2013 | Fri Mar 21 13:38:00 IST 2014
860 | CP96 | Tue Sep 30 08:00:00 IDT 2014 | Thu Nov 20 17:00:00 IST 2014
861 | CP97 Jet Grouting from Surface | Mon Jan 16 08:00:00 IST 2012 | Wed Oct 31 17:00:00 IST 2012
862 | CP97 | Sun Nov 30 08:00:00 IST 2014 | Tue Dec 09 17:00:00 IST 2014
863 | CP98 | Sat Nov 30 08:00:00 IST 2013 | Sat Nov 30 08:00:00 IST 2013
864 | TTM Scheme Submission & Approval | Mon Jan 31 08:00:00 IST 2011 | Tue Jul 19 17:00:00 IDT 2011
865 | Prepare Temporary Traffic Management | Mon Jan 31 08:00:00 IST 2011 | Tue Mar 01 17:00:00 IST 2011
866 | TTM reviewed by SLG | Wed Mar 02 08:00:00 IST 2011 | Tue Mar 08 17:00:00 IST 2011
867 | Notification to RMO | Sun Jun 19 08:00:00 IDT 2011 | Wed Jul 06 17:00:00 IDT 2011
868 | XP Application & Approval | Sun Jun 19 08:00:00 IDT 2011 | Tue Jul 19 17:00:00 IDT 2011
869 | Implement TTM | Sun Jun 19 17:00:00 IDT 2011 | Sun Jun 19 17:00:00 IDT 2011
870 | CP81 (XRL821) | Sat Feb 23 08:00:00 IST 2013 | Tue Jan 13 17:00:00 IST 2015
871 | CP81 Preparation works for Grouting | Mon Mar 04 08:00:00 IST 2013 | Tue Apr 02 17:00:00 IDT 2013
872 | CP81 Fissure Grouting from Tunnel | Mon Mar 04 08:00:00 IST 2013 | Thu May 16 17:00:00 IDT 2013
873 | Probing/Drainage (from DT) | Mon Mar 11 08:00:00 IST 2013 | Wed Mar 13 17:00:00 IST 2013
874 | Segment Dismantle (DT) | Mon Mar 11 08:00:00 IST 2013 | Sat Mar 16 17:00:00 IST 2013
875 | Tunnel Frame Support (DT) | Mon Mar 11 08:00:00 IST 2013 | Sat Mar 16 17:00:00 IST 2013
876 | Mobilization (UT) | Mon Nov 11 08:00:00 IST 2013 | Wed Nov 13 17:00:00 IST 2013
877 | Probing/Drainage (from UT) | Wed Nov 13 08:00:00 IST 2013 | Tue Nov 19 17:00:00 IST 2013
878 | Segment Dismantle (UT) | Fri Nov 15 08:00:00 IST 2013 | Thu Nov 21 17:00:00 IST 2013
879 | Cross Passage Excavation & Temp.Support (from UT) | Sat Feb 23 08:00:00 IST 2013 | Fri Mar 01 17:00:00 IST 2013
880 | Waterproofing | Tue Nov 19 08:00:00 IST 2013 | Thu Nov 28 17:00:00 IST 2013
881 | Permanent Beam | Sat Jan 04 08:00:00 IST 2014 | Tue Jan 14 17:00:00 IST 2014
882 | Permanent Lining | Wed Jan 07 08:00:00 IST 2015 | Tue Jan 13 17:00:00 IST 2015
883 | Permanent Slab | Mon Nov 25 08:00:00 IST 2013 | Sat Nov 30 17:00:00 IST 2013
884 | CP82 (XRL821) | Sat Dec 15 08:00:00 IST 2012 | Tue Mar 18 17:00:00 IST 2014
885 | CP82 (XRL821) | Tue Jul 23 08:00:00 IDT 2013 | Tue Mar 18 17:00:00 IST 2014
886 | CP82 Preparation works for Grouting | Sat Dec 15 08:00:00 IST 2012 | Wed Jan 16 17:00:00 IST 2013
887 | CP82 Fissure Grouting from Tunnel | Sat Dec 15 08:00:00 IST 2012 | Tue Mar 05 17:00:00 IST 2013
888 | Probing/Drainage (DT) | Sat Dec 15 08:00:00 IST 2012 | Sat Dec 22 17:00:00 IST 2012
889 | Segment Dismantle (DT) | Sat Dec 15 08:00:00 IST 2012 | Sat Dec 22 17:00:00 IST 2012
890 | Cross Passage Excavation & Temp.Support (from DT) | Tue Mar 12 08:00:00 IST 2013 | Mon Mar 25 17:00:00 IST 2013
891 | Waterproofing (DT) | Mon Mar 25 08:00:00 IST 2013 | Sat Apr 06 17:00:00 IDT 2013
892 | Permanent Beam (DT) | Mon Apr 08 08:00:00 IDT 2013 | Thu Apr 18 17:00:00 IDT 2013
893 | Probing/Drainage (UT) | Thu Nov 21 08:00:00 IST 2013 | Wed Nov 27 17:00:00 IST 2013
894 | Segment Dismantle (UT) | Thu Nov 21 08:00:00 IST 2013 | Wed Nov 27 17:00:00 IST 2013
895 | Cross Passage Excavation & Temp.Support (from UT) | Tue Mar 12 08:00:00 IST 2013 | Wed Mar 20 17:00:00 IST 2013
896 | Waterproofing (UT) | Thu Nov 21 08:00:00 IST 2013 | Sat Nov 30 17:00:00 IST 2013
897 | Permanent Beam (UT) | Thu Nov 21 08:00:00 IST 2013 | Sat Nov 30 17:00:00 IST 2013
898 | Permanent Lining | Thu Nov 21 08:00:00 IST 2013 | Wed Nov 27 17:00:00 IST 2013
899 | Permanent Slab | Thu Nov 21 08:00:00 IST 2013 | Wed Nov 27 17:00:00 IST 2013
900 | CP83 (XRL821) | Wed Oct 03 08:00:00 IST 2012 | Wed Jan 22 17:00:00 IST 2014
901 | CP83 (XRL821) | Sat May 11 08:00:00 IDT 2013 | Wed Jan 22 17:00:00 IST 2014
902 | CP83 Preparation works for Grouting | Wed Oct 03 08:00:00 IST 2012 | Sat Dec 15 17:00:00 IST 2012
903 | CP83 Re-setup for Grouting | Mon Oct 08 08:00:00 IST 2012 | Wed Oct 10 17:00:00 IST 2012
904 | CP83 Fissure Grouting from Tunnel Part I | Thu Oct 11 08:00:00 IST 2012 | Wed Jan 23 17:00:00 IST 2013
905 | CP83 Fissure Grouting from Tunnel Part II | Thu Oct 11 08:00:00 IST 2012 | Sat Oct 27 17:00:00 IST 2012
906 | Probing/Drainage (DT) | Thu Oct 18 08:00:00 IST 2012 | Thu Oct 25 17:00:00 IST 2012
907 | Segment Dismantle (DT) | Thu Oct 18 08:00:00 IST 2012 | Thu Oct 25 17:00:00 IST 2012
908 | Cross Passage Excavation & Temp.Support (from DT) | Fri Oct 19 08:00:00 IST 2012 | Thu Jan 31 17:00:00 IST 2013
909 | Waterproofing (DT) | Mon Mar 18 08:00:00 IST 2013 | Sat Mar 23 17:00:00 IST 2013
910 | Permanent Beam (DT) | Mon Mar 25 08:00:00 IST 2013 | Sat Apr 06 17:00:00 IDT 2013
911 | Probing/Drainage (UT) | Wed Oct 02 08:00:00 IDT 2013 | Fri Nov 22 17:00:00 IST 2013
912 | Segment Dismantle (UT) | Thu Nov 21 08:00:00 IST 2013 | Wed Nov 27 17:00:00 IST 2013
913 | Cross Passage Excavation & Temp.Support (from UT) | Sat Feb 23 08:00:00 IST 2013 | Mon Mar 04 17:00:00 IST 2013
914 | Waterproofing (UT) | Thu Nov 21 08:00:00 IST 2013 | Sat Nov 30 17:00:00 IST 2013
915 | Permanent Beam (UT) | Thu Nov 21 08:00:00 IST 2013 | Sat Nov 30 17:00:00 IST 2013
916 | Permanent Lining | Thu Nov 21 08:00:00 IST 2013 | Wed Nov 27 17:00:00 IST 2013
917 | Permanent Slab | Thu Nov 21 08:00:00 IST 2013 | Wed Nov 27 17:00:00 IST 2013
918 | CP84 (XRL821) | Mon Sep 03 08:00:00 IDT 2012 | Mon Sep 22 17:00:00 IDT 2014
919 | CP84 (XRL821) | Sat Apr 06 08:00:00 IDT 2013 | Wed Jan 08 17:00:00 IST 2014
920 | CP84 Preparation works for Grouting | Mon Sep 03 08:00:00 IDT 2012 | Thu Oct 04 17:00:00 IST 2012
921 | CP84 Fissure Grouting from Tunnel | Tue Sep 11 08:00:00 IDT 2012 | Sat Jan 12 17:00:00 IST 2013
922 | Probing/Drainage (DT) | Tue Sep 11 08:00:00 IDT 2012 | Mon Sep 17 17:00:00 IDT 2012
923 | Segment Dismantle (DT) | Wed Sep 19 08:00:00 IDT 2012 | Wed Sep 26 17:00:00 IST 2012
924 | Cross Passage Excavation & Temp.Support (from DT) | Wed Sep 26 08:00:00 IST 2012 | Sat Dec 29 17:00:00 IST 2012
925 | Waterproofing (DT) | Mon Mar 18 08:00:00 IST 2013 | Wed Mar 27 17:00:00 IST 2013
926 | Permanent Beam (DT) | Mon Mar 25 08:00:00 IST 2013 | Sat Apr 06 17:00:00 IDT 2013
927 | Probing/Drainage (UT) | Mon Aug 26 08:00:00 IDT 2013 | Tue Sep 03 17:00:00 IDT 2013
928 | Segment Dismantle (UT) | Mon Sep 02 08:00:00 IDT 2013 | Sat Sep 07 17:00:00 IDT 2013
929 | Cross Passage Excavation & Temp.Support (from U/T) | Wed Sep 04 08:00:00 IDT 2013 | Fri Sep 13 17:00:00 IDT 2013
930 | Waterproofing (UT) | Thu Sep 11 08:00:00 IDT 2014 | Mon Sep 22 17:00:00 IDT 2014
931 | Permanent Beam (UT) | Sat Sep 14 08:00:00 IDT 2013 | Thu Sep 26 17:00:00 IDT 2013
932 | Permanent Lining | Fri Sep 13 08:00:00 IDT 2013 | Sat Sep 21 17:00:00 IDT 2013
933 | Permanent Slab | Mon Sep 16 08:00:00 IDT 2013 | Tue Sep 24 17:00:00 IDT 2013
934 | CP85 | Tue Feb 01 08:00:00 IST 2011 | Thu Sep 26 17:00:00 IDT 2013
935 | GI works for CP85 | Tue Feb 01 08:00:00 IST 2011 | Tue Feb 15 17:00:00 IST 2011
936 | CP85 Preparation for Grouting works | Fri Jul 27 08:00:00 IDT 2012 | Thu Aug 23 17:00:00 IDT 2012
937 | CP85 Fissure Grouting from Tunnel | Fri Aug 24 08:00:00 IDT 2012 | Mon Jan 14 17:00:00 IST 2013
938 | Probing/Drainage (DT) | Tue Jan 15 08:00:00 IST 2013 | Mon Jan 21 17:00:00 IST 2013
939 | Segment Dismantle (DT) | Tue Jan 22 08:00:00 IST 2013 | Mon Jan 28 17:00:00 IST 2013
940 | Cross Passage Excavation & Temp.Support (from DT) | Fri Aug 31 08:00:00 IDT 2012 | Wed Sep 26 17:00:00 IST 2012
941 | Waterproofing (DT) | Thu Sep 27 08:00:00 IST 2012 | Tue Oct 09 17:00:00 IST 2012
942 | Permanent Beam (DT) | Wed Dec 19 08:00:00 IST 2012 | Wed Jan 02 17:00:00 IST 2013
943 | Probing/Drainage | Mon Jul 15 08:00:00 IDT 2013 | Mon Jul 22 17:00:00 IDT 2013
944 | Segment Dismantle | Tue Jul 23 08:00:00 IDT 2013 | Mon Jul 29 17:00:00 IDT 2013
945 | Cross Passage Excavation & Temp.Support (from UT) | Fri Jul 26 08:00:00 IDT 2013 | Sat Aug 03 17:00:00 IDT 2013
946 | Waterproofing (UT) | Sat Aug 24 08:00:00 IDT 2013 | Thu Sep 05 17:00:00 IDT 2013
947 | Permanent Beam (UT) | Fri Sep 06 08:00:00 IDT 2013 | Tue Sep 17 17:00:00 IDT 2013
948 | Permanent Lining | Wed Sep 18 08:00:00 IDT 2013 | Thu Sep 26 17:00:00 IDT 2013
949 | Permanent Slab | Mon Sep 09 08:00:00 IDT 2013 | Mon Sep 16 17:00:00 IDT 2013
950 | CP85 | Tue Jan 15 08:00:00 IST 2013 | Fri Jun 21 17:00:00 IDT 2013
951 | CP86 | Thu Oct 21 08:00:00 IST 2010 | Thu Oct 03 17:00:00 IDT 2013
952 | GI works for CP86 | Thu Oct 21 08:00:00 IST 2010 | Fri Oct 29 17:00:00 IST 2010
953 | Access Works Area 10.1 for Cross Passages CP86 | Tue Jun 21 08:00:00 IDT 2011 | Tue Jun 21 08:00:00 IDT 2011
954 | TTMS & Site Set up | Wed Aug 31 08:00:00 IDT 2011 | Fri Sep 30 17:00:00 IDT 2011
955 | Install Sleeve Pipes | Mon Jan 16 08:00:00 IST 2012 | Fri Feb 24 17:00:00 IST 2012
956 | CP86 Jet Grouting from Surface for Down Track Tunnel | Mon Jan 16 08:00:00 IST 2012 | Tue May 08 17:00:00 IDT 2012
957 | CP86 TAM Grouting from Surface for Down Track Tunnel | Thu Mar 01 08:00:00 IST 2012 | Mon Apr 30 17:00:00 IDT 2012
958 | Discussion with DSD for Sewage Pumping Station | Thu May 03 08:00:00 IDT 2012 | Tue Jul 31 17:00:00 IDT 2012
959 | CP86 Jet Grouting from Surface for Up Track Tunnel | Wed Aug 01 08:00:00 IDT 2012 | Wed Oct 03 17:00:00 IST 2012
960 | CP86 TAM Grouting from Surface for Up Track Tunnel | Thu Oct 04 08:00:00 IST 2012 | Fri Nov 30 17:00:00 IST 2012
961 | Reinstatement | Mon Sep 02 08:00:00 IDT 2013 | Thu Oct 03 17:00:00 IDT 2013
962 | Probing/Drainage (DT) | Sat Dec 15 08:00:00 IST 2012 | Sat Dec 22 17:00:00 IST 2012
963 | Segment Dismantle (DT) | Mon Dec 24 08:00:00 IST 2012 | Wed Jan 02 17:00:00 IST 2013
964 | Cross Passage Excavation & Temp.Support (from DT) | Sat Dec 15 08:00:00 IST 2012 | Sat Dec 29 17:00:00 IST 2012
965 | Waterproofing (DT) | Mon Dec 31 08:00:00 IST 2012 | Thu Jan 10 17:00:00 IST 2013
966 | Permanent Beam (DT) | Fri Jan 11 08:00:00 IST 2013 | Mon Jan 21 17:00:00 IST 2013
967 | Probing/Drainage (UT) | Sat Jun 08 08:00:00 IDT 2013 | Mon Jun 17 17:00:00 IDT 2013
968 | Segment Dismantle (UT) | Tue Jun 18 08:00:00 IDT 2013 | Tue Jun 25 17:00:00 IDT 2013
969 | Cross Passage Excavation & Temp.Support (from UT) | Wed Jun 26 08:00:00 IDT 2013 | Fri Jul 05 17:00:00 IDT 2013
970 | Waterproofing (UT) | Mon Aug 19 08:00:00 IDT 2013 | Thu Aug 29 17:00:00 IDT 2013
971 | Permanent Beam (UT) | Mon Sep 02 08:00:00 IDT 2013 | Thu Sep 12 17:00:00 IDT 2013
972 | Permanent Lining | Sat Sep 14 08:00:00 IDT 2013 | Mon Sep 23 17:00:00 IDT 2013
973 | Permanent Slab | Fri Sep 13 08:00:00 IDT 2013 | Sat Sep 21 17:00:00 IDT 2013
974 | CP86 Jet Grouting from Surface | Mon Jan 16 08:00:00 IST 2012 | Mon Jan 16 08:00:00 IST 2012
975 | CP86 | Mon Jan 07 08:00:00 IST 2013 | Mon Aug 12 17:00:00 IDT 2013
976 | CP87 | Sun Jun 19 17:00:00 IDT 2011 | Thu Sep 26 17:00:00 IDT 2013
977 | GI works for CP87 | Tue Jun 21 08:00:00 IDT 2011 | Mon Jun 27 17:00:00 IDT 2011
978 | Access Works Area 11.12 for Cross Passages CP87 | Sun Jun 19 17:00:00 IDT 2011 | Sun Jun 19 17:00:00 IDT 2011
979 | TTA Implemetation | Wed Aug 31 08:00:00 IDT 2011 | Thu Nov 24 17:00:00 IST 2011
980 | Install Steeve Pipe (for DT area) | Mon Jan 16 08:00:00 IST 2012 | Tue Feb 21 17:00:00 IST 2012
981 | CP87 Jet Grouting from Surface for Down Track Tunnel | Mon Jan 16 08:00:00 IST 2012 | Tue May 08 17:00:00 IDT 2012
982 | Tam Grouting from Surface for Down Track Tunnel | Thu Feb 16 08:00:00 IST 2012 | Wed Apr 18 17:00:00 IDT 2012
983 | Reinstatement & TTMS | Thu Apr 19 08:00:00 IDT 2012 | Thu May 17 17:00:00 IDT 2012
984 | Install Steeve Pipe (for UT area) | Sat May 19 08:00:00 IDT 2012 | Sat Jun 30 17:00:00 IDT 2012
985 | CP87 Jet Grouting from Surface for Up Track Tunnel | Tue Jul 03 08:00:00 IDT 2012 | Fri Aug 31 17:00:00 IDT 2012
986 | Tam Grouting from Surface for Up Track Tunnel | Sat Sep 01 08:00:00 IDT 2012 | Wed Oct 03 17:00:00 IST 2012
987 | Probing/Drainage (DT) | Fri Aug 31 08:00:00 IDT 2012 | Thu Sep 06 17:00:00 IDT 2012
988 | Segment Dismantle (DT) | Fri Sep 07 08:00:00 IDT 2012 | Fri Sep 14 17:00:00 IDT 2012
989 | Cross Passage Excavation & Temp.Support (from DT) | Sat Sep 15 08:00:00 IDT 2012 | Wed Sep 19 17:00:00 IDT 2012
990 | Waterproofing (DT) | Fri Sep 21 08:00:00 IDT 2012 | Wed Oct 03 17:00:00 IST 2012
991 | Permanent Beam (DT) | Thu Oct 04 08:00:00 IST 2012 | Sat Oct 13 17:00:00 IST 2012
992 | Probing/Drainage (UT) | Sat May 25 08:00:00 IDT 2013 | Fri May 31 17:00:00 IDT 2013
993 | Segment Dismantle (UT) | Sat Jun 01 08:00:00 IDT 2013 | Fri Jun 07 17:00:00 IDT 2013
994 | Cross Passage Excavation & Temp.Support (from UT) | Sat Jun 08 08:00:00 IDT 2013 | Wed Jun 19 17:00:00 IDT 2013
995 | Waterproofing (UT) | Fri Jun 21 08:00:00 IDT 2013 | Tue Jul 02 17:00:00 IDT 2013
996 | Permanent Beam (UT) | Wed Jul 03 08:00:00 IDT 2013 | Sat Jul 13 17:00:00 IDT 2013
997 | Permanent Lining | Mon Jul 15 08:00:00 IDT 2013 | Mon Jul 22 17:00:00 IDT 2013
998 | Permanent Slab | Tue Jul 23 08:00:00 IDT 2013 | Mon Jul 29 17:00:00 IDT 2013
999 | CP87 | Fri Aug 31 08:00:00 IDT 2012 | Thu Sep 26 17:00:00 IDT 2013
1000 | CP88 | Tue Feb 01 08:00:00 IST 2011 | Wed Sep 11 17:00:00 IDT 2013
1001 | GI works for CP88 | Tue Feb 01 08:00:00 IST 2011 | Mon Feb 07 17:00:00 IST 2011
1002 | Access Works Area 11.21 for Cross Passages CP88 | Wed Aug 31 08:00:00 IDT 2011 | Wed Aug 31 08:00:00 IDT 2011
1003 | Site Set up & Preparation | Tue Jun 21 08:00:00 IDT 2011 | Tue Aug 02 17:00:00 IDT 2011
1004 | CP88 Jet Grouting from Surface | Tue Aug 09 08:00:00 IDT 2011 | Sat Aug 20 17:00:00 IDT 2011
1005 | Suspension of Grouting Works | Sun Jun 19 08:00:00 IDT 2011 | Sun Jun 19 08:00:00 IDT 2011
1006 | Suspension Period for CP88 Jet Grouting Works | Sun Jun 19 08:00:00 IDT 2011 | Wed Jun 22 17:00:00 IDT 2011
1007 | Suspension Lifting | Tue Jun 21 08:00:00 IDT 2011 | Tue Jun 21 08:00:00 IDT 2011
1008 | Re-mobilization | Thu Aug 18 08:00:00 IDT 2011 | Sat Aug 20 17:00:00 IDT 2011
1009 | CP88 Jet Grouting from Surface (Remaining) | Thu Aug 18 08:00:00 IDT 2011 | Mon Dec 19 17:00:00 IST 2011
1010 | Probing/Drainage (DT) | Fri Aug 31 08:00:00 IDT 2012 | Thu Sep 06 17:00:00 IDT 2012
1011 | Segment Dismantle (DT) | Fri Sep 07 08:00:00 IDT 2012 | Fri Sep 14 17:00:00 IDT 2012
1012 | Cross Passage Excavation & Temp.Support (from DT) | Sat Sep 15 08:00:00 IDT 2012 | Mon Sep 17 17:00:00 IDT 2012
1013 | Waterproofing (DT) | Tue Sep 18 08:00:00 IDT 2012 | Fri Sep 28 17:00:00 IST 2012
1014 | Permanent Beam (DT) | Sat Sep 29 08:00:00 IST 2012 | Thu Oct 11 17:00:00 IST 2012
1015 | Probing/Drainage (UT) | Thu May 23 08:00:00 IDT 2013 | Wed May 29 17:00:00 IDT 2013
1016 | Segment Dismantle (UT) | Thu May 30 08:00:00 IDT 2013 | Wed Jun 05 17:00:00 IDT 2013
1017 | Cross Passage Excavation & Temp.Support (from UT) | Thu Jun 06 08:00:00 IDT 2013 | Mon Jun 17 17:00:00 IDT 2013
1018 | Waterproofing (UT) | Tue Jun 18 08:00:00 IDT 2013 | Fri Jun 28 17:00:00 IDT 2013
1019 | Permanent Beam (UT) | Sat Jun 29 08:00:00 IDT 2013 | Thu Jul 11 17:00:00 IDT 2013
1020 | Permanent Lining | Fri Jul 12 08:00:00 IDT 2013 | Thu Jul 18 17:00:00 IDT 2013
1021 | Permanent Slab | Sat Jul 20 08:00:00 IDT 2013 | Fri Jul 26 17:00:00 IDT 2013
1022 | CP88 | Fri Aug 31 08:00:00 IDT 2012 | Wed Sep 11 17:00:00 IDT 2013
1023 | CP89 | Tue Feb 01 08:00:00 IST 2011 | Tue Feb 18 17:00:00 IST 2014
1024 | GI works for CP89 | Tue Feb 01 08:00:00 IST 2011 | Sat Feb 12 17:00:00 IST 2011
1025 | Access Works Area 11.27 for Cross Passages CP89 | Sat May 28 17:00:00 IDT 2011 | Sat May 28 17:00:00 IDT 2011
1026 | Setup & Install Sleeve pipes | Wed Aug 31 08:00:00 IDT 2011 | Fri Sep 30 17:00:00 IDT 2011
1027 | Jet Grouting from Surface (DT) | Wed Aug 31 08:00:00 IDT 2011 | Tue Mar 13 17:00:00 IST 2012
1028 | Jet Grouting from Surface (UT) | Thu Mar 15 08:00:00 IST 2012 | Mon Apr 30 17:00:00 IDT 2012
1029 | Probing/Drainage (DT) | Fri Aug 31 08:00:00 IDT 2012 | Thu Sep 06 17:00:00 IDT 2012
1030 | Tunnel Frame Support | Fri Sep 07 08:00:00 IDT 2012 | Fri Sep 14 17:00:00 IDT 2012
1031 | Segment Dismantle (DT) | Sat Sep 15 08:00:00 IDT 2012 | Sat Sep 22 17:00:00 IDT 2012
1032 | Cross Passage Excavation & Temp.Support (from DT) | Mon Sep 24 08:00:00 IST 2012 | Tue Sep 25 17:00:00 IST 2012
1033 | Waterproofing (DT) | Wed Sep 26 08:00:00 IST 2012 | Mon Oct 08 17:00:00 IST 2012
1034 | Permanent Beam (DT) | Tue Oct 09 08:00:00 IST 2012 | Thu Oct 18 17:00:00 IST 2012
1035 | Probing/Drainage (from DT) | Tue Jan 07 08:00:00 IST 2014 | Mon Jan 13 17:00:00 IST 2014
1036 | Cross Passage Excavation & Temp.Support (from DT) | Sat Jan 11 08:00:00 IST 2014 | Mon Jan 20 17:00:00 IST 2014
1037 | Segment Dismantle (UT) | Wed Jan 08 08:00:00 IST 2014 | Tue Jan 14 17:00:00 IST 2014
1038 | Waterproofing (UT) | Tue Feb 04 08:00:00 IST 2014 | Thu Feb 13 17:00:00 IST 2014
1039 | Permanent Beam (UT) | Sat Feb 08 08:00:00 IST 2014 | Tue Feb 18 17:00:00 IST 2014
1040 | Permanent Lining | Tue Feb 11 08:00:00 IST 2014 | Mon Feb 17 17:00:00 IST 2014
1041 | Permanent Slab | Fri Feb 07 08:00:00 IST 2014 | Thu Feb 13 17:00:00 IST 2014
1042 | CP89 | Fri Sep 07 08:00:00 IDT 2012 | Sat Oct 26 17:00:00 IDT 2013
1043 | CP90 | Tue Feb 01 08:00:00 IST 2011 | Thu May 08 17:00:00 IDT 2014
1044 | GI works for CP90 | Tue Feb 01 08:00:00 IST 2011 | Wed Feb 09 17:00:00 IST 2011
1045 | Access Works Area 11.21 for Cross Passages CP90 | Sun Jun 19 17:00:00 IDT 2011 | Sun Jun 19 17:00:00 IDT 2011
1046 | TTA Implementation | Mon Jan 16 08:00:00 IST 2012 | Wed Feb 15 17:00:00 IST 2012
1047 | Installl Sleeve Pipes | Mon Jan 16 08:00:00 IST 2012 | Thu Feb 16 17:00:00 IST 2012
1048 | CP90 Jet Grouting from Surface (DT) | Mon Jan 16 08:00:00 IST 2012 | Fri Jun 15 17:00:00 IDT 2012
1049 | CP90 Jet Grouting from Surface (UT) | Wed May 02 08:00:00 IDT 2012 | Sat Sep 01 17:00:00 IDT 2012
1050 | Probing/Drainage (DT) | Fri Aug 31 08:00:00 IDT 2012 | Thu Sep 06 17:00:00 IDT 2012
1051 | Segment Dismantle (DT) | Fri Sep 07 08:00:00 IDT 2012 | Fri Sep 14 17:00:00 IDT 2012
1052 | Cross Passage Excavation & Temp.Support (from DT) | Sat Sep 15 08:00:00 IDT 2012 | Sat Sep 22 17:00:00 IDT 2012
1053 | Waterproofing (DT) | Mon Sep 24 08:00:00 IST 2012 | Fri Oct 05 17:00:00 IST 2012
1054 | Permanent Beam (DT) | Sat Oct 06 08:00:00 IST 2012 | Tue Oct 16 17:00:00 IST 2012
1055 | Probing/Drainage (UT) | Wed Apr 09 08:00:00 IDT 2014 | Wed Apr 16 17:00:00 IDT 2014
1056 | Cross Passage Excavation & Temp.Support (UT) | Sat Apr 12 08:00:00 IDT 2014 | Thu Apr 24 17:00:00 IDT 2014
1057 | Segment Dismantle (UT) | Fri Apr 11 08:00:00 IDT 2014 | Sat Apr 19 17:00:00 IDT 2014
1058 | Waterproofing (UT) | Tue Apr 22 08:00:00 IDT 2014 | Wed Apr 30 17:00:00 IDT 2014
1059 | Permanent Beam (UT) | Mon Apr 28 08:00:00 IDT 2014 | Thu May 08 17:00:00 IDT 2014
1060 | Permanent Lining | Wed Apr 30 08:00:00 IDT 2014 | Thu May 08 17:00:00 IDT 2014
1061 | Permanent Slab | Thu Apr 24 08:00:00 IDT 2014 | Wed Apr 30 17:00:00 IDT 2014
1062 | CP90 | Fri Aug 31 08:00:00 IDT 2012 | Sat Dec 28 17:00:00 IST 2013
1063 | CP91 | Tue Feb 01 08:00:00 IST 2011 | Thu May 22 17:00:00 IDT 2014
1064 | GI works for CP91 | Tue Feb 01 08:00:00 IST 2011 | Sat Feb 12 17:00:00 IST 2011
1065 | Access Works Area 11.21 for Cross Passages CP91 | Sun Jun 19 17:00:00 IDT 2011 | Sun Jun 19 17:00:00 IDT 2011
1066 | TTMS & Site Set up | Wed Aug 31 08:00:00 IDT 2011 | Mon Oct 17 17:00:00 IST 2011
1067 | Install Sleeve Pipes (DT) | Mon Jan 16 08:00:00 IST 2012 | Wed Feb 01 17:00:00 IST 2012
1068 | Jet Grouting from Surface for Down Track Tunnel | Mon Jan 16 08:00:00 IST 2012 | Tue Jun 05 17:00:00 IDT 2012
1069 | TTMS Rearrangement | Mon Apr 16 08:00:00 IDT 2012 | Mon May 14 17:00:00 IDT 2012
1070 | Install Sleeve Pipes (UT) | Tue May 15 08:00:00 IDT 2012 | Wed Jun 13 17:00:00 IDT 2012
1071 | Jet Grouting from Surface for Up Track Tunnel | Thu Jun 14 08:00:00 IDT 2012 | Fri Sep 14 17:00:00 IDT 2012
1072 | Probing/Drainage (DT) | Wed Oct 31 08:00:00 IST 2012 | Tue Nov 06 17:00:00 IST 2012
1073 | Tunnel Frame Support | Fri Nov 30 08:00:00 IST 2012 | Thu Dec 06 17:00:00 IST 2012
1074 | Segment Dismantle (DT) | Fri Dec 07 08:00:00 IST 2012 | Thu Dec 13 17:00:00 IST 2012
1075 | Cross Passage Excavation & Temp.Support (from DT) | Fri Dec 14 08:00:00 IST 2012 | Thu Dec 27 17:00:00 IST 2012
1076 | Waterproofing (DT) | Sat Dec 15 08:00:00 IST 2012 | Fri Dec 28 17:00:00 IST 2012
1077 | Permanent Beam (DT) | Fri Feb 01 08:00:00 IST 2013 | Sat Feb 16 17:00:00 IST 2013
1078 | Probing/Drainage (from DT) | Fri Apr 25 08:00:00 IDT 2014 | Fri May 02 17:00:00 IDT 2014
1079 | Segment Dismantle (UT) | Fri Apr 25 08:00:00 IDT 2014 | Fri May 02 17:00:00 IDT 2014
1080 | Waterproofing (UT) | Mon May 05 08:00:00 IDT 2014 | Fri May 16 17:00:00 IDT 2014
1081 | Permanent Beam (UT) | Mon May 12 08:00:00 IDT 2014 | Thu May 22 17:00:00 IDT 2014
1082 | Permanent Lining | Wed May 14 08:00:00 IDT 2014 | Wed May 21 17:00:00 IDT 2014
1083 | Permanent Slab | Thu May 08 08:00:00 IDT 2014 | Thu May 15 17:00:00 IDT 2014
1084 | CP91 Grouting from Surface | Mon Jan 16 08:00:00 IST 2012 | Wed Aug 01 17:00:00 IDT 2012
1085 | CP91 | Wed Oct 31 08:00:00 IST 2012 | Thu Oct 17 17:00:00 IDT 2013
1086 | CP92 | Sun Jun 19 17:00:00 IDT 2011 | Sat Jun 07 17:00:00 IDT 2014
1087 | GI works for CP92 | Tue Jun 21 08:00:00 IDT 2011 | Mon Jun 27 17:00:00 IDT 2011
1088 | Access Works Area 11.21 for Cross Passages CP92 | Sun Jun 19 17:00:00 IDT 2011 | Sun Jun 19 17:00:00 IDT 2011
1089 | TTMS & Site Set up | Tue Jun 21 08:00:00 IDT 2011 | Wed Aug 17 17:00:00 IDT 2011
1090 | Install Sleeve Pipes | Mon Jan 16 08:00:00 IST 2012 | Wed Feb 01 17:00:00 IST 2012
1091 | Jet Grouting from Surface for Up Track Tunnel | Mon Jan 16 08:00:00 IST 2012 | Tue Mar 27 17:00:00 IST 2012
1092 | TTMS Rearrangement | Mon Jan 16 08:00:00 IST 2012 | Thu Feb 16 17:00:00 IST 2012
1093 | Insall Sleeve Pipes | Sat Feb 04 08:00:00 IST 2012 | Fri Feb 17 17:00:00 IST 2012
1094 | Jet Grouting from Surface for Down Track Tunnel | Sat Feb 18 08:00:00 IST 2012 | Fri Jun 15 17:00:00 IDT 2012
1095 | Road Reinstatment | Sat Jun 16 08:00:00 IDT 2012 | Wed Jul 18 17:00:00 IDT 2012
1096 | Probing/Drainage (DT) | Wed Oct 31 08:00:00 IST 2012 | Tue Nov 06 17:00:00 IST 2012
1097 | Segment Dismantle (DT) | Wed Nov 07 08:00:00 IST 2012 | Tue Nov 13 17:00:00 IST 2012
1098 | Cross Passage Excavation & Temp.Support (from DT) | Fri Nov 30 08:00:00 IST 2012 | Thu Dec 06 17:00:00 IST 2012
1099 | Waterproofing (DT) | Sat Dec 15 08:00:00 IST 2012 | Fri Dec 28 17:00:00 IST 2012
1100 | Permanent Beam (DT) | Sat Dec 15 08:00:00 IST 2012 | Fri Dec 28 17:00:00 IST 2012
1101 | Probing/Drainage (from DT) | Sat May 10 08:00:00 IDT 2014 | Fri May 16 17:00:00 IDT 2014
1102 | Cross Passage Excavation & Temp.Support (from DT) | Mon May 12 08:00:00 IDT 2014 | Wed May 21 17:00:00 IDT 2014
1103 | Segment Dismantle (UT) | Sat May 10 08:00:00 IDT 2014 | Thu May 15 17:00:00 IDT 2014
1104 | Waterproofing (UT) | Wed May 21 08:00:00 IDT 2014 | Thu May 29 17:00:00 IDT 2014
1105 | Permanent Beam (UT) | Thu May 29 08:00:00 IDT 2014 | Sat Jun 07 17:00:00 IDT 2014
1106 | Permanent Lining | Sat May 31 08:00:00 IDT 2014 | Sat Jun 07 17:00:00 IDT 2014
1107 | Permanent Slab | Mon May 26 08:00:00 IDT 2014 | Sat May 31 17:00:00 IDT 2014
1108 | CP92 | Wed Oct 31 08:00:00 IST 2012 | Mon Nov 04 17:00:00 IST 2013
1109 | CP93 | Tue Feb 01 08:00:00 IST 2011 | Sat Jun 21 17:00:00 IDT 2014
1110 | GI works for CP93 | Tue Feb 01 08:00:00 IST 2011 | Thu Feb 10 17:00:00 IST 2011
1111 | Access Works Area 11.15 for Cross Passages CP93 | Wed Aug 31 08:00:00 IDT 2011 | Wed Aug 31 08:00:00 IDT 2011
1112 | TTMS & Site Set up | Wed Feb 01 08:00:00 IST 2012 | Fri Mar 02 17:00:00 IST 2012
1113 | Install Sleeve Pipes | Mon Jan 16 08:00:00 IST 2012 | Mon Feb 13 17:00:00 IST 2012
1114 | Jet Grouting from Surface | Mon Jan 16 08:00:00 IST 2012 | Thu Jul 12 17:00:00 IDT 2012
1115 | Probing/Drainage (DT) | Tue Nov 27 08:00:00 IST 2012 | Mon Dec 03 17:00:00 IST 2012
1116 | Segment Dismantle (DT) | Tue Dec 04 08:00:00 IST 2012 | Mon Dec 10 17:00:00 IST 2012
1117 | Cross Passage Excavation & Temp.Support (from DT) | Tue Dec 11 08:00:00 IST 2012 | Tue Dec 18 17:00:00 IST 2012
1118 | Waterproofing (DT) | Sat Dec 15 08:00:00 IST 2012 | Fri Dec 28 17:00:00 IST 2012
1119 | Permanent Beam (DT) | Sat Dec 29 08:00:00 IST 2012 | Wed Jan 09 17:00:00 IST 2013
1120 | Probing/Drainage (from UT) | Wed May 21 08:00:00 IDT 2014 | Tue May 27 17:00:00 IDT 2014
1121 | Cross Passage Excavation & Temp.Support (from DT) | Sat May 24 08:00:00 IDT 2014 | Tue Jun 03 17:00:00 IDT 2014
1122 | Segment Dismantle (UT) | Fri May 23 08:00:00 IDT 2014 | Wed May 28 17:00:00 IDT 2014
1123 | Waterproofing (UT) | Sat May 31 08:00:00 IDT 2014 | Mon Jun 09 17:00:00 IDT 2014
1124 | Permanent Beam (UT) | Thu Jun 12 08:00:00 IDT 2014 | Sat Jun 21 17:00:00 IDT 2014
1125 | Permanent Lining | Sat Jun 14 08:00:00 IDT 2014 | Thu Jun 19 17:00:00 IDT 2014
1126 | Permanent Slab | Mon Jun 09 08:00:00 IDT 2014 | Sat Jun 14 17:00:00 IDT 2014
1127 | CP93 | Tue Nov 27 08:00:00 IST 2012 | Mon Nov 18 17:00:00 IST 2013
1128 | CP94 | Tue Feb 01 08:00:00 IST 2011 | Sat Aug 09 17:00:00 IDT 2014
1129 | GI works for CP94 | Tue Feb 01 08:00:00 IST 2011 | Thu Feb 17 17:00:00 IST 2011
1130 | Access for Cross Passages CP94 | Mon Sep 03 17:00:00 IDT 2012 | Mon Sep 03 17:00:00 IDT 2012
1131 | Preparation for Grouting | Wed Oct 03 08:00:00 IST 2012 | Wed Oct 31 17:00:00 IST 2012
1132 | CP94 Fissure Grouting from Tunnel | Thu Nov 01 08:00:00 IST 2012 | Mon Dec 31 17:00:00 IST 2012
1133 | Probing/Drainage (DT) | Mon Dec 02 08:00:00 IST 2013 | Mon Dec 30 17:00:00 IST 2013
1134 | Segment Dismantle (DT) | Tue Dec 04 08:00:00 IST 2012 | Mon Dec 10 17:00:00 IST 2012
1135 | Cross Passage Excavation/ Temp.Support (from DT) | Tue Dec 11 08:00:00 IST 2012 | Tue Dec 18 17:00:00 IST 2012
1136 | Waterproofing (DT) | Tue Jul 02 08:00:00 IDT 2013 | Fri Jul 12 17:00:00 IDT 2013
1137 | Permanent Beam (DT) | Sat Jul 13 08:00:00 IDT 2013 | Wed Jul 24 17:00:00 IDT 2013
1138 | Probing/Drainage (from DT) | Mon Jul 14 08:00:00 IDT 2014 | Mon Jul 21 17:00:00 IDT 2014
1139 | Cross Passage Excavation /Temp.Support (from DT) | Sat Jul 19 08:00:00 IDT 2014 | Mon Jul 28 17:00:00 IDT 2014
1140 | Segment Dismantle (UT) | Mon Jul 14 08:00:00 IDT 2014 | Sat Jul 19 17:00:00 IDT 2014
1141 | Waterproofing (UT) | Fri Jul 25 08:00:00 IDT 2014 | Sat Aug 02 17:00:00 IDT 2014
1142 | Permanent Beam (UT) | Thu Jul 31 08:00:00 IDT 2014 | Sat Aug 09 17:00:00 IDT 2014
1143 | Permanent Lining | Sat Aug 02 08:00:00 IDT 2014 | Thu Aug 07 17:00:00 IDT 2014
1144 | Permanent Slab | Wed Jul 30 08:00:00 IDT 2014 | Mon Aug 04 17:00:00 IDT 2014
1145 | CP94 | Mon Dec 31 08:00:00 IST 2012 | Mon Dec 31 08:00:00 IST 2012
1146 | CP95 & Pump Sump | Tue Feb 01 08:00:00 IST 2011 | Mon Sep 08 17:00:00 IDT 2014
1147 | GI works for CP95 & Sump | Tue Feb 01 08:00:00 IST 2011 | Thu Feb 17 17:00:00 IST 2011
1148 | Preparation for Grouting | Sat Nov 24 08:00:00 IST 2012 | Mon Dec 24 17:00:00 IST 2012
1149 | CP95 Fissure Grouting from Tunnel | Sat Dec 08 08:00:00 IST 2012 | Mon May 27 17:00:00 IDT 2013
1150 | Probing/Drainage (DT) | Mon Dec 24 08:00:00 IST 2012 | Wed Jan 02 17:00:00 IST 2013
1151 | Segment Dismantle (DT) | Mon Dec 31 08:00:00 IST 2012 | Thu Feb 14 17:00:00 IST 2013
1152 | Cross Passage & Sump pit Excavation/ Temp.Support (from DT) | Thu Feb 14 08:00:00 IST 2013 | Thu Feb 21 17:00:00 IST 2013
1153 | Waterproofing (DT) | Mon Sep 02 08:00:00 IDT 2013 | Thu Sep 12 17:00:00 IDT 2013
1154 | Permanent Beam (DT) | Fri Sep 13 08:00:00 IDT 2013 | Wed Sep 25 17:00:00 IDT 2013
1155 | Cross Passage Excavation/Temp.Support U/T (from DT) | Mon Aug 18 08:00:00 IDT 2014 | Wed Aug 27 17:00:00 IDT 2014
1156 | Segment Dismantle (UT) | Tue Aug 12 08:00:00 IDT 2014 | Mon Aug 18 17:00:00 IDT 2014
1157 | Waterproofing (UT) | Tue Aug 26 08:00:00 IDT 2014 | Wed Sep 03 17:00:00 IDT 2014
1158 | Sump pit Concreting | Thu Sep 05 08:00:00 IDT 2013 | Fri Oct 04 17:00:00 IDT 2013
1159 | Permanet Beam, Lining& Slab (UT) | Thu Aug 28 08:00:00 IDT 2014 | Mon Sep 08 17:00:00 IDT 2014
1160 | CP96 | Tue Feb 01 08:00:00 IST 2011 | Tue Sep 30 17:00:00 IDT 2014
1161 | Segment Dismantle (DT) | Tue May 14 08:00:00 IDT 2013 | Wed May 22 17:00:00 IDT 2013
1162 | Cross Passage Excavation & Temp.Support (DT) | Tue May 21 08:00:00 IDT 2013 | Mon May 27 17:00:00 IDT 2013
1163 | Waterproofing (DT) | Tue Sep 24 08:00:00 IDT 2013 | Wed Oct 02 17:00:00 IDT 2013
1164 | Permanent Beam (DT) | Fri Sep 27 08:00:00 IDT 2013 | Mon Oct 07 17:00:00 IDT 2013
1165 | Permanent Lining (DT) | Fri Sep 27 08:00:00 IDT 2013 | Thu Oct 03 17:00:00 IDT 2013
1166 | Permanent Slab (DT) | Thu Sep 26 08:00:00 IDT 2013 | Wed Oct 02 17:00:00 IDT 2013
1167 | GI works for CP96 | Tue Feb 01 08:00:00 IST 2011 | Tue Feb 15 17:00:00 IST 2011
1168 | Preparation works for Grouting | Mon Feb 18 08:00:00 IST 2013 | Tue Mar 19 17:00:00 IST 2013
1169 | CP96 Fissure Grouting from Tunnel | Fri Mar 01 08:00:00 IST 2013 | Fri Jun 07 17:00:00 IDT 2013
1170 | Probing/Drainage (from UT) | Wed Sep 03 08:00:00 IDT 2014 | Thu Sep 11 17:00:00 IDT 2014
1171 | Segment Dismantle (UT) | Thu Sep 04 08:00:00 IDT 2014 | Fri Sep 12 17:00:00 IDT 2014
1172 | Cross Passage Excavation & Temp.Support (from UT) | Thu Sep 11 08:00:00 IDT 2014 | Wed Sep 17 17:00:00 IDT 2014
1173 | Waterproofing | Wed Sep 17 08:00:00 IDT 2014 | Thu Sep 25 17:00:00 IDT 2014
1174 | Permanent Beam | Mon Sep 22 08:00:00 IDT 2014 | Tue Sep 30 17:00:00 IDT 2014
1175 | Permanent Lining | Wed Sep 24 08:00:00 IDT 2014 | Mon Sep 29 17:00:00 IDT 2014
1176 | Permanent Slab | Sat Sep 20 08:00:00 IDT 2014 | Thu Sep 25 17:00:00 IDT 2014
1177 | Probing/Drainage (DT) | Sat May 11 08:00:00 IDT 2013 | Sat May 18 17:00:00 IDT 2013
1178 | CP97 | Tue Feb 01 08:00:00 IST 2011 | Thu Dec 18 17:00:00 IST 2014
1179 | CP97 Jet Grouting from Surface | Mon Jan 16 08:00:00 IST 2012 | Wed Oct 31 17:00:00 IST 2012
1180 | GI works for CP97 | Tue Feb 01 08:00:00 IST 2011 | Thu Feb 10 17:00:00 IST 2011
1181 | Access Works Area 12.1 for Cross Passages CP97 | Sun Jan 15 08:00:00 IST 2012 | Sun Jan 15 08:00:00 IST 2012
1182 | TTMS (Stage 1) | Mon Jan 16 08:00:00 IST 2012 | Wed Feb 15 17:00:00 IST 2012
1183 | Install Sleeve Pipes | Mon Jan 16 08:00:00 IST 2012 | Wed Feb 15 17:00:00 IST 2012
1184 | Jet Grouting from Surface for Down Track Tunnel | Thu Feb 16 08:00:00 IST 2012 | Thu May 31 17:00:00 IDT 2012
1185 | TTMS (Stage 2) Reinstate TTMS for Stage 4 | Fri Jun 01 08:00:00 IDT 2012 | Tue Jul 17 17:00:00 IDT 2012
1186 | Install Sleeve Pipes | Fri Jun 01 08:00:00 IDT 2012 | Thu Jun 14 17:00:00 IDT 2012
1187 | Jet Grouting from Surface for Up Track Tunnel | Sat Sep 21 08:00:00 IDT 2013 | Mon Dec 16 17:00:00 IST 2013
1188 | Probing/Drainage (UT) (after TBM removal) | Mon Nov 17 08:00:00 IST 2014 | Wed Nov 19 17:00:00 IST 2014
1189 | Segment Dismantle (UT) | Wed Nov 19 08:00:00 IST 2014 | Fri Nov 21 17:00:00 IST 2014
1190 | Cross Passage Excavation & Temp.Support (from UT) | Thu Nov 20 08:00:00 IST 2014 | Tue Nov 25 17:00:00 IST 2014
1191 | Waterproofing | Tue Dec 02 08:00:00 IST 2014 | Thu Dec 04 17:00:00 IST 2014
1192 | Permanent Beam | Thu Dec 11 08:00:00 IST 2014 | Sat Dec 13 17:00:00 IST 2014
1193 | Permanent Lining | Tue Dec 16 08:00:00 IST 2014 | Thu Dec 18 17:00:00 IST 2014
1194 | Permanent Slab | Mon Dec 08 08:00:00 IST 2014 | Wed Dec 10 17:00:00 IST 2014
1195 | Additional Jet Grout of CP97 U/T | Tue Jan 21 08:00:00 IST 2014 | Fri Aug 01 17:00:00 IDT 2014
1196 | Mobilization | Tue Jan 21 08:00:00 IST 2014 | Tue Jan 21 17:00:00 IST 2014
1197 | Steel Sleeve pipe installation | Tue Jan 21 08:00:00 IST 2014 | Thu Feb 06 17:00:00 IST 2014
1198 | Mobilization of Pre-drilling rig and mixing plant | Fri Feb 07 08:00:00 IST 2014 | Mon Feb 10 17:00:00 IST 2014
1199 | Pre-drilling (2 Rigs) | Tue Feb 11 08:00:00 IST 2014 | Wed Apr 30 17:00:00 IDT 2014
1200 | Trial pit for re-location of air release hole P2 | Mon May 12 08:00:00 IDT 2014 | Mon May 12 17:00:00 IDT 2014
1201 | Pre-drilling for air release hole P2 | Tue May 13 08:00:00 IDT 2014 | Wed May 14 17:00:00 IDT 2014
1202 | Demobilization of Pre-drilling plant | Thu May 15 08:00:00 IDT 2014 | Fri May 16 17:00:00 IDT 2014
1203 | Mobilization and Set up of Jet grouting plant | Sat May 17 08:00:00 IDT 2014 | Sat May 24 17:00:00 IDT 2014
1204 | Jet grouting (56 columns) | Wed May 21 08:00:00 IDT 2014 | Tue Jul 08 17:00:00 IDT 2014
1205 | Demobilization of Jet grout plant | Tue Jun 24 08:00:00 IDT 2014 | Mon Jun 30 17:00:00 IDT 2014
1206 | Mobilization and drilling rig for Proof Coring | Thu Jul 31 08:00:00 IDT 2014 | Fri Aug 01 17:00:00 IDT 2014
1207 | Proof Coring | Mon Jul 07 08:00:00 IDT 2014 | Mon Jul 14 17:00:00 IDT 2014
1208 | Demobilization of drilling rig | Mon Jul 28 08:00:00 IDT 2014 | Tue Jul 29 17:00:00 IDT 2014
1209 | CP98 | Tue Feb 01 08:00:00 IST 2011 | Fri Dec 19 17:00:00 IST 2014
1210 | Probing/Drainage (DT) | Sat May 11 08:00:00 IDT 2013 | Sat May 18 17:00:00 IDT 2013
1211 | Segment Dismantle (DT) | Tue May 14 08:00:00 IDT 2013 | Wed May 22 17:00:00 IDT 2013
1212 | Cross Passage Excavation & Temp.Support (DT) | Tue May 21 08:00:00 IDT 2013 | Mon May 27 17:00:00 IDT 2013
1213 | Waterproofing (DT) | Tue Sep 24 08:00:00 IDT 2013 | Wed Oct 02 17:00:00 IDT 2013
1214 | Permanent Slab (DT) | Thu Sep 26 08:00:00 IDT 2013 | Wed Oct 02 17:00:00 IDT 2013
1215 | Permanent Beam (DT) | Fri Sep 27 08:00:00 IDT 2013 | Mon Oct 07 17:00:00 IDT 2013
1216 | Permanent Lining (DT) | Fri Sep 27 08:00:00 IDT 2013 | Thu Oct 03 17:00:00 IDT 2013
1217 | GI works for CP98 | Tue Feb 01 08:00:00 IST 2011 | Mon Feb 14 17:00:00 IST 2011
1218 | Access Works Area 12.1 for Cross Passages CP98 | Sun Jan 15 08:00:00 IST 2012 | Sun Jan 15 08:00:00 IST 2012
1219 | TTA Implementation & Site Setup | Mon Jan 16 08:00:00 IST 2012 | Sat Mar 10 17:00:00 IST 2012
1220 | Install Sleeve Pipe | Wed Oct 03 08:00:00 IST 2012 | Wed Oct 31 17:00:00 IST 2012
1221 | CP98 Jet Grouting from Surface | Thu Nov 01 08:00:00 IST 2012 | Wed Feb 27 17:00:00 IST 2013
1222 | Road Reinstatement | Mon Dec 17 08:00:00 IST 2012 | Fri Jan 25 17:00:00 IST 2013
1223 | Probing/Drainage (UT) (after TBM removal) | Thu Nov 20 08:00:00 IST 2014 | Sat Nov 22 17:00:00 IST 2014
1224 | Segment Dismantle (UT) | Sat Nov 22 08:00:00 IST 2014 | Tue Nov 25 17:00:00 IST 2014
1225 | Cross Passage Excavation & Temp.Support (from UT) | Sat Nov 29 08:00:00 IST 2014 | Thu Dec 04 17:00:00 IST 2014
1226 | Segment Dismantle (DT) | Sat Nov 22 08:00:00 IST 2014 | Tue Nov 25 17:00:00 IST 2014
1227 | Waterproofing | Tue Dec 02 08:00:00 IST 2014 | Thu Dec 04 17:00:00 IST 2014
1228 | Permanent Beam | Mon Dec 15 08:00:00 IST 2014 | Wed Dec 17 17:00:00 IST 2014
1229 | Permanent Lining | Wed Dec 17 08:00:00 IST 2014 | Fri Dec 19 17:00:00 IST 2014
1230 | Permanent Slab | Wed Dec 10 08:00:00 IST 2014 | Fri Dec 12 17:00:00 IST 2014
1231 | Tunnel Lining Design/Submission/Approval | Mon Jan 31 08:00:00 IST 2011 | Wed Nov 30 17:00:00 IST 2011
1232 | Design | Mon Jan 31 08:00:00 IST 2011 | Wed Nov 30 17:00:00 IST 2011
1233 | AIP Submission Preparation - Tunnel Lining | Mon Jan 31 08:00:00 IST 2011 | Mon Feb 21 17:00:00 IST 2011
1234 | AIP Submission to MTR | Mon Feb 21 17:00:00 IST 2011 | Mon Feb 21 17:00:00 IST 2011
1235 | AIP Comment by MTR | Tue Feb 22 08:00:00 IST 2011 | Sun Mar 06 17:00:00 IST 2011
1236 | AIP ReSubmission Preparation - Tunnel Lining | Sat Mar 19 08:00:00 IST 2011 | Thu Mar 31 17:00:00 IST 2011
1237 | AIP ReSubmission to MTR | Mon Apr 04 17:00:00 IDT 2011 | Mon Apr 04 17:00:00 IDT 2011
1238 | AIP Approval by MTR | Tue Apr 05 08:00:00 IDT 2011 | Fri Apr 29 17:00:00 IDT 2011
1239 | DD Submission Preparation - Tunnel Lining | Tue Apr 26 08:00:00 IDT 2011 | Sat Jun 04 17:00:00 IDT 2011
1240 | DD Submission to MTR (RDO/GEO consultation) | Fri May 20 17:00:00 IDT 2011 | Fri May 20 17:00:00 IDT 2011
1241 | DD Comment by MTR (RDO/GEO consultation) | Sat May 21 08:00:00 IDT 2011 | Wed Jun 15 17:00:00 IDT 2011
1242 | DD ReSubmission Preparation - Tunnel Lining | Tue Jun 07 08:00:00 IDT 2011 | Mon Jun 20 17:00:00 IDT 2011
1243 | DD ReSubmission to MTR (RDO/GEO consultation) | Mon Jun 20 17:00:00 IDT 2011 | Mon Jun 20 17:00:00 IDT 2011
1244 | DD Approval by MTR (RDO/GEO consultation) | Tue Jun 21 08:00:00 IDT 2011 | Wed Nov 30 17:00:00 IST 2011
1245 | Tunnel Segment Fabrication | Wed May 18 08:00:00 IDT 2011 | Tue Jun 24 17:00:00 IDT 2014
1246 | Segment mould & Tunnel Segment Fabrication | Wed May 18 08:00:00 IDT 2011 | Fri Jun 28 17:00:00 IDT 2013
1247 | Fabrication | Wed May 18 08:00:00 IDT 2011 | Tue Jun 24 17:00:00 IDT 2014
1248 | Placing Order of Segment Moulds | Tue Jul 19 08:00:00 IDT 2011 | Tue Jul 19 08:00:00 IDT 2011
1249 | Segment Mould Fabrication | Tue Jul 19 08:00:00 IDT 2011 | Thu Mar 22 17:00:00 IST 2012
1250 | Fabrication of Precast Segments - 1st batch | Wed Aug 10 08:00:00 IDT 2011 | Wed Dec 28 17:00:00 IST 2011
1251 | Fabrication of Precast Segments - 2nd batch | Mon Jan 16 08:00:00 IST 2012 | Sat Sep 22 17:00:00 IDT 2012
1252 | 30% Precast Segments (Mil.C5) | Thu Dec 20 17:00:00 IST 2012 | Thu Dec 20 17:00:00 IST 2012
1253 | Fabrication of Precast Segments - 3rd batch | Fri Dec 21 08:00:00 IST 2012 | Fri Apr 19 17:00:00 IDT 2013
1254 | 45% Precast Segments (Mil.C6) | Fri Apr 19 17:00:00 IDT 2013 | Fri Apr 19 17:00:00 IDT 2013
1255 | Fabrication of Precast Segments (Remaining) | Sat Apr 20 08:00:00 IDT 2013 | Tue Jun 24 17:00:00 IDT 2014
1256 | Segment mould & Tunnel Segment Fabrication | Wed May 18 08:00:00 IDT 2011 | Sat Mar 01 17:00:00 IST 2014
1257 | Tunnelling Works
1258 | Submission | Mon Feb 02 08:00:00 IST 2015 | Thu Apr 30 17:00:00 IDT 2015
1259 | Completion | Mon Feb 02 08:00:00 IST 2015 | Thu Apr 30 17:00:00 IDT 2015
1260 | Prepare & Submit Draft As-built Drawings | Mon Feb 02 08:00:00 IST 2015 | Sat Mar 28 17:00:00 IDT 2015
1261 | Prepare & Submit As-built Drawings | Mon Mar 02 08:00:00 IST 2015 | Thu Apr 30 17:00:00 IDT 2015
1262 | Cost Centre D - Nam Cheong Building Cut & Cover Tunnel | Mon Jan 31 08:00:00 IST 2011 | Sun May 10 17:00:00 IDT 2015
1263 | IPS Milestones | Sun Mar 31 17:00:00 IDT 2013 | Sun May 10 17:00:00 IDT 2015
1264 | General | Sun Mar 31 17:00:00 IDT 2013 | Sun May 10 17:00:00 IDT 2015
1265 | Complete D/T Cut & Cover Tunnel - Track Slab | Sun Mar 31 17:00:00 IDT 2013 | Sun Mar 31 17:00:00 IDT 2013
1266 | Deg. 1 Completion for D/T Tunnel | Sun Jun 15 17:00:00 IDT 2014 | Sun Jun 15 17:00:00 IDT 2014
1267 | Complete 40% U/T Cut & Cover Tunnel Structure | Sun Jun 15 17:00:00 IDT 2014 | Sun Jun 15 17:00:00 IDT 2014
1268 | Deg. 1 Completion for U/T Tunnel | Fri Mar 13 17:00:00 IST 2015 | Fri Mar 13 17:00:00 IST 2015
1269 | Closure of Access Opening in Tunnel Roof | Mon Mar 30 17:00:00 IDT 2015 | Mon Mar 30 17:00:00 IDT 2015
1270 | Complete All Works | Sun May 10 17:00:00 IDT 2015 | Sun May 10 17:00:00 IDT 2015
1271 | Design Preparation/Submission/Approval | Mon Jan 31 08:00:00 IST 2011 | Thu Sep 27 17:00:00 IST 2012
1272 | Design | Mon Jan 31 08:00:00 IST 2011 | Thu Sep 27 17:00:00 IST 2012
1273 | Prepare AIP Submission for Cut & Cover Tunnels | Mon Jan 31 08:00:00 IST 2011 | Wed May 25 17:00:00 IDT 2011
1274 | Submit AIP Submission for Cut & Cover Tunnels | Sat Mar 05 17:00:00 IST 2011 | Sat Mar 05 17:00:00 IST 2011
1275 | AIP Comment & Approval for Cut & Cover Tunnels by MTR | Sun Mar 06 08:00:00 IST 2011 | Tue Apr 05 17:00:00 IDT 2011
1276 | Prepare 1st DDA for Cut & Cover Tunnels | Mon Mar 07 08:00:00 IST 2011 | Wed Jul 13 17:00:00 IDT 2011
1277 | Submit 1st DDA for Cut & Cover Tunnels | Mon Apr 11 17:00:00 IDT 2011 | Mon Apr 11 17:00:00 IDT 2011
1278 | 1st DDA Comment & Approval by MTR (RDO/GEO consultation) | Tue Apr 12 08:00:00 IDT 2011 | Sun Jun 19 17:00:00 IDT 2011
1279 | Prepare 2nd DDA for Cut & Cover Tunnels | Mon Jan 16 08:00:00 IST 2012 | Tue Feb 21 17:00:00 IST 2012
1280 | Submit 2nd DDA for Cut & Cover Tunnels | Mon Jan 16 08:00:00 IST 2012 | Mon Jan 16 08:00:00 IST 2012
1281 | 2nd DDA for Cut & Cover Tunnels Comment & Approval by MTR | Fri Aug 31 08:00:00 IDT 2012 | Thu Sep 27 17:00:00 IST 2012
1282 | Method Statement Submission and Approval | Sun Jan 15 08:00:00 IST 2012 | Thu Oct 25 17:00:00 IST 2012
1283 | Method Statement Submission and Approval | Sun Jan 15 08:00:00 IST 2012 | Thu Oct 25 17:00:00 IST 2012
1284 | MS Submission Preparation for Cut & Cover Tunnel | Mon Jan 16 08:00:00 IST 2012 | Thu Feb 16 17:00:00 IST 2012
1285 | MS Submission to MTR | Mon Jan 16 08:00:00 IST 2012 | Mon Jan 16 08:00:00 IST 2012
1286 | MS Comment by MTR | Sun Jan 15 08:00:00 IST 2012 | Sat Feb 11 17:00:00 IST 2012
1287 | MS Re-submission Preparation | Mon Jan 16 08:00:00 IST 2012 | Wed Feb 15 17:00:00 IST 2012
1288 | MS Comment & Approval by MTR | Fri Sep 28 08:00:00 IST 2012 | Thu Oct 25 17:00:00 IST 2012
1289 | Issue for Construction | Thu Oct 25 17:00:00 IST 2012 | Thu Oct 25 17:00:00 IST 2012
1290 | Construction | Sat May 05 08:00:00 IDT 2012 | Sat Apr 18 17:00:00 IDT 2015
1291 | Cut & Cover Tunnel - Track Level | Sat May 05 08:00:00 IDT 2012 | Wed Jul 17 17:00:00 IDT 2013
1292 | D/T: Cut & Cover Tunnel - Wall AW1 | Fri Oct 12 08:00:00 IST 2012 | Tue Nov 06 17:00:00 IST 2012
1293 | D/T: Cut & Cover Tunnel - Wall AW1a | Tue Nov 20 08:00:00 IST 2012 | Wed Dec 05 17:00:00 IST 2012
1294 | D/T: Cut & Cover Tunnel - Wall AW2 | Thu Dec 06 08:00:00 IST 2012 | Mon Dec 31 17:00:00 IST 2012
1295 | D/T: Cut & Cover Tunnel - Wall AD0 | Wed Nov 07 08:00:00 IST 2012 | Thu Nov 22 17:00:00 IST 2012
1296 | U/T: Cut & Cover Tunnel - Slab ATS1 | Thu Dec 20 08:00:00 IST 2012 | Wed Jan 16 17:00:00 IST 2013
1297 | U/T: Cut & Cover Tunnel - Slab ATS2 | Wed Jan 09 08:00:00 IST 2013 | Thu Jan 31 17:00:00 IST 2013
1298 | D/T: Cut & Cover Tunnel - Removal of S4 Struts 2-P1 to P3 | Mon Nov 12 08:00:00 IST 2012 | Sat Nov 24 17:00:00 IST 2012
1299 | D/T: Cut & Cover Tunnel - Wall AD1 | Sat Jun 29 08:00:00 IDT 2013 | Wed Jul 17 17:00:00 IDT 2013
1300 | D/T: Cut & Cover Tunnel - Wall AD2 | Sat May 05 08:00:00 IDT 2012 | Wed May 23 17:00:00 IDT 2012
1301 | Shaft Box B (Northern Portion) | Mon Jan 28 08:00:00 IST 2013 | Wed Jun 11 17:00:00 IDT 2014
1302 | G/L 1 - 5 | Mon Jan 28 08:00:00 IST 2013 | Wed Jun 11 17:00:00 IDT 2014
1303 | Construction of Above Track Slab D/T | Mon Jan 28 08:00:00 IST 2013 | Sat Apr 13 17:00:00 IDT 2013
1304 | Construction of Above Track Slab U/T (Part 1) | Mon Jan 28 08:00:00 IST 2013 | Wed Apr 17 17:00:00 IDT 2013
1305 | Steel Bell & False Tunnel Dismantling | Tue Apr 22 08:00:00 IDT 2014 | Thu May 08 17:00:00 IDT 2014
1306 | Construction of Above Track Slab U/T (Part 2) | Wed May 07 08:00:00 IDT 2014 | Wed Jun 11 17:00:00 IDT 2014
1307 | G/L 1 - 9 | Tue Dec 31 08:00:00 IST 2013 | Thu Feb 13 17:00:00 IST 2014
1308 | North D/T: Construction of Walkway (Dkb137+783 to Dkb 137+850) | Wed Jan 15 08:00:00 IST 2014 | Thu Jan 30 17:00:00 IST 2014
1309 | North U/T: Construction of C & C Tunnel (GL 1 - 9) & Deg. 1 works | Tue Dec 31 08:00:00 IST 2013 | Thu Feb 13 17:00:00 IST 2014
1310 | South Opening at NAC (Dkb137+907 to Dkb137+941) | Mon Dec 02 08:00:00 IST 2013 | Sat Jan 24 17:00:00 IST 2015
1311 | Area 1 - South D/T: Construction of Walkway, External wall, Internal wall, End wall & Above Track Slab (Target dates) | Mon Dec 02 08:00:00 IST 2013 | Sat May 17 17:00:00 IDT 2014
1312 | Area 3 - South U/T: Construction of Walkway, External wall & Internal wall( Target dates) | Mon Sep 01 08:00:00 IDT 2014 | Sat Dec 20 17:00:00 IST 2014
1313 | Area 3 - South U/T: Construction of Above-Track Roof Slab (Closure of Opening) (Target dates) | Mon Dec 22 08:00:00 IST 2014 | Sat Jan 24 17:00:00 IST 2015
1314 | NAC Shaft - Central Opening Structure (Dkb137+850 to Dkb137+885) | Mon May 19 08:00:00 IDT 2014 | Sat Apr 18 17:00:00 IDT 2015
1315 | G/L 9 - 13 (Dkb137+850 to Dkb137+885) | Mon May 19 08:00:00 IDT 2014 | Sat Apr 18 17:00:00 IDT 2015
1316 | Area 2 - D/T Construction of External wall & Walkways | Mon May 19 08:00:00 IDT 2014 | Sat Jun 14 17:00:00 IDT 2014
1317 | Area 4B - Construction of Internal walls and Central portion of Above-Track Roof Slab with falsework | Mon Dec 29 08:00:00 IST 2014 | Sat Feb 07 17:00:00 IST 2015
1318 | Area 4A - U/T Construction of External wall & Walkways (Target dates) | Mon Dec 29 08:00:00 IST 2014 | Sat Jan 24 17:00:00 IST 2015
1319 | Area 4C - Close remaining Above-Track Roof Slab & RC duct btw Dkb137+850 to 137+885 (Target dates) | Mon Dec 29 08:00:00 IST 2014 | Sat Apr 18 17:00:00 IDT 2015
1320 | Cut and Cover Tunnel works
1321 | Access Dates for Designated Contractor
1322 | Submission | Mon Mar 02 08:00:00 IST 2015 | Thu Apr 16 17:00:00 IDT 2015
1323 | Completion | Mon Mar 02 08:00:00 IST 2015 | Thu Apr 16 17:00:00 IDT 2015
1324 | Prepare & Submit Draft As-built Drawings | Mon Mar 02 08:00:00 IST 2015 | Thu Apr 16 17:00:00 IDT 2015
1325 | Prepare & Submit As-built Drawings | Mon Mar 02 08:00:00 IST 2015 | Thu Apr 16 17:00:00 IDT 2015
1326 | Cost Centre E - Nam Cheong Ventilation Building | Wed May 12 08:00:00 IDT 2010 | Mon Aug 24 17:00:00 IDT 2015
1327 | IPS Milestones | Mon Feb 28 08:00:00 IST 2011 | Mon Aug 24 17:00:00 IDT 2015
1328 | General | Mon Feb 28 08:00:00 IST 2011 | Mon Aug 24 17:00:00 IDT 2015
1329 | Complete 20% of Diaphragm Wall | Mon Feb 28 08:00:00 IST 2011 | Mon Feb 28 08:00:00 IST 2011
1330 | Complete 90% Diaphragm Wall | Sun Jun 19 17:00:00 IDT 2011 | Sun Jun 19 17:00:00 IDT 2011
1331 | Complete 100% Diaphragm Wall | Sun Jun 19 17:00:00 IDT 2011 | Sun Jun 19 17:00:00 IDT 2011
1332 | Complete 45% of Excavation | Wed Aug 31 08:00:00 IDT 2011 | Wed Aug 31 08:00:00 IDT 2011
1333 | Complete Excavation | Sun Jan 15 08:00:00 IST 2012 | Sun Jan 15 08:00:00 IST 2012
1334 | Complete 70% Nam Cheong Vent. Building Structure | Sat Sep 14 17:00:00 IDT 2013 | Sat Sep 14 17:00:00 IDT 2013
1335 | Deg.1 Completion for Nam Cheong Vent. Building (VB7), except Track level and Above Track level | Sat May 31 17:00:00 IDT 2014 | Sat May 31 17:00:00 IDT 2014
1336 | All Permanent Doors Installed | Tue Mar 31 17:00:00 IDT 2015 | Tue Mar 31 17:00:00 IDT 2015
1337 | All Work Completed & Statutory Inspection Successfully Undertaken | Mon Aug 24 17:00:00 IDT 2015 | Mon Aug 24 17:00:00 IDT 2015
1338 | Design Preparation/Submission/Approval | Mon Jan 31 08:00:00 IST 2011 | Fri Apr 01 17:00:00 IDT 2011
1339 | Temp.Works Design Submission | Mon Jan 31 08:00:00 IST 2011 | Fri Apr 01 17:00:00 IDT 2011
1340 | Temp. Wokrs Desgn for DW | Mon Jan 31 08:00:00 IST 2011 | Tue Feb 22 17:00:00 IST 2011
1341 | Temp. Works Design Submit to MTR | Thu Mar 03 17:00:00 IST 2011 | Thu Mar 03 17:00:00 IST 2011
1342 | Temp. Works Design Reviewed by MTR | Fri Mar 04 08:00:00 IST 2011 | Tue Mar 29 17:00:00 IST 2011
1343 | Issue for Construction | Fri Apr 01 17:00:00 IDT 2011 | Fri Apr 01 17:00:00 IDT 2011
1344 | Diaphragm Wall Design/submission/Approval | Sat Jan 08 08:00:00 IST 2011 | Tue Nov 29 17:00:00 IST 2011
1345 | Design | Sat Jan 08 08:00:00 IST 2011 | Tue Nov 29 17:00:00 IST 2011
1346 | Prepare Zone A - D-Wall General Arrangement Dwgs & Calculations Part 1 | Sat Jan 08 08:00:00 IST 2011 | Fri Feb 25 17:00:00 IST 2011
1347 | Submit Zone A - D-Wall General Arrangement to MTR (RDO/GEO consultation) | Mon Jan 31 08:00:00 IST 2011 | Mon Jan 31 08:00:00 IST 2011
1348 | Zone A- D-Wall General Arrangement Comments & Approval by MTR (RDO/GEO consultation) | Mon Jan 31 08:00:00 IST 2011 | Sun Feb 13 17:00:00 IST 2011
1349 | Prepare Zone A - D-Wall R.C Details Dwgs.& Calculation Part 2 | Mon Jan 31 08:00:00 IST 2011 | Fri Mar 25 17:00:00 IST 2011
1350 | Submit Zone A - D-Wall R.C Details to MTR | Fri Mar 11 17:00:00 IST 2011 | Fri Mar 11 17:00:00 IST 2011
1351 | Zone A - D-Wall R.C Details Comment & Approval by MTR | Sat Mar 12 08:00:00 IST 2011 | Tue Mar 29 17:00:00 IST 2011
1352 | Prepare Zone A - D-Wall ELS | Sat Mar 12 08:00:00 IST 2011 | Wed Aug 03 17:00:00 IDT 2011
1353 | Submit Zone A - D-Wall ELS to MTR | Wed Apr 27 17:00:00 IDT 2011 | Wed Apr 27 17:00:00 IDT 2011
1354 | Zone A - D-Wall ELS Comment & Approval by MTR | Thu Apr 28 08:00:00 IDT 2011 | Wed Jul 13 17:00:00 IDT 2011
1355 | Prepare Zone B - D-Wall General Arrangement Dwgs & Calculations Part 1 | Sat Jan 08 08:00:00 IST 2011 | Tue Mar 22 17:00:00 IST 2011
1356 | Submit Zone B - D-Wall General Arrangement to MTR (RDO/GEO consultation) | Wed Feb 09 17:00:00 IST 2011 | Wed Feb 09 17:00:00 IST 2011
1357 | Zone B - D-Wall General Arrangement Comments & Approval by MTR (RDO/GEO consultation) | Thu Feb 10 08:00:00 IST 2011 | Thu Mar 10 17:00:00 IST 2011
1358 | Prepare Zone B - D-Wall R.C Details Dwgs.& Calculation Part 2 | Sat Mar 12 08:00:00 IST 2011 | Mon May 16 17:00:00 IDT 2011
1359 | Submit Zone B - D-Wall R.C Details to MTR | Tue Apr 26 17:00:00 IDT 2011 | Tue Apr 26 17:00:00 IDT 2011
1360 | Zone B - D-Wall R.C Details Comments & Approval by MTR | Wed Apr 27 08:00:00 IDT 2011 | Sat May 14 17:00:00 IDT 2011
1361 | Prepare Zone B- D-Wall ELS | Wed Apr 06 08:00:00 IDT 2011 | Tue Nov 29 17:00:00 IST 2011
1362 | Submit Zone B - D-Wall ELS to MTR | Mon Jun 20 08:00:00 IDT 2011 | Mon Jun 20 08:00:00 IDT 2011
1363 | Zone B - D-Wall ELS Comment & Approval by MTR | Sun Jun 19 08:00:00 IDT 2011 | Tue Jul 19 17:00:00 IDT 2011
1364 | Method Statement Submission and Approval | Mon Jan 31 08:00:00 IST 2011 | Sat Apr 02 17:00:00 IDT 2011
1365 | Method Statement Submission and Approval | Mon Jan 31 08:00:00 IST 2011 | Sat Apr 02 17:00:00 IDT 2011
1366 | MS Preparation for Diaphragm wall | Mon Jan 31 08:00:00 IST 2011 | Wed Mar 16 17:00:00 IST 2011
1367 | MS Submission to MTR | Fri Mar 04 17:00:00 IST 2011 | Fri Mar 04 17:00:00 IST 2011
1368 | MS Comment & Approval by MTR | Sat Mar 05 08:00:00 IST 2011 | Wed Mar 23 17:00:00 IST 2011
1369 | Issue for Construction | Sat Apr 02 17:00:00 IDT 2011 | Sat Apr 02 17:00:00 IDT 2011
1370 | TTM Submission and Approval | Wed May 12 08:00:00 IDT 2010 | Sat Feb 12 17:00:00 IST 2011
1371 | TTM Scheme Submission & Approval | Wed May 12 08:00:00 IDT 2010 | Sat Feb 12 17:00:00 IST 2011
1372 | Prepare Temporary Traffic Management (Main Road) | Wed May 12 08:00:00 IDT 2010 | Tue Jun 08 17:00:00 IDT 2010
1373 | TTM reviewed by SLG | Wed May 12 08:00:00 IDT 2010 | Fri Jul 09 17:00:00 IDT 2010
1374 | Approved TTMS | Wed May 12 08:00:00 IDT 2010 | Wed May 12 08:00:00 IDT 2010
1375 | Issue Endorsed Drawings | Wed May 12 08:00:00 IDT 2010 | Tue May 18 17:00:00 IDT 2010
1376 | Notification to RMO | Wed May 12 08:00:00 IDT 2010 | Tue May 18 17:00:00 IDT 2010
1377 | XP Application & Approval (Main Road) | Sat Jan 08 08:00:00 IST 2011 | Sat Feb 12 17:00:00 IST 2011
1378 | Implement TTM (Main Road) | Fri Aug 06 17:00:00 IDT 2010 | Fri Aug 06 17:00:00 IDT 2010
1379 | Prepare TTM (Footpath Closure) | Wed May 12 08:00:00 IDT 2010 | Tue Jun 08 17:00:00 IDT 2010
1380 | TTM Reviewed by SLG | Wed May 12 08:00:00 IDT 2010 | Fri Jul 09 17:00:00 IDT 2010
1381 | Approved TTMS | Wed May 12 08:00:00 IDT 2010 | Wed May 12 08:00:00 IDT 2010
1382 | Issue Endorsed Drawings | Wed May 12 08:00:00 IDT 2010 | Tue May 18 17:00:00 IDT 2010
1383 | Notification to RMO | Wed May 12 08:00:00 IDT 2010 | Tue May 18 17:00:00 IDT 2010
1384 | Implement TTM (Footpath Closure) | Wed May 12 08:00:00 IDT 2010 | Wed May 12 08:00:00 IDT 2010
1385 | Site Establishment | Mon Jan 31 08:00:00 IST 2011 | Wed Apr 06 17:00:00 IDT 2011
1386 | General | Mon Jan 31 08:00:00 IST 2011 | Wed Apr 06 17:00:00 IDT 2011
1387 | Site Establishment for Works Areas 11.23,11.23A, 11.23B &11.26A | Tue Feb 01 08:00:00 IST 2011 | Thu Mar 03 17:00:00 IST 2011
1388 | Installation of Instrumentation for D-wall Construction | Fri Mar 04 08:00:00 IST 2011 | Wed Mar 16 17:00:00 IST 2011
1389 | Preparation of CNP for Shaft Works | Mon Jan 31 08:00:00 IST 2011 | Thu Mar 17 17:00:00 IST 2011
1390 | CNP Submission Approval by EPD | Mon Mar 21 08:00:00 IST 2011 | Wed Apr 06 17:00:00 IDT 2011
1391 | Zone A | Sat Jan 08 08:00:00 IST 2011 | Fri Aug 30 17:00:00 IDT 2013
1392 | D-wall Construction 38nos. & Pump Test | Mon Jan 07 08:00:00 IST 2013 | Sun Aug 25 17:00:00 IDT 2013
1393 | ELS | Mon Jan 07 08:00:00 IST 2013 | Fri Aug 23 17:00:00 IDT 2013
1394 | General | Tue Feb 01 08:00:00 IST 2011 | Mon Mar 28 17:00:00 IST 2011
1395 | Close Footpath (Zone 1) | Tue Feb 01 08:00:00 IST 2011 | Mon Feb 07 17:00:00 IST 2011
1396 | Trial Trench for Gas Main | Tue Feb 08 08:00:00 IST 2011 | Mon Feb 14 17:00:00 IST 2011
1397 | Gas Min Diversion (GAS210) | Tue Feb 15 08:00:00 IST 2011 | Mon Mar 28 17:00:00 IST 2011
1398 | Zone A Construction | Sat Jan 08 08:00:00 IST 2011 | Fri Aug 30 17:00:00 IDT 2013
1399 | Pre-Drilling | Sat Jan 08 08:00:00 IST 2011 | Fri Apr 01 17:00:00 IDT 2011
1400 | Ground Treatment to Previous Seawall Zone (for D1 to D15) | Sat Apr 09 08:00:00 IDT 2011 | Thu Jun 16 17:00:00 IDT 2011
1401 | Guide Wall Installation/Predrilling | Sat Mar 12 08:00:00 IST 2011 | Tue Aug 02 17:00:00 IDT 2011
1402 | Temp.D-Wall Installation (38 Panels) | Fri Mar 25 08:00:00 IST 2011 | Thu Aug 25 17:00:00 IDT 2011
1403 | Shear Pin Installation | Tue Feb 01 08:00:00 IST 2011 | Wed Mar 30 17:00:00 IST 2011
1404 | Toe Grouting | Mon Feb 21 08:00:00 IST 2011 | Sat May 07 17:00:00 IDT 2011
1405 | Capping Beam | Tue Feb 01 08:00:00 IST 2011 | Wed Mar 09 17:00:00 IST 2011
1406 | Installation of instrumentation and Pumping Test | Mon Feb 28 08:00:00 IST 2011 | Sat Apr 16 17:00:00 IDT 2011
1407 | King Post & Gantry Post Installation (KP-4nos. & GP-6nos.) | Tue Feb 01 08:00:00 IST 2011 | Thu Mar 03 17:00:00 IST 2011
1408 | D-wall Construction 38nos. & Pump Test | Mon Jan 07 08:00:00 IST 2013 | Fri Aug 30 17:00:00 IDT 2013
1409 | Stell Bell Installation | Fri Mar 09 08:00:00 IST 2012 | Thu Apr 19 17:00:00 IDT 2012
1410 | Zone A Excavation | Mon Mar 28 08:00:00 IST 2011 | Thu May 31 17:00:00 IDT 2012
1411 | VER.B
1412 | Shaft A ELS | Mon Mar 28 08:00:00 IST 2011 | Thu May 31 17:00:00 IDT 2012
1413 | Surface Levelling to +3.80mPD (for Capping Beam & S1 Strutting) | Mon Mar 28 08:00:00 IST 2011 | Sat Jun 04 17:00:00 IDT 2011
1414 | ELS for Box A (for Steel Bell installation) | Tue Jun 21 08:00:00 IDT 2011 | Thu Jan 26 17:00:00 IST 2012
1415 | ELS for Box A (Remaining) | Mon Jan 16 08:00:00 IST 2012 | Wed Mar 07 17:00:00 IST 2012
1416 | Base Slab Part 1 | Mon Jan 16 08:00:00 IST 2012 | Wed Feb 22 17:00:00 IST 2012
1417 | Strutting Removal for S5 & S6 | Mon Jan 16 08:00:00 IST 2012 | Mon Jan 30 17:00:00 IST 2012
1418 | Base Slab Part 2 | Mon Jan 16 08:00:00 IST 2012 | Thu Mar 15 17:00:00 IST 2012
1419 | Brackets Installation | Mon Jan 16 08:00:00 IST 2012 | Wed Jan 18 17:00:00 IST 2012
1420 | Steel Bell Installation | Mon Jan 16 08:00:00 IST 2012 | Tue Jan 31 17:00:00 IST 2012
1421 | Tympanum Drilling & Steel Fixing | Mon Jan 16 08:00:00 IST 2012 | Thu May 31 17:00:00 IDT 2012
1422 | Zone B | Wed May 12 08:00:00 IDT 2010 | Wed May 23 17:00:00 IDT 2012
1423 | D-wall Construction 13+20nos. & Pump Test | Mon Aug 15 08:00:00 IDT 2011 | Wed May 23 17:00:00 IDT 2012
1424 | ELS | Sun Jun 26 08:00:00 IDT 2011 | Thu Dec 22 17:00:00 IST 2011
1425 | General | Wed May 12 08:00:00 IDT 2010 | Thu Jun 23 17:00:00 IDT 2011
1426 | Tree Transplant by 801 Designated Contractor | Tue Sep 14 08:00:00 IST 2010 | Tue Sep 14 08:00:00 IST 2010
1427 | TTM Implementation (Footpath Closure) | Wed May 12 08:00:00 IDT 2010 | Wed May 12 17:00:00 IDT 2010
1428 | TTM Implementation (Main Road) | Sat Aug 07 08:00:00 IDT 2010 | Sat Aug 07 17:00:00 IDT 2010
1429 | Trial Trench to Expose Utilities @ Footpath | Sat Jan 08 08:00:00 IST 2011 | Fri Jan 21 17:00:00 IST 2011
1430 | Trial Trench for CLP Cable208&209 | Sat Jan 08 08:00:00 IST 2011 | Wed Jan 26 17:00:00 IST 2011
1431 | Excavate Trench for Utilities Diversion | Sat Jan 08 08:00:00 IST 2011 | Sat Jan 22 17:00:00 IST 2011
1432 | Gas Main Diversion (GAS209&GAS208) | Tue Jan 18 08:00:00 IST 2011 | Tue Feb 08 17:00:00 IST 2011
1433 | Preparation works & Excavation for Utilities Diversion | Wed May 12 08:00:00 IDT 2010 | Sat Jul 31 17:00:00 IDT 2010
1434 | Expose and Protect Saltwater Main (SW203) | Sat Jan 08 08:00:00 IST 2011 | Tue Jan 25 17:00:00 IST 2011
1435 | Slew HGC+Cable TV Cable (HGC204+CATV208) | Sat Jan 08 08:00:00 IST 2011 | Sat Feb 12 17:00:00 IST 2011
1436 | Slew WTT+PCCW Cable (WTT205+PCCW205) | Sat Jan 08 08:00:00 IST 2011 | Sat Feb 12 17:00:00 IST 2011
1437 | Slew CLP 11kV Cable | Thu Feb 17 08:00:00 IST 2011 | Thu Feb 24 17:00:00 IST 2011
1438 | Slew 400kV Cable (CLP208) | Sat Aug 07 08:00:00 IDT 2010 | Sat Oct 02 17:00:00 IST 2010
1439 | SlewTelecomCable(HGC204+CATV208)to UtilityTrough | Tue May 31 08:00:00 IDT 2011 | Thu Jun 23 17:00:00 IDT 2011
1440 | SlewTelecomCable(WTT205+PCCW205)to UtilityTrough | Tue May 31 08:00:00 IDT 2011 | Thu Jun 23 17:00:00 IDT 2011
1441 | Backfill & Protection for Utilities | Mon Feb 28 08:00:00 IST 2011 | Wed May 04 17:00:00 IDT 2011
1442 | Zone B West (Not within Utilities Zone) | Mon Feb 28 08:00:00 IST 2011 | Wed May 23 17:00:00 IDT 2012
1443 | Pre-drilling/Guide Wall Installation | Sat Mar 12 08:00:00 IST 2011 | Sat Apr 09 17:00:00 IDT 2011
1444 | Temp.D-Wall Installation (13Panels) | Thu Apr 28 08:00:00 IDT 2011 | Tue Aug 16 17:00:00 IDT 2011
1445 | Shear Pin Installation | Mon Feb 28 08:00:00 IST 2011 | Thu Jun 23 17:00:00 IDT 2011
1446 | Toe Grouting | Fri Apr 01 08:00:00 IDT 2011 | Wed Jul 27 17:00:00 IDT 2011
1447 | Stitch Grouting btn D-Wall & FS1 Culvert | Tue Jun 21 08:00:00 IDT 2011 | Mon Jul 18 17:00:00 IDT 2011
1448 | D-wall Construction 13+20nos. & Pump Test | Mon Aug 15 08:00:00 IDT 2011 | Wed May 23 17:00:00 IDT 2012
1449 | Zone B Remaining | Tue Feb 01 08:00:00 IST 2011 | Wed Feb 01 17:00:00 IST 2012
1450 | Ground Treatment to Previous Seawall Zone | Tue Feb 01 08:00:00 IST 2011 | Wed Jun 01 17:00:00 IDT 2011
1451 | Pre-drilling/ Guide Wall Installation | Tue Feb 01 08:00:00 IST 2011 | Mon Mar 21 17:00:00 IST 2011
1452 | Temp.D-Wall Installation ( 20 Panels) | Mon Mar 21 08:00:00 IST 2011 | Sat Oct 08 17:00:00 IST 2011
1453 | Shear Pin Installation | Thu Jul 14 11:00:00 IDT 2011 | Fri Sep 02 11:00:00 IDT 2011
1454 | Toe Grouting | Fri Jul 29 08:00:00 IDT 2011 | Tue Aug 30 17:00:00 IDT 2011
1455 | Stitch Grouting between D-Wall & FS1 Culvert | Wed Jul 06 08:00:00 IDT 2011 | Thu Aug 25 17:00:00 IDT 2011
1456 | Capping Beam | Tue Jun 21 08:00:00 IDT 2011 | Tue Aug 09 17:00:00 IDT 2011
1457 | Install Instrumentation+Pumping Test | Thu Aug 04 08:00:00 IDT 2011 | Wed Sep 21 17:00:00 IDT 2011
1458 | Utilities Common Trough | Mon Jan 16 08:00:00 IST 2012 | Wed Feb 01 17:00:00 IST 2012
1459 | Setup & Install Four Prebored H-piles (adjacent to Existing B17) | Fri Jul 08 08:00:00 IDT 2011 | Mon Jul 25 17:00:00 IDT 2011
1460 | King Post & Gantry Post Installation (7KP & 2GP) | Tue Jun 21 08:00:00 IDT 2011 | Tue Aug 02 17:00:00 IDT 2011
1461 | Zone B Excavation | Tue Jun 21 08:00:00 IDT 2011 | Tue Apr 03 17:00:00 IDT 2012
1462 | ELS | Sun Jun 26 08:00:00 IDT 2011 | Thu Dec 22 17:00:00 IST 2011
1463 | Steel Bell Installation | Sun Jan 15 08:00:00 IST 2012 | Sun Jan 15 08:00:00 IST 2012
1464 | Shaft B ELS | Tue Jun 21 08:00:00 IDT 2011 | Tue Apr 03 17:00:00 IDT 2012
1465 | Surface Levelling to +3.80mPD (for Capping Beam & S1 Strutting) | Wed Aug 24 08:00:00 IDT 2011 | Wed Sep 28 17:00:00 IDT 2011
1466 | ELS for Box B (for Steel Bell Installation) | Tue Jun 21 08:00:00 IDT 2011 | Thu Nov 10 17:00:00 IST 2011
1467 | ELS for Box B (Remaining) | Mon Jan 16 08:00:00 IST 2012 | Thu Mar 01 17:00:00 IST 2012
1468 | Base Slab Part 1 | Mon Jan 16 08:00:00 IST 2012 | Tue Feb 21 17:00:00 IST 2012
1469 | Strutting Removal for S5 & S6 | Mon Jan 16 08:00:00 IST 2012 | Thu Jan 26 17:00:00 IST 2012
1470 | Base Slab Part 2 | Mon Jan 16 08:00:00 IST 2012 | Wed Feb 29 17:00:00 IST 2012
1471 | Brackets Installation | Mon Jan 16 08:00:00 IST 2012 | Tue Jan 17 17:00:00 IST 2012
1472 | Steel Bell Installation | Mon Jan 16 08:00:00 IST 2012 | Wed Feb 01 17:00:00 IST 2012
1473 | Tympanum Drilling & Steel Fixing | Mon Jan 16 08:00:00 IST 2012 | Tue Apr 03 17:00:00 IDT 2012
1474 | Ventilation Building | Sat Sep 01 08:00:00 IDT 2012 | Mon Aug 24 17:00:00 IDT 2015
1475 | Access Dates for Designated Contractors | Mon Apr 28 08:00:00 IDT 2014 | Mon Apr 28 08:00:00 IDT 2014
1476 | *815 - Ironmongery Delivery to Site | Mon Apr 28 08:00:00 IDT 2014 | Mon Apr 28 08:00:00 IDT 2014
1477 | Reinforced Concrete Structure | Sat Sep 01 08:00:00 IDT 2012 | Thu Aug 13 17:00:00 IDT 2015
1478 | Shaft Box B (Northern Portion) | Sat Sep 01 08:00:00 IDT 2012 | Fri Jun 06 17:00:00 IDT 2014
1479 | G/L 1 - 5 | Fri Jan 04 08:00:00 IST 2013 | Sat Jul 06 17:00:00 IDT 2013
1480 | Construction of L2 Slab | Fri Jan 04 08:00:00 IST 2013 | Sat Feb 02 17:00:00 IST 2013
1481 | Construction of L1 Slab | Wed Feb 20 08:00:00 IST 2013 | Thu Mar 21 17:00:00 IST 2013
1482 | Construction of L0 Slab | Mon Jun 03 08:00:00 IDT 2013 | Sat Jul 06 17:00:00 IDT 2013
1483 | G/L 5 - 9 | Sat Sep 01 08:00:00 IDT 2012 | Thu Jul 11 17:00:00 IDT 2013
1484 | Construction of L2 Slab | Sat Sep 01 08:00:00 IDT 2012 | Wed Nov 28 17:00:00 IST 2012
1485 | Construction of L1 Slab (including 2 FS Tank) | Thu Nov 29 08:00:00 IST 2012 | Fri Mar 08 17:00:00 IST 2013
1486 | Construction of L0 Slab | Mon Apr 29 08:00:00 IDT 2013 | Thu Jul 11 17:00:00 IDT 2013
1487 | G/L 1 - 6 | Mon Nov 11 08:00:00 IST 2013 | Fri Jun 06 17:00:00 IDT 2014
1488 | Construction of G/L Slab | Tue Mar 04 08:00:00 IST 2014 | Wed Mar 26 17:00:00 IST 2014
1489 | Construction of U1 Slab | Mon Apr 14 08:00:00 IDT 2014 | Mon May 05 17:00:00 IDT 2014
1490 | Construction of Service Slab | Fri May 23 08:00:00 IDT 2014 | Fri Jun 06 17:00:00 IDT 2014
1491 | Construction of Roof Slab | Mon May 19 08:00:00 IDT 2014 | Wed Jun 04 17:00:00 IDT 2014
1492 | Gantry impact from TBM Re-assembly and False Tunnel Dismantling | Mon Nov 11 08:00:00 IST 2013 | Thu Jan 23 17:00:00 IST 2014
1493 | Ch137+968 to Ch138+328 (200 Ring nos.) | Sat Dec 14 08:00:00 IST 2013 | Tue Jan 21 17:00:00 IST 2014
1494 | Shaft Box A (Southern Portion)
1495 | G/L 13 - 15
1496 | G/L 11 - 13
1497 | FS1 Works at Shaft Central Portion | Mon Jun 15 08:00:00 IDT 2015 | Thu Aug 13 17:00:00 IDT 2015
1498 | G/L 9 - 11 | Mon Jun 15 08:00:00 IDT 2015 | Thu Aug 13 17:00:00 IDT 2015
1499 | Construction of column & cantilver slab under FS1 (after closure of opening) | Mon Jun 15 08:00:00 IDT 2015 | Thu Jul 09 17:00:00 IDT 2015
1500 | Backfilling & Reinstatement of FS1 | Sat Jul 11 08:00:00 IDT 2015 | Thu Aug 13 17:00:00 IDT 2015
1501 | Track Level
1502 | Above Track Level
1503 | L2 Level
1504 | L1 Level
1505 | L0 Level
1506 | G/F Level
1507 | U1 Level
1508 | Backfilling, Strut removal & Reinstatement | Mon Aug 05 08:00:00 IDT 2013 | Thu Jul 30 09:36:00 IDT 2015
1509 | Backfilling and Strut Removal | Mon Aug 05 08:00:00 IDT 2013 | Wed Jul 15 17:00:00 IDT 2015
1510 | GL 1 - 8 (works concurrently to VB7 construction) | Mon Aug 05 08:00:00 IDT 2013 | Fri Nov 22 17:00:00 IST 2013
1511 | GL 15 - 20 | Thu Apr 02 08:00:00 IDT 2015 | Mon Jun 08 17:00:00 IDT 2015
1512 | GL 8 - 15 | Mon May 18 08:00:00 IDT 2015 | Wed Jul 15 17:00:00 IDT 2015
1513 | Housing Car park and Podium Shop | Sat Jul 11 09:36:00 IDT 2015 | Thu Jul 30 09:36:00 IDT 2015
1514 | Concrete breaking of last 2m of D-wall (Option) | Sat Jul 11 09:36:00 IDT 2015 | Thu Jul 30 09:36:00 IDT 2015
1515 | ABWF works | Wed Sep 11 08:00:00 IDT 2013 | Mon Aug 24 17:00:00 IDT 2015
1516 | Degree 1 works | Wed Sep 11 08:00:00 IDT 2013 | Mon Jul 28 17:00:00 IDT 2014
1517 | Ref.4C (i) (Deg.1): All Rms within VB7 at Level L2, UL2, L1 and UL1 | Wed Sep 11 08:00:00 IDT 2013 | Fri Nov 29 17:00:00 IST 2013
1518 | Floor Screeding (L2) | Wed Sep 11 08:00:00 IDT 2013 | Fri Oct 25 17:00:00 IDT 2013
1519 | Floor Screeding (L1) | Fri Nov 01 08:00:00 IST 2013 | Fri Nov 29 17:00:00 IST 2013
1520 | Ref.4C (ii) (Deg.1): All Rms within VB7 at Track Level & Above Track Level | Mon Dec 02 08:00:00 IST 2013 | Sat Mar 01 17:00:00 IST 2014
1521 | Floor Screeding (Track Level & Above Track Level) | Mon Dec 02 08:00:00 IST 2013 | Wed Jan 15 17:00:00 IST 2014
1522 | Degree 1 works for 4C(ii) | Wed Jan 15 08:00:00 IST 2014 | Sat Mar 01 17:00:00 IST 2014
1523 | Ref.4C (iii) (Deg.1): All Rms within VB7 (excluding Ref.4C (i) & 4C (ii)) | Mon Apr 07 08:00:00 IDT 2014 | Mon Jul 28 17:00:00 IDT 2014
1524 | Floor Screeding (G/F) | Fri May 02 08:00:00 IDT 2014 | Fri May 16 17:00:00 IDT 2014
1525 | Degree 1 works for 4C (iii) | Mon Apr 07 08:00:00 IDT 2014 | Wed May 28 17:00:00 IDT 2014
1526 | Floor Screeding (U1/F) | Tue May 27 08:00:00 IDT 2014 | Tue Jun 10 17:00:00 IDT 2014
1527 | Floor Screeding & Waterproofing (Roof) | Wed Jul 23 08:00:00 IDT 2014 | Mon Jul 28 17:00:00 IDT 2014
1528 | Degree 2 works | Mon Nov 04 08:00:00 IST 2013 | Sat Jul 12 17:00:00 IDT 2014
1529 | Deg. 2 Works for Level L1, UL2, L1 and UL1 | Mon Nov 04 08:00:00 IST 2013 | Tue Feb 11 17:00:00 IST 2014
1530 | Deg. 2 Works for Track level and Above Track level | Tue Dec 31 08:00:00 IST 2013 | Sat Mar 22 17:00:00 IST 2014
1531 | Deg. 2 Works for Level L0, Ground Floor, U1, Service level & Roof | Mon Mar 24 08:00:00 IST 2014 | Sat Jul 12 17:00:00 IDT 2014
1532 | Degree 3 works | Mon Feb 24 08:00:00 IST 2014 | Fri Sep 05 17:00:00 IDT 2014
1533 | Deg. 3 Works for Level L1, UL2, L1 and UL1 | Mon Feb 24 08:00:00 IST 2014 | Thu Apr 17 17:00:00 IDT 2014
1534 | Deg. 3 Works for Track level and Above Track level | Mon Mar 24 08:00:00 IST 2014 | Sat May 17 17:00:00 IDT 2014
1535 | Deg. 3 Works for Level L0, Ground Floor, U1, Service level & Roof | Mon Jul 14 08:00:00 IDT 2014 | Fri Sep 05 17:00:00 IDT 2014
1536 | External Works | Fri May 23 08:00:00 IDT 2014 | Mon Aug 24 17:00:00 IDT 2015
1537 | Start External works | Fri May 23 08:00:00 IDT 2014 | Fri May 23 08:00:00 IDT 2014
1538 | Site Formation Works | Fri May 23 08:00:00 IDT 2014 | Thu Aug 07 17:00:00 IDT 2014
1539 | Roadworks and External Works | Fri Jun 13 08:00:00 IDT 2014 | Thu Aug 28 17:00:00 IDT 2014
1540 | Landscaping | Mon Dec 15 08:00:00 IST 2014 | Mon Mar 23 08:24:00 IST 2015
1541 | Paving | Thu Aug 14 08:00:00 IDT 2014 | Sat Oct 25 08:48:00 IDT 2014
1542 | Statutory Inspection | Sat Jul 25 08:00:00 IDT 2015 | Mon Aug 24 17:00:00 IDT 2015
1543 | Complete Ext. Water Works & Connect to Watermains | Fri Jul 24 17:00:00 IDT 2015 | Fri Jul 24 17:00:00 IDT 2015
1544 | Completion Ext. Telephone Drawpits & Ducts | Fri Jul 24 17:00:00 IDT 2015 | Fri Jul 24 17:00:00 IDT 2015
1545 | Submission | Mon Jan 12 08:00:00 IST 2015 | Thu Apr 30 17:00:00 IDT 2015
1546 | Completion | Mon Jan 12 08:00:00 IST 2015 | Thu Apr 30 17:00:00 IDT 2015
1547 | Prepare & Submit Draft As-built Drawings | Mon Jan 12 08:00:00 IST 2015 | Sat Feb 07 17:00:00 IST 2015
1548 | Prepare & Submit As-built Drawings | Mon Mar 02 08:00:00 IST 2015 | Thu Apr 30 17:00:00 IDT 2015
1549 | Prepare & Submit Draft O&M Manuals | Fri Jan 16 08:00:00 IST 2015 | Thu Feb 12 17:00:00 IST 2015
1550 | Prepare & Submit O&M Manuals | Mon Mar 02 08:00:00 IST 2015 | Thu Apr 30 17:00:00 IDT 2015
1551 | Cost Centre F - Obstruction removal & Reinstate Works | Sat Jan 08 08:00:00 IST 2011 | Sun May 10 17:00:00 IDT 2015
1552 | IPS Milestones | Mon Feb 28 08:00:00 IST 2011 | Sun May 10 17:00:00 IDT 2015
1553 | General | Mon Feb 28 08:00:00 IST 2011 | Sun May 10 17:00:00 IDT 2015
1554 | Obtain SLG Approval for Confirm Old CheungShaWan Cargo Pier Pile Locat'n | Mon Feb 28 08:00:00 IST 2011 | Mon Feb 28 08:00:00 IST 2011
1555 | Complete Removal of 3 nos. Existing Piles | Wed Sep 07 17:00:00 IDT 2011 | Wed Sep 07 17:00:00 IDT 2011
1556 | Complete 10% Mini-piles for Lai Chi Kok Overpass | Wed Aug 31 08:00:00 IDT 2011 | Wed Aug 31 08:00:00 IDT 2011
1557 | Complete Backfilling Works for Demolished FMO Maket Pier B | Sun Jan 15 08:00:00 IST 2012 | Sun Jan 15 08:00:00 IST 2012
1558 | Removal of Obstruction Piles for Demolished Sham Shui Po Pier (DT) | Tue Nov 13 17:00:00 IST 2012 | Tue Nov 13 17:00:00 IST 2012
1559 | Removal of Obstruction Piles for Old Cheung Sha Wan Cargo Pier(DT) | Fri Aug 31 08:00:00 IDT 2012 | Fri Aug 31 08:00:00 IDT 2012
1560 | Complete Reinstatement of TWL Sump | Tue Jan 15 17:00:00 IST 2013 | Tue Jan 15 17:00:00 IST 2013
1561 | Complete U/G Services & Reinstatement for Lai Chi Kok Overpass | Sun Sep 29 17:00:00 IDT 2013 | Sun Sep 29 17:00:00 IDT 2013
1562 | Complete All Works | Sun May 10 17:00:00 IDT 2015 | Sun May 10 17:00:00 IDT 2015
1563 | F1 Complete TWL New Sump Provision | Mon Feb 28 08:00:00 IST 2011 | Mon Jul 29 17:00:00 IDT 2013
1564 | Method Statement Submission and Approval | Mon May 16 08:00:00 IDT 2011 | Fri Nov 25 17:00:00 IST 2011
1565 | MS Preparation for TWL Sump Pit Modification | Mon May 16 08:00:00 IDT 2011 | Wed Oct 12 17:00:00 IST 2011
1566 | MS Submission to MTR | Wed Aug 31 08:00:00 IDT 2011 | Wed Aug 31 08:00:00 IDT 2011
1567 | MS Comment by MTR | Wed Aug 31 08:00:00 IDT 2011 | Tue Sep 27 17:00:00 IDT 2011
1568 | MS Re-submission Preparation | Wed Aug 31 08:00:00 IDT 2011 | Wed Sep 14 17:00:00 IDT 2011
1569 | MS Comment & Approval by MTR | Wed Aug 31 08:00:00 IDT 2011 | Tue Sep 27 17:00:00 IDT 2011
1570 | Issue for Construction | Fri Nov 25 17:00:00 IST 2011 | Fri Nov 25 17:00:00 IST 2011
1571 | Design Submission & Approval | Mon Feb 28 08:00:00 IST 2011 | Fri Oct 21 17:00:00 IST 2011
1572 | AIP Submission of Temp.& Permanent Sump Modification | Wed Jun 08 08:00:00 IDT 2011 | Thu Jul 07 17:00:00 IDT 2011
1573 | MTR's Comment for AIP of Temp.& Permanent Sump Modification | Mon Feb 28 08:00:00 IST 2011 | Sat Mar 12 17:00:00 IST 2011
1574 | AIP Re-submission of Temp.&Permanent Sump Modification | Mon Feb 28 08:00:00 IST 2011 | Wed Mar 30 17:00:00 IST 2011
1575 | MTR's Comment & Approval for AIP of Temp.Work Design for Sump Modification | Mon Feb 28 08:00:00 IST 2011 | Sun Jul 17 17:00:00 IDT 2011
1576 | DDA Submission of Temp.Shaft Design | Wed Jun 08 08:00:00 IDT 2011 | Wed Jul 06 17:00:00 IDT 2011
1577 | MTR's Comment & Approval for DDA of Temp.Shaft Design | Mon Feb 28 08:00:00 IST 2011 | Mon Aug 01 17:00:00 IDT 2011
1578 | DDA Submission of Permanent Sump Modification | Wed Aug 31 08:00:00 IDT 2011 | Wed Sep 28 17:00:00 IDT 2011
1579 | MTR's Comment & Approval for DDA of Permanent Sump Modification | Thu Sep 29 08:00:00 IDT 2011 | Fri Oct 21 17:00:00 IST 2011
1580 | AIP Submission of TWL Protection Works | Wed May 25 08:00:00 IDT 2011 | Tue Jun 21 17:00:00 IDT 2011
1581 | MTR's Comment for AIP of TWL Protection Works | Mon Feb 28 08:00:00 IST 2011 | Sun Mar 13 17:00:00 IST 2011
1582 | 1st AIP Re-submission of TWL Protection Works | Mon Feb 28 08:00:00 IST 2011 | Tue Mar 29 17:00:00 IST 2011
1583 | MTR's Comment & Approval for 1st AIP of TWL Protection Works | Mon Feb 28 08:00:00 IST 2011 | Tue Mar 22 17:00:00 IST 2011
1584 | 2nd AIP Re-submission of TWL Protection Works | Mon Feb 28 08:00:00 IST 2011 | Wed Jul 20 17:00:00 IDT 2011
1585 | MTR's Approval for 2nd AIP of TWL Protection Works | Thu Sep 01 08:00:00 IDT 2011 | Wed Sep 28 17:00:00 IDT 2011
1586 | DDA Submission of TWL Protection Works | Wed Aug 31 08:00:00 IDT 2011 | Wed Sep 28 17:00:00 IDT 2011
1587 | MTR's Approval for DDA of TWL Protection Works | Wed Aug 31 08:00:00 IDT 2011 | Tue Sep 27 17:00:00 IDT 2011
1588 | EDOC (TWL) Submission of Temp.Sump Modification | Wed Jun 08 08:00:00 IDT 2011 | Fri Jul 08 17:00:00 IDT 2011
1589 | MTR's Comment for EDOC (TWL)Temp.Sump Modification | Mon Feb 28 08:00:00 IST 2011 | Wed Mar 23 17:00:00 IST 2011
1590 | EDOC (TWL) Re-submission of Temp.Sump Modification | Mon Feb 28 08:00:00 IST 2011 | Wed May 11 17:00:00 IDT 2011
1591 | MTR's Comment & Approval for EDOC of Temp.Work Design for Sump Modification | Mon Feb 28 08:00:00 IST 2011 | Sun Jul 17 17:00:00 IDT 2011
1592 | EDOC (TWL) Submission of Protection Works | Wed Jun 08 08:00:00 IDT 2011 | Fri Jul 08 17:00:00 IDT 2011
1593 | MTR's Comment for EDOC (TWL) Protection Works | Mon Feb 28 08:00:00 IST 2011 | Sat Sep 24 17:00:00 IDT 2011
1594 | EDOC (TWL) Re-submission of Protection Works | Wed Aug 31 08:00:00 IDT 2011 | Thu Sep 29 17:00:00 IDT 2011
1595 | MTR's Comment & Approval for EDOC of Protection Works | Wed Aug 31 08:00:00 IDT 2011 | Fri Sep 23 17:00:00 IDT 2011
1596 | Circular Shaft Construction | Mon Feb 28 08:00:00 IST 2011 | Wed Jan 16 17:00:00 IST 2013
1597 | Area 37.3 Tree Transplant by 801 Designated Contrator | Mon Feb 28 08:00:00 IST 2011 | Mon Feb 28 08:00:00 IST 2011
1598 | Site Possession (Area 10.3) | Mon Mar 28 08:00:00 IST 2011 | Mon Mar 28 08:00:00 IST 2011
1599 | Set-up Plan & Hoarding Plan Submn & Approval | Mon Feb 28 08:00:00 IST 2011 | Tue Apr 12 17:00:00 IDT 2011
1600 | Site Setup & Hoarding Erection | Mon Feb 28 08:00:00 IST 2011 | Tue Mar 22 17:00:00 IST 2011
1601 | Install Instruments/Monitoring Stations | Mon Feb 28 08:00:00 IST 2011 | Sat Mar 19 17:00:00 IST 2011
1602 | Trial Trench to Locate Exist'g 400kV & StormDrain | Mon Mar 21 08:00:00 IST 2011 | Tue Apr 12 17:00:00 IDT 2011
1603 | Protection for 400kV & 600 dia.Storm Drain | Tue Jul 19 08:00:00 IDT 2011 | Sat Aug 20 17:00:00 IDT 2011
1604 | Drilling for Jet Grouting | Mon Aug 08 08:00:00 IDT 2011 | Thu Oct 27 17:00:00 IST 2011
1605 | Ground Treatment by Jet Grout | Wed Aug 31 08:00:00 IDT 2011 | Fri Sep 30 17:00:00 IDT 2011
1606 | Drilling for Fissure Grout | Wed Aug 31 08:00:00 IDT 2011 | Thu Sep 29 17:00:00 IDT 2011
1607 | Ground Treatment by Fissure Grout | Wed Aug 31 08:00:00 IDT 2011 | Wed Sep 28 17:00:00 IDT 2011
1608 | Bored Pile | Mon Jan 16 08:00:00 IST 2012 | Sat Feb 18 17:00:00 IST 2012
1609 | Install Internal Casing | Mon Jan 16 08:00:00 IST 2012 | Fri Jan 27 17:00:00 IST 2012
1610 | Concrete Water Plug | Mon Jan 16 08:00:00 IST 2012 | Tue Jan 17 17:00:00 IST 2012
1611 | Grouting & Extract External Casing | Mon Jan 16 08:00:00 IST 2012 | Tue Jan 17 17:00:00 IST 2012
1612 | Dewatering/ Pumping System | Mon Jan 16 08:00:00 IST 2012 | Fri Jan 20 17:00:00 IST 2012
1613 | Ventilation, Lighting System | Mon Jan 16 08:00:00 IST 2012 | Fri Jan 20 17:00:00 IST 2012
1614 | Setup Access Shaft | Mon Jan 16 08:00:00 IST 2012 | Fri Jan 20 17:00:00 IST 2012
1615 | Circular Shaft Const'n & Install Temp.Pumping System | Mon Aug 15 08:00:00 IDT 2011 | Wed Jan 16 17:00:00 IST 2013
1616 | Adit Construction | Mon Jan 16 08:00:00 IST 2012 | Tue Oct 09 17:00:00 IST 2012
1617 | Post Form Adit Opening | Mon Jan 16 08:00:00 IST 2012 | Fri Jan 20 17:00:00 IST 2012
1618 | Adit Excavation | Mon Jan 16 08:00:00 IST 2012 | Wed Feb 29 17:00:00 IST 2012
1619 | Lining for Adit | Wed Oct 03 08:00:00 IST 2012 | Tue Oct 09 17:00:00 IST 2012
1620 | Construction of Pipe Canopy | Wed Oct 10 08:00:00 IST 2012 | Fri Dec 21 17:00:00 IST 2012
1621 | Concrete Coring & Saw Cut for Sump Pit Wall | Wed Oct 10 08:00:00 IST 2012 | Tue Oct 16 17:00:00 IST 2012
1622 | Erection Temp. Props Support | Wed Oct 17 08:00:00 IST 2012 | Thu Oct 18 17:00:00 IST 2012
1623 | Enlarge Sump Pit Opening | Fri Oct 19 08:00:00 IST 2012 | Mon Oct 22 17:00:00 IST 2012
1624 | Erect Temporary Props | Wed Oct 24 08:00:00 IST 2012 | Tue Oct 30 17:00:00 IST 2012
1625 | Setup Pumping System | Wed Oct 31 08:00:00 IST 2012 | Tue Nov 06 17:00:00 IST 2012
1626 | Remove Existing Pumping System | Wed Nov 07 08:00:00 IST 2012 | Thu Nov 08 17:00:00 IST 2012
1627 | Mass Concrete for Drilling rig Platform | Fri Nov 09 08:00:00 IST 2012 | Mon Nov 12 17:00:00 IST 2012
1628 | Delivery and Setup Drillilng Rig | Tue Nov 13 08:00:00 IST 2012 | Mon Nov 19 17:00:00 IST 2012
1629 | Construction of Pipe Canopy | Tue Nov 20 08:00:00 IST 2012 | Fri Dec 21 17:00:00 IST 2012
1630 | Pipe Canopy Construction | Wed Oct 10 08:00:00 IST 2012 | Fri Dec 21 17:00:00 IST 2012
1631 | Modification of Existing Sump | Sat Dec 22 08:00:00 IST 2012 | Tue Jan 15 17:00:00 IST 2013
1632 | Strengthen Adit & Sump Opening Connection | Sat Dec 22 08:00:00 IST 2012 | Sat Dec 29 17:00:00 IST 2012
1633 | Install Prop above Slab Cut Line | Sat Dec 22 08:00:00 IST 2012 | Mon Dec 24 17:00:00 IST 2012
1634 | Saw Cut Pit Wall above Base Slab | Thu Dec 27 08:00:00 IST 2012 | Wed Jan 02 17:00:00 IST 2013
1635 | RC Base Slab Construction | Thu Jan 03 08:00:00 IST 2013 | Tue Jan 15 17:00:00 IST 2013
1636 | Modification of Existing Sump | Sat Dec 22 08:00:00 IST 2012 | Tue Jan 15 17:00:00 IST 2013
1637 | Reinstatement | Tue Nov 06 08:00:00 IST 2012 | Mon Apr 08 17:00:00 IDT 2013
1638 | Make Good Pit Wall | Wed Jan 16 08:00:00 IST 2013 | Tue Jan 22 17:00:00 IST 2013
1639 | GI at Sump Pit for TWL | Wed Jan 23 08:00:00 IST 2013 | Mon Feb 04 17:00:00 IST 2013
1640 | Reinstate Permanent Pump system | Tue Feb 05 08:00:00 IST 2013 | Tue Mar 05 17:00:00 IST 2013
1641 | Reinstate Pit Wall | Wed Mar 06 08:00:00 IST 2013 | Mon Mar 18 17:00:00 IST 2013
1642 | Backfill Adit & Shaft by Lean Concrete | Tue Nov 06 08:00:00 IST 2012 | Wed Nov 21 17:00:00 IST 2012
1643 | TWL Reinstatement | Wed Jan 16 08:00:00 IST 2013 | Mon Apr 08 17:00:00 IDT 2013
1644 | Completion | Tue Jul 02 08:00:00 IDT 2013 | Mon Jul 29 17:00:00 IDT 2013
1645 | Prepare & Submit Draft As-built Drawings | Tue Jul 02 08:00:00 IDT 2013 | Mon Jul 29 17:00:00 IDT 2013
1646 | Prepare & Submit As-built Drawings | Tue Jul 02 08:00:00 IDT 2013 | Mon Jul 29 17:00:00 IDT 2013
1647 | F2 Complete Lai Chi Kok Overpass New Concrete Beam | Mon Feb 28 08:00:00 IST 2011 | Wed Sep 25 17:00:00 IDT 2013
1648 | Method Statement Submission and Approval | Sun Jun 19 08:00:00 IDT 2011 | Tue Oct 04 17:00:00 IST 2011
1649 | MS Preparation for Underpinning | Sun Jun 19 08:00:00 IDT 2011 | Tue Oct 04 17:00:00 IST 2011
1650 | MS Submission to MTR/DSD | Wed Aug 31 08:00:00 IDT 2011 | Wed Aug 31 08:00:00 IDT 2011
1651 | MS Comment by MTR | Wed Aug 31 08:00:00 IDT 2011 | Fri Sep 23 17:00:00 IDT 2011
1652 | MS Re-submission Preparation | Wed Aug 31 08:00:00 IDT 2011 | Thu Sep 29 17:00:00 IDT 2011
1653 | MS Comment & Approval by MTR | Wed Aug 31 08:00:00 IDT 2011 | Tue Sep 27 17:00:00 IDT 2011
1654 | Issue for Construction | Wed Sep 28 17:00:00 IDT 2011 | Wed Sep 28 17:00:00 IDT 2011
1655 | TTM Scheme Submission & Approval | Mon Feb 28 08:00:00 IST 2011 | Thu Sep 29 17:00:00 IDT 2011
1656 | Prepare Temporary Traffic Management | Mon Feb 28 08:00:00 IST 2011 | Fri Mar 25 17:00:00 IST 2011
1657 | TTM reviewed by SLG | Sat Mar 26 08:00:00 IST 2011 | Sat Jun 18 17:00:00 IDT 2011
1658 | Resubmit TTM | Tue Jun 21 08:00:00 IDT 2011 | Mon Jun 27 17:00:00 IDT 2011
1659 | TTM reviewed by SLG | Tue Jun 28 08:00:00 IDT 2011 | Wed Jul 27 17:00:00 IDT 2011
1660 | Notification to RMO | Tue Jul 26 08:00:00 IDT 2011 | Mon Aug 01 17:00:00 IDT 2011
1661 | XP Application & Approval | Thu Jun 02 08:00:00 IDT 2011 | Fri Jun 17 17:00:00 IDT 2011
1662 | Implement TTM | Fri Aug 12 17:00:00 IDT 2011 | Fri Aug 12 17:00:00 IDT 2011
1663 | Traffic Diversion Works | Sat Aug 13 08:00:00 IDT 2011 | Thu Sep 29 17:00:00 IDT 2011
1664 | Design Submission & Approval | Mon Feb 28 08:00:00 IST 2011 | Wed Oct 12 17:00:00 IST 2011
1665 | Site Investigation | Wed Jun 01 08:00:00 IDT 2011 | Wed Oct 12 17:00:00 IST 2011
1666 | Prepare Temp.Work Design for Underpinning | Mon Feb 28 08:00:00 IST 2011 | Tue Jul 26 17:00:00 IDT 2011
1667 | Comment for Temp.Work Design Submission | Sun Jun 19 08:00:00 IDT 2011 | Thu Jul 07 17:00:00 IDT 2011
1668 | Proposed Temp.Work Design Re-submission | Wed Aug 31 08:00:00 IDT 2011 | Tue Sep 06 17:00:00 IDT 2011
1669 | Proposed Temp.Work Design Approval | Wed Aug 31 08:00:00 IDT 2011 | Wed Sep 21 17:00:00 IDT 2011
1670 | Utilities Coordination | Mon Feb 28 08:00:00 IST 2011 | Tue Jan 31 17:00:00 IST 2012
1671 | Prepare & Submit Utilities Diversion Scheme | Mon Feb 28 08:00:00 IST 2011 | Thu Mar 31 17:00:00 IST 2011
1672 | Comment of Utilities Diversion Scheme | Fri Apr 01 08:00:00 IDT 2011 | Mon May 23 17:00:00 IDT 2011
1673 | Utilities Diversion Scheme Re-submission | Fri Apr 29 08:00:00 IDT 2011 | Tue Jan 31 17:00:00 IST 2012
1674 | Utilities Diversion Scheme Approval | Wed Aug 31 08:00:00 IDT 2011 | Tue Sep 27 17:00:00 IDT 2011
1675 | Preparation Excavation Permit | Mon Apr 11 08:00:00 IDT 2011 | Fri Jun 17 17:00:00 IDT 2011
1676 | Excavation Permit Issue | Mon Jun 13 08:00:00 IDT 2011 | Mon Jun 13 08:00:00 IDT 2011
1677 | Site Possession Application | Mon Feb 28 08:00:00 IST 2011 | Tue Mar 29 17:00:00 IST 2011
1678 | Prepare Site Possession to SLG | Mon Feb 28 08:00:00 IST 2011 | Wed Mar 09 17:00:00 IST 2011
1679 | SLG Comments and Approval | Mon Feb 28 08:00:00 IST 2011 | Tue Mar 29 17:00:00 IST 2011
1680 | Site Possession | Mon Feb 28 08:00:00 IST 2011 | Mon Feb 28 08:00:00 IST 2011
1681 | Utilities Diversion | Wed Aug 31 08:00:00 IDT 2011 | Mon Feb 13 17:00:00 IST 2012
1682 | Trial Trench & Record | Wed Aug 31 08:00:00 IDT 2011 | Fri Sep 23 17:00:00 IDT 2011
1683 | Permanently Divert Existing Storm Drain (SD201-SD205) | Sat Sep 24 08:00:00 IDT 2011 | Mon Nov 21 17:00:00 IST 2011
1684 | Permanently Divert Existing DN150 (FW201) | Tue Nov 22 08:00:00 IST 2011 | Mon Dec 19 17:00:00 IST 2011
1685 | Temp. Relocation of Fire Hydrant (FH1643) | Tue Dec 20 08:00:00 IST 2011 | Thu Jan 12 17:00:00 IST 2012
1686 | Temp.Slew 3nos. 400kV Cable w/Temp.Support (CLP201) | Fri Jan 13 08:00:00 IST 2012 | Mon Feb 13 17:00:00 IST 2012
1687 | Utilities Diversion | Wed Aug 31 08:00:00 IDT 2011 | Wed Aug 31 08:00:00 IDT 2011
1688 | Underpinning Works for Pile Cap at Grid 3 | Mon Feb 28 08:00:00 IST 2011 | Mon Sep 16 17:00:00 IDT 2013
1689 | Tree Transplant (by 801) | Mon Feb 28 08:00:00 IST 2011 | Mon Mar 14 17:00:00 IST 2011
1690 | Site Mobilization | Sat Sep 24 08:00:00 IDT 2011 | Fri Sep 30 17:00:00 IDT 2011
1691 | Const.Raking Mini-piles 23 nos. | Wed Aug 31 08:00:00 IDT 2011 | Fri Dec 16 17:00:00 IST 2011
1692 | Sheetpile Driving | Mon Jan 16 08:00:00 IST 2012 | Wed Feb 01 17:00:00 IST 2012
1693 | Waling Installation | Mon Jan 16 08:00:00 IST 2012 | Sat Jan 21 17:00:00 IST 2012
1694 | Excavation to FormationLevel(Underneath Exist'gPileCap) | Mon Jan 16 08:00:00 IST 2012 | Sat Jan 28 17:00:00 IST 2012
1695 | Pile Head Exposure | Mon Jan 16 08:00:00 IST 2012 | Wed Feb 15 17:00:00 IST 2012
1696 | Pile Cap & Column Construction | Mon Jan 16 08:00:00 IST 2012 | Tue Jan 31 17:00:00 IST 2012
1697 | Portal Beam Construction | Fri Aug 31 08:00:00 IDT 2012 | Thu Sep 06 17:00:00 IDT 2012
1698 | Concrete Curing | Fri Sep 07 08:00:00 IDT 2012 | Sat Oct 20 17:00:00 IST 2012
1699 | Install Shear Key | Sat Oct 20 08:00:00 IST 2012 | Mon Oct 29 17:00:00 IST 2012
1700 | Install Flat Jack | Sat Oct 20 08:00:00 IST 2012 | Mon Nov 12 17:00:00 IST 2012
1701 | Load Transfer | Tue Nov 13 08:00:00 IST 2012 | Mon Dec 03 17:00:00 IST 2012
1702 | Disconnect Existing Pier | Mon Dec 03 08:00:00 IST 2012 | Sat Dec 22 17:00:00 IST 2012
1703 | Adjust Jacking Force | Fri Aug 31 08:00:00 IDT 2012 | Fri Sep 14 17:00:00 IDT 2012
1704 | Infill grout for pier head and existing pile cap | Mon Sep 24 08:00:00 IST 2012 | Sat Sep 29 17:00:00 IST 2012
1705 | Backfilling & Reinstatement | Mon Sep 02 08:00:00 IDT 2013 | Mon Sep 16 17:00:00 IDT 2013
1706 | Grid 3 Underpinning, Loading Transfer & Disconnection (DT) | Sat Sep 24 08:00:00 IDT 2011 | Tue Jul 03 17:00:00 IDT 2012
1707 | Underpinning Works for Pile Cap at Grid 2 | Mon Jan 16 08:00:00 IST 2012 | Mon Sep 16 17:00:00 IDT 2013
1708 | Const.Raking Mini-piles 21nos. | Mon Jan 16 08:00:00 IST 2012 | Fri May 11 17:00:00 IDT 2012
1709 | Sheetpile Driving | Mon Jan 16 08:00:00 IST 2012 | Wed Feb 01 17:00:00 IST 2012
1710 | Waling Installation | Mon Jan 16 08:00:00 IST 2012 | Sat Jan 21 17:00:00 IST 2012
1711 | Excavation | Mon Jan 16 08:00:00 IST 2012 | Sat Jan 28 17:00:00 IST 2012
1712 | Pile Head Exposure | Sat Jan 28 08:00:00 IST 2012 | Fri Feb 24 17:00:00 IST 2012
1713 | Pile Cap Construciton | Mon Jan 16 08:00:00 IST 2012 | Wed Feb 01 17:00:00 IST 2012
1714 | Coulumns Construction (2nos.) | Mon Jan 16 08:00:00 IST 2012 | Mon Jan 30 17:00:00 IST 2012
1715 | Falsework Erection | Tue Sep 11 08:00:00 IDT 2012 | Fri Sep 21 17:00:00 IDT 2012
1716 | Portal Beam Construction | Fri Sep 21 08:00:00 IDT 2012 | Sat Oct 06 17:00:00 IST 2012
1717 | Concrete Curing | Sat Oct 06 08:00:00 IST 2012 | Fri Oct 19 17:00:00 IST 2012
1718 | Install Shear Key | Sat Oct 20 08:00:00 IST 2012 | Sat Oct 27 17:00:00 IST 2012
1719 | Install Flat Jack | Sat Oct 27 08:00:00 IST 2012 | Fri Nov 16 17:00:00 IST 2012
1720 | Load Transfer | Fri Nov 16 08:00:00 IST 2012 | Thu Dec 06 17:00:00 IST 2012
1721 | Disconnect Existing pier | Thu Dec 06 08:00:00 IST 2012 | Fri Dec 28 17:00:00 IST 2012
1722 | Adjust Jacking Force | Fri Aug 31 08:00:00 IDT 2012 | Fri Sep 14 17:00:00 IDT 2012
1723 | Infill grout for pier head and existing pile cap | Mon Sep 24 08:00:00 IST 2012 | Sat Sep 29 17:00:00 IST 2012
1724 | Backfilling & Reinstatement | Mon Sep 02 08:00:00 IDT 2013 | Mon Sep 16 17:00:00 IDT 2013
1725 | Grid 2 Underpinning,Loading Transfer & Disconnection (UT) | Mon Jan 16 08:00:00 IST 2012 | Wed Aug 08 17:00:00 IDT 2012
1726 | Underpinning Works for Pile Cap at Grid 1 | Mon Jan 16 08:00:00 IST 2012 | Wed Sep 25 17:00:00 IDT 2013
1727 | Const piles | Mon Jan 16 08:00:00 IST 2012 | Tue May 15 17:00:00 IDT 2012
1728 | Loading Test | Mon Jan 16 08:00:00 IST 2012 | Wed Feb 15 17:00:00 IST 2012
1729 | Sheetpile Driving | Mon Jan 16 08:00:00 IST 2012 | Tue Feb 14 17:00:00 IST 2012
1730 | Waling Installation | Mon Jan 16 08:00:00 IST 2012 | Wed Feb 08 17:00:00 IST 2012
1731 | Excavation | Fri Aug 31 08:00:00 IDT 2012 | Fri Sep 14 17:00:00 IDT 2012
1732 | Shotcrete | Sat Sep 15 08:00:00 IDT 2012 | Tue Oct 09 17:00:00 IST 2012
1733 | Pile Head Exposure | Wed Oct 10 08:00:00 IST 2012 | Wed Nov 07 17:00:00 IST 2012
1734 | Pile Cap & Cantilever Corbel Construction | Thu Nov 08 08:00:00 IST 2012 | Wed Dec 05 17:00:00 IST 2012
1735 | Concrete Curing (28d) | Wed Dec 05 08:00:00 IST 2012 | Tue Jan 01 17:00:00 IST 2013
1736 | Install Flat Jack | Wed Jan 02 08:00:00 IST 2013 | Tue Jan 22 17:00:00 IST 2013
1737 | Load Transfer | Tue Jan 22 08:00:00 IST 2013 | Thu Jan 31 17:00:00 IST 2013
1738 | Disconnect Existing Piles 6nos. | Thu Jan 31 08:00:00 IST 2013 | Sat Mar 02 17:00:00 IST 2013
1739 | Adjust Jacking Force | Sat Mar 02 08:00:00 IST 2013 | Fri Mar 22 17:00:00 IST 2013
1740 | Cast remaining part of pile cap | Sat Mar 23 08:00:00 IST 2013 | Thu Apr 18 17:00:00 IDT 2013
1741 | Backfilling & Reinstatement | Mon Sep 02 08:00:00 IDT 2013 | Wed Sep 25 17:00:00 IDT 2013
1742 | Grid 1 Underpinning,Loading Transfer & Disconnection (UT) | Mon Jan 16 08:00:00 IST 2012 | Wed Aug 01 17:00:00 IDT 2012
1743 | Completion | Tue Mar 06 08:00:00 IST 2012 | Mon Apr 02 17:00:00 IDT 2012
1744 | Prepare & Submit Draft As-built Drawings | Tue Mar 06 08:00:00 IST 2012 | Mon Apr 02 17:00:00 IDT 2012
1745 | Prepare & Submit As-built Drawings | Tue Mar 06 08:00:00 IST 2012 | Mon Apr 02 17:00:00 IDT 2012
1746 | RD1 Pile Removal | Mon Jan 16 08:00:00 IST 2012 | Fri Feb 03 17:00:00 IST 2012
1747 | RD1 Parallel Seismic | Mon Jan 16 08:00:00 IST 2012 | Tue Jan 17 17:00:00 IST 2012
1748 | Issuance of EI21 - Additional Investigation Drill hole above Nullah Deck at LCK | Mon Jan 16 17:00:00 IST 2012 | Mon Jan 16 17:00:00 IST 2012
1749 | Pile A - 1st Investigation Campaign | Mon Jan 16 08:00:00 IST 2012 | Thu Jan 19 17:00:00 IST 2012
1750 | Issuance of EI24 - Additional Investigation Drillhole at existing pile above Nullah Deck at LCK | Mon Jan 16 17:00:00 IST 2012 | Mon Jan 16 17:00:00 IST 2012
1751 | Pile B - 1st Investigation Campaign | Mon Jan 16 08:00:00 IST 2012 | Tue Jan 17 17:00:00 IST 2012
1752 | Issuance of EI31 - Additional attempts of vertical drillholes and inclined drillholes at existing Pile of RD1 | Mon Jan 16 17:00:00 IST 2012 | Mon Jan 16 17:00:00 IST 2012
1753 | Pile B - 2nd Investigation Campaign | Mon Jan 16 08:00:00 IST 2012 | Sat Jan 21 17:00:00 IST 2012
1754 | Pile B - 3rd Investigation Campaign (inclined holes) | Mon Jan 16 08:00:00 IST 2012 | Fri Feb 03 17:00:00 IST 2012
1755 | F3 Ground Treatment Works for HKIVE (Haking Wong) School | Wed Aug 31 08:00:00 IDT 2011 | Wed Oct 31 17:00:00 IST 2012
1756 | Method Statement Submission and Approval | Wed Aug 31 08:00:00 IDT 2011 | Wed Sep 28 17:00:00 IDT 2011
1757 | MS Preparation | Wed Aug 31 08:00:00 IDT 2011 | Fri Sep 23 17:00:00 IDT 2011
1758 | MS Submission to MTR | Wed Aug 31 08:00:00 IDT 2011 | Wed Aug 31 08:00:00 IDT 2011
1759 | MS Comment by MTR | Wed Aug 31 08:00:00 IDT 2011 | Tue Sep 27 17:00:00 IDT 2011
1760 | MS Re-submission Preparation | Wed Aug 31 08:00:00 IDT 2011 | Wed Sep 28 17:00:00 IDT 2011
1761 | MS Comment & Approval by MTR | Wed Aug 31 08:00:00 IDT 2011 | Tue Sep 27 17:00:00 IDT 2011
1762 | Issue for Construction | Wed Aug 31 08:00:00 IDT 2011 | Wed Aug 31 08:00:00 IDT 2011
1763 | Construction | Sun Jan 15 08:00:00 IST 2012 | Wed Oct 31 17:00:00 IST 2012
1764 | Access for HKIVE | Sun Jan 15 08:00:00 IST 2012 | Sun Jan 15 08:00:00 IST 2012
1765 | Site Preparation | Mon Jan 16 08:00:00 IST 2012 | Sat Jan 21 17:00:00 IST 2012
1766 | Sleeve Pipe Installation and Verticality Check | Mon Jan 16 08:00:00 IST 2012 | Fri Feb 10 17:00:00 IST 2012
1767 | Set up Grouting Machine | Mon Jan 16 08:00:00 IST 2012 | Wed Jan 18 17:00:00 IST 2012
1768 | Jet Grouting for HKIVE (Haking Wong) School | Mon Jan 16 08:00:00 IST 2012 | Fri Feb 10 17:00:00 IST 2012
1769 | De-mobilization | Fri Aug 31 08:00:00 IDT 2012 | Fri Sep 14 17:00:00 IDT 2012
1770 | Reinstatment (subjected to IVE) | Sat Sep 15 08:00:00 IDT 2012 | Wed Oct 31 17:00:00 IST 2012
1771 | F4 Cheung Sha Wan Cargo Pier-Remvoe Obstruct Pile | Sat Jan 08 08:00:00 IST 2011 | Wed May 08 17:00:00 IDT 2013
1772 | Method Statement Submission and Approval | Mon Feb 28 08:00:00 IST 2011 | Tue Jun 21 17:00:00 IDT 2011
1773 | MS Preparation | Mon Feb 28 08:00:00 IST 2011 | Tue Apr 05 17:00:00 IDT 2011
1774 | MS Submission to MTR | Wed Mar 23 17:00:00 IST 2011 | Wed Mar 23 17:00:00 IST 2011
1775 | MS Comment by MTR | Thu Mar 24 08:00:00 IST 2011 | Wed Apr 20 17:00:00 IDT 2011
1776 | MS Re-submission Preparation | Thu Apr 21 08:00:00 IDT 2011 | Sat May 14 17:00:00 IDT 2011
1777 | MS Comment & Approval by MTR | Wed May 25 08:00:00 IDT 2011 | Wed Jun 15 17:00:00 IDT 2011
1778 | Issue for Construction | Tue Jun 21 17:00:00 IDT 2011 | Tue Jun 21 17:00:00 IDT 2011
1779 | TTM Scheme Submission & Approval | Sat Jan 08 08:00:00 IST 2011 | Sun Aug 14 17:00:00 IDT 2011
1780 | Prepare TTM for footpah closure | Sat Jan 08 08:00:00 IST 2011 | Mon Feb 07 17:00:00 IST 2011
1781 | TTM Comment & Approval by Relevant Authorities | Sat Feb 12 08:00:00 IST 2011 | Sun Apr 10 17:00:00 IDT 2011
1782 | Notification to RMO | Mon Feb 28 08:00:00 IST 2011 | Sun Mar 06 17:00:00 IST 2011
1783 | XP Application & Approval | Mon Feb 28 08:00:00 IST 2011 | Wed Apr 06 17:00:00 IDT 2011
1784 | Implement TTM (Footpath) | Wed May 18 17:00:00 IDT 2011 | Wed May 18 17:00:00 IDT 2011
1785 | Prepare Temporary Traffic Management | Mon Feb 28 08:00:00 IST 2011 | Thu Mar 24 17:00:00 IST 2011
1786 | TTM reviewed by SLG | Sun Mar 27 08:00:00 IST 2011 | Mon May 23 17:00:00 IDT 2011
1787 | XP Application & Approval | Sat Apr 23 08:00:00 IDT 2011 | Fri Apr 29 17:00:00 IDT 2011
1788 | Notification to RMO | Tue Aug 09 08:00:00 IDT 2011 | Sun Aug 14 17:00:00 IDT 2011
1789 | Implement TTM (Road) | Wed Jul 06 17:00:00 IDT 2011 | Wed Jul 06 17:00:00 IDT 2011
1790 | Utilities Diversion (DT) | Sat Jan 29 08:00:00 IST 2011 | Mon Oct 17 17:00:00 IST 2011
1791 | Implement TTM | Sat Jan 29 08:00:00 IST 2011 | Wed Mar 09 17:00:00 IST 2011
1792 | Trial Trench to Expose Pile Head & Utilities | Tue Jun 21 08:00:00 IDT 2011 | Fri Jul 22 17:00:00 IDT 2011
1793 | Divert Existing 1400D Watermain (FW204) | Tue Jun 21 08:00:00 IDT 2011 | Wed Sep 07 17:00:00 IDT 2011
1794 | Divert 450D Saltwater Main (SW201) | Tue Jun 21 08:00:00 IDT 2011 | Mon Jul 18 17:00:00 IDT 2011
1795 | Divert 1200D Stormwater Main (SD207) | Wed Aug 31 08:00:00 IDT 2011 | Mon Oct 17 17:00:00 IST 2011
1796 | Divert 225D Stormwater Drain (SD208) | Tue Jun 21 08:00:00 IDT 2011 | Fri Aug 26 17:00:00 IDT 2011
1797 | Stage 1 | Sat Jan 08 08:00:00 IST 2011 | Mon Mar 19 17:00:00 IST 2012
1798 | Access Date for Works Area 11.22 | Mon Feb 28 08:00:00 IST 2011 | Mon Feb 28 08:00:00 IST 2011
1799 | Tree Transplant Complete by 801 Designated Contractor | Mon Feb 28 08:00:00 IST 2011 | Mon Feb 28 08:00:00 IST 2011
1800 | Survey Existing Piles & Underground Utilities | Sat Jan 08 08:00:00 IST 2011 | Fri May 13 17:00:00 IDT 2011
1801 | Expose the Existing Pile Head | Sat May 21 08:00:00 IDT 2011 | Fri Nov 25 17:00:00 IST 2011
1802 | Expose and Verification of Pile 24E (DT) | Fri Jan 20 08:00:00 IST 2012 | Sat Jan 28 17:00:00 IST 2012
1803 | Remove Existing Vertical Pile 24H (DT) | Tue Jun 21 08:00:00 IDT 2011 | Mon Aug 29 17:00:00 IDT 2011
1804 | Backfill Existing Pile 24H | Sat Jul 16 08:00:00 IDT 2011 | Thu Jul 21 17:00:00 IDT 2011
1805 | Remove Existing Raking Pile 24G (DT) | Tue Jun 21 08:00:00 IDT 2011 | Wed Jul 27 17:00:00 IDT 2011
1806 | Backfill Existing Pile 24G | Wed Aug 31 08:00:00 IDT 2011 | Fri Sep 02 17:00:00 IDT 2011
1807 | Remove Existing Raking Pile 23F (DT) | Wed Aug 31 08:00:00 IDT 2011 | Fri Oct 07 17:00:00 IST 2011
1808 | Backfill Existing Pile 23F | Fri Jan 27 08:00:00 IST 2012 | Sat Jan 28 17:00:00 IST 2012
1809 | Remove Existing Vertical Pile 23E (DT) | Mon Sep 12 08:00:00 IDT 2011 | Sat Jan 14 17:00:00 IST 2012
1810 | Backfill Existing Pile 23E | Tue Feb 07 08:00:00 IST 2012 | Wed Feb 08 17:00:00 IST 2012
1811 | Remove Existing Raking Pile 24F (DT) | Fri Feb 10 08:00:00 IST 2012 | Tue Mar 06 17:00:00 IST 2012
1812 | Backfill Existing Pile 24F | Sat Mar 17 08:00:00 IST 2012 | Mon Mar 19 17:00:00 IST 2012
1813 | Utilities Diversion (UT) | Sat Jan 08 08:00:00 IST 2011 | Fri Dec 21 17:00:00 IST 2012
1814 | Implement TTM (Footpath Closure) | Sat Jan 08 08:00:00 IST 2011 | Mon Feb 21 17:00:00 IST 2011
1815 | Trial Trench to Expose U/G Utilities | Tue Jun 21 08:00:00 IDT 2011 | Thu Jul 07 17:00:00 IDT 2011
1816 | Divert Existing Gas Main 315D & 400D (GAS204&205) | Wed Aug 31 08:00:00 IDT 2011 | Fri Sep 23 17:00:00 IDT 2011
1817 | Slew TelecomCable(CATV205+HGC203+WTT204+PCCW202) | Fri Jan 27 08:00:00 IST 2012 | Tue Feb 07 17:00:00 IST 2012
1818 | Slew CLP Cable (11kV-CLP213) | Fri Jan 27 08:00:00 IST 2012 | Thu Feb 09 17:00:00 IST 2012
1819 | Slew CLP Cable (400kV-CLP214) | Thu Nov 22 08:00:00 IST 2012 | Fri Dec 21 17:00:00 IST 2012
1820 | Stage 2 | Tue Jun 21 08:00:00 IDT 2011 | Wed May 08 17:00:00 IDT 2013
1821 | Remove Existing Pile 23G (UT) | Tue Jun 21 08:00:00 IDT 2011 | Mon Jul 04 17:00:00 IDT 2011
1822 | Backfill Existing Pile 23G | Wed Aug 31 08:00:00 IDT 2011 | Thu Sep 01 17:00:00 IDT 2011
1823 | Remove Existing Pile 20E (UT) | Thu Dec 13 08:00:00 IST 2012 | Fri Jan 18 17:00:00 IST 2013
1824 | Backfill Existing Pile 20E | Sat Jan 19 08:00:00 IST 2013 | Mon Jan 21 17:00:00 IST 2013
1825 | Remove Existing Pile 23H (UT) | Thu Nov 22 08:00:00 IST 2012 | Sat Dec 08 17:00:00 IST 2012
1826 | Backfill Existing Pile 23H | Mon Dec 10 08:00:00 IST 2012 | Tue Dec 11 17:00:00 IST 2012
1827 | Remove Existing Pile 21L (UT) | Sat Apr 14 08:00:00 IDT 2012 | Tue Jul 17 17:00:00 IDT 2012
1828 | Backfill Existing Pile 21L | Mon Nov 19 08:00:00 IST 2012 | Tue Nov 20 17:00:00 IST 2012
1829 | Remove Existing Pile 20J (UT) | Wed Jan 23 08:00:00 IST 2013 | Thu Feb 28 17:00:00 IST 2013
1830 | Backfill Existing Pile 20J | Fri Mar 01 08:00:00 IST 2013 | Sat Mar 02 17:00:00 IST 2013
1831 | Remove Existing Pile 19E (UT) | Tue Mar 05 08:00:00 IST 2013 | Sat Apr 13 17:00:00 IDT 2013
1832 | Backfill Existing Pile 19E | Mon Apr 15 08:00:00 IDT 2013 | Tue Apr 16 17:00:00 IDT 2013
1833 | Reinstatement of Slewed CLP Cable (400kV - CLP214) | Tue Apr 02 08:00:00 IDT 2013 | Wed May 08 17:00:00 IDT 2013
1834 | Reinstatement works
1835 | Completion | Fri Jan 13 08:00:00 IST 2012 | Mon Feb 13 17:00:00 IST 2012
1836 | Prepare & Submit Draft As-built Drawings | Fri Jan 13 08:00:00 IST 2012 | Mon Feb 13 17:00:00 IST 2012
1837 | Prepare & Submit As-built Drawings | Fri Jan 13 08:00:00 IST 2012 | Mon Feb 13 17:00:00 IST 2012
1838 | F5 Pile Removal for Demolished FMO Market Pier B | Mon Feb 28 08:00:00 IST 2011 | Thu Jun 05 17:00:00 IDT 2014
1839 | Temp. Works Design Submission | Mon Jun 20 08:00:00 IDT 2011 | Mon Jul 18 08:00:00 IDT 2011
1840 | Temp. Works Design Preparation | Mon Jun 20 08:00:00 IDT 2011 | Sun Jul 17 17:00:00 IDT 2011
1841 | Temp. Works Design Submit to MTR | Mon Jul 18 08:00:00 IDT 2011 | Mon Jul 18 08:00:00 IDT 2011
1842 | Temp. Works Design Comment by MTR | Mon Jun 20 08:00:00 IDT 2011 | Sun Jul 17 17:00:00 IDT 2011
1843 | Temp. Works Design Re-submission Preparation | Mon Jun 20 08:00:00 IDT 2011 | Mon Jul 11 17:00:00 IDT 2011
1844 | Temp. Works Design Comment & Approval by MTR | Mon Jun 20 08:00:00 IDT 2011 | Sun Jul 17 17:00:00 IDT 2011
1845 | Issue for Construction | Mon Jun 20 08:00:00 IDT 2011 | Mon Jun 20 08:00:00 IDT 2011
1846 | Method Statement Submission and Approval | Mon Feb 28 08:00:00 IST 2011 | Tue Jun 14 17:00:00 IDT 2011
1847 | MS Preparation | Mon Feb 28 08:00:00 IST 2011 | Thu Mar 31 17:00:00 IST 2011
1848 | MS Submission to MTR | Wed Mar 23 17:00:00 IST 2011 | Wed Mar 23 17:00:00 IST 2011
1849 | MS Comment by MTR | Thu Mar 24 08:00:00 IST 2011 | Sun Apr 03 17:00:00 IDT 2011
1850 | MS Re-submission Preparation | Thu Apr 21 08:00:00 IDT 2011 | Fri Apr 29 17:00:00 IDT 2011
1851 | MS Comment & Approval by MTR | Wed May 18 08:00:00 IDT 2011 | Mon May 30 17:00:00 IDT 2011
1852 | Issue for Construction | Tue Jun 14 17:00:00 IDT 2011 | Tue Jun 14 17:00:00 IDT 2011
1853 | TTM Scheme Submission & Approval | Mon Feb 28 08:00:00 IST 2011 | Sun May 29 17:00:00 IDT 2011
1854 | Prepare Temporary Traffic Management | Mon Feb 28 08:00:00 IST 2011 | Mon Mar 14 17:00:00 IST 2011
1855 | TTM reviewed by SLG | Sat Mar 26 08:00:00 IST 2011 | Sun Apr 24 17:00:00 IDT 2011
1856 | Resubmit TTM | Mon Feb 28 08:00:00 IST 2011 | Mon Feb 28 17:00:00 IST 2011
1857 | TTM reviewed by SLG | Sat Apr 30 08:00:00 IDT 2011 | Sun May 29 17:00:00 IDT 2011
1858 | Notification to RMO | Tue May 24 08:00:00 IDT 2011 | Fri May 27 17:00:00 IDT 2011
1859 | XP Application & Approval | Mon Apr 25 08:00:00 IDT 2011 | Tue May 24 17:00:00 IDT 2011
1860 | Implement TTM | Mon Feb 28 08:00:00 IST 2011 | Mon Feb 28 08:00:00 IST 2011
1861 | Construction | Mon Feb 28 08:00:00 IST 2011 | Thu Jun 05 17:00:00 IDT 2014
1862 | Acccess Dates for Works Area 11.27 | Mon Feb 28 08:00:00 IST 2011 | Mon Feb 28 08:00:00 IST 2011
1863 | TTM Implementation | Mon Feb 28 08:00:00 IST 2011 | Mon Mar 28 17:00:00 IST 2011
1864 | Relocation of Toilet/Bus Operator Office | Mon Feb 28 08:00:00 IST 2011 | Sat Mar 26 17:00:00 IST 2011
1865 | Bus Stop Modification Stage 1 | Mon Feb 28 08:00:00 IST 2011 | Mon Mar 14 17:00:00 IST 2011
1866 | Bus Stop Modification Stage 2 | Mon Feb 28 08:00:00 IST 2011 | Fri Mar 04 17:00:00 IST 2011
1867 | Road Kerb Removal | Mon Feb 28 08:00:00 IST 2011 | Fri Mar 11 17:00:00 IST 2011
1868 | Trial Trench for Expose U/G Utilities | Mon Feb 28 08:00:00 IST 2011 | Tue Mar 22 17:00:00 IST 2011
1869 | Expose the Existing Pile Heads | Thu Apr 21 08:00:00 IDT 2011 | Wed May 18 17:00:00 IDT 2011
1870 | Backfill | Mon Feb 28 08:00:00 IST 2011 | Sat Mar 05 17:00:00 IST 2011
1871 | 1 Vertical Pile Removal UT(3G) | Mon Feb 28 08:00:00 IST 2011 | Wed Mar 02 17:00:00 IST 2011
1872 | 1 Vertical Pile Removal UT(1G) | Mon Feb 28 08:00:00 IST 2011 | Thu Mar 03 17:00:00 IST 2011
1873 | 1 Vertical Pile Removal UT(3H) | Wed Aug 31 08:00:00 IDT 2011 | Thu Sep 15 17:00:00 IDT 2011
1874 | 1 Vertical Pile Removal UT(1H) | Wed Aug 31 08:00:00 IDT 2011 | Thu Sep 15 17:00:00 IDT 2011
1875 | 1 Raking Pile Removal UT (2Fa) | Wed Aug 31 08:00:00 IDT 2011 | Mon Sep 26 17:00:00 IDT 2011
1876 | 4 Raking Pile Removal DT(2Ja,2Ha,2Hb & 2Gb) | Wed Aug 31 08:00:00 IDT 2011 | Wed Dec 07 17:00:00 IST 2011
1877 | PTI Reinstatement | Fri Feb 21 08:00:00 IST 2014 | Thu Jun 05 17:00:00 IDT 2014
1878 | FMO Pier B Piles Removal (4nos.) (DT) | Fri May 27 08:00:00 IDT 2011 | Sun Jun 24 17:00:00 IDT 2012
1879 | FMO Pier B Piles Removal (5nos.) (UT) | Fri May 27 08:00:00 IDT 2011 | Fri Feb 17 17:00:00 IST 2012
1880 | Completion | Thu Mar 15 08:00:00 IST 2012 | Mon Apr 16 17:00:00 IDT 2012
1881 | Prepare & Submit Draft As-built Drawings (PTI) | Thu Mar 15 08:00:00 IST 2012 | Mon Apr 16 17:00:00 IDT 2012
1882 | Prepare & Submit As-built Drawings (PTI) | Thu Mar 15 08:00:00 IST 2012 | Mon Apr 16 17:00:00 IDT 2012
1883 | F6 Sham Shui Po Ferry Pier - Pile removal | Mon Feb 28 08:00:00 IST 2011 | Thu Nov 07 17:00:00 IST 2013
1884 | Temp. Works Design Submission | Mon Feb 28 08:00:00 IST 2011 | Tue Jul 19 17:00:00 IDT 2011
1885 | Temp. Works Design Preparation | Mon Feb 28 08:00:00 IST 2011 | Wed Mar 30 17:00:00 IST 2011
1886 | Temp. Works Design Submit to MTR | Mon Mar 28 08:00:00 IST 2011 | Mon Mar 28 08:00:00 IST 2011
1887 | Temp. Works Design Comment by MTR | Mon Mar 28 08:00:00 IST 2011 | Tue Jul 19 17:00:00 IDT 2011
1888 | Temp. Works Design Re-submission Preparation | Tue Apr 26 08:00:00 IDT 2011 | Fri May 20 17:00:00 IDT 2011
1889 | Temp. Works Design Comment & Approval by MTR | Thu May 19 08:00:00 IDT 2011 | Sat Jun 04 17:00:00 IDT 2011
1890 | Issue for Construction | Wed Jun 15 17:00:00 IDT 2011 | Wed Jun 15 17:00:00 IDT 2011
1891 | Method Statement Submission and Approval | Mon Feb 28 08:00:00 IST 2011 | Wed Aug 31 08:00:00 IDT 2011
1892 | MS Submission Preparation | Wed Mar 16 08:00:00 IST 2011 | Wed Apr 06 17:00:00 IDT 2011
1893 | MS Submission to MTR | Wed Apr 13 17:00:00 IDT 2011 | Wed Apr 13 17:00:00 IDT 2011
1894 | MS Comment by MTR | Mon Feb 28 08:00:00 IST 2011 | Wed Mar 09 17:00:00 IST 2011
1895 | MS Re-submission Preparation | Mon Feb 28 08:00:00 IST 2011 | Sat Apr 16 17:00:00 IDT 2011
1896 | MS Comment & Approval by MTR | Mon Feb 28 08:00:00 IST 2011 | Mon Aug 01 17:00:00 IDT 2011
1897 | Issue for Construction | Wed Aug 31 08:00:00 IDT 2011 | Wed Aug 31 08:00:00 IDT 2011
1898 | TTM Scheme Submission & Approval | Mon Feb 28 08:00:00 IST 2011 | Mon Aug 08 17:00:00 IDT 2011
1899 | Prepare Temp.Traffic Mgmt for Tree Transplant | Mon Feb 28 08:00:00 IST 2011 | Wed Apr 13 17:00:00 IDT 2011
1900 | TTM Comment & Approval by Relevant Authorities | Thu Apr 14 08:00:00 IDT 2011 | Fri May 13 17:00:00 IDT 2011
1901 | Notification to RMO | Fri Jul 08 08:00:00 IDT 2011 | Mon Aug 08 17:00:00 IDT 2011
1902 | Implement TTM | Tue Jul 19 17:00:00 IDT 2011 | Tue Jul 19 17:00:00 IDT 2011
1903 | Stage 0 | Mon Feb 28 08:00:00 IST 2011 | Thu Nov 10 17:00:00 IST 2011
1904 | Group B TreeTransplant(T9746,U0019-24)Preparat'n | Wed Jul 20 08:00:00 IDT 2011 | Mon Aug 29 17:00:00 IDT 2011
1905 | Group D Tree Transplant (U0023) Preparation | Wed Jul 20 08:00:00 IDT 2011 | Mon Aug 29 17:00:00 IDT 2011
1906 | Access Date for Works Area 11.21 | Mon Feb 28 08:00:00 IST 2011 | Mon Feb 28 08:00:00 IST 2011
1907 | Stage 0 TTA | Mon Feb 28 08:00:00 IST 2011 | Wed Mar 30 17:00:00 IST 2011
1908 | Tree Transplanting | Thu Oct 06 08:00:00 IST 2011 | Thu Nov 10 17:00:00 IST 2011
1909 | Kerb & Footpath Removal | Tue Mar 29 08:00:00 IST 2011 | Wed May 11 17:00:00 IDT 2011
1910 | Pavement Excavation and Expose Underground Utilities | Wed Apr 06 08:00:00 IDT 2011 | Wed May 18 17:00:00 IDT 2011
1911 | Agree Diversion Scheme with CLP for 132kV | Mon Jun 20 08:00:00 IDT 2011 | Fri Jun 24 17:00:00 IDT 2011
1912 | Stage 0 Enabling Work | Mon Feb 28 08:00:00 IST 2011 | Mon Aug 29 17:00:00 IDT 2011
1913 | Stage 1 | Sun Jun 19 08:00:00 IDT 2011 | Sat Nov 02 17:00:00 IST 2013
1914 | Extended TTMs Application & Approval | Mon Jun 20 08:00:00 IDT 2011 | Thu Jun 30 17:00:00 IDT 2011
1915 | Stage 1 Extended TTMs Implementation | Sun Jun 19 08:00:00 IDT 2011 | Fri Jul 15 17:00:00 IDT 2011
1916 | Remove Retaining Wall for Watermain Diversion | Tue Jun 21 08:00:00 IDT 2011 | Tue Aug 09 17:00:00 IDT 2011
1917 | Prepare Trench for 132kV Diversion | Sat Jul 02 08:00:00 IDT 2011 | Fri Aug 12 17:00:00 IDT 2011
1918 | Divert 1400D Fresh Watermain (FW205) | Wed Aug 31 08:00:00 IDT 2011 | Thu Dec 22 17:00:00 IST 2011
1919 | Divert 600D Salt Watermain (SW202) | Sun Jan 15 08:00:00 IST 2012 | Tue Mar 13 17:00:00 IST 2012
1920 | Joint Bay Construction & Laying New Cable by CLP (132kV Diversion) | Sun Jan 15 08:00:00 IST 2012 | Fri Feb 17 17:00:00 IST 2012
1921 | Power Outage & Connection by CLP (132kV Diversion) | Sun Jan 15 08:00:00 IST 2012 | Wed Mar 07 17:00:00 IST 2012
1922 | Mobilization for Pile Removal | Fri Aug 31 08:00:00 IDT 2012 | Tue Sep 04 17:00:00 IDT 2012
1923 | Remove the Existing Vertical Piles @ GL.1 - DT(11nos.) | Mon Sep 03 08:00:00 IDT 2012 | Sat Nov 10 17:00:00 IST 2012
1924 | Remove the Existing Vertical Piles @ GL.2 - DT(11nos.) | Wed Sep 05 08:00:00 IDT 2012 | Tue Nov 13 17:00:00 IST 2012
1925 | Agree with WSD for reinstatement of diverted 1400D FW main (FW205) | Wed Nov 14 08:00:00 IST 2012 | Mon Feb 04 17:00:00 IST 2013
1926 | Reinstate diverted 1400D FW main (FW205) | Thu Feb 28 08:00:00 IST 2013 | Wed Mar 27 17:00:00 IST 2013
1927 | Temporary Road Reinstatement | Sat Oct 12 08:00:00 IDT 2013 | Sat Nov 02 17:00:00 IST 2013
1928 | Stage 1 Piles Removal (22nos.) (DT) | Sun Jun 19 08:00:00 IDT 2011 | Sat May 26 17:00:00 IDT 2012
1929 | Stage 2 | Wed Nov 28 08:00:00 IST 2012 | Thu Nov 07 17:00:00 IST 2013
1930 | Stage 2 TTM Implementation | Fri Mar 29 08:00:00 IDT 2013 | Sun Apr 14 17:00:00 IDT 2013
1931 | Divert 1200D Foul Sewer Drain (FD202) | Mon Apr 15 08:00:00 IDT 2013 | Mon May 13 17:00:00 IDT 2013
1932 | Remove the Existing 12 Piles (UT) @GL.4 | Tue May 14 08:00:00 IDT 2013 | Wed Jul 31 17:00:00 IDT 2013
1933 | Divert 900D Stormwater Drain (SD214) | Mon Aug 05 08:00:00 IDT 2013 | Wed Sep 04 17:00:00 IDT 2013
1934 | Remove the Existing 10 Piles (UT) @GL.5 | Wed Nov 28 08:00:00 IST 2012 | Mon Jan 28 17:00:00 IST 2013
1935 | Permanent Road Reinstatement | Mon Jan 07 08:00:00 IST 2013 | Thu May 09 17:00:00 IDT 2013
1936 | Stage 2 Piles Removal (20nos.) (UT) | Fri Mar 29 08:00:00 IDT 2013 | Thu Nov 07 17:00:00 IST 2013
1937 | Completion | Wed May 02 08:00:00 IDT 2012 | Tue May 29 17:00:00 IDT 2012
1938 | Prepare & Submit Draft As-built Drawings | Wed May 02 08:00:00 IDT 2012 | Tue May 29 17:00:00 IDT 2012
1939 | Prepare & Submit As-built Drawings | Wed May 02 08:00:00 IDT 2012 | Tue May 29 17:00:00 IDT 2012
1940 | Cost Centre G - Utility Diversion Works | Sat Aug 14 08:00:00 IDT 2010 | Sat Oct 10 17:00:00 IDT 2015
1941 | IPS Milestones | Sun Mar 27 17:00:00 IST 2011 | Tue Oct 29 17:00:00 IST 2013
1942 | General | Sun Mar 27 17:00:00 IST 2011 | Tue Oct 29 17:00:00 IST 2013
1943 | Complete Temp. Diversion of Box Culvert FS1 | Fri Sep 30 17:00:00 IDT 2011 | Fri Sep 30 17:00:00 IDT 2011
1944 | Complete Thrust Block for North Temp.DSD Rising Main | Sun Mar 27 17:00:00 IST 2011 | Sun Mar 27 17:00:00 IST 2011
1945 | Remove Pile for DSD Rising Main adj. TBM Launch Shaft | Sun Jan 15 08:00:00 IST 2012 | Sun Jan 15 08:00:00 IST 2012
1946 | Complete Removal of 60% of Obstruction Piles for WD1 | Fri Aug 31 08:00:00 IDT 2012 | Fri Aug 31 08:00:00 IDT 2012
1947 | Remove Barrettes for DSD Culvert NC1 | Fri Mar 23 17:00:00 IST 2012 | Fri Mar 23 17:00:00 IST 2012
1948 | Complete Box Culvert WD1 Reinstate Wk & Handover | Tue Oct 29 17:00:00 IST 2013 | Tue Oct 29 17:00:00 IST 2013
1949 | G4 DSD Culvert WD1 Potential Obstruction | Tue Dec 14 08:00:00 IST 2010 | Tue Oct 29 17:00:00 IST 2013
1950 | Obstruction Removal at 1.1m Dia.Sewer Pipe Area (UT) | Tue Dec 14 08:00:00 IST 2010 | Tue Dec 14 08:00:00 IST 2010
1951 | Obstruction Removal at 1.1m Dia.Sewer Pipe Area (DT) | Fri Jul 22 08:00:00 IDT 2011 | Wed Apr 18 17:00:00 IDT 2012
1952 | Obstruction Removal at 1.8m Dia.Sewer Pipe Area (DT) | Wed Aug 31 08:00:00 IDT 2011 | Mon May 28 17:00:00 IDT 2012
1953 | WD1 Piles Removal (P1,P3 & P9) (UT) | Sun Mar 13 08:00:00 IST 2011 | Thu Jul 07 17:00:00 IDT 2011
1954 | WD1Pre-bored Socket H-piles & Pile Cap (5nos..) | Tue Jun 21 08:00:00 IDT 2011 | Sun Oct 23 17:00:00 IST 2011
1955 | WD1 Piles Removal (P4,P6,P7 & P8) (UT) | Fri Apr 13 08:00:00 IDT 2012 | Wed Feb 27 17:00:00 IST 2013
1956 | Diversion Scheme Submission | Mon Feb 28 08:00:00 IST 2011 | Mon Aug 01 17:00:00 IDT 2011
1957 | Prepare Diversion Scheme Proposal | Mon Feb 28 08:00:00 IST 2011 | Tue Apr 26 17:00:00 IDT 2011
1958 | Comment of Diversion Scheme by DSD | Tue Apr 12 08:00:00 IDT 2011 | Sun Apr 17 17:00:00 IDT 2011
1959 | Proposed Diversion Scheme Re-subm'n | Wed May 11 08:00:00 IDT 2011 | Thu Jun 02 17:00:00 IDT 2011
1960 | Proposed Diversion Scheme Approval by DSD | Wed May 25 08:00:00 IDT 2011 | Mon Aug 01 17:00:00 IDT 2011
1961 | Method Statement Submission and Approval | Sat Jan 08 08:00:00 IST 2011 | Fri May 13 17:00:00 IDT 2011
1962 | MS Preparation for WDI Obstruction Removal | Sat Jan 08 08:00:00 IST 2011 | Tue Feb 08 17:00:00 IST 2011
1963 | MS Submission to MTR | Thu Mar 03 17:00:00 IST 2011 | Thu Mar 03 17:00:00 IST 2011
1964 | MS Comment by MTR | Fri Mar 04 08:00:00 IST 2011 | Tue Mar 22 17:00:00 IST 2011
1965 | MS Re-submission Preparation | Fri Apr 01 08:00:00 IDT 2011 | Fri Apr 08 17:00:00 IDT 2011
1966 | MS Comment & Approval by MTR | Sat Apr 16 08:00:00 IDT 2011 | Sun May 08 17:00:00 IDT 2011
1967 | Issue for Construction | Fri May 13 17:00:00 IDT 2011 | Fri May 13 17:00:00 IDT 2011
1968 | Temp.works Design Submission | Mon Feb 28 08:00:00 IST 2011 | Mon Aug 01 17:00:00 IDT 2011
1969 | Prepare Temp.Gate & Working Platform Proposal | Mon Feb 28 08:00:00 IST 2011 | Tue Apr 26 17:00:00 IDT 2011
1970 | Comment of Temp.Gate& Working Platform byRDO/DSD | Tue Apr 12 08:00:00 IDT 2011 | Sun Apr 17 17:00:00 IDT 2011
1971 | Proposed Temp.Gate & Working Platform Re-subm'n | Wed May 11 08:00:00 IDT 2011 | Thu Jun 02 17:00:00 IDT 2011
1972 | Proposed Temp.Gate& WorkingPlatf'mApp'l /RDO&DSD | Wed May 25 08:00:00 IDT 2011 | Mon Aug 01 17:00:00 IDT 2011
1973 | TTM Scheme Submission & Approval | Sat Jan 08 08:00:00 IST 2011 | Sat Jul 09 17:00:00 IDT 2011
1974 | Prepare Temp.Pedestrian Walkway Diversion Scheme | Sat Jan 08 08:00:00 IST 2011 | Fri Jan 21 17:00:00 IST 2011
1975 | Temp.Pedestrian Walkway Approval by SLG/HyD/etc. | Sat Jan 22 08:00:00 IST 2011 | Sun Apr 03 17:00:00 IDT 2011
1976 | Notification to RMO | Sat Apr 16 08:00:00 IDT 2011 | Thu Apr 21 17:00:00 IDT 2011
1977 | Implement for Temp.Pederstrian Walkway | Wed Apr 27 17:00:00 IDT 2011 | Wed Apr 27 17:00:00 IDT 2011
1978 | Prepare Temporary Traffic Management | Sat Jan 08 08:00:00 IST 2011 | Tue Feb 08 17:00:00 IST 2011
1979 | TTM reviewed by SLG | Wed Feb 09 08:00:00 IST 2011 | Thu Mar 03 17:00:00 IST 2011
1980 | Resubmit TTM | Wed May 04 08:00:00 IDT 2011 | Wed May 11 17:00:00 IDT 2011
1981 | TTM reviewed by SLG | Fri May 13 08:00:00 IDT 2011 | Sat Jun 11 17:00:00 IDT 2011
1982 | Notification to RMO | Sat Jun 11 08:00:00 IDT 2011 | Sat Jul 09 17:00:00 IDT 2011
1983 | XP Application & Approval | Mon Feb 28 08:00:00 IST 2011 | Mon Mar 14 17:00:00 IST 2011
1984 | Implement TTM | Tue Jun 28 17:00:00 IDT 2011 | Tue Jun 28 17:00:00 IDT 2011
1985 | Prepare Temp.TrafficManagem't for TreeTransplant | Sat Jan 08 08:00:00 IST 2011 | Tue Feb 08 17:00:00 IST 2011
1986 | TTM reviewed by SLG | Wed Feb 09 08:00:00 IST 2011 | Mon May 23 17:00:00 IDT 2011
1987 | Notification to RMO | Thu May 05 08:00:00 IDT 2011 | Sun May 08 17:00:00 IDT 2011
1988 | Proposed Culvert New Founding System | Mon Feb 28 08:00:00 IST 2011 | Tue Sep 27 17:00:00 IDT 2011
1989 | Prepare & Submit Culvert New Founding System | Mon Feb 28 08:00:00 IST 2011 | Fri Mar 11 17:00:00 IST 2011
1990 | Comment of Culvert New Founding System byRDO/DSD | Tue Apr 12 08:00:00 IDT 2011 | Tue Apr 26 17:00:00 IDT 2011
1991 | Culvert New Founding System Re-submission | Tue May 24 08:00:00 IDT 2011 | Tue Sep 27 17:00:00 IDT 2011
1992 | Culvert New Founding System Approval by RDO/DSD | Wed Jun 08 08:00:00 IDT 2011 | Wed Jul 27 17:00:00 IDT 2011
1993 | Site Possession Application | Mon Feb 28 08:00:00 IST 2011 | Mon Jun 06 08:00:00 IDT 2011
1994 | Apply Site Possession to SLG | Mon Feb 28 08:00:00 IST 2011 | Sat Mar 05 17:00:00 IST 2011
1995 | SLG Comments & Approval | Sun Mar 06 08:00:00 IST 2011 | Tue Mar 29 17:00:00 IST 2011
1996 | TGLA Comments & Approval | Tue Mar 29 08:00:00 IST 2011 | Sat Jun 04 17:00:00 IDT 2011
1997 | Site Possession | Mon Jun 06 08:00:00 IDT 2011 | Mon Jun 06 08:00:00 IDT 2011
1998 | Utilities Coordination | Mon Feb 28 08:00:00 IST 2011 | Thu Jun 30 17:00:00 IDT 2011
1999 | Prepare & Submit Utilities Diversion Scheme | Mon Feb 28 08:00:00 IST 2011 | Thu Mar 31 17:00:00 IST 2011
2000 | Comment of Utilities Diversion Scheme | Fri Apr 01 08:00:00 IDT 2011 | Thu Apr 28 17:00:00 IDT 2011
2001 | Utilities Diversion Scheme Re-submission | Fri Apr 29 08:00:00 IDT 2011 | Sat May 14 17:00:00 IDT 2011
2002 | Utilities Diversion Scheme Approval | Sun May 15 08:00:00 IDT 2011 | Thu Jun 30 17:00:00 IDT 2011
2003 | Preparation Excavation Permit | Mon Apr 11 08:00:00 IDT 2011 | Fri Jun 10 17:00:00 IDT 2011
2004 | Excavation Permit Issue | Mon Jun 13 08:00:00 IDT 2011 | Mon Jun 13 08:00:00 IDT 2011
2005 | Power Cable & Fresh Water Main | Sat Jan 08 08:00:00 IST 2011 | Wed Oct 31 17:00:00 IST 2012
2006 | GI works for WD1 | Sat Jan 08 08:00:00 IST 2011 | Wed Jun 01 17:00:00 IDT 2011
2007 | Site Mobilization | Tue Jun 07 08:00:00 IDT 2011 | Wed Jul 06 17:00:00 IDT 2011
2008 | Temp.Working Platform | Thu Jun 23 08:00:00 IDT 2011 | Tue Aug 23 17:00:00 IDT 2011
2009 | Temp.Traffic Diversion(Pedestrian Walkway) | Mon Feb 28 08:00:00 IST 2011 | Fri Mar 11 17:00:00 IST 2011
2010 | Trial Trench & Record | Mon Jun 13 08:00:00 IDT 2011 | Sat Aug 20 17:00:00 IDT 2011
2011 | Slew 400KV Cable(CLP204)& 2Sets of 11KV(CLP205) | Sat Jul 02 08:00:00 IDT 2011 | Mon Oct 10 17:00:00 IST 2011
2012 | Slew Tele Cables (PCCW204+HKBN201) | Wed Aug 24 08:00:00 IDT 2011 | Mon Aug 29 17:00:00 IDT 2011
2013 | Cosnt.Temp.300mm dia.WaterMain (FW203) | Mon Feb 20 08:00:00 IST 2012 | Tue Mar 27 17:00:00 IST 2012
2014 | Water Main Diversion (FW203) | Mon Jan 16 08:00:00 IST 2012 | Mon Jan 16 08:00:00 IST 2012
2015 | Slew 400KV & 2 Sets 11KV Cables Reinstatement | Sat Sep 01 08:00:00 IDT 2012 | Wed Oct 17 17:00:00 IST 2012
2016 | Remove Temp.Support for 400KV &11KV Cables | Wed Oct 17 08:00:00 IST 2012 | Wed Oct 31 17:00:00 IST 2012
2017 | Reinstate 300mmdia Fresh Water Main (FW203) | Sat Sep 01 08:00:00 IDT 2012 | Wed Oct 10 17:00:00 IST 2012
2018 | Remove Temp.300mm dia.Fresh Water Meter (FW203) | Thu Oct 11 08:00:00 IST 2012 | Thu Oct 25 17:00:00 IST 2012
2019 | Remove Temp.Support for Temp.Fresh Water Main | Thu Oct 25 08:00:00 IST 2012 | Wed Oct 31 17:00:00 IST 2012
2020 | 1.1m Dia. Sewer Pipe Diversion | Tue Dec 14 08:00:00 IST 2010 | Fri Mar 01 17:00:00 IST 2013
2021 | Coord'n w/DSD forTemp.Removal ofOverflow Pipe | Mon Jan 16 08:00:00 IST 2012 | Mon Jan 16 08:00:00 IST 2012
2022 | Trial Trench & Record | Wed Aug 31 08:00:00 IDT 2011 | Fri Sep 30 17:00:00 IDT 2011
2023 | Sheet Piles Cofferdam 1A | Fri Jul 22 08:00:00 IDT 2011 | Mon Oct 03 17:00:00 IST 2011
2024 | Expose and Protect 400mm dia.Gas Main (GAS211) | Thu Sep 08 08:00:00 IDT 2011 | Tue Oct 11 17:00:00 IST 2011
2025 | Drilling | Mon Jan 16 08:00:00 IST 2012 | Tue Jan 31 17:00:00 IST 2012
2026 | Grouting for MH-1 | Mon Jan 16 08:00:00 IST 2012 | Sat Jan 21 17:00:00 IST 2012
2027 | Excavate for dewatering well and place blinding | Mon Jan 16 08:00:00 IST 2012 | Thu Jan 19 17:00:00 IST 2012
2028 | Excavate for MH-1 Construction & Shoring Installation | Thu Mar 01 08:00:00 IST 2012 | Sat Mar 24 17:00:00 IST 2012
2029 | Construct MH-1 Stage 1 & pump test | Mon Sep 17 08:00:00 IDT 2012 | Fri Sep 28 17:00:00 IST 2012
2030 | Insert DN800 temp pipe and fill gap between temp pipe & DN1800 | Sat Sep 29 08:00:00 IST 2012 | Sat Oct 06 17:00:00 IST 2012
2031 | Installation of by-pass pipe, benching & Inspection | Mon Oct 08 08:00:00 IST 2012 | Mon Oct 15 17:00:00 IST 2012
2032 | Drilling | Mon Jan 16 08:00:00 IST 2012 | Sat Jan 21 17:00:00 IST 2012
2033 | Grouting for MH-2 | Mon Jan 16 08:00:00 IST 2012 | Sat Jan 28 17:00:00 IST 2012
2034 | Excavate for dewatering well and place blinding | Mon Jan 16 08:00:00 IST 2012 | Fri Jan 20 17:00:00 IST 2012
2035 | Excavate for MH-2 Construction & Shoring Installation | Mon Jan 16 08:00:00 IST 2012 | Fri Feb 17 17:00:00 IST 2012
2036 | Construct MH-2 Stage 1 & pump test | Thu Oct 04 08:00:00 IST 2012 | Mon Oct 15 17:00:00 IST 2012
2037 | Insert DN800 temp pipe and fill gap between temp pipe & DN1800 | Tue Oct 16 08:00:00 IST 2012 | Sat Oct 20 17:00:00 IST 2012
2038 | Installation of by-pass pipe, benching & Inspection | Sat Oct 20 08:00:00 IST 2012 | Mon Oct 29 17:00:00 IST 2012
2039 | Excavate for pipe laying between MH-1 to MH-2 & Shoring Installation | Tue Mar 06 08:00:00 IST 2012 | Thu Apr 19 17:00:00 IDT 2012
2040 | Pipe Laying, air test and concrete surround | Fri Oct 12 08:00:00 IST 2012 | Fri Oct 26 17:00:00 IST 2012
2041 | Diversion | Tue Oct 30 08:00:00 IST 2012 | Fri Nov 02 17:00:00 IST 2012
2042 | Backfill to 2nd layer waling and construct remaining part of manholes MH-1 & MH-2 | Fri Nov 02 08:00:00 IST 2012 | Tue Nov 20 17:00:00 IST 2012
2043 | Remove 1st layer waling and backfill to ground level | Wed Nov 21 08:00:00 IST 2012 | Sat Nov 24 17:00:00 IST 2012
2044 | Install Casing & Remove Piles (3nos at D/T) | Mon Nov 26 08:00:00 IST 2012 | Mon Dec 24 17:00:00 IST 2012
2045 | Install Casing & Remove Piles (4nos at U/T) | Fri Jan 11 08:00:00 IST 2013 | Fri Mar 01 17:00:00 IST 2013
2046 | Backfilling & Reinstate Road Surface | Fri Nov 23 08:00:00 IST 2012 | Mon Jan 07 17:00:00 IST 2013
2047 | Obstruction Removal at 1.1m Dia.Sewer Pipe Area (DT) | Fri Jul 22 08:00:00 IDT 2011 | Wed Apr 18 17:00:00 IDT 2012
2048 | Obstruction Removal at 1.1m Dia.Sewer Pipe Area (UT) | Tue Dec 14 08:00:00 IST 2010 | Tue Dec 14 08:00:00 IST 2010
2049 | 1.8m Dia. Sewer Pipe Diversion | Sat Jan 08 08:00:00 IST 2011 | Sat Nov 10 17:00:00 IST 2012
2050 | Group E Tree Transplant (T9605) Preparation Works | Sat Jan 08 08:00:00 IST 2011 | Sat Jul 02 17:00:00 IDT 2011
2051 | Group D Tree Transplant (T9603 & T9604) Preparation Works | Sat Jan 08 08:00:00 IST 2011 | Wed Jun 22 17:00:00 IDT 2011
2052 | Group B Tree Transplant (U0010) Preparation Works | Mon Feb 28 08:00:00 IST 2011 | Mon May 23 17:00:00 IDT 2011
2053 | Group D Tree Transplant (U0018) Preparation Works | Mon Feb 28 08:00:00 IST 2011 | Thu Aug 11 17:00:00 IDT 2011
2054 | Group E Tree Transplant (T9601&T9602)Preparation Works | Mon Feb 28 08:00:00 IST 2011 | Mon Aug 22 17:00:00 IDT 2011
2055 | Trial Trench & Record | Wed Aug 31 08:00:00 IDT 2011 | Fri Sep 30 17:00:00 IDT 2011
2056 | Construct Cofferdam 2: MH-4, excavate to formation level and place blinding layer | Wed Aug 31 08:00:00 IDT 2011 | Mon Dec 05 17:00:00 IST 2011
2057 | Slew 400KV (CLP221)+11kV (CLP222) w/Temp.Support | Mon Jan 16 08:00:00 IST 2012 | Sat Jan 21 17:00:00 IST 2012
2058 | Pipe Formation preparation | Thu Feb 09 08:00:00 IST 2012 | Wed Feb 15 17:00:00 IST 2012
2059 | Sewage Pipe Laying with concrete surround (btw MH-3 to MH-4) | Wed Feb 01 08:00:00 IST 2012 | Thu Feb 09 17:00:00 IST 2012
2060 | Construct Manhole - Stage 1 | Mon Jan 16 08:00:00 IST 2012 | Fri Jan 20 17:00:00 IST 2012
2061 | BreakDN1800 pipe top | Sat Jan 28 08:00:00 IST 2012 | Mon Jan 30 17:00:00 IST 2012
2062 | Construct Manhole - Stage 2 & pump test | Wed Feb 01 08:00:00 IST 2012 | Thu Feb 02 17:00:00 IST 2012
2063 | Insert Temp Pipe and Filling gap between temp pipe & DN1800 | Wed Feb 22 08:00:00 IST 2012 | Sat Feb 25 17:00:00 IST 2012
2064 | Installation of by-pass pipe, benching & inspection | Wed Feb 22 08:00:00 IST 2012 | Tue Feb 28 17:00:00 IST 2012
2065 | Diversion | Wed Jan 18 08:00:00 IST 2012 | Sat Jan 21 17:00:00 IST 2012
2066 | Make good manhole wall at original pipe opening | Fri Aug 31 08:00:00 IDT 2012 | Tue Sep 04 17:00:00 IDT 2012
2067 | Demolish pile cap and expose existing obstruction pile | Wed Sep 05 08:00:00 IDT 2012 | Fri Sep 07 17:00:00 IDT 2012
2068 | Backfill to 2nd layer waling and construct remaining part of manhole | Sat Sep 08 08:00:00 IDT 2012 | Tue Sep 25 17:00:00 IST 2012
2069 | Remove 1st layer waling and backfill to ground level | Wed Sep 26 08:00:00 IST 2012 | Fri Oct 05 17:00:00 IST 2012
2070 | Remove 1 no. of dia. 500 pile | Sat Oct 06 08:00:00 IST 2012 | Wed Oct 17 17:00:00 IST 2012
2071 | Construct Cofferdam 1B: MH-3, excavate to formation level and place blinding layer | Wed Aug 31 08:00:00 IDT 2011 | Mon Dec 05 17:00:00 IST 2011
2072 | Construct Manhole - Stage 1 & pump test | Wed Feb 01 08:00:00 IST 2012 | Mon Feb 13 17:00:00 IST 2012
2073 | Insert Temp Pipe and Filling gap between temp pipe & DN1800 | Wed Feb 01 08:00:00 IST 2012 | Sat Feb 04 17:00:00 IST 2012
2074 | Installation of by-pass pipe, benching & inspection | Wed Feb 22 08:00:00 IST 2012 | Tue Feb 28 17:00:00 IST 2012
2075 | Diversion | Wed Jan 18 08:00:00 IST 2012 | Sat Jan 21 17:00:00 IST 2012
2076 | Make good manhole wall at original pipe opening | Fri Aug 31 08:00:00 IDT 2012 | Tue Sep 04 17:00:00 IDT 2012
2077 | Demolish pile cap and expose existing obstruction pile | Wed Sep 05 08:00:00 IDT 2012 | Fri Sep 07 17:00:00 IDT 2012
2078 | Install guide steel liner | Sat Sep 08 08:00:00 IDT 2012 | Wed Sep 12 17:00:00 IDT 2012
2079 | Backfill to 2nd layer waling and construct remaining part of manhole | Thu Sep 13 08:00:00 IDT 2012 | Sat Sep 29 17:00:00 IST 2012
2080 | Remove 1st layer waling and backfill to ground level | Wed Oct 03 08:00:00 IST 2012 | Sat Oct 13 17:00:00 IST 2012
2081 | Remove 2 no. of dia. 500 pile | Thu Oct 18 08:00:00 IST 2012 | Sat Nov 10 17:00:00 IST 2012
2082 | Obstruction Removal at 1.8m Dia.Sewer Pipe Area (DT) | Wed Aug 31 08:00:00 IDT 2011 | Mon May 28 17:00:00 IDT 2012
2083 | Removal of Piles: P1 to P3 & P9 | Sat Mar 12 08:00:00 IST 2011 | Thu Mar 08 17:00:00 IST 2012
2084 | Open Cut to Expose Top Slab of Culvert Partially | Tue Nov 01 08:00:00 IST 2011 | Thu Nov 03 17:00:00 IST 2011
2085 | Break Top Slab of Box Culvert | Fri Nov 04 08:00:00 IST 2011 | Tue Jan 31 17:00:00 IST 2012
2086 | Install Temp.Working Platform & Cofferdam | Tue Jun 21 08:00:00 IDT 2011 | Tue Jul 05 17:00:00 IDT 2011
2087 | Mobilization | Mon Nov 07 08:00:00 IST 2011 | Fri Jan 13 17:00:00 IST 2012
2088 | Install Casing & Remove Pile: P1 | Tue Nov 01 08:00:00 IST 2011 | Wed Nov 16 17:00:00 IST 2011
2089 | Fill LeanConcrete &Reinstate BottomSlab for P1 | Tue Nov 01 08:00:00 IST 2011 | Sat Nov 26 17:00:00 IST 2011
2090 | Shift Temp.Cofferdam & Remove Pile: P2 | Sat Mar 12 08:00:00 IST 2011 | Tue Apr 12 17:00:00 IDT 2011
2091 | Fill Lean Concrete & Reinstate BottomSlab for P2 | Tue Nov 01 08:00:00 IST 2011 | Tue Dec 06 17:00:00 IST 2011
2092 | Install Temp. Cofferdam & Remove Pile: P3 | Thu Jan 19 08:00:00 IST 2012 | Wed Feb 01 17:00:00 IST 2012
2093 | Fill Lean Concrete & Reinstate BottomSlab for P3 | Thu Feb 09 08:00:00 IST 2012 | Thu Mar 08 17:00:00 IST 2012
2094 | Implement TTM | Tue Jun 28 17:00:00 IDT 2011 | Tue Jun 28 17:00:00 IDT 2011
2095 | Modification Works for Temp.Traffic Diversion | Wed Jun 29 08:00:00 IDT 2011 | Tue Nov 01 17:00:00 IST 2011
2096 | Install Casing & Remove Pile: P9 | Mon Mar 14 08:00:00 IST 2011 | Fri Nov 25 17:00:00 IST 2011
2097 | Fill Lean Concrete & Reinstate BottomSlab for P9 | Tue Nov 01 08:00:00 IST 2011 | Fri Nov 18 17:00:00 IST 2011
2098 | WD1 Piles Removal (P1,P3 & P9) (UT) | Sun Mar 13 08:00:00 IST 2011 | Thu Jul 07 17:00:00 IDT 2011
2099 | Removal of Piles: P4 to P6 & P7 &P8 | Tue Jun 21 08:00:00 IDT 2011 | Wed Feb 27 17:00:00 IST 2013
2100 | Working Platform for Prebore H Piles | Tue Jun 21 08:00:00 IDT 2011 | Thu Jul 14 17:00:00 IDT 2011
2101 | Install 5 nos.Pre-bored Socket H-piles | Tue Jun 21 08:00:00 IDT 2011 | Tue Jul 12 17:00:00 IDT 2011
2102 | Sheet Pile for Cofferdam | Fri Jul 22 08:00:00 IDT 2011 | Thu Aug 18 17:00:00 IDT 2011
2103 | Bulk Excqavation to Expose Top Slab of Culvert | Tue Jun 21 08:00:00 IDT 2011 | Sat Jul 02 17:00:00 IDT 2011
2104 | Place Concrete Block Wall | Tue Jun 21 08:00:00 IDT 2011 | Wed Jun 22 17:00:00 IDT 2011
2105 | Waling Installtion | Wed Aug 31 08:00:00 IDT 2011 | Wed Sep 21 17:00:00 IDT 2011
2106 | Blinding Slab | Wed Aug 31 08:00:00 IDT 2011 | Fri Sep 02 17:00:00 IDT 2011
2107 | Demolish TopSlab above PilesP1~ P3 & P9 | Wed Aug 31 08:00:00 IDT 2011 | Wed Sep 14 17:00:00 IDT 2011
2108 | Formwork & Planking | Wed Aug 31 08:00:00 IDT 2011 | Thu Sep 08 17:00:00 IDT 2011
2109 | Reinstate Top Slab and Corbel Beams | Wed Aug 31 08:00:00 IDT 2011 | Thu Oct 06 17:00:00 IST 2011
2110 | Concrete Curing | Sat Jan 28 08:00:00 IST 2012 | Fri Feb 24 17:00:00 IST 2012
2111 | Installation of Jacks | Sat Feb 25 08:00:00 IST 2012 | Sat Mar 03 17:00:00 IST 2012
2112 | Slew 400kV Cable to P1 to P3 | Mon Feb 06 08:00:00 IST 2012 | Thu Feb 16 17:00:00 IST 2012
2113 | Divert Watermain (FW203) | Mon Feb 20 08:00:00 IST 2012 | Sat Feb 25 17:00:00 IST 2012
2114 | Water Suspension & Connection | Sat Feb 25 08:00:00 IST 2012 | Fri Mar 02 17:00:00 IST 2012
2115 | Backfilling | Fri Mar 02 08:00:00 IST 2012 | Thu Mar 08 17:00:00 IST 2012
2116 | Excavation to Expose P4 to P8 | Thu Mar 08 08:00:00 IST 2012 | Wed Mar 21 17:00:00 IST 2012
2117 | Installation of Concrete Block Wall | Wed Mar 21 08:00:00 IST 2012 | Wed Apr 11 17:00:00 IDT 2012
2118 | Saw Cut Roof over P4 to P6, P7 & P8 | Fri Apr 13 08:00:00 IDT 2012 | Sat May 05 17:00:00 IDT 2012
2119 | Install Temp.Working Platform & Cofferdam of Work Area | Mon Jan 16 08:00:00 IST 2012 | Thu Jan 26 17:00:00 IST 2012
2120 | Install Casing & Remove Piles: P5 | Thu Nov 01 08:00:00 IST 2012 | Wed Dec 05 17:00:00 IST 2012
2121 | Fill Lean Concrete& Reinstate BottomSlab forP5 | Thu Nov 29 08:00:00 IST 2012 | Sat Dec 01 17:00:00 IST 2012
2122 | Shift Temp.Cofferdam & Remove Pile: P4 | Sat Dec 01 08:00:00 IST 2012 | Wed Dec 19 17:00:00 IST 2012
2123 | Fill Lean Concrete & Reinstate BottomSlab for P4 | Mon Nov 19 08:00:00 IST 2012 | Wed Nov 21 17:00:00 IST 2012
2124 | Shift Temp.Cofferdam & Remove Piles: P8 | Mon Dec 17 08:00:00 IST 2012 | Mon Jan 14 17:00:00 IST 2013
2125 | Fill Lean Concrete & Reinstate BottomSlab for P8 | Thu Jan 17 08:00:00 IST 2013 | Sat Jan 19 17:00:00 IST 2013
2126 | Shift Temp.Cofferdam & Remove Piles: P6 | Sat Jan 05 08:00:00 IST 2013 | Mon Feb 04 17:00:00 IST 2013
2127 | Fill Lean Concrete & Reinstate BottomSlab for P6 | Sat Feb 02 08:00:00 IST 2013 | Tue Feb 05 17:00:00 IST 2013
2128 | Shift Temp.Cofferdam & Remove Piles: P7 | Mon Jan 21 08:00:00 IST 2013 | Fri Feb 01 17:00:00 IST 2013
2129 | Fill Lean Concrete & Reinstate BottomSlab for P7 | Mon Feb 25 08:00:00 IST 2013 | Wed Feb 27 17:00:00 IST 2013
2130 | WD1Pre-bored Socket H-piles & Pile Cap (5nos..) | Tue Jun 21 08:00:00 IDT 2011 | Sun Oct 23 17:00:00 IST 2011
2131 | WD1 Piles Removal (P4,P6,P7 & P8) (UT) | Fri Apr 13 08:00:00 IDT 2012 | Sat Jan 19 17:00:00 IST 2013
2132 | Reinstatement | Fri Aug 31 08:00:00 IDT 2012 | Tue Oct 29 17:00:00 IST 2013
2133 | Reinstate Box Culvert (Invert & Roof) | Fri Aug 31 08:00:00 IDT 2012 | Mon Feb 04 17:00:00 IST 2013
2134 | Reinstate Road & Utilities | Thu Aug 01 08:00:00 IDT 2013 | Fri Aug 30 17:00:00 IDT 2013
2135 | DSD Inspection and Hand Over | Wed Oct 23 08:00:00 IDT 2013 | Tue Oct 29 17:00:00 IST 2013
2136 | Completion | Fri Jun 01 08:00:00 IDT 2012 | Fri Jun 29 17:00:00 IDT 2012
2137 | Prepare & Submit Draft As-built Drawings | Fri Jun 01 08:00:00 IDT 2012 | Fri Jun 29 17:00:00 IDT 2012
2138 | Prepare & Submit As-built Drawings | Fri Jun 01 08:00:00 IDT 2012 | Fri Jun 29 17:00:00 IDT 2012
2139 | G5 Rising Main Diversion & FMO Pier A Pile Remvoal | Mon Feb 28 08:00:00 IST 2011 | Fri Jul 31 17:00:00 IDT 2015
2140 | Rising Main & FMO Pier A Pile Removal (DT) | Sun Mar 13 08:00:00 IST 2011 | Sat Jan 05 17:00:00 IST 2013
2141 | Rising Main & FMO Pier A Pile Removal (UT) | Sun Mar 13 08:00:00 IST 2011 | Sat Sep 07 17:00:00 IDT 2013
2142 | Method Statement Submission and Approval | Mon Apr 04 08:00:00 IDT 2011 | Fri May 13 17:00:00 IDT 2011
2143 | MS Preparation | Mon Apr 04 08:00:00 IDT 2011 | Wed May 04 17:00:00 IDT 2011
2144 | MS Submission to MTR | Fri Apr 15 17:00:00 IDT 2011 | Fri Apr 15 17:00:00 IDT 2011
2145 | MS Comment & Approval by MTR | Sat Apr 16 08:00:00 IDT 2011 | Sat May 07 17:00:00 IDT 2011
2146 | Issue for Construction | Fri May 13 17:00:00 IDT 2011 | Fri May 13 17:00:00 IDT 2011
2147 | Temp. Works Design Submission | Mon Feb 28 08:00:00 IST 2011 | Wed Oct 05 17:00:00 IST 2011
2148 | Prepare Diversion Scheme to DSD | Mon Feb 28 08:00:00 IST 2011 | Sun Apr 03 17:00:00 IDT 2011
2149 | Propose Diversion Scheme to DSD | Mon Apr 04 08:00:00 IDT 2011 | Mon Apr 04 08:00:00 IDT 2011
2150 | No objection from DSD | Mon Apr 04 08:00:00 IDT 2011 | Fri Jul 08 17:00:00 IDT 2011
2151 | Prepare Temporary Work Design for Cofferdam | Sat Mar 12 08:00:00 IST 2011 | Mon May 16 17:00:00 IDT 2011
2152 | Temp. Works Design Comment & Approval by MTR/DSD | Tue Apr 19 08:00:00 IDT 2011 | Sat Jun 18 17:00:00 IDT 2011
2153 | Issue for Construction (Cofferdam) | Mon May 16 17:00:00 IDT 2011 | Mon May 16 17:00:00 IDT 2011
2154 | Prepare Design for DSD Main Support/Detailed Scheme | Fri Apr 08 08:00:00 IDT 2011 | Sat May 14 17:00:00 IDT 2011
2155 | DSD Main Support Approval by MTR/DSD | Sat May 14 08:00:00 IDT 2011 | Fri Jul 08 17:00:00 IDT 2011
2156 | Issue for Construction | Fri Jun 10 17:00:00 IDT 2011 | Fri Jun 10 17:00:00 IDT 2011
2157 | Pipe/Fitting Procurement | Sat Jun 11 08:00:00 IDT 2011 | Wed Oct 05 17:00:00 IST 2011
2158 | Construction | Mon Feb 28 08:00:00 IST 2011 | Fri Jul 31 17:00:00 IDT 2015
2159 | Cofferdam Reinstatement | Sat Mar 29 08:00:00 IDT 2014 | Thu Jun 19 17:00:00 IDT 2014
2160 | GI works for Rising Main Pile Removal | Mon Feb 28 08:00:00 IST 2011 | Sat Mar 19 17:00:00 IST 2011
2161 | Trial Trench for Existing Utilities | Tue Apr 19 08:00:00 IDT 2011 | Wed May 18 17:00:00 IDT 2011
2162 | Slew Telecom Cable (PCCW702+CATV704) | Sat Apr 30 08:00:00 IDT 2011 | Thu May 12 17:00:00 IDT 2011
2163 | Ground Treatment for Existing Seawall, if any | Tue May 17 08:00:00 IDT 2011 | Wed May 25 17:00:00 IDT 2011
2164 | Sheetpile Installation | Sat May 21 08:00:00 IDT 2011 | Sat Jun 04 17:00:00 IDT 2011
2165 | Northern Rising Main: Install Prebored H-pile (10nos.) | Tue Jun 14 08:00:00 IDT 2011 | Sat Jul 23 17:00:00 IDT 2011
2166 | Southern Rising Main: install Prebored H-pile (10nos.) | Tue Jun 14 08:00:00 IDT 2011 | Sat Jul 23 17:00:00 IDT 2011
2167 | Pile Testing | Mon Aug 01 08:00:00 IDT 2011 | Sat Aug 06 17:00:00 IDT 2011
2168 | Excavate & Expose Bottom of Rising Main (Trial Trench) | Mon Aug 01 08:00:00 IDT 2011 | Mon Aug 22 17:00:00 IDT 2011
2169 | Locate Existing Rising Main & FMO (A) Piles | Mon Aug 08 08:00:00 IDT 2011 | Sat Aug 20 17:00:00 IDT 2011
2170 | Removal FMO Pier A Vertical Piles D/T & Backfilling | Tue Aug 16 08:00:00 IDT 2011 | Thu Aug 25 17:00:00 IDT 2011
2171 | Removal Pier A Vertical Piles U/T & Backfilling | Thu Aug 25 08:00:00 IDT 2011 | Wed Aug 31 17:00:00 IDT 2011
2172 | Excavate to Capping Beam Formation Level | Mon Sep 12 08:00:00 IDT 2011 | Tue Oct 04 17:00:00 IST 2011
2173 | North Temp.Rising Main:Capping Beam | Fri Oct 07 08:00:00 IST 2011 | Sat Oct 29 17:00:00 IST 2011
2174 | South Temp.Rising Main:Capping Beam | Fri Oct 07 08:00:00 IST 2011 | Sat Oct 29 17:00:00 IST 2011
2175 | South Temp.Rising Main Installation+Thrust Block | Mon Oct 31 08:00:00 IST 2011 | Sat Nov 12 17:00:00 IST 2011
2176 | Expose Existing South Pipe | Thu Mar 24 08:00:00 IST 2011 | Wed Nov 02 17:00:00 IST 2011
2177 | Notification for South Rising Main & Flow Stop from DSD Station | Sat Nov 12 17:00:00 IST 2011 | Sat Nov 12 17:00:00 IST 2011
2178 | Diversion Works for Rising Main (South Pipe) | Mon Feb 28 08:00:00 IST 2011 | Fri Mar 11 17:00:00 IST 2011
2179 | North Temp.Rising Main Installation+Thrust Block | Mon Feb 28 08:00:00 IST 2011 | Wed Mar 30 17:00:00 IST 2011
2180 | Expose Existing North Pipe | Mon Mar 14 08:00:00 IST 2011 | Tue Dec 06 17:00:00 IST 2011
2181 | Notification for North Rising Main & Flow Stop from DSD Station | Thu Dec 15 17:00:00 IST 2011 | Thu Dec 15 17:00:00 IST 2011
2182 | Diversion Works for Rising Main (North Pipe) | Tue Nov 01 08:00:00 IST 2011 | Fri Nov 11 17:00:00 IST 2011
2183 | Dismantle Existing Rising Mains | Sat Nov 12 08:00:00 IST 2011 | Fri Nov 18 17:00:00 IST 2011
2184 | Form WorkingPlatform | Tue Jun 21 08:00:00 IDT 2011 | Thu Jul 21 17:00:00 IDT 2011
2185 | Locate Existing Rising Main & FMO (A) Piles | Tue Jun 21 08:00:00 IDT 2011 | Thu Jul 21 17:00:00 IDT 2011
2186 | Removal FMO Pier A Raking Piles DT & Backfilling | Wed Aug 31 08:00:00 IDT 2011 | Mon Nov 14 17:00:00 IST 2011
2187 | Remove Rising Mains Vertical Piles Clash D/T Tunnel & Backfilling | Wed Aug 31 08:00:00 IDT 2011 | Thu Dec 22 17:00:00 IST 2011
2188 | Removal FMO Pier A Raking Piles UT & Backfilling | Sat Oct 29 08:00:00 IST 2011 | Tue May 08 17:00:00 IDT 2012
2189 | Remove Rising Main Vertical Piles Clash U/T Tunnel & Backfilling | Wed Nov 30 08:00:00 IST 2011 | Thu Mar 22 17:00:00 IST 2012
2190 | Remove Working Platform | Tue Apr 17 08:00:00 IDT 2012 | Thu May 03 17:00:00 IDT 2012
2191 | Tie Beams Construction for New Rising Main | Mon Jan 16 08:00:00 IST 2012 | Mon Feb 27 17:00:00 IST 2012
2192 | Notification for South Rising Main & Flow Stop from DSD Station | Mon Oct 07 17:00:00 IDT 2013 | Mon Oct 07 17:00:00 IDT 2013
2193 | Reinstatement Works for Rising Mains (South pipe) | Fri Nov 01 08:00:00 IST 2013 | Tue Dec 31 17:00:00 IST 2013
2194 | Notification for North Rising Main & Flow Stop from DSD Station | Mon Dec 23 17:00:00 IST 2013 | Mon Dec 23 17:00:00 IST 2013
2195 | Reinstatement Works for Rising Mains (North pipe) | Tue Dec 24 08:00:00 IST 2013 | Thu Jan 23 17:00:00 IST 2014
2196 | Place Concrete Surround | Tue Jan 27 08:00:00 IST 2015 | Mon Feb 23 17:00:00 IST 2015
2197 | Utilities Reinstatement | Mon Jun 01 08:00:00 IDT 2015 | Fri Jul 31 17:00:00 IDT 2015
2198 | Rising Main & FMO Pier A Pile Removal (DT) | Sun Mar 13 08:00:00 IST 2011 | Sat Jan 05 17:00:00 IST 2013
2199 | Rising Main & FMO Pier A Pile Removal (UT) | Sun Mar 13 08:00:00 IST 2011 | Sat Sep 07 17:00:00 IDT 2013
2200 | Completion | Thu Sep 01 08:00:00 IDT 2011 | Thu Sep 29 17:00:00 IDT 2011
2201 | Prepare & Submit Draft As-built Drawings | Thu Sep 01 08:00:00 IDT 2011 | Thu Sep 29 17:00:00 IDT 2011
2202 | Prepare & Submit As-built Drawings | Thu Sep 01 08:00:00 IDT 2011 | Thu Sep 29 17:00:00 IDT 2011
2203 | G2 YC2 Culvet - Remove Barrette & Modify Foundation | Mon Feb 28 08:00:00 IST 2011 | Sat Aug 23 17:00:00 IDT 2014
2204 | Stage 1: YC2 Cofferdam Installation | Sun Mar 13 08:00:00 IST 2011 | Wed Aug 17 17:00:00 IDT 2011
2205 | Stage 2: YC2 Barrettes Removal (B15 - DT) | Sun Jun 19 08:00:00 IDT 2011 | Sat Mar 03 17:00:00 IST 2012
2206 | Stage 3: YC2 Barrettes Removal (B13 - UT) | Wed Nov 07 08:00:00 IST 2012 | Wed Nov 21 17:00:00 IST 2012
2207 | Temp.Works Design Submission | Mon Feb 28 08:00:00 IST 2011 | Thu Jun 23 17:00:00 IDT 2011
2208 | Temp. Works Design Preparation | Mon Feb 28 08:00:00 IST 2011 | Mon Apr 25 17:00:00 IDT 2011
2209 | Temp. Works Design Submit to MTR | Wed Mar 23 17:00:00 IST 2011 | Wed Mar 23 17:00:00 IST 2011
2210 | Temp. Works Design Comment by MTR/DSD | Thu Mar 24 08:00:00 IST 2011 | Thu Apr 07 17:00:00 IDT 2011
2211 | Temp. Works Design Re-submission Preparation | Thu Apr 21 08:00:00 IDT 2011 | Thu Jun 23 17:00:00 IDT 2011
2212 | Temp. Works Design Comment & Approval by MTR/DSD | Tue May 10 08:00:00 IDT 2011 | Sun May 22 17:00:00 IDT 2011
2213 | Issue for Construction | Tue Jun 07 08:00:00 IDT 2011 | Tue Jun 07 08:00:00 IDT 2011
2214 | Method Statement Submission and Approval | Mon Feb 28 08:00:00 IST 2011 | Tue Jun 21 17:00:00 IDT 2011
2215 | MS Preparation | Mon Feb 28 08:00:00 IST 2011 | Mon Apr 04 17:00:00 IDT 2011
2216 | MS Submission to MTR | Mon Mar 28 17:00:00 IST 2011 | Mon Mar 28 17:00:00 IST 2011
2217 | MS Comment by MTR/DSD | Tue Mar 29 08:00:00 IST 2011 | Sun May 01 17:00:00 IDT 2011
2218 | MS Re-submission Preparation | Tue Apr 26 08:00:00 IDT 2011 | Wed Jun 01 17:00:00 IDT 2011
2219 | MS Submission to MTR | Wed May 18 17:00:00 IDT 2011 | Wed May 18 17:00:00 IDT 2011
2220 | MS Comment & Approval by MTR/DSD | Thu May 19 08:00:00 IDT 2011 | Tue Jun 21 17:00:00 IDT 2011
2221 | Issue for Construction | Wed Jun 15 17:00:00 IDT 2011 | Wed Jun 15 17:00:00 IDT 2011
2222 | TTM Scheme Submission & Approval | Mon Feb 28 08:00:00 IST 2011 | Sun Aug 21 17:00:00 IDT 2011
2223 | Prepare Temporary Traffic Management | Mon Feb 28 08:00:00 IST 2011 | Wed Mar 23 17:00:00 IST 2011
2224 | TTM reviewed by SLG | Fri Mar 25 08:00:00 IST 2011 | Mon Jun 06 17:00:00 IDT 2011
2225 | Resubmit TTM | Sat Jun 18 08:00:00 IDT 2011 | Mon Jul 25 17:00:00 IDT 2011
2226 | TTM reviewed by SLG | Sun Jun 26 08:00:00 IDT 2011 | Mon Jul 25 17:00:00 IDT 2011
2227 | Notification to RMO | Sun Jul 24 08:00:00 IDT 2011 | Sun Aug 21 17:00:00 IDT 2011
2228 | XP Application & Approval | Sun May 01 08:00:00 IDT 2011 | Fri May 20 17:00:00 IDT 2011
2229 | Implement TTM | Fri Aug 05 17:00:00 IDT 2011 | Fri Aug 05 17:00:00 IDT 2011
2230 | Stage 1 | Mon Feb 28 08:00:00 IST 2011 | Wed Oct 26 17:00:00 IST 2011
2231 | GI works for YC2 Barrette Removal | Mon Feb 28 08:00:00 IST 2011 | Mon Mar 07 17:00:00 IST 2011
2232 | Area 40.4: Tree Transplant by 801 Designated Contractor | Mon Feb 28 08:00:00 IST 2011 | Mon Feb 28 08:00:00 IST 2011
2233 | Shum Mong Rd: Tree Transplant by 801 Designated | Mon Feb 28 08:00:00 IST 2011 | Mon Feb 28 08:00:00 IST 2011
2234 | TTA Stage 0 and 1 for YC2 and Shum Shui Po Pier | Sat Aug 06 08:00:00 IDT 2011 | Tue Sep 06 17:00:00 IDT 2011
2235 | Cofferdam: Sheetpile Installation | Tue Sep 06 08:00:00 IDT 2011 | Thu Sep 22 17:00:00 IDT 2011
2236 | Cofferdam: Excavation + Shoring | Mon Oct 03 08:00:00 IST 2011 | Wed Oct 26 17:00:00 IST 2011
2237 | Backfilling for Cofferdam | Tue Jun 21 08:00:00 IDT 2011 | Tue Jul 26 17:00:00 IDT 2011
2238 | Construct Temp. Pavement | Tue Jun 21 08:00:00 IDT 2011 | Wed Jul 13 17:00:00 IDT 2011
2239 | Stage 1: YC2 Cofferdam Installation | Sun Mar 13 08:00:00 IST 2011 | Wed Aug 17 17:00:00 IDT 2011
2240 | Stage 2 | Sun Jun 19 08:00:00 IDT 2011 | Tue Feb 05 17:00:00 IST 2013
2241 | GI works for YC2 Barrette Removal (Stage 2) | Tue Jun 21 08:00:00 IDT 2011 | Tue Jul 05 17:00:00 IDT 2011
2242 | TTA Stage 2 for Culvert YC2 and Shum Shui Po Pie | Sun Jun 19 08:00:00 IDT 2011 | Wed Jul 06 17:00:00 IDT 2011
2243 | Cofferdam: Sheetpile Installation | Wed Aug 31 08:00:00 IDT 2011 | Mon Oct 24 17:00:00 IST 2011
2244 | Compensation Grout for Culvert | Wed Aug 31 08:00:00 IDT 2011 | Fri Oct 21 17:00:00 IST 2011
2245 | Cofferdam: Excavation + Shoring | Mon Jan 16 08:00:00 IST 2012 | Wed Feb 01 17:00:00 IST 2012
2246 | Remove Culvert Top Slab (saw cut) | Thu Feb 02 08:00:00 IST 2012 | Wed Feb 08 17:00:00 IST 2012
2247 | Install Working Platform & Mini Cofferdam for 1st Cut | Thu Feb 02 08:00:00 IST 2012 | Sat Feb 04 17:00:00 IST 2012
2248 | Barrette Removal (B15) 1st Cut | Sat Feb 11 08:00:00 IST 2012 | Wed Mar 07 17:00:00 IST 2012
2249 | Temp. Base Slab Reinstatement (1st Cut) | Sat Mar 10 08:00:00 IST 2012 | Sat Mar 10 17:00:00 IST 2012
2250 | Remove & Re-install WP Cofferdam for 2nd Cut | Sat Mar 10 08:00:00 IST 2012 | Wed Mar 14 17:00:00 IST 2012
2251 | Barrette Removal (B15) 2nd Cut | Sat Mar 17 08:00:00 IST 2012 | Tue Nov 06 17:00:00 IST 2012
2252 | Barrette Backfilling | Mon Jan 16 08:00:00 IST 2012 | Wed Jan 18 17:00:00 IST 2012
2253 | Culvert Base & Top Slabs Reinstatement | Thu Jan 19 08:00:00 IST 2012 | Wed Nov 07 17:00:00 IST 2012
2254 | Backfill and Road Reinstatement | Wed Jan 09 08:00:00 IST 2013 | Tue Feb 05 17:00:00 IST 2013
2255 | Stage 2: YC2 Barrettes Removal (B15 - DT) | Sun Jun 19 08:00:00 IDT 2011 | Sat Mar 03 17:00:00 IST 2012
2256 | Stage 3 | Wed Oct 31 08:00:00 IST 2012 | Sat Aug 23 17:00:00 IDT 2014
2257 | Compensation grout (after TBM U/T pass through) | Tue Apr 22 08:00:00 IDT 2014 | Fri May 23 17:00:00 IDT 2014
2258 | TTMs Stage 3 for Barrette B13 Removal | Wed Oct 31 08:00:00 IST 2012 | Tue Nov 06 17:00:00 IST 2012
2259 | Remove Culvert Top Slab | Wed Nov 07 08:00:00 IST 2012 | Tue Nov 13 17:00:00 IST 2012
2260 | Install Working Platform & Mini Cofferdam for 1st Cut | Fri Nov 30 08:00:00 IST 2012 | Sat Dec 08 17:00:00 IST 2012
2261 | Barrette Removal (B13) 1st Cut | Sat Nov 10 08:00:00 IST 2012 | Tue Nov 27 17:00:00 IST 2012
2262 | Install Working Platform & Mini Cofferdam for 2nd Cut | Tue Dec 18 08:00:00 IST 2012 | Fri Dec 28 17:00:00 IST 2012
2263 | Barrette Removal (B13) 2nd Cut | Wed Dec 05 08:00:00 IST 2012 | Fri Dec 21 17:00:00 IST 2012
2264 | Barrette Backfill | Fri Dec 21 08:00:00 IST 2012 | Mon Dec 24 17:00:00 IST 2012
2265 | Culvert Base Slab Reinstatement | Thu Dec 27 08:00:00 IST 2012 | Mon Feb 04 17:00:00 IST 2013
2266 | Culvert Top Slab Temp. Reinstatement | Mon Jan 28 08:00:00 IST 2013 | Sat Mar 09 17:00:00 IST 2013
2267 | Top Slab Reinstatement | Sat May 10 08:00:00 IDT 2014 | Wed Jun 25 17:00:00 IDT 2014
2268 | Road Reinstatement / Final TTA | Mon Jun 16 08:00:00 IDT 2014 | Sat Aug 23 17:00:00 IDT 2014
2269 | Stage 3: YC2 Barrettes Removal (B13 - UT) | Wed Nov 07 08:00:00 IST 2012 | Tue Jun 25 17:00:00 IDT 2013
2270 | Completion | Wed May 02 08:00:00 IDT 2012 | Tue May 29 17:00:00 IDT 2012
2271 | Prepare & Submit Draft As-built Drawings | Wed May 02 08:00:00 IDT 2012 | Tue May 29 17:00:00 IDT 2012
2272 | Prepare & Submit As-built Drawings | Wed May 02 08:00:00 IDT 2012 | Tue May 29 17:00:00 IDT 2012
2273 | G3 NC1 DSD Culvert - Remove Barrette | Sat Aug 14 08:00:00 IDT 2010 | Tue Sep 17 17:00:00 IDT 2013
2274 | Barrette Removal B28 & B27 (DT) | Sat Apr 16 08:00:00 IDT 2011 | Wed Aug 08 17:00:00 IDT 2012
2275 | Barrette Removal B24,B21 & B22 (UT) | Sat Apr 16 08:00:00 IDT 2011 | Thu Sep 06 17:00:00 IDT 2012
2276 | Method Statement Submission and Approval | Sat Aug 14 08:00:00 IDT 2010 | Tue Jun 21 17:00:00 IDT 2011
2277 | MS Preparation | Mon Feb 28 08:00:00 IST 2011 | Wed Mar 09 17:00:00 IST 2011
2278 | MS Submission to MTR/DSD | Sat Mar 26 17:00:00 IST 2011 | Sat Mar 26 17:00:00 IST 2011
2279 | MS Comment by MTR/DSD | Sun Mar 27 08:00:00 IST 2011 | Fri Apr 29 17:00:00 IDT 2011
2280 | MS Re-submission Preparation | Sat Aug 14 08:00:00 IDT 2010 | Tue Aug 24 17:00:00 IDT 2010
2281 | MS Submission to MTR/DSD | Wed May 18 17:00:00 IDT 2011 | Wed May 18 17:00:00 IDT 2011
2282 | MS Comment & Approval by MTR/DSD | Thu May 19 08:00:00 IDT 2011 | Tue Jun 21 17:00:00 IDT 2011
2283 | Issue for Construction | Wed Jun 15 17:00:00 IDT 2011 | Wed Jun 15 17:00:00 IDT 2011
2284 | Tree Transplant Application Preparation | Mon Feb 28 08:00:00 IST 2011 | Thu Jun 09 17:00:00 IDT 2011
2285 | Application Submit to LandS Department | Sat Mar 26 17:00:00 IST 2011 | Sat Mar 26 17:00:00 IST 2011
2286 | Application Approval by LandS Department | Sun Mar 27 08:00:00 IST 2011 | Sun Apr 17 17:00:00 IDT 2011
2287 | TTM Scheme Submisssion & Approval | Mon Feb 28 08:00:00 IST 2011 | Sun Aug 21 17:00:00 IDT 2011
2288 | Prepare Temp.Traffic Management (for S.2 &S.2.1) | Mon Feb 28 08:00:00 IST 2011 | Thu Mar 24 17:00:00 IST 2011
2289 | TTM reviewed by SLG | Fri Mar 25 08:00:00 IST 2011 | Mon Jun 06 17:00:00 IDT 2011
2290 | Resubmit TTM | Sat Jun 18 08:00:00 IDT 2011 | Wed Jul 13 17:00:00 IDT 2011
2291 | TTM reviewed by SLG | Sun Jun 26 08:00:00 IDT 2011 | Mon Jul 25 17:00:00 IDT 2011
2292 | Notification to RMO | Sun Jul 24 08:00:00 IDT 2011 | Sun Aug 21 17:00:00 IDT 2011
2293 | XP Application & Approval | Tue May 31 08:00:00 IDT 2011 | Tue Jun 21 17:00:00 IDT 2011
2294 | Implement TTM | Thu Aug 11 17:00:00 IDT 2011 | Thu Aug 11 17:00:00 IDT 2011
2295 | Prepare Temp.Traffic Management(for U/T Group) | Mon Feb 28 08:00:00 IST 2011 | Sat Mar 12 17:00:00 IST 2011
2296 | TTM reviewed by SLG (S.2) | Sun Mar 13 08:00:00 IST 2011 | Sat May 21 17:00:00 IDT 2011
2297 | Notification to RMO | Sun May 22 08:00:00 IDT 2011 | Thu Jun 02 17:00:00 IDT 2011
2298 | Prepare TTMS for Tree Transplant(for D/T Group) | Mon Feb 28 08:00:00 IST 2011 | Fri Jun 17 17:00:00 IDT 2011
2299 | TTM reviewed by SLG (S.2.1) | Sun Mar 13 08:00:00 IST 2011 | Sat May 21 17:00:00 IDT 2011
2300 | Notification to RMO | Sun May 22 08:00:00 IDT 2011 | Thu Jun 02 17:00:00 IDT 2011
2301 | TBM D/T Culvert | Mon Feb 28 08:00:00 IST 2011 | Sat Jan 12 17:00:00 IST 2013
2302 | Works Area 11.21 (Subject to SLG Approval) | Mon Feb 28 08:00:00 IST 2011 | Mon Feb 28 08:00:00 IST 2011
2303 | Works Area 11.31 | Mon Feb 28 08:00:00 IST 2011 | Mon Feb 28 08:00:00 IST 2011
2304 | Works Area 11.32 | Mon Feb 28 08:00:00 IST 2011 | Mon Feb 28 08:00:00 IST 2011
2305 | GI works for NC1 Barrette Removal | Mon Feb 28 08:00:00 IST 2011 | Thu Jun 02 17:00:00 IDT 2011
2306 | Group B Tree Transplant (T9752-54, UC0009-10) Preparation & Transplant | Mon Feb 28 08:00:00 IST 2011 | Sat Apr 30 17:00:00 IDT 2011
2307 | TTA Stage 1 and 2.1 | Thu Apr 14 08:00:00 IDT 2011 | Fri Jun 03 17:00:00 IDT 2011
2308 | ELS Works to Culvert Level | Sat May 07 08:00:00 IDT 2011 | Thu May 26 17:00:00 IDT 2011
2309 | Probing for Existing Barrettes | Thu Apr 14 08:00:00 IDT 2011 | Thu Apr 14 17:00:00 IDT 2011
2310 | Remove Top Slab of Culvert | Tue Nov 01 08:00:00 IST 2011 | Fri Nov 04 17:00:00 IST 2011
2311 | Cofferdam installation and Excavation at B27 | Mon Feb 27 08:00:00 IST 2012 | Sat Mar 17 17:00:00 IST 2012
2312 | Saw Cut Culvert Top Slab at B27 | Mon Mar 19 08:00:00 IST 2012 | Sat Mar 24 17:00:00 IST 2012
2313 | Temp. Working Platform for Barrette Removal | Mon Mar 26 08:00:00 IST 2012 | Sat Apr 14 17:00:00 IDT 2012
2314 | Barrette Removal (B27) | Wed Nov 14 08:00:00 IST 2012 | Wed Jan 02 17:00:00 IST 2013
2315 | Barrette Backfilling | Thu Jan 03 08:00:00 IST 2013 | Sat Jan 05 17:00:00 IST 2013
2316 | Reinstate Culvert Base Slab | Thu Nov 15 08:00:00 IST 2012 | Sat Jan 12 17:00:00 IST 2013
2317 | Barrette Removal (B28) | Wed Jan 04 08:00:00 IST 2012 | Wed Feb 22 17:00:00 IST 2012
2318 | Barrette Backfilling | Tue Nov 01 08:00:00 IST 2011 | Thu Nov 03 17:00:00 IST 2011
2319 | Reinstate Culvert Base Slab | Sat Nov 26 08:00:00 IST 2011 | Wed Dec 28 17:00:00 IST 2011
2320 | Install Temp.Cover at Culvert Top Slab | Tue Nov 01 08:00:00 IST 2011 | Wed Nov 30 17:00:00 IST 2011
2321 | Temp.Backfill & Reinstate Pavement | Tue Jun 21 08:00:00 IDT 2011 | Mon Jul 04 17:00:00 IDT 2011
2322 | TTA Stage 3 | Tue Jun 21 08:00:00 IDT 2011 | Wed Jun 22 17:00:00 IDT 2011
2323 | TBM U/T Culvert | Mon Feb 28 08:00:00 IST 2011 | Tue Sep 17 17:00:00 IDT 2013
2324 | Group B Tree Transplant (T9752-54,T8836-37, UC0009-10)Preparation & Transplant | Mon Feb 28 08:00:00 IST 2011 | Thu Apr 28 17:00:00 IDT 2011
2325 | Group D Tree Transplant (T8838,T8843-44) Preparation & Transplant | Mon Feb 28 08:00:00 IST 2011 | Wed Jun 29 17:00:00 IDT 2011
2326 | Tree Transplant Complete by 801 Designated Contractor | Mon Feb 28 08:00:00 IST 2011 | Mon Feb 28 08:00:00 IST 2011
2327 | TTMS Implementation | Mon Feb 28 08:00:00 IST 2011 | Sat Mar 05 17:00:00 IST 2011
2328 | Trial Trench to Expose Existing U/G Utiltiies | Mon Mar 07 08:00:00 IST 2011 | Sat Mar 19 17:00:00 IST 2011
2329 | Slew 132kV Cable (CLP207) | Thu Apr 21 08:00:00 IDT 2011 | Mon Aug 08 17:00:00 IDT 2011
2330 | Slew Telecom Cable (CATV206&PCCW203) | Tue May 03 08:00:00 IDT 2011 | Wed May 18 17:00:00 IDT 2011
2331 | Probing for Existing Barrettes | Mon Apr 11 08:00:00 IDT 2011 | Mon Apr 11 17:00:00 IDT 2011
2332 | ELS for Roof Access | Thu May 19 08:00:00 IDT 2011 | Wed Jun 15 17:00:00 IDT 2011
2333 | Remove Top Slab of Culvert | Mon Mar 28 08:00:00 IST 2011 | Sat Nov 05 17:00:00 IST 2011
2334 | Temp. Working Platform for Barrette Removal | Tue Nov 08 08:00:00 IST 2011 | Sat Nov 12 17:00:00 IST 2011
2335 | Barrette Removal (B24) | Tue Dec 06 08:00:00 IST 2011 | Fri Jan 13 17:00:00 IST 2012
2336 | Barrette Backfilling | Tue Nov 01 08:00:00 IST 2011 | Wed Nov 02 17:00:00 IST 2011
2337 | Reinstate Culvert Base Slab | Tue Nov 01 08:00:00 IST 2011 | Tue Nov 29 17:00:00 IST 2011
2338 | Remove Crane Platform & Reinstate Culvert Top Slab | Tue Jun 21 08:00:00 IDT 2011 | Mon Aug 08 17:00:00 IDT 2011
2339 | Slew 11kV Cable & Connection (CLP219) | Tue Jun 21 08:00:00 IDT 2011 | Mon Aug 01 17:00:00 IDT 2011
2340 | Divert 400D&315D Low Pressure Gas Main (GAS206&207) | Tue Jun 21 08:00:00 IDT 2011 | Thu Jul 14 17:00:00 IDT 2011
2341 | Divert 200D Freshwater Main (FW211) | Tue Jun 21 08:00:00 IDT 2011 | Wed Aug 03 17:00:00 IDT 2011
2342 | Divert 150D Saltwater Main (SW207) | Tue Jun 21 08:00:00 IDT 2011 | Mon Jun 27 17:00:00 IDT 2011
2343 | Slew 400kV Cable Group | Fri Jan 20 08:00:00 IST 2012 | Mon Jan 30 17:00:00 IST 2012
2344 | Preparation Work for TTMS Stage 4 | Mon Jan 30 08:00:00 IST 2012 | Thu Feb 09 17:00:00 IST 2012
2345 | Implement TTMS Stage 4 | Sat Feb 25 08:00:00 IST 2012 | Sat Feb 25 17:00:00 IST 2012
2346 | Drive Sheetpile for Barrette Removal (B21 & B22) | Sat Feb 25 08:00:00 IST 2012 | Fri Mar 02 17:00:00 IST 2012
2347 | ELS to Top Slab of Culvert | Sat Mar 17 08:00:00 IST 2012 | Thu Mar 29 17:00:00 IST 2012
2348 | Barrette Removal (B21) | Thu Nov 01 08:00:00 IST 2012 | Mon Nov 26 17:00:00 IST 2012
2349 | Barrette Backfilling | Wed Dec 19 08:00:00 IST 2012 | Wed Dec 19 17:00:00 IST 2012
2350 | Reinstate Culvert Base Slab | Tue Dec 11 08:00:00 IST 2012 | Sat Jan 12 17:00:00 IST 2013
2351 | Barrette Removal (B22) | Thu Nov 01 08:00:00 IST 2012 | Wed Dec 05 17:00:00 IST 2012
2352 | Barrette Backfilling | Thu Dec 06 08:00:00 IST 2012 | Fri Dec 07 17:00:00 IST 2012
2353 | Reinstate Culvert Base Slab | Tue Dec 11 08:00:00 IST 2012 | Sat Jan 12 17:00:00 IST 2013
2354 | 4nos.Pre-bored H Pile Installallation | Mon Jan 14 08:00:00 IST 2013 | Thu Feb 28 17:00:00 IST 2013
2355 | Band Beam Construction for Connect Pile & Box Culvert | Fri Mar 01 08:00:00 IST 2013 | Thu Mar 28 17:00:00 IST 2013
2356 | Tie-beam Curing & Load Transfer from Box Culvert to Temp.Pile | Tue Apr 02 08:00:00 IDT 2013 | Mon Apr 29 17:00:00 IDT 2013
2357 | Permanent Reinstate Culvert Top Slab | Tue Apr 30 08:00:00 IDT 2013 | Fri Aug 02 17:00:00 IDT 2013
2358 | Permanent Reinstatement for DN200 FW Main | Wed Nov 28 08:00:00 IST 2012 | Sat Jan 05 17:00:00 IST 2013
2359 | Permanent Reinstatement for DN400 Gas Main | Sat Dec 01 08:00:00 IST 2012 | Sat Dec 22 17:00:00 IST 2012
2360 | Permanent Reinstatement for CLP 11kV Cables | Mon Dec 24 08:00:00 IST 2012 | Wed Jan 23 17:00:00 IST 2013
2361 | Permanent Reinstatement for CLP 400kV Cables | Thu Jan 24 08:00:00 IST 2013 | Thu Feb 07 17:00:00 IST 2013
2362 | Permanent Reinstatement for Telecom Cables | Mon Mar 18 08:00:00 IST 2013 | Thu Mar 28 17:00:00 IST 2013
2363 | Backfilling & Road Reinstatement | Sat Aug 17 08:00:00 IDT 2013 | Tue Sep 17 17:00:00 IDT 2013
2364 | Completion | Fri Jun 01 08:00:00 IDT 2012 | Fri Jun 29 17:00:00 IDT 2012
2365 | Prepare & Submit Draft As-built Drawings | Fri Jun 01 08:00:00 IDT 2012 | Fri Jun 29 17:00:00 IDT 2012
2366 | Prepare & Submit As-built Drawings | Fri Jun 01 08:00:00 IDT 2012 | Fri Jun 29 17:00:00 IDT 2012
2367 | Box Culvert FS1 Barrettes Removal | Mon Feb 28 08:00:00 IST 2011 | Sat Oct 10 17:00:00 IDT 2015
2368 | Underpinning Works for FS1 / Barrettes Removal | Wed Aug 31 08:00:00 IDT 2011 | Tue Dec 06 17:00:00 IST 2011
2369 | Temp. Works Design Submission | Mon Feb 28 08:00:00 IST 2011 | Sun Jul 17 17:00:00 IDT 2011
2370 | Temp. Works Design Preparation | Mon Feb 28 08:00:00 IST 2011 | Wed Apr 13 17:00:00 IDT 2011
2371 | Temp. Works Design Submit to MTR | Mon Mar 28 08:00:00 IST 2011 | Mon Mar 28 08:00:00 IST 2011
2372 | Temp. Works Design Comment by MTR/DSD | Mon Mar 28 08:00:00 IST 2011 | Mon Apr 11 17:00:00 IDT 2011
2373 | Temp. Works Design Re-submission Preparation | Tue Apr 26 08:00:00 IDT 2011 | Sat May 14 17:00:00 IDT 2011
2374 | Temp. Works Design Comment & Approval by MTR/DSD | Thu May 19 08:00:00 IDT 2011 | Sun Jul 17 17:00:00 IDT 2011
2375 | Issue for Construction | Wed Jun 15 17:00:00 IDT 2011 | Wed Jun 15 17:00:00 IDT 2011
2376 | Method Statement Submission and Approval | Mon Feb 28 08:00:00 IST 2011 | Wed Jun 15 17:00:00 IDT 2011
2377 | MS Preparation | Mon Feb 28 08:00:00 IST 2011 | Wed Mar 30 17:00:00 IST 2011
2378 | MS Submission to MTR | Sat Mar 26 17:00:00 IST 2011 | Sat Mar 26 17:00:00 IST 2011
2379 | MS Comment by MTR/DSD | Sun Mar 27 08:00:00 IST 2011 | Fri Apr 22 17:00:00 IDT 2011
2380 | MS Re-submission Preparation | Tue Apr 26 08:00:00 IDT 2011 | Sat May 28 17:00:00 IDT 2011
2381 | MS Submission to MTR | Wed May 18 17:00:00 IDT 2011 | Wed May 18 17:00:00 IDT 2011
2382 | MS Comment & Approval by MTR/DSD | Thu May 19 08:00:00 IDT 2011 | Tue Jun 14 17:00:00 IDT 2011
2383 | Issue for Construction | Wed Jun 15 17:00:00 IDT 2011 | Wed Jun 15 17:00:00 IDT 2011
2384 | Utilities Diversion
2385 | Underpinning Works for FS1 | Fri May 06 17:00:00 IDT 2011 | Thu Aug 13 17:00:00 IDT 2015
2386 | Area 39.1 Tree Transplant by 801 Designated Contractor | Fri May 06 17:00:00 IDT 2011 | Fri May 06 17:00:00 IDT 2011
2387 | Soft Excavation to S1 (~+4.5mPD) | Tue Oct 18 08:00:00 IST 2011 | Fri Oct 21 17:00:00 IST 2011
2388 | Soft Excavation & Expose Culvert FS1(~-2.0mPD) | Wed Aug 31 08:00:00 IDT 2011 | Wed Sep 14 17:00:00 IDT 2011
2389 | Cast in-situ RC Wall to Support Existing Ground (adjacent B14 & B19) | Wed Aug 31 08:00:00 IDT 2011 | Mon Sep 05 17:00:00 IDT 2011
2390 | Setup & Install Four Prebored H-piles (adjacent to Existing B17) | Wed Aug 31 08:00:00 IDT 2011 | Thu Sep 15 17:00:00 IDT 2011
2391 | Soft Excavation to 2m underneath Culvert | Tue Sep 06 08:00:00 IDT 2011 | Mon Sep 19 17:00:00 IDT 2011
2392 | Installation of Corbel Beams either Side of Culvert | Wed Aug 31 08:00:00 IDT 2011 | Tue Sep 06 17:00:00 IDT 2011
2393 | Steel Beam Installation underneath Corbel Beams & Connect to H-pile | Wed Aug 31 08:00:00 IDT 2011 | Tue Sep 06 17:00:00 IDT 2011
2394 | Loading Transfer with Jacks | Wed Aug 31 08:00:00 IDT 2011 | Wed Aug 31 17:00:00 IDT 2011
2395 | Excavation to foundation level for B19 | Wed Aug 31 08:00:00 IDT 2011 | Fri Dec 16 17:00:00 IST 2011
2396 | Excavation to foundation level for B14 | Fri Feb 17 08:00:00 IST 2012 | Sat Jun 16 17:00:00 IDT 2012
2397 | Barettes Breaking (B15-B18) | Wed Aug 31 08:00:00 IDT 2011 | Wed Dec 14 17:00:00 IST 2011
2398 | Install Lagging Wall (at West & East D-wall) | Wed Aug 31 08:00:00 IDT 2011 | Fri Nov 11 17:00:00 IST 2011
2399 | Backfilling, Compaction & Testing | Sat Jul 11 08:00:00 IDT 2015 | Wed Aug 05 17:00:00 IDT 2015
2400 | Disconnected Steel H-pile inside Tunnel Box | Thu Aug 06 08:00:00 IDT 2015 | Thu Aug 13 17:00:00 IDT 2015
2401 | Completion | Fri Aug 14 08:00:00 IDT 2015 | Sat Oct 10 17:00:00 IDT 2015
2402 | Prepare & Submit Draft As-built Drawings | Fri Aug 14 08:00:00 IDT 2015 | Thu Sep 10 17:00:00 IDT 2015
2403 | Prepare & Submit As-built Drawings | Fri Sep 11 08:00:00 IDT 2015 | Sat Oct 10 17:00:00 IDT 2015
2404 | Cost Centre H - Piling Works to Footbridges | Mon Feb 28 08:00:00 IST 2011 | Mon Nov 23 17:00:00 IST 2015
2405 | IPS Milestones | Mon Feb 28 08:00:00 IST 2011 | Thu Sep 24 17:00:00 IDT 2015
2406 | General | Mon Feb 28 08:00:00 IST 2011 | Thu Sep 24 17:00:00 IDT 2015
2407 | Obtain SLG of TTMS for Footbridge Piling Start | Mon Feb 28 08:00:00 IST 2011 | Mon Feb 28 08:00:00 IST 2011
2408 | Complete 9% of Piles | Fri Nov 30 08:00:00 IST 2012 | Fri Nov 30 08:00:00 IST 2012
2409 | Complete 60% of Piles | Sat May 18 17:00:00 IDT 2013 | Sat May 18 17:00:00 IDT 2013
2410 | Complete 70% of Piles | Mon Jul 27 17:00:00 IDT 2015 | Mon Jul 27 17:00:00 IDT 2015
2411 | Complete 100% Piles except Pile cap 28 | Fri Jun 26 17:00:00 IDT 2015 | Fri Jun 26 17:00:00 IDT 2015
2412 | Complete All Works | Thu Sep 24 17:00:00 IDT 2015 | Thu Sep 24 17:00:00 IDT 2015
2413 | Construction | Mon Feb 28 08:00:00 IST 2011 | Mon Nov 23 17:00:00 IST 2015
2414 | Footbridge No.1 (Hing Wai St. West) | Fri Aug 31 08:00:00 IDT 2012 | Sat Sep 07 17:00:00 IDT 2013
2415 | Footbridge No.2 (Tonkin St. West) (2 out of 17 nos.) | Wed Sep 12 08:00:00 IDT 2012 | Wed Feb 13 17:00:00 IST 2013
2416 | Footbridge No.3 (Yen Chow St. West) | Mon May 06 08:00:00 IDT 2013 | Wed Dec 11 17:00:00 IST 2013
2417 | Method Statement Submission and Approval | Mon Feb 28 08:00:00 IST 2011 | Fri Jan 04 17:00:00 IST 2013
2418 | MS Preparation | Mon Feb 28 08:00:00 IST 2011 | Fri Mar 25 17:00:00 IST 2011
2419 | MS Submission to CEDD | Mon Mar 28 17:00:00 IST 2011 | Mon Mar 28 17:00:00 IST 2011
2420 | MS Comment by CEDD / Alt. Design Review with CEDD | Tue Mar 29 08:00:00 IST 2011 | Fri Apr 29 17:00:00 IDT 2011
2421 | MS Re-submission Preparation | Thu Nov 08 08:00:00 IST 2012 | Thu Dec 06 17:00:00 IST 2012
2422 | MS Submission to CEDD | Thu Dec 06 17:00:00 IST 2012 | Thu Dec 06 17:00:00 IST 2012
2423 | MS Comment & Approval by CEDD | Fri Dec 07 08:00:00 IST 2012 | Thu Jan 03 17:00:00 IST 2013
2424 | Issue for Construction | Fri Jan 04 17:00:00 IST 2013 | Fri Jan 04 17:00:00 IST 2013
2425 | TTM Scheme Submission & Approval | Mon Feb 28 08:00:00 IST 2011 | Mon Aug 22 17:00:00 IDT 2011
2426 | Prepare Temporary Traffic Management | Mon Feb 28 08:00:00 IST 2011 | Wed Mar 23 17:00:00 IST 2011
2427 | TTM reviewed by SLG | Sat Mar 26 08:00:00 IST 2011 | Fri Apr 29 17:00:00 IDT 2011
2428 | Resubmit TTM | Mon Feb 28 08:00:00 IST 2011 | Sat Apr 02 17:00:00 IDT 2011
2429 | TTM reviewed by SLG | Mon Feb 28 08:00:00 IST 2011 | Fri Apr 08 17:00:00 IDT 2011
2430 | Notification to RMO | Mon Feb 28 08:00:00 IST 2011 | Sun Aug 07 17:00:00 IDT 2011
2431 | XP Application & Approval | Thu Jun 02 08:00:00 IDT 2011 | Wed Jul 27 17:00:00 IDT 2011
2432 | Implement TTM | Mon Aug 22 17:00:00 IDT 2011 | Mon Aug 22 17:00:00 IDT 2011
2433 | Footbridge No.1 (Hing Wai St. West) | Mon Feb 28 08:00:00 IST 2011 | Fri May 24 17:00:00 IDT 2013
2434 | Temp.Traffic Diversion | Mon Feb 28 08:00:00 IST 2011 | Mon Mar 07 17:00:00 IST 2011
2435 | Temp. Pedestrians Barriers Erection | Mon Feb 28 08:00:00 IST 2011 | Mon Mar 07 17:00:00 IST 2011
2436 | Trial Trench & Record | Mon Feb 28 08:00:00 IST 2011 | Tue Aug 23 17:00:00 IDT 2011
2437 | Area A PC6, PC7 & PC8 | Fri Aug 31 08:00:00 IDT 2012 | Mon Apr 22 17:00:00 IDT 2013
2438 | Trial Pit | Fri Aug 31 08:00:00 IDT 2012 | Fri Sep 21 17:00:00 IDT 2012
2439 | Utilities Diversion | Sat Sep 22 08:00:00 IDT 2012 | Fri Sep 28 17:00:00 IST 2012
2440 | Confirmation of design by CEDD | Sat Jan 05 08:00:00 IST 2013 | Fri Jan 11 17:00:00 IST 2013
2441 | Implementation of TTMS & Site setup | Fri Jan 11 08:00:00 IST 2013 | Mon Jan 21 17:00:00 IST 2013
2442 | Piling works (18 nos. Pre-bored H-piles) | Mon Jan 21 08:00:00 IST 2013 | Mon Apr 22 17:00:00 IDT 2013
2443 | Area B PC4, PC5, PC10 & PC11 | Fri Dec 14 08:00:00 IST 2012 | Fri May 24 17:00:00 IDT 2013
2444 | Trial Pit | Fri Dec 14 08:00:00 IST 2012 | Fri Dec 21 17:00:00 IST 2012
2445 | Utilities Diversion | Sat Dec 22 08:00:00 IST 2012 | Wed Jan 02 17:00:00 IST 2013
2446 | Site setup | Thu Jan 03 08:00:00 IST 2013 | Sat Jan 05 17:00:00 IST 2013
2447 | Piling works (26 nos. Pre-bored H-piles) | Mon Jan 07 08:00:00 IST 2013 | Fri May 24 17:00:00 IDT 2013
2448 | Footbridge No.2 (Tonkin St. West) | Mon Feb 28 08:00:00 IST 2011 | Tue May 19 17:00:00 IDT 2015
2449 | Temp.Traffic Diversion | Mon Feb 28 08:00:00 IST 2011 | Tue Mar 08 17:00:00 IST 2011
2450 | Temp. Pedestrians Barriers Erection | Mon Feb 28 08:00:00 IST 2011 | Mon Mar 07 17:00:00 IST 2011
2451 | Trial Trench & Record | Mon Feb 28 08:00:00 IST 2011 | Sat Mar 12 17:00:00 IST 2011
2452 | Area C PC22, PC23 & PC24 | Wed Sep 12 08:00:00 IDT 2012 | Tue May 19 17:00:00 IDT 2015
2453 | Implementation of TTMS & Site Clearance | Wed Sep 12 08:00:00 IDT 2012 | Fri Sep 21 17:00:00 IDT 2012
2454 | Trial Pit | Fri Sep 21 08:00:00 IDT 2012 | Mon Oct 08 17:00:00 IST 2012
2455 | Utilities Diversion & Protection | Mon Oct 08 08:00:00 IST 2012 | Fri Oct 26 17:00:00 IST 2012
2456 | Site formation | Thu Nov 01 08:00:00 IST 2012 | Wed Nov 14 17:00:00 IST 2012
2457 | Site Setup | Wed Nov 14 08:00:00 IST 2012 | Tue Nov 20 17:00:00 IST 2012
2458 | FB2 - Piling works (2 nos. Pre-bored H-piles) | Sat Dec 01 08:00:00 IST 2012 | Fri Dec 14 17:00:00 IST 2012
2459 | FB2 - Piling works (6 nos. Pre-bored H-piles) | Mon Feb 09 08:00:00 IST 2015 | Tue May 19 17:00:00 IDT 2015
2460 | Footbridge No.3 (Yen Chow St.West) | Mon Feb 28 08:00:00 IST 2011 | Thu Sep 24 17:00:00 IDT 2015
2461 | Temp.Traffic Diversion | Mon Feb 28 08:00:00 IST 2011 | Mon Mar 07 17:00:00 IST 2011
2462 | Temp. Steel Decking & Barrier for Pedestrians | Mon Feb 28 08:00:00 IST 2011 | Mon Mar 07 17:00:00 IST 2011
2463 | Trial Trench & Record | Mon Feb 28 08:00:00 IST 2011 | Tue Jul 05 17:00:00 IDT 2011
2464 | Area D PC25, PC26 & PC27 | Mon Nov 12 08:00:00 IST 2012 | Fri May 31 17:00:00 IDT 2013
2465 | Implementation of TTMS & Site Clearance | Mon Nov 12 08:00:00 IST 2012 | Sat Nov 17 17:00:00 IST 2012
2466 | Trial pit to expose utilities | Mon Nov 19 08:00:00 IST 2012 | Sat Nov 24 17:00:00 IST 2012
2467 | Utilities Diversion & Protection | Fri Feb 15 08:00:00 IST 2013 | Sat Mar 02 17:00:00 IST 2013
2468 | Implementation of TTMS | Fri Feb 08 08:00:00 IST 2013 | Mon Mar 25 17:00:00 IST 2013
2469 | Site Setup | Fri Mar 01 08:00:00 IST 2013 | Fri Mar 08 17:00:00 IST 2013
2470 | FB3a - Piling works (8 nos. Pre-bored H-piles) | Tue Apr 02 08:00:00 IDT 2013 | Fri May 31 17:00:00 IDT 2013
2471 | Area E PC28 | Thu Aug 22 08:00:00 IDT 2013 | Thu Sep 24 17:00:00 IDT 2015
2472 | Implementation of TTMS | Thu Aug 22 08:00:00 IDT 2013 | Thu Aug 22 17:00:00 IDT 2013
2473 | Trial Pit | Fri Aug 23 08:00:00 IDT 2013 | Fri Sep 06 17:00:00 IDT 2013
2474 | Utilities Diversion & Protection | Sat Sep 07 08:00:00 IDT 2013 | Tue Sep 24 17:00:00 IDT 2013
2475 | Site formation [Pending for further instruction by MTR] | Mon Jun 01 08:00:00 IDT 2015 | Sat Jun 06 17:00:00 IDT 2015
2476 | Site Setup [Pending for further instruction by MTR] | Sat Jun 06 08:00:00 IDT 2015 | Mon Jun 15 17:00:00 IDT 2015
2477 | FB3b - Piling works (18 nos. Pre-bored H-piles) [Pending for further instruction by MTR] | Mon Jun 15 08:00:00 IDT 2015 | Thu Sep 24 17:00:00 IDT 2015
2478 | Completion | Fri Sep 25 08:00:00 IDT 2015 | Mon Nov 23 17:00:00 IST 2015
2479 | Prepare & Submit Draft As-built Drawings | Fri Sep 25 08:00:00 IDT 2015 | Mon Oct 26 17:00:00 IST 2015
2480 | Prepare & Submit As-built Drawings | Tue Oct 27 08:00:00 IST 2015 | Mon Nov 23 17:00:00 IST 2015
2481 | Cost Centre I3 (Option) HD's Entrustment Works - Carpark/Welfare Block | Sun May 31 08:00:00 IDT 2015 | Thu Apr 07 17:00:00 IDT 2016
2482 | IPS Milestones | Wed Nov 18 17:00:00 IST 2015 | Thu Feb 04 17:00:00 IST 2016
2483 | General | Wed Nov 18 17:00:00 IST 2015 | Thu Feb 04 17:00:00 IST 2016
2484 | Complete 50% Carpark/Welfare Facilities Podium Foundation | Wed Nov 18 17:00:00 IST 2015 | Wed Nov 18 17:00:00 IST 2015
2485 | Complete All Works | Thu Feb 04 17:00:00 IST 2016 | Thu Feb 04 17:00:00 IST 2016
2486 | Method Statement Submission and Approval | Tue Jun 30 08:00:00 IDT 2015 | Thu Oct 29 17:00:00 IST 2015
2487 | Method Statement Submission and Approval | Tue Jun 30 08:00:00 IDT 2015 | Thu Oct 29 17:00:00 IST 2015
2488 | MS Preparation | Tue Jun 30 08:00:00 IDT 2015 | Fri Jul 31 17:00:00 IDT 2015
2489 | MS Submission to MTR | Fri Jul 31 17:00:00 IDT 2015 | Fri Jul 31 17:00:00 IDT 2015
2490 | MS Comment by MTR | Sat Aug 01 08:00:00 IDT 2015 | Fri Aug 28 17:00:00 IDT 2015
2491 | MS Re-submission Preparation | Sat Aug 29 08:00:00 IDT 2015 | Wed Sep 30 17:00:00 IDT 2015
2492 | MS Submission to MTR | Wed Sep 30 17:00:00 IDT 2015 | Wed Sep 30 17:00:00 IDT 2015
2493 | MS Comment & Approval by MTR | Thu Oct 01 08:00:00 IDT 2015 | Wed Oct 28 17:00:00 IST 2015
2494 | Issue for Construction | Thu Oct 29 17:00:00 IST 2015 | Thu Oct 29 17:00:00 IST 2015
2495 | Construction | Sun May 31 08:00:00 IDT 2015 | Thu Apr 07 17:00:00 IDT 2016
2496 | Raft Footing Construction | Sun May 31 08:00:00 IDT 2015 | Thu Feb 04 17:00:00 IST 2016
2497 | Latest Exercising Date - Carpark/Welfare Block | Sun May 31 08:00:00 IDT 2015 | Sun May 31 08:00:00 IDT 2015
2498 | Raft Footing Construction | Fri Oct 30 08:00:00 IST 2015 | Thu Dec 10 17:00:00 IST 2015
2499 | U/G Drainage /Utilities | Fri Dec 11 08:00:00 IST 2015 | Sat Jan 09 17:00:00 IST 2016
2500 | Backfilling & Compaction (up to ground level +5.5mPD) | Mon Jan 11 08:00:00 IST 2016 | Thu Feb 04 17:00:00 IST 2016
2501 | Completion | Fri Feb 05 08:00:00 IST 2016 | Thu Apr 07 17:00:00 IDT 2016
2502 | Prepare & Submit Draft As-built Drawings | Fri Feb 05 08:00:00 IST 2016 | Mon Mar 07 17:00:00 IST 2016
2503 | Prepare & Submit As-built Drawings | Tue Mar 08 08:00:00 IST 2016 | Thu Apr 07 17:00:00 IDT 2016
2504 | Cost Centre I4 (Option) HD's Entrustment Works - Podium Shop | Sun May 31 08:00:00 IDT 2015 | Thu Feb 25 17:00:00 IST 2016
2505 | IPS Milestones | Sun Aug 02 17:00:00 IDT 2015 | Thu Dec 24 17:00:00 IST 2015
2506 | General | Sun Aug 02 17:00:00 IDT 2015 | Thu Dec 24 17:00:00 IST 2015
2507 | Complete 50% Podium Shop Foundation | Sun Aug 02 17:00:00 IDT 2015 | Sun Aug 02 17:00:00 IDT 2015
2508 | Complete All Works | Thu Dec 24 17:00:00 IST 2015 | Thu Dec 24 17:00:00 IST 2015
2509 | Method Statement Submission and Approval | Tue Jun 30 08:00:00 IDT 2015 | Thu Oct 29 17:00:00 IST 2015
2510 | Method Statement Submission and Approval | Tue Jun 30 08:00:00 IDT 2015 | Thu Oct 29 17:00:00 IST 2015
2511 | MS Preparation | Tue Jun 30 08:00:00 IDT 2015 | Fri Jul 31 17:00:00 IDT 2015
2512 | MS Submission to HD/ICU | Fri Jul 31 17:00:00 IDT 2015 | Fri Jul 31 17:00:00 IDT 2015
2513 | MS Comment by HD/ICU | Sat Aug 01 08:00:00 IDT 2015 | Fri Aug 28 17:00:00 IDT 2015
2514 | MS Re-submission Preparation | Sat Aug 29 08:00:00 IDT 2015 | Wed Sep 30 17:00:00 IDT 2015
2515 | MS Submission to HD/ICU | Wed Sep 30 17:00:00 IDT 2015 | Wed Sep 30 17:00:00 IDT 2015
2516 | MS Comment & Approval by HD/ICU | Thu Oct 01 08:00:00 IDT 2015 | Wed Oct 28 17:00:00 IST 2015
2517 | Issue for Construction | Thu Oct 29 17:00:00 IST 2015 | Thu Oct 29 17:00:00 IST 2015
2518 | Construction | Sun May 31 08:00:00 IDT 2015 | Thu Feb 25 17:00:00 IST 2016
2519 | General | Sun May 31 08:00:00 IDT 2015 | Thu Dec 24 17:00:00 IST 2015
2520 | Latest Exercising Date - Podium Shop | Sun May 31 08:00:00 IDT 2015 | Sun May 31 08:00:00 IDT 2015
2521 | Foundation Construction | Fri Oct 30 08:00:00 IST 2015 | Thu Nov 19 17:00:00 IST 2015
2522 | U/G Drainage /Utilities | Fri Nov 20 08:00:00 IST 2015 | Thu Dec 10 17:00:00 IST 2015
2523 | Backfilling & Compaction (up to ground level +5.5mPD) | Fri Dec 11 08:00:00 IST 2015 | Thu Dec 24 17:00:00 IST 2015
2524 | Completion | Mon Dec 28 08:00:00 IST 2015 | Thu Feb 25 17:00:00 IST 2016
2525 | Prepare & Submit Draft As-built Drawings | Mon Dec 28 08:00:00 IST 2015 | Mon Jan 25 17:00:00 IST 2016
2526 | Prepare & Submit As-built Drawings | Tue Jan 26 08:00:00 IST 2016 | Thu Feb 25 17:00:00 IST 2016
2527 | Cost Centre I5 (Option) HD's Entrustment Works - Bored Piles to Elevated Walkway | Mon Feb 28 08:00:00 IST 2011 | Thu May 01 17:00:00 IDT 2014
2528 | IPS Milestones | Tue Oct 08 17:00:00 IDT 2013 | Thu Oct 24 17:00:00 IDT 2013
2529 | General | Tue Oct 08 17:00:00 IDT 2013 | Thu Oct 24 17:00:00 IDT 2013
2530 | Complete 4 nos. of Bored Piles (4 of 5 piles) | Tue Oct 08 17:00:00 IDT 2013 | Tue Oct 08 17:00:00 IDT 2013
2531 | Complete All Works | Thu Oct 24 17:00:00 IDT 2013 | Thu Oct 24 17:00:00 IDT 2013
2532 | Method Statement Submission and Approval | Mon May 06 08:00:00 IDT 2013 | Thu Jul 25 17:00:00 IDT 2013
2533 | Method Statement Submission and Approval | Mon May 06 08:00:00 IDT 2013 | Thu Jul 25 17:00:00 IDT 2013
2534 | MS Preparation | Mon May 06 08:00:00 IDT 2013 | Wed Jun 05 17:00:00 IDT 2013
2535 | MS Submission to HD/ICU | Wed Jun 05 17:00:00 IDT 2013 | Wed Jun 05 17:00:00 IDT 2013
2536 | MS Comment by HD/ICU | Thu Jun 06 08:00:00 IDT 2013 | Wed Jul 03 17:00:00 IDT 2013
2537 | MS Re-submission Preparation | Fri Jun 14 08:00:00 IDT 2013 | Tue Jul 16 17:00:00 IDT 2013
2538 | MS Submission to HD/ICU | Thu Jun 27 17:00:00 IDT 2013 | Thu Jun 27 17:00:00 IDT 2013
2539 | MS Comment & Approval by HD/ICU | Fri Jun 28 08:00:00 IDT 2013 | Thu Jul 25 17:00:00 IDT 2013
2540 | Issue for Construction | Sat Jun 29 17:00:00 IDT 2013 | Sat Jun 29 17:00:00 IDT 2013
2541 | Construction | Mon Feb 28 08:00:00 IST 2011 | Thu May 01 17:00:00 IDT 2014
2542 | General | Mon Feb 28 08:00:00 IST 2011 | Thu May 01 17:00:00 IDT 2014
2543 | Latest Exercising Date - Bored Piles | Mon Feb 28 08:00:00 IST 2011 | Mon Feb 28 08:00:00 IST 2011
2544 | Diversion of existing drain | Mon May 06 08:00:00 IDT 2013 | Wed Jun 05 17:00:00 IDT 2013
2545 | 1st no. Bored Pile P6 Construction | Tue Jul 02 08:00:00 IDT 2013 | Wed Jul 31 17:00:00 IDT 2013
2546 | 2nd no. Bored Pile P3 Construction | Wed Jul 24 08:00:00 IDT 2013 | Thu Aug 22 17:00:00 IDT 2013
2547 | 3rd no. Bored Pile P5 Construction | Fri Aug 23 08:00:00 IDT 2013 | Mon Sep 23 17:00:00 IDT 2013
2548 | 4th no. Bored Pile P2 Construction | Fri Sep 06 08:00:00 IDT 2013 | Tue Oct 08 17:00:00 IDT 2013
2549 | Pile Testing | Tue Jul 02 08:00:00 IDT 2013 | Wed Oct 02 17:00:00 IDT 2013
2550 | 5th no. Bored Pile P4 Construction | Sat Sep 28 08:00:00 IDT 2013 | Mon Oct 28 17:00:00 IST 2013
2551 | Bored Piles & Pile Testing | Mon Oct 28 08:00:00 IST 2013 | Thu May 01 17:00:00 IDT 2014
2552 | Completion | Mon Dec 02 08:00:00 IST 2013 | Tue Dec 31 17:00:00 IST 2013
2553 | Prepare & Submit Draft As-built Drawings | Mon Dec 02 08:00:00 IST 2013 | Tue Dec 31 17:00:00 IST 2013
2554 | Prepare & Submit As-built Drawings | Mon Dec 02 08:00:00 IST 2013 | Tue Dec 31 17:00:00 IST 2013
2555 | Cost Centre J - Cut & Cover Tunnels At Hoi Ting Road Retrieval Shaft | Thu Nov 07 08:00:00 IST 2013 | Thu Aug 06 17:00:00 IDT 2015
2556 | Underground Drainage & Utilities | Mon Jul 07 08:00:00 IDT 2014 | Mon Sep 22 17:00:00 IDT 2014
2557 | IPS Milestones | Tue Apr 01 17:00:00 IDT 2014 | Thu Aug 06 17:00:00 IDT 2015
2558 | Complete Roof slab of Down track cut and cover tunnel | Tue Apr 01 17:00:00 IDT 2014 | Tue Apr 01 17:00:00 IDT 2014
2559 | Achieve Degree 1 completion for the Down track cut and cover tunnel | Thu May 15 17:00:00 IDT 2014 | Thu May 15 17:00:00 IDT 2014
2560 | Complete Roof slab of Up track cut and cover tunnel | Thu Feb 05 17:00:00 IST 2015 | Thu Feb 05 17:00:00 IST 2015
2561 | Achieve Degree 1 completion for the Up track cut and cover tunnel | Fri Mar 13 17:00:00 IST 2015 | Fri Mar 13 17:00:00 IST 2015
2562 | Complete backfill and reinstatement at Works Areas 12.2 and 13.48 | Thu Aug 06 17:00:00 IDT 2015 | Thu Aug 06 17:00:00 IDT 2015
2563 | Construction | Thu Nov 07 08:00:00 IST 2013 | Thu Aug 06 17:00:00 IDT 2015
2564 | Down Track Cut & Cover Tunnel | Thu Nov 07 08:00:00 IST 2013 | Thu May 22 17:00:00 IDT 2014
2565 | TBM (S630-1) Backup Removal D/T | Sun Nov 10 17:00:00 IST 2013 | Sun Nov 10 17:00:00 IST 2013
2566 | Mobilization and Site Preparation works | Thu Nov 07 08:00:00 IST 2013 | Sat Nov 30 17:00:00 IST 2013
2567 | Clear Backfilled B5 and Trim to Formation Level | Thu Nov 07 08:00:00 IST 2013 | Mon Nov 18 17:00:00 IST 2013
2568 | Drill holes for mass infill wall | Mon Nov 18 08:00:00 IST 2013 | Fri Nov 22 17:00:00 IST 2013
2569 | Construction of Mass Infill Wall | Sat Nov 23 08:00:00 IST 2013 | Fri Dec 13 17:00:00 IST 2013
2570 | Waterproofing to Interface of TBM Tunnel & 811A | Thu Dec 19 08:00:00 IST 2013 | Sat Dec 21 17:00:00 IST 2013
2571 | Construction of Base Slab | Tue Dec 24 08:00:00 IST 2013 | Tue Jan 14 17:00:00 IST 2014
2572 | Curing, CJ preparation & Dismantle base slab formwork | Sat Jan 25 08:00:00 IST 2014 | Thu Jan 30 17:00:00 IST 2014
2573 | Construction of Lower Portion Wall | Sat Jan 25 08:00:00 IST 2014 | Wed Feb 05 17:00:00 IST 2014
2574 | Curing, CJ preparation & Dismantle wall formwork | Fri Mar 07 08:00:00 IST 2014 | Wed Mar 12 17:00:00 IST 2014
2575 | Construction of Upper Portion Wall & Roof Slab | Fri Mar 07 08:00:00 IST 2014 | Sat Mar 29 17:00:00 IDT 2014
2576 | Curing for Upper Portion Wall & Roof Slab | Wed Apr 02 08:00:00 IDT 2014 | Tue Apr 15 17:00:00 IDT 2014
2577 | Dismantle falsework and formwork | Wed Apr 09 08:00:00 IDT 2014 | Mon Apr 14 17:00:00 IDT 2014
2578 | Construction of Walkway | Fri May 02 08:00:00 IDT 2014 | Thu May 22 17:00:00 IDT 2014
2579 | 811A C&C D/T- Degree 1 works | Wed Apr 09 08:00:00 IDT 2014 | Wed Apr 30 17:00:00 IDT 2014
2580 | Up Track Cut & Cover Tunnel | Wed Jul 02 08:00:00 IDT 2014 | Fri Mar 06 17:00:00 IST 2015
2581 | TBM (S630-1) & Backup Removal U/T | Wed Nov 19 17:00:00 IST 2014 | Wed Nov 19 17:00:00 IST 2014
2582 | Re-mobilization and Site Preparation works | Thu Nov 20 08:00:00 IST 2014 | Wed Nov 26 17:00:00 IST 2014
2583 | Clear Backfilled B5 and Trim to Formation Level | Wed Jul 02 08:00:00 IDT 2014 | Tue Jul 08 17:00:00 IDT 2014
2584 | Drill holes for mass infill wall | Thu Nov 27 08:00:00 IST 2014 | Tue Dec 02 17:00:00 IST 2014
2585 | Construction of Mass Infill Wall | Sat Jan 03 08:00:00 IST 2015 | Fri Jan 16 17:00:00 IST 2015
2586 | Waterproofing to Interface of TBM Tunnel & 811A | Wed Dec 17 08:00:00 IST 2014 | Fri Dec 19 17:00:00 IST 2014
2587 | Construction of Base Slab | Sat Dec 20 08:00:00 IST 2014 | Sat Jan 03 17:00:00 IST 2015
2588 | Curing, CJ preparation & Dismantle base slab formwork | Mon Jan 05 08:00:00 IST 2015 | Fri Jan 09 17:00:00 IST 2015
2589 | Construction of Lower Portion Wall | Fri Jan 09 08:00:00 IST 2015 | Thu Jan 15 17:00:00 IST 2015
2590 | Curing, CJ preparation & Dismantle wall formwork | Fri Jan 16 08:00:00 IST 2015 | Wed Jan 21 17:00:00 IST 2015
2591 | Construction of Upper Portion Wall & Roof Slab | Thu Jan 22 08:00:00 IST 2015 | Fri Feb 13 17:00:00 IST 2015
2592 | Curing for Upper Portion Wall & Roof Slab | Sat Jan 31 08:00:00 IST 2015 | Wed Feb 11 17:00:00 IST 2015
2593 | Dismantle falsework and formwork | Fri Feb 06 08:00:00 IST 2015 | Tue Feb 10 17:00:00 IST 2015
2594 | Construction of Walkway | Wed Feb 11 08:00:00 IST 2015 | Mon Mar 02 17:00:00 IST 2015
2595 | 811A C&C U/T- Degree 1 works (Target: 25Jan15) | Mon Feb 16 08:00:00 IST 2015 | Fri Mar 06 17:00:00 IST 2015
2596 | Backfilling & Re-instatement | Wed Mar 25 08:00:00 IST 2015 | Thu Aug 06 17:00:00 IDT 2015
2597 | D/T & U/T: Second Cast Concrete | Tue Jun 16 08:00:00 IDT 2015 | Wed Jul 08 17:00:00 IDT 2015
2598 | Backfilling to +4.5mPD | Wed Mar 25 08:00:00 IST 2015 | Sat May 16 17:00:00 IDT 2015
2599 | Re-instatement and Make Good | Sat Jul 25 08:00:00 IDT 2015 | Thu Aug 06 17:00:00 IDT 2015
2600 | Injection of PU grouting at the interface of TBM & C&C tunnel (both D/T & U/T) | Sat Jul 25 08:00:00 IDT 2015 | Thu Aug 06 17:00:00 IDT 2015
2601 | Backfilling from +4.5mPD to Ground Level | Thu Jul 09 08:00:00 IDT 2015 | Fri Jul 24 17:00:00 IDT 2015